| R16 | OH | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-12 | -226 | -163 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-15 | 2023-08-16 | 2023-10-27 | IOU Designed & Installed | N/A | No | N/A | 10333.24 | 745.16 | Unknown | 1996.76 | Unknown | 7591.32 | 3981 | 963.19 | 10333.24 | -9370.05 | Yes | N/A | N/A | 2023-08-15 | 2023-08-16 | 2 | 2 | 2023-08-16 | 2023-08-16 | 1 | 1 | 2023-08-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-16 | 2023-10-27 | 73 | 53 | Unknown | Unknown | Unknown | Unknown | 2023-10-27 | 2023-10-30 | 4 | 2 | 2023-10-30 | 2023-10-30 | 1 | 1 | 75 | 55 | 6 | 4 | 81 | 59 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-11 | -348 | -249 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-03 | 2024-05-08 | 2024-11-27 | IOU Designed & Installed | N/A | No | N/A | 11039.76 | 2128.42 | Unknown | 332.21 | 19.12 | 8560.01 | 3981 | 1115.88 | 11039.76 | -9923.88 | Yes | N/A | N/A | 2024-05-03 | 2024-06-04 | 33 | 23 | 2024-06-04 | 2024-06-13 | 10 | 8 | 2024-06-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-25 | 2024-11-27 | 156 | 112 | Unknown | 2025-01-07 | Unknown | Unknown | 2024-11-27 | 2025-01-28 | 63 | 45 | 2025-01-28 | 2025-01-28 | 1 | 1 | 189 | 135 | 74 | 54 | 263 | 189 | Steps 2,3,5,6,7 | 41 | 29 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | N/A | 67.05 | 67.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-04-30 | 150 | 108 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-24 | 2023-04-19 | 2023-09-26 | IOU Designed & Installed | N/A | No | N/A | -2.8 | -5.48 | Unknown | Unknown | Unknown | 2.68 | 3981 | 357.5 | -2.8 | 360.3 | Yes | N/A | N/A | 2023-02-24 | 2023-08-08 | 166 | 118 | 2023-08-08 | 2023-08-08 | 1 | 1 | 2023-08-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-08 | 2023-09-26 | 50 | 36 | Unknown | 2023-08-19 | Unknown | Unknown | 2023-09-26 | 2023-09-28 | 3 | 3 | 2023-09-28 | 2023-09-27 | Unknown | Unknown | 216 | 154 | 4 | 4 | 220 | 158 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | Applicant Design | Residential | N/A | San Diego | San Diego | 236.25 | 236.25 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-05-01 | 291 | 210 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-31 | 2022-10-31 | 2023-10-25 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 21149.59 | 441.88 | Unknown | Unknown | 322.79 | 20384.92 | 19905 | 13465 | 21149.59 | -7684.59 | Yes | N/A | N/A | 2022-10-31 | 2023-02-01 | 94 | 68 | 2023-02-01 | Unknown | Unknown | Unknown | 2023-02-13 | 2023-06-22 | 35 | 26 | 2023-07-12 | 2023-08-18 | 14 | 10 | 2023-07-07 | 2023-10-25 | 111 | 79 | Unknown | 2024-11-21 | Unknown | Unknown | 2023-10-25 | 2024-02-16 | 115 | 83 | 2024-02-16 | 2024-02-16 | 1 | 1 | 240 | 173 | 130 | 94 | 370 | 267 | Steps 2,3,5,6,7 | 435 | 311 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 62 | 62 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-22 | -800 | -573 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-27 | 2023-03-20 | Unknown | IOU Designed & Installed | N/A | No | N/A | 117.03 | -22.55 | Unknown | Unknown | -725 | 864.58 | Unknown | 725.07 | 117.03 | 608.04 | Yes | N/A | N/A | 2023-02-27 | 2023-03-21 | 23 | 17 | 2023-03-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-14 | Unknown | Unknown | 2023-08-14 | 2023-08-14 | 1 | 1 | 23 | 17 | 1 | 1 | 24 | 18 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 357.1 | 357.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-02 | 717 | 512 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-01 | 2025-05-01 | 2025-05-12 | IOU Designed & Installed | N/A | No | N/A | 401.85 | -8.08 | Unknown | Unknown | Unknown | 409.93 | Unknown | 1231.31 | 401.85 | 829.46 | Yes | N/A | N/A | 2025-05-01 | 2025-04-30 | Unknown | Unknown | 2025-04-30 | 2025-05-01 | 2 | 2 | 2025-05-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-01 | 2025-05-12 | 12 | 8 | Unknown | Unknown | Unknown | Unknown | 2025-05-12 | 2025-05-19 | 8 | 6 | 2025-05-19 | 2025-05-19 | 1 | 1 | 12 | 8 | 11 | 9 | 23 | 17 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 81.05 | 81.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-21 | -104 | -75 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-21 | 2023-11-16 | Unknown | IOU Designed & Installed | N/A | No | N/A | 58.97 | -16.7 | Unknown | Unknown | 0.56 | 75.11 | 7962 | 1240.15 | 58.97 | 1181.18 | Yes | N/A | N/A | 2023-03-21 | 2023-06-09 | 81 | 59 | 2023-06-09 | 2023-11-22 | 167 | 119 | Unknown | Unknown | Unknown | Unknown | 2024-01-03 | Unknown | Unknown | Unknown | 2023-11-22 | 2023-11-27 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-04 | Unknown | Unknown | 2024-03-04 | 2024-01-08 | Unknown | Unknown | 87 | 63 | 167 | 119 | 254 | 182 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | N/A | 101.05 | 101.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-05 | -478 | -343 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-26 | 2024-09-26 | 2024-11-08 | IOU Designed & Installed | N/A | No | N/A | 1033.38 | Unknown | Unknown | Unknown | Unknown | 1033.38 | 3981 | 1121.39 | 1033.38 | 88.01 | Yes | N/A | N/A | 2024-09-26 | 2024-06-07 | Unknown | Unknown | 2024-06-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-26 | 2024-11-08 | 44 | 32 | Unknown | 2024-11-04 | Unknown | Unknown | 2024-11-08 | 2024-11-13 | 6 | 4 | 2024-11-13 | 2024-11-12 | Unknown | Unknown | 44 | 32 | 6 | 4 | 50 | 36 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R29/R45 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-29 | 206 | 147 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-06 | 2023-12-14 | 2025-03-05 | IOU Designed & Installed | N/A | No | N/A | 144661.73 | 310.86 | Unknown | Unknown | 1988.01 | 142362.86 | 0 | 102975.58 | 144661.73 | -41686.15 | Yes | N/A | N/A | 2023-09-06 | 2024-04-09 | 217 | 155 | 2024-04-09 | 2024-10-31 | 206 | 148 | 2024-06-13 | 2024-09-17 | 73 | 53 | 2024-09-30 | 2024-10-10 | 11 | 9 | 2024-10-31 | 2025-06-20 | 233 | 167 | 2025-03-19 | 2025-05-15 | 58 | 42 | 2025-03-05 | 2025-06-23 | 111 | 79 | 2025-06-23 | 2025-06-23 | 1 | 1 | 523 | 375 | 387 | 279 | 910 | 654 | Steps 2,3,5,6,7 | 304 | 218 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 52.4 | 52.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-24 | -678 | -485 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-30 | 2024-07-30 | 2024-07-30 | IOU Designed & Installed | N/A | No | N/A | 515.04 | -10.2 | Unknown | Unknown | Unknown | 525.24 | 3981 | 1967.77 | 515.04 | 1452.73 | Yes | N/A | N/A | 2024-07-30 | 2024-07-05 | Unknown | Unknown | 2024-07-05 | 2024-07-30 | 26 | 18 | 2024-07-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-30 | 2024-07-30 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-07-30 | 2024-08-12 | 14 | 10 | 2024-08-12 | 2024-08-15 | 4 | 4 | 1 | 1 | 44 | 32 | 45 | 33 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 134.05 | 134.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-18 | -437 | -314 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-23 | 2024-06-13 | 2024-08-05 | IOU Designed & Installed | N/A | No | N/A | 34.52 | Unknown | Unknown | Unknown | Unknown | 34.52 | 3981 | 1573.25 | 34.52 | 1538.73 | Yes | N/A | N/A | 2024-04-23 | 2024-01-04 | Unknown | Unknown | 2024-01-04 | 2024-05-21 | 139 | 99 | 2024-05-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-13 | 2024-08-05 | 54 | 38 | Unknown | 2024-09-18 | Unknown | Unknown | 2024-08-05 | 2024-10-07 | 64 | 46 | 2024-10-07 | 2024-10-07 | 1 | 1 | 54 | 38 | 204 | 146 | 258 | 184 | Steps 2,3,5,6,7 | 44 | 32 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | Oceanside | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-24 | 419 | 300 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-04 | 2025-04-04 | 2025-05-20 | IOU Designed & Installed | N/A | No | N/A | 27363.94 | 11582.8 | Unknown | Unknown | 119.59 | 15661.55 | Unknown | 33285.33 | 27363.94 | 5921.39 | Yes | N/A | N/A | 2025-04-04 | 2025-04-02 | Unknown | Unknown | 2025-04-02 | 2025-05-12 | 41 | 29 | Unknown | Unknown | Unknown | Unknown | 2025-05-12 | Unknown | Unknown | Unknown | 2025-05-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-20 | 2025-06-17 | 29 | 21 | 2025-06-17 | 2025-06-17 | 1 | 1 | 0 | 0 | 71 | 51 | 71 | 51 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-09 | -646 | -463 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-05 | 2024-08-05 | 2024-09-25 | IOU Designed & Installed | N/A | No | N/A | 45.18 | -0.31 | Unknown | Unknown | Unknown | 45.49 | 3981 | 1504.62 | 45.18 | 1459.44 | Yes | N/A | N/A | 2024-08-05 | 2024-08-05 | 1 | 1 | 2024-08-05 | 2024-08-05 | 1 | 1 | 2024-08-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-05 | 2024-09-25 | 52 | 38 | Unknown | Unknown | Unknown | Unknown | 2024-09-25 | 2024-10-01 | 7 | 5 | 2024-10-01 | 2024-10-01 | 1 | 1 | 53 | 39 | 9 | 7 | 62 | 46 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-07-08 | 328 | 235 | No | 2023-10-09 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-09 | 2023-10-09 | 2024-04-22 | IOU Designed & Installed | N/A | Yes | 204 | 1044.34 | -49.36 | Unknown | Unknown | Unknown | 1093.7 | 7962 | 1237.94 | 1044.34 | 193.6 | Yes | N/A | N/A | 2023-10-09 | 2024-04-30 | 205 | 147 | 2024-04-30 | 2023-10-09 | Unknown | Unknown | 2023-10-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-09 | 2024-04-22 | 197 | 141 | Unknown | Unknown | Unknown | Unknown | 2024-04-22 | 2024-05-24 | 33 | 25 | 2024-05-24 | 2024-05-31 | 8 | 6 | 402 | 288 | 41 | 31 | 443 | 319 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-19 | -519 | -372 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-08 | 2023-11-08 | 2024-01-09 | IOU Designed & Installed | N/A | No | N/A | 329.93 | 193.22 | Unknown | Unknown | Unknown | 136.71 | Unknown | 513.31 | 329.93 | 183.38 | Yes | N/A | N/A | 2023-11-08 | 2023-11-08 | 1 | 1 | 2023-11-08 | 2023-11-08 | 1 | 1 | 2023-11-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-08 | 2024-01-09 | 63 | 45 | Unknown | Unknown | Unknown | Unknown | 2024-01-09 | 2024-01-17 | 9 | 7 | 2024-01-17 | 2024-01-17 | 1 | 1 | 64 | 46 | 11 | 9 | 75 | 55 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2025-04-23 | 19 | 14 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-04 | 2025-03-04 | 2025-05-12 | IOU Designed & Installed | N/A | No | N/A | 3085.92 | 1140.85 | Unknown | 626.98 | Unknown | 1318.09 | Unknown | 265.75 | 3085.92 | -2820.17 | Yes | N/A | N/A | 2025-03-04 | 2025-03-04 | 1 | 1 | 2025-03-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-07 | 2025-03-19 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-12 | 2025-05-12 | 1 | 1 | 2025-05-12 | 2025-05-12 | 1 | 1 | 1 | 1 | 15 | 11 | 16 | 12 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | 183.45 | 183.45 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-31 | 125 | 90 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-21 | 2024-06-12 | 2025-03-26 | IOU Designed & Installed | N/A | No | N/A | 100553.1 | 23588.11 | Unknown | Unknown | 216.44 | 76748.55 | 0 | 40133.43 | 100553.1 | -60419.67 | Yes | N/A | N/A | 2024-05-21 | 2024-04-26 | Unknown | Unknown | 2024-04-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-29 | 2025-03-17 | 26 | 18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-26 | 2025-05-05 | 41 | 29 | 2025-05-05 | 2025-05-05 | 1 | 1 | 0 | 0 | 68 | 48 | 68 | 48 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-16 | -165 | -119 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-04 | 2023-08-19 | 2023-08-25 | IOU Designed & Installed | N/A | No | N/A | -7.73 | -5.61 | Unknown | Unknown | Unknown | -2.12 | Unknown | 496.37 | -7.73 | 504.1 | Yes | N/A | N/A | 2023-08-04 | 2023-08-19 | 16 | 11 | 2023-08-19 | 2023-08-19 | 1 | 0 | 2023-08-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-19 | 2023-08-25 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2023-08-25 | 2023-10-03 | 40 | 28 | 2023-10-03 | 2023-10-03 | 1 | 1 | 23 | 16 | 42 | 29 | 65 | 45 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-04-01 | 386 | 275 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-08 | 2023-02-10 | 2024-03-06 | IOU Designed & Installed | N/A | No | N/A | 28.72 | -25.53 | Unknown | Unknown | Unknown | 54.25 | 0 | 1060.61 | 28.72 | 1031.89 | Yes | N/A | N/A | 2023-02-08 | 2023-02-10 | 3 | 3 | 2023-02-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-10 | 2024-03-06 | 391 | 279 | Unknown | Unknown | Unknown | Unknown | 2024-03-06 | 2024-04-22 | 48 | 34 | 2024-04-22 | 2024-04-21 | Unknown | Unknown | 394 | 282 | 48 | 34 | 442 | 316 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-14 | -565 | -405 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-23 | 2024-04-25 | Unknown | IOU Designed & Installed | N/A | No | N/A | 90.01 | -1.26 | Unknown | Unknown | Unknown | 91.27 | Unknown | 1424.36 | 90.01 | 1334.35 | Yes | N/A | N/A | 2024-04-23 | 2024-03-19 | Unknown | Unknown | 2024-03-19 | 2024-06-10 | 84 | 60 | 2024-06-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-26 | Unknown | Unknown | 2024-08-26 | 2024-08-26 | 1 | 1 | 0 | 0 | 85 | 61 | 85 | 61 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SANTEE | N/A | 23 | 23 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-16 | -307 | -220 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-29 | 2024-04-29 | 2025-04-07 | IOU Designed & Installed | N/A | No | N/A | 501.63 | Unknown | Unknown | Unknown | 16.71 | 484.92 | 3981 | 1227.6 | 501.63 | 725.97 | Yes | N/A | N/A | 2024-04-29 | 2024-03-18 | Unknown | Unknown | 2024-03-18 | 2024-05-21 | 65 | 47 | 2024-05-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-21 | 2025-04-07 | 322 | 230 | Unknown | 2025-04-07 | Unknown | Unknown | 2025-04-07 | 2025-05-13 | 37 | 27 | 2025-05-13 | 2025-05-13 | 1 | 1 | 322 | 230 | 103 | 75 | 425 | 305 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-14 | 628 | 449 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-23 | 2024-04-24 | 2025-05-13 | IOU Designed & Installed | N/A | No | N/A | 7169.65 | -30.64 | Unknown | Unknown | 461.95 | 6738.34 | 0 | 4364.96 | 7169.65 | -2804.69 | Yes | N/A | N/A | 2024-04-23 | 2024-04-24 | 2 | 2 | 2024-04-24 | 2024-05-29 | 36 | 26 | Unknown | Unknown | Unknown | Unknown | 2024-05-02 | 2024-06-03 | 33 | 23 | 2024-05-29 | 2025-03-11 | 287 | 205 | Unknown | 2025-03-19 | Unknown | Unknown | 2025-05-13 | 2025-07-09 | 58 | 42 | 2025-07-09 | 2025-06-03 | Unknown | Unknown | 289 | 207 | 127 | 91 | 416 | 298 | Steps 2,3,5,6,7 | 5 | 3 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SANTEE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-30 | -693 | -496 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-08 | 2025-01-08 | 2025-01-15 | IOU Designed & Installed | N/A | No | N/A | 97.79 | -1.5 | Unknown | Unknown | Unknown | 99.29 | 3981 | 1561.94 | 97.79 | 1464.15 | Yes | N/A | N/A | 2025-01-08 | 2025-01-08 | 1 | 1 | 2025-01-08 | 2025-01-08 | 1 | 1 | 2025-01-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-08 | 2025-01-15 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2025-01-15 | 2025-02-05 | 22 | 16 | 2025-02-05 | 2025-02-05 | 1 | 1 | 9 | 7 | 24 | 18 | 33 | 25 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | Applicant Design | Commercial | Disadvantaged Community,Underserved Community | EL CAJON | EL CAJON | 4 | 4 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-04 | -30 | -23 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-31 | 2023-01-31 | 2025-04-23 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 12308.87 | 1039.01 | Unknown | Unknown | -7739.31 | 19009.17 | 432215 | 66337.95 | 12308.87 | 54029.08 | Yes | N/A | N/A | 2023-01-31 | 2024-09-10 | 589 | 421 | 2024-09-10 | 2025-01-14 | 127 | 91 | 2024-07-26 | 2024-09-25 | 6 | 4 | 2024-06-07 | 2025-04-24 | 113 | 83 | 2025-01-14 | Unknown | Unknown | Unknown | 2025-01-17 | 2025-04-07 | 81 | 57 | 2025-04-23 | 2025-05-05 | 13 | 9 | 2025-05-05 | 2025-05-05 | 1 | 1 | 595 | 425 | 335 | 241 | 930 | 666 | Steps 2,3,5,6,7 | 382 | 272 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2024-03-01 | 244 | 175 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-09 | 2023-01-09 | Unknown | IOU Designed & Installed | N/A | No | N/A | 133.51 | Unknown | Unknown | Unknown | -284.59 | 418.1 | 0 | 237.89 | 133.51 | 104.38 | Yes | N/A | N/A | 2023-01-09 | 2023-12-13 | 339 | 243 | 2023-12-13 | 2024-03-08 | 87 | 63 | Unknown | Unknown | Unknown | Unknown | 2023-12-11 | 2023-12-12 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-17 | Unknown | Unknown | Unknown | 2024-11-01 | Unknown | Unknown | 2024-11-01 | 2024-10-31 | Unknown | Unknown | 339 | 243 | 89 | 65 | 428 | 308 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 45.05 | 45.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-31 | -404 | -289 | No | 2024-10-02 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-02 | 2024-10-02 | 2025-04-14 | IOU Designed & Installed | N/A | Yes | 182 | 1397.73 | Unknown | Unknown | Unknown | 14.15 | 1383.58 | 3981 | 1413.98 | 1397.73 | 16.25 | Yes | N/A | N/A | 2024-10-02 | 2025-03-31 | 181 | 129 | 2025-03-31 | 2024-10-18 | Unknown | Unknown | 2024-10-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-18 | 2025-04-14 | 179 | 127 | Unknown | 2025-04-14 | Unknown | Unknown | 2025-04-14 | 2025-04-23 | 10 | 8 | 2025-04-23 | 2025-04-22 | Unknown | Unknown | 360 | 256 | 10 | 8 | 370 | 264 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-17 | -265 | -190 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-18 | 2023-06-08 | 2023-06-22 | IOU Designed & Installed | N/A | No | N/A | -4.91 | -3.57 | Unknown | Unknown | Unknown | -1.34 | Unknown | 495.75 | -4.91 | 500.66 | Yes | N/A | N/A | 2023-05-18 | 2023-06-08 | 22 | 16 | 2023-06-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-08 | 2023-06-22 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2023-06-22 | 2023-06-26 | 5 | 3 | 2023-06-26 | 2023-06-26 | 1 | 1 | 37 | 27 | 6 | 4 | 43 | 31 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | CORONADO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-11 | -564 | -403 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-21 | 2024-05-20 | 2024-06-06 | IOU Designed & Installed | N/A | No | N/A | 10.72 | -9.53 | Unknown | Unknown | Unknown | 20.25 | Unknown | 1129.27 | 10.72 | 1118.55 | Yes | N/A | N/A | 2024-03-21 | 2024-05-13 | 54 | 38 | 2024-05-13 | 2024-05-20 | 8 | 6 | 2024-05-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-20 | 2024-06-06 | 18 | 14 | Unknown | Unknown | Unknown | Unknown | 2024-06-06 | 2024-06-26 | 21 | 15 | 2024-06-26 | 2024-06-26 | 1 | 1 | 72 | 52 | 30 | 22 | 102 | 74 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 498 | 498 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-31 | -321 | -230 | No | 2022-01-26 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-01-26 | 2022-01-26 | Unknown | IOU Designed & Installed | N/A | Yes | 660 | 6.73 | -8.12 | Unknown | Unknown | Unknown | 14.85 | 3981 | 885.23 | 6.73 | 878.5 | Yes | N/A | N/A | 2022-01-26 | 2023-11-09 | 653 | 467 | 2023-11-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2022-01-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-28 | Unknown | Unknown | 2024-02-28 | 2024-02-14 | Unknown | Unknown | 653 | 467 | 0 | 0 | 653 | 467 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | EL CAJON | EL CAJON | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-07 | 24 | 19 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-28 | 2024-04-25 | 2025-01-29 | IOU Designed & Installed | N/A | No | N/A | 6813.98 | 1794.85 | Unknown | 179.31 | Unknown | 4839.82 | 11361 | 1912.62 | 6813.98 | -4901.36 | Yes | N/A | N/A | 2024-03-28 | 2024-02-29 | Unknown | Unknown | 2024-02-29 | 2024-12-05 | 281 | 201 | Unknown | Unknown | Unknown | Unknown | 2024-12-06 | 2025-01-13 | 39 | 27 | 2024-12-05 | 2024-11-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-29 | 2025-01-29 | 1 | 1 | 2025-01-29 | 2025-01-31 | 3 | 3 | 0 | 0 | 324 | 232 | 324 | 232 | Steps 2,3,5,6,7 | 39 | 27 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 112.05 | 112.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-22 | -282 | -203 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-26 | 2024-05-01 | Unknown | IOU Designed & Installed | N/A | No | N/A | 3390.38 | 638.74 | Unknown | 179.71 | 60.59 | 2511.34 | 7962 | 765.77 | 3390.38 | -2624.61 | Yes | N/A | N/A | 2024-04-26 | 2024-05-10 | 15 | 11 | 2024-05-10 | 2024-05-17 | 8 | 6 | 2024-05-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-17 | Unknown | Unknown | Unknown | Unknown | 2025-03-20 | Unknown | Unknown | Unknown | 2025-04-26 | Unknown | Unknown | 2025-04-26 | 2025-04-15 | Unknown | Unknown | 15 | 11 | 8 | 6 | 23 | 17 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | LA JOLLA | N/A | 38 | 38 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-31 | -173 | -124 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-27 | 2023-04-28 | Unknown | IOU Designed & Installed | N/A | No | N/A | -6.35 | -4.61 | Unknown | Unknown | Unknown | -1.74 | 3981 | 464.78 | -6.35 | 471.13 | Yes | N/A | N/A | 2023-04-27 | 2023-04-27 | 1 | 1 | 2023-04-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-11 | Unknown | Unknown | 2023-07-11 | 2023-07-11 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN MARCOS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-09 | -202 | -145 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-14 | 2024-05-23 | 2024-06-07 | IOU Designed & Installed | N/A | No | N/A | 2649.94 | Unknown | Unknown | Unknown | Unknown | 2649.94 | Unknown | 2089.29 | 2649.94 | -560.65 | Yes | N/A | N/A | 2024-05-14 | 2024-05-08 | Unknown | Unknown | 2024-05-08 | 2024-06-04 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-07 | 2024-06-21 | 15 | 11 | 2024-06-21 | 2024-06-21 | 1 | 1 | 0 | 0 | 44 | 32 | 44 | 32 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 93 | 93 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-09 | -405 | -290 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-09 | 2023-11-14 | 2023-12-05 | IOU Designed & Installed | N/A | No | N/A | 1527.48 | 497.1 | Unknown | 58.16 | Unknown | 972.22 | 3981 | 949.93 | 1527.48 | -577.55 | Yes | N/A | N/A | 2023-11-09 | 2023-11-14 | 6 | 4 | 2023-11-14 | 2023-11-14 | 1 | 1 | 2023-11-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-14 | 2023-12-05 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | 2023-12-05 | 2024-01-29 | 56 | 40 | 2024-01-29 | 2024-01-29 | 1 | 1 | 28 | 20 | 58 | 42 | 86 | 62 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| Combo (R15 & R16) | Both | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 1218.25 | 1218.25 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2025-09-08 | -620 | -443 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-03 | 2023-10-03 | 2023-12-15 | IOU Designed & Installed | N/A | No | N/A | 1576.95 | 986.37 | Unknown | Unknown | -4930 | 5520.58 | 3981 | 13422.6 | 1576.95 | 11845.65 | Yes | N/A | N/A | 2023-07-03 | 2023-08-23 | 52 | 38 | 2023-08-23 | 2023-10-03 | 42 | 30 | 2023-10-03 | 2023-10-16 | 14 | 10 | 2023-11-10 | 2023-11-14 | 5 | 3 | 2023-10-16 | 2023-12-15 | 61 | 45 | Unknown | 2023-11-07 | Unknown | Unknown | 2023-12-15 | 2023-12-28 | 14 | 10 | 2023-12-28 | 2023-12-28 | 1 | 1 | 127 | 93 | 62 | 44 | 189 | 137 | Steps 2,3,5,6,7 | 29 | 21 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-11 | -428 | -307 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-04 | 2024-01-04 | 2024-06-20 | IOU Designed & Installed | N/A | No | N/A | 570.92 | -11.39 | Unknown | Unknown | -762.79 | 1345.1 | Unknown | 778.08 | 570.92 | 207.16 | Yes | N/A | N/A | 2024-01-04 | 2023-09-22 | Unknown | Unknown | 2023-09-22 | 2024-01-19 | 120 | 86 | 2024-01-19 | 2024-03-13 | 55 | 39 | Unknown | Unknown | Unknown | Unknown | 2024-03-22 | 2024-06-20 | 91 | 65 | Unknown | 2024-06-11 | Unknown | Unknown | 2024-06-20 | 2024-07-10 | 21 | 15 | 2024-07-10 | 2024-07-10 | 1 | 1 | 146 | 104 | 142 | 102 | 288 | 206 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | 82.05 | 82.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-17 | -261 | -188 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-28 | 2024-02-28 | 2024-10-15 | IOU Designed & Installed | N/A | No | N/A | 10799.25 | 39.3 | Unknown | Unknown | 1.14 | 10758.81 | 3981 | 1112.74 | 10799.25 | -9686.51 | Yes | N/A | N/A | 2024-02-28 | 2023-10-30 | Unknown | Unknown | 2023-10-30 | 2024-03-25 | 148 | 106 | 2024-03-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-25 | 2024-10-15 | 205 | 147 | Unknown | 2024-09-25 | Unknown | Unknown | 2024-10-15 | 2024-11-05 | 22 | 16 | 2024-11-05 | 2024-10-29 | Unknown | Unknown | 205 | 147 | 170 | 122 | 375 | 269 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | 170.1 | 170.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-16 | -352 | -253 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-24 | 2024-05-09 | 2024-10-17 | IOU Designed & Installed | N/A | No | N/A | 33.99 | Unknown | Unknown | Unknown | Unknown | 33.99 | 7962 | 3621.63 | 33.99 | 3587.64 | Yes | N/A | N/A | 2023-08-24 | 2024-04-14 | 235 | 167 | 2024-04-14 | 2024-06-05 | 53 | 38 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-05 | 2024-10-10 | 128 | 92 | Unknown | Unknown | Unknown | Unknown | 2024-10-17 | 2024-10-30 | 14 | 10 | 2024-10-30 | 2024-10-29 | Unknown | Unknown | 363 | 259 | 67 | 48 | 430 | 307 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LAGUNA HILLS | N/A | 119.05 | 119.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-18 | -681 | -486 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-05 | 2024-11-05 | Unknown | IOU Designed & Installed | N/A | No | N/A | 2782.46 | -24.15 | Unknown | Unknown | 5.7 | 2800.91 | 3981 | 2048.81 | 2782.46 | -733.65 | Yes | N/A | N/A | 2024-11-05 | 2024-11-05 | 1 | 1 | 2024-11-05 | 2024-11-06 | 2 | 2 | 2024-11-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-06 | Unknown | Unknown | 2024-12-06 | 2024-12-06 | 1 | 1 | 1 | 1 | 3 | 3 | 4 | 4 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R29/R45 | UG | IOU Design | Commercial | Underserved Community | SAN JUAN CAPISTRANO | SAN JUAN CAPISTRANO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-18 | 1 | 2 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-28 | 2023-06-29 | 2024-01-11 | IOU Designed & Installed | N/A | No | N/A | 221252.76 | 34782.88 | Unknown | 1721.7 | 814.23 | 183933.95 | 0 | 117322.61 | 221252.76 | -103930.15 | Yes | N/A | N/A | 2023-02-28 | 2023-06-29 | 122 | 88 | 2023-06-29 | 2024-01-04 | 190 | 136 | 2023-08-15 | 2023-11-02 | 4 | 4 | 2023-04-27 | 2024-06-18 | 59 | 43 | 2024-01-04 | 2024-05-02 | 120 | 86 | Unknown | 2024-05-06 | Unknown | Unknown | 2024-01-11 | 2024-06-19 | 161 | 115 | 2024-06-19 | 2024-06-19 | 1 | 1 | 246 | 178 | 411 | 295 | 657 | 473 | Steps 2,3,5,6,7 | 613 | 437 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-26 | -468 | -335 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-28 | 2023-11-28 | 2024-02-02 | IOU Designed & Installed | N/A | No | N/A | 287.11 | -3.42 | Unknown | Unknown | Unknown | 290.53 | Unknown | 278.53 | 287.11 | -8.58 | Yes | N/A | N/A | 2023-11-28 | 2023-06-06 | Unknown | Unknown | 2023-06-06 | 2023-12-07 | 185 | 133 | 2023-12-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-07 | 2024-02-02 | 58 | 42 | Unknown | Unknown | Unknown | Unknown | 2024-02-02 | 2024-02-13 | 12 | 8 | 2024-02-13 | 2024-02-13 | 1 | 1 | 58 | 42 | 198 | 142 | 256 | 184 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 41.05 | 41.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-13 | -489 | -350 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-14 | 2023-09-14 | 2023-10-10 | IOU Designed & Installed | N/A | No | N/A | -8.45 | -6.64 | Unknown | Unknown | Unknown | -1.81 | 3241 | 480.37 | -8.45 | 488.82 | Yes | N/A | N/A | 2023-09-14 | 2023-09-14 | 1 | 1 | 2023-09-14 | 2023-09-14 | 1 | 1 | 2023-09-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-14 | 2023-10-10 | 27 | 19 | Unknown | Unknown | Unknown | Unknown | 2023-10-10 | 2023-10-13 | 4 | 4 | 2023-10-13 | 2023-10-13 | 1 | 1 | 28 | 20 | 6 | 6 | 34 | 26 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-11 | -536 | -385 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-02 | 2024-10-02 | 2025-02-14 | IOU Designed & Installed | N/A | No | N/A | 443.65 | Unknown | Unknown | Unknown | 10.21 | 433.44 | 3961 | 1370.92 | 443.65 | 927.27 | Yes | N/A | N/A | 2024-10-02 | 2024-10-25 | 24 | 18 | 2024-10-25 | 2024-10-25 | 1 | 1 | 2024-10-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-30 | 2025-02-14 | 108 | 78 | Unknown | Unknown | Unknown | Unknown | 2025-02-14 | 2025-03-24 | 39 | 27 | 2025-03-24 | 2025-03-24 | 1 | 1 | 132 | 96 | 41 | 29 | 173 | 125 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | Applicant Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2022-11-04 | 684 | 489 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-07 | 2024-05-07 | 2024-06-25 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | -20718.16 | 956.93 | Unknown | Unknown | -43708 | 22032.91 | Unknown | 29933.6 | -20718.16 | 50651.76 | Yes | N/A | N/A | 2024-05-07 | 2024-05-10 | 4 | 4 | 2024-05-10 | 2024-06-19 | 41 | 29 | 2024-05-16 | 2024-05-16 | 1 | 1 | 2024-05-17 | 2024-06-20 | 28 | 20 | 2024-06-21 | Unknown | Unknown | Unknown | 2024-06-21 | 2024-06-21 | 1 | 1 | 2024-06-25 | 2024-09-18 | 86 | 62 | 2024-09-18 | 2024-09-18 | 1 | 1 | 5 | 5 | 157 | 113 | 162 | 118 | Steps 2,3,5,6,7 | 34 | 24 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-26 | -614 | -439 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-09 | 2024-06-09 | 2024-08-19 | IOU Designed & Installed | N/A | No | N/A | 1192.92 | 345.98 | Unknown | 39.64 | Unknown | 807.3 | 3241 | 1516.79 | 1192.92 | 323.87 | Yes | N/A | N/A | 2024-06-09 | 2024-06-09 | 1 | 0 | 2024-06-09 | 2024-06-09 | 1 | 0 | 2024-06-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-09 | 2024-08-19 | 72 | 51 | Unknown | Unknown | Unknown | Unknown | 2024-08-19 | 2024-08-20 | 2 | 2 | 2024-08-20 | 2024-08-20 | 1 | 1 | 73 | 51 | 4 | 3 | 77 | 54 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 68 | 68 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-31 | 435 | 311 | No | 2024-01-17 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-17 | 2024-01-17 | Unknown | IOU Designed & Installed | N/A | Yes | 2 | 35.1 | Unknown | Unknown | Unknown | Unknown | 35.1 | 3961 | 845.05 | 35.1 | 809.95 | Yes | N/A | N/A | 2024-01-17 | 2024-01-09 | Unknown | Unknown | 2024-01-09 | 2024-01-19 | 11 | 9 | 2024-01-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-19 | Unknown | Unknown | Unknown | Unknown | 2024-12-02 | Unknown | Unknown | Unknown | 2025-03-24 | Unknown | Unknown | 2025-03-24 | 2025-03-10 | Unknown | Unknown | 0 | 0 | 11 | 9 | 11 | 9 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | ENCINITAS | N/A | 2608.05 | 2608.05 | Not Available | >2MW | No | N/A | N/A | N/A | 2027-03-19 | -639 | -458 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-09 | 2025-05-09 | 2025-05-22 | IOU Designed & Installed | N/A | No | N/A | 17367.35 | 7812.63 | Unknown | Unknown | Unknown | 9554.72 | Unknown | 3233.27 | 17367.35 | -14134.08 | Yes | N/A | N/A | 2025-05-09 | 2025-05-09 | 1 | 1 | 2025-05-09 | 2025-05-09 | 1 | 1 | 2025-05-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-16 | 2025-05-22 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2025-05-22 | 2025-06-18 | 28 | 20 | 2025-06-18 | 2025-06-18 | 1 | 1 | 8 | 6 | 30 | 22 | 38 | 28 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-27 | -588 | -421 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-21 | 2025-03-21 | 2025-06-12 | IOU Designed & Installed | N/A | No | N/A | 898.17 | Unknown | Unknown | Unknown | 12.24 | 885.93 | 3981 | 1265.01 | 898.17 | 366.84 | Yes | N/A | N/A | 2025-03-21 | 2025-04-03 | 14 | 10 | 2025-04-03 | 2025-04-17 | 15 | 11 | 2025-04-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-17 | 2025-06-12 | 57 | 41 | Unknown | 2025-06-12 | Unknown | Unknown | 2025-06-12 | 2025-06-18 | 7 | 5 | 2025-06-18 | 2025-06-18 | 1 | 1 | 71 | 51 | 23 | 17 | 94 | 68 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-15 | -585 | -418 | No | 2024-03-27 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-27 | 2024-04-15 | 2024-06-14 | IOU Designed & Installed | N/A | Yes | 76 | -11.12 | -9.28 | Unknown | Unknown | Unknown | -1.84 | 3981 | 163.83 | -11.12 | 174.95 | Yes | N/A | N/A | 2024-03-27 | 2024-06-11 | 77 | 55 | 2024-06-11 | 2024-04-15 | Unknown | Unknown | 2024-04-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-15 | 2024-06-14 | 61 | 45 | Unknown | Unknown | Unknown | Unknown | 2024-06-14 | 2024-07-10 | 27 | 19 | 2024-07-10 | 2024-07-10 | 1 | 1 | 138 | 100 | 28 | 20 | 166 | 120 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-28 | -283 | -203 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-01 | 2023-06-01 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1010.92 | -27.44 | Unknown | Unknown | Unknown | 1038.36 | Unknown | 1754.03 | 1010.92 | 743.11 | Yes | N/A | N/A | 2023-06-01 | 2023-06-05 | 5 | 3 | 2023-06-05 | 2024-02-02 | 243 | 175 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-20 | Unknown | Unknown | 2024-03-20 | 2024-03-20 | 1 | 1 | 5 | 3 | 244 | 176 | 249 | 179 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | BONSALL | N/A | 107 | 107 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-07-01 | 669 | 478 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-19 | 2023-04-03 | Unknown | IOU Designed & Installed | N/A | No | N/A | -992.58 | -15.47 | Unknown | Unknown | -1010 | 32.89 | 3981 | 1543.03 | -992.58 | 2535.61 | Yes | N/A | N/A | 2023-03-19 | 2023-04-03 | 16 | 11 | 2023-04-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-15 | Unknown | Unknown | Unknown | Unknown | 2024-04-26 | Unknown | Unknown | Unknown | 2024-05-01 | Unknown | Unknown | 2024-05-01 | 2024-04-30 | Unknown | Unknown | 16 | 11 | 0 | 0 | 16 | 11 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | RANCHO MISSION VIEJO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2021-12-20 | 1225 | 876 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-12 | 2024-03-12 | Unknown | IOU Designed & Installed | N/A | No | N/A | 2011.72 | -4.28 | Unknown | Unknown | 12.76 | 2003.24 | 3981 | 577.85 | 2011.72 | -1433.87 | Yes | N/A | N/A | 2024-03-12 | 2024-03-12 | 1 | 1 | 2024-03-12 | 2024-03-12 | 1 | 1 | 2024-03-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-12 | Unknown | Unknown | Unknown | Unknown | 2025-03-25 | Unknown | Unknown | Unknown | 2025-04-28 | Unknown | Unknown | 2025-04-28 | 2025-04-28 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-24 | 0 | 1 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-07 | 2025-05-07 | 2025-06-23 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 344.44 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-07 | 2025-05-07 | 1 | 1 | 2025-05-07 | 2025-06-02 | 27 | 19 | Unknown | Unknown | Unknown | Unknown | 2025-05-08 | 2025-05-23 | 16 | 12 | 2025-06-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-23 | 2025-06-24 | 2 | 2 | 2025-06-24 | 2025-06-24 | 1 | 1 | 1 | 1 | 46 | 34 | 47 | 35 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-05 | -699 | -500 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-14 | Unknown | 2024-08-21 | IOU Designed & Installed | N/A | No | N/A | 29.05 | Unknown | Unknown | Unknown | Unknown | 29.05 | 3981 | 1589.99 | 29.05 | 1560.94 | Yes | N/A | N/A | 2024-08-14 | 2024-08-14 | 1 | 1 | 2024-08-14 | 2024-08-14 | 1 | 1 | 2024-08-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-14 | 2024-08-21 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2024-08-21 | 2024-09-05 | 16 | 12 | 2024-09-05 | 2024-09-05 | 1 | 1 | 9 | 7 | 18 | 14 | 27 | 21 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-16 | -560 | -401 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-10 | 2025-01-10 | 2025-05-29 | IOU Designed & Installed | N/A | No | N/A | 1070.13 | -8.27 | Unknown | Unknown | 18.71 | 1059.69 | 3981 | 1213.24 | 1070.13 | 143.11 | Yes | N/A | N/A | 2025-01-10 | 2025-01-02 | Unknown | Unknown | 2025-01-02 | 2025-02-03 | 33 | 23 | 2025-02-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-05 | 2025-05-29 | 114 | 82 | Unknown | 2025-03-27 | Unknown | Unknown | 2025-05-29 | 2025-06-04 | 7 | 5 | 2025-06-04 | 2025-06-04 | 1 | 1 | 114 | 82 | 41 | 29 | 155 | 111 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-04 | -211 | -152 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-16 | 2024-05-20 | Unknown | IOU Designed & Installed | N/A | No | N/A | 2004.38 | -12.92 | Unknown | Unknown | Unknown | 2017.3 | Unknown | 307.58 | 2004.38 | -1696.8 | Yes | N/A | N/A | 2024-05-16 | 2024-04-02 | Unknown | Unknown | 2024-04-02 | 2024-05-20 | 49 | 35 | 2024-05-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-05 | Unknown | Unknown | 2024-08-05 | 2024-08-05 | 1 | 1 | 0 | 0 | 50 | 36 | 50 | 36 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-22 | -331 | -237 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-27 | 2024-02-27 | 2024-03-25 | IOU Designed & Installed | N/A | No | N/A | 13.76 | -12.21 | Unknown | Unknown | Unknown | 25.97 | Unknown | 700.07 | 13.76 | 686.31 | Yes | N/A | N/A | 2024-02-27 | 2024-02-26 | Unknown | Unknown | 2024-02-26 | 2024-02-27 | 2 | 2 | 2024-02-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-27 | 2024-03-25 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | 2024-03-25 | 2024-03-28 | 4 | 4 | 2024-03-28 | 2024-03-28 | 1 | 1 | 28 | 20 | 7 | 7 | 35 | 27 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-24 | -217 | -156 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-22 | Unknown | 2023-06-15 | IOU Designed & Installed | N/A | No | N/A | 210.37 | -9.95 | Unknown | Unknown | Unknown | 220.32 | 3981 | 950.24 | 210.37 | 739.87 | Yes | N/A | N/A | 2023-05-22 | 2023-05-22 | 1 | 1 | 2023-05-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-22 | 2023-06-15 | 25 | 19 | Unknown | 2023-06-09 | Unknown | Unknown | 2023-06-15 | 2023-06-21 | 7 | 5 | 2023-06-21 | 2023-06-21 | 1 | 1 | 26 | 20 | 8 | 6 | 34 | 26 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-04 | 411 | 294 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-12 | 2024-06-07 | 2025-06-18 | IOU Designed & Installed | N/A | No | N/A | 1669.64 | 427.01 | Unknown | Unknown | Unknown | 1242.63 | 3981 | 1375.94 | 1669.64 | -293.7 | Yes | N/A | N/A | 2023-12-12 | 2024-06-07 | 179 | 129 | 2024-06-07 | 2024-06-07 | 1 | 1 | 2024-06-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-07 | 2025-06-18 | 377 | 269 | Unknown | Unknown | Unknown | Unknown | 2025-06-18 | 2025-06-19 | 2 | 2 | 2025-06-19 | 2025-06-19 | 1 | 1 | 556 | 398 | 4 | 4 | 560 | 402 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LEMON GROVE | N/A | 47.05 | 47.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-18 | 353 | 252 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-03 | 2024-05-31 | 2024-10-16 | IOU Designed & Installed | N/A | No | N/A | 10.53 | Unknown | Unknown | Unknown | Unknown | 10.53 | 3981 | 1543.33 | 10.53 | 1532.8 | Yes | N/A | N/A | 2024-01-03 | 2024-05-30 | 149 | 107 | 2024-05-30 | 2024-05-31 | 2 | 2 | 2024-05-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-31 | 2024-10-16 | 139 | 99 | Unknown | Unknown | Unknown | Unknown | 2024-10-16 | 2024-10-31 | 16 | 12 | 2024-10-31 | 2024-11-05 | 6 | 4 | 288 | 206 | 24 | 18 | 312 | 224 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | CARLSBAD | N/A | 70.1 | 70.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-30 | 348 | 249 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-07 | 2023-09-19 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1427.41 | Unknown | Unknown | Unknown | 21.07 | 1406.34 | 3981 | 734.46 | 1427.41 | -692.95 | Yes | N/A | N/A | 2023-09-07 | 2023-11-20 | 75 | 53 | 2023-11-20 | 2023-11-22 | 3 | 3 | 2023-11-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-22 | Unknown | Unknown | Unknown | Unknown | 2024-10-04 | Unknown | Unknown | Unknown | 2024-11-12 | Unknown | Unknown | 2024-11-12 | 2024-11-12 | 1 | 1 | 75 | 53 | 4 | 4 | 79 | 57 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-06 | -183 | -132 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-03 | 2023-05-03 | Unknown | IOU Designed & Installed | N/A | No | N/A | 123.3 | -14.27 | Unknown | Unknown | 1.52 | 136.05 | 3981 | 651.64 | 123.3 | 528.34 | Yes | N/A | N/A | 2023-05-03 | 2023-05-19 | 17 | 13 | 2023-05-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-05 | Unknown | Unknown | 2023-09-05 | 2023-09-05 | 1 | 1 | 17 | 13 | 1 | 1 | 18 | 14 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community,Tribal Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-01 | -201 | -145 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-08 | 2024-02-08 | Unknown | IOU Designed & Installed | N/A | No | N/A | 506.57 | 3200.8 | Unknown | 284.07 | -4454 | 1475.7 | Unknown | 4453.98 | 506.57 | 3947.41 | Yes | N/A | N/A | 2024-02-08 | 2024-02-28 | 21 | 15 | 2024-02-28 | 2024-02-28 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 21 | 15 | 2 | 2 | 23 | 17 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-31 | 216 | 155 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-24 | 2025-01-08 | Unknown | IOU Designed & Installed | N/A | No | N/A | 0.5 | Unknown | Unknown | Unknown | Unknown | 0.5 | 3981 | 242.9 | 0.5 | 242.4 | Yes | N/A | N/A | 2024-10-24 | 2024-11-18 | 26 | 18 | 2024-11-18 | 2025-01-16 | 60 | 44 | Unknown | Unknown | Unknown | Unknown | 2025-01-16 | 2025-02-05 | 21 | 15 | 2025-01-16 | 2025-03-04 | 48 | 34 | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-05 | Unknown | Unknown | 2025-03-05 | 2025-03-04 | Unknown | Unknown | 74 | 52 | 81 | 59 | 155 | 111 | Steps 2,3,5,6,7 | 20 | 14 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | EL CAJON | EL CAJON | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-05-15 | 351 | 252 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-24 | 2023-10-16 | 2024-04-18 | IOU Designed & Installed | N/A | No | N/A | 10325.76 | -65.87 | Unknown | Unknown | Unknown | 10391.63 | 149497 | 14756.66 | 10325.76 | 4430.9 | Yes | N/A | N/A | 2023-08-24 | 2023-10-16 | 54 | 38 | 2023-10-16 | 2023-12-18 | 64 | 46 | 2023-12-19 | 2024-01-26 | 14 | 12 | 2023-12-11 | 2024-03-25 | 96 | 68 | 2023-12-18 | 2024-04-04 | 109 | 79 | Unknown | 2024-04-15 | Unknown | Unknown | 2024-04-18 | 2024-05-07 | 20 | 14 | 2024-05-07 | 2024-04-30 | Unknown | Unknown | 177 | 129 | 180 | 128 | 357 | 257 | Steps 2,3,5,6,7 | 144 | 104 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LEMON GROVE | N/A | 3.35 | 3.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-21 | 181 | 130 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-26 | 2024-08-21 | 2024-09-11 | IOU Designed & Installed | N/A | No | N/A | 22.95 | Unknown | Unknown | Unknown | Unknown | 22.95 | 3241 | 1519.24 | 22.95 | 1496.29 | Yes | N/A | N/A | 2024-06-26 | 2024-08-21 | 57 | 41 | 2024-08-21 | 2024-08-21 | 1 | 1 | 2024-08-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-22 | 2024-09-11 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | 2024-09-11 | 2024-09-18 | 8 | 6 | 2024-09-18 | 2024-09-18 | 1 | 1 | 78 | 56 | 10 | 8 | 88 | 64 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 603 | 603 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-07-14 | 622 | 445 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-02 | 2022-08-03 | 2024-03-26 | IOU Designed & Installed | N/A | No | N/A | 910.55 | 126.23 | Unknown | 18.3 | 9.16 | 756.86 | 3981 | 798.58 | 910.55 | -111.97 | Yes | N/A | N/A | 2022-08-02 | 2023-06-20 | 323 | 231 | 2023-06-20 | 2023-06-20 | 1 | 1 | 2023-06-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-20 | 2024-03-26 | 281 | 201 | Unknown | 2024-02-13 | Unknown | Unknown | 2024-03-26 | 2024-03-27 | 2 | 2 | 2024-03-27 | 2024-03-27 | 1 | 1 | 604 | 432 | 4 | 4 | 608 | 436 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 10.05 | 10.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-17 | -516 | -370 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-18 | 2025-05-06 | 2025-05-14 | IOU Designed & Installed | N/A | No | N/A | 450.27 | -9.05 | Unknown | Unknown | Unknown | 459.32 | 3981 | 1558.68 | 450.27 | 1108.41 | Yes | N/A | N/A | 2024-12-18 | 2025-04-30 | 134 | 96 | 2025-04-30 | 2025-04-09 | Unknown | Unknown | 2025-04-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-06 | 2025-05-14 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | 2025-05-14 | 2025-05-19 | 6 | 4 | 2025-05-19 | 2025-05-19 | 1 | 1 | 143 | 103 | 7 | 5 | 150 | 108 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-26 | -667 | -476 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-27 | 2024-08-27 | 2024-09-18 | IOU Designed & Installed | N/A | No | N/A | 64.11 | Unknown | Unknown | Unknown | Unknown | 64.11 | 3941 | 1411.09 | 64.11 | 1346.98 | Yes | N/A | N/A | 2024-08-27 | 2024-08-01 | Unknown | Unknown | 2024-08-01 | 2024-08-27 | 27 | 19 | 2024-08-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-27 | 2024-09-18 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | 2024-09-18 | 2024-09-27 | 10 | 8 | 2024-09-27 | 2024-09-27 | 1 | 1 | 23 | 17 | 38 | 28 | 61 | 45 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-06 | -589 | -422 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-10 | 2024-04-25 | 2024-05-07 | IOU Designed & Installed | N/A | No | N/A | -8.63 | -7 | Unknown | Unknown | Unknown | -1.63 | Unknown | 998.32 | -8.63 | 1006.95 | Yes | N/A | N/A | 2024-04-10 | 2024-04-25 | 16 | 12 | 2024-04-25 | 2025-03-06 | 316 | 226 | 2025-03-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-25 | 2024-05-07 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2024-05-07 | 2024-06-27 | 52 | 38 | 2024-06-27 | 2024-06-27 | 1 | 1 | 29 | 21 | 369 | 265 | 398 | 286 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 316.15 | 316.15 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-05 | -342 | -245 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-14 | 2023-08-14 | 2024-01-25 | IOU Designed & Installed | N/A | No | N/A | 720.81 | -7.91 | Unknown | Unknown | 6.75 | 721.97 | 3961 | 1043.56 | 720.81 | 322.75 | Yes | N/A | N/A | 2023-08-14 | 2023-06-05 | Unknown | Unknown | 2023-06-05 | 2023-10-11 | 129 | 93 | 2023-10-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-11 | 2024-01-25 | 107 | 77 | Unknown | 2024-01-05 | Unknown | Unknown | 2024-01-25 | 2024-01-29 | 5 | 3 | 2024-01-29 | 2024-01-29 | 1 | 1 | 107 | 77 | 135 | 97 | 242 | 174 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | BONSALL | N/A | 142 | 142 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-08 | -88 | -65 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-03 | 2023-11-03 | 2025-04-17 | IOU Designed & Installed | N/A | No | N/A | 4776.78 | 2134.3 | Unknown | Unknown | 11.18 | 2631.3 | 3981 | 954.03 | 4776.78 | -3822.75 | Yes | N/A | N/A | 2023-11-03 | 2024-02-14 | 104 | 74 | 2024-02-14 | 2024-09-19 | 219 | 157 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-19 | 2025-04-15 | 209 | 149 | Unknown | 2025-03-24 | Unknown | Unknown | 2025-04-17 | 2025-05-14 | 28 | 20 | 2025-05-14 | 2025-05-12 | Unknown | Unknown | 313 | 223 | 247 | 177 | 560 | 400 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | N/A | 192.75 | 192.75 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-16 | -453 | -324 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-22 | 2024-10-22 | 2025-06-20 | IOU Designed & Installed | N/A | No | N/A | 1437.3 | Unknown | Unknown | Unknown | 20.68 | 1416.62 | 3981 | 1570.98 | 1437.3 | 133.68 | Yes | N/A | N/A | 2024-10-22 | 2024-11-22 | 32 | 24 | 2024-11-22 | 2024-11-26 | 5 | 3 | 2024-11-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-26 | 2025-06-20 | 207 | 149 | Unknown | 2025-06-20 | Unknown | Unknown | 2025-06-20 | 2025-06-20 | 1 | 1 | 2025-06-20 | 2025-06-20 | 1 | 1 | 239 | 173 | 7 | 5 | 246 | 178 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R15 | OH | IOU Design | Residential | Underserved Community | El Cajon | COUNTY OF SAN DIEGO-SOUTH of 56 | 802.05 | 802.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-01 | -68 | -49 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-22 | 2024-01-22 | 2024-05-30 | IOU Designed & Installed | N/A | No | N/A | 113189.95 | 11391.75 | Unknown | Unknown | -2974.77 | 104772.97 | 1824.8 | 29185.38 | 113189.95 | -84004.57 | Yes | N/A | N/A | 2024-01-22 | 2024-01-22 | 1 | 1 | 2024-01-22 | 2024-05-10 | 110 | 80 | Unknown | Unknown | Unknown | Unknown | 2024-05-01 | 2024-05-23 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-30 | 2024-07-25 | 57 | 41 | 2024-07-25 | 2024-07-25 | 1 | 1 | 1 | 1 | 191 | 139 | 192 | 140 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 74 | 74 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-30 | -632 | -452 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-14 | 2024-08-14 | 2024-08-21 | IOU Designed & Installed | N/A | No | N/A | 14.24 | Unknown | Unknown | Unknown | Unknown | 14.24 | 3941 | 1415.04 | 14.24 | 1400.8 | Yes | N/A | N/A | 2024-08-14 | 2024-07-26 | Unknown | Unknown | 2024-07-26 | 2024-08-14 | 20 | 14 | 2024-08-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-14 | 2024-08-21 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2024-08-21 | 2024-08-27 | 7 | 5 | 2024-08-27 | 2024-09-05 | 10 | 8 | 8 | 6 | 37 | 27 | 45 | 33 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 44.05 | 44.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-19 | -467 | -334 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-02 | 2024-02-02 | 2024-06-26 | IOU Designed & Installed | N/A | No | N/A | -4.52 | -4.73 | Unknown | Unknown | Unknown | 0.21 | 3885 | 163.83 | -4.52 | 168.35 | Yes | N/A | N/A | 2024-02-02 | 2024-02-29 | 28 | 20 | 2024-02-29 | 2024-02-29 | 1 | 1 | 2024-02-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-04 | 2024-06-26 | 115 | 83 | Unknown | Unknown | Unknown | Unknown | 2024-06-26 | 2024-07-09 | 14 | 10 | 2024-07-09 | 2024-07-09 | 1 | 1 | 143 | 103 | 16 | 12 | 159 | 115 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 46.05 | 46.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-05 | -485 | -347 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-08 | 2023-10-08 | 2023-11-10 | IOU Designed & Installed | N/A | No | N/A | 1702.42 | 611.24 | Unknown | Unknown | Unknown | 1091.18 | 3981 | 786.95 | 1702.42 | -915.47 | Yes | N/A | N/A | 2023-10-08 | 2023-10-08 | 1 | 0 | 2023-10-08 | 2023-10-08 | 1 | 0 | 2023-10-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-08 | 2023-11-10 | 34 | 25 | Unknown | Unknown | Unknown | Unknown | 2023-11-10 | 2023-12-07 | 28 | 20 | 2023-12-07 | 2023-12-07 | 1 | 1 | 35 | 25 | 30 | 21 | 65 | 46 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-25 | -284 | -203 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-19 | 2024-07-19 | 2024-07-23 | IOU Designed & Installed | N/A | No | N/A | 35.7 | -3.96 | Unknown | Unknown | 17.51 | 22.15 | 3885 | 1528.78 | 35.7 | 1493.08 | Yes | N/A | N/A | 2024-07-19 | 2024-02-16 | Unknown | Unknown | 2024-02-16 | 2024-07-19 | 155 | 111 | 2024-07-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-19 | 2024-07-23 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | 2024-07-23 | 2025-04-16 | 268 | 192 | 2025-04-16 | 2025-04-16 | 1 | 1 | 5 | 3 | 424 | 304 | 429 | 307 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SOLANA BEACH | SOLANA BEACH | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-15 | -104 | -75 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-14 | 2023-03-15 | 2023-06-26 | IOU Designed & Installed | N/A | No | N/A | 4074.16 | Unknown | Unknown | Unknown | Unknown | 4074.16 | Unknown | 239.1 | 4074.16 | -3835.06 | Yes | N/A | N/A | 2023-03-14 | 2023-03-15 | 2 | 2 | 2023-03-15 | 2023-03-16 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2023-03-15 | 2023-04-21 | 38 | 28 | 2023-03-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-26 | 2023-07-03 | 8 | 6 | 2023-07-03 | 2023-07-03 | 1 | 1 | 2 | 2 | 49 | 37 | 51 | 39 | Steps 2,3,5,6,7 | 36 | 26 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 12.75 | 12.75 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-11 | -483 | -346 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-16 | 2023-11-17 | Unknown | IOU Designed & Installed | N/A | No | N/A | -457.55 | -11.26 | Unknown | Unknown | -709 | 262.71 | Unknown | 708.72 | -457.55 | 1166.27 | Yes | N/A | N/A | 2023-11-16 | 2023-10-10 | Unknown | Unknown | 2023-10-10 | 2023-12-28 | 80 | 58 | 2023-12-28 | 2024-01-24 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | 2024-01-25 | Unknown | Unknown | Unknown | Unknown | 2024-03-01 | Unknown | Unknown | Unknown | 2024-03-15 | Unknown | Unknown | 2024-03-15 | 2024-03-15 | 1 | 1 | 28 | 20 | 81 | 59 | 109 | 79 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | ENCINITAS | ENCINITAS | 92.05 | 92.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-03 | -60 | -45 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-23 | 2023-05-23 | 2023-08-07 | IOU Designed & Installed | N/A | No | N/A | 648.74 | -20.11 | Unknown | Unknown | 40.29 | 628.56 | 3981 | 1001.31 | 648.74 | 352.57 | Yes | N/A | N/A | 2023-05-23 | 2023-06-23 | 32 | 24 | 2023-06-23 | 2023-07-05 | 13 | 9 | 2023-07-05 | Unknown | Unknown | Unknown | 2023-05-25 | 2023-06-13 | 20 | 14 | 2023-07-05 | 2023-08-07 | 34 | 24 | Unknown | Unknown | Unknown | Unknown | 2023-08-07 | 2024-03-04 | 211 | 151 | 2024-03-04 | 2024-03-04 | 1 | 1 | 66 | 48 | 245 | 175 | 311 | 223 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | JAMUL | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-23 | -504 | -361 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-06 | 2024-03-06 | 2024-09-03 | IOU Designed & Installed | N/A | No | N/A | -422.62 | Unknown | Unknown | Unknown | -513 | 90.38 | 3981 | 2126.81 | -422.62 | 2549.43 | Yes | N/A | N/A | 2024-03-06 | 2024-02-01 | Unknown | Unknown | 2024-02-01 | 2024-03-06 | 35 | 25 | 2024-03-06 | 2024-03-19 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | 2024-03-06 | 2024-09-03 | 182 | 130 | Unknown | 2024-08-13 | Unknown | Unknown | 2024-09-03 | 2024-09-09 | 7 | 5 | 2024-09-09 | 2024-09-06 | Unknown | Unknown | 196 | 140 | 42 | 30 | 238 | 170 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | COUNTY OF SAN DIEGO-SOUTH of 56 | 48.05 | 48.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-01 | -413 | -296 | No | 2024-05-31 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-31 | 2024-05-31 | 2025-02-04 | IOU Designed & Installed | N/A | Yes | 230 | 539.89 | -10.2 | Unknown | Unknown | Unknown | 550.09 | 3981 | 1371.2 | 539.89 | 831.31 | Yes | N/A | N/A | 2024-05-31 | 2025-01-16 | 231 | 165 | 2025-01-16 | 2024-05-31 | Unknown | Unknown | 2024-05-31 | Unknown | Unknown | Unknown | 2025-01-27 | 2025-02-03 | 8 | 6 | 2024-05-31 | 2025-02-04 | 250 | 178 | Unknown | Unknown | Unknown | Unknown | 2025-02-04 | 2025-02-07 | 4 | 4 | 2025-02-07 | 2025-02-12 | 6 | 4 | 481 | 343 | 18 | 14 | 499 | 357 | Steps 2,3,5,6,7 | 248 | 176 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | LAKESIDE | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2024-05-31 | 69 | 50 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-08 | 2023-09-15 | 2024-07-10 | IOU Designed & Installed | N/A | No | N/A | 16378.67 | 5845.03 | Unknown | Unknown | -8159.38 | 18693.02 | 3981 | 17299.84 | 16378.67 | 921.17 | Yes | N/A | N/A | 2023-09-08 | 2023-08-10 | Unknown | Unknown | 2023-08-10 | 2024-04-30 | 265 | 189 | 2024-02-28 | 2024-02-28 | 1 | 1 | 2024-02-22 | 2024-05-01 | 16 | 12 | 2024-04-30 | 2024-06-26 | 58 | 42 | 2024-05-07 | 2024-06-24 | 49 | 35 | 2024-07-10 | 2024-08-12 | 34 | 24 | 2024-08-12 | 2024-08-08 | Unknown | Unknown | 59 | 43 | 364 | 260 | 423 | 303 | Steps 2,3,5,6,7 | 119 | 85 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | RAMONA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-01 | -653 | -466 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-27 | 2024-11-27 | 2024-12-10 | IOU Designed & Installed | N/A | No | N/A | 909.65 | 403.32 | Unknown | Unknown | Unknown | 506.33 | 3981 | 1820.32 | 909.65 | 910.67 | Yes | N/A | N/A | 2024-11-27 | 2024-11-27 | 1 | 1 | 2024-11-27 | 2024-11-27 | 1 | 1 | 2024-11-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-27 | 2024-12-10 | 14 | 10 | Unknown | 2024-12-07 | Unknown | Unknown | 2024-12-10 | 2025-01-17 | 39 | 29 | 2025-01-17 | 2025-01-17 | 1 | 1 | 15 | 11 | 41 | 31 | 56 | 42 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 49 | 49 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-27 | -652 | -466 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-23 | 2024-01-23 | 2024-02-08 | IOU Designed & Installed | N/A | No | N/A | 1894.81 | -23.97 | Unknown | Unknown | 10.33 | 1908.45 | 3981 | 1105.73 | 1894.81 | -789.08 | Yes | N/A | N/A | 2024-01-23 | 2024-01-04 | Unknown | Unknown | 2024-01-04 | 2024-01-23 | 20 | 14 | 2024-01-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-23 | 2024-02-08 | 17 | 13 | Unknown | Unknown | Unknown | Unknown | 2024-02-08 | 2024-03-15 | 37 | 27 | 2024-03-15 | 2024-03-15 | 1 | 1 | 17 | 13 | 58 | 42 | 75 | 55 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | LAKESIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-09 | -69 | -50 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-26 | 2023-08-15 | 2023-11-07 | IOU Designed & Installed | N/A | No | N/A | 0.66 | -9.72 | Unknown | Unknown | Unknown | 10.38 | Unknown | 270.36 | 0.66 | 269.7 | Yes | N/A | N/A | 2023-07-26 | 2023-05-22 | Unknown | Unknown | 2023-05-22 | 2023-08-15 | 86 | 62 | 2023-08-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-15 | 2023-11-07 | 85 | 61 | Unknown | Unknown | Unknown | Unknown | 2023-11-07 | 2024-03-01 | 116 | 84 | 2024-03-01 | 2024-03-01 | 1 | 1 | 85 | 61 | 203 | 147 | 288 | 208 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-11 | -137 | -98 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-24 | 2023-10-24 | 2024-03-05 | IOU Designed & Installed | N/A | No | N/A | -19.58 | -15.9 | Unknown | Unknown | Unknown | -3.68 | Unknown | 497.98 | -19.58 | 517.56 | Yes | N/A | N/A | 2023-10-24 | 2023-09-05 | Unknown | Unknown | 2023-09-05 | 2023-10-24 | 50 | 36 | 2023-10-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-24 | 2024-03-05 | 134 | 96 | Unknown | Unknown | Unknown | Unknown | 2024-03-05 | 2024-03-27 | 23 | 17 | 2024-03-27 | 2024-03-27 | 1 | 1 | 134 | 96 | 74 | 54 | 208 | 150 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CORONADO | N/A | 165.05 | 165.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-30 | -497 | -356 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-06 | 2024-02-06 | Unknown | IOU Designed & Installed | N/A | No | N/A | 4.19 | -3.71 | Unknown | Unknown | Unknown | 7.9 | Unknown | 287.46 | 4.19 | 283.27 | Yes | N/A | N/A | 2024-02-06 | 2024-02-16 | 11 | 9 | 2024-02-16 | 2024-02-21 | 6 | 4 | 2024-02-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-20 | Unknown | Unknown | 2024-06-20 | 2024-06-20 | 1 | 1 | 11 | 9 | 7 | 5 | 18 | 14 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN MARCOS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-29 | -682 | -489 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-15 | 2025-05-16 | 2025-06-04 | IOU Designed & Installed | N/A | No | N/A | 4883.52 | 1273.1 | Unknown | Unknown | Unknown | 3610.42 | 3981 | 1153.69 | 4883.52 | -3729.83 | Yes | N/A | N/A | 2025-05-15 | 2025-05-01 | Unknown | Unknown | 2025-05-01 | 2025-05-16 | 16 | 12 | 2025-05-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-16 | 2025-06-04 | 20 | 14 | Unknown | Unknown | Unknown | Unknown | 2025-06-04 | 2025-06-16 | 13 | 9 | 2025-06-16 | 2025-06-16 | 1 | 1 | 20 | 14 | 30 | 22 | 50 | 36 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 111 | 111 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-10 | -167 | -120 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-29 | 2023-09-29 | 2024-10-24 | IOU Designed & Installed | N/A | No | N/A | 852.88 | 253.74 | Unknown | Unknown | Unknown | 599.14 | 7962 | 808.26 | 852.88 | -44.62 | Yes | N/A | N/A | 2023-09-29 | 2023-09-29 | 1 | 1 | 2023-09-29 | 2023-09-29 | 1 | 1 | 2023-09-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-29 | 2024-10-24 | 392 | 280 | Unknown | Unknown | Unknown | Unknown | 2024-10-24 | 2024-10-28 | 5 | 3 | 2024-10-28 | 2024-10-25 | Unknown | Unknown | 393 | 281 | 6 | 4 | 399 | 285 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | 4471 | 4471 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-01-26 | 210 | 151 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-20 | 2022-05-20 | 2023-07-18 | IOU Designed & Installed | N/A | No | N/A | 56654.51 | 10280.51 | Unknown | Unknown | 296.69 | 46077.31 | 81226 | 9104.64 | 56654.51 | -47549.87 | Yes | N/A | N/A | 2022-05-20 | 2023-03-01 | 286 | 204 | 2023-03-01 | 2023-03-23 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | 2023-07-21 | 2023-07-27 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-26 | Unknown | Unknown | 2023-07-18 | 2023-08-24 | 38 | 28 | 2023-08-24 | 2023-08-24 | 1 | 1 | 286 | 204 | 69 | 51 | 355 | 255 | Steps 2,3,5,6,7 | 617 | 441 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 80.05 | 80.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-06 | 93 | 68 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-04 | 2024-04-12 | 2024-07-15 | IOU Designed & Installed | N/A | No | N/A | 2568.64 | 682.49 | Unknown | 43.19 | 15.1 | 1827.86 | 3981 | 979.86 | 2568.64 | -1588.78 | Yes | N/A | N/A | 2023-10-04 | 2024-04-22 | 202 | 144 | 2024-04-22 | 2024-04-22 | 1 | 1 | 2024-04-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-22 | 2024-07-15 | 85 | 61 | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | 2024-08-07 | 24 | 18 | 2024-08-07 | 2024-08-07 | 1 | 1 | 287 | 205 | 26 | 20 | 313 | 225 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 92.05 | 92.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-29 | 173 | 124 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-26 | 2025-03-28 | Unknown | IOU Designed & Installed | N/A | No | N/A | -852.14 | 31.24 | Unknown | Unknown | -1934 | 1050.62 | Unknown | 1648.7 | -852.14 | 2500.84 | Yes | N/A | N/A | 2024-12-26 | 2025-04-18 | 114 | 82 | 2025-04-18 | 2025-04-29 | 12 | 8 | Unknown | Unknown | Unknown | Unknown | 2025-04-22 | 2025-05-02 | 11 | 9 | 2025-04-29 | 2025-05-07 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-22 | Unknown | Unknown | 2025-05-22 | 2025-05-21 | Unknown | Unknown | 123 | 89 | 23 | 17 | 146 | 106 | Steps 2,3,5,6,7 | 3 | 3 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | CARLSBAD | N/A | 37 | 37 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-28 | -282 | -202 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-01 | 2024-07-29 | 2025-05-20 | IOU Designed & Installed | N/A | No | N/A | 297.06 | 509.4 | Unknown | 122.99 | -1845 | 1509.67 | Unknown | 1845.12 | 297.06 | 1548.06 | Yes | N/A | N/A | 2024-05-01 | 2024-07-12 | 73 | 53 | 2024-07-12 | 2024-07-31 | 20 | 14 | 2024-07-31 | 2025-05-14 | 288 | 206 | Unknown | Unknown | Unknown | Unknown | 2025-05-20 | 2025-05-20 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2025-05-20 | 2025-05-22 | 3 | 3 | 2025-05-22 | 2025-05-22 | 1 | 1 | 362 | 260 | 24 | 18 | 386 | 278 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN MARCOS | N/A | 30 | 30 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-18 | -394 | -283 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-13 | 2024-01-02 | 2024-08-16 | IOU Designed & Installed | N/A | No | N/A | 617.63 | Unknown | Unknown | Unknown | -711.88 | 1329.51 | Unknown | 722.5 | 617.63 | 104.87 | Yes | N/A | N/A | 2023-12-13 | 2024-01-22 | 41 | 29 | 2024-01-22 | 2024-02-12 | 22 | 16 | 2024-02-12 | 2024-04-17 | 66 | 48 | Unknown | Unknown | Unknown | Unknown | 2024-04-17 | 2024-08-16 | 122 | 88 | Unknown | 2024-08-13 | Unknown | Unknown | 2024-08-16 | 2024-08-26 | 11 | 7 | 2024-08-26 | 2024-08-20 | Unknown | Unknown | 229 | 165 | 33 | 23 | 262 | 188 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| Combo (R15 & R16) | OH | IOU Design | Residential | Underserved Community | JULIAN | N/A | 302 | 302 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-19 | -298 | -215 | No | 2022-04-07 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-07 | 2022-06-09 | 2023-07-24 | IOU Designed & Installed | N/A | Yes | 299 | 19190.7 | 1605.54 | Unknown | Unknown | -1207.6 | 18792.76 | 3885 | 8072.38 | 19190.7 | -11118.32 | Yes | N/A | N/A | 2022-04-07 | 2023-01-31 | 300 | 214 | 2023-01-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-23 | 2023-03-02 | 8 | 6 | 2022-08-03 | 2023-07-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-24 | 2023-09-05 | 44 | 32 | 2023-09-05 | 2023-03-27 | Unknown | Unknown | 300 | 214 | 52 | 38 | 352 | 252 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | Encinitas | N/A | 30000 | 30000 | Not Available | >2MW | No | N/A | N/A | N/A | 2022-11-01 | 965 | 690 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-10 | 2024-04-30 | 2025-04-28 | IOU Designed & Installed | N/A | No | N/A | 26516.34 | 4857.36 | Unknown | Unknown | -6656 | 28314.98 | 108867 | Not available | 26516.34 | Unknown | Yes | N/A | N/A | 2024-04-10 | 2023-07-11 | Unknown | Unknown | 2023-07-11 | 2024-05-07 | 302 | 216 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-07 | 2025-05-28 | 387 | 277 | Unknown | Unknown | Unknown | Unknown | 2025-04-28 | 2025-02-24 | Unknown | Unknown | 2025-02-24 | 2025-06-23 | 120 | 86 | 387 | 277 | 422 | 302 | 809 | 579 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-27 | -503 | -360 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-11 | 2024-11-12 | 2025-05-07 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1588.36 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-11 | 2024-10-23 | Unknown | Unknown | 2024-10-23 | 2024-11-12 | 21 | 15 | 2024-11-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-12 | 2025-05-07 | 177 | 127 | Unknown | Unknown | Unknown | Unknown | 2025-05-07 | 2025-05-12 | 6 | 4 | 2025-05-12 | 2025-05-12 | 1 | 1 | 177 | 127 | 28 | 20 | 205 | 147 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 66 | 66 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-19 | -561 | -401 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-03 | 2023-02-03 | 2023-04-06 | IOU Designed & Installed | N/A | No | N/A | 2483.4 | 846.06 | Unknown | 350.51 | Unknown | 1286.83 | 3885 | 755.77 | 2483.4 | -1727.63 | Yes | N/A | N/A | 2023-02-03 | 2023-02-03 | 1 | 1 | 2023-02-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-03 | 2023-04-06 | 63 | 45 | Unknown | Unknown | Unknown | Unknown | 2023-04-06 | 2023-04-07 | 2 | 2 | 2023-04-07 | 2023-04-07 | 1 | 1 | 64 | 46 | 3 | 3 | 67 | 49 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | POWAY | N/A | 149.05 | 149.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-24 | -344 | -247 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-01 | 2023-02-01 | 2023-11-03 | IOU Designed & Installed | N/A | No | N/A | 1202.52 | -15.89 | Unknown | Unknown | 81.43 | 1136.98 | 3981 | 2380.65 | 1202.52 | 1178.13 | Yes | N/A | N/A | 2023-02-01 | 2023-04-12 | 71 | 51 | 2023-04-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-12 | 2023-11-03 | 206 | 148 | Unknown | 2023-11-02 | Unknown | Unknown | 2023-11-03 | 2023-11-15 | 13 | 9 | 2023-11-15 | 2023-11-15 | 1 | 1 | 277 | 199 | 14 | 10 | 291 | 209 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | CARLSBAD | N/A | 10.05 | 10.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-03 | -142 | -103 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-17 | 2023-08-23 | 2023-11-03 | IOU Designed & Installed | N/A | No | N/A | 2577.79 | 737.28 | Unknown | 455.2 | Unknown | 1385.31 | 3981 | 1010.99 | 2577.79 | -1566.8 | Yes | N/A | N/A | 2023-08-17 | 2023-08-23 | 7 | 5 | 2023-08-23 | 2023-08-23 | 1 | 1 | 2023-08-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-23 | 2023-11-03 | 73 | 53 | Unknown | Unknown | Unknown | Unknown | 2023-11-03 | 2023-11-13 | 11 | 7 | 2023-11-13 | 2023-11-13 | 1 | 1 | 80 | 58 | 13 | 9 | 93 | 67 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 2054.1 | 2054.1 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-08-15 | 374 | 269 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-15 | 2023-02-15 | 2024-08-12 | IOU Designed & Installed | N/A | No | N/A | 10866.55 | 499.22 | Unknown | Unknown | -4920.15 | 15287.48 | 3981 | 8671.53 | 10866.55 | -2195.02 | Yes | N/A | N/A | 2023-02-15 | 2023-02-27 | 13 | 9 | 2023-02-27 | 2023-09-07 | 193 | 139 | 2023-02-21 | 2023-03-28 | 36 | 26 | 2023-08-28 | 2023-08-31 | 4 | 4 | 2023-09-07 | 2024-07-30 | 328 | 234 | 2024-02-20 | 2024-07-11 | 143 | 103 | 2024-08-12 | 2024-09-04 | 24 | 18 | 2024-09-04 | 2024-08-23 | Unknown | Unknown | 377 | 269 | 364 | 264 | 741 | 533 | Steps 2,3,5,6,7 | 359 | 257 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LEMON GROVE | N/A | 134.2 | 134.2 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-06 | -460 | -330 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-31 | 2024-07-31 | 2025-02-18 | IOU Designed & Installed | N/A | No | N/A | 33.39 | Unknown | Unknown | Unknown | Unknown | 33.39 | 3941 | 1415.16 | 33.39 | 1381.77 | Yes | N/A | N/A | 2024-07-31 | 2024-07-11 | Unknown | Unknown | 2024-07-11 | 2024-07-31 | 21 | 15 | 2024-07-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-31 | 2025-02-18 | 203 | 145 | Unknown | Unknown | Unknown | Unknown | 2025-02-18 | 2025-02-27 | 10 | 8 | 2025-02-27 | 2025-03-03 | 5 | 3 | 203 | 145 | 36 | 26 | 239 | 171 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 20 | 20 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-28 | -568 | -407 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-24 | 2024-08-14 | 2024-10-31 | IOU Designed & Installed | N/A | No | N/A | 128.97 | -1.88 | Unknown | Unknown | Unknown | 130.85 | 3981 | 1482.36 | 128.97 | 1353.39 | Yes | N/A | N/A | 2024-07-24 | 2024-06-10 | Unknown | Unknown | 2024-06-10 | 2024-08-22 | 74 | 54 | 2024-08-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-22 | 2024-10-31 | 71 | 51 | Unknown | Unknown | Unknown | Unknown | 2024-10-31 | 2024-11-06 | 7 | 5 | 2024-11-06 | 2024-11-06 | 1 | 1 | 71 | 51 | 82 | 60 | 153 | 111 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-05 | -36 | -26 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-19 | 2024-06-19 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1645.65 | -9.79 | Unknown | Unknown | Unknown | 1655.44 | Unknown | 2319.84 | 1645.65 | 674.19 | Yes | N/A | N/A | 2024-06-19 | 2025-02-07 | 234 | 168 | 2025-02-07 | 2025-02-11 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | 2024-09-05 | 2024-10-09 | 35 | 25 | 2025-02-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-28 | Unknown | Unknown | 2025-02-28 | 2025-02-28 | 1 | 1 | 234 | 168 | 41 | 29 | 275 | 197 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | LA MESA | LA MESA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-31 | -702 | -503 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-12 | 2023-09-13 | Unknown | IOU Designed & Installed | N/A | No | N/A | 0.11 | -3.11 | Unknown | Unknown | Unknown | 3.22 | Unknown | 237.15 | 0.11 | 237.04 | Yes | N/A | N/A | 2023-09-12 | 2023-09-13 | 2 | 2 | 2023-09-13 | 2023-10-02 | 20 | 14 | Unknown | Unknown | Unknown | Unknown | 2023-09-13 | 2023-10-05 | 23 | 17 | 2023-10-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-29 | Unknown | Unknown | 2024-01-29 | 2024-01-29 | 1 | 1 | 2 | 2 | 44 | 32 | 46 | 34 | Steps 2,3,5,6,7 | 3 | 3 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-12 | -432 | -309 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-06 | 2024-09-06 | Unknown | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 3609.56 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-06 | 2024-09-16 | 11 | 7 | 2024-09-16 | 2024-09-16 | 1 | 1 | 2024-09-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-06 | Unknown | Unknown | 2025-05-06 | 2025-05-06 | 1 | 1 | 11 | 7 | 2 | 2 | 13 | 9 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 159.05 | 159.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-25 | -368 | -264 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-04 | 2023-04-04 | Unknown | IOU Designed & Installed | N/A | No | N/A | 722.13 | -7.88 | Unknown | Unknown | 0.64 | 729.37 | 3981 | 1178.46 | 722.13 | 456.33 | Yes | N/A | N/A | 2023-04-04 | 2023-04-05 | 2 | 2 | 2023-04-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-27 | Unknown | Unknown | Unknown | Unknown | 2024-01-12 | Unknown | Unknown | Unknown | 2024-01-23 | Unknown | Unknown | 2024-01-23 | 2024-01-23 | 1 | 1 | 2 | 2 | 1 | 1 | 3 | 3 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | COUNTY OF SAN DIEGO-SOUTH of 56 | 131.05 | 131.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-31 | 491 | 351 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-16 | 2023-10-19 | 2025-04-16 | IOU Designed & Installed | N/A | No | N/A | 17861.34 | 4721.98 | Unknown | 744.47 | -452.49 | 12847.38 | 0 | 1467.45 | 17861.34 | -16393.89 | Yes | N/A | N/A | 2023-10-16 | 2023-10-30 | 15 | 11 | 2023-10-30 | 2023-11-30 | 32 | 24 | Unknown | Unknown | Unknown | Unknown | 2024-05-24 | 2024-06-18 | 26 | 18 | 2023-11-30 | 2025-03-12 | 469 | 335 | Unknown | Unknown | Unknown | Unknown | 2025-04-16 | 2025-05-05 | 20 | 14 | 2025-05-05 | 2025-05-05 | 1 | 1 | 484 | 346 | 79 | 57 | 563 | 403 | Steps 2,3,5,6,7 | 201 | 143 | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | Applicant Design | Commercial | Underserved Community | SAN DIEGO | NCTD-Trolly South of 56 | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2022-02-03 | 742 | 531 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-05 | 2023-04-05 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 26.09 | -31.61 | Unknown | Unknown | Unknown | 57.7 | 14288 | 5474.25 | 26.09 | 5448.16 | Yes | N/A | N/A | 2023-04-05 | 2023-04-17 | 13 | 9 | 2023-04-17 | 2023-08-02 | 108 | 78 | 2023-04-28 | 2023-08-02 | 72 | 52 | 2023-05-17 | 2023-10-18 | 94 | 68 | 2023-08-02 | 2024-01-23 | 175 | 125 | 2023-08-10 | 2024-01-08 | 152 | 108 | Unknown | 2024-03-14 | Unknown | Unknown | 2024-03-14 | 2024-02-15 | Unknown | Unknown | 260 | 186 | 354 | 254 | 614 | 440 | Steps 2,3,5,6,7 | 416 | 296 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2020-09-05 | 1286 | 919 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-23 | 2023-08-23 | 2023-12-12 | IOU Designed & Installed | N/A | No | N/A | 8701.48 | -69.95 | Unknown | Unknown | -842 | 9613.43 | Unknown | 841.85 | 8701.48 | -7859.63 | Yes | N/A | N/A | 2023-08-23 | 2023-08-24 | 2 | 2 | 2023-08-24 | 2023-11-03 | 72 | 52 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-03 | Unknown | Unknown | Unknown | Unknown | 2023-11-30 | Unknown | Unknown | 2023-12-12 | 2024-03-14 | 94 | 68 | 2024-03-14 | 2024-03-14 | 1 | 1 | 2 | 2 | 167 | 121 | 169 | 123 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-31 | -196 | -141 | No | 2022-05-17 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-17 | 2022-05-17 | 2023-04-07 | IOU Designed & Installed | N/A | Yes | 289 | 141.47 | -6.94 | Unknown | Unknown | 58.26 | 90.15 | 3885 | 760.18 | 141.47 | 618.71 | Yes | N/A | N/A | 2022-05-17 | 2023-03-02 | 290 | 208 | 2023-03-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2022-05-17 | 2023-04-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-07 | 2023-06-12 | 67 | 47 | 2023-06-12 | 2023-04-18 | Unknown | Unknown | 290 | 208 | 67 | 47 | 357 | 255 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| Combo (R15 & R16) | UG | IOU Design | Commercial | Underserved Community | Dana Point | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-08-02 | 686 | 491 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-30 | 2025-05-30 | 2025-06-13 | IOU Designed & Installed | N/A | No | N/A | 11142.17 | 11142.17 | Unknown | Unknown | -13731.28 | 13731.28 | Unknown | 91326.73 | 11142.17 | 80184.56 | Yes | N/A | N/A | 2025-05-30 | 2025-05-30 | 1 | 1 | 2025-05-30 | 2025-06-13 | 15 | 11 | 2025-06-03 | 2025-06-25 | 23 | 17 | 2025-06-12 | 2025-06-12 | 1 | 1 | 2025-06-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-13 | 2025-06-18 | 6 | 4 | 2025-06-18 | 2025-06-18 | 1 | 1 | 24 | 18 | 23 | 17 | 47 | 35 | Steps 2,3,5,6,7 | 23 | 17 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2021-06-03 | 1072 | 767 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-28 | 2023-11-28 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1064.73 | -17.83 | Unknown | Unknown | -2414 | 1367.1 | Unknown | 1925.61 | -1064.73 | 2990.34 | Yes | N/A | N/A | 2023-11-28 | 2023-10-30 | Unknown | Unknown | 2023-10-30 | 2024-04-01 | 155 | 111 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-01 | 2024-03-12 | Unknown | Unknown | Unknown | 2024-04-25 | Unknown | Unknown | Unknown | 2024-05-08 | Unknown | Unknown | 2024-05-08 | 2024-05-10 | 3 | 3 | 0 | 0 | 158 | 114 | 158 | 114 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R15 | UG | IOU Design | Residential | Underserved Community | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-12-01 | 372 | 267 | No | 2022-12-16 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-16 | 2023-01-30 | 2023-09-20 | IOU Designed & Installed | N/A | Yes | 40 | 10537.44 | 2024 | Unknown | 15.76 | -13263.18 | 21760.86 | Unknown | 13437.94 | 10537.44 | 2900.5 | Yes | N/A | N/A | 2022-12-16 | 2023-05-16 | 152 | 108 | 2023-05-16 | 2023-09-06 | 114 | 82 | 2023-02-10 | 2023-08-29 | 201 | 143 | 2023-02-23 | 2023-09-06 | 18 | 12 | 2023-09-19 | Unknown | Unknown | Unknown | 2023-09-19 | Unknown | Unknown | Unknown | 2023-09-20 | 2023-12-08 | 80 | 58 | 2023-12-08 | 2023-12-08 | 1 | 1 | 353 | 251 | 213 | 153 | 566 | 404 | Steps 2,3,5,6,7 | 395 | 281 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | ALPINE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-06 | -212 | -153 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-12 | 2024-06-12 | 2024-06-29 | IOU Designed & Installed | N/A | No | N/A | -1741.63 | 2481.44 | Unknown | 124.54 | -5437 | 1089.39 | Unknown | 5436.64 | -1741.63 | 7178.27 | Yes | N/A | N/A | 2024-06-12 | 2024-06-12 | 1 | 1 | 2024-06-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-29 | 2024-08-06 | 39 | 27 | 2024-08-06 | 2024-08-06 | 1 | 1 | 1 | 1 | 40 | 28 | 41 | 29 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-27 | -616 | -441 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-04 | 2025-03-04 | 2025-05-08 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 515.36 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-04 | 2025-02-10 | Unknown | Unknown | 2025-02-10 | 2025-03-04 | 23 | 17 | 2025-03-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-04 | 2025-05-08 | 66 | 48 | Unknown | Unknown | Unknown | Unknown | 2025-05-08 | 2025-05-21 | 14 | 10 | 2025-05-21 | 2025-05-21 | 1 | 1 | 66 | 48 | 38 | 28 | 104 | 76 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 97 | 97 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-01 | 242 | 174 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-01-25 | 2023-12-08 | 2024-05-24 | IOU Designed & Installed | N/A | No | N/A | 1025.66 | -2.89 | Unknown | Unknown | 33.5 | 995.05 | 3981 | 931.98 | 1025.66 | -93.68 | Yes | N/A | N/A | 2022-01-25 | 2023-12-12 | 687 | 491 | 2023-12-12 | 2023-12-14 | 3 | 3 | 2023-12-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-14 | 2024-05-24 | 163 | 117 | Unknown | 2024-05-22 | Unknown | Unknown | 2024-05-24 | 2024-07-09 | 47 | 33 | 2024-07-09 | 2024-05-30 | Unknown | Unknown | 850 | 608 | 50 | 36 | 900 | 644 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | JULIAN | COUNTY OF SAN DIEGO-NORTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-06 | -262 | -189 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-30 | 2024-07-26 | 2025-05-01 | IOU Designed & Installed | N/A | No | N/A | -5315.47 | 3985.08 | Unknown | Unknown | -14300 | 4999.45 | 0 | 24420.08 | -5315.47 | 29735.55 | Yes | N/A | N/A | 2024-05-30 | 2024-06-19 | 21 | 15 | 2024-06-19 | 2025-04-24 | 310 | 222 | Unknown | Unknown | Unknown | Unknown | 2024-10-07 | 2025-04-09 | 25 | 19 | 2025-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-01 | 2025-05-20 | 20 | 14 | 2025-05-20 | 2025-05-20 | 1 | 1 | 21 | 15 | 356 | 256 | 377 | 271 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 88.05 | 88.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-15 | -472 | -339 | No | 2023-03-01 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-01 | 2023-03-01 | 2023-08-01 | IOU Designed & Installed | N/A | Yes | 92 | 645.49 | -12.97 | Unknown | Unknown | 21.01 | 637.45 | 3981 | 719.26 | 645.49 | 73.77 | Yes | N/A | N/A | 2023-03-01 | 2023-06-01 | 93 | 67 | 2023-06-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-15 | 2023-08-01 | 140 | 100 | Unknown | 2023-06-13 | Unknown | Unknown | 2023-08-01 | 2023-08-01 | 1 | 1 | 2023-08-01 | 2023-08-01 | 1 | 1 | 233 | 167 | 2 | 2 | 235 | 169 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-09 | -640 | -459 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-18 | 2024-11-18 | 2024-12-27 | IOU Designed & Installed | N/A | No | N/A | 7.01 | Unknown | Unknown | Unknown | Unknown | 7.01 | Unknown | 197.01 | 7.01 | 190 | Yes | N/A | N/A | 2024-11-18 | 2024-10-31 | Unknown | Unknown | 2024-10-31 | 2024-11-25 | 26 | 18 | 2024-11-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-25 | 2024-12-27 | 33 | 25 | Unknown | Unknown | Unknown | Unknown | 2024-12-27 | 2025-01-07 | 12 | 8 | 2025-01-07 | 2025-01-07 | 1 | 1 | 33 | 25 | 39 | 27 | 72 | 52 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN MARCOS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-18 | -187 | -135 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-02 | 2024-04-02 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1560.73 | 489.72 | Unknown | 35.88 | -2307 | 220.67 | Unknown | 2306.73 | -1560.73 | 3867.46 | Yes | N/A | N/A | 2024-04-02 | 2024-04-02 | 1 | 1 | 2024-04-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 38 | 38 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-08 | 188 | 135 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-20 | 2023-01-20 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1394.87 | -14.51 | Unknown | Unknown | 14.9 | 1394.48 | 3981 | 563.21 | 1394.87 | -831.66 | Yes | N/A | N/A | 2023-01-20 | 2023-02-23 | 35 | 25 | 2023-02-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-23 | Unknown | Unknown | Unknown | Unknown | 2024-04-26 | Unknown | Unknown | Unknown | 2024-05-14 | Unknown | Unknown | 2024-05-14 | 2024-05-14 | 1 | 1 | 35 | 25 | 1 | 1 | 36 | 26 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 6 | 6 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-18 | -516 | -369 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-14 | 2025-01-14 | 2025-02-05 | IOU Designed & Installed | N/A | No | N/A | -4.74 | -19.78 | Unknown | Unknown | Unknown | 15.04 | 3981 | 2251.57 | -4.74 | 2256.31 | Yes | N/A | N/A | 2025-01-14 | 2025-01-14 | 1 | 1 | 2025-01-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-14 | 2025-02-05 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | 2025-02-05 | 2025-03-20 | 44 | 32 | 2025-03-20 | 2025-03-20 | 1 | 1 | 24 | 18 | 45 | 33 | 69 | 51 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-23 | -344 | -247 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-17 | 2023-03-17 | Unknown | IOU Designed & Installed | N/A | No | N/A | 806.78 | -5.13 | Unknown | Unknown | 3.32 | 808.59 | 3981 | 858.77 | 806.78 | 51.99 | Yes | N/A | N/A | 2023-03-17 | 2023-03-17 | 1 | 1 | 2023-03-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-14 | Unknown | Unknown | 2023-08-14 | 2023-08-14 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | RANCHO MISSION VIEJO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-01 | 322 | 231 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-09 | 2025-04-09 | 2025-06-18 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 1787 | 691.6 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-09 | 2025-04-09 | 1 | 1 | 2025-04-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-27 | Unknown | Unknown | 2025-06-18 | 2025-06-20 | 3 | 3 | 2025-06-20 | 2025-06-19 | Unknown | Unknown | 1 | 1 | 3 | 3 | 4 | 4 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 265 | 265 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-15 | 217 | 156 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-04 | 2024-08-09 | 2024-11-12 | IOU Designed & Installed | N/A | No | N/A | -1824.2 | Unknown | Unknown | Unknown | -1868 | 43.8 | Unknown | 1744.78 | -1824.2 | 3568.98 | Yes | N/A | N/A | 2023-10-04 | 2024-08-05 | 307 | 219 | 2024-08-05 | 2025-03-06 | 214 | 154 | 2025-03-06 | 2024-08-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-30 | 2024-11-12 | 75 | 53 | Unknown | 2024-11-11 | Unknown | Unknown | 2024-11-12 | 2024-11-19 | 8 | 6 | 2024-11-19 | 2024-11-18 | Unknown | Unknown | 382 | 272 | 222 | 160 | 604 | 432 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | CAPISTRANO BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-20 | -65 | -46 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-08 | 2024-08-13 | Unknown | IOU Designed & Installed | N/A | No | N/A | 44.13 | Unknown | Unknown | Unknown | 12.38 | 31.75 | Unknown | 1542.14 | 44.13 | 1498.01 | Yes | N/A | N/A | 2024-07-08 | 2024-08-07 | 31 | 23 | 2024-08-07 | 2025-03-06 | 212 | 152 | 2025-03-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-14 | Unknown | Unknown | 2025-02-14 | 2025-02-14 | 1 | 1 | 31 | 23 | 213 | 153 | 244 | 176 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LAGUNA HILLS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-06 | -159 | -114 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-05 | 2023-05-05 | Unknown | IOU Designed & Installed | N/A | No | N/A | 739.18 | 224.43 | Unknown | 89.36 | 3.21 | 422.18 | 3981 | 2188.84 | 739.18 | 1449.66 | Yes | N/A | N/A | 2023-05-05 | 2023-06-02 | 29 | 21 | 2023-06-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-29 | Unknown | Unknown | 2023-09-29 | 2023-09-29 | 1 | 1 | 29 | 21 | 1 | 1 | 30 | 22 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R29/R45 | UG | IOU Design | Commercial | N/A | SAN DIEGO | SAN DIEGO | 1161 | 1161 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2024-03-01 | 279 | 200 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-07 | 2023-06-09 | 2024-07-22 | IOU Designed & Installed | N/A | No | N/A | 260101.23 | 39021.06 | Unknown | 455.39 | 1003.22 | 219621.56 | 0 | 113871.92 | 260101.23 | -146229.31 | Yes | N/A | N/A | 2023-03-07 | 2023-06-09 | 95 | 69 | 2023-06-09 | 2024-02-27 | 264 | 188 | 2023-07-25 | 2024-02-06 | 142 | 100 | 2024-01-19 | 2024-08-08 | 31 | 25 | 2024-02-27 | 2024-09-24 | 211 | 151 | 2024-08-05 | 2024-10-02 | 59 | 43 | 2024-07-22 | 2024-12-05 | 137 | 99 | 2024-12-05 | 2024-12-05 | 1 | 1 | 448 | 320 | 492 | 356 | 940 | 676 | Steps 2,3,5,6,7 | 520 | 372 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | VALLEY CENTER | N/A | 78.05 | 78.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-16 | -573 | -410 | No | 2024-10-18 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-18 | 2024-10-18 | 2025-02-07 | IOU Designed & Installed | N/A | Yes | 56 | 986.71 | 251.36 | Unknown | Unknown | Unknown | 735.35 | 3981 | 1076.78 | 986.71 | 90.07 | Yes | N/A | N/A | 2024-10-18 | 2024-12-11 | 55 | 39 | 2024-12-11 | 2024-12-13 | 3 | 3 | 2024-12-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-18 | 2025-02-07 | 113 | 81 | Unknown | Unknown | Unknown | Unknown | 2025-02-07 | 2025-02-20 | 14 | 10 | 2025-02-20 | 2025-02-20 | 1 | 1 | 168 | 120 | 18 | 14 | 186 | 134 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 67 | 67 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-26 | -201 | -144 | No | 2024-01-12 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-12 | 2024-02-16 | Unknown | IOU Designed & Installed | N/A | Yes | 40 | -11.21 | -7.25 | Unknown | Unknown | Unknown | -3.96 | 3961 | 1101.15 | -11.21 | 1112.36 | Yes | N/A | N/A | 2024-01-12 | 2024-02-20 | 40 | 28 | 2024-02-20 | 2024-02-21 | 2 | 2 | 2024-02-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-08 | Unknown | Unknown | 2025-04-08 | 2025-04-08 | 1 | 1 | 40 | 28 | 3 | 3 | 43 | 31 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | N/A | 77.1 | 77.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-03 | -718 | -515 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-16 | 2023-07-19 | 2023-07-27 | IOU Designed & Installed | N/A | No | N/A | -5.2 | -3.76 | Unknown | Unknown | Unknown | -1.44 | Unknown | 1110.64 | -5.2 | 1115.84 | Yes | N/A | N/A | 2023-06-16 | 2023-07-19 | 34 | 24 | 2023-07-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-19 | 2023-07-27 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | 2023-07-27 | 2023-10-16 | 82 | 58 | 2023-10-16 | 2023-10-16 | 1 | 1 | 43 | 31 | 83 | 59 | 126 | 90 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-21 | -584 | -418 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-14 | 2024-06-15 | 2024-07-01 | IOU Designed & Installed | N/A | No | N/A | 1206.73 | 370.02 | Unknown | Unknown | Unknown | 836.71 | 7962 | 1509.17 | 1206.73 | 302.44 | Yes | N/A | N/A | 2024-06-14 | 2024-06-17 | 4 | 2 | 2024-06-17 | 2024-06-17 | 1 | 1 | 2024-06-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-17 | 2024-07-01 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2024-07-01 | 2024-07-17 | 17 | 13 | 2024-07-17 | 2024-07-17 | 1 | 1 | 19 | 13 | 19 | 15 | 38 | 28 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SOUTH LAGUNA | N/A | 82 | 82 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-08 | -271 | -194 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-09 | 2024-08-09 | Unknown | IOU Designed & Installed | N/A | No | N/A | 20.28 | Unknown | Unknown | Unknown | Unknown | 20.28 | 3981 | 1698.77 | 20.28 | 1678.49 | Yes | N/A | N/A | 2024-08-09 | 2024-08-09 | 1 | 1 | 2024-08-09 | 2024-08-09 | 1 | 1 | 2024-08-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-10 | Unknown | Unknown | 2024-10-10 | 2024-10-10 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-29 | -445 | -319 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-05 | 2024-02-12 | 2024-08-28 | IOU Designed & Installed | N/A | No | N/A | 10.95 | Unknown | Unknown | Unknown | Unknown | 10.95 | Unknown | 297.38 | 10.95 | 286.43 | Yes | N/A | N/A | 2024-02-05 | 2024-02-12 | 8 | 6 | 2024-02-12 | 2024-02-12 | 1 | 1 | 2024-02-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-12 | 2024-08-28 | 199 | 143 | Unknown | Unknown | Unknown | Unknown | 2024-08-28 | 2024-09-10 | 14 | 10 | 2024-09-10 | 2024-09-10 | 1 | 1 | 207 | 149 | 16 | 12 | 223 | 161 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 3984 | 3984 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-07-11 | -118 | -85 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-11 | 2023-12-12 | Unknown | IOU Designed & Installed | N/A | No | N/A | 2455.27 | 670.24 | Unknown | 371.87 | Unknown | 1413.16 | 19905 | 1330.88 | 2455.27 | -1124.39 | Yes | N/A | N/A | 2023-12-11 | 2023-12-12 | 2 | 2 | 2023-12-12 | 2023-12-27 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-27 | 2024-02-27 | 63 | 45 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-15 | Unknown | Unknown | 2024-03-15 | 2024-03-15 | 1 | 1 | 65 | 47 | 17 | 13 | 82 | 60 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 43.05 | 43.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-24 | -439 | -314 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-07 | 2024-06-07 | 2024-12-03 | IOU Designed & Installed | N/A | No | N/A | 1652.33 | -32.74 | Unknown | Unknown | Unknown | 1685.07 | 3981 | 1713.96 | 1652.33 | 61.63 | Yes | N/A | N/A | 2024-05-07 | 2024-04-12 | Unknown | Unknown | 2024-04-12 | 2024-06-07 | 57 | 41 | 2024-06-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-07 | 2024-12-03 | 180 | 128 | Unknown | Unknown | Unknown | Unknown | 2024-12-03 | 2024-12-16 | 14 | 10 | 2024-12-16 | 2024-12-12 | Unknown | Unknown | 180 | 128 | 71 | 51 | 251 | 179 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2019-03-30 | 2118 | 1513 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-08 | 2024-09-24 | 2025-01-15 | IOU Designed & Installed | N/A | No | N/A | 101.39 | 44.96 | Unknown | Unknown | Unknown | 56.43 | 3981 | 4551.28 | 101.39 | 4449.89 | Yes | N/A | N/A | 2024-08-08 | 2024-09-24 | 48 | 34 | 2024-09-24 | 2024-12-03 | 71 | 51 | Unknown | Unknown | Unknown | Unknown | 2024-09-25 | 2024-10-25 | 31 | 23 | 2024-12-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-15 | 2025-01-15 | 1 | 1 | 2025-01-15 | 2025-01-15 | 1 | 1 | 48 | 34 | 104 | 76 | 152 | 110 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2019-01-24 | 1975 | 1412 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-30 | 2023-11-30 | 2024-06-20 | IOU Designed & Installed | N/A | No | N/A | 102.65 | -10.25 | Unknown | Unknown | -527.81 | 640.71 | Unknown | 503.1 | 102.65 | 400.45 | Yes | N/A | N/A | 2023-11-30 | 2023-11-23 | Unknown | Unknown | 2023-11-23 | 2023-12-06 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-06 | 2024-04-29 | 146 | 104 | Unknown | 2024-04-30 | Unknown | Unknown | 2024-06-20 | 2024-07-11 | 22 | 16 | 2024-07-11 | 2024-06-21 | Unknown | Unknown | 146 | 104 | 36 | 26 | 182 | 130 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R15 | UG | Applicant Design | Residential | N/A | San Diego | N/A | 222214 | 222214 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-03-20 | 813 | 582 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-09 | 2022-09-09 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 55292.99 | 20624.75 | Unknown | Unknown | 2171.26 | 32496.98 | 0 | 28837.47 | 55292.99 | -26455.52 | Yes | N/A | N/A | 2022-09-09 | 2023-05-01 | 235 | 167 | 2023-05-01 | 2023-10-11 | 164 | 118 | 2023-05-24 | 2024-04-08 | 251 | 181 | 2023-09-22 | 2024-01-11 | 112 | 80 | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-29 | Unknown | Unknown | Unknown | 2025-06-10 | Unknown | Unknown | 2025-06-10 | 2025-06-10 | 1 | 1 | 486 | 348 | 277 | 199 | 763 | 547 | Steps 2,3,5,6,7 | 339 | 241 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-12 | -640 | -459 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-04 | 2025-04-04 | 2025-04-08 | IOU Designed & Installed | N/A | No | N/A | 391.33 | -8.08 | Unknown | Unknown | Unknown | 399.41 | 3981 | 1740.25 | 391.33 | 1348.92 | Yes | N/A | N/A | 2025-04-04 | 2025-04-04 | 1 | 1 | 2025-04-04 | 2025-04-04 | 1 | 1 | 2025-04-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-04 | 2025-04-08 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | 2025-04-08 | 2025-05-13 | 36 | 26 | 2025-05-13 | 2025-05-13 | 1 | 1 | 6 | 4 | 38 | 28 | 44 | 32 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 150.05 | 150.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-18 | -297 | -214 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-27 | 2023-04-27 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1274.97 | -13.54 | Unknown | Unknown | Unknown | 1288.51 | 3981 | 1152.44 | 1274.97 | -122.53 | Yes | N/A | N/A | 2023-04-27 | 2023-05-04 | 8 | 6 | 2023-05-04 | 2023-11-02 | 183 | 131 | 2023-11-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-02 | Unknown | Unknown | Unknown | Unknown | 2024-06-06 | Unknown | Unknown | Unknown | 2024-06-26 | Unknown | Unknown | 2024-06-26 | 2024-06-25 | Unknown | Unknown | 8 | 6 | 183 | 131 | 191 | 137 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-06 | -645 | -462 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-17 | 2024-06-19 | 2024-06-21 | IOU Designed & Installed | N/A | No | N/A | 754.98 | -14.6 | Unknown | Unknown | Unknown | 769.58 | Unknown | 1511 | 754.98 | 756.02 | Yes | N/A | N/A | 2024-06-17 | 2024-05-10 | Unknown | Unknown | 2024-05-10 | 2024-06-19 | 41 | 29 | 2024-06-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-19 | 2024-06-21 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2024-06-21 | 2024-07-30 | 40 | 28 | 2024-07-30 | 2024-07-30 | 1 | 1 | 3 | 3 | 82 | 58 | 85 | 61 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 2.7 | 2.7 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-02 | -507 | -362 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-28 | 2024-04-26 | 2024-05-23 | IOU Designed & Installed | N/A | No | N/A | 5.61 | -4.99 | Unknown | Unknown | Unknown | 10.6 | Unknown | 1261.92 | 5.61 | 1256.31 | Yes | N/A | N/A | 2024-03-28 | 2024-04-23 | 27 | 19 | 2024-04-23 | 2024-04-26 | 4 | 4 | 2024-04-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-26 | 2024-05-23 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | 2024-05-23 | 2024-06-13 | 22 | 16 | 2024-06-13 | 2024-06-13 | 1 | 1 | 55 | 39 | 27 | 21 | 82 | 60 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 10 | 10 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-02 | -500 | -357 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-23 | 2024-07-26 | 2024-07-30 | IOU Designed & Installed | N/A | No | N/A | 1287.5 | 380.61 | Unknown | Unknown | Unknown | 906.89 | 3885 | 1464.81 | 1287.5 | 177.31 | Yes | N/A | N/A | 2024-07-23 | 2024-02-09 | Unknown | Unknown | 2024-02-09 | 2024-07-26 | 169 | 121 | 2024-07-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-26 | 2024-07-30 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | 2024-07-30 | 2024-09-20 | 53 | 39 | 2024-09-20 | 2024-09-20 | 1 | 1 | 5 | 3 | 223 | 161 | 228 | 164 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-17 | -400 | -287 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-17 | 2023-04-28 | 2023-12-15 | IOU Designed & Installed | N/A | No | N/A | 474.72 | -9.92 | Unknown | Unknown | 5.02 | 479.62 | 3885 | 656.47 | 474.72 | 181.75 | Yes | N/A | N/A | 2023-03-17 | 2023-04-28 | 43 | 31 | 2023-04-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-28 | 2023-12-15 | 232 | 166 | Unknown | 2023-11-28 | Unknown | Unknown | 2023-12-15 | 2023-12-15 | 1 | 1 | 2023-12-15 | 2023-12-14 | Unknown | Unknown | 275 | 197 | 1 | 1 | 276 | 198 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-17 | 191 | 136 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-22 | 2024-04-22 | 2024-08-12 | IOU Designed & Installed | N/A | No | N/A | 53.03 | Unknown | Unknown | Unknown | Unknown | 53.03 | 3941 | 674.19 | 53.03 | 621.16 | Yes | N/A | N/A | 2024-04-22 | 2024-04-01 | Unknown | Unknown | 2024-04-01 | 2024-04-22 | 22 | 16 | 2024-04-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-24 | 2024-08-12 | 111 | 79 | Unknown | Unknown | Unknown | Unknown | 2024-08-12 | 2024-08-26 | 15 | 11 | 2024-08-26 | 2024-08-26 | 1 | 1 | 111 | 79 | 38 | 28 | 149 | 107 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2020-08-27 | 984 | 703 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-20 | 2023-03-20 | 2023-04-24 | IOU Designed & Installed | N/A | No | N/A | 1108.13 | Unknown | Unknown | Unknown | Unknown | 1108.13 | 3981 | 987.92 | 1108.13 | -120.21 | Yes | N/A | N/A | 2023-03-20 | 2023-03-20 | 1 | 1 | 2023-03-20 | 2023-03-30 | 11 | 9 | Unknown | Unknown | Unknown | Unknown | 2023-05-02 | 2023-05-02 | 1 | 1 | 2023-03-30 | 2023-05-03 | 35 | 25 | Unknown | 2023-04-20 | Unknown | Unknown | 2023-04-24 | 2023-05-17 | 24 | 18 | 2023-05-17 | 2023-05-08 | Unknown | Unknown | 36 | 26 | 36 | 28 | 72 | 54 | Steps 2,3,5,6,7 | 33 | 23 | Meeting | Meeting | Not Available | N/A
| R16 | Both | IOU Design | Residential | Underserved Community | ESCONDIDO | ESCONDIDO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-12 | -407 | -292 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-12 | 2024-03-12 | 2024-05-08 | IOU Designed & Installed | N/A | No | N/A | 14605.09 | Unknown | Unknown | Unknown | Unknown | 14605.09 | Unknown | 2224.8 | 14605.09 | -12380.29 | Yes | N/A | N/A | 2024-03-12 | 2024-02-13 | Unknown | Unknown | 2024-02-13 | 2024-05-07 | 85 | 61 | Unknown | Unknown | Unknown | Unknown | 2024-04-22 | 2024-05-06 | 7 | 3 | 2024-05-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-08 | 2024-10-31 | 177 | 127 | 2024-10-31 | 2024-10-31 | 1 | 1 | 0 | 0 | 270 | 192 | 270 | 192 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | 22.05 | 22.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-21 | -336 | -241 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-28 | 2024-03-28 | 2024-04-08 | IOU Designed & Installed | N/A | No | N/A | -13.55 | -12.15 | Unknown | Unknown | Unknown | -1.4 | Unknown | 169.69 | -13.55 | 183.24 | Yes | N/A | N/A | 2024-03-28 | 2024-03-27 | Unknown | Unknown | 2024-03-27 | 2024-04-08 | 13 | 9 | 2024-04-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-08 | 2024-04-08 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-04-08 | 2024-04-19 | 12 | 10 | 2024-04-19 | 2024-04-19 | 1 | 1 | 1 | 1 | 26 | 20 | 27 | 21 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-30 | -712 | -509 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-09 | 2025-06-09 | 2025-06-16 | IOU Designed & Installed | N/A | No | N/A | 64.74 | Unknown | Unknown | Unknown | Unknown | 64.74 | 3981 | 1203.84 | 64.74 | 1139.1 | Yes | N/A | N/A | 2025-06-09 | 2025-06-09 | 1 | 1 | 2025-06-09 | 2025-06-09 | 1 | 1 | 2025-06-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-09 | 2025-06-16 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2025-06-16 | 2025-06-17 | 2 | 2 | 2025-06-17 | 2025-06-17 | 1 | 1 | 9 | 7 | 4 | 4 | 13 | 11 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 39.35 | 39.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-01 | -159 | -114 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-17 | 2023-08-30 | Unknown | IOU Designed & Installed | N/A | No | N/A | 9.32 | Unknown | Unknown | Unknown | Unknown | 9.32 | 7962 | 887.73 | 9.32 | 878.41 | Yes | N/A | N/A | 2023-08-17 | 2023-08-30 | 14 | 10 | 2023-08-30 | 2023-08-30 | 1 | 1 | 2023-08-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-28 | Unknown | Unknown | 2024-10-28 | 2024-10-24 | Unknown | Unknown | 14 | 10 | 1 | 1 | 15 | 11 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | 61.05 | 61.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-24 | -686 | -491 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-08 | 2024-07-08 | 2024-07-31 | IOU Designed & Installed | N/A | No | N/A | 6.15 | Unknown | Unknown | Unknown | Unknown | 6.15 | Unknown | 186.52 | 6.15 | 180.37 | Yes | N/A | N/A | 2024-07-08 | 2024-07-05 | Unknown | Unknown | 2024-07-05 | 2024-07-29 | 25 | 17 | 2024-07-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-29 | 2024-07-31 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2024-07-31 | 2024-08-07 | 8 | 6 | 2024-08-07 | 2024-08-07 | 1 | 1 | 3 | 3 | 34 | 24 | 37 | 27 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | POWAY | N/A | 4.34 | 4.34 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-13 | -208 | -150 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-20 | 2024-03-22 | 2024-06-20 | IOU Designed & Installed | N/A | No | N/A | 47.15 | -10.31 | Unknown | Unknown | 33.77 | 23.69 | 3981 | 1425.92 | 47.15 | 1378.77 | Yes | N/A | N/A | 2024-03-20 | 2024-04-29 | 41 | 29 | 2024-04-29 | 2024-05-28 | 30 | 22 | 2024-05-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-28 | 2024-06-20 | 24 | 18 | Unknown | Unknown | Unknown | Unknown | 2024-06-20 | 2025-05-20 | 335 | 239 | 2025-05-20 | 2025-05-19 | Unknown | Unknown | 65 | 47 | 365 | 261 | 430 | 308 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 96.05 | 96.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-27 | -522 | -375 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-09 | 2024-09-06 | 2024-10-11 | IOU Designed & Installed | N/A | No | N/A | -868.92 | -11.11 | Unknown | Unknown | -1444 | 586.19 | Unknown | 1354.07 | -868.92 | 2222.99 | Yes | N/A | N/A | 2024-08-09 | 2024-07-18 | Unknown | Unknown | 2024-07-18 | 2024-09-06 | 51 | 37 | 2024-09-06 | 2024-10-08 | 33 | 23 | Unknown | Unknown | Unknown | Unknown | 2024-10-08 | 2024-10-11 | 4 | 4 | Unknown | Unknown | Unknown | Unknown | 2024-10-11 | 2024-10-21 | 11 | 7 | 2024-10-21 | 2024-10-21 | 1 | 1 | 37 | 27 | 63 | 45 | 100 | 72 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | JAMUL | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-16 | -315 | -226 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-03 | 2024-10-03 | 2024-10-30 | IOU Designed & Installed | N/A | No | N/A | -1921.5 | 1740.84 | Unknown | 175.06 | -4645 | 807.6 | Unknown | 4644.6 | -1921.5 | 6566.1 | Yes | N/A | N/A | 2024-10-03 | 2024-09-30 | Unknown | Unknown | 2024-09-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-30 | 2024-11-05 | 7 | 5 | 2024-11-05 | 2024-11-05 | 1 | 1 | 0 | 0 | 8 | 6 | 8 | 6 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-10 | -498 | -357 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-27 | 2023-07-27 | 2023-11-17 | IOU Designed & Installed | N/A | No | N/A | 696.23 | 426.13 | Unknown | Unknown | Unknown | 270.1 | Unknown | 153.83 | 696.23 | -542.4 | Yes | N/A | N/A | 2023-07-27 | 2023-08-14 | 19 | 13 | 2023-08-14 | 2023-08-14 | 1 | 1 | 2023-08-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-14 | 2023-11-17 | 96 | 70 | Unknown | Unknown | Unknown | Unknown | 2023-11-17 | 2023-11-29 | 13 | 9 | 2023-11-29 | 2023-11-29 | 1 | 1 | 115 | 83 | 15 | 11 | 130 | 94 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 12 | 12 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-12 | -115 | -84 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-06 | 2024-05-06 | 2024-05-06 | IOU Designed & Installed | N/A | No | N/A | -12.52 | -10.17 | Unknown | Unknown | Unknown | -2.35 | 3981 | 1721.92 | -12.52 | 1734.44 | Yes | N/A | N/A | 2024-05-06 | 2024-04-17 | Unknown | Unknown | 2024-04-17 | 2024-05-06 | 20 | 14 | 2024-05-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-06 | 2024-05-06 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-05-06 | 2024-05-20 | 15 | 11 | 2024-05-20 | 2024-05-20 | 1 | 1 | 1 | 1 | 36 | 26 | 37 | 27 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-19 | -337 | -242 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-05 | 2023-05-05 | 2023-05-17 | IOU Designed & Installed | N/A | No | N/A | 373612.56 | 174785.93 | Unknown | 89.36 | 6925.14 | 191812.13 | 3981 | 244.36 | 373612.56 | -373368.2 | Yes | N/A | N/A | 2023-05-05 | 2023-05-10 | 6 | 4 | 2023-05-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-10 | 2023-05-17 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2023-05-17 | 2024-01-07 | 236 | 168 | 2024-01-07 | 2023-05-18 | Unknown | Unknown | 14 | 10 | 236 | 168 | 250 | 178 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-23 | 259 | 186 | No | 2023-01-09 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-09 | 2023-01-12 | 2024-06-24 | IOU Designed & Installed | N/A | Yes | 520 | 16.03 | -12.36 | Unknown | Unknown | Unknown | 28.39 | 3981 | 718.5 | 16.03 | 702.47 | Yes | N/A | N/A | 2023-01-09 | 2024-06-11 | 520 | 372 | 2024-06-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-01-25 | 2024-06-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-24 | 2024-07-09 | 16 | 12 | 2024-07-09 | 2024-07-08 | Unknown | Unknown | 520 | 372 | 16 | 12 | 536 | 384 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-18 | -696 | -499 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-25 | 2025-03-25 | 2025-03-28 | IOU Designed & Installed | N/A | No | N/A | 3120.71 | 697.21 | Unknown | Unknown | Unknown | 2423.5 | 3981 | 1906.34 | 3120.71 | -1214.37 | Yes | N/A | N/A | 2025-03-25 | 2025-03-25 | 1 | 1 | 2025-03-25 | 2025-03-25 | 1 | 1 | 2025-03-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-25 | 2025-03-28 | 4 | 4 | Unknown | Unknown | Unknown | Unknown | 2025-03-28 | 2025-04-21 | 25 | 17 | 2025-04-21 | 2025-04-21 | 1 | 1 | 5 | 5 | 27 | 19 | 32 | 24 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A

## Tariff Ongoing
Preliminary Project Information | [7 empty] | Site Capacity & Capacity Requested |  |  |  | Upstream Capacity |  |  |  | Customer Desired Energization Date vs Final Energization Date |  |  | Additional Capacity, Flexible Service Option, & Cancelled/Delayed Project Information | [10 empty] | Tariff Upgrade |  |  | Customer Elect and Customer Project Delay |  |  |  | Costing Components | [9 empty] | Step 1 Intake (Customer) | [6 empty] | Step 2: Engineering and Design (IOU) |  |  |  | Step 3: Customer Dependencies (Customer) |  |  |  | Step 4: Utility Dependencies (IOU) |  |  |  | Step 5: Project Site Readiness (Customer) |  |  |  | Step 6: Project Site Readiness (IOU) |  |  |  | Step 7: Construction (IOU) |  |  |  | Step 8: Service Energization (IOU) |  |  |  | Customer Controlled Steps |  | IOU Controlled Steps |  | IOU & Customer Controlled Steps |  | Concurrent Steps |  |  | Meeting/Exceeding Energization Targets
Project Identifier # (project #) | Tariff (R15, R16, R29/R45, Combo) | OH (Overhead) or UG (Underground) | Applicant or IOU Design | Business Class (requested end-use) | Community type: Disadvantage Community (DAC) Underserved Community Tribal Community | City Project is Located in (City) | AHJ (Authority Having Jurisdiction) for permitting based off Project's location (AHJ) | Total Site Capacity at Time of Customer's Application for Service (kW) | Total Site Capacity Requested (kW) | Additional Capacity (kW) installed for future electric load deployment (as applicable) | Capacity Request Category: <1MW 1MW to 2M >2MW | Project triggered for upstream capacity project (Yes/No) | Date IOU identifies the need for an upstream capacity project and alerts customer of need for upstream capacity project (Date) | Date IOU completes the upstream capacity project (Date) | Time to complete upstream capacity project (Calendar Days) | Customer Desired Energization Date (Date) | Difference from Customer Desired Energization Date and Final Energization Date (Calendar Days) | Difference from Customer Desired Energization Date and Final Energization Date (Business Days) | Did customer install additional capacity to support future load growth? (Yes or No) | Identify when in the energization process the customer requested a change in design or scope (Date) | Identify when in energization process the customer requested a change in design or scope (Energization Step) | Customer cancelled/delayed project (as needed) (Yes or No) | Customer elected to install additional capacity to anticipate associated future load growth as indicated on customer's application (Yes or No) | Estimated timing for when customer anticipates additional capacity necessary as indicated on customer's application (Date) | Total additional kW capacity for the necessary future upgrade as listed on customer's application (kW) | If full energization of applicant site not feasible in a timely manner, explanation whether load management/flexible service options were installed/utilized to provide applicant with timely service | Amount of load (kW) provided to applicant using flexible service options (kW) | At the time energization provided, remaining (or total) unserved load requested by the applicant (kW) | Estimate when full service will be provided to the applicant for customers using flexible service and/or receiving tiered load schedules (Date) | Date when need for R15/16/29/45 upgrade identified (Date) | Date when Planning Work started R15/16/29/45 upgrade (Date) | Date when Construction Work started R15/16/29/45 upgrade (Date) | For R15/16 tariffs, did customer elect to take on typical IOU completed scope and vice versa. (i.e. Applicant Design or Applicant Install) (N/A, Customer elected Applicant Design/Install/Both) | For R15/16 tariffs, did customer elect to take on typical IOU completed scope and vice versa. Indicate Applicant Design or Applicant Install (N/A, Customer elected, IOU elected) Specify energization steps. (List Energization Steps) | For R15/R16 tariffs, project was delayed due to customer requested change in design or change in project scope (Yes, No) | For R15/R16 tariffs, the time the project was delayed due to customer requested change in design or change in project scope (Calendar Days) | Total Cost ($$$) to Complete All Energization Requests | Total Staffing, Labor, and Material Cost ($$$ Capital and Expense) | Total upstream capacity project cost ($$$) | Project Costs ($$$) for all IOU equipment for upstream capacity projects, Electric Rule 15, Electric Rule 16, and Electric Rule 29/45. | Project Costs ($$$) for anything else IOU covers | Total Construction/Overhead Costs ($$$) | Customer Allowance ($$$) | Estimated Costs ($$$) at Time of Design | Actual Costs ($$$) at Time of Energization | Difference of Estimated and Actual Costs at Time of Energization ($$$) | IOU assigned account/project manager for initial application (within 10 days) (Yes/No) | Date of IOU rejection of application (Date) | IOU reason for rejection of application (Reason) | Step 1 - Data Point Start 1) Intake Start Date (Date) | Step 1 - Data Point End 2) Intake End (Date) | Step 1: Intake (Calendar Days) | Step 1: Intake (Business Days) | Step 2 - Data Point Start 2) Engineering and Design Start (Date) | Step 2 - Data Point End 3) Engineering and Design End (Date) | Step 2: Engineering and Design (Calendar Days) | Step 2: Engineering and Design (Business Days) | Step 3 - Data Point Start 3) Customer Dependencies Start (Date) | Step 3 - Data Point End 4) Customer Dependencies End (Date) | Step 3: Customer Dependencies (Calendar Days) | Step 3: Customer Dependencies (Business Days) | Step 4 - Data Point Start 4) Utility Dependencies Start (Date) | Step 4 - Data Point End 5) Utility Dependencies End (Date) | Step 4: Utility Dependencies (Calendar Days) | Step 4: Utility Dependencies (Business Days) | Step 5 - Data Point Start 5) Customer Site Readiness Start (Date) | Step 5 - Data Point End 6) Customer Site Readiness End (Date) | Step 5: Site Readiness (Calendar Days) | Step 5: Site Readiness (Business Days) | Step 6 - Data Point Start 6) IOU Site Readiness Start (Date) | Step 6 - Data Point End 7) Site Readiness IOU End (Date) | Step 6: Site Readiness (Calendar Days) | Step 6: Site Readiness (Business Days) | Step 7 - Data Point Start 7) Construction Start (Date) | Step 7 - Data Point End 8) Construction End (Date) | Step 7: Construction (Calendar Days) | Step 7: Construction (Business Days) | Step 8 - Data Point Start 8) Service Energization Start (Date) | Step 8 - Data Point End 9) Service Energization End (Date) | Step 8: Service Energization (Calendar Days) | Step : Service Energization (Business Days) | Customer Controlled Steps: Step 1 - Intake, Step 3 - Customer Dependencies, & Step 5 - Site Readiness (Customer) (Calendar Days) | Customer Controlled Steps: Step 1 - Intake, Step 3 - Customer Dependencies, & Step 5 - Site Readiness (Customer) (Business Days) | IOU Controlled Steps: Step 2 - Engineering & Design, Step 4 - Utility Dependencies, Step 6 - Site Readiness (IOU), Step 7 - Construction, Step 8 - Service Energization (Calendar Days) | IOU Controlled Steps: Step 2 - Engineering & Design, Step 4 - Utility Dependencies, Step 6 - Site Readiness (IOU), Step 7 - Construction, Step 8 - Service Energization (Business Days) | End to End Cycle Time (1 to 8) (Calendar Days) | End to End Cycle Time (1 to 8) (Business Days) | Energization Steps Completed Concurrently (Energization Step(s) Listed) | Total time for Energization Steps Completed Concurrently (Calendar Days) | Total time for Energization Steps Completed Concurrently (Business Days) | R15/R16/R29/R45 Energization Average meeting/exceeding Average Energization Target (Meeting/Exceeding) | R15/R16/R29/R45 Energization Maximum meeting/exceeding Maximum Energization Target (Meeting/Exceeding) | R15/R16/R29/R45 Energization Reasoning as to why exceeded average/maximum Energization Target (Reasoning) | Location of project exceeding the maximum energization target: Location (circuit level)
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-30 | 2025-05-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 15112.26 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-30 | 2025-05-30 | 1 | 1 | 2025-05-30 | 2025-07-07 | 39 | 27 | Unknown | Unknown | Unknown | Unknown | 2025-06-24 | 2025-07-10 | 13 | 11 | 2025-07-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-08-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | Both | IOU Design | Residential | Underserved Community | NATIONAL CITY | N/A | 7150 | 7150 | Not Available | >2MW | No | N/A | N/A | N/A | 2025-08-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-30 | 2024-04-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | 740.06 | -21.62 | Unknown | Unknown | 59.83 | 701.85 | 26834.33 | 1840.27 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-30 | 2024-04-30 | 1 | 1 | 2024-04-30 | 2024-05-16 | 17 | 13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-16 | Unknown | Unknown | Unknown | Unknown | 2024-06-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | CORONADO | CORONADO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-20 | 2024-06-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1440.69 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-20 | 2024-03-27 | Unknown | Unknown | 2024-03-27 | 2024-06-20 | 86 | 62 | 2024-06-20 | 2024-07-10 | 3 | 3 | 2024-07-01 | 2024-07-08 | 8 | 6 | 2024-06-20 | 2025-08-25 | 432 | 308 | Unknown | Unknown | Unknown | Unknown | 2025-08-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-29 | 2025-01-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1982.68 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-29 | 2025-01-29 | 1 | 1 | 2025-01-29 | 2025-01-29 | 1 | 1 | 2025-01-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SANTEE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-06 | 2023-03-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 502.08 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-06 | 2023-03-14 | 9 | 7 | 2023-03-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | NATIONAL CITY | NATIONAL CITY | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2025-04-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-30 | 2024-05-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2024-04-30 | 2024-05-02 | 3 | 3 | 2024-05-02 | 2024-09-05 | 127 | 91 | 2024-07-24 | 2024-07-25 | 2 | 2 | 2024-05-30 | 2024-08-21 | 84 | 60 | 2024-09-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-18 | 2024-11-19 | 2025-01-09 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1620.99 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-18 | 2024-11-06 | Unknown | Unknown | 2024-11-06 | 2024-11-20 | 15 | 11 | 2024-11-20 | Unknown | Unknown | Unknown | 2024-11-20 | 2024-11-25 | 6 | 4 | 2024-11-20 | 2025-01-09 | 51 | 37 | Unknown | Unknown | Unknown | Unknown | 2025-01-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-31 | 2024-12-31 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3163.36 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-31 | 2024-12-31 | 1 | 1 | 2024-12-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | CHULA VISTA | SAN DIEGO | 2 | 2 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-12 | 2024-11-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2388 | 851.4 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-12 | 2024-11-12 | 1 | 1 | 2024-11-12 | 2025-03-11 | 120 | 86 | Unknown | Unknown | Unknown | Unknown | 2025-02-28 | 2025-03-22 | 23 | 16 | 2025-03-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 2.7 | 2.7 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-29 | 2025-01-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1899.5 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-29 | 2025-01-30 | 2 | 2 | 2025-01-30 | 2025-01-30 | 1 | 1 | 2025-01-30 | 2025-02-11 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2025-02-11 | 2025-08-18 | 189 | 135 | Unknown | Unknown | Unknown | Unknown | 2025-08-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-23 | 2024-05-08 | 2024-06-06 | IOU Designed & Installed | N/A | No | Unknown | 1176.39 | -31.43 | Unknown | Unknown | 120.7 | 1087.12 | 3241 | 911.58 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-23 | 2024-05-08 | 16 | 12 | 2024-05-08 | 2024-05-08 | 1 | 1 | 2024-05-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-08 | 2024-06-06 | 30 | 22 | Unknown | Unknown | Unknown | Unknown | 2024-06-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 98.05 | 98.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-27 | 2024-04-05 | 2024-05-13 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 3253.57 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-27 | 2024-04-05 | 10 | 8 | 2024-04-05 | 2024-04-05 | 1 | 1 | 2024-04-05 | 2024-04-29 | 25 | 17 | Unknown | Unknown | Unknown | Unknown | 2024-05-02 | 2024-05-13 | 12 | 8 | Unknown | 2024-05-07 | Unknown | Unknown | 2024-05-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-10 | 2024-12-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2831.38 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-10 | 2025-01-13 | 35 | 25 | 2025-01-13 | Unknown | Unknown | Unknown | 2025-02-19 | 2025-02-19 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2025-01-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-26 | 2023-12-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 515.81 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-26 | 2023-12-26 | 1 | 1 | 2023-12-26 | 2023-12-26 | 1 | 1 | 2023-12-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | NATIONAL CITY | N/A | 177.05 | 177.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-18 | 2024-05-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1282.49 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-18 | 2024-02-07 | Unknown | Unknown | 2024-02-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | NATIONAL CITY | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-17 | 2023-09-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 26990 | 930.8 | Unknown | Unknown | Yes | N/A | N/A | 2023-02-17 | 2023-02-17 | 1 | 1 | 2023-02-17 | 2023-11-21 | 278 | 198 | 2023-10-23 | 2024-04-23 | 27 | 21 | 2023-09-14 | 2025-02-14 | 144 | 102 | 2023-11-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-31 | 2023-06-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 868.14 | Unknown | Unknown | Yes | N/A | N/A | 2023-05-31 | 2023-06-01 | 2 | 2 | 2023-06-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-19 | 2025-06-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1011.69 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-19 | 2025-06-17 | 30 | 22 | 2025-06-17 | 2025-07-10 | 24 | 18 | 2025-05-21 | 2025-06-17 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | 2025-06-17 | 2025-07-10 | 24 | 18 | Unknown | Unknown | Unknown | Unknown | 2025-07-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | SAN CLEMENTE | 151 | 151 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-02 | 2023-03-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 13060.85 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-02 | 2023-07-25 | 146 | 104 | 2023-07-25 | 2025-01-08 | 534 | 382 | 2024-03-25 | 2024-03-25 | 1 | 1 | 2023-08-01 | 2024-12-02 | 25 | 19 | 2025-01-08 | Unknown | Unknown | Unknown | Unknown | 2025-07-29 | Unknown | Unknown | 2025-08-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 24 | 24 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-27 | 2025-05-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1084.78 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-27 | 2025-05-16 | Unknown | Unknown | 2025-05-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-28 | 2025-08-19 | 84 | 60 | Unknown | Unknown | Unknown | Unknown | 2025-08-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A |  | ENCINITAS | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-13 | 2025-01-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1524.25 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-13 | 2024-08-28 | 16 | 12 | 2024-08-28 | 2025-04-04 | 220 | 158 | Unknown | Unknown | Unknown | Unknown | 2025-03-08 | 2025-08-28 | 58 | 42 | 2025-04-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-05 | 2024-02-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 163.83 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-05 | 2023-11-29 | Unknown | Unknown | 2023-11-29 | 2024-02-16 | 80 | 58 | 2024-02-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R29/R45 | UG | IOU Design | Commercial | Underserved Community | CHULA VISTA | CHULA VISTA | 1344 | 1344 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2024-10-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-14 | 2024-03-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 146811.65 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-14 | 2024-07-18 | 156 | 112 | 2024-07-18 | Unknown | Unknown | Unknown | 2024-03-22 | 2024-10-28 | 44 | 32 | 2024-03-07 | 2025-04-02 | 182 | 130 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 41 | 41 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-23 | 2024-09-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1638.29 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-23 | 2024-08-16 | Unknown | Unknown | 2024-08-16 | 2024-09-30 | 46 | 32 | 2024-09-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-07 | 2025-05-07 | 2025-06-03 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2567.76 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-07 | 2025-05-07 | 1 | 1 | 2025-05-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN MARCOS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-12 | 2024-11-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1131.73 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-12 | 2025-02-21 | 102 | 74 | 2025-02-21 | 2025-02-26 | 6 | 4 | 2025-02-26 | 2025-06-04 | 99 | 71 | Unknown | Unknown | Unknown | Unknown | 2025-06-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 11 | 11 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-18 | 2024-03-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1038.55 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-18 | 2023-12-21 | Unknown | Unknown | 2023-12-21 | 2024-05-23 | 155 | 111 | 2024-05-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-05-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-12 | 2023-12-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 8370 | 705.44 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-12 | 2023-10-10 | 29 | 21 | 2023-10-10 | 2024-01-31 | 114 | 82 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 5 | 5 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-17 | 2025-01-31 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1791.07 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-17 | 2025-01-31 | 46 | 34 | 2025-01-31 | 2025-01-31 | 1 | 1 | 2025-01-31 | 2025-08-25 | 207 | 147 | Unknown | Unknown | Unknown | Unknown | 2025-06-02 | 2025-08-25 | 85 | 61 | Unknown | Unknown | Unknown | Unknown | 2025-08-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 13.5 | 13.5 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-12 | 2024-12-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7962 | 1801.2 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-12 | 2024-11-12 | 1 | 1 | 2024-11-12 | 2025-01-10 | 60 | 44 | 2025-01-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | 87.75 | 87.75 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-18 | 2024-11-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 801.19 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-18 | 2024-10-29 | Unknown | Unknown | 2024-10-29 | 2024-12-06 | 39 | 29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-06 | Unknown | Unknown | Unknown | Unknown | 2025-04-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-20 | 2025-02-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 35829 | 981.49 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-20 | 2025-05-08 | 78 | 56 | 2025-05-08 | 2025-06-25 | 49 | 35 | Unknown | Unknown | Unknown | Unknown | 2025-06-04 | 2025-06-24 | 21 | 15 | 2025-06-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | ESCONDIDO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-20 | 2025-03-20 | 2025-06-26 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1562.54 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-20 | 2025-03-20 | 1 | 1 | 2025-03-20 | 2025-03-20 | 1 | 1 | 2025-03-20 | Unknown | Unknown | Unknown | 2025-03-24 | 2025-04-08 | 16 | 12 | 2025-03-20 | 2025-06-26 | 99 | 71 | Unknown | Unknown | Unknown | Unknown | 2025-06-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | Applicant Design | Commercial | Underserved Community | San Diego | San Diego | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-05 | 2023-06-05 | Unknown | Both (Customer elected Applicant Design & Install) | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 1069941.94 | 178077.06 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-05 | 2024-09-12 | 466 | 334 | 2024-09-12 | 2025-05-28 | 259 | 185 | 2024-09-27 | 2025-05-27 | 165 | 117 | 2025-05-21 | 2025-07-09 | 31 | 21 | 2025-05-28 | Unknown | Unknown | Unknown | 2025-07-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-11 | 2024-07-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 697.1 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-11 | 2024-06-04 | Unknown | Unknown | 2024-06-04 | 2024-07-29 | 56 | 40 | 2024-07-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 5 | 5 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-23 | 2024-12-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1779.9 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-23 | 2024-12-31 | 9 | 7 | 2024-12-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | Applicant Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-13 | 2022-09-28 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2112.51 | Unknown | Unknown | Yes | N/A | N/A | 2022-07-13 | 2023-07-14 | 367 | 263 | 2023-07-14 | 2023-09-27 | 76 | 54 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | SAN DIEGO | 25 | 25 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-09 | 2025-01-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 268816 | 10507.12 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-09 | 2025-04-02 | 84 | 60 | 2025-04-02 | 2025-06-04 | 64 | 46 | Unknown | Unknown | Unknown | Unknown | 2025-05-28 | 2025-06-13 | 17 | 13 | 2025-06-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 125.1 | 125.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-01 | 2024-08-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1213.24 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-01 | 2024-08-19 | 19 | 13 | 2024-08-19 | 2024-08-19 | 1 | 1 | 2024-08-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | DANA POINT | N/A | 110.05 | 110.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-19 | 2023-06-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2296.83 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-19 | 2023-08-14 | 57 | 41 | 2023-08-14 | 2023-09-27 | 45 | 33 | 2023-09-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2030-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-26 | 2023-09-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 405.73 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-26 | 2023-09-26 | 1 | 1 | 2023-09-26 | 2023-10-09 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 18.1 | 18.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-16 | 2025-05-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1427.04 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-16 | 2025-05-21 | 6 | 4 | 2025-05-21 | 2025-05-21 | 1 | 1 | 2025-05-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-21 | 2025-08-04 | 76 | 54 | Unknown | Unknown | Unknown | Unknown | 2025-08-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-23 | 2024-10-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3241 | 507.87 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-23 | 2024-10-23 | 1 | 1 | 2024-10-23 | 2024-10-23 | 1 | 1 | 2024-10-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 93.05 | 93.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-27 | 2023-03-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1126.65 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-27 | 2023-03-29 | 3 | 3 | 2023-03-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-12 | 2025-09-04 | 786 | 562 | Unknown | 2025-08-07 | Unknown | Unknown | 2025-09-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-18 | 2024-02-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 570933 | 48184.07 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-18 | 2023-06-01 | Unknown | Unknown | 2023-06-01 | 2024-08-29 | 456 | 326 | 2024-02-12 | 2024-08-12 | 2 | 0 | 2024-03-19 | 2024-08-22 | 48 | 36 | 2024-08-29 | Unknown | Unknown | Unknown | 2024-12-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | San Diego | SAN DIEGO | 27.15 | 27.15 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-28 | 2024-09-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 20374.76 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-28 | 2024-09-06 | 10 | 8 | 2024-09-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-20 | 2025-03-21 | 30 | 22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | DANA POINT | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-29 | 2025-04-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1522.81 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-29 | 2025-04-09 | Unknown | Unknown | 2025-04-09 | 2025-04-29 | 21 | 15 | 2025-04-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | POWAY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-16 | 2025-05-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1102.57 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-16 | 2025-05-02 | Unknown | Unknown | 2025-05-02 | 2025-05-16 | 15 | 11 | 2025-05-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-16 | 2025-08-27 | 104 | 74 | Unknown | Unknown | Unknown | Unknown | 2025-08-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 2898 | 2898 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-12-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-14 | 2024-10-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 47772 | 2019.62 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-14 | 2024-09-04 | Unknown | Unknown | 2024-09-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | Applicant Design | Commercial | Underserved Community | San Diego | COUNTY OF SAN DIEGO-SOUTH of 56, SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-29 | 2024-02-29 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2221.25 | 40630.67 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-29 | 2024-05-16 | 78 | 56 | 2024-05-16 | 2025-02-18 | 279 | 199 | 2024-10-23 | 2025-02-13 | 3 | 3 | 2024-08-20 | 2025-02-19 | 42 | 30 | 2025-02-18 | Unknown | Unknown | Unknown | 2025-07-01 | 2025-07-21 | 21 | 15 | 2025-08-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 127 | 127 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | 2025-04-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1208.13 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-07 | 2025-04-07 | 1 | 1 | 2025-04-07 | 2025-06-26 | 81 | 59 | Unknown | Unknown | Unknown | Unknown | 2025-04-16 | 2025-04-25 | 10 | 8 | 2025-06-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-07-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-19 | Unknown | Unknown | No | 2024-03-21 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-21 | 2024-05-20 | 2024-05-31 | IOU Designed & Installed | N/A | Yes | 116 | -21.17 | -18.26 | Unknown | Unknown | Unknown | -2.91 | 3981 | 496.14 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-21 | 2024-07-12 | 114 | 82 | 2024-07-12 | 2024-07-15 | 4 | 2 | 2024-07-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-20 | 2024-05-31 | 12 | 10 | Unknown | Unknown | Unknown | Unknown | 2024-05-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | JULIAN | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-29 | 2023-06-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 877.72 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-29 | 2023-05-19 | Unknown | Unknown | 2023-05-19 | 2023-06-29 | 42 | 30 | 2023-06-29 | Unknown | Unknown | Unknown | 2023-06-29 | 2025-02-26 | 14 | 10 | 2023-07-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-26 | 2022-05-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 34965 | 1417.58 | Unknown | Unknown | Yes | N/A | N/A | 2022-05-26 | 2024-02-13 | 629 | 449 | 2024-02-13 | 2024-02-13 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-07-02 | Unknown | Unknown | 2025-08-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | ALISO VIEJO | N/A | 10 | 10 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-18 | 2025-02-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 689.42 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-18 | 2025-01-14 | Unknown | Unknown | 2025-01-14 | 2025-02-28 | 46 | 34 | 2025-02-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN JUAN CAPISTRANO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-03-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-07 | 2023-02-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 311.13 | Unknown | Unknown | Yes | N/A | N/A | 2023-02-07 | 2023-02-10 | 4 | 4 | 2023-02-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-05 | 2024-12-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2965.63 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-05 | 2025-02-21 | 79 | 57 | 2025-02-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-25 | 2024-07-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | 366.24 | 101.47 | Unknown | Unknown | 8.46 | 256.31 | 3981 | 921.91 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-25 | 2024-11-19 | 118 | 84 | 2024-11-19 | 2024-11-19 | 1 | 1 | 2024-11-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2026-03-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-04 | 2024-11-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 54814.9 | 13877 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-04 | 2025-01-13 | 71 | 51 | 2025-01-13 | 2025-05-28 | 136 | 98 | 2025-05-08 | 2025-05-08 | 1 | 1 | 2024-11-25 | 2025-06-05 | 66 | 48 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2025-08-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-10 | 2025-04-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3942.39 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-10 | 2025-04-14 | 5 | 3 | 2025-04-14 | 2025-05-23 | 40 | 30 | Unknown | Unknown | Unknown | Unknown | 2025-04-15 | 2025-04-22 | 8 | 6 | 2025-05-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-17 | 2024-12-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 22251.03 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-17 | 2024-10-09 | 23 | 17 | 2024-10-09 | 2025-04-10 | 184 | 132 | 2024-11-15 | 2025-03-10 | 81 | 57 | 2025-04-09 | 2025-04-28 | 15 | 9 | 2025-04-10 | Unknown | Unknown | Unknown | 2025-04-18 | 2025-07-11 | 85 | 61 | 2025-07-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R29/R45 | UG | IOU Design | Commercial | Underserved Community | VALLEY CENTER | COUNTY OF SAN DIEGO-NORTH of 56 | 200 | 200 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-12 | 2024-12-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 159920.66 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-12 | 2025-03-13 | 183 | 131 | 2025-03-13 | Unknown | Unknown | Unknown | 2025-04-25 | 2025-07-15 | 22 | 16 | 2025-04-16 | 2025-07-16 | 49 | 35 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-09 |  | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 590.47 | Unknown | Unknown | Yes | N/A | N/A | 2023-05-09 | 2023-03-06 | Unknown | Unknown | 2023-03-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | Underserved Community | PW 1190-C5 Harmon rch WO2 (E) | POWAY | 64512 | 64512 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-08-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-11 | 2024-01-11 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 39754.96 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-11 | 2024-08-20 | 223 | 159 | 2024-08-20 | 2025-05-05 | 259 | 185 | 2024-09-05 | 2025-07-14 | 156 | 112 | 2024-09-26 | 2025-08-15 | 136 | 98 | 2025-05-14 | Unknown | Unknown | Unknown | 2025-05-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | National City | NATIONAL CITY | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-03-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-13 | 2024-01-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 31068 | 16396.63 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-13 | 2024-01-18 | 98 | 70 | 2024-01-18 | 2025-04-30 | 469 | 335 | 2024-04-24 | 2025-04-28 | 300 | 214 | 2024-05-13 | 2025-03-12 | 95 | 69 | 2025-04-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 73.05 | 73.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-29 | 2024-08-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 744.1 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-29 | 2024-09-25 | 28 | 20 | 2024-09-25 | 2024-09-25 | 1 | 1 | 2024-09-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | RANCHO SANTA FE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-16 | 2024-02-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 308.87 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-16 | 2024-02-29 | 14 | 10 | 2024-02-29 | 2024-02-29 | 1 | 1 | 2024-02-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | Spring Valley | N/A | 3052 | 3052 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-11-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-25 | 2023-08-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | 18892.78 | 4165.63 | Unknown | Unknown | 3913.68 | 10813.47 | 67179 | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2023-07-25 | 2023-08-02 | 9 | 7 | 2023-08-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | EL CAJON, SAN DIEGO | 6 | 6 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-14 | 2024-09-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2788.14 | 84189.22 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-14 | 2024-09-13 | 31 | 23 | 2024-09-13 | 2025-05-15 | 245 | 175 | 2024-12-20 | 2025-01-22 | 28 | 18 | 2024-12-23 | 2025-05-27 | 64 | 46 | 2025-05-15 | Unknown | Unknown | Unknown | 2025-06-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-14 | 2025-05-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1185.74 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-14 | 2025-05-14 | 1 | 1 | 2025-05-14 | 2025-05-14 | 1 | 1 | 2025-05-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-14 | 2025-07-08 | 56 | 40 | Unknown | Unknown | Unknown | Unknown | 2025-07-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-28 | 2025-03-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2232.98 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-28 | 2025-03-10 | 11 | 7 | 2025-03-10 | 2025-03-10 | 1 | 1 | 2025-03-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-10 | 2025-08-26 | 170 | 122 | Unknown | Unknown | Unknown | Unknown | 2025-08-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-30 | 2025-01-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1727.53 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-30 | 2025-01-30 | 1 | 1 | 2025-01-30 | 2025-01-30 | 1 | 1 | 2025-01-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | ESCONDIDO | N/A | 65.05 | 65.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-05 | 2024-07-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 1382 | 1093.79 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-05 | 2024-06-12 | Unknown | Unknown | 2024-06-12 | 2024-07-05 | 24 | 18 | 2024-07-05 | 2024-07-05 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-07-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | Both | IOU Design | Commercial | Underserved Community | NATIONAL CITY | CHULA VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-09 | 2025-01-15 | 2025-06-18 | IOU Designed & Installed | N/A | No | Unknown | 2579.64 | 1057.4 | Unknown | Unknown | 3.99 | 1518.25 | 0 | 19194.06 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-09 | 2024-10-24 | Unknown | Unknown | 2024-10-24 | 2025-04-23 | 182 | 130 | Unknown | Unknown | Unknown | Unknown | 2025-02-20 | 2025-04-30 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-16 | Unknown | Unknown | 2025-06-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-25 | 2024-11-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3885 | 1135.72 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-25 | 2024-10-18 | Unknown | Unknown | 2024-10-18 | 2024-11-25 | 39 | 27 | 2024-11-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 43 | 43 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-17 | 2025-04-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 866.9 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-17 | 2025-04-04 | Unknown | Unknown | 2025-04-04 | 2025-08-04 | 123 | 87 | 2025-08-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 13.6 | 13.6 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-18 | 2024-04-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1055.3 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-18 | 2024-01-17 | Unknown | Unknown | 2024-01-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Residential | Underserved Community | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-22 | 2024-08-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 8552.58 | 23734.35 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-22 | 2024-07-26 | 5 | 5 | 2024-07-26 | 2025-01-21 | 180 | 128 | 2024-12-19 | 2025-08-01 | 155 | 114 | 2024-12-17 | 2025-02-15 | 41 | 28 | 2025-02-28 | Unknown | Unknown | Unknown | 2025-02-28 | 2025-08-08 | 162 | 116 | 2025-08-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | 177.1 | 177.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-17 | 2025-01-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1912.1 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-17 | 2025-01-02 | 78 | 56 | 2025-01-02 | 2025-04-21 | 110 | 78 | Unknown | Unknown | Unknown | Unknown | 2025-04-11 | 2025-04-22 | 12 | 8 | 2025-04-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Residential | Underserved Community | Spring Valley | N/A | 3052 | 3052 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-11-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-29 | 2024-01-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 15177.59 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-29 | 2024-05-01 | 94 | 68 | 2024-05-01 | 2024-08-29 | 121 | 87 | 2024-05-08 | 2024-06-03 | 27 | 19 | 2024-07-29 | 2024-08-13 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | Disadvantaged Community,Underserved Community | San Diego | San Diego | 2898 | 2898 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-12-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-03 | 2024-01-03 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 76706.96 | 26596.08 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-03 | 2024-07-26 | 206 | 148 | 2024-07-26 | 2025-02-20 | 210 | 150 | 2024-08-09 | 2025-02-18 | 75 | 53 | 2024-08-14 | 2025-03-21 | 66 | 48 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 8.1 | 8.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-05 | 2025-06-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1390.67 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-05 | 2025-06-24 | 112 | 80 | 2025-06-24 | 2025-06-24 | 1 | 1 | 2025-06-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | OH | IOU Design | Residential | Underserved Community | FALLBROOK | COUNTY OF SAN DIEGO-NORTH of 56 | 19.05 | 19.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-15 | 2024-10-09 | 2025-06-16 | IOU Designed & Installed | N/A | No | Unknown | 28439.48 | 12699.88 | Unknown | Unknown | 53.58 | 15686.02 | 1945.89 | 33551.3 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-15 | 2024-07-10 | Unknown | Unknown | 2024-07-10 | 2025-06-10 | 336 | 240 | 2025-02-11 | 2025-04-02 | 9 | 7 | 2025-04-02 | 2025-06-09 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | LEMON GROVE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-10 | 2024-12-10 | 2025-02-02 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1632.75 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-10 | 2025-01-15 | 37 | 27 | 2025-01-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-22 | 2024-07-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1234.29 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-22 | 2024-05-02 | Unknown | Unknown | 2024-05-02 | 2024-07-22 | 82 | 58 | 2024-07-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-23 | Unknown | Unknown | No | 2025-04-14 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-14 | 2025-04-14 | Unknown | IOU Designed & Installed | N/A | Yes | 14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 863.98 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-14 | 2025-04-28 | 15 | 11 | 2025-04-28 | 2025-04-28 | 1 | 1 | 2025-04-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-11 | 2025-03-20 | 2025-05-28 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 23886 | 2719.87 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-11 | 2025-04-09 | 30 | 22 | 2025-04-09 | 2025-04-10 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-10 | 2025-05-09 | 30 | 22 | Unknown | Unknown | Unknown | Unknown | 2025-05-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-06 | 2025-02-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1263.85 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-06 | 2025-01-31 | Unknown | Unknown | 2025-01-31 | 2025-02-11 | 12 | 8 | 2025-02-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-26 | 2024-04-03 | 2024-07-02 | IOU Designed & Installed | N/A | No | Unknown | 1231.81 | 370.02 | Unknown | Unknown | 55.73 | 806.06 | 3981 | 1435.78 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-26 | 2023-12-13 | Unknown | Unknown | 2023-12-13 | 2024-05-20 | 160 | 114 | 2024-05-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-20 | 2024-07-02 | 44 | 32 | Unknown | Unknown | Unknown | Unknown | 2024-07-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-21 | 2024-10-23 | 2025-06-26 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3973.02 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-21 | 2025-02-19 | 122 | 88 | 2025-02-19 | 2025-04-04 | 45 | 33 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-04 | Unknown | Unknown | Unknown | Unknown | 2025-06-24 | Unknown | Unknown | 2025-06-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 103.05 | 103.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-15 | Unknown | Unknown | No | 2024-08-07 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-07 | 2024-08-07 | Unknown | IOU Designed & Installed | N/A | Yes | 182 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 825.92 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-07 | 2025-01-10 | 157 | 113 | 2025-01-10 | 2024-09-09 | Unknown | Unknown | 2024-09-09 | 2025-07-30 | 325 | 233 | Unknown | Unknown | Unknown | Unknown | 2025-02-06 | 2025-07-16 | 161 | 115 | Unknown | Unknown | Unknown | Unknown | 2025-07-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | ALPINE | COUNTY OF SAN DIEGO-SOUTH of 56 | 50 | 50 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-24 | 2024-01-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2168.8 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-24 | 2024-01-29 | 6 | 4 | 2024-01-29 | 2024-06-12 | 136 | 98 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | N/A | VALLEY CENTER | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-03-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-29 | 2024-02-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1329.85 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-29 | 2024-02-26 | Unknown | Unknown | 2024-02-26 | 2024-03-08 | 12 | 10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | LA MESA | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-02 | 2025-06-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1124.89 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-02 | 2025-05-20 | Unknown | Unknown | 2025-05-20 | 2025-06-05 | 17 | 13 | 2025-06-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | 146.05 | 146.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-29 | 2025-01-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3202.08 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-29 | 2025-01-30 | 337 | 241 | 2025-01-30 | 2025-01-30 | 1 | 1 | 2025-01-30 | 2025-07-01 | 153 | 109 | Unknown | Unknown | Unknown | Unknown | 2025-02-03 | 2025-07-21 | 169 | 121 | Unknown | 2025-07-09 | Unknown | Unknown | 2025-07-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-27 | 2024-07-31 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 4296.29 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-27 | 2023-10-18 | 22 | 16 | 2023-10-18 | 2024-10-24 | 373 | 267 | Unknown | Unknown | Unknown | Unknown | 2025-02-11 | 2025-02-11 | 1 | 1 | 2024-10-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Residential | N/A | CB 1127-B7 | CARLSBAD | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-18 | Unknown | Unknown | No | 2021-12-09 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2021-12-09 | 2023-05-15 | Unknown | IOU Designed & Installed | N/A | Yes | 839 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 42715 | 22324.01 | Unknown | Unknown | Yes | N/A | N/A | 2021-12-09 | 2024-03-05 | 818 | 584 | 2024-03-05 | 2025-04-22 | 414 | 296 | 2023-06-21 | 2025-07-23 | 328 | 232 | 2023-10-10 | 2025-06-03 | 341 | 239 | 2025-05-21 | Unknown | Unknown | Unknown | 2025-05-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-20 | 2023-09-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3941 | 882.71 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-20 | 2023-07-07 | Unknown | Unknown | 2023-07-07 | 2023-09-20 | 76 | 54 | 2023-09-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 118.05 | 118.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-23 | 2023-08-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1570.71 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-23 | 2024-08-27 | 371 | 265 | 2024-08-27 | 2024-11-12 | 78 | 56 | 2024-11-12 | 2024-12-27 | 46 | 34 | Unknown | Unknown | Unknown | Unknown | 2024-11-12 | Unknown | Unknown | Unknown | Unknown | 2025-03-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | BONSALL | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-20 | 2025-03-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1231.32 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-20 | 2025-03-07 | Unknown | Unknown | 2025-03-07 | 2025-03-20 | 14 | 10 | 2025-03-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-05 | 2025-06-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 817.04 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-05 | 2025-05-20 | Unknown | Unknown | 2025-05-20 | 2025-06-16 | 28 | 20 | 2025-06-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN MARCOS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-11 | 2024-03-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 843.43 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-11 | 2024-10-16 | 220 | 158 | 2024-10-16 | 2024-10-16 | 1 | 1 | 2024-10-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | POWAY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-02 | 2024-10-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 8343.85 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-02 | 2024-09-30 | Unknown | Unknown | 2024-09-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-12 | 2023-05-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1584.34 | Unknown | Unknown | Yes | N/A | N/A | 2023-05-12 | 2023-05-12 | 1 | 1 | 2023-05-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-01 | 2025-05-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3241 | 383.95 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-01 | 2025-05-01 | 1 | 1 | 2025-05-01 | 2025-05-01 | 1 | 1 | 2025-05-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | CARLSBAD | 73.05 | 73.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-12 | 2024-08-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2395.75 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-12 | 2024-08-26 | 15 | 11 | 2024-08-26 | 2024-08-26 | 1 | 1 | 2024-08-26 | Unknown | Unknown | Unknown | 2024-08-20 | 2024-12-10 | 113 | 81 | 2024-08-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 96.05 | 96.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-06 | 2025-02-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1644.76 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-06 | 2025-02-12 | 7 | 5 | 2025-02-12 | 2025-03-06 | 23 | 17 | 2025-03-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 68.05 | 68.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-01 | 2024-10-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 8380.88 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-01 | 2024-03-05 | Unknown | Unknown | 2024-03-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-13 | 2025-02-20 | 8 | 6 | 2024-12-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | LAGUNA NIGUEL | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-15 | 2024-09-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7962 | 4903.13 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-15 | 2024-12-10 | 271 | 193 | 2024-12-10 | 2024-12-13 | 4 | 4 | 2024-09-17 | 2024-09-17 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-12-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | JAMUL | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-13 | 2025-03-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1667.46 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-13 | 2025-02-25 | Unknown | Unknown | 2025-02-25 | 2025-03-13 | 17 | 13 | 2025-03-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-13 | 2025-08-18 | 159 | 113 | Unknown | Unknown | Unknown | Unknown | 2025-08-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-21 | 2024-03-21 | 2024-09-06 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3837.78 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-21 | 2024-05-02 | 43 | 31 | 2024-05-02 | 2024-10-08 | 160 | 114 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-08 | Unknown | Unknown | Unknown | 2024-10-08 | 2024-10-08 | 1 | 1 | 2024-09-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | DANA POINT | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-01 | 2023-03-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 729.92 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-01 | 2023-03-10 | 10 | 8 | 2023-03-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 74 | 74 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-01 | 2024-03-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 893.06 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-01 | 2024-03-15 | 15 | 11 | 2024-03-15 | 2024-03-15 | 1 | 1 | 2024-03-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 106.2 | 106.2 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-26 | 2025-03-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 31848 | 1785.69 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-26 | 2025-04-01 | 7 | 5 | 2025-04-01 | 2025-05-12 | 42 | 30 | 2025-03-28 | 2025-04-28 | 32 | 22 | 2025-04-29 | 2025-06-16 | 49 | 35 | 2025-05-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-30 | 2024-09-09 | 2025-01-23 | IOU Designed & Installed | N/A | No | Unknown | 605.02 | -49.68 | Unknown | Unknown | 12.53 | 642.17 | 3981 | 1571.81 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-30 | 2024-09-05 | 38 | 28 | 2024-09-05 | 2024-09-09 | 5 | 3 | 2024-09-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-09 | 2025-01-23 | 137 | 99 | Unknown | Unknown | Unknown | Unknown | 2025-01-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | Applicant Design | Residential | N/A | SM 1128-H1 N. CITY PA5 MSJO (E) | SM 1128-H1 N. CITY PA5 MSJO (E) | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-27 | 2024-08-27 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 118140 | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2024-08-27 | 2024-08-23 | Unknown | Unknown | 2024-08-23 | 2025-03-07 | 197 | 141 | Unknown | Unknown | Unknown | Unknown | 2024-09-11 | 2025-07-03 | 23 | 17 | 2025-03-07 | 2025-08-07 | 154 | 110 | Unknown | Unknown | Unknown | Unknown | 2025-09-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-14 | 2025-03-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1717.18 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-14 | 2025-03-20 | 7 | 5 | 2025-03-20 | 2025-03-26 | 7 | 5 | 2025-03-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-26 | 2025-08-19 | 147 | 105 | Unknown | Unknown | Unknown | Unknown | 2025-08-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 8.35 | 8.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-29 | 2025-06-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1499.41 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-29 | 2025-06-12 | 15 | 11 | 2025-06-12 | 2025-06-19 | 8 | 6 | 2025-06-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 50 | 50 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-23 | 2024-07-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1130.51 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-23 | 2024-07-30 | 8 | 6 | 2024-07-30 | 2024-07-30 | 1 | 1 | 2024-07-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-12 | 2025-02-12 | 2025-05-02 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1635.21 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-12 | 2025-02-12 | 1 | 1 | 2025-02-12 | 2025-02-12 | 1 | 1 | 2025-02-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-12 | 2025-05-02 | 80 | 58 | Unknown | Unknown | Unknown | Unknown | 2025-05-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | CARLSBAD | N/A | 107.05 | 107.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-09 | Unknown | Unknown | No | 2025-04-30 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-30 | 2025-04-30 | Unknown | IOU Designed & Installed | N/A | Yes | 63 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1362.01 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-30 | 2025-07-01 | 63 | 45 | 2025-07-01 | 2025-07-11 | 11 | 9 | 2025-07-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-17 | 2023-05-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 135485 | 6892.81 | Unknown | Unknown | Yes | N/A | N/A | 2023-05-17 | 2023-05-17 | 1 | 1 | 2023-05-17 | 2023-06-29 | 44 | 32 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 131 | 131 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-13 | 2024-02-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1305.4 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-13 | 2024-02-16 | 4 | 4 | 2024-02-16 | 2024-02-22 | 7 | 5 | 2024-02-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | 1273.05 | 1273.05 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2026-02-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-02 | 2024-04-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 5892.66 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-02 | 2024-02-09 | Unknown | Unknown | 2024-02-09 | 2024-07-19 | 162 | 116 | 2024-07-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-19 | 2025-07-23 | 370 | 264 | Unknown | 2025-07-10 | Unknown | Unknown | 2025-07-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN YSIDRO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-09 | 2024-10-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3241 | 507.87 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-09 | 2024-10-09 | 1 | 1 | 2024-10-09 | 2024-10-09 | 1 | 1 | 2024-10-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-23 | 2025-06-11 | 2025-06-12 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1484.34 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-23 | 2025-06-09 | 18 | 12 | 2025-06-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 22 | 22 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-21 | 2024-09-24 | 2024-12-04 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1771.38 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-21 | 2024-10-16 | 149 | 107 | 2024-10-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-20 | 2024-12-04 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2024-12-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 37.05 | 37.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2028-05-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-02 | 2025-06-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1219.31 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-02 | 2025-06-04 | 3 | 3 | 2025-06-04 | 2025-06-05 | 2 | 2 | 2025-06-04 | 2025-06-05 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2025-06-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LEMON GROVE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-05 | 2023-09-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 680.92 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-05 | 2023-08-29 | Unknown | Unknown | 2023-08-29 | 2023-09-06 | 9 | 7 | 2023-09-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | Santee | SANTEE | 60 | 60 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-05 | 2024-08-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 22841.67 | 15013.47 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-05 | 2024-06-06 | 123 | 89 | 2024-06-06 | 2024-10-24 | 141 | 101 | 2024-09-27 | 2024-09-27 | 1 | 1 | 2024-10-14 | 2024-10-31 | 15 | 7 | 2024-10-24 | Unknown | Unknown | Unknown | 2025-02-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-05 | 2025-01-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 11943 | 1664.47 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-05 | 2025-01-14 | 132 | 94 | 2025-01-14 | 2025-03-17 | 63 | 45 | Unknown | Unknown | Unknown | Unknown | 2025-04-23 | 2025-05-09 | 17 | 13 | 2025-03-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | Rancho Viejo | N/A | 106.1 | 106.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-06-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-14 | 2025-04-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2025-04-14 | 2024-07-05 | Unknown | Unknown | 2024-07-05 | 2025-06-18 | 349 | 249 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-18 | 2025-04-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-25 | 2025-01-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1845.21 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-25 | 2025-01-08 | Unknown | Unknown | 2025-01-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-15 | 2024-05-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 4413.26 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-15 | 2024-07-31 | 78 | 56 | 2024-07-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | CORONADO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-11 | 2024-12-11 | 2025-06-19 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1711.51 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-11 | 2024-12-11 | 1 | 1 | 2024-12-11 | 2024-12-11 | 1 | 1 | 2024-12-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-11 | 2025-06-19 | 191 | 137 | Unknown | Unknown | Unknown | Unknown | 2025-06-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SOLANA BEACH | N/A | 47.34 | 47.34 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-09 | 2024-08-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 950.49 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-09 | 2024-07-26 | Unknown | Unknown | 2024-07-26 | 2024-12-06 | 134 | 96 | 2024-12-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-10 | 2023-05-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 43899.33 | Unknown | Unknown | Yes | N/A | N/A | 2023-05-10 | 2023-11-16 | 191 | 137 | 2023-11-16 | 2024-08-14 | 273 | 195 | 2024-06-06 | 2025-06-17 | 314 | 224 | 2024-05-15 | 2025-06-23 | 106 | 80 | 2024-08-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-07-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ALPINE | N/A | 145.05 | 145.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-18 | 2024-03-18 | 2024-08-28 | IOU Designed & Installed | N/A | No | Unknown | 1609.41 | 0 | Unknown | Unknown | 25.37 | 1584.04 | 3981 | 1804.1 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-18 | 2024-02-15 | Unknown | Unknown | 2024-02-15 | 2024-03-28 | 43 | 31 | 2024-03-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-28 | 2024-08-28 | 154 | 110 | Unknown | 2024-08-26 | Unknown | Unknown | 2024-08-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 68.05 | 68.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-21 | 2023-03-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | 91.88 | -2.55 | Unknown | Unknown | 16.61 | 77.82 | 3241 | 641.11 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-21 | 2023-05-11 | 52 | 38 | 2023-05-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-15 | 2024-04-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 9601 | 589.24 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-15 | 2024-02-07 | Unknown | Unknown | 2024-02-07 | 2024-04-18 | 72 | 52 | 2024-04-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-18 | 2025-08-08 | 478 | 342 | Unknown | Unknown | Unknown | Unknown | 2025-08-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | 75.1 | 75.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-16 | 2024-08-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7882 | 1443.89 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-16 | 2024-07-17 | Unknown | Unknown | 2024-07-17 | 2024-08-16 | 31 | 23 | 2024-08-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-03 | 2025-03-03 | 2025-03-11 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1819.24 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-03 | 2025-02-19 | Unknown | Unknown | 2025-02-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-18 | 2024-01-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 163.83 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-18 | 2024-01-18 | 1 | 1 | 2024-01-18 | 2024-01-31 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | N/A | 224.05 | 224.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-02 | 2023-11-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2023-11-02 | 2023-10-03 | Unknown | Unknown | 2023-10-03 | 2023-11-02 | 31 | 23 | 2023-11-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | OCEANSIDE | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2024-09-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-22 | 2024-10-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3753.77 | 1938.7 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-22 | 2024-10-22 | 1 | 1 | 2024-10-22 | 2025-06-23 | 245 | 175 | Unknown | Unknown | Unknown | Unknown | 2025-04-30 | 2025-05-29 | 30 | 22 | 2025-06-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 8.1 | 8.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-25 | 2024-11-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7962 | 1629.71 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-25 | 2024-11-25 | 1 | 1 | 2024-11-25 | 2024-11-26 | 2 | 2 | 2024-11-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-13 | 2024-12-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1126.82 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-13 | 2024-12-23 | 11 | 7 | 2024-12-23 | 2025-01-24 | 33 | 25 | 2025-01-24 | 2025-02-19 | 27 | 19 | Unknown | Unknown | Unknown | Unknown | 2025-02-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-28 | Unknown | Unknown | No | 2025-05-30 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-30 | 2025-06-05 | Unknown | IOU Designed & Installed | N/A | Yes | 27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1269.83 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-30 | 2025-06-27 | 29 | 21 | 2025-06-27 | 2025-06-05 | Unknown | Unknown | 2025-06-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-20 | 2023-04-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 499.96 | Unknown | Unknown | Yes | N/A | N/A | 2023-04-20 | 2023-04-20 | 1 | 1 | 2023-04-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 38.05 | 38.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-03 | 2024-12-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1322.06 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-03 | 2024-12-12 | 10 | 8 | 2024-12-12 | 2024-12-26 | 15 | 11 | 2024-12-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | CHULA VISTA | 136 | 136 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-01 | Unknown | Unknown | No | 2023-08-11 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-11 | 2023-09-15 | Unknown | IOU Designed & Installed | N/A | Yes | 35 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2194.92 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-11 | 2023-09-15 | 36 | 26 | 2023-09-15 | 2023-09-15 | 1 | 1 | 2023-09-15 | 2024-05-02 | 189 | 133 | 2023-10-11 | 2023-10-19 | 9 | 7 | 2024-11-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | 277 | 277 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-21 | 2023-03-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 646.35 | Unknown | Unknown | Yes | N/A | N/A | 2023-02-21 | 2023-03-29 | 37 | 27 | 2023-03-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-15 | Unknown | Unknown | No | 2024-04-18 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-18 | 2024-04-18 | Unknown | IOU Designed & Installed | N/A | Yes | 15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 12481 | 584.27 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-18 | 2024-05-03 | 16 | 12 | 2024-05-03 | 2024-04-18 | Unknown | Unknown | 2024-04-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-18 | 2025-07-31 | 470 | 336 | Unknown | Unknown | Unknown | Unknown | 2025-07-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-14 | 2024-03-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 163.83 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-14 | 2024-02-07 | Unknown | Unknown | 2024-02-07 | 2024-03-19 | 42 | 30 | 2024-03-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-20 | 2023-11-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1237.9 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-20 | 2023-10-20 | Unknown | Unknown | 2023-10-20 | 2023-12-01 | 43 | 31 | 2023-12-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | 142.45 | 142.45 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-17 | 2025-03-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 17711 | 715.96 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-17 | 2025-03-31 | 288 | 206 | 2025-03-31 | 2025-05-06 | 37 | 27 | Unknown | Unknown | Unknown | Unknown | 2025-03-31 | 2025-04-10 | 11 | 9 | 2025-05-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | 8004.05 | 8004.05 | Not Available | >2MW | No | N/A | N/A | N/A | 2026-01-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-19 | 2025-02-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7962 | 700.44 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-19 | 2025-03-06 | 16 | 12 | 2025-03-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-18 | 2025-05-01 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | DANA POINT | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-10 | 2025-01-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1743.54 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-10 | 2025-01-10 | 1 | 1 | 2025-01-10 | 2025-01-10 | 1 | 1 | 2025-01-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | 378.1 | 378.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-20 | 2025-02-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 435.59 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-20 | 2025-01-22 | Unknown | Unknown | 2025-01-22 | 2025-02-20 | 30 | 22 | 2025-02-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-25 | 2025-07-25 | 92 | 66 | Unknown | Unknown | Unknown | Unknown | 2025-07-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CAMPO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-30 | 2023-11-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 765.78 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-30 | 2023-11-01 | Unknown | Unknown | 2023-11-01 | 2023-11-30 | 30 | 22 | 2023-11-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community,Tribal Community | ALPINE | N/A | 67.05 | 67.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-27 | 2024-09-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 820.01 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-27 | 2024-09-06 | 11 | 9 | 2024-09-06 | 2025-03-18 | 194 | 138 | 2025-03-11 | 2025-03-11 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2025-03-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-26 | 2024-12-27 | 2025-04-23 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1066.55 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-26 | 2024-12-27 | 32 | 24 | 2024-12-27 | 2024-12-27 | 1 | 1 | 2024-12-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-27 | 2025-04-23 | 118 | 84 | Unknown | Unknown | Unknown | Unknown | 2025-04-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-04 | 2025-03-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1215.3 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-04 | 2025-03-17 | 14 | 10 | 2025-03-17 | 2025-03-18 | 2 | 2 | 2025-03-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-14 | 2023-04-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 648.47 | Unknown | Unknown | Yes | N/A | N/A | 2023-04-14 | 2023-04-17 | 4 | 2 | 2023-04-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-23 | 2025-04-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1307.63 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-23 | 2025-05-19 | 27 | 19 | 2025-05-19 | 2025-05-28 | 10 | 8 | 2025-05-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | Both | IOU Design | Residential | Underserved Community | ALPINE | N/A | 80.1 | 80.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-11 | 2025-03-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 16057.07 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-11 | 2025-01-17 | Unknown | Unknown | 2025-01-17 | 2025-05-01 | 105 | 75 | 2025-03-07 | 2025-05-01 | 56 | 40 | 2025-06-06 | 2025-07-01 | 26 | 18 | 2025-05-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | LAGUNA NIGUEL | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-12 | 2023-05-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1993.77 | Unknown | Unknown | Yes | N/A | N/A | 2023-05-12 | 2023-09-13 | 125 | 89 | 2023-09-13 | 2023-09-13 | 1 | 1 | 2023-09-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-23 | 2023-03-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 512.85 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-23 | 2023-06-12 | 82 | 58 | 2023-06-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SOLANA BEACH | N/A | 47.34 | 47.34 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-20 | 2025-02-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 905.45 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-20 | 2024-12-06 | Unknown | Unknown | 2024-12-06 | 2025-02-20 | 77 | 55 | 2025-02-20 | 2025-06-06 | 107 | 77 | Unknown | Unknown | Unknown | Unknown | 2025-06-05 | 2025-07-15 | 41 | 29 | Unknown | 2025-07-09 | Unknown | Unknown | 2025-07-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 112.05 | 112.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-24 | 2025-03-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1528 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-24 | 2025-04-01 | 9 | 7 | 2025-04-01 | 2025-04-01 | 1 | 1 | 2025-04-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-01 | 2025-07-24 | 115 | 83 | Unknown | 2025-08-26 | Unknown | Unknown | 2025-07-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-15 | 2024-03-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7962 | 3099.02 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-15 | 2024-02-15 | 1 | 1 | 2024-02-15 | 2024-04-30 | 76 | 54 | Unknown | Unknown | Unknown | Unknown | 2024-03-30 | 2024-11-04 | 27 | 19 | 2024-04-30 | 2024-12-09 | 224 | 160 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 232.2 | 232.2 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-03 | 2025-03-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 11943 | 1156.19 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-03 | 2025-03-14 | 12 | 10 | 2025-03-14 | 2025-03-14 | 1 | 1 | 2025-03-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-14 | 2025-08-06 | 146 | 104 | Unknown | Unknown | Unknown | Unknown | 2025-08-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 84.05 | 84.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-28 | Unknown | Unknown | No | 2023-12-27 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-25 | 2023-09-28 | 2024-03-13 | IOU Designed & Installed | N/A | Yes | 92 | 3204.05 | 445.99 | Unknown | Unknown | 247.82 | 2510.24 | 3241 | 989.34 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-25 | 2024-03-28 | 186 | 134 | 2024-03-28 | 2023-09-28 | Unknown | Unknown | 2023-09-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-14 | 2024-03-13 | 29 | 21 | Unknown | Unknown | Unknown | Unknown | 2024-03-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | 209.12 | 209.12 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-15 | 2024-02-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 509036 | 8688.69 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-15 | 2024-02-15 | 1 | 1 | 2024-02-15 | 2024-02-23 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CAPISTRANO BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-21 | 2024-11-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1682 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-21 | 2024-11-18 | Unknown | Unknown | 2024-11-18 | 2024-11-21 | 4 | 4 | 2024-11-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | OCEANSIDE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-20 | 2024-02-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2223.28 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-20 | 2024-02-23 | 4 | 4 | 2024-02-23 | 2024-02-26 | 4 | 2 | 2024-02-26 | 2024-03-08 | 12 | 10 | 2024-02-23 | 2024-03-12 | 19 | 13 | 2024-03-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | POWAY | COUNTY OF SAN DIEGO-NORTH of 56, POWAY | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-15 | 2024-08-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1647.81 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-15 | 2024-08-20 | 6 | 4 | 2024-08-20 | 2024-08-20 | 1 | 1 | 2024-08-20 | 2025-05-19 | 273 | 195 | 2025-05-09 | 2025-05-27 | 13 | 7 | 2025-05-20 | 2025-07-28 | 70 | 50 | Unknown | 2025-07-18 | Unknown | Unknown | 2025-07-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 4 | 4 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-29 | 2023-10-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3241 | 939.42 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-29 | 2023-10-16 | 18 | 12 | 2023-10-16 | 2023-10-16 | 1 | 1 | 2023-10-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | CORONADO | N/A | 46 | 46 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-13 | 2025-03-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2272.9 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-13 | 2025-03-19 | 7 | 5 | 2025-03-19 | 2025-03-19 | 1 | 1 | 2025-03-19 | 2025-03-27 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | 2025-03-27 | 2025-08-01 | 128 | 92 | Unknown | 2025-07-07 | Unknown | Unknown | 2025-08-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | MISSION VIEJO | MISSION VIEJO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-04 | 2024-06-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2875.23 | 789.5 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-04 | 2024-06-25 | 22 | 16 | 2024-06-25 | 2025-08-06 | 408 | 292 | Unknown | Unknown | Unknown | Unknown | 2025-06-24 | 2025-07-21 | 28 | 20 | 2025-08-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-08-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 142.05 | 142.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-05 | 2025-03-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2879.73 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-05 | 2025-04-03 | 30 | 22 | 2025-04-03 | 2025-04-14 | 12 | 8 | 2025-04-14 | 2025-07-08 | 86 | 62 | Unknown | Unknown | Unknown | Unknown | 2025-04-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Residential | Underserved Community | Santee | COUNTY OF SAN DIEGO-SOUTH of 56 | 44 | 44 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-01 | 2024-05-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3917 | 10426.35 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-01 | 2023-12-13 | 43 | 31 | 2023-12-13 | 2024-07-22 | 223 | 159 | 2024-04-30 | 2024-07-18 | 24 | 18 | 2024-05-16 | 2024-07-24 | 21 | 15 | 2025-08-11 | Unknown | Unknown | Unknown | 2025-08-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 108.05 | 108.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-20 | 2024-06-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2084.85 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-20 | 2024-05-08 | Unknown | Unknown | 2024-05-08 | 2024-06-21 | 45 | 33 | 2024-06-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 6 | 6 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-21 | 2023-04-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 717.61 | Unknown | Unknown | Yes | N/A | N/A | 2023-04-21 | 2023-05-20 | 30 | 21 | 2023-05-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | POWAY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-17 | 2025-03-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 832.06 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-17 | 2025-04-24 | 39 | 29 | 2025-04-24 | 2025-05-13 | 20 | 14 | 2025-05-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-13 | 2025-07-01 | 50 | 36 | Unknown | 2025-07-18 | Unknown | Unknown | 2025-07-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 98.05 | 98.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-19 | 2025-03-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1760.94 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-19 | 2025-03-14 | Unknown | Unknown | 2025-03-14 | 2025-06-06 | 85 | 61 | Unknown | Unknown | Unknown | Unknown | 2025-03-20 | 2025-04-03 | 15 | 11 | 2025-06-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-08-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-23 | 2023-03-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3661.75 | 365.03 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-23 | 2023-04-17 | 26 | 18 | 2023-04-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-04 | 2025-04-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 33427.73 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-04 | 2025-03-13 | 10 | 8 | 2025-03-13 | 2025-06-30 | 110 | 78 | Unknown | Unknown | Unknown | Unknown | 2025-05-16 | 2025-07-24 | 49 | 35 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-08-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-27 | 2025-03-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 883.73 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-27 | 2025-06-01 | 67 | 47 | 2025-06-01 | 2025-06-16 | 16 | 11 | 2025-06-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-25 | Unknown | Unknown | No | 2024-09-26 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-26 | 2024-09-26 | Unknown | IOU Designed & Installed | N/A | Yes | 26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 27449 | 507.87 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-26 | 2024-10-30 | 35 | 25 | 2024-10-30 | 2024-10-22 | Unknown | Unknown | 2024-10-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-02-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-05 | 2023-10-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 340.77 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-05 | 2023-10-20 | 16 | 12 | 2023-10-20 | 2024-01-08 | 81 | 57 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-08 | 2024-04-15 | 99 | 71 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-11 | 2024-09-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 6015.75 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-11 | 2024-09-11 | 1 | 1 | 2024-09-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 38.05 | 38.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-02 | 2023-03-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 363.72 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-02 | 2023-03-02 | 1 | 1 | 2023-03-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | OH | IOU Design | Commercial | Underserved Community | Jamul | CALTRANS-SOUTH of 56 | 194 | 194 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-22 | 2024-01-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 20612.99 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-22 | 2024-01-22 | 1 | 1 | 2024-01-22 | 2024-11-12 | 296 | 212 | 2024-06-11 | 2024-11-12 | 155 | 111 | 2024-04-26 | 2024-11-25 | 53 | 37 | 2024-11-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | Jamul | CALTRANS-SOUTH of 56 | 194 | 194 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-16 | 2024-01-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 4406 | 25928.87 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-16 | 2024-01-22 | 99 | 71 | 2024-01-22 | 2024-11-13 | 297 | 213 | 2024-05-03 | 2024-05-03 | 1 | 1 | 2024-06-05 | 2024-11-25 | 47 | 33 | 2024-11-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | SAN DIEGO | 176 | 176 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-31 | 2023-10-31 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 10000 | 6131.21 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-31 | 2024-06-11 | 225 | 161 | 2024-06-11 | 2024-09-23 | 105 | 75 | Unknown | Unknown | Unknown | Unknown | 2024-09-24 | 2024-10-22 | 29 | 21 | 2024-09-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-13 | 2023-10-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 737.97 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-13 | 2023-10-04 | 22 | 16 | 2023-10-04 | 2023-10-16 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2025-01-15 | 2025-01-15 | 1 | 1 | 2023-10-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LA JOLLA | N/A | 10 | 10 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-14 | 2025-03-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1279.68 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-14 | 2025-05-22 | 70 | 50 | 2025-05-22 | 2025-05-22 | 1 | 1 | 2025-05-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2020-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-08 | 2023-08-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 71.28 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-08 | 2023-08-08 | 1 | 1 | 2023-08-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | DANA POINT | N/A | 43.05 | 43.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-08 | 2024-10-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 4148.48 | 1812.35 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-08 | 2024-10-09 | 2 | 2 | 2024-10-09 | 2024-10-10 | 2 | 2 | 2024-10-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-15 | 2024-10-15 | 2025-06-30 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1683.03 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-15 | 2024-10-15 | 1 | 1 | 2024-10-15 | 2024-10-15 | 1 | 1 | 2024-10-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-15 | 2025-06-30 | 259 | 185 | Unknown | Unknown | Unknown | Unknown | 2025-06-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | SAN DIEGO | 7 | 7 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-03 | 2023-07-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1969.28 | Unknown | Unknown | Yes | N/A | N/A | 2023-01-03 | 2023-10-06 | 277 | 199 | 2023-10-06 | 2024-09-04 | 335 | 239 | Unknown | Unknown | Unknown | Unknown | 2023-08-16 | 2024-06-10 | 36 | 26 | 2024-09-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LA JOLLA | N/A | 234 | 234 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-30 | 2023-05-30 | 2025-06-30 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 12450.41 | Unknown | Unknown | Yes | N/A | N/A | 2023-05-30 | 2023-05-31 | 2 | 2 | 2023-05-31 | 2023-08-01 | 63 | 45 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-01 | 2025-05-30 | 669 | 479 | Unknown | 2025-06-09 | Unknown | Unknown | 2025-06-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | Underserved Community | SM 1128-C2 Restrnt row WO2 (E) | SAN MARCOS | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-11 | 2024-01-11 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 54984.34 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-11 | 2024-10-21 | 285 | 203 | 2024-10-21 | 2025-04-02 | 164 | 118 | 2024-10-30 | 2025-02-12 | 25 | 19 | 2024-11-13 | 2025-03-20 | 32 | 24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-10 | 2025-01-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1010.96 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-10 | 2024-12-11 | 2 | 2 | 2024-12-11 | 2025-01-03 | 24 | 18 | 2025-01-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | CHULA VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-20 | 2025-03-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1683.59 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-20 | 2025-01-17 | 29 | 21 | 2025-01-17 | 2025-03-28 | 71 | 51 | 2025-02-20 | 2025-02-24 | 5 | 3 | 2025-03-12 | 2025-03-20 | 9 | 7 | 2025-03-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-07 | 2024-08-07 | 2024-09-10 | IOU Designed & Installed | N/A | No | Unknown | 1308.48 | -15.61 | Unknown | Unknown | 95.02 | 1229.07 | 3981 | 1636.81 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-07 | 2024-08-06 | Unknown | Unknown | 2024-08-06 | 2024-08-07 | 2 | 2 | 2024-08-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-07 | 2024-09-10 | 35 | 25 | Unknown | Unknown | Unknown | Unknown | 2024-09-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-24 | 2025-06-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2031.32 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-24 | 2025-06-24 | 1 | 1 | 2025-06-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-07-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | CHULA VISTA | 114 | 114 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-07-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-13 | 2022-07-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 15924 | 2479.07 | Unknown | Unknown | Yes | N/A | N/A | 2022-06-13 | 2024-06-06 | 725 | 519 | 2024-06-06 | 2024-11-25 | 173 | 123 | Unknown | Unknown | Unknown | Unknown | 2024-04-16 | 2024-07-29 | 97 | 69 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | LAGUNA NIGUEL | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-11 | 2025-06-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 597.52 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-11 | 2025-06-19 | 9 | 7 | 2025-06-19 | 2025-06-19 | 1 | 1 | 2025-06-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-19 | 2025-07-30 | 42 | 30 | Unknown | Unknown | Unknown | Unknown | 2025-07-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-30 | 2025-03-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2875.33 | 662.75 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-30 | 2025-03-12 | 42 | 30 | 2025-03-12 | 2025-05-13 | 63 | 45 | Unknown | Unknown | Unknown | Unknown | 2025-03-20 | 2025-04-10 | 22 | 16 | 2025-05-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 41.05 | 41.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-02 | 2025-01-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2830.81 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-02 | 2025-01-06 | 5 | 3 | 2025-01-06 | 2025-01-10 | 5 | 5 | 2025-01-10 | 2025-02-28 | 50 | 36 | Unknown | Unknown | Unknown | Unknown | 2025-03-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | JACUMBA | N/A | 2947.05 | 2947.05 | Not Available | >2MW | No | N/A | N/A | N/A | 2026-08-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-18 | 2024-09-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1116.61 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-18 | 2024-08-14 | Unknown | Unknown | 2024-08-14 | 2024-09-18 | 36 | 26 | 2024-09-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | 2.7 | 2.7 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-12 | 2024-11-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1542.75 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-12 | 2024-11-13 | 2 | 2 | 2024-11-13 | 2024-11-13 | 1 | 1 | 2024-11-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 79.05 | 79.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-14 | 2023-09-15 | 2024-07-29 | IOU Designed & Installed | N/A | No | Unknown | 33.81 | 0 | Unknown | Unknown | Unknown | 33.81 | 3981 | 1079.76 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-14 | 2023-09-15 | 2 | 2 | 2023-09-15 | 2023-09-15 | 1 | 1 | 2023-09-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-15 | 2024-07-29 | 319 | 227 | Unknown | Unknown | Unknown | Unknown | 2024-07-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-16 | 2024-09-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1336.34 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-16 | 2024-09-04 | Unknown | Unknown | 2024-09-04 | 2024-09-19 | 16 | 12 | 2024-09-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-19 | Unknown | Unknown | Unknown | Unknown | 2025-05-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | NATIONAL CITY | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-02 | 2023-08-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2382.55 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-02 | 2023-10-05 | 65 | 47 | 2023-10-05 | 2023-10-25 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | 2023-08-28 | 2023-09-08 | 12 | 10 | 2023-10-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | BONSALL | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-04-12 | Unknown | Unknown | No | 2022-01-05 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2021-12-15 | 2022-01-05 | Unknown | IOU Designed & Installed | N/A | Yes | 1189 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1685.02 | Unknown | Unknown | Yes | N/A | N/A | 2021-12-15 | 2025-04-02 | 1205 | 861 | 2025-04-02 | 2025-05-06 | 35 | 25 | Unknown | Unknown | Unknown | Unknown | 2025-05-12 | 2025-05-12 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | RAMONA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-30 | 2023-10-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 13067 | 690.27 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-30 | 2023-10-11 | 43 | 31 | 2023-10-11 | 2023-10-11 | 1 | 1 | 2023-10-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-11 | Unknown | Unknown | Unknown | Unknown | 2025-08-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-15 | 2023-11-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2288.18 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-15 | 2023-10-26 | Unknown | Unknown | 2023-10-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-28 | 2024-02-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1027.42 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-28 | 2023-11-01 | Unknown | Unknown | 2023-11-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 34.05 | 34.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-08 | Unknown | Unknown | No | 2024-03-26 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-26 | 2024-04-03 | Unknown | IOU Designed & Installed | N/A | Yes | 276 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1504.17 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-26 | 2025-08-28 | 521 | 373 | 2025-08-28 | 2025-09-05 | 9 | 7 | 2025-08-13 | 2025-09-05 | 24 | 18 | Unknown | Unknown | Unknown | Unknown | 2024-04-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-20 | 2024-03-20 | 2024-03-21 | IOU Designed & Installed | N/A | No | Unknown | 11365.51 | 1685.12 | Unknown | 82.28 | 1543.88 | 8054.23 | 0 | 625.82 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-20 | 2024-03-20 | 1 | 1 | 2024-03-20 | 2024-03-20 | 1 | 1 | 2024-03-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-20 | 2024-03-21 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-03-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-30 | 2024-08-15 | 2025-06-17 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1094.9 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-30 | 2024-07-23 | Unknown | Unknown | 2024-07-23 | 2024-08-30 | 39 | 29 | 2024-08-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-30 | 2025-06-17 | 292 | 208 | Unknown | 2025-05-30 | Unknown | Unknown | 2025-06-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-02 | 2024-07-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1090.55 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-02 | 2024-05-29 | Unknown | Unknown | 2024-05-29 | 2024-08-09 | 73 | 53 | 2024-08-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | CORONADO | N/A | 216 | 216 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-10-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-31 | 2024-02-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7962 | 887.35 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-31 | 2024-02-01 | 2 | 2 | 2024-02-01 | 2024-02-02 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-02 | 2025-06-24 | 509 | 363 | Unknown | Unknown | Unknown | Unknown | 2025-07-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-06 | 2025-03-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 36201 | 4899.62 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-06 | 2025-04-08 | 34 | 24 | 2025-04-08 | 2025-06-18 | 72 | 52 | Unknown | Unknown | Unknown | Unknown | 2025-05-06 | 2025-05-28 | 23 | 17 | 2025-06-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-05 | 2024-03-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2801.91 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-05 | 2024-03-05 | 1 | 1 | 2024-03-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-08 |  | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1811.79 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-08 | 2024-10-08 | 1 | 1 | 2024-10-08 | 2024-10-08 | 1 | 1 | 2024-10-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 222214 | 222214 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-03-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-15 | 2025-01-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 31848 | 8150.34 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-15 | 2025-01-28 | 14 | 10 | 2025-01-28 | 2025-01-28 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-28 | 2025-07-14 | 168 | 120 | Unknown | 2025-07-25 | Unknown | Unknown | 2025-07-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 73.05 | 73.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-07 | Unknown | Unknown | No | 2025-04-24 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-24 | 2025-04-25 | Unknown | IOU Designed & Installed | N/A | Yes | 42 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1025.04 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-24 | 2025-06-02 | 40 | 28 | 2025-06-02 | 2025-06-05 | 4 | 4 | 2025-06-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 35.05 | 35.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-29 | 2024-04-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 162.34 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-29 | 2024-03-27 | Unknown | Unknown | 2024-03-27 | 2024-05-07 | 42 | 30 | 2024-05-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-07 | Unknown | Unknown | Unknown | Unknown | 2025-04-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-20 | 2024-09-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1271.11 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-20 | 2024-08-13 | Unknown | Unknown | 2024-08-13 | 2024-10-09 | 58 | 42 | 2024-10-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 47.1 | 47.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-27 | 2025-03-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1414.92 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-27 | 2025-03-19 | 21 | 15 | 2025-03-19 | 2025-03-21 | 3 | 3 | 2025-03-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-07 | 2023-02-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 98.41 | Unknown | Unknown | Yes | N/A | N/A | 2023-02-07 | 2023-02-17 | 11 | 9 | 2023-02-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | Chula Vista | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-24 | 2025-02-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 35422 | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2025-02-24 | 2025-01-08 | Unknown | Unknown | 2025-01-08 | 2025-03-25 | 77 | 55 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | JULIAN | N/A | 345.05 | 345.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-05 | 2025-03-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2834.39 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-05 | 2025-02-25 | Unknown | Unknown | 2025-02-25 | 2025-03-07 | 11 | 9 | 2025-03-07 | 2025-03-18 | 12 | 8 | Unknown | Unknown | Unknown | Unknown | 2025-03-18 | 2025-08-06 | 142 | 102 | Unknown | 2025-08-06 | Unknown | Unknown | 2025-08-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-09 | 2024-05-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 12481 | 584.27 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-09 | 2024-04-16 | Unknown | Unknown | 2024-04-16 | 2024-05-09 | 24 | 18 | 2024-05-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-09 | 2025-07-24 | 442 | 316 | Unknown | Unknown | Unknown | Unknown | 2025-07-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2018-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-30 | 2023-02-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 47.04 | Unknown | Unknown | Yes | N/A | N/A | 2023-01-30 | 2023-01-31 | 2 | 2 | 2023-01-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-20 | 2024-06-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 544874 | 30409.41 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-20 | 2024-06-20 | 1 | 1 | 2024-06-20 | 2024-08-29 | 71 | 51 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-15 | 2023-08-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | -13.99 | -6.75 | Unknown | Unknown | Unknown | -7.24 | 0 | 239.38 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-15 | 2023-03-08 | Unknown | Unknown | 2023-03-08 | 2023-09-22 | 199 | 143 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-22 | Unknown | Unknown | Unknown | Unknown | 2024-05-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-05-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-12 | 2023-11-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 8370 | 399.26 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-12 | 2023-10-10 | 29 | 21 | 2023-10-10 | 2023-11-28 | 50 | 36 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-28 | Unknown | Unknown | Unknown | Unknown | 2025-04-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | 795 | 795 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-29 | 2024-06-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 11943 | 1594.36 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-29 | 2024-05-23 | Unknown | Unknown | 2024-05-23 | 2024-11-12 | 174 | 124 | Unknown | Unknown | Unknown | Unknown | 2024-11-08 | 2024-12-12 | 35 | 25 | 2024-11-12 | 2025-02-05 | 86 | 62 | Unknown | Unknown | Unknown | Unknown | 2025-07-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 186.05 | 186.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-23 | 2023-04-13 | 2024-10-14 | IOU Designed & Installed | N/A | No | Unknown | 146.73 | 0 | Unknown | Unknown | 82.09 | 64.64 | 3981 | 1372.53 | Unknown | Unknown | Yes | N/A | N/A | 2023-02-23 | 2023-07-11 | 139 | 99 | 2023-07-11 | 2023-07-11 | 1 | 1 | 2023-07-11 | 2024-03-08 | 242 | 174 | Unknown | Unknown | Unknown | Unknown | 2024-03-08 | 2024-10-14 | 221 | 157 | Unknown | 2024-10-21 | Unknown | Unknown | 2024-10-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 79.05 | 79.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-27 | 2023-10-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 152.86 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-27 | 2023-09-13 | Unknown | Unknown | 2023-09-13 | 2023-11-07 | 56 | 40 | 2023-11-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2026-03-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-21 | 2024-03-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 54899 | 84.1 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-21 | 2025-05-08 | 414 | 296 | 2025-05-08 | 2025-06-19 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | 2024-04-04 | 2024-09-30 | 64 | 46 | 2025-06-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-18 | 2024-06-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2115.33 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-18 | 2024-07-26 | 39 | 29 | 2024-07-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | OCEANSIDE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-27 | 2025-05-27 | 2025-06-13 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1314.18 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-27 | 2025-05-27 | 1 | 1 | 2025-05-27 | 2025-05-27 | 1 | 1 | 2025-05-27 | Unknown | Unknown | Unknown | 2025-05-28 | 2025-06-13 | 17 | 13 | 2025-05-27 | 2025-06-13 | 18 | 14 | Unknown | Unknown | Unknown | Unknown | 2025-06-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | 8 | 8 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-02 | 2024-12-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2929.03 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-02 | 2025-02-13 | 74 | 54 | 2025-02-13 | 2025-02-24 | 12 | 8 | 2025-02-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | LAGUNA NIGUEL | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-30 | 2023-12-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 429.03 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-30 | 2023-11-08 | Unknown | Unknown | 2023-11-08 | 2024-01-18 | 72 | 52 | 2024-01-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA JOLLA | N/A | 71.05 | 71.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-10 | 2024-04-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1083.65 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-10 | 2024-04-15 | 97 | 69 | 2024-04-15 | 2024-04-19 | 5 | 5 | 2024-04-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | OH | Applicant Design | Residential | Underserved Community | San Diego | San Diego | 264 | 264 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-08-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-20 | 2023-09-20 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 76176.04 | 43769.84 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-20 | 2024-05-01 | 225 | 161 | 2024-05-01 | 2025-06-05 | 401 | 287 | 2024-05-09 | 2025-02-18 | 202 | 143 | 2024-08-14 | 2025-06-12 | 54 | 40 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-21 | 2025-03-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1224.49 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-21 | 2025-05-21 | 62 | 44 | 2025-05-21 | 2025-05-29 | 9 | 7 | 2025-05-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | Both | IOU Design | Residential | N/A | VALLEY CENTER | COUNTY OF SAN DIEGO-NORTH of 56 | 343 | 343 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-18 | Unknown | Unknown | No | 2023-01-06 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-04 | 2023-01-06 | Unknown | IOU Designed & Installed | N/A | Yes | 508 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 17834.49 | Unknown | Unknown | Yes | N/A | N/A | 2022-10-04 | 2024-05-14 | 589 | 421 | 2024-05-14 | 2024-09-25 | 135 | 97 | 2023-01-06 | Unknown | Unknown | Unknown | 2024-05-29 | 2024-10-02 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | 2024-10-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | San Diego | SAN DIEGO | 68.05 | 68.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-01-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-23 | 2024-11-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 8562.25 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-23 | 2024-09-09 | Unknown | Unknown | 2024-09-09 | 2025-03-19 | 192 | 138 | Unknown | Unknown | Unknown | Unknown | 2025-02-05 | 2025-04-10 | 43 | 31 | 2025-03-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Commercial | Underserved Community | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-11 | 2023-05-11 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 386411 | 53773.95 | Unknown | Unknown | Yes | N/A | N/A | 2023-05-11 | 2024-04-03 | 329 | 235 | 2024-04-03 | 2024-06-27 | 86 | 62 | 2024-04-11 | 2024-06-20 | 65 | 47 | 2024-03-20 | 2024-08-20 | 74 | 54 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-25 | 2025-03-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 1743 | 1738.24 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-25 | 2025-03-14 | Unknown | Unknown | 2025-03-14 | 2025-04-01 | 19 | 13 | 2025-04-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | ENCINITAS | ENCINITAS | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2025-10-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-30 | 2022-09-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 445.86 | Unknown | Unknown | Yes | N/A | N/A | 2022-08-30 | 2023-08-01 | 337 | 241 | 2023-08-01 | 2025-06-25 | 695 | 497 | 2023-03-28 | 2023-03-29 | 2 | 2 | 2023-02-17 | 2023-04-27 | 70 | 50 | 2025-06-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-27 | 2025-03-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 17711 | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2025-03-27 | 2025-03-21 | Unknown | Unknown | 2025-03-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-01 | 2025-05-16 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-31 | 2023-03-31 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 669.16 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-31 | 2023-03-31 | 1 | 1 | 2023-03-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-25 | 2025-02-25 | 2025-03-19 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2114.43 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-25 | 2025-02-10 | Unknown | Unknown | 2025-02-10 | 2025-02-25 | 16 | 12 | 2025-02-25 | Unknown | Unknown | Unknown | 2025-02-25 | 2025-03-12 | 16 | 12 | 2025-02-25 | 2025-03-19 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | 2025-03-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-12 | 2025-03-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1436.04 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-12 | 2025-03-27 | 16 | 12 | 2025-03-27 | 2025-04-09 | 14 | 10 | 2025-03-21 | 2025-04-01 | 12 | 8 | Unknown | Unknown | Unknown | Unknown | 2025-04-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-12 | 2025-02-12 | 2025-02-12 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1136.64 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-12 | 2025-02-12 | 1 | 1 | 2025-02-12 | 2025-02-12 | 1 | 1 | 2025-02-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-12 | 2025-02-12 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2025-02-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2020-07-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-30 | 2023-04-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 495.75 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-30 | 2023-04-26 | 28 | 20 | 2023-04-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 9.7 | 9.7 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-12 | 2025-06-03 | 2025-06-24 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1590.76 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-12 | 2025-06-03 | 23 | 17 | 2025-06-03 | 2025-06-03 | 1 | 1 | 2025-05-15 | 2025-06-10 | 27 | 19 | Unknown | Unknown | Unknown | Unknown | 2025-06-10 | 2025-06-24 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2025-06-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 1218.25 | 1218.25 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2025-09-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-16 | 2023-06-16 | 2023-09-05 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1881.32 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-16 | 2023-06-16 | 1 | 1 | 2023-06-16 | 2025-03-06 | 630 | 450 | 2025-03-06 | 2023-06-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-27 | 2023-09-05 | 71 | 51 | Unknown | 2023-08-17 | Unknown | Unknown | 2023-09-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-18 | 2025-02-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1655.84 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-18 | 2025-02-11 | 86 | 62 | 2025-02-11 | 2025-02-12 | 2 | 2 | 2025-02-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-12 | 2025-07-24 | 163 | 117 | Unknown | Unknown | Unknown | Unknown | 2025-07-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | 136 | 136 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-15 | 2022-07-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 54967 | 1758.38 | Unknown | Unknown | Yes | N/A | N/A | 2022-07-15 | 2023-05-11 | 301 | 215 | 2023-05-11 | 2023-09-26 | 139 | 99 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-02 | 2024-08-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 4611.19 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-02 | 2024-08-01 | 213 | 153 | 2024-08-01 | 2024-10-17 | 78 | 56 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-17 | 2025-07-10 | 267 | 191 | Unknown | 2025-08-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN MARCOS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-21 | 2024-05-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1523.58 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-21 | 2024-05-21 | 1 | 1 | 2024-05-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 12 | 12 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-24 | 2025-03-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2013.94 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-24 | 2025-03-03 | 8 | 6 | 2025-03-03 | 2025-03-03 | 1 | 1 | 2025-03-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | 48.4 | 48.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-22 | 2024-12-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 9945.25 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-22 | 2024-11-12 | Unknown | Unknown | 2024-11-12 | 2025-02-19 | 100 | 72 | Unknown | Unknown | Unknown | Unknown | 2025-08-04 | 2025-08-05 | 2 | 2 | 2025-02-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-14 | 2024-11-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 40553 | 949.7 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-14 | 2024-12-26 | 43 | 31 | 2024-12-26 | 2025-01-16 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | 2025-01-14 | 2025-02-05 | 23 | 17 | 2025-01-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-21 | 2023-09-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1057.01 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-21 | 2023-04-26 | Unknown | Unknown | 2023-04-26 | 2023-09-22 | 150 | 108 | 2023-09-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-23 | 2024-04-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 984.98 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-23 | 2024-03-15 | Unknown | Unknown | 2024-03-15 | 2024-06-10 | 88 | 62 | 2024-06-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN JUAN CAPISTRANO | N/A | 120 | 120 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-21 | 2022-12-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 67.06 | Unknown | Unknown | Yes | N/A | N/A | 2022-12-21 | 2023-02-03 | 45 | 33 | 2023-02-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-17 | 2024-09-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 19905 | 683.68 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-17 | 2024-09-19 | 3 | 3 | 2024-09-19 | 2025-01-03 | 107 | 77 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | RANCHO LA COSTA | N/A | 11520 | 11520 | Not Available | >2MW | No | N/A | N/A | N/A | 2027-04-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-07 | 2025-05-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2490.4 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-07 | 2025-06-11 | 36 | 26 | 2025-06-11 | 2025-06-11 | 1 | 1 | 2025-06-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-29 | 2025-06-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 343.27 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-29 | 2025-06-20 | 23 | 17 | 2025-06-20 | 2025-06-26 | 7 | 5 | 2025-06-26 | Unknown | Unknown | Unknown | 2025-06-26 | 2025-07-14 | 19 | 13 | 2025-06-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 11.35 | 11.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-10 | 2025-03-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1603.92 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-10 | 2025-04-08 | 30 | 22 | 2025-04-08 | 2025-06-06 | 60 | 44 | 2025-06-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-06 | 2025-07-11 | 36 | 26 | Unknown | Unknown | Unknown | Unknown | 2025-07-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN CLEMENTE | SAN CLEMENTE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-06-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-26 | 2025-06-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1507.51 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-26 | 2025-06-17 | Unknown | Unknown | 2025-06-17 | 2025-06-26 | 10 | 8 | 2025-06-26 | Unknown | Unknown | Unknown | 2025-06-26 | 2025-08-06 | 42 | 30 | 2025-06-26 | 2025-09-08 | 75 | 53 | Unknown | Unknown | Unknown | Unknown | 2025-09-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 3 | 3 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-03 | 2024-12-06 | 2025-03-19 | IOU Designed & Installed | N/A | No | Unknown | 754.74 | -15.17 | Unknown | Unknown | Unknown | 769.91 | 3981 | 1990.53 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-03 | 2024-12-06 | 4 | 4 | 2024-12-06 | 2024-12-06 | 1 | 1 | 2024-12-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-26 | 2025-07-25 | 212 | 152 | Unknown | Unknown | Unknown | Unknown | 2025-07-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CAMPO | N/A | 1084.05 | 1084.05 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2027-04-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-15 | 2025-05-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1395.09 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-15 | 2025-05-12 | Unknown | Unknown | 2025-05-12 | 2025-05-15 | 4 | 4 | 2025-05-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | N/A | 595.05 | 595.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-18 | 2024-03-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 3181.6 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-18 | 2024-03-19 | 2 | 2 | 2024-03-19 | 2024-04-10 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-11 | 2024-07-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1274.31 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-11 | 2024-05-17 | Unknown | Unknown | 2024-05-17 | 2024-07-25 | 70 | 50 | 2024-07-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-17 | 2025-04-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 53540 | 6500.13 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-17 | 2025-05-30 | 44 | 32 | 2025-05-30 | 2025-07-01 | 33 | 23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-07-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ALPINE | N/A | 131.05 | 131.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2028-08-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-22 | 2025-04-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 588.5 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-22 | 2025-04-25 | 613 | 439 | 2025-04-25 | 2025-06-06 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-06 | 2025-06-24 | 19 | 13 | Unknown | 2025-07-17 | Unknown | Unknown | 2025-07-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | VISTA | 29 | 29 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | 2025-04-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2025-04-07 | 2025-04-28 | 22 | 16 | 2025-04-28 | 2025-04-29 | 2 | 2 | 2025-04-29 | Unknown | Unknown | Unknown | 2025-04-30 | 2025-05-16 | 17 | 13 | 2025-04-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | 8196500 | 8196500 | Not Available | >2MW | No | N/A | N/A | N/A | 2026-07-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-09 | 2024-10-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 49559 | 1123.48 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-09 | 2024-10-09 | 1 | 1 | 2024-10-09 | 2024-10-22 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | 2024-10-15 | 2024-12-06 | 31 | 23 | 2024-10-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SANTEE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-07 | 2024-11-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1384.24 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-07 | 2025-01-31 | 86 | 62 | 2025-01-31 | 2025-02-04 | 5 | 3 | 2025-02-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 83.05 | 83.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-08 | 2023-07-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 835.98 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-08 | 2023-03-08 | Unknown | Unknown | 2023-03-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 128399.45 | 128399.45 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-10-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-27 | 2023-11-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1257.84 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-27 | 2023-10-13 | Unknown | Unknown | 2023-10-13 | 2023-12-07 | 56 | 40 | 2023-12-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-07 | Unknown | Unknown | Unknown | Unknown | 2025-07-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-12 | 2025-06-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 994.06 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-12 | 2025-06-11 | Unknown | Unknown | 2025-06-11 | 2025-06-25 | 15 | 11 | 2025-06-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-25 | 2025-08-25 | 62 | 44 | Unknown | Unknown | Unknown | Unknown | 2025-08-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-23 | 2024-10-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 9242.34 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-23 | 2024-11-05 | 14 | 10 | 2024-11-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | ESCONDIDO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2024-09-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-13 | 2024-09-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3980.39 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-13 | 2024-12-03 | 82 | 58 | 2024-12-03 | 2025-01-10 | 39 | 29 | Unknown | Unknown | Unknown | Unknown | 2024-11-08 | 2024-11-20 | 13 | 9 | 2025-01-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-25 | 2025-05-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1203.94 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-25 | 2025-05-08 | 14 | 10 | 2025-05-08 | 2025-05-09 | 2 | 2 | 2025-05-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-09 | 2025-08-05 | 89 | 63 | Unknown | Unknown | Unknown | Unknown | 2025-08-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | N/A | 179.05 | 179.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-27 | 2023-10-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1903.5 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-27 | 2023-09-27 | 1 | 1 | 2023-09-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-16 | 2024-12-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1619.22 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-16 | 2024-12-26 | 11 | 9 | 2024-12-26 | 2024-12-26 | 1 | 1 | 2024-12-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 129 | 129 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-04-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-13 | 2023-06-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 153.75 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-13 | 2023-06-22 | 10 | 8 | 2023-06-22 | 2023-06-22 | 1 | 1 | 2023-06-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SOUTH LAGUNA | N/A | 180.05 | 180.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-07-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-19 | 2024-08-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1057.64 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-19 | 2024-08-16 | 29 | 21 | 2024-08-16 | 2024-08-16 | 1 | 1 | 2024-08-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | 128.05 | 128.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-26 | 2024-12-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 692.97 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-26 | 2024-10-30 | 188 | 134 | 2024-10-30 | 2024-12-23 | 55 | 39 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-23 | 2025-07-31 | 221 | 159 | Unknown | 2025-08-14 | Unknown | Unknown | 2025-09-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 15 | 15 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-09 | 2024-02-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1175.42 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-09 | 2023-11-03 | Unknown | Unknown | 2023-11-03 | 2024-02-05 | 95 | 67 | 2024-02-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 5.4 | 5.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-15 | 2025-01-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1213.24 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-15 | 2025-02-06 | 23 | 17 | 2025-02-06 | 2025-02-06 | 1 | 1 | 2025-02-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-17 | 2025-06-17 | 2025-06-26 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1359.27 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-17 | 2025-06-11 | Unknown | Unknown | 2025-06-11 | 2025-06-17 | 7 | 5 | 2025-06-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-17 | 2025-06-26 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | 2025-06-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | LEMON GROVE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-01 | 2024-11-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 51120 | 3434.98 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-01 | 2024-07-24 | 146 | 104 | 2024-07-24 | 2024-12-12 | 142 | 102 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 2378.4 | 2378.4 | Not Available | >2MW | No | N/A | N/A | N/A | 2025-07-21 | Unknown | Unknown | No | 2024-09-11 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-11 | 2024-09-11 | Unknown | IOU Designed & Installed | N/A | Yes | 294 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3241 | 1219.03 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-11 | 2025-06-18 | 281 | 201 | 2025-06-18 | 2024-09-11 | Unknown | Unknown | 2024-09-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-11 | 2025-08-08 | 332 | 238 | Unknown | Unknown | Unknown | Unknown | 2025-08-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | OH | IOU Design | Commercial | N/A | Encinitas | ENCINITAS | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-04 | 2025-04-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 32997.38 | 79724.99 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-04 | 2025-04-03 | Unknown | Unknown | 2025-04-03 | 2025-09-02 | 153 | 109 | 2025-09-02 | 2025-09-02 | 1 | 1 | 2025-05-12 | 2025-06-13 | 33 | 25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN MARCOS | SAN MARCOS | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-21 | 2024-03-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 11637 | 47095.76 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-21 | 2023-11-13 | 85 | 61 | 2023-11-13 | 2025-05-19 | 554 | 396 | 2024-02-20 | 2024-09-18 | 212 | 152 | 2025-01-14 | 2025-06-09 | 52 | 36 | 2025-05-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | 99 | 99 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-14 | 2023-10-31 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3885 | 576.95 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-14 | 2023-10-31 | 18 | 12 | 2023-10-31 | 2023-10-31 | 1 | 1 | 2023-10-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-25 | 2024-06-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 20645 | 9283.87 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-25 | 2024-06-06 | Unknown | Unknown | 2024-06-06 | Unknown | Unknown | Unknown | 2025-01-10 | 2025-03-18 | 30 | 22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-23 | 2024-05-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 4570.7 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-23 | 2024-05-23 | 1 | 1 | 2024-05-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | 17.15 | 17.15 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-03 | Unknown | Unknown | No | 2025-04-21 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-21 | 2025-04-22 | Unknown | IOU Designed & Installed | N/A | Yes | 42 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1366.68 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-21 | 2025-06-02 | 43 | 31 | 2025-06-02 | 2025-04-01 | Unknown | Unknown | 2025-04-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-22 | 2025-08-13 | 114 | 82 | Unknown | Unknown | Unknown | Unknown | 2025-08-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-05 | 2023-09-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 851.99 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-05 | 2023-09-11 | 7 | 5 | 2023-09-11 | 2023-09-20 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-20 | Unknown | Unknown | Unknown | Unknown | 2023-09-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LA JOLLA | N/A | 111.05 | 111.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-20 | 2025-03-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1462.69 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-20 | 2025-03-19 | 28 | 20 | 2025-03-19 | 2025-04-02 | 15 | 11 | 2025-04-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-11 | 2024-09-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1112.74 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-11 | 2024-08-23 | Unknown | Unknown | 2024-08-23 | 2024-10-18 | 57 | 41 | 2024-10-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 37.8 | 37.8 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-28 | 2025-02-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 76.04 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-28 | 2025-03-27 | 28 | 20 | 2025-03-27 | 2025-03-27 | 1 | 1 | 2025-03-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-27 | 2025-07-23 | 119 | 85 | Unknown | Unknown | Unknown | Unknown | 2025-07-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 562 | 562 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | 2025-04-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1416.13 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-07 | 2025-04-17 | 11 | 9 | 2025-04-17 | 2025-04-17 | 1 | 1 | 2025-04-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-17 | 2025-08-13 | 119 | 85 | Unknown | 2025-07-22 | Unknown | Unknown | 2025-08-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | DEL MAR | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-18 | 2025-03-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1554.08 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-18 | 2024-12-04 | 48 | 34 | 2024-12-04 | 2025-06-04 | 183 | 131 | Unknown | Unknown | Unknown | Unknown | 2025-03-24 | 2025-05-30 | 68 | 50 | 2025-06-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Commercial | N/A | CB 1127-G1 CB Oaks Lot 3 (E) | CARLSBAD | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-16 | 2022-12-16 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 182497.85 | Unknown | Unknown | Yes | N/A | N/A | 2022-12-16 | 2023-09-13 | 272 | 194 | 2023-09-13 | 2025-01-22 | 498 | 356 | 2024-09-20 | 2025-09-04 | 8 | 6 | 2023-12-21 | 2025-08-14 | 431 | 309 | 2025-06-24 | Unknown | Unknown | Unknown | 2025-06-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | BORREGO SPRINGS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-23 | 2025-06-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 700.45 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-23 | 2025-05-20 | Unknown | Unknown | 2025-05-20 | 2025-06-23 | 35 | 25 | 2025-06-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-23 | 2025-07-03 | 11 | 9 | Unknown | Unknown | Unknown | Unknown | 2025-07-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-14 | 2024-05-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2177.84 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-14 | 2024-05-14 | 1 | 1 | 2024-05-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-04 | 2024-11-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1043.13 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-04 | 2024-11-04 | 1 | 1 | 2024-11-04 | 2024-11-04 | 1 | 1 | 2024-11-04 | Unknown | Unknown | Unknown | 2024-11-04 | 2024-11-06 | 3 | 3 | 2024-11-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-29 | 2022-10-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 478501 | 7360.06 | Unknown | Unknown | Yes | N/A | N/A | 2022-07-29 | 2023-03-28 | 243 | 173 | 2023-03-28 | 2023-03-29 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-07-10 | Unknown | Unknown | 2025-07-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | 216 | 216 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-03-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-29 | 2023-01-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 126095 | 10362.22 | Unknown | Unknown | Yes | N/A | N/A | 2022-09-29 | 2024-04-08 | 558 | 398 | 2024-04-08 | 2024-08-06 | 121 | 87 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-16 | 2024-08-16 | 2024-09-05 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2024-08-16 | 2024-08-15 | Unknown | Unknown | 2024-08-15 | 2024-08-19 | 5 | 3 | 2024-08-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-19 | 2024-09-05 | 18 | 14 | Unknown | Unknown | Unknown | Unknown | 2024-09-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-20 | 2024-08-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 192.95 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-20 | 2024-08-20 | 1 | 1 | 2024-08-20 | 2024-08-20 | 1 | 1 | 2024-08-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-23 | 2024-08-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2058.73 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-23 | 2024-09-26 | 66 | 48 | 2024-09-26 | 2024-09-27 | 2 | 2 | 2024-09-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-27 | 2025-08-19 | 327 | 233 | Unknown | Unknown | Unknown | Unknown | 2025-08-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 15 | 15 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-13 | 2025-03-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1954.79 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-13 | 2025-03-12 | Unknown | Unknown | 2025-03-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-13 | 2025-08-15 | 156 | 112 | Unknown | Unknown | Unknown | Unknown | 2025-08-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 48.05 | 48.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-11 | 2025-03-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1386.04 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-11 | 2025-03-13 | 3 | 3 | 2025-03-13 | 2025-03-13 | 1 | 1 | 2025-03-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-13 | 2025-07-31 | 141 | 101 | Unknown | Unknown | Unknown | Unknown | 2025-07-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | CORONADO | N/A | 86.05 | 86.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-13 | 2023-09-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7962 | 817.31 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-13 | 2023-09-13 | 1 | 1 | 2023-09-13 | 2024-01-31 | 141 | 101 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-31 | 2025-07-01 | 518 | 370 | Unknown | Unknown | Unknown | Unknown | 2025-07-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2021-04-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-04 | 2023-04-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 426.7 | Unknown | Unknown | Yes | N/A | N/A | 2023-04-04 | 2023-04-04 | 1 | 1 | 2023-04-04 | 2024-04-16 | 379 | 271 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-20 | 2023-10-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 21692 | 4623.34 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-20 | 2023-08-14 | 56 | 40 | 2023-08-14 | 2024-07-24 | 346 | 248 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 895 | 895 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-29 | 2022-11-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1578.98 | Unknown | Unknown | Yes | N/A | N/A | 2022-11-29 | 2023-02-13 | 77 | 55 | 2023-02-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 34.1 | 34.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-27 | 2025-04-24 | 2025-05-28 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2324.15 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-27 | 2025-04-23 | 28 | 20 | 2025-04-23 | 2025-04-24 | 2 | 2 | 2025-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-24 | 2025-05-28 | 35 | 25 | Unknown | Unknown | Unknown | Unknown | 2025-05-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-01 | 2024-06-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 27449 | 677.82 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-01 | 2024-06-01 | 1 | 0 | 2024-06-01 | 2024-06-01 | 1 | 0 | 2024-06-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 42 | 42 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-20 | 2025-02-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1753.19 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-20 | 2025-02-20 | 1 | 1 | 2025-02-20 | 2025-02-20 | 1 | 1 | 2025-02-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-17 | 2023-03-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 511.13 | Unknown | Unknown | Yes | N/A | N/A | 2023-01-17 | 2023-03-17 | 60 | 44 | 2023-03-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-04 | 2024-09-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 579.89 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-04 | 2024-08-29 | Unknown | Unknown | 2024-08-29 | 2024-10-04 | 37 | 27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-14 | 2025-05-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1151.7 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-14 | 2025-05-20 | 7 | 5 | 2025-05-20 | 2025-05-28 | 9 | 7 | 2025-05-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-13 | 2024-11-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1695.37 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-13 | 2025-01-07 | 56 | 40 | 2025-01-07 | 2025-01-13 | 7 | 5 | 2025-01-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-29 | 2023-11-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 978.42 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-29 | 2023-11-29 | 1 | 1 | 2023-11-29 | 2023-11-29 | 1 | 1 | 2023-11-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 104.05 | 104.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-08 | 2025-04-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7962 | 1043.36 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-08 | 2025-04-24 | 17 | 13 | 2025-04-24 | 2025-04-29 | 6 | 4 | 2025-04-21 | 2025-04-29 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | 2025-04-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-16 | 2024-06-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 560.26 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-16 | 2024-05-10 | 85 | 61 | 2024-05-10 | 2024-11-21 | 196 | 140 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-15 | 2025-01-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 924.08 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-15 | 2025-01-15 | 1 | 1 | 2025-01-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R29/R45) | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | 774 | 774 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-16 | 2024-03-04 | 2025-04-07 | IOU Designed & Installed | N/A | No | Unknown | 19318.14 | 496.71 | Unknown | Unknown | 2730.22 | 16091.21 | 1183586 | 113252.79 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-16 | 2024-03-04 | 355 | 253 | 2024-03-04 | 2024-08-29 | 179 | 129 | 2024-04-16 | 2025-04-04 | 53 | 39 | 2024-05-16 | 2024-08-27 | 35 | 25 | 2024-08-29 | 2025-06-30 | 306 | 218 | 2025-04-23 | 2025-07-09 | 78 | 56 | 2025-04-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-21 | 2024-05-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2024-05-21 | 2024-03-14 | Unknown | Unknown | 2024-03-14 | 2024-07-08 | 117 | 83 | 2024-07-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | ALPINE | N/A | 25 | 25 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-19 | 2024-12-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 818.62 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-19 | 2024-12-05 | Unknown | Unknown | 2024-12-05 | 2025-01-13 | 40 | 28 | 2025-01-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | 4674.4 | 4674.4 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-01-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-27 | 2024-08-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 15924 | 3750.17 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-27 | 2024-09-16 | 21 | 15 | 2024-09-16 | 2024-09-23 | 8 | 6 | 2024-09-17 | 2024-09-18 | 2 | 2 | 2024-09-16 | 2025-04-07 | 30 | 22 | 2024-09-23 | 2025-09-09 | 352 | 252 | Unknown | Unknown | Unknown | Unknown | 2025-07-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 64 | 64 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-28 | 2023-02-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 441.89 | Unknown | Unknown | Yes | N/A | N/A | 2023-02-28 | 2023-03-20 | 21 | 15 | 2023-03-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | 98 | 98 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-24 | 2024-09-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1231.32 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-24 | 2024-12-23 | 91 | 65 | 2024-12-23 | 2024-12-23 | 1 | 1 | 2024-12-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | RAMONA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-24 | 2025-01-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3987 | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2025-01-24 | 2025-01-28 | 5 | 3 | 2025-01-28 | 2025-02-25 | 29 | 21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-22 | Unknown | Unknown | No | 2024-12-17 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-17 | 2024-12-17 | Unknown | IOU Designed & Installed | N/A | Yes | 205 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 829.47 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-17 | 2025-07-10 | 206 | 148 | 2025-07-10 | 2025-07-10 | 1 | 1 | 2025-07-10 | 2025-04-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-04 | 2025-07-01 | 148 | 106 | Unknown | 2025-07-31 | Unknown | Unknown | 2025-07-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | Both | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-14 | 2025-02-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 855592.47 | 67702.87 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-14 | 2025-02-14 | 1 | 1 | 2025-02-14 | 2025-06-11 | 118 | 84 | 2025-03-25 | 2025-03-25 | 1 | 1 | 2025-04-10 | 2025-06-06 | 34 | 24 | 2025-06-11 | Unknown | Unknown | Unknown | 2025-06-30 | 2025-08-13 | 45 | 33 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | 33.05 | 33.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-12 | 2025-04-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 11943 | 1358.43 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-12 | 2025-04-25 | 73 | 53 | 2025-04-25 | 2025-05-21 | 27 | 19 | Unknown | Unknown | Unknown | Unknown | 2025-04-29 | 2025-05-16 | 18 | 14 | 2025-05-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | San Diego | SAN DIEGO | 21.6 | 21.6 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-27 | 2024-09-27 | 2025-06-19 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 30485.65 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-27 | 2024-08-02 | Unknown | Unknown | 2024-08-02 | 2025-03-18 | 229 | 163 | Unknown | Unknown | Unknown | Unknown | 2025-03-10 | 2025-05-06 | 37 | 25 | 2025-03-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community,Tribal Community | ALPINE | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-09 | 2024-02-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 396217.28 | 35578.29 | Unknown | Unknown | Yes | N/A | N/A | 2023-05-09 | 2023-06-14 | 37 | 27 | 2023-06-14 | 2024-08-29 | 443 | 317 | 2024-03-25 | 2025-05-16 | 337 | 243 | 2024-08-19 | 2025-05-16 | 271 | 195 | 2024-08-29 | Unknown | Unknown | Unknown | 2024-10-17 | 2025-05-21 | 217 | 155 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Commercial | N/A | San Diego | San Diego | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-10 | 2023-02-10 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 67705.38 | Unknown | Unknown | Yes | N/A | N/A | 2023-02-10 | 2023-05-11 | 91 | 65 | 2023-05-11 | 2025-04-29 | 720 | 514 | 2023-05-19 | 2025-04-30 | 21 | 15 | 2025-04-28 | 2025-05-16 | 19 | 15 | 2025-05-30 | Unknown | Unknown | Unknown | 2025-05-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-16 | 2024-02-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 850.59 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-16 | 2024-03-13 | 27 | 19 | 2024-03-13 | 2024-03-29 | 17 | 13 | 2024-03-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-05 | Unknown | Unknown | No | 2023-04-17 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-14 | 2023-04-17 | Unknown | IOU Designed & Installed | N/A | Yes | 543 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1177.93 | Unknown | Unknown | Yes | N/A | N/A | 2023-04-14 | 2024-10-08 | 544 | 388 | 2024-10-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-27 | 2023-07-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 650.91 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-27 | 2023-05-09 | Unknown | Unknown | 2023-05-09 | 2023-09-25 | 140 | 100 | 2023-09-25 | 2023-11-16 | 53 | 39 | Unknown | Unknown | Unknown | Unknown | 2023-11-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | N/A | 194 | 194 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-04 | 2023-12-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3793.02 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-04 | 2023-09-12 | Unknown | Unknown | 2023-09-12 | 2024-01-09 | 120 | 86 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | FALLBROOK | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-01 | 2023-12-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1031.76 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-01 | 2024-01-09 | 40 | 28 | 2024-01-09 | 2024-01-11 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | OH | IOU Design | Commercial | Disadvantaged Community,Underserved Community | EL CAJON | N/A | 168 | 168 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-31 | 2023-10-31 | 2024-01-18 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3391.38 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-31 | 2023-10-31 | 1 | 1 | 2023-10-31 | 2023-12-19 | 50 | 36 | Unknown | Unknown | Unknown | Unknown | 2024-01-10 | 2024-01-10 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | IOU Design | Residential | Underserved Community | La Mesa | La Mesa | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-01-01 | Unknown | Unknown | No | 2022-01-27 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-01-27 | 2022-01-31 | Unknown | IOU Designed & Installed | N/A | Yes | 621 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 175270.28 | 55582.97 | Unknown | Unknown | Yes | N/A | N/A | 2022-01-27 | 2024-03-12 | 776 | 554 | 2024-03-12 | 2024-05-06 | 56 | 40 | 2022-01-31 | 2024-10-31 | 86 | 60 | 2024-02-14 | 2024-06-28 | 71 | 53 | Unknown | Unknown | Unknown | Unknown | 2024-05-13 | 2025-03-11 | 303 | 217 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-23 | 2023-03-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 45577.6 | 2411.99 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-23 | 2023-02-15 | Unknown | Unknown | 2023-02-15 | 2023-04-06 | 51 | 37 | Unknown | Unknown | Unknown | Unknown | 2023-03-24 | 2023-04-05 | 13 | 9 | 2023-04-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 52.05 | 52.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-13 | 2024-09-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | 1868.03 | 0 | Unknown | Unknown | 52.47 | 1815.56 | 3981 | 1236.79 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-13 | 2024-12-11 | 90 | 64 | 2024-12-11 | 2024-12-12 | 2 | 2 | 2024-12-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-12 | 2025-07-01 | 202 | 144 | Unknown | 2025-06-30 | Unknown | Unknown | 2025-07-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | COUNTY OF SAN DIEGO-SOUTH of 56 | 225 | 225 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-09 | 2025-06-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 810.65 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-09 | 2025-05-23 | Unknown | Unknown | 2025-05-23 | 2025-06-13 | 22 | 16 | 2025-06-13 | Unknown | Unknown | Unknown | 2025-06-27 | 2025-07-03 | 7 | 5 | 2025-06-13 | 2025-07-22 | 40 | 28 | Unknown | Unknown | Unknown | Unknown | 2025-07-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | 16 | 16 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-06 | 2025-03-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7962 | 792.63 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-06 | 2024-11-14 | Unknown | Unknown | 2024-11-14 | 2025-04-08 | 146 | 104 | Unknown | Unknown | Unknown | Unknown | 2025-04-01 | 2025-04-22 | 22 | 16 | 2025-04-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 12 | 12 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-27 | 2023-02-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3885 | 503.31 | Unknown | Unknown | Yes | N/A | N/A | 2023-02-27 | 2023-03-06 | 8 | 6 | 2023-03-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-16 | 2025-01-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1082.63 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-16 | 2025-02-04 | 20 | 14 | 2025-02-04 | 2025-02-07 | 4 | 4 | 2025-02-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 135 | 135 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-24 | 2024-09-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1626.7 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-24 | 2024-10-04 | 11 | 9 | 2024-10-04 | 2024-10-10 | 7 | 5 | 2024-10-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-04 | 2024-12-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 18103.88 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-04 | 2024-11-15 | Unknown | Unknown | 2024-11-15 | 2025-01-27 | 74 | 52 | Unknown | Unknown | Unknown | Unknown | 2025-02-11 | 2025-02-11 | 1 | 1 | 2025-01-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R29/R45 | UG | IOU Design | Commercial | Underserved Community | VISTA | VISTA | 190 | 190 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-12 | 2024-08-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 73810.44 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-12 | 2025-01-27 | 200 | 142 | 2025-01-27 | 2025-06-03 | 128 | 92 | 2025-02-18 | 2025-05-02 | 4 | 4 | 2025-05-21 | 2025-07-08 | 48 | 34 | 2025-06-03 | Unknown | Unknown | Unknown | 2025-07-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | OH | IOU Design | Residential | Underserved Community | San Marcos | San Marcos | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-21 | 2024-02-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 41179.03 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-21 | 2024-11-25 | 279 | 199 | 2024-11-25 | 2025-08-05 | 254 | 182 | Unknown | Unknown | Unknown | Unknown | 2024-11-26 | 2025-08-07 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | RAMONA | N/A | 106.75 | 106.75 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-04 | 2025-06-04 | 2025-06-16 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1106.01 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-04 | 2025-05-20 | Unknown | Unknown | 2025-05-20 | 2025-06-04 | 16 | 12 | 2025-06-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-04 | 2025-06-16 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2025-06-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 30 | 30 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-20 | Unknown | Unknown | No | 2023-10-20 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-20 | 2023-11-02 | 2024-04-05 | IOU Designed & Installed | N/A | Yes | 143 | -19.1 | -15.5 | Unknown | Unknown | Unknown | -3.6 | 0 | 513.31 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-20 | 2024-03-11 | 144 | 102 | 2024-03-11 | 2023-10-31 | Unknown | Unknown | 2023-10-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-02 | 2024-04-05 | 156 | 112 | Unknown | Unknown | Unknown | Unknown | 2024-04-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-06 | 2025-01-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 9150 | 1050.86 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-06 | 2025-01-23 | 49 | 35 | 2025-01-23 | 2025-01-23 | 1 | 1 | 2025-01-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LAKESIDE | COUNTY OF SAN DIEGO-SOUTH of 56 | 21 | 21 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-02 | 2024-05-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 8353.3 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-02 | 2024-05-02 | 1 | 1 | 2024-05-02 | 2024-09-11 | 133 | 95 | 2024-06-12 | 2024-08-02 | 4 | 4 | 2024-08-02 | 2024-09-12 | 10 | 6 | 2024-09-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-20 | 2023-06-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 111.56 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-20 | 2023-07-07 | 18 | 14 | 2023-07-07 | 2023-07-07 | 1 | 1 | 2023-07-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 13.35 | 13.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-15 | 2024-10-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1227.38 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-15 | 2024-10-28 | 14 | 10 | 2024-10-28 | 2024-11-04 | 8 | 6 | 2024-11-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-10 | 2024-04-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 47772 | 4202.84 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-10 | 2024-04-10 | 1 | 1 | 2024-04-10 | 2024-05-30 | 51 | 37 | Unknown | Unknown | Unknown | Unknown | 2024-04-11 | 2024-05-03 | 23 | 17 | 2024-05-30 | 2025-07-25 | 422 | 302 | Unknown | 2025-07-25 | Unknown | Unknown | 2025-08-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | San Diego | SAN DIEGO | 1286 | 1286 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2024-04-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-14 | 2024-04-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 213266 | 24996.29 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-14 | 2024-03-25 | 194 | 138 | 2024-03-25 | 2024-10-10 | 200 | 144 | 2024-07-16 | 2024-07-17 | 2 | 2 | 2024-08-12 | 2024-10-29 | 59 | 43 | 2024-10-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | CARDIFF | ENCINITAS | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-18 | 2025-04-18 | 2025-06-23 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1637.39 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-18 | 2025-04-18 | 1 | 1 | 2025-04-18 | 2025-04-18 | 1 | 1 | 2025-04-18 | Unknown | Unknown | Unknown | 2025-04-21 | 2025-06-17 | 58 | 42 | 2025-04-18 | 2025-06-23 | 67 | 47 | Unknown | Unknown | Unknown | Unknown | 2025-06-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-19 | 2024-09-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 40893 | 2809.85 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-19 | 2024-04-24 | 6 | 4 | 2024-04-24 | 2024-09-20 | 150 | 108 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | BORREGO SPRINGS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-18 | 2025-03-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 16276.04 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-18 | 2025-03-18 | 1 | 1 | 2025-03-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 71 | 71 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-24 | 2025-03-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7962 | 1444.57 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-24 | 2025-01-27 | Unknown | Unknown | 2025-01-27 | 2025-03-27 | 60 | 44 | 2025-03-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-14 | 2025-03-31 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1752.38 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-14 | 2025-03-11 | Unknown | Unknown | 2025-03-11 | 2025-03-31 | 21 | 15 | 2025-03-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-06 | 2023-03-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 406.07 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-06 | 2023-03-06 | 1 | 1 | 2023-03-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | Disadvantaged Community,Underserved Community | San Diego | San Diego | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-18 | 2023-07-18 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 43569 | 38953.91 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-18 | 2023-11-13 | 119 | 85 | 2023-11-13 | 2024-10-09 | 332 | 238 | 2023-12-16 | 2024-05-29 | 28 | 20 | 2023-08-24 | 2024-06-04 | 11 | 7 | 2024-10-24 | Unknown | Unknown | Unknown | 2024-10-24 | 2025-07-28 | 278 | 198 | 2025-08-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | EL CAJON | 97.05 | 97.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-09 | 2024-12-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2219.08 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-09 | 2024-11-26 | Unknown | Unknown | 2024-11-26 | 2024-12-11 | 16 | 12 | 2024-12-11 | Unknown | Unknown | Unknown | 2025-01-13 | 2025-02-25 | 24 | 17 | 2024-12-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-14 | 2024-05-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 5804.29 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-14 | 2024-05-29 | 16 | 12 | 2024-05-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-17 | 2023-04-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 468.73 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-17 | 2023-04-14 | 29 | 21 | 2023-04-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN JUAN CAPISTRANO | N/A | 190 | 190 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-30 | 2023-10-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 158.14 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-30 | 2023-10-25 | Unknown | Unknown | 2023-10-25 | 2023-11-01 | 8 | 6 | 2023-11-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | RAMONA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-21 | 2025-05-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2063 | 568.05 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-21 | 2025-05-27 | 7 | 5 | 2025-05-27 | 2025-06-17 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | FALLBROOK | COUNTY OF SAN DIEGO-NORTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-22 | 2024-11-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1606.36 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-22 | 2024-10-18 | Unknown | Unknown | 2024-10-18 | 2024-11-25 | 39 | 27 | 2024-11-25 | Unknown | Unknown | Unknown | 2024-11-25 | 2024-12-06 | 12 | 10 | 2024-11-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-06 | 2024-11-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 24400.55 | 686.23 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-06 | 2024-10-20 | Unknown | Unknown | 2024-10-20 | 2025-01-24 | 97 | 70 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | OH | IOU Design | Residential | Underserved Community | San Marcos | N/A | 317 | 317 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-15 | 2023-05-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 14977.1 | Unknown | Unknown | Yes | N/A | N/A | 2022-12-15 | 2023-05-08 | 145 | 103 | 2023-05-08 | 2025-01-03 | 607 | 435 | Unknown | Unknown | Unknown | Unknown | 2024-12-18 | 2025-01-08 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 68.05 | 68.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-18 | 2024-07-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1823.46 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-18 | 2024-07-18 | 1 | 1 | 2024-07-18 | 2024-07-18 | 1 | 1 | 2024-07-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | CARLSBAD | CARLSBAD | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-18 | 2024-08-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 24883 | 759.97 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-18 | 2024-08-22 | 66 | 48 | 2024-08-22 | 2025-03-14 | 205 | 147 | 2024-10-01 | 2024-11-04 | 35 | 25 | 2024-08-27 | 2025-07-14 | 116 | 84 | 2025-03-14 | 2025-08-06 | 146 | 104 | Unknown | 2025-08-26 | Unknown | Unknown | 2025-08-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-15 | Unknown | Unknown | No | 2024-04-18 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-18 | 2024-04-18 | Unknown | IOU Designed & Installed | N/A | Yes | 15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 12481 | 584.27 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-18 | 2024-05-03 | 16 | 12 | 2024-05-03 | 2024-04-18 | Unknown | Unknown | 2024-04-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-18 | 2025-08-21 | 491 | 351 | Unknown | Unknown | Unknown | Unknown | 2025-08-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | CAPISTRANO BEACH | N/A | 105.05 | 105.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-28 | 2024-01-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7962 | 6891.3 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-28 | 2024-12-09 | 348 | 248 | 2024-12-09 | 2024-12-19 | 11 | 9 | 2024-12-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-19 | Unknown | Unknown | Unknown | Unknown | 2025-09-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 5 | 5 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-01 | Unknown | Unknown | No | 2024-01-18 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-18 | 2024-01-18 | 2024-07-10 | IOU Designed & Installed | N/A | Yes | 40 | 3513.55 | 626 | Unknown | Unknown | 176.86 | 2710.69 | 3981 | 1209.97 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-18 | 2024-02-27 | 41 | 29 | 2024-02-27 | 2024-01-19 | Unknown | Unknown | 2024-01-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-19 | 2024-07-10 | 174 | 124 | Unknown | Unknown | Unknown | Unknown | 2024-07-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SOLANA BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-13 | 2024-03-14 | 2024-07-31 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1003.25 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-13 | 2024-02-29 | 79 | 57 | 2024-02-29 | 2024-03-08 | 9 | 7 | 2024-03-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-14 | 2024-07-31 | 140 | 100 | Unknown | Unknown | Unknown | Unknown | 2024-07-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | BONITA | N/A | 13 | 13 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-16 | 2025-06-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1006.34 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-16 | 2025-06-16 | 1 | 1 | 2025-06-16 | 2025-06-27 | 12 | 10 | 2025-06-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-27 | 2025-07-02 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2025-07-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 503 | 503 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-16 | 2024-08-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1106.45 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-16 | 2024-07-24 | Unknown | Unknown | 2024-07-24 | 2024-09-04 | 43 | 31 | 2024-09-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | Underserved Community | Ramona | COUNTY OF SAN DIEGO-NORTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-07 | 2024-03-07 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 50822.72 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-07 | 2024-09-11 | 189 | 135 | 2024-09-11 | 2025-02-25 | 168 | 120 | 2024-09-11 | 2025-02-20 | 122 | 86 | 2025-02-20 | 2025-06-05 | 22 | 16 | 2025-03-24 | Unknown | Unknown | Unknown | 2025-03-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2028-04-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-30 | 2025-04-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1150.25 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-30 | 2025-04-18 | Unknown | Unknown | 2025-04-18 | 2025-08-04 | 109 | 77 | 2025-08-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | ESCONDIDO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2024-09-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-30 | 2024-10-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3753.77 | 1338.12 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-30 | 2024-10-30 | 1 | 1 | 2024-10-30 | 2025-06-13 | 227 | 163 | Unknown | Unknown | Unknown | Unknown | 2025-03-05 | 2025-05-23 | 80 | 58 | 2025-06-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | 49.28 | 49.28 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-30 | 2023-06-30 | 2024-06-12 | IOU Designed & Installed | N/A | No | Unknown | 2460.61 | 608.4 | Unknown | Unknown | 109.78 | 1742.43 | 3981 | 941.73 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-30 | 2023-06-30 | 1 | 1 | 2023-06-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-30 | 2024-06-12 | 349 | 249 | Unknown | Unknown | Unknown | Unknown | 2024-06-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ESCONDIDO | COUNTY OF SAN DIEGO-SOUTH of 56 | 65.05 | 65.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-11 | 2024-11-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 1603 | 13545.33 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-11 | 2024-11-11 | 1 | 1 | 2024-11-11 | 2025-07-02 | 234 | 168 | Unknown | Unknown | Unknown | Unknown | 2025-04-29 | 2025-07-15 | 24 | 18 | 2025-07-02 | Unknown | Unknown | Unknown | 2025-07-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | LEMON GROVE | N/A | 430 | 430 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-06 | 2024-05-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 320957 | 5327.81 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-06 | 2024-05-06 | 1 | 1 | 2024-05-06 | 2024-05-30 | 25 | 19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-08 | 2024-08-08 | 2024-10-30 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 462.37 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-08 | 2024-08-06 | Unknown | Unknown | 2024-08-06 | 2024-08-16 | 11 | 9 | 2024-08-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-16 | 2024-10-30 | 76 | 54 | Unknown | 2025-04-07 | Unknown | Unknown | 2024-10-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-12 | 2024-06-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1661.75 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-12 | 2024-05-28 | Unknown | Unknown | 2024-05-28 | 2024-06-21 | 25 | 19 | 2024-06-21 | Unknown | Unknown | Unknown | 2024-06-21 | 2024-07-11 | 21 | 15 | 2024-06-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-24 | 2025-02-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 988.78 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-24 | 2025-02-21 | Unknown | Unknown | 2025-02-21 | 2025-02-24 | 4 | 2 | 2025-02-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-15 | 2024-05-15 | 2025-02-04 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 4512.09 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-15 | 2024-05-15 | 1 | 1 | 2024-05-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | OH | IOU Design | Residential | Underserved Community | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-27 | 2024-02-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 21940.8 | 126311.82 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-27 | 2024-02-27 | 1 | 1 | 2024-02-27 | 2025-05-28 | 457 | 327 | Unknown | Unknown | Unknown | Unknown | 2024-05-31 | 2025-06-05 | 28 | 20 | 2025-05-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-06-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-16 | 2025-06-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 990.54 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-16 | 2025-06-16 | 1 | 1 | 2025-06-16 | 2025-06-16 | 1 | 1 | 2025-06-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-16 | 2025-07-29 | 44 | 32 | Unknown | Unknown | Unknown | Unknown | 2025-07-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-01 | 2023-03-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 14210 | 535.09 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-01 | 2023-03-01 | 1 | 1 | 2023-03-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-08-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-30 | 2024-08-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7995 | 511.86 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-30 | 2024-08-30 | 1 | 1 | 2024-08-30 | 2024-08-30 | 1 | 1 | 2024-08-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-30 | 2025-09-05 | 372 | 266 | Unknown | Unknown | Unknown | Unknown | 2025-09-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | POWAY | N/A | 18.05 | 18.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-30 | 2025-04-30 | 2025-05-20 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1196.57 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-30 | 2025-05-08 | 9 | 7 | 2025-05-08 | 2025-05-08 | 1 | 1 | 2025-05-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-14 | 2025-05-20 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2025-05-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SANTA YSABEL | N/A | 51 | 51 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-22 | 2023-05-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 584.47 | Unknown | Unknown | Yes | N/A | N/A | 2023-05-22 | 2023-06-02 | 12 | 10 | 2023-06-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-14 | 2024-12-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 19417.98 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-14 | 2024-08-20 | 7 | 5 | 2024-08-20 | 2025-02-11 | 176 | 126 | 2024-12-05 | 2024-12-05 | 1 | 1 | 2025-02-13 | 2025-02-24 | 12 | 8 | 2025-02-11 | Unknown | Unknown | Unknown | 2025-04-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | DANA POINT | N/A | 72 | 72 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-03 | 2025-04-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 196.59 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-03 | 2025-04-16 | 14 | 10 | 2025-04-16 | 2025-04-18 | 3 | 3 | 2025-04-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-24 | 2024-09-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1915.63 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-24 | 2024-09-13 | 52 | 38 | 2024-09-13 | 2024-09-30 | 18 | 12 | 2024-09-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 2638.25 | 2638.25 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-10-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-02 | 2023-10-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 154.99 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-02 | 2023-09-27 | Unknown | Unknown | 2023-09-27 | 2023-10-02 | 6 | 4 | 2023-10-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-27 | 2024-07-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2824.7 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-27 | 2023-10-18 | 22 | 16 | 2023-10-18 | 2024-11-25 | 405 | 289 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | 651 | 651 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-22 | 2024-02-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 85388 | 7882.82 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-22 | 2024-09-17 | 209 | 149 | 2024-09-17 | 2024-11-08 | 53 | 39 | Unknown | Unknown | Unknown | Unknown | 2024-10-31 | 2024-12-06 | 37 | 27 | 2024-11-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | VISTA | VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-02 | 2024-03-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 404387 | 47501.13 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-02 | 2024-01-24 | Unknown | Unknown | 2024-01-24 | 2024-11-11 | 293 | 209 | 2024-03-20 | 2025-02-19 | 129 | 93 | 2024-11-08 | 2025-07-22 | 113 | 81 | 2024-11-11 | 2025-07-08 | 240 | 172 | 2025-01-27 | 2025-08-14 | 200 | 144 | 2025-08-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-17 | Unknown | Unknown | No | 2024-07-25 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-25 | 2024-07-25 | Unknown | IOU Designed & Installed | N/A | Yes | 90 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1135.32 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-25 | 2024-10-23 | 91 | 65 | 2024-10-23 | 2024-08-01 | Unknown | Unknown | 2024-08-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 3.35 | 3.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-17 | 2023-10-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 762.65 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-17 | 2023-10-17 | 1 | 1 | 2023-10-17 | 2023-10-17 | 1 | 1 | 2023-10-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 35 | 35 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-27 | 2025-03-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1396.81 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-27 | 2025-03-17 | Unknown | Unknown | 2025-03-17 | 2025-03-28 | 12 | 10 | 2025-03-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | San Diego | N/A | 6720 | 6720 | Not Available | >2MW | No | N/A | N/A | N/A | 2025-11-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-18 | 2024-09-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 205791 | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2024-09-18 | 2023-06-28 | Unknown | Unknown | 2023-06-28 | 2025-01-09 | 562 | 402 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-05-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-12 | 2023-11-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 8370 | 610.1 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-12 | 2023-10-10 | 29 | 21 | 2023-10-10 | 2023-11-27 | 49 | 35 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-15 | 2024-11-15 | 2024-12-03 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1824.54 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-15 | 2024-11-14 | Unknown | Unknown | 2024-11-14 | 2024-11-15 | 2 | 2 | 2024-11-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-15 | 2024-12-03 | 19 | 13 | Unknown | Unknown | Unknown | Unknown | 2024-12-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 90 | 90 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-13 | 2024-09-16 | 2024-10-15 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1605.16 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-13 | 2024-05-20 | Unknown | Unknown | 2024-05-20 | 2024-09-16 | 120 | 86 | 2024-09-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-16 | 2024-10-15 | 30 | 22 | Unknown | Unknown | Unknown | Unknown | 2024-10-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-18 | 2024-07-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 174713 | 10494.41 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-18 | 2023-11-28 | Unknown | Unknown | 2023-11-28 | 2024-10-15 | 323 | 231 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-15 | 2025-07-31 | 290 | 208 | Unknown | 2025-07-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-19 | 2025-03-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1018.72 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-19 | 2025-03-12 | 22 | 16 | 2025-03-12 | 2025-03-12 | 1 | 1 | 2025-03-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | ENCINITAS | ENCINITAS | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-10 | 2023-04-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1026.64 | Unknown | Unknown | Yes | N/A | N/A | 2023-01-10 | 2023-04-10 | 91 | 65 | 2023-04-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-18 | 2023-06-20 | 34 | 24 | 2023-04-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-12 | 2025-05-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 450.11 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-12 | 2025-04-17 | Unknown | Unknown | 2025-04-17 | 2025-05-13 | 27 | 19 | 2025-05-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-13 | 2025-08-15 | 95 | 69 | Unknown | Unknown | Unknown | Unknown | 2025-08-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | N/A | 38 | 38 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-19 | 2023-12-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 5447.71 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-19 | 2023-12-19 | 1 | 1 | 2023-12-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 73 | 73 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-13 | 2025-04-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1901.08 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-13 | 2025-04-01 | 48 | 34 | 2025-04-01 | 2025-04-10 | 10 | 8 | 2025-04-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-10 | 2025-04-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 8878.25 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-10 | 2025-04-10 | 1 | 1 | 2025-04-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-08-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | LA JOLLA | 228.2 | 228.2 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-24 | 2023-09-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2275.74 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-24 | 2024-03-26 | 185 | 132 | 2024-03-26 | 2024-04-25 | 31 | 23 | Unknown | Unknown | Unknown | Unknown | 2024-04-24 | 2024-05-22 | 29 | 21 | 2024-04-25 | Unknown | Unknown | Unknown | Unknown | 2025-07-07 | Unknown | Unknown | 2025-08-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-03-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-24 | 2023-04-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 336.12 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-24 | 2023-04-04 | 12 | 8 | 2023-04-04 | 2023-05-16 | 43 | 31 | 2023-05-05 | 2023-07-31 | 80 | 56 | 2023-05-23 | 2023-08-04 | 15 | 13 | 2023-05-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | RAMONA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-16 | 2024-04-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 498.93 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-16 | 2023-11-14 | Unknown | Unknown | 2023-11-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-01 | 2025-05-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3241 | 383.95 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-01 | 2025-05-01 | 1 | 1 | 2025-05-01 | 2025-05-01 | 1 | 1 | 2025-05-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 50 | 50 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-04 | 2025-04-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 821.95 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-04 | 2025-04-28 | 25 | 17 | 2025-04-28 | 2025-05-07 | 10 | 8 | 2025-05-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-07 | 2025-09-02 | 119 | 85 | Unknown | 2025-09-02 | Unknown | Unknown | 2025-09-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-30 | 2024-05-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1078.83 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-30 | 2024-04-05 | Unknown | Unknown | 2024-04-05 | 2024-05-21 | 47 | 33 | 2024-05-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-02 | 2024-07-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | 509.67 | 136.64 | Unknown | Unknown | 20.28 | 352.75 | 3981 | 6579.06 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-02 | 2024-06-28 | Unknown | Unknown | 2024-06-28 | 2024-07-25 | 28 | 20 | 2024-07-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2018-04-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-24 | 2025-04-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 794.39 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-24 | 2025-04-22 | Unknown | Unknown | 2025-04-22 | 2025-04-24 | 3 | 3 | 2025-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-10 | 2024-09-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 9150 | 511.86 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-10 | 2024-09-10 | 1 | 1 | 2024-09-10 | 2024-09-10 | 1 | 1 | 2024-09-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2025-10-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-27 | 2025-02-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 6923.86 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-27 | 2025-01-27 | 1 | 1 | 2025-01-27 | 2025-04-25 | 89 | 65 | 2025-03-19 | 2025-03-28 | 10 | 8 | 2025-04-09 | 2025-05-07 | 29 | 21 | 2025-07-31 | Unknown | Unknown | Unknown | 2025-07-31 | 2025-08-18 | 19 | 13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 74 | 74 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-09 | 2023-10-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3941 | 942.99 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-09 | 2023-08-16 | Unknown | Unknown | 2023-08-16 | 2023-10-09 | 55 | 39 | 2023-10-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | OCEANSIDE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-09 | 2023-02-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1650.5 | Unknown | Unknown | Yes | N/A | N/A | 2023-02-09 | 2023-02-15 | 7 | 5 | 2023-02-15 | 2023-04-19 | 64 | 46 | Unknown | Unknown | Unknown | Unknown | 2023-02-16 | 2024-11-07 | 100 | 72 | 2023-04-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-12 | 2025-06-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1060.05 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-12 | 2025-07-08 | 27 | 19 | 2025-07-08 | 2025-06-18 | Unknown | Unknown | 2025-06-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2021-09-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-23 | 2023-10-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 385.42 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-23 | 2023-09-19 | 28 | 20 | 2023-09-19 | 2024-07-09 | 295 | 211 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-09 | 2025-08-04 | 392 | 280 | Unknown | 2025-06-27 | Unknown | Unknown | 2025-07-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 200043.05 | 200043.05 | Not Available | >2MW | No | N/A | N/A | N/A | 2025-02-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-03 | 2024-07-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7962 | 1698.13 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-03 | 2024-07-03 | 1 | 1 | 2024-07-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | ESCONDIDO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2024-09-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-29 | 2024-10-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3753.77 | 687.74 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-29 | 2024-10-29 | 1 | 1 | 2024-10-29 | 2025-05-06 | 190 | 136 | Unknown | Unknown | Unknown | Unknown | 2025-03-31 | 2025-04-11 | 12 | 10 | 2025-05-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-05 | 2024-06-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1407.12 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-05 | 2024-05-16 | Unknown | Unknown | 2024-05-16 | 2024-06-20 | 36 | 26 | 2024-06-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | LAKESIDE | N/A | 330 | 330 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-02-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-29 | 2023-03-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 662.86 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-29 | 2023-03-29 | 1 | 1 | 2023-03-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | 138 | 138 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-16 | 2023-08-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 508597 | 14318.24 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-16 | 2024-09-16 | 398 | 284 | 2024-09-16 | 2024-10-03 | 18 | 14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-03 | Unknown | Unknown | Unknown | Unknown | 2024-11-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | NATIONAL CITY, SAN DIEGO | 39.05 | 39.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-30 | 2025-02-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7962 | 1193.53 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-30 | 2025-02-06 | 8 | 6 | 2025-02-06 | 2025-02-27 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | 2025-02-11 | 2025-04-10 | 59 | 43 | 2025-02-27 | 2025-05-27 | 90 | 64 | Unknown | Unknown | Unknown | Unknown | 2025-07-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 63 | 63 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-13 | Unknown | Unknown | No | 2024-06-10 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-04 | 2024-06-10 | Unknown | IOU Designed & Installed | N/A | Yes | 357 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1351.12 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-04 | 2025-05-28 | 420 | 300 | 2025-05-28 | 2024-06-10 | Unknown | Unknown | 2024-06-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | RAMONA | N/A | 67.05 | 67.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-23 | 2024-10-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2638.66 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-23 | 2024-10-11 | Unknown | Unknown | 2024-10-11 | 2024-10-23 | 13 | 9 | 2024-10-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-23 | 2025-07-03 | 254 | 182 | Unknown | Unknown | Unknown | Unknown | 2025-07-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | BOULEVARD | COUNTY OF SAN DIEGO-SOUTH of 56 | 21.05 | 21.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-25 | 2024-07-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 467.95 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-25 | 2024-07-25 | 1 | 1 | 2024-07-25 | 2024-08-29 | 36 | 26 | Unknown | Unknown | Unknown | Unknown | 2024-08-07 | 2024-08-09 | 3 | 3 | 2024-08-29 | 2024-11-27 | 91 | 65 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | OCEANSIDE | 145 | 145 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-03 | 2025-02-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 12652.98 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-03 | 2025-01-22 | Unknown | Unknown | 2025-01-22 | 2025-05-19 | 118 | 84 | Unknown | Unknown | Unknown | Unknown | 2025-03-05 | 2025-05-01 | 46 | 34 | 2025-05-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-09 | 2024-09-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3236.63 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-09 | 2024-09-05 | Unknown | Unknown | 2024-09-05 | 2025-01-09 | 127 | 91 | Unknown | Unknown | Unknown | Unknown | 2025-06-30 | 2025-06-30 | 1 | 1 | 2025-01-09 | 2025-07-10 | 183 | 131 | Unknown | 2025-06-27 | Unknown | Unknown | 2025-07-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-09-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-04 | 2024-03-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 35829 | 1316.93 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-04 | 2024-02-29 | Unknown | Unknown | 2024-02-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 48.05 | 48.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-22 | 2023-11-22 | 2023-12-06 | IOU Designed & Installed | N/A | No | Unknown | 1330.11 | -43.71 | Unknown | Unknown | 85.95 | 1287.87 | 3981 | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2023-11-22 | 2023-08-10 | Unknown | Unknown | 2023-08-10 | 2023-11-22 | 105 | 75 | 2023-11-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-28 | 2023-12-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | MISSION VIEJO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-12 | 2024-02-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 823.57 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-12 | 2024-01-17 | Unknown | Unknown | 2024-01-17 | 2024-02-27 | 42 | 30 | 2024-02-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-09 | 2024-04-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 846.93 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-09 | 2024-03-20 | Unknown | Unknown | 2024-03-20 | 2024-04-30 | 42 | 30 | 2024-04-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-06-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-25 | 2025-06-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1026.48 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-25 | 2025-06-25 | 1 | 1 | 2025-06-25 | 2025-06-25 | 1 | 1 | 2025-06-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 2.7 | 2.7 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-01 | 2024-10-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 952.8 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-01 | 2024-10-10 | 10 | 8 | 2024-10-10 | 2024-10-18 | 9 | 7 | 2024-10-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-04 | 2025-04-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 932.2 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-04 | 2025-05-07 | 34 | 24 | 2025-05-07 | 2025-05-08 | 2 | 2 | 2025-05-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Residential | Underserved Community | La Jolla | N/A | 217 | 217 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-12-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-12 | 2023-09-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1105.43 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-12 | 2023-09-12 | 1 | 1 | 2023-09-12 | 2023-11-09 | 59 | 43 | Unknown | Unknown | Unknown | Unknown | 2023-11-09 | 2023-11-09 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-10 | 2024-05-10 | 2024-05-13 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 307.58 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-10 | 2024-02-09 | Unknown | Unknown | 2024-02-09 | 2024-05-10 | 92 | 66 | 2024-05-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-10 | 2024-05-13 | 4 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-05-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2024-01-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-31 | 2023-10-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 121810 | 25770.66 | Unknown | Unknown | Yes | N/A | N/A | 2023-01-31 | 2023-04-17 | 77 | 55 | 2023-04-17 | 2024-01-16 | 275 | 197 | 2023-10-04 | 2023-10-09 | 6 | 4 | 2024-01-16 | 2024-01-19 | 4 | 4 | 2024-01-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-10 | 2024-03-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 28804 | 344.91 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-10 | 2023-11-22 | Unknown | Unknown | 2023-11-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-04 | 2024-12-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 706.84 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-04 | 2024-12-10 | 7 | 5 | 2024-12-10 | 2024-12-11 | 2 | 2 | 2024-12-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | IOU Design | Commercial | N/A | RANCHO MISSION VIEJO | COUNTY OF ORANGE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-09 | 2024-08-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 4713492 | 292013.35 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-09 | 2024-06-18 | Unknown | Unknown | 2024-06-18 | 2025-05-16 | 333 | 239 | 2024-11-13 | 2025-08-26 | 108 | 78 | 2024-09-12 | 2025-03-14 | 55 | 39 | 2025-05-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | VALLEY CENTER | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-06-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-30 | 2025-05-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 1378.58 | 436.6 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-30 | 2025-05-27 | Unknown | Unknown | 2025-05-27 | 2025-06-05 | 10 | 8 | 2025-06-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 9.05 | 9.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-05 | 2025-06-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 3007 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-05 | 2025-05-15 | Unknown | Unknown | 2025-05-15 | 2025-06-06 | 23 | 17 | 2025-06-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-14 | 2023-07-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 894.89 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-14 | 2023-07-14 | 1 | 1 | 2023-07-14 | 2023-07-14 | 1 | 1 | 2023-07-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-04 | 2023-08-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3599 | 555.18 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-04 | 2023-08-07 | 4 | 2 | 2023-08-07 | 2023-08-07 | 1 | 1 | 2023-08-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 51.05 | 51.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-18 | 2025-03-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1804.2 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-18 | 2025-02-19 | Unknown | Unknown | 2025-02-19 | 2025-03-18 | 28 | 20 | 2025-03-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-18 | 2025-07-01 | 106 | 76 | Unknown | Unknown | Unknown | Unknown | 2025-07-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Agricultural | Underserved Community | ESCONDIDO | N/A | 75 | 75 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-17 | 2024-09-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 58490 | 3098.74 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-17 | 2024-09-24 | 8 | 6 | 2024-09-24 | 2025-01-29 | 128 | 92 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-29 | 2025-04-18 | 80 | 58 | Unknown | 2025-06-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | RAMONA | N/A | 67.05 | 67.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-25 | 2024-05-03 | 2024-07-12 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 473.53 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-25 | 2024-04-26 | 2 | 2 | 2024-04-26 | 2024-05-03 | 8 | 6 | 2024-05-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-03 | 2024-07-12 | 71 | 51 | Unknown | 2024-07-11 | Unknown | Unknown | 2024-07-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN MARCOS | COUNTY OF SAN DIEGO-NORTH of 56 | 264.2 | 264.2 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-20 | 2024-04-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 113480 | 23357.34 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-20 | 2024-03-20 | 1 | 1 | 2024-03-20 | 2024-10-17 | 212 | 152 | 2024-08-29 | 2024-10-15 | 15 | 11 | 2024-08-29 | 2024-10-25 | 58 | 42 | 2024-10-17 | Unknown | Unknown | Unknown | Unknown | 2025-08-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | OH | IOU Design | Residential | Underserved Community | VISTA | COUNTY OF SAN DIEGO-NORTH of 56 | 7941 | 7941 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-08-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-30 | 2024-08-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 8141.64 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-30 | 2024-06-18 | 294 | 210 | 2024-06-18 | 2025-01-03 | 200 | 144 | 2024-08-20 | 2024-08-21 | 2 | 2 | 2024-08-21 | 2024-08-28 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-07 | 2023-04-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1028.15 | Unknown | Unknown | Yes | N/A | N/A | 2023-04-07 | 2023-04-07 | 1 | 1 | 2023-04-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-23 | 2024-07-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1080.07 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-23 | 2024-07-23 | 1 | 1 | 2024-07-23 | 2024-07-23 | 1 | 1 | 2024-07-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-23 | Unknown | Unknown | Unknown | Unknown | 2024-09-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2026-03-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-06 | 2024-03-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 54899 | 81.53 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-06 | 2024-08-08 | 156 | 112 | 2024-08-08 | 2024-08-29 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | 2024-03-20 | 2024-07-16 | 52 | 38 | 2024-08-29 | Unknown | Unknown | Unknown | Unknown | 2025-08-21 | Unknown | Unknown | 2025-09-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | 5 | 5 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-11 | 2023-09-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 154.99 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-11 | 2023-09-28 | 18 | 14 | 2023-09-28 | 2023-09-28 | 1 | 1 | 2023-09-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community,Tribal Community | PAUMA VALLEY | N/A | 61 | 61 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-11 | 2024-06-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 914.77 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-11 | 2024-06-11 | 1 | 1 | 2024-06-11 | 2025-01-09 | 213 | 153 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-09 | 2025-04-18 | 100 | 72 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Residential | N/A | San Diego | San Diego | 150 | 150 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-13 | 2025-02-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 76869 | 71061.24 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-13 | 2024-08-01 | Unknown | Unknown | 2024-08-01 | 2025-06-03 | 307 | 219 | 2025-03-07 | 2025-05-21 | 10 | 6 | 2025-04-04 | 2025-06-05 | 13 | 7 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | Both | Applicant Design | Commercial | Underserved Community | San Diego | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-02 | 2024-01-10 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 11136.28 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-02 | 2024-03-19 | 170 | 122 | 2024-03-19 | 2024-10-17 | 213 | 153 | 2024-04-03 | 2025-05-16 | 395 | 283 | 2024-09-26 | 2025-05-28 | 40 | 30 | 2024-10-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-18 | 2024-07-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1554.02 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-18 | 2024-07-09 | 22 | 16 | 2024-07-09 | 2024-07-09 | 1 | 1 | 2024-07-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-07-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-14 | 2025-05-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 5018.3 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-14 | 2025-04-28 | Unknown | Unknown | 2025-04-28 | 2025-06-04 | 38 | 28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-08 | 2023-02-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2875.23 | 660.89 | Unknown | Unknown | Yes | N/A | N/A | 2023-02-08 | 2024-07-23 | 532 | 380 | 2024-07-23 | 2025-02-13 | 206 | 148 | Unknown | Unknown | Unknown | Unknown | 2024-08-20 | 2024-09-20 | 32 | 24 | 2025-02-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 12 | 12 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-18 | 2024-11-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1369.5 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-18 | 2025-01-21 | 65 | 47 | 2025-01-21 | 2025-01-23 | 3 | 3 | 2025-01-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | OCEANSIDE | 1 | 1 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-13 | 2025-05-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2875.23 | 2175.53 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-13 | 2025-04-29 | Unknown | Unknown | 2025-04-29 | 2025-05-28 | 30 | 22 | 2025-05-28 | 2025-07-01 | 18 | 14 | 2025-05-22 | 2025-07-11 | 45 | 33 | 2025-06-06 | 2025-09-03 | 90 | 64 | Unknown | 2025-08-27 | Unknown | Unknown | 2025-09-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN MARCOS | SAN MARCOS | 73.05 | 73.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-07 | 2025-01-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2533.15 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-07 | 2024-12-05 | Unknown | Unknown | 2024-12-05 | 2025-06-24 | 202 | 144 | 2025-01-17 | 2025-05-14 | 118 | 84 | 2025-01-07 | 2025-05-21 | 19 | 15 | 2025-06-24 | 2025-08-20 | 58 | 42 | Unknown | 2025-08-18 | Unknown | Unknown | 2025-08-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-31 | 2024-02-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1640.28 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-31 | 2023-12-07 | Unknown | Unknown | 2023-12-07 | 2024-02-23 | 79 | 57 | 2024-02-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-28 | 2025-02-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1594.63 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-28 | 2025-01-29 | 2 | 2 | 2025-01-29 | 2025-03-04 | 35 | 25 | Unknown | Unknown | Unknown | Unknown | 2025-02-12 | 2025-03-04 | 21 | 15 | 2025-03-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | Disadvantaged Community,Underserved Community | Chula Vista | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-10 | 2023-03-10 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 217016 | 51902.3 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-10 | 2023-06-30 | 113 | 81 | 2023-06-30 | 2024-07-16 | 383 | 273 | 2023-08-07 | 2024-06-18 | 11 | 9 | 2024-06-20 | 2024-07-30 | 41 | 29 | 2024-11-07 | Unknown | Unknown | Unknown | 2024-11-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-15 | 2024-10-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1709.22 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-15 | 2024-04-15 | 1 | 1 | 2024-04-15 | 2024-04-15 | 1 | 1 | 2024-04-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | POWAY | N/A | 69.05 | 69.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-06 | 2023-04-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 676.16 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-06 | 2023-04-04 | 30 | 22 | 2023-04-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | CORONADO | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-14 | Unknown | Unknown | No | 2024-05-23 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-23 | 2024-05-23 | 2024-12-06 | IOU Designed & Installed | N/A | Yes | 228 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1658.91 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-23 | 2025-01-06 | 229 | 163 | 2025-01-06 | 2024-06-21 | Unknown | Unknown | 2024-06-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-21 | 2024-12-06 | 169 | 121 | Unknown | Unknown | Unknown | Unknown | 2024-12-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-06 | 2024-12-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 3781.12 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-06 | 2024-12-03 | Unknown | Unknown | 2024-12-03 | 2024-12-20 | 18 | 14 | 2024-12-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 26.05 | 26.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-11 | 2024-12-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1644.02 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-11 | 2025-01-07 | 28 | 20 | 2025-01-07 | 2025-01-10 | 4 | 4 | 2025-01-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | CARDIFF | ENCINITAS | 76.1 | 76.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-12 | 2024-07-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1559.36 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-12 | 2024-06-21 | 10 | 8 | 2024-06-21 | 2024-07-03 | 13 | 9 | 2024-07-03 | Unknown | Unknown | Unknown | 2024-07-03 | 2024-08-07 | 36 | 26 | 2024-07-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-07 | 2025-05-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 344.44 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-07 | 2025-05-06 | Unknown | Unknown | 2025-05-06 | 2025-07-01 | 57 | 41 | Unknown | Unknown | Unknown | Unknown | 2025-05-08 | 2025-06-04 | 28 | 20 | 2025-07-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-08-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-19 | 2024-01-31 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2313.43 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-19 | 2023-12-05 | Unknown | Unknown | 2023-12-05 | 2024-01-31 | 58 | 42 | 2024-01-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-16 | 2025-06-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2191.28 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-16 | 2025-05-20 | 5 | 3 | 2025-05-20 | 2025-06-23 | 35 | 25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 73 | 73 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-11 | 2025-04-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1609.48 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-11 | 2025-03-03 | Unknown | Unknown | 2025-03-03 | 2025-04-18 | 47 | 35 | 2025-04-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-08 | 2023-08-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1535.6 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-08 | 2023-09-08 | 32 | 24 | 2023-09-08 | 2023-09-11 | 4 | 2 | 2023-09-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 64 | 64 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-08 | 2024-10-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1142.97 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-08 | 2024-10-24 | 17 | 13 | 2024-10-24 | 2024-11-14 | 22 | 16 | 2024-11-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-14 | 2025-07-01 | 230 | 164 | Unknown | 2025-07-08 | Unknown | Unknown | 2025-07-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-08 | 2024-08-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 28804 | 494.79 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-08 | 2024-08-22 | 15 | 11 | 2024-08-22 | 2024-08-22 | 1 | 1 | 2024-08-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | Underserved Community | San Marcos | SAN MARCOS | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-07 | 2022-12-07 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 214489.55 | 76137.4 | Unknown | Unknown | Yes | N/A | N/A | 2022-12-07 | 2024-06-12 | 554 | 396 | 2024-06-12 | 2024-12-30 | 202 | 144 | 2024-06-28 | 2025-02-19 | 85 | 61 | 2024-07-02 | 2025-01-24 | 43 | 32 | 2025-02-04 | Unknown | Unknown | Unknown | 2025-02-04 | 2025-08-01 | 179 | 129 | 2025-08-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-06-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-27 | 2025-06-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1555.33 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-27 | 2025-06-23 | Unknown | Unknown | 2025-06-23 | 2025-06-27 | 5 | 5 | 2025-06-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-27 | 2025-07-02 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2025-07-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 76.05 | 76.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-27 | 2025-03-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1894.03 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-27 | 2025-03-17 | 19 | 13 | 2025-03-17 | 2025-03-17 | 1 | 1 | 2025-03-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-17 | 2025-08-07 | 144 | 104 | Unknown | Unknown | Unknown | Unknown | 2025-08-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 10 | 10 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-06 | 2023-11-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 158.79 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-06 | 2023-06-21 | Unknown | Unknown | 2023-06-21 | 2023-12-08 | 171 | 123 | 2023-12-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | Both | IOU Design | Residential | N/A | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-18 | 2023-12-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 295462.8 | 75813.18 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-18 | 2023-12-04 | 48 | 34 | 2023-12-04 | 2024-12-03 | 366 | 262 | 2024-08-20 | 2024-08-30 | 11 | 9 | 2024-09-25 | 2024-12-13 | 43 | 31 | 2024-12-03 | Unknown | Unknown | Unknown | 2025-04-23 | 2025-06-26 | 65 | 47 | 2025-07-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | 21 | 21 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-23 | 2024-04-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 944.34 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-23 | 2024-02-15 | Unknown | Unknown | 2024-02-15 | 2024-04-30 | 76 | 54 | 2024-04-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | N/A | ENCINITAS | ENCINITAS | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-11 | 2024-01-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1141.18 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-11 | 2024-01-11 | 1 | 1 | 2024-01-11 | 2024-03-26 | 76 | 54 | Unknown | Unknown | Unknown | Unknown | 2024-01-31 | 2024-03-11 | 41 | 29 | 2024-03-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 71 | 71 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-02 | 2024-12-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2893.67 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-02 | 2025-01-22 | 52 | 38 | 2025-01-22 | 2025-01-31 | 10 | 8 | 2025-01-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-14 | 2025-02-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 9748.6 | 657.06 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-14 | 2025-02-20 | 7 | 5 | 2025-02-20 | 2025-05-08 | 78 | 56 | Unknown | Unknown | Unknown | Unknown | 2025-02-19 | 2025-03-06 | 16 | 12 | 2025-05-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 20 | 20 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-31 | 2025-05-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 863.98 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-31 | 2025-05-09 | 40 | 30 | 2025-05-09 | 2025-05-09 | 1 | 1 | 2025-05-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 419.05 | 419.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-06 | 2024-06-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1118.41 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-06 | 2024-10-29 | 146 | 104 | 2024-10-29 | 2024-11-01 | 4 | 4 | 2024-11-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | Both | IOU Design | Residential | Underserved Community | FALLBROOK | COUNTY OF SAN DIEGO-NORTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-11 | 2024-11-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7095 | 4284.21 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-11 | 2024-11-11 | 32 | 22 | 2024-11-11 | 2025-03-19 | 129 | 93 | Unknown | Unknown | Unknown | Unknown | 2025-01-07 | 2025-06-10 | 27 | 19 | 2025-03-19 | 2025-07-01 | 105 | 75 | Unknown | 2025-06-26 | Unknown | Unknown | 2025-07-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | La Mesa | N/A | 131.05 | 131.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-12 | 2025-03-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 46683.98 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-12 | 2025-02-13 | 2 | 2 | 2025-02-13 | 2025-06-25 | 133 | 95 | Unknown | Unknown | Unknown | Unknown | 2025-07-02 | 2025-07-07 | 6 | 4 | 2025-06-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN MARCOS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-15 | 2024-02-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 250149 | 25733.11 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-15 | 2023-09-19 | 36 | 26 | 2023-09-19 | 2024-12-31 | 470 | 336 | 2024-04-25 | 2024-10-01 | 86 | 62 | 2024-12-17 | 2025-01-03 | 18 | 14 | 2024-12-31 | Unknown | Unknown | Unknown | 2025-01-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | LAS FLORES | N/A | 23 | 23 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-30 | 2025-04-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1098.24 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-30 | 2025-04-30 | 1 | 1 | 2025-04-30 | 2025-05-22 | 23 | 17 | 2025-05-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-23 | 2024-09-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 27449 | 507.87 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-23 | 2024-10-15 | 23 | 17 | 2024-10-15 | 2024-10-15 | 1 | 1 | 2024-10-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-15 | Unknown | Unknown | Unknown | Unknown | 2025-07-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-15 | 2023-06-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 288418 | 24262.98 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-15 | 2023-06-20 | 6 | 4 | 2023-06-20 | 2023-07-20 | 31 | 23 | Unknown | Unknown | Unknown | Unknown | 2023-07-06 | 2023-07-12 | 7 | 5 | 2023-07-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 27.7 | 27.7 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-16 | Unknown | Unknown | No | 2024-03-18 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-18 | 2024-03-18 | Unknown | IOU Designed & Installed | N/A | Yes | 483 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3941 | 1400.58 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-18 | 2025-07-14 | 484 | 346 | 2025-07-14 | 2024-06-20 | Unknown | Unknown | 2024-06-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-20 | 2025-08-04 | 411 | 293 | Unknown | Unknown | Unknown | Unknown | 2025-08-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | 132.05 | 132.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-06 | 2024-11-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1236.27 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-06 | 2024-11-20 | 351 | 251 | 2024-11-20 | 2024-11-20 | 1 | 1 | 2024-11-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LEMON GROVE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-26 | 2024-06-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1446.04 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-26 | 2024-06-26 | 1 | 1 | 2024-06-26 | 2024-06-26 | 1 | 1 | 2024-06-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2020-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-23 | 2025-04-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2213.54 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-23 | 2025-04-28 | 6 | 4 | 2025-04-28 | 2025-06-03 | 37 | 27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-03 | Unknown | Unknown | Unknown | Unknown | 2025-07-09 | Unknown | Unknown | 2025-07-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | BONITA | N/A | 149.1 | 149.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-05-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-08 | 2025-01-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2837.38 | Unknown | Unknown | Yes | N/A | N/A | 2022-11-08 | 2024-01-24 | 443 | 317 | 2024-01-24 | 2025-04-29 | 462 | 330 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | IOU Design | Commercial | Underserved Community | LA MESA | LA MESA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-02 | 2024-04-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 30175.67 | 64196.55 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-02 | 2024-01-25 | 85 | 61 | 2024-01-25 | 2025-05-23 | 485 | 347 | 2025-03-04 | 2025-07-31 | 89 | 65 | 2024-04-05 | 2025-07-03 | 118 | 84 | 2025-05-23 | Unknown | Unknown | Unknown | 2025-08-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-20 | 2024-05-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7681 | 584.27 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-20 | 2024-05-02 | Unknown | Unknown | 2024-05-02 | 2024-05-20 | 19 | 13 | 2024-05-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 47.05 | 47.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-10 | Unknown | Unknown | No | 2024-10-17 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-17 | 2024-10-17 | Unknown | IOU Designed & Installed | N/A | Yes | 113 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 752.44 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-17 | 2025-02-05 | 112 | 80 | 2025-02-05 | 2025-04-18 | 73 | 53 | Unknown | Unknown | Unknown | Unknown | 2025-07-11 | 2025-07-11 | 1 | 1 | 2025-04-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | POWAY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-23 | 2024-09-23 | 2024-10-20 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3158.2 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-23 | 2024-09-19 | Unknown | Unknown | 2024-09-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-31 | 2025-02-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 18178 | 1771.55 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-31 | 2025-01-30 | Unknown | Unknown | 2025-01-30 | 2025-03-04 | 34 | 24 | Unknown | Unknown | Unknown | Unknown | 2025-02-01 | 2025-02-24 | 24 | 16 | 2025-03-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 13.05 | 13.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-17 | 2024-04-17 | 2024-10-23 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3941 | 944.52 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-17 | 2024-04-04 | Unknown | Unknown | 2024-04-04 | 2024-04-17 | 14 | 10 | 2024-04-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-17 | 2024-10-23 | 190 | 136 | Unknown | Unknown | Unknown | Unknown | 2024-10-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 331.2 | 331.2 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-14 | 2024-11-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 15924 | 1797.89 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-14 | 2024-11-12 | 30 | 22 | 2024-11-12 | 2025-04-03 | 143 | 103 | Unknown | Unknown | Unknown | Unknown | 2025-01-23 | 2025-02-13 | 22 | 16 | 2025-04-03 | 2025-04-18 | 16 | 12 | Unknown | 2025-05-07 | Unknown | Unknown | 2025-07-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 44.05 | 44.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-28 | 2024-12-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1279.69 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-28 | 2024-12-10 | 44 | 32 | 2024-12-10 | 2024-12-17 | 8 | 6 | 2024-12-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-17 | 2025-08-18 | 245 | 175 | Unknown | Unknown | Unknown | Unknown | 2025-08-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | Escondido | N/A | 246.2 | 246.2 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-12 | 2023-12-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 29905.55 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-12 | 2023-12-01 | Unknown | Unknown | 2023-12-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-11 | 2024-09-12 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-18 | 2023-04-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 451.25 | Unknown | Unknown | Yes | N/A | N/A | 2023-04-18 | 2023-06-26 | 70 | 50 | 2023-06-26 | 2023-07-27 | 32 | 24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 697 | 697 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-18 | 2024-11-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 23886 | 2060.1 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-18 | 2025-03-13 | 116 | 84 | 2025-03-13 | 2025-04-04 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | 2025-03-26 | 2025-04-08 | 14 | 10 | 2025-04-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-13 | 2024-06-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 609.36 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-13 | 2024-09-27 | 107 | 77 | 2024-09-27 | 2024-10-17 | 21 | 15 | 2024-10-02 | 2024-10-29 | 28 | 20 | 2024-10-01 | 2024-11-08 | 13 | 11 | 2024-10-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 78 | 78 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-29 | 2025-01-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 808.5 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-29 | 2025-02-10 | 13 | 9 | 2025-02-10 | 2025-05-21 | 101 | 73 | 2025-05-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-21 | 2025-07-31 | 72 | 52 | Unknown | 2025-06-23 | Unknown | Unknown | 2025-07-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 18.1 | 18.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-06 | 2024-03-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7962 | 1848.1 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-06 | 2024-03-06 | 1 | 1 | 2024-03-06 | 2025-07-17 | 499 | 357 | Unknown | Unknown | Unknown | Unknown | 2024-03-06 | 2024-03-29 | 24 | 18 | 2025-07-17 | 2025-07-11 | Unknown | Unknown | Unknown | 2025-08-15 | Unknown | Unknown | 2025-09-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | POWAY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-21 | 2025-02-21 | 2025-02-21 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 436.72 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-21 | 2025-02-18 | Unknown | Unknown | 2025-02-18 | 2025-02-21 | 4 | 4 | 2025-02-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-21 | 2025-02-21 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2025-02-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 12 | 12 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-25 | 2023-11-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 153.49 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-25 | 2024-01-16 | 53 | 37 | 2024-01-16 | 2024-01-19 | 4 | 4 | 2024-01-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-16 | 2024-03-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 97844.46 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-16 | 2024-03-12 | 57 | 41 | 2024-03-12 | 2025-03-05 | 359 | 257 | 2024-07-09 | 2024-10-03 | 87 | 63 | 2025-01-24 | 2025-04-10 | -10 | -12 | 2025-03-05 | Unknown | Unknown | Unknown | 2025-04-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | CHULA VISTA | CHULA VISTA | 8 | 8 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-27 | 2024-09-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 523.55 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-27 | 2024-07-25 | Unknown | Unknown | 2024-07-25 | 2024-11-08 | 107 | 77 | 2024-11-08 | Unknown | Unknown | Unknown | 2024-10-22 | 2024-11-05 | 15 | 11 | 2024-11-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 27.05 | 27.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-12 | 2025-06-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1356.45 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-12 | 2025-06-18 | 7 | 5 | 2025-06-18 | 2025-06-18 | 1 | 1 | 2025-06-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-28 | 2024-05-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 1378.58 | 1037.41 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-28 | 2024-05-01 | Unknown | Unknown | 2024-05-01 | 2024-05-30 | 30 | 22 | 2024-05-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-30 | 2025-08-11 | 439 | 313 | Unknown | 2025-07-21 | Unknown | Unknown | 2025-08-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-23 | 2024-07-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 93350 | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2024-07-23 | 2024-07-24 | 2 | 2 | 2024-07-24 | 2024-08-20 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R29/R45) | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | CALTRANS-NORTH of 56, OCEANSIDE | 3104 | 3104 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-10-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-17 | 2024-02-26 | 2025-04-17 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 745939 | 297683.91 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-17 | 2024-02-26 | 194 | 138 | 2024-02-26 | 2025-02-05 | 346 | 248 | 2024-06-07 | 2025-03-18 | 120 | 84 | 2024-03-19 | 2025-07-02 | 154 | 94 | 2025-02-05 | 2025-04-18 | 73 | 53 | 2025-05-21 | 2025-07-01 | 42 | 30 | 2025-04-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | OCEANSIDE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-29 | 2024-07-29 | 2024-08-15 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1636.81 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-29 | 2024-07-29 | 1 | 1 | 2024-07-29 | 2024-07-29 | 1 | 1 | 2024-07-29 | Unknown | Unknown | Unknown | 2024-07-29 | 2024-08-12 | 15 | 11 | 2024-07-29 | 2024-08-15 | 18 | 14 | Unknown | Unknown | Unknown | Unknown | 2024-08-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | ESCONDIDO | 64 | 64 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-27 | 2025-02-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 16630.79 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-27 | 2025-02-20 | Unknown | Unknown | 2025-02-20 | 2025-08-22 | 184 | 132 | 2025-07-23 | 2025-08-20 | 23 | 15 | 2025-04-18 | 2025-06-27 | 24 | 18 | 2025-08-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SANTEE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-31 | 2025-01-31 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 140140 | 6493.18 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-31 | 2025-03-07 | 36 | 26 | 2025-03-07 | 2025-03-12 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | Both | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-29 | 2023-03-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 396.99 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-29 | 2023-03-29 | 1 | 1 | 2023-03-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2017-11-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-23 | 2023-07-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 46962 | 555.26 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-23 | 2023-07-10 | Unknown | Unknown | 2023-07-10 | 2023-07-21 | 12 | 10 | 2023-07-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 66 | 66 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-26 | 2025-03-26 | 2025-04-25 | IOU Designed & Installed | N/A | No | Unknown | 47.15 | -0.94 | Unknown | Unknown | 0.5 | 47.59 | 3981 | 1149.06 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-26 | 2025-03-26 | 1 | 1 | 2025-03-26 | 2025-03-26 | 1 | 1 | 2025-03-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-26 | 2025-04-25 | 31 | 23 | Unknown | Unknown | Unknown | Unknown | 2025-04-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 296 | 296 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-07 | 2025-05-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 982.58 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-07 | 2025-05-06 | Unknown | Unknown | 2025-05-06 | 2025-05-14 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | 2025-05-09 | 2025-05-23 | 15 | 11 | 2025-05-14 | 2025-07-18 | 66 | 48 | Unknown | 2025-07-21 | Unknown | Unknown | 2025-07-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-18 | 2024-12-18 | 2024-12-18 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1702.59 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-18 | 2024-12-17 | Unknown | Unknown | 2024-12-17 | 2024-12-18 | 2 | 2 | 2024-12-18 | Unknown | Unknown | Unknown | 2024-12-18 | 2025-01-21 | 35 | 25 | 2024-12-18 | 2024-12-18 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-12-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LEMON GROVE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-01 | 2025-04-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1636.25 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-01 | 2025-04-01 | 1 | 1 | 2025-04-01 | 2025-04-01 | 1 | 1 | 2025-04-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | POWAY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-02 | 2025-06-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1361.4 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-02 | 2025-06-06 | 5 | 5 | 2025-06-06 | 2025-06-09 | 4 | 2 | 2025-06-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-09 | 2025-07-25 | 47 | 35 | Unknown | Unknown | Unknown | Unknown | 2025-07-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | CHULA VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-12 | 2025-02-12 | 2025-06-26 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1633.57 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-12 | 2025-02-12 | 1 | 1 | 2025-02-12 | 2025-02-12 | 1 | 1 | 2025-02-12 | Unknown | Unknown | Unknown | 2025-02-13 | 2025-03-05 | 21 | 15 | 2025-02-12 | 2025-06-26 | 135 | 97 | Unknown | Unknown | Unknown | Unknown | 2025-06-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | ESCONDIDO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-27 | 2024-02-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1108.74 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-27 | 2024-02-14 | Unknown | Unknown | 2024-02-14 | 2025-03-06 | 387 | 277 | 2025-03-06 | Unknown | Unknown | Unknown | 2024-02-27 | 2024-03-07 | 10 | 8 | 2024-02-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | PAUMA VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-03 | 2024-12-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 9851 | 4587.37 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-03 | 2024-09-21 | 19 | 14 | 2024-09-21 | 2025-01-28 | 130 | 92 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-28 | Unknown | Unknown | Unknown | Unknown | 2025-05-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 140.05 | 140.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-01 | 2023-03-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 216 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-01 | 2023-03-07 | 7 | 5 | 2023-03-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | DANA POINT | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-04 | 2024-06-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2875.23 | 780.27 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-04 | 2024-06-05 | 2 | 2 | 2024-06-05 | 2025-03-27 | 296 | 212 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN MARCOS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-11 | Unknown | Unknown | No | 2023-02-28 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-28 | 2023-02-28 | Unknown | IOU Designed & Installed | N/A | Yes | 372 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1424.12 | Unknown | Unknown | Yes | N/A | N/A | 2023-02-28 | 2024-03-06 | 373 | 267 | 2024-03-06 | 2023-06-21 | Unknown | Unknown | 2023-06-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-21 | 2025-09-04 | 807 | 577 | Unknown | 2025-06-11 | Unknown | Unknown | 2025-09-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | 40 | 40 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-15 | 2023-02-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1413.25 | Unknown | Unknown | Yes | N/A | N/A | 2023-02-15 | 2023-02-15 | 1 | 1 | 2023-02-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-11 | 2025-02-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1599.46 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-11 | 2025-02-13 | 3 | 3 | 2025-02-13 | 2025-02-13 | 1 | 1 | 2025-02-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | JAMUL | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-04 | 2024-03-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3241 | 640.24 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-04 | 2024-03-08 | 5 | 5 | 2024-03-08 | 2024-03-08 | 1 | 1 | 2024-03-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-15 | 2023-12-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 26990 | 257.93 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-15 | 2023-12-04 | 20 | 14 | 2023-12-04 | 2023-12-07 | 4 | 4 | 2023-12-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-10 | 2025-03-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 3284.32 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-10 | 2025-02-25 | Unknown | Unknown | 2025-02-25 | 2025-03-14 | 18 | 14 | 2025-03-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Commercial | Underserved Community | CAMPO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-03 | 2023-11-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 24309.59 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-03 | 2023-11-03 | 1 | 1 | 2023-11-03 | 2025-01-07 | 432 | 308 | Unknown | Unknown | Unknown | Unknown | 2024-12-02 | 2025-08-07 | 249 | 179 | 2025-01-14 | Unknown | Unknown | Unknown | 2025-01-14 | 2025-08-29 | 228 | 164 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R29/R45 | UG | IOU Design | Commercial | Underserved Community | VISTA | VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-15 | 2025-01-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 280351.54 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-15 | 2025-02-18 | 35 | 25 | 2025-02-18 | 2025-06-12 | 115 | 83 | 2025-03-26 | 2025-06-02 | 9 | 7 | 2025-02-25 | 2025-08-07 | 104 | 74 | 2025-06-12 | 2025-07-22 | 41 | 29 | 2025-06-18 | 2025-08-27 | 71 | 51 | 2025-07-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN MARCOS | N/A | 39.05 | 39.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-07 | 2023-06-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 934.54 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-07 | 2023-06-13 | 7 | 5 | 2023-06-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-10 | 2023-11-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1755.78 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-10 | 2023-11-10 | 1 | 1 | 2023-11-10 | 2023-11-10 | 1 | 1 | 2023-11-10 | 2024-11-26 | 383 | 273 | Unknown | Unknown | Unknown | Unknown | 2024-11-26 | 2025-08-07 | 255 | 183 | Unknown | 2025-04-04 | Unknown | Unknown | 2025-08-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 132.05 | 132.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-25 | 2024-03-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 748.42 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-25 | 2024-03-29 | 65 | 47 | 2024-03-29 | 2024-03-29 | 1 | 1 | 2024-03-29 | 2024-04-16 | 19 | 13 | Unknown | Unknown | Unknown | Unknown | 2024-03-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 65 | 65 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-02 | 2024-04-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3961 | 1507.82 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-02 | 2024-04-09 | 8 | 6 | 2024-04-09 | 2024-06-26 | 79 | 57 | 2024-06-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-10 | 2023-09-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 848.59 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-10 | 2023-09-10 | 1 | 0 | 2023-09-10 | 2023-09-10 | 1 | 0 | 2023-09-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | LEMON GROVE | LEMON GROVE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-29 | 2024-05-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 31807 | 5208.75 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-29 | 2024-05-29 | 1 | 1 | 2024-05-29 | 2024-06-12 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2024-05-29 | 2024-06-24 | 27 | 19 | 2024-06-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-13 | 2025-05-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 817.04 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-13 | 2025-04-22 | Unknown | Unknown | 2025-04-22 | 2025-05-30 | 39 | 29 | 2025-05-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-30 | 2025-07-08 | 40 | 28 | Unknown | 2025-06-30 | Unknown | Unknown | 2025-07-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | EL CAJON | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-21 | 2025-03-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1751.97 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-21 | 2025-03-17 | Unknown | Unknown | 2025-03-17 | 2025-05-23 | 68 | 50 | Unknown | Unknown | Unknown | Unknown | 2025-03-21 | 2025-05-21 | 62 | 44 | 2025-05-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-15 | 2023-06-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 861682 | 61527.09 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-15 | 2023-06-20 | 6 | 4 | 2023-06-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-06 | 2023-07-12 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | N/A | 191 | 191 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-15 | 2024-02-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 297.38 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-15 | 2024-02-06 | Unknown | Unknown | 2024-02-06 | 2024-02-20 | 15 | 11 | 2024-02-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | Oceanside | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-06 | 2024-12-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2024-12-06 | 2024-08-28 | Unknown | Unknown | 2024-08-28 | 2025-06-23 | 300 | 214 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-24 | 2024-06-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3627.56 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-24 | 2024-06-24 | 1 | 1 | 2024-06-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-15 | 2024-05-15 | 2024-12-26 | IOU Designed & Installed | N/A | No | Unknown | 2379.22 | 0 | Unknown | Unknown | 100.69 | 2278.53 | 3981 | 4084.54 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-15 | 2024-08-07 | 85 | 61 | 2024-08-07 | 2024-09-20 | 45 | 33 | 2024-09-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-20 | 2024-12-26 | 98 | 70 | Unknown | 2024-12-23 | Unknown | Unknown | 2024-12-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-02 | 2024-07-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 274.81 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-02 | 2024-07-25 | 24 | 18 | 2024-07-25 | 2024-07-25 | 1 | 1 | 2024-07-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | POWAY | N/A | 9.05 | 9.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | 2025-05-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1119 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-07 | 2025-04-29 | 23 | 17 | 2025-04-29 | 2025-05-06 | 8 | 6 | 2025-05-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CAPISTRANO BEACH | N/A | 7 | 7 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-07 | 2025-05-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1177.12 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-07 | 2025-05-20 | 14 | 10 | 2025-05-20 | 2025-05-30 | 11 | 9 | 2025-05-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN MARCOS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-18 | 2024-11-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2105.46 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-18 | 2024-11-07 | 51 | 37 | 2024-11-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 125.05 | 125.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-26 | 2024-04-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1029.82 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-26 | 2024-04-04 | 39 | 29 | 2024-04-04 | 2024-04-04 | 1 | 1 | 2024-04-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2018-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-30 | 2023-11-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1828.75 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-30 | 2023-11-01 | 3 | 3 | 2023-11-01 | 2023-11-06 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SANTEE | N/A | 25 | 25 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-24 | 2025-03-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1313.18 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-24 | 2025-03-31 | 8 | 6 | 2025-03-31 | 2025-04-10 | 11 | 9 | 2025-04-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-08 | 2025-05-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1023.89 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-08 | 2025-04-24 | Unknown | Unknown | 2025-04-24 | 2025-05-08 | 15 | 11 | 2025-05-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-08 | 2025-08-05 | 90 | 64 | Unknown | Unknown | Unknown | Unknown | 2025-08-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 52.05 | 52.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-20 | 2023-11-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1273.83 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-20 | 2023-10-20 | Unknown | Unknown | 2023-10-20 | 2023-12-04 | 46 | 32 | 2023-12-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-27 | 2024-04-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2001.1 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-27 | 2023-10-18 | 22 | 16 | 2023-10-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | IMPERIAL BEACH | 132.05 | 132.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-04 | 2023-05-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7962 | 716.64 | Unknown | Unknown | Yes | N/A | N/A | 2023-04-04 | 2023-04-03 | Unknown | Unknown | 2023-04-03 | Unknown | Unknown | Unknown | 2023-04-12 | 2025-03-03 | 124 | 88 | 2023-04-04 | 2024-11-14 | 439 | 315 | 2023-06-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | JULIAN | N/A | 102 | 102 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-23 | 2024-12-18 | 2025-06-17 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1195.76 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-23 | 2024-12-18 | 87 | 63 | 2024-12-18 | 2024-12-18 | 1 | 1 | 2024-12-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-20 | 2025-06-17 | 180 | 128 | Unknown | Unknown | Unknown | Unknown | 2025-06-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 62 | 62 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-18 | 2024-07-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3941 | 902.49 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-18 | 2024-09-30 | 75 | 53 | 2024-09-30 | 2024-11-04 | 36 | 26 | 2024-11-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-25 | 2023-10-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2207.74 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-25 | 2023-12-18 | 55 | 39 | 2023-12-18 | 2023-12-19 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 13.4 | 13.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-15 | 2024-11-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1725.19 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-15 | 2024-11-17 | 34 | 24 | 2024-11-17 | 2024-11-27 | 11 | 8 | 2024-11-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-06 | 2024-09-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 23991 | 677.91 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-06 | 2024-09-06 | 1 | 1 | 2024-09-06 | 2024-09-06 | 1 | 1 | 2024-09-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-07 | Unknown | Unknown | No | 2023-04-10 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-10 | 2023-04-10 | Unknown | IOU Designed & Installed | N/A | Yes | 490 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 232685 | 28863.26 | Unknown | Unknown | Yes | N/A | N/A | 2023-04-10 | 2024-07-16 | 464 | 332 | 2024-07-16 | 2023-06-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | LAGUNA HILLS | N/A | 3747 | 3747 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-10-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-20 | 2023-12-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 158.79 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-20 | 2023-12-29 | 10 | 8 | 2023-12-29 | 2024-01-03 | 6 | 4 | 2024-01-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 5.4 | 5.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-26 | 2024-12-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2029 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-26 | 2024-12-26 | 1 | 1 | 2024-12-26 | 2024-12-26 | 1 | 1 | 2024-12-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 43.1 | 43.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-01 | 2024-10-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1203 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-01 | 2025-01-21 | 113 | 81 | 2025-01-21 | 2025-01-21 | 1 | 1 | 2025-01-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 19.5 | 19.5 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-17 | 2024-10-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1142.97 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-17 | 2024-09-19 | Unknown | Unknown | 2024-09-19 | 2024-11-08 | 51 | 37 | 2024-11-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-08 | Unknown | Unknown | Unknown | Unknown | 2025-09-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-01 | 2024-08-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 23991 | 494.79 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-01 | 2024-08-12 | 12 | 8 | 2024-08-12 | 2024-08-12 | 1 | 1 | 2024-08-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | IOU Design | Residential | Underserved Community | FB 1028-D1 (E) | COUNTY OF SAN DIEGO-NORTH of 56 | 140.75 | 140.75 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-03 | 2024-09-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 1212.34 | 53876.85 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-03 | 2024-09-19 | 17 | 13 | 2024-09-19 | 2025-05-05 | 229 | 163 | 2024-11-14 | 2025-04-11 | 10 | 6 | 2024-11-18 | 2025-07-28 | 42 | 30 | 2025-05-05 | Unknown | Unknown | Unknown | 2025-06-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | 101 | 101 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-06 | 2024-04-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1162.07 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-06 | 2024-04-06 | 1 | 0 | 2024-04-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 56.05 | 56.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-03 | 2025-03-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1797.78 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-03 | 2025-03-04 | 2 | 2 | 2025-03-04 | 2025-03-04 | 1 | 1 | 2025-03-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-02 | 2025-05-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1145.66 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-02 | 2025-04-30 | Unknown | Unknown | 2025-04-30 | 2025-05-13 | 14 | 10 | 2025-05-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-13 | 2025-07-02 | 51 | 37 | Unknown | Unknown | Unknown | Unknown | 2025-07-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | 574 | 574 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-31 | 2024-05-31 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 7510.58 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-31 | 2024-07-22 | 53 | 37 | 2024-07-22 | 2024-08-06 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-25 | 2024-11-25 | 2024-12-03 | IOU Designed & Installed | N/A | No | Unknown | 24.54 | 0 | Unknown | Unknown | Unknown | 24.54 | 0 | 282.62 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-25 | 2024-11-08 | Unknown | Unknown | 2024-11-08 | 2024-11-25 | 18 | 12 | 2024-11-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-25 | 2024-12-03 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | 2024-12-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-06 | 2025-06-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1178.71 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-06 | 2025-06-12 | 99 | 71 | 2025-06-12 | 2025-06-23 | 12 | 8 | 2025-06-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | DANA POINT | N/A | 103 | 103 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-04 | 2023-10-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 158.51 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-04 | 2023-09-25 | Unknown | Unknown | 2023-09-25 | 2023-10-13 | 19 | 15 | 2023-10-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | COUNTY OF SAN DIEGO-NORTH of 56, SAN DIEGO | 2549 | 2549 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-06-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-22 | 2025-02-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 163085.93 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-22 | 2025-01-22 | 1 | 1 | 2025-01-22 | 2025-04-04 | 73 | 53 | 2025-02-18 | 2025-04-04 | 17 | 12 | 2025-03-11 | 2025-05-08 | 16 | 8 | 2025-04-04 | 2025-07-21 | 109 | 77 | 2025-04-17 | 2025-07-24 | 99 | 71 | 2025-07-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | 13 | 13 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-07 | 2025-03-07 | 2025-03-10 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1793.54 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-07 | 2025-02-25 | Unknown | Unknown | 2025-02-25 | 2025-03-07 | 11 | 9 | 2025-03-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-07 | 2025-03-10 | 4 | 2 | Unknown | Unknown | Unknown | Unknown | 2025-03-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2024-06-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-01 | 2023-12-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 10080.01 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-01 | 2023-11-30 | Unknown | Unknown | 2023-11-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 71.4 | 71.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-29 | 2024-12-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1790.06 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-29 | 2024-12-09 | 42 | 30 | 2024-12-09 | 2024-12-20 | 12 | 10 | 2024-12-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-07 | 2024-10-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 903.37 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-07 | 2024-12-03 | 58 | 42 | 2024-12-03 | 2025-02-12 | 72 | 52 | 2025-02-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-12 | 2025-08-04 | 174 | 124 | Unknown | 2025-07-28 | Unknown | Unknown | 2025-08-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN MARCOS | N/A | 25 | 25 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-14 | 2024-12-31 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3661 | 2267.83 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-14 | 2024-12-17 | 34 | 24 | 2024-12-17 | 2025-01-10 | 25 | 19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | LAGUNA NIGUEL | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-26 | 2023-06-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1025.91 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-26 | 2023-06-26 | 1 | 1 | 2023-06-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 1.35 | 1.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-30 | 2024-06-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1428.79 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-30 | 2024-06-30 | 1 | 0 | 2024-06-30 | 2025-08-12 | 409 | 292 | 2025-08-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-30 | 2025-09-03 | 431 | 308 | Unknown | Unknown | Unknown | Unknown | 2025-09-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | OH | IOU Design | Residential | Underserved Community | San Diego | COUNTY OF SAN DIEGO-SOUTH of 56, SAN DIEGO | 17184 | 17184 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-10 | 2024-10-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 129288.08 | 80352.31 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-10 | 2025-04-28 | 201 | 143 | 2025-04-28 | 2025-05-23 | 26 | 20 | 2025-03-31 | 2025-06-26 | 54 | 42 | 2025-03-31 | 2025-07-01 | 19 | 11 | 2025-05-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2020-12-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-21 | 2024-10-21 | 2024-11-18 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3018.8 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-21 | 2024-10-21 | 1 | 1 | 2024-10-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | Carlsbad | CARLSBAD | 16.05 | 16.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-15 | 2025-01-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 61810.86 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-15 | 2024-10-15 | 1 | 1 | 2024-10-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-02 | 2025-06-23 | 69 | 47 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-10-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-07 | 2023-06-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2273890 | 27395.84 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-07 | 2024-04-03 | 302 | 216 | 2024-04-03 | 2024-04-30 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-30 | Unknown | Unknown | Unknown | Unknown | 2024-07-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-02-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-22 | 2024-01-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3179.19 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-22 | 2024-01-24 | 3 | 3 | 2024-01-24 | 2024-03-25 | 62 | 44 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-25 | 2024-04-09 | 16 | 12 | Unknown | 2024-06-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | MISSION VIEJO | N/A | 103 | 103 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-12 | 2025-05-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1104.56 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-12 | 2025-06-03 | 23 | 17 | 2025-06-03 | 2025-06-04 | 2 | 2 | 2025-06-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-04 | 2025-07-30 | 57 | 41 | Unknown | 2025-07-15 | Unknown | Unknown | 2025-07-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-10 | 2025-06-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1117.16 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-10 | 2025-06-24 | 15 | 11 | 2025-06-24 | 2025-06-24 | 1 | 1 | 2025-06-10 | 2025-06-12 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2025-06-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | Underserved Community | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-25 | 2023-09-25 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 94207 | 33748.64 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-25 | 2024-04-16 | 205 | 147 | 2024-04-16 | 2024-08-20 | 127 | 91 | 2024-05-01 | 2024-08-16 | 47 | 32 | 2024-08-06 | 2024-09-06 | 30 | 21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-19 | 2025-05-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1000.35 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-19 | 2025-05-19 | 1 | 1 | 2025-05-19 | 2025-05-19 | 1 | 1 | 2025-05-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-21 | 2024-05-29 | 2024-07-16 | IOU Designed & Installed | N/A | No | Unknown | 699.32 | 0 | Unknown | Unknown | 79.29 | 620.03 | 0 | 1093.04 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-21 | 2024-04-23 | Unknown | Unknown | 2024-04-23 | 2024-06-20 | 59 | 43 | 2024-06-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-20 | 2024-07-16 | 27 | 19 | Unknown | 2024-06-25 | Unknown | Unknown | 2024-07-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | El Cajon | COUNTY OF SAN DIEGO-SOUTH of 56, EL CAJON | 218 | 218 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-09 | 2024-03-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 19963 | 59598.11 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-09 | 2023-12-07 | 29 | 21 | 2023-12-07 | 2025-06-26 | 568 | 406 | 2024-08-01 | Unknown | Unknown | Unknown | 2024-09-04 | 2025-08-04 | 56 | 32 | 2025-06-26 | Unknown | Unknown | Unknown | 2025-07-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SANTEE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-07 | 2024-11-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 197.01 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-07 | 2024-11-27 | 21 | 15 | 2024-11-27 | 2024-11-27 | 1 | 1 | 2024-11-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | N/A | 81.1 | 81.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-03 | 2024-09-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1189.69 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-03 | 2024-11-06 | 65 | 47 | 2024-11-06 | 2024-11-11 | 6 | 4 | 2024-11-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | N/A | SAN DIEGO | SAN DIEGO | 14 | 14 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-25 | 2024-03-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 10608 | 2122.19 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-25 | 2024-03-21 | Unknown | Unknown | 2024-03-21 | 2024-04-02 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2024-03-27 | 2024-04-15 | 20 | 14 | 2024-04-02 | Unknown | Unknown | Unknown | Unknown | 2025-05-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | Underserved Community | Chula Vista | CHULA VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-20 | 2022-05-20 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 181288.43 | 91444.11 | Unknown | Unknown | Yes | N/A | N/A | 2022-05-20 | 2024-08-20 | 824 | 588 | 2024-08-20 | 2025-01-22 | 156 | 112 | 2024-11-15 | 2025-04-07 | 8 | 6 | 2024-10-02 | 2025-04-15 | 89 | 65 | 2025-02-21 | Unknown | Unknown | Unknown | 2025-02-21 | 2025-07-07 | 137 | 97 | 2025-07-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 136.05 | 136.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-05 | 2024-09-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1422.98 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-05 | 2024-09-05 | 32 | 24 | 2024-09-05 | 2024-09-09 | 5 | 3 | 2024-09-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-13 | 2025-07-30 | 321 | 229 | Unknown | Unknown | Unknown | Unknown | 2025-07-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | 64 | 64 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-12 | 2023-10-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 949.16 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-12 | 2023-10-12 | 1 | 1 | 2023-10-12 | 2023-10-12 | 1 | 1 | 2023-10-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-03 | 2024-12-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3097.8 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-03 | 2024-11-07 | Unknown | Unknown | 2024-11-07 | 2024-12-06 | 30 | 22 | 2024-12-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | POWAY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-21 | 2024-11-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 275.8 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-21 | 2024-11-21 | 1 | 1 | 2024-11-21 | 2024-11-21 | 1 | 1 | 2024-11-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | Carlsbad | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-23 | 2025-05-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2025-05-23 | 2025-05-28 | 6 | 4 | 2025-05-28 | 2025-06-27 | 31 | 23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-27 | 2025-08-18 | 53 | 37 | Unknown | Unknown | Unknown | Unknown | 2025-08-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-14 | 2023-08-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 31061.47 | 4219.99 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-14 | 2023-08-16 | 3 | 3 | 2023-08-16 | 2024-02-02 | 171 | 123 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-02 | 2025-06-27 | 512 | 366 | Unknown | 2025-07-16 | Unknown | Unknown | 2025-07-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SPRING VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-09 | 2025-06-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1124.22 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-09 | 2025-05-21 | Unknown | Unknown | 2025-05-21 | 2025-06-12 | 23 | 17 | 2025-06-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | San Clemente | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-30 | 2024-12-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1333.23 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-30 | 2024-12-05 | 37 | 27 | 2024-12-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | Both | IOU Design | Residential | Underserved Community | San Diego | SAN DIEGO | 1152 | 1152 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2025-01-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-13 | 2024-12-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 533662.16 | 78079.48 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-13 | 2024-08-21 | 70 | 50 | 2024-08-21 | 2025-06-26 | 310 | 222 | 2025-03-04 | 2025-06-26 | 16 | 12 | 2025-02-24 | 2025-07-09 | 46 | 34 | 2025-06-26 | Unknown | Unknown | Unknown | 2025-07-28 | Unknown | Unknown | Unknown | 2025-08-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-11 | 2024-09-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 29653 | 729.14 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-11 | 2024-10-29 | 49 | 35 | 2024-10-29 | 2025-01-10 | 74 | 54 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | CARLSBAD | CARLSBAD | 8 | 8 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-25 | 2024-04-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2875.23 | 1950.71 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-25 | 2024-07-17 | 84 | 60 | 2024-07-17 | 2024-07-18 | 2 | 2 | 2024-10-11 | 2025-03-28 | 169 | 121 | 2024-05-13 | 2025-07-19 | 266 | 191 | 2024-07-18 | 2025-08-14 | 393 | 281 | Unknown | 2025-08-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 54.05 | 54.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-24 | 2025-02-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1676.05 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-24 | 2024-11-25 | Unknown | Unknown | 2024-11-25 | 2025-02-25 | 93 | 67 | 2025-02-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-17 |  | 2024-07-17 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1072.59 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-17 | 2024-05-17 | 1 | 1 | 2024-05-17 | 2024-05-17 | 1 | 1 | 2024-05-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-17 | 2024-07-17 | 62 | 44 | Unknown | Unknown | Unknown | Unknown | 2024-07-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-15 | 2023-08-15 | 2023-08-15 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 480.37 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-15 | 2023-05-16 | Unknown | Unknown | 2023-05-16 | 2023-08-15 | 92 | 66 | 2023-08-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-15 | 2023-08-15 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2023-08-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | OCEANSIDE | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2024-09-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-11 | 2024-12-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3753.77 | 483.39 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-11 | 2025-06-03 | 175 | 125 | 2025-06-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-01 | 2025-05-30 | 30 | 22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | Chula Vista | CHULA VISTA | 80 | 80 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-06 | 2024-10-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 21023 | 42340.12 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-06 | 2024-11-06 | 246 | 176 | 2024-11-06 | 2025-04-02 | 148 | 106 | 2025-01-13 | 2025-02-19 | 38 | 28 | 2025-02-14 | 2025-04-28 | 71 | 49 | 2025-04-02 | Unknown | Unknown | Unknown | 2025-05-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-07 | 2025-03-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1757.63 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-07 | 2025-02-19 | Unknown | Unknown | 2025-02-19 | 2025-03-07 | 17 | 13 | 2025-03-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-16 | 2024-11-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1567.86 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-16 | 2024-09-23 | Unknown | Unknown | 2024-09-23 | 2024-11-16 | 55 | 40 | 2024-11-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-16 | 2025-08-25 | 283 | 201 | Unknown | Unknown | Unknown | Unknown | 2025-08-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | CHULA VISTA | 139.1 | 139.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-21 | 2025-02-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 288.11 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-21 | 2024-12-30 | Unknown | Unknown | 2024-12-30 | 2025-06-02 | 155 | 111 | Unknown | Unknown | Unknown | Unknown | 2025-03-03 | 2025-03-21 | 19 | 15 | 2025-06-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SANTEE | N/A | 438 | 438 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-30 | 2025-01-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 114692 | 8248.37 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-30 | 2024-03-26 | Unknown | Unknown | 2024-03-26 | 2025-06-02 | 434 | 310 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 2898 | 2898 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-12-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-14 | 2024-10-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 35829 | 2035.97 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-14 | 2024-09-04 | Unknown | Unknown | 2024-09-04 | 2025-02-20 | 170 | 122 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CARLSBAD | CARLSBAD | 2.7 | 2.7 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-16 | 2025-06-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 998.14 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-16 | 2025-06-17 | 2 | 2 | 2025-06-17 | 2025-06-19 | 3 | 3 | 2025-06-19 | Unknown | Unknown | Unknown | 2025-06-23 | 2025-07-17 | 25 | 19 | 2025-06-19 | 2025-08-07 | 50 | 36 | Unknown | Unknown | Unknown | Unknown | 2025-08-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | BONITA | N/A | 10004.05 | 10004.05 | Not Available | >2MW | No | N/A | N/A | N/A | 2026-09-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-18 | 2025-02-18 | 2025-06-10 | IOU Designed & Installed | N/A | No | Unknown | -328.39 | 454.68 | Unknown | Unknown | -2387 | 1603.93 | Unknown | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2025-02-18 | 2025-02-26 | 9 | 7 | 2025-02-26 | 2025-03-12 | 15 | 11 | 2025-02-19 | 2025-04-15 | 56 | 40 | Unknown | Unknown | Unknown | Unknown | 2025-04-15 | 2025-06-10 | 57 | 41 | Unknown | 2025-05-06 | Unknown | Unknown | 2025-06-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-28 | 2025-01-28 | 2025-04-09 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1599.96 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-28 | 2025-01-28 | 1 | 1 | 2025-01-28 | 2025-01-28 | 1 | 1 | 2025-01-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-28 | 2025-04-09 | 72 | 52 | Unknown | Unknown | Unknown | Unknown | 2025-04-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 10 | 10 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-20 | 2025-05-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 869.44 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-20 | 2025-04-29 | Unknown | Unknown | 2025-04-29 | 2025-05-28 | 30 | 22 | 2025-05-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 69.05 | 69.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-10 | 2024-12-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1623.31 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-10 | 2024-10-31 | Unknown | Unknown | 2024-10-31 | 2024-12-10 | 41 | 29 | 2024-12-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-10 | 2025-08-13 | 247 | 177 | Unknown | Unknown | Unknown | Unknown | 2025-08-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-11 | 2025-04-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1118.01 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-11 | 2025-05-05 | 25 | 17 | 2025-05-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | LAGUNA NIGUEL | N/A | 68 | 68 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-05-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-11 | 2023-07-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2020.16 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-11 | 2023-07-31 | 21 | 15 | 2023-07-31 | 2023-08-09 | 10 | 8 | 2023-08-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-09 | Unknown | Unknown | Unknown | Unknown | 2023-09-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2020-02-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-30 | 2023-06-30 | 2023-07-24 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1110.53 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-30 | 2023-06-30 | 1 | 1 | 2023-06-30 | 2023-06-30 | 1 | 1 | 2023-06-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-30 | 2023-07-24 | 25 | 17 | Unknown | Unknown | Unknown | Unknown | 2023-07-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-09 | 2023-02-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3885 | 880.1 | Unknown | Unknown | Yes | N/A | N/A | 2023-01-09 | 2023-06-19 | 162 | 116 | 2023-06-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN CLEMENTE | SAN CLEMENTE | 130.05 | 130.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | 2025-04-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 3962.21 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-07 | 2025-04-30 | 24 | 18 | 2025-04-30 | 2025-05-14 | 15 | 11 | 2025-05-14 | Unknown | Unknown | Unknown | 2025-05-30 | 2025-06-16 | 18 | 12 | 2025-05-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-25 | 2023-01-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1519.49 | Unknown | Unknown | Yes | N/A | N/A | 2023-01-25 | 2023-03-11 | 46 | 33 | 2023-03-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | 5 | 5 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-03 | 2024-05-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3941 | 1006.89 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-03 | 2023-12-15 | Unknown | Unknown | 2023-12-15 | 2024-05-03 | 141 | 101 | 2024-05-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | 57.1 | 57.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-10 | 2024-09-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1545.62 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-10 | 2024-08-21 | Unknown | Unknown | 2024-08-21 | 2024-09-11 | 22 | 16 | 2024-09-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-11 | 2025-08-28 | 352 | 252 | Unknown | 2025-08-19 | Unknown | Unknown | 2025-08-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN MARCOS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2021-08-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-18 | 2025-02-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2388 | 663.29 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-18 | 2025-02-14 | Unknown | Unknown | 2025-02-14 | 2025-03-10 | 25 | 17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-10 | 2025-06-24 | 107 | 77 | Unknown | 2025-07-01 | Unknown | Unknown | 2025-07-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-26 | 2023-06-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 372.35 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-26 | 2023-07-22 | 27 | 20 | 2023-07-22 | 2023-07-22 | 1 | 0 | 2023-07-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | 795 | 795 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-29 | 2024-06-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1050.75 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-29 | 2024-05-23 | Unknown | Unknown | 2024-05-23 | 2024-09-09 | 110 | 78 | Unknown | Unknown | Unknown | Unknown | 2024-08-27 | 2024-09-26 | 31 | 23 | 2024-09-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-02 | 2025-04-08 | 2025-06-18 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2745.54 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-02 | 2024-10-24 | 115 | 83 | 2024-10-24 | 2025-04-21 | 180 | 128 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-21 | Unknown | Unknown | Unknown | Unknown | 2025-06-16 | Unknown | Unknown | 2025-06-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | POWAY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-12 | 2023-07-12 | 2023-09-07 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 802 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-12 | 2023-09-01 | 52 | 38 | 2023-09-01 | 2023-09-01 | 1 | 1 | 2023-09-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-01 | 2023-09-07 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2023-09-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 34.05 | 34.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-24 | 2025-02-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3961 | 1227.15 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-24 | 2025-02-11 | Unknown | Unknown | 2025-02-11 | 2025-02-24 | 14 | 10 | 2025-02-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-24 | 2025-07-29 | 156 | 112 | Unknown | Unknown | Unknown | Unknown | 2025-07-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | COUNTY OF SAN DIEGO-SOUTH of 56 | 5 | 5 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-21 | 2025-02-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1214.34 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-21 | 2025-03-04 | 135 | 97 | 2025-03-04 | 2025-03-11 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-08-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-10-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-07 | 2023-06-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 1129950 | 15773.99 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-07 | 2024-04-03 | 302 | 216 | 2024-04-03 | 2024-04-09 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2026-03-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-06 | 2024-03-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 54899 | 81.53 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-06 | 2024-09-20 | 199 | 143 | 2024-09-20 | 2024-10-15 | 26 | 18 | Unknown | Unknown | Unknown | Unknown | 2024-04-11 | 2024-10-09 | 61 | 43 | 2024-10-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 42.35 | 42.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-16 | Unknown | Unknown | No | 2025-01-17 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-17 | 2025-01-17 | Unknown | IOU Designed & Installed | N/A | Yes | 48 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1721.23 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-17 | 2025-03-06 | 49 | 35 | 2025-03-06 | 2025-01-17 | Unknown | Unknown | 2025-01-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-08 | 2025-04-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 11943 | 1609.19 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-08 | 2025-04-22 | 15 | 11 | 2025-04-22 | 2025-04-22 | 1 | 1 | 2025-04-17 | 2025-04-22 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2025-04-22 | 2025-08-05 | 106 | 76 | Unknown | Unknown | Unknown | Unknown | 2025-08-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 173.05 | 173.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-06 | 2025-05-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7962 | 1990.27 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-06 | 2025-05-29 | 24 | 18 | 2025-05-29 | 2025-06-02 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | 2025-05-29 | 2025-06-19 | 22 | 16 | 2025-06-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 20 | 20 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-17 | 2024-09-17 | 2024-11-15 | IOU Designed & Installed | N/A | No | Unknown | 720.36 | 456.4 | Unknown | 23.73 | Unknown | 240.23 | 0 | 2101.61 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-17 | 2024-09-11 | Unknown | Unknown | 2024-09-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-05-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-11 | 2023-10-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 800.45 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-11 | 2023-10-11 | 1 | 1 | 2023-10-11 | 2023-10-11 | 1 | 1 | 2023-10-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 375 | 375 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-26 | 2024-04-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 16517.24 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-26 | 2024-04-17 | 23 | 17 | 2024-04-17 | 2024-11-04 | 202 | 144 | 2024-07-19 | 2024-11-12 | 46 | 32 | 2024-08-09 | 2024-11-11 | 42 | 30 | 2025-02-18 | Unknown | Unknown | Unknown | 2025-02-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 9 | 9 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-18 | 2024-10-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1312.28 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-18 | 2024-09-27 | 10 | 8 | 2024-09-27 | 2024-10-14 | 18 | 12 | 2024-10-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 10 | 10 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-02 | 2025-01-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2683.7 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-02 | 2025-01-15 | 14 | 10 | 2025-01-15 | 2025-01-15 | 1 | 1 | 2025-01-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | OCEANSIDE | 134 | 134 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-06 | 2025-03-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7962 | 1949.03 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-06 | 2025-01-20 | Unknown | Unknown | 2025-01-20 | 2025-03-12 | 52 | 38 | Unknown | Unknown | Unknown | Unknown | 2025-03-12 | 2025-03-25 | 14 | 10 | 2025-03-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | 33 | 33 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-09 | 2024-10-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2379.78 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-09 | 2024-10-08 | Unknown | Unknown | 2024-10-08 | 2024-10-09 | 2 | 2 | 2024-10-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-09 | 2025-07-10 | 275 | 197 | Unknown | Unknown | Unknown | Unknown | 2025-07-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | N/A | 261.05 | 261.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-12 | 2023-04-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3987 | 642.73 | Unknown | Unknown | Yes | N/A | N/A | 2023-04-12 | 2023-04-17 | 6 | 4 | 2023-04-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 135.05 | 135.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-10 | 2023-11-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1777.95 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-10 | 2023-11-10 | 1 | 1 | 2023-11-10 | 2023-11-10 | 1 | 1 | 2023-11-10 | 2025-07-24 | 623 | 445 | Unknown | Unknown | Unknown | Unknown | 2023-11-10 | 2025-08-15 | 645 | 461 | Unknown | Unknown | Unknown | Unknown | 2025-08-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-27 | 2024-09-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1447.03 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-27 | 2024-09-27 | 1 | 1 | 2024-09-27 | 2024-09-27 | 1 | 1 | 2024-09-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2018-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-05 | 2023-04-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 71.74 | Unknown | Unknown | Yes | N/A | N/A | 2023-04-05 | 2023-04-06 | 2 | 2 | 2023-04-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-23 | 2024-01-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3075.4 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-23 | 2024-01-23 | 1 | 1 | 2024-01-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2021-03-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-23 | 2024-01-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2099.5 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-23 | 2024-01-24 | 2 | 2 | 2024-01-24 | 2024-02-02 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | 2024-01-24 | 2024-02-15 | 23 | 17 | 2024-02-02 | 2025-08-21 | 567 | 405 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-25 | 2024-01-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1101.2 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-25 | 2024-01-24 | Unknown | Unknown | 2024-01-24 | 2024-05-31 | 129 | 93 | 2024-05-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-14 | 2024-05-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 19202 | 511.69 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-14 | 2024-04-19 | 37 | 27 | 2024-04-19 | 2024-05-22 | 34 | 24 | 2024-05-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 29.35 | 29.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-23 | 2024-07-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 5768 | 2081.53 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-23 | 2024-07-23 | 1 | 1 | 2024-07-23 | 2024-10-24 | 94 | 68 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | VALLEY CENTER | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-25 | 2023-10-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 838.31 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-25 | 2023-08-10 | Unknown | Unknown | 2023-08-10 | 2023-10-25 | 77 | 55 | 2023-10-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 56 | 56 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-20 | 2025-06-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1638.38 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-20 | 2025-06-13 | Unknown | Unknown | 2025-06-13 | 2025-06-20 | 8 | 6 | 2025-06-20 | Unknown | Unknown | Unknown | 2025-06-20 | 2025-07-09 | 20 | 14 | 2025-06-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-12 | 2024-03-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 37616 | 754.13 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-12 | 2024-04-08 | 272 | 194 | 2024-04-08 | 2024-04-25 | 18 | 14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | Applicant Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-05 | 2023-07-07 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1679.78 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-05 | 2023-07-07 | 3 | 3 | 2023-07-07 | 2023-11-27 | 144 | 102 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 375 | 375 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-17 | 2024-04-17 | 2025-03-05 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 30033.72 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-17 | 2024-04-17 | 1 | 1 | 2024-04-17 | 2024-11-04 | 202 | 144 | 2024-10-14 | 2024-11-04 | 22 | 16 | 2024-07-23 | 2025-08-01 | 280 | 202 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 14400 | 14400 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-06-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-14 | 2023-08-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 153.83 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-14 | 2023-09-11 | 29 | 21 | 2023-09-11 | 2023-09-11 | 1 | 1 | 2023-09-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 111 | 111 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-08 | 2024-02-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2514.32 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-08 | 2024-01-04 | Unknown | Unknown | 2024-01-04 | 2024-10-11 | 282 | 202 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-11 | Unknown | Unknown | Unknown | Unknown | 2025-08-20 | Unknown | Unknown | 2025-09-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-14 | 2024-08-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1191.81 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-14 | 2025-01-13 | 153 | 109 | 2025-01-13 | 2025-01-23 | 11 | 9 | 2025-01-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-24 | 2025-07-01 | 159 | 113 | Unknown | 2025-07-25 | Unknown | Unknown | 2025-07-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Residential | Underserved Community | San Diego | SAN DIEGO | 681 | 681 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-07 | 2025-01-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 595 | 29171.4 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-07 | 2024-06-29 | Unknown | Unknown | 2024-06-29 | 2025-02-26 | 243 | 173 | 2024-12-27 | 2025-04-10 | 21 | 15 | 2025-02-04 | 2025-03-14 | 31 | 22 | 2025-03-04 | Unknown | Unknown | Unknown | 2025-03-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-11 | 2025-02-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1765.04 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-11 | 2025-02-28 | 18 | 14 | 2025-02-28 | 2025-02-28 | 1 | 1 | 2025-02-28 | 2025-04-30 | 62 | 44 | Unknown | Unknown | Unknown | Unknown | 2025-04-30 | 2025-07-29 | 91 | 65 | Unknown | Unknown | Unknown | Unknown | 2025-07-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-22 | 2024-11-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1549.08 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-22 | 2024-11-22 | 1 | 1 | 2024-11-22 | 2025-04-18 | 148 | 106 | Unknown | Unknown | Unknown | Unknown | 2024-11-25 | 2025-01-10 | 47 | 35 | 2025-04-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN JUAN CAPISTRANO | N/A | 108.05 | 108.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-24 | 2024-09-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1064.74 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-24 | 2024-12-06 | 74 | 54 | 2024-12-06 | 2024-12-09 | 4 | 2 | 2024-12-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 266 | 266 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-08 | 2024-01-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 11943 | 873.85 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-08 | 2024-01-11 | 4 | 4 | 2024-01-11 | 2024-01-17 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-17 | 2025-08-25 | 587 | 419 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LEMON GROVE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-23 |  | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1546.8 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-23 | 2024-08-23 | 1 | 1 | 2024-08-23 | 2024-08-23 | 1 | 1 | 2024-08-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | N/A | 36.36 | 36.36 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-15 | 2024-03-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 6563 | 608.01 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-15 | 2024-01-31 | Unknown | Unknown | 2024-01-31 | 2024-03-27 | 57 | 41 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-08 | 2024-10-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1220.59 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-08 | 2024-11-05 | 29 | 21 | 2024-11-05 | 2024-11-11 | 7 | 5 | 2024-11-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 39.05 | 39.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-07 | 2024-10-07 | 2024-12-02 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1714.96 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-07 | 2024-07-11 | Unknown | Unknown | 2024-07-11 | 2024-10-07 | 89 | 63 | 2024-10-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-07 | 2024-12-02 | 57 | 41 | Unknown | Unknown | Unknown | Unknown | 2024-12-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R29/R45 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | ENCINITAS, SAN DIEGO | 606136 | 606136 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-11-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-14 | 2024-04-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 46655.7 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-14 | 2024-07-01 | 110 | 78 | 2024-07-01 | 2025-01-24 | 208 | 150 | 2024-08-20 | 2025-05-22 | 17 | 13 | 2024-04-11 | 2025-02-20 | 47 | 34 | 2025-01-24 | Unknown | Unknown | Unknown | Unknown | 2025-08-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | Disadvantaged Community,Underserved Community | Chula Vista | CHULA VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-09 | 2023-11-09 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 42318 | 85704.64 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-09 | 2024-10-28 | 355 | 253 | 2024-10-28 | 2025-03-20 | 144 | 104 | 2024-11-07 | 2025-08-01 | 68 | 49 | 2025-03-03 | 2025-04-25 | 47 | 35 | 2025-07-02 | Unknown | Unknown | Unknown | 2025-07-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-14 | 2024-05-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 416.84 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-14 | 2024-05-14 | 1 | 1 | 2024-05-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | VALLEY CENTER | N/A | 188.05 | 188.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-24 | 2025-04-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1094.55 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-24 | 2025-04-23 | Unknown | Unknown | 2025-04-23 | 2025-04-24 | 2 | 2 | 2025-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN MARCOS | COUNTY OF SAN DIEGO-NORTH of 56, SAN MARCOS | 156 | 156 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-25 | 2024-10-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2652.32 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-25 | 2024-11-21 | 58 | 42 | 2024-11-21 | 2025-04-15 | 146 | 104 | 2025-01-17 | 2025-01-21 | 5 | 3 | 2025-01-08 | 2025-06-09 | 34 | 22 | 2025-04-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-31 | 2024-02-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | 150.09 | 70.27 | Unknown | Unknown | Unknown | 79.82 | 0 | 2575.2 | Unknown | Unknown | Yes | N/A | N/A | 2023-01-31 | 2023-09-25 | 238 | 170 | 2023-09-25 | 2025-01-22 | 486 | 348 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-22 | 2025-04-02 | 71 | 51 | Unknown | 2025-07-02 | Unknown | Unknown | 2025-07-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-15 | 2024-10-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2244.92 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-15 | 2024-10-15 | 1 | 1 | 2024-10-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 3 | 3 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-14 | 2025-03-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1231.32 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-14 | 2025-03-06 | Unknown | Unknown | 2025-03-06 | 2025-03-24 | 19 | 13 | 2025-03-24 | 2025-03-24 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2025-03-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | Applicant Design | Commercial | Underserved Community | ESCONDIDO | ESCONDIDO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2024-09-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-19 | 2024-09-19 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3753.77 | 460.73 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-19 | 2025-05-29 | 253 | 181 | 2025-05-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-14 | 2025-02-26 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | N/A | 147.05 | 147.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-27 | 2024-03-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2493.86 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-27 | 2024-03-27 | 1 | 1 | 2024-03-27 | 2024-10-24 | 212 | 152 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 39 | 39 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-06 | 2024-12-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1587.14 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-06 | 2024-12-06 | 1 | 1 | 2024-12-06 | 2024-12-06 | 1 | 1 | 2024-12-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | N/A | RAMONA | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-22 | 2023-08-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 470.08 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-22 | 2024-01-22 | 154 | 110 | 2024-01-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-04-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-15 | 2024-05-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2732.95 | Unknown | Unknown | Yes | N/A | N/A | 2022-04-15 | 2024-05-17 | 764 | 546 | 2024-05-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | 9.05 | 9.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-03 | 2025-03-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1242.16 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-03 | 2025-03-07 | 5 | 5 | 2025-03-07 | 2025-03-07 | 1 | 1 | 2025-03-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-16 | 2025-02-12 | 2025-05-02 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 996.16 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-16 | 2025-02-12 | 59 | 43 | 2025-02-12 | 2025-02-12 | 1 | 1 | 2025-02-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-12 | 2025-05-02 | 80 | 58 | Unknown | Unknown | Unknown | Unknown | 2025-05-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-01 | 2025-05-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1462.68 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-01 | 2025-05-15 | 15 | 11 | 2025-05-15 | 2025-05-15 | 1 | 1 | 2025-05-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-02 | 2023-03-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 403.49 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-02 | 2023-03-02 | 1 | 1 | 2023-03-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | POWAY | N/A | 22100 | 22100 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-09-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-15 | 2023-03-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1643.41 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-15 | 2023-10-10 | 210 | 150 | 2023-10-10 | 2023-12-06 | 58 | 42 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | La Mesa | LA MESA | 98.05 | 98.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-04 | 2024-04-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 35916.61 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-04 | 2024-04-05 | 2 | 2 | 2024-04-05 | 2024-12-12 | 252 | 180 | Unknown | Unknown | Unknown | Unknown | 2024-07-08 | 2025-09-03 | 82 | 60 | 2024-12-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | BONITA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-17 | 2024-10-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2465.21 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-17 | 2024-10-29 | 13 | 9 | 2024-10-29 | 2024-10-29 | 1 | 1 | 2024-10-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | IMPERIAL BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-08 | 2024-02-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 481.85 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-08 | 2024-03-11 | 33 | 23 | 2024-03-11 | 2024-07-09 | 121 | 87 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-09 | 2025-08-14 | 402 | 288 | Unknown | 2025-08-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-24 | 2025-02-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 313.85 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-24 | 2025-02-07 | Unknown | Unknown | 2025-02-07 | 2025-02-27 | 21 | 15 | 2025-02-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CORONADO | CORONADO | 138.05 | 138.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-17 | 2024-10-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 477.21 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-17 | 2024-10-17 | 1 | 1 | 2024-10-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-17 | 2024-11-19 | 34 | 24 | 2024-11-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-21 | 2024-02-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1363.7 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-21 | 2024-01-30 | 163 | 117 | 2024-01-30 | 2024-07-10 | 163 | 117 | 2023-08-21 | 2024-02-06 | 170 | 120 | Unknown | Unknown | Unknown | Unknown | 2024-07-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-07 | 2024-10-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | 5234.19 | 1152.74 | Unknown | 108.42 | Unknown | 3973.03 | 0 | 10928.21 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-07 | 2024-07-17 | Unknown | Unknown | 2024-07-17 | 2025-03-05 | 232 | 166 | 2024-10-18 | 2024-12-19 | 34 | 24 | 2024-10-17 | 2024-12-12 | 33 | 25 | 2025-03-05 | 2025-04-21 | 48 | 34 | Unknown | 2025-04-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 5 | 5 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-29 | 2024-01-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2665.45 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-29 | 2023-11-14 | Unknown | Unknown | 2023-11-14 | 2024-11-15 | 368 | 264 | 2024-11-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-04 | 2023-08-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 148.7 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-04 | 2023-05-25 | Unknown | Unknown | 2023-05-25 | 2023-08-04 | 72 | 52 | 2023-08-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LEMON GROVE | N/A | 62.05 | 62.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-06 | 2025-05-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1093.77 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-06 | 2025-05-28 | 23 | 17 | 2025-05-28 | 2025-05-28 | 1 | 1 | 2025-05-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CAMPO | N/A | 38 | 38 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-05 | 2024-01-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 983.69 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-05 | 2023-11-21 | Unknown | Unknown | 2023-11-21 | 2024-01-05 | 46 | 34 | 2024-01-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 179 | 179 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-07 | 2025-02-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1539.08 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-07 | 2025-02-07 | 1 | 1 | 2025-02-07 | 2025-02-07 | 1 | 1 | 2025-02-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-10 | 2024-05-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 930.68 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-10 | 2024-05-10 | 1 | 1 | 2024-05-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-20 | 2025-03-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1552.03 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-20 | 2025-03-20 | 1 | 1 | 2025-03-20 | 2025-03-26 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2025-03-20 | 2025-04-02 | 14 | 10 | 2025-03-26 | 2025-07-23 | 120 | 86 | Unknown | Unknown | Unknown | Unknown | 2025-08-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | 1014 | 1014 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2025-10-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-24 | 2024-12-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 4567.65 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-24 | 2024-12-06 | 197 | 141 | 2024-12-06 | 2024-12-06 | 1 | 1 | 2024-12-06 | 2024-12-18 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2024-12-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 64 | 64 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-23 | 2024-05-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1282.03 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-23 | 2024-04-04 | Unknown | Unknown | 2024-04-04 | 2024-05-31 | 58 | 42 | 2024-05-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-17 | 2024-04-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 32471.88 | 20892.18 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-17 | 2024-04-19 | 3 | 3 | 2024-04-19 | 2025-05-28 | 405 | 289 | 2024-05-28 | 2025-05-23 | 46 | 33 | 2024-08-01 | 2025-06-18 | 40 | 30 | 2025-05-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SOLANA BEACH | N/A | 155.05 | 155.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-02 | Unknown | Unknown | No | 2023-04-20 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-20 | 2023-07-26 | Unknown | IOU Designed & Installed | N/A | Yes | 679 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 3038.25 | Unknown | Unknown | Yes | N/A | N/A | 2023-04-20 | 2025-02-27 | 680 | 486 | 2025-02-27 | 2023-10-05 | Unknown | Unknown | 2023-10-05 | 2024-08-07 | 308 | 220 | Unknown | Unknown | Unknown | Unknown | 2024-08-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | RANCHO LA COSTA | N/A | 74 | 74 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-08 | 2024-01-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2574.48 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-08 | 2024-09-27 | 264 | 190 | 2024-09-27 | 2024-09-27 | 1 | 1 | 2024-09-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SOUTH LAGUNA | LAGUNA BEACH | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-13 | 2025-06-13 | 2025-06-17 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 257.6 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-13 | 2025-06-11 | Unknown | Unknown | 2025-06-11 | 2025-06-13 | 3 | 3 | 2025-06-13 | Unknown | Unknown | Unknown | 2025-06-18 | 2025-06-25 | 8 | 6 | 2025-06-13 | 2025-06-17 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | 2025-06-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2025-04-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-30 | 2024-05-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 472.65 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-30 | 2024-05-01 | 2 | 2 | 2024-05-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-17 | 2024-06-13 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | OH | IOU Design | Commercial | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-15 | 2025-02-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 112994.36 | 42093.93 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-15 | 2025-01-16 | 63 | 45 | 2025-01-16 | 2025-05-06 | 111 | 79 | 2025-04-07 | 2025-04-14 | 8 | 6 | 2025-04-30 | 2025-05-08 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-29 | Unknown | Unknown | No | 2024-05-08 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-08 | 2024-06-07 | Unknown | IOU Designed & Installed | N/A | Yes | 156 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1934 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-08 | 2024-08-08 | 93 | 67 | 2024-08-08 | 2024-10-31 | 85 | 61 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SPRING VALLEY | COUNTY OF SAN DIEGO-SOUTH of 56, LA MESA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-20 | 2024-06-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7382 | 875.09 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-20 | 2024-05-24 | 5 | 5 | 2024-05-24 | 2024-06-19 | 27 | 19 | 2024-06-27 | 2024-07-03 | 7 | 5 | 2024-06-18 | 2024-07-09 | 18 | 14 | 2024-06-19 | Unknown | Unknown | Unknown | Unknown | 2025-01-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-12 | 2024-02-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1028.28 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-12 | 2023-09-08 | Unknown | Unknown | 2023-09-08 | 2024-02-13 | 159 | 113 | 2024-02-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | LEMON GROVE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-02-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-18 | 2023-01-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 13818 | 250.05 | Unknown | Unknown | Yes | N/A | N/A | 2023-01-18 | 2023-02-13 | 27 | 19 | 2023-02-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-27 | 2023-09-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 158.14 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-27 | 2023-10-30 | 34 | 24 | 2023-10-30 | 2023-10-30 | 1 | 1 | 2023-10-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-14 | 2025-02-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 997.93 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-14 | 2025-02-10 | 28 | 20 | 2025-02-10 | 2025-02-10 | 1 | 1 | 2025-02-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-04 | 2025-03-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1361.52 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-04 | 2025-02-18 | Unknown | Unknown | 2025-02-18 | 2025-03-21 | 32 | 24 | 2025-03-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-21 | 2025-07-29 | 131 | 93 | Unknown | 2025-05-15 | Unknown | Unknown | 2025-07-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-17 | 2025-03-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 791.62 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-17 | 2025-04-30 | 45 | 33 | 2025-04-30 | 2025-05-05 | 6 | 4 | 2025-05-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-05 | 2025-07-07 | 64 | 46 | Unknown | 2025-07-11 | Unknown | Unknown | 2025-07-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | ESCONDIDO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2024-09-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-19 | 2024-09-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3753.77 | 735.01 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-19 | 2025-04-04 | 198 | 142 | 2025-04-04 | 2025-05-19 | 46 | 32 | Unknown | Unknown | Unknown | Unknown | 2025-02-14 | 2025-02-26 | 13 | 9 | 2025-05-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Disadvantaged Community,Underserved Community | CHULA VISTA | CHULA VISTA | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2025-04-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-30 | 2024-05-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 468.05 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-30 | 2024-05-02 | 3 | 3 | 2024-05-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-30 | 2024-07-11 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-14 | 2025-05-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1172.99 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-14 | 2025-05-21 | 8 | 6 | 2025-05-21 | 2025-05-29 | 9 | 7 | 2025-05-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | CORONADO | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-25 | 2025-03-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1501.5 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-25 | 2025-02-28 | Unknown | Unknown | 2025-02-28 | 2025-03-26 | 27 | 19 | 2025-03-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-30 | 2025-04-30 | 2025-05-30 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1193.84 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-30 | 2025-04-30 | 1 | 1 | 2025-04-30 | 2025-04-30 | 1 | 1 | 2025-04-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-30 | 2025-05-30 | 31 | 23 | Unknown | Unknown | Unknown | Unknown | 2025-05-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | Rancho Viejo | N/A | 5.4 | 5.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-19 | 2025-03-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2025-03-19 | 2024-11-01 | Unknown | Unknown | 2024-11-01 | 2025-06-18 | 230 | 164 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 118.1 | 118.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-02 | 2023-10-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1805.54 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-02 | 2023-09-08 | Unknown | Unknown | 2023-09-08 | 2023-10-06 | 29 | 21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-20 | 2023-07-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1852.11 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-20 | 2023-07-21 | 2 | 2 | 2023-07-21 | 2023-11-06 | 109 | 77 | Unknown | Unknown | Unknown | Unknown | 2023-07-24 | 2023-07-31 | 8 | 6 | 2023-11-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-25 | 2024-09-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1150.97 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-25 | 2024-09-10 | Unknown | Unknown | 2024-09-10 | 2024-10-04 | 25 | 19 | 2024-10-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 67.05 | 67.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-26 | 2025-03-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1852.91 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-26 | 2025-03-25 | Unknown | Unknown | 2025-03-25 | 2025-04-02 | 9 | 7 | 2025-04-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 149.05 | 149.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-10 | 2024-06-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3245.18 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-10 | 2023-11-16 | Unknown | Unknown | 2023-11-16 | 2024-06-13 | 211 | 151 | 2024-06-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-06 | 2025-05-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 600 | 425.86 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-06 | 2025-04-23 | Unknown | Unknown | 2025-04-23 | 2025-05-15 | 23 | 17 | 2025-05-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-12 | 2023-05-30 | 2025-06-27 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 807370 | 53838.33 | Unknown | Unknown | Yes | N/A | N/A | 2023-04-12 | 2023-04-11 | Unknown | Unknown | 2023-04-11 | 2024-03-19 | 344 | 246 | 2023-08-16 | 2023-11-07 | 3 | 3 | 2023-12-04 | 2024-03-22 | 8 | 8 | 2024-03-19 | 2025-04-29 | 407 | 291 | 2024-08-14 | 2025-05-27 | 287 | 205 | 2025-06-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | OH | Applicant Design | Commercial | N/A | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-10-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-09 | 2024-05-09 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 12397.28 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-09 | 2024-08-08 | 92 | 66 | 2024-08-08 | Unknown | Unknown | Unknown | 2024-07-26 | 2024-08-08 | 14 | 10 | 2024-06-26 | 2025-02-25 | 35 | 25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | LA MESA | LA MESA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-25 | 2023-05-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 5606 | 752.42 | Unknown | Unknown | Yes | N/A | N/A | 2023-05-25 | 2023-05-25 | 1 | 1 | 2023-05-25 | 2023-06-01 | 8 | 6 | 2024-05-16 | 2024-05-17 | 2 | 2 | 2023-05-25 | 2024-06-28 | 401 | 287 | 2023-06-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | CAPISTRANO BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-23 | 2024-08-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1472.92 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-23 | 2024-08-23 | 1 | 1 | 2024-08-23 | 2024-08-23 | 1 | 1 | 2024-08-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-26 | Unknown | Unknown | Unknown | Unknown | 2025-06-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-07 | 2024-04-08 | 2024-04-09 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1072.03 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-07 | 2024-01-10 | Unknown | Unknown | 2024-01-10 | 2024-04-08 | 90 | 64 | 2024-04-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-08 | 2024-04-09 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-04-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-23 | 2024-10-17 | 2024-11-12 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1665.9 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-23 | 2024-08-16 | Unknown | Unknown | 2024-08-16 | 2024-10-17 | 63 | 45 | 2024-10-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-17 | 2024-11-12 | 27 | 19 | Unknown | Unknown | Unknown | Unknown | 2024-11-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-22 | 2024-08-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1150.97 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-22 | 2024-08-07 | Unknown | Unknown | 2024-08-07 | 2024-09-27 | 52 | 38 | 2024-09-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | LEMON GROVE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-10 | 2024-12-10 | 2024-12-20 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1632.75 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-10 | 2024-12-13 | 4 | 4 | 2024-12-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | N/A | LA JOLLA | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-18 | 2024-01-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 712.76 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-18 | 2024-03-29 | 72 | 52 | 2024-03-29 | 2024-04-02 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | 2024-02-14 | 2024-03-06 | 22 | 16 | 2024-04-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-10 | 2023-05-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 110.98 | Unknown | Unknown | Yes | N/A | N/A | 2023-05-10 | 2023-05-10 | 1 | 1 | 2023-05-10 | 2023-05-15 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 781.1 | 781.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-21 | 2024-11-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1589.1 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-21 | 2024-11-05 | Unknown | Unknown | 2024-11-05 | 2025-02-12 | 100 | 72 | 2025-02-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-12 | 2025-08-07 | 177 | 127 | Unknown | Unknown | Unknown | Unknown | 2025-08-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 1182 | 1182 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2023-03-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-19 | 2024-06-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 852.7 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-19 | 2024-05-14 | Unknown | Unknown | 2024-05-14 | 2024-07-03 | 51 | 37 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | ESCONDIDO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2024-09-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-19 | 2024-09-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3753.77 | 676.86 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-19 | 2025-04-15 | 209 | 149 | 2025-04-15 | 2025-05-06 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | 2025-03-21 | 2025-04-08 | 19 | 13 | 2025-05-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-30 | 2025-04-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 12481 | 397.2 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-30 | 2025-04-16 | Unknown | Unknown | 2025-04-16 | 2025-04-30 | 15 | 11 | 2025-04-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 114.1 | 114.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-04 | 2025-03-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7962 | 1899.77 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-04 | 2025-03-25 | 50 | 36 | 2025-03-25 | 2025-04-15 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | 2025-06-27 | 2025-08-14 | 49 | 35 | 2025-04-15 | 2025-07-18 | 95 | 69 | Unknown | 2025-09-02 | Unknown | Unknown | 2025-09-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-17 | 2024-11-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2843.5 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-17 | 2024-11-07 | 22 | 16 | 2024-11-07 | 2024-11-07 | 1 | 1 | 2024-11-07 | 2025-07-08 | 244 | 174 | Unknown | Unknown | Unknown | Unknown | 2025-01-03 | Unknown | Unknown | Unknown | Unknown | 2025-09-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | Underserved Community | Escondido | ESCONDIDO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-11 | 2023-05-11 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 95533.85 | Unknown | Unknown | Yes | N/A | N/A | 2023-05-11 | 2023-08-08 | 90 | 64 | 2023-08-08 | 2024-08-01 | 360 | 258 | 2023-09-05 | 2024-02-20 | 72 | 52 | 2023-11-03 | 2024-10-14 | 31 | 23 | 2025-01-27 | Unknown | Unknown | Unknown | 2025-01-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-19 | 2024-12-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2145.8 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-19 | 2024-12-19 | 1 | 1 | 2024-12-19 | 2024-12-19 | 1 | 1 | 2024-12-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | 1286 | 1286 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2024-04-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-26 | 2024-08-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 221000 | 7224.44 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-26 | 2024-09-30 | 36 | 26 | 2024-09-30 | 2024-10-10 | 11 | 9 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LEMON GROVE | N/A | 3.35 | 3.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-20 | 2023-10-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 788.25 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-20 | 2023-10-12 | Unknown | Unknown | 2023-10-12 | 2023-10-20 | 9 | 7 | 2023-10-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-03 | 2025-06-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 817.04 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-03 | 2025-05-27 | Unknown | Unknown | 2025-05-27 | 2025-06-12 | 17 | 13 | 2025-06-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-12 | 2025-07-14 | 33 | 23 | Unknown | Unknown | Unknown | Unknown | 2025-07-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-10 | 2025-01-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 9150 | 525.43 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-10 | 2024-10-22 | Unknown | Unknown | 2024-10-22 | 2025-01-10 | 81 | 59 | 2025-01-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | Vista | N/A | 75 | 75 | Not Available | <1MW | No | N/A | N/A | N/A | 2020-08-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-28 | 2025-03-31 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2025-03-28 | 2025-02-14 | Unknown | Unknown | 2025-02-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-08 | 2024-08-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-08 | 2024-08-08 | 1 | 1 | 2024-08-08 | 2025-02-20 | 197 | 141 | Unknown | Unknown | Unknown | Unknown | 2024-12-01 | 2025-01-07 | 38 | 27 | 2025-02-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | VALLEY CENTER | N/A | 124 | 124 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-23 | 2025-05-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 985.48 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-23 | 2025-05-20 | Unknown | Unknown | 2025-05-20 | 2025-06-06 | 18 | 14 | 2025-06-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-18 | 2025-03-18 | 2025-03-25 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2138.41 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-18 | 2025-03-07 | Unknown | Unknown | 2025-03-07 | 2025-03-18 | 12 | 8 | 2025-03-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-18 | 2025-03-25 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2025-03-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 35 | 35 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-11 | 2025-03-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1830.82 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-11 | 2025-03-17 | 35 | 25 | 2025-03-17 | 2025-03-17 | 1 | 1 | 2025-02-28 | 2025-06-12 | 105 | 75 | Unknown | Unknown | Unknown | Unknown | 2025-03-17 | 2025-07-09 | 115 | 83 | Unknown | Unknown | Unknown | Unknown | 2025-07-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | Applicant Design | Commercial | Underserved Community | OCEANSIDE | OCEANSIDE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-03-18 | 2022-03-18 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 205500 | 28418.94 | Unknown | Unknown | Yes | N/A | N/A | 2022-03-18 | 2023-08-25 | 526 | 376 | 2023-08-25 | 2023-10-19 | 56 | 40 | 2023-09-18 | 2023-10-11 | 24 | 18 | 2023-10-19 | 2025-08-15 | -2753 | -1978 | Unknown | Unknown | Unknown | Unknown | 2025-02-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | 19.35 | 19.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-12 | 2024-07-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1722.95 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-12 | 2024-07-12 | 1 | 1 | 2024-07-12 | 2024-07-12 | 1 | 1 | 2024-07-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | VISTA | 102 | 102 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-18 | 2024-10-31 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2059.83 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-18 | 2024-10-31 | 44 | 32 | 2024-10-31 | 2024-11-01 | 2 | 2 | 2024-11-01 | Unknown | Unknown | Unknown | 2024-11-04 | 2024-11-21 | 18 | 14 | 2024-11-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-10 | 2024-07-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1595.2 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-10 | 2024-06-10 | Unknown | Unknown | 2024-06-10 | 2024-07-18 | 39 | 29 | 2024-07-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 185.25 | 185.25 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-28 | 2025-01-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2149.25 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-28 | 2025-02-03 | 7 | 5 | 2025-02-03 | 2025-02-14 | 12 | 10 | 2025-02-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN MARCOS | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-23 | 2022-06-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 432.61 | Unknown | Unknown | Yes | N/A | N/A | 2022-06-23 | 2023-01-31 | 223 | 159 | 2023-01-31 | 2023-02-13 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | Rancho Viejo | N/A | 3254 | 3254 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-10-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-31 | 2025-04-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2025-03-31 | 2024-07-01 | Unknown | Unknown | 2024-07-01 | 2025-06-18 | 353 | 253 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-18 | 2025-05-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-14 | 2024-11-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3568.94 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-14 | 2024-11-14 | 1 | 1 | 2024-11-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 8 | 8 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-31 | 2025-03-31 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1416.13 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-31 | 2025-03-20 | Unknown | Unknown | 2025-03-20 | 2025-04-02 | 14 | 10 | 2025-04-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-02 | 2025-08-14 | 135 | 97 | Unknown | 2025-07-30 | Unknown | Unknown | 2025-08-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-06 | 2024-02-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3844.22 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-06 | 2024-02-06 | 1 | 1 | 2024-02-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | 5.4 | 5.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-25 | 2025-06-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1082.64 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-25 | 2025-06-16 | Unknown | Unknown | 2025-06-16 | 2025-06-26 | 11 | 9 | 2025-06-26 | Unknown | Unknown | Unknown | 2025-09-03 | 2025-09-03 | 1 | 1 | 2025-06-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-12 | 2024-02-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 829.62 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-12 | 2024-02-23 | 12 | 10 | 2024-02-23 | 2024-02-23 | 1 | 1 | 2024-02-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LAKESIDE | LAKESIDE | 49 | 49 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-28 | 2024-12-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2838.62 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-28 | 2025-01-16 | 81 | 59 | 2025-01-16 | 2025-01-16 | 1 | 1 | 2025-01-16 | Unknown | Unknown | Unknown | 2025-01-22 | 2025-02-19 | 29 | 21 | 2025-01-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | ESCONDIDO | 1056 | 1056 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2023-12-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-28 | 2023-11-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2875.23 | 322.57 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-28 | 2024-01-11 | 45 | 33 | 2024-01-11 | 2024-03-08 | 58 | 42 | Unknown | Unknown | Unknown | Unknown | 2024-01-19 | 2024-01-31 | 13 | 9 | 2024-03-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-26 | 2024-08-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 27449 | 494.79 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-26 | 2024-09-19 | 25 | 19 | 2024-09-19 | 2024-09-19 | 1 | 1 | 2024-09-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-14 | 2024-11-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1166.99 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-14 | 2025-01-16 | 64 | 46 | 2025-01-16 | 2025-01-22 | 7 | 5 | 2025-01-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 17184 | 17184 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-11 | 2025-03-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 153065 | 8615.18 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-11 | 2025-03-27 | 442 | 316 | 2025-03-27 | 2025-05-23 | 58 | 42 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-29 | 2024-09-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2015.5 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-29 | 2024-06-18 | Unknown | Unknown | 2024-06-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | ENCINITAS | N/A | 39 | 39 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-13 | 2023-11-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 905.34 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-13 | 2023-11-27 | 15 | 11 | 2023-11-27 | 2023-11-27 | 1 | 1 | 2023-11-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 9 | 9 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-16 | 2025-04-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2485.62 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-16 | 2025-05-09 | 24 | 18 | 2025-05-09 | 2025-05-28 | 20 | 14 | 2025-05-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | COUNTY OF SAN DIEGO-SOUTH of 56 | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-20 | 2023-10-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 820.76 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-20 | 2023-08-31 | Unknown | Unknown | 2023-08-31 | 2023-10-20 | 51 | 37 | 2023-10-20 | Unknown | Unknown | Unknown | 2023-10-20 | 2023-10-25 | 6 | 4 | 2023-10-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-27 | 2024-05-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2777.6 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-27 | 2023-10-18 | 22 | 16 | 2023-10-18 | 2024-07-08 | 265 | 189 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-27 | 2024-05-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1831.42 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-27 | 2024-03-06 | Unknown | Unknown | 2024-03-06 | 2024-08-09 | 157 | 113 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 41.4 | 41.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-28 | 2024-03-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1637.61 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-28 | 2023-12-08 | Unknown | Unknown | 2023-12-08 | 2024-09-30 | 298 | 212 | 2024-09-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 39.05 | 39.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-05 | 2025-03-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 11943 | 2030.09 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-05 | 2025-03-05 | 1 | 1 | 2025-03-05 | 2025-03-14 | 10 | 8 | 2025-03-05 | 2025-06-18 | 106 | 76 | Unknown | Unknown | Unknown | Unknown | 2025-03-13 | 2025-09-09 | 181 | 129 | Unknown | Unknown | Unknown | Unknown | 2025-09-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | LAGUNA HILLS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-13 | 2024-03-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2313.21 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-13 | 2024-02-22 | Unknown | Unknown | 2024-02-22 | 2024-04-17 | 56 | 40 | 2024-04-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | CHULA VISTA | 108.05 | 108.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-19 | 2024-09-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2832.56 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-19 | 2024-10-03 | 46 | 34 | 2024-10-03 | 2024-12-09 | 68 | 48 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-09 | Unknown | Unknown | Unknown | Unknown | 2025-01-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-10 | 2025-02-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3982.41 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-10 | 2025-02-03 | Unknown | Unknown | 2025-02-03 | 2025-04-04 | 61 | 45 | Unknown | Unknown | Unknown | Unknown | 2025-02-18 | 2025-03-14 | 25 | 19 | 2025-04-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 194.05 | 194.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-23 | 2025-06-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1439.49 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-23 | 2025-05-19 | Unknown | Unknown | 2025-05-19 | 2025-06-25 | 38 | 28 | 2025-06-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-26 | 2025-08-13 | 49 | 35 | Unknown | Unknown | Unknown | Unknown | 2025-08-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | MISSION VIEJO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-31 | 2023-06-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 110.98 | Unknown | Unknown | Yes | N/A | N/A | 2023-05-31 | 2023-06-02 | 3 | 3 | 2023-06-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-10 | 2025-06-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2716.1 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-10 | 2025-06-20 | 11 | 9 | 2025-06-20 | 2025-06-20 | 1 | 1 | 2025-06-10 | 2025-06-11 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2025-06-20 | 2025-07-02 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2025-07-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-17 | 2025-06-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1120.95 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-17 | 2025-05-28 | Unknown | Unknown | 2025-05-28 | 2025-06-25 | 29 | 21 | 2025-06-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-18 | 2024-10-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1446.93 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-18 | 2024-10-17 | Unknown | Unknown | 2024-10-17 | 2024-10-18 | 2 | 2 | 2024-10-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SOLANA BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-23 |  | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1707.63 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-23 | 2024-08-23 | 1 | 1 | 2024-08-23 | 2024-08-23 | 1 | 1 | 2024-08-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-11 | 2025-03-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2051.23 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-11 | 2025-03-14 | 4 | 4 | 2025-03-14 | 2025-03-14 | 1 | 1 | 2025-03-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 6.05 | 6.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-13 | 2024-08-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1289.22 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-13 | 2024-08-28 | 16 | 12 | 2024-08-28 | 2024-08-28 | 1 | 1 | 2024-08-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-28 | Unknown | Unknown | Unknown | Unknown | 2025-08-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-27 | 2023-11-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3662 | 635.74 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-27 | 2023-11-27 | 1 | 1 | 2023-11-27 | 2023-12-07 | 11 | 9 | 2023-12-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | LAGUNA NIGUEL | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-20 | 2024-12-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1319.3 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-20 | 2024-12-20 | 1 | 1 | 2024-12-20 | 2024-12-20 | 1 | 1 | 2024-12-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | 2518 | 2518 | Not Available | >2MW | No | N/A | N/A | N/A | 2026-03-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-14 | 2024-05-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1023.78 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-14 | 2024-10-07 | 147 | 105 | 2024-10-07 | 2024-10-07 | 1 | 1 | 2024-10-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 10 | 10 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-28 | 2025-04-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 821.95 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-28 | 2025-04-24 | 28 | 20 | 2025-04-24 | 2025-04-24 | 1 | 1 | 2025-04-24 | 2025-04-28 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | 2025-04-28 | Unknown | Unknown | Unknown | Unknown | 2025-08-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | 6 | 6 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-12 | 2023-10-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 288.14 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-12 | 2023-08-11 | Unknown | Unknown | 2023-08-11 | 2023-11-29 | 111 | 79 | 2023-11-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-28 | 2024-10-28 | 2025-02-25 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 4079.07 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-28 | 2024-10-28 | 1 | 1 | 2024-10-28 | 2025-01-10 | 75 | 55 | 2024-12-30 | 2024-12-31 | 2 | 2 | 2024-12-31 | 2025-01-24 | 25 | 19 | 2025-01-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-14 | 2024-02-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 27365 | 344.88 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-14 | 2023-09-14 | Unknown | Unknown | 2023-09-14 | 2024-02-14 | 154 | 110 | 2024-02-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | 262 | 262 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-24 | 2024-07-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 5838.12 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-24 | 2024-04-24 | Unknown | Unknown | 2024-04-24 | 2025-03-26 | 337 | 241 | Unknown | Unknown | Unknown | Unknown | 2024-07-26 | 2024-08-28 | 34 | 24 | 2025-03-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-05 | 2025-03-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2160.88 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-05 | 2025-03-05 | 1 | 1 | 2025-03-05 | 2025-03-05 | 1 | 1 | 2025-03-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-05 | 2025-07-14 | 132 | 94 | Unknown | Unknown | Unknown | Unknown | 2025-07-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-28 | 2023-03-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1545.12 | Unknown | Unknown | Yes | N/A | N/A | 2023-02-28 | 2023-03-20 | 21 | 15 | 2023-03-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | CARDIFF | ENCINITAS | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-12 | 2025-05-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1077.51 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-12 | 2025-05-30 | 19 | 15 | 2025-05-30 | 2025-05-30 | 1 | 1 | 2025-05-30 | Unknown | Unknown | Unknown | 2025-05-30 | 2025-08-07 | 70 | 50 | 2025-05-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-08 | 2024-08-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 33635 | 5186.02 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-08 | 2024-04-11 | 4 | 4 | 2024-04-11 | 2025-01-22 | 287 | 205 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | CARLSBAD | CARLSBAD | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-18 | 2023-09-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 31848 | 39091.56 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-18 | 2023-03-17 | Unknown | Unknown | 2023-03-17 | 2024-10-22 | 586 | 418 | 2023-09-18 | 2024-01-22 | 33 | 23 | 2023-12-20 | 2025-08-29 | -385 | -280 | 2024-10-22 | Unknown | Unknown | Unknown | 2024-11-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2021-06-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-14 | 2023-03-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 161027 | 9310.26 | Unknown | Unknown | Yes | N/A | N/A | 2022-12-14 | 2023-03-21 | 98 | 70 | 2023-03-21 | 2025-02-27 | 710 | 508 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-08-05 | Unknown | Unknown | 2025-08-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-11-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-28 | 2025-02-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1221.55 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-28 | 2025-02-21 | Unknown | Unknown | 2025-02-21 | 2025-02-28 | 8 | 6 | 2025-02-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-28 | 2025-08-21 | 175 | 125 | Unknown | Unknown | Unknown | Unknown | 2025-08-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-17 | 2025-03-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2745.79 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-17 | 2025-04-15 | 30 | 22 | 2025-04-15 | 2025-05-02 | 18 | 14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-02 | Unknown | Unknown | Unknown | Unknown | 2025-08-12 | Unknown | Unknown | 2025-08-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | VALLEY CENTER | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-08 | 2023-11-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 839.24 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-08 | 2023-11-15 | 8 | 6 | 2023-11-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 14.05 | 14.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-02 | 2024-10-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3961 | 1158.4 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-02 | 2024-10-23 | 22 | 16 | 2024-10-23 | 2024-10-25 | 3 | 3 | 2024-10-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | OH | Applicant Design | Residential | N/A | San Diego | San Diego | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-17 | 2024-12-17 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 16545.3 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-17 | 2025-02-10 | 56 | 40 | 2025-02-10 | 2025-06-02 | 113 | 81 | 2025-02-13 | 2025-08-07 | 141 | 102 | 2025-06-05 | 2025-07-24 | 50 | 36 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 287.05 | 287.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-24 | 2023-10-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 809.55 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-24 | 2023-09-06 | Unknown | Unknown | 2023-09-06 | 2023-10-24 | 49 | 35 | 2023-10-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-05 | 2025-03-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2875.23 | 885.08 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-05 | 2025-03-03 | 27 | 19 | 2025-03-03 | 2025-03-12 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | el cajon | EL CAJON | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-11 | 2025-02-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 12531.44 | 26672.92 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-11 | 2024-12-06 | Unknown | Unknown | 2024-12-06 | 2025-06-18 | 195 | 139 | Unknown | Unknown | Unknown | Unknown | 2025-03-13 | 2025-07-29 | 126 | 88 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | EL CAJON | EL CAJON | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-02 | 2024-01-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1015.53 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-02 | 2023-05-26 | Unknown | Unknown | 2023-05-26 | 2024-03-07 | 287 | 205 | Unknown | Unknown | Unknown | Unknown | 2024-01-23 | 2024-01-30 | 8 | 6 | 2024-03-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | OCEANSIDE | 37.45 | 37.45 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-07 | 2025-01-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 3420 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-07 | 2025-01-13 | 99 | 71 | 2025-01-13 | 2025-01-13 | 1 | 1 | 2025-01-13 | 2025-04-09 | 87 | 63 | 2025-01-13 | 2025-02-14 | 33 | 25 | 2025-04-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | Applicant Design | Commercial | Underserved Community | San Diego | San Diego | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-07 | 2023-08-09 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 1732253.22 | 112984.07 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-07 | 2024-12-10 | 523 | 373 | 2024-12-10 | 2025-05-28 | 170 | 122 | 2024-12-16 | 2025-03-04 | 79 | 57 | 2025-04-25 | 2025-05-16 | 22 | 16 | 2025-05-28 | Unknown | Unknown | Unknown | 2025-06-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-20 | 2023-04-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1068.63 | Unknown | Unknown | Yes | N/A | N/A | 2023-04-20 | 2023-04-20 | 1 | 1 | 2023-04-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | ALPINE | ALPINE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2021-12-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-25 | 2024-02-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 52268 | 2850.93 | Unknown | Unknown | Yes | N/A | N/A | 2023-05-25 | 2024-04-15 | 327 | 233 | 2024-04-15 | 2024-08-14 | 122 | 88 | Unknown | Unknown | Unknown | Unknown | 2024-04-26 | 2024-05-15 | 20 | 14 | 2024-08-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-15 | 2022-08-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3508.22 | Unknown | Unknown | Yes | N/A | N/A | 2022-08-15 | 2024-08-27 | 744 | 532 | 2024-08-27 | 2025-02-10 | 168 | 120 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-29 | 2024-10-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2152.35 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-29 | 2024-10-29 | 1 | 1 | 2024-10-29 | 2025-01-16 | 80 | 58 | Unknown | Unknown | Unknown | Unknown | 2024-11-09 | 2024-12-12 | 34 | 24 | 2025-01-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 7.05 | 7.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-18 | 2024-11-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1590.34 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-18 | 2024-11-05 | Unknown | Unknown | 2024-11-05 | 2024-11-19 | 15 | 11 | 2024-11-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 67.05 | 67.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-21 | 2025-01-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2813.93 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-21 | 2025-01-29 | 9 | 7 | 2025-01-29 | 2025-02-19 | 22 | 16 | 2025-02-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 34.05 | 34.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-29 | 2024-05-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7962 | 1353.17 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-29 | 2024-09-13 | 138 | 100 | 2024-09-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-18 | 2023-09-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 33409 | 2713.24 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-18 | 2024-04-16 | 212 | 152 | 2024-04-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 39 | 39 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-11 | 2024-12-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3941 | 2967.8 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-11 | 2024-12-30 | 20 | 14 | 2024-12-30 | 2024-12-30 | 1 | 1 | 2024-12-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 358.15 | 358.15 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-29 | 2024-08-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 69470.24 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-29 | 2025-02-15 | 202 | 145 | 2025-02-15 | 2025-05-15 | 90 | 64 | 2025-04-30 | 2025-06-24 | 47 | 33 | 2025-04-01 | 2025-06-27 | 24 | 14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-28 | 2025-04-04 | 2025-04-09 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1952.43 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-28 | 2025-04-04 | 8 | 6 | 2025-04-04 | 2025-04-04 | 1 | 1 | 2025-04-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-04 | 2025-04-09 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2025-04-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | EL CAJON | EL CAJON | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-11 | 2023-07-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 484.94 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-11 | 2023-07-27 | 17 | 13 | 2023-07-27 | 2023-08-09 | 14 | 10 | 2023-08-01 | 2024-08-23 | 389 | 279 | 2023-07-18 | 2023-08-01 | 15 | 11 | 2023-08-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SOUTH LAGUNA | N/A | 92485 | 92485 | Not Available | >2MW | No | N/A | N/A | N/A | 2026-12-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-18 | 2025-02-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1231.32 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-18 | 2025-02-13 | Unknown | Unknown | 2025-02-13 | 2025-03-12 | 28 | 20 | 2025-03-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-07 | 2025-05-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 344.44 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-07 | 2025-05-07 | 1 | 1 | 2025-05-07 | 2025-06-10 | 35 | 25 | Unknown | Unknown | Unknown | Unknown | 2025-05-07 | 2025-05-23 | 17 | 13 | 2025-06-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 12 | 12 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-24 | 2025-06-25 | 2025-06-26 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1035.19 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-24 | 2025-06-05 | Unknown | Unknown | 2025-06-05 | 2025-06-25 | 21 | 15 | 2025-06-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-25 | 2025-06-26 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2025-06-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | N/A | 62 | 62 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-05 | 2024-07-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3649.6 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-05 | 2024-06-06 | Unknown | Unknown | 2024-06-06 | 2024-11-06 | 154 | 110 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 12 | 12 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-10 | 2024-04-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 903.42 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-10 | 2024-01-24 | Unknown | Unknown | 2024-01-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | JULIAN | COUNTY OF SAN DIEGO-NORTH of 56 | 67.05 | 67.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-06 | 2024-10-03 | 2025-06-27 | IOU Designed & Installed | N/A | No | Unknown | 5852.47 | 0 | Unknown | Unknown | 364.52 | 5487.95 | 3981 | 1479.96 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-06 | 2024-11-01 | 57 | 41 | 2024-11-01 | 2024-11-01 | 1 | 1 | 2024-11-01 | Unknown | Unknown | Unknown | 2024-11-05 | 2024-11-13 | 9 | 7 | 2024-11-15 | 2025-06-27 | 225 | 161 | Unknown | 2025-06-26 | Unknown | Unknown | 2025-06-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-23 | 2024-11-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1063.08 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-23 | 2024-11-11 | 20 | 14 | 2024-11-11 | 2025-03-04 | 114 | 82 | Unknown | Unknown | Unknown | Unknown | 2024-10-24 | 2024-11-26 | 34 | 24 | 2025-03-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-10 | 2025-03-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 33677 | 13788.73 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-10 | 2025-06-18 | 101 | 73 | 2025-06-18 | 2025-06-24 | 7 | 5 | 2025-04-14 | 2025-04-14 | 1 | 1 | 2025-06-04 | 2025-07-14 | 40 | 28 | 2025-06-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-18 | 2025-01-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2635.3 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-18 | 2024-01-07 | Unknown | Unknown | 2024-01-07 | 2025-05-05 | 485 | 346 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-05 | 2025-08-18 | 106 | 76 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 80 | 80 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-27 | 2025-03-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2232.98 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-27 | 2025-03-21 | 23 | 17 | 2025-03-21 | 2025-03-21 | 1 | 1 | 2025-03-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | Lakeside | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-23 | 2024-10-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 168541.43 | 67044.74 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-23 | 2024-09-26 | 66 | 48 | 2024-09-26 | 2025-04-22 | 209 | 149 | 2024-12-12 | 2024-12-19 | 8 | 6 | 2025-01-07 | 2025-04-29 | 31 | 23 | 2025-04-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-11 | 2025-06-11 | 2025-06-27 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1377.71 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-11 | 2025-06-12 | 2 | 2 | 2025-06-12 | 2025-06-19 | 8 | 6 | 2025-06-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-19 | 2025-06-27 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | 2025-06-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | N/A | Rancho Mission Viejo | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-19 | 2023-12-19 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 276671.11 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-19 | 2024-04-18 | 122 | 88 | 2024-04-18 | 2025-01-29 | 287 | 205 | 2024-07-09 | 2025-07-10 | 195 | 137 | 2024-09-06 | 2025-01-03 | 120 | 86 | 2025-04-11 | Unknown | Unknown | Unknown | 2025-04-11 | 2025-07-01 | 82 | 58 | 2025-07-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-10 | 2025-01-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 9150 | 525.43 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-10 | 2024-10-24 | Unknown | Unknown | 2024-10-24 | 2025-01-10 | 79 | 57 | 2025-01-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 96.05 | 96.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-25 | 2024-12-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1190.98 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-25 | 2024-12-06 | 12 | 10 | 2024-12-06 | 2024-12-06 | 1 | 1 | 2024-12-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-08 | 2024-05-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 11895 | 584.27 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-08 | 2024-05-08 | 1 | 1 | 2024-05-08 | 2024-05-08 | 1 | 1 | 2024-05-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-13 | 2025-07-30 | 444 | 318 | Unknown | Unknown | Unknown | Unknown | 2025-07-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | 4 | 4 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-25 | 2024-10-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3773.46 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-25 | 2024-10-25 | 1 | 1 | 2024-10-25 | 2024-12-26 | 63 | 45 | Unknown | Unknown | Unknown | Unknown | 2024-10-27 | 2024-11-26 | 31 | 22 | 2024-12-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | Applicant Design | Residential | Disadvantaged Community,Underserved Community | San Diego | CALTRANS-SOUTH of 56, SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-20 | 2023-09-20 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 326230.32 | 101212.48 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-20 | 2024-06-10 | 265 | 189 | 2024-06-10 | 2024-11-07 | 151 | 109 | 2024-01-22 | 2025-09-05 | 105 | 77 | 2024-04-03 | 2025-06-20 | 406 | 286 | 2024-11-07 | Unknown | Unknown | Unknown | 2024-11-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-07-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-08 | 2023-02-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 25294 | 852.98 | Unknown | Unknown | Yes | N/A | N/A | 2023-02-08 | 2023-02-08 | 1 | 1 | 2023-02-08 | 2023-02-17 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SOLANA BEACH | SOLANA BEACH | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-21 | 2023-06-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 991.44 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-21 | 2023-06-21 | 1 | 1 | 2023-06-21 | 2023-06-26 | 6 | 4 | 2023-06-26 | Unknown | Unknown | Unknown | 2023-06-26 | 2023-07-06 | 11 | 9 | 2023-06-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | RA 1152-E7 creekside WO1 (E) | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-15 | 2024-08-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2024-08-15 | 2024-08-17 | 3 | 2 | 2024-08-17 | 2025-04-28 | 255 | 181 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | NATIONAL CITY | N/A | 39.05 | 39.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-13 | 2025-03-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2013.22 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-13 | 2025-02-26 | Unknown | Unknown | 2025-02-26 | 2025-03-13 | 16 | 12 | 2025-03-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-13 | 2025-07-30 | 140 | 100 | Unknown | Unknown | Unknown | Unknown | 2025-07-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 40.8 | 40.8 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-29 | Unknown | Unknown | No | 2024-08-21 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-21 | 2024-09-20 | 2024-12-09 | IOU Designed & Installed | N/A | Yes | 61 | 1355.05 | 0 | Unknown | Unknown | Unknown | 1355.05 | 3981 | 1488.98 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-21 | 2024-10-21 | 62 | 44 | 2024-10-21 | 2024-09-20 | Unknown | Unknown | 2024-09-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-20 | 2024-12-09 | 81 | 57 | Unknown | 2024-12-06 | Unknown | Unknown | 2024-12-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 149.05 | 149.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-05 | Unknown | Unknown | No | 2025-04-11 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-11 | 2025-04-11 | Unknown | IOU Designed & Installed | N/A | Yes | 91 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1049.4 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-11 | 2025-07-03 | 84 | 60 | 2025-07-03 | 2025-07-11 | 9 | 7 | 2025-07-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-02 | 2025-07-15 | 44 | 32 | Unknown | Unknown | Unknown | Unknown | 2025-07-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-19 | 2025-05-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 512.75 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-19 | 2025-06-11 | 24 | 18 | 2025-06-11 | 2025-06-20 | 10 | 8 | 2025-06-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-20 | 2025-08-07 | 49 | 35 | Unknown | 2025-07-15 | Unknown | Unknown | 2025-08-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Residential | N/A | EN 1147-D7 OSUNA (E) | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2021-09-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-23 | 2023-10-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 13950.68 | 11282.11 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-23 | 2023-09-19 | 28 | 20 | 2023-09-19 | 2024-07-03 | 289 | 207 | 2024-06-28 | 2024-07-01 | 4 | 2 | 2024-07-02 | 2024-07-12 | 11 | 9 | 2024-07-12 | Unknown | Unknown | Unknown | 2024-07-12 | 2025-06-27 | 351 | 251 | 2025-07-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | Underserved Community | Chula Vista | CHULA VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-14 | 2022-09-14 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2673132.68 | 227849.35 | Unknown | Unknown | Yes | N/A | N/A | 2022-09-14 | 2023-08-07 | 328 | 234 | 2023-08-07 | 2024-07-23 | 352 | 252 | 2023-08-23 | 2025-09-09 | 320 | 229 | 2024-06-05 | 2024-08-27 | 84 | 60 | 2025-01-07 | Unknown | Unknown | Unknown | 2025-01-07 | 2025-09-09 | 246 | 176 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-27 | 2024-04-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1874.47 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-27 | 2023-10-18 | 22 | 16 | 2023-10-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 73.05 | 73.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-06 | 2025-01-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 934.41 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-06 | 2025-01-24 | 19 | 15 | 2025-01-24 | 2025-01-24 | 1 | 1 | 2025-01-24 | 2025-02-25 | 33 | 23 | Unknown | Unknown | Unknown | Unknown | 2025-02-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-11 | 2023-05-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 168746 | 5627.82 | Unknown | Unknown | Yes | N/A | N/A | 2023-04-11 | 2023-05-16 | 36 | 26 | 2023-05-16 | 2024-02-23 | 284 | 204 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-23 | 2025-07-16 | 510 | 364 | Unknown | 2025-07-16 | Unknown | Unknown | 2025-07-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | ALPINE | N/A | 137.05 | 137.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-28 | 2023-06-28 | 2025-01-02 | IOU Designed & Installed | N/A | No | Unknown | 1183.32 | 0 | Unknown | Unknown | 133.63 | 1049.69 | 3981 | 790.48 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-28 | 2023-05-04 | Unknown | Unknown | 2023-05-04 | 2023-07-25 | 83 | 59 | 2023-07-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-25 | 2025-01-02 | 528 | 378 | Unknown | 2024-12-17 | Unknown | Unknown | 2025-01-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-13 | 2025-02-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 10833.59 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-13 | 2024-10-22 | Unknown | Unknown | 2024-10-22 | 2025-04-04 | 165 | 119 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 53.05 | 53.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-04 | 2025-01-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 685.55 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-04 | 2024-12-10 | Unknown | Unknown | 2024-12-10 | 2025-01-06 | 28 | 20 | 2025-01-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 5.12 | 5.12 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-07-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-05 | 2023-10-05 | 2024-04-17 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 499.18 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-05 | 2023-07-10 | Unknown | Unknown | 2023-07-10 | 2023-12-18 | 162 | 116 | 2023-12-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-18 | 2024-04-17 | 122 | 88 | Unknown | 2024-04-16 | Unknown | Unknown | 2024-04-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-21 | 2025-06-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1638.38 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-21 | 2025-06-13 | 24 | 18 | 2025-06-13 | 2025-06-24 | 12 | 8 | 2025-06-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-24 | 2025-07-09 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | 2025-07-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 38 | 38 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-06 | 2024-11-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1032.11 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-06 | 2024-11-21 | 16 | 12 | 2024-11-21 | 2024-11-21 | 1 | 1 | 2024-11-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SPRING VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-06 | 2024-03-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 569539 | 2558.16 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-06 | 2024-08-08 | 156 | 112 | 2024-08-08 | 2024-08-14 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-22 | 2024-01-31 | 2024-02-14 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2033.46 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-22 | 2024-01-30 | 9 | 7 | 2024-01-30 | 2024-01-30 | 1 | 1 | 2024-01-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-31 | 2024-02-14 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2024-02-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 270 | 270 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-25 | 2024-07-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1074.83 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-25 | 2024-08-12 | 19 | 13 | 2024-08-12 | 2024-08-14 | 3 | 3 | 2024-08-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-10 | 2024-08-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2061159.1 | 188862.95 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-10 | 2023-07-31 | 22 | 16 | 2023-07-31 | 2025-05-08 | 648 | 464 | 2024-08-16 | 2025-05-07 | 123 | 89 | 2024-12-18 | 2025-05-20 | 46 | 34 | 2025-05-08 | Unknown | Unknown | Unknown | 2025-07-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | 100.05 | 100.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-13 | 2024-08-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1050.75 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-13 | 2024-08-14 | 2 | 2 | 2024-08-14 | 2024-08-14 | 1 | 1 | 2024-08-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 47.05 | 47.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-02 | 2024-05-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 648.41 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-02 | 2024-03-27 | Unknown | Unknown | 2024-03-27 | 2024-05-02 | 37 | 27 | 2024-05-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN MARCOS | N/A | 128.8 | 128.8 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-23 | 2025-04-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2045.73 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-23 | 2025-03-30 | Unknown | Unknown | 2025-03-30 | 2025-04-23 | 25 | 18 | 2025-04-23 | 2025-05-20 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | 2025-04-23 | Unknown | Unknown | Unknown | Unknown | 2025-09-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | 19 | 19 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-24 | Unknown | Unknown | No | 2025-01-17 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-17 | 2025-01-17 | 2025-06-18 | IOU Designed & Installed | N/A | Yes | 48 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2576.82 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-17 | 2025-03-06 | 49 | 35 | 2025-03-06 | 2025-01-22 | Unknown | Unknown | 2025-01-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-22 | 2025-06-18 | 148 | 106 | Unknown | Unknown | Unknown | Unknown | 2025-06-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-23 | 2024-09-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 358424 | 17590.68 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-23 | 2024-09-23 | 1 | 1 | 2024-09-23 | 2024-11-25 | 64 | 46 | Unknown | Unknown | Unknown | Unknown | 2024-10-24 | 2024-12-03 | 41 | 29 | 2024-11-25 | 2025-09-09 | 289 | 207 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SANTEE | SANTEE | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-12 | 2023-09-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1819.78 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-12 | 2024-12-06 | 452 | 324 | 2024-12-06 | 2024-12-26 | 21 | 15 | 2024-01-12 | 2024-07-16 | 187 | 133 | 2023-10-04 | 2024-07-24 | 110 | 80 | 2024-12-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | N/A | 18 | 18 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-19 | 2025-06-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 800.51 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-19 | 2025-06-24 | 6 | 4 | 2025-06-24 | 2025-06-24 | 1 | 1 | 2025-06-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-24 | 2025-09-03 | 72 | 52 | Unknown | Unknown | Unknown | Unknown | 2025-09-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | CHULA VISTA | 5.4 | 5.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-07 | 2025-01-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7962 | 1852.28 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-07 | 2025-01-07 | 1 | 1 | 2025-01-07 | 2025-02-11 | 36 | 26 | Unknown | Unknown | Unknown | Unknown | 2025-01-22 | 2025-02-05 | 15 | 11 | 2025-02-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-30 | 2024-10-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2572.13 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-30 | 2024-11-08 | 10 | 8 | 2024-11-08 | 2024-12-17 | 40 | 28 | Unknown | Unknown | Unknown | Unknown | 2024-11-14 | 2024-12-18 | 35 | 25 | 2024-12-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-08-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | 242 | 242 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-20 | 2025-02-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2158.81 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-20 | 2025-01-31 | Unknown | Unknown | 2025-01-31 | 2025-02-20 | 21 | 15 | 2025-02-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 92.1 | 92.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-14 | 2023-09-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 724.88 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-14 | 2023-09-15 | 2 | 2 | 2023-09-15 | 2023-09-15 | 1 | 1 | 2023-09-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2020-02-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-21 | 2023-06-21 | 2023-07-24 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1109.32 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-21 | 2023-06-21 | 1 | 1 | 2023-06-21 | 2023-06-30 | 10 | 8 | 2023-06-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-30 | 2023-07-24 | 25 | 17 | Unknown | Unknown | Unknown | Unknown | 2023-07-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | POWAY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-07 | 2024-08-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1526.1 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-07 | 2024-08-06 | Unknown | Unknown | 2024-08-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2026-03-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-06 | 2024-03-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 54899 | 81.53 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-06 | 2024-08-16 | 164 | 118 | 2024-08-16 | 2024-08-20 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | 2024-03-20 | 2024-07-24 | 55 | 41 | 2024-08-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-27 | 2024-07-31 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 4996.16 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-27 | 2024-07-31 | 309 | 221 | 2024-07-31 | 2024-10-14 | 76 | 54 | Unknown | Unknown | Unknown | Unknown | 2025-02-11 | 2025-02-11 | 1 | 1 | 2024-10-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 153.1 | 153.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-09 | 2024-07-15 | 2025-03-03 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1976.58 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-09 | 2024-07-15 | 7 | 5 | 2024-07-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-30 | 2025-03-03 | 217 | 155 | Unknown | 2024-08-19 | Unknown | Unknown | 2025-03-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | ENCINITAS | ENCINITAS | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-27 | 2024-11-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 34256.34 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-27 | 2024-08-28 | 2 | 2 | 2024-08-28 | 2025-04-04 | 220 | 158 | Unknown | Unknown | Unknown | Unknown | 2025-03-08 | 2025-05-02 | 43 | 29 | 2025-04-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | OH | IOU Design | Residential | Underserved Community | POTRERO | COUNTY OF SAN DIEGO-SOUTH of 56 | 146.05 | 146.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-27 | 2024-08-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2607.36 | 47963.46 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-27 | 2024-10-24 | 59 | 43 | 2024-10-24 | 2025-06-02 | 222 | 158 | 2025-01-17 | 2025-05-27 | 131 | 93 | 2024-10-24 | 2025-06-13 | 24 | 18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | BOULEVARD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-08 | 2024-10-08 | 2025-01-30 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1505.78 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-08 | 2024-10-07 | Unknown | Unknown | 2024-10-07 | 2024-10-08 | 2 | 2 | 2024-10-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-08 | 2025-01-30 | 115 | 83 | Unknown | Unknown | Unknown | Unknown | 2025-01-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | JULIAN | N/A | 22 | 22 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-24 | 2025-06-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 674.38 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-24 | 2025-06-05 | Unknown | Unknown | 2025-06-05 | 2025-07-01 | 27 | 19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-07-01 | 2025-08-26 | 57 | 41 | Unknown | 2025-08-12 | Unknown | Unknown | 2025-08-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | BONITA | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-20 | 2024-12-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1698.05 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-20 | 2024-11-21 | 2 | 2 | 2024-11-21 | 2025-02-28 | 100 | 72 | 2025-02-28 | Unknown | Unknown | Unknown | 2024-12-06 | 2024-12-17 | 12 | 8 | 2024-12-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-27 | 2025-04-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1841.04 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-27 | 2025-04-10 | 43 | 31 | 2025-04-10 | 2025-04-16 | 7 | 5 | 2025-04-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 25.4 | 25.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-29 | 2025-06-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 992.7 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-29 | 2025-06-18 | 51 | 37 | 2025-06-18 | 2025-06-18 | 1 | 1 | 2025-06-18 | 2025-06-18 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2025-06-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 68.05 | 68.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-28 | 2025-04-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 800.17 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-28 | 2025-04-22 | Unknown | Unknown | 2025-04-22 | 2025-04-30 | 9 | 7 | 2025-04-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-12 | Unknown | Unknown | No | 2023-10-05 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-05 | 2023-10-27 | Unknown | IOU Designed & Installed | N/A | Yes | 25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3661.75 | 1113.38 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-05 | 2023-10-30 | 26 | 18 | 2023-10-30 | 2023-10-27 | Unknown | Unknown | 2023-10-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-13 | 2024-05-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 997.19 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-13 | 2024-02-13 | Unknown | Unknown | 2024-02-13 | 2024-07-22 | 161 | 115 | Unknown | Unknown | Unknown | Unknown | 2024-07-09 | 2024-08-09 | 32 | 24 | 2024-07-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | OCEANSIDE | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2024-09-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-22 | 2024-10-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3753.77 | 473.47 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-22 | 2025-05-29 | 220 | 158 | 2025-05-29 | 2025-06-16 | 19 | 13 | Unknown | Unknown | Unknown | Unknown | 2025-04-29 | 2025-05-28 | 30 | 22 | 2025-06-16 | 2025-08-08 | 54 | 40 | Unknown | 2025-08-19 | Unknown | Unknown | 2025-08-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Commercial | Underserved Community | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-10 | 2025-02-10 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 7627.07 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-10 | 2025-05-28 | 108 | 78 | 2025-05-28 | 2025-07-29 | 63 | 45 | 2025-05-28 | 2025-05-28 | 1 | 1 | 2025-03-05 | 2025-03-18 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN MARCOS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-11 | 2025-04-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 520.78 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-11 | 2025-04-07 | Unknown | Unknown | 2025-04-07 | 2025-07-08 | 93 | 67 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-07-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-07-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 63.05 | 63.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-30 | 2025-06-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1070.17 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-30 | 2025-05-24 | Unknown | Unknown | 2025-05-24 | 2025-06-16 | 24 | 16 | 2025-06-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-05 | 2023-12-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 36349.88 | 698.37 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-05 | 2023-12-05 | 1 | 1 | 2023-12-05 | 2024-03-18 | 105 | 75 | 2024-03-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-11 | 2025-03-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 515.73 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-11 | 2025-04-10 | 31 | 23 | 2025-04-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-12 | 2025-03-25 | 14 | 10 | 2025-06-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-12 | 2023-12-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 153.49 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-12 | 2023-12-12 | 1 | 1 | 2023-12-12 | 2023-12-12 | 1 | 1 | 2023-12-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LAGUNA NIGUEL | N/A | 431.05 | 431.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-26 | 2025-02-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2869.64 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-26 | 2025-03-26 | 29 | 21 | 2025-03-26 | 2025-04-03 | 9 | 7 | 2025-04-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-03 | 2025-07-08 | 97 | 69 | Unknown | Unknown | Unknown | Unknown | 2025-07-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | Both | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 91791 | 91791 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-09-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-18 | 2024-09-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 93898 | 28656.88 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-18 | 2024-06-18 | 1 | 1 | 2024-06-18 | 2024-12-18 | 184 | 132 | 2024-08-29 | 2024-09-18 | 21 | 15 | 2024-11-19 | 2025-01-08 | 51 | 37 | 2024-12-18 | Unknown | Unknown | Unknown | 2025-01-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 141.99 | 141.99 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-07 | 2024-08-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1236.82 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-07 | 2024-04-25 | Unknown | Unknown | 2024-04-25 | 2024-12-10 | 230 | 164 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 8 | 8 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-12 | Unknown | Unknown | No | 2022-10-27 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-27 | 2022-10-27 | Unknown | IOU Designed & Installed | N/A | Yes | 137 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 910.33 | Unknown | Unknown | Yes | N/A | N/A | 2022-10-27 | 2023-03-13 | 138 | 98 | 2023-03-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 67.05 | 67.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-07 | 2024-03-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 755.54 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-07 | 2024-04-25 | 50 | 36 | 2024-04-25 | 2024-04-25 | 1 | 1 | 2024-04-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | LAKESIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-15 | 2024-08-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 1786 | 2851.31 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-15 | 2024-08-15 | 1 | 1 | 2024-08-15 | 2024-08-15 | 1 | 1 | 2024-08-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | OH | IOU Design | Residential | N/A | Dana Point | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-13 | 2024-02-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 37726.47 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-13 | 2024-01-16 | Unknown | Unknown | 2024-01-16 | 2024-11-11 | 301 | 215 | Unknown | Unknown | Unknown | Unknown | 2024-10-31 | 2024-11-05 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 1577.8 | 1577.8 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2025-07-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-08 | 2024-04-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1258.96 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-08 | 2024-02-28 | Unknown | Unknown | 2024-02-28 | 2024-04-16 | 49 | 35 | 2024-04-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN YSIDRO | SAN DIEGO | 102 | 102 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-30 | 2025-05-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1671.34 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-30 | 2025-05-12 | 225 | 161 | 2025-05-12 | 2025-05-20 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | 2025-05-07 | 2025-05-23 | 17 | 13 | 2025-05-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN JUAN CAPISTRANO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-29 | 2025-05-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2935.26 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-29 | 2025-06-11 | 14 | 10 | 2025-06-11 | 2025-06-20 | 10 | 8 | 2025-06-11 | 2025-06-11 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2025-06-20 | 2025-08-05 | 47 | 33 | Unknown | 2025-09-08 | Unknown | Unknown | 2025-08-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-25 | 2024-02-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 958.86 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-25 | 2024-02-26 | 33 | 23 | 2024-02-26 | 2024-02-26 | 1 | 1 | 2024-02-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-24 | 2024-06-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1665.03 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-24 | 2024-06-28 | 36 | 26 | 2024-06-28 | 2024-06-28 | 1 | 1 | 2024-06-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CARDIFF | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-10 | 2022-11-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 98.41 | Unknown | Unknown | Yes | N/A | N/A | 2022-11-10 | 2023-02-24 | 107 | 77 | 2023-02-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 29 | 29 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-31 |  | 2024-10-23 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1834.9 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-31 | 2024-07-31 | 1 | 1 | 2024-07-31 | 2024-07-31 | 1 | 1 | 2024-07-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-31 | 2024-10-23 | 85 | 61 | Unknown | Unknown | Unknown | Unknown | 2024-10-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | ALPINE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-29 | 2024-01-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3885 | 746.52 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-29 | 2024-02-05 | 8 | 6 | 2024-02-05 | 2024-02-05 | 1 | 1 | 2024-02-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | EL CAJON | N/A | 107.05 | 107.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-23 | 2024-07-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | -446.18 | 0 | Unknown | Unknown | 68 | -514.18 | 3981 | 196.44 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-23 | 2024-06-27 | Unknown | Unknown | 2024-06-27 | 2024-08-02 | 37 | 27 | 2024-08-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-02 | Unknown | Unknown | Unknown | Unknown | 2025-05-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 106.4 | 106.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-29 | 2024-08-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 609.71 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-29 | 2024-08-09 | 12 | 10 | 2024-08-09 | 2024-08-09 | 1 | 1 | 2024-08-09 | 2025-01-13 | 158 | 112 | Unknown | Unknown | Unknown | Unknown | 2025-01-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | RAMONA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-04 | 2025-02-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 519.08 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-04 | 2025-02-05 | 2 | 2 | 2025-02-05 | 2025-03-20 | 44 | 32 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-06-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-19 | 2025-06-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1495.23 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-19 | 2025-06-17 | Unknown | Unknown | 2025-06-17 | 2025-06-20 | 4 | 4 | 2025-06-20 | Unknown | Unknown | Unknown | 2025-06-20 | 2025-07-09 | 20 | 14 | 2025-06-19 | 2025-08-28 | 71 | 51 | Unknown | Unknown | Unknown | Unknown | 2025-08-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | 28 | 28 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-20 | 2024-03-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 287.96 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-20 | 2024-06-17 | 90 | 64 | 2024-06-17 | 2024-09-05 | 81 | 59 | Unknown | Unknown | Unknown | Unknown | 2024-08-27 | 2024-09-30 | 35 | 25 | 2024-09-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | POWAY | POWAY | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2024-12-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-26 | 2024-03-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 18157 | 34567.71 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-26 | 2024-02-22 | Unknown | Unknown | 2024-02-22 | 2024-11-26 | 279 | 199 | 2024-02-26 | 2024-04-15 | 50 | 36 | 2024-04-16 | 2025-08-27 | 216 | 146 | 2024-11-26 | 2025-02-13 | 80 | 58 | 2024-12-03 | 2025-07-22 | 232 | 166 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | N/A | 130.05 | 130.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-11 | 2024-02-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7962 | 500.71 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-11 | 2024-01-10 | Unknown | Unknown | 2024-01-10 | 2024-03-08 | 59 | 43 | Unknown | Unknown | Unknown | Unknown | 2025-05-07 | 2025-07-18 | 73 | 53 | 2024-03-08 | 2025-07-07 | 487 | 347 | Unknown | 2025-08-20 | Unknown | Unknown | 2025-09-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-22 | 2025-02-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 600 | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2023-08-22 | 2025-02-19 | 548 | 392 | 2025-02-19 | 2025-04-09 | 50 | 36 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-09 | 2958465 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2020-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-25 | 2025-03-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 608.75 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-25 | 2025-04-01 | 8 | 6 | 2025-04-01 | 2025-06-16 | 77 | 55 | Unknown | Unknown | Unknown | Unknown | 2025-04-08 | 2025-04-25 | 18 | 14 | 2025-06-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | CHULA VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-16 | 2023-08-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 480.37 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-16 | 2023-08-16 | 1 | 1 | 2023-08-16 | 2023-08-16 | 1 | 1 | 2023-08-16 | Unknown | Unknown | Unknown | 2024-02-29 | 2024-03-08 | 9 | 7 | 2023-08-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | CHULA VISTA | 46 | 46 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-06 | 2024-12-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 11943 | 1615.89 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-06 | 2024-12-05 | Unknown | Unknown | 2024-12-05 | 2025-07-14 | 222 | 158 | Unknown | Unknown | Unknown | Unknown | 2024-12-20 | 2025-01-07 | 19 | 13 | 2025-07-14 | 2025-06-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-08-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-27 | 2025-05-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 117.42 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-27 | 2025-08-08 | 74 | 54 | 2025-08-08 | 2025-08-08 | 1 | 1 | 2025-08-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-09 | 2025-08-27 | 80 | 58 | Unknown | Unknown | Unknown | Unknown | 2025-08-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 103.05 | 103.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-02 | 2025-04-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2638.46 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-02 | 2025-03-19 | Unknown | Unknown | 2025-03-19 | 2025-04-02 | 15 | 11 | 2025-04-02 | 2025-04-04 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2025-04-04 | Unknown | Unknown | Unknown | Unknown | 2025-04-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 43.05 | 43.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-12 | 2024-12-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1647.2 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-12 | 2025-01-02 | 52 | 38 | 2025-01-02 | 2025-05-19 | 138 | 98 | Unknown | Unknown | Unknown | Unknown | 2025-02-26 | 2025-03-18 | 21 | 15 | 2025-05-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-17 | 2024-04-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 15320.5 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-17 | 2024-04-23 | 7 | 5 | 2024-04-23 | 2024-05-23 | 31 | 23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 60 | 60 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-07 | 2025-02-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1241.46 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-07 | 2025-02-21 | 15 | 11 | 2025-02-21 | 2025-02-24 | 4 | 2 | 2025-02-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SOUTH LAGUNA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-18 | 2024-03-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 308.87 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-18 | 2024-03-18 | 1 | 1 | 2024-03-18 | 2024-03-18 | 1 | 1 | 2024-03-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 396 | 396 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-20 | 2025-03-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 33635 | 946.49 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-20 | 2025-05-31 | 73 | 52 | 2025-05-31 | 2025-06-05 | 6 | 4 | 2025-03-26 | 2025-06-02 | 69 | 49 | 2025-03-20 | 2025-04-03 | 15 | 11 | 2025-06-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 108 | 108 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-20 | 2024-08-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1567.34 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-20 | 2024-08-15 | Unknown | Unknown | 2024-08-15 | 2024-08-22 | 8 | 6 | 2024-08-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-14 | 2024-04-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 979.92 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-14 | 2024-02-05 | Unknown | Unknown | 2024-02-05 | 2024-04-08 | 64 | 46 | 2024-04-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CAPISTRANO BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-10 | 2025-03-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1815.59 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-10 | 2025-03-13 | 4 | 4 | 2025-03-13 | 2025-03-19 | 7 | 5 | 2025-03-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-15 | 2024-08-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 28804 | 494.79 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-15 | 2024-08-22 | 8 | 6 | 2024-08-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-16 | 2024-09-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 19905 | 730.53 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-16 | 2024-07-23 | 8 | 6 | 2024-07-23 | 2025-01-03 | 165 | 119 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LEMON GROVE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-10 | 2023-03-07 | 2023-09-22 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 363.72 | Unknown | Unknown | Yes | N/A | N/A | 2023-01-10 | 2023-03-07 | 57 | 41 | 2023-03-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-09 | 2023-09-22 | 198 | 142 | Unknown | Unknown | Unknown | Unknown | 2023-09-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-13 | 2025-06-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1190.38 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-13 | 2025-06-16 | 4 | 2 | 2025-06-16 | 2025-06-26 | 11 | 9 | 2025-06-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-26 | 2025-07-02 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2025-07-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2018-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-09 | 2023-02-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 47.04 | Unknown | Unknown | Yes | N/A | N/A | 2023-02-09 | 2023-02-09 | 1 | 1 | 2023-02-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | 62 | 62 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-21 | 2025-01-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1009.47 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-21 | 2025-01-08 | Unknown | Unknown | 2025-01-08 | 2025-01-23 | 16 | 12 | 2025-01-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-23 | Unknown | Unknown | Unknown | Unknown | 2025-04-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | LA JOLLA | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-03 | 2024-09-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 125833 | 56522 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-03 | 2024-12-02 | 91 | 65 | 2024-12-02 | 2025-05-08 | 158 | 114 | 2025-03-20 | 2025-03-20 | 1 | 1 | 2025-04-08 | 2025-05-12 | 23 | 17 | 2025-05-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | 70.05 | 70.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-14 | 2024-06-14 | 2025-06-04 | IOU Designed & Installed | N/A | No | Unknown | 1336.72 | 0 | Unknown | Unknown | 14.87 | 1321.85 | 0 | 1150.65 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-14 | 2024-06-14 | 1 | 1 | 2024-06-14 | 2024-06-25 | 12 | 8 | 2024-06-25 | 2025-03-19 | 268 | 192 | Unknown | Unknown | Unknown | Unknown | 2024-06-25 | 2025-06-04 | 345 | 247 | Unknown | 2025-05-29 | Unknown | Unknown | 2025-06-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2027-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-22 | 2023-09-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 1827193 | 6427.14 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-22 | 2023-10-05 | 14 | 10 | 2023-10-05 | 2023-10-17 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | San Diego | San Diego | 32 | 32 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-29 | 2025-02-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 11724.04 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-29 | 2024-08-20 | Unknown | Unknown | 2024-08-20 | 2025-05-20 | 274 | 196 | Unknown | Unknown | Unknown | Unknown | 2025-04-16 | 2025-05-21 | 28 | 20 | 2025-05-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | COUNTY OF SAN DIEGO-NORTH of 56 | 98.05 | 98.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-29 | 2024-07-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1605.25 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-29 | 2024-08-02 | 66 | 48 | 2024-08-02 | 2024-08-09 | 8 | 6 | 2024-08-09 | Unknown | Unknown | Unknown | 2024-08-12 | 2024-08-20 | 9 | 7 | 2024-08-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-28 | 2025-04-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2014.84 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-28 | 2025-04-01 | 5 | 3 | 2025-04-01 | 2025-04-03 | 3 | 3 | 2025-04-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | N/A | San Diego | San Diego | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-21 | 2023-11-21 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 60308.57 | 19580.46 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-21 | 2024-05-01 | 163 | 117 | 2024-05-01 | 2025-05-19 | 384 | 274 | 2024-05-08 | 2025-04-28 | 61 | 43 | 2024-06-19 | 2025-08-05 | 112 | 80 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-21 | 2023-06-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2856.39 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-21 | 2023-06-21 | 1 | 1 | 2023-06-21 | 2025-04-18 | 668 | 478 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 19.5 | 19.5 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-10 | 2025-04-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 798.93 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-10 | 2025-05-09 | 30 | 22 | 2025-05-09 | 2025-05-09 | 1 | 1 | 2025-05-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | Both | IOU Design | Commercial | N/A | San Diego | SAN DIEGO | 40000 | 40000 | Not Available | >2MW | No | N/A | N/A | N/A | 2025-12-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-02 | 2024-08-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2680756 | 435426.46 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-02 | 2023-11-29 | Unknown | Unknown | 2023-11-29 | 2025-03-19 | 477 | 341 | 2024-12-04 | 2025-03-13 | 2 | 2 | 2025-01-23 | 2025-08-13 | 129 | 93 | 2025-03-19 | Unknown | Unknown | Unknown | 2025-04-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-11 | 2024-12-11 | 2024-12-11 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1899.81 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-11 | 2024-12-09 | Unknown | Unknown | 2024-12-09 | 2024-12-11 | 3 | 3 | 2024-12-11 | Unknown | Unknown | Unknown | 2024-12-11 | 2025-01-27 | 48 | 34 | 2024-12-11 | 2024-12-11 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-12-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | IMPERIAL BEACH | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-27 | Unknown | Unknown | No | 2025-02-18 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-18 | 2025-02-18 | 2025-06-05 | IOU Designed & Installed | N/A | Yes | 2 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1899.5 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-18 | 2025-02-20 | 3 | 3 | 2025-02-20 | 2025-02-20 | 1 | 1 | 2025-02-20 | Unknown | Unknown | Unknown | 2025-02-18 | 2025-05-06 | 78 | 56 | 2025-02-18 | 2025-06-05 | 108 | 78 | Unknown | Unknown | Unknown | Unknown | 2025-06-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | 41 | 41 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-03 | 2024-12-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 820.4 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-03 | 2024-12-11 | 9 | 7 | 2024-12-11 | 2024-12-11 | 1 | 1 | 2024-12-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | FALLBROOK | N/A | 2 | 2 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-10-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-16 | 2024-02-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 937.38 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-16 | 2024-01-18 | Unknown | Unknown | 2024-01-18 | 2024-02-16 | 30 | 22 | 2024-02-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 2608.05 | 2608.05 | Not Available | >2MW | No | N/A | N/A | N/A | 2027-03-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | 2025-04-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1044.55 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-07 | 2025-05-09 | 33 | 25 | 2025-05-09 | 2025-05-09 | 1 | 1 | 2025-05-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 98.05 | 98.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-11 | 2024-10-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 197.01 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-11 | 2024-10-08 | Unknown | Unknown | 2024-10-08 | 2024-10-22 | 15 | 11 | 2024-10-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | IOU Design | Commercial | Underserved Community | EL CAJON | EL CAJON | 10980 | 10980 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-08-24 | Unknown | Unknown | No | 2022-04-26 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-26 | 2022-05-19 | Unknown | IOU Designed & Installed | N/A | Yes | 1021 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 117812.05 | Unknown | Unknown | Yes | N/A | N/A | 2022-04-26 | 2024-04-13 | 719 | 514 | 2024-04-13 | 2025-04-01 | 354 | 252 | 2023-03-11 | 2025-03-26 | 306 | 216 | 2023-03-02 | 2025-07-09 | 162 | 116 | Unknown | Unknown | Unknown | Unknown | 2025-04-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | CARLSBAD | N/A | 16.05 | 16.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-24 | Unknown | Unknown | No | 2024-12-09 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-09 | 2024-12-09 | Unknown | IOU Designed & Installed | N/A | Yes | 214 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 117.46 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-09 | 2025-07-11 | 215 | 155 | 2025-07-11 | 2025-07-16 | 6 | 4 | 2025-07-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-14 | 2025-01-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 666.64 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-14 | 2025-02-13 | 31 | 23 | 2025-02-13 | 2025-03-21 | 37 | 27 | 2025-03-21 | Unknown | Unknown | Unknown | 2025-02-19 | 2025-03-07 | 17 | 13 | 2025-02-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-26 | 2024-08-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 27449 | 507.87 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-26 | 2024-09-24 | 30 | 22 | 2024-09-24 | 2024-09-24 | 1 | 1 | 2024-09-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | FALLBROOK | COUNTY OF SAN DIEGO-NORTH of 56 | 47 | 47 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-03 | 2023-05-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 815.18 | Unknown | Unknown | Yes | N/A | N/A | 2023-05-03 | 2023-05-03 | 1 | 1 | 2023-05-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-03 | 2023-05-16 | 14 | 10 | 2023-05-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 220 | 220 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-11 | 2025-06-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1243.11 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-11 | 2025-06-12 | 2 | 2 | 2025-06-12 | 2025-06-13 | 2 | 2 | 2025-06-11 | 2025-06-13 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2025-06-13 | 2025-07-10 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | 2025-07-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-07 | 2024-02-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 825.7 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-07 | 2023-12-01 | Unknown | Unknown | 2023-12-01 | 2024-02-09 | 71 | 51 | 2024-02-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | IMPERIAL BEACH | IMPERIAL BEACH | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2025-04-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-30 | 2024-05-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 468.05 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-30 | 2024-05-02 | 3 | 3 | 2024-05-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-30 | 2024-07-11 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-09 | 2024-05-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 12481 | 584.27 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-09 | 2024-04-18 | Unknown | Unknown | 2024-04-18 | 2024-05-09 | 22 | 16 | 2024-05-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | N/A | 23 | 23 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-13 | 2023-09-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 26860 | 861.13 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-13 | 2023-09-13 | 1 | 1 | 2023-09-13 | 2023-09-19 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-17 | 2023-04-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 13669 | 344.93 | Unknown | Unknown | Yes | N/A | N/A | 2023-04-17 | 2023-05-12 | 26 | 20 | 2023-05-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-10 | 2024-12-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3941 | 2280.01 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-10 | 2024-12-10 | 1 | 1 | 2024-12-10 | 2024-12-17 | 8 | 6 | 2024-12-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | DANA POINT | N/A | 235 | 235 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-14 | 2024-11-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 16028.81 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-14 | 2024-10-09 | Unknown | Unknown | 2024-10-09 | 2024-12-18 | 71 | 51 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-18 | 2025-07-22 | 217 | 155 | Unknown | 2025-07-28 | Unknown | Unknown | 2025-07-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | N/A | 174 | 174 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-07 | 2025-03-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 926.21 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-07 | 2025-03-03 | Unknown | Unknown | 2025-03-03 | 2025-03-07 | 5 | 5 | 2025-03-07 | 2025-04-22 | 47 | 33 | Unknown | Unknown | Unknown | Unknown | 2025-04-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-03 | 2024-04-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1026.98 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-03 | 2024-04-15 | 13 | 9 | 2024-04-15 | 2024-04-15 | 1 | 1 | 2024-04-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 70.05 | 70.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-17 | 2025-04-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2382.86 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-17 | 2025-03-28 | Unknown | Unknown | 2025-03-28 | 2025-04-30 | 34 | 24 | 2025-04-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-18 | 2025-01-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1930.84 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-18 | 2024-11-26 | 9 | 7 | 2024-11-26 | 2025-01-17 | 53 | 39 | 2025-01-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 358.15 | 358.15 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-10 | 2025-04-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2025-04-10 | 2025-02-10 | Unknown | Unknown | 2025-02-10 | 2025-05-16 | 96 | 70 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-15 | 2024-03-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1881.23 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-15 | 2024-07-18 | 126 | 90 | 2024-07-18 | 2024-10-15 | 90 | 64 | 2024-10-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 37.05 | 37.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-28 | 2025-02-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1448.41 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-28 | 2025-01-10 | Unknown | Unknown | 2025-01-10 | 2025-02-28 | 50 | 36 | 2025-02-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 8 | 8 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-07 | 2025-05-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 842.44 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-07 | 2025-05-09 | 3 | 3 | 2025-05-09 | 2025-05-21 | 13 | 9 | 2025-05-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | 35 | 35 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-27 | 2025-01-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2063 | 3023 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-27 | 2025-01-23 | Unknown | Unknown | 2025-01-23 | 2025-02-11 | 20 | 14 | Unknown | Unknown | Unknown | Unknown | 2025-01-28 | 2025-02-19 | 23 | 17 | 2025-02-11 | 2025-06-24 | 134 | 96 | Unknown | 2025-08-13 | Unknown | Unknown | 2025-09-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-24 | 2025-04-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 13729 | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2025-04-24 | 2025-04-24 | 1 | 1 | 2025-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-27 | 2025-06-13 | 18 | 14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-23 | 2024-02-23 | 2024-08-13 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1016.17 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-23 | 2024-01-04 | Unknown | Unknown | 2024-01-04 | 2024-02-23 | 51 | 37 | 2024-02-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-26 | 2024-08-13 | 170 | 122 | Unknown | Unknown | Unknown | Unknown | 2024-08-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-30 | 2025-02-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1213.24 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-30 | 2025-02-18 | 20 | 14 | 2025-02-18 | 2025-02-21 | 4 | 4 | 2025-02-21 | 2025-04-02 | 41 | 29 | Unknown | Unknown | Unknown | Unknown | 2025-04-02 | 2025-08-25 | 146 | 104 | Unknown | 2025-05-07 | Unknown | Unknown | 2025-08-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-21 | 2025-03-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1608.74 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-21 | 2025-03-21 | 1 | 1 | 2025-03-21 | 2025-03-25 | 5 | 3 | 2025-03-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-31 | 2023-06-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 753.52 | Unknown | Unknown | Yes | N/A | N/A | 2023-05-31 | 2023-06-01 | 2 | 2 | 2023-06-01 | 2023-06-20 | 20 | 14 | 2023-06-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Residential | Underserved Community | Chula Vista | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-05 | 2024-04-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2889473 | 16096.26 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-05 | 2024-04-03 | 59 | 43 | 2024-04-03 | 2025-06-26 | 450 | 322 | 2025-02-05 | 2025-06-23 | 61 | 43 | 2025-07-01 | 2025-07-08 | 8 | 6 | 2025-07-03 | Unknown | Unknown | Unknown | 2025-07-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | CARLSBAD | N/A | 25.05 | 25.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-25 | 2024-10-03 | 2025-06-30 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1711.47 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-25 | 2024-10-03 | 9 | 7 | 2024-10-03 | 2024-10-03 | 1 | 1 | 2024-10-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-03 | 2025-06-30 | 271 | 193 | Unknown | Unknown | Unknown | Unknown | 2025-06-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LAKESIDE | COUNTY OF SAN DIEGO-SOUTH of 56 | 21 | 21 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-23 | 2024-04-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1174.25 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-23 | 2024-08-01 | 101 | 73 | 2024-08-01 | 2024-09-11 | 42 | 30 | 2024-08-01 | 2024-08-02 | 2 | 2 | 2024-08-02 | 2024-08-05 | 4 | 2 | 2024-09-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-24 | 2023-03-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 978.87 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-24 | 2023-03-07 | Unknown | Unknown | 2023-03-07 | 2023-04-18 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | 2023-03-27 | 2023-04-05 | 10 | 8 | 2023-04-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2018-10-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2020-05-25 | 2020-05-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 17399 | 1681.87 | Unknown | Unknown | Yes | N/A | N/A | 2020-05-25 | 2024-09-03 | 1563 | 1117 | 2024-09-03 | 2024-12-05 | 94 | 68 | Unknown | Unknown | Unknown | Unknown | 2025-03-31 | 2025-04-09 | 10 | 8 | 2024-12-05 | 2025-08-05 | 244 | 174 | Unknown | 2025-06-26 | Unknown | Unknown | 2025-08-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-11 | 2023-08-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 746.46 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-11 | 2023-08-11 | 1 | 1 | 2023-08-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LAGUNA NIGUEL | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-18 | 2025-02-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1237.59 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-18 | 2025-04-07 | 49 | 35 | 2025-04-07 | 2025-04-08 | 2 | 2 | 2025-04-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-08 | 2025-08-26 | 141 | 101 | Unknown | Unknown | Unknown | Unknown | 2025-08-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-14 | 2023-07-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3998 | 555.26 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-14 | 2023-07-14 | 1 | 1 | 2023-07-14 | 2023-07-14 | 1 | 1 | 2023-07-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | RAMONA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-16 | 2024-04-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 842.4 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-16 | 2023-11-14 | Unknown | Unknown | 2023-11-14 | 2024-11-06 | 359 | 257 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R29/R45 | UG | IOU Design | Commercial | Underserved Community | LA MESA | LA MESA | 1216 | 1216 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2024-10-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-01 | 2024-08-14 | 2025-01-14 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 35967.38 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-01 | 2024-07-23 | 236 | 168 | 2024-07-23 | 2025-01-09 | 171 | 123 | 2024-09-06 | 2024-12-19 | 40 | 28 | 2024-11-14 | 2025-01-08 | 46 | 34 | 2025-01-09 | 2025-07-07 | 180 | 128 | Unknown | 2025-08-15 | Unknown | Unknown | 2025-01-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 91 | 91 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-01 | 2025-06-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1250.75 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-01 | 2025-04-29 | Unknown | Unknown | 2025-04-29 | 2025-06-12 | 45 | 33 | 2025-06-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-12 | 2025-09-03 | 84 | 60 | Unknown | Unknown | Unknown | Unknown | 2025-09-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | OCEANSIDE | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2024-09-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-11 | 2024-12-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3753.77 | 3178.22 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-11 | 2025-05-30 | 171 | 123 | 2025-05-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-01 | 2025-05-29 | 29 | 21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 14.05 | 14.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-10 | 2025-04-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1794.75 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-10 | 2025-04-09 | Unknown | Unknown | 2025-04-09 | 2025-04-10 | 2 | 2 | 2025-04-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-10 | 2025-09-05 | 149 | 107 | Unknown | Unknown | Unknown | Unknown | 2025-09-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-16 | 2024-09-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 60779.26 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-16 | 2024-09-02 | Unknown | Unknown | 2024-09-02 | 2025-06-05 | 277 | 199 | Unknown | Unknown | Unknown | Unknown | 2025-02-24 | 2025-05-21 | 53 | 39 | 2025-06-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ESCONDIDO | N/A | 101 | 101 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-10 | 2023-05-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 431.58 | Unknown | Unknown | Yes | N/A | N/A | 2023-05-10 | 2023-06-12 | 34 | 24 | 2023-06-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | Chula Vista | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-25 | 2025-02-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 130559 | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2025-02-25 | 2025-01-08 | Unknown | Unknown | 2025-01-08 | 2025-03-25 | 77 | 55 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | CAPISTRANO BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-08-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-21 | 2023-07-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 989.85 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-21 | 2023-07-21 | 1 | 1 | 2023-07-21 | 2023-08-17 | 28 | 20 | 2023-08-17 | 2023-08-17 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2023-08-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | EL CAJON | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-20 | 2024-06-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1121.43 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-20 | 2024-06-20 | 1 | 1 | 2024-06-20 | 2024-06-27 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2024-06-20 | 2024-06-28 | 9 | 7 | 2024-06-27 | 2025-06-18 | 357 | 255 | Unknown | Unknown | Unknown | Unknown | 2025-07-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 113.36 | 113.36 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-17 | 2024-10-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1706.42 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-17 | 2025-02-11 | 118 | 84 | 2025-02-11 | 2025-02-13 | 3 | 3 | 2025-02-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-13 | 2025-08-07 | 176 | 126 | Unknown | Unknown | Unknown | Unknown | 2025-08-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | 12 | 12 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-04 | 2025-03-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1689.27 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-04 | 2025-03-06 | 3 | 3 | 2025-03-06 | 2025-03-07 | 2 | 2 | 2025-03-04 | 2025-03-07 | 4 | 4 | Unknown | Unknown | Unknown | Unknown | 2025-03-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Commercial | N/A | Santee | Santee | 438 | 438 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-23 | 2025-01-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 104361 | 84262.95 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-23 | 2024-03-26 | 156 | 112 | 2024-03-26 | 2025-06-25 | 457 | 327 | 2024-06-10 | 2025-05-19 | 238 | 170 | 2025-01-15 | 2025-06-20 | 78 | 56 | 2025-07-01 | Unknown | Unknown | Unknown | 2025-07-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-31 | 2025-03-31 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 190.04 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-31 | 2025-04-08 | 9 | 7 | 2025-04-08 | 2025-04-08 | 1 | 1 | 2025-04-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-18 | 2023-08-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3885 | 1069.15 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-18 | 2023-08-24 | 7 | 5 | 2023-08-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 21.6 | 21.6 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-24 | 2024-09-24 | 2025-06-19 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 15924 | 1723.37 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-24 | 2024-08-12 | Unknown | Unknown | 2024-08-12 | 2025-03-25 | 226 | 162 | Unknown | Unknown | Unknown | Unknown | 2025-03-10 | 2025-03-21 | 12 | 10 | 2025-03-25 | 2025-05-07 | 44 | 32 | Unknown | Unknown | Unknown | Unknown | 2025-06-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-27 | 2023-09-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2023-09-27 | 2023-07-19 | Unknown | Unknown | 2023-07-19 | 2023-10-06 | 80 | 58 | 2023-10-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-17 | 2024-04-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 336409 | 10053.77 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-17 | 2024-04-17 | 1 | 1 | 2024-04-17 | 2024-05-29 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-10 | 2024-06-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 4455.38 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-10 | 2023-04-21 | Unknown | Unknown | 2023-04-21 | 2024-10-15 | 544 | 388 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 74.05 | 74.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-03 | 2025-02-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2057.01 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-03 | 2025-02-19 | 48 | 34 | 2025-02-19 | 2025-02-19 | 1 | 1 | 2025-02-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SANTEE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-02 | 2024-12-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1376.32 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-02 | 2024-11-14 | Unknown | Unknown | 2024-11-14 | 2025-01-16 | 64 | 46 | 2025-01-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 81 | 81 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-31 | 2024-12-31 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1282.69 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-31 | 2025-02-19 | 51 | 37 | 2025-02-19 | 2025-03-03 | 13 | 9 | 2025-03-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | IOU Design | Commercial | Underserved Community | San Diego | SAN DIEGO | 70 | 70 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-20 | 2023-10-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 268544 | 17413.56 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-20 | 2023-08-07 | 19 | 13 | 2023-08-07 | 2024-06-10 | 309 | 221 | 2024-01-06 | 2024-06-06 | 5 | 3 | 2024-01-17 | 2024-06-14 | 18 | 14 | 2024-06-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-25 | 2025-05-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 826.99 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-25 | 2025-05-01 | 7 | 5 | 2025-05-01 | 2025-05-01 | 1 | 1 | 2025-05-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-01 | 2025-09-02 | 125 | 89 | Unknown | 2025-09-02 | Unknown | Unknown | 2025-09-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | 9.05 | 9.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-22 | 2024-08-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1318.91 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-22 | 2024-08-14 | Unknown | Unknown | 2024-08-14 | 2024-08-14 | 1 | 1 | 2024-08-14 | 2024-12-31 | 140 | 100 | Unknown | Unknown | Unknown | Unknown | 2024-12-31 | 2025-07-23 | 205 | 147 | Unknown | 2025-05-23 | Unknown | Unknown | 2025-07-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-07 | 2024-03-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 829.96 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-07 | 2024-04-12 | 37 | 27 | 2024-04-12 | 2024-05-03 | 22 | 16 | 2024-05-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-03 | Unknown | Unknown | Unknown | Unknown | 2024-10-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-01 | 2023-12-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 163.83 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-01 | 2024-02-16 | 78 | 56 | 2024-02-16 | 2024-02-16 | 1 | 1 | 2024-02-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CARLSBAD | N/A | 14 | 14 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-16 | 2025-04-30 | 2025-06-03 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1318.42 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-16 | 2025-04-01 | Unknown | Unknown | 2025-04-01 | 2025-05-19 | 49 | 35 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-19 | 2025-07-28 | 71 | 51 | Unknown | Unknown | Unknown | Unknown | 2025-06-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | LAGUNA NIGUEL | N/A | 32 | 32 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-05-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-28 | 2023-07-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1987.53 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-28 | 2023-07-14 | Unknown | Unknown | 2023-07-14 | 2023-07-28 | 15 | 11 | 2023-07-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | 80.2 | 80.2 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-01 | 2024-11-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 11943 | 2204.33 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-01 | 2024-11-08 | 39 | 29 | 2024-11-08 | 2025-06-03 | 208 | 148 | Unknown | Unknown | Unknown | Unknown | 2024-12-27 | 2025-01-24 | 29 | 21 | 2025-06-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | CHULA VISTA | CHULA VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-17 | 2023-06-09 | 2025-05-07 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 74509.17 | Unknown | Unknown | Yes | N/A | N/A | 2023-05-17 | 2023-05-17 | 1 | 1 | 2023-05-17 | 2024-03-06 | 295 | 211 | 2023-10-12 | 2023-10-13 | 2 | 2 | 2023-11-01 | 2025-05-05 | 12 | 8 | 2024-03-06 | 2024-09-03 | 182 | 130 | 2024-04-19 | 2024-08-20 | 124 | 88 | 2025-05-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | OCEANSIDE | 6.35 | 6.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-22 | 2024-10-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1745.58 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-22 | 2024-10-28 | 7 | 5 | 2024-10-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-16 | 2025-01-31 | 16 | 12 | 2024-10-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 36 | 36 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-25 | 2024-01-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 364.48 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-25 | 2024-01-09 | Unknown | Unknown | 2024-01-09 | 2024-01-25 | 17 | 13 | 2024-01-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-08 | 2023-10-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 879.66 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-08 | 2023-11-20 | 74 | 52 | 2023-11-20 | 2023-11-20 | 1 | 1 | 2023-11-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | Underserved Community | Vista | VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-11 | 2024-04-11 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 60786.41 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-11 | 2025-02-18 | 314 | 224 | 2025-02-18 | 2025-06-27 | 130 | 94 | 2025-03-04 | 2025-06-17 | 86 | 60 | 2024-12-12 | 2025-06-23 | 90 | 64 | 2025-07-15 | Unknown | Unknown | Unknown | 2025-07-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 50 | 50 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-09 | 2024-05-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3961 | 1536.31 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-09 | 2024-08-23 | 107 | 77 | 2024-08-23 | 2024-09-05 | 14 | 10 | 2024-09-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | LAS FLORES | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-18 | 2023-08-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1111.21 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-18 | 2023-08-10 | Unknown | Unknown | 2023-08-10 | 2023-08-18 | 9 | 7 | 2023-08-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 8 | 8 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-10 | 2025-01-28 | 2025-03-05 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2005.8 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-10 | 2025-01-02 | Unknown | Unknown | 2025-01-02 | 2025-01-28 | 27 | 19 | 2025-01-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-28 | 2025-03-05 | 37 | 27 | Unknown | Unknown | Unknown | Unknown | 2025-03-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CHULA VISTA | N/A | 10 | 10 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-14 | 2025-03-14 | 2025-06-05 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1177.56 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-14 | 2025-03-18 | 5 | 3 | 2025-03-18 | 2025-03-18 | 1 | 1 | 2025-03-18 | 2025-03-27 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | 2025-03-27 | 2025-06-05 | 71 | 51 | Unknown | 2025-06-05 | Unknown | Unknown | 2025-06-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | OH | IOU Design | Commercial | Underserved Community | Pauma Valley | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-04 | 2024-12-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 6721 | 11729.29 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-04 | 2024-09-21 | Unknown | Unknown | 2024-09-21 | 2025-02-24 | 157 | 111 | Unknown | Unknown | Unknown | Unknown | 2025-02-14 | 2025-02-21 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 160 | 160 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-18 | Unknown | Unknown | No | 2024-09-17 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-17 | 2024-09-19 | 2025-03-06 | IOU Designed & Installed | N/A | Yes | 175 | 524.98 | 0 | Unknown | Unknown | 64.41 | 460.57 | 3981 | 1342.91 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-17 | 2025-03-11 | 176 | 126 | 2025-03-11 | 2024-10-09 | Unknown | Unknown | 2024-10-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-09 | 2025-03-06 | 149 | 107 | Unknown | 2025-03-10 | Unknown | Unknown | 2025-03-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | 47 | 47 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-06 | 2025-03-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 30021 | 1146.05 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-06 | 2025-03-06 | 1 | 1 | 2025-03-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | Applicant Design | Commercial | N/A | RANCHO MISSION VIEJO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-17 | 2025-04-17 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 675.06 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-17 | 2025-04-08 | Unknown | Unknown | 2025-04-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 26 | 26 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-10-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-26 | 2023-05-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 364057 | 32143.02 | Unknown | Unknown | Yes | N/A | N/A | 2023-05-26 | 2023-05-26 | 1 | 1 | 2023-05-26 | 2025-06-24 | 761 | 543 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-24 | 2025-06-18 | Unknown | Unknown | Unknown | 2025-07-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-10 | 2024-04-29 | 2024-05-13 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 942.51 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-10 | 2024-04-29 | 20 | 14 | 2024-04-29 | 2024-04-29 | 1 | 1 | 2024-04-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-29 | 2024-05-13 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2024-05-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | CORONADO | CORONADO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-29 |  | 2024-08-22 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1479.32 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-29 | 2024-07-29 | 1 | 1 | 2024-07-29 | 2024-07-29 | 1 | 1 | 2024-07-29 | Unknown | Unknown | Unknown | 2024-07-29 | 2024-08-09 | 12 | 10 | 2024-07-29 | 2024-08-22 | 25 | 19 | Unknown | Unknown | Unknown | Unknown | 2024-08-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 1999 | 1999 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2026-08-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-20 | 2024-09-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1485.09 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-20 | 2025-03-26 | 188 | 134 | 2025-03-26 | 2025-04-21 | 27 | 19 | 2025-04-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-18 | 2025-02-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1640.28 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-18 | 2025-02-18 | 1 | 1 | 2025-02-18 | 2025-02-18 | 1 | 1 | 2025-02-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-08 | 2025-05-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1455.77 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-08 | 2025-04-10 | Unknown | Unknown | 2025-04-10 | 2025-05-08 | 29 | 21 | 2025-05-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-08 | 2025-07-02 | 56 | 40 | Unknown | Unknown | Unknown | Unknown | 2025-07-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SANTEE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-06 | 2023-04-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3885 | 1454.35 | Unknown | Unknown | Yes | N/A | N/A | 2023-04-06 | 2023-04-06 | 1 | 1 | 2023-04-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | 9025 | 9025 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-07-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-08 | 2024-01-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 599.09 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-08 | 2023-10-16 | Unknown | Unknown | 2023-10-16 | 2025-07-01 | 625 | 447 | Unknown | Unknown | Unknown | Unknown | 2024-01-09 | 2024-01-19 | 11 | 9 | 2025-07-01 | 2025-06-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-08-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2021-02-28 | Unknown | Unknown | No | 2020-04-02 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2020-04-02 | 2020-04-02 | Unknown | IOU Designed & Installed | N/A | Yes | 1257 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 658.46 | Unknown | Unknown | Yes | N/A | N/A | 2020-04-02 | 2023-08-21 | 1237 | 883 | 2023-08-21 | 2023-09-11 | 22 | 16 | 2023-09-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-22 | 2023-06-22 | 2023-07-21 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 372.35 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-22 | 2023-07-14 | 23 | 17 | 2023-07-14 | 2023-07-14 | 1 | 1 | 2023-07-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-14 | 2023-07-21 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2023-07-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 3.35 | 3.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-31 | 2023-10-31 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3885 | 890.78 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-31 | 2023-10-31 | 1 | 1 | 2023-10-31 | 2023-10-31 | 1 | 1 | 2023-10-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | CARLSBAD | CARLSBAD | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-08-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-05 | 2023-09-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3754 | 376.49 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-05 | 2023-04-18 | Unknown | Unknown | 2023-04-18 | 2023-09-15 | 151 | 109 | 2023-09-15 | Unknown | Unknown | Unknown | 2023-10-26 | 2023-12-08 | 44 | 32 | 2023-09-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-02 | 2025-01-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | 886.25 | 0 | Unknown | Unknown | Unknown | 886.25 | 0 | 1275.29 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-02 | 2025-01-13 | 12 | 8 | 2025-01-13 | 2025-01-13 | 1 | 1 | 2025-01-13 | 2025-01-27 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2025-01-27 | Unknown | Unknown | Unknown | Unknown | 2025-03-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-10 | 2024-12-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 25673 | 5929.89 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-10 | 2024-12-19 | 10 | 8 | 2024-12-19 | 2025-05-07 | 140 | 100 | Unknown | Unknown | Unknown | Unknown | 2025-01-09 | 2025-01-28 | 20 | 14 | 2025-05-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 45.05 | 45.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-06 | 2024-02-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 6632.61 | 12955.81 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-06 | 2023-11-08 | 3 | 3 | 2023-11-08 | 2024-11-04 | 363 | 259 | 2024-06-28 | 2024-06-28 | 1 | 1 | 2024-06-17 | 2024-11-19 | 67 | 49 | 2024-11-04 | Unknown | Unknown | Unknown | 2025-06-30 | 2025-07-18 | 19 | 15 | 2025-08-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-25 | Unknown | Unknown | No | 2024-05-20 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-20 | 2024-05-20 | Unknown | IOU Designed & Installed | N/A | Yes | 331 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1477.54 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-20 | 2025-04-14 | 330 | 236 | 2025-04-14 | 2024-05-23 | Unknown | Unknown | 2024-05-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-08 | 2024-10-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2060.94 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-08 | 2024-09-17 | Unknown | Unknown | 2024-09-17 | 2024-10-08 | 22 | 16 | 2024-10-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | OH | IOU Design | Residential | Underserved Community | National City | NATIONAL CITY | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-03-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-19 | 2024-01-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 28727 | 71641.65 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-19 | 2024-01-19 | 1 | 1 | 2024-01-19 | Unknown | Unknown | Unknown | 2024-06-28 | 2025-04-28 | 300 | 214 | 2024-05-01 | 2025-03-12 | 104 | 76 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 45.05 | 45.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-06 | 2024-02-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7962 | 1150.43 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-06 | 2023-11-08 | 3 | 3 | 2023-11-08 | 2024-09-19 | 317 | 227 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-19 | 2024-07-09 | Unknown | Unknown | 2025-07-18 | Unknown | Unknown | Unknown | 2025-08-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-22 | 2024-04-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 32463.03 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-22 | 2024-03-01 | Unknown | Unknown | 2024-03-01 | 2025-01-09 | 315 | 225 | Unknown | Unknown | Unknown | Unknown | 2024-08-06 | 2024-12-30 | 45 | 33 | 2025-01-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-12 | 2024-11-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1204.68 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-12 | 2024-11-12 | 1 | 1 | 2024-11-12 | 2024-11-12 | 1 | 1 | 2024-11-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2018-05-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-17 | 2023-05-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 743.75 | Unknown | Unknown | Yes | N/A | N/A | 2023-05-17 | 2023-05-26 | 10 | 8 | 2023-05-26 | 2023-06-08 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Commercial | Underserved Community | Dana Point | DANA POINT | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-08-02 | Unknown | Unknown | No | 2024-02-22 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-24 | 2024-05-16 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | Yes | 84 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 45582.9 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-24 | 2025-02-12 | 386 | 276 | 2025-02-12 | 2025-05-30 | 108 | 78 | 2025-04-10 | 2025-04-16 | 7 | 5 | 2025-05-14 | 2025-07-22 | 61 | 43 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | Applicant Design | Commercial | Underserved Community | SAN MARCOS | COUNTY OF SAN DIEGO-NORTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-15 | 2023-11-15 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 88497 | 29513.66 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-15 | 2024-02-13 | 91 | 65 | 2024-02-13 | 2024-06-25 | 134 | 96 | 2024-03-20 | 2024-05-16 | 23 | 17 | 2024-03-22 | 2024-05-28 | 18 | 12 | 2024-06-25 | Unknown | Unknown | Unknown | 2024-07-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-07 | 2024-10-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1101.26 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-07 | 2024-09-25 | Unknown | Unknown | 2024-09-25 | 2024-10-18 | 24 | 18 | 2024-10-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 11.05 | 11.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-11 | 2024-09-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1225.52 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-11 | 2024-08-20 | Unknown | Unknown | 2024-08-20 | 2024-09-23 | 35 | 25 | 2024-09-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | Applicant Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-01-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-12 | 2023-04-12 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 31009.42 | Unknown | Unknown | Yes | N/A | N/A | 2023-04-12 | 2024-07-31 | 477 | 341 | 2024-07-31 | 2024-10-17 | 79 | 57 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | OH | IOU Design | Commercial | Disadvantaged Community,Underserved Community | national city | NATIONAL CITY | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-21 | 2023-11-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 26784 | 15402.93 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-21 | 2023-09-22 | 94 | 68 | 2023-09-22 | 2025-04-16 | 573 | 409 | 2025-04-08 | 2025-04-08 | 1 | 1 | 2024-02-22 | 2025-04-29 | 241 | 173 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-25 | 2023-10-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 828.88 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-25 | 2023-07-26 | Unknown | Unknown | 2023-07-26 | 2023-10-25 | 92 | 66 | 2023-10-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-31 | 2025-04-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2272.88 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-31 | 2025-04-11 | 12 | 10 | 2025-04-11 | 2025-04-21 | 11 | 7 | 2025-04-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-21 | 2025-07-23 | 94 | 68 | Unknown | Unknown | Unknown | Unknown | 2025-07-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-16 | 2025-06-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1312.09 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-16 | 2025-07-26 | 41 | 30 | 2025-07-26 | 2025-06-16 | Unknown | Unknown | 2025-06-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 1.35 | 1.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-26 | 2024-08-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | 517.78 | 0 | Unknown | Unknown | 14.54 | 503.24 | 3981 | 1197.39 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-26 | 2024-12-05 | 102 | 74 | 2024-12-05 | 2025-01-17 | 44 | 32 | 2025-01-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-17 | 2025-07-07 | 172 | 122 | Unknown | Unknown | Unknown | Unknown | 2025-07-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-15 | 2025-05-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1120.45 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-15 | 2025-05-21 | 7 | 5 | 2025-05-21 | 2025-05-21 | 1 | 1 | 2025-05-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-06-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-25 | 2025-06-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1182.61 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-25 | 2025-06-25 | 1 | 1 | 2025-06-25 | 2025-06-25 | 1 | 1 | 2025-06-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-23 | Unknown | Unknown | No | 2023-01-30 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-30 | 2023-01-30 | Unknown | IOU Designed & Installed | N/A | Yes | 46 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 893.08 | Unknown | Unknown | Yes | N/A | N/A | 2023-01-30 | 2023-03-17 | 47 | 35 | 2023-03-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-13 | 2024-12-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1713.42 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-13 | 2024-12-13 | 1 | 1 | 2024-12-13 | 2024-12-19 | 7 | 5 | 2024-12-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 70.05 | 70.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-22 | 2024-08-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1046.27 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-22 | 2024-09-05 | 15 | 11 | 2024-09-05 | 2024-09-05 | 1 | 1 | 2024-09-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-25 | 2024-07-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 6691 | 820.51 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-25 | 2024-07-25 | 1 | 1 | 2024-07-25 | 2024-08-01 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2024-09-30 | 2025-03-03 | 155 | 111 | 2024-08-01 | 2025-02-13 | 197 | 141 | Unknown | 2025-01-27 | Unknown | Unknown | 2025-07-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-28 | 2025-01-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1811.92 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-28 | 2025-01-28 | 1 | 1 | 2025-01-28 | 2025-01-28 | 1 | 1 | 2025-01-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-17 | 2024-11-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2855.22 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-17 | 2024-11-07 | 22 | 16 | 2024-11-07 | 2024-11-07 | 1 | 1 | 2024-11-07 | 2025-09-05 | 303 | 217 | Unknown | Unknown | Unknown | Unknown | 2025-01-03 | Unknown | Unknown | Unknown | Unknown | 2025-07-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-01-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-27 | 2024-03-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 566.39 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-27 | 2024-03-19 | Unknown | Unknown | 2024-03-19 | 2024-10-03 | 199 | 143 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-03 | Unknown | Unknown | Unknown | Unknown | 2025-07-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | CORONADO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-02 | 2023-11-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1067.53 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-02 | 2023-11-02 | 1 | 1 | 2023-11-02 | 2023-11-02 | 1 | 1 | 2023-11-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 51.55 | 51.55 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-22 | 2024-08-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1150.97 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-22 | 2024-09-30 | 40 | 28 | 2024-09-30 | 2024-09-30 | 1 | 1 | 2024-09-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-30 | Unknown | Unknown | Unknown | Unknown | 2025-06-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-24 | 2025-02-26 | 2025-02-27 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1663.66 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-24 | 2025-02-26 | 3 | 3 | 2025-02-26 | 2025-02-26 | 1 | 1 | 2025-02-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-26 | 2025-02-27 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2025-02-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | POWAY | N/A | 1062.05 | 1062.05 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2026-05-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-15 | 2024-08-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1312.5 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-15 | 2024-11-14 | 92 | 66 | 2024-11-14 | 2024-11-27 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-27 | Unknown | Unknown | Unknown | Unknown | 2025-06-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | LAGUNA NIGUEL | N/A | 8 | 8 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-31 | 2023-03-31 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 705.42 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-31 | 2023-04-13 | 14 | 10 | 2023-04-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | 334.05 | 334.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-15 | Unknown | Unknown | No | 2023-10-17 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-17 | 2023-10-17 | Unknown | IOU Designed & Installed | N/A | Yes | 111 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3941 | 934.62 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-17 | 2024-03-27 | 163 | 117 | 2024-03-27 | 2024-01-03 | Unknown | Unknown | 2024-01-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-28 | Unknown | Unknown | Unknown | Unknown | 2024-06-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-05 |  | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1603.8 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-05 | 2024-11-05 | 1 | 1 | 2024-11-05 | 2024-11-05 | 1 | 1 | 2024-11-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | IOU Design | Residential | Underserved Community | SAN MARCOS | SAN MARCOS | 137.05 | 137.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-13 | 2024-09-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 18599.63 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-13 | 2024-06-24 | Unknown | Unknown | 2024-06-24 | 2025-01-24 | 215 | 155 | 2024-09-18 | 2025-01-17 | 68 | 50 | 2025-01-24 | 2025-07-01 | 17 | 13 | 2025-01-24 | Unknown | Unknown | Unknown | 2025-02-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 101 | 101 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-20 | 2025-02-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1397.81 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-20 | 2025-01-30 | Unknown | Unknown | 2025-01-30 | 2025-02-24 | 26 | 18 | 2025-02-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-08 | 2024-08-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 28804 | 494.79 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-08 | 2024-08-22 | 15 | 11 | 2024-08-22 | 2024-08-22 | 1 | 1 | 2024-08-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 224.1 | 224.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-13 | Unknown | Unknown | No | 2023-07-05 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-05 | 2023-07-05 | 2024-07-23 | IOU Designed & Installed | N/A | Yes | 286 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 11943 | 795.16 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-05 | 2024-04-16 | 287 | 205 | 2024-04-16 | 2023-07-05 | Unknown | Unknown | 2023-07-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-05 | 2024-07-23 | 385 | 275 | Unknown | Unknown | Unknown | Unknown | 2024-07-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | 118.05 | 118.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-04 | 2024-02-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 952.69 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-04 | 2024-01-18 | 15 | 11 | 2024-01-18 | 2024-02-07 | 21 | 15 | 2024-02-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 50 | 50 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-08 | 2023-12-08 | 2024-02-06 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 4603.71 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-08 | 2023-12-08 | 1 | 1 | 2023-12-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-08 | 2024-02-06 | 61 | 43 | Unknown | Unknown | Unknown | Unknown | 2024-02-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-23 | 2024-09-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 362405 | 19104.56 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-23 | 2024-09-23 | 1 | 1 | 2024-09-23 | 2024-11-25 | 64 | 46 | Unknown | Unknown | Unknown | Unknown | 2024-10-24 | 2024-12-03 | 41 | 29 | 2024-11-25 | 2025-09-03 | 283 | 203 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 182.15 | 182.15 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-30 | 2023-08-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 462.42 | Unknown | Unknown | Yes | N/A | N/A | 2022-09-30 | 2023-08-15 | 320 | 228 | 2023-08-15 | 2023-08-15 | 1 | 1 | 2023-08-15 | 2023-08-21 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2023-08-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 140.05 | 140.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-04 | 2025-03-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1232.19 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-04 | 2025-02-25 | Unknown | Unknown | 2025-02-25 | 2025-03-27 | 31 | 23 | 2025-03-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-27 | 2025-09-03 | 161 | 115 | Unknown | 2025-08-13 | Unknown | Unknown | 2025-09-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-11 | 2024-12-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1376.32 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-11 | 2024-11-07 | Unknown | Unknown | 2024-11-07 | 2025-01-16 | 71 | 51 | 2025-01-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN YSIDRO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-25 | 2024-11-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 12452 | 2769.3 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-25 | 2024-04-25 | 1 | 1 | 2024-04-25 | 2024-12-12 | 232 | 166 | Unknown | Unknown | Unknown | Unknown | 2024-11-13 | 2024-12-17 | 35 | 25 | 2024-12-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | RANCHO MISSION VIEJO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-09 | 2025-05-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 450.24 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-09 | 2025-05-07 | Unknown | Unknown | 2025-05-07 | 2025-06-16 | 41 | 29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | 145.05 | 145.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-21 | 2025-01-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1164.94 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-21 | 2025-01-08 | Unknown | Unknown | 2025-01-08 | 2025-01-22 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | N/A | 260.5 | 260.5 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-10 | 2023-11-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2874.15 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-10 | 2023-11-16 | 7 | 5 | 2023-11-16 | 2024-02-21 | 98 | 70 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community,Tribal Community | Valley Center | N/A | 9 | 9 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-27 | 2025-02-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3694.25 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-27 | 2025-02-27 | 1 | 1 | 2025-02-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-21 | 2025-03-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1231.32 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-21 | 2025-03-06 | 380 | 272 | 2025-03-06 | 2025-03-13 | 8 | 6 | 2025-03-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SANTEE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-20 | 2023-06-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 495.75 | Unknown | Unknown | Yes | N/A | N/A | 2023-02-20 | 2023-06-23 | 124 | 90 | 2023-06-23 | 2023-06-23 | 1 | 1 | 2023-06-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | LAGUNA HILLS | N/A | 72.05 | 72.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-20 | 2023-06-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1828.93 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-20 | 2023-04-10 | Unknown | Unknown | 2023-04-10 | 2023-07-07 | 89 | 65 | 2023-07-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | DANA POINT | N/A | 2 | 2 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-19 | 2024-08-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 250.93 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-19 | 2024-08-19 | 1 | 1 | 2024-08-19 | 2024-08-19 | 1 | 1 | 2024-08-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-05 | 2024-08-05 | 2024-08-21 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 186.52 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-05 | 2024-08-05 | 1 | 1 | 2024-08-05 | 2024-08-05 | 1 | 1 | 2024-08-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-05 | 2024-08-21 | 17 | 13 | Unknown | Unknown | Unknown | Unknown | 2024-08-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-12 | 2025-03-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2922.37 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-12 | 2025-03-12 | 1 | 1 | 2025-03-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-15 | 2024-07-18 | 2024-07-22 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 192.51 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-15 | 2024-07-02 | Unknown | Unknown | 2024-07-02 | 2024-07-18 | 17 | 13 | 2024-07-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-18 | 2024-07-22 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | 2024-07-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-23 | 2023-04-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 153.75 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-23 | 2023-04-24 | 33 | 23 | 2023-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-05 | 2025-03-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 996.66 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-05 | 2025-03-04 | Unknown | Unknown | 2025-03-04 | 2025-03-27 | 24 | 18 | Unknown | Unknown | Unknown | Unknown | 2025-03-05 | 2025-03-18 | 14 | 10 | 2025-03-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2025-04-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-30 | 2024-04-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 466.88 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-30 | 2024-04-30 | 1 | 1 | 2024-04-30 | 2024-09-04 | 128 | 92 | Unknown | Unknown | Unknown | Unknown | 2024-05-17 | 2024-06-12 | 27 | 19 | 2024-09-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Commercial | Underserved Community | El Cajon | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2021-12-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-15 | 2022-11-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 24372 | 32325.96 | Unknown | Unknown | Yes | N/A | N/A | 2022-09-15 | 2023-05-16 | 244 | 174 | 2023-05-16 | 2024-05-01 | 352 | 252 | 2023-02-23 | 2023-06-12 | 13 | 9 | 2023-04-11 | 2024-05-09 | 19 | 15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | 55 | 55 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-18 | 2024-10-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 825.27 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-18 | 2024-10-18 | 1 | 1 | 2024-10-18 | 2024-10-18 | 1 | 1 | 2024-10-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-01 | 2024-07-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2535.2 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-01 | 2024-07-01 | 1 | 1 | 2024-07-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R29/R45 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN YSIDRO | SAN DIEGO | 180 | 180 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-15 | 2024-06-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 86075.88 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-15 | 2024-09-18 | 188 | 134 | 2024-09-18 | 2025-03-06 | 170 | 122 | 2024-08-12 | 2024-11-27 | 3 | 1 | 2024-10-03 | 2025-03-19 | 43 | 31 | 2025-03-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-04-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-01 | 2023-03-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 553.66 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-01 | 2023-03-02 | 2 | 2 | 2023-03-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-02 | 2023-10-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 754.4 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-02 | 2023-07-11 | Unknown | Unknown | 2023-07-11 | 2023-10-13 | 95 | 69 | 2023-10-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | ALPINE | COUNTY OF SAN DIEGO-SOUTH of 56 | 62.05 | 62.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-16 | 2024-01-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 596.38 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-16 | 2024-01-03 | Unknown | Unknown | 2024-01-03 | 2024-01-18 | 16 | 12 | 2024-01-18 | Unknown | Unknown | Unknown | 2024-01-18 | 2024-01-19 | 2 | 2 | 2024-01-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | Applicant Design | Commercial | Underserved Community | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2021-09-17 | 2021-09-17 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 1450716 | 66083.21 | Unknown | Unknown | Yes | N/A | N/A | 2021-09-17 | 2023-02-23 | 525 | 375 | 2023-02-23 | 2023-02-24 | 2 | 2 | 2022-11-08 | 2022-11-10 | 3 | 3 | 2023-02-28 | 2023-07-28 | 151 | 109 | 2023-02-24 | Unknown | Unknown | Unknown | Unknown | 2025-05-19 | Unknown | Unknown | 2025-07-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-01 | 2024-08-01 | 2025-06-06 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1081.55 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-01 | 2024-10-18 | 79 | 57 | 2024-10-18 | 2024-10-18 | 1 | 1 | 2024-10-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-18 | 2025-06-06 | 232 | 166 | Unknown | 2025-08-21 | Unknown | Unknown | 2025-06-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-28 | 2025-03-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1952.78 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-28 | 2025-03-20 | Unknown | Unknown | 2025-03-20 | 2025-03-28 | 9 | 7 | 2025-03-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SOLANA BEACH | N/A | 192.5 | 192.5 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-09 | 2024-08-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2277.61 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-09 | 2024-08-15 | 7 | 5 | 2024-08-15 | 2024-08-15 | 1 | 1 | 2024-08-15 | 2025-01-21 | 160 | 114 | Unknown | Unknown | Unknown | Unknown | 2025-01-21 | Unknown | Unknown | Unknown | Unknown | 2025-07-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 40.05 | 40.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-12 | 2024-10-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1788.47 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-12 | 2024-05-15 | Unknown | Unknown | 2024-05-15 | 2024-10-15 | 154 | 110 | 2024-10-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | 70 | 70 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-04 | 2024-03-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 141375 | 6312.4 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-04 | 2024-02-23 | Unknown | Unknown | 2024-02-23 | 2024-06-13 | 112 | 80 | 2024-04-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-27 | 2025-02-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1232.07 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-27 | 2025-05-20 | 83 | 59 | 2025-05-20 | 2025-05-20 | 1 | 1 | 2025-05-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 63 | 63 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-24 | 2025-06-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1034.96 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-24 | 2025-06-03 | Unknown | Unknown | 2025-06-03 | 2025-06-24 | 22 | 16 | 2025-06-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-24 | 2025-07-07 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | 2025-07-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | EL CAJON | N/A | 3 | 3 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-09 | 2023-11-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 787.91 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-09 | 2023-10-11 | Unknown | Unknown | 2023-10-11 | 2023-11-09 | 30 | 22 | 2023-11-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 1113.15 | 1113.15 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2024-05-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-29 | 2023-08-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7962 | 690.25 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-29 | 2023-08-17 | 50 | 36 | 2023-08-17 | 2023-09-07 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN MARCOS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-06 | 2024-06-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 4949.88 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-06 | 2024-06-06 | 1 | 1 | 2024-06-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN MARCOS | N/A | 64 | 64 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-04 | 2025-06-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2486.96 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-04 | 2025-06-16 | 13 | 9 | 2025-06-16 | 2025-06-24 | 9 | 7 | 2025-06-11 | 2025-06-16 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2025-06-24 | 2025-07-09 | 16 | 12 | Unknown | 2025-09-02 | Unknown | Unknown | 2025-07-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Commercial | Underserved Community | National city | NATIONAL CITY | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-13 | 2025-02-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 26942.87 | 5631.19 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-13 | 2024-09-06 | Unknown | Unknown | 2024-09-06 | 2025-06-30 | 298 | 212 | 2025-02-26 | 2025-06-24 | 90 | 64 | 2025-02-26 | 2025-07-15 | 106 | 76 | 2025-08-07 | Unknown | Unknown | Unknown | 2025-08-07 | 2025-07-31 | Unknown | Unknown | 2025-08-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 2.7 | 2.7 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-05 | 2024-02-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1349.24 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-05 | 2024-04-05 | 61 | 45 | 2024-04-05 | 2024-04-05 | 1 | 1 | 2024-04-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-06-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-20 | 2025-06-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1119.65 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-20 | 2025-06-24 | 5 | 3 | 2025-06-24 | 2025-06-26 | 3 | 3 | 2025-06-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-26 | 2025-07-07 | 12 | 8 | Unknown | Unknown | Unknown | Unknown | 2025-07-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-11 | 2025-05-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1082.33 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-11 | 2025-02-26 | Unknown | Unknown | 2025-02-26 | 2025-05-15 | 79 | 57 | 2025-05-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CARDIFF | N/A | 18.75 | 18.75 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-01 | 2025-01-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1197.39 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-01 | 2025-01-22 | 83 | 59 | 2025-01-22 | 2025-01-22 | 1 | 1 | 2025-01-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | LAKESIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-26 | 2025-03-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 622140 | 2314.45 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-26 | 2025-03-03 | 6 | 4 | 2025-03-03 | 2025-03-17 | 15 | 11 | 2025-03-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-25 | 2024-07-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 978.03 | Unknown | Unknown | Yes | N/A | N/A | 2023-05-25 | 2024-07-12 | 415 | 297 | 2024-07-12 | 2024-07-12 | 1 | 1 | 2024-07-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 22 | 22 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-06 | 2025-06-16 | 2025-06-17 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1067.09 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-06 | 2025-06-12 | 7 | 5 | 2025-06-12 | 2025-06-16 | 5 | 3 | 2025-06-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-16 | 2025-06-17 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2025-06-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN MARCOS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-31 | 2025-03-31 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1479.74 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-31 | 2025-03-31 | 1 | 1 | 2025-03-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-18 | 2025-02-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2501.01 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-18 | 2025-02-18 | 1 | 1 | 2025-02-18 | 2025-02-18 | 1 | 1 | 2025-02-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SPRING VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-02 | 2025-05-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 4172.88 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-02 | 2025-03-19 | Unknown | Unknown | 2025-03-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | 61 | 61 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-04 | 2024-09-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 4290.11 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-04 | 2024-08-19 | Unknown | Unknown | 2024-08-19 | 2025-03-19 | 213 | 153 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-05 | 2025-03-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1978.22 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-05 | 2025-03-04 | Unknown | Unknown | 2025-03-04 | 2025-03-17 | 14 | 10 | 2025-03-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 31.35 | 31.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-09 | 2025-04-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1930.16 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-09 | 2025-04-11 | 3 | 3 | 2025-04-11 | 2025-06-25 | 76 | 54 | 2025-06-25 | Unknown | Unknown | Unknown | 2025-04-29 | 2025-05-16 | 18 | 14 | 2025-06-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-14 | 2025-06-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1755.79 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-14 | 2025-06-23 | 41 | 29 | 2025-06-23 | 2025-06-23 | 1 | 1 | 2025-06-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-23 | 2025-08-01 | 40 | 30 | Unknown | Unknown | Unknown | Unknown | 2025-08-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | IOU Design | Commercial | Underserved Community | VS 1108-A5 (E) | VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-18 | 2024-06-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 46176 | 105085 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-18 | 2024-03-05 | Unknown | Unknown | 2024-03-05 | 2025-03-19 | 380 | 272 | 2024-10-17 | 2025-05-14 | 39 | 27 | 2024-08-05 | 2025-06-17 | 117 | 85 | 2025-03-19 | Unknown | Unknown | Unknown | 2025-04-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | EL CAJON | N/A | 2700 | 2700 | Not Available | >2MW | No | N/A | N/A | N/A | 2025-01-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-28 | 2025-02-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 116480 | 5349.19 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-28 | 2025-05-06 | 68 | 48 | 2025-05-06 | 2025-06-26 | 52 | 38 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | 91.35 | 91.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-31 | 2024-12-31 | 2025-06-11 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 11943 | 1497.73 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-31 | 2024-09-04 | Unknown | Unknown | 2024-09-04 | 2025-02-19 | 169 | 121 | Unknown | Unknown | Unknown | Unknown | 2025-02-13 | 2025-03-06 | 22 | 16 | 2025-02-19 | 2025-07-14 | 146 | 104 | Unknown | Unknown | Unknown | Unknown | 2025-06-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | DANA POINT | N/A | 5.4 | 5.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-30 | 2025-03-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1836.05 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-30 | 2025-02-25 | 119 | 85 | 2025-02-25 | 2025-03-04 | 8 | 6 | 2025-03-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-04 | 2025-07-15 | 134 | 96 | Unknown | Unknown | Unknown | Unknown | 2025-07-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 146.25 | 146.25 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-29 | 2025-04-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1300.84 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-29 | 2025-03-26 | 57 | 41 | 2025-03-26 | 2025-04-04 | 10 | 8 | 2025-04-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | Underserved Community | Lakeside | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-02 | 2024-04-02 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 16509.95 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-02 | 2024-10-09 | 191 | 137 | 2024-10-09 | 2025-01-22 | 106 | 76 | 2024-10-17 | 2025-01-21 | 95 | 67 | 2025-01-27 | 2025-02-03 | 8 | 6 | 2025-01-28 | Unknown | Unknown | Unknown | 2025-01-28 | 2025-02-06 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 1952.75 | 1952.75 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2026-12-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-15 | 2025-02-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1809.03 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-15 | 2025-01-15 | 1 | 1 | 2025-01-15 | 2025-02-13 | 30 | 22 | 2025-02-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 90.2 | 90.2 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-14 | 2025-03-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7962 | 2008.3 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-14 | 2025-02-03 | Unknown | Unknown | 2025-02-03 | 2025-03-14 | 40 | 30 | 2025-03-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | POWAY | N/A | 33004.05 | 33004.05 | Not Available | >2MW | No | N/A | N/A | N/A | 2026-12-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-07 | 2025-01-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1387.31 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-07 | 2025-01-31 | 25 | 19 | 2025-01-31 | 2025-06-27 | 148 | 106 | 2025-06-27 | 2025-06-27 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2025-02-03 | 2025-07-08 | 156 | 112 | Unknown | 2025-06-26 | Unknown | Unknown | 2025-07-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | San Diego | San Diego | 54 | 54 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-15 | 2024-05-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 135550.81 | 26131.39 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-15 | 2024-05-15 | 1 | 1 | 2024-05-15 | 2024-10-25 | 164 | 118 | 2024-07-02 | 2024-07-02 | 1 | 1 | 2024-08-23 | 2024-12-09 | 19 | 11 | 2024-10-25 | Unknown | Unknown | Unknown | 2024-10-30 | 2025-07-19 | 263 | 188 | 2025-08-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-11 | 2024-11-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2063 | 735.22 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-11 | 2024-11-06 | Unknown | Unknown | 2024-11-06 | 2025-01-28 | 84 | 60 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-28 | Unknown | Unknown | Unknown | Unknown | 2025-08-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-15 | 2024-11-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1965.24 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-15 | 2024-10-31 | Unknown | Unknown | 2024-10-31 | 2024-11-15 | 16 | 12 | 2024-11-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | 36.05 | 36.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-11 | 2023-04-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 751.92 | Unknown | Unknown | Yes | N/A | N/A | 2023-04-11 | 2023-04-12 | 2 | 2 | 2023-04-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 49.25 | 49.25 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-31 | 2023-10-31 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1362.05 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-31 | 2023-09-27 | Unknown | Unknown | 2023-09-27 | 2024-01-24 | 120 | 86 | 2024-01-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 137 | 137 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-09 | 2024-12-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2207.11 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-09 | 2025-01-06 | 29 | 21 | 2025-01-06 | 2025-01-24 | 19 | 15 | 2025-01-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 42.05 | 42.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-10 | Unknown | Unknown | No | 2024-02-13 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-13 | 2024-02-27 | Unknown | IOU Designed & Installed | N/A | Yes | 359 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1581.95 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-13 | 2024-12-12 | 304 | 218 | 2024-12-12 | 2025-02-11 | 62 | 44 | Unknown | Unknown | Unknown | Unknown | 2024-05-02 | 2024-06-03 | 33 | 23 | 2025-02-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | JAMUL | N/A | 68.05 | 68.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-13 | 2024-12-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1663.24 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-13 | 2024-12-09 | 27 | 19 | 2024-12-09 | 2024-12-09 | 1 | 1 | 2024-12-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-16 | 2025-04-16 | 2025-06-03 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1863.79 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-16 | 2025-03-21 | Unknown | Unknown | 2025-03-21 | 2025-04-16 | 27 | 19 | 2025-04-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-16 | 2025-06-03 | 49 | 35 | Unknown | Unknown | Unknown | Unknown | 2025-06-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 67.05 | 67.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-04 | 2025-03-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1791.15 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-04 | 2025-03-20 | 17 | 13 | 2025-03-20 | 2025-03-20 | 1 | 1 | 2025-03-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 98 | 98 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-30 | 2024-07-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1970.25 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-30 | 2024-04-25 | Unknown | Unknown | 2024-04-25 | 2024-07-17 | 84 | 60 | 2024-07-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | BORREGO SPRINGS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-16 | 2024-10-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 4511.8 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-16 | 2024-10-16 | 1 | 1 | 2024-10-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LEMON GROVE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-08 | 2025-01-08 | 2025-01-14 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1621.16 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-08 | 2025-01-08 | 1 | 1 | 2025-01-08 | 2025-01-08 | 1 | 1 | 2025-01-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-08 | 2025-01-14 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2025-01-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-16 | 2024-02-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1198.92 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-16 | 2024-02-16 | 1 | 1 | 2024-02-16 | 2024-02-16 | 1 | 1 | 2024-02-16 | Unknown | Unknown | Unknown | 2024-02-16 | 2024-02-27 | 12 | 8 | 2024-02-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CAMPO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-09 | Unknown | Unknown | No | 2023-11-16 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-16 | 2023-11-16 | Unknown | IOU Designed & Installed | N/A | Yes | 71 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 522.33 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-16 | 2024-01-26 | 72 | 52 | 2024-01-26 | 2023-11-16 | Unknown | Unknown | 2023-11-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 2003 | 2003 | Not Available | >2MW | No | N/A | N/A | N/A | 2027-02-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-14 | 2025-05-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 250.9 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-14 | 2025-05-29 | 16 | 12 | 2025-05-29 | 2025-05-29 | 1 | 1 | 2025-05-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-29 | 2025-07-17 | 50 | 36 | Unknown | Unknown | Unknown | Unknown | 2025-07-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 133.05 | 133.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-01 | 2025-04-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1841.04 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-01 | 2025-03-25 | Unknown | Unknown | 2025-03-25 | 2025-04-01 | 8 | 6 | 2025-04-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-02 | 2025-07-24 | 114 | 82 | Unknown | Unknown | Unknown | Unknown | 2025-07-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | RAMONA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-13 | 2025-03-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3891 | 1825.98 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-13 | 2025-04-22 | 41 | 29 | 2025-04-22 | 2025-04-22 | 1 | 1 | 2025-04-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | ESCONDIDO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-30 | 2025-04-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1453.36 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-30 | 2025-05-09 | 10 | 8 | 2025-05-09 | 2025-05-21 | 13 | 9 | 2025-05-21 | Unknown | Unknown | Unknown | 2025-05-21 | 2025-06-02 | 13 | 9 | 2025-05-21 | 2025-07-01 | 42 | 30 | Unknown | Unknown | Unknown | Unknown | 2025-07-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | ESCONDIDO | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-13 | 2023-04-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 732.43 | Unknown | Unknown | Yes | N/A | N/A | 2023-04-13 | 2023-04-29 | 17 | 12 | 2023-04-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | OH | IOU Design | Commercial | Underserved Community | Dulzura | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-21 | 2024-07-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 21972.31 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-21 | 2024-05-08 | 323 | 231 | 2024-05-08 | 2025-02-27 | 296 | 212 | Unknown | Unknown | Unknown | Unknown | 2025-02-28 | 2025-03-07 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | DANA POINT | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-02-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-01 | 2023-02-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 276.8 | Unknown | Unknown | Yes | N/A | N/A | 2023-02-01 | 2023-02-01 | 1 | 1 | 2023-02-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | Both | IOU Design | Commercial | Disadvantaged Community,Underserved Community | National City | NATIONAL CITY | 396 | 396 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-05-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-17 | 2023-08-31 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 68046.44 | 18807.88 | Unknown | Unknown | Yes | N/A | N/A | 2023-05-17 | 2023-05-25 | 9 | 7 | 2023-05-25 | 2024-08-15 | 449 | 321 | 2023-12-08 | 2024-08-06 | 74 | 54 | 2024-02-22 | 2025-01-31 | 191 | 139 | 2025-06-12 | Unknown | Unknown | Unknown | 2025-06-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-02 | 2025-04-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 212.65 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-02 | 2025-04-30 | 29 | 21 | 2025-04-30 | 2025-05-07 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-07 | 2025-07-30 | 85 | 61 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-07 | 2023-06-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2023-06-07 | 2023-06-13 | 7 | 5 | 2023-06-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | EL CAJON | N/A | 600 | 600 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-03-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-18 | 2024-07-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 16098.49 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-18 | 2025-03-03 | 229 | 163 | 2025-03-03 | 2025-03-27 | 25 | 19 | Unknown | Unknown | Unknown | Unknown | 2025-03-27 | 2025-03-27 | 1 | 1 | 2025-03-27 | 2025-05-19 | 54 | 38 | Unknown | 2025-06-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-08 | 2025-01-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1711.51 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-08 | 2024-12-27 | Unknown | Unknown | 2024-12-27 | 2025-01-22 | 27 | 19 | 2025-01-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | JAMUL | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-13 | 2023-10-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 647.99 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-13 | 2023-08-23 | Unknown | Unknown | 2023-08-23 | 2023-10-16 | 55 | 39 | 2023-10-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | CHULA VISTA | CHULA VISTA | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2022-12-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-08 | 2024-04-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 678.59 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-08 | 2024-04-08 | 1 | 1 | 2024-04-08 | 2024-06-13 | 67 | 49 | Unknown | Unknown | Unknown | Unknown | 2024-04-17 | 2024-06-04 | 49 | 35 | 2024-06-13 | 2025-05-02 | 324 | 232 | Unknown | 2025-04-24 | Unknown | Unknown | 2025-07-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | IOU Design | Commercial | N/A | RSF 1168-D3 | COUNTY OF SAN DIEGO-NORTH of 56 | 114 | 114 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-02-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-29 | 2022-08-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 59547.24 | 75013.88 | Unknown | Unknown | Yes | N/A | N/A | 2022-08-29 | 2023-06-20 | 296 | 212 | 2023-06-20 | 2024-09-20 | 459 | 329 | 2023-08-16 | 2024-09-12 | 70 | 50 | 2024-01-22 | 2025-01-09 | 21 | 17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN JUAN CAPISTRANO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-16 | 2023-05-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1982.06 | Unknown | Unknown | Yes | N/A | N/A | 2023-05-16 | 2023-07-07 | 53 | 39 | 2023-07-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-07 | Unknown | Unknown | Unknown | Unknown | 2023-10-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 777.05 | 777.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-25 | 2025-06-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1049.71 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-25 | 2025-07-02 | 8 | 6 | 2025-07-02 | 2025-06-25 | Unknown | Unknown | 2025-06-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-25 | 2025-08-06 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | 2025-08-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | Applicant Design | Residential | Disadvantaged Community,Underserved Community | San Diego | San Diego | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-28 | 2023-06-28 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 88997 | 36774.55 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-28 | 2023-10-04 | 99 | 71 | 2023-10-04 | 2024-10-31 | 394 | 282 | 2023-10-10 | 2024-10-22 | 21 | 15 | 2023-10-02 | 2024-11-11 | 18 | 14 | 2024-10-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-08 | 2025-01-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1197.39 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-08 | 2024-12-23 | Unknown | Unknown | 2024-12-23 | 2025-01-22 | 31 | 23 | 2025-01-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-01-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-27 | 2024-11-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7962 | 4999.92 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-27 | 2024-11-21 | 87 | 63 | 2024-11-21 | 2024-12-03 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2025-02-11 | 2025-03-03 | 21 | 15 | 2024-12-03 | 2025-08-21 | 262 | 188 | Unknown | Unknown | Unknown | Unknown | 2025-09-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 8.1 | 8.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-13 | 2024-09-13 | 2024-11-05 | IOU Designed & Installed | N/A | No | Unknown | 45.51 | 0 | Unknown | Unknown | Unknown | 45.51 | 3981 | 1736 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-13 | 2024-09-06 | Unknown | Unknown | 2024-09-06 | 2024-09-13 | 8 | 6 | 2024-09-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-15 | 2024-11-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LEMON GROVE | N/A | 38.05 | 38.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-24 | 2025-04-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1080.66 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-24 | 2025-04-10 | Unknown | Unknown | 2025-04-10 | 2025-04-24 | 15 | 11 | 2025-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 39.05 | 39.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-04 | Unknown | Unknown | No | 2024-12-10 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-10 | 2024-12-10 | Unknown | IOU Designed & Installed | N/A | Yes | 184 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7962 | 802.26 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-10 | 2025-06-18 | 191 | 137 | 2025-06-18 | 2024-12-18 | Unknown | Unknown | 2024-12-18 | 2025-05-29 | 163 | 117 | Unknown | Unknown | Unknown | Unknown | 2024-12-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-30 | 2025-05-30 | 2025-06-24 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1258.74 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-30 | 2025-05-30 | 1 | 1 | 2025-05-30 | 2025-05-30 | 1 | 1 | 2025-05-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-30 | 2025-06-24 | 26 | 18 | Unknown | Unknown | Unknown | Unknown | 2025-06-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | Disadvantaged Community,Underserved Community | San Diego | San Diego | 11524 | 11524 | Not Available | >2MW | No | N/A | N/A | N/A | 2025-05-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-02 | 2024-01-02 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 6365.85 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-02 | 2024-03-18 | 77 | 55 | 2024-03-18 | 2024-10-15 | 212 | 152 | 2024-03-27 | 2025-07-07 | 91 | 65 | 2024-04-04 | 2024-10-11 | 35 | 25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | CHULA VISTA | CHULA VISTA | 201.1 | 201.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-24 | 2024-07-24 | 2025-04-23 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3469.07 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-24 | 2024-12-31 | 161 | 115 | 2024-12-31 | 2025-01-10 | 11 | 9 | Unknown | Unknown | Unknown | Unknown | 2024-12-31 | 2025-01-14 | 15 | 11 | 2025-01-10 | 2025-03-18 | 68 | 48 | Unknown | 2025-03-18 | Unknown | Unknown | 2025-04-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | N/A | Rancho Mission Viejo | COUNTY OF ORANGE, MISSION VIEJO | 5.4 | 5.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-20 | 2024-03-20 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 25179.56 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-20 | 2025-02-20 | 338 | 242 | 2025-02-20 | Unknown | Unknown | Unknown | 2025-02-28 | 2025-03-12 | 13 | 9 | 2025-03-21 | 2025-04-18 | 9 | 7 | 2025-05-07 | Unknown | Unknown | Unknown | 2025-05-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | N/A | LA JOLLA | N/A | 23371 | 23371 | Not Available | >2MW | No | N/A | N/A | N/A | 2026-03-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-09 | 2024-04-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1090.9 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-09 | 2024-09-28 | 173 | 124 | 2024-09-28 | 2024-09-30 | 3 | 1 | 2024-09-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SANTEE | N/A | 41.05 | 41.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-13 | 2024-03-13 | 2025-06-26 | IOU Designed & Installed | N/A | No | Unknown | 964.71 | 0 | Unknown | Unknown | 28.69 | 936.02 | 3981 | 1330.07 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-13 | 2024-02-13 | Unknown | Unknown | 2024-02-13 | 2024-05-09 | 87 | 63 | 2024-05-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-09 | 2025-06-26 | 414 | 296 | Unknown | 2024-09-24 | Unknown | Unknown | 2025-06-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | LA JOLLA | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-28 | 2023-04-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 900 | 337.5 | Unknown | Unknown | Yes | N/A | N/A | 2023-04-28 | 2023-04-28 | 1 | 1 | 2023-04-28 | 2023-09-11 | 137 | 97 | Unknown | Unknown | Unknown | Unknown | 2023-08-23 | 2023-08-29 | 7 | 5 | 2023-09-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-28 | 2024-05-06 | 2024-06-19 | IOU Designed & Installed | N/A | No | Unknown | 515.63 | -26.48 | Unknown | Unknown | 60.04 | 482.07 | 3981 | 1623.98 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-28 | 2024-02-29 | Unknown | Unknown | 2024-02-29 | 2024-05-06 | 68 | 48 | 2024-05-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-06 | 2024-06-19 | 45 | 33 | Unknown | Unknown | Unknown | Unknown | 2024-06-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-07 | 2024-06-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1458.4 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-07 | 2024-06-07 | 1 | 1 | 2024-06-07 | 2024-06-07 | 1 | 1 | 2024-06-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | Applicant Design | Residential | Underserved Community | San Diego | N/A | 39.05 | 39.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-06 | 2024-09-06 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2024-09-06 | 2024-05-24 | Unknown | Unknown | 2024-05-24 | 2024-12-10 | 201 | 143 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-19 | 2023-06-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 916.9 | Unknown | Unknown | Yes | N/A | N/A | 2023-04-19 | 2023-06-02 | 45 | 33 | 2023-06-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2027-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-22 | 2023-09-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 124302 | 23342.5 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-22 | 2023-10-05 | 14 | 10 | 2023-10-05 | 2023-10-17 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2025-08-06 | 2025-08-06 | 1 | 1 | 2023-10-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 124.05 | 124.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-06-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-25 | 2025-06-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1063.75 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-25 | 2025-06-06 | Unknown | Unknown | 2025-06-06 | 2025-06-25 | 20 | 14 | 2025-06-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-02 | 2024-05-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 496.14 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-02 | 2024-04-03 | Unknown | Unknown | 2024-04-03 | 2024-05-14 | 42 | 30 | 2024-05-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 104.05 | 104.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-21 | 2025-06-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 846.25 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-21 | 2025-01-28 | Unknown | Unknown | 2025-01-28 | 2025-06-27 | 151 | 109 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 542 | 542 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-06 | 2023-06-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 371.82 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-06 | 2023-06-08 | 3 | 3 | 2023-06-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-14 | 2023-04-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 576.62 | Unknown | Unknown | Yes | N/A | N/A | 2023-04-14 | 2023-04-17 | 4 | 2 | 2023-04-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-20 | 2025-01-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 390000 | 13496.27 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-20 | 2025-01-17 | 151 | 109 | 2025-01-17 | 2025-05-06 | 110 | 78 | Unknown | Unknown | Unknown | Unknown | 2025-05-08 | 2025-05-08 | 1 | 1 | 2025-05-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | LA MESA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-20 | 2023-11-28 | 2024-07-17 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1300.72 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-20 | 2023-10-16 | Unknown | Unknown | 2023-10-16 | 2023-11-28 | 44 | 32 | 2023-11-28 | Unknown | Unknown | Unknown | 2023-11-28 | 2023-11-30 | 3 | 3 | 2023-11-28 | 2024-07-17 | 233 | 167 | Unknown | Unknown | Unknown | Unknown | 2024-07-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-20 | 2025-05-20 | 2025-05-27 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 991.78 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-20 | 2025-05-20 | 1 | 1 | 2025-05-20 | 2025-05-20 | 1 | 1 | 2025-05-20 | Unknown | Unknown | Unknown | 2025-05-21 | 2025-05-28 | 8 | 6 | 2025-05-20 | 2025-05-27 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2025-05-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-18 | 2024-11-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1635.81 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-18 | 2024-10-05 | Unknown | Unknown | 2024-10-05 | 2024-11-18 | 45 | 31 | 2024-11-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-03 | 2024-12-03 | 2025-01-06 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 4356.38 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-03 | 2024-12-03 | 1 | 1 | 2024-12-03 | 2025-01-17 | 46 | 34 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-17 | Unknown | Unknown | Unknown | 2025-01-17 | 2025-01-17 | 1 | 1 | 2025-01-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-03 | 2025-02-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2122.32 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-03 | 2025-03-06 | 32 | 24 | 2025-03-06 | 2025-03-10 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | 2025-02-03 | 2025-02-26 | 24 | 18 | 2025-03-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-08-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | RAMONA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-22 | 2024-11-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1426.52 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-22 | 2025-01-03 | 43 | 31 | 2025-01-03 | 2025-01-09 | 7 | 5 | 2025-01-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-09 | 2025-08-27 | 231 | 165 | Unknown | 2025-08-22 | Unknown | Unknown | 2025-08-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 141 | 141 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-24 | 2024-04-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1058.42 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-24 | 2024-02-06 | Unknown | Unknown | 2024-02-06 | 2024-04-24 | 79 | 57 | 2024-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | 2.7 | 2.7 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-09 | 2025-04-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1061.92 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-09 | 2025-03-29 | Unknown | Unknown | 2025-03-29 | 2025-04-21 | 24 | 16 | 2025-04-21 | 2025-06-04 | 45 | 33 | Unknown | Unknown | Unknown | Unknown | 2025-06-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | POWAY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-21 | 2023-02-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 667.08 | Unknown | Unknown | Yes | N/A | N/A | 2023-02-21 | 2023-02-21 | 1 | 1 | 2023-02-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 156.05 | 156.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-31 | 2025-01-31 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1763.19 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-31 | 2025-01-31 | 1 | 1 | 2025-01-31 | 2025-01-31 | 1 | 1 | 2025-01-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | OCEANSIDE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-23 | 2024-07-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 680.06 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-23 | 2024-07-23 | 1 | 1 | 2024-07-23 | 2024-07-29 | 7 | 5 | 2024-07-29 | Unknown | Unknown | Unknown | 2024-07-25 | 2024-08-12 | 19 | 13 | 2024-07-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | DANA POINT | N/A | 11 | 11 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-29 | 2024-07-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1531.51 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-29 | 2024-07-29 | 1 | 1 | 2024-07-29 | 2024-07-29 | 1 | 1 | 2024-07-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-14 | 2025-03-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 250.06 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-14 | 2025-04-29 | 47 | 33 | 2025-04-29 | 2025-05-07 | 9 | 7 | 2025-05-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-07 | 2025-07-24 | 79 | 57 | Unknown | Unknown | Unknown | Unknown | 2025-07-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Commercial | Underserved Community | Lakeside | COUNTY OF SAN DIEGO-SOUTH of 56 | 53126 | 53126 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-08-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-11 | 2023-08-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 395937.93 | Unknown | Unknown | Yes | N/A | N/A | 2022-04-11 | 2023-08-11 | 488 | 350 | 2023-08-11 | 2025-03-31 | 599 | 427 | 2024-10-01 | 2025-03-24 | 109 | 79 | 2024-05-30 | 2025-05-05 | 55 | 39 | 2025-04-09 | Unknown | Unknown | Unknown | 2025-04-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 30.05 | 30.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-23 | 2024-10-23 | 2024-12-06 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1697.39 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-23 | 2024-10-22 | Unknown | Unknown | 2024-10-22 | 2024-11-27 | 37 | 27 | 2024-11-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-27 | 2024-12-06 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | 2024-12-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | 22.05 | 22.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-25 | 2025-02-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-25 | 2025-02-25 | 1 | 1 | 2025-02-25 | 2025-02-26 | 2 | 2 | 2025-02-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 9.05 | 9.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-20 | 2025-01-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 9676.99 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-20 | 2024-11-15 | Unknown | Unknown | 2024-11-15 | 2025-08-22 | 281 | 201 | Unknown | Unknown | Unknown | Unknown | 2025-01-22 | 2025-04-16 | 23 | 17 | 2025-08-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-08-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-09 | 2022-10-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 732.64 | Unknown | Unknown | Yes | N/A | N/A | 2022-10-09 | 2023-03-07 | 150 | 107 | 2023-03-07 | 2023-03-13 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 296 | 296 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-16 | 2024-04-10 | 2024-05-22 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1870.09 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-16 | 2023-11-16 | Unknown | Unknown | 2023-11-16 | 2024-04-10 | 147 | 105 | 2024-04-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-10 | 2024-05-22 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | 2024-05-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 9.05 | 9.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-31 | 2025-02-12 | 2025-06-03 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 15924 | 1285 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-31 | 2024-05-09 | Unknown | Unknown | 2024-05-09 | 2025-02-21 | 289 | 207 | Unknown | Unknown | Unknown | Unknown | 2025-02-13 | 2025-03-06 | 22 | 16 | 2025-02-21 | 2025-05-15 | 84 | 60 | Unknown | Unknown | Unknown | Unknown | 2025-06-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | JAMUL | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-04 | 2024-03-04 | 2024-03-21 | IOU Designed & Installed | N/A | No | Unknown | 160.16 | -13.68 | Unknown | Unknown | Unknown | 173.84 | 0 | 912.91 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-04 | 2024-02-29 | Unknown | Unknown | 2024-02-29 | 2024-03-06 | 7 | 5 | 2024-03-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-06 | 2024-03-21 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | 2024-03-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 10.05 | 10.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-29 | 2023-03-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3885 | 662.65 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-29 | 2023-03-29 | 1 | 1 | 2023-03-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | PAUMA VALLEY | N/A | 1791.5 | 1791.5 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2026-05-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-17 | 2025-05-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 723.94 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-17 | 2025-05-07 | 203 | 145 | 2025-05-07 | 2025-06-09 | 34 | 24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | MOUNT LAGUNA | N/A | 198 | 198 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-15 | 2023-11-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3281 | 603.34 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-15 | 2023-11-15 | 1 | 1 | 2023-11-15 | 2023-11-15 | 1 | 1 | 2023-11-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-27 | 2024-12-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 499.14 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-27 | 2024-12-02 | 6 | 4 | 2024-12-02 | 2025-02-11 | 72 | 52 | Unknown | Unknown | Unknown | Unknown | 2024-12-02 | 2025-01-07 | 37 | 27 | 2025-02-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | OH | IOU Design | Commercial | Underserved Community | FALLBROOK | COUNTY OF SAN DIEGO-NORTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-08 | 2023-03-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 44254.4 | 79221.21 | Unknown | Unknown | Yes | N/A | N/A | 2022-09-08 | 2023-07-10 | 306 | 218 | 2023-07-10 | 2024-07-03 | 360 | 258 | 2024-03-12 | 2024-05-10 | 60 | 44 | 2023-11-13 | 2024-05-14 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LAKESIDE | COUNTY OF SAN DIEGO-SOUTH of 56 | 25 | 25 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-02 | 2024-07-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2062.82 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-02 | 2024-07-02 | 1 | 1 | 2024-07-02 | 2024-07-03 | 2 | 2 | 2024-07-03 | Unknown | Unknown | Unknown | 2024-07-15 | 2024-07-17 | 3 | 3 | 2024-07-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | FALLBROOK | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-15 | 2023-12-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 619.25 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-15 | 2023-12-15 | 1 | 1 | 2023-12-15 | 2023-12-15 | 1 | 1 | 2023-12-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-19 | 2024-11-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1244.59 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-19 | 2024-12-05 | 17 | 13 | 2024-12-05 | 2024-12-09 | 5 | 3 | 2024-12-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-15 | 2024-10-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3144.9 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-15 | 2024-12-12 | 59 | 43 | 2024-12-12 | 2024-12-19 | 8 | 6 | 2024-12-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-06 | 2024-09-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2024-09-06 | 2024-09-06 | 1 | 1 | 2024-09-06 | 2024-09-10 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-10 | 2025-09-09 | 365 | 261 | Unknown | Unknown | Unknown | Unknown | 2025-07-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 14.05 | 14.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-16 | 2024-12-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 6378.36 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-16 | 2024-11-20 | Unknown | Unknown | 2024-11-20 | 2024-12-16 | 27 | 19 | 2024-12-16 | 2025-03-03 | 78 | 56 | Unknown | Unknown | Unknown | Unknown | 2024-12-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Residential | N/A | Rancho Mission Viejo | COUNTY OF ORANGE | 106.1 | 106.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-06-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-03 | 2024-08-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 145156.8 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-03 | 2024-06-26 | Unknown | Unknown | 2024-06-26 | 2025-03-10 | 258 | 184 | 2024-11-18 | 2025-05-22 | 43 | 29 | 2024-11-21 | 2025-02-27 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-25 | 2025-02-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2128.04 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-25 | 2025-04-03 | 38 | 28 | 2025-04-03 | 2025-04-04 | 2 | 2 | 2025-02-25 | 2025-04-02 | 37 | 27 | Unknown | Unknown | Unknown | Unknown | 2025-04-04 | 2025-07-01 | 89 | 63 | Unknown | Unknown | Unknown | Unknown | 2025-08-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 3 | 3 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-05 | 2024-08-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1708.53 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-05 | 2024-04-23 | Unknown | Unknown | 2024-04-23 | 2024-08-05 | 105 | 75 | 2024-08-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | POWAY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-26 | 2024-08-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 15924 | 1230 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-26 | 2024-03-29 | Unknown | Unknown | 2024-03-29 | 2025-01-02 | 280 | 200 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-29 | 2024-07-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 23991 | 677.91 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-29 | 2024-04-26 | Unknown | Unknown | 2024-04-26 | 2024-07-29 | 95 | 67 | 2024-07-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2020-01-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-30 | 2023-06-30 | 2023-07-24 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1110.53 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-30 | 2023-06-30 | 1 | 1 | 2023-06-30 | 2023-06-30 | 1 | 1 | 2023-06-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-30 | 2023-07-24 | 25 | 17 | Unknown | Unknown | Unknown | Unknown | 2023-07-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-29 | 2025-04-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1098.24 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-29 | 2025-04-21 | Unknown | Unknown | 2025-04-21 | 2025-05-19 | 29 | 21 | 2025-05-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | Underserved Community | OC 1086-G3 Summerwell WO3 | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-09 | 2023-02-09 | 2025-06-10 | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 57879 | 22263.52 | Unknown | Unknown | Yes | N/A | N/A | 2023-02-09 | 2023-03-02 | 22 | 16 | 2023-03-02 | 2024-11-15 | 625 | 447 | 2023-03-08 | 2024-11-07 | 573 | 411 | 2024-10-18 | 2024-10-25 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-07-11 | Unknown | Unknown | 2025-06-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | FALLBROOK | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-10 | 2025-06-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 4321.24 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-10 | 2025-06-18 | 9 | 7 | 2025-06-18 | 2025-06-27 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-07-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | LAGUNA NIGUEL | N/A | 127 | 127 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-18 | 2025-02-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1548.9 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-18 | 2025-03-07 | 18 | 14 | 2025-03-07 | 2025-03-07 | 1 | 1 | 2025-03-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-07 | 2025-09-09 | 187 | 133 | Unknown | 2025-09-04 | Unknown | Unknown | 2025-09-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-27 | 2025-03-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1631.08 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-27 | 2025-03-18 | Unknown | Unknown | 2025-03-18 | 2025-03-28 | 11 | 9 | 2025-03-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-08-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-08 | 2025-01-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7371 | 729.8 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-08 | 2025-01-09 | 2 | 2 | 2025-01-09 | 2025-01-22 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-22 | 2025-07-02 | 162 | 116 | Unknown | 2025-06-20 | Unknown | Unknown | 2025-07-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-13 | 2024-08-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1106.02 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-13 | 2024-07-22 | Unknown | Unknown | 2024-07-22 | 2024-07-22 | 1 | 1 | 2024-07-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-16 | 2024-02-16 | 2024-08-19 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 936.57 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-16 | 2024-02-16 | 1 | 1 | 2024-02-16 | 2024-02-16 | 1 | 1 | 2024-02-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-16 | 2024-08-19 | 186 | 132 | Unknown | Unknown | Unknown | Unknown | 2024-08-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LEMON GROVE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-25 | 2024-09-26 | 2025-01-13 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1485.54 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-25 | 2024-09-24 | Unknown | Unknown | 2024-09-24 | 2024-09-26 | 3 | 3 | 2024-09-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-26 | 2025-01-13 | 110 | 78 | Unknown | Unknown | Unknown | Unknown | 2025-01-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-27 | 2024-05-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1868.64 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-27 | 2024-03-06 | Unknown | Unknown | 2024-03-06 | 2024-08-09 | 157 | 113 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-29 | 2023-10-10 | 2023-10-13 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 284.12 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-29 | 2023-07-05 | Unknown | Unknown | 2023-07-05 | 2023-10-10 | 98 | 70 | 2023-10-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-10 | 2023-10-13 | 4 | 4 | Unknown | Unknown | Unknown | Unknown | 2023-10-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | CORONADO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-02 | 2025-06-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1120.76 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-02 | 2025-06-19 | 18 | 14 | 2025-06-19 | 2025-06-19 | 1 | 1 | 2025-06-19 | 2025-06-19 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2025-06-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | LA MESA | LA MESA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-15 | 2025-04-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1942.29 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-15 | 2025-04-15 | 1 | 1 | 2025-04-15 | 2025-05-23 | 39 | 29 | Unknown | Unknown | Unknown | Unknown | 2025-05-14 | 2025-05-22 | 9 | 7 | 2025-05-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | FALLBROOK | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-15 | 2022-08-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3496.8 | Unknown | Unknown | Yes | N/A | N/A | 2022-08-15 | 2023-10-11 | 423 | 303 | 2023-10-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2020-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-20 | 2023-11-20 | 2024-12-09 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1220.26 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-20 | 2023-12-04 | 15 | 11 | 2023-12-04 | 2023-12-13 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-13 | 2024-12-17 | 371 | 265 | Unknown | 2024-11-21 | Unknown | Unknown | 2024-12-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | Applicant Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-19 | 2022-10-19 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 26672.25 | Unknown | Unknown | Yes | N/A | N/A | 2022-10-19 | 2023-04-20 | 184 | 132 | 2023-04-20 | 2024-10-17 | 547 | 391 | 2023-05-31 | 2023-06-14 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CORONADO | N/A | 8.1 | 8.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-16 | 2024-07-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1167.86 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-16 | 2024-07-16 | 1 | 1 | 2024-07-16 | 2024-07-16 | 1 | 1 | 2024-07-16 | 2024-07-22 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2024-07-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 58.05 | 58.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-14 | 2025-01-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3685.96 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-14 | 2025-01-14 | 1 | 1 | 2025-01-14 | 2025-03-04 | 50 | 36 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | 2400 | 2400 | Not Available | >2MW | No | N/A | N/A | N/A | 2026-03-05 | Unknown | Unknown | No | 2024-07-01 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-01 | 2024-07-02 | 2024-09-26 | IOU Designed & Installed | N/A | Yes | 11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1210.37 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-01 | 2024-07-12 | 12 | 10 | 2024-07-12 | 2024-07-02 | Unknown | Unknown | 2024-07-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-02 | 2024-09-26 | 87 | 63 | Unknown | Unknown | Unknown | Unknown | 2024-09-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-29 | 2025-04-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 12481 | 397.2 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-29 | 2025-04-16 | Unknown | Unknown | 2025-04-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Commercial | Underserved Community | Valley Center | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2021-09-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-20 | 2025-05-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 9063.55 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-20 | 2025-05-16 | Unknown | Unknown | 2025-05-16 | 2025-07-22 | 68 | 48 | Unknown | Unknown | Unknown | Unknown | 2025-07-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-07-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | Applicant Design | Residential | Disadvantaged Community,Underserved Community | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-06 | 2022-12-06 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 766436 | 95107.6 | Unknown | Unknown | Yes | N/A | N/A | 2022-12-06 | 2024-03-29 | 480 | 344 | 2024-03-29 | 2024-09-27 | 183 | 131 | 2024-04-19 | 2024-07-08 | 58 | 42 | 2023-09-28 | 2024-10-16 | 35 | 25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | VALLEY CENTER | N/A | 64 | 64 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-05 | 2025-03-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1194.64 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-05 | 2025-03-19 | 15 | 11 | 2025-03-19 | 2025-04-09 | 22 | 16 | 2025-04-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-16 | Unknown | Unknown | Unknown | Unknown | 2025-08-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-11 | 2025-04-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1232.19 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-11 | 2025-03-24 | Unknown | Unknown | 2025-03-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2018-08-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-07 | 2023-08-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 71.28 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-07 | 2023-08-08 | 2 | 2 | 2023-08-08 | 2023-08-17 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | RAMONA | COUNTY OF SAN DIEGO-NORTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-06 | 2024-06-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1336.35 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-06 | 2024-06-18 | 13 | 9 | 2024-06-18 | 2024-06-18 | 1 | 1 | 2024-06-18 | 2025-04-28 | 298 | 212 | 2024-07-18 | 2025-05-08 | 15 | 13 | 2024-06-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Disadvantaged Community,Underserved Community | NATIONAL CITY | NATIONAL CITY | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-25 | 2023-02-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 26990 | 1396.19 | Unknown | Unknown | Yes | N/A | N/A | 2023-01-25 | 2023-02-28 | 35 | 25 | 2023-02-28 | 2023-11-27 | 273 | 195 | 2023-10-20 | 2024-04-25 | 37 | 27 | 2023-09-11 | 2025-07-03 | 300 | 218 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-07-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 20 | 20 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-26 | 2023-12-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 153.49 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-26 | 2023-09-25 | Unknown | Unknown | 2023-09-25 | 2024-01-05 | 103 | 75 | 2024-01-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | ALPINE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-25 | 2024-06-25 | 2024-07-19 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 11347.56 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-25 | 2024-06-25 | 1 | 1 | 2024-06-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | CAMPO | N/A | 52 | 52 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-21 | 2024-05-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3909.82 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-21 | 2024-05-22 | 2 | 2 | 2024-05-22 | 2024-07-24 | 64 | 46 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SOUTH LAGUNA | N/A | 129.05 | 129.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-10 | 2024-01-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1146 | Unknown | Unknown | Yes | N/A | N/A | 2022-10-10 | 2024-01-29 | 477 | 341 | 2024-01-29 | 2024-01-29 | 1 | 1 | 2024-01-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-05 | 2023-11-05 | 2023-12-19 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3941 | 221.58 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-05 | 2023-06-26 | Unknown | Unknown | 2023-06-26 | 2023-11-13 | 141 | 101 | 2023-11-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-13 | 2023-12-19 | 37 | 27 | Unknown | Unknown | Unknown | Unknown | 2023-12-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | NATIONAL CITY, SAN DIEGO | 5 | 5 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-27 | 2025-03-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2240.84 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-27 | 2025-03-25 | 27 | 19 | 2025-03-25 | 2025-04-23 | 30 | 22 | Unknown | Unknown | Unknown | Unknown | 2025-06-10 | 2025-06-27 | 18 | 14 | 2025-04-23 | 2025-06-02 | 41 | 29 | Unknown | Unknown | Unknown | Unknown | 2025-08-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | ENCINITAS | 24 | 24 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-10 | 2024-10-17 | 2024-12-09 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 634.76 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-10 | 2024-11-06 | 28 | 20 | 2024-11-06 | 2024-11-08 | 3 | 3 | 2024-11-08 | Unknown | Unknown | Unknown | 2024-11-08 | 2024-12-05 | 28 | 20 | 2024-11-08 | 2024-12-09 | 32 | 22 | Unknown | Unknown | Unknown | Unknown | 2024-12-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-17 | 2025-04-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3662 | 454.24 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-17 | 2025-01-14 | Unknown | Unknown | 2025-01-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | San Diego | SAN DIEGO | 61 | 61 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-19 | 2024-08-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 75500 | 23400.19 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-19 | 2024-08-19 | 1 | 1 | 2024-08-19 | 2025-03-19 | 213 | 153 | 2024-11-05 | 2024-11-06 | 2 | 2 | 2024-11-20 | 2025-03-31 | 41 | 29 | 2025-03-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-01 | 2025-04-01 | 2025-06-24 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2396.49 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-01 | 2025-03-20 | Unknown | Unknown | 2025-03-20 | 2025-05-06 | 48 | 34 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-17 | 2023-07-17 | 2023-07-17 | IOU Designed & Installed | N/A | No | Unknown | 7895.38 | 1933 | Unknown | 2117.36 | 353.21 | 3491.81 | 0 | 863.9 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-17 | 2023-07-17 | 1 | 1 | 2023-07-17 | 2023-07-17 | 1 | 1 | 2023-07-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-17 | 2023-07-17 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2023-07-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 138.05 | 138.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-23 | 2025-01-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 946.06 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-23 | 2025-02-11 | 20 | 14 | 2025-02-11 | 2025-02-20 | 10 | 8 | 2025-02-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-20 | 2025-08-21 | 183 | 131 | Unknown | 2025-08-21 | Unknown | Unknown | 2025-08-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SOLANA BEACH | N/A | 80 | 80 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-24 | 2024-07-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2573.07 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-24 | 2024-06-19 | Unknown | Unknown | 2024-06-19 | 2024-07-22 | 34 | 24 | 2024-07-22 | 2024-08-05 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2024-08-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | CORONADO | CORONADO | 15 | 15 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-29 | 2025-01-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1762.47 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-29 | 2025-01-29 | 1 | 1 | 2025-01-29 | 2025-01-29 | 1 | 1 | 2025-01-29 | Unknown | Unknown | Unknown | 2025-01-31 | 2025-03-05 | 34 | 24 | 2025-01-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ESCONDIDO | N/A | 43 | 43 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-13 | 2023-12-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 692.05 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-13 | 2023-09-11 | Unknown | Unknown | 2023-09-11 | 2023-12-29 | 110 | 80 | 2023-12-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | Both | IOU Design | Commercial | N/A | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-10 | 2024-01-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3141.88 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-10 | 2024-01-10 | 1 | 1 | 2024-01-10 | 2024-01-31 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2021-12-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-11 | 2023-04-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 118909 | 432.6 | Unknown | Unknown | Yes | N/A | N/A | 2023-04-11 | 2023-04-17 | 7 | 5 | 2023-04-17 | 2024-04-30 | 380 | 272 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 3 | 3 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-20 | 2025-01-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2115.43 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-20 | 2024-12-17 | Unknown | Unknown | 2024-12-17 | 2025-01-13 | 28 | 20 | 2025-01-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN JUAN CAPISTRANO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-30 | 2024-11-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2665.59 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-30 | 2024-11-18 | 20 | 14 | 2024-11-18 | 2024-11-21 | 4 | 4 | 2024-11-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-21 | Unknown | Unknown | Unknown | Unknown | 2025-02-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-10 | 2025-01-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1196.64 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-10 | 2025-01-13 | 4 | 2 | 2025-01-13 | 2025-02-10 | 29 | 21 | 2025-02-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2018-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-10 | 2023-11-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1370.33 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-10 | 2023-11-10 | 1 | 1 | 2023-11-10 | 2025-03-18 | 495 | 353 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-18 | 2025-07-24 | 129 | 93 | Unknown | 2025-05-30 | Unknown | Unknown | 2025-08-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-31 | 2023-01-31 | 2023-02-09 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3241 | 595.1 | Unknown | Unknown | Yes | N/A | N/A | 2023-01-31 | 2023-01-31 | 1 | 1 | 2023-01-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-01-31 | 2023-02-09 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | 2023-02-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-20 | 2023-04-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 391.87 | Unknown | Unknown | Yes | N/A | N/A | 2023-04-20 | 2023-06-14 | 56 | 40 | 2023-06-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-18 | 2023-06-01 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SANTEE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-07 | 2023-04-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1114.34 | Unknown | Unknown | Yes | N/A | N/A | 2023-04-07 | 2023-04-07 | 1 | 1 | 2023-04-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community,Tribal Community | PALA | N/A | 64.05 | 64.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-28 | 2024-10-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 550.66 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-28 | 2024-10-28 | 1 | 1 | 2024-10-28 | 2025-06-13 | 229 | 165 | 2025-05-27 | 2025-05-27 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2025-06-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-09 | 2024-06-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3961 | 1550.9 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-09 | 2024-08-27 | 141 | 101 | 2024-08-27 | 2024-09-30 | 35 | 25 | 2024-09-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-17 | 2025-06-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 883.73 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-17 | 2025-06-23 | 7 | 5 | 2025-06-23 | 2025-06-23 | 1 | 1 | 2025-06-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-17 | 2024-09-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2553.36 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-17 | 2024-08-30 | Unknown | Unknown | 2024-08-30 | 2024-09-25 | 27 | 19 | 2024-09-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | CARDIFF | ENCINITAS | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-03 | 2025-06-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1464.22 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-03 | 2025-06-11 | 9 | 7 | 2025-06-11 | 2025-06-12 | 2 | 2 | 2025-06-12 | Unknown | Unknown | Unknown | 2025-06-13 | 2025-07-08 | 26 | 18 | 2025-06-12 | 2025-09-04 | 85 | 61 | Unknown | Unknown | Unknown | Unknown | 2025-09-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-07 | Unknown | Unknown | No | 2024-04-18 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-18 | 2024-04-18 | Unknown | IOU Designed & Installed | N/A | Yes | 15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 12481 | 584.27 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-18 | 2024-05-03 | 16 | 12 | 2024-05-03 | 2024-04-18 | Unknown | Unknown | 2024-04-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-18 | 2023-07-18 | 2023-07-18 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 261.37 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-18 | 2023-06-22 | Unknown | Unknown | 2023-06-22 | 2023-07-18 | 27 | 19 | 2023-07-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-18 | 2023-07-18 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2023-07-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | EL CAJON | N/A | 68.05 | 68.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-05 | 2024-11-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1197.6 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-05 | 2024-11-19 | 15 | 11 | 2024-11-19 | 2024-11-20 | 2 | 2 | 2024-11-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-15 | 2024-08-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1182.35 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-15 | 2024-09-18 | 66 | 48 | 2024-09-18 | 2024-09-24 | 7 | 5 | 2024-09-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-16 | 2024-12-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 5264.13 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-16 | 2024-12-19 | 4 | 4 | 2024-12-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 20.05 | 20.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-25 | 2025-06-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1303.82 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-25 | 2025-06-09 | Unknown | Unknown | 2025-06-09 | 2025-06-25 | 17 | 13 | 2025-06-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-25 | 2025-08-19 | 56 | 40 | Unknown | Unknown | Unknown | Unknown | 2025-08-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R29/R45 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-09 | 2024-10-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 125346.13 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-09 | 2025-01-30 | 175 | 125 | 2025-01-30 | Unknown | Unknown | Unknown | 2025-03-17 | 2025-04-15 | 30 | 22 | 2024-12-04 | 2025-07-25 | 69 | 53 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-24 | 2024-07-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2543.48 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-24 | 2024-07-24 | 1 | 1 | 2024-07-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-06 | 2025-06-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1332.16 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-06 | 2025-06-06 | 1 | 1 | 2025-06-06 | 2025-06-06 | 1 | 1 | 2025-06-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SANTEE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-12 | 2024-11-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1189.69 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-12 | 2024-10-23 | Unknown | Unknown | 2024-10-23 | 2024-11-18 | 27 | 19 | 2024-11-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | 40000 | 40000 | Not Available | >2MW | No | N/A | N/A | N/A | 2025-12-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-27 | 2024-11-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 1127746 | 35067.44 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-27 | 2024-08-29 | Unknown | Unknown | 2024-08-29 | 2025-01-10 | 135 | 97 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-10 | 2025-06-25 | 167 | 119 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | OCEANSIDE | OCEANSIDE | 2 | 2 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-05 | 2024-02-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 808.75 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-05 | 2024-02-05 | 1 | 1 | 2024-02-05 | 2024-03-08 | 33 | 25 | 2024-03-15 | 2024-11-20 | 251 | 179 | 2024-03-01 | 2025-01-07 | 64 | 46 | 2024-03-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | 121.05 | 121.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-18 | 2025-05-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1252.97 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-18 | 2025-05-21 | 246 | 176 | 2025-05-21 | 2025-05-29 | 9 | 7 | 2025-05-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-29 | 2025-07-23 | 56 | 40 | Unknown | Unknown | Unknown | Unknown | 2025-07-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 1.35 | 1.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-27 | 2024-07-27 | 2024-09-03 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1626.9 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-27 | 2024-08-13 | 18 | 12 | 2024-08-13 | 2024-08-22 | 10 | 8 | 2024-08-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-22 | 2024-09-03 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2024-09-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2020-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-02 | 2023-02-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 47.04 | Unknown | Unknown | Yes | N/A | N/A | 2023-02-02 | 2023-02-02 | 1 | 1 | 2023-02-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 4127 | 4127 | Not Available | >2MW | No | N/A | N/A | N/A | 2022-04-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-16 | 2025-02-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 15505.12 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-16 | 2025-02-06 | 114 | 82 | 2025-02-06 | 2025-04-25 | 79 | 57 | Unknown | Unknown | Unknown | Unknown | 2025-02-19 | 2025-03-06 | 16 | 12 | 2025-04-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-22 | 2024-05-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 10980 | 584.27 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-22 | 2024-05-07 | 16 | 12 | 2024-05-07 | 2024-05-07 | 1 | 1 | 2024-05-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-09 | 2025-08-28 | 477 | 341 | Unknown | Unknown | Unknown | Unknown | 2025-08-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-21 | 2023-06-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 20170.85 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-21 | 2023-07-14 | 24 | 18 | 2023-07-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-17 | 2024-09-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2584.77 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-17 | 2024-09-18 | 2 | 2 | 2024-09-18 | 2024-10-17 | 30 | 22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | N/A | SAN CLEMENTE | N/A | 20 | 20 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-09-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-28 | 2023-06-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 36350 | 2748.68 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-28 | 2023-03-28 | 1 | 1 | 2023-03-28 | Unknown | Unknown | Unknown | 2023-06-01 | 2023-06-01 | 1 | 1 | 2023-06-08 | 2023-06-12 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | 874.05 | 874.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-28 | 2024-10-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1566.77 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-28 | 2024-09-04 | Unknown | Unknown | 2024-09-04 | 2024-10-28 | 55 | 39 | 2024-10-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-19 | 2025-01-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1928.43 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-19 | 2025-01-24 | 37 | 27 | 2025-01-24 | 2025-01-28 | 5 | 3 | 2025-01-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-04-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-12 | 2024-08-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1724.74 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-12 | 2024-05-24 | Unknown | Unknown | 2024-05-24 | 2024-08-12 | 81 | 57 | 2024-08-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | OH | IOU Design | Commercial | Disadvantaged Community,Underserved Community | national city | NATIONAL CITY | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-21 | 2023-11-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 27118 | 15932.69 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-21 | 2023-09-25 | 97 | 69 | 2023-09-25 | 2024-08-20 | 331 | 237 | 2023-06-21 | Unknown | Unknown | Unknown | 2024-03-01 | 2024-09-20 | 204 | 144 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 42.05 | 42.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-10 | 2024-09-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 192.95 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-10 | 2024-09-19 | 10 | 8 | 2024-09-19 | 2024-09-19 | 1 | 1 | 2024-09-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2018-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-18 | 2025-04-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 104.41 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-18 | 2025-04-18 | 1 | 1 | 2025-04-18 | 2025-05-05 | 18 | 12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-14 | 2025-03-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1336.15 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-14 | 2025-04-22 | 40 | 28 | 2025-04-22 | 2025-05-05 | 14 | 10 | 2025-05-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-17 | 2024-09-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3395.84 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-17 | 2024-09-26 | 10 | 8 | 2024-09-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | N/A | 368.45 | 368.45 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-26 | 2024-04-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1316.39 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-26 | 2024-10-15 | 204 | 146 | 2024-10-15 | 2024-11-18 | 35 | 25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-18 | 2025-06-26 | 221 | 159 | Unknown | 2025-07-03 | Unknown | Unknown | 2025-07-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-11 | 2025-05-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 450.11 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-11 | 2025-05-15 | 5 | 4 | 2025-05-15 | 2025-07-01 | 48 | 34 | Unknown | Unknown | Unknown | Unknown | 2025-05-20 | 2025-06-06 | 18 | 14 | 2025-07-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-08-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CHULA VISTA | N/A | 48 | 48 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-20 | 2025-05-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 823.59 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-20 | 2025-05-09 | Unknown | Unknown | 2025-05-09 | 2025-06-17 | 40 | 28 | 2025-06-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | 105.1 | 105.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-13 | 2024-08-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1946.94 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-13 | 2024-08-14 | 2 | 2 | 2024-08-14 | 2024-08-14 | 1 | 1 | 2024-08-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-18 | 2023-09-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 496.37 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-18 | 2023-09-18 | 1 | 1 | 2023-09-18 | 2023-09-18 | 1 | 1 | 2023-09-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 68.05 | 68.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-06 | 2025-02-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1279.74 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-06 | 2025-02-04 | Unknown | Unknown | 2025-02-04 | 2025-02-12 | 9 | 7 | 2025-02-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-25 | 2025-03-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1699.16 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-25 | 2025-03-11 | Unknown | Unknown | 2025-03-11 | 2025-03-26 | 16 | 12 | 2025-03-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-06 | 2025-05-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1036.52 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-06 | 2025-04-04 | Unknown | Unknown | 2025-04-04 | 2025-05-09 | 36 | 26 | 2025-05-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 32 | 32 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-29 | 2024-10-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1447.45 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-29 | 2025-01-29 | 93 | 67 | 2025-01-29 | 2025-02-11 | 14 | 10 | 2025-02-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-12 | 2025-08-04 | 174 | 124 | Unknown | 2025-07-17 | Unknown | Unknown | 2025-08-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-21 | 2025-04-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1063.13 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-21 | 2025-04-10 | Unknown | Unknown | 2025-04-10 | 2025-04-23 | 14 | 10 | 2025-04-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-23 | 2025-08-15 | 115 | 83 | Unknown | Unknown | Unknown | Unknown | 2025-08-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SANTEE | N/A | 39.05 | 39.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-04 | 2025-02-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1281.88 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-04 | 2025-02-24 | 21 | 15 | 2025-02-24 | 2025-02-27 | 4 | 4 | 2025-02-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2021-04-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-18 | 2023-09-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 371.59 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-18 | 2023-11-29 | 73 | 53 | 2023-11-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-04 | 2023-12-07 | 4 | 4 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | Applicant Design | Commercial | Underserved Community | Santee | SANTEE | 36 | 36 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-30 | 2024-05-30 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 85102 | 91907.55 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-30 | 2024-10-16 | 140 | 100 | 2024-10-16 | 2025-03-06 | 142 | 102 | 2024-10-22 | 2025-03-06 | 88 | 62 | 2024-09-16 | 2025-07-29 | 155 | 109 | 2025-03-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 36 | 36 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-20 | 2023-06-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 752.42 | Unknown | Unknown | Yes | N/A | N/A | 2023-05-20 | 2023-06-11 | 23 | 15 | 2023-06-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-13 | 2023-12-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 158.79 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-13 | 2023-08-18 | Unknown | Unknown | 2023-08-18 | 2023-12-15 | 120 | 86 | 2023-12-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 112 | 112 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-15 | Unknown | Unknown | No | 2024-09-05 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-05 | 2024-09-05 | 2024-12-16 | IOU Designed & Installed | N/A | Yes | 60 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1032.15 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-05 | 2024-09-26 | 22 | 16 | 2024-09-26 | 2024-11-04 | 40 | 28 | 2024-11-04 | 2024-12-13 | 40 | 30 | Unknown | Unknown | Unknown | Unknown | 2024-11-13 | 2024-12-16 | 34 | 24 | Unknown | 2024-12-12 | Unknown | Unknown | 2024-12-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-30 | 2024-09-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3278.05 | 98477.33 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-30 | 2024-08-30 | 1 | 1 | 2024-08-30 | 2025-06-03 | 278 | 198 | 2025-04-07 | 2025-05-09 | 33 | 25 | 2024-11-21 | 2025-08-06 | 125 | 89 | 2025-06-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-08-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | COUNTY OF SAN DIEGO-NORTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-14 | 2025-05-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2330.16 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-14 | 2025-04-04 | Unknown | Unknown | 2025-04-04 | 2025-06-30 | 88 | 62 | Unknown | Unknown | Unknown | Unknown | 2025-05-30 | 2025-06-10 | 12 | 8 | 2025-06-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-10 | 2024-01-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 13669 | 510.02 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-10 | 2023-10-19 | Unknown | Unknown | 2023-10-19 | 2024-01-12 | 86 | 62 | 2024-01-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 43 | 43 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-14 | 2023-11-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 949.93 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-14 | 2023-11-14 | 1 | 1 | 2023-11-14 | 2023-11-14 | 1 | 1 | 2023-11-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | CORONADO | N/A | 47.05 | 47.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-14 | 2024-11-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1847.47 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-14 | 2024-11-14 | 1 | 1 | 2024-11-14 | 2024-11-14 | 1 | 1 | 2024-11-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | IMPERIAL BEACH | 18 | 18 | Not Available | <1MW | No | N/A | N/A | N/A | 2021-07-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-20 | 2023-11-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 33176.24 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-20 | 2023-11-20 | 1 | 1 | 2023-11-20 | 2025-02-26 | 465 | 333 | 2024-03-06 | 2025-01-30 | 100 | 72 | 2024-05-09 | 2024-08-29 | 113 | 81 | 2025-02-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-13 | 2023-11-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1851.44 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-13 | 2023-11-17 | 5 | 5 | 2023-11-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-09-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | 528.05 | 528.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-23 | 2024-08-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1352.81 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-23 | 2024-07-05 | Unknown | Unknown | 2024-07-05 | 2024-08-29 | 56 | 40 | 2024-08-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | RANCHO LA COSTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-12 | 2023-10-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 158.51 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-12 | 2023-06-11 | Unknown | Unknown | 2023-06-11 | 2023-10-25 | 137 | 98 | 2023-10-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | ESCONDIDO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-28 | 2025-06-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1453.73 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-28 | 2025-05-14 | Unknown | Unknown | 2025-05-14 | 2025-05-30 | 17 | 13 | 2025-05-30 | Unknown | Unknown | Unknown | 2025-06-03 | 2025-06-12 | 10 | 8 | 2025-06-03 | 2025-07-23 | 51 | 37 | Unknown | Unknown | Unknown | Unknown | 2025-07-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Agricultural | Underserved Community | FALLBROOK | N/A | 26 | 26 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-07 | 2023-02-07 | 2024-08-08 | IOU Designed & Installed | N/A | No | Unknown | 16853.06 | 4267.8 | Unknown | 153.02 | 643.11 | 11789.13 | 3981 | 1222.42 | Unknown | Unknown | Yes | N/A | N/A | 2023-02-07 | 2023-06-14 | 128 | 92 | 2023-06-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-05 | 2024-08-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 38.05 | 38.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-05 | 2024-12-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 499.14 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-05 | 2024-12-05 | 1 | 1 | 2024-12-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | COUNTY OF SAN DIEGO-NORTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-19 | 2025-01-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 31993.27 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-19 | 2024-10-29 | Unknown | Unknown | 2024-10-29 | 2025-05-23 | 207 | 149 | 2025-02-04 | 2025-02-12 | 9 | 7 | 2025-05-19 | 2025-05-28 | 10 | 8 | 2025-05-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-07 | 2024-02-09 | 2024-04-16 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1022.67 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-07 | 2023-10-18 | Unknown | Unknown | 2023-10-18 | 2024-02-09 | 115 | 83 | 2024-02-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-09 | 2024-04-16 | 68 | 48 | Unknown | Unknown | Unknown | Unknown | 2024-04-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 69.05 | 69.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-14 | 2024-10-14 | 2025-02-12 | IOU Designed & Installed | N/A | No | Unknown | 1473.44 | 0 | Unknown | Unknown | 7.61 | 1465.83 | 3981 | 1330.03 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-14 | 2024-10-25 | 12 | 10 | 2024-10-25 | 2024-11-18 | 25 | 17 | 2024-11-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-18 | 2025-02-12 | 87 | 63 | Unknown | 2025-02-12 | Unknown | Unknown | 2025-02-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 71.05 | 71.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-07 | 2025-05-07 | 2025-06-18 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1253.02 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-07 | 2025-05-09 | 3 | 3 | 2025-05-09 | 2025-05-22 | 14 | 10 | 2025-05-07 | 2025-05-22 | 16 | 12 | 2025-05-22 | 2025-06-13 | 23 | 17 | 2025-05-22 | 2025-06-18 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | 2025-06-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | JULIAN | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-19 | 2025-02-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1151.34 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-19 | 2025-02-14 | Unknown | Unknown | 2025-02-14 | 2025-02-19 | 6 | 4 | 2025-02-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-07 | 2023-09-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 859.57 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-07 | 2024-01-30 | 146 | 104 | 2024-01-30 | 2024-01-30 | 1 | 1 | 2024-01-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | Applicant Design | Commercial | Underserved Community | ES 1129-H4 chic fil a - (E) | ESCONDIDO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-26 | 2023-12-26 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 31339.91 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-26 | 2024-10-22 | 302 | 216 | 2024-10-22 | 2025-04-04 | 165 | 119 | 2024-10-29 | 2024-11-11 | 14 | 10 | 2024-11-13 | 2025-04-16 | 36 | 26 | 2025-04-04 | Unknown | Unknown | Unknown | 2025-08-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SANTEE | N/A | 77 | 77 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-01 | 2024-10-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1624.87 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-01 | 2024-09-17 | Unknown | Unknown | 2024-09-17 | 2024-10-01 | 15 | 11 | 2024-10-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | NATIONAL CITY | N/A | 16.7 | 16.7 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-09 | Unknown | Unknown | No | 2025-05-21 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-21 | 2025-05-30 | Unknown | IOU Designed & Installed | N/A | Yes | 23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1172.72 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-21 | 2025-06-09 | 20 | 14 | 2025-06-09 | 2025-06-13 | 5 | 5 | 2025-06-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2021-09-09 | 2021-09-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 137141 | 3129.68 | Unknown | Unknown | Yes | N/A | N/A | 2021-09-09 | 2023-02-21 | 531 | 379 | 2023-02-21 | 2023-03-08 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | 2025-01-08 | 2025-01-09 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | JAMUL | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-14 | 2023-11-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3241 | 588.41 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-14 | 2023-09-28 | Unknown | Unknown | 2023-09-28 | 2023-11-14 | 48 | 34 | 2023-11-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-09 | 2025-01-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 12292.72 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-09 | 2025-01-09 | 1 | 1 | 2025-01-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SANTEE | N/A | 1024 | 1024 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2026-09-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-12 | 2025-06-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 89142 | 5969.32 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-12 | 2025-06-16 | 5 | 3 | 2025-06-16 | 2025-06-18 | 3 | 3 | 2025-06-13 | 2025-06-16 | 4 | 2 | Unknown | Unknown | Unknown | Unknown | 2025-06-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2022-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-19 | 2025-05-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2856.42 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-19 | 2025-05-19 | 1 | 1 | 2025-05-19 | 2025-06-11 | 24 | 18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-11 | 2025-06-23 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2025-07-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN JUAN CAPISTRANO | N/A | 19.05 | 19.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-19 | 2025-05-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2790.91 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-19 | 2025-06-02 | 15 | 11 | 2025-06-02 | 2025-06-11 | 10 | 8 | 2025-06-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-11 | 2025-07-28 | 48 | 34 | Unknown | 2025-07-16 | Unknown | Unknown | 2025-07-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SANTEE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-27 | 2024-03-27 | 2024-07-16 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 196.44 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-27 | 2024-07-09 | 105 | 75 | 2024-07-09 | 2024-07-09 | 1 | 1 | 2024-07-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-09 | 2024-07-16 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2024-07-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2021-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-18 | 2023-09-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 899.75 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-18 | 2023-10-10 | 23 | 17 | 2023-10-10 | 2023-10-10 | 1 | 1 | 2023-10-10 | 2023-10-10 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2023-10-10 | Unknown | Unknown | Unknown | Unknown | 2024-03-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Commercial | Disadvantaged Community,Underserved Community | Chula Vista | CHULA VISTA | 733 | 733 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-21 | 2024-02-21 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2024-02-21 | 2024-09-08 | 201 | 143 | 2024-09-08 | 2024-11-18 | 72 | 51 | 2024-08-16 | 2025-01-22 | 49 | 33 | 2024-09-03 | 2025-01-22 | 137 | 97 | 2025-08-28 | Unknown | Unknown | Unknown | 2025-08-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | MISSION VIEJO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-04-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2021-06-30 | 2021-06-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1115.8 | Unknown | Unknown | Yes | N/A | N/A | 2021-06-30 | 2025-03-05 | 1345 | 961 | 2025-03-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2021-06-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-29 | 2024-08-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1431.39 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-29 | 2024-08-21 | 24 | 18 | 2024-08-21 | 2024-08-29 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | 2024-08-21 | 2024-08-27 | 7 | 5 | 2024-08-29 | 2024-12-18 | 112 | 80 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | DANA POINT | N/A | 22.05 | 22.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-18 | 2024-07-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1503.68 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-18 | 2024-07-19 | 2 | 2 | 2024-07-19 | 2024-07-19 | 1 | 1 | 2024-07-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | CAPISTRANO BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-02 | 2025-06-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1301.52 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-02 | 2025-08-19 | 79 | 57 | 2025-08-19 | 2025-08-19 | 1 | 1 | 2025-08-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-25 | 2025-07-24 | 30 | 22 | Unknown | Unknown | Unknown | Unknown | 2025-07-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-05-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-12 | 2023-11-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 8370 | 493.62 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-12 | 2023-10-10 | 29 | 21 | 2023-10-10 | 2023-11-27 | 49 | 35 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | VISTA | VISTA | 2 | 2 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-31 | 2024-02-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1193.18 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-31 | 2024-01-24 | Unknown | Unknown | 2024-01-24 | 2024-03-08 | 45 | 33 | Unknown | Unknown | Unknown | Unknown | 2024-03-01 | 2024-07-09 | 55 | 39 | 2024-03-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-03 | 2023-08-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 496.37 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-03 | 2023-08-04 | 2 | 2 | 2023-08-04 | 2023-08-04 | 1 | 1 | 2023-08-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-21 | 2024-05-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 569.33 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-21 | 2024-05-30 | 10 | 8 | 2024-05-30 | 2024-07-03 | 35 | 25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-25 | 2025-03-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1684.66 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-25 | 2025-02-25 | Unknown | Unknown | 2025-02-25 | 2025-04-22 | 57 | 41 | Unknown | Unknown | Unknown | Unknown | 2025-04-02 | 2025-04-10 | 9 | 7 | 2025-04-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-13 | 2025-03-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 8571.87 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-13 | 2025-03-13 | 1 | 1 | 2025-03-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-11 | 2023-12-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 483.59 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-11 | 2023-12-11 | 1 | 1 | 2023-12-11 | 2023-12-15 | 5 | 5 | 2023-12-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-20 | 2025-03-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1184.45 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-20 | 2025-03-10 | 19 | 13 | 2025-03-10 | 2025-03-13 | 4 | 4 | 2025-03-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-13 | 2025-07-07 | 117 | 83 | Unknown | 2025-07-07 | Unknown | Unknown | 2025-07-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R29/R45) | Both | IOU Design | Commercial | N/A | CHULA VISTA | CHULA VISTA | 1620 | 1620 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2024-07-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-28 | 2024-07-31 | 2025-04-07 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 841139.99 | 503480.08 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-28 | 2024-09-04 | 435 | 311 | 2024-09-04 | 2025-03-27 | 205 | 147 | 2024-10-24 | 2025-07-22 | 46 | 32 | 2024-09-16 | 2025-08-06 | 166 | 120 | 2025-03-27 | Unknown | Unknown | Unknown | Unknown | 2025-04-24 | Unknown | Unknown | 2025-04-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-10 | 2025-03-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7196957 | 61788.11 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-10 | 2024-08-07 | Unknown | Unknown | 2024-08-07 | 2025-05-29 | 296 | 212 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | EL CAJON | N/A | 25.05 | 25.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-01 | 2024-08-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1050.75 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-01 | 2024-08-01 | 1 | 1 | 2024-08-01 | 2024-08-01 | 1 | 1 | 2024-08-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-03 | 2023-03-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 816.51 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-03 | 2023-03-03 | 1 | 1 | 2023-03-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-28 | 2023-02-28 | 2023-03-01 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 389.6 | Unknown | Unknown | Yes | N/A | N/A | 2023-02-28 | 2023-02-28 | 1 | 1 | 2023-02-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-28 | 2023-03-01 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2023-03-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SOUTH LAGUNA | SOUTH LAGUNA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-14 | 2023-08-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 998.32 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-14 | 2023-08-07 | Unknown | Unknown | 2023-08-07 | 2023-08-25 | 19 | 15 | 2023-08-25 | Unknown | Unknown | Unknown | 2023-08-25 | 2023-08-30 | 6 | 4 | 2023-08-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | Applicant Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2020-07-15 | 2020-07-15 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 559911.93 | Unknown | Unknown | Yes | N/A | N/A | 2020-07-15 | 2024-05-01 | 1387 | 991 | 2024-05-01 | 2025-06-25 | 421 | 301 | 2024-05-14 | 2025-09-03 | 155 | 109 | 2025-06-23 | 2025-08-22 | 61 | 45 | Unknown | Unknown | Unknown | Unknown | 2025-07-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-18 | Unknown | Unknown | No | 2025-04-01 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-01 | 2025-04-01 | 2025-04-14 | IOU Designed & Installed | N/A | Yes | 85 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 805.08 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-01 | 2025-06-25 | 86 | 62 | 2025-06-25 | 2025-04-10 | Unknown | Unknown | 2025-04-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-10 | 2025-04-14 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | 2025-04-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 18.75 | 18.75 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-23 | 2025-04-23 | 2025-05-28 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1543.84 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-23 | 2025-04-21 | Unknown | Unknown | 2025-04-21 | 2025-04-23 | 3 | 3 | 2025-04-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-23 | 2025-05-28 | 36 | 26 | Unknown | Unknown | Unknown | Unknown | 2025-05-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | CARDIFF | ENCINITAS | 1216 | 1216 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2026-09-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-10 | 2024-10-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1598.54 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-10 | 2024-10-17 | 8 | 6 | 2024-10-17 | 2024-10-28 | 12 | 8 | 2024-10-28 | Unknown | Unknown | Unknown | 2024-10-28 | 2024-12-06 | 40 | 30 | 2024-10-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN MARCOS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-03 | 2024-10-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1141.87 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-03 | 2024-08-26 | Unknown | Unknown | 2024-08-26 | 2024-10-17 | 53 | 39 | 2024-10-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LA MESA | N/A | 136.05 | 136.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-18 | 2023-08-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 372.47 | Unknown | Unknown | Yes | N/A | N/A | 2023-05-18 | 2023-03-22 | Unknown | Unknown | 2023-03-22 | 2024-05-29 | 435 | 311 | 2023-10-04 | 2023-10-04 | 1 | 1 | 2025-01-13 | 2025-01-13 | 1 | 1 | 2024-05-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 132 | 132 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-03-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-03 | 2024-07-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1419.04 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-03 | 2024-07-03 | 1 | 1 | 2024-07-03 | 2024-07-03 | 1 | 1 | 2024-07-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CORONADO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-10 | 2024-06-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 186.4 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-10 | 2024-06-17 | 8 | 6 | 2024-06-17 | 2024-06-17 | 1 | 1 | 2024-06-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | Applicant Design | Commercial | N/A | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-06 | 2023-10-06 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 608127.23 | 25534.59 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-06 | 2024-01-02 | 89 | 63 | 2024-01-02 | 2024-06-10 | 161 | 115 | 2024-01-09 | 2024-01-17 | 9 | 7 | 2024-06-10 | 2024-06-14 | 5 | 5 | 2024-06-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | CARLSBAD | N/A | 68 | 68 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-28 | 2025-03-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7962 | 1493.31 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-28 | 2025-03-14 | 15 | 11 | 2025-03-14 | 2025-05-06 | 54 | 38 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | 129.1 | 129.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-05 | 2024-09-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1050.75 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-05 | 2024-09-05 | 1 | 1 | 2024-09-05 | 2024-09-05 | 1 | 1 | 2024-09-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | DANA POINT | N/A | 243.05 | 243.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-25 | 2025-02-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1215.3 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-25 | 2025-02-18 | Unknown | Unknown | 2025-02-18 | 2025-03-04 | 15 | 11 | 2025-03-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-04 | 2025-08-12 | 162 | 116 | Unknown | 2025-07-29 | Unknown | Unknown | 2025-08-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-17 | 2025-04-17 | 2025-06-21 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3956.22 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-17 | 2025-04-16 | Unknown | Unknown | 2025-04-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-02 | 2025-04-02 | 2025-04-18 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3107.31 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-02 | 2025-04-04 | 3 | 3 | 2025-04-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN YSIDRO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-02-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-06 | 2023-03-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 334404 | 14805.81 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-06 | 2023-03-07 | 2 | 2 | 2023-03-07 | 2023-04-18 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-18 | 2025-03-26 | 709 | 507 | Unknown | 2025-03-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-06 | 2024-08-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3961 | 1454.16 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-06 | 2024-07-12 | Unknown | Unknown | 2024-07-12 | 2024-09-09 | 60 | 42 | 2024-09-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-06 | 2024-03-02 | 2024-03-06 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 308.87 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-06 | 2023-12-21 | Unknown | Unknown | 2023-12-21 | 2024-03-02 | 73 | 52 | 2024-03-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-02 | 2024-03-06 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | 2024-03-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-21 | 2024-06-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 443.54 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-21 | 2024-05-20 | 61 | 43 | 2024-05-20 | 2024-06-04 | 16 | 12 | 2024-06-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN MARCOS | SAN MARCOS | 205.15 | 205.15 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-08 | 2025-04-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2230.27 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-08 | 2025-02-27 | Unknown | Unknown | 2025-02-27 | 2025-04-08 | 41 | 29 | 2025-04-08 | Unknown | Unknown | Unknown | 2025-04-09 | 2025-05-05 | 27 | 19 | 2025-04-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | N/A | 165.25 | 165.25 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-06 | 2023-11-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 733.22 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-06 | 2023-11-06 | 1 | 1 | 2023-11-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-07 | 2024-05-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7320 | 584.27 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-07 | 2024-04-19 | Unknown | Unknown | 2024-04-19 | 2024-05-08 | 20 | 14 | 2024-05-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-08 | 2025-08-14 | 464 | 332 | Unknown | Unknown | Unknown | Unknown | 2025-08-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-05-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-10 | 2023-05-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 264.34 | Unknown | Unknown | Yes | N/A | N/A | 2023-05-10 | 2023-05-11 | 2 | 2 | 2023-05-11 | 2023-06-01 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-01 | 2023-07-06 | 36 | 26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | CORONADO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-20 | 2024-08-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1109.7 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-20 | 2024-08-01 | 43 | 31 | 2024-08-01 | 2024-06-28 | Unknown | Unknown | 2024-06-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 93.05 | 93.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-18 | 2025-06-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1293.84 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-18 | 2025-06-02 | Unknown | Unknown | 2025-06-02 | 2025-06-18 | 17 | 13 | 2025-06-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-18 | 2025-08-04 | 48 | 34 | Unknown | Unknown | Unknown | Unknown | 2025-08-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-24 | 2025-02-24 | 2025-02-28 | IOU Designed & Installed | N/A | No | Unknown | 50.92 | 0 | Unknown | Unknown | 12.91 | 38.01 | 3981 | 1642.85 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-24 | 2025-02-24 | 1 | 1 | 2025-02-24 | 2025-02-24 | 1 | 1 | 2025-02-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-24 | 2025-02-28 | 5 | 5 | Unknown | Unknown | Unknown | Unknown | 2025-02-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-26 | 2024-09-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 3066.36 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-26 | 2025-02-10 | 138 | 98 | 2025-02-10 | 2025-02-11 | 2 | 2 | 2025-02-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-26 | 2025-09-03 | 343 | 245 | Unknown | 2025-08-21 | Unknown | Unknown | 2025-09-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-27 | 2023-03-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 626.03 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-27 | 2023-03-27 | 1 | 1 | 2023-03-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | N/A | 9194.25 | 9194.25 | Not Available | >2MW | No | N/A | N/A | N/A | 2025-12-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-18 | 2024-03-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2112.73 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-18 | 2024-03-18 | 1 | 1 | 2024-03-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community,Tribal Community | LAKESIDE | COUNTY OF SAN DIEGO-SOUTH of 56 | 26.05 | 26.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-02 | 2024-08-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 50946.41 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-02 | 2024-06-28 | Unknown | Unknown | 2024-06-28 | 2025-07-29 | 397 | 283 | 2025-03-03 | 2025-09-04 | 4 | 2 | 2024-11-08 | 2025-08-07 | 13 | 9 | 2025-07-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | Both | IOU Design | Commercial | N/A | BONITA | COUNTY OF SAN DIEGO-SOUTH of 56 | 26 | 26 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-18 | 2024-02-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 1355333.64 | 123639.18 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-18 | 2023-10-30 | Unknown | Unknown | 2023-10-30 | 2025-06-05 | 585 | 419 | 2024-09-03 | 2025-02-06 | 22 | 16 | 2024-09-26 | 2025-03-10 | 24 | 18 | 2025-06-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | 71.5 | 71.5 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-11 | 2024-03-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 747.21 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-11 | 2024-02-06 | Unknown | Unknown | 2024-02-06 | 2024-03-13 | 37 | 27 | 2024-03-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-13 | 2025-08-06 | 512 | 366 | Unknown | Unknown | Unknown | Unknown | 2025-08-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-29 | 2025-05-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2025-05-29 | 2025-05-30 | 2 | 2 | 2025-05-30 | 2025-06-18 | 20 | 14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-02 | 2024-05-08 | 2024-07-30 | IOU Designed & Installed | N/A | No | Unknown | 665.23 | -12.92 | Unknown | Unknown | 25.08 | 653.07 | 3981 | 1116.35 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-02 | 2024-05-08 | 7 | 5 | 2024-05-08 | 2024-05-08 | 1 | 1 | 2024-05-08 | Unknown | Unknown | Unknown | 2024-05-10 | 2024-07-29 | 81 | 57 | 2024-05-08 | 2024-07-30 | 84 | 60 | Unknown | Unknown | Unknown | Unknown | 2024-07-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | COUNTY OF SAN DIEGO-SOUTH of 56, SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-26 | 2024-06-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 6882 | 812.52 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-26 | 2024-09-13 | 80 | 58 | 2024-09-13 | 2024-09-24 | 12 | 8 | 2024-10-09 | 2024-10-11 | 3 | 3 | 2024-09-13 | 2024-10-17 | 35 | 25 | 2024-09-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-22 | 2025-05-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 11943 | 1459.66 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-22 | 2025-05-22 | 1 | 1 | 2025-05-22 | 2025-07-01 | 41 | 29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-07-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-04 | 2025-03-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1196.61 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-04 | 2025-01-24 | Unknown | Unknown | 2025-01-24 | 2025-03-04 | 40 | 28 | 2025-03-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 425.05 | 425.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-02 | 2024-01-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 771.74 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-02 | 2024-04-26 | 116 | 84 | 2024-04-26 | 2024-05-07 | 12 | 8 | 2024-05-07 | 2024-12-03 | 211 | 151 | Unknown | Unknown | Unknown | Unknown | 2024-12-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 3 | 3 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-12 | 2024-07-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1877.96 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-12 | 2024-06-03 | Unknown | Unknown | 2024-06-03 | 2024-08-07 | 66 | 48 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 95 | 95 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-12 | 2025-02-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 407.1 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-12 | 2024-10-14 | Unknown | Unknown | 2024-10-14 | 2025-06-16 | 246 | 176 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-16 | 2025-07-15 | 30 | 22 | Unknown | 2025-08-18 | Unknown | Unknown | 2025-08-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-31 | 2024-11-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7962 | 1175.27 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-31 | 2025-01-10 | 72 | 52 | 2025-01-10 | 2024-12-23 | Unknown | Unknown | 2024-12-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-10 | 2025-07-22 | 194 | 138 | Unknown | 2025-07-07 | Unknown | Unknown | 2025-07-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 9.05 | 9.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-11 | 2024-04-11 | 2024-05-22 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3941 | 980.21 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-11 | 2024-02-14 | Unknown | Unknown | 2024-02-14 | 2024-04-11 | 58 | 42 | 2024-04-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-11 | 2024-05-22 | 42 | 30 | Unknown | Unknown | Unknown | Unknown | 2024-05-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 121.1 | 121.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-23 | 2025-05-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1080.02 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-23 | 2025-05-27 | 5 | 3 | 2025-05-27 | 2025-05-27 | 1 | 1 | 2025-05-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2022-02-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-20 | 2024-09-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2233.66 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-20 | 2024-12-12 | 84 | 60 | 2024-12-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-01 | 2024-12-06 | 36 | 26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 88 | 88 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-25 | 2025-06-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1106.3 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-25 | 2025-06-11 | Unknown | Unknown | 2025-06-11 | 2025-06-25 | 15 | 11 | 2025-06-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-25 | 2025-07-08 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | 2025-07-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-01 | 2024-05-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 998.32 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-01 | 2024-04-05 | Unknown | Unknown | 2024-04-05 | 2024-05-14 | 40 | 28 | 2024-05-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-02 | 2023-06-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 641.97 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-02 | 2023-06-15 | 14 | 10 | 2023-06-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 5.4 | 5.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-12 | 2024-07-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1604.54 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-12 | 2024-05-08 | Unknown | Unknown | 2024-05-08 | 2024-07-03 | 57 | 41 | 2024-07-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-04 | 2024-09-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 6344.86 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-04 | 2024-10-02 | 182 | 130 | 2024-10-02 | 2025-05-01 | 212 | 152 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-01 | 2025-09-08 | 131 | 93 | Unknown | 2025-09-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | Chula Vista | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-29 | 2024-05-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 1612132 | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2024-05-29 | 2024-05-22 | Unknown | Unknown | 2024-05-22 | 2024-06-27 | 37 | 27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-27 | 2025-09-05 | 436 | 312 | Unknown | Unknown | Unknown | Unknown | 2025-08-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-02 | 2023-11-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 826.11 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-02 | 2023-09-27 | Unknown | Unknown | 2023-09-27 | 2023-11-03 | 38 | 28 | 2023-11-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | LEMON GROVE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-14 | 2023-02-14 | 2023-03-12 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 182.09 | Unknown | Unknown | Yes | N/A | N/A | 2023-02-14 | 2023-02-14 | 1 | 1 | 2023-02-14 | 2023-02-21 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 51 | 51 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-02 | 2025-06-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1175.85 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-02 | 2025-06-13 | 12 | 10 | 2025-06-13 | 2025-06-13 | 1 | 1 | 2025-06-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-13 | 2025-07-08 | 26 | 18 | Unknown | Unknown | Unknown | Unknown | 2025-07-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | BOULEVARD | N/A | 84.05 | 84.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-08-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-20 | 2023-12-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 784.38 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-20 | 2023-08-30 | Unknown | Unknown | 2023-08-30 | 2023-12-26 | 119 | 85 | 2023-12-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SOUTH LAGUNA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-05 | 2024-06-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7962 | 1088.03 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-05 | 2024-06-24 | 20 | 14 | 2024-06-24 | 2024-06-28 | 5 | 5 | 2024-06-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | RANCHO MISSION VIEJO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-03 | 2025-06-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 4741 | 543.74 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-03 | 2025-06-03 | 1 | 1 | 2025-06-03 | 2025-07-09 | 37 | 27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-07-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | Both | IOU Design | Residential | Underserved Community | VISTA | N/A | 82.05 | 82.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-08 | 2024-12-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 3047.83 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-08 | 2024-12-13 | 159 | 115 | 2024-12-13 | 2024-12-13 | 1 | 1 | 2024-12-13 | 2025-03-24 | 102 | 72 | Unknown | Unknown | Unknown | Unknown | 2025-03-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN MARCOS | COUNTY OF SAN DIEGO-NORTH of 56 | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-27 | 2023-02-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 391.87 | Unknown | Unknown | Yes | N/A | N/A | 2023-02-27 | 2023-05-01 | 64 | 46 | 2023-05-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-07 | 2023-04-10 | 4 | 2 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-10 | 2025-03-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2122.53 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-10 | 2025-03-10 | 1 | 1 | 2025-03-10 | 2025-03-10 | 1 | 1 | 2025-03-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-08-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-15 | 2023-11-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1519.75 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-15 | 2023-11-07 | Unknown | Unknown | 2023-11-07 | 2023-11-15 | 9 | 7 | 2023-11-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-15 | Unknown | Unknown | Unknown | Unknown | 2025-08-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-14 | 2023-12-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 810.97 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-14 | 2023-11-27 | Unknown | Unknown | 2023-11-27 | 2023-12-14 | 18 | 14 | 2023-12-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | 39.05 | 39.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-20 | 2024-06-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2510.96 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-20 | 2024-05-13 | Unknown | Unknown | 2024-05-13 | 2024-08-02 | 82 | 60 | 2024-08-02 | 2024-08-13 | 12 | 8 | Unknown | Unknown | Unknown | Unknown | 2024-08-13 | Unknown | Unknown | Unknown | Unknown | 2025-05-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | N/A | 71 | 71 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-31 | 2024-10-31 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1275.29 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-31 | 2025-03-18 | 139 | 99 | 2025-03-18 | 2025-03-24 | 7 | 5 | 2025-03-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-24 | 2025-07-17 | 116 | 84 | Unknown | 2025-07-16 | Unknown | Unknown | 2025-07-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | N/A | 876.1 | 876.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-21 | 2025-04-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1538.56 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-21 | 2025-03-26 | 6 | 4 | 2025-03-26 | 2025-04-15 | 21 | 15 | 2025-04-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Commercial | Disadvantaged Community,Underserved Community | Chula Vista | CHULA VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-25 | 2024-09-25 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 22941.49 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-25 | 2025-03-05 | 162 | 116 | 2025-03-05 | 2025-06-02 | 90 | 64 | 2025-03-18 | 2025-07-08 | 11 | 9 | 2025-04-09 | 2025-07-08 | 51 | 37 | 2025-06-13 | Unknown | Unknown | Unknown | 2025-06-13 | 2025-06-26 | 14 | 10 | 2025-07-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | ESCONDIDO | 195.2 | 195.2 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-16 | 2024-06-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 117307 | 80920.48 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-16 | 2023-08-16 | 1 | 1 | 2023-08-16 | 2025-02-10 | 545 | 389 | 2024-09-30 | 2024-10-07 | 8 | 6 | 2024-09-27 | 2025-06-10 | 27 | 19 | 2025-02-10 | Unknown | Unknown | Unknown | Unknown | 2025-02-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-27 | 2023-03-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3885 | 574.62 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-27 | 2023-03-27 | 1 | 1 | 2023-03-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | VALLEY CENTER | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-06 | 2023-10-31 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 15127 | 4603.39 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-06 | 2023-09-11 | 6 | 4 | 2023-09-11 | Unknown | Unknown | Unknown | 2023-10-31 | 2024-03-14 | 136 | 98 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | NATIONAL CITY | NATIONAL CITY | 26 | 26 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-29 | 2023-10-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 19246 | 24623.37 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-29 | 2023-08-30 | 2 | 2 | 2023-08-30 | 2024-07-18 | 324 | 232 | 2024-04-17 | 2024-07-17 | 22 | 16 | 2024-07-17 | 2024-10-22 | 98 | 70 | 2024-07-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | Underserved Community | San Diego | San Diego | 9.05 | 9.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-29 | 2024-02-29 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 5203.64 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-29 | 2024-07-08 | 131 | 93 | 2024-07-08 | 2025-05-01 | 298 | 214 | 2024-10-23 | 2025-04-29 | 163 | 117 | 2025-03-10 | 2025-05-06 | 18 | 14 | 2025-05-15 | Unknown | Unknown | Unknown | 2025-05-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-29 | 2024-07-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 23991 | 677.91 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-29 | 2024-04-26 | Unknown | Unknown | 2024-04-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-29 | 2023-11-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 28804 | 257.93 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-29 | 2023-09-25 | Unknown | Unknown | 2023-09-25 | 2023-12-29 | 96 | 70 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2021-04-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-04 | 2024-03-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 401.61 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-04 | 2024-04-11 | 39 | 29 | 2024-04-11 | 2024-04-15 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | Both | IOU Design | Commercial | Underserved Community | Campo | COUNTY OF SAN DIEGO-SOUTH of 56 | 52 | 52 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-28 | 2023-12-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 49384.76 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-28 | 2023-12-01 | 157 | 113 | 2023-12-01 | 2024-07-24 | 237 | 169 | 2024-04-01 | 2024-04-02 | 2 | 2 | 2024-04-17 | 2024-08-22 | 48 | 36 | 2024-07-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2025-03-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-10 | 2024-10-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1437.85 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-10 | 2024-11-08 | 30 | 22 | 2024-11-08 | 2024-11-13 | 6 | 4 | 2024-11-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-13 | 2025-09-04 | 296 | 212 | Unknown | Unknown | Unknown | Unknown | 2025-09-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-18 | 2025-02-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1299.62 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-18 | 2025-02-24 | 7 | 5 | 2025-02-24 | 2025-02-24 | 1 | 1 | 2025-02-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-24 | 2025-07-18 | 145 | 105 | Unknown | 2025-06-17 | Unknown | Unknown | 2025-07-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2018-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-01 | 2023-11-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1336.7 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-01 | 2023-11-01 | 1 | 1 | 2023-11-01 | 2023-11-03 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-03 | 2023-11-13 | 11 | 7 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-10 | 2025-03-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1832.31 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-10 | 2025-02-27 | Unknown | Unknown | 2025-02-27 | 2025-03-10 | 12 | 8 | 2025-03-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-10 | 2025-07-28 | 141 | 101 | Unknown | Unknown | Unknown | Unknown | 2025-07-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | LAGUNA NIGUEL | LAGUNA NIGUEL | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-21 | 2025-05-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 344.44 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-21 | 2025-05-14 | Unknown | Unknown | 2025-05-14 | 2025-05-27 | 14 | 10 | 2025-05-27 | Unknown | Unknown | Unknown | 2025-05-23 | 2025-05-29 | 7 | 5 | 2025-05-27 | 2025-07-02 | 37 | 27 | Unknown | Unknown | Unknown | Unknown | 2025-07-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Residential | Underserved Community | CARLSBAD | CARLSBAD | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2019-12-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-15 | 2024-05-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 46191.87 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-15 | 2024-02-10 | Unknown | Unknown | 2024-02-10 | 2025-07-17 | 524 | 374 | 2024-12-23 | 2025-06-13 | 108 | 78 | 2024-12-19 | 2025-07-15 | 116 | 84 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-07-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-05 | 2025-01-31 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1207.66 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-05 | 2025-01-17 | 44 | 32 | 2025-01-17 | 2025-01-31 | 15 | 11 | 2025-01-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | N/A | 151.15 | 151.15 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-20 | 2024-01-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 999.55 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-20 | 2024-01-29 | 41 | 29 | 2024-01-29 | 2024-01-29 | 1 | 1 | 2024-01-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-29 | Unknown | Unknown | Unknown | Unknown | 2025-03-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-11-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-16 | 2024-12-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 668.21 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-16 | 2025-03-04 | 170 | 122 | 2025-03-04 | 2025-06-16 | 105 | 75 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-16 | 2025-04-23 | Unknown | Unknown | Unknown | 2025-09-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-14 | 2023-07-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3961 | 691.73 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-14 | 2023-08-21 | 39 | 27 | 2023-08-21 | 2023-08-21 | 1 | 1 | 2023-08-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-30 | 2024-05-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3599 | 511.69 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-30 | 2024-05-30 | 1 | 1 | 2024-05-30 | 2024-05-30 | 1 | 1 | 2024-05-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-16 | 2024-08-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 5106.85 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-16 | 2024-03-19 | 217 | 155 | 2024-03-19 | 2025-01-31 | 319 | 229 | 2025-08-13 | Unknown | Unknown | Unknown | 2024-08-15 | 2024-09-16 | 33 | 23 | 2025-01-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-31 | 2025-03-31 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2875.23 | 1880.05 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-31 | 2025-04-23 | 24 | 18 | 2025-04-23 | 2025-05-19 | 27 | 19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-04 | 2024-12-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 999.91 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-04 | 2024-11-27 | Unknown | Unknown | 2024-11-27 | 2024-12-13 | 17 | 13 | 2024-12-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-20 | 2023-07-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 163.83 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-20 | 2024-03-22 | 247 | 177 | 2024-03-22 | 2024-03-22 | 1 | 1 | 2024-03-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LEMON GROVE | N/A | 841 | 841 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-20 | 2024-05-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1435.75 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-20 | 2024-04-03 | Unknown | Unknown | 2024-04-03 | 2024-05-21 | 49 | 35 | 2024-05-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | Applicant Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-01-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-12 | 2023-04-12 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 41966.92 | Unknown | Unknown | Yes | N/A | N/A | 2023-04-12 | 2024-07-31 | 477 | 341 | 2024-07-31 | 2024-10-17 | 79 | 57 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 9.05 | 9.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-05 | 2025-05-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 786.62 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-05 | 2025-03-25 | Unknown | Unknown | 2025-03-25 | 2025-05-14 | 51 | 37 | 2025-05-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-14 | 2025-07-17 | 65 | 47 | Unknown | 2025-06-30 | Unknown | Unknown | 2025-07-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN MARCOS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-22 | 2024-01-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 746.52 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-22 | 2023-10-27 | Unknown | Unknown | 2023-10-27 | 2024-01-22 | 88 | 62 | 2024-01-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-23 | Unknown | Unknown | Unknown | Unknown | 2025-04-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | Applicant Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-28 | 2024-08-28 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 342004.14 | 78983.82 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-28 | 2025-01-09 | 135 | 97 | 2025-01-09 | 2025-05-16 | 128 | 92 | 2025-02-01 | 2025-04-09 | 22 | 16 | 2025-04-09 | 2025-04-14 | 6 | 4 | 2025-05-16 | Unknown | Unknown | Unknown | 2025-08-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-04 | 2024-01-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 829.46 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-04 | 2024-01-03 | Unknown | Unknown | 2024-01-03 | 2024-01-12 | 10 | 8 | 2024-01-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-27 | 2024-07-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2905.26 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-27 | 2023-10-18 | 22 | 16 | 2023-10-18 | 2024-11-25 | 405 | 289 | Unknown | Unknown | Unknown | Unknown | 2025-03-06 | 2025-03-06 | 1 | 1 | 2024-11-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-25 | Unknown | Unknown | No | 2024-05-02 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-02 | 2024-06-14 | 2024-06-17 | IOU Designed & Installed | N/A | Yes | 55 | -9.79 | -7.96 | Unknown | Unknown | Unknown | -1.83 | 3981 | 984.98 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-02 | 2024-06-26 | 56 | 40 | 2024-06-26 | 2024-06-26 | 1 | 1 | 2024-06-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-14 | 2024-06-17 | 4 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-06-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | CAPISTRANO BEACH | DANA POINT | 7 | 7 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-24 | 2023-04-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 808.83 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-24 | 2023-04-19 | 27 | 19 | 2023-04-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-19 | 2023-05-18 | 30 | 22 | 2023-04-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 11.05 | 11.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-27 | 2024-06-27 | 2025-03-31 | IOU Designed & Installed | N/A | No | Unknown | 402.98 | 0 | Unknown | Unknown | 17.93 | 385.05 | 3981 | 190.44 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-27 | 2024-10-12 | 108 | 77 | 2024-10-12 | 2024-11-13 | 33 | 23 | 2024-11-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-13 | 2025-03-31 | 139 | 99 | Unknown | Unknown | Unknown | Unknown | 2025-03-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 39.05 | 39.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-31 | 2025-01-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1420.25 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-31 | 2025-01-10 | 72 | 52 | 2025-01-10 | 2025-05-23 | 134 | 96 | 2025-05-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-23 | 2025-07-16 | 55 | 39 | Unknown | Unknown | Unknown | Unknown | 2025-07-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 5 | 5 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-23 | 2024-10-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1166.16 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-23 | 2024-11-07 | 16 | 12 | 2024-11-07 | 2024-11-07 | 1 | 1 | 2024-11-07 | 2024-11-13 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2024-11-13 | Unknown | Unknown | Unknown | Unknown | 2025-03-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 8 | 8 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-18 | 2025-02-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 189.89 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-18 | 2025-03-06 | 17 | 13 | 2025-03-06 | 2025-03-07 | 2 | 2 | 2025-03-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | COUNTY OF SAN DIEGO-NORTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-19 | 2024-07-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 10963.4 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-19 | 2024-09-25 | 69 | 49 | 2024-09-25 | 2025-01-03 | 101 | 73 | 2024-10-16 | 2024-10-21 | 6 | 4 | 2024-09-25 | 2024-10-29 | 2 | -2 | 2025-01-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-11 | 2022-10-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1188.75 | Unknown | Unknown | Yes | N/A | N/A | 2022-10-11 | 2023-03-23 | 164 | 118 | 2023-03-23 | 2023-04-25 | 34 | 24 | Unknown | Unknown | Unknown | Unknown | 2023-03-07 | 2023-03-13 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 10 | 10 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-25 | Unknown | Unknown | No | 2024-07-18 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-18 | 2024-07-18 | Unknown | IOU Designed & Installed | N/A | Yes | 370 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1160.44 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-18 | 2025-07-23 | 371 | 265 | 2025-07-23 | 2024-07-19 | Unknown | Unknown | 2024-07-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-19 | 2025-07-21 | 368 | 262 | Unknown | Unknown | Unknown | Unknown | 2025-07-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2025-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-20 | 2025-03-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 515.36 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-20 | 2025-03-20 | 1 | 1 | 2025-03-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | OCEANSIDE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-06-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-18 | 2025-06-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1345.26 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-18 | 2025-06-16 | Unknown | Unknown | 2025-06-16 | 2025-06-24 | 9 | 7 | 2025-06-24 | Unknown | Unknown | Unknown | 2025-06-25 | 2025-07-14 | 20 | 14 | 2025-06-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | DANA POINT | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-27 | 2025-06-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1170.55 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-27 | 2025-06-27 | 1 | 1 | 2025-06-27 | 2025-06-27 | 1 | 1 | 2025-06-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-27 | 2025-07-28 | 32 | 22 | Unknown | Unknown | Unknown | Unknown | 2025-07-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | MISSION VIEJO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-05-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-13 | 2023-06-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3991 | 415.36 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-13 | 2023-06-16 | 4 | 4 | 2023-06-16 | 2024-01-26 | 225 | 161 | 2024-01-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-22 | 2023-09-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 190.44 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-22 | 2024-11-22 | 428 | 306 | 2024-11-22 | 2024-12-13 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | 2024-11-23 | 2025-01-07 | 46 | 32 | 2024-12-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R29/R45 | UG | IOU Design | Commercial | Underserved Community | CHULA VISTA | CHULA VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-07 | 2024-03-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 63825.1 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-07 | 2024-06-06 | 213 | 153 | 2024-06-06 | 2025-01-13 | 222 | 158 | 2024-09-23 | 2025-06-16 | 25 | 17 | 2024-11-11 | 2024-12-31 | 24 | 18 | 2025-01-13 | 2025-07-11 | 180 | 130 | Unknown | 2025-07-28 | Unknown | Unknown | 2025-07-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LA MESA | N/A | 9.05 | 9.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-18 | 2025-03-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1243.05 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-18 | 2025-03-25 | 8 | 6 | 2025-03-25 | 2025-03-27 | 3 | 3 | 2025-03-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-15 | 2024-07-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2034.36 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-15 | 2024-05-10 | Unknown | Unknown | 2024-05-10 | 2025-02-05 | 272 | 194 | Unknown | Unknown | Unknown | Unknown | 2024-07-16 | 2024-08-13 | 29 | 21 | 2025-02-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 14 | 14 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-12 | 2024-08-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1342.22 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-12 | 2024-10-03 | 53 | 39 | 2024-10-03 | 2024-12-10 | 69 | 49 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-10 | Unknown | Unknown | Unknown | Unknown | 2025-09-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | OH | IOU Design | Residential | N/A | Encinitas | ENCINITAS | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-06-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-31 | 2023-03-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 10384.02 | Unknown | Unknown | Yes | N/A | N/A | 2023-01-31 | 2023-04-10 | 70 | 50 | 2023-04-10 | 2023-09-19 | 163 | 117 | 2023-08-10 | 2023-09-13 | 35 | 25 | 2023-05-26 | 2023-10-09 | 58 | 40 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 162.1 | 162.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-03 | 2025-02-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7962 | 2013.8 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-03 | 2025-01-23 | Unknown | Unknown | 2025-01-23 | 2025-02-04 | 13 | 9 | 2025-02-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-07 | 2024-08-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 1787 | 1329.35 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-07 | 2024-07-03 | Unknown | Unknown | 2024-07-03 | 2024-09-20 | 80 | 58 | Unknown | Unknown | Unknown | Unknown | 2024-08-13 | 2024-09-20 | 39 | 29 | 2024-09-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | 75.05 | 75.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-07 | 2025-05-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1091.24 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-07 | 2025-04-24 | Unknown | Unknown | 2025-04-24 | 2025-05-09 | 16 | 12 | 2025-05-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-09 | 2025-09-03 | 118 | 84 | Unknown | Unknown | Unknown | Unknown | 2025-09-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-25 | 2024-04-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 929.87 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-25 | 2024-04-23 | Unknown | Unknown | 2024-04-23 | 2024-04-25 | 3 | 3 | 2024-04-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | Disadvantaged Community,Underserved Community | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-04-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-14 | 2022-10-14 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 97729 | 21044.86 | Unknown | Unknown | Yes | N/A | N/A | 2022-10-14 | 2023-10-10 | 362 | 258 | 2023-10-10 | 2024-05-29 | 233 | 167 | 2023-12-21 | 2024-05-07 | 35 | 23 | 2023-12-28 | 2024-05-31 | 20 | 14 | 2025-04-07 | Unknown | Unknown | Unknown | 2025-04-07 | 2025-04-08 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | IOU Design | Commercial | Underserved Community | sm 1089-C7 | COUNTY OF SAN DIEGO-NORTH of 56 | 264.2 | 264.2 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-20 | 2024-03-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 89612 | 25515.35 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-20 | 2024-03-20 | 1 | 1 | 2024-03-20 | 2024-10-17 | 212 | 152 | 2024-08-19 | 2024-10-15 | 16 | 12 | 2024-10-19 | 2024-10-25 | 7 | 5 | 2024-10-17 | Unknown | Unknown | Unknown | 2025-03-28 | 2025-08-28 | 154 | 110 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-06 | Unknown | Unknown | No | 2024-02-14 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-14 | 2024-02-14 | Unknown | IOU Designed & Installed | N/A | Yes | 7 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 1787 | 615.37 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-14 | 2024-02-21 | 8 | 6 | 2024-02-21 | 2024-02-20 | Unknown | Unknown | 2024-02-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-27 | 2024-07-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3385.17 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-27 | 2024-07-10 | 288 | 206 | 2024-07-10 | 2024-11-20 | 134 | 96 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SOLANA BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-10 | 2024-04-16 | Unknown | Customer elected Applicant Install | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 381721 | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2024-04-10 | 2024-03-18 | Unknown | Unknown | 2024-03-18 | 2024-08-09 | 145 | 105 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-13 | 2024-08-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 27449 | 494.79 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-13 | 2024-09-09 | 28 | 20 | 2024-09-09 | 2024-09-09 | 1 | 1 | 2024-09-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 5 | 5 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-07-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-04 |  | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1611.19 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-04 | 2024-09-04 | 1 | 1 | 2024-09-04 | 2024-09-04 | 1 | 1 | 2024-09-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 7.05 | 7.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-08 | 2023-09-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 803.25 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-08 | 2023-06-28 | Unknown | Unknown | 2023-06-28 | 2023-09-08 | 73 | 53 | 2023-09-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | 105 | 105 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-10 | 2025-03-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2240.45 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-10 | 2025-02-10 | 1 | 1 | 2025-02-10 | 2025-03-13 | 32 | 24 | 2025-03-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-13 | Unknown | Unknown | Unknown | Unknown | 2025-03-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-22 | 2024-01-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1215.3 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-22 | 2024-01-03 | Unknown | Unknown | 2024-01-03 | 2024-02-02 | 31 | 23 | 2024-02-02 | 2025-01-15 | 349 | 249 | Unknown | Unknown | Unknown | Unknown | 2025-01-15 | Unknown | Unknown | Unknown | Unknown | 2025-06-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-03 | 2025-02-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1853.67 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-03 | 2025-01-31 | Unknown | Unknown | 2025-01-31 | 2025-02-03 | 4 | 2 | 2025-02-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-02 | 2025-06-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1203.84 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-02 | 2025-06-02 | 1 | 1 | 2025-06-02 | 2025-06-02 | 1 | 1 | 2025-06-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-02 | 2025-08-06 | 66 | 48 | Unknown | Unknown | Unknown | Unknown | 2025-08-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 51 | 51 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-08-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-14 | 2022-10-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 156.83 | Unknown | Unknown | Yes | N/A | N/A | 2022-10-14 | 2023-03-31 | 169 | 121 | 2023-03-31 | 2023-04-06 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-06 | Unknown | Unknown | Unknown | Unknown | 2023-04-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-18 | 2024-10-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2627.03 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-18 | 2024-10-10 | 23 | 17 | 2024-10-10 | 2024-10-29 | 20 | 14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 122 | 122 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-26 | 2024-01-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 746.52 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-26 | 2023-10-05 | Unknown | Unknown | 2023-10-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-20 | 2024-03-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3961 | 602.37 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-20 | 2024-02-22 | Unknown | Unknown | 2024-02-22 | 2024-03-28 | 36 | 26 | 2024-03-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | Applicant Design | Commercial | N/A | SD 1190-A2 CMR TS | COUNTY OF SAN DIEGO-NORTH of 56, SAN DIEGO | 222214 | 222214 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-03-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-03 | 2023-08-03 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 5056.29 | 11933.68 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-03 | 2023-12-20 | 140 | 100 | 2023-12-20 | 2024-05-09 | 142 | 102 | 2024-01-03 | 2024-05-02 | 110 | 80 | 2024-02-28 | 2025-03-12 | 36 | 26 | 2024-05-09 | Unknown | Unknown | Unknown | 2025-03-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | 46 | 46 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-10 | 2025-01-31 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7962 | 1889.15 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-10 | 2025-02-02 | 55 | 39 | 2025-02-02 | 2025-02-03 | 2 | 1 | Unknown | Unknown | Unknown | Unknown | 2025-02-03 | 2025-02-26 | 24 | 18 | 2025-02-03 | 2025-07-03 | 151 | 109 | Unknown | Unknown | Unknown | Unknown | 2025-07-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-01 | 2024-07-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2645.22 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-01 | 2024-05-30 | Unknown | Unknown | 2024-05-30 | 2024-07-26 | 58 | 42 | 2024-07-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 42.05 | 42.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-07 | 2024-05-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 801.56 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-07 | 2024-05-15 | 9 | 7 | 2024-05-15 | 2024-05-17 | 3 | 3 | 2024-05-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-24 | 2023-06-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 464.78 | Unknown | Unknown | Yes | N/A | N/A | 2023-04-24 | 2023-06-19 | 57 | 41 | 2023-06-19 | 2023-06-19 | 1 | 1 | 2023-06-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-09 | 2024-04-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 792168 | 18343.43 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-09 | 2024-04-15 | 7 | 5 | 2024-04-15 | 2024-04-18 | 4 | 4 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-07 | 2024-08-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 679.15 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-07 | 2024-08-02 | 423 | 303 | 2024-08-02 | 2024-08-14 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2024-08-08 | Unknown | Unknown | Unknown | 2024-08-14 | 2025-07-16 | 337 | 241 | Unknown | 2025-06-20 | Unknown | Unknown | 2025-08-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | ENCINITAS | N/A | 101.05 | 101.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-04 | 2023-12-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 483.59 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-04 | 2023-08-08 | Unknown | Unknown | 2023-08-08 | 2023-12-08 | 123 | 89 | 2023-12-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 5.4 | 5.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-13 | 2023-10-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2107.86 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-13 | 2023-11-08 | 27 | 19 | 2023-11-08 | 2023-11-08 | 1 | 1 | 2023-11-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | 48.05 | 48.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-03 | 2024-12-06 | 2025-06-30 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1575.47 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-03 | 2024-11-14 | Unknown | Unknown | 2024-11-14 | 2024-12-06 | 23 | 17 | 2024-12-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-06 | 2025-06-30 | 207 | 147 | Unknown | Unknown | Unknown | Unknown | 2025-06-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | MISSION VIEJO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-28 | 2024-08-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1220.55 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-28 | 2024-08-16 | Unknown | Unknown | 2024-08-16 | 2024-09-20 | 36 | 26 | 2024-09-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 10 | 10 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-24 | 2025-04-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1133.64 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-24 | 2025-04-25 | 2 | 2 | 2025-04-25 | 2025-04-29 | 5 | 3 | 2025-04-24 | 2025-04-29 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2025-04-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-11 | 2023-08-11 | 2023-09-18 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3961 | 153.83 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-11 | 2023-08-31 | 21 | 15 | 2023-08-31 | 2023-08-31 | 1 | 1 | 2023-08-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-31 | 2023-09-18 | 19 | 13 | Unknown | Unknown | Unknown | Unknown | 2023-09-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | Underserved Community | Alpine | COUNTY OF SAN DIEGO-NORTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-03-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-31 | 2022-08-31 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 32493.44 | Unknown | Unknown | Yes | N/A | N/A | 2022-08-31 | 2024-02-08 | 527 | 377 | 2024-02-08 | 2024-05-30 | 113 | 81 | 2024-02-23 | 2024-05-14 | 41 | 27 | 2024-05-21 | 2024-06-21 | 32 | 24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2024-03-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-10 | 2024-01-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 439.15 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-10 | 2024-01-10 | 1 | 1 | 2024-01-10 | 2024-04-26 | 108 | 78 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | Underserved Community | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-20 | 2024-08-20 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 48154 | 59132.54 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-20 | 2024-10-24 | 66 | 48 | 2024-10-24 | 2025-05-08 | 197 | 141 | 2024-11-05 | 2025-04-25 | 57 | 43 | 2024-12-11 | 2025-07-08 | 58 | 42 | 2025-08-20 | Unknown | Unknown | Unknown | 2025-08-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R29/R45) | UG | IOU Design | Commercial | Underserved Community | SAN MARCOS | SAN MARCOS | 1200 | 1200 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2024-07-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-22 | 2023-06-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 710262 | 339080.32 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-22 | 2024-04-16 | 300 | 214 | 2024-04-16 | 2025-03-21 | 340 | 244 | 2024-11-19 | 2025-03-05 | 5 | 5 | 2023-11-09 | 2025-06-26 | 171 | 125 | 2025-03-21 | Unknown | Unknown | Unknown | 2025-07-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CAMPO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-18 | 2024-07-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3941 | 992.73 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-18 | 2024-06-14 | Unknown | Unknown | 2024-06-14 | 2024-07-18 | 35 | 25 | 2024-07-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-09 | 2025-04-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1650.37 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-09 | 2025-03-24 | Unknown | Unknown | 2025-03-24 | 2025-03-24 | 1 | 1 | 2025-03-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-24 | 2025-04-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1174.98 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-24 | 2025-04-30 | 7 | 5 | 2025-04-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-30 | 2025-07-21 | 83 | 59 | Unknown | Unknown | Unknown | Unknown | 2025-07-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SOUTH LAGUNA | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-05 | 2024-06-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1446.72 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-05 | 2024-06-04 | Unknown | Unknown | 2024-06-04 | 2024-06-06 | 3 | 3 | 2024-06-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | 142.45 | 142.45 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-22 | 2024-08-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 4997 | 48607.39 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-22 | 2024-08-22 | 1 | 1 | 2024-08-22 | 2025-05-06 | 258 | 184 | 2025-04-10 | 2025-05-02 | 23 | 17 | 2025-04-10 | 2025-05-08 | 11 | 9 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-12 | 2025-05-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1124.95 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-12 | 2025-04-21 | Unknown | Unknown | 2025-04-21 | 2025-05-15 | 25 | 19 | 2025-05-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-15 | 2025-07-21 | 68 | 48 | Unknown | Unknown | Unknown | Unknown | 2025-07-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-05 | 2023-09-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 849.37 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-05 | 2023-09-12 | 8 | 6 | 2023-09-12 | 2023-12-08 | 88 | 64 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | OCEANSIDE | N/A | 13016.2 | 13016.2 | Not Available | >2MW | No | N/A | N/A | N/A | 2025-10-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-12 | 2025-01-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1548.27 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-12 | 2024-01-07 | Unknown | Unknown | 2024-01-07 | 2025-06-17 | 528 | 377 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-29 | 2024-07-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 9149 | 511.86 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-29 | 2024-07-17 | Unknown | Unknown | 2024-07-17 | 2024-07-29 | 13 | 9 | 2024-07-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | Applicant Design | Residential | Underserved Community | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-19 | 2024-11-25 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 10543.17 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-19 | 2023-04-21 | Unknown | Unknown | 2023-04-21 | 2025-01-23 | 644 | 460 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-08-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-30 | 2024-08-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7995 | 511.86 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-30 | 2024-08-30 | 1 | 1 | 2024-08-30 | 2024-08-30 | 1 | 1 | 2024-08-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | OH | IOU Design | Residential | Underserved Community | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-07 | 2024-09-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 39028.28 | 44065.04 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-07 | 2024-07-11 | 35 | 25 | 2024-07-11 | 2025-01-10 | 184 | 132 | Unknown | Unknown | Unknown | Unknown | 2024-10-10 | 2025-01-17 | 49 | 35 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-07 | Unknown | Unknown | No | 2023-04-10 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-10 | 2023-04-10 | Unknown | IOU Designed & Installed | N/A | Yes | 490 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 93350 | 8931.34 | Unknown | Unknown | Yes | N/A | N/A | 2023-04-10 | 2024-07-16 | 464 | 332 | 2024-07-16 | 2023-06-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 23.05 | 23.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-03 | 2025-02-03 | 2025-06-18 | IOU Designed & Installed | N/A | No | Unknown | 438.52 | 0 | Unknown | Unknown | 11.21 | 427.31 | 3981 | 1174.83 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-03 | 2025-04-28 | 85 | 61 | 2025-04-28 | 2025-04-28 | 1 | 1 | 2025-04-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-28 | 2025-06-18 | 52 | 38 | Unknown | Unknown | Unknown | Unknown | 2025-06-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-20 | 2025-03-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1736.89 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-20 | 2025-03-20 | 1 | 1 | 2025-03-20 | 2025-03-20 | 1 | 1 | 2025-03-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | CHULA VISTA | 67 | 67 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-03-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-21 | 2023-09-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7962 | 574.08 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-21 | 2023-07-13 | Unknown | Unknown | 2023-07-13 | 2023-10-16 | 96 | 68 | Unknown | Unknown | Unknown | Unknown | 2023-10-09 | 2023-10-13 | 5 | 5 | 2023-10-16 | Unknown | Unknown | Unknown | Unknown | 2024-10-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-25 | 2024-04-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3961 | 1397.81 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-25 | 2024-07-03 | 70 | 50 | 2024-07-03 | 2024-07-22 | 20 | 14 | 2024-07-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | NCTD-Trolly North of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-19 | 2025-02-19 | 2025-06-17 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 415.96 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-19 | 2025-03-05 | 15 | 11 | 2025-03-05 | 2025-06-02 | 90 | 64 | Unknown | Unknown | Unknown | Unknown | 2025-02-24 | 2025-03-04 | 9 | 7 | 2025-06-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | MISSION VIEJO | N/A | 44.05 | 44.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-18 | 2023-09-18 | 2023-11-05 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 154.99 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-18 | 2023-09-26 | 9 | 7 | 2023-09-26 | 2023-10-02 | 7 | 5 | 2023-10-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-02 | 2023-11-05 | 35 | 25 | Unknown | Unknown | Unknown | Unknown | 2023-11-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | Chula Vista | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-05 | 2024-06-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3306511 | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2024-06-05 | 2024-05-24 | Unknown | Unknown | 2024-05-24 | 2024-07-10 | 48 | 34 | Unknown | Unknown | Unknown | Unknown | 2024-06-26 | 2024-06-26 | 1 | 1 | 2024-07-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-26 | 2025-03-26 | 2025-05-30 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1439.49 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-26 | 2025-04-08 | 14 | 10 | 2025-04-08 | 2025-04-23 | 16 | 12 | 2025-04-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-21 | 2025-05-30 | 40 | 30 | Unknown | Unknown | Unknown | Unknown | 2025-05-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SANTEE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-01 | 2024-03-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 125174 | 11110.66 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-01 | 2024-04-15 | 137 | 97 | 2024-04-15 | 2024-05-13 | 29 | 21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-13 | 2025-05-02 | 355 | 255 | Unknown | 2025-05-22 | Unknown | Unknown | 2025-07-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | POWAY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-19 | 2024-12-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1186.03 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-19 | 2025-01-31 | 44 | 32 | 2025-01-31 | 2025-01-31 | 1 | 1 | 2025-01-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-10 | 2024-11-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1181.83 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-10 | 2024-09-18 | Unknown | Unknown | 2024-09-18 | 2024-11-04 | 48 | 34 | 2024-11-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-02 | 2024-01-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 44678 | 17644.22 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-02 | 2024-03-29 | 88 | 64 | 2024-03-29 | 2024-05-07 | 40 | 28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | Underserved Community | Chula Vista | CHULA VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-02-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-01 | 2022-09-01 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 37512.53 | Unknown | Unknown | Yes | N/A | N/A | 2022-09-01 | 2024-05-08 | 616 | 440 | 2024-05-08 | 2024-08-29 | 114 | 82 | 2024-04-08 | 2024-07-17 | 18 | 14 | 2024-06-05 | 2024-09-04 | 47 | 35 | 2024-09-10 | Unknown | Unknown | Unknown | 2024-09-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 18 | 18 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-03 | 2025-01-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1634.17 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-03 | 2025-01-13 | 11 | 7 | 2025-01-13 | 2025-01-14 | 2 | 2 | 2025-01-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | BONITA | N/A | 6.05 | 6.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-09 | 2024-11-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1223.23 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-09 | 2024-11-15 | 38 | 28 | 2024-11-15 | 2024-12-23 | 39 | 27 | 2024-12-23 | 2025-01-08 | 17 | 13 | Unknown | Unknown | Unknown | Unknown | 2024-12-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 18.05 | 18.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-06 | 2024-02-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 534.53 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-06 | 2024-02-06 | 1 | 1 | 2024-02-06 | 2024-02-06 | 1 | 1 | 2024-02-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-06 | 2023-11-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 34387 | 9036.5 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-06 | 2023-10-19 | 14 | 10 | 2023-10-19 | 2023-11-13 | 26 | 18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 84.05 | 84.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-27 | 2023-12-27 | 2024-01-03 | IOU Designed & Installed | N/A | No | Unknown | 1175.04 | 710.21 | Unknown | Unknown | Unknown | 464.83 | 0 | 515.81 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-27 | 2023-12-27 | 1 | 1 | 2023-12-27 | 2023-12-27 | 1 | 1 | 2023-12-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-14 | 2024-01-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Commercial | Underserved Community | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-10-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-09 | 2024-05-09 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1983.27 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-09 | 2024-08-08 | 92 | 66 | 2024-08-08 | Unknown | Unknown | Unknown | 2024-02-26 | 2024-08-07 | 164 | 118 | 2024-12-10 | 2025-02-25 | -2 | -4 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-16 | 2025-01-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3207.26 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-16 | 2025-01-16 | 1 | 1 | 2025-01-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-25 | 2025-03-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1745.58 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-25 | 2025-08-26 | 155 | 111 | 2025-08-26 | 2025-03-27 | Unknown | Unknown | 2025-03-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-20 | 2024-09-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7088 | 5271.94 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-20 | 2024-08-29 | 10 | 8 | 2024-08-29 | 2024-10-10 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-10 | 2025-06-06 | 240 | 172 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 832.75 | 832.75 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-27 | 2025-03-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2373.68 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-27 | 2025-03-03 | Unknown | Unknown | 2025-03-03 | 2025-03-27 | 25 | 19 | 2025-03-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-27 | 2025-07-22 | 118 | 84 | Unknown | Unknown | Unknown | Unknown | 2025-07-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-11 | 2024-10-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 9601 | 525.39 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-11 | 2024-07-16 | Unknown | Unknown | 2024-07-16 | 2024-10-11 | 88 | 64 | 2024-10-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 16.4 | 16.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-04 | 2024-06-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1134.87 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-04 | 2024-03-21 | Unknown | Unknown | 2024-03-21 | 2024-08-05 | 138 | 98 | 2024-08-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | Both | IOU Design | Residential | Underserved Community | LA MESA | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-29 | 2024-07-30 | 2025-06-19 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2567.26 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-29 | 2024-07-30 | 2 | 2 | 2024-07-30 | 2025-04-23 | 268 | 192 | Unknown | Unknown | Unknown | Unknown | 2024-07-30 | 2024-08-02 | 4 | 4 | 2025-04-23 | Unknown | Unknown | Unknown | Unknown | 2025-06-03 | Unknown | Unknown | 2025-06-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | COTO DE CAZA | N/A | 191 | 191 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-22 | 2025-01-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1213.24 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-22 | 2025-01-08 | Unknown | Unknown | 2025-01-08 | 2025-02-07 | 31 | 23 | 2025-02-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | OH | IOU Design | Commercial | Disadvantaged Community,Underserved Community | El Cajon | COUNTY OF SAN DIEGO-SOUTH of 56, EL CAJON | 218 | 218 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-27 | 2024-04-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 43875.89 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-27 | 2024-03-27 | 1 | 1 | 2024-03-27 | 2025-06-19 | 450 | 322 | 2024-11-13 | 2025-06-18 | 218 | 156 | 2024-08-01 | 2025-08-04 | 72 | 48 | 2025-06-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-08-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-04-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-15 | 2024-05-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2733 | Unknown | Unknown | Yes | N/A | N/A | 2022-04-15 | 2024-05-17 | 764 | 546 | 2024-05-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | POWAY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-24 | 2024-12-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1854.67 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-24 | 2024-10-31 | 8 | 6 | 2024-10-31 | 2024-12-23 | 54 | 38 | 2024-12-23 | 2025-01-07 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | 2025-01-07 | 2025-08-28 | 234 | 168 | Unknown | Unknown | Unknown | Unknown | 2025-08-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-08 | 2023-11-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | -292.99 | 0 | Unknown | Unknown | Unknown | -292.99 | 0 | 288.94 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-08 | 2023-12-04 | 27 | 19 | 2023-12-04 | 2024-08-09 | 250 | 180 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-09 | Unknown | Unknown | Unknown | Unknown | 2025-02-24 | Unknown | Unknown | 2025-07-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 3884.75 | 3884.75 | Not Available | >2MW | No | N/A | N/A | N/A | 2025-06-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-07 | 2025-03-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3078.15 | 18962.17 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-07 | 2025-02-06 | 184 | 132 | 2025-02-06 | 2025-05-19 | 103 | 73 | 2025-03-04 | 2025-03-04 | 1 | 1 | 2025-05-17 | 2025-06-06 | 21 | 15 | 2025-05-19 | Unknown | Unknown | Unknown | 2025-06-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-22 | 2025-04-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1049.53 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-22 | 2025-04-22 | 1 | 1 | 2025-04-22 | 2025-04-22 | 1 | 1 | 2025-04-22 | Unknown | Unknown | Unknown | 2025-04-23 | 2025-05-01 | 9 | 7 | 2025-04-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-03-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-03 | 2024-01-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 630.35 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-03 | 2024-02-06 | 35 | 25 | 2024-02-06 | 2024-09-03 | 211 | 151 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Residential | Underserved Community | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-08 | 2024-12-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 47039.87 | 40462.5 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-08 | 2024-12-02 | 270 | 192 | 2024-12-02 | 2025-07-01 | 212 | 152 | 2025-03-17 | 2025-06-20 | 15 | 11 | 2025-04-07 | 2025-07-09 | 29 | 21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | POWAY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-09 | 2025-02-09 | 2025-06-26 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1275.29 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-09 | 2025-03-18 | 38 | 27 | 2025-03-18 | 2025-03-19 | 2 | 2 | 2025-03-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-19 | 2025-06-26 | 100 | 72 | Unknown | 2025-06-24 | Unknown | Unknown | 2025-06-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-23 | 2024-05-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3047.18 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-23 | 2024-05-23 | 1 | 1 | 2024-05-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | JULIAN | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-14 | 2023-06-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1589.92 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-14 | 2023-06-14 | 1 | 1 | 2023-06-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R29/R45 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | 1935 | 1935 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2024-11-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-07 | 2024-01-31 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 129088.29 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-07 | 2024-03-29 | 144 | 104 | 2024-03-29 | 2025-04-15 | 383 | 273 | 2024-05-24 | 2025-01-14 | 81 | 57 | 2024-09-05 | 2024-10-03 | 26 | 16 | 2025-04-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 45.05 | 45.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-07 | 2023-08-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 496.37 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-07 | 2023-08-19 | 13 | 10 | 2023-08-19 | 2023-08-19 | 1 | 0 | 2023-08-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-28 | 2025-03-31 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1780.12 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-28 | 2025-02-27 | Unknown | Unknown | 2025-02-27 | 2025-03-28 | 30 | 22 | 2025-03-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-16 | 2024-05-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2036.86 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-16 | 2024-05-16 | 1 | 1 | 2024-05-16 | 2024-05-16 | 1 | 1 | 2024-05-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | CHULA VISTA | CHULA VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-11 | 2025-04-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 1673 | 521.49 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-11 | 2025-04-07 | Unknown | Unknown | 2025-04-07 | 2025-05-27 | 51 | 37 | Unknown | Unknown | Unknown | Unknown | 2025-04-29 | 2025-05-06 | 8 | 6 | 2025-05-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-20 | 2023-10-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 817.53 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-20 | 2023-09-07 | Unknown | Unknown | 2023-09-07 | 2023-10-26 | 50 | 36 | 2023-10-26 | Unknown | Unknown | Unknown | 2023-10-30 | 2023-11-01 | 3 | 3 | 2023-10-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | OH | IOU Design | Residential | N/A | Encinitas | ENCINITAS | 95 | 95 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-15 | 2024-11-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 38932.29 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-15 | 2024-10-14 | Unknown | Unknown | 2024-10-14 | 2025-06-16 | 246 | 176 | 2025-05-21 | 2025-07-14 | 37 | 27 | 2025-01-02 | 2025-06-26 | 176 | 126 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-08-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | DANA POINT | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-04 | Unknown | Unknown | No | 2023-10-18 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-18 | 2023-10-18 | 2025-06-11 | IOU Designed & Installed | N/A | Yes | 189 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 448.66 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-18 | 2024-04-24 | 190 | 136 | 2024-04-24 | 2024-04-24 | 1 | 1 | 2024-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-18 | 2025-06-11 | 603 | 431 | Unknown | 2025-07-10 | Unknown | Unknown | 2025-06-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | POWAY | N/A | 1409 | 1409 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2026-10-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-03 | 2024-12-03 | 2024-12-16 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2121.36 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-03 | 2024-12-03 | 1 | 1 | 2024-12-03 | 2024-12-13 | 11 | 9 | 2024-12-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-13 | 2024-12-16 | 4 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-12-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-13 | 2023-10-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3961 | 158.14 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-13 | 2023-07-25 | Unknown | Unknown | 2023-07-25 | 2023-11-27 | 126 | 90 | 2023-11-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | Underserved Community | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-11 | 2022-11-11 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 43948.82 | 16200.17 | Unknown | Unknown | Yes | N/A | N/A | 2022-11-11 | 2023-06-26 | 228 | 162 | 2023-06-26 | 2024-04-17 | 297 | 213 | 2023-06-26 | 2024-03-26 | 115 | 83 | 2023-12-30 | 2024-04-23 | 19 | 13 | 2024-09-25 | Unknown | Unknown | Unknown | 2024-09-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 15.05 | 15.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-17 | 2025-03-17 | 2025-06-23 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1206.25 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-17 | 2025-03-05 | Unknown | Unknown | 2025-03-05 | 2025-05-01 | 58 | 42 | 2025-05-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-01 | 2025-06-23 | 54 | 38 | Unknown | Unknown | Unknown | Unknown | 2025-06-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | POWAY | COUNTY OF SAN DIEGO-NORTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-09 | 2025-05-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2387.65 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-09 | 2025-05-12 | 4 | 2 | 2025-05-12 | 2025-05-12 | 1 | 1 | 2025-05-12 | 2025-05-21 | 10 | 8 | 2025-05-12 | 2025-05-27 | 10 | 6 | 2025-05-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | LAGUNA NIGUEL | N/A | 64 | 64 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-10 | 2025-04-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 821.95 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-10 | 2025-04-23 | 14 | 10 | 2025-04-23 | 2025-04-23 | 1 | 1 | 2025-04-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2019-03-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-13 | 2024-10-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3412.24 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-13 | 2024-10-01 | 50 | 36 | 2024-10-01 | 2024-11-08 | 39 | 29 | Unknown | Unknown | Unknown | Unknown | 2024-10-01 | 2024-11-01 | 32 | 24 | 2024-11-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 68.05 | 68.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-16 | 2025-02-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1589.1 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-16 | 2025-02-03 | 19 | 13 | 2025-02-03 | 2025-02-03 | 1 | 1 | 2025-02-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2026-03-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-06 | 2024-08-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 54814.9 | 11758.73 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-06 | 2024-08-21 | 16 | 12 | 2024-08-21 | 2025-06-18 | 302 | 216 | 2025-06-09 | 2025-06-09 | 1 | 1 | 2024-09-19 | 2025-06-26 | 41 | 29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-25 | 2025-02-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 196.44 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-25 | 2025-02-14 | Unknown | Unknown | 2025-02-14 | 2025-02-26 | 13 | 9 | 2025-02-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | CHULA VISTA | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-22 | 2023-08-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3496.8 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-22 | 2024-06-25 | 309 | 221 | 2024-06-25 | 2024-06-28 | 4 | 4 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-28 | 2024-09-04 | 69 | 49 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-28 | 2023-11-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 1379 | 652.76 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-28 | 2024-01-02 | 36 | 26 | 2024-01-02 | 2024-04-05 | 95 | 69 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-25 | 2024-12-31 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1049.51 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-25 | 2024-12-02 | 8 | 6 | 2024-12-02 | 2024-12-31 | 30 | 22 | 2024-12-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community,Tribal Community | LAKESIDE | COUNTY OF SAN DIEGO-SOUTH of 56 | 51.15 | 51.15 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-27 | 2024-08-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 13964.48 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-27 | 2024-06-28 | 94 | 68 | 2024-06-28 | 2025-07-29 | 397 | 283 | 2024-12-30 | 2025-01-16 | 18 | 14 | 2024-09-27 | 2025-08-08 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-18 | 2025-04-23 | 2025-06-25 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 798.66 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-18 | 2025-05-14 | 27 | 19 | 2025-05-14 | 2025-05-14 | 1 | 1 | 2025-05-09 | 2025-06-05 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | 2025-06-06 | 2025-06-25 | 20 | 14 | Unknown | 2025-06-20 | Unknown | Unknown | 2025-06-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 196.1 | 196.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-23 | 2024-08-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3336.08 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-23 | 2024-08-23 | 1 | 1 | 2024-08-23 | 2024-08-23 | 1 | 1 | 2024-08-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 188.1 | 188.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-15 | 2024-08-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3961 | 1411.69 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-15 | 2024-07-19 | Unknown | Unknown | 2024-07-19 | 2024-08-30 | 43 | 31 | 2024-08-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-14 | 2025-05-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1434.91 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-14 | 2025-05-09 | Unknown | Unknown | 2025-05-09 | 2025-05-14 | 6 | 4 | 2025-05-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | ALPINE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-03-10 | Unknown | Unknown | No | 2022-04-07 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-07 | 2022-04-07 | Unknown | IOU Designed & Installed | N/A | Yes | 707 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3885 | 1004.33 | Unknown | Unknown | Yes | N/A | N/A | 2022-04-07 | 2024-03-14 | 708 | 506 | 2024-03-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2022-05-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-01 | Unknown | Unknown | No | 2023-03-06 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-06 | 2023-03-06 | Unknown | IOU Designed & Installed | N/A | Yes | 343 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1028.45 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-06 | 2024-02-12 | 344 | 246 | 2024-02-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | 46 | 46 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-30 | 2024-07-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1961.2 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-30 | 2024-07-01 | Unknown | Unknown | 2024-07-01 | 2024-10-01 | 93 | 67 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-05-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-05 | 2022-05-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 32438 | 6124.75 | Unknown | Unknown | Yes | N/A | N/A | 2022-05-05 | 2023-09-01 | 485 | 347 | 2023-09-01 | 2023-10-13 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-09 | 2025-05-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2047.68 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-09 | 2025-05-16 | 8 | 6 | 2025-05-16 | 2025-05-21 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-13 | 2023-10-13 | 2023-11-07 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 153.22 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-13 | 2023-08-30 | Unknown | Unknown | 2023-08-30 | 2023-10-13 | 45 | 33 | 2023-10-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-13 | 2023-11-07 | 26 | 18 | Unknown | Unknown | Unknown | Unknown | 2023-11-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | N/A | 112 | 112 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-22 | 2023-04-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 1500 | 1188.62 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-22 | 2023-04-13 | 23 | 17 | 2023-04-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 9.05 | 9.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-23 | 2024-05-23 | 2024-07-19 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3941 | 1372.9 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-23 | 2024-04-08 | Unknown | Unknown | 2024-04-08 | 2024-05-23 | 46 | 34 | 2024-05-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-23 | 2024-07-19 | 58 | 42 | Unknown | Unknown | Unknown | Unknown | 2024-07-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | CAPISTRANO BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-12 | 2025-06-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1283.43 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-12 | 2025-06-12 | 1 | 1 | 2025-06-12 | 2025-06-12 | 1 | 1 | 2025-06-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-12 | 2025-08-20 | 70 | 50 | Unknown | Unknown | Unknown | Unknown | 2025-08-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 14 | 14 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-08 | Unknown | Unknown | No | 2023-06-05 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-05 | 2024-02-09 | 2025-05-29 | IOU Designed & Installed | N/A | Yes | 344 | 301.5 | 0 | Unknown | Unknown | 14.04 | 287.46 | 3981 | 1122.72 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-05 | 2024-05-13 | 344 | 246 | 2024-05-13 | 2024-09-25 | 136 | 98 | 2024-09-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-14 | 2025-05-29 | 381 | 273 | Unknown | Unknown | Unknown | Unknown | 2025-05-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SANTEE | N/A | 60 | 60 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-27 | 2024-09-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 23855 | 1013.33 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-27 | 2024-09-27 | 1 | 1 | 2024-09-27 | 2024-10-17 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 1.35 | 1.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-24 | 2025-04-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1155.36 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-24 | 2025-04-24 | 1 | 1 | 2025-04-24 | 2025-04-24 | 1 | 1 | 2025-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-24 | 2025-07-10 | 78 | 56 | Unknown | Unknown | Unknown | Unknown | 2025-07-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | Applicant Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-25 | 2025-02-05 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 4132.59 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-25 | 2025-03-20 | 116 | 84 | 2025-03-20 | 2025-06-10 | 83 | 59 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2020-01-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-30 | 2023-07-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1110.36 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-30 | 2023-07-26 | Unknown | Unknown | 2023-07-26 | 2023-07-30 | 5 | 3 | 2023-07-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | CARLSBAD | N/A | 64.15 | 64.15 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-28 | 2024-07-10 | 2025-06-24 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1130.31 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-28 | 2024-06-26 | Unknown | Unknown | 2024-06-26 | 2024-07-10 | 15 | 11 | 2024-07-10 | 2025-06-18 | 344 | 246 | Unknown | Unknown | Unknown | Unknown | 2025-06-24 | 2025-06-24 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2025-06-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-28 | 2023-02-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3991 | 642.35 | Unknown | Unknown | Yes | N/A | N/A | 2023-02-28 | 2023-02-28 | 1 | 1 | 2023-02-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN JUAN CAPISTRANO | N/A | 12 | 12 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | 2025-04-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1442.8 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-07 | 2025-04-17 | 11 | 9 | 2025-04-17 | 2025-04-17 | 1 | 1 | 2025-04-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-17 | Unknown | Unknown | Unknown | Unknown | 2025-06-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | VALLEY CENTER | N/A | 67.05 | 67.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-10 | 2023-04-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 611.23 | Unknown | Unknown | Yes | N/A | N/A | 2023-04-10 | 2023-04-17 | 8 | 6 | 2023-04-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN JUAN CAPISTRANO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-05 | 2025-02-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 28625 | 3118 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-05 | 2025-02-05 | 1 | 1 | 2025-02-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-05 | 2023-07-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2297.37 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-05 | 2023-05-08 | Unknown | Unknown | 2023-05-08 | 2023-07-20 | 74 | 54 | 2023-07-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-15 | 2023-06-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 441729 | 34963.37 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-15 | 2023-06-15 | 1 | 1 | 2023-06-15 | 2023-07-20 | 36 | 26 | Unknown | Unknown | Unknown | Unknown | 2023-07-06 | 2023-07-12 | 7 | 5 | 2023-07-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-21 | 2023-12-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 568.18 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-21 | 2023-12-18 | Unknown | Unknown | 2023-12-18 | 2023-12-21 | 4 | 4 | 2023-12-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | LAGUNA NIGUEL | N/A | 298.25 | 298.25 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-10 | 2024-04-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 746.99 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-10 | 2024-04-10 | 1 | 1 | 2024-04-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN MARCOS | SAN MARCOS | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-29 | 2025-01-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2895 | 569.44 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-29 | 2025-01-29 | 1 | 1 | 2025-01-29 | 2025-06-20 | 143 | 103 | Unknown | Unknown | Unknown | Unknown | 2025-02-19 | 2025-02-25 | 7 | 5 | 2025-06-20 | 2025-07-14 | 25 | 17 | Unknown | 2025-07-14 | Unknown | Unknown | 2025-07-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | OCEANSIDE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-19 | 2024-12-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1993.02 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-19 | 2024-12-18 | Unknown | Unknown | 2024-12-18 | 2024-12-19 | 2 | 2 | 2024-12-19 | Unknown | Unknown | Unknown | 2024-12-24 | 2025-01-13 | 21 | 15 | 2024-12-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 110.05 | 110.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-20 | 2024-11-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1844.63 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-20 | 2024-12-12 | 23 | 17 | 2024-12-12 | 2025-01-13 | 33 | 23 | 2025-01-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-13 | 2025-08-04 | 204 | 146 | Unknown | 2025-07-21 | Unknown | Unknown | 2025-08-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 173.05 | 173.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-06 | 2025-05-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7962 | 1144.49 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-06 | 2025-05-28 | 23 | 17 | 2025-05-28 | 2025-06-02 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2025-05-29 | 2025-06-19 | 22 | 16 | 2025-06-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-21 | 2025-03-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2239.12 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-21 | 2025-02-26 | Unknown | Unknown | 2025-02-26 | 2025-03-21 | 24 | 18 | 2025-03-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | 2025-04-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | 3885.58 | 983.32 | Unknown | Unknown | 26.75 | 2875.51 | 3981 | 2027.44 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-07 | 2025-04-07 | 1 | 1 | 2025-04-07 | 2025-04-07 | 1 | 1 | 2025-04-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 84.05 | 84.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-29 | 2025-02-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2012.18 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-29 | 2025-02-18 | 113 | 81 | 2025-02-18 | 2025-02-24 | 7 | 5 | 2025-02-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 12.05 | 12.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-23 | 2024-05-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3941 | 1372.9 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-23 | 2024-04-11 | Unknown | Unknown | 2024-04-11 | 2024-05-23 | 43 | 31 | 2024-05-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | Underserved Community | Vista | COUNTY OF SAN DIEGO-NORTH of 56 | 1470 | 1470 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2021-07-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2020-11-14 | 2021-04-15 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 20462 | 26657.65 | Unknown | Unknown | Yes | N/A | N/A | 2020-11-14 | 2024-09-27 | 1414 | 1010 | 2024-09-27 | 2025-05-19 | 235 | 167 | 2024-09-30 | 2025-05-05 | 196 | 140 | 2025-05-07 | 2025-06-06 | 20 | 16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN MARCOS | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-08-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2021-10-12 | 2021-10-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2754.16 | Unknown | Unknown | Yes | N/A | N/A | 2021-10-12 | 2023-06-28 | 625 | 447 | 2023-06-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 15 | 15 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-29 | 2024-10-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 3196.19 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-29 | 2025-06-06 | 221 | 159 | 2025-06-06 | 2025-06-06 | 1 | 1 | 2025-06-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2022-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-13 | 2023-11-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 73.36 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-13 | 2023-11-14 | 2 | 2 | 2023-11-14 | 2023-11-27 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | MISSION VIEJO | N/A | 69 | 69 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-16 | Unknown | Unknown | No | 2023-12-20 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-20 | 2023-12-20 | Unknown | IOU Designed & Installed | N/A | Yes | 497 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1198.95 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-20 | 2025-06-16 | 545 | 389 | 2025-06-16 | 2024-02-23 | Unknown | Unknown | 2024-02-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | 6.75 | 6.75 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-29 | 2025-06-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1270.75 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-29 | 2025-06-11 | 14 | 10 | 2025-06-11 | 2025-06-11 | 1 | 1 | 2025-06-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-17 | 2023-10-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 708.24 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-17 | 2023-08-23 | Unknown | Unknown | 2023-08-23 | 2023-10-17 | 56 | 40 | 2023-10-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-30 | 2024-07-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1356.9 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-30 | 2024-07-26 | Unknown | Unknown | 2024-07-26 | 2024-08-01 | 7 | 5 | 2024-08-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-02 | 2024-04-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3961 | 192.83 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-02 | 2024-03-12 | Unknown | Unknown | 2024-03-12 | 2024-05-31 | 81 | 59 | 2024-05-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-17 | 2025-04-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1649.27 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-17 | 2025-04-17 | 1 | 1 | 2025-04-17 | 2025-04-17 | 1 | 1 | 2025-04-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-16 | 2025-01-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1794.02 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-16 | 2025-01-16 | 1 | 1 | 2025-01-16 | 2025-01-17 | 2 | 2 | 2025-01-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-16 | 2025-07-02 | 168 | 120 | Unknown | Unknown | Unknown | Unknown | 2025-07-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-09 | Unknown | Unknown | No | 2025-04-28 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-28 | 2025-05-08 | Unknown | IOU Designed & Installed | N/A | Yes | 29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 821.27 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-28 | 2025-05-27 | 30 | 22 | 2025-05-27 | 2025-05-08 | Unknown | Unknown | 2025-05-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-08 | 2025-07-17 | 71 | 51 | Unknown | 2025-07-01 | Unknown | Unknown | 2025-07-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-02 | 2025-06-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1155.87 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-02 | 2025-06-02 | 1 | 1 | 2025-06-02 | 2025-06-02 | 1 | 1 | 2025-06-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 46.05 | 46.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-07 | 2024-11-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2059.07 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-07 | 2024-11-04 | Unknown | Unknown | 2024-11-04 | 2024-11-07 | 4 | 4 | 2024-11-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-06 | 2024-12-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1620.29 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-06 | 2024-11-01 | Unknown | Unknown | 2024-11-01 | 2024-12-02 | 32 | 22 | 2024-12-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | BONITA | N/A | 114 | 114 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-30 | 2025-04-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1675.8 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-30 | 2025-06-03 | 35 | 25 | 2025-06-03 | 2025-04-29 | Unknown | Unknown | 2025-04-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-13 | 2025-08-11 | 60 | 42 | Unknown | Unknown | Unknown | Unknown | 2025-08-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 661.05 | 661.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-02 | 2024-07-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1796.44 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-02 | 2024-08-01 | 31 | 23 | 2024-08-01 | 2024-08-01 | 1 | 1 | 2024-08-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 67.05 | 67.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-12 | 2025-05-12 | 2025-06-05 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1088.24 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-12 | 2025-05-12 | 1 | 1 | 2025-05-12 | 2025-05-12 | 1 | 1 | 2025-05-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-12 | 2025-06-05 | 25 | 19 | Unknown | Unknown | Unknown | Unknown | 2025-06-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LEMON GROVE | N/A | 68 | 68 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-28 | 2023-09-29 | 2024-06-25 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1050.61 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-28 | 2023-09-29 | 2 | 2 | 2023-09-29 | 2023-09-29 | 1 | 1 | 2023-09-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-19 | 2024-06-25 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2024-06-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-05-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-18 | 2022-10-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 24757 | 1330.54 | Unknown | Unknown | Yes | N/A | N/A | 2022-10-18 | 2023-03-07 | 141 | 101 | 2023-03-07 | 2023-10-13 | 221 | 159 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R29/R45 | UG | IOU Design | Commercial | Underserved Community | SAN MARCOS | SAN MARCOS | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-05 | 2023-05-25 | 2025-04-02 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 139742.94 | Unknown | Unknown | Yes | N/A | N/A | 2023-04-05 | 2023-07-07 | 94 | 68 | 2023-07-07 | 2025-01-08 | 552 | 394 | 2023-08-28 | 2024-10-11 | 45 | 33 | 2023-10-10 | 2025-04-07 | 36 | 24 | 2025-01-08 | 2025-08-06 | 211 | 151 | 2025-03-28 | 2025-06-30 | 95 | 67 | 2025-04-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 8 | 8 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-17 | 2024-09-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1422.65 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-17 | 2024-08-13 | Unknown | Unknown | 2024-08-13 | 2024-10-16 | 65 | 47 | 2024-10-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-17 | 2023-04-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3885 | 442.57 | Unknown | Unknown | Yes | N/A | N/A | 2023-04-17 | 2023-04-17 | 1 | 1 | 2023-04-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 42 | 42 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-30 | 2025-05-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 33635 | 1343.61 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-30 | 2025-05-02 | 3 | 3 | 2025-05-02 | 2025-05-12 | 11 | 7 | Unknown | Unknown | Unknown | Unknown | 2025-05-02 | 2025-05-16 | 15 | 11 | 2025-05-12 | 2025-08-21 | 102 | 74 | Unknown | Unknown | Unknown | Unknown | 2025-08-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2022-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-19 | 2023-07-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 336.51 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-19 | 2023-07-21 | 3 | 3 | 2023-07-21 | 2024-02-05 | 200 | 142 | Unknown | Unknown | Unknown | Unknown | 2023-07-31 | 2023-08-04 | 5 | 5 | 2024-02-05 | 2025-04-07 | 428 | 306 | Unknown | 2025-04-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | JULIAN | N/A | 4 | 4 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-06 | 2025-04-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1336.6 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-06 | 2025-04-07 | 92 | 66 | 2025-04-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | LEMON GROVE | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2024-04-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-21 | 2023-06-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 263.54 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-21 | 2023-06-22 | 2 | 2 | 2023-06-22 | 2024-09-12 | 449 | 321 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-12 | 2025-03-18 | 188 | 134 | Unknown | 2025-07-11 | Unknown | Unknown | 2025-08-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-28 | 2024-02-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 42920 | 2514.43 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-28 | 2024-02-28 | 1 | 1 | 2024-02-28 | 2024-03-21 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | JAMUL | N/A | 61 | 61 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-04 | 2025-04-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 8016 | 1632.33 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-04 | 2025-04-08 | 64 | 46 | 2025-04-08 | 2025-04-09 | 2 | 2 | 2025-04-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN YSIDRO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-03 | 2024-10-03 | 2024-10-29 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 4810.62 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-03 | 2024-10-03 | 1 | 1 | 2024-10-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-14 | 2023-09-14 | 2025-06-18 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 27640 | 360.91 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-14 | 2023-11-07 | 55 | 39 | 2023-11-07 | 2025-06-18 | 590 | 422 | 2025-06-18 | 2025-06-18 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2023-11-07 | 2025-06-18 | 590 | 422 | Unknown | 2025-06-04 | Unknown | Unknown | 2025-06-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | MISSION VIEJO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-16 | 2024-04-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 162.34 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-16 | 2024-05-01 | 16 | 12 | 2024-05-01 | 2024-05-01 | 1 | 1 | 2024-05-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CAMPO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2026-12-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-05 | 2024-07-05 | 2024-11-16 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1379.4 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-05 | 2024-07-05 | 1 | 1 | 2024-07-05 | 2024-07-05 | 1 | 1 | 2024-07-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-05 | 2024-11-16 | 135 | 96 | Unknown | Unknown | Unknown | Unknown | 2024-11-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 67.05 | 67.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-27 | 2025-02-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2579.39 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-27 | 2024-07-30 | Unknown | Unknown | 2024-07-30 | 2025-04-04 | 249 | 179 | Unknown | Unknown | Unknown | Unknown | 2025-05-16 | 2025-05-16 | 1 | 1 | 2025-04-04 | Unknown | Unknown | Unknown | Unknown | 2025-08-19 | Unknown | Unknown | 2025-08-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | 75.1 | 75.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-21 | 2025-05-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1701.94 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-21 | 2025-03-12 | Unknown | Unknown | 2025-03-12 | 2025-05-22 | 72 | 52 | 2025-05-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-22 | 2025-08-06 | 77 | 55 | Unknown | Unknown | Unknown | Unknown | 2025-08-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-15 | 2023-09-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 196.27 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-15 | 2023-08-09 | Unknown | Unknown | 2023-08-09 | 2023-09-15 | 38 | 28 | 2023-09-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | BONSALL | N/A | 97.05 | 97.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-13 | 2024-02-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 804.96 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-13 | 2023-05-22 | Unknown | Unknown | 2023-05-22 | 2024-03-05 | 289 | 207 | 2024-03-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 65.05 | 65.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-07 | 2025-02-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1215.3 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-07 | 2025-02-25 | 19 | 13 | 2025-02-25 | 2025-02-26 | 2 | 2 | 2025-02-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN JUAN CAPISTRANO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-24 | 2023-02-24 | 2023-06-12 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 216 | Unknown | Unknown | Yes | N/A | N/A | 2023-02-24 | 2023-02-24 | 1 | 1 | 2023-02-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-24 | 2023-06-12 | 109 | 77 | Unknown | Unknown | Unknown | Unknown | 2023-06-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 174 | 174 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-24 | 2025-01-22 | 2025-05-12 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 19814 | 1517.11 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-24 | 2025-02-07 | 107 | 77 | 2025-02-07 | 2025-04-23 | 76 | 54 | Unknown | Unknown | Unknown | Unknown | 2025-02-26 | 2025-03-12 | 15 | 11 | 2025-04-23 | 2025-07-18 | 87 | 63 | Unknown | Unknown | Unknown | Unknown | 2025-05-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 51.05 | 51.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-29 | 2024-01-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3941 | 734.66 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-29 | 2024-01-10 | Unknown | Unknown | 2024-01-10 | 2024-02-05 | 27 | 19 | 2024-02-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 81 | 81 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-01 | Unknown | Unknown | No | 2025-05-15 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-15 | 2025-05-15 | Unknown | IOU Designed & Installed | N/A | Yes | 68 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1124.26 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-15 | 2025-07-22 | 69 | 49 | 2025-07-22 | 2025-05-21 | Unknown | Unknown | 2025-05-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-21 | Unknown | Unknown | Unknown | Unknown | 2025-08-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | CORONADO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-30 | 2023-08-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 816.91 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-30 | 2023-08-30 | 1 | 1 | 2023-08-30 | 2023-08-30 | 1 | 1 | 2023-08-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 98.05 | 98.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-12 | 2024-11-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1082.17 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-12 | 2024-11-18 | 7 | 5 | 2024-11-18 | 2024-11-18 | 1 | 1 | 2024-11-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 43.05 | 43.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-20 | 2025-05-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 979.34 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-20 | 2025-06-13 | 25 | 19 | 2025-06-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-05 | 2024-09-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1857.89 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-05 | 2024-08-19 | Unknown | Unknown | 2024-08-19 | 2024-09-25 | 38 | 28 | 2024-09-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | Underserved Community | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-14 | 2023-09-14 | 2025-06-30 | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | 7584.03 | 245.38 | Unknown | Unknown | 1513 | 5825.65 | 21390.22 | 4989.25 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-14 | 2024-03-05 | 174 | 124 | 2024-03-05 | 2024-08-29 | 178 | 128 | 2024-03-12 | 2024-03-21 | 10 | 8 | 2024-03-25 | 2024-09-04 | 28 | 22 | 2024-11-27 | Unknown | Unknown | Unknown | 2024-11-27 | 2025-05-23 | 178 | 128 | 2025-06-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 120 | 120 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-22 | 2023-03-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 970.06 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-22 | 2023-03-22 | 1 | 1 | 2023-03-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 18.75 | 18.75 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-07 | 2025-03-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1445.16 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-07 | 2025-03-07 | 152 | 110 | 2025-03-07 | 2025-03-31 | 25 | 17 | Unknown | Unknown | Unknown | Unknown | 2025-03-08 | 2025-04-14 | 15 | 11 | 2025-03-31 | 2025-08-07 | 130 | 94 | Unknown | 2025-08-14 | Unknown | Unknown | 2025-08-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | 61 | 61 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-09 | 2024-10-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1598.54 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-09 | 2024-10-23 | 76 | 54 | 2024-10-23 | 2024-10-29 | 7 | 5 | 2024-10-29 | 2024-11-08 | 11 | 9 | Unknown | Unknown | Unknown | Unknown | 2024-11-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 117.05 | 117.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-11 | 2024-12-11 | 2025-01-03 | IOU Designed & Installed | N/A | No | Unknown | -1870.17 | 0 | Unknown | Unknown | -1896 | 25.83 | 0 | 1896.12 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-11 | 2024-11-01 | Unknown | Unknown | 2024-11-01 | 2024-12-11 | 41 | 29 | 2024-12-11 | 2025-01-23 | 44 | 32 | Unknown | Unknown | Unknown | Unknown | 2024-12-31 | 2025-01-03 | 4 | 4 | Unknown | Unknown | Unknown | Unknown | 2025-01-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 22 | 22 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-12 | Unknown | Unknown | No | 2025-03-31 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-31 | 2025-03-31 | Unknown | IOU Designed & Installed | N/A | Yes | 72 | 451.32 | 0 | Unknown | Unknown | 8.39 | 442.93 | 3981 | 1160.81 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-31 | 2025-06-11 | 73 | 53 | 2025-06-11 | 2025-05-21 | Unknown | Unknown | 2025-05-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-21 | 2025-07-01 | 72 | 52 | Unknown | 2025-06-30 | Unknown | Unknown | 2025-07-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | LAGUNA HILLS | N/A | 1701.05 | 1701.05 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2026-12-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-16 | 2025-01-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2929.03 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-16 | 2025-01-27 | 43 | 31 | 2025-01-27 | 2025-01-30 | 4 | 4 | 2025-01-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | BONITA | N/A | 39.05 | 39.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-27 | 2024-09-27 | 2024-10-24 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1767.09 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-27 | 2024-10-04 | 8 | 6 | 2024-10-04 | 2024-10-10 | 7 | 5 | 2024-10-10 | 2024-10-15 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2024-10-15 | 2024-10-24 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | 2024-10-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | Both | Applicant Design | Residential | Underserved Community | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-07 | 2022-11-07 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 703318.78 | 49572.35 | Unknown | Unknown | Yes | N/A | N/A | 2022-11-07 | 2023-03-22 | 136 | 98 | 2023-03-22 | 2024-06-27 | 464 | 332 | 2023-04-01 | 2024-06-25 | 82 | 58 | 2025-08-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 9.6 | 9.6 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-02 | 2025-05-09 | 2025-06-11 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1490.48 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-02 | 2025-05-09 | 128 | 92 | 2025-05-09 | 2025-05-09 | 1 | 1 | 2025-05-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-09 | 2025-06-11 | 34 | 24 | Unknown | Unknown | Unknown | Unknown | 2025-06-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 8 | 8 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-24 | 2025-02-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1476.3 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-24 | 2025-02-07 | Unknown | Unknown | 2025-02-07 | 2025-03-14 | 36 | 26 | 2025-03-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | Applicant Design | Commercial | N/A | ENCINITAS | N/A | 30000 | 30000 | Not Available | >2MW | No | N/A | N/A | N/A | 2022-11-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-28 | 2023-09-29 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 59036 | 5078.02 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-28 | 2023-06-29 | Unknown | Unknown | 2023-06-29 | 2023-12-05 | 160 | 114 | Unknown | Unknown | Unknown | Unknown | 2024-04-23 | 2024-04-23 | 1 | 1 | 2023-12-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 2.7 | 2.7 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-05 | 2023-10-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 847.64 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-05 | 2023-07-14 | Unknown | Unknown | 2023-07-14 | 2023-10-19 | 98 | 70 | 2023-10-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN MARCOS | N/A | 59.35 | 59.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-30 | 2024-07-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2179.69 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-30 | 2024-08-07 | 9 | 7 | 2024-08-07 | 2024-08-07 | 1 | 1 | 2024-08-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-03 | 2025-02-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2309.49 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-03 | 2025-01-22 | Unknown | Unknown | 2025-01-22 | 2025-02-27 | 37 | 27 | 2025-02-27 | Unknown | Unknown | Unknown | 2025-02-03 | 2025-02-26 | 24 | 18 | 2025-02-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | DANA POINT | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-30 | 2025-05-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 12129 | 337.59 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-30 | 2025-04-02 | Unknown | Unknown | 2025-04-02 | 2025-05-30 | 59 | 43 | 2025-05-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-10 | 2025-06-11 | 2025-06-13 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1243.79 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-10 | 2025-05-30 | Unknown | Unknown | 2025-05-30 | 2025-06-11 | 13 | 9 | 2025-06-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-11 | 2025-06-13 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2025-06-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-27 | 2023-10-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3889.6 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-27 | 2023-10-18 | 22 | 16 | 2023-10-18 | 2024-01-24 | 99 | 71 | Unknown | Unknown | Unknown | Unknown | 2024-08-06 | 2024-08-06 | 1 | 1 | 2024-01-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-08 | 2024-03-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 534.53 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-08 | 2024-03-08 | 1 | 1 | 2024-03-08 | 2024-03-08 | 1 | 1 | 2024-03-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN MARCOS | N/A | 12068.05 | 12068.05 | Not Available | >2MW | No | N/A | N/A | N/A | 2025-05-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-22 | 2025-04-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1002.11 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-22 | 2025-04-24 | 3 | 3 | 2025-04-24 | 2025-04-24 | 1 | 1 | 2025-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-05 | 2025-02-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2875.23 | 872.28 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-05 | 2025-02-27 | 23 | 17 | 2025-02-27 | 2025-03-12 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | IOU Design | Residential | Underserved Community | San Diego | San Diego | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-03-02 | 2022-09-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2680338.19 | 179251.75 | Unknown | Unknown | Yes | N/A | N/A | 2022-03-02 | 2024-12-10 | 1015 | 725 | 2024-12-10 | 2025-08-13 | 247 | 177 | 2023-01-04 | 2025-08-11 | 28 | 20 | 2025-07-03 | 2025-09-04 | 42 | 30 | Unknown | Unknown | Unknown | Unknown | 2025-09-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 84 | 84 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-06-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-12 | 2024-03-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1592.42 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-12 | 2024-03-12 | 1 | 1 | 2024-03-12 | 2024-03-12 | 1 | 1 | 2024-03-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-12 | 2025-07-07 | 483 | 345 | Unknown | 2025-06-30 | Unknown | Unknown | 2025-07-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN YSIDRO | N/A | 9.05 | 9.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-11 | 2025-03-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1880.82 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-11 | 2025-03-18 | 8 | 6 | 2025-03-18 | 2025-03-18 | 1 | 1 | 2025-03-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 69.05 | 69.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-29 | 2025-02-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1670.23 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-29 | 2025-02-20 | 23 | 17 | 2025-02-20 | 2025-02-20 | 1 | 1 | 2025-02-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-20 | 2025-08-12 | 174 | 124 | Unknown | Unknown | Unknown | Unknown | 2025-08-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2021-03-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-09 | 2024-05-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 351.58 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-09 | 2024-05-17 | 9 | 7 | 2024-05-17 | 2024-05-20 | 4 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-05-10 | 2024-06-07 | 29 | 21 | 2024-05-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | 106 | 106 | Not Available | <1MW | No | N/A | N/A | N/A | 2021-06-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2021-10-06 | 2023-05-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 36989 | 2778.96 | Unknown | Unknown | Yes | N/A | N/A | 2021-10-06 | 2023-03-31 | 542 | 388 | 2023-03-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-23 | 2023-06-14 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 52.05 | 52.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-18 | 2023-05-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 882.5 | Unknown | Unknown | Yes | N/A | N/A | 2023-05-18 | 2023-05-18 | 1 | 1 | 2023-05-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | ESCONDIDO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2024-09-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-05 | 2025-02-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3753.77 | 1619.16 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-05 | 2025-04-16 | 71 | 51 | 2025-04-16 | 2025-05-06 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | 2025-04-03 | 2025-04-11 | 9 | 7 | 2025-05-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-16 | 2024-08-26 | 2025-01-15 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 6038.76 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-16 | 2024-06-13 | Unknown | Unknown | 2024-06-13 | 2024-12-06 | 177 | 127 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-16 | 2024-12-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1313.88 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-16 | 2024-12-13 | Unknown | Unknown | 2024-12-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | NATIONAL CITY | N/A | 20 | 20 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-29 | 2024-04-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1808.26 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-29 | 2024-04-29 | 1 | 1 | 2024-04-29 | 2024-04-29 | 1 | 1 | 2024-04-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-14 | 2025-03-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 807.62 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-14 | 2025-04-22 | 40 | 28 | 2025-04-22 | 2025-05-05 | 14 | 10 | 2025-05-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | San Marcos | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-05 | 2024-06-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 66713 | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2024-06-05 | 2024-04-25 | Unknown | Unknown | 2024-04-25 | 2024-07-09 | 76 | 54 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-09 | 2025-09-08 | 427 | 305 | Unknown | Unknown | Unknown | Unknown | 2025-07-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SOLANA BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-27 | 2023-06-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | 273.07 | 0 | Unknown | Unknown | 4.97 | 268.1 | 3981 | 798.56 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-27 | 2024-03-20 | 268 | 192 | 2024-03-20 | 2024-03-20 | 1 | 1 | 2024-03-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-20 | 2025-07-08 | 476 | 340 | Unknown | 2025-06-26 | Unknown | Unknown | 2025-07-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-12-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-03-07 | 2022-09-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 5457815.16 | 278613.48 | Unknown | Unknown | Yes | N/A | N/A | 2022-03-07 | 2024-09-10 | 919 | 657 | 2024-09-10 | 2023-09-08 | Unknown | Unknown | 2023-02-10 | 2025-08-11 | 221 | 157 | 2023-02-23 | 2025-08-13 | 725 | 517 | Unknown | Unknown | Unknown | Unknown | 2024-07-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-16 | 2024-12-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1313.88 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-16 | 2024-12-13 | Unknown | Unknown | 2024-12-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | Oceanside | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-11 | 2025-03-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 4433.06 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-11 | 2025-03-11 | 1 | 1 | 2025-03-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-27 | 2023-11-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 5032.91 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-27 | 2023-11-10 | 45 | 33 | 2023-11-10 | 2024-04-18 | 161 | 115 | Unknown | Unknown | Unknown | Unknown | 2024-08-07 | 2024-08-07 | 1 | 1 | 2024-04-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-26 | 2023-06-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 8997 | 402.57 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-26 | 2023-04-12 | Unknown | Unknown | 2023-04-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-23 | 2025-01-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | 924.07 | -6.85 | Unknown | Unknown | Unknown | 930.92 | 0 | 10360.88 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-23 | 2025-01-23 | 1 | 1 | 2025-01-23 | 2025-03-20 | 57 | 41 | Unknown | Unknown | Unknown | Unknown | 2025-01-28 | 2025-02-19 | 23 | 17 | 2025-03-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | Underserved Community | San Marcos | SAN MARCOS | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-10 | 2022-08-10 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 90938.17 | Unknown | Unknown | Yes | N/A | N/A | 2022-08-10 | 2024-08-29 | 751 | 537 | 2024-08-29 | 2025-07-22 | 328 | 234 | 2024-09-13 | 2025-07-21 | 33 | 22 | 2024-09-26 | 2025-07-28 | 175 | 125 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-11 | 2023-10-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 57764 | 4329.52 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-11 | 2023-10-11 | 1 | 1 | 2023-10-11 | 2023-11-01 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | 2023-11-02 | 2023-11-02 | 1 | 1 | 2023-11-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-27 | 2023-10-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3993.58 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-27 | 2023-10-23 | 27 | 19 | 2023-10-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-06 | 2024-08-06 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | Underserved Community | San Marcos | SAN MARCOS | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-07 | 2022-12-07 | 2024-12-03 | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 166296.72 | Unknown | Unknown | Yes | N/A | N/A | 2022-12-07 | 2023-07-25 | 231 | 165 | 2023-07-25 | 2024-02-23 | 214 | 154 | 2023-08-22 | 2024-12-16 | 156 | 110 | 2023-04-28 | 2025-01-24 | -49 | -36 | 2024-03-04 | Unknown | Unknown | Unknown | 2024-03-04 | 2024-11-19 | 261 | 187 | 2024-12-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-10 | 2023-10-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 284.12 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-10 | 2023-10-10 | 1 | 1 | 2023-10-10 | 2023-10-16 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-26 | 2025-03-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1942.43 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-26 | 2025-04-09 | 15 | 11 | 2025-04-09 | 2025-04-22 | 14 | 10 | 2025-04-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 42.05 | 42.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-10 | 2024-01-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 773.01 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-10 | 2025-08-15 | 584 | 418 | 2025-08-15 | 2024-01-10 | Unknown | Unknown | 2024-01-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 11.5 | 11.5 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-21 | 2024-08-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1090.55 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-21 | 2024-08-07 | Unknown | Unknown | 2024-08-07 | 2024-08-29 | 23 | 17 | 2024-08-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | Underserved Community | OC 1106-E1 rincon Hms (E) | OCEANSIDE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-17 | 2023-07-17 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 23931.44 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-17 | 2024-02-20 | 219 | 157 | 2024-02-20 | 2025-01-08 | 324 | 232 | 2024-03-25 | 2025-07-18 | 317 | 227 | 2024-06-28 | 2025-07-11 | 38 | 24 | 2025-01-27 | Unknown | Unknown | Unknown | 2025-01-27 | 2025-07-10 | 165 | 119 | 2025-07-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 9.05 | 9.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-05 | 2024-12-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1975.88 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-05 | 2024-12-03 | Unknown | Unknown | 2024-12-03 | 2025-01-09 | 38 | 28 | 2025-01-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-09 | 2025-08-12 | 216 | 154 | Unknown | Unknown | Unknown | Unknown | 2025-08-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-12 | 2024-07-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1639.66 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-12 | 2024-07-12 | 1 | 1 | 2024-07-12 | 2024-07-12 | 1 | 1 | 2024-07-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 42 | 42 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-29 | 2023-11-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 725.76 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-29 | 2023-12-08 | 10 | 8 | 2023-12-08 | 2023-12-27 | 20 | 14 | 2023-12-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 48.4 | 48.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-17 | 2025-03-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1272.97 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-17 | 2025-02-27 | 134 | 96 | 2025-02-27 | 2025-03-21 | 23 | 17 | 2025-03-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-25 | 2024-12-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1763.06 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-25 | 2025-08-19 | 238 | 170 | 2025-08-19 | 2025-08-19 | 1 | 1 | 2025-08-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | RAMONA | N/A | 136.05 | 136.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-06 | 2025-02-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1829.65 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-06 | 2025-02-07 | 2 | 2 | 2025-02-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | LAKESIDE | N/A | 48 | 48 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-25 | 2023-09-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 4699 | 1774.96 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-25 | 2023-09-25 | 1 | 1 | 2023-09-25 | 2023-10-04 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-13 | 2025-02-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1275.29 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-13 | 2025-03-17 | 33 | 23 | 2025-03-17 | 2025-03-17 | 1 | 1 | 2025-03-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | COTO DE CAZA | N/A | 191 | 191 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-12 | 2025-06-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 835.79 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-12 | 2025-06-03 | Unknown | Unknown | 2025-06-03 | 2025-06-12 | 10 | 8 | 2025-06-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-12 | 2025-07-14 | 33 | 23 | Unknown | 2025-07-09 | Unknown | Unknown | 2025-07-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-01-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-29 | 2024-08-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 29883.21 | Unknown | Unknown | Yes | N/A | N/A | 2022-04-29 | 2024-08-07 | 832 | 594 | 2024-08-07 | 2024-10-15 | 70 | 50 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 49 | 49 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-09 | 2024-10-11 | 2024-10-17 | IOU Designed & Installed | N/A | No | Unknown | 30.16 | 0 | Unknown | Unknown | 11.09 | 19.07 | 0 | 688.12 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-09 | 2024-09-27 | Unknown | Unknown | 2024-09-27 | 2024-10-11 | 15 | 11 | 2024-10-11 | 2024-10-17 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-05-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-12 | 2023-11-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 8370 | 502.46 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-12 | 2023-10-10 | 29 | 21 | 2023-10-10 | 2023-11-29 | 51 | 37 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | OCEANSIDE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-09 | 2023-02-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1546.25 | Unknown | Unknown | Yes | N/A | N/A | 2023-02-09 | 2023-02-15 | 7 | 5 | 2023-02-15 | 2023-04-17 | 62 | 44 | Unknown | Unknown | Unknown | Unknown | 2023-02-16 | 2024-11-04 | 97 | 69 | 2023-04-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-29 | 2024-04-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2402.2 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-29 | 2024-08-26 | 120 | 86 | 2024-08-26 | 2024-08-28 | 3 | 3 | 2024-08-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Disadvantaged Community,Underserved Community | LEMON GROVE | LEMON GROVE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-01 | 2024-10-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 11928 | 2808.61 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-01 | 2024-10-10 | 10 | 8 | 2024-10-10 | 2024-12-12 | 64 | 46 | Unknown | Unknown | Unknown | Unknown | 2024-10-10 | 2024-11-14 | 36 | 26 | 2024-12-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community,Tribal Community | PALA | N/A | 98 | 98 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-03 | 2023-11-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3885 | 3658.13 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-03 | 2023-08-25 | Unknown | Unknown | 2023-08-25 | 2024-04-19 | 239 | 171 | 2024-04-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-19 | 2025-08-14 | 483 | 345 | Unknown | 2025-07-29 | Unknown | Unknown | 2025-08-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | RANCHO MISSION VIEJO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-03 | 2025-06-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 4741 | 538.18 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-03 | 2025-06-03 | 1 | 1 | 2025-06-03 | 2025-07-08 | 36 | 26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-07-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | Disadvantaged Community,Underserved Community | Chula Vista | CHULA VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-01 | 2024-10-01 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 48169.8 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-01 | 2024-12-04 | 65 | 47 | 2024-12-04 | 2025-03-20 | 107 | 77 | 2024-12-17 | 2025-04-09 | 83 | 61 | 2025-02-27 | 2025-04-25 | 51 | 37 | 2025-07-02 | Unknown | Unknown | Unknown | 2025-07-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LAKESIDE | COUNTY OF SAN DIEGO-NORTH of 56, COUNTY OF SAN DIEGO-SOUTH of 56 | 5.4 | 5.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-24 | 2024-05-24 | 2024-08-06 | IOU Designed & Installed | N/A | No | Unknown | 1080.34 | -20.4 | Unknown | Unknown | 28.79 | 1071.95 | 3981 | 1417.45 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-24 | 2024-04-18 | Unknown | Unknown | 2024-04-18 | 2024-05-24 | 37 | 27 | 2024-05-24 | Unknown | Unknown | Unknown | 2024-05-28 | 2024-06-18 | 22 | 16 | 2025-02-19 | 2024-08-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | OH | IOU Design | Commercial | Underserved Community | San Diego | SAN DIEGO | 11450 | 11450 | Not Available | >2MW | No | N/A | N/A | N/A | 2022-08-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-27 | 2024-08-28 | 2025-06-19 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 28677.58 | 40545 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-27 | 2024-04-15 | 20 | 14 | 2024-04-15 | 2025-03-25 | 345 | 247 | 2025-03-13 | 2025-03-13 | 1 | 1 | 2024-10-18 | 2025-03-28 | 31 | 23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | FALLBROOK | COUNTY OF SAN DIEGO-NORTH of 56 | 135 | 135 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-14 | 2024-11-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 685.91 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-14 | 2025-02-24 | 134 | 96 | 2025-02-24 | Unknown | Unknown | Unknown | 2025-02-19 | 2025-06-04 | 7 | 5 | 2025-03-10 | 2025-03-17 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-13 | 2023-11-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 158.14 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-13 | 2023-10-25 | 43 | 31 | 2023-10-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-27 | 2024-04-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 979.92 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-27 | 2024-02-23 | Unknown | Unknown | 2024-02-23 | 2024-04-22 | 60 | 42 | 2024-04-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-22 | 2025-01-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1573.51 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-22 | 2025-01-22 | 1 | 1 | 2025-01-22 | 2025-01-31 | 10 | 8 | 2025-01-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-30 | 2025-07-10 | 162 | 116 | Unknown | Unknown | Unknown | Unknown | 2025-07-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-27 | 2024-12-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 6673.07 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-27 | 2024-12-02 | 6 | 4 | 2024-12-02 | 2025-04-14 | 134 | 96 | Unknown | Unknown | Unknown | Unknown | 2025-01-07 | 2025-01-24 | 18 | 14 | 2025-04-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-18 | 2023-08-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 23558 | 2095.82 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-18 | 2023-07-19 | Unknown | Unknown | 2023-07-19 | 2023-09-06 | 50 | 36 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | 91.35 | 91.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-31 | 2024-12-31 | 2025-06-11 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 15924 | 1497.73 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-31 | 2024-09-04 | Unknown | Unknown | 2024-09-04 | 2025-02-19 | 169 | 121 | Unknown | Unknown | Unknown | Unknown | 2025-02-13 | 2025-03-06 | 22 | 16 | 2025-02-19 | 2025-08-11 | 174 | 124 | Unknown | Unknown | Unknown | Unknown | 2025-06-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 62 | 62 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-29 | 2023-12-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 670.46 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-29 | 2024-05-08 | 132 | 94 | 2024-05-08 | 2024-11-21 | 198 | 142 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN MARCOS | SAN MARCOS | 45906 | 45906 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-11-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-25 | 2025-01-07 | 2025-06-13 | IOU Designed & Installed | N/A | No | Unknown | 3544.96 | 0 | Unknown | Unknown | 18.62 | 3526.34 | Unknown | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2024-11-25 | 2025-01-07 | 44 | 32 | 2025-01-07 | 2025-01-27 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | 2025-01-14 | 2025-07-18 | 32 | 24 | 2025-01-27 | 2025-07-11 | 166 | 120 | Unknown | 2025-07-09 | Unknown | Unknown | 2025-06-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SOLANA BEACH | SOLANA BEACH | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-16 | 2025-05-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 254.87 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-16 | 2025-05-27 | 12 | 8 | 2025-05-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-17 | 2025-07-18 | 32 | 24 | 2025-06-17 | 2025-08-04 | 49 | 35 | Unknown | Unknown | Unknown | Unknown | 2025-08-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | JAMUL | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-12 | 2024-07-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1031.05 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-12 | 2024-07-16 | 5 | 3 | 2024-07-16 | 2024-07-16 | 1 | 1 | 2024-07-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-05-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-12 | 2023-09-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 8370 | 520.2 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-12 | 2023-10-10 | 29 | 21 | 2023-10-10 | 2023-11-27 | 49 | 35 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-28 | 2025-01-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2835.99 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-28 | 2025-01-28 | 1 | 1 | 2025-01-28 | 2025-01-28 | 1 | 1 | 2025-01-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-28 | 2025-07-21 | 175 | 125 | Unknown | Unknown | Unknown | Unknown | 2025-07-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN YSIDRO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-09-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-18 | 2024-10-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3241 | 507.87 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-18 | 2024-07-02 | Unknown | Unknown | 2024-07-02 | 2024-10-18 | 109 | 79 | 2024-10-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-13 | 2025-05-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3941 | 1003.16 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-13 | 2025-05-02 | Unknown | Unknown | 2025-05-02 | 2025-06-05 | 35 | 25 | 2025-06-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | OCEANSIDE | 145 | 145 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-08 | 2025-02-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7962 | 2257.83 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-08 | 2025-01-22 | 15 | 11 | 2025-01-22 | 2025-05-19 | 118 | 84 | Unknown | Unknown | Unknown | Unknown | 2025-03-05 | 2025-03-19 | 15 | 11 | 2025-05-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-29 | 2025-05-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1559.83 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-29 | 2025-05-29 | 1 | 1 | 2025-05-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R29/R45) | UG | IOU Design | Commercial | Underserved Community | POWAY | POWAY | 550 | 550 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-03-03 | Unknown | Unknown | No | 2023-04-21 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2021-04-23 | 2021-04-24 | 2025-04-07 | IOU Designed & Installed | N/A | Yes | 581 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 30687 | 73827.47 | Unknown | Unknown | Yes | N/A | N/A | 2021-04-23 | 2023-04-03 | 711 | 507 | 2023-04-03 | 2024-10-14 | 561 | 401 | 2023-05-25 | 2024-08-08 | 32 | 24 | 2023-06-08 | 2024-10-11 | 177 | 127 | Unknown | Unknown | Unknown | Unknown | 2025-04-28 | Unknown | Unknown | Unknown | 2025-04-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-05 | 2024-02-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1483.37 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-05 | 2024-01-24 | Unknown | Unknown | 2024-01-24 | 2024-02-13 | 21 | 15 | 2024-02-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-20 | 2023-12-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 515.81 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-20 | 2023-12-20 | 1 | 1 | 2023-12-20 | 2023-12-20 | 1 | 1 | 2023-12-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | El Cajon | EL CAJON | 600 | 600 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-03-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-02-16 | 2024-03-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 83578.86 | Unknown | Unknown | Yes | N/A | N/A | 2022-02-16 | 2024-03-22 | 766 | 548 | 2024-03-22 | 2025-03-28 | 372 | 266 | 2024-06-27 | 2024-08-09 | 44 | 32 | 2025-01-30 | 2025-07-16 | 87 | 63 | Unknown | Unknown | Unknown | Unknown | 2025-04-07 | 2025-05-29 | 53 | 39 | 2025-08-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-20 | 2024-02-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 163.83 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-20 | 2023-12-28 | Unknown | Unknown | 2023-12-28 | 2024-03-18 | 82 | 58 | 2024-03-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 145.05 | 145.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-13 | 2024-11-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1189.69 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-13 | 2024-10-23 | Unknown | Unknown | 2024-10-23 | 2024-11-18 | 27 | 19 | 2024-11-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-13 | 2025-05-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1092.02 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-13 | 2025-04-23 | Unknown | Unknown | 2025-04-23 | 2025-05-16 | 24 | 18 | 2025-05-16 | 2025-06-10 | 26 | 18 | Unknown | Unknown | Unknown | Unknown | 2025-05-16 | 2025-08-05 | 82 | 58 | Unknown | 2025-07-15 | Unknown | Unknown | 2025-08-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2026-03-05 | Unknown | Unknown | No | 2024-03-21 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-21 | 2024-03-27 | Unknown | IOU Designed & Installed | N/A | Yes | 439 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 54899 | 81.53 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-21 | 2024-09-03 | 167 | 119 | 2024-09-03 | 2024-09-16 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | 2024-04-04 | 2024-10-07 | 69 | 49 | 2024-09-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-20 | 2025-02-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 5171.93 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-20 | 2025-02-20 | 1 | 1 | 2025-02-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-21 | 2024-03-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 501.14 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-21 | 2024-01-05 | Unknown | Unknown | 2024-01-05 | 2024-03-01 | 57 | 41 | 2024-03-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LA JOLLA | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2018-04-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-09 | 2023-08-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 71.28 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-09 | 2023-08-09 | 1 | 1 | 2023-08-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-29 | 2024-05-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 11943 | 2224.9 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-29 | 2024-12-11 | 197 | 141 | 2024-12-11 | 2025-01-08 | 29 | 21 | Unknown | Unknown | Unknown | Unknown | 2024-12-12 | 2025-01-21 | 41 | 29 | 2025-01-08 | 2025-08-22 | 227 | 163 | Unknown | 2025-08-28 | Unknown | Unknown | 2025-09-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-27 | 2024-05-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 5589.25 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-27 | 2023-10-18 | 22 | 16 | 2023-10-18 | 2024-09-16 | 335 | 239 | Unknown | Unknown | Unknown | Unknown | 2024-12-11 | 2024-12-11 | 1 | 1 | 2024-09-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-18 | 2025-04-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1706.67 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-18 | 2025-04-22 | 5 | 3 | 2025-04-22 | 2025-04-24 | 3 | 3 | 2025-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-24 | 2025-07-15 | 83 | 59 | Unknown | Unknown | Unknown | Unknown | 2025-07-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | CORONADO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-13 | 2025-03-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2360.24 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-13 | 2025-01-21 | Unknown | Unknown | 2025-01-21 | 2025-03-20 | 59 | 43 | 2025-03-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-20 | 2025-08-26 | 160 | 114 | Unknown | Unknown | Unknown | Unknown | 2025-08-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-05 | 2024-09-05 | 2024-09-06 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 186.52 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-05 | 2024-09-06 | 2 | 2 | 2024-09-06 | 2024-09-06 | 1 | 1 | 2024-09-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-06 | 2024-09-06 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-09-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-03 | 2025-04-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 794.49 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-03 | 2025-04-03 | 1 | 1 | 2025-04-03 | 2025-05-09 | 37 | 27 | 2025-05-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-03 | 2025-08-20 | 140 | 100 | Unknown | 2025-07-16 | Unknown | Unknown | 2025-08-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-17 | 2024-09-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1558.07 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-17 | 2024-09-17 | 1 | 1 | 2024-09-17 | 2024-09-17 | 1 | 1 | 2024-09-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-01-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-29 | 2023-03-31 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 32625 | 229.69 | Unknown | Unknown | Yes | N/A | N/A | 2022-12-29 | 2023-03-13 | 75 | 53 | 2023-03-13 | 2023-07-31 | 141 | 101 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 315 | 315 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-18 | 2025-04-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 57521 | 2738.16 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-18 | 2025-04-09 | 23 | 17 | 2025-04-09 | 2025-06-19 | 72 | 52 | Unknown | Unknown | Unknown | Unknown | 2025-06-06 | 2025-06-24 | 19 | 13 | 2025-06-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-12 | 2023-06-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 893.38 | Unknown | Unknown | Yes | N/A | N/A | 2023-05-12 | 2023-08-21 | 102 | 72 | 2023-08-21 | 2023-10-04 | 45 | 33 | Unknown | Unknown | Unknown | Unknown | 2024-05-02 | 2024-05-24 | 23 | 17 | 2023-10-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 95.05 | 95.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-06 | 2023-12-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 893.54 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-06 | 2023-07-11 | Unknown | Unknown | 2023-07-11 | 2023-12-06 | 149 | 107 | 2023-12-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 6 | 6 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-28 | 2025-01-28 | 2025-05-09 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1647.26 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-28 | 2025-01-28 | 1 | 1 | 2025-01-28 | 2025-01-28 | 1 | 1 | 2025-01-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-28 | 2025-05-09 | 102 | 74 | Unknown | Unknown | Unknown | Unknown | 2025-05-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 16.72 | 16.72 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-09 | 2024-08-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1262.11 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-09 | 2024-07-17 | Unknown | Unknown | 2024-07-17 | 2024-09-17 | 63 | 45 | 2024-09-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | ESCONDIDO | 129.05 | 129.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-05 | 2025-03-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 996.66 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-05 | 2025-03-06 | 2 | 2 | 2025-03-06 | 2025-03-17 | 12 | 8 | 2025-03-05 | 2025-03-11 | 7 | 5 | 2025-03-06 | 2025-03-17 | 12 | 8 | 2025-03-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-23 | 2025-06-17 | 2025-06-23 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2025-05-23 | 2025-06-12 | 21 | 15 | 2025-06-12 | 2025-06-17 | 6 | 4 | 2025-06-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-17 | 2025-06-23 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2025-06-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | VISTA | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-29 | 2023-08-31 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 814.55 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-29 | 2023-08-30 | 2 | 2 | 2023-08-30 | 2023-09-06 | 8 | 6 | 2023-09-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 135.1 | 135.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-03 | 2024-12-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2771.28 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-03 | 2024-12-10 | 8 | 6 | 2024-12-10 | 2024-12-23 | 14 | 10 | 2024-12-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | 10 | 10 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-03 | 2024-10-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1241.23 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-03 | 2024-09-11 | Unknown | Unknown | 2024-09-11 | 2024-11-19 | 70 | 50 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-19 | Unknown | Unknown | Unknown | Unknown | 2025-08-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 12 | 12 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-04 | 2024-11-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1844.48 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-04 | 2024-11-05 | 2 | 2 | 2024-11-05 | 2024-11-05 | 1 | 1 | 2024-11-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | N/A | 20 | 20 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-27 | 2024-04-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 550.28 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-27 | 2024-04-10 | 15 | 11 | 2024-04-10 | 2024-04-11 | 2 | 2 | 2024-04-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-15 | 2025-04-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2765.36 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-15 | 2025-04-15 | 1 | 1 | 2025-04-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2018-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-21 | 2023-06-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 235.96 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-21 | 2023-06-22 | 2 | 2 | 2023-06-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-23 | 2023-08-25 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-25 | 2024-09-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 692.62 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-25 | 2024-11-21 | 58 | 42 | 2024-11-21 | 2025-01-31 | 72 | 52 | 2025-01-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-12 | 2023-09-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 695.98 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-12 | 2023-09-14 | 3 | 3 | 2023-09-14 | 2023-09-19 | 6 | 4 | 2023-09-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | 222214 | 222214 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-03-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-10 | 2025-01-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 14103 | 703.25 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-10 | 2025-01-10 | 1 | 1 | 2025-01-10 | 2025-01-27 | 18 | 12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-03 | 2024-09-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3759.82 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-03 | 2024-08-26 | Unknown | Unknown | 2024-08-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | RAMONA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-05 | 2023-07-05 | 2023-07-16 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 270.38 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-05 | 2023-07-07 | 3 | 3 | 2023-07-07 | 2023-07-07 | 1 | 1 | 2023-07-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-07 | 2023-07-16 | 10 | 6 | Unknown | Unknown | Unknown | Unknown | 2023-07-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Commercial | N/A | SD 1169-G3 (E) | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-25 | 2023-04-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 770857 | 87917.84 | Unknown | Unknown | Yes | N/A | N/A | 2023-04-25 | 2023-04-25 | 1 | 1 | 2023-04-25 | 2025-05-06 | 743 | 531 | 2025-04-07 | 2025-08-28 | 1 | 1 | 2024-06-14 | 2025-06-09 | 88 | 58 | 2025-05-21 | Unknown | Unknown | Unknown | 2025-05-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2020-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-22 | 2024-08-22 | 2024-11-05 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 102.78 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-22 | 2024-08-22 | 1 | 1 | 2024-08-22 | 2024-09-12 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 75 | 75 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-21 | 2024-08-21 | 2025-05-20 | IOU Designed & Installed | N/A | No | Unknown | 578.05 | -7.6 | Unknown | Unknown | Unknown | 585.65 | 0 | 8322.33 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-21 | 2024-06-06 | Unknown | Unknown | 2024-06-06 | 2024-12-10 | 188 | 134 | 2025-04-21 | 2025-04-21 | 1 | 1 | 2024-12-13 | 2025-06-19 | 37 | 27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | 38 | 38 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-30 | 2023-07-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3885 | 1024.49 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-30 | 2023-07-10 | 11 | 7 | 2023-07-10 | 2023-07-10 | 1 | 1 | 2023-07-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Disadvantaged Community,Underserved Community | EL CAJON | EL CAJON | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-12 | 2024-10-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 160305 | 3349.13 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-12 | 2024-11-21 | 102 | 74 | 2024-11-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-13 | 2024-09-04 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 14 | 14 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-30 | 2024-05-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3941 | 1421.98 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-30 | 2024-04-11 | Unknown | Unknown | 2024-04-11 | 2024-05-30 | 50 | 36 | 2024-05-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R29/R45 | UG | IOU Design | Commercial | N/A | SAN CLEMENTE | CALTRANS-Orange County, SAN CLEMENTE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-01 | 2024-01-16 | 2024-12-04 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 142316.24 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-01 | 2024-05-07 | 189 | 135 | 2024-05-07 | 2024-11-20 | 198 | 142 | 2024-07-09 | 2024-10-16 | 6 | 4 | 2024-01-16 | 2025-05-27 | 100 | 72 | 2024-11-20 | 2025-07-01 | 224 | 160 | Unknown | 2025-08-18 | Unknown | Unknown | 2024-12-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 131 | 131 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-22 | 2024-04-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 1219 | 2181.25 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-22 | 2024-04-12 | 51 | 37 | 2024-04-12 | 2024-04-12 | 1 | 1 | 2024-04-12 | 2024-04-24 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2024-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-28 | 2025-04-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1825.42 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-28 | 2025-04-03 | 7 | 5 | 2025-04-03 | 2025-04-03 | 1 | 1 | 2025-04-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | ESCONDIDO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2024-09-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-05 | 2025-02-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 4090.33 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-05 | 2025-04-30 | 85 | 61 | 2025-04-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-06 | 2025-03-17 | 12 | 8 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 12.1 | 12.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-23 | 2024-09-16 | 2025-03-06 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 48559.41 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-23 | 2024-08-26 | 35 | 25 | 2024-08-26 | 2025-02-05 | 164 | 118 | Unknown | Unknown | Unknown | Unknown | 2024-11-18 | 2025-02-25 | 37 | 27 | 2025-02-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 68.05 | 68.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-01-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-02 | 2025-03-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 15924 | 1592.03 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-02 | 2024-09-23 | 572 | 408 | 2024-09-23 | 2025-03-19 | 178 | 128 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | FALLBROOK | COUNTY OF SAN DIEGO-NORTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-15 | 2025-01-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 35548.75 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-15 | 2025-01-15 | 1 | 1 | 2025-01-15 | 2025-06-18 | 155 | 111 | 2025-01-20 | 2025-01-21 | 2 | 2 | 2025-06-19 | 2025-06-23 | 5 | 3 | 2025-06-18 | Unknown | Unknown | Unknown | 2025-06-27 | 2025-08-26 | 61 | 43 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | RAMONA | N/A | 171 | 171 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-08-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-04 | 2024-12-06 | 2025-06-24 | IOU Designed & Installed | N/A | No | Unknown | 314.82 | -4.14 | Unknown | Unknown | Unknown | 318.96 | 0 | 3956.07 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-04 | 2024-02-02 | Unknown | Unknown | 2024-02-02 | 2025-02-06 | 371 | 265 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-06 | 2025-05-21 | 105 | 75 | Unknown | 2025-06-18 | Unknown | Unknown | 2025-06-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | JAMUL | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-23 | 2024-01-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1209.27 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-23 | 2024-01-23 | 1 | 1 | 2024-01-23 | 2024-02-02 | 11 | 9 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | LAKESIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-12 | 2025-03-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1005.29 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-12 | 2025-03-12 | 1 | 1 | 2025-03-12 | 2025-03-12 | 1 | 1 | 2025-03-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 102.05 | 102.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-22 | 2024-08-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1226.88 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-22 | 2024-08-22 | 1 | 1 | 2024-08-22 | 2025-05-13 | 265 | 189 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-08-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-27 | 2024-10-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1166.61 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-27 | 2024-09-10 | Unknown | Unknown | 2024-09-10 | 2024-10-06 | 27 | 19 | 2024-10-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | OCEANSIDE | 93.05 | 93.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-19 | 2024-12-23 | 2025-03-04 | IOU Designed & Installed | N/A | No | Unknown | 17533.53 | 4173.4 | Unknown | 188.67 | 382.49 | 12788.97 | 0 | 2035.01 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-19 | 2024-12-11 | Unknown | Unknown | 2024-12-11 | 2024-12-23 | 13 | 9 | 2024-12-23 | Unknown | Unknown | Unknown | 2024-12-26 | 2025-01-13 | 19 | 13 | 2024-12-23 | 2025-03-04 | 72 | 52 | Unknown | Unknown | Unknown | Unknown | 2025-03-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-24 | 2024-01-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 517.29 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-24 | 2024-01-03 | Unknown | Unknown | 2024-01-03 | 2024-01-24 | 22 | 16 | 2024-01-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community,Tribal Community | LAKESIDE | N/A | 68.05 | 68.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-26 | 2024-07-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1092.23 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-26 | 2024-07-26 | 1 | 1 | 2024-07-26 | 2025-06-02 | 312 | 222 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-02 | 2025-08-04 | 64 | 46 | Unknown | 2025-08-20 | Unknown | Unknown | 2025-08-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-07 | 2025-01-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 4356.38 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-07 | 2025-01-06 | Unknown | Unknown | 2025-01-06 | 2025-01-23 | 18 | 14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-16 | 2025-04-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 26729.28 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-16 | 2025-04-04 | Unknown | Unknown | 2025-04-04 | 2025-04-16 | 13 | 9 | 2025-04-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-03 | 2024-12-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 3968.21 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-03 | 2024-12-03 | 1 | 1 | 2024-12-03 | 2024-12-19 | 17 | 13 | 2024-12-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 67 | 67 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-30 | 2024-11-11 | 2025-04-11 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1111.02 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-30 | 2024-10-08 | Unknown | Unknown | 2024-10-08 | 2024-11-11 | 35 | 25 | 2024-11-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-11 | 2025-04-11 | 152 | 110 | Unknown | Unknown | Unknown | Unknown | 2025-04-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SOLANA BEACH | SOLANA BEACH | 15284.05 | 15284.05 | Not Available | >2MW | No | N/A | N/A | N/A | 2027-05-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-11 | 2025-06-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1398 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-11 | 2025-06-16 | 6 | 4 | 2025-06-16 | 2025-06-16 | 1 | 1 | 2025-06-16 | Unknown | Unknown | Unknown | 2025-06-16 | 2025-07-18 | 33 | 25 | 2025-06-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2017-10-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-29 | 2024-11-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1050.78 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-29 | 2024-10-23 | Unknown | Unknown | 2024-10-23 | 2024-11-11 | 20 | 14 | 2024-11-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-14 | 2025-06-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1297.82 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-14 | 2025-06-02 | 20 | 14 | 2025-06-02 | 2025-06-10 | 9 | 7 | 2025-06-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 906.05 | 906.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-08 | Unknown | Unknown | No | 2024-09-04 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-04 | 2024-10-29 | Unknown | IOU Designed & Installed | N/A | Yes | 126 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1456.62 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-04 | 2024-12-17 | 105 | 75 | 2024-12-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | Applicant Design | Residential | Underserved Community | Chula Vista | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-25 | 2024-09-26 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2024-09-25 | 2024-09-26 | 2 | 2 | 2024-09-26 | 2025-01-29 | 126 | 90 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-02 | 2025-04-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 7301.99 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-02 | 2025-04-22 | 21 | 15 | 2025-04-22 | 2025-04-30 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | ALPINE | N/A | 5.4 | 5.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-25 | 2024-12-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1739.79 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-25 | 2024-12-23 | 29 | 21 | 2024-12-23 | 2024-12-26 | 4 | 4 | 2024-12-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-23 | 2024-10-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1369.64 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-23 | 2024-06-12 | Unknown | Unknown | 2024-06-12 | 2024-10-17 | 128 | 92 | 2024-10-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-17 | 2025-07-01 | 258 | 184 | Unknown | Unknown | Unknown | Unknown | 2025-07-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R29/R45 | UG | IOU Design | Commercial | N/A | SAN DIEGO | SAN DIEGO | 3043 | 3043 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-08-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-29 | 2024-04-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 41971.95 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-29 | 2024-07-01 | 124 | 88 | 2024-07-01 | 2025-02-27 | 242 | 174 | 2024-08-20 | 2025-02-12 | 51 | 37 | 2024-09-17 | 2025-03-07 | 81 | 59 | 2025-02-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-09 | 2025-04-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1063.64 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-09 | 2025-04-03 | 116 | 84 | 2025-04-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-15 | 2024-05-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 28804 | 352.82 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-15 | 2023-12-28 | 44 | 32 | 2023-12-28 | 2024-10-15 | 293 | 209 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 41.4 | 41.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-03 | 2024-06-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1144.15 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-03 | 2024-08-05 | 64 | 46 | 2024-08-05 | 2024-08-05 | 1 | 1 | 2024-08-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 208.6 | 208.6 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-13 | 2023-11-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 16964.08 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-13 | 2023-11-13 | 1 | 1 | 2023-11-13 | 2024-07-03 | 234 | 168 | 2023-11-17 | 2024-06-13 | 210 | 150 | 2024-07-09 | 2024-07-12 | 4 | 4 | 2024-07-03 | Unknown | Unknown | Unknown | 2025-07-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-17 | 2024-10-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2050.87 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-17 | 2024-10-10 | Unknown | Unknown | 2024-10-10 | 2024-11-14 | 36 | 26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 29.05 | 29.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-18 | 2025-04-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2025.32 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-18 | 2025-04-18 | 1 | 1 | 2025-04-18 | 2025-04-18 | 1 | 1 | 2025-04-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-18 | 2025-07-09 | 83 | 59 | Unknown | Unknown | Unknown | Unknown | 2025-07-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-11-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-20 | 2024-08-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2875.23 | 848.01 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-20 | 2025-02-11 | 176 | 126 | 2025-02-11 | 2025-02-25 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 358.15 | 358.15 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-15 | Unknown | Unknown | No | 2024-10-09 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-09 | 2024-10-09 | Unknown | IOU Designed & Installed | N/A | Yes | 169 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 8962 | 40633.67 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-09 | 2025-02-10 | 125 | 89 | 2025-02-10 | 2025-06-10 | 121 | 87 | 2025-03-21 | 2025-05-13 | 12 | 8 | 2025-04-16 | 2025-06-02 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 25.05 | 25.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-20 | 2024-09-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1675.63 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-20 | 2024-08-30 | Unknown | Unknown | 2024-08-30 | 2024-09-30 | 32 | 22 | 2024-09-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | JAMUL | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-13 | 2024-11-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 4615.18 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-13 | 2024-11-13 | 1 | 1 | 2024-11-13 | 2024-11-13 | 1 | 1 | 2024-11-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-21 | 2025-01-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 6206.14 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-21 | 2025-03-03 | 42 | 30 | 2025-03-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | DEL MAR | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-15 | 2023-07-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1061.78 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-15 | 2023-04-06 | Unknown | Unknown | 2023-04-06 | 2023-07-17 | 103 | 73 | 2023-07-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SANTEE | N/A | 53 | 53 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-03 | 2023-11-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3941 | 810.6 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-03 | 2023-09-28 | Unknown | Unknown | 2023-09-28 | 2023-11-03 | 37 | 27 | 2023-11-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2018-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-14 | 2023-07-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 427.63 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-14 | 2023-07-17 | 4 | 2 | 2023-07-17 | 2025-05-08 | 662 | 474 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Commercial | Underserved Community | San Ysidro | CALTRANS-SOUTH of 56, SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2021-03-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-18 | 2023-08-31 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 21765.78 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-18 | 2023-03-04 | Unknown | Unknown | 2023-03-04 | 2025-02-24 | 724 | 516 | 2024-11-06 | 2025-02-20 | 107 | 77 | 2024-08-13 | 2025-03-10 | 23 | 16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | N/A | 303.05 | 303.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-16 | 2023-05-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1812.55 | Unknown | Unknown | Yes | N/A | N/A | 2023-05-16 | 2023-05-16 | 1 | 1 | 2023-05-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2020-01-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-30 | 2023-07-05 | 2023-07-24 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1110.53 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-30 | 2023-07-03 | 4 | 2 | 2023-07-03 | 2023-07-03 | 1 | 1 | 2023-07-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-05 | 2023-07-24 | 20 | 14 | Unknown | Unknown | Unknown | Unknown | 2023-07-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-12 | 2025-03-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7962 | 804.3 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-12 | 2025-05-16 | 66 | 48 | 2025-05-16 | 2025-06-18 | 34 | 24 | 2025-03-28 | 2025-05-16 | 50 | 36 | Unknown | Unknown | Unknown | Unknown | 2025-06-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ESCONDIDO | COUNTY OF SAN DIEGO-NORTH of 56 | 65.05 | 65.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-11 | 2024-11-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1007.35 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-11 | 2024-11-11 | 1 | 1 | 2024-11-11 | 2025-07-16 | 248 | 178 | 2025-04-22 | 2025-04-23 | 2 | 2 | 2025-04-23 | 2025-07-16 | 55 | 39 | 2025-07-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN YSIDRO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2021-03-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-19 | 2023-12-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 994.14 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-19 | 2024-01-11 | 24 | 18 | 2024-01-11 | 2025-02-18 | 405 | 289 | Unknown | Unknown | Unknown | Unknown | 2024-01-19 | 2024-01-30 | 12 | 8 | 2025-02-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-28 | 2025-02-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1500.4 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-28 | 2025-02-26 | Unknown | Unknown | 2025-02-26 | 2025-02-28 | 3 | 3 | 2025-02-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | N/A | 112.05 | 112.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-06 | Unknown | Unknown | No | 2023-04-19 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-19 | 2023-04-19 | Unknown | IOU Designed & Installed | N/A | Yes | 183 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3961 | 154.99 | Unknown | Unknown | Yes | N/A | N/A | 2023-04-19 | 2023-10-18 | 183 | 131 | 2023-10-18 | 2023-10-19 | 2 | 2 | 2023-10-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | ESCONDIDO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-21 | 2024-10-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2780 | 491.5 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-21 | 2024-09-19 | Unknown | Unknown | 2024-09-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-22 | 2024-11-13 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | N/A | Rancho Mission Viejo | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-19 | 2023-12-19 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 357970.66 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-19 | 2024-04-08 | 112 | 80 | 2024-04-08 | 2025-01-08 | 276 | 198 | 2024-07-11 | 2025-04-29 | 111 | 79 | 2024-09-18 | 2025-02-07 | 141 | 100 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-08 | 2024-05-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7320 | 584.27 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-08 | 2024-02-28 | Unknown | Unknown | 2024-02-28 | 2024-05-08 | 71 | 51 | 2024-05-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-08 | 2025-08-28 | 478 | 342 | Unknown | Unknown | Unknown | Unknown | 2025-08-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | POWAY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-18 | 2025-02-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3566.76 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-18 | 2025-02-10 | 146 | 104 | 2025-02-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-24 | 2025-02-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1672.35 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-24 | 2025-02-13 | Unknown | Unknown | 2025-02-13 | 2025-03-13 | 29 | 21 | Unknown | Unknown | Unknown | Unknown | 2025-02-25 | 2025-03-12 | 16 | 12 | 2025-03-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-24 | 2024-10-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 4676292 | 17448.13 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-24 | 2024-06-18 | 147 | 105 | 2024-06-18 | 2024-11-26 | 162 | 116 | Unknown | Unknown | Unknown | Unknown | 2025-02-14 | 2025-02-14 | 1 | 1 | 2024-11-26 | 2025-06-26 | 213 | 153 | Unknown | 2025-08-26 | Unknown | Unknown | 2025-09-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-07 | 2025-05-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7962 | 1567.39 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-07 | 2025-04-23 | Unknown | Unknown | 2025-04-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LAGUNA NIGUEL | N/A | 12 | 12 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-17 | 2025-01-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 196.69 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-17 | 2025-02-03 | 18 | 12 | 2025-02-03 | 2025-02-05 | 3 | 3 | 2025-02-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 38 | 38 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-25 | 2025-06-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1067.09 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-25 | 2025-06-25 | 1 | 1 | 2025-06-25 | 2025-06-25 | 1 | 1 | 2025-06-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-25 | 2025-07-09 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2025-07-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | MISSION VIEJO | N/A | 68 | 68 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-28 | 2024-08-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1299.41 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-28 | 2024-08-27 | Unknown | Unknown | 2024-08-27 | 2024-09-18 | 23 | 17 | 2024-09-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-18 | 2025-07-15 | 301 | 215 | Unknown | 2025-06-30 | Unknown | Unknown | 2025-07-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 61 | 61 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-27 | 2024-08-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1116.14 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-27 | 2024-01-29 | Unknown | Unknown | 2024-01-29 | 2024-10-14 | 260 | 186 | 2024-10-14 | 2025-03-20 | 158 | 114 | Unknown | Unknown | Unknown | Unknown | 2025-03-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-25 | 2023-04-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 628.44 | Unknown | Unknown | Yes | N/A | N/A | 2023-04-25 | 2023-04-25 | 1 | 1 | 2023-04-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SPRING VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-28 | 2023-11-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 4492.53 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-28 | 2023-12-13 | 16 | 12 | 2023-12-13 | 2025-05-05 | 510 | 364 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 153 | 153 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-28 | 2023-12-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 21913.97 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-28 | 2023-12-28 | 1 | 1 | 2023-12-28 | 2024-08-07 | 224 | 160 | Unknown | Unknown | Unknown | Unknown | 2024-06-03 | 2024-09-26 | 72 | 52 | 2024-08-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 85.05 | 85.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-06 | 2025-03-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1403.25 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-06 | 2025-08-21 | 169 | 121 | 2025-08-21 | 2025-08-22 | 2 | 2 | 2025-03-12 | 2025-03-25 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | 2025-04-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | N/A | Chula Vista | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-02 | 2024-12-02 | 2025-03-07 | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 202134.78 | 119919.25 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-02 | 2024-12-12 | 11 | 9 | 2024-12-12 | 2025-02-27 | 78 | 56 | 2024-12-17 | 2025-02-11 | 57 | 41 | 2025-02-28 | 2025-04-07 | 39 | 27 | 2025-03-07 | Unknown | Unknown | Unknown | 2025-03-07 | 2025-04-14 | 39 | 27 | 2025-03-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2022-12-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-12 | 2023-01-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2875 | 1396.97 | Unknown | Unknown | Yes | N/A | N/A | 2023-01-12 | 2023-02-01 | 21 | 15 | 2023-02-01 | 2024-05-30 | 485 | 347 | Unknown | Unknown | Unknown | Unknown | 2024-07-10 | 2024-07-10 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | Underserved Community | San Diego | San Diego | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-16 | 2024-05-16 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 59787.87 | 20982.43 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-16 | 2024-08-26 | 103 | 73 | 2024-08-26 | 2025-06-30 | 309 | 221 | 2024-09-10 | 2025-06-24 | -87 | -71 | 2024-10-16 | 2025-07-09 | 80 | 57 | 2025-07-03 | Unknown | Unknown | Unknown | 2025-07-03 | 2025-08-22 | 51 | 37 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-18 | 2025-02-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1746.37 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-18 | 2025-02-20 | 3 | 3 | 2025-02-20 | 2025-02-20 | 1 | 1 | 2025-02-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2021-03-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-23 | 2024-10-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 482.45 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-23 | 2024-10-24 | 2 | 2 | 2024-10-24 | 2025-02-24 | 124 | 88 | Unknown | Unknown | Unknown | Unknown | 2024-11-30 | 2025-01-09 | 41 | 29 | 2025-02-24 | 2025-08-20 | 178 | 128 | Unknown | 2025-07-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | 1168 | 1168 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2024-07-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-26 | 2024-01-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | 71718.34 | 25721.18 | Unknown | 62.29 | 4022.66 | 41912.21 | 414493 | 22386.4 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-26 | 2024-01-26 | 1 | 1 | 2024-01-26 | 2024-02-22 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-22 | 2024-10-24 | 246 | 176 | Unknown | 2024-11-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-08 | 2025-01-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 730.21 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-08 | 2024-12-17 | Unknown | Unknown | 2024-12-17 | 2025-01-27 | 42 | 30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-27 | 2025-08-21 | 207 | 149 | Unknown | 2025-08-12 | Unknown | Unknown | 2025-08-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-03-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-02 | 2022-05-31 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2549.67 | Unknown | Unknown | Yes | N/A | N/A | 2022-05-02 | 2023-08-15 | 471 | 337 | 2023-08-15 | 2024-01-11 | 150 | 108 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-19 | 2023-05-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 479.76 | Unknown | Unknown | Yes | N/A | N/A | 2023-05-19 | 2023-05-19 | 1 | 1 | 2023-05-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | Oceanside | N/A | 80 | 80 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-17 | 2024-01-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 35321 | 13666.24 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-17 | 2023-11-17 | 1 | 1 | 2023-11-17 | 2024-06-05 | 202 | 144 | 2023-12-01 | 2024-01-12 | 43 | 31 | 2025-05-29 | 2025-07-15 | 47 | 31 | 2024-06-05 | Unknown | Unknown | Unknown | 2024-06-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | LAKESIDE | N/A | 75 | 75 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-18 | 2024-05-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2119.64 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-18 | 2024-05-14 | 27 | 19 | 2024-05-14 | 2024-07-18 | 66 | 48 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2022-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-19 | 2023-06-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 743.75 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-19 | 2023-06-19 | 1 | 1 | 2023-06-19 | 2023-06-28 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | 424 | 424 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-16 | 2024-04-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2109.63 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-16 | 2024-02-28 | Unknown | Unknown | 2024-02-28 | 2024-04-16 | 49 | 35 | 2024-04-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-07 | 2024-05-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 6237 | 46115.19 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-07 | 2024-02-02 | Unknown | Unknown | 2024-02-02 | 2025-05-09 | 463 | 331 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-09 | Unknown | Unknown | Unknown | Unknown | 2025-08-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | RAMONA | N/A | 67.05 | 67.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-07 | 2023-06-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 523.12 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-07 | 2023-06-02 | Unknown | Unknown | 2023-06-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | N/A | 9 | 9 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-02 | 2025-05-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 908.95 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-02 | 2025-05-09 | 8 | 6 | 2025-05-09 | 2025-06-02 | 25 | 17 | 2025-06-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | N/A | CB 1148-A2 town squre WO1 (E) | CARLSBAD | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-02-22 | 2022-10-25 | 2025-06-10 | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | 208658.55 | 59021.62 | Unknown | Unknown | 25891.99 | 123744.94 | 0 | 92656.78 | Unknown | Unknown | Yes | N/A | N/A | 2022-02-22 | 2023-03-09 | 381 | 273 | 2023-03-09 | 2023-10-24 | 230 | 164 | 2023-03-16 | 2024-01-22 | 39 | 29 | 2023-10-24 | 2024-03-08 | 136 | 98 | 2024-05-09 | Unknown | Unknown | Unknown | 2024-05-09 | 2025-06-03 | 391 | 279 | 2025-06-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | Applicant Design | Commercial | Underserved Community | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-08-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-03 | 2024-10-03 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 12033 | 54966.89 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-03 | 2024-10-15 | 13 | 9 | 2024-10-15 | 2025-05-01 | 199 | 143 | 2025-01-10 | 2025-02-19 | 4 | 2 | 2025-01-09 | 2025-05-07 | 32 | 24 | 2025-05-01 | Unknown | Unknown | Unknown | 2025-05-19 | 2025-06-20 | 33 | 25 | 2025-07-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 72 | 72 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-14 | 2024-02-14 | 2024-08-13 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7962 | 946.99 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-14 | 2023-09-07 | Unknown | Unknown | 2023-09-07 | 2024-04-21 | 228 | 162 | 2024-04-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-21 | 2024-08-13 | 115 | 82 | Unknown | Unknown | Unknown | Unknown | 2024-08-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CORONADO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-03-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-20 | 2023-04-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1126.45 | Unknown | Unknown | Yes | N/A | N/A | 2022-09-20 | 2023-04-24 | 217 | 155 | 2023-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-22 | 2025-04-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1240.65 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-22 | 2025-04-21 | Unknown | Unknown | 2025-04-21 | 2025-04-22 | 2 | 2 | 2025-04-22 | 2025-05-09 | 18 | 14 | Unknown | Unknown | Unknown | Unknown | 2025-04-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-26 | 2025-02-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3694.25 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-26 | 2025-02-26 | 1 | 1 | 2025-02-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | LADERA RANCH | N/A | 9 | 9 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-17 | 2024-05-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 74.16 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-17 | 2024-06-07 | 22 | 16 | 2024-06-07 | 2024-06-07 | 1 | 1 | 2024-06-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-23 | 2023-04-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 909.37 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-23 | 2023-04-20 | 29 | 21 | 2023-04-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | 142.45 | 142.45 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-17 | 2025-03-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 13730 | 793.77 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-17 | 2025-03-31 | 288 | 206 | 2025-03-31 | 2025-05-06 | 37 | 27 | Unknown | Unknown | Unknown | Unknown | 2025-03-31 | 2025-04-10 | 11 | 9 | 2025-05-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Commercial | Underserved Community | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-02 | 2024-12-02 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 52379.5 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-02 | 2025-05-05 | 155 | 111 | 2025-05-05 | 2025-06-04 | 31 | 23 | 2025-05-07 | 2025-05-30 | 10 | 8 | 2025-05-21 | 2025-06-13 | 23 | 16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-24 | 2025-04-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 817.06 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-24 | 2025-05-16 | 23 | 17 | 2025-05-16 | 2025-05-22 | 7 | 5 | 2025-05-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 145.05 | 145.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-19 | 2025-02-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 837.21 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-19 | 2025-02-03 | Unknown | Unknown | 2025-02-03 | 2025-04-30 | 87 | 63 | 2025-04-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-30 | 2025-08-11 | 104 | 74 | Unknown | 2025-07-22 | Unknown | Unknown | 2025-08-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-04-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-01 | 2023-03-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 290.7 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-01 | 2023-03-01 | 1 | 1 | 2023-03-01 | 2023-05-01 | 62 | 44 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-15 | 2025-01-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 316286 | 40483.68 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-15 | 2025-02-25 | 42 | 30 | 2025-02-25 | 2025-03-31 | 35 | 25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 39.05 | 39.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-25 | 2024-01-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 804.22 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-25 | 2024-04-03 | 70 | 50 | 2024-04-03 | 2024-04-03 | 1 | 1 | 2024-04-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 2.7 | 2.7 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-26 | 2025-04-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1254.69 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-26 | 2025-04-25 | Unknown | Unknown | 2025-04-25 | 2025-04-26 | 2 | 1 | 2025-04-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-26 | 2025-07-07 | 73 | 51 | Unknown | Unknown | Unknown | Unknown | 2025-07-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community,Tribal Community | VALLEY CENTER | N/A | 67.05 | 67.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-06 | 2024-12-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1080.21 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-06 | 2025-04-10 | 126 | 90 | 2025-04-10 | 2025-05-06 | 27 | 19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Commercial | Underserved Community | Chula Vista | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-03 | 2023-04-03 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 20487.49 | Unknown | Unknown | Yes | N/A | N/A | 2023-04-03 | 2023-07-27 | 116 | 84 | 2023-07-27 | 2023-11-20 | 117 | 83 | 2023-08-04 | 2023-11-15 | 66 | 46 | 2023-11-17 | 2023-11-22 | 6 | 4 | 2023-12-04 | Unknown | Unknown | Unknown | 2023-12-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-19 | 2025-02-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 205521 | 15382.54 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-19 | 2025-04-04 | 45 | 33 | 2025-04-04 | 2025-05-16 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | 125.75 | 125.75 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-06 | 2025-05-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1074.31 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-06 | 2025-05-15 | 10 | 8 | 2025-05-15 | 2025-05-20 | 6 | 4 | 2025-05-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN JUAN CAPISTRANO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-17 | 2023-10-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 955.97 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-17 | 2024-03-29 | 165 | 119 | 2024-03-29 | 2024-03-29 | 1 | 1 | 2024-03-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | ESCONDIDO | 12 | 12 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-05 | Unknown | Unknown | No | 2024-09-19 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-19 | 2024-09-19 | Unknown | IOU Designed & Installed | N/A | Yes | 119 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1393.1 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-19 | 2024-11-14 | 57 | 41 | 2024-11-14 | 2025-03-20 | 127 | 91 | Unknown | Unknown | Unknown | Unknown | 2025-01-06 | 2025-01-13 | 8 | 6 | 2025-03-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-02 | 2024-10-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3961 | 1150.65 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-02 | 2024-10-23 | 22 | 16 | 2024-10-23 | 2024-11-04 | 13 | 9 | 2024-11-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | IMPERIAL BEACH | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-14 | 2025-05-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 11943 | 2537.36 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-14 | 2025-05-08 | 84 | 60 | 2025-05-08 | 2025-05-15 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2025-05-08 | 2025-07-08 | 62 | 44 | 2025-05-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | 43 | 43 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-28 | 2024-06-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1435.45 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-28 | 2024-04-08 | Unknown | Unknown | 2024-04-08 | 2024-06-28 | 82 | 60 | 2024-06-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Residential | N/A | ENCINITAS | ENCINITAS | 112.05 | 112.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-03 | 2024-10-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 31766 | 70394.65 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-03 | 2024-06-03 | Unknown | Unknown | 2024-06-03 | 2025-05-30 | 362 | 260 | 2024-11-01 | 2025-05-30 | 18 | 14 | 2025-05-06 | 2025-07-21 | 77 | 55 | 2025-06-10 | Unknown | Unknown | Unknown | 2025-06-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | Underserved Community | Chula Vista | CHULA VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-02-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-05 | 2024-01-05 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 211390.62 | 122362.03 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-05 | 2024-07-23 | 201 | 143 | 2024-07-23 | 2025-04-16 | 268 | 192 | 2024-08-13 | 2025-09-02 | 177 | 127 | 2024-09-26 | 2025-05-08 | 32 | 24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 7 | 7 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-12 | 2024-03-19 | 2024-04-08 | IOU Designed & Installed | N/A | No | Unknown | 1.41 | 0 | Unknown | Unknown | Unknown | 1.41 | 3961 | 163.83 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-12 | 2024-02-08 | Unknown | Unknown | 2024-02-08 | 2024-04-05 | 58 | 42 | 2024-04-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-05 | 2024-04-08 | 4 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-04-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-03 |  | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 823.12 | Unknown | Unknown | Yes | N/A | N/A | 2023-05-03 | 2023-05-03 | 1 | 1 | 2023-05-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | OH | IOU Design | Residential | N/A | San Clemente | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-06 | 2025-01-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 6791.09 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-06 | 2025-01-06 | 1 | 1 | 2025-01-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-18 | 2025-06-18 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-07-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 142.05 | 142.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-05 | 2024-07-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1098.48 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-05 | 2024-09-18 | 76 | 54 | 2024-09-18 | 2024-09-20 | 3 | 3 | 2024-09-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SPRINg VALLEY | COUNTY OF SAN DIEGO-SOUTH of 56 | 154.05 | 154.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-18 | 2023-09-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 6367.78 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-18 | 2023-08-22 | 36 | 26 | 2023-08-22 | 2023-10-05 | 45 | 33 | Unknown | Unknown | Unknown | Unknown | 2023-09-18 | 2023-10-09 | 14 | 10 | 2023-10-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 31.35 | 31.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-11 | 2025-04-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3111.83 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-11 | 2025-05-07 | 27 | 19 | 2025-05-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-27 | Unknown | Unknown | Unknown | 2025-05-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | 121.05 | 121.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-09 | 2025-05-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1197.24 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-09 | 2025-03-20 | Unknown | Unknown | 2025-03-20 | 2025-05-05 | 47 | 33 | 2025-05-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | OH | Applicant Design | Residential | Underserved Community | San Diego | SAN DIEGO | 4127 | 4127 | Not Available | >2MW | No | N/A | N/A | N/A | 2022-04-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-23 | 2024-01-23 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 68037.61 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-23 | 2024-08-02 | 193 | 139 | 2024-08-02 | 2025-06-26 | 329 | 235 | 2024-08-14 | 2025-06-23 | 85 | 61 | 2025-01-29 | 2025-06-30 | 35 | 25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-08-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 20.05 | 20.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-16 | 2024-12-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1224.87 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-16 | 2025-01-23 | 39 | 29 | 2025-01-23 | 2025-01-23 | 1 | 1 | 2025-01-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-19 | 2023-05-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 8997 | 554.66 | Unknown | Unknown | Yes | N/A | N/A | 2023-05-19 | 2023-05-19 | 1 | 1 | 2023-05-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | MISSION VIEJO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-12 | 2025-06-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 567.22 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-12 | 2025-05-28 | Unknown | Unknown | 2025-05-28 | 2025-06-20 | 24 | 18 | 2025-06-12 | 2025-06-20 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | 2025-06-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2020-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-18 | 2024-12-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3211.01 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-18 | 2024-12-18 | 62 | 44 | 2024-12-18 | 2025-02-11 | 56 | 40 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-23 | 2024-04-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 529.2 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-23 | 2024-04-23 | 1 | 1 | 2024-04-23 | 2024-04-23 | 1 | 1 | 2024-04-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-03 | 2024-07-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1119.09 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-03 | 2024-07-03 | 1 | 1 | 2024-07-03 | 2024-07-03 | 1 | 1 | 2024-07-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | Oceanside | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-26 | 2024-09-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 15924 | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2024-06-26 | 2024-08-26 | 62 | 44 | 2024-08-26 | 2024-11-06 | 73 | 53 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-29 | 2023-03-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2693.42 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-29 | 2023-08-29 | 154 | 110 | 2023-08-29 | 2024-01-10 | 135 | 97 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | San Diego | CALTRANS-SOUTH of 56, SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2026-03-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-06 | 2024-03-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 54899 | 81.53 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-06 | 2024-08-16 | 164 | 118 | 2024-08-16 | 2024-08-29 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | 2024-03-20 | 2024-08-21 | 82 | 58 | 2024-08-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-30 | 2023-08-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 675.3 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-30 | 2023-06-22 | Unknown | Unknown | 2023-06-22 | 2023-09-07 | 78 | 56 | 2023-09-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-02 | 2025-01-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 196.69 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-02 | 2025-01-15 | 14 | 10 | 2025-01-15 | 2025-02-10 | 27 | 19 | 2025-02-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-15 | 2024-08-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2657.15 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-15 | 2024-08-16 | 2 | 2 | 2024-08-16 | 2024-08-16 | 1 | 1 | 2024-08-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-16 | 2025-08-13 | 363 | 259 | Unknown | 2025-07-17 | Unknown | Unknown | 2025-08-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-03 | 2025-06-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1044.6 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-03 | 2025-06-03 | 1 | 1 | 2025-06-03 | 2025-06-03 | 1 | 1 | 2025-06-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2018-03-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-10 | 2024-10-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1050.78 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-10 | 2024-09-09 | Unknown | Unknown | 2024-09-09 | 2024-10-10 | 32 | 24 | 2024-10-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-18 | 2024-07-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1389.94 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-18 | 2024-05-30 | Unknown | Unknown | 2024-05-30 | 2024-07-18 | 50 | 36 | 2024-07-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SANTEE | N/A | 57.05 | 57.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-03 | 2024-05-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1413.77 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-03 | 2024-03-06 | Unknown | Unknown | 2024-03-06 | 2024-05-17 | 73 | 53 | 2024-05-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-27 | 2025-03-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1716.03 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-27 | 2025-02-24 | Unknown | Unknown | 2025-02-24 | 2025-03-10 | 15 | 11 | 2025-03-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | 150 | 150 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-24 | 2025-04-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 47640.6 | 6598.47 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-24 | 2024-08-01 | Unknown | Unknown | 2024-08-01 | 2025-06-02 | 306 | 218 | Unknown | Unknown | Unknown | Unknown | 2025-04-04 | 2025-04-17 | 14 | 10 | 2025-06-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 55.05 | 55.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-04 | 2024-01-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1013.25 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-04 | 2023-12-29 | Unknown | Unknown | 2023-12-29 | 2024-01-10 | 13 | 9 | 2024-01-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community,Tribal Community | Valley Center | N/A | 9 | 9 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-16 | 2025-05-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 4322.14 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-16 | 2025-05-14 | Unknown | Unknown | 2025-05-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 1631.05 | 1631.05 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2026-07-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-18 | 2024-11-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1412.81 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-18 | 2024-11-11 | Unknown | Unknown | 2024-11-11 | 2024-11-21 | 11 | 9 | 2024-11-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | 9.05 | 9.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-17 | 2025-03-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1532.86 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-17 | 2025-05-21 | 66 | 48 | 2025-05-21 | 2025-05-29 | 9 | 7 | 2025-05-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 3.84 | 3.84 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-26 | 2024-08-26 | 2024-11-08 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1361.26 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-26 | 2024-07-29 | Unknown | Unknown | 2024-07-29 | 2024-09-09 | 43 | 31 | 2024-09-09 | Unknown | Unknown | Unknown | 2024-09-25 | 2024-09-25 | 1 | 1 | 2024-09-09 | 2024-11-08 | 61 | 45 | Unknown | Unknown | Unknown | Unknown | 2024-11-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | BOULEVARD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-01 | 2023-11-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 725.93 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-01 | 2023-09-27 | Unknown | Unknown | 2023-09-27 | 2023-11-02 | 37 | 27 | 2023-11-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 36 | 36 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-29 | 2025-05-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1091.99 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-29 | 2025-08-20 | 84 | 60 | 2025-08-20 | 2025-06-04 | Unknown | Unknown | 2025-06-04 | 2025-06-26 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | 2025-06-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-04 | 2025-06-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 487.61 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-04 | 2025-05-16 | Unknown | Unknown | 2025-05-16 | 2025-06-09 | 25 | 17 | 2025-06-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-28 | 2024-09-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1861.69 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-28 | 2024-08-29 | 2 | 2 | 2024-08-29 | 2024-10-02 | 35 | 25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | CAMPO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-13 | 2024-03-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1854.4 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-13 | 2024-02-06 | Unknown | Unknown | 2024-02-06 | 2024-03-13 | 37 | 27 | 2024-03-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-08 | 2025-04-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2193.9 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-08 | 2025-03-31 | Unknown | Unknown | 2025-03-31 | 2025-04-08 | 9 | 7 | 2025-04-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SPRING VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-02 | 2023-02-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 263.31 | Unknown | Unknown | Yes | N/A | N/A | 2023-02-02 | 2023-02-02 | 1 | 1 | 2023-02-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | 1569 | 1569 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2023-04-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-01 | 2023-07-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 5865 | 8952.84 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-01 | 2023-04-28 | Unknown | Unknown | 2023-04-28 | 2024-01-09 | 257 | 183 | Unknown | Unknown | Unknown | Unknown | 2023-07-07 | 2023-07-14 | 8 | 6 | 2024-01-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-09 | 2025-01-09 | 2025-03-06 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2344.92 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-09 | 2025-03-04 | 55 | 39 | 2025-03-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | LAGUNA NIGUEL | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-06-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-19 | 2025-06-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 872.52 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-19 | 2025-06-19 | 1 | 1 | 2025-06-19 | 2025-06-26 | 8 | 6 | 2025-06-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-26 | 2025-07-16 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | 2025-07-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | OH | Applicant Design | Commercial | Underserved Community | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-07 | 2024-03-07 | 2025-06-16 | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 602685 | 60938.33 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-07 | 2024-09-16 | 194 | 138 | 2024-09-16 | 2025-05-23 | 250 | 180 | 2024-09-30 | 2025-05-21 | 86 | 62 | 2024-10-28 | 2025-05-30 | 61 | 45 | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-11 | Unknown | Unknown | 2025-06-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | CALTRANS-SOUTH of 56, SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-13 | 2025-02-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 7060.6 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-13 | 2025-02-14 | 2 | 2 | 2025-02-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-10 | 2025-07-07 | 18 | 10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | LAGUNA NIGUEL | N/A | 97 | 97 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-03 | 2024-01-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 163324 | 2500 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-03 | 2024-01-10 | 8 | 6 | 2024-01-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-27 | 2023-10-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 916.08 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-27 | 2023-10-03 | Unknown | Unknown | 2023-10-03 | 2023-11-01 | 30 | 22 | 2023-11-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | 580.2 | 580.2 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-13 | 2024-11-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 11943 | 2154.71 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-13 | 2025-01-30 | 79 | 57 | 2025-01-30 | 2025-08-01 | 184 | 132 | Unknown | Unknown | Unknown | Unknown | 2025-01-30 | 2025-02-20 | 22 | 16 | 2025-08-01 | 2025-08-29 | 29 | 21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 39.05 | 39.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-29 | 2024-10-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 906.52 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-29 | 2025-01-14 | 78 | 56 | 2025-01-14 | 2025-01-14 | 1 | 1 | 2025-01-14 | 2025-01-29 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | 2025-01-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 49.4 | 49.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-28 | 2025-01-31 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1370.36 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-28 | 2025-01-31 | 4 | 4 | 2025-01-31 | 2025-01-31 | 1 | 1 | 2025-01-31 | 2025-02-11 | 12 | 8 | Unknown | Unknown | Unknown | Unknown | 2025-02-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-29 | 2023-10-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 514.57 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-29 | 2023-10-13 | 15 | 11 | 2023-10-13 | 2023-10-13 | 1 | 1 | 2023-10-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-09 | 2024-05-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7681 | 584.27 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-09 | 2024-04-16 | Unknown | Unknown | 2024-04-16 | 2024-05-09 | 24 | 18 | 2024-05-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-09 | 2025-08-21 | 470 | 336 | Unknown | Unknown | Unknown | Unknown | 2025-08-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | 54 | 54 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-15 | 2024-08-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 144706 | 8642.47 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-15 | 2024-05-21 | 7 | 5 | 2024-05-21 | 2024-09-04 | 107 | 77 | Unknown | Unknown | Unknown | Unknown | 2024-12-06 | 2024-12-06 | 1 | 1 | 2024-09-04 | 2025-07-17 | 317 | 227 | Unknown | 2025-07-19 | Unknown | Unknown | 2025-08-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-18 | 2025-06-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1025.1 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-18 | 2025-06-18 | 1 | 1 | 2025-06-18 | 2025-06-19 | 2 | 2 | 2025-06-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 44.2 | 44.2 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-13 | 2025-03-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 997.19 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-13 | 2025-03-12 | Unknown | Unknown | 2025-03-12 | 2025-03-28 | 17 | 13 | 2025-03-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-04 | 2025-03-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 822.57 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-04 | 2025-03-04 | 1 | 1 | 2025-03-04 | 2025-04-09 | 37 | 27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-09 | 2025-07-30 | 113 | 81 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-14 | 2025-05-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1458.07 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-14 | 2025-05-14 | 1 | 1 | 2025-05-14 | 2025-06-25 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-25 | Unknown | Unknown | Unknown | Unknown | 2025-07-28 | Unknown | Unknown | 2025-07-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-16 | 2024-08-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1147.19 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-16 | 2024-09-10 | 26 | 18 | 2024-09-10 | 2024-09-10 | 1 | 1 | 2024-09-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-10 | 2024-08-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 23886 | 1284.2 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-10 | 2024-07-10 | 1 | 1 | 2024-07-10 | 2024-11-27 | 141 | 101 | Unknown | Unknown | Unknown | Unknown | 2025-06-17 | 2025-07-08 | 22 | 16 | 2024-11-27 | 2025-08-29 | 276 | 198 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Disadvantaged Community,Underserved Community | NATIONAL CITY | NATIONAL CITY | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-27 | 2023-07-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 28804 | 334.14 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-27 | 2023-08-25 | 30 | 22 | 2023-08-25 | 2025-09-05 | 743 | 531 | 2023-10-03 | 2024-05-02 | 27 | 21 | 2023-08-29 | 2024-05-07 | 99 | 71 | 2025-09-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | LAKESIDE | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-09 | 2025-06-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 22587 | 2391.21 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-09 | 2025-06-09 | 1 | 1 | 2025-06-09 | 2025-06-18 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | 2025-06-09 | 2025-06-17 | 9 | 7 | 2025-06-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 730.05 | 730.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-22 | 2023-08-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 842.15 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-22 | 2023-08-22 | 1 | 1 | 2023-08-22 | 2023-08-23 | 2 | 2 | 2023-08-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-11 | 2024-04-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1195.65 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-11 | 2024-04-12 | 2 | 2 | 2024-04-12 | 2024-04-13 | 2 | 1 | 2024-04-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 43.05 | 43.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-19 | 2025-06-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1049.74 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-19 | 2025-06-03 | 16 | 12 | 2025-06-03 | 2025-06-03 | 1 | 1 | 2025-06-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-03 | 2025-09-03 | 93 | 67 | Unknown | Unknown | Unknown | Unknown | 2025-09-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2018-04-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-09 | 2024-09-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1023.72 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-09 | 2024-08-08 | Unknown | Unknown | 2024-08-08 | 2024-09-09 | 33 | 23 | 2024-09-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SOUTH LAGUNA | N/A | 76.05 | 76.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-24 | 2025-02-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1203.01 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-24 | 2025-02-28 | 5 | 5 | 2025-02-28 | 2025-02-28 | 1 | 1 | 2025-02-28 | 2025-06-23 | 116 | 82 | Unknown | Unknown | Unknown | Unknown | 2025-06-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | SAN DIEGO | 52 | 52 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-31 | 2023-08-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 99894 | 25375.08 | Unknown | Unknown | Yes | N/A | N/A | 2023-05-31 | 2023-08-07 | 69 | 49 | 2023-08-07 | 2023-10-19 | 74 | 54 | 2023-08-25 | 2023-08-30 | 6 | 4 | 2023-10-17 | 2023-10-25 | 8 | 4 | 2023-10-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | COUNTY OF SAN DIEGO-SOUTH of 56 | 36 | 36 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-15 | 2025-04-16 | 2025-04-22 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1763.5 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-15 | 2025-04-03 | Unknown | Unknown | 2025-04-03 | 2025-04-16 | 14 | 10 | 2025-04-16 | Unknown | Unknown | Unknown | 2025-04-16 | 2025-04-21 | 6 | 4 | 2025-04-16 | 2025-04-22 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2025-04-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | Lemon Grove | LEMON GROVE | 430 | 430 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-15 | 2024-02-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 315106.48 | 27913.19 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-15 | 2024-02-12 | 182 | 130 | 2024-02-12 | 2024-05-30 | 109 | 79 | 2024-03-25 | 2024-03-26 | 2 | 2 | 2024-05-21 | 2024-06-21 | 32 | 24 | 2024-05-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SD 1189-H1 JUNIPERS EV | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2024-03-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-03 | 2024-05-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 10272.56 | 16562.16 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-03 | 2024-06-19 | 78 | 56 | 2024-06-19 | 2024-07-11 | 23 | 17 | 2024-05-02 | 2024-05-03 | 2 | 2 | 2024-07-12 | 2024-07-16 | 5 | 3 | 2024-07-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-14 | 2024-06-27 | 2025-03-03 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 4273.48 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-14 | 2024-05-14 | 1 | 1 | 2024-05-14 | 2024-07-01 | 49 | 35 | 2024-07-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-27 | 2025-03-03 | 250 | 178 | Unknown | Unknown | Unknown | Unknown | 2025-03-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Residential | Underserved Community | Vista | COUNTY OF SAN DIEGO-NORTH of 56, VISTA | 146.05 | 146.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-25 | 2024-10-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 16828.55 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-25 | 2024-06-11 | Unknown | Unknown | 2024-06-11 | 2025-05-28 | 352 | 252 | 2025-02-04 | 2025-02-12 | 9 | 7 | 2025-02-18 | 2025-06-13 | 47 | 35 | 2025-06-24 | Unknown | Unknown | Unknown | 2025-06-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-08 | 2025-01-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 4878.17 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-08 | 2025-01-10 | 3 | 3 | 2025-01-10 | 2025-01-28 | 19 | 13 | 2025-01-13 | 2025-01-14 | 2 | 2 | 2025-01-14 | 2025-02-07 | 25 | 19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-15 | 2023-09-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 3073.28 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-15 | 2023-06-22 | Unknown | Unknown | 2023-06-22 | 2023-06-22 | 1 | 1 | 2023-06-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | RA 1152-E7 creekside WO2 (E) | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-31 | 2024-10-31 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2024-10-31 | 2024-10-31 | 1 | 1 | 2024-10-31 | 2025-04-28 | 180 | 128 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Commercial | Underserved Community | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2030-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-22 | 2023-10-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 946.86 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-22 | 2023-10-03 | 12 | 8 | 2023-10-03 | 2023-11-06 | 35 | 25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-11 | 2024-09-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1549.35 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-11 | 2024-09-13 | 3 | 3 | 2024-09-13 | 2024-09-13 | 1 | 1 | 2024-09-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-13 | 2025-01-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1706.51 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-13 | 2025-01-10 | Unknown | Unknown | 2025-01-10 | 2025-01-14 | 5 | 3 | 2025-01-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-04 | 2024-12-31 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1049.51 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-04 | 2024-12-13 | 10 | 8 | 2024-12-13 | 2024-12-31 | 19 | 13 | 2024-12-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-25 | 2024-11-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 311.78 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-25 | 2024-11-25 | 1 | 1 | 2024-11-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-06 | 2025-02-05 | 31 | 23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-27 | 2025-03-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2025.32 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-27 | 2025-03-18 | Unknown | Unknown | 2025-03-18 | 2025-03-27 | 10 | 8 | 2025-03-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-27 | 2025-07-24 | 120 | 86 | Unknown | Unknown | Unknown | Unknown | 2025-07-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2019-01-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-18 | 2023-05-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 4498 | 554.66 | Unknown | Unknown | Yes | N/A | N/A | 2023-05-18 | 2023-05-18 | 1 | 1 | 2023-05-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | ENCINITAS | ENCINITAS | 39.05 | 39.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-04 | 2025-04-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1907.48 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-04 | 2025-04-24 | 52 | 38 | 2025-04-24 | 2025-08-08 | 107 | 77 | Unknown | Unknown | Unknown | Unknown | 2025-05-14 | 2025-08-07 | 86 | 62 | 2025-08-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-08-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | BONITA | N/A | 57.05 | 57.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-05 | 2025-06-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 18300 | 2214.96 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-05 | 2025-05-27 | Unknown | Unknown | 2025-05-27 | 2025-06-05 | 10 | 8 | 2025-06-05 | 2025-06-19 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2025-06-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | ENCINITAS | ENCINITAS | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-06-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-16 | 2025-06-16 | 2025-06-18 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1763.5 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-16 | 2025-06-16 | 1 | 1 | 2025-06-16 | 2025-06-17 | 2 | 2 | 2025-06-17 | Unknown | Unknown | Unknown | 2025-06-17 | 2025-08-01 | 46 | 34 | 2025-06-16 | 2025-06-18 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2025-06-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | Disadvantaged Community,Underserved Community | Chula Vista | CHULA VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-09 | 2023-11-09 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 133802 | 111783.99 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-09 | 2024-10-28 | 355 | 253 | 2024-10-28 | 2025-03-19 | 143 | 103 | 2024-11-11 | 2025-08-01 | 32 | 23 | 2025-03-03 | 2025-04-25 | 48 | 36 | 2025-07-02 | Unknown | Unknown | Unknown | 2025-07-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | NATIONAL CITY | N/A | 465.05 | 465.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-22 | 2024-02-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1128.91 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-22 | 2023-12-28 | Unknown | Unknown | 2023-12-28 | 2024-02-26 | 61 | 43 | 2024-02-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | JAMUL | N/A | 67.05 | 67.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-22 | 2024-08-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3941 | 1472.99 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-22 | 2024-07-18 | Unknown | Unknown | 2024-07-18 | 2024-08-22 | 36 | 26 | 2024-08-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | POWAY | N/A | 5 | 5 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-29 | 2025-01-29 | 2025-02-19 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2220.96 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-29 | 2025-01-20 | Unknown | Unknown | 2025-01-20 | 2025-02-10 | 22 | 16 | 2025-02-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-10 | 2025-02-19 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | 2025-02-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | 21 | 21 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-02 | 2024-05-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 9490.07 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-02 | 2024-05-02 | 1 | 1 | 2024-05-02 | 2024-10-02 | 154 | 110 | 2024-06-07 | Unknown | Unknown | Unknown | 2024-10-03 | 2024-10-07 | 5 | 3 | 2024-10-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-09 | 2024-06-09 | 2024-12-11 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3241 | 2537.14 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-09 | 2024-06-09 | 1 | 0 | 2024-06-09 | 2024-06-09 | 1 | 0 | 2024-06-09 | 2024-06-25 | 17 | 12 | Unknown | Unknown | Unknown | Unknown | 2024-06-27 | 2024-12-11 | 168 | 120 | Unknown | 2024-11-08 | Unknown | Unknown | 2024-12-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | Underserved Community | SM 1128-C2 reloc rest. row | SAN MARCOS | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-10 | 2022-08-10 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 465628.56 | Unknown | Unknown | Yes | N/A | N/A | 2022-08-10 | 2024-05-23 | 653 | 467 | 2024-05-23 | Unknown | Unknown | Unknown | 2024-06-12 | 2024-06-28 | 17 | 13 | 2024-06-28 | 2024-11-15 | 110 | 80 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | VALLEY CENTER | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | 2025-06-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1544.6 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-07 | 2025-05-22 | 46 | 34 | 2025-05-22 | 2025-06-12 | 22 | 16 | 2025-06-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-05 | 2024-11-05 | 2025-03-18 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1682 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-05 | 2024-11-06 | 2 | 2 | 2024-11-06 | 2025-01-22 | 78 | 56 | 2025-01-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-28 | 2025-03-18 | 50 | 36 | Unknown | Unknown | Unknown | Unknown | 2025-03-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-02-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-08 | 2023-06-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 539.12 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-08 | 2023-06-13 | 6 | 4 | 2023-06-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-13 | Unknown | Unknown | Unknown | Unknown | 2025-06-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-01 | 2024-05-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7681 | 584.27 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-01 | 2024-02-14 | Unknown | Unknown | 2024-02-14 | 2024-05-01 | 78 | 56 | 2024-05-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-01 | 2025-07-24 | 450 | 322 | Unknown | Unknown | Unknown | Unknown | 2025-07-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | N/A | 130.05 | 130.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-11 | 2024-02-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7962 | 611.68 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-11 | 2024-01-10 | Unknown | Unknown | 2024-01-10 | 2024-03-08 | 59 | 43 | Unknown | Unknown | Unknown | Unknown | 2025-07-18 | 2025-07-18 | 1 | 1 | 2024-03-08 | Unknown | Unknown | Unknown | Unknown | 2025-08-20 | Unknown | Unknown | 2025-09-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 10006.75 | 10006.75 | Not Available | >2MW | No | N/A | N/A | N/A | 2027-05-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-29 | 2025-06-03 | 2025-06-23 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1106.23 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-29 | 2025-05-22 | Unknown | Unknown | 2025-05-22 | 2025-06-03 | 13 | 9 | 2025-06-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-03 | 2025-06-23 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | 2025-06-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | N/A | POWAY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-06 | 2023-06-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1026.09 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-06 | 2023-06-06 | 1 | 1 | 2023-06-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-27 | 2023-11-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 4445.69 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-27 | 2023-10-18 | 22 | 16 | 2023-10-18 | 2024-02-09 | 115 | 83 | Unknown | Unknown | Unknown | Unknown | 2024-08-06 | 2024-08-06 | 1 | 1 | 2024-02-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Residential | N/A | EN 1167-E3 (E) | ENCINITAS | 95 | 95 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-05 | 2024-12-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3097.91 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-05 | 2025-02-28 | 86 | 62 | 2025-02-28 | 2025-06-09 | 102 | 72 | 2025-02-12 | 2025-03-27 | 21 | 15 | 2025-03-19 | 2025-04-11 | 24 | 18 | 2025-06-24 | Unknown | Unknown | Unknown | 2025-06-24 | 2025-08-19 | 57 | 41 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 3.35 | 3.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-05 | 2025-05-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 250.9 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-05 | 2025-05-08 | 4 | 4 | 2025-05-08 | 2025-05-08 | 1 | 1 | 2025-05-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-08 | 2025-07-18 | 72 | 52 | Unknown | Unknown | Unknown | Unknown | 2025-07-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-12-09 | Unknown | Unknown | No | 2022-01-24 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-01-24 | 2022-01-24 | Unknown | IOU Designed & Installed | N/A | Yes | 819 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 158.37 | Unknown | Unknown | Yes | N/A | N/A | 2022-01-24 | 2024-04-22 | 820 | 586 | 2024-04-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2022-02-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-18 | 2024-09-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 9150 | 511.86 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-18 | 2024-09-18 | 1 | 1 | 2024-09-18 | 2024-09-18 | 1 | 1 | 2024-09-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-18 | 2025-09-05 | 353 | 253 | Unknown | Unknown | Unknown | Unknown | 2025-09-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-03 | 2024-06-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 27449 | 677.82 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-03 | 2024-06-04 | 2 | 2 | 2024-06-04 | 2024-06-04 | 1 | 1 | 2024-06-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 47.05 | 47.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-17 | 2023-11-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 842.62 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-17 | 2023-11-17 | 1 | 1 | 2023-11-17 | 2023-11-17 | 1 | 1 | 2023-11-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | RANCHO MISSION VIEJO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-13 | 2025-05-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 421.18 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-13 | 2025-05-07 | Unknown | Unknown | 2025-05-07 | 2025-06-16 | 41 | 29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-23 | 2024-10-23 | 2024-11-14 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1529.38 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-23 | 2024-10-23 | 1 | 1 | 2024-10-23 | 2024-10-23 | 1 | 1 | 2024-10-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-23 | 2024-11-14 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | 2024-11-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 39.05 | 39.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-13 | 2025-02-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1402.05 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-13 | 2025-02-25 | 13 | 9 | 2025-02-25 | 2025-02-28 | 4 | 4 | 2025-02-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-14 | 2024-05-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 111376.63 | 6109.61 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-14 | 2024-05-15 | 2 | 2 | 2024-05-15 | 2024-07-10 | 57 | 41 | Unknown | Unknown | Unknown | Unknown | 2024-07-11 | 2024-08-13 | 34 | 24 | 2024-07-10 | 2025-08-19 | 406 | 290 | Unknown | 2025-08-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-24 | 2024-09-24 | 2024-11-27 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1718.95 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-24 | 2024-09-18 | Unknown | Unknown | 2024-09-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-25 | 2024-11-27 | 64 | 46 | Unknown | Unknown | Unknown | Unknown | 2024-11-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LA JOLLA | SAN DIEGO | 16 | 16 | Not Available | <1MW | No | N/A | N/A | N/A | 2021-06-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-03 | 2024-10-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1083.48 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-03 | 2024-09-09 | Unknown | Unknown | 2024-09-09 | 2024-11-06 | 59 | 43 | Unknown | Unknown | Unknown | Unknown | 2024-10-08 | 2024-11-07 | 31 | 23 | 2024-11-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 13.1 | 13.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-10 | 2024-12-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 750.35 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-10 | 2024-12-13 | 4 | 4 | 2024-12-13 | 2025-02-19 | 69 | 49 | 2025-02-19 | 2025-02-21 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2025-02-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-11-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-16 | 2024-12-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 655.53 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-16 | 2024-12-03 | 79 | 57 | 2024-12-03 | 2025-07-02 | 212 | 152 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-07-02 | 2025-04-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-10 | 2023-07-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 4606 | 559.06 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-10 | 2023-10-04 | 87 | 63 | 2023-10-04 | 2023-10-04 | 1 | 1 | 2023-10-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN MARCOS | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-12 | 2024-07-31 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1488.73 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-12 | 2024-05-16 | Unknown | Unknown | 2024-05-16 | 2024-07-31 | 77 | 55 | 2024-07-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 75 | 75 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-26 | 2025-02-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1243.05 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-26 | 2025-04-04 | 38 | 28 | 2025-04-04 | 2025-04-04 | 1 | 1 | 2025-04-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-13 | 2024-08-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1356.14 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-13 | 2024-07-29 | Unknown | Unknown | 2024-07-29 | 2024-08-23 | 26 | 20 | 2024-08-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | 37 | 37 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-08 | 2025-05-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 78.51 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-08 | 2025-05-02 | Unknown | Unknown | 2025-05-02 | 2025-05-08 | 7 | 5 | 2025-05-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | LAGUNA HILLS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-22 | 2024-08-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2408.7 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-22 | 2024-09-04 | 14 | 10 | 2024-09-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | CORONADO | N/A | 48.1 | 48.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-11 | 2024-12-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1032.15 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-11 | 2024-12-11 | 1 | 1 | 2024-12-11 | 2024-12-11 | 1 | 1 | 2024-12-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-13 | 2025-07-11 | 211 | 151 | Unknown | Unknown | Unknown | Unknown | 2025-07-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 31.05 | 31.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-03 | 2023-04-03 | 2023-09-18 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 671.18 | Unknown | Unknown | Yes | N/A | N/A | 2023-04-03 | 2023-04-17 | 15 | 11 | 2023-04-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-05 | 2023-09-18 | 106 | 76 | Unknown | 2023-09-07 | Unknown | Unknown | 2023-09-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SANTEE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-14 | 2025-02-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1653.36 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-14 | 2025-02-14 | 1 | 1 | 2025-02-14 | 2025-02-14 | 1 | 1 | 2025-02-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-14 | 2025-07-10 | 147 | 105 | Unknown | Unknown | Unknown | Unknown | 2025-07-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | CARLSBAD | N/A | 55 | 55 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-02 | 2024-02-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 532.49 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-02 | 2024-01-29 | Unknown | Unknown | 2024-01-29 | 2024-02-05 | 8 | 6 | 2024-02-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-05 | 2025-07-08 | 520 | 372 | Unknown | Unknown | Unknown | Unknown | 2025-07-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-04 | 2025-06-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 826.94 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-04 | 2025-06-04 | 1 | 1 | 2025-06-04 | 2025-06-04 | 1 | 1 | 2025-06-04 | 2025-06-13 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | 2025-06-13 | 2025-08-05 | 54 | 38 | Unknown | 2025-08-04 | Unknown | Unknown | 2025-08-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 5.4 | 5.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-02 | 2024-05-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1666.28 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-02 | 2024-03-19 | Unknown | Unknown | 2024-03-19 | 2024-05-02 | 45 | 33 | 2024-05-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | OH | IOU Design | Commercial | Underserved Community | SAN MARCOS | COUNTY OF SAN DIEGO-NORTH of 56 | 264.2 | 264.2 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-20 | 2024-04-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 111147 | 35873.46 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-20 | 2024-03-20 | 1 | 1 | 2024-03-20 | 2024-10-17 | 212 | 152 | 2024-10-01 | 2024-10-15 | 15 | 11 | 2024-10-19 | 2024-10-25 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-04 | 2025-06-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 797.1 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-04 | 2025-07-15 | 42 | 30 | 2025-07-15 | 2025-07-25 | 11 | 9 | 2025-06-13 | 2025-06-24 | 12 | 8 | Unknown | Unknown | Unknown | Unknown | 2025-06-24 | 2025-07-28 | 35 | 25 | Unknown | Unknown | Unknown | Unknown | 2025-07-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-18 | 2024-10-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 9150 | 525.39 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-18 | 2024-10-18 | 1 | 1 | 2024-10-18 | 2024-10-18 | 1 | 1 | 2024-10-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SANTEE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-25 | 2025-04-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2394.48 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-25 | 2025-03-11 | Unknown | Unknown | 2025-03-11 | 2025-04-09 | 30 | 22 | 2025-04-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 96.05 | 96.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-29 | 2024-03-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 861.06 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-29 | 2024-03-29 | 61 | 45 | 2024-03-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 46 | 46 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-17 | 2023-06-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 889.43 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-17 | 2023-06-17 | 1 | 0 | 2023-06-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2024-08-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-04 | 2024-10-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1910.28 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-04 | 2024-10-04 | 1 | 1 | 2024-10-04 | 2025-03-31 | 179 | 127 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-31 | 2025-09-02 | 156 | 112 | Unknown | 2025-09-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-01 | 2024-07-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1049.43 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-01 | 2024-05-09 | Unknown | Unknown | 2024-05-09 | 2024-07-08 | 61 | 43 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN CLEMENTE | N/A | 107.05 | 107.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-22 | Unknown | Unknown | No | 2025-04-07 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | 2025-04-07 | Unknown | IOU Designed & Installed | N/A | Yes | 59 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1550.4 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-07 | 2025-06-05 | 60 | 44 | 2025-06-05 | 2025-06-05 | 1 | 1 | 2025-06-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-17 | 2023-02-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2515.62 | Unknown | Unknown | Yes | N/A | N/A | 2023-02-17 | 2023-02-22 | 6 | 4 | 2023-02-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | Underserved Community | SM 1129-E1 (E) | SAN MARCOS | 123.75 | 123.75 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-12 | 2022-12-12 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 19679.12 | Unknown | Unknown | Yes | N/A | N/A | 2022-12-12 | 2023-03-20 | 99 | 71 | 2023-03-20 | 2025-01-13 | 666 | 476 | 2023-04-05 | 2025-01-21 | 463 | 329 | 2023-03-01 | 2025-08-25 | 348 | 248 | 2025-03-24 | Unknown | Unknown | Unknown | 2025-03-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-29 | 2024-02-29 | 2024-03-07 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 163.83 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-29 | 2024-02-29 | 1 | 1 | 2024-02-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN MARCOS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-24 | Unknown | Unknown | No | 2024-09-03 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-03 | 2024-09-03 | Unknown | IOU Designed & Installed | N/A | Yes | 261 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1246.62 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-03 | 2025-05-22 | 262 | 188 | 2025-05-22 | 2025-05-22 | 1 | 1 | 2025-05-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-29 | 2024-04-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1215.3 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-29 | 2024-03-13 | Unknown | Unknown | 2024-03-13 | 2024-05-03 | 52 | 38 | 2024-05-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-21 | 2024-02-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2863 | 1424.99 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-21 | 2024-02-21 | 1 | 1 | 2024-02-21 | 2024-03-08 | 17 | 13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-22 | 2024-12-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1235.74 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-22 | 2024-12-05 | 14 | 10 | 2024-12-05 | 2024-12-27 | 23 | 17 | 2024-12-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 36.05 | 36.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-06 | 2025-05-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1104.56 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-06 | 2025-05-20 | 15 | 11 | 2025-05-20 | 2025-06-12 | 24 | 18 | 2025-06-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-12 | 2025-08-27 | 77 | 55 | Unknown | 2025-07-15 | Unknown | Unknown | 2025-08-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SANTEE | N/A | 68 | 68 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-28 | 2025-03-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1297.75 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-28 | 2025-02-28 | 1 | 1 | 2025-02-28 | 2025-03-06 | 7 | 5 | 2025-03-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-07 | 2025-05-20 | 2025-06-30 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1727.42 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-07 | 2025-04-25 | Unknown | Unknown | 2025-04-25 | 2025-05-20 | 26 | 18 | 2025-05-20 | Unknown | Unknown | Unknown | 2025-05-20 | 2025-06-11 | 23 | 17 | 2025-05-20 | 2025-06-30 | 42 | 30 | Unknown | Unknown | Unknown | Unknown | 2025-06-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-07-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-21 | 2023-09-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 97330 | 11044.01 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-21 | 2023-09-19 | Unknown | Unknown | 2023-09-19 | 2023-10-16 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | FALLBROOK | N/A | 12 | 12 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-24 | 2024-11-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 4198.69 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-24 | 2024-09-27 | 127 | 91 | 2024-09-27 | 2024-12-09 | 74 | 52 | Unknown | Unknown | Unknown | Unknown | 2025-01-16 | 2025-01-16 | 1 | 1 | 2024-12-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SOUTH LAGUNA | LAGUNA BEACH | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-31 | 2024-07-31 | 2025-01-11 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-31 | 2024-10-14 | 76 | 54 | 2024-10-14 | 2024-12-12 | 60 | 44 | 2024-12-12 | Unknown | Unknown | Unknown | 2024-09-09 | 2024-09-12 | 4 | 4 | 2024-12-12 | 2025-01-11 | 31 | 22 | Unknown | Unknown | Unknown | Unknown | 2025-01-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-12 | 2023-12-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 937.81 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-12 | 2023-12-12 | 1 | 1 | 2023-12-12 | 2023-12-12 | 1 | 1 | 2023-12-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-02-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-06 | 2024-03-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 15764 | 682.88 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-06 | 2023-06-27 | Unknown | Unknown | 2023-06-27 | 2024-03-29 | 277 | 199 | 2024-03-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-24 | 2024-10-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2318.55 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-24 | 2024-10-24 | 1 | 1 | 2024-10-24 | 2024-12-10 | 48 | 34 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | Both | Applicant Design | Commercial | Underserved Community | San Diego | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-27 | 2023-12-27 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2190 | 26638.39 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-27 | 2024-06-26 | 183 | 131 | 2024-06-26 | 2024-11-27 | 155 | 111 | 2024-07-08 | 2024-11-20 | 131 | 95 | 2024-11-22 | 2025-01-03 | 42 | 29 | 2025-03-07 | Unknown | Unknown | Unknown | 2025-03-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 94.36 | 94.36 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-20 | 2025-02-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1225.94 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-20 | 2025-02-20 | 1 | 1 | 2025-02-20 | 2025-03-05 | 14 | 10 | 2025-03-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-05 | 2025-08-25 | 174 | 124 | Unknown | 2025-08-15 | Unknown | Unknown | 2025-08-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 10400 | 10400 | Not Available | >2MW | No | N/A | N/A | N/A | 2025-06-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-01 | 2023-12-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 959.58 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-01 | 2023-12-01 | 1 | 1 | 2023-12-01 | 2023-12-01 | 1 | 1 | 2023-12-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-23 | 2024-07-24 | 2024-07-31 | IOU Designed & Installed | N/A | No | Unknown | 4215.88 | 1204.35 | Unknown | 113.91 | 162.51 | 2735.11 | 0 | 1165.49 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-23 | 2024-07-23 | 1 | 1 | 2024-07-23 | 2024-07-24 | 2 | 2 | 2024-07-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-24 | 2024-07-31 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2024-07-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 21 | 21 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-27 | 2023-12-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1109.09 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-27 | 2024-03-18 | 83 | 59 | 2024-03-18 | 2024-03-18 | 1 | 1 | 2024-03-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-18 | Unknown | Unknown | Unknown | Unknown | 2025-03-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 3 | 3 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-19 | 2023-09-29 | 2023-10-03 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 500.87 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-19 | 2023-06-23 | Unknown | Unknown | 2023-06-23 | 2023-09-29 | 99 | 71 | 2023-09-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-29 | 2023-10-03 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | 2023-10-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | Spring Valley | COUNTY OF SAN DIEGO-SOUTH of 56 | 232 | 232 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-01 | 2024-08-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 185570.67 | 16847.68 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-01 | 2024-02-01 | 1 | 1 | 2024-02-01 | 2024-09-16 | 229 | 163 | Unknown | Unknown | Unknown | Unknown | 2024-08-27 | 2024-10-03 | 35 | 25 | 2024-09-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-27 | 2023-12-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 298.57 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-27 | 2024-03-01 | 66 | 48 | 2024-03-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | BONITA | N/A | 175 | 175 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-11 | 2024-12-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1476.93 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-11 | 2025-01-21 | 42 | 30 | 2025-01-21 | 2025-02-19 | 30 | 22 | 2025-02-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-08 | 2024-05-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 288418.6 | 16066.62 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-08 | 2024-05-17 | 192 | 138 | 2024-05-17 | 2024-05-29 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-06 | 2023-07-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 688.88 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-06 | 2023-07-20 | 15 | 11 | 2023-07-20 | 2023-07-20 | 1 | 1 | 2023-07-20 | 2023-07-25 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2023-07-25 | Unknown | Unknown | Unknown | Unknown | 2023-08-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 95.05 | 95.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-21 | 2024-02-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 517.29 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-21 | 2024-02-21 | 1 | 1 | 2024-02-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | OH | IOU Design | Residential | Underserved Community | Fallbrook | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-27 | 2024-12-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 9173.47 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-27 | 2024-09-23 | Unknown | Unknown | 2024-09-23 | 2025-01-27 | 127 | 91 | Unknown | Unknown | Unknown | Unknown | 2025-01-13 | 2025-01-16 | 4 | 4 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | NATIONAL CITY | NATIONAL CITY | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-31 | 2025-03-31 | 2025-06-25 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1780.12 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-31 | 2025-03-31 | 1 | 1 | 2025-03-31 | 2025-03-31 | 1 | 1 | 2025-03-31 | Unknown | Unknown | Unknown | 2025-04-01 | 2025-06-24 | 85 | 61 | 2025-03-31 | 2025-06-25 | 87 | 63 | Unknown | Unknown | Unknown | Unknown | 2025-06-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 53.05 | 53.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-27 | 2024-12-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 587.95 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-27 | 2024-12-27 | 1 | 1 | 2024-12-27 | 2024-12-27 | 1 | 1 | 2024-12-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN MARCOS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-27 | 2025-03-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 1192.8 | 709.01 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-27 | 2025-03-27 | 1 | 1 | 2025-03-27 | 2025-04-28 | 33 | 23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | RANCHO LA COSTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-26 | 2025-02-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 875.02 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-26 | 2025-05-22 | 86 | 62 | 2025-05-22 | 2025-05-22 | 1 | 1 | 2025-03-07 | 2025-04-10 | 35 | 25 | Unknown | Unknown | Unknown | Unknown | 2025-05-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2026-03-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-06 | 2024-06-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 72776 | 71.74 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-06 | 2025-05-07 | 367 | 263 | 2025-05-07 | 2025-06-12 | 37 | 27 | Unknown | Unknown | Unknown | Unknown | 2024-05-20 | 2024-10-21 | 62 | 45 | 2025-06-12 | Unknown | Unknown | Unknown | Unknown | 2025-07-31 | Unknown | Unknown | 2025-08-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-06 | 2023-11-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 280609 | 82129.99 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-06 | 2023-11-04 | Unknown | Unknown | 2023-11-04 | 2023-12-08 | 35 | 25 | 2023-11-08 | 2023-12-07 | 7 | 5 | 2023-12-08 | 2023-12-13 | 6 | 4 | 2023-12-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-10 | 2025-03-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 36349.88 | 2056.67 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-10 | 2025-05-08 | 60 | 44 | 2025-05-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-26 | 2025-06-13 | 19 | 15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN JUAN CAPISTRANO | N/A | 14 | 14 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-12 | 2024-08-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2662.25 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-12 | 2024-10-09 | 59 | 43 | 2024-10-09 | 2024-10-22 | 14 | 10 | 2024-10-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | Both | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-10 | 2024-12-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 37616 | 6351.28 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-10 | 2024-12-19 | 10 | 8 | 2024-12-19 | 2025-05-07 | 140 | 100 | Unknown | Unknown | Unknown | Unknown | 2025-01-09 | 2025-01-28 | 20 | 14 | 2025-05-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-18 | 2025-06-18 | 2025-06-19 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1067.09 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-18 | 2025-06-18 | 1 | 1 | 2025-06-18 | 2025-06-18 | 1 | 1 | 2025-06-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-18 | 2025-06-19 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2025-06-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | N/A | 16.4 | 16.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-12 | 2025-05-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1117.54 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-12 | 2025-06-06 | 26 | 20 | 2025-06-06 | 2025-06-06 | 1 | 1 | 2025-06-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-15 | 2024-07-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3752.96 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-15 | 2024-07-19 | 5 | 5 | 2024-07-19 | 2024-08-29 | 42 | 30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-14 | 2025-05-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1037.65 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-14 | 2025-05-05 | Unknown | Unknown | 2025-05-05 | 2025-05-14 | 10 | 8 | 2025-05-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | N/A | 75 | 75 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-09 | 2024-10-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2655.75 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-09 | 2024-07-09 | 1 | 1 | 2024-07-09 | 2024-10-17 | 101 | 73 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 104.05 | 104.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-13 | 2025-04-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1345.28 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-13 | 2025-05-08 | 26 | 19 | 2025-05-08 | 2025-06-06 | 30 | 22 | 2025-06-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-09 | 2025-01-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 13907.45 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-09 | 2025-01-09 | 1 | 1 | 2025-01-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | NATIONAL CITY | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-28 | 2025-05-01 | 2025-06-05 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1384.46 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-28 | 2025-05-01 | 4 | 4 | 2025-05-01 | 2025-05-01 | 1 | 1 | 2025-04-29 | 2025-05-30 | 32 | 24 | Unknown | Unknown | Unknown | Unknown | 2025-05-30 | 2025-06-05 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2025-06-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | National City | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-07 | 2024-05-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 4202.98 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-07 | 2024-06-05 | 30 | 22 | 2024-06-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | OCEANSIDE | N/A | 1991.05 | 1991.05 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2026-09-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-23 | 2025-03-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1103.57 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-23 | 2025-04-10 | 170 | 122 | 2025-04-10 | 2025-04-14 | 5 | 3 | 2025-04-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 62 | 62 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-18 | 2025-06-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1164.99 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-18 | 2025-02-19 | Unknown | Unknown | 2025-02-19 | 2025-06-18 | 120 | 86 | 2025-06-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | VISTA | 18.75 | 18.75 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-04 | 2024-11-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1754.39 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-04 | 2024-10-18 | Unknown | Unknown | 2024-10-18 | 2024-11-12 | 26 | 18 | 2024-11-12 | Unknown | Unknown | Unknown | 2024-11-13 | 2024-11-21 | 9 | 7 | 2024-11-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | SAN DIEGO | 222214 | 222214 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-03-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-22 | 2025-01-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 499.95 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-22 | 2025-01-23 | 2 | 2 | 2025-01-23 | 2025-06-02 | 131 | 93 | 2025-02-27 | 2025-03-06 | 8 | 6 | 2025-02-21 | 2025-03-27 | 30 | 22 | 2025-06-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-06-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-31 | 2023-10-31 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 419.12 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-31 | 2023-12-12 | 43 | 31 | 2023-12-12 | 2024-02-08 | 59 | 43 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-01 | 2025-05-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1177.12 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-01 | 2025-05-14 | 14 | 10 | 2025-05-14 | 2025-05-27 | 14 | 10 | 2025-05-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-27 | 2025-07-28 | 63 | 45 | Unknown | Unknown | Unknown | Unknown | 2025-07-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | JAMUL | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-03 | 2025-04-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1137.82 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-03 | 2025-05-22 | 50 | 36 | 2025-05-22 | 2025-05-27 | 6 | 4 | 2025-05-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-16 | 2025-06-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1595.58 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-16 | 2025-06-16 | 1 | 1 | 2025-06-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-07-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-24 | 2025-03-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2163.61 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-24 | 2025-03-24 | 1 | 1 | 2025-03-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-02 | 2025-08-20 | 80 | 58 | Unknown | Unknown | Unknown | Unknown | 2025-08-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | OH | IOU Design | Residential | Underserved Community | Escondido | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-01-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-28 | 2023-04-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3799.55 | Unknown | Unknown | Yes | N/A | N/A | 2023-04-28 | 2023-04-28 | 1 | 1 | 2023-04-28 | 2024-02-05 | 284 | 202 | 2024-01-30 | 2024-01-30 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | N/A | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-08-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-08 | 2024-08-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 9041.57 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-08 | 2024-08-02 | Unknown | Unknown | 2024-08-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | CHULA VISTA | CHULA VISTA | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2025-04-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-30 | 2024-05-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 468.05 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-30 | 2024-05-02 | 3 | 3 | 2024-05-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-30 | 2024-07-11 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | OCEANSIDE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-16 | 2024-01-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1754.85 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-16 | 2024-01-20 | 5 | 4 | 2024-01-20 | 2024-01-20 | 1 | 0 | 2024-01-20 | Unknown | Unknown | Unknown | 2024-01-20 | 2024-02-07 | 19 | 13 | 2024-01-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-09 | 2023-11-06 | 2023-11-09 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 513.31 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-09 | 2023-10-31 | 23 | 17 | 2023-10-31 | 2023-10-31 | 1 | 1 | 2023-10-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-06 | 2023-11-09 | 4 | 4 | Unknown | Unknown | Unknown | Unknown | 2023-11-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-03 | 2024-04-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 758640 | 42613.18 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-03 | 2024-03-27 | Unknown | Unknown | 2024-03-27 | 2024-07-08 | 104 | 74 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-27 | 2025-05-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2390.43 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-27 | 2025-05-01 | Unknown | Unknown | 2025-05-01 | 2025-05-30 | 30 | 22 | 2025-05-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-30 | 2025-07-25 | 57 | 41 | Unknown | 2025-07-18 | Unknown | Unknown | 2025-07-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | FALLBROOK | COUNTY OF SAN DIEGO-NORTH of 56 | 196 | 196 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-01 | 2023-12-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 15576.19 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-01 | 2023-11-29 | Unknown | Unknown | 2023-11-29 | 2025-04-17 | 506 | 362 | 2024-02-14 | 2025-03-27 | 98 | 68 | 2025-01-14 | 2025-06-09 | 40 | 28 | 2025-04-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | 98 | 98 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-23 | 2025-05-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 737.56 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-23 | 2025-05-22 | Unknown | Unknown | 2025-05-22 | 2025-05-22 | 1 | 1 | 2025-05-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 92.05 | 92.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-06 | 2025-06-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1247.57 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-06 | 2025-06-09 | 4 | 2 | 2025-06-09 | 2025-06-24 | 16 | 12 | 2025-06-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-24 | 2025-08-19 | 57 | 41 | Unknown | Unknown | Unknown | Unknown | 2025-08-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Disadvantaged Community,Underserved Community,Tribal Community | PAUMA VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-26 | 2024-03-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1879.19 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-26 | 2024-04-24 | 59 | 43 | 2024-04-24 | 2025-05-13 | 385 | 275 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | DANA POINT | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-25 | 2024-07-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2875.23 | 780.27 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-25 | 2024-07-24 | 30 | 22 | 2024-07-24 | 2025-01-08 | 169 | 121 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2020-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-20 | 2023-04-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 558.3 | Unknown | Unknown | Yes | N/A | N/A | 2023-04-20 | 2023-04-20 | 1 | 1 | 2023-04-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-01-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-27 | 2024-03-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 635.36 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-27 | 2024-03-19 | Unknown | Unknown | 2024-03-19 | 2024-10-03 | 199 | 143 | Unknown | Unknown | Unknown | Unknown | 2025-06-30 | 2025-06-30 | 1 | 1 | 2024-10-03 | Unknown | Unknown | Unknown | Unknown | 2025-07-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R29/R45 | UG | IOU Design | Commercial | Underserved Community | VISTA | VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-03 | 2024-05-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 64257.84 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-03 | 2024-06-21 | 50 | 36 | 2024-06-21 | 2025-06-20 | 365 | 261 | 2024-08-06 | 2025-06-10 | 44 | 32 | 2024-11-01 | 2025-04-18 | 47 | 33 | 2025-06-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN MARCOS | N/A | 40 | 40 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-22 | 2025-04-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 624.58 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-22 | 2025-05-14 | 23 | 17 | 2025-05-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SANTEE | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-30 | 2024-05-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1522.47 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-30 | 2024-04-10 | Unknown | Unknown | 2024-04-10 | 2024-05-30 | 51 | 37 | 2024-05-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-21 | 2024-10-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 694049 | 41712.45 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-21 | 2024-10-21 | 1 | 1 | 2024-10-21 | 2025-02-19 | 122 | 88 | Unknown | Unknown | Unknown | Unknown | 2024-10-25 | 2024-12-04 | 41 | 29 | 2025-02-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 44.4 | 44.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-03 | 2025-06-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 807.6 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-03 | 2025-05-16 | Unknown | Unknown | 2025-05-16 | 2025-06-05 | 21 | 15 | 2025-06-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | CHULA VISTA | N/A | 2.7 | 2.7 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-18 | 2025-04-18 | 2025-06-11 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1700.33 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-18 | 2025-03-28 | Unknown | Unknown | 2025-03-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-18 | 2025-06-11 | 55 | 39 | Unknown | Unknown | Unknown | Unknown | 2025-06-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | N/A | Rancho Mission Viejo | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-19 | 2023-12-19 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 288101.88 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-19 | 2024-04-08 | 112 | 80 | 2024-04-08 | 2025-02-06 | 305 | 219 | 2024-07-11 | 2025-04-29 | 125 | 89 | 2024-09-18 | 2025-02-07 | 141 | 100 | 2025-06-25 | Unknown | Unknown | Unknown | 2025-06-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-04-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-13 | 2023-02-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 38523.51 | 2429.15 | Unknown | Unknown | Yes | N/A | N/A | 2023-02-13 | 2023-12-19 | 310 | 222 | 2023-12-19 | 2025-04-02 | 471 | 337 | Unknown | Unknown | Unknown | Unknown | 2024-07-03 | 2024-08-05 | 34 | 24 | 2025-04-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 5.4 | 5.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-28 | 2024-10-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1552.93 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-28 | 2024-10-11 | Unknown | Unknown | 2024-10-11 | 2024-10-30 | 20 | 14 | 2024-10-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 62.05 | 62.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-24 | Unknown | Unknown | No | 2024-03-18 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-18 | 2024-03-21 | 2025-04-30 | IOU Designed & Installed | N/A | Yes | 443 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1403.99 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-18 | 2025-06-04 | 444 | 318 | 2025-06-04 | 2024-03-21 | Unknown | Unknown | 2024-03-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-21 | 2025-04-30 | 406 | 290 | Unknown | Unknown | Unknown | Unknown | 2025-04-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | OH | IOU Design | Commercial | N/A | Encinitas | CALTRANS-NORTH of 56, ENCINITAS | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-06-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-30 | 2023-07-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 4876.41 | Unknown | Unknown | Yes | N/A | N/A | 2022-11-30 | 2023-03-14 | 105 | 75 | 2023-03-14 | 2025-09-08 | 910 | 650 | 2023-10-06 | 2023-12-21 | 77 | 55 | 2023-09-14 | 2025-09-08 | 131 | 89 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-04 | 2025-04-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 904.72 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-04 | 2024-10-29 | Unknown | Unknown | 2024-10-29 | 2025-05-23 | 207 | 149 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-23 | 2025-05-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-27 | 2025-02-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 515.36 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-27 | 2025-02-27 | 1 | 1 | 2025-02-27 | 2025-03-10 | 12 | 8 | 2025-03-10 | Unknown | Unknown | Unknown | 2025-03-07 | 2025-03-28 | 22 | 16 | 2025-03-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-06 | 2024-06-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 40716.6 | 30678.35 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-06 | 2024-06-07 | 2 | 2 | 2024-06-07 | 2024-06-21 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-21 | 2958465 | Unknown | Unknown | Unknown | 2025-07-31 | Unknown | Unknown | 2025-08-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | 74.05 | 74.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-03 | 2024-07-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 192.51 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-03 | 2024-06-25 | Unknown | Unknown | 2024-06-25 | 2024-07-09 | 15 | 11 | 2024-07-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-24 | 2024-06-24 | 2024-07-03 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1491.84 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-24 | 2024-06-24 | 1 | 1 | 2024-06-24 | 2024-06-24 | 1 | 1 | 2024-06-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-24 | 2024-07-03 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | 2024-07-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-15 | 2024-04-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7681 | 589.24 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-15 | 2024-02-15 | Unknown | Unknown | 2024-02-15 | 2024-04-18 | 64 | 46 | 2024-04-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-18 | 2025-08-08 | 478 | 342 | Unknown | Unknown | Unknown | Unknown | 2025-08-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 1.35 | 1.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-06 | 2024-12-23 | 2025-01-24 | IOU Designed & Installed | N/A | No | Unknown | 81.05 | 0 | Unknown | Unknown | 27.01 | 54.04 | 3981 | 1569.77 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-06 | 2024-11-21 | Unknown | Unknown | 2024-11-21 | 2024-12-23 | 33 | 23 | 2024-12-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-23 | 2025-01-24 | 33 | 25 | Unknown | Unknown | Unknown | Unknown | 2025-01-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | 156 | 156 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-21 | 2023-11-21 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 13522.95 | 58733.7 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-21 | 2024-01-25 | 66 | 48 | 2024-01-25 | 2024-05-29 | 126 | 90 | 2024-02-15 | 2024-05-24 | 59 | 43 | 2024-02-27 | 2024-06-04 | 32 | 24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-08 | 2025-05-09 | 2025-05-21 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1176.64 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-08 | 2025-05-08 | 1 | 1 | 2025-05-08 | 2025-05-08 | 1 | 1 | 2025-05-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-09 | 2025-05-21 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2025-05-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 68.05 | 68.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-13 | Unknown | Unknown | No | 2023-02-28 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-28 | 2023-02-28 | Unknown | IOU Designed & Installed | N/A | Yes | 412 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 943.29 | Unknown | Unknown | Yes | N/A | N/A | 2023-02-28 | 2024-04-15 | 413 | 295 | 2024-04-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-21 | 2025-09-09 | 782 | 558 | Unknown | 2025-03-18 | Unknown | Unknown | 2025-09-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-27 | 2024-10-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 11943 | 1478.66 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-27 | 2024-10-10 | 14 | 10 | 2024-10-10 | 2024-12-18 | 70 | 50 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-25 | 2025-04-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1096.32 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-25 | 2025-04-25 | 1 | 1 | 2025-04-25 | 2025-04-25 | 1 | 1 | 2025-04-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SANTEE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-03 | 2024-09-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1465.07 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-03 | 2024-08-21 | Unknown | Unknown | 2024-08-21 | 2024-09-03 | 14 | 10 | 2024-09-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 68.05 | 68.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-17 | 2023-05-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7962 | 456.03 | Unknown | Unknown | Yes | N/A | N/A | 2023-01-17 | 2023-02-06 | 21 | 15 | 2023-02-06 | 2023-05-31 | 115 | 83 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | ESCONDIDO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2024-09-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-05 | 2025-02-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3753.77 | 3098.32 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-05 | 2025-04-16 | 71 | 51 | 2025-04-16 | 2025-05-06 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | 2025-04-03 | 2025-04-11 | 9 | 7 | 2025-05-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-03 | 2024-11-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1161.26 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-03 | 2024-11-26 | 55 | 39 | 2024-11-26 | 2025-03-18 | 113 | 81 | Unknown | Unknown | Unknown | Unknown | 2024-12-16 | 2025-01-17 | 33 | 25 | 2025-03-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-10 | 2022-10-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 153.87 | Unknown | Unknown | Yes | N/A | N/A | 2022-10-10 | 2023-07-22 | 286 | 205 | 2023-07-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-23 | 2025-05-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7962 | 1079.15 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-23 | 2025-03-14 | Unknown | Unknown | 2025-03-14 | 2025-05-27 | 75 | 53 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-27 | 2025-07-30 | 65 | 47 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN JUAN CAPISTRANO | N/A | 5 | 5 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-06 | 2024-03-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 911.3 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-06 | 2024-03-18 | 13 | 9 | 2024-03-18 | 2024-03-21 | 4 | 4 | 2024-03-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-21 | Unknown | Unknown | Unknown | Unknown | 2024-04-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-23 | 2024-10-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3241 | 507.87 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-23 | 2024-10-24 | 2 | 2 | 2024-10-24 | 2024-10-24 | 1 | 1 | 2024-10-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | POWAY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-23 | 2024-09-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3158.2 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-23 | 2024-09-19 | Unknown | Unknown | 2024-09-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-19 | 2023-05-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 8997 | 554.66 | Unknown | Unknown | Yes | N/A | N/A | 2023-05-19 | 2023-05-19 | 1 | 1 | 2023-05-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | JAMUL | N/A | 67.05 | 67.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-11 | 2025-04-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2742.22 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-11 | 2025-03-31 | Unknown | Unknown | 2025-03-31 | 2025-04-11 | 12 | 10 | 2025-04-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-16 | 2024-09-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 19905 | 683.68 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-16 | 2024-09-19 | 66 | 48 | 2024-09-19 | 2025-01-03 | 107 | 77 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-03 | 2025-08-26 | 236 | 168 | Unknown | 2025-09-02 | Unknown | Unknown | 2025-09-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | OH | Applicant Design | Residential | Underserved Community | San Diego | San Diego | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-10 | 2024-10-10 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 44841.28 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-10 | 2025-02-24 | 138 | 98 | 2025-02-24 | 2025-07-25 | 152 | 110 | 2025-02-28 | 2025-06-24 | 79 | 57 | 2025-01-06 | 2025-07-21 | 36 | 26 | 2025-07-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-08-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-20 | 2024-02-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 53981 | 569.59 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-20 | 2023-12-20 | Unknown | Unknown | 2023-12-20 | 2024-04-12 | 115 | 83 | 2024-04-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-23 | 2024-01-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 297.38 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-23 | 2023-12-04 | Unknown | Unknown | 2023-12-04 | 2024-01-23 | 51 | 37 | 2024-01-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | RAMONA | N/A | 46.05 | 46.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-23 | 2025-06-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 814.82 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-23 | 2025-06-23 | 1 | 1 | 2025-06-23 | 2025-06-23 | 1 | 1 | 2025-06-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-20 | 2025-03-20 | 2025-04-30 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2094.49 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-20 | 2025-03-19 | Unknown | Unknown | 2025-03-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 85 | 85 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-10 | 2024-06-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1466.56 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-10 | 2024-04-04 | Unknown | Unknown | 2024-04-04 | 2024-06-12 | 70 | 50 | 2024-06-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | BONITA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-17 | 2025-03-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 799.52 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-17 | 2025-05-29 | 74 | 54 | 2025-05-29 | 2025-06-03 | 6 | 4 | 2025-04-10 | 2025-06-03 | 55 | 39 | Unknown | Unknown | Unknown | Unknown | 2025-06-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | 40 | 40 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-13 | 2025-05-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1104.59 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-13 | 2025-04-18 | Unknown | Unknown | 2025-04-18 | 2025-05-15 | 28 | 20 | 2025-05-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 3.35 | 3.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-25 | 2025-05-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1547.51 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-25 | 2025-04-21 | Unknown | Unknown | 2025-04-21 | 2025-05-08 | 18 | 14 | 2025-05-08 | 2025-08-11 | 96 | 68 | Unknown | Unknown | Unknown | Unknown | 2025-05-08 | 2025-08-11 | 96 | 68 | Unknown | Unknown | Unknown | Unknown | 2025-08-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SM 1129-E1 Montiel MSO (E) | N/A | 123.75 | 123.75 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-27 | 2025-03-31 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 11943 | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2025-03-27 | 2025-03-17 | Unknown | Unknown | 2025-03-17 | 2025-04-04 | 19 | 15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | LAGUNA HILLS | N/A | 8 | 8 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-27 | 2024-06-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1041.4 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-27 | 2024-07-26 | 30 | 22 | 2024-07-26 | 2024-07-26 | 1 | 1 | 2024-07-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-18 | 2023-05-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 632.49 | Unknown | Unknown | Yes | N/A | N/A | 2023-05-18 | 2023-05-18 | 1 | 1 | 2023-05-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-22 | 2024-01-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 163.83 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-22 | 2024-02-11 | 21 | 15 | 2024-02-11 | 2024-02-14 | 4 | 3 | 2024-02-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | RAMONA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-04 | 2025-02-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 798.4 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-04 | 2025-02-28 | 25 | 19 | 2025-02-28 | 2025-03-25 | 26 | 18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | OCEANSIDE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-14 | 2025-03-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1716.03 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-14 | 2025-03-14 | 1 | 1 | 2025-03-14 | 2025-03-14 | 1 | 1 | 2025-03-14 | Unknown | Unknown | Unknown | 2025-03-14 | 2025-04-03 | 21 | 15 | 2025-03-14 | 2025-07-02 | 111 | 79 | Unknown | Unknown | Unknown | Unknown | 2025-07-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-04 | 2025-05-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1030.73 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-04 | 2024-10-24 | 21 | 15 | 2024-10-24 | 2025-05-23 | 212 | 152 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-04 | 2024-01-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2144.62 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-04 | 2023-12-26 | Unknown | Unknown | 2023-12-26 | 2024-01-04 | 10 | 8 | 2024-01-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community,Tribal Community | VALLEY CENTER | N/A | 97.05 | 97.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-17 | 2024-10-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1410.23 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-17 | 2024-10-18 | 2 | 2 | 2024-10-18 | 2025-05-15 | 210 | 150 | 2025-05-13 | 2025-05-13 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2025-05-15 | 2025-06-23 | 40 | 28 | Unknown | 2025-07-03 | Unknown | Unknown | 2025-08-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | N/A | 81.05 | 81.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-10 | 2024-09-10 | 2025-06-30 | IOU Designed & Installed | N/A | No | Unknown | 717.69 | 0 | Unknown | Unknown | 17.05 | 700.64 | 3981 | 2626.81 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-10 | 2024-10-14 | 35 | 25 | 2024-10-14 | 2024-10-21 | 8 | 6 | 2024-10-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-21 | 2025-06-30 | 253 | 181 | Unknown | 2025-06-12 | Unknown | Unknown | 2025-06-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-11 | 2023-10-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 57764 | 4329.52 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-11 | 2023-10-11 | 1 | 1 | 2023-10-11 | 2023-11-01 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | 2023-11-02 | 2023-11-02 | 1 | 1 | 2023-11-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-29 | 2024-07-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1480.97 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-29 | 2024-06-27 | Unknown | Unknown | 2024-06-27 | 2024-08-12 | 47 | 33 | 2024-08-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-25 | 2022-07-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3595.04 | Unknown | Unknown | Yes | N/A | N/A | 2022-07-25 | 2023-03-29 | 248 | 178 | 2023-03-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-27 | 2025-02-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3753.77 | 1674.67 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-27 | 2025-04-11 | 44 | 32 | 2025-04-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-22 | 2024-01-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3662 | 1145.34 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-22 | 2023-11-15 | Unknown | Unknown | 2023-11-15 | 2024-02-02 | 80 | 58 | 2024-02-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | 66.65 | 66.65 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-21 | 2025-04-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1827.83 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-21 | 2025-05-21 | 31 | 23 | 2025-05-21 | 2025-07-11 | 52 | 38 | 2025-07-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-21 | 2025-07-03 | 44 | 32 | Unknown | 2025-06-25 | Unknown | Unknown | 2025-07-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Commercial | N/A | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-07 | 2023-03-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 8648.53 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-07 | 2023-03-21 | 15 | 11 | 2023-03-21 | 2023-08-25 | 158 | 114 | Unknown | Unknown | Unknown | Unknown | 2023-08-25 | 2023-09-26 | 33 | 23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | Applicant Design | Commercial | Disadvantaged Community,Underserved Community | Chula Vista | CHULA VISTA | 733 | 733 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-05 | 2023-12-05 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 106019.79 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-05 | 2024-08-01 | 241 | 173 | 2024-08-01 | 2024-04-23 | Unknown | Unknown | 2024-08-16 | 2025-06-18 | 297 | 213 | 2024-02-01 | 2025-03-10 | 236 | 168 | 2024-04-23 | Unknown | Unknown | Unknown | 2025-03-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 47.05 | 47.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-29 | 2024-09-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1106.45 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-29 | 2024-08-15 | Unknown | Unknown | 2024-08-15 | 2024-09-17 | 34 | 24 | 2024-09-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | N/A | 144 | 144 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-11 | 2025-05-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1543.62 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-11 | 2025-05-09 | 303 | 217 | 2025-05-09 | 2025-05-09 | 1 | 1 | 2025-05-09 | 2025-05-28 | 20 | 14 | Unknown | Unknown | Unknown | Unknown | 2025-05-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 75.15 | 75.15 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-06 | 2025-03-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1231.32 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-06 | 2025-02-13 | Unknown | Unknown | 2025-02-13 | 2025-03-10 | 26 | 18 | 2025-03-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-27 | 2025-04-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3318.39 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-27 | 2025-04-07 | 12 | 8 | 2025-04-07 | 2025-06-18 | 73 | 53 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-18 | 2025-06-26 | 9 | 7 | Unknown | 2025-07-30 | Unknown | Unknown | 2025-08-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 9.05 | 9.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-18 | 2025-03-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2167.38 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-18 | 2025-07-25 | 130 | 94 | 2025-07-25 | 2025-03-31 | Unknown | Unknown | 2025-03-18 | 2025-03-31 | 14 | 10 | 2025-08-15 | 2025-08-15 | 1 | 1 | 2025-03-31 | 2025-09-08 | 162 | 116 | Unknown | Unknown | Unknown | Unknown | 2025-09-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-20 | 2024-01-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2296.84 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-20 | 2023-12-27 | 8 | 6 | 2023-12-27 | 2024-02-02 | 38 | 28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-20 | 2025-06-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1083.85 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-20 | 2025-06-14 | Unknown | Unknown | 2025-06-14 | 2025-06-23 | 10 | 6 | 2025-06-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-23 | 2025-08-27 | 66 | 48 | Unknown | Unknown | Unknown | Unknown | 2025-08-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | 56.1 | 56.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-06 | 2024-12-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1794.26 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-06 | 2024-11-21 | Unknown | Unknown | 2024-11-21 | 2024-12-06 | 16 | 12 | 2024-12-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-06 | 2025-08-20 | 258 | 184 | Unknown | Unknown | Unknown | Unknown | 2025-08-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Commercial | Underserved Community | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-10 | 2024-12-10 | 2025-06-05 | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 8592.21 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-10 | 2025-01-06 | 28 | 20 | 2025-01-06 | 2025-02-20 | 46 | 34 | 2025-01-07 | 2025-01-14 | 8 | 6 | 2025-01-15 | 2025-02-25 | 42 | 30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2020-11-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-14 | 2023-12-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 17654 | 3692.14 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-14 | 2023-12-15 | 2 | 2 | 2023-12-15 | 2024-03-05 | 82 | 58 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 92.1 | 92.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-14 | 2023-09-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 586.68 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-14 | 2023-09-15 | 2 | 2 | 2023-09-15 | 2023-09-15 | 1 | 1 | 2023-09-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R29/R45) | UG | IOU Design | Commercial | Underserved Community | SAN MARCOS | NCTD-Trolly North of 56, SAN MARCOS | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-04 | 2023-07-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 355833 | 108121.32 | Unknown | Unknown | Yes | N/A | N/A | 2023-05-04 | 2023-07-26 | 84 | 60 | 2023-07-26 | 2024-04-03 | 253 | 181 | 2023-09-20 | 2025-01-02 | 46 | 34 | 2023-09-21 | 2025-06-26 | 146 | 103 | 2024-04-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | N/A | 26 | 26 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-05 | 2024-06-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1001.01 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-05 | 2024-06-05 | 1 | 1 | 2024-06-05 | 2024-06-20 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LEMON GROVE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-04-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-19 | 2023-05-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 495.75 | Unknown | Unknown | Yes | N/A | N/A | 2023-04-19 | 2023-05-19 | 31 | 23 | 2023-05-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | EL CAJON | EL CAJON | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2025-04-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-30 | 2024-05-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 468.05 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-30 | 2024-05-01 | 2 | 2 | 2024-05-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-09 | 2024-06-19 | 42 | 30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ALPINE | N/A | 136 | 136 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-29 | Unknown | Unknown | No | 2024-03-11 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-11 | 2024-03-11 | 2024-10-09 | IOU Designed & Installed | N/A | Yes | 168 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1224.88 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-11 | 2025-03-20 | 375 | 269 | 2025-03-20 | 2024-04-01 | Unknown | Unknown | 2024-04-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-01 | 2024-10-09 | 192 | 138 | Unknown | 2024-08-27 | Unknown | Unknown | 2024-10-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | COUNTY OF SAN DIEGO-SOUTH of 56 | 38.05 | 38.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-19 | 2023-10-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 818.5 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-19 | 2023-09-06 | Unknown | Unknown | 2023-09-06 | 2023-10-26 | 51 | 37 | 2023-10-26 | Unknown | Unknown | Unknown | 2023-10-30 | 2023-11-02 | 4 | 4 | 2023-10-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | 1109.7 | 1109.7 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2023-11-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-27 | 2025-03-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 545.93 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-27 | 2025-03-27 | 1 | 1 | 2025-03-27 | 2025-04-04 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-04 | 2025-06-24 | 82 | 58 | Unknown | 2025-06-27 | Unknown | Unknown | 2025-08-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | CARLSBAD | CARLSBAD | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-10 | 2023-11-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3661.75 | 367.38 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-10 | 2023-06-12 | Unknown | Unknown | 2023-06-12 | 2023-11-10 | 152 | 110 | 2023-11-10 | 2024-07-30 | 147 | 105 | 2023-11-28 | 2024-08-01 | 103 | 75 | 2023-11-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-25 | 2024-03-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1343.44 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-25 | 2024-02-08 | Unknown | Unknown | 2024-02-08 | 2024-04-05 | 58 | 42 | 2024-04-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-29 | 2023-11-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 961.13 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-29 | 2023-11-29 | 1 | 1 | 2023-11-29 | 2023-11-29 | 1 | 1 | 2023-11-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 27.02 | 27.02 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-06 | 2025-06-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1397.01 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-06 | 2025-06-23 | 322 | 230 | 2025-06-23 | 2025-06-23 | 1 | 1 | 2025-06-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-07 | 2023-02-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 893.64 | Unknown | Unknown | Yes | N/A | N/A | 2023-02-07 | 2023-02-07 | 1 | 1 | 2023-02-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 242.05 | 242.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-12 | 2023-09-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 814.95 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-12 | 2023-06-28 | Unknown | Unknown | 2023-06-28 | 2023-09-18 | 83 | 59 | 2023-09-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-08-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-05 | 2023-09-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3754 | 451.36 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-05 | 2023-04-10 | Unknown | Unknown | 2023-04-10 | 2023-09-15 | 159 | 115 | 2023-09-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-21 | 2024-12-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 46962 | 1050.86 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-21 | 2024-10-22 | Unknown | Unknown | 2024-10-22 | 2024-12-16 | 56 | 40 | 2024-12-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-01 | 2025-05-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1522.4 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-01 | 2025-05-01 | 1 | 1 | 2025-05-01 | 2025-05-01 | 1 | 1 | 2025-05-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | Both | IOU Design | Residential | Underserved Community | VS 1088-A2 | VISTA | 11220180 | 11220180 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-06-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-06 | 2023-04-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 21470 | 17389.81 | Unknown | Unknown | Yes | N/A | N/A | 2023-02-06 | 2023-02-06 | 1 | 1 | 2023-02-06 | 2024-10-11 | 614 | 440 | 2023-05-22 | 2024-10-09 | 5 | 5 | 2024-10-01 | 2025-05-01 | 58 | 40 | 2024-10-15 | Unknown | Unknown | Unknown | 2024-10-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-21 | 2025-04-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 809.95 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-21 | 2025-04-29 | 9 | 7 | 2025-04-29 | 2025-04-29 | 1 | 1 | 2025-04-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | 18.1 | 18.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-06 | 2025-02-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7962 | 1430.88 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-06 | 2024-04-17 | 72 | 52 | 2024-04-17 | 2025-03-04 | 322 | 230 | Unknown | Unknown | Unknown | Unknown | 2025-02-14 | 2025-03-06 | 21 | 15 | 2025-03-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | ENCINITAS | N/A | 76 | 76 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-08-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-25 | 2024-06-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1526.99 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-25 | 2024-06-26 | 2 | 2 | 2024-06-26 | 2024-06-26 | 1 | 1 | 2024-06-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | IOU Design | Commercial | Underserved Community | VISTA | VISTA | 26006.4 | 26006.4 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-03-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-28 | 2023-09-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 25308 | 134087.65 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-28 | 2023-07-11 | Unknown | Unknown | 2023-07-11 | 2025-01-27 | 567 | 405 | 2023-10-03 | 2024-12-09 | 107 | 77 | 2023-12-22 | 2025-05-21 | 121 | 83 | 2025-01-27 | Unknown | Unknown | Unknown | 2025-04-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 132 | 132 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-11 | 2023-12-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3941 | 806.16 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-11 | 2023-10-31 | Unknown | Unknown | 2023-10-31 | 2023-12-11 | 42 | 30 | 2023-12-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2026-08-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-15 | 2024-10-15 | 2025-01-06 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1583.75 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-15 | 2024-09-21 | Unknown | Unknown | 2024-09-21 | 2024-10-30 | 40 | 28 | 2024-10-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-30 | 2025-01-06 | 69 | 49 | Unknown | Unknown | Unknown | Unknown | 2025-01-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-09 | 2025-04-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1587.49 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-09 | 2025-04-09 | 1 | 1 | 2025-04-09 | 2025-04-09 | 1 | 1 | 2025-04-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-15 | 2025-01-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 184912 | 22475.1 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-15 | 2025-02-25 | 42 | 30 | 2025-02-25 | 2025-03-10 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 40 | 40 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-20 | 2025-06-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 829.06 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-20 | 2025-06-12 | Unknown | Unknown | 2025-06-12 | 2025-06-20 | 9 | 7 | 2025-06-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-11 | 2025-04-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1575.86 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-11 | 2025-04-11 | 1 | 1 | 2025-04-11 | 2025-04-16 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-16 | 2025-08-21 | 128 | 92 | Unknown | Unknown | Unknown | Unknown | 2025-08-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2030-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-21 | 2023-09-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 943.55 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-21 | 2023-09-21 | 1 | 1 | 2023-09-21 | 2023-12-28 | 99 | 71 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-12 | 2023-12-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2629.7 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-12 | 2024-02-05 | 56 | 40 | 2024-02-05 | 2024-03-01 | 26 | 20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN MARCOS | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-10 | 2025-02-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1225.94 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-10 | 2025-02-20 | 11 | 9 | 2025-02-20 | 2025-03-13 | 22 | 16 | 2025-03-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 16.4 | 16.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-24 | 2025-03-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-24 | 2025-05-22 | 60 | 44 | 2025-05-22 | 2025-05-29 | 8 | 6 | 2025-05-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | VALLEY CENTER | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-03 | 2025-03-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1690.13 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-03 | 2025-02-20 | Unknown | Unknown | 2025-02-20 | 2025-03-03 | 12 | 8 | 2025-03-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-18 | 2024-01-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 1034531 | 440492.03 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-18 | 2023-06-01 | Unknown | Unknown | 2023-06-01 | 2024-11-11 | 530 | 378 | 2024-02-12 | 2024-08-01 | 24 | 18 | 2024-03-19 | 2024-12-18 | 52 | 40 | 2024-11-11 | Unknown | Unknown | Unknown | 2025-05-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 74 | 74 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-10 | 2024-06-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1562.56 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-10 | 2024-04-30 | Unknown | Unknown | 2024-04-30 | 2024-06-14 | 46 | 34 | 2024-06-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN MARCOS | N/A | 8994 | 8994 | Not Available | >2MW | No | N/A | N/A | N/A | 2025-11-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-23 | 2025-01-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 65483 | 4325.54 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-23 | 2024-06-19 | Unknown | Unknown | 2024-06-19 | 2025-02-28 | 255 | 183 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | LAGUNA NIGUEL | N/A | 108.05 | 108.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-01 | 2023-03-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 657.09 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-01 | 2023-04-17 | 48 | 34 | 2023-04-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-17 | 2024-09-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1811.79 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-17 | 2024-09-26 | 10 | 8 | 2024-09-26 | 2024-09-26 | 1 | 1 | 2024-09-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | VALLEY CENTER | N/A | 73.05 | 73.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-21 | 2024-05-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1065.95 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-21 | 2024-05-22 | 2 | 2 | 2024-05-22 | 2024-11-06 | 169 | 121 | 2024-07-17 | 2024-07-17 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-11-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 18 | 18 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-25 | 2024-02-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1803.73 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-25 | 2023-11-22 | Unknown | Unknown | 2023-11-22 | 2024-02-15 | 86 | 62 | 2024-02-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | 75.05 | 75.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-12 | 2024-11-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1454.78 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-12 | 2024-12-03 | 22 | 16 | 2024-12-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-12 | 2025-02-05 | 44 | 30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | Oceanside | OCEANSIDE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-22 | 2023-05-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 280442 | 63794.85 | Unknown | Unknown | Yes | N/A | N/A | 2023-05-22 | 2023-04-10 | Unknown | Unknown | 2023-04-10 | 2023-09-07 | 151 | 109 | 2023-06-02 | 2023-06-07 | 6 | 4 | 2023-07-27 | 2023-09-11 | 33 | 23 | 2023-09-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-23 | 2025-04-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1014.27 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-23 | 2025-04-23 | 1 | 1 | 2025-04-23 | 2025-04-23 | 1 | 1 | 2025-04-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | 154.24 | 154.24 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-07-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-29 | 2023-01-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 22609.57 | 55679.35 | Unknown | Unknown | Yes | N/A | N/A | 2022-08-29 | 2023-01-31 | 156 | 112 | 2023-01-31 | Unknown | Unknown | Unknown | 2024-08-21 | 2025-01-23 | 156 | 112 | 2023-05-09 | 2023-05-17 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 73.05 | 73.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-27 | 2024-09-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 826.97 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-27 | 2025-04-22 | 239 | 171 | 2025-04-22 | 2025-04-23 | 2 | 2 | 2025-04-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-05 | 2025-01-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 999.91 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-05 | 2024-12-20 | 16 | 12 | 2024-12-20 | 2025-01-23 | 35 | 25 | Unknown | Unknown | Unknown | Unknown | 2024-12-05 | 2025-01-17 | 44 | 32 | 2025-01-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | OH | IOU Design | Commercial | N/A | Irvine | NATIONAL CITY | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-17 | 2023-04-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 9090.53 | Unknown | Unknown | Yes | N/A | N/A | 2023-02-17 | 2023-02-17 | 1 | 1 | 2023-02-17 | 2023-11-22 | 279 | 199 | 2023-09-06 | 2023-09-20 | 15 | 11 | 2023-07-28 | 2025-08-06 | 131 | 97 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-10 | 2025-06-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1689.91 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-10 | 2025-06-18 | 9 | 7 | 2025-06-18 | 2025-06-18 | 1 | 1 | 2025-06-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-18 | 2025-08-07 | 51 | 37 | Unknown | Unknown | Unknown | Unknown | 2025-08-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | RANCHO MISSION VIEJO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-03 | 2025-06-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 14231 | 538.18 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-03 | 2025-06-03 | 1 | 1 | 2025-06-03 | 2025-07-07 | 35 | 25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-07-07 | 2025-08-26 | 51 | 37 | Unknown | 2025-08-28 | Unknown | Unknown | 2025-09-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 16 | 16 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-21 | 2023-06-21 | 2023-11-01 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 916.14 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-21 | 2023-04-06 | Unknown | Unknown | 2023-04-06 | 2023-06-21 | 77 | 55 | 2023-06-21 | 2023-11-01 | 134 | 96 | Unknown | Unknown | Unknown | Unknown | 2023-11-01 | 2023-11-01 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2023-11-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | Underserved Community | Escondido | ESCONDIDO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-07-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-02-04 | 2022-12-19 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 163811 | 31419 | Unknown | Unknown | Yes | N/A | N/A | 2022-02-04 | 2023-06-27 | 509 | 363 | 2023-06-27 | 2023-10-16 | 112 | 80 | 2023-07-18 | 2023-10-11 | 77 | 57 | 2023-07-31 | 2023-10-23 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2021-04-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-04 | 2023-04-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 426.7 | Unknown | Unknown | Yes | N/A | N/A | 2023-04-04 | 2023-04-04 | 1 | 1 | 2023-04-04 | 2024-04-16 | 379 | 271 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-16 | Unknown | Unknown | Unknown | Unknown | 2025-04-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | NATIONAL CITY | NATIONAL CITY | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-13 | 2025-02-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 27449 | 506.13 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-13 | 2025-03-04 | 20 | 14 | 2025-03-04 | 2025-06-30 | 119 | 85 | Unknown | Unknown | Unknown | Unknown | 2025-02-26 | 2025-05-28 | 92 | 66 | 2025-06-30 | Unknown | Unknown | Unknown | Unknown | 2025-07-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-15 | Unknown | Unknown | No | 2024-04-18 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-18 | 2024-04-18 | Unknown | IOU Designed & Installed | N/A | Yes | 15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 12481 | 584.27 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-18 | 2024-05-03 | 16 | 12 | 2024-05-03 | 2024-04-18 | Unknown | Unknown | 2024-04-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-18 | 2025-07-31 | 470 | 336 | Unknown | Unknown | Unknown | Unknown | 2025-07-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | Underserved Community | ES 1110-F5 DIXON TL PH3 | ESCONDIDO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-01 | 2023-06-01 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 35452.77 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-01 | 2024-01-13 | 227 | 162 | 2024-01-13 | 2024-04-17 | 96 | 68 | 2024-02-08 | 2024-10-24 | 37 | 26 | 2024-02-08 | 2025-07-14 | 4 | 0 | 2024-07-03 | Unknown | Unknown | Unknown | 2024-07-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | BONITA | N/A | 59.4 | 59.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-19 | 2023-01-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 98.41 | Unknown | Unknown | Yes | N/A | N/A | 2023-01-19 | 2023-03-06 | 47 | 33 | 2023-03-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-11 | 2024-04-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2024-04-11 | 2023-12-21 | Unknown | Unknown | 2023-12-21 | 2024-05-20 | 152 | 108 | 2024-05-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | 283.1 | 283.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-30 | 2025-01-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7962 | 1494.35 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-30 | 2025-05-02 | 93 | 67 | 2025-05-02 | 2025-05-07 | 6 | 4 | 2025-02-14 | 2025-02-20 | 7 | 5 | 2025-02-12 | 2025-03-10 | 22 | 16 | 2025-05-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-12 | 2024-01-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 725.52 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-12 | 2024-01-12 | 1 | 1 | 2024-01-12 | 2024-01-12 | 1 | 1 | 2024-01-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 131.05 | 131.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-06 | 2024-08-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1939.84 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-06 | 2024-08-06 | 1 | 1 | 2024-08-06 | 2024-08-06 | 1 | 1 | 2024-08-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | VALLEY CENTER | N/A | 67.05 | 67.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-22 | 2025-04-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 867.94 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-22 | 2025-03-31 | Unknown | Unknown | 2025-03-31 | 2025-04-22 | 23 | 17 | 2025-04-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-23 | 2025-09-03 | 134 | 96 | Unknown | Unknown | Unknown | Unknown | 2025-09-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 55 | 55 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-25 | 2024-04-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 491.68 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-25 | 2024-04-15 | 22 | 16 | 2024-04-15 | 2024-04-15 | 1 | 1 | 2024-04-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-01 | 2023-06-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 464.78 | Unknown | Unknown | Yes | N/A | N/A | 2023-05-01 | 2023-06-26 | 57 | 41 | 2023-06-26 | 2023-06-26 | 1 | 1 | 2023-06-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | OCEANSIDE | 3 | 3 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-12 | 2023-12-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 36349.88 | 415.36 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-12 | 2023-08-08 | Unknown | Unknown | 2023-08-08 | 2024-01-26 | 172 | 124 | 2024-01-26 | 2024-01-30 | 2 | 2 | 2024-01-26 | 2024-02-13 | 19 | 13 | 2024-01-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SANTEE | N/A | 64 | 64 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-14 | 2024-02-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 163.83 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-14 | 2024-04-01 | 48 | 34 | 2024-04-01 | 2024-04-02 | 2 | 2 | 2024-04-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 68.05 | 68.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-18 | 2024-03-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 421.57 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-18 | 2024-01-26 | Unknown | Unknown | 2024-01-26 | 2024-04-02 | 68 | 48 | 2024-04-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | N/A | 32.05 | 32.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-11 | 2024-01-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 288.14 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-11 | 2024-01-11 | 1 | 1 | 2024-01-11 | 2024-01-11 | 1 | 1 | 2024-01-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-10 | 2025-01-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1621.42 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-10 | 2025-01-17 | 39 | 29 | 2025-01-17 | 2025-01-21 | 5 | 3 | 2025-01-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-16 | Unknown | Unknown | No | 2025-03-11 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-11 | 2025-03-11 | Unknown | IOU Designed & Installed | N/A | Yes | 9 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1546.19 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-11 | 2025-03-20 | 10 | 8 | 2025-03-20 | 2025-03-17 | Unknown | Unknown | 2025-03-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-17 | Unknown | Unknown | Unknown | Unknown | 2025-08-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2018-01-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-24 | 2025-04-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 794.39 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-24 | 2025-04-23 | Unknown | Unknown | 2025-04-23 | 2025-04-24 | 2 | 2 | 2025-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2020-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-24 | 2025-05-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 56.92 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-24 | 2025-05-05 | 12 | 8 | 2025-05-05 | 2025-05-23 | 19 | 15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-26 | 2023-12-26 | 2025-06-30 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 499.18 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-26 | 2023-12-26 | 1 | 1 | 2023-12-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-26 | 2025-06-30 | 553 | 395 | Unknown | Unknown | Unknown | Unknown | 2025-06-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 9.05 | 9.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-28 | 2025-01-31 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1610.59 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-28 | 2025-01-30 | 3 | 3 | 2025-01-30 | 2025-01-30 | 1 | 1 | 2025-01-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | N/A | 492.1 | 492.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-31 | Unknown | Unknown | No | 2022-04-05 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-05 | 2022-04-05 | Unknown | IOU Designed & Installed | N/A | Yes | 475 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3885 | 993.03 | Unknown | Unknown | Yes | N/A | N/A | 2022-04-05 | 2023-07-24 | 476 | 340 | 2023-07-24 | 2023-07-24 | 1 | 1 | 2023-07-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2022-05-06 | Unknown | Unknown | Unknown | Unknown | 2024-06-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | LA JOLLA | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-16 | 2024-10-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1635.81 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-16 | 2024-10-25 | 10 | 8 | 2024-10-25 | 2024-11-18 | 25 | 17 | Unknown | Unknown | Unknown | Unknown | 2024-10-16 | 2024-11-15 | 31 | 23 | 2024-11-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | OH | IOU Design | Commercial | Underserved Community | San Marcos | COUNTY OF SAN DIEGO-NORTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-15 | 2024-02-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 880871.22 | 109561.9 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-15 | 2023-09-19 | 36 | 26 | 2023-09-19 | 2024-12-31 | 470 | 336 | 2024-07-15 | 2024-09-24 | 72 | 52 | 2024-06-19 | 2025-06-10 | 84 | 62 | 2024-12-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-27 | 2024-09-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1230.39 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-27 | 2024-09-10 | Unknown | Unknown | 2024-09-10 | 2024-10-12 | 33 | 24 | 2024-10-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-29 | 2025-05-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 4868.43 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-29 | 2025-04-30 | 2 | 2 | 2025-04-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 14 | 14 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-03 | 2025-02-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1741.22 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-03 | 2025-01-22 | Unknown | Unknown | 2025-01-22 | 2025-02-05 | 15 | 11 | 2025-02-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-11 | 2025-02-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2238.04 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-11 | 2025-02-11 | 1 | 1 | 2025-02-11 | 2025-04-04 | 53 | 39 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-12 | 2025-06-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1016.9 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-12 | 2025-06-12 | 1 | 1 | 2025-06-12 | 2025-06-12 | 1 | 1 | 2025-06-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 5 | 5 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-24 | 2025-05-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 852.68 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-24 | 2025-05-29 | 67 | 49 | 2025-05-29 | 2025-05-29 | 1 | 1 | 2025-05-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-12 | 2024-12-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1237.72 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-12 | 2025-01-27 | 47 | 33 | 2025-01-27 | 2025-01-27 | 1 | 1 | 2025-01-27 | 2025-02-11 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | 2025-02-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 16.05 | 16.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-05 | 2025-05-05 | 2025-05-30 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 859.48 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-05 | 2025-05-12 | 8 | 6 | 2025-05-12 | 2025-05-12 | 1 | 1 | 2025-05-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-12 | 2025-05-30 | 19 | 15 | Unknown | Unknown | Unknown | Unknown | 2025-05-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LAGUNA HILLS | N/A | 6000 | 6000 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-03-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-08 | 2023-05-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 736.29 | Unknown | Unknown | Yes | N/A | N/A | 2023-05-08 | 2023-05-08 | 1 | 1 | 2023-05-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | EL CAJON | N/A | 538 | 538 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-02 | 2025-06-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7842 | 686.66 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-02 | 2025-05-07 | Unknown | Unknown | 2025-05-07 | 2025-05-07 | 1 | 1 | 2025-05-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-29 | 2024-08-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1050.75 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-29 | 2024-08-29 | 1 | 1 | 2024-08-29 | 2024-08-29 | 1 | 1 | 2024-08-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-06 | 2025-02-06 | 2025-06-11 | IOU Designed & Installed | N/A | No | Unknown | 1448.63 | 0 | Unknown | Unknown | 22.88 | 1425.75 | 3981 | 1394.71 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-06 | 2025-03-13 | 36 | 26 | 2025-03-13 | 2025-03-13 | 1 | 1 | 2025-03-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-13 | 2025-06-11 | 91 | 65 | Unknown | 2025-05-09 | Unknown | Unknown | 2025-06-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-18 | 2024-10-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 9150 | 525.39 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-18 | 2024-10-18 | 1 | 1 | 2024-10-18 | 2024-10-18 | 1 | 1 | 2024-10-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | 39.05 | 39.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-16 | 2025-05-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 11943 | 833.69 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-16 | 2025-05-23 | 38 | 28 | 2025-05-23 | 2025-05-29 | 7 | 5 | 2025-05-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-29 | 2025-08-05 | 69 | 49 | Unknown | Unknown | Unknown | Unknown | 2025-08-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-12 | 2025-06-12 | 2025-06-26 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1197.17 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-12 | 2025-04-30 | Unknown | Unknown | 2025-04-30 | 2025-06-13 | 45 | 33 | 2025-06-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-13 | 2025-06-26 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | 2025-06-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | IOU Design | Commercial | Underserved Community | DANA POINT | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-08-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-08 | 2024-03-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 22569.16 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-08 | 2024-01-08 | 1 | 1 | 2024-01-08 | 2024-12-12 | 340 | 244 | 2024-03-22 | 2024-10-18 | 38 | 28 | 2024-11-22 | 2024-12-11 | 20 | 14 | 2024-12-12 | Unknown | Unknown | Unknown | 2025-08-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 112.05 | 112.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-09 | 2025-02-05 | 2025-06-16 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2318.74 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-09 | 2025-01-24 | 47 | 35 | 2025-01-24 | 2025-02-05 | 13 | 9 | 2025-02-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-05 | 2025-06-16 | 132 | 94 | Unknown | Unknown | Unknown | Unknown | 2025-06-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-23 | 2025-01-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1570.22 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-23 | 2025-01-23 | 1 | 1 | 2025-01-23 | 2025-01-23 | 1 | 1 | 2025-01-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | DEL MAR | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2025-01-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-16 | 2024-01-17 | 2024-02-02 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3203.32 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-16 | 2024-01-16 | 1 | 1 | 2024-01-16 | 2024-06-21 | 158 | 114 | 2024-06-21 | 2024-06-21 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-06-21 | Unknown | Unknown | Unknown | 2024-06-21 | Unknown | Unknown | Unknown | 2024-02-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 39.05 | 39.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-26 | 2024-08-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2399.12 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-26 | 2024-08-28 | 3 | 3 | 2024-08-28 | 2024-08-29 | 2 | 2 | 2024-08-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-02 | 2025-01-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 9765.55 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-02 | 2025-02-25 | 55 | 39 | 2025-02-25 | 2025-05-07 | 72 | 52 | Unknown | Unknown | Unknown | Unknown | 2025-03-10 | 2025-03-31 | 22 | 16 | 2025-05-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-09-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-20 | 2025-02-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1253.06 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-20 | 2025-02-27 | 8 | 6 | 2025-02-27 | 2025-03-21 | 23 | 17 | 2025-03-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | IMPERIAL BEACH | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-22 | 2025-01-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 104.94 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-22 | 2025-01-15 | Unknown | Unknown | 2025-01-15 | 2025-05-09 | 115 | 83 | Unknown | Unknown | Unknown | Unknown | 2025-02-06 | 2025-03-27 | 50 | 36 | 2025-05-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LA JOLLA | N/A | 113.05 | 113.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-01 | 2024-08-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1130.51 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-01 | 2024-06-27 | Unknown | Unknown | 2024-06-27 | 2024-08-21 | 56 | 40 | 2024-08-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | OCEANSIDE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-02-01 | Unknown | Unknown | No | 2023-10-13 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-29 | 2023-10-23 | Unknown | IOU Designed & Installed | N/A | Yes | 234 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1539.08 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-29 | 2024-06-03 | 249 | 177 | 2024-06-03 | 2023-10-23 | Unknown | Unknown | 2023-10-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-23 | 2025-07-16 | 633 | 453 | Unknown | 2025-06-11 | Unknown | Unknown | 2025-07-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-10 | 2024-12-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1529.47 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-10 | 2024-12-10 | 1 | 1 | 2024-12-10 | 2024-12-10 | 1 | 1 | 2024-12-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | RANCHO LA COSTA | N/A | 24 | 24 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-29 | 2025-06-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 812.25 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-29 | 2025-06-11 | 14 | 10 | 2025-06-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-11 | 2025-08-04 | 55 | 39 | Unknown | 2025-07-25 | Unknown | Unknown | 2025-08-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 19 | 19 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-02 | 2025-06-06 | 2025-06-27 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 450.11 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-02 | 2025-06-06 | 5 | 5 | 2025-06-06 | 2025-06-06 | 1 | 1 | 2025-06-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-06 | 2025-06-27 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | 2025-06-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | CARLSBAD | 118 | 118 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-13 | 2024-03-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1333.1 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-13 | 2024-03-20 | 99 | 71 | 2024-03-20 | 2024-04-01 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2024-03-28 | 2025-05-16 | 415 | 297 | 2024-04-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-24 | 2025-06-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 885.69 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-24 | 2025-06-04 | Unknown | Unknown | 2025-06-04 | 2025-06-27 | 24 | 18 | 2025-06-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-30 | 2025-04-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1775.22 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-30 | 2025-05-12 | 13 | 9 | 2025-05-12 | 2025-05-23 | 12 | 10 | 2025-05-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Residential | N/A | Chula Vista | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-25 | 2025-03-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 4612.48 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-25 | 2025-03-25 | 1 | 1 | 2025-03-25 | 2025-04-15 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | 2025-04-12 | 2025-04-25 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | Underserved Community | Poway | POWAY | 64512 | 64512 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-08-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-11 | 2022-08-11 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 99261.82 | Unknown | Unknown | Yes | N/A | N/A | 2022-08-11 | 2024-07-03 | 693 | 495 | 2024-07-03 | 2025-05-09 | 311 | 223 | 2024-07-23 | 2025-07-14 | 104 | 74 | 2024-09-05 | 2025-06-16 | 95 | 67 | 2025-05-14 | Unknown | Unknown | Unknown | 2025-05-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | 331 | 331 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-12 | 2024-02-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 232447 | 6946.46 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-12 | 2024-03-18 | 36 | 26 | 2024-03-18 | 2024-03-20 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-08 | 2024-05-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7681 | 584.27 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-08 | 2024-04-19 | Unknown | Unknown | 2024-04-19 | 2024-05-08 | 20 | 14 | 2024-05-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-08 | 2025-08-21 | 471 | 337 | Unknown | Unknown | Unknown | Unknown | 2025-08-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | COUNTY OF SAN DIEGO-NORTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-27 | 2025-02-27 | 2025-06-26 | IOU Designed & Installed | N/A | No | Unknown | 483.61 | 0 | Unknown | Unknown | Unknown | 483.61 | 0 | 654.05 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-27 | 2025-02-25 | Unknown | Unknown | 2025-02-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-03 | 2025-03-11 | 9 | 7 | 2025-03-31 | 2025-06-26 | 88 | 64 | Unknown | Unknown | Unknown | Unknown | 2025-06-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-12 | 2023-08-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1131.51 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-12 | 2023-08-18 | 38 | 28 | 2023-08-18 | 2023-08-18 | 1 | 1 | 2023-08-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SANTEE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-22 | 2025-04-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1248.89 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-22 | 2025-04-03 | Unknown | Unknown | 2025-04-03 | 2025-04-24 | 22 | 16 | 2025-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-17 | 2025-04-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1663.81 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-17 | 2025-04-17 | 1 | 1 | 2025-04-17 | 2025-04-17 | 1 | 1 | 2025-04-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | Poway | POWAY | 128 | 128 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-11 | 2024-11-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 1484 | 19458.3 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-11 | 2025-01-10 | 61 | 45 | 2025-01-10 | 2025-06-16 | 158 | 112 | 2025-02-05 | 2025-07-14 | 53 | 37 | 2025-05-30 | 2025-07-18 | 12 | 6 | 2025-06-16 | Unknown | Unknown | Unknown | 2025-07-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SOLANA BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-12 | 2024-06-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1426.29 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-12 | 2024-11-13 | 155 | 111 | 2024-11-13 | 2024-11-25 | 13 | 9 | 2024-11-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | OH | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | 32 | 32 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-27 | 2023-10-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 72613 | 65719.94 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-27 | 2023-10-18 | Unknown | Unknown | 2023-10-18 | Unknown | Unknown | Unknown | 2024-02-01 | 2024-09-20 | 140 | 102 | 2024-01-30 | 2024-10-07 | 38 | 28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-11 | 2023-09-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2303 | 519.36 | Unknown | Unknown | Yes | N/A | N/A | 2023-05-11 | 2023-05-11 | 1 | 1 | 2023-05-11 | 2023-09-05 | 118 | 84 | 2023-09-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | VALLEY CENTER | N/A | 33 | 33 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-18 | 2025-05-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1107.31 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-18 | 2025-05-19 | 32 | 22 | 2025-05-19 | 2025-05-28 | 10 | 8 | 2025-05-28 | 2025-09-05 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | 2025-06-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-17 | 2024-09-17 | 2025-01-05 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 4356.38 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-17 | 2024-09-17 | 1 | 1 | 2024-09-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R29/R45) | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | OCEANSIDE | 7425 | 7425 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-10-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2021-12-06 | 2021-12-06 | 2025-04-15 | IOU Designed & Installed | N/A | No | Unknown | 358853.39 | 34198.83 | Unknown | Unknown | 2118.29 | 322536.27 | 36052 | 162227.92 | Unknown | Unknown | Yes | N/A | N/A | 2021-12-06 | 2023-06-10 | 552 | 395 | 2023-06-10 | 2025-04-08 | 669 | 477 | 2023-07-27 | 2025-03-19 | 129 | 91 | 2023-10-10 | 2025-04-03 | 128 | 94 | Unknown | Unknown | Unknown | Unknown | 2025-04-18 | 2025-06-02 | 46 | 32 | 2025-04-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-10 | 2023-11-09 | 2023-11-10 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1052.1 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-10 | 2023-11-09 | 31 | 23 | 2023-11-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-09 | 2023-11-10 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2023-11-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 80 | 80 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-07 | 2024-02-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 798.56 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-07 | 2024-02-29 | 23 | 17 | 2024-02-29 | 2024-02-15 | Unknown | Unknown | 2024-02-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | BOULEVARD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-20 | Unknown | Unknown | No | 2023-11-17 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-17 | 2023-11-17 | Unknown | IOU Designed & Installed | N/A | Yes | 231 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3941 | 555.51 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-17 | 2024-07-05 | 232 | 166 | 2024-07-05 | 2023-11-17 | Unknown | Unknown | 2023-11-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R29/R45 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | 7310 | 7310 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-09-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-01 | 2024-07-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 70656.95 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-01 | 2024-06-25 | 238 | 170 | 2024-06-25 | 2025-01-30 | 220 | 158 | 2024-09-19 | 2025-01-08 | 11 | 7 | 2025-01-08 | 2025-02-05 | 23 | 15 | 2025-01-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | N/A | 185.8 | 185.8 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-25 | 2023-09-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 571.18 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-25 | 2023-11-16 | 53 | 39 | 2023-11-16 | 2023-12-15 | 30 | 22 | 2023-12-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 8.1 | 8.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-17 | 2024-10-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1711.47 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-17 | 2024-10-08 | 114 | 82 | 2024-10-08 | 2024-10-08 | 1 | 1 | 2024-10-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-09 | 2025-09-08 | 335 | 239 | Unknown | Unknown | Unknown | Unknown | 2025-09-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | CARLSBAD | CARLSBAD | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-02 | 2025-06-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 1656 | 442.21 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-02 | 2025-05-15 | Unknown | Unknown | 2025-05-15 | 2025-06-04 | 21 | 15 | 2025-06-04 | Unknown | Unknown | Unknown | 2025-06-04 | 2025-07-15 | 42 | 30 | 2025-06-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R29/R45) | UG | IOU Design | Commercial | Underserved Community | SAN MARCOS | SAN MARCOS | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-09 | 2024-03-01 | 2025-03-05 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 1987328 | 182258.59 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-09 | 2024-05-22 | 135 | 97 | 2024-05-22 | 2025-01-22 | 246 | 176 | 2024-07-15 | 2025-01-17 | 59 | 43 | 2024-09-17 | 2025-06-26 | 153 | 111 | 2025-01-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2027-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-02 | 2023-03-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 328.26 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-02 | 2023-03-02 | 1 | 1 | 2023-03-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | COUNTY OF SAN DIEGO-NORTH of 56 | 101.05 | 101.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-10 | 2025-01-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 42747.42 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-10 | 2025-01-14 | 36 | 26 | 2025-01-14 | 2025-05-19 | 126 | 90 | Unknown | Unknown | Unknown | Unknown | 2025-03-05 | 2025-06-09 | 40 | 28 | 2025-05-19 | 2025-07-01 | 44 | 32 | Unknown | Unknown | Unknown | Unknown | 2025-07-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | 520.5 | 520.5 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-28 | 2025-01-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1188.48 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-28 | 2025-01-13 | Unknown | Unknown | 2025-01-13 | 2025-02-13 | 32 | 24 | 2025-02-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2021-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-14 | 2025-05-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2686.79 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-14 | 2025-05-14 | 1 | 1 | 2025-05-14 | 2025-06-20 | 38 | 28 | Unknown | Unknown | Unknown | Unknown | 2025-05-14 | 2025-06-11 | 29 | 21 | 2025-06-20 | 2025-07-16 | 27 | 19 | Unknown | Unknown | Unknown | Unknown | 2025-07-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | NATIONAL CITY | N/A | 170 | 170 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-20 | 2024-09-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1539.21 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-20 | 2024-09-24 | 5 | 3 | 2024-09-24 | 2024-09-24 | 1 | 1 | 2024-09-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-26 | 2024-08-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 430.01 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-26 | 2024-08-09 | Unknown | Unknown | 2024-08-09 | 2024-08-26 | 18 | 12 | 2024-08-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CAPISTRANO BEACH | N/A | 70 | 70 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-10 | 2024-09-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1638.29 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-10 | 2024-09-25 | 16 | 12 | 2024-09-25 | 2024-09-25 | 1 | 1 | 2024-09-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 8646.75 | 8646.75 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-12-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-27 | 2024-09-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 35829 | 422.02 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-27 | 2025-03-06 | 161 | 115 | 2025-03-06 | 2025-04-04 | 30 | 22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-21 | 2023-10-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 25673 | 1347.87 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-21 | 2024-04-12 | 205 | 147 | 2024-04-12 | 2024-04-16 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-24 | 2025-04-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1031.89 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-24 | 2025-04-14 | Unknown | Unknown | 2025-04-14 | 2025-04-28 | 15 | 11 | 2025-04-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-09 | 2025-05-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1516.71 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-09 | 2025-05-20 | 12 | 8 | 2025-05-20 | 2025-05-28 | 9 | 7 | 2025-05-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-28 | 2025-08-04 | 69 | 49 | Unknown | Unknown | Unknown | Unknown | 2025-08-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | 15.4 | 15.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-09 | 2024-08-23 | 2024-10-23 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1538.05 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-09 | 2024-08-23 | 15 | 11 | 2024-08-23 | 2024-08-26 | 4 | 2 | 2024-08-26 | 2024-10-16 | 52 | 38 | Unknown | Unknown | Unknown | Unknown | 2024-10-16 | 2024-10-23 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2024-10-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R29/R45 | UG | IOU Design | Commercial | Underserved Community,Tribal Community | PALA | COUNTY OF SAN DIEGO-NORTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-08-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-27 | 2023-04-18 | 2025-06-27 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 31626.11 | Unknown | Unknown | Yes | N/A | N/A | 2022-09-27 | 2023-04-14 | 200 | 144 | 2023-04-14 | 2025-01-08 | 636 | 454 | 2023-05-25 | 2024-01-26 | 7 | 5 | 2023-06-29 | 2023-07-05 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-14 | Unknown | Unknown | 2025-06-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 52.7 | 52.7 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-26 | 2025-03-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 838.24 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-26 | 2025-04-29 | 35 | 25 | 2025-04-29 | 2025-05-21 | 23 | 17 | 2025-05-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | LA MESA | LA MESA | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-29 | 2022-06-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1237.12 | Unknown | Unknown | Yes | N/A | N/A | 2022-06-29 | 2023-04-19 | 295 | 211 | 2023-04-19 | 2023-04-27 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | 2023-02-16 | 2023-04-11 | 55 | 39 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SD 1190-A2 CMR PA9 WO3 | N/A | 222214 | 222214 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-03-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-10 | 2024-09-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 141434 | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2024-09-10 | 2024-09-10 | 1 | 1 | 2024-09-10 | 2024-09-11 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-11 | 2025-09-05 | 360 | 258 | Unknown | Unknown | Unknown | Unknown | 2025-07-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-10 | 2025-04-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 515.73 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-10 | 2025-04-10 | 1 | 1 | 2025-04-10 | 2025-04-24 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-06 | 2025-01-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1310.57 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-06 | 2025-01-08 | 3 | 3 | 2025-01-08 | 2025-01-24 | 17 | 13 | 2025-01-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | N/A | 139 | 139 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-06 | Unknown | Unknown | No | 2025-01-24 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-24 | 2025-01-24 | 2025-05-02 | IOU Designed & Installed | N/A | Yes | 56 | 2744.17 | 254.7 | Unknown | Unknown | 42.53 | 2446.94 | 3981 | 1482.14 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-24 | 2025-03-21 | 57 | 41 | 2025-03-21 | 2025-02-04 | Unknown | Unknown | 2025-02-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-04 | 2025-05-02 | 88 | 64 | Unknown | 2025-05-06 | Unknown | Unknown | 2025-05-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | RANCHO SANTA FE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-16 | 2025-05-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 23721 | 6592.43 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-16 | 2025-04-30 | Unknown | Unknown | 2025-04-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-18 | 2023-05-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 495.75 | Unknown | Unknown | Yes | N/A | N/A | 2023-04-18 | 2023-08-17 | 122 | 88 | 2023-08-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | PAUMA VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-09 | 2025-04-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 422.01 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-09 | 2025-04-09 | 1 | 1 | 2025-04-09 | 2025-05-28 | 50 | 36 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 4 | 4 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-19 | 2024-01-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 163.83 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-19 | 2023-11-10 | Unknown | Unknown | 2023-11-10 | 2024-02-08 | 91 | 65 | 2024-02-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2026-02-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-22 | 2023-08-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 347.21 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-22 | 2023-06-30 | Unknown | Unknown | 2023-06-30 | 2023-09-14 | 77 | 55 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | JAMUL | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2024-09-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-26 | 2023-09-26 | 2024-10-21 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7900 | 2070.19 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-26 | 2023-09-26 | 1 | 1 | 2023-09-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-08 | Unknown | Unknown | 2024-10-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-31 | 2025-02-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1482.57 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-31 | 2025-01-15 | Unknown | Unknown | 2025-01-15 | 2025-02-07 | 24 | 18 | 2025-02-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-23 | 2023-08-23 | 2023-10-02 | IOU Designed & Installed | N/A | No | Unknown | 16.94 | 0 | Unknown | Unknown | Unknown | 16.94 | 0 | 149.82 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-23 | 2023-09-29 | 38 | 28 | 2023-09-29 | 2023-09-29 | 1 | 1 | 2023-09-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-29 | 2023-10-02 | 4 | 2 | Unknown | Unknown | Unknown | Unknown | 2023-10-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LAKESIDE | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2028-05-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-17 | 2025-06-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1121.66 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-17 | 2025-05-28 | Unknown | Unknown | 2025-05-28 | 2025-06-19 | 23 | 17 | 2025-06-19 | Unknown | Unknown | Unknown | 2025-06-20 | 2025-06-24 | 5 | 3 | 2025-06-19 | 2025-07-08 | 20 | 14 | Unknown | Unknown | Unknown | Unknown | 2025-07-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Commercial | Underserved Community,Tribal Community | Alpine | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-27 | 2023-10-27 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 53237 | 21099.49 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-27 | 2023-11-08 | 13 | 9 | 2023-11-08 | 2025-03-18 | 497 | 355 | 2023-11-27 | 2024-06-10 | 51 | 37 | 2024-06-11 | 2024-06-25 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-07-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SANTEE | SANTEE | Unknown | Unknown | Not Available | Unknown | Yes | 2021-12-06 | 2024-11-14 | 1074 | 2020-11-19 | Unknown | Unknown | No |  | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2019-11-19 | 2023-03-29 |  | IOU Designed & Installed | N/A | No |  |  |  | 4479401.03 |  |  |  | 12732661 | 38178.54 |  | Unknown | Yes | N/A | N/A | 2019-11-19 | 2023-03-06 | 1204 | 860 | 2023-03-06 | 2024-06-13 | 466 | 334 | 2023-12-14 | 2023-12-18 | 5 | 3 | 2024-01-17 | 2024-06-17 | 21 | 15 |  | Unknown | Unknown | Unknown | 2024-07-05 | 2025-05-02 | 302 | 216 | 2025-07-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-14 | Unknown | Unknown | No | 2024-01-09 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-09 | 2024-01-09 | Unknown | IOU Designed & Installed | N/A | Yes | 251 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 944.93 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-09 | 2024-09-16 | 252 | 180 | 2024-09-16 | 2024-02-28 | Unknown | Unknown | 2024-02-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | CARLSBAD | NCTD-Trolly North of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-26 | 2024-11-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1431.06 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-26 | 2024-11-26 | 1 | 1 | 2024-11-26 | 2025-02-07 | 74 | 54 | 2024-12-26 | 2025-02-12 | 40 | 30 | 2024-12-11 | 2025-02-21 | 36 | 26 | 2025-02-07 | Unknown | Unknown | Unknown | Unknown | 2025-05-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-18 | 2025-02-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2178 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-18 | 2025-02-18 | 1 | 1 | 2025-02-18 | 2025-02-18 | 1 | 1 | 2025-02-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-31 | 2024-05-31 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 13730 | 1066.7 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-31 | 2024-06-04 | 5 | 3 | 2024-06-04 | 2024-06-11 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2024-06-04 | 2024-07-02 | 29 | 21 | 2024-06-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-18 | 2024-03-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1232.93 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-18 | 2025-03-25 | 373 | 267 | 2025-03-25 | 2025-03-24 | Unknown | Unknown | 2025-03-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | CAPISTRANO BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-20 | 2025-04-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7962 | 1810.94 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-20 | 2025-03-28 | 9 | 7 | 2025-03-28 | 2025-04-01 | 5 | 3 | 2025-04-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LA MESA | LA MESA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-13 | 2024-05-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7962 | 1396.06 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-13 | 2024-05-15 | 3 | 3 | 2024-05-15 | 2024-05-24 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | 2024-05-24 | 2024-06-19 | 27 | 19 | 2024-05-24 | 2025-08-05 | 439 | 313 | Unknown | Unknown | Unknown | Unknown | 2025-08-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 23.35 | 23.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-13 | 2025-01-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1316.88 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-13 | 2025-02-03 | 22 | 16 | 2025-02-03 | 2025-02-10 | 8 | 6 | 2025-02-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 107 | 107 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-21 | 2024-08-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1874.52 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-21 | 2024-08-09 | 263 | 189 | 2024-08-09 | 2024-11-14 | 98 | 70 | Unknown | Unknown | Unknown | Unknown | 2024-10-30 | 2024-12-06 | 38 | 28 | 2024-11-14 | 2024-11-20 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2025-07-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 62.05 | 62.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-17 | 2025-06-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1046.03 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-17 | 2025-07-09 | 23 | 17 | 2025-07-09 | 2025-06-17 | Unknown | Unknown | 2025-06-17 | 2025-07-15 | 29 | 21 | Unknown | Unknown | Unknown | Unknown | 2025-06-17 | 2025-08-28 | 73 | 53 | Unknown | Unknown | Unknown | Unknown | 2025-08-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CARDIFF | ENCINITAS | 198.05 | 198.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-09 | 2024-10-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1977.07 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-09 | 2024-10-10 | 2 | 2 | 2024-10-10 | 2025-03-14 | 156 | 112 | 2025-03-20 | 2025-03-26 | 7 | 5 | 2025-03-07 | 2025-04-11 | 31 | 23 | 2025-03-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-17 | 2023-02-17 | 2023-04-11 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 691.12 | Unknown | Unknown | Yes | N/A | N/A | 2023-02-17 | 2023-02-17 | 1 | 1 | 2023-02-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-17 | 2023-04-11 | 54 | 38 | Unknown | Unknown | Unknown | Unknown | 2023-04-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-05 | 2024-03-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3309.91 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-05 | 2024-03-05 | 1 | 1 | 2024-03-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-31 | 2024-04-22 | 23 | 16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-25 | 2024-12-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1050.86 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-25 | 2024-12-02 | 8 | 6 | 2024-12-02 | 2024-12-30 | 29 | 21 | 2024-12-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | Chula Vista | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-04 | 2024-09-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1754.11 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-04 | 2024-09-04 | 1 | 1 | 2024-09-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-10 | 2024-04-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 334630 | 15374.88 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-10 | 2024-05-21 | 133 | 95 | 2024-05-21 | 2024-05-29 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-29 | 2025-08-15 | 444 | 318 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LA MESA | COUNTY OF SAN DIEGO-SOUTH of 56 | 180.05 | 180.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-30 | 2023-07-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2022.01 | Unknown | Unknown | Yes | N/A | N/A | 2023-01-30 | 2023-07-17 | 169 | 121 | 2023-07-17 | 2023-10-02 | 78 | 56 | Unknown | Unknown | Unknown | Unknown | 2024-06-11 | 2025-06-10 | 19 | 13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 47.05 | 47.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-13 | 2025-03-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1797.02 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-13 | 2025-03-13 | 1 | 1 | 2025-03-13 | 2025-03-13 | 1 | 1 | 2025-03-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-13 | 2025-07-14 | 124 | 88 | Unknown | Unknown | Unknown | Unknown | 2025-07-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | COUNTY OF SAN DIEGO-NORTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-11 | 2024-02-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 181042 | 63717.99 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-11 | 2024-01-26 | 16 | 12 | 2024-01-26 | 2025-04-01 | 432 | 308 | 2024-04-10 | 2024-11-13 | 51 | 37 | 2024-05-15 | 2025-03-24 | 52 | 38 | 2025-04-01 | 2025-06-24 | 85 | 61 | 2024-10-28 | 2025-06-30 | 246 | 176 | 2025-07-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 54 | 54 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-22 | 2024-10-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 142.83 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-22 | 2024-11-11 | 21 | 15 | 2024-11-11 | 2024-11-12 | 2 | 2 | 2024-11-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-12 | 2025-07-15 | 246 | 176 | Unknown | Unknown | Unknown | Unknown | 2025-07-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-08 | 2024-04-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 912.89 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-08 | 2024-03-07 | Unknown | Unknown | 2024-03-07 | 2024-04-12 | 37 | 27 | 2024-04-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-26 | 2023-07-27 | 2023-07-31 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 513.5 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-26 | 2023-05-23 | Unknown | Unknown | 2023-05-23 | 2023-07-23 | 62 | 44 | 2023-07-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-27 | 2023-07-31 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | 2023-07-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | PALA | N/A | 553 | 553 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-29 | 2025-01-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 21312.55 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-29 | 2024-05-30 | Unknown | Unknown | 2024-05-30 | Unknown | Unknown | Unknown | 2025-03-05 | 2025-03-05 | 1 | 1 | 2025-04-03 | 2025-04-22 | 20 | 14 | Unknown | Unknown | Unknown | Unknown | 2025-07-08 | 2025-07-31 | 24 | 18 | 2025-07-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Residential | N/A | SOLANA BEACH | SOLANA BEACH | 162.4 | 162.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-28 | 2025-02-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2606.47 | 12303.16 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-28 | 2025-02-07 | Unknown | Unknown | 2025-02-07 | 2025-06-12 | 126 | 90 | 2025-05-30 | 2025-06-02 | 4 | 2 | 2025-04-24 | 2025-06-17 | 42 | 30 | 2025-06-18 | Unknown | Unknown | Unknown | 2025-06-18 | 2025-07-15 | 28 | 20 | 2025-07-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-02 | 2024-01-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 576.69 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-02 | 2024-01-19 | 18 | 14 | 2024-01-19 | 2024-01-19 | 1 | 1 | 2024-01-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | N/A | 47.5 | 47.5 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-22 | 2024-08-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1173.98 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-22 | 2024-11-11 | 82 | 58 | 2024-11-11 | 2024-11-11 | 1 | 1 | 2024-11-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | LAKESIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-23 | 2025-01-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 186017 | 16948.97 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-23 | 2025-01-15 | 177 | 127 | 2025-01-15 | 2025-04-24 | 100 | 72 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | COUNTY OF SAN DIEGO-SOUTH of 56 | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-18 | 2025-01-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 958.29 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-18 | 2025-01-03 | 17 | 13 | 2025-01-03 | 2025-01-03 | 1 | 1 | 2025-01-03 | 2025-01-17 | 8 | 6 | 2025-01-09 | 2025-01-27 | 13 | 9 | 2025-01-03 | 2025-07-15 | 194 | 138 | Unknown | Unknown | Unknown | Unknown | 2025-07-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-10 | 2024-04-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1089.29 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-10 | 2024-04-24 | 15 | 11 | 2024-04-24 | 2024-04-24 | 1 | 1 | 2024-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | DANA POINT | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-30 | 2024-05-31 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 39810 | 1885.05 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-30 | 2024-05-31 | 2 | 2 | 2024-05-31 | 2024-05-31 | 1 | 1 | 2024-05-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | RAMONA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-16 | 2024-04-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 618.02 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-16 | 2023-11-14 | Unknown | Unknown | 2023-11-14 | 2024-11-06 | 359 | 257 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-25 | 2025-04-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1010.09 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-25 | 2025-04-25 | 1 | 1 | 2025-04-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-20 | 2023-10-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 643.25 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-20 | 2023-07-07 | Unknown | Unknown | 2023-07-07 | 2023-10-20 | 106 | 76 | 2023-10-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | N/A | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-08-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-03 | 2024-10-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 4662.56 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-03 | 2024-10-03 | 1 | 1 | 2024-10-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-19 | 2025-03-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2232.98 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-19 | 2025-02-20 | 2 | 2 | 2025-02-20 | 2025-03-07 | 16 | 12 | 2025-03-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-07 | 2025-08-15 | 162 | 116 | Unknown | Unknown | Unknown | Unknown | 2025-08-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-02 | 2023-02-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 513416 | 36879.8 | Unknown | Unknown | Yes | N/A | N/A | 2023-02-02 | 2023-02-03 | 2 | 2 | 2023-02-03 | 2024-09-20 | 596 | 426 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-10 | 2025-01-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 29655.41 | 34123.08 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-10 | 2025-01-10 | 1 | 1 | 2025-01-10 | 2025-06-26 | 168 | 120 | 2025-02-28 | 2025-06-24 | 34 | 24 | 2025-02-06 | 2025-07-08 | 44 | 32 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-17 | 2024-04-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1162.06 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-17 | 2024-04-23 | 7 | 5 | 2024-04-23 | 2024-04-23 | 1 | 1 | 2024-04-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | OH | IOU Design | Commercial | Underserved Community | San Diego | SAN DIEGO | 70 | 70 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-20 | 2023-10-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 227774 | 7020.35 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-20 | 2023-08-07 | 19 | 13 | 2023-08-07 | 2024-06-07 | 306 | 220 | 2024-06-06 | 2024-06-06 | 1 | 1 | 2024-01-17 | 2024-06-14 | 18 | 14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 359 | 359 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-06 | 2024-09-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1299.41 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-06 | 2024-08-19 | Unknown | Unknown | 2024-08-19 | 2024-10-08 | 51 | 37 | 2024-10-08 | 2025-05-14 | 219 | 157 | Unknown | Unknown | Unknown | Unknown | 2025-05-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-15 | 2023-09-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 26499.85 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-15 | 2024-03-19 | 187 | 133 | 2024-03-19 | 2025-01-31 | 319 | 229 | 2024-05-17 | 2025-01-30 | 2 | 0 | 2024-06-13 | 2025-02-07 | 41 | 29 | 2025-01-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN JUAN CAPISTRANO | N/A | 39.4 | 39.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-07 | 2025-01-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 991.62 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-07 | 2025-01-02 | Unknown | Unknown | 2025-01-02 | 2025-01-15 | 14 | 10 | 2025-01-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-15 | Unknown | Unknown | Unknown | Unknown | 2025-09-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-06 | 2024-04-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3941 | 624.55 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-06 | 2024-06-12 | 68 | 48 | 2024-06-12 | 2024-06-13 | 2 | 2 | 2024-06-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | ENCINITAS | ENCINITAS | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-15 | 2024-11-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 48830.75 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-15 | 2024-10-15 | 1 | 1 | 2024-10-15 | 2025-08-12 | 302 | 216 | Unknown | Unknown | Unknown | Unknown | 2024-12-13 | 2025-04-22 | 75 | 53 | 2025-08-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN YSIDRO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-23 | 2024-09-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 363154 | 20313.82 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-23 | 2024-09-23 | 1 | 1 | 2024-09-23 | 2024-10-03 | 11 | 9 | 2025-06-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2025-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-20 | 2025-03-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 393623.63 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-20 | 2025-01-29 | Unknown | Unknown | 2025-01-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | LAKESIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-12 | 2023-10-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 67512 | 14118.27 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-12 | 2023-10-12 | 1 | 1 | 2023-10-12 | 2024-05-06 | 208 | 148 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | OH | IOU Design | Residential | Underserved Community | Fallbrook | COUNTY OF SAN DIEGO-NORTH of 56 | 196 | 196 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-04 | 2023-12-01 | 2025-05-13 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2022-04-04 | 2023-11-29 | 605 | 433 | 2023-11-29 | 2025-05-06 | 525 | 375 | 2024-07-25 | 2025-03-27 | 133 | 95 | 2024-08-19 | 2025-04-29 | 38 | 28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-06 | 2024-05-23 | 2024-08-14 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1040.94 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-06 | 2024-04-11 | Unknown | Unknown | 2024-04-11 | 2024-07-02 | 83 | 59 | 2024-07-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-02 | 2024-08-14 | 44 | 32 | Unknown | 2024-07-11 | Unknown | Unknown | 2024-08-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CAMPO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-27 | 2023-09-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1076.68 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-27 | 2023-06-28 | Unknown | Unknown | 2023-06-28 | 2023-09-27 | 92 | 66 | 2023-09-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-15 | 2025-05-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1250.85 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-15 | 2025-05-15 | 1 | 1 | 2025-05-15 | 2025-05-15 | 1 | 1 | 2025-05-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-15 | 2025-07-08 | 55 | 39 | Unknown | Unknown | Unknown | Unknown | 2025-07-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R29/R45 | UG | IOU Design | Commercial | N/A | POWAY | POWAY | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-24 | 2024-04-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 227896.74 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-24 | 2024-09-03 | 377 | 269 | 2024-09-03 | Unknown | Unknown | Unknown | 2024-11-12 | 2025-02-12 | 17 | 13 | 2024-06-11 | 2025-08-05 | 63 | 45 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 3 | 3 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-24 | 2024-06-24 | 2024-08-16 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3885 | 1556.81 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-24 | 2024-02-28 | Unknown | Unknown | 2024-02-28 | 2024-06-24 | 118 | 84 | 2024-06-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-24 | 2024-08-16 | 54 | 40 | Unknown | Unknown | Unknown | Unknown | 2024-08-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 42.05 | 42.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-23 | 2024-12-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1743.18 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-23 | 2024-11-16 | Unknown | Unknown | 2024-11-16 | 2024-12-23 | 38 | 26 | 2024-12-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-23 | 2025-08-15 | 236 | 170 | Unknown | Unknown | Unknown | Unknown | 2025-08-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | 144.05 | 144.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-06 | 2025-01-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3083.56 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-06 | 2024-11-24 | Unknown | Unknown | 2024-11-24 | 2025-02-06 | 75 | 54 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-06 | 2025-07-18 | 163 | 117 | Unknown | 2025-07-23 | Unknown | Unknown | 2025-07-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | FALLBROOK | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-03 | 2025-06-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 1935 | 1158.28 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-03 | 2025-05-30 | Unknown | Unknown | 2025-05-30 | 2025-06-04 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 41.05 | 41.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-24 | 2024-01-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1123.95 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-24 | 2024-04-19 | 87 | 63 | 2024-04-19 | 2024-04-22 | 4 | 2 | 2024-04-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | 7 | 7 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-14 | 2025-03-31 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 990.39 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-14 | 2025-03-31 | 18 | 12 | 2025-03-31 | 2025-03-31 | 1 | 1 | 2025-03-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-31 | Unknown | Unknown | Unknown | Unknown | 2025-07-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-24 | 2024-05-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 429948 | 17332.01 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-24 | 2024-05-24 | 1 | 1 | 2024-05-24 | 2024-10-03 | 133 | 95 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | OH | IOU Design | Residential | N/A | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-03 | 2025-02-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 24408.65 | 28890.31 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-03 | 2024-12-09 | Unknown | Unknown | 2024-12-09 | 2025-05-01 | 144 | 104 | 2025-04-17 | 2025-04-28 | 12 | 8 | 2025-02-20 | 2025-05-07 | 19 | 13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-09 | 2024-10-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 6015.75 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-09 | 2024-10-30 | 22 | 16 | 2024-10-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | LAGUNA NIGUEL | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-10 | 2025-06-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | 566.23 | 137.6 | Unknown | Unknown | Unknown | 428.63 | 0 | 344.44 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-10 | 2025-05-28 | Unknown | Unknown | 2025-05-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-26 | 2025-07-01 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2025-07-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-06 | Unknown | Unknown | No | 2023-02-16 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-16 | 2023-02-16 | Unknown | IOU Designed & Installed | N/A | Yes | 18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 98.41 | Unknown | Unknown | Yes | N/A | N/A | 2023-02-16 | 2023-03-06 | 19 | 13 | 2023-03-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 61.05 | 61.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-15 | 2024-10-15 | 2025-01-30 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1683.03 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-15 | 2024-10-05 | Unknown | Unknown | 2024-10-05 | 2024-10-15 | 11 | 7 | 2024-10-15 | 2025-01-28 | 106 | 76 | Unknown | Unknown | Unknown | Unknown | 2025-01-28 | 2025-01-30 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2025-01-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | FALLBROOK | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-17 | 2023-11-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 46400 | 2092.74 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-17 | 2023-07-10 | Unknown | Unknown | 2023-07-10 | 2024-06-20 | 347 | 249 | Unknown | Unknown | Unknown | Unknown | 2025-08-20 | 2025-08-20 | 1 | 1 | 2024-06-20 | 2025-08-12 | 419 | 299 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | OH | IOU Design | Commercial | N/A | San Juan Capistrano | SAN JUAN CAPISTRANO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-03-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-26 | 2024-08-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 16302.24 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-26 | 2024-11-22 | 120 | 86 | 2024-11-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-10 | 2025-07-11 | 109 | 79 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-08-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | 8 | 8 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-23 | 2024-09-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 15924 | 1552.65 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-23 | 2024-11-07 | 46 | 34 | 2024-11-07 | 2024-11-08 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-10-09 | 2024-11-06 | 29 | 21 | 2024-11-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-29 | 2025-06-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 863.94 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-29 | 2025-06-06 | 9 | 7 | 2025-06-06 | 2025-06-09 | 4 | 2 | 2025-06-09 | 2025-06-11 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2025-06-11 | 2025-07-02 | 22 | 16 | Unknown | 2025-06-30 | Unknown | Unknown | 2025-07-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | 100 | 100 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-05 | 2024-10-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 279.3 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-05 | 2024-10-24 | 81 | 59 | 2024-10-24 | 2024-10-24 | 1 | 1 | 2024-10-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ALPINE | N/A | 87.05 | 87.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-12 | 2024-08-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1231.32 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-12 | 2024-09-05 | 25 | 19 | 2024-09-05 | 2024-09-05 | 1 | 1 | 2024-09-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-05 | 2025-08-01 | 331 | 237 | Unknown | 2025-07-17 | Unknown | Unknown | 2025-08-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | 34.05 | 34.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-06 | 2024-09-06 | 2025-06-25 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 6000 | 1980.38 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-06 | 2024-09-09 | 4 | 2 | 2024-09-09 | 2024-11-27 | 80 | 58 | Unknown | Unknown | Unknown | Unknown | 2024-11-08 | 2024-12-12 | 35 | 25 | 2024-11-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | BORREGO SPRINGS | COUNTY OF SAN DIEGO-NORTH of 56 | 19 | 19 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-20 | 2025-03-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1760.51 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-20 | 2025-03-20 | 1 | 1 | 2025-03-20 | 2025-04-04 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | 2025-03-21 | 2025-03-28 | 8 | 6 | 2025-04-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | 131.05 | 131.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-19 | 2023-09-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 10900 | 4080.48 | Unknown | Unknown | Yes | N/A | N/A | 2023-04-19 | 2023-05-17 | 29 | 21 | 2023-05-17 | 2024-02-07 | 267 | 191 | 2023-09-13 | 2024-02-05 | 2 | 2 | 2023-12-13 | 2024-02-26 | 27 | 19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-09 | 2025-01-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 9150 | 525.43 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-09 | 2024-10-22 | Unknown | Unknown | 2024-10-22 | 2025-01-09 | 80 | 58 | 2025-01-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-26 | 2024-11-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3241 | 507.91 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-26 | 2024-09-09 | Unknown | Unknown | 2024-09-09 | 2024-11-26 | 79 | 57 | 2024-11-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | 93.05 | 93.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-26 | 2023-01-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 98.41 | Unknown | Unknown | Yes | N/A | N/A | 2023-01-26 | 2023-03-09 | 43 | 31 | 2023-03-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 96.05 | 96.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-01 | 2024-08-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2038.39 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-01 | 2024-08-08 | 8 | 6 | 2024-08-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 109 | 109 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-03-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-31 | 2023-05-31 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 148.62 | Unknown | Unknown | Yes | N/A | N/A | 2023-05-31 | 2023-06-08 | 9 | 7 | 2023-06-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-01 | 2025-05-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1387.33 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-01 | 2025-05-01 | 1 | 1 | 2025-05-01 | 2025-05-01 | 1 | 1 | 2025-05-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-01 | 2025-08-07 | 99 | 71 | Unknown | Unknown | Unknown | Unknown | 2025-08-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | NATIONAL CITY | 406.05 | 406.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-27 | 2024-09-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7962 | 1356.04 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-27 | 2024-08-28 | Unknown | Unknown | 2024-08-28 | 2025-05-06 | 252 | 180 | Unknown | Unknown | Unknown | Unknown | 2025-02-14 | 2025-06-12 | 119 | 85 | 2025-05-06 | 2025-08-26 | 113 | 81 | Unknown | 2025-08-06 | Unknown | Unknown | 2025-08-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R29/R45 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | OCEANSIDE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-02 | 2023-11-27 | 2025-04-25 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 233313.69 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-02 | 2024-07-01 | 274 | 196 | 2024-07-01 | 2025-03-27 | 270 | 194 | 2024-09-24 | 2025-01-17 | 37 | 29 | 2024-11-09 | 2025-07-24 | 242 | 172 | 2025-03-27 | 2025-07-10 | 106 | 76 | 2025-05-21 | 2025-07-14 | 55 | 39 | 2025-04-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-05 | 2024-04-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 21900.19 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-05 | 2024-03-27 | 52 | 38 | 2024-03-27 | 2025-02-20 | 331 | 237 | 2024-04-29 | 2024-04-29 | 1 | 1 | 2025-01-29 | 2025-03-28 | 30 | 22 | 2025-02-20 | Unknown | Unknown | Unknown | 2025-05-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-11 | 2023-04-11 | 2024-01-29 | IOU Designed & Installed | N/A | No | Unknown | 5989.14 | 1238.7 | Unknown | 151.83 | Unknown | 4598.61 | 0 | 697.32 | Unknown | Unknown | Yes | N/A | N/A | 2023-04-11 | 2023-05-23 | 43 | 31 | 2023-05-23 | 2023-10-19 | 150 | 108 | 2023-10-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-23 | 2024-01-29 | 252 | 180 | Unknown | Unknown | Unknown | Unknown | 2024-01-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-24 |  | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 197.01 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-24 | 2024-09-09 | Unknown | Unknown | 2024-09-09 | 2024-10-01 | 23 | 17 | 2024-10-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-01 | 2025-07-10 | 283 | 203 | Unknown | Unknown | Unknown | Unknown | 2025-07-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | OH | IOU Design | Residential | Underserved Community | San Diego | SAN DIEGO | 326863 | 326863 | Not Available | >2MW | No | N/A | N/A | N/A | 2025-02-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-19 | 2024-09-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 11293 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-19 | 2024-08-06 | Unknown | Unknown | 2024-08-06 | 2025-06-23 | 322 | 230 | 2025-05-08 | 2025-06-23 | 10 | 6 | 2025-05-07 | 2025-07-03 | 31 | 23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-07-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-29 | 2023-09-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 765.87 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-29 | 2023-07-14 | Unknown | Unknown | 2023-07-14 | 2023-10-13 | 92 | 66 | 2023-10-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | ENCINITAS | ENCINITAS | 39 | 39 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-17 | 2024-06-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1686.09 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-17 | 2024-06-17 | 1 | 1 | 2024-06-17 | 2024-06-20 | 4 | 4 | 2024-06-20 | Unknown | Unknown | Unknown | 2024-06-20 | 2024-07-25 | 36 | 26 | 2024-06-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-18 | 2025-04-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1785.48 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-18 | 2025-04-16 | Unknown | Unknown | 2025-04-16 | 2025-04-22 | 7 | 5 | 2025-04-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 44.05 | 44.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-18 | 2024-11-19 | 2024-12-17 | IOU Designed & Installed | N/A | No | Unknown | 17.62 | 0 | Unknown | Unknown | Unknown | 17.62 | 3981 | 1718.9 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-18 | 2024-10-31 | Unknown | Unknown | 2024-10-31 | 2024-11-20 | 21 | 15 | 2024-11-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-19 | 2024-12-17 | 29 | 21 | Unknown | Unknown | Unknown | Unknown | 2024-12-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | JULIAN | N/A | 26 | 26 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-02 | Unknown | Unknown | No | 2024-06-14 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-14 | 2024-06-27 | Unknown | IOU Designed & Installed | N/A | Yes | 143 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 853.36 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-14 | 2024-11-01 | 141 | 101 | 2024-11-01 | 2024-11-26 | 26 | 18 | 2024-11-26 | Unknown | Unknown | Unknown | 2025-01-03 | 2025-01-03 | 1 | 1 | 2024-07-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-29 | 2024-05-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1474.62 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-29 | 2024-05-29 | 1 | 1 | 2024-05-29 | 2024-05-29 | 1 | 1 | 2024-05-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-22 | 2024-05-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 6314.93 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-22 | 2024-08-12 | 83 | 59 | 2024-08-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 135.2 | 135.2 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-21 | 2025-03-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1858.75 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-21 | 2025-04-24 | 35 | 25 | 2025-04-24 | 2025-04-24 | 1 | 1 | 2025-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-24 | 2025-08-26 | 125 | 89 | Unknown | 2025-08-26 | Unknown | Unknown | 2025-08-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2018-01-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-24 | 2025-04-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 794.39 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-24 | 2025-04-23 | Unknown | Unknown | 2025-04-23 | 2025-04-24 | 2 | 2 | 2025-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-08 | 2024-07-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3199.97 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-08 | 2024-07-08 | 1 | 1 | 2024-07-08 | 2024-07-08 | 1 | 1 | 2024-07-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-03 | 2024-12-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1247.58 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-03 | 2025-03-19 | 107 | 77 | 2025-03-19 | 2025-03-19 | 1 | 1 | 2025-03-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-19 | 2025-08-28 | 163 | 117 | Unknown | Unknown | Unknown | Unknown | 2025-08-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Commercial | N/A | San Diego | COUNTY OF SAN DIEGO-NORTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-16 | 2023-05-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 441346 | 12985.45 | Unknown | Unknown | Yes | N/A | N/A | 2023-05-16 | 2023-05-16 | 1 | 1 | 2023-05-16 | 2025-05-29 | 745 | 533 | 2024-11-12 | 2025-05-16 | 12 | 10 | 2024-10-10 | 2025-06-04 | 80 | 56 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | OH | IOU Design | Residential | N/A | Coronado | CORONADO | 1937 | 1937 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2023-08-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-14 | 2024-01-26 | 2024-04-01 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 4571.32 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-14 | 2024-03-05 | 113 | 81 | 2024-03-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-09 | 2024-03-21 | 12 | 10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2021-09-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-23 | 2023-10-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 858.66 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-23 | 2023-09-19 | 28 | 20 | 2023-09-19 | 2024-07-11 | 297 | 213 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-11 | Unknown | Unknown | Unknown | Unknown | 2025-06-27 | Unknown | Unknown | 2025-07-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | Applicant Design | Commercial | Disadvantaged Community,Underserved Community,Tribal Community | EL CAJON | COUNTY OF SAN DIEGO-SOUTH of 56, EL CAJON | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-19 | 2024-03-19 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 92029.06 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-19 | 2024-10-23 | 219 | 157 | 2024-10-23 | 2025-02-13 | 114 | 82 | 2024-11-07 | 2025-05-22 | 178 | 124 | 2024-12-06 | 2025-05-28 | 61 | 43 | 2025-02-13 | 2025-07-17 | 155 | 111 | 2025-02-27 | 2025-07-25 | 149 | 107 | 2025-08-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-02 | 2024-10-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 6006.35 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-02 | 2024-10-02 | 1 | 1 | 2024-10-02 | 2025-05-01 | 212 | 152 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-01 | 2025-09-04 | 127 | 91 | Unknown | 2025-09-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | RAMONA | N/A | 101.05 | 101.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-29 | 2025-02-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3600 | 2174.13 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-29 | 2025-01-29 | 1 | 1 | 2025-01-29 | 2025-02-25 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R29/R45 | Both | IOU Design | Commercial | Underserved Community | BORREGO SPRINGS | COUNTY OF SAN DIEGO-NORTH of 56 | 400 | 400 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-12 | 2024-12-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 140586.48 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-12 | 2025-03-11 | 181 | 129 | 2025-03-11 | Unknown | Unknown | Unknown | 2025-04-16 | 2025-04-16 | 1 | 1 | 2025-05-06 | 2025-07-09 | 63 | 43 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-01 | 2025-06-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1420.2 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-01 | 2025-06-13 | 44 | 32 | 2025-06-13 | 2025-06-13 | 1 | 1 | 2025-06-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | PINE VALLEY | COUNTY OF SAN DIEGO-SOUTH of 56 | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-27 | 2024-06-27 | 2024-12-20 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1510.95 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-27 | 2024-05-22 | Unknown | Unknown | 2024-05-22 | 2024-06-27 | 37 | 27 | 2024-06-27 | Unknown | Unknown | Unknown | 2024-12-04 | 2024-12-10 | 7 | 5 | 2024-08-19 | 2024-12-20 | 124 | 90 | Unknown | Unknown | Unknown | Unknown | 2024-12-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-11 | 2024-12-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1726.3 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-11 | 2024-12-10 | Unknown | Unknown | 2024-12-10 | 2024-12-11 | 2 | 2 | 2024-12-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-22 | 2024-12-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 9150 | 1050.86 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-22 | 2024-11-01 | Unknown | Unknown | 2024-11-01 | 2024-12-20 | 50 | 36 | 2024-12-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | Underserved Community | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-03 | 2023-04-03 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 509487 | 91038.52 | Unknown | Unknown | Yes | N/A | N/A | 2023-04-03 | 2024-01-23 | 296 | 212 | 2024-01-23 | 2024-09-05 | 227 | 163 | 2024-01-30 | 2024-08-29 | 74 | 54 | 2024-03-12 | 2024-09-19 | 40 | 30 | 2025-02-03 | Unknown | Unknown | Unknown | 2025-02-03 | 2025-08-13 | 192 | 138 | 2025-07-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | 5.4 | 5.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-04 | 2025-03-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2157.75 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-04 | 2025-03-04 | 1 | 1 | 2025-03-04 | 2025-03-21 | 18 | 14 | 2025-03-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CAPISTRANO BEACH | N/A | 65.05 | 65.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-24 | 2024-07-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2579.58 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-24 | 2024-10-18 | 87 | 63 | 2024-10-18 | 2024-10-21 | 4 | 2 | 2024-10-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Residential | N/A | DEL MAR | SAN DIEGO | 141.1 | 141.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-24 | 2025-02-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 37287.24 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-24 | 2025-01-24 | 1 | 1 | 2025-01-24 | 2025-05-15 | 112 | 80 | 2025-02-06 | 2025-05-13 | 11 | 9 | 2025-03-13 | 2025-05-07 | 33 | 23 | 2025-05-22 | 2025-07-09 | 49 | 35 | 2025-05-22 | 2025-06-30 | 40 | 28 | 2025-07-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-13 | 2023-10-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1262.11 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-13 | 2024-07-31 | 293 | 209 | 2024-07-31 | 2024-08-19 | 20 | 14 | 2024-08-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | N/A | Valley Center | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-07 | 2024-11-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1125.76 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-07 | 2024-11-05 | Unknown | Unknown | 2024-11-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-14 | 2025-04-14 | 2025-04-24 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3092.19 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-14 | 2025-04-14 | 1 | 1 | 2025-04-14 | 2025-04-14 | 1 | 1 | 2025-04-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-14 | 2025-04-24 | 11 | 9 | Unknown | Unknown | Unknown | Unknown | 2025-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN MARCOS | SAN MARCOS | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-27 | 2025-05-27 | 2025-06-23 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1111.8 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-27 | 2025-05-27 | 1 | 1 | 2025-05-27 | 2025-05-27 | 1 | 1 | 2025-05-27 | Unknown | Unknown | Unknown | 2025-05-27 | 2025-06-17 | 22 | 16 | 2025-05-27 | 2025-06-23 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | 2025-06-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | DEL MAR | 141.15 | 141.15 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-17 | 2024-01-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 4481.05 | Unknown | Unknown | Yes | N/A | N/A | 2022-05-17 | 2023-04-19 | 338 | 242 | 2023-04-19 | 2024-01-11 | 268 | 192 | 2023-10-30 | 2025-02-20 | 18 | 14 | 2024-01-12 | 2025-02-25 | 72 | 52 | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-08-19 | Unknown | Unknown | 2025-08-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | Applicant Design | Commercial | Underserved Community | SAN YSIDRO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-08 | 2024-10-08 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 130156 | 5429.86 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-08 | 2024-11-30 | 54 | 39 | 2024-11-30 | 2024-12-13 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 31.35 | 31.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-18 | 2025-03-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7882 | 250.9 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-18 | 2025-04-07 | 21 | 15 | 2025-04-07 | 2025-05-08 | 32 | 24 | 2025-05-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-11 | 2023-09-11 | 2023-10-04 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 154.99 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-11 | 2023-06-21 | Unknown | Unknown | 2023-06-21 | 2023-09-29 | 101 | 73 | 2023-09-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-29 | 2023-10-04 | 6 | 4 | Unknown | 2023-10-03 | Unknown | Unknown | 2023-10-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 17 | 17 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-03 | 2024-06-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1085.17 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-03 | 2024-04-02 | Unknown | Unknown | 2024-04-02 | 2024-06-20 | 80 | 58 | 2024-06-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | Underserved Community | RA 1153-E7 CREEKSD XING RELOC (E) | COUNTY OF SAN DIEGO-NORTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-07 | 2024-03-07 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 54669.74 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-07 | 2024-06-25 | 111 | 79 | 2024-06-25 | 2025-01-29 | 219 | 157 | 2024-07-03 | 2024-09-17 | 77 | 55 | 2024-08-14 | 2025-02-05 | 18 | 14 | 2025-01-31 | Unknown | Unknown | Unknown | 2025-01-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-28 | 2024-11-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 4029.28 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-28 | 2024-11-25 | 182 | 130 | 2024-11-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | CARLSBAD | CARLSBAD | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-08-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-05 | 2023-09-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3754 | 391 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-05 | 2023-04-18 | Unknown | Unknown | 2023-04-18 | 2023-09-15 | 151 | 109 | 2023-09-15 | Unknown | Unknown | Unknown | 2023-10-26 | 2023-12-08 | 44 | 32 | 2023-09-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | ALPINE | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2024-12-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-22 | 2024-05-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3375.42 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-22 | 2024-05-22 | 1 | 1 | 2024-05-22 | 2024-05-24 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-16 | 2024-08-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1514.12 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-16 | 2024-06-24 | Unknown | Unknown | 2024-06-24 | 2024-08-19 | 57 | 41 | 2024-08-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-05 | 2025-03-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 6923.28 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-05 | 2025-03-05 | 1 | 1 | 2025-03-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | N/A | 1299.05 | 1299.05 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2025-09-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-30 | 2025-04-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2472.03 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-30 | 2025-05-27 | 28 | 20 | 2025-05-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | POWAY | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-03 | 2025-02-03 | 2025-03-13 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1297.75 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-03 | 2025-02-14 | 12 | 10 | 2025-02-14 | 2025-03-11 | 26 | 18 | 2025-03-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-11 | 2025-03-13 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2025-03-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 222214 | 222214 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-03-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-11 | 2024-03-11 | 2024-12-16 | IOU Designed & Installed | N/A | No | Unknown | 892.72 | 0 | Unknown | Unknown | 83.72 | 809 | 0 | 326.9 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-11 | 2024-03-11 | 1 | 1 | 2024-03-11 | 2024-04-29 | 50 | 36 | Unknown | Unknown | Unknown | Unknown | 2024-07-31 | 2024-10-14 | 76 | 54 | 2024-04-29 | 2024-12-12 | 228 | 164 | Unknown | 2024-10-17 | Unknown | Unknown | 2024-12-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-21 | 2024-11-21 | 2025-03-26 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1411.69 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-21 | 2025-01-23 | 64 | 46 | 2025-01-23 | 2025-01-24 | 2 | 2 | 2025-01-24 | 2025-02-10 | 18 | 12 | Unknown | Unknown | Unknown | Unknown | 2025-02-10 | 2025-03-26 | 45 | 33 | Unknown | 2025-02-28 | Unknown | Unknown | 2025-03-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 181.05 | 181.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-19 | 2024-07-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3941 | 1467.71 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-19 | 2024-06-10 | Unknown | Unknown | 2024-06-10 | 2024-07-19 | 40 | 30 | 2024-07-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | Both | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-13 | 2024-05-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 4294.89 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-13 | 2024-05-13 | 1 | 1 | 2024-05-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 31 | 31 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-23 | 2024-07-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1424.45 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-23 | 2024-08-07 | 16 | 12 | 2024-08-07 | 2024-08-08 | 2 | 2 | 2024-08-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-23 | 2025-05-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1272.67 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-23 | 2025-05-23 | 1 | 1 | 2025-05-23 | 2025-05-23 | 1 | 1 | 2025-05-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-23 | 2025-07-14 | 53 | 37 | Unknown | Unknown | Unknown | Unknown | 2025-07-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 242.15 | 242.15 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-05 | 2025-03-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 3657.95 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-05 | 2025-03-05 | 1 | 1 | 2025-03-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-09-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | 282 | 282 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-06 | 2024-06-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 179320 | 18096.56 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-06 | 2023-02-16 | Unknown | Unknown | 2023-02-16 | 2025-06-10 | 846 | 604 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | VALLEY CENTER | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-21 | 2025-04-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1724.18 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-21 | 2025-03-27 | Unknown | Unknown | 2025-03-27 | 2025-04-21 | 26 | 18 | 2025-04-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-21 | 2025-07-10 | 81 | 59 | Unknown | Unknown | Unknown | Unknown | 2025-07-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN YSIDRO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-21 | 2024-11-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 4009.05 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-21 | 2024-11-18 | Unknown | Unknown | 2024-11-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-16 | 2024-04-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 553.02 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-16 | 2024-04-17 | 2 | 2 | 2024-04-17 | 2025-01-07 | 266 | 190 | Unknown | Unknown | Unknown | Unknown | 2024-04-18 | 2024-05-14 | 27 | 19 | 2025-01-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 10 | 10 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-19 | 2025-05-30 | 2025-06-09 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1383.65 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-19 | 2025-05-20 | 2 | 2 | 2025-05-20 | 2025-05-30 | 11 | 9 | 2025-05-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-30 | 2025-06-09 | 11 | 7 | Unknown | Unknown | Unknown | Unknown | 2025-06-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN MARCOS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-17 | 2025-01-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2854.33 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-17 | 2025-01-13 | Unknown | Unknown | 2025-01-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-02 | 2025-04-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1700.33 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-02 | 2025-02-20 | Unknown | Unknown | 2025-02-20 | 2025-04-02 | 42 | 30 | 2025-04-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | CARLSBAD | N/A | 5 | 5 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-10 | 2025-03-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2136.17 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-10 | 2025-04-03 | 25 | 19 | 2025-04-03 | 2025-04-10 | 8 | 6 | 2025-04-10 | Unknown | Unknown | Unknown | 2025-06-20 | 2025-06-20 | 1 | 1 | 2025-04-10 | 2025-07-24 | 106 | 76 | Unknown | 2025-07-17 | Unknown | Unknown | 2025-07-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 3646.05 | 3646.05 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-06-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-23 | 2024-08-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1139.07 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-23 | 2024-08-28 | 98 | 70 | 2024-08-28 | 2024-10-03 | 37 | 27 | Unknown | Unknown | Unknown | Unknown | 2024-06-12 | 2024-07-12 | 31 | 23 | 2024-10-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 42.05 | 42.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-05 | 2024-11-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1542.75 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-05 | 2024-11-14 | 10 | 8 | 2024-11-14 | 2024-11-14 | 1 | 1 | 2024-11-14 | 2025-02-11 | 90 | 64 | Unknown | Unknown | Unknown | Unknown | 2025-02-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | Applicant Design | Residential | N/A | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-17 | 2022-09-28 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 613971.12 | 98488.72 | Unknown | Unknown | Yes | N/A | N/A | 2022-08-17 | 2023-04-12 | 239 | 171 | 2023-04-12 | 2024-08-07 | 484 | 346 | 2023-04-13 | 2024-07-01 | 423 | 301 | 2024-08-06 | 2024-08-20 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 7 | 7 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-05 | 2025-06-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7962 | 747.14 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-05 | 2025-06-05 | 1 | 1 | 2025-06-05 | 2025-06-26 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | 2025-06-11 | 2025-06-25 | 15 | 11 | 2025-06-26 | 2025-07-03 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2025-07-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-22 | 2023-08-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 594.99 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-22 | 2023-12-05 | 106 | 76 | 2023-12-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-26 | 2023-10-03 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | N/A | 251.15 | 251.15 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-28 | 2023-03-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | 1726.94 | 0 | Unknown | Unknown | 206.66 | 1520.28 | 3981 | 1617.76 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-28 | 2023-05-15 | 49 | 35 | 2023-05-15 | 2023-07-25 | 72 | 52 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-25 | 2024-10-03 | 437 | 313 | Unknown | 2024-10-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-07 | 2025-02-07 | 2025-02-10 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1547.8 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-07 | 2025-02-07 | 1 | 1 | 2025-02-07 | 2025-02-07 | 1 | 1 | 2025-02-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-07 | 2025-02-10 | 4 | 2 | Unknown | Unknown | Unknown | Unknown | 2025-02-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | LA MESA | N/A | 38 | 38 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-25 | 2024-12-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1754.03 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-25 | 2024-12-25 | 1 | 1 | 2024-12-25 | 2024-12-25 | 1 | 1 | 2024-12-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-09 | 2024-12-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1203 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-09 | 2025-01-15 | 38 | 28 | 2025-01-15 | 2025-01-15 | 1 | 1 | 2025-01-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-19 | 2024-11-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1066.51 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-19 | 2024-09-09 | Unknown | Unknown | 2024-09-09 | 2024-11-12 | 65 | 47 | Unknown | Unknown | Unknown | Unknown | 2024-10-31 | 2024-12-06 | 37 | 27 | 2024-11-12 | 2025-07-15 | 246 | 176 | Unknown | 2024-12-18 | Unknown | Unknown | 2025-07-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | 50.05 | 50.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-19 | 2024-03-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1134.67 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-19 | 2024-01-17 | Unknown | Unknown | 2024-01-17 | 2024-03-21 | 65 | 47 | 2024-03-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-21 | 2025-08-01 | 499 | 357 | Unknown | Unknown | Unknown | Unknown | 2025-08-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-10 | 2025-03-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | 446.84 | 0 | Unknown | Unknown | Unknown | 446.84 | 0 | 696.35 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-10 | 2025-03-24 | 15 | 11 | 2025-03-24 | 2025-04-10 | 18 | 14 | 2025-04-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-10 | 2025-07-08 | 90 | 64 | Unknown | Unknown | Unknown | Unknown | 2025-07-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | DULZURA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-13 | 2024-10-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 36349.88 | 4534.17 | Unknown | Unknown | Yes | N/A | N/A | 2023-01-13 | 2024-11-21 | 679 | 485 | 2024-11-21 | 2025-02-27 | 99 | 71 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-10 | 2024-10-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1205.55 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-10 | 2024-09-19 | Unknown | Unknown | 2024-09-19 | 2024-11-08 | 51 | 37 | 2024-11-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | BONITA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-09 | 2024-10-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2949.59 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-09 | 2024-09-09 | 1 | 1 | 2024-09-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-21 | Unknown | Unknown | Unknown | Unknown | 2025-08-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | ESCONDIDO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2017-10-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-11 | 2024-11-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3660 | 1050.78 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-11 | 2024-11-11 | 1 | 1 | 2024-11-11 | 2024-11-11 | 1 | 1 | 2024-11-11 | Unknown | Unknown | Unknown | 2024-11-11 | 2024-11-21 | 11 | 9 | 2024-11-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | National City | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2020-12-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-29 | 2025-01-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2025-01-29 | 2025-01-29 | 1 | 1 | 2025-01-29 | 2025-02-21 | 24 | 18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-15 | 2024-05-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3241 | 618.21 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-15 | 2024-05-15 | 1 | 1 | 2024-05-15 | 2024-05-15 | 1 | 1 | 2024-05-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 58 | 58 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-22 | 2025-04-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1387.33 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-22 | 2025-04-23 | 2 | 2 | 2025-04-23 | 2025-04-23 | 1 | 1 | 2025-04-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 38.05 | 38.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-01-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-05 | 2025-03-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 15924 | 1357.95 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-05 | 2024-09-24 | Unknown | Unknown | 2024-09-24 | 2025-03-17 | 175 | 125 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-27 | 2023-02-27 | 2023-04-27 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 153.75 | Unknown | Unknown | Yes | N/A | N/A | 2023-02-27 | 2023-04-26 | 59 | 43 | 2023-04-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-26 | 2023-04-27 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2023-04-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | IOU Design | Commercial | N/A | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-07 | 2024-02-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 21331.37 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-07 | 2024-02-09 | 3 | 3 | 2024-02-09 | 2024-09-17 | 222 | 158 | Unknown | Unknown | Unknown | Unknown | 2024-09-13 | 2024-11-01 | 23 | 15 | 2024-09-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-09 | 2024-07-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1694.01 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-09 | 2024-07-19 | 11 | 9 | 2024-07-19 | 2024-07-19 | 1 | 1 | 2024-07-19 | 2025-03-31 | 256 | 182 | Unknown | Unknown | Unknown | Unknown | 2025-04-08 | 2025-07-18 | 102 | 74 | Unknown | 2025-07-09 | Unknown | Unknown | 2025-07-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | 80.2 | 80.2 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-16 | 2025-06-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 993.58 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-16 | 2025-06-16 | 1 | 1 | 2025-06-16 | 2025-06-20 | 5 | 5 | Unknown | Unknown | Unknown | Unknown | 2025-06-19 | 2025-06-27 | 9 | 7 | 2025-06-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-22 | 2024-12-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 9150 | 1050.86 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-22 | 2024-11-01 | Unknown | Unknown | 2024-11-01 | 2024-12-20 | 50 | 36 | 2024-12-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 80.2 | 80.2 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-21 | 2024-03-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 885.11 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-21 | 2024-01-11 | Unknown | Unknown | 2024-01-11 | 2024-03-11 | 61 | 43 | 2024-03-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 399 | 399 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-10-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-13 | 2024-11-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 27460 | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2024-11-13 | 2024-11-14 | 2 | 2 | 2024-11-14 | 2025-02-25 | 104 | 74 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-25 | 2025-08-28 | 185 | 133 | 2025-08-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-05 | 2025-03-06 | 2025-04-14 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1699.48 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-05 | 2025-03-05 | 1 | 1 | 2025-03-05 | 2025-03-05 | 1 | 1 | 2025-03-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-06 | 2025-04-14 | 40 | 28 | Unknown | Unknown | Unknown | Unknown | 2025-04-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | Applicant Design | Commercial | Underserved Community | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-15 | 2024-02-15 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 478659 | 39798.76 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-15 | 2024-10-10 | 239 | 171 | 2024-10-10 | 2024-12-13 | 65 | 47 | Unknown | Unknown | Unknown | Unknown | 2024-08-27 | 2024-12-19 | 74 | 54 | 2024-12-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CHULA VISTA | N/A | 95.05 | 95.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-14 | 2025-05-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 118.25 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-14 | 2025-05-06 | Unknown | Unknown | 2025-05-06 | 2025-07-01 | 57 | 41 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-07-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | 136 | 136 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-09 | 2025-02-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1840.91 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-09 | 2025-04-17 | 221 | 159 | 2025-04-17 | 2025-04-17 | 1 | 1 | 2025-04-17 | 2025-06-20 | 65 | 47 | Unknown | Unknown | Unknown | Unknown | 2025-06-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | 107.05 | 107.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-04 | 2025-05-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 23880.68 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-04 | 2024-09-04 | 1 | 1 | 2024-09-04 | 2025-06-19 | 289 | 207 | 2025-05-16 | 2025-05-28 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2025-06-19 | Unknown | Unknown | Unknown | 2025-07-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | Applicant Design | Residential | Underserved Community | SM 1128-H1 N.CITY PA7 (E) | SM 1128-H1 N.CITY PA7 (E) | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-27 | 2024-08-27 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 108455 | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2024-08-27 | 2024-08-23 | Unknown | Unknown | 2024-08-23 | 2025-05-01 | 252 | 180 | Unknown | Unknown | Unknown | Unknown | 2024-09-19 | 2025-07-03 | 105 | 75 | 2025-05-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | Disadvantaged Community,Underserved Community | Chula Vista | CHULA VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-09 | 2023-11-09 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 186585 | 152479.93 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-09 | 2024-10-28 | 355 | 253 | 2024-10-28 | 2025-03-18 | 142 | 102 | 2024-11-07 | 2025-08-01 | 34 | 25 | 2025-03-03 | 2025-04-25 | 48 | 36 | 2025-07-02 | Unknown | Unknown | Unknown | 2025-07-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SANTEE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-01 | 2025-05-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1027.74 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-01 | 2025-04-29 | Unknown | Unknown | 2025-04-29 | 2025-05-01 | 3 | 3 | 2025-05-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-01 | 2025-08-18 | 110 | 78 | Unknown | Unknown | Unknown | Unknown | 2025-08-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Commercial | Underserved Community | IMPERIAL BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-18 | Unknown | Unknown | No | 2022-11-18 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-18 | 2023-04-27 | Unknown | IOU Designed & Installed | N/A | Yes | 164 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2720.46 | Unknown | Unknown | Yes | N/A | N/A | 2022-11-18 | 2023-05-01 | 165 | 117 | 2023-05-01 | 2023-09-06 | 129 | 93 | 2023-04-27 | 2023-08-29 | 86 | 62 | 2023-09-05 | Unknown | Unknown | Unknown | 2025-05-15 | Unknown | Unknown | Unknown | 2025-05-15 | 2025-08-18 | 96 | 68 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-08-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-11 | 2024-01-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 38972 | 4041.67 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-11 | 2023-12-26 | 16 | 12 | 2023-12-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | DANA POINT | N/A | 9.05 | 9.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-06-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-26 | 2025-06-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1470.01 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-26 | 2025-06-17 | Unknown | Unknown | 2025-06-17 | 2025-06-27 | 11 | 9 | 2025-06-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2027-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-22 | 2023-09-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 493644 | 34527.18 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-22 | 2023-10-05 | 14 | 10 | 2023-10-05 | 2023-10-17 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-07 | 2023-09-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 932.32 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-07 | 2023-09-07 | 1 | 1 | 2023-09-07 | 2023-09-07 | 1 | 1 | 2023-09-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-07 | 2023-12-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3661.75 | 616.14 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-07 | 2023-08-08 | Unknown | Unknown | 2023-08-08 | 2023-12-20 | 135 | 97 | 2023-12-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 104.05 | 104.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-23 | 2023-08-23 | 2024-07-25 | IOU Designed & Installed | N/A | No | Unknown | 1234.24 | -15.92 | Unknown | Unknown | 203.94 | 1046.22 | 3981 | 1044.32 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-23 | 2023-08-31 | 9 | 7 | 2023-08-31 | 2023-11-03 | 65 | 47 | 2023-11-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-16 | 2024-07-25 | 253 | 181 | Unknown | 2024-04-24 | Unknown | Unknown | 2024-07-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | EL CAJON | N/A | 1.35 | 1.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-07 | 2023-07-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 563.03 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-07 | 2023-05-08 | Unknown | Unknown | 2023-05-08 | 2023-07-25 | 79 | 57 | 2023-07-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-07 | 2023-04-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 731.92 | Unknown | Unknown | Yes | N/A | N/A | 2023-04-07 | 2023-04-07 | 1 | 1 | 2023-04-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-07 | 2023-12-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 163.83 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-07 | 2024-01-29 | 84 | 60 | 2024-01-29 | 2024-02-05 | 8 | 6 | 2024-02-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SOLANA BEACH | SOLANA BEACH | 162.4 | 162.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-14 | 2025-01-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1098.24 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-14 | 2025-02-07 | 25 | 19 | 2025-02-07 | 2025-06-03 | 117 | 83 | Unknown | Unknown | Unknown | Unknown | 2025-04-24 | 2025-05-22 | 29 | 21 | 2025-06-03 | Unknown | Unknown | Unknown | Unknown | 2025-07-15 | Unknown | Unknown | 2025-07-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 120.7 | 120.7 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-12 | 2025-05-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 670.11 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-12 | 2025-05-22 | 162 | 116 | 2025-05-22 | 2025-06-05 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2025-05-22 | 2025-06-06 | 16 | 12 | 2025-06-05 | 2025-06-17 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2025-07-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | Underserved Community | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-20 | 2023-09-20 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 176562 | 37498.38 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-20 | 2024-01-23 | 126 | 90 | 2024-01-23 | 2024-06-28 | 158 | 114 | 2024-01-23 | Unknown | Unknown | Unknown | 2024-04-03 | 2024-07-10 | 47 | 33 | 2024-07-17 | Unknown | Unknown | Unknown | 2024-07-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2018-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-22 | 2023-05-31 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 71.28 | Unknown | Unknown | Yes | N/A | N/A | 2023-05-22 | 2023-05-31 | 10 | 8 | 2023-05-31 | 2023-08-24 | 86 | 62 | Unknown | Unknown | Unknown | Unknown | 2023-05-31 | 2023-06-14 | 15 | 11 | 2023-08-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | oc 1086-C6 (E) | oc 1086-C6 (E) | 14670 | 14670 | Not Available | >2MW | No | N/A | N/A | N/A | 2025-04-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-28 | 2024-06-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 36055.44 | 24241.11 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-28 | 2023-09-05 | Unknown | Unknown | 2023-09-05 | 2024-12-18 | 471 | 337 | 2024-10-15 | 2025-08-01 | 243 | 175 | 2024-11-15 | 2025-08-05 | 44 | 30 | 2024-12-18 | Unknown | Unknown | Unknown | 2025-01-27 | 2025-07-31 | 186 | 134 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-15 | 2024-07-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 837.68 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-15 | 2024-09-15 | 124 | 88 | 2024-09-15 | 2024-09-18 | 4 | 3 | 2024-09-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-08 | 2024-05-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7320 | 584.27 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-08 | 2024-02-26 | Unknown | Unknown | 2024-02-26 | 2024-05-08 | 73 | 53 | 2024-05-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-08 | 2025-08-14 | 464 | 332 | Unknown | Unknown | Unknown | Unknown | 2025-08-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | N/A | 8 | 8 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-04-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-08 | 2023-04-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7658 | 2544.28 | Unknown | Unknown | Yes | N/A | N/A | 2023-02-08 | 2023-02-27 | 20 | 14 | 2023-02-27 | 2023-08-28 | 183 | 131 | 2023-04-07 | 2023-06-22 | 77 | 55 | 2023-08-04 | 2023-08-04 | 1 | 1 | 2023-08-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | OH | Applicant Design | Residential | Disadvantaged Community,Underserved Community | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-04 | 2025-01-10 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 36576.26 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-04 | 2025-03-24 | 172 | 122 | 2025-03-24 | 2025-06-24 | 93 | 67 | 2025-02-18 | 2025-03-24 | 35 | 25 | 2025-03-21 | 2025-06-30 | 31 | 21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-19 | Unknown | Unknown | No | 2024-10-11 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-11 | 2024-12-16 | Unknown | IOU Designed & Installed | N/A | Yes | 178 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1332.82 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-11 | 2025-04-03 | 175 | 125 | 2025-04-03 | 2025-04-07 | 5 | 3 | 2025-04-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-05 | 2024-10-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1599.64 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-05 | 2024-08-15 | Unknown | Unknown | 2024-08-15 | 2024-10-01 | 48 | 34 | 2024-10-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 104.05 | 104.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-16 | 2025-04-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1890.4 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-16 | 2025-03-20 | Unknown | Unknown | 2025-03-20 | 2025-04-16 | 28 | 20 | 2025-04-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LEMON GROVE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-18 | 2025-01-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1254.59 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-18 | 2025-01-02 | 16 | 12 | 2025-01-02 | 2025-01-02 | 1 | 1 | 2025-01-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-27 | Unknown | Unknown | No | 2025-05-28 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-28 | 2025-05-28 | Unknown | IOU Designed & Installed | N/A | Yes | 44 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1410.72 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-28 | 2025-07-11 | 45 | 33 | 2025-07-11 | 2025-05-29 | Unknown | Unknown | 2025-05-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-29 | Unknown | Unknown | Unknown | Unknown | 2025-07-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-09 | 2025-05-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1854.38 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-09 | 2025-05-30 | 22 | 16 | 2025-05-30 | 2025-05-30 | 1 | 1 | 2025-05-13 | 2025-05-30 | 18 | 14 | Unknown | Unknown | Unknown | Unknown | 2025-05-30 | 2025-07-09 | 41 | 29 | Unknown | Unknown | Unknown | Unknown | 2025-07-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-09 | 2024-12-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 663.26 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-09 | 2024-12-09 | 1 | 1 | 2024-12-09 | 2025-06-25 | 199 | 143 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-25 | Unknown | Unknown | Unknown | Unknown | 2025-09-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | POWAY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-26 | 2024-08-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 19905 | 739.19 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-26 | 2024-03-29 | Unknown | Unknown | 2024-03-29 | 2025-01-02 | 280 | 200 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-21 | 2025-04-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 11943 | 663.58 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-21 | 2025-04-21 | 1 | 1 | 2025-04-21 | 2025-06-04 | 45 | 33 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 4 | 4 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-15 | 2023-05-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 148.62 | Unknown | Unknown | Yes | N/A | N/A | 2023-05-15 | 2023-05-15 | 1 | 1 | 2023-05-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | Applicant Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-23 | 2025-02-14 | Unknown | Both (Customer elected Applicant Design & Install) | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 589305 | 20702.78 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-23 | 2025-02-14 | 23 | 17 | 2025-02-14 | 2025-05-29 | 105 | 75 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | MISSION VIEJO | N/A | 42.1 | 42.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-13 | 2023-06-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2000.09 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-13 | 2023-04-05 | Unknown | Unknown | 2023-04-05 | 2023-07-07 | 94 | 68 | 2023-07-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LAKESIDE | COUNTY OF SAN DIEGO-SOUTH of 56 | 29 | 29 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-23 | 2024-01-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 593.61 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-23 | 2024-01-23 | 1 | 1 | 2024-01-23 | 2024-06-20 | 150 | 108 | Unknown | Unknown | Unknown | Unknown | 2024-05-01 | 2024-05-24 | 24 | 18 | 2024-06-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-19 | 2024-11-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1511.39 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-19 | 2024-11-21 | 3 | 3 | 2024-11-21 | 2024-11-26 | 6 | 4 | 2024-11-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-26 | 2025-09-09 | 288 | 206 | Unknown | Unknown | Unknown | Unknown | 2025-09-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | CORONADO | CORONADO | 138.05 | 138.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-24 | 2025-05-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 790.52 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-24 | 2025-05-28 | 217 | 155 | 2025-05-28 | 2025-06-13 | 17 | 13 | 2025-05-15 | 2025-07-08 | 41 | 29 | 2025-08-01 | 2025-08-07 | 7 | 5 | 2025-06-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Commercial | Underserved Community | Spring Valley | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-03 | 2024-01-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 569539 | 39529.85 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-03 | 2023-12-18 | 77 | 55 | 2023-12-18 | 2024-05-06 | 141 | 101 | 2024-01-03 | 2024-02-04 | 33 | 23 | 2024-02-15 | 2024-05-09 | 24 | 18 | 2025-08-13 | Unknown | Unknown | Unknown | 2025-08-13 | 2025-09-03 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 42 | 42 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-07 | 2023-03-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 341 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-07 | 2023-03-09 | 3 | 3 | 2023-03-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2030-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-26 | 2023-09-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 411.86 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-26 | 2023-09-26 | 1 | 1 | 2023-09-26 | 2023-10-17 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-14 | 2025-01-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 499.14 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-14 | 2025-01-10 | Unknown | Unknown | 2025-01-10 | 2025-06-11 | 153 | 109 | Unknown | Unknown | Unknown | Unknown | 2025-01-23 | 2025-02-13 | 22 | 16 | 2025-06-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-17 | 2024-05-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 871.24 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-17 | 2024-05-17 | 1 | 1 | 2024-05-17 | 2024-05-20 | 4 | 2 | 2024-05-20 | Unknown | Unknown | Unknown | 2024-05-21 | 2024-05-31 | 11 | 9 | 2024-05-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-04 | 2025-06-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1318.32 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-04 | 2025-05-14 | Unknown | Unknown | 2025-05-14 | 2025-06-04 | 22 | 16 | 2025-06-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 103.05 | 103.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-13 | 2025-01-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1873.04 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-13 | 2024-11-19 | 7 | 5 | 2024-11-19 | 2025-01-13 | 56 | 40 | 2025-01-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 71.05 | 71.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-15 | 2024-08-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1394.16 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-15 | 2024-08-01 | 140 | 100 | 2024-08-01 | 2024-08-16 | 16 | 12 | 2024-08-16 | 2024-10-18 | 64 | 46 | Unknown | Unknown | Unknown | Unknown | 2024-10-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 25.05 | 25.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-21 | 2025-06-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1197.17 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-21 | 2025-02-20 | Unknown | Unknown | 2025-02-20 | 2025-06-13 | 114 | 82 | 2025-06-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-28 | 2025-02-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2121.87 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-28 | 2025-02-10 | 14 | 10 | 2025-02-10 | 2025-02-10 | 1 | 1 | 2025-02-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-10 | 2025-08-11 | 183 | 131 | Unknown | Unknown | Unknown | Unknown | 2025-08-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | 57 | 57 | Not Available | <1MW | No | N/A | N/A | N/A | 2021-08-03 | Unknown | Unknown | No | 2021-07-19 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2021-07-19 | 2021-07-19 | Unknown | IOU Designed & Installed | N/A | Yes | 861 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 42601 | 31485.55 | Unknown | Unknown | Yes | N/A | N/A | 2021-07-19 | 2023-11-13 | 848 | 606 | 2023-11-13 | Unknown | Unknown | Unknown | 2024-04-23 | 2024-04-23 | 1 | 1 | 2024-06-20 | 2024-08-22 | 64 | 46 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-10 | 2024-07-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 119430 | 6789.53 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-10 | 2024-02-14 | Unknown | Unknown | 2024-02-14 | 2025-01-31 | 353 | 253 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2020-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-14 | 2025-02-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 4664.91 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-14 | 2025-02-27 | 45 | 33 | 2025-02-27 | 2025-04-02 | 35 | 25 | Unknown | Unknown | Unknown | Unknown | 2025-02-28 | 2025-03-14 | 15 | 11 | 2025-04-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-24 | 2024-08-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 985.1 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-24 | 2024-06-14 | Unknown | Unknown | 2024-06-14 | 2024-08-16 | 64 | 46 | 2024-08-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | CARLSBAD | CARLSBAD | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-07 | 2025-05-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2169.1 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-07 | 2025-05-07 | 1 | 1 | 2025-05-07 | 2025-05-07 | 1 | 1 | 2025-05-07 | Unknown | Unknown | Unknown | 2025-05-07 | 2025-06-11 | 36 | 26 | 2025-05-07 | 2025-09-08 | 125 | 89 | Unknown | Unknown | Unknown | Unknown | 2025-09-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-30 | 2024-06-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1049.43 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-30 | 2024-06-30 | 1 | 0 | 2024-06-30 | 2024-06-30 | 1 | 0 | 2024-06-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-27 | 2024-08-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1090.55 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-27 | 2024-08-14 | Unknown | Unknown | 2024-08-14 | 2024-08-29 | 16 | 12 | 2024-08-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | WARNER SPRINGS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-11-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-12 | 2023-11-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7953 | 4032.64 | Unknown | Unknown | Yes | N/A | N/A | 2022-10-12 | 2023-11-17 | 402 | 288 | 2023-11-17 | 2025-01-03 | 414 | 296 | 2024-03-21 | 2025-02-13 | 330 | 236 | Unknown | Unknown | Unknown | Unknown | 2025-01-03 | 2025-06-27 | 176 | 126 | Unknown | 2025-07-22 | Unknown | Unknown | 2025-07-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-10 | 2023-03-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 351.99 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-10 | 2023-03-10 | 1 | 1 | 2023-03-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | 43 | 43 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-01 | 2024-05-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1845.21 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-01 | 2023-11-20 | Unknown | Unknown | 2023-11-20 | 2024-05-01 | 164 | 118 | 2024-05-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | 816 | 816 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-17 | 2025-01-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1770.12 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-17 | 2024-11-15 | Unknown | Unknown | 2024-11-15 | 2025-01-17 | 64 | 46 | 2025-01-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-17 | 2025-09-04 | 231 | 165 | Unknown | Unknown | Unknown | Unknown | 2025-09-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 9.05 | 9.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-09 | 2025-06-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 250.06 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-09 | 2025-06-26 | 18 | 14 | 2025-06-26 | 2025-06-27 | 2 | 2 | 2025-06-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-14 | 2024-05-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 192.95 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-14 | 2024-08-02 | 81 | 59 | 2024-08-02 | 2024-08-02 | 1 | 1 | 2024-08-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-23 | 2024-04-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1360.52 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-23 | 2024-03-15 | Unknown | Unknown | 2024-03-15 | 2024-06-10 | 88 | 62 | 2024-06-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-29 | 2024-10-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1198.38 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-29 | 2024-11-06 | 9 | 7 | 2024-11-06 | 2024-12-02 | 27 | 19 | 2024-12-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 45.05 | 45.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-31 | 2025-03-31 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1465.42 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-31 | 2025-04-30 | 31 | 23 | 2025-04-30 | 2025-05-01 | 2 | 2 | 2025-05-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-01 | 2025-08-15 | 107 | 77 | Unknown | 2025-08-06 | Unknown | Unknown | 2025-08-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN JUAN CAPISTRANO | N/A | 147.05 | 147.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-08 | 2023-03-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1960.37 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-08 | 2023-05-22 | 76 | 54 | 2023-05-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-22 | Unknown | Unknown | Unknown | Unknown | 2023-09-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | Coronado | CORONADO | 138.05 | 138.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-21 | 2024-10-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 54096.74 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-21 | 2024-09-17 | 181 | 129 | 2024-09-17 | 2025-04-16 | 212 | 152 | Unknown | Unknown | Unknown | Unknown | 2024-12-17 | 2025-08-07 | 95 | 69 | 2025-04-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | 901 | 901 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-17 | 2025-01-17 | 2025-03-05 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1824.54 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-17 | 2024-11-13 | Unknown | Unknown | 2024-11-13 | 2025-01-17 | 66 | 48 | 2025-01-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-17 | 2025-03-05 | 48 | 34 | Unknown | Unknown | Unknown | Unknown | 2025-03-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-18 | 2024-04-26 | 2024-04-26 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 496.14 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-18 | 2024-03-21 | 4 | 4 | 2024-03-21 | 2024-04-26 | 37 | 27 | 2024-04-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-26 | 2024-04-26 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-04-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-09 | 2023-02-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 98.41 | Unknown | Unknown | Yes | N/A | N/A | 2023-02-09 | 2023-03-03 | 23 | 17 | 2023-03-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LAGUNA NIGUEL | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-24 | 2025-02-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 821.93 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-24 | 2025-03-18 | 23 | 17 | 2025-03-18 | 2025-03-18 | 1 | 1 | 2025-03-18 | 2025-06-11 | 86 | 62 | Unknown | Unknown | Unknown | Unknown | 2025-03-18 | Unknown | Unknown | Unknown | Unknown | 2025-08-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 62.05 | 62.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-21 | 2023-03-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 677.15 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-21 | 2023-03-21 | 1 | 1 | 2023-03-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Residential | Underserved Community | Santee | SANTEE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-02 | 2024-01-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 24098 | 19548.23 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-02 | 2024-01-23 | 22 | 16 | 2024-01-23 | Unknown | Unknown | Unknown | 2024-04-22 | 2025-02-10 | 165 | 117 | 2024-05-16 | 2025-02-28 | 38 | 28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | 3 | 3 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-08 | 2025-04-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 3006.23 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-08 | 2025-03-26 | Unknown | Unknown | 2025-03-26 | 2025-05-01 | 37 | 27 | 2025-05-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-01 | 2025-07-25 | 86 | 62 | Unknown | 2025-05-28 | Unknown | Unknown | 2025-07-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 75 | 75 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-25 | 2025-04-25 | 2025-05-14 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1953.1 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-25 | 2024-06-06 | Unknown | Unknown | 2024-06-06 | 2025-04-30 | 329 | 235 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-30 | 2024-12-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-21 | 2023-10-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 21692 | 1012.23 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-21 | 2024-03-28 | 190 | 136 | 2024-03-28 | 2024-04-17 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-26 | 2023-08-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3661.75 | 141.6 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-26 | 2023-07-26 | 1 | 1 | 2023-07-26 | 2023-08-16 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-16 | Unknown | Unknown | Unknown | Unknown | 2025-08-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-19 | 2024-07-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1017.4 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-19 | 2024-08-12 | 25 | 17 | 2024-08-12 | 2024-08-14 | 3 | 3 | 2024-08-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-27 | 2024-07-31 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2265.37 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-27 | 2024-07-31 | 309 | 221 | 2024-07-31 | 2024-10-14 | 76 | 54 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | IOU Design | Commercial | Underserved Community | CHULA VISTA | CHULA VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-11 | 2023-05-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 306432.9 | 40350.77 | Unknown | Unknown | Yes | N/A | N/A | 2023-04-11 | 2023-05-22 | 42 | 30 | 2023-05-22 | 2024-09-04 | 472 | 338 | 2023-07-10 | 2023-07-10 | 1 | 1 | 2023-09-27 | 2024-04-09 | 14 | 10 | 2024-09-04 | Unknown | Unknown | Unknown | 2024-08-20 | 2025-07-14 | 329 | 235 | 2025-07-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN JUAN CAPISTRANO | N/A | 103 | 103 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-29 | 2024-10-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1521.68 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-29 | 2024-11-18 | 21 | 15 | 2024-11-18 | 2024-11-26 | 9 | 7 | 2024-11-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-26 | 2025-07-29 | 246 | 176 | Unknown | 2025-07-22 | Unknown | Unknown | 2025-07-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 9.05 | 9.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-17 | Unknown | Unknown | No | 2024-10-20 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-20 | 2024-10-20 | Unknown | IOU Designed & Installed | N/A | Yes | 17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1372.03 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-20 | 2024-11-06 | 18 | 13 | 2024-11-06 | 2024-10-20 | Unknown | Unknown | 2024-10-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | Applicant Design | Commercial | Underserved Community | Escondido | ESCONDIDO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-22 | 2022-06-22 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 254563 | 30239.4 | Unknown | Unknown | Yes | N/A | N/A | 2022-06-22 | 2023-08-15 | 420 | 300 | 2023-08-15 | 2023-11-02 | 80 | 58 | 2023-08-29 | 2023-09-19 | 22 | 16 | 2023-10-10 | 2023-10-23 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-19 | 2024-12-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2819 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-19 | 2024-12-18 | Unknown | Unknown | 2024-12-18 | 2024-12-19 | 2 | 2 | 2024-12-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-19 | 2024-09-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1455.34 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-19 | 2024-09-04 | Unknown | Unknown | 2024-09-04 | 2024-09-19 | 16 | 12 | 2024-09-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | N/A | DEL MAR | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-01 | 2023-11-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 481.24 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-01 | 2023-11-02 | 2 | 2 | 2023-11-02 | 2023-11-09 | 8 | 6 | 2023-11-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-28 | 2024-08-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3391.22 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-28 | 2024-09-03 | 7 | 5 | 2024-09-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | ESCONDIDO | 73.05 | 73.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-13 | 2024-03-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 971.67 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-13 | 2023-11-27 | Unknown | Unknown | 2023-11-27 | 2024-03-13 | 108 | 78 | 2024-03-13 | Unknown | Unknown | Unknown | 2024-03-14 | 2024-03-25 | 12 | 8 | 2024-03-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-24 | 2025-04-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1145.79 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-24 | 2025-03-31 | Unknown | Unknown | 2025-03-31 | 2025-04-24 | 25 | 19 | 2025-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Commercial | N/A | ENCINITAS | ENCINITAS | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2022-12-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-30 | 2023-10-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2875 | 1495.14 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-30 | 2023-10-30 | 1 | 1 | 2023-10-30 | 2024-07-03 | 248 | 178 | 2024-02-05 | 2024-02-15 | 11 | 9 | 2024-05-02 | 2024-05-03 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | LAGUNA HILLS | N/A | 140.05 | 140.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-25 | 2023-10-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 158.14 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-25 | 2023-10-18 | Unknown | Unknown | 2023-10-18 | 2023-11-14 | 28 | 20 | 2023-11-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | Rancho Viejo | N/A | 3254 | 3254 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-10-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-02 | 2025-04-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2025-04-02 | 2024-07-01 | Unknown | Unknown | 2024-07-01 | 2025-06-18 | 353 | 253 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | Applicant Design | Commercial | Underserved Community | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-20 | 2024-06-20 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 124224.6 | 57596.43 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-20 | 2024-09-11 | 84 | 60 | 2024-09-11 | 2024-12-19 | 100 | 72 | 2024-09-23 | 2024-10-09 | 17 | 13 | 2024-07-25 | 2024-12-23 | 45 | 31 | 2024-12-19 | Unknown | Unknown | Unknown | 2025-03-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SANTEE | N/A | 134.05 | 134.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-12 | 2025-06-12 | 2025-06-18 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1082.85 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-12 | 2025-05-21 | Unknown | Unknown | 2025-05-21 | 2025-06-12 | 23 | 17 | 2025-06-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-12 | 2025-06-18 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2025-06-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-12 | 2025-06-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1439.74 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-12 | 2025-06-13 | 2 | 2 | 2025-06-13 | 2025-06-13 | 1 | 1 | 2025-06-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-13 | 2025-09-10 | 90 | 64 | Unknown | Unknown | Unknown | Unknown | 2025-09-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-05 | 2024-07-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 186.09 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-05 | 2024-06-05 | Unknown | Unknown | 2024-06-05 | 2024-07-15 | 41 | 29 | 2024-07-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-29 | 2024-03-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1809.03 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-29 | 2024-01-29 | Unknown | Unknown | 2024-01-29 | 2024-03-11 | 43 | 31 | 2024-03-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-02-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-15 | 2023-03-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 21977 | 3869.24 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-15 | 2023-03-15 | 1 | 1 | 2023-03-15 | 2023-04-07 | 24 | 18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | 37 | 37 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-08 | 2023-02-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 848.3 | Unknown | Unknown | Yes | N/A | N/A | 2023-02-08 | 2023-08-03 | 177 | 127 | 2023-08-03 | 2023-08-30 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | 2023-08-30 | 2023-09-09 | 11 | 8 | 2023-08-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-13 | 2023-06-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 23991 | 554.66 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-13 | 2023-06-13 | 1 | 1 | 2023-06-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SOUTH LAGUNA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-05-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-29 | 2024-03-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2875.23 | 295.09 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-29 | 2024-03-05 | 6 | 4 | 2024-03-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-29 | 2024-01-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 158.37 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-29 | 2024-01-19 | Unknown | Unknown | 2024-01-19 | 2024-02-15 | 28 | 20 | 2024-02-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | NATIONAL CITY | NATIONAL CITY | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2025-04-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-30 | 2024-05-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 51.19 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-30 | 2024-05-02 | 3 | 3 | 2024-05-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-22 | 2024-08-21 | 92 | 66 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | 19 | 19 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-19 | 2023-09-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1762.88 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-19 | 2023-07-14 | Unknown | Unknown | 2023-07-14 | 2023-09-20 | 69 | 49 | 2023-09-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-30 | 2025-05-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 5563.93 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-30 | 2025-05-05 | 6 | 4 | 2025-05-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SOUTH LAGUNA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-11 | 2024-01-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 977.59 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-11 | 2024-01-12 | 2 | 2 | 2024-01-12 | 2024-01-12 | 1 | 1 | 2024-01-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | LAGUNA NIGUEL | N/A | 136.05 | 136.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-09 | 2024-10-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1190.83 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-09 | 2024-11-25 | 48 | 34 | 2024-11-25 | 2024-11-25 | 1 | 1 | 2024-11-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 132.05 | 132.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-17 | 2024-12-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 499.14 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-17 | 2024-12-12 | Unknown | Unknown | 2024-12-12 | 2024-12-23 | 12 | 8 | 2024-12-23 | Unknown | Unknown | Unknown | 2024-12-17 | 2025-01-30 | 45 | 33 | 2024-12-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | JAMUL | N/A | 143.05 | 143.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-14 | 2024-10-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1600.22 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-14 | 2024-12-29 | 77 | 55 | 2024-12-29 | 2024-12-29 | 1 | 0 | 2024-12-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | 109.05 | 109.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-28 | 2024-12-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 972.99 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-28 | 2024-08-13 | 47 | 33 | 2024-08-13 | 2025-01-22 | 163 | 117 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 67 | 67 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-28 | 2024-04-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 5124 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-28 | 2024-02-23 | Unknown | Unknown | 2024-02-23 | 2024-04-05 | 43 | 31 | 2024-04-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-27 | 2025-03-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1231.32 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-27 | 2025-02-27 | 1 | 1 | 2025-02-27 | 2025-03-17 | 19 | 13 | 2025-03-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | POTRERO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-18 | 2025-02-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1664.72 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-18 | 2025-02-17 | Unknown | Unknown | 2025-02-17 | 2025-02-19 | 3 | 3 | 2025-02-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | BONITA | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-01 | Unknown | Unknown | No | 2024-05-01 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-01 | 2024-05-01 | Unknown | IOU Designed & Installed | N/A | Yes | 184 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2248 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-01 | 2024-11-04 | 188 | 134 | 2024-11-04 | 2024-12-11 | 38 | 28 | 2024-12-11 | Unknown | Unknown | Unknown | 2024-12-11 | 2024-12-23 | 13 | 9 | 2024-09-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | Underserved Community | San Marcos | SAN MARCOS | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-07 | 2022-12-07 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 276846.33 | 108929.19 | Unknown | Unknown | Yes | N/A | N/A | 2022-12-07 | 2024-06-11 | 553 | 395 | 2024-06-11 | 2024-12-30 | 203 | 145 | 2024-06-29 | 2025-02-19 | 84 | 60 | 2024-07-02 | 2025-06-26 | 50 | 40 | 2025-02-04 | Unknown | Unknown | Unknown | 2025-02-04 | 2025-08-01 | 179 | 129 | 2025-08-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 54 | 54 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-28 | 2025-02-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1627.15 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-28 | 2025-01-29 | 2 | 2 | 2025-01-29 | 2025-02-20 | 23 | 17 | 2025-02-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2022-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-09 | 2025-05-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 293.55 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-09 | 2025-05-12 | 4 | 2 | 2025-05-12 | 2025-05-22 | 11 | 9 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-08-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | DANA POINT | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-04 | 2024-09-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 799.48 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-04 | 2024-09-04 | 1 | 1 | 2024-09-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN JUAN CAPISTRANO | N/A | 124 | 124 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-10 | 2024-07-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1405.49 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-10 | 2024-08-02 | 24 | 18 | 2024-08-02 | 2024-08-08 | 7 | 5 | 2024-08-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-08 | Unknown | Unknown | Unknown | Unknown | 2025-09-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | Both | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-30 | 2025-01-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 82213.03 | 4188.93 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-30 | 2025-03-12 | 195 | 139 | 2025-03-12 | 2025-06-02 | 83 | 59 | Unknown | Unknown | Unknown | Unknown | 2025-03-13 | 2025-03-26 | 14 | 10 | 2025-06-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Commercial | N/A | Rancho Mission Viejo | Rancho Mission Viejo | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-30 | 2023-06-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 266239.4 | Unknown | Unknown | Yes | N/A | N/A | 2023-05-30 | 2023-05-08 | Unknown | Unknown | 2023-05-08 | Unknown | Unknown | Unknown | 2024-01-18 | 2024-01-19 | 2 | 2 | 2024-02-08 | 2025-03-12 | 370 | 264 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | DEL MAR | 42.45 | 42.45 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-06 | 2025-03-06 | 2025-05-08 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1216.31 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-06 | 2025-03-05 | Unknown | Unknown | 2025-03-05 | 2025-03-31 | 27 | 19 | Unknown | Unknown | Unknown | Unknown | 2025-03-18 | 2025-05-02 | 17 | 13 | 2025-03-31 | Unknown | Unknown | Unknown | Unknown | 2025-05-05 | Unknown | Unknown | 2025-05-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 42.05 | 42.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-06 | 2025-06-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1539.38 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-06 | 2025-06-09 | 4 | 2 | 2025-06-09 | 2025-06-20 | 12 | 10 | 2025-06-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-20 | 2025-07-14 | 25 | 17 | Unknown | Unknown | Unknown | Unknown | 2025-07-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-03 | 2025-06-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 1344.49 | 2559.48 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-03 | 2025-06-03 | 1 | 1 | 2025-06-03 | 2025-06-04 | 2 | 2 | 2025-06-04 | 2025-06-06 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2025-06-04 | 2025-08-26 | 84 | 60 | Unknown | 2025-08-21 | Unknown | Unknown | 2025-08-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 65 | 65 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-26 | 2023-09-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 158.14 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-26 | 2023-11-10 | 46 | 34 | 2023-11-10 | 2023-11-10 | 1 | 1 | 2023-11-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-23 | 2024-12-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 709.65 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-23 | 2024-12-29 | 7 | 5 | 2024-12-29 | 2025-02-04 | 38 | 27 | 2025-02-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-22 | 2024-05-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 10980 | 584.27 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-22 | 2024-05-10 | 19 | 15 | 2024-05-10 | 2024-05-10 | 1 | 1 | 2024-05-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-10 | 2025-08-21 | 469 | 335 | Unknown | Unknown | Unknown | Unknown | 2025-08-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LEMON GROVE | N/A | 65 | 65 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-10 | 2025-03-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1063.08 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-10 | 2025-02-20 | Unknown | Unknown | 2025-02-20 | 2025-03-12 | 21 | 15 | 2025-03-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-11 | 2023-10-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3941 | 492.85 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-11 | 2023-08-29 | Unknown | Unknown | 2023-08-29 | 2023-10-11 | 44 | 32 | 2023-10-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-11 | Unknown | Unknown | Unknown | Unknown | 2024-04-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 132 | 132 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-06 | 2025-05-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1104.56 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-06 | 2025-05-07 | 2 | 2 | 2025-05-07 | 2025-05-28 | 22 | 16 | 2025-05-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | RAMONA | N/A | 98.05 | 98.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-19 | 2023-09-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3985 | 13928.86 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-19 | 2023-09-18 | Unknown | Unknown | 2023-09-18 | 2023-09-19 | 2 | 2 | 2023-09-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-25 | 2024-11-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 499.14 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-25 | 2024-11-25 | 1 | 1 | 2024-11-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Residential | Underserved Community | Lakeside | COUNTY OF SAN DIEGO-SOUTH of 56 | 29 | 29 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-03 | 2024-01-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3274.34 | 12707.03 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-03 | 2023-12-13 | 41 | 29 | 2023-12-13 | 2024-06-11 | 182 | 130 | 2024-02-23 | 2024-06-07 | 34 | 25 | 2024-05-01 | 2025-06-24 | 34 | 26 | 2025-04-21 | Unknown | Unknown | Unknown | 2025-04-21 | 2025-08-21 | 123 | 89 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-25 | 2022-07-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 276.35 | Unknown | Unknown | Yes | N/A | N/A | 2022-07-25 | 2023-06-01 | 312 | 224 | 2023-06-01 | 2023-06-02 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2023-04-25 | 2023-05-08 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | 21 | 21 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-23 | 2024-04-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 662.9 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-23 | 2024-10-02 | 163 | 117 | 2024-10-02 | 2024-10-02 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 542.7 | 542.7 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-08 | 2023-10-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 35829 | 3256.26 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-08 | 2023-10-18 | 41 | 29 | 2023-10-18 | 2024-10-15 | 364 | 260 | Unknown | Unknown | Unknown | Unknown | 2024-10-08 | 2024-11-05 | 29 | 21 | 2024-10-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-28 | 2025-03-28 | 2025-04-03 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 6833.34 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-28 | 2025-03-28 | 1 | 1 | 2025-03-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-28 | 2025-04-03 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2025-04-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-25 | 2024-11-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 545.62 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-25 | 2025-01-02 | 39 | 29 | 2025-01-02 | 2025-02-28 | 58 | 42 | 2025-02-28 | Unknown | Unknown | Unknown | 2025-01-06 | 2025-01-25 | 20 | 15 | 2025-02-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | CAPISTRANO BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-06-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-24 | 2025-06-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1228.17 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-24 | 2025-06-24 | 1 | 1 | 2025-06-24 | 2025-06-24 | 1 | 1 | 2025-06-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-25 | 2025-08-12 | 49 | 35 | Unknown | Unknown | Unknown | Unknown | 2025-08-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | EL CAJON | N/A | 43.05 | 43.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-29 | Unknown | Unknown | No | 2024-07-16 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-16 | 2024-07-16 | Unknown | IOU Designed & Installed | N/A | Yes | 6 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1806.12 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-16 | 2024-07-22 | 7 | 5 | 2024-07-22 | 2024-07-18 | Unknown | Unknown | 2024-07-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | OCEANSIDE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-18 | 2025-06-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1304.6 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-18 | 2025-06-16 | Unknown | Unknown | 2025-06-16 | 2025-06-24 | 9 | 7 | 2025-06-24 | Unknown | Unknown | Unknown | 2025-06-25 | 2025-07-15 | 21 | 15 | 2025-06-24 | 2025-07-21 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | 2025-07-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-08 | 2024-05-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7320 | 584.27 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-08 | 2024-05-08 | 1 | 1 | 2024-05-08 | 2024-05-08 | 1 | 1 | 2024-05-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-08 | 2025-09-05 | 486 | 348 | Unknown | Unknown | Unknown | Unknown | 2025-09-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 15 | 15 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-20 | 2025-01-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1875.39 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-20 | 2024-12-16 | Unknown | Unknown | 2024-12-16 | 2025-01-07 | 23 | 17 | 2025-01-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 2650 | 2650 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-07-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-29 | 2024-03-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 23886 | 2094.24 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-29 | 2024-03-20 | 205 | 147 | 2024-03-20 | 2024-04-18 | 30 | 22 | Unknown | Unknown | Unknown | Unknown | 2024-03-21 | 2024-04-04 | 15 | 11 | 2024-04-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | FALLBROOK | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-21 | 2023-10-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 16912 | 3736.64 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-21 | 2023-06-28 | 8 | 6 | 2023-06-28 | 2024-10-11 | 472 | 338 | 2024-07-10 | 2024-07-10 | 1 | 1 | 2025-05-30 | 2025-05-30 | 1 | 1 | 2024-10-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 106 | 106 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-22 | 2025-02-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 997.93 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-22 | 2025-01-21 | Unknown | Unknown | 2025-01-21 | 2025-02-13 | 24 | 18 | 2025-02-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | LAGUNA NIGUEL | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-14 | 2023-08-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2008.64 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-14 | 2023-08-14 | 1 | 1 | 2023-08-14 | 2023-08-14 | 1 | 1 | 2023-08-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 88.05 | 88.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-27 | 2023-07-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 425.49 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-27 | 2023-07-27 | 1 | 1 | 2023-07-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-30 | 2024-05-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 23991 | 677.82 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-30 | 2024-05-20 | Unknown | Unknown | 2024-05-20 | 2024-05-30 | 11 | 9 | 2024-05-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | LA JOLLA | N/A | 101.05 | 101.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-01 | 2024-05-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1283.85 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-01 | 2024-05-01 | 1 | 1 | 2024-05-01 | 2024-05-01 | 1 | 1 | 2024-05-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-05 | 2024-12-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 999.91 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-05 | 2024-12-20 | 16 | 12 | 2024-12-20 | 2025-01-23 | 35 | 25 | Unknown | Unknown | Unknown | Unknown | 2024-12-05 | 2025-01-17 | 44 | 32 | 2025-01-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-28 | 2023-03-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 324247.6 | 22692.96 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-28 | 2023-03-29 | 2 | 2 | 2023-03-29 | 2023-04-10 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2023-04-06 | 2023-04-13 | 8 | 6 | 2023-04-10 | 2958465 | Unknown | Unknown | Unknown | 2025-07-03 | Unknown | Unknown | 2025-07-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | 42 | 42 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-03 | 2023-03-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 525.3 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-03 | 2023-03-03 | 1 | 1 | 2023-03-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | ALPINE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-26 | 2023-09-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 800.84 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-26 | 2023-08-23 | Unknown | Unknown | 2023-08-23 | 2023-09-26 | 35 | 25 | 2023-09-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | COUNTY OF SAN DIEGO-SOUTH of 56, SAN DIEGO | 88.05 | 88.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-23 | 2024-08-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 41506.11 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-23 | 2024-08-15 | 24 | 18 | 2024-08-15 | 2025-05-28 | 287 | 205 | 2025-01-27 | 2025-05-05 | 32 | 24 | 2025-01-24 | 2025-05-09 | 92 | 68 | 2025-05-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-09-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-25 | 2024-07-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 186.52 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-25 | 2024-05-30 | Unknown | Unknown | 2024-05-30 | 2024-08-20 | 83 | 59 | 2024-08-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-01 | 2025-05-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1133.7 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-01 | 2025-02-10 | Unknown | Unknown | 2025-02-10 | 2025-05-28 | 108 | 78 | 2025-05-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2019-03-30 | Unknown | Unknown | No | 2024-04-16 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-16 | 2024-05-02 | Unknown | IOU Designed & Installed | N/A | Yes | 16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 75.37 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-16 | 2024-05-02 | 17 | 13 | 2024-05-02 | 2024-05-14 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2024-06-07 | 2024-07-08 | 32 | 22 | 2024-05-14 | 2024-09-10 | 120 | 86 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 16.05 | 16.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-21 | 2025-03-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1585.86 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-21 | 2025-02-26 | Unknown | Unknown | 2025-02-26 | 2025-03-21 | 24 | 18 | 2025-03-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-28 | 2024-05-28 | 2024-09-10 | IOU Designed & Installed | N/A | No | Unknown | 813.04 | 492.42 | Unknown | Unknown | Unknown | 320.62 | 0 | 186.4 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-28 | 2024-05-21 | Unknown | Unknown | 2024-05-21 | 2024-06-06 | 17 | 13 | 2024-06-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-21 | 2024-09-10 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | 2024-09-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | BONSALL | N/A | 22 | 22 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-05 | 2024-11-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 840.48 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-05 | 2024-11-11 | 7 | 5 | 2024-11-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | Applicant Design | Commercial | Underserved Community | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-09 | 2023-02-09 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 1842381.21 | 64460.34 | Unknown | Unknown | Yes | N/A | N/A | 2023-02-09 | 2023-06-26 | 138 | 98 | 2023-06-26 | 2024-06-19 | 360 | 258 | 2023-06-27 | 2023-10-17 | 84 | 60 | 2023-06-13 | 2024-06-27 | 16 | 12 | 2024-06-19 | Unknown | Unknown | Unknown | 2025-01-23 | 2025-08-08 | 198 | 142 | 2025-08-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | 1163 | 1163 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2026-04-15 | Unknown | Unknown | No | 2025-01-27 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-27 | 2025-01-27 | Unknown | IOU Designed & Installed | N/A | Yes | 183 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1124.82 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-27 | 2025-07-29 | 184 | 132 | 2025-07-29 | 2025-02-03 | Unknown | Unknown | 2025-02-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | DESCANSO | N/A | 120 | 120 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-19 | 2024-09-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3948 | 1050.01 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-19 | 2024-08-15 | Unknown | Unknown | 2024-08-15 | 2024-09-20 | 37 | 27 | 2024-09-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | ALPINE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-11 | 2023-12-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 813.73 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-11 | 2023-12-06 | Unknown | Unknown | 2023-12-06 | 2024-01-03 | 29 | 21 | 2024-01-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN JUAN CAPISTRANO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-19 | 2024-03-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 153.26 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-19 | 2024-03-29 | 11 | 9 | 2024-03-29 | 2024-03-29 | 1 | 1 | 2024-03-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 68.05 | 68.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-08 | 2024-02-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1152.06 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-08 | 2023-11-03 | Unknown | Unknown | 2023-11-03 | 2024-02-15 | 105 | 75 | 2024-02-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | POWAY | N/A | 128 | 128 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-11 | 2024-11-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2371.99 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-11 | 2025-01-10 | 61 | 45 | 2025-01-10 | 2025-06-16 | 158 | 112 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-11 | 2025-02-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7962 | 1443.34 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-11 | 2025-02-04 | 86 | 62 | 2025-02-04 | 2025-06-02 | 119 | 85 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-02 | 2025-09-09 | 100 | 72 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-12 | 2025-05-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1398.33 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-12 | 2025-02-13 | Unknown | Unknown | 2025-02-13 | 2025-05-12 | 89 | 63 | 2025-05-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-28 | Unknown | Unknown | No | 2024-11-08 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-08 | 2024-11-08 | 2025-02-18 | IOU Designed & Installed | N/A | Yes | 91 | 23832.99 | 5681.94 | Unknown | 1268.81 | 385.68 | 16496.56 | 3981 | 3793.37 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-08 | 2025-02-07 | 92 | 66 | 2025-02-07 | 2024-12-09 | Unknown | Unknown | 2024-12-09 | 2025-02-07 | 61 | 45 | Unknown | Unknown | Unknown | Unknown | 2024-12-09 | 2025-02-18 | 72 | 52 | Unknown | 2025-02-10 | Unknown | Unknown | 2025-02-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | SAN DIEGO | 182.05 | 182.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-08 | 2024-01-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 9406.68 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-08 | 2024-01-03 | Unknown | Unknown | 2024-01-03 | 2024-02-06 | 35 | 25 | 2024-01-09 | 2024-01-10 | 2 | 2 | 2024-01-11 | 2024-02-14 | 21 | 15 | 2024-02-06 | Unknown | Unknown | Unknown | 2025-04-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-15 | 2024-04-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7681 | 589.24 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-15 | 2024-02-16 | Unknown | Unknown | 2024-02-16 | 2024-04-18 | 63 | 45 | 2024-04-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-18 | 2025-08-08 | 478 | 342 | Unknown | Unknown | Unknown | Unknown | 2025-08-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 12.05 | 12.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-10 | 2025-04-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1104.56 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-10 | 2025-05-23 | 44 | 32 | 2025-05-23 | 2025-05-27 | 5 | 3 | 2025-05-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 67.05 | 67.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-24 | 2024-07-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1549.66 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-24 | 2024-12-31 | 161 | 115 | 2024-12-31 | 2025-01-22 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | 2025-01-09 | 2025-01-28 | 20 | 14 | 2025-01-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-15 | 2024-10-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7962 | 1952.26 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-15 | 2024-08-14 | Unknown | Unknown | 2024-08-14 | 2025-01-10 | 150 | 108 | Unknown | Unknown | Unknown | Unknown | 2024-12-19 | 2025-01-21 | 34 | 24 | 2025-01-10 | 2025-07-10 | 182 | 130 | Unknown | Unknown | Unknown | Unknown | 2025-07-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community,Tribal Community | VALLEY CENTER | N/A | 9 | 9 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-24 | 2023-07-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 104394 | 3493.58 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-24 | 2023-07-18 | Unknown | Unknown | 2023-07-18 | 2023-10-10 | 85 | 61 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SANTEE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-19 | 2023-09-19 | 2023-09-29 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 154.99 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-19 | 2023-08-03 | Unknown | Unknown | 2023-08-03 | 2023-09-25 | 54 | 38 | 2023-09-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-25 | 2023-09-29 | 5 | 5 | Unknown | Unknown | Unknown | Unknown | 2023-09-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-09 | 2024-04-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7962 | 2836.43 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-09 | 2025-06-24 | 442 | 316 | 2025-06-24 | 2025-06-25 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 139.75 | 139.75 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-16 | 2024-01-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1353.17 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-16 | 2024-01-03 | Unknown | Unknown | 2024-01-03 | 2024-02-14 | 43 | 31 | 2024-02-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 69 | 69 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-06 | 2025-02-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1485.7 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-06 | 2025-02-10 | 5 | 3 | 2025-02-10 | 2025-02-28 | 19 | 15 | 2025-02-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | 341 | 341 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-03 | 2024-01-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 15924 | 2675.69 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-03 | 2024-01-03 | 1 | 1 | 2024-01-03 | 2024-01-18 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | 2024-01-04 | 2024-01-12 | 9 | 7 | 2024-01-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | NATIONAL CITY | NATIONAL CITY | 137.05 | 137.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-11 | 2024-09-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 18991.29 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-11 | 2025-01-02 | 114 | 82 | 2025-01-02 | 2025-06-16 | 166 | 118 | Unknown | Unknown | Unknown | Unknown | 2025-03-05 | 2025-06-24 | 106 | 76 | 2025-06-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-31 | 2024-02-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 875.34 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-31 | 2023-12-08 | Unknown | Unknown | 2023-12-08 | 2024-02-16 | 71 | 51 | 2024-02-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-21 | 2023-08-21 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 5244.26 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-21 | 2024-01-16 | 149 | 107 | 2024-01-16 | 2024-10-15 | 274 | 196 | 2024-01-30 | 2024-10-09 | 42 | 28 | 2024-03-26 | 2024-10-21 | 33 | 23 | 2025-02-18 | Unknown | Unknown | Unknown | 2025-02-18 | 2025-08-19 | 183 | 131 | 2025-09-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 35 | 35 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-11 | 2024-11-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1684.28 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-11 | 2024-11-12 | 2 | 2 | 2024-11-12 | 2024-11-14 | 3 | 3 | 2024-11-14 | 2024-12-30 | 47 | 33 | Unknown | Unknown | Unknown | Unknown | 2024-11-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | BONITA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-03 | 2025-02-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1546.02 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-03 | 2025-02-11 | 9 | 7 | 2025-02-11 | 2025-02-11 | 1 | 1 | 2025-02-11 | 2025-03-06 | 24 | 18 | Unknown | Unknown | Unknown | Unknown | 2025-02-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | BONITA | N/A | 19.05 | 19.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-28 | 2025-05-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1068.39 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-28 | 2025-05-14 | Unknown | Unknown | 2025-05-14 | 2025-06-09 | 27 | 19 | 2025-06-09 | 2025-06-12 | 4 | 4 | Unknown | Unknown | Unknown | Unknown | 2025-06-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-14 | 2023-11-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1122.95 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-14 | 2023-11-14 | 1 | 1 | 2023-11-14 | 2023-11-14 | 1 | 1 | 2023-11-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-02 | 2024-05-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7681 | 584.27 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-02 | 2024-02-28 | Unknown | Unknown | 2024-02-28 | 2024-05-02 | 65 | 47 | 2024-05-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 9 | 9 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-08 | 2025-05-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1293.03 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-08 | 2025-04-10 | Unknown | Unknown | 2025-04-10 | 2025-05-09 | 30 | 22 | 2025-05-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-29 | 2025-01-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1538.59 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-29 | 2025-01-27 | Unknown | Unknown | 2025-01-27 | 2025-01-29 | 3 | 3 | 2025-01-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-09 | 2025-04-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 114.3 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-09 | 2025-05-01 | 23 | 17 | 2025-05-01 | 2025-05-21 | 21 | 15 | 2025-05-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | IMPERIAL BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-23 | 2024-12-05 | 2025-06-05 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 18300 | 2639.68 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-23 | 2024-12-05 | 74 | 54 | 2024-12-05 | 2024-12-05 | 1 | 1 | 2024-12-05 | 2025-02-14 | 72 | 52 | Unknown | Unknown | Unknown | Unknown | 2025-02-14 | 2025-06-05 | 112 | 80 | Unknown | 2025-03-10 | Unknown | Unknown | 2025-06-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-17 | 2023-02-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 603.81 | Unknown | Unknown | Yes | N/A | N/A | 2023-02-17 | 2023-02-17 | 1 | 1 | 2023-02-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-06 | 2024-05-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 23991 | 564.79 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-06 | 2024-05-07 | 2 | 2 | 2024-05-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community,Tribal Community | Lakeside | N/A | 68.05 | 68.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-31 | Unknown | Unknown | No | 2024-01-10 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-21 | 2024-03-07 | Unknown | IOU Designed & Installed | N/A | Yes | 247 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2800 | 40570.67 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-21 | 2024-09-13 | 268 | 192 | 2024-09-13 | 2025-05-28 | 258 | 184 | 2024-09-13 | 2025-08-25 | 3 | 3 | 2025-05-28 | 2025-06-16 | 20 | 14 | 2025-05-28 | Unknown | Unknown | Unknown | 2025-06-12 | 2025-07-29 | 48 | 34 | 2025-08-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | N/A | Rancho Mission Viejo | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-16 | 2023-11-16 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 237915.44 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-16 | 2024-04-08 | 145 | 103 | 2024-04-08 | 2025-01-29 | 297 | 213 | 2024-04-30 | 2025-06-04 | 73 | 51 | 2024-07-29 | 2025-06-11 | 130 | 92 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Residential | Underserved Community | OC 1106-E1 (E) | OCEANSIDE | 14 | 14 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-09 | 2024-10-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1938.16 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-09 | 2024-10-03 | Unknown | Unknown | 2024-10-03 | 2024-12-10 | 69 | 49 | Unknown | Unknown | Unknown | Unknown | 2024-11-18 | 2024-12-20 | 33 | 25 | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-09-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-08 | 2024-08-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 224723 | 16972.2 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-08 | 2024-04-11 | 4 | 4 | 2024-04-11 | 2025-01-22 | 287 | 205 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | CHULA VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-09 | 2023-05-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 9749 | 1111.18 | Unknown | Unknown | Yes | N/A | N/A | 2023-05-09 | 2023-06-19 | 42 | 30 | 2023-06-19 | 2023-10-17 | 121 | 87 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-17 | 2025-05-28 | 590 | 422 | Unknown | 2025-06-25 | Unknown | Unknown | 2025-07-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | N/A | 103.05 | 103.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-18 | 2025-04-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 23886 | 1117.54 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-18 | 2025-05-28 | 41 | 29 | 2025-05-28 | 2025-06-11 | 15 | 11 | 2025-06-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | Underserved Community | SM 1129-B1 BARHAM TWNHM (E) | SAN MARCOS | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-20 | 2023-04-20 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 294671.81 | 80225.54 | Unknown | Unknown | Yes | N/A | N/A | 2023-04-20 | 2024-02-29 | 316 | 226 | 2024-02-29 | 2024-07-09 | 132 | 94 | 2024-04-09 | 2025-06-05 | 116 | 84 | 2023-08-16 | 2025-06-26 | -59 | -51 | 2024-10-29 | Unknown | Unknown | Unknown | 2024-10-29 | 2025-04-23 | 177 | 127 | 2025-07-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | 11450 | 11450 | Not Available | >2MW | No | N/A | N/A | N/A | 2022-08-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-19 | 2024-11-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 29470 | 2250.21 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-19 | 2025-01-21 | 64 | 46 | 2025-01-21 | 2025-03-25 | 64 | 46 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | JULIAN | N/A | 304.05 | 304.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-17 | 2025-03-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 812.48 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-17 | 2025-03-20 | 4 | 4 | 2025-03-20 | 2025-04-07 | 19 | 13 | 2025-04-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | BONITA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-08 | 2025-01-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 3524.94 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-08 | 2025-01-08 | 1 | 1 | 2025-01-08 | 2025-01-08 | 1 | 1 | 2025-01-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-08 | Unknown | Unknown | Unknown | Unknown | 2025-09-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | 104.05 | 104.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-31 | 2025-01-31 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1943.65 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-31 | 2025-01-15 | Unknown | Unknown | 2025-01-15 | 2025-02-03 | 20 | 14 | 2025-02-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-02 | 2025-08-27 | 207 | 148 | Unknown | Unknown | Unknown | Unknown | 2025-08-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-05-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-12 | 2024-02-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 8370 | 2549.24 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-12 | 2023-12-04 | 84 | 60 | 2023-12-04 | 2024-02-14 | 73 | 53 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 19.05 | 19.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-12 | 2025-03-12 | 2025-06-16 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1760.51 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-12 | 2024-07-10 | Unknown | Unknown | 2024-07-10 | 2025-06-03 | 329 | 235 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-03 | 2025-05-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 209 | 209 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-30 | 2023-03-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 763.04 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-30 | 2023-03-30 | 1 | 1 | 2023-03-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | OH | Applicant Design | Residential | N/A | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-05 | 2024-03-05 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 49443.07 | 31049.78 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-05 | 2024-05-02 | 59 | 43 | 2024-05-02 | 2025-05-19 | 383 | 273 | 2024-05-08 | 2025-04-30 | 190 | 136 | 2024-11-18 | 2025-08-05 | 104 | 74 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | CORONADO | N/A | 184.05 | 184.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-21 | 2024-10-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 918.94 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-21 | 2024-09-17 | Unknown | Unknown | 2024-09-17 | 2024-10-21 | 35 | 25 | 2024-10-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SOUTH LAGUNA | LAGUNA BEACH | 11.35 | 11.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-05 | 2024-06-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1497.1 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-05 | 2024-05-09 | Unknown | Unknown | 2024-05-09 | 2024-06-21 | 44 | 32 | 2024-06-21 | Unknown | Unknown | Unknown | 2024-06-21 | 2024-07-02 | 12 | 8 | 2024-06-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SANTEE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | 2025-04-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1699 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-07 | 2025-03-25 | Unknown | Unknown | 2025-03-25 | 2025-04-09 | 16 | 12 | 2025-04-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-09 | 2025-08-11 | 125 | 89 | Unknown | Unknown | Unknown | Unknown | 2025-08-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | IOU Design | Commercial | Underserved Community | DANA POINT | N/A | 640 | 640 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-18 | 2023-07-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2542359.55 | 58742.02 | Unknown | Unknown | Yes | N/A | N/A | 2023-04-18 | 2023-05-30 | 43 | 31 | 2023-05-30 | 2024-06-28 | 396 | 284 | 2023-07-28 | 2024-02-22 | 49 | 35 | 2024-02-23 | 2025-02-14 | 8 | 6 | 2024-06-28 | Unknown | Unknown | Unknown | 2025-08-12 | 2025-08-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2026-03-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-21 | 2024-03-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 54899 | 81.53 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-21 | 2024-08-08 | 141 | 101 | 2024-08-08 | 2024-08-20 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2024-03-27 | 2024-07-24 | 55 | 41 | 2024-08-20 | Unknown | Unknown | Unknown | Unknown | 2025-07-01 | Unknown | Unknown | 2025-07-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SANTEE | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-09 | 2024-01-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3941 | 1081.49 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-09 | 2023-11-22 | Unknown | Unknown | 2023-11-22 | 2024-01-09 | 49 | 35 | 2024-01-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | JAMUL | N/A | 47.05 | 47.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-08 | 2025-01-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 759.93 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-08 | 2025-01-27 | 20 | 14 | 2025-01-27 | 2025-01-27 | 1 | 1 | 2025-01-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | JULIAN | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-06 | 2024-09-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1152.46 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-06 | 2024-08-06 | Unknown | Unknown | 2024-08-06 | 2024-09-09 | 35 | 25 | 2024-09-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | Both | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-03 | 2024-05-31 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 77485.43 | 35147.15 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-03 | 2024-01-24 | Unknown | Unknown | 2024-01-24 | 2025-01-10 | 353 | 253 | 2024-08-22 | 2024-12-17 | 3 | 1 | 2024-10-03 | 2024-11-01 | 30 | 22 | 2025-09-09 | Unknown | Unknown | Unknown | 2025-09-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LA MESA | N/A | 890.7 | 890.7 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-22 | 2024-05-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 804.75 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-22 | 2024-04-10 | Unknown | Unknown | 2024-04-10 | 2024-06-27 | 79 | 57 | 2024-06-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 38.05 | 38.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-02 | 2025-06-02 | 2025-06-27 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 992.7 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-02 | 2025-06-03 | 2 | 2 | 2025-06-03 | 2025-06-24 | 22 | 16 | 2025-06-24 | 2025-06-24 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2025-06-24 | 2025-06-27 | 4 | 4 | Unknown | Unknown | Unknown | Unknown | 2025-06-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-27 | 2024-05-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1831.42 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-27 | 2024-03-06 | Unknown | Unknown | 2024-03-06 | 2024-08-09 | 157 | 113 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-28 | 2023-08-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 252589 | 22996.26 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-28 | 2023-08-28 | 1 | 1 | 2023-08-28 | 2024-08-07 | 346 | 248 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | Underserved Community | OC 1086-G3 Summerwell WO2 (E) | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-09 | 2023-02-09 | 2025-06-10 | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 142245 | 53944.18 | Unknown | Unknown | Yes | N/A | N/A | 2023-02-09 | 2023-03-02 | 22 | 16 | 2023-03-02 | 2025-01-06 | 677 | 483 | 2023-03-07 | 2024-11-07 | 418 | 300 | 2024-07-24 | 2024-08-07 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-03 | Unknown | Unknown | 2025-06-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Residential | Underserved Community | Carlsbad | Carlsbad | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-11-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-02-17 | 2024-09-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 6724.62 | Unknown | Unknown | Yes | N/A | N/A | 2022-02-17 | 2024-12-09 | 1027 | 733 | 2024-12-09 | 2025-04-23 | 136 | 98 | 2024-12-17 | 2025-04-18 | 39 | 28 | 2025-04-24 | 2025-07-28 | 91 | 63 | 2025-04-29 | Unknown | Unknown | Unknown | 2025-04-29 | 2025-09-03 | 128 | 92 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 64 | 64 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-08-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-08 | 2022-08-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 98.41 | Unknown | Unknown | Yes | N/A | N/A | 2022-08-08 | 2023-02-22 | 199 | 143 | 2023-02-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-13 | 2025-06-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1246.59 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-13 | 2025-06-18 | 6 | 4 | 2025-06-18 | 2025-06-19 | 2 | 2 | 2025-06-18 | 2025-07-08 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | 2025-06-19 | 2025-07-08 | 20 | 14 | Unknown | Unknown | Unknown | Unknown | 2025-07-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SOUTH LAGUNA | N/A | 180.05 | 180.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-07-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-16 | 2024-08-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1034.42 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-16 | 2024-08-16 | 1 | 1 | 2024-08-16 | 2024-08-16 | 1 | 1 | 2024-08-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-11 | 2025-06-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1018.11 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-11 | 2025-05-30 | Unknown | Unknown | 2025-05-30 | 2025-06-17 | 19 | 13 | 2025-06-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-17 | 2025-08-06 | 51 | 37 | Unknown | Unknown | Unknown | Unknown | 2025-08-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-09 | 2025-01-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 9150 | 525.43 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-09 | 2024-10-22 | Unknown | Unknown | 2024-10-22 | 2025-01-09 | 80 | 58 | 2025-01-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SANTEE | N/A | 67 | 67 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-25 | 2024-06-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3941 | 1301.25 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-25 | 2024-05-13 | Unknown | Unknown | 2024-05-13 | 2024-07-08 | 57 | 41 | 2024-07-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-07 | 2024-11-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 891.47 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-07 | 2024-11-07 | 1 | 1 | 2024-11-07 | 2024-11-07 | 1 | 1 | 2024-11-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 43.05 | 43.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-16 | 2025-04-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1650.37 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-16 | 2025-04-07 | Unknown | Unknown | 2025-04-07 | 2025-04-16 | 10 | 8 | 2025-04-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 301.05 | 301.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-28 | 2025-05-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1096.64 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-28 | 2025-05-06 | 9 | 7 | 2025-05-06 | 2025-05-06 | 1 | 1 | 2025-05-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-06 | 2025-07-01 | 57 | 41 | Unknown | Unknown | Unknown | Unknown | 2025-07-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | RAMONA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-27 | 2025-06-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1037.14 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-27 | 2025-06-14 | Unknown | Unknown | 2025-06-14 | 2025-06-27 | 14 | 10 | 2025-06-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-27 | 2025-07-08 | 12 | 8 | Unknown | Unknown | Unknown | Unknown | 2025-07-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | N/A | Rancho Mission Viejo | MISSION VIEJO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-09 | 2024-05-09 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 165976.01 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-09 | 2025-02-20 | 288 | 206 | 2025-02-20 | 2025-04-09 | 49 | 35 | 2025-03-10 | 2025-04-09 | 21 | 15 | 2025-03-21 | 2025-04-25 | 31 | 23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | 31.05 | 31.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-13 | 2023-11-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 876.99 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-13 | 2023-10-19 | Unknown | Unknown | 2023-10-19 | 2023-11-21 | 34 | 24 | 2023-11-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CORONADO | N/A | 215.05 | 215.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-17 | 2024-04-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 496.42 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-17 | 2024-02-05 | Unknown | Unknown | 2024-02-05 | 2024-08-25 | 203 | 145 | 2024-08-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 9602 | 9602 | Not Available | >2MW | No | N/A | N/A | N/A | 2026-05-27 | Unknown | Unknown | No | 2024-06-25 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-25 | 2024-06-27 | 2024-11-19 | IOU Designed & Installed | N/A | Yes | 31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 322.96 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-25 | 2024-07-24 | 30 | 22 | 2024-07-24 | 2024-07-29 | 6 | 4 | 2024-07-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-16 | 2024-11-19 | 127 | 91 | Unknown | Unknown | Unknown | Unknown | 2024-11-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | 37 | 37 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-29 | 2024-10-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 747.8 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-29 | 2025-05-23 | 207 | 149 | 2025-05-23 | 2025-06-09 | 18 | 12 | 2025-06-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 53.05 | 53.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-01-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-17 | 2023-06-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 955.85 | Unknown | Unknown | Yes | N/A | N/A | 2023-04-17 | 2023-06-23 | 68 | 50 | 2023-06-23 | 2023-07-31 | 39 | 27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-31 | 2023-08-11 | 12 | 10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 125.1 | 125.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-02 | 2024-08-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1271.11 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-02 | 2024-08-12 | 11 | 7 | 2024-08-12 | 2024-10-04 | 54 | 40 | 2024-10-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | VISTA | VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-20 | 2023-06-20 | 2023-09-27 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1432.45 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-20 | 2023-06-23 | 4 | 4 | 2023-06-23 | 2023-07-05 | 13 | 9 | 2023-07-05 | Unknown | Unknown | Unknown | 2023-06-28 | 2024-07-09 | 45 | 33 | 2023-07-05 | 2023-09-27 | 85 | 61 | Unknown | Unknown | Unknown | Unknown | 2023-09-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-30 | 2024-04-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 51113 | 3465.71 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-30 | 2024-04-30 | 1 | 1 | 2024-04-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SANTEE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-23 | 2024-08-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1436.87 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-23 | 2024-07-30 | Unknown | Unknown | 2024-07-30 | 2024-08-23 | 25 | 19 | 2024-08-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | N/A | 323 | 323 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-27 | 2023-10-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 751.8 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-27 | 2023-06-28 | Unknown | Unknown | 2023-06-28 | 2023-10-27 | 122 | 88 | 2023-10-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | LAKESIDE | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2020-12-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-17 | 2023-10-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3638.2 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-17 | 2023-10-23 | 7 | 5 | 2023-10-23 | 2023-10-27 | 5 | 5 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | OH | IOU Design | Commercial | Underserved Community | CAMPO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-03 | 2023-11-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 30289.06 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-03 | 2023-11-03 | 1 | 1 | 2023-11-03 | 2025-07-28 | 634 | 452 | Unknown | Unknown | Unknown | Unknown | 2025-05-29 | 2025-06-13 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-08-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SOUTH LAGUNA | N/A | 138 | 138 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-01 | 2024-11-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 666.64 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-01 | 2024-11-01 | 1 | 1 | 2024-11-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2021-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-02 | 2025-04-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1758.84 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-02 | 2025-04-02 | 1 | 1 | 2025-04-02 | 2025-06-23 | 83 | 59 | Unknown | Unknown | Unknown | Unknown | 2025-04-03 | 2025-04-16 | 14 | 10 | 2025-06-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community,Tribal Community | LAKESIDE | N/A | 47.05 | 47.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-17 | 2024-10-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 24601.88 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-17 | 2024-09-30 | 14 | 10 | 2024-09-30 | 2025-05-15 | 228 | 164 | 2024-10-31 | 2025-03-21 | 25 | 19 | 2025-05-16 | 2025-05-27 | 12 | 8 | 2025-05-15 | 2025-07-15 | 62 | 44 | 2025-06-13 | 2025-07-11 | 29 | 21 | 2025-08-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | COUNTY OF SAN DIEGO-NORTH of 56 | 312 | 312 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-07 | 2024-05-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 818.09 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-07 | 2024-07-18 | 73 | 53 | 2024-07-18 | Unknown | Unknown | Unknown | 2024-08-01 | 2024-09-19 | 50 | 36 | 2024-07-31 | 2024-09-27 | 11 | 9 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-13 | 2024-12-20 | 2025-05-14 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1734.21 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-13 | 2024-12-16 | 4 | 2 | 2024-12-16 | 2024-12-20 | 5 | 5 | 2024-12-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-20 | 2025-05-14 | 146 | 104 | Unknown | Unknown | Unknown | Unknown | 2025-05-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 387.05 | 387.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-12 | 2023-09-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 840.5 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-12 | 2023-09-01 | Unknown | Unknown | 2023-09-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-19 | 2023-06-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 80.5 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-19 | 2023-05-26 | Unknown | Unknown | 2023-05-26 | 2023-09-12 | 110 | 78 | Unknown | Unknown | Unknown | Unknown | 2023-09-08 | 2023-09-15 | 8 | 6 | 2023-09-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | BORREGO SPRINGS | N/A | 117 | 117 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-31 | 2023-10-31 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 3238.74 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-31 | 2023-10-31 | 62 | 44 | 2023-10-31 | 2024-03-08 | 130 | 94 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-08 | 2025-07-18 | 498 | 356 | Unknown | 2025-06-20 | Unknown | Unknown | 2025-07-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 116.05 | 116.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-12 | 2025-01-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1644.1 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-12 | 2024-12-10 | Unknown | Unknown | 2024-12-10 | 2025-01-20 | 42 | 30 | 2025-01-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 140.05 | 140.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-24 | 2025-03-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 961.8 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-24 | 2025-03-04 | Unknown | Unknown | 2025-03-04 | 2025-04-03 | 31 | 23 | 2025-04-03 | Unknown | Unknown | Unknown | 2025-06-30 | 2025-06-30 | 1 | 1 | 2025-04-04 | 2025-07-09 | 97 | 69 | Unknown | 2025-07-02 | Unknown | Unknown | 2025-07-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-15 | 2023-05-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | 9.57 | -2.21 | Unknown | Unknown | 10.3 | 1.48 | 3241 | 760.7 | Unknown | Unknown | Yes | N/A | N/A | 2023-05-15 | 2023-05-15 | 1 | 1 | 2023-05-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | IOU Design | Commercial | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-31 | 2024-12-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 52553.71 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-31 | 2024-07-31 | 1 | 1 | 2024-07-31 | 2025-02-06 | 191 | 137 | 2024-12-16 | 2025-01-07 | 23 | 17 | 2025-04-18 | 2025-04-22 | 5 | 3 | 2025-02-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-04 | 2024-12-31 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1049.51 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-04 | 2024-12-13 | 10 | 8 | 2024-12-13 | 2024-12-31 | 19 | 13 | 2024-12-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | 61 | 61 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-17 | 2025-02-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 11943 | 1591.79 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-17 | 2024-08-01 | Unknown | Unknown | 2024-08-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 64 | 64 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-13 | 2025-03-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 11943 | 1336.02 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-13 | 2025-03-27 | 15 | 11 | 2025-03-27 | 2025-07-01 | 97 | 69 | Unknown | Unknown | Unknown | Unknown | 2025-05-29 | 2025-06-16 | 19 | 13 | 2025-07-01 | 2025-08-22 | 53 | 39 | Unknown | Unknown | Unknown | Unknown | 2025-07-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | 6720 | 6720 | Not Available | >2MW | No | N/A | N/A | N/A | 2025-11-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-10 | 2023-07-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 211402.81 | 109024.58 | Unknown | Unknown | Yes | N/A | N/A | 2023-01-10 | 2023-06-28 | 170 | 122 | 2023-06-28 | 2024-12-03 | 525 | 375 | 2024-01-08 | 2025-04-16 | 53 | 39 | 2024-10-31 | 2025-08-14 | 288 | 206 | 2025-05-20 | Unknown | Unknown | Unknown | 2025-05-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 95.05 | 95.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-13 | 2023-10-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 564 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-13 | 2023-10-13 | 1 | 1 | 2023-10-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SANTEE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-31 | 2025-01-31 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1880.42 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-31 | 2025-03-07 | 36 | 26 | 2025-03-07 | 2025-03-12 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-19 | 2025-06-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1619.79 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-19 | 2025-06-04 | Unknown | Unknown | 2025-06-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-06-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-13 | 2025-06-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 829.56 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-13 | 2025-06-12 | Unknown | Unknown | 2025-06-12 | 2025-06-27 | 16 | 12 | 2025-06-26 | 2025-06-27 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2025-06-27 | 2025-09-08 | 74 | 52 | Unknown | 2025-08-27 | Unknown | Unknown | 2025-09-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 552.1 | 552.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-05 | 2025-02-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1747.24 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-05 | 2024-11-14 | Unknown | Unknown | 2024-11-14 | 2024-12-09 | 26 | 18 | 2024-12-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | N/A | Rancho Mission Viejo | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-16 | 2023-11-16 | 2025-02-22 | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 68016.57 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-16 | 2024-02-21 | 98 | 70 | 2024-02-21 | 2025-01-06 | 321 | 229 | 2024-04-19 | 2025-05-22 | 155 | 109 | 2024-07-23 | 2024-07-26 | 4 | 4 | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-06 | Unknown | Unknown | 2025-02-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-07 | Unknown | Unknown | No | 2024-09-17 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-17 | 2024-09-25 | Unknown | IOU Designed & Installed | N/A | Yes | 28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1494.01 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-17 | 2024-10-14 | 28 | 20 | 2024-10-14 | 2024-10-15 | 2 | 2 | 2024-10-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-25 | 2025-07-16 | 295 | 211 | Unknown | Unknown | Unknown | Unknown | 2025-07-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SM 1129-B1 Barham PH2 | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-18 | 2024-06-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 45494 | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2024-06-18 | 2024-04-24 | Unknown | Unknown | 2024-04-24 | 2024-08-23 | 122 | 88 | Unknown | Unknown | Unknown | Unknown | 2025-02-04 | 2025-02-04 | 1 | 1 | 2024-08-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-02 | 2023-10-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 228943 | 13978.22 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-02 | 2023-08-31 | Unknown | Unknown | 2023-08-31 | 2023-10-19 | 50 | 36 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-19 | 2024-11-12 | 391 | 279 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | LAKESIDE | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-27 | 2025-04-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 5629.75 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-27 | 2025-04-02 | 7 | 5 | 2025-04-02 | 2025-04-18 | 17 | 13 | Unknown | Unknown | Unknown | Unknown | 2025-04-08 | 2025-04-14 | 7 | 5 | 2025-04-18 | 2025-06-09 | 53 | 37 | Unknown | 2025-06-25 | Unknown | Unknown | 2025-07-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 172.05 | 172.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-29 | 2024-05-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 648.41 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-29 | 2024-03-13 | Unknown | Unknown | 2024-03-13 | 2024-05-14 | 63 | 45 | 2024-05-14 | 2025-05-05 | 357 | 255 | Unknown | Unknown | Unknown | Unknown | 2024-05-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-21 | 2022-10-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 341.57 | Unknown | Unknown | Yes | N/A | N/A | 2022-10-21 | 2023-05-01 | 193 | 137 | 2023-05-01 | 2023-05-08 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | IOU Design | Commercial | Underserved Community | VISTA | VISTA | 1103 | 1103 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2024-07-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-19 | 2023-10-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 85741 | 43617.76 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-19 | 2023-09-26 | Unknown | Unknown | 2023-09-26 | 2024-07-25 | 304 | 218 | 2024-01-11 | 2024-06-21 | 16 | 11 | 2024-04-16 | 2025-06-13 | 155 | 113 | 2024-07-25 | Unknown | Unknown | Unknown | 2024-09-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | N/A | 80 | 80 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-17 | 2024-01-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 36350 | 1038.29 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-17 | 2024-01-24 | 69 | 49 | 2024-01-24 | 2024-06-05 | 134 | 96 | Unknown | Unknown | Unknown | Unknown | 2024-11-04 | 2024-11-05 | 2 | 2 | 2024-06-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 195.35 | 195.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-27 | 2025-03-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1719.9 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-27 | 2025-02-27 | 1 | 1 | 2025-02-27 | 2025-04-07 | 40 | 28 | Unknown | Unknown | Unknown | Unknown | 2025-03-21 | 2025-04-04 | 15 | 11 | 2025-04-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-27 | 2024-05-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1982.16 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-27 | 2024-03-06 | Unknown | Unknown | 2024-03-06 | 2024-08-09 | 157 | 113 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | CARLSBAD | N/A | 68 | 68 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-28 | 2025-03-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7962 | 1493.31 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-28 | 2025-03-14 | 15 | 11 | 2025-03-14 | 2025-05-06 | 54 | 38 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 68 | 68 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-05 | 2024-09-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1206.27 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-05 | 2024-08-19 | Unknown | Unknown | 2024-08-19 | 2024-09-26 | 39 | 29 | 2024-09-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 82.05 | 82.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-29 | Unknown | Unknown | No | 2024-06-12 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-12 | 2024-06-12 | Unknown | IOU Designed & Installed | N/A | Yes | 379 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1521.96 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-12 | 2025-06-26 | 380 | 272 | 2025-06-26 | 2024-11-14 | Unknown | Unknown | 2024-11-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-12 | 2025-08-04 | 266 | 190 | Unknown | 2025-07-24 | Unknown | Unknown | 2025-08-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-06 | 2024-08-06 | 2024-08-13 | IOU Designed & Installed | N/A | No | Unknown | 8.76 | 0 | Unknown | Unknown | Unknown | 8.76 | 0 | 192.95 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-06 | 2024-08-06 | 1 | 1 | 2024-08-06 | 2024-08-06 | 1 | 1 | 2024-08-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-06 | 2024-08-13 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2024-08-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 68 | 68 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-29 | 2025-01-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1484.41 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-29 | 2025-02-04 | 7 | 5 | 2025-02-04 | 2025-02-12 | 9 | 7 | 2025-02-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-12 | 2025-07-08 | 147 | 105 | Unknown | 2025-07-08 | Unknown | Unknown | 2025-07-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-12 | 2023-09-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 659 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-12 | 2024-08-06 | 330 | 236 | 2024-08-06 | 2024-08-09 | 4 | 4 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-10 | 2025-01-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 7919.9 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-10 | 2025-01-10 | 1 | 1 | 2025-01-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2026-03-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-21 | 2024-03-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 54899 | 81.53 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-21 | 2024-09-20 | 184 | 132 | 2024-09-20 | 2024-10-15 | 26 | 18 | Unknown | Unknown | Unknown | Unknown | 2024-04-04 | 2024-09-25 | 60 | 44 | 2024-10-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Residential | N/A | Rancho Mission Viejo | N/A | 2838.8 | 2838.8 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-10-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-27 | 2024-08-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 106787.17 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-27 | 2024-07-01 | 5 | 3 | 2024-07-01 | 2025-01-08 | 192 | 138 | 2024-08-27 | 2025-04-22 | 198 | 140 | 2024-12-13 | 2025-01-07 | 26 | 18 | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-08-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-20 | 2024-05-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 435.21 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-20 | 2024-05-23 | 4 | 4 | 2024-05-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | OH | Applicant Design | Commercial | Underserved Community | San Marcos | COUNTY OF SAN DIEGO-NORTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-15 | 2023-11-15 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 112768.67 | 10037.95 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-15 | 2024-02-13 | 91 | 65 | 2024-02-13 | 2024-07-03 | 142 | 102 | 2024-03-20 | 2024-05-16 | 45 | 33 | 2024-03-22 | 2024-05-28 | 19 | 13 | 2024-07-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | Underserved Community | SD 1128-H1 N.CITY PA4 (E) | SAN MARCOS | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-07 | 2022-12-07 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 216649 | 110476.09 | Unknown | Unknown | Yes | N/A | N/A | 2022-12-07 | 2024-05-02 | 513 | 367 | 2024-05-02 | 2024-10-02 | 154 | 110 | 2024-05-31 | 2024-12-20 | 56 | 42 | 2024-05-31 | 2024-12-10 | 81 | 58 | 2024-10-29 | Unknown | Unknown | Unknown | 2024-10-29 | 2025-06-26 | 241 | 173 | 2025-07-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | PINE VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-08 | 2024-08-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2097.41 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-08 | 2024-07-16 | Unknown | Unknown | 2024-07-16 | 2024-08-08 | 24 | 18 | 2024-08-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 68.05 | 68.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-24 | 2024-11-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1876.27 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-24 | 2024-10-09 | Unknown | Unknown | 2024-10-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | COUNTY OF SAN DIEGO-SOUTH of 56 | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-20 | 2025-06-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1087.97 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-20 | 2025-05-28 | Unknown | Unknown | 2025-05-28 | 2025-06-20 | 24 | 18 | 2025-06-20 | Unknown | Unknown | Unknown | 2025-06-20 | 2025-06-25 | 6 | 4 | 2025-06-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 12 | 12 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-15 | 2025-04-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 794.47 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-15 | 2025-04-07 | Unknown | Unknown | 2025-04-07 | 2025-04-24 | 18 | 14 | 2025-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-24 | 2025-08-19 | 118 | 84 | Unknown | 2025-08-08 | Unknown | Unknown | 2025-08-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-22 | 2024-05-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 10980 | 584.27 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-22 | 2024-05-10 | 19 | 15 | 2024-05-10 | 2024-05-10 | 1 | 1 | 2024-05-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-10 | 2025-08-28 | 476 | 340 | Unknown | Unknown | Unknown | Unknown | 2025-08-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-18 | 2024-06-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 11943 | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2024-06-18 | 2024-03-28 | Unknown | Unknown | 2024-03-28 | 2024-06-20 | 85 | 61 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-20 | 2025-06-13 | 359 | 257 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | 64 | 64 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-15 | 2024-07-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1262.32 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-15 | 2025-04-22 | 282 | 202 | 2025-04-22 | 2025-04-28 | 7 | 5 | 2025-04-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LA JOLLA | N/A | 42.1 | 42.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-19 | 2024-12-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1213.24 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-19 | 2025-01-22 | 35 | 25 | 2025-01-22 | 2025-01-28 | 7 | 5 | 2025-01-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-04 | 2024-01-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 426000 | 30212.55 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-04 | 2023-08-04 | Unknown | Unknown | 2023-08-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-05 | 2025-03-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2875.23 | 863.97 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-05 | 2025-03-03 | 27 | 19 | 2025-03-03 | 2025-03-12 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 27 | 27 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-03-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-11 | 2024-06-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1796.3 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-11 | 2024-05-01 | Unknown | Unknown | 2024-05-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-24 | 2023-04-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 795.43 | Unknown | Unknown | Yes | N/A | N/A | 2023-04-24 | 2023-04-27 | 4 | 4 | 2023-04-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-17 | 2023-02-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 363.72 | Unknown | Unknown | Yes | N/A | N/A | 2023-02-17 | 2023-02-17 | 1 | 1 | 2023-02-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Residential | N/A | ENCINITAS | ENCINITAS | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-16 | 2024-09-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 73758 | 3590.9 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-16 | 2024-07-24 | 9 | 7 | 2024-07-24 | 2025-07-09 | 351 | 251 | 2024-11-13 | 2025-07-01 | 135 | 95 | 2024-12-05 | 2025-04-21 | 62 | 44 | 2025-07-24 | Unknown | Unknown | Unknown | 2025-07-24 | 2025-08-08 | 16 | 12 | 2025-08-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-22 | 2025-01-31 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1235.42 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-22 | 2025-01-22 | 1 | 1 | 2025-01-22 | 2025-01-31 | 10 | 8 | 2025-01-31 | Unknown | Unknown | Unknown | 2025-02-04 | 2025-02-13 | 10 | 8 | 2025-01-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 1.35 | 1.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-06 | 2024-09-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1521.96 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-06 | 2024-09-11 | 6 | 4 | 2024-09-11 | 2024-11-01 | 52 | 38 | 2024-11-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-24 | 2023-04-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 8997 | 554.66 | Unknown | Unknown | Yes | N/A | N/A | 2023-04-24 | 2023-04-24 | 1 | 1 | 2023-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Commercial | Underserved Community | OC 1106-C3 | OCEANSIDE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-15 | 2022-06-15 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 47575.07 | Unknown | Unknown | Yes | N/A | N/A | 2022-06-15 | 2023-06-05 | 356 | 254 | 2023-06-05 | 2024-09-10 | 464 | 332 | 2023-06-25 | 2023-10-10 | 108 | 77 | 2024-09-06 | 2025-01-09 | -327 | -243 | 2025-04-24 | Unknown | Unknown | Unknown | 2025-04-24 | 2025-05-22 | 29 | 21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-02 | 2023-06-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3241 | 536.16 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-02 | 2023-06-02 | 1 | 1 | 2023-06-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 131 | 131 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-25 | 2024-02-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1566.27 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-25 | 2024-04-01 | 252 | 180 | 2024-04-01 | 2024-12-09 | 253 | 181 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | Applicant Design | Residential | Underserved Community | Chula Vista | N/A | 73843.24 | 73843.24 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-06-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-04 | 2023-12-04 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 63289 | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2023-12-04 | 2023-11-09 | Unknown | Unknown | 2023-11-09 | 2024-05-20 | 194 | 138 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-20 | 2025-07-31 | 438 | 314 | Unknown | Unknown | Unknown | Unknown | 2025-08-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 231 | 231 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-22 | 2025-01-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1397.81 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-22 | 2025-02-04 | 14 | 10 | 2025-02-04 | 2025-02-05 | 2 | 2 | 2025-02-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-28 | 2025-02-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2121.87 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-28 | 2025-02-07 | 11 | 9 | 2025-02-07 | 2025-02-11 | 5 | 3 | 2025-02-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-11 | 2025-07-31 | 171 | 123 | Unknown | Unknown | Unknown | Unknown | 2025-07-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | Applicant Design | Residential | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-03 | 2024-06-03 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 33634.6 | 2086.67 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-03 | 2024-05-21 | Unknown | Unknown | 2024-05-21 | 2025-03-04 | 288 | 206 | Unknown | Unknown | Unknown | Unknown | 2024-06-12 | 2024-07-12 | 31 | 23 | 2025-03-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-14 | 2024-10-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 9601 | 525.39 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-14 | 2024-08-08 | Unknown | Unknown | 2024-08-08 | 2024-10-14 | 68 | 48 | 2024-10-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | ESCONDIDO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2024-09-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-05 | 2025-02-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3753.77 | 3399.65 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-05 | 2025-04-15 | 70 | 50 | 2025-04-15 | 2025-05-06 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | 2025-03-31 | 2025-04-11 | 12 | 10 | 2025-05-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-10 | 2023-11-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3756.63 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-10 | 2023-06-22 | Unknown | Unknown | 2023-06-22 | 2023-11-20 | 152 | 108 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | JULIAN | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-21 | 2024-10-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 672.3 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-21 | 2024-10-18 | Unknown | Unknown | 2024-10-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-18 | 2024-04-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 724.94 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-18 | 2024-02-23 | Unknown | Unknown | 2024-02-23 | 2024-02-23 | 1 | 1 | 2024-02-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | IOU Design | Residential | Underserved Community | SM 1108-G7 (E) | SAN MARCOS | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-02 | 2024-02-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 214762 | 90041.3 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-02 | 2023-08-23 | 22 | 16 | 2023-08-23 | 2025-05-14 | 631 | 451 | 2024-04-04 | 2025-04-14 | 7 | 3 | 2024-09-05 | 2025-09-02 | -192 | -142 | 2025-04-04 | Unknown | Unknown | Unknown | 2025-04-04 | 2025-08-28 | 147 | 105 | 2025-09-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-02 | 2023-03-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 804.89 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-02 | 2023-03-10 | 9 | 7 | 2023-03-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | VALLEY CENTER | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-11-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-24 | 2025-04-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 14125 | 1242.74 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-24 | 2025-04-23 | Unknown | Unknown | 2025-04-23 | 2025-06-30 | 69 | 49 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-02 | 2024-04-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3961 | 763.64 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-02 | 2024-03-08 | Unknown | Unknown | 2024-03-08 | 2024-05-15 | 69 | 49 | 2024-05-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-27 | 2023-11-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3400.8 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-27 | 2023-11-01 | 36 | 26 | 2023-11-01 | 2024-02-12 | 104 | 74 | Unknown | Unknown | Unknown | Unknown | 2024-08-07 | 2024-08-07 | 1 | 1 | 2024-02-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | N/A | Rancho Mission Viejo | COUNTY OF ORANGE, MISSION VIEJO | 208 | 208 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-20 | 2024-03-20 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 64618.66 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-20 | 2024-11-08 | 234 | 168 | 2024-11-08 | 2025-04-16 | 160 | 114 | 2024-11-25 | 2025-04-16 | 93 | 67 | 2025-03-13 | 2025-08-08 | 10 | 8 | 2025-04-16 | Unknown | Unknown | Unknown | 2025-04-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-31 | 2025-04-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2023.37 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-31 | 2025-03-20 | Unknown | Unknown | 2025-03-20 | 2025-04-01 | 13 | 9 | 2025-04-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-30 | 2023-03-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 363.72 | Unknown | Unknown | Yes | N/A | N/A | 2023-01-30 | 2023-03-14 | 44 | 32 | 2023-03-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-14 | 2024-10-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1412.81 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-14 | 2024-09-25 | Unknown | Unknown | 2024-09-25 | 2024-10-23 | 29 | 21 | 2024-10-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2024-01-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-06 | 2023-10-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 10785.7 | Unknown | Unknown | Yes | N/A | N/A | 2023-02-06 | 2023-04-17 | 71 | 51 | 2023-04-17 | 2024-01-16 | 275 | 197 | Unknown | Unknown | Unknown | Unknown | 2023-10-10 | 2024-01-19 | 15 | 13 | 2024-01-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | 15 | 15 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-09 | 2024-08-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1138.57 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-09 | 2024-07-30 | Unknown | Unknown | 2024-07-30 | 2024-08-09 | 11 | 9 | 2024-08-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-09 | 2025-07-10 | 336 | 240 | Unknown | 2025-07-02 | Unknown | Unknown | 2025-07-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 12 | 12 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-22 | 2024-07-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1336.34 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-22 | 2024-06-18 | Unknown | Unknown | 2024-06-18 | 2024-08-06 | 50 | 36 | 2024-08-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CORONADO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-30 | 2024-01-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 498.51 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-30 | 2025-04-18 | 445 | 319 | 2025-04-18 | 2025-05-09 | 22 | 16 | 2025-04-16 | 2025-05-13 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | 2025-05-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | OCEANSIDE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-10 | 2023-10-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 957.49 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-10 | 2023-10-23 | 14 | 10 | 2023-10-23 | 2023-10-23 | 1 | 1 | 2023-10-23 | Unknown | Unknown | Unknown | 2023-10-23 | 2023-11-03 | 12 | 10 | 2023-10-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2018-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-23 | 2025-01-08 | 2025-05-30 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1507.85 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-23 | 2025-01-08 | 17 | 13 | 2025-01-08 | 2025-04-09 | 92 | 66 | Unknown | Unknown | Unknown | Unknown | 2024-12-24 | 2024-12-27 | 4 | 4 | 2025-04-09 | 2025-04-03 | Unknown | Unknown | Unknown | 2025-05-23 | Unknown | Unknown | 2025-05-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-03 | 2025-04-11 | 2025-04-26 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 4583.66 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-03 | 2025-04-10 | 8 | 6 | 2025-04-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 197.05 | 197.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-25 | 2024-04-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1001.92 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-25 | 2024-04-03 | 10 | 8 | 2024-04-03 | 2024-04-12 | 10 | 8 | 2024-04-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-12 | 2025-07-24 | 469 | 335 | Unknown | 2025-08-19 | Unknown | Unknown | 2025-07-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | CARLSBAD | N/A | 12 | 12 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-27 | 2025-03-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1449.66 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-27 | 2025-03-27 | 29 | 21 | 2025-03-27 | 2025-03-28 | 2 | 2 | 2025-03-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-18 | 2025-02-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 59623.63 | 17938.82 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-18 | 2025-02-18 | 1 | 1 | 2025-02-18 | 2025-05-07 | 79 | 57 | Unknown | Unknown | Unknown | Unknown | 2025-02-18 | 2025-03-14 | 25 | 19 | 2025-05-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-16 | Unknown | Unknown | No | 2025-02-19 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-19 | 2025-02-20 | Unknown | IOU Designed & Installed | N/A | Yes | 119 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1064.83 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-19 | 2025-06-18 | 120 | 86 | 2025-06-18 | 2025-02-20 | Unknown | Unknown | 2025-02-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SANTEE | N/A | 31 | 31 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-29 | 2024-05-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 186.4 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-29 | 2024-04-23 | Unknown | Unknown | 2024-04-23 | 2024-06-11 | 50 | 36 | 2024-06-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | 76.1 | 76.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-24 | 2025-03-31 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 671.74 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-24 | 2025-05-01 | 39 | 29 | 2025-05-01 | 2025-05-01 | 1 | 1 | 2025-05-01 | 2025-05-05 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | 2025-05-06 | Unknown | Unknown | Unknown | Unknown | 2025-06-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 1087.05 | 1087.05 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2026-01-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-15 | 2024-05-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1781.14 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-15 | 2024-06-28 | 45 | 33 | 2024-06-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-06 | 2024-02-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 934 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-06 | 2024-02-05 | Unknown | Unknown | 2024-02-05 | 2024-02-06 | 2 | 2 | 2024-02-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 151 | 151 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-02 | 2023-11-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1255.57 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-02 | 2023-03-02 | Unknown | Unknown | 2023-03-02 | 2024-01-24 | 329 | 235 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-24 | 2025-08-06 | 561 | 401 | Unknown | 2025-07-29 | Unknown | Unknown | 2025-08-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-29 | 2025-04-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1151.76 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-29 | 2025-04-17 | Unknown | Unknown | 2025-04-17 | 2025-05-13 | 27 | 19 | 2025-05-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | BONSALL | N/A | 48 | 48 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-25 | 2024-08-14 | 2024-12-16 | IOU Designed & Installed | N/A | No | Unknown | 6981.98 | 1019.62 | Unknown | 356.47 | 353.45 | 5252.44 | 3981 | 748.61 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-25 | 2024-07-11 | Unknown | Unknown | 2024-07-11 | 2024-09-05 | 57 | 41 | 2024-09-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-05 | 2024-12-16 | 103 | 73 | Unknown | 2024-12-16 | Unknown | Unknown | 2024-12-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2026-03-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-21 | 2024-03-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 54899 | 81.53 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-21 | 2024-08-08 | 141 | 101 | 2024-08-08 | 2024-08-29 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | 2024-03-27 | 2024-07-16 | 54 | 40 | 2024-08-29 | Unknown | Unknown | Unknown | Unknown | 2025-07-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-21 | 2023-03-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 539.65 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-21 | 2023-03-27 | 7 | 5 | 2023-03-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | EL CAJON | EL CAJON | 81.12 | 81.12 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-09 | 2024-10-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 28441 | 4103.59 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-09 | 2025-01-29 | 113 | 81 | 2025-01-29 | 2025-01-29 | 1 | 1 | 2024-10-23 | 2025-01-06 | 76 | 54 | 2024-10-09 | 2025-02-15 | 56 | 41 | 2025-01-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-08 | 2023-08-21 | 2023-09-14 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 611.74 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-08 | 2023-08-21 | 14 | 10 | 2023-08-21 | 2023-08-21 | 1 | 1 | 2023-08-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-21 | 2023-09-14 | 25 | 19 | Unknown | Unknown | Unknown | Unknown | 2023-09-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | 9.05 | 9.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-23 | 2025-01-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2653.18 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-23 | 2025-02-13 | 22 | 16 | 2025-02-13 | 2025-03-25 | 41 | 29 | Unknown | Unknown | Unknown | Unknown | 2025-01-27 | 2025-02-13 | 18 | 14 | 2025-03-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2022-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-24 | 2025-04-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 4432.06 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-24 | 2025-04-15 | 327 | 233 | 2025-04-15 | 2025-06-11 | 58 | 42 | Unknown | Unknown | Unknown | Unknown | 2025-04-16 | 2025-04-28 | 13 | 9 | 2025-06-11 | 2025-08-28 | 79 | 57 | Unknown | Unknown | Unknown | Unknown | 2025-08-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-26 | 2024-09-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 27449 | 2553.5 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-26 | 2024-10-03 | 8 | 6 | 2024-10-03 | 2024-10-03 | 1 | 1 | 2024-10-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 5 | 5 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-16 | 2024-05-16 | 2024-09-10 | IOU Designed & Installed | N/A | No | Unknown | 1501 | 0 | Unknown | Unknown | 137.57 | 1363.43 | 3941 | 1353.81 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-16 | 2024-07-24 | 70 | 50 | 2024-07-24 | 2024-07-24 | 1 | 1 | 2024-07-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-24 | 2024-09-10 | 49 | 35 | Unknown | Unknown | Unknown | Unknown | 2024-09-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | N/A | San Diego | San Diego | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-13 | 2025-02-13 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 26147.3 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-13 | 2025-04-02 | 49 | 35 | 2025-04-02 | 2025-06-03 | 63 | 45 | 2025-04-17 | 2025-06-16 | 25 | 19 | 2025-03-07 | 2025-06-26 | 44 | 32 | 2025-06-10 | Unknown | Unknown | Unknown | 2025-06-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-05 | 2025-06-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2875.23 | 334.17 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-05 | 2025-06-09 | 5 | 3 | 2025-06-09 | 2025-07-14 | 36 | 26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-07-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-29 | 2024-01-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 729.47 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-29 | 2024-02-20 | 23 | 17 | 2024-02-20 | 2024-02-23 | 4 | 4 | 2024-02-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-15 | 2025-01-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 1026910 | 38279.87 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-15 | 2025-01-21 | 7 | 5 | 2025-01-21 | 2025-05-13 | 113 | 81 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-13 | Unknown | Unknown | Unknown | Unknown | 2025-08-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 106.2 | 106.2 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-26 | 2025-03-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 15924 | 2083.37 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-26 | 2025-04-29 | 35 | 25 | 2025-04-29 | 2025-05-12 | 14 | 10 | 2025-03-28 | 2025-04-29 | 33 | 23 | 2025-04-29 | 2025-05-16 | 18 | 14 | 2025-05-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | OH | IOU Design | Residential | N/A | Rancho Santa Fe | COUNTY OF SAN DIEGO-NORTH of 56 | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2024-08-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-14 | 2024-07-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 67036.03 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-14 | 2024-02-05 | 176 | 126 | 2024-02-05 | 2025-04-08 | 429 | 307 | 2025-08-28 | 2025-08-28 | 1 | 1 | 2025-02-28 | 2025-03-18 | 19 | 13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 39.05 | 39.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-20 | 2024-05-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 186.4 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-20 | 2024-06-13 | 25 | 19 | 2024-06-13 | 2024-06-13 | 1 | 1 | 2024-06-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-07-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-26 | 2023-09-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2385527 | 81647.86 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-26 | 2023-11-20 | 118 | 84 | 2023-11-20 | 2024-10-17 | 333 | 239 | 2024-05-15 | 2024-05-15 | 1 | 1 | 2024-09-04 | 2024-10-04 | 31 | 23 | 2024-10-17 | Unknown | Unknown | Unknown | 2024-11-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-30 | 2024-06-14 | 2024-06-26 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 984.98 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-30 | 2024-06-14 | 16 | 12 | 2024-06-14 | 2024-06-14 | 1 | 1 | 2024-06-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-14 | 2024-06-26 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2024-06-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | POWAY | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2022-03-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-21 | 2023-03-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 416.1 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-21 | 2023-03-21 | 1 | 1 | 2023-03-21 | 2023-06-20 | 92 | 66 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | ALPINE | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2024-05-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-22 | 2023-05-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 7007.57 | Unknown | Unknown | Yes | N/A | N/A | 2023-05-22 | 2023-05-22 | 1 | 1 | 2023-05-22 | 2023-05-23 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-23 | Unknown | Unknown | Unknown | Unknown | 2024-08-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SANTEE | SANTEE | 9.05 | 9.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-31 | 2025-03-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | 669.14 | 85.06 | Unknown | Unknown | 7.98 | 576.1 | 3981 | 1931.42 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-31 | 2025-03-11 | 40 | 28 | 2025-03-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-04 | 2025-06-24 | 82 | 58 | 2025-04-17 | 2025-07-08 | 83 | 59 | Unknown | Unknown | Unknown | Unknown | 2025-07-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 42 | 42 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-09 | 2023-11-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 809.45 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-09 | 2023-10-05 | Unknown | Unknown | 2023-10-05 | 2023-11-09 | 36 | 26 | 2023-11-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN JUAN CAPISTRANO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-15 | 2024-10-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | 2045.57 | -21.76 | Unknown | Unknown | 34.54 | 2032.79 | 3981 | 1102.56 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-15 | 2024-12-18 | 65 | 47 | 2024-12-18 | 2025-01-03 | 17 | 13 | 2025-01-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-03 | Unknown | Unknown | Unknown | Unknown | 2025-02-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-30 | 2024-07-31 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 5087.19 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-30 | 2024-10-05 | 68 | 49 | 2024-10-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 230 | 230 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-01 | 2024-04-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1431.53 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-01 | 2024-04-11 | 11 | 9 | 2024-04-11 | 2024-12-09 | 243 | 173 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-09 | 2025-09-05 | 271 | 195 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | Applicant Design | Residential | Underserved Community | JAMUL | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-05-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-17 | 2025-01-16 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 778.74 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-17 | 2025-01-16 | 31 | 23 | 2025-01-16 | 2025-03-06 | 50 | 36 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-06 | Unknown | Unknown | Unknown | Unknown | 2025-05-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-24 | 2024-06-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1455.49 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-24 | 2024-05-16 | Unknown | Unknown | 2024-05-16 | 2024-06-28 | 44 | 32 | 2024-06-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 200 | 200 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-14 | 2024-10-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2764.2 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-14 | 2024-11-12 | 30 | 22 | 2024-11-12 | 2024-11-18 | 7 | 5 | 2024-11-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-18 | 2025-09-03 | 290 | 208 | Unknown | 2025-08-26 | Unknown | Unknown | 2025-09-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-30 | 2024-09-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 38422.03 | 36290.93 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-30 | 2024-08-30 | 1 | 1 | 2024-08-30 | 2025-06-02 | 277 | 197 | 2024-11-19 | 2024-11-20 | 2 | 2 | 2024-12-10 | 2025-06-10 | 59 | 43 | 2025-06-02 | Unknown | Unknown | Unknown | 2025-06-16 | 2025-08-18 | 64 | 46 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Residential | N/A | Rancho Mission Viejo | COUNTY OF ORANGE | 106.1 | 106.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-06-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-03 | 2024-08-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 138153.49 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-03 | 2024-06-26 | Unknown | Unknown | 2024-06-26 | 2025-03-14 | 262 | 188 | 2024-10-21 | 2025-03-12 | 11 | 9 | 2024-11-21 | 2025-03-17 | 23 | 15 | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-20 | Unknown | Unknown | 2025-07-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LA MESA | COUNTY OF SAN DIEGO-SOUTH of 56 | 76.25 | 76.25 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-14 | 2024-03-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1820.15 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-14 | 2024-03-19 | 35 | 25 | 2024-03-19 | 2024-08-14 | 149 | 107 | Unknown | Unknown | Unknown | Unknown | 2024-04-09 | 2024-04-29 | 21 | 15 | 2024-08-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-06 | 2023-04-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1082.79 | Unknown | Unknown | Yes | N/A | N/A | 2023-04-06 | 2023-08-29 | 146 | 104 | 2023-08-29 | 2023-09-19 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | 2023-05-18 | 2023-06-01 | 15 | 11 | 2023-09-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-11 | 2024-11-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 252774.53 | 13864.91 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-11 | 2024-02-21 | Unknown | Unknown | 2024-02-21 | 2025-05-02 | 437 | 313 | Unknown | Unknown | Unknown | Unknown | 2024-11-21 | 2025-01-01 | 42 | 30 | 2025-05-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-01 | 2024-08-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 28804 | 494.79 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-01 | 2024-08-19 | 19 | 13 | 2024-08-19 | 2024-08-19 | 1 | 1 | 2024-08-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 14.75 | 14.75 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-21 | 2025-04-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1442.8 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-21 | 2025-04-08 | 19 | 13 | 2025-04-08 | 2025-04-14 | 7 | 5 | 2025-04-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ALPINE | N/A | 35 | 35 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-03 | 2025-04-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2532.24 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-03 | 2025-02-14 | Unknown | Unknown | 2025-02-14 | 2025-05-23 | 99 | 71 | 2025-05-23 | 2025-06-23 | 32 | 22 | Unknown | Unknown | Unknown | Unknown | 2025-06-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN MARCOS | N/A | 67.05 | 67.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-08 | 2024-09-26 | 2024-12-27 | IOU Designed & Installed | N/A | No | Unknown | 98.98 | 0 | Unknown | Unknown | 45.19 | 53.79 | 3981 | 2339.32 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-08 | 2024-04-25 | 18 | 14 | 2024-04-25 | 2024-09-26 | 155 | 111 | 2024-09-25 | 2024-10-15 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | 2024-10-15 | 2024-12-27 | 74 | 54 | Unknown | 2024-12-18 | Unknown | Unknown | 2024-12-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-06-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-26 | 2025-06-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 967.27 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-26 | 2025-06-26 | 1 | 1 | 2025-06-26 | 2025-06-26 | 1 | 1 | 2025-06-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-26 | 2025-09-10 | 77 | 55 | Unknown | Unknown | Unknown | Unknown | 2025-09-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | BONITA | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-04 | 2025-03-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1642.93 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-04 | 2025-02-28 | Unknown | Unknown | 2025-02-28 | 2025-03-04 | 5 | 3 | 2025-03-04 | 2025-06-04 | 2 | 2 | 2025-03-04 | 2025-06-06 | 11 | 3 | 2025-03-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | LA MESA | LA MESA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-07 | 2025-02-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 126707.82 | 51578.05 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-07 | 2025-04-08 | 61 | 43 | 2025-04-08 | 2025-06-11 | 65 | 47 | 2025-04-14 | 2025-04-21 | 8 | 6 | 2025-04-21 | 2025-06-09 | 27 | 19 | 2025-06-11 | Unknown | Unknown | Unknown | 2025-06-19 | 2025-08-28 | 71 | 51 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2026-03-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-21 | 2024-03-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 54899 | 81.53 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-21 | 2024-08-16 | 149 | 107 | 2024-08-16 | 2025-06-03 | 292 | 208 | Unknown | Unknown | Unknown | Unknown | 2024-03-27 | 2024-07-16 | 54 | 40 | 2025-06-03 | Unknown | Unknown | Unknown | Unknown | 2025-07-01 | Unknown | Unknown | 2025-07-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 6799.45 | 6799.45 | Not Available | >2MW | No | N/A | N/A | N/A | 2026-10-28 | Unknown | Unknown | No | 2024-11-14 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-14 | 2024-11-14 | Unknown | IOU Designed & Installed | N/A | Yes | 124 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1570.98 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-14 | 2025-03-14 | 121 | 87 | 2025-03-14 | 2025-03-18 | 5 | 3 | 2025-03-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-28 | 2025-04-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3601.84 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-28 | 2025-04-24 | Unknown | Unknown | 2025-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Disadvantaged Community,Underserved Community | NATIONAL CITY | NATIONAL CITY | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-23 | 2023-02-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 26990 | 1396.19 | Unknown | Unknown | Yes | N/A | N/A | 2023-01-23 | 2023-02-27 | 36 | 26 | 2023-02-27 | Unknown | Unknown | Unknown | 2024-02-29 | 2024-03-21 | 22 | 16 | 2023-08-24 | 2025-05-19 | 73 | 53 | 2023-12-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | CARDIFF | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-03 | 2025-05-01 | 2025-05-22 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1711.96 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-03 | 2025-03-07 | 95 | 69 | 2025-03-07 | 2025-06-06 | 92 | 66 | 2025-06-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-01 | 2025-05-22 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | 2025-05-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-01 | 2024-10-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1856.85 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-01 | 2024-10-11 | 11 | 9 | 2024-10-11 | 2025-01-22 | 104 | 74 | Unknown | Unknown | Unknown | Unknown | 2024-10-11 | 2024-11-11 | 32 | 22 | 2025-01-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-08-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-08 | 2023-08-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1479.5 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-08 | 2023-08-09 | 2 | 2 | 2023-08-09 | 2023-08-16 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2023-08-10 | 2023-08-18 | 9 | 7 | 2023-08-16 | 2023-08-22 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | POWAY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-24 | 2024-10-24 | 2024-11-23 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3484.1 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-24 | 2024-10-24 | 1 | 1 | 2024-10-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 69.1 | 69.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-05 | 2024-11-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7962 | 1472.78 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-05 | 2025-07-31 | 269 | 193 | 2025-07-31 | 2025-06-06 | Unknown | Unknown | 2025-04-16 | 2025-06-06 | 52 | 38 | 2025-08-15 | 2025-08-15 | 1 | 1 | 2025-06-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 14 | 14 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-28 | 2024-03-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3941 | 1754.08 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-28 | 2024-03-07 | Unknown | Unknown | 2024-03-07 | 2024-03-28 | 22 | 16 | 2024-03-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | 5 | 5 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-05 | 2025-01-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2985 | 1592.76 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-05 | 2025-01-06 | 63 | 45 | 2025-01-06 | 2025-02-11 | 37 | 27 | Unknown | Unknown | Unknown | Unknown | 2025-01-31 | 2025-02-24 | 25 | 17 | 2025-02-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 3.35 | 3.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-08-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-13 | 2025-02-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1215.3 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-13 | 2025-03-06 | 22 | 16 | 2025-03-06 | 2025-03-17 | 12 | 8 | 2025-03-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-11 | 2024-06-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 27587 | 1229.28 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-11 | 2024-04-09 | Unknown | Unknown | 2024-04-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-13 | Unknown | Unknown | Unknown | Unknown | 2025-09-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | OCEANSIDE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-05 | 2024-01-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 158.37 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-05 | 2024-01-23 | 19 | 13 | 2024-01-23 | 2024-01-31 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | 2024-01-23 | 2024-02-09 | 18 | 14 | 2024-01-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SOLANA BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-09 | 2024-04-09 | Unknown | Customer elected Applicant Install | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 567204 | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2024-04-09 | 2024-03-18 | Unknown | Unknown | 2024-03-18 | 2024-07-05 | 110 | 80 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 37.05 | 37.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-31 | 2024-07-08 | 2024-07-22 | IOU Designed & Installed | N/A | No | Unknown | 139.47 | 0 | Unknown | Unknown | 72.33 | 67.14 | 3981 | 1427.91 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-31 | 2024-07-08 | 39 | 27 | 2024-07-08 | 2024-07-08 | 1 | 1 | 2024-07-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-08 | 2024-07-22 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2024-07-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2022-02-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-02 | 2024-04-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2168.63 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-02 | 2024-04-03 | 2 | 2 | 2024-04-03 | 2024-05-14 | 42 | 30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-14 | 2025-08-25 | 469 | 335 | Unknown | Unknown | Unknown | Unknown | 2025-08-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-31 | 2025-04-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2174.52 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-31 | 2025-04-03 | 4 | 4 | 2025-04-03 | 2025-04-04 | 2 | 2 | 2025-04-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-16 | 2025-01-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 3027.78 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-16 | 2025-04-01 | 76 | 54 | 2025-04-01 | 2025-04-08 | 8 | 6 | 2025-04-08 | 2025-06-25 | 79 | 57 | Unknown | Unknown | Unknown | Unknown | 2025-06-25 | 2025-07-01 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2025-07-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | RAMONA | N/A | 13 | 13 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-04 | 2023-10-04 | 2023-12-12 | IOU Designed & Installed | N/A | No | Unknown | 1559.4 | 367.35 | Unknown | 333.2 | 69.58 | 789.27 | 3981 | 965.81 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-04 | 2023-10-17 | 14 | 10 | 2023-10-17 | 2023-10-10 | Unknown | Unknown | 2023-10-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-17 | 2023-12-12 | 57 | 41 | Unknown | Unknown | Unknown | Unknown | 2023-12-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-04 | 2025-04-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1579.49 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-04 | 2025-03-20 | Unknown | Unknown | 2025-03-20 | 2025-04-04 | 16 | 12 | 2025-04-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CORONADO | N/A | 102.05 | 102.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-10 | 2023-08-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 270.36 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-10 | 2023-08-10 | 1 | 1 | 2023-08-10 | 2023-08-10 | 1 | 1 | 2023-08-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-28 | 2024-11-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 33635 | 2614.55 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-28 | 2025-05-20 | 205 | 147 | 2025-05-20 | 2025-07-01 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | 2025-05-20 | 2025-06-11 | 23 | 17 | 2025-07-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | 7.05 | 7.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-20 | 2024-06-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2192.26 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-20 | 2024-04-05 | Unknown | Unknown | 2024-04-05 | 2024-06-20 | 77 | 55 | 2024-06-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | 45.05 | 45.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-05 | Unknown | Unknown | No | 2024-12-02 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-02 | 2024-12-03 | Unknown | IOU Designed & Installed | N/A | Yes | 137 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1066.55 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-02 | 2025-04-17 | 137 | 99 | 2025-04-17 | 2024-12-03 | Unknown | Unknown | 2024-12-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-03 | 2025-08-20 | 261 | 187 | Unknown | Unknown | Unknown | Unknown | 2025-08-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CORONADO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-19 | 2025-03-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | 40.1 | 0 | Unknown | Unknown | 6 | 34.1 | 0 | 1434.84 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-19 | 2025-03-05 | Unknown | Unknown | 2025-03-05 | 2025-03-20 | 16 | 12 | 2025-03-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-20 | 2025-07-02 | 105 | 75 | Unknown | Unknown | Unknown | Unknown | 2025-07-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-15 | 2023-08-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 618.58 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-15 | 2023-08-21 | 7 | 5 | 2023-08-21 | 2023-08-21 | 1 | 1 | 2023-08-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | N/A | 272 | 272 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-17 | 2024-04-23 | 2024-06-05 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3961 | 162.34 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-17 | 2024-03-21 | Unknown | Unknown | 2024-03-21 | 2024-05-06 | 47 | 33 | 2024-05-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-06 | 2024-06-05 | 31 | 23 | Unknown | 2024-06-03 | Unknown | Unknown | 2024-06-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-24 | 2025-04-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 1786 | 761.77 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-24 | 2025-04-25 | 2 | 2 | 2025-04-25 | 2025-04-25 | 1 | 1 | 2025-04-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 5 | 5 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-09 | 2024-10-09 | 2024-11-12 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1664.96 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-09 | 2024-08-29 | Unknown | Unknown | 2024-08-29 | 2024-10-16 | 49 | 35 | 2024-10-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-16 | 2024-11-12 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | 2024-11-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | POWAY | N/A | 68.05 | 68.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-06 | 2025-05-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 117.42 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-06 | 2025-06-12 | 38 | 28 | 2025-06-12 | 2025-06-17 | 6 | 4 | 2025-06-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-17 | 2025-07-29 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | 2025-07-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | 794 | 794 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-14 | 2025-03-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1956.39 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-14 | 2025-03-24 | 11 | 7 | 2025-03-24 | 2025-03-21 | Unknown | Unknown | 2025-03-21 | 2025-03-24 | 4 | 2 | Unknown | Unknown | Unknown | Unknown | 2025-03-24 | Unknown | Unknown | Unknown | Unknown | 2025-05-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | IOU Design | Residential | N/A | ALPINE | COUNTY OF SAN DIEGO-SOUTH of 56 | 58 | 58 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-02 | 2024-07-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 620 | 32716.56 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-02 | 2024-09-09 | 161 | 115 | 2024-09-09 | 2024-12-05 | 88 | 64 | 2024-07-19 | 2024-12-04 | 84 | 60 | 2024-08-12 | 2024-12-16 | 21 | 15 | 2024-12-05 | Unknown | Unknown | Unknown | 2025-01-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-11 | 2024-04-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3941 | 1074.85 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-11 | 2024-06-11 | 62 | 44 | 2024-06-11 | 2024-06-11 | 1 | 1 | 2024-06-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2025-12-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-27 | 2025-01-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7962 | 1642.84 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-27 | 2025-01-02 | 7 | 5 | 2025-01-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-03 | 2025-01-07 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-09 | 2024-02-09 | 2024-02-14 | IOU Designed & Installed | N/A | No | Unknown | 887.22 | 468.58 | Unknown | 81.4 | Unknown | 337.24 | 0 | 163.83 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-09 | 2024-02-09 | 1 | 1 | 2024-02-09 | 2024-02-09 | 1 | 1 | 2024-02-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-09 | 2024-02-14 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2024-02-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CARDIFF | N/A | 31 | 31 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | 2025-04-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1422.73 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-07 | 2025-04-17 | 11 | 9 | 2025-04-17 | 2025-04-17 | 1 | 1 | 2025-04-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-17 | 2025-07-01 | 76 | 54 | Unknown | 2025-06-24 | Unknown | Unknown | 2025-07-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-24 | 2023-01-24 | 2025-02-18 | IOU Designed & Installed | N/A | No | Unknown | 8805.23 | 2054.59 | Unknown | 24.25 | -1678.83 | 8405.22 | 0 | 1920.78 | Unknown | Unknown | Yes | N/A | N/A | 2023-01-24 | 2023-02-27 | 35 | 25 | 2023-02-27 | 2023-12-15 | 292 | 210 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-03 | Unknown | Unknown | 2025-02-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2018-03-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-09 | 2024-09-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1023.72 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-09 | 2024-08-08 | Unknown | Unknown | 2024-08-08 | 2024-09-09 | 33 | 23 | 2024-09-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-30 | 2025-04-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 17151.8 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-30 | 2025-03-03 | 613 | 437 | 2025-03-03 | 2025-06-16 | 106 | 76 | 2025-04-09 | 2025-04-23 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2025-06-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2018-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-30 | 2024-10-31 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 104.74 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-30 | 2024-10-31 | 2 | 2 | 2024-10-31 | 2025-06-11 | 224 | 160 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-15 | 2025-01-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2154 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-15 | 2025-01-07 | 85 | 61 | 2025-01-07 | 2025-06-24 | 169 | 121 | Unknown | Unknown | Unknown | Unknown | 2025-01-07 | 2025-01-28 | 22 | 16 | 2025-06-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-07-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | 25.05 | 25.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-11 | Unknown | Unknown | No | 2025-03-31 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-31 | 2025-04-01 | Unknown | IOU Designed & Installed | N/A | Yes | 49 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1173.06 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-31 | 2025-04-30 | 31 | 23 | 2025-04-30 | 2025-05-19 | 20 | 14 | 2025-05-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | National City | NATIONAL CITY | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-29 | 2023-10-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 36006 | 11702.72 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-29 | 2023-09-29 | 1 | 1 | 2023-09-29 | 2024-07-24 | 300 | 214 | 2024-01-05 | 2024-04-05 | 47 | 35 | 2024-03-08 | 2024-05-09 | 55 | 39 | 2024-07-24 | Unknown | Unknown | Unknown | 2025-08-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-30 | 2024-04-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1063.89 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-30 | 2024-03-07 | Unknown | Unknown | 2024-03-07 | 2024-08-08 | 155 | 111 | 2024-08-08 | 2025-06-25 | 322 | 230 | Unknown | Unknown | Unknown | Unknown | 2025-06-25 | Unknown | Unknown | Unknown | Unknown | 2025-08-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-14 | 2024-08-14 | 2025-06-20 | IOU Designed & Installed | N/A | No | Unknown | 2819.74 | 0 | Unknown | Unknown | 32.76 | 2786.98 | 0 | 1172.14 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-14 | 2025-03-05 | 204 | 146 | 2025-03-05 | 2025-03-10 | 6 | 4 | 2025-03-10 | 2025-03-31 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | 2025-03-31 | 2025-06-20 | 82 | 60 | Unknown | 2025-06-20 | Unknown | Unknown | 2025-06-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 98.05 | 98.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-09 | 2025-05-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1250.63 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-09 | 2025-04-25 | Unknown | Unknown | 2025-04-25 | 2025-05-16 | 22 | 16 | 2025-05-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | Both | IOU Design | Commercial | N/A | Santee | SANTEE | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2020-11-19 | Unknown | Unknown | No | 2023-02-28 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-28 | 2023-03-29 | Unknown | IOU Designed & Installed | N/A | Yes | 336 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 9234.61 | Unknown | Unknown | Yes | N/A | N/A | 2023-02-28 | 2023-12-18 | 294 | 210 | 2023-12-18 | 2024-07-16 | 212 | 152 | Unknown | Unknown | Unknown | Unknown | 2024-01-30 | 2024-04-22 | 12 | 10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-12 | 2024-03-12 | 2024-03-29 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 874.97 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-12 | 2024-02-01 | Unknown | Unknown | 2024-02-01 | 2024-03-12 | 41 | 29 | 2024-03-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-12 | 2024-03-29 | 18 | 14 | Unknown | Unknown | Unknown | Unknown | 2024-03-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 135.05 | 135.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-05-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-11 | 2023-05-11 | 2023-11-16 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 431.54 | Unknown | Unknown | Yes | N/A | N/A | 2023-05-11 | 2023-07-24 | 75 | 53 | 2023-07-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-24 | 2023-11-16 | 116 | 84 | Unknown | 2023-09-28 | Unknown | Unknown | 2023-11-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-27 | 2025-03-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 812.25 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-27 | 2025-05-29 | 92 | 66 | 2025-05-29 | 2025-05-29 | 1 | 1 | 2025-05-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-24 | Unknown | Unknown | No | 2023-09-13 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-13 | 2023-09-13 | Unknown | IOU Designed & Installed | N/A | Yes | 432 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 9749 | 1027.17 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-13 | 2024-11-22 | 437 | 313 | 2024-11-22 | 2024-02-08 | Unknown | Unknown | 2024-02-08 | 2024-11-18 | 285 | 203 | Unknown | Unknown | Unknown | Unknown | 2024-02-08 | 2025-08-15 | 555 | 397 | Unknown | Unknown | Unknown | Unknown | 2025-08-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 62 | 62 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-11 | 2024-04-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 12569.23 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-11 | 2024-04-10 | Unknown | Unknown | 2024-04-10 | 2024-11-11 | 216 | 154 | 2024-04-25 | 2024-04-25 | 1 | 1 | 2024-11-20 | 2024-11-26 | 7 | 5 | 2024-11-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | VALLEY CENTER | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-20 | 2023-07-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 775.76 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-20 | 2023-06-21 | Unknown | Unknown | 2023-06-21 | 2023-08-15 | 56 | 40 | 2023-08-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-08-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-05 | 2023-09-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3754 | 405.8 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-05 | 2023-04-18 | Unknown | Unknown | 2023-04-18 | 2023-09-15 | 151 | 109 | 2023-09-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2021-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-13 | 2024-10-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3433.29 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-13 | 2024-10-21 | 70 | 50 | 2024-10-21 | 2024-12-05 | 46 | 34 | Unknown | Unknown | Unknown | Unknown | 2024-10-22 | 2024-11-19 | 29 | 21 | 2024-12-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 98.05 | 98.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-01 | 2025-05-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 996.16 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-01 | 2025-04-14 | Unknown | Unknown | 2025-04-14 | 2025-05-16 | 33 | 25 | 2025-05-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-16 | 2025-09-05 | 113 | 81 | Unknown | Unknown | Unknown | Unknown | 2025-09-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-21 | 2025-01-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2035.01 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-21 | 2024-12-09 | Unknown | Unknown | 2024-12-09 | 2025-01-21 | 44 | 32 | 2025-01-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | ESCONDIDO | 64 | 64 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-24 | 2025-01-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 5180.47 | 5220.97 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-24 | 2025-02-20 | 28 | 20 | 2025-02-20 | Unknown | Unknown | Unknown | 2025-07-23 | 2025-08-20 | 29 | 19 | 2025-04-18 | 2025-06-05 | 19 | 13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | Underserved Community | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2021-10-01 | 2021-10-01 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 215338.77 | Unknown | Unknown | Yes | N/A | N/A | 2021-10-01 | 2024-03-22 | 904 | 646 | 2024-03-22 | 2024-11-06 | 230 | 164 | 2024-04-05 | 2025-01-14 | 169 | 121 | 2023-12-07 | 2024-12-12 | 61 | 43 | 2024-11-12 | Unknown | Unknown | Unknown | 2024-11-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | IOU Design | Residential | Underserved Community | RAMONA | COUNTY OF SAN DIEGO-NORTH of 56 | 449.05 | 449.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-08 | 2024-03-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 30082.65 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-08 | 2024-03-14 | 36 | 26 | 2024-03-14 | 2024-11-25 | 257 | 183 | 2024-05-28 | 2024-11-22 | 94 | 69 | 2024-07-25 | 2024-11-27 | 14 | 10 | 2024-11-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LA MESA | LA MESA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-13 | 2024-05-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 11943 | 1595.5 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-13 | 2024-05-15 | 3 | 3 | 2024-05-15 | 2024-06-05 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | 2024-05-24 | 2024-06-26 | 34 | 24 | 2024-06-05 | 2025-08-19 | 441 | 315 | Unknown | Unknown | Unknown | Unknown | 2025-08-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-25 | 2025-04-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 468.83 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-25 | 2025-04-28 | 4 | 2 | 2025-04-28 | 2025-05-07 | 10 | 8 | 2025-05-07 | 2025-05-13 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2025-05-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | JAMUL | N/A | 132.05 | 132.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-02 | 2023-08-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1002.01 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-02 | 2023-02-28 | Unknown | Unknown | 2023-02-28 | 2023-10-05 | 220 | 158 | 2023-10-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-05 | 2025-08-18 | 684 | 488 | Unknown | 2025-07-21 | Unknown | Unknown | 2025-08-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-04 | 2024-12-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1674.13 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-04 | 2024-12-03 | Unknown | Unknown | 2024-12-03 | 2024-12-09 | 7 | 5 | 2024-12-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-09 | 2025-08-05 | 240 | 172 | Unknown | 2025-07-18 | Unknown | Unknown | 2025-08-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-12 | Unknown | Unknown | No | 2024-04-24 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-24 | 2024-04-24 | Unknown | IOU Designed & Installed | N/A | Yes | 14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 779.89 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-24 | 2024-05-08 | 15 | 11 | 2024-05-08 | 2024-05-08 | 1 | 1 | 2024-05-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | LEMON GROVE | N/A | 25 | 25 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-28 | 2025-05-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3661.75 | 1320.87 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-28 | 2025-05-28 | 1 | 1 | 2025-05-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | 222214 | 222214 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-03-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-20 | 2024-07-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1571.77 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-20 | 2024-06-12 | Unknown | Unknown | 2024-06-12 | 2024-09-18 | 99 | 71 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 9.05 | 9.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-08 | 2025-01-08 | 2025-01-29 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2058.19 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-08 | 2024-12-23 | Unknown | Unknown | 2024-12-23 | 2025-01-08 | 17 | 13 | 2025-01-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-08 | 2025-01-29 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | 2025-01-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 667.4 | 667.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-24 | 2024-05-24 | 2024-06-13 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1447.02 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-24 | 2024-05-24 | 1 | 1 | 2024-05-24 | 2024-05-24 | 1 | 1 | 2024-05-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-24 | 2024-06-13 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | 2024-06-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | Underserved Community | OC 1086-G3 Summerwell WO4 (E) | OCEANSIDE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-23 | 2022-09-23 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 297664 | 206115.92 | Unknown | Unknown | Yes | N/A | N/A | 2022-09-23 | 2024-09-27 | 736 | 526 | 2024-09-27 | 2025-02-12 | 139 | 99 | 2024-11-07 | 2025-02-07 | 61 | 45 | 2025-02-13 | 2025-02-20 | 8 | 6 | 2025-07-03 | Unknown | Unknown | Unknown | 2025-07-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN JUAN CAPISTRANO | N/A | 309.05 | 309.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-07 | 2025-01-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1657.84 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-07 | 2025-02-13 | 38 | 28 | 2025-02-13 | 2025-02-19 | 7 | 5 | 2025-02-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-19 | 2025-09-03 | 197 | 141 | Unknown | 2025-08-08 | Unknown | Unknown | 2025-09-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SANTEE | N/A | 139 | 139 | Not Available | <1MW | No | N/A | N/A | N/A | 2021-04-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-20 | 2024-06-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 6293 | 3162.12 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-20 | 2024-06-21 | 2 | 2 | 2024-06-21 | 2024-10-31 | 133 | 95 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-27 | 2023-10-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 482.72 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-27 | 2023-10-27 | 1 | 1 | 2023-10-27 | 2023-12-06 | 41 | 29 | 2023-10-27 | 2023-10-31 | 5 | 3 | 2023-10-31 | 2023-11-02 | 3 | 3 | 2023-12-06 | 2025-03-18 | 469 | 335 | Unknown | 2025-08-20 | Unknown | Unknown | 2025-08-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CARDIFF | ENCINITAS | 195 | 195 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-27 | 2025-04-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3132.86 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-27 | 2025-04-01 | 6 | 4 | 2025-04-01 | 2025-04-03 | 3 | 3 | 2025-04-03 | 2025-05-27 | 55 | 39 | 2025-04-07 | 2025-04-29 | 23 | 17 | 2025-04-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 44 | 44 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-18 | 2025-02-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2166.77 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-18 | 2025-02-05 | Unknown | Unknown | 2025-02-05 | 2025-05-07 | 92 | 66 | Unknown | Unknown | Unknown | Unknown | 2025-02-21 | 2025-03-10 | 18 | 12 | 2025-05-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 57 | 57 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-06-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-24 | 2025-06-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1614.49 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-24 | 2025-06-24 | 1 | 1 | 2025-06-24 | 2025-06-26 | 3 | 3 | 2025-06-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-22 | 2023-09-25 | 2023-10-18 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1057.79 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-22 | 2023-09-25 | 4 | 2 | 2023-09-25 | 2023-09-25 | 1 | 1 | 2023-09-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-25 | 2023-10-18 | 24 | 18 | Unknown | Unknown | Unknown | Unknown | 2023-10-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | POWAY | N/A | 23 | 23 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-27 | 2025-05-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1562.12 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-27 | 2025-06-04 | 9 | 7 | 2025-06-04 | 2025-06-10 | 7 | 5 | 2025-06-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | Underserved Community | ESCONDIDO | ESCONDIDO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-10 | 2024-05-16 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 41574.48 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-10 | 2024-07-02 | 84 | 60 | 2024-07-02 | 2024-12-31 | 183 | 131 | 2024-07-20 | 2025-06-19 | 30 | 22 | 2024-08-08 | 2025-07-31 | 53 | 37 | 2025-01-14 | Unknown | Unknown | Unknown | 2025-01-14 | 2025-08-12 | 211 | 151 | 2025-08-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 86 | 86 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-30 | 2025-04-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1267.59 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-30 | 2025-04-17 | Unknown | Unknown | 2025-04-17 | 2025-04-30 | 14 | 10 | 2025-04-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-30 | 2025-08-18 | 111 | 79 | Unknown | Unknown | Unknown | Unknown | 2025-08-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 20.15 | 20.15 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-06 | 2025-03-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1220.59 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-06 | 2025-02-26 | Unknown | Unknown | 2025-02-26 | 2025-03-19 | 22 | 16 | 2025-03-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-19 | 2025-09-09 | 175 | 125 | Unknown | 2025-08-26 | Unknown | Unknown | 2025-09-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-30 | 2025-01-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2100.24 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-30 | 2025-01-30 | 1 | 1 | 2025-01-30 | 2025-01-30 | 1 | 1 | 2025-01-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | Both | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2024-02-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-03 | 2024-04-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 20288.21 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-03 | 2024-01-16 | Unknown | Unknown | 2024-01-16 | 2025-03-13 | 423 | 303 | 2024-08-02 | 2024-08-26 | 25 | 17 | 2025-03-17 | 2025-03-25 | 9 | 7 | 2025-03-13 | 2025-08-20 | 161 | 115 | 2025-04-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | ALPINE | COUNTY OF SAN DIEGO-SOUTH of 56 | 50 | 50 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-24 | 2024-01-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 276.55 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-24 | 2024-01-24 | 1 | 1 | 2024-01-24 | 2024-02-02 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-20 | 2023-04-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1432.46 | Unknown | Unknown | Yes | N/A | N/A | 2023-04-20 | 2023-04-20 | 1 | 1 | 2023-04-20 | 2023-05-11 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | 61 | 61 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-29 | 2023-08-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3797.59 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-29 | 2023-08-24 | Unknown | Unknown | 2023-08-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | ENCINITAS | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-29 | 2025-06-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1223.95 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-29 | 2025-06-04 | 7 | 5 | 2025-06-04 | 2025-06-11 | 8 | 6 | 2025-06-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-11 | 2025-08-13 | 64 | 46 | Unknown | Unknown | Unknown | Unknown | 2025-08-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 98.05 | 98.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-30 | 2024-07-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1296.44 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-30 | 2024-07-31 | 2 | 2 | 2024-07-31 | 2024-08-09 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-09 | 2025-07-01 | 327 | 233 | Unknown | 2025-07-16 | Unknown | Unknown | 2025-07-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-17 | 2024-01-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 483.62 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-17 | 2024-01-17 | 1 | 1 | 2024-01-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-17 | 2024-01-29 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 29 | 29 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-23 | 2025-05-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 956.7 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-23 | 2025-05-05 | Unknown | Unknown | 2025-05-05 | 2025-05-23 | 19 | 15 | 2025-05-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-23 | 2025-09-02 | 103 | 73 | Unknown | Unknown | Unknown | Unknown | 2025-09-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | Underserved Community | RA 1153-E7 CREEKSD XING WO1 (E) | COUNTY OF SAN DIEGO-NORTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-07 | 2024-03-07 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 72455.67 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-07 | 2024-06-25 | 111 | 79 | 2024-06-25 | 2024-11-25 | 154 | 110 | 2024-07-11 | 2025-01-10 | 65 | 47 | 2024-08-20 | 2025-08-20 | 308 | 218 | 2025-01-31 | Unknown | Unknown | Unknown | 2025-01-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-07 | 2025-05-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 4015.16 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-07 | 2025-05-13 | 7 | 5 | 2025-05-13 | 2025-05-21 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | FALLBROOK | N/A | 50 | 50 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-17 | 2024-10-31 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3940.48 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-17 | 2024-09-17 | 1 | 1 | 2024-09-17 | 2025-02-28 | 165 | 119 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-22 | 2025-02-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1564.26 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-22 | 2025-02-19 | Unknown | Unknown | 2025-02-19 | 2025-02-22 | 4 | 3 | 2025-02-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-30 | 2024-09-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1610.66 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-30 | 2024-09-25 | 240 | 172 | 2024-09-25 | 2024-09-25 | 1 | 1 | 2024-09-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | CHULA VISTA | 734 | 734 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-27 | 2023-10-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7962 | 1190.68 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-27 | 2023-08-23 | Unknown | Unknown | 2023-08-23 | 2023-11-13 | 83 | 59 | Unknown | Unknown | Unknown | Unknown | 2023-10-10 | 2023-10-18 | 9 | 7 | 2023-11-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | Both | IOU Design | Commercial | Underserved Community | Lakeside | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-02 | 2023-10-12 | 2025-02-09 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 66567.37 | 88272.39 | Unknown | Unknown | Yes | N/A | N/A | 2022-09-02 | 2023-04-12 | 223 | 159 | 2023-04-12 | 2024-04-18 | 373 | 267 | 2023-10-11 | 2024-05-03 | 29 | 19 | 2024-04-18 | 2024-04-30 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2025-01-22 | Unknown | Unknown | Unknown | 2025-02-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | DANA POINT | COUNTY OF ORANGE | 3 | 3 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-27 | 2024-10-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 643.19 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-27 | 2024-10-18 | 22 | 16 | 2024-10-18 | 2024-10-18 | 1 | 1 | 2024-10-18 | Unknown | Unknown | Unknown | 2024-10-18 | 2024-10-22 | 5 | 3 | 2024-10-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-18 | 2024-10-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 35829 | 2028.65 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-18 | 2024-04-13 | Unknown | Unknown | 2024-04-13 | 2025-05-27 | 410 | 292 | Unknown | Unknown | Unknown | Unknown | 2024-10-15 | 2025-06-18 | 30 | 22 | 2025-05-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | NATIONAL CITY | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-06-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-12 | 2025-06-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1122.72 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-12 | 2025-06-13 | 2 | 2 | 2025-06-13 | 2025-06-13 | 1 | 1 | 2025-06-13 | 2025-07-28 | 4 | 2 | 2025-06-16 | 2025-07-25 | 40 | 30 | 2025-06-13 | 2025-08-18 | 67 | 47 | Unknown | Unknown | Unknown | Unknown | 2025-08-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-22 | 2025-02-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1793.24 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-22 | 2024-12-13 | Unknown | Unknown | 2024-12-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-22 | 2025-02-11 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | VALLEY CENTER | N/A | 102.05 | 102.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-11 | 2023-08-11 | 2023-08-11 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 261.34 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-11 | 2023-08-11 | 1 | 1 | 2023-08-11 | 2023-08-11 | 1 | 1 | 2023-08-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-11 | 2023-08-11 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2023-08-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | Chula Vista | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-02-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-14 | 2024-08-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 126578 | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2024-08-14 | 2024-08-14 | 1 | 1 | 2024-08-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 9.05 | 9.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-10 | 2024-09-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1966.38 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-10 | 2024-07-22 | Unknown | Unknown | 2024-07-22 | 2025-04-25 | 278 | 200 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-25 | 2025-08-20 | 118 | 84 | Unknown | Unknown | Unknown | Unknown | 2025-08-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-29 | 2024-07-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 23991 | 677.91 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-29 | 2024-05-02 | Unknown | Unknown | 2024-05-02 | 2024-07-29 | 89 | 63 | 2024-07-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-18 | 2025-06-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 819.44 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-18 | 2025-06-24 | 7 | 5 | 2025-06-24 | 2025-06-24 | 1 | 1 | 2025-06-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-04 | 2025-06-04 | 2025-06-19 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1070.17 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-04 | 2025-09-05 | 94 | 68 | 2025-09-05 | 2025-06-09 | Unknown | Unknown | 2025-06-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-09 | 2025-06-19 | 11 | 9 | Unknown | Unknown | Unknown | Unknown | 2025-06-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-21 | 2024-03-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 530.79 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-21 | 2024-04-11 | 22 | 16 | 2024-04-11 | 2024-04-11 | 1 | 1 | 2024-04-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | BONSALL | N/A | 250.05 | 250.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-10 | 2025-03-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1728.53 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-10 | 2025-03-07 | Unknown | Unknown | 2025-03-07 | 2025-03-10 | 4 | 2 | 2025-03-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-17 | 2025-06-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1061.05 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-17 | 2025-05-28 | Unknown | Unknown | 2025-05-28 | 2025-06-19 | 23 | 17 | 2025-06-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-19 | 2025-07-23 | 35 | 25 | Unknown | Unknown | Unknown | Unknown | 2025-07-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-28 | 2025-04-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 5042.44 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-28 | 2025-04-24 | Unknown | Unknown | 2025-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-06-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-25 | 2025-06-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1721.74 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-25 | 2025-06-23 | Unknown | Unknown | 2025-06-23 | 2025-06-25 | 3 | 3 | 2025-06-25 | Unknown | Unknown | Unknown | 2025-06-25 | 2025-07-11 | 17 | 13 | 2025-06-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 81.05 | 81.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-06 | 2024-08-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1120.32 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-06 | 2024-10-14 | 70 | 50 | 2024-10-14 | 2024-10-18 | 5 | 5 | 2024-10-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | IOU Design | Residential | N/A | CORONADO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-01-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-04 | 2025-03-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | 18093.55 | 0 | Unknown | Unknown | 6615.22 | 11478.33 | 0 | 2993.09 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-04 | 2025-03-12 | 37 | 27 | 2025-03-12 | 2025-06-16 | 97 | 69 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-16 | 2025-07-01 | 16 | 12 | Unknown | 2025-06-25 | Unknown | Unknown | 2025-07-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 67 | 67 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-03-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-21 | 2023-08-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7962 | 461.97 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-21 | 2023-07-13 | Unknown | Unknown | 2023-07-13 | 2024-05-14 | 307 | 219 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 43 | 43 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-26 | 2024-05-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7962 | 3844.24 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-26 | 2024-02-15 | 113 | 81 | 2024-02-15 | 2024-07-19 | 156 | 112 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-09 | 2023-06-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 774.32 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-09 | 2023-06-15 | 7 | 5 | 2023-06-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Commercial | Underserved Community | EL CAJON | EL CAJON | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-10 | 2023-11-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 123714 | 39935.15 | Unknown | Unknown | Yes | N/A | N/A | 2022-06-10 | 2024-01-08 | 578 | 412 | 2024-01-08 | 2024-08-29 | 235 | 169 | 2024-01-04 | 2024-08-23 | 223 | 158 | 2023-12-19 | 2025-02-15 | 100 | 73 | 2024-10-25 | Unknown | Unknown | Unknown | 2024-10-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN YSIDRO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-08 | 2024-10-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3241 | 507.87 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-08 | 2024-10-08 | 1 | 1 | 2024-10-08 | 2024-10-08 | 1 | 1 | 2024-10-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-10 | 2025-04-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 104.51 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-10 | 2025-04-10 | 1 | 1 | 2025-04-10 | 2025-05-08 | 29 | 21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-05-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-19 | 2023-05-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 403.55 | Unknown | Unknown | Yes | N/A | N/A | 2023-05-19 | 2023-05-19 | 1 | 1 | 2023-05-19 | 2023-06-15 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-15 | 2023-07-06 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SPRING VALLEY | COUNTY OF SAN DIEGO-SOUTH of 56, LA MESA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-20 | 2024-05-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7382 | 785.94 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-20 | 2024-05-25 | 6 | 5 | 2024-05-25 | 2024-06-19 | 26 | 18 | 2024-06-27 | 2024-07-03 | 7 | 5 | 2024-06-18 | 2024-07-09 | 18 | 14 | 2024-06-19 | Unknown | Unknown | Unknown | Unknown | 2025-01-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-24 | 2023-07-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 11943 | 1570.15 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-24 | 2024-07-09 | 352 | 252 | 2024-07-09 | 2024-07-16 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2024-02-14 | 2024-03-06 | 22 | 16 | 2024-07-16 | 2025-07-10 | 360 | 258 | Unknown | Unknown | Unknown | Unknown | 2025-07-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-17 | 2025-06-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1580.79 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-17 | 2025-06-13 | Unknown | Unknown | 2025-06-13 | 2025-06-17 | 5 | 3 | 2025-06-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-18 | 2025-08-20 | 64 | 46 | Unknown | Unknown | Unknown | Unknown | 2025-08-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LEMON GROVE | N/A | 64 | 64 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-25 | 2024-01-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 966.47 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-25 | 2024-02-07 | 14 | 10 | 2024-02-07 | 2024-02-07 | 1 | 1 | 2024-02-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | 67.25 | 67.25 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-27 | 2024-08-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 4511.8 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-27 | 2024-08-23 | Unknown | Unknown | 2024-08-23 | 2024-10-03 | 42 | 30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-03 | 2024-11-08 | 37 | 27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R29/R45) | UG | IOU Design | Commercial | Underserved Community | EL CAJON | EL CAJON | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-14 | 2024-01-26 | 2025-03-31 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 204033 | 110898.74 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-14 | 2024-02-12 | 214 | 152 | 2024-02-12 | 2024-11-06 | 269 | 193 | 2023-11-07 | 2024-11-01 | 68 | 49 | 2023-10-25 | 2025-04-24 | 184 | 134 | 2024-11-06 | Unknown | Unknown | Unknown | Unknown | 2025-05-09 | Unknown | Unknown | 2025-03-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 20.1 | 20.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-11 | 2024-07-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7862 | 4532.23 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-11 | 2024-06-12 | Unknown | Unknown | 2024-06-12 | 2024-07-11 | 30 | 22 | 2024-07-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2020-01-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-28 | 2023-06-30 | 2023-07-24 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1110.53 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-28 | 2023-06-30 | 3 | 3 | 2023-06-30 | 2023-06-30 | 1 | 1 | 2023-06-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-30 | 2023-07-24 | 25 | 17 | Unknown | Unknown | Unknown | Unknown | 2023-07-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | VALLEY CENTER | N/A | 16 | 16 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-09 | 2025-04-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1267.31 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-09 | 2025-04-08 | Unknown | Unknown | 2025-04-08 | 2025-04-09 | 2 | 2 | 2025-04-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-01 | 2023-11-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 895.61 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-01 | 2023-10-03 | Unknown | Unknown | 2023-10-03 | 2023-11-01 | 30 | 22 | 2023-11-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | JAMUL | N/A | 194 | 194 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-23 | 2024-05-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 9034 | 4125.22 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-23 | 2024-05-23 | 1 | 1 | 2024-05-23 | 2024-11-13 | 175 | 125 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 47.05 | 47.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-05 | 2023-12-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | -1.12 | -4.61 | Unknown | Unknown | 3.22 | 0.27 | 3981 | 515.81 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-05 | 2023-12-05 | 1 | 1 | 2023-12-05 | 2023-12-05 | 1 | 1 | 2023-12-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-20 | 2023-04-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2405.39 | Unknown | Unknown | Yes | N/A | N/A | 2023-04-20 | 2023-06-15 | 57 | 41 | 2023-06-15 | 2023-06-19 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 15.05 | 15.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-24 | 2024-12-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1571.67 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-24 | 2024-10-31 | 8 | 6 | 2024-10-31 | 2024-12-06 | 37 | 27 | 2024-12-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-06 | 2025-07-21 | 228 | 162 | Unknown | Unknown | Unknown | Unknown | 2025-07-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | OH | Applicant Design | Residential | Disadvantaged Community,Underserved Community | Chula Vista | CHULA VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-09 | 2023-11-09 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 49158.52 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-09 | 2024-12-04 | 392 | 280 | 2024-12-04 | 2025-03-20 | 107 | 77 | 2024-12-26 | 2025-02-07 | 44 | 32 | 2025-02-27 | 2025-04-25 | 51 | 37 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | 324 | 324 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-19 | 2025-04-10 | 2025-05-22 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2318.81 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-19 | 2025-04-09 | 22 | 16 | 2025-04-09 | 2025-04-10 | 2 | 2 | 2025-04-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-10 | 2025-05-22 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | 2025-05-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | Applicant Design | Residential | N/A | San Marcos | San Marcos | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-27 | 2024-08-27 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2024-08-27 | 2024-08-23 | Unknown | Unknown | 2024-08-23 | 2025-02-24 | 186 | 132 | Unknown | Unknown | Unknown | Unknown | 2024-09-11 | 2024-10-02 | 22 | 16 | 2025-02-24 | 2025-09-02 | 191 | 137 | Unknown | Unknown | Unknown | Unknown | 2025-07-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-20 | 2024-12-31 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 3350.61 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-20 | 2024-11-20 | 1 | 1 | 2024-11-20 | 2024-12-31 | 42 | 30 | 2024-12-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-18 | 2025-03-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1713.7 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-18 | 2025-02-24 | Unknown | Unknown | 2025-02-24 | 2025-03-20 | 25 | 19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-07-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | 1644 | 1644 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2026-07-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-23 | 2024-11-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1318.78 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-23 | 2024-11-06 | 76 | 54 | 2024-11-06 | 2024-11-07 | 2 | 2 | 2024-11-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-25 | 2025-04-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1080.02 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-25 | 2025-05-13 | 19 | 13 | 2025-05-13 | 2025-06-04 | 23 | 17 | 2025-04-29 | 2025-05-30 | 32 | 24 | Unknown | Unknown | Unknown | Unknown | 2025-06-04 | 2025-09-08 | 97 | 69 | Unknown | 2025-08-20 | Unknown | Unknown | 2025-09-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-03 | 2025-03-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1448.41 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-03 | 2025-01-31 | Unknown | Unknown | 2025-01-31 | 2025-03-06 | 35 | 25 | 2025-03-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-06 | 2025-07-22 | 139 | 99 | Unknown | 2025-07-08 | Unknown | Unknown | 2025-07-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN JUAN CAPISTRANO | N/A | 1585.1 | 1585.1 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2027-01-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-05 | 2025-02-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1340.63 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-05 | 2025-02-16 | 12 | 8 | 2025-02-16 | 2025-02-19 | 4 | 3 | 2025-02-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-18 | 2024-01-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 11943 | 2524.28 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-18 | 2024-01-17 | 31 | 23 | 2024-01-17 | 2024-02-02 | 17 | 13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-02 | Unknown | Unknown | Unknown | Unknown | 2025-07-15 | Unknown | Unknown | 2025-07-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-31 | 2025-04-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1106.05 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-31 | 2025-04-25 | 26 | 20 | 2025-04-25 | 2025-04-25 | 1 | 1 | 2025-04-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-18 | 2023-07-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 855.99 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-18 | 2023-07-17 | Unknown | Unknown | 2023-07-17 | 2023-09-09 | 55 | 40 | 2023-09-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-23 | 2025-06-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1459.03 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-23 | 2025-06-16 | Unknown | Unknown | 2025-06-16 | 2025-06-24 | 9 | 7 | 2025-06-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-24 | 2025-07-08 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2025-07-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 226.75 | 226.75 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-11 | 2025-01-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1861.16 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-11 | 2025-01-23 | 44 | 32 | 2025-01-23 | 2025-01-23 | 1 | 1 | 2025-01-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | CHULA VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2021-02-01 | 2023-05-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 9749 | 1615.33 | Unknown | Unknown | Yes | N/A | N/A | 2021-02-01 | 2023-06-19 | 869 | 621 | 2023-06-19 | 2023-10-17 | 121 | 87 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-25 | Unknown | Unknown | 2025-07-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-23 | 2025-04-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1070.17 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-23 | 2025-06-11 | 50 | 36 | 2025-06-11 | 2025-06-11 | 1 | 1 | 2025-06-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-11 | 2025-08-13 | 64 | 46 | Unknown | Unknown | Unknown | Unknown | 2025-08-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 126.15 | 126.15 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-27 | 2022-10-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3885 | 763.27 | Unknown | Unknown | Yes | N/A | N/A | 2022-10-27 | 2023-02-10 | 107 | 77 | 2023-02-10 | 2023-02-24 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2023-02-10 | 2023-02-22 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-28 | 2025-05-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2316.64 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-28 | 2025-05-15 | Unknown | Unknown | 2025-05-15 | 2025-05-28 | 14 | 10 | 2025-05-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-28 | 2025-07-02 | 36 | 26 | Unknown | Unknown | Unknown | Unknown | 2025-07-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-02 | 2025-01-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1790.06 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-02 | 2025-01-09 | 8 | 6 | 2025-01-09 | 2025-01-13 | 5 | 3 | 2025-01-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | 10538.1 | 10538.1 | Not Available | >2MW | No | N/A | N/A | N/A | 2025-10-01 | Unknown | Unknown | No | 2024-01-03 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-03 | 2024-07-11 | Unknown | IOU Designed & Installed | N/A | Yes | 294 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1832.04 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-03 | 2024-10-23 | 295 | 211 | 2024-10-23 | 2024-10-23 | 1 | 1 | 2024-08-13 | 2025-01-09 | 80 | 58 | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-22 | 2023-09-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 132048 | 30908.25 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-22 | 2023-04-18 | Unknown | Unknown | 2023-04-18 | 2024-04-12 | 361 | 259 | 2023-09-26 | 2024-04-16 | 2 | 2 | 2024-04-09 | 2024-04-30 | 22 | 16 | 2024-04-12 | 2025-08-14 | 490 | 350 | 2024-04-15 | 2025-08-26 | 499 | 357 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 46.05 | 46.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-03 | 2024-09-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 278.35 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-03 | 2024-09-13 | 11 | 9 | 2024-09-13 | 2024-09-13 | 1 | 1 | 2024-09-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | NATIONAL CITY | NATIONAL CITY | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-03-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-19 | 2024-04-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 33634.6 | 1237.74 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-19 | 2024-06-17 | 151 | 107 | 2024-06-17 | 2025-06-19 | 368 | 264 | Unknown | Unknown | Unknown | Unknown | 2024-07-08 | 2025-03-12 | 95 | 69 | 2025-06-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-30 | 2025-05-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1001.53 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-30 | 2025-06-06 | 8 | 6 | 2025-06-06 | 2025-06-06 | 1 | 1 | 2025-06-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-06 | 2025-08-08 | 64 | 46 | Unknown | Unknown | Unknown | Unknown | 2025-08-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-12 | 2024-03-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 308.87 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-12 | 2024-01-31 | Unknown | Unknown | 2024-01-31 | 2024-03-15 | 45 | 33 | 2024-03-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-06-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-23 | 2025-06-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1034.49 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-23 | 2025-06-23 | 1 | 1 | 2025-06-23 | 2025-06-23 | 1 | 1 | 2025-06-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-23 | 2025-07-17 | 25 | 19 | Unknown | Unknown | Unknown | Unknown | 2025-07-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-24 | 2024-06-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1460.69 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-24 | 2024-05-15 | Unknown | Unknown | 2024-05-15 | 2024-06-26 | 43 | 31 | 2024-06-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | CARDIFF | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-29 | 2023-12-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 8863.83 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-29 | 2023-09-21 | Unknown | Unknown | 2023-09-21 | 2025-02-06 | 505 | 361 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R29/R45 | UG | IOU Design | Commercial | Underserved Community | CHULA VISTA | CALTRANS-SOUTH of 56, CHULA VISTA, COUNTY OF SAN DIEGO-SOUTH of 56 | 800 | 800 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-28 | 2024-07-30 | 2025-02-28 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 191238.31 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-28 | 2024-07-29 | 63 | 45 | 2024-07-29 | 2025-01-10 | 166 | 120 | 2024-10-23 | 2025-04-02 | 17 | 13 | 2024-09-10 | 2025-05-13 | -287 | -223 | 2025-01-10 | 2025-06-17 | 159 | 113 | Unknown | 2025-07-08 | Unknown | Unknown | 2025-02-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-21 | 2025-02-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 658.99 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-21 | 2025-01-25 | Unknown | Unknown | 2025-01-25 | 2025-02-21 | 28 | 20 | 2025-02-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | Underserved Community | Chula Vista | CHULA VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-02-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-01 | 2022-09-01 | 2024-08-14 | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 89234.54 | Unknown | Unknown | Yes | N/A | N/A | 2022-09-01 | 2023-10-16 | 411 | 293 | 2023-10-16 | 2024-02-13 | 121 | 87 | 2023-10-31 | 2024-04-08 | 67 | 49 | 2023-11-15 | 2024-02-14 | 13 | 9 | 2024-02-21 | Unknown | Unknown | Unknown | 2024-02-21 | 2024-07-19 | 150 | 108 | 2024-08-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 14.05 | 14.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-25 | 2024-11-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 11943 | 1572.39 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-25 | 2024-10-29 | Unknown | Unknown | 2024-10-29 | 2024-12-26 | 59 | 43 | Unknown | Unknown | Unknown | Unknown | 2024-11-27 | 2025-01-15 | 50 | 36 | 2024-12-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | 332 | 332 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-30 | 2024-06-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 41747 | 5565.19 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-30 | 2024-04-16 | Unknown | Unknown | 2024-04-16 | 2024-07-22 | 98 | 70 | Unknown | Unknown | Unknown | Unknown | 2025-03-11 | 2025-03-24 | 14 | 10 | 2024-07-22 | 2025-07-14 | 358 | 256 | Unknown | 2025-06-19 | Unknown | Unknown | 2025-07-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 64.05 | 64.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-18 | 2024-06-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1710.02 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-18 | 2024-04-04 | Unknown | Unknown | 2024-04-04 | 2024-06-27 | 85 | 61 | 2024-06-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-27 | Unknown | Unknown | Unknown | Unknown | 2025-08-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-25 | 2022-07-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 349.44 | Unknown | Unknown | Yes | N/A | N/A | 2022-07-25 | 2023-03-22 | 241 | 173 | 2023-03-22 | 2023-03-30 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | 2023-03-07 | 2023-03-13 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | OH | Applicant Design | Residential | Underserved Community | San Diego | SAN DIEGO | 216 | 216 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-02 | 2024-05-02 | 2025-06-17 | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 26288.26 | 72367.1 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-02 | 2024-08-02 | 93 | 67 | 2024-08-02 | 2025-06-06 | 309 | 221 | 2024-08-12 | 2024-08-19 | 8 | 6 | 2024-08-14 | 2025-06-16 | 34 | 24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | IOU Design | Residential | N/A | Rancho Santa Fe | COUNTY OF SAN DIEGO-NORTH of 56 | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2024-08-14 | Unknown | Unknown | No | 2024-02-06 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-14 | 2024-08-22 | Unknown | IOU Designed & Installed | N/A | Yes | 171 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 747 | 52882.27 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-14 | 2024-04-26 | 257 | 185 | 2024-04-26 | 2025-03-25 | 334 | 238 | 2024-07-26 | 2025-08-28 | 1 | 1 | 2025-03-03 | 2025-03-18 | 16 | 12 | 2025-03-25 | Unknown | Unknown | Unknown | 2025-04-04 | 2025-09-02 | 152 | 108 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | OH | Applicant Design | Residential | Underserved Community | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-16 | 2024-05-16 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 31847.72 | 44062.42 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-16 | 2024-08-26 | 103 | 73 | 2024-08-26 | 2025-07-08 | 317 | 227 | 2024-09-10 | 2025-01-02 | 115 | 83 | 2025-07-02 | 2025-07-09 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-08-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | LA MESA | N/A | 187.15 | 187.15 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-04 |  | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 901.28 | Unknown | Unknown | Yes | N/A | N/A | 2023-04-04 | 2023-04-04 | 1 | 1 | 2023-04-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | POWAY | N/A | 5.4 | 5.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-15 | 2024-12-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2004.25 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-15 | 2024-11-11 | Unknown | Unknown | 2024-11-11 | 2024-12-15 | 35 | 25 | 2024-12-15 | 2025-03-13 | 89 | 64 | Unknown | Unknown | Unknown | Unknown | 2025-03-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-22 | 2024-05-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1520.45 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-22 | 2024-05-23 | 2 | 2 | 2024-05-23 | 2024-05-23 | 1 | 1 | 2024-05-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 12 | 12 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-01 | 2023-11-21 | 2023-11-21 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1735.92 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-01 | 2023-08-21 | Unknown | Unknown | 2023-08-21 | 2023-11-21 | 93 | 67 | 2023-11-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-21 | 2023-11-21 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2023-11-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-03 | 2024-09-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1456.69 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-03 | 2024-09-03 | 1 | 1 | 2024-09-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | Rancho Viejo | N/A | 106.1 | 106.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-06-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-17 | 2025-04-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2025-04-17 | 2024-07-05 | Unknown | Unknown | 2024-07-05 | 2025-06-16 | 347 | 247 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | BORREGO SPRINGS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-06 | 2025-05-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2521.25 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-06 | 2025-05-06 | 1 | 1 | 2025-05-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-08-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | POWAY | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-18 | 2023-04-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 776.63 | Unknown | Unknown | Yes | N/A | N/A | 2023-04-18 | 2023-04-18 | 1 | 1 | 2023-04-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 478 | 478 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-29 | 2023-09-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 803.03 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-29 | 2023-09-11 | 14 | 10 | 2023-09-11 | 2023-09-11 | 1 | 1 | 2023-09-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | ESCONDIDO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-30 | 2025-04-30 | 2025-06-30 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1686.87 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-30 | 2025-05-09 | 10 | 8 | 2025-05-09 | 2025-05-21 | 13 | 9 | 2025-05-21 | Unknown | Unknown | Unknown | 2025-05-22 | 2025-06-02 | 12 | 8 | 2025-05-22 | 2025-06-30 | 40 | 28 | Unknown | Unknown | Unknown | Unknown | 2025-06-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | Chula Vista | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-02-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-07 | 2025-02-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | 3476.81 | 144.97 | Unknown | Unknown | 57 | 3274.84 | 65076 | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2025-02-07 | 2025-02-07 | 1 | 1 | 2025-02-07 | 2025-02-11 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-11 | 2025-09-02 | 204 | 146 | Unknown | 2025-08-29 | Unknown | Unknown | 2025-07-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | 33 | 33 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-19 | 2025-02-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1745.68 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-19 | 2025-04-17 | 58 | 42 | 2025-04-17 | 2025-04-17 | 1 | 1 | 2025-02-28 | 2025-04-17 | 49 | 35 | Unknown | Unknown | Unknown | Unknown | 2025-04-17 | 2025-07-08 | 83 | 59 | Unknown | 2025-06-27 | Unknown | Unknown | 2025-07-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 18.95 | 18.95 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-10 | 2024-09-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2109.47 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-10 | 2024-04-04 | Unknown | Unknown | 2024-04-04 | 2025-05-05 | 397 | 283 | 2025-03-03 | 2025-04-02 | 31 | 23 | 2025-04-09 | 2025-04-22 | 14 | 10 | 2025-05-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | POWAY | POWAY | 2050.25 | 2050.25 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-11-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-05 | 2023-05-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3241 | 10667 | Unknown | Unknown | Yes | N/A | N/A | 2023-05-05 | 2023-05-05 | 1 | 1 | 2023-05-05 | 2023-10-30 | 179 | 127 | 2023-06-19 | 2023-07-05 | 17 | 13 | 2023-08-30 | 2023-11-06 | 8 | 6 | 2023-10-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-13 | Unknown | Unknown | No | 2024-04-17 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-17 | 2024-04-17 | Unknown | IOU Designed & Installed | N/A | Yes | 2 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2141.91 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-17 | 2024-04-19 | 3 | 3 | 2024-04-19 | 2024-04-17 | Unknown | Unknown | 2024-04-17 | Unknown | Unknown | Unknown | 2024-06-05 | 2024-06-20 | 16 | 12 | 2024-04-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | IOU Design | Residential | Underserved Community | San Diego | San Diego | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-20 | 2024-06-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 210051 | 150933.73 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-20 | 2024-02-21 | 2 | 2 | 2024-02-21 | 2025-05-02 | 437 | 313 | 2025-03-24 | 2025-09-09 | 142 | 102 | 2024-11-21 | 2025-05-14 | 56 | 40 | 2025-05-02 | Unknown | Unknown | Unknown | 2025-08-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CHULA VISTA | N/A | 3 | 3 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-10 | 2025-03-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1237.59 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-10 | 2025-03-18 | 9 | 7 | 2025-03-18 | 2025-03-27 | 10 | 8 | 2025-03-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-08 | 2024-11-12 | 2025-01-08 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1666.21 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-08 | 2024-11-08 | 1 | 1 | 2024-11-08 | 2024-11-08 | 1 | 1 | 2024-11-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-12 | 2025-01-08 | 58 | 42 | Unknown | Unknown | Unknown | Unknown | 2025-01-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | 399 | 399 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-10-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-01-24 | 2024-04-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 32080.55 | 16243.9 | Unknown | Unknown | Yes | N/A | N/A | 2022-01-24 | 2024-04-23 | 821 | 587 | 2024-04-23 | 2025-02-25 | 309 | 221 | 2024-08-20 | 2025-02-19 | 102 | 74 | 2024-09-13 | 2025-05-16 | 33 | 25 | 2025-07-29 | Unknown | Unknown | Unknown | 2025-07-29 | 2025-09-03 | 37 | 27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-13 | Unknown | Unknown | No | 2024-01-09 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-09 | 2024-01-09 | 2024-05-23 | IOU Designed & Installed | N/A | Yes | 104 | 212.08 | 115.24 | Unknown | 10.85 | Unknown | 85.99 | 3961 | 163.83 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-09 | 2024-04-22 | 105 | 75 | 2024-04-22 | 2024-04-22 | 1 | 1 | 2024-04-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-23 | 2024-05-23 | 91 | 65 | Unknown | Unknown | Unknown | Unknown | 2024-05-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 5 | 5 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-04 | 2025-04-10 | 2025-04-16 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1717.18 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-04 | 2025-04-09 | 6 | 4 | 2025-04-09 | 2025-04-10 | 2 | 2 | 2025-04-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-10 | 2025-04-16 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2025-04-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-12 | 2024-07-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2841 | 965.12 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-12 | 2024-07-12 | 1 | 1 | 2024-07-12 | 2024-07-12 | 1 | 1 | 2024-07-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-23 | 2024-02-23 | 2024-03-19 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 308.87 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-23 | 2024-01-22 | Unknown | Unknown | 2024-01-22 | 2024-03-02 | 41 | 30 | 2024-03-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-02 | 2024-03-19 | 18 | 12 | Unknown | Unknown | Unknown | Unknown | 2024-03-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-26 | 2024-09-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 8059.45 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-26 | 2024-09-26 | 1 | 1 | 2024-09-26 | 2024-10-07 | 12 | 8 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 48.05 | 48.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-30 | Unknown | Unknown | No | 2024-07-12 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-12 | 2024-07-12 | Unknown | IOU Designed & Installed | N/A | Yes | 251 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1547.8 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-12 | 2025-03-20 | 252 | 180 | 2025-03-20 | 2024-07-19 | Unknown | Unknown | 2024-07-19 | 2024-07-30 | 12 | 8 | Unknown | Unknown | Unknown | Unknown | 2024-07-19 | 2025-07-02 | 349 | 249 | Unknown | Unknown | Unknown | Unknown | 2025-07-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-11 | 2024-07-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 363.17 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-11 | 2024-07-02 | Unknown | Unknown | 2024-07-02 | 2024-07-11 | 10 | 8 | 2024-07-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Commercial | Underserved Community | Santee | SANTEE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-18 | 2024-03-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 112436.72 | 72778.89 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-18 | 2023-12-26 | 70 | 50 | 2023-12-26 | 2024-05-13 | 140 | 100 | 2024-03-13 | 2025-07-03 | 204 | 144 | 2024-04-18 | 2025-06-10 | 48 | 32 | 2024-09-26 | Unknown | Unknown | Unknown | 2024-09-26 | 2025-05-22 | 239 | 171 | 2025-07-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | POWAY | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-31 | 2025-04-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1130.4 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-31 | 2025-04-28 | 29 | 21 | 2025-04-28 | 2025-04-28 | 1 | 1 | 2025-04-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 1152 | 1152 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2025-01-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-23 | 2025-01-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 54065 | 5258.56 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-23 | 2025-05-30 | 128 | 92 | 2025-05-30 | 2025-06-26 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | 2025-01-27 | 2025-02-13 | 18 | 14 | 2025-06-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-11 | 2025-04-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2930.45 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-11 | 2025-02-11 | 1 | 1 | 2025-02-11 | 2025-04-02 | 51 | 37 | 2025-04-02 | 2025-04-22 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | 2025-04-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | Applicant Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2021-07-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2020-07-15 | 2020-07-15 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 8131275.13 | 339594.47 | Unknown | Unknown | Yes | N/A | N/A | 2020-07-15 | 2023-05-23 | 1043 | 745 | 2023-05-23 | 2024-09-04 | 471 | 337 | 2023-05-23 | 2024-08-22 | 318 | 228 | 2024-07-26 | 2024-08-26 | 16 | 9 | Unknown | Unknown | Unknown | Unknown | 2024-12-04 | 2024-12-16 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | 67.05 | 67.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-28 | 2023-11-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 608.01 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-28 | 2023-10-31 | Unknown | Unknown | 2023-10-31 | 2023-11-30 | 31 | 23 | 2023-11-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-14 | 2024-11-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1650.97 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-14 | 2024-11-14 | 1 | 1 | 2024-11-14 | 2024-11-14 | 1 | 1 | 2024-11-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-12 | 2024-06-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3941 | 1414.05 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-12 | 2024-04-30 | Unknown | Unknown | 2024-04-30 | 2024-06-12 | 44 | 32 | 2024-06-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-01 | 2025-03-01 | 2025-03-25 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2051.23 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-01 | 2025-02-28 | Unknown | Unknown | 2025-02-28 | 2025-03-03 | 4 | 2 | 2025-03-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-01 | 2025-03-25 | 25 | 17 | Unknown | Unknown | Unknown | Unknown | 2025-03-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | OH | IOU Design | Commercial | Underserved Community | Poway | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-07 | 2025-05-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2025-05-07 | 2025-05-07 | 1 | 1 | 2025-05-07 | 2025-08-08 | 94 | 68 | Unknown | Unknown | Unknown | Unknown | 2025-06-13 | 2025-06-19 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-08-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-23 | 2023-08-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 820.32 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-23 | 2023-05-23 | Unknown | Unknown | 2023-05-23 | 2024-01-22 | 245 | 175 | 2024-01-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | CHULA VISTA | CHULA VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-07-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-11 | 2023-07-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 270.36 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-11 | 2023-07-13 | 3 | 3 | 2023-07-13 | 2023-08-24 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | 2023-07-12 | 2023-08-22 | 42 | 30 | 2023-08-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | 5 | 5 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-11 | 2024-10-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1654.69 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-11 | 2024-10-17 | 7 | 5 | 2024-10-17 | 2024-10-24 | 8 | 6 | 2024-10-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | 17 | 17 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-04 | 2025-06-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1279.96 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-04 | 2025-06-30 | 27 | 19 | 2025-06-30 | 2025-07-01 | 2 | 2 | 2025-07-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-12 | 2025-08-14 | 64 | 46 | Unknown | Unknown | Unknown | Unknown | 2025-08-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-08 | 2023-07-14 | 2023-07-31 | IOU Designed & Installed | N/A | No | Unknown | -8.39 | -6.12 | Unknown | Unknown | Unknown | -2.27 | 3981 | 465.44 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-08 | 2023-07-14 | 37 | 27 | 2023-07-14 | 2023-07-14 | 1 | 1 | 2023-07-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-14 | 2023-07-31 | 18 | 12 | Unknown | Unknown | Unknown | Unknown | 2023-07-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LEMON GROVE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-02 | 2025-06-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1124.89 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-02 | 2025-05-14 | Unknown | Unknown | 2025-05-14 | 2025-06-04 | 22 | 16 | 2025-06-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-23 | 2023-02-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 544.25 | Unknown | Unknown | Yes | N/A | N/A | 2023-02-23 | 2023-02-27 | 5 | 3 | 2023-02-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-02 | 2025-04-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 212.65 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-02 | 2025-04-30 | 29 | 21 | 2025-04-30 | 2025-05-07 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-07 | 2025-07-30 | 85 | 61 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 81.05 | 81.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-07 | 2025-05-07 | 2025-06-26 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1708.65 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-07 | 2025-04-09 | Unknown | Unknown | 2025-04-09 | 2025-05-23 | 45 | 33 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-23 | 2025-07-15 | 54 | 38 | Unknown | 2025-06-26 | Unknown | Unknown | 2025-07-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Commercial | Underserved Community | La Mesa | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-13 | 2024-03-13 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 11008.02 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-13 | 2024-06-03 | 83 | 59 | 2024-06-03 | 2025-05-01 | 333 | 239 | 2024-06-11 | 2024-08-26 | 77 | 55 | 2025-05-02 | 2025-05-05 | 4 | 2 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CORONADO | N/A | 43 | 43 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-06 | 2025-02-06 | 2025-03-27 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1699.31 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-06 | 2025-03-07 | 30 | 22 | 2025-03-07 | 2025-03-21 | 15 | 11 | 2025-02-14 | 2025-03-21 | 36 | 26 | Unknown | Unknown | Unknown | Unknown | 2025-03-21 | 2025-03-27 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2025-03-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | 493.4 | 493.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-04 | 2024-11-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1133.6 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-04 | 2025-01-07 | 65 | 47 | 2025-01-07 | 2025-06-20 | 165 | 119 | 2025-06-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN MARCOS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-28 | 2023-09-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 237881 | 9160.67 | Unknown | Unknown | Yes | N/A | N/A | 2023-04-28 | 2023-03-01 | Unknown | Unknown | 2023-03-01 | 2023-11-21 | 266 | 190 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-21 | 2025-08-06 | 625 | 447 | Unknown | 2025-08-01 | Unknown | Unknown | 2025-08-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-27 | 2024-07-31 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 4529.75 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-27 | 2023-10-18 | 22 | 16 | 2023-10-18 | 2024-09-11 | 330 | 236 | Unknown | Unknown | Unknown | Unknown | 2025-02-11 | 2025-02-11 | 1 | 1 | 2024-09-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | 50 | 50 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-23 | 2024-08-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1622.14 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-23 | 2024-03-22 | Unknown | Unknown | 2024-03-22 | 2024-08-27 | 159 | 113 | 2024-08-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | Alpine | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-02 | 2024-04-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 4602.1 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-02 | 2024-01-22 | Unknown | Unknown | 2024-01-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-30 | 2024-05-24 | 17 | 11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-21 | 2024-02-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 27449 | 330.78 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-21 | 2023-09-25 | 97 | 69 | 2023-09-25 | 2024-08-20 | 331 | 237 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 68.05 | 68.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-20 | 2023-03-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 264.34 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-20 | 2023-05-02 | 44 | 32 | 2023-05-02 | 2023-05-18 | 17 | 13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | Poway | POWAY | 128 | 128 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-11 | 2024-11-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 11970.41 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-11 | 2025-01-10 | 61 | 45 | 2025-01-10 | 2025-06-12 | 154 | 110 | 2025-06-19 | 2025-07-14 | 26 | 18 | 2025-05-30 | 2025-07-18 | 26 | 20 | 2025-06-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | BONITA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-07 | 2024-11-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1201.86 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-07 | 2024-12-01 | 25 | 17 | 2024-12-01 | 2025-01-08 | 39 | 28 | 2025-01-08 | 2025-07-07 | 181 | 129 | Unknown | Unknown | Unknown | Unknown | 2025-05-30 | 2025-08-07 | 70 | 50 | Unknown | 2025-07-08 | Unknown | Unknown | 2025-08-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2022-02-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-02 | 2024-04-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2234.23 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-02 | 2024-04-03 | 2 | 2 | 2024-04-03 | 2024-05-30 | 58 | 42 | Unknown | Unknown | Unknown | Unknown | 2024-04-17 | 2024-05-14 | 28 | 20 | 2024-05-30 | 2025-08-04 | 432 | 308 | Unknown | Unknown | Unknown | Unknown | 2025-08-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-11 | 2025-01-06 | 2025-06-25 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1202.68 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-11 | 2025-01-06 | 27 | 19 | 2025-01-06 | 2025-01-06 | 1 | 1 | 2025-01-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-06 | 2025-06-25 | 171 | 123 | Unknown | Unknown | Unknown | Unknown | 2025-06-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-25 | 2024-06-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 791 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-25 | 2024-06-25 | 1 | 1 | 2024-06-25 | 2024-06-25 | 1 | 1 | 2024-06-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | OH | IOU Design | Residential | Underserved Community | Santee | SANTEE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-23 | 2024-01-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2770 | 32769.8 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-23 | 2024-01-23 | 1 | 1 | 2024-01-23 | Unknown | Unknown | Unknown | 2024-09-05 | 2025-02-10 | 159 | 113 | 2024-05-15 | 2025-02-28 | 60 | 44 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | MISSION VIEJO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-24 | 2024-05-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 192.83 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-24 | 2024-05-22 | Unknown | Unknown | 2024-05-22 | 2024-05-24 | 3 | 3 | 2024-05-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-23 | 2025-04-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1461.51 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-23 | 2025-04-11 | Unknown | Unknown | 2025-04-11 | 2025-04-24 | 14 | 10 | 2025-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-01 | Unknown | Unknown | No | 2024-02-09 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-09 | 2025-03-21 | Unknown | IOU Designed & Installed | N/A | Yes | 406 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1098.75 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-09 | 2025-03-21 | 407 | 291 | 2025-03-21 | 2025-03-21 | 1 | 1 | 2025-03-21 | 2025-04-15 | 26 | 18 | Unknown | Unknown | Unknown | Unknown | 2025-04-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-02 | 2025-01-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1923.77 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-02 | 2025-01-16 | 15 | 11 | 2025-01-16 | 2025-01-16 | 1 | 1 | 2025-01-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | POWAY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-14 | 2024-05-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1166.44 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-14 | 2024-04-22 | 131 | 93 | 2024-04-22 | 2024-05-09 | 18 | 14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 35 | 35 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-04-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-05 | 2024-02-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 369.35 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-05 | 2024-03-07 | 94 | 68 | 2024-03-07 | 2024-06-19 | 105 | 75 | Unknown | Unknown | Unknown | Unknown | 2024-03-19 | 2024-04-09 | 22 | 16 | 2024-06-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-26 | 2025-02-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1797.02 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-26 | 2025-02-26 | 1 | 1 | 2025-02-26 | 2025-02-26 | 1 | 1 | 2025-02-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | MOUNT LAGUNA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-21 | 2024-06-21 | 2024-07-12 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 192.83 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-21 | 2024-05-08 | Unknown | Unknown | 2024-05-08 | 2024-06-24 | 48 | 34 | 2024-06-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-24 | 2024-07-12 | 19 | 15 | Unknown | Unknown | Unknown | Unknown | 2024-07-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | Underserved Community | Carlsbad | CARLSBAD | 384 | 384 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-24 | 2024-07-24 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 56606 | 9075 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-24 | 2025-01-14 | 175 | 125 | 2025-01-14 | 2025-06-04 | 142 | 102 | 2025-01-02 | 2025-06-03 | 89 | 63 | 2025-04-02 | 2025-08-07 | 52 | 38 | 2025-06-24 | Unknown | Unknown | Unknown | 2025-06-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-09 | 2025-04-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1332.94 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-09 | 2025-03-25 | Unknown | Unknown | 2025-03-25 | 2025-04-09 | 16 | 12 | 2025-04-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | NATIONAL CITY | NATIONAL CITY, SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-13 | 2024-08-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 449.58 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-13 | 2024-07-03 | Unknown | Unknown | 2024-07-03 | 2024-09-16 | 76 | 54 | Unknown | Unknown | Unknown | Unknown | 2024-08-20 | 2024-10-30 | 72 | 52 | 2024-09-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 57.15 | 57.15 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-06 | 2024-08-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1636.81 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-06 | 2024-07-11 | Unknown | Unknown | 2024-07-11 | 2024-08-30 | 51 | 37 | 2024-08-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 39 | 39 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-06 | 2024-08-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3941 | 1747.34 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-06 | 2024-06-07 | Unknown | Unknown | 2024-06-07 | 2024-08-06 | 61 | 43 | 2024-08-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-28 | 2023-02-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 490.18 | Unknown | Unknown | Yes | N/A | N/A | 2023-02-28 | 2023-02-28 | 1 | 1 | 2023-02-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-17 | 2024-10-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1427.15 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-17 | 2024-10-19 | 3 | 2 | 2024-10-19 | 2024-10-21 | 3 | 1 | 2024-10-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2019-11-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-30 | 2024-01-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 514.37 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-30 | 2024-01-29 | Unknown | Unknown | 2024-01-29 | 2025-03-10 | 407 | 291 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-10 | Unknown | Unknown | Unknown | Unknown | 2025-04-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-27 | 2025-02-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1421.49 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-27 | 2025-03-06 | 8 | 6 | 2025-03-06 | 2025-03-06 | 1 | 1 | 2025-03-06 | 2025-03-19 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | 2025-03-19 | 2025-07-07 | 111 | 79 | Unknown | 2025-06-24 | Unknown | Unknown | 2025-07-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-24 | 2025-02-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 642.24 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-24 | 2025-03-04 | 132 | 94 | 2025-03-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | OH | IOU Design | Residential | Underserved Community | FALLBROOK | COUNTY OF SAN DIEGO-NORTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-25 | 2024-06-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 37032 | 91644.36 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-25 | 2024-06-06 | Unknown | Unknown | 2024-06-06 | 2025-04-04 | 303 | 217 | 2025-01-29 | 2025-07-18 | 2 | 2 | 2025-02-21 | 2025-04-04 | 20 | 14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2017-10-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-19 | 2023-07-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1110.53 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-19 | 2023-07-21 | 3 | 3 | 2023-07-21 | 2023-07-21 | 1 | 1 | 2023-07-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-15 | 2023-06-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 503392 | 44957.11 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-15 | 2023-06-19 | 5 | 3 | 2023-06-19 | 2023-07-18 | 30 | 22 | Unknown | Unknown | Unknown | Unknown | 2023-07-06 | 2023-07-10 | 5 | 3 | 2023-07-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | LEMON GROVE | LEMON GROVE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-10 | 2023-10-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 55559.22 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-10 | 2023-09-06 | 28 | 20 | 2023-09-06 | 2024-05-09 | 247 | 177 | 2023-12-05 | 2023-12-05 | 1 | 1 | 2023-11-29 | 2024-05-14 | 21 | 15 | 2024-05-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | RANCHO MISSION VIEJO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-02 | 2023-06-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 481.12 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-02 | 2023-12-13 | 195 | 139 | 2023-12-13 | Unknown | Unknown | Unknown | 2023-12-04 | 2023-12-04 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2023-12-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 145.05 | 145.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-01 | 2024-10-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1643.91 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-01 | 2024-10-01 | 1 | 1 | 2024-10-01 | 2025-01-10 | 102 | 74 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | SAN DIEGO | 109.05 | 109.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-29 | 2024-09-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 32270.62 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-29 | 2024-08-13 | Unknown | Unknown | 2024-08-13 | Unknown | Unknown | Unknown | 2025-02-06 | 2025-02-11 | 2 | 2 | 2024-09-30 | 2025-06-30 | 67 | 49 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | ENCINITAS | ENCINITAS | 31.4 | 31.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-03 | Unknown | Unknown | No | 2024-11-04 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-04 | 2024-11-06 | Unknown | IOU Designed & Installed | N/A | Yes | 177 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2913.11 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-04 | 2025-04-03 | 151 | 109 | 2025-04-03 | 2025-06-03 | 62 | 44 | Unknown | Unknown | Unknown | Unknown | 2025-04-30 | 2025-06-17 | 49 | 35 | 2025-06-03 | Unknown | Unknown | Unknown | Unknown | 2025-07-22 | Unknown | Unknown | 2025-07-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | POWAY | POWAY | 595.05 | 595.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-23 | 2024-04-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 12674.68 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-23 | 2024-03-22 | 60 | 44 | 2024-03-22 | 2024-05-24 | 64 | 46 | 2024-04-29 | 2024-04-30 | 2 | 2 | 2024-05-03 | 2025-08-01 | 78 | 56 | 2024-05-24 | Unknown | Unknown | Unknown | 2024-07-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | OH | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-11 | 2025-02-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 18412.07 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-11 | 2025-02-11 | 1 | 1 | 2025-02-11 | 2025-05-28 | 107 | 77 | 2025-03-13 | 2025-03-14 | 2 | 2 | 2025-03-13 | 2025-06-06 | 31 | 23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-08 | 2024-04-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 684.16 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-08 | 2024-04-08 | 1 | 1 | 2024-04-08 | 2024-04-08 | 1 | 1 | 2024-04-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | Applicant Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-06 | Unknown | Unknown | No | 2022-02-23 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-02-23 | 2022-02-23 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | Yes | 842 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 480156.7 | 26637.65 | Unknown | Unknown | Yes | N/A | N/A | 2022-02-23 | 2023-10-02 | 587 | 419 | 2023-10-02 | 2024-10-03 | 368 | 264 | 2023-01-24 | 2024-08-22 | 506 | 360 | 2024-09-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-09 | 2025-08-18 | 253 | 181 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SANTEE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-06-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-19 | 2025-06-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 117.46 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-19 | 2025-06-16 | Unknown | Unknown | 2025-06-16 | 2025-06-23 | 8 | 6 | 2025-06-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-23 | 2025-07-10 | 18 | 14 | Unknown | Unknown | Unknown | Unknown | 2025-07-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LEMON GROVE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-26 | Unknown | Unknown | No | 2025-02-26 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-26 | 2025-02-27 | 2025-06-27 | IOU Designed & Installed | N/A | Yes | 98 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1730.52 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-26 | 2025-06-04 | 99 | 71 | 2025-06-04 | 2025-02-27 | Unknown | Unknown | 2025-02-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-27 | 2025-06-27 | 121 | 87 | Unknown | Unknown | Unknown | Unknown | 2025-06-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SOUTH LAGUNA | N/A | 112.05 | 112.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-11 | 2025-03-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2802.08 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-11 | 2025-04-28 | 49 | 35 | 2025-04-28 | 2025-06-06 | 40 | 30 | 2025-06-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | IMPERIAL BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-28 | 2025-04-28 | 2025-06-25 | IOU Designed & Installed | N/A | No | Unknown | 3170.98 | 86 | Unknown | Unknown | Unknown | 3084.98 | 0 | 6731.62 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-28 | 2025-04-28 | 1 | 1 | 2025-04-28 | 2025-05-12 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-12 | 2025-06-12 | 32 | 24 | Unknown | 2025-06-19 | Unknown | Unknown | 2025-06-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-18 | 2025-02-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1253.82 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-18 | 2025-02-25 | 8 | 6 | 2025-02-25 | 2025-02-25 | 1 | 1 | 2025-02-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | N/A | Rancho Mission Viejo | COUNTY OF ORANGE, MISSION VIEJO | 5.4 | 5.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-20 | 2024-03-20 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 23130.21 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-20 | 2025-01-13 | 300 | 214 | 2025-01-13 | 2025-05-16 | 124 | 90 | 2025-02-05 | 2025-05-19 | 78 | 56 | 2025-03-07 | 2025-03-19 | 13 | 7 | 2025-05-07 | Unknown | Unknown | Unknown | 2025-05-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-08-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-08 | 2024-01-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 16930.46 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-08 | 2024-01-17 | 71 | 51 | 2024-01-17 | 2025-01-03 | 353 | 253 | 2024-01-15 | 2024-01-16 | 2 | 2 | 2024-12-30 | 2025-07-21 | 50 | 36 | 2025-01-03 | 2025-07-22 | 201 | 143 | 2025-01-27 | 2025-07-09 | 164 | 118 | 2025-07-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-12 | 2023-12-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 4613.02 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-12 | 2023-12-12 | 1 | 1 | 2023-12-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-09 | 2024-12-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1634.84 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-09 | 2024-12-09 | 1 | 1 | 2024-12-09 | 2024-12-09 | 1 | 1 | 2024-12-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | 21527 | 21527 | Not Available | >2MW | No | N/A | N/A | N/A | 2027-01-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-10 | 2025-03-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1922.6 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-10 | 2025-01-30 | Unknown | Unknown | 2025-01-30 | 2025-03-21 | 51 | 37 | 2025-03-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-19 | Unknown | Unknown | Unknown | Unknown | 2025-08-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | ESCONDIDO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-12 | 2025-03-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7962 | 2126.57 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-12 | 2025-03-12 | 1 | 1 | 2025-03-12 | 2025-03-19 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2025-03-13 | 2025-03-31 | 19 | 13 | 2025-03-19 | 2025-06-25 | 99 | 71 | Unknown | Unknown | Unknown | Unknown | 2025-07-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LAKESIDE | LAKESIDE | 106 | 106 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-27 | 2024-08-27 | 2024-09-13 | IOU Designed & Installed | N/A | No | Unknown | 2796.19 | -52.7 | Unknown | Unknown | 133.89 | 2715 | 3941 | 1453.51 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-27 | 2024-07-31 | Unknown | Unknown | 2024-07-31 | 2024-08-27 | 28 | 20 | 2024-08-27 | Unknown | Unknown | Unknown | 2024-09-16 | 2024-09-19 | 4 | 4 | 2024-08-27 | 2024-09-13 | 18 | 14 | Unknown | Unknown | Unknown | Unknown | 2024-09-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-23 | 2025-04-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1751.46 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-23 | 2025-05-07 | 15 | 11 | 2025-05-07 | 2025-07-08 | 63 | 45 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-07-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-19 | 2025-03-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 997.19 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-19 | 2025-03-12 | Unknown | Unknown | 2025-03-12 | 2025-03-28 | 17 | 13 | 2025-03-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-28 | 2025-07-21 | 116 | 82 | Unknown | Unknown | Unknown | Unknown | 2025-07-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-16 | 2025-06-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1240.31 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-16 | 2025-07-26 | 41 | 30 | 2025-07-26 | 2025-06-17 | Unknown | Unknown | 2025-06-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-12 | 2023-12-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1372.05 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-12 | 2023-12-12 | 1 | 1 | 2023-12-12 | 2023-12-19 | 8 | 6 | 2023-12-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | DEL MAR | N/A | 68 | 68 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-06 | 2023-06-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 794.88 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-06 | 2023-06-12 | 7 | 5 | 2023-06-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 104.05 | 104.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-14 | 2025-04-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1746.16 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-14 | 2025-04-11 | Unknown | Unknown | 2025-04-11 | 2025-04-14 | 4 | 2 | 2025-04-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-17 | 2024-07-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1438.08 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-17 | 2024-08-23 | 68 | 50 | 2024-08-23 | 2024-09-03 | 12 | 8 | 2024-09-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-03 | 2025-09-10 | 373 | 267 | Unknown | Unknown | Unknown | Unknown | 2025-09-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 16.05 | 16.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-18 | 2025-04-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 821.95 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-18 | 2025-04-22 | 5 | 3 | 2025-04-22 | 2025-04-30 | 9 | 7 | 2025-04-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | NATIONAL CITY | 58.05 | 58.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-16 | 2025-05-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1221.41 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-16 | 2025-01-15 | 184 | 132 | 2025-01-15 | 2025-06-18 | 155 | 111 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-18 | Unknown | Unknown | Unknown | Unknown | 2025-07-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 101.05 | 101.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-14 | 2024-01-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 483.59 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-14 | 2023-09-07 | Unknown | Unknown | 2023-09-07 | 2024-01-04 | 120 | 86 | 2024-01-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2020-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-09 | 2024-09-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 4339.01 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-09 | 2024-09-09 | 1 | 1 | 2024-09-09 | 2024-11-01 | 54 | 40 | Unknown | Unknown | Unknown | Unknown | 2024-09-10 | 2024-10-09 | 30 | 22 | 2024-11-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-03 | 2024-06-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 29653.6 | 2123.43 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-03 | 2024-05-21 | Unknown | Unknown | 2024-05-21 | 2025-03-04 | 288 | 206 | Unknown | Unknown | Unknown | Unknown | 2024-06-12 | 2024-07-12 | 31 | 23 | 2025-03-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | DEL MAR | 74 | 74 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-09 | 2024-07-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1652.76 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-09 | 2024-09-05 | 59 | 43 | 2024-09-05 | 2024-09-05 | 1 | 1 | 2024-09-05 | 2025-08-06 | 336 | 240 | 2024-09-13 | 2024-11-04 | 53 | 37 | 2025-03-19 | 2025-08-19 | 154 | 110 | Unknown | 2025-08-06 | Unknown | Unknown | 2025-08-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-19 | 2023-12-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 8044 | 1819.78 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-19 | 2023-12-21 | 94 | 68 | 2023-12-21 | 2024-01-11 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | 2023-12-29 | 2024-01-04 | 7 | 5 | 2024-01-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 213.7 | 213.7 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-22 | 2024-11-22 | 2025-02-12 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1175.27 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-22 | 2025-01-22 | 62 | 44 | 2025-01-22 | 2025-01-23 | 2 | 2 | 2025-01-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-23 | 2025-02-12 | 21 | 15 | Unknown | 2025-02-11 | Unknown | Unknown | 2025-02-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-29 | 2025-05-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1067.7 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-29 | 2025-05-29 | 1 | 1 | 2025-05-29 | 2025-05-29 | 1 | 1 | 2025-05-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-29 | 2025-07-01 | 34 | 24 | Unknown | Unknown | Unknown | Unknown | 2025-07-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | Underserved Community | ESCONDIDO | ESCONDIDO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-06 | 2024-02-06 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 39850.04 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-06 | 2024-09-04 | 212 | 152 | 2024-09-04 | 2025-04-24 | 233 | 167 | 2024-09-21 | 2025-02-04 | 117 | 81 | 2024-10-28 | 2025-02-25 | 37 | 27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Commercial | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-06 | 2024-12-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 6733835 | 25193.72 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-06 | 2024-12-23 | 18 | 12 | 2024-12-23 | 2025-06-02 | 162 | 116 | 2025-02-03 | 2025-03-05 | 31 | 23 | 2025-05-29 | 2025-06-18 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2025-12-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-13 | 2023-06-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 743.75 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-13 | 2023-06-15 | 3 | 3 | 2023-06-15 | 2023-08-07 | 54 | 38 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Residential | N/A | CD 1167-D3 (E) | ENCINITAS | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-07 | 2024-11-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 5466.55 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-07 | 2024-10-25 | Unknown | Unknown | 2024-10-25 | 2025-03-31 | 158 | 112 | 2024-11-12 | 2025-01-22 | 37 | 25 | 2024-12-17 | 2025-02-20 | 66 | 48 | 2025-04-18 | Unknown | Unknown | Unknown | 2025-04-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 45 | 45 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-26 | 2025-03-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1298.65 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-26 | 2025-04-02 | 8 | 6 | 2025-04-02 | 2025-04-11 | 10 | 8 | 2025-04-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-27 | 2024-12-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2072.99 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-27 | 2024-12-27 | 1 | 1 | 2024-12-27 | 2024-12-27 | 1 | 1 | 2024-12-27 | Unknown | Unknown | Unknown | 2024-12-30 | 2025-01-17 | 19 | 15 | 2024-12-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | DANA POINT | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-03 | 2024-04-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1303.94 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-03 | 2024-03-01 | Unknown | Unknown | 2024-03-01 | 2024-04-04 | 35 | 25 | 2024-04-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | VALLEY CENTER | COUNTY OF SAN DIEGO-NORTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-05-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-01 | 2023-09-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1124.37 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-01 | 2023-09-15 | 15 | 11 | 2023-09-15 | 2023-10-06 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | 2023-09-15 | 2023-09-20 | 6 | 4 | 2023-10-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ALPINE | COUNTY OF SAN DIEGO-SOUTH of 56 | 58 | 58 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-02 | 2024-08-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2842.34 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-02 | 2024-09-09 | 161 | 115 | 2024-09-09 | 2024-12-05 | 88 | 64 | Unknown | Unknown | Unknown | Unknown | 2024-08-26 | 2024-09-03 | 9 | 7 | 2024-12-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | 1493.25 | 1493.25 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2024-11-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-29 | 2024-01-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2649.4 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-29 | 2024-01-17 | Unknown | Unknown | 2024-01-17 | 2024-03-26 | 70 | 50 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-15 | 2023-12-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 26990 | 332.81 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-15 | 2023-12-04 | 20 | 14 | 2023-12-04 | 2023-12-04 | 1 | 1 | 2023-12-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-29 | 2024-08-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1542.14 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-29 | 2024-06-25 | Unknown | Unknown | 2024-06-25 | 2024-08-01 | 38 | 28 | 2024-08-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 9.05 | 9.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-09 | 2024-12-09 | 2025-04-15 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 190.13 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-09 | 2025-01-09 | 32 | 24 | 2025-01-09 | 2025-02-14 | 37 | 27 | 2025-02-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-14 | 2025-04-15 | 61 | 43 | Unknown | Unknown | Unknown | Unknown | 2025-04-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | BORREGO SPRINGS | COUNTY OF SAN DIEGO-NORTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-24 | 2025-03-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1561.77 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-24 | 2025-03-24 | 1 | 1 | 2025-03-24 | 2025-04-18 | 26 | 20 | Unknown | Unknown | Unknown | Unknown | 2025-04-15 | 2025-04-22 | 8 | 6 | 2025-04-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | N/A | Rancho Mission Viejo | COUNTY OF ORANGE | 5.4 | 5.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-20 | 2024-03-20 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 23807.27 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-20 | 2024-11-01 | 227 | 163 | 2024-11-01 | 2025-03-13 | 133 | 95 | 2024-11-11 | 2025-05-22 | 156 | 112 | 2024-11-14 | 2025-02-04 | 69 | 49 | 2025-05-07 | Unknown | Unknown | Unknown | 2025-05-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-06 | 2024-03-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 163.83 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-06 | 2024-01-10 | Unknown | Unknown | 2024-01-10 | 2024-03-18 | 69 | 49 | 2024-03-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | Applicant Design | Residential | N/A | SD 1190-A2 CMR PA17 WO1 | N/A | 222214 | 222214 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-03-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-15 | 2024-05-15 | 2024-10-21 | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2024-05-15 | 2024-04-08 | Unknown | Unknown | 2024-04-08 | 2024-10-16 | 192 | 138 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-16 | 2024-10-23 | 8 | 6 | Unknown | 2024-10-21 | Unknown | Unknown | 2024-10-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Residential | N/A | San Diego | SAN DIEGO | 7 | 7 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-06 | 2023-12-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 47728.51 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-06 | 2023-10-06 | 1 | 1 | 2023-10-06 | 2024-09-04 | 335 | 239 | 2024-01-15 | 2025-03-12 | 92 | 66 | 2024-04-18 | 2024-10-24 | 78 | 56 | 2024-09-24 | Unknown | Unknown | Unknown | 2024-09-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R29/R45) | Both | IOU Design | Commercial | Underserved Community | JACUMBA | CALTRANS-SOUTH of 56, COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-22 | 2023-11-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 861545 | 205668.75 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-22 | 2023-12-18 | 88 | 62 | 2023-12-18 | 2024-10-10 | 298 | 214 | 2024-05-01 | 2025-07-15 | 155 | 109 | 2024-07-05 | 2025-07-23 | 138 | 95 | 2024-10-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-26 | 2025-02-26 | 2025-06-13 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1915.88 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-26 | 2025-02-26 | 1 | 1 | 2025-02-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-23 | 2025-06-13 | 52 | 38 | Unknown | Unknown | Unknown | Unknown | 2025-06-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | ESCONDIDO | 206 | 206 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-23 | 2024-10-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2548.64 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-23 | 2024-10-15 | 23 | 17 | 2024-10-15 | 2024-11-05 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 48.05 | 48.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-21 | 2024-05-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3941 | 1352.39 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-21 | 2024-04-03 | Unknown | Unknown | 2024-04-03 | 2024-05-21 | 49 | 35 | 2024-05-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-21 | 2025-07-21 | 427 | 305 | Unknown | Unknown | Unknown | Unknown | 2025-07-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2025-04-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-17 | 2024-04-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 482.43 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-17 | 2024-04-17 | 1 | 1 | 2024-04-17 | 2024-04-24 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-24 | 2024-10-23 | 183 | 131 | Unknown | 2025-08-13 | Unknown | Unknown | 2025-08-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 140.75 | 140.75 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-03 | 2024-09-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2485.7 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-03 | 2024-09-19 | 17 | 13 | 2024-09-19 | 2025-05-06 | 230 | 164 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-30 | 2024-12-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 695.89 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-30 | 2024-02-11 | Unknown | Unknown | 2024-02-11 | 2025-02-24 | 380 | 271 | 2025-02-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-05-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-23 | 2024-08-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 176950 | 14251.9 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-23 | 2024-08-23 | 1 | 1 | 2024-08-23 | 2024-09-04 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 108 | 108 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-18 | 2023-12-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1141.76 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-18 | 2023-12-18 | 1 | 1 | 2023-12-18 | 2023-12-18 | 1 | 1 | 2023-12-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 168.15 | 168.15 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-21 | 2024-05-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1484.59 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-21 | 2024-05-21 | 1 | 1 | 2024-05-21 | 2024-05-21 | 1 | 1 | 2024-05-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | 5 | 5 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-18 | 2025-04-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 642.71 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-18 | 2025-04-09 | Unknown | Unknown | 2025-04-09 | 2025-04-25 | 17 | 13 | 2025-04-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-25 | 2025-09-02 | 131 | 93 | Unknown | Unknown | Unknown | Unknown | 2025-09-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2021-11-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-03 | 2022-10-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 462332 | 7617.08 | Unknown | Unknown | Yes | N/A | N/A | 2022-10-03 | 2023-04-26 | 206 | 148 | 2023-04-26 | 2024-07-01 | 433 | 309 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | JAMUL | N/A | 67.05 | 67.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-22 | 2024-08-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3941 | 1451.44 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-22 | 2024-07-18 | Unknown | Unknown | 2024-07-18 | 2024-08-22 | 36 | 26 | 2024-08-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-22 | 2025-01-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1107.63 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-22 | 2025-01-15 | Unknown | Unknown | 2025-01-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 9.05 | 9.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-09 | 2025-01-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1774.21 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-09 | 2025-01-15 | 7 | 5 | 2025-01-15 | 2025-01-21 | 7 | 5 | 2025-01-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-04 | 2023-01-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | 18.51 | -2.42 | Unknown | Unknown | 7.94 | 12.99 | 3981 | 1102.73 | Unknown | Unknown | Yes | N/A | N/A | 2023-01-04 | 2023-02-24 | 52 | 38 | 2023-02-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-24 | Unknown | Unknown | Unknown | Unknown | 2024-07-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-27 | 2023-11-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 4055.15 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-27 | 2023-11-08 | 43 | 31 | 2023-11-08 | 2024-02-12 | 97 | 69 | Unknown | Unknown | Unknown | Unknown | 2024-08-07 | 2024-08-07 | 1 | 1 | 2024-02-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | Applicant Design | Commercial | Underserved Community | Vista | Vista | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-20 | 2024-08-20 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 67815.89 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-20 | 2024-11-15 | 88 | 64 | 2024-11-15 | 2025-01-27 | 74 | 52 | 2024-12-02 | 2025-01-16 | 15 | 11 | 2024-12-13 | 2025-01-27 | 25 | 17 | 2025-01-27 | Unknown | Unknown | Unknown | 2025-02-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | Both | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | IMPERIAL BEACH | 48.05 | 48.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-30 | Unknown | Unknown | No | 2024-04-18 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-18 | 2024-04-18 | 2025-03-20 | IOU Designed & Installed | N/A | Yes | 112 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1717.72 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-18 | 2024-08-16 | 121 | 87 | 2024-08-16 | 2024-05-06 | Unknown | Unknown | 2024-05-06 | 2024-08-21 | 108 | 78 | 2024-05-06 | 2024-07-30 | 40 | 30 | 2024-05-10 | 2025-03-20 | 315 | 225 | Unknown | Unknown | Unknown | Unknown | 2025-03-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | MOUNT LAGUNA | N/A | 73 | 73 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-11 | 2024-12-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 6582 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-11 | 2024-11-27 | Unknown | Unknown | 2024-11-27 | 2024-12-11 | 15 | 11 | 2024-12-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-03 | 2025-04-06 | 2025-06-19 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1210.27 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-03 | 2025-01-27 | 25 | 17 | 2025-01-27 | 2025-04-07 | 71 | 51 | 2025-04-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-06 | 2025-06-19 | 75 | 54 | Unknown | Unknown | Unknown | Unknown | 2025-06-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LA MESA | N/A | 13 | 13 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-11 | 2025-03-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2696.52 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-11 | 2025-03-17 | 7 | 5 | 2025-03-17 | 2025-05-22 | 67 | 49 | 2025-05-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-22 | Unknown | Unknown | Unknown | Unknown | 2025-08-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-15 | 2024-05-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2120.04 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-15 | 2024-05-30 | 16 | 12 | 2024-05-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-14 | 2024-02-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 534.53 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-14 | 2024-02-14 | 1 | 1 | 2024-02-14 | 2024-02-14 | 1 | 1 | 2024-02-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-26 | 2024-10-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 52.54 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-26 | 2024-10-04 | 9 | 7 | 2024-10-04 | 2024-10-04 | 1 | 1 | 2024-10-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-22 | 2024-11-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 1524 | 2527.94 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-22 | 2024-07-01 | Unknown | Unknown | 2024-07-01 | 2024-11-01 | 124 | 90 | 2024-11-01 | 2025-02-03 | 95 | 67 | Unknown | Unknown | Unknown | Unknown | 2025-02-03 | Unknown | Unknown | Unknown | Unknown | 2025-05-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | Applicant Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-04 | 2024-04-04 | 2025-06-27 | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | 24014.8 | 958.12 | Unknown | Unknown | Unknown | 23056.68 | 0 | 127205.43 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-04 | 2024-10-28 | 208 | 148 | 2024-10-28 | 2025-03-12 | 136 | 98 | 2024-10-28 | 2024-10-28 | 1 | 1 | 2025-03-17 | 2025-03-25 | 9 | 7 | 2025-03-12 | 2025-05-09 | 59 | 43 | 2025-03-26 | Unknown | Unknown | Unknown | 2025-06-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-26 | 2025-02-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1389.55 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-26 | 2025-01-28 | Unknown | Unknown | 2025-01-28 | 2025-02-27 | 31 | 23 | 2025-02-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-27 | 2025-07-22 | 146 | 104 | Unknown | 2025-07-11 | Unknown | Unknown | 2025-07-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-19 | 2025-05-19 | 2025-06-12 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3477.55 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-19 | 2025-05-05 | Unknown | Unknown | 2025-05-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | Santee | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-19 | 2024-09-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2105.46 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-19 | 2024-09-17 | Unknown | Unknown | 2024-09-17 | 2024-09-27 | 11 | 9 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-01 | 2025-05-15 | 2025-05-19 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1197.24 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-01 | 2025-04-17 | Unknown | Unknown | 2025-04-17 | 2025-05-16 | 30 | 22 | 2025-05-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-15 | 2025-05-19 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | 2025-05-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | CHULA VISTA | 6.05 | 6.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-20 | 2025-06-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1366.96 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-20 | 2025-06-20 | 1 | 1 | 2025-06-20 | 2025-06-20 | 1 | 1 | 2025-06-20 | Unknown | Unknown | Unknown | 2025-06-23 | 2025-06-27 | 5 | 5 | 2025-06-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SANTA YSABEL | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-16 | 2024-10-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 362124.08 | 6070.32 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-16 | 2024-05-23 | Unknown | Unknown | 2024-05-23 | 2025-03-10 | 292 | 208 | 2025-01-17 | 2025-02-11 | 26 | 18 | 2025-02-14 | 2025-02-14 | 1 | 1 | 2025-03-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-17 | 2025-03-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 4556.1 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-17 | 2025-03-03 | Unknown | Unknown | 2025-03-03 | 2025-05-05 | 64 | 46 | Unknown | Unknown | Unknown | Unknown | 2025-06-12 | 2025-06-27 | 16 | 12 | 2025-05-05 | Unknown | Unknown | Unknown | Unknown | 2025-07-01 | Unknown | Unknown | 2025-07-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 100.1 | 100.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-10 | 2024-12-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1525.69 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-10 | 2024-12-09 | Unknown | Unknown | 2024-12-09 | 2024-12-10 | 2 | 2 | 2024-12-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-30 | 2025-04-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 12481 | 397.2 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-30 | 2025-04-15 | Unknown | Unknown | 2025-04-15 | 2025-04-30 | 16 | 12 | 2025-04-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN MARCOS | N/A | 154.05 | 154.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-15 | 2024-04-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2447.3 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-15 | 2025-01-10 | 271 | 195 | 2025-01-10 | 2025-01-17 | 8 | 6 | 2024-12-11 | 2025-03-26 | 70 | 50 | Unknown | Unknown | Unknown | Unknown | 2025-03-26 | 2025-08-19 | 147 | 105 | Unknown | 2025-06-23 | Unknown | Unknown | 2025-08-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | RAMONA | COUNTY OF SAN DIEGO-NORTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-15 | 2024-02-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 898.72 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-15 | 2024-02-12 | Unknown | Unknown | 2024-02-12 | 2024-02-16 | 5 | 5 | 2024-02-16 | Unknown | Unknown | Unknown | 2024-02-16 | 2024-02-29 | 14 | 10 | 2024-02-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2025-12-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-15 | 2023-09-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1745.74 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-15 | 2023-09-27 | 13 | 9 | 2023-09-27 | 2023-10-09 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2023-09-28 | 2023-10-03 | 6 | 4 | 2023-10-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | ALPINE | N/A | 20 | 20 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-12 | 2025-03-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 4184.13 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-12 | 2025-03-12 | 1 | 1 | 2025-03-12 | 2025-03-13 | 2 | 2 | 2025-03-13 | 2025-04-15 | 34 | 24 | Unknown | Unknown | Unknown | Unknown | 2025-04-17 | Unknown | Unknown | Unknown | Unknown | 2025-05-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | 651 | 651 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-10 | 2023-08-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 79479.52 | 21943.89 | Unknown | Unknown | Yes | N/A | N/A | 2023-01-10 | 2023-06-28 | 170 | 122 | 2023-06-28 | 2024-11-26 | 518 | 370 | 2023-12-29 | 2024-01-08 | 11 | 7 | 2024-10-03 | 2024-12-04 | 50 | 36 | Unknown | Unknown | Unknown | Unknown | 2025-05-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-09 | 2025-06-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1124.22 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-09 | 2025-05-27 | Unknown | Unknown | 2025-05-27 | 2025-06-11 | 16 | 12 | 2025-06-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-18 | 2024-11-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3241 | 507.87 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-18 | 2024-11-18 | 1 | 1 | 2024-11-18 | 2024-11-18 | 1 | 1 | 2024-11-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | San Diego | COUNTY OF SAN DIEGO-SOUTH of 56, SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-24 | 2025-04-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 37843.22 | 38544.66 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-24 | 2025-03-14 | 50 | 36 | 2025-03-14 | 2025-06-25 | 104 | 74 | 2025-05-07 | 2025-05-08 | 2 | 2 | 2025-06-11 | 2025-07-09 | 27 | 17 | 2025-06-25 | Unknown | Unknown | Unknown | 2025-07-01 | 2025-07-22 | 22 | 16 | 2025-08-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-16 | 2024-06-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 560.26 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-16 | 2024-05-10 | 85 | 61 | 2024-05-10 | 2024-11-21 | 196 | 140 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | EL CAJON | EL CAJON | 55 | 55 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-10 | 2024-08-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 10499.59 | 23846.36 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-10 | 2024-07-23 | 44 | 32 | 2024-07-23 | 2024-10-29 | 99 | 71 | 2024-10-07 | 2024-11-04 | 5 | 3 | 2024-10-17 | 2025-07-10 | 54 | 36 | 2024-10-29 | Unknown | Unknown | Unknown | 2024-11-12 | 2025-06-06 | 207 | 149 | 2025-07-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LEMON GROVE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-08 | 2025-04-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1029.34 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-08 | 2025-03-04 | Unknown | Unknown | 2025-03-04 | 2025-04-08 | 36 | 26 | 2025-04-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-24 | 2024-01-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 872.08 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-24 | 2024-01-26 | 3 | 3 | 2024-01-26 | 2024-01-26 | 1 | 1 | 2024-01-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-06-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-17 | 2025-06-17 | 2025-06-24 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1194.27 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-17 | 2025-06-11 | Unknown | Unknown | 2025-06-11 | 2025-06-17 | 7 | 5 | 2025-06-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-17 | 2025-06-24 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2025-06-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-05 | 2024-09-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1577.33 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-05 | 2024-09-09 | 5 | 3 | 2024-09-09 | 2024-09-09 | 1 | 1 | 2024-09-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SANTEE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-29 | 2023-11-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 778.08 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-29 | 2023-10-26 | Unknown | Unknown | 2023-10-26 | 2023-12-14 | 50 | 36 | 2023-12-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 9000 | 9000 | Not Available | >2MW | No | N/A | N/A | N/A | 2025-11-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-05 | 2023-12-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2147.34 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-05 | 2023-11-14 | Unknown | Unknown | 2023-11-14 | 2024-01-19 | 67 | 49 | 2024-01-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-10 | 2023-08-17 | 2023-09-28 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 9638.23 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-10 | 2023-08-17 | 39 | 29 | 2023-08-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-19 | 2023-09-27 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-24 | 2025-01-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1623.21 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-24 | 2025-01-24 | 1 | 1 | 2025-01-24 | 2025-01-24 | 1 | 1 | 2025-01-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 33 | 33 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-22 | 2024-05-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 944.47 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-22 | 2024-05-17 | 26 | 20 | 2024-05-17 | 2024-05-17 | 1 | 1 | 2024-05-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-13 | 2025-05-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3758.74 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-13 | 2025-05-20 | 8 | 6 | 2025-05-20 | 2025-05-21 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | OC 1086-G1 RIVERVIEW SPRG | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-29 | 2024-06-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2024-01-29 | 2024-06-07 | 131 | 95 | 2024-06-07 | 2024-08-26 | 81 | 57 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 29.1 | 29.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-12 | 2024-12-12 | 2025-02-20 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3885 | 1818.6 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-12 | 2024-12-02 | Unknown | Unknown | 2024-12-02 | 2024-12-12 | 11 | 9 | 2024-12-12 | 2024-12-18 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2024-12-18 | 2025-02-20 | 65 | 47 | Unknown | 2025-01-28 | Unknown | Unknown | 2025-02-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-29 | 2025-05-29 | 2025-06-26 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 4868.43 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-29 | 2025-05-28 | Unknown | Unknown | 2025-05-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 68.05 | 68.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-03 | 2025-03-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1118.54 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-03 | 2025-03-05 | 3 | 3 | 2025-03-05 | 2025-03-05 | 1 | 1 | 2025-03-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-06 | 2025-06-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1421.05 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-06 | 2025-06-02 | Unknown | Unknown | 2025-06-02 | 2025-06-12 | 11 | 9 | 2025-06-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 146.1 | 146.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-27 | 2025-04-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7962 | 3980.14 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-27 | 2025-03-17 | Unknown | Unknown | 2025-03-17 | 2025-04-17 | 32 | 24 | 2025-04-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-17 | 2025-08-12 | 118 | 84 | Unknown | Unknown | Unknown | Unknown | 2025-08-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Commercial | Underserved Community | San Juan Capistrano | MISSION VIEJO | 6503 | 6503 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-08-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-04 | 2024-09-24 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 123584.71 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-04 | 2024-11-12 | 223 | 159 | 2024-11-12 | 2025-07-09 | 240 | 172 | 2025-04-22 | 2025-05-22 | 15 | 11 | 2025-02-11 | 2025-06-30 | 89 | 65 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2026-03-05 | Unknown | Unknown | No | 2024-09-03 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-03 | 2024-09-05 | Unknown | IOU Designed & Installed | N/A | Yes | 246 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 54899 | 7565.56 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-03 | 2025-08-12 | 344 | 246 | 2025-08-12 | 2025-06-04 | Unknown | Unknown | 2025-08-27 | 2025-08-27 | 1 | 1 | 2024-09-20 | 2024-10-22 | 33 | 23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN CLEMENTE | N/A | 136 | 136 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-23 | 2023-10-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 163.83 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-23 | 2023-10-19 | Unknown | Unknown | 2023-10-19 | 2024-01-26 | 100 | 72 | 2024-01-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | 2.7 | 2.7 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-31 | 2024-10-31 | 2024-10-31 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1633.98 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-31 | 2024-10-31 | 1 | 1 | 2024-10-31 | 2024-10-31 | 1 | 1 | 2024-10-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-31 | 2024-10-31 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-10-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | OCEANSIDE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-15 | 2024-02-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 298.57 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-15 | 2023-12-15 | Unknown | Unknown | 2023-12-15 | 2024-02-26 | 74 | 52 | 2024-02-26 | Unknown | Unknown | Unknown | 2024-03-08 | 2024-03-19 | 12 | 8 | 2024-03-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | CARLSBAD | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-14 | 2024-05-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1169.03 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-14 | 2024-04-04 | Unknown | Unknown | 2024-04-04 | Unknown | Unknown | Unknown | 2024-06-18 | 2024-07-10 | 23 | 17 | 2024-06-06 | 2024-06-18 | 13 | 9 | 2024-07-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 1 | 1 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-14 | 2023-07-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 496.45 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-14 | 2023-07-14 | 1 | 1 | 2023-07-14 | 2023-07-14 | 1 | 1 | 2023-07-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 302 | 302 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-30 | 2024-09-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2146.19 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-30 | 2024-08-21 | Unknown | Unknown | 2024-08-21 | 2025-05-27 | 280 | 200 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-22 | 2024-07-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3840 | 510.58 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-22 | 2024-07-22 | 1 | 1 | 2024-07-22 | 2024-07-22 | 1 | 1 | 2024-07-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-22 | 2025-07-24 | 368 | 264 | Unknown | Unknown | Unknown | Unknown | 2025-07-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 136 | 136 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-03 | 2024-07-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 444.8 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-03 | 2024-04-24 | Unknown | Unknown | 2024-04-24 | 2024-07-03 | 71 | 51 | 2024-07-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 126 | 126 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-11 | 2024-05-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1703.79 | Unknown | Unknown | Yes | N/A | N/A | 2022-09-11 | 2024-05-07 | 605 | 432 | 2024-05-07 | 2024-08-09 | 95 | 69 | Unknown | Unknown | Unknown | Unknown | 2024-08-06 | 2024-08-09 | 4 | 4 | 2024-08-09 | 2024-12-13 | 127 | 91 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 105.05 | 105.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-19 | 2023-12-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 501.62 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-19 | 2023-08-25 | Unknown | Unknown | 2023-08-25 | 2024-01-30 | 159 | 113 | 2024-01-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN MARCOS | N/A | 17 | 17 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-02 | 2025-04-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1074.31 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-02 | 2025-03-30 | Unknown | Unknown | 2025-03-30 | 2025-04-23 | 25 | 18 | 2025-04-03 | 2025-04-23 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | 2025-04-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-08 | 2025-05-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1076.04 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-08 | 2025-04-24 | Unknown | Unknown | 2025-04-24 | 2025-05-22 | 29 | 21 | 2025-05-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | EL CAJON | EL CAJON | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-05-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-17 | 2023-07-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2875 | 865.15 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-17 | 2023-07-17 | 1 | 1 | 2023-07-17 | 2024-02-05 | 204 | 146 | 2025-06-09 | Unknown | Unknown | Unknown | 2025-04-03 | 2025-06-09 | 68 | 48 | 2024-02-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-22 | 2024-04-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2024-04-22 | 2024-01-23 | Unknown | Unknown | 2024-01-23 | 2024-10-15 | 267 | 191 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-15 | 2025-02-12 | 121 | 87 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-16 | 2025-06-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1082.32 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-16 | 2025-06-23 | 190 | 136 | 2025-06-23 | 2025-06-24 | 2 | 2 | 2025-06-24 | Unknown | Unknown | Unknown | 2025-06-26 | 2025-07-03 | 8 | 6 | 2025-06-24 | 2025-07-07 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | 2025-07-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 65.05 | 65.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-20 | 2024-12-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1789.3 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-20 | 2024-10-11 | Unknown | Unknown | 2024-10-11 | 2024-12-20 | 71 | 51 | 2024-12-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN MARCOS | N/A | 117.05 | 117.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-28 | 2025-05-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1505.98 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-28 | 2025-05-15 | Unknown | Unknown | 2025-05-15 | 2025-05-30 | 16 | 12 | 2025-05-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | BONITA | N/A | 474.15 | 474.15 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-21 | 2023-03-21 | 2024-08-13 | IOU Designed & Installed | N/A | No | Unknown | 2747.55 | 0 | Unknown | Unknown | 209.02 | 2538.53 | 3941 | 695.77 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-21 | 2023-02-07 | Unknown | Unknown | 2023-02-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-20 | 2024-08-13 | Unknown | Unknown | Unknown | 2024-08-20 | Unknown | Unknown | 2024-08-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | JULIAN | COUNTY OF SAN DIEGO-NORTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-30 | 2024-07-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 21861.02 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-30 | 2024-06-19 | 21 | 15 | 2024-06-19 | Unknown | Unknown | Unknown | 2024-10-10 | 2024-10-17 | 8 | 6 | 2024-11-07 | 2025-03-20 | 29 | 21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | LA JOLLA | N/A | 83 | 83 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-08-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-04 | 2024-04-10 | 2025-03-14 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 813.93 | Unknown | Unknown | Yes | N/A | N/A | 2022-05-04 | 2024-04-03 | 701 | 501 | 2024-04-03 | 2024-04-10 | 8 | 6 | 2024-04-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-10 | 2025-03-14 | 339 | 243 | Unknown | Unknown | Unknown | Unknown | 2025-03-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2026-03-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-06 | 2024-03-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 54899 | 84.08 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-06 | 2025-05-20 | 441 | 315 | 2025-05-20 | 2024-11-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-11 | 2024-10-22 | 65 | 46 | 2024-11-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 104 | 104 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-21 | 2024-03-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3941 | 891.54 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-21 | 2024-02-07 | Unknown | Unknown | 2024-02-07 | 2024-03-21 | 44 | 32 | 2024-03-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | CHULA VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-14 | 2025-05-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1370.15 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-14 | 2025-05-14 | 1 | 1 | 2025-05-14 | 2025-05-14 | 1 | 1 | 2025-05-14 | Unknown | Unknown | Unknown | 2025-05-16 | 2025-05-23 | 8 | 6 | 2025-05-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-13 | 2024-09-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2614.73 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-13 | 2024-09-23 | 11 | 7 | 2024-09-23 | 2024-09-26 | 4 | 4 | 2024-09-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-24 | 2023-07-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2013.37 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-24 | 2023-07-31 | 8 | 6 | 2023-07-31 | 2023-08-11 | 12 | 10 | 2023-08-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 10 | 10 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-18 | Unknown | Unknown | No | 2024-03-29 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-29 | 2024-05-03 | 2025-01-24 | IOU Designed & Installed | N/A | Yes | 461 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 837.08 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-29 | 2025-07-03 | 462 | 330 | 2025-07-03 | 2024-05-03 | Unknown | Unknown | 2024-05-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-03 | 2025-01-24 | 267 | 191 | Unknown | Unknown | Unknown | Unknown | 2025-01-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-14 | 2023-07-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 793.52 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-14 | 2023-05-09 | Unknown | Unknown | 2023-05-09 | 2023-07-14 | 67 | 49 | 2023-07-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LAGUNA NIGUEL | N/A | 119 | 119 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-25 | 2025-02-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1454.85 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-25 | 2025-03-19 | 23 | 17 | 2025-03-19 | 2025-03-19 | 1 | 1 | 2025-03-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-10 | 2024-07-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3961 | 192.95 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-10 | 2024-06-04 | Unknown | Unknown | 2024-06-04 | 2024-07-29 | 56 | 40 | 2024-07-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-04 | 2025-04-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 853.08 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-04 | 2025-05-05 | 32 | 22 | 2025-05-05 | 2025-05-29 | 25 | 19 | 2025-04-09 | 2025-06-06 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | 2025-06-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Commercial | Underserved Community | CHULA VISTA | CHULA VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-27 | 2023-09-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2813.21 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-27 | 2023-09-27 | 1 | 1 | 2023-09-27 | 2023-11-20 | 55 | 39 | 2023-11-17 | 2023-11-17 | 1 | 1 | 2023-10-13 | 2023-10-18 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-07-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-11 | 2024-12-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 379981 | 19715.05 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-11 | 2024-12-05 | Unknown | Unknown | 2024-12-05 | 2025-01-09 | 36 | 26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | Chula Vista | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-02-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-20 | 2025-02-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 65076 | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2025-02-20 | 2025-02-24 | 5 | 3 | 2025-02-24 | 2025-02-26 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-12 | 2023-06-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 790.4 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-12 | 2023-06-09 | Unknown | Unknown | 2023-06-09 | 2023-06-20 | 12 | 8 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-31 | 2023-07-31 | Unknown | IOU Designed & Installed | N/A | No | Unknown | 526.96 | 0 | Unknown | Unknown | 6.1 | 520.86 | 3981 | 1108.58 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-31 | 2024-10-14 | 442 | 316 | 2024-10-14 | 2024-10-14 | 1 | 1 | 2024-10-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-14 | 2025-07-07 | 267 | 191 | Unknown | 2025-06-02 | Unknown | Unknown | 2025-07-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | LAKESIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-06 | 2024-08-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 1786 | 1202.05 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-06 | 2024-07-17 | Unknown | Unknown | 2024-07-17 | 2024-08-15 | 30 | 22 | 2024-08-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-11 | 2024-11-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1418.83 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-11 | 2024-11-01 | Unknown | Unknown | 2024-11-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-27 | 2025-08-18 | 145 | 103 | Unknown | 2025-06-27 | Unknown | Unknown | 2025-08-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-18 | 2025-03-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2221.71 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-18 | 2025-02-05 | Unknown | Unknown | 2025-02-05 | 2025-03-03 | 27 | 19 | 2025-03-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2022-02-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-02 | 2024-04-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 352.82 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-02 | 2024-04-03 | 2 | 2 | 2024-04-03 | 2024-05-09 | 37 | 27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-08-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-07 | 2025-02-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1589.72 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-07 | 2025-03-11 | 33 | 23 | 2025-03-11 | 2025-03-11 | 1 | 1 | 2025-03-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | ENCINITAS | N/A | 102.05 | 102.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-19 | 2024-08-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1537.34 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-19 | 2024-01-25 | Unknown | Unknown | 2024-01-25 | 2025-05-13 | 475 | 339 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-13 | 2025-07-31 | 80 | 58 | Unknown | Unknown | Unknown | Unknown | 2025-08-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | CARDIFF | ENCINITAS | 97 | 97 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-16 | 2024-01-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 957.59 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-16 | 2024-01-04 | 142 | 102 | 2024-01-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-10 | 2024-02-23 | 45 | 33 | 2024-01-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-02 | 2023-05-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 53981 | 555.18 | Unknown | Unknown | Yes | N/A | N/A | 2023-05-02 | 2023-08-20 | 111 | 79 | 2023-08-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | VALLEY CENTER | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2021-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-30 | 2023-09-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 641.28 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-30 | 2023-10-02 | 34 | 24 | 2023-10-02 | 2023-10-16 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 105 | 105 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-03 | 2025-04-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2153.74 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-03 | 2025-03-27 | Unknown | Unknown | 2025-03-27 | 2025-04-14 | 19 | 13 | 2025-04-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 6.75 | 6.75 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-22 | 2025-04-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1346.95 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-22 | 2025-04-11 | Unknown | Unknown | 2025-04-11 | 2025-04-28 | 18 | 12 | 2025-04-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-05 | 2024-12-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1266.45 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-05 | 2024-12-05 | 1 | 1 | 2024-12-05 | 2024-12-05 | 1 | 1 | 2024-12-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-11-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-20 | 2024-08-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 14088.1 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-20 | 2025-01-14 | 148 | 106 | 2025-01-14 | 2025-02-18 | 36 | 26 | Unknown | Unknown | Unknown | Unknown | 2024-08-29 | 2025-02-20 | 70 | 50 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-14 | 2024-03-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 759.79 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-14 | 2023-12-12 | Unknown | Unknown | 2023-12-12 | 2024-04-11 | 122 | 88 | 2024-04-11 | 2024-05-24 | 44 | 32 | Unknown | Unknown | Unknown | Unknown | 2024-05-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-05 | 2024-06-06 | 2024-07-23 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1526.71 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-05 | 2024-04-30 | Unknown | Unknown | 2024-04-30 | 2024-06-06 | 38 | 28 | 2024-06-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-06 | 2024-07-23 | 48 | 34 | Unknown | Unknown | Unknown | Unknown | 2024-07-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CORONADO | CORONADO | 5 | 5 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-06 | 2025-02-07 | 2025-03-31 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1762.47 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-06 | 2025-02-06 | 1 | 1 | 2025-02-06 | 2025-02-06 | 1 | 1 | 2025-02-06 | Unknown | Unknown | Unknown | 2025-02-11 | 2025-03-18 | 36 | 26 | 2025-02-07 | 2025-03-31 | 53 | 37 | Unknown | Unknown | Unknown | Unknown | 2025-03-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-06-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-20 | 2025-06-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1345.74 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-20 | 2025-06-11 | Unknown | Unknown | 2025-06-11 | 2025-06-26 | 16 | 12 | 2025-06-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | 65.05 | 65.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-02 | 2025-01-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 783.77 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-02 | 2024-12-12 | Unknown | Unknown | 2024-12-12 | 2025-01-06 | 26 | 18 | 2025-01-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-06 | 2025-07-11 | 187 | 135 | Unknown | 2025-06-30 | Unknown | Unknown | 2025-07-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 68.05 | 68.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-14 | 2024-03-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1109.09 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-14 | 2024-02-13 | Unknown | Unknown | 2024-02-13 | 2024-03-20 | 37 | 27 | 2024-03-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-20 | Unknown | Unknown | Unknown | Unknown | 2025-09-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | CORONADO | CORONADO | 325 | 325 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-04 | 2024-03-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 25258 | 7823.4 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-04 | 2024-06-12 | 101 | 73 | 2024-06-12 | 2024-09-09 | 90 | 64 | Unknown | Unknown | Unknown | Unknown | 2024-03-12 | 2024-04-02 | 22 | 16 | 2024-09-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | IOU Design | Commercial | N/A | POWAY | POWAY | 2915 | 2915 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-12-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-18 | 2024-06-20 | 2025-06-27 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 23593.46 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-18 | 2024-06-12 | Unknown | Unknown | 2024-06-12 | 2025-05-05 | 328 | 234 | Unknown | Unknown | Unknown | Unknown | 2024-08-27 | 2025-04-25 | 23 | 17 | 2025-05-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 553.15 | 553.15 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-20 | 2025-04-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 3205.58 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-20 | 2025-04-07 | 47 | 33 | 2025-04-07 | 2025-04-07 | 1 | 1 | 2025-03-26 | 2025-04-07 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2025-04-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | Julian | COUNTY OF SAN DIEGO-NORTH of 56 | 168.2 | 168.2 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-06 | 2025-05-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 15096.47 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-06 | 2025-05-07 | 2 | 2 | 2025-05-07 | Unknown | Unknown | Unknown | 2025-05-12 | 2025-06-23 | 23 | 17 | 2025-05-06 | 2025-07-02 | 19 | 15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 91 | 91 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-31 | 2023-08-16 | 2023-09-18 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 975.8 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-31 | 2023-08-16 | 17 | 13 | 2023-08-16 | 2023-08-16 | 1 | 1 | 2023-08-16 | 2023-09-19 | 35 | 25 | Unknown | Unknown | Unknown | Unknown | 2023-09-13 | 2023-09-18 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2023-09-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 14.7 | 14.7 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-08 | 2025-04-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1496.98 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-08 | 2025-06-19 | 73 | 53 | 2025-06-19 | 2025-06-19 | 1 | 1 | 2025-06-19 | 2025-08-14 | 57 | 41 | Unknown | Unknown | Unknown | Unknown | 2025-06-23 | Unknown | Unknown | Unknown | Unknown | 2025-08-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-23 | 2024-04-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1240.03 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-23 | 2024-06-11 | 50 | 36 | 2024-06-11 | 2024-07-05 | 25 | 19 | 2024-07-05 | 2024-08-14 | 41 | 29 | Unknown | Unknown | Unknown | Unknown | 2024-08-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-24 | 2025-06-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1283.4 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-24 | 2025-06-24 | 1 | 1 | 2025-06-24 | 2025-06-24 | 1 | 1 | 2025-06-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | Escondido | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-23 | 2024-09-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1680.8 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-23 | 2024-09-17 | Unknown | Unknown | 2024-09-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | CORONADO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-21 | Unknown | Unknown | No | 2023-01-18 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-18 | 2023-01-18 | 2023-01-18 | IOU Designed & Installed | N/A | Yes | 152 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 379.71 | Unknown | Unknown | Yes | N/A | N/A | 2023-01-18 | 2023-06-19 | 153 | 109 | 2023-06-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-01-30 | 2023-01-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-01-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-09 | 2025-06-13 | 2025-06-16 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1426.09 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-09 | 2025-06-11 | 3 | 3 | 2025-06-11 | 2025-06-13 | 3 | 3 | 2025-06-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-13 | 2025-06-16 | 4 | 2 | Unknown | Unknown | Unknown | Unknown | 2025-06-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-07 | 2024-06-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 113255 | 5155.54 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-07 | 2024-06-13 | 38 | 28 | 2024-06-13 | 2024-06-19 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-19 | 2025-07-18 | 395 | 283 | Unknown | 2025-07-07 | Unknown | Unknown | 2025-07-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-07 | 2023-03-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1005.21 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-07 | 2023-05-30 | 85 | 61 | 2023-05-30 | 2023-12-05 | 190 | 136 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | OH | IOU Design | Residential | N/A | ENCINITAS | ENCINITAS | 102.05 | 102.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-01 | 2024-01-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 41371.29 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-01 | 2024-01-11 | 225 | 161 | 2024-01-11 | 2025-05-13 | 489 | 349 | 2024-04-24 | 2025-04-08 | 7 | 3 | 2024-04-05 | 2025-04-03 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-08-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | CHULA VISTA | CALTRANS-SOUTH of 56, CHULA VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-07 | 2024-07-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3459.2 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-07 | 2024-04-30 | Unknown | Unknown | 2024-04-30 | 2024-09-27 | 151 | 109 | 2024-09-27 | 2024-11-27 | 57 | 41 | 2024-09-27 | 2025-01-31 | 81 | 59 | 2024-09-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-08 | 2024-07-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 579781 | 29778.51 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-08 | 2024-07-08 | 1 | 1 | 2024-07-08 | 2024-07-11 | 4 | 4 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-11 | 2025-09-03 | 420 | 300 | Unknown | 2025-09-02 | Unknown | Unknown | 2025-09-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | POWAY | POWAY | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-25 | 2022-07-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1288.17 | Unknown | Unknown | Yes | N/A | N/A | 2022-07-25 | 2023-04-03 | 253 | 181 | 2023-04-03 | 2023-05-08 | 36 | 26 | Unknown | Unknown | Unknown | Unknown | 2023-02-25 | 2023-03-17 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 60.05 | 60.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-23 | 2025-05-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1250.75 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-23 | 2025-05-30 | 8 | 6 | 2025-05-30 | 2025-05-30 | 1 | 1 | 2025-05-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-23 | 2024-11-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1185.03 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-23 | 2024-10-24 | 2 | 2 | 2024-10-24 | 2024-11-07 | 15 | 11 | 2024-11-07 | 2025-02-11 | 97 | 69 | Unknown | Unknown | Unknown | Unknown | 2025-02-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | N/A | 11 | 11 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-24 | 2024-06-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 282.95 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-24 | 2024-07-03 | 10 | 8 | 2024-07-03 | 2024-07-03 | 1 | 1 | 2024-07-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | 23 | 23 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-20 | 2023-11-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 57583 | 3738.48 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-20 | 2023-12-12 | 23 | 17 | 2023-12-12 | 2024-03-07 | 87 | 63 | Unknown | Unknown | Unknown | Unknown | 2024-03-06 | 2024-03-19 | 14 | 10 | 2024-03-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 68 | 68 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-17 | 2023-12-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 229.88 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-17 | 2023-10-19 | Unknown | Unknown | 2023-10-19 | 2023-12-19 | 62 | 44 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | IMPERIAL BEACH | IMPERIAL BEACH | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-08 | 2024-03-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1967 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-08 | 2024-03-29 | 51 | 37 | 2024-03-29 | 2024-10-31 | 217 | 155 | Unknown | Unknown | Unknown | Unknown | 2024-04-04 | 2024-07-10 | 98 | 70 | 2024-10-31 | Unknown | Unknown | Unknown | Unknown | 2025-09-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SANTEE | N/A | 70 | 70 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-12 | 2024-11-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2766.94 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-12 | 2024-10-30 | Unknown | Unknown | 2024-10-30 | 2024-11-26 | 28 | 20 | 2024-11-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | OCEANSIDE | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2024-09-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-17 | 2024-10-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 6875 | 588.31 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-17 | 2024-10-17 | 1 | 1 | 2024-10-17 | 2025-06-23 | 250 | 178 | Unknown | Unknown | Unknown | Unknown | 2025-04-04 | 2025-04-25 | 22 | 16 | 2025-06-23 | 2025-08-19 | 58 | 42 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | 68.05 | 68.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-02 | 2024-12-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1615.43 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-02 | 2024-11-15 | Unknown | Unknown | 2024-11-15 | 2024-12-05 | 21 | 15 | 2024-12-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SANTEE | SANTEE | 36 | 36 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-20 | 2024-09-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 73749 | 6236.96 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-20 | 2024-09-20 | 1 | 1 | 2024-09-20 | 2024-09-24 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | 2024-09-20 | 2024-10-07 | 18 | 12 | 2024-09-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | BORREGO SPRINGS | N/A | 131.05 | 131.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-23 | 2025-06-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1664.13 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-23 | 2025-05-20 | Unknown | Unknown | 2025-05-20 | 2025-06-23 | 35 | 25 | 2025-06-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-23 | 2025-08-22 | 61 | 45 | Unknown | Unknown | Unknown | Unknown | 2025-08-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 10.7 | 10.7 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-10 | 2025-02-10 | 2025-04-15 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2151.13 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-10 | 2025-02-24 | 15 | 11 | 2025-02-24 | 2025-03-20 | 25 | 19 | 2025-03-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-20 | 2025-04-15 | 27 | 19 | Unknown | Unknown | Unknown | Unknown | 2025-04-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | 3 | 3 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-07 | 2024-09-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 11943 | 1532.17 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-07 | 2024-09-10 | 35 | 25 | 2024-09-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-30 | 2024-11-01 | 33 | 25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-07 | 2023-09-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1274.02 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-07 | 2023-09-07 | 1 | 1 | 2023-09-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 93.05 | 93.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-26 | 2025-04-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 5680.95 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-26 | 2025-04-11 | 198 | 142 | 2025-04-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | POWAY | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-06 | 2025-05-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 863.94 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-06 | 2025-06-05 | 31 | 23 | 2025-06-05 | 2025-06-09 | 5 | 3 | 2025-06-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-09 | 2025-08-06 | 59 | 43 | Unknown | 2025-08-06 | Unknown | Unknown | 2025-08-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | N/A | ENCINITAS | N/A | 70 | 70 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-12 | 2025-04-03 | 2025-06-17 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 28703 | 2113.12 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-12 | 2025-04-01 | 202 | 144 | 2025-04-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-08-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CB 1127-B7 OCEAN VIEW MSO (E) | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-10 | 2023-10-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2023-10-10 | 2023-05-15 | Unknown | Unknown | 2023-05-15 | 2025-05-02 | 719 | 515 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | OH | IOU Design | Commercial | N/A | Irvine | NATIONAL CITY | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-04 | 2023-02-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 25593.56 | 11904.62 | Unknown | Unknown | Yes | N/A | N/A | 2023-01-04 | 2023-02-27 | 55 | 39 | 2023-02-27 | 2023-11-28 | 275 | 197 | 2023-07-21 | 2023-08-28 | 26 | 18 | 2023-06-19 | 2023-09-08 | 60 | 46 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | Both | IOU Design | Residential | Underserved Community | ES 1130-E7 BB (E) | N/A | 47.05 | 47.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-17 | 2024-10-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 27377.87 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-17 | 2024-10-11 | Unknown | Unknown | 2024-10-11 | 2025-04-18 | 190 | 136 | 2025-01-03 | 2025-02-05 | 34 | 24 | 2025-04-16 | 2025-04-30 | 15 | 11 | 2025-04-18 | Unknown | Unknown | Unknown | 2025-05-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-21 | 2025-04-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 118.25 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-21 | 2025-04-09 | Unknown | Unknown | 2025-04-09 | 2025-04-23 | 15 | 11 | 2025-04-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | 45.05 | 45.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-18 | 2025-05-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1043.26 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-18 | 2025-04-11 | Unknown | Unknown | 2025-04-11 | 2025-05-06 | 26 | 18 | 2025-05-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-03 | 2025-04-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 19905 | 1555.19 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-03 | 2025-04-07 | 36 | 26 | 2025-04-07 | 2025-04-09 | 3 | 3 | 2025-04-09 | 2025-04-09 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2025-04-09 | 2025-08-04 | 118 | 84 | Unknown | Unknown | Unknown | Unknown | 2025-08-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | CARLSBAD | CARLSBAD | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-02 | 2025-06-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 1656 | 661.11 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-02 | 2025-05-15 | Unknown | Unknown | 2025-05-15 | 2025-06-04 | 21 | 15 | 2025-06-04 | Unknown | Unknown | Unknown | 2025-06-04 | 2025-06-27 | 24 | 18 | 2025-06-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | NATIONAL CITY | NATIONAL CITY | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2025-04-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-30 | 2024-05-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 51.19 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-30 | 2024-05-01 | 2 | 2 | 2024-05-01 | 2024-09-12 | 135 | 97 | Unknown | Unknown | Unknown | Unknown | 2024-05-22 | 2024-08-21 | 92 | 66 | 2024-09-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-28 | 2025-01-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1270.28 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-28 | 2025-02-12 | 16 | 12 | 2025-02-12 | 2025-02-12 | 1 | 1 | 2025-02-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | LAGUNA NIGUEL | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-10 | 2024-09-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 850.21 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-10 | 2025-02-11 | 155 | 111 | 2025-02-11 | 2025-03-11 | 29 | 21 | 2025-03-11 | 2025-03-11 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2025-03-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 15 | 15 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-01 | 2023-11-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 481.24 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-01 | 2023-08-16 | Unknown | Unknown | 2023-08-16 | 2023-11-17 | 94 | 68 | 2023-11-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-22 | 2024-10-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2702.04 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-22 | 2024-09-27 | Unknown | Unknown | 2024-09-27 | 2024-12-18 | 83 | 59 | 2024-12-18 | 2025-01-07 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | 2025-01-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-25 | 2024-11-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1221.31 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-25 | 2024-11-22 | Unknown | Unknown | 2024-11-22 | 2025-03-13 | 112 | 80 | Unknown | Unknown | Unknown | Unknown | 2024-12-13 | 2025-01-15 | 34 | 24 | 2025-03-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 64.05 | 64.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-10 | 2024-12-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1724.69 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-10 | 2024-12-13 | 4 | 4 | 2024-12-13 | 2024-12-13 | 1 | 1 | 2024-12-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | Applicant Design | Residential | N/A | SM 1128-H1 N. CITY PA3C MSO (E) | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-27 | 2024-08-27 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 136844 | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2024-08-27 | 2024-08-27 | 1 | 1 | 2024-08-27 | 2025-02-07 | 165 | 119 | Unknown | Unknown | Unknown | Unknown | 2025-07-03 | 2025-07-03 | 1 | 1 | 2025-02-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | BONSALL | N/A | 127.05 | 127.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-08 | 2023-11-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1015.94 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-08 | 2023-10-05 | Unknown | Unknown | 2023-10-05 | 2023-11-17 | 44 | 32 | 2023-11-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | 17.05 | 17.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-06 | 2025-02-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1268.27 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-06 | 2025-03-10 | 33 | 23 | 2025-03-10 | 2025-03-11 | 2 | 2 | 2025-02-12 | 2025-03-13 | 30 | 22 | Unknown | Unknown | Unknown | Unknown | 2025-03-13 | 2025-08-13 | 154 | 110 | Unknown | 2025-08-12 | Unknown | Unknown | 2025-08-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 222214 | 222214 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-03-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-15 | 2025-01-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 41596.6 | 15450.76 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-15 | 2025-01-16 | 2 | 2 | 2025-01-16 | 2025-01-28 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-28 | 2025-07-14 | 168 | 120 | Unknown | 2025-07-25 | Unknown | Unknown | 2025-07-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 108.05 | 108.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-13 | 2025-03-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1134.08 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-13 | 2025-03-12 | Unknown | Unknown | 2025-03-12 | 2025-03-13 | 2 | 2 | 2025-03-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-13 | 2023-03-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 812.55 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-13 | 2023-03-23 | 11 | 9 | 2023-03-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-28 | 2025-03-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2232.98 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-28 | 2025-03-07 | 8 | 6 | 2025-03-07 | 2025-03-10 | 4 | 2 | 2025-03-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-07 | 2025-08-20 | 167 | 119 | Unknown | Unknown | Unknown | Unknown | 2025-08-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 3.35 | 3.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-22 | 2024-03-29 | 2024-07-22 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 808.46 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-22 | 2024-01-12 | Unknown | Unknown | 2024-01-12 | 2024-03-29 | 78 | 56 | 2024-03-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-29 | 2024-07-22 | 116 | 82 | Unknown | Unknown | Unknown | Unknown | 2024-07-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-26 | 2024-03-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 534.53 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-26 | 2024-03-04 | 8 | 6 | 2024-03-04 | 2024-03-04 | 1 | 1 | 2024-03-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-18 | 2024-11-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 9150 | 380.91 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-18 | 2024-10-16 | Unknown | Unknown | 2024-10-16 | 2024-11-18 | 34 | 24 | 2024-11-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN CLEMENTE | N/A | 34.05 | 34.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-06 | 2024-09-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1266.45 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-06 | 2024-09-06 | 1 | 1 | 2024-09-06 | 2024-09-06 | 1 | 1 | 2024-09-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | Underserved Community | San Diego | San Diego | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-19 | 2024-12-19 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 43085 | 17878.39 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-19 | 2025-03-28 | 100 | 72 | 2025-03-28 | 2025-06-19 | 84 | 60 | 2025-05-07 | 2025-07-11 | 28 | 20 | 2025-04-12 | 2025-06-30 | 26 | 18 | 2025-08-12 | Unknown | Unknown | Unknown | 2025-08-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 115 | 115 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-26 | 2025-03-31 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1726.34 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-26 | 2025-03-28 | 3 | 3 | 2025-03-28 | 2025-03-31 | 4 | 2 | 2025-03-31 | 2025-03-31 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2025-03-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-20 | 2024-03-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3961 | 1493.93 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-20 | 2024-05-15 | 57 | 41 | 2024-05-15 | 2024-06-10 | 27 | 19 | 2024-06-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-18 | 2025-05-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1092.28 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-18 | 2025-05-17 | 30 | 21 | 2025-05-17 | 2025-05-19 | 3 | 1 | 2025-05-19 | Unknown | Unknown | Unknown | 2025-05-22 | 2025-06-30 | 40 | 28 | 2025-05-19 | 2025-07-29 | 72 | 52 | Unknown | Unknown | Unknown | Unknown | 2025-07-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SANTEE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-18 | 2025-06-18 | 2025-06-24 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 6386.23 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-18 | 2025-06-18 | 1 | 1 | 2025-06-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-18 | 2025-06-24 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2025-06-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | Applicant Design | Residential | Underserved Community | LA MESA | LA MESA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-12-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2021-08-26 | 2021-08-26 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 175043 | 39417 | Unknown | Unknown | Yes | N/A | N/A | 2021-08-26 | 2023-12-12 | 839 | 599 | 2023-12-12 | 2024-03-11 | 91 | 65 | 2024-01-02 | 2024-01-26 | 12 | 10 | 2024-01-10 | 2024-03-14 | 53 | 39 | Unknown | Unknown | Unknown | Unknown | 2025-07-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-20 | 2024-11-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1144.18 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-20 | 2024-12-14 | 25 | 18 | 2024-12-14 | 2025-01-17 | 35 | 25 | 2025-01-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN JUAN CAPISTRANO | N/A | 49.4 | 49.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-24 | 2024-10-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2603.17 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-24 | 2024-11-18 | 26 | 18 | 2024-11-18 | 2024-11-20 | 3 | 3 | 2024-11-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 69 | 69 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-20 | 2024-06-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1379.08 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-20 | 2024-05-07 | Unknown | Unknown | 2024-05-07 | 2024-06-20 | 45 | 33 | 2024-06-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | RAMONA | N/A | 105.05 | 105.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-13 | 2024-11-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2099.14 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-13 | 2024-11-13 | 1 | 1 | 2024-11-13 | 2024-12-20 | 38 | 28 | 2024-12-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-20 | 2025-08-18 | 242 | 172 | Unknown | 2025-08-22 | Unknown | Unknown | 2025-08-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN MARCOS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-11 | 2024-03-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1363.88 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-11 | 2024-03-29 | 19 | 15 | 2024-03-29 | 2024-04-11 | 14 | 10 | 2024-04-11 | 2024-08-01 | 113 | 81 | 2024-09-10 | 2024-09-10 | 1 | 1 | 2024-04-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-10 | 2025-04-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 864 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-10 | 2025-04-08 | Unknown | Unknown | 2025-04-08 | 2025-05-06 | 29 | 21 | 2025-05-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-21 | 2024-05-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7962 | 649.24 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-21 | 2024-05-02 | 256 | 184 | 2024-05-02 | 2024-05-03 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 19.1 | 19.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-21 | 2023-09-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 794.22 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-21 | 2023-09-27 | 7 | 5 | 2023-09-27 | 2023-09-27 | 1 | 1 | 2023-09-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | OCEANSIDE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-15 | 2024-05-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1444.49 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-15 | 2024-05-21 | 7 | 5 | 2024-05-21 | 2024-05-21 | 1 | 1 | 2024-05-21 | Unknown | Unknown | Unknown | 2024-05-21 | 2024-05-23 | 3 | 3 | 2024-05-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | 37 | 37 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-08 | 2024-01-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 21094.98 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-08 | 2024-01-08 | 1 | 1 | 2024-01-08 | 2024-08-07 | 213 | 153 | Unknown | Unknown | Unknown | Unknown | 2024-07-26 | 2024-08-14 | 16 | 12 | 2024-08-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-01 | 2024-11-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 4511.8 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-01 | 2024-11-04 | 4 | 2 | 2024-11-04 | 2025-01-10 | 68 | 50 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-09 | Unknown | Unknown | No | 2025-01-22 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-22 | 2025-01-27 | Unknown | IOU Designed & Installed | N/A | Yes | 20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 729.49 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-22 | 2025-02-11 | 21 | 15 | 2025-02-11 | 2025-01-27 | Unknown | Unknown | 2025-01-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-01 | 2023-12-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2780.09 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-01 | 2023-12-04 | 4 | 2 | 2023-12-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-02 | 2024-08-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1207.66 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-02 | 2024-10-25 | 85 | 61 | 2024-10-25 | 2024-10-25 | 1 | 1 | 2024-10-25 | 2024-10-25 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-10-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-23 | 2024-09-23 | 2024-12-17 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3569.27 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-23 | 2024-09-24 | 2 | 2 | 2024-09-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 356 | 356 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-19 | 2025-03-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1451.84 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-19 | 2025-03-10 | 20 | 14 | 2025-03-10 | 2025-03-10 | 1 | 1 | 2025-03-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | 50 | 50 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-12 | 2024-04-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1226.79 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-12 | 2024-02-21 | Unknown | Unknown | 2024-02-21 | 2024-04-19 | 59 | 43 | 2024-04-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-09 | 2023-09-27 | 2023-11-08 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 375.66 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-09 | 2023-09-27 | 19 | 13 | 2023-09-27 | 2023-09-27 | 1 | 1 | 2023-09-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-27 | 2023-11-08 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | 2023-11-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 148628 | 148628 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-01-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-22 | 2025-01-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 810.93 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-22 | 2025-01-14 | Unknown | Unknown | 2025-01-14 | 2025-04-18 | 95 | 69 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-18 | 2025-08-14 | 119 | 85 | Unknown | 2025-08-27 | Unknown | Unknown | 2025-09-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Commercial | Underserved Community | LA JOLLA | SAN DIEGO | 120 | 120 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-13 | 2024-02-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 5939.82 | 21670.95 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-13 | 2024-03-08 | 25 | 19 | 2024-03-08 | 2024-08-09 | 155 | 111 | 2024-05-14 | 2024-08-07 | 39 | 27 | 2024-03-29 | 2024-08-16 | 33 | 25 | 2024-10-01 | Unknown | Unknown | Unknown | 2024-10-01 | 2025-09-05 | 340 | 244 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 404.05 | 404.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-07-28 | Unknown | Unknown | No | 2023-09-14 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-14 | 2023-09-14 | Unknown | IOU Designed & Installed | N/A | Yes | 691 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1106.15 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-14 | 2025-07-30 | 686 | 490 | 2025-07-30 | 2025-08-05 | 7 | 5 | 2025-08-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | PINE VALLEY | N/A | 111.05 | 111.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-13 | 2023-03-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2841 | 480.06 | Unknown | Unknown | Yes | N/A | N/A | 2023-02-13 | 2023-03-07 | 23 | 17 | 2023-03-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | OH | Applicant Design | Residential | Underserved Community | San Diego | San Diego | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-19 | 2024-12-19 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 40949.53 | 35928.54 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-19 | 2025-04-01 | 104 | 74 | 2025-04-01 | 2025-07-23 | 114 | 82 | 2025-05-07 | 2025-05-07 | 1 | 1 | 2025-04-12 | 2025-06-30 | 43 | 29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | OCEANSIDE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-28 | 2023-03-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 941.76 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-28 | 2023-05-05 | 39 | 29 | 2023-05-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-03 | 2023-05-02 | 30 | 22 | 2023-05-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | IMPERIAL BEACH | IMPERIAL BEACH | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-31 | 2022-11-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 499.16 | Unknown | Unknown | Yes | N/A | N/A | 2022-10-31 | 2023-04-27 | 179 | 129 | 2023-04-27 | 2023-09-06 | 133 | 95 | Unknown | Unknown | Unknown | Unknown | 2023-05-01 | 2025-06-20 | 55 | 41 | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-08-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 42 | 42 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-06 | 2024-08-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1416.09 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-06 | 2024-08-06 | 1 | 1 | 2024-08-06 | 2024-08-06 | 1 | 1 | 2024-08-06 | Unknown | Unknown | Unknown | 2024-08-06 | 2024-09-05 | 31 | 23 | 2024-08-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 146.3 | 146.3 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-26 | 2024-06-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7962 | 6003.35 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-26 | 2024-06-17 | Unknown | Unknown | 2024-06-17 | 2024-06-27 | 11 | 9 | 2024-06-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | 38 | 38 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-11 | 2024-11-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1575.57 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-11 | 2024-10-29 | Unknown | Unknown | 2024-10-29 | 2024-11-13 | 16 | 12 | 2024-11-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN YSIDRO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-09-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-14 | 2024-10-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 9601 | 525.39 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-14 | 2024-09-09 | Unknown | Unknown | 2024-09-09 | 2024-10-14 | 36 | 26 | 2024-10-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-09 | 2023-12-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 813.73 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-09 | 2023-07-11 | Unknown | Unknown | 2023-07-11 | 2023-12-04 | 147 | 105 | 2023-12-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 183.45 | 183.45 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-08 | 2023-07-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1922.17 | Unknown | Unknown | Yes | N/A | N/A | 2022-12-08 | 2023-07-10 | 215 | 153 | 2023-07-10 | 2025-04-30 | 661 | 473 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-30 | 2025-04-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LEMON GROVE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-15 | 2023-03-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3885 | 536.01 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-15 | 2023-03-15 | 1 | 1 | 2023-03-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | LAGUNA NIGUEL | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-08 | 2024-07-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2761.65 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-08 | 2024-06-05 | Unknown | Unknown | 2024-06-05 | 2024-07-26 | 52 | 38 | 2024-07-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-26 | 2025-08-06 | 377 | 269 | Unknown | 2025-07-16 | Unknown | Unknown | 2025-08-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-15 | 2023-11-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 31848 | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2023-11-15 | 2023-10-04 | Unknown | Unknown | 2023-10-04 | 2024-10-23 | 386 | 276 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-28 | 2025-01-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1196.64 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-28 | 2025-02-12 | 16 | 12 | 2025-02-12 | 2025-02-12 | 1 | 1 | 2025-02-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-16 | 2025-01-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 1183841 | 16672.74 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-16 | 2024-02-20 | Unknown | Unknown | 2024-02-20 | 2025-03-10 | 385 | 275 | Unknown | Unknown | Unknown | Unknown | 2025-02-20 | 2025-03-07 | 16 | 12 | 2025-03-10 | 2025-06-16 | 99 | 71 | Unknown | 2025-06-26 | Unknown | Unknown | 2025-08-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-15 | 2025-05-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1114.01 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-15 | 2025-05-15 | 1 | 1 | 2025-05-15 | 2025-05-15 | 1 | 1 | 2025-05-15 | 2025-07-07 | 5 | 3 | 2025-05-19 | 2025-07-11 | 51 | 39 | 2025-05-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 1425.1 | 1425.1 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2024-03-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-11 | 2023-04-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 182.98 | Unknown | Unknown | Yes | N/A | N/A | 2023-04-11 | 2023-04-10 | Unknown | Unknown | 2023-04-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Residential | Underserved Community | ES 1130-D3 (E) | COUNTY OF SAN DIEGO-NORTH of 56 | 2057 | 2057 | Not Available | >2MW | No | N/A | N/A | N/A | 2025-08-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-08 | 2024-02-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 9747 | 43822.02 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-08 | 2024-01-31 | Unknown | Unknown | 2024-01-31 | 2025-03-19 | 414 | 296 | 2024-05-15 | 2025-03-17 | 34 | 24 | 2024-02-26 | 2025-08-06 | -178 | -138 | 2025-03-28 | Unknown | Unknown | Unknown | 2025-03-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | JACUMBA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-23 | 2025-04-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1027.74 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-23 | 2025-04-23 | 1 | 1 | 2025-04-23 | 2025-04-23 | 1 | 1 | 2025-04-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 139.05 | 139.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-06 | 2022-12-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 995.25 | Unknown | Unknown | Yes | N/A | N/A | 2022-12-06 | 2023-04-21 | 137 | 99 | 2023-04-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-25 | 2024-07-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1367.4 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-25 | 2024-07-25 | 1 | 1 | 2024-07-25 | 2024-07-25 | 1 | 1 | 2024-07-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R29/R45 | UG | IOU Design | Commercial | Underserved Community | VISTA | VISTA | 224 | 224 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-06 | 2024-08-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 114101.66 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-06 | 2025-01-27 | 236 | 168 | 2025-01-27 | 2025-05-27 | 121 | 87 | 2025-02-18 | 2025-05-01 | 4 | 4 | 2025-05-02 | 2025-05-30 | 14 | 10 | 2025-05-27 | Unknown | Unknown | Unknown | 2025-07-15 | 2025-07-22 | 8 | 6 | 2025-07-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2022-02-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-23 | 2025-01-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3753.77 | 2645.68 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-23 | 2025-04-15 | 83 | 59 | 2025-04-15 | 2025-05-02 | 18 | 14 | Unknown | Unknown | Unknown | Unknown | 2025-03-31 | 2025-04-10 | 11 | 9 | 2025-05-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | IOU Design | Residential | Underserved Community | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-01 | 2024-10-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 75321.76 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-01 | 2024-07-24 | 115 | 83 | 2024-07-24 | 2025-07-08 | 350 | 250 | 2024-12-05 | 2025-06-05 | 79 | 57 | 2025-07-24 | 2025-08-14 | 22 | 16 | 2025-07-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-23 | 2024-07-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2907.23 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-23 | 2024-07-23 | 1 | 1 | 2024-07-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | VS 1087-H7 (E) | VISTA | 130.05 | 130.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-05 | 2024-02-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 14457 | 8659.62 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-05 | 2023-12-13 | Unknown | Unknown | 2023-12-13 | Unknown | Unknown | Unknown | 2024-01-11 | 2025-08-21 | -145 | -107 | 2024-03-06 | 2025-07-24 | 252 | 184 | Unknown | Unknown | Unknown | Unknown | 2024-04-24 | 2025-08-20 | 484 | 346 | 2025-09-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 11 | 11 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-05 | 2025-06-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 817.04 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-05 | 2025-06-11 | 7 | 5 | 2025-06-11 | 2025-06-12 | 2 | 2 | 2025-06-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SOUTH LAGUNA | DANA POINT | 1 | 1 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-07 | 2023-08-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 15340.17 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-07 | 2023-08-09 | 156 | 112 | 2023-08-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-08 | 2024-01-02 | 33 | 23 | 2023-12-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-09 | 2024-08-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1390.22 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-09 | 2024-08-28 | 20 | 14 | 2024-08-28 | 2025-05-23 | 269 | 193 | 2025-05-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-22 | 2024-11-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1682 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-22 | 2024-10-30 | Unknown | Unknown | 2024-10-30 | 2024-11-22 | 24 | 18 | 2024-11-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-22 | 2025-07-23 | 244 | 174 | Unknown | Unknown | Unknown | Unknown | 2025-07-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-11 | 2024-07-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 150291 | 4215.66 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-11 | 2024-07-11 | 1 | 1 | 2024-07-11 | 2024-07-24 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | 2024-07-23 | 2024-08-23 | 32 | 24 | 2024-07-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-24 | 2025-06-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1101.16 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-24 | 2025-06-24 | 1 | 1 | 2025-06-24 | 2025-06-24 | 1 | 1 | 2025-06-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-24 | 2025-07-16 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | 2025-07-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | FALLBROOK | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-13 | 2024-06-17 | 2024-07-30 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1486.09 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-13 | 2024-06-12 | Unknown | Unknown | 2024-06-12 | 2024-06-17 | 6 | 4 | 2024-06-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-17 | 2024-07-30 | 44 | 32 | Unknown | Unknown | Unknown | Unknown | 2024-07-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 29.4 | 29.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-03 | 2024-06-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1117.14 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-03 | 2024-05-16 | Unknown | Unknown | 2024-05-16 | 2024-06-06 | 22 | 16 | 2024-06-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-06 | 2025-07-09 | 399 | 285 | Unknown | 2025-07-08 | Unknown | Unknown | 2025-07-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 149.05 | 149.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-25 | 2025-03-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1039.42 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-25 | 2025-03-27 | 3 | 3 | 2025-03-27 | 2025-03-27 | 1 | 1 | 2025-03-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-10 | 2024-10-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1713.69 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-10 | 2024-10-14 | 35 | 25 | 2024-10-14 | 2024-10-21 | 8 | 6 | 2024-10-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-06 | 2025-06-06 | 2025-06-30 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1599.96 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-06 | 2025-06-05 | Unknown | Unknown | 2025-06-05 | 2025-08-20 | 77 | 55 | 2025-08-20 | Unknown | Unknown | Unknown | 2025-06-06 | 2025-06-24 | 19 | 13 | 2025-06-06 | 2025-06-30 | 25 | 17 | Unknown | Unknown | Unknown | Unknown | 2025-06-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-26 |  | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1654.49 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-26 | 2024-07-26 | 1 | 1 | 2024-07-26 | 2024-07-26 | 1 | 1 | 2024-07-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-21 | 2023-02-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 648.31 | Unknown | Unknown | Yes | N/A | N/A | 2023-02-21 | 2023-02-27 | 7 | 5 | 2023-02-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | POWAY | COUNTY OF SAN DIEGO-NORTH of 56, POWAY | 1372 | 1372 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2026-03-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-28 | 2025-03-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1442.41 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-28 | 2025-06-17 | 82 | 58 | 2025-06-17 | 2025-06-17 | 1 | 1 | 2025-06-17 | Unknown | Unknown | Unknown | 2025-06-23 | 2025-07-29 | 37 | 27 | 2025-06-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | WARNER SPRINGS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-20 | 2023-10-20 | 2023-10-30 | IOU Designed & Installed | N/A | No | Unknown | 3434.49 | 979.6 | Unknown | 471.68 | 139.17 | 1844.04 | 3981 | 904.67 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-20 | 2023-10-20 | 1 | 1 | 2023-10-20 | 2023-10-20 | 1 | 1 | 2023-10-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-20 | 2023-10-30 | 11 | 7 | Unknown | Unknown | Unknown | Unknown | 2023-10-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | EL CAJON, SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-23 | 2024-02-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 309.71 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-23 | 2024-02-29 | 7 | 5 | 2024-02-29 | 2024-04-19 | 51 | 37 | Unknown | Unknown | Unknown | Unknown | 2024-02-26 | 2024-03-27 | 31 | 21 | 2024-04-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | N/A | 20.5 | 20.5 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-06 | 2024-12-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1022.54 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-06 | 2024-12-06 | 1 | 1 | 2024-12-06 | 2024-12-06 | 1 | 1 | 2024-12-06 | 2024-12-18 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2024-12-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 335.05 | 335.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-14 | 2025-01-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3941 | 1238.62 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-14 | 2025-03-12 | 58 | 42 | 2025-03-12 | 2025-03-24 | 13 | 9 | 2025-03-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-24 | 2023-01-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 111.31 | Unknown | Unknown | Yes | N/A | N/A | 2023-01-24 | 2023-03-13 | 49 | 35 | 2023-03-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | POWAY | N/A | 110 | 110 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-18 | 2024-06-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1383.66 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-18 | 2025-06-04 | 352 | 252 | 2025-06-04 | 2025-06-04 | 1 | 1 | 2025-06-04 | 2025-06-09 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2025-06-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-23 | 2024-09-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 9601 | 525.39 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-23 | 2024-09-23 | 1 | 1 | 2024-09-23 | 2024-09-23 | 1 | 1 | 2024-09-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Commercial | Underserved Community | San Diego | SAN DIEGO | 1924 | 1924 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2025-09-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-03 | 2024-05-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 9309.98 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-03 | 2024-04-05 | 3 | 3 | 2024-04-05 | 2025-07-31 | 483 | 345 | Unknown | Unknown | Unknown | Unknown | 2024-08-15 | 2024-12-11 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 31.35 | 31.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-29 | Unknown | Unknown | No | 2025-02-06 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-06 | 2025-02-06 | Unknown | IOU Designed & Installed | N/A | Yes | 26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1273 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-06 | 2025-03-05 | 28 | 20 | 2025-03-05 | 2025-03-10 | 6 | 4 | 2025-02-11 | 2025-03-10 | 25 | 19 | Unknown | Unknown | Unknown | Unknown | 2025-03-10 | 2025-08-12 | 156 | 112 | Unknown | 2025-08-11 | Unknown | Unknown | 2025-08-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-16 | 2024-10-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1166.16 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-16 | 2024-11-01 | 17 | 13 | 2024-11-01 | 2024-11-05 | 5 | 3 | 2024-11-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-05 | 2025-07-24 | 262 | 188 | Unknown | 2025-07-07 | Unknown | Unknown | 2025-07-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN MARCOS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-11 | 2024-03-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 845.71 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-11 | 2024-01-29 | Unknown | Unknown | 2024-01-29 | 2024-03-19 | 51 | 37 | 2024-03-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-27 | 2024-04-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1024.22 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-27 | 2024-02-26 | Unknown | Unknown | 2024-02-26 | 2024-04-17 | 52 | 38 | 2024-04-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 30 | 30 | Not Available | <1MW | No | N/A | N/A | N/A | 2021-11-11 | Unknown | Unknown | No | 2022-12-08 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-08 | 2023-01-18 | 2023-01-19 | IOU Designed & Installed | N/A | Yes | 480 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1762.81 | Unknown | Unknown | Yes | N/A | N/A | 2022-12-08 | 2024-04-01 | 481 | 343 | 2024-04-01 | 2025-08-12 | 499 | 357 | 2025-08-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-01-30 | 2023-01-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-01-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 131.05 | 131.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-10 | 2025-05-09 | 2025-05-14 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1283.42 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-10 | 2025-05-09 | 30 | 22 | 2025-05-09 | 2025-05-09 | 1 | 1 | 2025-05-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-09 | 2025-05-14 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2025-05-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 3248.7 | 3248.7 | Not Available | >2MW | No | N/A | N/A | N/A | 2025-07-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-27 | 2025-06-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 791.92 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-27 | 2025-06-27 | 1 | 1 | 2025-06-27 | 2025-06-27 | 1 | 1 | 2025-06-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-31 | 2025-04-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1756.4 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-31 | 2025-04-09 | 10 | 8 | 2025-04-09 | 2025-04-09 | 1 | 1 | 2025-04-08 | 2025-04-09 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2025-04-09 | 2025-08-15 | 129 | 93 | Unknown | Unknown | Unknown | Unknown | 2025-08-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-02 | 2025-06-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1151.7 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-02 | 2025-06-09 | 8 | 6 | 2025-06-09 | 2025-06-11 | 3 | 3 | 2025-06-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-27 | 2023-11-27 | 2024-01-09 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 158.79 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-27 | 2023-07-26 | Unknown | Unknown | 2023-07-26 | 2023-12-20 | 148 | 106 | 2023-12-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-20 | 2024-01-09 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | 2024-01-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 58 | 58 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-06 | 2024-07-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1088.03 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-06 | 2024-05-01 | Unknown | Unknown | 2024-05-01 | 2024-07-09 | 70 | 50 | 2024-07-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-09 | Unknown | Unknown | Unknown | Unknown | 2024-08-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-01 | 2025-04-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3571.59 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-01 | 2025-04-10 | 10 | 8 | 2025-04-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-18 | 2023-11-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1036.61 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-18 | 2023-07-27 | Unknown | Unknown | 2023-07-27 | 2023-11-22 | 119 | 85 | 2023-11-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | Underserved Community | San Marcos | SAN MARCOS | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-07 | 2022-12-07 | 2025-04-14 | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 7751.39 | Unknown | Unknown | Yes | N/A | N/A | 2022-12-07 | 2023-07-19 | 225 | 161 | 2023-07-19 | 2024-02-23 | 220 | 158 | 2023-08-07 | 2024-12-09 | 92 | 66 | 2023-08-09 | 2024-12-20 | 73 | 55 | 2024-07-11 | Unknown | Unknown | Unknown | 2024-07-11 | 2025-02-24 | 229 | 163 | 2025-04-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 1045 | 1045 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2025-05-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-17 | 2024-07-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 374804 | 16325.28 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-17 | 2024-04-29 | Unknown | Unknown | 2024-04-29 | 2024-10-17 | 172 | 124 | Unknown | Unknown | Unknown | Unknown | 2025-05-02 | 2025-05-20 | 19 | 13 | 2024-10-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 93.05 | 93.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-18 | 2025-02-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1225.94 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-18 | 2025-03-05 | 16 | 12 | 2025-03-05 | 2025-03-05 | 1 | 1 | 2025-03-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 75.05 | 75.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-19 | 2023-10-31 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 513.31 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-19 | 2023-10-31 | 13 | 9 | 2023-10-31 | 2023-10-31 | 1 | 1 | 2023-10-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | 1109.7 | 1109.7 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2023-11-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-20 | 2023-12-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 11943 | 727.4 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-20 | 2024-04-10 | 174 | 124 | 2024-04-10 | 2024-04-12 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-12 | 2025-03-12 | 335 | 239 | Unknown | 2025-07-04 | Unknown | Unknown | 2025-08-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 103.05 | 103.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-08 | 2024-03-13 | 2024-08-02 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1991.64 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-08 | 2023-12-28 | Unknown | Unknown | 2023-12-28 | 2024-03-13 | 77 | 55 | 2024-03-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-13 | 2024-08-02 | 143 | 103 | Unknown | Unknown | Unknown | Unknown | 2024-08-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | JAMUL | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-06 | 2024-03-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 685.71 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-06 | 2024-02-01 | Unknown | Unknown | 2024-02-01 | 2024-03-06 | 35 | 25 | 2024-03-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-06 | 2025-07-24 | 506 | 362 | Unknown | Unknown | Unknown | Unknown | 2025-07-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 14.7 | 14.7 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-09 | 2024-12-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1297.75 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-09 | 2025-02-24 | 78 | 56 | 2025-02-24 | 2025-03-07 | 12 | 10 | 2025-03-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2020-02-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-03 | 2023-07-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1110.53 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-03 | 2023-05-31 | Unknown | Unknown | 2023-05-31 | 2023-07-07 | 38 | 28 | 2023-07-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-09 | 2023-03-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3885 | 517.7 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-09 | 2023-03-09 | 1 | 1 | 2023-03-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 1302.2 | 1302.2 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2024-06-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-24 | 2024-01-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 15924 | 1830.29 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-24 | 2024-01-30 | 7 | 5 | 2024-01-30 | 2025-01-29 | 366 | 262 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-29 | 2025-02-14 | 17 | 13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 94.7 | 94.7 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-09 | 2024-08-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1730.42 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-09 | 2024-06-24 | Unknown | Unknown | 2024-06-24 | 2024-08-12 | 50 | 36 | 2024-08-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-25 | 2023-07-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 46962 | 555.18 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-25 | 2023-07-25 | 1 | 1 | 2023-07-25 | 2023-07-25 | 1 | 1 | 2023-07-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-23 | 2024-10-31 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3985 | 2927.01 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-23 | 2024-11-01 | 376 | 270 | 2024-11-01 | 2024-12-13 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | 2024-11-18 | 2024-12-27 | 40 | 30 | 2024-12-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-12 | 2024-02-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1164.74 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-12 | 2024-02-08 | Unknown | Unknown | 2024-02-08 | 2024-02-08 | 1 | 1 | 2024-02-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-03 | 2023-01-03 | 2023-08-01 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 154.79 | Unknown | Unknown | Yes | N/A | N/A | 2023-01-03 | 2023-04-21 | 109 | 79 | 2023-04-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-21 | 2023-08-01 | 103 | 73 | Unknown | Unknown | Unknown | Unknown | 2023-08-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-18 | 2024-11-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1488.2 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-18 | 2024-11-14 | 150 | 108 | 2024-11-14 | 2025-01-03 | 51 | 37 | 2025-01-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-19 | 2025-03-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1906.34 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-19 | 2025-03-19 | 1 | 1 | 2025-03-19 | 2025-03-19 | 1 | 1 | 2025-03-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-09 | 2023-03-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 98.41 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-09 | 2023-03-08 | Unknown | Unknown | 2023-03-08 | 2023-03-20 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2023-05-02 | 2023-05-02 | 1 | 1 | 2023-03-20 | Unknown | Unknown | Unknown | Unknown | 2023-05-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Commercial | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-02 | 2024-09-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 365368.54 | 5855.63 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-02 | 2024-01-24 | Unknown | Unknown | 2024-01-24 | 2025-01-02 | 345 | 247 | Unknown | Unknown | Unknown | Unknown | 2024-12-26 | 2025-01-02 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-08-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | 140.05 | 140.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-29 | 2024-05-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2280.01 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-29 | 2024-02-21 | Unknown | Unknown | 2024-02-21 | 2024-10-24 | 247 | 177 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2022-11-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-21 | 2024-03-21 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 26008.15 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-21 | 2024-04-25 | 36 | 26 | 2024-04-25 | 2024-07-01 | 68 | 48 | 2024-05-01 | 2024-11-19 | 107 | 77 | 2024-05-03 | 2024-11-27 | 78 | 55 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | Santee | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-29 | 2024-07-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 4360.34 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-29 | 2024-07-26 | Unknown | Unknown | 2024-07-26 | 2024-08-06 | 12 | 8 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CORONADO | CORONADO | 18.1 | 18.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | 2025-04-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 496.67 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-07 | 2025-04-11 | 5 | 5 | 2025-04-11 | 2025-04-24 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | 2025-04-13 | 2025-07-29 | 53 | 38 | 2025-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 156 | 156 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-12 | 2024-09-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 999.88 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-12 | 2024-08-06 | Unknown | Unknown | 2024-08-06 | 2024-09-24 | 50 | 36 | 2024-09-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-24 | 2025-07-23 | 303 | 217 | Unknown | Unknown | Unknown | Unknown | 2025-07-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 1.35 | 1.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-06 | 2025-03-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2129.35 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-06 | 2025-03-07 | 2 | 2 | 2025-03-07 | 2025-03-07 | 1 | 1 | 2025-03-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | BONITA | COUNTY OF SAN DIEGO-SOUTH of 56 | 205.05 | 205.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-20 | 2024-08-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1724.54 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-20 | 2024-09-05 | 17 | 13 | 2024-09-05 | 2025-03-03 | 180 | 128 | 2025-03-03 | Unknown | Unknown | Unknown | 2024-08-20 | 2024-08-27 | 8 | 6 | 2024-08-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 837 | 837 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-26 | 2023-08-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1141.57 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-26 | 2023-07-06 | Unknown | Unknown | 2023-07-06 | 2023-10-06 | 93 | 67 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | ENCINITAS | ENCINITAS | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-04 | 2024-12-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1809.9 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-04 | 2024-12-11 | 38 | 28 | 2024-12-11 | 2024-12-26 | 16 | 12 | 2024-12-26 | 2025-06-17 | 8 | 6 | 2025-04-30 | 2025-07-15 | 71 | 51 | 2024-12-26 | 2025-07-28 | 215 | 153 | Unknown | Unknown | Unknown | Unknown | 2025-07-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-18 | 2024-07-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1661.09 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-18 | 2024-03-13 | Unknown | Unknown | 2024-03-13 | 2024-07-18 | 128 | 92 | 2024-07-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-27 | 2025-02-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1215.3 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-27 | 2025-02-06 | Unknown | Unknown | 2025-02-06 | 2025-03-05 | 28 | 20 | 2025-03-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-05 | 2025-09-02 | 182 | 130 | Unknown | 2025-08-28 | Unknown | Unknown | 2025-09-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2026-03-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-06 | 2024-03-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 54899 | 84.08 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-06 | 2024-10-28 | 237 | 169 | 2024-10-28 | 2024-11-12 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | 2024-03-20 | 2024-09-20 | 60 | 44 | 2024-11-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2025-08-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-22 | 2025-04-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1224.04 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-22 | 2025-04-22 | 1 | 1 | 2025-04-22 | 2025-06-26 | 66 | 48 | Unknown | Unknown | Unknown | Unknown | 2025-04-23 | 2025-05-07 | 15 | 11 | 2025-06-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-07-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2026-03-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-06 | 2024-03-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 54899 | 81.53 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-06 | 2024-08-16 | 164 | 118 | 2024-08-16 | 2024-08-29 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | 2024-03-20 | 2024-08-23 | 61 | 45 | 2024-08-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2021-01-29 | 2021-01-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7962 | 755.33 | Unknown | Unknown | Yes | N/A | N/A | 2021-01-29 | 2024-06-14 | 1233 | 881 | 2024-06-14 | 2024-06-17 | 4 | 2 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | LA JOLLA | 241.15 | 241.15 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-06 | 2025-02-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2064.44 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-06 | 2025-04-11 | 65 | 47 | 2025-04-11 | 2025-07-09 | 90 | 64 | Unknown | Unknown | Unknown | Unknown | 2025-04-11 | 2025-04-22 | 12 | 8 | 2025-07-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-07-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-06-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-24 | 2025-06-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1200.8 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-24 | 2025-06-24 | 1 | 1 | 2025-06-24 | 2025-06-24 | 1 | 1 | 2025-06-24 | Unknown | Unknown | Unknown | 2025-06-25 | 2025-07-10 | 16 | 12 | 2025-06-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | ESCONDIDO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-18 | 2024-08-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1102.91 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-18 | 2024-08-12 | 26 | 18 | 2024-08-12 | 2024-08-20 | 9 | 7 | 2024-08-20 | 2024-09-13 | 25 | 19 | 2024-07-23 | 2024-08-27 | 36 | 26 | 2024-09-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | 81.05 | 81.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-26 | 2024-06-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1222.34 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-26 | 2024-07-17 | 22 | 16 | 2024-07-17 | 2024-07-26 | 10 | 8 | 2024-07-26 | Unknown | Unknown | Unknown | 2024-10-09 | 2024-10-09 | 1 | 1 | 2024-07-26 | Unknown | Unknown | Unknown | Unknown | 2025-09-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-03 | 2024-12-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3684.13 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-03 | 2024-12-03 | 1 | 1 | 2024-12-03 | 2025-08-07 | 248 | 178 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-08-07 | Unknown | Unknown | Unknown | Unknown | 2025-09-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-06 | 2023-10-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 825.08 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-06 | 2023-08-28 | Unknown | Unknown | 2023-08-28 | 2023-10-06 | 40 | 30 | 2023-10-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-14 | 2024-05-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 208536.63 | 17195.93 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-14 | 2024-05-15 | 2 | 2 | 2024-05-15 | 2025-06-19 | 401 | 287 | Unknown | Unknown | Unknown | Unknown | 2024-07-11 | 2024-08-13 | 34 | 24 | 2025-06-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CORONADO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-01-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-04 | 2025-03-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 841.88 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-04 | 2025-02-04 | 1 | 1 | 2025-02-04 | 2025-04-29 | 85 | 61 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-29 | 2025-07-01 | 64 | 46 | Unknown | 2025-06-19 | Unknown | Unknown | 2025-07-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 39 | 39 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-19 | Unknown | Unknown | No | 2023-09-19 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-19 | 2023-09-19 | Unknown | IOU Designed & Installed | N/A | Yes | 549 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1697.18 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-19 | 2025-03-21 | 550 | 394 | 2025-03-21 | 2025-03-21 | 1 | 1 | 2025-03-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | OH | IOU Design | Commercial | Underserved Community | Dana Point | N/A | 640 | 640 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-27 | 2023-09-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 1203115.28 | 11179.95 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-27 | 2023-07-28 | 2 | 2 | 2023-07-28 | Unknown | Unknown | Unknown | 2023-07-28 | Unknown | Unknown | Unknown | 2024-02-23 | 2025-02-14 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2022-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-09 | 2023-08-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 1938639 | 1511.59 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-09 | 2023-08-10 | 2 | 2 | 2023-08-10 | 2023-09-01 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-01 | 2023-09-08 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 23 | 23 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-01 | 2023-11-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 11943 | 1300.73 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-01 | 2023-11-02 | 2 | 2 | 2023-11-02 | 2024-01-24 | 84 | 60 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | Applicant Design | Residential | N/A | SM 1128-H1 N. CITY PA3B MSO (E) | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-27 | 2024-08-30 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 159889 | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2024-08-27 | 2024-08-23 | Unknown | Unknown | 2024-08-23 | 2025-02-07 | 169 | 121 | Unknown | Unknown | Unknown | Unknown | 2025-07-03 | 2025-07-03 | 1 | 1 | 2025-02-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-02 | 2025-05-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1283.33 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-02 | 2025-05-07 | 6 | 4 | 2025-05-07 | 2025-05-28 | 22 | 16 | 2025-05-06 | 2025-05-28 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | 2025-05-28 | 2025-08-26 | 91 | 65 | Unknown | Unknown | Unknown | Unknown | 2025-08-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-01 | 2025-05-01 | 2025-06-24 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 607.62 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-01 | 2025-04-15 | Unknown | Unknown | 2025-04-15 | 2025-05-27 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | 2025-05-02 | 2025-05-16 | 15 | 11 | 2025-05-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-31 | 2023-01-31 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 474.55 | Unknown | Unknown | Yes | N/A | N/A | 2023-01-31 | 2023-01-31 | 1 | 1 | 2023-01-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-01-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-18 | 2025-02-18 | 2025-03-26 | IOU Designed & Installed | N/A | No | Unknown | 3745.34 | 190.75 | Unknown | Unknown | 19.27 | 3535.32 | 3981 | 1022.71 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-18 | 2025-02-12 | Unknown | Unknown | 2025-02-12 | 2025-02-18 | 7 | 5 | 2025-02-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-18 | 2025-03-26 | 37 | 27 | Unknown | Unknown | Unknown | Unknown | 2025-03-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | N/A | 81.15 | 81.15 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-24 | 2024-05-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1001.91 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-24 | 2024-06-12 | 50 | 36 | 2024-06-12 | 2024-06-18 | 7 | 5 | 2024-06-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | LEMON GROVE | LEMON GROVE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-19 | 2023-05-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 37981 | 1228.34 | Unknown | Unknown | Yes | N/A | N/A | 2023-05-19 | 2023-05-23 | 5 | 3 | 2023-05-23 | 2023-05-31 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | 2024-02-07 | 2024-02-29 | 23 | 17 | 2023-05-31 | Unknown | Unknown | Unknown | Unknown | 2024-01-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-22 | 2023-08-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 496.37 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-22 | 2023-08-22 | 1 | 1 | 2023-08-22 | 2023-08-22 | 1 | 1 | 2023-08-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 184 | 184 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-09 | 2023-02-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 925.55 | Unknown | Unknown | Yes | N/A | N/A | 2023-02-09 | 2023-02-09 | 1 | 1 | 2023-02-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-08-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-08 | 2025-01-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 6556 | 1019.67 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-08 | 2025-01-08 | 1 | 1 | 2025-01-08 | 2025-01-13 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2025-01-08 | 2025-01-28 | 21 | 15 | 2025-01-13 | Unknown | Unknown | Unknown | Unknown | 2025-06-20 | Unknown | Unknown | 2025-07-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | CHULA VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-21 | 2025-03-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 8819.3 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-21 | 2024-12-09 | Unknown | Unknown | 2024-12-09 | 2025-06-13 | 187 | 135 | Unknown | Unknown | Unknown | Unknown | 2025-05-07 | 2025-07-18 | 50 | 36 | 2025-06-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-09-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-26 | 2023-05-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 547.87 | Unknown | Unknown | Yes | N/A | N/A | 2023-05-26 | 2023-05-26 | 1 | 1 | 2023-05-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-27 | 2024-09-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 5263.82 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-27 | 2024-10-01 | 5 | 3 | 2024-10-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-03 | 2024-06-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 635.89 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-03 | 2024-10-17 | 137 | 99 | 2024-10-17 | 2024-11-15 | 30 | 22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | RANCHO MISSION VIEJO | N/A | 106.1 | 106.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-06-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-14 | 2025-03-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1289.58 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-14 | 2025-03-04 | Unknown | Unknown | 2025-03-04 | 2025-04-07 | 35 | 25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-07 | 2025-05-16 | 40 | 30 | Unknown | 2025-06-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2019-03-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | 2025-04-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1012.85 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-07 | 2025-04-08 | 2 | 2 | 2025-04-08 | 2025-05-23 | 46 | 34 | Unknown | Unknown | Unknown | Unknown | 2025-04-09 | 2025-04-22 | 14 | 10 | 2025-05-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-24 | 2025-02-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1325.98 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-24 | 2025-04-17 | 53 | 39 | 2025-04-17 | 2025-04-29 | 13 | 9 | 2025-04-29 | 2025-05-01 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2025-05-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | ES 1089-E6 | N/A | 246.2 | 246.2 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-12 | 2024-04-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 21760.15 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-12 | 2023-12-01 | Unknown | Unknown | 2023-12-01 | 2024-09-10 | 285 | 203 | 2024-03-14 | 2024-03-28 | 15 | 11 | 2024-09-11 | 2024-09-12 | 2 | 2 | 2024-09-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 4277666 | 4277666 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-01-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-04 | 2023-09-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 189390.55 | 20413.91 | Unknown | Unknown | Yes | N/A | N/A | 2022-10-04 | 2023-07-11 | 281 | 201 | 2023-07-11 | 2024-03-13 | 247 | 177 | 2022-06-27 | 2024-03-07 | 9 | 7 | 2023-12-05 | 2024-05-14 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | 2024-07-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-26 | Unknown | Unknown | No | 2025-04-07 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | 2025-04-08 | 2025-04-11 | IOU Designed & Installed | N/A | Yes | 59 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1327.25 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-07 | 2025-06-05 | 60 | 44 | 2025-06-05 | 2025-04-07 | Unknown | Unknown | 2025-04-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-08 | 2025-04-11 | 4 | 4 | Unknown | Unknown | Unknown | Unknown | 2025-04-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2020-02-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-11 | 2023-08-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1110.36 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-11 | 2023-07-07 | Unknown | Unknown | 2023-07-07 | 2023-08-11 | 36 | 26 | 2023-08-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | ENCINITAS | ENCINITAS | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-06 | 2023-12-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1405.6 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-06 | 2024-02-29 | 86 | 62 | 2024-02-29 | 2024-03-01 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2023-12-30 | 2024-02-23 | 56 | 40 | 2024-03-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 59.05 | 59.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-24 | 2025-03-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1847.45 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-24 | 2025-03-07 | 12 | 10 | 2025-03-07 | 2025-03-07 | 1 | 1 | 2025-03-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | Both | IOU Design | Residential | Underserved Community | OCEANSIDE | OCEANSIDE | 87 | 87 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-30 | 2024-01-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 11943 | 35201.21 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-30 | 2023-12-22 | 54 | 40 | 2023-12-22 | 2025-04-10 | 476 | 340 | 2024-04-10 | 2025-04-09 | 174 | 126 | 2024-01-23 | 2025-07-10 | 118 | 84 | 2025-04-10 | Unknown | Unknown | Unknown | 2025-06-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-04 | 2024-12-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1556.01 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-04 | 2024-12-05 | 2 | 2 | 2024-12-05 | 2024-12-06 | 2 | 2 | 2024-12-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 1 | 1 | Not Available | <1MW | No | N/A | N/A | N/A | 2021-03-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-19 | 2023-10-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1273.2 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-19 | 2023-09-20 | Unknown | Unknown | 2023-09-20 | 2023-10-23 | 34 | 24 | 2023-10-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 60 | 60 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-13 | 2025-04-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1305.26 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-13 | 2025-06-09 | 58 | 41 | 2025-06-09 | 2025-07-18 | 40 | 30 | 2025-07-18 | 2025-06-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-12 | 2024-04-12 | 2024-04-19 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 838.69 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-12 | 2024-01-03 | Unknown | Unknown | 2024-01-03 | 2024-04-12 | 101 | 73 | 2024-04-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-12 | 2024-04-19 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2024-04-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN MARCOS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-25 | 2023-05-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 112126 | 38507.92 | Unknown | Unknown | Yes | N/A | N/A | 2023-04-25 | 2023-04-25 | 1 | 1 | 2023-04-25 | 2023-05-15 | 21 | 15 | 2023-04-28 | 2023-05-12 | 9 | 7 | 2023-05-15 | 2023-05-19 | 5 | 5 | 2023-05-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | DANA POINT | N/A | 5.4 | 5.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-13 | 2024-12-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2639.61 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-13 | 2024-12-30 | 48 | 34 | 2024-12-30 | 2024-12-30 | 1 | 1 | 2024-12-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 20 | 20 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-16 | 2025-04-16 | 2025-05-14 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 196.38 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-16 | 2025-04-04 | Unknown | Unknown | 2025-04-04 | 2025-04-22 | 19 | 13 | 2025-04-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-22 | 2025-05-14 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | 2025-05-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 67.05 | 67.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-19 | 2024-09-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1329.27 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-19 | 2024-09-04 | Unknown | Unknown | 2024-09-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2026-03-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-06 | 2024-06-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 54899 | 81.53 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-06 | 2024-09-20 | 138 | 100 | 2024-09-20 | 2024-10-15 | 26 | 18 | Unknown | Unknown | Unknown | Unknown | 2024-05-20 | 2024-10-10 | 55 | 41 | 2024-10-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | POWAY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-21 | 2024-05-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1037.35 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-21 | 2024-03-27 | Unknown | Unknown | 2024-03-27 | 2024-05-21 | 56 | 40 | 2024-05-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | Applicant Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-17 | 2025-01-07 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3661.75 | 849.49 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-17 | 2024-09-06 | Unknown | Unknown | 2024-09-06 | 2025-02-19 | 167 | 119 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-19 | 2025-07-21 | 153 | 109 | Unknown | 2025-07-21 | Unknown | Unknown | 2025-08-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 36.15 | 36.15 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-10 | 2025-03-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1738.98 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-10 | 2025-02-20 | Unknown | Unknown | 2025-02-20 | 2025-03-12 | 21 | 15 | 2025-03-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | 63.05 | 63.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-13 | Unknown | Unknown | No | 2025-02-26 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-26 | 2025-02-26 | Unknown | IOU Designed & Installed | N/A | Yes | 138 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2695.91 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-26 | 2025-07-11 | 136 | 98 | 2025-07-11 | 2025-01-24 | Unknown | Unknown | 2025-01-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-26 | 2025-08-28 | 184 | 132 | Unknown | Unknown | Unknown | Unknown | 2025-08-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 7 | 7 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-04 | Unknown | Unknown | No | 2024-02-01 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-01 | 2024-02-01 | Unknown | IOU Designed & Installed | N/A | Yes | 32 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 955.79 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-01 | 2024-03-04 | 33 | 23 | 2024-03-04 | 2024-02-01 | Unknown | Unknown | 2024-02-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-04-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-01 | 2023-03-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 9341 | 3513 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-01 | 2023-03-13 | 13 | 9 | 2023-03-13 | 2023-05-01 | 50 | 36 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-05-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-03 | 2023-08-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 9695.43 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-03 | 2023-08-03 | 1 | 1 | 2023-08-03 | 2023-09-11 | 40 | 28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 28.05 | 28.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-26 | 2023-07-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 153.83 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-26 | 2023-07-26 | 1 | 1 | 2023-07-26 | 2023-07-26 | 1 | 1 | 2023-07-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-06 | 2025-03-31 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2023.37 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-06 | 2025-02-28 | Unknown | Unknown | 2025-02-28 | 2025-03-31 | 32 | 22 | 2025-03-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | MOUNT LAGUNA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-07 | 2023-06-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 732.43 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-07 | 2023-06-07 | 1 | 1 | 2023-06-07 | 2023-07-06 | 30 | 22 | 2023-07-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 3644 | 3644 | Not Available | >2MW | No | N/A | N/A | N/A | 2026-07-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-06 | 2024-08-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2041.69 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-06 | 2024-07-12 | Unknown | Unknown | 2024-07-12 | 2024-08-15 | 35 | 25 | 2024-08-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-10 | 2025-03-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1163.08 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-10 | 2025-03-03 | Unknown | Unknown | 2025-03-03 | 2025-03-13 | 11 | 9 | 2025-03-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-21 | 2024-09-10 | 2024-12-20 | IOU Designed & Installed | N/A | No | Unknown | 3927.83 | 853.92 | Unknown | 50.07 | 96.68 | 2927.16 | 3981 | 1137.18 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-21 | 2024-09-10 | 21 | 15 | 2024-09-10 | 2024-09-10 | 1 | 1 | 2024-09-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-10 | 2024-12-20 | 102 | 74 | Unknown | 2024-12-20 | Unknown | Unknown | 2024-12-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | OCEANSIDE | 2.7 | 2.7 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-27 | 2025-03-21 | 2025-06-30 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1819.06 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-27 | 2025-03-14 | 16 | 12 | 2025-03-14 | 2025-03-21 | 8 | 6 | 2025-02-28 | 2025-03-21 | 22 | 16 | 2025-03-24 | 2025-04-08 | 16 | 12 | 2025-03-21 | 2025-06-30 | 102 | 72 | Unknown | Unknown | Unknown | Unknown | 2025-06-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-12 | 2024-12-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 27449 | 688.14 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-12 | 2024-11-19 | Unknown | Unknown | 2024-11-19 | 2024-12-12 | 24 | 18 | 2024-12-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | OCEANSIDE | 19.05 | 19.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-23 | 2025-03-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2036.85 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-23 | 2025-03-07 | 166 | 120 | 2025-03-07 | 2025-03-07 | 1 | 1 | 2025-03-07 | Unknown | Unknown | Unknown | 2025-03-10 | 2025-03-25 | 16 | 12 | 2025-03-07 | 2025-09-03 | 181 | 129 | Unknown | Unknown | Unknown | Unknown | 2025-09-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-11 | 2025-04-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3519.63 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-11 | 2025-04-14 | 4 | 2 | 2025-04-14 | 2025-04-15 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | OH | IOU Design | Commercial | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2024-09-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-17 | 2025-04-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 14831 | 60810.08 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-17 | 2025-05-05 | 19 | 13 | 2025-05-05 | 2025-07-10 | 67 | 49 | 2025-06-13 | 2025-06-20 | 8 | 6 | 2025-06-24 | 2025-07-10 | 17 | 13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-07-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | OCEANSIDE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-09 | 2024-01-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1044.55 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-09 | 2024-01-11 | 3 | 3 | 2024-01-11 | 2024-01-11 | 1 | 1 | 2024-01-11 | Unknown | Unknown | Unknown | 2024-01-12 | 2024-01-25 | 14 | 10 | 2024-01-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | Applicant Design | Commercial | Underserved Community | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-14 | 2023-04-14 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 782552 | 47899.91 | Unknown | Unknown | Yes | N/A | N/A | 2023-04-14 | 2024-05-24 | 407 | 291 | 2024-05-24 | 2024-09-16 | 116 | 82 | 2024-04-30 | 2024-09-12 | 3 | 3 | 2024-05-29 | 2024-06-24 | 27 | 19 | 2024-09-16 | Unknown | Unknown | Unknown | 2025-05-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2025-05-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-17 | 2024-05-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 70025 | 5010.32 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-17 | 2024-04-12 | Unknown | Unknown | 2024-04-12 | 2024-06-18 | 68 | 48 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 10 | 10 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-06 | Unknown | Unknown | No | 2024-03-26 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-26 | 2024-03-26 | 2024-04-25 | IOU Designed & Installed | N/A | Yes | 3 | 745.73 | 183.68 | Unknown | Unknown | 99.6 | 462.45 | 0 | 981.91 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-26 | 2024-03-29 | 4 | 4 | 2024-03-29 | 2024-03-27 | Unknown | Unknown | 2024-03-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-27 | 2024-04-25 | 30 | 22 | Unknown | Unknown | Unknown | Unknown | 2024-04-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-29 | 2025-04-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1700.18 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-29 | 2025-04-15 | Unknown | Unknown | 2025-04-15 | 2025-04-29 | 15 | 11 | 2025-04-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-29 | 2025-07-29 | 92 | 66 | Unknown | Unknown | Unknown | Unknown | 2025-07-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | Underserved Community | San Diego | N/A | 39.05 | 39.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-22 | 2024-02-22 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 5347.78 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-22 | 2024-05-06 | 75 | 53 | 2024-05-06 | 2024-12-11 | 220 | 158 | 2024-05-21 | 2024-12-04 | 89 | 65 | 2024-12-06 | 2024-12-10 | 5 | 3 | 2025-01-27 | Unknown | Unknown | Unknown | 2025-01-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-13 | 2025-04-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1411.78 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-13 | 2025-04-30 | 18 | 13 | 2025-04-30 | 2025-05-21 | 22 | 16 | 2025-05-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 85 | 85 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-16 | 2023-10-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 940.94 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-16 | 2023-07-26 | Unknown | Unknown | 2023-07-26 | 2023-10-30 | 97 | 69 | 2023-10-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community,Tribal Community | PALA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-03 | 2024-05-03 | 2025-06-25 | IOU Designed & Installed | N/A | No | Unknown | 527.46 | 47.37 | Unknown | Unknown | 7.54 | 472.55 | 3981 | 393.97 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-03 | 2024-05-03 | 1 | 1 | 2024-05-03 | 2025-05-06 | 369 | 263 | 2024-07-17 | 2024-07-17 | 1 | 1 | 2025-05-28 | 2025-05-28 | 1 | 1 | 2025-05-06 | Unknown | Unknown | Unknown | Unknown | 2025-05-29 | Unknown | Unknown | 2025-06-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-10 | 2025-04-10 | 2025-05-13 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1619.68 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-10 | 2025-04-10 | 1 | 1 | 2025-04-10 | 2025-04-10 | 1 | 1 | 2025-04-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-10 | 2025-05-13 | 34 | 24 | Unknown | Unknown | Unknown | Unknown | 2025-05-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-21 | 2024-03-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3241 | 1716.73 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-21 | 2024-03-21 | 1 | 1 | 2024-03-21 | 2024-03-21 | 1 | 1 | 2024-03-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-21 | 2025-08-19 | 517 | 369 | Unknown | Unknown | Unknown | Unknown | 2025-08-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 37 | 37 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-11 | 2024-12-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2005.99 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-11 | 2025-01-16 | 37 | 27 | 2025-01-16 | 2025-02-21 | 37 | 27 | 2025-02-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 30 | 30 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-30 | 2024-03-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2088.56 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-30 | 2024-03-05 | 36 | 26 | 2024-03-05 | 2024-03-08 | 4 | 4 | 2024-03-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-08 | 2025-07-15 | 495 | 353 | Unknown | Unknown | Unknown | Unknown | 2025-07-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-18 | 2023-04-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1417.03 | Unknown | Unknown | Yes | N/A | N/A | 2023-04-18 | 2023-04-18 | 1 | 1 | 2023-04-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 127 | 127 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-30 | 2025-06-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 826.97 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-30 | 2025-06-12 | 14 | 10 | 2025-06-12 | 2025-06-12 | 1 | 1 | 2025-06-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-12 | 2025-08-18 | 68 | 48 | Unknown | 2025-08-14 | Unknown | Unknown | 2025-08-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | COUNTY OF SAN DIEGO-SOUTH of 56 | 9.05 | 9.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-30 | 2024-07-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3941 | 1480.74 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-30 | 2024-07-10 | Unknown | Unknown | 2024-07-10 | 2024-07-30 | 21 | 15 | 2024-07-30 | 2025-01-03 | 158 | 114 | 2025-01-03 | 2025-01-16 | 14 | 10 | 2024-07-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 61 | 61 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-14 | 2024-02-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 655.38 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-14 | 2023-12-15 | 2 | 2 | 2023-12-15 | 2024-06-06 | 175 | 125 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-25 | 2024-07-12 | 2025-06-30 | IOU Designed & Installed | N/A | No | Unknown | 1511.69 | 0 | Unknown | Unknown | 111.81 | 1399.88 | 3661.75 | 642.02 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-25 | 2024-09-17 | 85 | 61 | 2024-09-17 | 2024-09-17 | 1 | 1 | 2024-09-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-18 | 2025-06-30 | 286 | 204 | Unknown | 2025-07-16 | Unknown | Unknown | 2025-06-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Commercial | N/A | San Juan Capistrano | SAN JUAN CAPISTRANO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-03-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-20 | 2024-08-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 39831.16 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-20 | 2024-07-26 | 495 | 355 | 2024-07-26 | Unknown | Unknown | Unknown | 2024-10-08 | 2024-10-14 | 7 | 5 | 2024-08-30 | 2025-07-11 | 114 | 82 | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-31 | Unknown | Unknown | 2025-08-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | Santee | SANTEE | 1024 | 1024 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2026-09-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-16 | 2025-01-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 81170.19 | 74144.91 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-16 | 2024-12-10 | 56 | 40 | 2024-12-10 | 2025-06-18 | 191 | 137 | 2025-02-11 | 2025-06-16 | 5 | 3 | 2025-01-29 | 2025-07-02 | 118 | 84 | 2025-06-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-08 | 2024-05-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7320 | 584.27 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-08 | 2024-02-26 | Unknown | Unknown | 2024-02-26 | 2024-05-08 | 73 | 53 | 2024-05-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-08 | 2025-08-28 | 478 | 342 | Unknown | Unknown | Unknown | Unknown | 2025-08-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Commercial | Underserved Community | Imperial Beach | IMPERIAL BEACH | 4722 | 4722 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-07-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-09 | 2023-04-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3390.67 | Unknown | Unknown | Yes | N/A | N/A | 2023-02-09 | 2023-04-05 | 56 | 40 | 2023-04-05 | 2023-05-10 | 36 | 26 | 2023-04-05 | 2023-05-09 | 2 | 0 | 2023-04-13 | 2025-08-07 | 99 | 73 | 2025-05-06 | Unknown | Unknown | Unknown | 2025-05-06 | 2025-07-21 | 77 | 55 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-21 | 2023-09-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 38768 | 35882.68 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-21 | 2024-03-20 | 274 | 196 | 2024-03-20 | 2024-03-21 | 2 | 2 | 2024-01-22 | 2024-01-23 | 2 | 2 | 2024-03-05 | 2024-03-29 | 25 | 19 | 2024-03-21 | Unknown | Unknown | Unknown | 2025-01-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2020-12-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-05 | 2023-06-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 307.76 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-05 | 2023-06-05 | 1 | 1 | 2023-06-05 | 2023-09-12 | 100 | 72 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-12 | Unknown | Unknown | Unknown | Unknown | 2023-11-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 10 | 10 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-24 | 2025-03-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 482.54 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-24 | 2025-04-25 | 33 | 25 | 2025-04-25 | 2025-05-05 | 11 | 7 | 2025-05-05 | 2025-05-07 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2025-05-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-25 | 2024-12-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1049.51 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-25 | 2024-12-02 | 8 | 6 | 2024-12-02 | 2024-12-30 | 29 | 21 | 2024-12-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-10 | 2025-06-25 | 2025-06-30 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1303.82 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-10 | 2025-06-25 | 16 | 12 | 2025-06-25 | 2025-06-25 | 1 | 1 | 2025-06-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-25 | 2025-06-30 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2025-06-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-10 | 2024-09-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1150.97 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-10 | 2024-10-04 | 25 | 19 | 2024-10-04 | 2024-10-04 | 1 | 1 | 2024-10-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-26 | 2023-04-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 8997 | 502.66 | Unknown | Unknown | Yes | N/A | N/A | 2023-04-26 | 2023-04-26 | 1 | 1 | 2023-04-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 1296 | 1296 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2025-07-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-17 | 2023-10-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 708.24 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-17 | 2023-08-06 | Unknown | Unknown | 2023-08-06 | 2023-10-17 | 73 | 52 | 2023-10-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | N/A | 1004.1 | 1004.1 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2026-07-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-13 | 2024-09-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1589.95 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-13 | 2024-10-16 | 34 | 24 | 2024-10-16 | 2024-10-16 | 1 | 1 | 2024-10-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-03 | 2025-01-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3241 | 340.79 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-03 | 2024-11-11 | Unknown | Unknown | 2024-11-11 | 2025-01-03 | 54 | 40 | 2025-01-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | LAGUNA HILLS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-16 | 2023-05-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1950.5 | Unknown | Unknown | Yes | N/A | N/A | 2023-05-16 | 2023-05-23 | 8 | 6 | 2023-05-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | OCEANSIDE | 329.2 | 329.2 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-17 | 2024-07-31 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 10950.8 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-17 | 2024-07-24 | 8 | 6 | 2024-07-24 | 2025-01-14 | 175 | 125 | 2024-07-26 | 2024-07-28 | 3 | 1 | 2024-07-31 | 2025-08-06 | 30 | 22 | 2025-01-14 | Unknown | Unknown | Unknown | 2025-01-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | CORONADO | N/A | 17.75 | 17.75 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-02 | 2024-10-02 | 2025-03-10 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1159.32 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-02 | 2024-06-14 | Unknown | Unknown | 2024-06-14 | 2024-10-02 | 111 | 79 | 2024-10-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-02 | 2025-03-10 | 160 | 114 | Unknown | Unknown | Unknown | Unknown | 2025-03-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | OCEANSIDE | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2024-09-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-05 | 2023-10-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 16364 | 3875.01 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-05 | 2024-05-06 | 215 | 153 | 2024-05-06 | 2024-06-20 | 46 | 34 | Unknown | Unknown | Unknown | Unknown | 2024-02-15 | 2025-08-01 | 108 | 78 | 2024-06-20 | 2025-02-10 | 236 | 168 | Unknown | 2025-03-27 | Unknown | Unknown | 2025-07-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-27 | 2023-10-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 815.58 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-27 | 2023-09-13 | Unknown | Unknown | 2023-09-13 | 2023-10-27 | 45 | 33 | 2023-10-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | RAMONA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-16 | 2024-04-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 488.12 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-16 | 2023-11-14 | Unknown | Unknown | 2023-11-14 | 2024-11-06 | 359 | 257 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-09 | 2025-05-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1011.35 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-09 | 2025-05-09 | 1 | 1 | 2025-05-09 | 2025-05-09 | 1 | 1 | 2025-05-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-09 | 2025-07-16 | 69 | 49 | Unknown | Unknown | Unknown | Unknown | 2025-07-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | DANA POINT | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-16 | 2025-01-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 499.14 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-16 | 2025-01-14 | Unknown | Unknown | 2025-01-14 | 2025-01-31 | 18 | 14 | 2025-01-31 | Unknown | Unknown | Unknown | 2025-01-30 | 2025-02-19 | 21 | 15 | 2025-01-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-24 | Unknown | Unknown | No | 2023-05-26 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-26 | 2023-05-26 | Unknown | IOU Designed & Installed | N/A | Yes | 563 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3661 | 1207.66 | Unknown | Unknown | Yes | N/A | N/A | 2023-05-26 | 2024-12-06 | 561 | 401 | 2024-12-06 | 2024-12-09 | 4 | 2 | 2024-12-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-11 | 2025-04-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 983.49 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-11 | 2025-04-11 | 1 | 1 | 2025-04-11 | 2025-04-17 | 7 | 5 | 2025-04-17 | 2025-06-12 | 57 | 41 | Unknown | Unknown | Unknown | Unknown | 2025-06-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | 44.9 | 44.9 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-14 | 2024-08-14 | 2025-03-17 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 9873 | 1991.17 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-14 | 2024-08-14 | 1 | 1 | 2024-08-14 | 2024-06-24 | Unknown | Unknown | 2024-06-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-14 | 2025-03-17 | 216 | 154 | Unknown | Unknown | Unknown | Unknown | 2025-03-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-31 | 2025-04-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1940.77 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-31 | 2025-04-08 | 9 | 7 | 2025-04-08 | 2025-04-08 | 1 | 1 | 2025-04-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-08 | 2025-07-28 | 112 | 80 | Unknown | Unknown | Unknown | Unknown | 2025-07-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-23 | 2025-04-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2476.4 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-23 | 2025-05-19 | 27 | 19 | 2025-05-19 | 2025-05-28 | 10 | 8 | 2025-05-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-25 | 2024-06-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1247.19 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-25 | 2024-06-17 | Unknown | Unknown | 2024-06-17 | 2024-07-03 | 17 | 13 | 2024-07-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-03 | 2025-09-09 | 434 | 310 | Unknown | 2025-08-27 | Unknown | Unknown | 2025-09-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | LA JOLLA | N/A | 20800 | 20800 | Not Available | >2MW | No | N/A | N/A | N/A | 2027-05-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-29 | 2025-06-19 | 2025-06-24 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1117.16 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-29 | 2025-06-02 | 5 | 3 | 2025-06-02 | 2025-06-19 | 18 | 14 | 2025-06-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-19 | 2025-06-24 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2025-06-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SANTEE | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-16 | 2024-07-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1322.91 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-16 | 2024-06-21 | Unknown | Unknown | 2024-06-21 | 2024-07-18 | 28 | 20 | 2024-07-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 5.4 | 5.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-29 | 2025-06-09 | 2025-06-16 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1106.23 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-29 | 2025-06-06 | 9 | 7 | 2025-06-06 | 2025-06-09 | 4 | 2 | 2025-06-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-09 | 2025-06-16 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2025-06-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 16 | 16 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-30 | 2023-10-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 15924 | 1511.7 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-30 | 2023-10-30 | 62 | 44 | 2023-10-30 | 2024-01-24 | 87 | 63 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 61 | 61 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-14 | 2023-12-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 697.08 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-14 | 2023-12-15 | 2 | 2 | 2023-12-15 | 2024-06-06 | 175 | 125 | Unknown | Unknown | Unknown | Unknown | 2024-02-07 | 2024-03-05 | 28 | 20 | 2024-06-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-20 | 2024-05-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | 430.83 | 0 | Unknown | Unknown | Unknown | 430.83 | 0 | 1166.61 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-20 | 2024-09-24 | 128 | 92 | 2024-09-24 | 2024-10-02 | 9 | 7 | 2024-10-02 | 2025-03-28 | 178 | 128 | Unknown | Unknown | Unknown | Unknown | 2025-03-28 | 2025-07-01 | 96 | 68 | Unknown | 2025-06-26 | Unknown | Unknown | 2025-07-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-03 | 2025-06-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1101.26 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-03 | 2025-02-24 | Unknown | Unknown | 2025-02-24 | 2025-06-16 | 113 | 81 | 2025-06-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 70.05 | 70.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-25 | 2025-01-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 196.69 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-25 | 2024-12-31 | 37 | 27 | 2024-12-31 | 2025-01-27 | 28 | 20 | 2025-01-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-27 | 2025-07-15 | 170 | 122 | Unknown | 2025-07-07 | Unknown | Unknown | 2025-07-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | Applicant Design | Residential | N/A | San Diego | San Diego | 38528 | 38528 | Not Available | >2MW | No | N/A | N/A | N/A | 2025-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2021-10-20 | 2021-10-20 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2662056 | 314609.91 | Unknown | Unknown | Yes | N/A | N/A | 2021-10-20 | 2024-02-23 | 857 | 613 | 2024-02-23 | 2025-03-18 | 390 | 278 | 2024-03-05 | 2024-07-01 | 25 | 19 | 2024-03-21 | 2025-06-19 | 118 | 86 | 2025-03-18 | Unknown | Unknown | Unknown | 2025-06-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN JUAN CAPISTRANO | N/A | 177 | 177 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-05-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-19 | 2022-05-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1252.89 | Unknown | Unknown | Yes | N/A | N/A | 2022-05-19 | 2023-06-09 | 387 | 277 | 2023-06-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | 5.4 | 5.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-11 | 2024-06-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1100.63 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-11 | 2024-04-11 | Unknown | Unknown | 2024-04-11 | 2024-07-17 | 98 | 70 | 2024-07-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | La Mesa | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-08-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-31 | 2023-07-31 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 1000 | 181.36 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-31 | 2023-07-31 | 1 | 1 | 2023-07-31 | 2023-08-02 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 10 | 10 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-02 | 2023-12-02 | 2024-07-16 | IOU Designed & Installed | N/A | No | Unknown | 701.48 | -358.1 | Unknown | Unknown | 172.94 | 886.64 | 7962 | 549.32 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-02 | 2023-12-02 | 1 | 0 | 2023-12-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-04 | 2024-07-16 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | 2024-07-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SANTEE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-05 | 2024-04-05 | 2024-04-08 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 158.37 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-05 | 2024-02-23 | Unknown | Unknown | 2024-02-23 | 2024-04-05 | 43 | 31 | 2024-04-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-05 | 2024-04-08 | 4 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-04-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2030-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-26 | 2025-02-26 | 2025-04-12 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 4578.05 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-26 | 2025-02-26 | 1 | 1 | 2025-02-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-11 | 2025-06-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 4833.65 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-11 | 2025-06-09 | Unknown | Unknown | 2025-06-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-22 | 2024-05-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 6314.93 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-22 | 2024-08-12 | 83 | 59 | 2024-08-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-24 | 2025-03-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1899.57 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-24 | 2025-02-03 | Unknown | Unknown | 2025-02-03 | 2025-05-20 | 107 | 77 | Unknown | Unknown | Unknown | Unknown | 2025-03-25 | 2025-04-09 | 16 | 12 | 2025-05-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | RANCHO LA COSTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-16 | 2025-05-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 842.2 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-16 | 2025-05-12 | 148 | 106 | 2025-05-12 | 2025-05-12 | 1 | 1 | 2025-05-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-12 | 2025-07-01 | 51 | 37 | Unknown | 2025-06-27 | Unknown | Unknown | 2025-07-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | POWAY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-27 | 2025-05-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 886.18 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-27 | 2025-06-05 | 10 | 8 | 2025-06-05 | 2025-06-09 | 5 | 3 | 2025-06-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-19 | 2023-09-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 693.48 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-19 | 2023-07-13 | Unknown | Unknown | 2023-07-13 | 2023-09-28 | 78 | 56 | 2023-09-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Commercial | N/A | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-11-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-28 | 2023-09-28 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 19258.65 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-28 | 2023-10-23 | 26 | 18 | 2023-10-23 | 2024-08-08 | 291 | 209 | 2023-11-03 | 2023-11-15 | 13 | 9 | 2024-02-23 | 2024-04-05 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | Disadvantaged Community,Underserved Community | Chula Vista | CHULA VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-09 | 2023-11-09 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 163053 | 118089.49 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-09 | 2024-10-28 | 355 | 253 | 2024-10-28 | 2025-06-27 | 243 | 175 | 2024-11-07 | 2025-08-01 | 178 | 127 | 2025-03-03 | 2025-04-25 | 54 | 40 | 2025-07-02 | Unknown | Unknown | Unknown | 2025-07-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 8 | 8 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-16 | 2025-05-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 976.53 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-16 | 2025-04-22 | Unknown | Unknown | 2025-04-22 | 2025-05-21 | 30 | 22 | 2025-05-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community,Tribal Community | VALLEY CENTER | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-27 | 2025-03-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1467.99 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-27 | 2025-04-11 | 16 | 12 | 2025-04-11 | 2025-04-18 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-03 | 2024-12-03 | 2025-01-26 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1088.49 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-03 | 2024-12-02 | Unknown | Unknown | 2024-12-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SANTEE | N/A | 30 | 30 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-03 | 2023-04-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 526.82 | Unknown | Unknown | Yes | N/A | N/A | 2023-04-03 | 2023-04-03 | 1 | 1 | 2023-04-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | OCEANSIDE | N/A | 77 | 77 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-04 | 2025-01-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1506.99 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-04 | 2025-01-27 | 55 | 39 | 2025-01-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-01 | 2024-12-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 18300 | 525.43 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-01 | 2025-01-08 | 69 | 49 | 2025-01-08 | 2025-01-21 | 14 | 10 | 2025-01-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-03 | 2024-07-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1298.18 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-03 | 2024-06-05 | Unknown | Unknown | 2024-06-05 | 2024-07-22 | 48 | 34 | 2024-07-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 30 | 30 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-14 | 2023-03-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 363.72 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-14 | 2023-03-14 | 1 | 1 | 2023-03-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-20 | 2023-07-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 480.44 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-20 | 2023-05-10 | Unknown | Unknown | 2023-05-10 | 2023-07-20 | 72 | 52 | 2023-07-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | JAMUL | N/A | 67.05 | 67.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-22 | 2024-08-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3941 | 1480.97 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-22 | 2024-07-18 | Unknown | Unknown | 2024-07-18 | 2024-08-22 | 36 | 26 | 2024-08-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | CORONADO | N/A | 138.05 | 138.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-26 | 2025-02-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2207.31 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-26 | 2025-02-27 | 2 | 2 | 2025-02-27 | 2025-04-14 | 47 | 33 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LEMON GROVE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-21 | 2025-06-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1061.11 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-21 | 2025-05-21 | 1 | 1 | 2025-05-21 | 2025-06-05 | 16 | 12 | 2025-06-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-05 | 2025-07-25 | 51 | 37 | Unknown | Unknown | Unknown | Unknown | 2025-07-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-01 | Unknown | Unknown | No | 2022-04-11 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-11 | 2022-04-11 | Unknown | IOU Designed & Installed | N/A | Yes | 1086 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 14210 | 355.7 | Unknown | Unknown | Yes | N/A | N/A | 2022-04-11 | 2025-02-06 | 1033 | 739 | 2025-02-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2022-04-20 | 2025-07-29 | Unknown | Unknown | Unknown | 2025-04-10 | Unknown | Unknown | 2025-07-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-24 | 2024-04-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 12481 | 584.27 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-24 | 2024-02-14 | Unknown | Unknown | 2024-02-14 | 2024-04-24 | 71 | 51 | 2024-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-24 | 2025-07-24 | 457 | 327 | Unknown | Unknown | Unknown | Unknown | 2025-07-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-20 | 2023-12-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 885.19 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-20 | 2023-12-15 | Unknown | Unknown | 2023-12-15 | 2023-12-20 | 6 | 4 | 2023-12-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-07 | 2024-05-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1031.96 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-07 | 2024-05-15 | 9 | 7 | 2024-05-15 | 2024-05-15 | 1 | 1 | 2024-05-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-28 | 2024-09-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 505728 | 25516.84 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-28 | 2024-09-04 | 8 | 6 | 2024-09-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-28 | 2024-12-03 | 37 | 27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-29 | 2023-08-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2311.46 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-29 | 2023-09-21 | 24 | 18 | 2023-09-21 | 2023-09-21 | 1 | 1 | 2023-09-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-21 | Unknown | Unknown | Unknown | Unknown | 2023-10-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | EL CAJON | 12.05 | 12.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-07 | 2025-02-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 194.21 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-07 | 2025-02-07 | 1 | 1 | 2025-02-07 | 2025-05-28 | 111 | 79 | Unknown | Unknown | Unknown | Unknown | 2025-02-07 | 2025-06-18 | 52 | 38 | 2025-05-28 | 2025-07-17 | 51 | 37 | Unknown | 2025-06-09 | Unknown | Unknown | 2025-07-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 64.05 | 64.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-10 | 2024-10-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1501.95 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-10 | 2024-09-30 | 21 | 15 | 2024-09-30 | 2024-10-01 | 2 | 2 | 2024-10-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 878.05 | 878.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-12 | 2024-07-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1554.83 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-12 | 2024-05-09 | Unknown | Unknown | 2024-05-09 | 2024-07-12 | 65 | 47 | 2024-07-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | Poway | Poway | 43 | 43 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-06-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-19 | 2024-12-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 960.58 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-19 | 2024-12-19 | 1 | 1 | 2024-12-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-03 | 2025-01-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1459.01 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-03 | 2024-10-24 | Unknown | Unknown | 2024-10-24 | 2025-01-06 | 75 | 53 | 2025-01-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 47.1 | 47.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-19 | 2025-03-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1456.53 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-19 | 2025-03-20 | 2 | 2 | 2025-03-20 | 2025-03-29 | 10 | 7 | 2025-03-19 | 2025-03-20 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2025-03-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-11 | 2025-06-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1595.38 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-11 | 2025-07-30 | 50 | 36 | 2025-07-30 | 2025-08-04 | 6 | 4 | 2025-08-04 | 2025-06-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-17 | 2025-09-05 | 81 | 59 | Unknown | 2025-08-19 | Unknown | Unknown | 2025-09-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-18 | 2024-12-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1824.54 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-18 | 2024-12-18 | 1 | 1 | 2024-12-18 | 2024-12-18 | 1 | 1 | 2024-12-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Commercial | Disadvantaged Community,Underserved Community | National City | NATIONAL CITY | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-28 | 2024-04-17 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 308748.65 | 18979.35 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-28 | 2024-10-22 | 422 | 302 | 2024-10-22 | 2025-02-27 | 129 | 93 | 2024-10-29 | 2025-02-26 | 32 | 24 | 2024-08-19 | 2025-07-17 | 109 | 79 | 2025-05-28 | Unknown | Unknown | Unknown | 2025-05-28 | 2025-07-08 | 42 | 30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2017-10-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-21 | 2023-07-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1110.53 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-21 | 2023-07-21 | 1 | 1 | 2023-07-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-05-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-12 | 2023-12-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 8370 | 387.65 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-12 | 2023-10-10 | 29 | 21 | 2023-10-10 | 2024-01-31 | 114 | 82 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | FALLBROOK | COUNTY OF SAN DIEGO-NORTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-18 | 2024-04-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 637.53 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-18 | 2023-12-02 | Unknown | Unknown | 2023-12-02 | 2024-04-19 | 140 | 100 | 2024-04-19 | Unknown | Unknown | Unknown | 2024-04-23 | 2024-04-25 | 3 | 3 | 2024-04-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 5 | 5 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-10 | 2023-05-10 | 2023-09-27 | IOU Designed & Installed | N/A | No | Unknown | 747.4 | 271.9 | Unknown | Unknown | Unknown | 475.5 | 3981 | 871.71 | Unknown | Unknown | Yes | N/A | N/A | 2023-05-10 | 2023-05-10 | 1 | 1 | 2023-05-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-11 | 2023-09-27 | 140 | 100 | Unknown | Unknown | Unknown | Unknown | 2023-09-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 6.05 | 6.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-18 | 2023-10-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 927.18 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-18 | 2023-10-30 | 13 | 9 | 2023-10-30 | 2023-11-02 | 4 | 4 | 2023-11-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | N/A | 284.2 | 284.2 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-15 | 2024-05-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 808.78 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-15 | 2024-05-15 | 1 | 1 | 2024-05-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | CORONADO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-23 | 2024-10-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3540.35 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-23 | 2024-12-02 | 41 | 29 | 2024-12-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-21 | 2025-03-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 5776 | 1217.76 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-21 | 2025-03-18 | Unknown | Unknown | 2025-03-18 | 2025-03-25 | 8 | 6 | 2025-03-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | OH | IOU Design | Residential | Underserved Community | JULIAN | COUNTY OF SAN DIEGO-NORTH of 56 | 53.05 | 53.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-09 | 2023-11-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 10137.73 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-09 | 2023-12-28 | 50 | 36 | 2023-12-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-01 | 2023-12-06 | 6 | 4 | 2024-05-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-12 | 2024-02-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 534.53 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-12 | 2024-02-12 | 1 | 1 | 2024-02-12 | 2024-02-12 | 1 | 1 | 2024-02-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-20 | 2025-03-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 11943 | 1696.63 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-20 | 2025-03-20 | 1 | 1 | 2025-03-20 | 2025-04-07 | 19 | 13 | Unknown | Unknown | Unknown | Unknown | 2025-03-21 | 2025-04-03 | 14 | 10 | 2025-04-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | LA JOLLA | N/A | 12 | 12 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-21 | 2025-03-31 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 997.19 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-21 | 2025-03-24 | 4 | 2 | 2025-03-24 | 2025-03-31 | 8 | 6 | 2025-03-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | 234.05 | 234.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-07 | 2025-02-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2196.02 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-07 | 2025-01-22 | Unknown | Unknown | 2025-01-22 | 2025-02-07 | 17 | 13 | 2025-02-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN JUAN CAPISTRANO | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-31 | 2024-12-31 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1309.13 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-31 | 2025-03-12 | 72 | 52 | 2025-03-12 | 2025-03-17 | 6 | 4 | 2025-03-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-03 | 2024-12-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 18300 | 507.91 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-03 | 2024-11-19 | Unknown | Unknown | 2024-11-19 | 2024-12-30 | 42 | 30 | 2024-12-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-30 | Unknown | Unknown | Unknown | Unknown | 2025-04-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | 60 | 60 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-28 | 2023-04-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3279.62 | Unknown | Unknown | Yes | N/A | N/A | 2023-04-28 | 2023-06-02 | 36 | 26 | 2023-06-02 | 2023-06-23 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | 2023-06-06 | 2023-06-12 | 7 | 5 | 2023-06-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | OCEANSIDE | 20 | 20 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-03 | 2024-06-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1826.23 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-03 | 2024-05-15 | Unknown | Unknown | 2024-05-15 | 2024-06-17 | 34 | 24 | 2024-06-17 | Unknown | Unknown | Unknown | 2024-06-18 | 2024-07-01 | 14 | 10 | 2024-06-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CARDIFF | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-17 | 2024-07-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1142.92 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-17 | 2024-07-03 | 17 | 13 | 2024-07-03 | 2024-07-03 | 1 | 1 | 2024-07-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-27 | 2023-10-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 6034.35 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-27 | 2023-10-27 | 1 | 1 | 2023-10-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 7 | 7 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-22 | 2025-05-07 | 2025-06-27 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1286.56 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-22 | 2025-05-01 | 100 | 72 | 2025-05-01 | 2025-05-07 | 7 | 5 | 2025-05-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-07 | 2025-06-27 | 52 | 38 | Unknown | Unknown | Unknown | Unknown | 2025-06-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN MARCOS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-17 | 2023-10-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 734.74 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-17 | 2023-11-20 | 35 | 25 | 2023-11-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | LA MESA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-06-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-26 | 2025-06-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1047.92 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-26 | 2025-06-24 | Unknown | Unknown | 2025-06-24 | 2025-06-26 | 3 | 3 | 2025-06-26 | Unknown | Unknown | Unknown | 2025-06-26 | 2025-07-07 | 12 | 8 | 2025-06-26 | 2025-07-14 | 19 | 13 | Unknown | Unknown | Unknown | Unknown | 2025-07-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-31 | 2023-03-31 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 209.1 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-31 | 2023-03-31 | 1 | 1 | 2023-03-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | VISTA | 440.4 | 440.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-05 | 2025-05-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2576.55 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-05 | 2025-04-17 | Unknown | Unknown | 2025-04-17 | 2025-05-05 | 19 | 13 | 2025-05-05 | Unknown | Unknown | Unknown | 2025-05-06 | 2025-06-03 | 29 | 21 | 2025-05-05 | 2025-08-13 | 101 | 73 | Unknown | Unknown | Unknown | Unknown | 2025-08-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-26 | 2023-07-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 286556 | 5589.24 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-26 | 2023-04-10 | Unknown | Unknown | 2023-04-10 | 2023-09-07 | 151 | 109 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 7.6 | 7.6 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-02 | Unknown | Unknown | No | 2024-08-07 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-07 | 2024-08-07 | Unknown | IOU Designed & Installed | N/A | Yes | 338 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 117.46 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-07 | 2025-07-09 | 337 | 241 | 2025-07-09 | 2024-09-06 | Unknown | Unknown | 2024-09-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-06 | 2025-08-11 | 340 | 242 | Unknown | Unknown | Unknown | Unknown | 2025-08-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN JUAN CAPISTRANO | N/A | 924 | 924 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-09-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-03-16 | 2022-03-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3885 | 809.64 | Unknown | Unknown | Yes | N/A | N/A | 2022-03-16 | 2025-03-06 | 1087 | 777 | 2025-03-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2022-03-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2020-02-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-03 | 2023-07-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1110.53 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-03 | 2023-05-31 | Unknown | Unknown | 2023-05-31 | 2023-07-07 | 38 | 28 | 2023-07-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | ESCONDIDO | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-27 | 2025-02-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1063.08 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-27 | 2025-02-28 | 155 | 111 | 2025-02-28 | 2025-05-29 | 91 | 65 | Unknown | Unknown | Unknown | Unknown | 2025-03-27 | 2025-04-08 | 13 | 9 | 2025-05-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 132.05 | 132.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-30 | Unknown | Unknown | No | 2025-01-13 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-13 | 2025-01-31 | Unknown | IOU Designed & Installed | N/A | Yes | 135 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1150.99 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-13 | 2025-05-22 | 130 | 94 | 2025-05-22 | 2025-05-22 | 1 | 1 | 2025-05-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-07 | 2025-08-08 | 183 | 131 | Unknown | Unknown | Unknown | Unknown | 2025-08-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-03 | 2025-06-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1171.32 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-03 | 2025-06-03 | 1 | 1 | 2025-06-03 | 2025-06-03 | 1 | 1 | 2025-06-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | BONSALL | N/A | 189 | 189 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-18 | 2024-10-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1564.6 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-18 | 2024-10-14 | Unknown | Unknown | 2024-10-14 | 2024-11-21 | 39 | 29 | 2024-11-21 | 2024-12-18 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | 2024-12-18 | Unknown | Unknown | Unknown | Unknown | 2025-05-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-31 | 2025-04-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3300.25 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-31 | 2025-03-14 | Unknown | Unknown | 2025-03-14 | 2025-04-08 | 26 | 18 | 2025-04-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-30 | 2025-01-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1736.43 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-30 | 2025-01-30 | 1 | 1 | 2025-01-30 | 2025-01-30 | 1 | 1 | 2025-01-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | Applicant Design | Residential | Underserved Community | POTRERO | N/A | 142.05 | 142.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-01 | 2025-05-08 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7960 | 1793.45 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-01 | 2025-05-08 | 8 | 6 | 2025-05-08 | 2025-06-04 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-09 | 2024-12-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 5808.51 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-09 | 2024-12-09 | 1 | 1 | 2024-12-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-04 | 2023-12-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 792.91 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-04 | 2023-09-29 | Unknown | Unknown | 2023-09-29 | 2023-12-13 | 76 | 54 | 2023-12-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-08 | 2024-05-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7320 | 584.27 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-08 | 2024-05-08 | 1 | 1 | 2024-05-08 | 2024-05-08 | 1 | 1 | 2024-05-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-08 | 2025-08-14 | 464 | 332 | Unknown | Unknown | Unknown | Unknown | 2025-08-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-26 | 2024-04-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7320 | 584.27 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-26 | 2024-04-26 | 1 | 1 | 2024-04-26 | 2024-04-26 | 1 | 1 | 2024-04-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-08 | 2025-09-05 | 486 | 348 | Unknown | Unknown | Unknown | Unknown | 2025-09-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 16.1 | 16.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-01 | 2025-04-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1520.54 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-01 | 2025-04-15 | 15 | 11 | 2025-04-15 | 2025-04-15 | 1 | 1 | 2025-04-15 | 2025-08-12 | 120 | 86 | Unknown | Unknown | Unknown | Unknown | 2025-04-15 | 2025-07-18 | 95 | 69 | Unknown | Unknown | Unknown | Unknown | 2025-07-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-14 | 2025-04-11 | 2025-06-24 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1740.25 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-14 | 2025-04-11 | 29 | 21 | 2025-04-11 | 2025-04-11 | 1 | 1 | 2025-04-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-11 | 2025-06-24 | 75 | 53 | Unknown | Unknown | Unknown | Unknown | 2025-06-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-14 | 2024-11-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 741.96 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-14 | 2024-11-14 | 1 | 1 | 2024-11-14 | 2025-04-29 | 167 | 119 | Unknown | Unknown | Unknown | Unknown | 2024-11-15 | 2024-12-18 | 34 | 24 | 2025-04-29 | 2025-08-04 | 98 | 70 | Unknown | 2025-07-22 | Unknown | Unknown | 2025-08-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-23 | 2024-09-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 9601 | 525.39 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-23 | 2024-09-23 | 1 | 1 | 2024-09-23 | 2024-09-23 | 1 | 1 | 2024-09-23 | 2025-09-05 | 348 | 250 | Unknown | Unknown | Unknown | Unknown | 2024-09-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 81 | 81 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-25 | 2023-09-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 465.36 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-25 | 2023-09-09 | 16 | 11 | 2023-09-09 | 2023-09-09 | 1 | 0 | 2023-09-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-19 | 2025-06-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 381.78 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-19 | 2025-06-19 | 1 | 1 | 2025-06-19 | 2025-06-24 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-07-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | POWAY | N/A | 81.05 | 81.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-24 | 2024-01-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3961 | 163.83 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-24 | 2024-02-08 | 16 | 12 | 2024-02-08 | 2024-04-22 | 75 | 53 | 2024-04-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | VALLEY CENTER | N/A | 295.05 | 295.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-30 | 2025-06-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 865.4 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-30 | 2025-06-19 | 51 | 37 | 2025-06-19 | 2025-06-20 | 2 | 2 | 2025-06-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | ALPINE | COUNTY OF SAN DIEGO-SOUTH of 56 | 50 | 50 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-24 | 2024-01-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 381.45 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-24 | 2024-01-29 | 6 | 4 | 2024-01-29 | 2024-02-02 | 5 | 5 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 96.05 | 96.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-29 | 2025-01-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 695.25 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-29 | 2025-05-22 | 114 | 82 | 2025-05-22 | 2025-06-06 | 16 | 12 | 2025-02-14 | 2025-06-06 | 113 | 81 | Unknown | Unknown | Unknown | Unknown | 2025-06-06 | 2025-07-25 | 50 | 36 | Unknown | Unknown | Unknown | Unknown | 2025-07-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-22 | 2023-12-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 956.46 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-22 | 2023-12-05 | Unknown | Unknown | 2023-12-05 | 2024-03-19 | 106 | 76 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-02 | 2023-10-02 | 2024-03-25 | IOU Designed & Installed | N/A | No | Unknown | 338.2 | -3.07 | Unknown | Unknown | 75.88 | 265.39 | 3981 | 864.19 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-02 | 2023-10-02 | 1 | 1 | 2023-10-02 | 2023-11-09 | 39 | 29 | 2023-11-09 | Unknown | Unknown | Unknown | 2024-02-16 | 2024-02-16 | 1 | 1 | 2023-11-09 | 2024-03-25 | 138 | 98 | Unknown | 2024-03-13 | Unknown | Unknown | 2024-03-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN JUAN CAPISTRANO | N/A | 37 | 37 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-13 | 2025-02-13 | 2025-06-23 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1932.99 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-13 | 2025-02-13 | 1 | 1 | 2025-02-13 | 2025-02-13 | 1 | 1 | 2025-02-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-13 | 2025-06-23 | 131 | 93 | Unknown | Unknown | Unknown | Unknown | 2025-06-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | POWAY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-07 | 2025-05-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1527.43 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-07 | 2025-05-09 | 3 | 3 | 2025-05-09 | 2025-05-21 | 13 | 9 | 2025-05-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 287.05 | 287.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-30 | 2025-02-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1834.15 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-30 | 2025-02-21 | 23 | 17 | 2025-02-21 | 2025-02-21 | 1 | 1 | 2025-02-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-21 | 2025-07-23 | 153 | 109 | Unknown | Unknown | Unknown | Unknown | 2025-07-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2020-02-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-03 | 2023-07-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1110.53 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-03 | 2023-05-31 | Unknown | Unknown | 2023-05-31 | 2023-07-07 | 38 | 28 | 2023-07-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN MARCOS | SAN MARCOS | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-29 | 2025-01-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2875 | 420.18 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-29 | 2025-01-29 | 1 | 1 | 2025-01-29 | 2025-02-07 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | 2025-02-04 | 2025-04-11 | 17 | 13 | 2025-02-07 | 2025-06-17 | 131 | 93 | Unknown | 2025-07-14 | Unknown | Unknown | 2025-07-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ALPINE | N/A | 21.05 | 21.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-31 | 2023-08-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2445.36 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-31 | 2023-05-26 | Unknown | Unknown | 2023-05-26 | 2023-08-16 | 83 | 59 | 2023-08-16 | 2023-08-24 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | 2023-08-16 | Unknown | Unknown | Unknown | Unknown | 2023-10-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LAKESIDE | COUNTY OF SAN DIEGO-SOUTH of 56 | 12.75 | 12.75 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-21 | 2023-06-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1612.84 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-21 | 2023-05-25 | Unknown | Unknown | 2023-05-25 | 2024-09-24 | 489 | 349 | 2023-08-09 | 2023-08-09 | 1 | 1 | 2023-08-10 | 2023-08-21 | 12 | 8 | 2024-09-24 | 2024-10-31 | 38 | 28 | Unknown | 2025-08-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | Lakeside | COUNTY OF SAN DIEGO-SOUTH of 56 | 144 | 144 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-09-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-02-11 | 2023-05-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 12916.49 | Unknown | Unknown | Yes | N/A | N/A | 2022-02-11 | 2023-04-03 | 417 | 297 | 2023-04-03 | 2024-09-05 | 522 | 374 | 2023-09-18 | 2024-05-16 | 55 | 41 | 2023-09-07 | 2024-09-06 | 31 | 23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | 9 | 9 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-08 | 2024-02-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 896.58 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-08 | 2024-02-02 | 26 | 20 | 2024-02-02 | 2024-02-02 | 1 | 1 | 2024-02-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SOUTH LAGUNA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-27 | 2023-01-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 160.32 | Unknown | Unknown | Yes | N/A | N/A | 2023-01-27 | 2023-02-23 | 28 | 20 | 2023-02-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | JAMUL | N/A | 109.05 | 109.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-20 | 2024-02-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1155.28 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-20 | 2023-12-20 | Unknown | Unknown | 2023-12-20 | 2025-06-30 | 559 | 399 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Commercial | N/A | Santee | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-04-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-06 | 2024-12-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 21784.27 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-06 | 2024-12-06 | 1 | 1 | 2024-12-06 | 2025-01-09 | 35 | 25 | Unknown | Unknown | Unknown | Unknown | 2024-12-17 | 2024-12-19 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 16.2 | 16.2 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-07-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-19 | 2024-12-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 72184.42 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-19 | 2024-11-19 | 1 | 1 | 2024-11-19 | 2025-05-15 | 178 | 128 | Unknown | Unknown | Unknown | Unknown | 2025-01-31 | 2025-05-21 | 46 | 32 | 2025-05-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN MARCOS | SAN MARCOS | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-29 | 2025-01-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2895 | 586.8 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-29 | 2025-01-29 | 1 | 1 | 2025-01-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-19 | 2025-02-25 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | Applicant Design | Commercial | N/A | SD 1190-B1 CMR PA17 (E) | SAN DIEGO | 222214 | 222214 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-03-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-20 | 2023-09-20 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 113047 | 29954.26 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-20 | 2024-03-25 | 188 | 134 | 2024-03-25 | 2024-05-28 | 65 | 47 | 2024-04-04 | 2024-05-16 | 43 | 31 | 2024-05-03 | 2024-06-11 | 40 | 28 | 2024-05-28 | Unknown | Unknown | Unknown | Unknown | 2025-06-23 | Unknown | Unknown | 2025-07-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-24 | 2025-04-24 | 2025-05-09 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1096.32 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-24 | 2025-04-24 | 1 | 1 | 2025-04-24 | 2025-04-24 | 1 | 1 | 2025-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-24 | 2025-05-09 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | 2025-05-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-10 | 2024-08-21 | 2024-10-18 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1542.75 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-10 | 2024-08-21 | 43 | 31 | 2024-08-21 | 2024-08-21 | 1 | 1 | 2024-08-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-22 | 2024-10-18 | 58 | 42 | Unknown | Unknown | Unknown | Unknown | 2024-10-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 59.05 | 59.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-28 | 2025-01-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2038.63 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-28 | 2025-01-09 | Unknown | Unknown | 2025-01-09 | 2025-01-28 | 20 | 14 | 2025-01-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-18 | 2024-07-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 27449 | 494.79 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-18 | 2024-09-06 | 51 | 37 | 2024-09-06 | 2024-09-06 | 1 | 1 | 2024-09-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-03 | 2024-05-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3241 | 1726.93 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-03 | 2024-05-03 | 1 | 1 | 2024-05-03 | 2024-05-03 | 1 | 1 | 2024-05-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-11 | 2023-10-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 957.85 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-11 | 2023-06-02 | Unknown | Unknown | 2023-06-02 | 2023-10-24 | 145 | 103 | 2023-10-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | N/A | 142.05 | 142.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-07 | 2024-03-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2062.53 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-07 | 2024-03-07 | 1 | 1 | 2024-03-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-15 | 2024-03-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 757.99 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-15 | 2023-12-28 | Unknown | Unknown | 2023-12-28 | 2024-03-02 | 66 | 47 | 2024-03-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | N/A | 12.6 | 12.6 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-03 | 2025-04-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2485.64 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-03 | 2025-04-28 | 26 | 18 | 2025-04-28 | 2025-05-07 | 10 | 8 | 2025-05-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | 32 | 32 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-03 | 2023-10-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 62428.63 | 22527.49 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-03 | 2023-10-18 | 16 | 12 | 2023-10-18 | 2024-10-03 | 352 | 252 | 2024-01-24 | 2024-02-05 | 13 | 9 | 2024-03-06 | 2024-10-07 | 37 | 27 | 2024-10-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | NATIONAL CITY | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-09 | 2024-08-09 | 2025-06-18 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1532.34 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-09 | 2024-08-09 | 1 | 1 | 2024-08-09 | 2024-08-09 | 1 | 1 | 2024-08-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-09 | 2025-06-18 | 314 | 224 | Unknown | Unknown | Unknown | Unknown | 2025-06-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-07 | 2023-08-04 | 2023-09-08 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 153.83 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-07 | 2023-08-23 | 48 | 34 | 2023-08-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-23 | 2023-09-08 | 17 | 13 | Unknown | 2023-11-28 | Unknown | Unknown | 2023-09-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ALPINE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-03 | 2025-03-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 3343.75 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-03 | 2025-02-18 | Unknown | Unknown | 2025-02-18 | 2025-03-04 | 15 | 11 | 2025-03-04 | 2025-03-12 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | 2025-03-12 | Unknown | Unknown | Unknown | Unknown | 2025-03-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | POWAY | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-20 | 2024-03-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 869.73 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-20 | 2023-12-05 | Unknown | Unknown | 2023-12-05 | 2024-03-21 | 108 | 78 | 2024-03-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-21 | 2025-07-01 | 468 | 334 | Unknown | Unknown | Unknown | Unknown | 2025-07-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-09 | 2025-05-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2038.11 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-09 | 2025-05-16 | 8 | 6 | 2025-05-16 | 2025-05-21 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CORONADO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-02 | 2024-05-02 | 2025-03-19 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2318.23 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-02 | 2024-02-23 | Unknown | Unknown | 2024-02-23 | 2025-01-29 | 342 | 244 | 2025-01-29 | 2025-02-19 | 6 | 2 | Unknown | Unknown | Unknown | Unknown | 2025-01-29 | 2025-03-19 | 50 | 36 | Unknown | 2025-03-06 | Unknown | Unknown | 2025-03-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | BOULEVARD | N/A | 34.05 | 34.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-19 | 2024-06-20 | 2024-07-02 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1495.36 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-19 | 2024-05-10 | Unknown | Unknown | 2024-05-10 | 2024-06-25 | 47 | 33 | 2024-06-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-25 | 2024-07-02 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2024-07-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LA MESA | N/A | 61 | 61 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-20 | 2023-12-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3885 | 98.28 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-20 | 2024-01-02 | 14 | 10 | 2024-01-02 | 2024-01-02 | 1 | 1 | 2024-01-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | DANA POINT | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-05-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-31 | 2023-07-31 | Unknown | IOU Designed & Installed | N/A | No | Unknown | 25314.69 | 544.32 | Unknown | 83.02 | 2062.9 | 22624.45 | 3981 | 420.58 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-31 | 2024-01-19 | 173 | 125 | 2024-01-19 | 2024-01-19 | 1 | 1 | 2024-01-19 | 2024-12-24 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-01-19 | Unknown | Unknown | Unknown | Unknown | 2024-12-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-04 | 2025-01-04 | 2025-03-11 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1084.05 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-04 | 2025-01-03 | Unknown | Unknown | 2025-01-03 | 2025-01-04 | 2 | 1 | 2025-01-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-04 | 2025-03-11 | 67 | 47 | Unknown | Unknown | Unknown | Unknown | 2025-03-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | CARDIFF | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-21 | 2025-05-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1336.09 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-21 | 2025-05-14 | 24 | 18 | 2025-05-14 | 2025-05-14 | 1 | 1 | 2025-05-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | 96.05 | 96.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-04 | 2024-11-06 | 2024-12-18 | IOU Designed & Installed | N/A | No | Unknown | 1941.73 | 502.72 | Unknown | 33.99 | 60.03 | 1344.99 | 3981 | 3481.25 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-04 | 2024-11-26 | 23 | 17 | 2024-11-26 | 2024-11-26 | 1 | 1 | 2024-11-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-27 | 2024-12-18 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | 2024-12-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 153 | 153 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-28 | 2023-12-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7962 | 2168.42 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-28 | 2023-12-28 | 1 | 1 | 2023-12-28 | 2024-01-12 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | 2023-12-29 | 2024-01-08 | 11 | 7 | 2024-01-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 68 | 68 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-17 | 2023-01-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 98.41 | Unknown | Unknown | Yes | N/A | N/A | 2023-01-17 | 2023-02-15 | 30 | 22 | 2023-02-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-11 | 2024-11-11 | 2024-12-16 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1598.54 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-11 | 2024-11-11 | 1 | 1 | 2024-11-11 | 2024-11-11 | 1 | 1 | 2024-11-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-11 | 2024-12-16 | 36 | 26 | Unknown | Unknown | Unknown | Unknown | 2024-12-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SANTEE | N/A | 48.05 | 48.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-21 | 2025-01-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1656 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-21 | 2025-01-08 | Unknown | Unknown | 2025-01-08 | 2025-01-22 | 15 | 11 | 2025-01-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | CARLSBAD | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-06 | 2024-06-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1533.09 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-06 | 2024-06-11 | 6 | 4 | 2024-06-11 | 2024-06-11 | 1 | 1 | 2024-06-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 136 | 136 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-19 | 2023-12-19 | 2024-12-02 | IOU Designed & Installed | N/A | No | Unknown | 51.75 | 0 | Unknown | Unknown | 25.43 | 26.32 | 3981 | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2023-12-19 | 2023-10-31 | Unknown | Unknown | 2023-10-31 | 2023-12-19 | 50 | 36 | 2023-12-19 | 2024-03-06 | 79 | 57 | Unknown | Unknown | Unknown | Unknown | 2025-02-19 | 2024-12-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-06 | 2025-03-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1131.8 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-06 | 2025-02-13 | 8 | 6 | 2025-02-13 | 2025-03-13 | 29 | 21 | 2025-03-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | EL CAJON | EL CAJON | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-23 | 2022-06-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 479.08 | Unknown | Unknown | Yes | N/A | N/A | 2022-06-23 | 2023-02-21 | 244 | 174 | 2023-02-21 | 2023-03-17 | 25 | 19 | Unknown | Unknown | Unknown | Unknown | 2023-02-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-10 | 2024-09-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 192.95 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-10 | 2024-08-19 | Unknown | Unknown | 2024-08-19 | 2024-09-10 | 23 | 17 | 2024-09-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 70.05 | 70.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-10 | 2024-10-10 | 2025-06-17 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2088 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-10 | 2024-06-17 | Unknown | Unknown | 2024-06-17 | 2024-10-10 | 116 | 84 | 2024-10-10 | 2025-06-05 | 239 | 171 | Unknown | Unknown | Unknown | Unknown | 2025-06-05 | 2025-06-17 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2025-06-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2025-04-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-27 | 2025-02-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 52.44 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-27 | 2025-04-02 | 35 | 25 | 2025-04-02 | 2025-04-03 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2025-03-03 | 2025-03-24 | 22 | 16 | 2025-04-03 | Unknown | Unknown | Unknown | Unknown | 2025-08-06 | Unknown | Unknown | 2025-08-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-11 | 2024-06-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 409671 | 21018.22 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-11 | 2024-06-11 | 1 | 1 | 2024-06-11 | 2024-07-10 | 30 | 22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | RAMONA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-04 | 2025-06-04 | 2025-06-18 | IOU Designed & Installed | N/A | No | Unknown | 4.5 | 0 | Unknown | Unknown | Unknown | 4.5 | 3981 | 118.25 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-04 | 2025-05-20 | Unknown | Unknown | 2025-05-20 | 2025-06-16 | 28 | 20 | 2025-06-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-16 | 2025-06-18 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2025-06-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | JAMUL | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-06 | 2024-08-06 | 2024-10-10 | IOU Designed & Installed | N/A | No | Unknown | 5031.43 | 1349.5 | Unknown | 349.56 | 189.71 | 3142.66 | 0 | 1506.92 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-06 | 2024-06-21 | Unknown | Unknown | 2024-06-21 | 2024-08-06 | 47 | 33 | 2024-08-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-06 | 2024-10-10 | 66 | 48 | Unknown | Unknown | Unknown | Unknown | 2024-10-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | 95.05 | 95.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-17 | 2023-08-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 765.43 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-17 | 2023-06-07 | Unknown | Unknown | 2023-06-07 | 2023-08-18 | 73 | 53 | 2023-08-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-11 | 2024-05-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 31848 | 1162.16 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-11 | 2024-11-18 | 344 | 246 | 2024-11-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-16 | 2025-01-15 | 31 | 23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | DANA POINT | N/A | 17.4 | 17.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-01 | 2024-05-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2241.25 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-01 | 2024-05-20 | 20 | 14 | 2024-05-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 29.35 | 29.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-14 | 2025-03-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1311.09 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-14 | 2025-04-30 | 48 | 34 | 2025-04-30 | 2025-05-19 | 20 | 14 | 2025-05-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-11 | 2024-07-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2120.56 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-11 | 2024-07-11 | 31 | 23 | 2024-07-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CARLSBAD | CARLSBAD | 184 | 184 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-23 | 2025-02-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 15087.39 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-23 | 2024-08-23 | 1 | 1 | 2024-08-23 | Unknown | Unknown | Unknown | 2025-04-07 | 2025-04-08 | 2 | 2 | 2025-04-08 | 2025-08-06 | 117 | 82 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | JAMUL | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-09 | 2025-01-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | 317.84 | 77.16 | Unknown | Unknown | Unknown | 240.68 | 0 | 1853.9 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-09 | 2025-01-09 | 1 | 1 | 2025-01-09 | 2025-01-22 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-22 | 2025-04-01 | 70 | 50 | Unknown | 2025-03-26 | Unknown | Unknown | 2025-07-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | CORONADO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-13 | 2024-09-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2860.96 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-13 | 2024-10-28 | 46 | 32 | 2024-10-28 | 2025-01-08 | 73 | 53 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-07-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | MOUNT LAGUNA | COUNTY OF SAN DIEGO-SOUTH of 56 | 126 | 126 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-06 | 2025-01-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2047.97 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-06 | 2025-01-15 | 10 | 8 | 2025-01-15 | 2025-01-16 | 2 | 2 | 2025-01-16 | 2025-01-27 | 5 | 3 | 2025-01-17 | 2025-01-31 | 12 | 10 | 2025-01-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-21 | 2023-06-21 | 2023-09-06 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 28244.59 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-21 | 2023-08-08 | 49 | 35 | 2023-08-08 | 2023-08-11 | 4 | 4 | 2023-08-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-11 | 2023-09-06 | 27 | 19 | Unknown | Unknown | Unknown | Unknown | 2023-09-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-04 | 2023-10-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3662 | 265.49 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-04 | 2023-10-24 | 21 | 15 | 2023-10-24 | 2023-10-31 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-13 | 2024-11-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1590.73 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-13 | 2024-11-13 | 1 | 1 | 2024-11-13 | 2024-11-25 | 13 | 9 | 2024-11-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-02-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-11 | 2024-03-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 15764 | 823.07 | Unknown | Unknown | Yes | N/A | N/A | 2022-04-11 | 2023-06-27 | 443 | 317 | 2023-06-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 16 | 16 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-12 | 2025-04-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1232.19 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-12 | 2025-04-02 | 22 | 16 | 2025-04-02 | 2025-04-02 | 1 | 1 | 2025-03-12 | 2025-04-02 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | 2025-04-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-04 | 2025-04-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1315.73 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-04 | 2025-04-16 | 13 | 9 | 2025-04-16 | 2025-04-16 | 1 | 1 | 2025-04-16 | 2025-05-06 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | 2025-05-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Commercial | Underserved Community | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2026-03-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-04 | 2024-09-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 54899 | 3021.2 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-04 | 2024-09-18 | 15 | 11 | 2024-09-18 | 2025-06-10 | 266 | 190 | 2025-06-03 | 2025-06-04 | 2 | 2 | 2024-09-20 | 2024-10-22 | 33 | 23 | 2025-07-10 | Unknown | Unknown | Unknown | 2025-07-10 | 2025-07-31 | 22 | 16 | 2025-08-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-30 | 2024-05-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1709.92 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-30 | 2024-05-30 | 1 | 1 | 2024-05-30 | 2024-05-30 | 1 | 1 | 2024-05-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | CARLSBAD | N/A | 68 | 68 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-28 | 2025-02-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7962 | 1493.31 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-28 | 2025-03-15 | 16 | 11 | 2025-03-15 | 2025-05-06 | 53 | 37 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 145.4 | 145.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-17 | 2024-06-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2513.49 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-17 | 2024-06-17 | 1 | 1 | 2024-06-17 | 2024-06-17 | 1 | 1 | 2024-06-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-27 | 2025-02-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2216.09 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-27 | 2025-01-17 | Unknown | Unknown | 2025-01-17 | 2025-02-27 | 42 | 30 | 2025-02-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SOUTH LAGUNA | N/A | 1309.05 | 1309.05 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2025-07-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-21 | 2024-01-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 427.74 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-21 | 2024-01-12 | 23 | 17 | 2024-01-12 | 2024-01-12 | 1 | 1 | 2024-01-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | WARNER SPRINGS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-17 | 2024-04-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 491.09 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-17 | 2024-04-17 | 1 | 1 | 2024-04-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-23 | 2025-02-06 | 2025-05-07 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2264.17 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-23 | 2025-02-06 | 15 | 11 | 2025-02-06 | 2025-02-14 | 9 | 7 | 2025-02-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-13 | 2025-05-07 | 84 | 60 | Unknown | 2025-03-25 | Unknown | Unknown | 2025-05-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LAKESIDE | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-13 | 2024-05-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2069.18 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-13 | 2024-05-08 | 148 | 106 | 2024-05-08 | 2024-07-24 | 78 | 56 | Unknown | Unknown | Unknown | Unknown | 2024-05-16 | 2024-05-30 | 15 | 11 | 2024-07-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | N/A | 65.56 | 65.56 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-04 | 2025-03-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1448.41 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-04 | 2025-02-20 | Unknown | Unknown | 2025-02-20 | 2025-03-06 | 15 | 11 | 2025-03-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-25 | 2024-07-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1059.29 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-25 | 2024-08-19 | 26 | 18 | 2024-08-19 | 2024-08-20 | 2 | 2 | 2024-08-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | MISSION VIEJO | N/A | 200 | 200 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-30 | 2025-04-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2495.32 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-30 | 2025-04-29 | Unknown | Unknown | 2025-04-29 | 2025-05-22 | 24 | 18 | 2025-05-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | N/A | 623.05 | 623.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-24 | 2025-03-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1366.37 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-24 | 2025-03-24 | 1 | 1 | 2025-03-24 | 2025-03-25 | 2 | 2 | 2025-03-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 53.05 | 53.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-10 | 2025-02-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1253.54 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-10 | 2025-01-27 | 49 | 35 | 2025-01-27 | 2025-02-14 | 19 | 15 | 2025-02-14 | 2025-04-21 | 67 | 47 | Unknown | Unknown | Unknown | Unknown | 2025-04-21 | 2025-07-08 | 79 | 57 | Unknown | Unknown | Unknown | Unknown | 2025-07-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-12 | 2025-02-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1449.75 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-12 | 2025-02-03 | Unknown | Unknown | 2025-02-03 | 2025-02-21 | 19 | 15 | 2025-02-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-22 | 2024-01-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 854.21 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-22 | 2023-12-04 | Unknown | Unknown | 2023-12-04 | 2024-01-22 | 50 | 36 | 2024-01-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 2.7 | 2.7 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-30 | 2024-12-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1808.19 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-30 | 2024-12-11 | 73 | 53 | 2024-12-11 | 2024-12-12 | 2 | 2 | 2024-12-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | Applicant Design | Residential | Underserved Community | CB 1106-E5 hope apt EV (E) | CARLSBAD | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-26 | 2023-10-26 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 1274405 | 82209.62 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-26 | 2024-04-09 | 167 | 119 | 2024-04-09 | 2025-06-02 | 420 | 300 | 2024-04-23 | 2025-01-20 | 43 | 31 | 2024-05-09 | 2025-03-06 | 47 | 31 | 2025-06-02 | Unknown | Unknown | Unknown | 2025-06-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-19 | 2023-12-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 28804 | 552.92 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-19 | 2023-12-19 | 1 | 1 | 2023-12-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | Applicant Design | Residential | Underserved Community | San Diego | San Diego | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-24 | 2024-07-24 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 17667.47 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-24 | 2025-02-24 | 216 | 154 | 2025-02-24 | 2025-07-01 | 128 | 92 | 2025-01-07 | 2025-04-04 | 66 | 48 | 2025-01-06 | 2025-07-22 | 45 | 33 | 2025-07-01 | Unknown | Unknown | Unknown | 2025-07-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LEMON GROVE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-03 | 2024-12-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1534.24 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-03 | 2024-11-19 | Unknown | Unknown | 2024-11-19 | 2024-12-03 | 15 | 11 | 2024-12-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | 7 | 7 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-03 | 2025-03-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1282.52 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-03 | 2025-03-06 | 4 | 4 | 2025-03-06 | 2025-03-06 | 1 | 1 | 2025-03-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-06 | 2025-07-09 | 126 | 90 | Unknown | 2025-07-01 | Unknown | Unknown | 2025-07-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | Applicant Design | Commercial | Underserved Community | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-07 | 2024-03-07 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 634613 | 67615.32 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-07 | 2024-09-16 | 194 | 138 | 2024-09-16 | 2025-02-18 | 156 | 112 | 2024-09-23 | 2024-10-28 | 36 | 26 | 2024-10-28 | 2025-07-09 | 186 | 134 | 2025-02-18 | Unknown | Unknown | Unknown | 2025-05-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | 81.05 | 81.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-27 | 2024-09-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1636.48 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-27 | 2024-05-08 | Unknown | Unknown | 2024-05-08 | 2024-09-30 | 146 | 104 | 2024-09-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Residential | Underserved Community | OC 1107-A2 | OCEANSIDE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-31 | 2024-05-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 56669 | 33735.98 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-31 | 2024-02-16 | 201 | 145 | 2024-02-16 | 2024-11-06 | 265 | 189 | 2024-06-24 | 2024-10-09 | 16 | 12 | 2024-06-26 | 2024-11-16 | 37 | 26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | OH | IOU Design | Residential | N/A | Jamul | N/A | 109.05 | 109.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-20 | 2024-02-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2694 | 9957.42 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-20 | 2023-12-20 | Unknown | Unknown | 2023-12-20 | 2025-06-30 | 559 | 399 | Unknown | Unknown | Unknown | Unknown | 2025-07-02 | 2025-07-10 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | EL CAJON | EL CAJON | 600 | 600 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-03-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-28 | 2025-06-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1252.34 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-28 | 2025-06-19 | 112 | 80 | 2025-06-19 | 2025-06-20 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2025-06-19 | 2025-06-25 | 7 | 5 | 2025-06-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | OCEANSIDE | N/A | 108 | 108 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-29 | 2024-01-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 799 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-29 | 2023-09-06 | Unknown | Unknown | 2023-09-06 | 2024-01-25 | 142 | 102 | 2024-01-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Residential | N/A | Rancho Mission Viejo | N/A | 3254 | 3254 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-10-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-27 | 2024-09-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 102472.32 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-27 | 2024-07-01 | 5 | 3 | 2024-07-01 | 2025-04-18 | 292 | 210 | 2024-09-19 | 2025-07-15 | 45 | 33 | 2025-01-29 | 2025-05-13 | 18 | 14 | 2025-04-18 | Unknown | Unknown | Unknown | 2025-04-18 | 2025-07-28 | 102 | 72 | 2025-08-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-25 | 2023-08-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1066.56 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-25 | 2023-08-21 | 28 | 20 | 2023-08-21 | 2023-08-24 | 4 | 4 | 2023-08-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 100 | 100 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-02 | 2024-04-03 | 2024-04-12 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1072.05 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-02 | 2024-01-23 | Unknown | Unknown | 2024-01-23 | 2024-04-03 | 72 | 52 | 2024-04-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-03 | 2024-04-12 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | 2024-04-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-02 | 2025-01-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1390.98 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-02 | 2025-01-31 | 30 | 22 | 2025-01-31 | 2025-02-04 | 5 | 3 | 2025-02-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | Chula Vista | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-21 | 2025-02-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 67270 | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2025-02-21 | 2025-01-08 | Unknown | Unknown | 2025-01-08 | 2025-03-25 | 77 | 55 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SANTEE | COUNTY OF SAN DIEGO-SOUTH of 56, SAN DIEGO | 33 | 33 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-09 | 2023-08-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 20184 | 1653.3 | Unknown | Unknown | Yes | N/A | N/A | 2022-12-09 | 2023-06-01 | 175 | 125 | 2023-06-01 | 2023-10-17 | 139 | 99 | Unknown | Unknown | Unknown | Unknown | 2023-09-06 | 2025-07-09 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-09 | 2023-10-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 839.71 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-09 | 2023-08-17 | Unknown | Unknown | 2023-08-17 | 2023-10-09 | 54 | 38 | 2023-10-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 46 | 46 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-09 | 2024-02-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1105.93 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-09 | 2024-02-09 | 32 | 24 | 2024-02-09 | 2024-02-09 | 1 | 1 | 2024-02-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-22 | 2024-10-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 14210 | 506.13 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-22 | 2024-09-20 | Unknown | Unknown | 2024-09-20 | 2025-03-14 | 176 | 126 | 2025-03-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Residential | N/A | RANCHO MISSION VIEJO | N/A | 2838.8 | 2838.8 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-10-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-27 | 2024-08-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 144502.41 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-27 | 2024-07-01 | 5 | 3 | 2024-07-01 | 2025-03-25 | 268 | 192 | 2024-08-27 | 2025-04-22 | 202 | 142 | 2025-03-24 | 2025-04-19 | 27 | 20 | 2025-04-17 | Unknown | Unknown | Unknown | 2025-04-17 | 2025-04-17 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2021-09-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-30 | 2023-06-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1063.82 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-30 | 2023-02-16 | Unknown | Unknown | 2023-02-16 | 2023-08-31 | 197 | 141 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 30.1 | 30.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-21 | 2024-10-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1786.8 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-21 | 2024-10-28 | 8 | 6 | 2024-10-28 | 2024-10-28 | 1 | 1 | 2024-10-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 14.1 | 14.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-23 | 2025-05-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1316.83 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-23 | 2025-04-29 | 7 | 5 | 2025-04-29 | 2025-05-12 | 14 | 10 | 2025-05-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SOLANA BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-17 | 2023-06-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 646.79 | Unknown | Unknown | Yes | N/A | N/A | 2023-05-17 | 2023-06-05 | 20 | 14 | 2023-06-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 25.05 | 25.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-24 | 2025-04-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1434.91 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-24 | 2025-04-24 | 1 | 1 | 2025-04-24 | 2025-04-24 | 1 | 1 | 2025-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-11 | 2025-01-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2233.57 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-11 | 2024-04-18 | Unknown | Unknown | 2024-04-18 | 2025-01-11 | 269 | 192 | 2025-01-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 7 | 7 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-06 | 2025-05-06 | 2025-06-30 | IOU Designed & Installed | N/A | No | Unknown | 733.05 | 0 | Unknown | Unknown | 7.67 | 725.38 | 3981 | 876.14 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-06 | 2025-05-06 | 1 | 1 | 2025-05-06 | 2025-05-28 | 23 | 17 | 2025-05-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-28 | 2025-06-30 | 34 | 24 | Unknown | 2025-06-03 | Unknown | Unknown | 2025-06-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-14 | 2023-12-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 826.31 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-14 | 2023-11-17 | Unknown | Unknown | 2023-11-17 | 2024-01-11 | 56 | 40 | 2024-01-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-09 | 2024-08-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2906.94 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-09 | 2024-09-11 | 34 | 24 | 2024-09-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | CHULA VISTA | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-25 | 2024-06-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2797.47 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-25 | 2024-06-25 | 1 | 1 | 2024-06-25 | 2024-07-10 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-10 | 2024-05-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 129.05 | 129.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-30 | 2023-11-02 | 2023-11-14 | IOU Designed & Installed | N/A | No | Unknown | 3000.34 | 2008.49 | Unknown | Unknown | Unknown | 991.85 | 3981 | 481.24 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-30 | 2023-08-07 | Unknown | Unknown | 2023-08-07 | 2023-11-02 | 88 | 64 | 2023-11-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-02 | 2023-11-14 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2023-11-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | 92 | 92 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-01 | 2023-02-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3885 | 541.82 | Unknown | Unknown | Yes | N/A | N/A | 2023-02-01 | 2023-02-06 | 6 | 4 | 2023-02-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | EL CAJON | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-04 | 2025-02-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1573.49 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-04 | 2025-03-05 | 30 | 22 | 2025-03-05 | 2025-07-23 | 141 | 101 | Unknown | Unknown | Unknown | Unknown | 2025-03-05 | 2025-04-08 | 35 | 25 | 2025-07-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-10 | 2025-01-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 209.58 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-10 | 2025-01-03 | Unknown | Unknown | 2025-01-03 | 2025-01-10 | 8 | 6 | 2025-01-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community,Tribal Community | PINE VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-24 | 2023-10-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 13067 | 2005.69 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-24 | 2023-10-24 | 1 | 1 | 2023-10-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | RAMONA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-25 | 2024-08-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 5468.62 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-25 | 2024-12-11 | 140 | 100 | 2024-12-11 | 2024-12-19 | 9 | 7 | 2024-12-19 | 2025-06-20 | 184 | 132 | Unknown | Unknown | Unknown | Unknown | 2025-06-23 | 2025-08-20 | 59 | 43 | Unknown | 2025-08-19 | Unknown | Unknown | 2025-08-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-08 | 2024-08-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1908.5 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-08 | 2024-07-29 | Unknown | Unknown | 2024-07-29 | 2024-08-08 | 11 | 9 | 2024-08-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | LAS FLORES | N/A | 13.05 | 13.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-08 | 2024-03-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 95.69 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-08 | 2024-05-22 | 76 | 54 | 2024-05-22 | 2024-05-22 | 1 | 1 | 2024-05-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | Oceanside | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-23 | 2025-01-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 29095.7 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-23 | 2024-06-14 | Unknown | Unknown | 2024-06-14 | 2025-03-19 | 279 | 199 | Unknown | Unknown | Unknown | Unknown | 2025-03-12 | 2025-03-21 | 10 | 8 | 2025-03-19 | Unknown | Unknown | Unknown | 2025-05-22 | 2025-07-22 | 62 | 44 | 2025-07-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 12 | 12 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-11 | 2024-06-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1530.81 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-11 | 2024-04-08 | Unknown | Unknown | 2024-04-08 | 2024-06-12 | 66 | 48 | 2024-06-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 8 | 8 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-13 | 2023-09-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | 6120.02 | 1196.96 | Unknown | 592.05 | 34.14 | 4296.87 | 3885 | 678.6 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-13 | 2023-09-28 | 16 | 12 | 2023-09-28 | 2023-09-28 | 1 | 1 | 2023-09-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-20 | Unknown | Unknown | Unknown | Unknown | 2025-02-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SOLANA BEACH | N/A | 25.05 | 25.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-03 | 2024-12-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1909.35 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-03 | 2024-12-19 | 17 | 13 | 2024-12-19 | 2024-12-19 | 1 | 1 | 2024-12-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | ESCONDIDO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2024-09-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-29 | 2024-10-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3753.77 | 719.62 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-29 | 2024-10-29 | 1 | 1 | 2024-10-29 | 2025-05-06 | 190 | 136 | Unknown | Unknown | Unknown | Unknown | 2025-02-25 | 2025-03-13 | 17 | 13 | 2025-05-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-12 | 2024-11-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1266.9 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-12 | 2024-11-26 | 15 | 11 | 2024-11-26 | 2024-12-06 | 11 | 9 | 2024-12-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-07 | 2023-08-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 642.1 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-07 | 2023-05-11 | Unknown | Unknown | 2023-05-11 | 2023-08-18 | 100 | 72 | 2023-08-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | COUNTY OF SAN DIEGO-SOUTH of 56, SAN DIEGO | 1161.45 | 1161.45 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2025-09-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-29 | 2025-02-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 12422.84 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-29 | 2025-02-03 | 6 | 4 | 2025-02-03 | 2025-05-02 | 89 | 65 | Unknown | Unknown | Unknown | Unknown | 2025-04-16 | 2025-05-12 | 24 | 16 | 2025-05-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 70 | 70 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-28 | 2025-01-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7962 | 1932.99 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-28 | 2025-01-21 | Unknown | Unknown | 2025-01-21 | 2025-01-28 | 8 | 6 | 2025-01-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-24 | 2025-02-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3017.52 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-24 | 2025-02-24 | 1 | 1 | 2025-02-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | CARLSBAD | N/A | 20 | 20 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-01 | 2023-12-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3661.75 | 441.21 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-01 | 2024-03-01 | 92 | 66 | 2024-03-01 | 2024-03-01 | 1 | 1 | 2024-03-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 48 | 48 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-27 | 2025-04-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1952.78 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-27 | 2025-02-24 | Unknown | Unknown | 2025-02-24 | 2025-04-10 | 46 | 34 | 2025-04-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-10 | 2025-07-17 | 99 | 71 | Unknown | Unknown | Unknown | Unknown | 2025-07-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-25 | 2025-02-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 14748 | 1760.51 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-25 | 2025-02-25 | 1 | 1 | 2025-02-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-14 | 2024-10-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 19202 | 525.39 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-14 | 2024-07-15 | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | N/A | 88 | 88 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-11 | 2025-03-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 833.99 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-11 | 2025-03-05 | Unknown | Unknown | 2025-03-05 | 2025-03-12 | 8 | 6 | 2025-03-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2021-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-09 | 2025-05-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3195.75 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-09 | 2025-05-14 | 6 | 4 | 2025-05-14 | 2025-06-02 | 20 | 14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-11 | 2025-03-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1481.79 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-11 | 2025-03-25 | 15 | 11 | 2025-03-25 | 2025-03-26 | 2 | 2 | 2025-03-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-26 | 2023-09-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 343.9 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-26 | 2024-01-04 | 101 | 73 | 2024-01-04 | 2024-01-08 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-27 | 2024-09-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2617.85 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-27 | 2024-09-27 | 1 | 1 | 2024-09-27 | 2024-10-11 | 15 | 11 | 2024-10-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | VALLEY CENTER | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-14 | 2025-04-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2218 | 1200.53 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-14 | 2025-04-14 | 1 | 1 | 2025-04-14 | 2025-04-18 | 5 | 5 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-18 | 2025-06-30 | 74 | 52 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | WARNER SPRINGS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-10 | 2025-03-10 | 2025-03-20 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1684.42 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-10 | 2025-03-07 | Unknown | Unknown | 2025-03-07 | 2025-03-10 | 4 | 2 | 2025-03-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-10 | 2025-03-20 | 11 | 9 | Unknown | Unknown | Unknown | Unknown | 2025-03-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-24 | 2025-04-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1074.29 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-24 | 2025-06-03 | 41 | 29 | 2025-06-03 | 2025-06-05 | 3 | 3 | 2025-06-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-20 | 2024-05-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1604.92 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-20 | 2024-04-11 | Unknown | Unknown | 2024-04-11 | 2024-05-24 | 44 | 32 | 2024-05-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SD 1168-J3 ADU | N/A | 312 | 312 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-30 | 2024-09-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 8527.61 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-30 | 2024-07-18 | Unknown | Unknown | 2024-07-18 | 2024-12-18 | 154 | 110 | Unknown | Unknown | Unknown | Unknown | 2024-12-18 | 2024-12-19 | 2 | 2 | 2024-12-18 | Unknown | Unknown | Unknown | 2025-01-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | NATIONAL CITY | COUNTY OF SAN DIEGO-SOUTH of 56, NATIONAL CITY | 13.05 | 13.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-07 | 2025-01-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1899.5 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-07 | 2025-01-26 | 20 | 14 | 2025-01-26 | 2025-01-30 | 5 | 4 | 2025-01-30 | 2025-03-13 | 7 | 5 | 2025-01-30 | 2025-07-29 | 51 | 36 | 2025-01-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-12-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-07 | 2023-12-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 595.89 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-07 | 2023-12-05 | 121 | 87 | 2023-12-05 | 2023-12-20 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | 2023-12-08 | 2023-12-19 | 12 | 8 | 2023-12-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | NATIONAL CITY | 53.05 | 53.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-25 | 2024-04-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 959.38 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-25 | 2024-03-25 | 1 | 1 | 2024-03-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-09 | 2024-07-03 | 86 | 62 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | VALLEY CENTER | N/A | 74.05 | 74.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-15 | 2023-06-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 793.12 | Unknown | Unknown | Yes | N/A | N/A | 2023-05-15 | 2023-06-11 | 28 | 20 | 2023-06-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 1685 | 1685 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2023-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-13 | 2023-02-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 429948 | 23370.21 | Unknown | Unknown | Yes | N/A | N/A | 2023-02-13 | 2023-02-13 | 1 | 1 | 2023-02-13 | 2023-03-02 | 18 | 14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-02 | 2025-08-20 | 903 | 645 | Unknown | 2025-08-04 | Unknown | Unknown | 2025-08-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | 230 | 230 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-07 | 2024-09-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 25925 | 984.02 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-07 | 2024-09-27 | 52 | 38 | 2024-09-27 | Unknown | Unknown | Unknown | 2024-09-27 | 2024-09-30 | 4 | 2 | 2024-09-26 | 2024-10-25 | 28 | 22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 68.05 | 68.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-20 | 2025-02-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1626.68 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-20 | 2024-11-07 | Unknown | Unknown | 2024-11-07 | 2025-02-25 | 111 | 79 | 2025-02-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-06 | 2025-05-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 4868.43 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-06 | 2025-05-06 | 1 | 1 | 2025-05-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-11 | 2024-11-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1564.78 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-11 | 2024-10-29 | Unknown | Unknown | 2024-10-29 | 2024-11-12 | 15 | 11 | 2024-11-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | OCEANSIDE | N/A | 86 | 86 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-03 | 2025-04-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1294.46 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-03 | 2025-04-14 | 43 | 31 | 2025-04-14 | 2025-04-14 | 1 | 1 | 2025-04-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-14 | 2025-07-31 | 109 | 79 | Unknown | 2025-06-24 | Unknown | Unknown | 2025-07-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-25 | 2023-05-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 53981 | 554.66 | Unknown | Unknown | Yes | N/A | N/A | 2023-05-25 | 2023-06-14 | 21 | 15 | 2023-06-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-02 | 2025-06-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 1656 | 576.07 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-02 | 2025-05-12 | Unknown | Unknown | 2025-05-12 | 2025-06-04 | 24 | 18 | 2025-06-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-02 | 2025-07-01 | 30 | 22 | Unknown | 2025-07-01 | Unknown | Unknown | 2025-07-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | LAKESIDE | N/A | 47 | 47 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-05-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-10 | 2023-05-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3107 | 869.36 | Unknown | Unknown | Yes | N/A | N/A | 2023-05-10 | 2023-05-22 | 13 | 9 | 2023-05-22 | 2023-09-20 | 122 | 88 | 2023-05-23 | 2023-09-11 | 112 | 80 | Unknown | Unknown | Unknown | Unknown | 2023-09-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-22 | 2024-02-23 | 2024-03-04 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 817.87 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-22 | 2024-01-29 | Unknown | Unknown | 2024-01-29 | 2024-02-23 | 26 | 20 | 2024-02-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-23 | 2024-03-04 | 11 | 7 | Unknown | Unknown | Unknown | Unknown | 2024-03-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-28 | 2023-11-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 876.56 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-28 | 2023-11-28 | 1 | 1 | 2023-11-28 | 2023-11-28 | 1 | 1 | 2023-11-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | BONSALL | N/A | 106.05 | 106.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-29 | 2025-01-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2577.54 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-29 | 2024-12-19 | Unknown | Unknown | 2024-12-19 | 2025-01-29 | 42 | 30 | 2025-01-29 | 2025-02-24 | 27 | 19 | Unknown | Unknown | Unknown | Unknown | 2025-02-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 9.05 | 9.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-07 | 2025-05-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 842.41 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-07 | 2025-04-24 | Unknown | Unknown | 2025-04-24 | 2025-04-24 | 1 | 1 | 2025-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-30 | 2025-07-29 | 61 | 43 | Unknown | 2025-07-08 | Unknown | Unknown | 2025-07-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | DULZURA | N/A | 23 | 23 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-12 |  | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2240.53 | Unknown | Unknown | Yes | N/A | N/A | 2023-05-12 | 2023-05-12 | 1 | 1 | 2023-05-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-12 | Unknown | Unknown | Unknown | Unknown | 2023-06-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-01 | 2024-10-17 | 2024-10-23 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3569.19 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-01 | 2024-09-23 | Unknown | Unknown | 2024-09-23 | 2024-10-17 | 25 | 19 | 2024-10-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-17 | 2024-10-23 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2024-10-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | Applicant Design | Commercial | Underserved Community | Vista | VISTA | 440 | 440 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-09 | 2023-08-09 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 290490 | 60773.63 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-09 | 2023-11-08 | 92 | 66 | 2023-11-08 | 2025-05-14 | 554 | 396 | 2023-12-04 | 2025-03-28 | 434 | 312 | 2023-10-06 | 2025-06-02 | 220 | 155 | 2025-05-14 | Unknown | Unknown | Unknown | 2025-06-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-10 | 2023-02-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 691.94 | Unknown | Unknown | Yes | N/A | N/A | 2023-02-10 | 2023-02-23 | 14 | 10 | 2023-02-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | CHULA VISTA | 115.05 | 115.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-05 | 2024-10-17 | 2025-06-25 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 10934.67 | 31166.88 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-05 | 2025-01-09 | 127 | 91 | 2025-01-09 | 2025-04-03 | 85 | 61 | Unknown | Unknown | Unknown | Unknown | 2025-04-22 | 2025-05-16 | 25 | 19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-05 | 2025-06-05 | 2025-06-17 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1053.71 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-05 | 2025-05-15 | Unknown | Unknown | 2025-05-15 | 2025-06-05 | 22 | 16 | 2025-06-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-05 | 2025-06-17 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2025-06-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | RAMONA | N/A | 81.45 | 81.45 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-05 | 2024-08-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7895 | 8735.28 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-05 | 2024-08-26 | 175 | 125 | 2024-08-26 | 2024-11-06 | 73 | 53 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-06 | 2025-06-25 | 232 | 166 | Unknown | 2025-06-17 | Unknown | Unknown | 2025-07-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-18 | 2024-09-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3430 | 3996.98 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-18 | 2024-09-25 | 8 | 6 | 2024-09-25 | 2024-11-27 | 64 | 46 | Unknown | Unknown | Unknown | Unknown | 2024-09-25 | 2024-10-24 | 30 | 22 | 2024-11-27 | 2025-03-07 | 101 | 73 | Unknown | 2025-06-17 | Unknown | Unknown | 2025-07-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 124.05 | 124.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-31 | Unknown | Unknown | No | 2024-02-21 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-21 | 2024-03-04 | Unknown | IOU Designed & Installed | N/A | Yes | 145 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 933.28 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-21 | 2024-05-31 | 101 | 73 | 2024-05-31 | 2024-07-15 | 46 | 32 | 2024-07-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 137.05 | 137.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-20 | 2025-03-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1643.59 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-20 | 2025-03-03 | 12 | 8 | 2025-03-03 | 2025-03-03 | 1 | 1 | 2025-03-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-07 | 2024-12-07 | 2025-03-17 | IOU Designed & Installed | N/A | No | Unknown | 28.34 | 0 | Unknown | Unknown | 4.74 | 23.6 | 0 | 1631.94 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-07 | 2024-12-07 | 1 | 0 | 2024-12-07 | 2024-12-17 | 11 | 7 | 2024-12-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-11 | 2025-03-17 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2025-03-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-06 | 2024-03-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 285110 | 6419.34 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-06 | 2024-03-06 | 1 | 1 | 2024-03-06 | 2024-04-17 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2021-11-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-26 | 2022-10-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 14210 | 536.67 | Unknown | Unknown | Yes | N/A | N/A | 2022-10-26 | 2023-08-09 | 288 | 206 | 2023-08-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | Carlsbad | N/A | 384 | 384 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-27 | 2025-04-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 15924 | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2025-03-27 | 2025-03-06 | Unknown | Unknown | 2025-03-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 29.45 | 29.45 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-06 | 2024-12-20 | 2025-06-17 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1902.57 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-06 | 2024-11-13 | Unknown | Unknown | 2024-11-13 | 2024-12-20 | 38 | 28 | 2024-12-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-20 | 2025-06-17 | 180 | 128 | Unknown | Unknown | Unknown | Unknown | 2025-06-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-12 | 2022-10-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 5082.17 | Unknown | Unknown | Yes | N/A | N/A | 2022-10-12 | 2024-10-24 | 744 | 532 | 2024-10-24 | 2024-11-06 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-20 | 2024-02-20 | 2024-04-22 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 501.14 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-20 | 2023-12-12 | Unknown | Unknown | 2023-12-12 | 2024-02-23 | 74 | 54 | 2024-02-23 | Unknown | Unknown | Unknown | 2024-02-23 | 2024-03-18 | 25 | 17 | 2024-02-23 | 2024-04-22 | 60 | 42 | Unknown | Unknown | Unknown | Unknown | 2024-04-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-08 | 2023-09-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3754 | 1073.35 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-08 | 2023-09-14 | 7 | 5 | 2023-09-14 | 2023-09-14 | 1 | 1 | 2023-09-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-01 | 2024-11-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1429.96 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-01 | 2024-12-06 | 159 | 115 | 2024-12-06 | 2025-01-09 | 35 | 25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SANTEE | SANTEE | 123 | 123 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-02 | 2024-07-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7320 | 2468.32 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-02 | 2024-07-18 | 17 | 13 | 2024-07-18 | 2024-08-07 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | 2024-07-31 | 2024-08-06 | 7 | 5 | 2024-08-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 27.1 | 27.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-27 | 2024-12-27 | 2025-06-20 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2116.61 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-27 | 2024-11-05 | Unknown | Unknown | 2024-11-05 | 2024-12-27 | 53 | 39 | 2024-12-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-27 | 2025-06-20 | 176 | 126 | Unknown | Unknown | Unknown | Unknown | 2025-06-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | CORONADO | N/A | 133 | 133 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-12 | 2024-11-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1176.77 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-12 | 2024-11-12 | 1 | 1 | 2024-11-12 | 2025-01-02 | 52 | 38 | 2025-01-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-21 | 2025-03-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1265.01 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-21 | 2025-03-28 | 128 | 92 | 2025-03-28 | 2025-04-07 | 11 | 7 | 2025-03-31 | 2025-03-31 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2025-04-07 | 2025-07-22 | 107 | 77 | Unknown | 2025-07-03 | Unknown | Unknown | 2025-07-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-25 | 2025-05-07 | 2025-06-16 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1307.77 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-25 | 2025-05-06 | 12 | 8 | 2025-05-06 | 2025-05-07 | 2 | 2 | 2025-05-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-07 | 2025-06-16 | 41 | 29 | Unknown | Unknown | Unknown | Unknown | 2025-06-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 26 | 26 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-06 | 2025-05-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1336.92 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-06 | 2025-06-10 | 36 | 26 | 2025-06-10 | 2025-06-18 | 9 | 7 | 2025-06-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | N/A | 105 | 105 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-10 | 2025-03-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2898.92 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-10 | 2025-03-24 | 15 | 11 | 2025-03-24 | 2025-03-24 | 1 | 1 | 2025-03-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 88.05 | 88.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-20 | 2024-02-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1111.46 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-20 | 2024-03-30 | 40 | 29 | 2024-03-30 | 2024-04-08 | 10 | 6 | 2024-04-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-06 | 2023-12-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2870.19 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-06 | 2023-12-14 | 9 | 7 | 2023-12-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | IOU Design | Commercial | N/A | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-07 | 2024-02-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 19355.68 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-07 | 2024-02-09 | 3 | 3 | 2024-02-09 | Unknown | Unknown | Unknown | 2024-07-29 | Unknown | Unknown | Unknown | 2024-09-13 | 2024-11-01 | 35 | 23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | 144.1 | 144.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-22 | 2024-08-22 | 2024-10-01 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3941 | 1326.91 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-22 | 2024-07-29 | Unknown | Unknown | 2024-07-29 | 2024-09-18 | 52 | 38 | 2024-09-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-18 | 2024-10-01 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | 2024-10-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 9.05 | 9.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-02 | 2025-06-04 | 2025-06-27 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1143.85 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-02 | 2025-05-15 | Unknown | Unknown | 2025-05-15 | 2025-06-04 | 21 | 15 | 2025-06-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-04 | 2025-06-27 | 24 | 18 | Unknown | Unknown | Unknown | Unknown | 2025-06-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 2.7 | 2.7 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-21 | 2025-01-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 907.95 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-21 | 2025-04-07 | 77 | 55 | 2025-04-07 | 2025-04-21 | 15 | 11 | 2025-04-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-13 | 2024-09-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1131.72 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-13 | 2024-08-05 | Unknown | Unknown | 2024-08-05 | 2024-11-04 | 92 | 66 | 2024-11-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | 68 | 68 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-22 | 2024-08-01 | 2024-10-01 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1558.07 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-22 | 2024-08-01 | 11 | 9 | 2024-08-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-08 | 2024-10-01 | 55 | 39 | Unknown | Unknown | Unknown | Unknown | 2024-10-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | NATIONAL CITY | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-14 | 2025-03-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1785.48 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-14 | 2025-04-08 | 26 | 18 | 2025-04-08 | 2025-04-22 | 15 | 11 | 2025-04-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SOUTH LAGUNA | CALTRANS-Orange County, LAGUNA BEACH | 13.5 | 13.5 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-02 | 2025-05-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 569.54 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-02 | 2025-05-06 | 5 | 3 | 2025-05-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-07 | 2025-05-12 | 6 | 4 | 2025-05-13 | 2025-07-02 | 51 | 37 | Unknown | Unknown | Unknown | Unknown | 2025-07-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-18 | Unknown | Unknown | No | 2024-09-10 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-10 | 2024-09-10 | 2025-06-05 | IOU Designed & Installed | N/A | Yes | 198 | 1301.64 | 0 | Unknown | Unknown | 12.07 | 1289.57 | 3981 | 1636.65 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-10 | 2025-04-03 | 206 | 148 | 2025-04-03 | 2024-10-17 | Unknown | Unknown | 2024-10-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-17 | 2025-06-05 | 232 | 166 | Unknown | 2025-06-03 | Unknown | Unknown | 2025-06-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | MISSION VIEJO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-11 | 2023-07-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1982.72 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-11 | 2023-08-04 | 25 | 19 | 2023-08-04 | 2023-08-11 | 8 | 6 | 2023-08-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-11 | Unknown | Unknown | Unknown | Unknown | 2023-09-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-06 | 2024-09-24 | 2025-07-01 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 999.88 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-06 | 2024-08-19 | Unknown | Unknown | 2024-08-19 | 2024-09-24 | 37 | 27 | 2024-09-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-24 | 2025-07-01 | 281 | 201 | Unknown | Unknown | Unknown | Unknown | 2025-07-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | CHULA VISTA | CHULA VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-08 | 2024-04-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 138391.27 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-08 | 2023-12-21 | Unknown | Unknown | 2023-12-21 | 2025-04-03 | 470 | 336 | 2025-01-28 | 2025-06-26 | 78 | 56 | 2024-12-23 | 2025-06-14 | 162 | 113 | 2025-04-03 | 2025-06-16 | 75 | 53 | 2025-04-18 | 2025-06-03 | 47 | 33 | 2025-07-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2025-09-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-02 | 2024-08-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3241 | 494.79 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-02 | 2024-07-01 | Unknown | Unknown | 2024-07-01 | 2024-08-02 | 33 | 25 | 2024-08-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-24 | 2024-04-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1995.89 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-24 | 2024-04-24 | 1 | 1 | 2024-04-24 | 2024-04-24 | 1 | 1 | 2024-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | N/A | 12 | 12 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-13 | 2025-01-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 196.69 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-13 | 2025-02-03 | 22 | 16 | 2025-02-03 | 2025-02-05 | 3 | 3 | 2025-02-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | SAN CLEMENTE | 40 | 40 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-04 | 2025-01-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 870.36 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-04 | 2025-01-14 | 530 | 378 | 2025-01-14 | 2025-01-14 | 1 | 1 | 2025-01-14 | Unknown | Unknown | Unknown | 2025-01-14 | 2025-01-27 | 14 | 10 | 2025-01-14 | 2025-07-31 | 199 | 143 | Unknown | 2025-07-29 | Unknown | Unknown | 2025-07-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | OH | IOU Design | Commercial | Underserved Community | FALLBROOK | COUNTY OF SAN DIEGO-NORTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-15 | 2025-01-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 23365.8 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-15 | 2025-01-15 | 1 | 1 | 2025-01-15 | 2025-06-18 | 155 | 111 | Unknown | Unknown | Unknown | Unknown | 2025-06-19 | 2025-06-23 | 5 | 3 | 2025-06-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 144.05 | 144.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-30 | 2023-05-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1234.13 | Unknown | Unknown | Yes | N/A | N/A | 2023-05-30 | 2023-05-30 | 1 | 1 | 2023-05-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-30 | Unknown | Unknown | Unknown | Unknown | 2023-09-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | OCEANSIDE | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2024-09-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-22 | 2024-10-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3753.77 | 506.74 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-22 | 2025-05-29 | 220 | 158 | 2025-05-29 | 2025-06-16 | 19 | 13 | Unknown | Unknown | Unknown | Unknown | 2025-05-01 | 2025-05-27 | 27 | 19 | 2025-06-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | OH | IOU Design | Residential | Underserved Community | BORREGO SPRINGS | COUNTY OF SAN DIEGO-NORTH of 56 | 117 | 117 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-31 | 2023-11-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 1812 | 19965.54 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-31 | 2023-10-25 | 56 | 40 | 2023-10-25 | 2024-03-08 | 136 | 98 | 2024-02-05 | 2024-03-04 | 29 | 21 | 2024-03-04 | 2025-07-09 | 50 | 36 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-07-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | POWAY | N/A | 46 | 46 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-24 | 2024-10-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1428.33 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-24 | 2024-12-02 | 40 | 28 | 2024-12-02 | 2025-01-23 | 53 | 39 | 2025-01-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | PW 1190-D4 | POWAY | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-26 | 2024-08-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 133394.96 | 37172.38 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-26 | 2024-09-27 | 64 | 46 | 2024-09-27 | 2025-01-06 | 102 | 72 | 2024-08-05 | 2024-08-06 | 2 | 2 | 2025-01-02 | 2025-08-07 | 71 | 51 | 2025-01-06 | Unknown | Unknown | Unknown | 2025-03-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | DANA POINT | DANA POINT | 48 | 48 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-18 | 2024-11-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2445.72 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-18 | 2024-11-06 | Unknown | Unknown | 2024-11-06 | 2024-11-18 | 13 | 9 | 2024-11-18 | Unknown | Unknown | Unknown | 2024-11-26 | 2024-12-16 | 21 | 15 | 2025-02-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 30 | 30 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-04 | 2025-04-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2024-12-04 | 2025-04-22 | 140 | 100 | 2025-04-22 | 2025-04-30 | 9 | 7 | 2025-04-30 | 2025-06-13 | 45 | 33 | Unknown | Unknown | Unknown | Unknown | 2025-06-25 | 2025-07-14 | 20 | 14 | Unknown | Unknown | Unknown | Unknown | 2025-07-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2028-04-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-02 | 2025-05-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1372.46 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-02 | 2025-05-08 | 7 | 5 | 2025-05-08 | 2025-05-08 | 1 | 1 | 2025-05-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-08 | 2025-07-22 | 76 | 54 | Unknown | Unknown | Unknown | Unknown | 2025-07-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-21 | 2023-11-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 153.49 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-21 | 2023-12-19 | 29 | 21 | 2023-12-19 | 2023-12-19 | 1 | 1 | 2023-12-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | IOU Design | Residential | Underserved Community | San Diego | COUNTY OF SAN DIEGO-SOUTH of 56, SAN DIEGO | 17184 | 17184 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-11 | 2024-08-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 226958.84 | 72368.44 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-11 | 2024-07-12 | 184 | 132 | 2024-07-12 | 2025-05-23 | 316 | 226 | 2024-08-14 | 2025-05-20 | 75 | 53 | 2025-05-07 | 2025-06-16 | 26 | 14 | 2025-05-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-13 | Unknown | Unknown | No | 2023-03-01 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-01 | 2023-03-01 | Unknown | IOU Designed & Installed | N/A | Yes | 285 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 720.91 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-01 | 2023-12-11 | 286 | 204 | 2023-12-11 | 2023-12-11 | 1 | 1 | 2023-12-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | POWAY | N/A | 6 | 6 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-29 | 2024-07-29 | 2024-11-07 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1613.4 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-29 | 2024-07-30 | 2 | 2 | 2024-07-30 | 2024-08-09 | 11 | 9 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-04 | 2025-03-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1497.66 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-04 | 2025-02-11 | Unknown | Unknown | 2025-02-11 | 2025-03-14 | 32 | 24 | 2025-03-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | EL CAJON | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-16 | 2024-05-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 562.3 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-16 | 2024-04-30 | Unknown | Unknown | 2024-04-30 | 2024-09-27 | 151 | 109 | Unknown | Unknown | Unknown | Unknown | 2024-08-27 | 2024-09-23 | 28 | 20 | 2024-09-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | 1431.05 | 1431.05 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2027-02-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-24 | 2025-04-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1293.17 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-24 | 2025-04-24 | 1 | 1 | 2025-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | PINE VALLEY | N/A | 36 | 36 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-13 | 2024-02-13 | 2024-06-05 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 646.75 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-13 | 2024-01-25 | Unknown | Unknown | 2024-01-25 | 2024-02-13 | 20 | 14 | 2024-02-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-13 | 2024-06-05 | 114 | 82 | Unknown | Unknown | Unknown | Unknown | 2024-06-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | RAMONA | N/A | 38.05 | 38.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-23 | 2025-04-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 640.13 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-23 | 2025-04-30 | 8 | 6 | 2025-04-30 | 2025-04-30 | 1 | 1 | 2025-04-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2024-05-15 | Unknown | Unknown | No | 2023-09-12 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-15 | 2023-11-15 | Unknown | IOU Designed & Installed | N/A | Yes | 191 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 349420 | 148240.08 | Unknown | Unknown | Yes | N/A | N/A | 2023-05-15 | 2024-01-15 | 246 | 176 | 2024-01-15 | 2023-12-18 | Unknown | Unknown | 2023-08-10 | 2023-08-18 | 9 | 7 | 2023-12-18 | 2025-08-19 | 611 | 437 | 2023-12-18 | 2025-05-07 | 507 | 363 | 2024-04-16 | 2025-08-14 | 486 | 348 | 2025-09-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 6495 | 6495 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-01-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-02 | 2024-01-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 729.03 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-02 | 2023-11-08 | Unknown | Unknown | 2023-11-08 | 2024-01-02 | 56 | 40 | 2024-01-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Commercial | Disadvantaged Community,Underserved Community | El Cajon | EL CAJON | 4 | 4 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-09 | 2023-08-09 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 25577.25 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-09 | 2023-12-21 | 135 | 97 | 2023-12-21 | 2024-06-06 | 169 | 121 | 2024-01-10 | 2024-11-21 | 247 | 177 | 2024-03-11 | 2025-01-27 | 127 | 93 | 2024-06-28 | Unknown | Unknown | Unknown | 2024-06-28 | 2024-11-07 | 133 | 95 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-22 | 2025-05-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1398.33 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-22 | 2025-05-09 | Unknown | Unknown | 2025-05-09 | 2025-05-22 | 14 | 10 | 2025-05-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-22 | 2025-07-01 | 41 | 29 | Unknown | Unknown | Unknown | Unknown | 2025-07-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | CORONADO | CORONADO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-20 | 2024-11-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 870.98 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-20 | 2024-11-21 | 2 | 2 | 2024-11-21 | 2024-12-06 | 16 | 12 | 2024-12-06 | 2025-02-27 | 16 | 6 | 2024-12-06 | 2025-03-05 | 35 | 25 | 2025-02-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | N/A | 146 | 146 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-04 | 2024-10-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3147.84 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-04 | 2024-10-16 | 13 | 9 | 2024-10-16 | 2024-10-18 | 3 | 3 | 2024-10-18 | 2024-10-24 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2024-10-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | RAMONA | N/A | 60.05 | 60.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-22 | 2023-06-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 557.8 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-22 | 2023-06-21 | Unknown | Unknown | 2023-06-21 | 2023-06-28 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-07-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-12 | 2024-06-12 | 2024-06-25 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1546.51 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-12 | 2024-06-12 | 1 | 1 | 2024-06-12 | 2024-06-12 | 1 | 1 | 2024-06-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-12 | 2024-06-25 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | 2024-06-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-01 | 2024-05-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7681 | 584.27 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-01 | 2024-02-21 | Unknown | Unknown | 2024-02-21 | 2024-05-01 | 71 | 51 | 2024-05-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-01 | 2025-08-14 | 471 | 337 | Unknown | Unknown | Unknown | Unknown | 2025-08-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-24 | 2024-09-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 455326 | 22644.87 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-24 | 2024-09-24 | 1 | 1 | 2024-09-24 | 2024-10-03 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-04 | 2023-12-04 | 2023-12-17 | IOU Designed & Installed | N/A | No | Unknown | 1464.52 | 342.38 | Unknown | 327.36 | 154.67 | 640.11 | 3981 | 454.84 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-04 | 2023-12-04 | 1 | 1 | 2023-12-04 | 2023-12-04 | 1 | 1 | 2023-12-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-04 | 2023-12-17 | 14 | 10 | Unknown | 2023-12-07 | Unknown | Unknown | 2023-12-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | COUNTY OF SAN DIEGO-NORTH of 56 | 136.05 | 136.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-30 | 2025-02-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 587.76 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-30 | 2025-02-14 | 16 | 12 | 2025-02-14 | 2025-06-27 | 134 | 96 | Unknown | Unknown | Unknown | Unknown | 2025-04-25 | 2025-08-01 | 9 | 7 | 2025-06-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | CARLSBAD | N/A | 14 | 14 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-27 | 2024-04-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1307.32 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-27 | 2024-04-04 | 9 | 7 | 2024-04-04 | 2024-04-04 | 1 | 1 | 2024-04-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | MISSION VIEJO | N/A | 11.4 | 11.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-05 | 2025-06-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | 2.44 | 0 | Unknown | Unknown | Unknown | 2.44 | 3981 | 78.95 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-05 | 2025-06-19 | 15 | 11 | 2025-06-19 | 2025-06-19 | 1 | 1 | 2025-06-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-19 | 2025-07-08 | 20 | 14 | Unknown | Unknown | Unknown | Unknown | 2025-07-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | N/A | 12 | 12 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-30 | 2025-04-30 | Unknown | IOU Designed & Installed | N/A | No | Unknown | 488.18 | 0 | Unknown | Unknown | 4.57 | 483.61 | 3981 | 803.04 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-30 | 2025-05-22 | 23 | 17 | 2025-05-22 | 2025-05-22 | 1 | 1 | 2025-05-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-22 | 2025-07-07 | 47 | 33 | Unknown | Unknown | Unknown | Unknown | 2025-07-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | JAMUL | N/A | 96.05 | 96.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-07 | 2023-11-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3941 | 1074.59 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-07 | 2023-09-08 | Unknown | Unknown | 2023-09-08 | 2023-11-07 | 61 | 43 | 2023-11-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LEMON GROVE | N/A | 28.05 | 28.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-02 | 2025-06-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 470.36 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-02 | 2025-05-14 | Unknown | Unknown | 2025-05-14 | 2025-06-05 | 23 | 17 | 2025-06-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-05 | 2025-09-05 | 93 | 67 | Unknown | Unknown | Unknown | Unknown | 2025-09-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | OH | IOU Design | Residential | Underserved Community | JULIAN | COUNTY OF SAN DIEGO-NORTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-10 | 2024-07-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 8636.68 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-10 | 2024-07-10 | 1 | 1 | 2024-07-10 | 2025-03-03 | 237 | 169 | 2024-10-17 | 2025-02-28 | 2 | 2 | 2024-10-16 | 2025-06-05 | 38 | 28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | EL CAJON | N/A | 504 | 504 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-21 | 2024-10-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 76896 | 11717.37 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-21 | 2024-11-01 | 134 | 96 | 2024-11-01 | 2025-01-16 | 77 | 55 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | San Marcos | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-13 | 2025-05-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 10352.7 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-13 | 2025-05-13 | 1 | 1 | 2025-05-13 | 2025-06-20 | 39 | 29 | Unknown | Unknown | Unknown | Unknown | 2025-08-29 | 2025-08-29 | 1 | 1 | 2025-06-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-12 | 2025-05-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1387.32 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-12 | 2025-05-12 | 1 | 1 | 2025-05-12 | 2025-05-12 | 1 | 1 | 2025-05-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-12 | 2025-07-10 | 60 | 44 | Unknown | Unknown | Unknown | Unknown | 2025-07-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-20 | 2023-11-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 441.03 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-20 | 2023-11-10 | Unknown | Unknown | 2023-11-10 | 2024-02-09 | 92 | 66 | 2024-02-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2026-03-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-06 | 2024-03-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 54899 | 81.53 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-06 | 2024-08-08 | 156 | 112 | 2024-08-08 | 2024-08-20 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2024-03-20 | 2024-07-16 | 53 | 39 | 2024-08-20 | Unknown | Unknown | Unknown | Unknown | 2025-07-07 | Unknown | Unknown | 2025-07-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | COUNTY OF SAN DIEGO-NORTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2020-08-14 | 2020-10-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2875 | 1363.78 | Unknown | Unknown | Yes | N/A | N/A | 2020-08-14 | 2024-02-02 | 1268 | 906 | 2024-02-02 | 2024-02-06 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 21750 | 21750 | Not Available | >2MW | No | N/A | N/A | N/A | 2022-06-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-12 | 2023-07-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 131282 | 7784.2 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-12 | 2023-01-31 | Unknown | Unknown | 2023-01-31 | 2023-12-13 | 317 | 227 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 697 | 697 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-24 | 2025-04-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2211.08 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-24 | 2025-04-01 | 9 | 7 | 2025-04-01 | 2025-04-18 | 18 | 14 | 2025-04-18 | 2025-05-21 | 34 | 24 | Unknown | Unknown | Unknown | Unknown | 2025-05-20 | 2025-07-02 | 44 | 32 | Unknown | 2025-05-30 | Unknown | Unknown | 2025-07-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | POWAY | N/A | 33.05 | 33.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-08 | 2025-05-16 | 2025-06-06 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 996.15 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-08 | 2025-04-22 | Unknown | Unknown | 2025-04-22 | 2025-05-20 | 29 | 21 | 2025-05-20 | 2025-06-06 | 18 | 14 | Unknown | Unknown | Unknown | Unknown | 2025-06-06 | 2025-06-06 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2025-06-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | OCEANSIDE | 16 | 16 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-04 | 2024-04-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 5841 | 3061.19 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-04 | 2024-04-04 | 1 | 1 | 2024-04-04 | 2024-04-24 | 21 | 15 | 2025-05-07 | 2025-06-06 | 31 | 23 | 2024-04-04 | 2025-06-24 | 56 | 40 | 2024-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-19 | 2024-08-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 8520 | 942.03 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-19 | 2024-10-24 | 67 | 49 | 2024-10-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-27 | 2024-08-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2866.54 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-27 | 2024-08-01 | 310 | 222 | 2024-08-01 | 2024-10-14 | 75 | 53 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | NATIONAL CITY | N/A | 4 | 4 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-11 | 2025-04-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1809.53 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-11 | 2025-02-11 | 1 | 1 | 2025-02-11 | 2025-04-03 | 52 | 38 | 2025-04-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-03 | 2025-04-22 | 2025-06-30 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1896.45 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-03 | 2025-02-24 | 53 | 37 | 2025-02-24 | 2025-04-22 | 58 | 42 | 2025-04-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-22 | 2025-06-30 | 70 | 50 | Unknown | Unknown | Unknown | Unknown | 2025-06-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-22 | Unknown | Unknown | No | 2023-11-14 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-14 | 2023-12-29 | 2025-06-11 | IOU Designed & Installed | N/A | Yes | 540 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1286.43 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-14 | 2025-05-01 | 535 | 383 | 2025-05-01 | 2025-05-07 | 7 | 5 | 2025-05-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-29 | 2025-06-11 | 531 | 379 | Unknown | Unknown | Unknown | Unknown | 2025-06-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 74 | 74 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-27 | 2024-09-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1246.62 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-27 | 2024-09-09 | Unknown | Unknown | 2024-09-09 | 2024-10-12 | 34 | 25 | 2024-10-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | IMPERIAL BEACH | IMPERIAL BEACH | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-08 | 2024-03-11 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1678.31 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-08 | 2024-03-08 | 30 | 22 | 2024-03-08 | 2024-07-09 | 124 | 88 | Unknown | Unknown | Unknown | Unknown | 2024-04-02 | 2024-05-06 | 35 | 25 | 2024-07-09 | 2025-08-14 | 402 | 288 | Unknown | 2025-08-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-26 | 2023-12-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 839.18 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-26 | 2023-11-08 | Unknown | Unknown | 2023-11-08 | 2023-12-26 | 49 | 35 | 2023-12-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Commercial | Underserved Community | Oceanside | OCEANSIDE | 120 | 120 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-23 | 2025-06-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 35231.25 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-23 | 2025-06-23 | 1 | 1 | 2025-06-23 | 2025-06-27 | 5 | 5 | Unknown | Unknown | Unknown | Unknown | 2025-06-23 | 2025-07-10 | 18 | 14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-07-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 54.05 | 54.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-04 | 2024-12-13 | 2025-01-07 | IOU Designed & Installed | N/A | No | Unknown | 1280.93 | -23.61 | Unknown | Unknown | 44.25 | 1260.29 | 0 | 2208.38 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-04 | 2024-12-02 | Unknown | Unknown | 2024-12-02 | 2024-12-13 | 12 | 10 | 2024-12-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-13 | 2025-01-07 | 26 | 18 | Unknown | Unknown | Unknown | Unknown | 2025-01-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 10.05 | 10.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-14 | 2025-05-15 | 2025-06-19 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1171.4 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-14 | 2025-05-14 | 1 | 1 | 2025-05-14 | 2025-05-15 | 2 | 2 | 2025-05-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-15 | 2025-06-19 | 36 | 26 | Unknown | Unknown | Unknown | Unknown | 2025-06-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | Both | IOU Design | Residential | Underserved Community | SAN MARCOS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-20 | 2025-03-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2910.96 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-20 | 2025-03-03 | Unknown | Unknown | 2025-03-03 | 2025-03-20 | 18 | 14 | 2025-03-20 | 2025-05-02 | 44 | 32 | Unknown | Unknown | Unknown | Unknown | 2025-05-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 134.05 | 134.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-11 | Unknown | Unknown | No | 2024-07-29 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-29 | 2024-08-07 | Unknown | IOU Designed & Installed | N/A | Yes | 346 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 877.37 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-29 | 2025-07-10 | 347 | 249 | 2025-07-10 | 2024-09-06 | Unknown | Unknown | 2024-09-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-06 | 2025-08-19 | 348 | 248 | Unknown | 2025-08-18 | Unknown | Unknown | 2025-08-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-10 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-29 | 2025-05-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 983.43 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-29 | 2025-05-29 | 1 | 1 | 2025-05-29 | 2025-05-29 | 1 | 1 | 2025-05-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-29 | 2025-07-23 | 56 | 40 | Unknown | Unknown | Unknown | Unknown | 2025-07-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-28 | 2025-01-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 12129 | 686.26 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-28 | 2025-01-31 | 4 | 4 | 2025-01-31 | 2025-04-02 | 62 | 44 | 2025-04-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 39.05 | 39.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-09 | Unknown | Unknown | No | 2024-06-30 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-30 | 2024-07-19 | Unknown | IOU Designed & Installed | N/A | Yes | 37 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1049.43 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-30 | 2024-08-06 | 38 | 27 | 2024-08-06 | 2024-07-19 | Unknown | Unknown | 2024-07-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-14 | 2023-08-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 277081 | 30341.21 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-14 | 2023-07-17 | 4 | 2 | 2023-07-17 | 2024-04-17 | 276 | 198 | Unknown | Unknown | Unknown | Unknown | 2023-12-05 | 2024-04-24 | 25 | 19 | 2024-04-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-03-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-10 | 2022-05-31 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 3436.31 | Unknown | Unknown | Yes | N/A | N/A | 2022-05-10 | 2023-05-18 | 374 | 268 | 2023-05-18 | 2023-06-15 | 29 | 21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | POWAY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-19 | 2024-08-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1516.68 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-19 | 2024-08-16 | Unknown | Unknown | 2024-08-16 | 2024-08-27 | 12 | 8 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | CORONADO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-10 | 2025-01-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1180.79 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-10 | 2025-01-10 | 1 | 1 | 2025-01-10 | 2025-01-15 | 6 | 4 | 2025-01-15 | 2025-03-13 | 58 | 42 | Unknown | Unknown | Unknown | Unknown | 2025-01-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-26 | 2024-07-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1536.86 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-26 | 2024-07-26 | 1 | 1 | 2024-07-26 | 2024-07-26 | 1 | 1 | 2024-07-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-26 | 2025-08-20 | 391 | 279 | Unknown | Unknown | Unknown | Unknown | 2025-08-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | 20 | 20 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-11-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-16 | 2024-02-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 36350 | 1431.7 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-16 | 2024-09-25 | 223 | 159 | 2024-09-25 | 2024-10-17 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | 2024-12-09 | 2024-12-09 | 1 | 1 | 2024-10-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | ESCONDIDO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2024-09-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-06 | 2025-02-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3753.77 | 1336.91 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-06 | 2025-05-27 | 111 | 79 | 2025-05-27 | 2025-06-13 | 18 | 14 | Unknown | Unknown | Unknown | Unknown | 2025-05-01 | 2025-05-27 | 27 | 19 | 2025-06-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-05 | 2024-03-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2797.47 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-05 | 2024-06-18 | 106 | 76 | 2024-06-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | 53 | 53 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-26 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-17 | 2025-03-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 36442 | 2179.26 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-17 | 2025-05-22 | 67 | 49 | 2025-05-22 | 2025-06-11 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-10-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-06 | 2025-02-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 421.66 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-06 | 2025-01-09 | 4 | 4 | 2025-01-09 | 2025-03-05 | 56 | 40 | 2025-01-23 | 2025-01-24 | 2 | 2 | 2025-01-06 | 2025-02-07 | 33 | 25 | 2025-03-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-11-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-08 | 2024-07-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 4895.4 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-08 | 2024-07-08 | 1 | 1 | 2024-07-08 | 2024-08-07 | 31 | 23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-07 | 2024-08-19 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 44.1 | 44.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-07 | 2024-05-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 3131.98 | Unknown | Unknown | Yes | N/A | N/A | 2023-04-07 | 2024-04-26 | 386 | 276 | 2024-04-26 | 2024-06-05 | 41 | 29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-03-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-30 | 2022-06-30 | 2024-10-28 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 153.22 | Unknown | Unknown | Yes | N/A | N/A | 2022-06-30 | 2023-10-19 | 477 | 341 | 2023-10-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-19 | 2024-10-28 | 376 | 268 | Unknown | Unknown | Unknown | Unknown | 2024-10-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Residential | Underserved Community | Escondido | N/A | 112 | 112 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-05-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-08 | 2022-12-09 | 2023-03-13 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 52124.22 | Unknown | Unknown | Yes | N/A | N/A | 2022-12-08 | 2023-01-31 | 55 | 39 | 2023-01-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | CARDIFF | CARDIFF | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-17 | 2024-02-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1839.62 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-17 | 2024-01-16 | Unknown | Unknown | 2024-01-16 | 2024-02-01 | 17 | 13 | 2024-02-01 | Unknown | Unknown | Unknown | 2024-02-02 | 2024-03-04 | 32 | 22 | 2024-02-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-13 | 2025-05-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 829.57 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-13 | 2025-05-16 | 4 | 4 | 2025-05-16 | 2025-05-16 | 1 | 1 | 2025-05-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | N/A | Rancho Mission Viejo | Rancho Mission Viejo | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-09 | 2024-05-09 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 91342.86 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-09 | 2024-12-31 | 237 | 169 | 2024-12-31 | Unknown | Unknown | Unknown | 2025-01-17 | 2025-02-04 | 19 | 13 | 2025-03-21 | 2025-04-02 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 244 | 244 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-19 | 2023-10-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 408.69 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-19 | 2023-03-16 | Unknown | Unknown | 2023-03-16 | 2024-05-23 | 435 | 311 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-14 | 2024-05-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 200885.63 | 18603.95 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-14 | 2024-05-15 | 2 | 2 | 2024-05-15 | 2024-07-11 | 58 | 42 | Unknown | Unknown | Unknown | Unknown | 2024-07-11 | 2024-08-14 | 35 | 25 | 2024-07-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-25 | 2023-04-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3885 | 1074.15 | Unknown | Unknown | Yes | N/A | N/A | 2023-04-25 | 2023-04-27 | 3 | 3 | 2023-04-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-02 | 2024-07-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1472.92 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-02 | 2024-05-21 | Unknown | Unknown | 2024-05-21 | 2024-07-29 | 70 | 50 | 2024-07-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-04-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-18 | 2024-07-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2232.59 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-18 | 2024-07-18 | 1 | 1 | 2024-07-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-07 | 2023-02-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 311.78 | Unknown | Unknown | Yes | N/A | N/A | 2023-02-07 | 2023-02-07 | 1 | 1 | 2023-02-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 1338.05 | 1338.05 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2027-02-12 | Unknown | Unknown | No | 2025-03-26 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-26 | 2025-03-26 | Unknown | IOU Designed & Installed | N/A | Yes | 8 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2247.99 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-26 | 2025-04-03 | 9 | 7 | 2025-04-03 | 2025-03-26 | Unknown | Unknown | 2025-03-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-26 | 2025-09-09 | 168 | 120 | Unknown | Unknown | Unknown | Unknown | 2025-09-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | OH | IOU Design | Commercial | N/A | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2019-11-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-03 | 2022-08-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 38507.52 | Unknown | Unknown | Yes | N/A | N/A | 2022-08-03 | 2023-07-13 | 345 | 247 | 2023-07-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-10 | 2023-02-24 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-05 | 2024-08-05 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 679.15 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-05 | 2024-08-02 | Unknown | Unknown | 2024-08-02 | 2024-08-14 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2024-08-08 | Unknown | Unknown | Unknown | 2024-08-14 | 2025-07-16 | 337 | 241 | Unknown | 2025-06-20 | Unknown | Unknown | 2025-08-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SOLANA BEACH | SOLANA BEACH | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-19 | 2024-04-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 139243.63 | 7766.04 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-19 | 2024-04-11 | Unknown | Unknown | 2024-04-11 | 2024-06-10 | 61 | 43 | Unknown | Unknown | Unknown | Unknown | 2024-04-23 | 2024-05-08 | 16 | 12 | 2024-06-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-27 | 2024-08-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1455.34 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-27 | 2024-08-26 | Unknown | Unknown | 2024-08-26 | 2024-08-27 | 2 | 2 | 2024-08-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | RANCHO SANTA FE | N/A | 114 | 114 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-02-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-03 | 2023-10-03 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 24295 | 1710.27 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-03 | 2023-10-03 | 1 | 1 | 2023-10-03 | 2024-09-20 | 354 | 254 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | 3500 | 3500 | Not Available | >2MW | No | N/A | N/A | N/A | 2027-03-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-31 | 2025-04-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1649.85 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-31 | 2025-04-18 | 19 | 15 | 2025-04-18 | 2025-04-18 | 1 | 1 | 2025-04-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | FALLBROOK | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-01 | 2025-04-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2200.93 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-01 | 2025-04-01 | 1 | 1 | 2025-04-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | OH | Applicant Design | Residential | N/A | Encinitas | ENCINITAS | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-01-17 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-20 | 2022-05-20 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 75818.7 | Unknown | Unknown | Yes | N/A | N/A | 2022-05-20 | 2023-02-24 | 281 | 201 | 2023-02-24 | 2025-02-14 | 722 | 516 | 2023-04-18 | 2025-02-04 | 182 | 130 | 2023-06-27 | 2025-02-13 | 12 | 10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | LAKESIDE | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-09 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-04 | 2025-02-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 607.62 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-04 | 2025-06-09 | 126 | 90 | 2025-06-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-09 | 2025-06-17 | 9 | 7 | 2025-06-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LEMON GROVE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-24 | Unknown | Unknown | No | 2024-07-24 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-24 | 2024-07-24 | 2024-10-09 | IOU Designed & Installed | N/A | Yes | 92 | 576.25 | -10.2 | Unknown | Unknown | 41 | 545.45 | 3241 | 1543.69 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-24 | 2024-10-24 | 93 | 67 | 2024-10-24 | 2024-07-24 | Unknown | Unknown | 2024-07-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-24 | 2024-10-09 | 78 | 56 | Unknown | Unknown | Unknown | Unknown | 2024-10-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SOUTH LAGUNA | N/A | 43.05 | 43.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-06 | 2025-06-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 863.94 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-06 | 2025-06-06 | 1 | 1 | 2025-06-06 | 2025-06-06 | 1 | 1 | 2025-06-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | ENCINITAS | ENCINITAS | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-23 | 2022-06-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 666.47 | Unknown | Unknown | Yes | N/A | N/A | 2022-06-23 | 2023-04-18 | 300 | 214 | 2023-04-18 | 2023-05-03 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | 2023-03-08 | 2023-03-09 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SANTEE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-14 | 2023-03-20 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 95.37 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-14 | 2023-03-27 | 14 | 10 | 2023-03-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-19 | 2025-06-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1062.2 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-19 | 2025-06-18 | Unknown | Unknown | 2025-06-18 | 2025-06-19 | 2 | 2 | 2025-06-19 | Unknown | Unknown | Unknown | 2025-06-20 | 2025-06-26 | 7 | 5 | 2025-06-19 | 2025-08-22 | 65 | 47 | Unknown | Unknown | Unknown | Unknown | 2025-08-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 32 | 32 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-16 | 2024-03-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 69738 | 4196.59 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-16 | 2024-03-01 | 138 | 100 | 2024-03-01 | 2024-10-03 | 217 | 155 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-07 | 2023-03-07 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 4791.1 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-07 | 2024-12-02 | 637 | 455 | 2024-12-02 | 2025-04-14 | 134 | 96 | Unknown | Unknown | Unknown | Unknown | 2025-01-07 | 2025-01-24 | 18 | 14 | 2025-04-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-16 | 2024-07-16 | 2024-10-23 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 4511.8 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-16 | 2024-07-19 | 4 | 4 | 2024-07-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | N/A | San Diego | San Diego | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-14 | 2022-12-14 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 214815.37 | 27637.68 | Unknown | Unknown | Yes | N/A | N/A | 2022-12-14 | 2023-04-12 | 120 | 86 | 2023-04-12 | Unknown | Unknown | Unknown | 2023-04-13 | 2024-07-01 | 389 | 277 | 2023-09-16 | 2024-08-20 | 25 | 17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | Both | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | 14.15 | 14.15 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-02 | 2023-11-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 5262 | 1912.44 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-02 | 2023-10-12 | Unknown | Unknown | 2023-10-12 | 2023-12-15 | 65 | 47 | Unknown | Unknown | Unknown | Unknown | 2023-11-29 | 2023-12-04 | 6 | 4 | 2023-12-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2026-03-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-21 | 2024-03-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 54899 | 84.08 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-21 | 2024-09-03 | 167 | 119 | 2024-09-03 | 2024-10-03 | 31 | 23 | Unknown | Unknown | Unknown | Unknown | 2024-03-28 | 2024-06-19 | 44 | 32 | 2024-10-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 12.15 | 12.15 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-16 | 2025-05-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7962 | 1254.69 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-16 | 2025-04-08 | Unknown | Unknown | 2025-04-08 | 2025-05-22 | 45 | 33 | 2025-05-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-22 | 2025-08-14 | 85 | 61 | Unknown | Unknown | Unknown | Unknown | 2025-08-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | VISTA | 267.05 | 267.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-20 | 2024-06-04 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7975 | 2778.88 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-20 | 2024-03-04 | 76 | 54 | 2024-03-04 | 2024-08-09 | 159 | 115 | 2024-08-22 | 2024-09-04 | 14 | 10 | 2024-06-07 | 2024-12-31 | 61 | 45 | 2024-08-09 | 2025-09-08 | 396 | 282 | Unknown | 2024-10-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-06 | 2024-06-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 797.35 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-06 | 2025-02-19 | 259 | 185 | 2025-02-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 37.05 | 37.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-25 | 2025-02-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2140.76 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-25 | 2025-01-10 | Unknown | Unknown | 2025-01-10 | 2025-02-27 | 49 | 35 | 2025-02-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | Applicant Design | Residential | Disadvantaged Community,Underserved Community | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-09-30 | Unknown | Unknown | No | 2021-12-02 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2021-12-02 | 2021-12-02 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | Yes | 930 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 138302.09 | 24788.98 | Unknown | Unknown | Yes | N/A | N/A | 2021-12-02 | 2024-05-10 | 891 | 637 | 2024-05-10 | 2022-09-28 | Unknown | Unknown | 2022-04-21 | 2022-09-08 | 141 | 101 | 2022-09-22 | 2022-09-23 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-28 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-02 | 2024-04-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1243.66 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-02 | 2024-01-09 | Unknown | Unknown | 2024-01-09 | 2024-04-19 | 102 | 74 | 2024-04-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-01 | 2024-07-01 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1345.92 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-01 | 2024-11-22 | 145 | 105 | 2024-11-22 | 2025-01-08 | 48 | 34 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-31 | 2024-10-31 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1817.83 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-31 | 2024-12-27 | 58 | 42 | 2024-12-27 | 2024-12-27 | 1 | 1 | 2024-12-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-27 | 2025-08-26 | 243 | 173 | Unknown | Unknown | Unknown | Unknown | 2025-08-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 81.05 | 81.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-17 | 2024-10-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1798.24 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-17 | 2024-10-15 | Unknown | Unknown | 2024-10-15 | 2024-10-18 | 4 | 4 | 2024-10-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | Applicant Design | Commercial | Underserved Community | Dana Point | DANA POINT | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-08-02 | Unknown | Unknown | No | 2024-02-22 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-24 | 2024-05-16 | 2025-06-03 | Customer elected Applicant Design | Step 2 Engineering & Design | Yes | 11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 260151.97 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-24 | 2024-07-02 | 161 | 115 | 2024-07-02 | 2024-11-08 | 130 | 94 | 2024-07-19 | 2025-06-03 | 54 | 38 | 2024-08-27 | 2025-06-05 | 206 | 148 | 2024-11-08 | Unknown | Unknown | Unknown | Unknown | 2025-06-03 | Unknown | Unknown | 2025-06-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | OH | Applicant Design | Commercial | N/A | Encinitas | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-11-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-24 | 2023-02-24 | 2024-08-28 | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 6211.61 | Unknown | Unknown | Yes | N/A | N/A | 2023-02-24 | 2023-03-29 | 34 | 24 | 2023-03-29 | 2024-08-19 | 510 | 364 | 2023-05-15 | 2024-08-13 | 89 | 65 | 2024-07-30 | 2024-08-02 | 4 | 4 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 39 | 39 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-19 | 2025-05-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 809.75 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-19 | 2025-05-27 | 160 | 114 | 2025-05-27 | 2025-06-19 | 24 | 18 | 2025-06-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | Applicant Design | Residential | Underserved Community | Oceanside | Oceanside | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-29 | 2023-06-29 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 558795.42 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-29 | 2024-12-11 | 532 | 380 | 2024-12-11 | 2025-04-09 | 120 | 86 | 2024-04-15 | 2025-04-07 | 294 | 210 | 2024-06-19 | 2025-07-17 | 71 | 51 | 2025-04-09 | Unknown | Unknown | Unknown | 2025-04-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN MARCOS | SAN MARCOS | 131.05 | 131.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-12 | 2023-09-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2489.93 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-12 | 2023-12-19 | 99 | 71 | 2023-12-19 | 2024-01-11 | 24 | 18 | Unknown | Unknown | Unknown | Unknown | 2023-12-20 | 2024-03-18 | 90 | 64 | 2024-01-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | Applicant Design | Commercial | N/A | ALPINE | COUNTY OF SAN DIEGO-NORTH of 56, COUNTY OF SAN DIEGO-SOUTH of 56 | 50 | 50 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-24 | 2024-01-25 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1084.84 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-24 | 2024-01-29 | 6 | 4 | 2024-01-29 | 2024-06-12 | 136 | 98 | Unknown | Unknown | Unknown | Unknown | 2024-01-29 | 2024-02-06 | 9 | 7 | 2024-06-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | 10 | 10 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | 2025-04-07 | 2025-06-27 | IOU Designed & Installed | N/A | No | Unknown | 1476.04 | 0 | Unknown | Unknown | 16.67 | 1459.37 | 0 | 1098.24 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-07 | 2025-04-30 | 24 | 18 | 2025-04-30 | 2025-05-19 | 20 | 14 | 2025-05-19 | 2025-05-29 | 11 | 9 | Unknown | Unknown | Unknown | Unknown | 2025-05-21 | 2025-06-27 | 38 | 28 | Unknown | 2025-06-24 | Unknown | Unknown | 2025-06-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | CARLSBAD | CARLSBAD | 522 | 522 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-28 | 2024-04-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 296222 | 39040.35 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-28 | 2023-11-17 | Unknown | Unknown | 2023-11-17 | 2024-08-21 | 279 | 199 | 2024-04-23 | 2024-04-24 | 2 | 2 | 2024-04-23 | 2025-08-07 | 28 | 18 | 2024-08-21 | Unknown | Unknown | Unknown | 2025-07-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-13 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-19 | 2024-07-19 | 2025-02-03 | IOU Designed & Installed | N/A | No | Unknown | 152.54 | -3 | Unknown | Unknown | 3.48 | 152.06 | 3981 | 1954.53 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-19 | 2024-06-26 | Unknown | Unknown | 2024-06-26 | 2024-07-19 | 24 | 18 | 2024-07-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-19 | 2025-02-03 | 200 | 142 | Unknown | Unknown | Unknown | Unknown | 2025-02-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 10 | 10 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-22 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-13 | 2024-11-25 | 2025-02-28 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1306.38 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-13 | 2024-11-13 | 1 | 1 | 2024-11-13 | 2024-11-25 | 13 | 9 | 2024-11-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-25 | 2025-02-28 | 96 | 70 | Unknown | 2025-02-24 | Unknown | Unknown | 2025-02-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-24 | Unknown | Unknown | No | 2023-08-02 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-02 | 2023-08-10 | Unknown | IOU Designed & Installed | N/A | Yes | 8 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 465.36 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-02 | 2023-08-10 | 9 | 7 | 2023-08-10 | 2023-08-10 | 1 | 1 | 2023-08-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | ESCONDIDO | 194 | 194 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-04 | 2023-12-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 363140 | 8149.9 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-04 | 2023-09-12 | Unknown | Unknown | 2023-09-12 | 2024-01-09 | 120 | 86 | Unknown | Unknown | Unknown | Unknown | 2023-12-15 | 2024-01-03 | 20 | 14 | 2024-01-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-23 | 2024-09-24 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 90845 | 23603.72 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-23 | 2024-09-23 | 1 | 1 | 2024-09-23 | 2024-11-25 | 64 | 46 | Unknown | Unknown | Unknown | Unknown | 2024-10-24 | 2024-12-03 | 41 | 29 | 2024-11-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CAPISTRANO BEACH | DANA POINT | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-26 | 2023-10-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2534.38 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-26 | 2023-10-27 | 2 | 2 | 2023-10-27 | 2023-10-27 | 1 | 1 | 2023-10-27 | Unknown | Unknown | Unknown | 2025-04-16 | 2025-04-30 | 15 | 11 | 2023-10-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2020-09-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-17 | 2024-09-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2024-09-17 | 2024-10-20 | 34 | 24 | 2024-10-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | ESCONDIDO | ESCONDIDO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-16 | 2025-01-21 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 999.91 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-16 | 2025-01-02 | Unknown | Unknown | 2025-01-02 | 2025-04-15 | 104 | 74 | Unknown | Unknown | Unknown | Unknown | 2025-03-25 | 2025-04-08 | 15 | 11 | 2025-04-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | RAMONA | N/A | 62 | 62 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-14 | 2024-09-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1397.41 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-14 | 2024-08-19 | Unknown | Unknown | 2024-08-19 | 2024-09-16 | 29 | 21 | 2024-09-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | N/A | CB 1147-J2 Lacosta twn sq WO2 (E) | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-02-22 | 2022-10-25 | 2025-06-10 | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | 36588.79 | 11760.24 | Unknown | Unknown | 2184.04 | 22644.51 | 0 | 32091.57 | Unknown | Unknown | Yes | N/A | N/A | 2022-02-22 | 2023-03-09 | 381 | 273 | 2023-03-09 | 2023-10-17 | 223 | 159 | 2023-03-20 | 2024-01-22 | 12 | 10 | 2023-10-17 | 2023-12-01 | 46 | 34 | 2024-05-09 | Unknown | Unknown | Unknown | 2024-05-09 | 2025-06-03 | 391 | 279 | 2025-06-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | EL CAJON | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-26 | 2024-03-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3941 | 1210.62 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-26 | 2024-02-07 | Unknown | Unknown | 2024-02-07 | 2024-03-26 | 49 | 35 | 2024-03-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 2 | 2 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-13 | 2025-06-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1196.72 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-13 | 2025-05-27 | Unknown | Unknown | 2025-05-27 | 2025-06-13 | 18 | 14 | 2025-06-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | COUNTY OF SAN DIEGO-NORTH of 56 | 3611 | 3611 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-05-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-20 | 2025-01-14 | 2025-06-30 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 25500.21 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-20 | 2024-11-01 | 166 | 120 | 2024-11-01 | 2025-04-07 | 158 | 112 | 2025-01-03 | 2025-03-20 | 7 | 5 | 2025-02-05 | 2025-06-09 | 40 | 28 | 2025-04-07 | 2025-07-07 | 92 | 66 | 2025-04-18 | 2025-06-25 | 69 | 49 | 2025-06-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 67.05 | 67.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-28 | 2024-03-28 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1021.24 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-28 | 2023-12-19 | Unknown | Unknown | 2023-12-19 | 2024-05-13 | 147 | 105 | 2024-05-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-13 | 2025-07-15 | 429 | 307 | Unknown | Unknown | Unknown | Unknown | 2025-07-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-13 | 2025-04-10 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 10267.48 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-13 | 2025-02-03 | Unknown | Unknown | 2025-02-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-28 | 2025-05-12 | 15 | 11 | 2025-04-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-07 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-26 | 2025-03-26 | 2025-05-16 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1837.3 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-26 | 2025-04-04 | 10 | 8 | 2025-04-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-28 | 2025-05-16 | 19 | 15 | Unknown | Unknown | Unknown | Unknown | 2025-05-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-27 | 2023-03-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 352.77 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-27 | 2023-03-27 | 1 | 1 | 2023-03-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-24 | Unknown | Unknown | No | 2024-10-28 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-28 | 2024-10-28 | 2024-11-12 | IOU Designed & Installed | N/A | Yes | 17 | 488.01 | 0 | Unknown | Unknown | 73.7 | 414.31 | 3981 | 308.65 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-28 | 2024-11-13 | 17 | 13 | 2024-11-13 | 2024-10-31 | Unknown | Unknown | 2024-10-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-31 | 2024-11-12 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2024-11-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2024-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-14 | 2024-05-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 2269.05 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-14 | 2024-07-16 | 64 | 46 | 2024-07-16 | 2024-08-29 | 45 | 33 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-12 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-02 | 2025-06-02 | 2025-06-16 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1122.72 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-02 | 2025-06-02 | 1 | 1 | 2025-06-02 | 2025-06-02 | 1 | 1 | 2025-06-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-02 | 2025-06-16 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2025-06-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | 61 | 61 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-17 | 2025-01-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 11943 | 1591.79 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-17 | 2024-08-01 | Unknown | Unknown | 2024-08-01 | 2025-04-16 | 259 | 185 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | EL CAJON | N/A | 100 | 100 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-21 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-12 | 2024-12-25 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1883.4 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-12 | 2024-12-25 | 14 | 10 | 2024-12-25 | 2024-12-25 | 1 | 1 | 2024-12-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-04 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-04 | 2025-02-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1222.4 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-04 | 2025-02-14 | 11 | 9 | 2025-02-14 | 2025-02-14 | 1 | 1 | 2025-02-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-14 | 2025-07-24 | 161 | 115 | Unknown | Unknown | Unknown | Unknown | 2025-07-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | 147.05 | 147.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-15 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-16 | 2024-11-14 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 805.18 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-16 | 2024-11-12 | 302 | 216 | 2024-11-12 | 2024-11-14 | 3 | 3 | 2024-11-14 | 2025-07-17 | 246 | 176 | Unknown | Unknown | Unknown | Unknown | 2024-11-14 | 2025-07-17 | 246 | 176 | Unknown | 2025-04-09 | Unknown | Unknown | 2025-07-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-13 | Unknown | Unknown | No | 2023-02-22 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-22 | 2023-02-22 | Unknown | IOU Designed & Installed | N/A | Yes | 89 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 7962 | 709.63 | Unknown | Unknown | Yes | N/A | N/A | 2023-02-22 | 2023-05-22 | 90 | 64 | 2023-05-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-17 | 2025-06-17 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1523.2 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-17 | 2025-06-17 | 1 | 1 | 2025-06-17 | 2025-06-17 | 1 | 1 | 2025-06-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 13 | 13 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-25 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-16 | 2025-04-16 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2485.62 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-16 | 2025-05-06 | 21 | 15 | 2025-05-06 | 2025-05-28 | 23 | 17 | 2025-05-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LAGUNA NIGUEL | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-12 | 2025-05-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1092.02 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-12 | 2025-05-14 | 3 | 3 | 2025-05-14 | 2025-05-15 | 2 | 2 | 2025-05-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2025-09-20 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-26 | 2023-10-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 55446.8 | 27350.09 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-26 | 2023-11-08 | 14 | 10 | 2023-11-08 | 2024-04-15 | 160 | 114 | 2023-11-08 | 2023-11-08 | 1 | 1 | 2023-11-09 | 2023-11-17 | 9 | 7 | 2024-04-15 | Unknown | Unknown | Unknown | 2024-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2022-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-10 | 2023-08-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 1938639 | 1705.6 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-10 | 2023-08-31 | 22 | 16 | 2023-08-31 | 2023-09-01 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-01 | 2023-08-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 742 | 742 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-14 | 2025-04-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1111.56 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-14 | 2025-04-24 | 42 | 30 | 2025-04-24 | 2025-06-02 | 40 | 28 | Unknown | Unknown | Unknown | Unknown | 2025-05-12 | 2025-06-04 | 24 | 18 | 2025-06-02 | 2025-07-10 | 39 | 29 | Unknown | Unknown | Unknown | Unknown | 2025-07-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-14 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-15 | 2025-04-15 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 6197.55 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-15 | 2025-04-14 | Unknown | Unknown | 2025-04-14 | 2025-06-02 | 50 | 36 | Unknown | Unknown | Unknown | Unknown | 2025-04-15 | 2025-04-30 | 16 | 12 | 2025-06-02 | Unknown | Unknown | Unknown | Unknown | 2025-07-29 | Unknown | Unknown | 2025-08-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN MARCOS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-28 | 2024-07-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1216.49 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-28 | 2024-07-26 | 29 | 21 | 2024-07-26 | 2024-07-26 | 1 | 1 | 2024-07-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | ENCINITAS | 100.05 | 100.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-27 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-12 | 2025-06-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2130.14 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-12 | 2025-06-12 | 1 | 1 | 2025-06-12 | 2025-06-27 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | 2025-06-19 | 2025-08-07 | 26 | 16 | 2025-06-27 | Unknown | Unknown | Unknown | Unknown | 2025-08-07 | Unknown | Unknown | 2025-08-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-03 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-23 | 2024-07-23 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 444504 | 42428.12 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-23 | 2024-07-23 | 1 | 1 | 2024-07-23 | 2024-08-29 | 38 | 28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | N/A | 180 | 180 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-05 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-09 | 2024-07-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1227.95 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-09 | 2024-07-23 | 15 | 11 | 2024-07-23 | 2024-07-26 | 4 | 4 | 2024-07-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-26 | 2025-07-21 | 361 | 257 | Unknown | 2025-07-09 | Unknown | Unknown | 2025-07-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-08-18 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-13 | 2023-11-13 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1984.8 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-13 | 2023-11-07 | Unknown | Unknown | 2023-11-07 | 2023-11-15 | 9 | 7 | 2023-11-15 | 2025-06-04 | 568 | 406 | Unknown | Unknown | Unknown | Unknown | 2025-06-16 | Unknown | Unknown | Unknown | Unknown | 2025-08-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | 5 | 5 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-16 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-25 | 2025-06-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 760.39 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-25 | 2025-06-06 | Unknown | Unknown | 2025-06-06 | 2025-06-26 | 21 | 15 | 2025-06-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-31 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-06 | 2025-02-06 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 15924 | 1679 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-06 | 2025-01-28 | Unknown | Unknown | 2025-01-28 | 2025-08-11 | 196 | 140 | Unknown | Unknown | Unknown | Unknown | 2025-03-05 | 2025-03-18 | 14 | 10 | 2025-08-11 | 2025-08-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-08-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-12 | 2023-10-12 | 2024-10-15 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 514.57 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-12 | 2023-10-12 | 1 | 1 | 2023-10-12 | 2023-10-12 | 1 | 1 | 2023-10-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-12 | 2024-10-15 | 370 | 264 | Unknown | Unknown | Unknown | Unknown | 2024-10-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | IMPERIAL BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-02 | 2025-04-02 | Unknown | IOU Designed & Installed | N/A | No | Unknown | 10837.92 | 2517.71 | Unknown | Unknown | Unknown | 8320.21 | 0 | 1909.48 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-02 | 2025-04-03 | 2 | 2 | 2025-04-03 | 2025-04-15 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | IMPERIAL BEACH | IMPERIAL BEACH | 76.2 | 76.2 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-06 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-09 | 2024-05-09 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | Unkonwn | Unknown | Unknown | Yes | N/A | N/A | 2024-05-09 | 2024-04-16 | Unknown | Unknown | 2024-04-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-09 | 2024-08-21 | 44 | 32 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | 1.35 | 1.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-23 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-18 | 2025-02-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 489.5 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-18 | 2025-02-10 | Unknown | Unknown | 2025-02-10 | 2025-04-12 | 62 | 45 | 2025-04-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 40.05 | 40.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-29 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-28 | 2024-05-28 | 2024-06-03 | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1304.46 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-28 | 2024-04-18 | Unknown | Unknown | 2024-04-18 | 2024-05-30 | 43 | 31 | 2024-05-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-30 | 2024-06-03 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | 2024-06-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R29/R45) | UG | IOU Design | Commercial | N/A | ENCINITAS | ENCINITAS | 360 | 360 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-02 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-30 | 2024-10-08 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 49546 | 105363.79 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-30 | 2024-11-26 | 89 | 63 | 2024-11-26 | 2025-05-16 | 172 | 124 | 2025-01-29 | 2025-06-23 | 24 | 18 | 2024-10-18 | 2025-06-30 | 43 | 29 | 2025-05-16 | Unknown | Unknown | Unknown | 2025-06-10 | 2025-07-01 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | Underserved Community | Chula Vista | CHULA VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-02-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-01 | 2022-09-01 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 55311.73 | Unknown | Unknown | Yes | N/A | N/A | 2022-09-01 | 2023-06-29 | 302 | 216 | 2023-06-29 | 2023-10-11 | 105 | 75 | 2023-07-26 | 2024-04-08 | 41 | 29 | 2023-08-10 | 2023-11-01 | 30 | 22 | 2023-10-17 | Unknown | Unknown | Unknown | 2023-10-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R29/R45 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-08-01 | Unknown | Unknown | No | 2023-04-21 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2021-12-06 | 2022-02-22 | 2025-03-31 | IOU Designed & Installed | N/A | Yes | 581 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 68158.53 | Unknown | Unknown | Yes | N/A | N/A | 2021-12-06 | 2023-11-01 | 696 | 498 | 2023-11-01 | 2024-11-13 | 379 | 271 | 2022-12-29 | 2024-05-22 | 184 | 132 | 2024-03-12 | 2024-04-30 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | 2025-05-23 | Unknown | Unknown | Unknown | 2025-03-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-26 | 2025-03-26 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 398.49 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-26 | 2025-04-14 | 20 | 14 | 2025-04-14 | 2025-05-15 | 32 | 24 | Unknown | Unknown | Unknown | Unknown | 2025-04-24 | 2025-05-13 | 20 | 14 | 2025-05-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CARDIFF | N/A | 22320.96 | 22320.96 | Not Available | >2MW | No | N/A | N/A | N/A | 2026-07-30 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-10 | 2024-12-12 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1463.47 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-10 | 2025-03-28 | 109 | 79 | 2025-03-28 | 2025-04-03 | 7 | 5 | 2025-04-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 561.1 | 561.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-17 | Unknown | Unknown | No | 2024-11-19 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-19 | 2024-11-19 | Unknown | IOU Designed & Installed | N/A | Yes | 198 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1082.64 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-19 | 2025-07-09 | 233 | 167 | 2025-07-09 | 2025-02-21 | Unknown | Unknown | 2025-02-19 | 2025-06-13 | 115 | 83 | Unknown | Unknown | Unknown | Unknown | 2025-02-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | POWAY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-11 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-26 | 2024-08-22 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 67677 | 4227.72 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-26 | 2024-03-29 | Unknown | Unknown | 2024-03-29 | 2025-01-02 | 280 | 200 | Unknown | Unknown | Unknown | Unknown | 2025-06-04 | 2025-06-10 | 7 | 5 | 2025-01-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SOUTH LAGUNA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-19 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-18 | 2025-03-18 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 2156.6 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-18 | 2025-03-18 | 1 | 1 | 2025-03-18 | 2025-03-18 | 1 | 1 | 2025-03-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | RANCHO SANTA FE | COUNTY OF SAN DIEGO-NORTH of 56 | 112 | 112 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-01 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-27 | 2024-02-27 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1155.49 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-27 | 2024-02-19 | Unknown | Unknown | 2024-02-19 | 2024-02-27 | 9 | 7 | 2024-02-27 | Unknown | Unknown | Unknown | 2024-02-27 | 2024-03-01 | 4 | 4 | 2024-02-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ALPINE | N/A | 21.05 | 21.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-31 | Unknown | Unknown | No | 2024-06-11 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-11 | 2024-06-11 | 2025-03-03 | IOU Designed & Installed | N/A | Yes | 241 | 1955 | 0 | Unknown | Unknown | 155.04 | 1799.96 | 3981 | 1278.17 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-11 | 2025-02-07 | 242 | 174 | 2025-02-07 | 2024-10-31 | Unknown | Unknown | 2024-10-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-31 | 2025-03-03 | 124 | 88 | Unknown | 2025-01-23 | Unknown | Unknown | 2025-03-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | 12 | 12 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-24 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-19 | 2025-02-19 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 3981 | 1449.52 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-19 | 2025-03-02 | 12 | 8 | 2025-03-02 | 2025-03-04 | 3 | 2 | 2025-03-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-04 | 2025-07-30 | 149 | 107 | Unknown | 2025-07-10 | Unknown | Unknown | 2025-07-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-08 | Unknown | Unknown | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-29 | 2024-10-29 | Unknown | IOU Designed & Installed | N/A | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 0 | 1534.48 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-29 | 2024-10-16 | Unknown | Unknown | 2024-10-16 | 2024-10-29 | 14 | 10 | 2024-10-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-29 | 2025-08-29 | 305 | 219 | Unknown | Unknown | Unknown | Unknown | 2025-08-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Not Available | Unknown