## O&M Expense SRM
2024 RSAR 2023 GRC CYCLE EXPENSE COMPARISON FOR SAFETY, RELIABILITY AND MAINTENANCE WORK (a)(b) (THOUSANDS OF DOLLARS)
| A | B | C1 | C2 | C3 | C4 | C5 | C6 | C7 | D | E | F | G1 | G2 | G3 | H1 | H2 | H3 | I1 | I2 | J1 | J2 | K | L | M | N1 | N2 | N3 | O1 | O2 | O3 | P1 | P2 | Q1 | Q2 | R | S | T | U1 | U2 | U3 | V | W
Line No | Type (O&M Expense or Capital) | Functional Area | MWC | MWC Name | MAT | MAT Name | RAMP Risk Name | RAMP Mitigation and/or Control Name | 2023 GRC Testimony Reference | RAMP Roll-up (Yes/No) | Program/ Project Life (years) | Program/ Project Year | 2023 Imputed Adopted Costs | 2024 Imputed Adopted Costs | Imputed Costs for 2023 GRC Cycle to date($) (G1+G2) | 2023 Actual Costs | 2024 Actual Costs | Actual Costs for 2023 GRC Cycle to date($) (H1+H2) | Difference for 2024 ($) (H2-G2) | Difference for 2023 GRC Cycle to Date ($) (H3-G3) | Spending Percent Variance for 2024 (%) ((H-G)/G*100) | Spending Percent Variance for 2023 GRC Cycle (%) ((H3-G3)/G3*100) | Spending Variance Explanation Required (Y/N) | Percentage Variance Explanation Required (Y/N) | Unit Type | 2023 Imputed Adopted Units | 2024 Imputed Adopted Units | Imputed Units for 2023 GRC Cycle to Date (N2+N1) | 2023 Actual Units | 2024 Actual Units | Actual Units for 2023 GRC Cycle to Date (O2+O1) | Difference for 2024 (# of Units) (O2-N2) | Difference for 2023 GRC Cycle to Date (# of Units)​ (O3-N3) | Unit Percent Variance for 2024 (%) ((O2-N2)/N2*100) | Unit Percent Variance for 2023 GRC Cycle to Date (%)​ ((O3-N3)/N3) | Unit Variance Explanation Required (Y/N) | 2024 Cost Variance Explanation | 2024 Unit Variance Explanation | Forecast Scope (U, O, or T) | Schedule (U, O, or T) | Budget (U, O, or T) | Status | Completion Status Statement
1 | O&M Expense | Gas Distribution | DD | Provide Field Service | DDA | Field Services: Other | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 3, Ch 8 | No | On-Going | Annual | 0 | 0 | 0 | -25.8246 | 140.1379 | 114.3132 | 140.1379 | 114.3132 | 100% | 100% | N | N | non-unitized: This MAT has no measurable units because it is used for other support costs for field services. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
2 | O&M Expense | Gas Distribution | DD | Provide Field Service | DDD | Pilot Relight | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 3, Ch 8 | No | On-Going | Annual | 12170.1951 | 12585.3507 | 24755.5459 | 11078.2963 | 10643.0721 | 21721.3684 | -1942.2787 | -3034.1775 | -15.43% | -12.26% | N | N | # of Service Tickets | 138946 | 138946 | 277892 | 110292 | 104897 | 215189 | -34049 | -62703 | -24.51% | -22.56% | Y | N/A | Actual units were lower than imputed due to lower customer demand of Pilot Relight calls. | Under | On-Target | On-Target | Proceeding as Planned | Ongoing and will continue in PG&E's 2023 GRC period
3 | O&M Expense | Gas Distribution | DD | Provide Field Service | DDE | Appliance Adjs | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 3, Ch 8 | No | On-Going | Annual | 1153.0407 | 1192.3738 | 2345.4145 | 1557.4131 | 1324.5453 | 2881.9583 | 132.1715 | 536.5438 | 11.08% | 22.88% | N | N | # of Service Tickets | 12142 | 12142 | 24284 | 13949 | 11725 | 25674 | -417 | 1390 | -3.434% | 5.724% | N | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
4 | O&M Expense | Gas Distribution | DD | Provide Field Service | DDF | Gas Fumigation Activity | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 3595.0683 | 3717.705 | 7312.7734 | 2841.5014 | 3128.0413 | 5969.5428 | -589.6637 | -1343.2306 | -15.86% | -18.37% | N | N | # of Service Tickets | 34152 | 34152 | 68304 | 23250 | 25153 | 48403 | -8999 | -19901 | -26.35% | -29.14% | Y | N/A | Actual units were lower than imputed due to lower customer demand of Fumigation Activity calls. | Under | On-Target | On-Target | Proceeding as Planned | Ongoing and will continue in PG&E's 2023 GRC period
5 | O&M Expense | Gas Distribution | DD | Provide Field Service | DDF | Gas Fumigation Activity | Loss of Containment on Gas Customer Connected Equipment | CCEPQ-C015 Gas Fumigation | Ex 3, Ch 8 | No | On-Going | Annual | 3595.0683 | 3717.705 | 7312.7734 | 2840.5014 | 3128.0413 | 5968.5428 | -589.6637 | -1344.2306 | -15.86% | -18.38% | N/A | N/A | N/A | 34152 | 34152 | 68304 | 23250 | 25153 | 48403 | -8999 | -19901 | -26.35% | -29.14% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
6 | O&M Expense | Gas Distribution | DD | Provide Field Service | DDG | Gas Leaks & Emergencies | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 31400.9614 | 32472.1262 | 63873.0876 | 32228.0245 | 30186.1826 | 62414.2071 | -2285.9437 | -1458.8806 | -7.04% | -2.284% | N | N | # of Service Tickets | 160514 | 160514 | 321028 | 120636 | 106801 | 227437 | -53713 | -93591 | -33.46% | -29.15% | Y | N/A | Actual units were lower than imputed due to lower customer demand of Gas Leak & Emergency calls. | Under | On-Target | On-Target | Proceeding as Planned | Ongoing and will continue in PG&E's 2023 GRC period
7 | O&M Expense | Gas Distribution | DD | Provide Field Service | DDG | Gas Leaks & Emergencies | Loss of Containment on Gas Customer Connected Equipment | CCEPQ-C007 Gas Leaks and Emergencies | Ex 3, Ch 8 | No | On-Going | Annual | 31400.9614 | 32472.1262 | 63873.0876 | 32227.0245 | 30186.1826 | 62413.2071 | -2285.9437 | -1459.8806 | -7.04% | -2.286% | N/A | N/A | N/A | 160514 | 160514 | 321028 | 120636 | 106801 | 227437 | -53713 | -93591 | -33.46% | -29.15% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
8 | O&M Expense | Gas Distribution | DD | Provide Field Service | DDK | Gas Start | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 3, Ch 8 | No | On-Going | Annual | 5142.1119 | 5317.5221 | 10459.6339 | 4243.0061 | 3915.5849 | 8158.591 | -1401.9371 | -2301.0429 | -26.36% | -22% | N | N | # of Service Tickets | 45509 | 45509 | 91018 | 32056 | 29221 | 61277 | -16288 | -29741 | -35.79% | -32.68% | Y | N/A | Actual units were lower than imputed due to lower customer demand of Gas Start calls. | Under | On-Target | On-Target | Proceeding as Planned | Ongoing and will continue in PG&E's 2023 GRC period
9 | O&M Expense | Gas Distribution | DD | Provide Field Service | DDL | Gas Stop | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 3, Ch 8 | No | On-Going | Annual | 4594.6895 | 4751.4258 | 9346.1154 | 1525.5136 | 1414.8455 | 2940.3591 | -3336.5803 | -6405.7563 | -70.22% | -68.54% | N | N | # of Service Tickets | 77877 | 77877 | 155754 | 16453 | 17194 | 33647 | -60683 | -122107 | -77.92% | -78.4% | Y | N/A | Actual units were lower than imputed due to lower customer demand of Gas Stop calls. | Under | On-Target | On-Target | Proceeding as Planned | Ongoing and will continue in PG&E's 2023 GRC period
10 | O&M Expense | Gas Distribution | DD | Provide Field Service | DD# | Not assigned | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 3, Ch 8 | No | On-Going | Annual | 0 | 0 | 0 | 0.09522 | 0 | 0.09522 | 0 | 0.09522 | 0% | 0% | N | N | non-unitized: This MAT has no measurable units because it is used for adjustments related to labor and overheads under MWC DD. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A | N/A | N/A | N/A | N/A | N/A
11 | O&M Expense | Gas Distribution | DE | G Dist Leak Survey | DEA | Leak Survey | SRM Total | SRM Total | Ex 3, Ch 10 | No | On-Going | Annual | 10306.7242 | 10467.1392 | 20773.8634 | 15560.1884 | 17899.549 | 33459.7374 | 7432.4098 | 12685.874 | 71.01% | 61.07% | N | Y | Services Surveyed | 455760 | 455760 | 911520 | 1233158 | 1364697 | 2597855 | 908937 | 1686335 | 199.4% | 185% | Y | Actual costs were higher than imputed regulatory values due to a shift from MAT DEF to MAT DEA, leveraging Advanced Mobile Leak Detection (Picarro) cars to reduce emissions in the gas system faster, and drive down risk in the system utilizing the Super Emitter Program. | Actual units were higher than imputed units due to a shift from MAT DEF to MAT DEA, leveraging Advanced Mobile Leak Detection (Picarro) cars to reduce emissions in the gas system faster, and drive down risk in the system utilizing the Super Emitter Program. | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
12 | O&M Expense | Gas Distribution | DE | G Dist Leak Survey | DEA | Leak Survey | Loss of Containment on Gas Customer Connected Equipment | CCEPQ-C004 CCE Leak Management | Ex 3, Ch 10 | No | On-Going | Annual | 10306.7242 | 10467.1392 | 20773.8634 | 15558.1884 | 17899.547 | 33457.7354 | 7432.4078 | 12683.872 | 71.01% | 61.06% | N/A | N/A | N/A | 455760 | 455760 | 911520 | 1233158 | 1364697 | 2597855 | 908937 | 1686335 | 199.4% | 185% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
13 | O&M Expense | Gas Distribution | DE | G Dist Leak Survey | DEA | Leak Survey | Loss of Containment on Gas Distribution Main or Service | LOCDM-C014 Distribution Leak Management | Ex 3, Ch 10 | No | On-Going | Annual | 10306.7242 | 10467.1392 | 20773.8634 | 15559.1884 | 17899.548 | 33458.7364 | 7432.4088 | 12684.873 | 71.01% | 61.06% | N/A | N/A | N/A | 455760 | 455760 | 911520 | 1233158 | 1364697 | 2597855 | 908937 | 1686335 | 199.4% | 185% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
14 | O&M Expense | Gas Distribution | DE | G Dist Leak Survey | DEB | Special Leak Survey | SRM Total | SRM Total | Ex 3, Ch 10 | No | On-Going | Annual | 2810.1416 | 2853.8789 | 5664.0205 | 3438.2013 | 2850.7662 | 6288.9675 | -3.1127 | 624.947 | -0.1091% | 11.03% | N | N | # Customer Calls | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
15 | O&M Expense | Gas Distribution | DE | G Dist Leak Survey | DEB | Special Leak Survey | Loss of Containment on Gas Customer Connected Equipment | CCEPQ-C004 CCE Leak Management | Ex 3, Ch 10 | No | On-Going | Annual | 2810.1416 | 2853.8789 | 5664.0205 | 3436.2013 | 2850.7642 | 6286.9655 | -3.1147 | 622.945 | -0.1091% | 11% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
16 | O&M Expense | Gas Distribution | DE | G Dist Leak Survey | DEB | Special Leak Survey | Loss of Containment on Gas Distribution Main or Service | LOCDM-C014 Distribution Leak Management | Ex 3, Ch 10 | No | On-Going | Annual | 2810.1416 | 2853.8789 | 5664.0205 | 3437.2013 | 2850.7652 | 6287.9665 | -3.1137 | 623.946 | -0.1091% | 11.02% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
17 | O&M Expense | Gas Distribution | DE | G Dist Leak Survey | DEC | Downgrade No Repair | SRM Total | SRM Total | Ex 3, Ch 10 | No | On-Going | Annual | 3522.1487 | 3576.9678 | 7099.1164 | 4341.4318 | 3193.87 | 7535.3018 | -383.0978 | 436.1854 | -10.71% | 6.144% | N | N | Services Surveyed | 8936 | 8936 | 17872 | 2272 | 2703 | 4975 | -6233 | -12897 | -69.75% | -72.16% | Y | N/A | Actual units were lower than imputed units due to grade three leaks that were downgraded from a grade two leak now being charged to the respective repair MAT (FIG, FIP or FIH). | Under | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
18 | O&M Expense | Gas Distribution | DE | G Dist Leak Survey | DEC | Downgrade No Repair | Loss of Containment on Gas Distribution Main or Service | LOCDM-C014 Distribution Leak Management | Ex 3, Ch 10 | No | On-Going | Annual | 3522.1487 | 3576.9678 | 7099.1164 | 4340.4318 | 3193.87 | 7534.3018 | -383.0978 | 435.1854 | -10.71% | 6.13% | N/A | N/A | N/A | 8936 | 8936 | 17872 | 2272 | 2703 | 4975 | -6233 | -12897 | -69.75% | -72.16% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
19 | O&M Expense | Gas Distribution | DE | G Dist Leak Survey | DED | Rechecks | SRM Total | SRM Total | Ex 3, Ch 10 | No | On-Going | Annual | 2561.9606 | 2601.8352 | 5163.7958 | 863.4317 | 675.5844 | 1539.0162 | -1926.2508 | -3624.7797 | -74.03% | -70.2% | N | N | # of Rechecks Performed | 43484 | 43484 | 86968 | 22431 | 20175 | 42606 | -23309 | -44362 | -53.6% | -51.01% | Y | N/A | Actual units were lower than imputed units due: 1) leak find rates have decreased since the years 2020-2023 due to more frequent leak surveys; 2) the program was targeting leak repairs prior to the leak's first required recheck date, regardless of the compliance due date; and 3) Grade three leaks were added to the schedule for repair versus prior years where these leaks were not on a repair cycle. | Under | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
20 | O&M Expense | Gas Distribution | DE | G Dist Leak Survey | DED | Rechecks | Loss of Containment on Gas Distribution Main or Service | LOCDM-C014 Distribution Leak Management | Ex 3, Ch 10 | No | On-Going | Annual | 2561.9606 | 2601.8352 | 5163.7958 | 862.4317 | 675.5834 | 1538.0152 | -1926.2518 | -3625.7807 | -74.03% | -70.22% | N/A | N/A | N/A | 43484 | 43484 | 86968 | 22431 | 20175 | 42606 | -23309 | -44362 | -53.6% | -51.01% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
21 | O&M Expense | Gas Distribution | DE | G Dist Leak Survey | DEE | Customer Calls | SRM Total | SRM Total | Ex 3, Ch 10 | No | On-Going | Annual | 789.096 | 801.3776 | 1590.4735 | 2 | 0 | 2 | -801.3776 | -1588.4735 | -100% | -99.87% | N | N | Services Surveyed | 3693 | 3693 | 7386 | 0 | N/A | N/A | N/A | N/A | -100% | N/A | Y | N/A | Actual units were lower than imputed due to MAT no longer used, imputed will show up but no actuals | Under | Under | On-Target | Cancelled | MAT DEE no longer used, imputed will show up but no actuals
22 | O&M Expense | Gas Distribution | DE | G Dist Leak Survey | DEE | Customer Calls | Loss of Containment on Gas Customer Connected Equipment | CCEPQ-C004 CCE Leak Management | Ex 3, Ch 10 | No | On-Going | Annual | 789.096 | 801.3776 | 1590.4735 | 0 | 0 | 0 | -801.3776 | -1590.4735 | -100% | -100% | N/A | N/A | N/A | 3693 | 3693 | 7386 | 0 | N/A | N/A | N/A | N/A | -100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
23 | O&M Expense | Gas Distribution | DE | G Dist Leak Survey | DEE | Customer Calls | Loss of Containment on Gas Distribution Main or Service | LOCDM-C014 Distribution Leak Management | Ex 3, Ch 10 | No | On-Going | Annual | 789.096 | 801.3776 | 1590.4735 | 1 | 0 | 1 | -801.3776 | -1589.4735 | -100% | -99.94% | N/A | N/A | N/A | 3693 | 3693 | 7386 | 0 | N/A | N/A | N/A | N/A | -100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
24 | O&M Expense | Gas Distribution | DE | G Dist Leak Survey | DEF | Advanced Mobile Technology | SRM Total | SRM Total | Ex 3, Ch 10 | No | On-Going | Annual | 12396.0127 | 12588.9456 | 24984.9582 | 2787.5462 | -0.59873 | 2786.9475 | -12589.5443 | -22198.0107 | -100% | -88.85% | Y | Y | Services Surveyed | 905956 | 905956 | 1811912 | 244897 | 0 | 244897 | -905956 | -1567015 | -100% | -86.48% | Y | Actual costs were lower than imputed regulatory values due to a shift from MAT DEF to MAT DEA, leveraging Advanced Mobile Leak Detection (Picarro) cars to reduce emissions in the gas system faster, and drive down risk in the system utilizing the Super Emitter Program. | Actual units were lower than imputed units due to a shift from MAT DEF to MAT DEA, leveraging Advanced Mobile Leak Detection (Picarro) cars to reduce emissions in the gas system faster, and drive down risk in the system utilizing the Super Emitter Program. | Under | Under | Under | Rescheduled | This program will not meet the imputed units as all DEF units have now been optimized to DEA units.
25 | O&M Expense | Gas Distribution | DE | G Dist Leak Survey | DEF | Advanced MobileTechnology | Loss of Containment on Gas Customer Connected Equipment | CCEPQ-C004 CCE Leak Management | Ex 3, Ch 10 | No | On-Going | Annual | 12396.0127 | 12588.9456 | 24984.9582 | 2785.5462 | -0.60073 | 2784.9455 | -12589.5463 | -22200.0127 | -100% | -88.85% | N/A | N/A | N/A | 905956 | 905956 | 1811912 | 244897 | 0 | 244897 | -905956 | -1567015 | -100% | -86.48% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
26 | O&M Expense | Gas Distribution | DE | G Dist Leak Survey | DEF | Advanced MobileTechnology | Loss of Containment on Gas Distribution Main or Service | LOCDM-C014 Distribution Leak Management | Ex 3, Ch 10 | No | On-Going | Annual | 12396.0127 | 12588.9456 | 24984.9582 | 2786.5462 | -0.59973 | 2785.9465 | -12589.5453 | -22199.0117 | -100% | -88.85% | N/A | N/A | N/A | 905956 | 905956 | 1811912 | 244897 | 0 | 244897 | -905956 | -1567015 | -100% | -86.48% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
27 | O&M Expense | Gas Distribution | DE | G Dist Leak Survey | DEH | GD Capacity Uprates | SRM Total | SRM Total | Ex 3, Ch 11 | No | On-Going | Annual | 2434.7536 | 2474.5924 | 4909.346 | 1963.5864 | 1144.8425 | 3108.4289 | -1329.7499 | -1800.9171 | -53.74% | -36.68% | N | N | non-unitized: This program has no measurable units because it includes various activities to support pressure changes (e.g. engineering activities, repairs as needed, temporary piping needed) which cannot be measured in a meaningful way using a single unit of measure. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
28 | O&M Expense | Gas Distribution | DE | G Dist Leak Survey | DEH | GD Capacity Uprates | Insufficient Capacity to Meet Customer Demand | CPCTY-M007 Distribution Uprates and Downrates | Ex 3, Ch 11 | No | On-Going | Annual | 2434.7536 | 2474.5924 | 4909.346 | 1962.5864 | 1144.8415 | 3107.4279 | -1329.7509 | -1801.9181 | -53.74% | -36.7% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
29 | O&M Expense | Gas Distribution | DE | G Dist Leak Survey | DE# | Not assigned | SRM Total | SRM Total | Ex 3, Ch 10 | No | On-Going | Annual | 3036.9453 | 3084.2127 | 6121.158 | 1179.4048 | 1102 | 2281.4048 | -1982.2127 | -3839.7532 | -64.27% | -62.73% | N | N | non-unitized: This MAT has no measurable units because it is used to record other support costs for leak survey. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
30 | O&M Expense | Gas Distribution | DE | G Dist Leak Survey | DE# | Not assigned | Loss of Containment on Gas Customer Connected Equipment | CCEPQ-C004 CCE Leak Management | Ex 3, Ch 10 | No | On-Going | Annual | 3036.9453 | 3084.2127 | 6121.158 | 1179.4048 | 1102 | 2281.4048 | -1982.2127 | -3839.7532 | -64.27% | -62.73% | N | N | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A | N/A | N/A | N/A | N/A | N/A
31 | O&M Expense | Gas Distribution | DE | G Dist Leak Survey | DE# | Not assigned | Loss of Containment on Gas Distribution Main or Service | LOCDM-C014 Distribution Leak Management | Ex 3, Ch 10 | No | On-Going | Annual | 3036.9453 | 3084.2127 | 6121.158 | 1179.4048 | 1102 | 2281.4048 | -1982.2127 | -3839.7532 | -64.27% | -62.73% | N | N | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A | N/A | N/A | N/A | N/A | N/A
32 | O&M Expense | Gas Distribution | DF | G&E T&D Locate and Mark | DFA | Locate and Mark | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 75271.7222 | 77495.6162 | 152767.3383 | 57525.8466 | 59562.5885 | 117088.4351 | -17933.0277 | -35678.9033 | -23.14% | -23.36% | Y | Y | # of Tickets | 863682 | 863682 | 1727364 | 611600 | 600706 | 1212306 | -262976 | -515058 | -30.45% | -29.82% | Y | Actual costs were lower than imputed imputed regulatory values due to the ticket increase from third-party driven work not materializing as expected. | Actual units were lower than imputed units due to the ticket increase from third-party driven work not materializing as expected. | Under | On-Target | Under | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2027 GRC periond. The purpose of this program is to field mark PG&E's underground facilities in response to 811 tickets as required by CA GC 4216.
33 | O&M Expense | Gas Distribution | DF | G&E T&D Locate and Mark | DFA | Locate and Mark | Loss of Containment on Gas Distribution Main or Service | LOCDM-C017 Locate and Mark - Distribution | Ex 3, Ch 8 | No | On-Going | Annual | 75271.7222 | 77495.6162 | 152767.3383 | 57524.8466 | 59562.5875 | 117087.4341 | -17933.0287 | -35679.9043 | -23.14% | -23.36% | N/A | N/A | N/A | 863682 | 863682 | 1727364 | 611600 | 600706 | 1212306 | -262976 | -515058 | -30.45% | -29.82% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
34 | O&M Expense | Gas Distribution | DF | G&E T&D Locate and Mark | DFB | Locate and Mark - Standby | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 447.9214 | 461.1552 | 909.0766 | 289.107 | 353.6488 | 642.7558 | -107.5064 | -266.3208 | -23.31% | -29.3% | N | N | # of times standby is required onsite | 642 | 642 | 1284 | 528 | 311.65 | 839.65 | -330.35 | -444.35 | -51.46% | -34.61% | Y | N/A | Actual units were lower than imputed units due to the ticket increase from third-party driven work not materializing as expected. | Under | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2027 GRC periond. The purpose of this program is to perform watch and protect activies when an excavator is operating in the vacinitiy of an underground critical facility.
35 | O&M Expense | Gas Distribution | DF | G&E T&D Locate and Mark | DFB | Locate and Mark - Standby | Loss of Containment on Gas Distribution Main or Service | LOCDM-C017 Locate and Mark - Distribution | Ex 3, Ch 8 | No | On-Going | Annual | 447.9214 | 461.1552 | 909.0766 | 288.107 | 353.6477 | 641.7548 | -107.5074 | -267.3218 | -23.31% | -29.41% | N/A | N/A | N/A | 642 | 642 | 1284 | 528 | 311.65 | 839.65 | -330.35 | -444.35 | -51.46% | -34.61% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
36 | O&M Expense | Gas Distribution | DF | G&E T&D Locate and Mark | DF# | Not assigned | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 2191.2173 | 2255.9565 | 4447.1737 | 2235.1451 | 2775.6593 | 5010.8044 | 519.7028 | 563.6307 | 23.04% | 12.67% | N | N | non-unitized: This MAT has no measurable units because it is used to record other support costs and fees for locate and mark. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
37 | O&M Expense | Gas Distribution | DF | G&E T&D Locate and Mark | DF# | Not assigned | Loss of Containment on Gas Distribution Main or Service | LOCDM-C017 Locate and Mark - Distribution | Ex 3, Ch 8 | No | On-Going | Annual | 2191.2173 | 2255.9565 | 4447.1737 | 0 | 2775.6593 | 2775.6593 | 519.7028 | -1671.5144 | 23.04% | -37.59% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
38 | O&M Expense | Gas Distribution | DG | G Dist Cathodic Protection | DGA | Cath Protect - Monitoring | SRM Total | SRM Total | Ex 3, Ch 9 | No | On-Going | Annual | 4189.2806 | 4265.5739 | 8454.8545 | 5056.6783 | 5092.9976 | 10149.6759 | 827.4236 | 1694.8213 | 19.4% | 20.05% | N | N | # of monitoring points read (P/S reads) | 79622 | 79622 | 159244 | 97642 | 96906 | 194548 | 17284 | 35304 | 21.71% | 22.17% | Y | N/A | Actual units were higher than imputed units due to because imputed units were based on 2023 planned units that did not factor the increased units for the Electrically connected isolated steel(ECIS) Program that added ECIS monitoring units into SAP. | Over | On-Target | On-Target | Proceeding as Planned | Ongoing and will continue in PG&E's 2023 GRC period
39 | O&M Expense | Gas Distribution | DG | G Dist Cathodic Protection | DGA | Cath Protect - Monitoring | Loss of Containment on Gas Distribution Main or Service | LOCDM-C018 Distribution Corrosion Control Program | Ex 3, Ch 9 | No | On-Going | Annual | 4189.2806 | 4265.5739 | 8454.8545 | 5055.6783 | 5092.9966 | 10148.6749 | 827.4226 | 1693.8203 | 19.4% | 20.03% | N/A | N/A | N/A | 79622 | 79622 | 159244 | 97642 | 96906 | 194548 | 17284 | 35304 | 21.71% | 22.17% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
40 | O&M Expense | Gas Distribution | DG | G Dist Cathodic Protection | DGB | Cath Protect-Troubleshoot | SRM Total | SRM Total | Ex 3, Ch 9 | No | On-Going | Annual | 5017.1741 | 5108.5447 | 10125.7189 | 7484.5753 | 8553.7191 | 16038.2944 | 3445.1744 | 5912.5756 | 67.44% | 58.39% | N | N | # of CPA's troubleshot | 14103 | 14103 | 28206 | 14872 | 16636 | 31508 | 2533 | 3302 | 17.96% | 11.71% | N | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
41 | O&M Expense | Gas Distribution | DG | G Dist Cathodic Protection | DGB | Cath Protect-Troubleshoot | Loss of Containment on Gas Distribution Main or Service | LOCDM-C018 Distribution Corrosion Control Program | Ex 3, Ch 9 | No | On-Going | Annual | 5017.1741 | 5108.5447 | 10125.7189 | 7483.5753 | 8553.7181 | 16037.2934 | 3445.1734 | 5911.5746 | 67.44% | 58.38% | N/A | N/A | N/A | 14103 | 14103 | 28206 | 14872 | 16636 | 31508 | 2533 | 3302 | 17.96% | 11.71% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
42 | O&M Expense | Gas Distribution | DG | G Dist Cathodic Protection | DGC | Cath Protect - Rectifier Maint | SRM Total | SRM Total | Ex 3, Ch 9 | No | On-Going | Annual | 633.2267 | 644.7587 | 1277.9854 | 1360.7235 | 804.4499 | 2165.1735 | 159.6912 | 887.1881 | 24.77% | 69.42% | N | N | # of Rectifiers Maintained | 3942 | 3942 | 7884 | 4060 | 4108 | 8168 | 166 | 284 | 4.211% | 3.602% | N | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
43 | O&M Expense | Gas Distribution | DG | G Dist Cathodic Protection | DGC | Cath Protect - Rectifier Maint | Loss of Containment on Gas Distribution Main or Service | LOCDM-C018 Distribution Corrosion Control Program | Ex 3, Ch 9 | No | On-Going | Annual | 633.2267 | 644.7587 | 1277.9854 | 1359.7235 | 804.4489 | 2164.1725 | 159.6902 | 886.1871 | 24.77% | 69.34% | N/A | N/A | N/A | 3942 | 3942 | 7884 | 4060 | 4108 | 8168 | 166 | 284 | 4.211% | 3.602% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
44 | O&M Expense | Gas Distribution | DG | G Dist Cathodic Protection | DGD | Cath Protect - Resurvey | SRM Total | SRM Total | Ex 3, Ch 9 | No | 9 years | 8 | 3795.7013 | 3864.827 | 7660.5282 | 3570.7036 | 3463.7449 | 7034.4485 | -401.0821 | -626.0797 | -10.38% | -8.173% | N | N | non-unitized: This program has no measurable units because of the mixture of work, however, survey mileage is tracked to indicate overall program progress. Survey findings may lead to additional work in MAT DGB or MAT FII. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
45 | O&M Expense | Gas Distribution | DG | G Dist Cathodic Protection | DGD | Cath Protect - Resurvey | Loss of Containment on Gas Distribution Main or Service | LOCDM-M003 Enhanced CP Survey and Unprotected Main Evaluation | Ex 3, Ch 9 | No | 9 years | 8 | 3795.7013 | 3864.827 | 7660.5282 | 3569.7036 | 3463.7439 | 7033.4475 | -401.0831 | -627.0807 | -10.38% | -8.186% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
46 | O&M Expense | Gas Distribution | DG | G Dist Cathodic Protection | DGE | G:Isolated Steel Svc Evaluatn | SRM Total | SRM Total | Ex 3, Ch 9 | No | 9 years | 8 | 6548.2234 | 6667.4768 | 13215.7002 | 4084.4837 | 2904.5521 | 6989.0358 | -3762.9247 | -6226.6643 | -56.44% | -47.12% | N | N | non-unitized: This program has no measurable units because there are multiple aspects of the work including field survey, SAP record updates, and GIS mapping to complete the survey, however, service risers surveyed are tracked to indicate overall program progress. Survey findings may lead to additional work in MAT DGB or MAT FII. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
47 | O&M Expense | Gas Distribution | DG | G Dist Cathodic Protection | DGE | G:Isolated Steel Svc Evaluatn | Loss of Containment on Gas Distribution Main or Service | LOCDM-C022 Electrically Connected Isolated Steel Services | Ex 3, Ch 9 | No | 9 years | 8 | 6548.2234 | 6667.4768 | 13215.7002 | 4083.4837 | 2904.5511 | 6988.0348 | -3762.9257 | -6227.6653 | -56.44% | -47.12% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
48 | O&M Expense | Gas Distribution | DG | G Dist Cathodic Protection | DGG | Install casing test stations | SRM Total | SRM Total | Ex 3, Ch 9 | No | 8 years | 5 | 3249.6289 | 3308.8097 | 6558.4385 | 2496.5023 | 1068.0399 | 3564.5423 | -2240.7697 | -2993.8963 | -67.72% | -45.65% | N | N | # of Casing Test Stations Installed | 140 | 140 | 280 | 37 | 14 | 51 | -126 | -229 | -90% | -81.79% | Y | N/A | Actual units were lower than imputed units due to: 1) reprioritization in support of higher risk or compliance work; and 2) higher than expected unit costs due to the need for more detailed permit sketches to meet agency requirements, permitting and restoration costs, and increases in contract labor costs. | Under | Under | On-Target | Rescheduled | This program's work is ongoing and will continue in PG&E's 2023 GRC period. This program is to install casing test stations to support electrical isolation testing to meet the requirement of 49 CFR § 192.467 External corrosion control.
49 | O&M Expense | Gas Distribution | DG | G Dist Cathodic Protection | DGG | Install casing test stations | Loss of Containment on Gas Distribution Main or Service | LOCDM-C019 Casings | Ex 3, Ch 9 | No | 8 years | 5 | 3249.6289 | 3308.8097 | 6558.4385 | 2495.5023 | 1068.0389 | 3563.5413 | -2240.7707 | -2994.8973 | -67.72% | -45.66% | N/A | N/A | N/A | 140 | 140 | 280 | 37 | 14 | 51 | -126 | -229 | -90% | -81.79% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
50 | O&M Expense | Gas Distribution | DG | G Dist Cathodic Protection | DGH | Casing mitigate < than 100ft | SRM Total | SRM Total | Ex 3, Ch 9 | No | On-Going | Annual | 4263.4941 | 4341.139 | 8604.6332 | 1911.81 | 703.3024 | 2615.1123 | -3637.8367 | -5989.5209 | -83.8% | -69.61% | N | N | # of Casings Mitigated | 33 | 33 | 66 | 12 | 6 | 18 | -27 | -48 | -81.82% | -72.73% | Y | N/A | Actual units were lower than imputed units due to reprioritization in support of higher risk or compliance work. | Under | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. This program is to mitigate casings less than 40 feet to meet the requirement of 49 CFR § 192.467 External corrosion control.
51 | O&M Expense | Gas Distribution | DG | G Dist Cathodic Protection | DGH | Casing mitigate < than 100ft | Loss of Containment on Gas Distribution Main or Service | LOCDM-C019 Casings | Ex 3, Ch 9 | No | On-Going | Annual | 4263.4941 | 4341.139 | 8604.6332 | 1910.81 | 703.3014 | 2614.1113 | -3637.8377 | -5990.5219 | -83.8% | -69.62% | N/A | N/A | N/A | 33 | 33 | 66 | 12 | 6 | 18 | -27 | -48 | -81.82% | -72.73% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
52 | O&M Expense | Gas Distribution | EX | G Dist Meter Protection | EXB | MPP Protections | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 12709.0353 | 13133.4042 | 25842.4395 | 1006.3817 | 76.9891 | 1083.3708 | -13056.4151 | -24759.0687 | -99.41% | -95.81% | Y | Y | # of Locations | 15429 | 15429 | 30858 | 1255 | 0 | 1255 | -15429 | -29603 | -100% | -95.93% | Y | Actual costs were lower than imputed due to the reclassification of all Meter Protection Post installations from expense (MAT EXB) to capital (MAT 27A). | Actual units were lower than imputed units due to the reclassification of Meter Protection Post installations from Expense to Capital in addition to the delay of units to 2025-2026 | Under | Under | Under | Cancelled | MAT EXB formerly included the installtion of the Meter Protection Post ; however, this type of work is now being capitalized. Therefore, starting in 2024, this type of work is captured under MAT 27A.
53 | O&M Expense | Gas Distribution | EX | G Dist Meter Protection | EXB | MPP Protections | Loss of Containment on Gas Customer Connected Equipment | CCEPQ-C001 Meter Protection | Ex 3, Ch 8 | No | On-Going | Annual | 12709.0353 | 13133.4042 | 25842.4395 | 1005.3817 | 76.9881 | 1082.3698 | -13056.4161 | -24760.0697 | -99.41% | -95.81% | N/A | N/A | N/A | 15429 | 15429 | 30858 | 1255 | 0 | 1255 | -15429 | -29603 | -100% | -95.93% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
54 | O&M Expense | Gas Distribution | FG | G Dist Operate System | FGA | Gas Distribution Control Centr | SRM Total | SRM Total | Ex 3, Ch 11 | No | On-Going | Annual | 8861.5069 | 9125.6869 | 17987.1938 | 4 | 7798.0317 | 7802.0317 | -1327.6552 | -10185.1621 | -14.55% | -56.62% | N | N | non-unitized: This MAT has no measurable units because it is used to record staffing related costs for Gas Distribution Control Center employees. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
55 | O&M Expense | Gas Distribution | FG | G Dist Operate System | FGA | Gas Distribution Control Centr | Loss of Containment on Gas Customer Connected Equipment | CCEPQ-C006 Gas Distribution Control Center Operations | Ex 3, Ch 11 | No | On-Going | Annual | 8861.5069 | 9125.6869 | 17987.1938 | 0 | 7798.0277 | 7798.0277 | -1327.6592 | -10189.1661 | -14.55% | -56.65% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
56 | O&M Expense | Gas Distribution | FG | G Dist Operate System | FGA | Gas Distribution Control Centr | Insufficient Capacity to Meet Customer Demand | CPCTY-C001 Gas Distribution Control Center Operations | Ex 3, Ch 11 | No | On-Going | Annual | 8861.5069 | 9125.6869 | 17987.1938 | 1 | 7798.0287 | 7799.0287 | -1327.6582 | -10188.1651 | -14.55% | -56.64% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
57 | O&M Expense | Gas Distribution | FG | G Dist Operate System | FGA | Gas Distribution Control Centr | Loss of Containment on Gas Distribution Main or Service | LOCDM-C015 Gas Distribution Control Center Operations | Ex 3, Ch 11 | No | On-Going | Annual | 8861.5069 | 9125.6869 | 17987.1938 | 2 | 7798.0297 | 7800.0297 | -1327.6572 | -10187.1641 | -14.55% | -56.64% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
58 | O&M Expense | Gas Distribution | FG | G Dist Operate System | FGA | Gas Distribution Control Centr | Large Overpressure Event Downstream of Gas M&C Facility | LRGOP-C014 Gas Distribution Control Center Operations | Ex 3, Ch 11 | No | On-Going | Annual | 8861.5069 | 9125.6869 | 17987.1938 | 3 | 7798.0307 | 7801.0307 | -1327.6562 | -10186.1631 | -14.55% | -56.63% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
59 | O&M Expense | Gas Distribution | FG | G Dist Operate System | FGB | Op Distr-G Mns/Svcs | SRM Total | SRM Total | Ex 3, Ch 11 | No | On-Going | Annual | 968.0893 | 996.95 | 1965.0393 | 703.1888 | 655.53 | 1358.7188 | -341.42 | -606.3205 | -34.25% | -30.86% | N | N | non-unitized: This program has no measurable units because it encompasses a variety of different O&M activities. A count of the operations completed is captured in SAP. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
60 | O&M Expense | Gas Distribution | FG | G Dist Operate System | FGB | Op Distr-G Mns/Svcs | Loss of Containment on Gas Distribution Main or Service | LOCDM-C015 Gas Distribution Control Center Operations | Ex 3, Ch 11 | No | On-Going | Annual | 968.0893 | 996.95 | 1965.0393 | 702.1888 | 655.53 | 1357.7188 | -341.42 | -607.3205 | -34.25% | -30.91% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
61 | O&M Expense | Gas Distribution | FG | G Dist Operate System | FGC | Op Distr-G Reg Genl | SRM Total | SRM Total | Ex 3, Ch 11 | No | On-Going | Annual | 180.2244 | 185.5973 | 365.8217 | 222.9603 | 134.4546 | 357.4149 | -51.1427 | -8.4068 | -27.56% | -2.298% | N | N | # of valves repaired/replaced | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
62 | O&M Expense | Gas Distribution | FG | G Dist Operate System | FGC | Op Distr-G Reg Genl | Loss of Containment on Gas Distribution Main or Service | LOCDM-C015 Gas Distribution Control Center Operations | Ex 3, Ch 11 | No | On-Going | Annual | 180.2244 | 185.5973 | 365.8217 | 221.9603 | 134.4536 | 356.4139 | -51.1437 | -9.4078 | -27.56% | -2.572% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
63 | O&M Expense | Gas Distribution | FH | G Dist Preventive Maint | FHA | Maint-Prev-G Mains | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 2855.2508 | 2912.0449 | 5767.2957 | 1068.0082 | 1179.6821 | 2247.6903 | -1732.3628 | -3519.6054 | -59.49% | -61.03% | N | N | # Mains Maintained | 605 | 605 | 1210 | 192 | 165 | 357 | -440 | -853 | -72.73% | -70.5% | Y | N/A | Actual units lower than imputed due to unit delay for other higher priority work. Delayed units will be completed in 2025 and 2026. | Under | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to complete corrective maintenance on main distribution pipe lines < 100'.
64 | O&M Expense | Gas Distribution | FH | G Dist Preventive Maint | FHA | Maint-Prev-G Mains | Loss of Containment on Gas Distribution Main or Service | LOCDM-C027 Preventive Maintenance Gas Mains | Ex 3, Ch 8 | No | On-Going | Annual | 2855.2508 | 2912.0449 | 5767.2957 | 1067.0082 | 1179.6811 | 2246.6893 | -1732.3638 | -3520.6064 | -59.49% | -61.04% | N/A | N/A | N/A | 605 | 605 | 1210 | 192 | 165 | 357 | -440 | -853 | -72.73% | -70.5% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
65 | O&M Expense | Gas Distribution | FH | G Dist Preventive Maint | FHB | Maint-Prev-G Reg Sta | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 5161.5429 | 5264.2119 | 10425.7548 | 4396.4122 | 5698.302 | 10094.7142 | 434.0901 | -331.0405 | 8.246% | -3.175% | N | N | # Services Maintained | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
66 | O&M Expense | Gas Distribution | FH | G Dist Preventive Maint | FHB | Maint-Prev-G Reg Sta | Large Overpressure Event Downstream of Gas M&C Facility | LRGOP-C018 Distribution Regulator Maintenance | Ex 3, Ch 8 | No | On-Going | Annual | 5161.5429 | 5264.2119 | 10425.7548 | 4394.4122 | 5698.3 | 10092.7122 | 434.0881 | -333.0425 | 8.246% | -3.194% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
67 | O&M Expense | Gas Distribution | FH | G Dist Preventive Maint | FHB | Maint-Prev-G Reg Sta | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C011 Distribution Regulator Maintenance | Ex 3, Ch 8 | No | On-Going | Annual | 5161.5429 | 5264.2119 | 10425.7548 | 4395.4122 | 5698.301 | 10093.7132 | 434.0891 | -332.0415 | 8.246% | -3.185% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
68 | O&M Expense | Gas Distribution | FH | G Dist Preventive Maint | FHC | Maint-Prev-G Farm Tap | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 422.3104 | 430.7106 | 853.021 | 172.2999 | 349.9913 | 522.2912 | -80.7193 | -330.7298 | -18.74% | -38.77% | N | N | # of inspections completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
69 | O&M Expense | Gas Distribution | FH | G Dist Preventive Maint | FHC | Maint-Prev-G Farm Tap | Large Overpressure Event Downstream of Gas M&C Facility | LRGOP-C019 Farm Tap Maintenance | Ex 3, Ch 8 | No | On-Going | Annual | 422.3104 | 430.7106 | 853.021 | 170.2999 | 349.9893 | 520.2892 | -80.7213 | -332.7318 | -18.74% | -39.01% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
70 | O&M Expense | Gas Distribution | FH | G Dist Preventive Maint | FHC | Maint-Prev-G Farm Tap | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C012 Farm Tap Maintenance | Ex 3, Ch 8 | No | On-Going | Annual | 422.3104 | 430.7106 | 853.021 | 171.2999 | 349.9903 | 521.2902 | -80.7203 | -331.7308 | -18.74% | -38.89% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
71 | O&M Expense | Gas Distribution | FH | G Dist Preventive Maint | FHE | Maint-Prev-G Svcs | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 4808.3129 | 4903.9557 | 9712.2686 | 4348.9547 | 4194.99 | 8543.9447 | -708.9657 | -1168.3239 | -14.46% | -12.03% | N | N | # of Spans Mitigated | 2606 | 2606 | 5212 | 1656 | 1753 | 3409 | -853 | -1803 | -32.73% | -34.59% | Y | N/A | Actual units lower than imputed due to unit delay for other higher priority work. Delayed units will be completed in 2025 and 2026. | Under | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to complete corrective maintenance on services lines that do not include full service replacement.
72 | O&M Expense | Gas Distribution | FH | G Dist Preventive Maint | FHE | Maint-Prev-G Svcs | Loss of Containment on Gas Distribution Main or Service | LOCDM-C023 Preventive Maintenance Gas Services | Ex 3, Ch 8 | No | On-Going | Annual | 4808.3129 | 4903.9557 | 9712.2686 | 4347.9547 | 4194.99 | 8542.9447 | -708.9657 | -1169.3239 | -14.46% | -12.04% | N/A | N/A | N/A | 2606 | 2606 | 5212 | 1656 | 1753 | 3409 | -853 | -1803 | -32.73% | -34.59% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
73 | O&M Expense | Gas Distribution | FH | G Dist Preventive Maint | FHG | Maint-Prev-G Main Vlv | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 2503.6078 | 2553.4074 | 5057.0152 | 1463.3043 | 1487.5099 | 2950.8142 | -1065.8975 | -2106.201 | -41.74% | -41.65% | N | N | non-unitized: This program has no measurable units because it encompasses a variety of different O&M activities. A count of the operations completed is captured in SAP. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
74 | O&M Expense | Gas Distribution | FH | G Dist Preventive Maint | FHG | Maint-Prev-G Main Vlv | Loss of Containment on Gas Distribution Main or Service | LOCDM-C026 Maintenance, Preventative, Gas Valves | Ex 3, Ch 8 | No | On-Going | Annual | 2503.6078 | 2553.4074 | 5057.0152 | 1462.3043 | 1487.5089 | 2949.8132 | -1065.8985 | -2107.202 | -41.74% | -41.67% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
75 | O&M Expense | Gas Distribution | FH | G Dist Preventive Maint | FHI | Maint-Corr G Svc Valves | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 8267.1855 | 8431.6292 | 16698.8146 | 1905.797 | 5389.71 | 7295.507 | -3041.9192 | -9403.3076 | -36.08% | -56.31% | N | N | # of valves repaired/replaced | 32345 | 32345 | 64690 | 3045 | 9864 | 12909 | -22481 | -51781 | -69.5% | -80.04% | Y | N/A | Actual units lower than imputed due to unit delay for other higher priority work. Delayed units will be completed in 2025 and 2026. | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to replace service valves < 2"
76 | O&M Expense | Gas Distribution | FH | G Dist Preventive Maint | FHI | Maint-Corr G Svc Valves | Loss of Containment on Gas Customer Connected Equipment | CCEPQ-C011 Corrective Maintenance, Gas Service Valves | Ex 3, Ch 8 | No | On-Going | Annual | 8267.1855 | 8431.6292 | 16698.8146 | 1904.797 | 5389.71 | 7294.507 | -3041.9192 | -9404.3076 | -36.08% | -56.32% | N/A | N/A | N/A | 32345 | 32345 | 64690 | 3045 | 9864 | 12909 | -22481 | -51781 | -69.5% | -80.04% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
77 | O&M Expense | Gas Distribution | FH | G Dist Preventive Maint | FHJ | Gas Non-Recurring Projects | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 3884.0044 | 3961.2617 | 7845.2661 | 1380.3384 | 1429.4887 | 2809.8271 | -2531.7729 | -5035.4389 | -63.91% | -64.18% | N | N | non-unitized: This MAT has no measurable units because it includes one‑time non‑recurring maintenance projects. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
78 | O&M Expense | Gas Distribution | FH | G Dist Preventive Maint | FHJ | Gas Non-Recurring Projects | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C028 Preventive Maintenance Gas Valves | Ex 3, Ch 8 | No | On-Going | Annual | 3884.0044 | 3961.2617 | 7845.2661 | 1379.3384 | 1429.4878 | 2808.8261 | -2531.7739 | -5036.4399 | -63.91% | -64.2% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
79 | O&M Expense | Gas Distribution | FH | G Dist Preventive Maint | FHK | GD Corrosion AC Inspections | SRM Total | SRM Total | Ex 3, Ch 9 | No | On-Going | Annual | 145.3046 | 149.1743 | 294.4789 | 201.5149 | 108.2098 | 309.7247 | -40.9645 | 15.2458 | -27.46% | 5.177% | N | N | # of inspections completed | 461 | 461 | 922 | 597 | 454 | 1051 | -7 | 129 | -1.518% | 13.99% | N | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
80 | O&M Expense | Gas Distribution | FH | G Dist Preventive Maint | FHK | GD Corrosion AC Inspections | Loss of Containment on Gas Distribution Main or Service | LOCDM-C020 Atmospheric Corrosion, Mains and Services | Ex 3, Ch 9 | No | On-Going | Annual | 145.3046 | 149.1743 | 294.4789 | 200.5149 | 108.2088 | 308.7237 | -40.9655 | 14.2448 | -27.46% | 4.837% | N/A | N/A | N/A | 461 | 461 | 922 | 597 | 454 | 1051 | -7 | 129 | -1.518% | 13.99% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
81 | O&M Expense | Gas Distribution | FH | G Dist Preventive Maint | FHL | Atmospheric Corsn Main Rep | SRM Total | SRM Total | Ex 3, Ch 9 | No | On-Going | Annual | 3243.1871 | 3329.5597 | 6572.7468 | 2414.6908 | 1574.3474 | 3989.0382 | -1755.2123 | -2583.7087 | -52.72% | -39.31% | N | N | # of Riser Replacements & Service Spans | 145 | 145 | 290 | 143 | 73 | 216 | -72 | -74 | -49.66% | -25.52% | Y | N/A | Actual units were lower than imputed due to work pulled forward the previous year and job cancellation. | Under | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to maintain and re-coat facilities that have observed corrosion or have deteriorated coating.
82 | O&M Expense | Gas Distribution | FH | G Dist Preventive Maint | FHL | Atmospheric Corsn Main Rep | Loss of Containment on Gas Distribution Main or Service | LOCDM-C020 Atmospheric Corrosion, Mains and Services | Ex 3, Ch 9 | No | On-Going | Annual | 3243.1871 | 3329.5597 | 6572.7468 | 2413.6908 | 1574.3464 | 3988.0372 | -1755.2133 | -2584.7097 | -52.72% | -39.32% | N/A | N/A | N/A | 145 | 145 | 290 | 143 | 73 | 216 | -72 | -74 | -49.66% | -25.52% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
83 | O&M Expense | Gas Distribution | FH | G Dist Preventive Maint | FHM | Atmospheric Corsn Serv Rep | SRM Total | SRM Total | Ex 3, Ch 9 | No | On-Going | Annual | 12498.84 | 12831.7092 | 25330.5492 | 3702.0644 | 5509.0262 | 9211.0906 | -7322.683 | -16119.4586 | -57.07% | -63.64% | N | Y | # of Riser Replacements & Service Spans | 56822 | 56822 | 113644 | 13229 | 18607 | 31836 | -38215 | -81808 | -67.25% | -71.99% | Y | Actual costs were lower than imputed due to reprioritization for higher priority/risk work. | Actual units were lower than imputed units due to reprioritized for higher priority/risk work. | Under | On-Target | On-Target | Proceeding as Planned | Ongoing and will continue in PG&E's 2023 GRC period
84 | O&M Expense | Gas Distribution | FH | G Dist Preventive Maint | FHM | Atmospheric Corsn Serv Rep | Loss of Containment on Gas Distribution Main or Service | LOCDM-C020 Atmospheric Corrosion, Mains and Services | Ex 3, Ch 9 | No | On-Going | Annual | 12498.84 | 12831.7092 | 25330.5492 | 3701.0644 | 5509.0252 | 9210.0896 | -7322.684 | -16120.4596 | -57.07% | -63.64% | N/A | N/A | N/A | 56822 | 56822 | 113644 | 13229 | 18607 | 31836 | -38215 | -81808 | -67.25% | -71.99% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
85 | O&M Expense | Gas Distribution | FH | G Dist Preventive Maint | FHN | Atmospheric Corsn Reg Stn Rprs | SRM Total | SRM Total | Ex 3, Ch 9 | No | On-Going | Annual | 1050.6304 | 1078.6108 | 2129.2413 | 1747.6164 | 1246.0606 | 2993.6769 | 167.4497 | 864.4357 | 15.52% | 40.6% | N | N | # of Stations Mitigated | 60 | 60 | 120 | 51 | 30 | 81 | -30 | -39 | -50% | -32.5% | Y | N/A | Actual units were lower than imputed due to work pulled forward the previous year and job cancellation. | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to maintain and re-coat facilities that have observed corrosion or have deteriorated coating.
86 | O&M Expense | Gas Distribution | FH | G Dist Preventive Maint | FHN | Atmospheric Corsn Reg Stn Rprs | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C017 Facility Corrosion Control Program | Ex 3, Ch 9 | No | On-Going | Annual | 1050.6304 | 1078.6108 | 2129.2413 | 1746.6164 | 1246.0595 | 2992.6759 | 167.4487 | 863.4347 | 15.52% | 40.55% | N/A | N/A | N/A | 60 | 60 | 120 | 51 | 30 | 81 | -30 | -39 | -50% | -32.5% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
87 | O&M Expense | Gas Distribution | FH | G Dist Preventive Maint | FHO | PM SCADA | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 1501.4811 | 1531.3473 | 3032.8283 | 1135.3622 | 1244.5014 | 2379.8636 | -286.8458 | -652.9647 | -18.73% | -21.53% | N | N | non-unitized: This program has no measurable units because it encompasses a variety of different O&M activities. A count of the operations completed is captured in SAP. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
88 | O&M Expense | Gas Distribution | FH | G Dist Preventive Maint | FHO | PM SCADA | Insufficient Capacity to Meet Customer Demand | CPCTY-C006 Distribution SCADA Maintenance | Ex 3, Ch 8 | No | On-Going | Annual | 1501.4811 | 1531.3473 | 3032.8283 | 1132.3622 | 1244.4984 | 2376.8606 | -286.8488 | -655.9677 | -18.73% | -21.63% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
89 | O&M Expense | Gas Distribution | FH | G Dist Preventive Maint | FHO | PM SCADA | Large Overpressure Event Downstream of Gas M&C Facility | LRGOP-C017 Distribution SCADA Maintenance | Ex 3, Ch 8 | No | On-Going | Annual | 1501.4811 | 1531.3473 | 3032.8283 | 1133.3622 | 1244.4994 | 2377.8616 | -286.8478 | -654.9667 | -18.73% | -21.6% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
90 | O&M Expense | Gas Distribution | FH | G Dist Preventive Maint | FHO | PM SCADA | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C003 Distribution SCADA Maintenance | Ex 3, Ch 8 | No | On-Going | Annual | 1501.4811 | 1531.3473 | 3032.8283 | 1134.3622 | 1244.5004 | 2378.8627 | -286.8468 | -653.9657 | -18.73% | -21.56% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
91 | O&M Expense | Gas Distribution | FH | G Dist Preventive Maint | FHP | CM SCADA | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 776.843 | 792.2953 | 1569.1384 | 578.7979 | 643.6947 | 1222.4926 | -148.6007 | -346.6458 | -18.76% | -22.09% | N | N | non-unitized: This program has no measurable units because it encompasses a variety of different O&M activities. A count of the operations completed is captured in SAP. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
92 | O&M Expense | Gas Distribution | FH | G Dist Preventive Maint | FHP | CM SCADA | Insufficient Capacity to Meet Customer Demand | CPCTY-C006 Distribution SCADA Maintenance | Ex 3, Ch 8 | No | On-Going | Annual | 776.843 | 792.2953 | 1569.1384 | 575.7979 | 643.6917 | 1219.4896 | -148.6037 | -349.6488 | -18.76% | -22.28% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
93 | O&M Expense | Gas Distribution | FH | G Dist Preventive Maint | FHP | CM SCADA | Large Overpressure Event Downstream of Gas M&C Facility | LRGOP-C017 Distribution SCADA Maintenance | Ex 3, Ch 8 | No | On-Going | Annual | 776.843 | 792.2953 | 1569.1384 | 576.7979 | 643.6927 | 1220.4906 | -148.6027 | -348.6478 | -18.76% | -22.22% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
94 | O&M Expense | Gas Distribution | FH | G Dist Preventive Maint | FHP | CM SCADA | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C003 Distribution SCADA Maintenance | Ex 3, Ch 8 | No | On-Going | Annual | 776.843 | 792.2953 | 1569.1384 | 577.7979 | 643.6937 | 1221.4916 | -148.6017 | -347.6468 | -18.76% | -22.16% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
95 | O&M Expense | Gas Distribution | FH | G Dist Preventive Maint | FHQ | GD Over Pressure Protectn Exp. | SRM Total | SRM Total | Ex 3, Ch 6 | No | 5 | 4 | 0 | 0 | 0 | 1057.3792 | 859.5179 | 1916.8971 | 859.5179 | 1916.8971 | 100% | 100% | N | N | non-unitized: This program has no measurable units because it encompasses a variety of different expense-related activities that are associated with the Overpressure Protection Program, like sulfur filter installations and minor sense line work on low pressure stations, in addition to conducting studies, emergency response to an overpressure event, and other miscellaneous activities. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
96 | O&M Expense | Gas Distribution | FH | G Dist Preventive Maint | FHQ | GD Over Pressure Protectn Exp. | Large Overpressure Event Downstream of Gas M&C Facility | LRGOP-M003 GD Overpressure Protection | Ex 3, Ch 6 | No | 5 | 4 | 0 | 0 | 0 | 1056.3792 | 859.5169 | 1915.8961 | 859.5169 | 1915.8961 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
97 | O&M Expense | Gas Distribution | FH | G Dist Preventive Maint | FHR | Distribution Pipeline Markers | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 1852.6175 | 1889.4682 | 3742.0857 | 16.9692 | 75.212 | 92.1811 | -1814.2562 | -3649.9046 | -96.02% | -97.54% | N | N | non-unitized: This MAT has no measurable units because it is used for multiple work activities (e.g. distribution patrol and pipeline marker maintenance). | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
98 | O&M Expense | Gas Distribution | FH | G Dist Preventive Maint | FHR | Distribution Pipeline Markers | Loss of Containment on Gas Distribution Main or Service | LOCDM-C017 Locate and Mark - Distribution | Ex 3, Ch 8 | No | On-Going | Annual | 1852.6175 | 1889.4682 | 3742.0857 | 15.9692 | 75.211 | 91.1801 | -1814.2572 | -3650.9056 | -96.02% | -97.56% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
99 | O&M Expense | Gas Distribution | FH | G Dist Preventive Maint | FHS | GD One-Time Non-Recur Exp Pjts | SRM Total | SRM Total | N/A | No | On-Going | Annual | 0 | 0 | 0 | 1977.5283 | 0 | 1977.5283 | 0 | 1977.5283 | 0% | 100% | N | N | non-unitized: This MAT has no measurable units because it includes one‑time non‑recurring maintenance projects. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
100 | O&M Expense | Gas Distribution | FH | G Dist Preventive Maint | FH# | Not assigned | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 1212.3067 | 1236.4209 | 2448.7276 | 760.9022 | 936.2351 | 1697.1373 | -300.1858 | -751.5903 | -24.28% | -30.69% | N | N | non-unitized: This MAT has no measurable units because it is used to record other support costs for the gas distribution system or can reflect standard cost variance. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
101 | O&M Expense | Gas Distribution | FH | G Dist Preventive Maint | FH# | Not assigned | Large Overpressure Event Downstream of Gas M&C Facility | LRGOP-C018 Distribution Regulator Maintenance | Ex 3, Ch 8 | No | On-Going | Annual | 1212.3067 | 1236.4209 | 2448.7276 | 759.9022 | 936.2341 | 1696.1363 | -300.1868 | -752.5913 | -24.28% | -30.73% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
102 | O&M Expense | Gas Distribution | FI | G Dist Corrective Maint | FIB | Maint-Corr-G Reg Genl | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 2301.1064 | 2368.5142 | 4669.6207 | 1529.59 | 1795.9874 | 3325.5774 | -572.5268 | -1344.0432 | -24.17% | -28.78% | N | N | non-unitized: This program has no measurable units because it encompasses a variety of different O&M activities. A count of the operations completed is captured in SAP. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
103 | O&M Expense | Gas Distribution | FI | G Dist Corrective Maint | FIB | Maint-Corr-G Reg Genl | Large Overpressure Event Downstream of Gas M&C Facility | LRGOP-C018 Distribution Regulator Maintenance | Ex 3, Ch 8 | No | On-Going | Annual | 2301.1064 | 2368.5142 | 4669.6207 | 1527.59 | 1795.9854 | 3323.5754 | -572.5288 | -1346.0452 | -24.17% | -28.83% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
104 | O&M Expense | Gas Distribution | FI | G Dist Corrective Maint | FIB | Maint-Corr-G Reg Genl | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C011 Distribution Regulator Maintenance | Ex 3, Ch 8 | No | On-Going | Annual | 2301.1064 | 2368.5142 | 4669.6207 | 1528.59 | 1795.9864 | 3324.5764 | -572.5278 | -1345.0442 | -24.17% | -28.8% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
105 | O&M Expense | Gas Distribution | FI | G Dist Corrective Maint | FIC | Maint-Corr-G Farm Tap | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 995.0182 | 1024.1659 | 2019.1842 | 141.9053 | 163.1803 | 305.0855 | -860.9857 | -1714.0986 | -84.07% | -84.89% | N | N | # of Main Leaks Repaired (non-NERBA) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
106 | O&M Expense | Gas Distribution | FI | G Dist Corrective Maint | FIC | Maint-Corr-G Farm Tap | Large Overpressure Event Downstream of Gas M&C Facility | LRGOP-C019 Farm Tap Maintenance | Ex 3, Ch 8 | No | On-Going | Annual | 995.0182 | 1024.1659 | 2019.1842 | 139.9053 | 163.1782 | 303.0835 | -860.9877 | -1716.1006 | -84.07% | -84.99% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
107 | O&M Expense | Gas Distribution | FI | G Dist Corrective Maint | FIC | Maint-Corr-G Farm Tap | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C012 Farm Tap Maintenance | Ex 3, Ch 8 | No | On-Going | Annual | 995.0182 | 1024.1659 | 2019.1842 | 140.9053 | 163.1792 | 304.0845 | -860.9867 | -1715.0996 | -84.07% | -84.94% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
108 | O&M Expense | Gas Distribution | FI | G Dist Corrective Maint | FIF | Maint-Corr-G Main Vlv | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 395.2436 | 406.8218 | 802.0654 | 1027.1477 | 750.2145 | 1777.3623 | 343.3928 | 975.2969 | 84.41% | 121.6% | N | N | # Svc Leak Repairs_AG | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
109 | O&M Expense | Gas Distribution | FI | G Dist Corrective Maint | FIF | Maint-Corr-G Main Vlv | Loss of Containment on Gas Distribution Main or Service | LOCDM-C024 Corrective Maintenance, Gas, Main Valve | Ex 3, Ch 8 | No | On-Going | Annual | 395.2436 | 406.8218 | 802.0654 | 1026.1477 | 750.2135 | 1776.3612 | 343.3918 | 974.2959 | 84.41% | 121.5% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
110 | O&M Expense | Gas Distribution | FI | G Dist Corrective Maint | FIG/ LWG (a) | Maint-Corr-G Main Lk | SRM Total | SRM Total | Ex 3, Ch 10 | No | On-Going | Annual | 35095.9718 | 35680.4333 | 70776.4051 | 35102.5885 | 32775 | 67877.5885 | -2905.4333 | -2898.8166 | -8.143% | -4.096% | N | N | # of corrosion tags cleared | 3828 | 3828 | 7656 | 2592 | 2459 | 5051 | -1369 | -2605 | -35.76% | -34.03% | Y | Actual costs were lower than imputed due to decreased leak find rates in the last three years resulting in reduced leak finds and repairs. A second factor driving cost down is the implementation of process improvement initiatives such as leak bundling. | Actual units lower than imputed due to decreased leak find rates in the last three years resulting in reduced leak finds and repairs | Under | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to repair gradeable leaks on distribution main lines.
111 | O&M Expense | Gas Distribution | FI | G Dist Corrective Maint | FIG/ LWG (a) | Maint-Corr-G Main Lk | Loss of Containment on Gas Distribution Main or Service | LOCDM-C014 Distribution Leak Management | Ex 3, Ch 10 | No | On-Going | Annual | 35095.9718 | 35680.4333 | 70776.4051 | 35102.5885 | 32775 | 67877.5885 | -2905.4333 | -2898.8166 | -8.143% | -4.096% | N/A | N/A | N/A | 3828 | 3828 | 7656 | 2592 | 2459 | 5051 | -1369 | -2605 | -35.76% | -34.03% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
112 | O&M Expense | Gas Distribution | FI | G Dist Corrective Maint | FIH | Maint-Corr_G_Svc Leak_AG | SRM Total | SRM Total | Ex 3, Ch 10 | No | On-Going | Annual | 4097.634 | 4165.8729 | 8263.5069 | 2696.9242 | 2693.28 | 5390.2042 | -1472.5929 | -2873.3028 | -35.35% | -34.77% | N | N | # of Main Dig-ins Repaired | 7838 | 7838 | 15676 | 2044 | 1726 | 3770 | -6112 | -11906 | -77.98% | -75.95% | Y | N/A | Actual units lower than imputed due to decreased leak find rates in the last three years resulting in reduced leak finds and repairs | Under | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to repair above ground gradeable leaks.
113 | O&M Expense | Gas Distribution | FI | G Dist Corrective Maint | FIH | Maint-Corr_G_Svc Leak_AG | Loss of Containment on Gas Customer Connected Equipment | CCEPQ-C004 CCE Leak Management | Ex 3, Ch 10 | No | On-Going | Annual | 4097.634 | 4165.8729 | 8263.5069 | 2697.9242 | 2693.28 | 5391.2042 | -1472.5929 | -2872.3028 | -35.35% | -34.76% | N/A | N/A | N/A | 7838 | 7838 | 15676 | 2044 | 1726 | 3770 | -6112 | -11906 | -77.98% | -75.95% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
114 | O&M Expense | Gas Distribution | FI | G Dist Corrective Maint | FIH | Maint-Corr_G_Svc Leak_AG | Loss of Containment on Gas Distribution Main or Service | LOCDM-C014 Distribution Leak Management | Ex 3, Ch 10 | No | On-Going | Annual | 4097.634 | 4165.8729 | 8263.5069 | 2698.9242 | 2693.28 | 5392.2042 | -1472.5929 | -2871.3028 | -35.35% | -34.75% | N/A | N/A | N/A | 7838 | 7838 | 15676 | 2044 | 1726 | 3770 | -6112 | -11906 | -77.98% | -75.95% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
115 | O&M Expense | Gas Distribution | FI | G Dist Corrective Maint | FII | Maint-Corr-G Cath Prot | SRM Total | SRM Total | Ex 3, Ch 9 | No | On-Going | Annual | 6233.1691 | 6341.376 | 12574.5451 | 2699.9242 | 8860.48 | 11560.4042 | 2519.104 | -1014.1409 | 39.72% | -8.065% | N | N | # of Main Dig-ins Repaired | 7838 | 5375 | 13213 | 2044 | 2555 | 4599 | -2820 | -8614 | -52.47% | -65.19% | Y | N/A | Actual units were less than imputed due to less work materialized than what was planned. | Under | On-Target | On-Target | Proceeding as Planned | Ongoing and will continue in PG&E's 2023 GRC period
116 | O&M Expense | Gas Distribution | FI | G Dist Corrective Maint | FII | Maint-Corr-G Cath Prot | Loss of Containment on Gas Distribution Main or Service | LOCDM-C018 Distribution Corrosion Control Program | Ex 3, Ch 9 | No | On-Going | Annual | 6233.1691 | 6341.376 | 12574.5451 | 7351.0475 | 8860.48 | 16211.5275 | 2519.104 | 3636.9824 | 39.72% | 28.92% | N/A | N/A | N/A | 5375 | 5375 | 10750 | 1364 | 2555 | 3919 | -2820 | -6831 | -52.47% | -63.54% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
117 | O&M Expense | Gas Distribution | FI | G Dist Corrective Maint | FII | Maint-Corr-G Cath Prot | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C018 Cathodic Protection | Ex 3, Ch 9 | No | On-Going | Annual | 6233.1691 | 6341.376 | 12574.5451 | 7352.0475 | 8860.48 | 16212.5275 | 2519.104 | 3637.9824 | 39.72% | 28.93% | N/A | N/A | N/A | 5375 | 5375 | 10750 | 1364 | 2555 | 3919 | -2820 | -6831 | -52.47% | -63.54% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
118 | O&M Expense | Gas Distribution | FI | G Dist Corrective Maint | FIJ | Maint-Corr G Main Dig-in | SRM Total | SRM Total | Ex 3, Ch 10 | No | On-Going | Annual | 995.6968 | 1012.2784 | 2007.9752 | 1277.8729 | 3039.13 | 4317.0029 | 2026.8516 | 2309.0277 | 200.2% | 115% | N | N | # of Main Dig-ins Repaired | 298 | 298 | 596 | 158 | 161 | 319 | -137 | -277 | -45.97% | -46.48% | Y | N/A | Actual units lower than imputed due to improved performance in dig-in prevention activities resulting in decreased volume of 3rd party damages. | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to fix distribution main pipeline damages caused by 3rd parties and includes expense pipe replacements < 100' of pipe
119 | O&M Expense | Gas Distribution | FI | G Dist Corrective Maint | FIJ | Maint-Corr G Main Dig-in | Loss of Containment on Gas Distribution Main or Service | LOCDM-C014 Distribution Leak Management | Ex 3, Ch 10 | No | On-Going | Annual | 995.6968 | 1012.2784 | 2007.9752 | 1278.8729 | 3039.13 | 4318.0029 | 2026.8516 | 2310.0277 | 200.2% | 115% | N/A | N/A | N/A | 298 | 298 | 596 | 158 | 161 | 319 | -137 | -277 | -45.97% | -46.48% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
120 | O&M Expense | Gas Distribution | FI | G Dist Corrective Maint | FIK | Maint-Corr G Svc Dig-in | SRM Total | SRM Total | Ex 3, Ch 10 | No | On-Going | Annual | 1595.9294 | 1622.5068 | 3218.4363 | 2084.2267 | 1713.1621 | 3797.3888 | 90.6553 | 578.9526 | 5.587% | 17.99% | N | N | # of Svc Dig-ins Repaired | 1617 | 1617 | 3234 | 1221 | 1305 | 2526 | -312 | -708 | -19.29% | -21.89% | N | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to fix service damages caused by 3rd parties and includes expense repairs to services
121 | O&M Expense | Gas Distribution | FI | G Dist Corrective Maint | FIK | Maint-Corr G Svc Dig-in | Loss of Containment on Gas Distribution Main or Service | LOCDM-C014 Distribution Leak Management | Ex 3, Ch 10 | No | On-Going | Annual | 1595.9294 | 1622.5068 | 3218.4363 | 2085.2267 | 1713.1631 | 3798.3898 | 90.6563 | 579.9536 | 5.587% | 18.02% | N/A | N/A | N/A | 1617 | 1617 | 3234 | 1221 | 1305 | 2526 | -312 | -708 | -19.29% | -21.89% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
122 | O&M Expense | Gas Distribution | FI | G Dist Corrective Maint | FIM | Major Event-Distribution Gas | SRM Total | SRM Total | Ex 3, Ch 10 | No | On-Going | Annual | 490.2497 | 498.4139 | 988.6636 | 185.5336 | 116.8002 | 302.3338 | -381.6138 | -686.3299 | -76.57% | -69.42% | N | N | # Services Repaired | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A | On-Target | Over | On-Target | Emergent | N/A
123 | O&M Expense | Gas Distribution | FI | G Dist Corrective Maint | FIM | Major Event-Distribution Gas | Loss of Containment on Gas Customer Connected Equipment | CCEPQ-C009 Major Event - Distribution Gas | Ex 3, Ch 10 | No | On-Going | Annual | 490.2497 | 498.4139 | 988.6636 | 186.5336 | 116.8012 | 303.3347 | -381.6128 | -685.3289 | -76.57% | -69.32% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
124 | O&M Expense | Gas Distribution | FI | G Dist Corrective Maint | FIM | Major Event-Distribution Gas | Insufficient Capacity to Meet Customer Demand | CPCTY-C007 Operate Transmission Regulator Station | Ex 3, Ch 10 | No | On-Going | Annual | 490.2497 | 498.4139 | 988.6636 | 187.5336 | 116.8022 | 304.3358 | -381.6118 | -684.3279 | -76.57% | -69.22% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
125 | O&M Expense | Gas Distribution | FI | G Dist Corrective Maint | FIM | Major Event-Distribution Gas | Insufficient Capacity to Meet Customer Demand | CPCTY-C008 Major Event - Distribution Gas | Ex 3, Ch 10 | No | On-Going | Annual | 490.2497 | 498.4139 | 988.6636 | 188.5336 | 116.8032 | 305.3367 | -381.6108 | -683.3269 | -76.57% | -69.12% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
126 | O&M Expense | Gas Distribution | FI | G Dist Corrective Maint | FIM | Major Event-Distribution Gas | Loss of Containment on Gas Distribution Main or Service | LOCDM-C008 Major Event - Distribution Gas | Ex 3, Ch 10 | No | On-Going | Annual | 490.2497 | 498.4139 | 988.6636 | 189.5336 | 116.8042 | 306.3378 | -381.6098 | -682.3259 | -76.56% | -69.01% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
127 | O&M Expense | Gas Distribution | FI | G Dist Corrective Maint | FIM | Major Event-Distribution Gas | Large Overpressure Event Downstream of Gas M&C Facility | LRGOP-C013 Major Event - Distribution Gas | Ex 3, Ch 10 | No | On-Going | Annual | 490.2497 | 498.4139 | 988.6636 | 190.5336 | 116.8052 | 307.3388 | -381.6088 | -681.3249 | -76.56% | -68.91% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
128 | O&M Expense | Gas Distribution | FI | G Dist Corrective Maint | FIM | Major Event-Distribution Gas | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C013 Major Event - Distribution Gas | Ex 3, Ch 10 | No | On-Going | Annual | 490.2497 | 498.4139 | 988.6636 | 191.5336 | 116.8062 | 308.3397 | -381.6078 | -680.3239 | -76.56% | -68.81% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
129 | O&M Expense | Gas Distribution | FI | G Dist Corrective Maint | FIO | Gas Overbuild - G | SRM Total | SRM Total | Ex 3, Ch 4 | No | On-Going | Annual | 853.884 | 868.1419 | 1722.0259 | 765.65 | 2506.2 | 3271.85 | 1638.0581 | 1549.8241 | 188.7% | 90% | N | N | # Svc Leak Repairs_BG (non-NERBA) | 19 | 76 | 95 | 42.75 | 139 | 181.75 | 63 | 86.75 | 82.89% | 91.32% | Y | N/A | Actual units were hihger than imputed due to the Encroachment program is based on find-it-fix-it work that needs to be field verified to determine capital or expense scope. More work was field verified as expense encroachments (partial service replacement and/or less than 100' of main relocation based on overbuilt gas pipe) than imputed. | Over | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to relocation of partial gas service and/or main (<100') to clear overbuild conflicts. For the remainder of the GRC cycle, PG&E will prioritize this work and execute within six months of identification (subject to extension with notification to regulators).
130 | O&M Expense | Gas Distribution | FI | G Dist Corrective Maint | FIO | Gas Overbuild - G | Loss of Containment on Gas Customer Connected Equipment | CCEPQ-C002 Encroachment Program | Ex 3, Ch 4 | Yes | On-Going | Annual | 213.47 | 868.1419 | 1081.6119 | 766.65 | 2506.2 | 3272.85 | 1638.0581 | 2191.2381 | 188.7% | 202.6% | N/A | N/A | N/A | 19 | 76 | 95 | 42.75 | 139 | 181.75 | 63 | 86.75 | 82.89% | 91.32% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
131 | O&M Expense | Gas Distribution | FI | G Dist Corrective Maint | FIO | Gas Overbuild - G | Loss of Containment on Gas Distribution Main or Service | LOCDM-C009 Encroachment Program | Ex 3, Ch 4 | Yes | On-Going | Annual | 640.43 | 868.1419 | 1508.5719 | 767.65 | 2506.2 | 3273.85 | 1638.0581 | 1765.2781 | 188.7% | 117% | N/A | N/A | N/A | 19 | 76 | 95 | 42.75 | 139 | 181.75 | 63 | 86.75 | 82.89% | 91.32% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
132 | O&M Expense | Gas Distribution | FI | G Dist Corrective Maint | FIP/ LWH (a) | Maint-Corr_G_Svc Leak_BG | SRM Total | SRM Total | Ex 3, Ch 10 | No | On-Going | Annual | 31649.4275 | 32176.4929 | 63825.9205 | 27892.7822 | 27819 | 55711.7822 | -4357.4929 | -8114.1383 | -13.54% | -12.71% | N | N | # Locations Inspected | 7484 | 7484 | 14968 | 4509 | 4024 | 8533 | -3460 | -6435 | -46.23% | -42.99% | Y | Actual costs were lower than imputed due to decreased leak find rates in the last three years resulting in reduced leak finds and repairs. A second factor driving cost down is the implementation of process improvement initiatives such as leak bundling. | Actual units lower than imputed due to decreased leak find rates in the last three years resulting in reduced leak finds and repairs | Under | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to complete expense repairs of gradeable leaks on service lines.
133 | O&M Expense | Gas Distribution | FI | G Dist Corrective Maint | FIP/ LWH (a) | Maint-Corr_G_Svc Leak_BG | Loss of Containment on Gas Distribution Main or Service | LOCDM-C014 Distribution Leak Management | Ex 3, Ch 10 | No | On-Going | Annual | 31649.4275 | 32176.4929 | 63825.9205 | 27892.7822 | 27819 | 55711.7822 | -4357.4929 | -8114.1383 | -13.54% | -12.71% | N/A | N/A | N/A | 7484 | 7484 | 14968 | 4509 | 4024 | 8533 | -3460 | -6435 | -46.23% | -42.99% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
134 | O&M Expense | Gas Distribution | FI | G Dist Corrective Maint | FIQ | Atmospheric Corrosion Monitorg | SRM Total | SRM Total | Ex 3, Ch 10 | No | On-Going | Annual | 1356.0955 | 1378.6789 | 2734.7744 | 456.6 | 1245.17 | 1701.77 | -133.5089 | -1033.0044 | -9.684% | -37.77% | N | N | # Tee Caps Replaced | 7762 | 15524 | 23286 | 16754 | 44477 | 61231 | 28953 | 37945 | 186.5% | 163% | Y | N/A | Actual units were higher than imputed due to Covid and post Covid challenges to access of our gas meters resulting in more AC CGI's (can't get In). | Over | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
135 | O&M Expense | Gas Distribution | FI | G Dist Corrective Maint | FIQ | Atmospheric Corrosion Monitorg | Loss of Containment on Gas Customer Connected Equipment | CCEPQ-C017 Atmospheric Corrosion, Metersets | Ex 3, Ch 10 | No | On-Going | Annual | 678.05 | 1378.6789 | 2056.7289 | 457.6 | 1245.17 | 1702.77 | -133.5089 | -353.9589 | -9.684% | -17.21% | N/A | N/A | N/A | 7762 | 15524 | 23286 | 16754 | 44477 | 61231 | 28953 | 37945 | 186.5% | 163% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
136 | O&M Expense | Gas Distribution | FI | G Dist Corrective Maint | FIQ | Atmospheric Corrosion Monitorg | Loss of Containment on Gas Distribution Main or Service | LOCDM-C020 Atmospheric Corrosion, Mains and Services | Ex 3, Ch 10 | No | On-Going | Annual | 678.05 | 1378.6789 | 2056.7289 | 458.6 | 1245.17 | 1703.77 | -133.5089 | -352.9589 | -9.684% | -17.16% | N/A | N/A | N/A | 7762 | 15524 | 23286 | 16754 | 44477 | 61231 | 28953 | 37945 | 186.5% | 163% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
137 | O&M Expense | Gas Distribution | FI | G Dist Corrective Maint | FIR | Tee-Cap Replacement Program | SRM Total | SRM Total | Ex 3, Ch 4 | No | On-Going | Annual | 2209.0109 | 2245.8964 | 4454.9073 | 2039.4798 | 2356.3288 | 4395.8086 | 110.4324 | -59.0987 | 4.917% | -1.327% | N | N | # of Meters Repaired | 1165 | 1165 | 2330 | 1196 | 1165 | 2361 | 0 | 31 | 0% | 1.33% | N | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
138 | O&M Expense | Gas Distribution | FI | G Dist Corrective Maint | FIR | Tee-Cap Replacement Program | Loss of Containment on Gas Distribution Main or Service | LOCDM-C010 Tee Cap Replacement Program | Ex 3, Ch 4 | No | On-Going | Annual | 2209.0109 | 2245.8964 | 4454.9073 | 2040.4798 | 2356.3298 | 4396.8096 | 110.4334 | -58.0977 | 4.917% | -1.304% | N/A | N/A | N/A | 1165 | 1165 | 2330 | 1196 | 1165 | 2361 | 0 | 31 | 0% | 1.33% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
139 | O&M Expense | Gas Distribution | FI | G Dist Corrective Maint | FIS | Leak Survey Meter Repair | SRM Total | SRM Total | Ex 3, Ch 10 | No | On-Going | Annual | 9658.4871 | 9819.3322 | 19477.8193 | 8214.6477 | 8067.05 | 16281.6977 | -1752.2822 | -3196.1216 | -17.85% | -16.41% | N | N | # of Meters Repaired | 80000 | 80000 | 160000 | 56458 | 43188 | 99646 | -36812 | -60354 | -46.02% | -37.72% | Y | N/A | Actual units were lower than imputed units due to reprioritization in support of higher risk or compliance work. | On-Target | On-Target | On-Target | Proceeding as Planned | Ongoing and will continue in PG&E's 2023 GRC period
140 | O&M Expense | Gas Distribution | FI | G Dist Corrective Maint | FIS | Leak Survey Meter Repair | Loss of Containment on Gas Customer Connected Equipment | CCEPQ-C004 CCE Leak Management | Ex 3, Ch 10 | No | On-Going | Annual | 9658.4871 | 9819.3322 | 19477.8193 | 8215.6477 | 8067.05 | 16282.6977 | -1752.2822 | -3195.1216 | -17.85% | -16.4% | N/A | N/A | N/A | 80000 | 80000 | 160000 | 56458 | 43188 | 99646 | -36812 | -60354 | -46.02% | -37.72% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
141 | O&M Expense | Gas Distribution | FI | G Dist Corrective Maint | FI# | Not assigned | SRM Total | SRM Total | Ex 3, Ch 10 | No | On-Going | Annual | 4148.9624 | 4218.0561 | 8367.0185 | 1726.6783 | 1640 | 3366.6783 | -2578.0561 | -5000.3403 | -61.12% | -59.76% | N | N | non-unitized: This MAT has no measurable units because it is used to record other support costs for corrective maintenance such as leak repair. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
142 | O&M Expense | Gas Distribution | FI | G Dist Corrective Maint | FI# | Not assigned | Loss of Containment on Gas Customer Connected Equipment | CCEPQ-C004 CCE Leak Management | Ex 3, Ch 10 | No | On-Going | Annual | 4148.9624 | 4218.0561 | 8367.0185 | 1726.6783 | 1640 | 3366.6783 | -2578.0561 | -5000.3403 | -61.12% | -59.76% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
143 | O&M Expense | Gas Distribution | FI | G Dist Corrective Maint | FI# | Not assigned | Loss of Containment on Gas Distribution Main or Service | LOCDM-C014 Distribution Leak Management | Ex 3, Ch 10 | No | On-Going | Annual | 4148.9624 | 4218.0561 | 8367.0185 | 1726.6783 | 1640 | 3366.6783 | -2578.0561 | -5000.3403 | -61.12% | -59.76% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
144 | O&M Expense | Gas Distribution | GF | Gas Trans & Dist Sys Mapping | GFO | Mapping Support-Distribution | SRM Total | SRM Total | Ex 3, Ch 13 | No | On-Going | Annual | 4307.388 | 4414.517 | 8721.9049 | 4573.2335 | 3192.04 | 7765.2735 | -1222.477 | -956.6314 | -27.69% | -10.97% | N | N | non-unitized: This MAT has no measurable units because it is primarily used by Gas Distribution mappers for performing work that is not billable to orders, including: map correction notifications from the Corrective Action Program (CAP), map delineation requests, request for work notifications (RWs), operating diagrams, Gas Distribution Geographic Information System (GD-GIS) corrections, data requests, and mapping tasks on orders that are financially closed. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
145 | O&M Expense | Gas Distribution | GF | Gas Trans & Dist Sys Mapping | GFQ | GT&D Data Management | SRM Total | SRM Total | N/A | No | On-Going | Annual | 0 | 0 | 0 | 673.7231 | 1613.89 | 2287.6131 | 1613.89 | 2287.6131 | 0% | 100% | N | N | non-unitized: This MAT has no measurable units because it is primarily intended for Gas data enhancements in GD-GIS, Palantir Foundry implementation for Gas to enable data analysis, discrepancy identification and correction across core systems of record (i.e. GD-GIS and SAP), and Gas data maturity work in alignment with company data management standards. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
146 | O&M Expense | Gas Distribution | GG | Gas Trans & Dist Sys Modeling | GGA | Gas System Planning_GSO | SRM Total | SRM Total | Ex 3, Ch 11 | No | On-Going | Annual | 6923.6213 | 7162.3092 | 14085.9305 | 4934.0604 | 4857.8334 | 9791.8938 | -2304.4758 | -4294.0367 | -32.18% | -30.48% | N | N | non-unitized: This MAT has no measurable units because it is used to record labor costs. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
147 | O&M Expense | Gas Distribution | GG | Gas Trans & Dist Sys Modeling | GGA | Gas System Planning_GSO | Insufficient Capacity to Meet Customer Demand | CPCTY-C003 Gas System Planning | Ex 3, Ch 11 | No | On-Going | Annual | 6923.6213 | 7162.3092 | 14085.9305 | 4935.0604 | 4857.8344 | 9792.8948 | -2304.4748 | -4293.0357 | -32.18% | -30.48% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
148 | O&M Expense | Gas Distribution | GG | Gas Trans & Dist Sys Modeling | GG# | Not assigned | SRM Total | SRM Total | Ex 3, Ch 11 | No | On-Going | Annual | 2522.9469 | 2609.9241 | 5132.871 | 1 | 0 | 1 | -2609.9241 | -5131.871 | -100% | -99.98% | N | N | non-unitized: This MAT has no measurable units because it is used to record labor costs. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
149 | O&M Expense | Gas Distribution | GG | Gas Trans & Dist Sys Modeling | GG# | Not assigned | Insufficient Capacity to Meet Customer Demand | CPCTY-C004 Gas Distribution Portfolio Management and Engineering | Ex 3, Ch 11 | No | On-Going | Annual | 2522.9469 | 2609.9241 | 5132.871 | 0 | 0 | 0 | -2609.9241 | -5132.871 | -100% | -100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
150 | O&M Expense | Gas Distribution | GM | Manage Energy Efficiency-NonBA | GMC | GD LNG/CNG Station | SRM Total | SRM Total | Ex 3, Ch 6 | No | On-Going | Annual | 4592.6857 | 4670.9148 | 9263.6005 | 3452.7256 | 3070.7792 | 6523.5048 | -1600.1356 | -2740.0957 | -34.26% | -29.58% | N | N | # of Meters Remediated | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
151 | O&M Expense | Gas Distribution | GM | Manage Energy Efficiency-NonBA | GMC | GD LNG/CNG Station | Loss of Containment on CNG Station Equipment | CNGEQ-C002 Gas Distribution LNG/CNG Station O&M | Ex 3, Ch 6 | No | On-Going | Annual | 4592.6857 | 4670.9148 | 9263.6005 | 3453.7256 | 3070.7802 | 6524.5058 | -1600.1346 | -2739.0947 | -34.26% | -29.57% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
152 | O&M Expense | Gas Distribution | HY | Change/Maint Used Gas Meters | HYI | G Meter Atmospheric Corrosion | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 920.493 | 952.2265 | 1872.7195 | 787.4238 | 788.425 | 1575.8488 | -163.8015 | -296.8707 | -17.2% | -15.85% | N | N | # of Meters Remediated | 16077 | 16077 | 32154 | 0 | 8094 | 8094 | -7983 | -24060 | -49.65% | -74.83% | Y | N/A | Actual units were lower than imputed units due to a reduction in incoming workload due to fewer identified instances of Atmospheric Corrosion. | On-Target | On-Target | On-Target | Proceeding as Planned | Ongoing and will continue in PG&E's 2023 GRC period
153 | O&M Expense | Gas Distribution | HY | Change/Maint Used Gas Meters | HYI | G Meter Atmospheric Corrosion | Loss of Containment on Gas Customer Connected Equipment | CCEPQ-C008 Meter Set Atmospheric Corrosion Remediation | Ex 3, Ch 8 | No | On-Going | Annual | 920.493 | 952.2265 | 1872.7195 | 788.4238 | 788.426 | 1576.8498 | -163.8005 | -295.8697 | -17.2% | -15.8% | N/A | N/A | N/A | 16077 | 16077 | 32154 | 0 | 8094 | 8094 | -7983 | -24060 | -49.65% | -74.83% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
154 | O&M Expense | Gas Distribution | HY | Change/Maint Used Gas Meters | HY# | Not assigned | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 0 | 0 | 0 | 5.5846 | 0 | 5.5846 | 0 | 5.5846 | 0% | 100% | N | N | non-unitized: This MAT has no measurable units because it reflects standard cost variance related to field services provider cost centers. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
155 | O&M Expense | Gas Distribution | JQ | G Dist Integrity Mgt | JQA | DIMP Leak Survey | SRM Total | SRM Total | Ex 3, Ch 10 | No | On-Going | Annual | 861.2795 | 886.2255 | 1747.505 | 842.4522 | 578.2278 | 1420.68 | -307.9977 | -326.825 | -34.75% | -18.7% | N | N | # of Inspections | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
156 | O&M Expense | Gas Distribution | JQ | G Dist Integrity Mgt | JQA | DIMP Leak Survey | Loss of Containment on Gas Distribution Main or Service | LOCDM-C014 Distribution Leak Management | Ex 3, Ch 10 | No | On-Going | Annual | 861.2795 | 886.2255 | 1747.505 | 843.4522 | 578.2288 | 1421.681 | -307.9967 | -325.824 | -34.75% | -18.65% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
157 | O&M Expense | Gas Distribution | JQ | G Dist Integrity Mgt | JQC | Mark and Locate Program | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 3581.9039 | 3673.3146 | 7255.2185 | 3089.9506 | 3237.3108 | 6327.2614 | -436.0039 | -927.9572 | -11.87% | -12.79% | N | N | Fittings Mitigated | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
158 | O&M Expense | Gas Distribution | JQ | G Dist Integrity Mgt | JQC | Mark and Locate Program | Loss of Containment on Gas Distribution Main or Service | LOCDM-C025 Dig-In Reduction Team | Ex 3, Ch 8 | No | On-Going | Annual | 3581.9039 | 3673.3146 | 7255.2185 | 3090.9506 | 3237.3118 | 6328.2624 | -436.0029 | -926.9562 | -11.87% | -12.78% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
159 | O&M Expense | Gas Distribution | JQ | G Dist Integrity Mgt | JQD | DIMP Emergent Work | SRM Total | SRM Total | Ex 3, Ch 4 | No | On-Going | Annual | 4162.1311 | 4284.7357 | 8446.8668 | 75.5711 | 1279.6 | 1355.1711 | -3005.1357 | -7091.6958 | -70.14% | -83.96% | N | N | non-unitized: This program has no measurable units because DIMP emergent work consists of work resulting from risk analysis and operational events. This work includes laboratory analysis, engineering, and incident investigations. Projects vary considerably and are not comparable so this work is not unitized. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
160 | O&M Expense | Gas Distribution | JQ | G Dist Integrity Mgt | JQD | DIMP Emergent Work | Loss of Containment on Gas Customer Connected Equipment | CCEPQ-C005 DIMP Emergent Work | Ex 3, Ch 4 | No | On-Going | Annual | 208.1066 | 4284.7357 | 4492.8423 | 76.5711 | 1279.6 | 1356.1711 | -3005.1357 | -3136.6712 | -70.14% | -69.81% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
161 | O&M Expense | Gas Distribution | JQ | G Dist Integrity Mgt | JQD | DIMP Emergent Work | Loss of Containment on Gas Distribution Main or Service | LOCDM-C011 DIMP Emergent Work | Ex 3, Ch 4 | No | On-Going | Annual | 3954.0246 | 4284.7357 | 8238.7603 | 77.5711 | 1279.6 | 1357.1711 | -3005.1357 | -6881.5892 | -70.14% | -83.53% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
162 | O&M Expense | Gas Distribution | JQ | G Dist Integrity Mgt | JQE | Plastic Program | SRM Total | SRM Total | Ex 3, Ch 4 | No | On-Going | Annual | 330.7923 | 340.5365 | 671.3288 | 168.8791 | 46.3957 | 215.2748 | -294.1408 | -456.054 | -86.38% | -67.93% | N | N | non-unitized: This program has no measurable units because it oversees selecting, testing, and development of plastic materials, tools and construction methods for PG&E’s plastic gas distribution system. Projects vary considerably and are not comparable so this work is not unitized. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
163 | O&M Expense | Gas Distribution | JQ | G Dist Integrity Mgt | JQE | Plastic Program | Loss of Containment on Gas Distribution Main or Service | LOCDM-C012 Plastics Program | Ex 3, Ch 4 | No | On-Going | Annual | 330.7923 | 340.5365 | 671.3288 | 169.8791 | 46.3967 | 216.2758 | -294.1398 | -455.053 | -86.38% | -67.78% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
164 | O&M Expense | Gas Distribution | JQ | G Dist Integrity Mgt | JQG | Fitting Mitigation Program | SRM Total | SRM Total | Ex 3, Ch 4 | No | On-Going | Annual | 2431.5304 | 2503.1564 | 4934.6868 | 1983.518 | 521.3428 | 2504.8608 | -1981.8136 | -2429.8261 | -79.17% | -49.24% | N | N | Fittings Mitigated | 480 | 480 | 960 | 139 | 0 | 139 | -480 | -821 | -100% | -85.52% | Y | N/A | Actual units were lower than imputed units because MAT JQG consists of the Metfit and Kerotest fitting mitigation programs. The Metfit program is not unitized and the unitized Kerotest work has been delayed indefinitely. No Kerotest fittings were mitigated in 2024. | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to focus on removal of compression-style mechanical fittings with risk of corrosion, failure, and leak. For the remainder of the GRC cycle, PG&E anticipates that this program will continue to be lower priority than other work in Gas Distribution.
165 | O&M Expense | Gas Distribution | JQ | G Dist Integrity Mgt | JQG | Fitting Mitigation Program | Loss of Containment on Gas Distribution Main or Service | LOCDM-M005 Fitting Mitigation Program | Ex 3, Ch 4 | No | On-Going | Annual | 2431.5304 | 2503.1564 | 4934.6868 | 1984.518 | 521.3438 | 2505.8618 | -1981.8126 | -2428.8251 | -79.17% | -49.22% | N/A | N/A | N/A | 480 | 480 | 960 | 139 | 0 | 139 | -480 | -821 | -100% | -85.52% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
166 | O&M Expense | Gas Distribution | JQ | G Dist Integrity Mgt | JQK | Cross Bored Sewer Project | SRM Total | SRM Total | Ex 3, Ch 4 | No | On-Going | Annual | 13294.7392 | 13686.3645 | 26981.1037 | 13438.3777 | 6031.8131 | 19470.1907 | -7654.5514 | -7510.9129 | -55.93% | -27.84% | N | Y | # of Inspections | 19313 | 19313 | 38626 | 8085 | 3655 | 11740 | -15658 | -26886 | -81.07% | -69.61% | Y | Actual costs were lower than imputed costs due to reprioritization in support of higher risk or compliance work. | Actual units were lower than imputed units due to reprioritization in support of higher risk or compliance work. | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is locate and repair legacy crossbores.
167 | O&M Expense | Gas Distribution | JQ | G Dist Integrity Mgt | JQK | Cross Bored Sewer Project | Loss of Containment on Gas Distribution Main or Service | LOCDM-M006 Cross Bored Sewer Project | Ex 3, Ch 4 | No | On-Going | Annual | 13294.7392 | 13686.3645 | 26981.1037 | 13439.3777 | 6031.8141 | 19471.1917 | -7654.5504 | -7509.9119 | -55.93% | -27.83% | N/A | N/A | N/A | 19313 | 19313 | 38626 | 8085 | 3655 | 11740 | -15658 | -26886 | -81.07% | -69.61% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
168 | O&M Expense | Gas Distribution | JQ | G Dist Integrity Mgt | JQL | DIMP Program Management | SRM Total | SRM Total | Ex 3, Ch 4 | No | On-Going | Annual | 4868.1104 | 5011.5111 | 9879.6215 | 6.5947 | 158.68 | 165.2747 | -4852.8311 | -9714.3468 | -96.83% | -98.33% | N | N | non-unitized: This MAT has no measurable units because it is used to record labor costs and is not used to measure gas plant units repaired or replaced. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | Actual costs were lower than imputed due to DIMP labor cost being transitioned to OM/OS in 2021. | N/A | Under | Under | On-Target | Cancelled | Cancelled due to DIMP labor cost being transitioned to OM/OS in 2021.
169 | O&M Expense | Gas Distribution | JQ | G Dist Integrity Mgt | JQL | DIMP Program Management | Loss of Containment on Gas Customer Connected Equipment | CCEPQ-C010 DIMP Program Management | Ex 3, Ch 4 | Yes | On-Going | Annual | 243.4055 | 5011.5111 | 5254.9166 | 7.5947 | 158.68 | 166.2747 | -4852.8311 | -5088.6419 | -96.83% | -96.84% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
170 | O&M Expense | Gas Distribution | JQ | G Dist Integrity Mgt | JQL | DIMP Program Management | Loss of Containment on Gas Distribution Main or Service | LOCDM-C021 DIMP Program Management | Ex 3, Ch 4 | Yes | On-Going | Annual | 4624.7049 | 5011.5111 | 9636.216 | 8.5947 | 158.68 | 167.2747 | -4852.8311 | -9468.9412 | -96.83% | -98.26% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
171 | O&M Expense | Gas Distribution | OM | Operational Management | OM# | Not assigned | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 3, Ch 13 | No | On-Going | Annual | 13394.3553 | 13773.499 | 27167.8543 | 21468.7997 | 18764.1575 | 40232.9572 | 4990.6585 | 13065.1029 | 36.23% | 48.09% | N | N | non-unitized: This MAT has no measurable units because it is used to record labor and employee‑related costs to provide supervision and management support. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | Actual costs were lower than imputed regulatory values due to higher OM/OS allocation of supervision and management labor costs. MWC OM/OS represents labor costs to supervise or manage PG&E personnel who charge their time directly to orders, net of overhead allocations applied between capital and expense. The overhead is applied to both MWC OM and MWC OS, which represents labor costs in support of personnel. Due to a higher starting point in overall costs, driven by a mixture of different resources, and updated allocations a lower amount remained recorded in expense MWC OM/OS. | N/A | On-Target | On-Target | Over | Proceeding as Planned | N/A
172 | Expense | GT&S | 34 | Maint Gas Trans-Subsid | 34A(a) | Stan-Pac Expense | SRM Total | SRM Total | Ex 3, Ch 13 | No | On-Going | Annual | 2738.2705 | 2737.937 | 5476.2075 | 2090.9097 | 1449 | 3539.9097 | -1288.937 | -1936.2978 | -47.08% | -35.36% | NO | NO | Non-Unitized | 0 | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | N/A
173 | Expense | GT&S | 34 | Maint Gas Trans-Subsid | 34A(a) | Stan-Pac Expense | Loss of Containment on Gas Transmission Pipeline | LOCTM-C038 Stan-Pac Expense | Ex 3, Ch 13 | No | On-Going | Annual | 2738.2705 | 2737.937 | 5476.2075 | 2090.9097 | 1449 | 3539.9097 | -1288.937 | -1936.2978 | -47.08% | -35.36% | N/A | N/A | N/A | 0 | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
174 | Expense | GT&S | AH | Maint Gas Storage Fac | AH1(b) | WELL - Integrity Assessments | SRM Total | SRM Total | Ex 3, Ch 7 | No | On-Going | Annual | 9806.6629 | 9850.9111 | 19657.574 | 6542.8812 | 5813.6108 | 12356.492 | -4037.3003 | -7301.082 | -40.98% | -37.14% | NO | NO | Various | 268 | 268 | 536 | 255 | 265 | 520 | -3 | -16 | -1.119% | -2.985% | NO | N/A | N/A | On-Target | On-Target | Under | Proceeding as planned | N/A
175 | Expense | GT&S | AH | Maint Gas Storage Fac | AH1(b) | WELL - Integrity Assessments | Loss of Containment at Natural Gas Storage Well or Reservoir | NGSWR-C003 Well Inspections and Rework | Ex 3, Ch 7 | No | On-Going | Annual | 9806.6629 | 9850.9111 | 19657.574 | 6542.8812 | 5813.6108 | 12356.492 | -4037.3003 | -7301.082 | -40.98% | -37.14% | N/A | N/A | N/A | 268 | 268 | 536 | 255 | 265 | 520 | -3 | -16 | -1.119% | -2.985% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
176 | Expense | GT&S | AH | Maint Gas Storage Fac | AH2 | WELL - Reworks | SRM Total | SRM Total | Ex 3, Ch 7 | No | On-Going | Annual | 3427.5999 | 3443.065 | 6870.6649 | 0 | 0 | 0 | -3443.065 | -6870.6649 | -100% | -100% | NO | NO | # of Well reworks | 2 | 2 | 4 | 0 | 0 | 0 | -2 | -4 | -100% | -100% | YES | N/A | Actual units were lower than imputed units due to units now being capitalized under WELL Reworks MAT 3L3. | Under | On-Target | Under | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. Units are anticipated to remain capitalized and captured in MAT 3L3.
177 | Expense | GT&S | AH | Maint Gas Storage Fac | AH2 | WELL - Reworks | Loss of Containment at Natural Gas Storage Well or Reservoir | NGSWR-C003 Well Inspections and Rework | Ex 3, Ch 7 | No | On-Going | Annual | 3427.5999 | 3443.065 | 6870.6649 | 0 | 0 | 0 | -3443.065 | -6870.6649 | -100% | -100% | N/A | N/A | N/A | 2 | 2 | 4 | 0 | 0 | 0 | -2 | -4 | -100% | -100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
178 | Expense | GT&S | AH | Maint Gas Storage Fac | AH3 | WELL - Other | SRM Total | SRM Total | Ex 3, Ch 7 | No | On-Going | Annual | 2832.4107 | 2845.1907 | 5677.6014 | 1995.5589 | 3382.124 | 5377.6829 | 536.9333 | -299.9185 | 18.87% | -5.282% | NO | NO | non-unitized: This MAT has no measurable units because it captures miscellaneous engineering support. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | N/A
179 | Expense | GT&S | AH | Maint Gas Storage Fac | AH3 | WELL - Other | Loss of Containment at Natural Gas Storage Well or Reservoir | NGSWR-C004 Well Emergent and Emergency Support | Ex 3, Ch 7 | No | On-Going | Annual | 2832.4107 | 2845.1907 | 5677.6014 | 1995.5589 | 3382.124 | 5377.6829 | 536.9333 | -299.9185 | 18.87% | -5.282% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
180 | Expense | GT&S | AH | Maint Gas Storage Fac | AH4 | Gill Ranch Operations & Maint | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 3, Ch 7 | No | On-Going | Annual | 3189.0936 | 3202.1564 | 6391.25 | 4539.2451 | 6123.599 | 10662.8441 | 2921.4427 | 4271.5941 | 91.23% | 66.84% | NO | NO | non-unitized: This MAT has no measurable units because it is used to record costs for Gill Ranch Storage. The type of the work performed at the storage are different and are not comparable. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | N/A
181 | Expense | GT&S | AH | Maint Gas Storage Fac | AH# (c) | Not assigned | SRM Total | SRM Total | Ex 3, Ch 7 | No | On-Going | Annual | 2265.6949 | 2275.918 | 4541.6129 | 476.816 | 437.9405 | 914.7565 | -1837.9775 | -3626.8563 | -80.76% | -79.86% | NO | NO | non-unitized: This MAT has no measurable units because it is used to record various engineering support costs. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | N/A
182 | Expense | GT&S | AH | Maint Gas Storage Fac | AH# (c) | Not assigned | Loss of Containment at Natural Gas Storage Well or Reservoir | NGSWR-C003 Well Inspections and Rework | Ex 3, Ch 7 | No | On-Going | Annual | 2265.6949 | 2275.918 | 4541.6129 | 476.816 | 437.9405 | 914.7565 | -1837.9775 | -3626.8563 | -80.76% | -79.86% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
183 | Expense | GT&S | CM | GT Operate System | CMA | GT&S Operations | SRM Total | SRM Total | Ex 3, Ch 11 | No | On-Going | Annual | 15572.9448 | 16031.5777 | 31604.5225 | 13898.3144 | 14096.6 | 27994.9144 | -1934.9777 | -3609.6081 | -12.07% | -11.42% | NO | NO | non-unitized: This MAT has no measurable units because MAT CMA represents a chargeback MAT for Gas Control related headcount (operators). It represents non-workstream program thus it is a continuous program with no unit completions associated with the charges. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | N/A
184 | Expense | GT&S | CM | GT Operate System | CMA | GT&S Operations | Insufficient Capacity to Meet Customer Demand | CPCTY-C002 GT&S Operations | Ex 3, Ch 11 | No | On-Going | Annual | 15572.9448 | 16031.5777 | 31604.5225 | 13898.3144 | 14096.6 | 27994.9144 | -1934.9777 | -3609.6081 | -12.07% | -11.42% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
185 | Expense | GT&S | CM | GT Operate System | CMA | GT&S Operations | Loss of Containment on Gas Transmission Pipeline | LOCTM-C021 GT&S Operations | Ex 3, Ch 11 | No | On-Going | Annual | 15572.9448 | 16031.5777 | 31604.5225 | 13898.3144 | 14096.6 | 27994.9144 | -1934.9777 | -3609.6081 | -12.07% | -11.42% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
186 | Expense | GT&S | CM | GT Operate System | CMA | GT&S Operations | Large Overpressure Event Downstream of Gas M&C Facility | LRGOP-C015 GT&S Operations | Ex 3, Ch 11 | No | On-Going | Annual | 15572.9448 | 16031.5777 | 31604.5225 | 13898.3144 | 14096.6 | 27994.9144 | -1934.9777 | -3609.6081 | -12.07% | -11.42% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
187 | Expense | GT&S | CM | GT Operate System | CMA | GT&S Operations | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C026 GT&S Operations | Ex 3, Ch 11 | No | On-Going | Annual | 15572.9448 | 16031.5777 | 31604.5225 | 13898.3144 | 14096.6 | 27994.9144 | -1934.9777 | -3609.6081 | -12.07% | -11.42% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
188 | Expense | GT&S | CM | GT Operate System | CMA | GT&S Operations | Loss of Containment at Natural Gas Storage Well or Reservoir | NGSWR-C001 GT&S Operations | Ex 3, Ch 11 | No | On-Going | Annual | 15572.9448 | 16031.5777 | 31604.5225 | 13898.3144 | 14096.6 | 27994.9144 | -1934.9777 | -3609.6081 | -12.07% | -11.42% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
189 | Expense | GT&S | CM | GT Operate System | CMB | ElecPwr CompFuel & Oth Elec Eq | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 3, Ch 11 | No | On-Going | Annual | 27881.2489 | 28702.3689 | 56583.6178 | 35400.077 | 40866.3825 | 76266.4595 | 12164.0137 | 19682.8418 | 42.38% | 34.79% | YES | YES | non-unitized: his MAT has no measurable units because it includes electricity costs for electrically connected gas equipment, and electrically powered gas compressor stations. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | Actual costs were higher than imputed due to higher electricity costs and usage at electrically powered gas compressor stations. | N/A | On-Target | On-Target | Over | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to pay for the electricity costs used to power electrically powered gas compressors, and electrically connected gas field equipment.
190 | Expense | GT&S | DF | G&E T&D Locate and Mark | DFA | Locate and Mark | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 1346.3682 | 1386.1465 | 2732.5148 | 697.0116 | 891.7374 | 1588.749 | -494.4091 | -1143.7658 | -35.67% | -41.86% | NO | NO | # of Tickets | 6073 | 6073 | 12146 | 3402 | 3468 | 6870 | -2605 | -5276 | -42.89% | -43.44% | YES | N/A | Actual units were lower than imputed units due to the ticket increase from third-party driven work not materializing as expected. | Under | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2027 GRC periond. The purpose of this program is to field mark PG&E's underground facilities in response to 811 tickets as required by CA GC 4216.
191 | Expense | GT&S | DF | G&E T&D Locate and Mark | DFA | Locate and Mark | Loss of Containment on Gas Transmission Pipeline | LOCTM-C009 Locate and Mark - Transmission | Ex 3, Ch 8 | No | On-Going | Annual | 1346.3682 | 1386.1465 | 2732.5148 | 697.0116 | 891.7374 | 1588.749 | -494.4091 | -1143.7658 | -35.67% | -41.86% | N/A | N/A | N/A | 6073 | 6073 | 12146 | 3402 | 3468 | 6870 | -2605 | -5276 | -42.89% | -43.44% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
192 | Expense | GT&S | DF | G&E T&D Locate and Mark | DFB | Locate and Mark - Standby | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 5420.6595 | 5580.8123 | 11001.4718 | 5179.5161 | 7034.3445 | 12213.8607 | 1453.5323 | 1212.3889 | 26.05% | 11.02% | NO | NO | # of times standby is required onsite | 5381 | 5381 | 10762 | 5658 | 5706 | 11364 | 325 | 602 | 6.04% | 5.594% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | N/A
193 | Expense | GT&S | DF | G&E T&D Locate and Mark | DFB | Locate and Mark - Standby | Loss of Containment on Gas Transmission Pipeline | LOCTM-C010 Locate and Mark - Transmission Standby | Ex 3, Ch 8 | No | On-Going | Annual | 5420.6595 | 5580.8123 | 11001.4718 | 5179.5161 | 7034.3445 | 12213.8607 | 1453.5323 | 1212.3889 | 26.05% | 11.02% | N/A | N/A | N/A | N | 5381 | N/A | 5658 | 5706 | 11364 | 325 | 11364 | 6.04% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
194 | Expense | GT&S | GF | Gas Trans & Dist Sys Mapping | GFP | Mapping Support-Transmission | SRM Total | SRM Total | Ex 3, Ch 13 | No | On-Going | Annual | 5563.2373 | 5701.6005 | 11264.8379 | 2434.4455 | 2663.7679 | 5098.2134 | -3037.8326 | -6166.6245 | -53.28% | -54.74% | NO | NO | non-unitized: This MAT has no measurable units because the work encompassed is varied with no consistent unit of measure. This largely includes responding to requests, research, and remediation to data in gas systems (T&D) of record for assets not encompassed in an order. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | Under | Proceeding as planned | N/A
195 | Expense | GT&S | GF | Gas Trans & Dist Sys Mapping | GFP | Mapping Support-Transmission | Loss of Containment on Gas Transmission Pipeline | LOCTM-C036 Production Mapping Transmission | Ex 3, Ch 13 | No | On-Going | Annual | 5563.2373 | 5701.6005 | 11264.8379 | 2434.4455 | 2663.7679 | 5098.2134 | -3037.8326 | -6166.6245 | -53.28% | -54.74% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
196 | Expense | GT&S | GF | Gas Trans & Dist Sys Mapping | GFQ | GT&D Data Management | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | N/A | No | On-Going | Annual | 0 | 0 | 0 | 1036.2469 | 2305.3 | 3341.5469 | 2305.3 | 3341.5469 | 0% | N/A | NO | NO | non-unitized: This MAT has no measurable units because the work encompassed is varied with no consistent unit of measure. This largely includes responding to requests, research, and remediation to data in gas systems (T&D) of record for assets not encompassed in an order. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | N/A
197 | Expense | GT&S | GJ | Gas Transmission Mitigate Corr | GJA(d) | Electrical Interference - AC | SRM Total | SRM Total | Ex 3, Ch 9 | No | On-Going | Annual | 1539.3264 | 1552.8877 | 3092.214 | 1266.0421 | 1103.8303 | 2369.8723 | -449.0574 | -722.3417 | -28.92% | -23.36% | NO | NO | Various | 329 | 329 | 658 | 159 | 509 | 668 | 180 | 10 | 54.71% | 1.52% | YES | N/A | Actual units were higher than imputed units due to the catch up of low 2023 actual units. Arc Fault program starts to survey new locations in 2024, while 2023 focused on the clean up of multiple year program with low number of units being surveyed. | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to investigate and monitor AC Interference as required by 49 CFR § 192.467 and 473.
198 | Expense | GT&S | GJ | Gas Transmission Mitigate Corr | GJA(d) | Electrical Interference - AC | Loss of Containment on Gas Transmission Pipeline | LOCTM-C033 Electrical Interference Program | Ex 3, Ch 9 | No | On-Going | Annual | 1539.3264 | 1552.8877 | 3092.214 | 1266.0421 | 1103.8303 | 2369.8723 | -449.0574 | -722.3417 | -28.92% | -23.36% | N/A | N/A | N/A | 329 | 329 | 658 | 159 | 509 | 668 | 180 | 10 | 54.71% | 1.52% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
199 | Expense | GT&S | GJ | Gas Transmission Mitigate Corr | GJA(d) | Electrical Interference - AC | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C019 Electrical Interference | Ex 3, Ch 9 | No | On-Going | Annual | 1539.3264 | 1552.8877 | 3092.214 | 1266.0421 | 1103.8303 | 2369.8723 | -449.0574 | -722.3417 | -28.92% | -23.36% | N/A | N/A | N/A | 329 | 329 | 658 | 159 | 509 | 668 | 180 | 10 | 54.71% | 1.52% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
200 | Expense | GT&S | GJ | Gas Transmission Mitigate Corr | GJB | Atmospheric Corrosion | SRM Total | SRM Total | Ex 3, Ch 9 | No | On-Going | Annual | 3841.7394 | 3875.5847 | 7717.3241 | 7167.4575 | 15031.2045 | 22198.662 | 11155.6197 | 14481.3379 | 287.8% | 187.6% | YES | YES | Various | 94 | 94 | 188 | 62 | 45 | 107 | -49 | -81 | -52.13% | -43.09% | YES | Actual costs were higher than imputed due the majority of the units were on line 300/400, which are large pipelines and complex jobs. In 2024, asbestos abatement became a common mitigating factor which increased unit cost. | Actual units were lower than imputed units MAT was impacted by long lead permit delays and scope changes, including lead abatement requirements. Multiple jobs were underway in 2024, but completion will not be realized until 2025. Furthermore, in 2024 the threshold for capitalizing span re-coates changed from 100 feet to 40 feet, so actual units dropped in GJB and increased in 3KA. | Under | On-Target | Over | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to maintain and re-coat facilities that have observed corrosion or have deteriorated coating.
201 | Expense | GT&S | GJ | Gas Transmission Mitigate Corr | GJB | Atmospheric Corrosion | Loss of Containment on Gas Transmission Pipeline | LOCTM-C034 Atmospheric Corrosion Program | Ex 3, Ch 9 | No | On-Going | Annual | 3841.7394 | 3875.5847 | 7717.3241 | 7167.4575 | 15031.2045 | 22198.662 | 11155.6197 | 14481.3379 | 287.8% | 187.6% | N/A | N/A | N/A | 94 | 94 | 188 | 62 | 45 | 107 | -49 | -81 | -52.13% | -43.09% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
202 | Expense | GT&S | GJ | Gas Transmission Mitigate Corr | GJB | Atmospheric Corrosion | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C017 Facility Corrosion Control Program | Ex 3, Ch 9 | No | On-Going | Annual | 3841.7394 | 3875.5847 | 7717.3241 | 7167.4575 | 15031.2045 | 22198.662 | 11155.6197 | 14481.3379 | 287.8% | 187.6% | N/A | N/A | N/A | 94 | 94 | 188 | 62 | 45 | 107 | -49 | -81 | -52.13% | -43.09% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
203 | Expense | GT&S | GJ | Gas Transmission Mitigate Corr | GJC(e) | Cathodic Protection Exp | SRM Total | SRM Total | Ex 3, Ch 9 | No | On-Going | Annual | 414.4137 | 418.0646 | 832.4783 | 291.7303 | 601.4374 | 893.1678 | 183.3728 | 60.6894 | 43.86% | 7.29% | NO | NO | RMU Covered by Service Fees | 1000 | 1000 | 2000 | 889 | 965 | 1854 | -35 | -146 | -3.5% | -7.3% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | N/A
204 | Expense | GT&S | GJ | Gas Transmission Mitigate Corr | GJC(e) | Cathodic Protection Exp | Loss of Containment on Gas Transmission Pipeline | LOCTM-C019 Cathodic Protection | Ex 3, Ch 9 | No | On-Going | Annual | 414.4137 | 418.0646 | 832.4783 | 291.7303 | 601.4374 | 893.1678 | 183.3728 | 60.6894 | 43.86% | 7.29% | N/A | N/A | N/A | 1000 | 1000 | 2000 | 889 | 965 | 1854 | -35 | -146 | -3.5% | -7.3% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
205 | Expense | GT&S | GJ | Gas Transmission Mitigate Corr | GJD | Test Station Exp | SRM Total | SRM Total | Ex 3, Ch 9 | No | On-Going | Annual | 247.0824 | 249.2592 | 496.3416 | 242.5938 | 136.3159 | 378.9097 | -112.9433 | -117.4319 | -45.31% | -23.66% | NO | NO | # of test stations installed | 10 | 10 | 20 | 2 | 2 | 4 | -8 | -16 | -80% | -80% | YES | N/A | Actual units were lower than imputed units because fewer expense test stations (CTS) needed to be installed to meet requirement for 1 CTS per mile. | Under | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to install test station to meet the requirement of "sufficient test stations" required via 49 § 192.469.
206 | Expense | GT&S | GJ | Gas Transmission Mitigate Corr | GJD | Test Station Exp | Loss of Containment on Gas Transmission Pipeline | LOCTM-C019 Cathodic Protection | Ex 3, Ch 9 | No | On-Going | Annual | 247.0824 | 249.2592 | 496.3416 | 242.5938 | 136.3159 | 378.9097 | -112.9433 | -117.4319 | -45.31% | -23.66% | N/A | N/A | N/A | 10 | 10 | 20 | 2 | 2 | 4 | -8 | -16 | -80% | -80% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
207 | Expense | GT&S | GJ | Gas Transmission Mitigate Corr | GJE(f) | Close Interval Survey (CIS) | SRM Total | SRM Total | Ex 3, Ch 9 | No | On-Going | Annual | 4141.9315 | 4178.4215 | 8320.3529 | 1877.165 | 1071.0608 | 2948.2257 | -3107.3607 | -5372.1272 | -74.37% | -64.57% | NO | NO | Various | 451 | 451 | 902 | 178.17 | 92 | 270.17 | -359 | -631.83 | -79.6% | -70.05% | YES | N/A | Actual units were lower than imputed units due to reprioritization in support of higher risk or compliance work. | Under | On-Target | Under | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. This program is a method for determining the adequacy of cathodic protection between corrosion monitoring points. This data is used to evaluate the health of the corrosion control system. Locations of possible active external corrosion are identified and analyzed through excavation and/or direct examination.
208 | Expense | GT&S | GJ | Gas Transmission Mitigate Corr | GJE(f) | Close Interval Survey (CIS) | Loss of Containment on Gas Transmission Pipeline | LOCTM-C019 Cathodic Protection | Ex 3, Ch 9 | No | On-Going | Annual | 4141.9315 | 4178.4215 | 8320.3529 | 1877.165 | 1071.0608 | 2948.2257 | -3107.3607 | -5372.1272 | -74.37% | -64.57% | N/A | N/A | N/A | 451 | 451 | 902 | 178 | 92 | 270 | -359 | -632 | -79.6% | -70.07% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
209 | Expense | GT&S | GJ | Gas Transmission Mitigate Corr | GJE(f) | Close Interval Survey (CIS) | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C018 Cathodic Protection | Ex 3, Ch 9 | No | On-Going | Annual | 4141.9315 | 4178.4215 | 8320.3529 | 1877.165 | 1071.0608 | 2948.2257 | -3107.3607 | -5372.1272 | -74.37% | -64.57% | N/A | N/A | N/A | 451 | 451 | 902 | 178 | 92 | 270 | -359 | -632 | -79.6% | -70.07% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
210 | Expense | GT&S | GJ | Gas Transmission Mitigate Corr | GJF | Electrical Interference - DC | SRM Total | SRM Total | Ex 3, Ch 9 | No | On-Going | Annual | 801.9187 | 808.9835 | 1610.9022 | 1616.5283 | 2137.7661 | 3754.2943 | 1328.7825 | 2143.3921 | 164.3% | 133.1% | NO | NO | non-unitized: This MAT has no measurable units because this MAT code is to perform Dynamic/Static DC Reactive/Proactive investigation, and it is mainly vendor or employee’s time charged to perform the investigation. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | N/A
211 | Expense | GT&S | GJ | Gas Transmission Mitigate Corr | GJF | Electrical Interference - DC | Loss of Containment on Gas Transmission Pipeline | LOCTM-C033 Electrical Interference Program | Ex 3, Ch 9 | No | On-Going | Annual | 801.9187 | 808.9835 | 1610.9022 | 1616.5283 | 2137.7661 | 3754.2943 | 1328.7825 | 2143.3921 | 164.3% | 133.1% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
212 | Expense | GT&S | GJ | Gas Transmission Mitigate Corr | GJF | Electrical Interference - DC | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C019 Electrical Interference | Ex 3, Ch 9 | No | On-Going | Annual | 801.9187 | 808.9835 | 1610.9022 | 1616.5283 | 2137.7661 | 3754.2943 | 1328.7825 | 2143.3921 | 164.3% | 133.1% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
213 | Expense | GT&S | GJ | Gas Transmission Mitigate Corr | GJH(g) | Internal Corrosion | SRM Total | SRM Total | Ex 3, Ch 9 | No | On-Going | Annual | 6066.0923 | 6119.534 | 12185.6263 | 838.3169 | 2391.9185 | 3230.2354 | -3727.6155 | -8955.3909 | -60.91% | -73.49% | NO | NO | Various | 2743 | 2743 | 5486 | 1395 | 1571 | 2966 | -1172 | -2520 | -42.73% | -45.94% | YES | N/A | Actual units were lower than imputed units because: 1) work was done and paid by a third party, so no rate case units are claimed, 2) fewer internal corrosion monitoring devices were installed than anticipated that required monitoring, 3) drips required less frequent maintenance than anticipated, and 4) fewer internal corrosion non-destructive examinations were performed. | Under | On-Target | Under | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to investigate and monitor Internal Corrosion as required by 49 CFR § 192.475.
214 | Expense | GT&S | GJ | Gas Transmission Mitigate Corr | GJH(g) | Internal Corrosion | Loss of Containment on Gas Transmission Pipeline | LOCTM-C032 Internal Corrosion Program | Ex 3, Ch 9 | No | On-Going | Annual | 6066.0923 | 6119.534 | 12185.6263 | 838.3169 | 2391.9185 | 3230.2354 | -3727.6155 | -8955.3909 | -60.91% | -73.49% | N/A | N/A | N/A | 2743 | 2743 | 5486 | 1395 | 1571 | 2966 | -1172 | -2520 | -42.73% | -45.94% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
215 | Expense | GT&S | GJ | Gas Transmission Mitigate Corr | GJJ | Low Read Investigations | SRM Total | SRM Total | Ex 3, Ch 9 | No | On-Going | Annual | 290.9477 | 293.5109 | 584.4585 | 0 | 0.5451 | 0.5451 | -292.9658 | -583.9134 | -99.81% | -99.91% | NO | NO | non-unitized: This MAT has no measurable units because the type of work varies by situation. Complex corrosion investigations are driven by requests from corrosion field services to corrosion engineering to help troubleshoot complex corrosion issues as needed, and the level of support varies based on the unique circumstances of each problem. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | N/A
216 | Expense | GT&S | GJ | Gas Transmission Mitigate Corr | GJJ | Low Read Investigations | Loss of Containment on Gas Transmission Pipeline | LOCTM-C019 Cathodic Protection | Ex 3, Ch 9 | No | On-Going | Annual | 290.9477 | 293.5109 | 584.4585 | 0 | 0.5451 | 0.5451 | -292.9658 | -583.9134 | -99.81% | -99.91% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
217 | Expense | GT&S | GJ | Gas Transmission Mitigate Corr | GJK | Corrosion Support | SRM Total | SRM Total | Ex 3, Ch 9 | No | On-Going | Annual | 2865.1826 | 2890.4246 | 5755.6072 | 1445.9071 | 1667.5743 | 3113.4814 | -1222.8503 | -2642.1258 | -42.31% | -45.91% | NO | NO | non-unitized: This MAT has no measurable units because it reflects labor costs supporting data and program management. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | N/A
218 | Expense | GT&S | GJ | Gas Transmission Mitigate Corr | GJK | Corrosion Support | Loss of Containment on Gas Transmission Pipeline | LOCTM-C035 Transmission Corrosion Control Program | Ex 3, Ch 9 | No | On-Going | Annual | 2865.1826 | 2890.4246 | 5755.6072 | 1445.9071 | 1667.5743 | 3113.4814 | -1222.8503 | -2642.1258 | -42.31% | -45.91% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
219 | Expense | GT&S | GJ | Gas Transmission Mitigate Corr | GJK | Corrosion Support | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C017 Facility Corrosion Control Program | Ex 3, Ch 9 | No | On-Going | Annual | 2865.1826 | 2890.4246 | 5755.6072 | 1445.9071 | 1667.5743 | 3113.4814 | -1222.8503 | -2642.1258 | -42.31% | -45.91% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
220 | Expense | GT&S | GJ | Gas Transmission Mitigate Corr | GJM(h) | Casings | SRM Total | SRM Total | Ex 3, Ch 9 | No | On-Going | Annual | 4276.6017 | 4314.2782 | 8590.8799 | 2279.9808 | 790.8101 | 3070.7908 | -3523.4681 | -5520.0891 | -81.67% | -64.26% | NO | NO | Various | 1181 | 1181 | 2362 | 1137 | 857 | 1994 | -324 | -368 | -27.43% | -15.58% | YES | N/A | Actual units were lower than imputed units due to the threshold change of expense casing mitigation in April 2024 (casing length between 40 ft to 100 ft are moved to capital bucket) and the lower # of casings that required accelerated casing leak survey. | On-Target | On-Target | Under | Proceeding as planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The purpose of this program is to test, minitor and test casing to ensure each buried or submerged pipeline being electrically isolated from the metallic casing it is within (49 CFR Part 192.467) and all casings are tested/inspected to assure electrical isolation once per calendar year (49 CFR § 192.465).
221 | Expense | GT&S | GJ | Gas Transmission Mitigate Corr | GJM(h) | Casings | Loss of Containment on Gas Transmission Pipeline | LOCTM-C035 Transmission Corrosion Control Program | Ex 3, Ch 9 | No | On-Going | Annual | 4276.6017 | 4314.2782 | 8590.8799 | 2279.9808 | 790.8101 | 3070.7908 | -3523.4681 | -5520.0891 | -81.67% | -64.26% | N/A | N/A | N/A | 1181 | 1181 | 2362 | 1137 | 857 | 1994 | -324 | -368 | -27.43% | -15.58% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
222 | Expense | GT&S | GM | Manage Energy Efficiency-NonBA | GMD | LNG / CNG | SRM Total | SRM Total | Ex 3, Ch 5 | No | On-Going | Annual | 2650.8404 | 2699.0033 | 5349.8437 | 3616.9924 | 3850.3411 | 7467.3335 | 1151.3378 | 2117.4898 | 42.66% | 39.58% | NO | NO | non-unitized: This MAT has no measurable units due to the variability in O&M activities the MAT includes. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | N/A
223 | Expense | GT&S | GM | Manage Energy Efficiency-NonBA | GMD | LNG / CNG | Loss of Containment on LNG/CNG Portable Equipment | LNCNG-C002 LNG/CNG Portable Expense | Ex 3, Ch 5 | No | On-Going | Annual | 2650.8404 | 2699.0033 | 5349.8437 | 3616.9924 | 3850.3411 | 7467.3335 | 1151.3378 | 2117.4898 | 42.66% | 39.58% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
224 | Expense | GT&S | GM | Manage Energy Efficiency-NonBA | GMD | LNG / CNG | Loss of Containment on Gas Transmission Pipeline | LOCTM-C002 LNG/CNG to Support Strength Testing | Ex 3, Ch 5 | No | On-Going | Annual | 2650.8404 | 2699.0033 | 5349.8437 | 3616.9924 | 3850.3411 | 7467.3335 | 1151.3378 | 2117.4898 | 42.66% | 39.58% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
225 | Expense | GT&S | HP | CGT Balancing Accounts | HPA | TIMP - Other | SRM Total | SRM Total | Ex 3, Ch 5 | No | On-Going | Annual | 9804.1524 | 9880.5302 | 19684.6826 | 9706.6025 | 11029.0852 | 20735.6877 | 1148.555 | 1051.0051 | 11.62% | 5.339% | NO | NO | non-unitized: This MAT has no measurable units because it is used to record costs for Subpart O Integrity Management Risk Analysis. The type of work performed are not comparable. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | N/A
226 | Expense | GT&S | HP | CGT Balancing Accounts | HPA | TIMP - Other | Loss of Containment on Gas Transmission Pipeline | LOCTM-C029 Risk Analysis | Ex 3, Ch 5 | No | On-Going | Annual | 9804.1524 | 9880.5302 | 19684.6826 | 9706.6025 | 11029.0852 | 20735.6877 | 1148.555 | 1051.0051 | 11.62% | 5.339% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
227 | Expense | GT&S | HP | CGT Balancing Accounts | HPB | Traditional ILI Runs | SRM Total | SRM Total | Ex 3, Ch 5 | No | On-Going | Annual | 33561.7789 | 33823.2368 | 67385.0157 | 70894.1775 | 55800.0629 | 126694.2404 | 21976.8261 | 59309.2247 | 64.98% | 88.02% | YES | YES | Various | 337.27 | 337 | 674.27 | 457 | 358 | 815 | 21 | 140.73 | 6.231% | 20.87% | NO | Actual costs were higher than imputed due to increased costs associated with challenging inspections in the 2024 portfolio. These inspections required more sophisticated tools to assess the pipelines, increase the flow rate to enable inspection, and support customers that would have been impacted by the inspection. | N/A | Over | On-Target | Over | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to assess pipeline integrity for the internal and external condition of transmission line pipe as required by 49 CFR Subpart O.
228 | Expense | GT&S | HP | CGT Balancing Accounts | HPB | Traditional ILI Runs | Loss of Containment on Gas Transmission Pipeline | LOCTM-C005 In-Line Inspection | Ex 3, Ch 5 | No | On-Going | Annual | 33561.7789 | 33823.2368 | 67385.0157 | 70894.1775 | 55800.0629 | 126694.2404 | 21976.8261 | 59309.2247 | 64.98% | 88.02% | N/A | N/A | N/A | 337.27 | 337 | 674.27 | 457 | 358 | 815 | 21 | 140.73 | 6.231% | 20.87% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
229 | Expense | GT&S | HP | CGT Balancing Accounts | HPC | ECDA Indirect Inspections | SRM Total | SRM Total | Ex 3, Ch 5 | No | On-Going | Annual | 7382.6277 | 7440.1409 | 14822.7687 | 8316.0772 | 8920.3965 | 17236.4737 | 1480.2556 | 2413.705 | 19.9% | 16.28% | NO | NO | Miles inspected | 67.13 | 67 | 134.13 | 38.99 | 37 | 75.99 | -30 | -58.14 | -44.78% | -43.35% | YES | N/A | Actual units were lower than imputed units due to fewer miles of pipeline assessed with ECDA. This was due to the decision to utilize other assessment technologies which led to a lower scope of work materializing. | Under | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to perform indirect inspections along pipelines as part of an ECDA.
230 | Expense | GT&S | HP | CGT Balancing Accounts | HPC | ECDA Indirect Inspections | Loss of Containment on Gas Transmission Pipeline | LOCTM-C022 Direct Assessment | Ex 3, Ch 5 | No | On-Going | Annual | 7382.6277 | 7440.1409 | 14822.7687 | 8316.0772 | 8920.3965 | 17236.4737 | 1480.2556 | 2413.705 | 19.9% | 16.28% | N/A | N/A | N/A | 67.13 | 67 | 134.13 | 39 | 37 | 76 | -30 | -58.13 | -44.78% | -43.34% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
231 | Expense | GT&S | HP | CGT Balancing Accounts | HPE | Integrity Manage Leak Survey | SRM Total | SRM Total | Ex 3, Ch 5 | No | On-Going | annual | 276.1159 | 278.267 | 554.3829 | 179.4054 | 151.3539 | 330.7593 | -126.9131 | -223.6236 | -45.61% | -40.34% | NO | NO | non-unitized: This MAT has no measurable units because this programs records costs associated with transmission leak surveys conducted on conducted on Class 3/4 non HCA pipeline operating under 30 percent Specified Minimum Yield Strength as required by Subpart O. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | N/A
232 | Expense | GT&S | HP | CGT Balancing Accounts | HPE | Integrity Manage Leak Survey | Loss of Containment on Gas Transmission Pipeline | LOCTM-C029 Risk Analysis | Ex 3, Ch 5 | No | On-Going | annual | 276.1159 | 278.267 | 554.3829 | 179.4054 | 151.3539 | 330.7593 | -126.9131 | -223.6236 | -45.61% | -40.34% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
233 | Expense | GT&S | HP | CGT Balancing Accounts | HPF | Hydrostatic Testing - IM | SRM Total | SRM Total | Ex 3, Ch 5 | No | On-Going | Annual | 21325.5687 | 21491.7023 | 42817.271 | 35560.2918 | 22551.6239 | 58111.9157 | 1059.9216 | 15294.6447 | 4.932% | 35.72% | NO | NO | Miles | 3.27 | 3 | 6.27 | 12.02 | 5 | 17.02 | 2 | 10.75 | 66.67% | 171.5% | YES | N/A | Actual units were higher than imputed units due to a larger amount of in-year compliance driven work coming due | Over | On-Target | Over | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to conduct hydrostatic tests for the purpose of assessing pipeline identified by TIMP to be in compliance with 49 CFR Part 192, Subpart O. The hydrostatic testing work involves three efforts: 1. Review and validation of records to prove a pipeline has had a prior hydrostatic test performed 2. Pipeline replacement where necessary to prepare a pipeline for testing 3. Filling the inside of the pipeline with water and raising the pressure to a predetermined value and holding it for a period of time.
234 | Expense | GT&S | HP | CGT Balancing Accounts | HPF | Hydrostatic Testing - IM | Loss of Containment on Gas Transmission Pipeline | LOCTM-C026 TIMP Strength Testing | Ex 3, Ch 5 | No | On-Going | Annual | 21325.5687 | 21491.7023 | 42817.271 | 35560.2918 | 22551.6239 | 58111.9157 | 1059.9216 | 15294.6447 | 4.932% | 35.72% | N/A | N/A | N/A | 3.27 | 3 | 6.27 | 12.02 | 5 | 17.02 | 2 | 10.75 | 66.67% | 171.5% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
235 | Expense | GT&S | HP | CGT Balancing Accounts | HPI | ILI Direct Exam and Repair | SRM Total | SRM Total | Ex 3, Ch 5 | No | On-Going | Annual | 48185.77 | 48561.1539 | 96746.9239 | 47027.7249 | 24620.6201 | 71648.345 | -23940.5338 | -25098.5789 | -49.3% | -25.94% | YES | YES | non-unitized: This MAT has no measurable units because it involves direct examination and repair work that is based on data collected through both Traditional and Non-Traditional ILI runs. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | Actual costs were lower than imputed due to less digs materializing than expected which was driven by less scheduled or immediate anomalies found than on historical ILI runs. | N/A | On-Target | On-Target | Under | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to conduct direct examination digs and repairs made as a result of the ILI inspections.
236 | Expense | GT&S | HP | CGT Balancing Accounts | HPI | ILI Direct Exam and Repair | Loss of Containment on Gas Transmission Pipeline | LOCTM-C005 In-Line Inspection | Ex 3, Ch 5 | No | On-Going | Annual | 48185.77 | 48561.1539 | 96746.9239 | 47027.7249 | 24620.6201 | 71648.345 | -23940.5338 | -25098.5789 | -49.3% | -25.94% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
237 | Expense | GT&S | HP | CGT Balancing Accounts | HPJ | ICDA Indirect Inspections | SRM Total | SRM Total | Ex 3, Ch 5 | No | On-Going | Annual | 718.4544 | 724.0514 | 1442.5058 | 32.6216 | 0.03202 | 32.6536 | -724.0194 | -1409.8522 | -100% | -97.74% | NO | NO | # of Projects | 11 | 11 | 22 | 0 | 0 | 0 | -11 | -22 | -100% | -100% | YES | N/A | Actual units were lower than imputed units due to fewer miles of pipeline assessed with ICDA. This was due to the decision to utilize other assessment technologies which led to a lower scope of work materializing. | Under | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to perform engineering as part of ICDA.
238 | Expense | GT&S | HP | CGT Balancing Accounts | HPJ | ICDA Indirect Inspections | Loss of Containment on Gas Transmission Pipeline | LOCTM-C022 Direct Assessment | Ex 3, Ch 5 | No | On-Going | Annual | 718.4544 | 724.0514 | 1442.5058 | 32.6216 | 0.03202 | 32.6536 | -724.0194 | -1409.8522 | -100% | -97.74% | N/A | N/A | N/A | 11 | 11 | 22 | 0 | 0 | 0 | -11 | -22 | -100% | -100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
239 | Expense | GT&S | HP | CGT Balancing Accounts | HPK | SCCDA Indirect Inspections | SRM Total | SRM Total | Ex 3, Ch 5 | No | On-Going | Annual | 1745.2767 | 1758.8731 | 3504.1498 | 839.7284 | 2190.0242 | 3029.7526 | 431.1512 | -474.3972 | 24.51% | -13.54% | NO | NO | # Miles Assessed | 15.87 | 16 | 31.87 | 0 | 27 | 27 | 11 | -4.87 | 68.75% | -15.28% | YES | N/A | Actual units were higher than imputed units due to more miles of pipeline assessed with SCCDA. This was due to the decision to utilize SCCDA rather than other assessment technologies which led to higher scope of work. | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The pupose of this program is to perform indirect inspections along pipelines as part of SCCDA.
240 | Expense | GT&S | HP | CGT Balancing Accounts | HPK | SCCDA Indirect Inspections | Loss of Containment on Gas Transmission Pipeline | LOCTM-C022 Direct Assessment | Ex 3, Ch 5 | No | On-Going | Annual | 1745.2767 | 1758.8731 | 3504.1498 | 839.7284 | 2190.0242 | 3029.7526 | 431.1512 | -474.3972 | 24.51% | -13.54% | N/A | N/A | N/A | 15.87 | 16 | 31.87 | 0 | 27 | 27 | 11 | -4.87 | 68.75% | -15.28% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
241 | Expense | GT&S | HP | CGT Balancing Accounts | HPM | Repairs / Replace < '50ft | SRM Total | SRM Total | Ex 3, Ch 5 | No | On-Going | Annual | 4446.3524 | 4480.991 | 8927.3434 | 139.0111 | 1069.429 | 1208.4401 | -3411.562 | -7718.9033 | -76.13% | -86.46% | NO | NO | non-unitized: This MAT has no measurable units because it is used to record costs for very short pipe replacements in lieu of test (<50ft). | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | Under | Proceeding as planned | N/A
242 | Expense | GT&S | HP | CGT Balancing Accounts | HPM | Repairs / Replace < '50ft | Loss of Containment on Gas Transmission Pipeline | LOCTM-C026 TIMP Strength Testing | Ex 3, Ch 5 | No | On-Going | Annual | 4446.3524 | 4480.991 | 8927.3434 | 139.0111 | 1069.429 | 1208.4401 | -3411.562 | -7718.9033 | -76.13% | -86.46% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
243 | Expense | GT&S | HP | CGT Balancing Accounts | HPN | ECDA Direct Examinations | SRM Total | SRM Total | Ex 3, Ch 5 | No | On-Going | Annual | 36825.3393 | 37112.2215 | 73937.5609 | 27086.2017 | 21617.6936 | 48703.8954 | -15494.5279 | -25233.6655 | -41.75% | -34.13% | YES | YES | Digs | 168 | 168 | 336 | 122 | 95 | 217 | -73 | -119 | -43.45% | -35.42% | YES | Actual costs were lower than imputed due to fewer miles of pipeline assessed with ECDA. This was due to fewer miles of HCAs that required ECDA assessments which led to lower costs. | Actual units were lower than imputed units due to fewer miles of pipeline assessed with EDCA. This was due to the decision to utilize other assessment technologies which led to lower scope of work. | Under | On-Target | Under | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to perform direct examinations as part of ECDA.
244 | Expense | GT&S | HP | CGT Balancing Accounts | HPN | ECDA Direct Examinations | Loss of Containment on Gas Transmission Pipeline | LOCTM-C022 Direct Assessment | Ex 3, Ch 5 | No | On-Going | Annual | 36825.3393 | 37112.2215 | 73937.5609 | 27086.2017 | 21617.6936 | 48703.8954 | -15494.5279 | -25233.6655 | -41.75% | -34.13% | N/A | N/A | N/A | 168 | 168 | 336 | 122 | 95 | 217 | -73 | -119 | -43.45% | -35.42% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
245 | Expense | GT&S | HP | CGT Balancing Accounts | HPO | ICDA Direct Examinations | SRM Total | SRM Total | Ex 3, Ch 5 | No | On-Going | Annual | 12665.5697 | 12764.2389 | 25429.8086 | 1242.7365 | 131.9796 | 1374.7161 | -12632.2593 | -24055.0925 | -98.97% | -94.59% | YES | YES | Digs | 43 | 43 | 86 | 4 | 0 | 4 | -43 | -82 | -100% | -95.35% | YES | Actual costs were lower than imputed due to fewer miles of pipeline assessed with ICDA. This was due to fewer miles of HCAs that required ICDA assessments which led to lower costs. | Actual units were lower than imputed units due to fewer miles of pipeline assessed with IDCA. This was due to the decision to utilize other assessment technologies which led to lower scope of work. | Under | On-Target | Under | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to perform direct examinations as part of ICDA.
246 | Expense | GT&S | HP | CGT Balancing Accounts | HPO | ICDA Direct Examinations | Loss of Containment on Gas Transmission Pipeline | LOCTM-C022 Direct Assessment | Ex 3, Ch 5 | No | On-Going | Annual | 12665.5697 | 12764.2389 | 25429.8086 | 1242.7365 | 131.9796 | 1374.7161 | -12632.2593 | -24055.0925 | -98.97% | -94.59% | N/A | N/A | N/A | 43 | 43 | 86 | 4 | 0 | 4 | -43 | -82 | -100% | -95.35% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
247 | Expense | GT&S | HP | CGT Balancing Accounts | HPP | SCCDA Direct Examinations | SRM Total | SRM Total | Ex 3, Ch 5 | No | On-Going | Annual | 17035.1859 | 17167.8959 | 34203.0818 | 17.6374 | 15578.1959 | 15595.8333 | -1589.7001 | -18607.2485 | -9.26% | -54.4% | NO | NO | Digs | 77 | 77 | 154 | 0 | 103 | 103 | 26 | -51 | 33.77% | -33.12% | YES | N/A | Actual units were higher than imputed units due to more miles of pipeline assessed with SCCDCA. This was due to the decision to utilize SCCDA rather than other assessment technologies which led to higher scope of work. | Under | On-Target | Under | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to perform direct examinations as part of SCCDA.
248 | Expense | GT&S | HP | CGT Balancing Accounts | HPP | SCCDA Direct Examinations | Loss of Containment on Gas Transmission Pipeline | LOCTM-C022 Direct Assessment | Ex 3, Ch 5 | No | On-Going | Annual | 17035.1859 | 17167.8959 | 34203.0818 | 17.6374 | 15578.1959 | 15595.8333 | -1589.7001 | -18607.2485 | -9.26% | -54.4% | N/A | N/A | N/A | 77 | 77 | 154 | 0 | 103 | 103 | 26 | -51 | 33.77% | -33.12% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
249 | Expense | GT&S | HP | CGT Balancing Accounts | HPR | Non-Traditional ILI Runs | SRM Total | SRM Total | Ex 3, Ch 5 | No | On-Going | Annual | 14392.6442 | 14504.7679 | 28897.4121 | 17293.2659 | 20451.9811 | 37745.2471 | 5947.2133 | 8847.835 | 41% | 30.62% | NO | YES | Miles | 6.23 | 6 | 12.23 | 4.1 | 8 | 12.1 | 2 | -0.13 | 33.33% | -1.063% | YES | Actual costs were higher than imputed due to a larger volume of NT-ILI driven assessments which was driven by less alternative assessment methods, such as ECDA, Pipe Replacement, and Strength Testing, being feasible or more costly to perform integrity assessments in the planned 2024 locations. Furthermore, this program had emergent work and a stuck tool that also contributed to the increase in cost. | Actual units were higher than imputed units because alternative assessment methods, such as ECDA, Pipe Replacement, and Strength Testing, were not feasible or more costly to perform integrity assessments at planned locations in 2024. | On-Target | On-Target | Over | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to conduct non‐traditional ILI cleaning and inspection runs on gas transmission pipelines with tools propelled by any method other than gas flow.
250 | Expense | GT&S | HP | CGT Balancing Accounts | HPR | Non-Traditional ILI Runs | Loss of Containment on Gas Transmission Pipeline | LOCTM-C005 In-Line Inspection | Ex 3, Ch 5 | No | On-Going | Annual | 14392.6442 | 14504.7679 | 28897.4121 | 17293.2659 | 20451.9811 | 37745.2471 | 5947.2133 | 8847.835 | 41% | 30.62% | N/A | N/A | N/A | 6.23 | 6 | 12.23 | 4.1 | 8 | 12.1 | 2 | -0.13 | 33.33% | -1.063% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
251 | Expense | GT&S | HP | CGT Balancing Accounts | HPS | Geo-Hazard Studies | SRM Total | SRM Total | Ex 3, Ch 5 | No | On-Going | annual | 3014.4653 | 3037.9491 | 6052.4144 | 1927.311 | 1969.0724 | 3896.3834 | -1068.8767 | -2156.031 | -35.18% | -35.62% | NO | NO | non-unitized: This MAT has no measurable units because it is used to record costs for identifying geo-hazards such as soil-creep, dormant landslides with potential to re-activate, and subsidence. The type of work performed are not comparable. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | N/A
252 | Expense | GT&S | HP | CGT Balancing Accounts | HPS | Geo-Hazard Studies | Loss of Containment on Gas Transmission Pipeline | LOCTM-C001 Geo-Hazard Threat Identification and Mitigation | Ex 3, Ch 5 | No | On-Going | annual | 3014.4653 | 3037.9491 | 6052.4144 | 1927.311 | 1969.0724 | 3896.3834 | -1068.8767 | -2156.031 | -35.18% | -35.62% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
253 | Expense | GT&S | HP | CGT Balancing Accounts | HPT | Root Cause Analysis | SRM Total | SRM Total | Ex 3, Ch 5 | No | On-Going | Annual | 2871.0086 | 2893.3747 | 5764.3833 | 1048.0014 | 1203.1043 | 2251.1057 | -1690.2705 | -3513.2777 | -58.42% | -60.95% | NO | NO | non-unitized: This MAT has no measurable units because it is used to record costs to perform root cause analysis of significant incidents or issues on pipelines. The type of work performed are not comparable. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | N/A
254 | Expense | GT&S | HP | CGT Balancing Accounts | HPT | Root Cause Analysis | Loss of Containment on Gas Transmission Pipeline | LOCTM-C030 Root Cause Analysis | Ex 3, Ch 5 | No | On-Going | Annual | 2871.0086 | 2893.3747 | 5764.3833 | 1048.0014 | 1203.1043 | 2251.1057 | -1690.2705 | -3513.2777 | -58.42% | -60.95% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
255 | Expense | GT&S | HP | CGT Balancing Accounts | HPU | TIMP Direct Examinations | SRM Total | SRM Total | Ex 3, Ch 5 | No | On-Going | Annual | 25659.9366 | 25859.8364 | 51519.773 | 19207.7252 | 4777.069 | 23984.7942 | -21082.7674 | -27534.9788 | -81.53% | -53.45% | YES | YES | # of Direct Examination Projects | 24 | 24 | 48 | 17 | 9 | 26 | -15 | -22 | -62.5% | -45.83% | YES | Actual costs were lower than imputed units due to fewer miles of expense DE HCA assessments than anticipated and the capitalization of units. The capitialization threshold for recoats changed from 100 feet to 40 feet. | Actual units were lower than imputed units due to recapitalization of recoating from 100 feet to 40 feet and fewer miles of pipeline assessed with expense DE. This lead to fewer miles of HCAs that required expense DE assessments which led to lower units. | Under | On-Target | Under | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to perform 100% Direct Examinations on pipeline segments less than 40 feet.
256 | Expense | GT&S | HP | CGT Balancing Accounts | HPU | TIMP Direct Examinations | Loss of Containment on Gas Transmission Pipeline | LOCTM-C022 Direct Assessment | Ex 3, Ch 5 | No | On-Going | Annual | 25659.9366 | 25859.8364 | 51519.773 | 19207.7252 | 4777.069 | 23984.7942 | -21082.7674 | -27534.9788 | -81.53% | -53.45% | N/A | N/A | N/A | 24 | 24 | 48 | 17 | 9 | 26 | -15 | -22 | -62.5% | -45.83% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
257 | Expense | GT&S | JO | GT Pipeline Maintenance | JO1 | PM Scada Maintenance | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 349.0068 | 356.4646 | 705.4715 | 355.0947 | 376.8816 | 731.9764 | 20.417 | 26.5049 | 5.728% | 3.757% | NO | NO | non-unitized: This MAT has no measurable units because majority of the orders under these MATs exist as Asset Maintenance Backbone and Station (AMBBS) orders. AMBBS records “operations” which are not necessarily equivalent to a unit. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | N/A
258 | Expense | GT&S | JO | GT Pipeline Maintenance | JO1 | PM Scada Maintenance | Insufficient Capacity to Meet Customer Demand | CPCTY-C005 Transmission SCADA Maintenance | Ex 3, Ch 8 | No | On-Going | Annual | 349.0068 | 356.4646 | 705.4715 | 0 | 376.8816 | 376.8816 | 20.417 | -328.5899 | 5.728% | -46.58% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
259 | Expense | GT&S | JO | GT Pipeline Maintenance | JO1 | PM Scada Maintenance | Large Overpressure Event Downstream of Gas M&C Facility | LRGOP-C016 Transmission SCADA Maintenance | Ex 3, Ch 8 | No | On-Going | Annual | 349.0068 | 356.4646 | 705.4715 | 355.0947 | 376.8816 | 731.9764 | 20.417 | 26.5049 | 5.728% | 3.757% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
260 | Expense | GT&S | JO | GT Pipeline Maintenance | JO1 | PM Scada Maintenance | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C002 Transmission SCADA Maintenance | Ex 3, Ch 8 | No | On-Going | Annual | 349.0068 | 356.4646 | 705.4715 | 355.0947 | 376.8816 | 731.9764 | 20.417 | 26.5049 | 5.728% | 3.757% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
261 | Expense | GT&S | JO | GT Pipeline Maintenance | JO2 | CM Scada Maintenance | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 251.408 | 256.7802 | 508.1882 | 186.3302 | 185.7377 | 372.0679 | -71.0425 | -136.1203 | -27.67% | -26.79% | NO | NO | non-unitized: This MAT has no measurable units because majority of the orders under these MATs exist as Asset Maintenance Backbone and Station (AMBBS) orders. AMBBS records “operations” which are not necessarily equivalent to a unit. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | N/A
262 | Expense | GT&S | JO | GT Pipeline Maintenance | JO2 | CM Scada Maintenance | Insufficient Capacity to Meet Customer Demand | CPCTY-C005 Transmission SCADA Maintenance | Ex 3, Ch 8 | No | On-Going | Annual | 251.408 | 256.7802 | 508.1882 | 186.3302 | 185.7377 | 372.0679 | -71.0425 | -136.1203 | -27.67% | -26.79% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
263 | Expense | GT&S | JO | GT Pipeline Maintenance | JO2 | CM Scada Maintenance | Large Overpressure Event Downstream of Gas M&C Facility | LRGOP-C016 Transmission SCADA Maintenance | Ex 3, Ch 8 | No | On-Going | Annual | 251.408 | 256.7802 | 508.1882 | 186.3302 | 185.7377 | 372.0679 | -71.0425 | -136.1203 | -27.67% | -26.79% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
264 | Expense | GT&S | JO | GT Pipeline Maintenance | JO2 | CM Scada Maintenance | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C002 Transmission SCADA Maintenance | Ex 3, Ch 8 | No | On-Going | Annual | 251.408 | 256.7802 | 508.1882 | 0 | 185.7377 | 185.7377 | -71.0425 | -322.4505 | -27.67% | -63.45% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
265 | Expense | GT&S | JO | GT Pipeline Maintenance | JOA | Cath Prot Rectifier Maintenanc | SRM Total | SRM Total | Ex 3, Ch 9 | No | On-Going | Annual | 118.2768 | 120.8067 | 239.0835 | 326.5746 | 212.9497 | 539.5243 | 92.143 | 300.4408 | 76.27% | 125.7% | NO | NO | # of Rectifiers Maintained | 919 | 919 | 1838 | 944 | 886 | 1830 | -33 | -8 | -3.591% | -0.4353% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | N/A
266 | Expense | GT&S | JO | GT Pipeline Maintenance | JOA | Cath Prot Rectifier Maintenanc | Loss of Containment on Gas Transmission Pipeline | LOCTM-C019 Cathodic Protection | Ex 3, Ch 9 | No | On-Going | Annual | 118.2768 | 120.8067 | 239.0835 | 326.5746 | 212.9497 | 539.5243 | 92.143 | 300.4408 | 76.27% | 125.7% | N/A | N/A | N/A | 919 | 919 | 1838 | 944 | 886 | 1830 | -33 | -8 | -3.591% | -0.4353% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
267 | Expense | GT&S | JO | GT Pipeline Maintenance | JOB | Cath Prot Monitoring | SRM Total | SRM Total | Ex 3, Ch 9 | No | On-Going | Annual | 1289.5719 | 1317.1553 | 2606.7272 | 1882.3828 | 1862.6427 | 3745.0255 | 545.4874 | 1138.2983 | 41.41% | 43.67% | NO | NO | # of CP monitoring point reads (P/S reads) | 13674 | 13674 | 27348 | 18750 | 18640 | 37390 | 4966 | 10042 | 36.32% | 36.72% | YES | N/A | Actual units were higher than Imputed units due to not factoring in Bi-monthly Rectifier Reads for Backbone and GT due to the assumption that automated reads would not report units | Over | On-Target | On-Target | Proceeding as planned | Ongoing and will continue in PG&E's 2023 GRC period
268 | Expense | GT&S | JO | GT Pipeline Maintenance | JOB | Cath Prot Monitoring | Loss of Containment on Gas Transmission Pipeline | LOCTM-C019 Cathodic Protection | Ex 3, Ch 9 | No | On-Going | Annual | 1289.5719 | 1317.1553 | 2606.7272 | 0 | 1862.6427 | 1862.6427 | 545.4874 | -744.0845 | 41.41% | -28.54% | N/A | N/A | N/A | 13674 | 13674 | 27348 | 18750 | 18640 | 37390 | 4966 | 10042 | 36.32% | 36.72% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
269 | Expense | GT&S | JO | GT Pipeline Maintenance | JOB | Cath Prot Monitoring | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C018 Cathodic Protection | Ex 3, Ch 9 | No | On-Going | Annual | 1289.5719 | 1317.1553 | 2606.7272 | 1882.3828 | 1862.6427 | 3745.0255 | 545.4874 | 1138.2983 | 41.41% | 43.67% | N/A | N/A | N/A | 13674 | 13674 | 27348 | 18750 | 18640 | 37390 | 4966 | 10042 | 36.32% | 36.72% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
270 | Expense | GT&S | JO | GT Pipeline Maintenance | JOB | Cath Prot Monitoring | Loss of Containment at Natural Gas Storage Well or Reservoir | NGSWR-C007 Cathodic Protection | Ex 3, Ch 9 | No | On-Going | Annual | 1289.5719 | 1317.1553 | 2606.7272 | 1882.3828 | 1862.6427 | 3745.0255 | 545.4874 | 1138.2983 | 41.41% | 43.67% | N/A | N/A | N/A | 13674 | 13674 | 27348 | 18750 | 18640 | 37390 | 4966 | 10042 | 36.32% | 36.72% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
271 | Expense | GT&S | JO | GT Pipeline Maintenance | JOC | Cath Prot Troubleshoot | SRM Total | SRM Total | Ex 3, Ch 9 | No | On-Going | Annual | 812.5347 | 829.9145 | 1642.4492 | 1299.7089 | 1520.4492 | 2820.1582 | 690.5348 | 1177.709 | 83.21% | 71.7% | NO | NO | # of troubleshoots | 1787 | 1787 | 3574 | 3032 | 3930 | 6962 | 2143 | 3388 | 119.9% | 94.8% | YES | N/A | Actual units were higher than Imputed units due to not factoring in TS resulting from the 850 Off Program or Troubleshoot priority change due to Mega Rule | Over | On-Target | On-Target | Proceeding as planned | Ongoing and will continue in PG&E's 2023 GRC period
272 | Expense | GT&S | JO | GT Pipeline Maintenance | JOC | Cath Prot Troubleshoot | Loss of Containment on Gas Transmission Pipeline | LOCTM-C019 Cathodic Protection | Ex 3, Ch 9 | No | On-Going | Annual | 812.5347 | 829.9145 | 1642.4492 | 1299.7089 | 1520.4492 | 2820.1582 | 690.5348 | 1177.709 | 83.21% | 71.7% | N/A | N/A | N/A | 1787 | 1787 | 3574 | 3032 | 3930 | 6962 | 2143 | 3388 | 119.9% | 94.8% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
273 | Expense | GT&S | JO | GT Pipeline Maintenance | JOE | Ground Leak Survey | SRM Total | SRM Total | Ex 3, Ch 10 | No | On-Going | annual | 989.5046 | 1010.6704 | 2000.175 | 637.2403 | 558.3158 | 1195.5561 | -452.3546 | -804.6188 | -44.76% | -40.23% | NO | NO | Miles Ground Leak Surveyed | 440 | 440 | 880 | 477 | 440 | 917 | 0 | 37 | 0% | 4.205% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | N/A
274 | Expense | GT&S | JO | GT Pipeline Maintenance | JOE | Ground Leak Survey | Loss of Containment on Gas Transmission Pipeline | LOCTM-C020 Transmission Leak Management | Ex 3, Ch 10 | No | On-Going | annual | 989.5046 | 1010.6704 | 2000.175 | 637.2403 | 558.3158 | 1195.5561 | -452.3546 | -804.6188 | -44.76% | -40.23% | N/A | N/A | N/A | 440 | 440 | 880 | 477 | 440 | 917 | 0 | 37 | 0% | 4.205% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
275 | Expense | GT&S | JO | GT Pipeline Maintenance | JOF | Requird Ground Pipeline Patrol | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 1036.6933 | 1058.8459 | 2095.5392 | 842.5786 | 543.4369 | 1386.0155 | -515.4091 | -709.5238 | -48.68% | -33.86% | NO | NO | Hours | 10461 | 10461 | 20922 | 5880 | 3457 | 9337 | -7004 | -11585 | -66.95% | -55.37% | YES | N/A | REVIEW NEEDED - The units listed under "Units Actual" reflect observations, where the imputed reflects hours worked. The correct "Units Actual" is 3,457. The units are lower than imputed due to Ground Patrol shifting to Locate and Mark which reduced overtime and drive time. | Under | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to perform ground patrols in areas where the pipeline is visually obscured by vegetation from the view of aerial patrols. Additionally, ground patrols are performed to investigate aerial patrol observations that pose an immediate risk.
276 | Expense | GT&S | JO | GT Pipeline Maintenance | JOF | Requird Ground Pipeline Patrol | Loss of Containment on Gas Transmission Pipeline | LOCTM-C012 Required Pipeline Patrol Program | Ex 3, Ch 8 | No | On-Going | Annual | 1036.6933 | 1058.8459 | 2095.5392 | 842.5786 | 543.4369 | 1386.0155 | -515.4091 | -709.5238 | -48.68% | -33.86% | N/A | N/A | N/A | 10461 | 10461 | 20922 | 5880 | 3457 | 9337 | -7004 | -11585 | -66.95% | -55.37% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
277 | Expense | GT&S | JO | GT Pipeline Maintenance | JOG | PM G Regulator General | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 3956.9685 | 4041.5233 | 7998.4918 | 3671.0673 | 4147.8971 | 7818.9644 | 106.3737 | -179.5274 | 2.632% | -2.245% | NO | NO | non-unitized: This MAT has no measurable units because majority of the orders under these MATs exist as Asset Maintenance Backbone and Station (AMBBS) orders. AMBBS records “operations” which are not necessarily equivalent to a unit. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | N/A
278 | Expense | GT&S | JO | GT Pipeline Maintenance | JOG | PM G Regulator General | Large Overpressure Event Downstream of Gas M&C Facility | LRGOP-C020 Transmission Regulator Maintenance | Ex 3, Ch 8 | No | On-Going | Annual | 3956.9685 | 4041.5233 | 7998.4918 | 3671.0673 | 4147.8971 | 7818.9644 | 106.3737 | -179.5274 | 2.632% | -2.245% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
279 | Expense | GT&S | JO | GT Pipeline Maintenance | JOG | PM G Regulator General | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C014 Transmission Regulator Maintenance | Ex 3, Ch 8 | No | On-Going | Annual | 3956.9685 | 4041.5233 | 7998.4918 | 3671.0673 | 4147.8971 | 7818.9644 | 106.3737 | -179.5274 | 2.632% | -2.245% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
280 | Expense | GT&S | JO | GT Pipeline Maintenance | JOH | PM Gas Pipeline Valve Manual | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 1495.4205 | 1527.3756 | 3022.7961 | 1448.5255 | 1412.6771 | 2861.2027 | -114.6985 | -161.5934 | -7.51% | -5.346% | NO | NO | non-unitized: This MAT has no measurable units because majority of the orders under these MATs exist as Asset Maintenance Backbone and Station (AMBBS) orders. AMBBS records “operations” which are not necessarily equivalent to a unit. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | N/A
281 | Expense | GT&S | JO | GT Pipeline Maintenance | JOH | PM Gas Pipeline Valve Manual | Loss of Containment on Gas Transmission Pipeline | LOCTM-C013 PM Gas Pipeline Valves Program | Ex 3, Ch 8 | No | On-Going | Annual | 1495.4205 | 1527.3756 | 3022.7961 | 1448.5255 | 1412.6771 | 2861.2027 | -114.6985 | -161.5934 | -7.51% | -5.346% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
282 | Expense | GT&S | JO | GT Pipeline Maintenance | JOI | PM Gas Pipeline Valve Automate | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 39.5848 | 40.4306 | 80.0154 | 43.1587 | 59.5732 | 102.7319 | 19.1425 | 22.7164 | 47.35% | 28.39% | NO | NO | non-unitized: This MAT has no measurable units because majority of the orders under these MATs exist as Asset Maintenance Backbone and Station (AMBBS) orders. AMBBS records “operations” which are not necessarily equivalent to a unit. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | N/A
283 | Expense | GT&S | JO | GT Pipeline Maintenance | JOI | PM Gas Pipeline Valve Automate | Loss of Containment on Gas Transmission Pipeline | LOCTM-C013 PM Gas Pipeline Valves Program | Ex 3, Ch 8 | No | On-Going | Annual | 39.5848 | 40.4306 | 80.0154 | 43.1587 | 59.5732 | 102.7319 | 19.1425 | 22.7164 | 47.35% | 28.39% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
284 | Expense | GT&S | JO | GT Pipeline Maintenance | JOJ | Gas Holders Maintenance | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 126.576 | 129.2807 | 255.8567 | 96.6035 | 77.4767 | 174.0802 | -51.8041 | -81.7765 | -40.07% | -31.96% | NO | NO | non-unitized: This MAT has no measurable units because majority of the orders under these MATs exist as Asset Maintenance Backbone and Station (AMBBS) orders. AMBBS records “operations” which are not necessarily equivalent to a unit. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | N/A
285 | Expense | GT&S | JO | GT Pipeline Maintenance | JOJ | Gas Holders Maintenance | Loss of Containment on Gas Transmission Pipeline | LOCTM-C031 Gas Holder Maintenance | Ex 3, Ch 8 | No | On-Going | Annual | 126.576 | 129.2807 | 255.8567 | 96.6035 | 77.4767 | 174.0802 | -51.8041 | -81.7765 | -40.07% | -31.96% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
286 | Expense | GT&S | JO | GT Pipeline Maintenance | JOK | Oper Tranmission Pipelines | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 730.8928 | 746.511 | 1477.4039 | 439.9676 | 355.5278 | 795.4953 | -390.9833 | -681.9085 | -52.37% | -46.16% | NO | NO | non-unitized: This MAT has no measurable units because majority of the orders under these MATs exist as Asset Maintenance Backbone and Station (AMBBS) orders. AMBBS records “operations” which are not necessarily equivalent to a unit. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | N/A
287 | Expense | GT&S | JO | GT Pipeline Maintenance | JOK | Oper Tranmission Pipelines | Loss of Containment on Gas Transmission Pipeline | LOCTM-C023 Operate Transmission Pipelines | Ex 3, Ch 8 | No | On-Going | Annual | 730.8928 | 746.511 | 1477.4039 | 439.9676 | 355.5278 | 795.4953 | -390.9833 | -681.9085 | -52.37% | -46.16% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
288 | Expense | GT&S | JO | GT Pipeline Maintenance | JOK | Oper Tranmission Pipelines | Large Overpressure Event Downstream of Gas M&C Facility | LRGOP-C010 Operate Transmission Pipelines | Ex 3, Ch 8 | No | On-Going | Annual | 730.8928 | 746.511 | 1477.4039 | 439.9676 | 355.5278 | 795.4953 | -390.9833 | -681.9085 | -52.37% | -46.16% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
289 | Expense | GT&S | JO | GT Pipeline Maintenance | JOL | Oper Transmission Regl Station | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 461.3197 | 471.1774 | 932.4971 | 627.9131 | 861.0975 | 1489.0105 | 389.92 | 556.5134 | 82.75% | 59.68% | NO | NO | non-unitized: This MAT has no measurable units because majority of the orders under these MATs exist as Asset Maintenance Backbone and Station (AMBBS) orders. AMBBS records “operations” which are not necessarily equivalent to a unit. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | N/A
290 | Expense | GT&S | JO | GT Pipeline Maintenance | JOL | Oper Transmission Regl Station | Large Overpressure Event Downstream of Gas M&C Facility | LRGOP-C020 Transmission Regulator Maintenance | Ex 3, Ch 8 | No | On-Going | Annual | 461.3197 | 471.1774 | 932.4971 | 627.9131 | 861.0975 | 1489.0105 | 389.92 | 556.5134 | 82.75% | 59.68% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
291 | Expense | GT&S | JO | GT Pipeline Maintenance | JOL | Oper Transmission Regl Station | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C014 Transmission Regulator Maintenance | Ex 3, Ch 8 | No | On-Going | Annual | 461.3197 | 471.1774 | 932.4971 | 627.9131 | 861.0975 | 1489.0105 | 389.92 | 556.5134 | 82.75% | 59.68% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
292 | Expense | GT&S | JO | GT Pipeline Maintenance | JOM | CM G Regl Genl | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 1117.1112 | 1140.9823 | 2258.0936 | 1276.3045 | 688.0491 | 1964.3535 | -452.9333 | -293.74 | -39.7% | -13.01% | NO | NO | non-unitized: This MAT has no measurable units because majority of the orders under these MATs exist as Asset Maintenance Backbone and Station (AMBBS) orders. AMBBS records “operations” which are not necessarily equivalent to a unit. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | N/A
293 | Expense | GT&S | JO | GT Pipeline Maintenance | JOM | CM G Regl Genl | Large Overpressure Event Downstream of Gas M&C Facility | LRGOP-C020 Transmission Regulator Maintenance | Ex 3, Ch 8 | No | On-Going | Annual | 1117.1112 | 1140.9823 | 2258.0936 | 1276.3045 | 688.0491 | 1964.3535 | -452.9333 | -293.74 | -39.7% | -13.01% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
294 | Expense | GT&S | JO | GT Pipeline Maintenance | JOM | CM G Regl Genl | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C014 Transmission Regulator Maintenance | Ex 3, Ch 8 | No | On-Going | Annual | 1117.1112 | 1140.9823 | 2258.0936 | 1276.3045 | 688.0491 | 1964.3535 | -452.9333 | -293.74 | -39.7% | -13.01% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
295 | Expense | GT&S | JO | GT Pipeline Maintenance | JON | CM Gas Pipeline Valve Manual | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 950.0092 | 970.3095 | 1920.3187 | 724.2313 | 783.6291 | 1507.8603 | -186.6805 | -412.4584 | -19.24% | -21.48% | NO | NO | non-unitized: This MAT has no measurable units because majority of the orders under these MATs exist as Asset Maintenance Backbone and Station (AMBBS) orders. AMBBS records “operations” which are not necessarily equivalent to a unit. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | N/A
296 | Expense | GT&S | JO | GT Pipeline Maintenance | JON | CM Gas Pipeline Valve Manual | Loss of Containment on Gas Transmission Pipeline | LOCTM-C014 CM Gas Pipeline Valves Program | Ex 3, Ch 8 | No | On-Going | Annual | 950.0092 | 970.3095 | 1920.3187 | 724.2313 | 783.6291 | 1507.8603 | -186.6805 | -412.4584 | -19.24% | -21.48% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
297 | Expense | GT&S | JO | GT Pipeline Maintenance | JOO | CM Gas Pipeline Valve Automate | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 222.2539 | 227.0032 | 449.2571 | 603.8278 | 297.3552 | 901.183 | 70.352 | 451.9259 | 30.99% | 100.6% | NO | NO | non-unitized: This MAT has no measurable units because majority of the orders under these MATs exist as Asset Maintenance Backbone and Station (AMBBS) orders. AMBBS records “operations” which are not necessarily equivalent to a unit. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | N/A
298 | Expense | GT&S | JO | GT Pipeline Maintenance | JOO | CM Gas Pipeline Valve Automate | Loss of Containment on Gas Transmission Pipeline | LOCTM-C014 CM Gas Pipeline Valves Program | Ex 3, Ch 8 | No | On-Going | Annual | 222.2539 | 227.0032 | 449.2571 | 603.8278 | 297.3552 | 901.183 | 70.352 | 451.9259 | 30.99% | 100.6% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
299 | Expense | GT&S | JO | GT Pipeline Maintenance | JOP | CM G Main Lk | SRM Total | SRM Total | Ex 3, Ch 10 | No | On-Going | Annual | 11169.4509 | 11408.3688 | 22577.8196 | 1556.0525 | 932.3083 | 2488.3607 | -10476.0605 | -20089.4589 | -91.83% | -88.98% | YES | YES | # Leaks Repaired | 3281 | 3281 | 6562 | 1041 | 585 | 1626 | -2696 | -4936 | -82.17% | -75.22% | YES | Actual costs were lower than imputed due to decreased leak find rates in the last three years resulting in reduced leak finds and repairs. A second factor driving cost down is the implementation of process improvement initiatives such as leak bundling. | Actual units lower than imputed due to decreased leak find rates in the last three years resulting in reduced leak finds and repairs. | Under | On-Target | Under | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to fix gradeable transmission leaks that require TLA type of repairs.
300 | Expense | GT&S | JO | GT Pipeline Maintenance | JOP | CM G Main Lk | Loss of Containment on Gas Transmission Pipeline | LOCTM-C020 Transmission Leak Management | Ex 3, Ch 10 | No | On-Going | Annual | 11169.4509 | 11408.3688 | 22577.8196 | 1556.0525 | 932.3083 | 2488.3607 | -10476.0605 | -20089.4589 | -91.83% | -88.98% | N/A | N/A | N/A | 3281 | 3281 | 6562 | 1041 | 585 | 1626 | -2696 | -4936 | -82.17% | -75.22% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
301 | Expense | GT&S | JO | GT Pipeline Maintenance | JOQ | Cath Protection Corr Maintnc | SRM Total | SRM Total | Ex 3, Ch 9 | No | On-Going | Annual | 357.9554 | 365.6119 | 723.5673 | 353.6694 | 408.7493 | 762.4187 | 43.1374 | 38.8514 | 11.8% | 5.369% | NO | NO | # of corrective work orders completed | 324 | 324 | 648 | 237 | 302 | 539 | -22 | -109 | -6.79% | -16.82% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | N/A
302 | Expense | GT&S | JO | GT Pipeline Maintenance | JOQ | Cath Protection Corr Maintnc | Loss of Containment on Gas Transmission Pipeline | LOCTM-C019 Cathodic Protection | Ex 3, Ch 9 | No | On-Going | Annual | 357.9554 | 365.6119 | 723.5673 | 353.6694 | 408.7493 | 762.4187 | 43.1374 | 38.8514 | 11.8% | 5.369% | N/A | N/A | N/A | 324 | 324 | 648 | 237 | 302 | 539 | -22 | -109 | -6.79% | -16.82% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
303 | Expense | GT&S | JO | GT Pipeline Maintenance | JOR | Leak Rechecks | SRM Total | SRM Total | Ex 3, Ch 10 | No | On-Going | Annual | 264.4926 | 270.1502 | 534.6428 | 75.6114 | 24.1365 | 99.7479 | -246.0136 | -434.8949 | -91.07% | -81.34% | NO | NO | # of Rechecks Performed | 2816 | 2816 | 5632 | 884 | 574 | 1458 | -2242 | -4174 | -79.62% | -74.11% | YES | N/A | Actual units were lower than imputed due to accelerated repair timeframes driven by the CARB rules and regulations. | Under | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
304 | Expense | GT&S | JO | GT Pipeline Maintenance | JOR | Leak Rechecks | Loss of Containment on Gas Transmission Pipeline | LOCTM-C020 Transmission Leak Management | Ex 3, Ch 10 | No | On-Going | Annual | 264.4926 | 270.1502 | 534.6428 | 75.6114 | 24.1365 | 99.7479 | -246.0136 | -434.8949 | -91.07% | -81.34% | N/A | N/A | N/A | 2816 | 2816 | 5632 | 884 | 574 | 1458 | -2242 | -4174 | -79.62% | -74.11% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
305 | Expense | GT&S | JO | GT Pipeline Maintenance | JOS | Pipeline Marker Maintenance | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 1761.9545 | 1799.605 | 3561.5595 | 912.0574 | 899.5781 | 1811.6355 | -900.027 | -1749.924 | -50.01% | -49.13% | NO | NO | non-unitized: This MAT has no measurable units because majority of the orders under these MATs exist as Asset Maintenance Backbone and Station (AMBBS) orders. AMBBS records “operations” which are not necessarily equivalent to a unit. | N/A | N/A | N/A | N/A | 1522 | 1522 | 1522 | 1522 | 0% | 0% | NO | N/A | Actual units were higher than imputed due to this MAT not previously being unitized. | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. This program involves installing, replacing and maintaining transmission pipeline markers.
306 | Expense | GT&S | JO | GT Pipeline Maintenance | JOS | Pipeline Marker Maintenance | Loss of Containment on Gas Transmission Pipeline | LOCTM-C015 Pipeline Marker Maintenance | Ex 3, Ch 8 | No | On-Going | Annual | 1761.9545 | 1799.605 | 3561.5595 | 912.0574 | 899.5781 | 1811.6355 | -900.027 | -1749.924 | -50.01% | -49.13% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1522 | 1522 | 1522 | 1522 | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
307 | Expense | GT&S | JO | GT Pipeline Maintenance | JOT | Vegetation Management | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 1521.5369 | 1554.05 | 3075.5869 | 1446.9457 | 1569.2983 | 3016.244 | 15.2483 | -59.3429 | 0.9812% | -1.929% | NO | NO | non-unitized: This MAT has no measurable units because majority of the orders under these MATs exist as Asset Maintenance Backbone and Station (AMBBS) orders. AMBBS records “operations” which are not necessarily equivalent to a unit. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | N/A
308 | Expense | GT&S | JO | GT Pipeline Maintenance | JOT | Vegetation Management | Loss of Containment on Gas Transmission Pipeline | LOCTM-C016 Vegetation Management | Ex 3, Ch 8 | No | On-Going | Annual | 1521.5369 | 1554.05 | 3075.5869 | 0 | 1569.2983 | 1569.2983 | 15.2483 | -1506.2886 | 0.9812% | -48.98% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
309 | Expense | GT&S | JO | GT Pipeline Maintenance | JOT | Vegetation Management | Large Overpressure Event Downstream of Gas M&C Facility | LRGOP-C011 Vegetation Management | Ex 3, Ch 8 | No | On-Going | Annual | 1521.5369 | 1554.05 | 3075.5869 | 1446.9457 | 1569.2983 | 3016.244 | 15.2483 | -59.3429 | 0.9812% | -1.929% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
310 | Expense | GT&S | JO | GT Pipeline Maintenance | JOT | Vegetation Management | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C008 Vegetation Management | Ex 3, Ch 8 | No | On-Going | Annual | 1521.5369 | 1554.05 | 3075.5869 | 1446.9457 | 1569.2983 | 3016.244 | 15.2483 | -59.3429 | 0.9812% | -1.929% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
311 | Expense | GT&S | JO | GT Pipeline Maintenance | JOV | Requird Aerial Pipeline Patrol | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 4822.7535 | 4925.809 | 9748.5625 | 2450.6265 | 2278.5588 | 4729.1853 | -2647.2502 | -5019.3772 | -53.74% | -51.49% | NO | NO | Miles Aerial Patroled | 125656 | 125656 | 251312 | 25769.49 | 25724 | 51493.49 | -99932 | -199818.51 | -79.53% | -79.51% | YES | N/A | Actual units were lower than imputed units due to a change in the patrol frequency from monthly to quarterly, in alignment with regulatory requirements. | Under | On-Target | Under | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to observe surface conditions on and adjacent to the pipeline ROW for factors affecting safety and operations.
312 | Expense | GT&S | JO | GT Pipeline Maintenance | JOV | Requird Aerial Pipeline Patrol | Loss of Containment on Gas Transmission Pipeline | LOCTM-C012 Required Pipeline Patrol Program | Ex 3, Ch 8 | No | On-Going | Annual | 4822.7535 | 4925.809 | 9748.5625 | 2450.6265 | 2278.5588 | 4729.1853 | -2647.2502 | -5019.3772 | -53.74% | -51.49% | N/A | N/A | N/A | 125656 | 125656 | 251312 | 25769 | 25724 | 51493 | -99932 | -199819 | -79.53% | -79.51% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
313 | Expense | GT&S | JO | GT Pipeline Maintenance | JOW | Aerial Leak Survey | SRM Total | SRM Total | Ex 3, Ch 10 | No | On-Going | annual | 2493.68 | 2547.0206 | 5040.7006 | 1653.8888 | 1710.4059 | 3364.2947 | -836.6146 | -1676.4058 | -32.85% | -33.26% | NO | NO | Miles Aerial Leak Surveyed | 12807 | 12807 | 25614 | 12487 | 12608 | 25095 | -199 | -519 | -1.554% | -2.026% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | N/A
314 | Expense | GT&S | JO | GT Pipeline Maintenance | JOW | Aerial Leak Survey | Loss of Containment on Gas Transmission Pipeline | LOCTM-C020 Transmission Leak Management | Ex 3, Ch 10 | No | On-Going | annual | 2493.68 | 2547.0206 | 5040.7006 | 1653.8888 | 1710.4059 | 3364.2947 | -836.6146 | -1676.4058 | -32.85% | -33.26% | N/A | N/A | N/A | 12807 | 12807 | 25614 | 12487 | 12608 | 25095 | -199 | -519 | -1.554% | -2.026% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
315 | Expense | GT&S | JO | GT Pipeline Maintenance | JOX | PM Meter Maintenance | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 1948.5289 | 1990.1662 | 3938.6951 | 2247.6943 | 2202.0198 | 4449.7141 | 211.8535 | 511.019 | 10.65% | 12.97% | NO | NO | non-unitized: This MAT has no measurable units because majority of the orders under these MATs exist as Asset Maintenance Backbone and Station (AMBBS) orders. AMBBS records “operations” which are not necessarily equivalent to a unit. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | N/A
316 | Expense | GT&S | JO | GT Pipeline Maintenance | JOX | PM Meter Maintenance | Large Overpressure Event Downstream of Gas M&C Facility | LRGOP-C012 Meter Maintenance | Ex 3, Ch 8 | No | On-Going | Annual | 1948.5289 | 1990.1662 | 3938.6951 | 2247.6943 | 2202.0198 | 4449.7141 | 211.8535 | 511.019 | 10.65% | 12.97% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
317 | Expense | GT&S | JO | GT Pipeline Maintenance | JOY | CM Meter Maintenance | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 288.8485 | 295.0208 | 583.8692 | 301.7828 | 357.2075 | 658.9902 | 62.1867 | 75.121 | 21.08% | 12.87% | NO | NO | non-unitized: This MAT has no measurable units because majority of the orders under these MATs exist as Asset Maintenance Backbone and Station (AMBBS) orders. AMBBS records “operations” which are not necessarily equivalent to a unit. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | N/A
318 | Expense | GT&S | JO | GT Pipeline Maintenance | JOY | CM Meter Maintenance | Large Overpressure Event Downstream of Gas M&C Facility | LRGOP-C012 Meter Maintenance | Ex 3, Ch 8 | No | On-Going | Annual | 288.8485 | 295.0208 | 583.8692 | 301.7828 | 357.2075 | 658.9902 | 62.1867 | 75.121 | 21.08% | 12.87% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
319 | Expense | GT&S | JO | GT Pipeline Maintenance | JOZ | Atmospheric Corrosion Inspect | SRM Total | SRM Total | Ex 3, Ch 9 | No | On-Going | Annual | 500.2251 | 510.9247 | 1011.1498 | 87.9126 | 186.7792 | 274.6917 | -324.1455 | -736.458 | -63.44% | -72.83% | NO | NO | # of spans patrolled | 487 | 487 | 974 | 226 | 390 | 616 | -97 | -358 | -19.92% | -36.76% | NO | N/A | Actual units were lower than imputed due to original forecast was based on 2023 planned units. Variance is due to less spans in the field than originally input into the maintenance plan in 2020. Additionally, 33 units were recorded as MAT JOB due to object types reflecting Span_U; 3 units were recorded as MAT 34A because they are located at Stanpac Functional Location in the system | Under | On-Target | On-Target | Proceeding as planned | Ongoing and will continue in PG&E's 2023 GRC period
320 | Expense | GT&S | JO | GT Pipeline Maintenance | JOZ | Atmospheric Corrosion Inspect | Loss of Containment on Gas Transmission Pipeline | LOCTM-C034 Atmospheric Corrosion Program | Ex 3, Ch 9 | No | On-Going | Annual | 500.2251 | 510.9247 | 1011.1498 | 87.9126 | 186.7792 | 274.6917 | -324.1455 | -736.458 | -63.44% | -72.83% | N/A | N/A | N/A | 487 | 487 | 974 | 226 | 390 | 616 | -97 | -358 | -19.92% | -36.76% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
321 | Expense | GT&S | JP | GT Station Maintenance | JPA | PM StorCompStat Piping Assets | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 980.5475 | 1000.7219 | 1981.2694 | 1222.2772 | 1361.3641 | 2583.6413 | 360.6422 | 602.3719 | 36.04% | 30.4% | NO | NO | non-unitized: This MAT has no measurable units because majority of the orders under these MATs exist as Asset Maintenance Backbone and Station (AMBBS) orders. AMBBS records “operations” which are not necessarily equivalent to a unit. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | N/A
322 | Expense | GT&S | JP | GT Station Maintenance | JPA | PM StorCompStat Piping Assets | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C001 Transm Comprsr Station Corrective & Prevnt Maintn | Ex 3, Ch 8 | No | On-Going | Annual | 980.5475 | 1000.7219 | 1981.2694 | 1222.2772 | 1361.3641 | 2583.6413 | 360.6422 | 602.3719 | 0.36038 | 0.30403 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
323 | Expense | GT&S | JP | GT Station Maintenance | JPB | CM StorCompStat Piping Assets | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 473.1163 | 482.8505 | 955.9669 | 187.997 | 137.6769 | 325.6739 | -345.1736 | -630.293 | -0.71487 | -0.65933 | NO | NO | non-unitized: This MAT has no measurable units because majority of the orders under these MATs exist as Asset Maintenance Backbone and Station (AMBBS) orders. AMBBS records “operations” which are not necessarily equivalent to a unit. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | N/A
324 | Expense | GT&S | JP | GT Station Maintenance | JPB | CM StorCompStat Piping Assets | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C001 Transm Comprsr Station Corrective & Prevnt Maintn | Ex 3, Ch 8 | No | On-Going | Annual | 473.1163 | 482.8505 | 955.9669 | 187.997 | 137.6769 | 325.6739 | -345.1736 | -630.293 | -0.71487 | -0.65933 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
325 | Expense | GT&S | JP | GT Station Maintenance | JPC | PM StorCompStat GasProcess | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 1919.6246 | 1959.1202 | 3878.7448 | 2374.9648 | 1986.8205 | 4361.7854 | 27.7004 | 483.0406 | 0.014139 | 0.12454 | NO | NO | non-unitized: This MAT has no measurable units because majority of the orders under these MATs exist as Asset Maintenance Backbone and Station (AMBBS) orders. AMBBS records “operations” which are not necessarily equivalent to a unit. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | N/A
326 | Expense | GT&S | JP | GT Station Maintenance | JPC | PM StorCompStat GasProcess | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C001 Transm Comprsr Station Corrective & Prevnt Maintn | Ex 3, Ch 8 | No | On-Going | Annual | 1919.6246 | 1959.1202 | 3878.7448 | 2374.9648 | 1986.8205 | 4361.7854 | 27.7004 | 483.0406 | 0.014139 | 0.12454 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
327 | Expense | GT&S | JP | GT Station Maintenance | JPD | PM StorCompStat GasCompressor | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 1810.2541 | 1847.4995 | 3657.7536 | 3335.1249 | 3142.0609 | 6477.1858 | 1294.5614 | 2819.4322 | 0.70071 | 0.77081 | NO | NO | non-unitized: This MAT has no measurable units because majority of the orders under these MATs exist as Asset Maintenance Backbone and Station (AMBBS) orders. AMBBS records “operations” which are not necessarily equivalent to a unit. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | N/A
328 | Expense | GT&S | JP | GT Station Maintenance | JPD | PM StorCompStat GasCompressor | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C001 Transm Comprsr Station Corrective & Prevnt Maintn | Ex 3, Ch 8 | No | On-Going | Annual | 1810.2541 | 1847.4995 | 3657.7536 | 3335.1249 | 3142.0609 | 6477.1858 | 1294.5614 | 2819.4322 | 0.70071 | 0.77081 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
329 | Expense | GT&S | JP | GT Station Maintenance | JPE | PM StorCompStat Support | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 2279.9418 | 2326.8508 | 4606.7926 | 2467.8784 | 2163.3478 | 4631.2262 | -163.503 | 24.4337 | -0.070268 | 0.0053038 | NO | NO | non-unitized: This MAT has no measurable units because majority of the orders under these MATs exist as Asset Maintenance Backbone and Station (AMBBS) orders. AMBBS records “operations” which are not necessarily equivalent to a unit. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | N/A
330 | Expense | GT&S | JP | GT Station Maintenance | JPE | PM StorCompStat Support | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C001 Transm Comprsr Station Corrective & Prevnt Maintn | Ex 3, Ch 8 | No | On-Going | Annual | 2279.9418 | 2326.8508 | 4606.7926 | 2467.8784 | 2163.3478 | 4631.2262 | -163.503 | 24.4337 | -0.070268 | 0.0053038 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
331 | Expense | GT&S | JP | GT Station Maintenance | JPG | CM StorCompStat GasProcess | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 983.5494 | 1003.7856 | 1987.335 | 1628.4306 | 1158.3776 | 2786.8081 | 154.592 | 799.4731 | 0.15401 | 0.40228 | NO | NO | non-unitized: This MAT has no measurable units because majority of the orders under these MATs exist as Asset Maintenance Backbone and Station (AMBBS) orders. AMBBS records “operations” which are not necessarily equivalent to a unit. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | N/A
332 | Expense | GT&S | JP | GT Station Maintenance | JPG | CM StorCompStat GasProcess | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C001 Transm Comprsr Station Corrective & Prevnt Maintn | Ex 3, Ch 8 | No | On-Going | Annual | 983.5494 | 1003.7856 | 1987.335 | 1628.4306 | 1158.3776 | 2786.8081 | 154.592 | 799.4731 | 0.15401 | 0.40228 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
333 | Expense | GT&S | JP | GT Station Maintenance | JPH | CM StorCompStat GasCompress | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 2071.3098 | 2113.9263 | 4185.2361 | 2625.2979 | 2996.4714 | 5621.7693 | 882.5451 | 1436.5332 | 0.41749 | 0.34324 | NO | NO | non-unitized: This MAT has no measurable units because majority of the orders under these MATs exist as Asset Maintenance Backbone and Station (AMBBS) orders. AMBBS records “operations” which are not necessarily equivalent to a unit. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | N/A
334 | Expense | GT&S | JP | GT Station Maintenance | JPH | CM StorCompStat GasCompress | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C001 Transm Comprsr Station Corrective & Prevnt Maintn | Ex 3, Ch 8 | No | On-Going | Annual | 2071.3098 | 2113.9263 | 4185.2361 | 2625.2979 | 2996.4714 | 5621.7693 | 882.5451 | 1436.5332 | 0.41749 | 0.34324 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
335 | Expense | GT&S | JP | GT Station Maintenance | JPI | CM StorCompStat Support | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 1525.448 | 1556.8335 | 3082.2815 | 687.9186 | 572.2763 | 1260.1949 | -984.5572 | -1822.0866 | -0.63241 | -0.59115 | NO | NO | non-unitized: This MAT has no measurable units because majority of the orders under these MATs exist as Asset Maintenance Backbone and Station (AMBBS) orders. AMBBS records “operations” which are not necessarily equivalent to a unit. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | N/A
336 | Expense | GT&S | JP | GT Station Maintenance | JPI | CM StorCompStat Support | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C001 Transm Comprsr Station Corrective & Prevnt Maintn | Ex 3, Ch 8 | No | On-Going | Annual | 1525.448 | 1556.8335 | 3082.2815 | 687.9186 | 572.2763 | 1260.1949 | -984.5572 | -1822.0866 | -0.63241 | -0.59115 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
337 | Expense | GT&S | JP | GT Station Maintenance | JPK | PM Power Units | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 139.2082 | 142.0724 | 281.2806 | 330.4969 | 176.3057 | 506.8026 | 34.2333 | 225.522 | 0.24096 | 0.80177 | NO | NO | non-unitized: This MAT has no measurable units because majority of the orders under these MATs exist as Asset Maintenance Backbone and Station (AMBBS) orders. AMBBS records “operations” which are not necessarily equivalent to a unit. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | N/A
338 | Expense | GT&S | JP | GT Station Maintenance | JPK | PM Power Units | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C015 Power Units Maintenance | Ex 3, Ch 8 | No | On-Going | Annual | 139.2082 | 142.0724 | 281.2806 | 330.4969 | 176.3057 | 506.8026 | 34.2333 | 225.522 | 0.24096 | 0.80177 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
339 | Expense | GT&S | JP | GT Station Maintenance | JPL | CM Power Units | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 276.8857 | 282.5825 | 559.4682 | 386.6086 | 452.062 | 838.6706 | 169.4795 | 279.2024 | 0.59975 | 0.49905 | NO | NO | non-unitized: This MAT has no measurable units because majority of the orders under these MATs exist as Asset Maintenance Backbone and Station (AMBBS) orders. AMBBS records “operations” which are not necessarily equivalent to a unit. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | N/A
340 | Expense | GT&S | JP | GT Station Maintenance | JPL | CM Power Units | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C015 Power Units Maintenance | Ex 3, Ch 8 | No | On-Going | Annual | 276.8857 | 282.5825 | 559.4682 | 386.6086 | 452.062 | 838.6706 | 169.4795 | 279.2024 | 0.59975 | 0.49905 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
341 | Expense | GT&S | JP | GT Station Maintenance | JPN | Station Operations | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 6026.6487 | 6150.6448 | 12177.2936 | 6033.303 | 6531.002 | 12564.3049 | 380.3572 | 387.0114 | 0.06184 | 0.031781 | NO | NO | non-unitized: This MAT has no measurable units because majority of the orders under these MATs exist as Asset Maintenance Backbone and Station (AMBBS) orders. AMBBS records “operations” which are not necessarily equivalent to a unit. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | N/A
342 | Expense | GT&S | JP | GT Station Maintenance | JPN | Station Operations | Large Overpressure Event Downstream of Gas M&C Facility | LRGOP-C007 Station Operations | Ex 3, Ch 8 | No | On-Going | Annual | 6026.6487 | 6150.6448 | 12177.2936 | 6033.303 | 6531.002 | 12564.3049 | 380.3572 | 387.0114 | 0.06184 | 0.031781 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
343 | Expense | GT&S | JP | GT Station Maintenance | JPN | Station Operations | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C016 Station Operations | Ex 3, Ch 8 | No | On-Going | Annual | 6026.6487 | 6150.6448 | 12177.2936 | 6033.303 | 6531.002 | 12564.3049 | 380.3572 | 387.0114 | 0.06184 | 0.031781 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
344 | Expense | GT&S | JP | GT Station Maintenance | JPO | PM Storage Wells | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 570.257 | 581.9898 | 1152.2468 | 384.923 | 330.7638 | 715.6868 | -251.226 | -436.56 | -0.43167 | -0.37888 | NO | NO | non-unitized: This MAT has no measurable units because majority of the orders under these MATs exist as Asset Maintenance Backbone and Station (AMBBS) orders. AMBBS records “operations” which are not necessarily equivalent to a unit. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | N/A
345 | Expense | GT&S | JP | GT Station Maintenance | JPO | PM Storage Wells | Loss of Containment at Natural Gas Storage Well or Reservoir | NGSWR-C005 Preventive and Corrective Maintenance | Ex 3, Ch 8 | No | On-Going | Annual | 570.257 | 581.9898 | 1152.2468 | 384.923 | 330.7638 | 715.6868 | -251.226 | -436.56 | -0.43167 | -0.37888 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
346 | Expense | GT&S | JP | GT Station Maintenance | JPP | CM Storage Wells | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 81.2991 | 82.9718 | 164.2709 | 9.7878 | 69.4431 | 79.2309 | -13.5287 | -85.04 | -0.16305 | -0.51768 | NO | NO | non-unitized: This MAT has no measurable units because majority of the orders under these MATs exist as Asset Maintenance Backbone and Station (AMBBS) orders. AMBBS records “operations” which are not necessarily equivalent to a unit. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | N/A
347 | Expense | GT&S | JP | GT Station Maintenance | JPP | CM Storage Wells | Loss of Containment at Natural Gas Storage Well or Reservoir | NGSWR-C005 Preventive and Corrective Maintenance | Ex 3, Ch 8 | No | On-Going | Annual | 81.2991 | 82.9718 | 164.2709 | 9.7878 | 69.4431 | 79.2309 | -13.5287 | -85.04 | -0.16305 | -0.51768 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
348 | Expense | GT&S | JP | GT Station Maintenance | JPQ | CARB Leak Survey | SRM Total | SRM Total | Ex 3, Ch 10 | No | On-Going | annual | 3270.321 | 3337.6128 | 6607.9337 | 3332.4759 | 3756.9934 | 7089.4693 | 419.3806 | 481.5355 | 0.12565 | 0.072872 | NO | NO | non-unitized: This MAT has no measurable units because majority of the orders under these MATs exist as Asset Maintenance Backbone and Station (AMBBS) orders. AMBBS records “operations” which are not necessarily equivalent to a unit. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | N/A
349 | Expense | GT&S | JP | GT Station Maintenance | JPQ | CARB Leak Survey | Loss of Containment at Natural Gas Storage Well or Reservoir | NGSWR-C006 CARB Leak Management | Ex 3, Ch 10 | No | On-Going | annual | 3270.321 | 3337.6128 | 6607.9337 | 3332.4759 | 3756.9934 | 7089.4693 | 419.3806 | 481.5355 | 0.12565 | 0.072872 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
350 | Expense | GT&S | JP | GT Station Maintenance | JPR | CARB Leak Repairs | SRM Total | SRM Total | Ex 3, Ch 10 | No | On-Going | Annual | 2544.7033 | 2597.0645 | 5141.7678 | 416.1063 | 504.534 | 920.6403 | -2092.5305 | -4221.1275 | -0.80573 | -0.82095 | NO | NO | non-unitized: This MAT has no measurable units because majority of the orders under these MATs exist as Asset Maintenance Backbone and Station (AMBBS) orders. AMBBS records “operations” which are not necessarily equivalent to a unit. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | N/A
351 | Expense | GT&S | JP | GT Station Maintenance | JPR | CARB Leak Repairs | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C001 Transm Comprsr Station Corrective & Prevnt Maintn | Ex 3, Ch 10 | No | On-Going | Annual | 2544.7033 | 2597.0645 | 5141.7678 | 416.1063 | 504.534 | 920.6403 | -2092.5305 | -4221.1275 | -0.80573 | -0.82095 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
352 | Expense | GT&S | JP | GT Station Maintenance | JPR | CARB Leak Repairs | Loss of Containment at Natural Gas Storage Well or Reservoir | NGSWR-C006 CARB Leak Management | Ex 3, Ch 10 | No | On-Going | Annual | 2544.7033 | 2597.0645 | 5141.7678 | 416.1063 | 504.534 | 920.6403 | -2092.5305 | -4221.1275 | -0.80573 | -0.82095 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
353 | Expense | GT&S | JP | GT Station Maintenance | JP#(c) | Not assigned | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 0 | 0 | 0 | 401.0857 | 0.35357 | 401.4393 | 0.35357 | 401.4393 | 0% | N/A | NO | NO | non-unitized: This MAT has no measurable units because majority of the orders under these MATs exist as Asset Maintenance Backbone and Station (AMBBS) orders. AMBBS records “operations” which are not necessarily equivalent to a unit. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | N/A
354 | Expense | GT&S | JT | GT Reliability & General Maint | JT0 | Public Awareness | SRM Total | SRM Total | Ex 3, Ch 5 | No | On-Going | Annual | 3436.5769 | 3473.6995 | 6910.2764 | 2117.3198 | 1995.4611 | 4112.781 | -1478.2384 | -2797.4954 | -0.42555 | -0.40483 | NO | NO | non-unitized: This MAT has no measurable units because it is our funding for the Public Awareness program management. This MAT supports the outreach required pursuant to API RP 1162 which contains many activities to include direct mailings to parties with properties within 1000’ of a pipeline, other educational material publication, social media postings, etc. This program also manages our Public Awareness and Damage Prevention program documentation. There are no specific units associated with the activities performed in the Public Awareness MAT to meet the requirements of RP 1162. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | N/A
355 | Expense | GT&S | JT | GT Reliability & General Maint | JT0 | Public Awareness | Loss of Containment on Gas Transmission Pipeline | LOCTM-C011 Public Awareness | Ex 3, Ch 5 | No | On-Going | Annual | 3436.5769 | 3473.6995 | 6910.2764 | 2117.3198 | 1995.4611 | 4112.781 | -1478.2384 | -2797.4954 | -0.42555 | -0.40483 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
356 | Expense | GT&S | JT | GT Reliability & General Maint | JT1 | Engineering Support | SRM Total | SRM Total | Ex 3, Ch 5 | No | On-Going | Annual | 2572.1801 | 2599.9653 | 5172.1453 | -33.8536 | 23.2923 | -10.5613 | -2576.673 | -5182.7066 | -0.99104 | -1.002 | NO | NO | non-unitized: This MAT has no measurable units because it is used to record costs for various types of non-capitalizable work related to pipe investigations and field engineering support. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | Under | Proceeding as planned | N/A
357 | Expense | GT&S | JT | GT Reliability & General Maint | JT1 | Engineering Support | Loss of Containment on Gas Transmission Pipeline | LOCTM-C027 Pipe Investigations and Field Engineering | Ex 3, Ch 5 | No | On-Going | Annual | 2572.1801 | 2599.9653 | 5172.1453 | -33.8536 | 23.2923 | -10.5613 | -2576.673 | -5182.7066 | -0.99104 | -1.002 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
358 | Expense | GT&S | JT | GT Reliability & General Maint | JT2 | Water and Levee Crossings | SRM Total | SRM Total | Ex 3, Ch 5 | No | On-Going | annual | 1386.5269 | 1401.5044 | 2788.0312 | 465.6519 | 553.6942 | 1019.3462 | -847.8101 | -1768.6851 | -0.60493 | -0.63438 | NO | NO | non-unitized: This MAT has no measurable units because it is used to record costs for monitoring jurisdictional water crossings, jurisdictional levee crossings, and non-jurisdictional water crossings. The type of work performed are not comparable. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | N/A
359 | Expense | GT&S | JT | GT Reliability & General Maint | JT2 | Water and Levee Crossings | Loss of Containment on Gas Transmission Pipeline | LOCTM-C007 Shallow and Exposed Pipe (Including Water and Levee Crossing | Ex 3, Ch 5 | No | On-Going | annual | 1386.5269 | 1401.5044 | 2788.0312 | 465.6519 | 553.6942 | 1019.3462 | -847.8101 | -1768.6851 | -0.60493 | -0.63438 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
360 | Expense | GT&S | JT | GT Reliability & General Maint | JT3(i) | Fault Crossings | SRM Total | SRM Total | Ex 3, Ch 5 | No | On-Going | Annual | 1076.1995 | 1087.8248 | 2164.0244 | 180.2654 | 147.798 | 328.0635 | -940.0268 | -1835.9609 | -0.86413 | -0.8484 | NO | NO | non-unitized: This MAT has no measurable units because it is used to record costs for conducting studies of where gas transmission pipelines cross active and potentially active earthquake fault lines, and monitoring fault creep. The type of work performed are not comparable. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | N/A
361 | Expense | GT&S | JT | GT Reliability & General Maint | JT3(i) | Fault Crossings | Loss of Containment on Gas Transmission Pipeline | LOCTM-C004 Earthquake Fault Crossings | Ex 3, Ch 5 | No | On-Going | Annual | 1076.1995 | 1087.8248 | 2164.0244 | 180.2654 | 147.798 | 328.0635 | -940.0268 | -1835.9609 | -0.86413 | -0.8484 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
362 | Expense | GT&S | JT | GT Reliability & General Maint | JT4 | Shallow and Exposed Pipe | SRM Total | SRM Total | Ex 3, Ch 5 | No | On-Going | annual | 2751.2681 | 2780.9878 | 5532.256 | 942.1452 | 234.9186 | 1177.0638 | -2546.0692 | -4355.1921 | -0.91553 | -0.78724 | NO | NO | Projects | 4 | 4 | 8 | 1 | 0 | 1 | -4 | -7 | -100% | -87.5% | YES | N/A | Actual units were lower than Imputed units due to no projects were executed under this MAT, as funds were reallocated to other risk and compliance-driven programs. Additionally, the planned Project A-513 was canceled due to a low likelihood of further erosion at the site, which is being monitored under the TIMP Geohazards Program. | Under | On-Target | On-Target | Proceeding as planned | This programs work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to mitigate locations where a pipeline has insufficient cover, is vulnerable to damage from third parties, or has become exposed due to natural forces.
363 | Expense | GT&S | JT | GT Reliability & General Maint | JT4 | Shallow and Exposed Pipe | Loss of Containment on Gas Transmission Pipeline | LOCTM-C007 Shallow and Exposed Pipe (Including Water and Levee Crossing | Ex 3, Ch 5 | No | On-Going | annual | 2751.2681 | 2780.9878 | 5532.256 | 942.1452 | 234.9186 | 1177.0638 | -2546.0692 | -4355.1921 | -0.91553 | -0.78724 | N/A | N/A | N/A | 4 | 4 | 8 | 1 | 0 | 1 | -4 | -7 | -100% | -87.5% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
364 | Expense | GT&S | JT | GT Reliability & General Maint | JT6 | Pipe Replacements - (<50Ft) | SRM Total | SRM Total | Ex 3, Ch 5 | No | On-Going | Annual | 11283.8702 | 11405.7607 | 22689.6309 | 697.6098 | 139.1123 | 836.7221 | -11266.6484 | -21852.9088 | -0.9878 | -0.96312 | YES | YES | Miles | 0.17 | 0 | 0.17 | 0 | 0 | 0 | 0 | -0.17 | 0% | -100% | NO | Actual costs were lower than imputed because less work materialized owing to more scopes of work that reached 50 foot threshold for Capitalization. | Actual units were less than imputed because less work materialized owing to more scopes of work that reached 50 foot threshold for Capitalization. | Under | On-Target | Under | Proceeding as planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The purpose of this program is to implement Non-TIMP expense pipe replacements as an alternative option to strength testing.
365 | Expense | GT&S | JT | GT Reliability & General Maint | JT6 | Pipe Replacements - (<50Ft) | Loss of Containment on Gas Transmission Pipeline | LOCTM-M003 Non-TIMP Strength Testing | Ex 3, Ch 5 | No | On-Going | Annual | 11283.8702 | 11405.7607 | 22689.6309 | 697.6098 | 139.1123 | 836.7221 | -11266.6484 | -21852.9088 | -0.9878 | -0.96312 | N/A | N/A | N/A | 0.17 | 0 | 0.17 | 0 | 0 | 0 | 0 | -0.17 | 0% | -100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
366 | Expense | GT&S | JT | GT Reliability & General Maint | JT8 | Gas Quality Assessment - Exp | SRM Total | SRM Total | Ex 3, Ch 6 | No | On-Going | Annual | 2124.3321 | 2146.4864 | 4270.8185 | 1559.8324 | 2731.3066 | 4291.139 | 584.8202 | 20.3204 | 0.27245 | 0.004758 | NO | NO | non-unitized: This MAT has no measurable units because MAT includes programmatic costs for ongoing activities which are not unitized. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | N/A
367 | Expense | GT&S | JT | GT Reliability & General Maint | JT8 | Gas Quality Assessment - Exp | Large Overpressure Event Downstream of Gas M&C Facility | LRGOP-C005 Gas Quality Assessment - Expense | Ex 3, Ch 6 | No | On-Going | Annual | 2124.3321 | 2146.4864 | 4270.8185 | 1559.8324 | 2731.3066 | 4291.139 | 584.8202 | 20.3204 | 0.27245 | 0.004758 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
368 | Expense | GT&S | JT | GT Reliability & General Maint | JT8 | Gas Quality Assessment - Exp | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C027 Gas Quality Assessment - Expense | Ex 3, Ch 6 | No | On-Going | Annual | 2124.3321 | 2146.4864 | 4270.8185 | 1559.8324 | 2731.3066 | 4291.139 | 584.8202 | 20.3204 | 0.27245 | 0.004758 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
369 | Expense | GT&S | JT | GT Reliability & General Maint | JT9 | Hydrostatic Tstng - Class Lctn | SRM Total | SRM Total | Ex 3, Ch 5 | No | On-Going | Annual | 899.4658 | 909.182 | 1808.6478 | 179.0848 | 4148.3875 | 4327.4723 | 3239.2056 | 2518.8246 | 3.5628 | 1.3927 | NO | NO | non-unitized: This MAT has no measurable units because mitigation lengths for class location change cannot be ascertained until the completion of annual class location studies. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | N/A
370 | Expense | GT&S | JT | GT Reliability & General Maint | JT9 | Hydrostatic Tstng - Class Lctn | Loss of Containment on Gas Transmission Pipeline | LOCTM-C025 Class Location Change | Ex 3, Ch 5 | No | On-Going | Annual | 899.4658 | 909.182 | 1808.6478 | 179.0848 | 4148.3875 | 4327.4723 | 3239.2056 | 2518.8246 | 3.5628 | 1.3927 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
371 | Expense | GT&S | JT | GT Reliability & General Maint | JTB | Pipeline Repair | SRM Total | SRM Total | Ex 3, Ch 5 | No | On-Going | Annual | 6834.6356 | 6908.4645 | 13743.1001 | 4751.8962 | 12361.05 | 17112.9462 | 5452.5855 | 3369.8461 | 0.78926 | 0.2452 | NO | YES | non-unitized: This MAT has no measurable units because it is used to record costs for various types of expense work related to TIMP pipeline repair. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | Actual costs were higher than imputed due to more than anticipated higher-risk or compliance-driven repairs and replacement shorter than 50 feet | N/A | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to mitigate graded leaks and reliability risks along gas transmission pipelines.
372 | Expense | GT&S | JT | GT Reliability & General Maint | JTB | Pipeline Repair | Loss of Containment on Gas Transmission Pipeline | LOCTM-C008 Pipeline Safety and Reliability | Ex 3, Ch 5 | No | On-Going | Annual | 6834.6356 | 6908.4645 | 13743.1001 | 4751.8962 | 12361.05 | 17112.9462 | 5452.5855 | 3369.8461 | 0.78926 | 0.2452 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
373 | Expense | GT&S | JT | GT Reliability & General Maint | JTD | Pipeline Other | SRM Total | SRM Total | Ex 3, Ch 5 | No | On-Going | Annual | 18984.9792 | 19190.0584 | 38175.0376 | 4525.1633 | 5400.3807 | 9925.5441 | -13789.6777 | -28249.4935 | -0.71858 | -0.74 | YES | YES | non-unitized: This MAT has no measurable units because it is used to record costs for various types of expense work related to TIMP pipeline investigation. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | Actual costs were lower than imputed due to overestimated execution in the 2023 rate case, driven by uncertainty around Mega Rule Part 1 (RIN1) compliance. In practice, compliance was achieved at much lower cost. Additional savings came from deferring lower-risk investigations to prioritize higher-risk, non-JTD work, while maintaining RIN1 and JTD compliance. | N/A | On-Target | On-Target | Under | Proceeding as planned | This JTD Pipe Investigations program's work is ongoing and will continue in PG&E's 2027 GRC period. The purpose of this program is to perform material properties testing, verify pipeline segments and fittings, establish MAOP to comply with 49 CFR § 192.619 by validating unknown or assumed pipe and fitting specifications and potentially mitigating MAOP Design and underrated pipe issues, perform data validation, perform research for valid and invalid strength test records and pipeline material records, manage Opportunistic Inspection Program (OIP) and targeted inspections to comply with federal codes 49 CFR § 192.607 and § 192.712, investigate anomalous conditions and potential mechanical damage, and investigate cause and extent of failures or incidents to comply with 49 CFR § 192.617. This JTD program will continue to be medium priority compared to other gas tranmission pipe programs.
374 | Expense | GT&S | JT | GT Reliability & General Maint | JTD | Pipeline Other | Loss of Containment on Gas Transmission Pipeline | LOCTM-C027 Pipe Investigations and Field Engineering | Ex 3, Ch 5 | No | On-Going | Annual | 18984.9792 | 19190.0584 | 38175.0376 | 4525.1633 | 5400.3807 | 9925.5441 | -13789.6777 | -28249.4935 | -0.71858 | -0.74 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
375 | Expense | GT&S | JT | GT Reliability & General Maint | JTH | Permits & Fees Projects | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 3, Ch 8 | No | On-Going | Annual | 7906.4386 | 7991.8318 | 15898.2704 | 8973.6743 | 9450.8214 | 18424.4956 | 1458.9895 | 2526.2252 | 0.18256 | 0.1589 | NO | NO | non-unitized: This MAT has no measurable units because it is used to record costs for permits and fees associated with the operations of Gas Transmission stations. (Examples include McDonald Island Reclamation Fees, Gas Lease Fees, Department of Transportation Fees). | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | N/A
376 | Expense | GT&S | JT | GT Reliability & General Maint | JTK | Vegetation Manage Project | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 16877.2154 | 17059.4972 | 33936.7126 | 7397.9605 | 5357.349 | 12755.3096 | -11702.1482 | -21181.4031 | -0.68596 | -0.62414 | YES | YES | Non-unitized: This MAT has no measurable units because this MAT includes a mix of work involved in maintaining transmission Right-Of-Ways (ROW), some of which can be tracked in units (ex: tree removals), while some cannot like inspections. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | Actual costs were lower than imputed due to work reprioritization driven by Transmission Integrity Management Program, the budget was reduced by $11M. | N/A | Under | Under | Under | Rescheduled | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to support the safety and integrity of gas pipeline by inspecting, removing and maintaining vegetation in the ROW. This program continues to be reassessed for its priority relative to other emerging work and is rescheduled accordingly.
377 | Expense | GT&S | JT | GT Reliability & General Maint | JTK | Vegetation Manage Project | Loss of Containment on Gas Transmission Pipeline | LOCTM-C017 Vegetation Manage Project | Ex 3, Ch 8 | No | On-Going | Annual | 16877.2154 | 17059.4972 | 33936.7126 | 7397.9605 | 5357.349 | 12755.3096 | -11702.1482 | -21181.4031 | -0.68596 | -0.62414 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
378 | Expense | GT&S | JT | GT Reliability & General Maint | JTL | FIMP Risk Management | SRM Total | SRM Total | Ex 3, Ch 6 | No | On-Going | Annual | 2790.5397 | 2819.6418 | 5610.1815 | 1842.9263 | 1746.991 | 3589.9173 | -1072.6507 | -2020.2642 | -0.38042 | -0.36011 | NO | NO | non-unitized: This MAT has no measurable units because MAT includes programmatic costs for ongoing activities which are not unitized. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | N/A
379 | Expense | GT&S | JT | GT Reliability & General Maint | JTL | FIMP Risk Management | Large Overpressure Event Downstream of Gas M&C Facility | LRGOP-C006 FIMP Risk Assessment | Ex 3, Ch 6 | No | On-Going | Annual | 2790.5397 | 2819.6418 | 5610.1815 | 1842.9263 | 1746.991 | 3589.9173 | -1072.6507 | -2020.2642 | -0.38042 | -0.36011 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
380 | Expense | GT&S | JT | GT Reliability & General Maint | JTL | FIMP Risk Management | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C022 FIMP Risk Assessment | Ex 3, Ch 6 | No | On-Going | Annual | 2790.5397 | 2819.6418 | 5610.1815 | 1842.9263 | 1746.991 | 3589.9173 | -1072.6507 | -2020.2642 | -0.38042 | -0.36011 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
381 | Expense | GT&S | JT | GT Reliability & General Maint | JTM | Uprates | SRM Total | SRM Total | Ex 3, Ch 11 | No | On-Going | Annual | 997.7546 | 1008.5804 | 2006.335 | 72.0873 | 3321.1296 | 3393.2169 | 2312.5492 | 1386.8819 | 2.2929 | 0.69125 | NO | NO | non-unitized: This MAT has no measurable units because it is used to record costs to increase capacity of a hydraulically independent system as an alternative to increasing capacity by installing new facilities. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | N/A
382 | Expense | GT&S | JT | GT Reliability & General Maint | JTM | Uprates | Insufficient Capacity to Meet Customer Demand | CPCTY-M004 GT Capacity Uprates | Ex 3, Ch 11 | No | On-Going | Annual | 997.7546 | 1008.5804 | 2006.335 | 72.0873 | 3321.1296 | 3393.2169 | 2312.5492 | 1386.8819 | 2.2929 | 0.69125 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
383 | Expense | GT&S | JT | GT Reliability & General Maint | JTO | Encroachments Structures & ROW | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-Going | Annual | 1264.5425 | 1278.2002 | 2542.7427 | 981.8896 | 1393.9931 | 2375.8827 | 115.7929 | -166.8599 | 0.090591 | -0.065622 | NO | NO | non-unitized: This MAT has no measurable units because it combines different workstreams, access roads and structural encroachments, in a single MAT. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | N/A
384 | Expense | GT&S | JT | GT Reliability & General Maint | JTO | Encroachments Structures & ROW | Loss of Containment on Gas Transmission Pipeline | LOCTM-C018 Encroachments | Ex 3, Ch 8 | No | On-Going | Annual | 1264.5425 | 1278.2002 | 2542.7427 | 981.8896 | 1393.9931 | 2375.8827 | 115.7929 | -166.8599 | 0.090591 | -0.065622 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
385 | Expense | GT&S | JT | GT Reliability & General Maint | JTQ | Class Location Studies | SRM Total | SRM Total | Ex 3, Ch 5 | No | On-Going | Annual | 2185.0905 | 2208.6942 | 4393.7847 | 1588.1424 | 1580.8793 | 3169.0217 | -627.8149 | -1224.763 | -0.28425 | -0.27875 | NO | NO | non-unitized: This MAT has no measurable units because it is an continuous, annual class location study. The annual class location study includes: orthographically-corrected aerial photography; occupancy field verification; creation of a digitized structures layer; and annual class analysis, completed via a qualified third-party firm and verified internally. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | N/A
386 | Expense | GT&S | JT | GT Reliability & General Maint | JTQ | Class Location Studies | Loss of Containment on Gas Transmission Pipeline | LOCTM-C025 Class Location Change | Ex 3, Ch 5 | No | On-Going | Annual | 2185.0905 | 2208.6942 | 4393.7847 | 1588.1424 | 1580.8793 | 3169.0217 | -627.8149 | -1224.763 | -0.28425 | -0.27875 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
387 | Expense | GT&S | JT | GT Reliability & General Maint | JTR | Valve Program | SRM Total | SRM Total | Ex 3, Ch 5 | No | On-Going | Annual | 1370.7326 | 1385.5395 | 2756.2722 | 930.1459 | 789.1906 | 1719.3366 | -596.3489 | -1036.9356 | -0.43041 | -0.37621 | NO | NO | non-unitized: This MAT is non-unitized because it is used to record costs for various types of non-capitalizable work related to valve program | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | N/A
388 | Expense | GT&S | JT | GT Reliability & General Maint | JTR | Valve Program | Loss of Containment on Gas Transmission Pipeline | LOCTM-C024 Valve Safety and Reliability | Ex 3, Ch 5 | No | On-Going | Annual | 1370.7326 | 1385.5395 | 2756.2722 | 930.1459 | 789.1906 | 1719.3366 | -596.3489 | -1036.9356 | -0.43041 | -0.37621 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
389 | Expense | GT&S | JT | GT Reliability & General Maint | JTT | Geo-Hazard Mitigations | SRM Total | SRM Total | Ex 3, Ch 5 | No | On-Going | annual | 127.2186 | 128.5928 | 255.8114 | 158.9091 | 396.1266 | 555.0357 | 267.5338 | 299.2243 | 2.0805 | 1.1697 | NO | NO | non-unitized: This MAT has no measurable units because it is used to record costs for mitigating geo-hazards such as soil-creep, dormant landslides with potential to re-activate, and subsidence. The type of mitigation work performed are not comparable. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | N/A
390 | Expense | GT&S | JT | GT Reliability & General Maint | JTT | Geo-Hazard Mitigations | Loss of Containment on Gas Transmission Pipeline | LOCTM-C001 Geo-Hazard Threat Identification and Mitigation | Ex 3, Ch 5 | No | On-Going | annual | 127.2186 | 128.5928 | 255.8114 | 158.9091 | 396.1266 | 555.0357 | 267.5338 | 299.2243 | 2.0805 | 1.1697 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
391 | Expense | GT&S | JT | GT Reliability & General Maint | JTV | Station Strength Test Exp C&P | SRM Total | SRM Total | Ex 3, Ch 6 | No | #N/A | 9 | 2279.0093 | 2302.7767 | 4581.786 | 555.1061 | -113.5968 | 441.5092 | -2416.3735 | -4140.2768 | -1.0493 | -0.90364 | NO | NO | non-unitized: This MAT has no measurable units because project work that occurs under this MAT is non-fungible and covers a wide range of asset types, and scope of assets requiring work. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | N/A
392 | Expense | GT&S | JT | GT Reliability & General Maint | JTV | Station Strength Test Exp C&P | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-M006 Station Strength Test | Ex 3, Ch 6 | No | #N/A | 9 | 2279.0093 | 2302.7767 | 4581.786 | 555.1061 | -113.5968 | 441.5092 | -2416.3735 | -4140.2768 | -1.0493 | -0.90364 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
393 | Expense | GT&S | JT | GT Reliability & General Maint | JTW | Routine Spend M&C - Expense | SRM Total | SRM Total | Ex 3, Ch 6 | No | On-Going | Annual | 4676.4595 | 4725.2294 | 9401.6889 | 4102.8884 | 4445.0676 | 8547.9559 | -280.1619 | -853.733 | -0.059291 | -0.090806 | NO | NO | non-unitized: This MAT has no measurable units because this is a routine spend MAT. Includes a combination non-fungible project work and programmatic activities. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | N/A
394 | Expense | GT&S | JT | GT Reliability & General Maint | JTW | Routine Spend M&C - Expense | Large Overpressure Event Downstream of Gas M&C Facility | LRGOP-C004 Routine Spend M&C | Ex 3, Ch 6 | No | On-Going | Annual | 4676.4595 | 4725.2294 | 9401.6889 | 4102.8884 | 4445.0676 | 8547.9559 | -280.1619 | -853.733 | -0.059291 | -0.090806 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
395 | Expense | GT&S | JT | GT Reliability & General Maint | JTW | Routine Spend M&C - Expense | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C007 Routine Spend M&C | Ex 3, Ch 6 | No | On-Going | Annual | 4676.4595 | 4725.2294 | 9401.6889 | 4102.8884 | 4445.0676 | 8547.9559 | -280.1619 | -853.733 | -0.059291 | -0.090806 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
396 | Expense | GT&S | JT | GT Reliability & General Maint | JTX | GT Over Pressure Protection | SRM Total | SRM Total | Ex 3, Ch 6 | No | On-Going | Annual | 0 | 0 | 0 | 1056.6352 | 1086.9829 | 2143.6181 | 1086.9829 | 2143.6181 | 0% | N/A | NO | NO | non-unitized: This MAT has no measurable units because it is an expense code that captures a variety of studies, reports, and small projects that support PG&E’s Overpressure Elimination program objectives, all of which have different tasks and costs that are not comparable. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | N/A
397 | Expense | GT&S | JT | GT Reliability & General Maint | JTX | GT Over Pressure Protection | Large Overpressure Event Downstream of Gas M&C Facility | LRGOP-M002 GT Overpressure Protection | Ex 3, Ch 6 | No | On-Going | Annual | 0 | 0 | 0 | 1056.6352 | 1086.9829 | 2143.6181 | 1086.9829 | 2143.6181 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
398 | Expense | GT&S | JT | GT Reliability & General Maint | JTY | Routine Spend C&P Expense | SRM Total | SRM Total | Ex 3, Ch 6 | No | On-Going | Annual | 8776.6785 | 8868.2089 | 17644.8875 | 9186.6865 | 6494.9808 | 15681.6673 | -2373.2281 | -1963.2202 | -0.26761 | -0.11126 | NO | NO | non-unitized: This MAT has no measurable units because this is a routine spend MAT. Includes a combination non-fungible project work and programmatic activities. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | N/A
399 | Expense | GT&S | JT | GT Reliability & General Maint | JTY | Routine Spend C&P Expense | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C020 Routine Spend C&P | Ex 3, Ch 6 | No | On-Going | Annual | 8776.6785 | 8868.2089 | 17644.8875 | 9186.6865 | 6494.9808 | 15681.6673 | -2373.2281 | -1963.2202 | -0.26761 | -0.11126 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
400 | Expense | GT&S | LV | GTS Station Assessments-BA | LV1 | Engineering Crtcl Assmnt 1 | SRM Total | SRM Total | Ex 3, Ch 6 | No | On-Going | Annual | 0 | 0 | 0 | 1.63 | 15.5528 | 17.1828 | 15.5528 | 17.1828 | 0% | N/A | NO | NO | non-unitized: This MAT has no measurable units because project work that occurs under this MAT is non-fungible and covers a wide range of asset types, and scope of assets requiring work. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | N/A
401 | Expense | GT&S | LV | GTS Station Assessments-BA | LV1 | Engineering Crtcl Assmnt 1 | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-M007 Engineering Critical Assessment 1 | Ex 3, Ch 6 | No | On-Going | Annual | 0 | 0 | 0 | 1.63 | 15.5528 | 17.1828 | 15.5528 | 17.1828 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
402 | Expense | GT&S | LV | GTS Station Assessments-BA | LV2 | Engineering Crtcl Assmnt 2 | SRM Total | SRM Total | Ex 3, Ch 6 | No | #N/A | 9 | 5474.1818 | 5546.7649 | 11020.9468 | 3061.8889 | 2525.9326 | 5587.8216 | -3020.8323 | -5433.1252 | -0.54461 | -0.49298 | NO | NO | non-unitized: This MAT has no measurable units because project work that occurs under this MAT is non-fungible and covers a wide range of asset types, and scope of assets requiring work. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | Under | Proceeding as planned | N/A
403 | Expense | GT&S | LV | GTS Station Assessments-BA | LV2 | Engineering Crtcl Assmnt 2 | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-M008 Engineering Critical Assessment 2 | Ex 3, Ch 6 | No | #N/A | 9 | 5474.1818 | 5546.7649 | 11020.9468 | 3061.8889 | 2525.9326 | 5587.8216 | -3020.8323 | -5433.1252 | -0.54461 | -0.49298 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
404 | Expense | GT&S | OM | Operational Management | OM# (c) | Not assigned | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 3, Ch 13 | No | On-Going | Annual | 8663.7549 | 8908.993 | 17572.7479 | 3708.9081 | 5415.1061 | 9124.0141 | -3493.8869 | -8448.7338 | -0.39218 | -0.48079 | NO | NO | non-unitized: This MAT has no measurable units because this program records labor costs. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | NO | N/A | N/A | On-Target | On-Target | Under | Proceeding as planned | N/A
405 | Expense | Electric Distribution | AB | Misc Expense | AB6 | EPR Expense | SRM Total | SRM Total | Ex 4, Ch 4.1 Ex 4, Ch 4.2 Ex 4, Ch 5 | No | On-going | Annual | 193108.353 | 196495.5021 | 389603.8551 | 31503.0268 | 41146.9351 | 72649.9619 | -155348.567 | -316953.8932 | -79.06% | -81.35% | YES | YES | # of wildfire cameras | 10 | 10 | 20 | 0 | 0 | 0 | -10 | -20 | -100% | -100% | YES | Program expenses were below imputed regulatory values because several programs that were forecast in AB6 are being recorded in new MAT codes under MWC WF, which was created after the 2023 GRC was filed. The following program expenses were forecast in MAT AB6 in the 2023 GRC and are reflected in the imputed regulatory values: Emergency Preparedness and Response (EP&R), Cameras, Public Safety Power Shutoffs (PSPS), the Safety and Infrastructure Protection Team (SIPT), and Wildfire Mitigation Support. Actual expenses for EP&R remain recorded in MAT AB6 with a small portion also recorded to MAT IG#. Actual expenses for Cameras, EPSS, PSPS, SIPT and Weather Station Maintenance are recorded in various MAT codes under MWC WF and are explained further below. The difference between the imputed regulatory value and actual expenses for the EP&R portion remaining in MAT AB6 is below the variance threshold. | Actual units were lower than imputed units because actual units are reported in MAT Code WFC. There were 10 cameras forecasted in AB6 and 25 completed in WFC in 2024. See MAT WFC for an explanation of why PG&E completed more units than forecasted. | Under | On-Target | Under | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The following wildfire mitigation initiatives were forecast in MAT AB6 in the 2023 GRC and are reflected in the imputed regulatory values: EP&R, Cameras, EPSS, PSPS, SIPT, and Wildfire Mitigation Support. EP&R remains under MAT AB6 with a small portion also in MAT IG#. Cameras, EPSS, PSPS, SIPT and Weather Station Maintenance actual costs are reported in various MATs in MWC 3U and are explained in further detail in MWC WF below. The scope and budget is represented as under because for the remainder of the GRC cycle MAT AB6 will show under costs and units because the actuals are captured in MWC WF. Otherwise the programs forecasted in AB6 and remaining as recorded in AB6 are proceeding as planned.
406 | Expense | Electric Distribution | AB | Misc Expense | AB6 | EPR Expense | Emergency Preparedness & Response | EPNDR-C000: EP&R Controls | Ex 4, Ch 4.1 Ex 4, Ch 4.2 Ex 4, Ch 5 | Yes | N/A | N/A | 5397.4967 | 5461.0783 | 10858.5751 | 3670.2988 | 5914.8362 | 9585.135 | 453.7579 | -1273.44 | 8.309% | -11.73% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
407 | Expense | Electric Distribution | AB | Misc Expense | AB6 | EPR Expense | Emergency Preparedness & Response | EPNDR-C001: Situational Awareness and Forecasting Initiatives - SOPP Improvements | Ex 4, Ch 4.1 Ex 4, Ch 4.2 Ex 4, Ch 5 | Yes | N/A | N/A | 2206.5298 | 2232.5224 | 4439.0522 | 0 | 0 | 0 | -2232.5224 | -4439.0522 | -100% | -100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
408 | Expense | Electric Distribution | AB | Misc Expense | AB6 | EPR Expense | Emergency Preparedness & Response | EPNDR-C002: Situational Awareness and Forecasting Initiatives - WSOC | Ex 4, Ch 4.1 Ex 4, Ch 4.2 Ex 4, Ch 5 | Yes | N/A | N/A | 7808.5788 | 7900.5626 | 15709.1415 | 4644.7696 | 5824.2497 | 10469.0193 | -2076.3129 | -5240.1222 | -26.28% | -33.36% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
409 | Expense | Electric Distribution | AB | Misc Expense | AB6 | EPR Expense | Emergency Preparedness & Response | EPNDR-C004: EP&R Field Operations Technology | Ex 4, Ch 4.1 Ex 4, Ch 4.2 Ex 4, Ch 5 | Yes | N/A | N/A | 0 | 0 | 0 | 0 | 0.10075 | 0.10075 | 0.10075 | 0.10075 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
410 | Expense | Electric Distribution | AB | Misc Expense | AB6 | EPR Expense | Emergency Preparedness & Response | EPNDR-C005: EP&R Field Operations | Ex 4, Ch 4.1 Ex 4, Ch 4.2 Ex 4, Ch 5 | Yes | N/A | N/A | 634.8764 | 642.3551 | 1277.2316 | 610.5359 | 0 | 610.5359 | -642.3551 | -666.6956 | -100% | -52.2% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
411 | Expense | Electric Distribution | AB | Misc Expense | AB6 | EPR Expense | Emergency Preparedness & Response | EPNDR-C006: EP&R Distribution Support Headcount | Ex 4, Ch 4.1 Ex 4, Ch 4.2 Ex 4, Ch 5 | Yes | N/A | N/A | 7506.5454 | 7594.9713 | 15101.5167 | 4577.3593 | 0 | 4577.3593 | -7594.9713 | -10524.1574 | -100% | -69.69% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
412 | Expense | Electric Distribution | AB | Misc Expense | AB6 | EPR Expense | Emergency Preparedness & Response | EPNDR-M000: EP&R Mitigations | Ex 4, Ch 4.1 Ex 4, Ch 4.2 Ex 4, Ch 5 | Yes | N/A | N/A | 4416.132 | 4468.1533 | 8884.2852 | 3005.8982 | 4839.4114 | 7845.3096 | 371.2581 | -1038.9756 | 8.309% | -11.69% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
413 | Expense | Electric Distribution | AB | Misc Expense | AB6 | EPR Expense | Wildfire | WLDFR-M005: Public Safety Power Shutoff - PSPS Event (Distribution) | Ex 4, Ch 4.1 Ex 4, Ch 4.2 Ex 4, Ch 5 | Yes | N/A | N/A | 75968.2247 | 77374.8368 | 153343.0615 | 0 | 0 | 0 | -77374.8368 | -153343.0615 | -100% | -100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
414 | Expense | Electric Distribution | AB | Misc Expense | AB6 | EPR Expense | Wildfire | WLDFR-M006: PSPS Reduction Initiatives | Ex 4, Ch 4.1 Ex 4, Ch 4.2 Ex 4, Ch 5 | Yes | N/A | N/A | 43987.727 | 44802.1952 | 88789.9222 | 0 | 1074.1592 | 1074.1592 | -43728.036 | -87715.763 | -97.6% | -98.79% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
415 | Expense | Electric Distribution | AB | Misc Expense | AB6 | EPR Expense | Wildfire | WLDFR-M07B: Situational Awareness and Forecasting Initiatives - Weather Station | Ex 4, Ch 4.1 Ex 4, Ch 4.2 Ex 4, Ch 5 | Yes | N/A | N/A | 1836.2456 | 1870.2451 | 3706.4907 | 0 | 0 | 0 | -1870.2451 | -3706.4907 | -100% | -100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
416 | Expense | Electric Distribution | AB | Misc Expense | AB6 | EPR Expense | Wildfire | WLDFR-M07D: Situational Awareness and Forecasting Initiatives - Cameras | Ex 4, Ch 4.1 Ex 4, Ch 4.2 Ex 4, Ch 5 | Yes | N/A | N/A | 8568.7652 | 8727.4227 | 17296.1879 | 0 | 0 | 0 | -8727.4227 | -17296.1879 | -100% | -100% | N/A | N/A | # of wildfire cameras | 10 | 10 | 20 | 0 | 0 | 0 | -10 | -20 | -100% | -100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
417 | Expense | Electric Distribution | AB | Misc Expense | AB6 | EPR Expense | Wildfire | WLDFR-M07E: Situational Awareness and Forecasting Initiatives - Satellite Fire Detection | Ex 4, Ch 4.1 Ex 4, Ch 4.2 Ex 4, Ch 5 | Yes | N/A | N/A | 376.812 | 383.789 | 760.601 | 0 | 0 | 0 | -383.789 | -760.601 | -100% | -100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
418 | Expense | Electric Distribution | AB | Misc Expense | AB6 | EPR Expense | Wildfire | WLDFR-M07G: Situational Awareness and Forecasting Initiatives - Partial Voltage Detection | Ex 4, Ch 4.1 Ex 4, Ch 4.2 Ex 4, Ch 5 | Yes | N/A | N/A | 242.23 | 246.7151 | 488.945 | 0 | 0 | 0 | -246.7151 | -488.945 | -100% | -100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
419 | Expense | Electric Distribution | AB | Misc Expense | AB6 | EPR Expense | Wildfire | WLDFR-M07I: Situational Awareness and Forecasting Initiatives - Advanced Fire Modeling | Ex 4, Ch 4.1 Ex 4, Ch 4.2 Ex 4, Ch 5 | Yes | N/A | N/A | 6602.7424 | 6724.9974 | 13327.7399 | 0 | 0 | 0 | -6724.9974 | -13327.7399 | -100% | -100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
420 | Expense | Electric Distribution | AB | Misc Expense | AB6 | EPR Expense | Wildfire | WLDFR-M07J: Situational Awareness and Forecasting Initiatives - Meteorology | Ex 4, Ch 4.1 Ex 4, Ch 4.2 Ex 4, Ch 5 | Yes | N/A | N/A | 455.329 | 463.7597 | 919.0887 | 0 | 10.8834 | 10.8834 | -452.8763 | -908.2053 | -97.65% | -98.82% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
421 | Expense | Electric Distribution | AB | Misc Expense | AB6 | EPR Expense | Wildfire | WLDFR-M07K: Situational Awareness and Forecasting Initiatives - Fire Potential Index | Ex 4, Ch 4.1 Ex 4, Ch 4.2 Ex 4, Ch 5 | Yes | N/A | N/A | 180.8615 | 184.2103 | 365.0718 | 0 | 0 | 0 | -184.2103 | -365.0718 | -100% | -100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
422 | Expense | Electric Distribution | AB | Misc Expense | AB6 | EPR Expense | Wildfire | WLDFR-M008: Safety and Infrastructure Protection Teams | Ex 4, Ch 4.1 Ex 4, Ch 4.2 Ex 4, Ch 5 | Yes | N/A | N/A | 26919.2562 | 27417.6877 | 54336.9439 | 0 | 0 | 0 | -27417.6877 | -54336.9439 | -100% | -100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
423 | Expense | Electric Distribution | AB | Misc Expense | AB6 | EPR Expense | Wildfire | WLDFR-M009: Community Wildfire Safety Program PMO | Ex 4, Ch 4.1 Ex 4, Ch 4.2 Ex 4, Ch 5 | Yes | N/A | N/A | 0 | 0 | 0 | 14994.1649 | 18500.3762 | 33494.541 | 18500.3762 | 33494.541 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
424 | Expense | Electric Distribution | AB | Misc Expense | AB6 | EPR Expense | Wildfire | WLDFR-M017: System Hardening - Remote Grid | Ex 4, Ch 4.1 Ex 4, Ch 4.2 Ex 4, Ch 5 | Yes | N/A | N/A | 0 | 0 | 0 | 0 | 18.7605 | 18.7605 | 18.7605 | 18.7605 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
425 | Expense | Electric Distribution | AB | Misc Expense | AB6 | EPR Expense | SRM (NON-RAMP) | SRM (NON-RAMP) | Ex 4, Ch 4.1 Ex 4, Ch 4.2 Ex 4, Ch 5 | Yes | N/A | N/A | 0 | 0 | 0 | 0 | 4964.158 | 4964.158 | 4964.158 | 4964.158 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
426 | Expense | Electric Distribution | AB | Misc Expense | AB# | Not assigned | SRM Total | SRM Total | Ex 4, Ch 21 Ex 4, Ch 22 Ex 4, Ch 4.3 Ex 4, Ch 4.4 | No | On-going | Annual | 63301.3873 | 63700.064 | 127001.4513 | 76372.3953 | 90989.645 | 167362.0403 | 27289.581 | 40360.589 | 42.84% | 31.78% | YES | YES | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Program expenses exceeded imputed regulatory values due to a reduction in funding to this program in the 2023 GRC Final Decision. PG&E's forecast for AB# miscellaneous expense for Electric Distribution in the 2023 GRC was reduced in the 2023 GRC Final Decision. PG&E continues to incur costs for the support activities forecasted in the 2023 GRC as well as some new activities, for amounts at and above PG&E's GRC forecast. | N/A | On-Target | On-Target | Over | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. MAT AB# tracks costs for miscellaneous ongoing programs that include several activities that support electric operations including but not limited to Regulatory Compliance and Quality Assurance, the Corrective Actions Program, Data Response Unit, and the Compliance Group. PG&E expects to continue to be over the adopted amount for this program in the 2023 GRC cycle.
427 | Expense | Electric Distribution | AB | Misc Expense | AB# | Not assigned | Distribution Overhead | DOVHD-M005: Additional Asset Data Capture | Ex 4, Ch 21 Ex 4, Ch 22 Ex 4, Ch 4.3 Ex 4, Ch 4.4 | Yes | N/A | N/A | 688.1409 | 682.8827 | 1371.0236 | 0 | 0 | 0 | -682.8827 | -1371.0236 | -100% | -100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
428 | Expense | Electric Distribution | AB | Misc Expense | AB# | Not assigned | Distribution Overhead | DOVHD-M009: Improved Distribution Risk Model | Ex 4, Ch 21 Ex 4, Ch 22 Ex 4, Ch 4.3 Ex 4, Ch 4.4 | Yes | N/A | N/A | 802.9983 | 796.9055 | 1599.9037 | 0 | 0 | 0 | -796.9055 | -1599.9037 | -100% | -100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
429 | Expense | Electric Distribution | AB | Misc Expense | AB# | Not assigned | Wildfire | WLDFR-M002: System Hardening | Ex 4, Ch 21 Ex 4, Ch 22 Ex 4, Ch 4.3 Ex 4, Ch 4.4 | Yes | N/A | N/A | 0 | 0 | 0 | 0 | 689.195 | 689.195 | 689.195 | 689.195 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
430 | Expense | Electric Distribution | AB | Misc Expense | AB# | Not assigned | Wildfire | WLDFR-M006: PSPS Reduction Initiatives | Ex 4, Ch 21 Ex 4, Ch 22 Ex 4, Ch 4.3 Ex 4, Ch 4.4 | Yes | N/A | N/A | 2037.0957 | 2074.8141 | 4111.9099 | 0 | 0 | 0 | -2074.8141 | -4111.9099 | -100% | -100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
431 | Expense | Electric Distribution | AB | Misc Expense | AB# | Not assigned | Wildfire | WLDFR-M009: Community Wildfire Safety Program PMO | Ex 4, Ch 21 Ex 4, Ch 22 Ex 4, Ch 4.3 Ex 4, Ch 4.4 | Yes | N/A | N/A | 14007.291 | 14266.6471 | 28273.9381 | 10987.5866 | 5380.278 | 16367.8647 | -8886.3691 | -11906.0734 | -62.29% | -42.11% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
432 | Expense | Electric Distribution | AB | Misc Expense | AB# | Not assigned | Wildfire | WLDFR-M07F: Situational Awareness and Forecasting Initiatives - Sensor IQ | Ex 4, Ch 21 Ex 4, Ch 22 Ex 4, Ch 4.3 Ex 4, Ch 4.4 | Yes | N/A | N/A | 3936.4324 | 4009.3186 | 7945.751 | 6e-05 | 0 | 6e-05 | -4009.3186 | -7945.7509 | -100% | -100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
433 | Expense | Electric Distribution | AB | Misc Expense | AB# | Not assigned | Wildfire | WLDFR-M017: System Hardening - Remote Grid | Ex 4, Ch 21 Ex 4, Ch 22 Ex 4, Ch 4.3 Ex 4, Ch 4.4 | Yes | N/A | N/A | 1523.7359 | 1551.9491 | 3075.685 | 2494.8968 | 2867.3509 | 5362.2477 | 1315.4018 | 2286.5627 | 84.76% | 74.34% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
434 | Expense | Electric Distribution | AB | Misc Expense | AB# | Not assigned | Wildfire | WLDFR-M002: System Hardening | Ex 4, Ch 21 Ex 4, Ch 22 Ex 4, Ch 4.3 Ex 4, Ch 4.4 | Yes | N/A | N/A | 0 | 0 | 0 | 877.683 | 422.072 | 1299.755 | 422.072 | 1299.755 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
435 | Expense | Electric Distribution | AB | Misc Expense | AB# | Not assigned | Distribution Overhead | DOVHD-M011: Remote Grid | Ex 4, Ch 21 Ex 4, Ch 22 Ex 4, Ch 4.3 Ex 4, Ch 4.4 | Yes | N/A | N/A | 1523.7359 | 1551.9491 | 3075.685 | 0 | 0 | 0 | -1551.9491 | -3075.685 | -100% | -100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
436 | Expense | Electric Distribution | AB | Misc Expense | AB# | Not assigned | Wildfire | POST-GRC: Post-GRC Mitigation | Ex 4, Ch 21 Ex 4, Ch 22 Ex 4, Ch 4.3 Ex 4, Ch 4.4 | Yes | N/A | N/A | 0 | 0 | 0 | 24.9751 | 1.0327 | 26.0079 | 1.0327 | 26.0079 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
437 | Expense | Electric Distribution | AB | Misc Expense | AB# | Not assigned | SRM (NON-RAMP) | SRM (NON-RAMP) | Ex 4, Ch 21 Ex 4, Ch 22 Ex 4, Ch 4.3 Ex 4, Ch 4.4 | Yes | N/A | N/A | 40305.3969 | 40317.1647 | 80622.5616 | 61987.2537 | 81629.7164 | 143616.9701 | 41312.5517 | 62994.4085 | 102.5% | 78.13% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
438 | Expense | Electric Distribution | AR | Read & Investigate Meters | N/A | Not assigned | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 8 | No | On-going | Annual | 10437.6496 | 10773.4238 | 21211.0734 | 9189.4821 | 9666.4487 | 18855.9309 | -1106.9751 | -2355.1426 | -10.28% | -11.1% | NO | NO | Field orders | 854733 | 854733 | 1709466 | 765469 | 705075 | 1470544 | -149658 | -238922 | -17.51% | -13.98% | NO | Below variance threshold. | Below variance threshold. | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
439 | Expense | Electric Distribution | AT | Emerging Technology | N/A | Not assigned | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 21 | No | On-going | Annual | 2185.0619 | 2210.4564 | 4395.5183 | 0 | 0 | 0 | -2210.4564 | -4395.5183 | -100% | -100% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The purpose of this program is to fund Research and Development (R&D) Emerging Technology public partnerships. Actual research and development (R&D) support costs that were adopted in MAT Code AT# in the 2023 GRC were recorded in MAT Code AB#. PG&E incurred approximately two million dollars in 2023 & 2024, recorded in MAT AB#, for emerging technology utility partnerships, which is aligned with the GRC-adopted amounts.
440 | Expense | Electric Distribution | BA | E Dist Operate System | BAF | Genl Operate | SRM Total | SRM Total | Ex 4, Ch 4.6 Ex 4, Ch 7 | No | On-going | Annual | 27814.8879 | 28667.4965 | 56482.3843 | 18147.8013 | 19098.6238 | 37246.425 | -9568.8727 | -19235.9593 | -33.38% | -34.06% | NO | YES | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Program expenses were below imputed regulatory values due to some work forecast in this MAT code being recorded to routine and major emergency. In addition, weather conditions were favorable in 2024 and weather related costs, like distribution operations to support storms, heat events and EPSS, were lower than forecasted. | N/A | On-Target | On-Target | Under | Proceeding as Planned | This program is on-going work and will continue in PG&E's 2023 GRC Period. The purpose of the work is to manage and control the electric distribution systems that directly benefit customers by reducing the frequency and duration of power outages while ensuring a more reliable power supply and regulatory compliance. For the remainder of the GRC cycle Operations including EPSS is on proceeding as planned.
441 | Expense | Electric Distribution | BA | E Dist Operate System | BAF | Genl Operate | Wildfire | WLDFR-M020: Enhanced Powerline Safety Settings | Ex 4, Ch 4.6 Ex 4, Ch 7 | Yes | N/A | N/A | 1821.9541 | 1856.9878 | 3678.9419 | 791.8355 | 1225.6732 | 2017.5087 | -631.3146 | -1661.4331 | -34% | -45.16% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
442 | Expense | Electric Distribution | BA | E Dist Operate System | BAF | Genl Operate | SRM (NON-RAMP) | SRM (NON-RAMP) | Ex 4, Ch 4.6 Ex 4, Ch 7 | Yes | N/A | N/A | 25992.9338 | 26810.5087 | 52803.4425 | 17355.9657 | 17872.9506 | 35228.9163 | -8937.5581 | -17574.5261 | -33.34% | -33.28% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
443 | Expense | Electric Distribution | BA | E Dist Operate System | BAH | FLISR Maintenance | SRM Total | SRM Total | Ex 4, Ch 4.6 Ex 4, Ch 7 | No | On-going | Annual | 4252.9219 | 4380.7067 | 8633.6286 | 3784.9457 | 3541.101 | 7326.0467 | -839.6057 | -1307.5819 | -19.17% | -15.15% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
444 | Expense | Electric Distribution | BA | E Dist Operate System | BAH | FLISR Maintenance | Wildfire | WLDFR-M020: Enhanced Powerline Safety Settings | Ex 4, Ch 4.6 Ex 4, Ch 7 | Yes | N/A | N/A | 489.6046 | 499.019 | 988.6236 | 348.0288 | 323.5671 | 671.5959 | -175.4519 | -317.0277 | -35.16% | -32.07% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
445 | Expense | Electric Distribution | BA | E Dist Operate System | BAH | FLISR Maintenance | SRM (NON-RAMP) | SRM (NON-RAMP) | Ex 4, Ch 4.6 Ex 4, Ch 7 | Yes | N/A | N/A | 3763.3173 | 3881.6877 | 7645.005 | 3436.9169 | 3217.5339 | 6654.4507 | -664.1538 | -990.5543 | -17.11% | -12.96% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
446 | Expense | Electric Distribution | BA | E Dist Operate System | BA# | Not assigned | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 4.6 Ex 4, Ch 7 | No | On-going | Annual | 0 | 0 | 0 | 2450.2555 | 3524.7446 | 5975.0001 | 3524.7446 | 5975.0001 | 100% | 100% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | Over | Proceeding as Planned | N/A
447 | Expense | Electric Distribution | BF | E T&D Patrol/Insp | BF1 | Dist. Aerial Inspections | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 10 | No | On-going | Annual | 0 | 0 | 0 | 7431.7981 | 24648.0359 | 32079.834 | 24648.0359 | 32079.834 | 100% | 100% | YES | YES | # of Equipment Inspections | N/A | N/A | N/A | 64000 | 216926 | 280926 | 216926 | 280926 | 100% | 100% | YES | Program expenses exceeded imputed regulatory values due to this program not being forecasted in the 2023 GRC. PG&E incurred costs in 2024 to conduct aerial inspections in HFTDs, which allows us to detect conditions that are challenging to detect from ground inspections. The addition of aerial inspections to PG&E's distribution inspection portfolio enabled PG&E to address an "Area for Continuous Improvement" from the WMP proceeding, and brings PG&E into consistency with SDG&E and SCE, who also conduct risk-based aerial inspections in HFTD. | Actual units were higher than imputed units because PG&E transitioned to aerial inspections in HFTD instead of ground inspections beginning in 2024. | Over | On-Target | Over | Proceeding as Planned | This program was piloted in 2023 and fully implemented in 2024. This work is ongoing and will continue through PG&E’s 2023 GRC period where it was not forecasted. The purpose of this program is a continuing effort to identify abnormal conditions on PG&E assets through aerial inspection.
448 | Expense | Electric Distribution | BF | E T&D Patrol/Insp | BF3 | UG BART Cable Test/Insp | SRM Total | SRM Total | Ex 4, Ch 10 | No | On-going | Annual | 58.9724 | 59.0572 | 118.0296 | 0 | 39.58 | 39.58 | -19.4772 | -78.4496 | -32.98% | -66.47% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
449 | Expense | Electric Distribution | BF | E T&D Patrol/Insp | BF3 | UG BART Cable Test/Insp | Underground | DUNGD-C001: Patrols | Ex 4, Ch 10 | Yes | N/A | N/A | 58.9724 | 59.0572 | 118.0296 | 32.5747 | 39.58 | 72.1547 | -19.4772 | -45.8749 | -32.98% | -38.87% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
450 | Expense | Electric Distribution | BF | E T&D Patrol/Insp | BF4 | UG Auto Xfer Swch Test/Insp | SRM Total | SRM Total | Ex 4, Ch 10 | No | On-going | Annual | 145.2468 | 145.4557 | 290.7025 | 68.9669 | 134.042 | 203.0089 | -11.4136 | -87.6936 | -7.847% | -30.17% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
451 | Expense | Electric Distribution | BF | E T&D Patrol/Insp | BF4 | UG Auto Xfer Swch Test/Insp | Underground | DUNGD-C001: Patrols | Ex 4, Ch 10 | Yes | N/A | N/A | 145.2468 | 145.4557 | 290.7025 | 68.9669 | 134.042 | 203.0089 | -11.4136 | -87.6936 | -7.847% | -30.17% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
452 | Expense | Electric Distribution | BF | E T&D Patrol/Insp | BFA | OH Patrol | SRM Total | SRM Total | Ex 4, Ch 10 | No | On-going | Annual | 5056.3369 | 5063.6072 | 10119.9441 | 7613.2939 | 10773.5725 | 18386.8664 | 5709.9653 | 8266.9223 | 112.8% | 81.69% | NO | YES | # of Equipment Inspections | 1366233.24 | 1366233.2433 | 2732466.4833 | 1344289 | 1934507 | 3278796 | 568273.7567 | 546329.5167 | 41.59% | 19.99% | YES | Program expenses exceeded imputed regulatory values because more units were patrolled than originally forecasted. Every pole that doesn't get a detailed inspection received a patrol, including non-HFTD rural maps that are being patrolled annually which exceeds the GO165 requirements | Actual units were higher than imputed units because more units were patrolled than originally forecasted. Every pole that doesn't get a detailed inspection received a patrol, including non-HFTD rural maps that are being patrolled annually which exceeds the GO165 requirements and was not forecast in the 2023 GRC. | Over | On-Target | Over | Proceeding as Planned | This program’s work is ongoing and will continue through PG&E’s 2023 GRC period. The purpose of this program is a continuing effort to identify abnormal conditions on PG&E assets through patrols
453 | Expense | Electric Distribution | BF | E T&D Patrol/Insp | BFA | OH Patrol | Distribution Overhead | DOVHD-C013: Patrols - Distribution Overhead | Ex 4, Ch 10 | Yes | N/A | N/A | 5056.3369 | 5063.6072 | 10119.9441 | 7613.2939 | 10773.5725 | 18386.8664 | 5709.9653 | 8266.9223 | 112.8% | 81.69% | N/A | N/A | # poles patrolled | 1366233.24 | 1366233.2433 | 2732466.4833 | 1344289 | 1934507 | 3278796 | 568273.7567 | 546329.5167 | 41.59% | 19.99% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
454 | Expense | Electric Distribution | BF | E T&D Patrol/Insp | BFA | OH Patrol | Wildfire | WLDFR-C001: Patrols - Distribution Overhead | Ex 4, Ch 10 | Yes | N/A | N/A | 5056.3369 | 5063.6072 | 10119.9441 | 7613.2939 | 10773.5725 | 18386.8664 | 5709.9653 | 8266.9223 | 112.8% | 81.69% | N/A | N/A | # poles patrolled | 1366233.24 | 1366233.2433 | 2732466.4833 | 1344289 | 1934507 | 3278796 | 568273.7567 | 546329.5167 | 41.59% | 19.99% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
455 | Expense | Electric Distribution | BF | E T&D Patrol/Insp | BFB | OH Insp | SRM Total | SRM Total | Ex 4, Ch 10 | No | On-going | Annual | 53673.6169 | 53750.7918 | 107424.4087 | 65428.3223 | 26451.5516 | 91879.8739 | -27299.2402 | -15544.5348 | -50.79% | -14.47% | YES | YES | # of Poles Inspected | 508807.48 | 508806.59 | 1017614.07 | 550762 | 331105 | 881867 | -177701.59 | -135747.07 | -34.93% | -13.34% | YES | Program expenses were below imputed regulatory values because PG&E completed less units than originally planned as PG&E transitioned to conduct aerial inspections in HFTDs instead of ground inspections. | Actual units were lower than imputed units because PG&E transitioned to aerial inspections in HFTD instead of ground inspections. | Under | On-Target | Under | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The purpose of this program is to identify abnormal conditions on PG&E assets through detailed inspections.
456 | Expense | Electric Distribution | BF | E T&D Patrol/Insp | BFB | OH Insp | Distribution Overhead | DOVHD-C005: Inspections - Distribution Overhead | Ex 4, Ch 10 | Yes | N/A | N/A | 53673.6169 | 53750.7918 | 107424.4087 | 65428.3223 | 26451.5516 | 91879.8739 | -27299.2402 | -15544.5348 | -50.79% | -14.47% | N/A | N/A | # poles inspected | 508807.48 | 508806.59 | 1017614.07 | 550762 | 331105 | 881867 | -177701.59 | -135747.07 | -34.93% | -13.34% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
457 | Expense | Electric Distribution | BF | E T&D Patrol/Insp | BFB | OH Insp | Wildfire | WLDFR-C01A: Inspections - Distribution Overhead | Ex 4, Ch 10 | Yes | N/A | N/A | 53673.6169 | 53750.7918 | 107424.4087 | 65428.3223 | 26451.5516 | 91879.8739 | -27299.2402 | -15544.5348 | -50.79% | -14.47% | N/A | N/A | # poles inspected | 508807.48 | 508806.59 | 1017614.07 | 550762 | 331105 | 881867 | -177701.59 | -135747.07 | -34.93% | -13.34% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
458 | Expense | Electric Distribution | BF | E T&D Patrol/Insp | BFC | OH Insp Infrared | SRM Total | SRM Total | Ex 4, Ch 10 | No | On-going | Annual | 2833.9513 | 2838.0261 | 5671.9773 | 20.9235 | 1500.9111 | 1521.8347 | -1337.1149 | -4150.1427 | -47.11% | -73.17% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
459 | Expense | Electric Distribution | BF | E T&D Patrol/Insp | BFC | OH Insp Infrared | Distribution Overhead | DOVHD-C006: Infrared Inspections -Distribution Overhead | Ex 4, Ch 10 | Yes | N/A | N/A | 2833.9513 | 2838.0261 | 5671.9773 | 20.9235 | 1500.9111 | 1521.8347 | -1337.1149 | -4150.1427 | -47.11% | -73.17% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
460 | Expense | Electric Distribution | BF | E T&D Patrol/Insp | BFC | OH Insp Infrared | Wildfire | WLDFR-C01B: Infrared Inspections - Distribution Overhead | Ex 4, Ch 10 | Yes | N/A | N/A | 2833.9513 | 2838.0261 | 5671.9773 | 20.9235 | 1500.9111 | 1521.8347 | -1337.1149 | -4150.1427 | -47.11% | -73.17% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
461 | Expense | Electric Distribution | BF | E T&D Patrol/Insp | BFD | UG Patrol | SRM Total | SRM Total | Ex 4, Ch 10 | No | On-going | Annual | 2681.0599 | 2684.9148 | 5365.9747 | 3142.43 | 2974.7458 | 6117.1758 | 289.831 | 751.2011 | 10.79% | 14% | NO | NO | # of Enclosures Patrolled | 270158 | 270158.0008 | 540316.0008 | 268305 | 279676 | 547981 | 9517.9992 | 7664.9992 | 3.523% | 1.419% | NO | Below variance threshold. | Below variance threshold. | On-Target | On-Target | On-Target | Proceeding as Planned | This program has no end date and will continue through the remainder of the 2023 GRC period. The purpose of this program is a continuing effort to identify abnormal conditions on PG&E assets.
462 | Expense | Electric Distribution | BF | E T&D Patrol/Insp | BFD | UG Patrol | Underground | DUNGD-C001: Patrols | Ex 4, Ch 10 | Yes | N/A | N/A | 2681.0599 | 2684.9148 | 5365.9747 | 3142.43 | 2974.7458 | 6117.1758 | 289.831 | 751.2011 | 10.79% | 14% | N/A | N/A | # enclosures patrolled | 270158 | 270158.0008 | 540316.0008 | 268305 | 279676 | 547981 | 9517.9992 | 7664.9992 | 3.523% | 1.419% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
463 | Expense | Electric Distribution | BF | E T&D Patrol/Insp | BFE | UG Insp Infrared | SRM Total | SRM Total | Ex 4, Ch 10 | No | On-going | Annual | 14545.4322 | 14566.3465 | 29111.7787 | 16029.1789 | 14941.0189 | 30970.1978 | 374.6724 | 1858.4191 | 2.572% | 6.384% | NO | NO | # of Enclosures Inspected | 134979 | 134978.9999 | 269957.9999 | 148998 | 155381 | 304379 | 20402.0001 | 34421.0001 | 15.11% | 12.75% | NO | Below variance threshold. | Below variance threshold. | On-Target | On-Target | On-Target | Proceeding as Planned | This program has no end date and will continue through the remainder of the 2023 GRC period. The purpose of this program is a continuing effort to identify abnormal conditions on PG&E assets.
464 | Expense | Electric Distribution | BF | E T&D Patrol/Insp | BFE | UG Insp Infrared | Underground | DUNGD-C001: Patrols | Ex 4, Ch 10 | Yes | N/A | N/A | 14545.4322 | 14566.3465 | 29111.7787 | 16029.1789 | 14941.0189 | 30970.1978 | 374.6724 | 1858.4191 | 2.572% | 6.384% | N/A | N/A | # enclosures inspected | 134979 | 134978.9999 | 269957.9999 | 148998 | 155381 | 304379 | 20402.0001 | 34421.0001 | 15.11% | 12.75% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
465 | Expense | Electric Distribution | BF | E T&D Patrol/Insp | BFF | UG Manhole Insp Annual | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 10 | No | On-going | Annual | 506.7258 | 507.4544 | 1014.1801 | 0 | 160.2093 | 160.2093 | -347.2451 | -853.9708 | -68.43% | -84.2% | NO | NO | # of Manholes/Vaults Inspected | 1546 | 1546 | 3092 | 0 | 474 | 474 | -1072 | -2618 | -69.34% | -84.67% | YES | Below variance threshold. | Actual units were lower than imputed units due to funding for annual manhole inspections being re-prioritized to other high priority work in MWC BF, including aerial inspections in MAT BF1. A limited number of manhole inspections were completed in 2024 based on locations of high public safety consequence, typically located in densely populated areas. | Under | On-Target | Under | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The purpose of this program is to inspect manholes. Note that manholes are also inspected as part of GO 165 underground inspections program.
466 | Expense | Electric Distribution | BF | E T&D Patrol/Insp | BFG | OH Equip Test | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 10 | No | On-going | Annual | 2653.7578 | 2657.5735 | 5311.3313 | 3717.2796 | 3553.9803 | 7271.2599 | 896.4067 | 1959.9286 | 33.73% | 36.9% | NO | NO | # of Equip Inspections | 25576.24 | 25576.24 | 51152.48 | 24130 | 21099 | 45229 | -4477.24 | -5923.48 | -17.51% | -11.58% | NO | Below variance threshold. | Below variance threshold. | On-Target | On-Target | On-Target | Proceeding as Planned | This program has no end date and will continue through the remainder of the 2023 GRC period. The purpose of this program is a continuing effort to identify abnormal conditions on PG&E assets.
467 | Expense | Electric Distribution | BF | E T&D Patrol/Insp | BFH | Inspection Projects | SRM Total | SRM Total | Ex 4, Ch 10 | No | On-going | Annual | 4832.4602 | 4839.4086 | 9671.8688 | 6469.977 | 2699.2956 | 9169.2726 | -2140.113 | -502.5962 | -44.22% | -5.196% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
468 | Expense | Electric Distribution | BF | E T&D Patrol/Insp | BFH | Inspection Projects | Wildfire | WLDFR-C01E: Inspections | Ex 4, Ch 10 | Yes | N/A | N/A | 4832.4602 | 4839.4086 | 9671.8688 | 6469.977 | 2699.3 | 9169.2771 | -2140.1086 | -502.5918 | -44.22% | -5.196% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
469 | Expense | Electric Distribution | BF | E T&D Patrol/Insp | BFJ | OH Patrol ORT Post Outage | SRM Total | SRM Total | Ex 4, Ch 10 | No | On-going | Annual | 165.9964 | 166.2351 | 332.2314 | 146.3 | 127.5662 | 273.8662 | -38.6688 | -58.3652 | -23.26% | -17.57% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
470 | Expense | Electric Distribution | BF | E T&D Patrol/Insp | BFJ | OH Patrol ORT Post Outage | Distribution Overhead | DOVHD-M020: Enhanced Powerline Safety Settings | Ex 4, Ch 10 | Yes | N/A | N/A | 0 | 0 | 0 | 0 | 47.9 | 47.9 | 47.9 | 47.9 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
471 | Expense | Electric Distribution | BF | E T&D Patrol/Insp | BFJ | OH Patrol ORT Post Outage | Wildfire | WLDFR-M020: Enhanced Powerline Safety Settings | Ex 4, Ch 10 | Yes | N/A | N/A | 0 | 0 | 0 | 51.4 | 47.9 | 99.3 | 47.9 | 99.3 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
472 | Expense | Electric Distribution | BF | E T&D Patrol/Insp | BFJ | OH Patrol ORT Post Outage | SRM (NON-RAMP) | SRM (NON-RAMP) | Ex 4, Ch 10 | Yes | N/A | N/A | 165.9964 | 166.2351 | 332.2314 | 94.8353 | 79.6022 | 174.4375 | -86.6328 | -157.7939 | -52.11% | -47.5% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
473 | Expense | Electric Distribution | BF | E T&D Patrol/Insp | BF# | Not assigned | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 10 | No | On-going | Annual | 0 | 0 | 0 | 39972.1868 | 41526.8863 | 81499.0731 | 41526.8863 | 81499.0731 | 100% | 100% | YES | YES | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Program expenses exceeded imputed regulatory values due to the program not being forecasted in the 2023 GRC. These increased expenses are associated with headcount for the System Inspections Quality Control (QC) team, formed to perform system inspection QC audits and achieve the associated quality pass rate for HFTD areas. | N/A | Over | Over | Over | Emergent | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The purpose of this program is System Inspection QC, which was not forecasted in the 2023 GRC. PG&E anticipates that System Inspection QC costs will continue to be incurred in this MAT for the remainder of the GRC cycle.
474 | Expense | Electric Distribution | BH | E Dist Routine Emergency | N/A | Not assigned | SRM Total | SRM Total | Ex 4, Ch 4.6 Ex 4, Ch 6 | No | On-going | Annual | 193157.4894 | 197204.9399 | 390362.4293 | 119478.7682 | 137877.1335 | 257355.9017 | -59327.8064 | -133006.5275 | -30.08% | -34.07% | YES | YES | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Program expenses were below imputed regulatory values due to favorable weather conditions in 2024. Costs for EPSS have variability according to the weather; certain costs like Patrols and Post-Patrol investigation (includes helicopter) will increase or decrease related to weather events that require EPSS mitigation. In addition, when this program was forecasted in the 2023 GRC it was a new program and outages were expected to increase with the full implementation of EPSS. The level of outages, and therefore associated patrols was not realized as forecasted. | N/A | On-Target | On-Target | Under | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The purpose of this program is a continuing effort to patrol, including the use of helicopters, following an outage event and to restore customers to service as soon as possible. Program spend over the course of the remainder of the GRC cycle is expected to be under what was forecasted for EPSS. The routine emergency portion of this work is emergent depending on weather and the number of events. Overall the EPSS and routine emergency programs are proceeding as planned though the spend is likely to be under for the GRC cycle as explained in the cost variance explanation.
475 | Expense | Electric Distribution | BH | E Dist Routine Emergency | N/A | Not assigned | Wildfire | WLDFR-M020: Enhanced Powerline Safety Settings | Ex 4, Ch 4.6 Ex 4, Ch 6 | Yes | N/A | N/A | 117183.7596 | 119437.0415 | 236620.8011 | 10276.8746 | 10771.359 | 21048.2336 | -108665.6825 | -215572.5675 | -90.98% | -91.1% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
476 | Expense | Electric Distribution | BH | E Dist Routine Emergency | N/A | Not assigned | SRM (NON-RAMP) | SRM (NON-RAMP) | Ex 4, Ch 4.6 Ex 4, Ch 6 | Yes | N/A | N/A | 75973.7298 | 77767.8984 | 153741.6282 | 109201.8936 | 127105.7746 | 236307.6681 | 49337.8762 | 82566.04 | 63.44% | 53.7% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
477 | Expense | Electric Distribution | BK | Maint Other Equip | BKA | Transformer Repr Emeryville | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 11 | No | On-going | Annual | 1975.33 | 2019.5532 | 3994.8832 | 1597.5867 | 1633.4152 | 3231.0019 | -386.1381 | -763.8813 | -19.12% | -19.12% | NO | NO | Equipment overhauls | 1023 | 1023 | 2046 | 1603 | 1506 | 3109 | 483 | 1063 | 47.21% | 51.96% | YES | Below variance threshold. | Actual units were higher than imputed units due to operational need. This is a demand-driven program for transformer repair/refurbishment supporting maintenance, new construction, emergency response, and other programs. Demand for this program is determined by logistical planners, but is dependent on the availability of transformers from the manufacturer or refurbished/repaired transformer inventory. If transformer supplies are unavailable from the manufacturer, PG&E considers repairing/refurbishing to meet the demand. In 2024 the need for transformer repair/refurbishment was higher than forecast in the 2023 GRC. | Over | On-Target | On-Target | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The purpose of this program is to repair and refurbish transformers to meet demand.
478 | Expense | Electric Distribution | BK | Maint Other Equip | BKJ | Equip Overhaul Emeryville | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 11 | No | On-going | Annual | 0 | 0 | 0 | 104.1453 | 234.3877 | 338.533 | 234.3877 | 338.533 | 100% | 100% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | Over | Proceeding as Planned | N/A
479 | Expense | Electric Distribution | BK | Maint Other Equip | BKK | Equip Warranty Repr Emeryville | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 11 | No | On-going | Annual | 0 | 0 | 0 | 299.56 | 237.3134 | 536.8733 | 237.3134 | 536.8733 | 100% | 100% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | Over | Proceeding as Planned | N/A
480 | Expense | Electric Distribution | DD | Provide Field Service | DDC | Electric Start/Stop | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 8 | No | On-going | Annual | 482.2666 | 498.3348 | 980.6014 | 245.6925 | 279.178 | 524.8704 | -219.1568 | -455.731 | -43.98% | -46.47% | NO | NO | Field orders | 3603.81 | 3603.8094 | 7207.6194 | 1710 | 1731 | 3441 | -1872.8094 | -3766.6194 | -51.97% | -52.26% | YES | Below variance threshold. | Actual units were lower than imputed units due to fewer customer-generated start/stop requests than forecast. | Under | On-Target | On-Target | Proceeding as Planned | This program is on-going work and will continue in PG&E's 2023 GRC Period. The work supports customer-generated start/stop requests while ensuring safe delivery of electric service.
481 | Expense | Electric Distribution | DD | Provide Field Service | DDH | Electric Trouble Cust Equipt | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 7 | No | On-going | Annual | 6092.1497 | 6300.8473 | 12392.997 | 7159.0458 | 7444.1703 | 14603.2161 | 1143.323 | 2210.2191 | 18.15% | 17.83% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | This program is on-going work and will continue in PG&E's 2023 GRC Period. The work supports timely response to trouble on customer-owned equipment and maintains safety and reliability of the electric grid. PG&E changed from unitized to non-unitized in the 2023 GRC due to inconsistency in the unit cost per outage event.
482 | Expense | Electric Distribution | DD | Provide Field Service | DDJ | Electric - Other | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 7 | No | On-going | Annual | 11131.8549 | 11513.1968 | 22645.0517 | 17159.1279 | 13491.2097 | 30650.3376 | 1978.0129 | 8005.286 | 17.18% | 35.35% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | This program is on-going and will continue in PG&E's 2023 GRC Period. The work is driven by customer-initiated electrical service connections, particularly connects/reconnects like solar PV installations, Electric Main Panel Upgrades, and electric vehicle connections. PG&E changed from unitized to non-unitized in the 2023 GRC due to inconsistency in the unit cost per outage event.
483 | Expense | Electric Distribution | DD | Provide Field Service | DD# | Not assigned | SRM Total | SRM Total | Ex 4, Ch 7 | No | On-going | Annual | 6608.3486 | 6834.7296 | 13443.0781 | 7217.0524 | 8813.3711 | 16030.4235 | 1978.6416 | 2587.3454 | 28.95% | 19.25% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
484 | Expense | Electric Distribution | DD | Provide Field Service | DD# | Not assigned | Distribution Overhead | DOVHD-M020: Enhanced Powerline Safety Settings | Ex 4, Ch 7 | Yes | N/A | N/A | 0 | 0 | 0 | 0 | 148.3995 | 148.3995 | 148.3995 | 148.3995 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
485 | Expense | Electric Distribution | DD | Provide Field Service | DD# | Not assigned | Wildfire | WLDFR-M020: Enhanced Powerline Safety Settings | Ex 4, Ch 7 | Yes | N/A | N/A | 0 | 0 | 0 | 258.3307 | 148.3995 | 406.7302 | 148.3995 | 406.7302 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
486 | Expense | Electric Distribution | DD | Provide Field Service | DD# | Not assigned | SRM (NON-RAMP) | SRM (NON-RAMP) | Ex 4, Ch 7 | Yes | N/A | N/A | 6608.3486 | 6834.7296 | 13443.0781 | 6958.7217 | 8664.9716 | 15623.6933 | 1830.242 | 2180.6152 | 26.78% | 16.22% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
487 | Expense | Electric Distribution | EY | Change/Maint Used Elec Meter | N/A | Not assigned | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 8 | No | On-going | Annual | 8478.8029 | 8499.0083 | 16977.8113 | 9001.3117 | 9684.3638 | 18685.6756 | 1185.3555 | 1707.8643 | 13.95% | 10.06% | NO | NO | Field orders | 36757.8 | 36757.8009 | 73515.6009 | 35924 | 38531 | 74455 | 1773.1991 | 939.3991 | 4.824% | 1.278% | NO | Below variance threshold. | Below variance threshold. | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
488 | Expense | Electric Distribution | FZ | E Dist Planning & Ops Engineer | FZA | Genl Engineer | SRM Total | SRM Total | Ex 4, Ch 17 | No | On-going | Annual | 22543.5406 | 23198.0713 | 45741.6119 | 17070.6936 | 18939.0259 | 36009.7195 | -4259.0454 | -9731.8924 | -18.36% | -21.28% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
489 | Expense | Electric Distribution | FZ | E Dist Planning & Ops Engineer | FZA | Genl Engineer | Distribution Overhead | DOVHD-C008: Annual Protection Reviews | Ex 4, Ch 17 | Yes | N/A | N/A | 16913.6291 | 17422.1695 | 34335.7985 | 12145.3497 | 13551.7821 | 25697.1318 | -3870.3874 | -8638.6668 | -22.22% | -25.16% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
490 | Expense | Electric Distribution | FZ | E Dist Planning & Ops Engineer | FZA | Genl Engineer | Wildfire | WLDFR-M020: Enhanced Powerline Safety Settings | Ex 4, Ch 4.6 | Yes | N/A | N/A | 2111.442 | 2166.1942 | 4277.6362 | 2226.5793 | 2846.6561 | 5073.2354 | 680.4619 | 795.5991 | 31.41% | 18.6% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
491 | Expense | Electric Distribution | FZ | E Dist Planning & Ops Engineer | FZA | Genl Engineer | Wildfire | WLDFR-M07A: Situational Awareness and Forecasting Initiatives - Line Sensors | Ex 4, Ch 4.3 | Yes | N/A | N/A | 3518.4132 | 3609.6498 | 7128.063 | 2698.7647 | 2540.5877 | 5239.3524 | -1069.0621 | -1888.7107 | -29.62% | -26.5% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
492 | Expense | Electric Distribution | FZ | E Dist Planning & Ops Engineer | FZB | Voltage Complaints Invest | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 17 | No | On-going | Annual | 653.4074 | 673.0534 | 1326.4608 | 1761.7722 | 1652.2503 | 3414.0224 | 979.1969 | 2087.5616 | 145.5% | 157.4% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
493 | Expense | Electric Distribution | FZ | E Dist Planning & Ops Engineer | FZC | Transformer Reports Manage | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 17 | No | On-going | Annual | 237.0501 | 244.1775 | 481.2277 | 0 | 0 | 0 | -244.1775 | -481.2277 | -100% | -100% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
494 | Expense | Electric Distribution | FZ | E Dist Planning & Ops Engineer | FZD | Field Work Plan | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 17 | No | On-going | Annual | 859.0535 | 884.8826 | 1743.9361 | 283.2546 | 573.4817 | 856.7363 | -311.4009 | -887.1998 | -35.19% | -50.87% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
495 | Expense | Electric Distribution | FZ | E Dist Planning & Ops Engineer | FZE | Troublemen Field Work | SRM Total | SRM Total | Ex 4, Ch 17 | No | On-going | Annual | 1538.7999 | 1585.0668 | 3123.8667 | 5160.3261 | 4619.1347 | 9779.4609 | 3034.0679 | 6655.5942 | 191.4% | 213.1% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
496 | Expense | Electric Distribution | FZ | E Dist Planning & Ops Engineer | FZE | Troublemen Field Work | Wildfire | WLDFR-M020: Enhanced Powerline Safety Settings | Ex 4, Ch 4.6 | Yes | N/A | N/A | 0 | 0 | 0 | 2617.5919 | 2291.5817 | 4909.1736 | 2291.5817 | 4909.1736 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
497 | Expense | Electric Distribution | FZ | E Dist Planning & Ops Engineer | FZE | Troublemen Field Work | SRM (NON-RAMP) | SRM (NON-RAMP) | Ex 4, Ch 17 | Yes | N/A | N/A | 1538.7999 | 1585.0668 | 3123.8667 | 2542.7342 | 2327.553 | 4870.2872 | 742.4862 | 1746.4206 | 46.84% | 55.91% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
498 | Expense | Electric Distribution | GA | E T&D Maint OH Poles | GAA | Pole Test & Treat | SRM Total | SRM Total | Ex 4, Ch 12 | No | On-going | Annual | 21669.7722 | 21556.4696 | 43226.2418 | 34048.7679 | 13491.0593 | 47539.8271 | -8065.4103 | 4313.5853 | -37.42% | 9.979% | NO | YES | # Poles Tested & Treated | 259832.68 | 259832.6754 | 519665.3554 | 117091 | 62845 | 179936 | -196987.6754 | -339729.3554 | -75.81% | -65.37% | YES | Program expenses were below imputed regulatory values due to fewer units being completed. | Actual units were lower than imputed units due to PG&E temporarily shifting to a 20-year inspection cycle from a 10-year inspection cycle. | Under | Under | Over | Rescheduled | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The purpose of this program is a continuing effort to inspect and treat wood poles intrusively, to ensure the poles are in good condition and prevent premature failure in accordance with GO165. During the 2023 GRC cycle PG&E expects to continue to perform units to meet 20-year inspection cycle.
499 | Expense | Electric Distribution | GA | E T&D Maint OH Poles | GAA | Pole Test & Treat | Distribution Overhead | DOVHD-C011: Pole Programs | Ex 4, Ch 12 | Yes | N/A | N/A | 21669.7722 | 21556.4696 | 43226.2418 | 34048.7679 | 13491.0593 | 47539.8271 | -8065.4103 | 4313.5853 | -37.42% | 9.979% | N/A | N/A | # inspections | 259832.68 | 259832.6754 | 519665.3554 | 117091 | 62845 | 179936 | -196987.6754 | -339729.3554 | -75.81% | -65.37% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
500 | Expense | Electric Distribution | GA | E T&D Maint OH Poles | GAA | Pole Test & Treat | Wildfire | WLDFR-C12A: Wood Pole Inspection Program | Ex 4, Ch 12 | Yes | N/A | N/A | 21669.7722 | 21556.4696 | 43226.2418 | 34048.7679 | 13491.0593 | 47539.8271 | -8065.4103 | 4313.5853 | -37.42% | 9.979% | N/A | N/A | # inspections | 259832.68 | 259832.6754 | 519665.3554 | 117091 | 62845 | 179936 | -196987.6754 | -339729.3554 | -75.81% | -65.37% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
501 | Expense | Electric Distribution | GA | E T&D Maint OH Poles | GAB | Pole Joint Util Maint Reimb | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 12 | No | On-going | Annual | 0 | 0 | 0 | 177.4772 | 551.1657 | 728.6429 | 551.1657 | 728.6429 | 100% | 100% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | Over | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. Joint Utilities Maintenance Reimbursements are not forecast in the GRC and therefore will continue to appear over budget.
502 | Expense | Electric Distribution | GA | E T&D Maint OH Poles | GAC | Pole Analyze Loading | SRM Total | SRM Total | Ex 4, Ch 12 | No | On-going | Annual | 22710.056 | 22591.3141 | 45301.37 | 13502.0972 | 12431.0901 | 25933.1873 | -10160.224 | -19368.1827 | -44.97% | -42.75% | YES | YES | Poles Analyzed | 200000 | 200000 | 400000 | 162050 | 32008 | 194058 | -167992 | -205942 | -84% | -51.49% | YES | Program expenses were below imputed values due to the completion of a lower unit volume than forecasted at a higher unit cost. In 2024, the work focused on completing units in HFTD, which required more detailed engineering calculations for which desktop review was indeterminate. PG&E delayed transition of desktop reviews to non-HFTD poles in efforts to complete the outstanding HFTD poles. | Actual units were lower than imputed units due to work focused on completing units in HFTD, which required more detailed engineering calculations for which desktop review was indeterminate. PG&E delayed transition of desktop reviews to non-HFTD poles in efforts to complete the outstanding HFTD poles. | Under | On-Target | Under | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The purpose of this program is to review and analyze pole loading in order to prevent overloaded poles and premature pole failure. This program has concentrated on poles in Tier 2 and 3 HFTDs, through the performance of a desktop pole review calculation. PG&E has completed the desktop review pole loading analysis for all poles in the Tier 2 and 3 HFTDs. However, PG&E is now performing more detailed engineering calculations for all poles in the Tier 2 and 3 HFTDs for which the desktop review indicated a data anomaly (e.g., change of conductor type) or that could not be sufficiently analyzed because of obstructions to LiDAR data capture (e.g., dense vegetation). PG&E will transition to analysis of non-HFTD poles after completion of the HFTD poles.
503 | Expense | Electric Distribution | GA | E T&D Maint OH Poles | GAC | Pole Analyze Loading | Wildfire | WLDFR-C12B: Pole Analyze Loading | Ex 4, Ch 12 | Yes | N/A | N/A | 22710.056 | 22591.3141 | 45301.37 | 13502.0972 | 12431.0901 | 25933.1873 | -10160.224 | -19368.1827 | -44.97% | -42.75% | N/A | N/A | # poles analyzed | 200000 | 200000 | 400000 | 162050 | 32008 | 194058 | -167992 | -205942 | -84% | -51.49% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
504 | Expense | Electric Distribution | GA | E T&D Maint OH Poles | GAD | Pole Reinforce | SRM Total | SRM Total | Ex 4, Ch 12 | No | On-going | Annual | 4403.5311 | 4380.5068 | 8784.0379 | 7609.0663 | -1777.6728 | 5831.3935 | -6158.1796 | -2952.6445 | -140.6% | -33.61% | NO | YES | Poles Reinforced | 4500 | 4500 | 9000 | 3982 | 0 | 3982 | -4500 | -5018 | -100% | -55.76% | YES | Program expenses were below imputed adopted values due to recorded costs being transferred from MAT Code GAD to MAT Code 07R. MAT code 07R was created after 2023 GRC filing when costs for pole reinforcements were capitalized, beginning in 2024. | Actual units were lower than imputed units because costs and units were recorded to MAT 07R. See costs variance explanation for this program. | Under | On-Target | Under | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period, but under MAT 07R. The purpose of this program is a continuing effort to make safe degraded poles that would otherwise require replacement.
505 | Expense | Electric Distribution | GA | E T&D Maint OH Poles | GAD | Pole Reinforce | Distribution Overhead | DOVHD-C011: Pole Programs | Ex 4, Ch 12 | Yes | N/A | N/A | 4403.5311 | 4380.5068 | 8784.0379 | 7609.0663 | -1777.6728 | 5831.3935 | -6158.1796 | -2952.6445 | -140.6% | -33.61% | N/A | N/A | # reinforcements | 4500 | 4500 | 9000 | 3982 | 0 | 3982 | -4500 | -5018 | -100% | -55.76% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
506 | Expense | Electric Distribution | GA | E T&D Maint OH Poles | GAD | Pole Reinforce | Wildfire | WLDFR-C12E: Pole Restoration Program | Ex 4, Ch 12 | Yes | N/A | N/A | 4403.5311 | 4380.5068 | 8784.0379 | 7609.0663 | -1777.6728 | 5831.3935 | -6158.1796 | -2952.6445 | -140.6% | -33.61% | N/A | N/A | # reinforcements | 4500 | 4500 | 9000 | 3982 | 0 | 3982 | -4500 | -5018 | -100% | -55.76% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
507 | Expense | Electric Distribution | GA | E T&D Maint OH Poles | GAF | Telco Engr Revw Non-Reimbursed | SRM Total | SRM Total | Ex 4, Ch 12 | No | On-going | Annual | 176.1861 | 175.2649 | 351.4511 | 0 | 0 | 0 | -175.2649 | -351.4511 | -100% | -100% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
508 | Expense | Electric Distribution | GA | E T&D Maint OH Poles | GAF | Telco Engr Revw Non-Reimbursed | Distribution Overhead | DOVHD-C011: Pole Programs | Ex 4, Ch 12 | Yes | N/A | N/A | 176.1861 | 175.2649 | 351.4511 | 0 | 0 | 0 | -175.2649 | -351.4511 | -100% | -100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
509 | Expense | Electric Distribution | GA | E T&D Maint OH Poles | GAH | Pole Joint Util Maint Non-Reim | SRM Total | SRM Total | Ex 4, Ch 12 | No | On-going | Annual | 475.8148 | 473.3269 | 949.1417 | 444.3824 | 706.2257 | 1150.6081 | 232.8987 | 201.4664 | 49.2% | 21.23% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
510 | Expense | Electric Distribution | GA | E T&D Maint OH Poles | GAH | Pole Joint Util Maint Non-Reim | Distribution Overhead | DOVHD-C011: Pole Programs | Ex 4, Ch 12 | Yes | N/A | N/A | 475.8148 | 473.3269 | 949.1417 | 444.3824 | 706.2257 | 1150.6081 | 232.8987 | 201.4664 | 49.2% | 21.23% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
511 | Expense | Electric Distribution | GA | E T&D Maint OH Poles | GA# | Not assigned | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 12 | No | On-going | Annual | -5287.8284 | -5260.1804 | -10548.0089 | -5807.0151 | 1869.4175 | -3937.5975 | 7129.598 | 6610.4113 | -135.5% | -62.67% | NO | YES | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | For the 2023 GRC forecast, MAT GA# was used to track joint pole credits and pole management personnel costs for the intrusive inspection and pole restoration programs and therefore the imputed amount is negative. In 2024, GA# was only used to track the costs associated with management of pole test and treat, pole reinforcement, and comprehensive inspection programs. | N/A | On-Target | On-Target | Over | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The revised purpose of this program is to track pole management personnel costs.
512 | Expense | Electric Distribution | GC | E Dist Subst O&M | GC1 | El DSub-Engrg_Maint Support | SRM Total | SRM Total | Ex 4, Ch 15 | No | On-going | Annual | 5700.5611 | 5776.4015 | 11476.9626 | 4630.9512 | 4148.5711 | 8779.5223 | -1627.8305 | -2697.4403 | -28.18% | -23.5% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
513 | Expense | Electric Distribution | GC | E Dist Subst O&M | GC1 | El DSub-Engrg_Maint Support | Substation | SBSTN-C008: Design Criteria | Ex 4, Ch 15 | Yes | N/A | N/A | 544.2725 | 551.5135 | 1095.786 | 2289.1948 | 2492.7396 | 4781.9344 | 1941.2261 | 3686.1485 | 352% | 336.4% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
514 | Expense | Electric Distribution | GC | E Dist Subst O&M | GC1 | El DSub-Engrg_Maint Support | Substation | SBSTN-C017: Proactive Maintenance | Ex 4, Ch 15 | Yes | N/A | N/A | 4024.3681 | 4077.9084 | 8102.2765 | 2341.7564 | 1655.8315 | 3997.5878 | -2422.077 | -4104.6887 | -59.4% | -50.66% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
515 | Expense | Electric Distribution | GC | E Dist Subst O&M | GC1 | El DSub-Engrg_Maint Support | SRM (NON-RAMP) | SRM (NON-RAMP) | Ex 4, Ch 15 | Yes | N/A | N/A | 1131.9034 | 1146.9623 | 2278.8657 | 0 | 0 | 0 | -1146.9623 | -2278.8657 | -100% | -100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
516 | Expense | Electric Distribution | GC | E Dist Subst O&M | GC2 | El DSub-Major Emerg_Corr Maint | SRM Total | SRM Total | Ex 4, Ch 15 Ex 4, Ch 4.6 | No | On-going | Annual | 15750.297 | 15964.9815 | 31715.2784 | 4651.2106 | 5092.7712 | 9743.9818 | -10872.2103 | -21971.2966 | -68.1% | -69.28% | YES | YES | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Program expenses were below imputed regulatory values due to reprioritizing and funding overruns in our preventative substation programs. | N/A | Under | Under | Under | Rescheduled | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The purpose of this program is substation corrective work. PG&E anticipates completing this work as the need arises within the overall priority of the substation portfolio of work over the remainder of the course of the GRC cycle.
517 | Expense | Electric Distribution | GC | E Dist Subst O&M | GC2 | El DSub-Major Emerg_Corr Maint | Distribution Overhead | DOVHD-M020: Enhanced Powerline Safety Settings | Ex 4, Ch 15 Ex 4, Ch 4.6 | Yes | N/A | N/A | 0 | 0 | 0 | 0 | 54.6225 | 54.6225 | 54.6225 | 54.6225 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
518 | Expense | Electric Distribution | GC | E Dist Subst O&M | GC2 | El DSub-Major Emerg_Corr Maint | Wildfire | WLDFR-M020: Enhanced Powerline Safety Settings | Ex 4, Ch 15 Ex 4, Ch 4.6 | Yes | N/A | N/A | 867.9081 | 884.5968 | 1752.5048 | 210.8075 | 54.6225 | 265.4299 | -829.9743 | -1487.0749 | -93.83% | -84.85% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
519 | Expense | Electric Distribution | GC | E Dist Subst O&M | GC2 | El DSub-Major Emerg_Corr Maint | SRM (NON-RAMP) | SRM (NON-RAMP) | Ex 4, Ch 15 Ex 4, Ch 4.6 | Yes | N/A | N/A | 14882.3889 | 15080.3847 | 29962.7736 | 4440.4032 | 5038.1487 | 9478.5519 | -10042.236 | -20484.2217 | -66.59% | -68.37% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
520 | Expense | Electric Distribution | GC | E Dist Subst O&M | GC5 | Dist Sub enhanced inspections | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 15 | No | On-going | Annual | 0 | 0 | 0 | 1083.5342 | 1000.4815 | 2084.0157 | 1000.4815 | 2084.0157 | 100% | 100% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | Over | Proceeding as Planned | N/A
521 | Expense | Electric Distribution | GC | E Dist Subst O&M | GCA | Dsbn: TXfmr - prev maint. | SRM Total | SRM Total | Ex 4, Ch 15 | No | On-going | Annual | 1146.6707 | 1161.926 | 2308.5967 | 1519.1547 | 1485.4577 | 3004.6124 | 323.5316 | 696.0157 | 27.84% | 30.15% | NO | NO | Transformers Maintained | 4574.24 | 4574.2385 | 9148.4785 | 5373 | 4940 | 10313 | 365.7615 | 1164.5215 | 7.996% | 12.73% | NO | Below variance threshold. | Below variance threshold. | On-Target | On-Target | On-Target | Proceeding as Planned | This program has no end date and will continue through the remainder of the 2023 GRC period. The scope of this work is ongoing in accordance with General Order (GO) 174, which sets forth requirements for electric utility substations inspections and maintenance.
522 | Expense | Electric Distribution | GC | E Dist Subst O&M | GCA | Dsbn: TXfmr - prev maint. | Substation | SBSTN-C017: Proactive Maintenance | Ex 4, Ch 15 | Yes | N/A | N/A | 1146.6707 | 1161.926 | 2308.5967 | 1519.1547 | 1485.4577 | 3004.6124 | 323.5316 | 696.0157 | 27.84% | 30.15% | N/A | N/A | # of Transformers Maintained | 4574.24 | 4574.2385 | 9148.4785 | 5373 | 4940 | 10313 | 365.7615 | 1164.5215 | 7.996% | 12.73% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
523 | Expense | Electric Distribution | GC | E Dist Subst O&M | GCB | Dsbn: Breaker - prevent maint. | SRM Total | SRM Total | Ex 4, Ch 15 | No | On-going | Annual | 833.5576 | 844.6473 | 1678.205 | 962.1027 | 1050.2965 | 2012.3993 | 205.6492 | 334.1943 | 24.35% | 19.91% | NO | NO | Breakers Maintained | 1881.95 | 1881.9471 | 3763.8971 | 1167 | 1232 | 2399 | -649.9471 | -1364.8971 | -34.54% | -36.26% | YES | Below variance threshold. | Actual units were lower than imputed units due to higher actual unit costs than forecast. Higher unit costs are generally driven by labor, and resulted in fewer program units achieved. | Under | On-Target | On-Target | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The scope of work for this program is performed in accordance with GO174, which sets forth requirements for electric utility substation inspections and maintenance.
524 | Expense | Electric Distribution | GC | E Dist Subst O&M | GCB | Dsbn: Breaker - prevent maint. | Substation | SBSTN-C017: Proactive Maintenance | Ex 4, Ch 15 | Yes | N/A | N/A | 833.5576 | 844.6473 | 1678.205 | 962.1027 | 1050.2965 | 2012.3993 | 205.6492 | 334.1943 | 24.35% | 19.91% | N/A | N/A | # of Breakers Maintained | 1881.95 | 1881.9471 | 3763.8971 | 1167 | 1232 | 2399 | -649.9471 | -1364.8971 | -34.54% | -36.26% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
525 | Expense | Electric Distribution | GC | E Dist Subst O&M | GCC | Dist Sub: Substation Test Dpt | SRM Total | SRM Total | Ex 4, Ch 15 | No | On-going | Annual | 1599.4152 | 1620.6938 | 3220.109 | 3607.2022 | 3910.7222 | 7517.9243 | 2290.0283 | 4297.8153 | 141.3% | 133.5% | NO | NO | Relays Maintained | 1422.95 | 1422.9522 | 2845.9022 | 1364 | 1475 | 2839 | 52.0478 | -6.9022 | 3.658% | -0.2425% | NO | Below variance threshold. | Below variance threshold. | On-Target | On-Target | On-Target | Proceeding as Planned | This program has no end date and will continue through the remainder of the 2023 GRC period. The scope of this work is ongoing in accordance with GO174, which sets forth requirements for electric utility substations inspections and maintenance.
526 | Expense | Electric Distribution | GC | E Dist Subst O&M | GCC | Dist Sub: Substation Test Dpt | Substation | SBSTN-C017: Proactive Maintenance | Ex 4, Ch 15 | Yes | N/A | N/A | 1599.4152 | 1620.6938 | 3220.109 | 3607.2022 | 3910.7222 | 7517.9243 | 2290.0283 | 4297.8153 | 141.3% | 133.5% | N/A | N/A | # of Relays Maintained | 1422.95 | 1422.9522 | 2845.9022 | 1364 | 1475 | 2839 | 52.0478 | -6.9022 | 3.658% | -0.2425% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
527 | Expense | Electric Distribution | GC | E Dist Subst O&M | GCD | Dsbn: Station Read_prev maint. | SRM Total | SRM Total | Ex 4, Ch 15 | No | On-going | Annual | 3310.9587 | 3355.0078 | 6665.9664 | 3254.1144 | 3208.7438 | 6462.8581 | -146.264 | -203.1083 | -4.36% | -3.047% | NO | NO | Substation Inspections | 6849.81 | 6849.8134 | 13699.6234 | 6671 | 6319 | 12990 | -530.8134 | -709.6234 | -7.749% | -5.18% | NO | Below variance threshold. | Below variance threshold. | On-Target | On-Target | On-Target | Proceeding as Planned | This program has no end date and will continue through the remainder of the 2023 GRC period. The scope of this work is ongoing in accordance with GO174, which sets forth requirements for electric utility substations inspections and maintenance.
528 | Expense | Electric Distribution | GC | E Dist Subst O&M | GCD | Dsbn: Station Read_prev maint. | Substation | SBSTN-C017: Proactive Maintenance | Ex 4, Ch 15 | Yes | N/A | N/A | 3310.9587 | 3355.0078 | 6665.9664 | 3254.1144 | 3208.7438 | 6462.8581 | -146.264 | -203.1083 | -4.36% | -3.047% | N/A | N/A | # of Substation Inspections | 6849.81 | 6849.8134 | 13699.6234 | 6671 | 6319 | 12990 | -530.8134 | -709.6234 | -7.749% | -5.18% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
529 | Expense | Electric Distribution | GC | E Dist Subst O&M | GCD | Dsbn: Station Read_prev maint. | Wildfire | WLDFR-C003: Patrols and Inspections - Substation | Ex 4, Ch 15 | Yes | N/A | N/A | 3310.9587 | 3355.0078 | 6665.9664 | 3254.1144 | 3208.7438 | 6462.8581 | -146.264 | -203.1083 | -4.36% | -3.047% | N/A | N/A | # of Substation Inspections | 6849.81 | 6849.8134 | 13699.6234 | 6671 | 6319 | 12990 | -530.8134 | -709.6234 | -7.749% | -5.18% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
530 | Expense | Electric Distribution | GC | E Dist Subst O&M | GCE | Dsbn: Gnrl station_prev maint. | SRM Total | SRM Total | Ex 4, Ch 15 | No | On-going | Annual | 539.4853 | 546.6626 | 1086.1479 | 676.5371 | 546.3868 | 1222.9239 | -0.27579 | 136.776 | -0.05045% | 12.59% | NO | NO | Substation Preventative | 1176.97 | 1176.9733 | 2353.9433 | 1866 | 1487 | 3353 | 310.0267 | 999.0567 | 26.34% | 42.44% | YES | Below variance threshold. | Actual units were higher than imputed units due to the bundling of work for executional efficiencies, which resulted in additional program units being pulled into scope for a lower unit cost. | Over | On-Target | On-Target | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The scope of work for this program is performed in accordance with GO174, which sets forth requirements for electric utility substation inspections and maintenance.
531 | Expense | Electric Distribution | GC | E Dist Subst O&M | GCE | Dsbn: Gnrl station_prev maint. | Substation | SBSTN-C017: Proactive Maintenance | Ex 4, Ch 15 | Yes | N/A | N/A | 539.4853 | 546.6626 | 1086.1479 | 676.5371 | 546.3868 | 1222.9239 | -0.27579 | 136.776 | -0.05045% | 12.59% | N/A | N/A | # of Substation Preventative tasks | 1176.97 | 1176.9733 | 2353.9433 | 1866 | 1487 | 3353 | 310.0267 | 999.0567 | 26.34% | 42.44% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
532 | Expense | Electric Distribution | GC | E Dist Subst O&M | GCF | Dsbn: Batteries - prev maint. | SRM Total | SRM Total | Ex 4, Ch 15 | No | On-going | Annual | 528.9071 | 535.9437 | 1064.8509 | 456.1467 | 499.9527 | 956.0994 | -35.991 | -108.7514 | -6.715% | -10.21% | NO | NO | Batteries Maintained | 1238.98 | 1238.9791 | 2477.9591 | 1306 | 1200 | 2506 | -38.9791 | 28.0409 | -3.146% | 1.132% | NO | Below variance threshold. | Below variance threshold. | On-Target | On-Target | On-Target | Proceeding as Planned | This program has no end date and will continue through the remainder of the 2023 GRC period. The scope of this work is ongoing in accordance with GO174, which sets forth requirements for electric utility substations inspections and maintenance.
533 | Expense | Electric Distribution | GC | E Dist Subst O&M | GCF | Dsbn: Batteries - prev maint. | Substation | SBSTN-C017: Proactive Maintenance | Ex 4, Ch 15 | Yes | N/A | N/A | 528.9071 | 535.9437 | 1064.8509 | 456.1467 | 499.9527 | 956.0994 | -35.991 | -108.7514 | -6.715% | -10.21% | N/A | N/A | # of Batteries Maintained | 1238.98 | 1238.9791 | 2477.9591 | 1306 | 1200 | 2506 | -38.9791 | 28.0409 | -3.146% | 1.132% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
534 | Expense | Electric Distribution | GC | E Dist Subst O&M | GCG | Vegetation Management | SRM Total | SRM Total | Ex 4, Ch 15 | No | On-going | Annual | 10476.5925 | 10615.9734 | 21092.5659 | 8039.823 | 6484.1992 | 14524.0222 | -4131.7743 | -6568.5438 | -38.92% | -31.14% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
535 | Expense | Electric Distribution | GC | E Dist Subst O&M | GCG | Vegetation Management | Substation | SBSTN-C021: Vegetation Management | Ex 4, Ch 15 | Yes | N/A | N/A | 10476.5925 | 10615.9734 | 21092.5659 | 8039.823 | 6484.1992 | 14524.0222 | -4131.7743 | -6568.5438 | -38.92% | -31.14% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
536 | Expense | Electric Distribution | GC | E Dist Subst O&M | GCG | Vegetation Management | Wildfire | WLDFR-C006: Vegetation Management - Substation | Ex 4, Ch 15 | Yes | N/A | N/A | 10476.5925 | 10615.9734 | 21092.5659 | 8039.823 | 6484.1992 | 14524.0222 | -4131.7743 | -6568.5438 | -38.92% | -31.14% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
537 | Expense | Electric Distribution | GC | E Dist Subst O&M | GCH | Building Maintenance | SRM Total | SRM Total | Ex 4, Ch 15 | No | On-going | Annual | 1101.1846 | 1115.8349 | 2217.0195 | 3638.9453 | 3330.0338 | 6968.9791 | 2214.199 | 4751.9596 | 198.4% | 214.3% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
538 | Expense | Electric Distribution | GC | E Dist Subst O&M | GCH | Building Maintenance | Substation | SBSTN-C017: Proactive Maintenance | Ex 4, Ch 15 | Yes | N/A | N/A | 1101.1846 | 1115.8349 | 2217.0195 | 3638.9453 | 3330.0338 | 6968.9791 | 2214.199 | 4751.9596 | 198.4% | 214.3% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
539 | Expense | Electric Distribution | GC | E Dist Subst O&M | GCI | Dsbn: Switches_prevent maint. | SRM Total | SRM Total | Ex 4, Ch 15 | No | On-going | Annual | 106.8392 | 108.2606 | 215.0999 | 152.7471 | 30.4673 | 183.2143 | -77.7934 | -31.8855 | -71.86% | -14.82% | NO | NO | Switches Maintained | 112 | 112.0001 | 224.0001 | 70 | 24 | 94 | -88.0001 | -130.0001 | -78.57% | -58.04% | YES | Below variance threshold. | Actual units were lower than imputed units due to higher actual unit costs than forecast. Higher unit costs are generally driven by labor, and resulted in fewer program units achieved. | Under | On-Target | On-Target | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The scope of work for this program is performed in accordance with GO174, which sets forth requirements for electric utility substation inspections and maintenance.
540 | Expense | Electric Distribution | GC | E Dist Subst O&M | GCI | Dsbn: Switches_prevent maint. | Substation | SBSTN-C017: Proactive Maintenance | Ex 4, Ch 15 | Yes | N/A | N/A | 106.8392 | 108.2606 | 215.0999 | 152.7471 | 30.4673 | 183.2143 | -77.7934 | -31.8855 | -71.86% | -14.82% | N/A | N/A | N/A | 112 | N/A | N/A | 70 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
541 | Expense | Electric Distribution | GC | E Dist Subst O&M | GCJ | Dist Sub: Corrective (T80) | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 15 | No | On-going | Annual | 10080.9699 | 10215.0875 | 20296.0575 | 13311.7023 | 13822.7529 | 27134.4552 | 3607.6654 | 6838.3977 | 35.32% | 33.69% | NO | NO | Substation Corrective | 4726.85 | 4726.8456 | 9453.6956 | 8631 | 10577 | 19208 | 5850.1544 | 9754.3044 | 123.8% | 103.2% | YES | Below variance threshold. | Actual units were higher than imputed units due to the bundling of work for executional efficiencies, which resulted in additional program units being pulled into scope for a lower unit cost. | Over | On-Target | On-Target | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The scope of work for this program is performed in accordance with GO174, which sets forth requirements for electric utility substation inspections and maintenance.
542 | Expense | Electric Distribution | GC | E Dist Subst O&M | GCM | Breaker Mechanism Services | SRM Total | SRM Total | Ex 4, Ch 15 | No | On-going | Annual | 1588.837 | 1609.975 | 3198.812 | 2527.6063 | 2115.5727 | 4643.179 | 505.5977 | 1444.367 | 31.4% | 45.15% | NO | NO | # Mech Services | 709.98 | 709.9775 | 1419.9575 | 844 | 682 | 1526 | -27.9775 | 106.0425 | -3.941% | 7.468% | NO | Below variance threshold. | Below variance threshold. | On-Target | On-Target | On-Target | Proceeding as Planned | This program has no end date and will continue through the remainder of the 2023 GRC period. The scope of this work is ongoing in accordance with GO174, which sets forth requirements for electric utility substations inspections and maintenance.
543 | Expense | Electric Distribution | GC | E Dist Subst O&M | GCM | Breaker Mechanism Services | Substation | SBSTN-C017: Proactive Maintenance | Ex 4, Ch 15 | Yes | N/A | N/A | 1588.837 | 1609.975 | 3198.812 | 2527.6063 | 2115.5727 | 4643.179 | 505.5977 | 1444.367 | 31.4% | 45.15% | N/A | N/A | # of Mechanism Services | 709.98 | 709.9775 | 1419.9575 | 844 | 682 | 1526 | -27.9775 | 106.0425 | -3.941% | 7.468% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
544 | Expense | Electric Distribution | GC | E Dist Subst O&M | GCO | Transformer Overhauls | SRM Total | SRM Total | Ex 4, Ch 15 | No | On-going | Annual | 1291.5912 | 1308.7746 | 2600.3658 | 824.1389 | 1244.4521 | 2068.5911 | -64.3225 | -531.7747 | -4.915% | -20.45% | NO | NO | # Mech Services | 151 | 150.9977 | 301.9977 | 60 | 102 | 162 | -48.9977 | -139.9977 | -32.45% | -46.36% | YES | Below variance threshold. | Actual units were lower than imputed units due to higher actual unit costs than forecast. Higher unit costs are generally driven by labor, and resulted in fewer program units achieved. | Under | On-Target | On-Target | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The scope of work for this program is performed in accordance with GO174, which sets forth requirements for electric utility substation inspections and maintenance.
545 | Expense | Electric Distribution | GC | E Dist Subst O&M | GCO | Transformer Overhauls | Substation | SBSTN-C017: Proactive Maintenance | Ex 4, Ch 15 | Yes | N/A | N/A | 1291.5912 | 1308.7746 | 2600.3658 | 824.1389 | 1244.4521 | 2068.5911 | -64.3225 | -531.7747 | -4.915% | -20.45% | N/A | N/A | # of Mechanism Services | 151 | 150.9977 | 301.9977 | 60 | 102 | 162 | -48.9977 | -139.9977 | -32.45% | -46.36% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
546 | Expense | Electric Distribution | GC | E Dist Subst O&M | GCS | CKSW MOAS Mechanism Services | SRM Total | SRM Total | Ex 4, Ch 15 | No | On-going | Annual | 214.7363 | 217.5932 | 432.3295 | 256.403 | 555.6226 | 812.0256 | 338.0294 | 379.6961 | 155.3% | 87.83% | NO | NO | # Overhauls | 82 | 82.0024 | 164.0024 | 51 | 88 | 139 | 5.9976 | -25.0024 | 7.314% | -15.25% | NO | Below variance threshold. | Below variance threshold. | On-Target | On-Target | On-Target | Proceeding as Planned | This program has no end date and will continue through the remainder of the 2023 GRC period. The scope of this work is ongoing in accordance with GO174, which sets forth requirements for electric utility substations inspections and maintenance.
547 | Expense | Electric Distribution | GC | E Dist Subst O&M | GCS | CKSW MOAS Mechanism Services | Substation | SBSTN-C017: Proactive Maintenance | Ex 4, Ch 15 | Yes | N/A | N/A | 214.7363 | 217.5932 | 432.3295 | 256.403 | 555.6226 | 812.0256 | 338.0294 | 379.6961 | 155.3% | 87.83% | N/A | N/A | # of Overhauls | 82 | 82.0024 | 164.0024 | 51 | 88 | 139 | 5.9976 | -25.0024 | 7.314% | -15.25% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
548 | Expense | Electric Distribution | GC | E Dist Subst O&M | GCV | Breaker Overhauls | SRM Total | SRM Total | Ex 4, Ch 15 | No | On-going | Annual | 21.1563 | 21.4378 | 42.594 | 105.3334 | 83.9332 | 189.2666 | 62.4954 | 146.6725 | 291.5% | 344.3% | NO | NO | # Overhauls | 5 | 5.0012 | 10.0012 | 19 | 13 | 32 | 7.9988 | 21.9988 | 159.9% | 220% | YES | Below variance threshold. | Actual units were higher than imputed units based on objective to ensure circuit breakers are operating as intended, resulting in more overhauls than forecast. | Over | On-Target | On-Target | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The scope of work for this program is performed in accordance with GO174, which sets forth requirements for electric utility substation inspections and maintenance.
549 | Expense | Electric Distribution | GC | E Dist Subst O&M | GCV | Breaker Overhauls | Substation | SBSTN-C017: Proactive Maintenance | Ex 4, Ch 15 | Yes | N/A | N/A | 21.1563 | 21.4378 | 42.594 | 105.3334 | 83.9332 | 189.2666 | 62.4954 | 146.6725 | 291.5% | 344.3% | N/A | N/A | N/A | 5 | N/A | N/A | 19 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
550 | Expense | Electric Distribution | GC | E Dist Subst O&M | GCW | Dist Sub: Station Washes | SRM Total | SRM Total | Ex 4, Ch 15 | No | On-going | Annual | 463.3227 | 469.4867 | 932.8094 | 410.2365 | 472.6186 | 882.855 | 3.1318 | -49.9543 | 0.6671% | -5.355% | NO | NO | Substation Preventative | 429.99 | 429.9895 | 859.9795 | 458 | 457 | 915 | 27.0105 | 55.0205 | 6.282% | 6.398% | NO | Below variance threshold. | Below variance threshold. | On-Target | On-Target | On-Target | Proceeding as Planned | This program has no end date and will continue through the remainder of the 2023 GRC period. The scope of this work is ongoing in accordance with GO174, which sets forth requirements for electric utility substations inspections and maintenance.
551 | Expense | Electric Distribution | GC | E Dist Subst O&M | GCW | Dist Sub: Station Washes | Substation | SBSTN-C017: Proactive Maintenance | Ex 4, Ch 15 | Yes | N/A | N/A | 463.3227 | 469.4867 | 932.8094 | 410.2365 | 472.6186 | 882.855 | 3.1318 | -49.9543 | 0.6671% | -5.355% | N/A | N/A | N/A | 429.99 | N/A | N/A | 458 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
552 | Expense | Electric Distribution | GE | E Dist Mapping | N/A | Not assigned | SRM Total | SRM Total | Ex 4, Ch 20 | No | On-going | Annual | 19272.2306 | 19284.6971 | 38556.9277 | 24668.3532 | 29589.4787 | 54257.8319 | 10304.7816 | 15700.9042 | 53.44% | 40.72% | YES | YES | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Program expenses exceeded imputed regulatory values due to: (1) expenses to develop and implement PG&E’s Asset Data Management Plan, data management standards, tools, analytic products, and data quality improvement projects, and (2) expenses from emergent programs created to improve wildfire-related data, develop wildfire data and analytic products, and respond to wildfire related data requirements including the Wildfire Safety Division GIS Data Standard. | N/A | On-Target | On-Target | Over | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The purpose of this program is to: 1) manage the Electric Asset Registry including GIS systems of record, mapping of new assets, and conversion of records into digital form; 2) manage data quality; 3) provide data access and integration; and 4) develop new analytic tools in support of Electric Asset Management. PG&E may continue to spend more than adopted in this program over the course of the GRC cycle in order to manage data critical to Electric Operations.
553 | Expense | Electric Distribution | GE | E Dist Mapping | N/A | Not assigned | Wildfire | WLDFR-M002: System Hardening | Ex 4, Ch 20 | Yes | On-going | Annual | 0 | 0 | 0 | 0 | 199.4234 | 199.4234 | 199.4234 | 199.4234 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
554 | Expense | Electric Distribution | GE | E Dist Mapping | N/A | Not assigned | SRM (NON-RAMP) | SRM (NON-RAMP) | Ex 4, Ch 20 | Yes | On-going | Annual | 19272.2306 | 19284.6971 | 38556.9277 | 24668.3532 | 29390.0553 | 54058.4085 | 10105.3582 | 15501.4808 | 52.4% | 40.2% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
555 | Expense | Electric Distribution | HG | Elec Trans Ops Engr & Tech | HG# | Not assigned | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 21 | No | On-going | Annual | 0 | 0 | 0 | 0 | 2970.3987 | 2970.3987 | 2970.3987 | 2970.3987 | 100% | 100% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | Over | Proceeding as Planned | The DERMS program work is ongoing and will continue into PG&E's 2023 GRC period. New tools and processes for orchestration of Distributed Energy Resources (DERs) are required to safely and cost-effectively operate the grid. The Distributed Energy Resources Management (DERMS) Program includes the development, deployment, and operation of these tools and processes to enable these objectives. These costs support the ongoing operation and maintenance of these tools and processes. Note: DERMS program costs were originally adopted under the HGC MAT code, but have since been moved under HG#.
556 | Expense | Electric Distribution | HG | Elec Trans Ops Engr & Tech | HGC | Advanced Dist Mgmt System Dev | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 21 | No | 10 | 8 | 17229.2774 | 17159.8721 | 34389.1495 | 11058.9714 | 10731.9297 | 21790.9011 | -6427.9424 | -12598.2484 | -37.46% | -36.63% | NO | YES | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Program expenses were below imputed regulatory values due to the availability of a technological solution for obtaining phase identification data necessary to support the immediate needs of ADMS, eliminating the need to manually collect this data. | N/A | On-Target | On-Target | Under | Proceeding as Planned | The ADMS program is a one-time program, and is projected to be completed in 2026, prior to the end of the 2023 GRC cycle. PG&E anticipates continuing to spend below imputed amounts for the remainder of the GRC cycle because the program involves project-based work that may have peaked in the GRC Test Year.
557 | Expense | Electric Distribution | HG | Elec Trans Ops Engr & Tech | HGD | Distribution Operational Tech | SRM Total | SRM Total | Ex 4, Ch 7 | No | On-going | Annual | 5978.0311 | 5953.9495 | 11931.9806 | 7481.5202 | 9306.6721 | 16788.1924 | 3352.7226 | 4856.2117 | 56.31% | 40.7% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | This MAT Code is being used for ongoing maintenance tied to Distribution Operational Technology.
558 | Expense | Electric Distribution | HG | Elec Trans Ops Engr & Tech | HGD | Distribution Operational Tech | Wildfire | WLDFR-M020: Enhanced Powerline Safety Settings | Ex 4, Ch 7 | Yes | N/A | N/A | 0 | 0 | 0 | 82.8474 | 173.8516 | 256.699 | 173.8516 | 256.699 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
559 | Expense | Electric Distribution | HG | Elec Trans Ops Engr & Tech | HGD | Distribution Operational Tech | SRM (NON-RAMP) | SRM (NON-RAMP) | Ex 4, Ch 7 | Yes | N/A | N/A | 5978.0311 | 5953.9495 | 11931.9806 | 7398.6728 | 9132.8206 | 16531.4934 | 3178.871 | 4599.5128 | 53.39% | 38.55% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
560 | Expense | Electric Distribution | HN | E Dist Tree Trim Bal Acct | N/A | Not assigned | SRM Total | SRM Total | Ex 4, Ch 9 | No | On-going | Annual | 972012.9814 | 965868.48 | 1937881.4615 | 859187.0852 | 1002998.7474 | 1862185.8327 | 37130.2674 | -75695.6288 | 3.844% | -3.906% | YES | NO | # of Veg. Mgmt Trees | 1546783 | 1546783 | 3093566 | 1241025 | 1410201.22 | 2651226.22 | -136581.78 | -442339.78 | -8.83% | -14.3% | NO | Program expenses exceeded imputed regulatory values, primarily as the result of increased units completed due to a rebalance of work, based upon a risk-informed assessment of available tree work. Funding for work was reallocated to Distribution Routine to prioritize work in areas that held higher risk in the marked tree inventory and reduced the overall carryover. In addition, incremental Pole Clearing units were added to the work plan to address ignition risk identified using the Utility Fire Potential Index (FPI). | Below variance threshold. | On-Target | Under | Under | Rescheduled | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The purpose of this program is to perform routine tree work. PG&E anticipates continuing to perform fewer units than adopted over the remainder of the GRC cycle.
561 | Expense | Electric Distribution | HN | E Dist Tree Trim Bal Acct | N/A | Not assigned | Distribution Overhead | DOVHD-C001: Vegetation Management - Distribution Overhead | Ex 4, Ch 9 | Yes | N/A | N/A | 972012.9814 | 965868.48 | 1937881.4615 | 859187.1 | 1002998.7474 | 1862185.8474 | 37130.2674 | -75695.6141 | 3.844% | -3.906% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
562 | Expense | Electric Distribution | HN | E Dist Tree Trim Bal Acct | N/A | Not assigned | Wildfire | WLDFR-C004: Vegetation Management - Distribution Overhead | Ex 4, Ch 9 | Yes | N/A | N/A | 972012.9814 | 965868.48 | 1937881.4615 | 859187.1 | 1002998.7474 | 1862185.8474 | 37130.2674 | -75695.6141 | 3.844% | -3.906% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
563 | Expense | Electric Distribution | HX | E T&D Automation & Protection | N/A | Not assigned | SRM Total | SRM Total | Ex 4, Ch 16 | No | On-going | Annual | 3118.3174 | 3184 | 6302.3175 | 2693.8379 | 1990.0543 | 4683.8922 | -1193.9457 | -1618.4252 | -37.5% | -25.68% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
564 | Expense | Electric Distribution | HX | E T&D Automation & Protection | N/A | Not assigned | Distribution Overhead | DOVHD-C007: Supervisory Control and Data Acquisition | Ex 4, Ch 16 | Yes | N/A | N/A | 3118.3174 | 3184 | 6302.3175 | 2693.8379 | 1990.0543 | 4683.8922 | -1193.9457 | -1618.4252 | -37.5% | -25.68% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
565 | Expense | Electric Distribution | HX | E T&D Automation & Protection | N/A | Not assigned | Wildfire | WLDFR-M020: Enhanced Powerline Safety Settings | Ex 4, Ch 16 | Yes | N/A | N/A | 0 | 0 | 0 | 72.5254 | 57.1026 | 129.628 | 57.1026 | 129.628 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
566 | Expense | Electric Distribution | HY | Change/Maint Used Gas Meters | N/A | Not assigned | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 8 | No | On-going | Annual | 687.1 | 710.3007 | 1397.4007 | 250.6 | 289.4958 | 540.0958 | -420.8049 | -857.3049 | -59.24% | -61.35% | NO | NO | Field orders | 1466 | 1466 | 2932 | 2927 | 3478 | 6405 | 2012 | 3473 | 137.2% | 118.5% | YES | Below variance threshold. | Actual units were higher than imputed units because of an increase in the need to maintain or change used gas meters. This demand is from either 1) customer requests e.g., usage inquiries; or 2) automated system notification for resolution of a meter issue. | Over | On-Target | On-Target | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The purpose of this program is a continuing effort to provide gas meter maintenance, based on 1) customer-driven requests; and 2) automated system notifications for meter issue resolution.
567 | Expense | Electric Distribution | IF | E Dist Major Emergency | N/A | N/A | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 6 | No | On-going | Annual | 45380.7998 | 45908.2092 | 91289.009 | 38356.8805 | 214333.8032 | 252690.6837 | 168425.594 | 161401.6747 | 366.9% | 176.8% | YES | YES | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Program expenses exceeded imputed regulatory values due the February Winter Storms and the July Weather Event which caused a significant deviation from historical trends. | N/A | On-Target | On-Target | Over | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is for major emergencies. This is a demand driven program. This program has no end and is responsive to conditions that require immediate attention.
568 | Expense | Electric Distribution | IG | Manage Var Bal Acct Processes | IGI | Dead and Dying Trees | SRM Total | SRM Total | Ex 4, Ch 9 | No | On-going | Annual | 77991.4684 | 77468.8654 | 155460.3338 | 136577.1456 | 139861.4302 | 276438.5758 | 62392.5648 | 120978.242 | 80.54% | 77.82% | YES | YES | # of Veg. Mgmt Trees | 65000 | 65000 | 130000 | 81281 | 225345.35 | 306626.35 | 160345.35 | 176626.35 | 246.7% | 135.9% | YES | Program expenses exceeded imputed regulatory values due to increased tree units. Volume of work increased due to 1) rescheduled work from previous year; and 2) more work was identified due to changes in scope of patrol procedure. For example, including not just dead trees but healthy trees with defects and trees with growth that could break compliance distance. | Actual units were higher than imputed units of work due to 1) rescheduled work from previous year; and 2) more work was identified due to changes in scope of patrol procedure. For example, including not just dead trees but healthy trees with defects and growth that could break compliance distance. | Over | On-Target | Over | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. This program is scheduled to continue through 2026, and PG&E anticipates continuing to perform more units than adopted in the 2023 GRC.
569 | Expense | Electric Distribution | IG | Manage Var Bal Acct Processes | IGI | Dead and Dying Trees | Distribution Overhead | DOVHD-C002: Vegetation Management - CEMA/Tree Mortality | Ex 4, Ch 9 | Yes | N/A | N/A | 77991.4684 | 77468.8654 | 155460.3338 | 136577.1456 | 139861.4302 | 276438.5758 | 62392.5648 | 120978.242 | 80.54% | 77.82% | N/A | N/A | N/A | 65000 | N/A | N/A | 81281 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
570 | Expense | Electric Distribution | IG | Manage Var Bal Acct Processes | IGI | Dead and Dying Trees | Wildfire | WLDFR-C007: Vegetation Management - CEMA/Tree Mortality | Ex 4, Ch 9 | Yes | N/A | N/A | 77991.4684 | 77468.8654 | 155460.3338 | 136577.1456 | 139861.4302 | 276438.5758 | 62392.5648 | 120978.242 | 80.54% | 77.82% | N/A | N/A | N/A | 65000 | N/A | N/A | 81281 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
571 | Expense | Electric Distribution | IG | Manage Var Bal Acct Processes | IGJ | Enhanced Vegetation Management | SRM Total | SRM Total | Ex 4, Ch 9 | No | On-going | Annual | 131815.9685 | 130932.6999 | 262748.6684 | 161012.919 | 180873.9783 | 341886.8973 | 49941.2784 | 79138.2289 | 38.14% | 30.12% | YES | YES | # Miles | 1800 | 1800 | 3600 | 274 | N/A | 274 | -1800 | -3326 | -100% | -92.39% | YES | Program expenses exceed imputed regulatory values due to MAT IGJ imputed adopted values would have reflected a forecast for EVM which was discontinued at the end of 2022 and superseded by Wildfire Mitigation Plan programs: Focused Tree Inspection (FTI), Tree Removal Inventory (TRI) & VM for Operational Mitigations (VMOM). Wood Management for Wildfire Mitigation Programs is also included in MAT IGJ. Forecast Cost for EVM anticipated clearing overhanging branches for 1,800 miles, whereas the mitigation programs include 1,500 miles of FTI, detailed inspection, and TRI is whole tree removals listed under the previous EVM program. Under both of these programs work is predominantly tree removals rather than the anticipated clearing overhanging branches in 2023 GRC. | Actual units were lower than imputed units because the Enhanced Vegetation Management (EVM) program was discontinued at the end of 2022. The scope of work changed in 2023 to focus on four primary programs: Focused Tree Inspection (FTI), Tree Removal Inventory (TRI), VM for Operational Mitigations (VMOM) and Wood Management. The imputed adopted value reflected a unit forecast for EVM measured in miles, whereas the unit of measure for the new programs were a combination of trees, wood managed, and miles. | Under | Over | Over | Emergent | Work is ongoing and will continue in PG&E’s 2023 GRC period. The Enhanced Vegetation Management (EVM) program concluded in 2022, and the scope of the program was changed as described in the unit variance explanation. PG&E anticipates continuing with the adjusted scope of the program, focusing on Focused Tree Inspection, VMOM, Tree Removal Inventory, and Wood Management.
572 | Expense | Electric Distribution | IG | Manage Var Bal Acct Processes | IGJ | Enhanced Vegetation Management | Wildfire | WLDFR-M001: Enhanced Vegetation Management | Ex 4, Ch 9 | Yes | N/A | N/A | 131815.9685 | 130932.6999 | 262748.6684 | 161012.919 | 180873.9783 | 341886.8973 | 49941.2784 | 79138.2289 | 38.14% | 30.12% | N/A | N/A | N/A | 1800 | N/A | N/A | 274 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
573 | Expense | Electric Distribution | IG | Manage Var Bal Acct Processes | IG# | Not assigned | SRM Total | SRM Total | Ex 4, Ch 21 Ex 4, Ch 4.5 Ex 4, Ch 4.6 | No | On-going | Annual | 76787.2006 | 77665.1635 | 154452.3641 | 132422.3794 | 78133.3166 | 210555.696 | 468.1531 | 56103.3319 | 0.6028% | 36.32% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | Over | Over | Emergent | This work is ongoing and will continue in PG&Es 2023 GRC period. This MAT is used to record various balancing and memorandum account activities. PG&E anticipates that this program will be over the 2023 GRC cycle imputed regulatory values for MAT Code IG# due to activities for mitigating wildfire risk that were not forecast in IG# in the 2023 GRC. These include EPSS costs for helicopter standby, temporary generation, and battery programs.
574 | Expense | Electric Distribution | IG | Manage Var Bal Acct Processes | IG# | Not assigned | Distribution Overhead | DOVHD-C002: Vegetation Management - CEMA/Tree Mortality | Ex 4, Ch 21 Ex 4, Ch 4.5 Ex 4, Ch 4.6 | Yes | N/A | N/A | 0 | 0 | 0 | 0 | 2442.7271 | 2442.7271 | 2442.7271 | 2442.7271 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
575 | Expense | Electric Distribution | IG | Manage Var Bal Acct Processes | IG# | Not assigned | Distribution Overhead | DOVHD-M005: Additional Asset Data Capture | Ex 4, Ch 21 Ex 4, Ch 4.5 Ex 4, Ch 4.6 | No | N/A | N/A | 0 | 0 | 0 | 183.895 | 0 | 183.895 | 0 | 183.895 | 0% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
576 | Expense | Electric Distribution | IG | Manage Var Bal Acct Processes | IG# | Not assigned | Emergency Preparedness & Response | EPNDR-C000: EP&R Controls | Ex 4, Ch 21 Ex 4, Ch 4.5 Ex 4, Ch 4.6 | Yes | N/A | N/A | 0 | 0 | 0 | 232.201 | 350.6866 | 582.8875 | 350.6866 | 582.8875 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
577 | Expense | Electric Distribution | IG | Manage Var Bal Acct Processes | IG# | Not assigned | Emergency Preparedness & Response | EPNDR-C002: Situational Awareness and Forecasting Initiatives - WSOC | Ex 4, Ch 21 Ex 4, Ch 4.5 Ex 4, Ch 4.6 | No | N/A | N/A | 0 | 0 | 0 | 2724.6525 | 0 | 2724.6525 | 0 | 2724.6525 | 0% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
578 | Expense | Electric Distribution | IG | Manage Var Bal Acct Processes | IG# | Not assigned | Emergency Preparedness & Response | EPNDR-M000: EP&R Mitigations | Ex 4, Ch 21 Ex 4, Ch 4.5 Ex 4, Ch 4.6 | Yes | N/A | N/A | 0 | 0 | 0 | 189.9826 | 286.9254 | 476.908 | 286.9254 | 476.908 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
579 | Expense | Electric Distribution | IG | Manage Var Bal Acct Processes | IG# | Not assigned | Wildfire | WLDFR-C007: Vegetation Management - CEMA/Tree Mortality | Ex 4, Ch 21 Ex 4, Ch 4.5 Ex 4, Ch 4.6 | Yes | N/A | N/A | 0 | 0 | 0 | 0 | 2442.7271 | 2442.7271 | 2442.7271 | 2442.7271 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
580 | Expense | Electric Distribution | IG | Manage Var Bal Acct Processes | IG# | Not assigned | Wildfire | WLDFR-M006: PSPS Reduction Initiatives | Ex 4, Ch 21 Ex 4, Ch 4.5 Ex 4, Ch 4.6 | Yes | N/A | N/A | 0 | 0 | 0 | 7202.4815 | 4883.8865 | 12086.368 | 4883.8865 | 12086.368 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
581 | Expense | Electric Distribution | IG | Manage Var Bal Acct Processes | IG# | Not assigned | Wildfire | WLDFR-M0IT: Wildfire IT Work | Ex 4, Ch 21 Ex 4, Ch 4.5 Ex 4, Ch 4.6 | Yes | N/A | N/A | 38734.4 | 38882.8461 | 77617.2461 | 36120.5247 | 37507.9374 | 73628.4622 | -1374.9087 | -3988.7839 | -3.536% | -5.139% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
582 | Expense | Electric Distribution | IG | Manage Var Bal Acct Processes | IG# | Not assigned | Wildfire | WLDFR-M020: Enhanced Powerline Safety Settings | Ex 4, Ch 21 Ex 4, Ch 4.5 Ex 4, Ch 4.6 | Yes | N/A | N/A | 34895.7218 | 35566.7184 | 70462.4401 | 64233.3524 | 30783.913 | 95017.2655 | -4782.8053 | 24554.8253 | -13.45% | 34.85% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
583 | Expense | Electric Distribution | IG | Manage Var Bal Acct Processes | IG# | Not assigned | Wildfire | POST-GRC: Post-GRC Mitigation | Ex 4, Ch 21 Ex 4, Ch 4.5 Ex 4, Ch 4.6 | Yes | N/A | N/A | 0 | 0 | 0 | 18404.1181 | 1353.332 | 19757.4501 | 1353.332 | 19757.4501 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
584 | Expense | Electric Distribution | IG | Manage Var Bal Acct Processes | IG# | Not assigned | SRM (NON-RAMP) | SRM (NON-RAMP) | Ex 4, Ch 21 Ex 4, Ch 4.5 Ex 4, Ch 4.6 | Yes | N/A | N/A | 3157 | 3215.599 | 6372.599 | 3131.1716 | 523.9086 | 3655.0802 | -2691.6904 | -2717.5189 | -83.71% | -42.64% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
585 | Expense | Electric Distribution | IS | Bill Customers | N/A | Not assigned | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 22 | No | On-going | Annual | 1830.672 | 1819.0996 | 3649.7716 | 572.5527 | 672.9663 | 1245.5189 | -1146.1333 | -2404.2527 | -63.01% | -65.87% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
586 | Expense | Electric Distribution | IU | Collect Revenue | N/A | Not assigned | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 8 | No | On-going | Annual | 1589.8684 | 1659.8259 | 3249.6943 | 1088.0359 | 1274.3272 | 2362.3631 | -385.4988 | -887.3313 | -23.23% | -27.31% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
587 | Expense | Electric Distribution | JV | Maintain IT Apps & Infra | N/A | Not assigned | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 20 Ex 4, Ch 21 | No | On-going | Annual | 8419.0283 | 8471.7026 | 16890.7308 | 4430.1601 | 4715.7107 | 9145.8708 | -3755.9919 | -7744.86 | -44.34% | -45.85% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
588 | Expense | Electric Distribution | JV | Maintain IT Apps & Infra | N/A | Not assigned | Emergency Preparedness & Response | EPNDR-C002: Situational Awareness and Forecasting Initiatives - WSOC | Ex 4, Ch 20 Ex 4, Ch 21 | No | N/A | N/A | 0 | 0 | 0 | 755.5872 | 0 | 755.5872 | 0 | 755.5872 | 0% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
589 | Expense | Electric Distribution | JV | Maintain IT Apps & Infra | N/A | Not assigned | IT Asset Failure | ITAFL-M005: Multi-Faceted Mitigations | Ex 4, Ch 20 Ex 4, Ch 21 | Yes | N/A | N/A | 0 | 0 | 0 | 0 | 71.0928 | 71.0928 | 71.0928 | 71.0928 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
590 | Expense | Electric Distribution | JV | Maintain IT Apps & Infra | N/A | Not assigned | Wildfire | WLDFR-M0IT: Wildfire IT Work | Ex 4, Ch 20 Ex 4, Ch 21 | Yes | N/A | N/A | 0 | 0 | 0 | 0 | 293.8195 | 293.8195 | 293.8195 | 293.8195 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
591 | Expense | Electric Distribution | JV | Maintain IT Apps & Infra | N/A | Not assigned | SRM (NON-RAMP) | SRM (NON-RAMP) | Ex 4, Ch 20 Ex 4, Ch 21 | Yes | N/A | N/A | 8419.0283 | 8471.7026 | 16890.7308 | 3674.5729 | 4350.7984 | 8025.3713 | -4120.9042 | -8865.3595 | -48.64% | -52.49% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
592 | Expense | Electric Distribution | KA | E Dist Maint OH General | KAA | OH Genl CM Tag | SRM Total | SRM Total | Ex 4, Ch 11 | No | On-going | Annual | 22085.7202 | 22135.0216 | 44220.7418 | 75395.0109 | 139875.0479 | 215270.0588 | 117740.0263 | 171049.317 | 531.9% | 386.8% | YES | YES | # of Notifications Completed | 24150.66 | 24150.6645 | 48301.3245 | 26555 | 58049 | 84604 | 33898.3355 | 36302.6755 | 140.4% | 75.16% | YES | Program expenses exceeded imputed regulatory values due to higher volume of units completed at higher unit costs than adopted in the 2023 GRC Final Decision. PG&E's actual unit cost remain higher than imputed unit costs driven by the higher labor costs for this work. | Actual units were higher than imputed units due to address WMP commitments for the maintenance log. | Over | On-Target | Over | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The purpose of this program is the repair of overhead (OH) facilities or replacement of individual components that are not an imminent hazard. PG&E anticipates the program scope will remain on target while spending more than the GRC imputed adopted costs over the remainder of the cycle to address the maintenance log and meet WMP commitments.
593 | Expense | Electric Distribution | KA | E Dist Maint OH General | KAA | OH Genl CM Tag | Distribution Overhead | DOVHD-C003: Equipment Maintenance and Replacement - Distribution Overhead | Ex 4, Ch 11 | Yes | N/A | N/A | 22085.7202 | 22135.0216 | 44220.7418 | 75395.0109 | 139875.0479 | 215270.0588 | 117740.0263 | 171049.317 | 531.9% | 386.8% | N/A | N/A | # of Notifications Completed | 24150.66 | 24150.6645 | 48301.3245 | 26555 | 58049 | 84604 | 33898.3355 | 36302.6755 | 140.4% | 75.16% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
594 | Expense | Electric Distribution | KA | E Dist Maint OH General | KAA | OH Genl CM Tag | Wildfire | WLDFR-C008: Equipment Maintenance and Replacement - Distribution Overhead | Ex 4, Ch 11 | Yes | N/A | N/A | 22085.7202 | 22135.0216 | 44220.7418 | 75395.0109 | 139875.0479 | 215270.0588 | 117740.0263 | 171049.317 | 531.9% | 386.8% | N/A | N/A | # of Notifications Completed | 24150.66 | 24150.6645 | 48301.3245 | 26555 | 58049 | 84604 | 33898.3355 | 36302.6755 | 140.4% | 75.16% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
595 | Expense | Electric Distribution | KA | E Dist Maint OH General | KAC | Bird Safe Retrofit | SRM Total | SRM Total | Ex 4, Ch 11 | No | On-going | Annual | 1231.4039 | 1234.1528 | 2465.5567 | 683.0583 | 586.3039 | 1269.3623 | -647.8489 | -1196.1945 | -52.49% | -48.52% | NO | NO | # of Notifications Completed | 638.16 | 638.1579 | 1276.3179 | 402 | 228 | 630 | -410.1579 | -646.3179 | -64.27% | -50.64% | YES | Below variance threshold. | Actual units were lower than imputed units due to lower find rates than forecasted. | Under | On-Target | On-Target | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The purpose of this program is the replacement or installation of bird guard materials such as jumper covers, bushing covers, perch guards, or perching platforms on incident and/or adjacent poles in response to a bird electrocution, per U.S. Fish and Wildlife Service (USFWS) requirements and Utility Operating Standard S2321.
596 | Expense | Electric Distribution | KA | E Dist Maint OH General | KAC | Bird Safe Retrofit | Distribution Overhead | DOVHD-C003: Equipment Maintenance and Replacement - Distribution Overhead | Ex 4, Ch 11 | Yes | N/A | N/A | 1231.4039 | 1234.1528 | 2465.5567 | 683.0583 | 586.3039 | 1269.3623 | -647.8489 | -1196.1945 | -52.49% | -48.52% | N/A | N/A | # of Notifications Completed | 638.16 | 638.1579 | 1276.3179 | 402 | 228 | 630 | -410.1579 | -646.3179 | -64.27% | -50.64% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
597 | Expense | Electric Distribution | KA | E Dist Maint OH General | KAC | Bird Safe Retrofit | Wildfire | WLDFR-C011: Animal Abatement | Ex 4, Ch 11 | Yes | N/A | N/A | 1231.4039 | 1234.1528 | 2465.5567 | 683.0583 | 586.3039 | 1269.3623 | -647.8489 | -1196.1945 | -52.49% | -48.52% | N/A | N/A | # of Notifications Completed | 638.16 | 638.1579 | 1276.3179 | 402 | 228 | 630 | -410.1579 | -646.3179 | -64.27% | -50.64% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
598 | Expense | Electric Distribution | KA | E Dist Maint OH General | KAD | Bird Safe Retrofit Annual | SRM Total | SRM Total | Ex 4, Ch 11 | No | On-going | Annual | 1436.2747 | 1439.4809 | 2875.7555 | 312.6943 | 3467.5951 | 3780.2894 | 2028.1142 | 904.5339 | 140.9% | 31.45% | NO | NO | # of Notifications Completed | 1022 | 1022.0001 | 2044.0001 | 224 | 974 | 1198 | -48.0001 | -846.0001 | -4.697% | -41.39% | NO | Below variance threshold. | Below variance threshold. | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
599 | Expense | Electric Distribution | KA | E Dist Maint OH General | KAD | Bird Safe Retrofit Annual | Wildfire | WLDFR-C011: Animal Abatement | Ex 4, Ch 11 | Yes | N/A | N/A | 1436.2747 | 1439.4809 | 2875.7555 | 312.6943 | 3467.5951 | 3780.2894 | 2028.1142 | 904.5339 | 140.9% | 31.45% | N/A | N/A | # of Notifications Completed | 1022 | 1022.0001 | 2044.0001 | 224 | 974 | 1198 | -48.0001 | -846.0001 | -4.697% | -41.39% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
600 | Expense | Electric Distribution | KA | E Dist Maint OH General | KAF | OH COE CM Tag | SRM Total | SRM Total | Ex 4, Ch 11 | No | On-going | Annual | 7212.9759 | 7229.0772 | 14442.0531 | 6418.8636 | 5790.394 | 12209.2576 | -1438.6832 | -2232.7955 | -19.9% | -15.46% | NO | NO | # of Notifications Completed | 1380 | 1380.0002 | 2760.0002 | 1141 | 1250 | 2391 | -130.0002 | -369.0002 | -9.42% | -13.37% | NO | Below variance threshold. | Below variance threshold. | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
601 | Expense | Electric Distribution | KA | E Dist Maint OH General | KAF | OH COE CM Tag | Wildfire | WLDFR-C008: Equipment Maintenance and Replacement - Distribution Overhead | Ex 4, Ch 11 | Yes | N/A | N/A | 7212.9759 | 7229.0772 | 14442.0531 | 6418.8636 | 5790.394 | 12209.2576 | -1438.6832 | -2232.7955 | -19.9% | -15.46% | N/A | N/A | # of Notifications Completed | 1380 | 1380.0002 | 2760.0002 | 1141 | 1250 | 2391 | -130.0002 | -369.0002 | -9.42% | -13.37% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
602 | Expense | Electric Distribution | KA | E Dist Maint OH General | KAH | Streetlights Repl Burnouts | SRM Total | SRM Total | Ex 4, Ch 11 | No | On-going | Annual | 2171.8479 | 2176.696 | 4348.5439 | 1769.6744 | 1895.4349 | 3665.1093 | -281.2611 | -683.4345 | -12.92% | -15.72% | NO | NO | # of Burnout Repairs | 11714.32 | 11714.3214 | 23428.6414 | 6191 | 0 | 6191 | -11714.3214 | -17237.6414 | -100% | -73.58% | YES | Below variance threshold. | With the near completion of the LED conversion program, fewer HPSV bulb replacements will be needed (instead LED fixtures will need to be replaced under MAT 2AH) and replacements will be done ad-hoc. Therefore the costs are no longer unitized. | Under | On-Target | On-Target | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The purpose of this program is to repair streetlights when a streetlight outage has occurred. Since the LED conversion program is almost complete, a lower find rate for streetlights requiring bulb replacement is expected and the work will be tracked programmatically.
603 | Expense | Electric Distribution | KA | E Dist Maint OH General | KAH | Streetlights Repl Burnouts | Distribution Overhead | DOVHD-C003: Equipment Maintenance and Replacement - Distribution Overhead | Ex 4, Ch 11 | Yes | N/A | N/A | 2171.8479 | 2176.696 | 4348.5439 | 1769.6744 | 1895.4349 | 3665.1093 | -281.2611 | -683.4345 | -12.92% | -15.72% | N/A | N/A | # of Burnout Repairs | 11714.32 | 11714.3214 | 23428.6414 | 6191 | 0 | 6191 | -11714.3214 | -17237.6414 | -100% | -73.58% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
604 | Expense | Electric Distribution | KA | E Dist Maint OH General | KAK | RTVI Invest/Repr | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 11 | No | On-going | Annual | 126.4096 | 126.6918 | 253.1014 | 88.7648 | 80.9353 | 169.7001 | -45.7565 | -83.4013 | -36.12% | -32.95% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
605 | Expense | Electric Distribution | KA | E Dist Maint OH General | KAM | Insulators Wash | SRM Total | SRM Total | Ex 4, Ch 11 | No | On-going | Annual | 246.2808 | 246.8306 | 493.1114 | 304.7772 | 237.1062 | 541.8835 | -9.7243 | 48.7721 | -3.94% | 9.891% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
606 | Expense | Electric Distribution | KA | E Dist Maint OH General | KAM | Insulators Wash | Distribution Overhead | DOVHD-C003: Equipment Maintenance and Replacement - Distribution Overhead | Ex 4, Ch 11 | Yes | N/A | N/A | 246.2808 | 246.8306 | 493.1114 | 304.7772 | 237.1062 | 541.8835 | -9.7243 | 48.7721 | -3.94% | 9.891% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
607 | Expense | Electric Distribution | KA | E Dist Maint OH General | KAO | Idle Fac Invest - Svc Plng | SRM Total | SRM Total | Ex 4, Ch 11 | No | On-going | Annual | 214.6784 | 215.1576 | 429.836 | 2054.0632 | 1820.8959 | 3874.9591 | 1605.7383 | 3445.1231 | 746.3% | 801.5% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
608 | Expense | Electric Distribution | KA | E Dist Maint OH General | KAO | Idle Fac Invest - Svc Plng | Distribution Overhead | DOVHD-C003: Equipment Maintenance and Replacement - Distribution Overhead | Ex 4, Ch 11 | Yes | N/A | N/A | 214.6784 | 215.1576 | 429.836 | 2054.0632 | 1820.8959 | 3874.9591 | 1605.7383 | 3445.1231 | 746.3% | 801.5% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
609 | Expense | Electric Distribution | KA | E Dist Maint OH General | KAP | OH EXP Projects | SRM Total | SRM Total | Ex 4, Ch 11 | No | On-going | Annual | 1792.619 | 1796.6206 | 3589.2397 | 25.5764 | 3496.9548 | 3522.5311 | 1700.3341 | -66.7085 | 94.64% | -1.859% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
610 | Expense | Electric Distribution | KA | E Dist Maint OH General | KAP | OH EXP Projects | Distribution Overhead | DOVHD-C003: Equipment Maintenance and Replacement - Distribution Overhead | Ex 4, Ch 11 | Yes | N/A | N/A | 1792.619 | 1796.6206 | 3589.2397 | 25.5764 | 3496.9548 | 3522.5311 | 1700.3341 | -66.7085 | 94.64% | -1.859% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
611 | Expense | Electric Distribution | KA | E Dist Maint OH General | KAQ | Wood Pole Bridge Bonding | SRM Total | SRM Total | Ex 4, Ch 11 | No | On-going | Annual | 1.0897 | 1.0922 | 2.1819 | 881.7755 | 671.5721 | 1553.3476 | 670.48 | 1551.1657 | 61390% | 71092% | NO | NO | # of Notifications Completed | 2 | 2 | 4 | 296 | 237 | 533 | 235 | 529 | 11750% | 13225% | YES | Below variance threshold. | Actual units were higher than imputed units based on actual find rate (i.e. inspections that identified the need for a higher number of wood pole bridge bonding retrofits than anticipated) and targeted focus to complete this work as it is a control for reducing the risk of wildfire. | Over | On-Target | On-Target | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The purpose of this program is Wood Pole Bridge Bonding to prevent ignitions by ensuring grounding protection. Wood pole bonding is a maintenance activity where an existing wood pole supporting both electric transmission and distribution line facilities is retrofitted with grounding protection to prevent fires which can occur at the location on the pole where the electric distribution cross arm is bolted to the pole.
612 | Expense | Electric Distribution | KA | E Dist Maint OH General | KAQ | Wood Pole Bridge Bonding | Wildfire | WLDFR-C008: Equipment Maintenance and Replacement - Distribution Overhead | Ex 4, Ch 11 | Yes | N/A | N/A | 1.0897 | 1.0922 | 2.1819 | 881.7755 | 671.5721 | 1553.3476 | 670.48 | 1551.1657 | 61390% | 71092% | N/A | N/A | # of Notifications Completed | 2 | 2 | 4 | 296 | 237 | 533 | 235 | 529 | 11750% | 13225% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
613 | Expense | Electric Distribution | KA | E Dist Maint OH General | KAS | FAS Overhead Expense | SRM Total | SRM Total | Ex 4, Ch 11 | No | On-going | Annual | 1796.978 | 1800.9893 | 3597.9673 | 1150.2837 | 1051.3607 | 2201.6444 | -749.6286 | -1396.3229 | -41.62% | -38.81% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | 10453.34 | N/A | N/A | 8302 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | MAT KAS work is identified and performed by Troubleshooters in the field and is demand driven. Due to the variable nature of the work performed in MAT KAS, MAT KAS is non-unitized beginning in 2024. | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. This is a demand driven program. The program repairs overhead facilities identified during a field job and completed by a single PG&E Troubleshooter. The work could involve repairing overhead facilities such as: electric distribution conductors, components, structures, and associated equipment constructed above ground level. Due to the variable nature of the work performed in MAT KAS, MAT KAS is non-unitized beginning in 2024.
614 | Expense | Electric Distribution | KA | E Dist Maint OH General | KAS | FAS Overhead Expense | Distribution Overhead | DOVHD-C003: Equipment Maintenance and Replacement - Distribution Overhead | Ex 4, Ch 11 | Yes | N/A | N/A | 1796.978 | 1800.9893 | 3597.9673 | 1150.2837 | 1051.3607 | 2201.6444 | -749.6286 | -1396.3229 | -41.62% | -38.81% | N/A | N/A | N/A | 10453.34 | N/A | N/A | 8302 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
615 | Expense | Electric Distribution | KA | E Dist Maint OH General | KAT | Remote Grid SPS Maintenance | SRM Total | SRM Total | Ex 4, Ch 4.3 | No | On-going | Annual | 1038.7214 | 1041.0401 | 2079.7615 | 125.6272 | 667.0175 | 792.6447 | -374.0226 | -1287.1168 | -35.93% | -61.89% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
616 | Expense | Electric Distribution | KA | E Dist Maint OH General | KAT | Remote Grid SPS Maintenance | Distribution Overhead | DOVHD-M011: Remote Grid | Ex 4, Ch 4.3 | Yes | N/A | N/A | 1038.7214 | 1041.0401 | 2079.7615 | 25.839 | 667.0175 | 692.8565 | -374.0226 | -1386.905 | -35.93% | -66.69% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
617 | Expense | Electric Distribution | KA | E Dist Maint OH General | KAT | Remote Grid SPS Maintenance | Wildfire | WLDFR-M017: System Hardening - Remote Grid | Ex 4, Ch 4.3 | Yes | N/A | N/A | 1038.7214 | 1041.0401 | 2079.7615 | 125.6272 | 667.0175 | 792.6447 | -374.0226 | -1287.1168 | -35.93% | -61.89% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
618 | Expense | Electric Distribution | KA | E Dist Maint OH General | KA# | Not assigned | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 11 | No | On-going | Annual | 888.1365 | 890.119 | 1778.2555 | -34.2349 | 1591.6165 | 1557.3817 | 701.4975 | -220.8739 | 78.81% | -12.42% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
619 | Expense | Electric Distribution | KB | E Dist Maint UG | KBA | UG Genl CM Tag | SRM Total | SRM Total | Ex 4, Ch 11 | No | On-going | Annual | 17135.2076 | 17270.4231 | 34405.6308 | 15657.4038 | 18614.1991 | 34271.603 | 1343.776 | -134.0278 | 7.781% | -0.3896% | NO | NO | # of Notifications Completed | 6162.85 | 6162.8494 | 12325.6994 | 4916 | 4328 | 9244 | -1834.8494 | -3081.6994 | -29.77% | -25% | YES | Below variance threshold. | Actual units were lower than imputed units due to optimizing resources to focus on completing higher priority maintenance tags within MWCs KA and KB. | Under | On-Target | On-Target | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The purpose of this program is underground corrective maintenance that does not pose an imminent hazard and have not caused an outage. PG&E will continue to complete notifications based on the workplan maintenance schedule and priority of the tags.
620 | Expense | Electric Distribution | KB | E Dist Maint UG | KBA | UG Genl CM Tag | Underground | DUNGD-C002: Underground Notifications | Ex 4, Ch 11 | Yes | N/A | N/A | 17135.2076 | 17270.4231 | 34405.6308 | 15657.4038 | 18614.1991 | 34271.603 | 1343.776 | -134.0278 | 7.781% | -0.3896% | N/A | N/A | # of Notifications Completed | 6162.85 | 6162.8494 | 12325.6994 | 4916 | 4328 | 9244 | -1834.8494 | -3081.6994 | -29.77% | -25% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
621 | Expense | Electric Distribution | KB | E Dist Maint UG | KBC | UG COE CM Tag | SRM Total | SRM Total | Ex 4, Ch 11 | No | On-going | Annual | 1547.5023 | 1559.7138 | 3107.2161 | 403.6052 | 809.2628 | 1212.868 | -750.451 | -1894.3481 | -48.11% | -60.97% | NO | NO | # of Notifications Completed | 175 | 175.0001 | 350.0001 | 103 | 134 | 237 | -41.0001 | -113.0001 | -23.43% | -32.29% | YES | Below variance threshold. | Actual units were lower than imputed units due to optimizing resources to focus on completing higher priority maintenance tags within MWCs KA and KB. | Under | Under | Under | Rescheduled | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The purpose of the program is to repair of underground Critical Operating Equipment (COE). During the GRC cycle PG&E expects to continue to reprioritize the work in MAT KBC to other higher priority maintenance work in MWCs KA and KB.
622 | Expense | Electric Distribution | KB | E Dist Maint UG | KBC | UG COE CM Tag | Underground | DUNGD-C003: Equipment Maintenance and Replacement | Ex 4, Ch 11 | Yes | N/A | N/A | 1547.5023 | 1559.7138 | 3107.2161 | 403.6052 | 809.2628 | 1212.868 | -750.451 | -1894.3481 | -48.11% | -60.97% | N/A | N/A | # of Notifications Completed | 175 | 175.0001 | 350.0001 | 103 | 134 | 237 | -41.0001 | -113.0001 | -23.43% | -32.29% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
623 | Expense | Electric Distribution | KB | E Dist Maint UG | KBD | Nitrogen Cylinders CM | SRM Total | SRM Total | Ex 4, Ch 11 | No | On-going | Annual | 24.6828 | 24.8775 | 49.5603 | 8.4286 | 9.834 | 18.2627 | -15.0435 | -31.2977 | -60.47% | -63.15% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
624 | Expense | Electric Distribution | KB | E Dist Maint UG | KBD | Nitrogen Cylinders CM | Underground | DUNGD-C003: Equipment Maintenance and Replacement | Ex 4, Ch 11 | Yes | N/A | N/A | 24.6828 | 24.8775 | 49.5603 | 8.4286 | 9.834 | 18.2627 | -15.0435 | -31.2977 | -60.47% | -63.15% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
625 | Expense | Electric Distribution | KB | E Dist Maint UG | KBE | BART Cable Repr | SRM Total | SRM Total | Ex 4, Ch 11 | No | On-going | Annual | 70.8288 | 71.3877 | 142.2165 | 0.53587 | 2.1424 | 2.6782 | -69.2454 | -139.5383 | -97% | -98.12% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
626 | Expense | Electric Distribution | KB | E Dist Maint UG | KBE | BART Cable Repr | Underground | DUNGD-C003: Equipment Maintenance and Replacement | Ex 4, Ch 11 | Yes | N/A | N/A | 70.8288 | 71.3877 | 142.2165 | 0.53587 | 2.1424 | 2.6782 | -69.2454 | -139.5383 | -97% | -98.12% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
627 | Expense | Electric Distribution | KB | E Dist Maint UG | KBP | UG EXP Projects | SRM Total | SRM Total | Ex 4, Ch 11 | No | On-going | Annual | 788.7754 | 794.9997 | 1583.7752 | 1.0978 | 0.14433 | 1.2422 | -794.8554 | -1582.533 | -99.98% | -99.92% | NO | NO | # of Locations | 255.24 | 255.2413 | 510.4813 | 0 | 3 | 3 | -252.2413 | -507.4813 | -98.82% | -99.41% | YES | Below variance threshold. | Actual units were lower than imputed units because this is a project-based repair program. In 2024, PG&E did not identify any underground repair projects. | Under | On-Target | On-Target | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. This program supports major project underground work. Completion of work is dependent on the scope of the project.
628 | Expense | Electric Distribution | KB | E Dist Maint UG | KBP | UG EXP Projects | Underground | DUNGD-C004: Planned Major Projects | Ex 4, Ch 11 | Yes | N/A | N/A | 788.7754 | 794.9997 | 1583.7752 | 1.0978 | 0.14433 | 1.2422 | -794.8554 | -1582.533 | -99.98% | -99.92% | N/A | N/A | # of Locations | 255.24 | 255.2413 | 510.4813 | 0 | 3 | 3 | -252.2413 | -507.4813 | -98.82% | -99.41% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
629 | Expense | Electric Distribution | KB | E Dist Maint UG | KB# | Not assigned | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 11 | No | On-going | Annual | 757.6537 | 763.6324 | 1521.2861 | 0 | -63.9728 | -63.9728 | -827.6052 | -1585.2589 | -108.4% | -104.2% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
630 | Expense | Electric Distribution | KC | E Dist Maint Network | KCA | Ntwk Equip Correct Maint NWTX | SRM Total | SRM Total | Ex 4, Ch 14 | No | On-going | Annual | 449.8004 | 460.8723 | 910.6727 | 39.5717 | 322.0862 | 361.6578 | -138.7862 | -549.0149 | -30.11% | -60.29% | NO | NO | # of Locations | 80 | 80 | 160 | 17 | 63 | 80 | -17 | -80 | -21.25% | -50% | YES | Below variance threshold. | Actual units were lower than imputed units because this is demand-driven work and fluctuates year over year because there is a wide range of repairs covered in this MAT code and a varying number of repairs per year. Through 2024, fewer tags have been generated from abnormal operating conditions than expected. | Under | On-Target | On-Target | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The purpose of this program is a continuing effort to make repairs on network equipment e.g., transformers and protectors.
631 | Expense | Electric Distribution | KC | E Dist Maint Network | KCA | Ntwk Equip Correct Maint NWTX | Distribution Network | DNTWK-C002: Maintenance and Corrective Work | Ex 4, Ch 14 | Yes | N/A | N/A | 449.8004 | 460.8723 | 910.6727 | 39.5717 | 322.0862 | 361.6578 | -138.7862 | -549.0149 | -30.11% | -60.29% | N/A | N/A | # locations | 80 | 80 | 160 | 17 | 63 | 80 | -17 | -80 | -21.25% | -50% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
632 | Expense | Electric Distribution | KC | E Dist Maint Network | KCB | Ntwk Oil Repl & 60Day F/U NWTX | SRM Total | SRM Total | Ex 4, Ch 14 | No | On-going | Annual | 33.8891 | 34.7233 | 68.6123 | 5.2245 | 16.0789 | 21.3033 | -18.6444 | -47.309 | -53.69% | -68.95% | NO | NO | # of Locations | 25 | 25 | 50 | 8 | 7 | 15 | -18 | -35 | -72% | -70% | YES | Below variance threshold. | Actual units were lower than imputed units because fewer than expected transformers were identified as needing oil replacement as a result of dissolved gas analysis (DGA) testing. | Under | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E’s 2023 GRC period. The purpose of this program is a continuing effort to replace oil in network transformers based on dissolved gas analysis, and to perform 60-day follow-up re-torque requirement in order to maintain a safe and reliable distribution network system.
633 | Expense | Electric Distribution | KC | E Dist Maint Network | KCB | Ntwk Oil Repl & 60Day F/U NWTX | Distribution Network | DNTWK-C002: Maintenance and Corrective Work | Ex 4, Ch 14 | Yes | N/A | N/A | 33.8891 | 34.7233 | 68.6123 | 5.2245 | 16.0789 | 21.3033 | -18.6444 | -47.309 | -53.69% | -68.95% | N/A | N/A | # locations | 25 | 25 | 50 | 8 | 7 | 15 | -18 | -35 | -72% | -70% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
634 | Expense | Electric Distribution | KC | E Dist Maint Network | KCC | Ntwk Vault Correct Maint NWTX | SRM Total | SRM Total | Ex 4, Ch 14 | No | On-going | Annual | 134.5293 | 137.8408 | 272.3701 | 7.6588 | 310.5539 | 318.2127 | 172.7131 | 45.8426 | 125.3% | 16.83% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
635 | Expense | Electric Distribution | KC | E Dist Maint Network | KCC | Ntwk Vault Correct Maint NWTX | Distribution Network | DNTWK-C002: Maintenance and Corrective Work | Ex 4, Ch 14 | Yes | N/A | N/A | 134.5293 | 137.8408 | 272.3701 | 7.6588 | 310.5539 | 318.2127 | 172.7131 | 45.8426 | 125.3% | 16.83% | N/A | N/A | N/A | 7658.82 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
636 | Expense | Electric Distribution | KC | E Dist Maint Network | KCD | Ntwk Xfmr PrevMaint/Retst NWTX | SRM Total | SRM Total | Ex 4, Ch 14 | No | On-going | Annual | 2808.6851 | 2877.8214 | 5686.5065 | 4486.7169 | 4056.2771 | 8542.994 | 1178.4557 | 2856.4875 | 40.95% | 50.23% | NO | NO | Transformer Oil Tests | 3600 | 3600 | 7200 | 1363 | 1403 | 2766 | -2197 | -4434 | -61.03% | -61.58% | YES | Below variance threshold. | PG&E changed the unit of measure for this MAT in 2023 from (1) the number of chambers for which we drew oil samples from, to (2) the number of transformers maintained. The 2023 GRC unit forecast was based on the number of chambers that each network transformer can have; network transformers can have up to 3 chambers. The imputed and recorded + forecast units are not comparable. | Under | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E’s 2023 GRC period. The purpose of this program is a continuing effort to perform preventive maintenance on network transformers to maintain a safe and reliable distribution network system.
637 | Expense | Electric Distribution | KC | E Dist Maint Network | KCD | Ntwk Xfmr PrevMaint/Retst NWTX | Distribution Network | DNTWK-C002: Maintenance and Corrective Work | Ex 4, Ch 14 | Yes | N/A | N/A | 2808.6851 | 2877.8214 | 5686.5065 | 4486.7169 | 4056.2771 | 8542.994 | 1178.4557 | 2856.4875 | 40.95% | 50.23% | N/A | N/A | # Transformers | 3600 | 3600 | 7200 | 1363 | 1403 | 2766 | -2197 | -4434 | -61.03% | -61.58% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
638 | Expense | Electric Distribution | KC | E Dist Maint Network | KCE | Ntwk Protector Prev Maint NWTX | SRM Total | SRM Total | Ex 4, Ch 14 | No | On-going | Annual | 718.8591 | 736.5539 | 1455.413 | 1428.0841 | 1615.0506 | 3043.1347 | 878.4967 | 1587.7217 | 119.3% | 109.1% | NO | NO | Network Protectors | 402 | 402 | 804 | 374 | 474 | 848 | 72 | 44 | 17.91% | 5.473% | NO | Below variance threshold. | Below variance threshold. | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
639 | Expense | Electric Distribution | KC | E Dist Maint Network | KCE | Ntwk Protector Prev Maint NWTX | Distribution Network | DNTWK-C002: Maintenance and Corrective Work | Ex 4, Ch 14 | Yes | N/A | N/A | 718.8591 | 736.5539 | 1455.413 | 1428.0841 | 1615.0506 | 3043.1347 | 878.4967 | 1587.7217 | 119.3% | 109.1% | N/A | N/A | # network protectors | 402 | 402 | 804 | 374 | 474 | 848 | 72 | 44 | 17.91% | 5.473% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
640 | Expense | Electric Distribution | KC | E Dist Maint Network | KCF | Fiber/SCADA Comm Repr NWTX | SRM Total | SRM Total | Ex 4, Ch 14 | No | On-going | Annual | 1011.5374 | 1036.4366 | 2047.974 | 185.5123 | 1184.3166 | 1369.8289 | 147.88 | -678.1451 | 14.27% | -33.11% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
641 | Expense | Electric Distribution | KC | E Dist Maint Network | KCF | Fiber/SCADA Comm Repr NWTX | Distribution Network | DNTWK-C002: Maintenance and Corrective Work | Ex 4, Ch 14 | Yes | N/A | N/A | 1011.5374 | 1036.4366 | 2047.974 | 185.5123 | 1184.3166 | 1369.8289 | 147.88 | -678.1451 | 14.27% | -33.11% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
642 | Expense | Electric Distribution | OM | Operational Management | N/A | Not assigned | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 22 | No | On-going | Annual | 19950.3775 | 20477.3794 | 40427.757 | 12752.99 | 20920.0181 | 33673.0081 | 442.6387 | -6754.7488 | 2.162% | -16.71% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
643 | Expense | Electric Distribution | WF | Wildfire Mitigation | WFC | Cameras | SRM Total | SRM Total | Ex 4, Ch 4.1 | No | On-going | Annual | 0 | 0 | 0 | 12340.4302 | 11018.4514 | 23358.8816 | 11018.4514 | 23358.8816 | 100% | 100% | YES | YES | # of wildfire cameras | 0 | 0 | 0 | 10 | 25 | 35 | 25 | 35 | 100% | 100% | YES | Program expenses exceeded imputed regulatory values because costs for this program were imputed in MAT AB6. Actual expenses for cameras recorded in MAT WFC are within the variance threshold, although they exceeded imputed regulatory values due to 1) the implementation of artificial intelligence (AI) detection on the cameras which was not forecast in the 2023 GRC, and 2) the installation of more units than forecasted. See mitigation WLDFR-M07D in AB6 for the imputed amount for this program. | Actual units were higher than imputed units because 1) wildfire cameras were forecasted in AB6 and recorded in WFC, and 2) PG&E installed more units than forecasted. There were 10 cameras forecasted in AB6 and 25 completed in WFC in 2024. PG&E completed more units than forecasted because the wildfire risk team, working with CAL FIRE, identified numerous locations where additional cameras would reduce overall risk through enhanced situational awareness. See mitigation WLDFR-M07D in AB6 for the imputed units for this program. | Over | On-Target | Over | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. This program supports the installation, operation and maintenance of wildfire cameras. Scope and Budget forecast status are shown as over because for the remainder of the GRC cycle, costs and units will show over for MAT WFC because imputed amounts are captured in AB6. This program is otherwise proceeding as planned.
644 | Expense | Electric Distribution | WF | Wildfire Mitigation | WFC | Cameras | Wildfire | WLDFR-M07D: Situational Awareness and Forecasting Initiatives - Cameras | Ex 4, Ch 4.1 | No | N/A | N/A | 0 | 0 | 0 | 12340.4302 | 11018.4514 | 23358.8816 | 11018.4514 | 23358.8816 | 100% | 100% | N/A | N/A | # of wildfire cameras | 0 | 0 | 0 | 10 | 25 | 35 | 25 | 35 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
645 | Expense | Electric Distribution | WF | Wildfire Mitigation | WFM | Other Wildfire Support-Exp | SRM Total | SRM Total | Ex 4, Ch 4.1 Ex 4, Ch 5 | No | On-going | Annual | 0 | 0 | 0 | 8309.7448 | 9432.6035 | 17742.3483 | 9432.6035 | 17742.3483 | 100% | 100% | NO | YES | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Program expenses exceeded imputed regulatory values because costs for this program were imputed in MAT AB6. Actual expenses for Other Wildfire Support are recorded in MAT WFM, and the difference between the imputed regulatory value and actual expenses is below the variance threshold. See mitigation EPNDR-C001, WLDFR-M07E, WLDFR-M071, WLDFR-M07J and WLDFR-M07K in AB6 for the imputed amount for this program. | N/A | On-Target | On-Target | Over | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. This program supports PG&E's development operations, and maintenance of the fire potential index and other models that support PSPS, EPSS, and wildfire mitigations. Budget status is shown as over because imputed amounts are captured in AB6. This program is otherwise proceeding as planned.
646 | Expense | Electric Distribution | WF | Wildfire Mitigation | WFM | Other Wildfire Support-Exp | Emergency Preparedness & Response | EPNDR-C001: Situational Awareness and Forecasting Initiatives - SOPP Improvements | Ex 4, Ch 4.1 Ex 4, Ch 5 | Yes | N/A | N/A | 0 | 0 | 0 | 1880.6446 | 0 | 1880.6446 | 0 | 1880.6446 | 0% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
647 | Expense | Electric Distribution | WF | Wildfire Mitigation | WFM | Other Wildfire Support-Exp | Wildfire | WLDFR-M07E: Situational Awareness and Forecasting Initiatives - Satellite Fire Detection | Ex 4, Ch 4.1 Ex 4, Ch 5 | Yes | N/A | N/A | 0 | 0 | 0 | 89.732 | 187.3436 | 277.0756 | 187.3436 | 277.0756 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
648 | Expense | Electric Distribution | WF | Wildfire Mitigation | WFM | Other Wildfire Support-Exp | Wildfire | WLDFR-M07I: Situational Awareness and Forecasting Initiatives - Advanced Fire Modeling | Ex 4, Ch 4.1 Ex 4, Ch 5 | Yes | N/A | N/A | 0 | 0 | 0 | 6044.7454 | 6996.5688 | 13041.3143 | 6996.5688 | 13041.3143 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
649 | Expense | Electric Distribution | WF | Wildfire Mitigation | WFM | Other Wildfire Support-Exp | Wildfire | WLDFR-M07J: Situational Awareness and Forecasting Initiatives - Meteorology | Ex 4, Ch 4.1 Ex 4, Ch 5 | Yes | N/A | N/A | 0 | 0 | 0 | 153.6489 | 2139.0933 | 2292.7423 | 2139.0933 | 2292.7423 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
650 | Expense | Electric Distribution | WF | Wildfire Mitigation | WFM | Other Wildfire Support-Exp | Wildfire | WLDFR-M07K: Situational Awareness and Forecasting Initiatives - Fire Potential Index | Ex 4, Ch 4.1 Ex 4, Ch 5 | Yes | N/A | N/A | 0 | 0 | 0 | 140.9738 | 109.5977 | 250.5715 | 109.5977 | 250.5715 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
651 | Expense | Electric Distribution | WF | Wildfire Mitigation | WFM | Other Wildfire Support-Exp | SRM (NON-RAMP) | SRM (NON-RAMP) | Ex 4, Ch 4.1 Ex 4, Ch 5 | Yes | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
652 | Expense | Electric Distribution | WF | Wildfire Mitigation | WFN | PSPS Non-Event Expense | SRM Total | SRM Total | Ex 4, Ch 4.2 | No | On-going | Annual | 0 | 0 | 0 | 19942.8022 | 28489.808 | 48432.6101 | 28489.808 | 48432.6101 | 100% | 100% | YES | YES | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Program expenses exceeded imputed regulatory values because costs for this program were imputed in MAT AB6 and imputed and recorded to MAT IG#. When comparing to MAT AB6, and IG#, PSPS non-event actual expenses were below forecast due to: 1) lower than forecast costs for exclusive use helicopter contracts, and 2) lower than forecast costs for Community Resource Center (CRC) preparedness. See mitigation WLDFR-M006 in AB6 and IG# for the imputed amount for this program as well as some recorded amounts. The underspend in PSPS was offset by additional spend in Non-RAMP work in this program. | N/A | On-Target | On-Target | Over | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The purpose of this program is to prepare for PSPS events and improve the PSPS program when activated. Budget status is shown as over, even though actual expenses were under, because there are no imputed amounts in WFN, they are in AB6 and IG#. This program is otherwise proceeding as planned.
653 | Expense | Electric Distribution | WF | Wildfire Mitigation | WFN | PSPS Non-Event Expense | Emergency Preparedness & Response | EPNDR-C005: EP&R Field Operations | Ex 4, Ch 5 | Yes | N/A | N/A | 0 | 0 | 0 | 203.512 | 0 | 203.512 | 0 | 203.512 | 0% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
654 | Expense | Electric Distribution | WF | Wildfire Mitigation | WFN | PSPS Non-Event Expense | Emergency Preparedness & Response | EPNDR-C006: EP&R Distribution Support Headcount | Ex 4, Ch 5 | Yes | N/A | N/A | 0 | 0 | 0 | 1525.7864 | 6861.7804 | 8387.5668 | 6861.7804 | 8387.5668 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
655 | Expense | Electric Distribution | WF | Wildfire Mitigation | WFN | PSPS Non-Event Expense | Wildfire | WLDFR-M006: PSPS Reduction Initiatives | Ex 4, Ch 4.2 | Yes | N/A | N/A | 0 | 0 | 0 | 16155.7024 | 19661.0999 | 35816.8023 | 19661.0999 | 35816.8023 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
656 | Expense | Electric Distribution | WF | Wildfire Mitigation | WFN | PSPS Non-Event Expense | SRM (NON-RAMP) | SRM (NON-RAMP) | Ex 4, Ch 4.2 | Yes | N/A | N/A | 0 | 0 | 0 | 2057.8014 | 1966.9277 | 4024.729 | 1966.9277 | 4024.729 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
657 | Expense | Electric Distribution | WF | Wildfire Mitigation | WFP | PSPS Event Expense | SRM Total | SRM Total | Ex 4, Ch 4.2 | No | On-going | Annual | 0 | 0 | 0 | 5556.1937 | 24510.8988 | 30067.0925 | 24510.8988 | 30067.0925 | 100% | 100% | YES | YES | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Program expenses exceeded imputed regulatory values because costs for this program were imputed in MAT AB6. Actual expenses for active PSPS events are recorded in MAT WFP and were below imputed regulatory values in AB6 because PSPS events that occurred in 2024 were small in geographic scope and impacted fewer customers. See mitigation WLDFR-M005 in AB6 for the imputed amount for this program. | N/A | On-Target | On-Target | Over | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. This program supports PSPS and the spend is dependent on weather. This programs budget is presented as over, even though the actuals were under, because there were no imputed amounts in WFP, they were in AB6.
658 | Expense | Electric Distribution | WF | Wildfire Mitigation | WFP | PSPS Event Expense | Wildfire | WLDFR-M005: Public Safety Power Shutoff - PSPS Event (Distribution) | Ex 4, Ch 4.2 | Yes | N/A | N/A | 0 | 0 | 0 | 5455.4428 | 23955.7118 | 29411.1546 | 23955.7118 | 29411.1546 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
659 | Expense | Electric Distribution | WF | Wildfire Mitigation | WFP | PSPS Event Expense | Wildfire | POST-GRC: Post-GRC Mitigation | Ex 4, Ch 4.2 | Yes | N/A | N/A | 0 | 0 | 0 | 100.7509 | 555.187 | 655.9379 | 555.187 | 655.9379 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
660 | Expense | Electric Distribution | WF | Wildfire Mitigation | WFS | Safety Infra Protect Team(SIPT) | SRM Total | SRM Total | Ex 4, Ch 4.1 | No | On-going | Annual | 0 | 0 | 0 | 19869.7115 | 20667.55 | 40537.2614 | 20667.55 | 40537.2614 | 100% | 100% | YES | YES | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Program expenses exceeded imputed regulatory values because costs for this program were imputed in MAT AB6. Actual expenses for SIPT are recorded in MAT WFS and were below imputed regulatory values due to: 1) staffing constraints causing labor costs to be lower than forecast, 2) equipment delivery delays, and 3) fewer catastrophic events requiring deployment of the SIPT. See mitigation WLDFR-M008 in AB6 for the imputed amount for this program. | N/A | On-Target | On-Target | Over | Proceeding as Planned | This program’s work is ongoing. This program supports PG&E crews performing work in high fire risk areas. This programs budget is presented as over, even though the actuals were under, because there were no imputed amounts in WFS, they were in AB6. This program is otherwise proceeding as planned.
661 | Expense | Electric Distribution | WF | Wildfire Mitigation | WFS | Safety Infra Protect Team(SIPT) | Wildfire | WLDFR-M008: Safety and Infrastructure Protection Teams | Ex 4, Ch 4.1 | No | N/A | N/A | 0 | 0 | 0 | 19869.7115 | 20667.55 | 40537.2614 | 20667.55 | 40537.2614 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
662 | Expense | Electric Distribution | WF | Wildfire Mitigation | WFW | Weather Station Maintenance | SRM Total | SRM Total | Ex 4, Ch 4.1 | No | On-going | Annual | 0 | 0 | 0 | 2468.4283 | 2914.8629 | 5383.2911 | 2914.8629 | 5383.2911 | 100% | 100% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | Over | Proceeding as Planned | This program’s work is ongoing. This program is for the maintenance of weather stations. This programs budget is presented as over, because there were no imputed amounts in WFW, they were in AB6 for WLDFR-M07B. This program is otherwise proceeding as planned.
663 | Expense | Electric Distribution | WF | Wildfire Mitigation | WFW | Weather Station Maintenance | Wildfire | WLDFR-M07B: Situational Awareness and Forecasting Initiatives - Weather Station | Ex 4, Ch 4.1 | No | N/A | N/A | 0 | 0 | 0 | 2468.4283 | 2914.8629 | 5383.2911 | 2914.8629 | 5383.2911 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
664 | O&M Expense | Nuclear Generation | AB | Misc Expense |  |  | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 5, Ch 3 | No | On-going | Annual | 0 | 0 | 0 | 339.963 | 54.2897 | 394.2527 | 54.2897 | 394.2527 | 100.0% | 100.0% | NO | NO | [12 empty] | Below variance threshold. |  | On-Target | On-Target | On-Target | Proceeding as planned | N/A
665 | O&M Expense | Nuclear Generation | BP | Manage DCPP Business |  |  | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 5, Ch 3 | No | On-going | Annual | 13681.2538 | 13985.1376 | 27666.3914 | 12752.1994 | 12306.7352 | 25058.9347 | -1678.4024 | -2607.4567 | -12% | -9.425% | NO | NO | [12 empty] | Below variance threshold. |  | On-Target | On-Target | On-Target | Proceeding as planned | N/A
666 | O&M Expense | Nuclear Generation | BQ | DCPP Loss Prevention |  |  | SRM Total | SRM Total | Ex 5, Ch 3 | No | On-going | Annual | 42009.0817 | 45540.035 | 87549.1167 | 42675.2885 | 45423.0776 | 88098.3661 | -116.9574 | 549.2494 | -0.2568% | 0.6274% | NO | NO | [12 empty] | Below variance threshold. |  | On-Target | On-Target | On-Target | Proceeding as planned | N/A
667 | O&M Expense | Nuclear Generation | BQ | DCPP Loss Prevention |  |  | Core Damaging Event | NCORE-C4 - Security from External and Internal Threats, and Emergency Response | Ex 5, Ch 3 | Yes | On-going | Annual | 37808.1735 | 40986.0315 | 78794.205 | 38407.7596 | 40880.7699 | 79288.5295 | -105.2616 | 494.3245 | -0.2568% | 0.6274% | NO | NO | [12 empty] | Below variance threshold. |  | On-Target | On-Target | On-Target | Proceeding as planned | N/A
668 | O&M Expense | Nuclear Generation | BQ | DCPP Loss Prevention |  |  | Extended Shutdown | NSHUT-C4 - Security from External and Internal Threats, and Emergency Response | Ex 5, Ch 3 | Yes | On-going | Annual | 4200.9082 | 4554.0035 | 8754.9117 | 4267.5288 | 4542.3078 | 8809.8366 | -11.6957 | 54.9249 | -0.2568% | 0.6274% | NO | NO | [12 empty] | Below variance threshold. |  | On-Target | On-Target | On-Target | Proceeding as planned | N/A
669 | O&M Expense | Nuclear Generation | BR | Operate DCPP Plant |  |  | SRM Total | SRM Total | Ex 5, Ch 3 | No | On-going | Annual | 76609.161 | 80901.7849 | 157510.946 | 78631.2505 | 80901.779 | 159533.0296 | -0.00592 | 2022.0836 | -7.318e-06% | 1.284% | NO | NO | [12 empty] | Below variance threshold. |  | On-Target | On-Target | On-Target | Proceeding as planned | N/A
670 | O&M Expense | Nuclear Generation | BR | Operate DCPP Plant |  |  | Core Damaging Event | NCORE-C2 - Operating the Facility Within Requirements | Ex 5, Ch 3 | Yes | On-going | Annual | 51127.47 | 53242.4465 | 104369.9165 | 46887.75 | 52894.7379 | 99782.4879 | -347.7086 | -4587.4286 | -0.6531% | -4.395% | NO | NO | [12 empty] | Below variance threshold. |  | On-Target | On-Target | On-Target | Proceeding as planned | N/A. Combined BR NSHUT-C2 & C4
671 | O&M Expense | Nuclear Generation | BR | Operate DCPP Plant |  |  | Extended Shutdown | NSHUT-C2 - Operating the Facility Within Requirements | Ex 5, Ch 3 | Yes | On-going | Annual | 5680.83 | 5915.8274 | 11596.6574 | 5209.75 | 5877.1931 | 11086.9431 | -38.6343 | -509.7143 | -0.6531% | -4.395% | NO | NO | [12 empty] | Below variance threshold. |  | On-Target | On-Target | On-Target | Proceeding as planned | N/A. Combined BR NCORE-C2 & C5
672 | O&M Expense | Nuclear Generation | BR | Operate DCPP Plant |  |  | SRM (Non-RAMP) | SRM (Non-RAMP) | Ex 5, Ch 3 | Yes | On-going | Annual | 19800.861 | 21743.511 | 41544.372 | 26533.7505 | 22129.848 | 48663.5986 | 386.337 | 7119.2265 | 1.777% | 17.14% | NO | NO | [12 empty] | Below variance threshold. |  | On-Target | On-Target | On-Target | Proceeding as planned | N/A
673 | O&M Expense | Nuclear Generation | BS | Maintain DCPP Plant Assets |  |  | SRM Total | SRM Total | Ex 5, Ch 3 | No | On-going | Annual | 91686.3425 | 91456.8399 | 183143.1825 | 97104.0566 | 91456.8512 | 188560.9078 | 0.01122 | 5417.7253 | 1.227e-05% | 2.958% | NO | NO | [12 empty] | Below variance threshold. |  | On-Target | On-Target | On-Target | Proceeding as planned | N/A
674 | O&M Expense | Nuclear Generation | BS | Maintain DCPP Plant Assets |  |  | Core Damaging Event | NCORE-C1 - Maintaining the Systems | Ex 5, Ch 3 | Yes | On-going | Annual | 74928.69 | 74760.3639 | 149689.0539 | 78745.77 | 72020.6767 | 150766.4467 | -2739.6871 | 1077.3929 | -3.665% | 0.7198% | NO | NO | [12 empty] | Below variance threshold. |  | On-Target | On-Target | On-Target | Proceeding as planned | N/A
675 | O&M Expense | Nuclear Generation | BS | Maintain DCPP Plant Assets |  |  | Extended Shutdown | NSHUT-C1 - Maintaining the Systems | Ex 5, Ch 3 | Yes | On-going | Annual | 8325.41 | 8306.7071 | 16632.1171 | 8749.53 | 8002.2974 | 16751.8274 | -304.4097 | 119.7103 | -3.665% | 0.7198% | NO | NO | [12 empty] | Below variance threshold. |  | On-Target | On-Target | On-Target | Proceeding as planned | N/A
676 | O&M Expense | Nuclear Generation | BS | Maintain DCPP Plant Assets |  |  | SRM (Non-RAMP) | SRM (Non-RAMP) | Ex 5, Ch 3 | Yes | On-going | Annual | 8432.2425 | 8389.769 | 16822.0115 | 9608.7566 | 11433.877 | 21042.6336 | 3044.108 | 4220.6221 | 36.28% | 25.09% | NO | NO | [12 empty] | Below variance threshold. |  | On-Target | On-Target | On-Target | Proceeding as planned | N/A
677 | O&M Expense | Nuclear Generation | BV | Maintain DCPP Plant Configurtn |  |  | SRM Total | SRM Total | Ex 5, Ch 3 | No | On-going | Annual | 34728.7323 | 35078.3446 | 69807.0769 | 38316.8818 | 0 | 38316.8818 | -35078.3446 | -31490.195 | -100% | -45.11% | YES | YES | [12 empty] | Below variance threshold. |  | On-Target | On-Target | On-Target | Proceeding as planned | N/A
678 | O&M Expense | Nuclear Generation | BV | Maintain DCPP Plant Configurtn |  |  | Core Damaging Event | NCORE-C3 - Plant and System Configuration Control | Ex 5, Ch 3 | Yes | On-going | Annual | 23881.59 | 24475.0001 | 48356.5901 | 31615.65 | -8010.5211 | 23605.1289 | -32485.5212 | -24751.4612 | -132.7% | -51.19% | YES | YES | [12 empty] | Below variance threshold. |  | On-Target | On-Target | On-Target | Proceeding as planned | N/A
679 | O&M Expense | Nuclear Generation | BV | Maintain DCPP Plant Configurtn |  |  | Extended Shutdown | NSHUT-C3 - Plant and System Configuration Control | Ex 5, Ch 3 | Yes | On-going | Annual | 2653.51 | 2719.4445 | 5372.9545 | 3512.85 | -890.0579 | 2622.7921 | -3609.5024 | -2750.1624 | -132.7% | -51.19% | NO | NO | [12 empty] | Below variance threshold. |  | On-Target | On-Target | On-Target | Proceeding as planned | N/A
680 | O&M Expense | Nuclear Generation | BV | Maintain DCPP Plant Configurtn |  |  | SRM (Non-RAMP) | SRM (Non-RAMP) | Ex 5, Ch 3 | Yes | On-going | Annual | 8193.6323 | 7883.9 | 16077.5323 | 3188.3818 | 8900.579 | 12088.9608 | 1016.679 | -3988.5715 | 12.9% | -24.81% | NO | NO | [12 empty] | Below variance threshold. |  | On-Target | On-Target | On-Target | Proceeding as planned | N/A
681 | O&M Expense | Nuclear Generation | IG | Manage Var Bal Acct Processes |  |  | SRM Total | SRM Total (Non-RAMP) | Ex 5, Ch 3 | No | On-going | Annual | 2716.6764 | 2744.4614 | 5461.1378 | 2776.0952 | 3243.1599 | 6019.2551 | 498.6985 | 558.1173 | 18.17% | 10.22% | NO | NO | [12 empty] | Below variance threshold. |  | On-Target | On-Target | On-Target | Proceeding as planned | N/A
682 | O&M Expense | Power Generation | AX | Maint Resv,Dams&Waterways |  |  | SRM Total | SRM Total | Ex 5, Ch 4 | No | On-going | annual | 30569.0081 | 30952.5299 | 61521.538 | 31022.5245 | 25128.2553 | 56150.7798 | -5824.2746 | -5370.7581 | -18.82% | -8.73% | NO | NO | [12 empty] | Below variance threshold. |  | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
683 | O&M Expense | Power Generation | AX | Maint Resv,Dams&Waterways |  |  | Large Uncontrolled Water Release | C1 - Dam Safety Program | Ex 5, Ch 2 | Yes | N/A | N/A | 340.989 | 11115.0535 | 11456.0425 | 1918.285 | 9023.5523 | 10941.8373 | -2091.5012 | -514.2052 | -18.82% | -4.489% | N/A | N/A | [12 empty] | N/A |  | N/A | N/A | N/A | N/A | N/A
684 | O&M Expense | Power Generation | AX | Maint Resv,Dams&Waterways |  |  | Large Uncontrolled Water Release | M1 - Internal Erosion Mitigation | Ex 5, Ch 2 | Yes | N/A | N/A | 0 | 15.4763 | 15.4763 | 580.8633 | 12.5614 | 593.4248 | -2.9148 | 577.9485 | -18.83% | 3734% | N/A | N/A | [12 empty] | N/A |  | N/A | N/A | N/A | N/A | N/A
685 | O&M Expense | Power Generation | AX | Maint Resv,Dams&Waterways |  |  | Large Uncontrolled Water Release | M2 - Spillway Remediation | Ex 5, Ch 2 | Yes | N/A | N/A | 0 | 0 | 0 | 150.2803 | 0 | 150.2803 | 0 | 150.2803 | 100.0% | 100.0% | N/A | N/A | [12 empty] | N/A |  | N/A | N/A | N/A | N/A | N/A
686 | O&M Expense | Power Generation | AX | Maint Resv,Dams&Waterways |  |  | Large Uncontrolled Water Release | M4 - LLO Refurbishment | Ex 5, Ch 2 | Yes | N/A | N/A | 8754.285 | 0 | 8754.285 | 0 | 0 | 0 | 0 | -8754.285 | 100.0% | -100% | N/A | N/A | [12 empty] | N/A |  | N/A | N/A | N/A | N/A | N/A
687 | O&M Expense | Power Generation | AX | Maint Resv,Dams&Waterways |  |  | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 5, Ch 4 | Yes | N/A | N/A | 21473.7 | 19822.0002 | 41295.7002 | 28373.0963 | 16092.1416 | 44465.2378 | -3729.8586 | 3169.5377 | -18.82% | 7.675% | NO | NO | [12 empty] | Below variance threshold. |  | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
688 | O&M Expense | Power Generation | BC | Perf Reimburs Wk for Oth |  |  | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 5, Ch 4 | No | On-going | annual | 67.1284 | 72.7294 | 139.8578 | 353.2856 | -174.9713 | 178.3143 | -247.7007 | 38.4565 | -340.6% | 27.5% | NO | NO | [12 empty] | Below variance threshold. |  | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
689 | O&M Expense | Power Generation | IG | Manage Var Bal Acct Processes |  |  | SRM Total | SRM Total | Ex 5, Ch 4 | No | On-going | annual | 0 | 26780.6091 | 26780.6091 | 0 | 31214.4464 | 31214.4464 | 4433.8372 | 4433.8372 | 16.56% | 16.56% | NO | NO | [12 empty] | Below variance threshold. |  | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
690 | O&M Expense | Power Generation | IG | Manage Var Bal Acct Processes |  |  | Large Uncontrolled Water Release | C1 - Dam Safety Program | Ex 5, Ch 2 | Yes | N/A | N/A | 497.731 | 3047.6333 | 3545.3643 | 49.358 | 3201.2612 | 3250.6192 | 153.6279 | -294.7451 | 5.041% | -8.314% | N/A | N/A | [12 empty] | N/A |  | N/A | N/A | N/A | N/A | N/A
691 | O&M Expense | Power Generation | IG | Manage Var Bal Acct Processes |  |  | Large Uncontrolled Water Release | M2 - Spillway Remediation | Ex 5, Ch 2 | Yes | N/A | N/A | 485.934 | 881.082 | 1367.016 | 1396.133 | 925.4964 | 2321.6294 | 44.4144 | 954.6134 | 5.041% | 69.83% | N/A | N/A | [12 empty] | N/A |  | N/A | N/A | N/A | N/A | N/A
692 | O&M Expense | Power Generation | IG | Manage Var Bal Acct Processes |  |  | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 5, Ch 4 | Yes | N/A | N/A | 25753.368 | 22851.8938 | 48605.2618 | 24049.68 | 27087.6887 | 51137.3687 | 4235.7949 | 2532.1069 | 18.54% | 5.21% | NO | NO | [12 empty] | Below variance threshold. |  | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
693 | O&M Expense | Power Generation | KG | Operate Hydro Generation |  |  | SRM Total | SRM Total | Ex 5, Ch 4 | No | On-going | annual | 38215.7644 | 39099.9606 | 77315.725 | 38083.8685 | 40589.7913 | 78673.6599 | 1489.8308 | 1357.9349 | 3.81% | 1.756% | NO | NO | [12 empty] | Below variance threshold. |  | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
694 | O&M Expense | Power Generation | KG | Operate Hydro Generation |  |  | Large Uncontrolled Water Release | M3 - Seismic Retrofit | Ex 5, Ch 2 | Yes | N/A | N/A | 0 | 0 | 0 | 213.4434 | 0 | 213.4434 | 0 | 213.4434 | 100.0% | 100.0% | N/A | N/A | [12 empty] | N/A |  | N/A | N/A | N/A | N/A | N/A
695 | O&M Expense | Power Generation | KG | Operate Hydro Generation |  |  | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 5, Ch 4 | Yes | N/A | N/A | 38215.7644 | 39099.9606 | 77315.725 | 37870.4251 | 40589.7913 | 78460.2165 | 1489.8308 | 1144.4914 | 3.81% | 1.48% | NO | NO | [12 empty] | Below variance threshold. |  | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
696 | O&M Expense | Power Generation | KH | Maint Hydro Generating Equip |  |  | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 5, Ch 4 | No | On-going | annual | 24467.7421 | 24988.9983 | 49456.7405 | 24223.5652 | 24234.1136 | 48457.6788 | -754.8847 | -999.0617 | -3.021% | -2.02% | NO | NO | [12 empty] | Below variance threshold. |  | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
697 | O&M Expense | Power Generation | KI | Maint Hydro Bldg,Grnd,Infrast |  |  | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 5, Ch 4 | No | On-going | annual | 15363.235 | 15586.2717 | 30949.5068 | 13579.1383 | 12155.6218 | 25734.7601 | -3430.6499 | -5214.7467 | -22.01% | -16.85% | NO | NO | [12 empty] | Below variance threshold. |  | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
698 | O&M Expense | Power Generation | KJ | License Compliance Hydro Gen |  |  | SRM Total | SRM Total | Ex 5, Ch 4 | No | On-going | annual | 25712.7587 | 25987.814 | 51700.5727 | 24591.4514 | 24475.5289 | 49066.9803 | -1512.2851 | -2633.5924 | -5.819% | -5.094% | NO | NO | [12 empty] | Below variance threshold. |  | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
699 | O&M Expense | Power Generation | KJ | License Compliance Hydro Gen |  |  | Large Uncontrolled Water Release | C1 - Dam Safety Program | Ex 5, Ch 2 | Yes | N/A | N/A | 9068.986 | 10161.2353 | 19230.2213 | 9598.3182 | 9569.9319 | 19168.2501 | -591.3034 | -61.9712 | -5.819% | -0.3223% | N/A | N/A | [12 empty] | N/A |  | N/A | N/A | N/A | N/A | N/A
700 | O&M Expense | Power Generation | KJ | License Compliance Hydro Gen |  |  | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 5, Ch 4 | Yes | N/A | N/A | 16643.772 | 15826.5787 | 32470.3507 | 14993.133 | 14905.597 | 29898.73 | -920.9817 | -2571.6207 | -5.819% | -7.92% | NO | NO | [12 empty] | Below variance threshold. |  | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
701 | O&M Expense | Power Generation | KK | Operate Fossil Generation |  |  | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 5, Ch 5 | No | On-going | annual | 0 | 15230.3476 | 15230.3476 | 0 | 15827.5756 | 15827.5756 | 597.228 | 597.228 | 3.921% | 3.921% | NO | NO | [12 empty] | Below variance threshold. |  | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
702 | O&M Expense | Power Generation | KL | Maint Fossil Generating Equip |  |  | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 5, Ch 5 | No | On-going | annual | 0 | 32144.74 | 32144.74 | 0 | 22265.4242 | 22265.4242 | -9879.3158 | -9879.3158 | -30.73% | -30.73% | NO | YES | [12 empty] | Program expenses were below imputed adopted values due to the Long-Term Service Agreement costs, which are levelized in the imputed adopted value; however, the outage work associated with these costs only occurs on a periodic basis once every 4 to 6 years depending on operating profile. No major outage tied to the Long-Term Service Agreement occurred in 2024 at either Gateway Generation Station or Colusa Generation Station. Thus, no actual costs tied to the Agreement were recorded in 2024. |  | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is a continuing effort to support costs to maintain fossil power generating station equipment.
703 | O&M Expense | Power Generation | KM | Maint Fossil Bldg,Grnd,Infrast |  |  | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 5, Ch 5 | No | On-going | annual | 0 | 3329.8516 | 3329.8516 | 0 | 2905.8143 | 2905.8143 | -424.0373 | -424.0373 | -12.73% | -12.73% | NO | NO | [12 empty] | Below variance threshold. |  | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
704 | O&M Expense | Power Generation | KQ | Operate Alternative Gen |  |  | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 5, Ch 5 | No | On-going | annual | 0 | 494.7015 | 494.7015 | 0 | 0 | 0 | -494.7015 | -494.7015 | -100% | -100% | NO | NO | [12 empty] | Below variance threshold. |  | Over | Over | Over | Emergent | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is a continuing effort to support costs to operate alternative generation sites. In 2022, PG&E transferred O&M responsibilities for the Elkhorn Battery Energy Storage Station from Electric Distribution (Exhibit 4, MWC AB) to Power Generation (Exhibit 5, MWCs KQ and KR). Since the transfer occurred after the 2023 GRC was filed, the imputed adopted amounts for MWC KQ do not reflect Power Generation's ongoing O&M costs for the facility. Starting in the 2027 GRC, the Elkhorn Battery Energy Storage Station O&M costs will be forecast in the Energy Supply Exhibit.
705 | O&M Expense | Power Generation | KR | Maint AltGen Generating Equip |  |  | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 5, Ch 5 | No | On-going | annual | 0 | 1367.03 | 1367.03 | 0 | 0 | 0 | -1367.03 | -1367.03 | -100% | -100% | NO | NO | [12 empty] | Program expenses were above imputed adopted values due to the transfer of maintenance responsibilities of the Elkhorn Battery Energy Storage System from Electric Distribution to Energy Supply in 2022. The transfer happened part-way through 2022, which was not reflected in the imputed regulatory value informed by the 2023 GRC. |  | Over | Over | Over | Emergent | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is a continuing effort to support costs to maintain alternative generation sites. In 2022, PG&E transferred O&M responsibilities for the Elkhorn Battery Energy Storage Station from Electric Distribution (Exhibit 4, MWC AB) to Power Generation (Exhibit 5, MWCs KQ and KR). Since the transfer occurred after the 2023 GRC was filed, the imputed adopted amounts for MWC KR do not reflect Power Generation's ongoing O&M costs for the facility. Starting in the 2027 GRC, the Elkhorn Battery Energy Storage Station O&M costs will be forecast in the Energy Supply Exhibit.
706 | O&M Expense | Power Generation | KS | Maint AltGen Bldg,Grnd,Infrast |  |  | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 5, Ch 5 | No | On-going | annual | 0 | 569.0329 | 569.0329 | 0 | 0 | 0 | -569.0329 | -569.0329 | -100% | -100% | NO | NO | [12 empty] | Below variance threshold. |  | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
707 | O&M Expense | Customer and Communications | EY | Change/Maint Used Elec Meter |  |  | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 6, Ch 7 | No | On-going | Annual | 896.7439 | 923.6234 | 1820.3673 | 679.9111 | 650.6686 | 1330.5797 | -272.9547 | -489.7876 | -29.55% | -26.91% | NO | NO | [12 empty] | Below variance threshold. |  | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to engage in preventive and corrective maintenance for electric meters, meter programming, meter network maintenance, and electric meter accuracy testing.
708 | O&M Expense | Customer and Communications | GM | Manage Energy Efficiency-NonBA |  |  | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 6, Ch 3 | No | On-going | Annual | 11230.9173 | 11455.663 | 22686.5804 | 8527.5417 | 7737.0723 | 16264.614 | -3718.5907 | -6421.9664 | -32.46% | -28.31% | NO | NO | [12 empty] | Below variance threshold. |  | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to perform required safety and compliance work associated with Low Income Energy Efficiency direct installation measures, including Natural Gas Appliance Testing, and to support Cooling Centers.
709 | O&M Expense | Customer and Communications | HY | Change/Maint Used Gas Meters |  |  | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 6, Ch 7 | No | On-going | Annual | 6690.7444 | 6900.7236 | 13591.468 | 4685.4992 | 4410.4963 | 9095.9955 | -2490.2272 | -4495.4725 | -36.09% | -33.08% | NO | NO | [12 empty] | Below variance threshold. |  | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to perform gas meter maintenance activities that do not result in new meter exchanges, including meter tests, minimal regulator maintenance, meter/module communication trouble shooting, and meter/module repairs.
710 | O&M Expense | Customer and Communications | IG | Manage Var Bal Acct Processes |  |  | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 6, Ch 2 & 11 | No | On-going | Annual | 35501.4463 | 36006.3272 | 71507.7735 | 35491.8939 | 32993.8424 | 68485.7363 | -3012.4848 | -3022.0372 | -8.367% | -4.226% | NO | NO | [12 empty] | Below variance threshold. |  | On-Target | On-Target | On-Target | Proceeding as planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The purpose of this program is to perform wildfire risk mitigation work that is not otherwise recovered in PG&E’s adopted revenue requirements.
711 | O&M Expense | Customer and Communications | LB | Prov Advertising Svcs |  |  | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 6, Ch 11 | No | On-going | Annual | 0 | 0 | 0 | 4070.082 | 4284.122 | 8354.204 | 4284.122 | 8354.204 | 100.0% | 100.0% | NO | NO | [12 empty] | Below variance threshold. |  | On-Target | On-Target | Over | Proceeding as planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The purpose of this program is to provide above-the-line (ATL) advertising campaigns to educate and inform the public on important safety issues; BTL costs are excluded from this report. Note: For the 2023 GRC in Exhibit (PG&E-6), Chapter 11, PG&E forecasted activities for this MWC using FERC accounts. Therefore, the 2023 and 2024 Imputed Adopted Costs are $0 because a regulatory value breakout by MWC is not available.
712 | O&M Expense | Shared Services | AB | Misc Expense |  |  | SRM Total | SRM Total | Ex 7, Ch 1 Ex 7, Ch 2 Ex 7, Ch 7 | No | On-going | Annual | 17179.8844 | 35034.6094 | 52214.4938 | 17249.7296 | 25541.5314 | 42791.261 | -9493.078 | -9423.2328 | -27.1% | -18.05% | NO | YES | [12 empty] | Program expense were below imputed regulatory values due to the work being forecast and adopted in MWC AB as a part of the 2023 GRC Final Decision, but executed in MWC TA for Aviation Services and MWC JV for Enterprise Data Management. The decision to execute the forecast work in a different MWC was made after the 2023 GRC was submitted. The Aviation Services program in MWC AB primarily represents labor and non-labor expenditures required to maintain and operate Aviation assets to support both Wildfire Mitigations and Operations & Maintenance work and is in alignment with the safety commitments made in support of stopping Wildfires. The Enterprise Data Management program in MWC AB primarily represents labor and non-labor costs required to establish data management practices that improve the quality and governance of data and drive data informed decision making. |  | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC. The purpose of this program is to provide various safety initiatives that address employees, contractors, and customers. The initiatives support mitigations for Employees Safety Incident, Motor Vehicle Safety Incident, Wildfire, and Records and Information Management risks.
713 | O&M Expense | Shared Services | AB | Misc Expense |  |  | Employee Safety Incident (EMPSI) | Corrective Action Program (EMPSI-PRGB) | Ex 7, Ch 1 | Yes | On-going | Annual | 0 | 0 | 0 | 3553.5893 | 3123.224 | 6676.8133 | 3123.224 | 6676.8133 | 100.0% | 100.0% | N/A | N/A | [12 empty] | N/A |  | N/A | N/A | N/A | N/A | N/A
714 | O&M Expense | Shared Services | AB | Misc Expense |  |  | Employee Safety Incident (EMPSI) | Employee Health & Safety Guidance, Training & Oversight (EMPSI-PRGA) | Ex 7, Ch 1 | Yes | On-going | Annual | 0 | 0 | 0 | 4110 | 510.228 | 4620.228 | 510.228 | 4620.228 | 100.0% | 100.0% | N/A | N/A | [12 empty] | N/A |  | N/A | N/A | N/A | N/A | N/A
715 | O&M Expense | Shared Services | AB | Misc Expense |  |  | Employee Safety Incident (EMPSI) | Enterprise Safety Management System (EMPSI-M01B) | Ex 7, Ch 1 | Yes | On-going | Annual | 0 | 0 | 0 | 678 | 0 | 678 | 0 | 678 | 100.0% | 100.0% | N/A | N/A | [12 empty] | N/A |  | N/A | N/A | N/A | N/A | N/A
716 | O&M Expense | Shared Services | AB | Misc Expense |  |  | Employee Safety Incident (EMPSI) | PG&E Safety Excellence Management System Implementation (EMPSI-PRGF) | Ex 7, Ch 1 | Yes | On-going | Annual | 0 | 0 | 0 | 662 | 2851.409 | 3513.409 | 2851.409 | 3513.409 | 100.0% | 100.0% | N/A | N/A | [12 empty] | N/A |  | N/A | N/A | N/A | N/A | N/A
717 | O&M Expense | Shared Services | AB | Misc Expense |  |  | Motor Vehicle Safety Incident (MTRSI) | Transportation Safety (PRGA) | Ex 7, Ch 1 | Yes | On-going | Annual | 0 | 0 | 0 | 3150 | 2697.426 | 5847.426 | 2697.426 | 5847.426 | 100.0% | 100.0% | N/A | N/A | [12 empty] | N/A |  | N/A | N/A | N/A | N/A | N/A
718 | O&M Expense | Shared Services | AB | Misc Expense |  |  | Contractor Safety Incident (CNTSI) | Contractor Pre-Qualification Program (PRGA) Contractor Safety Oversight and Compliance (PRGB) | Ex 7, Ch 1 | Yes | On-going | Annual | 0 | 0 | 0 | 0 | 4443.961 | 4443.961 | 4443.961 | 4443.961 | 100.0% | 100.0% | N/A | N/A | [12 empty] | N/A |  | N/A | N/A | N/A | N/A | N/A
719 | O&M Expense | Shared Services | AB | Misc Expense |  |  | Records and Information Management (RECIM) | Accountability Control (RECIM-C001) | Ex 7, Ch 7 | Yes | On-going | Annual | 0 | 0 | 0 | 0 | 1047.9856 | 1047.9856 | 1047.9856 | 1047.9856 | 100.0% | 100.0% | N/A | N/A | [12 empty] | N/A |  | N/A | N/A | N/A | N/A | N/A
720 | O&M Expense | Shared Services | AB | Misc Expense |  |  | Records and Information Management (RECIM) | Transparency Control (RECIM-C002) | Ex 7, Ch 7 | Yes | On-going | Annual | 0 | 0 | 0 | 0 | 971.7685 | 971.7685 | 971.7685 | 971.7685 | 100.0% | 100.0% | N/A | N/A | [12 empty] | N/A |  | N/A | N/A | N/A | N/A | N/A
721 | O&M Expense | Shared Services | AB | Misc Expense |  |  | Records and Information Management (RECIM) | Compliance Control (RECIM-C003) | Ex 7, Ch 7 | Yes | On-going | Annual | 0 | 0 | 0 | 0 | 845.7985 | 845.7985 | 845.7985 | 845.7985 | 100.0% | 100.0% | N/A | N/A | [12 empty] | N/A |  | N/A | N/A | N/A | N/A | N/A
722 | O&M Expense | Shared Services | AB | Misc Expense |  |  | Records and Information Management (RECIM) | Retention Control (RECIM-C004) | Ex 7, Ch 7 | Yes | On-going | Annual | 0 | 0 | 0 | 0 | 2129.4212 | 2129.4212 | 2129.4212 | 2129.4212 | 100.0% | 100.0% | N/A | N/A | [12 empty] | N/A |  | N/A | N/A | N/A | N/A | N/A
723 | O&M Expense | Shared Services | AB | Misc Expense |  |  | Records and Information Management (RECIM) | Protection Control (RECIM-C005) | Ex 7, Ch 7 | Yes | On-going | Annual | 0 | 0 | 0 | 0 | 1790.3083 | 1790.3083 | 1790.3083 | 1790.3083 | 100.0% | 100.0% | N/A | N/A | [12 empty] | N/A |  | N/A | N/A | N/A | N/A | N/A
724 | O&M Expense | Shared Services | AB | Misc Expense |  |  | Records and Information Management (RECIM) | Availability Control (RECIM-C006) | Ex 7, Ch 7 | Yes | On-going | Annual | 0 | 0 | 0 | 0 | 391.6714 | 391.6714 | 391.6714 | 391.6714 | 100.0% | 100.0% | N/A | N/A | [12 empty] | N/A |  | N/A | N/A | N/A | N/A | N/A
725 | O&M Expense | Shared Services | AB | Misc Expense |  |  | Records and Information Management (RECIM) | Disposition Control (RECIM-C007) | Ex 7, Ch 7 | Yes | On-going | Annual | 0 | 0 | 0 | 0 | 582.2142 | 582.2142 | 582.2142 | 582.2142 | 100.0% | 100.0% | N/A | N/A | [12 empty] | N/A |  | N/A | N/A | N/A | N/A | N/A
726 | O&M Expense | Shared Services | AB | Misc Expense |  |  | Records and Information Management (RECIM) | Integrity Control (RECIM-C008) | Ex 7, Ch 7 | Yes | On-going | Annual | 0 | 0 | 0 | 0 | 217.0071 | 217.0071 | 217.0071 | 217.0071 | 100.0% | 100.0% | N/A | N/A | [12 empty] | N/A |  | N/A | N/A | N/A | N/A | N/A
727 | O&M Expense | Shared Services | AB | Misc Expense |  |  | Records and Information Management (RECIM) | Retention Mitigation (RECIM-M004) | Ex 7, Ch 7 | Yes | On-going | Annual | 0 | 0 | 0 | 0 | 211.7143 | 211.7143 | 211.7143 | 211.7143 | 100.0% | 100.0% | N/A | N/A | [12 empty] | N/A |  | N/A | N/A | N/A | N/A | N/A
728 | O&M Expense | Shared Services | AB | Misc Expense |  |  | Records and Information Management (RECIM) | Unstructured Mitigation (RECIM-M007) | Ex 7, Ch 7 | Yes | On-going | Annual | 0 | 0 | 0 | 0 | 961.0499 | 961.0499 | 961.0499 | 961.0499 | 100.0% | 100.0% | N/A | N/A | [12 empty] | N/A |  | N/A | N/A | N/A | N/A | N/A
729 | O&M Expense | Shared Services | AB | Misc Expense |  |  | Records and Information Management (RECIM) | Integrity Mitigation (RECIM-M011) | Ex 7, Ch 7 | Yes | On-going | Annual | 0 | 0 | 0 | 0 | 339.9075 | 339.9075 | 339.9075 | 339.9075 | 100.0% | 100.0% | N/A | N/A | [12 empty] | N/A |  | N/A | N/A | N/A | N/A | N/A
730 | O&M Expense | Shared Services | AB | Misc Expense |  |  | Records and Information Management (RECIM) | Structured Mitigation (RECIM-M013) | Ex 7, Ch 7 | Yes | On-going | Annual | 0 | 0 | 0 | 0 | 542.46 | 542.46 | 542.46 | 542.46 | 100.0% | 100.0% | N/A | N/A | [12 empty] | N/A |  | N/A | N/A | N/A | N/A | N/A
731 | O&M Expense | Shared Services | AB | Misc Expense |  |  | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 7, Ch 1 Ex 7, Ch 2 Ex 7, Ch 7 | No | On-going | Annual | 0 | 0 | 0 | 5096.1403 | 0.8131 | 5096.9534 | 0.8131 | 5096.9534 | 100.0% | 100.0% | N/A | N/A | [12 empty] | N/A |  | N/A | N/A | N/A | N/A | N/A
732 | O&M Expense | Shared Services | AK | Manage Environmental Oper |  |  | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 7, Ch 6 | No | On-going | Annual | 0 | 0 | 0 | 519.603 | 803.1103 | 1322.7133 | 803.1103 | 1322.7133 | 100.0% | 100.0% | NO | NO | [12 empty] | Below threshold variance. |  | On-Target | On-Target | On-Target | Proceeding as planned | N/A
733 | O&M Expense | Shared Services | BI | Maint Buildings |  |  | SRM Total | SRM Total | Ex 7, Ch 5 | No | On-going | Annual | 6005.6381 | 6122.2379 | 12127.8761 | 690.5606 | 2643.6611 | 3334.2217 | -3478.5769 | -8793.6544 | -56.82% | -72.51% | NO | NO | [12 empty] | Below threshold variance. |  | On-Target | On-Target | On-Target | Proceeding as planned | N/A
734 | O&M Expense | Shared Services | BI | Maint Buildings |  |  | Real Estate and Facilities Failure (REFFL) | Service Center Optimization (REFFL-C002) | Ex 7, Ch 5 | Yes | On-going | Annual | 0 | 0 | 0 | 413.8151 | 0 | 413.8151 | 0 | 413.8151 | 100.0% | 100.0% | N/A | N/A | [12 empty] | N/A |  | N/A | N/A | N/A | N/A | N/A
735 | O&M Expense | Shared Services | BI | Maint Buildings |  |  | Real Estate and Facilities Failure (REFFL) | Facilities Mgmt and Prevent Maint Prgm (REFFL-C004) | Ex 7, Ch 5 | Yes | On-going | Annual | 0 | 0 | 0 | 167.5727 | 1397.0154 | 1564.5881 | 1397.0154 | 1564.5881 | 100.0% | 100.0% | N/A | N/A | [12 empty] | N/A |  | N/A | N/A | N/A | N/A | N/A
736 | O&M Expense | Shared Services | BI | Maint Buildings |  |  | Real Estate and Facilities Failure (REFFL) | Renovate / Relocate Facilities Other than SFGO (REFFL-M006) | Ex 7, Ch 5 | Yes | On-going | Annual | 0 | 0 | 0 | 323.625 | 0 | 323.625 | 0 | 323.625 | 100.0% | 100.0% | N/A | N/A | [12 empty] | N/A |  | N/A | N/A | N/A | N/A | N/A
737 | O&M Expense | Shared Services | BI | Maint Buildings |  |  | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 7, Ch 5 | No | On-going | Annual | 0 | 0 | 0 | -214.4522 | 1246.6457 | 1032.1935 | 1246.6457 | 1032.1935 | 100.0% | 100.0% | N/A | N/A | [12 empty] | N/A |  | N/A | N/A | N/A | N/A | N/A
738 | O&M Expense | Shared Services | CR | Mnge Waste Disp & Transp |  |  | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 7, Ch 6 | No | On-going | Annual | 2367.9516 | 2351.1881 | 4719.1396 | 2472.6187 | 3377.0085 | 5849.6272 | 1025.8204 | 1130.4875 | 43.63% | 23.96% | NO | NO | [12 empty] | Below threshold variance. |  | On-Target | On-Target | On-Target | Proceeding as planned | N/A
739 | O&M Expense | Shared Services | EP | Manage Property & Bldgs |  |  | SRM Total | SRM Total | Ex 7, Ch 5 | No | On-going | Annual | 97560.1424 | 99454.2781 | 197014.4205 | 120592.7706 | 198432.192 | 319024.9626 | 98977.9139 | 122010.542 | 99.52% | 61.93% | YES | YES | [12 empty] | Program expenses exceeded imputed regulatory values primarily due to required facilities maintenance work driven by an aging portfolio of facilities; escalation of utilities higher than inflation; and increases in planned headcount to support company operations as part of CRESS organization transformation which included the addition of the Site Owner Program. |  | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC. The purpose of this program is to address operations and maintenance of facilities and shared conference centers to optimize the life of facilities, address safety issues, and improve operations and reliability of facility assets and related equipment.
740 | O&M Expense | Shared Services | EP | Manage Property & Bldgs |  |  | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 7, Ch 5 | No | On-going | Annual | 0 | 0 | 0 | 119954.7123 | 198432.192 | 318386.9043 | 198432.192 | 318386.9043 | 100.0% | 100.0% | N/A | N/A | [12 empty] | N/A |  | N/A | N/A | N/A | N/A | N/A
741 | O&M Expense | Shared Services | EP | Manage Property & Bldgs |  |  | Real Estate and Facilities Failure (REFFL) | Renovate / Relocate Facilities Other than SFGO (REFFL-M006) | Ex 7, Ch 5 | Yes | On-going | Annual | 0 | 0 | 0 | 638.0583 | 0 | 638.0583 | 0 | 638.0583 | 100.0% | 100.0% | N/A | N/A | [12 empty] | N/A |  | N/A | N/A | N/A | N/A | N/A
742 | O&M Expense | Shared Services | FL | Safety Engineering & OSHA Cmpl |  |  | SRM Total | SRM Total | Ex 7, Ch 1 | No | On-going | Annual | 18980.1136 | 19554.9644 | 38535.078 | 4614.2332 | 5410.9301 | 10025.1633 | -14144.0343 | -28509.9147 | -72.33% | -73.98% | YES | YES | [12 empty] | Program expense were below imputed regulatory values due to the work being forecast and adopted in MWC FL as a part of the 2023 GRC Final Decision, but executed in MWC OS. The decision to execute the forecast work in a different MWC was made after the 2023 GRC was submitted. This program primarily represents the development and deployment of the Regional Safety Program and is in alignment with the safety commitments made following the Plan of Reorganization. |  | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC. The purpose of this program is to provide various safety initiatives that address both employees and contractors. The initiatives support mitigations for Employees Safety Incident, Contractor Safety Incident, and Motor Vehicle Safety Incident risks.
743 | O&M Expense | Shared Services | FL | Safety Engineering & OSHA Cmpl |  |  | Contractor Safety Incident (CNTSI) | Contractor Safety Oversight and Compliance (PRGB) | Ex 7, Ch 1 | Yes | On-going | Annual | 0 | 0 | 0 | 1200 | 2335.538 | 3535.538 | 2335.538 | 3535.538 | 100.0% | 100.0% | N/A | N/A | [12 empty] | N/A |  | N/A | N/A | N/A | N/A | N/A
744 | O&M Expense | Shared Services | FL | Safety Engineering & OSHA Cmpl |  |  | Contractor Safety Incident (CNTSI) | Contractor Pre-Qualification Program (PRGA) | Ex 7, Ch 1 | Yes | On-going | Annual | 0 | 0 | 0 | 125 | 2335.538 | 2460.538 | 2335.538 | 2460.538 | 100.0% | 100.0% | N/A | N/A | [12 empty] | N/A |  | N/A | N/A | N/A | N/A | N/A
745 | O&M Expense | Shared Services | FL | Safety Engineering & OSHA Cmpl |  |  | Employee Safety Incident (EMPSI) | Employee Health & Safety Guidance, Training & Oversight (EMPSI-PRGA) | Ex 7, Ch 1 | Yes | On-going | Annual | 0 | 0 | 0 | 419.75 | 0 | 419.75 | 0 | 419.75 | 100.0% | 100.0% | N/A | N/A | [12 empty] | N/A |  | N/A | N/A | N/A | N/A | N/A
746 | O&M Expense | Shared Services | FL | Safety Engineering & OSHA Cmpl |  |  | Employee Safety Incident (EMPSI) | SIF Prevention Program and Field Oversight (PRGC) | Ex 7, Ch 1 | Yes | On-going | Annual | 0 | 0 | 0 | 2304.4332 | 464.4626 | 2768.8958 | 464.4626 | 2768.8958 | 100.0% | 100.0% | N/A | N/A | [12 empty] | N/A |  | N/A | N/A | N/A | N/A | N/A
747 | O&M Expense | Shared Services | FL | Safety Engineering & OSHA Cmpl |  |  | Motor Vehicle Safety Incident (MVSI) | Transportation Safety (PRGA) | Ex 7, Ch 1 | Yes | On-going | Annual | 0 | 0 | 0 | 565 | 91.6233 | 656.6233 | 91.6233 | 656.6233 | 100.0% | 100.0% | N/A | N/A | [12 empty] | N/A |  | N/A | N/A | N/A | N/A | N/A
748 | O&M Expense | Shared Services | FL | Safety Engineering & OSHA Cmpl |  |  | Employee Safety Incident (EMPSI) | Enterprise Safety Management System (EMPSI-M01B) | Ex 7, Ch 1 | Yes | On-going | Annual | 0 | 0 | 0 | 0 | 183.7682 | 183.7682 | 183.7682 | 183.7682 | 100.0% | 100.0% | N/A | N/A | [12 empty] | N/A |  | N/A | N/A | N/A | N/A | N/A
749 | O&M Expense | Shared Services | IG | Manage Var Bal Acct Processes |  |  | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 7 , Ch 5 | No | On-going | Annual | 0 | 1211.26 | 1211.26 | 1255.9957 | 2476.3541 | 3732.3497 | 1265.0941 | 2521.0897 | 104.4% | 208.1% | NO | NO | [12 empty] | Below threshold variance. |  | On-Target | On-Target | On-Target | Proceeding as planned | N/A
750 | O&M Expense | Shared Services | JH | Implement RealEstate Strategy |  |  | SRM Total | SRM Total | Ex 7 , Ch 5 | No | On-going | Annual | 6780.8434 | 6912.4939 | 13693.3373 | 8411.7406 | 4206.6558 | 12618.3963 | -2705.8381 | -1074.9409 | -39.14% | -7.85% | NO | NO | [12 empty] | Below threshold variance. |  | On-Target | On-Target | On-Target | Proceeding as planned | N/A
751 | O&M Expense | Shared Services | JH | Implement RealEstate Strategy |  |  | Real Estate and Facilities Failure (REFFL) | Facilities Mgmt and Prevent Maint Prgm (REFFL-C004) | Ex 7 , Ch 5 | Yes | On-going | Annual | 0 | 0 | 0 | 1566.7282 | 13.7862 | 1580.5145 | 13.7862 | 1580.5145 | 100.0% | 100.0% | N/A | N/A | [12 empty] | N/A |  | N/A | N/A | N/A | N/A | N/A
752 | O&M Expense | Shared Services | JH | Implement RealEstate Strategy |  |  | Real Estate and Facilities Failure (REFFL) | Renovate / Relocate Facilities Other than SFGO (REFFL-M006) | Ex 7 , Ch 5 | Yes | On-going | Annual | 0 | 0 | 0 | 791.5879 | 0 | 791.5879 | 0 | 791.5879 | 100.0% | 100.0% | N/A | N/A | [12 empty] | N/A |  | N/A | N/A | N/A | N/A | N/A
753 | O&M Expense | Shared Services | JH | Implement RealEstate Strategy |  |  | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 7 , Ch 5 | No | On-going | Annual | 0 | 0 | 0 | 6053.4244 | 4192.8695 | 10246.2939 | 4192.8695 | 10246.2939 | 100.0% | 100.0% | N/A | N/A | [12 empty] | N/A |  | N/A | N/A | N/A | N/A | N/A
754 | O&M Expense | Shared Services | JL | Procure Materials & Services |  |  | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 7, Ch 4 | No | On-going | Annual | 0 | 0 | 0 | 3930.4613 | 3001.5704 | 6932.0316 | 3001.5704 | 6932.0316 | 100.0% | 100.0% | NO | NO | [12 empty] | Below threshold variance. |  | On-Target | On-Target | On-Target | Proceeding as planned | N/A
755 | O&M Expense | Shared Services | JV | Maintain IT Apps & Infra |  |  | SRM Total | SRM Total | Ex 7, Ch 9 | No | On-going | Annual | 32806.2993 | 37893.3312 | 70699.6306 | 32417.7875 | 33765.358 | 66183.1455 | -4127.9732 | -4516.485 | -10.89% | -6.388% | NO | NO | [12 empty] | Below threshold variance. |  | On-Target | On-Target | On-Target | Proceeding as planned | N/A
756 | O&M Expense | Shared Services | JV | Maintain IT Apps & Infra |  |  | Cyber Security Incident (CYBER) | Security Intelligence and Operations Center (CYBER-C001) | Ex 7, Ch 9 | Yes | On-going | Annual | 0 | 0 | 0 | 5261.4102 | 6070.862 | 11332.2722 | 6070.862 | 11332.2722 | 100.0% | 100.0% | N/A | N/A | [12 empty] | N/A |  | N/A | N/A | N/A | N/A | N/A
757 | O&M Expense | Shared Services | JV | Maintain IT Apps & Infra |  |  | Cyber Security Incident (CYBER) | Cybersecurity Risk and Strategy (CYBER-C002) | Ex 7, Ch 9 | Yes | On-going | Annual | 0 | 0 | 0 | 9228.6591 | 9823.644 | 19052.3031 | 9823.644 | 19052.3031 | 100.0% | 100.0% | N/A | N/A | [12 empty] | N/A |  | N/A | N/A | N/A | N/A | N/A
758 | O&M Expense | Shared Services | JV | Maintain IT Apps & Infra |  |  | Cyber Security Incident (CYBER) | Cybersecurity Services (CYBER-C003) | Ex 7, Ch 9 | Yes | On-going | Annual | 0 | 0 | 0 | 13325.5324 | 17175.124 | 30500.6564 | 17175.124 | 30500.6564 | 100.0% | 100.0% | N/A | N/A | [12 empty] | N/A |  | N/A | N/A | N/A | N/A | N/A
759 | O&M Expense | Shared Services | JV | Maintain IT Apps & Infra |  |  | Cyber Security Incident (CYBER) | Communications (CYBER-C004) | Ex 7, Ch 9 | Yes | On-going | Annual | 0 | 0 | 0 | -27.9746 | -49.317 | -77.2916 | -49.317 | -77.2916 | 100.0% | 100.0% | N/A | N/A | [12 empty] | N/A |  | N/A | N/A | N/A | N/A | N/A
760 | O&M Expense | Shared Services | JV | Maintain IT Apps & Infra |  |  | Cyber Security Incident (CYBER) | Identify (CYBER-M001) | Ex 7, Ch 9 | Yes | On-going | Annual | 0 | 0 | 0 | 153.6222 | 0 | 153.6222 | 0 | 153.6222 | 100.0% | 100.0% | N/A | N/A | [12 empty] | N/A |  | N/A | N/A | N/A | N/A | N/A
761 | O&M Expense | Shared Services | JV | Maintain IT Apps & Infra |  |  | Cyber Security Incident (CYBER) | Protect (CYBER-M002) | Ex 7, Ch 9 | Yes | On-going | Annual | 0 | 0 | 0 | 3628.002 | 0 | 3628.002 | 0 | 3628.002 | 100.0% | 100.0% | N/A | N/A | [12 empty] | N/A |  | N/A | N/A | N/A | N/A | N/A
762 | O&M Expense | Shared Services | JV | Maintain IT Apps & Infra |  |  | Cyber Security Incident (CYBER) | Detect (CYBER-M003) | Ex 7, Ch 9 | Yes | On-going | Annual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100.0% | 100.0% | N/A | N/A | [12 empty] | N/A |  | N/A | N/A | N/A | N/A | N/A
763 | O&M Expense | Shared Services | JV | Maintain IT Apps & Infra |  |  | Cyber Security Incident (CYBER) | Respond (CYBER-M004) | Ex 7, Ch 9 | Yes | On-going | Annual | 0 | 0 | 0 | 32.2392 | 0 | 32.2392 | 0 | 32.2392 | 100.0% | 100.0% | N/A | N/A | [12 empty] | N/A |  | N/A | N/A | N/A | N/A | N/A
764 | O&M Expense | Shared Services | JV | Maintain IT Apps & Infra |  |  | Records and Information Management (RECIM) | Unstructured Mitigation (RECIM-M007) | Ex 7, Ch 7 | Yes | On-going | Annual | 0 | 0 | 0 | 0 | 432.5898 | 432.5898 | 432.5898 | 432.5898 | 100.0% | 100.0% | N/A | N/A | [12 empty] | N/A |  | N/A | N/A | N/A | N/A | N/A
765 | O&M Expense | Shared Services | JV | Maintain IT Apps & Infra |  |  | Records and Information Management (RECIM) | Structured Mitigation (RECIM-M013) | Ex 7, Ch 7 | Yes | On-going | Annual | 0 | 0 | 0 | 0 | 53.2081 | 53.2081 | 53.2081 | 53.2081 | 100.0% | 100.0% | N/A | N/A | [12 empty] | N/A |  | N/A | N/A | N/A | N/A | N/A
766 | O&M Expense | Shared Services | JV | Maintain IT Apps & Infra |  |  | Employee Safety Incident (EMPSI) | Employee Health & Wellness Programs (EMPSI-PRGD) | Ex 7 , Ch 1 | Yes | On-going | Annual | 0 | 0 | 0 | 0 | 259.248 | 259.248 | 259.248 | 259.248 | 100.0% | 100.0% | N/A | N/A | [12 empty] | N/A |  | N/A | N/A | N/A | N/A | N/A
767 | O&M Expense | Shared Services | JV | Maintain IT Apps & Infra |  |  | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 7, Ch 9 | No | On-going | Annual | 0 | 0 | 0 | 816.3513 | 0 | 816.3513 | 0 | 816.3513 | 100.0% | 100.0% | N/A | N/A | [12 empty] | N/A |  | N/A | N/A | N/A | N/A | N/A
768 | O&M Expense | Shared Services | KX | Prov Human Resource Svcs |  |  | SRM Total | SRM Total | Ex 7 , Ch 1 | No | On-going | Annual | 7608.8595 | 7839.3091 | 15448.1686 | 8375.5879 | 7355.2655 | 15730.8533 | -484.0437 | 282.6847 | -6.175% | 1.83% | NO | NO | [12 empty] | Below threshold variance. |  | On-Target | On-Target | On-Target | Proceeding as planned | N/A
769 | O&M Expense | Shared Services | KX | Prov Human Resource Svcs |  |  | Employee Safety Incident (EMPSI) | Employee Health & Wellness Programs (EMPSI-PRGD) | Ex 7 , Ch 1 | Yes | On-going | Annual | 0 | 0 | 0 | 8375.5879 | 7355.2655 | 15730.8533 | 7355.2655 | 15730.8533 | 100.0% | 100.0% | N/A | N/A | [12 empty] | N/A |  | N/A | N/A | N/A | N/A | N/A
770 | O&M Expense | Shared Services | KZ | Prov Risk/Security Svcs |  |  | SRM Total | SRM Total | Ex 7, Ch 9 | No | On-going | Annual | 24715.4045 | 25140.1531 | 49855.5576 | 23453.5349 | 32328.0526 | 55781.5875 | 7187.8994 | 5926.0299 | 28.59% | 11.89% | NO | YES | [12 empty] | Program expenditures were above imputed regulatory values primarily due to required increases in physical security initiatives that directly provide support to the Oakland General Office campus and surrounding community. These required investments were unknown at the time of the 2023 GRC and are attributed to efforts within the Physical Security control program (PHYSA-C001). |  | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC. While the purpose of this program is to address the ongoing development and deployment of physical security solutions, the majority of the program will focus spend on mitigation investments to reduce the Physical Attack Cross Cutter Factor risk.
771 | O&M Expense | Shared Services | KZ | Prov Risk/Security Svcs |  |  | Physical Attack (PHYSA) | Physical Security (PHYSA-C001) | Ex 7, Ch 9 | Yes | On-going | Annual | 0 | 0 | 0 | 17461.2577 | 23536.6401 | 40997.8978 | 23536.6401 | 40997.8978 | 100.0% | 100.0% | N/A | N/A | [12 empty] | N/A |  | N/A | N/A | N/A | N/A | N/A
772 | O&M Expense | Shared Services | KZ | Prov Risk/Security Svcs |  |  | Physical Attack (PHYSA) | Security Asset and Technology (PHYSA-C002) | Ex 7, Ch 9 | Yes | On-going | Annual | 0 | 0 | 0 | 1336.2551 | 1626.687 | 2962.9422 | 1626.687 | 2962.9422 | 100.0% | 100.0% | N/A | N/A | [12 empty] | N/A |  | N/A | N/A | N/A | N/A | N/A
773 | O&M Expense | Shared Services | KZ | Prov Risk/Security Svcs |  |  | Physical Attack (PHYSA) | Corporate Security Control Center (PHYSA-C003) | Ex 7, Ch 9 | Yes | On-going | Annual | 0 | 0 | 0 | 1394.9862 | 1506.4298 | 2901.416 | 1506.4298 | 2901.416 | 100.0% | 100.0% | N/A | N/A | [12 empty] | N/A |  | N/A | N/A | N/A | N/A | N/A
774 | O&M Expense | Shared Services | KZ | Prov Risk/Security Svcs |  |  | Physical Attack (PHYSA) | Investigation and Insider Threats (PHYSA-C004) | Ex 7, Ch 9 | Yes | On-going | Annual | 0 | 0 | 0 | 1657.224 | 2180.6491 | 3837.873 | 2180.6491 | 3837.873 | 100.0% | 100.0% | N/A | N/A | [12 empty] | N/A |  | N/A | N/A | N/A | N/A | N/A
775 | O&M Expense | Shared Services | KZ | Prov Risk/Security Svcs |  |  | Physical Attack (PHYSA) | Prevent (PHYSA-M001) | Ex 7, Ch 9 | Yes | On-going | Annual | 0 | 0 | 0 | 1442.2438 | 1030.3272 | 2472.571 | 1030.3272 | 2472.571 | 100.0% | 100.0% | N/A | N/A | [12 empty] | N/A |  | N/A | N/A | N/A | N/A | N/A
776 | O&M Expense | Shared Services | KZ | Prov Risk/Security Svcs |  |  | Physical Attack (PHYSA) | Detect (PHYSA-M002) | Ex 7, Ch 9 | Yes | On-going | Annual | 0 | 0 | 0 | 161.5681 | 178.2097 | 339.7778 | 178.2097 | 339.7778 | 100.0% | 100.0% | N/A | N/A | [12 empty] | N/A |  | N/A | N/A | N/A | N/A | N/A
777 | O&M Expense | Shared Services | KZ | Prov Risk/Security Svcs |  |  | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 7, Ch 9 | No | On-going | Annual | 0 | 0 | 0 | 0 | 2269.1057 | 2269.1057 | 2269.1057 | 2269.1057 | 100.0% | 100.0% | N/A | N/A | [12 empty] | N/A |  | N/A | N/A | N/A | N/A | N/A
778 | O&M Expense | Shared Services | OS | Operations Support |  |  | SRM Total | SRM Total | Ex 7 , Ch 1 | No | On-going | Annual | 0 | 0 | 0 | 12485.612 | 11740.5301 | 24226.1421 | 11740.5301 | 24226.1421 | 100.0% | 100.0% | YES | YES | [12 empty] | Program expenses exceeded imputed regulatory values due to the work being forecast and adopted in MWC FL as a part of the 2023 GRC Final Decision, but executed in MWC OS. The decision to execute the forecast work in a different MWC was made after the 2023 GRC was submitted. This program primarily represents the development and deployment of the Regional Safety Program and is in alignment with the safety commitments made following the Plan of Reorganization. |  | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC. The purpose of this program is to provide various safety initiatives that address both employees and contractors. The initiatives support mitigations for Employees Safety Incident, Contractor Safety Incident, and Motor Vehicle Safety Incident risks.
779 | O&M Expense | Shared Services | OS | Operations Support |  |  | Employee Safety Incident (EMPSI) | SIF Prevention Program and Field Oversight (PRGC) includes contract partner workforce field safety observations and compliance | Ex 7 , Ch 1 | Yes | On-going | Annual | 0 | 0 | 0 | 12485.612 | 11740.5301 | 24226.1421 | 11740.5301 | 24226.1421 | 100.0% | 100.0% | N/A | N/A | [12 empty] | N/A |  | N/A | N/A | N/A | N/A | N/A
780 | O&M Expense | Shared Services | ZC | Corporate Items |  |  | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 7 , Ch 5 | No | On-going | Annual | -63713.981 | -64979.6865 | -128693.6676 | -67971.1612 | -64015.84 | -131987.0012 | 963.8466 | -3293.3336 | -1.483% | 2.559% | NO | NO | [12 empty] | Below threshold variance. |  | On-Target | On-Target | On-Target | Proceeding as planned | N/A
781 | O&M Expense | IT | JV | Maintain IT Apps & Infra |  |  | SRM Total | SRM Total | Ex 7, Ch 8 | No | On-going | Annual | 0 | 0 | 0 | 38841.4705 | 26392.4884 | 65233.9589 | 26392.4884 | 65233.9589 | 100.0% | 100.0% | YES | YES | [12 empty] | Program expenses exceeded imputed regulatory values due to enterprise design costs for the Propel program which will upgrade, advance and improve PG&E's SAP system and related processes as well as optimizing how the system is used; various technology solutions in support of mitigating Network core assets; and incremental operations and maintenance costs in support of increased public cloud usage. |  | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC. The purpose of this program is to address the ongoing operations and maintenance of software and hardware technology assets and supporting systems, a modest percentage of the program will focus spend on supporting capital mitigation investments to improve the IT Asset Failure risk.
782 | O&M Expense | IT | JV | Maintain IT Apps & Infra |  |  | IT Asset Failure (ITAFL) | Lifecycle Obsolete and Low Health #Assets (ITAFL-M004) | Ex 7, Ch 8 | Yes | On-going | Annual | 0 | 0 | 0 | 2262.5372 | 3452.9822 | 5715.5194 | 3452.9822 | 5715.5194 | 100.0% | 100.0% | N/A | N/A | [12 empty] | N/A |  | N/A | N/A | N/A | N/A | N/A
783 | O&M Expense | IT | JV | Maintain IT Apps & Infra |  |  | IT Asset Failure (ITAFL) | Multi-Faceted Mitigations (ITAFL-M005) | Ex 7, Ch 8 | Yes | On-going | Annual | 0 | 0 | 0 | 2950.7719 | 1748.4626 | 4699.2345 | 1748.4626 | 4699.2345 | 100.0% | 100.0% | N/A | N/A | [12 empty] | N/A |  | N/A | N/A | N/A | N/A | N/A
784 | O&M Expense | IT | JV | Maintain IT Apps & Infra |  |  | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 7, Ch 8 | No | On-going | Annual | 0 | 0 | 0 | 33628.1614 | 21191.0436 | 54819.2051 | 21191.0436 | 54819.2051 | 100.0% | 100.0% | N/A | N/A | [12 empty] | N/A |  | N/A | N/A | N/A | N/A | N/A
785 | O&M Expense | Human Resources | N/A | PG&E Academy |  |  | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 8, Ch 6 | No | On-going | Annual | 40427.015 | 41244.3433 | 81671.3583 | 32021.052 | 33323.4654 | 65344.5174 | -7920.8779 | -16326.8409 | -19.2% | -19.99% | NO | NO | [12 empty] | Below variance threshold. |  | Target | Target | Target | Proceeding as Planned | N/A
(a) Consolidated tables do not include footnotes from the 2024 RSAR.
(b) Shaded cells reflect areas that were not included in the 2024 RSAR tables because they did not apply for that Functional Area.