## AllIOUs
Rule 21 Timeline Reporting Coversheet
This coversheet aggregates quarterly PG&E, SCE and SDG&E (Utilities) interconnection timeline reports from January 2021. Utilities submit quarterly reports to the Rulemaking R.17-07-007 Service List. To sign up for the service list, click the link below in row 7 and navigate to the "Subscribe" button near the top of the page. Quarterly reports will also be archived and posted at the CPUC Rule 21 Webpage (link below in cell A6).
Links to relevant information:
D.20-09-035 (see Issue 12 and Issue 8c)
Electric Rule 21 Webpage
Subscription to Rulemaking 1707007 Service List
Notes for interpreting spreadsheet: Row 9 indicates the relevant Ordering Paragraph (OP) in Decision D.20-09-035 that mandated the timeline tracking, which is specified in Row 10. An asterisk next to the OP in Row 9 indicates that customer time (i.e., time that is outside of the direct control of the Utility) is included in the tracked time. Row 10 draws directly from text in Issues 12 and 8c in D.20-09-035. The text in red is intended to increase clarity beyond the Issue 12 language in the OP. References to the Rule 21 Tariff section appears in parenthesis for ease of reference.
Project Specifics | [8 empty] | OP 22 a) | OP 22 b)* | OP 22 c) (no upgrade) | OP 22 c) (if upgrade required) | OP 22 d) (no Supplemental Review) | OP 22 d) (if Supplemental Review required) | OP 22 e) (if Electrical Independence Test required) | OP 22 f) (if Detailed Study Required)* | OP 22 g) (if Detailed Study Required)* | OP 22 h) (if Detailed Study required) | OP 22 i) | OP 22 i) | OP 22 j)* | OP 22 k) | OP 22 l)* | OP 22 m) | OP 22 m) | OP 22 n) | OP 24 o) | OP 24 p) | OP 24 q) | OP 22 r) | OP 22 s)* | OP 4 | OP 4 | OP 4
Project ID | Utility | ZIP Code | NEM / Non-NEM | Project Type (Request Type) | Project Status (Current Phase) | Technology Type | Size (kW - Net Nameplate Rating) | Cost Envelope Requested? | Time from Submission of Interconnection Request to Utility's Acknowledgement of Receipt of Interconnection Request | Time from submission of Interconnection Request to time deemed complete | Time from Interconnection Request deemed complete to completion of initial review and provision of results (if no upgrades are required) | Time from Interconnection Request deemed complete to completion of initial review and provision of results (if upgrades are required) | Time from Supplemental Review start date to completion of Supplemental Review (if no supplemental review is required) | Time from Supplemental Review start date to completion of Supplemental Review (if supplemental review required) | Time from receipt of Detailed Study Deposit (F.1.b) to perform Electrical Independence Test (Screens Q and R) and issue Electrical Independence Test (F.3.c.ii) results (if Electrical Independence Test required) | Time from Electrical Independence Test results issuance to scheduling of Detailed Study Scoping Meeting (F.3.b.i) (if Detailed Study required) | Time from Detailed Study Scoping Meeting held to issuance of draft Detailed Study Agreement (F.3.b.ii) (if Detailed Study required) | Time from Detailed Study Agreement execution to issuance of System Impact Study results/report (F.3.b.i.-ii) (if Detailed Study required) | Time from Applicable Milestone to Provision of Draft Generator Agreement (see applicable milestone in column U) | Applicable Milestone (referenced in column T) | Time from issuance of draft Generator Interconnection Agreement to date Generator Interconnection Agreement executed | Time from when the Producer completes "satisfactory compliance with the terms of all applicable agreements" to when the utility issues written Permission to Operate (F.5.b) | Total time from Utility receipt of Interconnection Request to issuance of Permission to Operate | Time from customer request to consider whether a proposed modification is material to issuance of material modification analysis/results by utility (F.3.b.v) (Note: customers are not limited in the number of material modification requests and the total number of customer material modification requests appears in column Z) | Total Number of Customer Material Modification Requests (referenced in column Y) | Time for responding to line-side taps variance requests (for Utilities that require a variance request) | Time from Utility confirmation that customer has taken all necessary steps to prepare for construction to Utility completion of design and invoice of net generation output meter | Time from date Utility issues a Service Request to date installation of net generation output meter is complete | Distribution Upgrades: Time from Utility confirmation that customer has taken all necessary steps to initiate Preliminary Design process to Utility submission of Preliminary Design to customer | Distribution Upgrades: Time from Customer Acceptance of Preliminary Design to Utility issuance of Final Design to Customer | Time from Utility scheduling commissioning test to completion of commissioning testing | (Y/N) Would Integration Capacity Analysis outdated values have lead to Interconnection Requests failing the Initial Review? | If Integration Capacity Analysis oudated values would have led to Interconnection Requests Failing the Initial Review, what cost was associated with the updates to the ICA necessitated by evaluating the outdated values? | Actual Costs Associated with processing of interconnection applications (as discussed in proposal 8s). | Notes
298676 | SDG&E | 90236 | NON-NEM | Rule 21 AES Non-Export | APPROVED | Battery Storage | 10 | No | 2 | 12 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 29 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | 385
298681 | SDG&E | 92060 | NON-NEM | Rule 21 AES Non-Export | APPROVED | Battery Storage | 10 | No | 2 | 11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 30 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | 385
299012 | SDG&E | 92028 | NON-NEM | Rule 21 AES Inadvertant -Export | APPROVED | Battery Storage | 140 | No | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 246 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | 581
299321 | SDG&E | 91935 | NON-NEM | Rule 21 AES Non-Export | APPROVED | Battery Storage | 10 | No | 1 | 8 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 27 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | 385
299457 | SDG&E | 92104 | NON-NEM | Rule 21 AES Inadvertant -Export | PENDING AHJ INSPECTION | Battery Storage | 210 | No | 1 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A
299461 | SDG&E | 91916 | NON-NEM | Rule 21 AES Non-Export | APPROVED | Battery Storage | 10 | No | 1 | 14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | 385
300610 | SDG&E | 91935 | NON-NEM | Rule 21 AES Non-Export | APPROVED | Battery Storage | 10 | No | 1 | 9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | 385
301270 | SDG&E | 92086 | NON-NEM | Rule 21 AES Non-Export | APPROVED | Battery Storage | 10 | No | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 114 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | 445
305452 | SDG&E | 92127 | NON-NEM | Rule 21 AES Non-Export | APPROVED | Battery Storage | 10 | No | 1 | 107 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 8 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | 385
305723 | SDG&E | 91935 | NON-NEM | Rule 21 AES Non-Export | APPROVED | Battery Storage | 10 | No | 1 | 19 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | 385
306201 | SDG&E | 92020 | NON-NEM | Rule 21 AES Inadvertant -Export | APPROVED | Battery Storage | 210 | No | 1 | 12 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 91 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | 649
306203 | SDG&E | 92083 | NON-NEM | Rule 21 AES Inadvertant -Export | APPROVED | Battery Storage | 210 | No | 1 | 76 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 67 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | 649
306204 | SDG&E | 91935 | NON-NEM | Rule 21 AES Non-Export | APPROVED | Battery Storage | 10 | No | 1 | 19 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | 385
306364 | SDG&E | 92128 | NON-NEM | Rule 21 AES Inadvertant -Export | APPROVED | Battery Storage | 210 | No | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 150 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | 649
309232 | SDG&E | 91935 | NON-NEM | Rule 21 AES Non-Export | APPROVED | Battery Storage | 20 | No | 1 | 46 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | 385
310361 | SDG&E | 92082 | NON-NEM | Rule 21 AES Non-Export | APPROVED | Battery Storage | 10 | No | 1 | 110 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 211 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | 385
312382 | SDG&E | 91905 | NON-NEM | Rule 21 AES Non-Export | APPROVED | Battery Storage | 7 | No | 1 | 119 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | 385
312847 | SDG&E | 92028 | NON-NEM | Rule 21 AES Inadvertant -Export | PENDING AHJ INSPECTION | Battery Storage | 232 | No | 1 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A
314158 | SDG&E | 91935 | NON-NEM | Rule 21 AES Non-Export | APPROVED | Battery Storage | 10 | No | 1 | 28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | 385
314210 | SDG&E | 92028 | NON-NEM | Rule 21 AES Non-Export | APPROVED | Battery Storage | 7 | No | 1 | 6 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 8 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | 385
314343 | SDG&E | 92126 | NON-NEM | Rule 21 AES Inadvertant -Export | APPROVED | Battery Storage | 715 | No | 1 | 36 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 170 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | 690
315244 | SDG&E | 91901 | NON-NEM | Rule 21 AES Inadvertant -Export | PENDING AHJ INSPECTION | Battery Storage | 420 | No | 1 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A
315730 | SDG&E | 92021 | NON-NEM | Rule 21 AES Non-Export | APPROVED | Battery Storage | 15 | No | 1 | 28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | 385
315839 | SDG&E | 91901 | NON-NEM | Rule 21 AES Non-Export | APPROVED | Battery Storage | 15 | No | 1 | 35 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | 385
315841 | SDG&E | 92065 | NON-NEM | Rule 21 AES Non-Export | APPROVED | Battery Storage | 10 | No | 1 | 32 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 3 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | 385
317414 | SDG&E | 92121 | NON-NEM | Rule 21 AES Inadvertant -Export | ISSUES | Battery Storage | 665 | No | 1 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A
317900 | SDG&E | 92110 | NON-NEM | Rule 21 AES Non-Export | PENDING AHJ INSPECTION | Battery Storage | 250 | No | 1 | 169 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A
318086 | SDG&E | 92029 | NON-NEM | Rule 21 AES Inadvertant -Export | PENDING AHJ INSPECTION | Battery Storage | 140 | No | 1 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A
318126 | SDG&E | 92028 | NON-NEM | Rule 21 AES Inadvertant -Export | APPROVED | Battery Storage | 210 | No | 1 | 18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 143 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | 649
318463 | SDG&E | 92028 | NON-NEM | Rule 21 AES Inadvertant -Export | ISSUES | Battery Storage | 210 | No | 1 | 16 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A
318658 | SDG&E | 92070 | NON-NEM | Rule 21 AES Non-Export | PENDING AHJ INSPECTION | Battery Storage | 10 | No | 1 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A
318852 | SDG&E | 92059 | NON-NEM | Rule 21 AES Non-Export | APPROVED | Battery Storage | 10 | No | 1 | 89 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 170 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | 385
318853 | SDG&E | 92082 | NON-NEM | Rule 21 AES Non-Export | PENDING AHJ INSPECTION | Battery Storage | 10 | No | 1 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A
319172 | SDG&E | 92078 | NON-NEM | Rule 21 AES Inadvertant -Export | PENDING AHJ INSPECTION | Battery Storage | 348 | No | 1 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A
319215 | SDG&E | 92036 | NON-NEM | Rule 21 AES Non-Export | APPROVED | Battery Storage | 10 | No | 1 | 36 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | 445
319535 | SDG&E | 92028 | NON-NEM | Rule 21 AES Inadvertant -Export | PENDING AHJ INSPECTION | Battery Storage | 140 | No | 1 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A
319561 | SDG&E | 92106 | NON-NEM | Rule 21 AES Non-Export | APPROVED | Battery Storage | 5 | No | 1 | 13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 20 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | 445
319653 | SDG&E | 92078 | NON-NEM | Rule 21 AES Inadvertant -Export | PENDING AHJ INSPECTION | Battery Storage | 210 | No | 1 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A
319668 | SDG&E | 92026 | NON-NEM | Rule 21 AES Inadvertant -Export | PENDING AHJ INSPECTION | Battery Storage | 490 | No | 1 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A
320017 | SDG&E | 92078 | NON-NEM | Rule 21 AES Export | PENDING AHJ INSPECTION | Battery Storage | 929.5 | No | 1 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A
320395 | SDG&E | 92028 | NON-NEM | Rule 21 AES Inadvertant -Export | APPROVED | Battery Storage | 420 | No | 1 | 5 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 246 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | 649
321297 | SDG&E | 91950 | NON-NEM | Rule 21 Non-Export | PENDING AHJ INSPECTION | Internal Combustion Engine | 350 | No | 1 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A
324881 | SDG&E | 92113 | NON-NEM | Rule 21 AES Non-Export | PENDING AHJ INSPECTION | Battery Storage | 60 | No | 1 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A
325005 | SDG&E | 92028 | NON-NEM | Rule 21 AES Non-Export | APPROVED | Battery Storage | 10 | No | 1 | 29 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 55 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | 385
325084 | SDG&E | 92009 | NON-NEM | Rule 21 AES Non-Export | PENDING AHJ INSPECTION | Battery Storage | 572 | No | 1 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A
328728 | SDG&E | 92154 | NON-NEM | PENDING | ISSUES | Hydroelectric Turbine | 157 | No | 1 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A
329462 | SDG&E | 91935 | NON-NEM | Rule 21 AES Non-Export | APPROVED | Battery Storage | 10 | No | 1 | 24 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 67 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | 385
330017 | SDG&E | 91950 | NON-NEM | Rule 21 AES Non-Export | PENDING FINAL REVIEW | Battery Storage | 29 | No | 1 | 98 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A
331229 | SDG&E | 92082 | NON-NEM | Rule 21 AES Non-Export | ISSUES | Battery Storage | 9 | No | 1 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A
331911 | SDG&E | 92037 | NON-NEM | PENDING | ISSUES | Battery Storage | 250 | No | 1 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A
335034 | SDG&E | 91935 | NON-NEM | Rule 21 AES Non-Export | ISSUES | Battery Storage | 8.96 | No | 1 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A
335495 | SDG&E | 92082 | NON-NEM | PENDING | ISSUES | Battery Storage | 15 | No | 1 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A
336967 | SDG&E | 92025 | NON-NEM | Rule 21 AES Inadvertant -Export | PENDING AHJ INSPECTION | Battery Storage | 174 | No | 1 | 61 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A
337936 | SDG&E | 92065 | NON-NEM | Rule 21 AES Non-Export | APPROVED | Battery Storage | 10 | No | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 33 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | 385
340932 | SDG&E | 92009 | NON-NEM | NEM-FC2 | PENDING AHJ INSPECTION | Fuel Cell | 250 | No | 1 | 44 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A
341055 | SDG&E | 92009 | NON-NEM | NEM-FC2 | PENDING AHJ INSPECTION | Fuel Cell | 350 | No | 1 | 55 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A
341094 | SDG&E | 92009 | NON-NEM | NEM-FC2 | PENDING AHJ INSPECTION | Fuel Cell | 500 | No | 1 | 55 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A
341952 | SDG&E | 91935 | NON-NEM | Rule 21 AES Non-Export | ISSUES | Battery Storage | 10 | No | 1 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A
342268 | SDG&E | 92069 | NON-NEM | Rule 21 AES Non-Export | PENDING AHJ INSPECTION | Battery Storage | 10 | No | 1 | 35 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A
343024 | SDG&E | 92069 | NON-NEM | Rule 21 AES Non-Export | ISSUES | Battery Storage | 10 | No | 1 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A
343979 | SDG&E | 91905 | NON-NEM | Rule 21 AES Non-Export | ISSUES | Battery Storage | 15 | No | 1 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A
345310 | SDG&E | 92014 | NON-NEM | PENDING | ISSUES | Battery Storage | 5 | No | 1 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A
346707 | SDG&E | 92029 | NON-NEM | Rule 21 Non-Export | APPROVED | Microturbine - Natural Gas | 65 | No | 1 | 10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | 562
347068 | SDG&E | 91935 | NON-NEM | Rule 21 AES Non-Export | ISSUES | Battery Storage | 10 | No | 1 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A
349020 | SDG&E | 92028 | NON-NEM | PENDING | INCOMPLETE | Battery Storage | 15 | No | 1 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A
349146 | SDG&E | 92067 | NON-NEM | Rule 21 AES Non-Export | ISSUES | Battery Storage | 5 | No | 1 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A
349182 | SDG&E | 92078 | NON-NEM | NEM-FC2 | ISSUES | Fuel Cell | 2000 | No | 1 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A
349310 | SDG&E | 91935 | NON-NEM | Rule 21 AES Non-Export | ISSUES | Battery Storage | 10 | No | 1 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A
350766 | SDG&E | 92028 | NON-NEM | PENDING | INCOMPLETE | Battery Storage | 5 | No | 1 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A
351071 | SDG&E | 92024 | NON-NEM | Rule 21 AES Non-Export | INCOMPLETE | Battery Storage | 20 | No | 1 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A
281969 | SDG&E | 92173 | NEM | NEMA | APPROVED | Solar PV | 151.145 | No | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 8 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
284099 | SDG&E | 92028 | NEM | NEMA | APPROVED | Solar PV | 308.119 | No | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 139 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
296922 | SDG&E | 92004 | NEM | NEMA | PENDING AHJ INSPECTION | Solar PV | 273.836 | No | 1 | 16 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
297175 | SDG&E | 92154 | NEM | NEMA | APRROVED | Solar PV | 134.816 | No | 1 | 27 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
297420 | SDG&E | 92119 | NEM | NEMA | APRROVED | Solar PV | 57.517 | No | 1 | 12 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 6 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
298210 | SDG&E | 92064 | NEM | NEMA | APPROVED | Solar PV | 86.127 | No | 1 | 12 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 93 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
304366 | SDG&E | 92121 | NEM | NEMA | APPROVED | Solar PV | 69.754 | No | 1 | 21 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 113 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
305275 | SDG&E | 92081 | NEM | NEMA | APPROVED | Solar PV | 152.373 | No | 1 | 84 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
305367 | SDG&E | 92071 | NEM | NEMA | APPROVED | Solar PV | 39.995 | No | 1 | 10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
306634 | SDG&E | 92020 | NEM | NEMA | APPROVED | Solar PV | 31.834 | No | 1 | 30 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 70 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
306694 | SDG&E | 92021 | NEM | NEMA | APPROVED | Solar PV | 40.87 | No | 1 | 29 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 6 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
306808 | SDG&E | 92064 | NEM | NEMA | PENDING AHJ INSPECTION | Battery Storage + Solar PV | 109.644 | No | 1 | 21 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
308211 | SDG&E | 92123 | NEM | NEMA | APPROVED | Solar PV | 140.907 | No | 1 | 21 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
310181 | SDG&E | 92011 | NEM | NEMA | APPROVED | Solar PV | 119.587 | No | 1 | 121 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 47 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
310427 | SDG&E | 92025 | NEM | NEMA | APPROVED | Solar PV | 43.141 | No | 1 | 17 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 5 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
312507 | SDG&E | 92008 | NEM | NEMA | APPROVED | Solar PV | 264.762 | No | 1 | 26 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 90 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
312971 | SDG&E | 91911 | NEM | NEMA | APPROVED | Solar PV | 114.437 | No | 1 | 20 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 111 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
313102 | SDG&E | 92154 | NEM | NEMA | APPROVED | Solar PV | 446.798 | No | 1 | 20 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 142 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
313107 | SDG&E | 92110 | NEM | NEMA | APPROVED | Solar PV | 52.101 | No | 1 | 19 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 37 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
313246 | SDG&E | 92026 | NEM | NEMA | APPROVED | Solar PV | 139.084 | No | 1 | 2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 231 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
314442 | SDG&E | 92054 | NEM | NEMA | APPROVED | Solar PV | 117.51 | No | 1 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 17 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
315959 | SDG&E | 91935 | NEM | NEMA | APPROVED | Solar PV | 38.751 | No | 1 | 6 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
317843 | SDG&E | 92026 | NEM | NEMA | APPROVED | Solar PV | 369.027 | No | 1 | 19 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 238 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
318150 | SDG&E | 92069 | NEM | NEMA | PENDING AHJ INSPECTION | Solar PV | 152.645 | No | 1 | 43 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
318779 | SDG&E | 92103 | NEM | NEMA | APPROVED | Solar PV | 36 | No | 1 | 231 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 5 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
320006 | SDG&E | 92108 | NEM | NEMA | APPROVED | Solar PV | 93.171 | No | 1 | 14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
325935 | SDG&E | 92004 | NEM | NEMA | PENDING AHJ INSPECTION | Solar PV | 621.971 | No | 1 | 18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
329795 | SDG&E | 92086 | NEM | NEMA | APPROVED | Solar PV | 89.192 | No | 1 | 77 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 8 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
331221 | SDG&E | 92111 | NEM | NEMA | APPROVED | Solar PV | 88.513 | No | 1 | 45 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 5 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
331497 | SDG&E | 92020 | NEM | NEMA | APPROVED | Solar PV | 30.09 | No | 1 | 7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
336749 | SDG&E | 92154 | NEM | NEMA | PENDING AHJ INSPECTION | Solar PV | 128 | No | 1 | 70 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
337018 | SDG&E | 92128 | NEM | NEMA | PENDING AHJ INSPECTION | Solar PV | 37 | No | 1 | 49 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
337161 | SDG&E | 92040 | NEM | NEMA | PENDING AHJ INSPECTION | Solar PV | 104 | No | 1 | 102 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
337953 | SDG&E | 92103 | NEM | NEMA | PENDING AHJ INSPECTION | Solar PV | 100.101 | No | 1 | 33 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
338446 | SDG&E | 92114 | NEM | NEMA | APPROVED | Solar PV | 84 | No | 1 | 30 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 6 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
339109 | SDG&E | 92675 | NEM | NEMA | PENDING AHJ INSPECTION | Solar PV | 301 | No | 1 | 90 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
340708 | SDG&E | 92104 | NEM | NEMA | PENDING AHJ INSPECTION | Solar PV | 42.636 | No | 1 | 13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
342897 | SDG&E | 92123 | NEM | NEMA | PENDING AHJ INSPECTION | Solar PV | 444 | No | 1 | 69 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
296952 | SDG&E | 92011 | NEM | VNEM | APPROVED | Solar PV | 139.917 | No | 1 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 142 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
298178 | SDG&E | 92123 | NEM | VNEM | PENDING AHJ INSPECTION | Solar PV | 69.05 | No | 1 | 184 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
298181 | SDG&E | 92130 | NEM | VNEM | PENDING AHJ INSPECTION | Solar PV | 69.05 | No | 1 | 184 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
298356 | SDG&E | 91914 | NEM | VNEM | PENDING AHJ INSPECTION | Solar PV | 75.9 | No | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
298371 | SDG&E | 91914 | NEM | VNEM | APPROVED | Solar PV | 133.2 | No | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 120 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
299354 | SDG&E | 92115 | NEM | VNEM | PENDING AHJ INSPECTION | Solar PV | 80.306 | No | 1 | 5 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
299713 | SDG&E | 92114 | NEM | VNEM | APPROVED | Solar PV | 59.81 | No | 1 | 227 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 174 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
299724 | SDG&E | 92058 | NEM | VNEM | PENDING AHJ INSPECTION | Solar PV | 43.59 | No | 1 | 259 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
299737 | SDG&E | 92129 | NEM | VNEM | APPROVED | Solar PV | 54.22 | No | 1 | 226 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 180 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
299764 | SDG&E | 92130 | NEM | VNEM | PENDING AHJ INSPECTION | Solar PV | 31.3 | No | 1 | 226 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
300021 | SDG&E | 92126 | NEM | VNEM | APPROVED | Solar PV | 73.92 | No | 1 | 6 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 223 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
300758 | SDG&E | 92025 | NEM | VNEM | APPROVED | Solar PV | 80.219 | No | 1 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 404 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
300779 | SDG&E | 92025 | NEM | VNEM | PENDING AHJ INSPECTION | Solar PV | 164.65 | No | 1 | 8 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
300988 | SDG&E | 92025 | NEM | VNEM | PENDING AHJ INSPECTION | Solar PV | 164.65 | No | 1 | 8 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
301817 | SDG&E | 92127 | NEM | VNEM | PENDING AHJ INSPECTION | Solar PV | 64.929 | No | 1 | 12 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
305880 | SDG&E | 92058 | NEM | VNEM | APPROVED | Solar PV | 583.858 | No | 1 | 6 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 336 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
305971 | SDG&E | 92673 | NEM | VNEM | PENDING AHJ INSPECTION | Solar PV | 61.481 | No | 1 | 3 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
305974 | SDG&E | 92673 | NEM | VNEM | PENDING AHJ INSPECTION | Solar PV | 53.897 | No | 1 | 6 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
306198 | SDG&E | 92122 | NEM | VNEM | APPROVED | Solar PV | 79.039 | No | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 216 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
306321 | SDG&E | 91942 | NEM | VNEM | APPROVED | Solar PV | 64.89 | No | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 78 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
306668 | SDG&E | 92111 | NEM | VNEM | APPROVED | Solar PV | 47.736 | No | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 81 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
315674 | SDG&E | 92673 | NEM | VNEM | APPROVED | Solar PV | 88.29 | No | 1 | 173 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 46 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
315683 | SDG&E | 92673 | NEM | VNEM | APPROVED | Solar PV | 333.3 | No | 1 | 173 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 46 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
317034 | SDG&E | 92122 | NEM | VNEM | APPROVED | Solar PV | 74.6 | No | 1 | 3 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 112 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
317039 | SDG&E | 92122 | NEM | VNEM | APPROVED | Solar PV | 36.92 | No | 1 | 3 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 112 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
317045 | SDG&E | 92122 | NEM | VNEM | APPROVED | Solar PV | 36.92 | No | 1 | 3 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 112 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
317125 | SDG&E | 92121 | NEM | VNEM | APPROVED | Solar PV | 104.388 | No | 1 | 3 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 130 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
317902 | SDG&E | 92122 | NEM | VNEM | APPROVED | Solar PV | 36.92 | No | 1 | 3 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 112 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
318181 | SDG&E | 92126 | NEM | VNEM | APPROVED | Solar PV | 73.54 | No | 1 | 6 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 223 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
318886 | SDG&E | 92054 | NEM | VNEM | APPROVED | Solar PV | 36.2 | No | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 204 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
319649 | SDG&E | 92128 | NEM | VNEM | APPROVED | Solar PV | 141.89 | No | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 83 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
321085 | SDG&E | 92130 | NEM | VNEM | PENDING AHJ INSPECTION | Solar PV | 90.03 | No | 1 | 184 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
323049 | SDG&E | 92020 | NEM | VNEM | APPROVED | Solar PV | 93.6 | No | 1 | 31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 101 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
324305 | SDG&E | 91950 | NEM | VNEM | PENDING AHJ INSPECTION | Solar PV | 78.824 | No | 1 | 10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
324310 | SDG&E | 91950 | NEM | VNEM | PENDING AHJ INSPECTION | Solar PV | 89.984 | No | 1 | 10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
324899 | SDG&E | 91950 | NEM | VNEM | PENDING AHJ INSPECTION | Solar PV | 34.18 | No | 1 | 10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
324908 | SDG&E | 92113 | NEM | VNEM | PENDING AHJ INSPECTION | Solar PV | 57.66 | No | 1 | 10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
325165 | SDG&E | 92673 | NEM | VNEM | PENDING AHJ INSPECTION | Solar PV | 110.3 | No | 1 | 11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
325584 | SDG&E | 92078 | NEM | VNEM | PENDING AHJ INSPECTION | Solar PV | 375 | No | 1 | 16 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
325931 | SDG&E | 91913 | NEM | VNEM | PENDING AHJ INSPECTION | Solar PV | 121 | No | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
327166 | SDG&E | 92078 | NEM | VNEM | PENDING AHJ INSPECTION | Solar PV | 133.2 | No | 1 | 16 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
328125 | SDG&E | 91913 | NEM | VNEM | PENDING AHJ INSPECTION | Solar PV | 137 | No | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
330149 | SDG&E | 92127 | NEM | VNEM | PENDING AHJ INSPECTION | Solar PV | 60.7 | No | 1 | 6 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
330796 | SDG&E | 92078 | NEM | VNEM | PENDING AHJ INSPECTION | Solar PV | 86.4 | No | 1 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
330937 | SDG&E | 92078 | NEM | VNEM | PENDING AHJ INSPECTION | Solar PV | 95.75 | No | 1 | 369 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
330940 | SDG&E | 92078 | NEM | VNEM | PENDING AHJ INSPECTION | Solar PV | 58.43 | No | 1 | 369 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
331375 | SDG&E | 92078 | NEM | VNEM | PENDING AHJ INSPECTION | Solar PV | 155.2 | No | 1 | 22 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
336504 | SDG&E | 91911 | NEM | VNEM | PENDING AHJ INSPECTION | Solar PV | 45.6 | No | 1 | 5 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
336639 | SDG&E | 91911 | NEM | VNEM | PENDING AHJ INSPECTION | Solar PV | 47.07 | No | 1 | 5 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
336664 | SDG&E | 91911 | NEM | VNEM | PENDING AHJ INSPECTION | Solar PV | 44.52 | No | 1 | 5 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
336683 | SDG&E | 91911 | NEM | VNEM | PENDING AHJ INSPECTION | Solar PV | 47.4 | No | 1 | 5 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
336685 | SDG&E | 91911 | NEM | VNEM | PENDING AHJ INSPECTION | Solar PV | 45.24 | No | 1 | 5 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
336692 | SDG&E | 91911 | NEM | VNEM | PENDING AHJ INSPECTION | Solar PV | 47.4 | No | 1 | 5 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
337348 | SDG&E | 92009 | NEM | VNEM | PENDING AHJ INSPECTION | Solar PV | 60.61 | No | 1 | 7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
337354 | SDG&E | 92009 | NEM | VNEM | PENDING AHJ INSPECTION | Solar PV | 59.54 | No | 1 | 7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
337882 | SDG&E | 92021 | NEM | VNEM | APPROVED | Solar PV | 86 | No | 1 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 97 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
281862 | SDG&E | 92154 | NEM | NEM-ST | APPROVED | Battery Storage + Solar PV | 406.84 | No | 1 | 173 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 284 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
296966 | SDG&E | 92121 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 44.214 | No | 1 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
295832 | SDG&E | 92108 | NEM | NEM-ST | APPROVED | Solar PV | 54.845 | No | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 34 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
297846 | SDG&E | 92025 | NEM | NEM-ST | APPROVED | Solar PV | 33.445 | No | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 8 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
297894 | SDG&E | 92120 | NEM | NEM-ST | APPROVED | Solar PV | 155.044 | No | 1 | 5 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 126 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
297972 | SDG&E | 92123 | NEM | NEM-ST | PENDING AHJ INSPECTION | Battery Storage + Solar PV | 851.674 | No | 1 | 33 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
297819 | SDG&E | 92037 | NEM | NEM-ST | PENDING AHJ INSPECTION | Battery Storage + Solar PV | 206.886 | No | 1 | 15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
299510 | SDG&E | 92025 | NEM | NEM-ST | APPROVED | Solar PV | 64.668 | No | 1 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
299459 | SDG&E | 92154 | NEM | NEM-ST | APPROVED | Solar PV | 290 | No | 1 | 109 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete |  |  | 200 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
299469 | SDG&E | 92126 | NEM | NEM-ST | APPROVED | Solar PV | 89.362 | No | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 177 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
299788 | SDG&E | 92028 | NEM | NEM-ST | APPROVED | Solar PV | 30.262 | No | 1 | 6 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 241 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
300182 | SDG&E | 92067 | NEM | NEM-ST | APPROVED | Solar PV | 31.786 | No | 1 | 3 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 45 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
300302 | SDG&E | 92113 | NEM | NEM-ST | APPROVED | Solar PV | 99.387 | No | 1 | 3 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 322 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
300476 | SDG&E | 92040 | NEM | NEM-ST | APPROVED | Solar PV | 348.66 | No | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 209 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
300569 | SDG&E | 92081 | NEM | NEM-ST | APPROVED | Solar PV | 427.071 | No | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 104 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
300570 | SDG&E | 92008 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 283.343 | No | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
300246 | SDG&E | 92027 | NEM | NEM-ST | APPROVED | Solar PV | 150.731 | No | 1 | 5 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 254 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
300756 | SDG&E | 92121 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 370.124 | No | 1 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
300868 | SDG&E | 92154 | NEM | NEM-ST | APPROVED | Solar PV | 854.143 | No | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 126 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
299331 | SDG&E | 91910 | NEM | NEM-ST | APPROVED | Solar PV | 57.783 | No | 1 | 6 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 87 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
301149 | SDG&E | 92071 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 234.534 | No | 1 | 165 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
301310 | SDG&E | 92121 | NEM | NEM-ST | APPROVED | Solar PV | 293.924 | No | 1 | 17 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 87 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
304291 | SDG&E | 92154 | NEM | NEM-ST | PENDING AHJ INSPECTION | Battery Storage + Solar PV | 306.729 | No | 1 | 6 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 321 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
304265 | SDG&E | 92078 | NEM | NEM-ST | APPROVED | Solar PV | 63.777 | No | 1 | 6 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
304193 | SDG&E | 92677 | NEM | NEM-ST | APPROVED | Solar PV | 84.302 | No | 1 | 5 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 197 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
304595 | SDG&E | 92672 | NEM | NEM-ST | ISSUES | Solar PV | 47.238 | No | 1 | 3 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
304775 | SDG&E | 92026 | NEM | NEM-ST | APPROVED | Solar PV | 44.752 | No | 1 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 134 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
301339 | SDG&E | 92121 | NEM | NEM-ST | APPROVED | Solar PV | 141.182 | No | 1 | 6 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 260 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
305478 | SDG&E | 92130 | NEM | NEM-ST | APPROVED | Solar PV | 35.838 | No | 1 | 7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 107 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
301675 | SDG&E | 92121 | NEM | NEM-ST | APPROVED | Solar PV | 258.191 | No | 1 | 72 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 194 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
262465 | SDG&E | 92019 | NEM | NEM-ST | APPROVED | Solar PV | 131.929 | No | 1 | 6 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 89 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
304597 | SDG&E | 92069 | NEM | NEM-ST | APPROVED | Solar PV | 35.41 | No | 1 | 5 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 55 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
304927 | SDG&E | 91910 | NEM | NEM-ST | APPROVED | Solar PV | 57.601 | No | 1 | 5 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 59 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
299074 | SDG&E | 92064 | NEM | NEM-ST | APPROVED | Solar PV | 54.01 | No | 1 | 8 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 30 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
306279 | SDG&E | 92067 | NEM | NEM-ST | APPROVED | Solar PV | 72.206 | No | 1 | 5 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 87 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
306362 | SDG&E | 92029 | NEM | NEM-ST | APPROVED | Solar PV | 39.03 | No | 1 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 178 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
301835 | SDG&E | 92028 | NEM | NEM-ST | APPROVED | Solar PV | 163.27 | No | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
300505 | SDG&E | 91911 | NEM | NEM-ST | APPROVED | Solar PV | 74.211 | No | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 208 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
304249 | SDG&E | 91911 | NEM | NEM-ST | APPROVED | Solar PV | 81.606 | No | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 210 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
304251 | SDG&E | 91911 | NEM | NEM-ST | APPROVED | Solar PV | 133.783 | No | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 212 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
304263 | SDG&E | 91911 | NEM | NEM-ST | APPROVED | Solar PV | 141.103 | No | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 208 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
304268 | SDG&E | 91911 | NEM | NEM-ST | APPROVED | Solar PV | 200.675 | No | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 202 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
304272 | SDG&E | 91911 | NEM | NEM-ST | APPROVED | Solar PV | 133.783 | No | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 208 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
304280 | SDG&E | 91911 | NEM | NEM-ST | APPROVED | Solar PV | 133.783 | No | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 208 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
304350 | SDG&E | 91914 | NEM | NEM-ST | APPROVED | Solar PV | 429.367 | No | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 138 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
305710 | SDG&E | 91913 | NEM | NEM-ST | APPROVED | Solar PV | 215.389 | No | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 202 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
301338 | SDG&E | 91209 | NEM | NEM-ST | APPROVED | Solar PV | 46.153 | No | 1 | 25 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 19 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
307202 | SDG&E | 92121 | NEM | NEM-ST | APPROVED | Solar PV | 106.294 | No | 1 | 8 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 61 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
306705 | SDG&E | 92057 | NEM | NEM-ST | APPROVED | Solar PV | 42.464 | No | 1 | 10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
307960 | SDG&E | 92154 | NEM | NEM/PRD | PENDING AHJ INSPECTION | Battery Storage | 429 | No | 1 | 10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
306067 | SDG&E | 92081 | NEM | NEM-ST | ISSUES | Solar PV | 651.932 | No | 1 | 22 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
307060 | SDG&E | 92037 | NEM | NEM-ST | ISSUES | Solar PV | 168.014 | No | 1 | 22 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
307412 | SDG&E | 92025 | NEM | NEM-ST | APPROVED | Solar PV | 35.416 | No | 1 | 7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
308194 | SDG&E | 91945 | NEM | NEM-ST | APPROVED | Solar PV | 63.003 | No | 1 | 6 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 197 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
308191 | SDG&E | 91941 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 80.024 | No | 1 | 6 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
307389 | SDG&E | 91902 | NEM | NEM-ST | APPROVED | Solar PV | 39.452 | No | 1 | 3 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
300349 | SDG&E | 92127 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 61.495 | No | 1 | 8 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
309793 | SDG&E | 91901 | NEM | NEM-ST | APPROVED | Battery Storage + Solar PV | 60.89 | No | 1 | 27 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
255189 | SDG&E | 92673 | NEM | NEM-ST | APPROVED | Solar PV | 61.087 | No | 1 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 47 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
309701 | SDG&E | 92105 | NEM | NEM-ST | APPROVED | Battery Storage + Solar PV | 62.204 | No | 1 | 25 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 40 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
308022 | SDG&E | 92624 | NEM | NEM-ST | APPROVED | Solar PV | 37.293 | No | 1 | 3 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 6 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
307358 | SDG&E | 91913 | NEM | NEM-ST | APPROVED | Solar PV | 156.081 | No | 1 | 2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 242 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
307379 | SDG&E | 91913 | NEM | NEM-ST | APPROVED | Solar PV | 185.81 | No | 1 | 2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 276 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
307385 | SDG&E | 91913 | NEM | NEM-ST | APPROVED | Solar PV | 185.81 | No | 1 | 2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 227 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
307390 | SDG&E | 91913 | NEM | NEM-ST | APPROVED | Solar PV | 133.783 | No | 1 | 2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 242 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
307393 | SDG&E | 91913 | NEM | NEM-ST | APPROVED | Solar PV | 133.783 | No | 1 | 2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 242 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
307399 | SDG&E | 91913 | NEM | NEM-ST | APPROVED | Solar PV | 133.783 | No | 1 | 2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 251 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
307402 | SDG&E | 91910 | NEM | NEM-ST | APPROVED | Solar PV | 156.081 | No | 1 | 2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 242 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
307404 | SDG&E | 91913 | NEM | NEM-ST | APPROVED | Solar PV | 200.524 | No | 1 | 2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 228 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
295911 | SDG&E | 92126 | NEM | NEM-ST | APPROVED | Solar PV | 71.324 | No | 1 | 5 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 135 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
310238 | SDG&E | 92122 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 189.716 | No | 1 | 5 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
310318 | SDG&E | 92124 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 259.049 | No | 1 | 5 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
310484 | SDG&E | 92082 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 481.552 | No | 1 | 10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
310486 | SDG&E | 92082 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 211.342 | No | 1 | 10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
310490 | SDG&E | 92082 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 72.659 | No | 1 | 10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
310611 | SDG&E | 92064 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 460.147 | No | 1 | 9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
310619 | SDG&E | 92064 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 372.628 | No | 1 | 9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
310741 | SDG&E | 92672 | NEM | NEM-ST | APPROVED | Solar PV | 41.527 | No | 1 | 7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 75 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
310796 | SDG&E | 92029 | NEM | NEM-ST | APPROVED | Solar PV | 33.423 | No | 1 | 7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 169 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
310336 | SDG&E | 92131 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 247.826 | No | 1 | 7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
311997 | SDG&E | 92653 | NEM | NEM-ST | APPROVED | Solar PV | 35.175 | No | 1 | 39 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 34 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
312026 | SDG&E | 91950 | NEM | NEM-ST | APPROVED | Solar PV | 31.798 | No | 1 | 9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
310814 | SDG&E | 92111 | NEM | NEM-ST | APPROVED | Solar PV | 393.578 | No | 1 | 83 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 259 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
312384 | SDG&E | 92114 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 249.462 | No | 1 | 8 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
312370 | SDG&E | 91913 | NEM | NEM-ST | APPROVED | Solar PV | 54.771 | No | 1 | 7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 139 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
312518 | SDG&E | 92675 | NEM | NEM-ST | APPROVED | Solar PV | 34.902 | No | 1 | 6 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 12 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
312450 | SDG&E | 92028 | NEM | NEM-ST | INITIAL REVIEW | Battery Storage | 500 | No | 1 | 59 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
312900 | SDG&E | 92078 | NEM | NEM-ST | APPROVED | Battery Storage + Solar PV | 47.4 | No | 1 | 2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
313131 | SDG&E | 91911 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 114.437 | No | 1 | 3 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
313243 | SDG&E | 92150 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 172.825 | No | 1 | 3 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
313534 | SDG&E | 92105 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 160.213 | No | 1 | 3 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
313812 | SDG&E | 92121 | NEM | NEM-ST | APPROVED | Solar PV | 70.882 | No | 1 | 6 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 83 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
313830 | SDG&E | 92113 | NEM | NEM-ST | APPROVED | Solar PV | 110.853 | No | 1 | 6 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 116 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
314001 | SDG&E | 92110 | NEM | NEM-ST | APPROVED | Solar PV | 31.149 | No | 1 | 9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 12 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
314336 | SDG&E | 91910 | NEM | NEM-ST | APPROVED | Solar PV | 112.557 | No | 1 | 7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 151 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
312775 | SDG&E | 91911 | NEM | NEM-ST | APPROVED | Solar PV | 89.076 | No | 1 | 3 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 315 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
312771 | SDG&E | 91902 | NEM | NEM-ST | ISSUES | Solar PV | 133.783 | No | 1 | 3 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
300503 | SDG&E | 91910 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 104.054 | No | 1 | 3 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
300519 | SDG&E | 91911 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 96.47 | No | 1 | 3 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
300525 | SDG&E | 91910 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 148.535 | No | 1 | 3 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
312773 | SDG&E | 91910 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 74.173 | No | 1 | 19 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
312826 | SDG&E | 91911 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 96.47 | No | 1 | 19 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
315694 | SDG&E | 92101 | NEM | NEM-ST | APPROVED | Solar PV | 36.856 | No | 1 | 20 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 5 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
316082 | SDG&E | 92067 | NEM | NEM-ST | PENDING AHJ INSPECTION | Battery Storage + Solar PV | 46.667 | No | 1 | 2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
315794 | SDG&E | 92123 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 290.343 | No | 1 | 2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
315018 | SDG&E | 92173 | NEM | NEM-ST | INITIAL REVIEW | Solar PV | 659.255 | No | 1 | 48 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
316341 | SDG&E | 92101 | NEM | NEM-ST | APPROVED | Solar PV | 68.726 | No | 1 | 24 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 69 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
316102 | SDG&E | 92117 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 407.029 | No | 1 | 14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
315424 | SDG&E | 91950 | NEM | NEM-ST | APPROVED | Solar PV | 49.217 | No | 1 | 5 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
317757 | SDG&E | 92067 | NEM | NEM-ST | APPROVED | Solar PV | 410.282 | No | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 224 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
317932 | SDG&E | 92108 | NEM | NEM-ST | APPROVED | Solar PV | 86.104 | No | 1 | 23 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 123 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
317913 | SDG&E | 92026 | NEM | NEM-ST | APPROVED | Solar PV | 146.281 | No | 1 | 7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 249 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
318437 | SDG&E | 92008 | NEM | NEM-ST | APPROVED | Solar PV | 132.884 | No | 1 | 2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 55 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
317369 | SDG&E | 92108 | NEM | NEM-ST | APPROVED | Solar PV | 65.814 | No | 1 | 6 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 55 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
317626 | SDG&E | 91914 | NEM | NEM-ST | APPROVED | Solar PV | 133.783 | No | 1 | 2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 19 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
317627 | SDG&E | 91914 | NEM | NEM-ST | APPROVED | Solar PV | 148.497 | No | 1 | 36 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 167 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
300523 | SDG&E | 91911 | NEM | NEM-ST | APPROVED | Solar PV | 154.924 | No | 1 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 259 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
317880 | SDG&E | 92081 | NEM | NEM-ST | APPROVED | Solar PV | 178.992 | No | 1 | 2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 211 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
317624 | SDG&E | 91911 | NEM | NEM-ST | APPROVED | Solar PV | 185.81 | No | 1 | 2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 222 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
317619 | SDG&E | 91911 | NEM | NEM-ST | APPROVED | Solar PV | 193.243 | No | 1 | 2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 222 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
317628 | SDG&E | 91914 | NEM | NEM-ST | APPROVED | Solar PV | 200.675 | No | 1 | 2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 197 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
319440 | SDG&E | 92091 | NEM | NEM-ST | APPROVED | Solar PV | 30.64 | No | 1 | 13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
318143 | SDG&E | 92069 | NEM | NEM-ST | PENDING AHJ INSPECTION | Battery Storage | 280 | No | 1 | 51 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
317896 | SDG&E | 92007 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 352.235 | No | 1 | 12 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
319746 | SDG&E | 92081 | NEM | NEM-ST | APPROVED | Solar PV | 63.922 | No | 1 | 7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 5 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
319656 | SDG&E | 92154 | NEM | NEM-ST | APPROVED | Solar PV | 294.48 | No | 1 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 111 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
320005 | SDG&E | 92067 | NEM | NEM-ST | APPROVED | Battery Storage + Solar PV | 35.786 | No | 1 | 7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 139 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
318316 | SDG&E | 92007 | NEM | NEM-ST | APPROVED | Solar PV | 71.752 | No | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 81 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
320616 | SDG&E | 92081 | NEM | NEM-ST | APPROVED | Solar PV | 413.36 | No | 1 | 3 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 32 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
321479 | SDG&E | 92106 | NEM | NEM-ST | APPROVED | Solar PV | 31.056 | No | 1 | 15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 8 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
321723 | SDG&E | 92036 | NEM | NEM-ST | APPROVED | Solar PV | 345.055 | No | 1 | 3 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 55 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
321900 | SDG&E | 92653 | NEM | NEM-ST | APPROVED | Solar PV | 31.257 | No | 1 | 2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 118 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
322216 | SDG&E | 92025 | NEM | NEM-ST | APPROVED | Solar PV | 31.834 | No | 1 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 139 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
322591 | SDG&E | 91914 | NEM | NEM-ST | APPROVED | Solar PV | 132.622 | No | 1 | 7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 160 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
322125 | SDG&E | 92154 | NEM | NEM-ST | APPROVED | Solar PV | 111.486 | No | 1 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 224 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
322605 | SDG&E | 91915 | NEM | NEM-ST | APPROVED | Solar PV | 133.783 | No | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 219 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
300496 | SDG&E | 91915 | NEM | NEM-ST | APPROVED | Solar PV | 133.783 | No | 1 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 241 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
322053 | SDG&E | 92154 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 133.783 | No | 1 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
300521 | SDG&E | 92154 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 163.513 | No | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
300491 | SDG&E | 91915 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 163.513 | No | 1 | 21 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
322121 | SDG&E | 92154 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 170.946 | No | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
323430 | SDG&E | 92024 | NEM | NEM-ST | APPROVED | Battery Storage | 30 | No | 1 | 15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 6 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
318148 | SDG&E | 92007 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 132.51 | No | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
322898 | SDG&E | 92037 | NEM | NEM-ST | APPROVED | Solar PV | 39.1 | No | 1 | 5 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 84 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
324041 | SDG&E | 91911 | NEM | NEM-ST | APPROVED | Solar PV | 30.617 | No | 1 | 2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
318988 | SDG&E | 91910 | NEM | NEM-ST | APPROVED | Solar PV | 48.754 | No | 1 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 121 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
324624 | SDG&E | 92121 | NEM | NEM-ST | APPROVED | Solar PV | 71.685 | No | 1 | 13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 134 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
323961 | SDG&E | 92054 | NEM | NEM-ST | APPROVED | Solar PV | 37.531 | No | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 73 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
324769 | SDG&E | 92131 | NEM | NEM-ST | APPROVED | Solar PV | 181.488 | No | 1 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
325383 | SDG&E | 92056 | NEM | NEM-ST | APPROVED | Solar PV | 131.027 | No | 1 | 22 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 41 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
327197 | SDG&E | 92078 | NEM | NEM-ST | ISSUES | Solar PV | 36.43 | No | 1 | 13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
325850 | SDG&E | 92027 | NEM | NEM-ST | APPROVED | Solar PV | 50.97 | No | 1 | 13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 175 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
327871 | SDG&E | 92071 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 66.741 | No | 1 | 6 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
327576 | SDG&E | 92071 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 83.274 | No | 1 | 6 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
327819 | SDG&E | 92111 | NEM | NEM-ST | APPROVED | Solar PV | 39.172 | No | 1 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 16 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
328307 | SDG&E | 92103 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 269.637 | No | 1 | 3 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
327133 | SDG&E | 92071 | NEM | NEM-ST | APPROVED | Solar PV | 35.672 | No | 1 | 5 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 6 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
319205 | SDG&E | 92107 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 42.727 | No | 1 | 22 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
328079 | SDG&E | 92128 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 475.049 | No | 1 | 15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
327497 | SDG&E | 92106 | NEM | NEM-ST | APPROVED | Solar PV | 41.109 | No | 1 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 176 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
297212 | SDG&E | 91902 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 89.038 | No | 1 | 7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
328996 | SDG&E | 92110 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 107.121 | No | 1 | 7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
328827 | SDG&E | 91902 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 111.486 | No | 1 | 7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
328566 | SDG&E | 91910 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 118.919 | No | 1 | 7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
300512 | SDG&E | 91910 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 126.351 | No | 1 | 7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
300517 | SDG&E | 91910 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 245.27 | No | 1 | 7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
328562 | SDG&E | 91910 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 104.054 | No | 1 | 6 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
329675 | SDG&E | 91913 | NEM | NEM-ST | APPROVED | Solar PV | 66.09 | No | 1 | 6 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 93 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
329673 | SDG&E | 91913 | NEM | NEM-ST | APPROVED | Solar PV | 119.765 | No | 1 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 99 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
329732 | SDG&E | 91913 | NEM | NEM-ST | APPROVED | Solar PV | 169.059 | No | 1 | 6 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 93 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
329988 | SDG&E | 92101 | NEM | NEM-ST | APPROVED | Solar PV | 96.26 | No | 1 | 20 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 84 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
330166 | SDG&E | 92109 | NEM | NEM-ST | APPROVED | Solar PV | 72.466 | No | 1 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
330930 | SDG&E | 92003 | NEM | NEM-ST | APPROVED | Solar PV | 89.58 | No | 1 | 3 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 152 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
331335 | SDG&E | 92037 | NEM | NEM-ST | APPROVED | Solar PV | 91.598 | No | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 112 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
331339 | SDG&E | 91906 | NEM | NEM-ST | APPROVED | Solar PV | 119.246 | No | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 92 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
331107 | SDG&E | 92121 | NEM | NEM-ST | APPROVED | Solar PV | 62.187 | No | 1 | 42 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
331488 | SDG&E | 92121 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 295.949 | No | 1 | 13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
331984 | SDG&E | 91913 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 178.378 | No | 1 | 2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
332150 | SDG&E | 92064 | NEM | NEM-ST | APPROVED | Solar PV | 34.431 | No | 1 | 6 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 134 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
332888 | SDG&E | 92110 | NEM | NEM-ST | APPROVED | Solar PV | 41.206 | No | 1 | 8 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 19 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
332890 | SDG&E | 92110 | NEM | NEM-ST | APPROVED | Solar PV | 41.206 | No | 1 | 8 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 19 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
333441 | SDG&E | 92083 | NEM | NEM-ST | ISSUES | Battery Storage + Solar PV | 43.643 | No | 1 | 12 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
330299 | SDG&E | 92127 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 336.693 | No | 1 | 7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
334038 | SDG&E | 92127 | NEM | NEM-ST | ISSUES | Battery Storage | 35 | No | 1 | 6 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
334087 | SDG&E | 92173 | NEM | NEM-ST | APPROVED | Solar PV | 62.977 | No | 1 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 48 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
334090 | SDG&E | 92065 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 90.737 | No | 1 | 20 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
334156 | SDG&E | 92008 | NEM | NEM-ST | APPROVED | Solar PV | 117.183 | No | 1 | 6 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
334006 | SDG&E | 91932 | NEM | NEM-ST | APPROVED | Solar PV | 125.954 | No | 1 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 30 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
334324 | SDG&E | 92056 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 35.758 | No | 1 | 5 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
335029 | SDG&E | 91914 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 39.453 | No | 1 | 7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
335118 | SDG&E | 91901 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 113.018 | No | 1 | 7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
335359 | SDG&E | 92026 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 112 | No | 1 | 103 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
336342 | SDG&E | 92008 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 984.198 | No | 1 | 30 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
337041 | SDG&E | 92019 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 42.83 | No | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
336833 | SDG&E | 92675 | NEM | NEM-ST | APPROVED | Solar PV | 49.685 | No | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 116 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
337207 | SDG&E | 92040 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 89.813 | No | 1 | 6 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
336735 | SDG&E | 92040 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 98.479 | No | 1 | 5 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
337206 | SDG&E | 92040 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 113.541 | No | 1 | 6 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
337210 | SDG&E | 92040 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 147.342 | No | 1 | 6 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
337169 | SDG&E | 92040 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 176.256 | No | 1 | 6 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
337258 | SDG&E | 92008 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 58.177 | No | 1 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
337261 | SDG&E | 92011 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 59 | No | 1 | 140 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
336922 | SDG&E | 91910 | NEM | NEM-ST | APPROVED | Solar PV | 106.049 | No | 1 | 3 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 55 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
337528 | SDG&E | 92057 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 85.999 | No | 1 | 8 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
337502 | SDG&E | 92057 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 162.429 | No | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
331555 | SDG&E | 92065 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 5.652 | No | 1 | 9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
337494 | SDG&E | 92057 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 388.892 | No | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
319491 | SDG&E | 92078 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 391.458 | No | 1 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
337976 | SDG&E | 92075 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 55.075 | No | 1 | 2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
337916 | SDG&E | 92082 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 84.63 | No | 1 | 2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
338237 | SDG&E | 92075 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 146.866 | No | 1 | 2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
337260 | SDG&E | 92020 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 33 | No | 1 | 91 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
337699 | SDG&E | 92024 | NEM | NEM-ST | APPROVED | Solar PV | 58.548 | No | 1 | 27 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 57 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
338480 | SDG&E | 92103 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 90.742 | No | 1 | 7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
338990 | SDG&E | 92064 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 44.026 | No | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
338987 | SDG&E | 92064 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 381.558 | No | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
335921 | SDG&E | 92071 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 44.398 | No | 1 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
339148 | SDG&E | 92130 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 94.167 | No | 1 | 7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
339272 | SDG&E | 92059 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 33.852 | No | 1 | 6 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
339276 | SDG&E | 92130 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 133.301 | No | 1 | 19 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
339319 | SDG&E | 92078 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 861.363 | No | 1 | 6 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
339106 | SDG&E | 92675 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 359 | No | 1 | 88 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
339179 | SDG&E | 92054 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 38.138 | No | 1 | 3 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
339184 | SDG&E | 92054 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 47.867 | No | 1 | 3 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
338546 | SDG&E | 92054 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 68.316 | No | 1 | 3 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
338768 | SDG&E | 92054 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 74.76 | No | 1 | 3 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
339446 | SDG&E | 92067 | NEM | NEM-ST | APPROVED | Battery Storage + Solar PV | 50.319 | No | 1 | 2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 110 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
339684 | SDG&E | 92084 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 1000 | No | 1 | 30 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
338906 | SDG&E | 92113 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 193 | No | 1 | 33 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
339969 | SDG&E | 92082 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 303 | No | 1 | 30 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
340088 | SDG&E | 92040 | NEM | NEM-ST | APPROVED | Battery Storage | 240 | No | 1 | 6 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 6 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
340713 | SDG&E | 92111 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 79.774 | No | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
340980 | SDG&E | 92058 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 50.387 | No | 1 | 8 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
340982 | SDG&E | 92058 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 62.621 | No | 1 | 8 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
340646 | SDG&E | 92010 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 81.724 | No | 1 | 7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
340367 | SDG&E | 91910 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 81.643 | No | 1 | 3 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
328659 | SDG&E | 91910 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 200.675 | No | 1 | 3 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
341489 | SDG&E | 92024 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 151.136 | No | 1 | 3 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
341155 | SDG&E | 92105 | NEM | NEM-ST | PENDING AHJ INSPECTION | Battery Storage + Solar PV | 165 | No | 1 | 30 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
337330 | SDG&E | 92071 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 397.561 | No | 1 | 2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
337332 | SDG&E | 92029 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 453 | No | 1 | 2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
340370 | SDG&E | 92024 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 93.676 | No | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
341746 | SDG&E | 92130 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 477 | No | 1 | 24 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
341889 | SDG&E | 92121 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 268 | No | 1 | 22 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
342317 | SDG&E | 91914 | NEM | NEM-PRD | PENDING AHJ INSPECTION | Battery Storage | 60 | No | 1 | 8 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
339712 | SDG&E | 91910 | NEM | NEM-PRD | PENDING AHJ INSPECTION | Battery Storage | 60 | No | 1 | 8 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
338910 | SDG&E | 92120 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 192.847 | No | 1 | 70 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
341159 | SDG&E | 92020 | NEM | NEM-ST | APPROVED | Solar PV | 52.042 | No | 1 | 2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
342515 | SDG&E | 92101 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 146.858 | No | 1 | 2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
342505 | SDG&E | 92101 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 161.382 | No | 1 | 2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
342494 | SDG&E | 92132 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 192.146 | No | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
342518 | SDG&E | 92101 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 215.849 | No | 1 | 2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
342502 | SDG&E | 92101 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 332.448 | No | 1 | 17 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
342675 | SDG&E | 92123 | NEM | NEM-ST | APPROVED | Solar PV | 52.903 | No | 1 | 21 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 19 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
342108 | SDG&E | 92115 | NEM | NEM-ST | APPROVED | Solar PV | 54.61 | No | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
342754 | SDG&E | 92102 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 201.306 | No | 1 | 5 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
306784 | SDG&E | 92082 | NEM | NEM-ST | APPROVED | Solar PV | 36.926 | No | 1 | 16 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 12 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
343091 | SDG&E | 92110 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 47.798 | No | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
342433 | SDG&E | 92126 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 215.535 | No | 1 | 63 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
342735 | SDG&E | 92126 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 234.702 | No | 1 | 50 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
344966 | SDG&E | 92020 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 176.158 | No | 1 | 24 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
342308 | SDG&E | 92069 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 56.925 | No | 1 | 6 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
345765 | SDG&E | 92101 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 40.481 | No | 1 | 9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
343799 | SDG&E | 92121 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 52.459 | No | 1 | 7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
335818 | SDG&E | 91901 | NEM | NEM-ST | APPROVED | Battery Storage + Solar PV | 45.319 | No | 1 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 38 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
346153 | SDG&E | 92104 | NEM | NEM-ST | APPROVED | Solar PV | 75.738 | No | 1 | 13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
346566 | SDG&E | 92061 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 90.331 | No | 1 | 10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
346757 | SDG&E | 92069 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 30.981 | No | 1 | 3 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
347416 | SDG&E | 92067 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 50.317 | No | 1 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
347558 | SDG&E | 92028 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 399.377 | No | 1 | 12 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
347148 | SDG&E | 92121 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 233.983 | No | 1 | 17 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
348896 | SDG&E | 92083 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 95.737 | No | 1 | 14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
348865 | SDG&E | 92113 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 174.57 | No | 1 | 22 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
348883 | SDG&E | 92028 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 991.048 | No | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
343685 | SDG&E | 92078 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 97.428 | No | 1 | 6 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
343696 | SDG&E | 92078 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 147.568 | No | 1 | 6 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
343609 | SDG&E | 92078 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 220.537 | No | 1 | 16 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
346562 | SDG&E | 92061 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 72.265 | No | 1 | 5 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
349434 | SDG&E | 92009 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 77.453 | No | 1 | 5 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
346573 | SDG&E | 92061 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 87.165 | No | 1 | 5 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
349427 | SDG&E | 92009 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 347.723 | No | 1 | 5 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
351096 | SDG&E | 92108 | NEM | NEM-ST | PENDING SDGE INSPECTION | Solar PV | 65.128 | No | 1 | 5 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
351052 | SDG&E | 92010 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 158.507 | No | 1 | 5 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
343602 | SDG&E | 92078 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 199.34 | No | 1 | 5 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
300753 | SDG&E | 92154 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 45.479 | No | 1 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
351580 | SDG&E | 91932 | NEM | NEM-ST | PENDING SDGE INSPECTION | Solar PV | 51.763 | No | 1 | 26 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
352069 | SDG&E | 92040 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 269.649 | No | 1 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
351595 | SDG&E | 92108 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 45.537 | No | 1 | 17 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
352034 | SDG&E | 92121 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 97.665 | No | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
353036 | SDG&E | 92067 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 132.755 | No | 1 | 16 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
353276 | SDG&E | 92154 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 40.481 | No | 1 | 13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
353715 | SDG&E | 92067 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 47.363 | No | 1 | 11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
354108 | SDG&E | 92071 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 47.823 | No | 1 | 9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
354121 | SDG&E | 92071 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 89.269 | No | 1 | 9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
289730 | SDG&E | 92629 | NEM | NEM-ST | PENDING AHJ INSPECTION | Battery Storage + Solar PV | 32.701 | No | 1 | 95 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
246756 | SDG&E | 92113 | NEM | NEM-ST | APPROVED | Battery Storage + Solar PV | 50.196 | No | 1 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 169 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
309632 | SDG&E | 92108 | NEM | NEM-ST | PENDING AHJ INSPECTION | Battery Storage + Solar PV | 956.563 | No | 1 | 47 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
310310 | SDG&E | 92691 | NEM | NEM-ST | APPROVED | Battery Storage + Solar PV | 53.959 | No | 1 | 26 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 225 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
315914 | SDG&E | 92121 | NEM | NEM-ST | APPROVED | Solar PV | 164.569 | No | 1 | 19 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 138 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
331497 | SDG&E | 92020 | NEM | NEM-ST | PENDING AHJ INSPECTION | Solar PV | 30.09 | No | 1 | 7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
319718 | SDG&E | 92110 | NEM | NEM-ST | PENDING AHJ INSPECTION | Battery Storage + Solar PV | 240.548 | No | 1 | 25 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
319427 | SDG&E | 92055 | NEM | NEM-ST | APPROVED | Solar PV | 49.857 | No | 1 | 7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 255 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
209040 | SDG&E | 92128 | NEM | NEM-ST | PENDING AHJ INSPECTION | Battery Storage + Solar PV | 796.384 | No | 1 | 7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
322820 | SDG&E | 92071 | NEM | NEM-ST | APPROVED | Solar PV | 143.489 | No | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 127 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
324142 | SDG&E | 92040 | NEM | NEM-ST | APPROVED | Solar PV | 396.653 | No | 1 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 118 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
325597 | SDG&E | 92069 | NEM | NEM-ST | PENDING AHJ INSPECTION | Battery Storage | 250 | No | 1 | 7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
305238 | SDG&E | 92120 | NEM | NEM-ST | APPROVED | Battery Storage + Solar PV | 85 | No | 1 | 76 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Interconnection Request Complete | N/A | N/A | 52 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
331691 | SDG&E | 92019 | NEM | NEM-ST | ISSUES | Battery Storage + Solar PV | 75 | No | 1 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
304455 | SDG&E | 92082 | NEM | NEM-ST | PENDING AHJ INSPECTION | Battery Storage + Solar PV | 383.868 | No | 1 | 119 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
339052 | SDG&E | 91935 | NEM | NEM-ST | PENDING AHJ INSPECTION | Battery Storage + Solar PV | 63.67 | No | 1 | 62 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
341593 | SDG&E | 92075 | NEM | NEM-ST | ISSUES | Solar PV | 201.331 | No | 1 | 25 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
318272 | SDG&E | 92656 | NEM | NEM-ST | PENDING AHJ INSPECTION | Battery Storage + Solar PV | 123.548 | No | 1 | 8 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A
345806 | SDG&E | 92108 | NEM | NEM-ST | ISSUES | Battery Storage + Solar PV | 593.652 | No | 1 | 36 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A

## Non-NEM_NEM>1MW
SDG&E's Rule 21 Processing Timelines Q1 2022
Project Specifics | [7 empty] | Application Review: |  |  |  |  | Fast Track Initial Review: |  |  | Initial Review Cost Report: |  | Fast Track Supplemental Review: |  |  | Supplemental Review Cost Report: |  | Electrical Independence Test (EIT): |  |  | Scoping Meeting and Study Agreement: |  |  | System Impact Study (SIS): |  |  | Facilities Study: | Draft Agreement: |  |  |  | Material Modification: |  |  | Net Generating Output Meter (NGOM): |  |  |  |  | Minor Upgrades Design: | [6 empty] | Minor Upgrades Construction: |  |  | Commissioning and In-Service:
[8 empty] | ● 10 Business Days for initial application review [E.5.a.] (15 Business Days if Cost Envelope Option is selected [E.5.a.]) |  |  |  |  | 15 Business Days [F.2.a.] |  |  | 15 Business Days [F.2.a. & F.2.b.] |  | 20 Business Days [F.2.c.i.] |  |  | 15 Business Days [F.2.c.iii.] |  | 20 Business Days [F.3.a.] |  |  | 5 Business Days [F.3.b.i.] |  |  | 60 Business Days [F.3.b.ii.] |  |  | F.3.b.vii |  |  |  |  | 10 Business Days [F.3.b.v] (20 Business Days if Cost Envelope Option is selected [F.3.b.v]) | [7 empty] | 60 Business Days (estimated timeline) | [6 empty] | 60 Business Days (estimated timeline) |  |  | Mutually Agreeable Date with Customer
[33 empty] | ● 15 Business Days for Fast Track [F.2.a] | [6 empty] | ● 20 Business Days to Design
[33 empty] | ● 30 Calendar Days for Detailed Study [F.3.e.i.] | [6 empty] | ● 20 Business Days to Install
Project ID | Zip Code | NEM Type | Project Type (Request Type) | Project Status (Current Phase) | Technology Type | Size (kW - Net Nameplate Rating) | Cost Envelope Requested? | Interconnection Request Received Date | Interconnection Request Submission Acknowledged Date | Business Days to Acknowledge Interconnection Request Submission | Application Deemed Complete Date | Business Days to Deem Complete | Fast Track Initial Review Start Date | Fast Track Initial Review Results Issued to Customer Date | Business Days to Issue Fast Track Initial Review Results | Fast Track Initial Review Cost Report Issued to Customer Date | Business Days to Issue Cost Report | Fast Track Supplemental Review Start Date | Fast Track Supplemental Review Results Issued to Customer Date | Business Days to Issue Fast Track Supplemental Review Results | Fast Track Supplemental Review Cost Report Issued to Customer Date | Business Days to Issue Cost Report | EIT Start Date | EIT Results Issued to Customer Date | Business Days to Issue Eletrical Independence Test Results | Scoping Meeting Date | Study Agreement Issued Date | Business Days to Issue Study Agreement | Interconnection SIS Start Date | Interconnection SIS Report Issued to Customer Date | Business Days to Issue SIS Results | Facilities Study Waived Date | Generator Interconnection Agreement Requested Date | Draft Generator Interconnection Agreement Sent to Customer Date | Business Days to Send Draft Agreement | Calendar Days to Send Draft Agreement | Material Modification Request Received Date | Material Modification Results Date | Business Days to Issue Material Modifcation Review Results | NGOM Design Start Date | NGOM Service Request Issued Date | Business Days to Issue NGOM Service Request | NGOM Installed Date | Business Days to Issue PTO (From NGOM Service Request Date) | Preliminary Design Start Date | Preliminary Design Issued to Customer Date | Business Days to Issue Preliminary Design | Preliminary Design Approved by Customer Date | Final Design Issued Date | Business Days to Issue Final Design | Total Design Business Days (Preliminary plus Final) | SDGE Construction Start Date | SDGE Construction Complete Date | Business Days to Construct | Commissioning Test Scheduled Date | Commissioning Test Date | Business Days to Perform Commissioning Test | Permission to Operate (PTO) Date | Business Days to Issue PTO (From Commissioning Test) | Calendar Days from Application Deemed Complete Date to PTO Date
298676 | 90236 | NON-NEM | Rule 21 AES Non-Export | APPROVED | Battery Storage | 10 | No | 2021-01-21 | 2021-01-23 | 2 | 2021-02-01 | 9 | 2021-02-01 | 2021-02-01 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-02-01 | 2021-02-01 | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-03-03 | N/A | 30
298681 | 92060 | NON-NEM | Rule 21 AES Non-Export | APPROVED | Battery Storage | 10 | No | 2021-01-21 | 2021-01-23 | 2 | 2021-02-01 | 9 | 2021-02-01 | 2021-02-01 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-02-01 | 2021-02-01 | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-03-03 | N/A | 30
299012 | 92028 | NON-NEM | Rule 21 AES Inadvertant -Export | APPROVED | Battery Storage | 140 | No | 2021-07-30 | 2021-08-02 | 1 | 2021-08-02 | 1 | 2021-08-02 | 2021-08-02 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-03-15 | 2022-03-16 | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-05 | N/A | 246
299321 | 91935 | NON-NEM | Rule 21 AES Non-Export | APPROVED | Battery Storage | 10 | No | 2021-01-28 | 2021-01-28 | 1 | 2021-02-05 | 8 | 2021-02-03 | 2021-02-03 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-02-03 | 2021-02-03 | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-03-03 | N/A | 26
299457 | 92104 | NON-NEM | Rule 21 AES Inadvertant -Export | PENDING AHJ INSPECTION | Battery Storage | 210 | No | 2021-03-16 | 2021-03-16 | 1 | 2021-03-18 | 2 | 2021-03-18 | 2021-03-30 | 12 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-03-16 | 2021-03-16 | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
299461 | 91916 | NON-NEM | Rule 21 AES Non-Export | APPROVED | Battery Storage | 10 | No | 2021-02-03 | 2021-02-03 | 1 | 2021-02-03 | 0 | 2021-02-03 | 2021-02-03 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-02-03 | 2021-02-03 | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-03-03 | N/A | 28
300610 | 91935 | NON-NEM | Rule 21 AES Non-Export | APPROVED | Battery Storage | 10 | No | 2021-03-16 | 2021-03-16 | 1 | 2021-03-25 | 9 | 2021-03-16 | 2021-03-16 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-03-16 | 2021-03-16 | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-03-25 | N/A | 0
301270 | 92086 | NON-NEM | Rule 21 AES Non-Export | APPROVED | Battery Storage | 10 | No | 2021-03-16 | 2021-03-16 | 1 | 2021-03-16 | 1 | 2021-03-16 | 2021-03-16 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-03-16 | 2021-03-16 | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-07-07 | N/A | 113
305452 | 92127 | NON-NEM | Rule 21 AES Non-Export | APPROVED | Battery Storage | 10 | No | 2021-03-16 | 2021-03-16 | 1 | 2021-03-16 | 0 | 2021-03-16 | 2021-03-16 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-03-16 | 2021-03-16 | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-07-08 | N/A | 114
305723 | 91935 | NON-NEM | Rule 21 AES Non-Export | APPROVED | Battery Storage | 10 | No | 2021-03-25 | 2021-03-25 | 1 | 2021-03-25 | 0 | 2021-03-25 | 2021-03-25 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-03-25 | 2021-03-25 | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-04-21 | N/A | 27
306201 | 92020 | NON-NEM | Rule 21 AES Inadvertant -Export | APPROVED | Battery Storage | 210 | No | 2021-04-05 | 2021-04-05 | 1 | 2021-04-19 | 14 | 2021-05-25 | 2021-06-11 | 12 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-06-04 | 2021-06-04 | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-09-14 | N/A | 148
306203 | 92083 | NON-NEM | Rule 21 AES Inadvertant -Export | APPROVED | Battery Storage | 210 | No | 2021-05-25 | 2021-05-25 | 1 | 2021-06-16 | 22 | 2021-05-25 | 2021-06-11 | 12 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-05-25 | 2021-05-25 | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-10-15 | N/A | 121
306204 | 91935 | NON-NEM | Rule 21 AES Non-Export | APPROVED | Battery Storage | 10 | No | 2021-03-25 | 2021-03-25 | 1 | 2021-04-13 | 19 | 2021-03-25 | 2021-03-25 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-03-25 | 2021-03-25 | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-04-13 | N/A | 0
306364 | 92128 | NON-NEM | Rule 21 AES Inadvertant -Export | APPROVED | Battery Storage | 210 | No | 2021-05-25 | 2021-05-25 | 1 | 2021-06-16 | 22 | 2021-05-25 | 2021-06-11 | 12 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-04-19 | 2021-04-19 | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-10-22 | N/A | 128
309232 | 91935 | NON-NEM | Rule 21 AES Non-Export | APPROVED | Battery Storage | 20 | No | 2021-04-19 | 2021-04-19 | 1 | 2021-06-03 | 45 | 2021-06-03 | 2021-06-04 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-06-03 | 2021-06-04 | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-06-07 | N/A | 4
310361 | 92082 | NON-NEM | Rule 21 AES Non-Export | APPROVED | Battery Storage | 10 | No | 2021-05-04 | 2021-05-04 | 1 | 2021-08-22 | 110 | 2021-06-03 | 2021-06-03 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-06-03 | 2021-11-22 | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-03-21 | N/A | 211
312382 | 91905 | NON-NEM | Rule 21 AES Non-Export | APPROVED | Battery Storage | 10 | No | 2021-06-10 | 2021-06-10 | 1 | 2021-10-07 | 119 | 2021-06-10 | 2021-06-10 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-06-04 | 2021-06-04 | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-10-07 | N/A | 0
312847 | 92028 | NON-NEM | Rule 21 AES Inadvertant -Export | PENDING AHJ INSPECTION | Battery Storage | 232 | No | 2021-07-27 | 2021-07-28 | 1 | 2021-07-28 | 0 | 2021-07-27 | 2021-07-28 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-07-27 |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A
314158 | 91935 | NON-NEM | Rule 21 AES Non-Export | APPROVED | Battery Storage | 10 | No | 2021-07-26 | 2021-07-26 | 1 | 2021-07-26 | 0 | 2021-07-26 | 2021-07-27 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-07-26 | 2021-07-26 | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-08-23 | N/A | 28
314210 | 92028 | NON-NEM | Rule 21 AES Non-Export | APPROVED | Battery Storage | 10 | No | 2021-07-27 | 2021-07-27 | 1 | 2021-07-27 | 0 | 2021-07-27 | 2021-07-27 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-07-27 | 2021-07-27 | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-08-09 | N/A | 13
314343 | 92126 | NON-NEM | Rule 21 AES Inadvertant -Export | APPROVED | Battery Storage | 715 | No | 2021-07-27 | 2021-07-27 | 1 | 2021-09-01 | 36 | 2021-07-27 | 2021-07-27 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-07-27 | 2022-02-15 | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-02-18 | N/A | 170
315244 | 91901 | NON-NEM | Rule 21 AES Inadvertant -Export | PENDING AHJ INSPECTION | Battery Storage | 420 | No | 2021-06-16 | 2021-06-16 | 1 | 2021-10-06 | 112 | 2021-07-13 | 2021-07-13 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-06-16 | 2021-06-16 | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
315730 | 92021 | NON-NEM | Rule 21 AES Non-Export | APPROVED | Battery Storage | 15 | No | 2021-07-26 | 2021-07-26 | 1 | 2021-07-26 | 0 | 2021-07-26 | 2021-07-26 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-07-26 | 2021-07-26 | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-08-23 | N/A | 28
315839 | 91901 | NON-NEM | Rule 21 AES Non-Export | APPROVED | Battery Storage | 15 | No | 2021-07-26 | 2021-07-26 | 1 | 2021-07-26 | 0 | 2021-07-26 | 2021-07-26 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-07-26 | 2021-07-26 | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-09-05 | N/A | 41
315841 | 92065 | NON-NEM | Rule 21 AES Non-Export | APPROVED | Battery Storage | 10 | No | 2021-07-26 | 2021-07-26 | 1 | 2021-07-26 | 0 | 2021-07-26 | 2021-07-26 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-07-26 | 2021-07-26 | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-08-29 | N/A | 34
317414 | 92121 | NON-NEM | Rule 21 AES Inadvertant -Export | ISSUES | Battery Storage | 665 | No | 2021-07-27 | 2021-07-27 | 1 |  |  |  |  | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 0
317900 | 92110 | NON-NEM | Rule 21 AES Non-Export | PENDING AHJ INSPECTION | Battery Storage | 250 | No | 2021-07-27 | 2021-07-27 | 1 | 2022-01-12 | 169 | 2022-01-12 | 2022-01-12 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-02-24 | 2022-02-25 | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
318086 | 92029 | NON-NEM | Rule 21 AES Inadvertant -Export | PENDING AHJ INSPECTION | Battery Storage | 140 | No | 2021-07-08 | 2021-07-08 | 1 | 2021-07-28 | 20 | 2021-07-27 | 2021-07-27 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-07-28 |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
318126 | 92028 | NON-NEM | Rule 21 AES Inadvertant -Export | APPROVED | Battery Storage | 210 | No | 2021-07-09 | 2021-07-09 | 1 | 2021-07-28 | 19 | 2021-07-27 | 2021-07-27 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-07-27 | 2021-07-27 | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-12-17 | N/A | 142
318463 | 92028 | NON-NEM | Rule 21 AES Inadvertant -Export | ISSUES | Battery Storage | 210 | No | 2021-07-12 | 2021-07-12 | 1 | 2021-07-28 | 16 | 2021-07-27 | 2021-07-27 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-27 | 2022-04-28 | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
318658 | 92070 | NON-NEM | Rule 21 AES Non-Export | PENDING AHJ INSPECTION | Battery Storage | 10 | No | 2021-07-15 | 2021-07-15 | 1 | 2021-10-07 | 84 | 2021-10-12 | 2021-10-12 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
318852 | 92059 | NON-NEM | Rule 21 AES Non-Export | APPROVED | Battery Storage | 10 | No | 2021-07-15 | 2021-07-15 | 1 | 2021-10-12 | 89 | 2021-10-12 | 2021-10-12 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-03-20 | 2022-03-21 | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-03-31 | N/A | 170
318853 | 92082 | NON-NEM | Rule 21 AES Non-Export | PENDING AHJ INSPECTION | Battery Storage | 10 | No | 2021-07-15 | 2021-07-15 | 1 | 2021-10-07 | 84 | 2021-10-13 | 2021-10-13 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
319172 | 92078 | NON-NEM | Rule 21 AES Inadvertant -Export | PENDING AHJ INSPECTION | Battery Storage | 348 | No | 2021-07-21 | 2021-07-21 | 1 | 2021-07-28 | 7 | 2021-07-28 | 2021-07-28 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
319215 | 92036 | NON-NEM | Rule 21 AES Non-Export | APPROVED | Battery Storage | 10 | No | 2021-07-19 | 2021-07-19 | 1 | 2021-07-26 | 7 | 2021-07-26 | 2021-07-26 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-07-26 | 2021-07-26 | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-09-06 | N/A | 42
319535 | 92028 | NON-NEM | Rule 21 AES Inadvertant -Export | PENDING AHJ INSPECTION | Battery Storage | 140 | No | 2021-07-21 | 2021-07-21 | 1 | 2021-07-28 | 7 | 2021-07-28 | 2021-07-28 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
319561 | 92106 | NON-NEM | Rule 21 AES Non-Export | APPROVED | Battery Storage | 5 | No | 2021-07-21 | 2021-07-21 | 1 | 2021-07-27 | 6 | 2021-07-27 | 2021-07-27 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-07-26 | 2021-07-26 | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-08-22 | N/A | 26
319653 | 92078 | NON-NEM | Rule 21 AES Inadvertant -Export | PENDING AHJ INSPECTION | Battery Storage | 210 | No | 2021-07-22 | 2021-07-22 | 1 | 2021-07-28 | 6 | 2021-07-28 | 2021-08-02 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
319668 | 92026 | NON-NEM | Rule 21 AES Inadvertant -Export | PENDING AHJ INSPECTION | Battery Storage | 490 | No | 2021-07-22 | 2021-07-22 | 1 | 2021-09-09 | 49 | 2021-09-09 | 2021-09-09 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
320017 | 92078 | NON-NEM | Rule 21 AES Export | PENDING AHJ INSPECTION | Battery Storage | 929.5 | No | 2021-07-26 | 2021-07-26 | 1 | 2021-07-28 | 2 | 2021-07-28 | 2021-07-28 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
320395 | 92028 | NON-NEM | Rule 21 AES Inadvertant -Export | APPROVED | Battery Storage | 420 | No | 2021-07-28 | 2021-07-28 | 1 | 2021-08-02 | 5 | 2021-07-28 | 2021-08-02 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-03-15 | 2022-03-16 | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-05 | N/A | 246
321297 | 91950 | NON-NEM | R21-NEX | PENDING AHJ INSPECTION | Internal Combustion Engine | 350 | No | 2021-09-15 | 2021-09-15 | 1 | 2021-10-28 | 43 | 2021-10-21 | 2021-10-28 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
324881 | 92113 | NON-NEM | Rule 21 AES Non-Export | PENDING AHJ INSPECTION | Battery Storage | 60 | No | 2021-09-07 | 2021-09-07 | 1 | 2021-10-06 | 29 | 2021-09-17 | 2021-10-06 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-10-05 | 2021-10-05 | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
325005 | 92028 | NON-NEM | Rule 21 AES Non-Export | APPROVED | Battery Storage | 10 | No | 2021-09-08 | 2021-09-08 | 1 | 2021-10-07 | 29 | 2021-09-16 | 2021-10-07 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-10-07 | 2021-10-07 | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-12-01 | N/A | 55
325084 | 92009 | NON-NEM | Rule 21 AES Non-Export | PENDING AHJ INSPECTION | Battery Storage | 572 | No | 2021-09-09 | 2021-09-09 | 1 | 2021-10-07 | 28 | 2021-09-16 | 2021-10-07 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-10-07 | 2021-10-07 | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
328728 | 92154 | NON-NEM | PENDING | ISSUES | Hydroelectric Turbine | 157 | No | 2021-11-07 | 2021-11-07 | 1 |  |  | 2021-11-09 | 2021-11-09 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 0
329462 | 91935 | NON-NEM | Rule 21 AES Non-Export | APPROVED | Battery Storage | 10 | No | 2021-10-11 | 2021-10-11 | 1 | 2021-10-22 | 11 | 2021-10-22 | 2021-10-22 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-01-05 | 2022-01-06 | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-01-10 | N/A | 80
330017 | 91950 | NON-NEM | Rule 21 AES Non-Export | PENDING FINAL REVIEW | Battery Storage | 29 | No | 2022-10-18 | 2021-10-18 | 1 | 2022-01-24 | 98 | 2021-10-22 | 2021-11-05 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-03 | 2022-04-04 | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
331229 | 92082 | NON-NEM | Rule 21 AES Non-Export | ISSUES | Battery Storage | 9 | No | 2021-10-25 | 2021-10-25 | 1 | 2021-11-29 | 35 | 2021-11-05 | 2021-11-05 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
331911 | 92037 | NON-NEM | PENDING | ISSUES | Battery Storage | 250 | No | 2021-10-29 | 2021-10-29 | 1 |  |  | 2022-01-28 | 2022-01-28 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 0
335034 | 91935 | NON-NEM | Rule 21 AES Non-Export | ISSUES | Battery Storage | 8.96 | No | 2021-11-24 | 2021-11-24 | 1 | 2022-02-22 | 90 | 2021-11-29 | 2021-11-29 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-01-05 | 2022-01-06 | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
335495 | 92082 | NON-NEM | PENDING | ISSUES | Battery Storage | 15 | No | 2021-11-30 | 2021-11-30 | 1 |  |  | 2021-12-08 | 2021-12-08 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 0
336967 | 92025 | NON-NEM | Rule 21 AES Inadvertant -Export | PENDING AHJ INSPECTION | Battery Storage | 174 | No | 2021-12-09 | 2021-12-09 | 1 | 2022-02-08 | 61 | 2021-12-19 | 2021-12-19 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
337936 | 92065 | NON-NEM | Rule 21 AES Non-Export | APPROVED | Battery Storage | 10 | No | 2021-12-16 | 2021-12-16 | 1 | 2022-01-06 | 21 | 2021-12-19 | 2021-12-19 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-01-11 | 2022-01-12 | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-01-18 | N/A | 12
340932 | 92009 | NON-NEM | NEM-FC2 | PENDING AHJ INSPECTION | Fuel Cell | 250 | No | 2022-01-19 | 2022-01-19 | 1 | 2022-03-04 | 44 | 2022-02-10 | 2022-02-10 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-09 | 2022-04-10 | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
341055 | 92009 | NON-NEM | NEM-FC2 | PENDING AHJ INSPECTION | Fuel Cell | 350 | No | 2022-01-20 | 2022-01-20 | 1 | 2022-03-16 | 55 | 2022-03-16 | 2022-03-16 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-09 | 2022-04-10 | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
341094 | 92009 | NON-NEM | NEM-FC2 | PENDING AHJ INSPECTION | Fuel Cell | 500 | No | 2022-01-20 | 2022-01-20 | 1 | 2022-03-16 | 55 | 2022-03-16 | 2022-03-16 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-09 | 2022-04-10 | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
341952 | 91935 | NON-NEM | Rule 21 AES Non-Export | ISSUES | Battery Storage | 10 | No | 2022-02-01 | 2022-02-01 | 1 |  |  | 2022-02-09 | 2022-02-09 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 0
342268 | 92069 | NON-NEM | Rule 21 AES Non-Export | PENDING AHJ INSPECTION | Battery Storage | 10 | No | 2022-02-28 | 2022-02-28 | 1 | 2022-04-04 | 35 | 2022-03-04 | 2022-03-04 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-03 | 2022-04-04 | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
343024 | 92069 | NON-NEM | Rule 21 AES Non-Export | ISSUES | Battery Storage | 10 | No | 2022-02-08 | 2022-02-08 | 1 |  |  | 2022-03-04 | 2022-03-04 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-03-04 | 2022-03-04 | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 0
343979 | 91905 | NON-NEM | Rule 21 AES Non-Export | ISSUES | Battery Storage | 15 | No | 2022-03-04 | 2022-03-04 | 1 |  |  | 2022-03-21 | 2022-03-21 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 0
345310 | 92014 | NON-NEM | PENDING | ISSUES | Battery Storage | 5 | No | 2022-03-11 | 2022-03-11 | 1 |  |  | 2022-03-21 | 2022-03-21 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 0
346707 | 92029 | NON-NEM | R21-NEX | APPROVED | Microturbine - Natural Gas | 65 | No | 2022-03-10 | 2022-03-10 | 1 | 2022-03-20 | 10 | 2022-03-15 | 2022-03-15 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-03-15 | 2022-03-16 | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-03 | N/A | 14
347068 | 91935 | NON-NEM | Rule 21 AES Non-Export | ISSUES | Battery Storage | 10 | No | 2022-03-15 | 2022-03-15 | 1 |  |  | 2022-03-21 | 2022-03-21 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-03-21 |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
349020 | 92028 | NON-NEM | PENDING | INCOMPLETE | Battery Storage | 15 | No | 2022-03-23 | 2022-03-23 | 1 |  |  |  |  | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
349146 | 92067 | NON-NEM | Rule 21 AES Non-Export | ISSUES | Battery Storage | 5 | No | 2022-03-22 | 2022-03-22 | 1 |  |  |  |  | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
349182 | 92078 | NON-NEM | NEM-FC2 | ISSUES | Fuel Cell | 2000 | No | 2022-03-22 | 2022-03-22 | 1 |  |  |  |  | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
349310 | 91935 | NON-NEM | Rule 21 AES Non-Export | ISSUES | Battery Storage | 10 | No | 2022-03-23 | 2022-03-23 | 1 |  |  |  |  | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
350766 | 92028 | NON-NEM | PENDING | INCOMPLETE | Battery Storage | 5 | No | 2022-03-28 | 2022-03-28 | 1 |  |  |  |  | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
351071 | 92024 | NON-NEM | Rule 21 AES Non-Export | INCOMPLETE | Battery Storage | 20 | No | 2022-03-30 | 2022-03-30 | 1 |  |  |  |  | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A

## OP4 Processing Cost
2022 Q1 Processing Cost Summary (≤ 1MW Rule 21 Non-NEM)
New Rule 21 Non-NEM projects Using “midpoint” of pay ranges for the labor rate component (based on the employees included in the “stage of processing” buckets)
Stage of Processing: | Number Evaluated | Total Cost per Stage | Average Cost per Stage
Application Review and Deficiency Clearing | 54 | 5084 | 94.1481
Technical Review/Engineering | 54 | 8942 | 165.5926
Agreement Execution, Insurance Requirements, Accounting/Costing | 54 | 5100 | 94.4444
Field Inspection | 32 | 2862 | 89.4375
Post Agreement Execution to PTO | 31 | 1863 | 60.0968
| Average Cost per Project* |  | 503.7195
* Based on average size of 10kW AES projects approved thorugh Q1 2022
**Costs are based on estimated time spent reviewing prior queued projects

## NEM-ST AGG1_Bill Method
SDG&E's Rule 21 Processing Timelines Q1 2022
NEM-ST AGG1_Bill Method
INTERCONNECTION TYPE | APP ID | PROJECT SIZE (kW) | TECHNOLOGY TYPE | DIIS APPLICATION STATUS | APPLICATION SUBMITTED | APPLICATION DEEMED COMPLETE | CUST GEN. ENG REVIEW SENT | CUST GEN. ENG REVIEW COMPLETED | SENT TO DP | RECEIVED DP APPROVAL | TRANSFORMER CHANGE YES/NO | ELECTRICAL DISTRIBUTION UPGRADE YES/NO | ICA SENT | ICA RECEIVED | ALLOCATION FORM SENT | ALLOCATION FORM RECEIVED | ALLOCATION FORM APPROVED | AHJ INSPECTION RECEIVED | FINAL FIELD INSPECTION | PTO PROVIDED | EXECUTED ICA SENT TO CUSTOMER* | ALLOCATION FORM SENT TO BILLING | Calendar Days from Application Deemed Complete Date to PTO Date
NEMA | 296922 | 273.836 | Solar PV | PENDING AHJ INSPECTION | 2020-12-30 | 2021-01-15 | N/A | N/A | 2021-01-15 | 2021-01-19 | NO | NO | 2021-01-15 | 2021-01-20 | 2021-01-04 | 2021-01-14 | 2021-01-14
NEMA | 297420 | 57.517 | Solar PV | APPROVED | 2021-01-07 | 2021-01-19 | N/A | N/A | 2021-01-19 | 2021-01-20 | NO | NO | 2021-01-19 | 2021-01-15 | 2021-01-08 | 2021-01-15 | 2021-01-15 | 2021-01-22 | 2021-01-25 | 2021-01-25 | 2021-01-26 | 2021-01-26 | 6
NEMA | 298637 | 14.01 | Solar PV | APPROVED | 2021-01-20 | 2021-01-25 | N/A | N/A | NA | NA | NA | NA | NA | NA | 2021-01-21 | 2021-01-25 | 2021-01-25 | 2020-12-21 | 2021-01-25 | 2021-07-02 | N/A | 2021-07-06 | 158
NEMA | 297175 | 134.816 | Solar PV | APPROVED | 2021-01-05 | 2021-02-01 | N/A | N/A | 2021-02-01 | 2021-02-02 | NO | NO | 2021-02-01 | 2021-02-12 | 2021-01-06 | 2021-01-20 | 2021-01-20 | 2020-12-14 | 2021-02-02 | 2021-02-12 | 2021-02-16 | 2021-02-16 | 11
NEMA | 298210 | 86.127 | Solar PV | APPROVED | 2021-01-20 | 2021-02-01 | N/A | N/A | 2021-02-01 | 2021-02-02 | NO | NO | 2021-02-01 | 2021-02-16 | 2021-01-21 | 2021-01-22 | 2021-01-22 | 2021-05-04 | 2021-05-05 | 2021-05-05 | 2021-05-06 | 2021-05-06 | 93
NEMA | 297340 | 19.879 | Solar PV | APPROVED | 2021-01-06 | 2021-02-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-01-27 | 2021-02-02 | 2021-02-02 | 2021-03-08 | N/A | 2021-03-08 | N/A | 2021-03-09 | 34
NEMA | 299670 | 10.977 | Solar PV | APPROVED | 2021-02-02 | 2021-02-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-02-02 | 2021-02-04 | 2021-02-04 | 2021-02-08 | 2021-02-08 | 2021-03-11 | N/A | 2021-03-19 | 35
NEMA | 300112 | 4.849 | Solar PV | APPROVED | 2021-02-08 | 2021-02-11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-02-09 | 2021-02-11 | 2021-02-11 | 2021-02-05 | 2021-02-16 | 2021-07-20 | N/A | 2021-07-21 | 159
NEMA | 300597 | 10.118 | Solar PV | APPROVED | 2021-02-11 | 2021-02-17 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-02-11 | 2021-02-11 | 2021-02-16 | 2021-02-12 | 2021-02-12 | 2021-03-23 | N/A | 2021-03-24 | 34
NEMA | 301498 | 20.36 | Solar PV | APPROVED | 2021-02-23 | 2021-03-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-02-23 | 2021-03-04 | 2021-03-04 | 2021-03-16 | 2021-03-16 | 2021-03-26 | N/A | 2021-03-29 | 22
NEMA | 304774 | 15.177 | Solar PV | APPROVED | 2021-03-08 | 2021-03-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-03-19 | 2021-03-08 | 2021-03-08 | 2021-03-10 | N/A | 2021-05-04 | N/A | 2021-05-05 | 57
NEMA | 299010 | 26.854 | Solar PV | APPROVED | 2021-02-16 | 2021-03-12 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-02-17 | 2021-03-12 | 2021-03-12 | 2021-06-30 | 2021-07-01 | 2021-07-01 | N/A | 2021-07-02 | 111
NEMA | 299106 | 26.854 | Solar PV | APPROVED | 2021-02-16 | 2021-03-12 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-02-17 | 2021-03-12 | 2021-03-12 | 2021-06-30 | 2021-07-01 | 2021-03-30 | N/A | 2021-03-21 | 18
NEMA | 295957 | 14.229 | Solar PV | APPROVED | 2021-02-26 | 2021-03-22 | N/A | N/A | 2020-12-28 | 2021-12-28 | YES | YES | 2021-03-22 | 2021-03-22 | 2021-02-26 | 2021-03-22 | 2021-03-22 | 2021-01-13 | 2021-03-23 | 2021-03-23 | 2021-03-24 | 2021-03-24 | 1
NEMA | 305367 | 39.995 | Solar PV | APPROVED | 2021-03-12 | 2021-03-22 | N/A | N/A | 2021-03-22 | 2021-03-26 | NO | NO | 2021-03-22 | 2021-03-22 | 2021-03-22 | 2021-03-22 | 2021-03-22 | 2021-03-24 | 2021-03-25 | 2021-03-26 | 2021-03-29 | 2021-03-29 | 4
NEMA | 284099 | 308.119 | Solar PV | APPROVED | 2021-03-25 | 2021-03-25 | N/A | N/A | N/A | N/A | N/A | N/A | 2021-03-31 | 2021-07-23 | N/A | 2021-04-02 | 2021-04-02 | 2021-07-09 | 2021-08-09 | 2021-08-11 | 2021-08-12 | 2021-08-12 | 139
NEMA | 297066 | 10.201 | Solar PV | APPROVED | 2021-03-03 | 2021-03-26 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-03-29 | 2021-03-25 | 2021-03-25 | 2021-01-08 | N/A | 2021-05-05 | N/A | 2021-05-06 | 40
NEMA | 304366 | 69.754 | Solar PV | APPROVED | 2021-03-08 | 2021-03-29 | N/A | N/A | 2021-03-29 | 2021-03-30 | NO | NO | 2021-03-29 | 2021-03-26 | 2021-03-08 | 2021-03-23 | 2021-03-23 | 2021-07-16 | 2021-07-19 | 2021-07-20 | 2021-07-21 | 2021-07-21 | 113
NEMA | 301890 | 7.932 | Solar PV | APPROVED | 2021-02-26 | 2021-04-07 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-04-21 | 2021-04-02 | 2021-04-02 | 2021-03-18 | N/A | 2021-04-20 | N/A | 2021-04-20 | 13
NEMA | 307029 | 19.884 | Solar PV | APPROVED | 2021-04-05 | 2021-04-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-04-06 | 2021-04-07 | 2021-04-07 | 2021-04-26 | 2021-04-26 | 2021-05-25 | N/A | 2021-05-26 | 47
NEMA | 306645 | 8.049 | Solar PV | APPROVED | 2021-04-09 | 2021-04-12 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-04-22 | 2021-04-12 | 2021-04-12 | 2021-04-28 | 2021-04-28 | 2021-04-29 | N/A | 2021-04-30 | 17
NEMA | 306808 | 109.644 | Battery Storage + Solar PV | PENDING AHJ INSPECTION | 2021-03-31 | 2021-04-21 | N/A | N/A | 2021-04-29 | 2021-04-30 | NO | NO | 2021-04-29 |  | 2021-04-15 | 2021-04-21 | 2021-04-21
NEMA | 309474 | 8.874 | Solar PV | PENDING AHJ INSPECTION | 2021-04-21 | 2021-04-23 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-04-22 | 2021-04-22 | 2021-04-22 |  |  |  | N/A
NEMA | 305753 | 7.403 | Solar PV | APPROVED | 2021-03-26 | 2021-04-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-04-28 | 2021-04-28 | 2021-04-13 | 2021-04-13 | 2021-04-28 | N/A | 2021-04-29 | 1
NEMA | 306694 | 40.87 | Solar PV | APPROVED | 2021-03-30 | 2021-04-28 | N/A | N/A | 2021-04-29 | 2021-04-30 | NO | NO | 2021-04-29 | 2021-04-30 | 2021-03-31 | 2021-04-27 | 2021-04-28 | 2021-04-05 | 2021-05-03 | 2021-05-04 | 2021-05-05 | 2021-05-06 | 6
NEMA | 306634 | 31.834 | Solar PV | APPROVED | 2021-03-30 | 2021-04-29 | 2021-05-03 | 2021-05-03 | 2021-05-03 | 2021-05-07 | NO | NO | 2021-05-03 | 2021-07-07 | 2021-03-30 | 2021-04-29 | 2021-04-29 | 2021-06-22 | 2021-06-23 | 2021-07-08 | 2021-07-09 | 2021-07-09 | 70
NEMA | 312537 | 15.917 | Solar PV | APPROVED | 2021-05-14 | 2021-05-14 | N/A | N/A | N/A | N/A | NO | NO | N/A | N/A | N/A | 2021-05-14 | 2021-05-14 | 2021-05-19 | N/A | 2021-05-19 | N/A | 2021-05-20 | 5
NEMA | 307984 | 14.453 | Solar PV | APPROVED | 2021-05-10 | 2021-05-12 | N/A | N/A | N/A | N/A | NO | NO | N/A | N/A | N/A | 2021-05-10 | 2021-05-10 | 2021-05-03 | N/A | 2021-05-12 | N/A | 2021-05-13 | 1
NEMA | 310427 | 43.141 | Solar PV | APPROVED | 2021-05-03 | 2021-05-20 | 2021-05-06 | 2021-05-06 | 2021-05-13 | 2021-05-20 | NO | NO | 2021-05-06 | 2021-05-06 | 2021-05-03 | 2021-05-04 | 2021-05-06 | 2021-04-29 | 2021-05-24 | 2021-05-25 | 2021-05-26 | 2021-05-26 | 5
NEMA | 310701 | 6.532 | Solar PV | APPROVED | 2021-05-20 | 2021-05-20 | N/A | N/A | N/A | N/A | NO | NO | N/A | N/A | N/A | 2021-05-20 | 2021-05-20 | 2021-05-05 | N/A | 2021-05-20 | N/A | 2021-05-21 | 1
NEMA | 307138 | 17.955 | Solar PV | APPROVED | 2021-05-24 | 2021-05-24 | N/A | N/A | N/A | N/A | NO | NO | N/A | N/A | N/A | 2021-05-24 | 2021-05-24 | 2021-05-13 | N/A | 2021-05-24 | N/A | 2021-05-25 | 1
NEMA | 313246 | 139.084 | Solar PV | APPROVED | 2021-05-25 | 2021-05-27 | 2021-05-27 | 2021-06-02 | 2021-05-27 | 2021-06-01 | YES | YES | 2021-05-27 | 2021-05-27 | 2021-05-27 | 2021-05-27 | 2021-05-27 | 2022-01-11 | 2022-01-13 | 2022-01-13 | 2022-01-14 | 2022-01-18 | 231
NEMA | 312477 | 27.71 | Solar PV | APPROVED | 2021-05-13 | 2021-05-28 | 2021-05-28 | 2021-05-28 | N/A | N/A | YES | YES | N/A | N/A | 2021-05-13 | 2021-05-17 | 2021-05-17 | 2021-04-16 | 2021-06-02 | 2021-06-02 | N/A | 2021-06-03 | 5
NEMA | 312904 | 4.839 | Solar PV | APPROVED | 2021-06-03 | 2021-06-03 | N/A | N/A | N/A | N/A | NO | NO | N/A | N/A | N/A | 2021-06-02 | 2021-06-02 | 2021-05-26 | N/A | 2021-06-04 | N/A | 2021-06-07 | 1
NEMA | 313107 | 52.101 | Solar PV | APPROVED | 2021-05-20 | 2021-06-08 | 2021-06-08 | 2021-06-08 | 2021-06-08 | 2021-06-10 | NO | NO | 2021-05-27 | 2021-05-27 | 2021-05-24 | 2021-06-03 | 2021-06-03 | 2021-07-14 | 2021-07-15 | 2021-07-15 | 2021-07-16 | 2021-07-16 | 37
NEMA | 312507 | 264.762 | Solar PV | APPROVED | 2021-05-14 | 2021-06-09 | 2021-06-10 | 2021-06-10 | 2021-06-10 | 2021-06-11 | NO | NO | 2021-06-10 | 2021-06-10 | 2021-05-20 | 2021-06-08 | 2021-06-09 | 2021-09-03 | 2021-09-07 | 2021-09-07 | 2021-09-08 | 2021-09-08 | 90
NEMA | 312971 | 114.437 | Solar PV | APPROVED | 2021-05-20 | 2021-06-09 | 2021-06-14 | 2021-06-14 | 2021-06-14 | 2021-06-15 | NO | NO | 2021-06-14 | 2021-06-28 | 2021-05-21 | 2021-06-09 | 2021-06-09 | 2021-09-03 | 2021-09-27 | 2021-09-28 | 2021-09-28 | 2021-09-29 | 111
NEMA | 313102 | 446.798 | Solar PV | APPROVED | 2021-05-20 | 2021-06-09 | 2021-06-10 | 2021-06-10 | 2021-06-10 | 2021-06-11 | NO | NO | 2021-06-10 | 2021-06-10 | 2021-05-24 | 2021-06-09 | 2021-06-09 | 2021-10-01 | 2021-10-04 | 2021-10-29 | 2021-11-01 | 2021-11-01 | 142
NEMA | 315915 | 4.155 | Solar PV | APPROVED | 2021-06-22 | 2021-06-22 | N/A | N/A | N/A | N/A | NO | NO | N/A | N/A | N/A | 2021-06-21 | 2021-06-21 | 2021-05-27 | N/A | 2021-06-22 | N/A | 2021-06-23 | 1
NEMA | 315959 | 38.751 | Solar PV | APPROVED | 2021-06-18 | 2021-06-24 | 2021-06-24 | 2021-06-24 | 2021-06-24 | 2021-06-24 | NO | NO | 2021-06-24 | 2021-06-24 | 2021-06-23 | 2021-06-23 | 2021-06-23 | 2021-01-13 | 2021-06-25 | 2021-06-25 | 2021-06-28 | 2021-06-28 | 1
NEMA | 305275 | 152.373 | Solar PV | APPROVED | 2021-04-06 | 2021-06-29 | 2021-06-29 | 2021-06-29 | 2021-06-29 | 2021-07-08 | NO | NO | 2021-06-29 | 2021-06-29 | 2021-04-07 | 2021-06-22 | 2021-06-22 | 2021-06-03 | 2021-06-30 | 2021-07-08 | 2021-07-09 | 2021-07-09 | 9
NEMA | 309848 | 21.793 | Solar PV | APPROVED | 2021-04-24 | 2021-07-08 | N/A | N/A | N/A | N/A | NO | NO | N/A | N/A | N/A | 2021-06-18 | 2021-06-18 | 2021-05-13 | N/A | 2021-07-08 | N/A | 2021-07-08 | 1
NEMA | 317934 | 22.023 | Solar PV | APPROVED | 2021-07-15 | 2021-07-15 | N/A | N/A | N/A | N/A | NO | NO | N/A | N/A | N/A | 2021-07-15 | 2021-07-15 | 2021-06-30 | N/A | 2021-07-15 | N/A | 2021-07-16 | 1
NEMA | 274981 | 7.201 | Solar PV | APPROVED | 2021-06-23 | 2021-07-26 | N/A | N/A | N/A | N/A | NO | NO | N/A | N/A | N/A | 2021-07-26 | 2021-07-26 | 2020-12-11 | N/A | 2021-07-29 | N/A | 2021-07-29 | 3
NEMA | 317843 | 369.027 | Solar PV | APPROVED | 2021-07-07 | 2021-07-26 | 2021-07-30 | 2021-07-30 | 2021-07-30 | 2021-08-03 | NO | NO | 2021-07-30 | 2021-08-02 | 2021-07-14 | 2021-07-16 | 2021-07-26 | 2022-03-12 | 2022-03-18 | 2022-03-21 | 2022-03-21 | 2022-03-22 | 238
NEMA | 318267 | 14.6 | Solar PV | APPROVED | 2021-07-09 | 2021-07-26 | N/A | N/A | N/A | N/A | NO | NO | N/A | N/A | 2021-07-09 | 2021-07-26 | 2021-07-26 | 2021-08-11 | N/A | 2021-08-11 | N/A | 2021-08-12 | 16
NEMA | 314442 | 117.51 | Solar PV | APPROVED | 2021-07-26 | 2021-07-30 | 2021-07-30 | 2021-07-30 | 2021-07-30 | 2021-08-03 | NO | NO | 2021-07-30 | 2021-07-30 | 2021-08-09 | 2021-08-13 | 2021-08-13 | 2021-07-16 | 2021-08-16 | 2021-08-16 | 2021-08-17 | 2021-08-17 | 17
NEMA | 320006 | 93.171 | Solar PV | APPROVED | 2021-07-26 | 2021-08-09 | 2021-08-13 | 2021-08-13 | 2021-08-13 | 2021-08-17 | NO | NO | N/A | 2021-08-12 | 2021-07-31 | 2021-08-09 | 2021-08-09 | 2021-08-13 | 2021-08-16 | 2021-08-23 | 2021-08-24 | 2021-08-24 | 14
NEMA | 312520 | 20.973 | Battery Storage + Solar PV | APPROVED | 2021-07-29 | 2021-08-09 | 2021-08-13 | 2021-08-13 | N/A | N/A | NO | NO | N/A | N/A | 2021-08-03 | 2021-08-09 | 2021-08-09 | 2021-07-28 | N/A | 2021-08-13 | N/A | 2021-08-16 | 4
NEMA | 308211 | 140.907 | Solar PV | APPROVED | 2021-08-02 | 2021-08-23 | 2021-08-24 | 2021-08-24 | 2021-08-24 | 2021-08-25 | NO | NO | 2021-08-24 | 2001-08-26 | 2021-08-05 | 2021-08-23 | 2021-08-23 | 2021-07-30 | 2021-08-25 | 2021-09-03 | 2021-09-07 | 2021-09-07 | 11
NEMA | 323111 | 13.643 | Solar PV | APPROVED | 2021-08-24 | 2021-08-24 | N/A | N/A | N/A | N/A | NO | NO | N/A | N/A | N/A | 2021-08-24 | 2021-08-24 | 2021-08-24 | N/A | 2021-08-24 | N/A | 2021-08-25 | 1
NEMA | 314610 | 3.647 | Solar PV | APPROVED | 2021-06-07 | 2021-08-26 | N/A | N/A | N/A | N/A | NO | NO | N/A | N/A | 2021-06-17 | 2021-08-26 | 2021-08-26 | 2021-04-27 | N/A | 2021-10-13 | N/A | 2021-10-14 | 48
NEMA | 310181 | 119.587 | Solar PV | APPROVED | 2021-04-28 | 2021-08-27 | 2021-08-27 | 2021-08-27 | 2021-08-27 | 2021-08-30 | NO | NO | 2021-08-27 | 2021-09-08 | 2021-04-30 | 2021-08-25 | 2021-08-25 | 2021-10-12 | 2021-10-13 | 2021-10-13 | 2021-10-14 | 2021-10-14 | 47
NEMA | 318150 | 152.645 | Solar PV | PENDING AHJ INSPECTION | 2021-07-19 | 2021-08-31 | 2021-09-01 | 2021-09-01 | 2021-09-01 | 2021-09-02 | NO | NO | 2021-09-01 |  | 2021-07-21 | 2021-08-31 | 2021-08-31
NEMA | 321498 | 12.84 | Solar PV | APPROVED | 2021-09-01 | 2021-09-01 | N/A | N/A | N/A | N/A | NO | NO | N/A | N/A | N/A | 2021-09-01 | 2021-09-01 | 2021-08-10 | N/A | 2021-09-02 | N/A | 2021-09-07 | 1
NEMA | 324938 | 4.899 | Solar PV | APPROVED | 2021-09-10 | 2021-09-20 | N/A | N/A | N/A | N/A | NO | NO | N/A | N/A | 2021-09-20 | 2021-09-20 | 2021-09-20 | 2021-09-09 | 2021-09-09 | 2021-09-21 | N/A | 2021-09-22 | 1
NEMA | 316448 | 5.354 | Solar PV | APPROVED | 2021-08-18 | 2021-09-23 | N/A | N/A | N/A | N/A | NO | NO | N/A | N/A | N/A | 2021-09-23 | 2021-09-23 | 2021-11-22 | N/A | 2021-12-14 | N/A | 2021-12-15 | 82
NEMA | 325935 | 621.971 | Solar PV | PENDING AHJ INSPECTION | 2021-09-16 | 2021-10-04 | 2021-10-04 | 2021-10-04 | 2021-10-04 | 2021-10-06 | NO | NO | 2021-10-04 |  | 2021-09-16 | 2021-09-30 | 2021-10-01
NEMA | 328885 | 17.848 | Solar PV | APPROVED | 2021-10-06 | 2021-10-06 | N/A | N/A | N/A | N/A | NO | NO | N/A | N/A | N/A | 2021-10-08 | 2021-10-13 | 2021-10-06 | 2021-10-06 | 2021-10-13 | N/A | 2021-10-14 | 7
NEMA | 328059 | 4.904 | Solar PV | APPROVED | 2021-09-30 | 2021-10-07 | N/A | N/A | N/A | N/A | NO | NO | N/A | N/A | N/A | 2021-10-07 | 2021-10-07 | 2021-10-07 | N/A | 2021-10-07 | N/A | 2021-10-08 | 1
NEMA | 327672 | 3.625 | Solar PV | APPROVED | 2021-10-06 | 2021-10-07 | N/A | N/A | N/A | N/A | NO | NO | N/A | N/A | N/A | 2021-10-06 | 2021-10-06 | 2021-09-15 | N/A | 2021-10-07 | N/A | 2021-10-11 | 1
NEMA | 322187 | 9.533 | Solar PV | APPROVED | 2021-09-03 | 2021-10-08 | N/A | N/A | N/A | N/A | NO | NO | N/A | N/A | N/A | 2021-10-08 | 2021-10-08 | 2021-08-10 | 2021-08-10 | 2021-10-08 | N/A | 2021-10-11 | 1
NEMA | 329679 | 5.298 | Solar PV | APPROVED | 2021-10-12 | 2021-10-18 | N/A | N/A | N/A | N/A | NO | NO | N/A | N/A | 2021-10-13 | 2021-10-18 | 2021-10-18 | 2021-10-07 | N/A | 2021-10-19 | N/A | 2021-10-20 | 1
NEMA | 329862 | 7.087 | Solar PV | APPROVED | 2021-10-18 | 2021-10-20 | N/A | N/A | N/A | N/A | NO | NO | N/A | N/A | N/A | 2021-10-20 | 2021-10-20 | 2021-10-11 | N/A | 2021-10-20 | N/A | 2021-10-21 | 1
NEMA | 328593 | 3.539 | Solar PV | APPROVED | 2021-10-03 | 2021-10-21 | N/A | N/A | N/A | N/A | NO | NO | N/A | N/A | 2021-10-05 | 2021-10-05 | 2021-10-05 | 2021-10-04 | 2021-10-22 | 2021-10-22 | N/A | 2021-10-25 | 1
NEMA | 330954 | 6.831 | Solar PV | APPROVED | 2021-10-21 | 2021-10-25 | N/A | N/A | N/A | N/A | NO | NO | N/A | N/A | 2021-10-22 | 2021-10-22 | 2021-10-22 | 2021-10-28 | N/A | 2021-10-28 | N/A | 2021-10-29 | 3
NEMA | 331736 | 12.128 | Solar PV | APPROVED | 2021-10-28 | 2021-10-28 | N/A | N/A | N/A | N/A | NO | NO | N/A | N/A | N/A | 2021-10-28 | 2021-10-28 | 2022-01-28 | N/A | 2022-01-31 | N/A | 2022-01-31 | 95
NEMA | 328134 | 4.889 | Solar PV | APPROVED | 2021-10-11 | 2021-10-29 | N/A | N/A | N/A | N/A | NO | NO | N/A | N/A | 2021-10-13 | 2021-10-27 | 2021-10-29 | 2021-09-29 | 2021-10-12 | 2021-10-29 | N/A | 2021-10-30 | 1
NEMA | 331497 | 30.09 | Solar PV | APPROVED | 2021-10-27 | 2021-11-03 | 2021-11-03 | 2021-11-03 | 2021-11-03 | 2021-11-03 | NO | NO | 2021-11-03 | 2021-11-30 | 2021-11-29 | 2021-11-29 | 2021-11-29 | 2022-02-23 | 2022-03-15 | 2022-03-16 | 2022-03-17 | 2022-03-17 | 133
NEMA | 332384 | 8.649 | Solar PV | APPROVED | 2021-11-04 | 2021-11-08 | N/A | N/A | N/A | N/A | NO | NO | N/A | N/A | 2021-11-05 | 2021-11-08 | 2021-11-08 | 2021-11-01 | N/A | 2021-11-08 | N/A | 2021-11-09 | 1
NEMA | 332157 | 4.614 | Solar PV | APPROVED | 2021-11-12 | 2021-11-18 | N/A | N/A | N/A | N/A | NO | NO | N/A | N/A | N/A | 2021-11-18 | 2021-11-18 | 2021-11-24 | N/A | 2021-11-24 | N/A | 2021-11-29 | 6
NEMA | 333201 | 7.195 | Solar PV | APPROVED | 11/10/20121 | 2021-11-18 | N/A | N/A | N/A | N/A | NO | NO | N/A | N/A | N/A | 2021-11-18 | 2021-11-18 | 2021-11-17 | N/A | 2021-11-18 | N/A | 2021-11-24 | 1
NEMA | 335598 | 5.465 | Solar PV | APPROVED | 2021-11-30 | 2021-12-06 | N/A | N/A | N/A | N/A | NO | NO | N/A | N/A | N/A | 2021-12-06 | 2021-12-06 | 2021-12-03 | 2021-12-06 | 2021-12-06 | N/A | 2021-12-07 | 1
NEMA | 335575 | 7.285 | Solar PV | APPROVED | 2021-11-30 | 2021-12-08 | N/A | N/A | N/A | N/A | NO | NO | N/A | N/A | 2021-12-01 | 2021-12-08 | 2021-12-08 | 2021-11-29 | N/A | 2021-12-08 | N/A | 2021-12-09 | 1
NEMA | 331221 | 88.513 | Solar PV | APPROVED | 2021-10-26 | 2021-12-10 | 2021-12-10 | 2021-12-10 | 2021-12-10 | 2021-12-15 | NO | NO | 2021-12-10 | 2021-12-10 | 2021-10-26 | 2021-12-02 | 2021-12-02 | 2021-10-07 | 2021-12-13 | 2021-12-15 | 2021-12-16 | 2021-12-16 | 5
NEMA | 304353 | 100.064 | Solar PV | PENDING SDGE INSPECTION | 2021-12-07 | 2021-12-10 | 2021-12-10 | 2021-12-10 | 2021-12-10 | 2021-12-15 | NO | NO | 2021-12-10 | 2022-03-21 | 2022-02-22 | 2022-03-21 | 2022-03-21 | 2022-04-05
NEMA | 336260 | 6.394 | Solar PV | APPROVED | 2021-12-09 | 2021-12-12 | N/A | N/A | N/A | N/A | NO | NO | N/A | N/A | 2021-12-10 | 2021-12-12 | 2021-12-12 | 2021-10-25 | N/A | 2021-12-13 | N/A | 2021-12-14 | 1
NEMA | 334398 | 23.308 | Solar PV | APPROVED | 2021-11-19 | 2021-12-15 | N/A | N/A | N/A | N/A | NO | NO | N/A | N/A | 2021-11-22 | 2021-12-15 | 2021-12-15 | 2021-11-19 | N/A | 2021-12-16 | N/A | 2021-12-17 | 1
NEMA | 336525 | 5.012 | Solar PV | APPROVED | 2021-12-07 | 2021-12-20 | N/A | N/A | N/A | N/A | NO | NO | N/A | N/A | 2021-12-09 | 2021-12-20 | 2021-12-20 | 2021-12-28 | N/A | 2021-12-28 | N/A | 2021-12-29 | 8
NEMA | 281969 | 151.145 | Solar PV | APPROVED | 2021-03-03 | 2021-12-27 | 2021-12-27 | 2021-12-27 | 2021-12-27 | 2021-12-28 | NO | NO | 2021-12-27 | 2021-12-28 | 2021-03-23 | 2021-12-27 | 2021-12-29 | 2021-12-27 | 2021-12-30 | 2022-01-04 | 2022-01-05 | 2021-01-05 | 8
NEMA | 336325 | 17.344 | Solar PV | APPROVED | 2021-12-22 | 2021-12-29 | N/A | N/A | N/A | N/A | NO | NO | N/A | N/A | 2021-12-27 | 2021-12-29 | 2021-12-29 | 2021-12-22 | 2021-12-30 | 2021-12-30 | N/A | 2022-01-03 | 1
NEMA | 339391 | 4.849 | Solar PV | APPROVED | 2022-01-03 | 2022-01-05 | N/A | N/A | N/A | N/A | NO | NO | N/A | N/A | 2022-01-04 | 2022-01-05 | 2022-01-05 | 2022-01-04 | N/A | 2022-01-05 | N/A | 2022-01-06 | 1
NEMA | 329795 | 89.192 | Solar PV | APPROVED | 2021-10-28 | 2022-01-13 | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2021-12-29 | NO | NO | 2021-12-29 | 2022-01-21 | 2021-11-03 | 2021-11-05 | 2021-11-05 | 2022-01-18 | 2022-01-20 | 2022-01-21 | 2022-01-24 | 2021-01-24 | 8
NEMA | 337953 | 100.101 | Solar PV | PENDING AHJ INSPECTION | 2021-12-16 | 2022-01-18 | 2022-01-18 | 2022-01-18 | 2022-01-18 | 2022-01-24 | NO | NO | 2022-01-18 | 2022-01-24 | 2021-12-19 | 2022-01-13 | 2022-01-14
NEMA | 339743 | 15.838 | Solar PV | APPROVED | 2022-01-06 | 2022-01-18 | N/A | N/A | N/A | N/A | NO | NO | N/A | N/A | 2022-01-06 | 2022-01-18 | 2022-01-18 | 2022-01-18 | 2022-01-24 | 2022-01-24 | N/A | 2022-01-25 | 6
NEMA | 339742 | 12.081 | Solar PV | APPROVED | 2022-01-06 | 2022-01-21 | N/A | N/A | N/A | N/A | NO | NO | N/A | N/A | 44567 | 44582 | 44582 | 2022-01-25 | 2022-01-27 | 2022-01-28 | N/A | 2022-01-28 | 7
NEMA | 340708 | 42.636 | Solar PV | PENDING AHJ INSPECTION | 2022-01-14 | 2022-01-27 | 44588 | 44588 | 44588 | 44596 | NO | NO | 44588 |  | 44589 | 44579 | 44580
NEMA | 341046 | 5.905 | Solar PV | APPROVED | 2022-01-20 | 2022-01-31 | N/A | N/A | N/A | N/A | NO | NO | N/A | N/A | N/A | 44592 | 44592 | 2022-02-24 | N/A | 2022-02-24 | N/A | 2022-02-25 | 24
NEMA | 337018 | 36.706 | Solar PV | PENDING AHJ INSPECTION | 2021-12-17 | 2022-02-04 | 44596 | 44596 | 44596 | 44600 | NO | NO | 44596 |  | 44547 | 44592 | 44592
NEMA | 338446 | 84.449 | Solar PV | APPROVED | 2022-01-05 | 2022-02-04 | 44596 | 44596 | 44596 | 44600 | NO | NO | 44596 | 44602 | 44566 | 44588 | 44589 | 2022-02-07 | 2022-02-09 | 2022-02-10 | 2022-02-11 | 2022-02-11 | 6
NEMA | 343103 | 15.813 | Solar PV | APPROVED | 2022-02-08 | 2022-02-09 | N/A | N/A | N/A | N/A | NO | NO | N/A | N/A | 44601 | 44601 | 44601 | 2022-02-11 | N/A | 2022-02-11 | N/A | 2022-02-11 | 2
NEMA | 336749 | 128.471 | Solar PV | PENDING AHJ INSPECTION | 2021-12-08 | 2022-02-16 | 2022-02-18 | 2022-02-18 | 2022-02-18 | 2022-02-28 | NO | NO | 2022-02-18 | 2022-02-18 | 2021-02-10 | 2022-02-15 | 2022-02-16
NEMA | 339835 | 9.448 | Solar PV | APPROVED | 2022-01-07 | 2022-03-01 | N/A | N/A | N/A | N/A | NO | NO | N/A | N/A | N/A | 2022-02-16 | 2022-02-16 | 2022-01-13 | 2022-03-03 | 2022-03-03 | N/A | 2022-03-04 | 2
NEMA | 318779 | 36.003 | Solar PV | APPROVED | 2021-07-15 | 2022-03-03 | 2022-03-03 | 2022-03-03 | 2022-03-03 | 2022-03-08 | NO | NO | 2022-03-03 | 2022-03-03 | 2021-07-23 | 2022-02-24 | 2022-02-24 | 2022-01-24 | 2022-03-03 | 2022-03-08 | 2022-03-09 | 2022-03-09 | 5
NEMA | 332854 | 17.297 | Solar PV | APPROVED | 2022-02-22 | 2022-03-03 | N/A | N/A | N/A | N/A | NO | NO | N/A | N/A | N/A | 2022-03-02 | 2022-03-02 | 2022-02-28 | N/A | 2022-03-03 | N/A | 2022-03-04 | 1
NEMA | 345847 | 5.215 | Solar PV | APPROVED | 2022-03-03 | 2022-03-14 | 2022-03-14 | 2022-03-14 | N/A | N/A | NO | NO | N/A | N/A | 2022-03-04 | 2022-03-10 | 2022-03-14 | 2022-02-23 | 2022-03-15 | 2022-03-16 | 2022-03-17 | 2022-03-17 | 2
NEMA | 333926 | 27.819 | Battery Storage + Solar PV | APPROVED | 2022-03-07 | 2022-03-14 | 2022-03-14 | 2022-03-14 | N/A | N/A | NO | NO | N/A | N/A | 2022-03-08 | 2022-03-10 | 2022-03-14 | 2022-02-04 | N/A | 2022-03-15 | 2022-03-16 | 2022-03-16 | 1
NEMA | 345038 | 18.378 | Solar PV | PENDING AHJ INSPECTION | 2022-03-07 | 2022-03-14 | 2022-03-14 | 2022-03-14 | N/A | N/A | NO | NO | N/A | N/A | 2022-03-08 | 2022-03-10 | 2022-03-14
NEMA | 304353 | 100.064 | Solar PV | PENDING AHJ INSPECTION | 2021-12-07 | 2022-03-22 | 2022-03-22 | 2022-03-22 | 2021-12-10 | 2021-12-15 | NO | NO | 2021-12-10 | 2022-03-21 | 2022-02-22 | 2022-03-18 | 2022-03-21
NEMA | 337161 | 104.068 | Solar PV | PENDING AHJ INSPECTION | 2021-12-10 | 2022-03-22 | 2022-03-22 | 2022-03-22 | 2022-03-22 | 2022-03-29 | NO | NO | 2022-03-22 |  | 2022-02-19 | 2022-03-21 | 2022-03-21
NEMA | 346348 | 18.283 | Solar PV | APPROVED | 2022-03-08 | 2022-03-24 | 2022-03-24 | 2022-03-24 | N/A | N/A | NO | NO | N/A | N/A | 2022-03-10 | 2022-03-22 | 2022-03-24 | 2022-02-25 | 2022-03-28 | 2022-03-28 | 2022-03-29 | 2022-03-29 | 4
NEMA | 339109 | 300.933 | Solar PV | PENDING AHJ INSPECTION | 2021-12-29 | 2022-03-29 | 2022-03-29 | 2022-03-29 | 2022-03-29 | 2022-03-29 | NO | NO | 2022-03-29 |  | 2022-03-12 | 2022-03-20 | 2022-03-20
NEMA | 347209 | 29.6 | Solar PV | APPROVED | 2022-03-15 | 2022-04-12 | 2022-04-12 | 2022-04-12 | N/A | N/A | NO | NO | N/A | N/A | 2022-03-16 | 2022-04-12 | 2022-04-12 | 2022-03-11 | 2022-04-14 | 2022-04-14 | N/A | 2022-04-15 | 2
NEMA | 334223 | 16.914 | Solar PV | APPROVED | 2022-04-11 | 2022-04-12 | N/A | N/A | N/A | N/A | NO | NO | N/A | N/A | 2022-04-12 | 2022-04-13 | 2022-04-13 | 2022-04-04 | 2022-04-13 | 2022-04-18 | N/A | 2022-04-19 | 6
NEMA | 342897 | 443.503 | Solar PV | PENDING AHJ INSPECTION | 2022-02-21 | 2022-05-01 | 2022-05-01 | 2022-05-01 | 2022-05-01 |  |  |  | 2022-05-01 |  | 2022-02-24 | 2022-04-21 | 2022-04-21
NEMA | 332987 | 17.344 | Solar PV | APPROVED | 2021-11-09 | 2021-11-11 | N/A | N/A | N/A | N/A | NO | NO | N/A | N/A | 2021-11-10 | 2021-11-11 | 2021-11-11 | 2021-12-15 | 2021-10-15 | 2021-12-20 | N/A | 2021-12-21 | 39

## NEM-V, SOMAH, AGG2_NGOM
SDG&E's Rule 21 Processing Timelines Q1 2022
NEM-V, SOMAH, AGG2_NGOM Method
INTERCONNECTION TYPE | APP ID | PROJECT SIZE (kW) | TECHNOLOGY TYPE | DIIS APPLICATION STATUS | DATE SDG&E WAS CONTACTED | INITIAL FIELD INSPECTION | APPLICATION SUBMITTED | APPLICATION DEEMED COMPLETE | CUST GEN. ENG REVIEW SENT | CUST GEN. ENG REVIEW COMPLETED | SENT TO DP | RECEIVED DP APPROVAL | TRANSFORMER CHANGE YES/NO | ELECTRICAL DISTRIBUTION UPGRADE YES/NO | COSTING INVOICE SENT | PAYMENT RECEIVED | RULE 2 SENT | RULE 2 RECEIVED | ICA SENT | ICA RECEIVED | ALLOCATION FORM SENT | ALLOCATION FORM RECEIVED | ALLOCATION FORM APPROVED | AHJ INSPECTION RECEIVED | CG METER INSPECTION RECEIVED | FINAL FIELD INSPECTION | VOLTAGE CHECK RECEIVED | EMAILED AMO | METER SET COMPLETED | Calendar Days from NGOM Request to NGOM Completed | PTO PROVIDED | EXECUTED ICA SENT TO CUSTOMER* | ALLOCATION FORM SENT TO BILLING | NGOM DATA SENT TO BILLING | Calendar Days from Application Deemed Complete Date to PTO Date
VNEM | 296952 | 139.917 | Solar PV | APPROVED | 2020-08-14 | 2020-12-31 | 2021-01-04 | 2021-01-04 | 2021-01-04 | 2021-01-04 | 2021-01-04 | 2021-01-04 | NO | NO | 2021-01-04 | 2021-04-08 | 2021-01-04 | 2021-03-31 | 2021-01-04 | 2021-03-29 | 2021-01-04 | 2021-03-29 | 2021-03-30 | 2021-04-09 | 2021-04-15 | 2021-04-20 | 2021-04-20 | 2021-05-07 | 2021-05-13 | 6 | 2021-05-26 | 2021-05-27 | 2021-05-27 | 2021-05-27 | 142
VNEM | 297206 | 28.767 | Solar PV | APPROVED | 2020-11-20 | 2020-12-07 | 2021-01-05 | 2021-01-08 | 2020-12-09 | 2021-01-13 | <30 | <30 | NO | NO | 2021-01-11 | 2021-01-26 | 2021-01-11 | 2021-01-20 | 2021-01-11 | 2021-10-08 | 2021-01-11 | 2021-01-11 | 2021-11-24 | 2021-10-08 | 2021-10-28 | 2021-02-17 | 2021-02-17 | 2022-03-03 | 2022-03-13 | 10 | 2022-03-15 | 2022-03-16 | 2022-03-16 | 2022-03-16 | 431
VNEM | 297223 | 28.767 | Solar PV | APPROVED | 2020-11-20 | 2020-12-07 | 2021-01-05 | 2021-01-08 | 2020-12-09 | 2021-01-13 | <30 | <30 | NO | NO | 2021-01-11 | 2021-01-26 | 2021-01-11 | 2021-01-20 | 2021-01-11 | 2021-10-08 | 2021-01-11 | 2021-01-11 | 2021-11-24 | 2021-10-08 | 2021-10-28 | 2021-02-17 | 2021-02-17 | 2022-03-03 | 2022-03-13 | 10 | 2022-03-15 | 2022-03-16 | 2022-03-16 | 2022-03-16 | 431
VNEM | 297227 | 28.767 | Solar PV | APPROVED | 2020-11-20 | 2020-12-07 | 2021-01-05 | 2021-01-08 | 2020-12-09 | 2021-01-13 | <30 | <30 | NO | NO | 2021-01-11 | 2021-01-26 | 2021-01-11 | 2021-01-20 | 2021-01-11 | 2021-10-08 | 2021-01-11 | 2021-01-11 | 2021-11-24 | 2021-10-08 | 2021-10-28 | 2021-02-17 | 2021-02-17 | 2022-03-03 | 2022-03-13 | 10 | 2022-03-15 | 2022-03-16 | 2022-03-16 | 2022-03-16 | 431
VNEM | 297230 | 28.767 | Solar PV | APPROVED | 2020-11-20 | 2020-12-07 | 2021-01-05 | 2021-01-08 | 2020-12-09 | 2021-01-13 | <30 | <30 | NO | NO | 2021-01-12 | 2021-01-26 | 2021-01-12 | 2021-01-20 | 2021-01-12 | 2021-10-08 | 2021-01-12 | 2021-01-11 | 2021-11-24 | 2021-10-08 | 2021-10-28 | 2021-02-17 | 2021-02-17 | 2022-03-03 | 2022-03-13 | 10 | 2022-03-15 | 2022-03-16 | 2022-03-16 | 2022-03-16 | 431
VNEM | 297241 | 28.767 | Solar PV | APPROVED | 2020-11-20 | 2020-12-07 | 2021-01-05 | 2021-01-08 | 2020-12-09 | 2021-01-13 | <30 | <30 | NO | NO | 2021-01-12 | 2021-01-26 | 2021-01-12 | 2021-01-20 | 2021-01-12 | 2021-10-08 | 2021-01-12 | 2021-01-11 | 2021-11-24 | 2021-10-08 | 2021-10-28 | 2021-02-17 | 2021-02-17 | 2022-03-03 | 2022-03-13 | 10 | 2022-03-15 | 2022-03-16 | 2022-03-16 | 2022-03-16 | 431
VNEM | 297244 | 28.767 | Solar PV | APPROVED | 2020-11-20 | 2020-12-07 | 2021-01-05 | 2021-01-08 | 2020-12-09 | 2021-01-13 | <30 | <30 | NO | NO | 2021-01-12 | 2021-01-26 | 2021-01-12 | 2021-01-20 | 2021-01-12 | 2021-10-08 | 2021-01-12 | 2021-01-11 | 2021-11-24 | 2021-10-08 | 2021-10-28 | 2021-02-17 | 2021-02-17 | 2022-03-03 | 2022-03-13 | 10 | 2022-03-15 | 2022-03-16 | 2022-03-16 | 2022-03-16 | 431
VNEM | 297245 | 28.767 | Solar PV | APPROVED | 2020-11-20 | 2020-12-07 | 2021-01-05 | 2021-01-08 | 2020-12-09 | 2021-01-13 | <30 | <30 | NO | NO | 2021-01-12 | 2021-01-26 | 2021-01-12 | 2021-01-20 | 2021-01-12 | 2021-10-08 | 2021-01-12 | 2021-01-11 | 2021-11-24 | 2021-10-08 | 2021-10-28 | 2021-02-17 | 2021-02-17 | 2022-03-03 | 2022-03-13 | 10 | 2022-03-15 | 2022-03-16 | 2022-03-16 | 2022-03-16 | 431
VNEM | 297246 | 28.767 | Solar PV | APPROVED | 2020-11-20 | 2020-12-07 | 2021-01-05 | 2021-01-08 | 2020-12-09 | 2021-01-13 | <30 | <30 | NO | NO | 2021-01-12 | 2021-01-26 | 2021-01-12 | 2021-01-20 | 2021-01-12 | 2021-10-08 | 2021-01-12 | 2021-01-11 | 2021-11-24 | 2021-10-08 | 2021-10-28 | 2021-02-17 | 2021-02-17 | 2022-03-03 | 2022-03-13 | 10 | 2022-03-15 | 2022-03-16 | 2022-03-16 | 2022-03-16 | 431
VNEM | 297250 | 28.767 | Solar PV | APPROVED | 2020-11-20 | 2020-12-07 | 2021-01-05 | 2021-01-08 | 2020-12-09 | 2021-01-13 | <30 | <30 | NO | NO | 2021-01-12 | 2021-01-26 | 2021-01-12 | 2021-01-20 | 2021-01-12 | 2021-10-08 | 2021-01-12 | 2021-01-11 | 2021-11-24 | 2021-10-08 | 2021-10-28 | 2021-02-17 | 2021-02-17 | 2022-03-03 | 2022-03-13 | 10 | 2022-03-15 | 2022-03-16 | 2022-03-16 | 2022-03-16 | 431
VNEM | 297252 | 28.767 | Solar PV | APPROVED | 2020-11-20 | 2020-12-07 | 2021-01-05 | 2021-01-08 | 2020-12-09 | 2021-01-13 | <30 | <30 | NO | NO | 2021-01-12 | 2021-01-26 | 2021-01-12 | 2021-01-20 | 2021-01-12 | 2021-10-08 | 2021-01-12 | 2021-01-11 | 2021-11-24 | 2021-10-08 | 2021-10-28 | 2021-02-17 | 2021-02-17 | 2022-03-03 | 2022-03-13 | 10 | 2022-03-15 | 2022-03-16 | 2022-03-16 | 2022-03-16 | 431
VNEM | 297253 | 28.767 | Solar PV | APPROVED | 2020-11-20 | 2020-12-07 | 2021-01-05 | 2021-01-08 | 2020-12-09 | 2021-01-13 | <30 | <30 | NO | NO | 2021-01-12 | 2021-01-26 | 2021-01-12 | 2021-01-20 | 2021-01-12 | 2021-10-08 | 2021-01-12 | 2021-01-11 | 2021-11-24 | 2021-10-08 | 2021-10-28 | 2021-02-17 | 2021-02-17 | 2022-03-03 | 2022-03-13 | 10 | 2022-03-15 | 2022-03-16 | 2022-03-16 | 2022-03-16 | 431
VNEM | 297255 | 28.767 | Solar PV | APPROVED | 2020-11-20 | 2020-12-07 | 2021-01-05 | 2021-01-08 | 2020-12-09 | 2021-01-13 | <30 | <30 | NO | NO | 2021-01-12 | 2021-01-26 | 2021-01-12 | 2021-01-20 | 2021-01-12 | 2021-10-08 | 2021-01-12 | 2021-01-11 | 2021-11-24 | 2021-10-08 | 2021-10-28 | 2021-02-17 | 2021-02-17 | 2022-03-03 | 2022-03-13 | 10 | 2022-03-15 | 2022-03-16 | 2022-03-16 | 2022-03-16 | 431
VNEM | 297256 | 28.767 | Solar PV | APPROVED | 2020-11-20 | 2020-12-07 | 2021-01-05 | 2021-01-08 | 2020-12-09 | 2021-01-13 | <30 | <30 | NO | NO | 2021-01-12 | 2021-01-26 | 2021-01-12 | 2021-01-20 | 2021-01-12 | 2021-10-08 | 2021-01-12 | 2021-01-11 | 2021-11-24 | 2021-10-08 | 2021-10-28 | 2021-02-17 | 2021-02-17 | 2022-03-03 | 2022-03-13 | 10 | 2022-03-15 | 2022-03-16 | 2022-03-16 | 2022-03-16 | 431
VNEM | 297319 | 23.622 | Solar PV | APPROVED | 2020-10-05 | 2020-10-27 | 2021-01-06 | 2021-01-11 | 2021-01-11 | 2021-01-14 | <30 | <30 | NO | NO | 2021-01-11 | 2021-02-23 | 2021-01-11 | 2021-02-03 | 2021-01-11 | 2021-02-03 | 2021-01-11 | 2020-10-05 | 2021-02-08 | 2021-01-11 | 2021-02-22 | 2021-02-23 | 2021-02-23 | 2021-02-25 | 2021-03-05 | 8 | 2021-03-05 | 2021-03-06 | 2021-03-08 | 2021-03-08 | 53
VNEM | 297321 | 23.906 | Solar PV | APPROVED | 2020-10-05 | 2020-10-27 | 2021-01-06 | 2021-01-11 | 2021-01-11 | 2021-01-14 | <30 | <30 | NO | NO | 2021-01-11 | 2021-02-23 | 2021-01-11 | 2021-02-03 | 2021-01-11 | 2021-02-03 | 2021-01-11 | 2020-10-05 | 2021-02-08 | 2021-01-11 | 2021-02-22 | 2021-02-23 | 2021-02-23 | 2021-02-25 | 2021-03-05 | 8 | 2021-03-05 | 2021-03-06 | 2021-03-08 | 2021-03-08 | 53
VNEM | 297322 | 23.622 | Solar PV | APPROVED | 2020-10-05 | 2020-10-27 | 2021-01-06 | 2021-01-11 | 2021-01-11 | 2021-01-14 | <30 | <30 | NO | NO | 2021-01-11 | 2021-02-23 | 2021-01-11 | 2021-02-03 | 2021-01-11 | 2021-02-03 | 2021-01-11 | 2020-10-05 | 2021-02-08 | 2021-01-11 | 2021-02-22 | 2021-02-23 | 2021-02-23 | 2021-02-25 | 2021-03-05 | 8 | 2021-03-05 | 2021-03-06 | 2021-03-08 | 2021-03-08 | 53
VNEM | 298371 | 133.2 | Solar PV | APPROVED | 2021-01-04 | 2021-01-07 | 2021-01-25 | 2021-01-26 | 2021-01-26 | 2021-01-26 | 2021-01-26 | 2021-01-27 | NO | NO | 2021-01-27 | 2021-05-24 | 2021-01-27 | 2021-01-25 | 2021-01-26 | 2021-01-26 | 2021-01-26 | 2021-01-26 | 2021-01-26 | 2021-07-20 | 2021-07-20 | 2021-07-27 | 2021-07-27 | 2021-07-29 | 2021-08-09 | 11 | 2021-05-26 | 2021-05-27 | 2021-05-27 | 2021-05-27 | 120
VNEM | 298356 | 75.9 | Solar PV | PENDING AHJ INSPECTION | 2021-01-04 | 2021-01-07 | 2021-01-25 | 2021-01-26 | 2021-01-26 | 2021-01-26 | 2021-01-26 | 2021-01-27 | NO | NO | 2021-01-27 | 2021-02-12 | 2021-01-27 |  | 2021-01-26 | 2021-01-26 | 2021-01-26 | 2021-01-26 | 2021-02-03
VNEM | 299354 | 80.306 | Solar PV | PENDING AHJ INSPECTION | 2021-01-04 | 2021-01-25 | 2021-01-28 | 2021-02-02 | 2021-02-02 | 2021-02-02 | 2021-02-02 | 2021-02-02 | NO | NO | 2021-02-03 | 2021-02-18 | 2021-02-03 |  | 2021-02-03 |  | 2021-02-03
VNEM | 300758 | 80.219 | Solar PV | APPROVED | 2021-02-06 | 2021-02-11 | 2021-02-12 | 2021-02-16 | 2021-02-16 | 2021-02-16 | 2021-02-16 | 2021-02-25 | NO | NO | 2021-02-26 | 2021-03-12 | 2021-02-26 | 2022-01-21 | 2021-02-26 | 2022-01-21 | 2021-02-26 | 2022-03-08 | 2022-03-08 | 2022-02-04 | 2022-02-04 | 2022-03-07 | 2022-03-07 | 2022-03-11 | 2022-03-25 | 14 | 2022-03-27 | 2022-03-29 | 2022-03-29 | 2022-03-29 | 404
VNEM | 300988 | 164.65 | Solar PV | PENDING AHJ INSPECTION | 2021-02-08 | 2021-02-11 | 2021-02-16 | 2021-02-24 | 2021-02-24 | 2021-02-24 | 2021-02-24 | 2021-02-25 | NO | NO | 2021-02-25 | 2021-03-12 | 2021-02-25 |  | 2021-02-25 |  | 2021-02-25
VNEM | 300779 | 164.65 | Solar PV | PENDING AHJ INSPECTION | 2021-02-09 | 2021-02-11 | 2021-02-16 | 2021-02-24 | 2021-02-24 | 2021-02-24 | 2021-02-24 | 2021-02-25 | NO | NO | 2021-02-25 | 2021-03-12 | 2021-02-25 |  | 2021-02-25 |  | 2021-02-25
VNEM | 301817 | 64.929 | Solar PV | PENDING AHJ INSPECTION | 2021-02-16 | 2021-02-17 | 2021-02-25 | 2021-03-09 | 2021-03-09 | 2021-03-09 | 2021-03-09 | 2021-03-09 | NO | NO | 2021-03-22 | 2021-04-08 | 2021-03-22 | 2021-05-07 | 2021-03-22 | 2021-05-07 | 2021-03-22 | 2021-07-12 | 2021-07-12
VNEM | 306198 | 79.039 | Solar PV | APPROVED | 2021-02-26 | 2021-03-18 | 2021-03-23 | 2021-03-23 | 2021-03-25 | 2021-03-25 | 2021-03-22 | 2021-03-29 | NO | NO | 2021-03-25 | 2021-04-28 | 2021-03-25 | 2021-06-18 | 2021-03-25 | 2021-06-18 | 2021-03-25 | 2021-06-18 | 2021-06-18 | 2021-08-30 | 2021-08-30 | 2021-09-08 | 2021-09-08 | 2021-10-14 | 2021-10-22 | 8 | 2021-10-25 | 2021-10-27 | 2021-10-27 | 2021-10-27 | 216
VNEM | 306321 | 64.89 | Solar PV | APPROVED | 2019-09-10 | 2019-09-10 | 2021-03-25 | 2021-03-25 | 2021-03-25 | 2021-03-25 | 2021-03-25 | 2021-03-29 | NO | NO | 2021-03-26 | 2021-04-08 | 2021-03-26 | 2021-04-01 | 2021-03-26 | 2021-04-01 | 2021-03-26 | 2021-04-19 | 2021-04-19 | 2021-06-09 | 2021-06-09 | 2021-06-09 | 2021-06-09 | 2021-06-10 | 2021-06-10 | 0 | 2021-06-11 | 2021-06-12 | 2021-06-12 | 2021-06-12 | 78
VNEM | 305880 | 583.858 | Solar PV | APPROVED | 2021-01-15 | 2021-03-15 | 2021-03-19 | 2021-03-25 | 2021-03-22 | 2021-03-25 | 2021-03-22 | 2021-03-25 | NO | NO | 2021-03-22 | 2021-04-08 | 2021-03-22 | 2021-05-07 | 2021-03-22 | 2021-05-07 | 2021-03-22 | 2022-01-05 | 2022-01-05 | 2021-12-01 | 2021-12-01 | 2021-01-13 | 2022-02-03 | 2022-02-07 | 2022-02-18 | 11 | 2022-02-24 | 2022-02-26 | 2022-02-26 | 2022-02-26 | 336
VNEM | 305971 | 61.481 | Solar PV | PENDING AHJ INSPECTION | 2021-02-26 | 2021-03-15 | 2021-03-22 | 2021-03-25 | 2021-03-25 | 2021-03-25 | 2021-03-26 | 2021-03-29 | NO | NO | 2021-03-25 | 2021-04-08 | 2021-03-25 |  | 2021-03-25 |  | 2021-03-25
VNEM | 305974 | 53.897 | Solar PV | PENDING AHJ INSPECTION | 2021-02-26 | 2021-03-15 | 2021-03-19 | 2021-03-25 | 2021-03-25 | 2021-03-25 | 2021-03-22 | 2021-03-30 | NO | NO | 2021-03-25 | 2021-04-08 | 2021-03-25 |  | 2021-03-25 |  | 2021-03-25
VNEM | 306577 | 27.3015 | Solar PV | APPROVED | 2021-02-17 | 2021-03-15 | 2021-03-29 | 2021-03-30 | 2021-03-30 | 2021-03-30 | <30 | <30 | NO | NO | 2021-04-12 | 2021-06-01 | 2021-04-12 | 2021-06-28 | 2021-04-12 | 2021-06-25 | 2021-04-12 | 2021-06-25 | 2021-06-25 | 2021-08-30 | 2021-08-30 | 2021-09-08 | 2021-09-08 | 2021-10-20 | 2021-10-22 | 2 | 2021-10-25 | 2021-10-27 | 2021-10-27 | 2021-10-27 | 209
VNEM | 306668 | 47.736 | Solar PV | APPROVED | 2021-03-15 | 2021-03-26 | 2021-03-30 | 2021-03-30 | 2021-03-30 | 2021-03-30 | 2021-03-31 | 2021-03-31 | NO | NO | 2021-03-30 | 2021-04-08 | 2021-03-30 | 2021-05-11 | 2021-03-30 | 2021-04-01 | 2021-03-30 | 2021-05-24 | 2021-05-24 | 2021-05-24 | 2021-05-24 | 2021-05-10 | 2021-05-10 | 2021-06-10 | 2021-06-14 | 4 | 2021-06-19 | 2021-06-20 | 2021-06-20 | 2021-06-12 | 81
VNEM | 306192 | 19.374 | Solar PV | APPROVED | 2021-03-09 | 2021-03-18 | 2021-03-23 | 2021-04-08 | 2021-04-08 | 2021-04-08 | <30 | <30 | NO | NO | 2021-04-08 | 2021-06-09 | 2021-04-08 | 2021-06-18 | 2021-04-08 | 2021-06-18 | 2021-04-08 | 2021-06-18 | 2021-06-18 | 2021-09-13 | 2021-09-13 | 2021-09-09 | 2021-09-09 | 2021-09-23 | 2021-10-06 | 13 | 2021-10-07 | 2021-10-08 | 2021-10-08 | 2021-10-08 | 182
VNEM | 306195 | 13.04 | Solar PV | APPROVED | 2021-03-09 | 2021-03-18 | 2021-03-23 | 2021-04-08 | 2021-04-08 | 2021-04-08 | <30 | <30 | NO | NO | 2021-04-08 | 2021-04-28 | 2021-04-08 | 2021-06-18 | 2021-04-08 | 2021-06-18 | 2021-04-08 | 2021-06-18 | 2021-06-18 | 2021-09-13 | 2021-09-13 | 2021-09-09 | 2021-09-09 | 2021-09-23 | 2021-10-06 | 13 | 2021-10-07 | 2021-10-08 | 2021-10-08 | 2021-10-08 | 182
VNEM | 306196 | 19.001 | Solar PV | APPROVED | 2021-03-09 | 2021-03-18 | 2021-03-23 | 2021-04-08 | 2021-04-08 | 2021-04-08 | <30 | <30 | NO | NO | 2021-04-08 | 2021-04-28 | 2021-04-08 | 2021-06-18 | 2021-04-08 | 2021-06-18 | 2021-04-08 | 2021-06-18 | 2021-06-18 | 2021-09-13 | 2021-09-13 | 2021-09-09 | 2021-09-09 | 2021-09-23 | 2021-10-06 | 13 | 2021-10-07 | 2021-10-08 | 2021-10-08 | 2021-10-08 | 182
VNEM | 300021 | 73.92 | Solar PV | APPROVED | 2021-02-17 | 2021-02-17 | 2021-07-09 | 2021-07-15 | 2021-07-15 | 2021-07-15 | 2021-07-15 | 2021-07-15 | NO | NO | 2021-07-16 | 2021-07-29 | 2021-07-16 | 2021-07-29 | 2021-07-16 | 2021-07-29 | 2021-07-16 | 2021-03-25 | 2021-09-08 | 2021-12-10 | 2021-12-17 | 2022-01-11 | 2021-02-07 | 2022-02-08 | 2022-02-18 | 10 | 2022-02-23 | 2022-02-25 | 2022-02-25 | 2022-02-25 | 223
VNEM | 318181 | 73.54 | Solar PV | APPROVED | 2021-02-17 | 2021-02-17 | 2021-07-09 | 2021-07-15 | 2021-07-15 | 2021-07-15 | 2021-07-15 | 2021-07-15 | NO | NO | 2021-07-16 | 2021-07-29 | 2021-07-16 | 2021-09-07 | 2021-07-16 | 2021-07-29 | 2021-07-16 | 2021-03-25 | 2021-11-04 | 2021-12-10 | 2021-12-17 | 2022-01-11 | 2021-02-07 | 2022-02-08 | 2022-02-18 | 10 | 2022-02-23 | 2022-02-25 | 2022-02-25 | 2022-02-25 | 223
VNEM | 319649 | 141.89 | Solar PV | APPROVED | 2021-06-30 | 2021-07-06 | 2021-07-23 | 2021-07-23 | 2021-07-23 | 2021-07-23 | 2021-07-23 | 2021-07-30 | NO | NO | 2021-07-23 | 2021-08-11 | 2021-07-23 | 2021-09-10 | 2021-07-23 | 2021-09-10 | 2021-07-23 | 2021-09-21 | 2021-09-21 | 2021-10-12 | 2021-10-12 | 2021-10-08 | 2021-10-08 | 2021-10-08 | 2021-10-14 | 6 | 2021-10-14 | 2021-10-15 | 2021-10-15 | 2021-10-15 | 83
VNEM | 317125 | 104.388 | Solar PV | APPROVED | 2021-01-26 | 2021-02-02 | 2021-07-26 | 2021-07-29 | 2021-07-29 | 2021-07-29 | 2021-07-29 | 2021-08-03 | NO | NO | 2021-07-29 | 2021-10-21 | 2021-07-29 | 2021-10-20 | 2021-07-29 | 2021-10-12 | 2021-07-29 | 2021-10-20 | 2021-10-20 | 2021-09-07 | 2021-09-17 | 2021-10-05 | 2021-10-05 | 2021-11-11 | 2021-11-19 | 8 | 2021-12-06 | 2021-12-08 | 2021-12-08 | 2021-12-08 | 130
VNEM | 317034 | 74.6 | Solar PV | APPROVED | 2021-02-02 | 2021-02-04 | 2021-07-26 | 2021-07-29 | 2021-07-29 | 2021-07-29 | 2021-07-29 | 2021-07-29 | NO | NO | 2021-09-29 | 2021-10-12 | 2021-09-29 | 2021-10-06 | 2021-09-29 | 2021-10-06 | 2021-09-29 | 2021-10-06 | 2021-10-07 | 2021-09-28 | 2021-09-28 | 2021-09-28 | 2021-09-28 | 2021-11-15 | 2021-11-17 | 2 | 2021-11-18 | 2021-11-19 | 2021-11-19 | 2021-11-19 | 112
VNEM | 317039 | 36.92 | Solar PV | APPROVED | 2021-02-02 | 2021-02-04 | 2021-07-26 | 2021-07-29 | 2021-07-29 | 2021-07-29 | 2021-07-29 | 2021-07-29 | NO | NO | 2021-09-29 | 2021-10-12 | 2021-09-29 | 2021-10-07 | 2021-09-29 | 2021-10-06 | 2021-09-29 | 2021-10-07 | 2021-10-07 | 2021-10-08 | 2021-09-28 | 2021-09-28 | 2021-09-28 | 2021-11-15 | 2021-11-17 | 2 | 2021-11-18 | 2021-11-19 | 2021-11-19 | 2021-11-19 | 112
VNEM | 317045 | 36.92 | Solar PV | APPROVED | 2021-02-02 | 2021-02-04 | 2021-07-26 | 2021-07-29 | 2021-07-29 | 2021-07-29 | 2021-07-29 | 2021-07-29 | NO | NO | 2021-09-29 | 2021-10-12 | 2021-09-29 | 2021-10-07 | 2021-09-29 | 2021-10-06 | 2021-09-29 | 2021-10-06 | 2021-10-06 | 2021-09-24 | 2021-09-29 | 2021-09-28 | 2021-09-28 | 2021-11-15 | 2021-11-17 | 2 | 2021-11-18 | 2021-11-19 | 2021-11-19 | 2021-11-19 | 112
VNEM | 317902 | 36.92 | Solar PV | APPROVED | 2021-02-02 | 2021-02-04 | 2021-07-26 | 2021-07-29 | 2021-07-29 | 2021-07-29 | 2021-07-29 | 2021-07-29 | NO | NO | 2021-09-29 | 2021-10-12 | 2021-09-29 | 2021-10-07 | 2021-09-29 | 2021-10-06 | 2021-09-29 | 2021-10-06 | 2021-10-06 | 2021-10-08 | 2021-10-08 | 2021-09-28 | 2021-09-28 | 2021-11-15 | 2021-11-17 | 2 | 2021-11-18 | 2021-11-19 | 2021-11-19 | 2021-11-19 | 112
VNEM | 318886 | 36.2 | Solar PV | APPROVED | 2021-07-15 | 2021-07-22 | 2021-08-02 | 2021-08-03 | 2021-08-03 | 2021-08-03 | 2021-08-03 | 2021-08-05 | NO | NO | 2021-08-05 | 2021-10-14 | 2021-08-04 | 2021-12-22 | 2021-08-04 | 2021-12-22 | 2021-08-04 | 2021-12-22 | 2021-12-22 | 2021-12-28 | 2021-12-28 | 2021-02-03 | 2021-02-03 | 2022-02-07 | 2022-02-17 | 10 | 2022-02-23 | 2022-02-25 | 2022-02-25 | 2022-02-25 | 204
VNEM | 298178 | 69.05 | Solar PV | PENDING AHJ INSPECTION | 2020-06-09 | 2020-07-24 | 2021-02-02 | 2021-08-05 | 2021-08-05 | 2021-08-05 | 2021-08-05 | 2021-08-11 | NO | NO | 2021-08-05 | 2021-09-28 | 2021-08-05 |  | 2021-08-05 |  | 2021-08-05
VNEM | 298181 | 69.05 | Solar PV | PENDING AHJ INSPECTION | 2020-06-09 | 2020-07-24 | 2021-02-02 | 2021-08-05 | 2021-08-05 | 2021-08-05 | 2021-08-05 | 2021-08-11 | NO | NO | 2021-08-05 | 2021-09-28 | 2021-08-05 |  | 2021-08-05 |  | 2021-08-05
VNEM | 321085 | 90.03 | Solar PV | PENDING AHJ INSPECTION | 2020-06-09 | 2020-07-24 | 2021-02-02 | 2021-08-05 | 2021-08-05 | 2021-08-05 | 2021-08-05
VNEM | 321085 | 90.03 | Solar PV | PENDING AHJ INSPECTION | 2020-12-08 | 2021-12-08 | 2021-02-02 | 2021-08-05 | 2021-08-05 | 2021-08-05 | 2021-08-05 | 2021-08-11 | NO | NO | 2021-08-05 | 2021-09-28 | 2021-08-05 |  | 2021-08-05 |  | 2021-08-05
VNEM | 319764 | 15.26 | Solar PV | APPROVED | 2021-07-29 | 2021-08-03 | 2021-07-23 | 2021-09-10 | 2021-09-10 | 2021-09-10 | <30 | <30 | NO | NO | 2021-09-10 | 2021-11-02 | 2021-09-10 | 2021-10-22 | 2021-09-10 | 2021-11-01 | 2021-09-10 | 2021-10-01 | 2021-10-01 | 2021-11-15 | 2021-11-15 | 2022-04-21 | 2022-04-14 | 2022-04-14 | 2022-04-21 | 7 | 2022-04-21 | 2022-04-25 | 2022-04-25 | 2022-04-25 | 223
VNEM | 324305 | 75.3 | Solar PV | PENDING AHJ INSPECTION | 2021-08-12 | 2021-08-17 | 2021-08-31 | 2021-09-10 | 2021-09-10 | 2021-09-10 | 2021-09-10 | 2021-09-16 | NO | NO | 2021-09-10 | 2021-09-28 | 2021-09-10 |  | 2021-09-10 |  | 2021-09-10
VNEM | 324310 | 75.3 | Solar PV | PENDING AHJ INSPECTION | 2021-08-12 | 2021-08-17 | 2021-08-31 | 2021-09-10 | 2021-09-10 | 2021-09-10 | 2021-09-10 | 2021-09-16 | NO | NO | 2021-09-10 | 2021-09-28 | 2021-09-10 |  | 2021-09-10 |  | 2021-09-10
VNEM | 324899 | 34.18 | Solar PV | PENDING AHJ INSPECTION | 2021-08-12 | 2021-08-17 | 2021-08-31 | 2021-09-10 | 2021-09-10 | 2021-09-10 | 2021-09-10 | 2021-09-16 | NO | NO | 2021-09-10 | 2021-09-28 | 2021-09-10 |  | 2021-09-10 |  | 2021-09-10
VNEM | 299722 | 13.76 | Solar PV | PENDING AHJ INSPECTION | 2021-08-17 | 2021-08-26 | 2021-02-04 | 2021-09-10 | 2021-09-10 | 2021-09-10 | <30 | <30 | NO | NO | 2021-09-16 | 2021-11-23 | 2021-09-16 | 2022-01-21 | 2021-09-16 | 2022-01-21 | 2021-09-16 | 2022-02-03 | 2022-02-03
VNEM | 275671 | 200.8 | Solar PV | PENDING AHJ INSPECTION | 2021-08-17 | 2021-08-26 | 2021-09-10 | 2021-09-10 | 2021-09-10 | 2021-09-10 | 2021-09-14 | 2021-04-08 | NO | NO | 2021-09-22 | 2021-10-05 | 2021-09-22 | 2021-11-17 | 2021-09-22 | 2021-11-17 | 2021-09-22 | 2022-03-22 | 2022-03-22 | 2022-03-18 | 2021-03-17
VNEM | 299703 | 21.15 | Solar PV | PENDING AHJ INSPECTION | 2021-08-17 | 2021-08-19 | 2021-02-01 | 2021-09-10 | 2021-09-01 | 2021-09-10 | <30 | <30 | NO | NO | 2021-09-01 | 2021-09-16 | 2021-09-01 |  | 2021-09-01 |  | 2021-09-01
VNEM | 299701 | 23.01 | Solar PV | PENDING AHJ INSPECTION | 2021-08-17 | 2021-08-19 | 2021-02-01 | 2021-09-10 | 2021-09-01 | 2021-09-10 | <30 | <30 | NO | NO | 2021-09-01 | 2021-09-16 | 2021-09-01 |  | 2021-09-01 |  | 2021-09-01
VNEM | 299686 | 26.72 | Solar PV | PENDING AHJ INSPECTION | 2021-08-17 | 2021-08-19 | 2021-02-01 | 2021-09-10 | 2021-09-01 | 2021-09-10 | <30 | <30 | NO | NO | 2021-09-01 | 2021-09-16 | 2021-09-01 |  | 2021-09-01 |  | 2021-09-01
VNEM | 299477 | 20.413 | Solar PV | PENDING AHJ INSPECTION | 2021-08-17 | 2021-08-19 | 2021-02-01 | 2021-09-10 | 2021-09-01 | 2021-09-10 | <30 | <30 | NO | NO | 2021-09-01 |  | 2021-09-01 |  | 2021-09-01 |  | 2021-09-01
VNEM | 299466 | 21.15 | Solar PV | PENDING AHJ INSPECTION | 2021-08-17 | 2021-08-19 | 2021-02-01 | 2021-09-10 | 2021-09-01 | 2021-09-10 | <30 | <30 | NO | NO | 2021-09-01 |  | 2021-09-01 |  | 2021-09-01 |  | 2021-09-01
VNEM | 299737 | 54.22 | Solar PV | APPROVED | 2021-08-17 | 2021-08-26 | 2021-02-02 | 2021-09-16 | 2021-09-16 | 2021-09-16 | 2022-02-07 | 2022-02-08 | NO | NO | 2021-10-01 | 2021-11-23 | 2021-10-01 | 2022-01-21 | 2021-10-01 | 2022-01-21 | 2021-10-01 | 2022-02-03 | 2022-02-03 | 2022-01-21 | 2022-01-21 | 2022-02-16 | 2022-02-16 | 2022-02-24 | 2022-03-08 | 12 | 2022-03-15 | 2022-03-17 | 2022-03-17 | 2022-03-17 | 180
VNEM | 299764 | 31.3 | Solar PV | PENDING AHJ INSPECTION | 2021-08-17 | 2021-08-26 | 2021-02-02 | 2021-09-16 | 2021-09-16 | 2021-09-16 | 2022-02-07 | 2022-02-08 | NO | NO | 2021-10-01 | 2021-11-23 | 2021-10-01 | 2022-01-21 | 2021-10-01 | 2022-01-21 | 2021-10-01 | 2022-02-03 | 2022-02-03 | 2022-01-21 | 2022-01-21 | 2022-02-16 | 2022-02-16 | 2022-02-24
VNEM | 324908 | 57.66 | Solar PV | PENDING AHJ INSPECTION | 2001-06-14 | 2021-06-23 | 2021-09-07 | 2021-09-17 | 2021-09-17 | 2021-09-17 | 2021-09-08 | 2021-09-17 | NO | NO | 2021-09-08 | 2021-09-21 | 2021-09-08 |  | 2021-09-08 |  | 2021-09-08
VNEM | 299713 | 59.81 | Solar PV | APPROVED | 2021-08-17 | 2021-08-26 | 2021-02-03 | 2021-09-18 | 2021-09-18 | 2021-09-18 | 2022-02-07 | 2022-02-08 | NO | NO | 2021-10-15 | 2021-10-28 | 2021-10-15 | 2022-01-18 | 2021-10-15 | 2022-01-18 | 2021-10-15 | 2022-02-04 | 2022-02-04 | 2021-12-21 | 2021-12-21 | 2022-02-16 | 2022-02-16 | 2022-02-24 | 2022-03-09 | 13 | 2022-03-11 | 2022-03-15 | 2022-03-15 | 2022-03-15 | 174
VNEM | 299716 | 21.81 | Solar PV | APPROVED | 2021-08-17 | 2021-08-26 | 2021-02-03 | 2021-09-18 | 2021-09-18 | 2021-09-18 | <30 | <30 | NO | NO | 2021-10-15 | 2021-11-23 | 2021-10-15 | 2022-01-21 | 2021-10-15 | 2022-01-21 | 2021-10-15 | 2022-02-04 | 2022-02-04 | 2022-01-04 | 2022-01-04 | 2022-02-16 | 2022-02-16 | 2022-02-24 | 2022-03-09 | 13 | 2022-03-11 | 2022-03-15 | 2022-03-15 | 2022-03-15 | 174
VNEM | 323049 | 93.6 | Solar PV | APPROVED | 2021-07-12 | 2021-07-14 | 2021-08-20 | 2021-09-20 | 2021-09-20 | 2021-09-20 | 2021-09-20 | 2021-09-23 | NO | NO | 2021-10-13 | 2021-10-10 | 2021-10-13 | 2021-11-24 | 2021-10-13 | 2021-11-24 | 2021-10-13 | 2021-12-01 | 2021-12-01 | 2021-11-01 | 2021-11-01 | 2021-12-16 | 2021-12-16 | 2021-12-17 | 2021-12-21 | 4 | 2021-12-30 | 2022-01-02 | 2022-01-02 | 2022-01-02 | 101
VNEM | 325165 | 110.3 | Solar PV | PENDING AHJ INSPECTION | 2021-08-12 | 2021-08-17 | 2021-09-09 | 2021-09-20 | 2021-09-20 | 2021-09-20 | 2021-09-20 | 2021-09-21 | NO | NO | 2021-09-20 | 2021-10-14 | 2021-09-20 |  | 2021-09-20 |  | 2021-09-20
VNEM | 325584 | 375 | Solar PV | PENDING AHJ INSPECTION | 2021-06-08 | 2021-06-10 | 2021-09-20 | 2021-10-06 | 2021-10-01 | 2021-10-06 | 2021-10-01 | 2021-10-06 | NO | NO | 2021-10-15 | 2021-10-19 | 2021-10-15 | 2021-11-12 | 2021-10-15 | 2022-01-12 | 2021-10-15 | 2022-03-09 | 2022-03-09
VNEM | 327166 | 133.2 | Solar PV | PENDING AHJ INSPECTION | 2021-06-08 | 2021-06-10 | 2021-09-20 | 2021-10-06 | 2021-10-01 | 2021-10-06 | 2021-10-01 | 2021-10-06 | NO | NO | 2021-10-15 | 2021-10-19 | 2021-10-15 | 2022-03-22 | 2021-10-15 | 2022-03-22 | 2021-10-15 | 2022-03-30 | 2022-03-30 | 2022-10-28
VNEM | 331375 | 155.2 | Solar PV | PENDING AHJ INSPECTION | 2021-06-08 | 2021-06-10 | 2021-09-14 | 2021-10-06 | 2021-10-06 | 2021-10-06 | 2022-04-15 | 2022-04-18 | NO | NO | 2021-10-28 | 2022-02-08 | 2021-10-28 |  | 2021-10-28 | 2021-11-01 | 2021-10-28
VNEM | 328753 | 28.511 | Solar PV | PENDING AHJ INSPECTION | 2021-09-20 | 2021-09-28 | 2021-10-04 | 2021-10-20 | 2021-10-20 | 2021-10-20 | <30 | <30 | NO | NO | 2021-10-13 |  | 2021-10-13 |  | 2021-10-13 |  | 2021-10-13
VNEM | 299724 | 43.59 | Solar PV | PENDING AHJ INSPECTION | 2021-08-17 | 2021-08-26 | 2021-02-04 | 2021-10-21 | 2021-10-21 | 2021-10-21 | 2021-10-21 | 2021-12-01 | NO | NO | 2021-10-21 | 2021-11-23 | 2021-10-21 | 2022-01-21 | 2021-10-21 | 2022-01-21 | 2021-10-21 | 2022-02-03 | 2022-02-03
VNEM | 330149 | 60.7 | Solar PV | PENDING AHJ INSPECTION | 2021-09-09 | 2021-09-21 | 2021-11-09 | 2021-11-15 | 2021-11-15 | 2021-11-15 | 2021-02-09 | 2022-02-24 | NO | NO | 2021-11-15 | 2021-12-15 | 2021-11-15 | 2022-01-31 | 2021-11-15 | 2021-12-13 | 2021-11-15 | 2022-01-31 | 2022-01-31
VNEM | 325931 | 121 | Solar PV | PENDING AHJ INSPECTION | 2021-03-09 | 2021-03-15 | 2021-12-01 | 2021-12-02 | 2021-12-02 | 2021-12-02 | 2021-12-02 | 2021-12-07 | NO | NO | 2021-12-08 | 2022-01-04 | 2021-12-08 | 2022-04-06 | 2021-12-08 | 2022-04-06 | 2021-12-08
VNEM | 328125 | 137 | Solar PV | PENDING AHJ INSPECTION | 2021-03-09 | 2021-03-15 | 2021-12-01 | 2021-12-02 | 2021-12-02 | 2021-12-02 | 2021-12-02 | 2021-12-07 | NO | NO | 2021-12-08 | 2022-01-04 | 2021-12-08 | 2022-04-06 | 2021-12-08 | 2022-04-06 | 2021-12-08
VNEM | 315674 | 88.29 | Solar PV | APPROVED | 2019-08-07 | 2019-08-07 | 2021-06-16 | 2021-12-06 | 2021-12-06 | 2021-12-09 | 2021-12-06 | 2021-12-14 | NO | NO | 2021-12-06 | 2021-12-15 | 2021-12-06 | 2022-01-11 | 2021-12-06 | 2022-01-11 | 2021-12-06 | 2021-12-21 | 2021-12-21 | 2021-12-15 | 2021-12-15 | 2021-12-10 | 2021-12-10 | 2022-01-13 | 2022-01-21 | 8 | 2022-01-21 | 2022-01-23 | 2022-01-23 | 2022-01-23 | 46
VNEM | 315683 | 333.3 | Solar PV | APPROVED | 2019-08-07 | 2019-08-07 | 2021-06-16 | 2021-12-06 | 2021-12-06 | 2021-12-09 | 2021-12-06 | 2021-12-18 | NO | NO | 2021-12-06 | 2021-12-15 | 2021-12-06 | 2022-01-11 | 2021-12-06 | 2022-01-11 | 2021-12-06 | 2021-12-21 | 2021-12-21 | 2021-12-15 | 2021-12-15 | 2021-12-10 | 2021-12-10 | 2022-01-13 | 2022-01-21 | 8 | 2022-01-21 | 2022-01-23 | 2022-01-23 | 2022-01-23 | 46
VNEM | 336523 | 87.32 | Solar PV | PENDING AHJ INSPECTION | 2020-12-22 | 2020-12-22 | 2021-12-07 | 2021-12-07 | 2021-12-14 | 2021-12-14 | 2022-03-18 | 2022-03-18 | NO | NO | 2021-12-14 | 2022-03-08 | 2021-12-14 | 2022-03-17 | 2021-12-14 | 2022-03-17 | 2021-12-14 | 2022-03-17 | 2022-03-17 | 2022-04-05
VNEM | 337882 | 86 | Solar PV | PENDING AHJ INSPECTION | 2021-07-12 | 2015-07-15 | 2021-12-16 | 2021-12-20 | 2021-12-20 | 2021-12-20 | 2022-02-11 | 2022-02-14 | NO | NO | 2021-12-22 |  | 2021-12-22 |  | 2021-12-22 |  | 2021-12-22
VNEM | 336504 | 47.4 | Solar PV | PENDING AHJ INSPECTION | 2021-07-13 | 2021-11-30 | 2021-12-15 | 2021-12-20 | 2021-12-20 | 2021-12-20 | 2022-03-18 | 2022-03-18 | NO | NO | 2022-01-06 |  | 2022-01-06 | 2022-04-01 | 2022-01-06 | 2022-04-01 | 2022-01-06 | 2022-04-01 | 2022-04-01
VNEM | 336639 | 41.7 | Solar PV | PENDING AHJ INSPECTION | 2021-07-13 | 2021-11-30 | 2021-12-15 | 2021-12-20 | 2021-12-20 | 2021-12-20 | 2022-03-18 | 2022-03-18 | NO | NO | 2022-01-06 |  | 2022-01-06 | 2022-04-01 | 2022-01-06 | 2022-04-01 | 2022-01-06 | 2022-04-01 | 2022-04-01
VNEM | 336664 | 33.1 | Solar PV | PENDING AHJ INSPECTION | 2021-07-13 | 2021-11-30 | 2021-12-15 | 2021-12-20 | 2021-12-20 | 2021-12-20 | 2022-03-18 | 2022-03-18 | NO | NO | 2022-01-06 |  | 2022-01-06 | 2022-04-01 | 2022-01-06 | 2022-04-01 | 2022-01-06 | 2022-04-01 | 2022-04-01
VNEM | 336683 | 47.4 | Solar PV | PENDING AHJ INSPECTION | 2021-07-13 | 2021-11-30 | 2021-12-15 | 2021-12-20 | 2021-12-20 | 2021-12-20 | 2022-03-18 | 2022-03-18 | NO | NO | 2022-01-06 |  | 2022-01-06 | 2022-04-01 | 2022-01-06 | 2022-04-01 | 2022-01-06 | 2022-04-01 | 2022-04-01
VNEM | 336685 | 47.4 | Solar PV | PENDING AHJ INSPECTION | 2021-07-13 | 2021-11-30 | 2021-12-15 | 2021-12-20 | 2021-12-20 | 2021-12-20 | 2022-03-18 | 2022-03-18 | NO | NO | 2022-01-06 |  | 2022-01-06 | 2022-04-01 | 2022-01-06 | 2022-04-01 | 2022-01-06 | 2022-04-01 | 2022-04-01
VNEM | 336692 | 47.4 | Solar PV | PENDING AHJ INSPECTION | 2021-07-13 | 2021-11-30 | 2021-12-15 | 2021-12-20 | 2021-12-20 | 2021-12-20 | 2022-03-18 | 2022-03-18 | NO | NO | 2022-01-06 |  | 2022-01-06 | 2022-04-01 | 2022-01-06 | 2022-04-01 | 2022-01-06 | 2022-04-01 | 2022-04-01
VNEM | 337344 | 17.83 | Solar PV | PENDING AHJ INSPECTION | 2021-10-06 | 2021-10-19 | 2021-12-13 | 2021-12-20 | 2021-12-20 | 2021-12-20 | <30 | <30 | NO | NO | 2022-01-13 | 2022-02-02 | 2022-01-13 |  | 2022-01-13 |  | 2022-01-13
VNEM | 337353 | 10.35 | Solar PV | PENDING AHJ INSPECTION | 2021-10-06 | 2021-10-19 | 2021-12-13 | 2021-12-20 | 2021-12-20 | 2021-12-20 | <30 | <30 | NO | NO | 2022-01-13 | 2022-02-02 | 2022-01-13 |  | 2022-01-13 |  | 2022-01-13
VNEM | 337354 | 59.54 | Solar PV | PENDING AHJ INSPECTION | 2021-10-06 | 2021-10-19 | 2021-12-13 | 2021-12-20 | 2021-12-20 | 2021-12-20 | 2022-02-14 | 2022-02-16 | NO | NO | 2022-01-13 | 2022-02-02 | 2022-01-13 |  | 2022-01-13 |  | 2022-01-13
VNEM | 337348 | 60.61 | Solar PV | PENDING AHJ INSPECTION | 2021-10-06 | 2021-10-19 | 2021-12-13 | 2021-12-20 | 2021-12-20 | 2021-12-20 | 2022-02-14 | 2022-02-16 | NO | NO | 2022-01-13 | 2022-02-02 | 2022-01-13 |  | 2022-01-13 |  | 2022-01-13
VNEM | 342197 | 69.7 | Solar PV | ISSUES | 2022-01-06 | 2021-01-13 | 2022-01-31 | 2022-02-08 | 2022-02-08 | 2022-02-08 | 2022-02-08 | 2022-02-10 | NO | NO | 2022-02-10 |  | 2022-02-10 |  | 2022-02-10 |  | 2022-02-10
VNEM | 343792 | 28.33 | Solar PV | PENDING AHJ INSPECTION | 2021-12-01 | 2021-12-15 | 2022-02-15 | 2022-02-16 | 2022-02-25 | 2022-02-25 | <30 | <30 | NO | NO | 2022-02-25 |  | 2022-02-25 |  | 2022-02-25 |  | 2022-02-25
VNEM | 343912 | 34 | Solar PV | PENDING AHJ INSPECTION | 2021-12-01 | 2021-12-15 | 2022-02-15 | 2022-02-16 | 2022-02-25 | 2022-02-25 | 2022-03-08 | 2022-03-10 | NO | NO | 2022-02-25 |  | 2022-02-25 |  | 2022-02-25 |  | 2022-02-25
VNEM | 343856 | 30 | Solar PV | PENDING AHJ INSPECTION | 2021-12-01 | 2021-12-15 | 2022-02-15 | 2022-02-16 | 2022-02-25 | 2022-02-25 | 2022-03-08 | 2022-03-10 | NO | NO | 2022-02-25 |  | 2022-02-25 |  | 2022-02-25 |  | 2022-02-25
VNEM | 343881 | 14.5 | Solar PV | PENDING AHJ INSPECTION | 2021-12-01 | 2021-12-15 | 2022-02-15 | 2022-02-16 | 2022-02-25 | 2022-02-25 | <30 | <30 | NO | NO | 2022-02-25 |  | 2022-02-25 |  | 2022-02-25 |  | 2022-02-25
VNEM | 343888 | 21.04 | Solar PV | PENDING AHJ INSPECTION | 2021-12-01 | 2021-12-15 | 2022-02-15 | 2022-02-16 | 2022-02-25 | 2022-02-25 | <30 | <30 | NO | NO | 2022-02-25 |  | 2022-02-25 |  | 2022-02-25 |  | 2022-02-25
VNEM | 345217 | 22.67 | Solar PV | PENDING AHJ INSPECTION | 2022-01-21 | 2022-01-31 | 2022-02-25 | 2022-02-28 | 2022-02-28 | 2022-02-28 | <30 | <30 | NO | NO | 2022-02-28 | 2022-03-08 | 2022-02-28 | 2022-03-07 | 2022-02-28 | 2022-03-28 | 2022-02-28 | 2022-03-07 | 2022-03-07
VNEM | 345209 | 25.8 | Solar PV | PENDING AHJ INSPECTION | 2022-01-21 | 2022-01-31 | 2022-02-25 | 2022-02-28 | 2022-02-28 | 2022-02-28 | <30 | <30 | NO | NO | 2022-02-28 | 2022-03-08 | 2022-02-28 | 2022-03-07 | 2022-02-28 | 2022-03-28 | 2022-02-28 | 2022-03-07 | 2022-03-07
VNEM | 345221 | 25.8 | Solar PV | PENDING AHJ INSPECTION | 2022-01-21 | 2022-01-31 | 2022-02-25 | 2022-02-28 | 2022-02-28 | 2022-02-28 | <30 | <30 | NO | NO | 2022-02-28 | 2022-03-08 | 2022-02-28 | 2022-03-07 | 2022-02-28 | 2022-03-28 | 2022-02-28 | 2022-03-07 | 2022-03-07
VNEM | 345225 | 18.2 | Solar PV | PENDING AHJ INSPECTION | 2022-01-21 | 2022-01-31 | 2022-02-25 | 2022-02-28 | 2022-02-28 | 2022-02-28 | <30 | <30 | NO | NO | 2022-02-28 | 2022-03-08 | 2022-02-28 | 2022-03-07 | 2022-02-28 | 2022-03-28 | 2022-02-28 | 2022-03-07 | 2022-03-07
VNEM | 345227 | 18.2 | Solar PV | PENDING AHJ INSPECTION | 2022-01-21 | 2022-01-31 | 2022-02-25 | 2022-02-28 | 2022-02-28 | 2022-02-28 | <30 | <30 | NO | NO | 2022-02-28 | 2022-03-08 | 2022-02-28 | 2022-03-07 | 2022-02-28 | 2022-03-28 | 2022-02-28 | 2022-03-07 | 2022-03-07
VNEM | 345228 | 27.7 | Solar PV | PENDING AHJ INSPECTION | 2022-01-21 | 2022-01-31 | 2022-02-25 | 2022-02-28 | 2022-02-28 | 2022-02-28 | <30 | <30 | NO | NO | 2022-02-28 | 2022-03-08 | 2022-02-28 | 2022-03-07 | 2022-02-28 | 2022-03-28 | 2022-02-28 | 2022-03-07 | 2022-03-07
VNEM | 330937 | 95.75 | Solar PV | PENDING AHJ INSPECTION | 2021-10-01 | 2021-10-12 | 2021-10-22 | 2022-10-26 | 2022-10-26 | 2022-10-26 | 2022-10-26 | 2021-11-03 | NO | NO | 2021-11-01 | 2021-11-09 | 2021-11-01 |  | 2021-11-01 |  | 2021-11-01
VNEM | 330940 | 58.43 | Solar PV | PENDING AHJ INSPECTION | 2021-10-01 | 2021-10-12 | 2021-10-22 | 2022-10-26 | 2022-10-26 | 2022-10-26 | 2022-10-26 | 2021-11-03 | NO | NO | 2021-11-01 | 2021-11-09 | 2021-11-01 |  | 2021-11-01 |  | 2021-11-01
VNEM | 330796 | 86.4 | Solar PV | PENDING AHJ INSPECTION | 2021-10-01 | 2021-10-12 | 2022-10-22 | 2022-10-26 | 2022-10-26 | 2022-10-26 | 2022-10-26 | 2021-11-03 | NO | NO | 2021-11-01 | 2021-11-09 | 2021-11-01 |  | 2021-11-01 |  | 2021-11-01

## >30kW NEM-ST
SDG&E's Rule 21 Processing Timelines Q1 2022
>30kW NEM-ST
INTERCONNECTION TYPE | APP ID | PROJECT SIZE (kW) | TECHNOLOGY TYPE | DIIS APPLICATION STATUS | APPLICATION SUBMITTED | APPLICATION DEEMED COMPLETE | CUST GEN. ENG REVIEW SENT | CUST GEN. ENG REVIEW COMPLETED | SENT TO DP | RECEIVED DP APPROVAL | TRANSFORMER CHANGE YES/NO | ELECTRICAL DISTRIBUTION UPGRADE YES/NO | ICA SENT | ICA RECEIVED | AHJ INSPECTION RECEIVED | FINAL FIELD INSPECTION | PTO PROVIDED | EXECUTED ICA SENT TO CUSTOMER* | Calendar Days from Application Deemed Complete Date to PTO Date
NEM-ST | 296966 | 44.214 | Solar PV | PENDING AHJ INSPECTION | 2020-12-31 | 2021-01-04 | 2021-01-04 | 2021-01-04 | 2021-01-04 | 2021-01-04 | NO | NO | 2021-01-04
NEM-ST | 295832 | 54.845 | Solar PV | APPROVED | 2021-01-12 | 2021-01-13 | 2021-01-13 | 2021-01-13 | 2021-01-13 | 2021-01-15 | NO | NO | 2021-01-13 | 2021-01-15 | 2021-02-11 | 2021-02-16 | 2021-02-16 | 2021-03-09 | 34
NEM-ST | 297846 | 33.445 | Solar PV | APPROVED | 2021-01-12 | 2021-01-13 | 2021-01-13 | 2021-01-13 | 2021-01-13 | 2021-01-15 | NO | NO | 2021-01-13 | 2021-01-21 | 2020-12-29 | 2021-01-14 | 2021-01-21 | 2021-03-09 | 8
NEM-ST | 297894 | 155.044 | Solar PV | APPROVED | 2021-01-14 | 2021-01-19 | 2021-01-19 | 2021-01-19 | 2021-01-19 | 2021-01-20 | NO | NO | 2021-01-19 | 2021-01-21 | 2021-05-22 | 2021-05-24 | 2021-05-25 | 2021-05-26 | 126
NEM-ST | 299510 | 64.668 | Solar PV | APPROVED | 2021-01-29 | 2021-02-02 | 2021-02-02 | 2021-02-02 | 2021-02-02 | 2021-02-02 | NO | NO | 2021-02-02 | 2021-02-12 | 2021-02-16 | 2021-02-17 | 2021-02-17 | 2021-03-09 | 15
NEM-ST | 299469 | 89.362 | Solar PV | APPROVED | 2021-02-01 | 2021-02-02 | 2021-02-02 | 2021-02-02 | 2021-02-02 | 2021-02-02 | NO | NO | 2021-02-02 | 2021-02-03 | 2021-07-27 | 2021-07-28 | 2021-07-29 | 2021-07-30 | 177
NEM-ST | 297819 | 206.886 | Battery Storage + Solar PV | PENDING AHJ INSPECTION | 2021-01-20 | 2021-02-04 | 2021-02-04 | 2021-02-04 | 2021-02-04 | 2021-02-09 | NO | NO | 2021-02-04 | 2021-03-17
NEM-ST | 299788 | 30.262 | Solar PV | APPROVED | 2021-02-02 | 2021-02-08 | 2021-02-08 | 2021-02-08 | 2021-02-08 | 2021-02-16 | NO | NO | 2021-02-08 | 2021-10-07 | 2021-09-30 | 2021-10-01 | 2021-10-07 | 2021-10-08 | 241
NEM-ST | 300182 | 31.786 | Solar PV | APPROVED | 2021-02-05 | 2021-02-08 | 2021-02-08 | 2021-02-08 | 2021-02-08 | 2021-02-09 | NO | NO | 2021-02-08 | 2021-03-12 | 2021-02-08 | 2021-02-09 | 2021-03-25 | 2021-05-17 | 45
NEM-ST | 300302 | 99.387 | Solar PV | APPROVED | 2021-02-08 | 2021-02-11 | 2021-02-11 | 2021-02-11 | 2021-02-11 | 2021-02-16 | NO | NO | 2021-02-11 | 2021-07-28 | 2021-12-08 | 2021-12-30 | 2021-12-30 | 2022-01-03 | 322
NEM-ST | 300476 | 348.66 | Solar PV | APPROVED | 2021-02-10 | 2021-02-11 | 2021-02-11 | 2021-02-11 | 2021-02-11 | 2021-02-16 | NO | NO | 2021-02-11 | 2021-06-11 | 2021-09-07 | 2021-09-08 | 2021-09-08 | 2021-09-09 | 209
NEM-ST | 300569 | 427.071 | Solar PV | APPROVED | 2021-02-10 | 2021-02-11 | 2021-02-11 | 2021-02-11 | 2021-02-11 | 2021-02-16 | NO | NO | 2021-02-11 | 2021-03-17 | 2021-05-25 | 2021-05-26 | 2021-05-26 | 2021-05-27 | 104
NEM-ST | 297972 | 851.674 | Battery Storage + Solar PV | PENDING AHJ INSPECTION | 2021-01-14 | 2021-02-16 | 2021-02-16 | 2021-02-16 | 2021-01-15 | 2021-01-19 | NO | NO | 2021-02-18 | 2021-03-17
NEM-ST | 300246 | 150.731 | Solar PV | APPROVED | 2021-02-11 | 2021-02-16 | 2021-02-16 | 2021-02-16 | 2021-02-16 | 2021-02-18 | NO | NO | 2021-02-16 | 2021-06-22 | 2021-10-22 | 2021-10-26 | 2021-10-28 | 2021-10-29 | 254
NEM-ST | 300756 | 370.124 | Solar PV | PENDING AHJ INSPECTION | 2021-02-12 | 2021-02-16 | 2021-02-16 | 2021-02-16 | 2021-02-16 | 2021-02-18 | NO | NO | 2021-02-16 | 2021-02-22
NEM-ST | 300868 | 854.143 | Solar PV | APPROVED | 2021-02-15 | 2021-02-16 | 2021-02-16 | 2021-02-16 | 2021-02-16 | 2021-02-18 | NO | NO | 2021-02-16 | 2021-06-10 | 2021-06-19 | 2021-06-21 | 2021-06-22 | 2021-06-23 | 126
NEM-ST | 299331 | 57.783 | Solar PV | APPROVED | 2021-02-17 | 2021-02-23 | 2021-02-23 | 2021-02-23 | 2021-02-23 | 2021-02-24 | NO | NO | 2021-02-23 | 2021-04-22 | 2021-03-02 | 2021-03-03 | 2021-05-21 | 2021-05-24 | 87
NEM-ST | 281862 | 406.84 | Battery Storage + Solar PV | APPROVED | 2020-09-16 | 2021-03-08 | 2021-03-08 | 2021-03-08 | 2020-12-18 | 2020-12-21 | NO | NO | 2021-03-08 | 2021-11-16 | 2021-11-11 | 2021-11-16 | 2021-12-17 | 2021-12-20 | 284
NEM-ST | 301310 | 293.924 | Solar PV | APPROVED | 2021-02-19 | 2021-03-08 | 2021-03-08 | 2021-03-08 | 2021-02-23 | 2021-02-24 | NO | NO | 2021-03-08 | 2021-03-23 | 2021-06-02 | 2021-06-03 | 2021-06-03 | 2021-06-04 | 87
NEM-ST | 304291 | 306.729 | Battery Storage + Solar PV | APPROVED | 2021-03-02 | 2021-03-08 | 2021-03-08 | 2021-03-08 | 2021-03-08 | 2021-03-09 | NO | NO | 2021-03-08 | 2021-11-16 | 2021-11-11 | 2021-11-16 | 2022-01-23 | 2022-01-24 | 321
NEM-ST | 304265 | 63.777 | Solar PV | APPROVED | 2021-03-02 | 2021-03-08 | 2021-03-08 | 2021-03-08 | 2021-03-08 | 2021-03-09 | NO | NO | 2021-03-08 | 2021-03-12 | 2021-03-10 | 2021-03-11 | 2021-03-12 | 2021-05-17 | 4
NEM-ST | 304193 | 84.302 | Solar PV | APPROVED | 2021-03-03 | 2021-03-08 | 2021-03-08 | 2021-03-08 | 2021-03-08 | 2021-03-09 | NO | NO | 2021-03-08 | 2021-03-25 | 2021-07-15 | 2021-07-19 | 2021-09-21 | 2021-09-22 | 197
NEM-ST | 304595 | 47.238 | Solar PV | ISSUES | 2021-03-05 | 2021-03-08 | 2021-03-08 | 2021-03-08 | 2021-03-08 | 2021-03-09 | NO | NO | 2021-03-08 | 2021-07-23 | 2021-05-26 | 2021-05-27
NEM-ST | 304775 | 44.752 | Solar PV | APPROVED | 2021-03-08 | 2021-03-08 | 2021-03-08 | 2021-03-08 | 2021-03-08 | 2021-03-09 | NO | NO | 2021-03-08 | 2021-03-17 | 2021-07-16 | 2021-07-19 | 2021-07-20 | 2021-07-21 | 134
NEM-ST | 301339 | 141.182 | Solar PV | APPROVED | 2021-03-16 | 2021-03-22 | 2021-03-22 | 2021-03-22 | 2021-03-22 | 2021-03-26 | NO | NO | 2021-03-22 | 2021-05-06 | 2021-12-06 | 2021-12-07 | 2021-12-07 | 2021-12-08 | 260
NEM-ST | 305478 | 35.838 | Solar PV | APPROVED | 2021-03-16 | 2021-03-23 | 2021-03-23 | 2021-03-23 | 2021-03-23 | 2021-03-26 | NO | NO | 2021-03-23 | 2021-03-23 | 2021-07-06 | 2021-07-07 | 2021-07-08 | 2021-07-09 | 107
NEM-ST | 262465 | 131.929 | Solar PV | APPROVED | 2021-03-17 | 2021-03-23 | 2021-03-23 | 2021-03-23 | 2020-04-05 | 2020-04-06 | NO | NO | 2021-03-23 | 2021-06-08 | 2021-06-17 | 2021-06-18 | 2021-06-20 | 2021-06-21 | 89
NEM-ST | 304597 | 35.41 | Solar PV | APPROVED | 2021-03-18 | 2021-03-23 | 2021-03-23 | 2021-03-23 | 2021-03-23 | 2021-03-26 | NO | NO | 2021-03-23 | 2021-03-31 | 2021-04-28 | 2021-04-29 | 2021-05-17 | 2021-05-18 | 55
NEM-ST | 304927 | 57.601 | Solar PV | APPROVED | 2021-03-18 | 2021-03-23 | 2021-03-23 | 2021-03-23 | 2021-03-23 | 2021-03-26 | NO | NO | 2021-03-23 | 2021-04-22 | 2021-04-14 | 2021-04-15 | 2021-05-21 | 2021-05-24 | 59
NEM-ST | 306279 | 72.206 | Solar PV | APPROVED | 2021-03-24 | 2021-03-29 | 2021-03-29 | 2021-03-29 | 2021-03-29 | 2021-03-30 | YES | YES | 2021-03-29 | 2021-03-29 | 2021-03-24 | 2021-06-24 | 2021-06-24 | 2021-06-25 | 87
NEM-ST | 306362 | 39.03 | Solar PV | APPROVED | 2021-03-25 | 2021-03-29 | 2021-03-29 | 2021-03-29 | 2021-03-29 | 2021-03-30 | NO | NO | 2021-03-29 | 2021-04-12 | 2021-09-22 | 2021-09-23 | 2021-09-23 | 2021-09-24 | 178
NEM-ST | 299074 | 54.01 | Solar PV | APPROVED | 2021-03-22 | 2021-03-30 | 2021-03-30 | 2021-03-30 | 2021-03-30 | 2021-03-31 | NO | NO | 2021-03-30 | 2021-03-30 | 2021-04-19 | 2021-04-29 | 2021-04-29 | 2021-05-17 | 30
NEM-ST | 301835 | 163.27 | Solar PV | APPROVED | 2021-03-29 | 2021-03-30 | 2021-03-30 | 2021-03-30 | 2021-03-30 | 2021-03-31 | NO | NO | 2021-03-30 | 2021-04-12 | 2021-03-30 | 2021-03-31 | 2021-04-12 | 2021-04-13 | 13
NEM-ST | 300505 | 74.211 | Solar PV | APPROVED | 2021-03-30 | 2021-03-31 | 2021-03-31 | 2021-03-31 | 2021-03-31 | 2021-04-06 | NO | NO | 2021-03-31 | 2021-03-31 | 2021-10-18 | 2021-10-19 | 2021-10-25 | 2021-10-26 | 208
NEM-ST | 304249 | 81.606 | Solar PV | APPROVED | 2021-03-30 | 2021-03-31 | 2021-03-31 | 2021-03-31 | 2021-03-31 | 2021-04-28 | NO | NO | 2021-03-31 | 2021-03-31 | 2021-10-25 | 2021-10-27 | 2021-10-27 | 2021-10-28 | 210
NEM-ST | 304251 | 133.783 | Solar PV | APPROVED | 2021-03-30 | 2021-03-31 | 2021-03-31 | 2021-03-31 | 2021-03-31 | 2021-04-06 | NO | NO | 2021-03-31 | 2021-03-31 | 2021-10-18 | 2021-10-28 | 2021-10-29 | 2021-11-01 | 212
NEM-ST | 304263 | 141.103 | Solar PV | APPROVED | 2021-03-30 | 2021-03-31 | 2021-03-31 | 2021-03-31 | 2021-03-31 | 2021-04-06 | NO | NO | 2021-03-31 | 2021-03-31 | 2021-10-18 | 2021-10-19 | 2021-10-25 | 2021-10-26 | 208
NEM-ST | 304268 | 200.675 | Solar PV | APPROVED | 2021-03-30 | 2021-03-31 | 2021-03-31 | 2021-03-31 | 2021-03-31 | 2021-04-06 | NO | NO | 2021-03-31 | 2021-03-31 | 2021-10-18 | 2021-10-29 | 2021-10-19 | 2021-10-20 | 202
NEM-ST | 304272 | 133.783 | Solar PV | APPROVED | 2021-03-30 | 2021-03-31 | 2021-03-31 | 2021-03-31 | 2021-03-31 | 2021-04-06 | NO | NO | 2021-03-31 | 2021-03-31 | 2021-10-18 | 2021-10-19 | 2021-10-25 | 2021-10-26 | 208
NEM-ST | 304280 | 133.783 | Solar PV | APPROVED | 2021-03-30 | 2021-03-31 | 2021-03-31 | 2021-03-31 | 2021-03-31 | 2021-04-06 | NO | NO | 2021-03-31 | 2021-03-31 | 2021-10-18 | 2021-10-19 | 2021-10-25 | 2021-10-26 | 208
NEM-ST | 304350 | 429.367 | Solar PV | APPROVED | 2021-03-30 | 2021-03-31 | 2021-03-31 | 2021-03-31 | 2021-03-31 | 2021-04-06 | NO | NO | 2021-03-31 | 2021-04-29 | 2021-08-13 | 2021-08-16 | 2021-08-16 | 2021-08-17 | 138
NEM-ST | 305710 | 215.389 | Solar PV | APPROVED | 2021-03-30 | 2021-03-31 | 2021-03-31 | 2021-03-31 | 2021-03-31 | 2021-04-06 | NO | NO | 2021-03-31 | 2021-03-31 | 2021-10-18 | 2021-10-19 | 2021-10-19 | 2021-10-20 | 202
NEM-ST | 307202 | 106.294 | Solar PV | APPROVED | 2021-04-07 | 2021-04-15 | 2021-04-15 | 2021-04-15 | 2021-04-15 | 2021-04-19 | NO | NO | 2021-04-15 | 2021-04-19 | 2021-06-11 | 2021-06-14 | 2021-06-15 | 2021-06-16 | 61
NEM-ST | 306705 | 42.464 | Solar PV | APPROVED | 2021-04-12 | 2021-04-22 | 2021-04-22 | 2021-04-22 | 2021-04-22 | 2021-04-23 | NO | NO | 2021-04-12 | 2021-04-12 | 2021-04-16 | 2021-04-23 | 2021-04-26 | 2021-05-17 | 4
NEM/PRD | 307960 | 429 | Battery Storage | PENDING AHJ INSPECTION | 2021-04-12 | 2021-04-22 | 2021-04-22 | 2021-04-22 | 2021-04-22 | 2021-04-23 | NO | NO | N/A | N/A
NEM-ST | 307412 | 35.416 | Solar PV | APPROVED | 2021-04-15 | 2021-04-22 | 2021-04-22 | 2021-04-22 | 2021-04-22 | 2021-04-23 | NO | NO | 2021-04-12 | 2021-04-12 | 2021-03-18 | 2021-04-23 | 2021-04-29 | 2021-05-17 | 7
NEM-ST | 308194 | 63.003 | Solar PV | APPROVED | 2021-04-16 | 2021-04-22 | 2021-04-22 | 2021-04-22 | 2021-04-22 | 2021-04-23 | NO | NO | 2021-04-22 | 2021-04-22 | 2021-11-03 | 2021-11-04 | 2021-11-05 | 2021-11-08 | 197
NEM-ST | 308191 | 80.024 | Solar PV | PENDING AHJ INSPECTION | 2021-04-16 | 2021-04-22 | 2021-04-22 | 2021-04-22 | 2021-04-22 | 2021-04-23 | NO | NO | 2021-04-22 | 2021-04-22
NEM-ST | 307389 | 39.452 | Solar PV | APPROVED | 2021-04-19 | 2021-04-22 | 2021-04-22 | 2021-04-22 | 2021-04-22 | 2021-04-23 | NO | NO | 2021-04-22 | 2021-04-29 | 2021-04-08 | 2021-04-23 | 2021-05-06 | 2021-05-07 | 14
NEM-ST | 301338 | 46.153 | Solar PV | APPROVED | 2021-04-05 | 2021-04-30 | 2021-04-30 | 2021-04-30 | 2021-04-30 | 2021-04-30 | NO | NO | 2021-04-30 | 2021-04-12 | 2021-05-18 | 2021-05-19 | 2021-05-19 | 2021-05-20 | 19
NEM-ST | 300349 | 61.495 | Solar PV | PENDING AHJ INSPECTION | 2021-04-22 | 2021-04-30 | 2021-04-30 | 2021-04-30 | 2021-04-30 | 2021-04-30 | NO | NO | 2021-04-30 | 2021-05-06
NEM-ST | 255189 | 61.087 | Solar PV | APPROVED | 2021-04-26 | 2021-04-30 | 2021-04-30 | 2021-04-30 | 2021-04-30 | 2021-04-30 | NO | NO | 2021-04-30 | 2021-06-16 | 2021-06-01 | 2021-06-03 | 2021-06-16 | 2021-06-17 | 47
NEM-ST | 308022 | 37.293 | Solar PV | APPROVED | 2021-04-27 | 2021-04-30 | 2021-04-30 | 2021-04-30 | 2021-04-30 | 2021-04-30 | NO | NO | 2021-04-30 | 2021-05-06 | 2021-04-12 | 2021-05-03 | 2021-05-06 | 2021-05-07 | 6
NEM-ST | 307358 | 156.081 | Solar PV | APPROVED | 2021-04-28 | 2021-04-30 | 2021-04-30 | 2021-04-30 | 2021-04-30 | 2021-04-30 | NO | NO | 2021-04-30 | 2021-04-30 | 2021-12-20 | 2021-12-21 | 2021-12-28 | 2021-12-29 | 242
NEM-ST | 307379 | 185.81 | Solar PV | APPROVED | 2021-04-28 | 2021-04-30 | 2021-04-30 | 2021-04-30 | 2021-04-30 | 2021-04-30 | NO | NO | 2021-04-30 | 2021-04-30 | 2022-01-26 | 2022-01-28 | 2022-01-31 | 2022-02-01 | 276
NEM-ST | 307385 | 185.81 | Solar PV | APPROVED | 2021-04-28 | 2021-04-30 | 2021-04-30 | 2021-04-30 | 2021-04-30 | 2021-04-30 | NO | NO | 2021-04-30 | 2021-04-30 | 2021-12-07 | 2021-12-13 | 2021-12-13 | 2021-12-14 | 227
NEM-ST | 307390 | 133.783 | Solar PV | APPROVED | 2021-04-28 | 2021-04-30 | 2021-04-30 | 2021-04-30 | 2021-04-30 | 2021-04-30 | NO | NO | 2021-04-30 | 2021-12-17 | 2021-12-07 | 2021-12-10 | 2021-12-28 | 2021-12-29 | 242
NEM-ST | 307393 | 133.783 | Solar PV | APPROVED | 2021-04-28 | 2021-04-30 | 2021-04-30 | 2021-04-30 | 2021-04-30 | 2021-04-30 | NO | NO | 2021-04-30 | 2021-12-17 | 2021-12-07 | 2021-12-10 | 2021-12-28 | 2021-12-29 | 242
NEM-ST | 307399 | 133.783 | Solar PV | APPROVED | 2021-04-28 | 2021-04-30 | 2021-04-30 | 2021-04-30 | 2021-04-30 | 2021-04-30 | NO | NO | 2021-04-30 | 2022-01-06 | 2021-12-07 | 2021-12-21 | 2022-01-06 | 2022-01-07 | 251
NEM-ST | 307402 | 156.081 | Solar PV | APPROVED | 2021-04-28 | 2021-04-30 | 2021-04-30 | 2021-04-30 | 2021-04-30 | 2021-04-30 | NO | NO | 2021-04-30 | 2021-12-21 | 2021-12-07 | 2021-12-10 | 2021-12-28 | 2021-12-29 | 242
NEM-ST | 307404 | 200.524 | Solar PV | APPROVED | 2021-04-28 | 2021-04-30 | 2021-04-30 | 2021-04-30 | 2021-04-30 | 2021-04-30 | NO | NO | 2021-04-30 | 2021-04-30 | 2021-12-07 | 2021-12-10 | 2021-12-14 | 2021-12-15 | 228
NEM-ST | 306067 | 651.932 | Solar PV | ISSUES | 2021-04-12 | 2021-05-04 | 2021-05-04 | 2021-07-09 | 2021-05-04 | 2021-05-06 | NO | NO | 2021-07-09 | 2021-07-09 | 2022-03-28 | 2022-03-29
NEM-ST | 307060 | 168.014 | Solar PV | ISSUES | 2021-04-12 | 2021-05-04 | 2021-05-04 | 2021-05-06 | 2021-05-04 | 2021-05-06 | NO | NO | 2021-05-04 |  | 2022-01-14 | 2021-11-12
NEM-ST | 295911 | 71.324 | Solar PV | APPROVED | 2021-04-29 | 2021-05-04 | 2021-05-04 | 2021-05-04 | 2021-05-04 | 2021-05-06 | NO | NO | 2021-05-04 | 2021-05-04 | 2021-09-10 | 2021-09-13 | 2021-09-16 | 2021-09-17 | 135
NEM-ST | 310238 | 189.716 | Solar PV | PENDING AHJ INSPECTION | 2021-04-29 | 2021-05-04 | 2021-05-04 | 2021-05-04 | 2021-05-04 | 2021-05-06 | NO | NO | 2021-05-04 | 2021-10-01
NEM-ST | 310318 | 259.049 | Solar PV | PENDING AHJ INSPECTION | 2021-04-29 | 2021-05-04 | 2021-05-04 | 2021-05-04 | 2021-05-04 | 2021-05-06 | NO | NO | 2021-05-04 | 2021-10-01
NEM-ST | 310484 | 481.552 | Solar PV | PENDING AHJ INSPECTION | 2021-05-03 | 2021-05-13 | 2021-05-13 | 2021-05-13 | 2021-05-13 | 2021-05-20 | NO | NO | 2021-05-13
NEM-ST | 310486 | 211.342 | Solar PV | PENDING AHJ INSPECTION | 2021-05-03 | 2021-05-13 | 2021-05-13 | 2021-05-13 | 2021-05-13 | 2021-05-20 | NO | NO | 2021-05-13
NEM-ST | 310490 | 72.659 | Solar PV | PENDING AHJ INSPECTION | 2021-05-03 | 2021-05-13 | 2021-05-13 | 2021-05-13 | 2021-05-13 | 2021-05-20 | NO | NO | 2021-05-13
NEM-ST | 310611 | 460.147 | Solar PV | PENDING AHJ INSPECTION | 2021-05-04 | 2021-05-13 | 2021-05-13 | 2021-05-13 | 2021-05-13 | 2021-05-20 | NO | NO | 2021-05-13 | 2021-05-13
NEM-ST | 310619 | 372.628 | Solar PV | PENDING AHJ INSPECTION | 2021-05-04 | 2021-05-13 | 2021-05-13 | 2021-05-13 | 2021-05-13 | 2021-05-20 | NO | NO | 2021-05-13 | 2021-05-13
NEM-ST | 310741 | 41.527 | Solar PV | APPROVED | 2021-05-06 | 2021-05-13 | 2021-05-13 | 2021-05-13 | 2021-05-13 | 2021-05-20 | NO | NO | 2021-05-13 | 2021-05-21 | 2021-07-22 | 2021-07-27 | 2021-07-27 | 2021-07-28 | 75
NEM-ST | 310796 | 33.423 | Solar PV | APPROVED | 2021-05-06 | 2021-05-13 | 2021-05-13 | 2021-05-13 | 2021-05-13 | 2021-05-20 | NO | NO | 2021-05-13 | 2021-07-28 | 2021-10-20 | 2021-10-22 | 2021-10-29 | 2021-11-01 | 169
NEM-ST | 310336 | 247.826 | Solar PV | PENDING AHJ INSPECTION | 2021-05-06 | 2021-05-13 | 2021-05-13 | 2021-05-13 | 2021-05-13 | 2021-05-20 | NO | NO | 2021-05-13 | 2021-10-01
NEM/PRD | 308183 | 15.36 | Battery Storage | APPROVED | 2021-04-22 | 2021-05-20 | 2021-05-20 | 2021-05-20 | 2021-05-20 | 2021-06-01 | NO | NO | N/A | N/A | 2021-12-06 | 2021-12-09 | 2021-12-20 | N/A | 214
NEM-ST | 309793 | 60.89 | Battery Storage + Solar PV | APPROVED | 2021-04-23 | 2021-05-20 | 2021-05-20 | 2021-05-20 | 2021-05-20 | 2021-06-01 | YES | YES | 2021-05-20 | 2021-05-20 | 2021-04-23 | 2021-05-26 | 2021-06-02 | 2021-06-03 | 13
NEM-ST | 312026 | 31.798 | Solar PV | APPROVED | 2021-05-11 | 2021-05-20 | 2021-05-20 | 2021-05-20 | 2021-05-20 | 2021-06-01 | NO | NO | 2021-05-20 | 2021-05-20 | 2021-05-13 | 2021-05-25 | 2021-06-03 | 2021-06-04 | 14
NEM-ST | 312384 | 249.462 | Solar PV | PENDING AHJ INSPECTION | 2021-05-12 | 2021-05-20 | 2021-05-20 | 2021-05-20 | 2021-05-20 | 2021-06-01 | NO | NO | 2021-05-20 | 2021-10-01
NEM-ST | 312370 | 54.771 | Solar PV | APPROVED | 2021-05-13 | 2021-05-20 | 2021-05-20 | 2021-05-20 | 2021-05-20 | 2021-06-01 | NO | NO | 2021-05-20 | 2021-10-06 | 2021-04-27 | 2021-05-24 | 2021-10-06 | 2021-10-07 | 139
NEM-ST | 312518 | 34.902 | Solar PV | APPROVED | 2021-05-14 | 2021-05-20 | 2021-05-20 | 2021-05-20 | 2021-05-20 | 2021-06-01 | NO | NO | 2021-05-20 | 2021-05-27 | 2021-05-05 | 2021-05-24 | 2021-06-01 | 2021-06-02 | 12
NEM-ST | 299459 | 290.07 | Solar PV | APPROVED | 2021-02-01 | 2021-05-21 | 2021-05-21 | 2021-05-21 | 2021-03-29 | 2021-03-30 | NO | NO | 2021-05-21 | 2021-06-16 | 2021-12-02 | 2021-12-07 | 2021-12-07 | 2021-12-08 | 200
NEM-ST | 309701 | 62.204 | Battery Storage + Solar PV | APPROVED | 2021-04-26 | 2021-05-21 | 2021-05-21 | 2021-05-21 | 2021-05-21 | 2021-06-01 | NO | NO | 2021-05-21 | 2021-06-30 | 2021-06-21 | 2021-06-21 | 2021-06-30 | 2021-07-01 | 40
NEM-ST | 312900 | 47.4 | Battery Storage + Solar PV | APPROVED | 2021-05-19 | 2021-05-21 | 2021-05-21 | 2021-05-21 | 2021-05-21 | 2021-06-01 | NO | NO | 2021-05-21 | 2021-06-08 | 2021-05-17 | 2021-05-21 | 2021-06-08 | 2021-06-09 | 18
NEM-ST | 313131 | 114.437 | Solar PV | PENDING AHJ INSPECTION | 2021-05-21 | 2021-05-24 | 2021-05-24 | 2021-05-24 | 2021-05-24 | 2021-06-01 | NO | NO | 2021-05-24 | 2021-05-27
NEM-ST | 313243 | 172.825 | Solar PV | PENDING AHJ INSPECTION | 2021-05-21 | 2021-05-24 | 2021-05-24 | 2021-05-24 | 2021-05-24 | 2021-06-02 | NO | NO | 2021-05-24 | 2021-10-01
NEM-ST | 301675 | 258.191 | Solar PV | APPROVED | 2021-03-16 | 2021-05-27 | 2021-05-27 | 2021-05-27 | 2021-03-23 | 2021-03-26 | NO | NO | 2021-03-23 | 2021-04-23 | 2021-12-06 | 2021-12-07 | 2021-12-07 | 2021-12-08 | 194
NEM-ST | 313534 | 160.213 | Solar PV | PENDING AHJ INSPECTION | 2021-05-25 | 2021-05-28 | 2021-05-28 | 2021-05-28 | 2021-05-28 | 2021-06-01 | NO | NO | 2021-05-28 | 2021-10-01
NEM-ST | 313812 | 70.882 | Solar PV | APPROVED | 2021-05-28 | 2021-06-03 | 2021-06-03 | 2021-06-03 | 2021-06-03 | 2021-06-08 | NO | NO | 2021-06-03 | 2021-08-25 | 2021-08-19 | 2021-08-20 | 2021-08-25 | 2021-08-26 | 83
NEM-ST | 313830 | 110.853 | Solar PV | APPROVED | 2021-05-28 | 2021-06-03 | 2021-06-03 | 2021-06-03 | 2021-06-03 | 2021-06-08 | NO | NO | 2021-06-03 | 2021-06-29 | 2021-09-24 | 2021-09-27 | 2021-09-27 | 2021-09-28 | 116
NEM-ST | 314001 | 31.149 | Solar PV | APPROVED | 2021-06-01 | 2021-06-10 | 2021-06-10 | 2021-06-10 | 2021-06-10 | 2021-06-11 | NO | NO | 2021-06-10 | 2021-06-22 | 2021-06-15 | 2021-06-16 | 2021-06-22 | 2021-06-23 | 12
NEM-ST | 314336 | 112.557 | Solar PV | APPROVED | 2021-06-03 | 2021-06-10 | 2021-06-10 | 2021-06-10 | 2021-06-10 | 2021-06-11 | NO | NO | 2021-06-10 | 2021-06-10 | 2021-11-05 | 2021-11-08 | 2021-11-08 | 2021-11-09 | 151
NEM-ST | 312775 | 89.076 | Solar PV | APPROVED | 2021-06-11 | 2021-06-14 | 2021-06-14 | 2021-06-14 | 2021-06-14 | 2021-06-15 | NO | NO | 2021-06-14 | 2022-04-25 | 2022-03-31 | 2022-04-01 | 2022-04-25 | 2022-04-26 | 315
NEM-ST | 312771 | 133.783 | Solar PV | ISSUES | 2021-06-11 | 2021-06-14 | 2021-06-14 | 2021-06-14 | 2021-06-14 | 2021-06-15 | NO | NO | 2021-06-14 |  | 2022-03-31 | 2022-04-01
NEM-ST | 300503 | 104.054 | Solar PV | PENDING AHJ INSPECTION | 2021-06-11 | 2021-06-14 | 2021-06-14 | 2021-06-14 | 2021-06-14 | 2021-06-15 | NO | NO | 2021-06-14
NEM-ST | 300519 | 96.47 | Solar PV | PENDING AHJ INSPECTION | 2021-06-11 | 2021-06-14 | 2021-06-14 | 2021-06-14 | 2021-06-14 | 2021-06-15 | NO | NO | 2021-06-14
NEM-ST | 300525 | 148.535 | Solar PV | PENDING AHJ INSPECTION | 2021-06-11 | 2021-06-14 | 2021-06-14 | 2021-06-14 | 2021-06-14 | 2021-06-15 | NO | NO | 2021-06-14
NEM-ST | 311997 | 35.175 | Solar PV | APPROVED | 2021-05-10 | 2021-06-18 | 2021-06-18 | 2021-06-18 | 2021-06-18 | 2021-06-21 | NO | NO | 2021-06-18 | 2021-06-18 | 2021-07-20 | 2021-07-22 | 2021-07-22 | 2021-07-26 | 34
NEM-ST | 316082 | 46.667 | Battery Storage + Solar PV | PENDING AHJ INSPECTION | 2021-06-21 | 2021-06-23 | 2021-06-23 | 2021-06-23 | 2021-06-23 | 2021-06-24 | NO | NO | 2021-06-23 | 2021-07-07
NEM-ST | 315794 | 290.343 | Solar PV | PENDING AHJ INSPECTION | 2021-06-21 | 2021-06-23 | 2021-06-23 | 2021-06-23 | 2021-06-23 | 2021-06-24 | NO | NO | 2021-06-23 | 2022-02-17
NEM-ST | 312773 | 74.173 | Solar PV | PENDING AHJ INSPECTION | 2021-06-11 | 2021-06-30 | 2021-06-30 | 2021-06-30 | 2021-06-30 | 2021-06-30 | NO | NO | 2021-06-30
NEM-ST | 312826 | 96.47 | Solar PV | PENDING AHJ INSPECTION | 2021-06-11 | 2021-06-30 | 2021-06-30 | 2021-06-30 | 2021-06-30 | 2021-06-30 | NO | NO | 2021-06-30
NEM-ST | 315694 | 36.856 | Solar PV | APPROVED | 2021-06-17 | 2021-07-07 | 2021-07-07 | 2021-07-07 | 2021-07-07 | 2021-07-08 | NO | NO | 2021-07-07 | 2021-07-12 | 2021-03-19 | 2021-07-08 | 2021-07-12 | 2021-07-13 | 5
NEM-ST | 315424 | 49.217 | Solar PV | APPROVED | 2021-07-02 | 2021-07-07 | 2021-07-07 | 2021-07-07 | 2021-07-07 | 2021-07-08 | NO | NO | 2021-07-07 | 2021-07-14 | 2021-07-08 | 2021-07-09 | 2021-07-14 | 2021-07-15 | 7
NEM-ST | 317757 | 410.282 | Solar PV | APPROVED | 2021-07-06 | 2021-07-07 | 2021-07-07 | 2021-07-07 | 2021-07-07 | 2021-07-08 | NO | NO | 2021-07-07 | 2021-12-09 | 2022-02-14 | 2022-02-15 | 2022-02-16 | 2022-02-17 | 224
NEM-ST | 316102 | 407.029 | Solar PV | PENDING AHJ INSPECTION | 2021-06-30 | 2021-07-14 | 2021-07-07 | 2021-07-07 | 2021-07-14 | 2021-07-14 | NO | NO | 2021-07-14 | 2021-07-23
NEM-ST | 317913 | 146.281 | Solar PV | APPROVED | 2021-07-07 | 2021-07-14 | 2021-07-14 | 2021-07-14 | 2021-07-14 | 2021-07-20 | NO | NO | 2021-07-14 | 2021-07-23 | 2022-03-02 | 2022-03-18 | 2022-03-20 | 2022-03-21 | 249
NEM-ST | 317840 | 29.084 | Solar PV | APPROVED | 2021-07-09 | 2021-07-14 | 2021-07-14 | 2021-07-14 | 2021-07-14 | 2021-07-20 | NO | NO | 2021-07-14 | 2021-07-14 | 2021-11-04 | 2021-11-06 | 2021-11-09 | 2021-11-10 | 118
NEM-ST | 318437 | 132.884 | Solar PV | APPROVED | 2021-07-12 | 2021-07-14 | 2021-07-14 | 2021-07-14 | 2021-07-14 | 2021-07-14 | NO | NO | 2021-07-14 | 2021-07-23 | 2021-09-01 | 2021-09-05 | 2021-09-07 | 2021-09-08 | 55
NEM/PRD | 312450 | 500 | Battery Storage | INITIAL REVIEW | 2021-05-17 | 2021-07-15 | 2021-07-27 | 2021-07-27 | 2021-08-12 | 2021-08-17 | NO | NO | N/A
NEM-ST | 317369 | 65.814 | Solar PV | APPROVED | 2021-07-14 | 2021-07-20 | 2021-07-20 | 2021-07-20 | 2021-07-20 | 2021-07-23 | NO | NO | 2021-07-20 | 2021-07-20 | 2021-09-09 | 2021-09-13 | 2021-09-13 | 2021-09-14 | 55
NEM-ST | 317619 | 193.243 | Solar PV | APPROVED | 2021-07-19 | 2021-07-21 | 2021-07-21 | 2021-07-21 | 2021-07-21 | 2021-07-23 | NO | NO | 2021-07-21 | 2021-07-21 | 2022-02-22 | 2022-02-23 | 2022-02-28 | 2022-03-01 | 222
NEM-ST | 317624 | 185.81 | Solar PV | APPROVED | 2021-07-19 | 2021-07-21 | 2021-07-21 | 2021-07-21 | 2021-07-21 | 2021-07-23 | NO | NO | 2021-07-21 | 2021-07-21 | 2022-02-22 | 2022-02-23 | 2022-02-28 | 2022-03-01 | 222
NEM-ST | 317626 | 133.783 | Solar PV | APPROVED | 2021-07-19 | 2021-07-21 | 2021-07-21 | 2021-07-21 | 2021-07-21 | 2021-07-23 | NO | NO | 2021-07-21 | 2021-07-21 | 2022-01-26 | 2022-01-28 | 2022-01-31 | 2022-02-01 | 194
NEM-ST | 317628 | 200.675 | Solar PV | APPROVED | 2021-07-19 | 2021-07-21 | 2021-07-21 | 2021-07-21 | 2021-07-21 | 2021-07-23 | NO | NO | 2021-07-21 | 2022-02-03 | 2022-01-26 | 2022-01-28 | 2022-02-03 | 2022-02-04 | 197
NEM-ST | 317880 | 178.992 | Solar PV | APPROVED | 2021-07-19 | 2021-07-21 | 2021-07-21 | 2021-07-21 | 2021-07-21 | 2021-07-23 | NO | NO | 2021-07-21 | 2022-02-17 | 2022-02-11 | 2022-02-14 | 2022-02-17 | 2022-02-18 | 211
NEM-ST | 316341 | 68.726 | Solar PV | APPROVED | 2021-06-29 | 2021-07-23 | 2021-07-23 | 2021-07-23 | 2021-07-23 | 2021-07-26 | NO | NO | 2021-07-23 | 2021-09-30 | 2021-09-17 | 2021-09-21 | 2021-09-30 | 2021-10-01 | 69
NEM-ST | 300523 | 154.924 | Solar PV | APPROVED | 2021-07-19 | 2021-07-23 | 2021-07-23 | 2021-07-23 | 2021-07-23 | 2021-07-26 | NO | NO | 2021-07-23 | 2021-07-23 | 2022-04-04 | 2022-04-06 | 2022-04-08 | 2022-04-11 | 259
NEM-ST | 317932 | 86.104 | Solar PV | APPROVED | 2021-07-07 | 2021-07-30 | 2021-07-30 | 2021-07-30 | 2021-07-30 | 2021-08-03 | NO | NO | 2021-07-30 | 2021-07-30 | 2021-11-29 | 2021-11-30 | 2021-11-30 | 2021-12-01 | 123
NEM-ST | 319746 | 63.922 | Solar PV | APPROVED | 2021-07-23 | 2021-07-30 | 2021-07-30 | 2021-07-30 | 2021-07-30 | 2021-08-03 | NO | NO | 2021-07-30 | 2021-07-30 | 2021-07-22 | 2021-08-03 | 2021-08-04 | 2021-08-05 | 5
NEM-ST | 319656 | 294.48 | Solar PV | APPROVED | 2021-07-26 | 2021-07-30 | 2021-07-30 | 2021-07-30 | 2021-07-30 | 2021-08-03 | NO | NO | 2021-07-30 | 2021-08-12 | 2021-11-15 | 2021-11-17 | 2021-11-18 | 2021-11-19 | 111
NEM-ST | 318316 | 71.752 | Solar PV | APPROVED | 2021-07-29 | 2021-07-30 | 2021-07-30 | 2021-07-30 | 2021-07-30 | 2021-08-03 | NO | NO | 2021-07-30 | 2021-07-30 | 2021-10-15 | 2021-10-19 | 2021-10-19 | 2021-10-20 | 81
NEM-ST | 301149 | 234.534 | Solar PV | PENDING AHJ INSPECTION | 2021-02-18 | 2021-08-02 | 2021-03-08 | 2021-03-08 | 2021-03-08 | 2021-03-09 | NO | NO | 2021-03-08 | 2021-08-02
NEM-ST | 310814 | 393.578 | Solar PV | APPROVED | 2021-05-11 | 2021-08-02 | 2021-08-02 | 2021-08-02 | 2021-08-02 | 2021-08-03 | NO | NO | 2021-08-02 | 2021-09-21 | 2022-04-12 | 2022-04-15 | 2022-04-18 | 2022-04-19 | 259
NEM-ST | 319440 | 30.64 | Solar PV | APPROVED | 2021-07-20 | 2021-08-02 | 2021-08-02 | 2021-08-02 | 2021-08-02 | 2021-08-03 | NO | NO | 2021-08-02 | 2021-08-12 | 2021-07-12 | 2021-08-03 | 2021-08-12 | 2021-08-13 | 10
NEM-ST | 317896 | 352.235 | Solar PV | PENDING AHJ INSPECTION | 2021-07-21 | 2021-08-02 | 2021-08-02 | 2021-08-02 | 2021-08-02 | 2021-08-03 | NO | NO | 2021-08-02 | 2021-08-02
NEM-ST | 319960 | 9.372 | Solar PV | APPROVED | 2021-07-26 | 2021-08-02 | 2021-08-02 | 2021-08-02 | 2021-08-02 | 2021-08-05 | NO | NO | 2021-08-02 | 2021-08-02 | 2021-10-15 | 2021-10-20 | 2021-10-20 | 2021-10-21 | 79
NEM-ST | 320616 | 413.36 | Solar PV | APPROVED | 2021-07-30 | 2021-08-02 | 2021-08-02 | 2021-08-02 | 2021-08-02 | 2021-08-03 | NO | NO | 2021-08-02 | 2021-09-02 | 2021-08-24 | 2021-08-25 | 2021-09-03 | 2021-09-07 | 32
NEM-ST | 320005 | 35.786 | Battery Storage + Solar PV | APPROVED | 2021-07-29 | 2021-08-05 | 2021-08-05 | 2021-08-05 | 2021-08-05 | 2021-08-09 | NO | NO | 2021-08-02 | 2021-08-02 | 2021-08-26 | 2021-08-27 | 2021-12-22 | 2021-12-27 | 139
NEM-ST | 315018 | 659.255 | Solar PV | INITIAL REVIEW | 2021-06-22 | 2021-08-09 | 2021-08-09 | 2021-08-09 | 2021-08-09 | 2021-08-12 | NO | NO | 2021-08-09
NEM-ST | 321723 | 345.055 | Solar PV | APPROVED | 2021-08-10 | 2021-08-13 | 2021-08-24 | 2021-08-24 | 2021-08-24 | 2021-08-25 | NO | NO | 2021-08-10 | 2021-08-10 | 2021-10-06 | 2021-10-07 | 2021-10-07 | 2021-10-08 | 55
NEM-ST | 321900 | 31.257 | Solar PV | APPROVED | 2021-08-11 | 2021-08-13 | 2021-08-13 | 2021-08-13 | 2021-08-13 | 2002-08-17 | NO | NO | 2021-08-13 | 2021-10-06 | 2021-07-28 | 2021-10-13 | 2021-12-09 | 2021-12-10 | 118
NEM-ST | 322034 | 21.224 | Solar PV | APPROVED | 2021-08-12 | 2021-08-13 | 2021-08-13 | 2021-08-13 | 2021-08-13 | 2021-08-17 | NO | NO | 2021-08-12 | 2021-08-12 | 2021-11-01 | 2021-11-02 | 2021-11-04 | 2021-11-05 | 83
NEM-ST | 322216 | 31.834 | Solar PV | APPROVED | 2021-08-13 | 2021-08-13 | 2021-08-13 | 2021-08-13 | 2021-08-13 | 2021-08-17 | NO | NO | 2021-08-13 | 2021-08-13 | 2021-12-01 | 2021-12-03 | 2021-12-30 | 2022-01-03 | 139
NEM-ST | 317627 | 148.497 | Solar PV | APPROVED | 2021-07-19 | 2021-08-24 | 2021-08-24 | 2021-08-24 | 2021-08-24 | 2021-08-25 | NO | NO | 2021-08-24 | 2022-02-07 | 2022-01-26 | 2022-01-28 | 2022-02-07 | 2022-02-08 | 167
NEM-ST | 321479 | 31.056 | Solar PV | APPROVED | 2021-08-09 | 2021-08-24 | 2021-08-24 | 2021-08-24 | 2021-08-24 | 2021-08-25 | NO | NO | 2021-08-24 | 2021-08-24 | 2021-08-09 | 2021-08-25 | 2021-09-01 | 2021-09-02 | 8
NEM-ST | 322591 | 132.622 | Solar PV | APPROVED | 2021-08-17 | 2021-08-24 | 2021-08-24 | 2021-08-24 | 2021-08-24 | 2021-08-25 | NO | NO | 2021-08-24 | 2021-12-29 | 2022-01-26 | 2022-01-28 | 2022-01-31 | 2022-02-01 | 160
NEM-ST | 322605 | 133.783 | Solar PV | APPROVED | 2021-08-23 | 2021-08-24 | 2021-08-24 | 2021-08-24 | 2021-08-24 | 2021-08-25 | NO | NO | 2021-08-24 | 2021-08-24 | 2022-03-29 | 2022-03-31 | 2022-03-31 | 2022-04-01 | 219
NEM-ST | 300521 | 163.513 | Solar PV | PENDING AHJ INSPECTION | 2021-08-23 | 2021-08-24 | 2021-08-24 | 2021-08-24 | 2021-08-24 | 2021-08-25 | NO | NO | 2021-08-24
NEM-ST | 322121 | 170.946 | Solar PV | PENDING AHJ INSPECTION | 2021-08-23 | 2021-08-24 | 2021-08-24 | 2021-08-24 | 2021-08-24 | 2021-08-25 | NO | NO | 2021-08-24 | 2021-08-24
NEM-ST | 300496 | 133.783 | Solar PV | APPROVED | 2021-08-23 | 2021-08-27 | 2021-08-27 | 2021-08-27 | 2021-08-27 | 2021-08-30 | NO | NO | 2021-08-27 | 2022-04-25 | 2022-03-29 | 2022-03-31 | 2022-04-25 | 2022-04-26 | 241
NEM-ST | 322125 | 111.486 | Solar PV | APPROVED | 2021-08-23 | 2021-08-27 | 2021-08-27 | 2021-08-27 | 2021-08-27 | 2021-08-30 | NO | NO | 2021-08-27 | 2021-08-27 | 2022-03-31 | 2022-04-01 | 2022-04-08 | 2022-04-11 | 224
NEM-ST | 322053 | 133.783 | Solar PV | PENDING AHJ INSPECTION | 2021-08-23 | 2021-08-27 | 2021-08-27 | 2021-08-27 | 2021-08-27 | 2021-08-30 | NO | NO | 2021-08-27 | 2021-08-27
NEM-ST | 318148 | 132.51 | Solar PV | PENDING AHJ INSPECTION | 2021-08-26 | 2021-08-27 | 2021-08-27 | 2021-08-27 | 2021-08-27 | 2021-08-30 | NO | NO | 2021-08-27 | 2021-11-09
NEM-ST | 322898 | 39.1 | Solar PV | APPROVED | 2021-08-27 | 2021-09-01 | 2021-09-01 | 2021-09-07 | 2021-09-07 | 2021-09-08 | NO | NO | 2021-08-27 | 2021-08-27 | 2021-11-10 | 2021-11-11 | 2021-11-24 | 2021-11-29 | 84
NEM-ST | 324041 | 30.617 | Solar PV | APPROVED | 2021-08-30 | 2021-09-01 | 2021-09-01 | 2021-09-01 | 2021-09-01 | 2021-09-02 | NO | NO | 2021-09-01 | 2021-09-01 | 2021-08-30 | 2021-09-02 | 2021-09-02 | 2021-09-03 | 1
NEM-ST | 324126 | 6.576 | Solar PV | APPROVED | 2021-08-30 | 2021-09-01 | 2021-09-01 | 2021-09-01 | 2021-09-01 | 2021-09-02 | NO | NO | 2021-09-01 | 2021-09-02 | 2021-09-07 | 2021-09-08 | 2021-09-16 | 2021-09-17 | 15
NEM-ST | 318988 | 48.754 | Solar PV | APPROVED | 2021-09-07 | 2021-09-07 | 2021-09-07 | 2021-09-07 | 2021-09-07 | 2021-09-08 | NO | NO | 2021-09-07 | 2022-01-06 | 2021-12-30 | 2022-01-03 | 2022-01-06 | 2022-01-07 | 121
NEM-ST | 323430 | 30 | Battery Storage | APPROVED | 2021-08-25 | 2021-09-09 | 2021-09-09 | 2021-09-09 | 2021-09-09 | 2021-09-15 | NO | NO | N/A | N/A | 2021-09-02 | 2021-09-13 | 2021-09-15 | N/A | 6
NEM/PRD | 318143 | 280 | Battery Storage | PENDING AHJ INSPECTION | 2021-07-21 | 2021-09-10 | 2021-09-10 | 2021-09-10 | 2021-09-10 | 2021-09-15 | NO | NO | 2021-09-10
NEM-ST | 324944 | 19.557 | Solar PV | APPROVED | 2021-09-08 | 2021-09-10 | 2021-09-10 | 2021-09-10 | 2021-09-10 | 2021-09-15 | NO | NO | 2021-09-10 | 2021-09-21 | 2021-10-22 | 2021-10-25 | 2021-10-25 | 2021-10-26 | 45
NEM-ST | 323961 | 37.531 | Solar PV | APPROVED | 2021-09-09 | 2021-09-10 | 2021-09-10 | 2021-09-10 | 2021-09-10 | 2021-09-15 | NO | NO | 2021-09-10 | 2021-09-10 | 2021-10-21 | 2021-11-22 | 2021-11-22 | 2021-11-23 | 73
NEM-ST | 300491 | 163.513 | Solar PV | PENDING AHJ INSPECTION | 2021-08-23 | 2021-09-13 | 2021-09-13 | 2021-09-13 | 2021-09-13 | 2021-09-15 | NO | NO | 2021-09-13
NEM-ST | 324769 | 181.488 | Solar PV | APPROVED | 2021-09-13 | 2021-09-13 | 2021-09-13 | 2021-09-13 | 2021-09-13 | 2021-09-15 | NO | NO | 2021-09-13 | 2021-09-13 | 2021-09-01 | 2021-09-14 | 2021-09-15 | 2021-09-16 | 2
NEM-ST | 324624 | 71.685 | Solar PV | APPROVED | 2021-09-07 | 2021-09-20 | 2021-09-20 | 2021-09-20 | 2021-09-20 | 2021-09-21 | NO | NO | 2021-09-20 | 2022-01-31 | 2021-01-18 | 2022-01-21 | 2022-02-01 | 2022-02-02 | 134
NEM-ST | 325850 | 50.97 | Solar PV | APPROVED | 2021-09-20 | 2021-10-03 | 2021-10-03 | 2021-10-03 | 2021-10-03 | 2021-10-06 | NO | NO | 2021-10-03 | 2021-10-03 | 2022-03-24 | 2022-03-25 | 2022-03-27 | 2022-03-28 | 175
NEM-ST | 327197 | 36.43 | Solar PV | ISSUES | 2021-09-20 | 2021-10-03 | 2021-10-03 | 2021-10-03 | 2021-10-03 | 2021-10-06 | NO | NO | 2021-10-03 | 2022-05-01 | 2022-04-06 | 2022-04-12
NEM-ST | 327576 | 83.274 | Solar PV | PENDING AHJ INSPECTION | 2021-09-27 | 2021-10-03 | 2021-10-03 | 2021-10-03 | 2021-10-03 | 2021-10-06 | NO | NO | 2021-10-03 | 2021-10-03
NEM-ST | 327871 | 66.741 | Solar PV | PENDING AHJ INSPECTION | 2021-09-27 | 2021-10-03 | 2021-10-03 | 2021-10-03 | 2021-10-03 | 2021-10-06 | NO | NO | 2021-10-03 | 2021-10-03
NEM-ST | 327819 | 39.172 | Solar PV | APPROVED | 2021-09-29 | 2021-10-03 | 2021-10-03 | 2021-10-03 | 2021-10-03 | 2021-10-06 | NO | NO | 2021-10-03 | 2021-10-03 | 2021-10-13 | 2021-10-15 | 2021-10-19 | 2021-10-20 | 16
NEM-ST | 328307 | 269.637 | Solar PV | PENDING AHJ INSPECTION | 2021-09-30 | 2021-10-03 | 2021-10-03 | 2021-10-13 | 2021-10-13 | 2021-10-15 | NO | NO | 2021-10-13 | 2021-10-13
NEM-ST | 325383 | 131.027 | Solar PV | APPROVED | 2021-09-14 | 2021-10-06 | 2021-10-06 | 2021-10-08 | 2021-10-06 | 2021-10-13 | NO | NO | 2021-09-14 | 2021-09-14 | 2021-10-08 | 2021-10-11 | 2021-11-16 | 2021-11-17 | 41
NEM-ST | 327133 | 35.672 | Solar PV | APPROVED | 2021-10-01 | 2021-10-06 | 2021-10-06 | 2021-10-06 | 2021-10-06 | 2021-10-12 | NO | NO | 2021-10-06 | 2021-10-06 | 2021-10-06 | 2021-10-07 | 2021-10-12 | 2021-10-13 | 6
NEM-ST | 327497 | 41.109 | Solar PV | APPROVED | 2021-10-06 | 2021-10-06 | 2021-10-06 | 2021-10-06 | 2021-10-06 | 2021-10-12 | NO | NO | 2021-10-06 | 2021-10-06 | 2022-03-04 | 2022-03-31 | 2022-03-31 | 2022-04-01 | 176
NEM-ST | 297212 | 89.038 | Solar PV | PENDING AHJ INSPECTION | 2021-10-06 | 2021-10-13 | 2021-10-13 | 2021-10-13 | 2021-10-13 | 2021-10-15 | NO | NO | 2021-10-13 | 2021-10-13
NEM-ST | 300512 | 126.351 | Solar PV | PENDING AHJ INSPECTION | 2021-10-06 | 2021-10-13 | 2021-10-13 | 2021-10-13 | 2021-10-13 | 2021-10-15 | NO | NO | 2021-10-13 | 2021-10-13
NEM-ST | 300517 | 245.27 | Solar PV | PENDING AHJ INSPECTION | 2021-10-06 | 2021-10-13 | 2021-10-13 | 2021-10-13 | 2021-10-13 | 2021-10-15 | NO | NO | 2021-10-13 | 2021-10-13
NEM-ST | 328566 | 118.919 | Solar PV | PENDING AHJ INSPECTION | 2021-10-06 | 2021-10-13 | 2021-10-13 | 2021-10-13 | 2021-10-13 | 2021-10-15 | NO | NO | 2021-10-13
NEM-ST | 328827 | 111.486 | Solar PV | PENDING AHJ INSPECTION | 2021-10-06 | 2021-10-13 | 2021-10-13 | 2021-10-13 | 2021-10-13 | 2021-10-15 | NO | NO | 2021-10-13
NEM-ST | 328996 | 107.121 | Solar PV | PENDING AHJ INSPECTION | 2021-10-06 | 2021-10-13 | 2021-10-13 | 2021-10-13 | 2021-10-13 | 2021-10-15 | NO | NO | 2021-10-13 | 2021-10-13
NEM-ST | 328562 | 104.054 | Solar PV | PENDING AHJ INSPECTION | 2021-10-07 | 2021-10-13 | 2021-10-13 | 2021-10-13 | 2021-10-13 | 2021-10-15 | NO | NO | 2021-10-13 | 2021-10-13
NEM-ST | 329673 | 119.765 | Solar PV | APPROVED | 2021-10-13 | 2021-10-13 | 2021-10-13 | 2021-10-13 | 2021-10-13 | 2021-10-15 | NO | NO | 2021-10-13 | 2021-12-15 | 2022-01-18 | 2022-01-20 | 2022-01-20 | 2022-01-21 | 99
NEM-ST | 328079 | 475.049 | Solar PV | PENDING AHJ INSPECTION | 2021-10-04 | 2021-10-19 | 2021-10-19 | 2021-10-19 | 2021-10-19 | 2021-10-19 | NO | NO | 2021-10-19
NEM-ST | 329675 | 66.09 | Solar PV | APPROVED | 2021-10-13 | 2021-10-19 | 2021-10-19 | 2021-10-19 | 2021-10-19 | 2021-10-21 | NO | NO | 2021-10-19 | 2021-12-15 | 2022-01-18 | 2022-01-20 | 2022-01-20 | 2022-01-21 | 93
NEM-ST | 329732 | 169.059 | Solar PV | APPROVED | 2021-10-13 | 2021-10-19 | 2021-10-19 | 2021-10-19 | 2021-10-19 | 2021-10-21 | NO | NO | 2021-10-19 | 2021-12-15 | 2022-01-18 | 2022-01-20 | 2022-01-20 | 2022-01-21 | 93
NEM-ST | 330166 | 72.466 | Solar PV | APPROVED | 2021-10-15 | 2021-10-19 | 2021-10-19 | 2021-10-19 | 2021-10-19 | 2021-10-20 | NO | NO | 2021-10-19 | 2021-10-20 | 2021-04-27 | 2021-10-20 | 2021-10-26 | 2021-10-27 | 7
NEM-ST | 319205 | 42.727 | Solar PV | PENDING AHJ INSPECTION | 2021-10-04 | 2021-10-26 | 2021-10-26 | 2021-10-26 | 2021-10-26 | 2021-11-04 | NO | NO | 2021-10-26
NEM-ST | 331335 | 91.598 | Solar PV | APPROVED | 2021-10-25 | 2021-10-26 | 2021-10-26 | 2021-10-26 | 2021-10-26 | 2021-11-03 | NO | NO | 2021-10-26 | 2022-01-12 | 2022-02-14 | 2022-02-15 | 2022-02-15 | 2022-02-16 | 112
NEM-ST | 331339 | 119.246 | Solar PV | APPROVED | 2021-10-25 | 2021-10-26 | 2021-10-26 | 2021-10-26 | 2021-10-26 | 2021-11-03 | NO | NO | 2021-10-26 | 2022-01-12 | 2022-01-25 | 2022-01-26 | 2022-01-26 | 2022-01-27 | 92
NEM-ST | 330930 | 89.58 | Solar PV | APPROVED | 2021-10-25 | 2021-10-28 | 2021-10-28 | 2021-10-28 | 2021-10-28 | 2021-11-03 | NO | NO | 2021-10-28 | 1991-10-28 | 2022-03-24 | 2022-03-28 | 2022-03-29 | 2022-03-30 | 152
NEM-ST | 329988 | 96.26 | Solar PV | APPROVED | 2021-10-14 | 2021-11-03 | 2021-11-03 | 2021-11-03 | 2021-11-03 | 2021-11-03 | NO | NO | 2021-11-03 | 2021-11-09 | 2022-02-10 | 2022-02-11 | 2022-02-11 | 2022-02-14 | 100
NEM-ST | 331372 | 10.451 | Solar PV | APPROVED | 2021-11-01 | 2021-11-03 | 2021-11-03 | 2021-11-03 | 2021-11-03 | 2021-11-09 | NO | NO | 2021-11-03 | 2021-11-03 | 2021-10-12 | 2021-11-29 | 2021-11-30 | 2021-12-01 | 27
NEM-ST | 331984 | 178.378 | Solar PV | PENDING AHJ INSPECTION | 2021-11-01 | 2021-11-03 | 2021-11-03 | 2021-11-03 | 2021-11-03 | 2021-12-15 | NO | NO | 2021-11-03
NEM-ST | 331488 | 295.949 | Solar PV | PENDING AHJ INSPECTION | 2021-10-26 | 2021-11-08 | 2021-11-08 | 2021-11-08 | 2021-11-08 | 2021-11-09 | NO | NO | 2021-11-08 | 2021-12-09
NEM-ST | 332150 | 34.431 | Solar PV | APPROVED | 2021-11-02 | 2021-11-08 | 2021-11-08 | 2021-11-08 | 2021-11-08 | 2021-11-09 | NO | NO | 2021-11-08 | 2021-11-16 | 2022-03-03 | 2022-03-22 | 2022-03-22 | 2022-03-23 | 134
NEM-ST | 332888 | 41.206 | Solar PV | APPROVED | 2021-11-09 | 2021-11-17 | 2021-11-17 | 2021-11-17 | 2021-11-17 | 2021-11-23 | NO | NO | 2021-11-17 | 2021-12-06 | 2021-10-06 | 2021-11-19 | 2021-12-06 | 2021-12-07 | 19
NEM-ST | 332890 | 41.206 | Solar PV | APPROVED | 2021-11-09 | 2021-11-17 | 2021-11-17 | 2021-11-17 | 2021-11-17 | 2021-11-23 | NO | NO | 2021-11-17 | 2021-12-06 | 2021-10-06 | 2021-11-17 | 2021-12-06 | 2021-12-07 | 19
NEM-ST | 334006 | 125.954 | Solar PV | APPROVED | 2021-11-17 | 2021-11-17 | 2021-11-17 | 2021-11-17 | 2021-11-17 | 2021-11-23 | NO | NO | 2021-11-17 | 2021-12-17 | 2021-12-07 | 2021-12-16 | 2021-12-17 | 2021-12-20 | 30
NEM-ST | 334087 | 62.977 | Solar PV | APPROVED | 2021-11-17 | 2021-11-17 | 2021-11-17 | 2021-11-17 | 2021-11-17 | 2021-11-23 | NO | NO | 2021-11-17 | 2021-12-22 | 2021-12-30 | 2022-01-03 | 2022-01-04 | 2022-01-05 | 48
NEM-ST | 330299 | 336.693 | Solar PV | PENDING AHJ INSPECTION | 2021-11-16 | 2021-11-23 | 2021-11-23 | 2021-11-23 | 2021-11-23 | 2021-11-24 | NO | NO | 2021-11-16 | 2021-11-16
NEM-ST | 334050 | 20.328 | Battery Storage + Solar PV | APPROVED | 2021-11-17 | 2021-11-23 | 2021-11-23 | 2021-11-23 | 2021-11-23 | 2021-11-24 | NO | NO | 2021-11-23 | 2021-12-02 | 2022-02-04 | 2022-02-04 | 2022-02-07 | 2022-02-08 | 76
NEM-ST | 334156 | 117.183 | Solar PV | APPROVED | 2021-11-17 | 2021-11-23 | 2021-11-23 | 2021-11-23 | 2021-11-23 | 2021-11-24 | NO | NO | 2021-11-23 | 2021-12-02 | 2021-11-30 | 2021-12-02 | 2021-12-03 | 2021-12-05 | 10
NEM/PRD | 334038 | 35 | Battery Storage | ISSUES | 2021-11-17 | 2021-11-23 | 2021-11-23 | 2021-11-23 | 2021-11-23 | 2021-11-24 | NO | NO | N/A | N/A | 2022-04-05 | 2022-04-06 |  | N/A
NEM-ST | 334324 | 35.758 | Solar PV | PENDING AHJ INSPECTION | 2021-11-18 | 2021-11-23 | 2021-11-23 | 2021-11-23 | 2021-11-23 | 2021-11-24 | NO | NO | 2021-11-23 | 2021-11-30
NEM-ST | 333441 | 43.643 | Battery Storage + Solar PV | ISSUES | 2021-11-12 | 2021-11-24 | 2021-11-24 | 2021-11-24 | 2021-11-24 | 2021-11-24 | NO | NO | 2021-11-12 | 2021-11-12 | 2021-09-22
NEM-ST | 331555 | 5.652 | Solar PV | APPROVED | 2021-11-22 | 2021-12-01 | 2021-12-01 | 2021-12-01 | 2021-12-01 | 2021-12-06 | NO | NO | 2021-12-01 | 2021-12-15 | 2021-10-21 | 2022-02-07 | 2022-02-09 | 2022-02-10 | 70
NEM-ST | 334858 | 11.204 | Solar PV | PENDING AHJ INSPECTION | 2021-11-23 | 2021-12-01 | 2021-12-01 | 2021-12-01 | 2021-12-01 | 2021-12-06 | NO | NO | 2021-11-23 | 2021-11-23
NEM-ST | 335118 | 113.018 | Solar PV | PENDING AHJ INSPECTION | 2021-11-24 | 2021-12-01 | 2021-12-01 | 2021-12-01 | 2021-12-01 | 2021-12-06 | NO | NO | 2021-12-01 | 2021-12-19
NEM-ST | 335029 | 39.453 | Solar PV | PENDING SDGE INSPECTION | 2021-11-24 | 2021-12-01 | 2021-12-01 | 2021-12-01 | 2021-12-01 | 2021-12-06 | NO | NO | 2021-12-01 | 2021-12-06 | 2022-04-25
NEM-ST | 300570 | 283.031 | Solar PV | PENDING AHJ INSPECTION | 2021-02-10 | 2021-12-07 | 2021-02-11 | 2021-02-11 | 2021-02-11 | 2021-02-16 | NO | NO | 2021-02-11 | 2022-01-24
NEM-ST | 331107 | 62.187 | Solar PV | APPROVED | 2021-10-26 | 2021-12-07 | 2021-12-07 | 2021-12-07 | 2021-12-07 | 2021-12-09 | NO | NO | 2021-12-07 | 2021-12-09 | 2021-11-08 | 2021-12-08 | 2021-12-09 | 2021-12-10 | 2
NEM-ST | 334090 | 90.737 | Solar PV | PENDING AHJ INSPECTION | 2021-11-17 | 2021-12-07 | 2021-12-07 | 2021-12-07 | 2021-12-07 | 2021-12-09 | NO | NO | 2021-12-07 | 2021-12-07
NEM-ST | 336833 | 49.685 | Solar PV | APPROVED | 2021-12-09 | 2021-12-10 | 2021-12-10 | 2021-12-10 | 2021-12-10 | 2021-12-15 | NO | NO | 2021-12-10 | 2021-12-10 | 2022-03-22 | 2022-03-29 | 2022-04-05 | 2022-04-06 | 116
NEM-ST | 337041 | 42.83 | Solar PV | PENDING AHJ INSPECTION | 2021-12-09 | 2021-12-10 | 2021-12-10 | 2021-12-10 | 2021-12-10 | 2021-12-15 | NO | NO | 2021-12-10
NEM-ST | 336735 | 98.479 | Solar PV | PENDING AHJ INSPECTION | 2021-12-10 | 2021-12-15 | 2021-12-15 | 2021-12-15 | 2021-12-15 | 2021-12-20 | NO | NO | 2021-12-15
NEM-ST | 337494 | 388.892 | Solar PV | PENDING AHJ INSPECTION | 2021-12-14 | 2021-12-15 | 2021-12-15 | 2021-12-15 | 2021-12-15 | 2021-12-17 | NO | NO | 2021-12-15 | 2021-12-29
NEM-ST | 337502 | 162.429 | Solar PV | PENDING AHJ INSPECTION | 2021-12-14 | 2021-12-15 | 2021-12-15 | 2021-12-15 | 2021-12-15 | 2021-12-20 | NO | NO | 2021-12-15 | 2021-12-29
NEM-ST | 337169 | 176.256 | Solar PV | PENDING AHJ INSPECTION | 2021-12-10 | 2021-12-16 | 2021-12-16 | 2021-12-16 | 2021-12-16 | 2021-12-20 | NO | NO | 2021-12-16
NEM-ST | 337206 | 113.541 | Solar PV | PENDING AHJ INSPECTION | 2021-12-10 | 2021-12-16 | 2021-12-16 | 2021-12-16 | 2021-12-16 | 2021-12-20 | NO | NO | 2021-12-16
NEM-ST | 337207 | 89.813 | Solar PV | PENDING AHJ INSPECTION | 2021-12-10 | 2021-12-16 | 2021-12-16 | 2021-12-16 | 2021-12-16 | 2021-12-20 | NO | NO | 2021-12-16
NEM-ST | 337210 | 147.342 | Solar PV | PENDING AHJ INSPECTION | 2021-12-10 | 2021-12-16 | 2021-12-16 | 2021-12-16 | 2021-12-16 | 2021-12-20 | NO | NO | 2021-12-16
NEM-ST | 337258 | 58.177 | Solar PV | PENDING AHJ INSPECTION | 2021-12-12 | 2021-12-16 | 2021-12-16 | 2021-12-16 | 2021-12-16 | 2021-12-20 | NO | NO | 2021-12-16
NEM-ST | 336922 | 106.049 | Solar PV | APPROVED | 2021-12-13 | 2021-12-16 | 2021-12-16 | 2021-12-16 | 2021-12-16 | 2021-12-20 | NO | NO | 2021-12-16 | 2021-12-16 | 2022-01-20 | 2022-02-08 | 2022-02-09 | 2022-02-10 | 55
NEM-ST | 337555 | 252.582 | Solar PV | PENDING AHJ INSPECTION | 2021-12-14 | 2021-12-16 | 2021-12-16 | 2021-12-16 | 2021-12-16 | 2021-12-20 | NO | NO | 2021-12-16 | 2021-12-16
NEM-ST | 319491 | 391.458 | Solar PV | PENDING AHJ INSPECTION | 2021-12-15 | 2021-12-19 | 2021-12-19 | 2021-12-19 | 2021-12-19 | 2021-12-29 | NO | NO | 2021-12-19 | 2022-01-10
NEM-ST | 337976 | 55.075 | Solar PV | PENDING SDGE INSPECTION | 2021-12-17 | 2021-12-19 | 2021-12-19 | 2021-12-19 | 2021-12-19 | 2021-12-29 | NO | NO | 2021-12-17 | 2021-12-17 | 2022-04-19
NEM-ST | 337528 | 85.999 | Solar PV | PENDING AHJ INSPECTION | 2021-12-14 | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2021-12-29 | NO | NO | 2021-12-22 | 2021-12-29
NEM-ST | 337916 | 84.63 | Solar PV | PENDING AHJ INSPECTION | 2021-12-20 | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2021-12-29 | NO | NO | 2021-12-22
NEM-ST | 338237 | 146.866 | Solar PV | PENDING AHJ INSPECTION | 2021-12-20 | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2021-12-29 | NO | NO | 2021-12-22 | 2022-01-06
NEM-ST | 338480 | 90.742 | Solar PV | PENDING AHJ INSPECTION | 2021-12-22 | 2021-12-29 | 2021-12-29 | 2021-12-29 | 2021-12-29 | 2022-01-04 | NO | NO | 2021-12-29 | 2021-12-29
NEM-ST | 338987 | 381.558 | Solar PV | PENDING AHJ INSPECTION | 2021-12-28 | 2021-12-29 | 2021-12-29 | 2021-12-29 | 2021-12-29 | 2022-01-04 | NO | NO | 2021-12-29
NEM-ST | 338990 | 44.026 | Solar PV | PENDING AHJ INSPECTION | 2021-12-28 | 2021-12-29 | 2021-12-29 | 2021-12-29 | 2021-12-29 | 2022-01-04 | NO | NO | 2021-12-29
NEM-ST | 335921 | 44.398 | Solar PV | PENDING AHJ INSPECTION | 2021-12-29 | 2021-12-29 | 2021-12-29 | 2021-12-29 | 2021-12-29 | 2022-01-04 | NO | NO | 2021-12-29 | 2021-01-24
NEM-ST | 339148 | 94.167 | Solar PV | PENDING AHJ INSPECTION | 2021-12-29 | 2022-01-05 | 2022-01-05 | 2022-01-05 | 2022-01-05 | 2022-01-12 | NO | NO | 2022-01-05
NEM-ST | 339319 | 861.363 | Solar PV | PENDING AHJ INSPECTION | 2021-12-30 | 2022-01-05 | 2022-01-05 | 2022-01-05 | 2022-01-05 | 2022-01-12 | NO | NO | 2022-01-05 | 2022-01-10
NEM-ST | 339272 | 33.852 | Solar PV | PENDING AHJ INSPECTION | 2021-12-30 | 2022-01-05 | 2022-01-05 | 2022-01-05 | 2022-01-05 | 2022-01-12 | NO | NO | 2022-01-05 | 2022-01-05
NEM-ST | 338546 | 68.316 | Solar PV | PENDING AHJ INSPECTION | 2022-01-02 | 2022-01-05 | 2022-01-05 | 2022-01-05 | 2022-01-05 | 2022-01-12 | NO | NO | 2022-01-05 | 2022-01-10
NEM-ST | 339179 | 38.138 | Solar PV | PENDING AHJ INSPECTION | 2022-01-02 | 2022-01-05 | 2022-01-05 | 2022-01-05 | 2022-01-05 | 2022-01-12 | NO | NO | 2022-01-05 | 2022-01-10
NEM-ST | 339184 | 47.867 | Solar PV | PENDING AHJ INSPECTION | 2022-01-02 | 2022-01-05 | 2022-01-05 | 2022-01-05 | 2022-01-05 | 2022-01-12 | NO | NO | 2022-01-05 | 2022-01-10
NEM-ST | 338768 | 74.76 | Solar PV | PENDING AHJ INSPECTION | 2022-01-02 | 2022-01-05 | 2022-01-05 | 2022-01-05 | 2022-01-05 | 2022-01-12 | NO | NO | 2022-01-05 | 2022-01-10
NEM-ST | 339446 | 50.319 | Battery Storage + Solar PV | APPROVED | 2022-01-03 | 2022-01-05 | 2022-01-05 | 2022-01-05 | 2022-01-05 | 2022-01-12 | NO | NO | 2022-01-05 | 2022-01-05 | 2022-04-08 | 2022-04-13 | 2022-04-25 | 2022-04-26 | 110
NEM-ST | 339496 | 13.769 | Solar PV | APPROVED | 2022-01-03 | 2022-01-05 | 2022-01-05 | 2022-01-05 | 2022-01-05 | 2022-01-12 | NO | NO | 2022-01-05 | 2022-02-17 | 2022-04-05 | 2022-04-08 | 2022-04-08 | 2022-04-11 | 93
NEM-ST | 337699 | 58.548 | Solar PV | APPROVED | 2021-12-22 | 2022-01-18 | 2022-01-18 | 2022-01-18 | 2022-01-18 | 2022-01-24 | NO | NO | 2022-01-18 | 2022-03-16 | 2022-03-03 | 2022-03-07 | 2022-03-16 | 2022-03-17 | 57
NEM-ST | 339276 | 133.301 | Solar PV | PENDING AHJ INSPECTION | 2021-12-30 | 2022-01-18 | 2022-01-18 | 2022-01-18 | 2022-01-18 | 2022-01-24 | NO | NO | 2022-01-18
NEM/PRD | 340088 | 240 | Battery Storage | APPROVED | 2022-01-12 | 2022-01-18 | 2022-01-18 | 2022-01-18 | 2022-01-18 | 2022-01-24 | NO | NO | N/A | N/A | 2021-11-16 | 2022-01-21 | 2022-01-24 | N/A | 6
NEM-ST | 340713 | 79.774 | Solar PV | PENDING AHJ INSPECTION | 2022-01-17 | 2022-01-18 | 2022-01-18 | 2022-01-18 | 2022-01-18 | 2022-01-24 | NO | NO | 2022-01-18
NEM-ST | 340980 | 50.387 | Solar PV | PENDING AHJ INSPECTION | 2022-01-19 | 2022-01-27 | 2022-01-27 | 2022-01-27 | 2022-01-27 | 2022-02-04 | NO | NO | 2022-01-27
NEM-ST | 340982 | 62.621 | Solar PV | PENDING AHJ INSPECTION | 2022-01-19 | 2022-01-27 | 2022-01-27 | 2022-01-27 | 2022-01-27 | 2022-02-04 | NO | NO | 2022-01-27
NEM-ST | 340646 | 81.724 | Solar PV | PENDING AHJ INSPECTION | 2022-01-20 | 2022-01-27 | 2022-01-27 | 2022-01-27 | 2022-01-27 | 2022-02-04 | NO | NO | 2022-01-27 | 2022-01-27
NEM-ST | 328659 | 200.675 | Solar PV | PENDING AHJ INSPECTION | 2022-01-24 | 2022-01-27 | 2022-01-27 | 2022-01-27 | 2022-01-27 | 2022-02-04 | NO | NO | 2022-01-27 | 2022-01-27
NEM-ST | 340367 | 81.643 | Solar PV | PENDING AHJ INSPECTION | 2022-01-24 | 2022-01-27 | 2022-01-27 | 2022-01-27 | 2022-01-27 | 2022-02-04 | NO | NO | 2022-01-27
NEM-ST | 337330 | 397.561 | Solar PV | PENDING AHJ INSPECTION | 2022-01-25 | 2022-01-27 | 2022-01-27 | 2022-01-27 | 2022-01-27 | 2022-02-04 | NO | NO | 2022-01-27
NEM-ST | 337332 | 453.359 | Solar PV | PENDING AHJ INSPECTION | 2022-01-25 | 2022-01-27 | 2022-01-27 | 2022-01-27 | 2022-01-27 | 2022-02-04 | NO | NO | 2022-01-27
NEM-ST | 340370 | 93.676 | Solar PV | PENDING AHJ INSPECTION | 2022-01-26 | 2022-01-27 | 2022-01-27 | 2022-01-27 | 2022-01-27 | 2022-02-04 | NO | NO | 2022-01-27 | 2022-01-27
NEM-ST | 341489 | 151.136 | Solar PV | PENDING AHJ INSPECTION | 2022-01-25 | 2022-01-28 | 2022-01-28 | 2022-01-28 | 2022-01-28 | 2022-02-04 | NO | NO | 2022-01-28
NEM-ST | 342494 | 192.146 | Solar PV | PENDING AHJ INSPECTION | 2022-02-02 | 2022-02-03 | 2022-02-03 | 2022-02-03 | N/A | N/A | NO | NO | 2022-02-03
NEM-ST | 339684 | 999.729 | Solar PV | PENDING AHJ INSPECTION | 2022-01-05 | 2022-02-04 | 2022-02-04 | 2022-02-04 | 2022-02-04 | 2022-02-08 | NO | NO | 2022-02-04
NEM-ST | 341159 | 52.042 | Solar PV | APPROVED | 2022-02-02 | 2022-02-04 | 2022-02-04 | 2022-02-04 | 2022-02-04 | 2022-02-08 | NO | NO | 2022-02-04 | 2022-02-04 | 2022-01-06 | 2022-02-07 | 2022-02-08 | 2022-02-09 | 4
NEM-ST | 342505 | 161.382 | Solar PV | PENDING AHJ INSPECTION | 2022-02-02 | 2022-02-04 | 2022-02-04 | 2022-02-04 | N/A | N/A | NO | NO | 2022-02-07
NEM-ST | 342515 | 146.858 | Solar PV | PENDING AHJ INSPECTION | 2022-02-02 | 2022-02-04 | 2022-02-04 | 2022-02-04 | N/A | N/A | NO | NO | 2022-02-04
NEM-ST | 342518 | 215.849 | Solar PV | PENDING AHJ INSPECTION | 2022-02-02 | 2022-02-04 | 2022-02-04 | 2022-02-04 | N/A | N/A | NO | NO | 2022-02-04
NEM-ST | 342108 | 54.61 | Solar PV | APPROVED | 2022-02-03 | 2022-02-04 | 2022-02-04 | 2022-02-04 | 2022-02-04 | 2022-02-08 | NO | NO | 2022-02-04 | 2022-02-17 | 2022-01-25 | 2022-02-09 | 2022-02-17 | 2022-02-18 | 13
NEM-ST | 338906 | 193.443 | Solar PV | PENDING AHJ INSPECTION | 2022-01-07 | 2022-02-09 | 2022-02-09 | 2022-02-09 | 2022-02-09 | 2022-02-15 | NO | NO | 2022-02-09
NEM-ST | 339969 | 302.793 | Solar PV | PENDING AHJ INSPECTION | 2022-01-10 | 2022-02-09 | 2022-02-09 | 2022-02-09 | 2022-02-09 | 2022-02-15 | NO | NO | 2022-02-09
NEM-PRD | 342317 | 60 | Battery Storage | PENDING AHJ INSPECTION | 2022-02-01 | 2022-02-09 | 2022-02-09 | 2022-02-09 | 2022-02-09 | 2022-02-15 | NO | NO | N/A | N/A
NEM-PRD | 339712 | 60 | Battery Storage | PENDING AHJ INSPECTION | 2022-02-01 | 2022-02-09 | 2022-02-09 | 2022-02-09 | 2022-02-09 | 2022-02-15 | NO | NO | N/A
NEM-ST | 342754 | 201.306 | Solar PV | PENDING AHJ INSPECTION | 2022-02-04 | 2022-02-09 | 2022-02-09 | 2022-02-09 | 2022-02-09 | 2022-02-15 | NO | NO | 2022-02-09
NEM-ST | 343091 | 47.798 | Solar PV | PENDING AHJ INSPECTION | 2022-02-08 | 2022-02-09 | 2022-02-09 | 2022-02-09 | 2022-02-09 | 2022-02-15 | NO | NO | 2022-02-09
NEM-ST | 343165 | 14.062 | Solar PV | PENDING AHJ INSPECTION | 2022-02-09 | 2022-02-09 | 2022-02-09 | 2022-02-09 | 2022-02-09 | 2022-02-28 | NO | NO | 2022-02-09 | 2022-02-17
NEM-ST | 328848 | 91.228 | Solar PV | APPROVED | 2021-10-05 | 2022-02-19 | 2022-02-19 | 2022-02-19 | 2022-02-19 | 2022-02-28 | NO | NO | 2022-02-19 | 2022-02-28 | 2022-01-28 | 2022-02-23 | 2022-02-28 | 2022-03-01 | 9
NEM-ST | 341746 | 476.576 | Solar PV | PENDING AHJ INSPECTION | 2022-01-26 | 2022-02-19 | 2022-02-19 | 2022-02-19 | 2022-02-19 | 2022-02-28 | NO | NO | 2022-02-19
NEM-ST | 341889 | 268.149 | Solar PV | PENDING AHJ INSPECTION | 2022-01-28 | 2022-02-19 | 2022-02-19 | 2022-02-19 | 2022-02-19 | 2022-02-28 | NO | NO | 2022-02-19
NEM-ST | 342502 | 332.448 | Solar PV | PENDING AHJ INSPECTION | 2022-02-02 | 2022-02-19 | 2022-02-19 | 2022-02-19 | 2022-02-19 | 2022-02-28 | NO | NO | 2022-02-19
NEM-ST | 341155 | 165.133 | Battery Storage + Solar PV | PENDING AHJ INSPECTION | 2022-01-25 | 2022-02-24 | 2022-02-24 | 2022-02-24 | 2022-02-24 | 2022-02-28 | NO | NO | 2022-02-24
NEM-ST | 342675 | 52.903 | Solar PV | APPROVED | 2022-02-03 | 2022-02-24 | 2022-02-24 | 2022-02-24 | 2022-02-24 | 2022-02-28 | NO | NO | 2022-02-24 | 2022-03-15 | 2022-02-15 | 2022-02-25 | 2022-03-15 | 2022-03-16 | 19
NEM-ST | 306784 | 36.926 | Solar PV | APPROVED | 2022-02-08 | 2022-02-24 | 2022-02-24 | 2022-02-24 | 2022-02-24 | 2022-02-28 | NO | NO | 2022-02-24 | 2022-03-02 | 2022-02-08 | 2022-02-25 | 2022-03-08 | 2022-03-09 | 12
NEM-ST | 284485 | 51.913 | Battery Storage + Solar PV | PENDING AHJ INSPECTION | 2020-10-13 | 2022-03-03 | 2022-03-03 | 2022-03-03 | 2020-11-10 | 2020-11-15 | NO | NO | 2020-11-05 | 2022-03-03
NEM-ST | 342308 | 56.925 | Solar PV | PENDING AHJ INSPECTION | 2022-02-25 | 2022-03-03 | 2022-03-03 | 2022-03-03 | 2022-03-03 | 2022-03-08 | NO | NO | 2022-03-03
NEM-ST | 343799 | 52.459 | Solar PV | PENDING AHJ INSPECTION | 2022-03-04 | 2022-03-11 | 2022-03-11 | 2022-03-11 | 2022-03-11 | 2022-03-20 | NO | NO | 2022-03-11 | 2022-03-11
NEM-ST | 335818 | 45.319 | Battery Storage + Solar PV | APPROVED | 2022-03-07 | 2022-03-11 | 2022-03-11 | 2022-03-11 | 2021-12-07 | 2021-12-16 | NO | NO | 2021-12-07 | 2022-03-15 | 2022-04-01 | 2022-04-08 | 2022-04-18 | 2022-04-19 | 38
NEM-ST | 335359 | 111.699 | Solar PV | PENDING AHJ INSPECTION | 2021-11-29 | 2022-03-12 | 2022-03-12 | 2022-03-12 | 2022-03-12 | 2022-03-16 | NO | NO | 2022-03-12 | 2022-03-12
NEM-ST | 345765 | 40.481 | Solar PV | PENDING AHJ INSPECTION | 2022-03-03 | 2022-03-12 | 2022-03-12 | 2022-03-12 | 2022-03-12 | 2022-03-16 | NO | NO | 2022-03-12
NEM-ST | 346757 | 30.981 | Solar PV | PENDING AHJ INSPECTION | 2022-03-15 | 2022-03-18 | 2022-03-18 | 2022-03-18 | 2022-03-18 | 2022-03-20 | NO | NO | 2022-03-18 | 2022-03-20
NEM-ST | 344966 | 176.158 | Solar PV | PENDING AHJ INSPECTION | 2022-02-24 | 2022-03-20 | 2022-03-20 | 2022-03-20 | 2022-03-20 | 2022-03-29 | NO | NO | 2022-03-20 | 2022-03-21
NEM-ST | 346153 | 75.738 | Solar PV | APPROVED | 2022-03-07 | 2022-03-20 | 2022-03-12 | 2022-03-12 | 2022-03-12 | 2022-03-16 | NO | NO | 2022-03-12 | 2022-03-12 | 2022-02-18 | 2022-03-21 | 2022-03-21 | 2022-03-22 | 1
NEM-ST | 346566 | 90.331 | Solar PV | PENDING AHJ INSPECTION | 2022-03-10 | 2022-03-20 | 2022-03-20 | 2022-03-20 | 2022-03-20 | 2022-03-29 | NO | NO | 2022-03-20 | 2022-03-20
NEM-ST | 347416 | 50.317 | Solar PV | PENDING AHJ INSPECTION | 2022-03-16 | 2022-03-20 | 2022-03-20 | 2022-03-20 | 2022-03-20 | 2022-03-29 | NO | NO | 2022-03-20
NEM-ST | 337260 | 33.208 | Solar PV | PENDING AHJ INSPECTION | 2021-12-21 | 2022-03-22 | 2022-03-22 | 2022-03-22 | 2022-03-22 | 2022-03-29 | NO | NO | 2022-03-22 | 2022-03-22
NEM-ST | 347276 | 16.266 | Solar PV | PENDING AHJ INSPECTION | 2022-03-16 | 2022-03-22 | 2022-03-22 | 2022-03-22 | 2022-03-22 | 2022-03-29 | NO | NO | 2022-03-22 | 2022-03-22
NEM-ST | 348883 | 991.048 | Solar PV | PENDING AHJ INSPECTION | 2022-03-21 | 2022-03-22 | 2022-03-22 | 2022-03-22 | 2022-03-22 | 2022-03-29 | NO | NO | 2022-03-22
NEM-ST | 339106 | 358.899 | Solar PV | PENDING AHJ INSPECTION | 2021-12-31 | 2022-03-29 | 2022-03-29 | 2022-03-29 | 2022-03-29 | 2022-03-29 | NO | NO | 2022-03-29
NEM-ST | 345358 | 18.241 | Solar PV | PENDING AHJ INSPECTION | 2022-03-09 | 2022-03-29 | 2022-03-29 | 2022-03-29 | 2022-03-29 | 2022-03-29 | NO | NO | 2022-03-29
NEM-ST | 347558 | 399.377 | Solar PV | PENDING AHJ INSPECTION | 2022-03-17 | 2022-03-29 | 2022-03-29 | 2022-03-29 | 2022-03-29 | 2022-03-29 | NO | NO | 2022-03-29
NEM-ST | 343685 | 97.428 | Solar PV | PENDING AHJ INSPECTION | 2022-03-23 | 2022-03-29 | 2022-03-29 | 2022-03-29 | 2022-03-29 | 2022-03-29 | NO | NO | 2022-03-29
NEM-ST | 343696 | 147.568 | Solar PV | PENDING AHJ INSPECTION | 2022-03-23 | 2022-03-29 | 2022-03-29 | 2022-03-29 | 2022-03-29 | 2022-03-29 | NO | NO | 2022-03-29
NEM-ST | 346562 | 72.265 | Solar PV | PENDING AHJ INSPECTION | 2022-03-24 | 2022-03-29 | 2022-03-29 | 2022-03-29 | 2022-03-29 | 2022-03-29 | NO | NO | 2022-03-29 | 2022-03-29
NEM-ST | 346573 | 87.165 | Solar PV | PENDING AHJ INSPECTION | 2022-03-24 | 2022-03-29 | 2022-03-29 | 2022-03-29 | 2022-03-29 | 2022-03-29 | NO | NO | 2022-03-29 | 2022-03-29
NEM-ST | 349427 | 347.723 | Solar PV | PENDING AHJ INSPECTION | 2022-03-24 | 2022-03-29 | 2022-03-29 | 2022-03-29 | 2022-03-29 | 2022-03-29 | NO | NO | 2022-03-29
NEM-ST | 349434 | 77.453 | Solar PV | PENDING AHJ INSPECTION | 2022-03-24 | 2022-03-29 | 2022-03-29 | 2022-03-29 | 2022-03-29 | 2022-03-29 | NO | NO | 2022-03-29
NEM-ST | 347148 | 233.983 | Solar PV | PENDING AHJ INSPECTION | 2022-03-18 | 2022-04-04 | 2022-04-04 | 2022-04-04 | 2022-04-04 | 2022-04-05 | NO | NO | 2022-04-04
NEM-ST | 348896 | 95.737 | Solar PV | PENDING AHJ INSPECTION | 2022-03-21 | 2022-04-04 | 2022-04-04 | 2022-04-04 | 2022-04-04 | 2022-04-05 | NO | NO | 2022-04-04 | 2022-04-04
NEM-ST | 351052 | 158.507 | Solar PV | PENDING AHJ INSPECTION | 2022-03-30 | 2022-04-04 | 2022-04-04 | 2022-04-04 | 2022-04-04 | 2022-04-05 | NO | NO | 2022-04-04
NEM-ST | 343602 | 199.34 | Solar PV | PENDING AHJ INSPECTION | 2022-03-30 | 2022-04-04 | 2022-04-04 | 2022-04-04 | 2022-04-04 | 2022-04-05 | NO | NO | 2022-04-04
NEM-ST | 351096 | 65.128 | Solar PV | PENDING SDGE INSPECTION | 2022-03-30 | 2022-04-04 | 2022-04-04 | 2022-04-04 | 2022-04-04 | 2022-04-05 | NO | NO | 2022-04-04 | 2022-04-10
NEM-ST | 300753 | 45.479 | Solar PV | PENDING AHJ INSPECTION | 2022-03-31 | 2022-04-04 | 2022-04-04 | 2022-04-04 | 2022-04-04 | 2022-04-05 | NO | NO | 2022-04-04 | 2022-04-07
NEM-ST | 343609 | 220.537 | Solar PV | PENDING AHJ INSPECTION | 2022-03-23 | 2022-04-08 | 2022-04-08 | 2022-04-08 | 2022-04-08 | 2022-04-11 | NO | NO | 2022-04-08
NEM-ST | 352069 | 269.649 | Solar PV | PENDING AHJ INSPECTION | 2022-04-08 | 2022-04-08 | 2022-04-08 | 2022-04-08 | 2022-04-08 | 2022-04-11 | NO | NO | 2022-04-08
NEM-ST | 352228 | 8.057 | Solar PV | ISSUES | 2022-04-08 | 2022-04-10 | 2022-04-10 | 2022-04-10 | 2022-04-10 | 2022-04-11 | YES | NO | 2022-04-10
NEM-ST | 338910 | 192.847 | Solar PV | PENDING AHJ INSPECTION | 2022-02-01 | 2022-04-12 | 2022-04-12 | 2022-04-12 | 2022-04-12 | 2022-04-14 | NO | NO | 2022-02-04
NEM-ST | 342433 | 215.535 | Solar PV | PENDING AHJ INSPECTION | 2022-02-08 | 2022-04-12 | 2022-04-12 | 2022-04-12 | 2022-04-12 | 2022-04-14 | NO | NO | 2022-02-09
NEM-ST | 342735 | 234.702 | Solar PV | PENDING AHJ INSPECTION | 2022-02-21 | 2022-04-12 | 2022-04-12 | 2022-04-12 | 2022-04-12 | 2022-04-14 | NO | NO | 2022-02-24
NEM-ST | 348865 | 174.57 | Solar PV | PENDING AHJ INSPECTION | 2022-03-21 | 2022-04-12 | 2022-04-12 | 2022-04-12 | 2022-04-12 | 2022-04-14 | NO | NO | 2022-04-12
NEM-ST | 352034 | 97.665 | Solar PV | PENDING AHJ INSPECTION | 2022-04-11 | 2022-04-12 | 2022-04-12 | 2022-04-12 | 2022-04-12 | 2022-04-14 | NO | NO | 2022-04-12
NEM-ST | 351595 | 45.537 | Solar PV | PENDING AHJ INSPECTION | 2022-04-11 | 2022-04-28 | 2022-04-28 | 2022-04-28 | 2022-04-28 | 2022-05-01 | NO | NO | 2022-04-28 | 2022-04-28
NEM-ST | 336342 | 984.198 | Solar PV | PENDING AHJ INSPECTION | 2021-12-06 | 2022-05-01 | 2022-05-01 | 2022-05-01 | 2022-01-05 | 2022-01-12 | NO | NO | 2022-01-05
NEM-ST | 337261 | 58.946 | Solar PV | PENDING AHJ INSPECTION | 2021-12-12 | 2022-05-01 | 2022-05-01 | 2022-05-01 | 2022-05-01 |  |  |  | 2022-05-01
NEM-ST | 351580 | 51.763 | Solar PV | PENDING SDGE INSPECTION | 2022-04-05 | 2022-05-01 | 2022-05-01 | 2022-05-01 | 2022-05-01 |  |  |  | 2022-05-01 |  | 2022-04-28
NEM-ST | 353036 | 132.755 | Solar PV | PENDING AHJ INSPECTION | 2022-04-15 | 2022-05-01 | 2022-05-01 | 2022-05-01 | 2022-05-01 |  |  |  | 2022-05-01
NEM-ST | 353276 | 40.481 | Solar PV | PENDING AHJ INSPECTION | 2022-04-18 | 2022-05-01 | 2022-05-01 | 2022-05-01 | 2022-05-01 |  |  |  | 2022-05-01
NEM-ST | 353715 | 47.363 | Solar PV | PENDING AHJ INSPECTION | 2022-04-20 | 2022-05-01 | 2022-05-01 | 2022-05-01 | 2022-05-01 |  |  |  | 2022-05-01
NEM-ST | 354108 | 47.823 | Solar PV | PENDING AHJ INSPECTION | 2022-04-22 | 2022-05-01 | 2022-05-01 | 2022-05-01 | 2022-05-01 |  |  |  | 2022-05-01
NEM-ST | 354121 | 89.269 | Solar PV | PENDING AHJ INSPECTION | 2022-04-22 | 2022-05-01 | 2022-05-01 | 2022-05-01 | 2022-05-01 |  |  |  | 2022-05-01

## NEM-ST NGOM
SDG&E's Rule 21 Processing Timelines Q1 2022
NEM-ST NGOM
INTERCONNECTION TYPE | APP ID | PROJECT SIZE (kW) | TECHNOLOGY TYPE | DIIS APPLICATION STATUS | APPLICATION SUBMITTED | APPLICATION DEEMED COMPLETE | CUST GEN. ENG REVIEW SENT | CUST GEN. ENG REVIEW COMPLETED | SENT TO DP | RECEIVED DP APPROVAL | TRANSFORMER CHANGE YES/NO | ELECTRICAL DISTRIBUTION UPGRADE YES/NO | INITIAL FIELD INSPECTION | COSTING INVOICE SENT | PAYMENT RECEIVED | RULE 2 SENT | RULE 2 RECEIVED | ICA SENT | ICA RECEIVED | AHJ INSPECTION RECEIVED | CG METER INSPECTION RECEIVED | FINAL FIELD INSPECTION | VOLTAGE CHECK RECEIVED | EMAILED AMO | METER SET COMPLETED | Calendar Days from NGOM Request to NGOM Completed | PTO PROVIDED | EXECUTED ICA SENT TO CUSTOMER | NGOM DATA SENT TO BILLING | Calendar Days from Application Deemed Complete Date to PTO Date
NEM-ST NGOM | 246756 | 50.196 | Battery Storage + Solar PV | APPROVED | 2021-01-21 | 2021-01-21 | 2021-01-21 | 2021-01-21 | N/A | N/A | NO | NO | 2021-02-17 | 2021-02-19 | 2021-03-04 | 2021-02-19 | 2021-02-26 | N/A | N/A | 2021-05-27 | 2021-07-09 | 2021-06-22 | 2021-01-27 |  | 2021-07-09 |  | 2021-07-09 | N/A | 2021-07-12 | 1900-06-17
NEM-ST NGOM | 298792 | 11.52 | Battery Storage + Solar PV | APPROVED | 2021-01-28 | 2021-01-29 | N/A | N/A | N/A | N/A | NO | NO | 2021-01-29 | 2021-02-03 | 2021-02-16 | 2021-02-03 | 2021-04-05 | N/A | N/A | 2021-01-15 | 2021-02-08 | 2021-01-29 | 2021-01-29 | 2021-02-03 | 2021-02-08 | 1900-01-04 | 2021-02-10 | N/A | 2021-02-10 | 1900-01-11
NEM-ST NGOM | 289730 | 32.701 | Battery Storage + Solar PV | PENDING AHJ INSPECTION | 2020-11-20 | 2021-02-23 | 2021-02-23 | 2021-02-23 | N/A | N/A | NO | NO | 2021-03-04 | 2021-03-09 | 2021-03-29 | 2021-03-09 | 2021-04-09 | N/A | N/A | [6 empty] | 0 |  | N/A
NEM-ST NGOM | 310310 | 53.959 | Battery Storage + Solar PV | APPROVED | 2021-05-07 | 2021-06-02 | 2021-06-02 | 2021-06-02 | N/A | N/A | NO | NO | 2021-06-22 | 2021-07-06 | 2021-07-13 | 2021-07-06 | 2021-07-09 | N/A | N/A | 2021-04-28 | 2021-06-30 | 2021-06-28 | 2021-06-28 | 2021-07-30 | 2021-09-28 | 1900-02-28 | 2022-01-13 | N/A | 2022-01-13 | 1900-08-12
NEM-ST NGOM | 309632 | 956.563 | Battery Storage + Solar PV | PENDING AHJ INSPECTION | 2021-04-22 | 2021-06-08 | 2021-05-04 | 2021-06-08 | 2021-05-04 | 2021-05-06 | NO | NO | 2021-06-22 | 2021-07-06 | 2021-07-13 | 2021-07-06 | 2021-07-09 | 2021-06-08 | N/A
NEM-ST NGOM | 315914 | 164.569 | Solar PV | APPROVED | 2021-06-18 | 2021-07-07 | 2021-07-07 | 2021-07-07 | 2021-07-07 | 2021-07-08 | NO | NO | 2021-09-14 | 2021-09-08 | 2021-09-29 | 2021-09-08 | 2021-09-16 | 2021-07-07 | 2021-07-23 | 2021-09-16 | 2021-09-16 | 2021-11-04 | 2021-09-14 |  | 2021-11-22 |  | 2021-11-22 | 2021-11-23 | 2021-11-24 | 1900-05-17
NEM-ST NGOM | 319427 | 49.857 | Solar PV | APPROVED | 2021-08-02 | 2021-08-09 | 2021-08-09 | 2021-08-09 | 2021-08-09 | 2021-08-12 | NO | NO | 2021-08-12 | 2021-10-01 | 2022-04-21 | 2021-10-01 | 2022-04-21 | 2021-08-09 | 2022-04-21 | 2022-01-12 | 2022-01-13 | 2022-04-21 | 2021-08-12 | 2022-04-11 | 2022-04-21 | 1900-01-09 | 2022-04-21 | 2022-04-22 | 2022-04-21 | 1900-09-11
NEM-ST NGOM | 209040 | 796.384 | Battery Storage + Solar PV | PENDING AHJ INSPECTION | 2021-08-06 | 2021-08-13 | 2021-08-13 | 2021-08-13 | 8//13/21 | 2021-08-17 | NO | NO | 2021-09-09 | 2021-10-06 |  | 2021-10-06 |  | 2021-08-13
NEM-ST NGOM | 319718 | 240.548 | Battery Storage + Solar PV | PENDING AHJ INSPECTION | 2021-07-23 | 2021-08-17 | 2021-08-24 | 2021-08-24 | 2021-08-24 | 2021-08-25 | NO | NO | 2021-09-08 | 2021-09-22 | 2021-10-07 | 2021-09-22 |  | 2021-08-24 | 2021-08-12
NEM-ST NGOM | 322820 | 143.489 | Solar PV | APPROVED | 2021-08-23 | 2021-08-24 | 2021-08-24 | 2021-08-24 | 2021-08-24 | 2021-08-25 | NO | NO | 2021-10-04 | 2021-10-13 | 2021-11-02 | 2021-10-13 | 2021-11-04 | 2021-08-24 | 2021-08-25 | 2021-09-30 | 2021-11-03 | 2021-11-09 | 2021-11-08 | 2021-12-16 | 2021-12-27 | 1900-01-10 | 2021-12-29 | 2021-12-30 | 2021-12-30 | 1900-05-06
NEM-ST NGOM | 324142 | 396.653 | Solar PV | APPROVED | 2021-08-30 | 2021-09-03 | 2021-09-03 | 2021-09-03 | 2021-09-03 | 2021-09-07 | NO | NO | 2021-09-28 | 2021-11-08 | 2021-11-16 | 2021-11-08 | 2021-11-22 | 2021-09-03 | 2021-10-20 | 2021-11-02 | 2021-11-16 | 2021-11-18 | 2021-11-18 | 2021-12-17 | 2021-12-30 | 1900-01-12 | 2021-12-30 | 2022-01-03 | 2022-01-03 | 1900-04-27
NEM-ST NGOM | 318497 | 214.038 | Battery Storage + Solar PV | PENDING AHJ INSPECTION | 2021-07-13 | 2021-09-20 | 2021-07-14 | 2021-09-20 | 2021-07-14 | 2021-07-14 | NO | NO | [5 empty] | 2021-09-20
NEM-ST NGOM | 325597 | 250 | Battery Storage | PENDING AHJ INSPECTION | 2021-09-14 | 2021-09-21 | 2021-09-21 | 2021-09-21 | 2021-09-21 | 2021-09-24 | NO | NO | [5 empty] | N/A | N/A
NEM-ST NGOM | 330017 | 29 | Battery Storage | PENDING FINAL REVIEW | 2021-10-18 | 2021-11-05 | 2021-11-05 | 2021-11-05 | N/A | N/A | NO | NO | 2021-01-04
NEM-ST NGOM | 331691 | 74.613 | Battery Storage + Solar PV | APPROVED | 2021-10-28 | 2021-11-23 | 2021-11-23 | 2021-11-23 | 2021-11-23 | 2021-11-24 | NO | NO | 2021-12-03 | 2021-12-09 | 2021-12-15 | 2021-12-09 | 2021-12-14 | 2021-11-23 | 2021-11-23 | 2021-12-03 | 2021-12-03 | 2021-12-08 | 2021-12-28 | 2022-01-20 | 2022-02-02 | 1900-01-12 | 2022-02-03 | 2022-02-04 | 2022-02-03 | 1900-03-12
NEM-ST NGOM | 305238 | 85.249 | Battery Storage + Solar PV | APPROVED | 2021-10-20 | 2022-01-04 | 2022-01-04 | 2022-01-04 | N/A | N/A | NO | NO | 2021-10-28 | 2021-10-27 | 2021-11-09 | 2021-10-27 | 2021-11-15 | N/A | N/A | 2022-01-04 | 2022-01-04 | 2022-01-21 | 2022-01-24 | 2022-02-22 | 2022-02-25 | 1900-01-02 | 2022-02-25 | N/A | 2022-02-25 | 1900-02-20
NEM-ST NGOM | 318272 | 123.548 | Battery Storage + Solar PV | PENDING AHJ INSPECTION | 2022-01-27 | 2022-02-04 | 2022-02-04 | 2022-02-04 | 2022-02-04 | 2022-02-08 | NO | NO | [5 empty] | 2022-02-04
NEM-ST NGOM | 341593 | 201.331 | Solar PV | ISSUES | 2022-01-25 | 2022-02-19 | 2022-02-19 | 2022-02-19 | 2022-02-19 | 2022-02-28 | NO | NO
NEM-ST NGOM | 304455 | 383.868 | Battery Storage + Solar PV | PENDING AHJ INSPECTION | 2021-10-27 | 2022-02-23 | 2022-02-23 | 2022-02-23 | 2022-02-23 | 2022-02-28 | NO | NO | [5 empty] | 2022-02-23
NEM-ST NGOM | 341708 | 4514.644 | Battery Storage + Solar PV | INITIAL REVIEW | 2022-02-11 | 2022-02-23 | 2022-03-10 |  | 2022-03-10
NEM-ST NGOM | 339052 | 63.67 | Battery Storage + Solar PV | PENDING AHJ INSPECTION | 2021-12-28 | 2022-02-28 | 2022-02-28 | 2022-02-28 | N/A | N/A | NO | NO | 2022-03-08 | 2022-03-17 |  | 2022-03-17
NEM-ST NGOM | 345806 | 593.652 | Battery Storage + Solar PV | ISSUES | 2022-03-03 | 2022-04-08 | 2022-04-08 |  | 2022-04-08 | 2022-04-11 | NO | NO | [5 empty] | 2022-04-08