## Instructions
Instructions for 2025 SB 1174 Reporting
Pursuant to SB 1174 (Hertzberg, Stat. 2022, Ch. 229) and Pub. Util. Code § 399.13(a)(2)(B), electrical corporations that own transmission facilities are required to provide information within their RPS Procurement Plans detailing the impact that delays to transmission facilities and network system upgrades have had on renewable energy and energy storage resources with executed interconnection agreements. Electrical corporations shall use this template to report the related data. Electrical corporations shall complete all fields in: 1. Transmission Delay Reporting tab: - List all "in-development" transmission projects, and all projects that have become operational between January 1, 2020 and March 31, 2025. - For each transmission project list all in-development renewable energy and energy storage resources (with an executed interconnection agreement) that depend on the project. 2. Generation Reporting tab: - List every renewable energy and energy storage resource (with executed interconnection agreements) currently in the CAISO, WDAT, or other interconnection queues. Electrical corporations shall list each “transmission project” that is: 1. A CAISO-approved or utility self-approved transmission project, interconnection project, or network upgrade needed for generator interconnection; 2. Delayed OR not delayed (i.e. do not consider delay when listing projects); and 3. “In development”, meaning the project has commenced, but is not yet in-service OR became operational between January 1, 2020 and March 31, 2025. Please do not alter the contents of any tabs except the two listed above. Thank you!
"1. Transmission Delay Reporting" TAB
Section 1: TRANSMISSION PROJECT DETAILS
Field # | Project Data Field | Input Format | Input Example | Input Description
1 | Transmission Project Name | Text string. | Manzanita Substation | Project's name at the date of filing this report. Identify all prior project names and alternative names currently used in different venues, including the name as approved and included in the CAISO's TPP.
2 | Transmission Project Unique ID #1 | Text string. | 78493 | Unique identification (ID) code(s) or number(s) for transmission project. Most specific (PG&E = Planning Order, SCE = SCE ID, SDG&E = Project ID).
3 | Transmission Project Unique ID #2 | Text string. | 432 | Unique identification (ID) code(s) or number(s) for transmission project. Less specific (PG&E = T.dot, SCE = Capital Work Breakdown Structure, SDG&E = Budget Code).
4 | Transmission Project Unique ID #3 | Text string. | 92 | Unique identification (ID) code(s) or number(s) for transmission project. Least specific (PG&E = Major Work Category, SCE = Project Identification Number , SDG&E = N/A)
5 | Description | Text string. | Repairs the transmission line connecting 4th and Townsend to the East Northfork station which failed due to the 2019 San Clemente Hedge Fire. | Brief project summary, including assets to be installed.
6 | Status | Drop-down menu selection. | Construction (10%-25%) | See drop-down menu. Indicate the status of the project.
7 | Operational Date | Date, formatted YYYY-MM-DD; N/A if not yet operational. | 2025-08-15 | If "Operational" was chosen in the "Status" field, then indicate the date the project became operational. If the project is already in-service, then this date should match the "Planned or Actual In-service Date". If not Operational, indicate "N/A".
8 | Latitude | Number (decimal), separated by "¦" for multiple locations; N/A if no geolocation. | 20.234 ¦ 19.983 | Positive number indicates north of equator.
9 | Longitude | Number (decimal), separated by "¦" for multiple locations; N/A if no geolocation. | -132.018 ¦ -132.231 | Negative number indicates west of Prime Meridian.
10 | Location | Text String, with comma between City and County. Multiple entries separated by "¦". Order of values consistent with latitude and longitude. | Berkeley, Alameda ¦ Concord, Contra Costa | All Cities and Counties included in the scope of the project.
11 | CAISO Study Area | Drop-down menu selection. | PG&E: Central Coast & Los Padres Areas | See drop-down menu. Study Areas based on CAISO 25-26 Transmission Planning Process (TPP)
12 | GIDAP Related | Drop-down menu selection. | Yes | Generator Interconnection and Deliverability Allocation Procedures (GIDAP). Is this transmission project a network upgrade associated with specific projects in the queue? (Yes/No)
13 | Year Expected to be Considered in CAISO TPP | Years, formatted YYYY and separated by "¦", or N/A. | 2025 | If not yet considered in the CAISO TPP, indicate the year when it is expected to be considered in the CAISO TPP.
14 | Project Dependencies | Number (whole) indicating required projects' Transmission Project Unique ID #(s), separated by "¦" as necessary. | 235435 ¦ 432787 | Identify all other projects (Transmission Project Unique ID #1) in the spreadsheet that this project depends on and/or whose construction will be bundled with this project.
15 | Action Taken | Drop-down menu selection. | Upgrade/Retrofit | See drop-down menu. If two or more options are required, select "Multiple Options" and provide remaining responses, pipe-delimited, in "Notes" field. If the purpose or purpose details relates to complying with a NERC, WECC, or CAISO requirement, list specific standard(s), requirement(s), and/or any contingencies that are being addressed.
16 | Purpose | Drop-down menu selection. | Reliability | See drop-down menu. In the "Notes" field, please explain a purpose identified as "Other" or provide details on the purpose identified.
17 | Purpose Details | Drop-down menu selection. | Age/Condition - Anti Climb Guards | See drop-down menu. If the purpose details is to comply with a NERC, WECC, or CAISO requirement, list the standard, requirement, and/or any contingencies that are being addressed in the "Notes" field.
18 | Transmission Project Size | Number (decimal), or N/A. | 42.66 | Miles of transmission power lines included in the project.
19 | Substation Project Footprint | Number (decimal), or N/A. | 12.25 | Acres of substation footprint included in the project.
20 | Transmission Voltage Level | Number (whole), separated by "¦" as necessary, or N/A. | 230 | Use kV for transmission power lines ratings.
21 | Substation or Transformer Capacity | Text String, separated by "¦" as necessary, or N/A if unrelated. | 115kV | Use MVA and/or kV for substations.
Section 2: TRANSMISSION PROJECT VARIANCES
Field # | Project Data Field | Input Format | Input Example | Input Description
22 | Planned or Actual Construction Start Date | Date, formatted YYYY-MM-DD. | 2024-12-15 | At the time the data was extracted from the utility’s database(s) as provided in Section 2.1.5 of the Transmission Project Review Process Description. If the project has not been delayed, the original and current construction dates should match.
23 | Original In-service Date | Date, formatted YYYY-MM-DD. | 2025-06-01 | The expected in-service start date when the project was first approved. Look to the following prioritized sources to identify the Original In-service Date: 1) CAISO transmission plans; 2) Transmission Project Review Process data (Resolution E-5252 Attach B); 3) Transmission Development Forum "In-service Date at Approval in Transmission Plan" date; or 4) Internal utility project approval dates, including the first approved business case.
24 | Planned or Actual In-service Date | Date, formatted YYYY-MM-DD. | 2021-01-01 | At the time the data was extracted from the utility’s database(s) as provided in Section 2.1.5 of the Transmission Project Review Process Description. If the project has not been delayed, the original and current in-service dates should match.
25 | Original In-service Date Source | Text string. | CAISO Transmission Plan | Identify the source used to determine the "Original In-service Date". See the "Original In-service Date" field description and list of prioritized sources.
26 | In-service Date Total Delay | No input needed. Automatically populated. | 365 | If the Original In-service Date and the Planned or Actual In-service Date are different, the difference in days will automatically be calculated. No input is needed.
27 | Project is Delayed | No input needed. Automatically populated. | Yes | If "Original In-service Date" is equal to or later than the "Planned or Actual In-service Date", the project is not delayed (No). If "Original In-service Date" is earlier than the "Planned or Actual In-service Date", the project is delayed (Yes). No input is needed.
28 | Delay Resolver | Drop-down menu selection. | Customer | See drop-down menu. Select the party that can resolve the current delay. Select N/A only if the project is NOT delayed. If selecting "Agency - Federal", "Agency - Local", or "Agency - State", identify the specific agency in the "Notes" field. If selecting "Agency - Federal", "Agency - Local", "Agency - State", "CAISO", or "CPUC", identify the specific delays with the entity and how to resolve.
29 | In-service Date Change Reason | Drop-down menu selection. | Financing | See drop-down menu. Select the primary reason for the change from the original in-service date. Select N/A only if the project is NOT delayed. If selecting "Permitting (non-CPUC/CEQA)", identify the specific entities involved in the permitting delay (e.g. Federal, State, Local agencies) in the "Notes" field.
Section 3: PERMITTING STATUS (CPUC/CEQA)
Field # | Project Data Field | Input Format | Input Example | Input Description
30 | CEQA Status | Drop-down menu selection. | PEA Deemed Complete | Status of the project in the CEQA permitting process.
31 | CEQA Status Date | Date, formatted YYYY-MM-DD. | 2023-05-01 | CEQA Status as of the date entered here. Example: If a CEQA Status of "PEA Deemed Complete" was last verified on 2023-05-01, then enter "2023-05-01" here.
32 | CEQA Document Type | Drop-down menu selection. | EIR | Examples include: IS/ND, IS/MND, EIR, Exempted, Other, or N/A. If "Other" include explanation in the "Notes" field.
33 | NEPA Document Type | Drop-down menu selection. | EIS | Examples include: EIS, EA, Categorical Exclusion, Other, or N/A. If "Other" include explanation in the "Notes" field.
34 | CEQA Lead Agency | Text string, or N/A | CPUC | Some examples include: CPUC, SWRCB, CSLC, not applicable (N/A).
35 | NEPA Lead Agency | Text string, or N/A | USFS | Some examples include: USFS, not applicable (N/A).
36 | CPUC Filing Type | Text string, or N/A | PG&E AL 2355-E | Type of permit. Some examples include: NOC, Advice Letter (AL) Application for 851, PTC, CPCN, or not applicable (N/A).
37 | CPUC Date Filed | Date, formatted YYYY-MM-DD. | 2012-09-30 | Date when permits were filed with CPUC.
38 | CPUC Status | Drop-down menu selection. | Filed and Under Administrative Review | Status of the project in the CPUC permitting process.
39 | CPUC Status Date | Date, formatted YYYY-MM-DD. | 2022-12-13 | CPUC Status as of the date entered here. Example: If a CPUC Status of "Filed and Under Administrative Review" was last verified on 2022-12-13, then enter "2022-12-13" here.
Section 4: TRANSMISSION PROJECT NOTES
Field # | Project Data Field | Input Format | Input Example | Input Description
40 | Notes | Text strings, inclusive of field identifiers in brackets, separated by line break. | [4. Status] PPA negotiation failure. [6. Purpose] Experimental breaker testing. | For all fields in which an option including "[See Notes]" was selected, please enter a description or explanation here.
41 | Secondary/Other Reasons for Delay | Text string. | Although the most significant reason for delay on this project has been due to Land Rights issues, this project has also been subject to delays caused by unforeseen Weather circumstances, such as flooding experienced in the first 6 months of the project. Project staff estimate that Weather-related issues have contributed to about 25% of the total delay experienced. | For all projects that have been identified as being delayed (Project is Delayed = Yes), provide any additional context into reasons other than the primary reason for delay identified in "In-service Date Change Reason" and explained in "Notes". Please provide secondary reasons for delays and estimated contribution to the project's total delay, if available.
Section 5: GENERATION RESOURCE DEPENDENCIES
Field # | Project Data Field | Input Format | Input Example | Input Description
42+ | Dependent Resource In-Queue Generation Number (CAISO and WDAT) | Text string. Only 1 ID per cell. | 0002CONV | Enter in only 1 ID per cell. CAISO and WDAT queue numbers. Identify all generation resources (with executed interconnection agreements) that are operationally dependent on this project. If the generation resource is connecting to a PTO's distribution system then Queue numbers can include "W", "WDT", "WD", "GFID", "RD" or "Rule 21". Submitter may add additional columns for additional generation projects as necessary. List all queue position #s both CAISO and WDAT generation projects. Types of queue position labels include, but are not limited to: - ##, or, if two queues have combined then the queue number will reflect ##,##. - ####CONV is a two-to-three party contract conversion or is a conversion project repowering with new generation. - ####PREC, that is an existing two-party generating facility that has yet to complete a contract conversion. - #### for generation resources that are dynamic or pseudo-ties (projects in a balancing authority area other than the CAISO but are treated as Participating Generators under the CAISO Tariff).
"2. Generation Reporting" TAB
Section 1: GENERATION RESOURCES DETAILS
Field # | Project Data Field | Input Format | Input Example | Input Description
1 | Generation Facility Name | Text string. | Sierra Solar Farm Project | Name of generating facility (with executed interconnection agreement) that is currently in development. Any resources identified on tab 1. Transmission Delay Reporting under the Dependent Resource In-Queue Generation Number (CAISO and WDAT) fields must also be listed on this tab or data request will be considered incomplete.
2 | In-Queue Number (CAISO or WDAT) | Text string. | 0002CONV | If generation resources were entered on tab 1. Transmission Delay Reporting in any of the "Dependent Resource In-Queue Generation Number (CAISO and WDAT)" fields, inputs here must match. CAISO queue or WDAT (Wholesale Distribution Access Tariff) queue number of the generating facility. If the generation resource is connecting to a Participating TO's distribution system then Queue numbers can include "W", "WDT", "WD", "GFID", "RD" or "Rule 21". Types of queue position labels include: - ##, or, if two queues have combined then the queue number will reflect ##,##. - ####CONV is a two-to-three party contract conversion or is a conversion project repowering with new generation. - ####PREC, that is an existing two-party generating facility that has yet to complete a contract conversion. - #### for generation resources that are dynamic or pseudo-ties (projects in a balancing authority area other than the CAISO but are treated as Participating Generators under the CAISO Tariff).
3 | Generator Resource ID | TEXT STRING IN CAPS, underscore(_), #(s), underscore (_), TEXT STRING IN CAPS, #(s). | HENRUA_6_ACDSR3 | The resource ID for this generating facility. Resource ID is assigned during "model build" stage of the New Resource Implementation (NRI) Process.
4 | Primary Developer | Text string. | SuperSun Renewables, LCC | Developer with the highest percentage interest in the project.
5 | Developer Parent Company Name | Text string. | Orion Energy Corp. | Parent company name of primary developer. For wholesale aggregated contracts, use name of aggregator (e.g., Shell, Barclays etc.).
6 | Nameplate Capacity | Number (decimal). | 100.5 | Total nameplate capacity of the whole project in MW. This should be the maximum MW it can deliver under the interconnection agreement.
7 | Expected Annual RPS Eligible Generation | Number (decimal) or N/A. | 29396.8 | The anticipated total energy generated by this RPS eligible resource each year in MWh. If not applicable, enter N/A.
8 | Planned Construction Start Date | Date, formatted YYYY-MM-DD. | 2024-06-17 | Identify planned construction start dates for in-queue resource or generation project.
9 | Planned In-service Date | Date, formatted YYYY-MM-DD. | 2025-09-01 | Identify planned in-service date for in-queue resource and generation project.
10 | Interconnection Request Type | Drop-down menu selection. | Fully deliverable | See drop-down menu. Select deliverability status sought in interconnection agreement.
11 | Technology Type | Drop-down menu selection. | Biogas | See drop-down menu. Select resource technology type.
12 | RPS Eligible | Drop-down menu selection. | Yes | Is this resource RPS-eligible? (Yes or No)
13 | PTO Service Territory | Drop-down menu selection. | PG&E | See drop-down menu. Select the PTO service territory that this generation resource is located in. If "Other" is selected, please explain in the "Notes" field.
Section 2: GENERATION RESOURCES NOTES
Field # | Project Data Field | Input Format | Input Example | Input Description
14 | Notes | Text strings, inclusive of field identifiers in brackets, separated by line break. | [11. Technology Type] Mixed technology, solar and battery storage. | For all fields in which an option including "[See Notes]" was selected, please enter a description or explanation here.
Section 3: CONNECTING TRANSMISSION PROJECTS
Field # | Project Data Field | Input Format | Input Example | Input Description
15 | Dependent on Delayed Transmission Project | Drop-down menu selection. | Yes | See drop-down menu. If the generation or storage resource coming online is dependent on the completion of a transmission project that has already experienced a delay, select "Yes". If the generation or storage resource coming online is dependent on a transmission project that has not been delayed or not dependent on a transmission project's completion, select "No".
16 | Impact of Transmission Delay on Resource | Text string. | This generation resource will not be able to come online until the completion of the GreenZone transmission project (ID 482859) is completed. As the GreenZone project has been delayed by one year, and this project was expected to come online 6 months after GreenZone's completion, we anticipate this generation resource being delayed by 6 months. | If "Yes" was chosen for "Dependent on Delayed Transmission Project", please explain the expected impact on this generation or storage resource. Please include as much details as possible, including expected in-service date delays for the generation or storage resource.

## Definitions
Acronym List |  |  | Date Change Reasons Defined
| Acronym | Definition | Reason | Definition
| AFUDC | Allowance for Funds Used During Construction | Bundling Dependencies | Another delayed project must be completed before this project can continue. Can be in any phase of the project (i.e. planning, engineering, construction, etc.).
| AL | Advice Letter | Clearances | Non-permit related clearance delays from any governmental entity with authority or jurisdiction over any phase of this project.
| CAISO | California Independent System Operator | Completed Early | Project completed before originally scheduled in-service date.
| CEQA | California Environmental Quality Act | Financing | Project delayed due to capital and financial availability constraints.
| CPUC | California Public Utilities Commission | ISO Action | The CAISO de-prioritized or re-prioritized the project. De-prioritization would typically manifest with an on-hold project status.
| CSLC | California State Lands Commission | Land Rights | The project required easements, exercise of eminent domain, etc. that the utility has not been able to effect.
| EIR | Environmental Impact Report | Material | Issues with equipment or components themselves but are not related to vendor error (see "Vendor Quality/Delays")
| EIS | Environmental Impact Statements | Outage | Outages (planned or unplanned) that impacted the in-service date.
| FERC | Federal Energy Regulatory Commission | Permitting (CPUC/CEQA) | Project delays related to CPUC permitting or CEQA environmental reviews. Examples: CPCN, PTC, or PEA review times are unusually long.
| GO | General Order | Permitting (non-CPUC/CEQA) | Project delays related to federal, state, or local agency permitting downstream of CPUC/CEQA permitting. Example: BLM permitting process is unusually long.
| ID | Identification | Project Design | Any additional design work outside of the initially approved project design, not related to "Workforce Availability", "Bundling Dependencies" or "Clearances".
| IS/MND | Initial Study and Mitigated Negative Declaration | Supply Chain Delays | Requested project resources have not been delivered as scheduled.
| IS/ND | Initial Study and Negative Declaration | Vendor Quality/Delays | Issues with vendor/suppliers that are not related to the failure of equipment, material, or components (see "Material").
| ISD | In-service Date | Weather | An unforeseen weather event that causes a delay or set-back in construction work. Example: mudslides resulting from El Nino.
| IT | Information Technology | Workforce Availability | Impacts due to staffing shortages at any phase of the project (i.e. planning, engineering, construction, etc.).
| IX | Interconnection
| KV | Kilovolt
| MPAC | Modular Protection Automation & Control
| MVA | Megavolt-ampere
| MW | Megawatt
| MWh | Megawatt-hour
| N/A | Not applicable
| NEPA | National Environmental Policy Act
| NERC | North American Electric Reliability Corporation
| NOC | Notice of Construction
| NRI | New Resource Implementation
| OAI | Operative as Installed
| PEA | Proponent’s Environmental Assessments
| PG&E | Pacific Gas and Electric
| PTC | Permit to Construct
| PTO | Participating Transmission Owner
| RPS | Renewables Portfolio Standard
| RTU | Remote Terminal Unit
| SB | Senate Bill
| SCADA | Supervisory Control and Data Acquisition
| SCE | Southern California Edison
| SDG&E | San Diego Gas & Electric
| SWRCB | California State Water Resources Control Board
| TDF | Transmission Development Form
| TPP | Transmission Planning Process
| TX | Transmission
| USFS | United States Forest Service
| WDAT | Wholesale Distribution Access Tariff
| WECC | Western Electricity Coordinating Council

## Choices
1. TRANSMISSION DELAY REPORTING | [11 empty] | 2. GENERATION REPORTING
6 | 11 | 12 | 15 | 16 | 17 | 28 | 29 | 30 | 32 | 33 | 38 | 10 | 11 | 12 | 13 | 15
Status | Caiso Study Area | GIDAP Related | Action Taken | Purpose | Purpose Details | Delay Resolver | In-service Date Change Reason | CEQA Status | CEQA Document Type | NEPA Document Type | CPUC Status | Interconnection Request Type | Technology Type | RPS Eligible | PTO Service Territory | Dependent on Delayed Transmission Project
Abandoned | PG&E: Humboldt Area | Yes | New | Address Results of Power Flow Analysis | 3rd Party Damage | Utility | Bundling Dependencies | CEQA Draft Published | EIR | EA | Approved | Energy Only | Battery Storage | Yes | PG&E | Yes
Canceled | PG&E: North Coast & North Bay Area | No | Relocate | Address Results of Protection Studies | Age/Condition | Customer | Clearances | CEQA Final Published | IS/MND | EIS | Filed and Under Administrative Review | Fully Deliverable | Biodiesel | No | SCE | No
Construction (10%-25%) | PG&E: North Valley Area |  | Removal | Age/End of Life | Age/Condition - 230/115/70/60 kV Relay Replacement | Developer | Completed Early | Expected PEA Completion | N/A | N/A | To be Filed | Partially Deliverable | Biogas |  | SDG&E
Construction (25%-50%) | PG&E: Central Valley Area |  | Replace | Asset Condition | Age/Condition - 500 kV Relay Replacement | CAISO | Financing | PEA Deemed Complete |  |  | Other [See Notes] | Other [See Notes] | Biomass |  | Other [See Notes]
Construction (50%-75%) | PG&E: Greater Bay Area |  | Upgrade/Retrofit | CAISO Transmission Planning Standards [See Notes for NERC Compliance and contingency code, WECC Requirement (and the specific requirement)] | Age/Condition - Anti Climb Guards | CPUC | ISO Action | Final Certified |  |  | N/A [See Notes] |  | Conduit Hydro
Construction (over 75%) | PG&E: Greater Fresno Area |  | N/A | Economic | Age/Condition - Insulator Replacement - Steel | Agency - Federal | Land Rights | N/A |  |  |  |  | Digester Gas
Construction (under 10%) | PG&E Kern Area |  | Multiple Options [See Notes] | Emergency Event | Age/Condition - Insulator Replacement - Wood | Agency - Local | Material | [5 empty] | Geothermal
Engineering less than 50% complete | PG&E: Central Coast & Los Padres Areas |  |  | Field Test Results | Age/Condition - Raptor Protection - Steel | Agency - State | Outage | [5 empty] | Hybrid
Engineering more than 50% complete | SCE: Tehachapi & Big Creek Corridor |  |  | Generator Interconnection | Age/Condition - Replace 230/115/70/60 kV Breakers | N/A | Permitting (CPUC/CEQA) | [5 empty] | Hybrid/Paired Solar and Battery
On Hold | SCE: North of Lugo Area |  |  | Load Growth | Age/Condition - Replace 230/115/70/60 kV Transformers |  | Permitting (non-CPUC/CEQA) | [5 empty] | Landfill Gas
Operational | SCE: East of Lugo Area |  |  | Local Capacity Requirement | Age/Condition - Replace 500 kV Breakers |  | Project Design | [5 empty] | Muni Solid Waste
Permitting | SCE: Eastern Area |  |  | Location, Environmental Conditions | Age/Condition - Replace 500 kV Transformers |  | Supply Chain Delays | [5 empty] | Ocean/Tidal
Planning | SCE: Metro Area |  |  | Physical Security | Age/Condition - Replace Boardwalks |  | Vendor Quality/Delays | [5 empty] | Pumped Storage
Other [See Notes] | SDG&E Area |  |  | Policy | Age/Condition - Replace Breakers |  | Weather | [5 empty] | Solar
| Valley Electric Association Area |  |  | Reliability | Age/Condition - Replace Civil Structures |  | Workforce Availability | [5 empty] | Various
| N/A |  |  | Safety | Age/Condition - Replace Conductor |  | N/A | [5 empty] | Wind
|  |  |  | Wildfire Mitigation | Age/Condition - Replace Insulators | [7 empty] | Other [See Notes]
|  |  |  | Work Requested by Others | Age/Condition - Replace Other Substation Equipment
|  |  |  | Another Project Or Resource [See Notes] | Age/Condition - Replace Other T-Line Equipment
|  |  |  | Other [See Notes] | Age/Condition - Replace Reactors, Age/Condition - Replace Relays
Age/Condition - Replace Relays
Age/Condition - Replace SCADA/RTU
Age/Condition - Replace Steel Poles
Age/Condition - Replace Switches, Age/Condition - Replace Transformers
Age/Condition - Replace Underground System
Age/Condition - Replace Wood Poles
Age/Condition - Switch Replacement - Steel
Age/Condition - Switch Replacement - Wood
Age/Condition - Targeted Relay Replacement
Age/Condition - Wood Pole Reframe
Animal Abatement
Automation
Bus Upgrade
Compliance - Remove Idle Facilities
Construct Roads/Gates/Culverts
Emergency Response - Fire Related
Emergency Response - Storm Related
Environmental
Facility Relocation
Fire Protection
Generation Interconnection
GO95 Mitigation - Steel
Install SCADA/RTU
Line Reconductoring
Line Termination
Load Interconnection
Modular Protection and Automation Control
NERC CIP Compliance
NERC Compliance - GO 95
New Substation
New T-Line
Priority 1 Steel Structure Replacement
Priority 1 Wood Structure Replacement
Protection NERC Compliance
Relay Upgrades
Replace Breakers
Replace Other Substation Equipment
Replace Transformer
Safety - Line Right of Way Access
SCADA Emergency Replacement
SCADA Switch Installation
Security Upgrades
Seismic Upgrade - Replace Conductor
Special Protection Scheme
Substation Capacity
Substation Reliability
System Design Upgrade
System Operations
Targeted Line Reliability
T-Line Capacity
T-Line Emergency
T-Line Reliability
Tools, Transformer Addition/Replacement
Underground Emergency
Voltage Conversion
Voltage Support
Other [See Notes]
Note on C5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: NORTH
Note on C6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: NORTH
Note on C7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: NORTH
Note on C9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: GBAY
Note on C10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: FRESNO
Note on C11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: KERN

## Changes
Changes from the 2024 to 2025 SB 1174 Data Reporting Template
Tab | Change
All | General formatting changes.
All | General editing for clarity.
Instructions | Further defined what transmission projects must be reported within the 1174 SB data request.
Instructions | The date range for completed transmission projects that must be reported has been updated.
Instructions | Clarified that "Operational" projects' operational date should match the actual in-service date.
Instructions | Updated the Input Description for several fields.
Definitions | Added new acronyms to Acronym List.
Definitions | Updated definitions in the Date Change Reasons Defined table.
Transmission Delay Reporting | Added field for GIDAP Related.
Transmission Delay Reporting | Added field for Year Expected to be Considered in CAISO TPP.
Transmission Delay Reporting | Added field for Location.
Transmission Delay Reporting | Added fields for Latitude and Longitude.
Transmission Delay Reporting | Added fields for Transmission Project Unique ID #2 and #3.
Transmission Delay Reporting | Added field for CAISO Study Area.
Transmission Delay Reporting | Added field for Project Dependencies.
Transmission Delay Reporting | Added field for Transmission Project Size.
Transmission Delay Reporting | Added field for Substation Project Footprint.
Transmission Delay Reporting | Added field for Transmission Voltage Level.
Transmission Delay Reporting | Added field for Substation or Transformer Capacity.
Transmission Delay Reporting | Added field for Project is Delayed.
Transmission Delay Reporting | Added field for Original In-service Date Source.
Transmission Delay Reporting | Added field for In-service Date Total Delay (Days).
Transmission Delay Reporting | Added field for Secondary/Other Reasons for Delay.
Transmission Delay Reporting | Added new section for Permitting Status (CPUC/CEQA) and 10 associated new fields.
Transmission Delay Reporting | Changed In-service Date Change Initiator field to Delay Resolver.
Transmission Delay Reporting | Changed options for In-service Date Change Reason.
Transmission Delay Reporting | Changed Notes field to be required for all delayed projects.
Transmission Delay Reporting | Removed certain fields related to construction dates.
Generation Reporting | Added field for PTO Service Territory.
Generation Reporting | Added field for Dependent on Delayed Transmission Project.
Generation Reporting | Added field for Impact of Transmission Delay on Resource.
Generation Reporting | Removed Transmission Project Unique ID fields.

## 1. Transmission Delay Reporting
Transmission Delay Reporting
List transmission projects and complete all fields, and list all in-development renewable energy and energy storage resources (with an executed interconnection agreement) that depends on the project. Electrical corporations shall list each “transmission project” that is: 1. A CAISO-approved or utility self-approved transmission project, interconnection project, or network upgrade needed for generator interconnection; 2. Delayed OR not delayed (i.e. do not consider delay when listing projects); and 3. “In development”, meaning the project has commenced, but is not yet in-service OR became operational between January 1, 2020 and March 31, 2025. | [9 empty] | All fields are mandatory. Blank fields or data that doesn't match the Input Format on the Instructions tab will be considered incomplete. Tab sections in black text refer to transmission projects, tab sections in red text refer to generation projects. | [14 empty] | Fields 25 and 26 below are automatically populated. No input needed. |  | Fields 27 and 28 below will highlight in light red if the project has been delayed. Please indicate choices other than N/A. | [11 empty] | Fields 39 and 40 below will highlight in light red if the project has been delayed. Please provide additional details. |  | Add new columns to Section 5 as needed.
Section 1: TRANSMISSION PROJECT DETAILS | [20 empty] | Section 2: TRANSMISSION PROJECT VARIANCES | [7 empty] | Section 3: PERMITTING STATUS (CPUC/CEQA) | [9 empty] | Section 4: TRANSMISSION PROJECT NOTES |  | Section 5: GENERATION RESOURCE DEPENDENCIES
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61
Transmission Project Name | Transmission Project Unique ID #1 | Transmission Project Unique ID #2 | Transmission Project Unique ID #3 | Description | Status | Operational Date | Latitude | Longitude | Location | CAISO Study Area | GIDAP Related | Year Expected to be Considered in CAISO TPP | Project Dependencies | Action Taken | Purpose | Purpose Details | Transmission Project Size | Substation Project Footprint | Transmission Voltage Level | Substation or Transformer Capacity | Planned or Actual Construction Start Date | Original In-service Date | Planned or Actual In-service Date | Original In-service Date Source | In-service Date Total Delay (Days) | Project is Delayed | Delay Resolver | In-service Date Change Reason | CEQA Status | CEQA Status Date | CEQA Document Type | NEPA Document Type | CEQA Lead Agency | NEPA Lead Agency | CPUC Filing Type | CPUC Date Filed | CPUC Status | CPUC Status Date | Notes (Required for Any Delayed Projects) | Secondary/Other Reasons for Delay (Required for Any Delayed Projects) | Dependent Resource In-Queue Generation Number (CAISO and WDAT) | Dependent Resource In-Queue Generation Number (CAISO and WDAT)2 | Dependent Resource In-Queue Generation Number (CAISO and WDAT)3 | Dependent Resource In-Queue Generation Number (CAISO and WDAT)4 | Dependent Resource In-Queue Generation Number (CAISO and WDAT)5 | Dependent Resource In-Queue Generation Number (CAISO and WDAT)6 | Dependent Resource In-Queue Generation Number (CAISO and WDAT)7 | Dependent Resource In-Queue Generation Number (CAISO and WDAT)8 | Dependent Resource In-Queue Generation Number (CAISO and WDAT)9 | Dependent Resource In-Queue Generation Number (CAISO and WDAT)10 | Dependent Resource In-Queue Generation Number (CAISO and WDAT)11 | Dependent Resource In-Queue Generation Number (CAISO and WDAT)12 | Dependent Resource In-Queue Generation Number (CAISO and WDAT)13 | Dependent Resource In-Queue Generation Number (CAISO and WDAT)14 | Dependent Resource In-Queue Generation Number (CAISO and WDAT)15 | Dependent Resource In-Queue Generation Number (CAISO and WDAT)16 | Dependent Resource In-Queue Generation Number (CAISO and WDAT)17 | Dependent Resource In-Queue Generation Number (CAISO and WDAT)18 | Dependent Resource In-Queue Generation Number (CAISO and WDAT)19 | Dependent Resource In-Queue Generation Number (CAISO and WDAT)20
Wheeler Ridge Junction Substation (Casa Loma) | 5523422 | T.0000156 | 60C | The C11P2-KT01 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Wheeler Ridge Junction in Kern County, California. | Engineering more than 50% complete | 2020-05-01 |  |  | Kern | PG&E: North Valley Area | No | 2014 | 0 | New | Reliability | T-Line Capacity | N/A | 10.403 | N/A | N/A | N/A | 2020-05-01 | 2029-03-06 | Transmission Project Review Process data (Resolution E-5252 Attach B | 3231 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 04/23/25 - In scope development. Amber. Not Triggered yet by EGI. Project(s) parked | Utility - !Telecom! | Q2015 | Q2015
Vierra 115 kV Looping Project | 5527666 | T.0000597 | 60W | The C14P2-NPT04 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Vierra 115kV in San Joaquin County, California. | Operational | 2014-05-01 |  |  | Lathrop, San Joaquin ¦ San Joaquin ¦ Tracy, San Joaquin | PG&E: North Valley Area | No | 2011 | T.0011086 ¦ T.0010853 ¦ 0 ¦ T.0011168 ¦ 0 | New | Reliability | T-Line Capacity | N/A | NA | N/A | N/A | N/A | 2014-05-01 | 2025-02-23 | Transmission Project Review Process data (Resolution E-5252 Attach B | 3951 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom! | Q1867, Q1887, Q1904, Q1920, Q1929 | Q1867 | Q1887 | Q1904 | Q1920 | Q1929
74024590_BORDEN_SUB_#1_20264_TERMS | 5534923 | T.0007056 | 82W | The C8P2-1 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Borden-Gregg 230kV Line #1 in Madera County, California. | Engineering more than 50% complete | 2020-09-30 |  |  | Madera | PG&E: Greater Fresno Area | Yes | N/A | T.0003742 ¦ T.0003743 ¦ T.0004490 ¦ T.0008538 ¦ 0 ¦ T.0010467 ¦ T.0010817 ¦ T.0010942 ¦ 0 ¦ T.0010738 ¦ 0 ¦ 0 ¦ 0 | Upgrade/Retrofit | Generator Interconnection | Generation Interconnection | N/A | 7.1874 | N/A | 230 kV | 2026-10-16 | 2020-09-30 | 2027-02-12 | Transmission Project Review Process data (Resolution E-5252 Attach B | 2326 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | NOC: AL 7393-E | 2024-10-02 | Approved | 2024 |  | Utility - !Telecom!
74024591_GREGG_SUB_#1_20264_TERMS | 5534924 | T.0007056 | 82W | The C8P2-1 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Borden-Gregg 230kV Line #1 in Madera County, California. | Engineering more than 50% complete | 2020-09-30 |  |  | Madera | PG&E: Greater Fresno Area | Yes | N/A | T.0003742 ¦ T.0003743 ¦ T.0004490 ¦ T.0008538 ¦ 0 ¦ T.0010467 ¦ T.0010817 ¦ T.0010942 ¦ 0 ¦ T.0010738 ¦ 0 ¦ 0 ¦ 0 | Upgrade/Retrofit | Generator Interconnection | Generation Interconnection | N/A | 13.266 | N/A | 230 kV | 2026-10-16 | 2020-09-30 | 2027-02-12 | Transmission Project Review Process data (Resolution E-5252 Attach B | 2326 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | NOC: AL 7393-E | 2024-10-02 | Approved | 2024 |  | Utility - !Telecom! | Q1135, Q1158, Q1129, Q1713, Q1568, Q1709, Q1930, Q1935, Q1953, Q1956, Q1966, Q1968, Q1975 | Q1135 | Q1158 | Q1129 | Q1713 | Q1568 | Q1709 | Q1930 | Q1935 | Q1953 | Q1956 | Q1966 | Q1968 | Q1975
LOS BANOS - PADRE FLAT 20074: RECON-LAND | 5536583 | T.0003016 | 82B | The C8P2-6 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Los-Banos-Padre Flat SS 230kV in Merced County, California. | Operational | 2021-09-30 |  |  | Fresno ¦ Merced | 0 | Yes | N/A | T.0003005 ¦ T.0002987 ¦ T.0003743 ¦ T.0004490 ¦ 0 ¦ T.0010467 ¦ T.0008538 ¦ T.0003742 | Upgrade/Retrofit | Generator Interconnection | Generation Interconnection | N/A | N/A | 230 | N/A | N/A | 2021-09-30 | 2022-10-31 | Transmission Project Review Process data (Resolution E-5252 Attach B | 396 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | NOC: AL 6527-E | 2022-03-11 | Approved | 2022 |  | Utility - !Telecom! | Q1127, Q1128, Q1158, Q1129, Q1568, 2181-WD, Q1709, Q1713, 2226-WD, 2484-WD, Q1135 | Q1127 | Q1128 | Q1158 | Q1129 | Q1568 | 2181-WD | Q1709 | Q1713 | 2226-WD | 2484-WD | Q1135
PADRE FLAT - PANOCHE#1 20074: RECON-LAND | 5536585 | T.0003792 | 82B | The C8P1-34 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Padre Flat-Panoche 230kV Line #1 in Kings County, California. | Operational | 2021-09-30 |  |  | Fresno ¦ Merced | PG&E: Greater Bay Area | Yes | N/A | T.0003005 ¦ T.0002987 ¦ T.0003743 ¦ T.0003742 ¦ T.0004490 ¦ 0 | New | Generator Interconnection | Safety - Line Right of Way Access | 32.6 | N/A | 230 | N/A | N/A | 2021-09-30 | 2024-02-23 | Transmission Project Review Process data (Resolution E-5252 Attach B | 876 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | NOC: AL 6857-E | 2022-11-21 | Approved | 2023 | 04/23/25 - Operative | Utility - !Telecom! | Q1127, Q1128, Q1158, Q1135, Q1129, Q1568, 2181-WD | Q1127 | Q1128 | Q1158 | Q1135 | Q1129 | Q1568 | 2181-WD
74027828_BORDEN-GREGG_LAND_RIGHTS | 5536587 | T.0007056 | 82B | The C8P2-1 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Borden-Gregg 230kV Line #1 in Madera County, California. | Engineering more than 50% complete | 2020-09-30 |  |  | Madera | 0 | Yes | N/A | T.0003742 ¦ T.0003743 ¦ T.0004490 ¦ T.0008538 ¦ 0 ¦ T.0010467 ¦ T.0010817 ¦ T.0010942 ¦ 0 ¦ T.0010738 ¦ 0 ¦ 0 ¦ 0 | Upgrade/Retrofit | Generator Interconnection | Safety - Line Right of Way Access | 6.2 | N/A | 230 | N/A | 2025-07-07 | 2020-09-30 | 2026-02-23 | Transmission Project Review Process data (Resolution E-5252 Attach B | 1972 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | NOC: AL 7393-E | 2024-10-02 | Approved | 2024 |  | Utility - !Telecom! | Q1135, Q1158, Q1129, Q1713, Q1568, Q1709, Q1930, Q1935, Q1953, Q1956, Q1966, Q1968, Q1975 | Q1135 | Q1158 | Q1129 | Q1713 | Q1568 | Q1709 | Q1930 | Q1935 | Q1953 | Q1956 | Q1966 | Q1968 | Q1975
Convert Midway Substation 230 kV Bus D to BAAH in order to install bus reactors & RAS | 5537608 | T.0001650 | 94D | The C13P1-KPN02 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Midway 230kV in Kern County, California. | Construction (25%-50%) | 2022-04-01 |  |  | San Luis Obispo | 0 | No | N/A | 0 ¦ 0 ¦ T.0010479 ¦ T.0010519 ¦ T.0010025 ¦ 0 ¦ 0 ¦ 0 ¦ T.0009383 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 | Upgrade/Retrofit | Reliability | T-Line Capacity | N/A | NA | N/A | 230 kV | 2021-04-08 | 2022-04-01 | 2028-05-24 | Transmission Project Review Process data (Resolution E-5252 Attach B | 2245 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 04/23/25 - Project is still working through the Prioritization Impacts from 2023 | Utility - !Telecom! | Q1740, Q1749, Q1739, Q1751, Q1744, Q1980, Q1987, Q2001, Q1949, Q1983, Q1995, Q2004, Q2006, Q2010, Q2013, Q2015 | Q1740 | Q1749 | Q1739 | Q1751 | Q1744 | Q1980 | Q1987 | Q2001 | Q1949 | Q1983 | Q1995 | Q2004 | Q2006 | Q2010 | Q2013 | Q2015
GATES BUS SECTION E PACIRAS – SFGO (Q12 | 5538721 | T.0006452 | 82W | The C9P2-F13-F15 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Gates 230kV in Fresno County, California. | Operational | 2023-08-15 |  |  | San Francisco, San Francisco | N/A | Yes | N/A | T.0009863 ¦ T.0005678 ¦ T.0005679 ¦ T.0009923 ¦ T.0009924 ¦ T.0007971 ¦ T.0006953 ¦ T.0007329 ¦ T.0006952 ¦ T.0004974 ¦ T.0006847 ¦ T.0006119 ¦ T.0007165 ¦ T.0006097 ¦ 0 ¦ T.0009393 ¦ T.0009193 ¦ T.0008735 ¦ T.0010467 ¦ T.0008538 ¦ 0 ¦ 0 ¦ T.0010025 ¦ T.0010519 | Upgrade/Retrofit | Generator Interconnection | Special Protection Scheme | N/A | 1.2173 | N/A | 230 kV | 2022-09-19 | 2023-08-15 | 2023-04-17 | Transmission Project Review Process data (Resolution E-5252 Attach B | -120 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/04/23 - Energized April 2023. Castanea Line relacation reamins. Due 5/29/23 | Utility - !Telecom! | Q1223, Q1242, Q1243, Q1379, Q1380, Q1389, Q1391, Q1394, Q1397, Q1398, Q1443, Q1493, Q1495, Q1499, Q1568, Q1586, Q1587, Q1593, Q1709, Q1713, Q1736, Q1740, Q1744, Q1751 | Q1223 | Q1242 | Q1243 | Q1379 | Q1380 | Q1389 | Q1391 | Q1394 | Q1397 | Q1398 | Q1443 | Q1493 | Q1495 | Q1499 | Q1568 | Q1586 | Q1587 | Q1593 | Q1709
GATES BUS SECTION E PACIRAS – VGCC (Q12 | 5538722 | T.0006452 | 82W | The C9P2-F13-F15 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Gates 230kV in Fresno County, California. | Operational | 2023-08-15 |  |  | Solano | N/A | Yes | N/A | T.0009863 ¦ T.0005678 ¦ T.0005679 ¦ T.0009923 ¦ T.0009924 ¦ T.0007971 ¦ T.0006953 ¦ T.0007329 ¦ T.0006952 ¦ T.0004974 ¦ T.0006847 ¦ T.0006119 ¦ T.0007165 ¦ T.0006097 ¦ 0 ¦ T.0009393 ¦ T.0009193 ¦ T.0008735 ¦ T.0010467 ¦ T.0008538 ¦ 0 ¦ 0 ¦ T.0010025 ¦ T.0010519 | Upgrade/Retrofit | Generator Interconnection | Special Protection Scheme | N/A | N/A | N/A | 230 kV | 2022-09-09 | 2023-08-15 | 2023-04-17 | Transmission Project Review Process data (Resolution E-5252 Attach B | -120 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/04/23 - Energized April 2023. Castanea Line relacation reamins. Due 5/29/23 | Utility - !Telecom! | Q1223, Q1242, Q1243, Q1379, Q1380, Q1389, Q1391, Q1394, Q1397, Q1398, Q1443, Q1493, Q1495, Q1499, Q1568, Q1586, Q1587, Q1593, Q1709, Q1713, Q1736, Q1740, Q1744, Q1751 | Q1223 | Q1242 | Q1243 | Q1379 | Q1380 | Q1389 | Q1391 | Q1394 | Q1397 | Q1398 | Q1443 | Q1493 | Q1495 | Q1499 | Q1568 | Q1586 | Q1587 | Q1593 | Q1709
Q1349 - ARAMIS GEN SITE MTR DA | 5538979 | T.0005689 | 82Y | The Q1349 Aramis Power Plant Project from Cluster 10, proposes to interconnect a 100 megawatt (MW) (net output) Solar + Battery generation facility to Cayetano 230kV in Alameda County, California. The project has a contractual In-service date of: 12/3/27 with a current planned In-service date of: 3/6/26 | Planning | 2023-04-14 |  |  | Alameda | #REF! | Yes | N/A | T.0004673 ¦ T.0004673 ¦ T.0008048 | Upgrade/Retrofit | Generator Interconnection | Generation Interconnection | N/A | 0.26068 | N/A | 230 kV | 2025-12-10 | 2027-12-03 | 2026-03-06 | Transmission Project Review Process data (Resolution E-5252 Attach B | -637 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 06/02/25 - Customer mobilization and ground-breaking are scheduled for July, with the final design review expected to conclude in two weeks. The ISD remains set for March 6, 2026. | Customer - !Telecom! | 1349 | 1349
Q1398 SANDRINI SOL 2 PV SUBSTATION METER | 5541486 | T.0004974 | 82Y | The Q1398 Sandrini Sol #2 Project from Cluster 10, proposes to interconnect a 200 megawatt (MW) (net output) Solar generation facility to Wheeler Ridge 230kV in Kern County, California. The project has a contractual In-service date of: 7/6/23 with a current planned In-service date of: 2/7/24 | Operational | 2022-08-15 |  |  | Kern | PG&E Kern Area | Yes | N/A | T.0006452 | Upgrade/Retrofit | Generator Interconnection | Generation Interconnection | N/A | 10.403 | N/A | 230 kV | 2023-06-22 | 2023-07-06 | 2024-02-07 | Transmission Project Review Process data (Resolution E-5252 Attach B | 216 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | In-Service - 2/7/24 2/5/24 - Customer installed incorrect components which delayed testing - weather impacts to testing in Jan as well. PPI rescheduled to 2/7 1/3/24 - Sandrini failed their PPI prior to the Holiday's, that is what is pushing them out. The IC didn't get their updated relay settings approved by protection timely. They have since been reviewed and approved, and their 2nd PPI attempt is this week. EMS/SCADA still needs to complete their work, end of January is a more realistic backfeed date. 12/11/23 - PPI scheduled week of 12/11. backfeed in 2024 10/24/23 - Risk to IC to procure some underground comms material (~300 ft). 10/2/23 - with no Fiber in yet, the ISD will slip. IT needs 4 to 5 weeks to get splicing and all circuites up and tested. Planned ISD to shift approximately a month. PPI letter is needed. MMA was approved. Triggered an FRR due to the adding of a battery. 8/21/23 - MMA about to be executed that will take this back to green. 8/7/23 - IC telecom to be completed end of Aug. PGE to follow remaining activities end of Oct. MMA in play need completed due to inverter changes. 07/27/23 - Craig says Customers Telecom is driving the schedule to get their OPGW transition to underground going into the substation. PGE has installed 5 of 6 TL foundations. 6/22/23 - Civil contract pricing received and contract is routed. IC has to cross I-5 and CA-99. Permit Status. String to POCO last week of August. 5/22/23 - ISD depends on IC. | Customer - Bundling Dependencies | 1398 | 1398
OAKLAND UNIT 2 METER-DA | 5543863 | T.0006936 | 82Y | The 0051CONV Oakland C Unit 2 Repower Project from Cluster Repower, proposes to interconnect a 55 megawatt (MW) (net output) Repower generation facility to Oakland C Substation in Alameda County, California. The project has a contractual In-service date of: 12/1/26 with a current planned In-service date of: 12/1/26 | Operational | 2023-08-04 |  |  | Hydesville CDP, Humboldt | PG&E: Greater Fresno Area | No | N/A |  | Replace | Emergency Event | Age/Condition - Replace Relays | N/A | 0.41044 | N/A | 60 kV | 2022-08-15 | 2026-12-01 | 2026-12-01 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - IC stopped their scope and has not engaged project management. MMA in process to change date to 2026. | Utility - !Telecom! | 0051CONV | 0051CONV
Q1540-PLANO STORAGE METER-DA | 5544345 | T.0007032 | 82Y | The Q1540 Plano Energy Storage Project from Cluster ISP, proposes to interconnect a 350 megawatt (MW) (net output) Battery generation facility to Moss Landing 500kV in Monterey County, California. The project has a contractual In-service date of: 12/1/21 with a current planned In-service date of: 3/1/23 | Operational | 2021-04-21 |  |  | American Canyon, Napa ¦ Black Point-Green Point CDP, Marin ¦ Fairfield, Solano ¦ Marin ¦ Napa ¦ Novato, Marin ¦ Solano ¦ Sonoma ¦ Vallejo, Solano | PG&E: Greater Fresno Area | No | N/A |  | New | Asset Condition | Generation Interconnection | N/A | NA | 115 | N/A | 2023-11-30 | 2021-12-01 | 2023-03-01 | Transmission Project Review Process data (Resolution E-5252 Attach B | 455 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | COD - 5/19/23 for In-Service - 3/1/23 | Utility - Bundling Dependencies | 1540 | 1540
Q1350 - PAULSELL METER-DA | 5544563 | T.0007108 | 82Y | The Q1350 Paulsell Solar Project from Cluster 10, proposes to interconnect a 20 megawatt (MW) (net output) Solar + Battery generation facility to Crow Creek SW 60kV in Stanislaus County, California. The project has a contractual In-service date of: 12/1/23 with a current planned In-service date of: 3/28/24 | Operational | 2022-11-30 |  |  | N/A | 0 | No | N/A |  | Upgrade/Retrofit | Other [See Notes] | System Operations | N/A | N/A | N/A | N/A | 2021-02-19 | 2023-12-01 | 2024-03-28 | Transmission Project Review Process data (Resolution E-5252 Attach B | 118 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | In-Service - 3/37/24 3/4/24 - Customer Failed PPI. New clearance set for 3/27. 2/5/24 -Likely ISD End of April 2024. Pending easements for Microwave at Wesley. 1/23/24 - Due to weather, the IC could not complete the test reports for submittal. Working on catchback and rescheduling PPI. 1/8/24 - Targeting COD by 4/1 per the IC. 12/12/23 - ISD is tracking. Gentie work is completed. 11/1/23 - ISD Tracking 10/2/23 - Work at Crowcreek is complete. IC has started construction 9/20/23 - Tline Switch has TID distribution equipment to be removed by the 3rd party. Low risk associated to the tline work and coordination. 9/18/23 - IT resource constraints due to overall volume of work. 8/7/23 - IC has not started construction. Expect ISD to trend later in Q1 2024. 07/27/23 - Need update on the IC schedule. 6/22/23 - some IC delays related IC customers XFMR order. Verify with SDQ1 expected. Check in with SDQ1 | Customer - !Telecom! | 1350 | 1350
Q1470 CABALLERO STORAGE - METER DA | 5544946 | T.0007181 | 82Y | The Q1470 Caballero Storage Project from Cluster 11, proposes to interconnect a 99.7 megawatt (MW) (net output) Battery generation facility to Mesa 230kV in San Luis Obispo County, California. The project has a contractual In-service date of: 9/15/24 with a current planned In-service date of: 10/9/24 | Engineering more than 50% complete | 2024-05-30 |  |  | Kern | PG&E Kern Area | Yes | N/A | Maintenance ¦ Maintenance | New | Generator Interconnection | Generation Interconnection | N/A | 4.5471 | N/A | 230 kV | 2025-12-01 | 2024-09-15 | 2024-10-09 | Transmission Project Review Process data (Resolution E-5252 Attach B | 24 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | ISD on track to Sept 2024. | - | 1470 | 1470
Q1495 CHALAN SOLAR (DA) METER PV | 5544947 | T.0007165 | 82Y | The Q1495 Chalan Solar Project from Cluster 11, proposes to interconnect a 64.9 megawatt (MW) (net output) Solar + Battery generation facility to Arco 230kV in Kern County, California. The project has a contractual In-service date of: 12/20/24 with a current planned In-service date of: 3/24/26 | Engineering more than 50% complete | 2024-05-30 |  |  | Kern | N/A | Yes | N/A | T.0007289 ¦ T.0006452 | New | Generator Interconnection | Generation Interconnection | N/A | 4.5471 | N/A | 230 kV | 2025-12-01 | 2024-12-20 | 2026-03-24 | Transmission Project Review Process data (Resolution E-5252 Attach B | 459 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - MMA submitted to change ISD and Technology. With PGE for Round 4 review. Tracking ISD to Dec 2025 with risk to complete in 2025. | Customer - Construction Delays | 1495 | 1495
Q1495 CHALAN SOLAR (DA) METER BESS | 5544948 | T.0007165 | 82Y | The Q1495 Chalan Solar Project from Cluster 11, proposes to interconnect a 64.9 megawatt (MW) (net output) Solar + Battery generation facility to Arco 230kV in Kern County, California. The project has a contractual In-service date of: 12/20/24 with a current planned In-service date of: 3/24/26 | Engineering more than 50% complete | 2024-05-30 |  |  | Kern | PG&E Kern Area | Yes | N/A | T.0007289 ¦ T.0006452 | New | Generator Interconnection | Generation Interconnection | N/A | 4.5471 | N/A | 230 kV | 2025-12-01 | 2024-12-20 | 2026-03-24 | Transmission Project Review Process data (Resolution E-5252 Attach B | 459 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - MMA submitted to change ISD and Technology. With PGE for Round 4 review. Tracking ISD to Dec 2025 with risk to complete in 2025. | Customer - Construction Delays | 1495 | 1495
Q1270_CORBY METER-BESS-DA | 5545041 | T.0007195 | 82Y | The Q1270 Corby Energy Storage Project from Cluster 9, proposes to interconnect a 300 megawatt (MW) (net output) Battery generation facility to Vaca Dixon 230kV in Solano County, California. The project has a contractual In-service date of: 2/28/27 with a current planned In-service date of: 2/28/27 | Engineering more than 50% complete | 2025-03-30 |  |  | Merced | PG&E Kern Area | Yes | N/A | T.0008048 ¦ T.0004673 ¦ T.0001609 ¦ T.0007288 | New | Generator Interconnection | Generation Interconnection | N/A | 53.2803 | N/A | 230 kV | 2026-06-10 | 2027-02-28 | 2027-02-28 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 06/02/25 - ISD reset to the contract ISD until construction clearances and sequencing can be verified. This depends on the Vaca OSB mitigation with ISD in Dec 2026. 05/19/25 - The breaker delivery and outdoor construction begin in June 2025, with design reviews and orders progressing. No restraints reported, next steps include T-Line 60% design completion and steel structure orders by July 2025. Tracking ISD in Q4 2026 | - | 1270 | 1270
Q1382-LAS CAMAS 1-METER-DA | 5545266 | T.0007250 | 82Y | The Q1382 Las Camas 1 Project from Cluster 10, proposes to interconnect a 100 megawatt (MW) (net output) Solar generation facility to Los Banos 230kV in Merced County, California. The project has a contractual In-service date of: 3/30/25 with a current planned In-service date of: 7/17/26 | Engineering more than 50% complete | 2025-03-30 |  |  | Merced | N/A | Yes | N/A |  | New | Generator Interconnection | Generation Interconnection | N/A | 53.2803 | N/A | 230 kV | 2026-06-10 | 2025-03-30 | 2026-07-17 | Transmission Project Review Process data (Resolution E-5252 Attach B | 474 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - MMA required to push ISD to Q3 2026 | - | 1382 | 1382
MENDOTA-NORTH STAR 115KV LINE RERATE DA | 5545664 | T.0002465 | 82D | The Q1028_Q1029 Little Bear Solar 1 & 2 Project from Cluster 7, proposes to interconnect a 40 megawatt (MW) (net output) + generation facility to Mendota 115kV in Fresno County, California. The project has a contractual In-service date of: with a current planned In-service date of: 9/21/20 | Engineering more than 50% complete | N/A |  |  | N/A | N/A | No | N/A |  | Upgrade/Retrofit | Other [See Notes] | T-Line Capacity | N/A | NA | N/A | N/A | N/A | 2020-11-30 | 2020-09-21 | Transmission Project Review Process data (Resolution E-5252 Attach B | -70 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | - | 1028_1029 | 1028_1029
Q1394 DRIFTWOOD STELLA METER DA | 5545670 | T.0007329 | 82Y | The Q1394 Driftwood Stella Project from Cluster 10, proposes to interconnect a 200 megawatt (MW) (net output) Solar + Battery generation facility to Midway 115kV in Kern County, California. The project has a contractual In-service date of: 4/1/26 with a current planned In-service date of: 4/27/26 | Engineering more than 50% complete | N/A |  |  | N/A | PG&E: Greater Bay Area | No | N/A | Maintenance ¦ Maintenance ¦ T.0006452 | New | Other [See Notes] | System Operations | N/A | NA | N/A | N/A | N/A | 2024-02-01 | 2026-04-27 | Transmission Project Review Process data (Resolution E-5252 Attach B | 816 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - Tracking ISD to April 2026. IC late on deliverables | - | 1394 | 1394
Q1244 PROXIMA LAND ACQUISITION | 5545722 | T.0003770 | 82W | The Q1244 Proxima Solar Project from Cluster 9, proposes to interconnect a 300 megawatt (MW) (net output) Solar + Battery generation facility to Fink 230kV switching station in Stainslaus County, California. The project has a contractual In-service date of: 10/15/23 with a current planned In-service date of: 3/6/24 | Operational | 2020-01-10 |  |  | Merced | 0 | Yes | N/A |  | New | Generator Interconnection | Safety - Line Right of Way Access | N/A | 53.2803 | N/A | 230 kV | N/A | 2023-10-15 | 2024-03-06 | Transmission Project Review Process data (Resolution E-5252 Attach B | 143 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | NOC: AL 6529-E | 2022-03-16 | Approved | 2022 | COD - 3/18/24 for 162MW 3/6/24 - The Q1244 Proxima Solar project achieved In-Service Date (ISD) today March 6, 2024. This project will generate 300 MW of renewable PV energy and capable of 150 MW of battery storage. The project encompasses approximately 1,100 acres. Final testing of the facility is scheduled for next Wednesday March 13th, 2024 and a Commercial Operation Date letter is expected by the end of the month. To interconnect the customer project, PG&E teams engineered, permitted, tested and placed into service on March 5, 2024 a greenfield looped Switching Station (SS) 11 acres in size named Fink SS. The SS was an EPC contract type project completed through the competitive bid process. Fink SS connects to the 230 kV system approximately 4 miles north of the PG&E Quinto SS and a few miles south of the third party utility owned 230 kV substation Westley substation in Stanislaus County. To interconnect the new 230 kV SS the project called for protective relay upgrades at Los Banos, Quinto SS, and Westley Substation. The PG&E project team coordinated with Modesto Irrigation District (MID) to get the project successful. There was also telecommunications and testing coordination at Westley Substation MID teams and PG&E teams. The energization of Fink SS and Proxima occurred via radial connection. This energization test process spanned a few days to fully test the SS and the third party customer substation. There is remaining work to be completed in order to energize the Fink SS – Westley 230 kV line and is scheduled to finalize April 1, 2024. This project had many barriers to get towards completion. One of the major barriers was permitting and acquiring the land from Stanislaus County. I want to shout out @Everett, Kirsten and @Crossfield, Scott for essentially being a Stanislaus county resource and spending many days waiting at their counter or hand delivering necessary requirements to complete permitting and acquisition activities. This project kicked off in Q2 2018 with a total of over 165 different resources attending project meetings and lending their expertise throughout the project lifecycle. Thank you to everyone involved in this project and helping to bring expertise and professionalism when interacting with NextEra as well as overcome obstacles and provide a quality product. 3/4/24 -Expecting to energize Proxima on 3/6. Fink SS is 3/5. 2/5/25 - PGE Microwave scope between Mt Oso and MID's Wesley Substation cannot be started until Agreements between MID and PGE are made. Scope and Cost impacts being worked out between multi-parties. Interim solution being reviewed but may conflict with the original scope and schedule. 1/23/24 - MID delays have put IC at risk of default. They are incurring costs due to Generators of battery minimally charging. Impacting their Environmental Air Quality Permits if they keep running longer. 1/11/24 - IC does not have their CAISO letter for Permission to Test which was required to put load on Fink thus energizing both SS and Gensite. ISD moved to March after MID work is complete which would no required Q1244 as load to test Fink. 12/14/23 - IC could not get a CAISO clearance until 12/20 due to telecom commissiong, key predecessor activities, and EoY CAISO clearance congestion. Due to the late December date, the PG&E resources to backfeed the customer are insufficient to safely perform the work. 12/13/23 - PTO letter to CAISO on 12/13. Clearance for backfeed 12/20. Requires Battery Loads to Sync Sw Sta. 12/12/23 - Line Connector assemblies were ACSR and not ACSS. This results in temporary re-rate on the line until the repair can be completed. Estimated at 100 to 150K to fix. Mike Milbury and CM Kevin Withrow know the details. 12/7/23 - SCADA/EMS release planned for 12/11/23. Backfeed planned for 12/15. IC is ready to provide 120MWs of load given 24 hours of notice. Potential they can increase that. MID on a call today due to Turlock irrigation district impact.MID needs the Turlock concent to proceed to EoFeb. 11/1/23 - Verify with SQ ISD Trending to Jan 2024 12/15/23 at this time for ISD. 10/2/23 - MID is no longer critical path. Moved to the end of the sequence and affect COD only. Internal only - PM is looking at possibly pulling the ISD into December. Telecom and NERC activity impacting. 9/19/23 - MID work on the DTT on the line is critical to hit the Tline work sequence. 9/18/23 - ISD is tracking to Jan 2024. 8/21/23 - MID is asking for 25 weeks now. rebalanced the clearance so MID comes at the end. Affect COD but not ISD. 8/7/23 - ISD is likely to delay due to MID. MID asking for 20 weeks to do relay work starting in Oct. Meeting next week discuss. 07/27/23 - Schedule is the same for last note. 6/22/23 - Oct 10-20 Tline to set poles for the new SS loop in. 5/15/23 - ISD is pusing to 2024 due to SS construction. Permanent Land acquisitions still with Legal. T_line foundations installed for the loop-in. Clearance to come back in Fall. | Utility - !Telecom! | 1244 | 1244
Q1106 FOUNTAIN WIND NU BUYBACK SWITCHING | 5545804 | T.0003035 | 82W | The Q1106 Fountain Wind Project from Cluster 8, proposes to interconnect a 200 megawatt (MW) (net output) Wind Turbine generation facility to Pit1-Cottonwood 230kV Line in Shasta County, California. The project has a contractual In-service date of: 4/30/27 with a current planned In-service date of: 9/9/27 | Engineering more than 50% complete | 2020-06-01 |  |  | Cottonwood CDP, Shasta | 0 | Yes | N/A | T.0009188 ¦ T.0003035 | New | Generator Interconnection | New Substation | N/A | 26.1945 | N/A | 230 kV | 2027-03-04 | 2027-04-30 | 2027-09-09 | Transmission Project Review Process data (Resolution E-5252 Attach B | 132 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 06/02/25 - Current ISD 2027 unachievable. Customer CEQA/EIR CEC Permit process still outstanding wiyth expectation to receive permit in August 2025. ISD depends on a GIP RAS and construction of new customer built switching station. | Customer - Permitting (Customer) | 1106 | 1106
Q1493 AZALEA (NU) ARCO SUB | 5545945 | T.0006119 | 82W | The Q1493 Azalea Project from Cluster 11, proposes to interconnect a 60 megawatt (MW) (net output) Solar + Battery generation facility to Arco 70kV in Kern County, California. The project has a contractual In-service date of: 5/20/25 with a current planned In-service date of: 5/20/25 | Operational | 2024-12-07 |  |  | Kern | PG&E Kern Area | Yes | N/A | T.0006452 | New | Generator Interconnection | Generation Interconnection | N/A | 4.5471 | N/A | 70 kV | 2023-11-15 | 2025-05-20 | 2025-05-20 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - Customer moved ISD to May 2025. | - | 1493 | 1493
Q1493 AZALEA (NU) GATES SUB | 5545947 | T.0006119 | 82W | The Q1493 Azalea Project from Cluster 11, proposes to interconnect a 60 megawatt (MW) (net output) Solar + Battery generation facility to Arco 70kV in Kern County, California. The project has a contractual In-service date of: 5/20/25 with a current planned In-service date of: 5/20/25 | Operational | 2024-12-07 |  |  | Fresno | PG&E Kern Area | Yes | N/A | T.0006452 | Upgrade/Retrofit | Generator Interconnection | Special Protection Scheme | N/A | 77.6619 | N/A | 70 kV | 2024-03-01 | 2025-05-20 | 2025-05-20 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - Customer moved ISD to May 2025. | - | 1493 | 1493
Q1557 NOOSA ENERGY STORAGE METER DA | 5546248 | T.0007445 | 82Y | The Q1557 Noosa Energy Storage Project from Cluster 12, proposes to interconnect a 99 megawatt (MW) (net output) Battery generation facility to Ripon 115kV in San Joaquin County, California. The project has a contractual In-service date of: 1/29/26 with a current planned In-service date of: 3/31/26 | Engineering more than 50% complete | 2025-01-10 |  |  | Ripon, San Joaquin | 0 | Yes | N/A | T.0007979 ¦ T.0007979 ¦ T.0007979 ¦ T.0004515 | Upgrade/Retrofit | Generator Interconnection | Generation Interconnection | N/A | 2.0603 | N/A | 115 kV | 2025-08-14 | 2026-01-29 | 2026-03-31 | Transmission Project Review Process data (Resolution E-5252 Attach B | 61 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 06/02/25 - MMA was submitted. Customer has not started construction yet. It is expected the IC cannot finish Gensite construction and interconnection until Q1 2026. | - | 1557 | 1557
Q1539 IRVING STORAGE-METER DA | 5546344 | T.0007467 | 82Y | The Q1539 Irving Storage Project from Cluster ISP, proposes to interconnect a 750 megawatt (MW) (net output) Battery generation facility to Moss Landing 500kV in Monterey County, California. The project has a contractual In-service date of: 8/30/25 with a current planned In-service date of: 11/19/27 | Engineering more than 50% complete | 2025-08-30 |  |  | Monterey | 0 | Yes | N/A | T.0007290 ¦ T.0007291 ¦ T.0007288 | New | Generator Interconnection | Generation Interconnection | N/A | 41.3213 | N/A | 500 kV | 2027-04-15 | 2025-08-30 | 2027-11-19 | Transmission Project Review Process data (Resolution E-5252 Attach B | 811 | Yes |  |  | N/A |  | TBD | N/A | TBD | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - Tracking ISD to late 2027. MMA required to adjust to earliest ISD | - | 1539 | 1539
Q1493 AZALEA (DA) METER | 5546403 | T.0006119 | 82Y | The Q1493 Azalea Project from Cluster 11, proposes to interconnect a 60 megawatt (MW) (net output) Solar + Battery generation facility to Arco 70kV in Kern County, California. The project has a contractual In-service date of: 5/20/25 with a current planned In-service date of: 5/20/25 | Operational | 2017-05-31 |  |  | Butte ¦ Chico, Butte ¦ Durham CDP, Butte | PG&E: Greater Fresno Area | No | N/A | T.0006452 | New | Asset Condition | NERC Compliance - GO 95 | N/A | N/A | 115 | N/A | N/A | 2025-05-20 | 2025-05-20 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - Customer moved ISD to May 2025. | - | 1493 | 1493
Q1507 PROSPECT (DA) MTR | 5546763 | T.0006433 | 82Y | The Q1507 Prospect Energy Project from Cluster 11, proposes to interconnect a 49.9 megawatt (MW) (net output) Battery generation facility to Gold Hill 60kV in Sacramento County, California. The project has a contractual In-service date of: 5/2/28 with a current planned In-service date of: 4/18/28 | Engineering more than 50% complete | 2023-08-07 |  |  | Folsom, Sacramento | N/A | Yes | N/A | T.0006348 | New | Generator Interconnection | Generation Interconnection | N/A | N/A | N/A | 60 kV | 2027-02-01 | 2028-05-02 | 2028-04-18 | Transmission Project Review Process data (Resolution E-5252 Attach B | -14 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - Updated ISD in schedule. MMA has been requested. 02/10/25 - IC need to submit new MMA and schedule 11/20/24 - ISD must be moved out on resuming project. Project was due to return in Oct 2024 but has not. | Customer - Permitting (Customer) | 1507 | 1507
Q1565 - DYNAMO SOLAR METER DA | 5546926 | T.0007591 | 82Y | The Q1565 Dynamo Solar Project from Cluster 12, proposes to interconnect a 24.5 megawatt (MW) (net output) Solar generation facility to Tulucay 60kV in Napa County, California. The project has a contractual In-service date of: 10/10/25 with a current planned In-service date of: 10/10/25 | Engineering more than 50% complete | N/A |  |  | N/A | 0 | No | N/A |  | Upgrade/Retrofit | Asset Condition | Age/Condition - Replace Other T-Line Equipment | N/A | NA | N/A | N/A | N/A | 2025-10-10 | 2026-03-31 | Transmission Project Review Process data (Resolution E-5252 Attach B | 172 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - Tracking ISD to Q3 2026 due to IC CEQA process related delays. | Customer - Permitting (Customer) | 1565 | 1565
Q1479 KEY STRGE 1 METER DA | 5547568 | T.0007722 | 82Y | The Q1479 Key Storage 1 Project from Cluster 11, proposes to interconnect a 300.1 megawatt (MW) (net output) Battery generation facility to Gates 500kV in Fresno County, California. The project has a contractual In-service date of: 6/1/26 with a current planned In-service date of: 6/1/26 | Engineering more than 50% complete | N/A |  |  | N/A | 0 | No | N/A | Maintenance ¦ Maintenance ¦ T.0007289 ¦ Maintenance | Upgrade/Retrofit | Asset Condition | Age/Condition - Replace Other T-Line Equipment | N/A | NA | N/A | N/A | N/A | 2026-06-01 | 2026-06-01 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - Customer wants to relocate Metering from existing drawings. RFI needed to relocate meters. Tracking ISD in Jun 2026 | - | 1479 | 1479
Q1596 BUTTONBUSH SLR METER DA | 5547703 | T.0007731 | 82Y | The Q1596 Buttonbush Solar Hybrid Energy Center Project from Cluster 12, proposes to interconnect a 800 megawatt (MW) (net output) Solar + Battery generation facility to Midway 500kV in Kern County, California. The project has a contractual In-service date of: 11/5/26 with a current planned In-service date of: 11/5/26 | Planning | N/A |  |  | N/A | N/A | No | N/A | Maintenance ¦ Maintenance ¦ Maintenance ¦ T.0007289 | New | Other [See Notes] | System Operations | N/A | NA | N/A | N/A | N/A | 2026-11-05 | 2026-11-05 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/05/25 - MMA submitted to change ISD and Technology. With ISO for engineering review and approval. Tracking ISD in Nov 2026 | - | 1596 | 1596
DOS AMIGOS - PANOCHE T-LINE LAND ACQ. | 5547947 | T.0004255 | 82B | The C9P1-F11 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Dos Amigos–Panoche # 3 230 kV Line in Merced County, California. | Engineering more than 50% complete | 2021-09-30 |  |  | Fresno ¦ Merced | PG&E: Greater Bay Area | Yes | N/A | T.0003742 ¦ T.0003005 ¦ T.0002987 ¦ T.0004490 ¦ T.0008538 ¦ 0 ¦ T.0010467 ¦ 0 ¦ T.0010817 ¦ T.0010816 ¦ 0 ¦ 0 ¦ T.0010942 ¦ TBD ¦ 0 ¦ T.0010887 ¦ T.0010738 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 | New | Generator Interconnection | Safety - Line Right of Way Access | 23.6 | N/A | 230 | N/A | N/A | 2021-09-30 | 2026-05-18 | Transmission Project Review Process data (Resolution E-5252 Attach B | 1691 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | NOC: AL 7392-E | 2024-10-02 | Approved | 2024 | 04/07/25 - Project tracking to ISD on schedule | Utility - !Telecom! | Q1135, Q1127, Q1128, Q1129, Q1713, Q1568, Q1709, 2226-WD, Q1928, Q1930, Q1932, Q1933, Q1934, Q1935, Q1940, Q1953, Q1955, Q1956, Q1963, Q1966, Q1968, Q1970, Q1975, Q1977 | Q1135 | Q1127 | Q1128 | Q1129 | Q1713 | Q1568 | Q1709 | 2226-WD | Q1928 | Q1930 | Q1932 | Q1933 | Q1934 | Q1935 | Q1940 | Q1953 | Q1955 | Q1956 | Q1963
W FORD FLAT - ESTORAGE METER-DA | 5548060 | T.0007849 | 82Y | The Q1367 West Ford Flat Energy Storage Project from Cluster 10, proposes to interconnect a 25 megawatt (MW) (net output) Battery generation facility to Fulton 230kV in Lake County, California. The project has a contractual In-service date of: 2/15/24 with a current planned In-service date of: 4/19/24 | Operational | 2023-06-30 |  |  | Antioch, Contra Costa | 0 | No | N/A |  | Replace | Asset Condition | Age/Condition - Replace Switches | N/A | 15.1779 | N/A | 230 kV | 2023-05-01 | 2024-02-15 | 2024-04-19 | Transmission Project Review Process data (Resolution E-5252 Attach B | 64 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | In-Service - 4/18/24 - Commencing Commercial Testing 4/15/24 - Short on 2 points on EMS/SCADA. Next chance to prove comms on 4/19. Pending on other test results. 3/27/24 - Temporary Comms solution required to backfeed until Telco solution is in place 3/25/24 - PPI is completed as of 2/23/24. ISD to be 3/27/24 2/5/24 - MRS (Managed Router Service) needed. will require Telco configuration. Dates ?. Assume a month delay. 1/4/24 - ASEoD meeting held. This project PA is exceeded and needs reauthorized. PM to go to AM Supv to confirm AM to assist in PA. 1/3/24 to coordinate and schedule Q1097. They need to order the MRS service (end points orders) 12/4/23 - FDP is proceeding. 11/1/23 - ISD in 2024 tracking 10/2/24 - ISD of 2/13/24 is achievable. MMA # 2 active for 8/21/23 - ISD of 2/13/24 remains achievable. IC schedule appears to be tracking. | Customer - !Telecom! | 1367 | 1367
Q1552 CORMORANT STRGE 1 METER DA | 5548500 | T.0008098 | 82Y | The Q1552 Cormorant Storage Project from Cluster 12, proposes to interconnect a 250 megawatt (MW) (net output) Battery generation facility to Martin 115kV in San Francisco County, California. The project has a contractual In-service date of: 12/15/24 with a current planned In-service date of: 3/2/27 | Engineering more than 50% complete | 2024-12-15 |  |  | Brisbane, San Mateo | N/A | Yes | N/A | T.0007290 ¦ T.0007287 ¦ Maintenance | Upgrade/Retrofit | Generator Interconnection | Generation Interconnection | N/A | 18.2105 | N/A | 115 kV | 2026-05-01 | 2024-12-15 | 2027-03-02 | Transmission Project Review Process data (Resolution E-5252 Attach B | 807 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - Location problem for POCO, estimated solution for August to confirm location for POCO | - | 1552 | 1552
Q1496 DESCENDANT RNCH 1 1 METER DA | 5548503 | T.0008063 | 82Y | The Q1496 Descendant Ranch 1 Project from Cluster 11, proposes to interconnect a 500 megawatt (MW) (net output) Solar + Battery generation facility to Delevan 230kV in Colusa County, California. The project has a contractual In-service date of: 8/30/25 with a current planned In-service date of: 9/7/28 | Planning | 2025-01-01 |  |  | San Jose, Santa Clara | N/A | Yes | N/A | T.0009188 ¦ T.0008063 ¦ T.0001609 | New | Generator Interconnection | Generation Interconnection | N/A | 13.1703 | N/A | 230 kV | 2027-07-07 | 2025-08-30 | 2028-09-07 | Transmission Project Review Process data (Resolution E-5252 Attach B | 1104 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - IC is suspending project. Notice from IC that they are behind an affected system (TANC) with estimated cost of of $50M and 5Yr Duration. Asks to cease all work on IF & IRNUs. At risk to withdraw. | Customer + Utility - GIP Upgrades | 1496 | 1496
Q1550 TANAGER STRGE 1 METER DA | 5548523 | T.0007981 | 82Y | The Q1550 Tanager Energy Storage Project from Cluster 12, proposes to interconnect a 200 megawatt (MW) (net output) Battery generation facility to Los Esteros 230kV in Santa Clara County, California. The project has a contractual In-service date of: 1/1/25 with a current planned In-service date of: 8/31/27 | Planning | 2025-01-01 |  |  | San Jose, Santa Clara | N/A | Yes | N/A | T.0007290 ¦ Maintenance | New | Generator Interconnection | Generation Interconnection | N/A | 13.1703 | N/A | 230 kV | 2027-07-07 | 2025-01-01 | 2027-08-31 | Transmission Project Review Process data (Resolution E-5252 Attach B | 972 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - 1/1/2025 ISD, 4/1/2025 COD, Tracking to Q3 2027 attributed to IC has no site control | - | 1550 | 1550
Q1444 SALOON ENERGY METER (DA) | 5548811 | T.0008218 | 82Y | The Q1444 Saloon Energy Storage Project Project from Cluster 11, proposes to interconnect a 150 megawatt (MW) (net output) Solar + Battery generation facility to Cortina 115kV in Colusa County, California. The project has a contractual In-service date of: 6/9/27 with a current planned In-service date of: 7/27/27 | Engineering more than 50% complete | 2025-04-28 |  |  | Colusa | N/A | Yes | N/A | T.0007629 ¦ T.0007629 ¦ T.0001609 | New | Generator Interconnection | Generation Interconnection | N/A | 6.7436 | N/A | 115 kV | 2025-11-10 | 2027-06-09 | 2027-07-27 | Transmission Project Review Process data (Resolution E-5252 Attach B | 48 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - Tracking ISD in Q2 2027 | Customer - Permitting (Customer) | 1444 | 1444
Q1461 RECLAIMED WIND 1 METER DA | 5549419 | T.0008307 | 82Y | The Q1461 Reclaimed Wind Project from Cluster 11, proposes to interconnect a 90.7 megawatt (MW) (net output) Wind Turbine generation facility to Kelso-Tesla Tap 230kV Line in Alameda County, California. The project has a contractual In-service date of: 10/5/26 with a current planned In-service date of: 8/24/26 | Operational | 2023-06-30 |  |  | Mendocino ¦ Ukiah, Mendocino | N/A | No | N/A | T.0004673 | N/A | Asset Condition | Compliance - Remove Idle Facilities | N/A | NA | 60 | N/A | 2024-06-24 | 2026-10-05 | 2026-08-24 | Transmission Project Review Process data (Resolution E-5252 Attach B | -42 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - Tracking ISD in Q3 2026 attributed to customer POI change | Customer - Project Design | 1461 | 1461
Contra Costa 230kV SW's 601, 603 overload | 5549722 | T.0008048 | 61W | The C11P2-NP01 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Contra Costa Substation 230kV in Contra Costa County, California. | Construction (25%-50%) | 2025-05-01 |  |  | Solano | PG&E: North Valley Area | No | 2022 | T.0010478 ¦ 0 ¦ 0 ¦ 0 ¦ 0 | Upgrade/Retrofit | Reliability | T-Line Capacity | N/A | 3.4512 | N/A | 230 kV | 2024-12-06 | 2025-05-01 | 2025-05-30 | Transmission Project Review Process data (Resolution E-5252 Attach B | 29 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom! | Q1691, Q1842, Q1843, Q1850, Q1915 | Q1691 | Q1842 | Q1843 | Q1850 | Q1915
Contra Costa 230kV SW's 601, 603 overload | 5549723 | T.0008048 | 61W | The C11P2-NP01 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Contra Costa Substation 230kV in Contra Costa County, California. | Construction (25%-50%) | 2025-05-01 |  |  | Antioch, Contra Costa | PG&E: North Valley Area | No | 2022 | T.0010478 ¦ 0 ¦ 0 ¦ 0 ¦ 0 | Upgrade/Retrofit | Reliability | T-Line Capacity | N/A | 2.3791 | N/A | 230 kV | 2025-01-28 | 2025-05-01 | 2025-05-30 | Transmission Project Review Process data (Resolution E-5252 Attach B | 29 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom! | Q1691, Q1842, Q1843, Q1850, Q1915 | Q1691 | Q1842 | Q1843 | Q1850 | Q1915
Q1499 JASMINE SOLAR (DA) METER | 5549794 | T.0006097 | 82Y | The Q1499 Jasmine Solar Project from Cluster 11, proposes to interconnect a 70 megawatt (MW) (net output) Solar + Battery generation facility to Lakeview 70kV in Kern County, California. The project has a contractual In-service date of: 6/15/26 with a current planned In-service date of: 10/13/26 | Engineering more than 50% complete | 2024-07-07 |  |  | Kern | #REF! | Yes | N/A | T.0006452 ¦ Maintenance | New | Generator Interconnection | Generation Interconnection | N/A | 1.3475 | N/A | 70 kV | 2026-08-03 | 2026-06-15 | 2026-10-13 | Transmission Project Review Process data (Resolution E-5252 Attach B | 120 | Yes |  |  | Final Certified | 45390 | EIR | N/A | Kern County | N/A | NOC: AL 7247-E | 2024-04-26 | Approved | 2024 | 05/06/25 - Project sold to new IC. Potential ISD impact. | Customer - Project Changing Ownership | 1499 | 1499
Q1499 JASMINE LAND ACQUISITION | 5549795 | T.0006097 | 82W | The Q1499 Jasmine Solar Project from Cluster 11, proposes to interconnect a 70 megawatt (MW) (net output) Solar + Battery generation facility to Lakeview 70kV in Kern County, California. The project has a contractual In-service date of: 6/15/26 with a current planned In-service date of: 10/13/26 | Operational | 2024-07-07 |  |  | Kern | PG&E Kern Area | Yes | N/A | T.0006452 ¦ Maintenance | New | Generator Interconnection | Safety - Line Right of Way Access | N/A | 1.3475 | N/A | 70 kV | N/A | 2026-06-15 | 2026-10-13 | Transmission Project Review Process data (Resolution E-5252 Attach B | 120 | Yes |  |  | Final Certified | 45390 | EIR | N/A | Kern County | N/A | NOC: AL 7247-E | 2024-04-26 | Approved | 2024 | 05/06/25 - Project sold to new IC. Potential ISD impact. | Customer - Project Changing Ownership | 1499 | 1499
Q1835 CASCADE ES EXPN METER DA | 5550124 | T.0008519 | 82Y | The Q1835 Cascade ES Expansion Project from Cluster 9, proposes to interconnect a 20 megawatt (MW) (net output) Battery generation facility to Weber in San Joaquin County, California. The project has a contractual In-service date of: 8/14/24 with a current planned In-service date of: 12/4/24 | Operational | N/A |  |  | Foster City, San Mateo ¦ Menlo Park, San Mateo ¦ Redwood City, San Mateo ¦ San Mateo, San Mateo | N/A | No | N/A |  | Replace | Asset Condition | Age/Condition - Replace Steel Poles | N/A | NA | 230 | N/A | 2022-07-25 | 2024-08-14 | 2024-12-04 | Transmission Project Review Process data (Resolution E-5252 Attach B | 112 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 11/07/24 - Q1835 Cascade 20W did not energize 11/5 as planned. The customer was not ready and has pushed out their energization out a week and I believe the date is TBD. 10/31/24 - ISD delayed to November 4 2024 due to Customer delays | Customer - Construction Delays | 1835 | 1835
Q1459 Mulqueeny Ranch Wind 2 metering (DA) | 5550660 | T.0004354 | 82Y | The Q1459 Mulqueeney Ranch Wind 2 Project from Cluster 11, proposes to interconnect a 60 megawatt (MW) (net output) Wind Turbine generation facility to Tesla 230kV in Alameda County, California. The project has a contractual In-service date of: 10/15/25 with a current planned In-service date of: 10/15/25 | Engineering more than 50% complete | N/A |  |  | Deer Park CDP, Napa ¦ Fulton CDP, Sonoma ¦ Kenwood CDP, Sonoma ¦ Lake ¦ Larkfield-Wikiup CDP, Sonoma ¦ Napa ¦ Saint Helena, Napa ¦ Santa Rosa, Sonoma ¦ Sonoma | 0 | No | N/A | T.0004673 ¦ T.0007288 ¦ Maintenance ¦ T.0007288 | New | Reliability | T-Line Capacity | N/A | NA | 60 | N/A | N/A | 2025-10-15 | 2025-10-15 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - Tracking ISD to Jun 2026 attributed to 20rsmt-5 Tesla CB612. | - | 1459 | 1459
Q946 NORTHERN ORCHARD (MTR) | 5550661 | T.0001353 | 82Y | The Q946 Northern Orchard Solar Project from Cluster 6, proposes to interconnect a 100 megawatt (MW) (net output) Solar + Battery generation facility to Midway-Wheeler Ridge #2 230kV Line in Kern County, California. The project has a contractual In-service date of: 5/23/24 with a current planned In-service date of: 5/23/24 | Engineering more than 50% complete | N/A |  |  | Deer Park CDP, Napa ¦ Fulton CDP, Sonoma ¦ Kenwood CDP, Sonoma ¦ Lake ¦ Larkfield-Wikiup CDP, Sonoma ¦ Napa ¦ Saint Helena, Napa ¦ Santa Rosa, Sonoma ¦ Sonoma | PG&E: Greater Bay Area | No | N/A |  | New | Reliability | Safety - Line Right of Way Access | N/A | N/A | 60 | N/A | N/A | 2024-05-23 | 2024-05-23 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | In-Service - 5/24/24 4/22/24 - SS Testing Tcom circuits did not pass. Planned ISD with Gensite May 7. At risk pending Tcom resolution. 2/5/24 - ISD planned for April 30 2024 12/18/23 - moved out the date per Amber Fields and Alfredo. TLine critical path results in May 2024 ISD worst case. 12/12/23 - Tline Work has slipped into March based on contract process. TLine is critical path. The design took a long time due to various changes in plan, shoofly, land rights. etc 11/1/23 - ISD Tracking 9/19/23 - Tline is critical path for the whole project. LLM delivery is the only risk to schedule being tracked. (2) 90 and (2) 120 foot TSPs being delivered. 07/27/23 - TL installing a WP/LDSP shoofly to help hold main project schedule primarily delayed due material lead times. Sierra Utilities say Nov for Anchor Bolts and Dec for (4) TSPs. 6/22/23 - delayed to 2024. Tline procurement is critical path. 5/16/23 - Line work impacting an adjacent tower and could trigger the tower to be replaced. TSPs must be ordered. Expecting this 1/16/24 ISD to be even later. | Customer - !Telecom! | 946 | 946
Q1275 - KOLA GEN SITE MTR | 5550681 | T.0004563 | 82Y | The Q1275 Kola Project from Cluster 9, proposes to interconnect a 418 megawatt (MW) (net output) Battery generation facility to Tesla 230kV in Livermore County, California. The project has a contractual In-service date of: 4/15/25 with a current planned In-service date of: 7/11/25 | Engineering more than 50% complete | N/A |  |  | Deer Park CDP, Napa ¦ Fulton CDP, Sonoma ¦ Kenwood CDP, Sonoma ¦ Lake ¦ Larkfield-Wikiup CDP, Sonoma ¦ Napa ¦ Saint Helena, Napa ¦ Santa Rosa, Sonoma ¦ Sonoma | PG&E: North Valley Area | No | N/A | T.0007288 | New | Reliability | Safety - Line Right of Way Access | N/A | N/A | 60 | N/A | N/A | 2025-04-15 | 2025-07-11 | Transmission Project Review Process data (Resolution E-5252 Attach B | 87 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - ISD tracking July 2025. PG&E UG work at Tesla underway but delayed with expected ISD July 15 2025. 04/08/25 - ISD July 2025, delay due to Tline work schedule and resource constraints including Material delays. 03/11/25 - Tracking ISD in May 2025. Tesla CB642/CB542 PNU remain. Others removed. | Utility - Construction Delays | 1275 | 1275
Q1272 - CASCADE GEN SITE DA MTR | 5550682 | T.0004561 | 82Y | The Q1272 Cascade Energy Storage Project from Cluster 9, proposes to interconnect a 25 megawatt (MW) (net output) Battery generation facility to Weber 60kV in San Joaquin County, California. The project has a contractual In-service date of: 1/12/23 with a current planned In-service date of: 5/31/23 | Engineering more than 50% complete | N/A |  |  | Deer Park CDP, Napa ¦ Fulton CDP, Sonoma ¦ Kenwood CDP, Sonoma ¦ Lake ¦ Larkfield-Wikiup CDP, Sonoma ¦ Napa ¦ Saint Helena, Napa ¦ Santa Rosa, Sonoma ¦ Sonoma | N/A | No | N/A | T.0004561 | New | Reliability | Safety - Line Right of Way Access | N/A | NA | 60 | N/A | N/A | 2023-01-12 | 2023-05-31 | Transmission Project Review Process data (Resolution E-5252 Attach B | 139 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | COD - 8/31/23 for 25MW In-service 5/31/23 | Utility - Bundling Dependencies | 1272 | 1272
Q1106 - FOUNTAIN WIND MTR | 5550728 | T.0003035 | 82Y | The Q1106 Fountain Wind Project from Cluster 8, proposes to interconnect a 200 megawatt (MW) (net output) Wind Turbine generation facility to Pit1-Cottonwood 230kV Line in Shasta County, California. The project has a contractual In-service date of: 4/30/27 with a current planned In-service date of: 9/9/27 | Planning | 2020-06-01 |  |  | Burney CDP, Shasta ¦ Cottonwood CDP, Shasta ¦ Johnson Park CDP, Shasta ¦ Millville CDP, Shasta ¦ Oak Run CDP, Shasta ¦ Round Mountain CDP, Shasta ¦ Shasta | kern | Yes | N/A | T.0009188 ¦ T.0003035 | New | Generator Interconnection | Generation Interconnection | N/A | NA | N/A | 230 kV | 2027-03-19 | 2027-04-30 | 2027-09-09 | Transmission Project Review Process data (Resolution E-5252 Attach B | 132 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 06/02/25 - Current ISD 2027 unachievable. Customer CEQA/EIR CEC Permit process still outstanding wiyth expectation to receive permit in August 2025. ISD depends on a GIP RAS and construction of new customer built switching station. | Customer - Permitting (Customer) | 1106 | 1106
Q1143 - LAKE ALPAUGH BESS (MTR) | 5550842 | T.0003744 | 82Y | The Q1143 Lake Alpaugh BESS & Alpaugh 3 BESS Project from Cluster 8, proposes to interconnect a 10 megawatt (MW) (net output) Battery generation facility to Corcoran-Olive SW 115kV Line in Tulare County, California. The project has a contractual In-service date of: 7/15/25 with a current planned In-service date of: 10/31/25 | Engineering more than 50% complete | 2019-11-01 |  |  | Tulare | PG&E: Greater Fresno Area | Yes | N/A | T.0003009 ¦ T.0003789 | New | Generator Interconnection | Generation Interconnection | N/A | N/A | N/A | 115 kV | 2025-04-28 | 2025-07-15 | 2025-10-31 | Transmission Project Review Process data (Resolution E-5252 Attach B | 108 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - Tracking ISD delays. MMA approval required for redesign of ICs point of interconnection | Customer - Project / Design Changes | 1143 | 1143
Q1363 SANDHILL DA METERING | 5550843 | T.0004575 | 82Y | The Q1363 Sandhill C DTTs Project from Cluster 10, proposes to interconnect a 80.8 megawatt (MW) (net output) Wind Turbine generation facility to Delta Switching Yard-Tesla 230kV Line in Alameda County, California. The project has a contractual In-service date of: 3/21/25 with a current planned In-service date of: 10/8/25 | Construction (under 10%) | 2020-08-01 |  |  | Santa Clara | PG&E: North Valley Area | Yes | N/A | T.0004673 ¦ T.0004673 | New | Generator Interconnection | Generation Interconnection | N/A | 37.8815 | N/A | 115 kV | 2025-03-03 | 2025-03-21 | 2025-10-08 | Transmission Project Review Process data (Resolution E-5252 Attach B | 201 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - MMA to push out project for a few years. IC needs to submit MMA. IC not engaged for nearly a year. | Customer - Construction Delays | 1363 | 1363
Q1454 HUMMINGBIRD (MTR) | 5550876 | T.0004676 | 82Y | The Q1454 Hummingbird Energy Storage Project from Cluster 11, proposes to interconnect a 75 megawatt (MW) (net output) Battery generation facility to Metcalf 115kV in Santa Clara County, California. The project has a contractual In-service date of: 2/24/25 with a current planned In-service date of: 8/26/25 | Construction (under 10%) | 2020-08-01 |  |  | Santa Clara | PG&E: Greater Bay Area | Yes | N/A |  | New | Generator Interconnection | Generation Interconnection | N/A | N/A | N/A | 115 kV | 2025-03-03 | 2025-02-24 | 2025-08-26 | Transmission Project Review Process data (Resolution E-5252 Attach B | 183 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/05/25 - CAISO required MMA has been submitted and is under review; however, IC is exploring coming on-line without the Cap bank but delivery is expected early May. This would require further RFI and an MMA modification. PGE will submit PPI and clearance scheduled once MMAs are final. Realistic ISD is July/Aug. 04/08/25 - Still waiting on the IC to fulfill construction scope pertaining to NGR needed to safely connect to grid. MMA to delay is likely if IC delays fulfilling scope requirements. | Customer - Engineering Review | 1454 | 1454
NORTHERN ORCHARD (NU) SS BUYBACK | 5550944 | T.0001353 | 82W | The Q946 Northern Orchard Solar Project from Cluster 6, proposes to interconnect a 100 megawatt (MW) (net output) Solar + Battery generation facility to Midway-Wheeler Ridge #2 230kV Line in Kern County, California. The project has a contractual In-service date of: 5/23/24 with a current planned In-service date of: 5/23/24 | Engineering more than 50% complete | N/A |  |  | Brisbane, San Mateo ¦ Daly City, San Mateo ¦ San Mateo | 0 | No | N/A |  | New | Asset Condition | New Substation | N/A | N/A | 115 | N/A | 2026-10-02 | 2024-05-23 | 2024-05-23 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | In-Service - 5/24/24 4/22/24 - SS Testing Tcom circuits did not pass. Planned ISD with Gensite May 7. At risk pending Tcom resolution. 2/5/24 - ISD planned for April 30 2024 12/18/23 - moved out the date per Amber Fields and Alfredo. TLine critical path results in May 2024 ISD worst case. 12/12/23 - Tline Work has slipped into March based on contract process. TLine is critical path. The design took a long time due to various changes in plan, shoofly, land rights. etc 11/1/23 - ISD Tracking 9/19/23 - Tline is critical path for the whole project. LLM delivery is the only risk to schedule being tracked. (2) 90 and (2) 120 foot TSPs being delivered. 07/27/23 - TL installing a WP/LDSP shoofly to help hold main project schedule primarily delayed due material lead times. Sierra Utilities say Nov for Anchor Bolts and Dec for (4) TSPs. 6/22/23 - delayed to 2024. Tline procurement is critical path. 5/16/23 - Line work impacting an adjacent tower and could trigger the tower to be replaced. TSPs must be ordered. Expecting this 1/16/24 ISD to be even later. | Customer - !Telecom! | 946 | 946
Q1120 CHESTNUT WESTSIDE METER | 5550947 | T.0004565 | 82Y | The Q1120 Castanea Project from Cluster 8, proposes to interconnect a 150 megawatt (MW) (net output) Solar + Battery generation facility to Gates 230kV in Fresno County, California. The project has a contractual In-service date of: 4/17/23 with a current planned In-service date of: 8/9/23 | Engineering more than 50% complete | N/A |  |  | Brisbane, San Mateo ¦ Daly City, San Mateo ¦ San Mateo | PG&E: North Valley Area | No | N/A | T.0007289 ¦ T.0003009 ¦ T.0003789 | New | Asset Condition | Generation Interconnection | N/A | NA | 115 | N/A | 2026-10-02 | 2023-04-17 | 2023-08-09 | Transmission Project Review Process data (Resolution E-5252 Attach B | 114 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | COD - 11/2/23 for 135MW BESS + 150MW PV In-service 8/9/23 | Customer - Bundling Dependencies | 1120 | 1120
Q965 JAVA SOLAR (MTR) | 5550948 | T.0001354 | 82Y | The Q965 Java Solar Project from Cluster 6, proposes to interconnect a 13.5 megawatt (MW) (net output) Solar generation facility to Henrietta-GWF 115kV in Kings County, California. The project has a contractual In-service date of: 9/28/22 with a current planned In-service date of: 10/12/22 | Engineering more than 50% complete | N/A |  |  | Brisbane, San Mateo ¦ Daly City, San Mateo ¦ San Mateo | PG&E: PG&E: North Valley Area Coast & PG&E: North Valley Area Bay Area | No | N/A |  | New | Asset Condition | Generation Interconnection | N/A | NA | 115 | N/A | 2026-10-02 | 2022-09-28 | 2022-10-12 | Transmission Project Review Process data (Resolution E-5252 Attach B | 14 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Customer - Bundling Dependencies
Q1242 PLUOT METERING (DA) | 5550949 | T.0005678 | 82Y | The Q1242 Pluot Project from Cluster 9, proposes to interconnect a 246.4 megawatt (MW) (net output) Solar + Battery generation facility to Gates 230kV in Fresno County, California. The project has a contractual In-service date of: 1/30/26 with a current planned In-service date of: 9/1/26 | Engineering more than 50% complete | N/A |  |  | Brisbane, San Mateo ¦ Daly City, San Mateo ¦ San Mateo | PG&E: North Valley Area | No | N/A | T.0007289 ¦ T.0006452 | Replace | Asset Condition | Age/Condition - Replace Steel Poles | N/A | NA | 115 | N/A | 2026-10-02 | 2026-01-30 | 2026-09-01 | Transmission Project Review Process data (Resolution E-5252 Attach B | 214 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - MMA approval required to extend the ISD to Q3 2026 | Customer - Project Design | 1242 | 1242
Q1243 POMEGRANATE SOLAR METER (DA) | 5550950 | T.0005679 | 82Y | The Q1243 Pomegranate Project from Cluster 9, proposes to interconnect a 249.7 megawatt (MW) (net output) Solar + Battery generation facility to Gates 230kV in Huron / Fresno County, California. The project has a contractual In-service date of: 12/15/23 with a current planned In-service date of: 9/30/25 | Engineering more than 50% complete | N/A |  |  | Brisbane, San Mateo ¦ Daly City, San Mateo ¦ San Mateo | PG&E: North Valley Area | No | N/A | T.0007289 ¦ T.0006452 | Replace | Asset Condition | Age/Condition - Replace Steel Poles | N/A | NA | 115 | N/A | 2026-10-02 | 2023-12-15 | 2025-09-30 | Transmission Project Review Process data (Resolution E-5252 Attach B | 655 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - MMA technology change completed on 4/14/25 04/08/25 - MMA submitted for Technology changes. Tracking ISD to Q1 2026. | Customer - Project Design | 1243 | 1243
Q1136 WESTLANDS ALMOND (METER) | 5550952 | T.0003752 | 82Y | The Q1136 Westlands Almond Project from Cluster 8, proposes to interconnect a 19.88 megawatt (MW) (net output) Solar generation facility to Kent SW STA 70kV in Kings County, California. The project has a contractual In-service date of: 5/31/23 with a current planned In-service date of: 7/20/23 | Engineering more than 50% complete | N/A |  |  | Brisbane, San Mateo ¦ Daly City, San Mateo ¦ San Mateo | KERN | No | N/A |  | New | Asset Condition | Generation Interconnection | N/A | N/A | 115 | N/A | 2026-10-02 | 2023-05-31 | 2023-07-20 | Transmission Project Review Process data (Resolution E-5252 Attach B | 50 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | COD - 9/7/23 for 19.88MW In-service 7/20/23 | Customer - Bundling Dependencies | 1136 | 1136
Q1139 WESTLANDS SOLAR BLUE METER | 5550953 | T.0004560 | 82Y | The Q1139 Westlands Solar Blue Project from Cluster 8, proposes to interconnect a 250 megawatt (MW) (net output) Solar + Battery generation facility to Gates 230kV in Fresno County, California. The project has a contractual In-service date of: 7/24/23 with a current planned In-service date of: 7/26/23 | Engineering more than 50% complete | N/A |  |  | Brisbane, San Mateo ¦ Daly City, San Mateo ¦ San Mateo | PG&E: North Valley Area | No | N/A | T.0007289 ¦ T.0003009 ¦ T.0003789 | New | Asset Condition | Generation Interconnection | N/A | NA | 115 | N/A | 2026-10-02 | 2023-07-24 | 2023-07-26 | Transmission Project Review Process data (Resolution E-5252 Attach B | 2 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | COD - 11/14/23 for 250MW In-service 7/26/23 | - | 1139 | 1139
Q1378 - GONZAGA WIND METERING | 5550982 | T.0004423 | 82Y | The Q1378 Gonzaga Wind Farm Project from Cluster 10, proposes to interconnect a 76.35 megawatt (MW) (net output) Wind Turbine + Battery generation facility to Los Banos 70kV in Merced County, California. The project has a contractual In-service date of: 11/1/25 with a current planned In-service date of: 12/18/25 | Engineering more than 50% complete | N/A |  |  | Brisbane, San Mateo ¦ Daly City, San Mateo ¦ San Mateo | PG&E: North Valley Area | No | N/A |  | Replace | Asset Condition | Age/Condition - Replace Steel Poles | N/A | NA | 115 | N/A | 2026-10-02 | 2025-11-01 | 2025-11-01 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - Tracking ISD to Q4 2025. Tline material ordered Oct 2024 with Q3 2025 delivery. IC Delays: At risk, IC's design not complete. Construction needs to start Q2 2025. Low confidence ISD in 2025. | Customer - Construction Delays | 1378 | 1378
Gonzaga Wind Farm | 5550982 | T.0004423 | 82W | The Q1378 Gonzaga Wind Farm Project from Cluster 10, proposes to interconnect a 76.35 megawatt (MW) (net output) Wind Turbine + Battery generation facility to Los Banos 70kV in Merced County, California. The project has a contractual In-service date of: 11/1/25 with a current planned In-service date of: 12/18/25 | Planning | 0 |  |  | N/A |  | No | N/A | N/A | Replace | Asset Condition | Age/Condition - Replace Wood Poles | N/A | #REF! | N/A | N/A | N/A | 2025-11-01 | 2025-11-01 |  | 0 | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A [See Notes] | NA |  |  | 1378 | 1378
Q1244 - PROXIMA SOLAR (MTR) | 5550999 | T.0003770 | 82Y | The Q1244 Proxima Solar Project from Cluster 9, proposes to interconnect a 300 megawatt (MW) (net output) Solar + Battery generation facility to Fink 230kV switching station in Stainslaus County, California. The project has a contractual In-service date of: 10/15/23 with a current planned In-service date of: 3/6/24 | Engineering more than 50% complete | N/A |  |  | Brisbane, San Mateo ¦ Daly City, San Mateo ¦ San Mateo | S500 | No | N/A |  | Replace | Asset Condition | Age/Condition - Replace Steel Poles | N/A | NA | 115 | N/A | 2026-10-02 | 2023-10-15 | 2024-03-06 | Transmission Project Review Process data (Resolution E-5252 Attach B | 143 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | COD - 3/18/24 for 162MW 3/6/24 - The Q1244 Proxima Solar project achieved In-Service Date (ISD) today March 6, 2024. This project will generate 300 MW of renewable PV energy and capable of 150 MW of battery storage. The project encompasses approximately 1,100 acres. Final testing of the facility is scheduled for next Wednesday March 13th, 2024 and a Commercial Operation Date letter is expected by the end of the month. To interconnect the customer project, PG&E teams engineered, permitted, tested and placed into service on March 5, 2024 a greenfield looped Switching Station (SS) 11 acres in size named Fink SS. The SS was an EPC contract type project completed through the competitive bid process. Fink SS connects to the 230 kV system approximately 4 miles north of the PG&E Quinto SS and a few miles south of the third party utility owned 230 kV substation Westley substation in Stanislaus County. To interconnect the new 230 kV SS the project called for protective relay upgrades at Los Banos, Quinto SS, and Westley Substation. The PG&E project team coordinated with Modesto Irrigation District (MID) to get the project successful. There was also telecommunications and testing coordination at Westley Substation MID teams and PG&E teams. The energization of Fink SS and Proxima occurred via radial connection. This energization test process spanned a few days to fully test the SS and the third party customer substation. There is remaining work to be completed in order to energize the Fink SS – Westley 230 kV line and is scheduled to finalize April 1, 2024. This project had many barriers to get towards completion. One of the major barriers was permitting and acquiring the land from Stanislaus County. I want to shout out @Everett, Kirsten and @Crossfield, Scott for essentially being a Stanislaus county resource and spending many days waiting at their counter or hand delivering necessary requirements to complete permitting and acquisition activities. This project kicked off in Q2 2018 with a total of over 165 different resources attending project meetings and lending their expertise throughout the project lifecycle. Thank you to everyone involved in this project and helping to bring expertise and professionalism when interacting with NextEra as well as overcome obstacles and provide a quality product. 3/4/24 -Expecting to energize Proxima on 3/6. Fink SS is 3/5. 2/5/25 - PGE Microwave scope between Mt Oso and MID's Wesley Substation cannot be started until Agreements between MID and PGE are made. Scope and Cost impacts being worked out between multi-parties. Interim solution being reviewed but may conflict with the original scope and schedule. 1/23/24 - MID delays have put IC at risk of default. They are incurring costs due to Generators of battery minimally charging. Impacting their Environmental Air Quality Permits if they keep running longer. 1/11/24 - IC does not have their CAISO letter for Permission to Test which was required to put load on Fink thus energizing both SS and Gensite. ISD moved to March after MID work is complete which would no required Q1244 as load to test Fink. 12/14/23 - IC could not get a CAISO clearance until 12/20 due to telecom commissiong, key predecessor activities, and EoY CAISO clearance congestion. Due to the late December date, the PG&E resources to backfeed the customer are insufficient to safely perform the work. 12/13/23 - PTO letter to CAISO on 12/13. Clearance for backfeed 12/20. Requires Battery Loads to Sync Sw Sta. 12/12/23 - Line Connector assemblies were ACSR and not ACSS. This results in temporary re-rate on the line until the repair can be completed. Estimated at 100 to 150K to fix. Mike Milbury and CM Kevin Withrow know the details. 12/7/23 - SCADA/EMS release planned for 12/11/23. Backfeed planned for 12/15. IC is ready to provide 120MWs of load given 24 hours of notice. Potential they can increase that. MID on a call today due to Turlock irrigation district impact.MID needs the Turlock concent to proceed to EoFeb. 11/1/23 - Verify with SQ ISD Trending to Jan 2024 12/15/23 at this time for ISD. 10/2/23 - MID is no longer critical path. Moved to the end of the sequence and affect COD only. Internal only - PM is looking at possibly pulling the ISD into December. Telecom and NERC activity impacting. 9/19/23 - MID work on the DTT on the line is critical to hit the Tline work sequence. 9/18/23 - ISD is tracking to Jan 2024. 8/21/23 - MID is asking for 25 weeks now. rebalanced the clearance so MID comes at the end. Affect COD but not ISD. 8/7/23 - ISD is likely to delay due to MID. MID asking for 20 weeks to do relay work starting in Oct. Meeting next week discuss. 07/27/23 - Schedule is the same for last note. 6/22/23 - Oct 10-20 Tline to set poles for the new SS loop in. 5/15/23 - ISD is pusing to 2024 due to SS construction. Permanent Land acquisitions still with Legal. T_line foundations installed for the loop-in. Clearance to come back in Fall. | Utility - !Telecom! | 1244 | 1244
Q1713 BIA 1 METER DA | 5551027 | T.0008538 | 82Y | The Q1713 BIA Bess 1 Project from Cluster 13, proposes to interconnect a 32 megawatt (MW) (net output) Battery generation facility to GWF SW 115kV in Kings County, California. The project has a contractual In-service date of: 4/15/24 with a current planned In-service date of: 5/22/25 | Engineering more than 50% complete | N/A |  |  | Brisbane, San Mateo ¦ Daly City, San Mateo ¦ San Mateo | N/A | No | N/A | T.0003009 ¦ T.0000043 ¦ T.0007056 ¦ T.0004255 ¦ T.0007056 ¦ T.0003016 ¦ T.0006452 ¦ T.0009177 | Replace | Asset Condition | Age/Condition - Replace Steel Poles | N/A | NA | 115 | N/A | 2026-10-02 | 2024-04-15 | 2025-05-22 | Transmission Project Review Process data (Resolution E-5252 Attach B | 402 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - The customer's control room building delay construction activities. PG&E comms depend on IC construction schedule. PM indicated July energization date | Customer + Utility - Construction Delays | 1713 | 1713
Q1593 PELICANS (DA) METER | 5551240 | T.0008735 | 82Y | The Q1593 Pelicans Jaw Hybrid Solar Project from Cluster 12, proposes to interconnect a 500 megawatt (MW) (net output) Solar + Battery generation facility to Gates-Midway 230kV Line in Kings County, California. The project has a contractual In-service date of: 8/22/27 with a current planned In-service date of: 5/1/26 | Planning | 2021-12-01 |  |  | Millbrae, San Mateo ¦ San Bruno, San Mateo ¦ San Mateo | N/A | No | 2015 | T.0007289 ¦ T.0006452 ¦ T.0008543 | Relocate | Reliability | T-Line Capacity | TBD | NA | 230 | N/A | N/A | 2026-09-22 | 2026-05-01 | Transmission Project Review Process data (Resolution E-5252 Attach B | -144 | No |  |  | Final Certified | 44025 | EIR | N/A | CPUC | N/A | CPCN: A.17-12-021 | 2017-12-28 | Approved | 2020 | 05/06/25 - MMA submitted 04/08/25 - ISD tracking May 2026 | - | 1593 | 1593
Q954 FIFTH STANDARD SOLAR (MTR) | 5551242 | T.0001403 | 82Y | The Q954 Fifth Standard Project from Cluster 6, proposes to interconnect a 150 megawatt (MW) (net output) Solar + Battery generation facility to Gates 230kV in Fresno County, California. The project has a contractual In-service date of: 2/17/23 with a current planned In-service date of: 2/17/23 | Planning | 2021-12-01 |  |  | Millbrae, San Mateo ¦ San Bruno, San Mateo ¦ San Mateo | N/A | No | 2015 |  | New | Reliability | Generation Interconnection | TBD | N/A | 230 | N/A | N/A | 2023-02-17 | 2023-02-17 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | Final Certified | 44025 | EIR | N/A | CPUC | N/A | CPCN: A.17-12-021 | 2017-12-28 | Approved | 2020 | COD - 9/12/23 for 150MW In-Service - 2/17/23 | Customer - Bundling Dependencies
Q1135 SCARLET (MTR) | 5551243 | T.0003742 | 82Y | The Q1135 Scarlet Project from Cluster 8, proposes to interconnect a 400 megawatt (MW) (net output) Solar + Battery generation facility to Tranquility SW 230kV in Fresno County, California. The project has a contractual In-service date of: 11/17/23 with a current planned In-service date of: 12/1/23 | Planning | 2021-12-01 |  |  | Millbrae, San Mateo ¦ San Bruno, San Mateo ¦ San Mateo | fsno | No | 2015 | T.0007056 ¦ T.0004255 ¦ T.0007056 ¦ T.0009177 ¦ T.0007289 ¦ T.0003009 ¦ T.0004760 ¦ T.0003792 ¦ T.0003789 ¦ T.0003016 | Relocate | Reliability | T-Line Capacity | TBD | NA | 230 | N/A | N/A | 2023-11-17 | 2023-12-01 | Transmission Project Review Process data (Resolution E-5252 Attach B | 14 | Yes |  |  | Final Certified | 44025 | EIR | N/A | CPUC | N/A | CPCN: A.17-12-021 | 2017-12-28 | Approved | 2020 | COD - 4/11/24 for 240MW Summary of commercial letters for the Scarlet Project: 1. Phase 1 (SCARLT_2_SSBSR1 - 100 MW) commercial operation letter released 02-27-24. 2. Phase 2 (SCARLT_2_SSBBT1 – 30 MW) commercial operation letter released 04-01-24. 3. Phase 3 (SCARLT_2_SSASR1 – 100 MW) commercial operation letter released 04-01-24. 4. Phase 4 (SCARLT_2_SSABT1 - 10 MW) commercial operation letter released 04-11-24. 9/7/23 - MMA received, ISD 10/4/23, CODs 2/20/24 through 10/31/25 in 7 phases. 8/7/23 - ISD scheduled Oct 4th subject to MMA being done in time. PPI is 9/20. Need the MMA by the 9/6 to move forward. MMA submitted 7/24. 7/17/23 - Need ICs test reports on time to meet dates. A customer proposed schedule needed to finalize the MMA dates. MMA not submitted- needed by Sept wk 1. PPI Sept 20. May not be achievable given the MMA timeline 6/22/23 - SEECO rep coordination is a critical issue. The IC will get the Rep back out to dial in the switches on 6/21. Inspections had issues with the ICs grounding. 5/16/23 - POCO has OPGW and Manual Switch on same TSP. Requires modification of the TSP to support these. Lesson learned not to have ICs OPGW on same structure. Should have been taken to ground 1 span sooner. 5/1/23 - 6/21/23 ISD is not likely achievable due to IC test reports delayed that were due 4/21/23. AFW needs submitted to change the clearance points all the way to tranquility since the team has to release the POCO pole switch. Ops will do a 30 day break-in. | Customer - Material
Luna Valley Solar | 5551244 | T.0004490 | 82Y | The Q1129 Luna Valley Solar Project from Cluster 8, proposes to interconnect a 200 megawatt (MW) (net output) Solar + Battery generation facility to Tranquility SW 230kV in Fresno County, California. The project has a contractual In-service date of: 6/30/25 with a current planned In-service date of: 4/7/25 | Planning | 04/07/2025 |  |  | N/A |  | No | N/A | N/A | Replace | Asset Condition | Age/Condition - Replace Wood Poles | N/A | #REF! | N/A | N/A | N/A | 2025-06-30 | 2025-04-07 |  | -84 | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A [See Notes] | NA |  |  | 1129 | 1129
Q1109 North Central Valley 1 Meter DA | 5551345 | T.0004818 | 82Y | The Q1109 North Central Valley Project from Cluster 8, proposes to interconnect a 150 megawatt (MW) (net output) Battery generation facility to Belotta 115kV in San Joaquin County, California. The project has a contractual In-service date of: 6/21/23 with a current planned In-service date of: 8/3/23 | Engineering more than 50% complete | N/A |  |  | N/A | PG&E: North Valley Area | No | N/A |  | New | Other [See Notes] | Generation Interconnection | N/A | NA | N/A | N/A | N/A | 2023-06-21 | 2023-08-03 | Transmission Project Review Process data (Resolution E-5252 Attach B | 43 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | COD - 8/24/23 for 132MW In-service 8/2/23, requires clearance to reclose once CAISO letter is received and Ops can re-clear the bus at POI | Customer - !Telecom! | 1109 | 1109
Q1455-JANUS SOLAR-METER (DA) | 5551381 | T.0006968 | 82Y | The Q1455 Janus Project from Cluster 11, proposes to interconnect a 80 megawatt (MW) (net output) Solar + Battery generation facility to Cortina 60kV in Colusa County, California. The project has a contractual In-service date of: 4/15/26 with a current planned In-service date of: 6/30/26 | Engineering more than 50% complete | N/A |  |  | N/A | PG&E: Greater Fresno Area | No | N/A | T.0007629 ¦ T.0007629 | Upgrade/Retrofit | Other [See Notes] | System Operations | N/A | NA | N/A | N/A | N/A | 2026-04-15 | 2026-06-30 | Transmission Project Review Process data (Resolution E-5252 Attach B | 76 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - Tracking ISD to Q2 2026 due to IC permitting. | Customer - Permitting (Customer) | 1455 | 1455
Contra Costa 230kV SW's 601, 603 overload | 5551485 | T.0008048 | 61X | The C11P2-NP01 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Contra Costa Substation 230kV in Contra Costa County, California. | Operational | 2025-05-01 |  |  | Antioch, Contra Costa | PG&E: North Valley Area | No | 2022 | T.0010478 ¦ 0 ¦ 0 ¦ 0 ¦ 0 | Upgrade/Retrofit | Reliability | T-Line Capacity | N/A | 19.1042 | N/A | 230 kV | 2024-10-11 | 2025-05-01 | 2025-03-12 | Transmission Project Review Process data (Resolution E-5252 Attach B | -50 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom!
Stanislaus-Melones Sw Sta-Manteca #1 115 kV Line Reconductor | 5551528 | T.0004301 | 93C | The C12P2-LDNU2 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Stanislaus-Melones Sw Sta-Manteca #1 115kV Line in San Joaquin County, California. | Operational | 2030-05-01 |  |  | Angels, Calaveras ¦ Calaveras ¦ Copperopolis CDP, Calaveras ¦ Manteca, San Joaquin ¦ Murphys CDP, Calaveras ¦ San Joaquin ¦ Stanislaus ¦ Tuolumne ¦ Vallecito CDP, Calaveras | 0 | No | N/A | T.0007445 ¦ 0 | New | Asset Condition | T-Line Capacity | N/A | NA | 115 | N/A | N/A | 2030-05-01 | 2030-05-01 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom! | Q1557, Q1904 | Q1557 | Q1904
Q1702 POTENTIA-VIRIDI 1 METER DA | 5551689 | T.0008918 | 82Y | The Q1702 Potentia-Viridi Project from Cluster 13, proposes to interconnect a 400 megawatt (MW) (net output) Wind Turbine + Solar generation facility to Tesla 500kV in San Joaquin County, California. The project has a contractual In-service date of: 3/30/28 with a current planned In-service date of: 3/30/28 | Planning | 2028-03-20 |  |  | Alameda | N/A | Yes | N/A | T.0004673 ¦ Maintenance ¦ T.0001609 ¦ T.0007288 ¦ Maintenance ¦ T.0007288 | New | Generator Interconnection | Generation Interconnection | N/A | 69.382 | N/A | 500 kV | 2026-02-09 | 2028-03-30 | 2028-03-30 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - Changed ISD to match contractual date pending PG&E and customer Project Sequencing coordination. | - | 1702 | 1702
Q1718 - GONZAGA - METER (DA) | 5551978 | T.0008968 | 82Y | The Q1718 Gonzaga Hybrid Project from Cluster 13, proposes to interconnect a 103.65 megawatt (MW) (net output) Wind Turbine + Battery generation facility to Los Banos 70kV in Merced County, California. The project has a contractual In-service date of: 11/1/25 with a current planned In-service date of: 11/3/25 | On Hold | 2021-04-27 |  |  | Rodeo CDP, Contra Costa | N/A | No | N/A | T.0003009 | Replace | Asset Condition | Age/Condition - Replace Conductor | N/A | 2.851 | 115 | N/A | 2031-01-21 | 2025-11-01 | 2025-11-03 | Transmission Project Review Process data (Resolution E-5252 Attach B | 2 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | NOC: AL 6202-E | 2021-05-26 | Approved | 2021 | 05/06/25 - Tracking ISD to Q3 2026. Connects behind Gonzaga Wind. Low confidence ISD in 2025. | - | 1718 | 1718
Q1587- KINGSROAD - METER (DA) | 5552504 | T.0009193 | 82Y | The Q1587 Kingsroad Hybrid Solar Project from Cluster 12, proposes to interconnect a 100 megawatt (MW) (net output) Solar + Battery generation facility to Arco 230kV in Kern County, California. The project has a contractual In-service date of: 12/15/25 with a current planned In-service date of: 7/24/26 | Planning | 2025-12-15 |  |  | Kern | N/A | Yes | N/A | Maintenance ¦ T.0006452 | New | Generator Interconnection | Generation Interconnection | N/A | 4.5471 | N/A | 230 kV | 2027-02-04 | 2025-12-15 | 2026-07-24 | Transmission Project Review Process data (Resolution E-5252 Attach B | 221 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - MMA needed to move out ISD. ISD TBD. IC CB on order, IC working through permitting. | - | 1587 | 1587
Estrella Substation Project | 5553459 | T.0000154 | 61A | The C14P2-NFT01 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Estrella Sub in ? County, California. | Planning | 2019-05-01 |  |  | San Luis Obispo | PG&E: North Valley Area | No | 2014 | 0 ¦ T.0010878 ¦ 0 ¦ 0 ¦ 0 ¦ 0 | New | Reliability | T-Line Capacity | N/A | 2.6839 | N/A | N/A | N/A | 2019-05-01 | 2019-05-01 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom!
Q1596 BUTTONBUSH SLR DIABLO | 5553765 | T.0007731 | 82W | The Q1596 Buttonbush Solar Hybrid Energy Center Project from Cluster 12, proposes to interconnect a 800 megawatt (MW) (net output) Solar + Battery generation facility to Midway 500kV in Kern County, California. The project has a contractual In-service date of: 11/5/26 with a current planned In-service date of: 11/5/26 | Engineering less than 50% complete | 2025-05-01 |  |  | Buttonwillow CDP, Kern | N/A | Yes | N/A | Maintenance ¦ Maintenance ¦ Maintenance ¦ T.0007289 | Upgrade/Retrofit | Generator Interconnection | Special Protection Scheme | N/A | 94.5324 | N/A | 230 kV | 2026-04-03 | 2026-11-05 | 2026-11-05 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/05/25 - MMA submitted to change ISD and Technology. With ISO for engineering review and approval. Tracking ISD in Nov 2026 | - | 1596 | 1596
Q1949 DARDEN (DA) METER | 5553828 | T.0009383 | 82Y | The Q1949 Darden Hybrid Solar Project from Cluster 14, proposes to interconnect a 1150 megawatt (MW) (net output) Solar + Battery generation facility to Los Banos-Midway 500kV #2 Line in Fresno County, California. The project has a contractual In-service date of: 2/28/31 with a current planned In-service date of: 11/18/30 | Operational | N/A |  |  | Cottonwood CDP, Shasta | N/A | No | N/A | T.0010032 ¦ T.0008543 ¦ T.0001650 ¦ T.0009194 ¦ T.0010787 ¦ T.0010836 ¦ T.0004292 | Replace | Emergency Event | Age/Condition - Replace Relays | N/A | N/A | N/A | 115 kV | 2024-01-11 | 2031-02-28 | 2030-11-18 | Transmission Project Review Process data (Resolution E-5252 Attach B | -102 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - Customer wants to move date forward. Earliest backfeed Q1, 2031 pending mitigations for Network Upgrades, C14P2-FGR04 - Los Banos 500 kV circuit breakers 822, 832 & 842 overstress, Q1 2031 ISD, C14P1-KGR11 - Midway 500 kV CB 742, 912, 942 Overstress beyond 50 kA Q1 2031 ISD. PG&E will uprate Midway breakers and Los Banos Breakers CB822 & 832 and must replacce CB842. Breaker ordered by Material Purchase Program. ISDs to be determined once design is complete. 04/08/25 - Tracking ISD to Q3 2030 with no current delays | Customer - Material | 1949 | 1949
Estrella Substation Project | 5554009 | T.0000154 | 60X | The C14P2-NFT01 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Estrella Sub in ? County, California. | Planning | 2019-05-01 |  |  | El Paso de Robles, San Luis Obispo ¦ San Luis Obispo ¦ San Miguel CDP, San Luis Obispo | PG&E: North Valley Area | No | 2014 | 0 ¦ T.0010878 ¦ 0 ¦ 0 ¦ 0 ¦ 0 | New | Reliability | T-Line Capacity | N/A | NA | 70 | N/A | N/A | 2019-05-01 | 2019-05-01 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom! | Q1831, Q1959, Q1983, Q2010, Q2012, Q2013 | Q1831 | Q1959 | Q1983 | Q2010 | Q2012 | Q2013
Estrella Substation Project | 5554010 | T.0000154 | 60X | The C14P2-NFT01 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Estrella Sub in ? County, California. | Planning | 2019-05-01 |  |  | El Paso de Robles, San Luis Obispo ¦ San Luis Obispo ¦ San Miguel CDP, San Luis Obispo | PG&E: North Valley Area | No | 2014 | 0 ¦ T.0010878 ¦ 0 ¦ 0 ¦ 0 ¦ 0 | New | Reliability | T-Line Capacity | N/A | NA | 70 | N/A | N/A | 2019-05-01 | 2019-05-01 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom! | Q1831, Q1959, Q1983, Q2010, Q2012, Q2013 | Q1831 | Q1959 | Q1983 | Q2010 | Q2012 | Q2013
Estrella Substation Project | 5554011 | T.0000154 | 60C | The C14P2-NFT01 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Estrella Sub in ? County, California. | Planning | 2019-05-01 |  |  | El Paso de Robles, San Luis Obispo ¦ San Luis Obispo ¦ San Miguel CDP, San Luis Obispo | PG&E: North Valley Area | No | 2014 | 0 ¦ T.0010878 ¦ 0 ¦ 0 ¦ 0 ¦ 0 | New | Reliability | T-Line Capacity | 9.9 | NA | 70 | N/A | N/A | 2022-02-15 | 2022-02-15 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom! | Q1831, Q1959, Q1983, Q2010, Q2012, Q2013 | Q1831 | Q1959 | Q1983 | Q2010 | Q2012 | Q2013
Q1949 DARDEN (NU) SS BUYBACK | 5554012 | T.0009383 | 82W | The Q1949 Darden Hybrid Solar Project from Cluster 14, proposes to interconnect a 1150 megawatt (MW) (net output) Solar + Battery generation facility to Los Banos-Midway 500kV #2 Line in Fresno County, California. The project has a contractual In-service date of: 2/28/31 with a current planned In-service date of: 11/18/30 | Engineering more than 50% complete | 2028-08-01 |  |  | Fresno | N/A | Yes | N/A | T.0010032 ¦ T.0008543 ¦ T.0001650 ¦ T.0009194 ¦ T.0010787 ¦ T.0010836 ¦ T.0004292 | New | Generator Interconnection | New Substation | N/A | 77.6619 | N/A | 500 kV | N/A | 2031-02-28 | 2030-11-18 | Transmission Project Review Process data (Resolution E-5252 Attach B | -102 | No |  |  | N/A |  | N/A | N/A | CEC | N/A | NOC |  | N/A [See Notes] |  | 05/06/25 - Customer wants to move date forward. Earliest backfeed Q1, 2031 pending mitigations for Network Upgrades, C14P2-FGR04 - Los Banos 500 kV circuit breakers 822, 832 & 842 overstress, Q1 2031 ISD, C14P1-KGR11 - Midway 500 kV CB 742, 912, 942 Overstress beyond 50 kA Q1 2031 ISD. PG&E will uprate Midway breakers and Los Banos Breakers CB822 & 832 and must replacce CB842. Breaker ordered by Material Purchase Program. ISDs to be determined once design is complete. 04/08/25 - Tracking ISD to Q3 2030 with no current delays | Customer - Material | 1949 | 1949
Q1728 -Zeta - Meter (DA) | 5555378 | T.0009846 | 82Y | The Q1728 Zeta Project from Cluster 13, proposes to interconnect a 75 megawatt (MW) (net output) Solar + Battery generation facility to Mercy Springs SW 70kV in Merced County, California. The project has a contractual In-service date of: 3/9/27 with a current planned In-service date of: 5/26/27 | Planning | 2027-03-09 |  |  | Merced | N/A | Yes | N/A | T.0003009 ¦ T.0000157 | New | Generator Interconnection | Generation Interconnection | N/A | N/A | N/A | 70 kV | 2027-01-04 | 2027-03-09 | 2027-03-09 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - Tracking ISD Q2 2027. Potential Impact due to TPP PNU Oro Loma 70kV Reinforcement dependency with Q1 2028 ISD. | - | 1728 | 1728
Q1223-DAYLIGHT-MTR DA | 5555509 | T.0009863 | 82Y | The Q1223 Daylight Project Project from Cluster 9, proposes to interconnect a 300 megawatt (MW) (net output) Solar + Battery generation facility to Mustang SW 230kV in Kings County, California. The project has a contractual In-service date of: 11/19/27 with a current planned In-service date of: 12/23/27 | Planning | 2027-11-19 |  |  | Fresno | N/A | Yes | N/A | T.0007289 ¦ T.0006452 | New | Generator Interconnection | Generation Interconnection | N/A | N/A | N/A | 230 kV | 2027-12-07 | 2027-11-19 | 2027-11-19 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - Tracking ISD to Q3 2027 | - | 1223 | 1223
Q1379 HEARTLAND SOLAR 1 (DA) METER | 5555654 | T.0009923 | 82Y | The Q1379 Heartland 1 Project from Cluster 10, proposes to interconnect a 150 megawatt (MW) (net output) Solar generation facility to Tranquility SW 230kV in Fresno County, California. The project has a contractual In-service date of: 4/30/28 with a current planned In-service date of: 11/7/28 | Planning | 2028-04-30 |  |  | Fresno | N/A | Yes | N/A | T.0006452 | New | Generator Interconnection | Generation Interconnection | N/A | 19.3832 | N/A | 230 kV | 2028-04-24 | 2028-04-30 | 2028-04-30 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - Tracking ISD to Q3/Q4 2028. LLM (CBs) in July 2026. The IC team is still in beginning stages of design. | Utility - Bundling Dependencies | 1379 | 1379
Q1380 HEARTLAND (DA) METER | 5555739 | T.0009924 | 82Y | The Q1380 Heartland 2 Project from Cluster 10, proposes to interconnect a 150 megawatt (MW) (net output) Solar generation facility to Tranquility SW 230kV in Fresno County, California. The project has a contractual In-service date of: 4/30/28 with a current planned In-service date of: 10/25/28 | Planning | 2027-04-30 |  |  | Fresno | N/A | Yes | N/A | T.0006452 | New | Generator Interconnection | Generation Interconnection | N/A | N/A | N/A | 230 kV | 2028-06-07 | 2028-04-30 | 2028-04-30 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - Tracking ISD to Q3/Q4 2028. LLM (CBs) in July 2026. The IC team is still in beginning stages of design. | Utility - Material | 1380 | 1380
Q1443 ANGELA METER DA | 5555930 | T.0006847 | 82Y | The Q1443 Angela (Angiola East) Project from Cluster 11, proposes to interconnect a 40 megawatt (MW) (net output) Solar + Battery generation facility to Olive SW 115kV in Tulare County, California. The project has a contractual In-service date of: 10/15/25 with a current planned In-service date of: 12/17/25 | Engineering more than 50% complete | N/A |  |  | N/A | N/A | No | N/A | T.0006452 ¦ Maintenance | New | Other [See Notes] | System Operations | N/A | NA | N/A | N/A | N/A | 2025-10-15 | 2025-10-15 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - MMA submitted, ISD 10/15/2025, COD 12/15/2025. Tracking ISD in Dec 2025. IC design is delayed. IC in construction at risk to complete in 2025 | Customer - Customer Action | 1443 | 1443
Q1744-CRYSTAL FLATS-MTR DA | 5556010 | T.0010025 | 82Y | The Q1744 Crystal Flats Project from Cluster 13, proposes to interconnect a 100 megawatt (MW) (net output) Solar + Battery generation facility to Lamont 115kV in Kern County, California. The project has a contractual In-service date of: 10/12/30 with a current planned In-service date of: 10/12/30 | Engineering more than 50% complete | N/A |  |  | Fresno ¦ Fresno, Fresno ¦ Madera ¦ Madera Ranchos CDP, Madera ¦ Rolling Hills CDP, Madera | N/A | No | N/A | T.0003009 ¦ Maintenance ¦ T.0001650 ¦ T.0004292 ¦ T.0006452 ¦ T.0010032 ¦ T.0010031 ¦ T.0007722 ¦ Maintenance | Relocate | Work Requested by Others | Facility Relocation | 2 | N/A | 70 | N/A | 2025-11-10 | 2030-10-12 | 2030-10-12 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - IC non-responsive to meetings. ISD shown is IA ISD. Real ISD TBD. | Customer - Non-Responsive | 1744 | 1744
Q1593 PELICANS (RNU) SS - BUYBACK | 5556900 | T.0008735 | 82W | The Q1593 Pelicans Jaw Hybrid Solar Project from Cluster 12, proposes to interconnect a 500 megawatt (MW) (net output) Solar + Battery generation facility to Gates-Midway 230kV Line in Kings County, California. The project has a contractual In-service date of: 8/22/27 with a current planned In-service date of: 5/1/26 | Planning | N/A |  |  | N/A | N/A | No | N/A | T.0007289 ¦ T.0006452 ¦ T.0008543 | New | Asset Condition | New Substation | N/A | NA | N/A | N/A | N/A | 2026-09-22 | 2026-05-01 | Transmission Project Review Process data (Resolution E-5252 Attach B | -144 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - MMA submitted 04/08/25 - ISD tracking May 2026 | - | 1593 | 1593
Q1389 REDUX GEN SITE_METER (DA) | 5557009 | T.0007971 | 82Y | The Q1389 Redux Solar Project from Cluster 10, proposes to interconnect a 125 megawatt (MW) (net output) Solar + Battery generation facility to Gates 230kV in Fresno County, California. The project has a contractual In-service date of: 12/2/24 with a current planned In-service date of: 8/21/26 | Planning | N/A |  |  | N/A | 0 | No | N/A | Maintenance ¦ T.0007289 ¦ T.0006452 | Replace | Asset Condition | Age/Condition - Replace Relays | N/A | NA | N/A | N/A | N/A | 2024-12-02 | 2026-08-21 | Transmission Project Review Process data (Resolution E-5252 Attach B | 627 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/05/25 - MMA submitted for ISD and technology changes. Tracking ISD to Q2 2026. Customer moved POCO pole location multiple times. Customer started gentie route design. Customer submitted IDP and accepted. Customer's POCO location changes delayed PG&E's T-line design which includes 5 spans, 2 H frames, 2 TSPs. | - | 1389 | 1389
Q1260 KYAN-METER-DA | 5558852 | T.0010617 | 82Y | The Q1260 Kyan Solar Project from Cluster 9, proposes to interconnect a 100 megawatt (MW) (net output) Solar generation facility to BitterWater Sw Sta in Kern County, California. The project has a contractual In-service date of: 3/30/29 with a current planned In-service date of: 7/31/27 | Planning | 0 |  |  | N/A |  | No | N/A | N/A | Replace | Asset Condition | Age/Condition - Replace Wood Poles | N/A | #REF! | N/A | N/A | N/A | 2029-03-30 | 2027-07-31 |  | -608 | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A [See Notes] | NA |  |  | 1260 | 1260
Rio Oso Substation 115 kV circuit breakers 412, 422, 482, 522 and 542 overstress | 5726234 | T.0000614 | 61Z | The C12P1-NPT03 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Rio Oso Substation 115kV in Sutter County, California. | Construction (over 75%) | 2009-05-01 |  |  | Sutter | PG&E: North Valley Area | No | 2007 | 0 ¦ 0 | Upgrade/Retrofit | Reliability | T-Line Capacity | N/A | 9.3219 | N/A | 230 ¦ 115 kV | 2022-07-05 | 2009-05-01 | 2025-04-18 | Transmission Project Review Process data (Resolution E-5252 Attach B | 5831 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/08/25 - all overstressed breakers online with the exception of CB412. which is on track to be replaced by 06/02/25. | Utility - !Telecom! | Q1687, Q1871 | Q1687 | Q1871
Rio Oso Substation 115 kV circuit breakers 412, 422, 482, 522 and 542 overstress | 5732693 | T.0000614 | 67A | The C12P1-NPT03 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Rio Oso Substation 115kV in Sutter County, California. | Operational | 2019-12-02 |  |  | Sutter | PG&E: North Valley Area | No | N/A | 0 ¦ 0 | New | Other [See Notes] | T-Line Capacity | N/A | 9.3219 | N/A | 230 kV | 2022-12-06 | 2019-12-02 | 2024-12-29 | Transmission Project Review Process data (Resolution E-5252 Attach B | 1854 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/08/25 - all overstressed breakers online with the exception of CB412. which is on track to be replaced by 06/02/25. | Utility - !Telecom! | Q1687, Q1871 | Q1687 | Q1871
Rio Oso Substation 115 kV circuit breakers 412, 422, 482, 522 and 542 overstress | 5732785 | T.0000614 | 94D | The C12P1-NPT03 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Rio Oso Substation 115kV in Sutter County, California. | Operational | 2019-12-02 |  |  | Sutter | 0 | No | N/A | 0 ¦ 0 | Upgrade/Retrofit | Reliability | T-Line Capacity | N/A | 9.3219 | N/A | 230 kV | 2022-08-25 | 2019-12-02 | 2024-12-29 | Transmission Project Review Process data (Resolution E-5252 Attach B | 1854 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/08/25 - all overstressed breakers online with the exception of CB412. which is on track to be replaced by 06/02/25. | Utility - !Telecom! | Q1687, Q1871 | Q1687 | Q1871
GATES BUS SECTION "E" LINE RELOCATIONS | 5738327 | T.0006452 | 82B | The C9P2-F13-F15 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Gates 230kV in Fresno County, California. | Operational | 2023-08-15 |  |  | Fresno | N/A | Yes | N/A | T.0009863 ¦ T.0005678 ¦ T.0005679 ¦ T.0009923 ¦ T.0009924 ¦ T.0007971 ¦ T.0006953 ¦ T.0007329 ¦ T.0006952 ¦ T.0004974 ¦ T.0006847 ¦ T.0006119 ¦ T.0007165 ¦ T.0006097 ¦ 0 ¦ T.0009393 ¦ T.0009193 ¦ T.0008735 ¦ T.0010467 ¦ T.0008538 ¦ 0 ¦ 0 ¦ T.0010025 ¦ T.0010519 | New | Generator Interconnection | Generation Interconnection | N/A | N/A | 230 | N/A | 2021-03-08 | 2023-08-15 | 2021-04-20 | Transmission Project Review Process data (Resolution E-5252 Attach B | -847 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/04/23 - Energized April 2023. Castanea Line relacation reamins. Due 5/29/23 | Utility - !Telecom! | Q1223, Q1242, Q1243, Q1379, Q1380, Q1389, Q1391, Q1394, Q1397, Q1398, Q1443, Q1493, Q1495, Q1499, Q1568, Q1586, Q1587, Q1593, Q1709, Q1713, Q1736, Q1740, Q1744, Q1751 | Q1223 | Q1242 | Q1243 | Q1379 | Q1380 | Q1389 | Q1391 | Q1394 | Q1397 | Q1398 | Q1443 | Q1493 | Q1495 | Q1499 | Q1568 | Q1586 | Q1587 | Q1593 | Q1709
Rio Oso Substation 115 kV circuit breakers 412, 422, 482, 522 and 542 overstress | 5739019 | T.0000614 | 67A | The C12P1-NPT03 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Rio Oso Substation 115kV in Sutter County, California. | Operational | 2019-12-02 |  |  | Sutter | PG&E: North Valley Area | No | N/A | 0 ¦ 0 | New | Other [See Notes] | T-Line Capacity | N/A | 9.3219 | N/A | 115 kV | 2023-03-20 | 2019-12-02 | 2024-12-29 | Transmission Project Review Process data (Resolution E-5252 Attach B | 1854 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/08/25 - all overstressed breakers online with the exception of CB412. which is on track to be replaced by 06/02/25. | Utility - !Telecom! | Q1687, Q1871 | Q1687 | Q1871
Rio Oso Substation 115 kV circuit breakers 412, 422, 482, 522 and 542 overstress | 5740958 | T.0000614 | 94D | The C12P1-NPT03 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Rio Oso Substation 115kV in Sutter County, California. | Operational | 2019-12-02 |  |  | Sutter | 0 | No | N/A | 0 ¦ 0 | Upgrade/Retrofit | Reliability | T-Line Capacity | N/A | 9.3219 | N/A | 115 kV | 2022-10-28 | 2019-12-02 | 2024-12-29 | Transmission Project Review Process data (Resolution E-5252 Attach B | 1854 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/08/25 - all overstressed breakers online with the exception of CB412. which is on track to be replaced by 06/02/25. | Utility - !Telecom! | Q1687, Q1871 | Q1687 | Q1871
Vierra 115 kV Looping Project | 5746744 | T.0000597 | 60Z | The C14P2-NPT04 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Vierra 115kV in San Joaquin County, California. | Operational | 2014-05-01 |  |  | Lathrop, San Joaquin ¦ San Joaquin ¦ Tracy, San Joaquin | PG&E: North Valley Area | No | 2011 | T.0011086 ¦ T.0010853 ¦ 0 ¦ T.0011168 ¦ 0 | Relocate | Reliability | T-Line Capacity | 2 | 1.355 | 115 | N/A | 2024-11-01 | 2014-05-01 | 2025-02-24 | Transmission Project Review Process data (Resolution E-5252 Attach B | 3952 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom!
Vierra 115 kV Looping Project | 5746745 | T.0000597 | 61G | The C14P2-NPT04 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Vierra 115kV in San Joaquin County, California. | Construction (10%-25%) | 2014-05-01 |  |  | Lathrop, San Joaquin | PG&E: North Valley Area | No | 2011 | T.0011086 ¦ T.0010853 ¦ 0 ¦ T.0011168 ¦ 0 | Upgrade/Retrofit | Reliability | T-Line Capacity | N/A | 1.355 | N/A | 115 kV | 2024-05-21 | 2014-05-01 | 2025-07-24 | Transmission Project Review Process data (Resolution E-5252 Attach B | 4102 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom! | Q1867, Q1887, Q1904, Q1920, Q1929 | Q1867 | Q1887 | Q1904 | Q1920 | Q1929
Moraga-Castro Valley 230 kV Line Capacity Increase | 5747775 | T.0004421 | 61X | The C11P2-GP01 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Moraga 230kV in Contra Costa County, California. | Operational | 2013-05-01 |  |  | Orinda, Contra Costa | PG&E: North Valley Area | No | 2011 | T.0007418 ¦ T.0010478 | Upgrade/Retrofit | Reliability | T-Line Capacity | N/A | 15.8714 | N/A | 230 kV | 2024-08-27 | 2013-05-01 | 2025-01-31 | Transmission Project Review Process data (Resolution E-5252 Attach B | 4293 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom!
Reconductor Bellota-Warnerville 230 kV Line | 5756012 | T.0000043 | 60X | The C13P1-FPT02 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Bellota-Warnerville 230kV Line in Madera County, California. | Operational | 2024-12-31 |  |  | San Joaquin | PG&E: North Valley Area | No | 2013 | T.0010467 ¦ T.0008538 ¦ T.0010817 ¦ T.0010816 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 | Upgrade/Retrofit | Policy | T-Line Capacity | 23 | NA | 230 | N/A | 2022-06-01 | 2024-12-31 | 2019-05-01 | Transmission Project Review Process data (Resolution E-5252 Attach B | -2071 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 04/04/24 - Final ISD 3/30/24 6/26/23 - B-W ISD was 04/28/2023. B-C ISD is 4/30/24 likely a $2M flex into 2024 for remaining phase. | Utility - !Telecom! | Q1709, Q1713, Q1930, Q1932, Q1933, Q1934, Q1953, Q1963, Q1970, Q1977 | Q1709 | Q1713 | Q1930 | Q1932 | Q1933 | Q1934 | Q1953 | Q1963 | Q1970 | Q1977
Reconductor Bellota-Warnerville 230 kV Line | 5756037 | T.0000043 | 61X | The C13P1-FPT02 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Bellota-Warnerville 230kV Line in Madera County, California. | Operational | 2024-12-31 |  |  | San Joaquin | PG&E: North Valley Area | No | 2013 | T.0010467 ¦ T.0008538 ¦ T.0010817 ¦ T.0010816 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 | Upgrade/Retrofit | Policy | T-Line Capacity | N/A | 14.7513 | N/A | 230 kV | 2023-01-10 | 2024-12-31 | 2023-04-28 | Transmission Project Review Process data (Resolution E-5252 Attach B | -613 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 04/04/24 - Final ISD 3/30/24 6/26/23 - B-W ISD was 04/28/2023. B-C ISD is 4/30/24 likely a $2M flex into 2024 for remaining phase. | Utility - !Telecom!
Lodi Substation 60 kV circuit breakers 12 and 22 overstress | 5756866 | T.0000303 | 64C | The C12P1-NPN02 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Lodi Substation 60kV Bus in San Joaquin County, California. | Operational | 2019-10-17 |  |  | Lodi, San Joaquin | PG&E: North Valley Area | No | N/A |  | Replace | Asset Condition | T-Line Capacity | N/A | 0.93622 | N/A | 60 kV | 2020-08-04 | 2019-10-17 | 2022-05-20 | Transmission Project Review Process data (Resolution E-5252 Attach B | 946 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom!
Q954 FIFTH STANDARD SOLAR (NU) GATES | 5757640 | T.0001403 | 82W | The Q954 Fifth Standard Project from Cluster 6, proposes to interconnect a 150 megawatt (MW) (net output) Solar + Battery generation facility to Gates 230kV in Fresno County, California. The project has a contractual In-service date of: 2/17/23 with a current planned In-service date of: 2/17/23 | Operational | 2017-12-01 |  |  | Fresno | 0 | Yes | N/A |  | New | Generator Interconnection | Generation Interconnection | N/A | N/A | N/A | 230 kV | 2019-04-01 | 2023-02-17 | 2023-02-17 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | COD - 9/12/23 for 150MW In-Service - 2/17/23 | Customer - Bundling Dependencies | 954 | 954
Kern PP Substation 115 kV CBs 182, 262 and 282 overstress | 5759901 | T.0000980 | 67A | The 21rsmt-3 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Kern PP Substation 115kV in Kern County, California. | Operational | 2022-10-12 |  |  | Bakersfield, Kern | PG&E: North Valley Area | No | N/A | 0 ¦ 0 ¦ 0 ¦ 0 | New | Other [See Notes] | T-Line Capacity | N/A | 37.7504 | N/A | 115 kV | 2021-08-23 | 2022-10-12 | 2025-01-09 | Transmission Project Review Process data (Resolution E-5252 Attach B | 820 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 04/23/25 - Not yet triggered by EGI. Q2001 Negotiating agreements. Project is still working through Prioritization Impacts from 2023. 04/07/25 - Project going through GRB funding. Project on schedule 11/30/23 - On-hold until 2024. Removed as PNU. | Utility - !Telecom! | Q1995, Q2001, Q2006, Q2015 | Q1995 | Q2001 | Q2006 | Q2015
Vaca Dixon Substation 230 kV Circuit Breakers 442, 452 and 462 overstress | 5761196 | T.0001609 | 64C | The C12P1-NPT04 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Vaca Dixon Substation 230kV in Solano County, California. | Engineering more than 50% complete | 2027-03-01 |  |  | Solano | PG&E: North Valley Area | No | N/A | T.0007195 ¦ T.0010478 ¦ T.0007418 ¦ T.0008063 ¦ T.0008218 ¦ T.0008918 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 | New | Asset Condition | T-Line Capacity | N/A | 42.1076 | N/A | 230 kV | 2026-04-06 | 2027-03-01 | 2026-07-28 | Transmission Project Review Process data (Resolution E-5252 Attach B | -216 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom! | Q1270, Q1691, Q1463, Q1496, Q1444, Q1702, Q1837, Q1838, Q1840, Q1842, Q1843, Q1847, Q1854, Q1856 | Q1270 | Q1691 | Q1463 | Q1496 | Q1444 | Q1702 | Q1837 | Q1838 | Q1840 | Q1842 | Q1843 | Q1847 | Q1854 | Q1856
Wheeler Ridge Junction Substation (Casa Loma) | 5767199 | T.0000156 | 61C | The C11P2-KT01 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Wheeler Ridge Junction in Kern County, California. | Engineering more than 50% complete | 2020-05-01 |  |  | Kern | PG&E: North Valley Area | No | 2014 | 0 | New | Reliability | T-Line Capacity | N/A | 10.403 | N/A | 230 ¦ 115 kV | 2029-06-04 | 2020-05-01 | 2032-06-02 | Transmission Project Review Process data (Resolution E-5252 Attach B | 4415 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 04/23/25 - In scope development. Amber. Not Triggered yet by EGI. Project(s) parked | Utility - !Telecom!
Oro Loma 70 kV Reinforcement | 5767200 | T.0000157 | 61X | The C13P1-FPT03 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Oro Loma Substation 70kV Bus in Fresno County, California. | Engineering less than 50% complete | 2015-05-01 |  |  | Los Banos, Merced | PG&E: North Valley Area | No | 2011 | T.0009846 | Upgrade/Retrofit | Reliability | T-Line Capacity | N/A | 2.7007 | N/A | 70 kV | 2027-09-28 | 2015-05-01 | 2028-01-07 | Transmission Project Review Process data (Resolution E-5252 Attach B | 4634 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom!
Oro Loma 70 kV Reinforcement | 5767204 | T.0000157 | 60X | The C13P1-FPT03 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Oro Loma Substation 70kV Bus in Fresno County, California. | Engineering less than 50% complete | 2015-05-01 |  |  | Firebaugh, Fresno ¦ Fresno | PG&E: North Valley Area | No | 2011 | T.0009846 | Upgrade/Retrofit | Reliability | T-Line Capacity | 2.4 | NA | 70 | N/A | 2028-03-28 | 2015-05-01 | 2030-05-01 | Transmission Project Review Process data (Resolution E-5252 Attach B | 5479 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom! | Q1728 | Q1728
Estrella Substation Project | 5767207 | T.0000154 | 61C | The C14P2-NFT01 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Estrella Sub in ? County, California. | Planning | 2019-05-01 |  |  | Paso Robles, San Luis Obispo | PG&E: North Valley Area | No | 2014 | 0 ¦ T.0010878 ¦ 0 ¦ 0 ¦ 0 ¦ 0 | New | Reliability | T-Line Capacity | N/A | TBD | N/A | 70 kV | 2027-07-20 | 2019-05-01 | 2028-05-26 | Transmission Project Review Process data (Resolution E-5252 Attach B | 3313 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom!
Estrella Substation Project | 5767208 | T.0000154 | 60C | The C14P2-NFT01 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Estrella Sub in ? County, California. | Engineering more than 50% complete | 2019-05-01 |  |  | El Paso de Robles, San Luis Obispo ¦ Fresno ¦ Kings ¦ Monterey ¦ San Luis Obispo | PG&E: North Valley Area | No | 2014 | 0 ¦ T.0010878 ¦ 0 ¦ 0 ¦ 0 ¦ 0 | New | Reliability | T-Line Capacity | N/A | NA | 230 | N/A | 2026-10-01 | 2019-05-01 | 2028-05-26 | Transmission Project Review Process data (Resolution E-5252 Attach B | 3313 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom! | Q1831, Q1959, Q1983, Q2010, Q2012, Q2013 | Q1831 | Q1959 | Q1983 | Q2010 | Q2012 | Q2013
Wheeler Ridge Junction Substation (Casa Loma) | 5767215 | T.0000156 | 61C | The C11P2-KT01 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Wheeler Ridge Junction in Kern County, California. | Engineering more than 50% complete | 2020-05-01 |  |  | Kern | PG&E: North Valley Area | No | 2014 | 0 | New | Reliability | T-Line Capacity | N/A | 10.403 | N/A | 230 ¦ 115 kV | 2028-06-05 | 2020-05-01 | 2031-05-30 | Transmission Project Review Process data (Resolution E-5252 Attach B | 4046 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 04/23/25 - In scope development. Amber. Not Triggered yet by EGI. Project(s) parked | Utility - !Telecom!
Estrella Substation Project | 5767230 | T.0000154 | 60C | The C14P2-NFT01 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Estrella Sub in ? County, California. | Planning | 2019-05-01 |  |  | N/A | PG&E: North Valley Area | No | 2014 | 0 ¦ T.0010878 ¦ 0 ¦ 0 ¦ 0 ¦ 0 | New | Reliability | T-Line Capacity | N/A | NA | 230 ¦ 70 | N/A | N/A | 2019-05-01 | 2025-05-01 | Transmission Project Review Process data (Resolution E-5252 Attach B | 2192 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom! | Q1831, Q1959, Q1983, Q2010, Q2012, Q2013 | Q1831 | Q1959 | Q1983 | Q2010 | Q2012 | Q2013
Estrella Substation Project | 5767231 | T.0000154 | 60C | The C14P2-NFT01 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Estrella Sub in ? County, California. | Engineering more than 50% complete | 2019-05-01 |  |  | El Paso de Robles, San Luis Obispo | PG&E: North Valley Area | No | 2014 | 0 ¦ T.0010878 ¦ 0 ¦ 0 ¦ 0 ¦ 0 | New | Reliability | T-Line Capacity | N/A | NA | 70 | N/A | 2025-09-10 | 2019-05-01 | 2026-05-11 | Transmission Project Review Process data (Resolution E-5252 Attach B | 2567 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom! | Q1831, Q1959, Q1983, Q2010, Q2012, Q2013 | Q1831 | Q1959 | Q1983 | Q2010 | Q2012 | Q2013
Wheeler Ridge Junction Substation (Casa Loma) | 5767232 | T.0000156 | 61C | The C11P2-KT01 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Wheeler Ridge Junction in Kern County, California. | Engineering less than 50% complete | 2020-05-01 |  |  | Kern | PG&E: North Valley Area | No | 2014 | 0 | New | Reliability | T-Line Capacity | N/A | 10.403 | N/A | 230 ¦ 115 kV | 2026-05-01 | 2020-05-01 | 2029-04-05 | Transmission Project Review Process data (Resolution E-5252 Attach B | 3261 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 04/23/25 - In scope development. Amber. Not Triggered yet by EGI. Project(s) parked | Utility - !Telecom!
Wheeler Ridge Junction Substation (Casa Loma) | 5767233 | T.0000156 | 60C | The C11P2-KT01 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Wheeler Ridge Junction in Kern County, California. | Engineering less than 50% complete | 2020-05-01 |  |  | Kern | PG&E: North Valley Area | No | 2014 | 0 | New | Reliability | T-Line Capacity | N/A | 10.403 | 230 ¦ 115 | N/A | 2026-05-01 | 2020-05-01 | 2027-12-08 | Transmission Project Review Process data (Resolution E-5252 Attach B | 2777 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 04/23/25 - In scope development. Amber. Not Triggered yet by EGI. Project(s) parked | Utility - !Telecom! | Q2015 | Q2015
Wheeler Ridge Junction Substation (Casa Loma) | 5767234 | T.0000156 | 60C | The C11P2-KT01 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Wheeler Ridge Junction in Kern County, California. | Engineering less than 50% complete | 2020-05-01 |  |  | Bakersfield, Kern ¦ Fuller Acres CDP, Kern ¦ Kern | PG&E: North Valley Area | No | 2014 | 0 | Upgrade/Retrofit | Reliability | T-Line Capacity | 19.65 | NA | 115 | N/A | 2029-05-01 | 2020-05-01 | 2032-12-01 | Transmission Project Review Process data (Resolution E-5252 Attach B | 4597 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 04/23/25 - In scope development. Amber. Not Triggered yet by EGI. Project(s) parked | Utility - !Telecom! | Q2015 | Q2015
Wheeler Ridge Junction Substation (Casa Loma) | 5767235 | T.0000156 | 60C | The C11P2-KT01 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Wheeler Ridge Junction in Kern County, California. | Engineering less than 50% complete | 2020-05-01 |  |  | Bakersfield, Kern ¦ East Niles CDP, Kern ¦ Fairfax CDP, Kern ¦ Fuller Acres CDP, Kern ¦ Kern | PG&E: North Valley Area | No | 2014 | 0 | Upgrade/Retrofit | Reliability | T-Line Capacity | 18.23 | NA | 115 | N/A | 2028-03-01 | 2020-05-01 | 2032-12-01 | Transmission Project Review Process data (Resolution E-5252 Attach B | 4597 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 04/23/25 - In scope development. Amber. Not Triggered yet by EGI. Project(s) parked | Utility - !Telecom! | Q2015 | Q2015
Wheeler Ridge Junction Substation (Casa Loma) | 5767236 | T.0000156 | 60C | The C11P2-KT01 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Wheeler Ridge Junction in Kern County, California. | Engineering less than 50% complete | 2020-05-01 |  |  | Kern | PG&E: North Valley Area | No | 2014 | 0 | New | Reliability | T-Line Capacity | 6.25 | NA | 230 ¦ 115 | N/A | 2028-03-01 | 2020-05-01 | 2032-12-01 | Transmission Project Review Process data (Resolution E-5252 Attach B | 4597 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 04/23/25 - In scope development. Amber. Not Triggered yet by EGI. Project(s) parked | Utility - !Telecom! | Q2015 | Q2015
Wheeler Ridge Junction Substation (Casa Loma) | 5767237 | T.0000156 | 60C | The C11P2-KT01 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Wheeler Ridge Junction in Kern County, California. | Engineering less than 50% complete | 2020-05-01 |  |  | Bakersfield, Kern ¦ Fuller Acres CDP, Kern ¦ Kern | PG&E: North Valley Area | No | 2014 | 0 | Upgrade/Retrofit | Reliability | T-Line Capacity | 6 | NA | 115 | N/A | 2028-03-01 | 2020-05-01 | 2032-12-01 | Transmission Project Review Process data (Resolution E-5252 Attach B | 4597 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 04/23/25 - In scope development. Amber. Not Triggered yet by EGI. Project(s) parked | Utility - !Telecom! | Q2015 | Q2015
Oro Loma 70 kV Reinforcement | 5767240 | T.0000157 | 60X | The C13P1-FPT03 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Oro Loma Substation 70kV Bus in Fresno County, California. | Engineering less than 50% complete | 2015-05-01 |  |  | Fresno | PG&E: North Valley Area | No | 2011 | T.0009846 | Upgrade/Retrofit | Reliability | T-Line Capacity | 10.8 | NA | 70 | N/A | 2027-09-15 | 2015-05-01 | 2027-12-28 | Transmission Project Review Process data (Resolution E-5252 Attach B | 4624 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom! | Q1728 | Q1728
Q272 AMERICAN KINGS SOLAR T-LINE (DA) | 5767389 | T.0000674 | 82B | The Q272 American Kings Solar Project from Cluster TC, proposes to interconnect a 123 megawatt (MW) (net output) Solar + Battery generation facility to Henrietta 70kV in Kings County, California. The project has a contractual In-service date of: 4/1/20 with a current planned In-service date of: 6/8/20 | Operational | 2016-10-11 |  |  | Hanford, Kings | 0 | Yes | N/A |  | New | Generator Interconnection | Generation Interconnection | 0.14 | N/A | 70 | N/A | 2020-03-16 | 2022-02-15 | 2020-06-08 | Transmission Project Review Process data (Resolution E-5252 Attach B | -617 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | NOC: AL 5599-E | 2019-07-30 | Approved | 2019 |  | !No Data! - !No Data! | 272 | 272
Q272 AMERICAN KINGS SOLAR (DA) | 5767871 | T.0000674 | 82Y | The Q272 American Kings Solar Project from Cluster TC, proposes to interconnect a 123 megawatt (MW) (net output) Solar + Battery generation facility to Henrietta 70kV in Kings County, California. The project has a contractual In-service date of: 4/1/20 with a current planned In-service date of: 6/8/20 | Operational | 2016-10-11 |  |  | Kings | PG&E: North Valley Area | Yes | N/A |  | New | Generator Interconnection | Generation Interconnection | N/A | 7.0079 | N/A | 70 kV | 2019-10-18 | 2022-02-15 | 2020-06-08 | Transmission Project Review Process data (Resolution E-5252 Attach B | -617 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | NOC: AL 5599-E | 2019-07-30 | Approved | 2019 |  | !No Data! - !No Data! | 272 | 272
Q272 AMERICAN KINGS SOLAR (MTR) | 5768175 | T.0000674 | 82Y | The Q272 American Kings Solar Project from Cluster TC, proposes to interconnect a 123 megawatt (MW) (net output) Solar + Battery generation facility to Henrietta 70kV in Kings County, California. The project has a contractual In-service date of: 4/1/20 with a current planned In-service date of: 6/8/20 | Operational | 2016-05-31 |  |  | Sutter | PG&E: Greater Fresno Area | No | 2013 |  | Upgrade/Retrofit | Reliability | Bus Upgrade | N/A | 4.6809 | N/A | 115 kV | 2018-07-25 | 2022-02-15 | 2020-06-08 | Transmission Project Review Process data (Resolution E-5252 Attach B | -617 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | !No Data! - !No Data! | 272 | 272
Q946 NORTHERN ORCHARD (DA) GEN SITE | 5768558 | T.0001353 | 82Y | The Q946 Northern Orchard Solar Project from Cluster 6, proposes to interconnect a 100 megawatt (MW) (net output) Solar + Battery generation facility to Midway-Wheeler Ridge #2 230kV Line in Kern County, California. The project has a contractual In-service date of: 5/23/24 with a current planned In-service date of: 5/23/24 | Operational | 2018-12-01 |  |  | Kern | PG&E: Greater Bay Area | Yes | N/A |  | New | Generator Interconnection | Generation Interconnection | N/A | 94.53 | N/A | 230 kV | 2024-04-09 | 2024-05-23 | 2024-05-23 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | NOC: AL 6634-E | 2022-06-30 | Approved | 2022 | In-Service - 5/24/24 4/22/24 - SS Testing Tcom circuits did not pass. Planned ISD with Gensite May 7. At risk pending Tcom resolution. 2/5/24 - ISD planned for April 30 2024 12/18/23 - moved out the date per Amber Fields and Alfredo. TLine critical path results in May 2024 ISD worst case. 12/12/23 - Tline Work has slipped into March based on contract process. TLine is critical path. The design took a long time due to various changes in plan, shoofly, land rights. etc 11/1/23 - ISD Tracking 9/19/23 - Tline is critical path for the whole project. LLM delivery is the only risk to schedule being tracked. (2) 90 and (2) 120 foot TSPs being delivered. 07/27/23 - TL installing a WP/LDSP shoofly to help hold main project schedule primarily delayed due material lead times. Sierra Utilities say Nov for Anchor Bolts and Dec for (4) TSPs. 6/22/23 - delayed to 2024. Tline procurement is critical path. 5/16/23 - Line work impacting an adjacent tower and could trigger the tower to be replaced. TSPs must be ordered. Expecting this 1/16/24 ISD to be even later. | Customer - !Telecom! | 946 | 946
Q946 NORTHERN ORCHARD (NU) MIDWAY SUBSTA | 5768560 | T.0001353 | 82W | The Q946 Northern Orchard Solar Project from Cluster 6, proposes to interconnect a 100 megawatt (MW) (net output) Solar + Battery generation facility to Midway-Wheeler Ridge #2 230kV Line in Kern County, California. The project has a contractual In-service date of: 5/23/24 with a current planned In-service date of: 5/23/24 | Operational | 2018-12-01 |  |  | Kern | 0 | Yes | N/A |  | New | Generator Interconnection | Special Protection Scheme | N/A | 94.53 | N/A | 230 kV | 2024-04-09 | 2024-05-23 | 2024-05-23 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | NOC: AL 6634-E | 2022-06-30 | Approved | 2022 | In-Service - 5/24/24 4/22/24 - SS Testing Tcom circuits did not pass. Planned ISD with Gensite May 7. At risk pending Tcom resolution. 2/5/24 - ISD planned for April 30 2024 12/18/23 - moved out the date per Amber Fields and Alfredo. TLine critical path results in May 2024 ISD worst case. 12/12/23 - Tline Work has slipped into March based on contract process. TLine is critical path. The design took a long time due to various changes in plan, shoofly, land rights. etc 11/1/23 - ISD Tracking 9/19/23 - Tline is critical path for the whole project. LLM delivery is the only risk to schedule being tracked. (2) 90 and (2) 120 foot TSPs being delivered. 07/27/23 - TL installing a WP/LDSP shoofly to help hold main project schedule primarily delayed due material lead times. Sierra Utilities say Nov for Anchor Bolts and Dec for (4) TSPs. 6/22/23 - delayed to 2024. Tline procurement is critical path. 5/16/23 - Line work impacting an adjacent tower and could trigger the tower to be replaced. TSPs must be ordered. Expecting this 1/16/24 ISD to be even later. | Customer - !Telecom!
Q946 NORTHERN ORCHARD (NU) WHEELER RIDGE | 5768561 | T.0001353 | 82W | The Q946 Northern Orchard Solar Project from Cluster 6, proposes to interconnect a 100 megawatt (MW) (net output) Solar + Battery generation facility to Midway-Wheeler Ridge #2 230kV Line in Kern County, California. The project has a contractual In-service date of: 5/23/24 with a current planned In-service date of: 5/23/24 | Operational | 2018-12-01 |  |  | Kern | 0 | Yes | N/A |  | New | Generator Interconnection | Special Protection Scheme | N/A | N/A | N/A | 230 kV | 2024-04-08 | 2024-05-23 | 2024-05-23 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | NOC: AL 6634-E | 2022-06-30 | Approved | 2022 | In-Service - 5/24/24 4/22/24 - SS Testing Tcom circuits did not pass. Planned ISD with Gensite May 7. At risk pending Tcom resolution. 2/5/24 - ISD planned for April 30 2024 12/18/23 - moved out the date per Amber Fields and Alfredo. TLine critical path results in May 2024 ISD worst case. 12/12/23 - Tline Work has slipped into March based on contract process. TLine is critical path. The design took a long time due to various changes in plan, shoofly, land rights. etc 11/1/23 - ISD Tracking 9/19/23 - Tline is critical path for the whole project. LLM delivery is the only risk to schedule being tracked. (2) 90 and (2) 120 foot TSPs being delivered. 07/27/23 - TL installing a WP/LDSP shoofly to help hold main project schedule primarily delayed due material lead times. Sierra Utilities say Nov for Anchor Bolts and Dec for (4) TSPs. 6/22/23 - delayed to 2024. Tline procurement is critical path. 5/16/23 - Line work impacting an adjacent tower and could trigger the tower to be replaced. TSPs must be ordered. Expecting this 1/16/24 ISD to be even later. | Customer - !Telecom!
Q946 NORTHERN ORCHARD T-LINE NU | 5768562 | T.0001353 | 82B | The Q946 Northern Orchard Solar Project from Cluster 6, proposes to interconnect a 100 megawatt (MW) (net output) Solar + Battery generation facility to Midway-Wheeler Ridge #2 230kV Line in Kern County, California. The project has a contractual In-service date of: 5/23/24 with a current planned In-service date of: 5/23/24 | Operational | 2018-12-01 |  |  | Kern | 0 | Yes | N/A |  | New | Generator Interconnection | Generation Interconnection | 0.02 | N/A | 230 | N/A | 2024-02-27 | 2024-05-23 | 2024-05-23 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | NOC: AL 6634-E | 2022-06-30 | Approved | 2022 | In-Service - 5/24/24 4/22/24 - SS Testing Tcom circuits did not pass. Planned ISD with Gensite May 7. At risk pending Tcom resolution. 2/5/24 - ISD planned for April 30 2024 12/18/23 - moved out the date per Amber Fields and Alfredo. TLine critical path results in May 2024 ISD worst case. 12/12/23 - Tline Work has slipped into March based on contract process. TLine is critical path. The design took a long time due to various changes in plan, shoofly, land rights. etc 11/1/23 - ISD Tracking 9/19/23 - Tline is critical path for the whole project. LLM delivery is the only risk to schedule being tracked. (2) 90 and (2) 120 foot TSPs being delivered. 07/27/23 - TL installing a WP/LDSP shoofly to help hold main project schedule primarily delayed due material lead times. Sierra Utilities say Nov for Anchor Bolts and Dec for (4) TSPs. 6/22/23 - delayed to 2024. Tline procurement is critical path. 5/16/23 - Line work impacting an adjacent tower and could trigger the tower to be replaced. TSPs must be ordered. Expecting this 1/16/24 ISD to be even later. | Customer - !Telecom! | 946 | 946
Q946 NORTHERN ORCHARD (NU) SS OVERSIGHT | 5768563 | T.0001353 | 82W | The Q946 Northern Orchard Solar Project from Cluster 6, proposes to interconnect a 100 megawatt (MW) (net output) Solar + Battery generation facility to Midway-Wheeler Ridge #2 230kV Line in Kern County, California. The project has a contractual In-service date of: 5/23/24 with a current planned In-service date of: 5/23/24 | Operational | 2018-12-01 |  |  | Kern | 0 | Yes | N/A |  | New | Generator Interconnection | Generation Interconnection | N/A | N/A | N/A | 230 kV | 2023-02-14 | 2024-05-23 | 2024-05-23 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | NOC: AL 6634-E | 2022-06-30 | Approved | 2022 | In-Service - 5/24/24 4/22/24 - SS Testing Tcom circuits did not pass. Planned ISD with Gensite May 7. At risk pending Tcom resolution. 2/5/24 - ISD planned for April 30 2024 12/18/23 - moved out the date per Amber Fields and Alfredo. TLine critical path results in May 2024 ISD worst case. 12/12/23 - Tline Work has slipped into March based on contract process. TLine is critical path. The design took a long time due to various changes in plan, shoofly, land rights. etc 11/1/23 - ISD Tracking 9/19/23 - Tline is critical path for the whole project. LLM delivery is the only risk to schedule being tracked. (2) 90 and (2) 120 foot TSPs being delivered. 07/27/23 - TL installing a WP/LDSP shoofly to help hold main project schedule primarily delayed due material lead times. Sierra Utilities say Nov for Anchor Bolts and Dec for (4) TSPs. 6/22/23 - delayed to 2024. Tline procurement is critical path. 5/16/23 - Line work impacting an adjacent tower and could trigger the tower to be replaced. TSPs must be ordered. Expecting this 1/16/24 ISD to be even later. | Customer - !Telecom!
Q965 JAVA SOLAR (DA) | 5768565 | T.0001354 | 82Y | The Q965 Java Solar Project from Cluster 6, proposes to interconnect a 13.5 megawatt (MW) (net output) Solar generation facility to Henrietta-GWF 115kV in Kings County, California. The project has a contractual In-service date of: 9/28/22 with a current planned In-service date of: 10/12/22 | Operational | 2020-05-01 |  |  | San Joaquin | PG&E: PG&E: North Valley Area Coast & PG&E: North Valley Area Bay Area | No | 2016 |  | New | Reliability | Voltage Support | N/A | 14.7513 | N/A | 230 kV | 2018-10-31 | 2022-09-28 | 2022-10-12 | Transmission Project Review Process data (Resolution E-5252 Attach B | 14 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Customer - Bundling Dependencies | 965 | 965
Convert Midway Substation 230 kV Bus D to BAAH in order to install bus reactors & RAS | 5768786 | T.0001650 | 94D | The C13P1-KPN02 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Midway 230kV in Kern County, California. | Construction (50%-75%) | 2022-04-01 |  |  | Buttonwillow CDP, Kern | 0 | No | N/A | 0 ¦ 0 ¦ T.0010479 ¦ T.0010519 ¦ T.0010025 ¦ 0 ¦ 0 ¦ 0 ¦ T.0009383 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 | Upgrade/Retrofit | Reliability | T-Line Capacity | N/A | #REF! | N/A | 230 kV | 2021-07-08 | 2022-04-01 | 2025-10-24 | Transmission Project Review Process data (Resolution E-5252 Attach B | 1302 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 04/23/25 - Project is still working through the Prioritization Impacts from 2023 | Utility - !Telecom! | Q1740, Q1749, Q1739, Q1751, Q1744, Q1980, Q1987, Q2001, Q1949, Q1983, Q1995, Q2004, Q2006, Q2010, Q2013, Q2015 | Q1740 | Q1749 | Q1739 | Q1751 | Q1744 | Q1980 | Q1987 | Q2001 | Q1949 | Q1983 | Q1995 | Q2004 | Q2006 | Q2010 | Q2013 | Q2015
Q954 FIFTH STANDARD SOLAR (DA) GATES SUB | 5769289 | T.0001403 | 82Y | The Q954 Fifth Standard Project from Cluster 6, proposes to interconnect a 150 megawatt (MW) (net output) Solar + Battery generation facility to Gates 230kV in Fresno County, California. The project has a contractual In-service date of: 2/17/23 with a current planned In-service date of: 2/17/23 | Operational | 2017-12-01 |  |  | Fresno | PG&E: PG&E: North Valley Area Coast & PG&E: North Valley Area Bay Area | Yes | N/A |  | New | Generator Interconnection | Generation Interconnection | N/A | N/A | N/A | 230 kV | 2021-01-07 | 2023-02-17 | 2023-02-17 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | COD - 9/12/23 for 150MW In-Service - 2/17/23 | Customer - Bundling Dependencies
Rio Oso Substation 115 kV circuit breakers 412, 422, 482, 522 and 542 overstress | 5770422 | T.0000614 | 67A | The C12P1-NPT03 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Rio Oso Substation 115kV in Sutter County, California. | Construction (25%-50%) | 2019-12-02 |  |  | Butte | PG&E: North Valley Area | No | N/A | 0 ¦ 0 | New | Other [See Notes] | T-Line Capacity | N/A | 47.516 | N/A | 230 kV | 2025-02-24 | 2019-12-02 | 2025-04-16 | Transmission Project Review Process data (Resolution E-5252 Attach B | 1962 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/08/25 - all overstressed breakers online with the exception of CB412. which is on track to be replaced by 06/02/25. | Utility - !Telecom! | Q1687, Q1871 | Q1687 | Q1871
Rio Oso Substation 115 kV circuit breakers 412, 422, 482, 522 and 542 overstress | 5770425 | T.0000614 | 67A | The C12P1-NPT03 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Rio Oso Substation 115kV in Sutter County, California. | Engineering more than 50% complete | 2019-12-02 |  |  | Roseville, Placer | PG&E: North Valley Area | No | N/A | 0 ¦ 0 | New | Other [See Notes] | T-Line Capacity | N/A | 10.6984 | N/A | 230 kV | 2025-10-01 | 2019-12-02 | 2025-12-01 | Transmission Project Review Process data (Resolution E-5252 Attach B | 2191 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/08/25 - all overstressed breakers online with the exception of CB412. which is on track to be replaced by 06/02/25. | Utility - !Telecom! | Q1687, Q1871 | Q1687 | Q1871
Rio Oso Substation 115 kV circuit breakers 412, 422, 482, 522 and 542 overstress | 5770426 | T.0000614 | 67A | The C12P1-NPT03 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Rio Oso Substation 115kV in Sutter County, California. | Engineering more than 50% complete | 2019-12-02 |  |  | Sacramento, Sacramento | PG&E: North Valley Area | No | N/A | 0 ¦ 0 | New | Other [See Notes] | T-Line Capacity | N/A | 6.4413 | N/A | 230 kV | 2025-11-17 | 2019-12-02 | 2025-12-12 | Transmission Project Review Process data (Resolution E-5252 Attach B | 2202 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/08/25 - all overstressed breakers online with the exception of CB412. which is on track to be replaced by 06/02/25. | Utility - !Telecom! | Q1687, Q1871 | Q1687 | Q1871
Rio Oso Substation 115 kV circuit breakers 412, 422, 482, 522 and 542 overstress | 5770427 | T.0000614 | 67A | The C12P1-NPT03 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Rio Oso Substation 115kV in Sutter County, California. | Operational | 2019-12-02 |  |  | Woodland, Yolo | PG&E: North Valley Area | No | N/A | 0 ¦ 0 | New | Other [See Notes] | T-Line Capacity | N/A | 1.8386 | N/A | 115 kV | 2020-01-06 | 2019-12-02 | 2023-03-08 | Transmission Project Review Process data (Resolution E-5252 Attach B | 1192 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/08/25 - all overstressed breakers online with the exception of CB412. which is on track to be replaced by 06/02/25. | Utility - !Telecom! | Q1687, Q1871 | Q1687 | Q1871
Rio Oso Substation 115 kV circuit breakers 412, 422, 482, 522 and 542 overstress | 5770430 | T.0000614 | 67A | The C12P1-NPT03 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Rio Oso Substation 115kV in Sutter County, California. | Engineering more than 50% complete | 2019-12-02 |  |  | Placer | PG&E: North Valley Area | No | N/A | 0 ¦ 0 | New | Other [See Notes] | T-Line Capacity | N/A | 2.2491 | N/A | 115 kV | 2025-10-15 | 2019-12-02 | 2025-12-24 | Transmission Project Review Process data (Resolution E-5252 Attach B | 2214 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/08/25 - all overstressed breakers online with the exception of CB412. which is on track to be replaced by 06/02/25. | Utility - !Telecom! | Q1687, Q1871 | Q1687 | Q1871
Q723 LOTUS SOLAR FARM (DA | 5770488 | T.0001627 | 82Y | The Q723 Lotus Solar Farm Project from Cluster 4, proposes to interconnect a 50 megawatt (MW) (net output) Solar generation facility to Borden 70kV in Fresno County, California. The project has a contractual In-service date of: 12/1/19 with a current planned In-service date of: 2/5/20 | Operational | 2016-04-10 |  |  | Madera | PG&E: PG&E: North Valley Area Coast & PG&E: North Valley Area Bay Area | Yes | N/A |  | Upgrade/Retrofit | Generator Interconnection | Generation Interconnection | N/A | N/A | N/A | 70 kV | 2019-08-14 | 2022-02-15 | 2020-02-05 | Transmission Project Review Process data (Resolution E-5252 Attach B | -741 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | !No Data! - !No Data!
Q723 LOTUS SOLAR FARM (MTR) | 5770489 | T.0001627 | 82Y | The Q723 Lotus Solar Farm Project from Cluster 4, proposes to interconnect a 50 megawatt (MW) (net output) Solar generation facility to Borden 70kV in Fresno County, California. The project has a contractual In-service date of: 12/1/19 with a current planned In-service date of: 2/5/20 | Operational | 2020-12-31 |  |  | Vallejo, Solano | PG&E: PG&E: North Valley Area Coast & PG&E: North Valley Area Bay Area | No | N/A |  | Replace | Asset Condition | Age/Condition - Replace Insulators | N/A | N/A | N/A | 115 kV | 2021-04-16 | 2022-02-15 | 2020-02-05 | Transmission Project Review Process data (Resolution E-5252 Attach B | -741 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | !No Data! - !No Data!
Q723 LOTUS SOLAR FARM- BORDEN SUB- (NU) | 5770490 | T.0001627 | 82W | The Q723 Lotus Solar Farm Project from Cluster 4, proposes to interconnect a 50 megawatt (MW) (net output) Solar generation facility to Borden 70kV in Fresno County, California. The project has a contractual In-service date of: 12/1/19 with a current planned In-service date of: 2/5/20 | Operational | 2020-12-31 |  |  | Vallejo, Solano | PG&E: Greater Bay Area | No | N/A |  | Replace | Asset Condition | Age/Condition - Replace Insulators | N/A | N/A | N/A | 115 kV | 2021-04-16 | 2022-02-15 | 2020-02-05 | Transmission Project Review Process data (Resolution E-5252 Attach B | -741 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | !No Data! - !No Data! | 723 | 723
Q779 LOTUS SOLAR T-LINE | 5770638 | T.0001627 | 82D | The Q723 Lotus Solar Farm Project from Cluster 4, proposes to interconnect a 50 megawatt (MW) (net output) Solar generation facility to Borden 70kV in Fresno County, California. The project has a contractual In-service date of: 12/1/19 with a current planned In-service date of: 2/5/20 | Operational | 2016-04-10 |  |  | Madera | PG&E: North Valley Area | Yes | N/A |  | New | Generator Interconnection | Generation Interconnection | 2.5 | 7.1874 | 70 | N/A | 2019-12-03 | 2022-02-15 | 2020-02-05 | Transmission Project Review Process data (Resolution E-5252 Attach B | -741 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | !No Data! - !No Data! | 723 | 723
Kern PP Substation 115 kV CBs 182, 262 and 282 overstress | 5770678 | T.0000980 | 94D | The 21rsmt-3 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Kern PP Substation 115kV in Kern County, California. | Operational | 2022-10-12 |  |  | Bakersfield, Kern | 0 | No | N/A | 0 ¦ 0 ¦ 0 ¦ 0 | Upgrade/Retrofit | Reliability | T-Line Capacity | N/A | #REF! | N/A | 115 kV | 2021-10-01 | 2022-10-12 | 2025-01-09 | Transmission Project Review Process data (Resolution E-5252 Attach B | 820 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 04/23/25 - Not yet triggered by EGI. Q2001 Negotiating agreements. Project is still working through Prioritization Impacts from 2023. 04/07/25 - Project going through GRB funding. Project on schedule 11/30/23 - On-hold until 2024. Removed as PNU. | Utility - !Telecom! | Q1995, Q2001, Q2006, Q2015 | Q1995 | Q2001 | Q2006 | Q2015
Estrella Substation Project | 5771718 | T.0000154 | 60C | The C14P2-NFT01 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Estrella Sub in ? County, California. | Engineering more than 50% complete | 2019-05-01 |  |  | El Paso de Robles, San Luis Obispo | PG&E: North Valley Area | No | 2014 | 0 ¦ T.0010878 ¦ 0 ¦ 0 ¦ 0 ¦ 0 | New | Reliability | T-Line Capacity | TBD | 1.6272 | 230 | N/A | 2026-10-01 | 2019-05-01 | 2026-12-14 | Transmission Project Review Process data (Resolution E-5252 Attach B | 2784 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom! | Q1831, Q1959, Q1983, Q2010, Q2012, Q2013 | Q1831 | Q1959 | Q1983 | Q2010 | Q2012 | Q2013
Estrella Substation Project | 5771719 | T.0000154 | 60C | The C14P2-NFT01 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Estrella Sub in ? County, California. | Engineering more than 50% complete | 2019-05-01 |  |  | El Paso de Robles, San Luis Obispo | PG&E: North Valley Area | No | 2014 | 0 ¦ T.0010878 ¦ 0 ¦ 0 ¦ 0 ¦ 0 | New | Reliability | T-Line Capacity | N/A | NA | 70 | N/A | 2027-08-16 | 2019-05-01 | 2029-03-30 | Transmission Project Review Process data (Resolution E-5252 Attach B | 3621 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom! | Q1831, Q1959, Q1983, Q2010, Q2012, Q2013 | Q1831 | Q1959 | Q1983 | Q2010 | Q2012 | Q2013
Estrella Substation Project | 5771720 | T.0000154 | 61C | The C14P2-NFT01 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Estrella Sub in ? County, California. | Engineering less than 50% complete | 2019-05-01 |  |  | El Paso de Robles, San Luis Obispo | PG&E: North Valley Area | No | 2014 | 0 ¦ T.0010878 ¦ 0 ¦ 0 ¦ 0 ¦ 0 | Upgrade/Retrofit | Reliability | T-Line Capacity | N/A | 4.4097 | N/A | 230 kV | 2027-05-28 | 2019-05-01 | 2027-07-16 | Transmission Project Review Process data (Resolution E-5252 Attach B | 2998 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom! | Q1831, Q1959, Q1983, Q2010, Q2012, Q2013 | Q1831 | Q1959 | Q1983 | Q2010 | Q2012 | Q2013
Estrella Substation Project | 5771721 | T.0000154 | 61C | The C14P2-NFT01 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Estrella Sub in ? County, California. | Engineering less than 50% complete | 2019-05-01 |  |  | El Paso de Robles, San Luis Obispo | PG&E: North Valley Area | No | 2014 | 0 ¦ T.0010878 ¦ 0 ¦ 0 ¦ 0 ¦ 0 | Upgrade/Retrofit | Reliability | T-Line Capacity | N/A | 4.4097 | N/A | 230 kV | 2027-05-28 | 2019-05-01 | 2027-07-16 | Transmission Project Review Process data (Resolution E-5252 Attach B | 2998 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom!
Estrella Substation Project | 5771722 | T.0000154 | 61C | The C14P2-NFT01 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Estrella Sub in ? County, California. | Engineering more than 50% complete | 2019-05-01 |  |  | El Paso de Robles, San Luis Obispo | PG&E: North Valley Area | No | 2014 | 0 ¦ T.0010878 ¦ 0 ¦ 0 ¦ 0 ¦ 0 | Upgrade/Retrofit | Reliability | T-Line Capacity | N/A | 12.614 | N/A | 230 kV | 2027-07-01 | 2019-05-01 | 2027-07-23 | Transmission Project Review Process data (Resolution E-5252 Attach B | 3005 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom!
Kern PP Substation 115 kV CBs 182, 262 and 282 overstress | 5771732 | T.0000980 | 94A | The 21rsmt-3 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Kern PP Substation 115kV in Kern County, California. | Operational | 2022-10-12 |  |  | Bakersfield, Kern ¦ East Niles CDP, Kern ¦ Fairfax CDP, Kern ¦ Fuller Acres CDP, Kern ¦ Kern | 0 | No | N/A | 0 ¦ 0 ¦ 0 ¦ 0 | Upgrade/Retrofit | Reliability | T-Line Capacity | N/A | 37.7504 | 115 | N/A | 2021-03-08 | 2022-10-12 | 2025-03-03 | Transmission Project Review Process data (Resolution E-5252 Attach B | 873 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 04/23/25 - Not yet triggered by EGI. Q2001 Negotiating agreements. Project is still working through Prioritization Impacts from 2023. 04/07/25 - Project going through GRB funding. Project on schedule 11/30/23 - On-hold until 2024. Removed as PNU. | Utility - !Telecom! | Q1995, Q2001, Q2006, Q2015 | Q1995 | Q2001 | Q2006 | Q2015
Wheeler Ridge Junction Substation (Casa Loma) | 5771733 | T.0000156 | 61C | The C11P2-KT01 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Wheeler Ridge Junction in Kern County, California. | Planning | 2020-05-01 |  |  | Kern | PG&E: North Valley Area | No | 2014 | 0 | New | Reliability | T-Line Capacity | N/A | 10.403 | N/A | 115 kV | 2029-01-02 | 2020-05-01 | 2030-10-31 | Transmission Project Review Process data (Resolution E-5252 Attach B | 3835 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 04/23/25 - In scope development. Amber. Not Triggered yet by EGI. Project(s) parked | Utility - !Telecom!
Wheeler Ridge Junction Substation (Casa Loma) | 5771734 | T.0000156 | 61C | The C11P2-KT01 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Wheeler Ridge Junction in Kern County, California. | Planning | 2020-05-01 |  |  | Kern | PG&E: North Valley Area | No | 2014 | 0 | New | Reliability | T-Line Capacity | N/A | 10.403 | N/A | 115 kV | 2030-11-25 | 2020-05-01 | 2030-11-25 | Transmission Project Review Process data (Resolution E-5252 Attach B | 3860 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 04/23/25 - In scope development. Amber. Not Triggered yet by EGI. Project(s) parked | Utility - !Telecom!
Wheeler Ridge Junction Substation (Casa Loma) | 5771736 | T.0000156 | 61C | The C11P2-KT01 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Wheeler Ridge Junction in Kern County, California. | Planning | 2020-05-01 |  |  | Kern | PG&E: North Valley Area | No | 2014 | 0 | New | Reliability | T-Line Capacity | N/A | 10.403 | N/A | 115 kV | 2029-12-26 | 2020-05-01 | 2031-06-25 | Transmission Project Review Process data (Resolution E-5252 Attach B | 4072 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 04/23/25 - In scope development. Amber. Not Triggered yet by EGI. Project(s) parked | Utility - !Telecom!
Wheeler Ridge Junction Substation (Casa Loma) | 5771737 | T.0000156 | 61C | The C11P2-KT01 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Wheeler Ridge Junction in Kern County, California. | Engineering more than 50% complete | 2020-05-01 |  |  | Kern | PG&E: North Valley Area | No | 2014 | 0 | Upgrade/Retrofit | Reliability | T-Line Capacity | N/A | 10.403 | N/A | 230 kV | 2029-10-01 | 2020-05-01 | 2031-02-24 | Transmission Project Review Process data (Resolution E-5252 Attach B | 3951 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 04/23/25 - In scope development. Amber. Not Triggered yet by EGI. Project(s) parked | Utility - !Telecom!
Wheeler Ridge Junction Substation (Casa Loma) | 5771738 | T.0000156 | 61C | The C11P2-KT01 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Wheeler Ridge Junction in Kern County, California. | Planning | 2020-05-01 |  |  | Kern | PG&E: North Valley Area | No | 2014 | 0 | New | Reliability | T-Line Capacity | N/A | 10.403 | N/A | 230 kV | 2029-04-16 | 2020-05-01 | 2031-03-31 | Transmission Project Review Process data (Resolution E-5252 Attach B | 3986 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 04/23/25 - In scope development. Amber. Not Triggered yet by EGI. Project(s) parked | Utility - !Telecom!
Wheeler Ridge Junction Substation (Casa Loma) | 5771739 | T.0000156 | 61C | The C11P2-KT01 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Wheeler Ridge Junction in Kern County, California. | Engineering more than 50% complete | 2020-05-01 |  |  | Kern | PG&E: North Valley Area | No | 2014 | 0 | Upgrade/Retrofit | Reliability | T-Line Capacity | N/A | 10.403 | N/A | 230 kV | 2029-10-01 | 2020-05-01 | 2032-01-13 | Transmission Project Review Process data (Resolution E-5252 Attach B | 4274 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 04/23/25 - In scope development. Amber. Not Triggered yet by EGI. Project(s) parked | Utility - !Telecom!
Q1036 MUSTANG 2 (DA) GEN SITE | 5771959 | T.0002125 | 82Y | The Q1036 Mustang Two Project from Cluster 7, proposes to interconnect a 150 megawatt (MW) (net output) Solar generation facility to Mustang SW 230kV in Kings County, California. The project has a contractual In-service date of: 8/7/20 with a current planned In-service date of: 8/7/20 | Operational | 2017-07-30 |  |  | Kings | PG&E: PG&E: North Valley Area Coast & PG&E: North Valley Area Bay Area | Yes | N/A |  | Upgrade/Retrofit | Generator Interconnection | Generation Interconnection | N/A | N/A | N/A | 230 kV | 2020-08-07 | 2022-02-15 | 2020-08-07 | Transmission Project Review Process data (Resolution E-5252 Attach B | -557 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Customer - !Telecom!
Q1036 MUSTANG 2 (DA) 230 KV SS | 5771960 | T.0002125 | 82Y | The Q1036 Mustang Two Project from Cluster 7, proposes to interconnect a 150 megawatt (MW) (net output) Solar generation facility to Mustang SW 230kV in Kings County, California. The project has a contractual In-service date of: 8/7/20 with a current planned In-service date of: 8/7/20 | Operational | 2017-07-30 |  |  | Kings | PG&E: Greater Bay Area | Yes | N/A |  | New | Generator Interconnection | Generation Interconnection | N/A | 7.0079 | N/A | 230 kV | 2018-04-25 | 2022-02-15 | 2020-08-07 | Transmission Project Review Process data (Resolution E-5252 Attach B | -557 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Customer - !Telecom!
Q1032 MUSTANG 2 (MTR) | 5771961 | T.0002125 | 82Y | The Q1036 Mustang Two Project from Cluster 7, proposes to interconnect a 150 megawatt (MW) (net output) Solar generation facility to Mustang SW 230kV in Kings County, California. The project has a contractual In-service date of: 8/7/20 with a current planned In-service date of: 8/7/20 | Operational | 2017-07-30 |  |  | Kings | N/A | Yes | N/A |  | New | Generator Interconnection | Generation Interconnection | N/A | 7.0079 | N/A | 230 kV | 2018-04-25 | 2022-02-15 | 2020-08-07 | Transmission Project Review Process data (Resolution E-5252 Attach B | -557 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Customer - !Telecom!
Q1036 MUSTANG 2 (DA) T-LINE | 5771962 | T.0002125 | 82D | The Q1036 Mustang Two Project from Cluster 7, proposes to interconnect a 150 megawatt (MW) (net output) Solar generation facility to Mustang SW 230kV in Kings County, California. The project has a contractual In-service date of: 8/7/20 with a current planned In-service date of: 8/7/20 | Operational | 2017-07-30 |  |  | Kings | PG&E: North Valley Area | Yes | N/A |  | New | Generator Interconnection | Generation Interconnection | N/A | 7.0079 | N/A | 230 kV | 2018-04-25 | 2022-02-15 | 2020-08-07 | Transmission Project Review Process data (Resolution E-5252 Attach B | -557 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Customer - !Telecom! | 1036 | 1036
Q1036 MUSTANG 2 (NU) 230 KV SS | 5771963 | T.0002125 | 82W | The Q1036 Mustang Two Project from Cluster 7, proposes to interconnect a 150 megawatt (MW) (net output) Solar generation facility to Mustang SW 230kV in Kings County, California. The project has a contractual In-service date of: 8/7/20 with a current planned In-service date of: 8/7/20 | Operational | 2017-07-30 |  |  | Kings | PG&E: North Valley Area | Yes | N/A |  | New | Generator Interconnection | Generation Interconnection | N/A | N/A | N/A | 230 kV | 2018-04-25 | 2022-02-15 | 2020-08-07 | Transmission Project Review Process data (Resolution E-5252 Attach B | -557 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Customer - !Telecom! | 1036 | 1036
Q954 FIFTH STANDARD SOLAR T-LINE - DA | 5772119 | T.0001403 | 82D | The Q954 Fifth Standard Project from Cluster 6, proposes to interconnect a 150 megawatt (MW) (net output) Solar + Battery generation facility to Gates 230kV in Fresno County, California. The project has a contractual In-service date of: 2/17/23 with a current planned In-service date of: 2/17/23 | Operational | 2021-06-15 |  |  | Antioch, Contra Costa | PG&E: North Valley Area | No | N/A |  | Upgrade/Retrofit | Address Results of Protection Studies | Protection NERC Compliance | N/A | 15.1779 | N/A | 230 kV | 2020-09-01 | 2023-02-17 | 2023-02-17 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | COD - 9/12/23 for 150MW In-Service - 2/17/23 | Customer - Bundling Dependencies
Q946 NORTHERN ORCHARD (DA) SS | 5772227 | T.0001353 | 82Y | The Q946 Northern Orchard Solar Project from Cluster 6, proposes to interconnect a 100 megawatt (MW) (net output) Solar + Battery generation facility to Midway-Wheeler Ridge #2 230kV Line in Kern County, California. The project has a contractual In-service date of: 5/23/24 with a current planned In-service date of: 5/23/24 | Operational | 2018-02-01 |  |  | Alameda ¦ Contra Costa ¦ Livermore, Alameda | PG&E: Greater Bay Area | Yes | N/A |  | New | Generator Interconnection | Generation Interconnection | N/A | NA | N/A | 60 kV | 2020-10-01 | 2024-05-23 | 2024-05-23 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | In-Service - 5/24/24 4/22/24 - SS Testing Tcom circuits did not pass. Planned ISD with Gensite May 7. At risk pending Tcom resolution. 2/5/24 - ISD planned for April 30 2024 12/18/23 - moved out the date per Amber Fields and Alfredo. TLine critical path results in May 2024 ISD worst case. 12/12/23 - Tline Work has slipped into March based on contract process. TLine is critical path. The design took a long time due to various changes in plan, shoofly, land rights. etc 11/1/23 - ISD Tracking 9/19/23 - Tline is critical path for the whole project. LLM delivery is the only risk to schedule being tracked. (2) 90 and (2) 120 foot TSPs being delivered. 07/27/23 - TL installing a WP/LDSP shoofly to help hold main project schedule primarily delayed due material lead times. Sierra Utilities say Nov for Anchor Bolts and Dec for (4) TSPs. 6/22/23 - delayed to 2024. Tline procurement is critical path. 5/16/23 - Line work impacting an adjacent tower and could trigger the tower to be replaced. TSPs must be ordered. Expecting this 1/16/24 ISD to be even later. | Customer - !Telecom! | 946 | 946
Q1010 DYER SUMMIT WIND SUBSTATION (DA) | 5772228 | T.0002228 | 82Y | The Q1010 Dyer Wind Project from Cluster 7, proposes to interconnect a 35.15 megawatt (MW) (net output) Wind Turbine generation facility to Vasco-Herdlyn 60kV Line in Alameda County, California. The project has a contractual In-service date of: 3/19/21 with a current planned In-service date of: 6/4/21 | Operational | 2018-02-01 |  |  | Alameda ¦ Contra Costa ¦ Livermore, Alameda | PG&E: North Valley Area | Yes | N/A |  | New | Generator Interconnection | Generation Interconnection | N/A | N/A | N/A | 60 kV | 2020-10-01 | 2022-02-15 | 2021-06-04 | Transmission Project Review Process data (Resolution E-5252 Attach B | -256 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom! | 1010 | 1010
Q1010 DYER SUMMIT WIND HERDLYN DTT | 5772230 | T.0002228 | 82W | The Q1010 Dyer Wind Project from Cluster 7, proposes to interconnect a 35.15 megawatt (MW) (net output) Wind Turbine generation facility to Vasco-Herdlyn 60kV Line in Alameda County, California. The project has a contractual In-service date of: 3/19/21 with a current planned In-service date of: 6/4/21 | Operational | 2018-02-01 |  |  | Contra Costa | 0 | Yes | N/A |  | New | Generator Interconnection | Special Protection Scheme | N/A | N/A | N/A | 60 kV | 2020-10-01 | 2022-02-15 | 2021-06-04 | Transmission Project Review Process data (Resolution E-5252 Attach B | -256 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom! | 1010 | 1010
Q1010 DYER SUMMIT WIND LAS POSITAS DTT | 5772231 | T.0002228 | 82W | The Q1010 Dyer Wind Project from Cluster 7, proposes to interconnect a 35.15 megawatt (MW) (net output) Wind Turbine generation facility to Vasco-Herdlyn 60kV Line in Alameda County, California. The project has a contractual In-service date of: 3/19/21 with a current planned In-service date of: 6/4/21 | Operational | 2018-02-01 |  |  | Livermore, Alameda | 0 | Yes | N/A |  | New | Generator Interconnection | Special Protection Scheme | N/A | N/A | N/A | 60 kV | 2020-10-01 | 2022-02-15 | 2021-06-04 | Transmission Project Review Process data (Resolution E-5252 Attach B | -256 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom! | 1010 | 1010
FRICK SUMMIT WIND REPOWER DA SUBSTATION | 5772232 | T.0002230 | 82Y | The FrickWindRE Frick Summit Wind Repower Project from Cluster Repower, proposes to interconnect a 8.4 megawatt (MW) (net output) + generation facility to in Alameda County, California. The project has a contractual In-service date of: 10/1/20 with a current planned In-service date of: 6/4/21 | Operational | 2021-06-30 |  |  | San Jose, Santa Clara | N/A | No | 2017 |  | New | Work Requested by Others | Load Interconnection | 0.25 | N/A | 115 | N/A | 2019-05-13 | 2022-02-15 | 2021-06-04 | Transmission Project Review Process data (Resolution E-5252 Attach B | -256 | No |  |  | Final Certified | 43018 | EIR | N/A | CalTrain | N/A | NOC: AL 5442-E | 2018-12-12 | Approved | 2019 |  | Utility - !Telecom! | FrickWindRE | FrickWindRE
FRICK SUMMIT WIND REPOWER HERDLYN DTT TR | 5772233 | T.0002230 | 82W | The FrickWindRE Frick Summit Wind Repower Project from Cluster Repower, proposes to interconnect a 8.4 megawatt (MW) (net output) + generation facility to in Alameda County, California. The project has a contractual In-service date of: 10/1/20 with a current planned In-service date of: 6/4/21 | Operational | 2021-06-30 |  |  | San Jose, Santa Clara | N/A | No | 2017 |  | New | Work Requested by Others | Load Interconnection | 0.25 | N/A | 115 | N/A | 2019-05-13 | 2022-02-15 | 2021-06-04 | Transmission Project Review Process data (Resolution E-5252 Attach B | -256 | No |  |  | Final Certified | 43018 | EIR | N/A | CalTrain | N/A | NOC: AL 5442-E | 2018-12-12 | Approved | 2019 |  | Utility - !Telecom! | FrickWindRE | FrickWindRE
FRICK SUMMIT WIND REPOWER LAS POSITAS DT | 5772234 | T.0002230 | 82W | The FrickWindRE Frick Summit Wind Repower Project from Cluster Repower, proposes to interconnect a 8.4 megawatt (MW) (net output) + generation facility to in Alameda County, California. The project has a contractual In-service date of: 10/1/20 with a current planned In-service date of: 6/4/21 | Operational | 2021-06-30 |  |  | San Jose, Santa Clara | N/A | No | 2017 |  | New | Work Requested by Others | Special Protection Scheme | 0.25 | N/A | 115 | N/A | 2019-05-13 | 2022-02-15 | 2021-06-04 | Transmission Project Review Process data (Resolution E-5252 Attach B | -256 | No |  |  | Final Certified | 43018 | EIR | N/A | CalTrain | N/A | NOC: AL 5442-E | 2018-12-12 | Approved | 2019 |  | Utility - !Telecom! | FrickWindRE | FrickWindRE
Q779 WRIGHT SOLAR IC SS (NU) | 5772423 | T.0002321 | 82W | The Q779 Wright Solar Project from Cluster 4, proposes to interconnect a 200 megawatt (MW) (net output) Solar + Battery generation facility to Los Banos-Panoche #1 230kV in Merced County, California. The project has a contractual In-service date of: 12/31/19 with a current planned In-service date of: 11/2/19 | Operational | 2016-04-01 |  |  | Merced | fresno | Yes | N/A |  | New | Generator Interconnection | Generation Interconnection | N/A | N/A | N/A | 230 kV | 2019-01-02 | 2022-02-15 | 2019-11-02 | Transmission Project Review Process data (Resolution E-5252 Attach B | -836 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | NOC: AL 5318-E | 2018-06-25 | Approved | 2018 |  | Utility - !GO-851 Process! | 779 | 779
Q779 WRIGHT PANOCHE SUB DTT (NU) | 5772425 | T.0002321 | 82W | The Q779 Wright Solar Project from Cluster 4, proposes to interconnect a 200 megawatt (MW) (net output) Solar + Battery generation facility to Los Banos-Panoche #1 230kV in Merced County, California. The project has a contractual In-service date of: 12/31/19 with a current planned In-service date of: 11/2/19 | Operational | 2016-04-01 |  |  | Merced | fresno | Yes | N/A |  | New | Generator Interconnection | Special Protection Scheme | N/A | N/A | N/A | 230 kV | 2019-11-04 | 2022-02-15 | 2019-11-02 | Transmission Project Review Process data (Resolution E-5252 Attach B | -836 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | NOC: AL 5318-E | 2018-06-25 | Approved | 2018 |  | Utility - !GO-851 Process!
Q779 WRIGHT SOLAR LOS BANOS SUB (NU) | 5772426 | T.0002321 | 82W | The Q779 Wright Solar Project from Cluster 4, proposes to interconnect a 200 megawatt (MW) (net output) Solar + Battery generation facility to Los Banos-Panoche #1 230kV in Merced County, California. The project has a contractual In-service date of: 12/31/19 with a current planned In-service date of: 11/2/19 | Operational | 2016-04-01 |  |  | Merced | fresno | Yes | N/A |  | New | Generator Interconnection | Special Protection Scheme | N/A | N/A | N/A | 230 kV | 2019-01-02 | 2022-02-15 | 2019-11-02 | Transmission Project Review Process data (Resolution E-5252 Attach B | -836 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | NOC: AL 5318-E | 2018-06-25 | Approved | 2018 |  | Utility - !GO-851 Process!
Q779 WRIGHT SOLAR QUSTINE(DA) | 5772427 | T.0002321 | 82Y | The Q779 Wright Solar Project from Cluster 4, proposes to interconnect a 200 megawatt (MW) (net output) Solar + Battery generation facility to Los Banos-Panoche #1 230kV in Merced County, California. The project has a contractual In-service date of: 12/31/19 with a current planned In-service date of: 11/2/19 | Operational | 2016-04-01 |  |  | Merced | N/A | Yes | N/A |  | Upgrade/Retrofit | Generator Interconnection | Generation Interconnection | N/A | 53.2803 | N/A | 230 kV | 2019-12-01 | 2022-02-15 | 2019-11-02 | Transmission Project Review Process data (Resolution E-5252 Attach B | -836 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | NOC: AL 5318-E | 2018-06-25 | Approved | 2018 |  | Utility - !GO-851 Process! | 779 | 779
Q779 WRIGHT SOLAR QUSTINE (MTR) | 5772428 | T.0002321 | 82Y | The Q779 Wright Solar Project from Cluster 4, proposes to interconnect a 200 megawatt (MW) (net output) Solar + Battery generation facility to Los Banos-Panoche #1 230kV in Merced County, California. The project has a contractual In-service date of: 12/31/19 with a current planned In-service date of: 11/2/19 | Operational | 2016-04-01 |  |  | Merced | PG&E: Greater Bay Area | Yes | N/A |  | Upgrade/Retrofit | Generator Interconnection | Generation Interconnection | N/A | 53.2803 | N/A | 230 kV | 2019-12-01 | 2022-02-15 | 2019-11-02 | Transmission Project Review Process data (Resolution E-5252 Attach B | -836 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | NOC: AL 5318-E | 2018-06-25 | Approved | 2018 |  | Utility - !GO-851 Process! | 779 | 779
Q779 WRIGHT SOLAR T-LINE (NU) | 5772429 | T.0002321 | 82B | The Q779 Wright Solar Project from Cluster 4, proposes to interconnect a 200 megawatt (MW) (net output) Solar + Battery generation facility to Los Banos-Panoche #1 230kV in Merced County, California. The project has a contractual In-service date of: 12/31/19 with a current planned In-service date of: 11/2/19 | Operational | 2020-03-05 |  |  | Greenfield, Monterey ¦ King City, Monterey ¦ Monterey ¦ Soledad, Monterey | 0 | No | N/A |  | Upgrade/Retrofit | Reliability | T-Line Capacity | N/A | N/A | 60 | N/A | 2017-09-29 | 2022-02-15 | 2019-11-02 | Transmission Project Review Process data (Resolution E-5252 Attach B | -836 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !GO-851 Process! | 779 | 779
Q779 WRIGHT SOLAR T-LINE OPGW (NU) | 5772430 | T.0002321 | 82B | The Q779 Wright Solar Project from Cluster 4, proposes to interconnect a 200 megawatt (MW) (net output) Solar + Battery generation facility to Los Banos-Panoche #1 230kV in Merced County, California. The project has a contractual In-service date of: 12/31/19 with a current planned In-service date of: 11/2/19 | Operational | 2020-03-05 |  |  | Greenfield, Monterey ¦ King City, Monterey ¦ Monterey ¦ Soledad, Monterey | 0 | No | N/A |  | Upgrade/Retrofit | Reliability | System Design Upgrade | N/A | N/A | 60 | N/A | 2017-09-29 | 2022-02-15 | 2019-11-02 | Transmission Project Review Process data (Resolution E-5252 Attach B | -836 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !GO-851 Process! | 779 | 779
Q779 WRIGHT BUY BACK | 5772690 | T.0002321 | 82W | The Q779 Wright Solar Project from Cluster 4, proposes to interconnect a 200 megawatt (MW) (net output) Solar + Battery generation facility to Los Banos-Panoche #1 230kV in Merced County, California. The project has a contractual In-service date of: 12/31/19 with a current planned In-service date of: 11/2/19 | Operational | 2016-04-01 |  |  | Merced | N/A | Yes | N/A |  | New | Generator Interconnection | New Substation | N/A | 53.2803 | N/A | 230 kV | N/A | 2022-02-15 | 2019-11-02 | Transmission Project Review Process data (Resolution E-5252 Attach B | -836 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | NOC: AL 5318-E | 2018-06-25 | Approved | 2018 |  | Utility - !GO-851 Process! | 779 | 779
Q272 AMERICAN KINGS SOLAR (NU) | 5772784 | T.0000674 | 82W | The Q272 American Kings Solar Project from Cluster TC, proposes to interconnect a 123 megawatt (MW) (net output) Solar + Battery generation facility to Henrietta 70kV in Kings County, California. The project has a contractual In-service date of: 4/1/20 with a current planned In-service date of: 6/8/20 | Operational | 2016-10-11 |  |  | Kings | 0 | Yes | N/A |  | New | Generator Interconnection | Generation Interconnection | N/A | 7.0079 | N/A | 70 kV | 2020-01-06 | 2022-02-15 | 2020-06-08 | Transmission Project Review Process data (Resolution E-5252 Attach B | -617 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | NOC: AL 5599-E | 2019-07-30 | Approved | 2019 |  | !No Data! - !No Data! | 272 | 272
Kern PP Substation 115 kV CBs 182, 262 and 282 overstress | 5773025 | T.0000980 | 67A | The 21rsmt-3 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Kern PP Substation 115kV in Kern County, California. | Construction (10%-25%) | 2022-10-12 |  |  | Bakersfield, Kern | PG&E: North Valley Area | No | N/A | 0 ¦ 0 ¦ 0 ¦ 0 | New | Other [See Notes] | T-Line Capacity | N/A | 1.7259 | N/A | 115 kV | 2023-08-21 | 2022-10-12 | 2026-04-30 | Transmission Project Review Process data (Resolution E-5252 Attach B | 1296 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 04/23/25 - Not yet triggered by EGI. Q2001 Negotiating agreements. Project is still working through Prioritization Impacts from 2023. 04/07/25 - Project going through GRB funding. Project on schedule 11/30/23 - On-hold until 2024. Removed as PNU. | Utility - !Telecom! | Q1995, Q2001, Q2006, Q2015 | Q1995 | Q2001 | Q2006 | Q2015
Q1028 LITTLE BEAR SOLAR 1 AND 2 DA | 5773242 | T.0002465 | 82Y | The Q1028_Q1029 Little Bear Solar 1 & 2 Project from Cluster 7, proposes to interconnect a 40 megawatt (MW) (net output) + generation facility to Mendota 115kV in Fresno County, California. The project has a contractual In-service date of: with a current planned In-service date of: 9/21/20 | Engineering less than 50% complete | 2020-05-01 |  |  | Bakersfield, Kern ¦ Kern ¦ Weedpatch CDP, Kern | s500 | No | 2014 |  | Upgrade/Retrofit | Reliability | T-Line Capacity | 22.4 | NA | 70 | N/A | 2029-12-07 | 2020-11-30 | 2020-09-21 | Transmission Project Review Process data (Resolution E-5252 Attach B | -70 | No |  |  | Complete |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | - | 1028_1029 | 1028_1029
Wheeler Ridge Junction Substation (Casa Loma) | 5773278 | T.0000156 | 60C | The C11P2-KT01 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Wheeler Ridge Junction in Kern County, California. | Engineering less than 50% complete | 2020-05-01 |  |  | Bakersfield, Kern ¦ Kern ¦ Weedpatch CDP, Kern | PG&E: North Valley Area | No | 2014 | 0 | Upgrade/Retrofit | Reliability | T-Line Capacity | 22.4 | NA | 70 | N/A | 2029-12-07 | 2020-05-01 | 2033-07-11 | Transmission Project Review Process data (Resolution E-5252 Attach B | 4819 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 04/23/25 - In scope development. Amber. Not Triggered yet by EGI. Project(s) parked | Utility - !Telecom!
Q1027 BLACKBRIAR (DA) GEN SITE | 5773594 | T.0002543 | 82Y | The Q1027 Blackbriar Project from Cluster 7, proposes to interconnect a 20 megawatt (MW) (net output) Battery generation facility to Gates 230kV in Fresno County, California. The project has a contractual In-service date of: 2/17/23 with a current planned In-service date of: 2/17/23 | Operational | 2020-05-01 |  |  | Brentwood, Contra Costa ¦ Contra Costa | s500 | No | 2016 |  | Relocate | Reliability | T-Line Capacity | N/A | NA | 115 | N/A | 2020-07-01 | 2023-02-17 | 2023-02-17 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | COD - 5/11/23 In-Service - 2/17/23 | Customer - Bundling Dependencies | 1027 | 1027
Kern PP Substation 115 kV CBs 182, 262 and 282 overstress | 5774637 | T.0000980 | 67A | The 21rsmt-3 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Kern PP Substation 115kV in Kern County, California. | On Hold | 2022-10-12 |  |  | Bakersfield, Kern | PG&E: North Valley Area | No | N/A | 0 ¦ 0 ¦ 0 ¦ 0 | Upgrade/Retrofit | Other [See Notes] | T-Line Capacity | N/A | 37.7504 | N/A | 115 kV | 2028-01-26 | 2022-10-12 | 2028-02-24 | Transmission Project Review Process data (Resolution E-5252 Attach B | 1961 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 04/23/25 - Not yet triggered by EGI. Q2001 Negotiating agreements. Project is still working through Prioritization Impacts from 2023. 04/07/25 - Project going through GRB funding. Project on schedule 11/30/23 - On-hold until 2024. Removed as PNU. | Utility - !Telecom! | Q1995, Q2001, Q2006, Q2015 | Q1995 | Q2001 | Q2006 | Q2015
Kern PP Substation 115 kV CBs 182, 262 and 282 overstress | 5774638 | T.0000980 | 67A | The 21rsmt-3 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Kern PP Substation 115kV in Kern County, California. | Engineering more than 50% complete | 2022-10-12 |  |  | Bakersfield, Kern | PG&E: North Valley Area | No | N/A | 0 ¦ 0 ¦ 0 ¦ 0 | Upgrade/Retrofit | Other [See Notes] | T-Line Capacity | N/A | 37.7504 | N/A | 115 kV | 2028-01-31 | 2022-10-12 | 2028-02-24 | Transmission Project Review Process data (Resolution E-5252 Attach B | 1961 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 04/23/25 - Not yet triggered by EGI. Q2001 Negotiating agreements. Project is still working through Prioritization Impacts from 2023. 04/07/25 - Project going through GRB funding. Project on schedule 11/30/23 - On-hold until 2024. Removed as PNU. | Utility - !Telecom! | Q1995, Q2001, Q2006, Q2015 | Q1995 | Q2001 | Q2006 | Q2015
Q1010 DYER SUMMIT WIND DA (METER) | 5774665 | T.0002228 | 82Y | The Q1010 Dyer Wind Project from Cluster 7, proposes to interconnect a 35.15 megawatt (MW) (net output) Wind Turbine generation facility to Vasco-Herdlyn 60kV Line in Alameda County, California. The project has a contractual In-service date of: 3/19/21 with a current planned In-service date of: 6/4/21 | Operational | 2018-01-16 |  |  | Solano | PG&E: North Valley Area | No | N/A |  | Replace | Emergency Event | Age/Condition - Replace Other Substation Equipment | N/A | 42.1076 | N/A | 230 ¦ 115 kV | 2017-11-28 | 2022-02-15 | 2021-06-04 | Transmission Project Review Process data (Resolution E-5252 Attach B | -256 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom! | 1010 | 1010
FRICK SUMMIT WIND REPOWER DA (METER | 5774666 | T.0002230 | 82Y | The FrickWindRE Frick Summit Wind Repower Project from Cluster Repower, proposes to interconnect a 8.4 megawatt (MW) (net output) + generation facility to in Alameda County, California. The project has a contractual In-service date of: 10/1/20 with a current planned In-service date of: 6/4/21 | Operational | 2018-01-16 |  |  | Solano | 0 | No | N/A |  | Replace | Emergency Event | Age/Condition - Replace Other Substation Equipment | N/A | N/A | N/A | 230 ¦ 115 kV | 2017-11-28 | 2022-02-15 | 2021-06-04 | Transmission Project Review Process data (Resolution E-5252 Attach B | -256 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom! | FrickWindRE | FrickWindRE
Lodi Substation 60 kV circuit breakers 12 and 22 overstress | 5774920 | T.0000303 | 60W | The C12P1-NPN02 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Lodi Substation 60kV Bus in San Joaquin County, California. | Operational | 2019-10-17 |  |  | Lockeford CDP, San Joaquin ¦ Lodi, San Joaquin ¦ San Joaquin ¦ Victor CDP, San Joaquin | PG&E: North Valley Area | No | N/A |  | Upgrade/Retrofit | Asset Condition | T-Line Capacity | N/A | NA | 60 | N/A | 2020-12-10 | 2019-10-17 | 2021-01-14 | Transmission Project Review Process data (Resolution E-5252 Attach B | 455 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom!
Q1127 LITTLE BEAR SOLAR 3 GENSITE DA-IC | 5774921 | T.0003005 | 82Y | The Q1127 Little Bear 3 Project from Cluster 8, proposes to interconnect a 20 megawatt (MW) (net output) Solar generation facility to Mendota 115kV in Fresno County, California. The project has a contractual In-service date of: 4/1/20 with a current planned In-service date of: 10/30/20 | Operational | 2020-04-30 |  |  | Fresno | KERN | Yes | N/A | T.0003009 ¦ T.0003792 ¦ T.0003789 ¦ T.0003016 ¦ T.0004255 ¦ T.0009177 | New | Generator Interconnection | Generation Interconnection | N/A | 10.0936 | N/A | 115 kV | 2020-02-01 | 2022-02-15 | 2020-10-30 | Transmission Project Review Process data (Resolution E-5252 Attach B | -473 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | - | 1127 | 1127
Q1127 LITTLE BEAR SOLAR 3 MTR | 5774922 | T.0003005 | 82Y | The Q1127 Little Bear 3 Project from Cluster 8, proposes to interconnect a 20 megawatt (MW) (net output) Solar generation facility to Mendota 115kV in Fresno County, California. The project has a contractual In-service date of: 4/1/20 with a current planned In-service date of: 10/30/20 | Operational | 2020-04-30 |  |  | Fresno | KERN | Yes | N/A | T.0003009 ¦ T.0003792 ¦ T.0003789 ¦ T.0003016 ¦ T.0004255 ¦ T.0009177 | New | Generator Interconnection | Generation Interconnection | N/A | 10.0936 | N/A | 115 kV | 2020-02-01 | 2022-02-15 | 2020-10-30 | Transmission Project Review Process data (Resolution E-5252 Attach B | -473 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | -
Q1127 LITTLE BEAR SOLAR 3 NU MENDOTA | 5774923 | T.0003005 | 82W | The Q1127 Little Bear 3 Project from Cluster 8, proposes to interconnect a 20 megawatt (MW) (net output) Solar generation facility to Mendota 115kV in Fresno County, California. The project has a contractual In-service date of: 4/1/20 with a current planned In-service date of: 10/30/20 | Operational | 2020-04-30 |  |  | Fresno | KERN | Yes | N/A | T.0003009 ¦ T.0003792 ¦ T.0003789 ¦ T.0003016 ¦ T.0004255 ¦ T.0009177 | New | Generator Interconnection | Generation Interconnection | N/A | 10.0936 | N/A | 115 kV | 2020-02-01 | 2022-02-15 | 2020-10-30 | Transmission Project Review Process data (Resolution E-5252 Attach B | -473 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | -
Q1128 - LITTLE BEAR SOLAR 4 DA IF | 5774958 | T.0002987 | 82Y | The Q1128 Little Bear 4 & 5 Project from Cluster 8, proposes to interconnect a 100 megawatt (MW) (net output) Solar generation facility to Mendota 115kV in Fresno County, California. The project has a contractual In-service date of: 4/1/20 with a current planned In-service date of: 10/30/20 | Operational | 2021-01-01 |  |  | Fresno | fsno | Yes | N/A | T.0003009 ¦ T.0003792 ¦ T.0003789 ¦ T.0003016 ¦ T.0004255 ¦ T.0009177 | New | Generator Interconnection | Generation Interconnection | N/A | 77.6619 | N/A | 500 ¦ 230 kV | 2022-06-13 | 2022-02-15 | 2020-10-30 | Transmission Project Review Process data (Resolution E-5252 Attach B | -473 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | - | 1128 | 1128
Q1128 - LITTLE BEAR SOLAR 4 DA MTR | 5774959 | T.0002987 | 82Y | The Q1128 Little Bear 4 & 5 Project from Cluster 8, proposes to interconnect a 100 megawatt (MW) (net output) Solar generation facility to Mendota 115kV in Fresno County, California. The project has a contractual In-service date of: 4/1/20 with a current planned In-service date of: 10/30/20 | Operational | 2021-01-01 |  |  | Fresno | PG&E: Greater Fresno Area | Yes | N/A | T.0003009 ¦ T.0003792 ¦ T.0003789 ¦ T.0003016 ¦ T.0004255 ¦ T.0009177 | New | Generator Interconnection | Generation Interconnection | N/A | N/A | N/A | 500 ¦ 230 kV | 2022-06-13 | 2022-02-15 | 2020-10-30 | Transmission Project Review Process data (Resolution E-5252 Attach B | -473 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | - | 1128 | 1128
Q1128 - LITTLE BEAR SOLAR 4 RNU MENDOTA | 5774960 | T.0002987 | 82W | The Q1128 Little Bear 4 & 5 Project from Cluster 8, proposes to interconnect a 100 megawatt (MW) (net output) Solar generation facility to Mendota 115kV in Fresno County, California. The project has a contractual In-service date of: 4/1/20 with a current planned In-service date of: 10/30/20 | Operational | 2021-01-01 |  |  | Fresno | KERN | Yes | N/A | T.0003009 ¦ T.0003792 ¦ T.0003789 ¦ T.0003016 ¦ T.0004255 ¦ T.0009177 | New | Generator Interconnection | Generation Interconnection | N/A | N/A | N/A | 500 ¦ 230 kV | 2022-06-13 | 2022-02-15 | 2020-10-30 | Transmission Project Review Process data (Resolution E-5252 Attach B | -473 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | -
QC8RAS-08 GATES 500/230 KV TRANSF. NU BK | 5774961 | T.0003009 | 82W | The C8P2-3 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Gates 230kV in Fresno County, California. | Operational | 2021-01-01 |  |  | Fresno | kern | Yes | N/A | T.0004490 ¦ T.0003744 ¦ T.0003750 ¦ T.0004565 ¦ T.0003005 ¦ T.0002987 ¦ T.0004560 ¦ T.0003743 ¦ T.0003742 ¦ T.0008538 ¦ T.0008968 ¦ T.0009846 ¦ T.0010025 ¦ T.0008967 ¦ T.0010467 ¦ 0 ¦ T.0010479 ¦ 0 ¦ 0 ¦ 0 ¦ T.0010519 ¦ 0 ¦ 0 ¦ 0 ¦ T.0010817 ¦ T.0010816 ¦ 0 ¦ 0 ¦ T.0010942 ¦ TBD ¦ T.0011060 ¦ 0 ¦ T.0011125 ¦ T.0010887 ¦ T.0010738 ¦ T.0011131 ¦ T.0010878 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 | New | Generator Interconnection | Special Protection Scheme | N/A | 77.6619 | N/A | 500 ¦ 230 kV | 2022-06-13 | 2021-01-01 | 2024-10-16 | Transmission Project Review Process data (Resolution E-5252 Attach B | 1384 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom! | Q1129, Q1143, Q1117, Q1120, Q1127, Q1128, Q1139, Q1158, Q1135, Q1713, Q1718, Q1728, Q1744, Q1750, Q1709, Q1736, Q1739, Q1740, Q1745, Q1749, Q1751, 2226-WD, 2484-WD, Q1831, Q1895, Q1928, Q1930, Q1932, Q1933, Q1934, Q1935, Q1940, Q1952, Q1953, Q1954, Q1955, Q1956, Q1958, Q1959, Q1960, Q1963, Q1966, Q1968, Q1970, Q1975, Q1977, Q1980, Q1983, Q1992, Q1994, Q1995, Q2001, Q2004, Q2010, Q2012, Q2013, Q2015 | Q1129 | Q1143 | Q1117 | Q1120 | Q1127 | Q1128 | Q1139 | Q1158 | Q1135 | Q1713 | Q1718 | Q1728 | Q1744 | Q1750 | Q1709 | Q1736 | Q1739 | Q1740 | Q1745
LOS BANOS - PADRE FLAT SS 20266: RECON - | 5774966 | T.0003016 | 82B | The C8P2-6 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Los-Banos-Padre Flat SS 230kV in Merced County, California. | Operational | 2021-09-30 |  |  | Fresno ¦ Merced | 0 | Yes | N/A | T.0003005 ¦ T.0002987 ¦ T.0003743 ¦ T.0004490 ¦ 0 ¦ T.0010467 ¦ T.0008538 ¦ T.0003742 | Upgrade/Retrofit | Generator Interconnection | T-Line Capacity | 3.7 | N/A | 230 | N/A | 2022-10-31 | 2021-09-30 | 2022-12-24 | Transmission Project Review Process data (Resolution E-5252 Attach B | 450 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | NOC: AL 6527-E | 2022-03-11 | Approved | 2022 |  | Utility - !Telecom! | Q1127, Q1128, Q1158, Q1129, Q1568, 2181-WD, Q1709, Q1713, 2226-WD, 2484-WD, Q1135 | Q1127 | Q1128 | Q1158 | Q1129 | Q1568 | 2181-WD | Q1709 | Q1713 | 2226-WD | 2484-WD | Q1135
Q954 FIFTH STANDARD SOLAR (DA) GEN SITE | 5775018 | T.0001403 | 82Y | The Q954 Fifth Standard Project from Cluster 6, proposes to interconnect a 150 megawatt (MW) (net output) Solar + Battery generation facility to Gates 230kV in Fresno County, California. The project has a contractual In-service date of: 2/17/23 with a current planned In-service date of: 2/17/23 | Operational | 2017-12-01 |  |  | Fresno | gbay | Yes | N/A |  | New | Generator Interconnection | Generation Interconnection | N/A | N/A | N/A | 230 kV | 2022-07-22 | 2023-02-17 | 2023-02-17 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | COD - 9/12/23 for 150MW In-Service - 2/17/23 | Customer - Bundling Dependencies
Q1106 - FOUNTAIN WIND DA IF | 5775138 | T.0003035 | 82Y | The Q1106 Fountain Wind Project from Cluster 8, proposes to interconnect a 200 megawatt (MW) (net output) Wind Turbine generation facility to Pit1-Cottonwood 230kV Line in Shasta County, California. The project has a contractual In-service date of: 4/30/27 with a current planned In-service date of: 9/9/27 | Planning | 2020-06-01 |  |  | Burney CDP, Shasta ¦ Cottonwood CDP, Shasta ¦ Johnson Park CDP, Shasta ¦ Millville CDP, Shasta ¦ Oak Run CDP, Shasta ¦ Round Mountain CDP, Shasta ¦ Shasta | kern | Yes | N/A | T.0009188 ¦ T.0003035 | Upgrade/Retrofit | Generator Interconnection | Generation Interconnection | N/A | 26.1945 | N/A | 230 kV | 2026-12-18 | 2027-04-30 | 2027-09-09 | Transmission Project Review Process data (Resolution E-5252 Attach B | 132 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 06/02/25 - Current ISD 2027 unachievable. Customer CEQA/EIR CEC Permit process still outstanding wiyth expectation to receive permit in August 2025. ISD depends on a GIP RAS and construction of new customer built switching station. | Customer - Permitting (Customer)
Q1106 - FOUNTAIN WIND COTTONWOOD SUB RNU | 5775140 | T.0003035 | 82W | The Q1106 Fountain Wind Project from Cluster 8, proposes to interconnect a 200 megawatt (MW) (net output) Wind Turbine generation facility to Pit1-Cottonwood 230kV Line in Shasta County, California. The project has a contractual In-service date of: 4/30/27 with a current planned In-service date of: 9/9/27 | On Hold | 2020-06-01 |  |  | Cottonwood CDP, Shasta | kern | Yes | N/A | T.0009188 ¦ T.0003035 | New | Generator Interconnection | Generation Interconnection | N/A | 26.1945 | N/A | 230 kV | 2029-06-01 | 2027-04-30 | 2027-09-09 | Transmission Project Review Process data (Resolution E-5252 Attach B | 132 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 06/02/25 - Current ISD 2027 unachievable. Customer CEQA/EIR CEC Permit process still outstanding wiyth expectation to receive permit in August 2025. ISD depends on a GIP RAS and construction of new customer built switching station. | Customer - Permitting (Customer)
Q1106 - FOUNTAIN WIND PIT #1 SUB RNU | 5775141 | T.0003035 | 82W | The Q1106 Fountain Wind Project from Cluster 8, proposes to interconnect a 200 megawatt (MW) (net output) Wind Turbine generation facility to Pit1-Cottonwood 230kV Line in Shasta County, California. The project has a contractual In-service date of: 4/30/27 with a current planned In-service date of: 9/9/27 | On Hold | 2020-06-01 |  |  | Shasta | 0 | Yes | N/A | T.0009188 ¦ T.0003035 | New | Generator Interconnection | Special Protection Scheme | N/A | 2.7679 | N/A | 230 kV | 2029-01-05 | 2027-04-30 | 2027-09-09 | Transmission Project Review Process data (Resolution E-5252 Attach B | 132 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 06/02/25 - Current ISD 2027 unachievable. Customer CEQA/EIR CEC Permit process still outstanding wiyth expectation to receive permit in August 2025. ISD depends on a GIP RAS and construction of new customer built switching station. | Customer - Permitting (Customer)
Q1106-FOUNTAIN WIND NU SS OVERSIGHT IC-B | 5775142 | T.0003035 | 82W | The Q1106 Fountain Wind Project from Cluster 8, proposes to interconnect a 200 megawatt (MW) (net output) Wind Turbine generation facility to Pit1-Cottonwood 230kV Line in Shasta County, California. The project has a contractual In-service date of: 4/30/27 with a current planned In-service date of: 9/9/27 | Engineering more than 50% complete | 2020-06-01 |  |  | Cottonwood CDP, Shasta | N/A | Yes | N/A | T.0009188 ¦ T.0003035 | New | Generator Interconnection | Generation Interconnection | N/A | 26.1945 | N/A | 230 kV | 2026-01-05 | 2027-04-30 | 2027-09-09 | Transmission Project Review Process data (Resolution E-5252 Attach B | 132 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 06/02/25 - Current ISD 2027 unachievable. Customer CEQA/EIR CEC Permit process still outstanding wiyth expectation to receive permit in August 2025. ISD depends on a GIP RAS and construction of new customer built switching station. | Customer - Permitting (Customer) | 1106 | 1106
Q1106 - FOUNTAIN WIND T-LINE RNU | 5775143 | T.0003035 | 82B | The Q1106 Fountain Wind Project from Cluster 8, proposes to interconnect a 200 megawatt (MW) (net output) Wind Turbine generation facility to Pit1-Cottonwood 230kV Line in Shasta County, California. The project has a contractual In-service date of: 4/30/27 with a current planned In-service date of: 9/9/27 | Planning | 2020-06-01 |  |  | Cottonwood CDP, Shasta | N/A | Yes | N/A | T.0009188 ¦ T.0003035 | New | Generator Interconnection | Generation Interconnection | 2 | N/A | 230 | N/A | 2028-05-26 | 2027-04-30 | 2027-09-09 | Transmission Project Review Process data (Resolution E-5252 Attach B | 132 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 06/02/25 - Current ISD 2027 unachievable. Customer CEQA/EIR CEC Permit process still outstanding wiyth expectation to receive permit in August 2025. ISD depends on a GIP RAS and construction of new customer built switching station. | Customer - Permitting (Customer) | 1106 | 1106
Q1106 - FOUNTAIN WIND QC8RAS-02 RAS (DRN | 5775144 | T.0003035 | 82W | The Q1106 Fountain Wind Project from Cluster 8, proposes to interconnect a 200 megawatt (MW) (net output) Wind Turbine generation facility to Pit1-Cottonwood 230kV Line in Shasta County, California. The project has a contractual In-service date of: 4/30/27 with a current planned In-service date of: 9/9/27 | On Hold | 2020-06-01 |  |  | Cottonwood CDP, Shasta | N/A | Yes | N/A | T.0009188 ¦ T.0003035 | New | Generator Interconnection | Special Protection Scheme | N/A | 26.1945 | N/A | 230 kV | 2026-10-01 | 2027-04-30 | 2027-09-09 | Transmission Project Review Process data (Resolution E-5252 Attach B | 132 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 06/02/25 - Current ISD 2027 unachievable. Customer CEQA/EIR CEC Permit process still outstanding wiyth expectation to receive permit in August 2025. ISD depends on a GIP RAS and construction of new customer built switching station. | Customer - Permitting (Customer) | 1106 | 1106
Q1106 - FOUNTAIN WIND COTTONWOOD 230 KV | 5775145 | T.0009188 | 82W | The C8P2-15 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Cottonwood 230kV in Shasta County, California. | Engineering more than 50% complete | 2020-06-01 |  |  | Cottonwood CDP, Shasta | N/A | Yes | N/A | T.0003035 ¦ T.0008063 ¦ 0 ¦ 0 | Replace | Generator Interconnection | Substation Capacity | N/A | 26.1945 | N/A | 230 kV | 2025-08-05 | 2020-06-01 | 2025-12-29 | Transmission Project Review Process data (Resolution E-5252 Attach B | 2037 | Yes |  |  | N/A |  | TBD | TBD | TBD | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom!
TESLA: Install 230 KV MPAC | 5776769 | T.0003456 | 67A |  | Engineering more than 50% complete | 2026-12-01 |  |  | Alameda | PG&E: North Valley Area | No | N/A | NF | New | Other [See Notes] | T-Line Capacity | N/A | 69.382 | N/A | 230 kV | 2025-10-06 | 2026-12-01 | 2028-01-11 | Transmission Project Review Process data (Resolution E-5252 Attach B | 406 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 03/17/25 - ISD Jan 2028 very achievable, 14 Breakers total for project. 5-31-23 - ISD is not realistic. It is trending into 2026. | Utility - !Telecom! | mitigated until C14 | mitigated until C14
TESLA: Install 230 KV MPAC | 5776770 | T.0003456 | 67A |  | Engineering more than 50% complete | 2026-12-01 |  |  | Alameda | PG&E: North Valley Area | No | N/A | NF | New | Other [See Notes] | T-Line Capacity | N/A | 69.382 | N/A | 230 kV | 2025-10-06 | 2026-12-01 | 2028-01-11 | Transmission Project Review Process data (Resolution E-5252 Attach B | 406 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 03/17/25 - ISD Jan 2028 very achievable, 14 Breakers total for project. 5-31-23 - ISD is not realistic. It is trending into 2026. | Utility - !Telecom! | mitigated until C14 | mitigated until C14
Rio Oso Substation 115 kV circuit breakers 412, 422, 482, 522 and 542 overstress | 5777058 | T.0000614 | 60W | The C12P1-NPT03 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Rio Oso Substation 115kV in Sutter County, California. | Construction (10%-25%) | 2009-05-01 |  |  | Lincoln, Placer ¦ Placer ¦ Sutter | PG&E: North Valley Area | No | 2007 | 0 ¦ 0 | Upgrade/Retrofit | Reliability | T-Line Capacity | N/A | NA | 230 | N/A | 2024-10-29 | 2009-05-01 | 2025-05-05 | Transmission Project Review Process data (Resolution E-5252 Attach B | 5848 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/08/25 - all overstressed breakers online with the exception of CB412. which is on track to be replaced by 06/02/25. | Utility - !Telecom! | Q1687, Q1871 | Q1687 | Q1871
Oro Loma 70 kV Reinforcement | 5777179 | T.0000157 | 61X | The C13P1-FPT03 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Oro Loma Substation 70kV Bus in Fresno County, California. | Engineering less than 50% complete | 2015-05-01 |  |  | Fresno | PG&E: North Valley Area | No | 2011 | T.0009846 | Upgrade/Retrofit | Reliability | T-Line Capacity | N/A | 3.8637 | N/A | 70 kV | 2028-03-31 | 2015-05-01 | 2028-05-11 | Transmission Project Review Process data (Resolution E-5252 Attach B | 4759 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom!
Vierra 115 kV Looping Project | 5777259 | T.0000597 | 60W | The C14P2-NPT04 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Vierra 115kV in San Joaquin County, California. | Operational | 2021-08-31 |  |  | Shasta | PG&E: North Valley Area | No | N/A | T.0011086 ¦ T.0010853 ¦ 0 ¦ T.0011168 ¦ 0 | Replace | Asset Condition | T-Line Capacity | N/A | 2.7679 | N/A | 230 kV | 2021-09-07 | 2021-08-31 | 2022-04-30 | Transmission Project Review Process data (Resolution E-5252 Attach B | 242 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom! | Q1867, Q1887, Q1904, Q1920, Q1929 | Q1867 | Q1887 | Q1904 | Q1920 | Q1929
Vierra 115 kV Looping Project | 5777394 | T.0000597 | 67A | The C14P2-NPT04 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Vierra 115kV in San Joaquin County, California. | Construction (25%-50%) | 2023-01-24 |  |  | Lathrop, San Joaquin | PG&E: North Valley Area | No | N/A | T.0011086 ¦ T.0010853 ¦ 0 ¦ T.0011168 ¦ 0 | New | Other [See Notes] | T-Line Capacity | N/A | 1.355 | N/A | 115 kV | 2024-05-21 | 2023-01-24 | 2025-06-12 | Transmission Project Review Process data (Resolution E-5252 Attach B | 870 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom! | Q1867, Q1887, Q1904, Q1920, Q1929 | Q1867 | Q1887 | Q1904 | Q1920 | Q1929
Vierra 115 kV Looping Project | 5777395 | T.0000597 | 67A | The C14P2-NPT04 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Vierra 115kV in San Joaquin County, California. | Engineering more than 50% complete | 2023-01-24 |  |  | Alameda | PG&E: North Valley Area | No | N/A | T.0011086 ¦ T.0010853 ¦ 0 ¦ T.0011168 ¦ 0 | Upgrade/Retrofit | Other [See Notes] | T-Line Capacity | N/A | 69.382 | N/A | 115 kV | 2025-04-17 | 2023-01-24 | 2025-06-05 | Transmission Project Review Process data (Resolution E-5252 Attach B | 863 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom! | Q1867, Q1887, Q1904, Q1920, Q1929 | Q1867 | Q1887 | Q1904 | Q1920 | Q1929
Vierra 115 kV Looping Project | 5777396 | T.0000597 | 67A | The C14P2-NPT04 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Vierra 115kV in San Joaquin County, California. | Engineering more than 50% complete | 2023-01-24 |  |  | San Joaquin | PG&E: North Valley Area | No | N/A | T.0011086 ¦ T.0010853 ¦ 0 ¦ T.0011168 ¦ 0 | Upgrade/Retrofit | Other [See Notes] | T-Line Capacity | N/A | 3.1988 | N/A | 115 kV | 2025-06-06 | 2023-01-24 | 2025-09-30 | Transmission Project Review Process data (Resolution E-5252 Attach B | 980 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom! | Q1867, Q1887, Q1904, Q1920, Q1929 | Q1867 | Q1887 | Q1904 | Q1920 | Q1929
Vierra 115 kV Looping Project | 5777397 | T.0000597 | 67A | The C14P2-NPT04 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Vierra 115kV in San Joaquin County, California. | Engineering more than 50% complete | 2023-01-24 |  |  | Tracy, San Joaquin | PG&E: North Valley Area | No | N/A | T.0011086 ¦ T.0010853 ¦ 0 ¦ T.0011168 ¦ 0 | Upgrade/Retrofit | Other [See Notes] | T-Line Capacity | N/A | 1.7469 | N/A | 115 kV | 2025-08-20 | 2023-01-24 | 2025-09-30 | Transmission Project Review Process data (Resolution E-5252 Attach B | 980 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom! | Q1867, Q1887, Q1904, Q1920, Q1929 | Q1867 | Q1887 | Q1904 | Q1920 | Q1929
Vierra 115 kV Looping Project | 5777418 | T.0000597 | 67A | The C14P2-NPT04 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Vierra 115kV in San Joaquin County, California. | Engineering more than 50% complete | 2023-01-24 |  |  | Manteca, San Joaquin | PG&E: North Valley Area | No | N/A | T.0011086 ¦ T.0010853 ¦ 0 ¦ T.0011168 ¦ 0 | Upgrade/Retrofit | Other [See Notes] | T-Line Capacity | N/A | 9.8539 | N/A | 115 kV | 2025-07-15 | 2023-01-24 | 2025-09-30 | Transmission Project Review Process data (Resolution E-5252 Attach B | 980 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom! | Q1867, Q1887, Q1904, Q1920, Q1929 | Q1867 | Q1887 | Q1904 | Q1920 | Q1929
Vierra 115 kV Looping Project | 5777421 | T.0000597 | 67A | The C14P2-NPT04 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Vierra 115kV in San Joaquin County, California. | Engineering more than 50% complete | 2023-01-24 |  |  | Ripon, San Joaquin | PG&E: North Valley Area | No | N/A | T.0011086 ¦ T.0010853 ¦ 0 ¦ T.0011168 ¦ 0 | Upgrade/Retrofit | Other [See Notes] | T-Line Capacity | N/A | 2.0603 | N/A | 115 kV | 2025-04-30 | 2023-01-24 | 2025-07-10 | Transmission Project Review Process data (Resolution E-5252 Attach B | 898 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom! | Q1867, Q1887, Q1904, Q1920, Q1929 | Q1867 | Q1887 | Q1904 | Q1920 | Q1929
Q1135 SCARLET (DA) GEN SITE | 5778458 | T.0003742 | 82Y | The Q1135 Scarlet Project from Cluster 8, proposes to interconnect a 400 megawatt (MW) (net output) Solar + Battery generation facility to Tranquility SW 230kV in Fresno County, California. The project has a contractual In-service date of: 11/17/23 with a current planned In-service date of: 12/1/23 | Operational | 2020-12-31 |  |  | Fresno | fsno | Yes | N/A | T.0007056 ¦ T.0004255 ¦ T.0007056 ¦ T.0009177 ¦ T.0007289 ¦ T.0003009 ¦ T.0004760 ¦ T.0003792 ¦ T.0003789 ¦ T.0003016 | Upgrade/Retrofit | Generator Interconnection | Generation Interconnection | N/A | 6.7555 | N/A | 230 kV | 2021-12-15 | 2023-11-17 | 2023-12-01 | Transmission Project Review Process data (Resolution E-5252 Attach B | 14 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | COD - 4/11/24 for 240MW Summary of commercial letters for the Scarlet Project: 1. Phase 1 (SCARLT_2_SSBSR1 - 100 MW) commercial operation letter released 02-27-24. 2. Phase 2 (SCARLT_2_SSBBT1 – 30 MW) commercial operation letter released 04-01-24. 3. Phase 3 (SCARLT_2_SSASR1 – 100 MW) commercial operation letter released 04-01-24. 4. Phase 4 (SCARLT_2_SSABT1 - 10 MW) commercial operation letter released 04-11-24. 9/7/23 - MMA received, ISD 10/4/23, CODs 2/20/24 through 10/31/25 in 7 phases. 8/7/23 - ISD scheduled Oct 4th subject to MMA being done in time. PPI is 9/20. Need the MMA by the 9/6 to move forward. MMA submitted 7/24. 7/17/23 - Need ICs test reports on time to meet dates. A customer proposed schedule needed to finalize the MMA dates. MMA not submitted- needed by Sept wk 1. PPI Sept 20. May not be achievable given the MMA timeline 6/22/23 - SEECO rep coordination is a critical issue. The IC will get the Rep back out to dial in the switches on 6/21. Inspections had issues with the ICs grounding. 5/16/23 - POCO has OPGW and Manual Switch on same TSP. Requires modification of the TSP to support these. Lesson learned not to have ICs OPGW on same structure. Should have been taken to ground 1 span sooner. 5/1/23 - 6/21/23 ISD is not likely achievable due to IC test reports delayed that were due 4/21/23. AFW needs submitted to change the clearance points all the way to tranquility since the team has to release the POCO pole switch. Ops will do a 30 day break-in. | Customer - Material | 1135 | 1135
Q1135 SCARLET T-LINE DA | 5778460 | T.0003742 | 82D | The Q1135 Scarlet Project from Cluster 8, proposes to interconnect a 400 megawatt (MW) (net output) Solar + Battery generation facility to Tranquility SW 230kV in Fresno County, California. The project has a contractual In-service date of: 11/17/23 with a current planned In-service date of: 12/1/23 | Operational | 2020-12-31 |  |  | Fresno | N/A | Yes | N/A | T.0007056 ¦ T.0004255 ¦ T.0007056 ¦ T.0009177 ¦ T.0007289 ¦ T.0003009 ¦ T.0004760 ¦ T.0003792 ¦ T.0003789 ¦ T.0003016 | New | Generator Interconnection | Generation Interconnection | 1 | N/A | 230 | N/A | 2023-01-16 | 2023-11-17 | 2023-12-01 | Transmission Project Review Process data (Resolution E-5252 Attach B | 14 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | COD - 4/11/24 for 240MW Summary of commercial letters for the Scarlet Project: 1. Phase 1 (SCARLT_2_SSBSR1 - 100 MW) commercial operation letter released 02-27-24. 2. Phase 2 (SCARLT_2_SSBBT1 – 30 MW) commercial operation letter released 04-01-24. 3. Phase 3 (SCARLT_2_SSASR1 – 100 MW) commercial operation letter released 04-01-24. 4. Phase 4 (SCARLT_2_SSABT1 - 10 MW) commercial operation letter released 04-11-24. 9/7/23 - MMA received, ISD 10/4/23, CODs 2/20/24 through 10/31/25 in 7 phases. 8/7/23 - ISD scheduled Oct 4th subject to MMA being done in time. PPI is 9/20. Need the MMA by the 9/6 to move forward. MMA submitted 7/24. 7/17/23 - Need ICs test reports on time to meet dates. A customer proposed schedule needed to finalize the MMA dates. MMA not submitted- needed by Sept wk 1. PPI Sept 20. May not be achievable given the MMA timeline 6/22/23 - SEECO rep coordination is a critical issue. The IC will get the Rep back out to dial in the switches on 6/21. Inspections had issues with the ICs grounding. 5/16/23 - POCO has OPGW and Manual Switch on same TSP. Requires modification of the TSP to support these. Lesson learned not to have ICs OPGW on same structure. Should have been taken to ground 1 span sooner. 5/1/23 - 6/21/23 ISD is not likely achievable due to IC test reports delayed that were due 4/21/23. AFW needs submitted to change the clearance points all the way to tranquility since the team has to release the POCO pole switch. Ops will do a 30 day break-in. | Customer - Material | 1135 | 1135
Q1135 SCARLET (NU) TRANQUILITY SS | 5778461 | T.0003742 | 82W | The Q1135 Scarlet Project from Cluster 8, proposes to interconnect a 400 megawatt (MW) (net output) Solar + Battery generation facility to Tranquility SW 230kV in Fresno County, California. The project has a contractual In-service date of: 11/17/23 with a current planned In-service date of: 12/1/23 | Operational | 2020-12-31 |  |  | Fresno | N/A | Yes | N/A | T.0007056 ¦ T.0004255 ¦ T.0007056 ¦ T.0009177 ¦ T.0007289 ¦ T.0003009 ¦ T.0004760 ¦ T.0003792 ¦ T.0003789 ¦ T.0003016 | New | Generator Interconnection | Generation Interconnection | N/A | 6.7555 | N/A | 230 kV | 2022-04-19 | 2023-11-17 | 2023-12-01 | Transmission Project Review Process data (Resolution E-5252 Attach B | 14 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | COD - 4/11/24 for 240MW Summary of commercial letters for the Scarlet Project: 1. Phase 1 (SCARLT_2_SSBSR1 - 100 MW) commercial operation letter released 02-27-24. 2. Phase 2 (SCARLT_2_SSBBT1 – 30 MW) commercial operation letter released 04-01-24. 3. Phase 3 (SCARLT_2_SSASR1 – 100 MW) commercial operation letter released 04-01-24. 4. Phase 4 (SCARLT_2_SSABT1 - 10 MW) commercial operation letter released 04-11-24. 9/7/23 - MMA received, ISD 10/4/23, CODs 2/20/24 through 10/31/25 in 7 phases. 8/7/23 - ISD scheduled Oct 4th subject to MMA being done in time. PPI is 9/20. Need the MMA by the 9/6 to move forward. MMA submitted 7/24. 7/17/23 - Need ICs test reports on time to meet dates. A customer proposed schedule needed to finalize the MMA dates. MMA not submitted- needed by Sept wk 1. PPI Sept 20. May not be achievable given the MMA timeline 6/22/23 - SEECO rep coordination is a critical issue. The IC will get the Rep back out to dial in the switches on 6/21. Inspections had issues with the ICs grounding. 5/16/23 - POCO has OPGW and Manual Switch on same TSP. Requires modification of the TSP to support these. Lesson learned not to have ICs OPGW on same structure. Should have been taken to ground 1 span sooner. 5/1/23 - 6/21/23 ISD is not likely achievable due to IC test reports delayed that were due 4/21/23. AFW needs submitted to change the clearance points all the way to tranquility since the team has to release the POCO pole switch. Ops will do a 30 day break-in. | Customer - Material | 1135 | 1135
Q1158 SLATE (DA) GEN SITE | 5778462 | T.0003743 | 82Y | The Q1158 Slate Project from Cluster 8, proposes to interconnect a 300 megawatt (MW) (net output) Solar + Battery generation facility to Mustang SW 230kV in Kings County, California. The project has a contractual In-service date of: 8/19/21 with a current planned In-service date of: 8/19/21 | Operational | 2024-07-05 |  |  | N/A | PG&E: Greater Fresno Area | No | N/A | T.0007289 ¦ T.0003009 ¦ T.0003792 ¦ T.0003789 ¦ T.0007056 ¦ T.0003016 ¦ T.0007056 | Upgrade/Retrofit | Other [See Notes] | System Operations | N/A | N/A | N/A | N/A | 2023-10-16 | 2022-02-15 | 2021-08-19 | Transmission Project Review Process data (Resolution E-5252 Attach B | -180 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | -
Q1158 SLATE (MTR) | 5778463 | T.0003743 | 82Y | The Q1158 Slate Project from Cluster 8, proposes to interconnect a 300 megawatt (MW) (net output) Solar + Battery generation facility to Mustang SW 230kV in Kings County, California. The project has a contractual In-service date of: 8/19/21 with a current planned In-service date of: 8/19/21 | Operational | 2024-07-05 |  |  | N/A | PG&E: Greater Fresno Area | No | N/A | T.0007289 ¦ T.0003009 ¦ T.0003792 ¦ T.0003789 ¦ T.0007056 ¦ T.0003016 ¦ T.0007056 | New | Other [See Notes] | Generation Interconnection | N/A | N/A | N/A | N/A | 2023-10-16 | 2022-02-15 | 2021-08-19 | Transmission Project Review Process data (Resolution E-5252 Attach B | -180 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | -
Q1143 - LAKE ALPAUGH BESS (DA) | 5778901 | T.0003744 | 82Y | The Q1143 Lake Alpaugh BESS & Alpaugh 3 BESS Project from Cluster 8, proposes to interconnect a 10 megawatt (MW) (net output) Battery generation facility to Corcoran-Olive SW 115kV Line in Tulare County, California. The project has a contractual In-service date of: 7/15/25 with a current planned In-service date of: 10/31/25 | Construction (10%-25%) | 2019-11-01 |  |  | Tulare | PG&E: Greater Fresno Area | Yes | N/A | T.0003009 ¦ T.0003789 | New | Generator Interconnection | Generation Interconnection | N/A | 1.6444 | N/A | 115 kV | 2025-02-19 | 2025-07-15 | 2025-10-31 | Transmission Project Review Process data (Resolution E-5252 Attach B | 108 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - Tracking ISD delays. MMA approval required for redesign of ICs point of interconnection | Customer - Project / Design Changes | 1143 | 1143
Q1143 - LAKE ALPAUGH BESS - CORCORAN SS | 5778903 | T.0003744 | 82W | The Q1143 Lake Alpaugh BESS & Alpaugh 3 BESS Project from Cluster 8, proposes to interconnect a 10 megawatt (MW) (net output) Battery generation facility to Corcoran-Olive SW 115kV Line in Tulare County, California. The project has a contractual In-service date of: 7/15/25 with a current planned In-service date of: 10/31/25 | Construction (over 75%) | 2019-11-01 |  |  | Kings | 0 | Yes | N/A | T.0003009 ¦ T.0003789 | New | Generator Interconnection | Special Protection Scheme | N/A | N/A | N/A | 115 kV | 2022-09-01 | 2025-07-15 | 2025-10-31 | Transmission Project Review Process data (Resolution E-5252 Attach B | 108 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - Tracking ISD delays. MMA approval required for redesign of ICs point of interconnection | Customer - Project / Design Changes | 1143 | 1143
Q1143 - LAKE ALPAUGH BESS - OLIVE SS DTT | 5778904 | T.0003744 | 82W | The Q1143 Lake Alpaugh BESS & Alpaugh 3 BESS Project from Cluster 8, proposes to interconnect a 10 megawatt (MW) (net output) Battery generation facility to Corcoran-Olive SW 115kV Line in Tulare County, California. The project has a contractual In-service date of: 7/15/25 with a current planned In-service date of: 10/31/25 | Construction (over 75%) | 2019-11-01 |  |  | Kern | 0 | Yes | N/A | T.0003009 ¦ T.0003789 | New | Generator Interconnection | Special Protection Scheme | N/A | 2.2701 | N/A | 115 kV | 2022-09-01 | 2025-07-15 | 2025-10-31 | Transmission Project Review Process data (Resolution E-5252 Attach B | 108 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - Tracking ISD delays. MMA approval required for redesign of ICs point of interconnection | Customer - Project / Design Changes | 1143 | 1143
Q1111 BLACK DIAMOND BESS(DA) PITTSBURG P | 5779007 | T.0003747 | 82Y | The Q1111 Black Diamond Energy Storage Project from Cluster 8, proposes to interconnect a 200 megawatt (MW) (net output) Battery generation facility to Pittsburgh 230kV in Contra Costa County, California. The project has a contractual In-service date of: 6/14/21 with a current planned In-service date of: 6/14/21 | Operational | 2021-03-01 |  |  | Pittsburg, Contra Costa | PG&E: Greater Fresno Area | Yes | N/A |  | Upgrade/Retrofit | Generator Interconnection | Generation Interconnection | N/A | 0.72358 | N/A | 230 kV | 2020-11-09 | 2022-02-15 | 2021-06-14 | Transmission Project Review Process data (Resolution E-5252 Attach B | -246 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | - | 1111 | 1111
Q1111 BLACK DIAMOND BESS (DA) GEN SITE | 5779008 | T.0003747 | 82Y | The Q1111 Black Diamond Energy Storage Project from Cluster 8, proposes to interconnect a 200 megawatt (MW) (net output) Battery generation facility to Pittsburgh 230kV in Contra Costa County, California. The project has a contractual In-service date of: 6/14/21 with a current planned In-service date of: 6/14/21 | Operational | 2021-03-01 |  |  | Pittsburg, Contra Costa | PG&E: Greater Fresno Area | Yes | N/A |  | Upgrade/Retrofit | Generator Interconnection | Generation Interconnection | N/A | 0.72358 | N/A | 230 kV | 2020-11-09 | 2022-02-15 | 2021-06-14 | Transmission Project Review Process data (Resolution E-5252 Attach B | -246 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | - | 1111 | 1111
Q1111 BLACK DIAMOND BESS (NU) PITTSBURG | 5779009 | T.0003747 | 82W | The Q1111 Black Diamond Energy Storage Project from Cluster 8, proposes to interconnect a 200 megawatt (MW) (net output) Battery generation facility to Pittsburgh 230kV in Contra Costa County, California. The project has a contractual In-service date of: 6/14/21 with a current planned In-service date of: 6/14/21 | Operational | 2021-03-01 |  |  | Pittsburg, Contra Costa | 0 | Yes | N/A |  | New | Generator Interconnection | Generation Interconnection | N/A | 0.72358 | N/A | 230 kV | 2020-12-01 | 2022-02-15 | 2021-06-14 | Transmission Project Review Process data (Resolution E-5252 Attach B | -246 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | - | 1111 | 1111
Q1111 BLACK DIAMOND BESS (DA) T-LINE | 5779010 | T.0003747 | 82D | The Q1111 Black Diamond Energy Storage Project from Cluster 8, proposes to interconnect a 200 megawatt (MW) (net output) Battery generation facility to Pittsburgh 230kV in Contra Costa County, California. The project has a contractual In-service date of: 6/14/21 with a current planned In-service date of: 6/14/21 | Operational | 2020-09-28 |  |  | Fresno | PG&E Kern Area | Yes | N/A |  | New | Generator Interconnection | Generation Interconnection | N/A | N/A | N/A | 230 kV | 2020-03-26 | 2022-02-15 | 2021-06-14 | Transmission Project Review Process data (Resolution E-5252 Attach B | -246 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | - | 1111 | 1111
Q1103 CENTRAL 40 DA | 5779011 | T.0003766 | 82Y | The Q1103 Central 40 Project from Cluster 8, proposes to interconnect a 40 megawatt (MW) (net output) Solar generation facility to Miller #1 115kV Line in Merced County, California. The project has a contractual In-service date of: 11/1/20 with a current planned In-service date of: 12/7/20 | Operational | 2020-09-28 |  |  | Fresno |  | Yes | N/A |  | New | Generator Interconnection | Generation Interconnection | N/A | 77.6619 | N/A | 230 kV | 2020-03-26 | 2022-02-15 | 2020-12-07 | Transmission Project Review Process data (Resolution E-5252 Attach B | -435 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | -
Q1103 - CENTRAL 40 METERING | 5779012 | T.0003766 | 82Y | The Q1103 Central 40 Project from Cluster 8, proposes to interconnect a 40 megawatt (MW) (net output) Solar generation facility to Miller #1 115kV Line in Merced County, California. The project has a contractual In-service date of: 11/1/20 with a current planned In-service date of: 12/7/20 | Operational | 2020-09-28 |  |  | Fresno |  | Yes | N/A |  | New | Generator Interconnection | Generation Interconnection | N/A | N/A | N/A | 230 kV | 2020-03-26 | 2022-02-15 | 2020-12-07 | Transmission Project Review Process data (Resolution E-5252 Attach B | -435 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | -
Q1103 - CENTRAL 40 TESLA SUB DTT (RNU) | 5779013 | T.0003766 | 82W | The Q1103 Central 40 Project from Cluster 8, proposes to interconnect a 40 megawatt (MW) (net output) Solar generation facility to Miller #1 115kV Line in Merced County, California. The project has a contractual In-service date of: 11/1/20 with a current planned In-service date of: 12/7/20 | Operational | 2020-09-28 |  |  | Fresno | 0 | Yes | N/A |  | New | Generator Interconnection | Special Protection Scheme | N/A | N/A | N/A | 230 kV | 2020-03-26 | 2022-02-15 | 2020-12-07 | Transmission Project Review Process data (Resolution E-5252 Attach B | -435 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | - | 1103 | 1103
Q1103 - CENTRAL 40 SALADO SUB DTT (RNU) | 5779014 | T.0003766 | 82W | The Q1103 Central 40 Project from Cluster 8, proposes to interconnect a 40 megawatt (MW) (net output) Solar generation facility to Miller #1 115kV Line in Merced County, California. The project has a contractual In-service date of: 11/1/20 with a current planned In-service date of: 12/7/20 | Operational | 2020-09-28 |  |  | Fresno | PG&E: Greater Fresno Area | Yes | N/A |  | New | Generator Interconnection | Special Protection Scheme | N/A | 77.6619 | N/A | 230 kV | 2020-03-26 | 2022-02-15 | 2020-12-07 | Transmission Project Review Process data (Resolution E-5252 Attach B | -435 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | - | 1103 | 1103
Q1103 - CENTRAL 40 MANTECA SUB DTT (RNU) | 5779015 | T.0003766 | 82W | The Q1103 Central 40 Project from Cluster 8, proposes to interconnect a 40 megawatt (MW) (net output) Solar generation facility to Miller #1 115kV Line in Merced County, California. The project has a contractual In-service date of: 11/1/20 with a current planned In-service date of: 12/7/20 | Operational | 2020-09-28 |  |  | Fresno | PG&E: Greater Fresno Area | Yes | N/A |  | New | Generator Interconnection | Special Protection Scheme | N/A | 77.6619 | N/A | 230 kV | 2020-03-26 | 2022-02-15 | 2020-12-07 | Transmission Project Review Process data (Resolution E-5252 Attach B | -435 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | - | 1103 | 1103
Q1117 AQUAMARINE WESTSIDE DA GATES SUB | 5779026 | T.0003750 | 82Y | The Q1117 Aquamarine Westside Project from Cluster 8, proposes to interconnect a 250 megawatt (MW) (net output) Solar generation facility to Gates 230kV in Fresno County, California. The project has a contractual In-service date of: 9/15/21 with a current planned In-service date of: 8/10/21 | Operational | 2020-09-28 |  |  | Fresno | PG&E: Greater Fresno Area | Yes | N/A | T.0003009 ¦ T.0003789 | New | Generator Interconnection | Generation Interconnection | N/A | 77.6619 | N/A | 230 kV | 2020-03-26 | 2022-02-15 | 2021-08-10 | Transmission Project Review Process data (Resolution E-5252 Attach B | -189 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Customer - Bundling Dependencies | 1117 | 1117
Q1117 AQUAMARINE WESTSIDE DA | 5779027 | T.0003750 | 82Y | The Q1117 Aquamarine Westside Project from Cluster 8, proposes to interconnect a 250 megawatt (MW) (net output) Solar generation facility to Gates 230kV in Fresno County, California. The project has a contractual In-service date of: 9/15/21 with a current planned In-service date of: 8/10/21 | Operational | 2020-09-28 |  |  | Fresno | PG&E: Greater Fresno Area | Yes | N/A | T.0003009 ¦ T.0003789 | New | Generator Interconnection | Generation Interconnection | N/A | N/A | N/A | 230 kV | 2020-04-06 | 2022-02-15 | 2021-08-10 | Transmission Project Review Process data (Resolution E-5252 Attach B | -189 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Customer - Bundling Dependencies
Q1117 AQUAMARINE WESTSIDE T-LINE DA | 5779028 | T.0003750 | 82D | The Q1117 Aquamarine Westside Project from Cluster 8, proposes to interconnect a 250 megawatt (MW) (net output) Solar generation facility to Gates 230kV in Fresno County, California. The project has a contractual In-service date of: 9/15/21 with a current planned In-service date of: 8/10/21 | Operational | 2020-09-28 |  |  | Fresno | N/A | Yes | N/A | T.0003009 ¦ T.0003789 | New | Generator Interconnection | Generation Interconnection | N/A | N/A | N/A | 230 kV | 2020-04-06 | 2022-02-15 | 2021-08-10 | Transmission Project Review Process data (Resolution E-5252 Attach B | -189 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Customer - Bundling Dependencies | 1117 | 1117
Q1117 AQUAMARINE WESTSIDE DA (METER) | 5779029 | T.0003750 | 82Y | The Q1117 Aquamarine Westside Project from Cluster 8, proposes to interconnect a 250 megawatt (MW) (net output) Solar generation facility to Gates 230kV in Fresno County, California. The project has a contractual In-service date of: 9/15/21 with a current planned In-service date of: 8/10/21 | Operational | 2020-09-28 |  |  | Fresno | N/A | Yes | N/A | T.0003009 ¦ T.0003789 | New | Generator Interconnection | Generation Interconnection | N/A | 77.6619 | N/A | 230 kV | 2020-04-06 | 2022-02-15 | 2021-08-10 | Transmission Project Review Process data (Resolution E-5252 Attach B | -189 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Customer - Bundling Dependencies | 1117 | 1117
Q1117 AQUAMARINE WESTSIDE GATES SUB RNU | 5779030 | T.0003750 | 82W | The Q1117 Aquamarine Westside Project from Cluster 8, proposes to interconnect a 250 megawatt (MW) (net output) Solar generation facility to Gates 230kV in Fresno County, California. The project has a contractual In-service date of: 9/15/21 with a current planned In-service date of: 8/10/21 | Operational | 2020-09-28 |  |  | Fresno | ngba | Yes | N/A | T.0003009 ¦ T.0003789 | New | Generator Interconnection | Generation Interconnection | N/A | 77.6619 | N/A | 230 kV | 2020-04-06 | 2022-02-15 | 2021-08-10 | Transmission Project Review Process data (Resolution E-5252 Attach B | -189 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Customer - Bundling Dependencies | 1117 | 1117
LOS BANOS - QUINTO SS 20244: RECON - EGI | 5779031 | T.0003789 | 82B | The C8P1-35 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Los Banos-Quinto SS 230 kV in Merced County, California. | Operational | 2020-04-30 |  |  | Merced | PG&E: Greater Bay Area | Yes | N/A | T.0003750 ¦ T.0004565 ¦ T.0003005 ¦ T.0002987 ¦ T.0004560 ¦ T.0003743 ¦ T.0003742 ¦ T.0004490 ¦ T.0003744 | Upgrade/Retrofit | Generator Interconnection | T-Line Capacity | 12 | NA | 230 | N/A | 2023-03-06 | 2020-04-30 | 2023-05-08 | Transmission Project Review Process data (Resolution E-5252 Attach B | 1103 | Yes |  |  | Final Certified | 41219 | EIR | N/A | Merced County | N/A | NOC: AL 4180-E | 2013-01-17 | Approved | 2013 | In-service 5/5/23 | Utility - !Telecom! | Q1117, Q1120, Q1127, Q1128, Q1139, Q1158, Q1135, Q1129, Q1143 | Q1117 | Q1120 | Q1127 | Q1128 | Q1139 | Q1158 | Q1135 | Q1129 | Q1143
Q1136 WESTLANDS ALMOND KENT SW STA (DA) | 5779032 | T.0003752 | 82Y | The Q1136 Westlands Almond Project from Cluster 8, proposes to interconnect a 19.88 megawatt (MW) (net output) Solar generation facility to Kent SW STA 70kV in Kings County, California. The project has a contractual In-service date of: 5/31/23 with a current planned In-service date of: 7/20/23 | Construction (50%-75%) | 2021-09-30 |  |  | Fresno ¦ Merced | N/A | Yes | N/A |  | Upgrade/Retrofit | Generator Interconnection | Generation Interconnection | 33.5 | NA | 230 | N/A | 2023-11-02 | 2023-05-31 | 2023-07-20 | Transmission Project Review Process data (Resolution E-5252 Attach B | 50 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | NOC: AL 6857-E | 2022-11-21 | Approved | 2023 | COD - 9/7/23 for 19.88MW In-service 7/20/23 | Customer - Bundling Dependencies | 1136 | 1136
Q1136 WESTLANDS ALMOND (DA) | 5779033 | T.0003752 | 82Y | The Q1136 Westlands Almond Project from Cluster 8, proposes to interconnect a 19.88 megawatt (MW) (net output) Solar generation facility to Kent SW STA 70kV in Kings County, California. The project has a contractual In-service date of: 5/31/23 with a current planned In-service date of: 7/20/23 | Construction (50%-75%) | 2021-09-30 |  |  | Fresno ¦ Merced | KERN | Yes | N/A |  | Upgrade/Retrofit | Generator Interconnection | Generation Interconnection | 33.5 | NA | 230 | N/A | 2023-11-02 | 2023-05-31 | 2023-07-20 | Transmission Project Review Process data (Resolution E-5252 Attach B | 50 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | NOC: AL 6857-E | 2022-11-21 | Approved | 2023 | COD - 9/7/23 for 19.88MW In-service 7/20/23 | Customer - Bundling Dependencies | 1136 | 1136
Q1136 WESTLANDS ALMOND T-LINE DA | 5779035 | T.0003752 | 82D | The Q1136 Westlands Almond Project from Cluster 8, proposes to interconnect a 19.88 megawatt (MW) (net output) Solar generation facility to Kent SW STA 70kV in Kings County, California. The project has a contractual In-service date of: 5/31/23 with a current planned In-service date of: 7/20/23 | Construction (50%-75%) | 2021-09-30 |  |  | Fresno ¦ Merced | N/A | Yes | N/A |  | Upgrade/Retrofit | Generator Interconnection | Generation Interconnection | 33.5 | N/A | 230 | N/A | 2023-11-02 | 2023-05-31 | 2023-07-20 | Transmission Project Review Process data (Resolution E-5252 Attach B | 50 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | NOC: AL 6857-E | 2022-11-21 | Approved | 2023 | COD - 9/7/23 for 19.88MW In-service 7/20/23 | Customer - Bundling Dependencies | 1136 | 1136
Q1136 WESTLANDS ALMOND KENT SW STA (NU) | 5779036 | T.0003752 | 82W | The Q1136 Westlands Almond Project from Cluster 8, proposes to interconnect a 19.88 megawatt (MW) (net output) Solar generation facility to Kent SW STA 70kV in Kings County, California. The project has a contractual In-service date of: 5/31/23 with a current planned In-service date of: 7/20/23 | Construction (50%-75%) | 2021-09-30 |  |  | Fresno ¦ Merced | N/A | Yes | N/A |  | Upgrade/Retrofit | Generator Interconnection | Generation Interconnection | 33.5 | NA | 230 | N/A | 2023-11-02 | 2023-05-31 | 2023-07-20 | Transmission Project Review Process data (Resolution E-5252 Attach B | 50 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | NOC: AL 6857-E | 2022-11-21 | Approved | 2023 | COD - 9/7/23 for 19.88MW In-service 7/20/23 | Customer - Bundling Dependencies | 1136 | 1136
PADRE FLAT- PANOCHE#1 20267: RECON - EGI | 5779058 | T.0003792 | 82B | The C8P1-34 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Padre Flat-Panoche 230kV Line #1 in Kings County, California. | Construction (50%-75%) | 2021-09-30 |  |  | Fresno ¦ Merced | PG&E: Greater Bay Area | Yes | N/A | T.0003005 ¦ T.0002987 ¦ T.0003743 ¦ T.0003742 ¦ T.0004490 ¦ 0 | Upgrade/Retrofit | Generator Interconnection | T-Line Capacity | 33.5 | N/A | 230 | N/A | 2023-11-02 | 2021-09-30 | 2025-05-09 | Transmission Project Review Process data (Resolution E-5252 Attach B | 1317 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | NOC: AL 6857-E | 2022-11-21 | Approved | 2023 | 04/23/25 - Operative | Utility - !Telecom! | Q1127, Q1128, Q1158, Q1135, Q1129, Q1568, 2181-WD | Q1127 | Q1128 | Q1158 | Q1135 | Q1129 | Q1568 | 2181-WD
74017328_BORDEN-GREGG_#1_20264_LINE | 5779059 | T.0007056 | 82B | The C8P2-1 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Borden-Gregg 230kV Line #1 in Madera County, California. | Engineering more than 50% complete | 2020-09-30 |  |  | Madera | 0 | Yes | N/A | T.0003742 ¦ T.0003743 ¦ T.0004490 ¦ T.0008538 ¦ 0 ¦ T.0010467 ¦ T.0010817 ¦ T.0010942 ¦ 0 ¦ T.0010738 ¦ 0 ¦ 0 ¦ 0 | Upgrade/Retrofit | Generator Interconnection | T-Line Capacity | 6.2 | N/A | 230 | N/A | 2026-10-05 | 2020-09-30 | 2027-01-08 | Transmission Project Review Process data (Resolution E-5252 Attach B | 2291 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | NOC: AL 7393-E | 2024-10-02 | Approved | 2024 |  | Utility - !Telecom! | Q1135, Q1158, Q1129, Q1713, Q1568, Q1709, Q1930, Q1935, Q1953, Q1956, Q1966, Q1968, Q1975 | Q1135 | Q1158 | Q1129 | Q1713 | Q1568 | Q1709 | Q1930 | Q1935 | Q1953 | Q1956 | Q1966 | Q1968 | Q1975
74017329_BORDEN-GREGG_#2_20009_LINE | 5779060 | T.0007056 | 82B | The C8P2-1 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Borden-Gregg 230kV Line #1 in Madera County, California. | Engineering more than 50% complete | 2020-09-30 |  |  | Madera | PG&E: Greater Fresno Area | Yes | N/A | T.0003742 ¦ T.0003743 ¦ T.0004490 ¦ T.0008538 ¦ 0 ¦ T.0010467 ¦ T.0010817 ¦ T.0010942 ¦ 0 ¦ T.0010738 ¦ 0 ¦ 0 ¦ 0 | Upgrade/Retrofit | Generator Interconnection | Generation Interconnection | 6.25 | NA | 230 | N/A | 2027-01-19 | 2020-09-30 | 2027-05-12 | Transmission Project Review Process data (Resolution E-5252 Attach B | 2415 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | NOC: AL 7393-E | 2024-10-02 | Approved | 2024 |  | Utility - !Telecom! | Q1135, Q1158, Q1129, Q1713, Q1568, Q1709, Q1930, Q1935, Q1953, Q1956, Q1966, Q1968, Q1975 | Q1135 | Q1158 | Q1129 | Q1713 | Q1568 | Q1709 | Q1930 | Q1935 | Q1953 | Q1956 | Q1966 | Q1968 | Q1975
Q1244 - PROXIMA SOLAR - QUINTO SWITCHING | 5779104 | T.0003770 | 82W | The Q1244 Proxima Solar Project from Cluster 9, proposes to interconnect a 300 megawatt (MW) (net output) Solar + Battery generation facility to Fink 230kV switching station in Stainslaus County, California. The project has a contractual In-service date of: 10/15/23 with a current planned In-service date of: 3/6/24 | Operational | 2020-01-10 |  |  | Merced | PG&E: Greater Fresno Area | Yes | N/A |  | New | Generator Interconnection | Line Reconductoring | N/A | 53.2803 | N/A | 230 kV | 2022-06-29 | 2023-10-15 | 2024-03-06 | Transmission Project Review Process data (Resolution E-5252 Attach B | 143 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | NOC: AL 6529-E | 2022-03-16 | Approved | 2022 | COD - 3/18/24 for 162MW 3/6/24 - The Q1244 Proxima Solar project achieved In-Service Date (ISD) today March 6, 2024. This project will generate 300 MW of renewable PV energy and capable of 150 MW of battery storage. The project encompasses approximately 1,100 acres. Final testing of the facility is scheduled for next Wednesday March 13th, 2024 and a Commercial Operation Date letter is expected by the end of the month. To interconnect the customer project, PG&E teams engineered, permitted, tested and placed into service on March 5, 2024 a greenfield looped Switching Station (SS) 11 acres in size named Fink SS. The SS was an EPC contract type project completed through the competitive bid process. Fink SS connects to the 230 kV system approximately 4 miles north of the PG&E Quinto SS and a few miles south of the third party utility owned 230 kV substation Westley substation in Stanislaus County. To interconnect the new 230 kV SS the project called for protective relay upgrades at Los Banos, Quinto SS, and Westley Substation. The PG&E project team coordinated with Modesto Irrigation District (MID) to get the project successful. There was also telecommunications and testing coordination at Westley Substation MID teams and PG&E teams. The energization of Fink SS and Proxima occurred via radial connection. This energization test process spanned a few days to fully test the SS and the third party customer substation. There is remaining work to be completed in order to energize the Fink SS – Westley 230 kV line and is scheduled to finalize April 1, 2024. This project had many barriers to get towards completion. One of the major barriers was permitting and acquiring the land from Stanislaus County. I want to shout out @Everett, Kirsten and @Crossfield, Scott for essentially being a Stanislaus county resource and spending many days waiting at their counter or hand delivering necessary requirements to complete permitting and acquisition activities. This project kicked off in Q2 2018 with a total of over 165 different resources attending project meetings and lending their expertise throughout the project lifecycle. Thank you to everyone involved in this project and helping to bring expertise and professionalism when interacting with NextEra as well as overcome obstacles and provide a quality product. 3/4/24 -Expecting to energize Proxima on 3/6. Fink SS is 3/5. 2/5/25 - PGE Microwave scope between Mt Oso and MID's Wesley Substation cannot be started until Agreements between MID and PGE are made. Scope and Cost impacts being worked out between multi-parties. Interim solution being reviewed but may conflict with the original scope and schedule. 1/23/24 - MID delays have put IC at risk of default. They are incurring costs due to Generators of battery minimally charging. Impacting their Environmental Air Quality Permits if they keep running longer. 1/11/24 - IC does not have their CAISO letter for Permission to Test which was required to put load on Fink thus energizing both SS and Gensite. ISD moved to March after MID work is complete which would no required Q1244 as load to test Fink. 12/14/23 - IC could not get a CAISO clearance until 12/20 due to telecom commissiong, key predecessor activities, and EoY CAISO clearance congestion. Due to the late December date, the PG&E resources to backfeed the customer are insufficient to safely perform the work. 12/13/23 - PTO letter to CAISO on 12/13. Clearance for backfeed 12/20. Requires Battery Loads to Sync Sw Sta. 12/12/23 - Line Connector assemblies were ACSR and not ACSS. This results in temporary re-rate on the line until the repair can be completed. Estimated at 100 to 150K to fix. Mike Milbury and CM Kevin Withrow know the details. 12/7/23 - SCADA/EMS release planned for 12/11/23. Backfeed planned for 12/15. IC is ready to provide 120MWs of load given 24 hours of notice. Potential they can increase that. MID on a call today due to Turlock irrigation district impact.MID needs the Turlock concent to proceed to EoFeb. 11/1/23 - Verify with SQ ISD Trending to Jan 2024 12/15/23 at this time for ISD. 10/2/23 - MID is no longer critical path. Moved to the end of the sequence and affect COD only. Internal only - PM is looking at possibly pulling the ISD into December. Telecom and NERC activity impacting. 9/19/23 - MID work on the DTT on the line is critical to hit the Tline work sequence. 9/18/23 - ISD is tracking to Jan 2024. 8/21/23 - MID is asking for 25 weeks now. rebalanced the clearance so MID comes at the end. Affect COD but not ISD. 8/7/23 - ISD is likely to delay due to MID. MID asking for 20 weeks to do relay work starting in Oct. Meeting next week discuss. 07/27/23 - Schedule is the same for last note. 6/22/23 - Oct 10-20 Tline to set poles for the new SS loop in. 5/15/23 - ISD is pusing to 2024 due to SS construction. Permanent Land acquisitions still with Legal. T_line foundations installed for the loop-in. Clearance to come back in Fall. | Utility - !Telecom! | 1244 | 1244
Q1244 - PROXIMA SOLAR - LOS BANOS SUBSTA | 5779105 | T.0003770 | 82W | The Q1244 Proxima Solar Project from Cluster 9, proposes to interconnect a 300 megawatt (MW) (net output) Solar + Battery generation facility to Fink 230kV switching station in Stainslaus County, California. The project has a contractual In-service date of: 10/15/23 with a current planned In-service date of: 3/6/24 | Operational | 2020-01-10 |  |  | Merced | 0 | Yes | N/A |  | New | Generator Interconnection | Line Reconductoring | N/A | 53.2803 | N/A | 230 kV | 2022-08-16 | 2023-10-15 | 2024-03-06 | Transmission Project Review Process data (Resolution E-5252 Attach B | 143 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | NOC: AL 6529-E | 2022-03-16 | Approved | 2022 | COD - 3/18/24 for 162MW 3/6/24 - The Q1244 Proxima Solar project achieved In-Service Date (ISD) today March 6, 2024. This project will generate 300 MW of renewable PV energy and capable of 150 MW of battery storage. The project encompasses approximately 1,100 acres. Final testing of the facility is scheduled for next Wednesday March 13th, 2024 and a Commercial Operation Date letter is expected by the end of the month. To interconnect the customer project, PG&E teams engineered, permitted, tested and placed into service on March 5, 2024 a greenfield looped Switching Station (SS) 11 acres in size named Fink SS. The SS was an EPC contract type project completed through the competitive bid process. Fink SS connects to the 230 kV system approximately 4 miles north of the PG&E Quinto SS and a few miles south of the third party utility owned 230 kV substation Westley substation in Stanislaus County. To interconnect the new 230 kV SS the project called for protective relay upgrades at Los Banos, Quinto SS, and Westley Substation. The PG&E project team coordinated with Modesto Irrigation District (MID) to get the project successful. There was also telecommunications and testing coordination at Westley Substation MID teams and PG&E teams. The energization of Fink SS and Proxima occurred via radial connection. This energization test process spanned a few days to fully test the SS and the third party customer substation. There is remaining work to be completed in order to energize the Fink SS – Westley 230 kV line and is scheduled to finalize April 1, 2024. This project had many barriers to get towards completion. One of the major barriers was permitting and acquiring the land from Stanislaus County. I want to shout out @Everett, Kirsten and @Crossfield, Scott for essentially being a Stanislaus county resource and spending many days waiting at their counter or hand delivering necessary requirements to complete permitting and acquisition activities. This project kicked off in Q2 2018 with a total of over 165 different resources attending project meetings and lending their expertise throughout the project lifecycle. Thank you to everyone involved in this project and helping to bring expertise and professionalism when interacting with NextEra as well as overcome obstacles and provide a quality product. 3/4/24 -Expecting to energize Proxima on 3/6. Fink SS is 3/5. 2/5/25 - PGE Microwave scope between Mt Oso and MID's Wesley Substation cannot be started until Agreements between MID and PGE are made. Scope and Cost impacts being worked out between multi-parties. Interim solution being reviewed but may conflict with the original scope and schedule. 1/23/24 - MID delays have put IC at risk of default. They are incurring costs due to Generators of battery minimally charging. Impacting their Environmental Air Quality Permits if they keep running longer. 1/11/24 - IC does not have their CAISO letter for Permission to Test which was required to put load on Fink thus energizing both SS and Gensite. ISD moved to March after MID work is complete which would no required Q1244 as load to test Fink. 12/14/23 - IC could not get a CAISO clearance until 12/20 due to telecom commissiong, key predecessor activities, and EoY CAISO clearance congestion. Due to the late December date, the PG&E resources to backfeed the customer are insufficient to safely perform the work. 12/13/23 - PTO letter to CAISO on 12/13. Clearance for backfeed 12/20. Requires Battery Loads to Sync Sw Sta. 12/12/23 - Line Connector assemblies were ACSR and not ACSS. This results in temporary re-rate on the line until the repair can be completed. Estimated at 100 to 150K to fix. Mike Milbury and CM Kevin Withrow know the details. 12/7/23 - SCADA/EMS release planned for 12/11/23. Backfeed planned for 12/15. IC is ready to provide 120MWs of load given 24 hours of notice. Potential they can increase that. MID on a call today due to Turlock irrigation district impact.MID needs the Turlock concent to proceed to EoFeb. 11/1/23 - Verify with SQ ISD Trending to Jan 2024 12/15/23 at this time for ISD. 10/2/23 - MID is no longer critical path. Moved to the end of the sequence and affect COD only. Internal only - PM is looking at possibly pulling the ISD into December. Telecom and NERC activity impacting. 9/19/23 - MID work on the DTT on the line is critical to hit the Tline work sequence. 9/18/23 - ISD is tracking to Jan 2024. 8/21/23 - MID is asking for 25 weeks now. rebalanced the clearance so MID comes at the end. Affect COD but not ISD. 8/7/23 - ISD is likely to delay due to MID. MID asking for 20 weeks to do relay work starting in Oct. Meeting next week discuss. 07/27/23 - Schedule is the same for last note. 6/22/23 - Oct 10-20 Tline to set poles for the new SS loop in. 5/15/23 - ISD is pusing to 2024 due to SS construction. Permanent Land acquisitions still with Legal. T_line foundations installed for the loop-in. Clearance to come back in Fall. | Utility - !Telecom! | 1244 | 1244
Q1244 - PROXIMA SOLAR (DA) | 5779138 | T.0003770 | 82Y | The Q1244 Proxima Solar Project from Cluster 9, proposes to interconnect a 300 megawatt (MW) (net output) Solar + Battery generation facility to Fink 230kV switching station in Stainslaus County, California. The project has a contractual In-service date of: 10/15/23 with a current planned In-service date of: 3/6/24 | Operational | 2020-01-10 |  |  | Stanislaus | KERN | Yes | N/A |  | New | Generator Interconnection | Generation Interconnection | N/A | N/A | N/A | 230 kV | 2023-06-02 | 2023-10-15 | 2024-03-06 | Transmission Project Review Process data (Resolution E-5252 Attach B | 143 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | NOC: AL 6529-E | 2022-03-16 | Approved | 2022 | COD - 3/18/24 for 162MW 3/6/24 - The Q1244 Proxima Solar project achieved In-Service Date (ISD) today March 6, 2024. This project will generate 300 MW of renewable PV energy and capable of 150 MW of battery storage. The project encompasses approximately 1,100 acres. Final testing of the facility is scheduled for next Wednesday March 13th, 2024 and a Commercial Operation Date letter is expected by the end of the month. To interconnect the customer project, PG&E teams engineered, permitted, tested and placed into service on March 5, 2024 a greenfield looped Switching Station (SS) 11 acres in size named Fink SS. The SS was an EPC contract type project completed through the competitive bid process. Fink SS connects to the 230 kV system approximately 4 miles north of the PG&E Quinto SS and a few miles south of the third party utility owned 230 kV substation Westley substation in Stanislaus County. To interconnect the new 230 kV SS the project called for protective relay upgrades at Los Banos, Quinto SS, and Westley Substation. The PG&E project team coordinated with Modesto Irrigation District (MID) to get the project successful. There was also telecommunications and testing coordination at Westley Substation MID teams and PG&E teams. The energization of Fink SS and Proxima occurred via radial connection. This energization test process spanned a few days to fully test the SS and the third party customer substation. There is remaining work to be completed in order to energize the Fink SS – Westley 230 kV line and is scheduled to finalize April 1, 2024. This project had many barriers to get towards completion. One of the major barriers was permitting and acquiring the land from Stanislaus County. I want to shout out @Everett, Kirsten and @Crossfield, Scott for essentially being a Stanislaus county resource and spending many days waiting at their counter or hand delivering necessary requirements to complete permitting and acquisition activities. This project kicked off in Q2 2018 with a total of over 165 different resources attending project meetings and lending their expertise throughout the project lifecycle. Thank you to everyone involved in this project and helping to bring expertise and professionalism when interacting with NextEra as well as overcome obstacles and provide a quality product. 3/4/24 -Expecting to energize Proxima on 3/6. Fink SS is 3/5. 2/5/25 - PGE Microwave scope between Mt Oso and MID's Wesley Substation cannot be started until Agreements between MID and PGE are made. Scope and Cost impacts being worked out between multi-parties. Interim solution being reviewed but may conflict with the original scope and schedule. 1/23/24 - MID delays have put IC at risk of default. They are incurring costs due to Generators of battery minimally charging. Impacting their Environmental Air Quality Permits if they keep running longer. 1/11/24 - IC does not have their CAISO letter for Permission to Test which was required to put load on Fink thus energizing both SS and Gensite. ISD moved to March after MID work is complete which would no required Q1244 as load to test Fink. 12/14/23 - IC could not get a CAISO clearance until 12/20 due to telecom commissiong, key predecessor activities, and EoY CAISO clearance congestion. Due to the late December date, the PG&E resources to backfeed the customer are insufficient to safely perform the work. 12/13/23 - PTO letter to CAISO on 12/13. Clearance for backfeed 12/20. Requires Battery Loads to Sync Sw Sta. 12/12/23 - Line Connector assemblies were ACSR and not ACSS. This results in temporary re-rate on the line until the repair can be completed. Estimated at 100 to 150K to fix. Mike Milbury and CM Kevin Withrow know the details. 12/7/23 - SCADA/EMS release planned for 12/11/23. Backfeed planned for 12/15. IC is ready to provide 120MWs of load given 24 hours of notice. Potential they can increase that. MID on a call today due to Turlock irrigation district impact.MID needs the Turlock concent to proceed to EoFeb. 11/1/23 - Verify with SQ ISD Trending to Jan 2024 12/15/23 at this time for ISD. 10/2/23 - MID is no longer critical path. Moved to the end of the sequence and affect COD only. Internal only - PM is looking at possibly pulling the ISD into December. Telecom and NERC activity impacting. 9/19/23 - MID work on the DTT on the line is critical to hit the Tline work sequence. 9/18/23 - ISD is tracking to Jan 2024. 8/21/23 - MID is asking for 25 weeks now. rebalanced the clearance so MID comes at the end. Affect COD but not ISD. 8/7/23 - ISD is likely to delay due to MID. MID asking for 20 weeks to do relay work starting in Oct. Meeting next week discuss. 07/27/23 - Schedule is the same for last note. 6/22/23 - Oct 10-20 Tline to set poles for the new SS loop in. 5/15/23 - ISD is pusing to 2024 due to SS construction. Permanent Land acquisitions still with Legal. T_line foundations installed for the loop-in. Clearance to come back in Fall. | Utility - !Telecom!
Q1244 - PROXIMA SOLAR SS (NU) | 5779140 | T.0003770 | 82W | The Q1244 Proxima Solar Project from Cluster 9, proposes to interconnect a 300 megawatt (MW) (net output) Solar + Battery generation facility to Fink 230kV switching station in Stainslaus County, California. The project has a contractual In-service date of: 10/15/23 with a current planned In-service date of: 3/6/24 | Operational | 2020-01-10 |  |  | Stanislaus | 0 | Yes | N/A |  | New | Generator Interconnection | Generation Interconnection | N/A | 0.67641 | N/A | 230 kV | 2023-06-02 | 2023-10-15 | 2024-03-06 | Transmission Project Review Process data (Resolution E-5252 Attach B | 143 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | NOC: AL 6529-E | 2022-03-16 | Approved | 2022 | COD - 3/18/24 for 162MW 3/6/24 - The Q1244 Proxima Solar project achieved In-Service Date (ISD) today March 6, 2024. This project will generate 300 MW of renewable PV energy and capable of 150 MW of battery storage. The project encompasses approximately 1,100 acres. Final testing of the facility is scheduled for next Wednesday March 13th, 2024 and a Commercial Operation Date letter is expected by the end of the month. To interconnect the customer project, PG&E teams engineered, permitted, tested and placed into service on March 5, 2024 a greenfield looped Switching Station (SS) 11 acres in size named Fink SS. The SS was an EPC contract type project completed through the competitive bid process. Fink SS connects to the 230 kV system approximately 4 miles north of the PG&E Quinto SS and a few miles south of the third party utility owned 230 kV substation Westley substation in Stanislaus County. To interconnect the new 230 kV SS the project called for protective relay upgrades at Los Banos, Quinto SS, and Westley Substation. The PG&E project team coordinated with Modesto Irrigation District (MID) to get the project successful. There was also telecommunications and testing coordination at Westley Substation MID teams and PG&E teams. The energization of Fink SS and Proxima occurred via radial connection. This energization test process spanned a few days to fully test the SS and the third party customer substation. There is remaining work to be completed in order to energize the Fink SS – Westley 230 kV line and is scheduled to finalize April 1, 2024. This project had many barriers to get towards completion. One of the major barriers was permitting and acquiring the land from Stanislaus County. I want to shout out @Everett, Kirsten and @Crossfield, Scott for essentially being a Stanislaus county resource and spending many days waiting at their counter or hand delivering necessary requirements to complete permitting and acquisition activities. This project kicked off in Q2 2018 with a total of over 165 different resources attending project meetings and lending their expertise throughout the project lifecycle. Thank you to everyone involved in this project and helping to bring expertise and professionalism when interacting with NextEra as well as overcome obstacles and provide a quality product. 3/4/24 -Expecting to energize Proxima on 3/6. Fink SS is 3/5. 2/5/25 - PGE Microwave scope between Mt Oso and MID's Wesley Substation cannot be started until Agreements between MID and PGE are made. Scope and Cost impacts being worked out between multi-parties. Interim solution being reviewed but may conflict with the original scope and schedule. 1/23/24 - MID delays have put IC at risk of default. They are incurring costs due to Generators of battery minimally charging. Impacting their Environmental Air Quality Permits if they keep running longer. 1/11/24 - IC does not have their CAISO letter for Permission to Test which was required to put load on Fink thus energizing both SS and Gensite. ISD moved to March after MID work is complete which would no required Q1244 as load to test Fink. 12/14/23 - IC could not get a CAISO clearance until 12/20 due to telecom commissiong, key predecessor activities, and EoY CAISO clearance congestion. Due to the late December date, the PG&E resources to backfeed the customer are insufficient to safely perform the work. 12/13/23 - PTO letter to CAISO on 12/13. Clearance for backfeed 12/20. Requires Battery Loads to Sync Sw Sta. 12/12/23 - Line Connector assemblies were ACSR and not ACSS. This results in temporary re-rate on the line until the repair can be completed. Estimated at 100 to 150K to fix. Mike Milbury and CM Kevin Withrow know the details. 12/7/23 - SCADA/EMS release planned for 12/11/23. Backfeed planned for 12/15. IC is ready to provide 120MWs of load given 24 hours of notice. Potential they can increase that. MID on a call today due to Turlock irrigation district impact.MID needs the Turlock concent to proceed to EoFeb. 11/1/23 - Verify with SQ ISD Trending to Jan 2024 12/15/23 at this time for ISD. 10/2/23 - MID is no longer critical path. Moved to the end of the sequence and affect COD only. Internal only - PM is looking at possibly pulling the ISD into December. Telecom and NERC activity impacting. 9/19/23 - MID work on the DTT on the line is critical to hit the Tline work sequence. 9/18/23 - ISD is tracking to Jan 2024. 8/21/23 - MID is asking for 25 weeks now. rebalanced the clearance so MID comes at the end. Affect COD but not ISD. 8/7/23 - ISD is likely to delay due to MID. MID asking for 20 weeks to do relay work starting in Oct. Meeting next week discuss. 07/27/23 - Schedule is the same for last note. 6/22/23 - Oct 10-20 Tline to set poles for the new SS loop in. 5/15/23 - ISD is pusing to 2024 due to SS construction. Permanent Land acquisitions still with Legal. T_line foundations installed for the loop-in. Clearance to come back in Fall. | Utility - !Telecom! | 1244 | 1244
Q1244 PROXIMA SOLAR T-LINE - EGI (NU) | 5779143 | T.0003770 | 82B | The Q1244 Proxima Solar Project from Cluster 9, proposes to interconnect a 300 megawatt (MW) (net output) Solar + Battery generation facility to Fink 230kV switching station in Stainslaus County, California. The project has a contractual In-service date of: 10/15/23 with a current planned In-service date of: 3/6/24 | Operational | 2020-01-10 |  |  | Merced ¦ Stanislaus | PG&E: Greater Bay Area | Yes | N/A |  | New | Generator Interconnection | Generation Interconnection | 0.02 | NA | 230 | N/A | 2023-10-23 | 2023-10-15 | 2024-03-06 | Transmission Project Review Process data (Resolution E-5252 Attach B | 143 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | NOC: AL 6529-E | 2022-03-16 | Approved | 2022 | COD - 3/18/24 for 162MW 3/6/24 - The Q1244 Proxima Solar project achieved In-Service Date (ISD) today March 6, 2024. This project will generate 300 MW of renewable PV energy and capable of 150 MW of battery storage. The project encompasses approximately 1,100 acres. Final testing of the facility is scheduled for next Wednesday March 13th, 2024 and a Commercial Operation Date letter is expected by the end of the month. To interconnect the customer project, PG&E teams engineered, permitted, tested and placed into service on March 5, 2024 a greenfield looped Switching Station (SS) 11 acres in size named Fink SS. The SS was an EPC contract type project completed through the competitive bid process. Fink SS connects to the 230 kV system approximately 4 miles north of the PG&E Quinto SS and a few miles south of the third party utility owned 230 kV substation Westley substation in Stanislaus County. To interconnect the new 230 kV SS the project called for protective relay upgrades at Los Banos, Quinto SS, and Westley Substation. The PG&E project team coordinated with Modesto Irrigation District (MID) to get the project successful. There was also telecommunications and testing coordination at Westley Substation MID teams and PG&E teams. The energization of Fink SS and Proxima occurred via radial connection. This energization test process spanned a few days to fully test the SS and the third party customer substation. There is remaining work to be completed in order to energize the Fink SS – Westley 230 kV line and is scheduled to finalize April 1, 2024. This project had many barriers to get towards completion. One of the major barriers was permitting and acquiring the land from Stanislaus County. I want to shout out @Everett, Kirsten and @Crossfield, Scott for essentially being a Stanislaus county resource and spending many days waiting at their counter or hand delivering necessary requirements to complete permitting and acquisition activities. This project kicked off in Q2 2018 with a total of over 165 different resources attending project meetings and lending their expertise throughout the project lifecycle. Thank you to everyone involved in this project and helping to bring expertise and professionalism when interacting with NextEra as well as overcome obstacles and provide a quality product. 3/4/24 -Expecting to energize Proxima on 3/6. Fink SS is 3/5. 2/5/25 - PGE Microwave scope between Mt Oso and MID's Wesley Substation cannot be started until Agreements between MID and PGE are made. Scope and Cost impacts being worked out between multi-parties. Interim solution being reviewed but may conflict with the original scope and schedule. 1/23/24 - MID delays have put IC at risk of default. They are incurring costs due to Generators of battery minimally charging. Impacting their Environmental Air Quality Permits if they keep running longer. 1/11/24 - IC does not have their CAISO letter for Permission to Test which was required to put load on Fink thus energizing both SS and Gensite. ISD moved to March after MID work is complete which would no required Q1244 as load to test Fink. 12/14/23 - IC could not get a CAISO clearance until 12/20 due to telecom commissiong, key predecessor activities, and EoY CAISO clearance congestion. Due to the late December date, the PG&E resources to backfeed the customer are insufficient to safely perform the work. 12/13/23 - PTO letter to CAISO on 12/13. Clearance for backfeed 12/20. Requires Battery Loads to Sync Sw Sta. 12/12/23 - Line Connector assemblies were ACSR and not ACSS. This results in temporary re-rate on the line until the repair can be completed. Estimated at 100 to 150K to fix. Mike Milbury and CM Kevin Withrow know the details. 12/7/23 - SCADA/EMS release planned for 12/11/23. Backfeed planned for 12/15. IC is ready to provide 120MWs of load given 24 hours of notice. Potential they can increase that. MID on a call today due to Turlock irrigation district impact.MID needs the Turlock concent to proceed to EoFeb. 11/1/23 - Verify with SQ ISD Trending to Jan 2024 12/15/23 at this time for ISD. 10/2/23 - MID is no longer critical path. Moved to the end of the sequence and affect COD only. Internal only - PM is looking at possibly pulling the ISD into December. Telecom and NERC activity impacting. 9/19/23 - MID work on the DTT on the line is critical to hit the Tline work sequence. 9/18/23 - ISD is tracking to Jan 2024. 8/21/23 - MID is asking for 25 weeks now. rebalanced the clearance so MID comes at the end. Affect COD but not ISD. 8/7/23 - ISD is likely to delay due to MID. MID asking for 20 weeks to do relay work starting in Oct. Meeting next week discuss. 07/27/23 - Schedule is the same for last note. 6/22/23 - Oct 10-20 Tline to set poles for the new SS loop in. 5/15/23 - ISD is pusing to 2024 due to SS construction. Permanent Land acquisitions still with Legal. T_line foundations installed for the loop-in. Clearance to come back in Fall. | Utility - !Telecom! | 1244 | 1244
BEAR CANYON - ENG REVIEW, PPI, PM (IF) | 5779304 | T.0003860 | 82Y | The Q1097 Bear Canyon Project from Cluster 8, proposes to interconnect a 13 megawatt (MW) (net output) Battery generation facility to Geysers #12-Fulton 230kV Line in Lake County, California. The project has a contractual In-service date of: 3/1/24 with a current planned In-service date of: 4/19/24 | Operational | 2023-09-25 |  |  | N/A | PG&E Kern Area | No | N/A |  | New | Other [See Notes] | System Operations | N/A | N/A | N/A | N/A | N/A | 2024-03-01 | 2024-04-19 | Transmission Project Review Process data (Resolution E-5252 Attach B | 49 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | In-Service - 4/18/24 - Commencing Commercial Testing 4/15/24 - Short on 2 points on EMS/SCADA. Next chance to prove comms on 4/19. Pending on other test results. 3/27/24 - Temporary Comms solution required to backfeed until Telco solution is in place 3/4/24 - ISD to be 3/27 2/5/24 - MRS (Managed Router Service) needed. will require Telco configuration. Dates ?. Assume a month delay. 1/4/24 - ASEoD meeting held. This project PA is exceeded and needs reauthorized. PM to go to AM Supv to confirm AM to assist in PA. 1/3/24 to coordinate and schedule Q1097. They need to order the MRS service (end points orders) 12/4/23 - FDP is proceeding. At risk over AT&T ASEoD. 11/1/23 - IC ISD shift to late 2024 10/16/23 - IC (Calpine) think they can rush through the DP process. ISD is at risk due to IC delaying their progress on DP. 10/2/24 - ISD of 2/14/24 remains achievable 8/21/23 - ISD of 2/14/24 remains achievable. IC schedule appears to be tracking. | Customer - !Telecom!
BEAR CANYON - FULTON SUB DTT TX (NU) | 5779305 | T.0003861 | 82W | The Q1097 Bear Canyon Project from Cluster 8, proposes to interconnect a 13 megawatt (MW) (net output) Battery generation facility to Geysers #12-Fulton 230kV Line in Lake County, California. The project has a contractual In-service date of: 3/1/24 with a current planned In-service date of: 4/19/24 | Operational | 2023-09-25 |  |  | N/A | PG&E: North Valley Area | No | N/A |  | New | Other [See Notes] | Special Protection Scheme | N/A | NA | N/A | N/A | N/A | 2024-03-01 | 2024-04-19 | Transmission Project Review Process data (Resolution E-5252 Attach B | 49 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | In-Service - 4/18/24 - Commencing Commercial Testing 4/15/24 - Short on 2 points on EMS/SCADA. Next chance to prove comms on 4/19. Pending on other test results. 3/27/24 - Temporary Comms solution required to backfeed until Telco solution is in place 3/4/24 - ISD to be 3/27 2/5/24 - MRS (Managed Router Service) needed. will require Telco configuration. Dates ?. Assume a month delay. 1/4/24 - ASEoD meeting held. This project PA is exceeded and needs reauthorized. PM to go to AM Supv to confirm AM to assist in PA. 1/3/24 to coordinate and schedule Q1097. They need to order the MRS service (end points orders) 12/4/23 - FDP is proceeding. At risk over AT&T ASEoD. 11/1/23 - IC ISD shift to late 2024 10/16/23 - IC (Calpine) think they can rush through the DP process. ISD is at risk due to IC delaying their progress on DP. 10/2/24 - ISD of 2/14/24 remains achievable 8/21/23 - ISD of 2/14/24 remains achievable. IC schedule appears to be tracking. | Customer - !Telecom! | 1097 | 1097
Q779 WRIGHT SOLAR ACCELERATION WORK (DA) | 5781079 | T.0002321 | 82Y | The Q779 Wright Solar Project from Cluster 4, proposes to interconnect a 200 megawatt (MW) (net output) Solar + Battery generation facility to Los Banos-Panoche #1 230kV in Merced County, California. The project has a contractual In-service date of: 12/31/19 with a current planned In-service date of: 11/2/19 | Operational | 2016-04-01 |  |  | Merced | N/A | Yes | N/A |  | Upgrade/Retrofit | Generator Interconnection | Generation Interconnection | N/A | 53.2803 | N/A | 230 kV | 2019-12-01 | 2022-02-15 | 2019-11-02 | Transmission Project Review Process data (Resolution E-5252 Attach B | -836 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | NOC: AL 5318-E | 2018-06-25 | Approved | 2018 |  | Utility - !GO-851 Process! | 779 | 779
Wilson 115 kV Area Reinforcement | 5781259 | T.0004116 | 61G | The C14P2-NFT03 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Wilson 115kV in Merced County, California. | Planning | 2015-05-01 |  |  | Merced, Merced | PG&E: North Valley Area | No | 2011 | 0 | Upgrade/Retrofit | Reliability | T-Line Capacity | N/A | 22.8151 | N/A | 115 kV | 2027-10-13 | 2015-05-01 | 2028-06-15 | Transmission Project Review Process data (Resolution E-5252 Attach B | 4794 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 01/06/25 - Construction sequence may push the project completion to 2030. TBD on when the Q1895 could come online and if their breaker could come earlier. | Utility - !Telecom! | Q1895 | Q1895
Wilson 115 kV Area Reinforcement | 5781260 | T.0004116 | 61Z | The C14P2-NFT03 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Wilson 115kV in Merced County, California. | Engineering more than 50% complete | 2015-05-01 |  |  | Merced, Merced | PG&E: North Valley Area | No | 2011 | 0 | New | Reliability | T-Line Capacity | N/A | 22.8151 | N/A | 115 kV | 2027-10-27 | 2015-05-01 | 2029-08-16 | Transmission Project Review Process data (Resolution E-5252 Attach B | 5221 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 01/06/25 - Construction sequence may push the project completion to 2030. TBD on when the Q1895 could come online and if their breaker could come earlier. | Utility - !Telecom! | Q1895 | Q1895
Wilson 115 kV Area Reinforcement | 5781261 | T.0004116 | 67A | The C14P2-NFT03 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Wilson 115kV in Merced County, California. | Engineering more than 50% complete | 2022-08-12 |  |  | Merced, Merced | PG&E: North Valley Area | No | N/A | 0 | New | Other [See Notes] | T-Line Capacity | N/A | 22.8151 | N/A | 115 kV | 2027-04-15 | 2022-08-12 | 2028-03-24 | Transmission Project Review Process data (Resolution E-5252 Attach B | 2051 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 01/06/25 - Construction sequence may push the project completion to 2030. TBD on when the Q1895 could come online and if their breaker could come earlier. | Utility - !Telecom! | Q1895 | Q1895
REPLACE PANOCHE 115 KV CB 112 WITH 50 KA | 5782068 | T.0004760 | 82W | The 18rsmt-8 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Panoche Substation 115kV Bus in Fresno County, California. | Operational | 2020-09-01 |  |  | Fresno | PG&E: Greater Bay Area | Yes | N/A | T.0003742 ¦ T.0008338 | Replace | Generator Interconnection | Substation Capacity | N/A | 19.3832 | N/A | 115 kV | 2020-10-26 | 2020-09-01 | 2021-03-05 | Transmission Project Review Process data (Resolution E-5252 Attach B | 185 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom! | Q1135, Q1456 | Q1135 | Q1456
DOS AMIGOS PP-PANOCHE 20032: RECON - | 5782110 | T.0004255 | 82B | The C9P1-F11 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Dos Amigos–Panoche # 3 230 kV Line in Merced County, California. | Engineering more than 50% complete | 2021-09-30 |  |  | Fresno ¦ Merced | PG&E: Greater Bay Area | Yes | N/A | T.0003742 ¦ T.0003005 ¦ T.0002987 ¦ T.0004490 ¦ T.0008538 ¦ 0 ¦ T.0010467 ¦ 0 ¦ T.0010817 ¦ T.0010816 ¦ 0 ¦ 0 ¦ T.0010942 ¦ TBD ¦ 0 ¦ T.0010887 ¦ T.0010738 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 | Upgrade/Retrofit | Generator Interconnection | T-Line Capacity | 23.6 | N/A | 230 | N/A | 2025-04-01 | 2021-09-30 | 2026-05-04 | Transmission Project Review Process data (Resolution E-5252 Attach B | 1677 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | NOC: AL 7392-E | 2024-10-02 | Approved | 2024 | 04/07/25 - Project tracking to ISD on schedule | Utility - !Telecom! | Q1135, Q1127, Q1128, Q1129, Q1713, Q1568, Q1709, 2226-WD, Q1928, Q1930, Q1932, Q1933, Q1934, Q1935, Q1940, Q1953, Q1955, Q1956, Q1963, Q1966, Q1968, Q1970, Q1975, Q1977 | Q1135 | Q1127 | Q1128 | Q1129 | Q1713 | Q1568 | Q1709 | 2226-WD | Q1928 | Q1930 | Q1932 | Q1933 | Q1934 | Q1935 | Q1940 | Q1953 | Q1955 | Q1956 | Q1963
Midway Substation 500 kV Control Building | 5782198 | T.0004292 | 3FA | The C13P2-SPN01 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Midway 500kV in Kern County, California. | Operational | 2022-02-15 |  |  | Buttonwillow CDP, Kern | PG&E: North Valley Area | No | N/A | 0 ¦ T.0010479 ¦ 0 ¦ T.0010025 ¦ 0 ¦ T.0010519 ¦ 0 ¦ T.0010878 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ T.0009383 | Replace | Asset Condition | T-Line Capacity | N/A | 94.5324 | N/A | 500 kV | 2022-08-10 | 2022-02-15 | 2023-03-15 | Transmission Project Review Process data (Resolution E-5252 Attach B | 393 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 07/19/23 - call Scott to verify | Utility - !Telecom! | Q1736, Q1739, Q1740, Q1744, Q1749, Q1751, Q1831, Q1959, Q1968, Q1980, Q1983, Q1992, Q1994, Q1995, Q2001, Q2004, Q2006, Q2010, Q2012, Q2013, Q2015, Q2017, Q1949 | Q1736 | Q1739 | Q1740 | Q1744 | Q1749 | Q1751 | Q1831 | Q1959 | Q1968 | Q1980 | Q1983 | Q1992 | Q1994 | Q1995 | Q2001 | Q2004 | Q2006 | Q2010 | Q2012
Stanislaus-Melones Sw Sta-Manteca #1 115 kV Line Reconductor | 5782307 | T.0004301 | 93C | The C12P2-LDNU2 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Stanislaus-Melones Sw Sta-Manteca #1 115kV Line in San Joaquin County, California. | Operational | 2030-05-01 |  |  | Angels, Calaveras ¦ Calaveras ¦ Copperopolis CDP, Calaveras ¦ Manteca, San Joaquin ¦ Murphys CDP, Calaveras ¦ San Joaquin ¦ Stanislaus ¦ Tuolumne ¦ Vallecito CDP, Calaveras | 0 | No | N/A | T.0007445 ¦ 0 | Replace | Asset Condition | T-Line Capacity | 30.6 | NA | 115 | N/A | 2024-10-24 | 2030-05-01 | 2024-11-04 | Transmission Project Review Process data (Resolution E-5252 Attach B | -2004 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom! | Q1557, Q1904 | Q1557 | Q1904
Q1135 SCARLET (DA) TRANQILITY SS | 5782469 | T.0003742 | 82Y | The Q1135 Scarlet Project from Cluster 8, proposes to interconnect a 400 megawatt (MW) (net output) Solar + Battery generation facility to Tranquility SW 230kV in Fresno County, California. The project has a contractual In-service date of: 11/17/23 with a current planned In-service date of: 12/1/23 | Operational | 2020-12-31 |  |  | Fresno | PG&E: Greater Fresno Area | Yes | N/A | T.0007056 ¦ T.0004255 ¦ T.0007056 ¦ T.0009177 ¦ T.0007289 ¦ T.0003009 ¦ T.0004760 ¦ T.0003792 ¦ T.0003789 ¦ T.0003016 | New | Generator Interconnection | Generation Interconnection | N/A | N/A | N/A | 230 kV | 2022-04-19 | 2023-11-17 | 2023-12-01 | Transmission Project Review Process data (Resolution E-5252 Attach B | 14 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | COD - 4/11/24 for 240MW Summary of commercial letters for the Scarlet Project: 1. Phase 1 (SCARLT_2_SSBSR1 - 100 MW) commercial operation letter released 02-27-24. 2. Phase 2 (SCARLT_2_SSBBT1 – 30 MW) commercial operation letter released 04-01-24. 3. Phase 3 (SCARLT_2_SSASR1 – 100 MW) commercial operation letter released 04-01-24. 4. Phase 4 (SCARLT_2_SSABT1 - 10 MW) commercial operation letter released 04-11-24. 9/7/23 - MMA received, ISD 10/4/23, CODs 2/20/24 through 10/31/25 in 7 phases. 8/7/23 - ISD scheduled Oct 4th subject to MMA being done in time. PPI is 9/20. Need the MMA by the 9/6 to move forward. MMA submitted 7/24. 7/17/23 - Need ICs test reports on time to meet dates. A customer proposed schedule needed to finalize the MMA dates. MMA not submitted- needed by Sept wk 1. PPI Sept 20. May not be achievable given the MMA timeline 6/22/23 - SEECO rep coordination is a critical issue. The IC will get the Rep back out to dial in the switches on 6/21. Inspections had issues with the ICs grounding. 5/16/23 - POCO has OPGW and Manual Switch on same TSP. Requires modification of the TSP to support these. Lesson learned not to have ICs OPGW on same structure. Should have been taken to ground 1 span sooner. 5/1/23 - 6/21/23 ISD is not likely achievable due to IC test reports delayed that were due 4/21/23. AFW needs submitted to change the clearance points all the way to tranquility since the team has to release the POCO pole switch. Ops will do a 30 day break-in. | Customer - Material
Convert Midway Substation 230 kV Bus D to BAAH in order to install bus reactors & RAS | 5782562 | T.0001650 | 67A | The C13P1-KPN02 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Midway 230kV in Kern County, California. | Construction (over 75%) | 2022-04-01 |  |  | Buttonwillow CDP, Kern | PG&E: North Valley Area | No | N/A | 0 ¦ 0 ¦ T.0010479 ¦ T.0010519 ¦ T.0010025 ¦ 0 ¦ 0 ¦ 0 ¦ T.0009383 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 | New | Other [See Notes] | T-Line Capacity | N/A | 94.5324 | N/A | 230 kV | 2021-06-14 | 2022-04-01 | 2025-11-14 | Transmission Project Review Process data (Resolution E-5252 Attach B | 1323 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 04/23/25 - Project is still working through the Prioritization Impacts from 2023 | Utility - !Telecom! | Q1740, Q1749, Q1739, Q1751, Q1744, Q1980, Q1987, Q2001, Q1949, Q1983, Q1995, Q2004, Q2006, Q2010, Q2013, Q2015 | Q1740 | Q1749 | Q1739 | Q1751 | Q1744 | Q1980 | Q1987 | Q2001 | Q1949 | Q1983 | Q1995 | Q2004 | Q2006 | Q2010 | Q2013 | Q2015
Convert Midway Substation 230 kV Bus D to BAAH in order to install bus reactors & RAS | 5782605 | T.0001650 | 94A | The C13P1-KPN02 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Midway 230kV in Kern County, California. | Operational | 2022-04-01 |  |  | Bakersfield, Kern ¦ Buttonwillow CDP, Kern ¦ Greenacres CDP, Kern ¦ Kern ¦ Rosedale CDP, Kern | 0 | No | N/A | 0 ¦ 0 ¦ T.0010479 ¦ T.0010519 ¦ T.0010025 ¦ 0 ¦ 0 ¦ 0 ¦ T.0009383 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 | Upgrade/Retrofit | Reliability | T-Line Capacity | N/A | NA | 230 | N/A | 2021-04-07 | 2022-04-01 | 2023-05-29 | Transmission Project Review Process data (Resolution E-5252 Attach B | 423 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 04/23/25 - Project is still working through the Prioritization Impacts from 2023 | Utility - !Telecom! | Q1740, Q1749, Q1739, Q1751, Q1744, Q1980, Q1987, Q2001, Q1949, Q1983, Q1995, Q2004, Q2006, Q2010, Q2013, Q2015 | Q1740 | Q1749 | Q1739 | Q1751 | Q1744 | Q1980 | Q1987 | Q2001 | Q1949 | Q1983 | Q1995 | Q2004 | Q2006 | Q2010 | Q2013 | Q2015
Q1459 Mulqueeny Ranch Wind 2 | 5782658 | T.0004354 | 82Y | The Q1459 Mulqueeney Ranch Wind 2 Project from Cluster 11, proposes to interconnect a 60 megawatt (MW) (net output) Wind Turbine generation facility to Tesla 230kV in Alameda County, California. The project has a contractual In-service date of: 10/15/25 with a current planned In-service date of: 10/15/25 | Engineering more than 50% complete | 2021-01-14 |  |  | Alameda | 0 | Yes | N/A | T.0004673 ¦ T.0007288 ¦ Maintenance ¦ T.0007288 | Upgrade/Retrofit | Generator Interconnection | T-Line Capacity | N/A | 69.382 | N/A | 230 kV | 2025-08-04 | 2025-10-15 | 2025-10-15 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - Tracking ISD to Jun 2026 attributed to 20rsmt-5 Tesla CB612. | - | 1459 | 1459
Q1277 TELSA SUBSTATION (DA) | 5782660 | T.0004354 | 82Y | The Q1277 Mulqueeney Ranch Wind Project from Cluster 9, proposes to interconnect a 20 megawatt (MW) (net output) Wind Turbine generation facility to Tesla 230kV in Alameda County, California. The project has a contractual In-service date of: 10/15/25 with a current planned In-service date of: 10/15/25 | Construction (under 10%) | 2021-01-14 |  |  | Alameda | PG&E: North Valley Area | Yes | N/A | T.0007288 | New | Generator Interconnection | Generation Interconnection | N/A | N/A | N/A | 230 kV | 2024-09-09 | 2025-10-15 | 2025-10-15 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - ISD 10/15/25. | - | 1277 | 1277
Q1277: TESLA - MULQUEENEY T-LINE | 5782661 | T.0004354 | 82D | The Q1277 Mulqueeney Ranch Wind Project from Cluster 9, proposes to interconnect a 20 megawatt (MW) (net output) Wind Turbine generation facility to Tesla 230kV in Alameda County, California. The project has a contractual In-service date of: 10/15/25 with a current planned In-service date of: 10/15/25 | Engineering more than 50% complete | 2021-01-14 |  |  | Alameda ¦ Merced ¦ San Joaquin ¦ Stanislaus | PG&E: North Valley Area | Yes | N/A | T.0007288 | New | Generator Interconnection | T-Line Capacity | 1.04 | NA | 230 | N/A | 2025-06-20 | 2025-10-15 | 2025-10-15 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - ISD 10/15/25. | - | 1277 | 1277
Q1277 TESLA MULQUEENY (RNU) | 5782662 | T.0004354 | 82W | The Q1277 Mulqueeney Ranch Wind Project from Cluster 9, proposes to interconnect a 20 megawatt (MW) (net output) Wind Turbine generation facility to Tesla 230kV in Alameda County, California. The project has a contractual In-service date of: 10/15/25 with a current planned In-service date of: 10/15/25 | Construction (25%-50%) | 2021-01-14 |  |  | Alameda | 0 | Yes | N/A | T.0007288 | New | Generator Interconnection | Generation Interconnection | N/A | 69.382 | N/A | 230 kV | 2024-06-25 | 2025-10-15 | 2025-10-15 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - ISD 10/15/25. | - | 1277 | 1277
Q1378 - GONZAGA WIND (LOS BANOS SUB DA) | 5783298 | T.0004423 | 82Y | The Q1378 Gonzaga Wind Farm Project from Cluster 10, proposes to interconnect a 76.35 megawatt (MW) (net output) Wind Turbine + Battery generation facility to Los Banos 70kV in Merced County, California. The project has a contractual In-service date of: 11/1/25 with a current planned In-service date of: 12/18/25 | Operational | 2023-07-01 |  |  | Merced | PG&E: North Valley Area | Yes | N/A |  | Upgrade/Retrofit | Generator Interconnection | Generation Interconnection | N/A | 53.2803 | N/A | 70 kV | 2023-07-03 | 2025-11-01 | 2025-11-01 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - Tracking ISD to Q4 2025. Tline material ordered Oct 2024 with Q3 2025 delivery. IC Delays: At risk, IC's design not complete. Construction needs to start Q2 2025. Low confidence ISD in 2025. | Customer - Construction Delays | 1378 | 1378
Q1378 GONZAGA WIND T-LINE DA | 5783299 | T.0004423 | 82D | The Q1378 Gonzaga Wind Farm Project from Cluster 10, proposes to interconnect a 76.35 megawatt (MW) (net output) Wind Turbine + Battery generation facility to Los Banos 70kV in Merced County, California. The project has a contractual In-service date of: 11/1/25 with a current planned In-service date of: 12/18/25 | Engineering more than 50% complete | 2023-07-01 |  |  | Merced | PG&E: North Valley Area | Yes | N/A |  | New | Generator Interconnection | Generation Interconnection | 12 | NA | 70 | N/A | 2025-11-07 | 2025-11-01 | 2025-11-01 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - Tracking ISD to Q4 2025. Tline material ordered Oct 2024 with Q3 2025 delivery. IC Delays: At risk, IC's design not complete. Construction needs to start Q2 2025. Low confidence ISD in 2025. | Customer - Construction Delays | 1378 | 1378
Q1378 - GONZAGA WIND DA GENSITE | 5783300 | T.0004423 | 82Y | The Q1378 Gonzaga Wind Farm Project from Cluster 10, proposes to interconnect a 76.35 megawatt (MW) (net output) Wind Turbine + Battery generation facility to Los Banos 70kV in Merced County, California. The project has a contractual In-service date of: 11/1/25 with a current planned In-service date of: 12/18/25 | Engineering more than 50% complete | 2023-07-01 |  |  | Merced | PG&E: North Valley Area | Yes | N/A |  | Upgrade/Retrofit | Generator Interconnection | Generation Interconnection | N/A | 53.2803 | N/A | 70 kV | 2025-05-02 | 2025-11-01 | 2025-11-01 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - Tracking ISD to Q4 2025. Tline material ordered Oct 2024 with Q3 2025 delivery. IC Delays: At risk, IC's design not complete. Construction needs to start Q2 2025. Low confidence ISD in 2025. | Customer - Construction Delays | 1378 | 1378
Q1378 - LOS BANOS SUBSTATION RNU | 5783302 | T.0004423 | 82W | The Q1378 Gonzaga Wind Farm Project from Cluster 10, proposes to interconnect a 76.35 megawatt (MW) (net output) Wind Turbine + Battery generation facility to Los Banos 70kV in Merced County, California. The project has a contractual In-service date of: 11/1/25 with a current planned In-service date of: 12/18/25 | Operational | 2023-07-01 |  |  | Merced | 0 | Yes | N/A |  | New | Generator Interconnection | Generation Interconnection | N/A | 53.2803 | N/A | 70 kV | 2023-07-03 | 2025-11-01 | 2025-11-01 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - Tracking ISD to Q4 2025. Tline material ordered Oct 2024 with Q3 2025 delivery. IC Delays: At risk, IC's design not complete. Construction needs to start Q2 2025. Low confidence ISD in 2025. | Customer - Construction Delays | 1378 | 1378
Q1127 LITTLE BEAR 3 MENDOTA SUB TLINE DA | 5783400 | T.0003005 | 82Y | The Q1127 Little Bear 3 Project from Cluster 8, proposes to interconnect a 20 megawatt (MW) (net output) Solar generation facility to Mendota 115kV in Fresno County, California. The project has a contractual In-service date of: 4/1/20 with a current planned In-service date of: 10/30/20 | Operational | 2021-03-12 |  |  | Madera | N/A | No | N/A | T.0003009 ¦ T.0003792 ¦ T.0003789 ¦ T.0003016 ¦ T.0004255 ¦ T.0009177 | Replace | Emergency Event | Age/Condition - Replace Relays | N/A | 13.266 | N/A | 230 kV | 2020-06-01 | 2022-02-15 | 2020-10-30 | Transmission Project Review Process data (Resolution E-5252 Attach B | -473 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | -
Wilson 115 kV Area Reinforcement | 5783478 | T.0004116 | 60C | The C14P2-NFT03 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Wilson 115kV in Merced County, California. | Engineering more than 50% complete | 2015-05-01 |  |  | Merced ¦ Merced, Merced | PG&E: North Valley Area | No | 2011 | 0 | Upgrade/Retrofit | Reliability | T-Line Capacity | N/A | NA | 230 ¦ 115 | N/A | 2027-03-02 | 2015-05-01 | 2027-12-15 | Transmission Project Review Process data (Resolution E-5252 Attach B | 4611 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 01/06/25 - Construction sequence may push the project completion to 2030. TBD on when the Q1895 could come online and if their breaker could come earlier. | Utility - !Telecom! | Q1895 | Q1895
Q1129 LUNA VALLEY SOLAR (DA) GEN SITE | 5783479 | T.0004490 | 82Y | The Q1129 Luna Valley Solar Project from Cluster 8, proposes to interconnect a 200 megawatt (MW) (net output) Solar + Battery generation facility to Tranquility SW 230kV in Fresno County, California. The project has a contractual In-service date of: 6/30/25 with a current planned In-service date of: 4/7/25 | Engineering more than 50% complete | 2015-05-01 |  |  | Merced, Merced | PG&E: North Valley Area | No | 2011 | T.0003009 ¦ T.0003792 ¦ T.0003789 ¦ T.0003016 ¦ T.0007056 ¦ T.0004255 ¦ T.0007056 ¦ T.0009177 | Upgrade/Retrofit | Reliability | Bus Upgrade | N/A | 22.8151 | N/A | 230 kV | 2026-12-21 | 2025-06-30 | 2025-04-07 | Transmission Project Review Process data (Resolution E-5252 Attach B | -84 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 04/14/25 - Backfeed complete 4/7/25. The Luna Valley Q1129 project was released to PG&E Operations on Monday April 7, 2025 at approximately 1528 and subsequently given permission to Parallel for Test Purposes on Wednesday April 9, 2025. The project will contribute 200 Megawatts (MWs) to the PG&E renewable generation portfolio by July 2025. | - | 1129 | 1129
Q1129 LUNA VALLEY SOLAR (DA) 230KV TRANQ | 5783482 | T.0004490 | 82Y | The Q1129 Luna Valley Solar Project from Cluster 8, proposes to interconnect a 200 megawatt (MW) (net output) Solar + Battery generation facility to Tranquility SW 230kV in Fresno County, California. The project has a contractual In-service date of: 6/30/25 with a current planned In-service date of: 4/7/25 | Engineering more than 50% complete | 2015-05-01 |  |  | Merced, Merced | PG&E: North Valley Area | No | 2011 | T.0003009 ¦ T.0003792 ¦ T.0003789 ¦ T.0003016 ¦ T.0007056 ¦ T.0004255 ¦ T.0007056 ¦ T.0009177 | Upgrade/Retrofit | Reliability | Bus Upgrade | N/A | 22.8151 | N/A | 230 kV | 2026-12-21 | 2025-06-30 | 2025-04-07 | Transmission Project Review Process data (Resolution E-5252 Attach B | -84 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 04/14/25 - Backfeed complete 4/7/25. The Luna Valley Q1129 project was released to PG&E Operations on Monday April 7, 2025 at approximately 1528 and subsequently given permission to Parallel for Test Purposes on Wednesday April 9, 2025. The project will contribute 200 Megawatts (MWs) to the PG&E renewable generation portfolio by July 2025. | - | 1129 | 1129
Q1129 LUNA VALLEY SOLAR (DA) T-LINE | 5783483 | T.0004490 | 82D | The Q1129 Luna Valley Solar Project from Cluster 8, proposes to interconnect a 200 megawatt (MW) (net output) Solar + Battery generation facility to Tranquility SW 230kV in Fresno County, California. The project has a contractual In-service date of: 6/30/25 with a current planned In-service date of: 4/7/25 | Engineering more than 50% complete | 2015-05-01 |  |  | Merced, Merced | PG&E: North Valley Area | No | 2011 | T.0003009 ¦ T.0003792 ¦ T.0003789 ¦ T.0003016 ¦ T.0007056 ¦ T.0004255 ¦ T.0007056 ¦ T.0009177 | Upgrade/Retrofit | Reliability | Bus Upgrade | N/A | N/A | N/A | 230 kV | 2026-12-21 | 2025-06-30 | 2025-04-07 | Transmission Project Review Process data (Resolution E-5252 Attach B | -84 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 04/14/25 - Backfeed complete 4/7/25. The Luna Valley Q1129 project was released to PG&E Operations on Monday April 7, 2025 at approximately 1528 and subsequently given permission to Parallel for Test Purposes on Wednesday April 9, 2025. The project will contribute 200 Megawatts (MWs) to the PG&E renewable generation portfolio by July 2025. | - | 1129 | 1129
Wilson 115 kV Area Reinforcement | 5783618 | T.0004116 | 61G | The C14P2-NFT03 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Wilson 115kV in Merced County, California. | Engineering more than 50% complete | 2015-05-01 |  |  | Merced, Merced | PG&E: North Valley Area | No | 2011 | 0 | Upgrade/Retrofit | Reliability | T-Line Capacity | N/A | 22.8151 | N/A | 230 kV | 2026-12-21 | 2015-05-01 | 2029-02-09 | Transmission Project Review Process data (Resolution E-5252 Attach B | 5033 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 01/06/25 - Construction sequence may push the project completion to 2030. TBD on when the Q1895 could come online and if their breaker could come earlier. | Utility - !Telecom! | Q1895 | Q1895
Reconductor Bellota-Warnerville 230 kV Line | 5783639 | T.0000043 | 61X | The C13P1-FPT02 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Bellota-Warnerville 230kV Line in Madera County, California. | Operational | 2025-05-01 |  |  | San Joaquin | PG&E: North Valley Area | No | 2013 | T.0010467 ¦ T.0008538 ¦ T.0010817 ¦ T.0010816 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 | Upgrade/Retrofit | Policy | T-Line Capacity | N/A | 14.7513 | N/A | 230 kV | 2023-02-16 | 2025-05-01 | 2023-04-28 | Transmission Project Review Process data (Resolution E-5252 Attach B | -734 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 04/04/24 - Final ISD 3/30/24 6/26/23 - B-W ISD was 04/28/2023. B-C ISD is 4/30/24 likely a $2M flex into 2024 for remaining phase. | Utility - !Telecom!
Stanislaus-Melones Sw STA-Riverbank Jct Sw Sta 115 kV Line Reconductor | 5783641 | T.0004515 | 93C | The C12P2-LDNU4 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Stanislaus-Melones SW STA-Riverbank Jct Sw Sta 115kV Line in San Joaquin County, California. | Engineering more than 50% complete | N/A |  |  | Angels, Calaveras ¦ Calaveras ¦ Copperopolis CDP, Calaveras ¦ Manteca, San Joaquin ¦ Murphys CDP, Calaveras ¦ San Joaquin ¦ Stanislaus ¦ Tuolumne ¦ Vallecito CDP, Calaveras | 0 | No | N/A | T.0007445 | Replace | Asset Condition | T-Line Capacity | 15.1 | NA | 115 | N/A | 2028-12-20 | 2026-01-29 | 2029-01-19 | Transmission Project Review Process data (Resolution E-5252 Attach B | 1086 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom! | Q1557 | Q1557
Q1139 WESTLANDS SOLAR BLUE GENSITE DA | 5783859 | T.0004560 | 82Y | The Q1139 Westlands Solar Blue Project from Cluster 8, proposes to interconnect a 250 megawatt (MW) (net output) Solar + Battery generation facility to Gates 230kV in Fresno County, California. The project has a contractual In-service date of: 7/24/23 with a current planned In-service date of: 7/26/23 | Operational | 2021-11-01 |  |  | San Joaquin | PG&E: North Valley Area | Yes | N/A | T.0007289 ¦ T.0003009 ¦ T.0003789 | New | Generator Interconnection | Generation Interconnection | N/A | 6.1366 | N/A | 60 kV | 2022-02-01 | 2023-07-24 | 2023-07-26 | Transmission Project Review Process data (Resolution E-5252 Attach B | 2 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | NOC: AL 5770-E | 2020-02-25 | Approved | 2020 | COD - 11/14/23 for 250MW In-service 7/26/23 | - | 1139 | 1139
Q1120 CHESTNUT WESTSIDE GENSITE DA | 5783865 | T.0004565 | 82Y | The Q1120 Castanea Project from Cluster 8, proposes to interconnect a 150 megawatt (MW) (net output) Solar + Battery generation facility to Gates 230kV in Fresno County, California. The project has a contractual In-service date of: 4/17/23 with a current planned In-service date of: 8/9/23 | Operational | 2021-11-01 |  |  | San Joaquin | N/A | Yes | N/A | T.0007289 ¦ T.0003009 ¦ T.0003789 | New | Generator Interconnection | Generation Interconnection | N/A | N/A | N/A | 60 kV | 2022-02-01 | 2023-04-17 | 2023-08-09 | Transmission Project Review Process data (Resolution E-5252 Attach B | 114 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | NOC: AL 5770-E | 2020-02-25 | Approved | 2020 | COD - 11/2/23 for 135MW BESS + 150MW PV In-service 8/9/23 | Customer - Bundling Dependencies | 1120 | 1120
Q1272 - WEBER SUBSTATION DA | 5783869 | T.0004561 | 82Y | The Q1272 Cascade Energy Storage Project from Cluster 9, proposes to interconnect a 25 megawatt (MW) (net output) Battery generation facility to Weber 60kV in San Joaquin County, California. The project has a contractual In-service date of: 1/12/23 with a current planned In-service date of: 5/31/23 | Operational | 2021-11-01 |  |  | San Joaquin | PG&E: North Valley Area | Yes | N/A | T.0004561 | New | Generator Interconnection | Generation Interconnection | N/A | 6.1366 | N/A | 60 kV | 2022-02-01 | 2023-01-12 | 2023-05-31 | Transmission Project Review Process data (Resolution E-5252 Attach B | 139 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | NOC: AL 5770-E | 2020-02-25 | Approved | 2020 | COD - 8/31/23 for 25MW In-service 5/31/23 | Utility - Bundling Dependencies | 1272 | 1272
Q1272 - CASCADE GEN SITE DA | 5783870 | T.0004561 | 82Y | The Q1272 Cascade Energy Storage Project from Cluster 9, proposes to interconnect a 25 megawatt (MW) (net output) Battery generation facility to Weber 60kV in San Joaquin County, California. The project has a contractual In-service date of: 1/12/23 with a current planned In-service date of: 5/31/23 | Operational | 2021-11-01 |  |  | Kennedy CDP, San Joaquin ¦ San Joaquin ¦ Stockton, San Joaquin | PG&E: North Valley Area | Yes | N/A | T.0004561 | New | Generator Interconnection | Generation Interconnection | 0.15 | NA | 60 | N/A | 2022-04-01 | 2023-01-12 | 2023-05-31 | Transmission Project Review Process data (Resolution E-5252 Attach B | 139 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | NOC: AL 5770-E | 2020-02-25 | Approved | 2020 | COD - 8/31/23 for 25MW In-service 5/31/23 | Utility - Bundling Dependencies | 1272 | 1272
Q1272 CASCADE ENERGY T-LINE DA | 5783872 | T.0004561 | 82D | The Q1272 Cascade Energy Storage Project from Cluster 9, proposes to interconnect a 25 megawatt (MW) (net output) Battery generation facility to Weber 60kV in San Joaquin County, California. The project has a contractual In-service date of: 1/12/23 with a current planned In-service date of: 5/31/23 | Operational | 2021-11-01 |  |  | Kennedy CDP, San Joaquin ¦ San Joaquin ¦ Stockton, San Joaquin | PG&E: North Valley Area | Yes | N/A | T.0004561 | New | Generator Interconnection | Generation Interconnection | 0.15 | N/A | 60 | N/A | 2022-04-01 | 2023-01-12 | 2023-05-31 | Transmission Project Review Process data (Resolution E-5252 Attach B | 139 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | NOC: AL 5770-E | 2020-02-25 | Approved | 2020 | COD - 8/31/23 for 25MW In-service 5/31/23 | Utility - Bundling Dependencies | 1272 | 1272
Q1272 - WEBER SUBSTATION RNU | 5783873 | T.0004561 | 82W | The Q1272 Cascade Energy Storage Project from Cluster 9, proposes to interconnect a 25 megawatt (MW) (net output) Battery generation facility to Weber 60kV in San Joaquin County, California. The project has a contractual In-service date of: 1/12/23 with a current planned In-service date of: 5/31/23 | Operational | 2021-11-01 |  |  | San Joaquin | 0 | Yes | N/A | T.0004561 | New | Generator Interconnection | Generation Interconnection | N/A | 6.1366 | N/A | 60 kV | 2022-02-01 | 2023-01-12 | 2023-05-31 | Transmission Project Review Process data (Resolution E-5252 Attach B | 139 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | COD - 8/31/23 for 25MW In-service 5/31/23 | Utility - Bundling Dependencies | 1272 | 1272
Q1272 CASCADE ENERGY T-LINE RNU | 5783874 | T.0004561 | 82B | The Q1272 Cascade Energy Storage Project from Cluster 9, proposes to interconnect a 25 megawatt (MW) (net output) Battery generation facility to Weber 60kV in San Joaquin County, California. The project has a contractual In-service date of: 1/12/23 with a current planned In-service date of: 5/31/23 | Operational | 2021-11-01 |  |  | Kennedy CDP, San Joaquin ¦ San Joaquin ¦ Stockton, San Joaquin | 0 | Yes | N/A | T.0004561 | New | Generator Interconnection | T-Line Capacity | 0.15 | N/A | 60 | N/A | 2022-04-09 | 2023-01-12 | 2023-05-31 | Transmission Project Review Process data (Resolution E-5252 Attach B | 139 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | NOC: AL 5770-E | 2020-02-25 | Approved | 2020 | COD - 8/31/23 for 25MW In-service 5/31/23 | Utility - Bundling Dependencies | 1272 | 1272
Q1272 - STOCKTON A-WEBER #3 RECON RNU | 5783875 | T.0004561 | 82B | The C9P2-N09 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Stockton A-Weber #3 60 kV Line in San Joaquin County, California. | Operational | 2021-11-01 |  |  | Kennedy CDP, San Joaquin ¦ San Joaquin ¦ Stockton, San Joaquin | 0 | Yes | N/A | T.0004561 | Upgrade/Retrofit | Generator Interconnection | T-Line Capacity | 0.9 | N/A | 60 | N/A | 2022-01-18 | 2021-11-01 | 2022-02-28 | Transmission Project Review Process data (Resolution E-5252 Attach B | 119 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | NOC: AL 5770-E | 2020-02-25 | Approved | 2020 | In-service 3/31/23 | Utility - !Telecom! | Q1272 | Q1272
Q1275 KOLA - TESLA SUBSTATION DA | 5783900 | T.0004563 | 82Y | The Q1275 Kola Project from Cluster 9, proposes to interconnect a 418 megawatt (MW) (net output) Battery generation facility to Tesla 230kV in Livermore County, California. The project has a contractual In-service date of: 4/15/25 with a current planned In-service date of: 7/11/25 | Construction (10%-25%) | 2023-01-10 |  |  | Alameda | PG&E: North Valley Area | Yes | N/A | T.0007288 | New | Generator Interconnection | Generation Interconnection | N/A | 69.382 | N/A | 115 kV | 2024-08-19 | 2025-04-15 | 2025-07-11 | Transmission Project Review Process data (Resolution E-5252 Attach B | 87 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - ISD tracking July 2025. PG&E UG work at Tesla underway but delayed with expected ISD July 15 2025. 04/08/25 - ISD July 2025, delay due to Tline work schedule and resource constraints including Material delays. 03/11/25 - Tracking ISD in May 2025. Tesla CB642/CB542 PNU remain. Others removed. | Utility - Construction Delays | 1275 | 1275
Q1275 - KOLA GEN SITE DA | 5783901 | T.0004563 | 82Y | The Q1275 Kola Project from Cluster 9, proposes to interconnect a 418 megawatt (MW) (net output) Battery generation facility to Tesla 230kV in Livermore County, California. The project has a contractual In-service date of: 4/15/25 with a current planned In-service date of: 7/11/25 | Construction (over 75%) | 2023-01-10 |  |  | Alameda | PG&E: North Valley Area | Yes | N/A | T.0007288 | Upgrade/Retrofit | Generator Interconnection | Generation Interconnection | N/A | 69.382 | N/A | 115 kV | 2024-10-31 | 2025-04-15 | 2025-07-11 | Transmission Project Review Process data (Resolution E-5252 Attach B | 87 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - ISD tracking July 2025. PG&E UG work at Tesla underway but delayed with expected ISD July 15 2025. 04/08/25 - ISD July 2025, delay due to Tline work schedule and resource constraints including Material delays. 03/11/25 - Tracking ISD in May 2025. Tesla CB642/CB542 PNU remain. Others removed. | Utility - Construction Delays | 1275 | 1275
Q1275 KOLA T-LINE DA | 5783903 | T.0004563 | 82D | The Q1275 Kola Project from Cluster 9, proposes to interconnect a 418 megawatt (MW) (net output) Battery generation facility to Tesla 230kV in Livermore County, California. The project has a contractual In-service date of: 4/15/25 with a current planned In-service date of: 7/11/25 | Construction (under 10%) | 2023-01-10 |  |  | Alameda ¦ Fremont, Alameda ¦ Livermore, Alameda ¦ Sunol CDP, Alameda | PG&E: Greater Fresno Area | Yes | N/A | T.0007288 | New | Generator Interconnection | Generation Interconnection | 4 | N/A | 115 | N/A | 2024-09-10 | 2025-04-15 | 2025-07-11 | Transmission Project Review Process data (Resolution E-5252 Attach B | 87 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - ISD tracking July 2025. PG&E UG work at Tesla underway but delayed with expected ISD July 15 2025. 04/08/25 - ISD July 2025, delay due to Tline work schedule and resource constraints including Material delays. 03/11/25 - Tracking ISD in May 2025. Tesla CB642/CB542 PNU remain. Others removed. | Utility - Construction Delays
Q1275 - TESLA SUBSTATION RNU | 5783904 | T.0004563 | 82W | The Q1275 Kola Project from Cluster 9, proposes to interconnect a 418 megawatt (MW) (net output) Battery generation facility to Tesla 230kV in Livermore County, California. The project has a contractual In-service date of: 4/15/25 with a current planned In-service date of: 7/11/25 | Construction (10%-25%) | 2023-01-10 |  |  | Alameda | 0 | Yes | N/A | T.0007288 | New | Generator Interconnection | Generation Interconnection | N/A | 69.382 | N/A | 115 kV | 2024-08-19 | 2025-04-15 | 2025-07-11 | Transmission Project Review Process data (Resolution E-5252 Attach B | 87 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - ISD tracking July 2025. PG&E UG work at Tesla underway but delayed with expected ISD July 15 2025. 04/08/25 - ISD July 2025, delay due to Tline work schedule and resource constraints including Material delays. 03/11/25 - Tracking ISD in May 2025. Tesla CB642/CB542 PNU remain. Others removed. | Utility - Construction Delays | 1275 | 1275
Q1103 CENTRAL 40 TLINE DA | 5784027 | T.0003766 | 82D | The Q1103 Central 40 Project from Cluster 8, proposes to interconnect a 40 megawatt (MW) (net output) Solar generation facility to Miller #1 115kV Line in Merced County, California. The project has a contractual In-service date of: 11/1/20 with a current planned In-service date of: 12/7/20 | Operational | 2019-06-15 |  |  | N/A | 0 | No | N/A |  | New | Other [See Notes] | System Operations | N/A | NA | N/A | N/A | 2019-02-07 | 2022-02-15 | 2020-12-07 | Transmission Project Review Process data (Resolution E-5252 Attach B | -435 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | - | 1103 | 1103
Q1363 SANDHILL GENERATION SITE (DA) | 5784059 | T.0004575 | 82Y | The Q1363 Sandhill C DTTs Project from Cluster 10, proposes to interconnect a 80.8 megawatt (MW) (net output) Wind Turbine generation facility to Delta Switching Yard-Tesla 230kV Line in Alameda County, California. The project has a contractual In-service date of: 3/21/25 with a current planned In-service date of: 10/8/25 | Operational | 2019-06-15 |  |  | N/A | PG&E: North Valley Area | No | N/A | T.0004673 ¦ T.0004673 | New | Other [See Notes] | System Operations | N/A | NA | N/A | N/A | 2019-02-07 | 2025-03-21 | 2025-10-08 | Transmission Project Review Process data (Resolution E-5252 Attach B | 201 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - MMA to push out project for a few years. IC needs to submit MMA. IC not engaged for nearly a year. | Customer - Construction Delays | 1363 | 1363
Q1363 SANDHILL - TESLA SUBSTATION RNU | 5784062 | T.0004575 | 82W | The Q1363 Sandhill C DTTs Project from Cluster 10, proposes to interconnect a 80.8 megawatt (MW) (net output) Wind Turbine generation facility to Delta Switching Yard-Tesla 230kV Line in Alameda County, California. The project has a contractual In-service date of: 3/21/25 with a current planned In-service date of: 10/8/25 | Operational | 2019-06-15 |  |  | N/A | PG&E Kern Area | No | N/A | T.0004673 ¦ T.0004673 | New | Other [See Notes] | System Operations | N/A | NA | N/A | N/A | 2019-02-07 | 2025-03-21 | 2025-10-08 | Transmission Project Review Process data (Resolution E-5252 Attach B | 201 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - MMA to push out project for a few years. IC needs to submit MMA. IC not engaged for nearly a year. | Customer - Construction Delays | 1363 | 1363
Q1116 SIERRA ENERGY GEN SITE DA | 5784358 | T.0004624 | 82Y | The Q1116 Ultrapower Chinese Station Project from Cluster 8, proposes to interconnect a 10 megawatt (MW) (net output) Battery generation facility to Melones-Curtis 115kV Line in Tuolumne County, California. The project has a contractual In-service date of: 7/21/22 with a current planned In-service date of: 7/21/22 | Operational | 2020-12-18 |  |  | Folsom, Sacramento | PG&E: North Valley Area | No | N/A |  | Replace | Asset Condition | Age/Condition - Replace 230/115/70/60 kV Breakers | N/A | 12.8702 | N/A | 230 kV | 2019-06-05 | 2022-07-21 | 2022-07-21 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/15/23 - PTA notice. In-sync and COD dates to be coordinated for EoY. | Customer - Material | 1116 | 1116
Q1116 SIERRA ENERGY GEN SITE DA MTR | 5784359 | T.0004624 | 82Y | The Q1116 Ultrapower Chinese Station Project from Cluster 8, proposes to interconnect a 10 megawatt (MW) (net output) Battery generation facility to Melones-Curtis 115kV Line in Tuolumne County, California. The project has a contractual In-service date of: 7/21/22 with a current planned In-service date of: 7/21/22 | Operational | 2020-12-18 |  |  | Folsom, Sacramento | PG&E: North Valley Area | No | N/A |  | New | Asset Condition | Generation Interconnection | N/A | 12.8702 | N/A | 230 kV | 2019-06-05 | 2022-07-21 | 2022-07-21 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/15/23 - PTA notice. In-sync and COD dates to be coordinated for EoY. | Customer - Material | 1116 | 1116
Q1116 SIERRA ENERGY MELONES SS RNU | 5784360 | T.0004624 | 82W | The Q1116 Ultrapower Chinese Station Project from Cluster 8, proposes to interconnect a 10 megawatt (MW) (net output) Battery generation facility to Melones-Curtis 115kV Line in Tuolumne County, California. The project has a contractual In-service date of: 7/21/22 with a current planned In-service date of: 7/21/22 | Operational | 2020-12-18 |  |  | Folsom, Sacramento | 0 | No | N/A |  | Replace | Asset Condition | Special Protection Scheme | N/A | 12.8702 | N/A | 230 kV | 2019-06-05 | 2022-07-21 | 2022-07-21 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/15/23 - PTA notice. In-sync and COD dates to be coordinated for EoY. | Customer - Material | 1116 | 1116
Q1116 SIERRA ENERGY CURTIS SUB RNU | 5784362 | T.0004624 | 82W | The Q1116 Ultrapower Chinese Station Project from Cluster 8, proposes to interconnect a 10 megawatt (MW) (net output) Battery generation facility to Melones-Curtis 115kV Line in Tuolumne County, California. The project has a contractual In-service date of: 7/21/22 with a current planned In-service date of: 7/21/22 | Operational | 2020-12-18 |  |  | Folsom, Sacramento | 0 | No | N/A |  | Replace | Asset Condition | Special Protection Scheme | N/A | 12.8702 | N/A | 230 kV | 2019-06-05 | 2022-07-21 | 2022-07-21 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/15/23 - PTA notice. In-sync and COD dates to be coordinated for EoY. | Customer - Material | 1116 | 1116
Q1028-1029 LITTLE BEAR 1 2 DA MTR | 5784364 | T.0002465 | 82Y | The Q1028_Q1029 Little Bear Solar 1 & 2 Project from Cluster 7, proposes to interconnect a 40 megawatt (MW) (net output) + generation facility to Mendota 115kV in Fresno County, California. The project has a contractual In-service date of: with a current planned In-service date of: 9/21/20 | Operational | 2020-12-18 |  |  | Folsom, Sacramento | s500 | No | N/A |  | Replace | Asset Condition | Age/Condition - Replace 230/115/70/60 kV Breakers | N/A | 12.8702 | N/A | 230 kV | 2019-06-05 | 2020-11-30 | 2020-09-21 | Transmission Project Review Process data (Resolution E-5252 Attach B | -70 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | -
Stanislaus-Melones Sw Sta-Manteca #1 115 kV Line Reconductor | 5784382 | T.0004301 | 66A | The C12P2-LDNU2 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Stanislaus-Melones Sw Sta-Manteca #1 115kV Line in San Joaquin County, California. | Engineering more than 50% complete | 2030-05-01 |  |  | Tuolumne | PG&E: North Valley Area | No | N/A | T.0007445 ¦ 0 | Upgrade/Retrofit | Asset Condition | T-Line Capacity | N/A | 1.932 | N/A | 115 kV | 2025-09-27 | 2030-05-01 | 2028-10-12 | Transmission Project Review Process data (Resolution E-5252 Attach B | -566 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom! | Q1557, Q1904 | Q1557 | Q1904
Q1472 - MOSS LANDING SUBSTATION DA | 5784780 | T.0004662 | 82Y | The Q1472 Dallas Energy (400 MW) Project from Cluster 11, proposes to interconnect a 400 megawatt (MW) (net output) Battery generation facility to Moss Landing 500kV in Monterey County, California. The project has a contractual In-service date of: 11/15/20 with a current planned In-service date of: 11/20/20 | Operational | 2020-08-01 |  |  | Monterey | PG&E: North Valley Area | Yes | N/A |  | New | Generator Interconnection | Generation Interconnection | N/A | 41.3213 | N/A | 500 kV | 2020-07-15 | 2022-02-15 | 2020-11-20 | Transmission Project Review Process data (Resolution E-5252 Attach B | -452 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | - | 1472 | 1472
Q1472 - DALLAS GEN SITE DA | 5784782 | T.0004662 | 82Y | The Q1472 Dallas Energy (400 MW) Project from Cluster 11, proposes to interconnect a 400 megawatt (MW) (net output) Battery generation facility to Moss Landing 500kV in Monterey County, California. The project has a contractual In-service date of: 11/15/20 with a current planned In-service date of: 11/20/20 | Operational | 2020-08-01 |  |  | Monterey | PG&E: North Valley Area | Yes | N/A |  | New | Generator Interconnection | Generation Interconnection | N/A | 41.3213 | N/A | 500 kV | 2020-07-15 | 2022-02-15 | 2020-11-20 | Transmission Project Review Process data (Resolution E-5252 Attach B | -452 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | - | 1472 | 1472
Q1472 - DALLAS GEN SITE MTR | 5784783 | T.0004662 | 82Y | The Q1472 Dallas Energy (400 MW) Project from Cluster 11, proposes to interconnect a 400 megawatt (MW) (net output) Battery generation facility to Moss Landing 500kV in Monterey County, California. The project has a contractual In-service date of: 11/15/20 with a current planned In-service date of: 11/20/20 | Operational | 2020-08-01 |  |  | Monterey | PG&E: North Valley Area | Yes | N/A |  | New | Generator Interconnection | Generation Interconnection | N/A | 41.3213 | N/A | 500 kV | 2020-07-15 | 2022-02-15 | 2020-11-20 | Transmission Project Review Process data (Resolution E-5252 Attach B | -452 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | - | 1472 | 1472
Q1472 - MOSS LANDING SUBSTATION RNU | 5784784 | T.0004662 | 82W | The Q1472 Dallas Energy (400 MW) Project from Cluster 11, proposes to interconnect a 400 megawatt (MW) (net output) Battery generation facility to Moss Landing 500kV in Monterey County, California. The project has a contractual In-service date of: 11/15/20 with a current planned In-service date of: 11/20/20 | Operational | 2020-08-01 |  |  | Monterey | 0 | Yes | N/A |  | New | Generator Interconnection | Generation Interconnection | N/A | N/A | N/A | 500 kV | 2020-07-15 | 2022-02-15 | 2020-11-20 | Transmission Project Review Process data (Resolution E-5252 Attach B | -452 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | - | 1472 | 1472
Tesla Substation 230 kV bus reactors C-D,D-E circuit breakers 372, 382 and 842 overstress | 5784841 | T.0004673 | 61Y | The C11P2-NC01 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Tesla 230kV in Alameda County, California. | Operational | 2023-12-31 |  |  | Alameda | PG&E: North Valley Area | No | 2019 | T.0007195 ¦ T.0005689 ¦ T.0004575 ¦ T.0005689 ¦ T.0004575 ¦ T.0008307 ¦ T.0010648 ¦ T.0010478 ¦ T.0008918 ¦ T.0004354 | Upgrade/Retrofit | Reliability | T-Line Capacity | N/A | 69.382 | N/A | 230 kV | 2022-04-19 | 2023-12-31 | 2023-06-14 | Transmission Project Review Process data (Resolution E-5252 Attach B | -200 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 03/17/25 - Currently energized, remaining punch list items to be completed then start project close out 4/3/24 - Project went ISD 3/25. 12/12/23 - TLine work. 9/25/23 - ISD 3/29/24 is still achievable. 7/31/23 - ISD is achievable. 6/26/23 - ISD is for the last asset going in service. By Nov 2023 3/4 reactors will be in-service. Then the 4th will start. 5-31-23 - On track. See notes below. D-E on track with test program in June 2023. C-D - starts construction June 20. On track to be online by Q1 2024. | Utility - !Telecom! | Q1270, Q1349, Q1363, Q1349, Q1363, Q1461, Q1683, Q1691, Q1702, Q1459 | Q1270 | Q1349 | Q1363 | Q1349 | Q1363 | Q1461 | Q1683 | Q1691 | Q1702 | Q1459
Q1454 HUMMINGBIRD (DA) METCALF SUB | 5784843 | T.0004676 | 82Y | The Q1454 Hummingbird Energy Storage Project from Cluster 11, proposes to interconnect a 75 megawatt (MW) (net output) Battery generation facility to Metcalf 115kV in Santa Clara County, California. The project has a contractual In-service date of: 2/24/25 with a current planned In-service date of: 8/26/25 | Operational | 2020-08-01 |  |  | Santa Clara | PG&E: North Valley Area | Yes | N/A |  | New | Generator Interconnection | Generation Interconnection | N/A | N/A | N/A | 115 kV | 2022-10-21 | 2025-02-24 | 2025-08-26 | Transmission Project Review Process data (Resolution E-5252 Attach B | 183 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/05/25 - CAISO required MMA has been submitted and is under review; however, IC is exploring coming on-line without the Cap bank but delivery is expected early May. This would require further RFI and an MMA modification. PGE will submit PPI and clearance scheduled once MMAs are final. Realistic ISD is July/Aug. 04/08/25 - Still waiting on the IC to fulfill construction scope pertaining to NGR needed to safely connect to grid. MMA to delay is likely if IC delays fulfilling scope requirements. | Customer - Engineering Review | 1454 | 1454
Q1454 HUMMINGBIRD (DA) T-LINE | 5784844 | T.0004676 | 82D | The Q1454 Hummingbird Energy Storage Project from Cluster 11, proposes to interconnect a 75 megawatt (MW) (net output) Battery generation facility to Metcalf 115kV in Santa Clara County, California. The project has a contractual In-service date of: 2/24/25 with a current planned In-service date of: 8/26/25 | Construction (under 10%) | 2020-08-01 |  |  | Santa Clara | PG&E: Greater Bay Area | Yes | N/A |  | Upgrade/Retrofit | Generator Interconnection | Generation Interconnection | N/A | 37.8815 | N/A | 115 kV | 2024-10-01 | 2025-02-24 | 2025-08-26 | Transmission Project Review Process data (Resolution E-5252 Attach B | 183 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/05/25 - CAISO required MMA has been submitted and is under review; however, IC is exploring coming on-line without the Cap bank but delivery is expected early May. This would require further RFI and an MMA modification. PGE will submit PPI and clearance scheduled once MMAs are final. Realistic ISD is July/Aug. 04/08/25 - Still waiting on the IC to fulfill construction scope pertaining to NGR needed to safely connect to grid. MMA to delay is likely if IC delays fulfilling scope requirements. | Customer - Engineering Review
Q1454 HUMMINGBIRD (DA) GEN SITE | 5784845 | T.0004676 | 82Y | The Q1454 Hummingbird Energy Storage Project from Cluster 11, proposes to interconnect a 75 megawatt (MW) (net output) Battery generation facility to Metcalf 115kV in Santa Clara County, California. The project has a contractual In-service date of: 2/24/25 with a current planned In-service date of: 8/26/25 | Construction (under 10%) | 2020-08-01 |  |  | Santa Clara | PG&E: North Coast & North Bay Area | Yes | N/A |  | Upgrade/Retrofit | Generator Interconnection | Generation Interconnection | N/A | 37.8815 | N/A | 115 kV | 2024-10-01 | 2025-02-24 | 2025-08-26 | Transmission Project Review Process data (Resolution E-5252 Attach B | 183 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/05/25 - CAISO required MMA has been submitted and is under review; however, IC is exploring coming on-line without the Cap bank but delivery is expected early May. This would require further RFI and an MMA modification. PGE will submit PPI and clearance scheduled once MMAs are final. Realistic ISD is July/Aug. 04/08/25 - Still waiting on the IC to fulfill construction scope pertaining to NGR needed to safely connect to grid. MMA to delay is likely if IC delays fulfilling scope requirements. | Customer - Engineering Review | 1454 | 1454
Q1454 HUMMINGBIRD (NU) METCALF SUB | 5784846 | T.0004676 | 82W | The Q1454 Hummingbird Energy Storage Project from Cluster 11, proposes to interconnect a 75 megawatt (MW) (net output) Battery generation facility to Metcalf 115kV in Santa Clara County, California. The project has a contractual In-service date of: 2/24/25 with a current planned In-service date of: 8/26/25 | Operational | 2020-08-01 |  |  | Santa Clara | PG&E: Greater Bay Area | Yes | N/A |  | New | Generator Interconnection | Generation Interconnection | N/A | N/A | N/A | 115 kV | 2022-10-21 | 2025-02-24 | 2025-08-26 | Transmission Project Review Process data (Resolution E-5252 Attach B | 183 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/05/25 - CAISO required MMA has been submitted and is under review; however, IC is exploring coming on-line without the Cap bank but delivery is expected early May. This would require further RFI and an MMA modification. PGE will submit PPI and clearance scheduled once MMAs are final. Realistic ISD is July/Aug. 04/08/25 - Still waiting on the IC to fulfill construction scope pertaining to NGR needed to safely connect to grid. MMA to delay is likely if IC delays fulfilling scope requirements. | Customer - Engineering Review | 1454 | 1454
Q1109 - BELLOTA SUBSTATION (DA-ELECTRIC) | 5785808 | T.0004818 | 82Y | The Q1109 North Central Valley Project from Cluster 8, proposes to interconnect a 150 megawatt (MW) (net output) Battery generation facility to Belotta 115kV in San Joaquin County, California. The project has a contractual In-service date of: 6/21/23 with a current planned In-service date of: 8/3/23 | Operational | 2022-01-15 |  |  | San Joaquin | N/A | Yes | N/A |  | New | Generator Interconnection | Generation Interconnection | N/A | 14.7513 | N/A | 115 kV | 2023-03-01 | 2023-06-21 | 2023-08-03 | Transmission Project Review Process data (Resolution E-5252 Attach B | 43 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | NOC: AL 6581-E | 2022-05-04 | Approved | 2022 | COD - 8/24/23 for 132MW In-service 8/2/23, requires clearance to reclose once CAISO letter is received and Ops can re-clear the bus at POI | Customer - !Telecom! | 1109 | 1109
Q1109 - BELLOTA T-LINE (DA) | 5785809 | T.0004818 | 82D | The Q1109 North Central Valley Project from Cluster 8, proposes to interconnect a 150 megawatt (MW) (net output) Battery generation facility to Belotta 115kV in San Joaquin County, California. The project has a contractual In-service date of: 6/21/23 with a current planned In-service date of: 8/3/23 | Operational | 2022-01-15 |  |  | San Joaquin | PG&E: Greater Bay Area | Yes | N/A |  | New | Generator Interconnection | Generation Interconnection | N/A | 14.7513 | N/A | 115 kV | 2023-03-01 | 2023-06-21 | 2023-08-03 | Transmission Project Review Process data (Resolution E-5252 Attach B | 43 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | NOC: AL 6581-E | 2022-05-04 | Approved | 2022 | COD - 8/24/23 for 132MW In-service 8/2/23, requires clearance to reclose once CAISO letter is received and Ops can re-clear the bus at POI | Customer - !Telecom!
Q1109 - BELLOTA SUBSTATION (RNU-CIVIL) | 5785810 | T.0004818 | 82W | The Q1109 North Central Valley Project from Cluster 8, proposes to interconnect a 150 megawatt (MW) (net output) Battery generation facility to Belotta 115kV in San Joaquin County, California. The project has a contractual In-service date of: 6/21/23 with a current planned In-service date of: 8/3/23 | Operational | 2022-01-15 |  |  | San Joaquin | PG&E: North Valley Area | Yes | N/A |  | New | Generator Interconnection | Generation Interconnection | N/A | 14.7513 | N/A | 115 kV | 2023-03-01 | 2023-06-21 | 2023-08-03 | Transmission Project Review Process data (Resolution E-5252 Attach B | 43 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | NOC: AL 6581-E | 2022-05-04 | Approved | 2022 | COD - 8/24/23 for 132MW In-service 8/2/23, requires clearance to reclose once CAISO letter is received and Ops can re-clear the bus at POI | Customer - !Telecom! | 1109 | 1109
Reconductor Bellota-Warnerville 230 kV Line | 5785878 | T.0000043 | 60X | The C13P1-FPT02 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Bellota-Warnerville 230kV Line in Madera County, California. | Operational | 2024-12-31 |  |  | East Oakdale CDP, Stanislaus ¦ Oakdale, Stanislaus ¦ San Joaquin ¦ Stanislaus | PG&E: North Valley Area | No | 2013 | T.0010467 ¦ T.0008538 ¦ T.0010817 ¦ T.0010816 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 | Upgrade/Retrofit | Policy | T-Line Capacity | 45 | NA | 230 | N/A | 2023-11-01 | 2024-12-31 | 2024-03-31 | Transmission Project Review Process data (Resolution E-5252 Attach B | -275 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 04/04/24 - Final ISD 3/30/24 6/26/23 - B-W ISD was 04/28/2023. B-C ISD is 4/30/24 likely a $2M flex into 2024 for remaining phase. | Utility - !Telecom! | Q1709, Q1713, Q1930, Q1932, Q1933, Q1934, Q1953, Q1963, Q1970, Q1977 | Q1709 | Q1713 | Q1930 | Q1932 | Q1933 | Q1934 | Q1953 | Q1963 | Q1970 | Q1977
Reconductor Bellota-Warnerville 230 kV Line | 5786047 | T.0000043 | 61X | The C13P1-FPT02 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Bellota-Warnerville 230kV Line in Madera County, California. | Operational | 2025-05-01 |  |  | Oakdale, Stanislaus | PG&E: North Valley Area | No | 2013 | T.0010467 ¦ T.0008538 ¦ T.0010817 ¦ T.0010816 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 | Upgrade/Retrofit | Policy | T-Line Capacity | N/A | 3.1 | N/A | 115 kV | 2023-10-30 | 2025-05-01 | 2024-03-31 | Transmission Project Review Process data (Resolution E-5252 Attach B | -396 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 04/04/24 - Final ISD 3/30/24 6/26/23 - B-W ISD was 04/28/2023. B-C ISD is 4/30/24 likely a $2M flex into 2024 for remaining phase. | Utility - !Telecom! | Q1709, Q1713, Q1930, Q1932, Q1933, Q1934, Q1953, Q1963, Q1970, Q1977 | Q1709 | Q1713 | Q1930 | Q1932 | Q1933 | Q1934 | Q1953 | Q1963 | Q1970 | Q1977
Q1109 - GENERATION SITE (DA) | 5786118 | T.0004818 | 82Y | The Q1109 North Central Valley Project from Cluster 8, proposes to interconnect a 150 megawatt (MW) (net output) Battery generation facility to Belotta 115kV in San Joaquin County, California. The project has a contractual In-service date of: 6/21/23 with a current planned In-service date of: 8/3/23 | Planning | N/A |  |  | Butte ¦ Butte Creek Canyon CDP, Butte ¦ Chico, Butte ¦ Cohasset CDP, Butte ¦ Round Mountain CDP, Shasta ¦ Shasta ¦ Tehama ¦ Whitmore CDP, Shasta | N/A | No | N/A |  | Replace | Asset Condition | Age/Condition - Insulator Replacement - Steel | N/A | NA | 500 | N/A | 2030-01-01 | 2023-06-21 | 2023-08-03 | Transmission Project Review Process data (Resolution E-5252 Attach B | 43 | Yes |  |  | Complete |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | COD - 8/24/23 for 132MW In-service 8/2/23, requires clearance to reclose once CAISO letter is received and Ops can re-clear the bus at POI | Customer - !Telecom! | 1109 | 1109
Q1128 - LITTLE BEAR 5 DA IF | 5786402 | T.0002987 | 82Y | The Q1128 Little Bear 4 & 5 Project from Cluster 8, proposes to interconnect a 100 megawatt (MW) (net output) Solar generation facility to Mendota 115kV in Fresno County, California. The project has a contractual In-service date of: 4/1/20 with a current planned In-service date of: 10/30/20 | Operational | 2020-01-28 |  |  | Novato, Marin | PG&E: Greater Fresno Area | No | N/A | T.0003009 ¦ T.0003792 ¦ T.0003789 ¦ T.0003016 ¦ T.0004255 ¦ T.0009177 | Replace | Emergency Event | Replace Transformer | N/A | N/A | N/A | 115 ¦ 60 kV | 2020-01-21 | 2022-02-15 | 2020-10-30 | Transmission Project Review Process data (Resolution E-5252 Attach B | -473 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | - | 1128 | 1128
Q1128 - LITTLE BEAR 5 DA MTR | 5786403 | T.0002987 | 82Y | The Q1128 Little Bear 4 & 5 Project from Cluster 8, proposes to interconnect a 100 megawatt (MW) (net output) Solar generation facility to Mendota 115kV in Fresno County, California. The project has a contractual In-service date of: 4/1/20 with a current planned In-service date of: 10/30/20 | Operational | 2020-01-28 |  |  | Novato, Marin | PG&E: Greater Fresno Area | No | N/A | T.0003009 ¦ T.0003792 ¦ T.0003789 ¦ T.0003016 ¦ T.0004255 ¦ T.0009177 | New | Emergency Event | Generation Interconnection | N/A | 11.9486 | N/A | 115 ¦ 60 kV | 2020-01-21 | 2022-02-15 | 2020-10-30 | Transmission Project Review Process data (Resolution E-5252 Attach B | -473 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | - | 1128 | 1128
74028581_BORDEN-GREGG_OPGW_#1 | 5787080 | T.0007056 | 82W | The C8P2-1 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Borden-Gregg 230kV Line #1 in Madera County, California. | Engineering more than 50% complete | 2020-09-30 |  |  | Madera | PG&E: Greater Fresno Area | Yes | N/A | T.0003742 ¦ T.0003743 ¦ T.0004490 ¦ T.0008538 ¦ 0 ¦ T.0010467 ¦ T.0010817 ¦ T.0010942 ¦ 0 ¦ T.0010738 ¦ 0 ¦ 0 ¦ 0 | New | Generator Interconnection | Generation Interconnection | 6.25 | NA | 230 | N/A | 2026-10-06 | 2020-09-30 | 2027-05-12 | Transmission Project Review Process data (Resolution E-5252 Attach B | 2415 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | NOC: AL 7393-E | 2024-10-02 | Approved | 2024 |  | Utility - !Telecom! | Q1135, Q1158, Q1129, Q1713, Q1568, Q1709, Q1930, Q1935, Q1953, Q1956, Q1966, Q1968, Q1975 | Q1135 | Q1158 | Q1129 | Q1713 | Q1568 | Q1709 | Q1930 | Q1935 | Q1953 | Q1956 | Q1966 | Q1968 | Q1975
GATES SUB BUS SECTION "E" (RNU) (Q1223/Q | 5787158 | T.0006452 | 82W | The C9P2-F13-F15 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Gates 230kV in Fresno County, California. | Operational | 2023-08-15 |  |  | Fresno | N/A | Yes | N/A | T.0009863 ¦ T.0005678 ¦ T.0005679 ¦ T.0009923 ¦ T.0009924 ¦ T.0007971 ¦ T.0006953 ¦ T.0007329 ¦ T.0006952 ¦ T.0004974 ¦ T.0006847 ¦ T.0006119 ¦ T.0007165 ¦ T.0006097 ¦ 0 ¦ T.0009393 ¦ T.0009193 ¦ T.0008735 ¦ T.0010467 ¦ T.0008538 ¦ 0 ¦ 0 ¦ T.0010025 ¦ T.0010519 | Replace | Generator Interconnection | Bus Upgrade | N/A | 77.6619 | N/A | 230 kV | 2021-09-23 | 2023-08-15 | 2023-04-17 | Transmission Project Review Process data (Resolution E-5252 Attach B | -120 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/04/23 - Energized April 2023. Castanea Line relacation reamins. Due 5/29/23 | Utility - !Telecom! | Q1223, Q1242, Q1243, Q1379, Q1380, Q1389, Q1391, Q1394, Q1397, Q1398, Q1443, Q1493, Q1495, Q1499, Q1568, Q1586, Q1587, Q1593, Q1709, Q1713, Q1736, Q1740, Q1744, Q1751 | Q1223 | Q1242 | Q1243 | Q1379 | Q1380 | Q1389 | Q1391 | Q1394 | Q1397 | Q1398 | Q1443 | Q1493 | Q1495 | Q1499 | Q1568 | Q1586 | Q1587 | Q1593 | Q1709
Q1398 SANDRINI SOL 2 GEN SITE (DA) | 5787420 | T.0004974 | 82Y | The Q1398 Sandrini Sol #2 Project from Cluster 10, proposes to interconnect a 200 megawatt (MW) (net output) Solar generation facility to Wheeler Ridge 230kV in Kern County, California. The project has a contractual In-service date of: 7/6/23 with a current planned In-service date of: 2/7/24 | Operational | 2022-08-15 |  |  | Kern | PG&E Kern Area | Yes | N/A | T.0006452 | Upgrade/Retrofit | Generator Interconnection | Generation Interconnection | N/A | 10.403 | N/A | 230 kV | 2023-05-04 | 2023-07-06 | 2024-02-07 | Transmission Project Review Process data (Resolution E-5252 Attach B | 216 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | In-Service - 2/7/24 2/5/24 - Customer installed incorrect components which delayed testing - weather impacts to testing in Jan as well. PPI rescheduled to 2/7 1/3/24 - Sandrini failed their PPI prior to the Holiday's, that is what is pushing them out. The IC didn't get their updated relay settings approved by protection timely. They have since been reviewed and approved, and their 2nd PPI attempt is this week. EMS/SCADA still needs to complete their work, end of January is a more realistic backfeed date. 12/11/23 - PPI scheduled week of 12/11. backfeed in 2024 10/24/23 - Risk to IC to procure some underground comms material (~300 ft). 10/2/23 - with no Fiber in yet, the ISD will slip. IT needs 4 to 5 weeks to get splicing and all circuites up and tested. Planned ISD to shift approximately a month. PPI letter is needed. MMA was approved. Triggered an FRR due to the adding of a battery. 8/21/23 - MMA about to be executed that will take this back to green. 8/7/23 - IC telecom to be completed end of Aug. PGE to follow remaining activities end of Oct. MMA in play need completed due to inverter changes. 07/27/23 - Craig says Customers Telecom is driving the schedule to get their OPGW transition to underground going into the substation. PGE has installed 5 of 6 TL foundations. 6/22/23 - Civil contract pricing received and contract is routed. IC has to cross I-5 and CA-99. Permit Status. String to POCO last week of August. 5/22/23 - ISD depends on IC. | Customer - Bundling Dependencies | 1398 | 1398
Q1398 SANDRINI SOL2-WHEELER RIDGE SUB(RN | 5787421 | T.0004974 | 82W | The Q1398 Sandrini Sol #2 Project from Cluster 10, proposes to interconnect a 200 megawatt (MW) (net output) Solar generation facility to Wheeler Ridge 230kV in Kern County, California. The project has a contractual In-service date of: 7/6/23 with a current planned In-service date of: 2/7/24 | Operational | 2022-08-15 |  |  | Kern | PG&E Kern Area | Yes | N/A | T.0006452 | New | Generator Interconnection | Generation Interconnection | N/A | 10.403 | N/A | 230 kV | 2022-10-03 | 2023-07-06 | 2024-02-07 | Transmission Project Review Process data (Resolution E-5252 Attach B | 216 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | In-Service - 2/7/24 2/5/24 - Customer installed incorrect components which delayed testing - weather impacts to testing in Jan as well. PPI rescheduled to 2/7 1/3/24 - Sandrini failed their PPI prior to the Holiday's, that is what is pushing them out. The IC didn't get their updated relay settings approved by protection timely. They have since been reviewed and approved, and their 2nd PPI attempt is this week. EMS/SCADA still needs to complete their work, end of January is a more realistic backfeed date. 12/11/23 - PPI scheduled week of 12/11. backfeed in 2024 10/24/23 - Risk to IC to procure some underground comms material (~300 ft). 10/2/23 - with no Fiber in yet, the ISD will slip. IT needs 4 to 5 weeks to get splicing and all circuites up and tested. Planned ISD to shift approximately a month. PPI letter is needed. MMA was approved. Triggered an FRR due to the adding of a battery. 8/21/23 - MMA about to be executed that will take this back to green. 8/7/23 - IC telecom to be completed end of Aug. PGE to follow remaining activities end of Oct. MMA in play need completed due to inverter changes. 07/27/23 - Craig says Customers Telecom is driving the schedule to get their OPGW transition to underground going into the substation. PGE has installed 5 of 6 TL foundations. 6/22/23 - Civil contract pricing received and contract is routed. IC has to cross I-5 and CA-99. Permit Status. String to POCO last week of August. 5/22/23 - ISD depends on IC. | Customer - Bundling Dependencies | 1398 | 1398
Q1398 SANDRINI SOL2-MIDWAY SUB(RNU) | 5787422 | T.0004974 | 82W | The Q1398 Sandrini Sol #2 Project from Cluster 10, proposes to interconnect a 200 megawatt (MW) (net output) Solar generation facility to Wheeler Ridge 230kV in Kern County, California. The project has a contractual In-service date of: 7/6/23 with a current planned In-service date of: 2/7/24 | Operational | 2022-08-15 |  |  | Kern | PG&E Kern Area | Yes | N/A | T.0006452 | New | Generator Interconnection | Special Protection Scheme | N/A | N/A | N/A | 230 kV | 2022-11-01 | 2023-07-06 | 2024-02-07 | Transmission Project Review Process data (Resolution E-5252 Attach B | 216 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | In-Service - 2/7/24 2/5/24 - Customer installed incorrect components which delayed testing - weather impacts to testing in Jan as well. PPI rescheduled to 2/7 1/3/24 - Sandrini failed their PPI prior to the Holiday's, that is what is pushing them out. The IC didn't get their updated relay settings approved by protection timely. They have since been reviewed and approved, and their 2nd PPI attempt is this week. EMS/SCADA still needs to complete their work, end of January is a more realistic backfeed date. 12/11/23 - PPI scheduled week of 12/11. backfeed in 2024 10/24/23 - Risk to IC to procure some underground comms material (~300 ft). 10/2/23 - with no Fiber in yet, the ISD will slip. IT needs 4 to 5 weeks to get splicing and all circuites up and tested. Planned ISD to shift approximately a month. PPI letter is needed. MMA was approved. Triggered an FRR due to the adding of a battery. 8/21/23 - MMA about to be executed that will take this back to green. 8/7/23 - IC telecom to be completed end of Aug. PGE to follow remaining activities end of Oct. MMA in play need completed due to inverter changes. 07/27/23 - Craig says Customers Telecom is driving the schedule to get their OPGW transition to underground going into the substation. PGE has installed 5 of 6 TL foundations. 6/22/23 - Civil contract pricing received and contract is routed. IC has to cross I-5 and CA-99. Permit Status. String to POCO last week of August. 5/22/23 - ISD depends on IC. | Customer - Bundling Dependencies | 1398 | 1398
Convert Midway Substation 230 kV Bus D to BAAH in order to install bus reactors & RAS | 5787769 | T.0001650 | 94D | The C13P1-KPN02 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Midway 230kV in Kern County, California. | Operational | 2022-04-01 |  |  | Buttonwillow CDP, Kern | 0 | No | N/A | 0 ¦ 0 ¦ T.0010479 ¦ T.0010519 ¦ T.0010025 ¦ 0 ¦ 0 ¦ 0 ¦ T.0009383 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 | Upgrade/Retrofit | Reliability | T-Line Capacity | N/A | 94.5324 | N/A | 230 kV | 2021-11-10 | 2022-04-01 | 2021-11-10 | Transmission Project Review Process data (Resolution E-5252 Attach B | -142 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 04/23/25 - Project is still working through the Prioritization Impacts from 2023 | Utility - !Telecom! | Q1740, Q1749, Q1739, Q1751, Q1744, Q1980, Q1987, Q2001, Q1949, Q1983, Q1995, Q2004, Q2006, Q2010, Q2013, Q2015 | Q1740 | Q1749 | Q1739 | Q1751 | Q1744 | Q1980 | Q1987 | Q2001 | Q1949 | Q1983 | Q1995 | Q2004 | Q2006 | Q2010 | Q2013 | Q2015
Convert Midway Substation 230 kV Bus D to BAAH in order to install bus reactors & RAS | 5787770 | T.0001650 | 94D | The C13P1-KPN02 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Midway 230kV in Kern County, California. | Operational | 2022-04-01 |  |  | Buttonwillow CDP, Kern | 0 | No | N/A | 0 ¦ 0 ¦ T.0010479 ¦ T.0010519 ¦ T.0010025 ¦ 0 ¦ 0 ¦ 0 ¦ T.0009383 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 | Upgrade/Retrofit | Reliability | T-Line Capacity | N/A | #REF! | N/A | 230 kV | 2022-10-11 | 2022-04-01 | 2023-04-24 | Transmission Project Review Process data (Resolution E-5252 Attach B | 388 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 04/23/25 - Project is still working through the Prioritization Impacts from 2023 | Utility - !Telecom! | Q1740, Q1749, Q1739, Q1751, Q1744, Q1980, Q1987, Q2001, Q1949, Q1983, Q1995, Q2004, Q2006, Q2010, Q2013, Q2015 | Q1740 | Q1749 | Q1739 | Q1751 | Q1744 | Q1980 | Q1987 | Q2001 | Q1949 | Q1983 | Q1995 | Q2004 | Q2006 | Q2010 | Q2013 | Q2015
Convert Midway Substation 230 kV Bus D to BAAH in order to install bus reactors & RAS | 5787771 | T.0001650 | 94D | The C13P1-KPN02 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Midway 230kV in Kern County, California. | Engineering more than 50% complete | 2022-04-01 |  |  | Buttonwillow CDP, Kern | 0 | No | N/A | 0 ¦ 0 ¦ T.0010479 ¦ T.0010519 ¦ T.0010025 ¦ 0 ¦ 0 ¦ 0 ¦ T.0009383 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 | Upgrade/Retrofit | Reliability | T-Line Capacity | N/A | #REF! | N/A | 230 kV | 2026-01-23 | 2022-04-01 | 2026-02-19 | Transmission Project Review Process data (Resolution E-5252 Attach B | 1420 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 04/23/25 - Project is still working through the Prioritization Impacts from 2023 | Utility - !Telecom! | Q1740, Q1749, Q1739, Q1751, Q1744, Q1980, Q1987, Q2001, Q1949, Q1983, Q1995, Q2004, Q2006, Q2010, Q2013, Q2015 | Q1740 | Q1749 | Q1739 | Q1751 | Q1744 | Q1980 | Q1987 | Q2001 | Q1949 | Q1983 | Q1995 | Q2004 | Q2006 | Q2010 | Q2013 | Q2015
Convert Midway Substation 230 kV Bus D to BAAH in order to install bus reactors & RAS | 5787772 | T.0001650 | 94D | The C13P1-KPN02 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Midway 230kV in Kern County, California. | Engineering more than 50% complete | 2022-04-01 |  |  | Buttonwillow CDP, Kern | 0 | No | N/A | 0 ¦ 0 ¦ T.0010479 ¦ T.0010519 ¦ T.0010025 ¦ 0 ¦ 0 ¦ 0 ¦ T.0009383 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 | Upgrade/Retrofit | Reliability | T-Line Capacity | N/A | #REF! | N/A | 230 kV | 2027-05-13 | 2022-04-01 | 2028-02-18 | Transmission Project Review Process data (Resolution E-5252 Attach B | 2149 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 04/23/25 - Project is still working through the Prioritization Impacts from 2023 | Utility - !Telecom! | Q1740, Q1749, Q1739, Q1751, Q1744, Q1980, Q1987, Q2001, Q1949, Q1983, Q1995, Q2004, Q2006, Q2010, Q2013, Q2015 | Q1740 | Q1749 | Q1739 | Q1751 | Q1744 | Q1980 | Q1987 | Q2001 | Q1949 | Q1983 | Q1995 | Q2004 | Q2006 | Q2010 | Q2013 | Q2015
Wilson 115 kV Area Reinforcement | 5787806 | T.0004116 | 61W | The C14P2-NFT03 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Wilson 115kV in Merced County, California. | Engineering more than 50% complete | 2022-08-12 |  |  | Merced, Merced | PG&E: North Valley Area | No | N/A | 0 | Upgrade/Retrofit | CAISO Transmission Planning Standards | T-Line Capacity | N/A | 1.954 | N/A | 115 kV | 2026-10-12 | 2022-08-12 | 2026-12-01 | Transmission Project Review Process data (Resolution E-5252 Attach B | 1572 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 01/06/25 - Construction sequence may push the project completion to 2030. TBD on when the Q1895 could come online and if their breaker could come earlier. | Utility - !Telecom! | Q1895 | Q1895
FOREBAY WIND REPOWER - GEN SITE DA | 5787838 | T.0005178 | 82Y | The ForebayWindRE Forebay Wind Project from Cluster , proposes to interconnect a 13 megawatt (MW) (net output) Wind generation facility to in Alameda County, California. The project has a contractual In-service date of: 3/21/27 with a current planned In-service date of: 12/17/26 | Engineering more than 50% complete | 2021-12-01 |  |  | Contra Costa | PG&E: North Valley Area | Yes | N/A |  | New | Generator Interconnection | Generation Interconnection | N/A | 0.81883 | N/A | 60 kV | 2026-03-23 | 2027-03-21 | 2026-12-17 | Transmission Project Review Process data (Resolution E-5252 Attach B | -94 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - Tracking ISD in Q4 2026. Project closely aligned with Zond Wind. | Utility - !Telecom! | ForebayWindRE | ForebayWindRE
FOREBAY WIND REPWR - HERDLYN SUB RNU | 5787841 | T.0005178 | 82W | The ForebayWindRE Forebay Wind Project from Cluster , proposes to interconnect a 13 megawatt (MW) (net output) Wind generation facility to in Alameda County, California. The project has a contractual In-service date of: 3/21/27 with a current planned In-service date of: 12/17/26 | Engineering more than 50% complete | 2021-12-01 |  |  | Contra Costa | 0 | Yes | N/A |  | New | Generator Interconnection | Generation Interconnection | N/A | 0.81883 | N/A | 60 kV | 2026-03-23 | 2027-03-21 | 2026-12-17 | Transmission Project Review Process data (Resolution E-5252 Attach B | -94 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - Tracking ISD in Q4 2026. Project closely aligned with Zond Wind. | Utility - !Telecom! | ForebayWindRE | ForebayWindRE
FOREBAY WIND REPWR - LAS POSITAS RNU | 5787842 | T.0005178 | 82W | The ForebayWindRE Forebay Wind Project from Cluster , proposes to interconnect a 13 megawatt (MW) (net output) Wind generation facility to in Alameda County, California. The project has a contractual In-service date of: 3/21/27 with a current planned In-service date of: 12/17/26 | Engineering more than 50% complete | 2021-12-01 |  |  | Contra Costa | 0 | Yes | N/A |  | New | Generator Interconnection | Special Protection Scheme | N/A | 0.81883 | N/A | 60 kV | 2026-03-23 | 2027-03-21 | 2026-12-17 | Transmission Project Review Process data (Resolution E-5252 Attach B | -94 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - Tracking ISD in Q4 2026. Project closely aligned with Zond Wind. | Utility - !Telecom! | ForebayWindRE | ForebayWindRE
SANTA CLARA WIND REPOWER - GEN SITE DA | 5787843 | T.0005176 | 82Y | The SantaClaraWindRE Zond (Santa Clara) Project from Cluster , proposes to interconnect a 21.3 megawatt (MW) (net output) Wind generation facility to The Point of Interconnection (POI) for Santa Clara Wind will change from Herdlyn-Vasco-Livermore 60 kV line to Las Positas-Vasco 60 kV Line The POI is not physically changing but the configuration of the PG&E transmission system and transmission line names have changed in Alameda County, California. The project has a contractual In-service date of: 8/7/25 with a current planned In-service date of: 10/2/26 | Engineering more than 50% complete | 2021-12-01 |  |  | Contra Costa | N/A | Yes | N/A |  | New | Generator Interconnection | Generation Interconnection | N/A | N/A | N/A | 60 kV | 2026-03-23 | 2025-08-07 | 2026-10-02 | Transmission Project Review Process data (Resolution E-5252 Attach B | 421 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - Tracking ISD to Q3 2026. Project closely aligned with Forebay Wind. Third party Telco dependencies. IC still on delay schedule, new IC project management team in transistion. IC needs to submit new schedule. Customer gensite activities running late with dependencies mostly on AT&T/Control Building readiness | - | SantaClaraWindRE | SantaClaraWindRE
SANTA CLARA WIND REPOWER - TLINE REMOVAL | 5787844 | T.0005176 | 82D | The SantaClaraWindRE Zond (Santa Clara) Project from Cluster , proposes to interconnect a 21.3 megawatt (MW) (net output) Wind generation facility to The Point of Interconnection (POI) for Santa Clara Wind will change from Herdlyn-Vasco-Livermore 60 kV line to Las Positas-Vasco 60 kV Line The POI is not physically changing but the configuration of the PG&E transmission system and transmission line names have changed in Alameda County, California. The project has a contractual In-service date of: 8/7/25 with a current planned In-service date of: 10/2/26 | Engineering more than 50% complete | 2021-12-01 |  |  | Livermore, Alameda | PG&E: Greater Bay Area | Yes | N/A |  | Replace | Generator Interconnection | Generation Interconnection | 3.77 | NA | 60 | N/A | 2025-08-20 | 2025-08-07 | 2026-10-02 | Transmission Project Review Process data (Resolution E-5252 Attach B | 421 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - Tracking ISD to Q3 2026. Project closely aligned with Forebay Wind. Third party Telco dependencies. IC still on delay schedule, new IC project management team in transistion. IC needs to submit new schedule. Customer gensite activities running late with dependencies mostly on AT&T/Control Building readiness | - | SantaClaraWindRE | SantaClaraWindRE
SANTA CLARA WIND REPWR - HERDLYN SUB RNU | 5787845 | T.0005176 | 82W | The SantaClaraWindRE Zond (Santa Clara) Project from Cluster , proposes to interconnect a 21.3 megawatt (MW) (net output) Wind generation facility to The Point of Interconnection (POI) for Santa Clara Wind will change from Herdlyn-Vasco-Livermore 60 kV line to Las Positas-Vasco 60 kV Line The POI is not physically changing but the configuration of the PG&E transmission system and transmission line names have changed in Alameda County, California. The project has a contractual In-service date of: 8/7/25 with a current planned In-service date of: 10/2/26 | Engineering more than 50% complete | 2021-12-01 |  |  | Contra Costa | N/A | Yes | N/A |  | New | Generator Interconnection | Generation Interconnection | N/A | N/A | N/A | 60 kV | 2025-05-27 | 2025-08-07 | 2026-10-02 | Transmission Project Review Process data (Resolution E-5252 Attach B | 421 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - Tracking ISD to Q3 2026. Project closely aligned with Forebay Wind. Third party Telco dependencies. IC still on delay schedule, new IC project management team in transistion. IC needs to submit new schedule. Customer gensite activities running late with dependencies mostly on AT&T/Control Building readiness | - | SantaClaraWindRE | SantaClaraWindRE
SANTA CLARA WIND REPWR - LAS POSITAS RNU | 5787846 | T.0005176 | 82W | The SantaClaraWindRE Zond (Santa Clara) Project from Cluster , proposes to interconnect a 21.3 megawatt (MW) (net output) Wind generation facility to The Point of Interconnection (POI) for Santa Clara Wind will change from Herdlyn-Vasco-Livermore 60 kV line to Las Positas-Vasco 60 kV Line The POI is not physically changing but the configuration of the PG&E transmission system and transmission line names have changed in Alameda County, California. The project has a contractual In-service date of: 8/7/25 with a current planned In-service date of: 10/2/26 | Engineering more than 50% complete | 2021-12-01 |  |  | Livermore, Alameda | 0 | Yes | N/A |  | New | Generator Interconnection | Special Protection Scheme | N/A | N/A | N/A | 60 kV | 2025-09-09 | 2025-08-07 | 2026-10-02 | Transmission Project Review Process data (Resolution E-5252 Attach B | 421 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - Tracking ISD to Q3 2026. Project closely aligned with Forebay Wind. Third party Telco dependencies. IC still on delay schedule, new IC project management team in transistion. IC needs to submit new schedule. Customer gensite activities running late with dependencies mostly on AT&T/Control Building readiness | -
Kern PP Substation 115 kV CBs 182, 262 and 282 overstress | 5787960 | T.0000980 | 94D | The 21rsmt-3 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Kern PP Substation 115kV in Kern County, California. | Engineering more than 50% complete | 2022-10-12 |  |  | Bakersfield, Kern | 0 | No | N/A | 0 ¦ 0 ¦ 0 ¦ 0 | Upgrade/Retrofit | Reliability | T-Line Capacity | N/A | #REF! | N/A | 115 kV | 2025-05-01 | 2022-10-12 | 2025-12-05 | Transmission Project Review Process data (Resolution E-5252 Attach B | 1150 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 04/23/25 - Not yet triggered by EGI. Q2001 Negotiating agreements. Project is still working through Prioritization Impacts from 2023. 04/07/25 - Project going through GRB funding. Project on schedule 11/30/23 - On-hold until 2024. Removed as PNU. | Utility - !Telecom! | Q1995, Q2001, Q2006, Q2015 | Q1995 | Q2001 | Q2006 | Q2015
Kern PP Substation 115 kV CBs 182, 262 and 282 overstress | 5787961 | T.0000980 | 94D | The 21rsmt-3 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Kern PP Substation 115kV in Kern County, California. | Engineering more than 50% complete | 2022-10-12 |  |  | Bakersfield, Kern | 0 | No | N/A | 0 ¦ 0 ¦ 0 ¦ 0 | Upgrade/Retrofit | Reliability | T-Line Capacity | N/A | #REF! | N/A | 115 kV | 2026-01-08 | 2022-10-12 | 2026-12-04 | Transmission Project Review Process data (Resolution E-5252 Attach B | 1514 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 04/23/25 - Not yet triggered by EGI. Q2001 Negotiating agreements. Project is still working through Prioritization Impacts from 2023. 04/07/25 - Project going through GRB funding. Project on schedule 11/30/23 - On-hold until 2024. Removed as PNU. | Utility - !Telecom! | Q1995, Q2001, Q2006, Q2015 | Q1995 | Q2001 | Q2006 | Q2015
Kern PP Substation 115 kV CBs 182, 262 and 282 overstress | 5787962 | T.0000980 | 94D | The 21rsmt-3 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Kern PP Substation 115kV in Kern County, California. | Engineering more than 50% complete | 2022-10-12 |  |  | Bakersfield, Kern | 0 | No | N/A | 0 ¦ 0 ¦ 0 ¦ 0 | Upgrade/Retrofit | Reliability | T-Line Capacity | N/A | 37.7504 | N/A | 115 kV | 2027-11-01 | 2022-10-12 | 2027-12-13 | Transmission Project Review Process data (Resolution E-5252 Attach B | 1888 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 04/23/25 - Not yet triggered by EGI. Q2001 Negotiating agreements. Project is still working through Prioritization Impacts from 2023. 04/07/25 - Project going through GRB funding. Project on schedule 11/30/23 - On-hold until 2024. Removed as PNU. | Utility - !Telecom! | Q1995, Q2001, Q2006, Q2015 | Q1995 | Q2001 | Q2006 | Q2015
Kern PP Substation 115 kV CBs 182, 262 and 282 overstress | 5788178 | T.0000980 | 94A | The 21rsmt-3 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Kern PP Substation 115kV in Kern County, California. | Engineering more than 50% complete | 2022-10-12 |  |  | Bakersfield, Kern ¦ Kern | 0 | No | N/A | 0 ¦ 0 ¦ 0 ¦ 0 | Upgrade/Retrofit | Reliability | T-Line Capacity | N/A | NA | 115 | N/A | 2026-05-01 | 2022-10-12 | 2027-05-21 | Transmission Project Review Process data (Resolution E-5252 Attach B | 1682 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 04/23/25 - Not yet triggered by EGI. Q2001 Negotiating agreements. Project is still working through Prioritization Impacts from 2023. 04/07/25 - Project going through GRB funding. Project on schedule 11/30/23 - On-hold until 2024. Removed as PNU. | Utility - !Telecom! | Q1995, Q2001, Q2006, Q2015 | Q1995 | Q2001 | Q2006 | Q2015
Kern PP Substation 115 kV CBs 182, 262 and 282 overstress | 5788179 | T.0000980 | 94A | The 21rsmt-3 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Kern PP Substation 115kV in Kern County, California. | On Hold | 2022-10-12 |  |  | Bakersfield, Kern ¦ Kern | 0 | No | N/A | 0 ¦ 0 ¦ 0 ¦ 0 | Upgrade/Retrofit | Reliability | T-Line Capacity | N/A | NA | 115 | N/A | 2027-04-02 | 2022-10-12 | 2028-04-03 | Transmission Project Review Process data (Resolution E-5252 Attach B | 2000 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 04/23/25 - Not yet triggered by EGI. Q2001 Negotiating agreements. Project is still working through Prioritization Impacts from 2023. 04/07/25 - Project going through GRB funding. Project on schedule 11/30/23 - On-hold until 2024. Removed as PNU. | Utility - !Telecom! | Q1995, Q2001, Q2006, Q2015 | Q1995 | Q2001 | Q2006 | Q2015
Convert Midway Substation 230 kV Bus D to BAAH in order to install bus reactors & RAS | 5788381 | T.0001650 | 94A | The C13P1-KPN02 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Midway 230kV in Kern County, California. | Engineering more than 50% complete | 2022-04-01 |  |  | Kern | 0 | No | N/A | 0 ¦ 0 ¦ T.0010479 ¦ T.0010519 ¦ T.0010025 ¦ 0 ¦ 0 ¦ 0 ¦ T.0009383 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 | Upgrade/Retrofit | Reliability | T-Line Capacity | N/A | NA | 230 | N/A | 2025-08-05 | 2022-04-01 | 2026-09-08 | Transmission Project Review Process data (Resolution E-5252 Attach B | 1621 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 04/23/25 - Project is still working through the Prioritization Impacts from 2023 | Utility - !Telecom! | Q1740, Q1749, Q1739, Q1751, Q1744, Q1980, Q1987, Q2001, Q1949, Q1983, Q1995, Q2004, Q2006, Q2010, Q2013, Q2015 | Q1740 | Q1749 | Q1739 | Q1751 | Q1744 | Q1980 | Q1987 | Q2001 | Q1949 | Q1983 | Q1995 | Q2004 | Q2006 | Q2010 | Q2013 | Q2015
Convert Midway Substation 230 kV Bus D to BAAH in order to install bus reactors & RAS | 5788382 | T.0001650 | 94A | The C13P1-KPN02 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Midway 230kV in Kern County, California. | Engineering more than 50% complete | 2022-04-01 |  |  | Bakersfield, Kern ¦ Kern | 0 | No | N/A | 0 ¦ 0 ¦ T.0010479 ¦ T.0010519 ¦ T.0010025 ¦ 0 ¦ 0 ¦ 0 ¦ T.0009383 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 | Relocate | Reliability | T-Line Capacity | N/A | NA | 230 | N/A | 2026-05-19 | 2022-04-01 | 2026-10-15 | Transmission Project Review Process data (Resolution E-5252 Attach B | 1658 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 04/23/25 - Project is still working through the Prioritization Impacts from 2023 | Utility - !Telecom! | Q1740, Q1749, Q1739, Q1751, Q1744, Q1980, Q1987, Q2001, Q1949, Q1983, Q1995, Q2004, Q2006, Q2010, Q2013, Q2015 | Q1740 | Q1749 | Q1739 | Q1751 | Q1744 | Q1980 | Q1987 | Q2001 | Q1949 | Q1983 | Q1995 | Q2004 | Q2006 | Q2010 | Q2013 | Q2015
Convert Midway Substation 230 kV Bus D to BAAH in order to install bus reactors & RAS | 5788383 | T.0001650 | 94A | The C13P1-KPN02 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Midway 230kV in Kern County, California. | Engineering more than 50% complete | 2022-04-01 |  |  | Bakersfield, Kern ¦ Kern | 0 | No | N/A | 0 ¦ 0 ¦ T.0010479 ¦ T.0010519 ¦ T.0010025 ¦ 0 ¦ 0 ¦ 0 ¦ T.0009383 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 | Relocate | Reliability | T-Line Capacity | N/A | NA | 230 | N/A | 2027-08-06 | 2022-04-01 | 2028-02-03 | Transmission Project Review Process data (Resolution E-5252 Attach B | 2134 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 04/23/25 - Project is still working through the Prioritization Impacts from 2023 | Utility - !Telecom! | Q1740, Q1749, Q1739, Q1751, Q1744, Q1980, Q1987, Q2001, Q1949, Q1983, Q1995, Q2004, Q2006, Q2010, Q2013, Q2015 | Q1740 | Q1749 | Q1739 | Q1751 | Q1744 | Q1980 | Q1987 | Q2001 | Q1949 | Q1983 | Q1995 | Q2004 | Q2006 | Q2010 | Q2013 | Q2015
Convert Midway Substation 230 kV Bus D to BAAH in order to install bus reactors & RAS | 5788384 | T.0001650 | 94A | The C13P1-KPN02 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Midway 230kV in Kern County, California. | Engineering more than 50% complete | 2022-04-01 |  |  | Bakersfield, Kern ¦ Kern | 0 | No | N/A | 0 ¦ 0 ¦ T.0010479 ¦ T.0010519 ¦ T.0010025 ¦ 0 ¦ 0 ¦ 0 ¦ T.0009383 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 | Relocate | Reliability | T-Line Capacity | N/A | NA | 230 | N/A | 2028-02-17 | 2022-04-01 | 2030-08-22 | Transmission Project Review Process data (Resolution E-5252 Attach B | 3065 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 04/23/25 - Project is still working through the Prioritization Impacts from 2023 | Utility - !Telecom! | Q1740, Q1749, Q1739, Q1751, Q1744, Q1980, Q1987, Q2001, Q1949, Q1983, Q1995, Q2004, Q2006, Q2010, Q2013, Q2015 | Q1740 | Q1749 | Q1739 | Q1751 | Q1744 | Q1980 | Q1987 | Q2001 | Q1949 | Q1983 | Q1995 | Q2004 | Q2006 | Q2010 | Q2013 | Q2015
Q1242 PLUOT GEN SITE (DA) | 5789264 | T.0005678 | 82Y | The Q1242 Pluot Project from Cluster 9, proposes to interconnect a 246.4 megawatt (MW) (net output) Solar + Battery generation facility to Gates 230kV in Fresno County, California. The project has a contractual In-service date of: 1/30/26 with a current planned In-service date of: 9/1/26 | Construction (under 10%) | 2023-04-14 |  |  | Alameda | PG&E: North Valley Area | Yes | N/A | T.0007289 ¦ T.0006452 | New | Generator Interconnection | Generation Interconnection | N/A | 0.26068 | N/A | 230 kV | 2024-12-10 | 2026-01-30 | 2026-09-01 | Transmission Project Review Process data (Resolution E-5252 Attach B | 214 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - MMA approval required to extend the ISD to Q3 2026 | Customer - Project Design | 1242 | 1242
Q1243 POMEGRANATE SOLAR GEN SITE (DA) | 5789265 | T.0005679 | 82Y | The Q1243 Pomegranate Project from Cluster 9, proposes to interconnect a 249.7 megawatt (MW) (net output) Solar + Battery generation facility to Gates 230kV in Huron / Fresno County, California. The project has a contractual In-service date of: 12/15/23 with a current planned In-service date of: 9/30/25 | Construction (under 10%) | 2023-04-14 |  |  | Alameda | PG&E: North Valley Area | Yes | N/A | T.0007289 ¦ T.0006452 | New | Generator Interconnection | Generation Interconnection | N/A | 0.26068 | N/A | 230 kV | 2024-12-10 | 2023-12-15 | 2025-09-30 | Transmission Project Review Process data (Resolution E-5252 Attach B | 655 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - MMA technology change completed on 4/14/25 04/08/25 - MMA submitted for Technology changes. Tracking ISD to Q1 2026. | Customer - Project Design | 1243 | 1243
Q1349 - ARAMIS - CAYETANO SUB DA | 5789326 | T.0005689 | 82Y | The Q1349 Aramis Power Plant Project from Cluster 10, proposes to interconnect a 100 megawatt (MW) (net output) Solar + Battery generation facility to Cayetano 230kV in Alameda County, California. The project has a contractual In-service date of: 12/3/27 with a current planned In-service date of: 3/6/26 | Construction (under 10%) | 2023-04-14 |  |  | Alameda | PG&E: North Valley Area | Yes | N/A | T.0004673 ¦ T.0004673 ¦ T.0008048 | New | Generator Interconnection | Generation Interconnection | N/A | 0.26068 | N/A | 230 kV | 2024-12-10 | 2027-12-03 | 2026-03-06 | Transmission Project Review Process data (Resolution E-5252 Attach B | -637 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 06/02/25 - Customer mobilization and ground-breaking are scheduled for July, with the final design review expected to conclude in two weeks. The ISD remains set for March 6, 2026. | Customer - !Telecom! | 1349 | 1349
Q1349 - ARAMIS GEN SITE DA | 5789328 | T.0005689 | 82Y | The Q1349 Aramis Power Plant Project from Cluster 10, proposes to interconnect a 100 megawatt (MW) (net output) Solar + Battery generation facility to Cayetano 230kV in Alameda County, California. The project has a contractual In-service date of: 12/3/27 with a current planned In-service date of: 3/6/26 | Engineering more than 50% complete | 2023-04-14 |  |  | Alameda | #REF! | Yes | N/A | T.0004673 ¦ T.0004673 ¦ T.0008048 | Upgrade/Retrofit | Generator Interconnection | Generation Interconnection | N/A | N/A | N/A | 230 kV | 2025-09-30 | 2027-12-03 | 2026-03-06 | Transmission Project Review Process data (Resolution E-5252 Attach B | -637 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 06/02/25 - Customer mobilization and ground-breaking are scheduled for July, with the final design review expected to conclude in two weeks. The ISD remains set for March 6, 2026. | Customer - !Telecom! | 1349 | 1349
Q1349 - ARAMIS - CAYETANO SUB RNU | 5789329 | T.0005689 | 82W | The Q1349 Aramis Power Plant Project from Cluster 10, proposes to interconnect a 100 megawatt (MW) (net output) Solar + Battery generation facility to Cayetano 230kV in Alameda County, California. The project has a contractual In-service date of: 12/3/27 with a current planned In-service date of: 3/6/26 | Construction (25%-50%) | 2023-04-14 |  |  | Alameda | N/A | Yes | N/A | T.0004673 ¦ T.0004673 ¦ T.0008048 | New | Generator Interconnection | Generation Interconnection | N/A | 0.26068 | N/A | 230 kV | 2024-11-18 | 2027-12-03 | 2026-03-06 | Transmission Project Review Process data (Resolution E-5252 Attach B | -637 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 06/02/25 - Customer mobilization and ground-breaking are scheduled for July, with the final design review expected to conclude in two weeks. The ISD remains set for March 6, 2026. | Customer - !Telecom! | 1349 | 1349
Q1349 ARAMIS T-LINE (DA) | 5789330 | T.0005689 | 82D | The Q1349 Aramis Power Plant Project from Cluster 10, proposes to interconnect a 100 megawatt (MW) (net output) Solar + Battery generation facility to Cayetano 230kV in Alameda County, California. The project has a contractual In-service date of: 12/3/27 with a current planned In-service date of: 3/6/26 | Engineering more than 50% complete | 2023-04-14 |  |  | Alameda | N/A | Yes | N/A | T.0004673 ¦ T.0004673 ¦ T.0008048 | New | Generator Interconnection | Generation Interconnection | 2 | 0.26068 | 230 | N/A | 2025-07-01 | 2027-12-03 | 2026-03-06 | Transmission Project Review Process data (Resolution E-5252 Attach B | -637 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 06/02/25 - Customer mobilization and ground-breaking are scheduled for July, with the final design review expected to conclude in two weeks. The ISD remains set for March 6, 2026. | Customer - !Telecom! | 1349 | 1349
Q1349 - ARAMIS - NORTH DUBLIN SUB DTT RN | 5789331 | T.0005689 | 82W | The Q1349 Aramis Power Plant Project from Cluster 10, proposes to interconnect a 100 megawatt (MW) (net output) Solar + Battery generation facility to Cayetano 230kV in Alameda County, California. The project has a contractual In-service date of: 12/3/27 with a current planned In-service date of: 3/6/26 | Engineering more than 50% complete | 2023-04-14 |  |  | Contra Costa | PG&E: North Valley Area | Yes | N/A | T.0004673 ¦ T.0004673 ¦ T.0008048 | New | Generator Interconnection | Special Protection Scheme | N/A | 2.373 | N/A | 230 kV | 2025-09-09 | 2027-12-03 | 2026-03-06 | Transmission Project Review Process data (Resolution E-5252 Attach B | -637 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 06/02/25 - Customer mobilization and ground-breaking are scheduled for July, with the final design review expected to conclude in two weeks. The ISD remains set for March 6, 2026. | Customer - !Telecom! | 1349 | 1349
Q1374 ELKHORN METER (DA) | 5790383 | T.0004697 | 82Y | The Q1374 Elkhorn Energy Storage Project from Cluster 10, proposes to interconnect a 182.5 megawatt (MW) (net output) Battery generation facility to Moss Landing 115kV in Monterey County, California. The project has a contractual In-service date of: with a current planned In-service date of: 6/9/21 | Engineering more than 50% complete | 2023-08-31 |  |  | Oildale CDP, Kern | PG&E: Greater Bay Area | No | N/A |  | Replace | Asset Condition | Age/Condition - 230/115/70/60 kV Relay Replacement | N/A | 4.2122 | N/A | 230 kV | 2025-07-31 | 2020-10-15 | 2021-06-09 | Transmission Project Review Process data (Resolution E-5252 Attach B | 237 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | - | 1374 | 1374
Q1096 SANDHILL B ALTAMONT MIDWAY REPOWER | 5790398 | T.0005867 | 82Y | The Q1096 Sandhill B Repower Project from Cluster FT, proposes to interconnect a 5 megawatt (MW) (net output) Wind Turbine generation facility to Altamont Midway 230kV in Alameda County, California. The project has a contractual In-service date of: 3/21/25 with a current planned In-service date of: 9/15/25 | Engineering more than 50% complete | 2021-12-31 |  |  | Butte | N/A | No | N/A |  | Upgrade/Retrofit | Work Requested by Others | Load Interconnection | N/A | 1.4913 | N/A | 230 kV | 2025-06-13 | 2025-03-21 | 2025-09-15 | Transmission Project Review Process data (Resolution E-5252 Attach B | 178 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 04/08/25 - IC needs to submit MMA. IC not engaged for nearly a year. | Customer - Construction Delays | 1096 | 1096
Q1096 SANDHILL B ALTAMONT MIDWAY REPOWE | 5790399 | T.0005867 | 82D | The Q1096 Sandhill B Repower Project from Cluster FT, proposes to interconnect a 5 megawatt (MW) (net output) Wind Turbine generation facility to Altamont Midway 230kV in Alameda County, California. The project has a contractual In-service date of: 3/21/25 with a current planned In-service date of: 9/15/25 | Engineering more than 50% complete | 2021-12-31 |  |  | Butte | PG&E: North Coast & North Bay Area | No | N/A |  | Upgrade/Retrofit | Work Requested by Others | Load Interconnection | N/A | N/A | N/A | 230 kV | 2025-06-13 | 2025-03-21 | 2025-09-15 | Transmission Project Review Process data (Resolution E-5252 Attach B | 178 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 04/08/25 - IC needs to submit MMA. IC not engaged for nearly a year. | Customer - Construction Delays | 1096 | 1096
GATES BUS SECTION "E" | 5790590 | T.0006452 | 66A | The C9P2-F13-F15 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Gates 230kV in Fresno County, California. | Operational | 2023-08-15 |  |  | Fresno | PG&E: North Valley Area | No | N/A | T.0009863 ¦ T.0005678 ¦ T.0005679 ¦ T.0009923 ¦ T.0009924 ¦ T.0007971 ¦ T.0006953 ¦ T.0007329 ¦ T.0006952 ¦ T.0004974 ¦ T.0006847 ¦ T.0006119 ¦ T.0007165 ¦ T.0006097 ¦ 0 ¦ T.0009393 ¦ T.0009193 ¦ T.0008735 ¦ T.0010467 ¦ T.0008538 ¦ 0 ¦ 0 ¦ T.0010025 ¦ T.0010519 | Upgrade/Retrofit | Asset Condition | T-Line Capacity | N/A | 77.6619 | N/A | 230 kV | 2022-04-18 | 2023-08-15 | 2022-10-05 | Transmission Project Review Process data (Resolution E-5252 Attach B | -314 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/04/23 - Energized April 2023. Castanea Line relacation reamins. Due 5/29/23 | Utility - !Telecom! | Q1223, Q1242, Q1243, Q1379, Q1380, Q1389, Q1391, Q1394, Q1397, Q1398, Q1443, Q1493, Q1495, Q1499, Q1568, Q1586, Q1587, Q1593, Q1709, Q1713, Q1736, Q1740, Q1744, Q1751 | Q1223 | Q1242 | Q1243 | Q1379 | Q1380 | Q1389 | Q1391 | Q1394 | Q1397 | Q1398 | Q1443 | Q1493 | Q1495 | Q1499 | Q1568 | Q1586 | Q1587 | Q1593 | Q1709
Q1499 JASMINE (DA) GEN SITE | 5791718 | T.0006097 | 82Y | The Q1499 Jasmine Solar Project from Cluster 11, proposes to interconnect a 70 megawatt (MW) (net output) Solar + Battery generation facility to Lakeview 70kV in Kern County, California. The project has a contractual In-service date of: 6/15/26 with a current planned In-service date of: 10/13/26 | Engineering more than 50% complete | 2024-07-07 |  |  | Kern | PG&E: North Coast & North Bay Area | Yes | N/A | T.0006452 ¦ Maintenance | Upgrade/Retrofit | Generator Interconnection | Generation Interconnection | N/A | 1.3475 | N/A | 70 kV | 2025-12-02 | 2026-06-15 | 2026-10-13 | Transmission Project Review Process data (Resolution E-5252 Attach B | 120 | Yes |  |  | Final Certified | 45390 | EIR | N/A | Kern County | N/A | NOC: AL 7247-E | 2024-04-26 | Approved | 2024 | 05/06/25 - Project sold to new IC. Potential ISD impact. | Customer - Project Changing Ownership | 1499 | 1499
Q1499 JASMINE T-LINE (DA) | 5791719 | T.0006097 | 82D | The Q1499 Jasmine Solar Project from Cluster 11, proposes to interconnect a 70 megawatt (MW) (net output) Solar + Battery generation facility to Lakeview 70kV in Kern County, California. The project has a contractual In-service date of: 6/15/26 with a current planned In-service date of: 10/13/26 | Engineering more than 50% complete | 2024-07-07 |  |  | Kern | PG&E: Greater Bay Area | Yes | N/A | T.0006452 ¦ Maintenance | New | Generator Interconnection | Generation Interconnection | 0.5 | N/A | 70 | N/A | 2025-12-26 | 2026-06-15 | 2026-10-13 | Transmission Project Review Process data (Resolution E-5252 Attach B | 120 | Yes |  |  | Final Certified | 45390 | EIR | N/A | Kern County | N/A | NOC: AL 7247-E | 2024-04-26 | Approved | 2024 | 05/06/25 - Project sold to new IC. Potential ISD impact. | Customer - Project Changing Ownership | 1499 | 1499
Q1499 JASMINE (DA) LAKEVIEW SUB | 5791720 | T.0006097 | 82Y | The Q1499 Jasmine Solar Project from Cluster 11, proposes to interconnect a 70 megawatt (MW) (net output) Solar + Battery generation facility to Lakeview 70kV in Kern County, California. The project has a contractual In-service date of: 6/15/26 with a current planned In-service date of: 10/13/26 | Engineering more than 50% complete | 2024-07-07 |  |  | Kern | PG&E: North Coast & North Bay Area | Yes | N/A | T.0006452 ¦ Maintenance | New | Generator Interconnection | Generation Interconnection | N/A | 1.3475 | N/A | 70 kV | 2025-04-03 | 2026-06-15 | 2026-10-13 | Transmission Project Review Process data (Resolution E-5252 Attach B | 120 | Yes |  |  | Final Certified | 45390 | EIR | N/A | Kern County | N/A | NOC: AL 7247-E | 2024-04-26 | Approved | 2024 | 05/06/25 - Project sold to new IC. Potential ISD impact. | Customer - Project Changing Ownership | 1499 | 1499
Q1499 JASMINE (NU) LAKEVIEW SUB | 5791721 | T.0006097 | 82W | The Q1499 Jasmine Solar Project from Cluster 11, proposes to interconnect a 70 megawatt (MW) (net output) Solar + Battery generation facility to Lakeview 70kV in Kern County, California. The project has a contractual In-service date of: 6/15/26 with a current planned In-service date of: 10/13/26 | Construction (under 10%) | 2024-07-07 |  |  | Kern | PG&E: North Coast & North Bay Area | Yes | N/A | T.0006452 ¦ Maintenance | New | Generator Interconnection | Generation Interconnection | N/A | 1.3475 | N/A | 70 kV | 2025-03-28 | 2026-06-15 | 2026-10-13 | Transmission Project Review Process data (Resolution E-5252 Attach B | 120 | Yes |  |  | Final Certified | 45390 | EIR | N/A | Kern County | N/A | NOC: AL 7247-E | 2024-04-26 | Approved | 2024 | 05/06/25 - Project sold to new IC. Potential ISD impact. | Customer - Project Changing Ownership | 1499 | 1499
Q1499 JASMINE (NU) COPUS SUB | 5791722 | T.0006097 | 82W | The Q1499 Jasmine Solar Project from Cluster 11, proposes to interconnect a 70 megawatt (MW) (net output) Solar + Battery generation facility to Lakeview 70kV in Kern County, California. The project has a contractual In-service date of: 6/15/26 with a current planned In-service date of: 10/13/26 | Engineering more than 50% complete | 2024-07-07 |  |  | Kern | N/A | Yes | N/A | T.0006452 ¦ Maintenance | Upgrade/Retrofit | Generator Interconnection | Special Protection Scheme | N/A | 0.94829 | N/A | 70 kV | 2026-01-02 | 2026-06-15 | 2026-10-13 | Transmission Project Review Process data (Resolution E-5252 Attach B | 120 | Yes |  |  | Final Certified | 45390 | EIR | N/A | Kern County | N/A | NOC: AL 7247-E | 2024-04-26 | Approved | 2024 | 05/06/25 - Project sold to new IC. Potential ISD impact. | Customer - Project Changing Ownership | 1499 | 1499
Q1499 JASMINE (NU) OLD RIVER SUB | 5791723 | T.0006097 | 82W | The Q1499 Jasmine Solar Project from Cluster 11, proposes to interconnect a 70 megawatt (MW) (net output) Solar + Battery generation facility to Lakeview 70kV in Kern County, California. The project has a contractual In-service date of: 6/15/26 with a current planned In-service date of: 10/13/26 | Construction (under 10%) | 2024-07-07 |  |  | Kern | PG&E Kern Area | Yes | N/A | T.0006452 ¦ Maintenance | Upgrade/Retrofit | Generator Interconnection | Special Protection Scheme | N/A | 1.3755 | N/A | 70 kV | 2025-03-06 | 2026-06-15 | 2026-10-13 | Transmission Project Review Process data (Resolution E-5252 Attach B | 120 | Yes |  |  | Final Certified | 45390 | EIR | N/A | Kern County | N/A | NOC: AL 7247-E | 2024-04-26 | Approved | 2024 | 05/06/25 - Project sold to new IC. Potential ISD impact. | Customer - Project Changing Ownership | 1499 | 1499
Q1499 JASMINE (NU) WHEELER RIDGE SUB | 5791724 | T.0006097 | 82W | The Q1499 Jasmine Solar Project from Cluster 11, proposes to interconnect a 70 megawatt (MW) (net output) Solar + Battery generation facility to Lakeview 70kV in Kern County, California. The project has a contractual In-service date of: 6/15/26 with a current planned In-service date of: 10/13/26 | Construction (25%-50%) | 2024-07-07 |  |  | Kern | PG&E Kern Area | Yes | N/A | T.0006452 ¦ Maintenance | Upgrade/Retrofit | Generator Interconnection | Special Protection Scheme | N/A | 10.403 | N/A | 70 kV | 2025-02-06 | 2026-06-15 | 2026-10-13 | Transmission Project Review Process data (Resolution E-5252 Attach B | 120 | Yes |  |  | Final Certified | 45390 | EIR | N/A | Kern County | N/A | NOC: AL 7247-E | 2024-04-26 | Approved | 2024 | 05/06/25 - Project sold to new IC. Potential ISD impact. | Customer - Project Changing Ownership | 1499 | 1499
Q1499 JASMINE (NU) T-LINE | 5791725 | T.0006097 | 82B | The Q1499 Jasmine Solar Project from Cluster 11, proposes to interconnect a 70 megawatt (MW) (net output) Solar + Battery generation facility to Lakeview 70kV in Kern County, California. The project has a contractual In-service date of: 6/15/26 with a current planned In-service date of: 10/13/26 | Engineering more than 50% complete | 2024-07-07 |  |  | Kern | PG&E Kern Area | Yes | N/A | T.0006452 ¦ Maintenance | New | Generator Interconnection | T-Line Capacity | 0.5 | N/A | 70 | N/A | 2025-11-10 | 2026-06-15 | 2026-10-13 | Transmission Project Review Process data (Resolution E-5252 Attach B | 120 | Yes |  |  | Final Certified | 45363 | EIR | N/A | Kern County | N/A | NOC: AL 7247-E | 2024-04-26 | Approved | 2024 | 05/06/25 - Project sold to new IC. Potential ISD impact. | Customer - Project Changing Ownership | 1499 | 1499
Q1493 AZALEA (DA) GEN SITE | 5792024 | T.0006119 | 82Y | The Q1493 Azalea Project from Cluster 11, proposes to interconnect a 60 megawatt (MW) (net output) Solar + Battery generation facility to Arco 70kV in Kern County, California. The project has a contractual In-service date of: 5/20/25 with a current planned In-service date of: 5/20/25 | Construction (under 10%) | 2024-12-07 |  |  | Kern | #REF! | Yes | N/A | T.0006452 | Upgrade/Retrofit | Generator Interconnection | Generation Interconnection | N/A | 4.5471 | N/A | 70 kV | 2025-03-06 | 2025-05-20 | 2025-05-20 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - Customer moved ISD to May 2025. | - | 1493 | 1493
Q1493 AZALEA (DA) T-LINE | 5792025 | T.0006119 | 82D | The Q1493 Azalea Project from Cluster 11, proposes to interconnect a 60 megawatt (MW) (net output) Solar + Battery generation facility to Arco 70kV in Kern County, California. The project has a contractual In-service date of: 5/20/25 with a current planned In-service date of: 5/20/25 | Operational | 2024-12-07 |  |  | Kern ¦ Kings | ngba | Yes | N/A | T.0006452 | New | Generator Interconnection | Generation Interconnection | 0.5 | N/A | 70 | N/A | 2024-03-04 | 2025-05-20 | 2025-05-20 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - Customer moved ISD to May 2025. | - | 1493 | 1493
Q1493 AZALEA (DA) ARCO SUB | 5792026 | T.0006119 | 82Y | The Q1493 Azalea Project from Cluster 11, proposes to interconnect a 60 megawatt (MW) (net output) Solar + Battery generation facility to Arco 70kV in Kern County, California. The project has a contractual In-service date of: 5/20/25 with a current planned In-service date of: 5/20/25 | Construction (over 75%) | 2024-12-07 |  |  | Kern | #REF! | Yes | N/A | T.0006452 | New | Generator Interconnection | Generation Interconnection | N/A | N/A | N/A | 70 kV | 2023-11-06 | 2025-05-20 | 2025-05-20 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - Customer moved ISD to May 2025. | - | 1493 | 1493
Q1398 SANDRINI 2 WHEELER RIDGE SUB (DA) | 5792218 | T.0004974 | 82Y | The Q1398 Sandrini Sol #2 Project from Cluster 10, proposes to interconnect a 200 megawatt (MW) (net output) Solar generation facility to Wheeler Ridge 230kV in Kern County, California. The project has a contractual In-service date of: 7/6/23 with a current planned In-service date of: 2/7/24 | Planning | N/A |  |  | Madera | PG&E Kern Area | No | N/A | T.0006452 | Upgrade/Retrofit | Asset Condition | Age/Condition - 230/115/70/60 kV Relay Replacement | N/A | 13.266 | N/A | 230 kV | 2030-01-01 | 2023-07-06 | 2024-02-07 | Transmission Project Review Process data (Resolution E-5252 Attach B | 216 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | In-Service - 2/7/24 2/5/24 - Customer installed incorrect components which delayed testing - weather impacts to testing in Jan as well. PPI rescheduled to 2/7 1/3/24 - Sandrini failed their PPI prior to the Holiday's, that is what is pushing them out. The IC didn't get their updated relay settings approved by protection timely. They have since been reviewed and approved, and their 2nd PPI attempt is this week. EMS/SCADA still needs to complete their work, end of January is a more realistic backfeed date. 12/11/23 - PPI scheduled week of 12/11. backfeed in 2024 10/24/23 - Risk to IC to procure some underground comms material (~300 ft). 10/2/23 - with no Fiber in yet, the ISD will slip. IT needs 4 to 5 weeks to get splicing and all circuites up and tested. Planned ISD to shift approximately a month. PPI letter is needed. MMA was approved. Triggered an FRR due to the adding of a battery. 8/21/23 - MMA about to be executed that will take this back to green. 8/7/23 - IC telecom to be completed end of Aug. PGE to follow remaining activities end of Oct. MMA in play need completed due to inverter changes. 07/27/23 - Craig says Customers Telecom is driving the schedule to get their OPGW transition to underground going into the substation. PGE has installed 5 of 6 TL foundations. 6/22/23 - Civil contract pricing received and contract is routed. IC has to cross I-5 and CA-99. Permit Status. String to POCO last week of August. 5/22/23 - ISD depends on IC. | Customer - Bundling Dependencies | 1398 | 1398
Q1398 SANDRINI T-LINE GEN TIE LINE (DA) | 5792219 | T.0004974 | 82D | The Q1398 Sandrini Sol #2 Project from Cluster 10, proposes to interconnect a 200 megawatt (MW) (net output) Solar generation facility to Wheeler Ridge 230kV in Kern County, California. The project has a contractual In-service date of: 7/6/23 with a current planned In-service date of: 2/7/24 | Planning | N/A |  |  | Madera | PG&E Kern Area | No | N/A | T.0006452 | Upgrade/Retrofit | Asset Condition | Age/Condition - 230/115/70/60 kV Relay Replacement | N/A | N/A | N/A | 230 kV | 2030-01-01 | 2023-07-06 | 2024-02-07 | Transmission Project Review Process data (Resolution E-5252 Attach B | 216 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | In-Service - 2/7/24 2/5/24 - Customer installed incorrect components which delayed testing - weather impacts to testing in Jan as well. PPI rescheduled to 2/7 1/3/24 - Sandrini failed their PPI prior to the Holiday's, that is what is pushing them out. The IC didn't get their updated relay settings approved by protection timely. They have since been reviewed and approved, and their 2nd PPI attempt is this week. EMS/SCADA still needs to complete their work, end of January is a more realistic backfeed date. 12/11/23 - PPI scheduled week of 12/11. backfeed in 2024 10/24/23 - Risk to IC to procure some underground comms material (~300 ft). 10/2/23 - with no Fiber in yet, the ISD will slip. IT needs 4 to 5 weeks to get splicing and all circuites up and tested. Planned ISD to shift approximately a month. PPI letter is needed. MMA was approved. Triggered an FRR due to the adding of a battery. 8/21/23 - MMA about to be executed that will take this back to green. 8/7/23 - IC telecom to be completed end of Aug. PGE to follow remaining activities end of Oct. MMA in play need completed due to inverter changes. 07/27/23 - Craig says Customers Telecom is driving the schedule to get their OPGW transition to underground going into the substation. PGE has installed 5 of 6 TL foundations. 6/22/23 - Civil contract pricing received and contract is routed. IC has to cross I-5 and CA-99. Permit Status. String to POCO last week of August. 5/22/23 - ISD depends on IC. | Customer - Bundling Dependencies
Q1244 PROXIMA SOLAR SS (DA) | 5792366 | T.0003770 | 82Y | The Q1244 Proxima Solar Project from Cluster 9, proposes to interconnect a 300 megawatt (MW) (net output) Solar + Battery generation facility to Fink 230kV switching station in Stainslaus County, California. The project has a contractual In-service date of: 10/15/23 with a current planned In-service date of: 3/6/24 | Operational | 2021-10-31 |  |  | Amador ¦ Buena Vista CDP, Amador ¦ Calaveras ¦ Ione, Amador | PG&E Kern Area | No | N/A |  | Upgrade/Retrofit | Reliability | SCADA Switch Installation | N/A | NA | 60 | N/A | 2021-12-06 | 2023-10-15 | 2024-03-06 | Transmission Project Review Process data (Resolution E-5252 Attach B | 143 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | NOC: AL 5801-E | 2020-04-03 | Approved | 2020 | COD - 3/18/24 for 162MW 3/6/24 - The Q1244 Proxima Solar project achieved In-Service Date (ISD) today March 6, 2024. This project will generate 300 MW of renewable PV energy and capable of 150 MW of battery storage. The project encompasses approximately 1,100 acres. Final testing of the facility is scheduled for next Wednesday March 13th, 2024 and a Commercial Operation Date letter is expected by the end of the month. To interconnect the customer project, PG&E teams engineered, permitted, tested and placed into service on March 5, 2024 a greenfield looped Switching Station (SS) 11 acres in size named Fink SS. The SS was an EPC contract type project completed through the competitive bid process. Fink SS connects to the 230 kV system approximately 4 miles north of the PG&E Quinto SS and a few miles south of the third party utility owned 230 kV substation Westley substation in Stanislaus County. To interconnect the new 230 kV SS the project called for protective relay upgrades at Los Banos, Quinto SS, and Westley Substation. The PG&E project team coordinated with Modesto Irrigation District (MID) to get the project successful. There was also telecommunications and testing coordination at Westley Substation MID teams and PG&E teams. The energization of Fink SS and Proxima occurred via radial connection. This energization test process spanned a few days to fully test the SS and the third party customer substation. There is remaining work to be completed in order to energize the Fink SS – Westley 230 kV line and is scheduled to finalize April 1, 2024. This project had many barriers to get towards completion. One of the major barriers was permitting and acquiring the land from Stanislaus County. I want to shout out @Everett, Kirsten and @Crossfield, Scott for essentially being a Stanislaus county resource and spending many days waiting at their counter or hand delivering necessary requirements to complete permitting and acquisition activities. This project kicked off in Q2 2018 with a total of over 165 different resources attending project meetings and lending their expertise throughout the project lifecycle. Thank you to everyone involved in this project and helping to bring expertise and professionalism when interacting with NextEra as well as overcome obstacles and provide a quality product. 3/4/24 -Expecting to energize Proxima on 3/6. Fink SS is 3/5. 2/5/25 - PGE Microwave scope between Mt Oso and MID's Wesley Substation cannot be started until Agreements between MID and PGE are made. Scope and Cost impacts being worked out between multi-parties. Interim solution being reviewed but may conflict with the original scope and schedule. 1/23/24 - MID delays have put IC at risk of default. They are incurring costs due to Generators of battery minimally charging. Impacting their Environmental Air Quality Permits if they keep running longer. 1/11/24 - IC does not have their CAISO letter for Permission to Test which was required to put load on Fink thus energizing both SS and Gensite. ISD moved to March after MID work is complete which would no required Q1244 as load to test Fink. 12/14/23 - IC could not get a CAISO clearance until 12/20 due to telecom commissiong, key predecessor activities, and EoY CAISO clearance congestion. Due to the late December date, the PG&E resources to backfeed the customer are insufficient to safely perform the work. 12/13/23 - PTO letter to CAISO on 12/13. Clearance for backfeed 12/20. Requires Battery Loads to Sync Sw Sta. 12/12/23 - Line Connector assemblies were ACSR and not ACSS. This results in temporary re-rate on the line until the repair can be completed. Estimated at 100 to 150K to fix. Mike Milbury and CM Kevin Withrow know the details. 12/7/23 - SCADA/EMS release planned for 12/11/23. Backfeed planned for 12/15. IC is ready to provide 120MWs of load given 24 hours of notice. Potential they can increase that. MID on a call today due to Turlock irrigation district impact.MID needs the Turlock concent to proceed to EoFeb. 11/1/23 - Verify with SQ ISD Trending to Jan 2024 12/15/23 at this time for ISD. 10/2/23 - MID is no longer critical path. Moved to the end of the sequence and affect COD only. Internal only - PM is looking at possibly pulling the ISD into December. Telecom and NERC activity impacting. 9/19/23 - MID work on the DTT on the line is critical to hit the Tline work sequence. 9/18/23 - ISD is tracking to Jan 2024. 8/21/23 - MID is asking for 25 weeks now. rebalanced the clearance so MID comes at the end. Affect COD but not ISD. 8/7/23 - ISD is likely to delay due to MID. MID asking for 20 weeks to do relay work starting in Oct. Meeting next week discuss. 07/27/23 - Schedule is the same for last note. 6/22/23 - Oct 10-20 Tline to set poles for the new SS loop in. 5/15/23 - ISD is pusing to 2024 due to SS construction. Permanent Land acquisitions still with Legal. T_line foundations installed for the loop-in. Clearance to come back in Fall. | Utility - !Telecom! | 1244 | 1244
Q1349 – ARAMIS - CONTRA COSTA SUB DTT | 5792479 | T.0005689 | 82W | The Q1349 Aramis Power Plant Project from Cluster 10, proposes to interconnect a 100 megawatt (MW) (net output) Solar + Battery generation facility to Cayetano 230kV in Alameda County, California. The project has a contractual In-service date of: 12/3/27 with a current planned In-service date of: 3/6/26 | Construction (25%-50%) | 2023-04-14 |  |  | Antioch, Contra Costa | PG&E: North Valley Area | Yes | N/A | T.0004673 ¦ T.0004673 ¦ T.0008048 | New | Generator Interconnection | Special Protection Scheme | N/A | 15.1779 | N/A | 230 kV | 2025-01-24 | 2027-12-03 | 2026-03-06 | Transmission Project Review Process data (Resolution E-5252 Attach B | -637 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 06/02/25 - Customer mobilization and ground-breaking are scheduled for July, with the final design review expected to conclude in two weeks. The ISD remains set for March 6, 2026. | Customer - !Telecom! | 1349 | 1349
Q1349 – ARAMIS - NEWARK SUB DTT | 5792480 | T.0005689 | 82W | The Q1349 Aramis Power Plant Project from Cluster 10, proposes to interconnect a 100 megawatt (MW) (net output) Solar + Battery generation facility to Cayetano 230kV in Alameda County, California. The project has a contractual In-service date of: 12/3/27 with a current planned In-service date of: 3/6/26 | Engineering more than 50% complete | 2023-04-14 |  |  | Fremont, Alameda | PG&E: North Valley Area | Yes | N/A | T.0004673 ¦ T.0004673 ¦ T.0008048 | New | Generator Interconnection | Special Protection Scheme | N/A | 27.7611 | N/A | 230 kV | 2025-08-26 | 2027-12-03 | 2026-03-06 | Transmission Project Review Process data (Resolution E-5252 Attach B | -637 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 06/02/25 - Customer mobilization and ground-breaking are scheduled for July, with the final design review expected to conclude in two weeks. The ISD remains set for March 6, 2026. | Customer - !Telecom! | 1349 | 1349
Q1349 – ARAMIS - LONE TREE SUB DTT | 5792514 | T.0005689 | 82W | The Q1349 Aramis Power Plant Project from Cluster 10, proposes to interconnect a 100 megawatt (MW) (net output) Solar + Battery generation facility to Cayetano 230kV in Alameda County, California. The project has a contractual In-service date of: 12/3/27 with a current planned In-service date of: 3/6/26 | Construction (25%-50%) | 2023-04-14 |  |  | Antioch, Contra Costa | PG&E: North Valley Area | Yes | N/A | T.0004673 ¦ T.0004673 ¦ T.0008048 | New | Generator Interconnection | Special Protection Scheme | N/A | N/A | N/A | 230 kV | 2024-10-18 | 2027-12-03 | 2026-03-06 | Transmission Project Review Process data (Resolution E-5252 Attach B | -637 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 06/02/25 - Customer mobilization and ground-breaking are scheduled for July, with the final design review expected to conclude in two weeks. The ISD remains set for March 6, 2026. | Customer - !Telecom! | 1349 | 1349
Q1349 - ARAMIS - VINEYARD SUB DTT | 5792515 | T.0005689 | 82W | The Q1349 Aramis Power Plant Project from Cluster 10, proposes to interconnect a 100 megawatt (MW) (net output) Solar + Battery generation facility to Cayetano 230kV in Alameda County, California. The project has a contractual In-service date of: 12/3/27 with a current planned In-service date of: 3/6/26 | Engineering more than 50% complete | 2023-04-14 |  |  | Pleasanton, Alameda | PG&E: North Valley Area | Yes | N/A | T.0004673 ¦ T.0004673 ¦ T.0008048 | New | Generator Interconnection | Special Protection Scheme | N/A | 3.9102 | N/A | 230 kV | 2025-08-06 | 2027-12-03 | 2026-03-06 | Transmission Project Review Process data (Resolution E-5252 Attach B | -637 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 06/02/25 - Customer mobilization and ground-breaking are scheduled for July, with the final design review expected to conclude in two weeks. The ISD remains set for March 6, 2026. | Customer - !Telecom!
PANOCHE 230 KV BUS (RNU) (Q1223/Q1242/Q1 | 5792517 | T.0006452 | 82W | The C9P2-F13-F15 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Gates 230kV in Fresno County, California. | Operational | 2023-08-15 |  |  | Fresno | N/A | Yes | N/A | T.0009863 ¦ T.0005678 ¦ T.0005679 ¦ T.0009923 ¦ T.0009924 ¦ T.0007971 ¦ T.0006953 ¦ T.0007329 ¦ T.0006952 ¦ T.0004974 ¦ T.0006847 ¦ T.0006119 ¦ T.0007165 ¦ T.0006097 ¦ 0 ¦ T.0009393 ¦ T.0009193 ¦ T.0008735 ¦ T.0010467 ¦ T.0008538 ¦ 0 ¦ 0 ¦ T.0010025 ¦ T.0010519 | Upgrade/Retrofit | Generator Interconnection | Generation Interconnection | N/A | 19.3832 | N/A | 230 kV | 2022-07-15 | 2023-08-15 | 2023-04-17 | Transmission Project Review Process data (Resolution E-5252 Attach B | -120 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/04/23 - Energized April 2023. Castanea Line relacation reamins. Due 5/29/23 | Utility - !Telecom! | Q1223, Q1242, Q1243, Q1379, Q1380, Q1389, Q1391, Q1394, Q1397, Q1398, Q1443, Q1493, Q1495, Q1499, Q1568, Q1586, Q1587, Q1593, Q1709, Q1713, Q1736, Q1740, Q1744, Q1751 | Q1223 | Q1242 | Q1243 | Q1379 | Q1380 | Q1389 | Q1391 | Q1394 | Q1397 | Q1398 | Q1443 | Q1493 | Q1495 | Q1499 | Q1568 | Q1586 | Q1587 | Q1593 | Q1709
Q1507 PROSPECT (DA) GEN SITE | 5792767 | T.0006433 | 82Y | The Q1507 Prospect Energy Project from Cluster 11, proposes to interconnect a 49.9 megawatt (MW) (net output) Battery generation facility to Gold Hill 60kV in Sacramento County, California. The project has a contractual In-service date of: 5/2/28 with a current planned In-service date of: 4/18/28 | Engineering more than 50% complete | 2023-08-07 |  |  | Folsom, Sacramento | N/A | Yes | N/A | T.0006348 | New | Generator Interconnection | Generation Interconnection | N/A | 12.8702 | N/A | 60 kV | 2027-11-08 | 2028-05-02 | 2028-04-18 | Transmission Project Review Process data (Resolution E-5252 Attach B | -14 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - Updated ISD in schedule. MMA has been requested. 02/10/25 - IC need to submit new MMA and schedule 11/20/24 - ISD must be moved out on resuming project. Project was due to return in Oct 2024 but has not. | Customer - Permitting (Customer) | 1507 | 1507
Q1507 PROSPECT (DA) T-LINE | 5792768 | T.0006433 | 82D | The Q1507 Prospect Energy Project from Cluster 11, proposes to interconnect a 49.9 megawatt (MW) (net output) Battery generation facility to Gold Hill 60kV in Sacramento County, California. The project has a contractual In-service date of: 5/2/28 with a current planned In-service date of: 4/18/28 | On Hold | 2023-08-07 |  |  | El Dorado ¦ El Dorado Hills CDP, El Dorado ¦ Folsom, Sacramento | N/A | Yes | N/A | T.0006348 | New | Generator Interconnection | Generation Interconnection | 0.052 | N/A | 60 | N/A | 2031-05-20 | 2028-05-02 | 2028-04-18 | Transmission Project Review Process data (Resolution E-5252 Attach B | -14 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - Updated ISD in schedule. MMA has been requested. 02/10/25 - IC need to submit new MMA and schedule 11/20/24 - ISD must be moved out on resuming project. Project was due to return in Oct 2024 but has not. | Customer - Permitting (Customer) | 1507 | 1507
Q1507 PROSPECT (DA) GOLD HILL SUB | 5792769 | T.0006433 | 82Y | The Q1507 Prospect Energy Project from Cluster 11, proposes to interconnect a 49.9 megawatt (MW) (net output) Battery generation facility to Gold Hill 60kV in Sacramento County, California. The project has a contractual In-service date of: 5/2/28 with a current planned In-service date of: 4/18/28 | On Hold | 2023-08-07 |  |  | Folsom, Sacramento | N/A | Yes | N/A | T.0006348 | New | Generator Interconnection | Generation Interconnection | N/A | 12.8702 | N/A | 60 kV | 2031-05-20 | 2028-05-02 | 2028-04-18 | Transmission Project Review Process data (Resolution E-5252 Attach B | -14 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - Updated ISD in schedule. MMA has been requested. 02/10/25 - IC need to submit new MMA and schedule 11/20/24 - ISD must be moved out on resuming project. Project was due to return in Oct 2024 but has not. | Customer - Permitting (Customer) | 1507 | 1507
Q877 CA FLATS-BESS INTERCONNECTION (DA) | 5793119 | T.0006635 | 82D |  | Operational | 2024-09-06 |  |  | N/A | N/A | Yes | N/A | NF | Upgrade/Retrofit | Physical Security | T-Line Capacity | N/A | #REF! | N/A | N/A | N/A | 2022-02-15 | 2021-07-14 | Transmission Project Review Process data (Resolution E-5252 Attach B | -216 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !GO-851 Process! | 877 | 877
TESLA: Install 230 KV MPAC | 5793899 | T.0003456 | 67A |  | Engineering more than 50% complete | 2026-12-01 |  |  | Alameda | PG&E: North Valley Area | No | N/A | NF | Upgrade/Retrofit | Other [See Notes] | T-Line Capacity | N/A | 69.382 | N/A | 230 kV | 2026-12-08 | 2026-12-01 | 2027-02-04 | Transmission Project Review Process data (Resolution E-5252 Attach B | 65 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 03/17/25 - ISD Jan 2028 very achievable, 14 Breakers total for project. 5-31-23 - ISD is not realistic. It is trending into 2026. | Utility - !Telecom! | mitigated until C14 | mitigated until C14
TESLA: Install 230 KV MPAC | 5793900 | T.0003456 | 67A |  | Engineering more than 50% complete | 2026-12-01 |  |  | Alameda | PG&E: North Valley Area | No | N/A | NF | Upgrade/Retrofit | Other [See Notes] | T-Line Capacity | N/A | 69.382 | N/A | 230 kV | 2027-02-10 | 2026-12-01 | 2027-04-07 | Transmission Project Review Process data (Resolution E-5252 Attach B | 127 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 03/17/25 - ISD Jan 2028 very achievable, 14 Breakers total for project. 5-31-23 - ISD is not realistic. It is trending into 2026. | Utility - !Telecom! | mitigated until C14 | mitigated until C14
TESLA: Install 230 KV MPAC | 5793901 | T.0003456 | 67A |  | Engineering more than 50% complete | 2026-12-01 |  |  | Alameda | PG&E: North Valley Area | No | N/A | NF | Upgrade/Retrofit | Other [See Notes] | T-Line Capacity | N/A | 69.382 | N/A | 230 kV | 2027-04-12 | 2026-12-01 | 2027-06-07 | Transmission Project Review Process data (Resolution E-5252 Attach B | 188 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 03/17/25 - ISD Jan 2028 very achievable, 14 Breakers total for project. 5-31-23 - ISD is not realistic. It is trending into 2026. | Utility - !Telecom! | mitigated until C14 | mitigated until C14
TESLA: Install 230 KV MPAC | 5793902 | T.0003456 | 67A |  | Engineering more than 50% complete | 2026-12-01 |  |  | Alameda | PG&E: North Valley Area | No | N/A | NF | Upgrade/Retrofit | Other [See Notes] | T-Line Capacity | N/A | 69.382 | N/A | 230 kV | 2027-06-10 | 2026-12-01 | 2027-08-06 | Transmission Project Review Process data (Resolution E-5252 Attach B | 248 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 03/17/25 - ISD Jan 2028 very achievable, 14 Breakers total for project. 5-31-23 - ISD is not realistic. It is trending into 2026. | Utility - !Telecom! | mitigated until C14 | mitigated until C14
TESLA: Install 230 KV MPAC | 5793907 | T.0003456 | 67A |  | Engineering more than 50% complete | 2026-12-01 |  |  | Alameda | PG&E: North Valley Area | No | N/A | NF | Upgrade/Retrofit | Other [See Notes] | T-Line Capacity | N/A | 69.382 | N/A | 230 kV | 2027-08-10 | 2026-12-01 | 2027-10-05 | Transmission Project Review Process data (Resolution E-5252 Attach B | 308 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 03/17/25 - ISD Jan 2028 very achievable, 14 Breakers total for project. 5-31-23 - ISD is not realistic. It is trending into 2026. | Utility - !Telecom! | mitigated until C14 | mitigated until C14
TESLA: Install 230 KV MPAC | 5793908 | T.0003456 | 67A |  | Engineering more than 50% complete | 2026-12-01 |  |  | Alameda | PG&E: North Valley Area | No | N/A | NF | Upgrade/Retrofit | Other [See Notes] | T-Line Capacity | N/A | 69.382 | N/A | 230 kV | 2027-10-14 | 2026-12-01 | 2027-12-13 | Transmission Project Review Process data (Resolution E-5252 Attach B | 377 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 03/17/25 - ISD Jan 2028 very achievable, 14 Breakers total for project. 5-31-23 - ISD is not realistic. It is trending into 2026. | Utility - !Telecom! | mitigated until C14 | mitigated until C14
TESLA: Install 230 KV MPAC | 5793938 | T.0003456 | 67A |  | Engineering more than 50% complete | 2026-12-01 |  |  | Alameda | PG&E: North Valley Area | No | N/A | NF | Upgrade/Retrofit | Other [See Notes] | T-Line Capacity | N/A | 69.382 | N/A | 230 kV | 2026-08-25 | 2026-12-01 | 2026-10-20 | Transmission Project Review Process data (Resolution E-5252 Attach B | -42 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 03/17/25 - ISD Jan 2028 very achievable, 14 Breakers total for project. 5-31-23 - ISD is not realistic. It is trending into 2026. | Utility - !Telecom! | mitigated until C14 | mitigated until C14
TESLA: Install 230 KV MPAC | 5793940 | T.0003456 | 67A |  | Engineering more than 50% complete | 2026-12-01 |  |  | Alameda | PG&E: North Valley Area | No | N/A | NF | Upgrade/Retrofit | Other [See Notes] | T-Line Capacity | N/A | 69.382 | N/A | 230 kV | 2026-09-30 | 2026-12-01 | 2027-01-20 | Transmission Project Review Process data (Resolution E-5252 Attach B | 50 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 03/17/25 - ISD Jan 2028 very achievable, 14 Breakers total for project. 5-31-23 - ISD is not realistic. It is trending into 2026. | Utility - !Telecom! | mitigated until C14 | mitigated until C14
Tesla Substation 230 kV bus reactors C-D,D-E circuit breakers 372, 382 and 842 overstress | 5793942 | T.0004673 | 61Y | The C11P2-NC01 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Tesla 230kV in Alameda County, California. | Operational | 2023-12-31 |  |  | Alameda | PG&E: North Valley Area | No | 2019 | T.0007195 ¦ T.0005689 ¦ T.0004575 ¦ T.0005689 ¦ T.0004575 ¦ T.0008307 ¦ T.0010648 ¦ T.0010478 ¦ T.0008918 ¦ T.0004354 | Upgrade/Retrofit | Reliability | T-Line Capacity | N/A | 69.382 | N/A | 230 kV | 2023-06-15 | 2023-12-31 | 2024-03-25 | Transmission Project Review Process data (Resolution E-5252 Attach B | 85 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 03/17/25 - Currently energized, remaining punch list items to be completed then start project close out 4/3/24 - Project went ISD 3/25. 12/12/23 - TLine work. 9/25/23 - ISD 3/29/24 is still achievable. 7/31/23 - ISD is achievable. 6/26/23 - ISD is for the last asset going in service. By Nov 2023 3/4 reactors will be in-service. Then the 4th will start. 5-31-23 - On track. See notes below. D-E on track with test program in June 2023. C-D - starts construction June 20. On track to be online by Q1 2024. | Utility - !Telecom! | Q1270, Q1349, Q1363, Q1349, Q1363, Q1461, Q1683, Q1691, Q1702, Q1459 | Q1270 | Q1349 | Q1363 | Q1349 | Q1363 | Q1461 | Q1683 | Q1691 | Q1702 | Q1459
Round Mountain 500 kV Dynamic Voltage Support | 5793953 | T.0006815 | 61Y | The C14P2-NPT02 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Round Mountain 500 kV in Shasta County, California. | Construction (50%-75%) | 2024-12-31 |  |  | Butte | PG&E: North Valley Area | No | 2019 | 0 ¦ 0 ¦ 0 | Upgrade/Retrofit | Reliability | T-Line Capacity | N/A | 47.516 | N/A | 500 kV | 2023-02-15 | 2024-12-31 | 2025-04-01 | Transmission Project Review Process data (Resolution E-5252 Attach B | 91 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom! | Q1844, Q1858, Q1863 | Q1844 | Q1858 | Q1863
Round Mountain 500 kV Dynamic Voltage Support | 5793954 | T.0006815 | 61Y | The C14P2-NPT02 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Round Mountain 500 kV in Shasta County, California. | Construction (10%-25%) | 2024-12-31 |  |  | Round Mountain CDP, Shasta | PG&E: North Valley Area | No | 2019 | 0 ¦ 0 ¦ 0 | Upgrade/Retrofit | Reliability | T-Line Capacity | N/A | 29.1389 | N/A | 500 kV | 2025-02-03 | 2024-12-31 | 2025-11-15 | Transmission Project Review Process data (Resolution E-5252 Attach B | 319 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom! | Q1844, Q1858, Q1863 | Q1844 | Q1858 | Q1863
Q1443 ANGELA (RNU) OLIVE SW STATION | 5794018 | T.0006847 | 82W | The Q1443 Angela (Angiola East) Project from Cluster 11, proposes to interconnect a 40 megawatt (MW) (net output) Solar + Battery generation facility to Olive SW 115kV in Tulare County, California. The project has a contractual In-service date of: 10/15/25 with a current planned In-service date of: 12/17/25 | Operational | 2023-02-07 |  |  | Tulare | N/A | Yes | N/A | T.0006452 ¦ Maintenance | New | Generator Interconnection | Generation Interconnection | N/A | 4.0905 | N/A | 115 kV | 2022-05-13 | 2025-10-15 | 2025-10-15 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - MMA submitted, ISD 10/15/2025, COD 12/15/2025. Tracking ISD in Dec 2025. IC design is delayed. IC in construction at risk to complete in 2025 | Customer - Customer Action
Q1443 ANGELA (RNU) MIDWAY SUB | 5794019 | T.0006847 | 82W | The Q1443 Angela (Angiola East) Project from Cluster 11, proposes to interconnect a 40 megawatt (MW) (net output) Solar + Battery generation facility to Olive SW 115kV in Tulare County, California. The project has a contractual In-service date of: 10/15/25 with a current planned In-service date of: 12/17/25 | Construction (over 75%) | 2023-02-07 |  |  | Buttonwillow CDP, Kern | N/A | Yes | N/A | T.0006452 ¦ Maintenance | Upgrade/Retrofit | Generator Interconnection | Special Protection Scheme | N/A | 94.5324 | N/A | 115 kV | 2022-09-02 | 2025-10-15 | 2025-10-15 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - MMA submitted, ISD 10/15/2025, COD 12/15/2025. Tracking ISD in Dec 2025. IC design is delayed. IC in construction at risk to complete in 2025 | Customer - Customer Action | 1443 | 1443
Q1443 ANGELA (RNU) SMYRNA SUB | 5794020 | T.0006847 | 82W | The Q1443 Angela (Angiola East) Project from Cluster 11, proposes to interconnect a 40 megawatt (MW) (net output) Solar + Battery generation facility to Olive SW 115kV in Tulare County, California. The project has a contractual In-service date of: 10/15/25 with a current planned In-service date of: 12/17/25 | Construction (over 75%) | 2023-02-07 |  |  | Kern | N/A | Yes | N/A | T.0006452 ¦ Maintenance | Upgrade/Retrofit | Generator Interconnection | Special Protection Scheme | N/A | 1.3608 | N/A | 115 kV | 2022-09-02 | 2025-10-15 | 2025-10-15 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - MMA submitted, ISD 10/15/2025, COD 12/15/2025. Tracking ISD in Dec 2025. IC design is delayed. IC in construction at risk to complete in 2025 | Customer - Customer Action | 1443 | 1443
Q1443 ANGELA (RNU) CORCORAN SUB | 5794021 | T.0006847 | 82W | The Q1443 Angela (Angiola East) Project from Cluster 11, proposes to interconnect a 40 megawatt (MW) (net output) Solar + Battery generation facility to Olive SW 115kV in Tulare County, California. The project has a contractual In-service date of: 10/15/25 with a current planned In-service date of: 12/17/25 | Construction (over 75%) | 2023-02-07 |  |  | Kings | PG&E: PG&E: North Valley Area Coast & PG&E: North Valley Area Bay Area | Yes | N/A | T.0006452 ¦ Maintenance | Upgrade/Retrofit | Generator Interconnection | Special Protection Scheme | N/A | 3.8529 | N/A | 115 kV | 2022-09-02 | 2025-10-15 | 2025-10-15 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - MMA submitted, ISD 10/15/2025, COD 12/15/2025. Tracking ISD in Dec 2025. IC design is delayed. IC in construction at risk to complete in 2025 | Customer - Customer Action
Q1443 ANGELA (DA) GEN SITE | 5794022 | T.0006847 | 82Y | The Q1443 Angela (Angiola East) Project from Cluster 11, proposes to interconnect a 40 megawatt (MW) (net output) Solar + Battery generation facility to Olive SW 115kV in Tulare County, California. The project has a contractual In-service date of: 10/15/25 with a current planned In-service date of: 12/17/25 | Engineering more than 50% complete | 2023-02-07 |  |  | Tulare | PG&E Kern Area | Yes | N/A | T.0006452 ¦ Maintenance | Upgrade/Retrofit | Generator Interconnection | Generation Interconnection | N/A | 4.0905 | N/A | 115 kV | 2025-07-23 | 2025-10-15 | 2025-10-15 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - MMA submitted, ISD 10/15/2025, COD 12/15/2025. Tracking ISD in Dec 2025. IC design is delayed. IC in construction at risk to complete in 2025 | Customer - Customer Action | 1443 | 1443
Q1443 ANGELA (DA) OLIVE SW STATION | 5794023 | T.0006847 | 82Y | The Q1443 Angela (Angiola East) Project from Cluster 11, proposes to interconnect a 40 megawatt (MW) (net output) Solar + Battery generation facility to Olive SW 115kV in Tulare County, California. The project has a contractual In-service date of: 10/15/25 with a current planned In-service date of: 12/17/25 | Construction (over 75%) | 2023-02-07 |  |  | Tulare | PG&E Kern Area | Yes | N/A | T.0006452 ¦ Maintenance | New | Generator Interconnection | Generation Interconnection | N/A | 4.0905 | N/A | 115 kV | 2022-05-13 | 2025-10-15 | 2025-10-15 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - MMA submitted, ISD 10/15/2025, COD 12/15/2025. Tracking ISD in Dec 2025. IC design is delayed. IC in construction at risk to complete in 2025 | Customer - Customer Action | 1443 | 1443
Q1443 ANGELA (DA) WHITE RIVER | 5794024 | T.0006847 | 82Y | The Q1443 Angela (Angiola East) Project from Cluster 11, proposes to interconnect a 40 megawatt (MW) (net output) Solar + Battery generation facility to Olive SW 115kV in Tulare County, California. The project has a contractual In-service date of: 10/15/25 with a current planned In-service date of: 12/17/25 | Construction (50%-75%) | 2023-02-07 |  |  | Tulare | N/A | Yes | N/A | T.0006452 ¦ Maintenance | New | Generator Interconnection | Generation Interconnection | N/A | 4.0905 | N/A | 115 kV | 2022-11-01 | 2025-10-15 | 2025-10-15 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - MMA submitted, ISD 10/15/2025, COD 12/15/2025. Tracking ISD in Dec 2025. IC design is delayed. IC in construction at risk to complete in 2025 | Customer - Customer Action | 1443 | 1443
Q1443 ANGELA (DA) T-LINE | 5794025 | T.0006847 | 82D | The Q1443 Angela (Angiola East) Project from Cluster 11, proposes to interconnect a 40 megawatt (MW) (net output) Solar + Battery generation facility to Olive SW 115kV in Tulare County, California. The project has a contractual In-service date of: 10/15/25 with a current planned In-service date of: 12/17/25 | Engineering more than 50% complete | 2023-02-07 |  |  | Corcoran, Kings ¦ Kings ¦ Tulare | ngba | Yes | N/A | T.0006452 ¦ Maintenance | New | Generator Interconnection | Generation Interconnection | 0.5 | N/A | 115 | N/A | 2025-04-03 | 2025-10-15 | 2025-10-15 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - MMA submitted, ISD 10/15/2025, COD 12/15/2025. Tracking ISD in Dec 2025. IC design is delayed. IC in construction at risk to complete in 2025 | Customer - Customer Action | 1443 | 1443
Q1397 Sandrini Sol 1 Gen Site–DA | 5794389 | T.0006952 | 82Y | The Q1397 Sandrini Sol #1 Project from Cluster 10, proposes to interconnect a 100 megawatt (MW) (net output) Solar + Battery generation facility to Wheeler Ridge 70kV in Kern County, California. The project has a contractual In-service date of: 7/6/23 with a current planned In-service date of: 2/7/24 | Operational | 2021-11-01 |  |  | San Joaquin | PG&E: Greater Fresno Area | Yes | N/A | T.0006452 | New | Generator Interconnection | Generation Interconnection | 0.9 | 6.1366 | 60 | N/A | 2022-02-15 | 2023-07-06 | 2024-02-07 | Transmission Project Review Process data (Resolution E-5252 Attach B | 216 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | NOC: AL 5770-E | 2020-02-25 | Approved | 2020 | In-Service - 2/7/24 2/5/24 - Customer installed incorrect components which delayed testing - weather impacts to testing in Jan as well. PPI rescheduled to 2/7 12/11/23 - PPI scheduled week of 12/11. backfeed in 2024. 10/2/23 - with no Fiber in yet, the ISD will slip. IT needs 4 to 5 weeks to get splicing and all circuites up and tested. Planned ISD to shift approximately a month. PPI letter is needed. - 9/18/23 - ISD looks to be late Oct - early Nov. Tline has October 10th clearance for 115kV and 70kV Line crossings 8/21/23 - MMA about to be executed that will take this back to green. 07/27/23 - See Q1398 comments. 5/22/23 - ISD depends on IC. | Customer - Material | 1397 | 1397
Q1455-JANUS SOLAR-GEN SITE (DA) | 5794556 | T.0006968 | 82Y | The Q1455 Janus Project from Cluster 11, proposes to interconnect a 80 megawatt (MW) (net output) Solar + Battery generation facility to Cortina 60kV in Colusa County, California. The project has a contractual In-service date of: 4/15/26 with a current planned In-service date of: 6/30/26 | Operational | 2021-11-01 |  |  | San Joaquin | PG&E Kern Area | Yes | N/A | T.0007629 ¦ T.0007629 | New | Generator Interconnection | Generation Interconnection | 0.9 | 6.1366 | 60 | N/A | 2022-02-15 | 2026-04-15 | 2026-06-30 | Transmission Project Review Process data (Resolution E-5252 Attach B | 76 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | NOC: AL 5770-E | 2020-02-25 | Approved | 2020 | 05/06/25 - Tracking ISD to Q2 2026 due to IC permitting. | Customer - Permitting (Customer) | 1455 | 1455
Q1455-JANUS SOLAR-TLINE (DA) | 5794557 | T.0006968 | 82D | The Q1455 Janus Project from Cluster 11, proposes to interconnect a 80 megawatt (MW) (net output) Solar + Battery generation facility to Cortina 60kV in Colusa County, California. The project has a contractual In-service date of: 4/15/26 with a current planned In-service date of: 6/30/26 | Operational | 2021-11-01 |  |  | San Joaquin | PG&E: Greater Fresno Area | Yes | N/A | T.0007629 ¦ T.0007629 | New | Generator Interconnection | Generation Interconnection | 0.9 | N/A | 60 | N/A | 2022-02-15 | 2026-04-15 | 2026-06-30 | Transmission Project Review Process data (Resolution E-5252 Attach B | 76 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | NOC: AL 5770-E | 2020-02-25 | Approved | 2020 | 05/06/25 - Tracking ISD to Q2 2026 due to IC permitting. | Customer - Permitting (Customer) | 1455 | 1455
Q1455-JANUS SOLAR-STATION (DA) | 5794558 | T.0006968 | 82Y | The Q1455 Janus Project from Cluster 11, proposes to interconnect a 80 megawatt (MW) (net output) Solar + Battery generation facility to Cortina 60kV in Colusa County, California. The project has a contractual In-service date of: 4/15/26 with a current planned In-service date of: 6/30/26 | Operational | 2021-11-01 |  |  | San Joaquin | PG&E Kern Area | Yes | N/A | T.0007629 ¦ T.0007629 | New | Generator Interconnection | Generation Interconnection | 0.9 | 6.1366 | 60 | N/A | 2022-02-15 | 2026-04-15 | 2026-06-30 | Transmission Project Review Process data (Resolution E-5252 Attach B | 76 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | NOC: AL 5770-E | 2020-02-25 | Approved | 2020 | 05/06/25 - Tracking ISD to Q2 2026 due to IC permitting. | Customer - Permitting (Customer) | 1455 | 1455
Q1455-JANUS SOLAR-STATION (RNU) | 5794559 | T.0006968 | 82W | The Q1455 Janus Project from Cluster 11, proposes to interconnect a 80 megawatt (MW) (net output) Solar + Battery generation facility to Cortina 60kV in Colusa County, California. The project has a contractual In-service date of: 4/15/26 with a current planned In-service date of: 6/30/26 | Operational | 2021-11-01 |  |  | San Joaquin | PG&E: Greater Fresno Area | Yes | N/A | T.0007629 ¦ T.0007629 | New | Generator Interconnection | Generation Interconnection | 0.9 | 6.1366 | 60 | N/A | 2022-02-15 | 2026-04-15 | 2026-06-30 | Transmission Project Review Process data (Resolution E-5252 Attach B | 76 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | NOC: AL 5770-E | 2020-02-25 | Approved | 2020 | 05/06/25 - Tracking ISD to Q2 2026 due to IC permitting. | Customer - Permitting (Customer) | 1455 | 1455
Q1272 CASCADE RECON STOCKTON A WEBBER RN | 5794597 | T.0004561 | 82W | The C9P2-N09 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Stockton A-Weber #3 60 kV Line in San Joaquin County, California. | Operational | 2021-11-01 |  |  | San Joaquin |  | Yes | N/A | T.0004561 | New | Generator Interconnection | Generation Interconnection | 0.9 | 6.1366 | 60 | N/A | 2022-02-15 | 2021-11-01 | 2023-05-31 | Transmission Project Review Process data (Resolution E-5252 Attach B | 576 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | NOC: AL 5770-E | 2020-02-25 | Approved | 2020 | In-service 3/31/23 | Utility - !Telecom! | Q1272 | Q1272
Round Mountain 500 kV Dynamic Voltage Support | 5794601 | T.0006815 | 60Z | The C14P2-NPT02 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Round Mountain 500 kV in Shasta County, California. | Construction (25%-50%) | 2024-12-31 |  |  | Butte ¦ Butte Creek Canyon CDP, Butte ¦ Chico, Butte ¦ Cohasset CDP, Butte ¦ Round Mountain CDP, Shasta ¦ Shasta ¦ Tehama ¦ Whitmore CDP, Shasta | PG&E: North Valley Area | No | 2019 | 0 ¦ 0 ¦ 0 | New | Reliability | T-Line Capacity | N/A | NA | 500 | N/A | 2024-10-25 | 2024-12-31 | 2025-11-15 | Transmission Project Review Process data (Resolution E-5252 Attach B | 319 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom!
OAKLAND UNIT 2 T-LINE FIBER–DA | 5794807 | T.0006936 | 82D | The 0051CONV Oakland C Unit 2 Repower Project from Cluster Repower, proposes to interconnect a 55 megawatt (MW) (net output) Repower generation facility to Oakland C Substation in Alameda County, California. The project has a contractual In-service date of: 12/1/26 with a current planned In-service date of: 12/1/26 | Operational | 2020-04-30 |  |  | Merced | PG&E: Greater Fresno Area | Yes | N/A |  | Upgrade/Retrofit | Generator Interconnection | Generation Interconnection | N/A | N/A | N/A | 230 kV | 2023-03-06 | 2026-12-01 | 2026-12-01 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | Final Certified | 41219 | EIR | N/A | Merced County | N/A | NOC: AL 4180-E | 2013-01-17 | Approved | 2013 | 05/06/25 - IC stopped their scope and has not engaged project management. MMA in process to change date to 2026. | Utility - !Telecom! | 0051CONV | 0051CONV
OAKLAND UNIT 2 GEN SITE - DA | 5794808 | T.0006936 | 82D | The 0051CONV Oakland C Unit 2 Repower Project from Cluster Repower, proposes to interconnect a 55 megawatt (MW) (net output) Repower generation facility to Oakland C Substation in Alameda County, California. The project has a contractual In-service date of: 12/1/26 with a current planned In-service date of: 12/1/26 | Operational | 2020-04-30 |  |  | Merced | PG&E: Greater Fresno Area | Yes | N/A |  | Upgrade/Retrofit | Generator Interconnection | Generation Interconnection | N/A | N/A | N/A | 230 kV | 2023-03-06 | 2026-12-01 | 2026-12-01 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | Final Certified | 41219 | EIR | N/A | Merced County | N/A | NOC: AL 4180-E | 2013-01-17 | Approved | 2013 | 05/06/25 - IC stopped their scope and has not engaged project management. MMA in process to change date to 2026. | Utility - !Telecom! | 0051CONV | 0051CONV
OAKLAND UNIT 2 C SUB-DA | 5794809 | T.0006936 | 82Y | The 0051CONV Oakland C Unit 2 Repower Project from Cluster Repower, proposes to interconnect a 55 megawatt (MW) (net output) Repower generation facility to Oakland C Substation in Alameda County, California. The project has a contractual In-service date of: 12/1/26 with a current planned In-service date of: 12/1/26 | Operational | 2020-04-30 |  |  | Merced | PG&E: Greater Fresno Area | Yes | N/A |  | Upgrade/Retrofit | Generator Interconnection | Generation Interconnection | N/A | 53.2803 | N/A | 230 kV | 2023-03-06 | 2026-12-01 | 2026-12-01 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | Final Certified | 41219 | EIR | N/A | Merced County | N/A | NOC: AL 4180-E | 2013-01-17 | Approved | 2013 | 05/06/25 - IC stopped their scope and has not engaged project management. MMA in process to change date to 2026. | Utility - !Telecom! | 0051CONV | 0051CONV
Q1391 SONRISA (DA) GEN SITE | 5794823 | T.0006953 | 82Y | The Q1391 Sonrisa Project from Cluster 10, proposes to interconnect a 200 megawatt (MW) (net output) Solar + Battery generation facility to Tranquility SW 230kV in Fresno County, California. The project has a contractual In-service date of: 5/11/25 with a current planned In-service date of: 3/27/26 | Operational | 2020-04-30 |  |  | Merced | N/A | Yes | N/A | T.0006452 | Upgrade/Retrofit | Generator Interconnection | Generation Interconnection | N/A | 53.2803 | N/A | 230 kV | 2023-03-06 | 2025-05-11 | 2026-03-27 | Transmission Project Review Process data (Resolution E-5252 Attach B | 320 | Yes |  |  | Final Certified | 41219 | EIR | N/A | Merced County | N/A | NOC: AL 4180-E | 2013-01-17 | Approved | 2013 | 05/06/25 -IC design delays. PGE deliverables already completed by Q1135 Scarlet ISD tracking to Q1 2026 | Customer - Project Design | 1391 | 1391
LOS BANOS: UPGD EQUIP TO 3000A–EGI QUINT | 5794846 | T.0003789 | 82W | The C8P1-35 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Los Banos-Quinto SS 230 kV in Merced County, California. | Operational | 2020-04-30 |  |  | Merced | KERN | Yes | N/A | T.0003750 ¦ T.0004565 ¦ T.0003005 ¦ T.0002987 ¦ T.0004560 ¦ T.0003743 ¦ T.0003742 ¦ T.0004490 ¦ T.0003744 | Upgrade/Retrofit | Generator Interconnection | Substation Capacity | N/A | 53.2803 | N/A | 230 kV | 2023-03-06 | 2020-04-30 | 2023-05-08 | Transmission Project Review Process data (Resolution E-5252 Attach B | 1103 | Yes |  |  | Final Certified | 41219 | EIR | N/A | Merced County | N/A | NOC: AL 4180-E | 2013-01-17 | Approved | 2013 | In-service 5/5/23 | Utility - !Telecom! | Q1117, Q1120, Q1127, Q1128, Q1139, Q1158, Q1135, Q1129, Q1143 | Q1117 | Q1120 | Q1127 | Q1128 | Q1139 | Q1158 | Q1135 | Q1129 | Q1143
PANOCHE: UPGD EQUIP TO 1517A – EGI PADRE | 5794847 | T.0003792 | 82W | The C8P1-34 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Padre Flat-Panoche 230kV Line #1 in Kings County, California. | Operational | 2021-09-30 |  |  | Fresno | PG&E: North Valley Area | Yes | N/A | T.0003005 ¦ T.0002987 ¦ T.0003743 ¦ T.0003742 ¦ T.0004490 ¦ 0 | Upgrade/Retrofit | Generator Interconnection | Substation Capacity | N/A | 19.3832 | N/A | 230 kV | 2024-01-22 | 2021-09-30 | 2024-05-10 | Transmission Project Review Process data (Resolution E-5252 Attach B | 953 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 04/23/25 - Operative | Utility - !Telecom! | Q1127, Q1128, Q1158, Q1135, Q1129, Q1568, 2181-WD | Q1127 | Q1128 | Q1158 | Q1135 | Q1129 | Q1568 | 2181-WD
LOS BANOS: UPGD EQUIP TO 1900A–EGI PADRE | 5794848 | T.0003016 | 82W | The C8P2-6 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Los-Banos-Padre Flat SS 230kV in Merced County, California. | Operational | 2021-09-30 |  |  | Merced | kern | Yes | N/A | T.0003005 ¦ T.0002987 ¦ T.0003743 ¦ T.0004490 ¦ 0 ¦ T.0010467 ¦ T.0008538 ¦ T.0003742 | Upgrade/Retrofit | Generator Interconnection | Substation Capacity | N/A | 53.2803 | N/A | 230 kV | 2022-10-31 | 2021-09-30 | 2022-12-24 | Transmission Project Review Process data (Resolution E-5252 Attach B | 450 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | NOC: AL 6527-E | 2022-03-11 | Approved | 2022 |  | Utility - !Telecom! | Q1127, Q1128, Q1158, Q1129, Q1568, 2181-WD, Q1709, Q1713, 2226-WD, 2484-WD, Q1135 | Q1127 | Q1128 | Q1158 | Q1129 | Q1568 | 2181-WD | Q1709 | Q1713 | 2226-WD | 2484-WD | Q1135
Q1374 ELKHORN GEN SITE (DA) | 5794899 | T.0004697 | 82Y | The Q1374 Elkhorn Energy Storage Project from Cluster 10, proposes to interconnect a 182.5 megawatt (MW) (net output) Battery generation facility to Moss Landing 115kV in Monterey County, California. The project has a contractual In-service date of: with a current planned In-service date of: 6/9/21 | Operational | N/A |  |  | Sutter | PG&E: Greater Bay Area | No | N/A |  | Replace | Emergency Event | Replace Transformer | N/A | 9.3219 | N/A | 230 ¦ 115 kV | 2022-07-05 | 2020-10-15 | 2021-06-09 | Transmission Project Review Process data (Resolution E-5252 Attach B | 237 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | - | 1374 | 1374
Q1010 DYER SUMMIT WIND RECONDUCTOR WORK | 5795058 | T.0002228 | 82D | The POS-Q1010-LDNU Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the US Windpower 60kV Tap in Alameda County, California. | Engineering more than 50% complete | 2023-04-14 |  |  | Alameda | PG&E: North Valley Area | Yes | N/A |  | New | Generator Interconnection | Generation Interconnection | N/A | N/A | N/A | 230 kV | 2025-07-30 | 2023-04-14 | 2025-09-05 | Transmission Project Review Process data (Resolution E-5252 Attach B | 875 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom! | Q1010 | Q1010
Q1349 - ARAMIS - JACKSON RANCH SUB DTT | 5795098 | T.0005689 | 82W | The Q1349 Aramis Power Plant Project from Cluster 10, proposes to interconnect a 100 megawatt (MW) (net output) Solar + Battery generation facility to Cayetano 230kV in Alameda County, California. The project has a contractual In-service date of: 12/3/27 with a current planned In-service date of: 3/6/26 | Engineering more than 50% complete | 2023-04-14 |  |  | Alameda | PG&E Kern Area | Yes | N/A | T.0004673 ¦ T.0004673 ¦ T.0008048 | New | Generator Interconnection | Special Protection Scheme | N/A | 0.26068 | N/A | 230 kV | 2025-07-30 | 2027-12-03 | 2026-03-06 | Transmission Project Review Process data (Resolution E-5252 Attach B | -637 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 06/02/25 - Customer mobilization and ground-breaking are scheduled for July, with the final design review expected to conclude in two weeks. The ISD remains set for March 6, 2026. | Customer - !Telecom! | 1349 | 1349
Q1540 - PLANO STORAGE – GEN SITE-DA | 5795347 | T.0007032 | 82D | The Q1540 Plano Energy Storage Project from Cluster ISP, proposes to interconnect a 350 megawatt (MW) (net output) Battery generation facility to Moss Landing 500kV in Monterey County, California. The project has a contractual In-service date of: 12/1/21 with a current planned In-service date of: 3/1/23 | Operational | 2024-12-31 |  |  | Grayson CDP, Stanislaus ¦ Manteca, San Joaquin ¦ San Joaquin ¦ Stanislaus | N/A | No | 2021 |  | Upgrade/Retrofit | Reliability | Line Reconductoring | 1.13 | NA | 60 | N/A | 2024-12-09 | 2021-12-01 | 2023-03-01 | Transmission Project Review Process data (Resolution E-5252 Attach B | 455 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | NOC: AL 7359-E | 2024-08-23 | Approved | 2024 | COD - 5/19/23 for In-Service - 3/1/23 | Utility - Bundling Dependencies | 1540 | 1540
Q1350 - PAULSELL CROW CREEK SUB-DA | 5795661 | T.0007108 | 82Y | The Q1350 Paulsell Solar Project from Cluster 10, proposes to interconnect a 20 megawatt (MW) (net output) Solar + Battery generation facility to Crow Creek SW 60kV in Stanislaus County, California. The project has a contractual In-service date of: 12/1/23 with a current planned In-service date of: 3/28/24 | Operational | 2023-02-01 |  |  | Stanislaus | #REF! | Yes | N/A |  | Upgrade/Retrofit | Generator Interconnection | Generation Interconnection | N/A | 1.036 | N/A | 60 kV | 2024-01-03 | 2023-12-01 | 2024-03-28 | Transmission Project Review Process data (Resolution E-5252 Attach B | 118 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | In-Service - 3/37/24 3/4/24 - Customer Failed PPI. New clearance set for 3/27. 2/5/24 -Likely ISD End of April 2024. Pending easements for Microwave at Wesley. 1/23/24 - Due to weather, the IC could not complete the test reports for submittal. Working on catchback and rescheduling PPI. 1/8/24 - Targeting COD by 4/1 per the IC. 12/12/23 - ISD is tracking. Gentie work is completed. 11/1/23 - ISD Tracking 10/2/23 - Work at Crowcreek is complete. IC has started construction 9/20/23 - Tline Switch has TID distribution equipment to be removed by the 3rd party. Low risk associated to the tline work and coordination. 9/18/23 - IT resource constraints due to overall volume of work. 8/7/23 - IC has not started construction. Expect ISD to trend later in Q1 2024. 07/27/23 - Need update on the IC schedule. 6/22/23 - some IC delays related IC customers XFMR order. Verify with SDQ1 expected. Check in with SDQ1 | Customer - !Telecom! | 1350 | 1350
Q1350 - PAULSELL GEN SITE-DA | 5795662 | T.0007108 | 82Y | The Q1350 Paulsell Solar Project from Cluster 10, proposes to interconnect a 20 megawatt (MW) (net output) Solar + Battery generation facility to Crow Creek SW 60kV in Stanislaus County, California. The project has a contractual In-service date of: 12/1/23 with a current planned In-service date of: 3/28/24 | Operational | 2023-02-01 |  |  | Stanislaus | 0 | Yes | N/A |  | Upgrade/Retrofit | Generator Interconnection | Generation Interconnection | N/A | 1.036 | N/A | 60 kV | 2024-01-03 | 2023-12-01 | 2024-03-28 | Transmission Project Review Process data (Resolution E-5252 Attach B | 118 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | In-Service - 3/37/24 3/4/24 - Customer Failed PPI. New clearance set for 3/27. 2/5/24 -Likely ISD End of April 2024. Pending easements for Microwave at Wesley. 1/23/24 - Due to weather, the IC could not complete the test reports for submittal. Working on catchback and rescheduling PPI. 1/8/24 - Targeting COD by 4/1 per the IC. 12/12/23 - ISD is tracking. Gentie work is completed. 11/1/23 - ISD Tracking 10/2/23 - Work at Crowcreek is complete. IC has started construction 9/20/23 - Tline Switch has TID distribution equipment to be removed by the 3rd party. Low risk associated to the tline work and coordination. 9/18/23 - IT resource constraints due to overall volume of work. 8/7/23 - IC has not started construction. Expect ISD to trend later in Q1 2024. 07/27/23 - Need update on the IC schedule. 6/22/23 - some IC delays related IC customers XFMR order. Verify with SDQ1 expected. Check in with SDQ1 | Customer - !Telecom! | 1350 | 1350
Q1350 - PAULSELL T-LINE DA | 5795663 | T.0007108 | 82D | The Q1350 Paulsell Solar Project from Cluster 10, proposes to interconnect a 20 megawatt (MW) (net output) Solar + Battery generation facility to Crow Creek SW 60kV in Stanislaus County, California. The project has a contractual In-service date of: 12/1/23 with a current planned In-service date of: 3/28/24 | Operational | 2023-02-01 |  |  | Crows Landing CDP, Stanislaus ¦ Stanislaus | 0 | Yes | N/A |  | New | Generator Interconnection | Generation Interconnection | 0.1 | NA | 60 | N/A | 2023-11-27 | 2023-12-01 | 2024-03-28 | Transmission Project Review Process data (Resolution E-5252 Attach B | 118 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | In-Service - 3/37/24 3/4/24 - Customer Failed PPI. New clearance set for 3/27. 2/5/24 -Likely ISD End of April 2024. Pending easements for Microwave at Wesley. 1/23/24 - Due to weather, the IC could not complete the test reports for submittal. Working on catchback and rescheduling PPI. 1/8/24 - Targeting COD by 4/1 per the IC. 12/12/23 - ISD is tracking. Gentie work is completed. 11/1/23 - ISD Tracking 10/2/23 - Work at Crowcreek is complete. IC has started construction 9/20/23 - Tline Switch has TID distribution equipment to be removed by the 3rd party. Low risk associated to the tline work and coordination. 9/18/23 - IT resource constraints due to overall volume of work. 8/7/23 - IC has not started construction. Expect ISD to trend later in Q1 2024. 07/27/23 - Need update on the IC schedule. 6/22/23 - some IC delays related IC customers XFMR order. Verify with SDQ1 expected. Check in with SDQ1 | Customer - !Telecom! | 1350 | 1350
Q1350 - PAULSELL CROW CREEK SUB-RNU | 5795664 | T.0007108 | 82W | The Q1350 Paulsell Solar Project from Cluster 10, proposes to interconnect a 20 megawatt (MW) (net output) Solar + Battery generation facility to Crow Creek SW 60kV in Stanislaus County, California. The project has a contractual In-service date of: 12/1/23 with a current planned In-service date of: 3/28/24 | Operational | 2023-02-01 |  |  | Stanislaus | fresno | Yes | N/A |  | New | Generator Interconnection | Generation Interconnection | N/A | 1.036 | N/A | 60 kV | 2023-01-02 | 2023-12-01 | 2024-03-28 | Transmission Project Review Process data (Resolution E-5252 Attach B | 118 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | In-Service - 3/37/24 3/4/24 - Customer Failed PPI. New clearance set for 3/27. 2/5/24 -Likely ISD End of April 2024. Pending easements for Microwave at Wesley. 1/23/24 - Due to weather, the IC could not complete the test reports for submittal. Working on catchback and rescheduling PPI. 1/8/24 - Targeting COD by 4/1 per the IC. 12/12/23 - ISD is tracking. Gentie work is completed. 11/1/23 - ISD Tracking 10/2/23 - Work at Crowcreek is complete. IC has started construction 9/20/23 - Tline Switch has TID distribution equipment to be removed by the 3rd party. Low risk associated to the tline work and coordination. 9/18/23 - IT resource constraints due to overall volume of work. 8/7/23 - IC has not started construction. Expect ISD to trend later in Q1 2024. 07/27/23 - Need update on the IC schedule. 6/22/23 - some IC delays related IC customers XFMR order. Verify with SDQ1 expected. Check in with SDQ1 | Customer - !Telecom! | 1350 | 1350
TESLA: Install 230 KV MPAC | 5795704 | T.0003456 | 67A |  | Engineering more than 50% complete | 2026-12-01 |  |  | San Joaquin | PG&E: North Valley Area | No | N/A | NF | Upgrade/Retrofit | Other [See Notes] | T-Line Capacity | N/A | 6.1366 | N/A | 230 kV | 2027-12-09 | 2026-12-01 | 2028-02-07 | Transmission Project Review Process data (Resolution E-5252 Attach B | 433 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 03/17/25 - ISD Jan 2028 very achievable, 14 Breakers total for project. 5-31-23 - ISD is not realistic. It is trending into 2026. | Utility - !Telecom! | mitigated until C14 | mitigated until C14
TESLA: Install 230 KV MPAC | 5795708 | T.0003456 | 67A |  | Engineering more than 50% complete | 2026-12-01 |  |  | Brentwood, Alameda | PG&E: North Valley Area | No | N/A | NF | Upgrade/Retrofit | Other [See Notes] | T-Line Capacity | N/A | NA | N/A | 230 kV | 2028-06-12 | 2026-12-01 | 2028-08-08 | Transmission Project Review Process data (Resolution E-5252 Attach B | 616 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 03/17/25 - ISD Jan 2028 very achievable, 14 Breakers total for project. 5-31-23 - ISD is not realistic. It is trending into 2026. | Utility - !Telecom! | mitigated until C14 | mitigated until C14
TESLA: Install 230 KV MPAC | 5795709 | T.0003456 | 67A |  | Engineering more than 50% complete | 2026-12-01 |  |  | Alameda | PG&E: North Valley Area | No | N/A | NF | Upgrade/Retrofit | Other [See Notes] | T-Line Capacity | N/A | 2.4538 | N/A | 230 kV | 2028-08-10 | 2026-12-01 | 2028-10-05 | Transmission Project Review Process data (Resolution E-5252 Attach B | 674 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 03/17/25 - ISD Jan 2028 very achievable, 14 Breakers total for project. 5-31-23 - ISD is not realistic. It is trending into 2026. | Utility - !Telecom! | mitigated until C14 | mitigated until C14
CASTANEA LINE RELOCATIONS | 5795825 | T.0006452 | 82B | The C9P2-F13-F15 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Gates 230kV in Fresno County, California. | Operational | 2023-08-15 |  |  | Fresno | N/A | Yes | N/A | T.0009863 ¦ T.0005678 ¦ T.0005679 ¦ T.0009923 ¦ T.0009924 ¦ T.0007971 ¦ T.0006953 ¦ T.0007329 ¦ T.0006952 ¦ T.0004974 ¦ T.0006847 ¦ T.0006119 ¦ T.0007165 ¦ T.0006097 ¦ 0 ¦ T.0009393 ¦ T.0009193 ¦ T.0008735 ¦ T.0010467 ¦ T.0008538 ¦ 0 ¦ 0 ¦ T.0010025 ¦ T.0010519 | Relocate | Generator Interconnection | Generation Interconnection | 0.02 | N/A | 230 | N/A | 2023-03-13 | 2023-08-15 | 2023-05-23 | Transmission Project Review Process data (Resolution E-5252 Attach B | -84 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/04/23 - Energized April 2023. Castanea Line relacation reamins. Due 5/29/23 | Utility - !Telecom! | Q1223, Q1242, Q1243, Q1379, Q1380, Q1389, Q1391, Q1394, Q1397, Q1398, Q1443, Q1493, Q1495, Q1499, Q1568, Q1586, Q1587, Q1593, Q1709, Q1713, Q1736, Q1740, Q1744, Q1751 | Q1223 | Q1242 | Q1243 | Q1379 | Q1380 | Q1389 | Q1391 | Q1394 | Q1397 | Q1398 | Q1443 | Q1493 | Q1495 | Q1499 | Q1568 | Q1586 | Q1587 | Q1593 | Q1709
Q1010 DYER SUMMIT WIND RECONDUCTOR WORK | 5795882 | T.0002228 | 82B | The POS-Q1010-LDNU Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the US Windpower 60kV Tap in Alameda County, California. | Operational | 2021-11-30 |  |  | Benicia, Solano ¦ Fairfield, Solano ¦ Hartley CDP, Solano ¦ Solano ¦ Vacaville, Solano ¦ Vallejo, Solano | N/A | Yes | N/A |  | Replace | Asset Condition | T-Line Capacity | N/A | N/A | 115 | N/A | 2022-05-06 | 2021-11-30 | 2022-05-11 | Transmission Project Review Process data (Resolution E-5252 Attach B | 162 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom! | Q1010 | Q1010
TESLA: Install 230 KV MPAC | 5795886 | T.0003456 | 67A |  | Engineering more than 50% complete | 2026-12-01 |  |  | Alameda | PG&E: North Valley Area | No | N/A | NF | New | Other [See Notes] | T-Line Capacity | N/A | 69.382 | N/A | 230 kV | 2025-12-29 | 2026-12-01 | 2026-11-20 | Transmission Project Review Process data (Resolution E-5252 Attach B | -11 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 03/17/25 - ISD Jan 2028 very achievable, 14 Breakers total for project. 5-31-23 - ISD is not realistic. It is trending into 2026. | Utility - !Telecom! | mitigated until C14 | mitigated until C14
GATES-PANOCHE 230 LINE RELOCATIONS | 5795899 | T.0006452 | 82B | The C9P2-F13-F15 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Gates 230kV in Fresno County, California. | Operational | 2023-08-15 |  |  | Fresno | N/A | Yes | N/A | T.0009863 ¦ T.0005678 ¦ T.0005679 ¦ T.0009923 ¦ T.0009924 ¦ T.0007971 ¦ T.0006953 ¦ T.0007329 ¦ T.0006952 ¦ T.0004974 ¦ T.0006847 ¦ T.0006119 ¦ T.0007165 ¦ T.0006097 ¦ 0 ¦ T.0009393 ¦ T.0009193 ¦ T.0008735 ¦ T.0010467 ¦ T.0008538 ¦ 0 ¦ 0 ¦ T.0010025 ¦ T.0010519 | Relocate | Generator Interconnection | Generation Interconnection | 0.02 | N/A | 230 | N/A | 2023-01-09 | 2023-08-15 | 2023-04-17 | Transmission Project Review Process data (Resolution E-5252 Attach B | -120 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/04/23 - Energized April 2023. Castanea Line relacation reamins. Due 5/29/23 | Utility - !Telecom! | Q1223, Q1242, Q1243, Q1379, Q1380, Q1389, Q1391, Q1394, Q1397, Q1398, Q1443, Q1493, Q1495, Q1499, Q1568, Q1586, Q1587, Q1593, Q1709, Q1713, Q1736, Q1740, Q1744, Q1751 | Q1223 | Q1242 | Q1243 | Q1379 | Q1380 | Q1389 | Q1391 | Q1394 | Q1397 | Q1398 | Q1443 | Q1493 | Q1495 | Q1499 | Q1568 | Q1586 | Q1587 | Q1593 | Q1709
Q1470 CABALLERO STORAGE-MESA SUB DA | 5796079 | T.0007181 | 82Y | The Q1470 Caballero Storage Project from Cluster 11, proposes to interconnect a 99.7 megawatt (MW) (net output) Battery generation facility to Mesa 230kV in San Luis Obispo County, California. The project has a contractual In-service date of: 9/15/24 with a current planned In-service date of: 10/9/24 | Operational | 2023-10-01 |  |  | Nipomo CDP, San Luis Obispo | PG&E Kern Area | Yes | N/A | Maintenance ¦ Maintenance | New | Generator Interconnection | Generation Interconnection | N/A | N/A | N/A | 230 kV | 2023-05-08 | 2024-09-15 | 2024-10-09 | Transmission Project Review Process data (Resolution E-5252 Attach B | 24 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | ISD on track to Sept 2024. | - | 1470 | 1470
Q1470 CABALLERO STORAGE-GENSITE DA | 5796080 | T.0007181 | 82Y | The Q1470 Caballero Storage Project from Cluster 11, proposes to interconnect a 99.7 megawatt (MW) (net output) Battery generation facility to Mesa 230kV in San Luis Obispo County, California. The project has a contractual In-service date of: 9/15/24 with a current planned In-service date of: 10/9/24 | Operational | 2023-10-01 |  |  | Nipomo CDP, San Luis Obispo | PG&E Kern Area | Yes | N/A | Maintenance ¦ Maintenance | Upgrade/Retrofit | Generator Interconnection | Generation Interconnection | N/A | 10.5414 | N/A | 230 kV | 2024-09-30 | 2024-09-15 | 2024-10-09 | Transmission Project Review Process data (Resolution E-5252 Attach B | 24 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | ISD on track to Sept 2024. | - | 1470 | 1470
Q1470 CABALLERO STORAGE -TRANSMISSION DA | 5796081 | T.0007181 | 82D | The Q1470 Caballero Storage Project from Cluster 11, proposes to interconnect a 99.7 megawatt (MW) (net output) Battery generation facility to Mesa 230kV in San Luis Obispo County, California. The project has a contractual In-service date of: 9/15/24 with a current planned In-service date of: 10/9/24 | Operational | 2023-10-01 |  |  | Nipomo CDP, San Luis Obispo | PG&E Kern Area | Yes | N/A | Maintenance ¦ Maintenance | New | Generator Interconnection | Generation Interconnection | N/A | N/A | N/A | 230 kV | 2023-06-01 | 2024-09-15 | 2024-10-09 | Transmission Project Review Process data (Resolution E-5252 Attach B | 24 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | ISD on track to Sept 2024. | - | 1470 | 1470
Q1470 CABALLERO STORAGE-MESA SUB IRNU | 5796082 | T.0007181 | 82W | The Q1470 Caballero Storage Project from Cluster 11, proposes to interconnect a 99.7 megawatt (MW) (net output) Battery generation facility to Mesa 230kV in San Luis Obispo County, California. The project has a contractual In-service date of: 9/15/24 with a current planned In-service date of: 10/9/24 | Operational | 2023-10-01 |  |  | Nipomo CDP, San Luis Obispo | PG&E Kern Area | Yes | N/A | Maintenance ¦ Maintenance | New | Generator Interconnection | Generation Interconnection | N/A | 10.5414 | N/A | 230 kV | 2023-06-01 | 2024-09-15 | 2024-10-09 | Transmission Project Review Process data (Resolution E-5252 Attach B | 24 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | ISD on track to Sept 2024. | - | 1470 | 1470
Q1470 CABALLERO STORAGE-DC PP IRNU | 5796083 | T.0007181 | 82W | The Q1470 Caballero Storage Project from Cluster 11, proposes to interconnect a 99.7 megawatt (MW) (net output) Battery generation facility to Mesa 230kV in San Luis Obispo County, California. The project has a contractual In-service date of: 9/15/24 with a current planned In-service date of: 10/9/24 | Operational | 2023-10-01 |  |  | San Luis Obispo | PG&E Kern Area | Yes | N/A | Maintenance ¦ Maintenance | Upgrade/Retrofit | Generator Interconnection | Special Protection Scheme | N/A | 35.6227 | N/A | 230 kV | 2024-07-29 | 2024-09-15 | 2024-10-09 | Transmission Project Review Process data (Resolution E-5252 Attach B | 24 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | ISD on track to Sept 2024. | - | 1470 | 1470
Q1470 CABALLERO STORAGE-MORRO SUB IRNU | 5796084 | T.0007181 | 82W | The Q1470 Caballero Storage Project from Cluster 11, proposes to interconnect a 99.7 megawatt (MW) (net output) Battery generation facility to Mesa 230kV in San Luis Obispo County, California. The project has a contractual In-service date of: 9/15/24 with a current planned In-service date of: 10/9/24 | Operational | 2023-10-01 |  |  | Morro Bay, San Luis Obispo | PG&E Kern Area | Yes | N/A | Maintenance ¦ Maintenance | Upgrade/Retrofit | Generator Interconnection | Special Protection Scheme | N/A | 7.6079 | N/A | 230 kV | 2023-12-01 | 2024-09-15 | 2024-10-09 | Transmission Project Review Process data (Resolution E-5252 Attach B | 24 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | ISD on track to Sept 2024. | -
Q1495 CHALAN SOLAR (DA) ARCO SUB | 5796085 | T.0007165 | 82Y | The Q1495 Chalan Solar Project from Cluster 11, proposes to interconnect a 64.9 megawatt (MW) (net output) Solar + Battery generation facility to Arco 230kV in Kern County, California. The project has a contractual In-service date of: 12/20/24 with a current planned In-service date of: 3/24/26 | Construction (50%-75%) | 2024-05-30 |  |  | Kern | 0 | Yes | N/A | T.0007289 ¦ T.0006452 | New | Generator Interconnection | Generation Interconnection | N/A | 4.5471 | N/A | 230 kV | 2023-07-25 | 2024-12-20 | 2026-03-24 | Transmission Project Review Process data (Resolution E-5252 Attach B | 459 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - MMA submitted to change ISD and Technology. With PGE for Round 4 review. Tracking ISD to Dec 2025 with risk to complete in 2025. | Customer - Construction Delays | 1495 | 1495
Q1495 CHALAN SOLAR (DA) GEN SITE | 5796086 | T.0007165 | 82Y | The Q1495 Chalan Solar Project from Cluster 11, proposes to interconnect a 64.9 megawatt (MW) (net output) Solar + Battery generation facility to Arco 230kV in Kern County, California. The project has a contractual In-service date of: 12/20/24 with a current planned In-service date of: 3/24/26 | Engineering more than 50% complete | 2024-05-30 |  |  | Kern | 0 | Yes | N/A | T.0007289 ¦ T.0006452 | Upgrade/Retrofit | Generator Interconnection | Generation Interconnection | N/A | 4.5471 | N/A | 230 kV | 2025-06-03 | 2024-12-20 | 2026-03-24 | Transmission Project Review Process data (Resolution E-5252 Attach B | 459 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - MMA submitted to change ISD and Technology. With PGE for Round 4 review. Tracking ISD to Dec 2025 with risk to complete in 2025. | Customer - Construction Delays | 1495 | 1495
Q1495 CHALAN SOLAR (DA) T LINE | 5796087 | T.0007165 | 82D | The Q1495 Chalan Solar Project from Cluster 11, proposes to interconnect a 64.9 megawatt (MW) (net output) Solar + Battery generation facility to Arco 230kV in Kern County, California. The project has a contractual In-service date of: 12/20/24 with a current planned In-service date of: 3/24/26 | Engineering more than 50% complete | 2024-05-30 |  |  | Avenal, Kings ¦ Fresno ¦ Kern ¦ Kings | kern | Yes | N/A | T.0007289 ¦ T.0006452 | New | Generator Interconnection | Generation Interconnection | 0.1 | NA | 230 | N/A | 2025-04-02 | 2024-12-20 | 2026-03-24 | Transmission Project Review Process data (Resolution E-5252 Attach B | 459 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - MMA submitted to change ISD and Technology. With PGE for Round 4 review. Tracking ISD to Dec 2025 with risk to complete in 2025. | Customer - Construction Delays | 1495 | 1495
Q1495 CHALAN SOLAR (RNU) ARCO SUB | 5796088 | T.0007165 | 82W | The Q1495 Chalan Solar Project from Cluster 11, proposes to interconnect a 64.9 megawatt (MW) (net output) Solar + Battery generation facility to Arco 230kV in Kern County, California. The project has a contractual In-service date of: 12/20/24 with a current planned In-service date of: 3/24/26 | Operational | 2024-05-30 |  |  | Kern | N/A | Yes | N/A | T.0007289 ¦ T.0006452 | New | Generator Interconnection | Generation Interconnection | N/A | 4.5471 | N/A | 230 kV | 2023-07-24 | 2024-12-20 | 2026-03-24 | Transmission Project Review Process data (Resolution E-5252 Attach B | 459 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - MMA submitted to change ISD and Technology. With PGE for Round 4 review. Tracking ISD to Dec 2025 with risk to complete in 2025. | Customer - Construction Delays | 1495 | 1495
Q1270 - CORBY VACA-DIXON SUB WORK-DA | 5796188 | T.0007195 | 82Y | The Q1270 Corby Energy Storage Project from Cluster 9, proposes to interconnect a 300 megawatt (MW) (net output) Battery generation facility to Vaca Dixon 230kV in Solano County, California. The project has a contractual In-service date of: 2/28/27 with a current planned In-service date of: 2/28/27 | Engineering more than 50% complete | 2024-02-01 |  |  | Solano | PG&E Kern Area | Yes | N/A | T.0008048 ¦ T.0004673 ¦ T.0001609 ¦ T.0007288 | New | Generator Interconnection | Generation Interconnection | N/A | 42.1076 | N/A | 230 kV | 2025-07-29 | 2027-02-28 | 2027-02-28 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 06/02/25 - ISD reset to the contract ISD until construction clearances and sequencing can be verified. This depends on the Vaca OSB mitigation with ISD in Dec 2026. 05/19/25 - The breaker delivery and outdoor construction begin in June 2025, with design reviews and orders progressing. No restraints reported, next steps include T-Line 60% design completion and steel structure orders by July 2025. Tracking ISD in Q4 2026 | - | 1270 | 1270
Q1270 - CORBY GEN SITE-DA | 5796189 | T.0007195 | 82Y | The Q1270 Corby Energy Storage Project from Cluster 9, proposes to interconnect a 300 megawatt (MW) (net output) Battery generation facility to Vaca Dixon 230kV in Solano County, California. The project has a contractual In-service date of: 2/28/27 with a current planned In-service date of: 2/28/27 | Engineering more than 50% complete | 2024-02-01 |  |  | Solano | PG&E Kern Area | Yes | N/A | T.0008048 ¦ T.0004673 ¦ T.0001609 ¦ T.0007288 | New | Generator Interconnection | Generation Interconnection | N/A | 42.1076 | N/A | 230 kV | 2025-07-29 | 2027-02-28 | 2027-02-28 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 06/02/25 - ISD reset to the contract ISD until construction clearances and sequencing can be verified. This depends on the Vaca OSB mitigation with ISD in Dec 2026. 05/19/25 - The breaker delivery and outdoor construction begin in June 2025, with design reviews and orders progressing. No restraints reported, next steps include T-Line 60% design completion and steel structure orders by July 2025. Tracking ISD in Q4 2026 | - | 1270 | 1270
Q1270 CORBY T-LINE-DA | 5796190 | T.0007195 | 82D | The Q1270 Corby Energy Storage Project from Cluster 9, proposes to interconnect a 300 megawatt (MW) (net output) Battery generation facility to Vaca Dixon 230kV in Solano County, California. The project has a contractual In-service date of: 2/28/27 with a current planned In-service date of: 2/28/27 | Engineering more than 50% complete | 2024-02-01 |  |  | Solano | PG&E Kern Area | Yes | N/A | T.0008048 ¦ T.0004673 ¦ T.0001609 ¦ T.0007288 | New | Generator Interconnection | Generation Interconnection | N/A | N/A | N/A | 230 kV | 2025-07-29 | 2027-02-28 | 2027-02-28 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 06/02/25 - ISD reset to the contract ISD until construction clearances and sequencing can be verified. This depends on the Vaca OSB mitigation with ISD in Dec 2026. 05/19/25 - The breaker delivery and outdoor construction begin in June 2025, with design reviews and orders progressing. No restraints reported, next steps include T-Line 60% design completion and steel structure orders by July 2025. Tracking ISD in Q4 2026 | - | 1270 | 1270
Q1270-CORBY VACA-DIXON SUB-RNU | 5796191 | T.0007195 | 82W | The Q1270 Corby Energy Storage Project from Cluster 9, proposes to interconnect a 300 megawatt (MW) (net output) Battery generation facility to Vaca Dixon 230kV in Solano County, California. The project has a contractual In-service date of: 2/28/27 with a current planned In-service date of: 2/28/27 | Engineering more than 50% complete | 2024-02-01 |  |  | Solano | PG&E Kern Area | Yes | N/A | T.0008048 ¦ T.0004673 ¦ T.0001609 ¦ T.0007288 | New | Generator Interconnection | Generation Interconnection | N/A | 42.1076 | N/A | 230 kV | 2025-07-29 | 2027-02-28 | 2027-02-28 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 06/02/25 - ISD reset to the contract ISD until construction clearances and sequencing can be verified. This depends on the Vaca OSB mitigation with ISD in Dec 2026. 05/19/25 - The breaker delivery and outdoor construction begin in June 2025, with design reviews and orders progressing. No restraints reported, next steps include T-Line 60% design completion and steel structure orders by July 2025. Tracking ISD in Q4 2026 | -
Q1382-LAS CAMAS 1-LOS BANOS SUB DA | 5796580 | T.0007250 | 82Y | The Q1382 Las Camas 1 Project from Cluster 10, proposes to interconnect a 100 megawatt (MW) (net output) Solar generation facility to Los Banos 230kV in Merced County, California. The project has a contractual In-service date of: 3/30/25 with a current planned In-service date of: 7/17/26 | Construction (under 10%) | 2025-03-30 |  |  | Merced | PG&E Kern Area | Yes | N/A |  | New | Generator Interconnection | Generation Interconnection | N/A | N/A | N/A | 230 kV | 2025-02-03 | 2025-03-30 | 2026-07-17 | Transmission Project Review Process data (Resolution E-5252 Attach B | 474 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - MMA required to push ISD to Q3 2026 | - | 1382 | 1382
Q1382-LAS CAMAS 1-GEN-SITE DA | 5796581 | T.0007250 | 82Y | The Q1382 Las Camas 1 Project from Cluster 10, proposes to interconnect a 100 megawatt (MW) (net output) Solar generation facility to Los Banos 230kV in Merced County, California. The project has a contractual In-service date of: 3/30/25 with a current planned In-service date of: 7/17/26 | Engineering more than 50% complete | 2025-03-30 |  |  | Merced | PG&E Kern Area | Yes | N/A |  | Upgrade/Retrofit | Generator Interconnection | Generation Interconnection | N/A | 53.2803 | N/A | 230 kV | 2025-12-02 | 2025-03-30 | 2026-07-17 | Transmission Project Review Process data (Resolution E-5252 Attach B | 474 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - MMA required to push ISD to Q3 2026 | - | 1382 | 1382
Q1382-LAS CAMAS 1-T-LINE DA | 5796582 | T.0007250 | 82D | The Q1382 Las Camas 1 Project from Cluster 10, proposes to interconnect a 100 megawatt (MW) (net output) Solar generation facility to Los Banos 230kV in Merced County, California. The project has a contractual In-service date of: 3/30/25 with a current planned In-service date of: 7/17/26 | Engineering more than 50% complete | 2025-03-30 |  |  | Merced | PG&E Kern Area | Yes | N/A |  | New | Generator Interconnection | Generation Interconnection | 2 | NA | 230 | N/A | 2025-09-23 | 2025-03-30 | 2026-07-17 | Transmission Project Review Process data (Resolution E-5252 Attach B | 474 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - MMA required to push ISD to Q3 2026 | -
Q1382-LAS CAMAS 1-LOS BANOS SUB RNU | 5796583 | T.0007250 | 82W | The Q1382 Las Camas 1 Project from Cluster 10, proposes to interconnect a 100 megawatt (MW) (net output) Solar generation facility to Los Banos 230kV in Merced County, California. The project has a contractual In-service date of: 3/30/25 with a current planned In-service date of: 7/17/26 | Construction (under 10%) | 2025-03-30 |  |  | Merced | PG&E Kern Area | Yes | N/A |  | New | Generator Interconnection | Generation Interconnection | N/A | 53.2803 | N/A | 230 kV | 2025-01-13 | 2025-03-30 | 2026-07-17 | Transmission Project Review Process data (Resolution E-5252 Attach B | 474 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - MMA required to push ISD to Q3 2026 | - | 1382 | 1382
GATES: REPLACE CBS 352, 362, 372 | 5796864 | T.0007289 | 82W | The C12P2-PNU-02 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Gates 230kV in Fresno County, California. | Operational | 2023-03-31 |  |  | Fresno | N/A | Yes | N/A | T.0004565 ¦ T.0004560 ¦ T.0003743 ¦ T.0003742 ¦ T.0009863 ¦ T.0005678 ¦ T.0005679 ¦ T.0007971 ¦ T.0007722 ¦ T.0007165 ¦ T.0008735 ¦ T.0007731 | Replace | Generator Interconnection | Substation Capacity | N/A | 77.6619 | N/A | 230 kV | 2022-10-24 | 2023-03-31 | 2023-07-12 | Transmission Project Review Process data (Resolution E-5252 Attach B | 103 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | In-service 7/12/23 | Utility - !Telecom! | Q1120, Q1139, Q1158, Q1135, Q1223, Q1242, Q1243, Q1389, Q1479, Q1495, Q1593, Q1596 | Q1120 | Q1139 | Q1158 | Q1135 | Q1223 | Q1242 | Q1243 | Q1389 | Q1479 | Q1495 | Q1593 | Q1596
TESLA 500KV: REPLACE CB 542 AND CB 642 | 5796865 | T.0007288 | 82W | The 20rsmt-5 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Tesla 500kV in Alameda County, California. | Operational | 2024-09-30 |  |  | Alameda | N/A | Yes | N/A | T.0004354 ¦ 0 ¦ T.0008918 | Replace | Generator Interconnection | Generation Interconnection | N/A | N/A | N/A | 500 kV | 2024-09-16 | 2024-09-30 | 2025-03-27 | Transmission Project Review Process data (Resolution E-5252 Attach B | 178 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom! | Q1459, Q1553, Q1702 | Q1459 | Q1553 | Q1702
METCALF: REPLACE OVERSTRESSED CBS | 5796866 | T.0007291 | 82W | The 20rsmt-4 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Metcalf 115kV in Santa Clara County, California. | Engineering more than 50% complete | 2028-01-28 |  |  | Santa Clara | N/A | Yes | N/A | T.0008230 ¦ T.0007467 ¦ 0 ¦ T.0010944 ¦ 0 | Replace | Generator Interconnection | Substation Capacity | N/A | 37.8815 | N/A | 115 kV | 2026-05-19 | 2028-01-28 | 2027-04-19 | Transmission Project Review Process data (Resolution E-5252 Attach B | -284 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom! | Q1442, Q1539, Q1553, Q1866, Q1889 | Q1442 | Q1539 | Q1553 | Q1866 | Q1889
Q1394 - DRIFTWOOD STELLA MIDWAY SUB DA | 5796966 | T.0007329 | 82Y | The Q1394 Driftwood Stella Project from Cluster 10, proposes to interconnect a 200 megawatt (MW) (net output) Solar + Battery generation facility to Midway 115kV in Kern County, California. The project has a contractual In-service date of: 4/1/26 with a current planned In-service date of: 4/27/26 | Engineering more than 50% complete | 2028-01-28 |  |  | Santa Clara | N/A | No | N/A | Maintenance ¦ Maintenance ¦ T.0006452 | Replace | Generator Interconnection | Generation Interconnection | N/A | N/A | N/A | 230 kV | 2027-07-08 | 2024-02-01 | 2026-04-27 | Transmission Project Review Process data (Resolution E-5252 Attach B | 816 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - Tracking ISD to April 2026. IC late on deliverables | - | 1394 | 1394
Q1394 - DRIFTWOOD STELLA GEN SITE DA | 5796967 | T.0007329 | 82Y | The Q1394 Driftwood Stella Project from Cluster 10, proposes to interconnect a 200 megawatt (MW) (net output) Solar + Battery generation facility to Midway 115kV in Kern County, California. The project has a contractual In-service date of: 4/1/26 with a current planned In-service date of: 4/27/26 | Engineering more than 50% complete | 2028-01-28 |  |  | Santa Clara | N/A | No | N/A | Maintenance ¦ Maintenance ¦ T.0006452 | Replace | Generator Interconnection | Generation Interconnection | N/A | 37.8815 | N/A | 230 kV | 2027-07-08 | 2024-02-01 | 2026-04-27 | Transmission Project Review Process data (Resolution E-5252 Attach B | 816 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - Tracking ISD to April 2026. IC late on deliverables | - | 1394 | 1394
Q1394 - DRIFTWOOD STELLA MIDWAY SUB RNU | 5796968 | T.0007329 | 82W | The Q1394 Driftwood Stella Project from Cluster 10, proposes to interconnect a 200 megawatt (MW) (net output) Solar + Battery generation facility to Midway 115kV in Kern County, California. The project has a contractual In-service date of: 4/1/26 with a current planned In-service date of: 4/27/26 | Engineering more than 50% complete | 2028-01-28 |  |  | Santa Clara | N/A | No | N/A | Maintenance ¦ Maintenance ¦ T.0006452 | Replace | Generator Interconnection | Generation Interconnection | N/A | 37.8815 | N/A | 230 kV | 2027-07-08 | 2024-02-01 | 2026-04-27 | Transmission Project Review Process data (Resolution E-5252 Attach B | 816 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - Tracking ISD to April 2026. IC late on deliverables | - | 1394 | 1394
Q1394 - DRIFTWOOD STELLA T-LINE DA | 5796970 | T.0007329 | 82D | The Q1394 Driftwood Stella Project from Cluster 10, proposes to interconnect a 200 megawatt (MW) (net output) Solar + Battery generation facility to Midway 115kV in Kern County, California. The project has a contractual In-service date of: 4/1/26 with a current planned In-service date of: 4/27/26 | Engineering more than 50% complete | 2028-01-28 |  |  | Santa Clara | N/A | No | N/A | Maintenance ¦ Maintenance ¦ T.0006452 | Replace | Generator Interconnection | Generation Interconnection | N/A | N/A | N/A | 230 kV | 2027-07-08 | 2024-02-01 | 2026-04-27 | Transmission Project Review Process data (Resolution E-5252 Attach B | 816 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - Tracking ISD to April 2026. IC late on deliverables | -
Metcalf 115kV: (New XFMR Reactors): BK1-4 | 5796971 | T.0007291 | 64C | The 20rsmt-4 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Metcalf 115kV in Santa Clara County, California. | Engineering more than 50% complete | 2028-01-28 |  |  | Santa Clara | PG&E: North Valley Area | No | N/A | T.0008230 ¦ T.0007467 ¦ 0 ¦ T.0010944 ¦ 0 | Replace | Generator Interconnection | T-Line Capacity | N/A | 37.8815 | N/A | 230 kV | 2027-07-08 | 2028-01-28 | 2028-01-28 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom! | Q1442, Q1539, Q1553, Q1866, Q1889 | Q1442 | Q1539 | Q1553 | Q1866 | Q1889
Q1463 SOLANO - GEN SITE (DA) | 5797639 | T.0007418 | 82Y | The Q1463 Solano 4 Wind Project from Cluster 11, proposes to interconnect a 90.8 megawatt (MW) (net output) Wind Turbine generation facility to Birds Landing SW 230kV in Solano County, California. The project has a contractual In-service date of: 2/1/25 with a current planned In-service date of: 12/15/23 | Planning | N/A |  |  | Novato, Marin | PG&E: Greater Bay Area | No | N/A | T.0007846 ¦ T.0008048 ¦ T.0001609 ¦ T.0004421 | Upgrade/Retrofit | Other [See Notes] | Modular Protection and Automation Control | N/A | N/A | N/A | 230 kV | 2027-04-01 | 2025-02-01 | 2023-12-15 | Transmission Project Review Process data (Resolution E-5252 Attach B | -414 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | Customer Curtailed until 2026 | Utility - GIP Upgrades | 1463 | 1463
TESLA 500KV: REPLACE CB 612 | 5797750 | T.0007288 | 82W | The 20rsmt-5 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Tesla 500kV in Alameda County, California. | Engineering more than 50% complete | 2024-09-30 |  |  | Alameda | N/A | Yes | N/A | T.0004354 ¦ 0 ¦ T.0008918 | Replace | Generator Interconnection | Substation Capacity | N/A | 69.382 | N/A | 500 kV | 2025-10-01 | 2024-09-30 | 2026-06-08 | Transmission Project Review Process data (Resolution E-5252 Attach B | 616 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom! | Q1459, Q1553, Q1702 | Q1459 | Q1553 | Q1702
Q1557 NOOSA ENERGY STORAGE T-LINE DA | 5797827 | T.0007445 | 82D | The Q1557 Noosa Energy Storage Project from Cluster 12, proposes to interconnect a 99 megawatt (MW) (net output) Battery generation facility to Ripon 115kV in San Joaquin County, California. The project has a contractual In-service date of: 1/29/26 with a current planned In-service date of: 3/31/26 | Engineering more than 50% complete | 2025-01-10 |  |  | Ripon, San Joaquin | PG&E: Greater Fresno Area | Yes | N/A | T.0007979 ¦ T.0007979 ¦ T.0007979 ¦ T.0004515 | New | Generator Interconnection | Generation Interconnection | 0.19 | N/A | 115 | N/A | 2025-07-28 | 2026-01-29 | 2026-03-31 | Transmission Project Review Process data (Resolution E-5252 Attach B | 61 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 06/02/25 - MMA was submitted. Customer has not started construction yet. It is expected the IC cannot finish Gensite construction and interconnection until Q1 2026. | -
Q1557 NOOSA ENERGY STORAGE RIPON SUB RNU | 5797828 | T.0007445 | 82W | The Q1557 Noosa Energy Storage Project from Cluster 12, proposes to interconnect a 99 megawatt (MW) (net output) Battery generation facility to Ripon 115kV in San Joaquin County, California. The project has a contractual In-service date of: 1/29/26 with a current planned In-service date of: 3/31/26 | Construction (50%-75%) | 2025-01-10 |  |  | Ripon, San Joaquin | PG&E: Greater Fresno Area | Yes | N/A | T.0007979 ¦ T.0007979 ¦ T.0007979 ¦ T.0004515 | New | Generator Interconnection | Generation Interconnection | N/A | N/A | N/A | 115 kV | 2024-02-12 | 2026-01-29 | 2026-03-31 | Transmission Project Review Process data (Resolution E-5252 Attach B | 61 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 06/02/25 - MMA was submitted. Customer has not started construction yet. It is expected the IC cannot finish Gensite construction and interconnection until Q1 2026. | - | 1557 | 1557
Q1557 NOOSA ENERGY STORAGE STAN PH RNU | 5797829 | T.0007445 | 82W | The Q1557 Noosa Energy Storage Project from Cluster 12, proposes to interconnect a 99 megawatt (MW) (net output) Battery generation facility to Ripon 115kV in San Joaquin County, California. The project has a contractual In-service date of: 1/29/26 with a current planned In-service date of: 3/31/26 | Construction (10%-25%) | 2025-01-10 |  |  | Ripon, San Joaquin | PG&E: Greater Fresno Area | Yes | N/A | T.0007979 ¦ T.0007979 ¦ T.0007979 ¦ T.0004515 | Upgrade/Retrofit | Generator Interconnection | Special Protection Scheme | N/A | N/A | N/A | 115 kV | 2025-02-11 | 2026-01-29 | 2026-03-31 | Transmission Project Review Process data (Resolution E-5252 Attach B | 61 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 06/02/25 - MMA was submitted. Customer has not started construction yet. It is expected the IC cannot finish Gensite construction and interconnection until Q1 2026. | - | 1557 | 1557
Q1557 NOOSA ENERGY STORAGE MELO SUB RNU | 5797830 | T.0007445 | 82W | The Q1557 Noosa Energy Storage Project from Cluster 12, proposes to interconnect a 99 megawatt (MW) (net output) Battery generation facility to Ripon 115kV in San Joaquin County, California. The project has a contractual In-service date of: 1/29/26 with a current planned In-service date of: 3/31/26 | Construction (10%-25%) | 2025-01-10 |  |  | Ripon, San Joaquin | PG&E: Greater Fresno Area | Yes | N/A | T.0007979 ¦ T.0007979 ¦ T.0007979 ¦ T.0004515 | Upgrade/Retrofit | Generator Interconnection | Special Protection Scheme | N/A | 2.0603 | N/A | 115 kV | 2025-02-05 | 2026-01-29 | 2026-03-31 | Transmission Project Review Process data (Resolution E-5252 Attach B | 61 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 06/02/25 - MMA was submitted. Customer has not started construction yet. It is expected the IC cannot finish Gensite construction and interconnection until Q1 2026. | - | 1557 | 1557
Q1557 NOOSA ENERGY STORAGE RIVER JCT RNU | 5797831 | T.0007445 | 82W | The Q1557 Noosa Energy Storage Project from Cluster 12, proposes to interconnect a 99 megawatt (MW) (net output) Battery generation facility to Ripon 115kV in San Joaquin County, California. The project has a contractual In-service date of: 1/29/26 with a current planned In-service date of: 3/31/26 | Engineering more than 50% complete | 2025-01-10 |  |  | Ripon, San Joaquin | PG&E: Greater Fresno Area | Yes | N/A | T.0007979 ¦ T.0007979 ¦ T.0007979 ¦ T.0004515 | New | Generator Interconnection | Special Protection Scheme | N/A | 1.3123 | N/A | 115 kV | 2025-05-08 | 2026-01-29 | 2026-03-31 | Transmission Project Review Process data (Resolution E-5252 Attach B | 61 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 06/02/25 - MMA was submitted. Customer has not started construction yet. It is expected the IC cannot finish Gensite construction and interconnection until Q1 2026. | - | 1557 | 1557
Q1557 NOOSA ENERGY STORAGE MANT SUB RNU | 5797832 | T.0007445 | 82W | The Q1557 Noosa Energy Storage Project from Cluster 12, proposes to interconnect a 99 megawatt (MW) (net output) Battery generation facility to Ripon 115kV in San Joaquin County, California. The project has a contractual In-service date of: 1/29/26 with a current planned In-service date of: 3/31/26 | Construction (10%-25%) | 2025-01-10 |  |  | Ripon, San Joaquin | N/A | Yes | N/A | T.0007979 ¦ T.0007979 ¦ T.0007979 ¦ T.0004515 | Upgrade/Retrofit | Generator Interconnection | Special Protection Scheme | N/A | 2.0603 | N/A | 115 kV | 2025-02-05 | 2026-01-29 | 2026-03-31 | Transmission Project Review Process data (Resolution E-5252 Attach B | 61 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 06/02/25 - MMA was submitted. Customer has not started construction yet. It is expected the IC cannot finish Gensite construction and interconnection until Q1 2026. | - | 1557 | 1557
Q1557 NOOSA ENERGY STORAGE RIPON SUB DA | 5797834 | T.0007445 | 82Y | The Q1557 Noosa Energy Storage Project from Cluster 12, proposes to interconnect a 99 megawatt (MW) (net output) Battery generation facility to Ripon 115kV in San Joaquin County, California. The project has a contractual In-service date of: 1/29/26 with a current planned In-service date of: 3/31/26 | Construction (50%-75%) | 2025-01-10 |  |  | Ripon, San Joaquin | PG&E: Greater Bay Area | Yes | N/A | T.0007979 ¦ T.0007979 ¦ T.0007979 ¦ T.0004515 | New | Generator Interconnection | Generation Interconnection | N/A | 2.0603 | N/A | 115 kV | 2024-01-15 | 2026-01-29 | 2026-03-31 | Transmission Project Review Process data (Resolution E-5252 Attach B | 61 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 06/02/25 - MMA was submitted. Customer has not started construction yet. It is expected the IC cannot finish Gensite construction and interconnection until Q1 2026. | - | 1557 | 1557
Q1557 NOOSA ENERGY STORAGE GEN SITE DA | 5797835 | T.0007445 | 82Y | The Q1557 Noosa Energy Storage Project from Cluster 12, proposes to interconnect a 99 megawatt (MW) (net output) Battery generation facility to Ripon 115kV in San Joaquin County, California. The project has a contractual In-service date of: 1/29/26 with a current planned In-service date of: 3/31/26 | Engineering more than 50% complete | 2025-01-10 |  |  | Ripon, San Joaquin | PG&E: Greater Bay Area | Yes | N/A | T.0007979 ¦ T.0007979 ¦ T.0007979 ¦ T.0004515 | Upgrade/Retrofit | Generator Interconnection | Generation Interconnection | N/A | 2.0603 | N/A | 115 kV | 2025-06-24 | 2026-01-29 | 2026-03-31 | Transmission Project Review Process data (Resolution E-5252 Attach B | 61 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 06/02/25 - MMA was submitted. Customer has not started construction yet. It is expected the IC cannot finish Gensite construction and interconnection until Q1 2026. | - | 1557 | 1557
Q1539 IRVING STORAGE-MLNG SUB RNU | 5797901 | T.0007467 | 82W | The Q1539 Irving Storage Project from Cluster ISP, proposes to interconnect a 750 megawatt (MW) (net output) Battery generation facility to Moss Landing 500kV in Monterey County, California. The project has a contractual In-service date of: 8/30/25 with a current planned In-service date of: 11/19/27 | Engineering more than 50% complete | 2025-08-30 |  |  | Monterey | PG&E: North Valley Area | Yes | N/A | T.0007290 ¦ T.0007291 ¦ T.0007288 | New | Generator Interconnection | Generation Interconnection | N/A | 41.3213 | N/A | 500 kV | 2026-03-31 | 2025-08-30 | 2027-11-19 | Transmission Project Review Process data (Resolution E-5252 Attach B | 811 | Yes |  |  | N/A |  | TBD | N/A | TBD | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - Tracking ISD to late 2027. MMA required to adjust to earliest ISD | - | 1539 | 1539
Q1539 IRVING STORAGE-MOSS LANDING SUB DA | 5797903 | T.0007467 | 82Y | The Q1539 Irving Storage Project from Cluster ISP, proposes to interconnect a 750 megawatt (MW) (net output) Battery generation facility to Moss Landing 500kV in Monterey County, California. The project has a contractual In-service date of: 8/30/25 with a current planned In-service date of: 11/19/27 | Engineering more than 50% complete | 2025-08-30 |  |  | Monterey | 0 | Yes | N/A | T.0007290 ¦ T.0007291 ¦ T.0007288 | New | Generator Interconnection | Generation Interconnection | N/A | 41.3213 | N/A | 500 kV | 2026-03-31 | 2025-08-30 | 2027-11-19 | Transmission Project Review Process data (Resolution E-5252 Attach B | 811 | Yes |  |  | N/A |  | TBD | N/A | TBD | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - Tracking ISD to late 2027. MMA required to adjust to earliest ISD | - | 1539 | 1539
Q1539 IRVING STORAGE-GEN SITE DA | 5797904 | T.0007467 | 82Y | The Q1539 Irving Storage Project from Cluster ISP, proposes to interconnect a 750 megawatt (MW) (net output) Battery generation facility to Moss Landing 500kV in Monterey County, California. The project has a contractual In-service date of: 8/30/25 with a current planned In-service date of: 11/19/27 | Engineering more than 50% complete | 2025-08-30 |  |  | Monterey | 0 | Yes | N/A | T.0007290 ¦ T.0007291 ¦ T.0007288 | Upgrade/Retrofit | Generator Interconnection | Generation Interconnection | N/A | N/A | N/A | 500 kV | 2026-07-15 | 2025-08-30 | 2027-11-19 | Transmission Project Review Process data (Resolution E-5252 Attach B | 811 | Yes |  |  | N/A |  | TBD | N/A | TBD | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - Tracking ISD to late 2027. MMA required to adjust to earliest ISD | - | 1539 | 1539
Q946-N. ORCHARD- WR SUB RAS-NU | 5798542 | T.0001353 | 82W | The 20rsmt-6 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Midway-Wheeler Ridge #2-230kV Line in Kern County, California. | Operational | 2018-12-01 |  |  | Kern | 0 | Yes | N/A | T.0010617 | New | Generator Interconnection | Special Protection Scheme | N/A | N/A | N/A | 230 kV | 2024-04-08 | 2018-12-01 | 2024-04-23 | Transmission Project Review Process data (Resolution E-5252 Attach B | 1970 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | NOC: AL 6634-E | 2022-06-30 | Approved | 2022 |  | Utility - !Telecom! | Q1260 | Q1260
Q946-N. ORCHARD-MIDWAY SUB RAS-DA | 5798543 | T.0001353 | 82Y | The 20rsmt-6 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Midway-Wheeler Ridge #2-230kV Line in Kern County, California. | Engineering more than 50% complete | 2025-10-10 |  |  | Green Valley CDP, Napa ¦ Green Valley CDP, Solano ¦ Hartley CDP, Solano ¦ Napa ¦ Solano ¦ Vacaville, Solano | 0 | Yes | N/A | T.0010617 | New | Generator Interconnection | Special Protection Scheme | 2 | NA | 60 | N/A | 2026-01-13 | 2025-10-10 | 2026-05-07 | Transmission Project Review Process data (Resolution E-5252 Attach B | 209 | Yes |  |  | CEQA Final Published | 45397 | IS/MND | N/A | County of Napa | N/A | NOC: AL 7472-E | 2025-01-02 | Approved | 2025 |  | Utility - !Telecom! | Q1260 | Q1260
Q1565 - DYNAMO SOLAR T-LINE RNU | 5798546 | T.0007591 | 82B | The Q1565 Dynamo Solar Project from Cluster 12, proposes to interconnect a 24.5 megawatt (MW) (net output) Solar generation facility to Tulucay 60kV in Napa County, California. The project has a contractual In-service date of: 10/10/25 with a current planned In-service date of: 10/10/25 | Engineering more than 50% complete | 2025-10-10 |  |  | Green Valley CDP, Napa ¦ Green Valley CDP, Solano ¦ Hartley CDP, Solano ¦ Napa ¦ Solano ¦ Vacaville, Solano | PG&E: North Valley Area | Yes | N/A |  | New | Generator Interconnection | T-Line Capacity | 2 | NA | 60 | N/A | 2026-01-13 | 2025-10-10 | 2025-10-10 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | CEQA Final Published | 45397 | IS/MND | N/A | County of Napa | N/A | NOC: AL 7472-E | 2025-01-02 | Approved | 2025 | 05/06/25 - Tracking ISD to Q3 2026 due to IC CEQA process related delays. | Customer - Permitting (Customer) | 1565 | 1565
Q1565 - DYNAMO SOLAR T-LINE DA | 5798547 | T.0007591 | 82D | The Q1565 Dynamo Solar Project from Cluster 12, proposes to interconnect a 24.5 megawatt (MW) (net output) Solar generation facility to Tulucay 60kV in Napa County, California. The project has a contractual In-service date of: 10/10/25 with a current planned In-service date of: 10/10/25 | Engineering more than 50% complete | 2025-10-10 |  |  | Green Valley CDP, Napa ¦ Green Valley CDP, Solano ¦ Hartley CDP, Solano ¦ Napa ¦ Solano ¦ Vacaville, Solano | 0 | Yes | N/A |  | New | Generator Interconnection | Generation Interconnection | 2 | NA | 60 | N/A | 2026-03-23 | 2025-10-10 | 2026-03-31 | Transmission Project Review Process data (Resolution E-5252 Attach B | 172 | Yes |  |  | CEQA Final Published | 45390 | IS/MND | N/A | County of Napa | N/A | NOC: AL 7472-E | 2025-01-02 | Approved | 2025 | 05/06/25 - Tracking ISD to Q3 2026 due to IC CEQA process related delays. | Customer - Permitting (Customer) | 1565 | 1565
Q1565 - DYNAMO SOLAR TULUCAY SUB RNU | 5798548 | T.0007591 | 82W | The Q1565 Dynamo Solar Project from Cluster 12, proposes to interconnect a 24.5 megawatt (MW) (net output) Solar generation facility to Tulucay 60kV in Napa County, California. The project has a contractual In-service date of: 10/10/25 with a current planned In-service date of: 10/10/25 | Engineering more than 50% complete | 2025-10-10 |  |  | Napa | PG&E: Greater Fresno Area | Yes | N/A |  | New | Generator Interconnection | Generation Interconnection | N/A | 4.1869 | N/A | 60 kV | 2026-01-13 | 2025-10-10 | 2026-03-31 | Transmission Project Review Process data (Resolution E-5252 Attach B | 172 | Yes |  |  | CEQA Final Published | 45390 | IS/MND | N/A | County of Napa | N/A | NOC: AL 7472-E | 2025-01-02 | Approved | 2025 | 05/06/25 - Tracking ISD to Q3 2026 due to IC CEQA process related delays. | Customer - Permitting (Customer) | 1565 | 1565
Q1565 - DYNAMO SOLAR VACA-DIXON SUB RNU | 5798549 | T.0007591 | 82W | The Q1565 Dynamo Solar Project from Cluster 12, proposes to interconnect a 24.5 megawatt (MW) (net output) Solar generation facility to Tulucay 60kV in Napa County, California. The project has a contractual In-service date of: 10/10/25 with a current planned In-service date of: 10/10/25 | Engineering more than 50% complete | 2025-10-10 |  |  | Solano | PG&E: Greater Fresno Area | Yes | N/A |  | Upgrade/Retrofit | Generator Interconnection | Special Protection Scheme | N/A | 42.1076 | N/A | 60 kV | 2026-01-13 | 2025-10-10 | 2026-03-31 | Transmission Project Review Process data (Resolution E-5252 Attach B | 172 | Yes |  |  | CEQA Final Published | 45390 | IS/MND | N/A | County of Napa | N/A | NOC: AL 7472-E | 2025-01-02 | Approved | 2025 | 05/06/25 - Tracking ISD to Q3 2026 due to IC CEQA process related delays. | Customer - Permitting (Customer) | 1565 | 1565
Q1565 - DYNAMO SOLAR LAKEVILLE SUB RNU | 5798550 | T.0007591 | 82W | The Q1565 Dynamo Solar Project from Cluster 12, proposes to interconnect a 24.5 megawatt (MW) (net output) Solar generation facility to Tulucay 60kV in Napa County, California. The project has a contractual In-service date of: 10/10/25 with a current planned In-service date of: 10/10/25 | Engineering more than 50% complete | 2025-10-10 |  |  | Sonoma | PG&E: Greater Fresno Area | Yes | N/A |  | Upgrade/Retrofit | Generator Interconnection | Special Protection Scheme | N/A | 14.7021 | N/A | 60 kV | 2026-01-13 | 2025-10-10 | 2026-03-31 | Transmission Project Review Process data (Resolution E-5252 Attach B | 172 | Yes |  |  | CEQA Final Published | 45390 | IS/MND | N/A | County of Napa | N/A | NOC: AL 7472-E | 2025-01-02 | Approved | 2025 | 05/06/25 - Tracking ISD to Q3 2026 due to IC CEQA process related delays. | Customer - Permitting (Customer) | 1565 | 1565
Q1565 - DYNAMO SOLAR TULUCAY SUB DA | 5798551 | T.0007591 | 82Y | The Q1565 Dynamo Solar Project from Cluster 12, proposes to interconnect a 24.5 megawatt (MW) (net output) Solar generation facility to Tulucay 60kV in Napa County, California. The project has a contractual In-service date of: 10/10/25 with a current planned In-service date of: 10/10/25 | Engineering more than 50% complete | 2025-10-10 |  |  | Napa | N/A | Yes | N/A |  | New | Generator Interconnection | Generation Interconnection | N/A | 4.1869 | N/A | 60 kV | 2026-01-09 | 2025-10-10 | 2026-03-31 | Transmission Project Review Process data (Resolution E-5252 Attach B | 172 | Yes |  |  | CEQA Final Published | 45390 | IS/MND | N/A | County of Napa | N/A | NOC: AL 7472-E | 2025-01-02 | Approved | 2025 | 05/06/25 - Tracking ISD to Q3 2026 due to IC CEQA process related delays. | Customer - Permitting (Customer) | 1565 | 1565
Q1565 - DYNAMO SOLAR GEN SITE DA | 5798552 | T.0007591 | 82Y | The Q1565 Dynamo Solar Project from Cluster 12, proposes to interconnect a 24.5 megawatt (MW) (net output) Solar generation facility to Tulucay 60kV in Napa County, California. The project has a contractual In-service date of: 10/10/25 with a current planned In-service date of: 10/10/25 | Engineering more than 50% complete | 2025-10-10 |  |  | Napa | 0 | Yes | N/A |  | Upgrade/Retrofit | Generator Interconnection | Generation Interconnection | N/A | 4.1869 | N/A | 60 kV | 2026-01-13 | 2025-10-10 | 2026-03-31 | Transmission Project Review Process data (Resolution E-5252 Attach B | 172 | Yes |  |  | CEQA Final Published | 45390 | IS/MND | N/A | County of Napa | N/A | NOC: AL 7472-E | 2025-01-02 | Approved | 2025 | 05/06/25 - Tracking ISD to Q3 2026 due to IC CEQA process related delays. | Customer - Permitting (Customer) | 1565 | 1565
Q946-N. ORCHARD-MIDWAY SUB RAS-NU | 5798626 | T.0001353 | 82W | The 20rsmt-6 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Midway-Wheeler Ridge #2-230kV Line in Kern County, California. | Engineering more than 50% complete | 2018-12-01 |  |  | Buttonwillow CDP, Kern | 0 | Yes | N/A | T.0010617 | New | Generator Interconnection | Special Protection Scheme | N/A | N/A | N/A | 230 kV | 2027-04-05 | 2018-12-01 | 2027-07-13 | Transmission Project Review Process data (Resolution E-5252 Attach B | 3146 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | NOC: AL 6634-E | 2022-06-30 | Approved | 2022 |  | Utility - !Telecom! | Q1260 | Q1260
Round Mountain 500 kV Dynamic Voltage Support | 5798638 | T.0006815 | 3FA | The C14P2-NPT02 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Round Mountain 500 kV in Shasta County, California. | Planning | 2024-04-30 |  |  | Round Mountain CDP, Shasta | PG&E: North Valley Area | No | 2019 | 0 ¦ 0 ¦ 0 | New | Reliability | T-Line Capacity | N/A | 29.1389 | N/A | 500 kV | 2025-11-04 | 2024-04-30 | 2025-11-15 | Transmission Project Review Process data (Resolution E-5252 Attach B | 564 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom! | Q1844, Q1858, Q1863 | Q1844 | Q1858 | Q1863
Round Mountain 500 kV Dynamic Voltage Support | 5798639 | T.0006815 | 3FA | The C14P2-NPT02 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Round Mountain 500 kV in Shasta County, California. | Construction (25%-50%) | 2024-04-30 |  |  | Round Mountain CDP, Shasta | PG&E: North Valley Area | No | 2019 | 0 ¦ 0 ¦ 0 | New | Reliability | T-Line Capacity | N/A | 29.1389 | N/A | 500 kV | 2024-12-12 | 2024-04-30 | 2025-11-15 | Transmission Project Review Process data (Resolution E-5252 Attach B | 564 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom! | Q1844, Q1858, Q1863 | Q1844 | Q1858 | Q1863
Q1143 - Lake Alpaugh BESS - Midway DTT | 5798800 | T.0003744 | 82W | The Q1143 Lake Alpaugh BESS & Alpaugh 3 BESS Project from Cluster 8, proposes to interconnect a 10 megawatt (MW) (net output) Battery generation facility to Corcoran-Olive SW 115kV Line in Tulare County, California. The project has a contractual In-service date of: 7/15/25 with a current planned In-service date of: 10/31/25 | Construction (over 75%) | 2019-11-01 |  |  | Buttonwillow CDP, Kern | 0 | Yes | N/A | T.0003009 ¦ T.0003789 | New | Generator Interconnection | Special Protection Scheme | N/A | 94.5324 | N/A | 115 kV | 2022-09-01 | 2025-07-15 | 2025-10-31 | Transmission Project Review Process data (Resolution E-5252 Attach B | 108 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - Tracking ISD delays. MMA approval required for redesign of ICs point of interconnection | Customer - Project / Design Changes | 1143 | 1143
Q1143 - Lake Alpaugh BESS - Smyrna | 5798801 | T.0003744 | 82W | The Q1143 Lake Alpaugh BESS & Alpaugh 3 BESS Project from Cluster 8, proposes to interconnect a 10 megawatt (MW) (net output) Battery generation facility to Corcoran-Olive SW 115kV Line in Tulare County, California. The project has a contractual In-service date of: 7/15/25 with a current planned In-service date of: 10/31/25 | Construction (over 75%) | 2019-11-01 |  |  | Kern | 0 | Yes | N/A | T.0003009 ¦ T.0003789 | New | Generator Interconnection | Generation Interconnection | N/A | 1.3608 | N/A | 115 kV | 2022-09-01 | 2025-07-15 | 2025-10-31 | Transmission Project Review Process data (Resolution E-5252 Attach B | 108 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - Tracking ISD delays. MMA approval required for redesign of ICs point of interconnection | Customer - Project / Design Changes | 1143 | 1143
FULTON-HOPLAND RECON (GEYSERS-FITCH MTN) | 5798804 | T.0007629 | 82B | The C9P2-N02 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Fulton-Hopland 60kV Line in Sonoma County, California. | Engineering more than 50% complete | 2027-03-31 |  |  | Fulton CDP, Sonoma ¦ Healdsburg, Sonoma ¦ Larkfield-Wikiup CDP, Sonoma ¦ Mendocino ¦ Sonoma ¦ Windsor, Sonoma | N/A | Yes | N/A | T.0008218 ¦ T.0006968 | Upgrade/Retrofit | Generator Interconnection | T-Line Capacity | 7 | NA | 60 | N/A | 2027-02-04 | 2027-03-31 | 2027-03-31 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | NOC: AL 7532-E | 2025-03-11 | Approved | 2025 |  | Utility - !Telecom! | Q1444, Q1455 | Q1444 | Q1455
Metcalf 115kV: (New XFMR Reactors): BK1-4 | 5798882 | T.0007291 | 64C | The 20rsmt-4 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Metcalf 115kV in Santa Clara County, California. | Operational | 2028-01-28 |  |  | Santa Clara | PG&E: North Valley Area | No | N/A | T.0008230 ¦ T.0007467 ¦ 0 ¦ T.0010944 ¦ 0 | Replace | Generator Interconnection | T-Line Capacity | N/A | 37.8815 | N/A | 230 kV | 2022-10-13 | 2028-01-28 | 2022-11-01 | Transmission Project Review Process data (Resolution E-5252 Attach B | -1914 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom! | Q1442, Q1539, Q1553, Q1866, Q1889 | Q1442 | Q1539 | Q1553 | Q1866 | Q1889
FULTON-HOPLAND RECON (HOPLAND-GEYSERS) | 5798940 | T.0007629 | 82B | The C9P2-N02 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Fulton-Hopland 60kV Line in Sonoma County, California. | Engineering more than 50% complete | 2027-03-31 |  |  | Fulton CDP, Sonoma ¦ Healdsburg, Sonoma ¦ Larkfield-Wikiup CDP, Sonoma ¦ Mendocino ¦ Sonoma ¦ Windsor, Sonoma | N/A | Yes | N/A | T.0008218 ¦ T.0006968 | Upgrade/Retrofit | Generator Interconnection | Generation Interconnection | 24.21 | N/A | 60 | N/A | 2025-11-01 | 2027-03-31 | 2027-02-02 | Transmission Project Review Process data (Resolution E-5252 Attach B | -57 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | NOC: AL 7532-E | 2025-03-11 | Approved | 2025 |  | Utility - !Telecom!
Q1479 KEY STRGE 1 GATES IF (DA) | 5799145 | T.0007722 | 82Y | The Q1479 Key Storage 1 Project from Cluster 11, proposes to interconnect a 300.1 megawatt (MW) (net output) Battery generation facility to Gates 500kV in Fresno County, California. The project has a contractual In-service date of: 6/1/26 with a current planned In-service date of: 6/1/26 | Construction (under 10%) | 2025-08-01 |  |  | Fresno | PG&E Kern Area | Yes | N/A | Maintenance ¦ Maintenance ¦ T.0007289 ¦ Maintenance | New | Generator Interconnection | Generation Interconnection | N/A | 77.6619 | N/A | 500 kV | 2025-02-03 | 2026-06-01 | 2026-06-01 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - Customer wants to relocate Metering from existing drawings. RFI needed to relocate meters. Tracking ISD in Jun 2026 | - | 1479 | 1479
Q1479 KEY STRGE 1 GENSITE (DA) | 5799146 | T.0007722 | 82Y | The Q1479 Key Storage 1 Project from Cluster 11, proposes to interconnect a 300.1 megawatt (MW) (net output) Battery generation facility to Gates 500kV in Fresno County, California. The project has a contractual In-service date of: 6/1/26 with a current planned In-service date of: 6/1/26 | Engineering more than 50% complete | 2025-08-01 |  |  | Fresno | PG&E Kern Area | Yes | N/A | Maintenance ¦ Maintenance ¦ T.0007289 ¦ Maintenance | Upgrade/Retrofit | Generator Interconnection | Generation Interconnection | N/A | 77.6619 | N/A | 500 kV | 2025-07-30 | 2026-06-01 | 2026-06-01 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - Customer wants to relocate Metering from existing drawings. RFI needed to relocate meters. Tracking ISD in Jun 2026 | - | 1479 | 1479
Q1479 KEY STRGE 1 GENTIE (DA) | 5799147 | T.0007722 | 82D | The Q1479 Key Storage 1 Project from Cluster 11, proposes to interconnect a 300.1 megawatt (MW) (net output) Battery generation facility to Gates 500kV in Fresno County, California. The project has a contractual In-service date of: 6/1/26 with a current planned In-service date of: 6/1/26 | Engineering more than 50% complete | 2025-08-01 |  |  | Fresno | PG&E: PG&E: North Valley Area Coast & PG&E: North Valley Area Bay Area | Yes | N/A | Maintenance ¦ Maintenance ¦ T.0007289 ¦ Maintenance | New | Generator Interconnection | Generation Interconnection | 0.25 | NA | 500 | N/A | 2025-12-15 | 2026-06-01 | 2026-06-01 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - Customer wants to relocate Metering from existing drawings. RFI needed to relocate meters. Tracking ISD in Jun 2026 | - | 1479 | 1479
Q1479 KEY STRGE 1 GATES (NU) | 5799148 | T.0007722 | 82W | The Q1479 Key Storage 1 Project from Cluster 11, proposes to interconnect a 300.1 megawatt (MW) (net output) Battery generation facility to Gates 500kV in Fresno County, California. The project has a contractual In-service date of: 6/1/26 with a current planned In-service date of: 6/1/26 | Construction (under 10%) | 2025-08-01 |  |  | Fresno | PG&E Kern Area | Yes | N/A | Maintenance ¦ Maintenance ¦ T.0007289 ¦ Maintenance | New | Generator Interconnection | Generation Interconnection | N/A | 77.6619 | N/A | 500 kV | 2025-03-18 | 2026-06-01 | 2026-06-01 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - Customer wants to relocate Metering from existing drawings. RFI needed to relocate meters. Tracking ISD in Jun 2026 | - | 1479 | 1479
Q1479 KEY STRGE 1 MDWY SUB OVSTRS RNU | 5799149 | T.0007722 | 82W | The Q1479 Key Storage 1 Project from Cluster 11, proposes to interconnect a 300.1 megawatt (MW) (net output) Battery generation facility to Gates 500kV in Fresno County, California. The project has a contractual In-service date of: 6/1/26 with a current planned In-service date of: 6/1/26 | Operational | 2025-08-01 |  |  | Buttonwillow CDP, Kern | PG&E Kern Area | Yes | N/A | Maintenance ¦ Maintenance ¦ T.0007289 ¦ Maintenance | Upgrade/Retrofit | Generator Interconnection | Substation Capacity | N/A | 77.6619 | N/A | 500 kV | 2024-10-07 | 2026-06-01 | 2026-06-01 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - Customer wants to relocate Metering from existing drawings. RFI needed to relocate meters. Tracking ISD in Jun 2026 | - | 1479 | 1479
Q1596 BUTTONBUSH SLR MDWY SUB DA | 5799282 | T.0007731 | 82Y | The Q1596 Buttonbush Solar Hybrid Energy Center Project from Cluster 12, proposes to interconnect a 800 megawatt (MW) (net output) Solar + Battery generation facility to Midway 500kV in Kern County, California. The project has a contractual In-service date of: 11/5/26 with a current planned In-service date of: 11/5/26 | Construction (10%-25%) | 2025-05-01 |  |  | Buttonwillow CDP, Kern | N/A | Yes | N/A | Maintenance ¦ Maintenance ¦ Maintenance ¦ T.0007289 | New | Generator Interconnection | Generation Interconnection | N/A | 94.5324 | N/A | 230 kV | 2024-11-08 | 2026-11-05 | 2026-11-05 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/05/25 - MMA submitted to change ISD and Technology. With ISO for engineering review and approval. Tracking ISD in Nov 2026 | - | 1596 | 1596
Q1596 BUTTONBUSH SLR GEN SITE DA | 5799283 | T.0007731 | 82Y | The Q1596 Buttonbush Solar Hybrid Energy Center Project from Cluster 12, proposes to interconnect a 800 megawatt (MW) (net output) Solar + Battery generation facility to Midway 500kV in Kern County, California. The project has a contractual In-service date of: 11/5/26 with a current planned In-service date of: 11/5/26 | Engineering more than 50% complete | 2025-05-01 |  |  | Buttonwillow CDP, Kern | N/A | Yes | N/A | Maintenance ¦ Maintenance ¦ Maintenance ¦ T.0007289 | Upgrade/Retrofit | Generator Interconnection | Generation Interconnection | N/A | 94.5324 | N/A | 230 kV | 2026-08-21 | 2026-11-05 | 2026-11-05 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/05/25 - MMA submitted to change ISD and Technology. With ISO for engineering review and approval. Tracking ISD in Nov 2026 | - | 1596 | 1596
Q1596 BUTTONBUSH SLR TLINE DA | 5799284 | T.0007731 | 82D | The Q1596 Buttonbush Solar Hybrid Energy Center Project from Cluster 12, proposes to interconnect a 800 megawatt (MW) (net output) Solar + Battery generation facility to Midway 500kV in Kern County, California. The project has a contractual In-service date of: 11/5/26 with a current planned In-service date of: 11/5/26 | Engineering more than 50% complete | 2025-05-01 |  |  | Buttonwillow CDP, Kern ¦ Kern ¦ Taft, Kern | N/A | Yes | N/A | Maintenance ¦ Maintenance ¦ Maintenance ¦ T.0007289 | New | Generator Interconnection | Generation Interconnection | 4 | N/A | 230 | N/A | 2026-07-03 | 2026-11-05 | 2026-11-05 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/05/25 - MMA submitted to change ISD and Technology. With ISO for engineering review and approval. Tracking ISD in Nov 2026 | - | 1596 | 1596
Q1596 BUTTONBUSH SLR MDWY SUB RNU | 5799285 | T.0007731 | 82W | The Q1596 Buttonbush Solar Hybrid Energy Center Project from Cluster 12, proposes to interconnect a 800 megawatt (MW) (net output) Solar + Battery generation facility to Midway 500kV in Kern County, California. The project has a contractual In-service date of: 11/5/26 with a current planned In-service date of: 11/5/26 | Engineering more than 50% complete | 2025-05-01 |  |  | Buttonwillow CDP, Kern | N/A | Yes | N/A | Maintenance ¦ Maintenance ¦ Maintenance ¦ T.0007289 | New | Generator Interconnection | Generation Interconnection | N/A | 94.5324 | N/A | 230 kV | 2025-06-03 | 2026-11-05 | 2026-11-05 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/05/25 - MMA submitted to change ISD and Technology. With ISO for engineering review and approval. Tracking ISD in Nov 2026 | - | 1596 | 1596
GATES: 230KV REACTORS BUS E-F (RNU 1596– | 5799287 | T.0008543 | 82W | The C12P2-GRNU2 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Gates 230kV in Fresno County, California. | Construction (10%-25%) | 2025-05-01 |  |  | Fresno | N/A | Yes | N/A | 0 ¦ T.0010479 ¦ T.0008735 ¦ 0 ¦ T.0011125 ¦ T.0010878 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ T.0009383 | New | Generator Interconnection | Substation Capacity | N/A | 77.6619 | N/A | 230 kV | 2024-11-06 | 2025-05-01 | 2026-04-10 | Transmission Project Review Process data (Resolution E-5252 Attach B | 344 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom!
Q1463 - N. DUBLIN-CAYETANO 230 KV LN | 5799480 | T.0007846 | 82B | The C11P2-ND03 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the North Dublin-Cayetano 230kV Line in Solano County, California. | Engineering more than 50% complete | 2025-03-31 |  |  | Alameda ¦ Contra Costa | N/A | Yes | N/A | T.0007418 ¦ T.0010478 ¦ T.0010648 ¦ 0 ¦ 0 ¦ 0 ¦ 0 | Relocate | Generator Interconnection | T-Line Capacity | 5.4 | NA | 230 | N/A | 2025-10-07 | 2025-03-31 | 2026-05-01 | Transmission Project Review Process data (Resolution E-5252 Attach B | 396 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom! | 2497-WD, Q1463, Q1691, Q1683, Q1842, Q1843, Q1892, Q1915 | 2497-WD | Q1463 | Q1691 | Q1683 | Q1842 | Q1843 | Q1892 | Q1915
W FORD FLAT ESTORAGE - WFFPP-DA | 5799519 | T.0007849 | 82Y | The Q1367 West Ford Flat Energy Storage Project from Cluster 10, proposes to interconnect a 25 megawatt (MW) (net output) Battery generation facility to Fulton 230kV in Lake County, California. The project has a contractual In-service date of: 2/15/24 with a current planned In-service date of: 4/19/24 | Engineering more than 50% complete | N/A |  |  | Interlaken CDP, Santa Cruz | 0 | No | N/A |  | Upgrade/Retrofit | Reliability | Transformer Addition/Replacement | N/A | 6.6121 | N/A | 115 kV | 2024-03-01 | 2024-02-15 | 2024-04-19 | Transmission Project Review Process data (Resolution E-5252 Attach B | 64 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | In-Service - 4/18/24 - Commencing Commercial Testing 4/15/24 - Short on 2 points on EMS/SCADA. Next chance to prove comms on 4/19. Pending on other test results. 3/27/24 - Temporary Comms solution required to backfeed until Telco solution is in place 3/25/24 - PPI is completed as of 2/23/24. ISD to be 3/27/24 2/5/24 - MRS (Managed Router Service) needed. will require Telco configuration. Dates ?. Assume a month delay. 1/4/24 - ASEoD meeting held. This project PA is exceeded and needs reauthorized. PM to go to AM Supv to confirm AM to assist in PA. 1/3/24 to coordinate and schedule Q1097. They need to order the MRS service (end points orders) 12/4/23 - FDP is proceeding. 11/1/23 - ISD in 2024 tracking 10/2/24 - ISD of 2/13/24 is achievable. MMA # 2 active for 8/21/23 - ISD of 2/13/24 remains achievable. IC schedule appears to be tracking. | Customer - !Telecom! | 1367 | 1367
W FORD FLAT - ESTORAGE GEN SITE-DA | 5799520 | T.0007849 | 82Y | The Q1367 West Ford Flat Energy Storage Project from Cluster 10, proposes to interconnect a 25 megawatt (MW) (net output) Battery generation facility to Fulton 230kV in Lake County, California. The project has a contractual In-service date of: 2/15/24 with a current planned In-service date of: 4/19/24 | Engineering more than 50% complete | N/A |  |  | Interlaken CDP, Santa Cruz | 0 | No | N/A |  | Upgrade/Retrofit | Reliability | Transformer Addition/Replacement | N/A | 6.6121 | N/A | 115 kV | 2024-03-01 | 2024-02-15 | 2024-04-19 | Transmission Project Review Process data (Resolution E-5252 Attach B | 64 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | In-Service - 4/18/24 - Commencing Commercial Testing 4/15/24 - Short on 2 points on EMS/SCADA. Next chance to prove comms on 4/19. Pending on other test results. 3/27/24 - Temporary Comms solution required to backfeed until Telco solution is in place 3/25/24 - PPI is completed as of 2/23/24. ISD to be 3/27/24 2/5/24 - MRS (Managed Router Service) needed. will require Telco configuration. Dates ?. Assume a month delay. 1/4/24 - ASEoD meeting held. This project PA is exceeded and needs reauthorized. PM to go to AM Supv to confirm AM to assist in PA. 1/3/24 to coordinate and schedule Q1097. They need to order the MRS service (end points orders) 12/4/23 - FDP is proceeding. 11/1/23 - ISD in 2024 tracking 10/2/24 - ISD of 2/13/24 is achievable. MMA # 2 active for 8/21/23 - ISD of 2/13/24 remains achievable. IC schedule appears to be tracking. | Customer - !Telecom! | 1367 | 1367
W FORD FLAT - ESTORAGE FLTN SUB-RNU | 5799521 | T.0007849 | 82W | The Q1367 West Ford Flat Energy Storage Project from Cluster 10, proposes to interconnect a 25 megawatt (MW) (net output) Battery generation facility to Fulton 230kV in Lake County, California. The project has a contractual In-service date of: 2/15/24 with a current planned In-service date of: 4/19/24 | Engineering more than 50% complete | N/A |  |  | Interlaken CDP, Santa Cruz | PG&E: North Valley Area | No | N/A |  | Upgrade/Retrofit | Reliability | Transformer Addition/Replacement | N/A | 6.6121 | N/A | 115 kV | 2024-03-01 | 2024-02-15 | 2024-04-19 | Transmission Project Review Process data (Resolution E-5252 Attach B | 64 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | In-Service - 4/18/24 - Commencing Commercial Testing 4/15/24 - Short on 2 points on EMS/SCADA. Next chance to prove comms on 4/19. Pending on other test results. 3/27/24 - Temporary Comms solution required to backfeed until Telco solution is in place 3/25/24 - PPI is completed as of 2/23/24. ISD to be 3/27/24 2/5/24 - MRS (Managed Router Service) needed. will require Telco configuration. Dates ?. Assume a month delay. 1/4/24 - ASEoD meeting held. This project PA is exceeded and needs reauthorized. PM to go to AM Supv to confirm AM to assist in PA. 1/3/24 to coordinate and schedule Q1097. They need to order the MRS service (end points orders) 12/4/23 - FDP is proceeding. 11/1/23 - ISD in 2024 tracking 10/2/24 - ISD of 2/13/24 is achievable. MMA # 2 active for 8/21/23 - ISD of 2/13/24 remains achievable. IC schedule appears to be tracking. | Customer - !Telecom! | 1367 | 1367
Q1389 REDUX GATES SUB (DA) | 5799691 | T.0007971 | 82Y | The Q1389 Redux Solar Project from Cluster 10, proposes to interconnect a 125 megawatt (MW) (net output) Solar + Battery generation facility to Gates 230kV in Fresno County, California. The project has a contractual In-service date of: 12/2/24 with a current planned In-service date of: 8/21/26 | Engineering more than 50% complete | 2024-12-02 |  |  | Fresno | N/A | Yes | N/A | Maintenance ¦ T.0007289 ¦ T.0006452 | New | Generator Interconnection | Generation Interconnection | N/A | 77.6619 | N/A | 230 kV | 2025-08-04 | 2024-12-02 | 2026-08-21 | Transmission Project Review Process data (Resolution E-5252 Attach B | 627 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/05/25 - MMA submitted for ISD and technology changes. Tracking ISD to Q2 2026. Customer moved POCO pole location multiple times. Customer started gentie route design. Customer submitted IDP and accepted. Customer's POCO location changes delayed PG&E's T-line design which includes 5 spans, 2 H frames, 2 TSPs. | - | 1389 | 1389
Q1389 REDUX GEN SITE (DA) | 5799692 | T.0007971 | 82Y | The Q1389 Redux Solar Project from Cluster 10, proposes to interconnect a 125 megawatt (MW) (net output) Solar + Battery generation facility to Gates 230kV in Fresno County, California. The project has a contractual In-service date of: 12/2/24 with a current planned In-service date of: 8/21/26 | Engineering less than 50% complete | 2024-12-02 |  |  | Fresno | N/A | Yes | N/A | Maintenance ¦ T.0007289 ¦ T.0006452 | New | Generator Interconnection | Generation Interconnection | N/A | N/A | N/A | 230 kV | 2025-12-26 | 2024-12-02 | 2026-08-21 | Transmission Project Review Process data (Resolution E-5252 Attach B | 627 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/05/25 - MMA submitted for ISD and technology changes. Tracking ISD to Q2 2026. Customer moved POCO pole location multiple times. Customer started gentie route design. Customer submitted IDP and accepted. Customer's POCO location changes delayed PG&E's T-line design which includes 5 spans, 2 H frames, 2 TSPs. | - | 1389 | 1389
Q1389 REDUX T LINE (DA) | 5799693 | T.0007971 | 82D | The Q1389 Redux Solar Project from Cluster 10, proposes to interconnect a 125 megawatt (MW) (net output) Solar + Battery generation facility to Gates 230kV in Fresno County, California. The project has a contractual In-service date of: 12/2/24 with a current planned In-service date of: 8/21/26 | Engineering more than 50% complete | 2024-12-02 |  |  | Fresno ¦ Kings | N/A | Yes | N/A | Maintenance ¦ T.0007289 ¦ T.0006452 | New | Generator Interconnection | Generation Interconnection | 3.2 | NA | 230 | N/A | 2026-01-02 | 2024-12-02 | 2026-08-21 | Transmission Project Review Process data (Resolution E-5252 Attach B | 627 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/05/25 - MMA submitted for ISD and technology changes. Tracking ISD to Q2 2026. Customer moved POCO pole location multiple times. Customer started gentie route design. Customer submitted IDP and accepted. Customer's POCO location changes delayed PG&E's T-line design which includes 5 spans, 2 H frames, 2 TSPs. | -
Q1550 TANAGER STRGE LOS ESTEROS SUB DA | 5799783 | T.0007981 | 82Y | The Q1550 Tanager Energy Storage Project from Cluster 12, proposes to interconnect a 200 megawatt (MW) (net output) Battery generation facility to Los Esteros 230kV in Santa Clara County, California. The project has a contractual In-service date of: 1/1/25 with a current planned In-service date of: 8/31/27 | Engineering more than 50% complete | 2025-01-01 |  |  | San Jose, Santa Clara | N/A | Yes | N/A | T.0007290 ¦ Maintenance | New | Generator Interconnection | Generation Interconnection | N/A | N/A | N/A | 230 kV | 2026-06-12 | 2025-01-01 | 2027-08-31 | Transmission Project Review Process data (Resolution E-5252 Attach B | 972 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - 1/1/2025 ISD, 4/1/2025 COD, Tracking to Q3 2027 attributed to IC has no site control | - | 1550 | 1550
Q1550 TANAGER STRGE 230 KV TLINE DA | 5799784 | T.0007981 | 82D | The Q1550 Tanager Energy Storage Project from Cluster 12, proposes to interconnect a 200 megawatt (MW) (net output) Battery generation facility to Los Esteros 230kV in Santa Clara County, California. The project has a contractual In-service date of: 1/1/25 with a current planned In-service date of: 8/31/27 | Engineering more than 50% complete | 2025-01-01 |  |  | San Jose, Santa Clara | PG&E: North Valley Area | Yes | N/A | T.0007290 ¦ Maintenance | New | Generator Interconnection | Generation Interconnection | 0.15 | NA | 230 | N/A | 2027-01-06 | 2025-01-01 | 2027-08-31 | Transmission Project Review Process data (Resolution E-5252 Attach B | 972 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - 1/1/2025 ISD, 4/1/2025 COD, Tracking to Q3 2027 attributed to IC has no site control | - | 1550 | 1550
Q1550 TANAGER STRGE RVWS PPI GEN SITE DA | 5799785 | T.0007981 | 82Y | The Q1550 Tanager Energy Storage Project from Cluster 12, proposes to interconnect a 200 megawatt (MW) (net output) Battery generation facility to Los Esteros 230kV in Santa Clara County, California. The project has a contractual In-service date of: 1/1/25 with a current planned In-service date of: 8/31/27 | Engineering more than 50% complete | 2025-01-01 |  |  | San Jose, Santa Clara | N/A | Yes | N/A | T.0007290 ¦ Maintenance | Upgrade/Retrofit | Generator Interconnection | Generation Interconnection | N/A | 13.1703 | N/A | 230 kV | 2027-02-05 | 2025-01-01 | 2027-08-31 | Transmission Project Review Process data (Resolution E-5252 Attach B | 972 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - 1/1/2025 ISD, 4/1/2025 COD, Tracking to Q3 2027 attributed to IC has no site control | - | 1550 | 1550
Q1550 TANAGER STRGE NW BAAH 2 CB RNU | 5799786 | T.0007981 | 82W | The Q1550 Tanager Energy Storage Project from Cluster 12, proposes to interconnect a 200 megawatt (MW) (net output) Battery generation facility to Los Esteros 230kV in Santa Clara County, California. The project has a contractual In-service date of: 1/1/25 with a current planned In-service date of: 8/31/27 | Engineering more than 50% complete | 2025-01-01 |  |  | San Jose, Santa Clara | N/A | Yes | N/A | T.0007290 ¦ Maintenance | New | Generator Interconnection | Generation Interconnection | N/A | 13.1703 | N/A | 230 kV | 2026-09-25 | 2025-01-01 | 2027-08-31 | Transmission Project Review Process data (Resolution E-5252 Attach B | 972 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - 1/1/2025 ISD, 4/1/2025 COD, Tracking to Q3 2027 attributed to IC has no site control | - | 1550 | 1550
Q1557 NOOSA RPN-MNTC 115 T-L DNU | 5799798 | T.0007979 | 82B | The C12P2-LDNU1 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Ripon-Manteca 115 kV Line in San Joaquin County, California. | Engineering more than 50% complete | 2025-01-10 |  |  | Grayson CDP, Stanislaus ¦ Manteca, San Joaquin ¦ San Joaquin ¦ Stanislaus | PG&E Kern Area | Yes | N/A | T.0007445 ¦ 0 | Upgrade/Retrofit | Generator Interconnection | T-Line Capacity | 0.9 | NA | 115 | N/A | 2027-03-08 | 2025-01-10 | 2028-04-25 | Transmission Project Review Process data (Resolution E-5252 Attach B | 1201 | Yes |  |  | N/A |  | TBD | TBD | TBD | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom! | Q1557, Q1904 | Q1557 | Q1904
Q1557 NOOSA STNSL-MLNS 115 T-L DNU | 5799799 | T.0007979 | 82B | The C12P2-LDNU1 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Ripon-Manteca 115 kV Line in San Joaquin County, California. | Engineering more than 50% complete | 2025-01-10 |  |  | Angels, Calaveras ¦ Calaveras ¦ Copperopolis CDP, Calaveras ¦ Manteca, San Joaquin ¦ Murphys CDP, Calaveras ¦ San Joaquin ¦ Stanislaus ¦ Tuolumne ¦ Vallecito CDP, Calaveras | N/A | Yes | N/A | T.0007445 ¦ 0 | Upgrade/Retrofit | Generator Interconnection | Generation Interconnection | 25.23 | NA | 115 | N/A | 2027-06-07 | 2025-01-10 | 2029-07-05 | Transmission Project Review Process data (Resolution E-5252 Attach B | 1637 | Yes |  |  | N/A |  | TBD | TBD | TBD | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom! | Q1557, Q1904 | Q1557 | Q1904
Q1557 NOOSA BLLT-RVRBK-MLNS 115 T-L DNU | 5799800 | T.0007979 | 82B | The C12P2-LDNU1 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Ripon-Manteca 115 kV Line in San Joaquin County, California. | Engineering more than 50% complete | 2025-01-10 |  |  | Calaveras ¦ San Joaquin ¦ Stanislaus ¦ Tuolumne | N/A | Yes | N/A | T.0007445 ¦ 0 | Upgrade/Retrofit | Generator Interconnection | Generation Interconnection | 17 | NA | 115 | N/A | 2027-08-16 | 2025-01-10 | 2028-02-08 | Transmission Project Review Process data (Resolution E-5252 Attach B | 1124 | Yes |  |  | N/A |  | TBD | TBD | TBD | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom! | Q1557, Q1904 | Q1557 | Q1904
Q1552 CORMORANT STRGE MARTIN SF H SUB DA | 5799978 | T.0008098 | 82Y | The Q1552 Cormorant Storage Project from Cluster 12, proposes to interconnect a 250 megawatt (MW) (net output) Battery generation facility to Martin 115kV in San Francisco County, California. The project has a contractual In-service date of: 12/15/24 with a current planned In-service date of: 3/2/27 | Engineering more than 50% complete | 2024-12-15 |  |  | Brisbane, San Mateo | N/A | Yes | N/A | T.0007290 ¦ T.0007287 ¦ Maintenance | New | Generator Interconnection | Generation Interconnection | N/A | N/A | N/A | 115 kV | 2026-01-21 | 2024-12-15 | 2027-03-02 | Transmission Project Review Process data (Resolution E-5252 Attach B | 807 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - Location problem for POCO, estimated solution for August to confirm location for POCO | - | 1552 | 1552
Q1552 CORMORANT STRGE GEN SITE DA | 5799979 | T.0008098 | 82Y | The Q1552 Cormorant Storage Project from Cluster 12, proposes to interconnect a 250 megawatt (MW) (net output) Battery generation facility to Martin 115kV in San Francisco County, California. The project has a contractual In-service date of: 12/15/24 with a current planned In-service date of: 3/2/27 | Engineering more than 50% complete | 2024-12-15 |  |  | Brisbane, San Mateo | N/A | Yes | N/A | T.0007290 ¦ T.0007287 ¦ Maintenance | Upgrade/Retrofit | Generator Interconnection | Generation Interconnection | N/A | 18.2105 | N/A | 115 kV | 2026-05-15 | 2024-12-15 | 2027-03-02 | Transmission Project Review Process data (Resolution E-5252 Attach B | 807 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - Location problem for POCO, estimated solution for August to confirm location for POCO | - | 1552 | 1552
Q1552 CORMORANT STRGE T LINE DA | 5799980 | T.0008098 | 82D | The Q1552 Cormorant Storage Project from Cluster 12, proposes to interconnect a 250 megawatt (MW) (net output) Battery generation facility to Martin 115kV in San Francisco County, California. The project has a contractual In-service date of: 12/15/24 with a current planned In-service date of: 3/2/27 | Engineering more than 50% complete | 2024-12-15 |  |  | Brisbane, San Mateo ¦ Burlingame, San Mateo ¦ Millbrae, San Mateo ¦ San Mateo ¦ San Mateo, San Mateo ¦ South San Francisco, San Mateo | N/A | Yes | N/A | T.0007290 ¦ T.0007287 ¦ Maintenance | New | Generator Interconnection | Generation Interconnection | 0.2 | NA | 115 | N/A | 2026-08-06 | 2024-12-15 | 2027-03-02 | Transmission Project Review Process data (Resolution E-5252 Attach B | 807 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - Location problem for POCO, estimated solution for August to confirm location for POCO | - | 1552 | 1552
Q1552 CORMORANT STRGE BAAH BAY, 1 CB RNU | 5799981 | T.0008098 | 82W | The Q1552 Cormorant Storage Project from Cluster 12, proposes to interconnect a 250 megawatt (MW) (net output) Battery generation facility to Martin 115kV in San Francisco County, California. The project has a contractual In-service date of: 12/15/24 with a current planned In-service date of: 3/2/27 | Engineering more than 50% complete | 2024-12-15 |  |  | Brisbane, San Mateo | N/A | Yes | N/A | T.0007290 ¦ T.0007287 ¦ Maintenance | New | Generator Interconnection | Generation Interconnection | N/A | 18.2105 | N/A | 115 kV | 2026-01-21 | 2024-12-15 | 2027-03-02 | Transmission Project Review Process data (Resolution E-5252 Attach B | 807 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - Location problem for POCO, estimated solution for August to confirm location for POCO | - | 1552 | 1552
Q1496 DESCENDANT RNCH 1 DELEVAN SUB DA | 5799983 | T.0008063 | 82Y | The Q1496 Descendant Ranch 1 Project from Cluster 11, proposes to interconnect a 500 megawatt (MW) (net output) Solar + Battery generation facility to Delevan 230kV in Colusa County, California. The project has a contractual In-service date of: 8/30/25 with a current planned In-service date of: 9/7/28 | Engineering more than 50% complete | 2025-03-21 |  |  | Colusa | N/A | Yes | N/A | T.0009188 ¦ T.0008063 ¦ T.0001609 | New | Generator Interconnection | Generation Interconnection | N/A | N/A | N/A | 230 kV | 2025-11-25 | 2025-08-30 |  | Transmission Project Review Process data (Resolution E-5252 Attach B | -45899 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - IC is suspending project. Notice from IC that they are behind an affected system (TANC) with estimated cost of of $50M and 5Yr Duration. Asks to cease all work on IF & IRNUs. At risk to withdraw. | Customer + Utility - GIP Upgrades | 1496 | 1496
Q1496 DESCENDANT RNCH 1 GEN SITE DA | 5799984 | T.0008063 | 82Y | The Q1496 Descendant Ranch 1 Project from Cluster 11, proposes to interconnect a 500 megawatt (MW) (net output) Solar + Battery generation facility to Delevan 230kV in Colusa County, California. The project has a contractual In-service date of: 8/30/25 with a current planned In-service date of: 9/7/28 | Planning | 2025-03-21 |  |  | Colusa | N/A | Yes | N/A | T.0009188 ¦ T.0008063 ¦ T.0001609 | Upgrade/Retrofit | Generator Interconnection | Generation Interconnection | N/A | 9.7615 | N/A | 230 kV | 2026-11-17 | 2025-08-30 | 2028-09-07 | Transmission Project Review Process data (Resolution E-5252 Attach B | 1104 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - IC is suspending project. Notice from IC that they are behind an affected system (TANC) with estimated cost of of $50M and 5Yr Duration. Asks to cease all work on IF & IRNUs. At risk to withdraw. | Customer + Utility - GIP Upgrades | 1496 | 1496
Q1496 DESCENDANT RNCH 1 T LINE DA | 5799985 | T.0008063 | 82D | The Q1496 Descendant Ranch 1 Project from Cluster 11, proposes to interconnect a 500 megawatt (MW) (net output) Solar + Battery generation facility to Delevan 230kV in Colusa County, California. The project has a contractual In-service date of: 8/30/25 with a current planned In-service date of: 9/7/28 | Planning | 2025-03-21 |  |  | Colusa ¦ Cottonwood CDP, Shasta ¦ Glenn ¦ Shasta ¦ Tehama | N/A | Yes | N/A | T.0009188 ¦ T.0008063 ¦ T.0001609 | New | Generator Interconnection | Generation Interconnection | 0.25 | NA | 230 | N/A | 2026-07-22 | 2025-08-30 | 2028-09-07 | Transmission Project Review Process data (Resolution E-5252 Attach B | 1104 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - IC is suspending project. Notice from IC that they are behind an affected system (TANC) with estimated cost of of $50M and 5Yr Duration. Asks to cease all work on IF & IRNUs. At risk to withdraw. | Customer + Utility - GIP Upgrades | 1496 | 1496
Q1496 DESCENDANT RNCH 1 DELEVAN SUB RNU | 5799986 | T.0008063 | 82W | The Q1496 Descendant Ranch 1 Project from Cluster 11, proposes to interconnect a 500 megawatt (MW) (net output) Solar + Battery generation facility to Delevan 230kV in Colusa County, California. The project has a contractual In-service date of: 8/30/25 with a current planned In-service date of: 9/7/28 | Engineering more than 50% complete | 2025-03-21 |  |  | Colusa | N/A | Yes | N/A | T.0009188 ¦ T.0008063 ¦ T.0001609 | New | Generator Interconnection | Generation Interconnection | N/A | N/A | N/A | 230 kV | 2026-03-03 | 2025-08-30 | 2028-09-07 | Transmission Project Review Process data (Resolution E-5252 Attach B | 1104 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - IC is suspending project. Notice from IC that they are behind an affected system (TANC) with estimated cost of of $50M and 5Yr Duration. Asks to cease all work on IF & IRNUs. At risk to withdraw. | Customer + Utility - GIP Upgrades
Q1496 DESCENDANT RNCH 1 CTTNWD SUB RNU | 5799987 | T.0008063 | 82W | The Q1496 Descendant Ranch 1 Project from Cluster 11, proposes to interconnect a 500 megawatt (MW) (net output) Solar + Battery generation facility to Delevan 230kV in Colusa County, California. The project has a contractual In-service date of: 8/30/25 with a current planned In-service date of: 9/7/28 | Engineering more than 50% complete | 2025-03-21 |  |  | Cottonwood CDP, Shasta | N/A | Yes | N/A | T.0009188 ¦ T.0008063 ¦ T.0001609 | New | Generator Interconnection | Special Protection Scheme | N/A | 26.1945 | N/A | 230 kV | 2026-06-17 | 2025-08-30 | 2028-09-07 | Transmission Project Review Process data (Resolution E-5252 Attach B | 1104 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - IC is suspending project. Notice from IC that they are behind an affected system (TANC) with estimated cost of of $50M and 5Yr Duration. Asks to cease all work on IF & IRNUs. At risk to withdraw. | Customer + Utility - GIP Upgrades | 1496 | 1496
Contra Costa 230kV SW's 601, 603 overload | 5800030 | T.0008048 | 60W | The C11P2-NP01 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Contra Costa Substation 230kV in Contra Costa County, California. | Construction (25%-50%) | 2025-05-01 |  |  | Antioch, Contra Costa ¦ Contra Costa ¦ Sacramento ¦ Solano | PG&E: North Valley Area | No | 2022 | T.0010478 ¦ 0 ¦ 0 ¦ 0 ¦ 0 | Relocate | Reliability | T-Line Capacity | N/A | NA | 230 | N/A | 2025-01-08 | 2025-05-01 | 2025-05-30 | Transmission Project Review Process data (Resolution E-5252 Attach B | 29 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom! | Q1691, Q1842, Q1843, Q1850, Q1915 | Q1691 | Q1842 | Q1843 | Q1850 | Q1915
Contra Costa 230kV SW's 601, 603 overload | 5800031 | T.0008048 | 60W | The C11P2-NP01 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Contra Costa Substation 230kV in Contra Costa County, California. | Construction (25%-50%) | 2025-05-01 |  |  | Antioch, Contra Costa | PG&E: North Valley Area | No | 2022 | T.0010478 ¦ 0 ¦ 0 ¦ 0 ¦ 0 | Relocate | Reliability | T-Line Capacity | N/A | NA | 230 | N/A | 2025-02-03 | 2025-05-01 | 2025-05-30 | Transmission Project Review Process data (Resolution E-5252 Attach B | 29 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom! | Q1691, Q1842, Q1843, Q1850, Q1915 | Q1691 | Q1842 | Q1843 | Q1850 | Q1915
Contra Costa 230kV SW's 601, 603 overload | 5800032 | T.0008048 | 60W | The C11P2-NP01 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Contra Costa Substation 230kV in Contra Costa County, California. | Engineering more than 50% complete | 2025-05-01 |  |  | Alameda ¦ Antioch, Contra Costa ¦ Brentwood, Contra Costa ¦ Contra Costa | PG&E: North Valley Area | No | 2022 | T.0010478 ¦ 0 ¦ 0 ¦ 0 ¦ 0 | Relocate | Reliability | T-Line Capacity | N/A | NA | 230 | N/A | 2025-07-16 | 2025-05-01 | 2025-09-02 | Transmission Project Review Process data (Resolution E-5252 Attach B | 124 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom! | Q1691, Q1842, Q1843, Q1850, Q1915 | Q1691 | Q1842 | Q1843 | Q1850 | Q1915
Contra Costa 230kV SW's 601, 603 overload | 5800033 | T.0008048 | 61X | The C11P2-NP01 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Contra Costa Substation 230kV in Contra Costa County, California. | Construction (50%-75%) | 2025-05-01 |  |  | Antioch, Contra Costa | PG&E: North Valley Area | No | 2022 | T.0010478 ¦ 0 ¦ 0 ¦ 0 ¦ 0 | Upgrade/Retrofit | Reliability | T-Line Capacity | N/A | 19.1042 | N/A | 230 kV | 2024-12-06 | 2025-05-01 | 2025-05-30 | Transmission Project Review Process data (Resolution E-5252 Attach B | 29 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom! | Q1691, Q1842, Q1843, Q1850, Q1915 | Q1691 | Q1842 | Q1843 | Q1850 | Q1915
ARCO 230KV CONTROL BUILDING NU | 5800064 | T.0008073 | 82W | The POS-Q1586-NU1, POS-Q1587-NU1 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Arco 230kV in Kern County, California. | Operational | 2023-07-30 |  |  | Kern | N/A | Yes | N/A |  | New | Generator Interconnection | Modular Protection and Automation Control | N/A | N/A | N/A | 230 kV | 2023-08-21 | 2023-07-30 | 2024-05-22 | Transmission Project Review Process data (Resolution E-5252 Attach B | 297 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom! | Q1495, Q1586, Q1587, Q1736, Q1740 | Q1495 | Q1586 | Q1587 | Q1736 | Q1740
Q1444 SALOON ENERGY STORAGE (DA) | 5800364 | T.0008218 | 82Y | The Q1444 Saloon Energy Storage Project Project from Cluster 11, proposes to interconnect a 150 megawatt (MW) (net output) Solar + Battery generation facility to Cortina 115kV in Colusa County, California. The project has a contractual In-service date of: 6/9/27 with a current planned In-service date of: 7/27/27 | Engineering more than 50% complete | 2025-04-28 |  |  | Colusa | N/A | Yes | N/A | T.0007629 ¦ T.0007629 ¦ T.0001609 | Upgrade/Retrofit | Generator Interconnection | Generation Interconnection | N/A | N/A | N/A | 115 kV | 2026-11-20 | 2027-06-09 | 2027-07-27 | Transmission Project Review Process data (Resolution E-5252 Attach B | 48 | Yes |  |  | N/A |  | N/A | N/A | CEC | N/A | NOC |  | N/A [See Notes] |  | 05/06/25 - Tracking ISD in Q2 2027 | Customer - Permitting (Customer) | 1444 | 1444
Q1444 SALOON ENERGY GEN SITE (DA) | 5800365 | T.0008218 | 82Y | The Q1444 Saloon Energy Storage Project Project from Cluster 11, proposes to interconnect a 150 megawatt (MW) (net output) Solar + Battery generation facility to Cortina 115kV in Colusa County, California. The project has a contractual In-service date of: 6/9/27 with a current planned In-service date of: 7/27/27 | Engineering more than 50% complete | 2025-04-28 |  |  | Colusa | N/A | Yes | N/A | T.0007629 ¦ T.0007629 ¦ T.0001609 | Upgrade/Retrofit | Generator Interconnection | Generation Interconnection | N/A | 6.7436 | N/A | 115 kV | 2026-02-13 | 2027-06-09 | 2027-07-27 | Transmission Project Review Process data (Resolution E-5252 Attach B | 48 | Yes |  |  | N/A |  | N/A | N/A | CEC | N/A | NOC |  | N/A [See Notes] |  | 05/06/25 - Tracking ISD in Q2 2027 | Customer - Permitting (Customer) | 1444 | 1444
Q1444 SALOON ENERGY T-LINE (DA) | 5800366 | T.0008218 | 82D | The Q1444 Saloon Energy Storage Project Project from Cluster 11, proposes to interconnect a 150 megawatt (MW) (net output) Solar + Battery generation facility to Cortina 115kV in Colusa County, California. The project has a contractual In-service date of: 6/9/27 with a current planned In-service date of: 7/27/27 | Engineering more than 50% complete | 2025-04-28 |  |  | Colusa ¦ Hartley CDP, Solano ¦ Solano ¦ Yolo | N/A | Yes | N/A | T.0007629 ¦ T.0007629 ¦ T.0001609 | New | Generator Interconnection | Generation Interconnection | 3.25 | NA | 115 | N/A | 2026-02-02 | 2027-06-09 | 2027-07-27 | Transmission Project Review Process data (Resolution E-5252 Attach B | 48 | Yes |  |  | N/A |  | N/A | N/A | CEC | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - Tracking ISD in Q2 2027 | Customer - Permitting (Customer) | 1444 | 1444
Q1444 SALOON ENRGY CRTNA CB(RNU) | 5800367 | T.0008218 | 82W | The Q1444 Saloon Energy Storage Project Project from Cluster 11, proposes to interconnect a 150 megawatt (MW) (net output) Solar + Battery generation facility to Cortina 115kV in Colusa County, California. The project has a contractual In-service date of: 6/9/27 with a current planned In-service date of: 7/27/27 | Engineering more than 50% complete | 2025-04-28 |  |  | Colusa | N/A | Yes | N/A | T.0007629 ¦ T.0007629 ¦ T.0001609 | New | Generator Interconnection | Generation Interconnection | N/A | 6.7436 | N/A | 115 kV | 2025-12-23 | 2027-06-09 | 2027-07-27 | Transmission Project Review Process data (Resolution E-5252 Attach B | 48 | Yes |  |  | N/A |  | N/A | N/A | CEC | N/A | NOC |  | N/A [See Notes] |  | 05/06/25 - Tracking ISD in Q2 2027 | Customer - Permitting (Customer) | 1444 | 1444
Q1461 RECLAIMED WIND GEN SITE DA | 5800939 | T.0008307 | 82Y | The Q1461 Reclaimed Wind Project from Cluster 11, proposes to interconnect a 90.7 megawatt (MW) (net output) Wind Turbine generation facility to Kelso-Tesla Tap 230kV Line in Alameda County, California. The project has a contractual In-service date of: 10/5/26 with a current planned In-service date of: 8/24/26 | Operational | 2023-06-30 |  |  | Hayward, Alameda | N/A | No | N/A | T.0004673 | Upgrade/Retrofit | Work Requested by Others | Load Interconnection | N/A | 9.9849 | N/A | 230 kV | 2023-12-29 | 2026-10-05 | 2026-08-24 | Transmission Project Review Process data (Resolution E-5252 Attach B | -42 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | NOC: AL 6570-E | 2022-04-22 | Approved | 2022 | 05/06/25 - Tracking ISD in Q3 2026 attributed to customer POI change | Customer - Project Design | 1461 | 1461
Q1461 RECLAIMED WIND KELSO SUB RNU | 5800942 | T.0008307 | 82W | The Q1461 Reclaimed Wind Project from Cluster 11, proposes to interconnect a 90.7 megawatt (MW) (net output) Wind Turbine generation facility to Kelso-Tesla Tap 230kV Line in Alameda County, California. The project has a contractual In-service date of: 10/5/26 with a current planned In-service date of: 8/24/26 | Operational | 2023-06-30 |  |  | Hayward, Alameda | N/A | No | N/A | T.0004673 | Upgrade/Retrofit | Work Requested by Others | Special Protection Scheme | N/A | 9.9849 | N/A | 230 kV | 2023-12-29 | 2026-10-05 | 2026-08-24 | Transmission Project Review Process data (Resolution E-5252 Attach B | -42 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | NOC: AL 6570-E | 2022-04-22 | Approved | 2022 | 05/06/25 - Tracking ISD in Q3 2026 attributed to customer POI change | Customer - Project Design | 1461 | 1461
Q1461 RECLAIMED WIND TESLA SUB RNU | 5800943 | T.0008307 | 82W | The Q1461 Reclaimed Wind Project from Cluster 11, proposes to interconnect a 90.7 megawatt (MW) (net output) Wind Turbine generation facility to Kelso-Tesla Tap 230kV Line in Alameda County, California. The project has a contractual In-service date of: 10/5/26 with a current planned In-service date of: 8/24/26 | Operational | 2023-06-30 |  |  | Hayward, Alameda | N/A | No | N/A | T.0004673 | Upgrade/Retrofit | Work Requested by Others | Special Protection Scheme | N/A | 9.9849 | N/A | 230 kV | 2023-12-29 | 2026-10-05 | 2026-08-24 | Transmission Project Review Process data (Resolution E-5252 Attach B | -42 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | NOC: AL 6570-E | 2022-04-22 | Approved | 2022 | 05/06/25 - Tracking ISD in Q3 2026 attributed to customer POI change | Customer - Project Design | 1461 | 1461
Gold Hill Substation 115 kV circuit breakers 142 and 172 overstress | 5801228 | T.0006348 | 64C | The C12P1-NPT01 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Gold Hill 115kV in Sacramento County, California. | Construction (25%-50%) | 2025-05-30 |  |  | Folsom, Sacramento | PG&E: North Valley Area | No | N/A | 0 ¦ T.0006433 | Replace | Asset Condition | T-Line Capacity | N/A | 12.8702 | N/A | 115 kV | 2024-05-13 | 2025-05-30 | 2025-06-04 | Transmission Project Review Process data (Resolution E-5252 Attach B | 5 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom! | Q1687, Q1507 | Q1687 | Q1507
Q1835 CASCADE ES EXPN GEN SITE DA | 5801704 | T.0008519 | 82Y | The Q1835 Cascade ES Expansion Project from Cluster 9, proposes to interconnect a 20 megawatt (MW) (net output) Battery generation facility to Weber in San Joaquin County, California. The project has a contractual In-service date of: 8/14/24 with a current planned In-service date of: 12/4/24 | Engineering more than 50% complete | 2030-05-01 |  |  | Angels, Calaveras ¦ Calaveras ¦ Copperopolis CDP, Calaveras ¦ Stanislaus ¦ Tuolumne ¦ Vallecito CDP, Calaveras | N/A | No | N/A |  | Replace | Asset Condition | Age/Condition - Replace Conductor | 1 | NA | 115 | N/A | 2025-11-04 | 2024-08-14 | 2024-12-04 | Transmission Project Review Process data (Resolution E-5252 Attach B | 112 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | NOC: AL 6382-E | 2021-10-28 | Approved | 2021 | 11/07/24 - Q1835 Cascade 20W did not energize 11/5 as planned. The customer was not ready and has pushed out their energization out a week and I believe the date is TBD. 10/31/24 - ISD delayed to November 4 2024 due to Customer delays | Customer - Construction Delays | 1835 | 1835
Q1835 CASCADE ES EXPN WEB SUB RNU | 5801705 | T.0008519 | 82W | The Q1835 Cascade ES Expansion Project from Cluster 9, proposes to interconnect a 20 megawatt (MW) (net output) Battery generation facility to Weber in San Joaquin County, California. The project has a contractual In-service date of: 8/14/24 with a current planned In-service date of: 12/4/24 | Engineering more than 50% complete | 2030-05-01 |  |  | Angels, Calaveras ¦ Calaveras ¦ Copperopolis CDP, Calaveras ¦ Stanislaus ¦ Tuolumne ¦ Vallecito CDP, Calaveras | N/A | No | N/A |  | Replace | Asset Condition | Age/Condition - Replace Conductor | 1 | NA | 115 | N/A | 2025-11-04 | 2024-08-14 | 2024-12-04 | Transmission Project Review Process data (Resolution E-5252 Attach B | 112 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | NOC: AL 6382-E | 2021-10-28 | Approved | 2021 | 11/07/24 - Q1835 Cascade 20W did not energize 11/5 as planned. The customer was not ready and has pushed out their energization out a week and I believe the date is TBD. 10/31/24 - ISD delayed to November 4 2024 due to Customer delays | Customer - Construction Delays
Q1484 - PEC - GENSITE DA PHASE 2 | 5801740 | T.0007449 | 82Y | The Q1484 Panoche Energy Center, 16 MW Project from Cluster 11, proposes to interconnect a 16 megawatt (MW) (net output) Natural Gas generation facility to Panoche 230kV in Fresno County, California. The project has a contractual In-service date of: 9/15/21 with a current planned In-service date of: 9/15/21 | Engineering more than 50% complete | 2030-05-01 |  |  | Angels, Calaveras ¦ Calaveras ¦ Copperopolis CDP, Calaveras ¦ Stanislaus ¦ Tuolumne ¦ Vallecito CDP, Calaveras | 0 | No | N/A | #N/A | Replace | Asset Condition | Age/Condition - Replace Conductor | 1 | NA | 115 | N/A | 2025-11-04 | 2022-02-15 | 2021-09-15 | Transmission Project Review Process data (Resolution E-5252 Attach B | -153 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | NOC: AL 6382-E | 2021-10-28 | Approved | 2021 | 11/28/23 - customer opted for the 16MW and cancelled the remaining 47 MWs. | #VALUE! | #N/A
Stanislaus-Melones Sw Sta-Manteca #1 115 kV Line Reconductor | 5801741 | T.0004301 | 93C | The C12P2-LDNU2 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Stanislaus-Melones Sw Sta-Manteca #1 115kV Line in San Joaquin County, California. | Engineering more than 50% complete | 2030-05-01 |  |  | Angels, Calaveras ¦ Calaveras ¦ Copperopolis CDP, Calaveras ¦ Stanislaus ¦ Tuolumne ¦ Vallecito CDP, Calaveras | 0 | No | N/A | T.0007445 ¦ 0 | Replace | Asset Condition | T-Line Capacity | 1 | NA | 115 | N/A | 2025-11-04 | 2030-05-01 | 2025-11-27 | Transmission Project Review Process data (Resolution E-5252 Attach B | -1616 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom! | Q1557, Q1904 | Q1557 | Q1904
Q1713 BIA GWF HNFRD SWTCHNG STTN DA | 5801981 | T.0008538 | 82Y | The Q1713 BIA Bess 1 Project from Cluster 13, proposes to interconnect a 32 megawatt (MW) (net output) Battery generation facility to GWF SW 115kV in Kings County, California. The project has a contractual In-service date of: 4/15/24 with a current planned In-service date of: 5/22/25 | Construction (50%-75%) | 2023-09-30 |  |  | San Joaquin | N/A | No | N/A | T.0003009 ¦ T.0000043 ¦ T.0007056 ¦ T.0004255 ¦ T.0007056 ¦ T.0003016 ¦ T.0006452 ¦ T.0009177 | Relocate | Load Growth | System Design Upgrade | N/A | 0.27151 | 60 | N/A | 2022-11-17 | 2024-04-15 | 2025-05-22 | Transmission Project Review Process data (Resolution E-5252 Attach B | 402 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - The customer's control room building delay construction activities. PG&E comms depend on IC construction schedule. PM indicated July energization date | Customer + Utility - Construction Delays | 1713 | 1713
Q1713 BIA GEN SITE DA | 5801982 | T.0008538 | 82Y | The Q1713 BIA Bess 1 Project from Cluster 13, proposes to interconnect a 32 megawatt (MW) (net output) Battery generation facility to GWF SW 115kV in Kings County, California. The project has a contractual In-service date of: 4/15/24 with a current planned In-service date of: 5/22/25 | Construction (50%-75%) | 2023-09-30 |  |  | San Joaquin | N/A | No | N/A | T.0003009 ¦ T.0000043 ¦ T.0007056 ¦ T.0004255 ¦ T.0007056 ¦ T.0003016 ¦ T.0006452 ¦ T.0009177 | Relocate | Load Growth | System Design Upgrade | N/A | 0.27151 | 60 | N/A | 2022-11-17 | 2024-04-15 | 2025-05-22 | Transmission Project Review Process data (Resolution E-5252 Attach B | 402 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - The customer's control room building delay construction activities. PG&E comms depend on IC construction schedule. PM indicated July energization date | Customer + Utility - Construction Delays | 1713 | 1713
Q1593 PELICANS (DA) GEN-SITE | 5803139 | T.0008735 | 82Y | The Q1593 Pelicans Jaw Hybrid Solar Project from Cluster 12, proposes to interconnect a 500 megawatt (MW) (net output) Solar + Battery generation facility to Gates-Midway 230kV Line in Kings County, California. The project has a contractual In-service date of: 8/22/27 with a current planned In-service date of: 5/1/26 | Engineering more than 50% complete | 2026-09-22 |  |  | Fresno | N/A | Yes | N/A | T.0007289 ¦ T.0006452 ¦ T.0008543 | Upgrade/Retrofit | Generator Interconnection | Generation Interconnection | N/A | 77.6619 | N/A | 230 kV | 2025-07-23 | 2026-09-22 | 2026-05-01 | Transmission Project Review Process data (Resolution E-5252 Attach B | -144 | No |  |  | Final Certified | 45261 | EIR | N/A | Kern County | N/A | NOC: AL 7236-E | 2024-04-05 | Approved | 2024 | 05/06/25 - MMA submitted 04/08/25 - ISD tracking May 2026 | - | 1593 | 1593
Q1593 PELICANS (DA) SS OVERSIGHT | 5803140 | T.0008735 | 82Y | The Q1593 Pelicans Jaw Hybrid Solar Project from Cluster 12, proposes to interconnect a 500 megawatt (MW) (net output) Solar + Battery generation facility to Gates-Midway 230kV Line in Kings County, California. The project has a contractual In-service date of: 8/22/27 with a current planned In-service date of: 5/1/26 | Construction (under 10%) | 2026-09-22 |  |  | Buttonwillow CDP, Kern | N/A | Yes | N/A | T.0007289 ¦ T.0006452 ¦ T.0008543 | New | Generator Interconnection | Generation Interconnection | N/A | 94.5324 | N/A | 230 kV | 2025-01-06 | 2026-09-22 | 2026-05-01 | Transmission Project Review Process data (Resolution E-5252 Attach B | -144 | No |  |  | Final Certified | 45261 | EIR | N/A | Kern County | N/A | NOC: AL 7236-E | 2024-04-05 | Approved | 2024 | 05/06/25 - MMA submitted 04/08/25 - ISD tracking May 2026 | - | 1593 | 1593
Q1593 PELICANS (RNU) MIDWAY SUB DDT | 5803141 | T.0008735 | 82W | The Q1593 Pelicans Jaw Hybrid Solar Project from Cluster 12, proposes to interconnect a 500 megawatt (MW) (net output) Solar + Battery generation facility to Gates-Midway 230kV Line in Kings County, California. The project has a contractual In-service date of: 8/22/27 with a current planned In-service date of: 5/1/26 | Engineering more than 50% complete | 2026-09-22 |  |  | Buttonwillow CDP, Kern | N/A | Yes | N/A | T.0007289 ¦ T.0006452 ¦ T.0008543 | Upgrade/Retrofit | Generator Interconnection | Special Protection Scheme | N/A | 94.5324 | N/A | 230 kV | 2026-02-18 | 2026-09-22 | 2026-05-01 | Transmission Project Review Process data (Resolution E-5252 Attach B | -144 | No |  |  | Final Certified | 45261 | EIR | N/A | Kern County | N/A | NOC: AL 7236-E | 2024-04-05 | Approved | 2024 | 05/06/25 - MMA submitted 04/08/25 - ISD tracking May 2026 | -
Q1593 PELICANS (RNU) GATES SUB DDT | 5803142 | T.0008735 | 82W | The Q1593 Pelicans Jaw Hybrid Solar Project from Cluster 12, proposes to interconnect a 500 megawatt (MW) (net output) Solar + Battery generation facility to Gates-Midway 230kV Line in Kings County, California. The project has a contractual In-service date of: 8/22/27 with a current planned In-service date of: 5/1/26 | Engineering more than 50% complete | 2026-09-22 |  |  | Fresno | N/A | Yes | N/A | T.0007289 ¦ T.0006452 ¦ T.0008543 | Upgrade/Retrofit | Generator Interconnection | Special Protection Scheme | N/A | 77.6619 | N/A | 230 kV | 2026-02-03 | 2026-09-22 | 2026-05-01 | Transmission Project Review Process data (Resolution E-5252 Attach B | -144 | No |  |  | Final Certified | 45261 | EIR | N/A | Kern County | N/A | NOC: AL 7236-E | 2024-04-05 | Approved | 2024 | 05/06/25 - MMA submitted 04/08/25 - ISD tracking May 2026 | -
Q1593 PELICANS (RNU) ARCO SUB TERM OPGW | 5803143 | T.0008735 | 82W | The Q1593 Pelicans Jaw Hybrid Solar Project from Cluster 12, proposes to interconnect a 500 megawatt (MW) (net output) Solar + Battery generation facility to Gates-Midway 230kV Line in Kings County, California. The project has a contractual In-service date of: 8/22/27 with a current planned In-service date of: 5/1/26 | Engineering more than 50% complete | 2026-09-22 |  |  | Kern | N/A | Yes | N/A | T.0007289 ¦ T.0006452 ¦ T.0008543 | Upgrade/Retrofit | Generator Interconnection | System Design Upgrade | N/A | 4.5471 | N/A | 230 kV | 2025-11-14 | 2026-09-22 | 2026-05-01 | Transmission Project Review Process data (Resolution E-5252 Attach B | -144 | No |  |  | Final Certified | 45261 | EIR | N/A | Kern County | N/A | NOC: AL 7236-E | 2024-04-05 | Approved | 2024 | 05/06/25 - MMA submitted 04/08/25 - ISD tracking May 2026 | -
Q1593 PELICANS (RNU) T-LINE OPGW | 5803144 | T.0008735 | 82B | The Q1593 Pelicans Jaw Hybrid Solar Project from Cluster 12, proposes to interconnect a 500 megawatt (MW) (net output) Solar + Battery generation facility to Gates-Midway 230kV Line in Kings County, California. The project has a contractual In-service date of: 8/22/27 with a current planned In-service date of: 5/1/26 | Engineering more than 50% complete | 2026-09-22 |  |  | Kettleman City, Fresno | N/A | Yes | N/A | T.0007289 ¦ T.0006452 ¦ T.0008543 | Upgrade/Retrofit | Generator Interconnection | System Design Upgrade | 10 | N/A | 230 | N/A | 2025-09-25 | 2027-08-22 | 2026-05-01 | Transmission Project Review Process data (Resolution E-5252 Attach B | -478 | No |  |  | Final Certified | 45261 | EIR | N/A | Kern County | N/A | NOC: AL 7236-E | 2024-04-05 | Approved | 2024 | 05/06/25 - MMA submitted 04/08/25 - ISD tracking May 2026 | - | 1593 | 1593
Q1593 PELICANS (RNU) SS OVERSIGHT | 5803145 | T.0008735 | 82W | The Q1593 Pelicans Jaw Hybrid Solar Project from Cluster 12, proposes to interconnect a 500 megawatt (MW) (net output) Solar + Battery generation facility to Gates-Midway 230kV Line in Kings County, California. The project has a contractual In-service date of: 8/22/27 with a current planned In-service date of: 5/1/26 | Construction (under 10%) | 2026-09-22 |  |  | Buttonwillow CDP, Kern | N/A | Yes | N/A | T.0007289 ¦ T.0006452 ¦ T.0008543 | New | Generator Interconnection | Generation Interconnection | N/A | 94.5324 | N/A | 230 kV | 2024-12-16 | 2026-09-22 | 2026-05-01 | Transmission Project Review Process data (Resolution E-5252 Attach B | -144 | No |  |  | Final Certified | 45261 | EIR | N/A | Kern County | N/A | NOC: AL 7236-E | 2024-04-05 | Approved | 2024 | 05/06/25 - MMA submitted 04/08/25 - ISD tracking May 2026 | - | 1593 | 1593
Stanislaus-Melones Sw Sta-Manteca #1 115 kV Line Reconductor | 5803427 | T.0004301 | 93C | The C12P2-LDNU2 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Stanislaus-Melones Sw Sta-Manteca #1 115kV Line in San Joaquin County, California. | Engineering more than 50% complete | 2030-05-01 |  |  | Angels, Calaveras ¦ Calaveras ¦ Copperopolis CDP, Calaveras ¦ Manteca, San Joaquin ¦ Murphys CDP, Calaveras ¦ San Joaquin ¦ Stanislaus ¦ Tuolumne ¦ Vallecito CDP, Calaveras | 0 | No | N/A | T.0007445 ¦ 0 | Replace | Asset Condition | T-Line Capacity | 12 | NA | 115 | N/A | 2030-04-06 | 2030-05-01 | 2030-04-18 | Transmission Project Review Process data (Resolution E-5252 Attach B | -13 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom! | Q1557, Q1904 | Q1557 | Q1904
Stanislaus-Melones Sw Sta-Manteca #1 115 kV Line Reconductor | 5803428 | T.0004301 | 93C | The C12P2-LDNU2 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Stanislaus-Melones Sw Sta-Manteca #1 115kV Line in San Joaquin County, California. | Engineering more than 50% complete | 2030-05-01 |  |  | Angels, Calaveras ¦ Calaveras ¦ Copperopolis CDP, Calaveras ¦ Stanislaus ¦ Tuolumne ¦ Vallecito CDP, Calaveras | 0 | No | N/A | T.0007445 ¦ 0 | Replace | Asset Condition | T-Line Capacity | 2 | NA | 115 | N/A | 2031-05-08 | 2030-05-01 | 2031-06-01 | Transmission Project Review Process data (Resolution E-5252 Attach B | 396 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom! | Q1557, Q1904 | Q1557 | Q1904
Contra Costa 230kV SW's 601, 603 overload | 5803600 | T.0008048 | 61X | The C11P2-NP01 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Contra Costa Substation 230kV in Contra Costa County, California. | Engineering more than 50% complete | 2025-05-01 |  |  | Antioch, Contra Costa | PG&E: North Valley Area | No | 2022 | T.0010478 ¦ 0 ¦ 0 ¦ 0 ¦ 0 | Upgrade/Retrofit | Reliability | T-Line Capacity | N/A | 19.1042 | N/A | 230 kV | 2025-07-29 | 2025-05-01 | 2025-09-15 | Transmission Project Review Process data (Resolution E-5252 Attach B | 137 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom! | Q1691, Q1842, Q1843, Q1850, Q1915 | Q1691 | Q1842 | Q1843 | Q1850 | Q1915
Q1702 POTENTIA-VIRIDI TESLA SUB DA | 5803781 | T.0008918 | 82Y | The Q1702 Potentia-Viridi Project from Cluster 13, proposes to interconnect a 400 megawatt (MW) (net output) Wind Turbine + Solar generation facility to Tesla 500kV in San Joaquin County, California. The project has a contractual In-service date of: 3/30/28 with a current planned In-service date of: 3/30/28 | Engineering more than 50% complete | 2028-03-20 |  |  | Alameda | N/A | Yes | N/A | T.0004673 ¦ Maintenance ¦ T.0001609 ¦ T.0007288 ¦ Maintenance ¦ T.0007288 | New | Generator Interconnection | Generation Interconnection | N/A | 69.382 | N/A | 500 kV | 2026-08-03 | 2028-03-30 | 2028-03-30 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - Changed ISD to match contractual date pending PG&E and customer Project Sequencing coordination. | - | 1702 | 1702
Q1702 POTENTIA-VIRIDI GEN SITE DA | 5803782 | T.0008918 | 82Y | The Q1702 Potentia-Viridi Project from Cluster 13, proposes to interconnect a 400 megawatt (MW) (net output) Wind Turbine + Solar generation facility to Tesla 500kV in San Joaquin County, California. The project has a contractual In-service date of: 3/30/28 with a current planned In-service date of: 3/30/28 | Engineering more than 50% complete | 2028-03-20 |  |  | Alameda | N/A | Yes | N/A | T.0004673 ¦ Maintenance ¦ T.0001609 ¦ T.0007288 ¦ Maintenance ¦ T.0007288 | Upgrade/Retrofit | Generator Interconnection | Generation Interconnection | N/A | 69.382 | N/A | 500 kV | 2026-02-19 | 2028-03-30 | 2028-03-30 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - Changed ISD to match contractual date pending PG&E and customer Project Sequencing coordination. | - | 1702 | 1702
Q1702 POTENTIA-VIRIDI T LINE DA | 5803783 | T.0008918 | 82D | The Q1702 Potentia-Viridi Project from Cluster 13, proposes to interconnect a 400 megawatt (MW) (net output) Wind Turbine + Solar generation facility to Tesla 500kV in San Joaquin County, California. The project has a contractual In-service date of: 3/30/28 with a current planned In-service date of: 3/30/28 | Engineering more than 50% complete | 2028-03-20 |  |  | Alameda | N/A | Yes | N/A | T.0004673 ¦ Maintenance ¦ T.0001609 ¦ T.0007288 ¦ Maintenance ¦ T.0007288 | New | Generator Interconnection | Generation Interconnection | 1.5 | 69.382 | 500 | N/A | 2028-01-10 | 2028-03-30 | 2028-03-30 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - Changed ISD to match contractual date pending PG&E and customer Project Sequencing coordination. | - | 1702 | 1702
Q1702 POTENTIA-VIRIDI BAAH TESLA RNU | 5803784 | T.0008918 | 82W | The Q1702 Potentia-Viridi Project from Cluster 13, proposes to interconnect a 400 megawatt (MW) (net output) Wind Turbine + Solar generation facility to Tesla 500kV in San Joaquin County, California. The project has a contractual In-service date of: 3/30/28 with a current planned In-service date of: 3/30/28 | Engineering more than 50% complete | 2028-03-20 |  |  | Alameda | N/A | Yes | N/A | T.0004673 ¦ Maintenance ¦ T.0001609 ¦ T.0007288 ¦ Maintenance ¦ T.0007288 | New | Generator Interconnection | Generation Interconnection | N/A | 69.382 | N/A | 500 kV | 2026-08-03 | 2028-03-30 | 2028-03-30 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - Changed ISD to match contractual date pending PG&E and customer Project Sequencing coordination. | - | 1702 | 1702
ARCO 230KV - MIDWAY LCD | 5803819 | T.0008073 | 82W | The POS-Q1586-NU1, POS-Q1587-NU1 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Arco 230kV in Kern County, California. | Operational | 2023-07-30 |  |  | Kern | N/A | Yes | N/A |  | Upgrade/Retrofit | Generator Interconnection | Generation Interconnection | N/A | N/A | N/A | 230 kV | 2024-10-01 | 2023-07-30 | 2025-03-31 | Transmission Project Review Process data (Resolution E-5252 Attach B | 610 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom! | Q1495, Q1586, Q1587, Q1736, Q1740 | Q1495 | Q1586 | Q1587 | Q1736 | Q1740
Q1718- GONZAGA-GENSITE (DA) | 5804084 | T.0008968 | 82Y | The Q1718 Gonzaga Hybrid Project from Cluster 13, proposes to interconnect a 103.65 megawatt (MW) (net output) Wind Turbine + Battery generation facility to Los Banos 70kV in Merced County, California. The project has a contractual In-service date of: 11/1/25 with a current planned In-service date of: 11/3/25 | Engineering more than 50% complete | N/A |  |  | Walnut Creek, Contra Costa | N/A | No | N/A | T.0003009 | New | Emergency Event | Replace Breakers | N/A | 2.0542 | N/A | 230 kV | 2025-10-17 | 2025-11-01 | 2025-11-03 | Transmission Project Review Process data (Resolution E-5252 Attach B | 2 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - Tracking ISD to Q3 2026. Connects behind Gonzaga Wind. Low confidence ISD in 2025. | - | 1718 | 1718
Q1750 WINDWALKER OS DIABLO CANYON SUB (D | 5804094 | T.0008967 | 82Y | The Q1750 Windwalker Offshore Project from Cluster 13, proposes to interconnect a 1000 megawatt (MW) (net output) Wind Turbine generation facility to Diablo Canyon SW 500kV in San Luis Obispo County, California. The project has a contractual In-service date of: 4/12/28 with a current planned In-service date of: 3/27/28 | Engineering less than 50% complete | 2028-04-12 |  |  | San Luis Obispo | N/A | Yes | N/A | Maintenance ¦ Maintenance ¦ T.0003009 ¦ Maintenance ¦ Maintenance ¦ T.0007722 | New | Generator Interconnection | Generation Interconnection | N/A | 35.6227 | N/A | 500 kV | 2029-12-03 | 2028-04-12 | 2028-03-27 | Transmission Project Review Process data (Resolution E-5252 Attach B | -16 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - IC delays due to Gentie route acquisitions and permitting. | Customer - Land Rights | 1750 | 1750
Q1750 WINDWALKER OS T-LINE (DA) | 5804095 | T.0008967 | 82D | The Q1750 Windwalker Offshore Project from Cluster 13, proposes to interconnect a 1000 megawatt (MW) (net output) Wind Turbine generation facility to Diablo Canyon SW 500kV in San Luis Obispo County, California. The project has a contractual In-service date of: 4/12/28 with a current planned In-service date of: 3/27/28 | Engineering less than 50% complete | 2028-04-12 |  |  | San Luis Obispo | N/A | Yes | N/A | Maintenance ¦ Maintenance ¦ T.0003009 ¦ Maintenance ¦ Maintenance ¦ T.0007722 | New | Generator Interconnection | Generation Interconnection | N/A | 35.6227 | N/A | 500 kV | 2029-12-03 | 2028-04-12 | 2028-03-27 | Transmission Project Review Process data (Resolution E-5252 Attach B | -16 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - IC delays due to Gentie route acquisitions and permitting. | Customer - Land Rights | 1750 | 1750
Q1750 WINDWALKER OS DIABLO CANYON SUB (R | 5804097 | T.0008967 | 82W | The Q1750 Windwalker Offshore Project from Cluster 13, proposes to interconnect a 1000 megawatt (MW) (net output) Wind Turbine generation facility to Diablo Canyon SW 500kV in San Luis Obispo County, California. The project has a contractual In-service date of: 4/12/28 with a current planned In-service date of: 3/27/28 | Engineering less than 50% complete | 2028-04-12 |  |  | San Luis Obispo | N/A | Yes | N/A | Maintenance ¦ Maintenance ¦ T.0003009 ¦ Maintenance ¦ Maintenance ¦ T.0007722 | New | Generator Interconnection | Generation Interconnection | N/A | 35.6227 | N/A | 500 kV | 2029-12-03 | 2028-04-12 | 2028-03-27 | Transmission Project Review Process data (Resolution E-5252 Attach B | -16 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - IC delays due to Gentie route acquisitions and permitting. | Customer - Land Rights | 1750 | 1750
Q1350 - PAULSELL 60KV T-LINE-RNU | 5804359 | T.0007108 | 82B | The Q1350 Paulsell Solar Project from Cluster 10, proposes to interconnect a 20 megawatt (MW) (net output) Solar + Battery generation facility to Crow Creek SW 60kV in Stanislaus County, California. The project has a contractual In-service date of: 12/1/23 with a current planned In-service date of: 3/28/24 | Operational | 2023-02-01 |  |  | Crows Landing CDP, Stanislaus ¦ Stanislaus | PG&E: North Valley Area | Yes | N/A |  | Upgrade/Retrofit | Generator Interconnection | Line Reconductoring | 0.1 | NA | 60 | N/A | 2024-03-21 | 2023-12-01 | 2024-03-28 | Transmission Project Review Process data (Resolution E-5252 Attach B | 118 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | In-Service - 3/37/24 3/4/24 - Customer Failed PPI. New clearance set for 3/27. 2/5/24 -Likely ISD End of April 2024. Pending easements for Microwave at Wesley. 1/23/24 - Due to weather, the IC could not complete the test reports for submittal. Working on catchback and rescheduling PPI. 1/8/24 - Targeting COD by 4/1 per the IC. 12/12/23 - ISD is tracking. Gentie work is completed. 11/1/23 - ISD Tracking 10/2/23 - Work at Crowcreek is complete. IC has started construction 9/20/23 - Tline Switch has TID distribution equipment to be removed by the 3rd party. Low risk associated to the tline work and coordination. 9/18/23 - IT resource constraints due to overall volume of work. 8/7/23 - IC has not started construction. Expect ISD to trend later in Q1 2024. 07/27/23 - Need update on the IC schedule. 6/22/23 - some IC delays related IC customers XFMR order. Verify with SDQ1 expected. Check in with SDQ1 | Customer - !Telecom! | 1350 | 1350
NEW SS FOR LOS BANOS-PANOCHE 230KV | 5804622 | T.0009177 | 82W | The 22rsmt-4 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Dos Amigos–Panoche # 3 230 kV Line in Merced County, California. | Engineering less than 50% complete | 2028-05-01 |  |  | Merced | N/A | Yes | N/A | T.0003742 ¦ 0 ¦ T.0010817 ¦ T.0010816 ¦ 0 ¦ 0 ¦ T.0010942 ¦ TBD ¦ 0 ¦ T.0010887 ¦ T.0010738 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ T.0003005 ¦ T.0002987 ¦ T.0004490 ¦ T.0010467 ¦ T.0008538 | New | Generator Interconnection | T-Line Capacity | N/A | 4.17 | N/A | 230 kV | 2029-11-28 | 2028-05-01 | 2030-04-29 | Transmission Project Review Process data (Resolution E-5252 Attach B | 728 | Yes |  |  | N/A |  | TBD | TBD | TBD | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom!
Q1587- KINGSROAD-GENSITE (DA) | 5804790 | T.0009193 | 82Y | The Q1587 Kingsroad Hybrid Solar Project from Cluster 12, proposes to interconnect a 100 megawatt (MW) (net output) Solar + Battery generation facility to Arco 230kV in Kern County, California. The project has a contractual In-service date of: 12/15/25 with a current planned In-service date of: 7/24/26 | Planning | 2025-12-15 |  |  | Kern | N/A | Yes | N/A | Maintenance ¦ T.0006452 | New | Generator Interconnection | Generation Interconnection | N/A | 4.5471 | N/A | 230 kV | 2026-05-06 | 2025-12-15 | 2026-07-24 | Transmission Project Review Process data (Resolution E-5252 Attach B | 221 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - MMA needed to move out ISD. ISD TBD. IC CB on order, IC working through permitting. | - | 1587 | 1587
Q1587- KINGSROAD-ARCO SUB (DA) | 5804791 | T.0009193 | 82Y | The Q1587 Kingsroad Hybrid Solar Project from Cluster 12, proposes to interconnect a 100 megawatt (MW) (net output) Solar + Battery generation facility to Arco 230kV in Kern County, California. The project has a contractual In-service date of: 12/15/25 with a current planned In-service date of: 7/24/26 | Engineering less than 50% complete | 2025-12-15 |  |  | Kern | N/A | Yes | N/A | Maintenance ¦ T.0006452 | New | Generator Interconnection | Generation Interconnection | N/A | 4.5471 | N/A | 230 kV | 2027-06-10 | 2025-12-15 | 2026-07-24 | Transmission Project Review Process data (Resolution E-5252 Attach B | 221 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - MMA needed to move out ISD. ISD TBD. IC CB on order, IC working through permitting. | - | 1587 | 1587
Q1587- KINGSROAD - TLINE (DA) | 5804792 | T.0009193 | 82D | The Q1587 Kingsroad Hybrid Solar Project from Cluster 12, proposes to interconnect a 100 megawatt (MW) (net output) Solar + Battery generation facility to Arco 230kV in Kern County, California. The project has a contractual In-service date of: 12/15/25 with a current planned In-service date of: 7/24/26 | Planning | 2025-12-15 |  |  | Avenal, Kings ¦ Fresno ¦ Kern ¦ Kings | N/A | Yes | N/A | Maintenance ¦ T.0006452 | New | Generator Interconnection | Generation Interconnection | 1 | NA | 230 | N/A | 2027-02-08 | 2025-12-15 | 2026-07-24 | Transmission Project Review Process data (Resolution E-5252 Attach B | 221 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - MMA needed to move out ISD. ISD TBD. IC CB on order, IC working through permitting. | - | 1587 | 1587
Q1587- KINGSROAD-ARCO SUB (NU) | 5804793 | T.0009193 | 82W | The Q1587 Kingsroad Hybrid Solar Project from Cluster 12, proposes to interconnect a 100 megawatt (MW) (net output) Solar + Battery generation facility to Arco 230kV in Kern County, California. The project has a contractual In-service date of: 12/15/25 with a current planned In-service date of: 7/24/26 | Engineering less than 50% complete | 2025-12-15 |  |  | Kern | N/A | Yes | N/A | Maintenance ¦ T.0006452 | New | Generator Interconnection | Generation Interconnection | N/A | 4.5471 | N/A | 230 kV | 2027-06-24 | 2025-12-15 | 2026-07-24 | Transmission Project Review Process data (Resolution E-5252 Attach B | 221 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - MMA needed to move out ISD. ISD TBD. IC CB on order, IC working through permitting. | -
Q1587- KINGSROAD-GATES SUB (NU) | 5804794 | T.0009193 | 82W | The Q1587 Kingsroad Hybrid Solar Project from Cluster 12, proposes to interconnect a 100 megawatt (MW) (net output) Solar + Battery generation facility to Arco 230kV in Kern County, California. The project has a contractual In-service date of: 12/15/25 with a current planned In-service date of: 7/24/26 | Engineering less than 50% complete | 2025-12-15 |  |  | Fresno | N/A | Yes | N/A | Maintenance ¦ T.0006452 | New | Generator Interconnection | Generation Interconnection | N/A | 77.6619 | N/A | 230 kV | 2027-07-01 | 2025-12-15 | 2026-07-24 | Transmission Project Review Process data (Resolution E-5252 Attach B | 221 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - MMA needed to move out ISD. ISD TBD. IC CB on order, IC working through permitting. | -
Q1587- KINGSROAD-MIDWAY SUB (NU) | 5804795 | T.0009193 | 82W | The Q1587 Kingsroad Hybrid Solar Project from Cluster 12, proposes to interconnect a 100 megawatt (MW) (net output) Solar + Battery generation facility to Arco 230kV in Kern County, California. The project has a contractual In-service date of: 12/15/25 with a current planned In-service date of: 7/24/26 | Engineering less than 50% complete | 2025-12-15 |  |  | Buttonwillow CDP, Kern | N/A | Yes | N/A | Maintenance ¦ T.0006452 | New | Generator Interconnection | Special Protection Scheme | N/A | 94.5324 | N/A | 230 kV | 2027-04-05 | 2025-12-15 | 2026-07-24 | Transmission Project Review Process data (Resolution E-5252 Attach B | 221 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - MMA needed to move out ISD. ISD TBD. IC CB on order, IC working through permitting. | - | 1587 | 1587
Panoche 115 kV CB 102 overstress upgrade | 5804800 | T.0009194 | 60C | The 22rsmt-1 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Panoche 115 kV bus in Fresno County, California. | Engineering less than 50% complete | 2028-01-01 |  |  | Fresno ¦ Merced | PG&E: North Valley Area | No | 2022 | TBD ¦ T.0010887 | Upgrade/Retrofit | Policy | T-Line Capacity | N/A | NA | 500 | N/A | 2027-07-15 | 2028-01-01 | 2028-05-30 | Transmission Project Review Process data (Resolution E-5252 Attach B | 150 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom! | Q1940, Q1955 | Q1940 | Q1955
Panoche 115 kV CB 102 overstress upgrade | 5804801 | T.0009194 | 60C | The 22rsmt-1 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Panoche 115 kV bus in Fresno County, California. | Engineering more than 50% complete | 2028-01-01 |  |  | Fresno | PG&E: North Valley Area | No | 2022 | TBD ¦ T.0010887 | Upgrade/Retrofit | Policy | T-Line Capacity | N/A | NA | 230 | N/A | 2027-01-11 | 2028-01-01 | 2028-05-30 | Transmission Project Review Process data (Resolution E-5252 Attach B | 150 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom! | Q1940, Q1955 | Q1940 | Q1955
Panoche 115 kV CB 102 overstress upgrade | 5804804 | T.0009194 | 61C | The 22rsmt-1 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Panoche 115 kV bus in Fresno County, California. | Engineering more than 50% complete | 2028-01-01 |  |  | Merced | PG&E: North Valley Area | No | 2022 | TBD ¦ T.0010887 | Upgrade/Retrofit | Policy | T-Line Capacity | N/A | 53.2803 | N/A | 500 kV | 2027-11-02 | 2028-01-01 | 2028-04-04 | Transmission Project Review Process data (Resolution E-5252 Attach B | 94 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom!
Panoche 115 kV CB 102 overstress upgrade | 5804805 | T.0009194 | 61C | The 22rsmt-1 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Panoche 115 kV bus in Fresno County, California. | Engineering more than 50% complete | 2028-01-01 |  |  | Buttonwillow CDP, Kern | PG&E: North Valley Area | No | 2022 | TBD ¦ T.0010887 | Upgrade/Retrofit | Policy | T-Line Capacity | N/A | 94.5324 | N/A | 500 kV | 2028-02-04 | 2028-01-01 | 2028-04-28 | Transmission Project Review Process data (Resolution E-5252 Attach B | 118 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom!
Panoche 115 kV CB 102 overstress upgrade | 5804806 | T.0009194 | 61C | The 22rsmt-1 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Panoche 115 kV bus in Fresno County, California. | Engineering more than 50% complete | 2028-01-01 |  |  | Fresno | PG&E: North Valley Area | No | 2023 | TBD ¦ T.0010887 | Upgrade/Retrofit | Reliability | T-Line Capacity | N/A | 19.3832 | N/A | 500 kV | 2026-05-25 | 2028-01-01 | 2028-04-03 | Transmission Project Review Process data (Resolution E-5252 Attach B | 93 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom! | Q1940, Q1955 | Q1940 | Q1955
Panoche 115 kV CB 102 overstress upgrade | 5804811 | T.0009194 | 60C | The 22rsmt-1 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Panoche 115 kV bus in Fresno County, California. | Engineering more than 50% complete | 2028-01-01 |  |  | Fresno | PG&E: North Valley Area | No | 2022 | TBD ¦ T.0010887 | New | Policy | T-Line Capacity | 24.3 | NA | 230 | N/A | 2026-10-06 | 2028-01-01 | 2027-04-30 | Transmission Project Review Process data (Resolution E-5252 Attach B | -246 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom! | Q1940, Q1955 | Q1940 | Q1955
Panoche 115 kV CB 102 overstress upgrade | 5804813 | T.0009194 | 61C | The 22rsmt-1 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Panoche 115 kV bus in Fresno County, California. | Engineering more than 50% complete | 2028-01-01 |  |  | Fresno | PG&E: North Valley Area | No | 2022 | TBD ¦ T.0010887 | New | Policy | T-Line Capacity | N/A | 19.3832 | N/A | 500 kV | 2026-06-01 | 2028-01-01 | 2028-04-03 | Transmission Project Review Process data (Resolution E-5252 Attach B | 93 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom! | Q1940, Q1955 | Q1940 | Q1955
Panoche 115 kV CB 102 overstress upgrade | 5804878 | T.0009194 | 61C | The 22rsmt-1 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Panoche 115 kV bus in Fresno County, California. | Engineering more than 50% complete | 2028-01-01 |  |  | Fresno | PG&E: North Valley Area | No | 2022 | TBD ¦ T.0010887 | Upgrade/Retrofit | Policy | T-Line Capacity | N/A | 77.6619 | N/A | 500 kV | 2027-03-17 | 2028-01-01 | 2028-04-03 | Transmission Project Review Process data (Resolution E-5252 Attach B | 93 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom! | Q1940, Q1955 | Q1940 | Q1955
PANOCHE: UPGD EQUIP TO 1517A–EGI DOS AMI | 5805074 | T.0004255 | 82W | The C9P1-F11 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Dos Amigos–Panoche # 3 230 kV Line in Merced County, California. | Engineering more than 50% complete | 2021-09-30 |  |  | Fresno | 0 | Yes | N/A | T.0003742 ¦ T.0003005 ¦ T.0002987 ¦ T.0004490 ¦ T.0008538 ¦ 0 ¦ T.0010467 ¦ 0 ¦ T.0010817 ¦ T.0010816 ¦ 0 ¦ 0 ¦ T.0010942 ¦ TBD ¦ 0 ¦ T.0010887 ¦ T.0010738 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 | Upgrade/Retrofit | Generator Interconnection | Generation Interconnection | N/A | 19.3832 | N/A | 230 kV | 2025-11-10 | 2021-09-30 | 2026-03-10 | Transmission Project Review Process data (Resolution E-5252 Attach B | 1622 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | NOC: AL 7392-E | 2024-10-02 | Approved | 2024 | 04/07/25 - Project tracking to ISD on schedule | Utility - !Telecom! | Q1135, Q1127, Q1128, Q1129, Q1713, Q1568, Q1709, 2226-WD, Q1928, Q1930, Q1932, Q1933, Q1934, Q1935, Q1940, Q1953, Q1955, Q1956, Q1963, Q1966, Q1968, Q1970, Q1975, Q1977 | Q1135 | Q1127 | Q1128 | Q1129 | Q1713 | Q1568 | Q1709 | 2226-WD | Q1928 | Q1930 | Q1932 | Q1933 | Q1934 | Q1935 | Q1940 | Q1953 | Q1955 | Q1956 | Q1963
Vierra 115 kV Looping Project | 5805478 | T.0000597 | 61G | The C14P2-NPT04 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Vierra 115kV in San Joaquin County, California. | Engineering more than 50% complete | 2014-05-01 |  |  | Lathrop, San Joaquin | PG&E: North Valley Area | No | 2011 | T.0011086 ¦ T.0010853 ¦ 0 ¦ T.0011168 ¦ 0 | Upgrade/Retrofit | Reliability | T-Line Capacity | N/A | 1.355 | N/A | 115 kV | 2025-06-03 | 2014-05-01 | 2026-06-04 | Transmission Project Review Process data (Resolution E-5252 Attach B | 4417 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom! | Q1867, Q1887, Q1904, Q1920, Q1929 | Q1867 | Q1887 | Q1904 | Q1920 | Q1929
Estrella Substation Project | 5805505 | T.0000154 | 60X | The C14P2-NFT01 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Estrella Sub in ? County, California. | Engineering more than 50% complete | 2019-05-01 |  |  | El Paso de Robles, San Luis Obispo ¦ San Luis Obispo ¦ San Miguel CDP, San Luis Obispo | PG&E: North Valley Area | No | 2014 | 0 ¦ T.0010878 ¦ 0 ¦ 0 ¦ 0 ¦ 0 | Upgrade/Retrofit | Reliability | T-Line Capacity | 9.9 | NA | 70 | N/A | 2026-11-02 | 2019-05-01 | 2028-01-28 | Transmission Project Review Process data (Resolution E-5252 Attach B | 3194 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom! | Q1831, Q1959, Q1983, Q2010, Q2012, Q2013 | Q1831 | Q1959 | Q1983 | Q2010 | Q2012 | Q2013
Estrella Substation Project | 5805506 | T.0000154 | 61X | The C14P2-NFT01 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Estrella Sub in ? County, California. | Engineering more than 50% complete | 2019-05-01 |  |  | El Paso de Robles, San Luis Obispo | PG&E: North Valley Area | No | 2014 | 0 ¦ T.0010878 ¦ 0 ¦ 0 ¦ 0 ¦ 0 | Upgrade/Retrofit | Reliability | T-Line Capacity | N/A | 1.6272 | N/A | 70 kV | 2025-12-01 | 2019-05-01 | 2026-01-30 | Transmission Project Review Process data (Resolution E-5252 Attach B | 2466 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom! | Q1831, Q1959, Q1983, Q2010, Q2012, Q2013 | Q1831 | Q1959 | Q1983 | Q2010 | Q2012 | Q2013
Vierra 115 kV Looping Project | 5805561 | T.0000597 | 60W | The C14P2-NPT04 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Vierra 115kV in San Joaquin County, California. | Engineering more than 50% complete | 2023-01-24 |  |  | Lathrop, San Joaquin ¦ San Joaquin ¦ Tracy, San Joaquin | PG&E: North Valley Area | No | 2011 | T.0011086 ¦ T.0010853 ¦ 0 ¦ T.0011168 ¦ 0 | Upgrade/Retrofit | Reliability | T-Line Capacity | N/A | NA | 115 | N/A | 2025-10-01 | 2023-01-24 | 2025-10-07 | Transmission Project Review Process data (Resolution E-5252 Attach B | 987 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom! | Q1867, Q1887, Q1904, Q1920, Q1929 | Q1867 | Q1887 | Q1904 | Q1920 | Q1929
Estrella Substation Project | 5805698 | T.0000154 | 61N | The C14P2-NFT01 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Estrella Sub in ? County, California. | Engineering less than 50% complete | 2019-05-01 |  |  | San Luis Obispo | PG&E: North Valley Area | No | 2014 | 0 ¦ T.0010878 ¦ 0 ¦ 0 ¦ 0 ¦ 0 | Upgrade/Retrofit | Reliability | T-Line Capacity | N/A | 2.6839 | N/A | 230 kV | 2027-07-26 | 2019-05-01 | 2027-09-30 | Transmission Project Review Process data (Resolution E-5252 Attach B | 3074 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom! | Q1831, Q1959, Q1983, Q2010, Q2012, Q2013 | Q1831 | Q1959 | Q1983 | Q2010 | Q2012 | Q2013
Q1949 DARDEN (DA) SS OVERSIGHT | 5805801 | T.0009383 | 82Y | The Q1949 Darden Hybrid Solar Project from Cluster 14, proposes to interconnect a 1150 megawatt (MW) (net output) Solar + Battery generation facility to Los Banos-Midway 500kV #2 Line in Fresno County, California. The project has a contractual In-service date of: 2/28/31 with a current planned In-service date of: 11/18/30 | Engineering more than 50% complete | 2028-08-01 |  |  | Fresno | N/A | Yes | N/A | T.0010032 ¦ T.0008543 ¦ T.0001650 ¦ T.0009194 ¦ T.0010787 ¦ T.0010836 ¦ T.0004292 | New | Generator Interconnection | Generation Interconnection | N/A | 77.6619 | N/A | 500 kV | 2027-01-19 | 2031-02-28 | 2030-11-18 | Transmission Project Review Process data (Resolution E-5252 Attach B | -102 | No |  |  | N/A |  | N/A | N/A | CEC | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - Customer wants to move date forward. Earliest backfeed Q1, 2031 pending mitigations for Network Upgrades, C14P2-FGR04 - Los Banos 500 kV circuit breakers 822, 832 & 842 overstress, Q1 2031 ISD, C14P1-KGR11 - Midway 500 kV CB 742, 912, 942 Overstress beyond 50 kA Q1 2031 ISD. PG&E will uprate Midway breakers and Los Banos Breakers CB822 & 832 and must replacce CB842. Breaker ordered by Material Purchase Program. ISDs to be determined once design is complete. 04/08/25 - Tracking ISD to Q3 2030 with no current delays | Customer - Material | 1949 | 1949
Q1949 DARDEN (NU) SS OVERSIGHT | 5805802 | T.0009383 | 82W | The Q1949 Darden Hybrid Solar Project from Cluster 14, proposes to interconnect a 1150 megawatt (MW) (net output) Solar + Battery generation facility to Los Banos-Midway 500kV #2 Line in Fresno County, California. The project has a contractual In-service date of: 2/28/31 with a current planned In-service date of: 11/18/30 | Engineering less than 50% complete | 2028-08-01 |  |  | Fresno | N/A | Yes | N/A | T.0010032 ¦ T.0008543 ¦ T.0001650 ¦ T.0009194 ¦ T.0010787 ¦ T.0010836 ¦ T.0004292 | New | Generator Interconnection | Generation Interconnection | N/A | 77.6619 | N/A | 500 kV | 2028-10-20 | 2031-02-28 | 2030-11-18 | Transmission Project Review Process data (Resolution E-5252 Attach B | -102 | No |  |  | N/A |  | N/A | N/A | CEC | N/A | NOC |  | N/A [See Notes] |  | 05/06/25 - Customer wants to move date forward. Earliest backfeed Q1, 2031 pending mitigations for Network Upgrades, C14P2-FGR04 - Los Banos 500 kV circuit breakers 822, 832 & 842 overstress, Q1 2031 ISD, C14P1-KGR11 - Midway 500 kV CB 742, 912, 942 Overstress beyond 50 kA Q1 2031 ISD. PG&E will uprate Midway breakers and Los Banos Breakers CB822 & 832 and must replacce CB842. Breaker ordered by Material Purchase Program. ISDs to be determined once design is complete. 04/08/25 - Tracking ISD to Q3 2030 with no current delays | Customer - Material | 1949 | 1949
Q1949 DARDEN (NU) MIDWAY SUB DTT | 5805804 | T.0009383 | 82W | The Q1949 Darden Hybrid Solar Project from Cluster 14, proposes to interconnect a 1150 megawatt (MW) (net output) Solar + Battery generation facility to Los Banos-Midway 500kV #2 Line in Fresno County, California. The project has a contractual In-service date of: 2/28/31 with a current planned In-service date of: 11/18/30 | Engineering less than 50% complete | 2028-08-01 |  |  | Buttonwillow CDP, Kern | N/A | Yes | N/A | T.0010032 ¦ T.0008543 ¦ T.0001650 ¦ T.0009194 ¦ T.0010787 ¦ T.0010836 ¦ T.0004292 | New | Generator Interconnection | Special Protection Scheme | N/A | 94.5324 | N/A | 500 kV | 2029-08-15 | 2031-02-28 | 2030-11-18 | Transmission Project Review Process data (Resolution E-5252 Attach B | -102 | No |  |  | N/A |  | N/A | N/A | CEC | N/A | NOC |  | N/A [See Notes] |  | 05/06/25 - Customer wants to move date forward. Earliest backfeed Q1, 2031 pending mitigations for Network Upgrades, C14P2-FGR04 - Los Banos 500 kV circuit breakers 822, 832 & 842 overstress, Q1 2031 ISD, C14P1-KGR11 - Midway 500 kV CB 742, 912, 942 Overstress beyond 50 kA Q1 2031 ISD. PG&E will uprate Midway breakers and Los Banos Breakers CB822 & 832 and must replacce CB842. Breaker ordered by Material Purchase Program. ISDs to be determined once design is complete. 04/08/25 - Tracking ISD to Q3 2030 with no current delays | Customer - Material | 1949 | 1949
Q1949 DARDEN (NU LOS BANOS SUB DTT | 5805805 | T.0009383 | 82W | The Q1949 Darden Hybrid Solar Project from Cluster 14, proposes to interconnect a 1150 megawatt (MW) (net output) Solar + Battery generation facility to Los Banos-Midway 500kV #2 Line in Fresno County, California. The project has a contractual In-service date of: 2/28/31 with a current planned In-service date of: 11/18/30 | Planning | 2028-08-01 |  |  | Merced | N/A | Yes | N/A | T.0010032 ¦ T.0008543 ¦ T.0001650 ¦ T.0009194 ¦ T.0010787 ¦ T.0010836 ¦ T.0004292 | New | Generator Interconnection | Special Protection Scheme | N/A | 53.2803 | N/A | 500 kV | 2029-05-17 | 2031-02-28 | 2030-11-18 | Transmission Project Review Process data (Resolution E-5252 Attach B | -102 | No |  |  | N/A |  | N/A | N/A | CEC | N/A | NOC |  | N/A [See Notes] |  | 05/06/25 - Customer wants to move date forward. Earliest backfeed Q1, 2031 pending mitigations for Network Upgrades, C14P2-FGR04 - Los Banos 500 kV circuit breakers 822, 832 & 842 overstress, Q1 2031 ISD, C14P1-KGR11 - Midway 500 kV CB 742, 912, 942 Overstress beyond 50 kA Q1 2031 ISD. PG&E will uprate Midway breakers and Los Banos Breakers CB822 & 832 and must replacce CB842. Breaker ordered by Material Purchase Program. ISDs to be determined once design is complete. 04/08/25 - Tracking ISD to Q3 2030 with no current delays | Customer - Material | 1949 | 1949
Q1949 DARDEN (NU) GATES SUB | 5805806 | T.0009383 | 82W | The Q1949 Darden Hybrid Solar Project from Cluster 14, proposes to interconnect a 1150 megawatt (MW) (net output) Solar + Battery generation facility to Los Banos-Midway 500kV #2 Line in Fresno County, California. The project has a contractual In-service date of: 2/28/31 with a current planned In-service date of: 11/18/30 | Engineering less than 50% complete | 2028-08-01 |  |  | Fresno | N/A | Yes | N/A | T.0010032 ¦ T.0008543 ¦ T.0001650 ¦ T.0009194 ¦ T.0010787 ¦ T.0010836 ¦ T.0004292 | New | Generator Interconnection | Special Protection Scheme | N/A | 77.6619 | N/A | 500 kV | 2029-07-30 | 2031-02-28 | 2030-11-18 | Transmission Project Review Process data (Resolution E-5252 Attach B | -102 | No |  |  | N/A |  | N/A | N/A | CEC | N/A | NOC |  | N/A [See Notes] |  | 05/06/25 - Customer wants to move date forward. Earliest backfeed Q1, 2031 pending mitigations for Network Upgrades, C14P2-FGR04 - Los Banos 500 kV circuit breakers 822, 832 & 842 overstress, Q1 2031 ISD, C14P1-KGR11 - Midway 500 kV CB 742, 912, 942 Overstress beyond 50 kA Q1 2031 ISD. PG&E will uprate Midway breakers and Los Banos Breakers CB822 & 832 and must replacce CB842. Breaker ordered by Material Purchase Program. ISDs to be determined once design is complete. 04/08/25 - Tracking ISD to Q3 2030 with no current delays | Customer - Material | 1949 | 1949
Q1949 DARDEN (NU) OPGW T-LINE | 5805808 | T.0009383 | 82B | The Q1949 Darden Hybrid Solar Project from Cluster 14, proposes to interconnect a 1150 megawatt (MW) (net output) Solar + Battery generation facility to Los Banos-Midway 500kV #2 Line in Fresno County, California. The project has a contractual In-service date of: 2/28/31 with a current planned In-service date of: 11/18/30 | Engineering more than 50% complete | 2028-08-01 |  |  | Avenal, Kings ¦ Buttonwillow CDP, Kern ¦ Fresno ¦ Kern ¦ Kings ¦ Merced | N/A | Yes | N/A | T.0010032 ¦ T.0008543 ¦ T.0001650 ¦ T.0009194 ¦ T.0010787 ¦ T.0010836 ¦ T.0004292 | Upgrade/Retrofit | Generator Interconnection | Generation Interconnection | 104.5 | N/A | 500 | N/A | 2030-01-03 | 2031-02-28 | 2030-11-18 | Transmission Project Review Process data (Resolution E-5252 Attach B | -102 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | NOC |  | N/A [See Notes] |  | 05/06/25 - Customer wants to move date forward. Earliest backfeed Q1, 2031 pending mitigations for Network Upgrades, C14P2-FGR04 - Los Banos 500 kV circuit breakers 822, 832 & 842 overstress, Q1 2031 ISD, C14P1-KGR11 - Midway 500 kV CB 742, 912, 942 Overstress beyond 50 kA Q1 2031 ISD. PG&E will uprate Midway breakers and Los Banos Breakers CB822 & 832 and must replacce CB842. Breaker ordered by Material Purchase Program. ISDs to be determined once design is complete. 04/08/25 - Tracking ISD to Q3 2030 with no current delays | Customer - Material | 1949 | 1949
Moraga-Castro Valley 230 kV Line Capacity Increase | 5806178 | T.0004421 | 61C | The C11P2-GP01 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Moraga 230kV in Contra Costa County, California. | Construction (50%-75%) | 2013-05-01 |  |  | Orinda, Contra Costa | PG&E: North Valley Area | No | 2011 | T.0007418 ¦ T.0010478 | Upgrade/Retrofit | Reliability | T-Line Capacity | N/A | 5.428 | N/A | 230 kV | 2025-03-03 | 2013-05-01 | 2025-04-07 | Transmission Project Review Process data (Resolution E-5252 Attach B | 4359 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom! | Q1463, Q1691 | Q1463 | Q1691
Moraga-Castro Valley 230 kV Line Capacity Increase | 5806179 | T.0004421 | 61C | The C11P2-GP01 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Moraga 230kV in Contra Costa County, California. | Operational | 2013-05-01 |  |  | Fremont, Alameda | PG&E: North Valley Area | No | 2011 | T.0007418 ¦ T.0010478 | Upgrade/Retrofit | Reliability | T-Line Capacity | N/A | 5.43 | N/A | 230 kV | 2024-08-22 | 2013-05-01 | 2025-03-24 | Transmission Project Review Process data (Resolution E-5252 Attach B | 4345 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom! | Q1463, Q1691 | Q1463 | Q1691
Estrella Substation Project | 5806384 | T.0000154 | 60C | The C14P2-NFT01 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Estrella Sub in ? County, California. | Engineering more than 50% complete | 2019-05-01 |  |  | El Paso de Robles, San Luis Obispo ¦ San Luis Obispo ¦ San Miguel CDP, San Luis Obispo | PG&E: North Valley Area | No | 2014 | 0 ¦ T.0010878 ¦ 0 ¦ 0 ¦ 0 ¦ 0 | Upgrade/Retrofit | Reliability | T-Line Capacity | 9.9 | NA | 70 | N/A | 2027-08-16 | 2019-05-01 | 2029-03-30 | Transmission Project Review Process data (Resolution E-5252 Attach B | 3621 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom! | Q1831, Q1959, Q1983, Q2010, Q2012, Q2013 | Q1831 | Q1959 | Q1983 | Q2010 | Q2012 | Q2013
Cortina 230/115/60 kV Transformer Bank No. 1 Replacement Project | 5806847 | T.0009531 | 61Z | The C14P2-NPT01 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Cortina 230kV in Colusa County, California. | Engineering less than 50% complete | 2027-12-01 |  |  | Colusa | PG&E: North Valley Area | No | 2022 | 0 ¦ 0 ¦ 0 | Upgrade/Retrofit | Reliability | T-Line Capacity | N/A | 6.7436 | N/A | 230 ¦ 115 ¦ 60 kV | 2027-07-09 | 2027-12-01 | 2027-10-12 | Transmission Project Review Process data (Resolution E-5252 Attach B | -50 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom! | Q1837, Q1838, Q1846 | Q1837 | Q1838 | Q1846
Los Banos 230 kV circuit breakers 212 & 222 overstress | 5806918 | T.0009550 | 61W | The C14P2-FPN03 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Los Banos 230kV in Merced County, California. | Engineering more than 50% complete | 2032-12-31 |  |  | Merced | PG&E: North Valley Area | No | 2023 | TBD ¦ 0 ¦ T.0011060 ¦ T.0011131 ¦ 0 | Upgrade/Retrofit | Reliability | T-Line Capacity | N/A | 53.2803 | N/A | 230 kV | 2025-05-19 | 2032-12-31 | 2026-06-01 | Transmission Project Review Process data (Resolution E-5252 Attach B | -2405 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom! | Q1903, Q1943, Q1952, Q1958, Q1960 | Q1903 | Q1943 | Q1952 | Q1958 | Q1960
Los Banos 230 kV circuit breakers 212 & 222 overstress | 5806919 | T.0009550 | 61W | The C14P2-FPN03 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Los Banos 230kV in Merced County, California. | Construction (under 10%) | 2032-12-31 |  |  | Merced | PG&E: North Valley Area | No | 2023 | TBD ¦ 0 ¦ T.0011060 ¦ T.0011131 ¦ 0 | Upgrade/Retrofit | Reliability | T-Line Capacity | N/A | 53.2803 | N/A | 230 kV | 2025-02-25 | 2032-12-31 | 2025-07-07 | Transmission Project Review Process data (Resolution E-5252 Attach B | -2734 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom! | Q1903, Q1943, Q1952, Q1958, Q1960 | Q1903 | Q1943 | Q1952 | Q1958 | Q1960
Oro Loma 70 kV Reinforcement | 5807500 | T.0009617 | 60Z | The C13P1-FPT03 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Oro Loma Substation 70kV Bus in Fresno County, California. | Planning | 2029-12-31 |  |  | Merced | PG&E: North Valley Area | No | 2023 | T.0009846 | New | Reliability | T-Line Capacity | 1 | 53.2803 | 70 | N/A | 2028-04-14 | 2029-12-31 | 2029-07-18 | Transmission Project Review Process data (Resolution E-5252 Attach B | -166 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom!
Oro Loma 70 kV Reinforcement | 5807501 | T.0009617 | 61Z | The C13P1-FPT03 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Oro Loma Substation 70kV Bus in Fresno County, California. | Planning | 2029-12-31 |  |  | Merced | PG&E: North Valley Area | No | 2023 | T.0009846 | New | Reliability | T-Line Capacity | N/A | 2.8847 | N/A | 70 kV | 2028-09-21 | 2029-12-31 | 2030-10-11 | Transmission Project Review Process data (Resolution E-5252 Attach B | 284 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom! | #N/A
Oro Loma 70 kV Reinforcement | 5807502 | T.0009617 | 61X | The C13P1-FPT03 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Oro Loma Substation 70kV Bus in Fresno County, California. | Planning | 2029-12-31 |  |  | Merced | PG&E: North Valley Area | No | 2023 | T.0009846 | New | Reliability | T-Line Capacity | N/A | 53.2803 | N/A | 230 ¦ 70 kV | 2028-03-09 | 2029-12-31 | 2028-07-24 | Transmission Project Review Process data (Resolution E-5252 Attach B | -525 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom! | #N/A
Borden-Storey 230 kV 1 and 2 Line Reconductoring | 5807523 | T.0009662 | 60X | The C14P2-NFT04 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Borden-Storey 230kV 1 and 2 Line in Madera County, California. | Engineering less than 50% complete | 2032-12-31 |  |  | Chowchilla, Madera ¦ Madera ¦ Madera Acres CDP, Madera ¦ Merced ¦ Merced, Merced ¦ Parksdale CDP, Madera | PG&E: North Valley Area | No | 2023 | T.0010817 ¦ 0 ¦ 0 ¦ T.0010942 ¦ 0 ¦ T.0010738 ¦ 0 ¦ 0 | Upgrade/Retrofit | Policy | T-Line Capacity | 10 | NA | 230 | N/A | 2028-11-06 | 2032-12-31 | 2029-05-08 | Transmission Project Review Process data (Resolution E-5252 Attach B | -1333 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom! | Q1930, Q1933, Q1934, Q1935, Q1953, Q1956, Q1966, Q1975 | Q1930 | Q1933 | Q1934 | Q1935 | Q1953 | Q1956 | Q1966 | Q1975
Borden-Storey 230 kV 1 and 2 Line Reconductoring | 5807524 | T.0009662 | 61X | The C14P2-NFT04 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Borden-Storey 230kV 1 and 2 Line in Madera County, California. | Planning | 2032-12-31 |  |  | Chowchilla, Madera ¦ Madera ¦ Madera Acres CDP, Madera ¦ Merced ¦ Merced, Merced ¦ Parksdale CDP, Madera | PG&E: North Valley Area | No | 2023 | T.0010817 ¦ 0 ¦ 0 ¦ T.0010942 ¦ 0 ¦ T.0010738 ¦ 0 ¦ 0 | Upgrade/Retrofit | Policy | T-Line Capacity | N/A | NA | N/A | 230 kV | 2028-01-27 | 2032-12-31 | 2028-03-09 | Transmission Project Review Process data (Resolution E-5252 Attach B | -1758 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom! | Q1930, Q1933, Q1934, Q1935, Q1953, Q1956, Q1966, Q1975 | Q1930 | Q1933 | Q1934 | Q1935 | Q1953 | Q1956 | Q1966 | Q1975
Q1728_ZETA_TLINE (DA) | 5807927 | T.0009846 | 82D | The Q1728 Zeta Project from Cluster 13, proposes to interconnect a 75 megawatt (MW) (net output) Solar + Battery generation facility to Mercy Springs SW 70kV in Merced County, California. The project has a contractual In-service date of: 3/9/27 with a current planned In-service date of: 5/26/27 | Engineering less than 50% complete | 2027-03-09 |  |  | Fresno ¦ Los Banos, Merced ¦ Merced | N/A | Yes | N/A | T.0003009 ¦ T.0000157 | New | Generator Interconnection | Generation Interconnection | 0.25 | NA | 70 | N/A | 2027-03-01 | 2027-03-09 | 2027-03-09 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - Tracking ISD Q2 2027. Potential Impact due to TPP PNU Oro Loma 70kV Reinforcement dependency with Q1 2028 ISD. | -
Q1728 - ZETA - MERCY SPRINGS (NU) | 5807928 | T.0009846 | 82W | The Q1728 Zeta Project from Cluster 13, proposes to interconnect a 75 megawatt (MW) (net output) Solar + Battery generation facility to Mercy Springs SW 70kV in Merced County, California. The project has a contractual In-service date of: 3/9/27 with a current planned In-service date of: 5/26/27 | Engineering more than 50% complete | 2027-03-09 |  |  | Merced | N/A | Yes | N/A | T.0003009 ¦ T.0000157 | New | Generator Interconnection | Generation Interconnection | N/A | N/A | N/A | 70 kV | 2026-04-01 | 2027-03-09 | 2027-03-09 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - Tracking ISD Q2 2027. Potential Impact due to TPP PNU Oro Loma 70kV Reinforcement dependency with Q1 2028 ISD. | - | 1728 | 1728
Q1728- ZETA-GENSITE (DA) | 5807963 | T.0009846 | 82Y | The Q1728 Zeta Project from Cluster 13, proposes to interconnect a 75 megawatt (MW) (net output) Solar + Battery generation facility to Mercy Springs SW 70kV in Merced County, California. The project has a contractual In-service date of: 3/9/27 with a current planned In-service date of: 5/26/27 | Engineering less than 50% complete | 2027-03-09 |  |  | Merced | N/A | Yes | N/A | T.0003009 ¦ T.0000157 | New | Generator Interconnection | Generation Interconnection | N/A | N/A | N/A | 70 kV | 2026-06-12 | 2027-03-09 | 2027-03-09 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - Tracking ISD Q2 2027. Potential Impact due to TPP PNU Oro Loma 70kV Reinforcement dependency with Q1 2028 ISD. | - | 1728 | 1728
Q1728- ZETA-MERCY SPRINGS (DA) | 5807964 | T.0009846 | 82Y | The Q1728 Zeta Project from Cluster 13, proposes to interconnect a 75 megawatt (MW) (net output) Solar + Battery generation facility to Mercy Springs SW 70kV in Merced County, California. The project has a contractual In-service date of: 3/9/27 with a current planned In-service date of: 5/26/27 | Engineering more than 50% complete | 2027-03-09 |  |  | Merced | N/A | Yes | N/A | T.0003009 ¦ T.0000157 | New | Generator Interconnection | Generation Interconnection | N/A | N/A | N/A | 70 kV | 2025-08-01 | 2027-03-09 | 2027-03-09 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - Tracking ISD Q2 2027. Potential Impact due to TPP PNU Oro Loma 70kV Reinforcement dependency with Q1 2028 ISD. | - | 1728 | 1728
Q1223-DAYLIGHT-MUSTANG SS DA | 5808244 | T.0009863 | 82Y | The Q1223 Daylight Project Project from Cluster 9, proposes to interconnect a 300 megawatt (MW) (net output) Solar + Battery generation facility to Mustang SW 230kV in Kings County, California. The project has a contractual In-service date of: 11/19/27 with a current planned In-service date of: 12/23/27 | Engineering less than 50% complete | 2027-11-19 |  |  | Fresno | N/A | Yes | N/A | T.0007289 ¦ T.0006452 | New | Generator Interconnection | Generation Interconnection | N/A | 77.6619 | N/A | 230 kV | 2027-05-26 | 2027-11-19 | 2027-11-19 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - Tracking ISD to Q3 2027 | - | 1223 | 1223
Q1223-DAYLIGHT-GEN SITE DA | 5808245 | T.0009863 | 82Y | The Q1223 Daylight Project Project from Cluster 9, proposes to interconnect a 300 megawatt (MW) (net output) Solar + Battery generation facility to Mustang SW 230kV in Kings County, California. The project has a contractual In-service date of: 11/19/27 with a current planned In-service date of: 12/23/27 | Planning | 2027-11-19 |  |  | Fresno | N/A | Yes | N/A | T.0007289 ¦ T.0006452 | New | Generator Interconnection | Generation Interconnection | N/A | 77.6619 | N/A | 230 kV | 2027-05-26 | 2027-11-19 | 2027-11-19 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - Tracking ISD to Q3 2027 | - | 1223 | 1223
Q1223-DAYLIGHT-T-LINE DA | 5808246 | T.0009863 | 82D | The Q1223 Daylight Project Project from Cluster 9, proposes to interconnect a 300 megawatt (MW) (net output) Solar + Battery generation facility to Mustang SW 230kV in Kings County, California. The project has a contractual In-service date of: 11/19/27 with a current planned In-service date of: 12/23/27 | Planning | 2027-11-19 |  |  | Fresno ¦ Kings | N/A | Yes | N/A | T.0007289 ¦ T.0006452 | New | Generator Interconnection | Generation Interconnection | 4.15 | NA | 230 | N/A | 2027-11-23 | 2027-11-19 | 2027-11-19 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - Tracking ISD to Q3 2027 | - | 1223 | 1223
Q1223-DAYLIGHT- MUSTANG SS RNU | 5808247 | T.0009863 | 82W | The Q1223 Daylight Project Project from Cluster 9, proposes to interconnect a 300 megawatt (MW) (net output) Solar + Battery generation facility to Mustang SW 230kV in Kings County, California. The project has a contractual In-service date of: 11/19/27 with a current planned In-service date of: 12/23/27 | Engineering less than 50% complete | 2027-11-19 |  |  | Fresno | N/A | Yes | N/A | T.0007289 ¦ T.0006452 | New | Generator Interconnection | Generation Interconnection | N/A | 77.6619 | N/A | 230 kV | 2027-05-26 | 2027-11-19 | 2027-11-19 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - Tracking ISD to Q3 2027 | - | 1223 | 1223
Q1223-DAYLIGHT- GATES 230 KV OM RNU | 5808278 | T.0009863 | 82W | The Q1223 Daylight Project Project from Cluster 9, proposes to interconnect a 300 megawatt (MW) (net output) Solar + Battery generation facility to Mustang SW 230kV in Kings County, California. The project has a contractual In-service date of: 11/19/27 with a current planned In-service date of: 12/23/27 | Construction (50%-75%) | 2023-12-31 |  |  | N/A | N/A | No | N/A | T.0007289 ¦ T.0006452 | Upgrade/Retrofit | Other [See Notes] | Special Protection Scheme | N/A | NA | N/A | N/A | 2024-05-30 | 2027-11-19 | 2027-11-19 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - Tracking ISD to Q3 2027 | - | 1223 | 1223
Stanislaus-Melones Sw Sta-Manteca #1 115 kV Line Reconductor | 5808393 | T.0004301 | 93C | The C12P2-LDNU2 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Stanislaus-Melones Sw Sta-Manteca #1 115kV Line in San Joaquin County, California. | Engineering more than 50% complete | 2030-05-01 |  |  | Angels, Calaveras ¦ Calaveras ¦ Copperopolis CDP, Calaveras ¦ Stanislaus ¦ Tuolumne ¦ Vallecito CDP, Calaveras | 0 | No | N/A | T.0007445 ¦ 0 | Replace | Asset Condition | T-Line Capacity | 9.7 | NA | 115 | N/A | 2026-10-09 | 2030-05-01 | 2026-12-11 | Transmission Project Review Process data (Resolution E-5252 Attach B | -1237 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom! | Q1557, Q1904 | Q1557 | Q1904
Stanislaus-Melones Sw Sta-Manteca #1 115 kV Line Reconductor | 5808394 | T.0004301 | 93C | The C12P2-LDNU2 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Stanislaus-Melones Sw Sta-Manteca #1 115kV Line in San Joaquin County, California. | Engineering more than 50% complete | 2030-05-01 |  |  | Angels, Calaveras ¦ Calaveras ¦ Copperopolis CDP, Calaveras ¦ Stanislaus ¦ Tuolumne ¦ Vallecito CDP, Calaveras | 0 | No | N/A | T.0007445 ¦ 0 | Replace | Asset Condition | T-Line Capacity | 7.7 | NA | 115 | N/A | 2028-08-10 | 2030-05-01 | 2029-02-01 | Transmission Project Review Process data (Resolution E-5252 Attach B | -454 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom! | Q1557, Q1904 | Q1557 | Q1904
Stanislaus-Melones Sw Sta-Manteca #1 115 kV Line Reconductor | 5808441 | T.0004301 | 93C | The C12P2-LDNU2 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Stanislaus-Melones Sw Sta-Manteca #1 115kV Line in San Joaquin County, California. | Engineering more than 50% complete | 2030-05-01 |  |  | Angels, Calaveras ¦ Calaveras ¦ Copperopolis CDP, Calaveras ¦ Manteca, San Joaquin ¦ Murphys CDP, Calaveras ¦ San Joaquin ¦ Stanislaus ¦ Tuolumne ¦ Vallecito CDP, Calaveras | 0 | No | N/A | T.0007445 ¦ 0 | Replace | Asset Condition | T-Line Capacity | 19.4 | NA | 115 | N/A | 2026-11-10 | 2030-05-01 | 2026-12-01 | Transmission Project Review Process data (Resolution E-5252 Attach B | -1247 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom! | Q1557, Q1904 | Q1557 | Q1904
Stanislaus-Melones Sw Sta-Manteca #1 115 kV Line Reconductor | 5808442 | T.0004301 | 93C | The C12P2-LDNU2 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Stanislaus-Melones Sw Sta-Manteca #1 115kV Line in San Joaquin County, California. | Planning | 2030-05-01 |  |  | Angels, Calaveras ¦ Calaveras ¦ Copperopolis CDP, Calaveras ¦ Manteca, San Joaquin ¦ Murphys CDP, Calaveras ¦ San Joaquin ¦ Stanislaus ¦ Tuolumne ¦ Vallecito CDP, Calaveras | 0 | No | N/A | T.0007445 ¦ 0 | Replace | Asset Condition | T-Line Capacity | 15.4 | NA | 115 | N/A | 2028-09-01 | 2030-05-01 | 2028-09-22 | Transmission Project Review Process data (Resolution E-5252 Attach B | -586 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom! | Q1557, Q1904 | Q1557 | Q1904
Q1379 HEARTLAND SOLAR 1 (DA) TRANQUILITY | 5808498 | T.0009923 | 82Y | The Q1379 Heartland 1 Project from Cluster 10, proposes to interconnect a 150 megawatt (MW) (net output) Solar generation facility to Tranquility SW 230kV in Fresno County, California. The project has a contractual In-service date of: 4/30/28 with a current planned In-service date of: 11/7/28 | Engineering less than 50% complete | 2028-04-30 |  |  | Fresno | N/A | Yes | N/A | T.0006452 | New | Generator Interconnection | Generation Interconnection | N/A | 19.3832 | N/A | 230 kV | 2027-12-08 | 2028-04-30 | 2028-04-30 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - Tracking ISD to Q3/Q4 2028. LLM (CBs) in July 2026. The IC team is still in beginning stages of design. | Utility - Bundling Dependencies | 1379 | 1379
Q1379 HEARTLAND SOLAR 1 (DA) GEN-SITE | 5808499 | T.0009923 | 82Y | The Q1379 Heartland 1 Project from Cluster 10, proposes to interconnect a 150 megawatt (MW) (net output) Solar generation facility to Tranquility SW 230kV in Fresno County, California. The project has a contractual In-service date of: 4/30/28 with a current planned In-service date of: 11/7/28 | Planning | 2028-04-30 |  |  | Fresno | N/A | Yes | N/A | T.0006452 | New | Generator Interconnection | Generation Interconnection | N/A | 19.3832 | N/A | 230 kV | 2028-03-22 | 2028-04-30 | 2028-04-30 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - Tracking ISD to Q3/Q4 2028. LLM (CBs) in July 2026. The IC team is still in beginning stages of design. | Utility - Bundling Dependencies | 1379 | 1379
Q1379 HEARTLAND SOLAR 1 (DA) T-LINE | 5808500 | T.0009923 | 82Y | The Q1379 Heartland 1 Project from Cluster 10, proposes to interconnect a 150 megawatt (MW) (net output) Solar generation facility to Tranquility SW 230kV in Fresno County, California. The project has a contractual In-service date of: 4/30/28 with a current planned In-service date of: 11/7/28 | Planning | 2028-04-30 |  |  | Fresno ¦ San Joaquin, Fresno | N/A | Yes | N/A | T.0006452 | New | Generator Interconnection | Generation Interconnection | 1.96 | N/A | 230 | N/A | 2028-05-24 | 2028-04-30 | 2028-04-30 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - Tracking ISD to Q3/Q4 2028. LLM (CBs) in July 2026. The IC team is still in beginning stages of design. | Utility - Bundling Dependencies | 1379 | 1379
Q1380 HEARTLAND (DA) GEN-SITE | 5808518 | T.0009924 | 82Y | The Q1380 Heartland 2 Project from Cluster 10, proposes to interconnect a 150 megawatt (MW) (net output) Solar generation facility to Tranquility SW 230kV in Fresno County, California. The project has a contractual In-service date of: 4/30/28 with a current planned In-service date of: 10/25/28 | Planning | 2027-04-30 |  |  | Fresno | N/A | Yes | N/A | T.0006452 | New | Generator Interconnection | Generation Interconnection | N/A | N/A | N/A | 230 kV | 2028-03-22 | 2028-04-30 | 2028-04-30 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - Tracking ISD to Q3/Q4 2028. LLM (CBs) in July 2026. The IC team is still in beginning stages of design. | Utility - Material | 1380 | 1380
Panoche 115 kV CB 102 overstress upgrade | 5808684 | T.0009194 | 61G | The 22rsmt-1 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Panoche 115 kV bus in Fresno County, California. | Engineering more than 50% complete | 2028-01-01 |  |  | Fresno | PG&E: North Valley Area | No | 2023 | TBD ¦ T.0010887 | Upgrade/Retrofit | Reliability | T-Line Capacity | N/A | 19.3832 | N/A | 230 kV | 2027-03-08 | 2028-01-01 | 2028-04-04 | Transmission Project Review Process data (Resolution E-5252 Attach B | 94 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom! | Q1940, Q1955 | Q1940 | Q1955
Stanislaus-Melones Sw STA-Riverbank Jct Sw Sta 115 kV Line Reconductor | 5809024 | T.0004515 | 66A | The C12P2-LDNU4 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Stanislaus-Melones SW STA-Riverbank Jct Sw Sta 115kV Line in San Joaquin County, California. | Planning | N/A |  |  | Tuolumne | PG&E: North Valley Area | No | N/A | T.0007445 | Upgrade/Retrofit | Reliability | T-Line Capacity | N/A | 0.85823 | N/A | 115 kV | 2028-12-20 | 2026-01-29 | 2029-01-19 | Transmission Project Review Process data (Resolution E-5252 Attach B | 1086 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom! | Q1557 | Q1557
Q1744- CRYSTAL FLATS- LAMONT SS IRNU | 5809025 | T.0010025 | 82W | The Q1744 Crystal Flats Project from Cluster 13, proposes to interconnect a 100 megawatt (MW) (net output) Solar + Battery generation facility to Lamont 115kV in Kern County, California. The project has a contractual In-service date of: 10/12/30 with a current planned In-service date of: 10/12/30 | Engineering more than 50% complete | 2028-01-01 |  |  | Fresno | N/A | No | 2022 | T.0003009 ¦ Maintenance ¦ T.0001650 ¦ T.0004292 ¦ T.0006452 ¦ T.0010032 ¦ T.0010031 ¦ T.0007722 ¦ Maintenance | Upgrade/Retrofit | Policy | Substation Capacity | N/A | 77.6619 | N/A | 500 kV | 2026-04-29 | 2030-10-12 | 2030-10-12 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - IC non-responsive to meetings. ISD shown is IA ISD. Real ISD TBD. | Customer - Non-Responsive | 1744 | 1744
Panoche 115 kV CB 102 overstress upgrade | 5809028 | T.0009194 | 61C | The 22rsmt-1 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Panoche 115 kV bus in Fresno County, California. | Engineering more than 50% complete | 2028-01-01 |  |  | Fresno | PG&E: North Valley Area | No | 2022 | TBD ¦ T.0010887 | Upgrade/Retrofit | Policy | T-Line Capacity | N/A | 77.6619 | N/A | 500 kV | 2026-04-29 | 2028-01-01 | 2028-04-28 | Transmission Project Review Process data (Resolution E-5252 Attach B | 118 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom! | Q1940, Q1955 | Q1940 | Q1955
Q1744-CRYSTAL FLATS-LAMONT SS DA | 5809038 | T.0010025 | 82Y | The Q1744 Crystal Flats Project from Cluster 13, proposes to interconnect a 100 megawatt (MW) (net output) Solar + Battery generation facility to Lamont 115kV in Kern County, California. The project has a contractual In-service date of: 10/12/30 with a current planned In-service date of: 10/12/30 | Engineering less than 50% complete | N/A |  |  | Fulton CDP, Sonoma | N/A | No | N/A | T.0003009 ¦ Maintenance ¦ T.0001650 ¦ T.0004292 ¦ T.0006452 ¦ T.0010032 ¦ T.0010031 ¦ T.0007722 ¦ Maintenance | New | Load Growth | Substation Capacity | N/A | N/A | N/A | 230 kV | 2026-12-01 | 2030-10-12 | 2030-10-12 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - IC non-responsive to meetings. ISD shown is IA ISD. Real ISD TBD. | Customer - Non-Responsive | 1744 | 1744
Q1744-CRYSTAL FLATS -GEN SITE DA | 5809039 | T.0010025 | 82Y | The Q1744 Crystal Flats Project from Cluster 13, proposes to interconnect a 100 megawatt (MW) (net output) Solar + Battery generation facility to Lamont 115kV in Kern County, California. The project has a contractual In-service date of: 10/12/30 with a current planned In-service date of: 10/12/30 | Engineering less than 50% complete | N/A |  |  | Fulton CDP, Sonoma | N/A | No | N/A | T.0003009 ¦ Maintenance ¦ T.0001650 ¦ T.0004292 ¦ T.0006452 ¦ T.0010032 ¦ T.0010031 ¦ T.0007722 ¦ Maintenance | New | Load Growth | Substation Capacity | N/A | N/A | N/A | 230 kV | 2026-12-01 | 2030-10-12 | 2030-10-12 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - IC non-responsive to meetings. ISD shown is IA ISD. Real ISD TBD. | Customer - Non-Responsive | 1744 | 1744
Q1744-CRYSTAL FLATS-T-LINE DA | 5809045 | T.0010025 | 82D | The Q1744 Crystal Flats Project from Cluster 13, proposes to interconnect a 100 megawatt (MW) (net output) Solar + Battery generation facility to Lamont 115kV in Kern County, California. The project has a contractual In-service date of: 10/12/30 with a current planned In-service date of: 10/12/30 | Engineering less than 50% complete | N/A |  |  | Menlo Park, San Mateo | N/A | No | N/A | T.0003009 ¦ Maintenance ¦ T.0001650 ¦ T.0004292 ¦ T.0006452 ¦ T.0010032 ¦ T.0010031 ¦ T.0007722 ¦ Maintenance | New | Work Requested by Others | Load Interconnection | N/A | N/A | N/A | 115 kV | 2027-01-13 | 2030-10-12 | 2030-10-12 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - IC non-responsive to meetings. ISD shown is IA ISD. Real ISD TBD. | Customer - Non-Responsive | 1744 | 1744
MIDWAY 500 KV RAS C13P1-KGR01 NU | 5809123 | T.0010031 | 82W | The C13P1-KGR01 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Midway 500kV/230kV in Kern County, California. | Engineering less than 50% complete | N/A |  |  | Menlo Park, San Mateo | N/A | Yes | N/A | 0 ¦ T.0010479 ¦ 0 ¦ T.0010025 ¦ 0 ¦ T.0010519 ¦ 0 ¦ T.0010878 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 | New | Work Requested by Others | Special Protection Scheme | N/A | 11.3472 | N/A | 115 kV | 2027-01-13 | 2030-10-12 | 2027-03-04 | Transmission Project Review Process data (Resolution E-5252 Attach B | -1318 | No |  |  | N/A |  | TBD | TBD | TBD | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom! | Q1736, Q1739, Q1740, Q1744, Q1749, Q1751, Q1831, Q1959, Q1968, Q1980, Q1983, Q1992, Q1994, Q1995, Q2001, Q2004, Q2006, Q2010, Q2012, Q2013, Q2015, Q2017 | Q1736 | Q1739 | Q1740 | Q1744 | Q1749 | Q1751 | Q1831 | Q1959 | Q1968 | Q1980 | Q1983 | Q1992 | Q1994 | Q1995 | Q2001 | Q2004 | Q2006 | Q2010 | Q2012
MIDWAY 230KVBUSD-E BUSRCTRSC13P1KGR05NU | 5809124 | T.0010032 | 82W | The C13P1-KGR05 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Midway 230kV in Kern County, California. | Engineering less than 50% complete | N/A |  |  | Menlo Park, San Mateo | N/A | Yes | N/A | T.0010479 ¦ T.0010025 ¦ 0 ¦ T.0010519 ¦ T.0009383 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 | New | Work Requested by Others | Substation Capacity | N/A | 11.3472 | N/A | 115 kV | 2027-01-13 | 2030-10-12 | 2027-03-04 | Transmission Project Review Process data (Resolution E-5252 Attach B | -1318 | No |  |  | N/A |  | TBD | TBD | TBD | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom! | Q1739, Q1744, Q1749, Q1751, Q1949, Q1980, Q1983, Q1987, Q1995, Q2001, Q2004, Q2006, Q2010, Q2013, Q2015 | Q1739 | Q1744 | Q1749 | Q1751 | Q1949 | Q1980 | Q1983 | Q1987 | Q1995 | Q2001 | Q2004 | Q2006 | Q2010 | Q2013 | Q2015
TRANQLTY SS 230KV BAAH 2CB_Q1379 Q1380 | 5809203 | T.0009923 | 82W | The Q1379 Heartland 1 Project from Cluster 10, proposes to interconnect a 150 megawatt (MW) (net output) Solar generation facility to Tranquility SW 230kV in Fresno County, California. The project has a contractual In-service date of: 4/30/28 with a current planned In-service date of: 11/7/28 | Engineering less than 50% complete | 2028-04-30 |  |  | Fresno | N/A | Yes | N/A | T.0006452 | New | Generator Interconnection | Generation Interconnection | N/A | 19.3832 | N/A | 230 kV | 2028-02-16 | 2028-04-30 | 2028-04-30 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - Tracking ISD to Q3/Q4 2028. LLM (CBs) in July 2026. The IC team is still in beginning stages of design. | Utility - Bundling Dependencies | 1379 | 1379
Panoche 115 kV CB 102 overstress upgrade | 5809623 | T.0009194 | 60X | The 22rsmt-1 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Panoche 115 kV bus in Fresno County, California. | Engineering more than 50% complete | 2028-01-01 |  |  | Fresno | PG&E: North Valley Area | No | 2022 | TBD ¦ T.0010887 | Upgrade/Retrofit | Policy | T-Line Capacity | TBD | NA | 500 | N/A | 2027-04-30 | 2028-01-01 | 2027-05-06 | Transmission Project Review Process data (Resolution E-5252 Attach B | -240 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom! | Q1940, Q1955 | Q1940 | Q1955
Panoche 115 kV CB 102 overstress upgrade | 5809639 | T.0009194 | 60X | The 22rsmt-1 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Panoche 115 kV bus in Fresno County, California. | Engineering more than 50% complete | 2028-01-01 |  |  | Fresno | PG&E: North Valley Area | No | 2022 | TBD ¦ T.0010887 | Upgrade/Retrofit | Policy | T-Line Capacity | 87.2 | NA | 500 | N/A | 2026-06-22 | 2028-01-01 | 2027-03-19 | Transmission Project Review Process data (Resolution E-5252 Attach B | -288 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom! | Q1940, Q1955 | Q1940 | Q1955
Panoche 115 kV CB 102 overstress upgrade | 5809640 | T.0009194 | 60X | The 22rsmt-1 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Panoche 115 kV bus in Fresno County, California. | Engineering less than 50% complete | 2028-01-01 |  |  | Fresno | PG&E: North Valley Area | No | 2022 | TBD ¦ T.0010887 | New | Policy | T-Line Capacity | TBD | NA | 500 | N/A | 2027-09-17 | 2028-01-01 | 2028-04-06 | Transmission Project Review Process data (Resolution E-5252 Attach B | 96 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom! | Q1940, Q1955 | Q1940 | Q1955
Panoche 115 kV CB 102 overstress upgrade | 5809641 | T.0009194 | 60X | The 22rsmt-1 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Panoche 115 kV bus in Fresno County, California. | Engineering less than 50% complete | 2028-01-01 |  |  | Fresno | PG&E: North Valley Area | No | 2022 | TBD ¦ T.0010887 | Upgrade/Retrofit | Policy | T-Line Capacity | 57 | NA | 115 | N/A | 2026-06-01 | 2028-01-01 | 2026-11-17 | Transmission Project Review Process data (Resolution E-5252 Attach B | -410 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom! | Q1940, Q1955 | Q1940 | Q1955
Panoche 115 kV CB 102 overstress upgrade | 5809978 | T.0009194 | 61C | The 22rsmt-1 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Panoche 115 kV bus in Fresno County, California. | Engineering more than 50% complete | 2028-01-01 |  |  | San Benito | PG&E: North Valley Area | No | 2022 | TBD ¦ T.0010887 | Upgrade/Retrofit | Policy | T-Line Capacity | N/A | 6.0534 | N/A | 500 kV | 2027-02-05 | 2028-01-01 | 2028-04-03 | Transmission Project Review Process data (Resolution E-5252 Attach B | 93 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom! | Q1940, Q1955 | Q1940 | Q1955
Panoche 115 kV CB 102 overstress upgrade | 5809979 | T.0009194 | 61C | The 22rsmt-1 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Panoche 115 kV bus in Fresno County, California. | Engineering more than 50% complete | 2028-01-01 |  |  | Fresno | PG&E: North Valley Area | No | 2022 | TBD ¦ T.0010887 | Upgrade/Retrofit | Policy | T-Line Capacity | N/A | 19.3832 | N/A | 500 kV | 2027-03-05 | 2028-01-01 | 2028-04-03 | Transmission Project Review Process data (Resolution E-5252 Attach B | 93 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom! | Q1940, Q1955 | Q1940 | Q1955
Cortina 230/115/60 kV Transformer Bank No. 1 Replacement Project | 5810077 | T.0009531 | 60Y | The C14P2-NPT01 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Cortina 230kV in Colusa County, California. | Engineering less than 50% complete | 2027-12-01 |  |  | Clearlake Oaks CDP, Lake ¦ Colusa ¦ Lake ¦ Lucerne CDP, Lake ¦ Mendocino ¦ Nice CDP, Lake | PG&E: North Valley Area | No | 2022 | 0 ¦ 0 ¦ 0 | Upgrade/Retrofit | Reliability | T-Line Capacity | N/A | NA | 230 ¦ 115 ¦ 60 | N/A | 2027-02-22 | 2027-12-01 | 2027-08-11 | Transmission Project Review Process data (Resolution E-5252 Attach B | -112 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom!
Cortina 230/115/60 kV Transformer Bank No. 1 Replacement Project | 5810098 | T.0009531 | 61Z | The C14P2-NPT01 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Cortina 230kV in Colusa County, California. | Engineering less than 50% complete | 2027-12-01 |  |  | Colusa | PG&E: North Valley Area | No | 2022 | 0 ¦ 0 ¦ 0 | Upgrade/Retrofit | Reliability | T-Line Capacity | N/A | 6.7436 | N/A | 230 ¦ 115 ¦ 60 kV | 2027-03-29 | 2027-12-01 | 2027-04-22 | Transmission Project Review Process data (Resolution E-5252 Attach B | -223 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom! | Q1837, Q1838, Q1846 | Q1837 | Q1838 | Q1846
Estrella Substation Project | 5810240 | T.0000154 | 60X | The C14P2-NFT01 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Estrella Sub in ? County, California. | Engineering more than 50% complete | 2019-05-01 |  |  | El Paso de Robles, San Luis Obispo ¦ San Luis Obispo ¦ San Miguel CDP, San Luis Obispo | PG&E: North Valley Area | No | 2014 | 0 ¦ T.0010878 ¦ 0 ¦ 0 ¦ 0 ¦ 0 | Upgrade/Retrofit | Reliability | T-Line Capacity | 5 | NA | 70 | N/A | 2026-11-02 | 2019-05-01 | 2027-12-29 | Transmission Project Review Process data (Resolution E-5252 Attach B | 3164 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom!
Vaca Dixon Substation 230 kV Circuit Breakers 442, 452 and 462 overstress | 5810426 | T.0001609 | 64C | The C12P1-NPT04 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Vaca Dixon Substation 230kV in Solano County, California. | Engineering more than 50% complete | 2027-03-01 |  |  | Solano | PG&E: North Valley Area | No | N/A | T.0007195 ¦ T.0010478 ¦ T.0007418 ¦ T.0008063 ¦ T.0008218 ¦ T.0008918 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 | Replace | Asset Condition | T-Line Capacity | N/A | 42.1076 | N/A | 230 kV | 2027-08-19 | 2027-03-01 | 2027-09-28 | Transmission Project Review Process data (Resolution E-5252 Attach B | 211 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom! | Q1270, Q1691, Q1463, Q1496, Q1444, Q1702, Q1837, Q1838, Q1840, Q1842, Q1843, Q1847, Q1854, Q1856 | Q1270 | Q1691 | Q1463 | Q1496 | Q1444 | Q1702 | Q1837 | Q1838 | Q1840 | Q1842 | Q1843 | Q1847 | Q1854 | Q1856
Vaca Dixon Substation 230 kV Circuit Breakers 442, 452 and 462 overstress | 5810427 | T.0001609 | 64C | The C12P1-NPT04 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Vaca Dixon Substation 230kV in Solano County, California. | Engineering more than 50% complete | 2027-03-01 |  |  | Solano | PG&E: North Valley Area | No | N/A | T.0007195 ¦ T.0010478 ¦ T.0007418 ¦ T.0008063 ¦ T.0008218 ¦ T.0008918 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 | Replace | Asset Condition | T-Line Capacity | N/A | 42.1076 | N/A | 230 kV | 2027-05-24 | 2027-03-01 | 2027-07-21 | Transmission Project Review Process data (Resolution E-5252 Attach B | 142 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom! | Q1270, Q1691, Q1463, Q1496, Q1444, Q1702, Q1837, Q1838, Q1840, Q1842, Q1843, Q1847, Q1854, Q1856 | Q1270 | Q1691 | Q1463 | Q1496 | Q1444 | Q1702 | Q1837 | Q1838 | Q1840 | Q1842 | Q1843 | Q1847 | Q1854 | Q1856
Vaca Dixon Substation 230 kV Circuit Breakers 442, 452 and 462 overstress | 5810428 | T.0001609 | 64C | The C12P1-NPT04 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Vaca Dixon Substation 230kV in Solano County, California. | Engineering more than 50% complete | 2027-03-01 |  |  | Solano | PG&E: North Valley Area | No | N/A | T.0007195 ¦ T.0010478 ¦ T.0007418 ¦ T.0008063 ¦ T.0008218 ¦ T.0008918 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 | Replace | Asset Condition | T-Line Capacity | N/A | 42.1076 | N/A | 230 kV | 2026-10-16 | 2027-03-01 | 2026-10-16 | Transmission Project Review Process data (Resolution E-5252 Attach B | -136 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom! | Q1270, Q1691, Q1463, Q1496, Q1444, Q1702, Q1837, Q1838, Q1840, Q1842, Q1843, Q1847, Q1854, Q1856 | Q1270 | Q1691 | Q1463 | Q1496 | Q1444 | Q1702 | Q1837 | Q1838 | Q1840 | Q1842 | Q1843 | Q1847 | Q1854 | Q1856
Q1709 - ROSEMARY-GENSITE (DA) | 5811147 | T.0010467 | 82Y | The Q1709 Rosemary Project from Cluster 13, proposes to interconnect a 35 megawatt (MW) (net output) Solar + Battery generation facility to Crescent SW 70kV in Fresno County, California. The project has a contractual In-service date of: 12/3/27 with a current planned In-service date of: 12/3/27 | Planning | 2025-03-28 |  |  | N/A | N/A | No | N/A | T.0003009 ¦ T.0010934 ¦ T.0000043 ¦ T.0007056 ¦ T.0004255 ¦ T.0007056 ¦ T.0003016 ¦ T.0006452 ¦ T.0009177 | Upgrade/Retrofit | Other [See Notes] | System Operations | N/A | N/A | N/A | N/A | N/A | 2027-12-03 | 2027-12-03 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - Tracking to Dec 2027 | - | 1709 | 1709
Q1709 - Rosemary -Crescent SS (DA) | 5811148 | T.0010467 | 82Y | The Q1709 Rosemary Project from Cluster 13, proposes to interconnect a 35 megawatt (MW) (net output) Solar + Battery generation facility to Crescent SW 70kV in Fresno County, California. The project has a contractual In-service date of: 12/3/27 with a current planned In-service date of: 12/3/27 | Planning | 2025-03-28 |  |  | N/A | N/A | No | N/A | T.0003009 ¦ T.0010934 ¦ T.0000043 ¦ T.0007056 ¦ T.0004255 ¦ T.0007056 ¦ T.0003016 ¦ T.0006452 ¦ T.0009177 | Upgrade/Retrofit | Other [See Notes] | System Operations | N/A | N/A | N/A | N/A | N/A | 2027-12-03 | 2027-12-03 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - Tracking to Dec 2027 | - | 1709 | 1709
Q1709 - Rosemary - Crescent SS (NU) | 5811150 | T.0010467 | 82W | The Q1709 Rosemary Project from Cluster 13, proposes to interconnect a 35 megawatt (MW) (net output) Solar + Battery generation facility to Crescent SW 70kV in Fresno County, California. The project has a contractual In-service date of: 12/3/27 with a current planned In-service date of: 12/3/27 | Planning | 2025-03-28 |  |  | N/A | N/A | No | N/A | T.0003009 ¦ T.0010934 ¦ T.0000043 ¦ T.0007056 ¦ T.0004255 ¦ T.0007056 ¦ T.0003016 ¦ T.0006452 ¦ T.0009177 | Upgrade/Retrofit | Other [See Notes] | System Operations | N/A | N/A | N/A | N/A | N/A | 2027-12-03 | 2027-12-03 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - Tracking to Dec 2027 | - | 1709 | 1709
Q1751 PV BESS GEN SITE DA | 5811319 | T.0010519 | 82Y | The Q1751 Winston Hybrid PV And BESS Project from Cluster 13, proposes to interconnect a 200 megawatt (MW) (net output) Solar + Battery generation facility to Midway 115kV in Kern County, California. The project has a contractual In-service date of: 10/12/30 with a current planned In-service date of: 10/12/30 | Engineering more than 50% complete | 2028-06-01 |  |  | Arbuckle CDP, Colusa ¦ Colusa ¦ Yolo | N/A | No | 2024 | Maintenance ¦ Maintenance ¦ Maintenance ¦ Maintenance ¦ T.0003009 ¦ T.0001650 ¦ T.0004292 ¦ T.0006452 ¦ T.0010031 ¦ T.0010032 ¦ T.0007722 | Upgrade/Retrofit | Reliability | Line Reconductoring | 26.2 | #REF! | 60 | N/A | 2027-11-22 | 2030-10-12 | 2030-10-12 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | NOC |  | N/A [See Notes] |  | 05/06/25 - PM assigned | - | 1751 | 1751
Vaca Dixon Substation 230 kV Circuit Breakers 442, 452 and 462 overstress | 5811558 | T.0001609 | 93P | The C12P1-NPT04 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Vaca Dixon Substation 230kV in Solano County, California. | Engineering more than 50% complete | 2027-03-01 |  |  | Green Valley CDP, Napa ¦ Green Valley CDP, Solano ¦ Hartley CDP, Solano ¦ Napa ¦ Solano ¦ Vacaville, Solano | 0 | No | N/A | T.0007195 ¦ T.0010478 ¦ T.0007418 ¦ T.0008063 ¦ T.0008218 ¦ T.0008918 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 ¦ 0 | New | Asset Condition | T-Line Capacity | 0.1 | NA | 230 | N/A | 2026-02-24 | 2027-03-01 | 2026-06-16 | Transmission Project Review Process data (Resolution E-5252 Attach B | -258 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom! | Q1270, Q1691, Q1463, Q1496, Q1444, Q1702, Q1837, Q1838, Q1840, Q1842, Q1843, Q1847, Q1854, Q1856 | Q1270 | Q1691 | Q1463 | Q1496 | Q1444 | Q1702 | Q1837 | Q1838 | Q1840 | Q1842 | Q1843 | Q1847 | Q1854 | Q1856
Q1260 KYAN-Q946 SS-DA | 5811842 | T.0010617 | 82Y | The Q1260 Kyan Solar Project from Cluster 9, proposes to interconnect a 100 megawatt (MW) (net output) Solar generation facility to BitterWater Sw Sta in Kern County, California. The project has a contractual In-service date of: 3/30/29 with a current planned In-service date of: 7/31/27 | Construction (under 10%) | 2023-12-01 |  |  | Folsom, Sacramento | N/A | No | N/A | T.0001353 | Replace | Emergency Event | Replace Transformer | N/A | #REF! | N/A | 115 ¦ 60 kV | 2025-01-28 | 2029-03-30 | 2027-07-31 | Transmission Project Review Process data (Resolution E-5252 Attach B | -608 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - PTO acceleration was completed to plan In-service date (ISD) of: July 3, 2027 | - | 1260 | 1260
Q1260 KYAN-GENSITE-DA | 5811843 | T.0010617 | 82Y | The Q1260 Kyan Solar Project from Cluster 9, proposes to interconnect a 100 megawatt (MW) (net output) Solar generation facility to BitterWater Sw Sta in Kern County, California. The project has a contractual In-service date of: 3/30/29 with a current planned In-service date of: 7/31/27 | Construction (under 10%) | 2023-12-01 |  |  | Folsom, Sacramento | N/A | No | N/A | T.0001353 | Replace | Emergency Event | Replace Transformer | N/A | #REF! | N/A | 115 ¦ 60 kV | 2025-01-28 | 2029-03-30 | 2027-07-31 | Transmission Project Review Process data (Resolution E-5252 Attach B | -608 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - PTO acceleration was completed to plan In-service date (ISD) of: July 3, 2027 | - | 1260 | 1260
Q1260 KYAN-T-LINE-DA | 5811844 | T.0010617 | 82D | The Q1260 Kyan Solar Project from Cluster 9, proposes to interconnect a 100 megawatt (MW) (net output) Solar generation facility to BitterWater Sw Sta in Kern County, California. The project has a contractual In-service date of: 3/30/29 with a current planned In-service date of: 7/31/27 | Construction (under 10%) | 2023-12-01 |  |  | Folsom, Sacramento | N/A | No | N/A | T.0001353 | Replace | Emergency Event | Replace Transformer | N/A | #REF! | N/A | 115 ¦ 60 kV | 2025-01-28 | 2029-03-30 | 2027-07-31 | Transmission Project Review Process data (Resolution E-5252 Attach B | -608 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - PTO acceleration was completed to plan In-service date (ISD) of: July 3, 2027 | - | 1260 | 1260
Q1260 KYAN-Q946 SS-RNU | 5811845 | T.0010617 | 82W | The Q1260 Kyan Solar Project from Cluster 9, proposes to interconnect a 100 megawatt (MW) (net output) Solar generation facility to BitterWater Sw Sta in Kern County, California. The project has a contractual In-service date of: 3/30/29 with a current planned In-service date of: 7/31/27 | Construction (under 10%) | 2023-12-01 |  |  | Folsom, Sacramento | N/A | No | N/A | T.0001353 | Replace | Emergency Event | Replace Transformer | N/A | #REF! | N/A | 115 ¦ 60 kV | 2025-01-28 | 2029-03-30 | 2027-07-31 | Transmission Project Review Process data (Resolution E-5252 Attach B | -608 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - PTO acceleration was completed to plan In-service date (ISD) of: July 3, 2027 | - | 1260 | 1260
Q1496 DESC RNCH 1 CTTNWD SUB RNU CB242 | 5812423 | T.0008063 | 82W | The C11P2-NR01 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Cottonwood Substation 230kV in Shasta County, California. | Engineering more than 50% complete | 2025-03-21 |  |  | Cottonwood CDP, Shasta | N/A | Yes | N/A | T.0008063 ¦ 0 ¦ 0 | New | Generator Interconnection | Generation Interconnection | N/A | N/A | N/A | 230 kV | 2026-04-21 | 2025-03-21 | 2026-05-19 | Transmission Project Review Process data (Resolution E-5252 Attach B | 424 | Yes |  |  | N/A |  | TBD | TBD | TBD | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom! | Q1496, Q1858, Q1863 | Q1496 | Q1858 | Q1863
Q1496 DESC RNCH 1 CTTNWD SUB RNU CB222 | 5812424 | T.0008063 | 82W | The C11P2-NR01 Network Upgrade Project supports interconnections of new Transmission Generation projects by performing upgrades to PG&E's facilities at the Cottonwood Substation 230kV in Shasta County, California. | Engineering less than 50% complete | 2025-03-21 |  |  | Cottonwood CDP, Shasta | N/A | Yes | N/A | T.0008063 ¦ 0 ¦ 0 | New | Generator Interconnection | Generation Interconnection | N/A | N/A | N/A | 230 kV | 2026-08-11 | 2025-03-21 | 2026-09-08 | Transmission Project Review Process data (Resolution E-5252 Attach B | 536 | Yes |  |  | N/A |  | TBD | TBD | TBD | N/A | N/A |  | N/A [See Notes] |  |  | Utility - !Telecom! | Q1496, Q1858, Q1863 | Q1496 | Q1858 | Q1863
TESLA: Install 230 KV MPAC | 5812669 | T.0003456 | 67A |  | Engineering more than 50% complete | 2026-12-01 |  |  | Alameda | PG&E: North Valley Area | No | N/A | NF | New | Other [See Notes] | T-Line Capacity | N/A | 69.382 | N/A | 500 ¦ 230 kV | 2026-10-16 | 2026-12-01 | 2027-02-22 | Transmission Project Review Process data (Resolution E-5252 Attach B | 83 | Yes |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 03/17/25 - ISD Jan 2028 very achievable, 14 Breakers total for project. 5-31-23 - ISD is not realistic. It is trending into 2026. | Utility - !Telecom! | mitigated until C14 | mitigated until C14
Q1378 - GONZAGA WIND - SHOOFLY | 5812904 | T.0004423 | 82B | The Q1378 Gonzaga Wind Farm Project from Cluster 10, proposes to interconnect a 76.35 megawatt (MW) (net output) Wind Turbine + Battery generation facility to Los Banos 70kV in Merced County, California. The project has a contractual In-service date of: 11/1/25 with a current planned In-service date of: 12/18/25 | Operational | 2023-07-01 |  |  | Merced | 0 | Yes | N/A |  | New | Generator Interconnection | T-Line Reliability | 0.1 | N/A | 70 | N/A | 2024-12-01 | 2025-11-01 | 2025-11-01 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - Tracking ISD to Q4 2025. Tline material ordered Oct 2024 with Q3 2025 delivery. IC Delays: At risk, IC's design not complete. Construction needs to start Q2 2025. Low confidence ISD in 2025. | Customer - Construction Delays | 1378 | 1378
Q1956 - GENSITE | 5813139 | T.0010738 | 82Y | The Q1956 Sequoia (Clarkson) Project from Cluster 14, proposes to interconnect a 200 megawatt (MW) (net output) Solar + Battery generation facility to Tranquility SW 230kV in Fresno County, California. The project has a contractual In-service date of: 5/30/29 with a current planned In-service date of: 3/27/28 | Engineering less than 50% complete | 2030-06-01 |  |  | San Jose, Santa Clara | N/A | No | 2022 | T.0009177 ¦ T.0009194 ¦ T.0009662 ¦ T.0007056 ¦ T.0003009 ¦ T.0004255 ¦ T.0007056 | New | Reliability | Bus Upgrade | N/A | #REF! | N/A | 230 kV | 2028-03-20 | 2029-05-30 | 2028-03-27 | Transmission Project Review Process data (Resolution E-5252 Attach B | -429 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | NOC: AL 7391-E | 2024-10-10 | N/A [See Notes] |  | 05/06/25 - PM assigned | - | 1956 | 1956
Q1277 MULQUEENY METERING (DA) | 5550660 | T.0004354 | 82Y | The Q1277 Mulqueeney Ranch Wind Project from Cluster 9, proposes to interconnect a 20 megawatt (MW) (net output) Wind Turbine generation facility to Tesla 230kV in Alameda County, California. The project has a contractual In-service date of: 10/15/25 with a current planned In-service date of: 10/15/25 | Engineering more than 50% complete | N/A |  |  | Deer Park CDP, Napa ¦ Fulton CDP, Sonoma ¦ Kenwood CDP, Sonoma ¦ Lake ¦ Larkfield-Wikiup CDP, Sonoma ¦ Napa ¦ Saint Helena, Napa ¦ Santa Rosa, Sonoma ¦ Sonoma | PG&E: Greater Fresno Area | No | N/A | T.0007288 | New | Reliability | Safety - Line Right of Way Access | N/A | N/A | 60 | N/A | N/A | 2025-10-15 | 2025-10-15 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - ISD 10/15/25. | -
WINDWALKER OS METER (DA) | 5551986 | T.0008967 | 82Y | The Q1750 Windwalker Offshore Project from Cluster 13, proposes to interconnect a 1000 megawatt (MW) (net output) Wind Turbine generation facility to Diablo Canyon SW 500kV in San Luis Obispo County, California. The project has a contractual In-service date of: 4/12/28 with a current planned In-service date of: 3/27/28 | On Hold | 2021-04-27 |  |  | Rodeo CDP, Contra Costa | N/A | No | N/A | Maintenance ¦ Maintenance ¦ T.0003009 ¦ Maintenance ¦ Maintenance ¦ T.0007722 | Replace | Asset Condition | Age/Condition - Replace Conductor | N/A | 2.851 | 115 | N/A | 2031-01-21 | 2028-04-12 | 2028-03-27 | Transmission Project Review Process data (Resolution E-5252 Attach B | -16 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | NOC: AL 6202-E | 2021-05-26 | Approved | 2021 | 05/06/25 - IC delays due to Gentie route acquisitions and permitting. | Customer - Land Rights | 1750 | 1750
Q1277 MULQUEENY GENERATION SITE (DA) | 5782658 | T.0004354 | 82Y | The Q1277 Mulqueeney Ranch Wind Project from Cluster 9, proposes to interconnect a 20 megawatt (MW) (net output) Wind Turbine generation facility to Tesla 230kV in Alameda County, California. The project has a contractual In-service date of: 10/15/25 with a current planned In-service date of: 10/15/25 | Engineering more than 50% complete | 2021-01-14 |  |  | Alameda | PG&E: Greater Fresno Area | Yes | N/A | T.0007288 | Upgrade/Retrofit | Generator Interconnection | Generation Interconnection | N/A | 69.382 | N/A | 230 kV | 2025-08-04 | 2025-10-15 | 2025-10-15 | Transmission Project Review Process data (Resolution E-5252 Attach B | 0 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - ISD 10/15/25. | -
Q1750 WINDWALKER OS GEN SITE (DA) | 5804096 | T.0008967 | 82Y | The Q1750 Windwalker Offshore Project from Cluster 13, proposes to interconnect a 1000 megawatt (MW) (net output) Wind Turbine generation facility to Diablo Canyon SW 500kV in San Luis Obispo County, California. The project has a contractual In-service date of: 4/12/28 with a current planned In-service date of: 3/27/28 | Engineering less than 50% complete | 2028-04-12 |  |  | San Luis Obispo | N/A | Yes | N/A | Maintenance ¦ Maintenance ¦ T.0003009 ¦ Maintenance ¦ Maintenance ¦ T.0007722 | New | Generator Interconnection | Generation Interconnection | N/A | 35.6227 | N/A | 500 kV | 2029-12-03 | 2028-04-12 | 2028-03-27 | Transmission Project Review Process data (Resolution E-5252 Attach B | -16 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - IC delays due to Gentie route acquisitions and permitting. | Customer - Land Rights | 1750 | 1750
Q1949 DARDEN (DA) GEN-SITE | 5805800 | T.0009383 | 82Y | The Q1949 Darden Hybrid Solar Project from Cluster 14, proposes to interconnect a 1150 megawatt (MW) (net output) Solar + Battery generation facility to Los Banos-Midway 500kV #2 Line in Fresno County, California. The project has a contractual In-service date of: 2/28/31 with a current planned In-service date of: 11/18/30 | Engineering less than 50% complete | 2028-08-01 |  |  | Fresno | N/A | Yes | N/A | T.0010032 ¦ T.0008543 ¦ T.0001650 ¦ T.0009194 ¦ T.0010787 ¦ T.0010836 ¦ T.0004292 | Upgrade/Retrofit | Generator Interconnection | Generation Interconnection | N/A | 77.6619 | N/A | 500 kV | 2029-03-07 | 2031-02-28 | 2030-11-18 | Transmission Project Review Process data (Resolution E-5252 Attach B | -102 | No |  |  | N/A |  | N/A | N/A | CEC | N/A | N/A |  | N/A [See Notes] |  | 05/06/25 - Customer wants to move date forward. Earliest backfeed Q1, 2031 pending mitigations for Network Upgrades, C14P2-FGR04 - Los Banos 500 kV circuit breakers 822, 832 & 842 overstress, Q1 2031 ISD, C14P1-KGR11 - Midway 500 kV CB 742, 912, 942 Overstress beyond 50 kA Q1 2031 ISD. PG&E will uprate Midway breakers and Los Banos Breakers CB822 & 832 and must replacce CB842. Breaker ordered by Material Purchase Program. ISDs to be determined once design is complete. 04/08/25 - Tracking ISD to Q3 2030 with no current delays | Customer - Material | 1949 | 1949
Q1949 DARDEN (NU) 500KV T-LINE | 5809671 | T.0009383 | 82B | The Q1949 Darden Hybrid Solar Project from Cluster 14, proposes to interconnect a 1150 megawatt (MW) (net output) Solar + Battery generation facility to Los Banos-Midway 500kV #2 Line in Fresno County, California. The project has a contractual In-service date of: 2/28/31 with a current planned In-service date of: 11/18/30 | Engineering less than 50% complete | 2028-08-01 |  |  | Avenal, Kings ¦ Buttonwillow CDP, Kern ¦ Fresno ¦ Kern ¦ Kings ¦ Merced | N/A | Yes | N/A | T.0010032 ¦ T.0008543 ¦ T.0001650 ¦ T.0009194 ¦ T.0010787 ¦ T.0010836 ¦ T.0004292 | New | Generator Interconnection | T-Line Capacity | 15 | N/A | 500 | N/A | 2029-10-03 | 2031-02-28 | 2030-11-18 | Transmission Project Review Process data (Resolution E-5252 Attach B | -102 | No |  |  | N/A |  | N/A | N/A | N/A | N/A | NOC |  | N/A [See Notes] |  | 05/06/25 - Customer wants to move date forward. Earliest backfeed Q1, 2031 pending mitigations for Network Upgrades, C14P2-FGR04 - Los Banos 500 kV circuit breakers 822, 832 & 842 overstress, Q1 2031 ISD, C14P1-KGR11 - Midway 500 kV CB 742, 912, 942 Overstress beyond 50 kA Q1 2031 ISD. PG&E will uprate Midway breakers and Los Banos Breakers CB822 & 832 and must replacce CB842. Breaker ordered by Material Purchase Program. ISDs to be determined once design is complete. 04/08/25 - Tracking ISD to Q3 2030 with no current delays | Customer - Material

## 2. Generation Reporting
Generation Reporting |  |  | Cells highlighted like this are missing requested data
List every renewable energy and energy storage resource (with executed interconnection agreements) currently in the CAISO, WDAT, or other interconnection queues. |  |  | All fields are mandatory. Blank fields or data that doesn't match the Input Format on the Instructions tab will be considered incomplete. Tab sections in black text refer to transmission projects, tab sections in red text refer to generation projects. | [7 empty] | What qualifies as RPS Eligible?
Section 1: GENERATION RESOURCES DETAILS | [13 empty] | Section 3: CONNECTING TRANSMISSION PROJECTS
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
Generation Facility Name | In-Queue Number (CAISO or WDAT) | Generator Resource ID | Primary Developer | Developer Parent Company Name | Nameplate Capacity | Expected Annual RPS Eligible Generation | Planned Construction Start Date | Planned In-service Date | Interconnection Request Type | Technology Type | RPS Eligible | PTO Service Territory | Notes | Dependent on Delayed Transmission Project | Impact of Transmission Delay on Resource
Oakland C Unit 2 Repower | 0051CONV | Still TBD by CAISO | Oakland Energy Storage 1, LLC | Oakland Energy Storage 1, LLC | 0 | 0 | 2026-07-28 | 2026-12-01 |  | Various |  | PG&E | [Type] Repower 05/06/25 - IC stopped their scope and has not engaged project management. MMA in process to change date to 2026. | No | N/A
Eagle 2 Solar | 1620-WD | Still TBD by CAISO | Apex Eagle Creek 2, LLC | Apex Eagle Creek 2, LLC | 3 | 8777.52 | 2019-05-21 | 2027-10-31 | Partial Capacity | Solar | Yes | PG&E |  | No | N/A
WCW Generator 1 | 1827-RD | Still TBD by CAISO | West Coast Waste | West Coast Waste | 3.88 | Not RPS Eligible | 2019-06-25 | 2027-12-01 | Energy Only | Other [See Notes] | No | PG&E | Reciprocating Engine | No | N/A
Berry Petroleum Company | 1990-RD | Still TBD by CAISO | Berry Petroleum, LLC | Berry Petroleum, LLC | 10 | Not RPS Eligible | n/a - R21 | 2025-12-01 | Energy Only | Other [See Notes] | No | PG&E | Cogeneration | No | N/A
Napa Recycling Biomass Plant - 2nd MW | 1991-RD | Still TBD by CAISO | Napa Recycling & Waste Services | Napa Recycling & Waste Services | 1.172 | 3429.0845 | n/a - R21 | 2020-06-25 | Energy Only | Solar | Yes | PG&E |  | No | N/A
Steelhead Energy Storage | 2005-WD | Still TBD by CAISO | Pacific Gas & Electric | Pacific Gas & Electric | 6 | Not RPS Eligible | n/a - UOG | 2026-02-25 | Energy Only | Battery Storage | No | PG&E |  | No | N/A
North Fork Community Power | 2007-RD | Still TBD by CAISO | North Fork Community Power, LLC | North Fork Community Power, LLC | 2 | 5851.68 | 2019-07-24 | 2025-04-18 | Energy Only | Solar | Yes | PG&E |  | No | N/A
Blue Mountain Electric Company | 2008-RD | Still TBD by CAISO | Blue Mountain Electric Company, LLC | Blue Mountain Electric Company, LLC | 3 | 8777.52 | 2020-08-28 | 2025-12-31 | Energy Only | Solar | Yes | PG&E |  | No | N/A
Gas Co Road Solar 1 | 2040-WD | Still TBD by CAISO | GasCo Rd, LLC | GasCo Rd, LLC | 2.2 | 6436.848 | 2020-06-09 | 2027-01-01 | Full Capacity | Solar | Yes | PG&E |  | No | N/A
Gas Co Road Solar 2 | 2105-WD | Still TBD by CAISO | GasCo Rd, LLC | GasCo Rd, LLC | 2 | 5851.68 | 2020-06-09 | 2027-01-01 | Full Capacity | Hybrid/Paired Solar and Battery | Yes | PG&E |  | No | N/A
Gas Co Road Solar 3 | 2174-WD | Still TBD by CAISO | GasCo Rd, LLC | GasCo Rd, LLC | 2.162 | 6325.6661 | 2020-07-27 | 2027-01-01 | Partial Capacity | Other [See Notes] | Yes | PG&E | Hybrid: Solar PV / Biomass | No | N/A
Gas Co Road Solar 4 | 2175-WD | Still TBD by CAISO | GasCo Rd, LLC | GasCo Rd, LLC | 2.162 | 6325.6661 | 2020-07-27 | 2027-01-01 | Partial Capacity | Solar | Yes | PG&E |  | No | N/A
Coyote Valley Energy Storage 2 | 2181-WD | Still TBD by CAISO | Pacific Gas and Electric Company | Pacific Gas and Electric Company | 20 | Not RPS Eligible | n/a - UOG | 2026-12-30 | Full Capacity | Battery Storage | No | PG&E |  | No | N/A
Tracy Desalination Project | 2187-RD | Still TBD by CAISO | Combined Solar Technologies | Combined Solar Technologies | 3.6 | Not RPS Eligible | 2021-02-26 | 2026-12-30 | Energy Only | Other [See Notes] | No | PG&E | Turbine | No | N/A
CES Electron Farm One LLC | 2226-WD | Still TBD by CAISO | ELECTRON FARM ONE, LLC | ELECTRON FARM ONE, LLC | 4 | 11703.36 | 2022-11-02 | 2025-05-30 | Full Capacity | Solar | Yes | PG&E |  | No | N/A
Jade Solar 3 | 2327-WD | Still TBD by CAISO | Apex Jade, LLC | Apex Jade, LLC | 1.5 | 4388.76 | 2020-11-30 | 2027-10-01 | Energy Only | Solar | Yes | PG&E |  | No | N/A
Scotts Valley Indian Energy | 2371-RD | Still TBD by CAISO | Scotts Valley Energy Company, LLC | Scotts Valley Energy Company, LLC | 0.3 | 877.752 | n/a - R21 | 2025-06-30 | Energy Only | Solar | Yes | PG&E |  | No | N/A
Quail Energy Storage | 2389-WD | Still TBD by CAISO | PG&E | PG&E | 20 | Not RPS Eligible | n/a - UOG | 2027-01-15 | Full Capacity | Battery Storage | No | PG&E |  | No | N/A
East Road Storage | 2390-WD | Still TBD by CAISO | FORM ENERGY, INC. | FORM ENERGY, INC. | 5 | Not RPS Eligible | 2024-12-23 | 2026-03-27 | Full Capacity | Battery Storage | No | PG&E |  | No | N/A
North Coast Highway Solar 1 | 2399-WD | Still TBD by CAISO | NORTH COAST HIGHWAY SOLAR 1, LLC | NORTH COAST HIGHWAY SOLAR 1, LLC | 1 | 2925.84 | 2020-07-02 | 2025-11-22 | Energy Only | Solar | Yes | PG&E |  | No | N/A
North Coast Highway Solar 2 | 2400-WD | Still TBD by CAISO | NORTH COAST HIGHWAY SOLAR 1, LLC | NORTH COAST HIGHWAY SOLAR 1, LLC | 0.975 | 2852.694 | 2020-12-17 | 2025-11-22 | Energy Only | Solar | Yes | PG&E |  | No | N/A
Stodola BESS | 2495-WD | Still TBD by CAISO | Stodola BESS, LLC | Stodola BESS, LLC | 10 | Not RPS Eligible | 2021-08-07 | 2026-11-20 | Full Capacity | Battery Storage | No | PG&E |  | No | N/A
Madena Solar 3 | 2533-WD | Still TBD by CAISO | Apex Energy Solutions, LLC | Apex Energy Solutions, LLC | 0.1 | 292.584 | 2021-12-25 | 2025-11-21 | Energy Only | Other [See Notes] | Yes | PG&E | Hybrid: Solar PV / Biogas / Engine | No | N/A
Merced BESS | 2569-WD | Still TBD by CAISO | APEX ENERGY SOLUTIONS, LLC | APEX ENERGY SOLUTIONS, LLC | 3 | Not RPS Eligible | 2021-12-03 | 2025-12-01 | Energy Only | Battery Storage | No | PG&E |  | No | N/A
Gibson Solar Project | 2595-WD | Still TBD by CAISO | RENESOLA POWER | RENESOLA POWER | 21.6 | 63198.144 | 2023-08-01 | 2026-03-01 | Full Capacity | Hybrid/Paired Solar and Battery | Yes | PG&E |  | No | N/A
Merced 2 | 2596-WD | Still TBD by CAISO | Apex Energy Solutions, LLC | Apex Energy Solutions, LLC | 0.1 | 292.584 | 2022-01-24 | 2025-11-21 | Energy Only | Hybrid/Paired Solar and Battery | Yes | PG&E |  | No | N/A
Ranch Sereno Clean Power | 2597-WD | Still TBD by CAISO | RANCH SERENO CLEAN POWER LLC | RANCH SERENO CLEAN POWER LLC | 2 | 5851.68 | 2021-10-29 | 2026-03-01 | Energy Only | Hybrid/Paired Solar and Battery | Yes | PG&E |  | No | N/A
Discovery Bay South Clean Power | 2598-WD | Still TBD by CAISO | Suntech Power Development America | Suntech Power Development America | 3 | 8777.52 | 2021-07-30 | 2026-11-26 | Energy Only | Hybrid/Paired Solar and Battery | Yes | PG&E |  | No | N/A
Madena Solar 4 | 2706-WD | Still TBD by CAISO | Apex Energy Solutions, LLC | Apex Energy Solutions, LLC | 5 | 14629.2 | 2022-10-09 | 2026-11-20 | Energy Only | Hybrid/Paired Solar and Battery | Yes | PG&E |  | No | N/A
Soscol Ferry Storage | 2762-WD | Still TBD by CAISO | Renewable Properties, LLC | Renewable Properties, LLC | 5 | 14629.2 | 2024-11-01 | 2026-09-01 | Full Capacity | Solar | Yes | PG&E |  | No | N/A
Industrial Parkway Storage | 2764-WD | Still TBD by CAISO | Renewable Properties, LLC | Renewable Properties, LLC | 10 | 29258.4 | 2024-01-01 | 2026-09-01 | Full Capacity | Solar | Yes | PG&E |  | No | N/A
1 W Barrett Ave Richmond | 2818-RD | Still TBD by CAISO | Pristine Sun Cop. | Pristine Sun Cop. | 2.25 | 6583.14 | 2022-03-25 | 2025-05-01 | Energy Only | Solar | Yes | PG&E |  | No | N/A
Sutro Reservoir | 2848-WD | Still TBD by CAISO | City and County of San Francisco | City and County of San Francisco | 2.85 | 8338.644 | 2022-09-13 | 2027-08-05 | Full Capacity | Solar | Yes | PG&E |  | No | N/A
University Mound Reservoir - North Basin | 2849-WD | Still TBD by CAISO | City and County of San Francisco | City and County of San Francisco | 4.62 | 13517.3808 | 2022-09-13 | 2026-08-05 | Full Capacity | Hybrid/Paired Solar and Battery | Yes | PG&E |  | No | N/A
Fuji battery storage | 2927-WD | Still TBD by CAISO | Apex Energy Solutions, LLC | Apex Energy Solutions, LLC | 5 | Not RPS Eligible | 2023-12-12 | 2026-12-01 | Full Capacity | Battery Storage | No | PG&E |  | No | N/A
Stella | 2958-WD | Still TBD by CAISO | Apex Energy Solutions, LLC | Apex Energy Solutions, LLC | 5 | Not RPS Eligible | 2024-10-01 | 2026-12-01 | Full Capacity | Battery Storage | No | PG&E |  | No | N/A
Canyon Road Solar | 3042-WD | Still TBD by CAISO | Renewable Properties, LLC | Renewable Properties, LLC | 5 | 14629.2 | 2023-04-30 | 2026-12-31 | Energy Only | Solar | Yes | PG&E |  | No | N/A
Confliti Jr. | 3057-WD | Still TBD by CAISO | CES Electron Farm One, LLC | CES Electron Farm One, LLC | 0.25 | 731.46 | 2023-10-30 | 2025-05-30 | Energy Only | Solar | Yes | PG&E |  | No | N/A
Fox 3 | 3074-WD | Still TBD by CAISO | Apex Energy Solutions LLC | Apex Energy Solutions LLC | 6.81 | 19924.9704 | 2023-05-05 | 2026-11-02 | Energy Only | Solar | Yes | PG&E |  | No | N/A
Redemeyer Road Solar | 3086-WD | Still TBD by CAISO | Renewable Properties, LLC | Renewable Properties, LLC | 4 | 11703.36 | 2023-06-30 | 2025-07-18 | Full Capacity | Hybrid/Paired Solar and Battery | Yes | PG&E |  | No | N/A
TESORO COMMONS LLC | 3098-WD | Still TBD by CAISO | Tesoro Commons LLC | Tesoro Commons LLC | 2.631 | 7697.885 | 2023-05-20 | 2025-11-18 | Energy Only | Solar | Yes | PG&E |  | No | N/A
Wunpost Clean Power | 3113-WD | Still TBD by CAISO | Renewable America LLC | Renewable America LLC | 3 | 8777.52 | 2024-03-26 | 2025-12-31 | Energy Only | Solar | Yes | PG&E |  | No | N/A
Hat Creek Bioenergy | 3126-RD | Still TBD by CAISO | Hat Creek Bioenergy, LLC | Hat Creek Bioenergy, LLC | 3.6 | 10533.024 | 2023-02-14 | 2025-05-31 | Energy Only | Biomass | Yes | PG&E |  | No | N/A
Fox 1 | 3131-WD | Still TBD by CAISO | Apex Energy Solutions, LLC | Apex Energy Solutions, LLC | 3 | 8777.52 | 2023-09-26 | 2026-11-02 | Energy Only | Solar | Yes | PG&E |  | No | N/A
Fox 2 | 3134-WD | Still TBD by CAISO | Apex Energy Solutions, LLC | Apex Energy Solutions, LLC | 5 | 14629.2 | 2023-09-20 | 2026-11-02 | Energy Only | Solar | Yes | PG&E |  | No | N/A
Althea Avenue Solar Phase I | 3170-WD | Still TBD by CAISO | Central Coast Community Energy | Central Coast Community Energy | 5 | 14629.2 | 2024-02-05 | 2025-09-26 | Energy Only | Solar | Yes | PG&E |  | No | N/A
Althea Avenue Solar Phase II | 3179-WD | Still TBD by CAISO | Central Coast Community Energy | Central Coast Community Energy | 4.5 | Not RPS Eligible | 2024-02-05 | 2025-09-26 | Energy Only | Battery Storage | No | PG&E |  | No | N/A
Fox 4 | 3194-WD | Still TBD by CAISO | Apex Energy Solutions LLC | Apex Energy Solutions LLC | 5 | 14629.2 | 2024-02-27 | 2026-11-02 | Energy Only | Solar | Yes | PG&E |  | No | N/A
King Kettle Clean Power I | 3195-WD | Still TBD by CAISO | King Kettle Clean Power I LLC | King Kettle Clean Power I LLC | 5 | 14629.2 | 2024-06-24 | 2025-06-30 | Energy Only | Hybrid/Paired Solar and Battery | Yes | PG&E |  | No | N/A
Gardenia 1 | 3198-WD | Still TBD by CAISO | Central Coast Community Energy | Central Coast Community Energy | 3 | 8777.52 | 2024-01-29 | 2026-11-02 | Energy Only | Hybrid/Paired Solar and Battery | Yes | PG&E |  | No | N/A
PLD - SolarChoice - Stockton 1 | 3204-WD | Still TBD by CAISO | Prologis Energy LLC | Prologis Energy LLC | 1 | 2925.84 | 2024-04-17 | 2026-06-09 | Energy Only | Solar | Yes | PG&E |  | No | N/A
PLD - SolarChoice - Stockton 9 | 3206-WD | Still TBD by CAISO | Prologis Energy LLC | Prologis Energy LLC | 1 | 2925.84 | 2024-04-14 | 2026-06-09 | Energy Only | Solar | Yes | PG&E |  | No | N/A
CA - PLD RFO - San Lean 9 | 3209-WD | Still TBD by CAISO | Prologis Energy LLC | Prologis Energy LLC | 1 | 2925.84 | 2023-09-29 | 2026-08-14 | Energy Only | Solar | Yes | PG&E |  | No | N/A
Berrenda Mesa Solar | 3226-WD | Still TBD by CAISO | Wasco CSG 2 LLC | Wasco CSG 2 LLC | 1 | 2925.84 | 2025-05-30 | 2026-03-27 | Energy Only | Solar | Yes | PG&E |  | No | N/A
Battle Creek Bottom Road Solar | 3233-WD | Still TBD by CAISO | RPCA SOLAR 14, LLC | RPCA SOLAR 14, LLC | 3 | 8777.52 | 2025-06-10 | 2026-11-05 | Energy Only | Solar | Yes | PG&E |  | No | N/A
Gateway Solar RV & Boat Storage, LLC | 3238-RD | Still TBD by CAISO | Gateway Solar RV & Boat Storage, LLC | Gateway Solar RV & Boat Storage, LLC | 2.975 | 8704.374 | n/a - R21 | 2025-08-01 | Energy Only | Solar | Yes | PG&E |  | No | N/A
American Power Company, LLC | 3267-WD | Still TBD by CAISO |  |  | 0.999 | 2922.9142 | 2025-08-06 | 2027-11-10 | Energy Only | Solar | Yes | PG&E |  | No | N/A
Promus Hillcrest Digester | 3273-WD | Still TBD by CAISO | Prologis Energy LLC | Prologis Energy LLC | 0.999 | 2922.9142 | 2024-11-03 | 2026-06-19 | Energy Only | Biomass | Yes | PG&E |  | No | N/A
Godinho Dairy Digester | 3281-RD | Still TBD by CAISO | ALIGNED DIGESTERS CO., LLC | ALIGNED DIGESTERS CO., LLC | 1.998 | Not RPS Eligible | n/a - R21 | 2025-07-10 | Energy Only | Other [See Notes] | No | PG&E | Cogeneration | No | N/A
Blue Mines 1 | 3292-RD | Still TBD by CAISO | BAKERSFIELD CSG 2 LLC | BAKERSFIELD CSG 2 LLC | 4.6 | 13458.864 | 2025-05-23 | 2026-10-12 | Energy Only | Solar | Yes | PG&E |  | No | N/A
Blue Mines 2 | 3293-RD | Still TBD by CAISO | BAKERSFIELD CSG 3 LLC | BAKERSFIELD CSG 3 LLC | 5.724 | 16747.5082 | 2025-06-20 | 2026-11-23 | Energy Only | Solar | Yes | PG&E |  | No | N/A
Valley Ag | 3298-RD | Still TBD by CAISO | WASCO CSG 1 LLC | WASCO CSG 1 LLC | 4.6 | 13458.864 | 2025-04-08 | 2026-03-26 | Energy Only | Solar | Yes | PG&E |  | No | N/A
Roberts | 3317-RD | Still TBD by CAISO | FIREBAUGH CSG 1 LLC | FIREBAUGH CSG 1 LLC | 4.6 | 13458.864 | n/a - R21 | 2026-09-30 | Energy Only | Solar | Yes | PG&E |  | No | N/A
Melcat 1 | 3335-RD | Still TBD by CAISO | ARVIN CSG 1 LLC | ARVIN CSG 1 LLC | 6.042 | 17677.9253 | 2025-05-23 | 2026-10-12 | Energy Only | Solar | Yes | PG&E |  | No | N/A
Big Gem | 3355-WD | Still TBD by CAISO | LITTLE GEM SOLAR,LLC, | LITTLE GEM SOLAR,LLC, | 9.95 | 29112.108 | 2025-02-07 | 2026-02-27 | Energy Only | Hybrid/Paired Solar and Battery | Yes | PG&E |  | No | N/A
Melcat 2 | 3377-RD | Still TBD by CAISO | ARVIN CSG 2 LLC | ARVIN CSG 2 LLC | 5.1 | 14921.784 | 2025-06-20 | 2026-11-23 | Energy Only | Solar | Yes | PG&E |  | No | N/A
Chico Bay DG Solar | 3439-RD | Still TBD by CAISO | Dynamic Solar and Storage Solu | Dynamic Solar and Storage Solu | 4.65 | 13605.156 | n/a - R21 | 2026-02-09 | Energy Only | Solar | Yes | PG&E |  | No | N/A
Lupine DG Solar | 3464-RD | Still TBD by CAISO | DYNAMIC SOLAR AND STORAGE SOLUTIONS | DYNAMIC SOLAR AND STORAGE SOLUTIONS | 8.26 | 24167.4384 | n/a - R21 | 2026-02-09 | Energy Only | Solar | Yes | PG&E |  | No | N/A
Sierra Road DG Solar | 3481-RD | Still TBD by CAISO | DYNAMIC SOLAR AND STORAGE SOLUTIONS | DYNAMIC SOLAR AND STORAGE SOLUTIONS | 8.253 | 24146.9575 | n/a - R21 | 2026-02-13 | Energy Only | Solar | Yes | PG&E |  | No | N/A
Flying Goose Deuce | 3497-WD | Still TBD by CAISO | White Pine Development, LLC | White Pine Development, LLC | 3 | 8777.52 | 2025-03-10 | 2026-05-10 | Energy Only | Solar | Yes | PG&E |  | No | N/A
Engeman Svrc Green Energy, LP | 3507-RD | Still TBD by CAISO | ENGEMAN SVRC GREEN ENERGY, LP | ENGEMAN SVRC GREEN ENERGY, LP | 5 | Not RPS Eligible |  | 2026-09-30 | Energy Only | Other [See Notes] | No | PG&E | Turbine | No | N/A
Rosedale Rio Bravo | 3519-RD | Still TBD by CAISO | ROSEDALE RIO BRAVO WATER STORAGE DISTRICT | ROSEDALE RIO BRAVO WATER STORAGE DISTRICT | 4.999 | 14626.2742 | n/a - R21 | 2026-07-21 | Energy Only | Solar | Yes | PG&E |  | No | N/A
American Canyon RV & Boat Storage | 3547-RD | Still TBD by CAISO | NAPA JUNCTION RV STORAGE LLC | NAPA JUNCTION RV STORAGE LLC | 1.85 | 5412.804 | n/a - R21 | 2026-01-07 | Energy Only | Solar | Yes | PG&E |  | No | N/A
Dantley Solar | 3549-RD | Still TBD by CAISO | DANTLEY SOLAR, LLC | DANTLEY SOLAR, LLC | 5 | 14629.2 | n/a - R21 | 2026-05-01 | Energy Only | Solar | Yes | PG&E |  | No | N/A
San Leandro 10 | 3556-WD | Still TBD by CAISO | Prologis Energy LLC | Prologis Energy LLC | 1.087 | 3180.3881 | 2024-10-25 | 2026-09-16 | Energy Only | Solar | Yes | PG&E |  | No | N/A
Swainson Solar | 3571-RD | Still TBD by CAISO | SWAINSON SOLAR, LLC | SWAINSON SOLAR, LLC | 5 | 14629.2 | n/a - R21 | 2026-04-06 | Energy Only | Solar | Yes | PG&E |  | No | N/A
Valpredo | 3580-RD | Still TBD by CAISO | ForeFront Power LLC | ForeFront Power LLC | 7.214 | 21107.0098 | 2025-10-27 | 2027-09-17 | Energy Only | Solar | Yes | PG&E |  | No | N/A
Oakland 1 | 3581-WD | Still TBD by CAISO | Prologis Energy LLC | Prologis Energy LLC | 0.725 | 2121.234 | 2024-10-01 | 2026-01-15 | Energy Only | Solar | Yes | PG&E |  | No | N/A
Hayward | 3582-WD | Still TBD by CAISO | Prologis Energy LLC | Prologis Energy LLC | 0.6 | 1755.504 | 2024-10-25 | 2025-11-14 | Energy Only | Solar | Yes | PG&E |  | No | N/A
Saltbush DG Solar | 3588-RD | Still TBD by CAISO | Dynamic Solar and Storage Solutions, LLC | Dynamic Solar and Storage Solutions, LLC | 2.49 | 7285.3416 | n/a - R21 | 2026-12-31 | Energy Only | Solar | Yes | PG&E |  | No | N/A
Royal PV, LLC | 3594-WD | Still TBD by CAISO | Royal PV, LLC | Royal PV, LLC | 4.99 | 14599.9416 | 2025-03-14 | 2026-04-10 | Energy Only | Solar | Yes | PG&E |  | No | N/A
Semi Solar, LLC | 3596-WD | Still TBD by CAISO | Semi Solar, LLC (AKA White Pine Renewables) | Semi Solar, LLC (AKA White Pine Renewables) | 4.99 | 14599.9416 | 2025-03-22 | 2026-10-15 | Energy Only | Solar | Yes | PG&E |  | No | N/A
Pristine Solar, LLC | 3597-WD | Still TBD by CAISO | Pristine Solar, LLC | Pristine Solar, LLC | 4.99 | 14599.9416 | 2025-03-13 | 2026-10-15 | Energy Only | Solar | Yes | PG&E |  | No | N/A
Magenta Solar | 3608-WD | Still TBD by CAISO | MAGENTA SOLAR, LLC, | MAGENTA SOLAR, LLC, | 4.999 | 14626.2742 | 2024-12-23 | 2026-03-20 | Energy Only | Solar | Yes | PG&E |  | No | N/A
Nickel Middle WDAT | 3624-WD | Still TBD by CAISO | BAP (Cenergy) Power Corporation | BAP (Cenergy) Power Corporation | 5.505 | 16106.7492 | 2025-07-03 | 2027-07-01 | Full Capacity | Solar | Yes | PG&E |  | No | N/A
Comet CS, LLC | 3640-WD | Still TBD by CAISO | Comet CS LLC | Comet CS LLC | 9.95 | 29112.108 | 2025-03-17 | 2026-03-26 | Energy Only | Solar | Yes | PG&E |  | No | N/A
Sage Creek | 3643-WD | Still TBD by CAISO | Cenergy Power | Cenergy Power | 5.505 | 16106.7492 | 2025-06-17 | 2026-07-29 | Full Capacity | Solar | Yes | PG&E |  | No | N/A
Opal 2 | 3694-WD | Still TBD by CAISO |  |  | 2 | Not RPS Eligible | 2025-06-30 | 2027-11-10 | Energy Only | Other [See Notes] | No | PG&E | Synchronous Engine | No | N/A
Shafter Wasco ID Solar | 3717-RD | Still TBD by CAISO | SHAFTER-WASCO IRRIGATION DISTRICT | SHAFTER-WASCO IRRIGATION DISTRICT | 0.7 | 2048.088 | n/a - R21 | 2025-09-01 | Energy Only | Solar | Yes | PG&E |  | No | N/A
Fern Creek Rd. Solar | 3722-RD | Still TBD by CAISO | Renewables Properties, LLC | Renewables Properties, LLC | 2 | 5851.68 | 2025-08-23 | 2027-02-24 | Energy Only | Solar | Yes | PG&E |  | No | N/A
Hatchery Road Solar Phase I | 3806-WD | Still TBD by CAISO |  |  | 1.222 | 3575.3765 | 2025-06-22 | 2027-02-12 | Energy Only | Solar | Yes | PG&E |  | No | N/A
Vigneto Solar | 3817-RD | Still TBD by CAISO | CP Development 1, LLC | CP Development 1, LLC | 2.988 | 8742.4099 | n/a - R21 | 2026-02-02 | Energy Only | Solar | Yes | PG&E |  | No | N/A
190 9th Street Rooftop Solar | 3866-WD | Still TBD by CAISO | CITY AND COUNTY OF SAN FRANCISCO | CITY AND COUNTY OF SAN FRANCISCO | 0.083 | 242.8447 | 2024-06-28 | 2025-06-27 | Energy Only | Solar | Yes | PG&E |  | No | N/A
Mission Bay School - Rooftop Solar Array | 3898-WD | Still TBD by CAISO | CITY AND COUNTY OF SAN FRANCISCO | CITY AND COUNTY OF SAN FRANCISCO | 0.1 | 292.584 | 2024-07-15 | 2025-06-27 | Energy Only | Solar | Yes | PG&E |  | No | N/A
0 Potato Rd Arvin | 3983-RD | Still TBD by CAISO | YOU HAD ME AT POTATO LLC | YOU HAD ME AT POTATO LLC | 1.25 | 3657.3 | 2025-03-20 | 2026-02-10 | Energy Only | Solar | Yes | PG&E |  | No | N/A
3200 Dyer Rd, Livermore | 4033-RD | Still TBD by CAISO | NEXTGRID CALIFORNIA HOLDINGS LLC | NEXTGRID CALIFORNIA HOLDINGS LLC | 0 | 0 | n/a - R21 | 2026-07-08 | Energy Only | Solar | Yes | PG&E |  | No | N/A
Covarrubias 1 | 4046-RD | Still TBD by CAISO | SDG BESS, LLC | SDG BESS, LLC | 0.979 | 2864.3974 | n/a - R21 | 2026-09-17 | Energy Only | Solar | Yes | PG&E |  | No | N/A
Covarrubias 2 | 4047-RD | Still TBD by CAISO | SDG BESS, LLC | SDG BESS, LLC | 0.979 | Not RPS Eligible | n/a - R21 | 2026-09-17 | Energy Only | Battery Storage | No | PG&E |  | No | N/A
Covarrubias 3 | 4048-RD | Still TBD by CAISO | SDG BESS, LLC | SDG BESS, LLC | 0.979 | 2864.3974 | n/a - R21 | 2026-09-17 | Energy Only | Solar | Yes | PG&E |  | No | N/A
Forebay Wind | ForebayWindRE | Still TBD by CAISO | Salk Energy | Salk Energy | 13 | 38035.92 | 2026-03-10 | 2026-12-17 |  | Wind | Yes | PG&E | 05/06/25 - Tracking ISD in Q4 2026. Project closely aligned with Zond Wind. | No | N/A
Sandhill B Repower | Q1096 | Still TBD by CAISO | Sand Hill LLC S-Power | Sand Hill LLC S-Power | 5 | 14629.2 | 2025-08-27 | 2025-09-15 | Energy Only | Wind | Yes | PG&E | 04/08/25 - IC needs to submit MMA. IC not engaged for nearly a year. | No | N/A
Fountain Wind | Q1106 | Still TBD by CAISO | ConnectGen LLC | ConnectGen LLC | 200 | 585168 | 2026-01-05 | 2027-09-09 | Fully Deliverable | Wind | Yes | PG&E | 05/05/25 - Current ISD 2027 unachievable. Customer CEQA/EIR CEC Permit process still outstanding. ISD depends on a GIP RAS and construction of new customer built switching station. | No | N/A
Lake Alpaugh BESS & Alpaugh 3 BESS | Q1143 | Still TBD by CAISO | Alpaugh 50, LLC | Alpaugh 50, LLC | 10 | Not RPS Eligible | 2022-09-01 | 2025-10-31 | Fully Deliverable | Battery Storage | No | PG&E | 05/06/25 - Tracking ISD delays. MMA approval required for redesign of ICs point of interconnection | No | N/A
Daylight Project | Q1223 | Still TBD by CAISO | Daylight Legacy Solar, LLC | Daylight Legacy Solar, LLC | 300 | 877752 | 2027-03-10 | 2027-12-23 | Energy Only | Hybrid/Paired Solar and Battery | Yes | PG&E | 05/06/25 - Tracking ISD to Q3 2027 | No | N/A
Pluot | Q1242 | Still TBD by CAISO | Per Chris entity name change has been completed. | Per Chris entity name change has been completed. | 246.4 | 720926.976 | 2026-04-01 | 2026-09-01 | Fully Deliverable | Hybrid/Paired Solar and Battery | Yes | PG&E | 05/06/25 - MMA approval required to extend the ISD to Q3 2026 | No | N/A
Pomegranate | Q1243 | Still TBD by CAISO | Westlands Cherry, LLC | Westlands Cherry, LLC | 249.7 | 730582.248 | 2025-12-08 | 2025-09-30 | Fully Deliverable | Hybrid/Paired Solar and Battery | Yes | PG&E | 05/06/25 - MMA technology change completed on 4/14/25 04/08/25 - MMA submitted for Technology changes. Tracking ISD to Q1 2026. | No | N/A
Kyan Solar | Q1260 | Still TBD by CAISO | EC&R Solar Development, LLC | EC&R Solar Development, LLC | 100 | 292584 | 2026-09-15 | 2027-07-31 | Energy Only | Solar | Yes | PG&E | 05/06/25 - PTO acceleration was completed to plan In-service date (ISD) of: July 3, 2027 | No | N/A
Corby Energy Storage | Q1270 | Still TBD by CAISO | NextEra Energy Resources | NextEra Energy Resources | 300 | Not RPS Eligible | 2024-09-03 | 2026-12-31 | Fully Deliverable | Battery Storage | No | PG&E | 05/19/25 - The breaker delivery and outdoor construction begin in June 2025, with design reviews and orders progressing. No restraints reported, next steps include T-Line 60% design completion and steel structure orders by July 2025. Tracking ISD in Q4 2026 | No | N/A
Kola | Q1275 | Still TBD by CAISO | NextEra Energy Resources | NextEra Energy Resources | 400 | Not RPS Eligible | 2024-06-11 | 2025-07-11 | Fully Deliverable | Battery Storage | No | PG&E | 05/06/25 - ISD tracking July 2025. PG&E UG work at Tesla underway but delayed with expected ISD July 15 2025. 04/08/25 - ISD July 2025, delay due to Tline work schedule and resource constraints including Material delays. 03/11/25 - Tracking ISD in May 2025. Tesla CB642/CB542 PNU remain. Others removed. | No | N/A
Mulqueeny Ranch Wind | Q1277 | Still TBD by CAISO | brookfieldrenewable | brookfieldrenewable | 20 | 58516.8 | 2023-07-21 | 2025-10-15 | Fully Deliverable | Wind | Yes | PG&E |  | No | N/A
Aramis Power Plant | Q1349 | Still TBD by CAISO | IP ARAMIS, LLC | IP ARAMIS, LLC | 100 | 292584 | 2024-06-17 | 2026-03-06 | Fully Deliverable | Hybrid/Paired Solar and Battery | Yes | PG&E | 05/06/25 - The customer has submitted the final design package, which is currently under review. MMA has been submitted. Efforts are underway to adjust ISD from 3/20/26 to 3/06/26. 04/07/25 - Based on customer RFI, project schedule. Follow up with MMA 03/11/25 - Tracking ISD in Dec 2025. IC has requested MMA including milestone & technology changes. Initiated in Feb 2025. | No | N/A
Sandhill C DTTs | Q1363 | Still TBD by CAISO | sPower Development Company | sPower Development Company | 80.8 | 236407.872 | 2025-08-27 | 2025-10-08 | Fully Deliverable | Wind | Yes | PG&E | 05/06/25 - MMA to push out project for a few years. IC needs to submit MMA. IC not engaged for nearly a year. | No | N/A
Gonzaga Wind Farm | Q1378 | Still TBD by CAISO | Gonzaga Ridge Wind Farm, LLC | Gonzaga Ridge Wind Farm, LLC | 76.4 | 223534.176 | 2023-07-03 | 2025-12-18 | Fully Deliverable | Hybrid | Yes | PG&E | [Type] = Wind Turbine + Battery 05/06/25 - Tracking ISD to Q4 2025. Tline material ordered Oct 2024 with Q3 2025 delivery. IC Delays: At risk, IC's design not complete. Construction needs to start Q2 2025. Low confidence ISD in 2025. | No | N/A
Heartland 1 | Q1379 | Still TBD by CAISO | Heartland Solar 1, LLC | Heartland Solar 1, LLC | 150 | 438876 | 2027-11-16 | 2028-11-07 | Energy Only | Solar | Yes | PG&E | 05/06/25 - Tracking ISD to Q3/Q4 2028. LLM (CBs) in July 2026. The IC team is still in beginning stages of design. | No | N/A
Heartland 2 | Q1380 | Still TBD by CAISO | Heartland Solar 1, LLC | Heartland Solar 1, LLC | 150 | 438876 | 2028-06-20 | 2028-10-25 | Energy Only | Solar | Yes | PG&E | 05/06/25 - Tracking ISD to Q3/Q4 2028. LLM (CBs) in July 2026. The IC team is still in beginning stages of design. | No | N/A
Las Camas 1 | Q1382 | Still TBD by CAISO | EDPR | EDPR | 100 | 292584 | 2025-01-13 | 2026-07-17 | Fully Deliverable | Solar | Yes | PG&E | 05/06/25 - MMA required to push ISD to Q3 2026 | No | N/A
Redux Solar | Q1389 | Still TBD by CAISO | SAN LUIS WEST SOLAR, LLC | SAN LUIS WEST SOLAR, LLC | 125 | 365730 | 2022-01-31 | 2026-08-21 | Fully Deliverable | Hybrid/Paired Solar and Battery | Yes | PG&E | 05/05/25 - MMA submitted for ISD and technology changes. Tracking ISD to Q2 2026. Customer moved POCO pole location multiple times. Customer started gentie route design. Customer submitted IDP and accepted. Customer's POCO location changes delayed PG&E's T-line design which includes 5 spans, 2 H frames, 2 TSPs. | No | N/A
Sonrisa | Q1391 | Still TBD by CAISO | EDPR | EDPR | 200 | 585168 | 2024-02-14 | 2026-03-27 | Fully Deliverable | Hybrid/Paired Solar and Battery | Yes | PG&E | 05/06/25 -IC design delays. PGE deliverables already completed by Q1135 Scarlet ISD tracking to Q1 2026 | No | N/A
Driftwood Stella | Q1394 | Still TBD by CAISO | EDPR | EDPR | 200 | 585168 | 2023-08-02 | 2026-04-27 | Energy Only | Hybrid/Paired Solar and Battery | Yes | PG&E | 05/06/25 - Tracking ISD to April 2026. IC late on deliverables | No | N/A
Ajo Power Bank | Q1442 | Still TBD by CAISO | Calpine Corporation | Calpine Corporation | 120 | Not RPS Eligible | 2026-12-16 | 2027-03-18 | Fully Deliverable | Battery Storage | No | PG&E | 05/06/25 - MMA required to move ISD on resuming project. Suspension ends April 2026 9/18/23 - Q1705 suspended and should return March 2024. | No | N/A
Angela (Angiola East) | Q1443 | Still TBD by CAISO | Angiola East | Angiola East | 40 | 117033.6 | 2021-10-19 | 2025-12-17 | Fully Deliverable | Hybrid/Paired Solar and Battery | Yes | PG&E | 05/06/25 - MMA submitted, ISD 10/15/2025, COD 12/15/2025. Tracking ISD in Dec 2025. IC design is delayed. IC in construction at risk to complete in 2025 | No | N/A
Saloon Energy Storage Project | Q1444 | Still TBD by CAISO | Qcells USA Corp | Qcells USA Corp | 150 | 438876 | 2025-10-31 | 2027-07-27 | Partially Deliverable | Hybrid/Paired Solar and Battery | Yes | PG&E | 05/06/25 - Tracking ISD in Q2 2027 | No | N/A
Hummingbird Energy Storage | Q1454 | Still TBD by CAISO | esVolta | esVolta | 75 | Not RPS Eligible | 2022-01-12 | 2025-08-26 | Fully Deliverable | Battery Storage | No | PG&E | 05/05/25 - CAISO required MMA has been submitted and is under review; however, IC is exploring coming on-line without the Cap bank but delivery is expected early May. This would require further RFI and an MMA modification. PGE will submit PPI and clearance scheduled once MMAs are final. Realistic ISD is July/Aug. 04/08/25 - Still waiting on the IC to fulfill construction scope pertaining to NGR needed to safely connect to grid. MMA to delay is likely if IC delays fulfilling scope requirements. | No | N/A
Janus | Q1455 | Still TBD by CAISO | JANUS SOLAR PV, LLC | JANUS SOLAR PV, LLC | 80 | 234067.2 | 2022-07-25 | 2026-06-30 | Fully Deliverable | Hybrid/Paired Solar and Battery | Yes | PG&E | 05/06/25 - Tracking ISD to Q2 2026 due to IC permitting. | No | N/A
Las Camas 3 | Q1456 | Still TBD by CAISO | EDP | EDP | 100 | 292584 | 2025-01-13 | 2026-07-17 | Fully Deliverable | Solar | Yes | PG&E |  | No | N/A
Mulqueeney Ranch Wind 2 | Q1459 | Still TBD by CAISO | Gridbright | Gridbright | 60 | 175550.4 | 2025-08-04 | 2025-10-15 | Fully Deliverable | Wind | Yes | PG&E | 05/06/25 - Tracking ISD to Jun 2026 attributed to 20rsmt-5 Tesla CB612. | No | N/A
Reclaimed Wind | Q1461 | Still TBD by CAISO | Viracocha Wind LLC for Reclaimed Wind, LLC | Viracocha Wind LLC for Reclaimed Wind, LLC | 90.7 | 265373.688 | 2025-12-04 | 2026-08-24 | Partially Deliverable | Wind | Yes | PG&E | 05/06/25 - Tracking ISD in Q3 2026 attributed to customer POI change | No | N/A
Key Storage 1 | Q1479 | Still TBD by CAISO | NextEra Energy Resources | NextEra Energy Resources | 300.1 | Not RPS Eligible | 2024-02-20 | 2026-06-01 | Fully Deliverable | Battery Storage | No | PG&E | 05/06/25 - Customer wants to relocate Metering from existing drawings. RFI needed to relocate meters. Tracking ISD in Jun 2026 | No | N/A
Azalea | Q1493 | Still TBD by CAISO | SF AZALEA, llc | SF AZALEA, llc | 60 | 175550.4 | 2023-04-10 | 2025-05-20 | Partially Deliverable | Hybrid/Paired Solar and Battery | Yes | PG&E | 05/06/25 - Customer moved ISD to May 2025. | No | N/A
Chalan Solar | Q1495 | Still TBD by CAISO | Origis Operating Services, LLC | Origis Operating Services, LLC | 64.9 | 189887.016 | 2023-05-01 | 2026-03-24 | Fully Deliverable | Hybrid/Paired Solar and Battery | Yes | PG&E | 05/06/25 - MMA submitted to change ISD and Technology. With PGE for Round 4 review. Tracking ISD to Dec 2025 with risk to complete in 2025. | No | N/A
Descendant Ranch 1 | Q1496 | Still TBD by CAISO | NextEra Energy Resources | NextEra Energy Resources | 500 | 1462920 | 2026-01-30 | 2028-08-08 | Partially Deliverable | Hybrid/Paired Solar and Battery | Yes | PG&E | 05/06/25 - IC is suspending project. Notice from IC that they are behind an affected system (TANC) with estimated cost of of $50M and 5Yr Duration. Asks to cease all work on IF & IRNUs. At risk to withdraw. | No | N/A
Jasmine Solar | Q1499 | Still TBD by CAISO | SF Jasmine, LLC | SF Jasmine, LLC | 70 | 204808.8 | 2025-03-31 | 2026-10-13 | Partially Deliverable | Hybrid/Paired Solar and Battery | Yes | PG&E | 05/06/25 - Project sold to new IC. Potential ISD impact. | No | N/A
Prospect Energy | Q1507 | Still TBD by CAISO | PG&E | PG&E | 49.9 | Not RPS Eligible | 2027-12-13 | 2028-04-18 | Fully Deliverable | Battery Storage | No | PG&E | 05/06/25 - Updated ISD in schedule. MMA has been requested. 02/10/25 - IC need to submit new MMA and schedule 11/20/24 - ISD must be moved out on resuming project. Project was due to return in Oct 2024 but has not. | No | N/A
Irving Storage | Q1539 | Still TBD by CAISO | Dynegy Power Generation Inc | Dynegy Power Generation Inc | 750 | Not RPS Eligible | 2026-08-03 | 2027-11-19 | Fully Deliverable | Battery Storage | No | PG&E | 05/06/25 - Tracking ISD to late 2027. MMA required to adjust to earliest ISD | No | N/A
Tanager Energy Storage | Q1550 | Still TBD by CAISO | Tenasca Energy Holdings | Tenasca Energy Holdings | 200 | Not RPS Eligible | 2026-06-23 | 2027-08-31 | Fully Deliverable | Battery Storage | No | PG&E | 05/06/25 - 1/1/2025 ISD,4/1/2025 COD, Tracking to Q3 2027 attributed to IC has no site control | No | N/A
Cormorant Storage | Q1552 | Still TBD by CAISO | Arvon | Arvon | 250 | Not RPS Eligible | 2026-01-16 | 2027-03-02 | Fully Deliverable | Battery Storage | No | PG&E | 05/06/25 - Location problem for POCO, estimated solution for August to confirm location for POCO | No | N/A
Noosa Energy Storage | Q1557 | Still TBD by CAISO | ENGIE | ENGIE | 99 | Not RPS Eligible | 2023-12-08 | 2025-09-24 | Fully Deliverable | Battery Storage | No | PG&E | 05/05/25 - Tracking 9/24. MMA due 5/19 to be approved by PTO | No | N/A
Dynamo Solar | Q1565 | Still TBD by CAISO | DYNAMO SOLAR LLC | DYNAMO SOLAR LLC | 24.5 | 71683.08 | 2026-01-06 | 2025-10-10 | Fully Deliverable | Solar | Yes | PG&E | 05/06/25 - Tracking ISD to Q3 2026 due to IC CEQA process related delays. | No | N/A
Arcturus | Q1586 | Still TBD by CAISO | Recurrent Energy | Recurrent Energy | 0 | 0 | 2026-10-08 | 2028-03-10 | Energy Only | Hybrid/Paired Solar and Battery | Yes | PG&E | 04/08/25 - Q1586 withdrawing 02/03/25 - IC has not started on their third financial posting delaying PG&E ability to proceed with procurements and key deliverables due to no project TPD allocation. | No | N/A
Kingsroad Hybrid Solar | Q1587 | Still TBD by CAISO | Sonoma Reliability Project LLC | Sonoma Reliability Project LLC | 100 | 292584 | 2026-06-03 | 2026-07-24 | Energy Only | Hybrid/Paired Solar and Battery | Yes | PG&E | 05/06/25 - MMA needed to move out ISD. ISD TBD. IC CB on order, IC working through permitting. | No | N/A
Pelicans Jaw Hybrid Solar | Q1593 | Still TBD by CAISO | SB Energy | SB Energy | 500 | 1462920 | 2024-12-16 | 2026-05-01 | Partially Deliverable | Hybrid/Paired Solar and Battery | Yes | PG&E | 05/06/25 - MMA submitted 04/08/25 - ISD tracking May 2026 | No | N/A
Buttonbush Solar Hybrid Energy Center | Q1596 | Still TBD by CAISO | 29SC 8ME LLC | 29SC 8ME LLC | 800 | 2340672 | 2024-10-01 | 2026-11-05 | Fully Deliverable | Hybrid/Paired Solar and Battery | Yes | PG&E | 05/05/25 - MMA submitted to change ISD and Technology. With ISO for engineering review and approval. Tracking ISD in Nov 2026 | No | N/A
Aqueduct Energy Storage | Q1683 | Still TBD by CAISO | Aqueduct Energy Storage LLC | Aqueduct Energy Storage LLC | 100 | Not RPS Eligible | 2025-02-04 | 2026-01-18 | Energy Only | Battery Storage | No | PG&E |  | No | N/A
VESI 17 LLC (Denali Energy Storage) | Q1690 | Still TBD by CAISO | VESI 17 LLC | VESI 17 LLC | 101.2 | Not RPS Eligible | 2025-01-30 | 2028-07-30 | Partially Deliverable | Battery Storage | No | PG&E |  | No | N/A
North Bay Energy Storage | Q1700 | Still TBD by CAISO | Bollero ES LLC | Bollero ES LLC | 0 | Not RPS Eligible | withdrawn | 2027-06-29 | Energy Only | Battery Storage | No | PG&E | 06/12/25 - project is withdrawn | No | N/A
Potentia-Viridi | Q1702 | Still TBD by CAISO | Capstone Infrastructure | Capstone Infrastructure | 400 | 1170336 | 2026-04-22 | 2028-03-30 | Fully Deliverable | Hybrid | Yes | PG&E | [Type] = Wind Turbine + Solar 05/06/25 - Changed ISD to match contractual date pending PG&E and customer Project Sequencing coordination. | No | N/A
Steel City Battery Storage | Q1705 | Still TBD by CAISO | STEEL CITY ENERGY STORAGE, LLC | STEEL CITY ENERGY STORAGE, LLC | 220 | Not RPS Eligible | 2027-05-11 | 2029-01-01 | Energy Only | Battery Storage | No | PG&E | 05/06/25 - MMA required to move ISD on resuming project. 9/18/23 - Q1705 suspended and should return March 2024. | No | N/A
Rosemary | Q1709 | Still TBD by CAISO | #REF! | #REF! | 35 | 102404.4 | TBD | 2027-12-03 | Fully Deliverable | Hybrid/Paired Solar and Battery | Yes | PG&E | 05/06/25 - Tracking to Dec 2027 | No | N/A
BIA Bess 1 | Q1713 | Still TBD by CAISO | Middle River Power | Middle River Power | 32 | Not RPS Eligible | 2025-04-07 | 2025-05-22 | Fully Deliverable | Battery Storage | No | PG&E | 05/06/25 - The customer's control room building delay construction activities. PG&E comms depend on IC construction schedule. PM indicated July energization date | No | N/A
Gonzaga Hybrid | Q1718 | Still TBD by CAISO | Gonzaga Ridge Wind Farm | Gonzaga Ridge Wind Farm | 103.65 | 303263.316 | 2025-08-13 | 2025-11-03 | Fully Deliverable | Hybrid | Yes | PG&E | [Type] = Wind Turbine + Battery 05/06/25 - Tracking ISD to Q3 2026. Connects behind Gonzaga Wind. Low confidence ISD in 2025. | No | N/A
Zeta | Q1728 | Still TBD by CAISO | Long Road Energy | Long Road Energy | 75 | 219438 | 2025-09-01 | 2027-05-26 | Fully Deliverable | Hybrid/Paired Solar and Battery | Yes | PG&E | 05/06/25 - Tracking ISD Q2 2027. Potential Impact due to TPP PNU Oro Loma 70kV Reinforcement dependency with Q1 2028 ISD. | No | N/A
Crystal Flats | Q1744 | Still TBD by CAISO | #REF! | #REF! | 100 | 292584 | 2026-06-15 | 2030-10-12 | Energy Only | Hybrid/Paired Solar and Battery | Yes | PG&E | 05/06/25 - IC non-responsive to meetings. ISD shown is IA ISD. Real ISD TBD. | No | N/A
Windwalker Offshore | Q1750 | Still TBD by CAISO | Ocean Winds | Ocean Winds | 1000 | 2925840 | 2027-07-23 | 2028-03-27 | Fully Deliverable | Wind | Yes | PG&E | 05/06/25 - IC delays due to Gentie route acquisitions and permitting. | No | N/A
Winston Hybrid PV And BESS | Q1751 | Still TBD by CAISO | #REF! | #REF! | 200 | 585168 | TBD | 2030-10-12 | Fully Deliverable | Hybrid/Paired Solar and Battery | Yes | PG&E | 05/06/25 - PM assigned | No | N/A
Seahawk Storage (Sequoia Energy Storage 1 LLC) | Q1865 | Still TBD by CAISO | SEQUOIA ENERGY STORAGE 1, LLC | SEQUOIA ENERGY STORAGE 1, LLC | 200 | Not RPS Eligible | 2025-03-24 | 2029-06-30 | Fully Deliverable | Battery Storage | No | PG&E |  | No | N/A
Double Springs Energy Storage (Double Springs Energy Storage, LLC) | Q1876 | Still TBD by CAISO | Double Springs Energy Storage, LLC, | Double Springs Energy Storage, LLC, | 100 | Not RPS Eligible | 2025-05-24 | 2028-04-18 | Fully Deliverable | Battery Storage | No | PG&E |  | No | N/A
Presidio (Presidio Renewables LLC) | Q1887 | Still TBD by CAISO | Presidio Renewables LLC | Presidio Renewables LLC | 350 | 1024044 | TBD | 2030-11-04 | Fully Deliverable | Hybrid/Paired Solar and Battery | Yes | PG&E |  | No | N/A
Pathfinder Storage (Pathfinder BESS, LLC) | Q1896 | Still TBD by CAISO | Pathfinder BESS, LLC | Pathfinder BESS, LLC | 260 | Not RPS Eligible | 2024-04-16 | 2031-04-18 | Fully Deliverable | Battery Storage | No | PG&E |  | No | N/A
Golden Flats (NextEra Energy Resources Interconnection Holdings, LLC) | Q1903 | Still TBD by CAISO | Lock Energy Center, LLC | Lock Energy Center, LLC | 300 | Not RPS Eligible | 2025-08-30 | 2031-10-28 | Fully Deliverable | Battery Storage | No | PG&E |  | No | N/A
Expresso | Q1912 | Still TBD by CAISO | NextEra Energy Resources Interconnection Holdings, LLC, | NextEra Energy Resources Interconnection Holdings, LLC, | 300 | Not RPS Eligible | 2025-06-13 | 2031-04-18 | Fully Deliverable | Battery Storage | No | PG&E |  | No | N/A
Zeus BESS LLC (Zeus BESS) | Q1920 | Still TBD by CAISO | Zeus BESS LLC | Zeus BESS LLC | 200 | Not RPS Eligible | 2024-04-25 | 2031-07-31 | Fully Deliverable | Battery Storage | No | PG&E |  | No | N/A
Allium Hybrid (Allium Hybrid, LLC) | Q1921 | Still TBD by CAISO | Allium Hybrid, LLC | Allium Hybrid, LLC | 110 | 321842.4 | 2025-07-05 | 2030-09-19 | Fully Deliverable | Hybrid/Paired Solar and Battery | Yes | PG&E |  | No | N/A
Alta Casa Storage (Alta Casa BESS, LLC) | Q1922 | Still TBD by CAISO | Alta Casa BESS, LLC, | Alta Casa BESS, LLC, | 500 | Not RPS Eligible | TBD | 2031-04-21 | Fully Deliverable | Battery Storage | No | PG&E |  | No | N/A
Apache Storage (Apache Energy Storage 1 LLC) | Q1930 | Still TBD by CAISO | Apache Energy Storage 1, LLC | Apache Energy Storage 1, LLC | 200 | Not RPS Eligible | 2025-03-19 | 2029-02-18 | Fully Deliverable | Battery Storage | No | PG&E |  | No | N/A
Cougar Storage (Cougar Energy Storage 1, LLC) | Q1932 | Still TBD by CAISO | New Leaf Energy | New Leaf Energy | 200 | Not RPS Eligible | 2025-04-22 | 2030-06-18 | Fully Deliverable | Battery Storage | No | PG&E |  | No | N/A
Elysian (RE Elysian LLC) | Q1935 | Still TBD by CAISO | RE ELYSIAN LLC | RE ELYSIAN LLC | 200 | 585168 | 2025-04-20 | 2029-09-18 | Fully Deliverable | Hybrid/Paired Solar and Battery | Yes | PG&E |  | No | N/A
Darden Hybrid Solar | Q1949 | Still TBD by CAISO | IP Renewable Energy Holdings LLC | IP Renewable Energy Holdings LLC | 1150 | 3364716 | 2027-01-19 | 2030-11-18 | Fully Deliverable | Hybrid/Paired Solar and Battery | Yes | PG&E | 05/06/25 - Customer wants to move date forward. Earliest backfeed Q1, 2031 pending mitigations for Network Upgrades, C14P2-FGR04 - Los Banos 500 kV circuit breakers 822, 832 & 842 overstress, Q1 2031 ISD, C14P1-KGR11 - Midway 500 kV CB 742, 912, 942 Overstress beyond 50 kA Q1 2031 ISD. PG&E will uprate Midway breakers and Los Banos Breakers CB822 & 832 and must replacce CB842. Breaker ordered by Material Purchase Program. ISDs to be determined once design is complete. 04/08/25 - Tracking ISD to Q3 2030 with no current delays | No | N/A
Australis | Q1952 | Still TBD by CAISO | Volta Solar LLC, | Volta Solar LLC, | 300 | 877752 | 2025-06-24 | 2030-10-18 | Fully Deliverable | Hybrid/Paired Solar and Battery | Yes | PG&E |  | No | N/A
Huaso Hybrid (CA SB 4, LLC) | Q1954 | Still TBD by CAISO | CA SB 4, LLC | CA SB 4, LLC | 100 | 292584 | 2025-07-22 | 2026-12-14 | Fully Deliverable | Hybrid/Paired Solar and Battery | Yes | PG&E |  | No | N/A
Ciervo Mountain Hybrid (CA GP SB 3, LLC) | Q1955 | Still TBD by CAISO | CA GP SB, LLC | CA GP SB, LLC | 125 | 365730 | 2025-05-06 | 2029-04-18 | Fully Deliverable | Hybrid/Paired Solar and Battery | Yes | PG&E |  | No | N/A
Sequoia (Clarkson) | Q1956 | Still TBD by CAISO | Clearway Energy | Clearway Energy | 200 | 585168 | 2026-12-02 | 2027-04-12 | Fully Deliverable | Hybrid/Paired Solar and Battery | Yes | PG&E | 05/06/25 - PM assigned | No | N/A
Spikes Peak Solar (Spikes Peak Solar, LLC) | Q1958 | Still TBD by CAISO | Spikes Peak Solar, LLC | Spikes Peak Solar, LLC | 150 | 438876 | 2025-07-04 | 2029-08-28 | Fully Deliverable | Hybrid/Paired Solar and Battery | Yes | PG&E |  | No | N/A
Cornucopia Hybrid (Cornucopia Hybrid LLC) | Q1959 | Still TBD by CAISO | Cornucopia Hybrid, LLC | Cornucopia Hybrid, LLC | 300 | 877752 | 2025-11-03 | 2030-08-18 | Fully Deliverable | Hybrid/Paired Solar and Battery | Yes | PG&E |  | No | N/A
Lock Storage (Lock Energy Center, LLC) | Q1962 | Still TBD by CAISO | NextEra Energy Resources Interconnection Holdings, LLC | NextEra Energy Resources Interconnection Holdings, LLC | 500.01 | Not RPS Eligible | 2025-08-30 | 2027-10-15 | Fully Deliverable | Battery Storage | No | PG&E |  | No | N/A
Peaceful Hollow BESS (CED Solar Development LLC) | Q1973 | Still TBD by CAISO | CED Solar Development, LLC | CED Solar Development, LLC | 75 | 219438 | 2025-03-14 | 2027-10-18 | Fully Deliverable | Solar | Yes | PG&E |  | No | N/A
Los Esteros Critical Energy Facility BESS | Q378 | Still TBD by CAISO | Los Esteros Critical Energy Facility, LLC | Los Esteros Critical Energy Facility, LLC | 120 | Not RPS Eligible | On-hold by IC | 2027-10-06 | Fully Deliverable | Hybrid | No | PG&E | [Type] = Natural Gas + Battery 11/20/24 - EGI should cancel this project scope. | No | N/A
Apparent First Hybrid Project | Q653F | Still TBD by CAISO | Silverado Power | Silverado Power | 0 | 0 | 2017-02-13 | 2024-09-30 | Energy Only | Hybrid/Paired Solar and Battery | Yes | PG&E | 10/09/24 - proceeding to termination. 3/4/24 - Customer is in default ending 4/8. If we terminate them, we need to retain funds to remove equipment and reverse the design. 11/1/23 - ISD Tracking 10/2/23 - MMA #5 IC wants New ISD to be 4/1/24 8/7/23 - IC wants to delay to middle of 2024. Minimal Team now supporting. 5/22/23 - IC is a-wol. Need EGI IM support | No | N/A
Lassen Lodge Hydroelectric Project | Q720 | Still TBD by CAISO |  |  | 0 | 0 | On-hold by IC | 2025-03-31 | Energy Only | Conduit Hydro | Yes | PG&E | 11/20/24 - EGI should cancel this project scope. 11/28/23 - was this actually withdrawn | No | N/A
Redwood Solar - Phase 5 | Q744 | Still TBD by CAISO | sPower Development Company | sPower Development Company | 0 | 0 | 2021-01-04 | 2024-03-01 | Partially Deliverable | Solar | Yes | PG&E | 05/15/23 - Signal to the IM that this project needs to re-engage 6 months prior to the new COD date. | No | N/A
Zond (Santa Clara) | SantaClaraWindRE | Still TBD by CAISO | Salk Energy | Salk Energy | 21.3 | 62320.392 | 2025-07-29 | 2026-10-02 |  | Wind | Yes | PG&E | 05/06/25 - Tracking ISD to Q3 2026. Project closely aligned with Forebay Wind. Third party Telco dependencies. IC still on delay schedule, new IC project management team in transistion. IC needs to submit new schedule. Customer gensite activities running late with dependencies mostly on AT&T/Control Building readiness | No | N/A

## Stats1 (hidden)
Autocalculated Stats
Transmission Projects | Delay Resolver |  | In-service Date Change Reason
| Total Number | Percentage | Total Number | Percentage | Average Delay (Days) | Median Delay (Days) | Dependent Resources Total | Dependent Resources (MW) | Dependent Resources At Risk | Dependent Resources Delayed
Total Number | Utility |  | Bundling Dependencies
647 | 0 | #DIV/0! | 0 | #DIV/0! | #DIV/0! | #NUM! | #REF! | 0 | 0 | #REF!
Total Number Delayed | Customer |  | Clearances
369 | 0 | #DIV/0! | 0 | #DIV/0! | #DIV/0! | #NUM! | #REF! | 0 | 0 | #REF!
Percent Delayed | Developer |  | Completed Early
57.03% | 0 | #DIV/0! | 0 | #DIV/0! | -- | -- | #REF! | 0 | -- | --
Average Delay (Days) | CAISO |  | Financing
965.6369 | 0 | #DIV/0! | 0 | #DIV/0! | #DIV/0! | #NUM! | #REF! | 0 | 0 | #REF!
Median Delay (Days) | CPUC |  | ISO Action
320 | 0 | #DIV/0! | 0 | #DIV/0! | #DIV/0! | #NUM! | #REF! | 0 | 0 | #REF!
| Agency - Federal |  | Land Rights
| 0 | #DIV/0! | 0 | #DIV/0! | #DIV/0! | #NUM! | #REF! | 0 | 0 | #REF!
| Agency - Local |  | Material
| 0 | #DIV/0! | 0 | #DIV/0! | #DIV/0! | #NUM! | #REF! | 0 | 0 | #REF!
| Agency - State |  | Outage
| 0 | #DIV/0! | 0 | #DIV/0! | #DIV/0! | #NUM! | #REF! | 0 | 0 | #REF!
Permitting (CPUC/CEQA)
|  |  | 0 | #DIV/0! | #DIV/0! | #NUM! | #REF! | 0 | 0 | #REF!
Permitting (non-CPUC/CEQA)
|  |  | 0 | #DIV/0! | #DIV/0! | #NUM! | #REF! | 0 | 0 | #REF!
Project Design
|  |  | 0 | #DIV/0! | #DIV/0! | #NUM! | #REF! | 0 | 0 | #REF!
Supply Chain Delays
|  |  | 0 | #DIV/0! | #DIV/0! | #NUM! | #REF! | 0 | 0 | #REF!
Vendor Quality/Delays
|  |  | 0 | #DIV/0! | #DIV/0! | #NUM! | #REF! | 0 | 0 | #REF!
Weather
|  |  | 0 | #DIV/0! | #DIV/0! | #NUM! | #REF! | 0 | 0 | #REF!
Workforce Availability
|  |  | 0 | #DIV/0! | #DIV/0! | #NUM! | #REF! | 0 | 0 | #REF!

## Stats2 (hidden)
Autocalculated Stats
Transmission Projects' Dependent Resource Capacity
Transmission Project Name | Transmission Project Unique ID #1 | Project is Delayed | In-service Date Change Reason | Sum of Dependent Resource Capacity (MW) | Dependent Resource Capacity 1 | Dependent Resource Capacity 2 | Dependent Resource Capacity 3 | Dependent Resource Capacity 4 | Dependent Resource Capacity 5 | Dependent Resource Capacity 6 | Dependent Resource Capacity 7 | Dependent Resource Capacity 8 | Dependent Resource Capacity 9 | Dependent Resource Capacity 10 | Dependent Resource Capacity 11 | Dependent Resource Capacity 12 | Dependent Resource Capacity 13 | Dependent Resource Capacity 14 | Dependent Resource Capacity 15 | Dependent Resource Capacity 16 | Dependent Resource Capacity 17 | Dependent Resource Capacity 18 | Dependent Resource Capacity 19 | Dependent Resource Capacity 20
Wheeler Ridge Junction Substation (Casa Loma) | 5523422 | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | No | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | No | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | No | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | No | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | No | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | No | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | No | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | No | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | No | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | No | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | No | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | No | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | No | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | No | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | No | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | No | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | No | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | No | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | No | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | No | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | No | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | No | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | No | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | No | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | No | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | No | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | No | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | No | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | No | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | No | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | No | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | No | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | No | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | No | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | No | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | No | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | No | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | No | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | No | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | No | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | No | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | No | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | No | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | No | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | No | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | No | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | No | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | No | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | No | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | No | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | No | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | No | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | No | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | No | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | No | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | No | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | No | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | No | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | No | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | No | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | No | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | No | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | No | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | No | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | No | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | No | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | No | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | No | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | No | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | No | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | No | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | No | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | No | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | No | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | No | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | No | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | No | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | No | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | No | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | No | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | No | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | No | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | No | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | No | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | No | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | No | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | No | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | No | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | No | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | No | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | Yes | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!