## Instructions
Instructions for 2025 SB 1174 Reporting
Pursuant to SB 1174 (Hertzberg, Stat. 2022, Ch. 229) and Pub. Util. Code § 399.13(a)(2)(B), electrical corporations that own transmission facilities are required to provide information within their RPS Procurement Plans detailing the impact that delays to transmission facilities and network system upgrades have had on renewable energy and energy storage resources with executed interconnection agreements. Electrical corporations shall use this template to report the related data. Electrical corporations shall complete all fields in: 1. Transmission Delay Reporting tab: - List all "in-development" transmission projects, and all projects that have become operational between January 1, 2020 and March 31, 2025. - For each transmission project list all in-development renewable energy and energy storage resources (with an executed interconnection agreement) that depend on the project. 2. Generation Reporting tab: - List every renewable energy and energy storage resource (with executed interconnection agreements) currently in the CAISO, WDAT, or other interconnection queues. Electrical corporations shall list each “transmission project” that is: 1. A CAISO-approved or utility self-approved transmission project, interconnection project, or network upgrade needed for generator interconnection; 2. Delayed OR not delayed (i.e. do not consider delay when listing projects); and 3. “In development”, meaning the project has commenced, but is not yet in-service OR became operational between January 1, 2020 and March 31, 2025. Please do not alter the contents of any tabs except the two listed above. Thank you!
"1. Transmission Delay Reporting" TAB
Section 1: TRANSMISSION PROJECT DETAILS
Field # | Project Data Field | Input Format | Input Example | Input Description
1 | Transmission Project Name | Text string. | Manzanita Substation | Project's name at the date of filing this report. Identify all prior project names and alternative names currently used in different venues, including the name as approved and included in the CAISO's TPP.
2 | Transmission Project Unique ID #1 | Text string. | 78493 | Unique identification (ID) code(s) or number(s) for transmission project. Most specific (PG&E = Planning Order, SCE = SCE ID, SDG&E = Project ID).
3 | Transmission Project Unique ID #2 | Text string. | 432 | Unique identification (ID) code(s) or number(s) for transmission project. Less specific (PG&E = T.dot, SCE = Capital Work Breakdown Structure, SDG&E = Budget Code).
4 | Transmission Project Unique ID #3 | Text string. | 92 | Unique identification (ID) code(s) or number(s) for transmission project. Least specific (PG&E = Major Work Category, SCE = Project Identification Number , SDG&E = N/A)
5 | Description | Text string. | Repairs the transmission line connecting 4th and Townsend to the East Northfork station which failed due to the 2019 San Clemente Hedge Fire. | Brief project summary, including assets to be installed.
6 | Status | Drop-down menu selection. | Construction (10%-25%) | See drop-down menu. Indicate the status of the project.
7 | Operational Date | Date, formatted YYYY-MM-DD; N/A if not yet operational. | 2025-08-15 | If "Operational" was chosen in the "Status" field, then indicate the date the project became operational. If the project is already in-service, then this date should match the "Planned or Actual In-service Date". If not Operational, indicate "N/A".
8 | Latitude | Number (decimal), separated by "¦" for multiple locations; N/A if no geolocation. | 20.234 ¦ 19.983 | Positive number indicates north of equator.
9 | Longitude | Number (decimal), separated by "¦" for multiple locations; N/A if no geolocation. | -132.018 ¦ -132.231 | Negative number indicates west of Prime Meridian.
10 | Location | Text String, with comma between City and County. Multiple entries separated by "¦". Order of values consistent with latitude and longitude. | Berkeley, Alameda ¦ Concord, Contra Costa | All Cities and Counties included in the scope of the project.
11 | CAISO Study Area | Drop-down menu selection. | PG&E: Central Coast & Los Padres Areas | See drop-down menu. Study Areas based on CAISO 25-26 Transmission Planning Process (TPP)
12 | GIDAP Related | Drop-down menu selection. | Yes | Generator Interconnection and Deliverability Allocation Procedures (GIDAP). Is this transmission project a network upgrade associated with specific projects in the queue? (Yes/No)
13 | Year Expected to be Considered in CAISO TPP | Years, formatted YYYY and separated by "¦", or N/A. | 2025 | If not yet considered in the CAISO TPP, indicate the year when it is expected to be considered in the CAISO TPP.
14 | Project Dependencies | Number (whole) indicating required projects' Transmission Project Unique ID #(s), separated by "¦" as necessary. | 235435 ¦ 432787 | Identify all other projects (Transmission Project Unique ID #1) in the spreadsheet that this project depends on and/or whose construction will be bundled with this project.
15 | Action Taken | Drop-down menu selection. | Upgrade/Retrofit | See drop-down menu. If two or more options are required, select "Multiple Options" and provide remaining responses, pipe-delimited, in "Notes" field. If the purpose or purpose details relates to complying with a NERC, WECC, or CAISO requirement, list specific standard(s), requirement(s), and/or any contingencies that are being addressed.
16 | Purpose | Drop-down menu selection. | Reliability | See drop-down menu. In the "Notes" field, please explain a purpose identified as "Other" or provide details on the purpose identified.
17 | Purpose Details | Drop-down menu selection. | Age/Condition - Anti Climb Guards | See drop-down menu. If the purpose details is to comply with a NERC, WECC, or CAISO requirement, list the standard, requirement, and/or any contingencies that are being addressed in the "Notes" field.
18 | Transmission Project Size | Number (decimal), or N/A. | 42.66 | Miles of transmission power lines included in the project.
19 | Substation Project Footprint | Number (decimal), or N/A. | 12.25 | Acres of substation footprint included in the project.
20 | Transmission Voltage Level | Number (whole), separated by "¦" as necessary, or N/A. | 230 | Use kV for transmission power lines ratings.
21 | Substation or Transformer Capacity | Text String, separated by "¦" as necessary, or N/A if unrelated. | 115kV | Use MVA and/or kV for substations.
Section 2: TRANSMISSION PROJECT VARIANCES
Field # | Project Data Field | Input Format | Input Example | Input Description
22 | Planned or Actual Construction Start Date | Date, formatted YYYY-MM-DD. | 2024-12-15 | At the time the data was extracted from the utility’s database(s) as provided in Section 2.1.5 of the Transmission Project Review Process Description. If the project has not been delayed, the original and current construction dates should match.
23 | Original In-service Date | Date, formatted YYYY-MM-DD. | 2025-06-01 | The expected in-service start date when the project was first approved. Look to the following prioritized sources to identify the Original In-service Date: 1) CAISO transmission plans; 2) Transmission Project Review Process data (Resolution E-5252 Attach B); 3) Transmission Development Forum "In-service Date at Approval in Transmission Plan" date; or 4) Internal utility project approval dates, including the first approved business case.
24 | Planned or Actual In-service Date | Date, formatted YYYY-MM-DD. | 2021-01-01 | At the time the data was extracted from the utility’s database(s) as provided in Section 2.1.5 of the Transmission Project Review Process Description. If the project has not been delayed, the original and current in-service dates should match.
25 | Original In-service Date Source | Text string. | CAISO Transmission Plan | Identify the source used to determine the "Original In-service Date". See the "Original In-service Date" field description and list of prioritized sources.
26 | In-service Date Total Delay | No input needed. Automatically populated. | 365 | If the Original In-service Date and the Planned or Actual In-service Date are different, the difference in days will automatically be calculated. No input is needed.
27 | Project is Delayed | No input needed. Automatically populated. | Yes | If "Original In-service Date" is equal to or later than the "Planned or Actual In-service Date", the project is not delayed (No). If "Original In-service Date" is earlier than the "Planned or Actual In-service Date", the project is delayed (Yes). No input is needed.
28 | Delay Resolver | Drop-down menu selection. | Customer | See drop-down menu. Select the party that can resolve the current delay. Select N/A only if the project is NOT delayed. If selecting "Agency - Federal", "Agency - Local", or "Agency - State", identify the specific agency in the "Notes" field. If selecting "Agency - Federal", "Agency - Local", "Agency - State", "CAISO", or "CPUC", identify the specific delays with the entity and how to resolve.
29 | In-service Date Change Reason | Drop-down menu selection. | Financing | See drop-down menu. Select the primary reason for the change from the original in-service date. Select N/A only if the project is NOT delayed. If selecting "Permitting (non-CPUC/CEQA)", identify the specific entities involved in the permitting delay (e.g. Federal, State, Local agencies) in the "Notes" field.
Section 3: PERMITTING STATUS (CPUC/CEQA)
Field # | Project Data Field | Input Format | Input Example | Input Description
30 | CEQA Status | Drop-down menu selection. | PEA Deemed Complete | Status of the project in the CEQA permitting process.
31 | CEQA Status Date | Date, formatted YYYY-MM-DD. | 2023-05-01 | CEQA Status as of the date entered here. Example: If a CEQA Status of "PEA Deemed Complete" was last verified on 2023-05-01, then enter "2023-05-01" here.
32 | CEQA Document Type | Drop-down menu selection. | EIR | Examples include: IS/ND, IS/MND, EIR, Exempted, Other, or N/A. If "Other" include explanation in the "Notes" field.
33 | NEPA Document Type | Drop-down menu selection. | EIS | Examples include: EIS, EA, Categorical Exclusion, Other, or N/A. If "Other" include explanation in the "Notes" field.
34 | CEQA Lead Agency | Text string, or N/A | CPUC | Some examples include: CPUC, SWRCB, CSLC, not applicable (N/A).
35 | NEPA Lead Agency | Text string, or N/A | USFS | Some examples include: USFS, not applicable (N/A).
36 | CPUC Filing Type | Text string, or N/A | PG&E AL 2355-E | Type of permit. Some examples include: NOC, Advice Letter (AL) Application for 851, PTC, CPCN, or not applicable (N/A).
37 | CPUC Date Filed | Date, formatted YYYY-MM-DD. | 2012-09-30 | Date when permits were filed with CPUC.
38 | CPUC Status | Drop-down menu selection. | Filed and Under Administrative Review | Status of the project in the CPUC permitting process.
39 | CPUC Status Date | Date, formatted YYYY-MM-DD. | 2022-12-13 | CPUC Status as of the date entered here. Example: If a CPUC Status of "Filed and Under Administrative Review" was last verified on 2022-12-13, then enter "2022-12-13" here.
Section 4: TRANSMISSION PROJECT NOTES
Field # | Project Data Field | Input Format | Input Example | Input Description
40 | Notes | Text strings, inclusive of field identifiers in brackets, separated by line break. | [4. Status] PPA negotiation failure. [6. Purpose] Experimental breaker testing. | For all fields in which an option including "[See Notes]" was selected, please enter a description or explanation here.
41 | Secondary/Other Reasons for Delay | Text string. | Although the most significant reason for delay on this project has been due to Land Rights issues, this project has also been subject to delays caused by unforeseen Weather circumstances, such as flooding experienced in the first 6 months of the project. Project staff estimate that Weather-related issues have contributed to about 25% of the total delay experienced. | For all projects that have been identified as being delayed (Project is Delayed = Yes), provide any additional context into reasons other than the primary reason for delay identified in "In-service Date Change Reason" and explained in "Notes". Please provide secondary reasons for delays and estimated contribution to the project's total delay, if available.
Section 5: GENERATION RESOURCE DEPENDENCIES
Field # | Project Data Field | Input Format | Input Example | Input Description
42+ | Dependent Resource In-Queue Generation Number (CAISO and WDAT) | Text string. Only 1 ID per cell. | 0002CONV | Enter in only 1 ID per cell. CAISO and WDAT queue numbers. Identify all generation resources (with executed interconnection agreements) that are operationally dependent on this project. If the generation resource is connecting to a PTO's distribution system then Queue numbers can include "W", "WDT", "WD", "GFID", "RD" or "Rule 21". Submitter may add additional columns for additional generation projects as necessary. List all queue position #s both CAISO and WDAT generation projects. Types of queue position labels include, but are not limited to: - ##, or, if two queues have combined then the queue number will reflect ##,##. - ####CONV is a two-to-three party contract conversion or is a conversion project repowering with new generation. - ####PREC, that is an existing two-party generating facility that has yet to complete a contract conversion. - #### for generation resources that are dynamic or pseudo-ties (projects in a balancing authority area other than the CAISO but are treated as Participating Generators under the CAISO Tariff).
"2. Generation Reporting" TAB
Section 1: GENERATION RESOURCES DETAILS
Field # | Project Data Field | Input Format | Input Example | Input Description
1 | Generation Facility Name | Text string. | Sierra Solar Farm Project | Name of generating facility (with executed interconnection agreement) that is currently in development. Any resources identified on tab 1. Transmission Delay Reporting under the Dependent Resource In-Queue Generation Number (CAISO and WDAT) fields must also be listed on this tab or data request will be considered incomplete.
2 | In-Queue Number (CAISO or WDAT) | Text string. | 0002CONV | If generation resources were entered on tab 1. Transmission Delay Reporting in any of the "Dependent Resource In-Queue Generation Number (CAISO and WDAT)" fields, inputs here must match. CAISO queue or WDAT (Wholesale Distribution Access Tariff) queue number of the generating facility. If the generation resource is connecting to a Participating TO's distribution system then Queue numbers can include "W", "WDT", "WD", "GFID", "RD" or "Rule 21". Types of queue position labels include: - ##, or, if two queues have combined then the queue number will reflect ##,##. - ####CONV is a two-to-three party contract conversion or is a conversion project repowering with new generation. - ####PREC, that is an existing two-party generating facility that has yet to complete a contract conversion. - #### for generation resources that are dynamic or pseudo-ties (projects in a balancing authority area other than the CAISO but are treated as Participating Generators under the CAISO Tariff).
3 | Generator Resource ID | TEXT STRING IN CAPS, underscore(_), #(s), underscore (_), TEXT STRING IN CAPS, #(s). | HENRUA_6_ACDSR3 | The resource ID for this generating facility. Resource ID is assigned during "model build" stage of the New Resource Implementation (NRI) Process.
4 | Primary Developer | Text string. | SuperSun Renewables, LCC | Developer with the highest percentage interest in the project.
5 | Developer Parent Company Name | Text string. | Orion Energy Corp. | Parent company name of primary developer. For wholesale aggregated contracts, use name of aggregator (e.g., Shell, Barclays etc.).
6 | Nameplate Capacity | Number (decimal). | 100.5 | Total nameplate capacity of the whole project in MW. This should be the maximum MW it can deliver under the interconnection agreement.
7 | Expected Annual RPS Eligible Generation | Number (decimal) or N/A. | 29396.8 | The anticipated total energy generated by this RPS eligible resource each year in MWh. If not applicable, enter N/A.
8 | Planned Construction Start Date | Date, formatted YYYY-MM-DD. | 2024-06-17 | Identify planned construction start dates for in-queue resource or generation project.
9 | Planned In-service Date | Date, formatted YYYY-MM-DD. | 2025-09-01 | Identify planned in-service date for in-queue resource and generation project.
10 | Interconnection Request Type | Drop-down menu selection. | Fully deliverable | See drop-down menu. Select deliverability status sought in interconnection agreement.
11 | Technology Type | Drop-down menu selection. | Biogas | See drop-down menu. Select resource technology type.
12 | RPS Eligible | Drop-down menu selection. | Yes | Is this resource RPS-eligible? (Yes or No)
13 | PTO Service Territory | Drop-down menu selection. | PG&E | See drop-down menu. Select the PTO service territory that this generation resource is located in. If "Other" is selected, please explain in the "Notes" field.
Section 2: GENERATION RESOURCES NOTES
Field # | Project Data Field | Input Format | Input Example | Input Description
14 | Notes | Text strings, inclusive of field identifiers in brackets, separated by line break. | [11. Technology Type] Mixed technology, solar and battery storage. | For all fields in which an option including "[See Notes]" was selected, please enter a description or explanation here.
Section 3: CONNECTING TRANSMISSION PROJECTS
Field # | Project Data Field | Input Format | Input Example | Input Description
15 | Dependent on Delayed Transmission Project | Drop-down menu selection. | Yes | See drop-down menu. If the generation or storage resource coming online is dependent on the completion of a transmission project that has already experienced a delay, select "Yes". If the generation or storage resource coming online is dependent on a transmission project that has not been delayed or not dependent on a transmission project's completion, select "No".
16 | Impact of Transmission Delay on Resource | Text string. | This generation resource will not be able to come online until the completion of the GreenZone transmission project (ID 482859) is completed. As the GreenZone project has been delayed by one year, and this project was expected to come online 6 months after GreenZone's completion, we anticipate this generation resource being delayed by 6 months. | If "Yes" was chosen for "Dependent on Delayed Transmission Project", please explain the expected impact on this generation or storage resource. Please include as much details as possible, including expected in-service date delays for the generation or storage resource.

## Definitions
Acronym List |  |  | Date Change Reasons Defined
| Acronym | Definition | Reason | Definition
| AFUDC | Allowance for Funds Used During Construction | Bundling Dependencies | Another delayed project must be completed before this project can continue. Can be in any phase of the project (i.e. planning, engineering, construction, etc.).
| AL | Advice Letter | Clearances | Non-permit related clearance delays from any governmental entity with authority or jurisdiction over any phase of this project.
| CAISO | California Independent System Operator | Completed Early | Project completed before originally scheduled in-service date.
| CEQA | California Environmental Quality Act | Financing | Project delayed due to capital and financial availability constraints.
| CPUC | California Public Utilities Commission | ISO Action | The CAISO de-prioritized or re-prioritized the project. De-prioritization would typically manifest with an on-hold project status.
| CSLC | California State Lands Commission | Land Rights | The project required easements, exercise of eminent domain, etc. that the utility has not been able to effect.
| EIR | Environmental Impact Report | Material | Issues with equipment or components themselves but are not related to vendor error (see "Vendor Quality/Delays")
| EIS | Environmental Impact Statements | Outage | Outages (planned or unplanned) that impacted the in-service date.
| FERC | Federal Energy Regulatory Commission | Permitting (CPUC/CEQA) | Project delays related to CPUC permitting or CEQA environmental reviews. Examples: CPCN, PTC, or PEA review times are unusually long.
| GO | General Order | Permitting (non-CPUC/CEQA) | Project delays related to federal, state, or local agency permitting downstream of CPUC/CEQA permitting. Example: BLM permitting process is unusually long.
| ID | Identification | Project Design | Any additional design work outside of the initially approved project design, not related to "Workforce Availability", "Bundling Dependencies" or "Clearances".
| IS/MND | Initial Study and Mitigated Negative Declaration | Supply Chain Delays | Requested project resources have not been delivered as scheduled.
| IS/ND | Initial Study and Negative Declaration | Vendor Quality/Delays | Issues with vendor/suppliers that are not related to the failure of equipment, material, or components (see "Material").
| ISD | In-service Date | Weather | An unforeseen weather event that causes a delay or set-back in construction work. Example: mudslides resulting from El Nino.
| IT | Information Technology | Workforce Availability | Impacts due to staffing shortages at any phase of the project (i.e. planning, engineering, construction, etc.).
| IX | Interconnection
| KV | Kilovolt
| MPAC | Modular Protection Automation & Control
| MVA | Megavolt-ampere
| MW | Megawatt
| MWh | Megawatt-hour
| N/A | Not applicable
| NEPA | National Environmental Policy Act
| NERC | North American Electric Reliability Corporation
| NOC | Notice of Construction
| NRI | New Resource Implementation
| OAI | Operative as Installed
| PEA | Proponent’s Environmental Assessments
| PG&E | Pacific Gas and Electric
| PTC | Permit to Construct
| PTO | Participating Transmission Owner
| RPS | Renewables Portfolio Standard
| RTU | Remote Terminal Unit
| SB | Senate Bill
| SCADA | Supervisory Control and Data Acquisition
| SCE | Southern California Edison
| SDG&E | San Diego Gas & Electric
| SWRCB | California State Water Resources Control Board
| TDF | Transmission Development Form
| TPP | Transmission Planning Process
| TX | Transmission
| USFS | United States Forest Service
| WDAT | Wholesale Distribution Access Tariff
| WECC | Western Electricity Coordinating Council

## Changes
Changes from the 2024 to 2025 SB 1174 Data Reporting Template
Tab | Change
All | General formatting changes.
All | General editing for clarity.
Instructions | Further defined what transmission projects must be reported within the 1174 SB data request.
Instructions | The date range for completed transmission projects that must be reported has been updated.
Instructions | Clarified that "Operational" projects' operational date should match the actual in-service date.
Instructions | Updated the Input Description for several fields.
Definitions | Added new acronyms to Acronym List.
Definitions | Updated definitions in the Date Change Reasons Defined table.
Transmission Delay Reporting | Added field for GIDAP Related.
Transmission Delay Reporting | Added field for Year Expected to be Considered in CAISO TPP.
Transmission Delay Reporting | Added field for Location.
Transmission Delay Reporting | Added fields for Latitude and Longitude.
Transmission Delay Reporting | Added fields for Transmission Project Unique ID #2 and #3.
Transmission Delay Reporting | Added field for CAISO Study Area.
Transmission Delay Reporting | Added field for Project Dependencies.
Transmission Delay Reporting | Added field for Transmission Project Size.
Transmission Delay Reporting | Added field for Substation Project Footprint.
Transmission Delay Reporting | Added field for Transmission Voltage Level.
Transmission Delay Reporting | Added field for Substation or Transformer Capacity.
Transmission Delay Reporting | Added field for Project is Delayed.
Transmission Delay Reporting | Added field for Original In-service Date Source.
Transmission Delay Reporting | Added field for In-service Date Total Delay (Days).
Transmission Delay Reporting | Added field for Secondary/Other Reasons for Delay.
Transmission Delay Reporting | Added new section for Permitting Status (CPUC/CEQA) and 10 associated new fields.
Transmission Delay Reporting | Changed In-service Date Change Initiator field to Delay Resolver.
Transmission Delay Reporting | Changed options for In-service Date Change Reason.
Transmission Delay Reporting | Changed Notes field to be required for all delayed projects.
Transmission Delay Reporting | Removed certain fields related to construction dates.
Generation Reporting | Added field for PTO Service Territory.
Generation Reporting | Added field for Dependent on Delayed Transmission Project.
Generation Reporting | Added field for Impact of Transmission Delay on Resource.
Generation Reporting | Removed Transmission Project Unique ID fields.

## 1. Transmission Delay Reporting
Transmission Delay Reporting
List transmission projects and complete all fields, and list all in-development renewable energy and energy storage resources (with an executed interconnection agreement) that depends on the project. Electrical corporations shall list each “transmission project” that is: 1. A CAISO-approved or utility self-approved transmission project, interconnection project, or network upgrade needed for generator interconnection; 2. Delayed OR not delayed (i.e. do not consider delay when listing projects); and 3. “In development”, meaning the project has commenced, but is not yet in-service OR became operational between January 1, 2020 and March 31, 2025. | [9 empty] | All fields are mandatory. Blank fields or data that doesn't match the Input Format on the Instructions tab will be considered incomplete. Tab sections in black text refer to transmission projects, tab sections in red text refer to generation projects. | [14 empty] | Fields 25 and 26 below are automatically populated. No input needed. |  | Fields 27 and 28 below will highlight in light red if the project has been delayed. Please indicate choices other than N/A. | [11 empty] | Fields 39 and 40 below will highlight in light red if the project has been delayed. Please provide additional details. |  | Add new columns to Section 5 as needed.
Section 1: TRANSMISSION PROJECT DETAILS | [20 empty] | Section 2: TRANSMISSION PROJECT VARIANCES | [7 empty] | Section 3: PERMITTING STATUS (CPUC/CEQA) | [9 empty] | Section 4: TRANSMISSION PROJECT NOTES |  | Section 5: GENERATION RESOURCE DEPENDENCIES
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61
Transmission Project Name | Transmission Project Unique ID #1 | Transmission Project Unique ID #2 | Transmission Project Unique ID #3 | Description | Status | Operational Date | Latitude | Longitude | Location | CAISO Study Area | GIDAP Related | Year Expected to be Considered in CAISO TPP | Project Dependencies | Action Taken | Purpose | Purpose Details | Transmission Project Size | Substation Project Footprint | Transmission Voltage Level | Substation or Transformer Capacity | Planned or Actual Construction Start Date | Original In-service Date | Planned or Actual In-service Date | Original In-service Date Source | In-service Date Total Delay (Days) | Project is Delayed | Delay Resolver | In-service Date Change Reason | CEQA Status | CEQA Status Date | CEQA Document Type | NEPA Document Type | CEQA Lead Agency | NEPA Lead Agency | CPUC Filing Type | CPUC Date Filed | CPUC Status | CPUC Status Date | Notes (Required for Any Delayed Projects) | Secondary/Other Reasons for Delay (Required for Any Delayed Projects) | Dependent Resource In-Queue Generation Number (CAISO and WDAT) | Dependent Resource In-Queue Generation Number (CAISO and WDAT)2 | Dependent Resource In-Queue Generation Number (CAISO and WDAT)3 | Dependent Resource In-Queue Generation Number (CAISO and WDAT)4 | Dependent Resource In-Queue Generation Number (CAISO and WDAT)5 | Dependent Resource In-Queue Generation Number (CAISO and WDAT)6 | Dependent Resource In-Queue Generation Number (CAISO and WDAT)7 | Dependent Resource In-Queue Generation Number (CAISO and WDAT)8 | Dependent Resource In-Queue Generation Number (CAISO and WDAT)9 | Dependent Resource In-Queue Generation Number (CAISO and WDAT)10 | Dependent Resource In-Queue Generation Number (CAISO and WDAT)11 | Dependent Resource In-Queue Generation Number (CAISO and WDAT)12 | Dependent Resource In-Queue Generation Number (CAISO and WDAT)13 | Dependent Resource In-Queue Generation Number (CAISO and WDAT)14 | Dependent Resource In-Queue Generation Number (CAISO and WDAT)15 | Dependent Resource In-Queue Generation Number (CAISO and WDAT)16 | Dependent Resource In-Queue Generation Number (CAISO and WDAT)17 | Dependent Resource In-Queue Generation Number (CAISO and WDAT)18 | Dependent Resource In-Queue Generation Number (CAISO and WDAT)19 | Dependent Resource In-Queue Generation Number (CAISO and WDAT)20 | Dependent Resource In-Queue Generation Number (CAISO and WDAT)21 | Dependent Resource In-Queue Generation Number (CAISO and WDAT)22 | Dependent Resource In-Queue Generation Number (CAISO and WDAT)23 | Dependent Resource In-Queue Generation Number (CAISO and WDAT)24
Riverside Transmission Reliability Project | Multiple Workorders | Multiple CWBSs | 5450 | Riverside Transmission Reliability Project | Planning | 2029-10-31 |  |  | Jurupa Valley, Riverside County ¦ Ontario, San Bernardino |  | No | NA | NA | NA | Work Requested by Others | Load Interconnection | 8 | 3 | 230 | 560 MVA ¦ 230kV | 2025-06-23 | 2008-01-01 | 2029-10-31 | Transmission Project Review Process data | 7974 | Yes | Customer | N/A | FiN/Al Certified | 2020-03-18 | EIR | NA | CPUC | NA | CPCN A.15-04-013 | 42109 | Approved | 2020 |  | Customer Action
Colorado River Substation Expansion: Dracker Project (TOT276_Q294) | Multiple Workorders | CET-ET-TP-RL-816900 | 8169 | Colorado River Substation Expansion: Dracker Project (TOT276_Q294) | Operational | 2021-11-05 |  |  | Blythe, Riverside County |  | Yes | NA | SP-33 | SP-33 | Work Requested by Others | Generation Interconnection | NA | 77 | NA | 1120 MVA ¦ 500kV ¦ 220kV | 2021-02-01 | 2020-12-01 | 2021-11-05 | Transmission Project Review Process data | 339 | Yes | Utility | Bundling Dependencies | N/A | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA |  | N/A
Lugo Substation Transformer Bank Conversion | 800308934 | CET-ET-TP-RL-679100 | 6791 | Lugo Substation Transformer Bank Conversion | Engineering more than 50% complete | 2032-06-29 |  |  | Hesperia, San Bernardino County |  | No | NA | NA | NA | Reliability | Substation Reliability | NA | 46 | NA | 500kV ¦ 220kV | 2031-01-02 | 2011-12-01 | 2032-06-29 | Transmission Project Review Process data | 7516 | Yes | Utility | Bundling Dependencies | N/A | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA
Calcite Substation Construction | Multiple Workorders | Multiple CWBSs | 6902 | Calcite Substation Construction | Planning | 2028-06-30 |  |  | Lucerne Valley, San Bernardino County |  | Yes | NA | NA | NA | Generator Interconnection | Generation Interconnection | NA | 10 | NA | 230kV | 2027-01-04 | 2021-03-04 | 2028-06-30 | Transmission Project Review Process data | 2675 | Yes | Customer | N/A | CEQA Draft Published | 2023-08-30 | EIR | NA | San Bernardino County | NA | PTC | Not yet filed 2025 | To be Filed | NA |  | Customer Action | Q897 | Q1207 | Q2097
Eldorado-Lugo-Mohave RPS Upgrade | Multiple Workorders | Multiple CWBSs | 7546 | Eldorado-Lugo-Mohave RPS Upgrade | Construction (over 75%) | 2025-06-30 |  |  | Hesperia, San Bernardino County ¦ Boulder City, Clark County ¦ Laughlin, Clark County |  | No | NA | NA | NA | Policy | Generation Interconnection | NA | NA | NA | NA | 2020-11-02 | 2016-12-31 | 2025-06-30 | Transmission Project Review Process data | 3103 | Yes | CPUC | Permitting (CPUC/CEQA) | FiN/Al Certified | 2020-08-27 | IS/MND | EIS | CPUC | BLM | CPCN A.18-05-007 | 43222 | Approved | 2020 |  | Material | Q1522 | Q1647 | Q1636 | Q1642 | Q1643 | Q1757 | Q1758 | Q1795 | Q2050 | Q1761 | Q1764 | Q1768 | Q1796
Johanna Substation Transformer Bank Conversion | 902067053 | CET-ET-TP-RL-711500 | 7115 | Johanna Substation Transformer Bank Conversion | Operational | 2021-12-22 |  |  | Santa Ana, Orange County |  | No | NA | NA | NA | Reliability | Substation Reliability | NA | NA | NA | NA | 2021-07-06 | 2019-12-31 | 2021-12-22 | Transmission Project Review Process data | 722 | Yes | Utility | Bundling Dependencies | N/A | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA
Magunden-Springville No,1 & No.2 Tower Replacement | Multiple Workorders | Multiple CWBSs | 7558 | Magunden-Springville No,1 & No.2 Tower Replacement | Operational | 2022-02-25 |  |  | City of Porterville, Tulare County |  | No | NA | NA | NA | Asset Condition | Age/Condition - Replace Steel Poles | 2 | NA | 220 | NA | 2021-09-03 | 2021-06-01 | 2022-02-25 | Transmission Project Review Process data | 269 | Yes | CPUC | Permitting (CPUC/CEQA) | FiN/Al Certified | 2021-01-21 | EIR | EIS | Lower Tule River Irrigation District | US Army Corps of Engineers | NA | NA | NA [See Notes] | NA |  | N/A
Desert Harvest Generation Project (TOT486_Q643AE) | 901395606 | CET-ET-TP-RN-772900 | 7729 | Desert Harvest Generation Project (TOT486_Q643AE) | Operational | 2021-02-03 |  |  | Desert Center, Riverside County |  | Yes | NA | SP-37 ¦ SP-03 | SP-37 ¦ SP-03 | Work Requested by Others | Generation Interconnection | NA | 75.7 | NA | 220kV | 2020-03-16 | 2016-08-01 | 2021-02-03 | Transmission Project Review Process data | 1647 | Yes | Utility | Bundling Dependencies | N/A | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA |  | N/A | Q1405
Lugo-Victorville RAS | Multiple Workorders | Multiple CWBSs | 7763 | Lugo-Victorville RAS | Construction (25%-50%) | 2025-12-31 |  |  | Hesperia, San Bernardino County ¦ Newberry Springs, San Bernardino County ¦ Daggett, San Bernardino County ¦ Boulder City, Clark County ¦ Laughlin, Clark County |  | Yes | NA | NA | NA | Reliability | Generation Interconnection | NA | NA | NA | NA | 2017-06-21 | 2016-12-31 | 2025-12-31 | Transmission Project Review Process data | 3287 | Yes | Agency - Federal | Permitting (non-CPUC/CEQA) | CEQA Draft Published | 2023-12-22 | IS/MND | EA | CDFW | BLM | NA | NA | NA [See Notes] | NA |  | N/A | Q1522 | Q1795 | Q1796 | Q1647
Big Creek Corridor Rating Upgrade | Multiple Workorders | Multiple CWBSs | 7866 | Big Creek Corridor Rating Upgrade | Operational | 2020-01-31 |  |  | Bakersfield, Kern County ¦ Richgrove, Tulare County ¦ Farmersville, Tulare County |  | No | NA | PB-22.03 ¦ PB-22.04 ¦ PB-22.05 ¦ PB-22.06 | PB-22.03 ¦ PB-22.04 ¦ PB-22.05 ¦ PB-22.06 | Work Requested by Others | System Design Upgrade | NA | NA | NA | NA | 2019-10-09 | 2018-12-31 | 2020-01-31 | Transmission Project Review Process data | 396 | Yes | Utility | Project Design | N/A | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA |  | N/A
Cerritos Channel Tower Relocation | Multiple Workorders | Multiple CWBSs | 7884 | Cerritos Channel Tower Relocation | Construction (under 10%) | 2028-03-02 |  |  | Long Beach, Los Angeles County |  | No | NA | NA | NA | Work Requested by Others | Facility Relocation | 0.25 | 2.25 | 230 | 220kV | 2018-11-14 | 2019-01-01 | 2028-03-02 | Transmission Project Review Process data | 3348 | Yes | Utility | Project Design | FiN/Al Certified | 2017-12-11 | EIR | NA | Port of Long Beach | NA | PTC A.18-02-002 | 43132 | Approved | 2018 |  | Customer Action
Stage Coach Solar RNU (TOT640_Q897) | Multiple Workorders | Multiple CWBSs | 7902 | Stage Coach Solar RNU (TOT640_Q897) | On Hold | 2027-05-31 |  |  | Lucerne Valley, San Bernardino County |  | Yes | NA | NA | NA | Generator Interconnection | Generation Interconnection | 7 | 12.33 | 220 | 220kV | NA | 2023-09-01 | 2027-05-31 | Transmission Project Review Process data | 1368 | Yes | Utility | Bundling Dependencies | CEQA Draft Published | 2021-10-22 | EIR | NA | San Bernardino County | NA | PTC | Not yet filed TBD | To be Filed | NA |  | Customer Action | Q897
Lugo-Victorville 500 kV Transmission Line Upgrade | Multiple Workorders | Multiple CWBSs | 8029 | Lugo-Victorville 500 kV Transmission Line Upgrade | Engineering more than 50% complete | 2027-03-31 |  |  | Hesperia, San Bernardino County |  | No | NA | NA | NA | Address Results of Power Flow Analysis | Age/Condition - Replace 500 kV Breakers | NA | 87.9 | NA | 500kV | 2027-10-01 | 2018-12-31 | 2027-03-31 | Transmission Project Review Process data | 3012 | Yes | Utility | Bundling Dependencies | N/A | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA |  |  | Q1647 | Q1795 | Q1796 | Q1636 | Q1642 | Q1643 | Q1757 | Q1758 | Q2050 | Q1761 | Q1764 | Q1768 | Q2042
Arlington Solar Project (TOT781_Q1196) | Multiple Workorders | Multiple CWBSs | 8081 | Arlington Solar Project (TOT781_Q1196) | Operational | 2021-12-02 |  |  | Blythe, Riverside County |  | Yes | NA | SP-02 ¦ SP-03 | SP-02 ¦ SP-03 | Work Requested by Others | Generation Interconnection | 10 | 77 | 220 | 220kV | 2020-02-10 | 2020-12-01 | 2021-12-02 | Transmission Project Review Process data | 366 | Yes | Customer | N/A | N/A | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA |  | Customer Action
Moorpark-Pardee Circuit Install | Multiple Workorders | Multiple CWBSs | 8104 | Moorpark-Pardee Circuit Install | Operational | 2022-05-18 |  |  | Sylmar, Los Angeles County ¦ Moorpark, Ventura County |  | No | NA | NA | NA | Local Capacity Requirement | New T-Line | 26 | 29.4 ¦ 38.8 | 220 | 220kV | 2019-08-05 | 2020-12-31 | 2022-05-18 | Transmission Project Review Process data | 503 | Yes | Utility | Project Design | N/A | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Scope Change | N/A
Red Bluff Substation Transformer Bank Install (TOT486_Q643AE) | Multiple Workorders | CET-ET-TP-RL-816300 | 8163 | Red Bluff Substation Transformer Bank Install (TOT486_Q643AE) | Operational | 2022-04-25 |  |  | Desert Center, Riverside County |  | No | NA | SP-37 ¦SP-03 | SP-37 ¦SP-03 | Work Requested by Others | Generation Interconnection | NA | 75.7 | NA | 1120 MVA ¦ 500kV ¦ 220kV | 2021-02-05 | 2021-10-08 | 2022-04-25 | Transmission Project Review Process data | 199 | Yes | Utility | Bundling Dependencies | N/A | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA
WDAT315 - Casa Diablo 4 - Casa Diablo (D) Install interconnection facilities | Multiple Workorders | Multiple CWBSs | 7227 | WDAT315 - Casa Diablo 4 - Casa Diablo (D) Install interconnection facilities | Operational | 2023-12-22 |  |  | Mammoth Lakes, Mono County |  | Yes | NA | NA | NA | Work Requested by Others | Generation Interconnection | 0.3 | 2.4 | 33 | 115kV ¦ 33kV | 2021-01-21 | 2020-02-01 | 2023-12-22 | Transmission Project Review Process data | 1420 | Yes | CPUC | Permitting (CPUC/CEQA) | N/A | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA |  | Weather
Substation Protection Upgrades - San Joaquin Region | Multiple Workorders | Multiple CWBSs | 8077 | Substation Protection Upgrades - San Joaquin Region | Construction (10%-25%) | 2027-08-30 |  |  | Bakersfield, Kern County |  | No | NA | NA | NA | CAISO Transmission Planning Standards [See Notes for NERC Compliance and contingency code, WECC Requirement (and the specific requirement)] | Protection NERC Compliance | NA | 15.3 | NA | 220kV | 2020-03-02 | 2021-06-01 | 2027-08-30 | Transmission Project Review Process data | 2281 | Yes | Utility | Bundling Dependencies | N/A | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Scope Change, Material, Construction Delays. | Multiple Options [See Notes]
Devers Substation Reliability Network Upgrade (TOT789_Q1295) | 902748920 | CET-ET-TP-RN-819500 | 8195 | Devers Substation Reliability Network Upgrade (TOT789_Q1295) | Operational | 2024-04-30 |  |  | Palm Springs, Riverside County |  | Yes | NA | NA | NA | Work Requested by Others | Generation Interconnection | 1 | 98 | 220 | 220kV | 2022-01-03 | 2022-10-01 | 2024-04-30 | Transmission Project Review Process data | 577 | Yes | Utility | Project Design | N/A | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Scope Change | N/A
Victory Pass Solar | Multiple Workorders | Multiple CWBSs | 8214 | Victory Pass Solar | Operational | 2023-09-03 |  |  | Desert Center, Riverside County |  | Yes | NA | NA | NA | Work Requested by Others | Generation Interconnection | 3 | 75.7 | 220 | 220kV | 2023-03-08 | 2021-10-01 | 2023-09-03 | Transmission Project Review Process data | 702 | Yes | Utility | Project Design | N/A | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Scope Change | Material
Whirlwind Substation (RNU) (TOT778_Q1217) | 902668204 | CET-ET-TP-RN-820100 | 8201 | Whirlwind Substation (RNU) (TOT778_Q1217) | Operational | 2024-03-22 |  |  | Rosamond, Kern County |  | Yes | NA | NA | NA | Work Requested by Others | Generation Interconnection | 7.2 | NA | 220 | NA | 2024-01-22 | 2022-03-01 | 2024-03-22 | Transmission Project Review Process data | 752 | Yes | Customer | N/A | N/A | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA |  | Customer Action | Q1217
Athos Power Plant RNU (TOT849_Q1405) | Multiple Workorders | Multiple CWBSs | 8220 | Athos Power Plant RNU (TOT849_Q1405) | Operational | 2021-10-08 |  |  | Desert Center, Riverside County |  | Yes | NA | PB-40 | PB-40 | Work Requested by Others | Generation Interconnection | 1 | 75.7 | 220 | 220kV | 2020-11-16 | 2021-07-31 | 2021-10-08 | Transmission Project Review Process data | 69 | Yes | N/A | N/A | N/A | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA |  | N/A | Q1405
Kramer Substation Interconnect (TOT773_Q1204) | 902342409 | CET-ET-TP-RN-810701 | 8107 | Kramer Substation Interconnect (TOT773_Q1204) | Construction (over 75%) | 2025-11-01 |  |  | Kramer Junction, San Bernardino County |  | Yes | NA | NA | NA | Work Requested by Others | Generation Interconnection | 5 | 20.6 | 220 | 220kV | 2022-07-05 | 2020-06-01 | 2025-11-01 | Transmission Project Review Process data | 1979 | Yes | Customer | N/A | N/A | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA |  | Customer Action | Q1204
TOT821-Q1323 Solar Star 4 | 903115822 | CET-ET-TP-RL-826900 | 8269 | TOT821-Q1323 Solar Star 4 | Construction (50%-75%) | 2025-04-30 |  |  | Rosamond, Kern County |  | Yes | NA | NA | NA | Generator Interconnection | Generation Interconnection | NA | 92 | NA | 500kV ¦ 220kV | 2024-09-19 | 2024-08-15 | 2025-04-30 | Transmission Project Review Process data | 258 | Yes | Customer | N/A | N/A | NA | EIR | NA | NA | NA | NA | NA | NA [See Notes] | NA |  | Customer Action
WOCR CRAS Inland Devers Extension | Multiple Workorders | Multiple CWBSs | 8284 | WOCR CRAS Inland Devers Extension | Operational | 2024-04-09 |  |  | Salome, La Paz County, Arizona |  | Yes | NA | NA | NA | Generator Interconnection | Generation Interconnection | NA | NA | NA | NA | 2021-09-27 | 2022-12-30 | 2024-04-09 | Transmission Project Review Process data | 466 | Yes | Utility | Bundling Dependencies | N/A | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA |  |  | Q1405 | Q1642
Techren Solar RNU (TOT809_Q1339) | 902460358 | CET-ET-TP-RN-817100 | 8171 | Techren Solar RNU (TOT809_Q1339) | Operational | 2024-04-22 |  |  | Boulder City, Clark County, Nevada |  | Yes | NA | SP-72 | SP-72 | Work Requested by Others | Generation Interconnection | 1 | 86.7 | 230 | 230kV | 2023-03-30 | 2021-03-13 | 2024-04-22 | Transmission Project Review Process data | 1136 | Yes | Utility | Project Design | N/A | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA |  | Customer Action | Q1339
Rosamond West Solar RNU (TOT411_Q506) | Multiple Workorders | Multiple CWBSs | 7733 | Rosamond West Solar RNU (TOT411_Q506) | Operational | 2020-09-01 |  |  | Rosamond, Kern County |  | Yes | NA | NA | NA | Work Requested by Others | Generation Interconnection | 2.4 | 92 | 220 | 500kV ¦ 200kV | 2019-12-27 | 2016-11-01 | 2020-09-01 | Transmission Project Review Process data | 1400 | Yes | Utility | Project Design | N/A | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Scope Change | N/A
Golden Fields Solar RNU (TOT754_Q1212) | 903099017 | CET-ET-TP-RN-828500 | 8285 | Golden Fields Solar RNU (TOT754_Q1212) | Engineering more than 50% complete | 2026-03-31 |  |  | Rosamond, Kern County |  | Yes | NA | SP-29 | SP-29 | Work Requested by Others | Generation Interconnection | 6 | 92 | 220 | 220kV | 2026-02-02 | 2022-04-01 | 2026-03-31 | Transmission Project Review Process data | 1460 | Yes | Utility | Material | N/A | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA |  | Customer Action | Q1212
Almasol Generating Station Project RNU (TOT 321_Q365) | 900346247 | CET-ET-TP-RN-705900 | 7059 | Almasol Generating Station Project RNU (TOT 321_Q365) | Operational | 2020-12-30 |  |  | Desert Center, Riverside County |  | Yes | NA | NA | NA | Work Requested by Others | Generation Interconnection | NA | NA | NA | NA | 2019-10-07 | 2021-02-02 | 2020-12-30 | Transmission Project Review Process data | -34 | No | N/A | N/A | N/A | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA |  | N/A
Control-Silver Peak 55 kV Reliability Project | Multiple Workorders | Multiple CWBSs | 8019 | Control-Silver Peak 55 kV Reliability Project | Operational | 2023-03-16 |  |  | West Bishop, Inyo County ¦ Silver Peak, Esmeralda County |  | No | NA | NA | NA | Reliability | Substation Reliability | 66.73 | NA | 55 | NA | 2019-11-04 | 2018-10-01 | 2023-03-16 | Transmission Project Review Process data | 1627 | Yes | N/A | Weather | N/A | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Permitting, Land Rights, Outage. | Multiple Options [See Notes]
Pardee-Sylmar No. 1 and No. 2 230 kV Lines Rating Increase ¦ Pardee-Sylmar 230 kV Line Rating Increase Project | Multiple Workorders | Multiple CWBSs | 8294 | Pardee-Sylmar No. 1 and No. 2 230 kV Lines Rating Increase ¦ Pardee-Sylmar 230 kV Line Rating Increase Project | Construction (50%-75%) | 2029-06-01 |  |  | Santa Clarita, Los Angeles County ¦ Sylmar, Los Angeles County |  | No | NA | NA | NA | Reliability | System Design Upgrade | 11.5 | NA | 220 | NA | 2022-09-01 | 2023-06-01 | 2029-06-01 | Transmission Project Review Process data | 2192 | Yes | Utility | Project Design | N/A | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Scope Change | Material
Bellefield Solar Farm RNU (TOT892_Q1510) | Multiple Workorders | Multiple CWBSs | 8298 | Bellefield Solar Farm RNU (TOT892_Q1510) | Construction (over 75%) | 2025-07-18 |  |  | Mojave, Kern County |  | Yes | NA | SP-29 | SP-29 | Work Requested by Others | Generation Interconnection | 14 | 59.2 | 220 | 220kV | 2024-05-01 | 2022-10-15 | 2025-07-18 | Transmission Project Review Process data | 1007 | Yes | Customer | N/A | N/A | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA |  | Customer Action | Q1510
Digital 395 Project: North-of-Kramer Area Telecom Network and RAS Upgrades | Multiple Workorders | Multiple CWBSs | 7727 | Digital 395 Project: North-of-Kramer Area Telecom Network and RAS Upgrades | Operational | 2024-03-29 |  |  | West Bishop, Inyo County ¦Hesperia, San Bernardino County |  | No | NA | NA | NA | Reliability | Generation Interconnection | NA | NA | NA | NA | 2021-09-27 | 2016-12-31 | 2024-03-29 | Transmission Project Review Process data | 2645 | Yes | Utility | Bundling Dependencies | N/A | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA
Crimson - TOT764_Q1192 | Multiple Workorders | CET-ET-TP-RN-821601 | 8216 | Crimson - TOT764_Q1192 | Operational | 2022-05-02 |  |  | Blythe, Riverside County |  | Yes | NA | PB-40 | PB-40 | Work Requested by Others | Generation Interconnection | 1 | 77 | 220 | 220kV | 2021-04-19 | 2021-04-01 | 2022-05-02 | Transmission Project Review Process data | 396 | Yes | Utility | Bundling Dependencies | N/A | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA
Rexford Solar Farm RNU (TOT896_Q1516) | Multiple Workorders | Multiple CWBSs | 8320 | Rexford Solar Farm RNU (TOT896_Q1516) | Construction (over 75%) | 2025-12-19 |  |  | Richgrove, Tulare County |  | Yes | NA | NA | NA | Generator Interconnection | Generation Interconnection | 0.7 | 48.96 | 220¦66 | 220kV ¦ 66kV | 2023-06-01 | 2022-10-15 | 2025-12-19 | Transmission Project Review Process data | 1161 | Yes | Utility | Project Design | N/A | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Scope Change | Material | WDT1580
ARIDA SOLAR FARM TOT880 (Q1522) | Multiple Workorders | Multiple CWBSs | 8326 | ARIDA SOLAR FARM TOT880 (Q1522) | Engineering more than 50% complete | 2028-03-01 |  |  | Laughlin, Clark County |  | Yes | NA | SP-72 | SP-72 | Generator Interconnection | Generation Interconnection | NA | 11.5 | NA | 500kV | 2026-12-16 | 2024-08-01 | 2028-03-01 | Transmission Project Review Process data | 1308 | Yes | Customer | N/A | N/A | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA |  | Customer Action | Q1522
Sanborn Hybrid 3 - TOT915_Q1632 | Multiple Workorders | CET-ET-CR-WC-834204 | 8342 | Sanborn Hybrid 3 - TOT915_Q1632 | Engineering more than 50% complete | 2026-05-28 |  |  | Mojave, Kern County |  | Yes | NA | NA | NA | Generator Interconnection | Generation Interconnection | 0.4 | 59.2 | 500 | 500kV ¦ 220kV | 2005-10-01 | 2025-04-15 | 2026-05-28 | Transmission Project Review Process data | 408 | Yes | Customer | N/A | FiN/Al Certified | 2024-03-19 | EIR | NA | Kern County | NA | AL 5520-E | 45763 | Filed and Under Administrative Review | 2025 |  | Customer Action | Q1632
Lugo-Victorville Centralized RAS | Multiple Workorders | Multiple CWBSs | 8345 | Lugo-Victorville Centralized RAS | Engineering more than 50% complete | 2028-06-30 |  |  | Hesperia, San Bernardino County ¦ Newberry Springs, San Bernardino County ¦ Daggett, San Bernardino County ¦ Boulder City, Clark County ¦ Laughlin, Clark County |  | Yes | NA | SP-70 ¦ SP-112 ¦ SP-114 ¦ SP-115 | SP-70 ¦ SP-112 ¦ SP-114 ¦ SP-115 | Reliability | Generation Interconnection | NA | NA | NA | NA | 2025-05-30 | 2024-06-30 | 2028-06-30 | Transmission Project Review Process data | 1461 | Yes | Utility | Bundling Dependencies | N/A | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA |  |  | Q1522 | Q1647
North of Lugo Centralized RAS (NoL CRAS)11225 | Multiple Workorders | Multiple CWBSs | 8350 | North of Lugo Centralized RAS (NoL CRAS)11225 | Engineering more than 50% complete | 2028-06-01 |  |  | NA |  | Yes | NA | SP-01 ¦ SP-40 ¦ SP-41 ¦ SP48 ¦ SP-51 ¦ SP-116 | SP-01 ¦ SP-40 ¦ SP-41 ¦ SP48 ¦ SP-51 ¦ SP-116 | Reliability | Generation Interconnection | NA | NA | NA | NA | 2027-01-04 | 2024-06-30 | 2028-06-01 | Transmission Project Review Process data | 1432 | Yes | Utility | Bundling Dependencies | N/A | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA |  |  | Q1604 | Q0043, Q1617, Q1775 | Q1774 | Q1776
Glenfeliz Solar Farm (TOT909_Q1631) | Multiple Workorders | Multiple CWBSs | 8355 | Glenfeliz Solar Farm (TOT909_Q1631) | Engineering more than 50% complete | 2026-03-31 |  |  | Mojave, Kern County |  | Yes | NA | SP-29 ¦ SP-61 | SP-29 ¦ SP-61 | Generator Interconnection | Generation Interconnection | 13 | 59.2 | 220 | 220kV | 2005-10-01 | 2024-03-01 | 2026-03-31 | Transmission Project Review Process data | 760 | Yes | Customer | N/A | N/A | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA |  | Customer Action
Yellow Pine 2, LLC (TOT796_Q1341) | Multiple Workorders | Multiple CWBSs | 8358 | Yellow Pine 2, LLC (TOT796_Q1341) | Construction (over 75%) | 2025-08-21 |  |  | Pahrump, Nye County |  | Yes | NA | SP-72 | SP-72 | Generator Interconnection | Generation Interconnection | 0.25 | 86.7 | 220 | 220kV | 2023-02-13 | 2023-02-27 | 2025-08-21 | Transmission Project Review Process data | 906 | Yes | Utility | Project Design | N/A | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Scope Change | N/A
Aratina Solar | Multiple Workorders | CET-ET-TP-RN-838000 | 8380 | Aratina Solar | Planning | 2028-12-29 |  |  | Boron, Kern County |  | Yes | NA | SP-41 | SP-41 | Work Requested by Others | Generation Interconnection | 5 | 20.6 | 220 | 220kV | 2026-09-30 | 2024-08-01 | 2028-12-29 | Transmission Project Review Process data | 1611 | Yes | Customer | N/A | N/A | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA |  | Customer Action | Q1204
Hinson 220/66 kV - TOT906 (Q1608) Avocet Energy Storage 200 MW Project Interconnection | Multiple Workorders | CET-ET-CR-WC-833600 | 8389 | Hinson 220/66 kV - TOT906 (Q1608) Avocet Energy Storage 200 MW Project Interconnection | Permitting | 2025-12-31 |  |  | Long Beach, Los Angeles County |  | Yes | NA | NA | NA | Generator Interconnection | Generation Interconnection | NA | 12.2 | NA | 220kV ¦ 66kV | 2025-08-05 | 2024-01-15 | 2025-12-31 | Transmission Project Review Process data | 716 | Yes | Utility | Vendor Quality/Delays | N/A | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA |  | Customer Action | Q1608
Kestrel Storage Project (TOT907/Q1616) | Multiple Workorders | Multiple CWBSs | 8393 | Kestrel Storage Project (TOT907/Q1616) | Permitting | 2026-12-29 |  |  | Industry, Los Angeles County |  | Yes | NA | NA | NA | Generator Interconnection | Generation Interconnection | NA | 14.3 | NA | 220kV ¦ 66kV | 2025-08-18 | 2023-10-01 | 2026-12-29 | Transmission Project Review Process data | 1185 | Yes | Customer | N/A | N/A | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA |  | Customer Action | Q1615
Humidor Storage - TOT959- Q1629 | 903516981 | CET-ET-CR-WC-839401 | 8394 | Humidor Storage - TOT959- Q1629 | Permitting | 2027-10-20 |  |  | Palmdale, Los Angeles County |  | Yes | NA | NA | NA | Generator Interconnection | Generation Interconnection | 5 | 46 | 500 | 500kV ¦ 220kV | 2027-06-01 | 2023-10-15 | 2027-10-20 | Transmission Project Review Process data | 1466 | Yes | Agency - Local | Permitting (non-CPUC/CEQA) | N/A | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA |  | Customer Action | Q1629
Goldback Solar Center (TOT943 - Q1619) | Multiple Workorders | Multiple CWBSs | 8398 | Goldback Solar Center (TOT943 - Q1619) | On Hold | 2027-01-12 |  |  | Moorpark, Ventura County |  | Yes | NA | NA | NA | Generator Interconnection | Generation Interconnection | NA | 40 | NA | 220kV ¦ 66kV ¦ 12kV | 2025-07-25 | 2024-07-15 | 2027-01-12 | Transmission Project Review Process data | 911 | Yes | Customer | N/A | N/A | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA |  | Customer Action
Commerce Energy Storage - TOT927_Q1611 | Multiple Workorders | Multiple CWBSs | 8418 | Commerce Energy Storage - TOT927_Q1611 | Permitting | 2026-01-22 |  |  | Commerce, Los Angeles County |  | Yes | NA | NA | NA | Work Requested by Others | Generation Interconnection | 1 | 25.2 | 220 | 220kV | 2025-07-01 | 2024-03-01 | 2026-01-22 | Transmission Project Review Process data | 692 | Yes | Utility | Material | N/A | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA |  | Customer Action | Q1611
Bonanza Solar - TOT931_Q1649 | 903606178 | CET-ET-CR-WC-842600 | 8426 | Bonanza Solar - TOT931_Q1649 | Planning | 2026-07-09 |  |  | Amargosa Valley, Nye County, Nevada |  | Yes | NA | NA | NA | Generator Interconnection | Generation Interconnection | 5.4 | 86.7 | 220 | 500kV ¦ 220kV | 2026-06-11 | 2025-06-01 | 2026-07-09 | Transmission Project Review Process data | 403 | Yes | Utility | Bundling Dependencies | N/A | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA
ED&P scope of work for 500kV Gen-Tie TOT905/Q1647 Angora Solar Farm | Multiple Workorders | Multiple CWBSs | 8433 | ED&P scope of work for 500kV Gen-Tie TOT905/Q1647 Angora Solar Farm | Planning | 2028-03-31 |  |  | Laughlin, Clark County, Nevada |  | Yes | NA | SP-115 | SP-115 | Generator Interconnection | Generation Interconnection | 5.07 | 11.5 | 500 | 500kV | 2026-10-13 | 2025-06-02 | 2028-03-31 | Transmission Project Review Process data | 1033 | Yes | Utility | Land Rights | N/A | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Bundling Dependencies, Outage. | Multiple Options [See Notes] | Q1647
TOT903 - Q1625 - Angeleno Solar Farm | 903659196 | CET-ET-CR-WC-843401 | 8434 | TOT903 - Q1625 - Angeleno Solar Farm | Engineering more than 50% complete | 2027-07-29 |  |  | Palmdale, Los Angeles County |  | Yes | NA | NA | NA | Generator Interconnection | Generation Interconnection | 24.4 | 55 | 500 | 500kV | 2027-07-01 | 2026-04-01 | 2027-07-29 | Transmission Project Review Process data | 484 | Yes | Utility | Material | N/A | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA |  | Customer Action | Q1625
Laguna Bell-Mesa No. 1 230 kV Line Rating Increase Project | Multiple Workorders | Multiple CWBSs | 8448 | Laguna Bell-Mesa No. 1 230 kV Line Rating Increase Project | Construction (50%-75%) | 2025-06-02 |  |  | Commerce, Los Angeles County ¦ Monterey Park, Los Angeles County |  | No | NA | NA | NA | Local Capacity Requirement | Line Reconductoring | 5 | NA | 220 | NA | 2023-05-08 | 2023-12-31 | 2025-06-02 | Transmission Project Review Process data | 519 | Yes | CAISO | Outage | N/A | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA |  | N/A
Gwent Storage 1 (SCE WDT 1647) | Multiple Workorders | Multiple CWBSs | 8456 | Gwent Storage 1 (SCE WDT 1647) | On Hold | 2025-11-24 |  |  | Moorpark, Ventura County |  | Yes | NA | NA | NA | Generator Interconnection | Generation Interconnection | 1 | NA | 220 | NA | NA | 2022-05-12 | 2025-11-24 | Transmission Project Review Process data | 1292 | Yes | Customer | N/A | N/A | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA |  | Customer Action | Q1647
Lycan Solar (TOT921; Q1643) | Multiple Workorders | Multiple CWBSs | 8457 | Lycan Solar (TOT921; Q1643) | Planning | 2029-09-21 |  |  | Desert Center, Riverside County |  | Yes | NA | NA | NA | Generator Interconnection | Generation Interconnection | 1.9 | 75.7 | 500 | 220kV ¦ 500kV | 2027-01-25 | 2025-10-15 | 2029-09-21 | Transmission Project Review Process data | 1437 | Yes | Customer | N/A | N/A | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA |  | Customer Action | Q1643
VISTA RNU-SCD | 903901445 | CET-ET-TP-RN-837603 | 8376 | VISTA RNU-SCD | Operational | 2024-03-22 |  |  | Grand Terrance, San Bernardino County |  | Yes | NA | NA | NA | Reliability | Age/Condition - Replace Underground System | NA | 29.6 | NA | 220kV ¦ 115kV ¦ 66kV ¦ 495 MVA | 2024-02-21 | 2024-03-15 | 2024-03-22 | Transmission Project Review Process data | 7 | Yes | N/A | N/A | N/A | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA |  | N/A
Menifee Power Bank (TOT934/Q1645) | Multiple Workorders | Multiple CWBSs | 8430 | Menifee Power Bank (TOT934/Q1645) | Operational | 2024-07-30 |  |  | Menifee, Riverside County |  | Yes | NA | NA | NA | Generator Interconnection | Generation Interconnection | 0.75 | NA | 500 | NA | 2024-02-29 | 2024-03-01 | 2024-07-30 | Transmission Project Review Process data | 151 | Yes | N/A | N/A | N/A | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA |  | N/A | Q1645
Devers 230 kV Reconfiguration Project | Multiple Workorders | CET-ET-TP-RL-847300 | 8473 | Devers 230 kV Reconfiguration Project | Engineering more than 50% complete | 2027-05-12 |  |  | North Palm Springs, Riverside County |  | No | NA | NA | NA | Reliability | System Design Upgrade | NA | 98 | NA | 220kV | 2024-06-12 | 2024-06-01 | 2027-05-12 | Transmission Project Review Process data | 1075 | Yes | Utility | Bundling Dependencies | N/A | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA
Antelope 66 kV CB Upgrade | Multiple Workorders | Multiple CWBSs | 8474 | Antelope 66 kV CB Upgrade | Construction (over 75%) | 2025-12-31 |  |  | Lancaster, Los Angeles County |  | No | NA | NA | NA | Asset Condition | Substation Capacity | NA | 73 | NA | 220kV | 2024-10-07 | 2025-12-31 | 2025-12-31 | Transmission Project Review Process data | 0 | No | N/A | N/A | N/A | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA |  | N/A
Keyhole Wind (TOT983) | Multiple Workorders | CET-ET-CR-WC-848300 | 8483 | Keyhole Wind (TOT983) | Engineering less than 50% Complete | 2028-06-19 |  |  | Rosamond, Kern County |  | Yes | NA | NA | NA | Generator Interconnection | Generation Interconnection | 2 | 92 | 220 | 220kV | 2027-06-01 | 2026-04-15 | 2028-06-19 | Transmission Project Review Process data | 796 | Yes | Utility | Material | N/A | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA |  | N/A | Q1784
Delamar Energy Storage (TOT995; Q1796) | Multiple Workorders | CET-ET-CR-WC-479102 | 8498 | Delamar Energy Storage (TOT995; Q1796) | Engineering less than 50% Complete | 2027-02-03 |  |  | Boulder City, Clark County, Nevada |  | Yes | NA | NA | NA | Generator Interconnection | Generation Interconnection | 4 | 86.7 | 220 | 220kV | 2026-08-07 | 2026-02-01 | 2027-02-03 | Transmission Project Review Process data | 367 | Yes | Utility | Material | N/A | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA |  | N/A | Q1796
Victor 230 kV Switchrack Reconfiguration | 903911198 | CET-ET-TP-RN-695798 | 8506 | Victor 230 kV Switchrack Reconfiguration | Engineering less than 50% complete | 2027-06-01 |  |  | Victorville, San Bernardino County |  | No | NA | NA | NA | Reliability | System Design Upgrade | NA | NA | NA | NA | 2026-09-23 | 2025-06-01 | 2027-06-01 | Transmission Project Review Process data | 730 | Yes | Utility | Material | N/A | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA |  | N/A
Barre 230 kV Switchrack Conversion to Breaker-And-A-Half Project | Multiple Workorders | Multiple CWBSs | 8519 | Barre 230 kV Switchrack Conversion to Breaker-And-A-Half Project | Engineering more than 50% complete | 2026-06-26 |  |  | Stanton, Orange County |  | No | NA | NA | NA | Reliability | System Design Upgrade | NA | 18.6 | NA | 230kV ¦ 66kV | 2025-08-04 | 2026-06-30 | 2026-06-26 | Transmission Project Review Process data | -4 | No | N/A | N/A | N/A | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA |  | N/A
Roadhouse Storage Project (TOT1008/Q1768) | Multiple Workorders | CET-ET-CR-WC-479102 | 8525 | Roadhouse Storage Project (TOT1008/Q1768) | Engineering more than 50% complete | 2027-01-27 |  |  | Ontario, San Bernardino County |  | Yes | NA | NA | NA | Generator Interconnection | Generation Interconnection | 0.095 | 102.1 | 230 | 220kV | 2026-08-04 | 2025-12-01 | 2027-01-27 | Transmission Project Review Process data | 422 | Yes | Utility | Material | N/A | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA |  | N/A | Q1768
Eldorado 220 kV Jointed-Owned Bus Split (Section A) | Multiple Workorders | CET-ET-TP-RL-854500 | 8545 | Eldorado 220 kV Jointed-Owned Bus Split (Section A) | Engineering less than 50% complete | 2029-12-31 |  |  | Boulder City, Clark County, Nevada |  | No | NA | NA | NA | Safety | Substation Reliability | NA | 89.6 | NA | 230kV | 2029-01-23 | 2029-12-31 | 2029-12-31 | Transmission Project Review Process data | 0 | No | N/A | N/A | N/A | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA |  | N/A
Gracesol Substation: Colorado River Substation-(IRNU-Shared) - TOT1006 (Q1761) Grace Energy Center | Multiple Workorders | CET-ET-TP-RN-695798 | 8546 | Gracesol Substation: Colorado River Substation-(IRNU-Shared) - TOT1006 (Q1761) Grace Energy Center | Engineering more than 50% complete | 2026-12-22 |  |  | Blythe, Riverside County |  | Yes | NA | NA | NA | Generator Interconnection | Generation Interconnection | 12 | 2843 | 220 | 220kV | 2026-05-15 | 2026-07-01 | 2026-12-22 | Transmission Project Review Process data | 174 | Yes | Utility | Vendor Quality/Delays | N/A | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA |  | N/A | Q1761
Bolt Substation: Colorado River Substation-(IRNU-Shared) - TOT1013 (Q1757) Cobalt Project | Multiple Workorders | CET-ET-TP-RN-695798 | 8547 | Bolt Substation: Colorado River Substation-(IRNU-Shared) - TOT1013 (Q1757) Cobalt Project | Engineering more than 50% complete | 2026-12-22 |  |  | Blythe, Riverside County |  | Yes | NA | NA | NA | Generator Interconnection | Generation Interconnection | 1 | 1182 | 220 | 220kV | 2026-02-02 | 2026-05-01 | 2026-12-22 | Transmission Project Review Process data | 235 | Yes | Utility | Vendor Quality/Delays | N/A | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA |  | N/A | Q1757
Rough Hat 2 TOT979 (Q1799) - Add to Lugo-Victorville CRAS | 904215732 | CET-ET-TP-RN-855600 | 8556 | Rough Hat 2 TOT979 (Q1799) - Add to Lugo-Victorville CRAS | Planning | 2026-03-12 |  |  | Jean, Clark County |  | Yes | NA | NA | NA | Generator Interconnection | Generation Interconnection | NA | NA | NA | NA | 2026-02-12 | 2025-11-01 | 2026-03-12 | Transmission Project Review Process data | 131 | Yes | N/A | N/A | N/A | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA |  | N/A
Mira Loma 500 kV CB Upgrade | 904143442 | CET-ET-TP-RL-855700 | 8557 | Mira Loma 500 kV CB Upgrade | Engineering more than 50% complete | 2028-08-14 |  |  | Ontario, San Bernardino County |  | No | NA | NA | NA | Reliability | Substation Capacity | NA | 102.1 | NA | 500kV | 2028-05-18 | 2026-12-31 | 2028-08-14 | Transmission Project Review Process data | 592 | Yes | Utility | Material | N/A | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA |  | N/A
Windhub 220 kV - TOT985 - Q1791 - Sanborn 5 Hybrid | Multiple Workorders | Multiple CWBSs | 8563 | Windhub 220 kV - TOT985 - Q1791 - Sanborn 5 Hybrid | Engineering less than 50% complete | 2027-02-01 |  |  | Mojave, Kern County |  | Yes | NA | NA | NA | Generator Interconnection | Generation Interconnection | 9.1 | 75.73 | 220 | 220kV | 2027-01-04 | 2027-01-02 | 2027-02-01 | Transmission Project Review Process data | 30 | Yes | Utility | Material | N/A | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA |  | N/A | Q1791
New Coolwater A 115/230 kV Bank | 904164457 | CET-ET-TP-RL-856400 | 8564 | New Coolwater A 115/230 kV Bank | Engineering less than 50% complete | 2027-04-30 |  |  | Daggett, San Bernardino County |  | No | NA | NA | NA | Local Capacity Requirement | Substation Reliability | NA | 7 | NA | 280 MVA ¦ 230kV ¦ 115kV | 2026-09-28 | 2026-12-31 | 2027-04-30 | Transmission Project Review Process data | 120 | Yes | N/A | N/A | N/A | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA |  | N/A
New Serrano 4AA 500/230 kV Bank and 230 kV GIS Rebuild | 904187129 | CET-ET-TP-RL-856700 | 8567 | New Serrano 4AA 500/230 kV Bank and 230 kV GIS Rebuild | Engineering more than 50% complete | 2027-12-30 |  |  | Orange, Orange County |  | No | NA | NA | NA | Reliability | Substation Reliability | NA | 19.3 | NA | 1120 MVA ¦ 500kV ¦ 230kV | 2027-03-29 | 2027-12-31 | 2027-12-31 | Transmission Project Review Process data | 0 | No | N/A | N/A | N/A | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA |  | N/A
Mesa - Del Amo - Serrano 500 kV Upgrade | Multiple Workorders | Multiple CWBSs | 8575 | Mesa - Del Amo - Serrano 500 kV Upgrade | Planning | 2033-11-02 |  |  | Monterey Park, Los Angeles County ¦Cerritos, Los Angeles County¦ Orange, Orange County |  | No | NA | NA | NA | Policy | T-Line Reliability | 41 | 40 ¦ 0.65 ¦ 1.02 | 500 | 1120 MVA ¦ 500kV ¦ 230kV | 2026-06-10 | 2033-12-31 | 2033-11-02 | Transmission Project Review Process data | -59 | No | N/A | N/A | Expected PEA Completion | 2026-11-30 | EIR | NA | CPUC | NA | CPCN | Not yet filed 2027-02-01 | To be Filed | NA |  | N/A
Antelope - Whirlwind - Raise approximately 9 towers in order to fix ground clearance and increase line rating to 3421/3880 MVA | 904186957 | CET-ET-TP-RL-857600 | 8576 | Antelope - Whirlwind - Raise approximately 9 towers in order to fix ground clearance and increase line rating to 3421/3880 MVA | Planning | 2026-01-06 |  |  | Lancaster, Los Angeles County ¦ Rosamond, Kern County |  | No | NA | NA | NA | Local Capacity Requirement | T-Line Reliability | 14 | NA | 500 | NA | 2025-10-01 | 2025-12-31 | 2026-01-06 | Transmission Project Review Process data | 6 | Yes | N/A | N/A | N/A | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA |  | N/A
TOT923 (Q1636) - Calypso Solar LLC. - Colorado River 500/220 (T) - Large Generator Interconnection Customer | Multiple Workorders | Multiple CWBSs | 8593 | TOT923 (Q1636) - Calypso Solar LLC. - Colorado River 500/220 (T) - Large Generator Interconnection Customer | Planning | 2031-07-10 |  |  | Blythe, Riverside County |  | Yes | NA | NA | NA | Generator Interconnection | Generation Interconnection | 4.01 | NA | 230 | NA | 2030-08-12 | 2031-04-01 | 2031-07-10 | Transmission Project Review Process data | 100 | Yes | N/A | N/A | N/A | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA |  | N/A | Q1636
New Inyo 230 kV Shunt Reactor | 904188170 | CET-ET-TP-Rl-695798 | 8599 | New Inyo 230 kV Shunt Reactor | Engineering more than 50% complete | 2026-09-25 |  |  | Bishop, Inyo County |  | No | NA | NA | NA | CAISO Transmission Planning Standards [See Notes for NERC Compliance and contingency code, WECC Requirement (and the specific requirement)] | Voltage Support | NA | 2.76 | NA | 230kV ¦ 115kV | 2026-06-01 | 2026-12-31 | 2026-09-25 | Transmission Project Review Process data | -97 | No | N/A | N/A | N/A | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA |  | N/A
Mirage 220/115 (S) - Install Phasor Measurement Unit (PMU) | 903853954 | CET-ET-TP-RL-848700 | 8487 | Mirage 220/115 (S) - Install Phasor Measurement Unit (PMU) | Operational | 2024-01-29 |  |  | Thousand Palms, Riverside County |  | No | NA | NA | NA | Reliability | Protection NERC Compliance | NA | 16.25 | NA | 220kV ¦ 115kV | 2023-08-28 | 2023-12-31 | 2024-01-29 | Transmission Project Review Process data | 29 | Yes | N/A | N/A | N/A | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA |  | N/A
Quartzite Solar 8 RNU (TOT749_Q1198) | 902598927 | CET-ET-CR-WC-820701 | 8207 | Quartzite Solar 8 RNU (TOT749_Q1198) | Operational | 2024-07-12 |  |  | Blythe, Riverside County |  | Yes | NA | NA | NA | Generator Interconnection | Generation Interconnection | 3.9 | 77 | 220 | 220kV ¦ 500kV | 2023-08-28 | 2022-01-15 | 2024-07-12 | Transmission Project Review Process data | 909 | Yes | Utility | Material | N/A | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA |  | N/A
New Lugo 3AA 500/230 kV Bank | 904187434 | CET-ET-TP-RN-695798 | 8600 | New Lugo 3AA 500/230 kV Bank | Engineering less than 50% complete | 2027-12-30 |  |  | Lugo, San Bernardino County |  | No | NA | SP-165¦SP-170 | SP-165¦SP-170 | Local Capacity Requirement | Substation Reliability | NA | 60 | NA | 1120 MVA ¦ 500kV ¦ 230kV | 2027-03-01 | 2027-12-31 | 2027-12-31 | Transmission Project Review Process data | 0 | No | N/A | N/A | N/A | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA |  | N/A | Q2103 | Q2097
Sylmar Sub: Replace 230kV/220kV Transformer with one rated for 1290 MVA normal and 1610 MVA Emergency (Procurement Only) | 904209302 | CET-ET-TP-RL-860200 | 8602 | Sylmar Sub: Replace 230kV/220kV Transformer with one rated for 1290 MVA normal and 1610 MVA Emergency (Procurement Only) | Planning | 2028-06-01 |  |  | Sylmar, Los Angeles County |  | No | NA | NA | NA | Local Capacity Requirement | Substation Reliability | NA | 46.4 | NA | 1290 MVA ¦ 230kV ¦ 230kV | 2025-11-10 | 2026-06-01 | 2028-06-01 | Transmission Project Review Process data | 731 | Yes | Utility | Material | N/A | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA |  | N/A
Serrano-Alberhill-Valley 500 kV 1 Line Upgrade (removing the limiting component which is the terminal equipment (i.e. substation work). | Multiple Workorders | Multiple CWBSs | 8608 | Serrano-Alberhill-Valley 500 kV 1 Line Upgrade (removing the limiting component which is the terminal equipment (i.e. substation work). | Engineering less than 50% complete | 2027-12-30 |  |  | Orange, Orange County ¦ Lake Elsinore, Riverside County ¦ Romoland, Riverside County |  | No | NA | NA | NA | Policy | T-Line Capacity | 39.5 | NA | 500 | NA | 2027-03-15 | 2028-12-31 | 2027-12-30 | Transmission Project Review Process data | -367 | No | N/A | N/A | N/A | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA |  | N/A | Q138 | Q1405 | Q1643 | Q1646 | Q1758 | Q1761
Kramer-Victor 115 kV to 230 kV Rebuild 7884 | Multiple Workorders | Multiple CWBSs | 8610 | Kramer-Victor 115 kV to 230 kV Rebuild 7884 | Planning | 2033-12-31 |  |  | Boron, Kern County ¦ Victorville, San Bernardino County |  | No | NA | SP-151¦SP-170 | SP-151¦SP-170 | Local Capacity Requirement | Substation Capacity | 64.29 | 20.89 ¦ 35.46 | 115 ¦ 220 | 115kV ¦ 230kV | 2026-05-18 | 2033-12-31 | 2033-12-31 | Transmission Project Review Process data | 0 | No | N/A | N/A | TBD | NA | NA | NA | NA | NA | NA | NA | Other [See Notes] | NA |  | N/A
San Bernardino-Vista 230 kV 1 Line Upgrade | Multiple Workorders | Multiple CWBSs | 8615 | San Bernardino-Vista 230 kV 1 Line Upgrade | Planning | 2028-06-19 |  |  | Redlands, San Bernardino County¦ Grand Terrace, San Bernardino County |  | No | NA | NA | NA | Local Capacity Requirement | T-Line Capacity | 8.18 | 8.54 ¦ 0.93 | 230 | 230kV | 2027-02-01 | 2026-12-31 | 2028-06-19 | Transmission Project Review Process data | 536 | Yes | Utility | Material | TBD | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA |  | N/A | Q138 | Q1405 | Q1643 | Q1646 | Q1758 | Q1761
Mesa - Mira Loma 500 kV UG Third Cable | Multiple Workorders | Multiple CWBSs | 8616 | Mesa - Mira Loma 500 kV UG Third Cable | Planning | 2027-01-14 |  |  | Monterey Park, Los Angeles County ¦ Ontario, San Bernardino County |  | No | NA | NA | NA | Address Results of Power Flow Analysis | Line Reconductoring | 3.98 | 79.67 ¦ 96.32 | 500 | 500kV | 2026-01-05 | 2026-12-31 | 2027-01-14 | Transmission Project Review Process data | 14 | Yes | N/A | N/A | TBD | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA |  | N/A | Q138 | Q1405 | Q1643 | Q1646 | Q1758 | Q1761
TOT910 (Q1642) Oberon | Multiple Workorders | Multiple CWBSs | 8308 | TOT910 (Q1642) Oberon | Operational | 2023-05-10 |  |  | Desert Center, Riverside County |  | Yes | NA | NA | NA | Generator Interconnection | Generation Interconnection | 4.5 | 75.7 | 500 ¦ 230 | 500kV ¦ 220kV ¦ 1120 MVA | 2022-08-01 | 2023-12-15 | 2023-05-10 | Transmission Project Review Process data | -219 | No | N/A | N/A | N/A | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA |  | N/A | Q1642
Vista-Etiwanda 230 kV 1 Line Upgrade | 904484617 | CET-ET-TP-RN-861700 | 8617 | Vista-Etiwanda 230 kV 1 Line Upgrade | Planning | 2027-01-29 |  |  | Grand Terrace, San Bernardino County ¦ Rancho Cucamonga, San Bernardino County |  | No | NA | NA | NA | Local Capacity Requirement | T-Line Capacity | 15.3 | 0.93 ¦ 44.58 | 230 | 230kV | NA | 2031-12-31 | 2027-01-29 | Transmission Project Review Process data | -1797 | No | N/A | N/A | TBD | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA |  | N/A | Q138 | Q1405 | Q1643 | Q1646 | Q1758 | Q1761
Devers-Valley No.1 500 kV Line Upgrade | Multiple Workorders | Multiple CWBSs | 8618 | Devers-Valley No.1 500 kV Line Upgrade | Planning | 2031-10-24 |  |  | Palm Springs, Riverside County ¦ Menifee, Riverside County |  | No | NA | NA | NA | Policy | T-Line Capacity | 42 | NA | 500 | NA | 2027-01-04 | 2028-12-31 | 2031-10-24 | Transmission Project Review Process data | 1027 | Yes | Utility | Material | TBD | NA | IS/MND | EA | CPUC | BLM | PTC | Not Yet Filed TBD | To be Filed | NA |  | N/A | Q138 | Q1405 | Q1643 | Q1646 | Q1758 | Q1761
Colorado River-Red Bluff No.1 500 kV Line Upgrade | 904238626 | CET-ET-TP-RN-861900 | 8619 | Colorado River-Red Bluff No.1 500 kV Line Upgrade | Planning | 2026-12-31 |  |  | Blythe, Riverside County ¦ Desert Center, Riverside County |  | No | NA | NA | NA | Policy | T-Line Capacity | 42 | NA | 500 | NA | 2026-10-01 | 2028-12-31 | 2026-12-31 | Transmission Project Review Process data | -731 | No | N/A | N/A | TBD | NA | IS/MND | EA | CPUC | BLM | PTC | Not Yet Filed TBD | To be Filed | NA |  | N/A
Atlas Solar Project (TOT870Q1402) | Multiple Workorders | CET-ET-CR-WC-833600 | 8336 | Atlas Solar Project (TOT870Q1402) | Operational | 2025-01-30 |  |  | Salome, La Paz County, Arizona |  | Yes | NA | NA | NA | Generator Interconnection | Generation Interconnection | 70 | 77 | 500 | 500kV | 2024-11-18 | 2022-10-01 | 2025-01-30 | Transmission Project Review Process data | 852 | Yes | Utility | Bundling Dependencies | N/A | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA |  | N/A
Devers-Red Bluff No.1 and No.2 500 kV Line Upgrade | Multiple Workorders | Multiple CWBSs | 8620 | Devers-Red Bluff No.1 and No.2 500 kV Line Upgrade | Planning | 2030-04-30 |  |  | Palm Springs, Riverside County ¦ Desert Center, Riverside County |  | No | NA | NA | NA | Policy | T-Line Capacity | 81 | NA | 500 | NA | 2028-10-02 | 2030-12-31 | 2030-04-30 | Transmission Project Review Process data | -245 | No | N/A | N/A | TBD | NA | IS/MND | EA | CPUC | BLM | PTC | Not Yet Filed TBD | To be Filed | NA |  | N/A | Q1405 | Q2042 | Q1761 | Q1643 | Q1642 | Q1764
San Bernardino-Etiwanda 230 kV 1 Line Upgrade | Multiple Workorders | Multiple CWBSs | 8630 | San Bernardino-Etiwanda 230 kV 1 Line Upgrade | Planning | 2031-02-14 |  |  | Redlands, San Bernardino County ¦ Rancho Cucamonga, San Bernardino County |  | No | NA | NA | NA | Local Capacity Requirement | T-Line Capacity | 21 | 8.54 ¦ 44.58 | 230 | 230kV | 2027-10-01 | 2031-12-31 | 2031-02-14 | Transmission Project Review Process data | -320 | No | N/A | N/A | TBD | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA |  | N/A | Q138 | Q1405 | Q1643 | Q1646 | Q1758 | Q1761 | Q1764
Lugo-Victor 230 kV Line Reconductor | Multiple Workorders | Multiple CWBSs | 8631 | Lugo-Victor 230 kV Line Reconductor | Planning | 2027-12-31 |  |  | Hesperia, San Bernardino County ¦ Victorville, San Bernardino County |  | No | NA | SP-151¦SP-165 | SP-151¦SP-165 | Address Results of Power Flow Analysis | Line Reconductoring | 43.2 | 34.81 ¦ 35.46 | 230 | 230kV | 2025-10-01 | 2031-12-31 | 2027-12-31 | Transmission Project Review Process data | -1461 | No | N/A | N/A | TBD | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA |  | N/A
TOT993 (Q1776) - Ventoso | Multiple Workorders | Multiple CWBSs | 8636 | TOT993 (Q1776) - Ventoso | On Hold | 2029-03-27 |  |  | Daggett, San Bernardino County |  | Yes | NA | NA | NA | Generator Interconnection | Generation Interconnection | 6 | 336.87 | 220¦115 | 220kV ¦ 115 kV | 2026-06-18 | 2027-02-01 | 2029-03-27 | Transmission Project Review Process data | 785 | Yes | Utility | Material | TBD | NA | NA | NA | NA | NA | Advice Letter | Not Yet Filed TBD | To be Filed | NA |  | N/A | Q1776
Etiwanda 220 kV Circuit Breaker Upgrade | 904435120 | CET-ET-TP-RL-865800 | 8658 | Etiwanda 220 kV Circuit Breaker Upgrade | Engineering less than 50% complete | 2029-08-20 |  |  | Rancho Cucamonga, San Bernardino County |  | No | NA | NA | NA | Reliability | Substation Reliability | NA | 26.36 | NA | 230kV | 2029-07-24 | 2030-12-31 | 2029-08-20 | Transmission Project Review Process data | -498 | No | N/A | N/A | N/A | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA |  | N/A | Q2032
TOT1002 (Q1782) - Willow Rock Energy Storage Project | 904441782 | CET-ET-TP-RN-866209 | 8662 | TOT1002 (Q1782) - Willow Rock Energy Storage Project | Engineering less than 50% complete | 2029-10-25 |  |  | Rosamond, Kern County |  | Yes | NA | NA | NA | Generator Interconnection | Generation Interconnection | 10.49 | 60 | 230 | 220kV | 2027-12-01 | 2029-11-16 | 2029-10-25 | Transmission Project Review Process data | -22 | No | N/A | N/A | N/A | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA |  | N/A | Q1782
TOT1028 (Q2113) - Gabriel Energy Storage | 904425203 | CET-ET-CR-WC-866401 | 8664 | TOT1028 (Q2113) - Gabriel Energy Storage | Engineering less than 50% complete | 2026-12-01 |  |  | Irwindale, Los Angeles County |  | Yes | NA | NA | NA | Generator Interconnection | Generation Interconnection | NA | 29.88 | NA | 220kV ¦ 66kV | 2026-10-26 | 2026-12-01 | 2026-12-01 | Transmission Project Review Process data | 0 | No | N/A | N/A | N/A | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA |  | N/A | Q2113
TOT1035 (Q2032) Trolley Project-Etiwanda Substation 220 kV | Multiple Workorders | Multiple CWBSs | 8668 | TOT1035 (Q2032) Trolley Project-Etiwanda Substation 220 kV | Engineering less than 50% complete | 2029-06-13 |  |  | Etiwanda, San Bernardino County |  | Yes | NA | NA | NA | Generator Interconnection | Generation Interconnection | NA | 17.13 | NA | 220kV ¦ 66kV | 2029-05-16 | 2030-08-10 | 2029-06-13 | Transmission Project Review Process data | -423 | No | N/A | N/A | N/A | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA |  | N/A | Q2032
TOT1029 (Q2114) - Dirac Energy Storage Project | 904445372 | CET-ET-TP-RN-867100 | 8671 | TOT1029 (Q2114) - Dirac Energy Storage Project | Planning | 2028-08-29 |  |  | Chino, San Bernadino County |  | Yes | NA | NA | NA | Generator Interconnection | Generation Interconnection | 0.6 | 10 | 230 | 220kV | 2028-05-05 | 2029-04-01 | 2028-08-29 | Transmission Project Review Process data | -215 | No | N/A | N/A | N/A | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA |  | N/A | Q2114
TOT1033 (Q2116) - Marici Project | 904442159 | CET-ET-TP-RN-867200 | 8672 | TOT1033 (Q2116) - Marici Project | Engineering less than 50% complete | 2026-12-01 |  |  | City of Industry, Los Angeles County |  | Yes | NA | NA | NA | Generator Interconnection | Generation Interconnection | 0.1 | 15.5 | 230 | 220kV | 2029-10-23 | 2029-04-01 | 2026-12-01 | Transmission Project Review Process data | -852 | No | N/A | N/A | N/A | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA |  | N/A | Q2116
Northern CRAS to Tehachapi CRAS | Multiple Workorders | Multiple CWBSs | 8009 | Northern CRAS to Tehachapi CRAS | Operational | 2020-09-23 |  |  | NA |  | No | NA | PB-07.01 ¦ PB-11.03 ¦ PB-11.07 ¦ PB-16.04 ¦ PB-16.17 ¦ PB-16.18 ¦ PB-18.11 ¦ PB-18.12 ¦ PB-19.01 ¦ SP-29 ¦ SP-58 ¦ SP-61 ¦ SP-81 ¦ SP-107 | PB-07.01 ¦ PB-11.03 ¦ PB-11.07 ¦ PB-16.04 ¦ PB-16.17 ¦ PB-16.18 ¦ PB-18.11 ¦ PB-18.12 ¦ PB-19.01 ¦ SP-29 ¦ SP-58 ¦ SP-61 ¦ SP-81 ¦ SP-107 | Reliability | Generation Interconnection | NA | NA | NA | NA | 2019-04-01 | 2018-12-31 | 2020-09-23 | Transmission Project Review Process data | 632 | Yes | Utility | Project Design | N/A | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Scope Change | Workforce
TOT1032 (Q2055) - Euismod Project | 904425207 | CET-ET-CR-WC-867301 | 8673 | TOT1032 (Q2055) - Euismod Project | Engineering more than 50% complete | 2027-07-28 |  |  | Rosamond, Kern County |  | Yes | NA | NA | NA | Generator Interconnection | Generation Interconnection | NA | 133.79 | NA | 500kV ¦ 220kV | 2027-06-30 | 2029-04-01 | 2027-07-28 | Transmission Project Review Process data | -613 | No | N/A | N/A | N/A | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA |  | N/A | Q2055
Valley Substation - TOT935 (Q1646) Double Butte Project | 904474007 | CET-ET-CR-WC-869902 | 8699 | Valley Substation - TOT935 (Q1646) Double Butte Project | Engineering less than 50% complete | 2028-06-23 |  |  | Menifee, Riverside County |  | Yes | NA | NA | NA | Generator Interconnection | Generation Interconnection | 0.5 | 78.97 | 500¦115¦12 | 500kV ¦ 115kV ¦ 12kV | 2028-05-26 | 2030-04-01 | 2028-06-23 | Transmission Project Review Process data | -647 | No | N/A | N/A | N/A | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA |  | N/A | Q1646

## 2. Generation Reporting
Generation Reporting
List every renewable energy and energy storage resource (with executed interconnection agreements) currently in the CAISO, WDAT, or other interconnection queues. |  |  | All fields are mandatory. Blank fields or data that doesn't match the Input Format on the Instructions tab will be considered incomplete. Tab sections in black text refer to transmission projects, tab sections in red text refer to generation projects.
Section 1: GENERATION RESOURCES DETAILS | [12 empty] | Section 2: GENERATION PROJECT NOTES | Section 3: CONNECTING TRANSMISSION PROJECTS
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
Generation Facility Name | In-Queue Number (CAISO or WDAT) | Generator Resource ID | Primary Developer | Developer Parent Company Name | Nameplate Capacity | Expected Annual RPS Eligible Generation | Planned Construction Start Date | Planned In-service Date | Interconnection Request Type | Technology Type | RPS Eligible | PTO Service Territory | Notes | Dependent on Delayed Transmission Project | Impact of Transmission Delay on Resource
Willow Rock Energy Storage | Q1782 | N/A | GEM A-CAES LLC | Hydrostor | 500 | N/A | N/A | 2029-11-16 | Fully Deliverable | Hybrid | No | SCE |  | No
Grace Energy Center | Q1761 | N/A | Nextera Energy Resources Interconnection Holdings, LLC | NextEra Energy Resources, LLC | 500 | 1314000 | N/A | 2026-11-13 | Energy Only | Hybrid/Paired Solar and Battery | Yes | SCE |  | Yes | The resource is impacted by the following delayed transmission projects: Eldorado-Lugo-Mohave RPS Upgrade, Lugo-Victorville 500 kV Transmission Line Upgrade, Gracesol Substation: Colorado River Substation-(IRNU-Shared) - TOT1006 (Q1761) Grace Energy Center, San Bernardino-Vista 230 kV 1 Line Upgrade, Mesa - Mira Loma 500 kV UG Third Cable, Devers-Valley No.1 500 kV Line Upgrade
Roadhouse Storage | Q1768 | N/A | NextEra Energy Resources Interconnection Holdings, LLC | NextEra | 300 | N/A | N/A | 2027-03-31 | Fully Deliverable | Battery Storage | No | SCE |  | Yes | The resource is impacted by the following delayed transmission projects: Eldorado-Lugo-Mohave RPS Upgrade, Roadhouse Storage Project (TOT1008/Q1768)
Cobalt | Q1757 | N/A | RE Cobalt LLC | Recurrent Energy | 250 | 657000 | N/A | 2026-08-02 | Fully Deliverable | Hybrid/Paired Solar and Battery | Yes | SCE |  | Yes | The resource is impacted by the following delayed transmission projects: Eldorado-Lugo-Mohave RPS Upgrade, Lugo-Victorville 500 kV Transmission Line Upgrade, Bolt Substation: Colorado River Substation-(IRNU-Shared) - TOT1013 (Q1757) Cobalt Project
Easley | Q2042 | N/A | IP Easley, LLC | Intersect Power | 650 | 3552688.08 | N/A | 2026-02-02 | Fully Deliverable | Hybrid/Paired Solar and Battery | Yes | SCE |  | No
Lake Elsinore Advanced Pumping Storage | 72 | N/A | The Nevada Hydro Company, Inc. | The Nevada Hydro Company, Inc. | 500 | N/A | N/A | TBD; see notes | Other [See Notes] | Conduit Hydro | No | SCE | ISD is on or before fifty three (53) months following the CPCN Approval Date of Alberhill Substation and receipt of payments pursuant to Appendix A, Section 17. | No
Stage Coach Solar | Q897 | N/A | Aurora Solar LLC | Aurora Solar LLC | 200 | 525600 | N/A | 2027-04-01 | Fully Deliverable | Solar | Yes | SCE |  | Yes | The resource is impacted by the following delayed transmission projects: Calcite Substation Construction, Stage Coach Solar RNU (TOT640_Q897)
Golden Fields Solar | Q1212 | N/A | Raven Solar Development Company, LLC | Clearway Energy | 100 | 262800 | N/A | 2026-07-02 | Fully Deliverable | Solar | Yes | SCE |  | Yes | The resource is impacted by the following delayed transmission project: Golden Fields Solar RNU (TOT754_Q1212)
Sienna Solar 1 | Q1207 | N/A | 99MT 8ME, LLC | Avantus | 200 | 525600 | N/A | 2028-05-01 | Fully Deliverable | Solar | Yes | SCE |  | Yes | The resource is impacted by the following delayed transmission project: Calcite Substation Construction
Aratina Solar Center 1 | Q1204 | N/A | 91MC 8me, LLC; 64NB 8me LLC; 98ES 8me LLC | Avantus | 200 | 525600 | N/A | 2025-11-01 | Fully Deliverable | Hybrid/Paired Solar and Battery | Yes | SCE |  | Yes | The resource is impacted by the following delayed transmission projects: Kramer Substation Interconnect (TOT773_Q1204), Aratina Solar
Tahoe {Phase 4} | Q1339 | N/A | Silver Peak Solar, LLC | 174 Power Global | 300 | 788400 | N/A | 2026-03-15 | Fully Deliverable | Hybrid/Paired Solar and Battery | Yes | SCE | 300 MW total. Of that, BESS resource for Phases 1 – 3 has 279 MW of FCDS and the BESS resource for Phase 4 has 21 MW of Energy-Only Deliverability Status (“EODS”). | No
Pastoria Solar | Q1335 | N/A | Pastoria Solar Energy Company, LLC | Calpine | 112.5 | 295650 | N/A | 2025-08-25 | Fully Deliverable | Solar | Yes | SCE |  | No
Alamitos Energy Center | 0002CONV | N/A | AES Alamitos Energy, LLC | AES | 674.8 | N/A | N/A | 2026-07-01 | Other [See Notes] | Battery Storage | No | SCE |  | No
Bellefield Solar Farm | Q1510 | N/A | 50LW 8ME LLC | AES | 500 | 1314000 | N/A | 2027-01-15 | Fully Deliverable | Hybrid/Paired Solar and Battery | Yes | SCE |  | Yes | The resource is impacted by the following delayed transmission project: Bellefield Solar Farm RNU (TOT892_Q1510)
Angeleno Solar Farm | Q1625 | N/A | 16DO 8ME LLC | Avantus | 1150 | 3022200 | N/A | 2027-11-19 | Fully Deliverable | Hybrid/Paired Solar and Battery | Yes | SCE |  | Yes | The resource is impacted by the following delayed transmission project: TOT903 - Q1625 - Angeleno Solar Farm
Aratina Solar Center 2 | Q1604 | N/A | 45MG 8me LLC | Avantus LLC | 200 | 525600 | N/A | 2025-12-01 | Fully Deliverable | Hybrid/Paired Solar and Battery | Yes | SCE |  | Yes | The resource is impacted by the following delayed transmission project: North of Lugo Centralized RAS (NoL CRAS)11225
Avocet Storage | Q1608 | N/A | Avocet Energy Storage, LLC | Arevon Energy | 200 | N/A | N/A | 2026-05-15 | Fully Deliverable | Battery Storage | No | SCE |  | Yes | The resource is impacted by the following delayed transmission project: Hinson 220/66 kV - TOT906 (Q1608) Avocet Energy Storage 200 MW Project Interconnection
Kestrel Storage | Q1615 | N/A | Kestrel Energy Storage, LLC | RWE | 200 | N/A | N/A | 2026-12-31 | Fully Deliverable | Battery Storage | No | SCE |  | Yes | The resource is impacted by the following delayed transmission project: Kestrel Storage Project (TOT907/Q1616)
Sanborn Hybrid 3 | Q1632 | N/A | Terra-Gen Development Company, LLC | Terra-Gen | 915.9 | 4246585.2 | N/A | 2026-06-01 | Fully Deliverable | Hybrid/Paired Solar and Battery | Yes | SCE |  | Yes | The resource is impacted by the following delayed transmission project: Sanborn Hybrid 3 - TOT915_Q1632
Lycan Solar Project | Q1643 | N/A | Lycan Solar, LLC | EDF Renewables | 400 | 1051200 | N/A | 2029-09-21 | Energy Only | Hybrid/Paired Solar and Battery | Yes | SCE |  | Yes | The resource is impacted by the following delayed transmission projects: Eldorado-Lugo-Mohave RPS Upgrade, Lugo-Victorville 500 kV Transmission Line Upgrade, San Bernardino-Vista 230 kV 1 Line Upgrade, Mesa - Mira Loma 500 kV UG Third Cable, Devers-Valley No.1 500 kV Line Upgrade , Lycan Solar (TOT921; Q1643)
Calypso Solar | Q1636 | N/A | Calypso Solar, LLC | EDF Renewables | 400 | 1370239.2 | N/A | 2031-04-01 | Energy Only | Hybrid/Paired Solar and Battery | Yes | SCE |  | Yes | The resource is impacted by the following delayed transmission projects: Eldorado-Lugo-Mohave RPS Upgrade, Lugo-Victorville 500 kV Transmission Line Upgrade, TOT923 (Q1636) - Calypso Solar LLC. - Colorado River 500/220 (T) - Large Generator Interconnection Customer
Commerce Energy Storage | Q1611 | N/A | Commerce Energy Storage, LLC | REV Renewables | 250 | N/A | N/A | 2025-10-01 | Fully Deliverable | Battery Storage | No | SCE |  | Yes | The resource is impacted by the following delayed transmission project: Commerce Energy Storage - TOT927_Q1611
Goldback Solar Center | Q1619 | N/A | 100RD 8me, LLC | Aypa Power | 500 | 1314000 | N/A | 2025-07-15 | Fully Deliverable | Hybrid/Paired Solar and Battery | Yes | SCE |  | Yes | The resource is impacted by the following delayed transmission project: Goldback Solar Center (TOT943 - Q1619)
Humidor Storage 1 | Q1629 | N/A | Hecate Grid Humidor 1 LLC | Hecate Energy | 300 | 791400 | N/A | 2025-10-01 | Fully Deliverable | Battery Storage | No | SCE |  | Yes | The resource is impacted by the following delayed transmission project: Humidor Storage - TOT959- Q1629
Bellefield 3 Solar Farm | Q1779 | N/A | 51LV 8Me, LLC | Avantus | 150 | 394200 | N/A | 2027-01-15 | Energy Only | Hybrid/Paired Solar and Battery | Yes | SCE |  | No
Sapphire Solar | Q1764 | N/A | Sapphire Solar, LLC | EDF Renewables | 117 | 307476 | N/A | 2027-02-12 | Energy Only | Solar | Yes | SCE |  | Yes | The resource is impacted by the following delayed transmission projects: Eldorado-Lugo-Mohave RPS Upgrade, Lugo-Victorville 500 kV Transmission Line Upgrade
Overnight Solar | Q1774 | N/A | Overnight Solar, LLC | Atlantica | 150 | 394200 | N/A | 2027-02-15 | Fully Deliverable | Hybrid/Paired Solar and Battery | Yes | SCE |  | Yes | The resource is impacted by the following delayed transmission project: North of Lugo Centralized RAS (NoL CRAS)11225
Sanborn 5 Hybrid | Q1791 | N/A | Terra-Gen Development Company, LLC | Terra-Gen | 550 | N/A | N/A | 2027-04-01 | Energy Only | Battery Storage | No | SCE |  | Yes | The resource is impacted by the following delayed transmission project: Windhub 220 kV - TOT985 - Q1791 - Sanborn 5 Hybrid
Ventoso | Q1776 | N/A | Thomas Sang, LLC | Capstone Infrastructure Corporation | 200 | 530856 | N/A | 2027-08-02 | Energy Only | Hybrid/Paired Solar and Battery | Yes | SCE |  | Yes | The resource is impacted by the following delayed transmission projects: TOT993 (Q1776) - Ventoso , North of Lugo Centralized RAS (NoL CRAS)11225
Delamar Energy Storage | Q1796 | N/A | Delamar Energy Storage, LLC | REV Renewables | 250 | N/A | N/A | 2026-04-01 | Fully Deliverable | Battery Storage | No | SCE |  | Yes | The resource is impacted by the following delayed transmission projects: Eldorado-Lugo-Mohave RPS Upgrade, Lugo-Victorville RAS, Lugo-Victorville 500 kV Transmission Line Upgrade, Delamar Energy Storage (TOT995; Q1796)
Commerce Energy Storage 2 | Q1766 | N/A | Commerce Energy Storage, LLC | REV Renewables | 250 | N/A | N/A | 2026-06-15 | Fully Deliverable | Battery Storage | No | SCE |  | No
Syracuse | WDT1267 | N/A | Syracuse Solar, LLC | Lendlease Energy Development LLC | 22 | 57816 | N/A | 2028-10-01 | Fully Deliverable | Solar | Yes | SCE |  | No
Tours | WDT1268 | N/A | Tours Solar, LLC | Lendlease Energy Development LLC | 22 | 57816 | N/A | 2028-10-01 | Fully Deliverable | Solar | Yes | SCE |  | No
Gettysburg | WDT1380 | N/A | Gettysburg Solar Farm, LLC | Lendlease Energy Development LLC | 20 | 52560 | N/A | 2025-11-30 | Fully Deliverable | Solar | Yes | SCE |  | No
Deer Creek Solar 1 | WDT1384 | N/A | Deer Creek Solar 1 LLC | Vistra Energy | 50 | 131400 | N/A | 2026-06-15 | Fully Deliverable | Hybrid/Paired Solar and Battery | Yes | SCE |  | No
Radiant Pappas | WDT1499 | N/A | Radiant BMT, LLC | Radiant West | 3 | 7884 | N/A | 2026-05-20 | Energy Only | Solar | Yes | SCE |  | No
Radiant Minneola | WDT1505 | N/A | BMT Minneola, LLC | Redwood Energy | 3 | 7884 | N/A | 2025-10-01 | Energy Only | Hybrid/Paired Solar and Battery | Yes | SCE |  | No
Windhub Solar B | WDT1515 | N/A | Windhub Solar B, LLC | Balanced Rock Power | 20 | 52560 | N/A | 2026-04-23 | Fully Deliverable | Solar | Yes | SCE |  | No
Portal Ridge Solar A | WDT1517 | N/A | Portal Ridge Solar A, LLC | Leeward Energy | 18.55 | 48749.4 | N/A | 2026-08-15 | Fully Deliverable | Solar | Yes | SCE |  | No
Trestles Grid | WDT1559 | N/A | Trestles Grid, LLC | Hecate Grid | 150 | N/A | N/A | 2025-12-20 | Energy Only | Battery Storage | No | SCE |  | No
Tulare 40 | WDT1580 | N/A | Coldwell Solar 1, LLC | Coldwell Solar | 40 | 105120 | N/A | 2026-07-01 | Fully Deliverable | Hybrid/Paired Solar and Battery | Yes | SCE |  | Yes | The resource is impacted by the following delayed transmission project: Rexford Solar Farm RNU (TOT896_Q1516)
Jazmin Solar 2 | WDT1623 | N/A | Imperial Renewables, LLC | Imperial Renewables, LLC | 2 | 5256 | N/A | 2026-11-01 | Energy Only | Hybrid/Paired Solar and Battery | Yes | SCE |  | No
Chiquito Grid | WDT1635 | N/A | Chiquito Grid, LLC | HECATE Grid LLC | 80 | N/A | N/A | 2026-01-30 | Fully Deliverable | Battery Storage | No | SCE |  | No
Gwent Storage 1 | WDT1647 | N/A | Hecate Grid Gwent 1, LLC | Hecate Energy | 134.9 | N/A | N/A | 2025-12-31 | Fully Deliverable | Battery Storage | No | SCE |  | No
Shirk Road ESS | WDT1650 | N/A | VESI 15 LLC | Ormat | 80 | N/A | N/A | 2025-12-01 | Fully Deliverable | Battery Storage | No | SCE |  | No
Griffith Energy Storage | WDT1652 | N/A | VESI 27 LLC | Ormat / Viridity Energy Solutions, Inc. | 100 | N/A | N/A | 2025-12-01 | Fully Deliverable | Battery Storage | No | SCE |  | No
Pier S Energy Storage | WDT1683 | N/A | Pier S Energy Storage LLC | Elevate Renewables | 70 | N/A | N/A | 2026-06-01 | Fully Deliverable | Battery Storage | No | SCE |  | No
EG-29 Palms-I | WDT1704 | N/A | E-Group PS LLC | E-Group PS LLC | 37.8 | 99338.4 | N/A | 2029-06-01 | Energy Only | Solar | Yes | SCE |  | No
Zephyr 40 MW Storage | WDT1706 | N/A | Engie Distributed Storage Development LLC | Engie Distributed Storage Development LLC | 39.8 | N/A | N/A | 2026-01-05 | Fully Deliverable | Battery Storage | No | SCE |  | No
Homestead Energy Storage,LLC | WDT1710 | N/A | Homestead Energy Storage, LLC | Homestead Energy Storage, LLC | 15 | N/A | N/A | 2025-12-31 | Fully Deliverable | Battery Storage | No | SCE |  | No
Isabella Hydroelectric | WDT1713 | VESTAL_6_QF | Isabella Partners | Hydro Dynamics | 11.95 | 26170.5 | N/A | 2025-07-01 | Other [See Notes] | Conduit Hydro | Yes | SCE | Will need MMA to push out date – no new movement on project | No
Horsetown Energy Storage | WDT1719 | N/A | Circle City Energy Storage LLC | Upstream Energy Services | 85 | N/A | N/A | 2025-12-31 | Fully Deliverable | Battery Storage | No | SCE |  | No
38630 National Trails Hwy | WDT1720 | N/A | Ralph Laks, Individual | Ralph Laks, Individual | 4.9 | 12877.2 | N/A | 2027-09-30 | Energy Only | Solar | Yes | SCE |  | No
Pearblossom Clean Power A | WDT1731 | N/A | Renewable America LLC | Renewable America LLC | 2 | 5256 | N/A | 2026-12-01 | Other [See Notes] | Hybrid/Paired Solar and Battery | Yes | SCE |  | No
McFadden Energy Storage | WDT1739 | N/A | Engie Distributed Storage Development, LLC | Engie Distributed Storage Development | 50.3 | N/A | N/A | 2026-01-15 | Fully Deliverable | Battery Storage | No | SCE |  | No
Greenbark 30 Energy Storage | WDT1740 | N/A | Greenbark30 BESS, LLC | GenOn | 30 | N/A | N/A | 2027-06-30 | Fully Deliverable | Battery Storage | No | SCE |  | No
Ranger Energy Storage | WDT1774 | N/A | Ranger Energy Storage, LLC | esVolta | 60 | N/A | N/A | 2029-02-08 | Fully Deliverable | Battery Storage | No | SCE | LA was terminated. New ISD will be identified if GIA is executed | No
Pronghorn Solar | WDT1782 | N/A | Pronghorn Solar Plus LLC | Upstream Energy | 38 | 99864 | N/A | 2026-03-15 | Fully Deliverable | Hybrid/Paired Solar and Battery | Yes | SCE |  | No
Jazmin Solar 1 | WDT1792 | N/A | Apex Energy Solutions, LLC | ZGlobal | 4 | 10512 | N/A | 2026-11-01 | Energy Only | Hybrid/Paired Solar and Battery | Yes | SCE |  | No
Ventura Reliability | WDT1808 | N/A | Ventura Reliability Project, LLC | Savion Energy | 100 | N/A | N/A | 2027-02-15 | Fully Deliverable | Battery Storage | No | SCE |  | No
Radiant Corral | WDT1809 | N/A | Radiant BMT, LLC | Radiant BMT, LLC | 3 | 7884 | N/A | 2025-10-27 | Energy Only | Solar | Yes | SCE |  | No
Westminster Reliability Project | WDT1816 | N/A | Westminster Reliability Project LLC | Upstream Energy | 110 | N/A | N/A | 2026-06-01 | Energy Only | Battery Storage | No | SCE |  | No
Blythe Solar Plus | WDT1823 | N/A | Blythe Solar Plus LLC | Upstream Energy | 11 | 28908 | N/A | 2025-11-01 | Fully Deliverable | Hybrid/Paired Solar and Battery | Yes | SCE |  | No
Covina Reliability Project | WDT1848 | N/A | RWE | Upstream Energy | 110 | N/A | N/A | 2026-12-01 | Fully Deliverable | Battery Storage | No | SCE |  | No
CPA Carson 20500 Fordyce | WDT1946 | N/A | ESCA-PLD-SOUTHBAY2, LLC | ProLogis Logistics Services | 1.38 | 3626.64 | N/A | 2025-10-25 | Other [See Notes] | Solar | Yes | SCE |  | No
CPA RFO-5959 Randolph | WDT1980 | N/A | ESCA-PLD-Commerce3, LLC | ProLogis Logistics Services | 1.24 | 3258.72 | N/A | 2025-08-25 | Other [See Notes] | Solar | Yes | SCE |  | No
Keyhole Wind | Q1784 | N/A | Keyhole Wind, LLC | EDF Renewables | 100 | 262800 | N/A | 2028-03-30 | Fully Deliverable | Wind | Yes | SCE |  | Yes | The resource is impacted by the following delayed transmission project: Keyhole Wind (TOT983)
Dirac Energy Storage Project | Q2114 | N/A | Dirac Project LLC | Aypa Power | 400 | N/A | N/A | 2028-08-29 | Fully Deliverable | Battery Storage | No | SCE |  | No
Marici Project | Q2116 | N/A | Marici Project LLC | Aypa Power LLC | 400 | N/A | N/A | 2026-12-01 | Fully Deliverable | Battery Storage | No | SCE |  | No
Gabriel Storage | Q2113 | N/A | San Gabriel Project LLC | Aypa Power | 400 | N/A | N/A | 2026-12-01 | Fully Deliverable | Battery Storage | No | SCE |  | No
Trolley Project | Q2032 | N/A | Trolley Pass Project LLC | Aypa Power | 400 | N/A | N/A | 2030-11-15 | Fully Deliverable | Battery Storage | No | SCE |  | No
Euismod Project | Q2055 | N/A | Euismod Project LLC | Aypa Power | 600 | 1576800 | N/A | 2029-04-01 | Fully Deliverable | Hybrid/Paired Solar and Battery | Yes | SCE |  | No
Double Butte Project | Q1646 | N/A | ACE Development Company, LLC | FTP Power, LLC dba sPower | 500 | 1314000 | N/A | 2030-04-01 | Fully Deliverable | Hybrid/Paired Solar and Battery | Yes | SCE |  | Yes
Arida 3 Solar Farm | Q1795 | N/A | 330MV 8ME LLC | Avantus | 450 | 1182600 | N/A | 2030-02-01 | Fully Deliverable | Hybrid/Paired Solar and Battery | Yes | SCE |  | Yes
Desert Sands | Q1758 | N/A | Nextera Energy Resources Interconnection Holdings, LLC | NextEra Energy Resources, LLC | 300 | N/A | N/A | 2026-06-01 | Fully Deliverable | Battery Storage | No | SCE |  | Yes
Sunrise Road Solar | WDT1813 | N/A | RPCA Solar 13, LLC | Renewable Properties | 14 | 36792 | N/A | 2026-01-15 | Energy Only | Solar | Yes | SCE |  | No
Plymouth Road Solar | WDT1805 | N/A | RPCA Solar 16, LLC | Renewable Properties | 15.96 | 41942.88 | N/A | 2025-09-14 | Energy Only | Solar | Yes | SCE |  | No
Haven Storage | Q2136 | N/A | Nextera Energy Resources Interconnection Holdings, LLC | NextEra Energy Resources, LLC | 300 | N/A | N/A | 2030-12-26 | Fully Deliverable | Battery Storage | No | SCE |  | No
Bolthouse A | WDT1830 | N/A | Wilsona CSG 1, LLC | Dimension Energy | 5 | 13140 | N/A | 2025-09-01 | Energy Only | Solar | Yes | SCE |  | No
38305 National Trails Project | WDT1720 | N/A | Ralph Laks, Individual | CRS LLC | 4.9 | 12877.2 | N/A | 2027-05-06 | Energy Only | Solar | Yes | SCE |  | No
Wallace Energy Storage | WDT1754 | N/A | ESS-CA-Wallace, LLC | Broad Reach Power II LLC | 55 | N/A | N/A | 2029-05-01 | Fully Deliverable | Battery Storage | No | SCE |  | No
Sandstorm Wind Power | Q138 | N/A | CABAZON WIND ENERGY, LLC | Terra Gen, LLC | 150 | 394200 | N/A | 2026-12-01 | Partially Deliverable | Wind | Yes | SCE |  | Yes | The resource is impacted by the following delayed transmission projects: San Bernardino-Vista 230 kV 1 Line Upgrade, Mesa - Mira Loma 500 kV UG Third Cable, Devers-Valley No.1 500 kV Line Upgrade
Athos Power Plant | Q1405 | N/A | SE Athos I, LLC | N/A | 450 | 1182600 | N/A | 2026-12-01 | Fully Deliverable | Solar | Yes | SCE |  | Yes | The resource is impacted by the following delayed transmission projects: Desert Harvest Generation Project (TOT486_Q643AE), Athos Power Plant RNU (TOT849_Q1405), WOCR CRAS Inland Devers Extension , San Bernardino-Vista 230 kV 1 Line Upgrade, Mesa - Mira Loma 500 kV UG Third Cable, Devers-Valley No.1 500 kV Line Upgrade
Oberon BESS | Q1642 | N/A | Intersect Power | IP Renewable Energy Holdings LLC | 500 | 1314000 | N/A | 2026-03-30 | Fully Deliverable | Hybrid/Paired Solar and Battery | Yes | SCE |  | Yes | The resource is impacted by the following delayed transmission projects: Eldorado-Lugo-Mohave RPS Upgrade, Lugo-Victorville 500 kV Transmission Line Upgrade, WOCR CRAS Inland Devers Extension
Menifee Power Bank 5 | Q1645 | N/A | Nova Power, LLC | Calpine Corporation | 680 | N/A | N/A | 2025-09-01 | Fully Deliverable | Battery Storage | No | SCE | Partially in-service, Phase 5 (62.8 MW) in-service 9/1/2025 | Yes | The resource is impacted by the following delayed transmission project: Menifee Power Bank (TOT934/Q1645)
Sienna Solar 2 | Q2097 | N/A | 44ST 8me LLC | 8minute Solar Energy LLC | 55 | 144540 | N/A | 2028-12-26 | Fully Deliverable | Hybrid/Paired Solar and Battery | Yes | SCE |  | Yes | The resource is impacted by the following delayed transmission project: Calcite Substation Construction
Cady Solar | Q2103 | N/A | Argenta Solar Energy Center, LLC | NextEra Energy Resources | 300 | 788400 | N/A | 2030-08-10 | Fully Deliverable | Hybrid/Paired Solar and Battery | Yes | SCE |  | No
Santa Fe Springs Energy Storage Project | WDT1725 | N/A | SFS Energy Storage LLC | N/A | 90 | N/A | N/A | 2026-05-01 | Fully Deliverable | Battery Storage | No | SCE |  | No
Roadhouse | Q1768 | N/A | NextEra Energy Resources Interconnection Holdings, LLC | NextEra Energy Resources, LLC | 300 | N/A | N/A | 2027-01-27 | Fully Deliverable | Battery Storage | No | SCE |  | Yes
Harper Solar | WDT1945 | N/A | Harper Solar LLC | N/A | 4 | 10512 | N/A | 2027-04-23 | Energy Only | Hybrid/Paired Solar and Battery | Yes | SCE |  | No
Lockhart Solar 1 & 2, SEGS Expansion Hybrid 2 | Q0043, Q1617, Q1775 | N/A | Terra-Gen Development Company, LLC | Terra Gen, LLC | 125 | 328500 | N/A | See notes | Fully Deliverable | Hybrid/Paired Solar and Battery | Yes | SCE | TOT697QFC, TOT914, TOT989; phased projects, latest estimated ISD - Phase 3, PV (125 MW): 3/1/25. Nameplate capacity = 125 MW of pending generation. | Yes | The resource is impacted by the following delayed transmission project: North of Lugo Centralized RAS (NoL CRAS)11225
Baldy Mesa 1 & 2 | Q1413, Q1519 | N/A | sPower Development Company, LLC | Sustainable Power Group, LLC | 200 | 525600 | N/A | 2025-11-01 | Fully Deliverable | Hybrid/Paired Solar and Battery | Yes | SCE |  | No
Luz 9 (SEGS 9) | QF5051, 0043CONV | N/A | Luz Solar Partners Ltd, IX | Terra-Gen, LLC | 80 | 210240 | N/A | 2025-10-01 | Fully Deliverable | Solar | Yes | SCE | Partially in-service but portion is in-construction. | No
Goleta Energy Center | WDT1187 | N/A | Wellhead Energy, LLC | Wellhead Electric | 99.5 | N/A | N/A | 2027-05-01 | Fully Deliverable | Battery Storage | No | SCE |  | No
Gaskell West | Q1074 | N/A | RE GASKELL WEST 1 LLC | Recurrent Energy | 125 | 328500 | N/A | 2026-10-02 | Fully Deliverable | Hybrid/Paired Solar and Battery | Yes | SCE |  | No
Tumbleweed Energy | Q1076 | N/A | Tumbleweed Energy LLC | First Solar Development, LLC | 50 | N/A | N/A | 2026-06-01 | Fully Deliverable | Battery Storage | No | SCE |  | No
Antelope Valley Complex | Q1215, Q1319 | N/A | Rabbitbrush Solar, LLC; Avep BESS, LLCFirst Solar | First Solar Development, LLC | 400 | N/A | N/A | 2023-01-14 | Fully Deliverable | Battery Storage | No | SCE | Sola and BOS battery storage; N/AMW; 400MW in-serviced | No
Tumbleweed Energy Storage 2 | Q1217 | N/A | Tumbleweed Energy, LLC | First Solar | 75 | 197100 | N/A | 2026-06-01 | Fully Deliverable | Hybrid/Paired Solar and Battery | Yes | SCE |  | Yes | The resource is impacted by the following delayed transmission project: Whirlwind Substation (RNU) (TOT778_Q1217)
Sanborn Solar 2 and Sanborn Hybrid 4 | Q1518, Q1790 | N/A | EdSan 1C Solar, LLC | TERRA-GEN DEVELOPMENT COMPANY, LLC | 600 | 1576800 | N/A | 2025-04-01 | Fully Deliverable | Hybrid/Paired Solar and Battery | Yes | SCE | 600MW; in-serviced | No
J90 Energy Storage | Q2059 | N/A | Terra-Gen Development Company, LLC | Terra Gen, LLC | 250 | N/A | N/A | 2033-03-15 | Fully Deliverable | Battery Storage | No | SCE |  | No
Twin Palms Solar | Q2048 | N/A | Twin Palms Solar, LLC (assigned by ACE Development Company, LLC) | AES Clean Energy Development, LLC | 313.2 | 823089.6 | N/A | 2030-02-01 | Fully Deliverable | Solar | Yes | SCE |  | No
Carson Hybrid Energy Storage [Addition to WDT1005QFC] | WDT1742 | N/A | Carson Hybrid Energy Storage LLC | Acme Engineering | 69.95 | N/A | N/A | 2026-03-01 | Fully Deliverable | Other [See Notes] | No | SCE | Gas Turbine and Battery Storage | No
Snow Peak Energy Storage | WDT1768 | N/A | VESI 44 LLC | Viridity Energy Solutions Inc. | 87.12 | N/A | N/A | 2028-12-01 | Fully Deliverable | Battery Storage | No | SCE |  | No
Olinda Reliability Project [see WDT2038] | WDT1907 | N/A | Olinda Reliability Project LLC | Upstream Energy | 117.5 | N/A | N/A | 2027-03-01 | Fully Deliverable | Battery Storage | No | SCE |  | No
Lear Avenue Solar | WDT1806 | N/A | RPCA Solar 15, LLC | Renewprop | 9.99 | 26253.72 | N/A | 2026-05-15 | Energy Only | Solar | Yes | SCE |  | No
NON-DIVESTED GENERATION – TULE POWER HOUSE (SCE WDT010) | WDT010 | N/A | SOUTHERN CALIFORNIA EDISON COMPANY GENERATION DEPARTMENT | SCE Grid Technology & Modernization | 2.5 | N/A | N/A | 2027-05-01 |  | Conduit Hydro | No | SCE | Its not clear if project meets RPS eligibility requirements for conduit hydro. | No
Eternal 2 | Q2050 | N/A | NextEra Energy Resources Interconnection Holdings, LLC | NextEra Energy Resources | 1400 |  | N/A | 2027-10-31 |  | Hybrid |  | SCE | Hydro and Battery Storage | Yes | The resource is impacted by the following delayed transmission project: Eldorado-Lugo-Mohave RPS Upgrade, Lugo-Victorville 500 kV Transmission Line Upgrade
Arida 2 Solar Farm | Q1647 | N/A | 328CH 8me LLC | 8minutenergy Renewables LLC | 700 | 1839600 | N/A | 2028-01-01 | Fully Deliverable | Hybrid/Paired Solar and Battery | Yes | SCE |  | Yes | The resource is impacted by the following delayed transmission project: Eldorado-Lugo-Mohave RPS Upgrade, Lugo-Victorville RAS, Lugo-Victorville 500 kV Transmission Line Upgrade, Gwent Storage 1 (SCE WDT 1647), ED&P scope of work for 500kV Gen-Tie TOT905/Q1647 Angora Solar Farm, Lugo-Victorville Centralized RAS
Arida Solar Farm | Q1522 | N/A | 326FW 8me LLC | 8minutenergy Renewables LLC | 370 | 972360 | N/A | 2028-01-01 | Fully Deliverable | Hybrid/Paired Solar and Battery | Yes | SCE |  | Yes | The resource is impacted by the following delayed transmission project: Eldorado-Lugo-Mohave RPS Upgrade, Lugo-Victorville RAS, ARIDA SOLAR FARM

## Choices
1. TRANSMISSION DELAY REPORTING | [11 empty] | 2. GENERATION REPORTING
6 | 11 | 12 | 15 | 16 | 17 | 28 | 29 | 30 | 32 | 33 | 38 | 10 | 11 | 12 | 13 | 15
Status | Caiso Study Area | GIDAP Related | Action Taken | Purpose | Purpose Details | Delay Resolver | In-service Date Change Reason | CEQA Status | CEQA Document Type | NEPA Document Type | CPUC Status | Interconnection Request Type | Technology Type | RPS Eligible | PTO Service Territory | Dependent on Delayed Transmission Project
Abandoned | PG&E: Humboldt Area | Yes | New | Address Results of Power Flow Analysis | 3rd Party Damage | Utility | Bundling Dependencies | CEQA Draft Published | EIR | EA | Approved | Energy Only | Battery Storage | Yes | PG&E | Yes
Canceled | PG&E: North Coast & North Bay Area | No | Relocate | Address Results of Protection Studies | Age/Condition | Customer | Clearances | CEQA Final Published | IS/MND | EIS | Filed and Under Administrative Review | Fully Deliverable | Biodiesel | No | SCE | No
Construction (10%-25%) | PG&E: North Valley Area |  | Removal | Age/End of Life | Age/Condition - 230/115/70/60 kV Relay Replacement | Developer | Completed Early | Expected PEA Completion | N/A | N/A | To be Filed | Partially Deliverable | Biogas |  | SDG&E
Construction (25%-50%) | PG&E: Central Valley Area |  | Replace | Asset Condition | Age/Condition - 500 kV Relay Replacement | CAISO | Financing | PEA Deemed Complete |  |  | Other [See Notes] | Other [See Notes] | Biomass |  | Other [See Notes]
Construction (50%-75%) | PG&E: Greater Bay Area |  | Upgrade/Retrofit | CAISO Transmission Planning Standards [See Notes for NERC Compliance and contingency code, WECC Requirement (and the specific requirement)] | Age/Condition - Anti Climb Guards | CPUC | ISO Action | Final Certified |  |  | N/A [See Notes] |  | Conduit Hydro
Construction (over 75%) | PG&E: Greater Fresno Area |  | N/A | Economic | Age/Condition - Insulator Replacement - Steel | Agency - Federal | Land Rights | N/A |  |  |  |  | Digester Gas
Construction (under 10%) | PG&E Kern Area |  | Multiple Options [See Notes] | Emergency Event | Age/Condition - Insulator Replacement - Wood | Agency - Local | Material | [5 empty] | Geothermal
Engineering less than 50% complete | PG&E: Central Coast & Los Padres Areas |  |  | Field Test Results | Age/Condition - Raptor Protection - Steel | Agency - State | Outage | [5 empty] | Hybrid
Engineering more than 50% complete | SCE: Tehachapi & Big Creek Corridor |  |  | Generator Interconnection | Age/Condition - Replace 230/115/70/60 kV Breakers | N/A | Permitting (CPUC/CEQA) | [5 empty] | Hybrid/Paired Solar and Battery
On Hold | SCE: North of Lugo Area |  |  | Load Growth | Age/Condition - Replace 230/115/70/60 kV Transformers |  | Permitting (non-CPUC/CEQA) | [5 empty] | Landfill Gas
Operational | SCE: East of Lugo Area |  |  | Local Capacity Requirement | Age/Condition - Replace 500 kV Breakers |  | Project Design | [5 empty] | Muni Solid Waste
Permitting | SCE: Eastern Area |  |  | Location, Environmental Conditions | Age/Condition - Replace 500 kV Transformers |  | Supply Chain Delays | [5 empty] | Ocean/Tidal
Planning | SCE: Metro Area |  |  | Physical Security | Age/Condition - Replace Boardwalks |  | Vendor Quality/Delays | [5 empty] | Pumped Storage
Other [See Notes] | SDG&E Area |  |  | Policy | Age/Condition - Replace Breakers |  | Weather | [5 empty] | Solar
| Valley Electric Association Area |  |  | Reliability | Age/Condition - Replace Civil Structures |  | Workforce Availability | [5 empty] | Various
| N/A |  |  | Safety | Age/Condition - Replace Conductor |  | N/A | [5 empty] | Wind
|  |  |  | Wildfire Mitigation | Age/Condition - Replace Insulators | [7 empty] | Other [See Notes]
|  |  |  | Work Requested by Others | Age/Condition - Replace Other Substation Equipment
|  |  |  | Another Project Or Resource [See Notes] | Age/Condition - Replace Other T-Line Equipment
|  |  |  | Other [See Notes] | Age/Condition - Replace Reactors, Age/Condition - Replace Relays
Age/Condition - Replace Relays
Age/Condition - Replace SCADA/RTU
Age/Condition - Replace Steel Poles
Age/Condition - Replace Switches, Age/Condition - Replace Transformers
Age/Condition - Replace Underground System
Age/Condition - Replace Wood Poles
Age/Condition - Switch Replacement - Steel
Age/Condition - Switch Replacement - Wood
Age/Condition - Targeted Relay Replacement
Age/Condition - Wood Pole Reframe
Animal Abatement
Automation
Bus Upgrade
Compliance - Remove Idle Facilities
Construct Roads/Gates/Culverts
Emergency Response - Fire Related
Emergency Response - Storm Related
Environmental
Facility Relocation
Fire Protection
Generation Interconnection
GO95 Mitigation - Steel
Install SCADA/RTU
Line Reconductoring
Line Termination
Load Interconnection
Modular Protection and Automation Control
NERC CIP Compliance
NERC Compliance - GO 95
New Substation
New T-Line
Priority 1 Steel Structure Replacement
Priority 1 Wood Structure Replacement
Protection NERC Compliance
Relay Upgrades
Replace Breakers
Replace Other Substation Equipment
Replace Transformer
Safety - Line Right of Way Access
SCADA Emergency Replacement
SCADA Switch Installation
Security Upgrades
Seismic Upgrade - Replace Conductor
Special Protection Scheme
Substation Capacity
Substation Reliability
System Design Upgrade
System Operations
Targeted Line Reliability
T-Line Capacity
T-Line Emergency
T-Line Reliability
Tools, Transformer Addition/Replacement
Underground Emergency
Voltage Conversion
Voltage Support
Other [See Notes]