## Projects
| Project Description | [32 empty] | Utility ¦CAISO Approval and FERC Rate Cases | [9 empty] | CPUC Permit Status | [9 empty] | Project Status | [7 empty] | Cost
1 | 2 | 3a | 3b | 4 | 5 | 6 | 7 | 7 | 8 | 9 | 10 | 11 | 11 | 12 | 13 | 14 | 15a | 15b | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 27b | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40a | 40b | 41a | 41b | 42a | 42b | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 52 | 53 | 54 | 55 | 56 | 57 | 57 | 57 | 57 | 57 | 58 | 58 | 58 | 58 | 58 | 58 | 59 | 60 | 61 | 62 | 63 | 63 | 63 | 63 | 63 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70
Row No | Project Name(s) | Latitude | Longitude | Location | Project Description | Project Description - What | Project Description - Action Taken | Project Description - Action Taken (2) | Project Dependencies | Primary Purpose | Secondary Purpose | NERC/WECC/CAISO Standard/Requirement/Contingency | NERC/WECC/CAISO Standard/Requirement/Contingency (2) | Last Inspection | Age of Asset | Types of Analyses | Alternative Solutions and Costs - Solutions | Alternative Solutions and Costs - Costs | CPUC Fire Threat Zone/Rating | Wildfire Related | RAMP | Other Environmental Factors | Project Manager2 | Transmission Project Size (length in miles) | Substation Project Footprint (acres) | Transmission Voltage Level (kV) | Substation or Transformer Capacity (MVA and/or kV) | Utility Prioritization Ranking | Utility Unique ID #1(Most Specific) | Utility Unique ID #2 (Less Specific) | Total Number of Projects under Parent Work Order | Utility Unique ID #3 (Least Specific) | Changes in Unique IDs | Utility Approval | Year of Internal Utility Approval | Process(es) for Utility Approval | Long term Transmission Investment Plan Inclusion | CAISO Year | TPP Phase 3 | Year(s) when considered in CAISO TPP | Year when expected to be considered in CAISO TPP | Link to TPP where project has been considered, approved, and/or expected to be considered | GIDAP-Related | CEQA Status | CEQA Status - Date | CEQA Document Type | NEPA Document Type | CEQA Lead Agency | NEPA Lead Agency | CPUC Filing Type | CPUC Date Filed | CPUC Status | CPUC Status - Year | Project Status | AACE Class | Construction Start Date | Original Planned In-Service Date | Current Projected or Actual In-Service Date | Reason for Change in In-Service Date | Reason for Change in In-Service Date (2) | In-Flight Projects | Original Projected Cost or Cost Range ($000) | Cost Cap ($000) | Current Projected Total or Actual Final Cost ($000) | Actual Capital Expenditures 2021 ($000) | Actual Capital Expenditures 2022 ($000) | Actual Capital Expenditures 2023 ($000) | Actual Capital Expenditures 2024 ($000) | Actual Capital Expenditures 2025($000) | Projected Capital Expenditures 2025 ($0000) | Projected Capital Expenditures 2026 ($000) | Projected Capital Expenditures 2027 ($000) | Projected Capital Expenditures 2028 ($000) | Projected Capital Expenditures 2029 ($000) | Projected Capital Expenditures 2030 ($000) | Construction Work in Progress ($000) | Accrued Overhead ($000) | Accrued AFUDC ($000) | FERC: Year(s) | 2021 Actual FERC Dollars Ratebased ($000) | 2022 Actual FERC Dollars Ratebased ($000) | 2023 Actual FERC Dollars Ratebased ($000) | 2024 Actual FERC Dollars Ratebased ($000) | 2025 Actual FERC Dollars Ratebased ($000) | 2026 Projected FERC Dollars Ratebased ($000) | Percentage of Bid | Percentage and Value ($000) of Work Requested by Others Passed onto Ratepayers | Cost-Benefit Analysis | FERC Incentives | Percentage of Cost in High Voltage TAC | Percentage of Cost in Low Voltage TAC | New Notes
1 | [Programmatic] Synchrophasors (PMU/WASA) |  |  | Multiple | This project provides funds for the installation, upgrade, and expansion of SDG&E’s Phasor Measurement Units (PMUs), commonly referred to as Synchronized Phasors or Synchrophasors which will be used for monitoring the health of the Electric System, Wide Area situational Awareness (WASA) and Wide Area Monitoring Protection and Control (WAMPAC). The project will install new PMUs or upgrade existing PMUs and install Phasor Data Concentrators (PDC), hardware, associated communication network, and software. | Substation - Protection Relay | Replace | Upgrade/Retrofit | NA | Reliability | Relay Upgrades | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | Individual Project Review Required |  | NA | NA | Multiple | 138 kV ¦ 230 kV ¦ 500 kV | 4.3 | Multiple | QBL0062 | 52 | 10138 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-12-11 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | TBD | TBD | NA | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | NA | 2024-12-31 | Multiple | NA | NA | TRUE | NA | NA ¦ NA | 31339.8822 | 639.667 | -147.8552 | 102.4974 | 640.9089 | 3132.022 | 1901.4929 | 4258.8384 | 4345.3211 | 4778.9201 | 5193.6793 | 0 | 1921.4576 | NA | NA | 2021 ¦ 2023 ¦ 2024 ¦ 2025 ¦ 2026 | 11.5456 | 0 | 1058.2385 | -1.5629 | 1377.5612 | 2472.238 | 0% | NA ¦ NA | 5.2 | NA | 13.55% | 86.45% | [CPUC Status] Exempt
2 | SYNCHRO VSUBS 2022 |  |  | Escondido, San Diego | PMU/WASA deployments at multiple substations | Substation - Protection Relay | Upgrade/Retrofit | NA | NA | Reliability | Relay Upgrades | NA | NA | 2025-10-29 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69 ¦ 500 | 373MVA | 4.3 | Multiple | QBL0062 | 1 | 10138 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2021-12-01 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2023-04-17 | 2023-12-31 | 2024-10-25 | Prioritization | NA | FALSE | 9874.4119 | NA ¦ NA | 7293.7181 | 674.9986 | 2679.2701 | 2462.7281 | 1464.331 | 12.3903 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2024 ¦ 2025 | 0 | 0 | 0 | 7281.3278 | 12.3903 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 13.55% | 86.45% | [CPUC Status] Exempt [Utility Unique ID #1(Less Specific)] 2021-2149 , 2022-3042
3 | TRANS SYNCHROPHASOR VAR SUB |  |  | Multiple | PMU/WASA deployments at multiple substations | Substation - Protection Relay | Upgrade/Retrofit | NA | NA | Reliability | Relay Upgrades | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69 ¦ 500 | 373MVA | 4.3 | Multiple | QBL0062 | 1 | 10138 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2018-03-23 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Construction (over 75%) | NA | NA | 2019-03-31 | Multiple | NA | NA | FALSE | 1403.683 | NA ¦ NA | 23781.9168 | 6187.6461 | 83.5886 | 271.2511 | 130.0683 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 | 6187.6461 | 83.5886 | 271.2511 | 130.0683 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 13.55% | 86.45% | [Utility Unique ID #1(Less Specific)] 2021-2143 , 2023-3601 , 2021-2051 , 2021-2042 , 2021-2026 , 2022-2933 , 2022-2935 , 2021-2401 , 2021-2130 , 2021-2149 , 2021-2132 , 2021-2134 , 2021-2148 , 2021-2136 , 2023-3594 , 2023-3600 , 2023-3602 , 2018-1009 , 2021-2131 , 2019-2124 , 2023-3595 , 2021-2035 [CPUC Status] NA
4 | WASA SYNCHROWAVE SOFTWARE APPL |  |  | San Diego, San Diego | Continued development of WASA-Synchrowave Central software application. Enhancements includes Linear State Estimating (LSE), Phase Contour, addition of Operations and Admin roles, phase angle reference, and support for end-user configuration. | Other - Operations Tech | Upgrade/Retrofit | NA | NA | Reliability | Automation | NERC CIP Compliance | NERC CIP Compliance | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | NA | NA | 4.3 | NA | QBL0062 | 1 | 10138 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-10-30 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | PEA Deemed Complete | NA | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Engineering more than 50% complete | NA | 2024-01-01 | 2025-12-31 | 2025-12-31 | NA | NA | FALSE | 1585.0195 | NA ¦ NA | 2623.6117 | 0 | 0 | 0 | 1448.4178 | 447.5799 | 727.6141 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2025 | 0 | 0 | 0 | 0 | 2623.6117 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] Exempt
5 | [Programmatic] Transmission Substation Responsive Asset Replacement |  |  | Multiple | This budget is required to maintain the reliability and integrity of Transmission substations. The specific work required to meet safety requirements, replace obsolete or failed equipment, and make necessary small capital additions is based on requests from Engineering, Planning, Operations, and Maintenance groups. | Substation - Multiple | New | Upgrade/Retrofit | NA | Reliability | Substation Reliability | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | Multiple | NA | 4.1 | Multiple | QB00012 | 126 | 103 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-12-16 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | Other [See Notes] | TBD | Exempted | NA | NA | NA | NA | NA | To be Filed | NA | Operational | NA | NA | 2024-12-31 | Multiple | NA | NA | TRUE | NA | NA ¦ NA | 114782.1331 | -116.5513 | -73.094 | 834.566 | 1630.4499 | 4114.0591 | 3161.318 | 4795.0931 | 5330.8209 | 5927.2308 | 6587.5452 | 7311.4937 | 3568.4531 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 ¦ 2026 | 831.448 | 41.6286 | 1105.1901 | -576.9645 | 1419.6745 | 4758.6804 | 0% | NA ¦ NA | 2.1 | NA | 13.55% | 86.45% | [Types of Analyses] Responsive budget due to reactive work at substation; projects are under Programmatic budget;
6 | IID, SRP, APS SDGE SHARE ON CAP |  |  | Multiple | Capital upgrades between Arizona Public Services, Salt River Project and IID | Substation - Other Equipment | Upgrade/Retrofit | NA | NA | Work Requested by Others | Substation Reliability | NA | NA | 2025-04-26 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | NA | NA | 4.1 | NA | QB00012 | 1 | 103 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2021-12-28 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | Expected PEA Completion | TBD | Exempted | NA | NA | NA | Exempt | NA | To be Filed | NA | Operational | NA | 2022-12-28 | 2022-12-31 | 2022-12-31 | Weather | NA | FALSE | 3866.5808 | NA ¦ NA | 11631.202 | 0 | 12271.1182 | -586.1013 | 39.5816 | -93.3965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 0 | 12271.1182 | -586.1013 | 39.5816 | -93.3965 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [Reason for Change in In-Service Date] SDGE does not manage the construction of these projects and that it up to the APS and IID to manage the construction that would be great, other wise I would say customer action
7 | KYOCERA BK 30 REPLACEMENT |  |  | San Diego, San Diego | Replace Bk30 at Kyocera Substation | Substation - Transformer | Replace | Upgrade/Retrofit | NA | Reliability | Substation Reliability | NA | NA | 2025-11-04 | 7 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 0.17 | 69 | 69 kV | 4.1 | 2019-1024 | QB00012 | 1 | 103 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-09-25 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | To be Filed | NA | Construction (50%-75%) | NA | 2023-06-12 | 2020-12-31 | 2025-01-01 | Construction Delays | NA | FALSE | NA | NA ¦ NA | 2373.9209 | 188.5972 | 184.1777 | 958.5305 | 331.427 | 147.3711 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2023 ¦ 2024 ¦ 2025 | 0 | 0 | 1895.1228 | 331.427 | 147.3711 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
8 | IID, SRP, APS SDGE SHARE ON CAP |  |  | Multiple | Capital upgrades between Arizona Public Services, Salt River Project and IID | Substation - Other Equipment | Upgrade/Retrofit | NA | NA | Work Requested by Others | Substation Reliability | NA | NA | 2025-04-26 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | NA | NA | 4.1 | NA | QB00012 | 1 | 103 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-04-03 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | To be Filed | NA | Operational | NA | 2020-04-03 | 2020-12-31 | NA | NA | NA | FALSE | 1115.598 | NA ¦ NA | 2577.8396 | 1037.2104 | 1.0071 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 | 1037.2104 | 1.0071 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [Reason for Change in In-Service Date] SDGE does not manage the construction of these projects and that it up to the APS and IID to manage the construction that would be great, other wise I would say customer action
9 | MIGUEL BK80 12KV TERTIARY BREAK |  |  | San Diego County | Replace (3) 12kv Tertiary breakers; install two SEL487 relay panels | Substation - Circuit Breaker | Replace | Upgrade/Retrofit | NA | Reliability | Substation Reliability | NA | NA | 2025-11-14 | 24; 24; 24 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 12.37 | 12 | 230 kV ¦ 69 kV ¦ 12 kV | 4.1 | 2019-1018 | QB00012 | 1 | 103 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-02-08; 2019 -12-10 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | To be Filed | NA | Operational | NA | 2020-05-04 | 2019-12-31 | 2023-11-14 | Project design | NA | FALSE | 2515.493 | NA ¦ NA | 3950.8774 | 336.7671 | 229.9036 | 1335.5361 | 305.771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2023 ¦ 2024 | 0 | 0 | 1012.1408 | 2938.7366 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
10 | SAN ONOFRE RTV COATING |  |  | San Diego, San Diego | Remove existing Insulgrease on all 230kV insulators and bushings at San Onofre Substation. Apply RTV silicone (room-temperature vulcanizing silicone) coating to all 230kV insulators and bushings. | Substation - Multiple | New | New | NA | Safety | 3rd Party Damage | NERC CIP Compliance | NERC CIP Compliance | 2025-10-16 | NA | NA | NA | NA | Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 5.14 | 230 | 230kV | 4.1 | NA | QB00012 | 1 | 103 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-10-10 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | CPUC | NA | Exempt | NA | To be Filed | NA | Operational | NA | 2024-10-10 | 2025-07-01 | 2025-01-07 | Completed early | NA | FALSE | 1244.8453 | NA ¦ NA | 1135.7012 | 0 | 0 | 0 | 566.3842 | 523.5822 | 45.7348 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2025 | 0 | 0 | 0 | 0 | 1135.7012 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0%
11 | [Programmatic] Renewal of Electric Transmission Line Easements |  |  | Multiple | The purpose of this parent work order is to renew various easements and/or permits for transmission rights of way that will expire within the next 5 years. These easements will allow SDGE to install and maintain electric transmission facilities across public and private lands. These transmission lines are an integral part of our electric transmission system. | Transmission Line - Right of Way | NA | NA | NA | Other [See Notes] | System Operations | NA | NA | NA | NA | NA | NA | NA | Tier 1¦ Tier 2 ¦ Tier 3 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | Multiple | NA | NA | Multiple | QB00008 | 5 | 104 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-12-11 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | NA | NA | To be Filed | NA | Operational | NA | NA | NA | Multiple | NA | NA | TRUE | NA | NA ¦ NA | 92254.4041 | 30.7355 | 71.7872 | 16.0811 | 78.1974 | 5020.1766 | 5020.1766 | 1300.6678 | 793.6871 | 800.2113 | 1009.0213 | 961.2887 | 0 | NA | NA | 2021 ¦ 2024 ¦ 2025 ¦ 2026 | 30.8162 | 0 | 0 | 171.2547 | 5020.1766 | 1300.6678 | 0% | NA ¦ NA | 12.6 | NA | 13.55% | 86.45% | [Primary Purpose] Easement review
12 | TL 682 LA JOLLA ET EASEMENT |  |  | San Diego County | Renewal of TL 682 Transmission Easement | Transmission Line - Right of Way | NA | NA | NA | Other [See Notes] | Safety - Line Right of Way Access | NA | NA | 2025-01-07 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69 | NA | NA | NA | QB00008 | 1 | 104 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2022-06-27 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | EA | NA | BIA | Exempt | NA | NA [See Notes] | NA | Operational | NA | NA | NA | 2024-08-30 | NA | NA | FALSE | 674.9614 | NA ¦ NA | 1757.7589 | 0 | 440.5826 | 709.3057 | 530.0569 | 77.8137 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2024 ¦ 2025 | 0 | 0 | 0 | 1679.9451 | 77.8137 | 0 | 0% | NA ¦ NA | 1.3 | NA | 0% | 100% | [Primary Purpose] Easement review [CPUC Status] NA
13 | [Programmatic] Electric Transmission Tools & Equipment |  |  | NA | Purchase tools and test equipment to support the safe and reliable operations of substation and transmission equipment. | Substation - Multiple | New | Replace | NA | Reliability | Substation Reliability | NA | NA | NA | NA | NA | NA | NA | Tier 1 ¦ Tier 2 ¦ Tier 3 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | NA | NA | 1.3 | Multiple | QB00145 | 1 | 106 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-11-22 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | TBD | NA | NA | NA | CPUC | NA | NA | NA | NA | NA | Operational | NA | NA | 2025-12-31 | Monthly | NA | NA | TRUE | NA | NA ¦ NA | 3025.454 | 86.2931 | 83.1998 | 93.5771 | 76.5512 | 157.3892 | 135.7782 | 146.2887 | 161.171 | 177.4282 | 195.1874 | 213.7613 | 12.2793 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 ¦ 2026 | 86.2931 | 83.1998 | 93.5771 | 76.5512 | 145.1099 | 145.8775 | 0% | NA ¦ NA | 2.2 | NA | 0% | 0% | [CPUC Status] NA
14 | [Programmatic] Transmission Substation Proactive Asset Program |  |  | Multiple | The Substation Equipment Assessment Team will develop alternatives to replace or remove obsolete and problematic equipment. A condition assessment process and evaluation criteria have been created using probability and risk analysis, financial impacts and present value analysis to justify projects. Equipment that is truly obsolete such as equipment that cannot be maintained (no spare parts available), or which poses a safety risk will be replaced. Each year the average age of all substation equipment increases, with the oldest transformer currently 60+ years old. The ranking of substation equipment is an ongoing process and involves identifying equipment that presents a significant risk to the system. Based on the cost availability of raw materials and global demand, the lead times for major substation equipment have increased to 6 months for breakers and at least 1.5 years for transformers. | Substation - Multiple | Replace | Upgrade/Retrofit | NA | Reliability | Substation Reliability | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | Multiple | NA | 4.1 | Multiple | QBL0003 | 228 | 1145 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-12-11 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | Expected PEA Completion | TBD | Exempted | NA | NA | NA | NA | NA | To be Filed | NA | Planning | NA | NA | 2024-12-31 | Multiple | NA | NA | TRUE | NA | NA ¦ NA | 190838.6047 | 2098.7396 | 3543.0102 | 3556.8307 | 2878.4288 | 8424.62 | 7247.9056 | 8009.198 | 9325.0397 | 10724.6245 | 11927.6742 | 13247.1603 | 3530.5163 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 ¦ 2026 | 1491.0718 | 3832.8418 | 3061.685 | 6037.7036 | 2547.8108 | 7687.1278 | 0% | NA ¦ NA | 3.7 | NA | 13.55% | 86.45%
15 | MIGUEL FIRE PROTECTION SYS REPR |  |  | San Diego County | Repair of Fire protection system at Miguel | Other - Civil | Upgrade/Retrofit | Upgrade/Retrofit | NA | Safety | Fire Protection | NA | NA | 2025-11-14 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 2.9 | 69 ¦500 | NA | 4.1 | NA | QBL0003 | 1 | 1145 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-10-01 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | Expected PEA Completion | TBD | Exempted | NA | NA | NA | Exempt | NA | To be Filed | NA | Operational | NA | 2019-10-03 | 2020-12-31 | 2021-05-18 | Construction Delays | NA | FALSE | 69.27 | NA ¦ NA | 1746.3209 | 759.4003 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 | 1746.3209 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 13.55% | 86.45%
16 | GLENCLIFF SUB ADD 69KV BREAKER |  |  | San Diego, San Diego | Install 69kv Bank Breaker and SCADA | Substation - Circuit Breaker | New | New | NA | Reliability | Substation Reliability | NA | NA | 2025-11-12 | 7 | NA | NA | NA | Tier 3 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 0.15 | 69 | 69 kV | 4.1 | 2014-01091-ZZ | QBL0003 | 1 | 1145 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2018-03-04;2019-09-16; 2019-09-16 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | Expected PEA Completion | TBD | Exempted | NA | NA | NA | Exempt | NA | To be Filed | NA | Operational | NA | 2020-07-27 | 2019-03-01 | 2020-11-04 | Construction Delays | NA | FALSE | 1165.524 | NA ¦ NA | 2025.9441 | 280.8401 | 72.345 | 0 | 0.99677 | 0.12232 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2022 ¦ 2024 ¦ 2025 | 0 | 2024.825 | 0 | 0.99677 | 0.12232 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
17 | MERCHANT REPLACE 3 230KV BRKR |  |  | NA | Replace (3) Oil circuit breakers due to leaking hydraulic fluid | Substation - Circuit Breaker | Replace | Upgrade/Retrofit | NA | Safety | Substation Reliability | NA | NA | 2025-11-05 | 28; 28; 28 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 72.12 | 230 | NA | 4.1 | 2020-1020 | QBL0003 | 1 | 1145 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-06-07 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | Expected PEA Completion | TBD | Exempted | NA | NA | NA | Exempt | NA | To be Filed | NA | Construction (over 75%) | NA | 2022-03-31 | 2020-11-30 | 2025-08-05 | Project Design | NA | FALSE | 95.52 | NA ¦ NA | 8332.7371 | 750.5718 | 1271.3793 | 2355.3583 | 1372.2536 | 2023.5664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2025 | 0 | 0 | 0 | 0 | 8332.7371 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0%
18 | PENAQUITOS SUBST 230KV DISCON R |  |  | San Diego, San Diego | Replace (8) 230kv disconnect switches, (8) 230kv disconnect stands, and upgrade the associated concrete pads | Substation - Switch | Replace | Upgrade/Retrofit | NA | Reliability | Substation Reliability | NA | NA | 2025-11-16 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 13.94 | 230 | 230kV | 4.1 | 2019-1022 | QBL0003 | 1 | 1145 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-06-20 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | Expected PEA Completion | TBD | Exempted | NA | NA | NA | Exempt | NA | To be Filed | NA | Operational | NA | 2020-04-13 | 2020-07-06 | 2021-07-27 | Weather | NA | FALSE | 2270.915 | NA ¦ NA | 2597.4832 | 1102.6513 | 3.3797 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 | 2594.1036 | 3.3797 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0% | [Reason for Change in In-Service Date] In-service dates are estimated during preliminary design and permitting stages of a project; date shifted to reflect actual design and construction schedule.
19 | SCRIPPS SUBST RPL 69KV BUS DISC |  |  | San Diego, San Diego | Replace 69KV bus disconnects for BK 30,31 & 32, existing disconnects are breaking down and limited spare parts since these were manuf.; use (3) spare EVB ( 69kv,1200A) switches from Caspian for this work | Substation - Bus Arrangement | Replace | Replace | NA | Age/End of Life | Age/Condition | NA | NA | 2025-11-06 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 1.1 | 69 | 69 kV | 4.1 | 2020-1038 | QBL0003 | 1 | 1145 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-07-24 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | To be Filed | NA | Operational | NA | 2022-01-10 | 2020-12-31 | 2023-04-14 | Project design | NA | FALSE | 189.161 | NA ¦ NA | 1783.4936 | 323.5922 | 1079.982 | 376.5437 | 0.07194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2023 ¦ 2024 | 0 | 0 | 1783.4216 | 0.07194 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
20 | MURRAY RPL RELAY ON TL 618,619, |  |  | San Diego, San Diego | Remove existing control shelter and panels, RTU & CBM cabinets, AC/DC panels; install new control shelter and panels, new CBM & Telecom cabinets, new AC/DC panels. | Substation - Multiple | Removal | New | NA | Reliability | Age/Condition - Replace Other Substation Equipment | NA | NA | 2025-11-05 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 9 | 69 | 69 kV | 4.1 | 2014-00247-ZZ | QBL0003 | 1 | 1145 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2017-04-24 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | Expected PEA Completion | TBD | Exempted | NA | NA | NA | Exempt | NA | To be Filed | NA | Operational | NA | 2017-07-25 | 2019-12-31 | 2021-06-09 | Project design | NA | FALSE | 2832.691 | NA ¦ NA | 3532.7589 | 191.4279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 | 3532.7589 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
21 | IMPERIAL VALLEY MAST RPL |  |  | Imperial County | Replacement of Static Mast structures at Imperial Valley | Substation - Structure | Replace | Replace | NA | Age/End of Life | Age/Condition | NA | NA | 2025-11-18 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 55.48 | 500 | 500 kV | 4.1 | 2020-1025 | QBL0003 | 1 | 1145 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-04-29 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | Expected PEA Completion | TBD | Exempted | NA | NA | NA | Exempt | NA | To be Filed | NA | Operational | NA | 2021-01-25 | 2019-12-31 | 2024-01-17 | Project design | NA | FALSE | 558.815 | NA ¦ NA | 1281.6462 | 225.8838 | 220.1826 | 281.4983 | 31.0638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2024 | 0 | 0 | 0 | 1281.6462 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0%
22 | PENASQUITOS AGING INFRS. 138K B |  |  | San Diego, San Diego | Replace (5)138kV Breakers | Substation - Circuit Breaker | Replace | Upgrade/Retrofit | NA | Reliability | Age/Condition - Replace Breakers | NA | NA | 2025-11-16 | 62; 59; 46; 46 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 13.94 | 138 | 138 kV | 4.1 | 2021-2457 | QBL0003 | 1 | 1145 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-05-08 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | To be Filed | NA | On Hold | NA | 2025-09-05 | 2020-12-31 | 2027-07-07 | Weather | NA | TRUE | 1313.224 | NA ¦ NA | 2237.3351 | 48.2835 | 509.533 | 469.8479 | 479.3168 | 57.2646 | 90.7774 | 137.0128 | 0 | 0 | 0 | 0 | 2009.5449 | NA | NA | 2026 | 0 | 0 | 0 | 0 | 0 | 2237.3351 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [Reason for Change in In-Service Date] Project was placed on hold under further review.
23 | SAN YSIDRO AGING INFRAS. 69KV B |  |  | San Diego, San Diego | Replace (3) 69kV circuit breakers at San Ysidro | Substation - Circuit Breaker | Replace | Upgrade/Retrofit | NA | Reliability | Age/Condition - Replace Breakers | NA | NA | 2025-10-08 | 53; 53; 33 | NA | NA | NA | Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 1.57 | 69 | 69 kV ¦ 12 kV | 4.1 | 2020-1030 | QBL0003 | 1 | 1145 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-05-09 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | Expected PEA Completion | TBD | Exempted | NA | NA | NA | Exempt | NA | To be Filed | NA | Operational | NA | 2021-08-02 | 2020-12-31 | 2023-03-14 | Construction Delays | NA | FALSE | 741.287 | NA ¦ NA | 2156.2311 | 475.4767 | 349.219 | 804.8363 | 122.8656 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2023 ¦ 2024 | 0 | 0 | 2033.3655 | 122.8656 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
24 | TORREY PINES TL662 REPLACEMENT |  |  | San Diego, San Diego County | Replace 69kV CB4 and CB5 with new gas breakers Install (2) new 4 inch conduits for each breaker part of replacement Install new cables for each breaker part of replacement Install new zipper box for each breaker part of replacement Repair/install new ground leads for each breaker part of replacement Install (2) new 4 inch conduits to spare breaker pad | Substation - Circuit Breaker | Replace | Upgrade/Retrofit | NA | Reliability | Age/Condition - Replace Breakers | NA | NA | 2025-11-07 | 33; 33 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | TBD |  | NA | 0.79 | 69 | 12 kV ¦ 69KV | 4.1 | 2024-4121 | QBL0003 | 1 | 1145 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-10-10 | Work Order Authorization | 2024 | NA | FALSE | NA | NA | NA | FALSE | Expected PEA Completion | TBD | Exempted | NA | CPUC | NA | NA | NA | To be Filed | NA | Construction (50%-75%) | NA | 2024-07-15 | 2025-01-31 | 2025-08-06 | NA | NA | FALSE | 767.5924 | NA ¦ NA | 3743.9261 | 0 | 0 | 6.1175 | 1586.4526 | 2108.0221 | 43.3339 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2025 | 0 | 0 | 0 | 0 | 3743.9261 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] - new project no construction date
25 | FELECITAS AGING INFRAS. 69KV BR |  |  | Escondido, San Diego | The purpose of this project is to upgrade the reliability of Felicita Substation by replacing equipment exceeding 47 years in service, adding a new high side bank circuit breaker, and upgrading the line, bank, and bus relay protection associated with the circuit breakers being installed. | Substation - Circuit Breaker | Upgrade/Retrofit | Upgrade/Retrofit | NA | Reliability | Age/Condition | NA | NA | 2025-10-08 | 53; 50; 41 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | TBD |  | NA | 1.51 | 69 | 69KV | 4.1 | 2019-1021 | QBL0003 | 1 | 1145 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-05-08 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | Expected PEA Completion | TBD | Exempted | NA | CPUC | NA | Exempt | NA | To be Filed | NA | Engineering more than 50% complete | NA | 2025-09-18 | 2020-12-31 | 2026-02-17 | Project design | NA | FALSE | 741.287 | NA ¦ NA | 2262.6691 | 36.1215 | 149.7262 | 428.3646 | 1300.2126 | 97.3281 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2024 ¦ 2025 | 0 | 0 | 0 | 2165.341 | 97.3281 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] NA
26 | [Programmatic] Automated Fault Location (TEAM) |  |  | Multiple | This project provides funds for installation, upgrade, and expansion of SDG&Es Event Reporting Software and hardware to include Automated Fault Locator. This new system known as TEAM will provide accurate fault location within seconds by measuring the parameters at both ends of the line (multiple ends on multi-terminal lines) and time synchronizing the events with GPS clock. | Substation - Multiple | Upgrade/Retrofit | NA | NA | Reliability | Automation | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | Multiple | 373MVA | 4.3 | Multiple | QBL0063 | 3 | 12129 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2022-10-05 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | NA | 2022-12-31 | 2022-12-31 | Input Error | NA | FALSE | NA | NA ¦ NA | 815.8623 | 422.6652 | 81.1314 | 7.0931 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2022 ¦ 2023 | 0 | 502.8661 | 43.1545 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
27 | AFL VARIOUS SUB |  |  | San Diego, San Diego | Automated Fault Location (TEAM) deployments at multiple substations. | Substation - Other Equipment | Upgrade/Retrofit | NA | NA | Reliability | Relay Upgrades | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69 ¦ 138 | 373MVA | 4.3 | NA | QBL0063 | 1 | 12129 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-04-15 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | NA | 2019-12-31 | 2021-01-30 | Prioritization | NA | FALSE | 161.18 | NA ¦ NA | 1034.7721 | 128.1801 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 | 1034.7721 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
28 | [Programmatic] Substation SCADA Expansion |  |  | Multiple | The project provides funding for the installation, upgrades, and expansion of the Supervisory Control and Data Acquisition (SCADA) system at transmission substations. Additionally, this project improves the protection of SDG&E’s transmission system to provide fast isolation for faults and system disturbances. Includes upgrading relays including increased security, differential protection, and traveling wave fault finding technology to reduce restoration times. | Substation - Multiple | Upgrade/Retrofit | NA | NA | Reliability | Install SCADA/RTU | NERC PRC Compliance | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69 | 373MVA | 4.3 | Multiple | QBL0064 | 27 | 12132 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-12-09 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | NA | 2024-12-31 | Multiple | NA | NA | TRUE | NA | NA ¦ NA | 71573.8281 | 1087.1578 | 785.8235 | 517.4789 | 1412.4694 | 2148.9241 | 594.0566 | 2557.9842 | 4017.0102 | 4483.156 | 4994.7354 | 5556.0129 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 ¦ 2026 | 2000.6913 | 385.5493 | 1098.9512 | 1.3718 | 2070.7546 | 1398.2787 | 0% | NA ¦ NA | 4.42 | NA | 0% | 100% | [CPUC Status] Exempt
29 | T SCADA: TRABUCO RTU |  |  | Laguna Niguel, Orange | Trabuco substation Transmission RTU upgrades | Substation - Protection Relay | Upgrade/Retrofit | NA | NA | Reliability | Relay Upgrades | NA | NA | 2025-10-17 | 4.7 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 1.92 | 69 | 373MVA | 4.3 | 2023-3393 | QBL0064 | 1 | 12132 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2022-09-01 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Engineering more than 50% complete | NA | 2025-07-28 | 2023-12-30 | 2026-01-07 | Prioritization | NA | TRUE | 363.9492 | NA ¦ NA | 1396.1184 | 0 | 15.1845 | 245.1148 | 597.3973 | 106.0799 | 179.9731 | 252.3689 | 0 | 0 | 0 | 0 | 963.7765 | NA | NA | 2026 | 0 | 0 | 0 | 0 | 0 | 1396.1184 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
30 | RANCHO CARMEL T SCADA |  |  | San Diego, San Diego | Rancho Carmel substation Transmission SCADA upgrades. | Substation - Protection Relay | Upgrade/Retrofit | NA | NA | Reliability | Relay Upgrades | NA | NA | 2025-10-20 | 6.52 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 1.35 | 69 | 373MVA | 4.3 | 2023-3392 | QBL0064 | 1 | 12132 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2021-09-15 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | On Hold | NA | 2025-04-30 | 2023-12-31 | 2026-06-10 | Prioritization | NA | TRUE | 298.1449 | NA ¦ NA | 1707.6486 | 0.58867 | 4.3537 | 179.4357 | 700.8313 | 66.6276 | 221.2 | 534.6116 | 0 | 0 | 0 | 0 | 951.837 | NA | NA | 2026 | 0 | 0 | 0 | 0 | 0 | 1707.6486 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
31 | TRANSMISSION SCADA TL23014_015 |  |  | Escondido, San Diego | Replace (2) GE L-90 relays with latest SDG&E standard, (2) SEL-411L at ES (TL23014/15) | Substation - Protection Relay | Upgrade/Retrofit | NA | NA | Reliability | Relay Upgrades | NA | NA | 2025-02-20 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 4.66 | 230 | 373MVA | 4.3 | 2021-2013 | QBL0064 | 1 | 12132 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-10-30 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | NA | 2023-12-31 | 2024-11-08 | Construction Delays | NA | FALSE | 951.309 | NA ¦ NA | 1001.7985 | 201.2061 | 265.8805 | 522.1258 | 12.5862 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2023 ¦ 2024 | 0 | 0 | 989.2124 | 12.5862 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0% | [CPUC Status] Exempt
32 | IV 230KV RTU REPLACEMENT |  |  | Imperial County | Install two new RTU panels, remove two SEL PDC's, Remove the RS416, Install 7 SEL 3610's. | Substation - Multiple | New | New | NA | CAISO Transmission Planning Standards [See Notes for NERC Compliance and contingency code, WECC Requirement (and the specific requirement)] | 3rd Party Damage | NERC CIP Compliance | NERC CIP Compliance | 2025-11-18 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 55.48 | Multiple | 230kV | 4.3 | 2025-4183 | QBL0064 | 1 | 12132 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-07-19 | Work Order Authorization | 2025 | NA | FALSE | NA | NA | NA | FALSE | Expected PEA Completion | NA | IS/ND | EIS | NA | NA | Exempt | NA | To be Filed | NA | Planning | NA | 2026-07-31 | 2025-12-31 | 2027-03-31 | Project Design | Prioritization | FALSE | 342.0158 | NA ¦ NA | 1134.0345 | 0 | 0 | 0 | 1.6358 | 141.6799 | 523.8727 | 445.836 | 21.0102 | 0 | 0 | 0 | 143.3157 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 13.55% | 86.45%
33 | [Programmatic] Aerial Marking for Safety |  |  | Multiple | This project will add aerial marker balls and /or lighting at locations identified by Transmission Engineering, Transmission maintenance personnel, or AL&M support team as safety concerns or necessary for FAA compliance. These locations fall under SDG&E’s expanded aerial lighting and marking policy that seeks to reduce the risk of collisions and improve safety. This will be an ongoing project as Transmission Construction & Maintenance may provide additional locations with safety concerns and for the Aerial Lighting and Marking company initiative. The work includes analyzing current structures for strength and clearance to add marking, replacing structures as necessary, and installing aerial marking and/or lighting. | Transmission Line - Multiple | NA | NA | NA | Safety | T-Line Reliability | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | Multiple | NA | 1.1 | Multiple | QBL0065 | 78 | 12159 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2022-12-09 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | NA | NA | To be Filed | NA | Operational | NA | NA | 2023-12-31 | Multiple | NA | NA | FALSE | NA | NA ¦ NA | 25188.1524 | 337.9964 | 69.5109 | 9.3215 | 0.00105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 | 1408.1155 | 75.2202 | 9.3215 | 0.00105 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 13.55% | 86.45%
34 | AL&M system wide assessment |  |  | San Diego, San Diego | Aerial Lighting and Marking Project to meet FAA Regulations | Transmission Line - Pole/Tower | New | NA | NA | Safety | T-Line Reliability | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | NA | NA | 1.1 | ALM-SW | QBL0065 | 1 | 12159 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2018-07-30; 2018-05-29; 2012-12-12 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | NA | NA | NA [See Notes] | NA | Operational | NA | NA | 2019-12-31 | Multiple | NA | NA | FALSE | 846.516 | NA ¦ NA | 4356.8678 | 361.1757 | 50.3264 | 4.0735 | 0.00168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 | 4302.4662 | 50.3264 | 4.0735 | 0.00168 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0%
35 | [Programmatic] CAST Security Upgrades |  |  | Multiple | CAST is an ongoing program that addresses security for critical substation assets. | Substation - Other Equipment | New | NA | NA | Physical Security | Security Upgrades | NERC CIP Compliance | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | Multiple | Multiple | 1.1 | Multiple | QBL0020 | 35 | 15125 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-12-09 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | Expected PEA Completion | NA | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | Multiple | Multiple | Multiple | NA | NA | FALSE | 216954.9592 | NA ¦ NA | 0 | 333.5327 | 312.9607 | -1002.0375 | 54.0073 | 15298.0518 | 0.49102 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 94.0047 | 39.8652 | -489.414 | 54.0073 | 0.49102 | 0 | 0% | NA ¦ NA | 1.6 | NA | 100% | 0% | [CPUC Status] Exempt
36 | CAST PENASQUITOS (PQ) |  |  | San Diego, San Diego | Physical security hardening | Other - Physical Security | New | NA | NA | Physical Security | Security Upgrades | NERC CIP Compliance | NA | 2025-11-16 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 13.94 | 230 ¦ 500 | 230kV ¦500kV | 1.1 | 2023-3286 | QBL0020 | 1 | 15125 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2022-07-27 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | Expected PEA Completion | NA | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2023-05-30 | 2024-12-31 | 2024-08-14 | NA | NA | FALSE | 369.2342 | NA ¦ NA | 18994.008 | 0 | 1667.5722 | 9071.5199 | 8242.4071 | 12.5087 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2024 ¦ 2025 | 0 | 0 | 0 | 18981.4993 | 12.5087 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0%
37 | CAST EAST CO SUB PERIMETER |  |  | San Diego, San Diego | Physical security hardening | Other - Physical Security | New | NA | NA | Physical Security | Security Upgrades | NERC CIP Compliance | NA | 2025-11-16 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 66.56 | 230 ¦ 500 | 230kV ¦500kV | 1.1 | 2021-2561 | QBL0020 | 1 | 15125 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-12-28 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | Expected PEA Completion | NA | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2021-08-20 | 2021-12-31 | 2022-11-22 | Multiple Options[See Notes] | NA | FALSE | 409.5425 | NA ¦ NA | 31558.0535 | 13896.3193 | 17555.2216 | 80.7694 | 25.7432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2022 ¦ 2023 ¦ 2024 | 0 | 31451.5408 | 80.7694 | 25.7432 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0% | [Reason for Change in In-Service Date] Prioritization, Construction Delays, Scope Change [CPUC Status] Exempt
38 | CAST SYCAMORE CANYON |  |  | San Diego, San Diego | Physical security hardening | Other - Physical Security | New | NA | NA | Physical Security | Security Upgrades | NERC CIP Compliance | NA | 2025-10-14 | NA | NA | NA | NA | Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 10.79 | 230 ¦ 500 | 230kV ¦500kV | 1.1 | 2023-3284 | QBL0020 | 1 | 15125 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2022-09-22 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | Expected PEA Completion | NA | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2023-09-15 | 2024-01-31 | 2024-07-01 | Permitting | NA | FALSE | 4261.2035 | NA ¦ NA | 14087.1131 | 0 | 864.9117 | 6654.1274 | 6562.1073 | 5.9667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2024 ¦ 2025 | 0 | 0 | 0 | 14081.1465 | 5.9667 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0% | [CPUC Status] Exempt
39 | CAST MISSION FRONT ENTRANCE |  |  | San Diego, San Diego | Physical security hardening | Other - Physical Security | New | NA | NA | Physical Security | Security Upgrades | NERC CIP Compliance | NA | 2025-11-12 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 9 | 230 ¦ 500 | 230kV ¦500kV | 1.1 | 2022-2976 | QBL0020 | 1 | 15125 | NA ¦ NA ¦ NA ¦ NA | TRUE | 12/28/2020;12/23/2024 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | Expected PEA Completion | NA | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2022-08-22 | 2025-12-31 | 2025-06-11 | NA | NA | FALSE | 5847.1004 | NA ¦ NA | 25730.4917 | 772.6935 | 2301.7353 | 7337.3744 | 12821.5414 | 2369.4941 | 127.6531 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2024 ¦ 2025 | 0 | 0 | 0 | 23233.3446 | 2497.1472 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0% | [CPUC Status] Exempt
40 | CAST GUARD SHELTER REBUILD |  |  | Multiple | Physical security hardening | Other - Physical Security | New | NA | NA | Physical Security | Security Upgrades | NERC CIP Compliance | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 230 ¦ 500 | 230kV ¦500kV | 1.1 | 2023-3287 | QBL0020 | 1 | 15125 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2022-08-16 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | NA | 2023-12-31 | 2023-12-31 | NA | NA | FALSE | 8105.7854 | NA ¦ NA | 6635.5741 | 0 | -5.4329 | 5728.1337 | 950.2604 | -37.3871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2023 ¦ 2024 ¦ 2025 | 0 | 0 | 5722.7008 | 950.2604 | -37.3871 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0% | [CPUC Status] Exempt
41 | CAST IMPERIAL VLLY SUBS PERIMET |  |  | Imperial County | Physical security hardening | Other - Physical Security | New | NA | NA | Physical Security | Security Upgrades | NERC CIP Compliance | NA | 2025-11-18 | NA | NA | NA | NA | Tier 3 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 55.48 | 230 ¦ 500 | 230kV ¦500kV | 1.1 | 2021-2097 | QBL0020 | 1 | 15125 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-08-28 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | Expected PEA Completion | NA | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2020-11-30 | 2021-12-31 | 2022-01-18 | Construction Delays | NA | FALSE | 19307.087 | NA ¦ NA | 20699.2221 | 15252.6844 | 26.6981 | 5.724 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 | 20666.7999 | 26.6981 | 5.724 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0% | [CPUC Status] Exempt
42 | CAST OCOTILLO |  |  | Imperial County | Physical security hardening | Other - Physical Security | New | NA | NA | Physical Security | Security Upgrades | NERC CIP Compliance | NA | 2025-11-17 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 28.98 | 230 ¦ 500 | 230kV ¦500kV | 1.1 | 2022-2977 | QBL0020 | 1 | 15125 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2022-02-08 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | Expected PEA Completion | NA | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2023-10-09 | 2023-12-31 | 2024-12-30 | Multiple Options[See Notes] | NA | FALSE | 362.4209 | NA ¦ NA | 13809.5982 | 0 | 70.8717 | 5204.6986 | 8215.3314 | 318.6965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2024 ¦ 2025 | 0 | 0 | 0 | 13490.9017 | 318.6965 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0% | [Reason for Change in In-Service Date] Prioritization, Construction Delays, Scope Change [CPUC Status] Exempt
43 | CAST SUNCREST SUB PERIMETER |  |  | San Diego, San Diego | Physical security hardening | Other - Physical Security | New | NA | NA | Physical Security | Security Upgrades | NERC CIP Compliance | NA | 2025-11-03 | NA | NA | NA | NA | Tier 3 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 40.94 | 230 ¦ 500 | 230kV ¦500kV | 1.1 | 2022-2929 | QBL0020 | 1 | 15125 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-12-20 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | Expected PEA Completion | NA | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2022-05-31 | 2020-12-31 | 2023-09-18 | Multiple Options[See Notes] | NA | FALSE | 371.3412 | NA ¦ NA | 29602.4834 | 5938.8692 | 11745.8702 | 7885.8844 | 3985.379 | 46.4806 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2023 ¦ 2024 ¦ 2025 | 0 | 0 | 25570.6238 | 3985.379 | 46.4806 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0% | [Reason for Change in In-Service Date] Prioritization, Construction Delays, Scope Change [CPUC Status] Exempt
44 | CAST SECURITY VARIOUS SUBS |  |  | Multiple | Physical security hardening | Other - Physical Security | New | NA | NA | Physical Security | Security Upgrades | NERC CIP Compliance | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 230 ¦ 500 | 230kV ¦500kV | 1.1 | NA | QBL0020 | 1 | 15125 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2018-04-25 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | Expected PEA Completion | NA | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Canceled | NA | NA | 2019-12-31 | 2021-11-30 | Scope Change | NA | FALSE | 712.577 | NA ¦ NA | 3274.9228 | 634.3393 | 53.9794 | 0.08947 | 0.40581 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 | 3220.4482 | 53.9794 | 0.08947 | 0.40581 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0% | [CPUC Status] Exempt
45 | CAST TALEGA |  |  | San Clemente, San Diego | Physical security hardening | Other - Physical Security | New | NA | NA | Physical Security | Security Upgrades | NERC CIP Compliance | NA | 2025-10-21 | NA | NA | NA | NA | Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 6.2 | 230 ¦ 500 | 230kV ¦500kV | 1.1 | 2024-3902 | QBL0020 | 1 | 15125 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-08-24 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Construction (25%-50%) | NA | 2025-02-10 | 2025-03-31 | 2025-11-03 | Scope Change | NA | TRUE | 17520.0262 | NA ¦ NA | 15363.7475 | 0 | 0 | 0.21244 | 3086.2953 | 4653.3051 | 7596.0861 | 27.8486 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2025 ¦ 2026 | 0 | 0 | 0 | 0 | 15335.8989 | 27.8486 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0% | [CPUC Status] Exempt
46 | CAST OTAY MESA |  |  | Otay Mesa, San Diego | Physical security hardening | Other - Physical Security | New | NA | NA | Physical Security | Security Upgrades | NERC CIP Compliance | NA | 2025-11-18 | NA | NA | NA | NA | Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 4 | 230 ¦ 500 | 230kV ¦500kV | 1.1 | 2024-3903 | QBL0020 | 1 | 15125 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2022-02-08 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2024-07-30 | 2023-12-31 | 2024-12-24 | Prioritization | NA | FALSE | 362.4209 | NA ¦ NA | 2594.4452 | 0 | 0 | 0.0713 | 2557.2477 | 37.1262 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2024 ¦ 2025 | 0 | 0 | 0 | 2557.319 | 37.1262 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0% | [CPUC Status] Exempt
47 | CAST SAN LUIS REY |  |  | Oceanside, San Diego | Physical security hardening | Other - Physical Security | New | NA | NA | Physical Security | Security Upgrades | NERC CIP Compliance | NA | 2025-10-30 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 7.4 | 230 ¦ 500 | 230kV ¦500kV | 1.1 | 2024-3904 | QBL0020 | 1 | 15125 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-03-18 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Construction (under 10%) | NA | 2025-07-01 | 2026-01-31 | 2026-06-30 | Project Design | NA | TRUE | 26711.4404 | NA ¦ NA | 11308.4675 | 0 | 0 | 0 | 62.5448 | 372.2203 | 7573.8216 | 3299.8808 | 0 | 0 | 0 | 0 | 434.7651 | NA | NA | 2026 | 0 | 0 | 0 | 0 | 0 | 11308.4675 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0% | [CPUC Status] Exempt
48 | [Programmatic] Advanced Protection |  |  | Multiple | Replaces aging circuit breakers and/or obsolete electromechanical relays, to create a more comprehensive protection system by taking advantage of newer field technologies under installation by the FiRM program, and to create visibility in fire threat areas with installation of Distribution SCADA. Adding distribution SCADA and replacing obsolete distribution relays and aging equipment. Improve distribution reliability and improve fire safety. | Substation - Multiple | Upgrade/Retrofit | NA | NA | Wildfire Mitigation | SCADA Switch Installation | NERC CIP Compliance | NA | NA | NA | NA | NA | NA | Tier 2 ¦ Tier 3 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | NA | NA | Multiple | 120MVA | 1.2 | Multiple | QBL0071 | 52 | 15259 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-12-11 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | NA | 2024-12-31 | Multiple | NA | NA | TRUE | NA | NA ¦ NA | 7361.2815 | 754.289 | 1596.8845 | 1010.3759 | 1390.2288 | 583.4637 | 64.1118 | 204.1303 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 ¦ 2026 | 545.0247 | 849.8923 | 1305.7861 | 1118.1088 | 2743.5042 | 204.1303 | 0% | NA ¦ NA | 5.4 | NA | 0% | 100% | [CPUC Status] Exempt
49 | APP WMP: BORDER SUBSTATION |  |  | San Diego, San Diego | Replace existing oil circuit breakers with vacuum, upgrade RTU and associated relay equipment. | Substation - Multiple | Upgrade/Retrofit | NA | NA | Wildfire Mitigation | Install SCADA/RTU | NA | NA | 2025-11-17 | NA | NA | NA | NA | Tier 2 ¦ Tier 3 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | NA | 0.94 | 69 | 373MVA | 1.2 | 2021-2054 | QBL0071 | 1 | 15259 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2021-02-18 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2022-05-18 | 2022-12-31 | 2024-04-23 | Construction Delays | NA | FALSE | 1682.9944 | NA ¦ NA | 1309.951 | 98.5274 | 618.9882 | 539.5663 | 48.1926 | 4.6765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2024 ¦ 2025 | 0 | 0 | 0 | 1305.2745 | 4.6764 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
50 | APP WMP: PALA SUBSTATION |  |  | San Diego County | Replace existing relays and RTU, other supporting equipment. | Substation - Multiple | Upgrade/Retrofit | NA | NA | Wildfire Mitigation | Install SCADA/RTU | NA | NA | 2025-11-19 | NA | NA | NA | NA | Tier 3 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | NA | 0.84 | 69 | 373MVA | 1.2 | 2021-2316 | QBL0071 | 1 | 15259 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2021-02-16 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Construction (50%-75%) | NA | 2023-05-08 | 2022-12-31 | 2025-06-17 | Workforce | NA | FALSE | 437.8891 | NA ¦ NA | 1313.7626 | 0 | 3.8588 | 762.793 | 497.1065 | 50.0042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2024 ¦ 2025 | 0 | 0 | 0 | 1263.7584 | 50.0042 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
51 | CAMERON ADD 69KV BUS TIE |  |  | San Diego County | Add 69kV bus tie circuit breaker, conductor and associated equipment. | Substation - Circuit Breaker | Upgrade/Retrofit | NA | NA | Wildfire Mitigation | Bus Upgrade | NA | NA | 2025-11-12 | NA | NA | NA | NA | Tier 3 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | NA | NA | 69 | 373MVA | 1.2 | 2014-01075-ZZ | QBL0071 | 1 | 15259 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2018-03-14 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2020-12-07 | 2019-03-01 | 2021-11-01 | Input Error | NA | FALSE | 2429 | NA ¦ NA | 3433.348 | 2084.9862 | 10.2088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 | 3423.1392 | 10.2088 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
52 | SANTA YSABEL 69KV REBUILD |  |  | San Diego County | Replace existing 69kV bus, circuit breaker, and control shelter. | Substation - Multiple | Upgrade/Retrofit | NA | NA | Wildfire Mitigation | Bus Upgrade | NA | NA | 2025-10-16 | 54 | NA | NA | NA | Tier 3 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | NA | NA | 69 | 373MVA | 1.2 | 2019-0222 | QBL0071 | 1 | 15259 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-05-17; 2018-03-14 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2020-08-31 | 2019-06-01 | 2023-03-23 | Input Error | NA | FALSE | 9392.736 | NA ¦ NA | 10304.2741 | 3052.3057 | 1859.5361 | 840.3981 | 16.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2023 ¦ 2024 | 0 | 0 | 10287.7442 | 16.53 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
53 | WMP APP DESCANSO BK30 & YARD |  |  | San Diego County | Replace bank xfmr, extend yard for access. | Substation - Multiple | Upgrade/Retrofit | NA | NA | Wildfire Mitigation | Replace Transformer | NA | NA | 2025-11-13 | 44 | NA | NA | NA | Tier 3 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | NA | 0.34 | 69 | 373MVA | 1.2 | 2021-2202 | QBL0071 | 1 | 15259 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-12-18 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2022-08-01 | 2021-10-30 | 2023-11-18 | Input Error | NA | FALSE | 3469.791 | NA ¦ NA | 4365.3564 | 159.9943 | 2247.369 | 1727.4986 | 227.0474 | 0.21071 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2023 ¦ 2024 ¦ 2025 | 0 | 0 | 4138.0982 | 227.0474 | 0.21071 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
54 | DESCANSO UPGRADE TL626 RELAYING |  |  | San Diego County | Replace 69/12kV circuit breakers in support of FCP. | Substation - Multiple | Upgrade/Retrofit | NA | NA | Wildfire Mitigation | Relay Upgrades | NA | NA | 2025-11-13 | 3.2 | NA | NA | NA | Tier 3 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | NA | 0.34 | 69 | 373MVA | 1.2 | 2014-00432-ZZ-SUB | QBL0071 | 1 | 15259 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2016-08-31 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2016-11-07 | 2017-12-01 | 2021-06-30 | Input Error | NA | FALSE | 4278 | NA ¦ NA | 5055.0616 | 807.0655 | 45.0175 | -0.48344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2022 ¦ 2023 | 0 | 5055.5451 | -0.48344 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
55 | WARNERS UPGRADE TRANS RELAYING |  |  | San Diego County | Replace 69/12kV circuit breakers in support of FCP. | Substation - Multiple | Upgrade/Retrofit | NA | NA | Wildfire Mitigation | Relay Upgrades | NA | NA | 2025-10-15 | 3.2 | NA | NA | NA | Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | NA | 1.08 | 69 | 373MVA | 1.2 | 2014-00278-ZZ-CIR | QBL0071 | 1 | 15259 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2016-08-31 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2016-11-08 | 2017-12-01 | 2021-12-17 | Input Error | NA | FALSE | 5090 | NA ¦ NA | 5802.8858 | 905.0979 | 770.9282 | 77.9159 | 0.04789 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2023 ¦ 2024 | -0.86438 | 0 | 5803.7023 | 0.04789 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
56 | APPWMP: POMERADO SUBSTATION |  |  | Poway, San Diego County | RTU and Relay Replacement | Substation - Multiple | Upgrade/Retrofit | NA | NA | Wildfire Mitigation | Relay Upgrades | NA | NA | 2025-11-04 | 19; 33; 27 | NA | NA | NA | Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | NA | 1.37 | 69 | 373MVA | 1.2 | 2021-2178 | QBL0071 | 1 | 15259 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2021-02-16 | Work Order Authorization | 2022 | NA | FALSE | NA | NA | NA | FALSE | TBD | TBD | NA | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2023-12-11 | 2022-07-31 | 2024-08-02 | Input Error | NA | FALSE | 508.0072 | NA ¦ NA | 1053.6016 | 37.0979 | 58.7327 | 546.5654 | 404.8551 | 6.3505 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2024 ¦ 2025 | 0 | 0 | 0 | 1047.2511 | 6.3505 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
57 | STUART SUBSTATION APP/DCRU |  |  | San Diego County | Breaker and RTU Replacement | Substation - Multiple | Upgrade/Retrofit | NA | NA | Wildfire Mitigation | Relay Upgrades | NA | NA | 2025-10-09 | 63; 12 | NA | NA | NA | Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | NA | 0.12 | 69 | 373MVA | 1.2 | 2021-2177 | QBL0071 | 1 | 15259 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2018-01-30 | Work Order Authorization | 2021 | NA | FALSE | NA | NA | NA | FALSE | TBD | TBD | NA | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2022-10-25 | 2022-07-31 | 2024-10-25 | Construction Delays | NA | FALSE | 112.179 | NA ¦ NA | 1097.71 | 87.1562 | 336.3774 | 203.7923 | 152.9362 | -3.3299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 407.934 | 336.3774 | 203.7923 | 152.9362 | -3.3299 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
58 | [Programmatic] Substation Security Installations (16126) |  |  | Multiple | This budget is required to maintain the reliability and integrity of the security of electric substations. The specific work required to meet safety requirements, replace obsolete or failed equipment, and make necessary small capital additions is based on requests from Engineering, Planning, Operations, and Maintenance groups. | Other - Physical Security | Upgrade/Retrofit | NA | NA | Reliability | Security Upgrades | NERC CIP Compliance | NA | NA | NA | NA | Wires - New Substation Alternative | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | Multiple | NA | 4.3 | Multiple | QBL0002 | 41 | 16126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2025-04-28 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | NA | NA | NA | NA | Planning | NA | NA | 2024-12-31 | Multiple | NA | NA | TRUE | NA | NA ¦ NA | 73788.1867 | 2024.6019 | 1675.1554 | 3274.9969 | 646.8744 | 6166.7646 | 4979.2916 | 1064.5594 | 3862.589 | 4243.6438 | 4722.7582 | 5211.5331 | 5488.6089 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 ¦ 2026 | 269.1069 | 4148.4855 | 1940.1926 | 1300.6347 | 641.3647 | 6427.8337 | 0% | NA ¦ NA | 8.53 | NA | 13.55% | 86.45% | [CPUC Status] NA
59 | NON CAST SECURITY VARIOUS SUBS |  |  | San Diego, San Diego | Security Upgrade and Fence project | Other - Physical Security | Upgrade/Retrofit | NA | NA | Physical Security | Security Upgrades | NA | NA | 2025-10-09 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | NA | NA | 4.3 | NA | QBL0002 | 1 | 16126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2021-01-29 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | To be Filed | NA | Operational | NA | NA | 2021-12-31 | 2023-07-30 | Other : Multiple projects tied to this work order | NA | FALSE | 2214.5143 | NA ¦ NA | 9124.9231 | 5152.3225 | 3045.8478 | 938.3538 | -11.6009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2023 ¦ 2024 | 0 | 0 | 9136.5241 | -11.6009 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0%
60 | ELLIOT SUB FENCE GATE BROW DITC |  |  | San Diego, San Diego | Elliot Sub fence, gate, and brow ditch rebuild. | Substation - Structure | Upgrade/Retrofit | Replace | NA | Physical Security | Security Upgrades | NA | NA | 2025-11-04 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 0.8 | 69 | NA | 4.3 | 2022-2767 | QBL0002 | 1 | 16126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2021-12-03 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | To be Filed | NA | Operational | NA | 2022-12-13 | 2022-12-31 | 2023-04-17 | Project design | NA | FALSE | 2536.5572 | NA ¦ NA | 1812.181 | 11.2673 | 674.8257 | 1126.088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2023 | 0 | 0 | 1812.181 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
61 | STATION F NON CAST SECURITY |  |  | San Diego, San Diego | Install new security system. | Other - Physical Security | Upgrade/Retrofit | New | NA | Physical Security | Security Upgrades | NA | NA | 2025-11-13 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 0.7 | 69 ¦ 12 | 69kV | 4.3 | 2021-2001 | QBL0002 | 1 | 16126 | 2025-12-10 ¦ 2023-3526 ¦ NA ¦ NA | TRUE | 2021-12-07 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | To be Filed | NA | Operational | NA | 2023-03-23 | 2023-06-30 | 2025-04-07 | Material | NA | FALSE | 971.7073 | NA ¦ NA | 1351.7176 | 0 | 65.1837 | 1254.2796 | 32.2543 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2024 | 0 | 0 | 0 | 1351.7176 | 0 | 0 | 1% | 100% ¦ 1454 | NA ¦ NA | NA | 0% | 100%
62 | PACIFIC BEACH NON CAST SECURITY |  |  | San Diego, San Diego | Fence Perimeter: Repair/Replace Fence or fencing material as required. ­Yard: Install low voltage and power conduit for security as required per plan New Pull Boxes, SP­Pads and 2” & 4” conduits will be required for security design. Note: Where possible existing trough, pull boxes, and existing conduit may be utilized for this effort ­Electrical Provide and install new electrical panel where applicable or identify existing panel and position. | Other - Physical Security | Replace | Replace | NA | Physical Security | Security Upgrades | NA | NA | 2025-11-03 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 0.35 | NA | NA | 4.3 | 2021-2004 | QBL0002 | 1 | 16126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2021-04-09 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | To be Filed | NA | Operational | NA | 2021-10-27 | 2022-05-31 | 2022-12-08 | Weather | NA | FALSE | 878.4705 | NA ¦ NA | 1441.9029 | 128.8945 | 1254.4041 | 50.133 | 8.4714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2023 ¦ 2024 | 0 | 0 | 1433.4316 | 8.4714 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [Reason for Change in In-Service Date] In-service dates are estimated during preliminary design and permitting stages of a project; date shifted to reflect actual design and construction schedule.
63 | SAN MARCOS NON CAST |  |  | San Marcos, San Diego | Fence Perimeter repair/replace fencing materials as needed; install low voltage and power conduit from security as required per plan, new pull boxes, SP Pads, where possible use existing pull boxes, conduit and trough | Other - Physical Security | Replace | Upgrade/Retrofit | NA | Physical Security | Security Upgrades | NA | NA | 2025-10-29 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 1.59 | 69 | 69 kV | 4.3 | 2021-2381 | QBL0002 | 1 | 16126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2021-07-22; 2021-05-20 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | To be Filed | NA | Operational | NA | 2021-10-25 | 2022-12-31 | 2024-03-06 | Material | NA | FALSE | 2189.4406 | NA ¦ NA | 1564.0222 | 73.2847 | 293.3693 | 970.6194 | 226.7488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2024 | 0 | 0 | 0 | 1564.0222 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
64 | VALLEY CENTER NON CAST SECURITY |  |  | Valley Center, San Diego | New Security System Installation | Other - Physical Security | New | New | NA | Physical Security | Security Upgrades | NA | NA | 2025-10-13 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 1.23 | 69 ¦ 12 | 69/12kV | 4.3 | 2023-3526 | QBL0002 | 1 | 16126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-08-02 | Work Order Authorization | 2023 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | CPUC | NA | Exempt | NA | To be Filed | NA | Operational | NA | 2023-10-03 | 2025-03-27 | 2025-03-28 | Material | NA | FALSE | 911.4247 | NA ¦ NA | 1429.8629 | 0 | 0 | 29.0159 | 908.4324 | 492.4147 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2025 | 0 | 0 | 0 | 0 | 1429.8629 | 0 | 100% | 100% ¦ $1,425,000 | NA ¦ NA | NA | 0% | 100%
65 | CHOLLAS WEST NON CAST SECURITY |  |  | Lemon Grove, San Diego | Security Systems Installation | Substation - Multiple | Upgrade/Retrofit | New | NA | Physical Security | Security Upgrades | NA | NA | 2025-11-19 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 1.455 | 69 ¦ 12 | 69kV | 4.3 | 2023-3525 | QBL0002 | 1 | 16126 | 2025-12-10 ¦ NA ¦ NA ¦ NA | TRUE | 2023-08-01 | Work Order Authorization | 2023 | NA | FALSE | NA | NA | NA | FALSE | PEA Deemed Complete | NA | Exempted | NA | CPUC | NA | Exempt | NA | To be Filed | NA | Operational | NA | 2024-05-03 | 2024-12-13 | 2025-12-13 | Material | NA | FALSE | 1335.6712 | NA ¦ NA | 1425.9032 | 0 | 0 | 15.0361 | 1323.281 | 87.5861 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2025 | 0 | 0 | 0 | 0 | 1425.9032 | 0 | 100% | 100% ¦ $1,406,000 | NA ¦ NA | NA | 0% | 100%
66 | ENCINA SEURITY/FENCING |  |  | Encinitas, San Diego | New Fencing/Life Cycle Upgrade | Other - Physical Security | Upgrade/Retrofit | Upgrade/Retrofit | NA | Physical Security | Security Upgrades | NA | NA | 2025-11-04 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 4.86 | Multiple | 230kV | 4.3 | 2024-3884 | QBL0002 | 1 | 16126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-02-06 | Work Order Authorization | 2024 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | CPUC | NA | Exempt | NA | To be Filed | NA | Operational | NA | 2024-04-22 | 2024-10-10 | 2024-10-10 | NA | NA | FALSE | 2707.4516 | NA ¦ NA | 1301.7233 | 0 | 0 | 0 | 1252.741 | 48.9823 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2024 ¦ 2025 | 0 | 0 | 0 | 1252.741 | 48.9823 | 0 | 100% | 100% ¦ $1,467,000 | NA ¦ NA | NA | 13.55% | 86.45%
67 | ROSE CANYON NON CAST SECURITY |  |  | San Diego, San Diego | Non-Cast Security System Life Cycle Upgrade | Other - Physical Security | Upgrade/Retrofit | Upgrade/Retrofit | NA | Physical Security | Security Upgrades | NA | NA | 2025-11-03 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 1.32 | 69 ¦ 12 | 69kV | 4.3 | 2023-3520 | QBL0002 | 1 | 16126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-08-02 | Work Order Authorization | 2023 | NA | FALSE | NA | NA | NA | FALSE | PEA Deemed Complete | NA | Exempted | NA | CPUC | NA | Exempt | NA | To be Filed | NA | Operational | NA | 2023-10-03 | 2024-11-27 | 2024-11-27 | NA | NA | FALSE | 1083.7527 | NA ¦ NA | 1523.8436 | 0 | 0 | 32.731 | 1431.8276 | 59.285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2025 | 0 | 0 | 0 | 0 | 1523.8436 | 0 | 100% | 100% ¦ $1,513,000 | NA ¦ NA | NA | 0% | 100%
68 | TORREY PINES NON CAST |  |  | San Diego, San Diego | Non Cast New Security System | Other - Physical Security | New | New | NA | Physical Security | Security Upgrades | NA | NA | 2025-11-07 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | .811 | 69 ¦ 12 | 69kV | 4.3 | 2021-2380 | QBL0002 | 1 | 16126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2021-07-21 | Work Order Authorization | 2021 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | CPUC | NA | Exempt | NA | To be Filed | NA | Construction (25%-50%) | NA | 2020-03-11 | NA | 2027-03-10 | NA | NA | FALSE | 839.3466 | NA ¦ NA | 1070.1571 | 74.345 | 242.5152 | 110.0629 | 556.1138 | 87.1201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2024 ¦ 2025 | 0 | 0 | 0 | 983.037 | 87.1201 | 0 | 100% | 100% ¦ $1,534,000 | NA ¦ NA | NA | 0% | 100%
69 | CRESTWOOD NON CAST SECURITY |  |  | San Diego, San Diego | NON-CAST New Security System | Other - Physical Security | New | New | NA | Physical Security | Security Upgrades | NA | NA | 2025-11-13 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | .687 | 69 ¦ 12 | 69kV | 4.3 | 2023-3524 | QBL0002 | 1 | 16126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-08-01 | Work Order Authorization | 2023 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | CPUC | NA | Exempt | NA | To be Filed | NA | Construction (over 75%) | NA | 2023-10-19 | 2025-06-23 | 2025-06-20 | NA | NA | TRUE | 900.9477 | NA ¦ NA | 1497.1763 | 0 | 0 | 46.1263 | 1039.2304 | 310.1946 | 62.7943 | 38.8307 | 0 | 0 | 0 | 0 | 1395.5513 | NA | NA | 2026 | 0 | 0 | 0 | 0 | 0 | 1497.1763 | 100% | 100% ¦ $1,474,000 | NA ¦ NA | NA | 0% | 100%
70 | [Programmatic] Substation DC Reliability Upgrades |  |  | Multiple | This project installs new assets in existing substation control shelters to support increased power requirements driven by aging infrastructure replacements of telecommunication hardware. Scope includes installation of new communication racks, upgrades to 125V DC systems for power, adding HVAC in transmission substation control shelters to support equipment environmental control requirements, DC-DC power converters, as well as batteries and Station Light & Power (SL&P) upgrades. | Substation - Multiple | Upgrade/Retrofit | NA | NA | Reliability | Replace Other Substation Equipment | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | Multiple | 373MVA | 4.3 | Multiple | QBL0094 | 159 | 16138 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2025-01-27 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | NA | 2024-12-31 | Multiple | NA | NA | TRUE | NA | NA ¦ NA | 52533.2819 | 3436.2843 | 2517.7948 | 3489.8236 | 5322.7614 | 5880.9765 | 2378.8706 | 4630.2144 | 4602.4316 | 3068.1439 | 0 | 0 | 539.1981 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 ¦ 2026 | 2308.1485 | 3728.1573 | 1791.8945 | 4486.9083 | 7793.3341 | 1441.9901 | 0% | NA ¦ NA | 3.65 | NA | 13.55% | 86.45% | [CPUC Status] Exempt
71 | DCRU: VARIOUS SUBS 2022 |  |  | San Diego, San Diego | DC Reliability Upgrades at multiple substations | Substation - Other Equipment | Upgrade/Retrofit | NA | NA | Reliability | Replace Other Substation Equipment | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | Multiple | 373MVA | 4.3 | Multiple | QBL0094 | 1 | 16138 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2021-12-01 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | NA | 2022-12-31 | 2023-09-30 | Prioritization | NA | FALSE | 1428.1784 | NA ¦ NA | 2032.4925 | 25.7325 | 1520.8642 | 473.1137 | 12.782 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2023 ¦ 2024 | 0 | 0 | 2019.7105 | 12.782 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 13.55% | 86.45% | [CPUC Status] Exempt [Utility Unique ID #1(Less Specific)] 2021-2315 , 2022-2975 , 2022-2766 , 2021-2457 , 2021-2010 , 2024-3883 , 2022-3046 , 2022-2956 , 2022-2948 , 2022-2930 , 2014-00575-ZZ , 2022-3047
72 | VARIOUS SUBS DC REL UPGR 2020 |  |  | San Diego, San Diego | DC Reliability Upgrades at multiple substations | Substation - Other Equipment | Upgrade/Retrofit | NA | NA | Reliability | Replace Other Substation Equipment | NA | NA | NA | NA | NA | NA | NA | Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 5.14 | Multiple | 373MVA | 4.3 | 2021-2057 | QBL0094 | 1 | 16138 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-04-07 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2021-05-10 | 2020-12-31 | 2021-11-09 | Prioritization | NA | FALSE | 1420.411 | NA ¦ NA | 2987.492 | 287.8832 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 | 2987.492 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 13.55% | 86.45% | [CPUC Status] Exempt
73 | DCRU PHASE IV IMPERIAL BEACH |  |  | San Diego, San Diego | Imperial Beach substation DC reliability upgrades | Substation - Other Equipment | Upgrade/Retrofit | NA | NA | Reliability | Replace Other Substation Equipment | NA | NA | 2025-10-02 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69 | 373MVA | 4.3 | 2020-2055 | QBL0094 | 1 | 16138 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-08-20 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2021-11-02 | 2021-12-31 | 2022-06-17 | Construction Delays | NA | FALSE | 211.161 | NA ¦ NA | 1497.4438 | 523.2661 | 830.3421 | 12.3177 | 2.2148 | 16.9044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 0.058964 | 1465.948 | 12.3177 | 2.2148 | 16.9044 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
74 | DCRU PHASE IV MIRAMAR |  |  | San Diego, San Diego | Miramar substation DC reliability upgrades | Substation - Protection Relay | Upgrade/Retrofit | NA | NA | Reliability | Replace Other Substation Equipment | NA | NA | 2025-11-06 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 0.76 | 69 | 373MVA | 4.3 | 2020-2054 | QBL0094 | 1 | 16138 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-08-20 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2024-03-04 | 2021-12-31 | 2025-01-14 | Construction Delays | NA | FALSE | 1868.1833 | NA ¦ NA | 2767.4987 | 124.3884 | 378.0122 | 235.6891 | 1985.4425 | 8.7289 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2024 ¦ 2025 | 0.0018632 | 0 | 0 | 2636.0175 | 131.4793 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
75 | DCRU: VARIOUS SUBS 2021 |  |  | San Diego, San Diego | DC Reliability Upgrades at multiple substations | Substation - Other Equipment | Upgrade/Retrofit | NA | NA | Reliability | Replace Other Substation Equipment | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | Multiple | 373MVA | 4.3 | Multiple | QBL0094 | 1 | 16138 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2021-02-16 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | NA | 2021-12-31 | 2021-12-31 | NA | NA | FALSE | 1512.758 | NA ¦ NA | 1930.476 | 1876.3438 | 54.1322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2022 | 0 | 1930.476 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 13.55% | 86.45% | [CPUC Status] Exempt [Utility Unique ID #1(Less Specific)] 2021-2178 , 2020-2101 , 2021-2315 , 2022-2765
76 | DCRU: SONGS (SAN ONOFRE) |  |  | San Diego, San Diego | Install two new 8.5 Ton HVAC units to replace existing end of life units. | Substation - Multiple | Upgrade/Retrofit | NA | NA | Reliability | Replace Other Substation Equipment | NA | NA | 2025-10-16 | NA | NA | NA | NA | Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 5.14 | 230 | 373MVA | 4.3 | 2024-3883 | QBL0094 | 1 | 16138 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-10-26 | Work Order Authorization | 2023 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Planning | NA | 2025-08-25 | NA | 2025-10-27 | Prioritization | NA | FALSE | 395.3153 | NA ¦ NA | 1141.6606 | 0 | 0.9567 | 45.8754 | 274.5863 | 160.8687 | 659.3736 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2025 | 0 | 0 | 0 | 0 | 1141.6606 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0% | [CPUC Status] Exempt
77 | [Programmatic] Trans Fiber Links HFTD |  |  | Multiple | Install ADSS and or OPGW on existing Transmission overhead structures to support the Wildfire Mitigation Plan | Other | New | NA | NA | Wildfire Mitigation | System Operations | NA | NA | NA | NA | NA | NA | NA | Tier 2 ¦ Tier 3 | TRUE ¦ TRUE ¦ TRUE | FALSE | NA |  | NA | NA | Multiple | NA | 1.2 | Multiple | QBL0100 | 53 | 19134 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-12-11 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | NA | NA | NA [See Notes] | NA | Operational | NA | NA | 2025-12-31 | Multiple | NA | NA | TRUE | NA | NA ¦ NA | 403009.8445 | 345.5437 | 893.8339 | 1233.1972 | 2875.3134 | 14171.4548 | 11311.4034 | 25792.2195 | 26030.9947 | 24623.1206 | 34537.1831 | 37496.0623 | 15225.9825 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 ¦ 2026 | 163.9221 | 152.0779 | 1032.388 | 1659.5538 | 1285.4188 | 13412.2359 | 0% | NA ¦ NA | 6.9 | NA | 13.55% | 86.45% | [CPUC Status] Exempt [Wildfire Related] The purpose of this program is to install ADSS and or OPGW on existing Transmission overhead structures to support the Wildfire Mitigation Plan
78 | CMP_T0_LR_TL689_Z614851X_NON_TT |  |  | San Diego, San Diego | Two poles are being replaced with foundation poles (Z12466, Z614851), one pole topped (Z12469), and one RFS pole (Z12467). | Other | New | New | NA | Reliability | System Operations | NA | NA | 2025-01-28 | 68 | NA | NA | NA | Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 7 | NA | NA | NA | 1.2 | TL689 Z614851/Z12466 | QBL0100 | 1 | 19134 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-08-21 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2020-05-28 | 2021-12-31 | 2023-09-18 | NA | NA | FALSE | 999.999 | NA ¦ NA | 1686.7875 | 69.8871 | 225.8063 | 735.6259 | 335.1959 | 12.4752 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2023 ¦ 2024 ¦ 2025 | 0 | 0 | 1339.1165 | 335.1959 | 12.4751 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] Exempt
79 | FBI TL6945 LH OLV |  |  | San Diego, San Diego | The project will include stringing 3.1 miles of new DNA-30411 ADSS conductor and about 2000 ft of DNO-11177 OPGW conductor, installing fiber attachments on existing transmission/distribution poles and installing fiber splice boxes. The conductor will enter Olivenhain and Lake Hodges substation overhead, attaching to existing substation infrastructure. It will also include lowering the crossarm on Z712320 and resagging the distribution conductor from Z220660 to Z201929 to mitigate clearances between the 69kV conductors and 12kV conductors. | Other | New | New | NA | Reliability | System Operations | NA | NA | 2025-01-28 | NA | NA | NA | NA | Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 4.3 | NA | NA | NA | 1.2 | 2019-4014 | QBL0100 | 1 | 19134 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-03-02; 2020-07-06; 2020-07-06 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | 2023-01-24 | 2022-06-01 | 2023-07-24 | NA | NA | FALSE | 2727.241 | NA ¦ NA | 1539.1717 | 132.3647 | 421.6995 | 624.975 | 286.1159 | 4.0743 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2023 ¦ 2024 ¦ 2025 | 0 | 0 | 1248.9816 | 286.1159 | 4.0743 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] NA
80 | FBI TL6930 ESCONDIDO OLIVEHAIN |  |  | Escondido, San Diego | The project will include stringing 2.2 miles of new DNA-30411 ADSS conductor (including 1.1 miles of underground ADSS, 0.1 miles of which will require new trenching), installing fiber attachments, and installing fiber splice boxes. It will also include reframing the transmission insulators on Z510521 and Z712314 to deadend attachments and the subsequent conductor work that follows. | Other | New | New | NA | Reliability | System Operations | NA | NA | 2025-02-02 | NA | NA | NA | NA | Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 3.8 | NA | NA | NA | 1.2 | 2019-4016 | QBL0100 | 1 | 19134 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-01-12; 2020-04-30; 2020-07-06 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2023-10-23 | 2022-06-01 | 2024-01-18 | NA | NA | FALSE | 3350.8595 | NA ¦ NA | 1142.7168 | 155.8618 | 278.3722 | 608.4003 | -49.8906 | 114.1271 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2024 ¦ 2025 | 0 | 0 | 0 | 1028.5897 | 114.1271 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] Exempt
81 | TL23022/23023 MISSION EL R2 |  |  | San Diego, Lakeside, Rancho San Diego | Reinforcement of all Towers. installing 15.5 miles of OPGW | Other | New | New | NA | Reliability | System Operations | NA | NA | 2025-02-20 | NA | NA | NA | NA | Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 39.57 | NA | NA | NA | 1.2 | 2009-00009-ZZ | QBL0100 | 1 | 19134 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2022-10-21 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | To be Filed | NA | Operational | NA | 2024-08-19 | 2024-10-24 | 2025-09-23 | NA | NA | FALSE | 19458.775 | NA ¦ NA | 8252.9794 | 134.6871 | 340.2847 | 378.6109 | 1703.5783 | 5453.7785 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2025 | 0 | 0 | 0 | 0 | 8252.9794 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] NA
82 | FBI_T2_L3_TL23051_Z873123_NONTT |  |  | Poway, San Diego | Install Fiber Sycamore to Chicarita Sub ( 5.8 miles).. Install Fiber from Chicarita sub to Artesia (5 miles) | Other | New | New | NA | Reliability | System Operations | NA | NA | 2025-06-10 | NA | NA | NA | NA | Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 1.88 | NA | NA | NA | 1.2 | 2009-00014-ZZ | QBL0100 | 1 | 19134 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2022-11-29; 2020-02-06; 2021-12-15 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | To be Filed | NA | Engineering more than 50% complete | NA | 2025-08-12 | 2024-12-31 | 2026-06-18 | NA | NA | FALSE | 15134.7583 | NA ¦ NA | 1563.937 | 48.0817 | 156.4773 | 699.3388 | 607.3652 | -3.1892 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 48.0817 | 156.4773 | 699.3388 | 607.3652 | -3.1892 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] NA
83 | TL23030 6932 PA LI FIBER L3 |  |  | San Diego, San Diego | Engineer and construct 9.3-miles of overhead OPGW-96 fiber optic cable structures between Lilac and Pala substations. | Other | New | New | NA | Reliability | System Operations | NA | NA | 2025-06-10 | NA | NA | NA | NA | Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 7.97 | NA | NA | NA | 1.2 | 2014-00958-ZZ | QBL0100 | 1 | 19134 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-03-16; 2019-04-29 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | To be Filed | NA | Construction (over 75%) | NA | 2025-08-18 | 2020-12-15 | 2026-01-09 | NA | NA | TRUE | 6333.0187 | NA ¦ NA | 4962.2938 | 309.0717 | 676.0852 | 1731.2528 | 1253.9359 | 296.4962 | 213.6785 | 57.9225 | 0 | 0 | 0 | 0 | 4690.6927 | NA | NA | 2026 | 0 | 0 | 0 | 0 | 0 | 4962.2938 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] NA
84 | TL689 BERNARDO FELECIT R4 |  |  | San Diego, San Diego | Engineer and construct 6.3 Miles of Overhead (OH) ADSS-96 fiber on 87 poles. Replace 9 new steel poles. 800 feet of UG fiber only trench & conduit from last pole to Felicita substation. Terminate, and test at substation control shelters. | Other | New | New | NA | Reliability | System Operations | NA | NA | 2025-01-28 | 40; 79; 79; 49; 60; 55; 58; 53 | NA | NA | NA | Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 7 | NA | NA | NA | 1.2 | 2014-00626-ZZ | QBL0100 | 1 | 19134 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-01-05; 2016-08-30; 2017-06-30; 2020-02-26 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2024-01-08 | 2018-06-20 | 2024-04-17 | NA | NA | FALSE | 5422.3961 | NA ¦ NA | 3189.9719 | 171.5073 | 616.5232 | 301.8656 | 1277.5654 | 17.8339 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2024 ¦ 2025 | 0 | 0 | 0 | 3172.138 | 17.8339 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0%
85 | TL635 LOS COCHES CREELMAN SUBS |  |  | Ramona, San Diego | This project installs a fiber optic connection between Creelman Substation and Los Coches Substation. | Other | New | New | NA | Reliability | System Operations | NA | NA | 2025-01-07 | NA | NA | NA | NA | Tier 3 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 10.5 | NA | NA | NA | 1.2 | 2014-01080-ZZ | QBL0100 | 1 | 19134 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-01-28; 2020-02-26; 2020-02-26 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | To be Filed | NA | Operational | NA | 2020-09-30 | 2021-06-01 | 2022-03-22 | NA | NA | FALSE | 4982.346 | NA ¦ NA | 1826.1336 | 3151.6998 | 326.408 | 65.2845 | -2351.1425 | 56.0882 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 0 | 4055.9034 | 65.2845 | -2351.1425 | 56.0882 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] NA
86 | TL6917 CREELMAN SYCAMORE CYN |  |  | Ramona, San Diego | This project installs a fiber optic connection between Sycamore Canyon Substation and Creelman Substation. | Other | New | New | NA | Reliability | System Operations | NA | NA | 2025-01-13 | 27 | NA | NA | NA | Tier 3 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 12.2 | NA | NA | NA | 1.2 | 2014-01079-ZZ | QBL0100 | 1 | 19134 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-01-28 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2020-09-30 | 2021-06-01 | 2022-02-17 | NA | NA | FALSE | 5467.342 | NA ¦ NA | 2006.7811 | 1162.539 | 211.2685 | 88.8135 | -149.1958 | 72.526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 0 | 1994.6373 | 88.8135 | -149.1958 | 72.526 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] Exempt
87 | FBI_T2_L3_TL230001_Z96439_NONTT |  |  | San Diego, San Diego | FBI TL23004-TL23001 MROPS - RBDC Fiber Build | Other | New | New | NA | Reliability | System Operations | NA | NA | 2025-10-03 | NA | NA | NA | NA | Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 4.81 | NA | NA | NA | 1.2 | 2014-00950-ZZ | QBL0100 | 1 | 19134 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-07-25 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | To be Filed | NA | Operational | NA | 2024-11-08 | 2020-12-01 | 2025-09-15 | NA | NA | FALSE | 3099.5761 | NA ¦ NA | 5722.5655 | 822.6322 | 547.967 | 1450.8858 | 1001.5417 | 1706.7291 | 189.9954 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2025 | 0 | 0 | 0 | 0 | 5722.5655 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] NA
88 | TL6904 ALPINE LOVELAND TRNM FIB |  |  | Alpine, San Diego | Install a level of ADSS fiber on 2.4 miles of TL6904 poles between Alpine Substation and Loveland Substation. Construct ADSS conduit on Z770043 and trench into Loveland Substation. Construct ADSS conduit on Z875063 and trench into Alpine Substation. Construct ADSS conduit on Z770043 and trench into Loveland Substation (to be designed by others). 3 Steel Pole Replacements | Other | New | New | NA | Reliability | System Operations | NA | NA | 2025-10-03 | 54; 54; 54 | NA | NA | NA | Tier 3 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 0.5 | NA | NA | NA | 1.2 | 2019-4008 | QBL0100 | 1 | 19134 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-01-05; 2020-01-08; 2020-01-16; 2020-01-16 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2023-06-19 | 2022-08-20 | 2023-11-15 | NA | NA | FALSE | 2201.0696 | NA ¦ NA | 1815.4521 | 111.7932 | 327.4758 | 977.8927 | 262.7786 | 62.2646 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2023 ¦ 2024 ¦ 2025 | 0 | 0 | 1490.4089 | 262.7786 | 62.2646 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] Exempt
89 | TL23022/23 MISSION TO LOS COCHE |  |  | San Diego ¦ Santee ¦ Granite Hills, San Diego | Remove and replace 19miles of OHGW with OPGW. | Other | Upgrade/Retrofit | Upgrade/Retrofit | NA | Reliability | System Operations | NA | NA | 2025-02-02 | NA | NA | NA | NA | Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | TBD |  | 39.57 | NA | NA | NA | 1.2 | 2023-3234 | QBL0100 | 1 | 19134 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-01-11 | Work Order Authorization | 2023 | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | CPUC | NA | Exempt | NA | NA | NA | Engineering more than 50% complete | NA | 2026-05-26 | 2025-12-01 | 2027-07-21 | NA | NA | FALSE | 16508.676 | NA ¦ NA | 2354.3932 | 0 | 0 | 476.3328 | 1163.8882 | 295.6179 | 87.4479 | 186.9251 | 144.1813 | 0 | 0 | 0 | 1935.8389 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] NA
90 | FBI TL23002/23010 SOSA |  |  | Camp Pendleton, San Diego | Remove and replace 18 miles of OHGW with OPGW | Other | Replace | Upgrade/Retrofit | NA | Reliability | System Operations | NA | NA | 2025-01-05 | NA | NA | NA | NA | Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | TBD |  | 17.74 | NA | NA | NA | 1.2 | 2023-3433 | QBL0100 | 1 | 19134 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-06-28 | Work Order Authorization | 2024 | NA | FALSE | NA | NA | NA | FALSE | TBD | TBD | Exempted | NA | CPUC | NA | Exempt | NA | NA | NA | Engineering less than 50% complete | NA | 2025-11-11 | 2027-04-30 | 2027-03-24 | NA | NA | FALSE | NA | NA ¦ NA | 3877.9624 | 0 | 0 | 24.3011 | 2129.6834 | 1055.3996 | 139.685 | 298.5851 | 230.3082 | 0 | 0 | 0 | 3209.3841 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] NA
91 | FBI TL23006 SO SA |  |  | Camp Pendleton, San Diego | Remove and replace 18 miles of OHGW with OPGW | Other | Replace | Upgrade/Retrofit | NA | Reliability | System Operations | NA | NA | 2025-08-01 | NA | NA | NA | NA | Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | TBD |  | 17.74 | NA | NA | NA | 1.2 | 2023-3431 | QBL0100 | 1 | 19134 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-06-28 | Work Order Authorization | 2024 | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Engineering less than 50% complete | NA | 2025-11-11 | 2027-01-30 | 2027-02-26 | NA | NA | FALSE | 2256.547 | NA ¦ NA | 5054.2079 | 0 | 0 | 165.3863 | 2911.161 | 1122.7189 | 186.3105 | 398.2499 | 270.3812 | 0 | 0 | 0 | 4199.2663 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] Exempt
92 | FBI TL23052/23007 SO TA |  |  | Camp Pendleton, San Diego | Remove and replace 7 miles of OHGW with OPGW | Other | Replace | Upgrade/Retrofit | NA | Reliability | System Operations | NA | NA | 2025-07-26 | NA | NA | NA | NA | Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | TBD |  | 8.23 | NA | NA | NA | 1.2 | 2023-3434 | QBL0100 | 1 | 19134 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-06-30 | Work Order Authorization | 2024 | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Engineering less than 50% complete | NA | 2025-06-03 | 2026-11-15 | 2027-05-03 | NA | NA | FALSE | NA | NA ¦ NA | 2837.0201 | 0 | 0 | 176.1924 | 1232.9519 | 947.9722 | 104.5815 | 223.5493 | 151.7728 | 0 | 0 | 0 | 2357.1165 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] Exempt
93 | FBI TL23004/23001 SAN LUIS REY |  |  | San Diego, San Diego | Remove and replace 6miles of OHGW with OPGW | Other | Upgrade/Retrofit | Upgrade/Retrofit | NA | Reliability | System Operations | NA | NA | 2025-07-23 | NA | NA | NA | NA | Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | TBD |  | 41.64 | NA | NA | NA | 1.2 | 2023-3412 | QBL0100 | 1 | 19134 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-06-07 | Work Order Authorization | 2023 | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2026-09-25 | 2025-12-31 | 2025-05-17 | NA | NA | FALSE | 2143.4765 | NA ¦ NA | 2916.7485 | 0 | 0 | 369.4347 | 1366.2285 | 304.269 | 92.0913 | 196.8506 | 215.0371 | 234.9037 | 137.9337 | 0 | 2039.9322 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] Exempt
94 | TL685 SANTA YSABEL TO WA R1 |  |  | San Diego, San Diego | Install approximately 11 miles of 96 count fiber optic DNA-30411. Installation will begin at Warner Springs Substation and terminate at Santa Ysabel Substation. There are a total of 155 structures along the TL at which fiber optic will be installed. | Other | New | New | NA | Reliability | System Operations | NA | NA | 2025-08-27 | NA | NA | NA | NA | Tier 2 ¦ Tier 3 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 13.33 | NA | NA | NA | 1.2 | 2014-00624-ZZ | QBL0100 | 1 | 19134 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2022-02-04; 2020-01-27; 2020-01-14; 2020-01-14 | Work Order Authorization | 2019 | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2020-05-18 | 2020-11-30 | 2022-09-28 | NA | NA | FALSE | 7336.2692 | NA ¦ NA | 1062.405 | 188.2618 | 146.2065 | 84.7003 | 5.297 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2022 ¦ 2023 ¦ 2024 | 0 | 972.4077 | 84.7003 | 5.297 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] Exempt
95 | FBI_T2_L2_TL683_Z518466_NONTT |  |  | Valley Center, San Diego | This project installs 9.7 miles of ADSS fiber | Other | New | New | NA | Reliability | System Operations | NA | NA | 2025-08-27 | 54; 54; 25; 54; 37; 54; 54; 42 | NA | NA | NA | Tier 2 ¦ Tier 3 | FALSE ¦ TRUE ¦ FALSE | FALSE | TBD |  | 11.86 | NA | NA | NA | 1.2 | 2014-00983-ZZ | QBL0100 | 1 | 19134 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-01-08; 2021-12-15; 2021-12-15 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Permitting | NA | NA | 2022-12-01 | 2026-04-27 | NA | NA | FALSE | 4223.5163 | NA ¦ NA | 3052.0965 | 50.311 | 288.6427 | 409.4544 | 1893.4302 | 326.0825 | 79.1976 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2025 | 0 | 0 | 0 | 0 | 3052.0965 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] Exempt
96 | RINCON SUB TO PALOMAR MT C214 |  |  | San Diego, San Diego | Engineer and construct a total of 9.0 miles of new 96-single mode fiber optic cable for mountaintop fiber installation. Install 9.0 miles of OH (S197808 / DNA-30411) All-Dielectric Self Support (ADSS) 96-fiber on existing distribution structures. GO95 Compliance review and report ( 30% pass/fail to report) will determine any structure/pole replacements, upgrades, or any Distribution underbuild that may be required prior to stringing. Splice and test as per SDG&E Fiber Build standards. | Substation - Multiple | New | New | NA | Reliability | System Operations | NA | NA | NA | NA | NA | NA | NA | Tier 3 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 9 | NA | 69 | NA | 1.2 | Rincon to Palomar | QBL0100 | 1 | 19134 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2022-12-14 | Work Order Authorization | 2023 | NA | FALSE | NA | NA | NA | FALSE | PEA Deemed Complete | NA | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | On Hold | NA | NA | NA | NA | NA | NA | TRUE | 1590.7568 | NA ¦ NA | 1691.9545 | 0 | 0 | 61.1034 | 1344.3693 | 81.4789 | 66.9976 | 138.0053 | 0 | 0 | 0 | 0 | 1483.1295 | NA | NA | 2025 ¦ 2026 | 0 | 0 | 0 | 0 | 3.8221 | 1688.1325 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
97 | FBI TL694 Z31079 Z317898 |  |  | Oceanside, San Diego | San Diego Gas and Electric (SDG&E) proposes to install approximately 3.2 miles of 96-count ADSS fiber optic cable. 3.2 miles of OH (S197808 / DNA-30411) All-Dielectric Self Support (ADSS) 96-fiber on existing structures. GO95 Compliance review and report will determine any structure/pole replacements, upgrades, or any Distribution underbuild that may be required prior to stringing. GO128 review and report to determine if any existing handholes will require upgrades or new handholes installations. Splice and test as per SDG&E Fiber Build standards. | Substation - Multiple | New | New | NA | Reliability | System Operations | NA | NA | 2025-01-30 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 9.51 | NA | 69 | NA | 1.2 | 2020-4024 | QBL0100 | 1 | 19134 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2022-02-24 | Work Order Authorization | 2022 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Planning | NA | 2024-10-09 | 2024-07-22 | 2025-05-16 | NA | NA | FALSE | 5767.7932 | NA ¦ NA | 3652.64 | 0 | 62.6967 | 350.1312 | 2320.4702 | 876.9918 | 42.35 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2025 | 0 | 0 | 0 | 0 | 3652.64 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
98 | FBI TL694 NVY OCR ME PHASE 1 UG |  |  | Oceanside, San Diego | Engineer and construct a total of 6.5 miles of new 96-singlemode fiber optic cable for relay protection and network communications. Install 3X inner-ducts and (S197826 / DNL-4599) All-Dielectric 96-fiber through existing UG ducts, and 3.5 miles of OH (S197808 / DNA-30411) All-Dielectric Self Support (ADSS) 96-fiber on existing structures. GO95 Compliance review and report will determine any structure/pole replacements, upgrades, or any Distribution underbuild that may be required prior to stringing. GO128 review and report to determine if any existing handholes will require upgrades or new handholes installations. Splice and test as per SDG&E Fiber Build standards. | Substation - Multiple | New | New | NA | Reliability | 3rd Party Damage | NA | NA | 2025-01-30 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 9.51 | NA | 69 | NA | 1.2 | 2014-00979-ZZ | QBL0100 | 1 | 19134 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-04-04; 2024-01-23; 2022-01-31 | Work Order Authorization | 2023 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2024-08-19 | 2022-12-10 | 2025-04-16 | NA | NA | FALSE | 5814.2996 | NA ¦ NA | 4646.7441 | 0 | 100.6571 | 332.9439 | 2833.091 | 1380.0521 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2025 | 0 | 0 | 0 | 0 | 4646.7441 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
99 | TL681 VALLEY ASH FIB R3 |  |  | Escondido ¦ Valley Center, San Diego | This project installs a fiber optic connection between Valley Center Substation and Ash Substation. | Substation - Multiple | New | New | NA | Reliability | 3rd Party Damage | NA | NA | 2025-02-28 | NA | NA | NA | NA | Tier 1 ¦ Tier 2 ¦ Tier 3 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 8 | NA | 69 | NA | 1.2 | 2014-00949-ZZ | QBL0100 | 1 | 19134 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-01-29; 2020-02-07 | Work Order Authorization | 2019 | NA | FALSE | NA | NA | NA | FALSE | PEA Deemed Complete | NA | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Engineering more than 50% complete | NA | 2025-09-10 | 2024-12-01 | 2026-08-12 | NA | NA | TRUE | 4090.086 | NA ¦ NA | 6191.4184 | 151.1181 | 184.7559 | 284.8158 | 4214.981 | 562.0838 | 254.3017 | 337.8405 | 0 | 0 | 0 | 0 | 5599.2762 | NA | NA | 2024 ¦ 2025 ¦ 2026 | 0 | 0 | 0 | -11.963 | -10.3905 | 6213.7719 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
100 | FBI MIGUEL TO MIGUEL |  |  | San Diego, San Diego | This is a fiber project to add communication cable ADSS 7.8 miles UG & OH from Miguel tower to Miguel substation | Other | New | New | NA | Reliability | System Operations | NA | NA | NA | NA | NA | NA | NA | Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | TBD |  | NA | 12.37 | 69 | NA | 1.2 | 2022-3158 | QBL0100 | 1 | 19134 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2022-12-16 | Work Order Authorization | 2023 | NA | FALSE | NA | NA | NA | FALSE | TBD | TBD | Exempted | Other [See Notes] | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Engineering less than 50% complete | NA | 2026-09-10 | 2026-09-28 | 2027-07-30 | NA | NA | FALSE | 1508.8844 | NA ¦ NA | 1129.1452 | 0 | 0 | 89.4503 | 251.7647 | 564.4721 | 41.4558 | 88.6462 | 93.3561 | 0 | 0 | 0 | 905.6871 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] NA
101 | GLENCLIFF SUB-MONUMENTPEAKC440 |  |  | San Diego, San Diego | This is a fiber project to add communication cable ADSS 11.5 miles UG & OH from Glencliff to Monument peak substation | Other | New | New | NA | Reliability | System Operations | NA | NA | NA | NA | NA | NA | NA | Tier 3 | FALSE ¦ FALSE ¦ FALSE | FALSE | TBD |  | NA | 0.15 | 69 | NA | 1.2 | 2022-3136 | QBL0100 | 1 | 19134 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2022-12-14 | Work Order Authorization | 2023 | NA | FALSE | NA | NA | NA | FALSE | TBD | TBD | Exempted | Other [See Notes] | CPUC | CNF | Exempt | NA | NA [See Notes] | NA | Engineering more than 50% complete | NA | 2027-12-26 | 2026-09-18 | 2028-03-22 | NA | NA | FALSE | 1590.7568 | NA ¦ NA | 1157.5562 | 0 | 0 | 44.7336 | 224.7437 | 601.6884 | 39.3735 | 84.1631 | 91.9387 | 70.9153 | 0 | 0 | 871.1657 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] NA
102 | [Programmatic] PSPS Engineering Enhancements |  |  | Multiple | Mitigate the impact to customers and communities involved in PSPS events by installing additional remote distribution sectionalizing devices (reclosers) within the HFTD. ​ | Other | New | Upgrade/Retrofit | NA | Wildfire Mitigation | Fire Protection | NA | NA | NA | NA | NA | NA | NA | Tier 2 ¦ Tier 3 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | NA | NA | NA | NA | 1.2 | Multiple | NA | 7 | 19245 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-11-16 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Operational | NA | NA | 2024-12-31 | NA | NA | NA | TRUE | NA | NA ¦ NA | 1890.1606 | 140.7236 | 86.0347 | 54.0949 | 85.3059 | 45.8499 | 32.7767 | 158.866 | 173.5294 | 269.1981 | 19.8373 | 9.4538 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 ¦ 2026 | 117.009 | 904.8739 | 62.5786 | 74.5874 | -0.79237 | 37.2068 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] NA
103 | [Programmatic] HFTD Undergrounding |  |  | Multiple | Blanket budget for High Fire Threat District undergrounding work. This is an electric distribution blanket budget. The forecasted costs shown for this project are only the FERC-specific transmission costs. | Transmission Line/Substation | Upgrade/Retrofit | NA | NA | Wildfire Mitigation | Fire Protection | NA | NA | NA | NA | NA | NA | NA | Tier 1 ¦ Tier 2 ¦ Tier 3 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | Multiple | Multiple | 1.2 | Multiple | QBL0081 | 6 | 19246 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2025-03-17 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Operational | NA | Multiple | Multiple | Multiple | NA | NA | FALSE | NA | NA ¦ NA | 411.7796 | -259.1355 | -20.1032 | 747.9368 | -724.5059 | 302.0345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 55.9535 | 11.0168 | 24.1834 | -59.4965 | 380.1224 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 13.55% | 86.45% | [CPUC Status] Exempt
104 | HFTD Undergrounding |  |  | Multiple | Conversion of OH dist. lines to UG dist. lines within the HFTD | Other | Upgrade/Retrofit | NA | NA | Wildfire Mitigation | Facility Relocation | NA | NA | NA | NA | NA | NA | NA | Tier 2 ¦ Tier 3 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | NA | NA | NA | NA | 1.2 | NA | QBL0081 | 1 | 19246 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2025-03-17 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | Multiple | Multiple | Multiple | NA | NA | FALSE | NA | NA ¦ NA | 3360.8872 | 33.6557 | 2349.5081 | 154.8362 | 523.1324 | 292.7826 | 0 | 0 | 0 | 0 | 0 | 0 | 809.5759 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 19.8374 | 267.2411 | 2238.4636 | 17.5389 | 1.2582 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] Exempt
105 | [Programmatic] Fire Science Enhancement |  |  | Multiple | This project will enhance the fire science capabilities at SDGE. New tools and technologies will be developed to greatly enhance current technologies such as the fire potential index and create the next generation of fire weather tools. Partnerships with leading academic innovators on the cutting edge of research and development in fire science will ensure SDGE remains an industry leader. | Other - Operations Tech | NA | NA | NA | Wildfire Mitigation | Fire Protection | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | NA | NA | 1.2 | Multiple |  | 4 | 19248 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-11-22 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Operational | NA | NA | 2023-12-31 | NA | NA | NA | FALSE | NA | NA ¦ NA | 1006.726 | 240.0384 | 283.2154 | 233.0757 | 210.3933 | -206.6508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 486.6925 | 283.2154 | 233.0757 | 210.3933 | -206.6508 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 13.55% | 86.45%
106 | [Programmatic] Transmission CMP Non HFTD |  |  | Multiple | Remediate CMP Issues in the Non-HFTD Zone | Transmission Line - Pole/Tower | Replace | NA | NA | Asset Condition | Age/Condition | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | Individual Project Review Required |  | NA | NA | Multiple | NA | 1.1 | Multiple | QBL0098 | 1054 | 20126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-12-11 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | TBD | TBD | Exempted | NA | CPUC | NA | Exempt | NA | To be Filed | NA | Operational | NA | NA | NA | Multiple | NA | NA | TRUE | NA | NA ¦ NA | 780122.1586 | 33137.7366 | 32081.3685 | 34373.4904 | 30559.2269 | 39556.1374 | 24503.766 | 42521.0108 | 40824.2535 | 43113.5471 | 45898.9632 | 45387.5632 | 19902.9797 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 ¦ 2026 | 33399.2033 | 32892.6986 | 35616.8424 | 31458.44 | 16437.7959 | 42808.4164 | 0% | NA ¦ NA | 2.1 | NA | 13.55% | 86.45%
107 | CMP_T0_L2_TL6925_Z273965_14637 |  |  | El Cajon, San Diego | Remediate CMP Issues in the Non-HFTD Zone | Transmission Line - Pole/Tower | Replace | Upgrade/Retrofit | NA | Other [See Notes] | Age/Condition | NA | NA | 2025-02-15 | 65 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.1 | NA | Multiple | NA | 1.1 | 2023-3297 | QBL0098 | 1 | 20126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-06-19; 2024-04-22 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | To be Filed | NA | Permitting | NA | 2026-03-15 | 2022-12-31 | 2026-06-15 | Permitting | Scope Change | FALSE | 582.9629 | NA ¦ NA | 1970.4939 | 186.6442 | 343.7054 | 266.8045 | 964.4946 | 141.7838 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2024 ¦ 2025 | 0 | 0 | 0 | 1828.7101 | 141.7838 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 13.55% | 86.45% | [Primary Purpose] Fire Damage
108 | CMP_T0_TL630_Z475724_TT13577 |  |  | El Cajon, San Diego | Remediate CMP Issues in the Non-HFTD Zone | Transmission Line - Pole/Tower | Replace | Upgrade/Retrofit | NA | Asset Condition | Age/Condition | NA | NA | 2025-02-15 | 63 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.1 | NA | 69 | NA | 1.1 | TL630 Z475724 | QBL0098 | 1 | 20126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2021-03-08; 2018-02-20 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2018-02-14 | 2020-02-14 | 2023-12-03 | Permitting | Material | FALSE | 84.4165 | NA ¦ NA | 2949.1705 | 283.6215 | 547.349 | 1233.3298 | 659.4369 | -5.8171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2024 ¦ 2025 | 0 | 0 | 0 | 2954.9876 | -5.8171 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] NA
109 | CMP_T0_L2_TL600_Z91160_14180 |  |  | San Diego, San Diego | Remediate CMP Issues in the Non-HFTD Zone | Transmission Line - Pole/Tower | Replace | Upgrade/Retrofit | NA | Asset Condition | Age/Condition | NA | NA | 2025-02-15 | 73 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69 | NA | 1.1 | TL600 Z91160 | QBL0098 | 1 | 20126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-08-21 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | To be Filed | NA | Operational | NA | 2022-02-04 | 2020-12-31 | 2023-06-11 | Permitting | Material | FALSE | 999.999 | NA ¦ NA | 1441.9853 | 121.8526 | 736.2249 | 396.4809 | 26.0207 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2023 ¦ 2024 | 0 | 0 | 1415.9646 | 26.0207 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
110 | CMP_T0_L2_TL6908_Z618845_11163 |  |  | Escondido, San Diego | Remediate CMP Issues in the Non-HFTD Zone | Transmission Line - Pole/Tower | Replace | Upgrade/Retrofit | NA | Asset Condition | Age/Condition | NA | NA | 2025-02-10 | 32 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69 | NA | 1.1 | TL6908 Z618845 | QBL0098 | 1 | 20126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-03-06 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | To be Filed | NA | Operational | NA | 2021-07-01 | 2021-10-04 | 2021-09-22 | NA | NA | FALSE | 80 | NA ¦ NA | 1016.1745 | 876.3129 | 33.283 | 22.972 | 0.00052 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 | 959.9189 | 33.283 | 22.972 | 0.00052 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
111 | CMP_T0_L3_TL655/699_ STRUCTURES |  |  | San Diego, San Diego | Remediate CMP Issues in the Non-HFTD Zone | Transmission Line - Pole/Tower | Replace | Upgrade/Retrofit | NA | Asset Condition | Age/Condition | NA | NA | 2025-02-11 | 28 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.1 | NA | 69 | NA | 1.1 | 2022-2738 | QBL0098 | 1 | 20126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2021-11-04; 2015-02-11 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | To be Filed | NA | Construction (25%-50%) | NA | 2024-03-30 | 2020-12-31 | 2026-02-01 | Permitting | Material | FALSE | 229.4765 | NA ¦ NA | 2640.7564 | 63.8041 | 373.7149 | 700.6281 | 276.5893 | 888.9091 | 40.9363 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2025 | 0 | 0 | 0 | 0 | 2640.7564 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [Reason for Change in In-Service Date] Multiple ESP Project. Delays from the agency to obtain the approved Railroad Permit Application. Job was awarded to one Contractor and re assigned to a different one due to the original contractor moving away from supporting the program
112 | CMP_T0_L3_TL13815_Z731374_TT119 |  |  | San Diego, San Diego | Remediate CMP Issues in the Non-HFTD Zone | Transmission Line - Pole/Tower | Replace | Upgrade/Retrofit | NA | Asset Condition | Age/Condition | NA | NA | 2025-02-11 | 48 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 138 | NA | 1.1 | TL13815 Z731374 | QBL0098 | 1 | 20126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2015-06-09 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | To be Filed | NA | Operational | NA | 2020-04-21 | 2017-12-31 | 2020-08-23 | Permitting | Permitting | FALSE | 229.4765 | NA ¦ NA | 1589.0168 | 121.7024 | 77.7803 | 11.3399 | 0.56295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 | 1499.3336 | 77.7803 | 11.3399 | 0.56295 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
113 | CMP_T0_L3_TL651_Z730387_TT13534 |  |  | San Diego, San Diego | Remediate CMP Issues in the Non-HFTD Zone | Transmission Line - Pole/Tower | Replace | Upgrade/Retrofit | NA | Field Test Results | Age/Condition | NA | NA | 2025-02-11 | 54 | NA | NA | NA | Tier 0 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.1 | NA | 69 | NA | 1.1 | TL651 Z730387 | QBL0098 | 1 | 20126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2021-03-26; 2018-01-31 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | To be Filed | NA | Operational | NA | 2021-04-09 | 2019-12-31 | 2023-05-21 | Permitting | Permitting | FALSE | 138.8568 | NA ¦ NA | 2797.2897 | 1419.8572 | 805.0292 | 30.8096 | 324.9223 | 1.9667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 0 | 2439.591 | 30.8096 | 324.9223 | 1.9667 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
114 | TL23026 13815 Z189540 IN R3 |  |  | National City, San Diego | Remediate CMP Issues in the Non-HFTD Zone | Transmission Line - Other Equipment | Replace | NA | NA | Asset Condition | Age/Condition | NA | NA | 2025-07-21 | 18 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.1 | NA | 138¦230 | NA | 1.1 | 2019-4001 | QBL0098 | 1 | 20126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2018-10-01 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | To be Filed | NA | Planning | NA | 2020-10-08 | 2021-08-22 | 2021-04-08 | NA | NA | FALSE | 3804.368 | NA ¦ NA | 3476.8949 | 2840.4149 | 1.8014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 | 3475.0934 | 1.8014 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 13.55% | 86.45%
115 | CMP_T0_L2_TL652_Z214987X_15018 |  |  | San Diego, San Diego | Remediate CMP Issues in the Non-HFTD Zone | Transmission Line - Pole/Tower | Replace | Upgrade/Retrofit | NA | Asset Condition | Age/Condition | NA | NA | 2025-07-21 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.1 | NA | 69 | NA | 1.1 | TL652 Group 01 | QBL0098 | 1 | 20126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2018-10-23 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | To be Filed | NA | Operational | NA | 2020-12-31 | 2021-10-17 | 2021-05-17 | NA | NA | FALSE | 9.999 | NA ¦ NA | 1219.5434 | 495.9643 | 29.2382 | 104.0368 | 51.842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 | 1034.4264 | 29.2382 | 104.0368 | 51.842 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
116 | CMP_T0_L2_TL608_Z371845X_NON_TT |  |  | Lemon Grove, San Diego | Remediate CMP Issues in the Non-HFTD Zone | Transmission Line - Pole/Tower | Replace | NA | NA | Asset Condition | Age/Condition | NA | NA | 2025-04-25 | 73 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.1 | NA | 69 | NA | 1.1 | TL608 Group 01 | QBL0098 | 1 | 20126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-08-13 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | To be Filed | NA | Operational | NA | 2022-06-17 | 2021-12-31 | 2023-04-24 | Project Design | Permitting | FALSE | 999.999 | NA ¦ NA | 1365.0031 | 82.5021 | 1006.9006 | 92.0874 | 195.0773 | 3.451 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2023 ¦ 2024 ¦ 2025 | 0 | 0 | 1166.4749 | 195.0773 | 3.451 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
117 | CMP_T0_L2_TL617_2320469X_NON_TT |  |  | San Diego, San Diego | Remediate CMP Issues in the Non-HFTD Zone | Transmission Line - Pole/Tower | Replace | NA | NA | Asset Condition | Age/Condition | NA | NA | 2025-04-25 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.1 | NA | 69 | NA | 1.1 | TL617 Group 01 | QBL0098 | 1 | 20126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-09-27 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | To be Filed | NA | Operational | NA | 2021-11-25 | 2020-12-31 | 2022-04-10 | Project Design | Permitting | FALSE | 999.999 | NA ¦ NA | 1380.5653 | 315.8678 | 464.5618 | 61.7387 | 114.9573 | -11.9451 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 0 | 1215.8144 | 61.7387 | 114.9573 | -11.9451 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
118 | CMP_T0_L2_TL684_Z114414X_NON_TT |  |  | San Marcos, San Diego | Remediate CMP Issues in the Non-HFTD Zone | Transmission Line - Pole/Tower | Replace | NA | NA | Asset Condition | Age/Condition | NA | NA | 2025-02-20 | 30 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.1 | NA | 69 | NA | 1.1 | TL684 Group 03 | QBL0098 | 1 | 20126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-09-27 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | To be Filed | NA | Operational | NA | 2021-01-15 | 2020-12-31 | 2021-06-28 | Project Design | NA | FALSE | 999.999 | NA ¦ NA | 1024.1634 | 611.2737 | 64.1403 | 25.0141 | 49.0023 | 0.4293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 885.5775 | 64.1403 | 25.0141 | 49.0023 | 0.4293 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
119 | CMP_T0_L2_TL684_Z815163X_NON_TT |  |  | San Marcos, San Diego | Remediate CMP Issues in the Non-HFTD Zone | Transmission Line - Pole/Tower | Replace | Replace | NA | Asset Condition | Age/Condition | NA | NA | 2025-02-20 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.1 | NA | 69 | NA | 1.1 | TL684 Group 05 | QBL0098 | 1 | 20126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-09-27 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | To be Filed | NA | Operational | NA | 2021-03-02 | 2020-12-31 | 2021-07-24 | Project Design | NA | FALSE | 999.999 | NA ¦ NA | 1322.0239 | 133.553 | -25.3601 | 704.0905 | 66.2854 | 7.1343 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 569.8737 | -25.3601 | 704.0905 | 66.2854 | 7.1343 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
120 | CMP_T0_L2_TL624_Z371343X_NON_TT |  |  | El Cajon, San Diego | Remediate CMP Issues in the Non-HFTD Zone | Transmission Line - Pole/Tower | Replace | Upgrade/Retrofit | NA | Asset Condition | Age/Condition | NA | NA | 2025-02-15 | 36 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.1 | NA | 69 | NA | 1.1 | TL624 Group 04 | QBL0098 | 1 | 20126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2021-03-26;2019-10-11 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | To be Filed | NA | Operational | NA | 2022-03-26 | 2020-12-31 | 2022-12-10 | Permitting | Project Design | FALSE | 1128.8568 | NA ¦ NA | 1142.3024 | 212.0273 | 652.9327 | 182.8411 | 10.52 | 0.36686 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2023 ¦ 2024 ¦ 2025 | 0 | 0 | 1131.4156 | 10.52 | 0.36686 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
121 | CMP_T0_L2_TL603_Z183889X_14421 |  |  | National City, San Diego | Remediate CMP Issues in the Non-HFTD Zone | Transmission Line - Pole/Tower | Replace | Upgrade/Retrofit | NA | Asset Condition | Age/Condition | NA | NA | 2025-02-28 | 76 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.1 | NA | 69 | NA | 1.1 | TL603 Z1838893443 | QBL0098 | 1 | 20126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2021-10-18; 2019-12-12; 2019-12-12 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | To be Filed | NA | Construction (25%-50%) | NA | 2023-01-10 | 2023-06-15 | 2026-03-15 | Permitting | Project Design | FALSE | 1314.2046 | NA ¦ NA | 3025.076 | 566.8735 | 294.3714 | 704.2704 | 1191.6785 | 30.4631 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 0 | 1094.8542 | 78.7618 | 1820.997 | 30.4631 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
122 | CMP_T0_L2_TL681_Z12922,X_NON_TT |  |  | Escondido, San Diego | Remediate CMP Issues in the Non-HFTD Zone | Transmission Line - Pole/Tower | Replace | NA | NA | Asset Condition | Age/Condition | NA | NA | 2025-02-28 | 62; 62; 62; 46; 52; 43 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.1 | NA | 69 | NA | 1.1 | TL681 Group 03 | QBL0098 | 1 | 20126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-02-21 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | To be Filed | NA | Operational | NA | 2021-11-01 | 2021-01-09 | 2022-03-19 | Project Design | NA | FALSE | 999.999 | NA ¦ NA | 1022.9813 | 222.4498 | 670.626 | 111.0577 | 1.6852 | 0.14597 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 0 | 910.0924 | 111.0577 | 1.6852 | 0.14597 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
123 | CMP_T0_LX_TL662 TL6905_COASTAL |  |  | San Diego, San Diego | Remediate CMP Issues in the Non-HFTD Zone | Transmission Line - Pole/Tower | Replace | NA | NA | Asset Condition | Age/Condition | NA | NA | 2025-02-15 | 34; 34; 34; 34; 34; 45; 34; 45 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | Coastal |  | 0.1 | NA | 69 | NA | 1.1 | 2023-3590 | QBL0098 | 1 | 20126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-11-15 | Work Order Authorization | 2024 | NA | FALSE | NA | NA | NA | FALSE | CEQA Final Published | TBD | Exempted | NA | CPUC | NA | Exempt | NA | To be Filed | NA | Operational | NA | 2024-08-12 | 2024-08-30 | 2025-03-09 | Construction Delays | Outage | FALSE | 513.5659 | NA ¦ NA | 1745.3839 | 0 | 0 | 3.5589 | 1292.1099 | 449.7151 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2025 | 0 | 0 | 0 | 0 | 1745.3839 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
124 | CMP_T0_L3_TL13840_Z579784_11835 |  |  | San Diego, San Diego | Remediate CMP Issues in the Non-HFTD Zone | Transmission Line - Pole/Tower | Replace | Upgrade/Retrofit | NA | Asset Condition | Age/Condition | NA | NA | 2025-05-23 | 55 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | TBD |  | 0.1 | NA | 138 | NA | 1.1 | TL13840 Z579784 | QBL0098 | 1 | 20126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2017-05-03 | Work Order Authorization | 2019 | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | CPUC | NA | Exempt | NA | To be Filed | NA | Construction (25%-50%) | NA | 2025-04-30 | 2018-12-31 | 2026-02-24 | Permitting | NA | FALSE | 80 | NA ¦ NA | 4514.8018 | 17.2361 | 74.0575 | 147.9806 | 3329.3827 | 108.5558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 17.2361 | 74.0575 | 147.9806 | 3329.3827 | 108.5558 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
125 | CMP_T0_L2_TL642_Z184518X_12827 |  |  | San Diego, San Diego | Remediate CMP Issues in the Non-HFTD Zone | Transmission Line - Pole/Tower | Replace | Upgrade/Retrofit | NA | Asset Condition | Age/Condition | NA | NA | 2025-05-23 | 50; 50 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | TBD |  | 0.32 | NA | 69 | NA | 1.1 | 2022-2728 | QBL0098 | 1 | 20126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2022-04-05; 2024-06-24;2016-08-15 | Work Order Authorization | 2019 | NA | FALSE | NA | NA | NA | FALSE | TBD | TBD | Exempted | NA | CPUC | NA | Exempt | NA | To be Filed | NA | Operational | NA | 2022-05-25 | 2017-12-31 | 2024-08-03 | Permitting | Project Design | FALSE | 396.5096 | NA ¦ NA | 5659.8408 | 261.3795 | 553.4478 | 582.1503 | 2449.289 | 161.8107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2024 ¦ 2025 | 0 | 0 | 0 | 5498.03 | 161.8107 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
126 | CMP_T0_L3_TL618/619_Z579013X_12 |  |  | San Diego, San Diego | Remediate CMP Issues | Transmission Line - Pole/Tower | Replace | Upgrade/Retrofit | NA | Asset Condition | Age/Condition | NA | NA | 2025-02-15 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 1 | NA | 69 | NA | 1.1 | 2024-3689 | QBL0098 | 1 | 20126 | 2025-12-10 ¦ NA ¦ QBL0092 ¦ NA | TRUE | 06-24-2025;10-7-2015;8-27-2015;08-31-2015 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | To be Filed | NA | Construction (under 10%) | NA | 2025-04-30 | 2018-12-31 | 2026-04-15 | Permitting | Multiple Options[See Notes] | FALSE | 179.998 | NA ¦ NA | 1737.3176 | -22.8419 | 3.7452 | 1171.4526 | 531.7255 | 8.2416 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 22.1527 | 3.7452 | 1171.4526 | 531.7255 | 8.2416 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [Reason for Change in In-Service Date] Permitting, material and access issues all caused delays on this project. New access roads and work pads needed to be established.
127 | CMP_T0_LX_TL687_GROUP03_NONTT |  |  | Borrego Springs, San Diego | Remediate CMP Issues in the Non-HFTD Zone | Transmission Line - Pole/Tower | Replace | NA | NA | Asset Condition | Age/Condition | NA | NA | 2025-02-10 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 1.2 | NA | 69 | NA | 1.1 | 2023-3531 | QBL0098 | 1 | 20126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-09-25 | Work Order Authorization | 2024 | NA | FALSE | NA | NA | NA | FALSE | CEQA Final Published | NA | Exempted | NA | CPUC | NA | Exempt | NA | To be Filed | NA | Operational | NA | 2024-07-11 | 2024-10-02 | 2024-11-21 | Outage | NA | FALSE | 2159.3121 | NA ¦ NA | 1038.2124 | 0 | 0 | 72.539 | 1199.7895 | -234.1161 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2024 ¦ 2025 | 0 | 0 | 0 | 1272.3285 | -234.1161 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
128 | CMP_T0_LX_TL688 Z214887_TT15487 |  |  | Escondido, San Diego | Remediate CMP Issues in the Non-HFTD Zone | Transmission Line - Pole/Tower | Replace | NA | NA | Asset Condition | Age/Condition | NA | NA | 2025-05-14 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.2 | NA | 69 | NA | 1.1 | 2021-2354 | QBL0098 | 1 | 20126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-10-10; 2021-08-16 | Work Order Authorization | 2022 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | CPUC | NA | Exempt | NA | To be Filed | NA | Operational | NA | 2024-05-30 | 2021-12-31 | 2024-11-24 | Permitting | Project Design | FALSE | 361.0344 | NA ¦ NA | 1249.2431 | 14.9283 | 65.4007 | 372.2749 | 514.5565 | 282.0827 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2024 ¦ 2025 | 0 | 0 | 0 | 967.1604 | 282.0827 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
129 | CMP_T0_L2_664_Z96050_NON_TT |  |  | San Diego, San Diego | CMP_T0_Lx_TL664_Group03_NonTT | Transmission Line - Pole/Tower | Replace | NA | NA | Asset Condition | Age/Condition | NA | NA | 2025-08-27 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.3 | NA | 69 | NA | 1.1 | 2021-2545 | QBL0098 | 1 | 20126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2021-12-06 | Work Order Authorization | 2022 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | CPUC | NA | Exempt | NA | To be Filed | NA | Operational | NA | 2022-10-20 | 2023-02-14 | 2023-11-12 | Outage | Project Design | FALSE | 361.3033 | NA ¦ NA | 1102.3134 | 0 | 350.8379 | 512.586 | 142.1545 | 96.735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2024 ¦ 2025 | 0 | 0 | 0 | 1005.5784 | 96.735 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
130 | CMP_T0_L2_TL688 (99901)_Z214887 |  |  | Escondido, San Diego | Remediate CMP Issues in the Non-HFTD Zone | Transmission Line - Pole/Tower | Replace | NA | NA | Asset Condition | Age/Condition | NA | NA | 2025-05-14 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.1 | NA | 69 | NA | 1.1 | 2022-2639 | QBL0098 | 1 | 20126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-03-06 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | CPUC | NA | Exempt | NA | To be Filed | NA | Operational | NA | 2024-05-29 | 2021-12-31 | 2024-11-24 | Permitting | Material | FALSE | 80 | NA ¦ NA | 1155.0864 | 142.0736 | 289.7707 | 101.3229 | 351.3769 | 63.4031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2024 ¦ 2025 | 0 | 0 | 0 | 1091.6833 | 63.4031 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
131 | CMP_T0_L2_TL13834_Z128033_13605 |  |  | Laguna Niguel, Orange | Remediate CMP Issues in the Non-HFTD Zone | Transmission Line/Substation | Replace | NA | NA | Asset Condition | Age/Condition | NA | NA | 2025-05-14 | 29; 23; 52 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.2 | NA | 138 | NA | 1.1 | TL13834 Z128033 | QBL0098 | 1 | 20126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2018-03-11 | Work Order Authorization | 2019 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | CPUC | NA | Exempt | NA | To be Filed | NA | Operational | NA | 2023-07-19 | 2020-12-31 | 2024-10-02 | Permitting | Project Design | FALSE | 9.999 | NA ¦ NA | 1574.8578 | 132.2845 | 216.1809 | 63.9558 | 757.01 | 48.8524 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2024 ¦ 2025 | 0 | 0 | 0 | 1526.0054 | 48.8524 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
132 | CMP_T0_L2_TL684_Z210594X_NON_TT |  |  | San Marcos, San Diego | TL684 Group 01- CMP- Non-TT (Pole Loading) | Transmission Line - Pole/Tower | Replace | NA | NA | Asset Condition | Age/Condition | NA | NA | 2025-02-20 | 46; 46; 34; 40; 40; 40 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.3 | NA | 69 | NA | 1.1 | TL684 Group 01 | QBL0098 | 1 | 20126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-09-27 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | CPUC | NA | Exempt | NA | To be Filed | NA | Operational | NA | 2021-03-01 | 2021-12-31 | 2020-12-13 | Permitting | NA | FALSE | 999.999 | NA ¦ NA | 1055.8794 | 427.1028 | 45.6275 | 30.9775 | 85.4049 | 23.5556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 870.3139 | 45.6275 | 30.9775 | 85.4049 | 23.5556 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
133 | [Programmatic] Transmission CMP HFTD |  |  | Multiple | Transmission CMP HFTD | Transmission Line - Pole/Tower | Replace | NA | NA | Asset Condition | Age/Condition | NA | NA | NA | NA | NA | NA | NA | Tier 2 ¦ Tier 3 | FALSE ¦ FALSE ¦ FALSE | FALSE | Individual Project Review Required |  | NA | NA | Multiple | NA | 1.1 | Multiple | QBL0092 | 378 | 20127 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-12-11 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | TBD | TBD | Exempted | NA | CPUC | NA | Exempt | NA | To be Filed | NA | Operational | NA | NA | 2024-12-31 | 2021-12-18 | NA | NA | TRUE | NA | NA ¦ NA | 237747.1205 | 10834.17 | 13370.509 | 15424.2958 | 10592.9116 | 12794.6104 | 7337.5847 | 11818.0783 | 11367.8493 | 12071.7705 | 12855.3226 | 12715.9774 | 5401.006 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 ¦ 2026 | 10686.1059 | 11193.4569 | 16820.15 | 11242.4118 | 7673.3662 | 11507.9005 | 0% | NA ¦ NA | 3.3 | NA | 13.55% | 86.45%
134 | CMP_T3_L3_TL50003_Z123862X_1498 |  |  | San Diego, San Diego | Remediate CMP Issues | Transmission Line - Other Equipment | Replace | NA | NA | Asset Condition | Age/Condition - Insulator Replacement - Wood | NA | NA | 2025-07-05 | 10 | NA | NA | NA | Tier 3 | TRUE ¦ FALSE ¦ FALSE | FALSE | NA |  | 6 | NA | 500 | NA | 1.1 | TL50003 Group 01 | QBL0092 | 1 | 20127 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-12-05 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | To be Filed | NA | Operational | NA | 2021-08-30 | 2021-11-03 | 2021-12-18 | Outage | NA | FALSE | 2255.5422 | NA ¦ NA | 1415.0222 | 1215.4861 | 87.6968 | 111.5707 | 0 | 0.2686 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2022 ¦ 2023 ¦ 2025 | 0 | 1303.183 | 111.5707 | 0 | 0.2686 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0%
135 | CMP_T0_L3_TL13834_Z29678_10182 |  |  | San Juan Capistrano, Orange | Remediate CMP Issues | Transmission Line - Pole/Tower | Replace | NA | NA | Asset Condition | Age/Condition | NA | NA | 2025-05-14 | 51 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.1 | NA | 138 | NA | 1.1 | TL13834 Z29678 | QBL0092 | 1 | 20127 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2014-09-10 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | To be Filed | NA | Operational | NA | 2021-12-01 | 2019-03-18 | 2022-10-19 | Permitting | NA | FALSE | 80 | NA ¦ NA | 1221.0289 | 104.0399 | 460.2218 | 365.1485 | 63.1036 | -17.1708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2023 ¦ 2024 ¦ 2025 | 0 | 0 | 1175.096 | 63.1036 | -17.1708 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
136 | CMP_T0_L2_TL694_Z317855_10167 |  |  | Oceanside, San Diego | Remediate CMP Issues | Transmission Line - Pole/Tower | Replace | NA | NA | Asset Condition | Age/Condition | NA | NA | 2025-01-30 | 38 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.1 | NA | 69 | NA | 1.1 | TL694 Z317855 | QBL0092 | 1 | 20127 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2018-03-09 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | To be Filed | NA | Operational | NA | 2021-12-01 | 2020-12-31 | 2021-10-20 | Permitting | Land Rights | FALSE | 9.999 | NA ¦ NA | 1517.6998 | 125.2839 | 215.0283 | 753.0893 | 126.6958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2023 ¦ 2024 | 0 | 0 | 1391.004 | 126.6958 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
137 | CMP_T0_L2_TL23010/02_Z223661_TT |  |  | San Diego, San Diego | Remediate CMP Issues in the HFTD Zone (Tier 2 & Tier 3) | Transmission Line - Conductor | Upgrade/Retrofit | NA | NA | Asset Condition | Age/Condition | NA | NA | 2025-01-05 | NA | NA | NA | NA | Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 0.3 | NA | 230 | NA | 1.1 | TL23002 Z223661 | QBL0092 | 1 | 20127 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-06-17 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | To be Filed | NA | Operational | NA | 2024-05-15 | 2020-12-31 | 2024-12-22 | Multiple Options[See Notes] | NA | FALSE | 999.999 | NA ¦ NA | 1811.5468 | 481.4532 | -246.0084 | 1041.3942 | 443.8809 | 76.0594 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2023 ¦ 2024 ¦ 2025 | 0 | 0 | 1291.6065 | 443.8809 | 76.0594 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0% | [Reason for Change in In-Service Date] Permitting, Design delays, Constructuability constraints.
138 | ET/OH&UG MISC CONST INST/RFS |  |  | Multiple | Remediate CMP Issues | Transmission Line - Pole/Tower | Replace | NA | NA | Asset Condition | Age/Condition | NA | NA | NA | NA | NA | NA | NA | Tier 2 ¦ Tier 3 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69 ¦500 | NA | 1.1 | TL627 Z971741, Z971739 | QBL0092 | 1 | 20127 | 2025-12-10 ¦ NA ¦ NA ¦ NA | TRUE | 2025-01-01 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | To be Filed | NA | Operational | NA | 2020-10-16 | 2024-12-31 | 2020-10-16 | NA | NA | FALSE | NA | NA ¦ NA | 7699.5732 | 398.5445 | 175.5652 | 453.7483 | 146.8314 | 6.8311 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 398.5445 | 175.5652 | 453.7483 | 146.8314 | 6.8311 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 13.55% | 86.45%
139 | [Programmatic] Overhead System Traditional Hardening |  |  | Multiple | This program (i.e., many projects) focuses on projects that replace OH Distribution system in fire prone areas including HFTD Tier 2, Tier 3, and Wildland Urban Interface. In some cases the distribution lines are underbuilt on transmission structures and require some amount of FERC spend. | Other | Replace | NA | NA | Wildfire Mitigation | Line Reconductoring | NA | NA | NA | NA | NA | NA | NA | Tier 2 ¦ Tier 3 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | NA | NA | Multiple | Multiple | 1.2 | Multiple | QBL0118 | 350 | 20284 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2021-01-21 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Construction (25%-50%) | NA | Multiple | Multiple | Multiple | NA | NA | FALSE | NA | NA ¦ NA | 3171.8162 | 358.0998 | 133.5155 | 42.6517 | 52.4895 | 14.5574 | 0.84745 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 924.6159 | 124.5997 | 50.8098 | 16.2163 | 25.7769 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
140 | FIRE RISK MITIGATION(FIRM) CWIP |  |  | San Diego, San Diego | Electric System Hardening program focused on the replacement of wood poles and bare conductor with weathering steel poles and new bare conductor on our 12 kV system, and in some cases includes some underbuilt distribution lines on transmission. | Other | Replace | NA | NA | Wildfire Mitigation | Line Reconductoring | NA | NA | NA | NA | NA | NA | NA | Tier 2 ¦ Tier 3 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | NA | NA | 12 | NA | 1.2 | NA | QBL0118 | 1 | 20284 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-08-26 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Construction (25%-50%) | NA | 2025-01-01 | 2020-12-31 | 2025-01-01 | Weather | Weather | FALSE | 24956.77 | NA ¦ NA | 3550.4199 | 1110.6252 | 824.0799 | 293.8148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2023 | 0 | 0 | 3550.4199 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [Reason for Change in In-Service Date] This is a program with a large quantity of projects included
141 | [Programmatic] Overhead System Covered Conductor |  |  | Multiple | Electric System Hardening program focused on the replacement of wood poles and bare conductor with weathering steel poles and covered conductor on our 12 kV system, and in some cases includes some underbuilt distribution lines on transmission. | Other | Replace | NA | NA | Wildfire Mitigation | Line Reconductoring | NA | NA | NA | NA | NA | NA | NA | Tier 2 ¦ Tier 3 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | NA | NA | Multiple | Multiple | 1.2 | Multiple | QBL0117 | 10 | 20285 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-12-16 | Work Order Authorization | 2021 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Construction (25%-50%) | NA | Multiple | Multiple | Multiple | NA | NA | FALSE | NA | NA ¦ NA | 567.1225 | 26.183 | 140.9086 | 203.2484 | 124.4595 | 203.1068 | 0 | 0 | 0 | 0 | 0 | 0 | 185.2081 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 28.7601 | 134.7849 | 164.8418 | 139.6661 | 44.6453 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
142 | FIRM COVERED CONDUCTOR CWIP |  |  | San Diego, San Diego | Electric System Hardening program focused on the replacement of wood poles and bare conductor with weathering steel poles and covered conductor on our 12 kV system, and in some cases includes some underbuilt distribution lines on transmission. | Other | Replace | NA | NA | Wildfire Mitigation | Line Reconductoring | NA | NA | NA | NA | NA | NA | NA | Tier 2 ¦ Tier 3 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | NA | NA | 12 | NA | 1.2 | NA | QBL0117 | 1 | 20285 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-09-17 | Work Order Authorization | 2021 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Construction (25%-50%) | NA | NA | 2025-12-31 | 2025-12-31 | NA | NA | FALSE | 306.6309 | NA ¦ NA | 3207.8054 | 220.8903 | 515.3381 | 651.7329 | 1023.953 | 651.362 | 136.5962 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2025 | 0 | 0 | 0 | 0 | 3207.8054 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
143 | [Programmatic] Drone Assessments |  |  | Multiple | The project was focused on flying and assessing all structures within the HFTD (Tier 2) with the purpose of mitigating any fire-related issues. | Other | Replace | NA | NA | Wildfire Mitigation | Fire Protection | NA | NA | NA | NA | NA | NA | NA | Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | Multiple | NA | 1.2 | Multiple | QBL0124 | 4 | 20286 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-12-17 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | NA | NA | NA | NA | NA | NA | To be Filed | NA | Operational | NA | NA | 2024-12-31 | Multiple | NA | NA | TRUE | NA | NA ¦ NA | 890.2405 | 49.4976 | 0.0020165 | 0.61774 | 661.1775 | 92.5925 | 51.7836 | 86.3532 | 0 | 0 | 0 | 0 | 5.5434 | NA | NA | 2022 ¦ 2023 ¦ 2024 ¦ 2025 ¦ 2026 | 0 | 49.4996 | 0.48685 | 441.868 | 306.4895 | 91.8965 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
144 | DRONE INVESTIGATION ASSESSMENT |  |  | Multiple | Perform drone inspections for all of Tier 2 HFTD and higher risk WUI areas and complete follow-up repairs of any infractions identified. | Other | Replace | Replace | NA | Wildfire Mitigation | Age/Condition | NERC CIP Compliance | NERC CIP Compliance | NA | NA | NA | NA | NA | Tier 2 ¦ Tier 3 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | NA | NA | NA | NA | 1.2 | NA | QBL0124 | 1 | 20286 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-02-14 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Construction (over 75%) | NA | NA | 2023-12-31 | 2023-12-31 | NA | NA | FALSE | 818.022 | NA ¦ NA | 3269.0617 | 773.2967 | 1314.0803 | 843.8187 | -189.2602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2024 | 0 | 0 | 0 | 3269.0617 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] NA
145 | [Programmatic] Electric Distribution Tools & Equipment |  |  | NA | This blanket budget provides funding for new tools and equipment required by field personnel to inspect, operate and maintain the electric distribution system. | Other | New | NA | NA | Safety | Automation | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | Multiple | NA | 1.3 | Multiple | QB00028 | 10 | 206 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2025-01-24 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | NA | NA | To be Filed | NA | Operational | NA | NA | 2024-12-31 | Multiple | NA | NA | TRUE | NA | NA ¦ NA | 4783.6387 | 0.50352 | 0 | 0 | -0.0052359 | 82.4661 | 82.4661 | 364.271 | 377.0096 | 390.2116 | 403.8678 | 413.9623 | 0 | NA | NA | 2021 ¦ 2024 ¦ 2025 ¦ 2026 | 40.0083 | 0 | 0 | -0.0052359 | 58.3985 | 370.3427 | 0% | NA ¦ NA | 1.5 | NA | 0% | 100%
146 | INTERIM CAPITAL TOOLS C&O |  |  | NA | Provides the necessary tools and equipment to economically and safely inspect, operate and maintain the electric distribution facilities. Failure to replace outdated, old or worn-out tools will result in decreased crew productivity, increase accident frequency and increase system failure. | Other | Upgrade/Retrofit | Multiple Options [See Notes] | NA | Safety | 3rd Party Damage | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | Individual Project Review Required |  | NA | NA | NA | NA | 1.3 | NA | QB00028 | 1 | 206 | NA ¦ NA ¦ NA ¦ NA | TRUE | 0 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | NA | NA | To be Filed | NA | Operational | NA | NA | 2024-12-31 | Monthly | NA | NA | FALSE | 100 | NA ¦ NA | 3304.7113 | 547.5016 | 196.3277 | 171.4613 | 189.0856 | 44.0829 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 547.5016 | 196.3277 | 171.4613 | 189.0856 | 44.0829 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [Project Description - Action Taken (2)] The main purpose of the project is to improve safety so multiple options are taken.
147 | [Programmatic] ELEC TRANS SMALL RELIABILITY - HFTD |  |  | San Diego, San Diego | This budget code is all Electric Transmission projects under $4M, including shared equipment on the structures for both Transmission and Distribution. The funds are applied to the infrastructure to meet SDGE’s obligation to increase safety and reliability of the electric system. Budget includes proactive system upgrades and reactive projects that include poles, insulators, conductor and other electric infrastructure when reliability issues are identified in the HFTD. | Transmission Line - Multiple | Replace | Upgrade/Retrofit | NA | Reliability | T-Line Reliability | NA | NA | NA | NA | NA | NA | NA | Tier 2 ¦ Tier 3 | FALSE ¦ FALSE ¦ FALSE | FALSE | Individual Project Review Required |  | NA | NA | Multiple | NA | 1.2 | Multiple | QBL0125 | 124 | 21134 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-12-16 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | TBD | TBD | Exempted | NA | CPUC | NA | NA | NA | To be Filed | NA | Operational | NA | NA | 2024-12-31 | Multiple | NA | NA | TRUE | NA | NA ¦ NA | 298184.27 | 2868.6125 | 6998.5762 | 9969.4542 | 8975.7385 | 14248.9554 | 10106.7823 | 14259.1642 | 16858.225 | 18560.6266 | 20713.8526 | 23082.3567 | 9407.5811 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 ¦ 2026 | 1938.3898 | 5651.5666 | 7738.8713 | 12527.6416 | 5797.2865 | 10106.7823 | 0% | NA ¦ NA | 1.8 | NA | 13.55% | 86.45% | [CPUC Status] permitting may vary based on projects under this programmatic budget
148 | REL_T2_TL678_Z104100_W2S |  |  | San Diego, San Diego | 3 poles in HFTD 2 to be replaced from wood to steel, and a total of 0.247 miles of existing 636 ACSS/AW to be reconductored. Structure #s: Z104100 636 ACSS/AW Z170670 636 ACSS/AW Z75086 636 ACSS/AW ​​ | Transmission Line - Pole/Tower | Replace | NA | NA | Reliability | Age/Condition - Replace Wood Poles | NA | NA | 2025-02-25 | 32; 37; 48; 55; 32; 55 | NA | NA | NA | Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 0.3 | NA | 69 | NA | 1.2 | 2020-0283 | QBL0125 | 1 | 21134 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-08-05; 2022-10-04 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | To be Filed | NA | Engineering more than 50% complete | NA | 2025-05-05 | 2024-12-30 | 2025-06-02 | Prioritization | NA | FALSE | 1746.2787 | NA ¦ NA | 1540.3325 | 331.3782 | 234.8051 | 274.5971 | 495.1763 | 95.7082 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 331.3782 | 234.8051 | 274.5971 | 495.1763 | 95.7082 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
149 | W2S_T2_TL6917_4 STRUCTURES |  |  | Camp Pendleton, San Diego | 6 poles in HFTD 2 to be replaced from wood to steel, and a total of 0.416 miles of existing 1/0 CU B.S. & 394.5 5005 AL to be reconductored. Structure #s: Z21282 1/0 CU B.S. Z22190 394.5 5005 AL Z22191 394.5 5005 AL Z22192 394.5 5005 AL Z22193 394.5 5005 AL Z22194 394.5 5005 AL ​​ | Transmission Line - Pole/Tower | Replace | NA | NA | Reliability | Age/Condition - Replace Wood Poles | NA | NA | 2025-01-12 | 30; 30; 70; 30; 20 | NA | NA | NA | Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 0.42 | NA | 69 | NA | 1.2 | 2020-0285 | QBL0125 | 1 | 21134 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-08-05; 2021-11-04; 2021-11-04 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | To be Filed | NA | Operational | NA | 2023-12-11 | 2024-12-30 | 2023-12-16 | NA | NA | FALSE | 2013.332 | NA ¦ NA | 1430.5058 | 198.2888 | 243.3452 | 864.1304 | -33.7359 | 79.3878 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2024 ¦ 2025 | 0 | 0 | 0 | 1351.118 | 79.3878 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
150 | REL_TL621_Z118874 W2S |  |  | San Diego, San Diego | 2 Poles in HFTD 2 to be replaced from wood to steel, and a total of 0.0356 miles (188’) of existing 1033.5 ACSR/AW. Structure #: Z118874 1033.5 ACSR/AW Dead-End | Transmission Line - Pole/Tower | Replace | NA | NA | Reliability | Age/Condition - Replace Wood Poles | NA | NA | 2025-02-08 | 21 | NA | NA | NA | Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 0.1 | NA | 69 | NA | 1.2 | 2021-0382 | QBL0125 | 1 | 21134 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2021-04-07; 2022-10-04;2021-11-23 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | 2023-11-03 | Approved | 2023 | Permitting | NA | 2025-07-17 | 2025-12-31 | 2026-05-13 | Prioritization | NA | FALSE | 546.3001 | NA ¦ NA | 1431.6093 | 50.6354 | 177.5671 | 633.987 | 636.9557 | -67.536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2024 ¦ 2025 | 0 | 0 | 0 | 1298.4845 | 133.1248 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
151 | REL_TL632_Z118872_W2S |  |  | San Diego, San Diego | 1 Pole in HFTD to be replaced from wood to steel | Transmission Line - Pole/Tower | Replace | NA | NA | Reliability | Age/Condition - Replace Wood Poles | NA | NA | 2025-02-11 | 21 | NA | NA | NA | Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | TBD |  | 0.1 | NA | 69 | NA | 1.2 | 2021-0387 | QBL0125 | 1 | 21134 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2021-11-23; 2021-04-07; 2022-10-04 | Work Order Authorization | 2022 | NA | FALSE | NA | NA | NA | FALSE | TBD | TBD | Exempted | NA | CPUC | NA | Exempt | 2023-08-15 | Approved | 2023 | Engineering more than 50% complete | NA | 2026-03-27 | 2025-12-31 | 2026-07-17 | Prioritization | NA | FALSE | 546.149 | NA ¦ NA | 1259.4233 | 41.7975 | 172.7752 | 438.0483 | 516.4827 | 90.3196 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2024 ¦ 2025 | 0 | 0 | 0 | 1169.1037 | 90.3196 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
152 | REL_TL6924 W2S 3 STRUCTURES |  |  | San Diego, San Diego | 4 Poles in HFTD 2 to be replaced from wood to steel, and a total of 0.1591 miles of existing 900 ACSS/AW. | Substation - Multiple | New | New | NA | Reliability | 3rd Party Damage | NERC CIP Compliance | NERC CIP Compliance | 2025-01-17 | NA | NA | NA | NA | Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.3 | NA | 69 | NA | 1.2 | 2021-0388 | QBL0125 | 1 | 21134 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2021-04-07 | Work Order Authorization | 2021 | NA | FALSE | NA | NA | NA | FALSE | PEA Deemed Complete | NA | Exempted | NA | CPUC | NA | Exempt | NA | To be Filed | NA | Planning | NA | 2023-12-16 | 2025-03-24 | 2025-03-24 | Weather | Weather | FALSE | 685.7119 | NA ¦ NA | 1042.072 | 106.6484 | 239.9213 | 492.6213 | 204.0273 | -1.1464 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2023 ¦ 2024 ¦ 2025 | 0 | 0 | 839.1911 | 204.0273 | -1.1464 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
153 | W2S_T2_TL684_3 STRUCTURES |  |  | San Marcos, San Diego | 3 poles in HFTD 2 to be replaced from wood to steel, and a total of 0.405 miles of existing 1033.5 ACSR/AW to be reconductored. | Substation - Multiple | New | New | NA | Reliability | 3rd Party Damage | NERC CIP Compliance | NERC CIP Compliance | 2025-02-20 | 25 | NA | NA | NA | Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.4 | NA | 69 | NA | 1.2 | 2020-0284 | QBL0125 | 1 | 21134 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-08-07; 2021-11-04 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | PEA Deemed Complete | NA | Exempted | NA | CPUC | NA | Exempt | NA | To be Filed | NA | Planning | NA | 2024-05-06 | 2025-08-22 | 2025-01-30 | Weather | Weather | FALSE | 1740.62 | NA ¦ NA | 1178.9129 | 147.0336 | 162.0479 | 227.7163 | 315.671 | 241.0102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2025 | 0 | 0 | 0 | 0 | 1178.9129 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
154 | [Programmatic] ELEC TRANS SMALL RELIABILITY – non HFTD |  |  | Multiple | This budget code is all Electric Transmission projects under $2M, including shared equipment on the structures for both Transmission and Distribution. The funds are applied to the infrastructure to meet SDGE’s obligation to increase safety and reliability of the electric system. Budget includes proactive system upgrades and reactive projects that include poles, insulators, conductor and other electric infrastructure when reliability issues are identified in the non-HFTD. | Transmission Line - Multiple | Replace | Upgrade/Retrofit | NA | Reliability | T-Line Reliability | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | NA | NA | 4.1 | Multiple | QBL0126 | 177 | 21135 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-12-16 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | NA | NA | To be Filed | NA | Operational | NA | NA | 2024-12-31 | Multiple | NA | NA | TRUE | NA | NA ¦ NA | 319984.0507 | 3836.8366 | 6757.0041 | 11161.8195 | 13153.6653 | 15269.3406 | 9427.7934 | 15906.7639 | 17175.7478 | 19366.86 | 21501.5259 | 23883.755 | 17662.3965 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 ¦ 2026 | 2500.2053 | 3563.7698 | 6604.1633 | 14627.1121 | 5221.0191 | 13102.4132 | 0% | NA ¦ NA | 5.1 | NA | 0% | 0%
155 | 5 RELIABILITY (NON CMP) POLES |  |  | Vista, San Diego | TL680B-Z218305, Z218306, Z218309, Z218301, Z115895. | Transmission Line - Pole/Tower | Replace | NA | 2988970 | Reliability | Age/Condition - Replace Wood Poles | NA | NA | 2025-02-11 | 50.7 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.5 | NA | 69 | NA | 4.1 | TL680B Group-Fndtn | QBL0126 | 1 | 21135 | 2025-12-10 ¦ Multiple ¦ NA ¦ NA | TRUE | 2020-12-11 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | To be Filed | NA | Operational | NA | 2020-06-28 | 2022-12-31 | 2021-06-01 | NA | NA | FALSE | 2762.0811 | NA ¦ NA | 1555.2433 | 67.8536 | 5.1993 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2022 | 0 | 1555.2433 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [Utility Unique ID #1(Less Specific)] TL612_TL604_Z279897 , TL680B Group-Fndtn
156 | REL_TL612_TL604_Z279897 |  |  | San Diego, San Diego | FTD to be replaced from wood to steel | Transmission Line - Pole/Tower | Replace | NA | NA | Reliability | Age/Condition - Wood Pole Reframe | NA | NA | 2025-02-15 | 22 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | TBD |  | 0.1 | NA | 69 | NA | 4.1 | 2021-0406 | QBL0126 | 1 | 21135 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2022-08-02 | Work Order Authorization | 2023 | NA | FALSE | NA | NA | NA | FALSE | TBD | TBD | Exempted | NA | NA | NA | Exempt | NA | To be Filed | NA | Engineering more than 50% complete | NA | 2026-01-20 | 2023-12-31 | 2025-12-24 | Prioritization | NA | FALSE | 2143.4324 | NA ¦ NA | 1027.1049 | 0 | 20.4055 | 479.0869 | 278.9653 | 110.0218 | 24.7937 | 52.998 | 57.8943 | 2.9393 | 0 | 0 | 888.4795 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
157 | REL_T0_TL615_Z730769 |  |  | San Diego, San Diego | The purpose of the TL615 REL Project is to replace structures Z730769, Z730764, Z730774, from wood to steel. Replacing existing Z730769 with a new 70’-H3 Galvanized SW pole • Replacing existing Z730764 with a new 70’-H3 Galvanized SW pole • Replacing existing Z730774 with a new 75’-H3 Galvanized SW pole • Replacing existing Z730770 with a new 80’-H3 Galvanized SW pole • Replacing existing pole top configuration on Z730773 with current standard. • Retaining Wall Scope: o Remove a portion of the existing masonry retaining wall, concrete foundation, and sidewalk at (2) locations o Install new concrete masonry retaining wall and concrete foundation set back from existing wall at (2) locations | Transmission Line - Pole/Tower | Replace | Upgrade/Retrofit | N/A | Reliability | Age/Condition | NERC CIP Compliance | NERC CIP Compliance | 2025-02-11 | 57; 57; 57; 58 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | TBD |  | 0.32 | NA | 69 | NA | 4.1 | 2021-2501 | QBL0126 | 1 | 21135 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2021-11-19 | Work Order Authorization | 2022 | NA | FALSE | NA | NA | NA | FALSE | TBD | TBD | Other [See Notes] | EIS | CPUC | NA | N/A | N/A | To be Filed | N/A | Planning | NA | 2025-03-24 | 2024-02-04 | 2025-04-02 | Prioritization | Other[See Notes] | FALSE | 1101.2271 | NA ¦ NA | 1050.6964 | 12.7453 | 144.7113 | 203.6647 | 155.6819 | 533.8932 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2023 ¦ 2024 ¦ 2025 | 0 | 0 | 361.1213 | 155.6819 | 533.8932 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [Reason for Change in In-Service Date] Budget Constraints
158 | [Programmatic] TRANSMISSION CONSTRUCTION & MAINT |  |  | Multiple | Transmission jobs in the HFTD to comply with SDG&Es obligation to serve and meet safety requirements. Most of the activities that fall under this blanket budget are necessary to comply with Federal, State, and Local regulations. Activities include poles that need to be replaced due to reaching life expectancy, capital repairs related to inspections (visual, infrared, LiDAR, etc.), and emergency situations. This work is scheduled and managed by Transmission, Construction & Maintenance. | Transmission Line - Multiple | Upgrade/Retrofit | Replace | NA | Safety | Age/Condition | NA | NA | NA | NA | NA | NA | NA | Tier 2 ¦ Tier 3 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | NA | NA | Multiple | NA | 1.1 | Multiple | QBL0127 | 403 | 21136 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-12-16 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | NA | NA | To be Filed | NA | Operational | NA | NA | NA | Multiple | NA | NA | TRUE | NA | NA ¦ NA | 127808.6688 | 887.1519 | 1638.4009 | 3392.394 | 4010.892 | 5973.2209 | 4452.2727 | 6706.9448 | 7344.9782 | 8117.1272 | 9027.5947 | 10026.1811 | 4409.9364 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 ¦ 2026 | 1263.927 | 748.7844 | 2830.8089 | 3867.0768 | 2781.5262 | 4837.1218 | 0% | NA ¦ NA | 1.3 | NA | 13.55% | 86.45% | [CPUC Status] NA
159 | 2022 CIVIL ENG CAPITAL PROJECTS |  |  | San Diego, San Diego | The purpose of this work is mandatory Environmental Site restoration. | Other - Civil | Upgrade/Retrofit | NA | NA | Safety | Construct Roads/Gates/Culverts | NA | NA | NA | 29 | NA | NA | NA | Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | NA | NA | 1.1 | 2022-3126 | QBL0127 | 1 | 21136 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2022-11-17 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | To be Filed | NA | Operational | NA | 2022-11-15 | NA | 2023-06-11 | NA | NA | FALSE | 1606.935 | NA ¦ NA | 1718.411 | 0 | 1535.07 | 197.8079 | -20.2609 | 5.794 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2024 ¦ 2025 | 0 | 0 | 0 | 1712.617 | 5.7941 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] NA
160 | [Programmatic] HATS |  |  | San Diego, San Diego | This project will facilitate ongoing compliance and safe and efficient operations and maintenance of the transmission system by addressing helicopter access constraints and supporting the latest work practices. The project will provide additional Helicopter Access for Transmission Structures (HATS) that currently have helicopter access constraints. | Other | New | NA | NA | Other [See Notes] | Safety - Line Right of Way Access | NA | NA | NA | NA | NA | NA | NA | Tier 1 ¦ Tier 2 ¦ Tier 3 ¦ Zone 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | Multiple | Multiple | 1.3 | Multiple | QBL0130 | 2 | 21146 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2025-04-12 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | Multiple | Multiple | Multiple | NA | NA | FALSE | NA | NA ¦ NA | 0 | 0 | 0 | 0 | 0 | 7915.7995 | 7915.7995 | 0 | 0 | 0 | 0 | 0 | 7915.7995 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | 25.8 | NA | 100% | 0% | [Primary Purpose] Specialized Structure Access
161 | HATS WORK RELEASE 3 |  |  | San Diego, San Diego | Contractor shall provide all services, labor, material, equipment, transportation, supervision, and incidental related work necessary for the installation of two types of helicopter landing facilities at various locations along Company’s 230kV and 500kV transmission system. One type is a Transmission Staging Access Pad (TSAP) which is a level, bare ground area cleared and maintained of vegetation used for intermittent landing of Company or authorized contractor helicopters. The TSAP scope includes ten (10) TSAP locations. The other type is an engineered structural steel helicopter landing platform used for intermittent landing of Company or authorized contractor helicopters (Platform). The Platform scope includes two (2) permanent, engineered structural landing platforms. These facilities are generally located in steep, rugged and mountainous terrain and are necessary due to lack of available roads for vehicle access and will assist in the safe and efficient maintenance and operation of electric transmission facilities. | Other | New | NA | NA | Other [See Notes] | Safety - Line Right of Way Access | NA | NA | NA | NA | NA | NA | NA | Tier 2 ¦ Tier 3 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 230 ¦ 500 | NA | 1.3 | 2022-2623 | QBL0130 | 1 | 21146 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2021-10-23 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2023-07-31 | 2023-12-31 | 2024-07-01 | Construction Delays | NA | FALSE | 12044.5322 | NA ¦ NA | 14634.3646 | 0 | 336.5763 | 12184.1401 | 2078.2014 | 35.4468 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2024 ¦ 2025 | 0 | 0 | 0 | 14598.9178 | 35.4468 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0% | [Primary Purpose] Specialized Structure Access
162 | HATS WORK RELEASE 2 |  |  | San Diego, San Diego | Contractor shall provide all services, labor, material, equipment, transportation, supervision, and incidental related work necessary for the installation of two types of helicopter landing facilities at various locations along Company’s 230kV and 500kV transmission system. One type is a Transmission Staging Access Pad (TSAP) which is a level, bare ground area cleared and maintained of vegetation used for intermittent landing of Company or authorized contractor helicopters. The TSAP scope includes (2) TSAP locations. The other type is an engineered structural steel helicopter landing platform used for intermittent landing of Company or authorized contractor helicopters (Platform). The Platform scope includes seven (7) permanent, engineered structural landing platforms. These facilities are generally located in steep, rugged and mountainous terrain and are necessary due to lack of available roads for vehicle access and will assist in the safe and efficient maintenance and operation of electric transmission facilities. | Other | New | NA | NA | Other [See Notes] | Safety - Line Right of Way Access | NA | NA | NA | NA | NA | NA | NA | Tier 2 ¦ Tier 3 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 230 ¦ 500 | NA | 1.3 | 2022-2622 | QBL0130 | 1 | 21146 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2021-09-08 | Work Order Authorization | 2021 | 2021 | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2021-01-22 | 2021-12-31 | 2022-09-27 | Weather | NA | FALSE | 13068.4013 | NA ¦ NA | 20476.1112 | 11684.9933 | 8457.9153 | 215.5547 | 117.4167 | 0.23123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 11684.9933 | 8457.9153 | 215.5547 | 117.4167 | 0.23123 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0%
163 | HATS Release 4 |  |  | San Diego, San Diego | Contractor shall provide all services, labor, material, equipment, transportation, supervision, and incidental related work necessary for the installation of two types of helicopter landing facilities at various locations along Company’s 230kV/500kV transmission system. One type is a Tower Staging Access Pad (TSAP) which is a level, bare ground area cleared and maintained of vegetation used for intermittent landing of Company or authorized contractor helicopters. The TSAP scope includes eight (8) TSAP locations. The other type is an engineered structural steel helicopter landing platform (Platform or HLP) used for intermittent landing of Company or authorized contractor helicopters. The Platform scope includes six (6) engineered structural landing platforms. These facilities are generally located in steep, rugged and mountainous terrain and are necessary due to lack of available roads for vehicle access and will assist in the safe and efficient maintenance and operation of electric transmission facilities. | Other | New | NA | NA | Other [See Notes] | Safety - Line Right of Way Access | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 230 ¦ 500 | NA | 1.3 | 2024-3824 | QBL0130 | 1 | 21146 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-08-15 | Work Order Authorization | 2024 | 2024 | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2024-10-21 | 2024-12-31 | 2025-08-16 | Weather | NA | FALSE | 1126.3555 | NA ¦ NA | 219570.2142 | 0 | 0 | 35.6888 | 6278.6164 | 18477.6256 | 0 | 15119.9588 | 16761.6567 | 17198.0574 | 17799.9894 | 18422.989 | 0 | NA | NA | 2024 ¦ 2025 | 0 | 0 | 0 | 6314.3052 | 18477.6256 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0%
164 | HATS Release 5 |  |  | San Diego, San Diego | Contractor shall provide all services, labor, material, equipment, transportation, supervision, and incidental related work necessary for the installation of two types of helicopter landing facilities at various locations along Company’s 230kV/500kV transmission system. One type is a Tower Staging Access Pad (TSAP) which is a level, bare ground area cleared and maintained of vegetation used for intermittent landing of Company or authorized contractor helicopters. The TSAP scope includes three (3) TSAP locations. The other type is an engineered structural steel helicopter landing platform (Platform or HLP) used for intermittent landing of Company or authorized contractor helicopters. The Platform scope includes seven (7) engineered structural landing platforms. These facilities are generally located in steep, rugged and mountainous terrain and are necessary due to lack of available roads for vehicle access and will assist in the safe and efficient maintenance and operation of electric transmission facilities. | Other | New | NA | NA | Other [See Notes] | Safety - Line Right of Way Access | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | TBD |  | NA | NA | 69 ¦ 230 ¦ 500 | NA | 1.3 | 2025-4253 | QBL0130 | 1 | 21146 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-08-06 | Work Order Authorization | 2025 | NA | FALSE | NA | NA | NA | FALSE | TBD | TBD | Exempted | Categorical Exclusion | CPUC | CNF, BLM | Exempt | NA | NA [See Notes] | NA | Permitting | NA | 2026-07-06 | 2027-03-12 | 2027-03-12 | NA | NA | FALSE | 769.7092 | NA ¦ NA | 29180.2023 | 0 | 0 | 0 | 19.1756 | 236.3748 | 0 | 2369.1287 | 2514.2485 | 2579.7086 | 2669.9984 | 2763.4484 | 0 | NA | NA | 2024 ¦ 2025 | 0 | 0 | 0 | 19.1756 | 236.3748 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0%
165 | [Programmatic] TCM Non-HFTD |  |  | Multiple | Transmission jobs in the non-HFTD to comply with SDG&Es obligation to serve and meet safety requirements set by General Orders 95,128, and other regulations. Budget provides resources to provide support to reactive issues that arise such as storm, fire and pole car contact. The majority of the activities that fall under this blanket budget are necessary to comply with Federal, State , and Local regulations. Activities include poles that need to be replaced due to deterioration, capital repairs related to inspections (visual, infrared, LiDAR, etc.), and emergency situations. This work is scheduled and managed by Transmission, Construction & Maintenance. | Transmission Line - Multiple | Upgrade/Retrofit | NA | NA | Safety | Construct Roads/Gates/Culverts | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | Multiple | NA | 1.1 | Multiple | QBL0135 | 496 | 21150 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-12-16 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | NA | NA | To be Filed | NA | Operational | NA | NA | 2024-12-31 | Multiple | NA | NA | TRUE | NA | NA ¦ NA | 109231.2818 | 1089.7304 | 800.338 | 2420.8718 | 6750.8275 | 5114.5966 | 2784.9827 | 6951.1338 | 5940.979 | 6615.8831 | 7356.2944 | 8168.3312 | 2119.1015 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 ¦ 2026 | 1657.1346 | 716.1609 | 1201.9266 | 7948.4084 | 2533.6324 | 3798.6656 | 0% | NA ¦ NA | 2.1 | NA | 13.55% | 86.45%
166 | TL676 Z96677 NEW ACCESS RD AND |  |  | San Diego, San Diego | Mobilize, Clear and Grub Pad, Place BMPs Rough Grade, Over Excavate and Compact Pad, Place 9" of Class 2 base, Over excavate and compact Access Rd, Place 9" of class 2 base on road, Form and construct wall footings and CMU wall, Waterproof and Backfill Wall, Construct Brow and Wall ditch, Construct Cross Gutter, Install Rip-rap Dissipater with Filter Fabric, Construct Type D Brow ditch, install Cable railing at CMU wall. Demobilize. | Other - Civil | Upgrade/Retrofit | NA | NA | Safety | Construct Roads/Gates/Culverts | NA | NA | 2025-02-15 | 50 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69 | NA | 1.1 | 2023-3244 | QBL0135 | 1 | 21150 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-01-13 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | To be Filed | NA | Operational | NA | 2023-09-07 | NA | 2023-10-24 | NA | NA | FALSE | 1421.7099 | NA ¦ NA | 1308.0284 | 0 | 0 | 1303.151 | 4.8774 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2023 ¦ 2024 | 0 | 0 | 1303.151 | 4.8774 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] NA
167 | ET/OH CORRECTIVE MAINT PROGRAM |  |  | Multiple | Transmission jobs in the Non-HFTD to comply with SDG&Es obligation to serve and meet safety requirements. Most of the activities that fall under this blanket budget are necessary to comply with Federal, State, and Local regulations. Activities include poles that need to be replaced due to reaching life expectancy, capital repairs related to inspections (visual, infrared, LiDAR, etc.), and emergency situations. This work is scheduled and managed by Transmission, Construction & Maintenance. | Transmission Line - Multiple | Upgrade/Retrofit | Replace | NA | Safety | Age/Condition | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | Multiple | NA | 1.1 | Multiple | QBL0135 | 1 | 21150 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2025-01-01 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | NA | NA | To be Filed | NA | Operational | NA | NA | NA | Multiple | NA | NA | FALSE | NA | NA ¦ NA | 13759.2103 | 6268.6902 | 1463.9724 | 68.5797 | 0.06983 | -68.759 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 6268.6902 | 1463.9724 | 68.5797 | 0.06983 | -68.759 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 13.55% | 86.45% | [Utility Unique ID #1(Less Specific)] 2022-3131 , 2022-2726 , 2022-3133 [CPUC Status] NA
168 | TL23012 Z710036 BRIDGE CROSSING |  |  | San Diego, San Diego | Installing a new bridge to allow SDG&E vehicles to cross over drainage. | Transmission Line - Right of Way | New | New | NA | Safety | 3rd Party Damage | NA | NA | 2025-02-08 | 53 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | TBD |  | 0.41 | NA | 230 | NA | 1.1 | 2022-3123 | QBL0135 | 1 | 21150 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2022-11-08 | Work Order Authorization | 2023 | NA | FALSE | NA | NA | NA | FALSE | TBD | TBD | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2025-01-20 | NA | 2025-05-02 | NA | NA | FALSE | 670.3235 | NA ¦ NA | 1754.3669 | 0 | 7.519 | 75.4535 | 168.9869 | 1502.4075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2025 | 0 | 0 | 0 | 0 | 1754.3669 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0% | [CPUC Status] NA
169 | [Programmatic] Generation Interconnection Projects |  |  | Multiple | This is a blanket authorization for a multitude of CAISO mandated projects. CAISO approval for these projects is made in the form of a Three Party Interconnection Agreement. SDG&E has historically undertaken work for many of these types of projects to enhance and maintain reliability of the transmission grid. These projects are typically Battery Energy Storage (BESS) or other renewable projects from external parties where infrastructure is created in order to connect to SDG&Es grid through genties connecting to one of the companys many existing 69kV and above substations. Typical scope of these projects include the construction of Interconnection Facilities (ICF) which are 100% customer funded as well as Reliability Network Upgrades (RNUs) will be charged to ratepayers. Given the similar nature of many of these projects as well as the fact that the majority of these costs are refundable, our proposal will be to combine the scope of all existing projects with schedules shifting out into next year and future projects into one authorization for 2022 and future years on an annual basis. | Multiple Options [See Notes] | NA | NA | NA | Generator Interconnection | Generation Interconnection | CAISO Requirement | NA | NA | NA | NA | Other - Status Quo | NA | Tier 1 ¦ Tier 2 ¦ Tier 3 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69 - 500 | 69kV - 500kV | 2.1 | Multiple | QBL0141 | 120 | 21156 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-12-09 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | TRUE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Planning | NA | NA | NA | Multiple | NA | NA | TRUE | NA | $96,000 per MW ¦ CAISO GIDAP | 60555.1198 | 5346.4278 | 1256.4033 | -1201.2452 | 6005.0302 | -7923.6089 | -2131.0559 | 26274.4627 | 2554.1732 | 824.9908 | 574.6511 | 408.9588 | 1002.5818 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 ¦ 2026 | 4861.7289 | 1236.0261 | -4348.0554 | -1506.5488 | 2237.2747 | 1517.294 | 0% | NA ¦ NA | 3.63 | NA | 13.55% | 86.45% | [Project Description - What] New & Upgrade [CPUC Status] Multiple Options [Project Description - What] Project scope and description varies for projects; Permitting and CEQA responsibility of 3rd party interconnection customers (not SDG&E); status varies by project
170 | Q1657 Sandpiper Energy Storage Generation interconnection |  |  | Orange County | Sandpiper Energy Storage, LLC, an Interconnection Customer (IC), submitted a completed Interconnection Request (IR) to the California Independent System Operator Corporation (CAISO) to interconnect Sandpiper Storage (Project) to the CAISO Controlled Grid. The Project is a battery energy storage system (BESS) generating facility with a requested net output of 200 MW at the Point of Interconnection (POI). The IC requested that the POI for the Project be at a Talega 138 kV substation. | Substation - Multiple | Upgrade/Retrofit | NA | NA | Generator Interconnection | Generation Interconnection | CAISO Requirement | NA | 2025-10-21 | NA | NA | NA | NA | Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 6.92 | 138 | 138kV | 2.1 | 2021-2433 | QBL0141 | 1 | 21156 | 2025-12-10 ¦ 2022-2757 ¦ NA ¦ NA | TRUE | 2021-10-27 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | TRUE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Construction (50%-75%) | NA | 2024-10-07 | 2023-03-31 | 2025-12-01 | Customer Action | NA | TRUE | 269.8495 | NA ¦ NA | 1493.9032 | 4.3253 | 261.4703 | 437.8069 | 150.0009 | 538.6911 | 60.9015 | 40.7072 | 0 | 0 | 0 | 0 | 1392.2945 | NA | NA | 2026 | 0 | 0 | 0 | 0 | 0 | 1493.9032 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
171 | Q1532 KETTLE SOLAR ONE SANU |  |  | San Diego, San Diego | Generation interconnection project; interconnection customer responsible for design, procurement, and construction of new 138kV Carrizo Gorge switchyard and 138 kV loop in; SDG&E will purchase these high voltage assets from the interconnection customer; SDG&E providing design and construction oversight | Substation - Multiple | New | NA | NA | Generator Interconnection | Generation Interconnection | CAISO Requirement | NA | 2025-05-31 | 33 | NA | NA | NA | Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 1.94 | 138 | 138kV | 2.1 | 2019-0227 | QBL0141 | 1 | 21156 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-10-23 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | TRUE | NA | NA | NA | NA | NA | NA | Advice Letter | 2027-02-16 | To be Filed | TBD | Engineering more than 50% complete | NA | 2025-10-01 | 2022-10-01 | 2026-08-01 | Customer Action | NA | TRUE | 9681 | $11000 ¦ CAISO GIDAP | 10045.2249 | 37.3978 | 104.3318 | 77.6388 | 355.1564 | 233.796 | 438.2799 | 3410.8067 | 5384.8237 | 0 | 0 | 0 | 808.3209 | NA | NA | 2026 | 0 | 0 | 0 | 0 | 0 | 4660.4013 | 0% | 58% ¦ 11200 | NA ¦ NA | NA | 0% | 100% | [Project Description - What] New 138kV switchyard and 138kV loop in
172 | Q1429 MOUNT LAGUNA WIND 2 Generation Interconnection |  |  | San Diego, San Diego | Boulder Brush, LLC Q1429 is a 400MW Generation Facility that requires a new 500kV swithcyard between Suncrest-Ocotillo 500kV line located on the Campo Indian Reservation in Mountain Empire in San Diego County, CA. | Substation - Multiple | New | NA | NA | Generator Interconnection | New Substation | CAISO Requirement | NA | 2025-11-03 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | TBD |  | 0.38 | NA | 500 | 500kV | 2.1 | 2018-3004 | QBL0141 | 1 | 21156 | 2025-12-10 ¦ 2017-0140 ¦ NA ¦ NA | TRUE | 2023-07-24 | Work Order Authorization | 2024 | NA | FALSE | NA | NA | NA | TRUE | TBD | NA | NA | NA | CPUC | NA | Advice Letter | 2025-12-31 | To be Filed | TBD | On Hold | NA | NA | 2029-06-29 | NA | NA | NA | FALSE | 4013.44 | $62000 ¦ CAISO GIDAP | 76910.6463 | 0 | 0 | 1.2724 | 156.8405 | 3.1092 | 0 | 0 | 0 | 0 | 0 | 13535.1679 | 161.2221 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% ¦ 62000 | NA ¦ NA | NA | 100% | 0% | [CPUC Status] NA - On hold due to customer.
173 | Q1670 PEREGRINE RNU |  |  | San Diego, San Diego | The Project is a 200 MW battery energy storage system (“BESS”). The Point of Interconnection is at the 230 kV bus of PTO’s existing Silvergate Substation. Point of Change of Ownership (“POCO”) is located where the IC’s 230 kV generation tie line (“gen-tie”) crosses the vertical plane of the PTO’s property line surrounding the Silvergate Substation. The IC’s Interconnection Facilities include 230 kV underground cable and conduit package from the POCO to the Project’s substation. | Substation - Multiple | Upgrade/Retrofit | NA | NA | Generator Interconnection | Generation Interconnection | CAISO Requirement | NA | 2025-11-20 | 3 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | TBD |  | NA | NA | 230 | 230kV | 2.1 | 2021-2091 | QBL0141 | 1 | 21156 | 2025-12-10 ¦ 2020-0319 ¦ NA ¦ NA | TRUE | 2021-04-28 | Work Order Authorization | 2022 | NA | FALSE | NA | NA | NA | TRUE | NA | NA | NA | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2024-03-11 | 2022-09-30 | 2025-01-03 | Customer Action | NA | FALSE | 359.7892 | NA ¦ NA | 1448.3024 | 18.568 | 284.5556 | 495.2361 | 601.3453 | 48.5973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2025 | 0 | 0 | 0 | 0 | 1448.3024 | 0 | 0% | 64% ¦ 2148 | NA ¦ NA | NA | 100% | 0% | [CPUC Status] NA
174 | Q1810 EAST FIELD ENERGY CNTR PTO NU |  |  | San Diego, San Diego | The project will connect to the PTOs transmission system via the Projects 230kV gen-tie emanation from the Otay Mesa substation. | Substation - Multiple | Upgrade/Retrofit | NA | NA | Generator Interconnection | Generation Interconnection | CAISO Requirement | NA | 2025-11-19 | NA | NA | NA | NA | Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | TBD |  | NA | 32.81 | 230 | 230kV | 2.1 | 2024-3985 | QBL0141 | 1 | 21156 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-05-02 | Work Order Authorization | 2024 | NA | FALSE | NA | NA | NA | TRUE | TBD | NA | NA | NA | CPUC | NA | Exempt | NA | NA [See Notes] | TBD | Engineering less than 50% complete | NA | NA | 2027-08-20 | 2030-03-25 | Customer Action | NA | FALSE | 4897 | NA ¦ NA | 1558.3999 | 0 | 0 | 0 | 25.7254 | 93.9962 | 5.3631 | 11.4639 | 12.5231 | 249.041 | 1118.0572 | 42.23 | 119.7216 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 15% ¦ 844 | NA ¦ NA | NA | 100% | 0% | Project in 30% design. Material lead time delays [CPUC Status] NA
175 | Q2166 UMBRIEL Generation Interconnection |  |  | Imperial County | New 500kV Switchyard supporting 1150 MW solar PV | Substation - Multiple | New | NA | NA | Generator Interconnection | Generation Interconnection | CAISO Requirement | NA | 2025-11-18 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 2.0 | 19.38 | 500 | 500kV | 2.1 | 2023-3247 | QBL0141 | 1 | 21156 | 2025-12-10 ¦ NA ¦ NA ¦ NA | TRUE | 2/7/2024;6/17/2023 | Work Order Authorization | 2024 | NA | FALSE | NA | NA | NA | TRUE | CEQA Draft Published | NA | Exempted | NA | CPUC | NA | Advice Letter | To be filed | To be Filed | TBD | Engineering less than 50% complete | NA | NA | 2028-12-15 | 2031-12-15 | Customer Action | NA | FALSE | 4493.2716 | $177000 ¦ CAISO GIDAP | 118357.1611 | 0 | 0 | 19.755 | 217.715 | 343.0667 | 506.0252 | 543.1393 | 1759.8709 | 2911.9058 | 112052.6481 | 0.50913 | 580.5366 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 71% ¦ 126500 | NA ¦ NA | NA | 100% | 0%
176 | Q1806 Captiva Energy Storage |  |  | San Juan Capistrano, CA | New 138kV Switchyard to support 250MW BESS | Substation - Multiple | New | NA | NA | Generator Interconnection | New Substation | CAISO Requirement | NA | NA | NA | NA | NA | NA | Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 1.0 | 3.06 | 138 | 138kV | 2.1 | 2021-2462 | QBL0141 | 1 | 21156 | 2025-12-10 ¦ 2014-01085-ZZ ¦ NA ¦ NA | TRUE | 2022-06-22 | Work Order Authorization | 2023 | NA | FALSE | NA | NA | NA | TRUE | NA | NA | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Engineering more than 50% complete | NA | 2026-01-01 | 2025-05-20 | 2028-01-31 | Customer Action | NA | FALSE | 48.0858 | $27500 ¦ CAISO | 25975.5661 | 0 | 0.92185 | 0.033307 | 15.9804 | 812.0761 | 143.1172 | 548.4176 | 24324.431 | 130.5887 | 0 | 0 | 829.0116 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% ¦ 27500 | NA ¦ NA | NA | 0% | 100% | [CPUC Status] NA
177 | Q1665 Kingsley Generation Interconnection |  |  | Imperial County | 135 MW (Phase 1) and 225 MW (Phase 2) solar PV and battery energy storage system (BESS) with POI at Imperial Valley Substation 230kV bus | Substation - Multiple | New | New | NA | Generator Interconnection | Generation Interconnection | CAISO Requirement | NA | 2025-11-18 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | TBD |  | NA | 55.48 | 230 | 230kV | 2.1 | 2025-4218 | QBL0141 | 1 | 21156 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-12-06 | Work Order Authorization | 2025 | NA | FALSE | NA | NA | NA | TRUE | TBD | TBD | Exempted | NA | CPUC | BLM | TBD | TBD | Other [See Notes] | TBD | Planning | NA | 2026-08-06 | 2029-10-05 | 2029-10-05 | NA | NA | FALSE | 2488.0003 | $1,174 ¦ CAISO | 2769.3108 | 0 | 0 | 0 | 0 | 22.3107 | 127.3997 | 1466.7724 | 624.2729 | 281.4315 | 247.1236 | 0 | 22.3107 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% ¦ 1,174 | NA ¦ NA | NA | 0% | 0% | [CPUC Status] TBD
178 | [Programmatic] Transmission Power Quality |  |  | Multiple | This project will deploy Power Quality Meters in SDG&E electric substations on transmission circuits to enable the collection of time-series analog data used to detect incipient failures of electrical equipment and locate that failing equipment before it can cause significant damage. | Substation - Multiple | Upgrade/Retrofit | NA | NA | Reliability | Replace Other Substation Equipment | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | Multiple | 373MVA | 4.3 | Multiple | QBL0157 | 9 | 22126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-12-11 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | NA | NA | NA | NA | Exempt | NA | To be Filed | NA | Operational | NA | NA | 2024-12-31 | Multiple | NA | NA | TRUE | NA | NA ¦ NA | 12925.5228 | 33.6898 | 491.093 | 866.1993 | 531.5391 | 1146.9014 | 395.6206 | 596.0009 | 709.6646 | 708.2326 | 789.914 | 879.3879 | 1028.1933 | NA | NA | 2021 ¦ 2023 ¦ 2024 ¦ 2025 ¦ 2026 | 0.023536 | 0 | 664.4589 | 615.9295 | 760.8174 | 1002.3956 | 0% | NA ¦ NA | 26.1 | NA | 13.55% | 86.45%
179 | [Programmatic] Early Fault Detection |  |  | Multiple | This project will deploy Power Quality Meters and advanced Radio Frequency (RF) Sensors in SDG&E electric substations and electric distribution circuits within the High Fire Threat District to enable the collection of time-series analog data used to detect incipient failures of electrical equipment and locate that failing equipment before it can cause significant damage. The program will also fund various analytical / software tools utilized to aggregate this highly sampled data, analyze it and use it to triangulate the failure locations so crews may be dispatched to proactively inspect / investigate with a goal of preventing significant damage. | Substation - Multiple | Upgrade/Retrofit | NA | NA | Wildfire Mitigation | Automation | NA | NA | NA | NA | NA | NA | NA | Tier 2 ¦ Tier 3 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | NA | NA | NA | NA | 1.2 | Multiple | QBL0148 | 2 | 22256 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-12-11 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | NA | 2024-12-31 | Multiple | NA | NA | FALSE | NA | NA ¦ NA | 194.1203 | 0 | 0 | 0 | 194.1129 | 0.0073828 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2024 ¦ 2025 | 0 | 0 | 0 | 194.1129 | 0.0073828 | 0 | 0% | NA ¦ NA | 7.3 | NA | 0% | 0% | [CPUC Status] Exempt
180 | EFD WMP IPREDICT |  |  | San Diego, San Diego | Internal development of iPredict software platform | Other - Operations Tech | Upgrade/Retrofit | NA | NA | Wildfire Mitigation | Automation | NA | NA | NA | NA | NA | NA | NA | Tier 2 ¦ Tier 3 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | NA | NA | NA | NA | 1.2 | NA | QBL0148 | 1 | 22256 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2022-10-31 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | NA | 2026-12-31 | 2025-04-24 | Prioritization | NA | FALSE | 26582.4918 | NA ¦ NA | 2565.0194 | 0 | 1224.6787 | 1043.8824 | 291.2447 | 5.2135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2025 | 0 | 0 | 0 | 0 | 2565.0194 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] Exempt
181 | [Programmatic] CNF PLRP PROJ MGMT/PMO |  |  | Multiple | The scope for this project includes post-construction habitat restoration that is required by project permits for temporarily impacted mitigatable vegetation communities. This includes restoration implementation (weed control and seeding), supplemental seeding, monitoring and maintenance, reporting, and agency meetings/site visits. | Other | NA | NA | NA | Other [See Notes] | Environmental | NA | NA | NA | NA | NA | NA | NA | Tier 2 ¦ Tier 3 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | Multiple | Multiple | 2.2 | Multiple | QBL0159 | 0 | 23128 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-12-15 | Work Order Authorization | 2024 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Operational | NA | Multiple | Multiple | Multiple | NA | NA | FALSE | 271.3179 | NA ¦ NA | 0 | 0 | 0 | 0 | 0 | 117.5424 | 2.4158e-13 | 0 | 0 | 0 | 0 | 0 | 117.5424 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 13.55% | 86.45% | [Primary Purpose] Environmental Remediation
182 | CNF PLRP PROJ MGMT/PMO |  |  | Multiple | The scope for this project includes post-construction habitat restoration that is required by project permits for temporarily impacted mitigatable vegetation communities. This includes restoration implementation (weed control and seeding), supplemental seeding, monitoring and maintenance, reporting, and agency meetings/site visits. | Other | NA | NA | NA | Other [See Notes] | Environmental | NA | NA | NA | NA | NA | NA | NA | Tier 2 ¦ Tier 3 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | Multiple | NA | 2.2 | NA | QBL0159 | 1 | 23128 | 2025-12-10 ¦ Multiple ¦ NA ¦ NA | TRUE | 2023-12-15 | Work Order Authorization | 2024 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Operational | NA | Multiple | Multiple | M | NA | NA | FALSE | NA | NA ¦ NA | 1113.2398 | 0 | 0 | 0 | 60.3979 | 47.6633 | 117.5424 | 240.2351 | 198.073 | 216.373 | 232.9551 | 0 | 108.0612 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 13.55% | 86.45% | [Primary Purpose] Environmental Remediation [CPUC Status] NA
183 | [Programmatic] Substation External Routable Connectivity (SERC) |  |  | Multiple | The SERC program deploys secure routable protocol connections providing event retrieval, password management and remote secure event access to all CIP Medium, Low and No Impact substations. It achieves this by deploying Advanced Relay Event Retrieval (ARER) hardware, Siemens Crossbow devices, and deployment of systems in support thereof. The program also analyses and tests emerging ERC technology use cases and solutions. | Substation - Other Equipment | Upgrade/Retrofit | NA | NA | Reliability | System Operations | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | Multiple | 373MVA | 4.3 | Multiple | QBL0160 | 48 | 23129 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-12-11 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | NA | 2024-12-31 | Multiple | NA | NA | TRUE | 3560 | NA ¦ NA | 70057.1852 | 0 | 0 | 1.9057 | 1423.4601 | 3050.8792 | 1818.1065 | 3944.3168 | 4251.3062 | 4803.5821 | 5383.9352 | 5981.9744 | 2674.471 | NA | NA | 2024 ¦ 2025 ¦ 2026 | 0 | 0 | 0 | 521.5564 | 1280.2175 | 5471.7986 | 0% | NA ¦ NA | 3.4 | NA | 13.55% | 86.45% | [CPUC Status] Exempt
184 | [Programmatic] Customer Relocation Projects |  |  | Multiple | Blanket budget code for internally funded customer relocation projects. | Transmission Line - Multiple | Relocate | NA | NA | Work Requested by Others | Facility Relocation | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | Multiple | Multiple | 3.1 | Multiple | QBL0166 | 1 | 23130 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-12-13 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Operational | NA | Multiple | Multiple | Multiple | NA | NA | FALSE | NA | NA ¦ NA | 320.1406 | 32.0058 | 126.7428 | 105.877 | 37.4745 | 561.5589 | 0 | 0 | 0 | 0 | 0 | 0 | 543.5184 | NA | NA | 2025 | 0 | 0 | 0 | 0 | 320.1406 | 0 | 0% | NA ¦ NA | 6.2 | NA | 0% | 0% | [CPUC Status] ¦ NA [Long Term Transmission Investment Plan Inclusion] new budget code created in late 2023.
185 | TL651 BOUNDARY ST RELOCATION |  |  | San Diego, San Diego | Internally-funded relocation project to replace three (3) transmission poles with 69 kV/4 kV/Communication and install approximately 800 ft. of new transmission and distribution conductor. Relocate Z730600 away from an eroding drainage bank. Replace structures adjacent to HWY-15 (Z730600 and Z2034273419) with self-supporting steel structures. Replace Z730598 with a direct-bury steel pole. | Transmission Line - Multiple | New | New | NA | Work Requested by Others | Facility Relocation | NA | NA | 2025-02-11 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.44 | NA | 69 | NA | 3.1 | 2017-0118 | QBL0166 | 1 | 23130 | 2025-12-10 ¦ NA ¦ NA ¦ NA | TRUE | 2022-08-01 | Work Order Authorization | 2021 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Planning | NA | TBD | 2026-12-15 | 2027-01-29 | Land Rights | Land Rights | TRUE | 4358.261 | NA ¦ NA | 17729.4292 | 0 | 14.9572 | 150.9451 | 251.7517 | 342.3332 | 194.4415 | 16775.0006 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2025 ¦ 2026 | 0 | 0 | 0 | 0 | 954.4286 | 16775.0006 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [See Notes for NERC Compliance and contingency code, WECC Requirement (and the specific requirement)]
186 | TL683 COLE GRADE ROAD |  |  | Valley Center, San Diego | The TL683 Cole Grade Road Project is a part of the Customer Relocation Program. This project is located along Cole Grade Road near the intersection of Hilldale Road in Valley Center, CA. The County has requested two transmission structures on the west side of the road and any associated stub poles on the east side of the road from their current franchise position to be relocated due to the road widening. | Substation - Multiple | New | Replace | NA | Work Requested by Others | Facility Relocation | NA | NA | 2025-08-27 | NA | NA | NA | NA | Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.1 | NA | 69 | NA | 3.1 | 2016-0001-A | QBL0166 | 1 | 23130 | 2025-12-10 ¦ NA ¦ NA ¦ NA | TRUE | 2021-09-30 | Work Order Authorization | 2021 | NA | FALSE | NA | NA | NA | FALSE | PEA Deemed Complete | NA | Exempted | NA | CPUC | NA | AL-[4081-E] | 2022-09-23 | Approved | 2022 | Construction (over 75%) | NA | 2025-04-14 | 2025-05-09 | 2025-06-09 | Customer Action | NA | FALSE | 2870.5547 | NA ¦ NA | 1496.1327 | 59.709 | 178.4254 | 294.2508 | 199.1644 | 458.6827 | 305.9004 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2025 | 0 | 0 | 0 | 0 | 1496.1327 | 0 | 0% | 100% ¦ 100 | NA ¦ NA | NA | 0% | 100% | [See Notes for NERC Compliance and contingency code, WECC Requirement (and the specific requirement)]
187 | TL634 JUNIPER ST CRP |  |  | Escondido, San Diego | The City of Escondido has provided SDGE with plans for the Safe Routes to School Juniper Street Improvements PROJECT which will require approximately seven (7) SDGE structures to be relocated or modified due to the improvements. The project is located along Juniper Street near Idaho Avenue and Felicita Avenue. SDGE (AI Conde) performed a conflict check for the City of Escondido and identified the following structures may result in potential conflicts: Z16648, P516576, Z16649, P513748, Z16643, P512805, and Z16644. | Transmission Line - Multiple | New | New | NA | Work Requested by Others | Facility Relocation | NA | NA | 2025-01-17 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.3 | NA | 69 | NA | 3.1 | 2021-2096 | QBL0166 | 1 | 23130 | 2025-12-10 ¦ NA ¦ NA ¦ NA | TRUE | 2021-08-30 | Work Order Authorization | 2021 | NA | FALSE | NA | NA | NA | FALSE | PEA Deemed Complete | NA | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2024-04-30 | 2024-11-26 | 2024-11-26 | NA | NA | FALSE | 2359.0354 | NA ¦ NA | 1464.9837 | 14.6157 | 203.4255 | 301.4164 | 724.0287 | 178.3208 | 43.1766 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2025 | 0 | 0 | 0 | 0 | 1464.9837 | 0 | 0% | 100% ¦ 100 | NA ¦ NA | NA | 0% | 100% | [See Notes for NERC Compliance and contingency code, WECC Requirement (and the specific requirement)] [CPUC Status] NA
188 | [Programmatic] Transmission Failing Cable Replacement |  |  | San Diego, San Diego | Replace underground cable systems targeting hand taped splices exhibiting degradation leading to failure. | Transmission Line - Underground | Upgrade/Retrofit | NA | NA | Reliability | Age/Condition | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 23 | NA | 69 | NA | 4.1 | Multiple | QBL0171 | 0 | 24129 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-12-16 | Work Order Authorization | 2024 | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | To be Filed | NA | Planning | NA | NA | 2026-12-31 | 2026-12-30 | NA | NA | FALSE | 31289.7138 | NA ¦ NA | 62028.4639 | 0 | 0 | 0 | 0 | 17209.1289 | 17209.1289 | 20113.1421 | 24706.1929 | 0 | 0 | 0 | 17209.1289 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | 37.4 | NA | 0% | 100%
189 | UG TRANS CABLE REPL: 2024 SCOPE |  |  | San Diego, San Diego | Replace underground cable systems targeting hand taped splices exhibiting degradation leading to failure. | Transmission Line - Underground | Upgrade/Retrofit | NA | NA | Reliability | Age/Condition - Replace Underground System | NA | NA | 2025-10-31 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 3 | NA | 69 | NA | 4.1 | Multiple | QBL0171 | 1 | 24129 | 2025-12-10 ¦ 2024-3828 ¦ NA ¦ NA | TRUE | 2024-06-04 | Work Order Authorization | 2024 | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | To be Filed | NA | Operational | NA | 2024-10-01 | 2024-12-31 | 2025-03-15 | Permitting | Permitting | FALSE | 134697.3219 | NA ¦ NA | 40913.4987 | 0 | 0 | 0 | 23601.4129 | 17312.0858 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2025 | 0 | 0 | 0 | 0 | 40913.4987 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Project was Exempt from CPUC filing per GO-131D.
190 | Golden Pacific Powerlink (GPP) Project |  |  | Multiple | New CAISO-approved 500kV transmission line connecting IV Substation to a new Substation north of SONGS near border of San Diego and Orange County. | Transmission Line - Pole/Tower | New | NA | N/A | Policy | New T-Line | CAISO Requirement | CAISO Requirement | NA | NA | NA | Wires - New T-Line Alternative | Over $500 Mil | TBD | FALSE ¦ FALSE ¦ FALSE | FALSE | TBD |  | 150 | NA | 500 | NA | 2.1 | 2025-4735 | QS00794 | 1 | 25150 | NA ¦ NA ¦ NA ¦ NA | FALSE | NA | Work Order Authorization | 2025 | 2022-2023 | 2023-2024 | 2022-2023 | 2022-2023 | https://stakeholdercenter.caiso.com/InitiativeDocuments/ISO-Board-Approved-2022-2023-Transmission-Plan.pdf | FALSE | TBD | TBD | EIR | EIS | CPUC | TBD | CPCN | TBD | To be Filed | NA | Planning | NA | 2029-09-30 | 2032-01-31 | 2032-01-31 | NA | NA | FALSE | 1,300,000 - 2,200,000 | NA ¦ NA | 1,300,000 - 2,200,000 | 0 | 0 | 0 | 0 | 133 | 460 | 46154 | TBD | TBD | TBD | TBD | 133 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | N/A | 100% | 0% | SDG&E is providing a preliminary project cost estimate range. Given the cost uncertainty associated with the early-stage development of the project to date prior to engaging with potential suppliers, this preliminary range is an estimate. SDG&E expects refined cost data will be included in future TPR reports.
191 | [Programmatic] Transmission System Automation |  |  | Multiple | To enhance transmission system reliability, capital projects are required to 1) install new transmission SCADA systems and 2) replace/upgrade existing transmission SCADA systems to provide control and monitoring capability for grid operations. In addition, there is a requirement to install systems to provide monitoring of certain critical substation apparatus to provide data for enhanced scheduling of maintenance. There are also new security requirements based upon NERC guidelines and the SEMPRA Control System security policy, which mandate the need to install equipment to control access to equipment installed in substations. The budget also allows us to enable remote event retrieval in non-Medium Impact substations to significantly reduce the time it takes to obtain event records and situational awareness during system disturbances. | Substation - Multiple | Upgrade/Retrofit | NA | NA | Reliability | Relay Upgrades | NERC CIP Compliance | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69 ¦ 500 | 373MVA | 2.1 | Multiple | QBL0001 | 58 | 3171 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-12-11 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | NA | 2024-12-31 | Multiple | NA | NA | TRUE | NA | NA ¦ NA | 68149.5465 | 1813.0371 | 2321.0586 | 2272.7135 | 763.1142 | 2198.4015 | 1948.3166 | 3382.4962 | 3741.4955 | 4206.8226 | 4719.3186 | 5246.9118 | 1307.8834 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 ¦ 2026 | 265.5254 | 2153.7936 | 3856.2026 | 1232.6206 | 552.2994 | 3031.3331 | 0% | NA ¦ NA | 3.1 | NA | 13.55% | 86.45% | [CPUC Status] ¦ NA [Types of Analyses] Information security
192 | CEC RAS SONGS |  |  | San Diego, San Diego | SONGS substation CEC-RAS upgrades | Substation - Protection Relay | Upgrade/Retrofit | NA | NA | Reliability | Relay Upgrades | NA | NA | 2025-10-16 | 3.85 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 230 | NA | 2.1 | 2022-2912 | QBL0001 | 1 | 3171 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2022-05-11; 2022-05-1; 2022-05-11 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2023-03-06 | 2023-08-03 | 2023-08-20 | Prioritization | NA | FALSE | 2114.7965 | NA ¦ NA | 1122.593 | 0 | 22.411 | 994.6953 | 41.578 | 63.9086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2023 ¦ 2024 ¦ 2025 | 0 | 0 | 1017.1063 | 41.578 | 63.9086 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0% | [CPUC Status] Exempt [Types of Analyses] Information security
193 | SYSTEM AUTOMATION CROSSBOW |  |  | San Diego, San Diego | Siemens Crossbow deployments at multiple substations | Substation - Protection Relay | Upgrade/Retrofit | NA | NA | Reliability | Relay Upgrades | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69 ¦ 138 | 373MVA | 2.1 | NA | QBL0001 | 1 | 3171 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-05-11 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | NA | 2023-12-31 | 2024-10-31 | Prioritization | NA | FALSE | 5626.5931 | NA ¦ NA | 3356.5817 | 659.0243 | 741.0698 | 441.3229 | 305.2445 | 6.0791 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2024 ¦ 2025 | 0 | 0 | 0 | 3350.5026 | 6.0791 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
194 | SYSTEM AUTOMATION VARIOUS SUBS |  |  | San Diego, San Diego | Transmission System Automation (TSA) upgrades at multiple substations | Substation - Protection Relay | Upgrade/Retrofit | NA | NA | Reliability | Relay Upgrades | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69 | 373MVA | 2.1 | 2020-2045 | QBL0001 | 1 | 3171 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-03-04 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2020-08-12 | 2020-04-01 | 2021-04-08 | Prioritization | NA | FALSE | 685.319 | NA ¦ NA | 5057.1067 | 2370.1925 | 178.7026 | -6.2042 | 0.00179 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 | 0.36639 | 5062.9427 | -6.2042 | 0.00179 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] ¦ NA
195 | ADVANCED RLY EVENT RETRVL SUBS |  |  | San Diego, San Diego | Advanced Relay Event Retrieval (ARER) deployments at multiple substations | Substation - Protection Relay | Upgrade/Retrofit | NA | NA | Reliability | Relay Upgrades | NA | NA | 2025-10-01 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69 | 373MVA | 2.1 | Multiple | QBL0001 | 1 | 3171 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-08-07 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2022-09-12 | 2023-12-31 | 2022-08-30 | Prioritization | NA | FALSE | 4466.8942 | NA ¦ NA | 3102.4293 | 930.75 | 1331.2285 | 597.451 | 210.5402 | 31.4449 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 0 | 2262.9932 | 597.451 | 210.5402 | 31.4449 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt [Utility Unique ID #1(Less Specific)] 2019-2110 , 2014-00646-ZZ , 2022-2975 , 2021-2053 , 2021-2130 , 2021-2134 , 2023-3594 , 2023-3600 , 2023-3602 , 2021-2023 , 2021-2022 , 2021-2020 , 2021-2024 , 2021-2461 , 2022-2919 , 2022-2927 , 2021-2131 , 2020-2051 , 2020-2080 , 2021-2003 , 2021-2315
196 | MISSION SUBSTATION: PILOT TELEP |  |  | San Diego, San Diego | Pilot Telephony deployment at Mission Substation | Substation - Protection Relay | Upgrade/Retrofit | NA | NA | Reliability | Relay Upgrades | NA | NA | 2025-11-12 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 1.83 | 69 | NA | 2.1 | NA | QBL0001 | 1 | 3171 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2015-10-16 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | NA | 2016-12-31 | 2022-05-30 | Prioritization | NA | FALSE | 200 | NA ¦ NA | 1893.8837 | 741.5454 | 287.3885 | 4.9655 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 | -17.6185 | 1906.5367 | 4.9655 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] NA
197 | BERNARDO SUBST. RPL TL689 RLY |  |  | San Diego, San Diego | Upgrade 69kV relays and supporting equipment for TL689. | Substation - Protection Relay | Upgrade/Retrofit | NA | NA | Reliability | Relay Upgrades | NA | NA | 2025-11-11 | 4.32 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 2.51 (BE) / 4.66 (ES) | 69 | 373MVA | 2.1 | 2014-01115-ZZ | QBL0001 | 1 | 3171 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-09-16; 2019-01-28; 2019-09-16; 2019-01-25; 2019-01-25 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2021-04-27 | 2023-11-14 | 2024-12-26 | Prioritization | NA | FALSE | 10428.1179 | NA ¦ NA | 11906.6922 | 1207.5322 | 4046.0331 | 1806.6638 | 1679.0852 | 239.8396 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2024 ¦ 2025 | 1.2305 | -0.25875 | 0 | 3352.0871 | 8553.6334 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
198 | [Programmatic] Emergency Equipment Purchase |  |  | Multiple | This budget supports the restoration of service to our distribution customers following outages caused by equipment failure by purchasing additional emergency spare and mobile equipment. Spare equipment is necessary to provide construction and operations with the appropriate spares to replacement equipment under failure conditions. Spare equipment is typically use for critical situations and the stock must be kept up to date to minimize chances for mismatch in field. | Substation - Multiple | Replace | NA | NA | Reliability | Substation Reliability | NERC TPL Standards | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | Multiple | 28MVA | 4.1 | Multiple | QBL0024 | 35 | 6254 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-12-16 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | NA | NA | To be Filed | NA | Operational | NA | NA | 2024-12-31 | Multiple | NA | NA | TRUE | NA | NA ¦ NA | 39289.7205 | 994.4584 | 280.2973 | 319.7617 | 264.9001 | 1075.9162 | 1053.5865 | 775.2383 | 1170.63 | 1179.7303 | 2802.7042 | 3619.0892 | 822.6371 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 ¦ 2026 | 1171.5107 | 333.7874 | 266.4494 | 318.2124 | 22.7367 | 1053.1795 | 0% | NA ¦ NA | 8.1 | NA | 0% | 100%
199 | ES SPARE 69KV & 138KV CBS |  |  | Escondido, San Diego | The purchase of (2) spare 69kV, 3000A, 63kA Circuit Breakers, and (2) spare 138kV, 3000A, 63kA Circuit Breakers. These breakers will be used on substation capital projects and emergency breaker replacements | Substation - Multiple | New | New | NA | Reliability | 3rd Party Damage | NERC CIP Compliance | NERC CIP Compliance | 2025-11-20 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 4.66 | 69 and 13 | 69kV and 138kV | 4.1 | NA | QBL0024 | 1 | 6254 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-03-07 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | CPUC | NA | NA | NA | To be Filed | NA | Operational | NA | 2023-03-07 | NA | 2025-04-14 | Material | Material | FALSE | 512.7173 | NA ¦ NA | 1018.7814 | 0 | 0 | 0.39574 | 804.8984 | 213.4872 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2025 | 0 | 0 | 0 | 0 | 1018.7814 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
200 | [Programmatic] Fiber Build Initiative |  |  | Multiple | Install ADSS and or OPGW fiber optic cables on existing Transmission overhead structures and build UG facilities as required. | Other | New | NA | NA | Reliability | System Operations | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | Multiple | NA | 4.3 | Multiple | QBL0025 | 199 | 7144 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-12-16 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | Categorical Exclusion | NA | NA | NA | NA | NA | NA | Operational | NA | NA | 2025-12-30 | Multiple | NA | NA | TRUE | NA | NA ¦ NA | 213254.2199 | 990.9859 | 836.8156 | 2686.0093 | 5241.3919 | 13259.4201 | 9228.961 | 13385.1776 | 12757.2304 | 17069.8659 | 14723.817 | 16084.0945 | 14436.6289 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 ¦ 2026 | 896.5278 | 309.7797 | 1786.845 | 1370.6533 | 4214.188 | 12706.7373 | 0% | NA ¦ NA | 2.1 | NA | 13.55% | 86.45% | [CPUC Status] NA
201 | FBI TL23012/53/674(Z710041 ENC) |  |  | Encinitas, San Diego | TL674/6973 EN-DM with OPGW attachments on TL23012/23053. | Other | New | New | NA | Reliability | System Operations | NA | NA | 2025-01-28 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 8.05 | NA | NA | NA | 4.3 | 2019-4010 | QBL0025 | 1 | 7144 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-01-20; 2024 -09-04 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | To be Filed | NA | Engineering less than 50% complete | NA | 2027-03-03 | 2021-10-30 | 2027-09-01 | NA | NA | FALSE | 6204.8081 | NA ¦ NA | 2883.5952 | 96.4412 | 352.8243 | 215.2307 | 1747.7447 | 318.0819 | 13.3685 | 27.0264 | 20.5259 | 0 | 0 | 0 | 2822.6745 | NA | NA | 2025 | 0 | 0 | 0 | 0 | -77.193 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] NA
202 | FBI_TL23027 TL23028 MS OT |  |  | San Diego, San Diego | This project installs a fiber optic connection between Mission Substation and Oldtown Substation. | Other | New | New | NA | Reliability | System Operations | NA | NA | 2025-02-04 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 1.84 | NA | NA | NA | 4.3 | 2009-00015-ZZ | QBL0025 | 1 | 7144 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2018-09-13; 2019-11-20; 2019-11-20 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2020-09-15 | 2021-09-30 | 2022-05-24 | NA | NA | FALSE | 2930.258 | NA ¦ NA | 3839.5737 | 2546.6883 | 338.0937 | 46.1068 | 118.8795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2022 ¦ 2023 ¦ 2024 | 0 | 3674.5874 | 46.1068 | 118.8795 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0%
203 | TL 654 MISSIONSTATION F R3 |  |  | San Diego, San Diego | This project installs fiber optic approximately 2.2 miles of 96-count ADSS Fiber Optic Cable on TL654 between Station F and Mission Substation as well as 5 pole replacement, and installation of 2 new Fiber-only poles, 3 fiber optic splice boxes and 10ft UG trench. | Other | New | New | NA | Reliability | System Operations | NA | NA | 2025-02-15 | 34; 34; 34; 34; 61 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | TBD |  | 5.28 | NA | NA | NA | 4.3 | 2014-00430-ZZ | QBL0025 | 1 | 7144 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-02-10; 2020-02-26; 2020-02-26 | Work Order Authorization | 2019 | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | CPUC | NA | Exempt | NA | To be Filed | NA | Operational | NA | 2021-02-24 | 2021-04-01 | 2021-08-23 | NA | NA | FALSE | 1921.408 | NA ¦ NA | 1095.2417 | 476.4009 | 77.6071 | 38.2451 | 57.6668 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 | 921.7226 | 77.6071 | 38.2451 | 57.6668 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] NA
204 | TL608 STREAMVIEWCHOLLAS R4 |  |  | San Diego, San Diego | This project installs ADSS fiber from Streamview to Chollas | Other | New | New | NA | Reliability | System Operations | NA | NA | 2025-04-25 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | TBD |  | 2.54 | NA | NA | NA | 4.3 | 2010-00005-ZZ | QBL0025 | 1 | 7144 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2013-05-13 | Work Order Authorization | 2019 | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | On Hold | NA | 2026-05-13 | 2013-12-31 | 2028-10-10 | NA | NA | TRUE | 390 | NA ¦ NA | 1496.4008 | 89.4288 | 166.7859 | 94.8248 | 350.0449 | 3.1503 | 0 | 0 | 0 | 0 | 0 | 0 | 1496.4008 | NA | NA | 2026 | 0 | 0 | 0 | 0 | 0 | 1496.4008 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] Exempt [Reason for Change in In-Service Date] This project has been suspended due to CPUC budget cuts.
205 | TL 621 PARADISEMIGUEL F R2 |  |  | San Diego, San Diego | This projects installs 6.7miles of ADSS friber from Paradise to Miguel | Other | New | New | NA | Reliability | System Operations | NA | NA | 2025-02-08 | NA | NA | NA | NA | Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | TBD |  | 7.484 | NA | NA | NA | 4.3 | 2010-00007-ZZ | QBL0025 | 1 | 7144 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2018-04-10; 2020-04-24; 2020-04-24 | Work Order Authorization | 2019 | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | On Hold | NA | 2025-04-30 | 2019-12-01 | 2026-11-04 | NA | NA | TRUE | 2794.298 | NA ¦ NA | 2354.6175 | 320.5978 | 508.7839 | 6.6927 | 1273.2979 | 10.02 | 33.5519 | 3.3332 | 0 | 0 | 0 | 0 | 2119.3924 | NA | NA | 2026 | 0 | 0 | 0 | 0 | 0 | 2354.6175 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] Exempt [Reason for Change in In-Service Date] This project has been suspended due to CPUC budget cuts.
206 | TL697 SAN LUIS REY OCE R7 |  |  | Oceanside, San diego | This project consists of installing 1 cable (192-Fiber DNA-33029 ADSS) on TL697 between structures Z229374 to Z28268, approximately 1 mile. Project includes installing 3 fiber optic splice locations and 26 ADSS connections. | Other | New | New | NA | Reliability | System Operations | NA | NA | 2025-02-08 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | TBD |  | 1.49 | NA | NA | NA | 4.3 | 2014-00465-ZZ | QBL0025 | 1 | 7144 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-01-27; 2020-01-16 | Work Order Authorization | 2019 | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | NA | 2020-11-01 | 2022-09-28 | NA | NA | FALSE | 135.665 | NA ¦ NA | 1247.3706 | 85.3147 | 495.0539 | 51.1882 | 212.6971 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2022 ¦ 2023 ¦ 2024 | 0 | 983.4853 | 51.1882 | 212.6971 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] Exempt
207 | FIBER BUILD TL6973 DM NCW |  |  | San Diego, San Diego | Project consists of installing two miles of UG fiber & 1 mile of OPGW to connect DM-NCW | Other | New | New | NA | Reliability | System Operations | NA | NA | 2025-01-28 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 3 | NA | 230 | NA | 4.3 | 2020-4032 | QBL0025 | 1 | 7144 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-11-13; 2023-03-07; 2021-12-15 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2025-02-04 | 2024-12-10 | 2025-09-02 | NA | NA | FALSE | 3018.685 | NA ¦ NA | 1916.3101 | 21.0855 | 120.1882 | 297.3859 | 1130.587 | 310.7033 | 36.3602 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2025 | 0 | 0 | 0 | 0 | 1916.3101 | 0 | 100% | NA ¦ NA | NA ¦ NA | NA | 100% | 0% | [CPUC Status] Exempt
208 | TL608 STRUCTURE RPL GRP 1 |  |  | San Diego, San Diego | Pole Replacements for Z371045, Z473553. This project is only a pole replacement and does not include any mileage. | Other | New | New | NA | Reliability | System Operations | NA | NA | 2025-04-25 | 57 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.1 | NA | NA | NA | 4.3 | 2022-3097 | QBL0025 | 1 | 7144 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2022-10-10; 2022-12-01 | Work Order Authorization | 2023 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | CPUC | NA | Exempt | 2023-02-07 | Approved | NA | Construction (under 10%) | NA | 2025-10-16 | 2024-08-07 | 2026-04-07 | NA | NA | FALSE | 2017.4396 | NA ¦ NA | 1370.4859 | 0 | 1.7024 | 268.7547 | 879.72 | 168.0661 | 52.2426 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2025 | 0 | 0 | 0 | 0 | 1370.4859 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] NA
209 | FBI TL652/653 METRO STATION F |  |  | San Diego, San Diego | This is a fiber project for reverse engineering from Metro- Station F Sub, to bring this TL up to SDGE standards | Other | New | New | NA | Reliability | System Operations | NA | NA | 2025-07-21 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 3.7 | NA | NA | NA | 4.3 | 2021-2218 | QBL0025 | 1 | 7144 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2021-07-14 | Work Order Authorization | 2022 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | CPUC | NA | Exempt | NA | To be Filed | NA | Engineering more than 50% complete | NA | 2026-07-30 | 2023-12-10 | 2027-07-16 | NA | NA | FALSE | 382.1892 | NA ¦ NA | 1483.9047 | 0.23163 | 57.4894 | 295.9945 | 475.5031 | 466.3597 | 58.0165 | 124.0137 | 6.2962 | 0 | 0 | 0 | 1295.614 | NA | NA | 2025 | 0 | 0 | 0 | 0 | -0.035641 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] NA
210 | TL674 RANCHO SANTA FE TO Z12322 |  |  | San Diego, Rancho Santa Fe | this Fiber Build Project involves installation of 3.5-miles of fiber optic cable (ADSS) on existing TL674 between structures Z710041 (TL23012/23053) and Z192874 (TL674). | Other | New | New | NA | Reliability | System Operations | NA | NA | 2025-01-28 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 3.5 | NA | NA | NA | 4.3 | 2019-4013 | QBL0025 | 1 | 7144 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-01-08 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Engineering more than 50% complete | NA | 2027-10-15 | 2024-03-10 | 2028-03-17 | NA | NA | FALSE | 5140.496 | NA ¦ NA | 2648.381 | 87.8171 | 206.9926 | 1.0593 | 1261.672 | 424.1231 | 92.4187 | 197.5506 | 215.8017 | 48.9763 | 0 | 0 | 1991.3827 | NA | NA | 2025 | 0 | 0 | 0 | 0 | -9.7185 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] Exempt
211 | TL652 STATION F WABASH F R4 |  |  | San Diego, San Diego | TL652 F-WAC Fiber Build | Other | New | New | NA | Reliability | System Operations | NA | NA | 2025-07-21 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 2.48 | NA | NA | NA | 4.3 | 2010-00003-ZZ | QBL0025 | 1 | 7144 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-02-10 | Work Order Authorization | 2019 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | CPUC | NA | Exempt | NA | To be Filed | NA | On Hold | NA | NA | 2023-01-15 | 2028-10-10 | NA | NA | FALSE | 1940.972 | NA ¦ NA | 2492.6267 | 146.6675 | 143.9066 | 0.76998 | 1504.9648 | 26.0935 | 86.0846 | 184.011 | 201.0112 | 81.5593 | 0 | 0 | 1822.4023 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] NA
212 | TL607 WABASH STREAMVIEW R4 |  |  | San Diego, San Diego | TL607 WAC-SR Fiber Build | Other | New | New | NA | Reliability | System Operations | NA | NA | 2025-02-25 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 3.19 | NA | NA | NA | 4.3 | 2010-00004-ZZ | QBL0025 | 1 | 7144 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-02-10; 2020-04-24; 2020-04-24 | Work Order Authorization | 2019 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | On Hold | NA | NA | 2023-01-10 | 2027-01-26 | NA | NA | TRUE | 2794.924 | NA ¦ NA | 1607.5398 | 65.4742 | 135.3998 | 81.8998 | 1186.1884 | 10.6669 | 0 | 0 | 0 | 0 | 0 | 0 | 1479.629 | NA | NA | 2026 | 0 | 0 | 0 | 0 | 0 | 1607.5398 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] Exempt
213 | TL 624 JAMACHA EL CAJON R4 |  |  | El Cajon, San Diego | Install a level of ADSS fiber on 4.8 miles of TL624 poles between Jamacha Substation and El Cajon Substation (0.7 miles from Z371408 to El Cajon Substation is double circuit with TL 630), 7 Steel Pole Replacement, Construct ADSS conduit on Z778064 (inside of Jamacha Substation) and trench into Jamacha Substation. Construct ADSS conduits on Z75142 for TL624 Fiber Build and TL630 FIber Build and trench into El Cajon Substation. Construct ADSS conduit on P100483 and Z371410 and trench 0.2 miles in between. Correct all non-compliance, both existing and caused by proposed ADSS addition. This to be done be replacing poles and reframing distribution. | Other | New | New | NA | Reliability | System Operations | NA | NA | 2025-11-06 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 4.8 | NA | NA | NA | 4.3 | 2010-00010-ZZ | QBL0025 | 1 | 7144 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-02-10; 2018-03-02 | Work Order Authorization | 2019 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | CPUC | NA | Exempt | NA | To be Filed | NA | On Hold | NA | NA | 2024-12-02 | 2027-03-22 | NA | NA | FALSE | 3133.983 | NA ¦ NA | 1660.7528 | 38.6457 | 361.0917 | 74.7756 | 898.548 | -31.0343 | 49.7297 | 106.3002 | 43.1308 | 0 | 0 | 0 | 1461.5922 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] NA
214 | TL 600 ROSECANYON CLAIRE R3 |  |  | San Diego, San Diego | The proposed Project aims to install approximately 4 miles of 96-Count ADSS Fiber Optic Cable between these substations, along existing TL 600 structures. The proposed route would attach to 72 existing structures supporting TL 600 conductor. There are 5 proposed new structures proposed specifically for the fiber addition. At each substation, the fiber will convert from an overhead to underground configuration at the last pole outside the substation. From there, SDG&E will install fiber in existing underground conduit into each substation. | Other | New | New | NA | Reliability | System Operations | NA | NA | 2025-02-15 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 4.76 | NA | NA | NA | 4.3 | 2010-00012-ZZ | QBL0025 | 1 | 7144 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-02-10; 2020-02-26; 2018-02-01 | Work Order Authorization | 2019 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | On Hold | NA | NA | 2022-12-10 | 2026-12-14 | NA | NA | TRUE | 2465.449 | NA ¦ NA | 1162.1635 | 285.9957 | 82.8769 | 14.74 | 690.3848 | 7.5197 | 13.0646 | 3.5416 | 0 | 0 | 0 | 0 | 1081.517 | NA | NA | 2026 | 0 | 0 | 0 | 0 | 0 | 1162.1635 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] Exempt
215 | TL674 STURCTURE RPL GRP 1 |  |  | San Diego, San Diego | Compliance pole replacements for structures Z12322 & Z12323 | Other | New | New | NA | Reliability | System Operations | NA | NA | 2025-01-28 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.04 | NA | NA | NA | 4.3 | 2022-2988 | QBL0025 | 1 | 7144 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2022-09-20 | Work Order Authorization | 2022 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | CPUC | NA | Exempt | 2025-10-23 | Filed and Under Administrative Review | NA | Construction (over 75%) | NA | 2025-02-06 | 2024-04-03 | 2025-05-02 | NA | NA | FALSE | 983.397 | NA ¦ NA | 1082.4925 | 0 | 18.4744 | 355.2612 | 197.5604 | 506.8073 | 4.3891 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2023 ¦ 2024 ¦ 2025 | 0 | 0 | 373.7356 | 170.7371 | 538.0197 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] NA
216 | TL680B MELROSE MELROSE T R6 |  |  | Vista, San Diego | The project will include stringing 4.0 miles of new DNA-30411 ADSS conductor (including 2.0 miles of underground ADSS from Z115895 to Melrose Substation, 0.2 miles of which will require new trenching), installing fiber attachments, and installing fiber splice boxes. Fiber connection to substation to utilize existing infrastructure. | Other | New | New | NA | Reliability | System Operations | NA | NA | 2025-02-11 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 6.2 | NA | NA | NA | 4.3 | 2015-00015-ZZ | QBL0025 | 1 | 7144 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-01-28; 2020;01-29 | Work Order Authorization | 2019 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | On Hold | NA | 2026-06-18 | 2023-12-10 | 2027-01-18 | NA | NA | TRUE | 6070.021 | NA ¦ NA | 3577.7082 | 187.8281 | 127.8449 | 4.9681 | 2626.6664 | 24.3163 | 149.4152 | 40.5041 | 0 | 0 | 0 | 0 | 3035.914 | NA | NA | 2025 ¦ 2026 | 0 | 0 | 0 | 0 | -64.29 | 3641.9982 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] Exempt
217 | FBI_TL652POLE REPLACEMENTS SR94 |  |  | San Diego, San Diego | Replacing 2 poles (Z730989, Z730996) with ESPs on TL652, crossing 94 freeway. No newfiber stringing. Mitigating L2 issues due to overutilization.​ | Other | New | New | NA | Reliability | System Operations | NA | NA | 2025-07-21 | 70 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | TBD |  | 2.48 | NA | NA | NA | 4.3 | 2024-3974 | QBL0025 | 1 | 7144 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-07-29 | Work Order Authorization | 2024 | NA | FALSE | NA | NA | NA | FALSE | TBD | TBD | Exempted | Other [See Notes] | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Engineering more than 50% complete | NA | 2026-09-02 | 2026-04-03 | 2026-09-18 | NA | NA | TRUE | 1174.8215 | NA ¦ NA | 1055.2498 | 0 | 0 | 0 | 460.8772 | 474.1846 | 41.8046 | 78.3834 | 0 | 0 | 0 | 0 | 935.0617 | NA | NA | 2026 | 0 | 0 | 0 | 0 | 0 | 1055.2498 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] NA
218 | [Programmatic] Overstressed Breakers |  |  | Multiple | Replace overstressed breakers as identified at the following substations : Bay Boulevard, Mission, Sycamore Canyon, San Luis Rey, Miguel | Substation - Circuit Breaker | Replace | NA | NA | Reliability | Age/Condition | NERC TPL Standards | NA | NA | NA | NA | Wires - Replacement Alternative | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | Multiple | NA | 2.1 | Multiple | QBL0061 | 13 | 9170 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-12-16 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | NA | NA | To be Filed | NA | Planning | NA | NA | 2024-12-31 | Multiple | NA | NA | TRUE | NA | NA ¦ NA | 67869.5977 | 18.8614 | 42.2006 | 301.2157 | 237.0847 | 1811.2795 | 1479.4177 | 2564.8317 | 3221.733 | 3531.9563 | 3871.2187 | 4242.2244 | 1622.7855 | NA | NA | 2024 ¦ 2025 ¦ 2026 | 0 | 0 | 0 | 607.4359 | 180.4205 | 1479.4177 | 0% | NA ¦ NA | 3.3 | NA | 0% | 100%
219 | SAN LUIS RAY OVERSTRES |  |  | Oceanside, San Diego | Replace breakers based on short circuit study | Substation - Circuit Breaker | Replace | Upgrade/Retrofit | NA | Reliability | Replace Breakers | NA | NA | 2025-10-30 | 51; 51; 51; 54; 51; 51; 54; 54; 54; 51; 54; 54; 54; 54 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 6.12 | 69 | 230 kV ¦ 69 kV | 2.1 | 2022-2943 | QBL0061 | 1 | 9170 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2021-06-18 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | To be Filed | NA | Engineering more than 50% complete | NA | 2025-09-08 | 2023-12-31 | 2026-07-07 | Weather | NA | TRUE | 3106.3706 | NA ¦ NA | 3748.5484 | 1659.8046 | 335.3891 | 307.8147 | 610.7175 | 454.8066 | 151.4414 | 228.5745 | 0 | 0 | 0 | 0 | 3368.5325 | NA | NA | 2026 | 0 | 0 | 0 | 0 | 0 | 3748.5484 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [Reason for Change in In-Service Date] In-service dates are estimated during preliminary design and permitting stages of a project; date shifted to reflect actual design and construction schedule.
220 | MIGUEL OVERSTRESSED BREAKER |  |  | San Diego, San Diego | Miguel - 69kV Overduty CB/DC Motor Retrofit | Substation - Circuit Breaker | Replace | Upgrade/Retrofit | NA | Reliability | Age/Condition - Replace Breakers | NA | NA | 2025-11-14 | 52 | NA | NA | NA | Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 12.37 | 69 | 69 kV | 2.1 | 2021-2498 | QBL0061 | 1 | 9170 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-10-13 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | 2024-01-17 | 2021-09-01 | 2024-04-17 | Weather | NA | FALSE | 300.6063 | NA ¦ NA | 1446.9231 | 103.6174 | 499.083 | 225.32 | 657.3331 | -38.4304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2024 ¦ 2025 | 0 | 0 | 0 | 1485.3535 | -38.4304 | 0 | 46% | 100% ¦ 1921 | NA ¦ NA | NA | 0% | 100% | [Reason for Change in In-Service Date] In-service dates are estimated during preliminary design and permitting stages of a project; date shifted to reflect actual design and construction schedule. [CPUC Status] NA
221 | SYCAMORE CYN OVERSTRESSED BKR R |  |  | San Diego, San Diego | Sycamore Canyon Overstressed Breaker Replacement | Substation - Circuit Breaker | Replace | Upgrade/Retrofit | NA | Reliability | Age/Condition - Replace Breakers | NA | NA | 2025-10-14 | 17; 17; 17; 17; 17; 17; 17; 32; 33; 33; 33; 33; 33; 33; 34; 26; 26; 32 | NA | NA | NA | Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 10.79 | 69 | 138 kV ¦ 69 kV | 2.1 | 2019-1023 | QBL0061 | 1 | 9170 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-04-23 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | To be Filed | NA | Operational | NA | 2020-05-04 | 2020-12-31 | 2022-06-13 | Weather | NA | FALSE | 6052.048 | NA ¦ NA | 8569.7065 | 1815.8743 | 1495.8071 | 109.4131 | -0.12432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2022 ¦ 2023 ¦ 2024 | 0 | 8460.4178 | 109.4131 | -0.12432 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [Reason for Change in In-Service Date] In-service dates are estimated during preliminary design and permitting stages of a project; date shifted to reflect actual design and construction schedule.
222 | [Programmatic] IT Enterprise Network Operation Support |  |  | Multiple | IT Enterprise Network Operation Support | Other - IT | New | Multiple Options [See Notes] | NA | Other [See Notes] | System Operations | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | NA | NA | NA | Multiple | Multiple | 79 | 925 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-12-09 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | NA | NA | NA [See Notes] | NA | Operational | NA | NA | 2025-12-31 | Multiple | NA | NA | TRUE | NA | NA ¦ NA | 38053.6104 | 861.883 | 1373.2652 | 1288.9571 | 1655.3502 | 1166.5918 | 0 | 3740.7851 | 3772.763 | 3205.2692 | 2791.077 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 ¦ 2026 | 667.6486 | 1497.317 | 1088.4337 | 1065.3399 | 2027.3083 | 3740.7851 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [Proj Descrip- Action Taken (2)] new replace, upgrade/retrofit [Primary Purpose] Age/End of Life and Reliability
223 | Data Center Network Core Implementation |  |  | Multiple | Replacing End of Support Data Centers | Other - IT | Replace | Upgrade/Retrofit | NA | Age/End of Life | Age/Condition | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | NA | NA | NA | T000021 | P000021 | 1 | 925 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-10-14; 2020-10-14 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | NA | NA | To be Filed | NA | Operational | NA | 2020-09-30 | 2021-07-31 | 2024-12-31 | NA | NA | FALSE | 16033.1912 | NA ¦ NA | 3689.9031 | 1179.2323 | 581.6243 | 415.6746 | 261.4921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2023 ¦ 2024 | 0 | 0 | 957.3909 | 2732.5123 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0%
224 | SDGE LAN Refresh |  |  | Multiple | Replacing End of Support SDGE IT Network Hardware | Other - IT | Replace | NA | NA | Age/End of Life | Age/Condition | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | NA | NA | NA | T19005 | PT19005 | 1 | 925 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-03-20 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | NA | NA | NA [See Notes] | NA | Operational | NA | 2019-03-15 | 2019-12-31 | 2023-02-28 | NA | NA | FALSE | 4104.536 | NA ¦ NA | 3245.0817 | 661.6256 | 91.0149 | 7.454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 | 3146.6129 | 91.0149 | 7.454 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] NA
225 | SDGE WAN and PNER Network Refresh |  |  | Multiple | Replacing End of Support SDGE IT Network Hardware, Retrofit Communications Towers | Other - IT | Replace | Upgrade/Retrofit | NA | Age/End of Life | System Operations | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | NA | NA | NA | T19027 | PT19027 | 1 | 925 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-07-02 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | NA | NA | To be Filed | NA | Operational | NA | 2019-07-28 | 2019-12-31 | 2024-03-31 | NA | NA | FALSE | 3665.389 | NA ¦ NA | 2416.3344 | 634.0038 | 580.1764 | 21.156 | -0.00028957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2022 ¦ 2023 ¦ 2024 | 0 | 2395.1787 | 21.156 | -0.00028957 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0%
226 | Distributed Communications Reliability Initiative |  |  | Multiple | Install a Private LTE network to serve HFTD 2 and 3 | Other - Operations Tech | New | Upgrade/Retrofit | NA | Reliability | System Operations | NA | NA | NA | NA | NA | NA | NA | Tier 2 ¦ Tier 3 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | NA | NA | NA | T18018 | PT18018 | 1 | 925 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2018-09-06; 2019-12-02 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | NA | NA | NA [See Notes] | NA | Operational | NA | 2018-09-27 | 2020-10-31 | 2022-12-31 | NA | NA | FALSE | 16219.699 | NA ¦ NA | 1295.8398 | 99.2211 | 4.0466 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 | 1291.7932 | 4.0466 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] NA [Project Description - What] Reliability and Wildfire Mitigation
227 | NEW: SDGE Microwave Backhaul 2028 (P) |  |  | Multiple | Project ensures the Field Area Network core is upgraded/updated. Essential for effective monitoring of our grid. | Other - IT | Replace | Upgrade/Retrofit | NA | Age/End of Life | System Operations | NA | NA | NA | NA | NA | NA | NA | Tier 1 ¦ Tier 2 ¦ Tier 3 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | NA | NA | NA | BD25190 | NA | 1 | 925 | NA ¦ NA ¦ NA ¦ NA | TRUE | NA | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | NA | NA | NA [See Notes] | NA | Planning | NA | NA | 2028-12-31 | NA | NA | NA | FALSE | 1472.4551 | NA ¦ NA | 1472.4551 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1472.4551 | 0 | 0 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] NA
228 | NEW: SDGE Microwave Backhaul 2026 (P) |  |  | Multiple | Project mitigates 6ghz interference by upgrading/updates the microwave backhaul used within our territory | Other - IT | Replace | Upgrade/Retrofit | NA | Age/End of Life | System Operations | NA | NA | NA | NA | NA | NA | NA | Tier 1 ¦ Tier 2 ¦ Tier 3 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | NA | NA | NA | BD25149 | NA | 1 | 925 | NA ¦ NA ¦ NA ¦ NA | TRUE | NA | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | NA | NA | NA [See Notes] | NA | Planning | NA | NA | 2028-12-31 | NA | NA | NA | FALSE | 1041.8435 | NA ¦ NA | 1041.8435 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1041.8435 | 0 | 0 | 0 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] NA
229 | NEW: 2027 SDGE DC Edge Switching Refresh (P) |  |  | Multiple | Project mitigates 6ghz interference by upgrading/updates the microwave backhaul used within our territory | Other - IT | Replace | Upgrade/Retrofit | NA | Age/End of Life | System Operations | NA | NA | NA | NA | NA | NA | NA | Tier 1 ¦ Tier 2 ¦ Tier 3 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | NA | NA | NA | BD25130 | NA | 1 | 925 | NA ¦ NA ¦ NA ¦ NA | TRUE | NA | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | NA | NA | NA [See Notes] | NA | Planning | NA | NA | 2027-12-31 | NA | NA | NA | FALSE | 1472.4551 | NA ¦ NA | 1472.4551 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1472.4551 | 0 | 0 | 0 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] NA
230 | NEW: 2026 SDGE F5 Refresh (P) |  |  | Multiple | Project updates/upgrades our switches used to protect and route on the edge of our data center | Other - IT | Replace | Upgrade/Retrofit | NA | Age/End of Life | Age/Condition | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | NA | NA | NA | BD25125 | NA | 1 | 925 | NA ¦ NA ¦ NA ¦ NA | TRUE | NA | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | NA | NA | NA [See Notes] | NA | Planning | NA | NA | 2027-12-31 | NA | NA | NA | FALSE | 1032.0992 | NA ¦ NA | 1032.0992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1032.0992 | 0 | 0 | 0 | 0 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] NA
231 | NEW: 2027 SDGE Cloud NGFW Cost Optimization (P) |  |  | Multiple | System refresh and upgrade on the f5 hardware within the Data Center | Other - IT | Replace | Upgrade/Retrofit | NA | Age/End of Life | Age/Condition | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | NA | NA | NA | BD25094 | NA | 1 | 925 | NA ¦ NA ¦ NA ¦ NA | TRUE | NA | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | NA | NA | NA [See Notes] | NA | Planning | NA | NA | 2027-12-31 | NA | NA | NA | FALSE | 1063.1425 | NA ¦ NA | 1063.1425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1063.1425 | 0 | 0 | 0 | 0 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] NA
232 | NEW: 2028 SDGE Network Modernization (P) |  |  | Multiple | Critical enablement to gain cost efficiencies and improve our gateways to the cloud. | Other - IT | Replace | Upgrade/Retrofit | NA | Age/End of Life | System Operations | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | NA | NA | NA | BD25077 | NA | 1 | 925 | NA ¦ NA ¦ NA ¦ NA | TRUE | NA | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | NA | NA | NA [See Notes] | NA | Planning | NA | NA | 2027-12-31 | NA | NA | NA | FALSE | 1612.9246 | NA ¦ NA | 1612.9246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1612.9246 | 0 | 0 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] NA
233 | NEW: 2027 SDGE Network Modernization (P) |  |  | Multiple | Project upgrades/updates the network switches that serve our corporate sites. Critical updates are needed to mitigate EOL systems | Other - IT | Replace | Upgrade/Retrofit | NA | Age/End of Life | System Operations | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | NA | NA | NA | BD25076 | NA | 1 | 925 | NA ¦ NA ¦ NA ¦ NA | TRUE | NA | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | NA | NA | NA [See Notes] | NA | Planning | NA | NA | 2028-12-31 | NA | NA | NA | FALSE | 1404.6809 | NA ¦ NA | 1404.6809 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1404.6809 | 0 | 0 | 0 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] NA
234 | NEW: 2027 SDGE DCN Refresh (P) |  |  | Multiple | Project upgrades/updates the network switches that serve our corporate sites. Critical updates are needed to mitigate EOL systems | Other - IT | Replace | Upgrade/Retrofit | NA | Age/End of Life | System Operations | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | NA | NA | NA | BD25075 | NA | 1 | 925 | NA ¦ NA ¦ NA ¦ NA | TRUE | NA | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | NA | NA | NA [See Notes] | NA | Planning | NA | NA | 2027-12-31 | NA | NA | NA | FALSE | 1898.9064 | NA ¦ NA | 1898.9064 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1898.9064 | 0 | 0 | 0 | 0 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] NA
235 | NEW: 2026 SDGE F5 Refresh (P) |  |  | Multiple | Project updates/upgrades the network switches/routes within our data center. Replaced end of life equipment. | Other - IT | Replace | Upgrade/Retrofit | NA | Age/End of Life | System Operations | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | NA | NA | NA | BD24037 | NA | 1 | 925 | NA ¦ NA ¦ NA ¦ NA | TRUE | NA | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | NA | NA | NA [See Notes] | NA | Planning | NA | NA | 2027-12-31 | NA | NA | NA | FALSE | 1213.4625 | NA ¦ NA | 1213.4625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1213.4625 | 0 | 0 | 0 | 0 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0%
236 | TL690E – Camp Pendleton – Wood to Steel |  |  | Camp Pendleton, San Diego | Replace approx. 69 wood poles with overhead steel poles and/or underground cabling. Reconductor approx. 5.5 mi from Stuart Tap to Las Pulgas Substation. | Transmission Line - Multiple | Replace | Upgrade/Retrofit | NA | Wildfire Mitigation | T-Line Reliability | NERC TPL Standards | NA | 2025-01-12 | 58.5556 | Steady State Power Flow System Analysis | Wires - Reconductor/Line Rebuild Alternative | NA | Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | OPEN, Coastal |  | 5.350611 | NA | 69 | NA | 1.2 | 2014-00050-ZZ | QS00040 | 1 | 10143 | NA ¦ NA ¦ NA ¦ NA | FALSE | NA | Work Order Authorization | 2012 | 2014 | FALSE | 2014 | NA | https://www.caiso.com/planning/Pages/TransmissionPlanning/2013-2014TransmissionPlanningProcess.aspx | FALSE | NA | NA | Exempted | NA | CPUC | MCBCP | Exempt | NA | NA [See Notes] | NA | Engineering more than 50% complete | NA | 2028-03-16 | 2015-06-01 | 2029-03-21 | Permitting | NA | FALSE | 142840.7251 | NA ¦ NA | 47407.3096 | 1383.3476 | 1527.0309 | 1676.1514 | 1964.336 | 1110.599 | 1302.3385 | 2565.8737 | 7055.0634 | 20054.1382 | 2973.9345 | 0 | 7661.4649 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | 4.8 | NA | 0% | 100% | [CPUC Status] Exempt
237 | TL691 Avocado to Camp Pendleton |  |  | Fallbrook, San Diego ¦ Camp Pendleton North, San Diego ¦ Fallbrook Naval Weapons Station | This project will replace approx 140 existing wood poles along TL691 within the Fire Threat Zone with new steel poles and associated hardware. | Transmission Line - Multiple | Replace | NA | NA | Wildfire Mitigation | T-Line Reliability | NA | NA | 2025-01-12 | 50.4247 | NA | NA | NA | Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 11.548521 | NA | 69 | NA | 1.2 | 2014-00051-ZZ | QS00041 | 1 | 10144 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2022-12-19 | Work Order Authorization | 2012 | NA | FALSE | NA | NA | NA | FALSE | NA | 2019-11-01 | Exempted | Categorical Exclusion | CPUC | MCBCP | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2023-04-28 | 2024-02-29 | 2024-01-17 | NA | NA | FALSE | 43446.3952 | NA ¦ NA | 47153.3988 | 3971.736 | 2405.8417 | 28254.1162 | 6952.0503 | 349.2255 | 194.8862 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2024 ¦ 2025 | 0 | 0 | 0 | 46609.287 | 544.1117 | 0 | 0% | NA ¦ NA | 4.1 | NA | 0% | 100% | [CPUC Status] Exempt
238 | TL692 Horno Pulgas (Camp Pend) |  |  | Camp Pendleton, San Diego | This project will replace approx 87 existing wood poles along TL692 within the Fire Threat Zone with new steel poles and associated hardware. | Transmission Line - Multiple | Replace | NA | NA | Wildfire Mitigation | T-Line Reliability | NA | NA | 2025-01-12 | 58.9452 | NA | NA | NA | Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 6.653334 | NA | 69 | NA | 1.2 | 2014-00225-ZZ | QS00042 | 1 | 10145 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-02-19 | Work Order Authorization | 2012 | 2014 | FALSE | NA | NA | NA | FALSE | NA | 2019-07-19 | Exempted | Categorical Exclusion | CPUC | MCBCP | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2021-05-17 | 2021-11-01 | 2021-11-01 | NA | NA | FALSE | 24755.7706 | NA ¦ NA | 17797.8315 | 11169.0268 | 1339.9907 | 43.5217 | 3.2178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 | 16411.1014 | 1339.9907 | 43.5217 | 3.2178 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
239 | TL695/6971 Talega Cristianitos Japanese (Camp Pend) |  |  | Camp Pendleton, San Diego | Replace approximately 72 existing poles with 69 new steel poles and install approximately 9.7 miles of 69kV conductor and approximately 2.5 miles of distribution underbuild between Talega Substation to Basilone Substation (TL695) and the prior Japanese Mesa Substation location to Basilone substation (Originally TL6971 but now TL692). Approximately 2.4 miles of TL695 is being rerouted onto an existing tower line occupied by TL99904 (2.5 miles) and that section of TL99904 will become TL692. | Transmission Line - Multiple | Replace | New | NA | Wildfire Mitigation | T-Line Reliability | NERC TPL Standards | NA | 2025-05-30 | 54.7193 | Steady State Power Flow System Analysis | Wires - Reconductor/Line Rebuild Alternative | NA | Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | OPEN, Coastal |  | 7.800761 | NA | 69 | NA | 1.2 | 2014-00074-ZZ | QS00043 | 1 | 10146 | NA ¦ NA ¦ NA ¦ NA | FALSE | NA | Work Order Authorization | 2012 | 2012 | FALSE | 2012 | NA | https://www.caiso.com/planning/Pages/TransmissionPlanning/2011-2012TransmissionPlanningProcess.aspx | FALSE | CEQA Draft Published | 2017-07-07 | IS/MND | EA | CPUC | MCBCP | PTC | 2016-04-25 | Approved | 2018 | Permitting | NA | 2026-04-21 | 2028-01-26 | 2028-01-26 | Project Design | Permitting | FALSE | 44272.5792 | NA ¦ NA | 61009.284 | 2875.0483 | 2320.4083 | 1770.8854 | 1940.217 | 979.0072 | 1272.1542 | 12420.9075 | 25341.4697 | 4777.2047 | 0 | 0 | 17065.2641 | NA | NA | 2023 | 0 | 0 | 132.2838 | 0 | 0 | 0 | 0% | NA ¦ NA | 1.4 | NA | 0% | 100% | [Reason for Change in In-Service Date] Design
240 | TL6912 San Luis Rey to Camp Pendleton |  |  | Camp Pendleton, San Diego | This project will replace approx 78 existing wood poles along TL6912 within the Fire Threat Zone with new steel poles and associated hardware. | Transmission Line - Multiple | Replace | Upgrade/Retrofit | NA | Wildfire Mitigation | T-Line Reliability | NA | NA | 2025-01-12 | 64.0685 | NA | NA | NA | Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 7.505768 | NA | 69 | NA | 1.2 | 2014-00073-ZZ | QS00045 | 1 | 10149 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-07-26 | Work Order Authorization | 2012 | NA | FALSE | NA | NA | NA | FALSE | NA | 2017-12-01 | Exempted | Categorical Exclusion | CPUC | MCBCP | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2020-01-27 | 2020-09-04 | 2020-09-04 | NA | NA | FALSE | 23135.8596 | NA ¦ NA | 14701.5855 | 1266.3612 | -375.0751 | 98.0092 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 | 1283.0638 | -372.9957 | 98.0092 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
241 | TL663 Reconductor (Mission Kearny) |  |  | San Diego, San Diego | Construction of this project provides a long term “wires” mitigation for the identified NERC CAT B reliability criteria indications. Availability of the short term non wires option of depending on the pre contingency dispatch of the Kearny gas turbines to provide loading relief is no longer available after 2013. | Transmission Line - Conductor | Upgrade/Retrofit | NA | NA | Local Capacity Requirement | T-Line Capacity | NERC TPL Standards | NA | 2025-02-15 | 29; 61; 39 | Steady State Power Flow System Analysis | Wires - Reconductor/Line Rebuild Alternative | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 6.590164 | NA | 69 | NA | 2.1 | 2011-00018-ZZ | QS00049 | 1 | 11126 | NA ¦ NA ¦ NA ¦ NA | FALSE | NA | Work Order Authorization | 2012 | 2011 | FALSE | 2011 | NA | https://www.caiso.com/planning/Pages/TransmissionPlanning/2010-2011TransmissionPlanningProcess.aspx | FALSE | NA | TBD | Exempted | NA | NA | NA | Advice Letter | 2017-05-31 | Approved | 2017 | Operational | NA | 2017-12-13 | 2015-06-01 | 2020-02-26 | Bundling Dependencies | Permitting | FALSE | 8171.0385 | NA ¦ NA | 39939.9122 | 249.7861 | 550.5743 | 59.2286 | 39.4769 | -0.04309 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 1177.3096 | 590.6773 | 59.2286 | 39.4769 | -0.04309 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
242 | TL644 Reconductor (Bay Blvd Sweetwater) |  |  | National City, San Diego ¦ Chula Vista, San Diego | The purpose of the TL644 Reconductor Project is to improve the reliability of the Transmission System by mitigating potential NERC Category B Criteria violations. The Project will increase the ampacity of TL644 to 204MVA (1,708A) by replacing the single-circuit underground 1750kCMIL aluminum cable to a twin-circuit underground 3000kCMIL copper cable system. Upon completion, the upgrades will mitigate overloads on TL644 in the event of an outage on TL642. | Transmission Line - Conductor | Upgrade/Retrofit | NA | NA | Reliability | T-Line Capacity | NERC TPL Standards | NA | 2025-02-08 | 26; 26 | Steady State Power Flow System Analysis | Wires - Reconductor/Line Rebuild Alternative | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | Coastal |  | 1 | NA | 69 | NA | 2.1 | 2011-00021-ZZ | QS00054 | 1 | 11154 | NA ¦ NA ¦ NA ¦ NA | FALSE | NA | Work Order Authorization | 2012 | 2011 | FALSE | 2011 | NA | https://www.caiso.com/planning/Pages/TransmissionPlanning/2010-2011TransmissionPlanningProcess.aspx | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | Approved | 2019 | Operational | NA | 2021-12-06 | 2013-06-01 | 2022-05-15 | Prioritization | Prioritization | FALSE | 9464.457 | NA ¦ NA | 10805.1556 | 2906.133 | 2524.9442 | 709.313 | 72.0071 | 1.5855 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 0 | 10022.2501 | 709.313 | 72.0071 | 1.5855 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
243 | TL639 Wood to Steel Replacement |  |  | San Diego, San Diego | The TL639 Fire Hardening and Reconductor Project consists of installing new steel structures along the 69kV tie line between Elliott Substation and Structure Z100981, located inside Sycamore Canyon. The replacement structures from TL639 Elliott to Structure Z379545 will be constructed in conjunction with TL636, since most of the structures in that portion are single pole double circuit. TL639 Wood to Steel will cover pole replacements starting at Sycamore Canyon Substation to Structure Z379545. The project spans approximately 4.8 miles. | Transmission Line - Multiple | Replace | Upgrade/Retrofit | NA | Wildfire Mitigation | Priority 1 Steel Structure Replacement | NA | NA | 2025-09-30 | 41.7273 | NA | NA | NA | Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 8.176705 | NA | 69 | NA | 1.2 | 2012-00005-ZZ | QS00066 | 1 | 12136 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-09-18 | Work Order Authorization | 2015 | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | CPUC | NA | Exempt | NA | To be Filed | NA | Operational | NA | 2022-10-31 | 2024-01-31 | 2023-10-07 | NA | NA | FALSE | 241.5125 | NA ¦ NA | 12774.7862 | 874.9164 | 2296.9075 | 7361.9751 | 894.4513 | 65.3511 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 0 | 53.9001 | 1.445 | 12654.0899 | 65.3511 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
244 | TL6916 Wood to Steel Replacement |  |  | San Diego, San Diego | Approximately 5 miles of fire hardening on TL6916 wood to steel project. All existing wood transmission poles will be removed from service/replaced with pre-engineered poles or engineered steel poles and associated distribution wood poles on C434 and C920 will be replaced with steel poles. New conductor 900ACSS will replace existing 900ACSS conductor due to construction and outage constraints of existing configuration. Distribution conductor will be upgraded to 636 and #2 ACSR Conductor. 1-96CT ADSS will be installed from Z678465 to Z100980. 31 new SW poles will be installed along with 12 new engineered steel poles. We predict 9 drilled pier foundations and 3 new micropile foundations will be installed. | Transmission Line - Pole/Tower | Replace | NA | NA | Wildfire Mitigation | T-Line Reliability | NA | NA | 2025-08-21 | 47.8049 | NA | NA | NA | Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 4.767863 | NA | 69 | NA | 1.2 | 2012-00006-ZZ | QS00067 | 1 | 12137 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-07-22 | Work Order Authorization | 2015 | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | Approved | 2021 | Operational | NA | 2022-03-07 | 2022-07-01 | 2022-07-11 | NA | NA | FALSE | 104.0282 | NA ¦ NA | 14675.0997 | 1495.1294 | 11255.3314 | 221.3696 | 64.1849 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2022 ¦ 2023 ¦ 2024 | 0 | 14371.4153 | 239.4994 | 64.1849 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
245 | TL615 TL659 Direct Buried Cable Replacement (Cabrillo Point Loma) |  |  | San Diego, San Diego | Replace approximately six (6) miles of direct buried cable on TL615 and TL659 within the streets of Point Loma into a new double circuit 69kV duct package infrastructure with off-setting substructures in an effort to mitigate reliability issues associated with aging direct buried cable systems. | Transmission Line - Underground | Upgrade/Retrofit | NA | NA | Reliability | Age/Condition | NA | NA | 2025-05-23 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 4 | NA | 69 | NA | 4.1 | 2012-00011-ZZ | QS00068 | 1 | 12138 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-07-03 | Work Order Authorization | 2012 | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | 2024-12-13 | Approved | 2024 | Construction (25%-50%) | NA | 2024-10-30 | 2026-12-31 | 2026-06-30 | Land Rights | Land Rights | TRUE | 46528 | NA ¦ NA | 88275.8525 | 13695.3243 | 2707.0372 | 4920.9316 | 13359.7809 | 27275.0732 | 7988.386 | 10117.6776 | 0 | 0 | 0 | 0 | 70169.7889 | NA | NA | 2026 | 0 | 0 | 0 | 0 | 0 | 88275.8525 | 0% | NA ¦ NA | 6.00 | NA | 0% | 100%
246 | TL636 Wood to Steel Replacement |  |  | San Diego, San Diego | Replacing wood pole with steel equivalent from Northern structure at Z200694 to Elliott Substation. The purpose for this project is for fire hardening of this corridor due to it being within the FTZ and classified as high to extreme fire danger. The project spans approximately 6.07 miles. | Transmission Line - Multiple | Replace | Upgrade/Retrofit | NA | Wildfire Mitigation | Priority 1 Steel Structure Replacement | NA | NA | 2025-10-20 | 46.1475 | NA | NA | NA | Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 5.86719 | NA | 69 | NA | 1.2 | 2012-00015-ZZ | QS00071 | 1 | 12144 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2022-05-19 | Work Order Authorization | 2015 | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | CPUC | NA | Exempt | NA | To be Filed | NA | Operational | NA | 2022-03-18 | 2022-12-31 | 2022-10-17 | NA | NA | FALSE | 25131.9882 | NA ¦ NA | 21549.7771 | 2745.577 | 15752.6745 | 152.8457 | 100.6546 | 29.5206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 0 | 21266.7562 | 152.8457 | 100.6546 | 29.5206 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
247 | TL694 Wood to Steel Replacement |  |  | Fallbrook, San Diego ¦ Oceanside, San Diego | This project replaces 4.8 miles, approximately 80 wood structures, to direct-embed and engineered steel poles and replace the existing 636 ASCR/AW conductor to harden the electric transmission and distribution systems and increase reliability in the region. This project will also mitigate some existing access issues to the structures. | Transmission Line - Pole/Tower | Replace | NA | NA | Wildfire Mitigation | T-Line Reliability | NA | NA | 2025-01-30 | 61.4051 | NA | NA | NA | Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 4.85 | NA | 69 | NA | 1.2 | 2012-00014-ZZ | QS00073 | 1 | 12149 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-11-06 | Work Order Authorization | 2015 | NA | FALSE | NA | NA | NA | FALSE | TBD | TBD | Exempted | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Permitting | NA | 2026-01-01 | 2020-12-31 | 2026-12-18 | Material | Material | TRUE | 36464.0897 | NA ¦ NA | 35265.4221 | 720.4648 | 576.5602 | 639.7541 | 2933.1438 | 775.1766 | 2294.4478 | 25374.638 | 0 | 0 | 0 | 0 | 7596.3362 | NA | NA | 2026 | 0 | 0 | 0 | 0 | 0 | 35265.4221 | 0% | NA ¦ NA | 11.6 | NA | 0% | 100%
248 | TL13831 Wood to Steel Replacement (Talega Racho Mission Viejo) |  |  | Orange County | The purpose of project is to replace approximately 72 wood poles for steel equivalent from Rancho Mission Viejo to Talega Substation for fire hardening. The project spans approximately 6.46 miles. | Transmission Line - Multiple | Replace | Upgrade/Retrofit | NA | Wildfire Mitigation | Priority 1 Wood Structure Replacement | NA | NA | 2025-04-16 | 29.2055 | NA | NA | NA | Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 6.377019 | NA | 138 | NA | 1.2 | 2012-00019-ZZ | QS00074 | 1 | 12150 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-12-05 | Work Order Authorization | 2015 | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | CPUC | NA | Exempt | NA | NA | NA | Operational | NA | 2022-08-15 | 2024-12-30 | 2023-04-23 | NA | NA | FALSE | 317.2364 | NA ¦ NA | 21781.5058 | 2288.5516 | 11949.8744 | 5638.7274 | 101.9908 | 34.6912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 2280.3549 | 11932.3906 | 5667.4972 | 101.9908 | 34.6912 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
249 | TL13838 Wood to Steel Replacement (Magarita Rancho Mission Viejo) |  |  | Orange County | This project replaces nine poles with steel, approximately 1.4 miles of 1033.5ACSR/AW, insulators and hardware. | Transmission Line - Multiple | Replace | Upgrade/Retrofit | NA | Wildfire Mitigation | Priority 1 Steel Structure Replacement | NA | NA | 2025-03-10 | 29; 29; 29; 29; 8; 29; 29; 29; 11; 2 | NA | NA | NA | Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 1.674834 | NA | 138 | NA | 1.2 | 2012-00020-ZZ | QS00075 | 1 | 12152 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-11-06 | Work Order Authorization | 2015 | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | CPUC | NA | Exempt | NA | To be Filed | NA | Operational | NA | 2021-09-24 | 2024-12-30 | 2022-01-17 | NA | NA | FALSE | 249.9409 | NA ¦ NA | 2579.386 | 1149.8398 | 408.9902 | 232.709 | 1.4772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 | 1146.3368 | 412.4949 | 232.709 | 1.4772 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
250 | TL600 Reliability Pole Replacements |  |  | San Diego, San Diego | This project replaces 32 transmission and 1 distribution structures to current standards on TL600 across 3 phases of work. | Transmission Line - Pole/Tower | Replace | Upgrade/Retrofit | NA | Reliability | T-Line Reliability | NA | NA | 2025-02-15 | 56.1429 | NA | Wires - Reconductor/Line Rebuild Alternative | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 3.999067 | NA | 69 | NA | 4.1 | 2012-00023-ZZ | QS00077 | 1 | 12156 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-10-06 | Work Order Authorization | 2015 | NA | FALSE | NA | NA | NA | FALSE | Expected PEA Completion | TBD | Exempted | NA | NA | NA | Exempt | NA | Approved | 2018 | Operational | NA | 2013-02-01 | 2021-04-30 | 2022-08-29 | Vendor Quality/Delays | Permitting | FALSE | 1260.0786 | NA ¦ NA | 8349.7901 | 1913.5322 | 1043.6201 | 406.0304 | 465.9009 | 53.6172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 0 | 6109.9589 | 406.0304 | 465.9009 | 53.6172 | 0 | 93% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
251 | TL674A Loop in Del Mar |  |  | Del Mar, San Diego ¦ Solano Beach, San Diego ¦ San Diego, San Diego | Eliminate the need for ongoing O&M work in environmentally sensitive areas (San Dieguito Lagoon, Torrey Pines State Park and Los Penasquitos Lagoon) by removing TL666D from service (Phase IV). Install a new underground 69kV transmission line segment along Via de la Valle, which will provide a new TL connecting the Del Mar Substation to the North City West Substation. This will replace the existing TL 674A tap that will be eliminated in Phase II as part of the Rancho Santa Fe Tap reconfiguration. | Transmission Line - Multiple | Upgrade/Retrofit | Relocate | NA | Reliability | Environmental | NA | NA | 2025-11-13 | NA | Steady State Power Flow System Analysis | Wires - Replacement Alternative | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 7.248895 | NA | 69 | NA | 2.1 | 2013-00010-ZZ | QS00082 | 1 | 13130 | NA ¦ NA ¦ NA ¦ NA | FALSE | NA | Work Order Authorization | 2015 | 2013 | FALSE | 2013 | NA | https://www.caiso.com/planning/Pages/TransmissionPlanning/2012-2013TransmissionPlanningProcess.aspx | FALSE | Final Certified | 2019-03-21 | IS/MND | NA | CPUC | NA | PTC | 2017-06-28 | Approved | 2019 | Operational | NA | 2020-12-30 | 2015-06-01 | 2023-12-15 | Permitting | NA | FALSE | 17532.6862 | NA ¦ NA | 28191.135 | 3327.1239 | 16089.0943 | 1267.4146 | 167.5427 | 63.0297 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 0 | 26693.2096 | 1267.4146 | 167.5427 | 63.0297 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [Reason for Change in In-Service Date] In-service dates are estimated during preliminary design and permitting stages of a project; date shifted to reflect actual design and construction schedule.
252 | CBM Gas Breakers |  |  | Multiple | This project is a continuing effort to sustain GCB SF6 Tracking and implement Condition Based Maintenance by installing monitors on approximately 900 Gas Circuit Breakers (GCBs). | Substation - Circuit Breaker | Upgrade/Retrofit | NA | NA | Reliability | Age/Condition - Replace Breakers | NA | NA | NA | NA | NA | NA | NA | Tier 1 ¦ Tier 2 ¦ Tier 3 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69 ¦500 | NA | 4.3 | NA | QS00086 | 1 | 13139 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-09-21 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | CPUC | NA | NA | NA | NA [See Notes] | NA | Operational | NA | NA | 2025-12-31 | Multiple | NA | NA | FALSE | 2971.124 | NA ¦ NA | 33768.7644 | 5194.7858 | 2671.1227 | 2323.3223 | 2073.2266 | 1068.4581 | 1184.4691 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 3570.9276 | 3687.4675 | 1351.3365 | 917.8003 | 12769.694 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 13.55% | 86.45% | [CPUC Status] NA
253 | Streamview |  |  | San Diego, San Diego | Initially expand the existing 69 ¦12 kV substation from two to three banks to increase capacity on the system, with future expansion to four banks. | Transmission Line/Substation | Upgrade/Retrofit | New | NA | Reliability | Age/Condition | NA | NA | 2025-10-13 | 22; 55; 22; 53; 7; 3 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 0.388157 | 69 | 12kV ¦69kV ¦28MVA | 4.2 | 2014-00062-ZZ | QS00089 | 1 | 13244 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-12-19 | Work Order Authorization | 2015 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | Categorical Exclusion | CPUC | NA | Exempt | NA | NA [See Notes] | 2020 | Construction (10%-25%) | NA | 2020-03-11 | 2027-05-31 | 2027-08-31 | Permitting | NA | TRUE | 543 | NA ¦ NA | 46168.5865 | 761.4417 | 3181.6008 | 2184.3822 | 10982.4692 | 4263.1486 | 5349.1563 | 10051.0554 | 2486.4888 | 0 | 0 | 0 | 124.3633 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2025 ¦ 2026 | 3622.8086 | 299.6637 | 33.7723 | 0 | 29550.4343 | 4856.1524 | 0% | NA ¦ NA | 5.16 | NA | 0% | 100% | [CPUC Status] Exempt
254 | Artesian 230kV Sub Expansion |  |  | San Diego, San Diego | Per the CAISO 2013-2014 Final Plan, SDG&E will expand the existing 69 ¦12kV Artesian Substation to a 230 ¦69 ¦12kV Substation (Artesian East Substation) to alleviate the existing 69kV congestion at Sycamore Canyon Substation. In addition, the project will help mitigate Cat B contingencies and increase reliability to the Poway Area Load Pocket which is expected to grow by as much as 12% in the next 10 years. The project will be built on existing SDG&E Artesian Substation land and adjacent land east of the current substation site, also owned by SDG&E. Transmission work includes the loop-in of TL23051 (SX-PEN), terminating TL616C into the Artesian 69kV substation to form two (2) 69 kV Artesian - Bernardo lines; reconductoring both Artesian - Bernardo lines to achieve a 145 ¦179 rating (TL6939 & segment of TLNew), and replacing underground getaways at Artesian, Bernardo, Rancho Carmel, and Poway to achieve new ratings. Permitting and Environmental will be required for the expanded 230 ¦69 ¦12kV substation, in addition to the reconductor work associated with the project. | Substation - Multiple | Upgrade/Retrofit | NA | NA | Reliability | Substation Capacity | NERC TPL Standards | NA | 2025-11-19 | 22; 22; 22; 16; 24; 16; 24; 16; 24; 16; 16 | Steady State Power Flow System Analysis | Wires - Bus Upgrade Alternative | NA | Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 1.937683 | 230 | 69kV ¦230kV ¦224MVA | 2.1 | 2014-00056-ZZ | QS00099 | 1 | 14128 | NA ¦ NA ¦ NA ¦ NA | FALSE | NA | Work Order Authorization | 2015 | 2014 | FALSE | 2014 | NA | https://www.caiso.com/planning/Pages/TransmissionPlanning/2013-2014TransmissionPlanningProcess.aspx | FALSE | Final Certified | 2019-03-22 | IS/MND | NA | CPUC | NA | PTC | 2019-10-07 | Approved | 2020 | Operational | NA | 2020-04-17 | 2016-06-01 | 2022-12-04 | Construction Delays | NA | FALSE | 17140 | NA ¦ NA | 132219.274 | 32690.8213 | 20376.5233 | 1653.6356 | 1245.4533 | 247.4774 | 156.8623 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 50361.7741 | 74652.8038 | 1653.6356 | 1245.4533 | 404.3398 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0%
255 | TL6975 Escondido San Marcos |  |  | San Marcos, San Diego ¦ Carlsbad, San Diego ¦ Lake San Marcos, San Diego ¦ Escondido, San Diego | Segment 1: Rebuild approximately 1.8 miles of an existing 69kV circuit (TL 680C) to create a double circuit from San Marcos Substation to Melrose Tap. Construction at San Marcos Substation including installation of a new circuit breaker par, seven piers, and an A-frame for the new line. Along Segment 1, all wood pole structures would be replaced with steel poles; porcelain insulators would be replaced with polymer insulators. Segment 2: Construct 2.8 miles of new single-circuit 69kV overhead power line on new steel poles in the existing transmission corridor from Melrose Tap to Meadowlark Junction adjacent to existing TL 13811/13825 power line, approximately 50-feet east of the centerline of the existing structures. Segment 3: Transition new line (described under Segment 2, above) and reconductor approximately 7.4 miles of power line; remove and replace existing copper conductors with new 636 ACSS/AW conductors and existing porcelain insulators with polymer insulators; construction at the existing Escondido Substation to accommodate new circuit. | Transmission Line - Multiple | New | NA | NA | Load Growth | New T-Line | NERC TPL Standards | NA | 2025-01-30 | NA | Steady State Power Flow System Analysis | Wires - New T-Line Alternative | NA | Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 11.903558 | NA | 69 | 69kV | 2.1 | 2014-00078-ZZ | QS00101 | 1 | 14137 | NA ¦ NA ¦ NA ¦ NA | FALSE | NA | Work Order Authorization | 2015 | 2014 | FALSE | 2014 | NA | https://www.caiso.com/planning/Pages/TransmissionPlanning/2013-2014TransmissionPlanningProcess.aspx | FALSE | Expected PEA Completion | 2018-03-16 | IS/MND | NA | NA | NA | PTC | 2017-11-15 | Approved | 2021 | Operational | NA | 2021-10-19 | 2015-06-01 | 2023-02-28 | Permitting | Land Rights | FALSE | 5626.42 | NA ¦ NA | 52334.2031 | 9221.2832 | 32210.4332 | 2820.3867 | 1777.4885 | 82.3247 | 2.7585 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 529.1659 | 332.0915 | 49610.3741 | 1777.4885 | 85.0832 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
256 | TL698 W2S PROJECT |  |  | Fallbrook, San Diego | The TL698 Fire Hardening & Reconductor Project consists of replacing existing structures and installing new steel structures along the 69kV tie line 698 in FTZ from Z10213, north of Monserate Substation, to structure Z293941, south of Avocado Substation, with new light duty and heavy engineered steel poles. This project is needed to mitigate loss of service due to wildfires by replacing existing wood poles with new steel structures. The new steel poles shall be designed to 138kV specifications and accommodate existing and future 12kV distribution underbuild and communications circuits. TL698 is located within existing easements. TL698 will be designed for (3)-636 ACSS/AW conductors and the existing 336 ACSR/AW conductors will be retired. There will be one SDG&E 96-count ADSS and one position for a third party installed along the line from Z10212 to Z293941. Additional installs: P219762J Removals: P253660S, Z208037S, P253653S | Transmission Line - Pole/Tower | Replace | NA | NA | Wildfire Mitigation | 3rd Party Damage | NA | NA | 2025-09-22 | 48.6154 | NA | NA | NA | Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 5.16 | NA | 69 | NA | 1.2 | 2014-00009-ZZ | QS00103 | 1 | 14140 | 2025-12-10 ¦ NA ¦ NA ¦ NA | TRUE | 2025-04-30 | Work Order Authorization | 2023 | NA | FALSE | NA | NA | NA | FALSE | PEA Deemed Complete | NA | Exempted | NA | CPUC | NA | Exempt | NA | To be Filed | NA | Operational | NA | 2023-11-01 | 2024-08-31 | 2024-08-23 | Completed Early | Weather | FALSE | 28671.0689 | NA ¦ NA | 21219.6462 | 525.7454 | 1287.7238 | 5494.102 | 10217.1935 | 993.1611 | 1188.0141 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 2039.4517 | 1287.3471 | 3337.4987 | 12374.1735 | 2181.1752 | 0 | 0% | NA ¦ NA | 8.0 | NA | 0% | 100%
257 | Poway 69kV Substation Rebuild |  |  | Poway, San Diego | The purpose of this project is to rebuild Poway Substation to a low profile distribution substation with an ultimate capacity of 120MVA. The current substation consists of aging infrastructure, no SCADA control, and a control shelter that cannot accommodate new panels for any SCADA upgrades. Adding SCADA control and replacing old equipment will increase the reliability of this sub and allow room for any future expansion. Substation, Transmission, and Distribution work are required for this rebuild. Installing SCADA to Poway Sub will increase reliability by giving Mission Control remote access to operate the equipment. Replacing aging infrastructure also increases reliability. Building a new control shelter allows for any future expansion. | Substation - Multiple | Upgrade/Retrofit | Removal | NA | Reliability | Age/Condition | NA | NA | 2025-11-04 | 25; 32; 48; 32; 49; 51 | NA | Wires - Minimum Required Scope (spot repair) Alternative | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 0.369559229 | 69 | 120MVA | 4.1 | 2017-0095 | QS00104 | 1 | 14143 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-04-03 | Work Order Authorization | 2015 | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | To be Filed | NA | Operational | NA | 2015-10-26 | 2023-03-31 | 2018-11-06 | NA | NA | FALSE | 1727.9587 | NA ¦ NA | 21954.3998 | 389.6282 | 804.5641 | 10.3026 | -16.3174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 | 2.4422 | 1398.6141 | 10.3026 | -16.3174 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
258 | HATS Legacy Work Order |  |  | San Diego, San Diego | Obtain the necessary permits, environmental clearance and regulatory authority for the helicopter landing areas along our transmission system. Relocate approximately 6 existing Sunrise Tower Staging Access Pads (TSAP) to locations that are better suited for TCMs O&M requirements. Build platforms at approximately 12 of the TSAPs and create 8 new TSAPs at tower locations to ensure safer and more secure landing areas for TCM. Establish approximately 15 permanent staging/fly yard locations, one acre or less in size, at locations along Sunrise that will best meet TCMs needs. Many of these will be at the same fly yard locations utilized for construction of Sunrise. | Other | New | NA | NA | Other [See Notes] | Safety - Line Right of Way Access | NA | NA | NA | 45 | NA | NA | NA | Tier 3 ¦ Zone 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 230 ¦ 500 | NA | 1.3 | 2014-00060-ZZ | QS00105 | 1 | 14145 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-01-27 | Work Order Authorization | 2015 | 2019 | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2019-06-24 | 2021-12-31 | 2020-12-28 | NA | NA | FALSE | 499 | NA ¦ NA | 15086.375 | 4215.1246 | -185.8243 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 | 4215.1246 | -185.8243 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0% | [Primary Purpose] Remote access landing pads for transmission structures [CPUC Status] Exempt
259 | Rancho Santa Fe Substation Fire Hardening |  |  | Rancho Santa Fe, San Diego | The Rancho Santa Fe Substation fire hardening project will consist of removing the aging 69/4 kV substation, cutting it over to existing 12 kV circuits, replacing aging infrastructure on the 12kV and 69 kV equipment, replacing the 12 kV circuit getaways, replacing the 12.5 MVA 69/12 kV spare with a 28 MVA transformer, and installing distribution SCADA | Substation - Multiple | Upgrade/Retrofit | NA | NA | Reliability | Substation Reliability | NA | NA | 2025-11-10 | 66; 71; 63 | NA | Wires - Minimum Required Scope (spot repair) Alternative | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.120944 | NA | 69 | 69kV | 1.2 | 2014-00289-ZZ | QS00123 | 1 | 15246 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-03-05 | Work Order Authorization | 2015 | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | To be Filed | NA | Operational | NA | 2017-07-10 | 2020-11-18 | 2020-11-18 | NA | NA | FALSE | 5719.0763 | NA ¦ NA | 7937.0511 | 1461.0882 | 8.9299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 | 7548.5966 | 8.9299 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
260 | Mid Coast Trolley Electric |  |  | San Diego, San Diego | Mid-Coast: As part of SANDAGs Mid Coast Trolley Extension Project, SDG&E will be relocating multiple electric and gas services from the Santa Fe Depot in downtown San Diego to the University City community. | Transmission Line - Multiple | Relocate | NA | NA | Work Requested by Others | Facility Relocation | NA | NA | 2025-02-15 | 34.875 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 4.21246 | NA | 69 | NA | 3.1 | 2015-00016 | QS00125 | 1 | 15258 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-04-12 | Work Order Authorization | 2017 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2016-10-03 | 2022-02-03 | 2022-08-17 | Weather | NA | FALSE | 8347.5827 | NA ¦ NA | 7398.3173 | 1272.7225 | 2232.3897 | 392.8702 | 5.7645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 | 165.6965 | 3503.5331 | 392.8702 | 5.7645 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] NA
261 | TL605 Reconductor (Silvergate Urban) |  |  | San Diego, San Diego | Reconductor TL605 with 2-636ACSS (200MVA) or equivalent Note: there is an active project (ID:2015-00013; budget code: 16158) with ISD of 6/26/2024. This new summited cost request is to upgrade the current design line rating from 137 MVA to 200MVA | Transmission Line - Conductor | Upgrade/Retrofit | NA | NA | Local Capacity Requirement | Line Reconductoring | NERC TPL Standards | NA | 2025-02-11 | 17 | Steady State Power Flow System Analysis | Wires - Reconductor/Line Rebuild Alternative | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | Coastal |  | 2 | NA | 69 | NA | 2.1 | 2015-00013 | QS00144 | 1 | 16158 | NA ¦ NA ¦ NA ¦ NA | FALSE | NA | Work Order Authorization | 2017 | 2016 | FALSE | 2016 | NA | https://www.caiso.com/planning/Pages/TransmissionPlanning/2015-2016TransmissionPlanningProcess.aspx | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | Approved | 2023 | Operational | NA | 2024-01-15 | 2018-06-01 | 2024-11-20 | ISO Action | ISO Action | FALSE | 545 | NA ¦ NA | 32783.0052 | 5495.897 | 773.0469 | 8170.9024 | 15142.4978 | 2030.7541 | 564.9458 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2024 ¦ 2025 | 0 | 0 | 0 | 30129.8042 | 2653.2011 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
262 | TL632A Loop In (Granite) |  |  | El Cajon, San Diego ¦ Crest, San Diego ¦ Granite Hills, San Diego | Convert TL632 from a tap into Granite Substation to a loop-in. Based on routing study, underground along La Cresta Rd to Granite Substation is most feasible route. 1.9 miles of 69kV underground. | Transmission Line - Multiple | Upgrade/Retrofit | NA | NA | Reliability | T-Line Reliability | NERC TPL Standards | NA | 2025-02-11 | 19 | Steady State Power Flow System Analysis | Wires - System Configuration Alternative | $10 Mil -$15 Mil | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 2.5 | NA | 69 | NA | 2.1 | 2015-00005 | QS00158 | 1 | 17125 | NA ¦ NA ¦ NA ¦ NA | FALSE | NA | Work Order Authorization | 2017 | 2015 | FALSE | 2015 | NA | https://www.caiso.com/planning/Pages/TransmissionPlanning/2014-2015TransmissionPlanningProcess.aspx | FALSE | TBD | TBD | Exempted | NA | NA | NA | AL-4597-E | 2025-01-30 | Approved | 2025 | Permitting | NA | 2025-09-01 | 2017-06-01 | 2027-05-24 | Land Rights | Land Rights | TRUE | 14057.888 | NA ¦ NA | 56705.6804 | 333.8327 | 325.5874 | 7751.4818 | 1404.4027 | 745.1579 | 12413.3404 | 29550.5773 | 2001.337 | 0 | 0 | 0 | 12740.4257 | NA | NA | 2026 | 0 | 0 | 0 | 0 | 0 | 666.3075 | 0% | NA ¦ NA | 3.4 | NA | 0% | 100%
263 | TL611 Direct Buried Cable Replacement (Old Town Point Loma) |  |  | San Diego, San Diego | Direct-Buried Cable Replacement (Approx. 1-mile trench and substructures) | Transmission Line - Underground | Replace | NA | NA | Reliability | Age/Condition | NA | NA | 2025-02-11 | 58; 58 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | Coastal |  | 2 | NA | 69 | NA | 4.1 | 2012-0002-ZZ | QS00720 | 1 | 17127 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-11-25 | Work Order Authorization | 2017 | NA | FALSE | NA | NA | NA | FALSE | TBD | TBD | Exempted | NA | NA | NA | TBD | NA | To be Filed | 2027 | Engineering less than 50% complete | NA | 2027-12-02 | 2026-12-31 | 2028-04-05 | Outage | Outage | TRUE | 28043.924 | NA ¦ NA | 28043.924 | 0 | 0 | 112.2093 | 948.6228 | 454.7239 | 5705.9086 | 17180.2624 | 3642.197 | 0 | 0 | 0 | 1515.5559 | NA | NA | 2026 | 0 | 0 | 0 | 0 | 0 | 24401.727 | 0% | NA ¦ NA | 3.4 | NA | 0% | 100%
264 | TL603 Loop in (Sweetwater, National City, and Naval Station Metering) |  |  | National City, San Diego | Open Sweetwater Tap and make TL603D and TL603B one continuous 69kV line from national City to Sweetwater. | Transmission Line - Multiple | Upgrade/Retrofit | NA | NA | Reliability | T-Line Reliability | NERC TPL Standards | NA | 2025-02-28 | NA | Steady State Power Flow System Analysis | Wires - System Configuration Alternative | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 2 | NA | 69 | NA | 2.1 | 2015-00066 | QS00159 | 1 | 17129 | NA ¦ NA ¦ NA ¦ NA | FALSE | NA | Work Order Authorization | 2017 | 2013 | FALSE | 2013 | NA | https://www.caiso.com/planning/Pages/TransmissionPlanning/2012-2013TransmissionPlanningProcess.aspx | FALSE | TBD | TBD | Exempted | NA | CPUC | NA | Exempt | 2025-05-30 | Approved | 2025 | Permitting | NA | 2025-09-15 | 2017-06-01 | 2026-07-23 | Permitting | Permitting | TRUE | 13584.367 | NA ¦ NA | 50063.0054 | 5306.3214 | 210.5866 | 681.428 | 835.5795 | 497.1728 | 9533.231 | 30422.1665 | 0 | 0 | 0 | 0 | 10107.6078 | NA | NA | 2026 | 0 | 0 | 0 | 0 | 0 | 50063.0054 | 0% | NA ¦ NA | 4.3 | NA | 0% | 100% | [Project Description - What] TL603D (National City – Sweetwater Tap) and TL603B (Sweetwater – Sweetwater Tap) will be made into one continuous line segment running from National City to Sweetwater Substation to achieve a minimum continuous/emergency rating of 102 MVA. The project is expected to cost $10 to $12 million and the expected in-service date is June, 2017.
265 | TL690 Direct Buried Cable Replacement (Oceanside Oceanside Tap) |  |  | Oceanside, San Diego ¦ Camp Pendleton South, San Diego | Direct-Buried Cable Replacement. Approx. 1-mile trench and substructures. | Transmission Line - Underground | Replace | NA | NA | Reliability | Age/Condition | NA | NA | 2025-01-12 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 1.5 | NA | 69 | NA | 4.1 | 2014-00017-ZZ | QS00163 | 1 | 17142 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-08-31 | Work Order Authorization | 2017 | NA | FALSE | NA | NA | NA | FALSE | TBD | TBD | Exempted | NA | NA | NA | TBD | 2027-06-14 | To be Filed | 2027 | On Hold | NA | NA | 2028-11-13 | NA | NA | NA | FALSE | 905.761 | NA ¦ NA | 1094.04 | 0 | 0 | 0 | 127.688 | 162.7876 | 6.66 | 13.4642 | 13.6588 | 0 | 0 | 0 | 924.836 | NA | NA | 2024 ¦ 2025 | 0 | 0 | 0 | 140.9282 | -5.5072 | 0 | 0% | NA ¦ NA | 2.6 | NA | 0% | 100%
266 | TL628 Direct Buried Cable Replacement (Rancho Del Rey & H St.) |  |  | Chula Vista, San Diego | Direct-Buried Cable Replacement | Transmission Line - Underground | Replace | NA | NA | Reliability | Age/Condition | NA | NA | 2025-02-11 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 2 | NA | 69 | NA | 4.1 | 2017-0021 | QS00164 | 1 | 17143 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2018-09-04 | Work Order Authorization | 2018 | NA | FALSE | NA | NA | NA | FALSE | TBD | TBD | Exempted | NA | NA | NA | TBD | NA | To be Filed | 2027 | On Hold | NA | 2027-12-02 | 2021-04-01 | 2028-03-17 | NA | NA | FALSE | 360 | NA ¦ NA | 1303.3032 | 15.6756 | 54.4923 | 45.6665 | 8.6489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1303.3032 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | 3.7 | NA | 0% | 100% | [Reason for Change in In-Service Date] Project was put on hold for prioritization purposes and budget constraints.
267 | TL697 Direct Buried Cable Replacement (Oceaside Sub Getaway) |  |  | Oceanside, San Diego | Direct-Buried Cable Replacement | Transmission Line - Underground | Replace | NA | NA | Reliability | Age/Condition | NA | NA | 2025-02-08 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.5 | NA | 69 | NA | 4.1 | 2017-0025 | QS00167 | 1 | 17147 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-06-05 | Work Order Authorization | 2017 | NA | FALSE | NA | NA | NA | FALSE | TBD | TBD | Exempted | NA | NA | NA | TBD | 2027-03-24 | To be Filed | 2027 | On Hold | NA | NA | 2027-12-31 | NA | NA | NA | FALSE | 1500.416 | NA ¦ NA | 3923.802 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3567.5296 | 0 | 0 | 0 | 356.2724 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | 8.1 | NA | 0% | 100%
268 | TL667 Direct Buried Cable Replacement (El Camino Real) |  |  | San Diego, San Diego | Direct-Buried Cable Replacement | Transmission Line - Underground | Replace | NA | NA | Reliability | Age/Condition | NA | NA | 2025-04-03 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 5 | NA | 69 | NA | 4.1 | 2017-0022 | QS00169 | 1 | 17151 | 2025-12-10 ¦ 2014-0022 ¦ NA ¦ NA | TRUE | 2017-09-18 | Work Order Authorization | 2018 | NA | FALSE | NA | NA | NA | FALSE | TBD | TBD | Exempted | NA | NA | NA | TBD | 2024-12-26 | To be Filed | 2025 | On Hold | NA | 2027-11-05 | 2020-12-31 | 2028-01-26 | NA | NA | FALSE | 15490.906 | NA ¦ NA | 1883.4373 | 23.9228 | 23.2003 | 23.4068 | 13.9001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1883.4373 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | 11.0 | NA | 0% | 100% | [Reason for Change in In-Service Date] Project was put on hold for prioritization purposes and budget constraints.
269 | TL673 Direct Buried Cable Replacement (Rose Canyon La Jolla) |  |  | San Diego, San Diego | Currently TL673 consist entirely of aging 69kV direct-buried cable from Rose Canyon to La Jolla substations at approximately three miles. This existing direct-buried cable is of 1967 vintage year and has far exceeded its designed operational expectancy of 30 years. Transmission Engineering anticipates an increase rate in outages caused by failures on this existing aging cable system in the near future. This project will replace all existing direct-buried cable from Rose Canyon to La Jolla substations within a newly constructed underground trench conduit package and substructures which will improve electric transmission reliability to the La Jolla area as well as resolve the ongoing maintenance issue for TL673. | Transmission Line - Underground | Upgrade/Retrofit | NA | NA | Reliability | Age/Condition | NA | NA | 2025-04-03 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 5 | NA | 69 | NA | 4.1 | 2017-0023 | QS00170 | 1 | 17152 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2022-12-13 | Work Order Authorization | 2018 | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | To be Filed | NA | Operational | NA | 2021-07-26 | 2023-06-30 | 2023-06-30 | Land Rights | Land Rights | FALSE | 2600 | NA ¦ NA | 64098.0013 | 13885.5181 | 19644.0673 | 15451.8939 | -48.4234 | 216.1056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 | -170.835 | 244.5547 | 58056.242 | -48.4234 | 216.1056 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
270 | Avocado Substation 69kV Rebuild |  |  | San Diego, San Diego | Substation Rebuild, Transformers, Control Shelter & Relays & CS equipment, expanded the substation, change out 69kV circuit breakers, PT, and disconnects. | Substation - Multiple | Upgrade/Retrofit | NA | NA | Reliability | Substation Reliability | NA | NA | 2025-10-21 | 51; 51; 62 | NA | Wires - Replacement Alternative | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 3.128295 | 1.719191 | 69 | 60MVA | 2.1 | 2014-00941-ZZ | QS00171 | 1 | 17153 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2022-06-28 | Work Order Authorization | 2017 | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | To be Filed | NA | Operational | NA | 2018-09-17 | 2021-10-14 | 2020-11-16 | NA | NA | FALSE | 2020 | NA ¦ NA | 16778.2241 | 2428.5638 | 3.1856 | 0 | 179.3453 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2024 | 16499.6679 | 3.1856 | 0 | 179.3453 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
271 | TL662 TL666 Reliability Project |  |  | San Diego, San Diego | Project involves installing two new retaining walls to mitigate potential landslide risk for overhead electric poles within existing SDG&E utility easement located in Torrey Pines. | Other - Civil | Upgrade/Retrofit | NA | NA | Safety | Age/Condition | NA | NA | 2025-02-08 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69 ¦ 12 | NA | 4.1 | 2023-3558 | QS00196 | 1 | 18126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2018-02-21 | Work Order Authorization | 2024 | NA | FALSE | NA | NA | NA | FALSE | TBD | NA | NA | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Planning | NA | 2027-03-04 | 2021-12-31 | 2027-09-30 | Other[See Notes] | NA | TRUE | 6808.179 | NA ¦ NA | 7920.8794 | 157.1544 | 259.0357 | 82.0949 | 5.7561 | 165.426 | 719.0406 | 856.9 | 5297.4893 | 0 | 0 | 0 | 0 | NA | NA | 2024 ¦ 2025 ¦ 2026 | 0 | 0 | 0 | 882.0236 | 884.4666 | 856.9 | 0% | NA ¦ NA | 4.2 | NA | 0% | 100% | [Reason for Change in In-Service Date] Contracting delays [CPUC Status] N/A - Prescoping efforts. Filing type not yet determined.
272 | Escondido Substation 230kV Rebuild |  |  | Escondido, San Diego | The Escondido 230kV rebuild includes: replacing aging equipment, bringing the substation up to current seismic standards and upgrading the undersized bus. The rebuild will also replace existing control shelter and will make room within the substation to accommodate new bay additions. | Substation - Multiple | Replace | Upgrade/Retrofit | NA | Reliability | Substation Reliability | NA | NA | 2025-11-20 | 41; 45; 47; 17; 17; 17; 24; 17; 17; 25; 25 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 4.66311 | 230 | 230kV | 4.1 | 2024-4134 | QS00197 | 1 | 18127 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-05-18 | Work Order Authorization | 2018 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Planning | NA | TBD | 2022-12-31 | 2032-01-31 | Project Design | NA | FALSE | 982 | NA ¦ NA | 192822.948 | 5.867 | 14.0554 | 45.3664 | 87.018 | 262.2597 | 366.5939 | 16767.5072 | 25872.8495 | 36226.3777 | 59761.2295 | 42095.9605 | 11732.4298 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | 1.6 | NA | 100% | 0% | [CPUC Status] Exempt
273 | Mission 69kV Sub Rebuild |  |  | San Diego, San Diego | Install shoo-flys for TL618, TL663 & TL13822 in conflict and replace 69kV AIS with a GIS | Substation - Multiple | Replace | Upgrade/Retrofit | NA | Reliability | Substation Reliability | NA | NA | 2025-11-12 | 52 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | Coastal |  | NA | 8.996664 | 69 ¦ 138 | 69kV | 4.1 | 2019-1012 | QS00198 | 1 | 18128 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-02-01 | Work Order Authorization | 2018 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Construction (over 75%) | NA | 2022-12-05 | 2025-12-01 | 2025-06-30 | Other[See Notes] | NA | TRUE | 97625.0096 | NA ¦ NA | 141160.2554 | 821.6072 | 16116.6832 | 27651.0585 | 39500.8664 | 21727.671 | 20358.7089 | 14933.3482 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2023 ¦ 2025 ¦ 2026 | 0 | 0 | 1.9299 | 0 | 126224.9773 | 14933.3482 | 0% | NA ¦ NA | 1.3 | NA | 0% | 100% | [Reason for Change in In-Service Date] Approval for Mission was July 2021, then we onboard a contractor in June 2022. [CPUC Status] Exempt
274 | Skills Training Center – Transmission Yard Expansion |  |  | San Diego, San Diego | The purpose of this project is to expand the transmission yard at Skills Training Center for crews to train safely on. A new OH potion will be installed, along with an UG portion, a 500kV Insulator Replica, and an SW pole with a new stepping pattern will be installed. | Transmission Line - Conductor | Upgrade/Retrofit | NA | NA | Other [See Notes] | System Operations | NA | NA | NA | 55 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.076428 | NA | NA | NA | 1.3 | 2018-4002 | QS00380 | 1 | 18136 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-06-28 | Work Order Authorization | 2019 | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | 2020-05-18 | 2021-11-29 | 2022-04-01 | Project Design | NA | FALSE | 2475.891 | NA ¦ NA | 1948.0484 | 972.9268 | 558.2736 | 1.8695 | 0 | 0 | 0.21641 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2022 ¦ 2023 ¦ 2025 | 0 | 1945.9625 | 1.8695 | 0 | 0.21641 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 13.55% | 86.45% | [Primary Purpose] Infrastructure not connected to the grid for training purposes. [CPUC Status] NA
275 | Miguel Substation 230kV Rebuild |  |  | San Diego, San Diego | Upgrade relaying for Bk70/71, replace 32 disconnects, replace 32 switch stands to meet our new seismic standards, replace one overstressed breaker, and eight (8) panel changeouts. Remove existing relaying panels #403 & #406 | Substation - Multiple | Upgrade/Retrofit | NA | NA | Reliability | Age/Condition - Replace 230/115/70/60 kV Breakers | NA | NA | 2025-11-14 | NA | NA | Wires - Replacement Alternative | NA | Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 12.37 | 230 | 660MVA | 4.1 | 2014-01074-ZZ | QS00350 | 1 | 18139 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-12-18 | Work Order Authorization | 2019 | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | 2019-09-23 | 2022-07-31 | 2022-03-23 | Weather | NA | FALSE | 10503 | NA ¦ NA | 11568.2146 | 2385.1998 | 974.2539 | 5.9404 | 0.00208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2022 ¦ 2023 ¦ 2024 | 0 | 11562.2721 | 5.9404 | 0.00208 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0% | [Reason for Change in In-Service Date] In-service dates are estimated during preliminary design and permitting stages of a project; date shifted to reflect actual design and construction schedule. [CPUC Status] NA
276 | Mission Substation 230kV Rebuild |  |  | San Diego, San Diego | Rebuilding the Mission Substation, increase 230kV bus rating to 3k Amps. Replacing 230kV disconnects to latest standards. Replacing control shelter and equipment. Equipment was upgraded to meet standards, increase reliability and replace aging infrastructure | Substation - Multiple | Upgrade/Retrofit | NA | NA | Reliability | Age/Condition | NA | NA | 2025-11-12 | NA | NA | Wires - Replacement Alternative | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 9 | 230 | 230kV | 4.1 | 2014-01071-ZZ | QS00373 | 1 | 18140 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2022-08-17 | Work Order Authorization | 2019 | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | To be Filed | NA | Operational | NA | 2018-08-22 | 2022-06-30 | 2021-04-23 | Weather | NA | FALSE | 39512 | NA ¦ NA | 36157.6528 | 3769.3878 | 545.109 | 0 | -0.07175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2024 | 3834.7014 | 9573.6459 | 0 | -0.07175 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0% | [Reason for Change in In-Service Date] In-service dates are estimated during preliminary design and permitting stages of a project; date shifted to reflect actual design and construction schedule.
277 | NEW DOWNTOWN 69/12KV |  |  | San Diego, San Diego | New Downtown Substation 69 ¦12kV | Substation - Multiple | New | NA | NA | Load Growth | New Substation | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.5 | 2 | 69 ¦ 12 | 12kV ¦69kV | 4.2 | 2024-9876 | QS00318 | 1 | 18251 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2025-05-07 | Work Order Authorization | 2019 | NA | FALSE | NA | NA | NA | FALSE | Expected PEA Completion | NA | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Planning | NA | 2030-07-09 | 2031-12-31 | 2032-02-12 | Other[See Notes] | NA | TRUE | 501 | NA ¦ NA | 144254.6671 | 54.0713 | 10.0565 | 193.879 | 305.3035 | 552.3511 | 926.0512 | 2196.2931 | 4320.3937 | 4791.0436 | 3381.2817 | 4064.0075 | 545.3077 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 ¦ 2026 | 54.0713 | 10.0565 | 193.879 | 305.3035 | 933.0945 | 658.4659 | 0% | NA ¦ NA | 3.8 | NA | 0% | 100% | [Reason for Change in In-Service Date] Updated timelines as scope continues to develop [CPUC Status] Exempt
278 | TL13831 Rancho Mission Viejo Customer Relocation |  |  | Orange County | Install ten (10) transmission poles with pier foundation​ Install around one (1) mile of transmission conductor and ADSS fiber​ RFS fourteen (14) transmission poles and associated hardware​ RFS around 1.2 miles of transmission conductor | Transmission Line - Multiple | Relocate | New | NA | Work Requested by Others | 3rd Party Damage | NA | NA | 2025-04-16 | NA | NA | NA | NA | Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | TBD |  | 1.38 | NA | 138 | NA | 3.1 | 2017-0128 | QS00364 | 1 | 19129 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2021-01-07 | Work Order Authorization | 2019 | NA | FALSE | NA | NA | NA | FALSE | TBD | TBD | Exempted | NA | CPUC | NA | Exempt | NA | To be Filed | NA | Planning | NA | 2020-07-13 | 2020-12-31 | 2022-10-20 | Weather | Weather | FALSE | 6738.5499 | NA ¦ NA | 0.0050106 | 2351.4874 | 97.1672 | -892.8598 | -161.0921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 | 2351.4874 | 97.1672 | -892.8598 | -161.0921 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
279 | Urban Substation Rebuild |  |  | San Diego, San Diego | Urban Substation - new perimeter wall construction and 12kV Switchgear & Capacitor Replacement | Substation - Other Equipment | Upgrade/Retrofit | NA | NA | Reliability | Age/Condition - Replace Other Substation Equipment | NA | NA | 2025-09-10 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 0.566344 | 69 | 69kV ¦12kV | 4.1 | 2021-2065 | QS00397 | 1 | 19252 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-08-22 | Work Order Authorization | 2019 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Construction (10%-25%) | NA | 2023-07-13 | 2027-03-31 | 2027-04-07 | Weather | NA | FALSE | 5891.5596 | NA ¦ NA | 20973.577 | 311.129 | 640.6636 | 1245.1791 | 10027.7029 | 666.3958 | 1542.6058 | 3736.0167 | 2577.8042 | 0 | 0 | 0 | 726.6084 | NA | NA | 2024 ¦ 2025 | 0 | 0 | 0 | 11899.0971 | 491.4447 | 0 | 0% | NA ¦ NA | 31.5 | NA | 0% | 100% | [CPUC Status] NA [Reason for Change in In-Service Date] In-service dates are estimated during preliminary design and permitting stages of a project; date shifted to reflect actual design and construction schedule.
280 | Electric Transmission EMS/SCADA Replacement |  |  | San Diego, San Diego | Replacement of Energy Management System (EMS) software, applications, and supporting infrastructure at Electric Transmissions Mission Control Center and Metro Control Center. The EMS is used by Grid Operators to monitor and control the transmission grid. | Other - Operations Tech | Replace | NA | NA | Reliability | NERC CIP Compliance | NERC CIP Compliance | NA | NA | 47 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69 ¦500 | NA | 1.1 | NA | QS00452 | 1 | 20125 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-02-16 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | NA | NA | To be Filed | NA | Engineering less than 50% complete | NA | NA | 2022-06-30 | NA | NA | NA | TRUE | 16373.37 | NA ¦ NA | 13748.2929 | 0 | 0 | 0 | 3874.0547 | 351.4924 | 4814.7512 | 4253.695 | 454.2996 | 0 | 0 | 0 | 4225.5471 | NA | NA | 2026 | 0 | 0 | 0 | 0 | 0 | 13293.9933 | 0% | NA ¦ NA | 1.3 | NA | 13.55% | 86.45%
281 | TL610 Tier 2 W2S Project |  |  | San Diego, San Diego | Replace 12 wood pole structures in HFTD Tier 2 with steel pole structures and transfer approximately 1.6 miles of overhead conductor. | Transmission Line - Pole/Tower | Replace | NA | 20139 | Wildfire Mitigation | T-Line Reliability | NA | NA | 2025-01-28 | 37.0833 | NA | NA | NA | Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 1.6 | NA | 69 | NA | 1.2 | 2020-0272 | QS00474 | 1 | 20133 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-06-18 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | TBD | TBD | Exempted | NA | NA | NA | TBD | 2023-02-13 | Approved | 2023 | Engineering more than 50% complete | NA | 2027-01-01 | 2024-12-31 | 2027-05-01 | Land Rights | NA | TRUE | 1979.963 | NA ¦ NA | 10497.5469 | 112.1826 | 110.4849 | 125.6946 | 162.5457 | 56.9052 | 117.2355 | 2045.315 | 7729.5377 | 0 | 0 | 0 | 0 | NA | NA | 2025 ¦ 2026 | 0 | 0 | 0 | 0 | 722.6943 | 2045.315 | 0% | NA ¦ NA | 3.4 | NA | 0% | 100%
282 | TL627 Tier 2 W2S Project |  |  | Rancho San Diego, San Diego ¦ Spring Valley, San Diego | The TL627 Wood-to-Steel project consists of installing new steel pole structures, re-frame existing steel structures, and conductor along the existing 69kV tie line between Structure Z777999 and Structure Z971734 located in Spring Valley. As part of TL627 rebuild, C91 & C524 will be reconductored as well. This project was initiated as part of SDG&E’s continuous effort to improve reliability and reduce fire risks in fire-prone areas. | Transmission Line - Multiple | Replace | NA | NA | Wildfire Mitigation | Fire Protection | NA | NA | 2025-02-02 | 45.9091 | NA | NA | NA | Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 2.1 | NA | 69 | NA | 1.2 | 2019-0257 | QS00473 | 1 | 20134 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-07-30 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | Approved | 2023 | Permitting | NA | 2026-06-30 | 2027-04-30 | 2027-06-30 | Other[See Notes] | Other[See Notes] | FALSE | 1979.963 | NA ¦ NA | 15371.4963 | 110.013 | 423.3457 | 504.2678 | 3145.6159 | 850.9897 | 43.9937 | 974.7882 | 8423.1432 | 825.3227 | 0 | 0 | 0 | NA | NA | 2025 | 0 | 0 | 0 | 0 | 5104.2486 | 0 | 0% | NA ¦ NA | 1.6 | NA | 0% | 100% | [Reason for Change in In-Service Date] Agency permittng and easement acquisition delays [Project Description - What] Project is both structure and conductor replacement. [Reason for Change in In-Service Date] - Dependency on C75 SUG completion to start the construction of TL627 W2S.
283 | TL649 Tier 2 W2S Project |  |  | San Diego, San Diego ¦ Chula Vista, San Diego | 23 wood poles in HFTD2 to be replaced from wood to steel. Two of the poles (Z192597 and Z82136), are multi-transmission wood pole structures (two poles). 1.162 Miles to be re-conductored. | Transmission Line - Pole/Tower | Upgrade/Retrofit | NA | NA | Wildfire Mitigation | T-Line Reliability | NA | NA | NA | 40.4483 | NA | NA | NA | Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 1.682637 | NA | 69 | NA | 1.2 | 2019-0268 | QS00472 | 1 | 20135 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-06-10 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | Final Certified | 2018-10-05 | IS/MND | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2024-06-24 | 2024-12-31 | 2024-12-20 | NA | NA | FALSE | 1486.209 | NA ¦ NA | 7892.1593 | 189.4133 | 612.1586 | 829.9482 | 5451.9799 | 256.8213 | 515.6701 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2024 ¦ 2025 | 0 | 0 | 0 | 7114.3608 | 777.7985 | 0 | 0% | NA ¦ NA | 43.6 | NA | 0% | 100% | [CPUC Status] Exempt [Project Description - What] Project is both structure and conductor replacement.
284 | TL13804 Wood to Steel |  |  | Encinitas, San Diego ¦ Rancho Santa Fe, San Diego ¦ Carlsbad, San Diego ¦ San Diego, San Diego | Replace 15 existing wood structures (h-frames) with steel structures. Project spans approximately 5 miles of TL13804 and includes ~0.6 miles of reconductoring with transferring of existing conductor and fiber optic cable to new structures for the remainder. | Transmission Line - Pole/Tower | Replace | Removal | NA | Wildfire Mitigation | T-Line Reliability | NA | NA | 2025-02-08 | NA | NA | NA | NA | Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | Project In Coastal Zone; Requires Galvanized Steel Poles |  | 2.7 | NA | 138 | NA | 1.2 | 2019-0255 | QS00490 | 1 | 20136 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-07-25 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2024-09-10 | 2025-02-12 | 2024-12-19 | NA | NA | FALSE | 3628.655 | NA ¦ NA | 10405.6804 | 229.5117 | 297.0474 | 477.1188 | 8433.2258 | 39.5174 | 879.493 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2024 ¦ 2025 | 0 | 0 | 0 | 9486.67 | 919.0104 | 0 | 0% | NA ¦ NA | 8.1 | NA | 0% | 100% | [Reason for Change in In-Service Date] In-service dates are estimated during preliminary design and permitting stages of a project; date shifted to reflect actual design and construction schedule. [CPUC Status] Exempt
285 | TL23001/04 Insulator and Hardware Replacement |  |  | Encinitas, San Diego ¦ Rancho Santa Fe, San Diego ¦ Carlsbad, San Diego ¦ San Diego, San Diego ¦ Oceanside, San Diego | TL23001 TL23004 Insulator and Hardware Replacement | Transmission Line - Other Equipment | Upgrade/Retrofit | NA | NA | Reliability | Age/Condition - Replace Insulators | NA | NA | 2025-07-23 | NA | NA | NA | NA | Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 34.828406 | NA | 230 | NA | 4.1 | 2019-4004 | QS00479 | 1 | 20138 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2022-07-07 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | To be Filed | NA | Operational | NA | 2022-03-01 | 2022-07-29 | 2022-10-11 | Construction Delays | NA | FALSE | 8040.059 | NA ¦ NA | 10628.4182 | 3593.8105 | 6816.3403 | 81.5084 | 126.4645 | -3.079 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 0 | 10423.5243 | 81.5084 | 126.4645 | -3.079 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0%
286 | TL6952 Tier 2 W2S Project |  |  | San Diego, San Diego | Replace 9 wood pole structures in HFTD Tier 2 with steel pole structures and transfer approximately 1.5 miles of overhead conductor. | Transmission Line - Pole/Tower | Replace | NA | 20133 | Wildfire Mitigation | T-Line Reliability | NA | NA | 2025-08-27 | NA | NA | NA | NA | Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | Coastal |  | 1.5 | NA | 69 | NA | 1.2 | 2020-0287 | QS00466 | 1 | 20139 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-06-18 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | TBD | TBD | Exempted | NA | NA | NA | Exempt | NA | To be Filed | NA | Engineering more than 50% complete | NA | 2027-01-01 | 2022-12-31 | 2027-05-01 | Land Rights | NA | TRUE | 1810.588 | NA ¦ NA | 9405.0174 | 85.2687 | 108.168 | 115.8357 | 186.8303 | 56.5833 | 107.6907 | 2131.0959 | 6599.7534 | 0 | 0 | 0 | 0 | NA | NA | 2025 ¦ 2026 | 0 | 0 | 0 | 0 | 674.1681 | 2131.0959 | 0% | NA ¦ NA | 0.8 | NA | 0% | 100%
287 | TL661/TL664 Tier 2 W2S Project |  |  | San Diego, San Diego | Replace 14 wood pole structures in HFTD Tier 2 with steel pole structures and install approximately 1.16 miles of overhead conductor. | Transmission Line - Pole/Tower | Replace | NA | NA | Wildfire Mitigation | T-Line Reliability | NA | NA | 2025-08-27 | NA | NA | NA | NA | Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | Coastal |  | 1.16 | NA | 69 | NA | 1.2 | 2020-0289 | QS00471 | 1 | 20140 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-06-18 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | TBD | TBD | Exempted | NA | NA | NA | TBD | TBD | Other [See Notes] | TBD | Engineering less than 50% complete | NA | TBD | 2022-12-31 | 2027-12-31 | Project Design | Scope Change | FALSE | 1810.588 | NA ¦ NA | 19897.4023 | 150.0426 | 274.8061 | 558.0351 | 226.0215 | 348.7464 | 370.019 | 1661.9522 | 10873.7459 | 5407.8727 | 0 | 0 | 0 | NA | NA | 2025 | 0 | 0 | 0 | 0 | 1590.502 | 0 | 0% | NA ¦ NA | 2.5 | NA | 0% | 100%
288 | TL691 Tier 2 W2S Project |  |  | Fallbrook, San Diego ¦, Camp Pendleton North | The TL691 Fire Hardening & Reconductor Project consists of replacing existing structures and installing new steel structures along the 69kV tie line 691 in FTZ from Z19800, north of Camp Pendleton to structure Z293940, south of Avocado Substation, with new light duty and heavy engineered steel poles. This project is needed to mitigate loss of service due to wildfires by replacing existing wood poles with new steel structures. The new steel poles shall be designed to 138kV specifications and accommodate existing and future 12kV distribution underbuild and communications circuits. | Transmission Line - Pole/Tower | Replace | NA | NA | Wildfire Mitigation | T-Line Reliability | NA | NA | 2025-01-12 | 52.5091 | NA | NA | NA | Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 6.177837 | NA | 69 | NA | 1.2 | 2019-0269 | QS00469 | 1 | 20141 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-06-18 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | TBD | TBD | Other [See Notes] | TBD | Engineering less than 50% complete | NA | 2027-03-08 | 2024-12-31 | 2027-09-10 | Weather | NA | TRUE | 1979.963 | NA ¦ NA | 23049.2476 | 177.1658 | 521.1869 | 373.7411 | 328.1684 | 140.0065 | 233.2117 | 1809.3202 | 19421.8529 | 0 | 0 | 0 | 1423.2304 | NA | NA | 2025 ¦ 2026 | 0 | 0 | 0 | 0 | 161.6325 | 3465.7623 | 0% | NA ¦ NA | 4.1 | NA | 0% | 100% | [Reason for Change in In-Service Date] In-service dates are estimated during preliminary design and permitting stages of a project; date shifted to reflect actual design and construction schedule.
289 | TL675 Tier 2 W2S Project |  |  | San Diego, San Diego | ​57 poles to be replaced from wood to steel, and 6 miles to be reconductored. | Transmission Line - Pole/Tower | Replace | NA | NA | Wildfire Mitigation | T-Line Reliability | NA | NA | 2025-07-10 | 33.6154 | NA | NA | NA | Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | Coastal |  | 5.450292 | NA | 69 | NA | 1.2 | 2019-0251 | QS00470 | 1 | 20142 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-08-29 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | To be Filed | NA | Construction (under 10%) | NA | 2025-10-27 | 2026-12-31 | 2026-12-31 | NA | NA | TRUE | 1979.963 | NA ¦ NA | 23924.3794 | 257.9922 | 292.5942 | 545.0621 | 3288.587 | 2136.9747 | 3856.7886 | 11936.4701 | 1582.5951 | 0 | 0 | 0 | 2844.3213 | NA | NA | 2025 ¦ 2026 | 0 | 0 | 0 | 0 | 3704.2043 | 18637.58 | 0% | NA ¦ NA | 1.9 | NA | 0% | 100%
290 | TL6939 Tier 2 W2S Project |  |  | San Diego, San Diego | 42 poles in HFTD 2 to be replaced from wood to steel, and 2.5 miles to be reconductored. | Transmission Line - Multiple | Replace | Upgrade/Retrofit | NA | Wildfire Mitigation | Priority 1 Wood Structure Replacement | NA | NA | 2025-07-10 | NA | NA | NA | NA | Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.9 | NA | 69 | NA | 1.2 | 2019-0256 | QS00467 | 1 | 20143 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-06-18 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | TBD | NA | To be Filed | NA | Engineering less than 50% complete | NA | 2027-01-25 | 2024-12-31 | 2026-12-31 | Workforce | Project Design | TRUE | 1973 | NA ¦ NA | 4666.6231 | 56.2863 | 139.3699 | 257.6459 | 125.859 | 136.201 | 44.2029 | 3907.0581 | 0 | 0 | 0 | 0 | 715.3621 | NA | NA | 2026 | 0 | 0 | 0 | 0 | 0 | 4666.6231 | 0% | NA ¦ NA | 2.1 | NA | 0% | 100%
291 | TL6910 Tier 2 W2S Project |  |  | Chula Vista, San Diego | R​eplace 14 wood poles to steel poles. | Transmission Line - Multiple | Replace | Upgrade/Retrofit | NA | Wildfire Mitigation | Priority 1 Wood Structure Replacement | NA | NA | 2025-10-30 | 32.6875 | NA | NA | NA | Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 2.8 | NA | 69 | NA | 1.2 | 2019-0254 | QS00468 | 1 | 20144 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-06-18 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | TBD | NA | NA | NA | Engineering less than 50% complete | NA | 2027-01-25 | 2024-12-31 | 2027-01-25 | Project Design | NA | FALSE | 1973.076 | NA ¦ NA | 5608.7827 | 56.6194 | 46.5005 | 93.7415 | 354.0428 | 178.4547 | 77.9616 | 4531.4531 | 270.0091 | 0 | 0 | 0 | 729.3588 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | 1.1 | NA | 0% | 100% | [CPUC Status] NA
292 | TL13811 W2S |  |  | San Marcos San Diego ¦ Encinitas, San Diego ¦ San Diego, San Diego | TL13811 W2S is a hardening project driven by the circuit’s location within the High Fire Threat District (HFTD) Tier 2. This project will replace all transmission structures from Chicarita Sub to Z312843, and then again from Z200897 to North County Metering Station. Throughout these sections (approximately 11.25 miles in length) the 138 kV mainline will be replaced with 636 kcmil 24/7 Strand “Rook” ACSS/AW. 96 Count OPGW will be installed from Z872457 – Z312843 (approximately 10.75 miles in length). Distribution circuits C1101 and C182 that are in the underbuild position of TL13811 will be reconductored with Covered 336.4 kcmil 26/7 Strands “Linnet” ACSR, and covered 1/0 6/1 Strands “Raven” ACSR, respectively. | Transmission Line - Multiple | Replace | Removal | NA | Wildfire Mitigation | T-Line Reliability | NA | NA | 2025-02-20 | 62.1818 | NA | NA | NA | Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 13.000333 | NA | 138 | NA | 1.2 | 2019-0253 | QS00465 | 1 | 20145 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-04-23 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | TBD | TBD | Other [See Notes] | NA | Engineering more than 50% complete | NA | 2026-01-16 | 2024-12-31 | 2026-12-10 | Project Design | NA | TRUE | 88878 | NA ¦ NA | 79986.501 | 811.9706 | 1536.3214 | 1213.4383 | 3719.1329 | 2471.6233 | 13363.2706 | 56528.7495 | 152.8833 | 0 | 0 | 0 | 9941.5975 | NA | NA | 2026 | 0 | 0 | 0 | 0 | 0 | 79833.6177 | 0% | NA ¦ NA | 3.8 | NA | 0% | 100% | [CPUC Status] TBD
293 | IV Shunt Reactor Replacement |  |  | Fallbrook, San Diego ¦ Camp Pendleton North | Replace the existing 500kV shunt reactors at Imperial Valley substation with spares at Miguel substation. | Substation - Reactive Equipment | Replace | NA | NA | Reliability | 3rd Party Damage | NA | NA | 2025-11-18 | 42; 42; 42 | NA | Wires - Minimum Required Scope (spot repair) Alternative | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 55.477548 | 500 | 500kV | 4.1 | 2021-2176 | QS00482 | 1 | 20148 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-08-06 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | To be Filed | NA | Construction (50%-75%) | NA | 2022-06-01 | 2024-08-31 | 2024-08-02 | Weather | NA | FALSE | 3742.255 | NA ¦ NA | 4257.0618 | 1479.6704 | 1043.8368 | 472.7717 | 1205.2794 | 47.9711 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2024 ¦ 2025 | 0 | 0 | 0 | 4209.0907 | 47.9711 | 0 | 0% | NA ¦ NA | 18.5 | NA | 100% | 0% | [Reason for Change in In-Service Date] In-service dates are estimated during preliminary design and permitting stages of a project; date shifted to reflect actual design and construction schedule.
294 | TL6920 Wood to Steel |  |  | San Diego, San Diego | 7 poles in HFTD 2 to be replaced from wood to steel, and a total of 0.584 miles of existing 1033.5 ACSR/AW to be reconductored. | Transmission Line - Pole/Tower | Replace | NA | NA | Wildfire Mitigation | T-Line Reliability | NA | NA | 2025-02-20 | 29; 29; 29; 29; 29 | NA | NA | NA | Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.286309 | NA | 69 | NA | 1.2 | 2020-0286 | QS00504 | 1 | 20149 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-06-30 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | Approved | 2022 | Operational | NA | 2023-05-08 | 2024-01-18 | 2023-08-02 | NA | NA | FALSE | 1959.396 | NA ¦ NA | 4266.4749 | 171.0337 | 300.7648 | 3682.8958 | 110.8792 | 0.15428 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2023 ¦ 2024 ¦ 2025 | 0 | 0 | 4155.4414 | 110.8792 | 0.15428 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
295 | TL690C Camp Pendleton Wood to Steel |  |  | Camp Pendleton South, San Diego | approx 8 poles in HFTD 2 to be replaced from wood to steel. A total of 0.57 miles of existing 1/0 CU and 336.4 ACSR/AW to be reconductored. | Transmission Line - Multiple | Replace | Upgrade/Retrofit | NA | Wildfire Mitigation | T-Line Reliability | NA | NA | 2025-01-12 | NA | NA | NA | NA | Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 0.499472 | NA | 69 | NA | 1.2 | 2020-0273 | QS00496 | 1 | 20152 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-08-02 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | Categorical Exclusion | CPUC | MCBCP | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2024-06-28 | 2024-10-31 | 2024-07-31 | NA | NA | FALSE | 3977.8055 | NA ¦ NA | 2968.9743 | 140.182 | 218.2715 | 631.0719 | 1777.3783 | 201.2162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2023 ¦ 2024 ¦ 2025 | 0 | 0 | 990.3798 | 1777.3783 | 201.2162 | 0 | 0% | NA ¦ NA | 0.32 | NA | 0% | 100% | [Reason for Change in In-Service Date] In-service dates are estimated during preliminary design and permitting stages of a project; date shifted to reflect actual design and construction schedule. [CPUC Status] Exempt
296 | Granite 12kV Breaker and Switchgear Replacements |  |  | Granite Hills, San Diego | Rebuild of the 69kV bus reconfiguring it from an ultimate 2 tie line bus to an ultimate 3 tie line substation. Replace all seven (qty: 7) 69kV kV circuit breakers (5 OCB and 2 GCB ¦older style). Install new 69kV Potential Transformers. Replace 12kV open rack bus and (qty. 8) 12kV circuit breakers and (qty:2) 12kV 1 ¦4 section Switchgear at Granite Substation, due to operational problems, again infrastructure, environmental concerns, in addition to meeting current reliability standards. Rebuilding the 69kV bus and rotating the phases at the transmission pole will allow for a third tie line position. Replacing the 12kV open rack will RFS the OCBs and address the some 12kV reliability issues, will update relaying to support WMP initiatives (advance protection). The new control shelter will assist with updating relaying to include TCRI, new 69kV BT, and increase operational ability. | Substation - Circuit Breaker | Replace | Upgrade/Retrofit | NA | Reliability | Age/Condition - Replace Breakers | NA | NA | 2025-11-14 | NA | NA | Wires - Replacement Alternative | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 1.38 | 12 ¦69 | 12kV ¦69kV | 4.1 | 2021-2405 | QS00430 | 1 | 20244 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-10-24 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | Expected PEA Completion | TBD | Exempted | NA | NA | NA | Exempt | NA | To be Filed | NA | Construction (10%-25%) | NA | 2024-02-14 | 2028-12-31 | 2028-10-19 | NA | NA | TRUE | 4693.6589 | NA ¦ NA | 18969.5459 | 30.2266 | 440.1786 | 1135.9573 | 5398.2963 | 4677.0378 | 3330.1087 | 2650.5165 | 372.0948 | 55.4249 | 0 | 0 | 12499.2522 | NA | NA | 2024 ¦ 2025 ¦ 2026 | 0 | 0 | 0 | 240.4806 | -178.3317 | 18479.0294 | 0% | NA ¦ NA | 2.4 | NA | 0% | 100%
297 | Kettner Substation 69/12kV Rebuild Project |  |  | San Diego, San Diego | The Kettner Substation Rebuild includes the installation of two 69kV GCB, six 12kV VCB, and one 12kV Capacitor Bank with stepwise switching. This will make Kettner Substation an ultimate 30MVA. The project also includes the construction of a new concrete block control shelter and a new perimeter fence/wall. The project includes removal of old infrastructure no longer in use, including two 12kV cap banks, eleven 12kV OCBs, one 12kV VCB, and two 69kV OCB. The current shipping container control shelter will also be removed once cutover is complete to the new concrete block control shelter. | Substation - Multiple | Upgrade/Retrofit | Removal | NA | Reliability | Replace Other Substation Equipment | NA | NA | 2025-11-05 | 44; 44; 27 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 0.3 | 69 | 30MVA | 4.1 | 2014-00599-ZZ | QS00478 | 1 | 20251 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-05-10 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2022-11-28 | 2024-12-31 | 2024-09-20 | NA | NA | FALSE | 6659.3357 | NA ¦ NA | 10088.6933 | 1836.4478 | 1386.0173 | 3480.4105 | 1834.7917 | 1293.5236 | 54.0408 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 0 | 704.9014 | 13.3813 | 7245.8922 | 2124.5184 | 0 | 0% | NA ¦ NA | 17.3 | NA | 0% | 100% | [CPUC Status] Exempt
298 | Aviation Firefighting Program |  |  | NA | Purchase, equipping and initial training of a new Sikorsky S-70i Firehawk helicopter. | Other | NA | NA | NA | Wildfire Mitigation | Fire Protection | NERC CIP Compliance | NA | NA | 61 | NA | NA | NA | Tier 2 ¦ Tier 3 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | NA | NA | Multiple | NA | 1.2 | NA | QS00481 | 1 | 20277 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-10-24 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | NA | NA | To be Filed | NA | Permitting | NA | 2020-07-23 | 2024-10-31 | 2026-02-21 | NA | NA | TRUE | 28561.627 | NA ¦ NA | 5482.2293 | 1917.2812 | 376.7674 | 290.8835 | 461.529 | 69.2849 | 249.9999 | 310.0035 | 57.715 | 58.6168 | 59.5186 | 60.4204 | 65.6292 | NA | NA | 2022 ¦ 2023 ¦ 2024 ¦ 2025 ¦ 2026 | 0 | 35.0873 | 18.1185 | 67.164 | 4499.9559 | 310.0035 | 0% | NA ¦ NA | 17.9 | NA | 0% | 100% | [Reason for Change in In-Service Date] NA
299 | Suncrest Tertiary Reactor Replacement |  |  | San Diego, San Diego | The BK80/81 tertiary 12kV reactors are failing at a high rate (one in 2016, one in 2020, and two in 2021). Reactors are necessary to allow critical 500kV voltage control for grid operations. Newer, better designed, and insulated reactors are available to replace units that are failing at a quick rate. | Substation - Reactive Equipment | Upgrade/Retrofit | Replace | NA | Safety | Substation Reliability | NA | NA | 2025-11-03 | 13 | NA | Wires - Replacement Alternative | NA | Tier 3 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 40.94 | 500 | 12kV | 4.1 | 2021-2012 | QS00580 | 1 | 21137 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2022-07-19 | Work Order Authorization | 2021 | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | To be Filed | NA | Operational | NA | 2022-03-07 | 2022-06-30 | 2022-06-30 | Weather | NA | FALSE | 2699 | NA ¦ NA | 2111.8255 | 1904.6749 | 203.0249 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2022 | 0 | 2111.8255 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0% | [Reason for Change in In-Service Date] In-service dates are estimated during preliminary design and permitting stages of a project; date shifted to reflect actual design and construction schedule.
300 | TL623C Wood to Steel Project |  |  | San Diego, San Diego | This project replaces 4/0 B.S. CU Conductor. OH Full Rebuild approx. 1.30 miles from structure Z180990 to Z181008 South of Otay Valley Regional Park Removes 19 existing wood structures. | Transmission Line - Multiple | Replace | NA | NA | Wildfire Mitigation | System Design Upgrade | NERC TPL Standards | NA | 2025-01-13 | 70.0833 | NA | NA | NA | Tier 2 | FALSE ¦ FALSE ¦ TRUE | FALSE | NA |  | 1.6 | NA | 69 | NA | 2.1 | 2020-0327 | QS00634 | 1 | 21148 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2021-12-14 | Work Order Authorization | 2022 | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | TBD | 2026-10-29 | To be Filed | 2029 | Engineering more than 50% complete | NA | 2027-01-11 | 2027-12-31 | 2027-12-31 | Weather | NA | TRUE | 1876.6324 | NA ¦ NA | 2674.6212 | 0 | 0.52013 | 30.4255 | 202.4276 | 191.976 | 95.7888 | 634.0997 | 1375.6458 | 143.7376 | 0 | 0 | 0 | NA | NA | 2024 ¦ 2025 ¦ 2026 | 0 | 0 | 0 | 233.3732 | 287.7648 | 634.0997 | 0% | NA ¦ NA | 15.4 | NA | 0% | 100% | [Wildfire Related] Being in or out of the HFTD is not a bright-line litmus test. The CEQA categorical exemption for emergencies is based on why we are proposing the project. In or out notwithstanding, we should be able to utilize the emergency exemption for CEQA clearance if the purpose is to avoid the risk of wildfire.
301 | Twin Engine Medium Lift Helicopter |  |  | Gillespie Field, San Diego | Purchase of a twin engine, multi­mission, medium lift helicopter for primary use of external load work. The helicopter allows for heavier lift capability for continual distribution and transmission work in the high fire threat district. The helicopter also has fire fighting capabilities | Other | New | NA | NA | Wildfire Mitigation | Safety - Line Right of Way Access | NA | NA | NA | 61 | NA | NA | NA | Tier 1 ¦ Tier 2 | TRUE ¦ TRUE ¦ FALSE | FALSE | NA |  | NA | NA | NA | NA | 1.2 | NA | QS00609 | 1 | 21256 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2025-05-06 | Work Order Authorization | 2021 | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | NA | NA | To be Filed | NA | Operational | NA | 2021-12-30 | 2022-12-31 | 2023-01-23 | NA | NA | FALSE | 2119.6081 | NA ¦ NA | 2361.7393 | 368.2172 | 1658.298 | 208.6423 | 116.6109 | 3.9588 | 6.012 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2023 ¦ 2024 ¦ 2025 | 0 | 0 | 2235.1575 | 116.6109 | 9.9708 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [Primary Purpose] Initial investigation of potential projects.
302 | Smart Meter 2.0 |  |  | Multiple | Deployment of next generation smart metering technology and hardware | Multiple Options [See Notes] | Replace | Removal | n/a | Age/End of Life | Age/Condition | NA | NA | NA | NA | NA | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | n/a | NA | NA | T0092 | QBL0141 | 1 | 21881 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-11-29 | Work Order Authorization | 2022 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | Other [See Notes] | CPUC | NA | Standalone Application | N/A | To be Filed | NA | Planning | NA | 2026-07-01 | 2027-07-01 | 2027-07-01 | NA | NA | TRUE | 3782.466 | NA ¦ NA | 3782.466 | 0 | 130.9574 | 499.4895 | 2253.9494 | 651.0339 | 126.6191 | 120.4167 | 0 | 0 | 0 | 0 | 3292.964 | NA | NA | 2024 ¦ 2025 ¦ 2026 | 0 | 0 | 0 | 128.0795 | 114.3866 | 3539.9998 | 0% | NA ¦ NA | 1.1 | NA | 0% | 0% | [Project Description - What] Deployment of next generation smart metering technology and hardware
303 | Wildfire Resiliency Platform (WiNGS) |  |  | Multiple | Predictive analytic capabilities for WiNGS using Digital Twin technology | Other - Operations Tech | New | NA | NA | Wildfire Mitigation | Automation | NA | NA | NA | NA | NA | NA | NA | Tier 1 | TRUE ¦ TRUE ¦ TRUE | FALSE | NA |  | NA | NA | NA | NA | 1.2 | 53030 | QS00675 | 1 | 22255 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-06-30 | Work Order Authorization | 2022 | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | NA | NA | To be Filed | NA | Operational | NA | NA | 2023-11-30 | 2024-12-31 | NA | NA | FALSE | 247.3305 | NA ¦ NA | 1156.1266 | 0 | 381.4164 | 653.8465 | 60.4421 | 0 | 60.4217 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2024 ¦ 2025 | 0 | 0 | 0 | 1095.7049 | 60.4217 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [Wildfire Related] Provides insights that support wildfire risk assessment and planning. [Primary Purpose] Initial investigation of potential projects.
304 | Miguel-Sycamore Canyon 230kV Loop-in Suncrest |  |  | San Diego, San Diego | Mitigate the CAISO identified constraints consisting of the following: A 14.5-mile double circuit 230kV transmission line that will loop-in the existing TL23021 Miguel-Sycamore Canyon into Suncrest substation; and Install two new 500/230kV banks at Suncrest and Miguel Substations (one at each substation). | Transmission Line/Substation | New | NA | NA | CAISO Transmission Planning Standards [See Notes for NERC Compliance and contingency code, WECC Requirement (and the specific requirement)] | T-Line Reliability | CAISO Requirement | NA | 2025-11-03 | NA | Steady State Power Flow System Analysis | NA | $0 Mil – $1 Mil | Tier 3 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 14.5 | 55.48 | 230 ¦ 500 | 230kV ¦500kV | 2.1 | 2024-3714 | QS00734 | 1 | 23127 | 2025-12-10 ¦ 2021-2097 ¦ NA ¦ NA | TRUE | NA | Work Order Authorization | 2023 | 2023 | FALSE | 2023 | NA | https://www.caiso.com/Documents/ISO-Board-Approved-2022-2023-Transmission-Plan.pdf | FALSE | TBD | NA | EIR | NA | CPUC | NA | PTC | To Be Filed | To be Filed | TBD | Engineering less than 50% complete | NA | 2027-10-27 | 2032-12-31 | 2031-04-28 | NA | NA | FALSE | 375000 | NA ¦ NA | 426682.7845 | 0 | 0 | 0.29146 | 1768.5276 | 1477.8993 | 1780.0046 | 11642.4459 | 35529.5641 | 58681.5209 | 77962.2236 | 98076.7827 | 3246.7184 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0%
305 | BK30, BD: New Bank 30 |  |  | San Diego, San Diego | This project will be installing a New Bank 30MVA at Border Substation to address an overload. | Substation - Multiple | New | New | NA | Load Growth | Substation Capacity | NA | NA | 2025-11-17 | NA | NA | NA | NA | Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 0.94 | 69 | NA | 1.4 | 3-578735 | QS00703 | 1 | 23242 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-09-21 | Work Order Authorization | 2024 | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | To be Filed | NA | Construction (over 75%) | NA | 2025-01-01 | 2025-12-31 | 2025-12-31 | NA | NA | FALSE | 11703.4576 | NA ¦ NA | 4769.9316 | 0 | 0 | 110.2998 | 3040.3095 | 1165.7131 | 453.6091 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2025 | 0 | 0 | 0 | 0 | 4769.9316 | 0 | 0% | NA ¦ NA | 18.5 | NA | 0% | 100% | [CPUC Status] This project is not subject to PTC
306 | OT33, OT: New Sub Bank 33 |  |  | San Diego, San Diego | Instatallion of 69/12kv substation transformer and assoicated equipment | Substation - Multiple | New | NA | NA | Load Growth | Load Interconnection | NA | NA | 2025-11-06 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 2.78 | Multiple | NA | 1.4 | 3-684733 | QS00713 | 1 | 23258 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-05-01 | Work Order Authorization | 2024 | NA | FALSE | NA | NA | NA | FALSE | TBD | TBD | Exempted | NA | NA | NA | Exempt | NA | To be Filed | NA | Engineering less than 50% complete | NA | 2026-06-01 | 2024-12-31 | 2028-11-13 | Project Design | NA | FALSE | 8648.8448 | NA ¦ NA | 1234.2579 | 0 | 0 | 0.41068 | 159.9399 | 16.9251 | 37.9294 | 527.7016 | 404.1249 | 87.2263 | 0 | 0 | 177.2756 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | 13.5 | NA | 0% | 100% | [CPUC Status] This project is not subject to PTC
307 | TL631 UG Cable Replacement Project |  |  | El Cajon, San Diego | Project Scope: Remove and replace failing underground cables on TL631 that have been in operation for ~30years. The hand-taped splices are exhibiting significant degradation with (3) cable failures in the past 3 years. | Transmission Line - Underground | Upgrade/Retrofit | NA | NA | Reliability | Age/Condition | NA | NA | 2025-01-28 | 32; 32 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 1 | NA | 69 | NA | 4.1 | 2024-3662 | QS00731 | 1 | 24125 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-01-16 | Work Order Authorization | 2024 | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | To be Filed | NA | Operational | NA | 2024-02-26 | 2024-08-30 | 2024-04-21 | NA | NA | FALSE | 6625.166 | NA ¦ NA | 6668.9886 | 0 | 0 | 0 | 6630.5525 | 38.436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2024 ¦ 2025 | 0 | 0 | 0 | 6630.5525 | 38.436 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
308 | 3 ohm Series Reactor on Sycamore Penasquitos 230 kV line |  |  | San Diego, San Diego | Install a new 3 ohm series reactor on the Sycamore – Penasquitos 230 kV line; reactor will be installed at Sycamore Canyon Substation due to physical space requirements. | Substation - Reactive Equipment | New | NA | NA | CAISO Transmission Planning Standards [See Notes for NERC Compliance and contingency code, WECC Requirement (and the specific requirement)] | T-Line Reliability | CAISO Requirement | NA | 2025-02-04 | NA | Steady State Power Flow System Analysis | NA | $5 Mil - $10 Mil | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 13.94 | 230 | NA | 2.1 | 2022-3181 | QS00735 | 1 | 24126 | NA ¦ NA ¦ NA ¦ NA | FALSE | NA | Work Order Authorization | 2024 | 2023 | FALSE | 2023 | NA | https://www.caiso.com/Documents/ISO-Board-Approved-2022-2023-Transmission-Plan.pdf | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Engineering more than 50% complete | NA | 2025-12-15 | 2032-12-31 | 2027-07-30 | NA | NA | FALSE | 7290 | NA ¦ NA | 18635.8332 | 0 | 0 | 0 | 429.623 | 501.1695 | 4832.8091 | 3487.4748 | 9384.7568 | 0 | 0 | 0 | 930.7925 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0% | [See Notes for NERC Compliance and contingency code, WECC Requirement (and the specific requirement)] [CPUC Status] Substation Exemption [Primary Purpose] Project identified in 2022-23 CAISO Transmission Planning Process
309 | Rearrange TL23013 PQ OT and TL6959 PQ Mira Sorrento |  |  | San Diego. San Diego | Alternative to 2020-0291 (Relocate OH Section of TL23071 to UG)​Per CAISO request to SDG&E to identify potential solutions to address the overload problems on TL13810 (FR-DD-PQ) caused by credible P7 (N-2: TL23013 & TL23071) contingency. The overload has created some system operation congestions that will increase ​the operating cost to address system reliability. This project is proposed to swap TL23013 and TL6959 from PQ (2 miles between Z479065 and Z100258). To do that it will require to upgrade 2 miles of existing TL13810 structures to 230kV double circuit structures for TL23013 with 2-1033 ACSR and TL13810 with 1-1033 ACSR. TL23013 & TL13810 will share the same structures and TL23071 and TL6959 will be on the other structures. This will eliminate the credible P7 outage (N-2 TL23013 & TL23071)​. | Transmission Line - Multiple | Relocate | NA | NA | CAISO Transmission Planning Standards [See Notes for NERC Compliance and contingency code, WECC Requirement (and the specific requirement)] | T-Line Reliability | CAISO Requirement | NA | 2025-02-08 | NA | Steady State Power Flow System Analysis | NA | $20 Mil - $30 Mil | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 2 | NA | 69 ¦ 138 ¦ 230 | NA | 2.1 | 2020-0294 | QS00736 | 1 | 24127 | NA ¦ NA ¦ NA ¦ NA | FALSE | NA | Work Order Authorization | 2024 | 2023 | FALSE | 2023 | NA | https://www.caiso.com/Documents/ISO-Board-Approved-2022-2023-Transmission-Plan.pdf | FALSE | NA | NA | NA | NA | NA | NA | TBD | TBD | Other [See Notes] | TBD | Engineering less than 50% complete | NA | TBD | 2032-06-01 | 2032-12-31 | Project Design | NA | FALSE | 17942 | NA ¦ NA | 19488.0657 | 0 | 0 | 0 | 209.6776 | 230.3413 | 211.9274 | 323.3623 | 353.2367 | 385.8712 | 421.5206 | 460.4636 | 440.0189 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 13.55% | 86.45% | [See Notes for NERC Compliance and contingency code, WECC Requirement (and the specific requirement)] [Primary Purpose] Project identified in 2022-23 CAISO Transmission Planning Process [CPUC Status] TBD
310 | TL680C MELROSE RECONDUCTOR |  |  | Oceanside, San Marcos, Carlsbad, Vista, San Diego | Address the existing San Marcos Substation-Melrose Tap constraint by reconductoring the line to continuous/4 hour emergency rating of 102/234MVA | Transmission Line - Conductor | Upgrade/Retrofit | NA | NA | CAISO Transmission Planning Standards [See Notes for NERC Compliance and contingency code, WECC Requirement (and the specific requirement)] | T-Line Capacity | CAISO Requirement | NA | 2025-01-30 | 46.1889 | Steady State Power Flow System Analysis | Wires - Reconductor/Line Rebuild Alternative | $15 Mil - $20 Mil | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 6.3 | NA | 69 | NA | 2.1 | 2024-4035 | QS00743 | 1 | 24130 | NA ¦ NA ¦ NA ¦ NA | FALSE | NA | Work Order Authorization | 2024 | 2023 | FALSE | 2023 | NA | https://www.caiso.com/Documents/ISO-Board-Approved-2022-2023-Transmission-Plan.pdf | FALSE | NA | NA | NA | NA | NA | NA | TBD | TBD | Other [See Notes] | TBD | Planning | NA | 2026-10-02 | 2032-12-31 | 2032-12-31 | NA | NA | FALSE | 2000 | NA ¦ NA | 28207.7459 | 0 | 0 | 0 | 55.5192 | 531.4025 | 292.0623 | 624.3008 | 681.978 | 744.9838 | 813.8105 | 888.9959 | 586.9218 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | 6.8 | NA | 0% | 100% | [CPUC Status] TBD
311 | TL13820 CHICARITA RECONDUCTOR |  |  | San Diego ¦ Poway, San Diego | Reconductor the line to 250MVA from Chicarita Substation to Sycamore Canyon | Transmission Line - Conductor | Upgrade/Retrofit | NA | NA | CAISO Transmission Planning Standards [See Notes for NERC Compliance and contingency code, WECC Requirement (and the specific requirement)] | T-Line Capacity | CAISO Requirement | NA | 2025-10-06 | NA | Steady State Power Flow System Analysis | Wires - Reconductor/Line Rebuild Alternative | $15 Mil - $20 Mil | Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 5.2 | NA | 138 | NA | 2.1 | 2024-4036 | QS00744 | 1 | 24131 | NA ¦ NA ¦ NA ¦ NA | FALSE | NA | Work Order Authorization | 2024 | 2023 | FALSE | 2023 | NA | https://www.caiso.com/Documents/ISO-Board-Approved-2022-2023-Transmission-Plan.pdf | FALSE | TBD | NA | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Engineering less than 50% complete | NA | TBD | 2032-12-31 | 2032-12-31 | NA | NA | FALSE | 2000 | NA ¦ NA | 58628.0703 | 0 | 0 | 0 | 79.0354 | 393.0593 | 467.9309 | 1000.2303 | 1092.6385 | 1193.5839 | 1303.8554 | 51326.4796 | 472.0947 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | 0.8 | NA | 0% | 100% | [CPUC Status] NA
312 | Oceanside Area Sub: Electrification |  |  | Oceanside, San Diego | Oceanside load pocket consists of Cannon, Oceanside, San Luis Rey, and Stewart substations. Based on Distribution planning 2025 Forecast refresh (issued on March 10th, 2025), this load pocket will reach 85% in 2028 and 100% in 2036 of current capacity. In order to mitigate forecasted overload for load pocket the business unit is considering adding capacity to transfer load to a new substation, rebuild, or expansion of existing substations. | Substation - Multiple | New | New | NA | Load Growth | Substation Reliability | NA | NA | 2025-10-03 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 0.22 | NA | NA | 2.1 | 2025-4308 | QS00750 | 1 | 24133 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-08-30 | Work Order Authorization | 2025 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | CPUC | NA | TBD | NA | TBD | TBD | Planning | NA | TBD | 2031-12-31 | 2031-12-31 | Project Design | Permitting | TRUE | 21121.7902 | NA ¦ NA | 113765.4042 | 0 | 0 | 0 | 113.6741 | 98.3888 | 833.5358 | 16529.4806 | 8978.4044 | 31397.7406 | 43708.2368 | 11607.1456 | 544.4013 | NA | NA | 2025 ¦ 2026 | 0 | 0 | 0 | 0 | 501.1973 | 15543.3953 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0%
313 | BORDER-SAN YSIDRO SUBSTATION |  |  | San Diego, San Diego | The Border-San Ysidro substation project is part of the Electrification Capital Plan to ensure SDGE is meeting the growing load demands of the area. Projections show that a new substation and upgrades to existing substations will be required to mitigate OL conditions by 2031 and ensure reliability of the SDG&E electrical system. | Substation - Multiple | New | Upgrade/Retrofit | NA | Load Growth | New Substation | NA | NA | 2025-11-17 | NA | NA | NA | NA | Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69 | 69kV/12kV | 4.2 | 2024-4111 | QS00752 | 1 | 24134 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-09-12 | Work Order Authorization | 2025 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | CPUC | NA | PTC | To Be Filed | To be Filed | TBD | Planning | NA | NA | 2035-12-31 | 2031-12-31 | NA | NA | TRUE | 1932.7565 | NA ¦ NA | 241587.478 | 0 | 0 | 0 | 26.124 | 177.9382 | 130.7062 | 29773.6178 | 3221.0054 | 35574.4742 | 62565.2219 | 27022.1485 | 204.0621 | NA | NA | 2026 | 0 | 0 | 0 | 0 | 0 | 29416.8231 | 0% | NA ¦ NA | 2.0 | NA | 0% | 100%
314 | Pacific Beach - Rose Canyon Electrification |  |  | San Diego, San Diego | Increase overall capacity in the Pacific Beach - Rose Canyon load pocket to meet expected loads per the 10+ year forecast. | Substation - Multiple | New | New | NA | Load Growth | Substation Capacity | NA | NA | 2025-11-03 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 0.35 | NA | 30 MVA | 4.2 | 2025-4180 | QS00756 | 1 | 24135 | 2025-12-10 ¦ TBD ¦ NA ¦ NA | TRUE | 2024-09-30 | Work Order Authorization | 2025 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | CPUC | NA | TBD | TBD | Other [See Notes] | TBD | Planning | NA | NA | NA | TBD | NA | NA | FALSE | 1932.7565 | NA ¦ NA | 142331.2382 | 0 | 0 | 0 | 26.2579 | 77.4159 | 12.1907 | 10.221 | 11.0554 | 12.0686 | 13.1753 | 1884.3126 | 103.6737 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] TBD
315 | Coronado Island Reliability Reinforcement |  |  | Coronado, San Diego | Coronado Island Reliability Reinforcement: To support in increased Coronado Island load forecast SDGE will install a new 69kV transmission line (TL6977) from downtown San Diego to Coronado Island and reconductor existing transmission lines (TL650 and TL655). | Substation - Multiple | New | New | NA | CAISO Transmission Planning Standards [See Notes for NERC Compliance and contingency code, WECC Requirement (and the specific requirement)] | T-Line Capacity | CAISO Requirement | NA | NA | NA | Steady State Power Flow System Analysis | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 0.44 | 69 | NA | 2.1 | 2024-3886 | QS00755 | 1 | 24136 | 2025-12-10 ¦ 2025-4220 ¦ NA ¦ NA | TRUE | NA | Work Order Authorization | 2025 | 2025 | FALSE | 2025 | NA | https://www.caiso.com/documents/iso-board-approved-2024-2025-transmission-plan.pdf | FALSE | NA | NA | Exempted | NA | CPUC | NA | AL | To Be Filed | To be Filed | TBD | Engineering less than 50% complete | NA | NA | 2027-08-30 | 2028-11-30 | Weather | NA | FALSE | 3000.2772 | NA ¦ NA | 153707.4006 | 0 | 0 | 0 | 41.7452 | 781.2899 | 12464.7522 | 19945.2201 | 57981.9663 | 62492.427 | 0 | 0 | 823.0351 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [See Notes for NERC Compliance and contingency code, WECC Requirement (and the specific requirement)]
316 | Escondido Area Substation - Electrification |  |  | Escondido, San Diego | Escondido load pocket consists of Ash, Batiquitos, Esco, Escondido, Olivenhain and San Marcos substations. Based on Distribution Planning 2025 Forecast refresh (issued on March 10, 2025), this load pocket will reach 85% in 2030 and 100% in 2034 of current capacity. In order to mitigate forecasted overload for load pocket, the business unit is considering adding capacity to transfer load to rebuild, or expansion of existing Esco substations. | Substation - Multiple | New | New | NA | Load Growth | Substation Reliability | NA | NA | 2025-11-20 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 4.66 | NA | NA | 4.2 | 2025-4356 | QS00759 | 1 | 24138 | 2025-12-10 ¦ 2024-4134 ¦ NA ¦ NA | TRUE | 2024-10-30 | Work Order Authorization | 2025 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | IS/MND | NA | CPUC | NA | PTC | TBD | Other [See Notes] | NA | Planning | NA | TBD | 2033-12-31 | 2033-12-31 | NA | NA | FALSE | 1927.4041 | NA ¦ NA | 4217.388 | 0 | 0 | 0 | 7.9416 | 106.3208 | 176.0357 | 376.2873 | 411.052 | 449.0285 | 490.5136 | 527.9816 | 114.2624 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | 3.6 | NA | 0% | 0% | [CPUC Status] TBD
317 | IV Sub Short Circuit Mitigation |  |  | Imperial County | Imperial Valley Short Circuit: CAISO, as part of the 2023-2024 Transmission Plan, approved a reliability solution to address short circuit concerns at the SDG&E Imperial Valley Substation. The solution involves installing two sets of current-limiting reactors (CLRs) on the 230kV buses and rearranging related 230kV transmission lines that connect at IV Substation. | Substation - Multiple | New | New | NA | CAISO Transmission Planning Standards [See Notes for NERC Compliance and contingency code, WECC Requirement (and the specific requirement)] | Substation Reliability | CAISO Requirement | NA | 2025-11-18 | NA | Short Circuit Duty Analysis | Wires - System Configuration Alternative | $100 Mil – $125 Mil | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 55.48 | 230 | NA | 2.1 | 2025-4217 | QS00763 | 1 | 24139 | 2025-12-10 ¦ NA ¦ NA ¦ NA | TRUE | NA | Work Order Authorization | 2025 | 2024 | FALSE | 2024 | NA | https://www.caiso.com/documents/iso-board-approved-2023-2024-transmission-plan.pdf | FALSE | NA | NA | Exempted | Other [See Notes] | CPUC | BLM | PTC | To Be Filed | To be Filed | TBD | Planning | NA | NA | 2035-06-30 | 2035-06-30 | NA | NA | TRUE | 4099.974 | NA ¦ NA | 92495.2862 | 0 | 0 | 0 | 10.2178 | 129.0163 | 1648.016 | 1909.3149 | 5612.0702 | 10515.3411 | 2130.6767 | 30341.3167 | 139.9934 | NA | NA | 2025 ¦ 2026 | 0 | 0 | 0 | 0 | 1647.2566 | 1907.7796 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0% | [See Notes for NERC Compliance and contingency code, WECC Requirement (and the specific requirement)]
318 | Miguel BK 82 Expansion |  |  | San Diego, San Diego | Miguel Sub Bank 82 modification. GIS Expansion. 230kV Sub modification | Substation - Multiple | Upgrade/Retrofit | NA | NA | CAISO Transmission Planning Standards [See Notes for NERC Compliance and contingency code, WECC Requirement (and the specific requirement)] | System Operations | CAISO Requirement | NA | 2025-11-14 | 9; 9 | Lifecycle Replacement Analysis | Non-Wires - Large Scale Energy Alternative | $250 Mil – $300 Mil | Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | TBD |  | NA | 12.37 | 500 | 500kV | 2.1 | 2024-4097 | QS00755 | 1 | 24140 | NA ¦ NA ¦ NA ¦ NA | FALSE | NA | Work Order Authorization | 2025 | 2023 | FALSE | 2023 | NA | https://stakeholdercenter.caiso.com/InitiativeDocuments/ISO-Board-Approved-2022-2023-Transmission-Plan.pdf | FALSE | TBD | TBD | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Planning | NA | 2026-05-10 | 2033-01-03 | 2033-01-03 | NA | NA | FALSE | 186278 | NA ¦ NA | 191072.0767 | 0 | 0 | 0 | 76.2813 | 638.5416 | 4895.9214 | 35628.7639 | 4630.0666 | 27941.2429 | 17693.8347 | 50341.2941 | 714.8229 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | TBD | TBD | NA ¦ NA | NA | 100% | 0% | [CPUC Status] Exempt
319 | BK33, PD: New Bank 33 |  |  | San Diego, San Diego | Instatallion of 69/12kv substation transformer and assoicated equipment | Substation - Multiple | New | New | NA | Load Growth | Load Interconnection | NA | NA | 2025-10-15 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 2.78 | 69 | NA | 1.4 | 3-719759 | QS00767 | 1 | 24246 | 2025-12-10 ¦ NA ¦ NA ¦ NA | TRUE | 2025-01-16 | Work Order Authorization | 2025 | NA | FALSE | NA | NA | NA | FALSE | TBD | NA | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Engineering less than 50% complete | NA | 2025-08-15 | 2028-06-01 | 2028-02-11 | Project Design | NA | FALSE | NA | NA ¦ NA | 1588.5652 | 0 | 0 | 0 | 0 | 57.7521 | 411.1581 | 313.5368 | 806.118 | 0 | 0 | 0 | 57.7521 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | 11.5 | NA | 0% | 100% | [CPUC Status] This project is not subject to PTC
320 | Jamacha 69/12kV Substation Rebuild |  |  | La Mesa, San Diego | 69/12kV rebuild at Jamacha substation to develop and implement advanced protection technologies within electric substations and on the electric distribution system to prevent and mitigate the risks of fire incidents, create higher visibility and situational awareness in fire‐prone areas, and allow for the implementation of new relay standards in locations where protection coordination is difficult due to lower fault currents attributed to high impedance faults. | Substation - Multiple | Upgrade/Retrofit | NA | NA | Wildfire Mitigation | System Design Upgrade | NA | NA | NA | 53 | NA | NA | NA | Tier 2 ¦ Tier 3 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | NA | NA | 69 | 373MVA | 1.2 | 2020-1016 | QS00762 | 1 | 24251 | 2025-12-10 ¦ NA ¦ NA ¦ NA | TRUE | 2025-01-16 | Work Order Authorization | 2025 | NA | FALSE | NA | NA | NA | FALSE | TBD | NA | Exempted | NA | CPUC | NA | Exempt | 2022-04-14 | NA [See Notes] | NA | Construction (25%-50%) | NA | 2022-07-18 | 2022-12-31 | 2026-12-23 | Scope Change | NA | TRUE | 34252.457 | NA ¦ NA | 42133.5411 | 1577.9954 | 5352.3547 | 8586.9166 | 7706.451 | 6742.8327 | 4728.0755 | 6242.9945 | 447.2603 | 0 | 0 | 0 | 29545.1391 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 ¦ 2026 | 2.5985 | 208.7487 | 251.0339 | 306.4601 | 401.2305 | 40516.2091 | 0% | NA ¦ NA | 34.0 | NA | 0% | 100% | [CPUC Status] NA
321 | North Valley 69/12kV Substation Rebuild |  |  | Oceanside, San Diego | Rebuild and expand the existing North Valley Substation (69/12 kV) to improve safety, reliability, and system capacity amid regional growth. Scope includes removal of overhead 12kV distribution lines and undergrounding along North River Road, replacement of aging infrastructure, and expansion of current substation. | Substation - Multiple | Upgrade/Retrofit | NA | NA | Reliability | System Design Upgrade | NA | NA | NA | 46 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.34 | 2.17 | 69 | 69kV | 4.1 | 2020-2092 | QS00770 | 1 | 24252 | 2025-12-10 ¦ NA ¦ NA ¦ NA | TRUE | 2025-01-24 | Work Order Authorization | 2025 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Engineering more than 50% complete | NA | 2025-12-19 | 2027-02-27 | 2027-06-21 | Scope Change | Prioritization | TRUE | 21262.2381 | NA ¦ NA | 19786.951 | 713.0957 | 1066.6295 | 1525.8894 | 1113.2468 | 564.1366 | 3721.4406 | 10195.7123 | 876.9344 | 0 | 0 | 0 | 1539.3734 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 ¦ 2026 | 0.0026326 | 17.0071 | 2421.2163 | 855.4289 | 3881.2759 | 6628.1071 | 0% | 100% ¦ 30,763 | 7.3 | NA | 0% | 100% | [Reason for Change in In-Service Date] Project placed on temporary hold while new specific budget was created. [CPUC Status] Exempt
322 | Miguel Short Circuit Mitigation |  |  | Miguel and Bay Boulevard Substation | Reliability transmission solution to address the Short Circuit Duty(SCD) concerns at Miguel: Install a 3-Ohm series reactor on TL23026 Silvergate –Bay Boulevard 230 kV line which will be located at Bay Boulevard substation | Substation - Other Equipment | New | New | NA | CAISO Transmission Planning Standards [See Notes for NERC Compliance and contingency code, WECC Requirement (and the specific requirement)] | System Operations | CAISO Requirement | NA | 2025-11-14 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 2 | 230 | 230kV | 2.1 | 2025-4352 | QS00777 | 1 | 25143 | 2025-12-10 ¦ NA ¦ NA ¦ NA | FALSE | NA | Work Order Authorization | 2025 | 2024 | FALSE | 2024 | NA | https://www.caiso.com/documents/iso-board-approved-2023-2024-transmission-plan.pdf | FALSE | NA | NA | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Planning | NA | NA | 2035-06-01 | 2030-01-01 | NA | NA | FALSE | NA | NA ¦ NA | 81855.698 | 0 | 0 | 0 | 0 | 26.0578 | 110.8714 | 3539.2375 | 23731.9132 | 25919.5327 | 28057.8355 | 470.2499 | 26.0578 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0% | [See Notes for NERC Compliance and contingency code, WECC Requirement (and the specific requirement)] [CPUC Status] Exempt
323 | Valley Center system Improvement |  |  | Valley Center ¦ Escondido, San Diego | Reliability transmission solution to address several thermal overloads in the 69kV transmission system around Valley Center area due to the charging/discharging of Valley Center energy storage. | Transmission Line/Substation | New | Replace | NA | CAISO Transmission Planning Standards [See Notes for NERC Compliance and contingency code, WECC Requirement (and the specific requirement)] | Substation Reliability | CAISO Requirement | NA | NA | NA | NA | NA | NA | Tier 3 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 5 | 1 | 69 | 69 kv | 2.1 | 2025-4354 | QS00776 | 1 | 25144 | 2025-12-10 ¦ NA ¦ NA ¦ NA | FALSE | NA | Work Order Authorization | 2025 | 2024 | FALSE | 2024 | NA | https://www.caiso.com/documents/iso-board-approved-2023-2024-transmission-plan.pdf | FALSE | NA | NA | IS/MND | NA | CPUC | NA | TBD | TBD | Other [See Notes] | TBD | Planning | NA | TBD | 2028-06-01 | 2028-06-01 | NA | NA | FALSE | NA | NA ¦ NA | 73744.4903 | 0 | 0 | 0 | 0 | 28.1609 | 1189.2958 | 2548.2921 | 2783.7208 | 15086.5918 | 25272.5299 | 24504.2552 | 28.1609 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [See Notes for NERC Compliance and contingency code, WECC Requirement (and the specific requirement)]
324 | Mission 138kV Rebuild |  |  | San Diego, San Diego | Rebuild Mission 138kV substation to upgrade existing breaker infrastructure with new Gas Insulated Substation (GIS) system. | Substation - Circuit Breaker | Upgrade/Retrofit | NA | NA | Reliability | Substation Reliability | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | TBD |  | NA | 9 | 138 | 138kV | 4.1 | TBD | TBD | 1 | 25146 | NA ¦ NA ¦ NA ¦ NA | TRUE | NA | Work Order Authorization | 2025 | NA | FALSE | NA | NA | NA | FALSE | TBD | TBD | Other [See Notes] | Other [See Notes] | CPUC | NA | TBD | NA | Other [See Notes] | NA | Planning | NA | TBD | TBD | TBD | NA | NA | FALSE | NA | NA ¦ NA | 34044.4365 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2885.9876 | 7035.5829 | 0 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] TBD
325 | SOCRE (South Orange County Reliability Enhancement) |  |  | San Juan Capistrano, Orange ¦ San Clemente, Orange | To rebuild the existing Capistrano Substation, which is currently a 138/12kV distribution substation to a 230/138/12kV. Remove TL13835 (SMO-LNL) between Talega Substation and Capistrano Substation. Open TL23007 (SONGS-TA) at Talega Substation and loop into Capistrano Substation two new 230kV TLs (SONGS-CP230kV & CP-TA 230kV). Re-arrange 138kV TLs 13833, 138736, and 13812 bay positions at Talega to allow for the termination of TL13835 (SMO-TA) at Talega Substation. | Transmission Line/Substation | Upgrade/Retrofit | New | NA | Load Growth | Substation Capacity | NERC TPL Standards | NA | 2025-11-27 | 56; 63; 53; 57; 55; 20 | Steady State Power Flow System Analysis | Wires - Reconductor/Line Rebuild Alternative | Multiple Options [See Notes] | Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | Transmission Foundations At Talega Canyon Containing High Levels Of Sulfate. Mitigated By Installing Cmp To Protect Concrete Foundations |  | 9.133859 | 6 | 230 | 230kV | 2.1 | 2014-00068-ZZ | QS00009 | 1 | 6129 | NA ¦ NA ¦ NA ¦ NA | FALSE | NA | Work Order Authorization | 2006 | 2011 | FALSE | 2011 | NA | https://www.caiso.com/planning/Pages/TransmissionPlanning/2010-2011TransmissionPlanningProcess.aspx | FALSE | Final Certified | 2016-04-25 | EIR | NA | CPUC | NA | CPCN | 2012-05-18 | Approved | 2016 | Construction (over 75%) | NA | 2018-06-29 | 2015-05-18 | 2024-08-15 | Construction Delays | Construction Delays | FALSE | 363363 | 410000 ¦ CPUC | 365436.5751 | 46910.7232 | 29821.7373 | 39636.0331 | 15518.8887 | 1594.8526 | 3823.9959 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 132700.278 | 5577.5856 | 129956.0519 | 15600.8675 | 5418.8485 | 0 | 0% | NA ¦ NA | 10.6 | NA | 100% | 0% | [Alternative Solutions and Costs - Costs] SOCRUP Alternative 1: Rebuild Capistrano 230 kV substation, build a new SONGS – Capistrano 230 kV line using existing right-of-way, and build a new Escondido to Capistrano 230 kV line using existing right-of-way. Estimated cost for this alternative is $454.8 million. 2. SOCRUP Alternative 2: Rebuild Capistrano 138kV substation (aging infrastructure maintenance project), reconductor 138kV lines – Talega – Pico, Talega – Laguna Niguel, Talega – Trabuco, Capistrano – Trabuco, Talega – Rancho Mission Viejo, and upgrade SONGS – Talega 230 kV lines. Upgrade two 230/138 kV transformer banks at Talega. Estimated cost for this alternative is $347.6 million. 3. SOCRUP Alternative 3: Rebuild Capistrano 230 kV substation, build a new SONGS – Capistrano 230 kV line using existing right-of-way, and tap off a 230 kV line to Capistrano from existing Escondido – Talega 230 kV line. Estimated cost for this alternative is $364.8 million. Approved Alternative [Types of Analyses] Distribution Planning
326 | TL6926 Rincon to Valley Center Fire Hardening |  |  | Valley Center, San Diego | Fire harden a portion of TL6926 by replacing approximately 50 wood poles with equivalent steel poles in the high fire threat and wind-prone areas. TL6926 is a single circuit 69 kV transmission line located between the Valley Center Substation and the Rincon Substation. Approximately one mile of the line will be reconductored. The line will be fire hardened between poles Z12820 and Z114811, with the exception of the portion located adjacent to Valley Center Road near the Rincon Casino. Approximately one mile of the transmission line will be reconductored. | Transmission Line - Multiple | Replace | Removal | NA | Wildfire Mitigation | T-Line Reliability | NA | NA | 2025-02-04 | NA | NA | NA | NA | Tier 3 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 4.637369 | NA | 69 | NA | 1.2 | 2014-00061-ZZ | QS00025 | 1 | 9132 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2011-12-08 | Work Order Authorization | 2009 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | NA | NA | AL [3460-E] | 2019-11-13 | Approved | 2020 | Operational | NA | 2020-10-19 | 2013-01-31 | 2022-12-15 | Multiple Options[See Notes] | NA | FALSE | 65729 | NA ¦ NA | 105118.1157 | 57303.6517 | 16554.1531 | 2325.7931 | 333.3879 | 40.1926 | 0 | 0 | 2029.0844 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 1.1761 | 99114.3707 | 3515.0473 | 333.3879 | 40.1926 | 0 | 0% | NA ¦ NA | 21.6 | NA | 0% | 100% | [Reason for Change in In-Service Date] Permitting, design and construction delays. Construction delays, County of Valley Center issuing a stop work order due to dewatering issues.
327 | TL686 W2S_Wind |  |  | San Diego, San Diego | TL686 Wood-to-Steel will include the replacement of 182 wood and wood equivalent steel (SW) poles with 120 new poles. Scope includes the reconductoring of 14.6 miles of 69kV transmission and associated 12kV distribution underbuild (where underbuild is present) from Warners substation to just outside the Tier 2 HFTD (ending at structure Z118409). All replacements will be either direct-buried SW poles or foundation steel poles. Per SDG&E’s fire hardening standards, traditional 69 kV design and construction standards with additional phase spacing and insulation shall be used and guy anchors shall be avoided. Shield wire with a fiber (OPGW) will be added to protect phase conductors from lightning damage. All transmission conductors in this project shall be reconductored. All poles will be designed to accommodate one level of third-party communication. | Transmission Line - Pole/Tower | Replace | Removal | 23126 | Wildfire Mitigation | T-Line Reliability | NA | NA | 2025-01-07 | 47.7975 | NA | NA | NA | Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 14.6 | NA | 69 | NA | 1.2 | 2018-0161 | QS00027 | 1 | 9142 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-11-06 | Work Order Authorization | 2012 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | NA | BLM | Exempt | NA | NA [See Notes] | NA | Engineering more than 50% complete | NA | 2036-01-18 | 2027-08-24 | 2037-07-06 | Permitting | Permitting | FALSE | 5446.0598 | NA ¦ NA | 155533.8165 | 1923.6474 | 1337.7718 | 1315.6179 | -66.3227 | 532.9914 | 705.8253 | 867.205 | 765.0966 | 822.1968 | 897.4895 | 979.7287 | 5043.7057 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | 7.2 | NA | 0% | 100% | [CPUC Status] Exempt [Reason for Change in In-Service Date] Other project dependencies (rebuild/upgrade of existing Narrows substation) pushing out schedule
328 | CNF MSUP |  |  | Multiple | Design, procure materials for and construct Cleveland National Forest (CNF) Master Special Use Permit (MSUP) fire hardening program | Other | NA | NA | NA | Wildfire Mitigation | Fire Protection | NA | NA | NA | NA | NA | NA | NA | Tier 2 ¦ Tier 3 | FALSE ¦ FALSE ¦ FALSE | FALSE | Complete |  | NA | NA | Multiple | NA | 1.2 | Multiple | NA | 1 | 8165 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2016-06-15 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | TBD | NA | NA | NA | CPUC | CNF | PTC | 2012-10-17 | Approved | 2016 | Operational | NA | Multiple | Multiple | Multiple | NA | NA | FALSE | 418777 | NA ¦ NA | 423436.973 | 16335.9501 | 686.2607 | 94.14 | 13.5584 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 | 14926.9032 | 686.2607 | 94.14 | 15.8146 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [Utility Unique ID #1(Less Specific)] CNF-C157, CNF-C222, CNF-C440 I, CNF-C440 II, CNF-C442, CNF-C449, CNF-C79A, CNF-C79B, CNF-EPC-63, CNF-TL625C, CNF-TL626, CNF-TL629A, CNF-TL629C, CNF-TL682, CNF-TL6923, CNF-TL6931,CNF-TL6957, CNF-TL6958
329 | CIS Envision |  |  | NA | Replacing SDG&Es legacy Customer Information System (CIS) with a new SAP system | Other - IT | Replace | NA | NA | Age/End of Life | Age/Condition | NA | NA | NA | 60 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | NA | NA | NA | NA | QS00194 | 1 | CIS001 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2018-09-11 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | TBD | TBD | Exempted | NA | NA | NA | Application 17-04-027 | 2017-04-27 | Approved | 2018 | Operational | NA | NA | 2021-01-31 | NA | NA | NA | TRUE | 187200.951 | NA ¦ NA | 30549.1371 | 7032.298 | 2.6294 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 | 29155.1242 | 2.6294 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0%

## Options List
06. Project Description - What | 07. Project Description - Action taken | 09. Primary Purpose | 10. Secondary Purpose | 11. NERC/WECC/CAISO Standard/Requirement/Contingency | 14. Types of Analyses | 15a. Alternative Solutions and Costs - Solutions | 15b. Alternative Solutions and Costs - Costs | 40. CEQA Status | 41a. CEQA Document Type | 41b. NEPA Document Type | 45. CPUC Status | 47. Project Status | 48. AACE Class | 52. Reason for Change in In-Service Date | Complete
Substation - Multiple | New | CAISO Transmission Planning Standards [See Notes for NERC Compliance and contingency code, WECC Requirement (and the specific requirement)] | 3rd Party Damage | NERC CIP Compliance | Lifecycle Replacement Analysis | Wires - System Configuration Alternative | $0 Mil – $1 Mil | Expected PEA Completion | IS/ND | EIS | To be Filed | Planning | 1 | Weather | Yes
Substation - Other Equipment | Replace | Reliability | Age/Condition | NERC BAL Compliance | Steady State Power Flow System Analysis | Wires - Location/Route Alternative | $1 Mil - $2 Mil | PEA Deemed Complete | IS/MND | EA | Filed and Under Administrative Review | Engineering less than 50% complete | 2 | Permitting | No
Substation - Transformer | Upgrade/Retrofit | Load Growth | Age/Condition - 230/115/70/60 kV Relay Replacement | NERC FAC Compliance | Dynamic System Analysis | Wires - Reconductor/Line Rebuild Alternative | $2 Mil - $3 Mil | CEQA Draft Published | EIR | Categorical Exclusion | Administratively Complete and Under Technical Review | Engineering more than 50% complete | 3 | Clearances
Substation - Circuit Breaker | Relocate | Local Capacity Requirement | Age/Condition - 500 kV Relay Replacement | WECC Audit Findings | Short Circuit Duty Analysis | Wires - Replacement Alternative | $3 Mil -$5 Mil | CEQA Final Published | Exempted | Other [See Notes] | Approved | Permitting | 4 | Material
Substation - Line Termination | Removal | Address Results of Power Flow Analysis | Age/Condition - Anti Climb Guards | NERC PRC Compliance | Protection Studies | Wires - Minimum Required Scope (spot repair) Alternative | $5 Mil - $10 Mil | Final Certified | Other [See Notes] | NA | Rejected | Construction (under 10%) | 5 | Workforce
Substation - Voltage Support Equipment | NA | Address Results of Protection Studies | Age/Condition - Insulator Replacement - Steel | NERC TPL Standards | Interconnection System Impact/Facilities Studies | Wires - Voltage Support/Reactive Support Alternative | $10 Mil -$15 Mil | TBD | NA |  | Advice Letter Filed and In-Process | Construction (10%-25%) | NA | Prioritization
Substation - Bus Arrangement | Multiple Options [See Notes] | Physical Security | Age/Condition - Insulator Replacement - Wood | CAISO Requirement | Other [See Notes] | Wires - New Substation Alternative | $15 Mil - $20 Mil | Other [See Notes] |  |  | Other [See Notes] | Construction (25%-50%) |  | Bundling Dependencies
Substation - Switch |  | Policy | Age/Condition - Raptor Protection - Steel | Other [See Notes] | Multiple Options [See Notes] | Wires - Bus Upgrade Alternative | $20 Mil - $30 Mil | NA |  |  | NA [See Notes] | Construction (50%-75%) |  | Customer Action
Substation - Modular Protection and Automation Control Building |  | Economic | Age/Condition - Replace 230/115/70/60 kV Breakers | NA | NA | Wires - New T-Line Alternative | $30 Mil - $40 Mil |  |  |  |  | Construction (over 75%) |  | ISO Action
Substation - Protection Relay |  | Generator Interconnection | Age/Condition - Replace 230/115/70/60 kV Transformers | Multiple Options [See Notes] |  | Non-Wires - Large Scale Energy Alternative | $40 Mil - $50 Mil |  |  |  |  | Operational |  | Completed Early
Substation - Reactive Equipment |  | Work Requested by Others | Age/Condition - Replace 500 kV Breakers |  |  | Non-Wires - System DER Alternative | $50 Mil – $75 Mil |  |  |  |  | On Hold |  | Construction Delays
Substation - Structure |  | Age/End of Life | Age/Condition - Replace 500 kV Transformers |  |  | Other - Status Quo | $75 Mil – $100 Mil |  |  |  |  | Canceled |  | Outage
Other - IT |  | Wildfire Mitigation | Age/Condition - Replace Boardwalks |  |  | Other - Deferral | $100 Mil – $125 Mil |  |  |  |  | Abandoned |  | Project Design
Other - Physical Security |  | Field Test Results | Age/Condition - Replace Breakers |  |  | TBD | $125 Mil - $150 Mil | [6 empty] | Input Error
Other - Operations Tech |  | Emergency Event | Age/Condition - Replace Civil Structures |  |  | NA | $150 Mil - $175 Mil | [6 empty] | Vendor Quality/Delays
Other - Cybersecurity |  | Location, Environmental Conditions | Age/Condition - Replace Conductor |  |  |  | $175 Mil - $200 Mil | [6 empty] | Scope Change
Other - Remedial Action Scheme/Special Protection Scheme |  | Safety | Age/Condition - Replace Insulators |  |  |  | $200 Mil - $250 Mil | [6 empty] | Land Rights
Other |  | Asset Condition | Age/Condition - Replace Other Substation Equipment |  |  |  | $250 Mil – $300 Mil | [6 empty] | Other [See Notes]
Other - Environmental |  | Other [See Notes] | Age/Condition - Replace Other T-Line Equipment |  |  |  | $300 Mil - $350 Mil | [6 empty] | NA
Other - Civil |  |  | Age/Condition - Replace Reactors, Age/Condition - Replace Relays |  |  |  | $350 Mil – $400 Mil | [6 empty] | Multiple Options [See Notes]
Transmission Line/Substation |  |  | Age/Condition - Replace Relays |  |  |  | $400 Mil - $500 Mil
Transmission Line - Multiple |  |  | Age/Condition - Replace SCADA/RTU |  |  |  | Over $500 Mil
Transmission Line - Switch |  |  | Age/Condition - Replace Steel Poles |  |  |  | Multiple Options [See Notes]
Transmission Line - Underground |  |  | Age/Condition - Replace Switches, Age/Condition - Replace Transformers |  |  |  | NA
Transmission Line - Pole/Tower |  |  | Age/Condition - Replace Underground System
Transmission Line - Conductor |  |  | Age/Condition - Replace Wood Poles
Transmission Line - Other Equipment |  |  | Age/Condition - Switch Replacement - Steel
Transmission Line - Right of Way |  |  | Age/Condition - Switch Replacement - Wood
Multiple Options [See Notes] |  |  | Age/Condition - Targeted Relay Replacement
Age/Condition - Wood Pole Reframe
Animal Abatement
Automation
Bus Upgrade
Compliance - Remove Idle Facilities
Construct Roads/Gates/Culverts
Emergency Response - Fire Related
Emergency Response - Storm Related
Environmental
Facility Relocation
Fire Protection
Generation Interconnection
GO95 Mitigation - Steel
Install SCADA/RTU
Line Reconductoring
Line Termination
Load Interconnection
Modular Protection and Automation Control
NERC CIP Compliance
NERC Compliance - GO 95
New Substation
New T-Line
Priority 1 Steel Structure Replacement
Priority 1 Wood Structure Replacement
Protection NERC Compliance
Relay Upgrades
Replace Breakers
Replace Other Substation Equipment
Replace Transformer
Safety - Line Right of Way Access
SCADA Emergency Replacement
SCADA Switch Installation
Security Upgrades
Seismic Upgrade - Replace Conductor
Special Protection Scheme
Substation Capacity
Substation Reliability
System Design Upgrade
System Operations
Targeted Line Reliability
T-Line Capacity
T-Line Emergency
T-Line Reliability
Tools, Transformer Addition/Replacement
Underground Emergency
Voltage Conversion
Voltage Support

## Definitions
Category | Sorting Order | Data Field # | Transmission Project Data Field | Format | Example | Input Terms and Descriptions | Column1
Project Description | 1 | 1 | Row/Line No. | Number (whole number) | 4 | Row/line number in spreadsheet. Include separate project lines, as described and required in data fields 26-28, for all subparts, i.e., ID #1 of all FERC-jurisdictional electric transmission projects, including generator interconnection-related network upgrades: 1. the total cost of which At Unique ID #2 will at any point equal or exceed $1 million. In the event that there is no ID#2 to provide, the million-dollar threshold applies to ID #1. and 2. for which there were capital expenditures in the last five years OR for which any capital expenditures are anticipated in the current or next four years, regardless of the actual or anticipated operative date. Each project should have at least one Row/Line No. in this spreadsheet, as subparts of projects will require additional project lines. | Row/line number in spreadsheet. Include separate project lines, as described and required in data fields 26-28, for all subparts, i.e., ID #1 of all FERC-jurisdictional electric transmission projects, including generator interconnection-related network upgrades: 1. the total cost of which At Unique ID #2 will at any point equal or exceed $1 million. In the event that there is no ID#2 to provide, the million-dollar threshold applies to ID #1. and 2. for which there were capital expenditures in the last five years OR for which any capital expenditures are anticipated in the current or next four years, regardless of the actual or anticipated operative date. Each project should have at least one Row/Line No. in this spreadsheet, as subparts of projects will require additional project lines. Example: 4
Project Description | 2 | 2 | Project Name | Text String, separated by " ¦ " as necessary | Manzanita Substation | Include Project Name at date of report filing. Identify all prior names of the project and other names currently used in different venues, including the name as approved and included in the CAISO's TPP. | Include Project Name at date of report filing. Identify all prior names of the project and other names currently used in different venues, including the name as approved and included in the CAISO's TPP. Example: Manzanita Substation
Project Description | 3 | 3a | Latitude | Number (decimal), separated by " ¦ " for multiple locations; NA if no geolocation | 20.234 ¦ 19.983 | Positive number indicates north of equator. Subject to redaction in the public data. | Positive number indicates north of equator. Subject to redaction in the public data. Example: 20.234 ¦ 19.983
Project Description | 4 | 3b | Longitude | Number (decimal), separated by " ¦ " for multiple locations; NA if no geolocation | -132.018 ¦ -132.231 | Negative number indicates west of Prime Meridian. Subject to redaction in the public data. | Negative number indicates west of Prime Meridian. Subject to redaction in the public data. Example: -132.018 ¦ -132.231
Project Description | 5 | 4 | Location 2 | Text String, with comma separator between City and County. Multiple entries separated by " ¦ ". Order of values to be consistent with latitude and longitude values * City1, County1 ¦ City2, County2 | Berkeley, Alameda ¦ Concord, Contra Costa | All Cities and Counties included in the scope of the project. | All Cities and Counties included in the scope of the project. Example: Berkeley, Alameda ¦ Concord, Contra Costa
Project Description | 6 | 5 | Project Description | Text String | This project will repair the transmission line connecting 4th and Townsend to the East Northfork station which failed as consequence of the 2019 San Clemente Hedge Fire. Assets to be replaced include... at ....kV. | General project overview: what, where, and why. Discuss all assets to be installed and include all capacities (MVA) and voltages (kV). | General project overview: what, where, and why. Discuss all assets to be installed and include all capacities (MVA) and voltages (kV). Example: This project will repair the transmission line connecting 4th and Townsend to the East Northfork station which failed as consequence of the 2019 San Clemente Hedge Fire. Assets to be replaced include... at ....kV.
Project Description | 7 | 6 | Project Description - What | Select text from drop-down menu | Substation - Circuit Breaker | Transmission line (new, reconductor, relocation), substation (breaker, transformer relay protection), etc. | Transmission line (new, reconductor, relocation), substation (breaker, transformer relay protection), etc. Example: Substation - Circuit Breaker
Project Description | 8 | 7 | Project Description - Action Taken (2) | Select text from drop-down menu(s) | Upgrade/Retrofit | See drop-down menu for options. If more than two options are required, select "Multiple Options" in second column and provide remaining responses, pipe-delimited, in "Notes" data field. If the primary or secondary purpose relates to complying with a NERC, WECC, or CAISO requirement, list the specific standard(s), requirement(s), and/or any contingencies that are being addressed. | See drop-down menu for options. If more than two options are required, select "Multiple Options" in second column and provide remaining responses, pipe-delimited, in "Notes" data field. If the primary or secondary purpose relates to complying with a NERC, WECC, or CAISO requirement, list the specific standard(s), requirement(s), and/or any contingencies that are being addressed. Example: Upgrade/Retrofit
Project Description | 9 | 7 | Project Description - Action Taken | Select text from drop-down menu(s) | Upgrade/Retrofit | See drop-down menu for options. If more than two options are required, select "Multiple Options" in second column and provide remaining responses, pipe-delimited, in "Notes" data field. If the primary or secondary purpose relates to complying with a NERC, WECC, or CAISO requirement, list the specific standard(s), requirement(s), and/or any contingencies that are being addressed. | See drop-down menu for options. If more than two options are required, select "Multiple Options" in second column and provide remaining responses, pipe-delimited, in "Notes" data field. If the primary or secondary purpose relates to complying with a NERC, WECC, or CAISO requirement, list the specific standard(s), requirement(s), and/or any contingencies that are being addressed. Example: Upgrade/Retrofit
Project Description | 10 | 8 | Project Dependencies | Number (whole) indicating required project or projects' Unique ID #(s), separated by " ¦ " as necessary | 235435 ¦ 432787 | Identify all other projects (Unique ID #1) in the spreadsheet that this project depends on and/or whose construction will be bundled with this project. | Identify all other projects (Unique ID #1) in the spreadsheet that this project depends on and/or whose construction will be bundled with this project. Example: 235435 ¦ 432787
Project Description | 11 | 9 | Primary Purpose | Select text from drop-down menu | Reliability | May include, but not limited to: CAISO Transmission Planning Standards (NERC Compliance and contingency code, WECC Requirement (and the specific requirement)), Reliability, Load Growth, Local Capacity Requirement, Address Results of Power Flow Analysis, Address Results of Protection Studies, Physical Security, Policy, Economic, Generator Interconnection, Work Requested by Others, Age/End of Life, Wildfire Mitigation, Field Test Results, Emergency Event, Location, Environmental Conditions, Safety, Asset Condition, or Other. In the "Notes" data field, please explain a purpose identified as "Other" or provide additional details on the purpose identified. | May include, but not limited to: CAISO Transmission Planning Standards (NERC Compliance and contingency code, WECC Requirement (and the specific requirement)), Reliability, Load Growth, Local Capacity Requirement, Address Results of Power Flow Analysis, Address Results of Protection Studies, Physical Security, Policy, Economic, Generator Interconnection, Work Requested by Others, Age/End of Life, Wildfire Mitigation, Field Test Results, Emergency Event, Location, Environmental Conditions, Safety, Asset Condition, or Other. In the "Notes" data field, please explain a purpose identified as "Other" or provide additional details on the purpose identified. Example: Reliability
Project Description | 12 | 10 | Secondary Purpose | Select text from drop-down menu | Age/Condition - Anti Climb Guards | May include, but not limited to: 3rd Party Damage, Age/Condition, Age/Condition - 230/115/70/60 kV Relay Replacement, Age/Condition - 500 kV Relay Replacement, Age/Condition - Anti Climb Guards, Age/Condition - Insulator Replacement - Steel, Age/Condition - Insulator Replacement - Wood, Age/Condition - Raptor Protection - Steel, Age/Condition - Replace 230/115/70/60 kV Breakers, Age/Condition - Replace 230/115/70/60 kV Transformers, Age/Condition - Replace 500 kV Breakers, Age/Condition - Replace 500 kV Transformers, Age/Condition - Replace Boardwalks, Age/Condition - Replace Breakers, Age/Condition - Replace Civil Structures, Age/Condition - Replace Conductor, Age/Condition - Replace Insulators, Age/Condition - Replace Other Substation Equipment, Age/Condition - Replace Other T-Line Equipment, Age/Condition - Replace Reactors, Age/Condition - Replace Relays, Age/Condition - Replace Relays, Age/Condition - Replace SCADA/RTU, Age/Condition - Replace Steel Poles, Age/Condition - Replace Switches, Age/Condition - Replace Transformers, Age/Condition - Replace Underground System, Age/Condition - Replace Wood Poles, Age/Condition - Switch Replacement - Steel, Age/Condition - Switch Replacement - Wood, Age/Condition - Targeted Relay Replacement, Age/Condition - Wood Pole Reframe, Animal Abatement, Automation, Bus Upgrade, Compliance - Remove Idle Facilities, Construct Roads/Gates/Culverts, Emergency Response - Fire Related, Emergency Response - Storm Related, Environmental, Facility Relocation, Fire Protection, Generation Interconnection, GO95 Mitigation - Steel, Install SCADA/RTU, Line Reconductoring, Line Termination, Load Interconnection, Modular Protection and Automation Control, NERC CIP Compliance, NERC Compliance - GO 95, New Substation, New T-Line, Priority 1 Steel Structure Replacement, Priority 1 Wood Structure Replacement, Protection NERC Compliance, Relay Upgrades, Replace Breakers, Replace Other Substation Equipment, Replace Transformers, Safety - Line Right of Way Access, SCADA Emergency Replacement, SCADA Switch Installation, Security Upgrades, Seismic Upgrade - Replace Conductor, Special Protection Scheme, Substation Capacity, Substation Reliability, System Design Upgrade, System Operations, Targeted Line Reliability, T-Line Capacity, T-Line Emergency, T-Line Reliability, Tools, Transformer Addition/Replacement, Underground Emergency, Voltage Conversion, Voltage Support. If the secondary purpose is to comply with a NERC, WECC, or CAISO requirement, list the standard, requirement, and/or any contingencies that are being addressed in the "Notes" data field. | May include, but not limited to: 3rd Party Damage, Age/Condition, Age/Condition - 230/115/70/60 kV Relay Replacement, Age/Condition - 500 kV Relay Replacement, Age/Condition - Anti Climb Guards, Age/Condition - Insulator Replacement - Steel, Age/Condition - Insulator Replacement - Wood, Age/Condition - Raptor Protection - Steel, Age/Condition - Replace 230/115/70/60 kV Breakers, Age/Condition - Replace 230/115/70/60 kV Transformers, Age/Condition - Replace 500 kV Breakers, Age/Condition - Replace 500 kV Transformers, Age/Condition - Replace Boardwalks, Age/Condition - Replace Breakers, Age/Condition - Replace Civil Structures, Age/Condition - Replace Conductor, Age/Condition - Replace Insulators, Age/Condition - Replace Other Substation Equipment, Age/Condition - Replace Other T-Line Equipment, Age/Condition - Replace Reactors, Age/Condition - Replace Relays, Age/Condition - Replace Relays, Age/Condition - Replace SCADA/RTU, Age/Condition - Replace Steel Poles, Age/Condition - Replace Switches, Age/Condition - Replace Transformers, Age/Condition - Replace Underground System, Age/Condition - Replace Wood Poles, Age/Condition - Switch Replacement - Steel, Age/Condition - Switch Replacement - Wood, Age/Condition - Targeted Relay Replacement, Age/Condition - Wood Pole Reframe, Animal Abatement, Automation, Bus Upgrade, Compliance - Remove Idle Facilities, Construct Roads/Gates/Culverts, Emergency Response - Fire Related, Emergency Response - Storm Related, Environmental, Facility Relocation, Fire Protection, Generation Interconnection, GO95 Mitigation - Steel, Install SCADA/RTU, Line Reconductoring, Line Termination, Load Interconnection, Modular Protection and Automation Control, NERC CIP Compliance, NERC Compliance - GO 95, New Substation, New T-Line, Priority 1 Steel Structure Replacement, Priority 1 Wood Structure Replacement, Protection NERC Compliance, Relay Upgrades, Replace Breakers, Replace Other Substation Equipment, Replace Transformers, Safety - Line Right of Way Access, SCADA Emergency Replacement, SCADA Switch Installation, Security Upgrades, Seismic Upgrade - Replace Conductor, Special Protection Scheme, Substation Capacity, Substation Reliability, System Design Upgrade, System Operations, Targeted Line Reliability, T-Line Capacity, T-Line Emergency, T-Line Reliability, Tools, Transformer Addition/Replacement, Underground Emergency, Voltage Conversion, Voltage Support. If the secondary purpose is to comply with a NERC, WECC, or CAISO requirement, list the standard, requirement, and/or any contingencies that are being addressed in the "Notes" data field. Example: Age/Condition - Anti Climb Guards
Project Description | 13 | 11 | NERC / WECC / CAISO Standard / Requirement / Contingency | Select text from drop-down menu(s) | CIP-006 | See drop-down menu for options. If more than two options are required, select "Multiple Options" in second column and provide remaining responses, pipe-delimited, in "Notes" data field. If the primary or secondary purpose relates to complying with a NERC, WECC, or CAISO requirement, list the specific standard(s), requirement(s), and/or any contingencies that are being addressed in the "Notes" data field. | See drop-down menu for options. If more than two options are required, select "Multiple Options" in second column and provide remaining responses, pipe-delimited, in "Notes" data field. If the primary or secondary purpose relates to complying with a NERC, WECC, or CAISO requirement, list the specific standard(s), requirement(s), and/or any contingencies that are being addressed in the "Notes" data field. Example: CIP-006
Project Description | 14 | 11 | NERC/WECC/CAISO Standard/Requirement/Contingency (2) | Select text from drop-down menu(s) | CIP-006 | See drop-down menu for options. If more than two options are required, select "Multiple Options" in second column and provide remaining responses, pipe-delimited, in "Notes" data field. If the primary or secondary purpose relates to complying with a NERC, WECC, or CAISO requirement, list the specific standard(s), requirement(s), and/or any contingencies that are being addressed in the "Notes" data field. | See drop-down menu for options. If more than two options are required, select "Multiple Options" in second column and provide remaining responses, pipe-delimited, in "Notes" data field. If the primary or secondary purpose relates to complying with a NERC, WECC, or CAISO requirement, list the specific standard(s), requirement(s), and/or any contingencies that are being addressed in the "Notes" data field. Example: CIP-006
Project Description | 15 | 12 | Last Inspection | Date, formatted YYYY-MM-DD if text; NA if not yet inspected | 2019-12-10 | Specific date when the last inspection of the asset being repaired, replaced, or upgraded occurred. | Specific date when the last inspection of the asset being repaired, replaced, or upgraded occurred. Example: 2019-12-10
Project Description | 16 | 13 | Age of Asset | Number (whole number) | 12 | Age in years from original in-service date of the asset being repaired, replaced, or upgraded. | Age in years from original in-service date of the asset being repaired, replaced, or upgraded. Example: 12
Project Description | 17 | 14 | Types of Analyses | Select text from drop-down menu | Load Flow | Types of analyses that have been performed on the asset being repaired, replaced, or upgraded (e.g., load flow, short circuit, corrosion). List all field test and results that indicated the need for the project, and include inspector ID, when available in the "Notes" data field. | Types of analyses that have been performed on the asset being repaired, replaced, or upgraded (e.g., load flow, short circuit, corrosion). List all field test and results that indicated the need for the project, and include inspector ID, when available in the "Notes" data field. Example: Load Flow
Project Description | 18 | 15a | Alternative Solutions and Costs - Solutions | Select text from drop-down menu(s) | Dynamic System Analysis | See drop-down menu for options. If more than two options are required, select "Multiple Options" in second column and provide remaining responses, pipe-delimited, in "Notes" data field. Include all alternative solutions to the project that were considered and the costs of all alternatives considered. | See drop-down menu for options. If more than two options are required, select "Multiple Options" in second column and provide remaining responses, pipe-delimited, in "Notes" data field. Include all alternative solutions to the project that were considered and the costs of all alternatives considered. Example: Dynamic System Analysis
Project Description | 19 | 15b | Alternative Solutions and Costs - Costs | Select text from drop-down menu(s) | $5 Mil - $10 Mil | See drop-down menu for options. If more than two options are required, select "Multiple Options" in second column and provide remaining responses, pipe-delimited, in "Notes" data field. If multiple responses as included for the Sulutions and Costs fields, please provide costs in the same order as solutions. | See drop-down menu for options. If more than two options are required, select "Multiple Options" in second column and provide remaining responses, pipe-delimited, in "Notes" data field. If multiple responses as included for the Sulutions and Costs fields, please provide costs in the same order as solutions. Example: $5 Mil - $10 Mil
Project Description | 20 | 16 | CPUC Fire Threat Zone/Rating | Text String, separated by " ¦ " as necessary, or NA | HFTD Tier 2 | Indicate whether the project is located in Tier1, Tier 2, or Tier 3 of CPUC's High Fire-Threat Districts (HFTD) or Zone 1 in CalFire/USFS High Hazard Zone (HHZ). | Indicate whether the project is located in Tier1, Tier 2, or Tier 3 of CPUC's High Fire-Threat Districts (HFTD) or Zone 1 in CalFire/USFS High Hazard Zone (HHZ). Example: HFTD Tier 2
Project Description | 21 | 17 | Wildfire Related | Boolean, TRUE or FALSE, divided by " ¦ " | TRUE ¦ TRUE ¦ FALSE | Indicate whether the project is 1. related to repairing wildfire damage, 2. a measure identified in the Wildfire Mitigation Plan, or 3. is related to wildfire in some other way. If #3, please explain in the "Notes" data field. | Indicate whether the project is 1. related to repairing wildfire damage, 2. a measure identified in the Wildfire Mitigation Plan, or 3. is related to wildfire in some other way. If #3, please explain in the "Notes" data field. Example: TRUE ¦ TRUE ¦ FALSE
Project Description | 22 | 18 | RAMP | Boolean, TRUE or FALSE | TRUE | Indicate whether the project is a proposed mitigation measure in the utility's Risk Assessment & Mitigation Phase (RAMP). | Indicate whether the project is a proposed mitigation measure in the utility's Risk Assessment & Mitigation Phase (RAMP). Example: TRUE
Project Description | 23 | 19 | Other Environmental Factors | Text String, or NA | Project exists in CA Building Climate Zone 3 which presents a high risk of accelerated oxidation or steel structures due to coastal humidity and salt exposure. | Environmental factors in the project's location that may affect the length of the asset's service life. | Environmental factors in the project's location that may affect the length of the asset's service life. Example: Project exists in CA Building Climate Zone 3 which presents a high risk of accelerated oxidation or steel structures due to coastal humidity and salt exposure.
Project Description | 24 | 20 | Project Manager | Text String: Last, First | Doe, John | Person in charge of the implementation of this project for the Utility. | Person in charge of the implementation of this project for the Utility. Example: Doe, John
Project Description | 25 | 21 | Transmission Project Size (length in miles) | Number (decimal), or NA | 42.66 | Miles of transmission power lines included in the project. | Miles of transmission power lines included in the project. Example: 42.66
Project Description | 26 | 22 | Substation Project Footprint (acres) | Number (decimal), or NA | 12.25 | Acres of substation footprint included in the project. | Acres of substation footprint included in the project. Example: 12.25
Project Description | 27 | 23 | Transmission Voltage Level (kV) | Number (whole), or NA | 230 | Use kV for transmission power lines ratings. | Use kV for transmission power lines ratings. Example: 230
Project Description | 28 | 24 | Substation or Transformer Capacity (MVA and/or kV) | Text String, or NA if unrelated | 115kV | Use MVA and/or kV for substations. | Use MVA and/or kV for substations. Example: 115kV
Project Description | 29 | 25 | Utility Prioritization Ranking | Number (whole), in reference to ranking system identified in field name | 1 | Using the Utility's prioritization ranking. If multiple metrics are used to prioritize projects, please include a separate data subfield for each. (Sub-columns can be created to accommodate multiple or tiered ranking methodologies.) | Using the Utility's prioritization ranking. If multiple metrics are used to prioritize projects, please include a separate data subfield for each. (Sub-columns can be created to accommodate multiple or tiered ranking methodologies.) Example: 1
Project Description | 30 | 26 | Work Order (Utility Unique ID #1) | Text String | 78493 | Most specific (PG&E = Planning Order, SCE = SCE ID, SDG&E = Project ID) | Most specific (PG&E = Planning Order, SCE = SCE ID, SDG&E = Project ID) Example: 78493
Project Description | 31 | 27 | Project ID (Utility Unique ID #2) | Text String | 432 | Less specific (PG&E = T.dot, SCE = Capital Work Breakdown Structure, SDG&E = Budget Code) | Less specific (PG&E = T.dot, SCE = Capital Work Breakdown Structure, SDG&E = Budget Code) Example: 432
Project Description | 32 | 28 | Budget Code (Utility Unique ID #3) | Text String | 92 | Least specific (PG&E = Major Work Category, SCE = Project Identification Number , SDG&E = NA) | Least specific (PG&E = Major Work Category, SCE = Project Identification Number , SDG&E = NA) Example: 92
Project Description | 33 | 29 | Changes in Unique IDs | Date, formatted YYYY-MM-DD, and former identifiers: YYYY-MM-DD ¦ UID1 ¦ UID2 ¦ UID 3 If any components remain unchanged, use NA for those UIDs | 2022-05-05 ¦ NA ¦ NA ¦ 78322 | If any of the Unique IDs above changed at any time, please note the date of change and the former ID. | If any of the Unique IDs above changed at any time, please note the date of change and the former ID. Example: 2022-05-05 ¦ NA ¦ NA ¦ 78322
Utility/CAISO Approval and FERC Rate Cases | 34 | 30 | Utility Approval | Boolean: TRUE or FALSE | TRUE | "TRUE" if the Utility self-approved the project; "FALSE" if not. | "TRUE" if the Utility self-approved the project; "FALSE" if not. Example: TRUE
Utility/CAISO Approval and FERC Rate Cases | 35 | 31 | Year of Internal Utility Approval | Date, formatted YYYY-MM-DD, or NA | 2022-01-02 | If utility has approved the project, insert first year of internal approval. If not insert "NA." | If utility has approved the project, insert first year of internal approval. If not insert "NA." Example: 2022-01-02
Utility/CAISO Approval and FERC Rate Cases | 36 | 32 | Process(es) for Utility Approval | Text String, or NA | Annual Capital Operating Plan Process | If utility has approved the project, insert utility approval process for which a description has been provided to the CPUC and Stakeholders. | If utility has approved the project, insert utility approval process for which a description has been provided to the CPUC and Stakeholders. Example: Annual Capital Operating Plan Process
Utility/CAISO Approval and FERC Rate Cases | 37 | 33 | Long term Transmission Investment Plan Inclusion | Year, formatted YYYY | 2022 | The year in which the project was first included in the utility's long-term transmission investment plan. | The year in which the project was first included in the utility's long-term transmission investment plan. Example: 2022
Utility/CAISO Approval and FERC Rate Cases | 38 | 34 | CAISO Year | Year, formatted YYYY, or NA | 2019 | Insert the year when approved by CAISO. If not a CAISO-approved project, insert "NA". | Insert the year when approved by CAISO. If not a CAISO-approved project, insert "NA". Example: 2019
Utility/CAISO Approval and FERC Rate Cases | 39 | 35 | Transmission Planning Process ("TPP") Phase 3 | Boolean: TRUE or FALSE | FALSE | Please indicate with "TRUE" if any part of this project was subject to the competitive solicitation process in the TPP. In the "Notes" section briefly describe any portion of the project awarded to another developer and how it relates to the project in this Spreadsheet. | Please indicate with "TRUE" if any part of this project was subject to the competitive solicitation process in the TPP. In the "Notes" section briefly describe any portion of the project awarded to another developer and how it relates to the project in this Spreadsheet. Example: FALSE
Utility/CAISO Approval and FERC Rate Cases | 40 | 36 | Year(s) when considered in CAISO TPP | Years, formatted YYYY and separated by " ¦ ", or NA | 2020 ¦ 2021 | Indicate years in which the project was considered in the TPP. If considered in year(s) prior to CAISO approval, please indicate all years. | Indicate years in which the project was considered in the TPP. If considered in year(s) prior to CAISO approval, please indicate all years. Example: 2020 ¦ 2021
Utility/CAISO Approval and FERC Rate Cases | 41 | 37 | Year when expected to be considered in CAISO TPP | Years, formatted YYYY and separated by " ¦ ", or NA | 2025 | If not yet considered in the CAISO TPP, indicate the year when it is expected to be considered in the CAISO TPP. | If not yet considered in the CAISO TPP, indicate the year when it is expected to be considered in the CAISO TPP. Example: 2025
Utility/CAISO Approval and FERC Rate Cases | 42 | 38 | Link to TPP where project has been considered, approved, and/or expected to be considered | URL | http://www.caiso.com/Documents/BoardApproved-2017-2018_Transmission_Plan.pdf | Insert active hyperlink to any TPP where project was considered, including years in which the project was not approved. | Insert active hyperlink to any TPP where project was considered, including years in which the project was not approved. Example: http://www.caiso.com/Documents/BoardApproved-2017-2018_Transmission_Plan.pdf
Utility/CAISO Approval and FERC Rate Cases | 43 | 39 | Generator Interconnection and Deliverability Allocation Procedures (GIDAP) Related | Boolean: TRUE or FALSE | TRUE | Please indicate with TRUE or FALSE whether this transmission project is a transmission network upgrade related to generator interconnection(s). | Please indicate with TRUE or FALSE whether this transmission project is a transmission network upgrade related to generator interconnection(s). Example: TRUE
CPUC Permit Status | 44 | 40a | CEQA Status | Select text from drop-down menu | Final Certified | See drop-down menu for options. Include one of the following: Expected PEA Completion, PEA Deemed Complete, CEQA Draft Published, CEQA Final Published, Final Certified, TBD, Other [See Notes], or NA. | See drop-down menu for options. Include one of the following: Expected PEA Completion, PEA Deemed Complete, CEQA Draft Published, CEQA Final Published, Final Certified, TBD, Other [See Notes], or NA. Example: Final Certified
CPUC Permit Status | 45 | 40b | CEQA Status - Date | Date, formatted YYYY-MM-DD, or NA | 2020-03-29 | Include the date that corresponds with the CEQA status. | Include the date that corresponds with the CEQA status. Example: 2020-03-29
CPUC Permit Status | 46 | 41a | CEQA Document Type | Select text from drop-down menu | EIR | Examples include: IS/ND, IS/MND, EIR, Exempted, Other, or NA (If "Other," include explanation in the "Notes" data field.). | Examples include: IS/ND, IS/MND, EIR, Exempted, Other, or NA (If "Other," include explanation in the "Notes" data field.). Example: EIR
CPUC Permit Status | 47 | 41b | NEPA Document Type | Select text from drop-down menu | EIS | Examples include: EIS, EA, Categorical Exclusion, Other, or NA (If "Other," include explanation in the "Notes" data field.). | Examples include: EIS, EA, Categorical Exclusion, Other, or NA (If "Other," include explanation in the "Notes" data field.). Example: EIS
CPUC Permit Status | 48 | 42a | CEQA Lead Agency | Text String, separated by " ¦ " as necessary, or NA | CPUC | Examples include: CPUC, SWRCB, CSLC, NA etc. If more than two options are required, enter each, pipe-delimited. | Examples include: CPUC, SWRCB, CSLC, NA etc. If more than two options are required, enter each, pipe-delimited. Example: CPUC
CPUC Permit Status | 49 | 42b | NEPA Lead Agency | Text String, separated by " ¦ " as necessary, or NA | USFS | Examples include: USFS, NA etc. If more than two options are required, enter each, pipe-delimited. | Examples include: USFS, NA etc. If more than two options are required, enter each, pipe-delimited. Example: USFS
CPUC Permit Status | 50 | 43 | CPUC Filing Type | Text String, or NA | PG&E AL 2355-E | NOC Advice Letter (AL), Application for 851, PTC, CPCN, or NA. If an AL, include the number. If an Application, include number. | NOC Advice Letter (AL), Application for 851, PTC, CPCN, or NA. If an AL, include the number. If an Application, include number. Example: PG&E AL 2355-E
CPUC Permit Status | 51 | 44 | CPUC Date Filed | Date, formatted YYYY-MM-DD, or NA | 2022-04-08 | The year filed at the CPUC or insert "Not yet filed" with the expected filing date. | The year filed at the CPUC or insert "Not yet filed" with the expected filing date. Example: 2022-04-08
CPUC Permit Status | 52 | 45 | CPUC Status | Select text from drop-down menu | Approved | Indicate "Approved", "Rejected", "To be Filed", "Filed and Under Review," "Other," or "NA" (If "Other" or "NA", include explanation in the "Notes" data field.). | Indicate "Approved", "Rejected", "To be Filed", "Filed and Under Review," "Other," or "NA" (If "Other" or "NA", include explanation in the "Notes" data field.). Example: Approved
CPUC Permit Status | 53 | 46 | CPUC Status: Year | Year, formatted YYYY, or NA | 2019 | Insert the year this CPUC Status was determined. | Insert the year this CPUC Status was determined. Example: 2019
Project status | 54 | 47 | Project Status | Select text from drop-down menu | Construction (10%-25%) | See drop-down menu for options. Examples include: Planning, Engineering less than 50% complete, Engineering more than 50% complete, Permitting, Construction (include percentage of construction completed at the time this data spreadsheet is provided (i.e., less than 10%, 10%-25%, 25%-50%, 50%-75%, greater than 75%), Operational, On Hold, Canceled, or Abandoned (if On Hold, Canceled, or Abandoned, include explanation in the "Notes" data field.). | See drop-down menu for options. Examples include: Planning, Engineering less than 50% complete, Engineering more than 50% complete, Permitting, Construction (include percentage of construction completed at the time this data spreadsheet is provided (i.e., less than 10%, 10%-25%, 25%-50%, 50%-75%, greater than 75%), Operational, On Hold, Canceled, or Abandoned (if On Hold, Canceled, or Abandoned, include explanation in the "Notes" data field.). Example: Construction (10%-25%)
Project status | 55 | 48 | AACE Class | Select text from drop-down menu | 3 | The current Estimate Class in AACE International's Cost Estimate Classification System at the time this data spreadsheet is provided. | The current Estimate Class in AACE International's Cost Estimate Classification System at the time this data spreadsheet is provided. Example: 3
Project status | 56 | 49 | Construction Start Date | Date, formatted YYYY-MM-DD, or NA | 45809 | The date on which construction began or is expected to begin. | The date on which construction began or is expected to begin. Example: 45809
Project status | 57 | 50 | Original Planned In- Service Date | Date, formatted YYYY-MM-DD, or NA* | 45809 | What was the expected in-service date when the project was first approved by the CAISO? If not a CAISO-approved project, provide the expected in-service date when the project was approved internally by the Utility. | What was the expected in-service date when the project was first approved by the CAISO? If not a CAISO-approved project, provide the expected in-service date when the project was approved internally by the Utility. Example: 45809
Project status | 58 | 51 | Current Projected or Actual In-Service Date | Date, formatted YYYY-MM-DD, followed by OAI indicator if applicable (or NA) | 2021-01-01 ¦ NA 2021-01-01 ¦ OAI | At the time the data was extracted from the Utility’s Database(s) as provided in Section 2.1.5 of the Transmission Project Review Process Description. Projects without identified in-service dates that are "Operative as Installed" should be identified as "OAI". | At the time the data was extracted from the Utility’s Database(s) as provided in Section 2.1.5 of the Transmission Project Review Process Description. Projects without identified in-service dates that are "Operative as Installed" should be identified as "OAI". Example: 2021-01-01 ¦ NA 2021-01-01 ¦ OAI
Project status | 59 | 52 | Reason for Change in In- Service Date | Select text from drop-down menu(s) | Customer Action | See drop-down menu for options. If the current projected or actual in-service date varies more than six months from the original in-service date, please select all reasons for this change. If more than two options are required, select "Multiple Options" in second column and provide remaining responses, pipe-delimited, in "Notes" data field. | See drop-down menu for options. If the current projected or actual in-service date varies more than six months from the original in-service date, please select all reasons for this change. If more than two options are required, select "Multiple Options" in second column and provide remaining responses, pipe-delimited, in "Notes" data field. Example: Customer Action
Project status | 60 | 52 | Reason for Change in In-Service Date (2) | Select text from drop-down menu(s) | Customer Action | See drop-down menu for options. If the current projected or actual in-service date varies more than six months from the original in-service date, please select all reasons for this change. If more than two options are required, select "Multiple Options" in second column and provide remaining responses, pipe-delimited, in "Notes" data field. | See drop-down menu for options. If the current projected or actual in-service date varies more than six months from the original in-service date, please select all reasons for this change. If more than two options are required, select "Multiple Options" in second column and provide remaining responses, pipe-delimited, in "Notes" data field. Example: Customer Action
Project status | 61 | 53 | In-Flight Projects | Boolean: TRUE or FALSE | TRUE | For projects with costs expected to go into rate base in the current rate year or in the following rate year at FERC, please indicate with "TRUE." If there will be no additions to rate base in either year, indicate with "FALSE." | For projects with costs expected to go into rate base in the current rate year or in the following rate year at FERC, please indicate with "TRUE." If there will be no additions to rate base in either year, indicate with "FALSE." Example: TRUE
Costs | 62 | 54 | Original Projected Cost or Cost Range ($000) | Dollar value, or dollar value range, separated by " ¦ " | 2100 ¦ 2500 | Forecast cost or forecast cost range for Utility Unique ID #2, i.e., the totality of the project, at the earliest of CAISO, CPUC, or utility internal approval. | Forecast cost or forecast cost range for Utility Unique ID #2, i.e., the totality of the project, at the earliest of CAISO, CPUC, or utility internal approval. Example: 2100 ¦ 2500
Costs | 63 | 55 | Cost Cap ($000) | Dollar value and Text String, separated by " ¦ ", or NA | 2500 ¦ CAISO TPP | Insert Cost Cap on project if available, as well as the authority imposing the cost cap. This shall include any maximum cost determined to be reasonable and prudent in a CPUC proceeding or a cost cap set for a competitively bid project in the CAISO's Transmission Planning Process. | Insert Cost Cap on project if available, as well as the authority imposing the cost cap. This shall include any maximum cost determined to be reasonable and prudent in a CPUC proceeding or a cost cap set for a competitively bid project in the CAISO's Transmission Planning Process. Example: 2500 ¦ CAISO TPP
Costs | 64 | 56 | Current Projected Total or Actual Final Cost ($000) | Dollar value | 78 | Updated projected fully-loaded total or actual fully loaded final cost of project. Projected total should be the anticipated sum of all capital expenditures, overhead,and AFUDC. Actual cost should be the total expenditures, overhead and AFUDC in the addition to rate base. Operational projects and all data must remain in this report for at least five (5) years after the last of the project's expenditures and capital additions. | Updated projected fully-loaded total or actual fully loaded final cost of project. Projected total should be the anticipated sum of all capital expenditures, overhead,and AFUDC. Actual cost should be the total expenditures, overhead and AFUDC in the addition to rate base. Operational projects and all data must remain in this report for at least five (5) years after the last of the project's expenditures and capital additions. Example: 78
Costs | 65 | 57 | 2019 Actual Capital Expenditures ($000) | Dollar value | 12 | Please include separate columns for each of the previous five (5) years and one for actual expenditures for the current year as of the date the data was extracted. If these expenditures do not include overheads and AFUDC, please provide those year-by-year. | Please include separate columns for each of the previous five (5) years and one for actual expenditures for the current year as of the date the data was extracted. If these expenditures do not include overheads and AFUDC, please provide those year-by-year. Example: 12
Costs | 66 | 57 B | 2020 Actual Capital Expenditures ($000) | Dollar value | 12 | Please include separate columns for each of the previous five (5) years and one for actual expenditures for the current year as of the date the data was extracted. If these expenditures do not include overheads and AFUDC, please provide those year-by-year. | Please include separate columns for each of the previous five (5) years and one for actual expenditures for the current year as of the date the data was extracted. If these expenditures do not include overheads and AFUDC, please provide those year-by-year. Example: 12
Costs | 67 | 57 C | 2021 Actual Capital Expenditures ($000) | Dollar value | 12 | Please include separate columns for each of the previous five (5) years and one for actual expenditures for the current year as of the date the data was extracted. If these expenditures do not include overheads and AFUDC, please provide those year-by-year. | Please include separate columns for each of the previous five (5) years and one for actual expenditures for the current year as of the date the data was extracted. If these expenditures do not include overheads and AFUDC, please provide those year-by-year. Example: 12
Costs | 68 | 57 D | 2022 Actual Capital Expenditures ($000) | Dollar value | 12 | Please include separate columns for each of the previous five (5) years and one for actual expenditures for the current year as of the date the data was extracted. If these expenditures do not include overheads and AFUDC, please provide those year-by-year. | Please include separate columns for each of the previous five (5) years and one for actual expenditures for the current year as of the date the data was extracted. If these expenditures do not include overheads and AFUDC, please provide those year-by-year. Example: 12
Costs | 69 | Internal | October 2023 YTD Actual Capital Expenditures ($000) | Dollar value | 12 | Please include separate columns for each of the previous five (5) years and one for actual expenditures for the current year as of the date the data was extracted. If these expenditures do not include overheads and AFUDC, please provide those year-by-year. | Please include separate columns for each of the previous five (5) years and one for actual expenditures for the current year as of the date the data was extracted. If these expenditures do not include overheads and AFUDC, please provide those year-by-year. Example: 12
Costs | 70 | 58 | Nov & Dec 2023 Projected Capital Expenditures ($000) | Dollar value | 4650 | For the current year and four (4) future years, provide the year-by-year fully-loaded forecast capital expenditures for the project. Please include separate columns for each year. If these expenditures do not include overheads and AFUDC, please provide those year-by-year. | For the current year and four (4) future years, provide the year-by-year fully-loaded forecast capital expenditures for the project. Please include separate columns for each year. If these expenditures do not include overheads and AFUDC, please provide those year-by-year. Example: 4650
Costs | 71 | 58 B | 2024 Projected Capital Expenditures ($000) | Dollar value | 4650 | For the current year and four (4) future years, provide the year-by-year fully-loaded forecast capital expenditures for the project. Please include separate columns for each year. If these expenditures do not include overheads and AFUDC, please provide those year-by-year. | For the current year and four (4) future years, provide the year-by-year fully-loaded forecast capital expenditures for the project. Please include separate columns for each year. If these expenditures do not include overheads and AFUDC, please provide those year-by-year. Example: 4650
Costs | 72 | 58 C | 2025 Projected Capital Expenditures ($000) | Dollar value | 4650 | For the current year and four (4) future years, provide the year-by-year fully-loaded forecast capital expenditures for the project. Please include separate columns for each year. If these expenditures do not include overheads and AFUDC, please provide those year-by-year. | For the current year and four (4) future years, provide the year-by-year fully-loaded forecast capital expenditures for the project. Please include separate columns for each year. If these expenditures do not include overheads and AFUDC, please provide those year-by-year. Example: 4650
Costs | 73 | 58 D | 2026 Projected Capital Expenditures ($000) | Dollar value | 4650 | For the current year and four (4) future years, provide the year-by-year fully-loaded forecast capital expenditures for the project. Please include separate columns for each year. If these expenditures do not include overheads and AFUDC, please provide those year-by-year. | For the current year and four (4) future years, provide the year-by-year fully-loaded forecast capital expenditures for the project. Please include separate columns for each year. If these expenditures do not include overheads and AFUDC, please provide those year-by-year. Example: 4650
Costs | 74 | 58 E | 2027 Projected Capital Expenditures ($000) | Dollar value | 4650 | For the current year and four (4) future years, provide the year-by-year fully-loaded forecast capital expenditures for the project. Please include separate columns for each year. If these expenditures do not include overheads and AFUDC, please provide those year-by-year. | For the current year and four (4) future years, provide the year-by-year fully-loaded forecast capital expenditures for the project. Please include separate columns for each year. If these expenditures do not include overheads and AFUDC, please provide those year-by-year. Example: 4650
Costs | 75 | 58 F | 2028 Projected Capital Expenditures ($000) | Dollar value | 4650 | For the current year and four (4) future years, provide the year-by-year fully-loaded forecast capital expenditures for the project. Please include separate columns for each year. If these expenditures do not include overheads and AFUDC, please provide those year-by-year. | For the current year and four (4) future years, provide the year-by-year fully-loaded forecast capital expenditures for the project. Please include separate columns for each year. If these expenditures do not include overheads and AFUDC, please provide those year-by-year. Example: 4650
Costs | 76 | 59 | Construction Work in Progress Expenditures ($000) | Dollar value | 2350 | Total amount of money that has been spent so far for the project through the last calendar year. | Total amount of money that has been spent so far for the project through the last calendar year. Example: 2350
Costs | 77 | 60 | Accrued Overhead | Dollar value | 12 | If the capital expenditures provided in Data Field #57 do not include Overhead, please provide the accrued Overhead through the last calendar year. | If the capital expenditures provided in Data Field #57 do not include Overhead, please provide the accrued Overhead through the last calendar year. Example: 12
Costs | 78 | 61 | Accrued AFUDC | Dollar value | 0 | If the capital expenditures provided in Data Field #57 do not include AFUDC, please provide the accrued AFUDC through the last calendar year. | If the capital expenditures provided in Data Field #57 do not include AFUDC, please provide the accrued AFUDC through the last calendar year. Example: 0
Costs | 79 | 62 | FERC: Year(s) | Years, separated by " ¦ ", or NA | 2023 ¦ 2024 ¦ 2025 ¦ 2026 ¦ 2027 | Insert ALL rate years when any costs of this project went - or are forecast to go - into FERC jurisdictional transmission rate base. | Insert ALL rate years when any costs of this project went - or are forecast to go - into FERC jurisdictional transmission rate base. Example: 2023 ¦ 2024 ¦ 2025 ¦ 2026 ¦ 2027
Costs | 80 | 63 | 2020 Actual FERC Dollars Ratebased ($000) | Dollar Value, per year column e.g., FERC_dollars_in_rate_base_2022 | 500000 | Insert the year(s) and actual dollars added to FERC jursidictional transmission rate base on the project for each of the four prior years and the present year. This should include additional costs added to rate base in years after operation first occurred. | Insert the year(s) and actual dollars added to FERC jursidictional transmission rate base on the project for each of the four prior years and the present year. This should include additional costs added to rate base in years after operation first occurred. Example: 500000
Costs | 81 | 63 B | 2021 Actual FERC Dollars Ratebased ($000) | Dollar Value, per year column e.g., FERC_dollars_in_rate_base_2023 | 500000 | Insert the year(s) and actual dollars added to FERC jursidictional transmission rate base on the project for each of the four prior years and the present year. This should include additional costs added to rate base in years after operation first occurred. | Insert the year(s) and actual dollars added to FERC jursidictional transmission rate base on the project for each of the four prior years and the present year. This should include additional costs added to rate base in years after operation first occurred. Example: 500000
Costs | 82 | 63 C | 2022 Actual FERC Dollars Ratebased ($000) | Dollar Value, per year column e.g., FERC_dollars_in_rate_base_2024 | 500000 | Insert the year(s) and actual dollars added to FERC jursidictional transmission rate base on the project for each of the four prior years and the present year. This should include additional costs added to rate base in years after operation first occurred. | Insert the year(s) and actual dollars added to FERC jursidictional transmission rate base on the project for each of the four prior years and the present year. This should include additional costs added to rate base in years after operation first occurred. Example: 500000
Costs | 83 | 63 D | October 2023 YTD Actual FERC Dollars Ratebased ($000) | Dollar Value, per year column e.g., FERC_dollars_in_rate_base_2025 | 500000 | Insert the year(s) and actual dollars added to FERC jursidictional transmission rate base on the project for each of the four prior years and the present year. This should include additional costs added to rate base in years after operation first occurred. | Insert the year(s) and actual dollars added to FERC jursidictional transmission rate base on the project for each of the four prior years and the present year. This should include additional costs added to rate base in years after operation first occurred. Example: 500000
Costs | 84 | 63 E | Nov & Dec 2023 Projected FERC Dollars Ratebased ($000) | Dollar Value, per year column e.g., FERC_dollars_in_rate_base_2026 | 500000 | Insert the year(s) and actual dollars added to FERC jursidictional transmission rate base on the project for each of the four prior years and the present year. This should include additional costs added to rate base in years after operation first occurred. | Insert the year(s) and actual dollars added to FERC jursidictional transmission rate base on the project for each of the four prior years and the present year. This should include additional costs added to rate base in years after operation first occurred. Example: 500000
Costs | 85 | 63 F | 2024 Projected FERC Dollars Ratebased ($000) | Dollar Value, per year column e.g., FERC_dollars_in_rate_base_2027 | 500000 | Insert the year(s) and actual dollars added to FERC jursidictional transmission rate base on the project for each of the four prior years and the present year. This should include additional costs added to rate base in years after operation first occurred. | Insert the year(s) and actual dollars added to FERC jursidictional transmission rate base on the project for each of the four prior years and the present year. This should include additional costs added to rate base in years after operation first occurred. Example: 500000
Costs | 86 | 64 | Percentage of Bid | Percentage to two decimals, and Text String, separated by " ¦ " | 33.33% ¦ "SuperPower LLC is developing a third of the project as part of its "TransValley Electrification" project. See http://.... | Percentage (or actual cost) of project implemented by outside developer, as opposed to the incumbent utility. If there is a project being developed by a non-incumbent utility that relates to this project, please indicate the name of the project as approved in the CAISO TPP. | Percentage (or actual cost) of project implemented by outside developer, as opposed to the incumbent utility. If there is a project being developed by a non-incumbent utility that relates to this project, please indicate the name of the project as approved in the CAISO TPP. Example: 33.33% ¦ "SuperPower LLC is developing a third of the project as part of its "TransValley Electrification" project. See http://....
Costs | 87 | 65 | Percentage of Work Requested by Others Passed onto Ratepayers | Percentage to two decimals and/or dollar value. If both, separate by " ¦ ". If either is not provided, please enter NA. | 25.00% ¦ 2300 35% ¦ NA NA ¦ 50000 | If the project is work requested by others or customer-driven, what percentage of the projects costs has been - or is expected to be - passed onto ratepayers? If the dollar amount being passed onto ratepayers is fixed, then this number can be expressed as a dollar amount. | If the project is work requested by others or customer-driven, what percentage of the projects costs has been - or is expected to be - passed onto ratepayers? If the dollar amount being passed onto ratepayers is fixed, then this number can be expressed as a dollar amount. Example: 25.00% ¦ 2300 35% ¦ NA NA ¦ 50000
Costs | 88 | 66 | Cost-Benefit Analysis | Percentage to two decimals, and ranking system identifier, separated by " ¦ " | 25.00% ¦ EnergyRank | The Cost-to-Benefit ratio. If the Utility's Cost-Benefit analysis related to its Risk-Based Decision-Making Framework (RDF) has not already been included in the "Utility Prioritization Ranking" data field above, please include it here. | The Cost-to-Benefit ratio. If the Utility's Cost-Benefit analysis related to its Risk-Based Decision-Making Framework (RDF) has not already been included in the "Utility Prioritization Ranking" data field above, please include it here. Example: 25.00% ¦ EnergyRank
Costs | 89 | 67 | FERC Incentives | Test Strings, separated by " ¦ ", or NA | Abandoned Plant ¦ CWIP | List any project-specific transmission incentives granted under any FERC Orders. | List any project-specific transmission incentives granted under any FERC Orders. Example: Abandoned Plant ¦ CWIP
Costs | 90 | 68 | Percentage of Cost in High Voltage TAC | Percentage to two decimals | 0.2305 | Insert % of project cost recovered in the high-voltage TAC. | Insert % of project cost recovered in the high-voltage TAC. Example: 0.2305
Costs | 91 | 69 | Percentage of Cost in Low Voltage TAC | Percentage to two decimals | 0 | Insert % of project cost recovered in the low-voltage TAC. | Insert % of project cost recovered in the low-voltage TAC. Example: 0
Notes | 92 | 70 | Notes | Strings, inclusive of field identifiers in brackets, separated by 3 linebreaks ("\n\n\n"), or NA [ID1] String1 [ID2] String2 | [CEQA/NEPA Document Type] Form STD762 [CPUC Status] Approved in part following bifurcation. Details indeterminate as of 5/6/2024. Expected update and clarification by 8/1/2024. | Any additionally requested information or other needed details about the project that were not otherwise covered. | Any additionally requested information or other needed details about the project that were not otherwise covered. Example: [CEQA/NEPA Document Type] Form STD762 [CPUC Status] Approved in part following bifurcation. Details indeterminate as of 5/6/2024. Expected update and clarification by 8/1/2024.