## Project List
| Project Description | [32 empty] | Utility ¦CAISO Approval and FERC Rate Cases | [9 empty] | CPUC Permit Status | [9 empty] | Project Status | [7 empty] | Cost
1 | 2 | 3a | 3b | 4 | 5 | 6 | 7 | 7 | 8 | 9 | 10 | 11 | 11 | 12 | 13 | 14 | 15a | 15b | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 27b | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40a | 40b | 41a | 41b | 42a | 42b | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 52 | 53 | 54 | 55 | 56 | 57 | 57 | 57 | 57 | 57 | 57 | 58 | 58 | 58 | 58 | 58 | 59 | 60 | 61 | 62 | 63 | 63 | 63 | 63 | 63 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70
Row No | Project Name(s) | Latitude | Longitude | Location | Project Description | Project Description - What | Project Description - Action Taken | Project Description - Action Taken (2) | Project Dependencies | Primary Purpose | Secondary Purpose | NERC/WECC/CAISO Standard/Requirement/Contingency | NERC/WECC/CAISO Standard/Requirement/Contingency (2) | Last Inspection | Age of Asset | Types of Analyses | Alternative Solutions and Costs - Solutions | Alternative Solutions and Costs - Costs | CPUC Fire Threat Zone/Rating | Wildfire Related | RAMP | Other Environmental Factors | Project Manager | Transmission Project Size (length in miles) | Substation Project Footprint (acres) | Transmission Voltage Level (kV) | Substation or Transformer Capacity (MVA and/or kV) | Utility Prioritization Ranking | Utility Unique ID #1(Most Specific) | Utility Unique ID #2 (Less Specific) | Total Number of Projects under Parent Work Order | Utility Unique ID #3 (Least Specific) | Changes in Unique IDs | Utility Approval | Year of Internal Utility Approval | Process(es) for Utility Approval | Long term Transmission Investment Plan Inclusion | CAISO Year | TPP Phase 3 | Year(s) when considered in CAISO TPP | Year when expected to be considered in CAISO TPP | Link to TPP where project has been considered, approved, and/or expected to be considered | GIDAP-Related | CEQA Status | CEQA Status - Date | CEQA Document Type | NEPA Document Type | CEQA Lead Agency | NEPA Lead Agency | CPUC Filing Type | CPUC Date Filed | CPUC Status | CPUC Status - Year | Project Status | AACE Class | Construction Start Date | Original Planned In-Service Date | Current Projected or Actual In-Service Date | Reason for Change in In-Service Date | Reason for Change in In-Service Date (2) | In-Flight Projects | Original Projected Cost or Cost Range ($000) | Cost Cap ($000) | Current Projected Total or Actual Final Cost ($000) | Actual Capital Expenditures 2021 ($000) | Actual Capital Expenditures 2022 ($000) | Actual Capital Expenditures 2023 ($000) | Actual Capital Expenditures 2024 ($000) | Actual Capital Expenditures 2025($000) | Actual Capital Expenditures 2026($000) | Projected Capital Expenditures 2026 ($000) | Projected Capital Expenditures 2027 ($000) | Projected Capital Expenditures 2028 ($000) | Projected Capital Expenditures 2029 ($000) | Projected Capital Expenditures 2030 ($000) | Construction Work in Progress ($000) | Accrued Overhead ($000) | Accrued AFUDC ($000) | FERC: Year(s) | 2021 Actual FERC Dollars Ratebased ($000) | 2022 Actual FERC Dollars Ratebased ($000) | 2023 Actual FERC Dollars Ratebased ($000) | 2024 Actual FERC Dollars Ratebased ($000) | 2025 Actual FERC Dollars Ratebased ($000) | 2026 Projected FERC Dollars Ratebased ($000) | Percentage of Bid | Percentage and Value ($000) of Work Requested by Others Passed onto Ratepayers | Cost-Benefit Analysis | FERC Incentives | Percentage of Cost in High Voltage TAC | Percentage of Cost in Low Voltage TAC | Notes
1 | [Programmatic] Synchrophasors (PMU/WASA) |  |  | Multiple | This project provides funds for the installation, upgrade, and expansion of SDG&E’s Phasor Measurement Units (PMUs), commonly referred to as Synchronized Phasors or Synchrophasors which will be used for monitoring the health of the Electric System, Wide Area situational Awareness (WASA) and Wide Area Monitoring Protection and Control (WAMPAC). The project will install new PMUs or upgrade existing PMUs and install Phasor Data Concentrators (PDC), hardware, associated communication network, and software. | Substation - Protection Relay | Replace | Upgrade/Retrofit | NA | Reliability | Relay Upgrades | NA | NA | NA | NA | Short Circuit Duty Analysis | NA | NA | Multiple | FALSE ¦ FALSE ¦ FALSE | FALSE | Individual Project Review Required |  | NA | NA | Multiple | 138kV¦230kV¦500kV | 4.3 | Multiple | QBL0062 | 67 | 10138 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-12-11 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | TBD | TBD | NA | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | NA | NA | NA | NA | NA | TRUE | NA | NA ¦ NA | 28525.0848 | 639.667 | -147.8552 | 102.4974 | 640.9089 | 1373.2488 | 1195.5218 | 2541.3215 | 4020.4831 | 4432.1033 | 4603.6909 | 0 | 1398.6556 | NA | NA | 2021 ¦ 2023 ¦ 2024 ¦ 2025 ¦ 2026 | 11.5456 | 0 | 1058.2385 | -1.5629 | 1337.1117 | 4502.0095 | 0% | NA ¦ NA | 5.2 | NA | 45.85% | 54.15% | [CPUC Status] Exempt
2 | SYNCHRO VSUBS 2022 |  |  | Escondido, San Diego | PMU/WASA deployments at multiple substations | Substation - Protection Relay | Upgrade/Retrofit | NA | NA | Reliability | Relay Upgrades | NA | NA | 2026-05-22 | NA | NA | NA | NA | Multiple | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69 ¦ 500 | 373MVA | 4.3 | Multiple | QBL0062 | 1 | 10138 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2021-12-01 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | NA | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2023-04-17 | 2023-12-31 | 2024-10-25 | Prioritization | NA | FALSE | 9874.4119 | NA ¦ NA | 7261.7303 | 674.9986 | 2679.2701 | 2462.7281 | 1464.331 | -19.5975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2024 ¦ 2025 | 0 | 0 | 0 | 7281.3278 | -19.5975 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 45.85% | 54.15% | [CPUC Status] Exempt [Utility Unique ID #1(Most Specific)] 2021-2149 , 2022-3042
3 | WASA SYNCHROWAVE SOFTWARE APPL |  |  | San Diego, San Diego | Continued development of WASA-Synchrowave Central software application. Enhancements includes Linear State Estimating (LSE), Phase Contour, addition of Operations and Admin roles, phase angle reference, and support for end-user configuration. | Other - Operations Tech | Upgrade/Retrofit | NA | NA | Reliability | Automation | NERC CIP Compliance | NERC CIP Compliance | NA | NA | NA | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | NA | NA | 4.3 | NA | QBL0062 | 1 | 10138 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-10-30 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2024-01-01 | 2025-12-31 | 2025-12-31 | NA | NA | FALSE | 1585.0195 | NA ¦ NA | 3687.1534 | 0 | 0 | 0 | 1448.4178 | 1237.3539 | 172.72 | 643.9708 | 184.6909 | 0 | 0 | 0 | 2858.4916 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] Exempt
4 | TRANS SYNCHROPHASOR VAR SUB |  |  | Multiple | PMU/WASA deployments at multiple substations | Substation - Protection Relay | Upgrade/Retrofit | NA | NA | Reliability | Relay Upgrades | NA | NA | NA | NA | NA | NA | NA | Multiple | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69 ¦ 500 | 373MVA | 4.3 | Multiple | QBL0062 | 1 | 10138 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2018-03-23 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | NA | 2019-03-31 | Multiple | NA | NA | FALSE | 1403.683 | NA ¦ NA | 23694.0135 | 6187.6461 | 83.5886 | 271.2511 | 130.0683 | -87.9033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 6187.6461 | 83.5886 | 271.2511 | 130.0683 | -87.9033 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 45.85% | 54.15% | [CPUC Status] Exempt [Utility Unique ID #1(Most Specific)] 2021-2143 , 2023-3601 , 2021-2051 , 2021-2042 , 2021-2026 , 2022-2933 , 2022-2935 , 2021-2401 , 2021-2130 , 2021-2149 , 2021-2132 , 2021-2134 , 2021-2148 , 2021-2136 , 2023-3594 , 2023-3600 , 2023-3602 , 2018-1009 , 2021-2131 , 2019-2124 , 2023-3595 , 2021-2035
5 | [Programmatic] Transmission Substation Responsive Asset Replacement |  |  | Multiple | This budget is required to maintain the reliability and integrity of Transmission substations. The specific work required to meet safety requirements, replace obsolete or failed equipment, and make necessary small capital additions is based on requests from Engineering, Planning, Operations, and Maintenance groups. | Substation - Multiple | New | Upgrade/Retrofit | NA | Reliability | Substation Reliability | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | Multiple | NA | 4.1 | Multiple | QB00012 | 145 | 103 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-12-16 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | NA | NA | To be Filed | NA | Operational | NA | NA | NA | NA | NA | NA | TRUE | NA | NA ¦ NA | 103608.5286 | 84.5573 | 38.3723 | 1881.3579 | 1772.984 | 2750.5042 | 556.7182 | 1651.1983 | 4711.4836 | 5615.7985 | 5596.1426 | 6228.7502 | 974.2693 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 ¦ 2026 | 831.448 | 41.6286 | 1105.1901 | 2198.5351 | 1933.4227 | 3690.3825 | 0% | NA ¦ NA | 2.1 | NA | 45.85% | 54.15%
6 | IID, SRP, APS SDGE SHARE ON CAP |  |  | Multiple | Capital upgrades between Arizona Public Services, Salt River Project and IID | Substation - Other Equipment | Upgrade/Retrofit | NA | NA | Work Requested by Others | Substation Reliability | NA | NA | 2026-01-20 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | NA | NA | 4.1 | NA | QB00012 | 1 | 103 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2021-12-28 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2022-12-28 | 2022-12-31 | 2022-12-31 | NA | NA | FALSE | 3866.5808 | NA ¦ NA | 11622.4106 | 0 | 12271.1182 | -586.1013 | 39.5816 | -102.1879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 0 | 12271.1182 | -586.1013 | 39.5816 | -102.1879 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] Exempt
7 | KYOCERA BK 30 REPLACEMENT |  |  | San Diego, San Diego | Replace Bk30 at Kyocera Substation | Substation - Transformer | Replace | Upgrade/Retrofit | NA | Reliability | Substation Reliability | NA | NA | 2026-05-13 | 7 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 0.17 | 69 | 69kV | 4.1 | 2019-1024 | QB00012 | 1 | 103 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-09-25 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2023-06-12 | 2020-12-31 | 2025-04-25 | Construction Delays | NA | TRUE | 1614.462 | NA ¦ NA | 2385.6103 | 188.5972 | 184.1777 | 958.5305 | 331.427 | 158.0336 | 1.0269 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2023 ¦ 2024 ¦ 2025 ¦ 2026 | 0 | 0 | 1895.1228 | 331.427 | 158.0336 | 1.0269 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
8 | MIGUEL BK80 12KV TERTIARY BREAK |  |  | San Diego County | Replace (3) 12kv Tertiary breakers; install two SEL487 relay panels | Substation - Circuit Breaker | Replace | Upgrade/Retrofit | NA | Reliability | Substation Reliability | NA | NA | 2026-05-19 | 24; 24; 24 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 12.37 | 12 | 230kV¦69kV¦12kV | 4.1 | 2019-1018 | QB00012 | 1 | 103 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-02-08 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2020-05-04 | 2019-12-31 | 2024-06-30 | Material | NA | FALSE | 2515.493 | NA ¦ NA | 3925.5907 | 336.7671 | 229.9036 | 1335.5361 | 305.771 | -25.2867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2023 ¦ 2024 ¦ 2025 | 0 | 0 | 1012.1408 | 2938.7366 | -25.2867 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
9 | SAN ONOFRE RTV COATING |  |  | San Diego, San Diego | Remove existing Insulgrease on all 230kV insulators and bushings at San Onofre Substation. Apply RTV silicone (room-temperature vulcanizing silicone) coating to all 230kV insulators and bushings. | Substation - Multiple | New | New | NA | Safety | 3rd Party Damage | NERC CIP Compliance | NERC CIP Compliance | 2026-05-27 | NA | NA | NA | NA | Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 5.14 | 230 | 230kV | 4.1 | NA | QB00012 | 1 | 103 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-10-10 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | CPUC | Dept of Navy | Exempt | NA | NA [See Notes] | NA | Construction (50%-75%) | NA | 2024-10-10 | 2025-07-01 | 2026-06-30 | Outage | NA | TRUE | 1244.8453 | NA ¦ NA | 2437.4574 | 0 | 0 | 0 | 566.3842 | 1462.6336 | 181.2035 | 227.2361 | 0 | 0 | 0 | 0 | 2210.2213 | NA | NA | 2026 | 0 | 0 | 0 | 0 | 0 | 2437.4574 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0% | [CPUC Status] Exempt
10 | IID, SRP, APS SDGE SHARE ON CAP |  |  | Multiple | Capital upgrades between Arizona Public Services, Salt River Project and IID | Substation - Other Equipment | Upgrade/Retrofit | NA | NA | Work Requested by Others | Substation Reliability | NA | NA | 2025-04-26 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | NA | NA | 4.1 | NA | QB00012 | 1 | 103 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2021-12-28 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2020-04-03 | 2020-12-31 | NA | NA | NA | FALSE | 1115.598 | NA ¦ NA | 2577.7894 | 1037.2104 | 1.0071 | 0 | 0 | -0.05021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2025 | 1037.2104 | 1.0071 | 0 | 0 | -0.05021 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] Exempt
11 | [Programmatic] Renewal of Electric Transmission Line Easements |  |  | Multiple | The purpose of this parent work order is to renew various easements and/or permits for transmission rights of way that will expire within the next 5 years. These easements will allow SDGE to install and maintain electric transmission facilities across public and private lands. These transmission lines are an integral part of our electric transmission system. | Transmission Line - Right of Way | NA | NA | NA | Other [See Notes] | System Operations | NA | NA | NA | NA | NA | NA | NA | Tier 1 ¦ Tier 2 ¦ Tier 3 | FALSE ¦ FALSE ¦ FALSE | FALSE | Individual Project/Easement Review Required |  | NA | NA | Multiple | NA | NA | Multiple | QB00008 | 5 | 104 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-12-11 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | TBD | TBD | NA | NA | To be Filed | NA | Operational | NA | NA | NA | NA | NA | NA | TRUE | NA | NA ¦ NA | 89905.4896 | 30.7355 | 71.7872 | 16.0811 | 78.1974 | -2.3387 | 3080.9488 | 1331.6485 | 780.9837 | 787.1492 | 994.7695 | 946.8574 | 3075.6791 | NA | NA | 2021 ¦ 2024 ¦ 2025 ¦ 2026 | 30.8162 | 0 | 0 | 171.2547 | -2.3387 | 4412.5974 | 0% | NA ¦ NA | 12.6 | NA | 45.85% | 54.15% | [Primary Purpose] Easement review
12 | TL 682 LA JOLLA ET EASEMENT |  |  | San Diego County | Renewal of TL682 Transmission Easement | Transmission Line - Right of Way | NA | NA | NA | Other [See Notes] | Safety - Line Right of Way Access | NA | NA | 2026-01-22 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69 | NA | NA | NA | QB00008 | 1 | 104 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2022-06-27 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | NA | EA | NA | BIA | Exempt | NA | NA [See Notes] | NA | Operational | NA | NA | NA | 2024-08-30 | NA | NA | TRUE | 674.9614 | NA ¦ NA | 2043.7314 | 0 | 440.5826 | 709.3057 | 530.0569 | 331.8554 | 31.9309 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2024 ¦ 2025 ¦ 2026 | 0 | 0 | 0 | 1679.9451 | 331.8554 | 31.9309 | 0% | NA ¦ NA | 1.3 | NA | 0% | 100% | [Primary Purpose] Easement review [CPUC Status] Exempt
13 | SR 224136, 472545 BOUNDARY ST |  |  | San Diego, San Diego | Condemnation costs for project known as SRs 224136, 472545 to acquire land rights for SDGE for Electric Transmission facilities on Boundary Street. | Transmission Line - Right of Way | NA | NA | NA | Other [See Notes] | System Operations | NA | NA | 2026-02-19 | NA | NA | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | 0 | NA |  | 0.44 | NA | 69 | NA | NA | 2316418 | QB00008 | 1 | 104 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2025-07-25 | Work Order Authorization | 2025 | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | NA | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | NA | NA | 2025-06-02 | NA | NA | FALSE | 1504.6557 | NA ¦ NA | 1444.9348 | 0 | 0 | 0 | 0 | 1444.9348 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2025 | 0 | 0 | 0 | 0 | 1444.9348 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [Primary Purpose] Easement review [CPUC Status] Exempt
14 | [Programmatic] Electric Transmission Tools & Equipment |  |  | NA | Purchase tools and test equipment to support the safe and reliable operations of substation and transmission equipment. | Substation - Multiple | New | Replace | NA | Reliability | Substation Reliability | NA | NA | NA | NA | NA | NA | NA | Tier 1 ¦ Tier 2 ¦ Tier 3 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | NA | NA | 1.3 | Multiple | QB00145 | 0 | 106 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-11-22 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Operational | NA | NA | NA | NA | NA | NA | TRUE | NA | NA ¦ NA | 2823.7342 | 86.2931 | 83.1998 | 93.5771 | 76.5512 | 85.7769 | 33.8539 | 104.8787 | 185.1911 | 163.8881 | 180.472 | 197.7732 | 33.8539 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 ¦ 2026 | 86.2931 | 83.1998 | 93.5771 | 76.5512 | 85.7769 | 126.7315 | 0% | NA ¦ NA | 2.2 | NA | 0% | 0% | [CPUC Status] Exempt
15 | [Programmatic] Transmission Substation Proactive Asset Program |  |  | Multiple | The Substation Equipment Assessment Team will develop alternatives to replace or remove obsolete and problematic equipment. A condition assessment process and evaluation criteria have been created using probability and risk analysis, financial impacts and present value analysis to justify projects. Equipment that is truly obsolete such as equipment that cannot be maintained (no spare parts available), or which poses a safety risk will be replaced. Each year the average age of all substation equipment increases, with the oldest transformer currently 60+ years old. The ranking of substation equipment is an ongoing process and involves identifying equipment that presents a significant risk to the system. Based on the cost availability of raw materials and global demand, the lead times for major substation equipment have increased to 6 months for breakers and at least 1.5 years for transformers. | Substation - Multiple | Replace | Upgrade/Retrofit | NA | Reliability | Substation Reliability | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | Individual project review required |  | NA | NA | Multiple | NA | 4.1 | Multiple | QBL0003 | 231 | 1145 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-12-11 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | NA | NA | NA | TBD | NA | NA | To be Filed | NA | Operational | NA | NA | NA | NA | NA | NA | TRUE | NA | NA ¦ NA | 152589.893 | 1688.6904 | 3382.9658 | 2502.1587 | 2663.9716 | 1847.0916 | 281.5641 | 2315.9708 | 6048.3169 | 8897.4081 | 9931.6808 | 11067.1884 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 ¦ 2026 | 1392.5616 | 3433.4672 | 3053.8049 | 3257.6319 | 3058.4474 | 2038.0321 | 0% | NA ¦ NA | 3.7 | NA | 45.85% | 54.15%
16 | MELROSE CB REPLACEMENT |  |  | Vista, San Diego | Replace Bank 31 Circuit breaker do to having known issues of failures. CB 9. | Substation - Multiple | New | Upgrade/Retrofit | NA | Reliability | Substation Reliability | NA | NA | 2026-05-19 | NA | NA | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | 0 | NA |  | NA | 1.13 | 69 | 69¦12kV | 4.1 | 2023-3407 | QBL0003 | 1 | 1145 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-11-22 | Work Order Authorization | 2024 | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | NA | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2025-09-22 | 2024-02-06 | 2025-10-22 | Material | NA | TRUE | 460.9882 | NA ¦ NA | 1053.4263 | 0 | 0 | 0 | 16.4839 | 1009.1939 | 12.3089 | 15.4396 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2026 | 0 | 0 | 0 | 0 | 0 | 1053.4263 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
17 | SAN ONOFRE 230KV DISCONNECT REP |  |  | Camp Pendleton | disconnects are rated as POOR, indicating widespread serious deterioration and nearing end of life. The existing disconnects have been identified as having multiple critical issues that compromise both reliability and safety. These include: Severely corroded hand-operated/gang-operated (HOGO) mechanisms Worn output shaft connections, for which no spare parts are available Damaged or completely severed ground tails | Substation - Multiple | New | Upgrade/Retrofit | NA | Reliability | Substation Reliability | NA | NA | 2026-05-27 | NA | NA | NA | NA | Tier 2 | FALSE ¦ FALSE ¦ FALSE | 0 | NA |  | NA | 5.14 | 230 | 230kV¦69kV | 4.1 | 2026-4802 | QBL0003 | 1 | 1145 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2025-12-17 | Work Order Authorization | 2025 | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | CPUC | Dept. of Navy - Discretionary action not anticipated | Exempt | NA | NA [See Notes] | NA | Engineering less than 50% complete | NA | 2027-10-11 | 2028-05-31 | 2028-05-31 | NA | NA | FALSE | 3699.9955 | NA ¦ NA | 3244.7379 | 0 | 0 | 0 | 0 | 0.92116 | 9.6331 | 468.8377 | 1596.9903 | 1168.3556 | 0 | 0 | 10.5543 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0% | [CPUC Status] Exempt
18 | STUART PHASE 2 PT DISCONNECT |  |  | Camp Pendleton | Phase 2 Stuart substation (TL680C 69kV Disconnect, 2" Bus Tap, Jumpers) Scope: 1. Demolition A-Frame (aka termination tower) 2. Install new 69kV Disconnects (gang-operated) 3. Install new 69kV Fuse Disconnects (3) 4. Retrofit H-Frame (PT Steel Structure) 5. Reconductor TL690E to extend H-Frame, from Z228028. (On TED's budget) 6. New 12kV H-Frame structure w/ insulator to support secondary conductor between BK30 and the main bus. (will need CPUC cost) 6.1: Second Option: if CPUC budget is insufficient, then reuse existing A-Frame to support secondary. 7. Optional: Demolition the remaining (2) north piers of the A-Frame. | Substation - Multiple | New | Upgrade/Retrofit | NA | Reliability | Substation Reliability | NA | NA | 2026-04-13 | NA | NA | NA | NA | Camp Pendleton | FALSE ¦ FALSE ¦ FALSE | 0 | NA |  | NA | 0.12 | 69 | 69¦12kV | 4.1 | 2026-4797 | QBL0003 | 1 | 1145 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2025-07-25 | Work Order Authorization | 2025 | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | CPUC | Dept. of Navy - Discretionary action not anticipated | Exempt | NA | NA [See Notes] | NA | Engineering less than 50% complete | NA | 2027-05-26 | 2027-11-04 | 2027-11-04 | NA | NA | FALSE | 1051.8412 | NA ¦ NA | 1118.6279 | 0 | 0 | 0 | 0 | 15.7552 | 32.3649 | 404.5395 | 665.9683 | 0 | 0 | 0 | 48.1201 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
19 | TRABUCO 138KV DISCONNECT RPLMT |  |  | Laguna Niguel, Orange County | The replacement and installation of 138K disconnects at Trabuco substation. | Substation - Multiple | New | Upgrade/Retrofit | NA | Reliability | Substation Reliability | NA | NA | 2026-04-20 | NA | NA | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | 0 | NA |  | NA | 1.92 | 138 | 138¦12kV | 4.1 | 2025-4461 | QBL0003 | 1 | 1145 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2025-05-08 | Work Order Authorization | 2025 | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | Other [See Notes] | CPUC | Dept. of Navy - Discretionary action not anticipated | Exempt | NA | NA [See Notes] | NA | Engineering less than 50% complete | NA | 2027-01-22 | 2027-01-14 | 2027-03-25 | NA | NA | FALSE | 1333.7632 | NA ¦ NA | 1350.3711 | 0 | 0 | 0 | 0 | 36.059 | 21.9789 | 1251.3342 | 40.999 | 0 | 0 | 0 | 58.0379 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
20 | GENESEE 69KV BREAKER RPLT |  |  | San Diego, San Diego | Design & Installation of two (2) new 69kV circuit breakers (CB 8 & CB9) at Genesee substation. Includes new control cable and UG infrastructure as needed. Project initiated by Kearny to mitigate aging equipment failure risks. | Substation - Multiple | New | Upgrade/Retrofit | NA | Reliability | Substation Reliability | NA | NA | 2026-05-07 | NA | NA | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | 0 | NA |  | NA | 0.92 | 69 | 69¦12kV | 4.1 | 2025-4255 | QBL0003 | 1 | 1145 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-12-12 | Work Order Authorization | 2025 | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | CPUC | NA | NA | NA | To be Filed | NA | Engineering more than 50% complete | NA | 2027-01-25 | 2027-05-14 | 2027-05-14 | NA | NA | FALSE | 1225.8816 | NA ¦ NA | 1456.629 | 0 | 0 | 0 | 0 | 71.4887 | 26.9087 | 1341.2546 | 16.9769 | 0 | 0 | 0 | 98.3975 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
21 | CABRILLO 69KV CB AND DISC RPL |  |  | San Diego, San Diego | Replace TL615 and TL659 69KV CB's. Possible CB pad replacement. | Substation - Multiple | New | Upgrade/Retrofit | NA | Reliability | Substation Reliability | NA | NA | 2026-05-21 | NA | NA | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | 0 | NA |  | NA | 0.45 | 69 | 69¦12kV | 4.1 | 2024-3994 | QBL0003 | 1 | 1145 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-12-28 | Work Order Authorization | 2024 | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | Other [See Notes] | CPUC | Dept. of Navy - Discretionary action not anticipated | Exempt | NA | NA [See Notes] | NA | Engineering more than 50% complete | NA | 2026-11-10 | 2027-01-29 | 2027-02-26 | NA | NA | TRUE | 1144.93 | NA ¦ NA | 2643.6746 | 0 | 0 | 0 | 50.8671 | 406.6158 | 375.5265 | 1810.6652 | 0 | 0 | 0 | 0 | 833.0094 | NA | NA | 2026 | 0 | 0 | 0 | 0 | 0 | 2643.6746 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
22 | EL CAJON ROCKET LAUNCHER BRKRS |  |  | El Cajon, San Diego | The replacement and installation of rocket launcher breakers at El Cajon substation. | Substation - Multiple | New | Upgrade/Retrofit | NA | Reliability | Substation Reliability | NA | NA | 2026-05-05 | NA | NA | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | 0 | NA |  | NA | 1.1 | 69 | 69¦12kV | 4.1 | 2025-4706 | QBL0003 | 1 | 1145 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2025-05-09 | Work Order Authorization | 2025 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Engineering more than 50% complete | NA | 2028-02-10 | 2028-05-18 | 2028-05-18 | NA | NA | FALSE | 2751.8153 | NA ¦ NA | 2136.8337 | 0 | 0 | 0 | 0 | 1.7665 | 35.0057 | 178.3168 | 927.0737 | 994.671 | 0 | 0 | 36.7721 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
23 | MIGUEL FIRE PROTECTION SYS REPR |  |  | San Diego County | Repair of Fire protection system at Miguel | Other - Civil | Upgrade/Retrofit | Upgrade/Retrofit | NA | Safety | Fire Protection | NA | NA | 2026-05-19 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 2.9 | 69 ¦500 | NA | 4.1 | NA | QBL0003 | 1 | 1145 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-10-01 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2019-10-03 | 2020-12-31 | 2021-05-18 | NA | NA | FALSE | 69.27 | NA ¦ NA | 1744.9102 | 759.4003 | 0 | 0 | 0 | -1.4106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2025 | 1746.3209 | 0 | 0 | 0 | -1.4106 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 45.85% | 54.15% | [CPUC Status] Exempt
24 | GLENCLIFF SUB ADD 69KV BREAKER |  |  | San Diego, San Diego | Install 69kv Bank Breaker and SCADA | Substation - Circuit Breaker | New | New | NA | Reliability | Substation Reliability | NA | NA | 2026-05-14 | 7 | NA | NA | NA | Tier 3 | FALSE ¦ FALSE ¦ FALSE | FALSE | A portion of the substation is owned by CNF and a portion is outisde federal lands |  | NA | 0.15 | 69 | 69kV | 4.1 | 2014-01091-ZZ | QBL0003 | 1 | 1145 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2016-07-13 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | CPUC | CNF - TBD | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2020-07-27 | 2019-03-01 | 2020-11-04 | Construction Delays | NA | FALSE | 1165.524 | NA ¦ NA | 2626.7612 | 519.8004 | 120.9231 | 7.8802 | 5.5689 | -3.6322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 105.8718 | 2424.1996 | 7.8802 | 5.5689 | -3.6322 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
25 | MERCHANT REPLACE 3 230KV BRKR |  |  | NA | Replace (3) Oil circuit breakers due to leaking hydraulic fluid | Substation - Circuit Breaker | Replace | Upgrade/Retrofit | NA | Safety | Substation Reliability | NA | NA | 2026-05-27 | 28; 28; 28 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 72.12 | 230 | NA | 4.1 | 2020-1020 | QBL0003 | 1 | 1145 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-06-07 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2022-03-31 | 2020-11-30 | 2025-06-20 | Project Design | NA | TRUE | 95.52 | NA ¦ NA | 8536.1934 | 750.5718 | 1271.3793 | 2355.3583 | 1372.2536 | 2224.6619 | 2.3608 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2025 ¦ 2026 | 0 | 0 | 0 | 0 | 8533.8325 | 2.3608 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0% | [CPUC Status] Exempt
26 | PENAQUITOS SUBST 230KV DISCON R |  |  | San Diego, San Diego | Replace (8) 230kv disconnect switches, (8) 230kv disconnect stands, and upgrade the associated concrete pads | Substation - Switch | Replace | Upgrade/Retrofit | NA | Reliability | Substation Reliability | NA | NA | 2026-05-10 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 13.94 | 230 | 230kV | 4.1 | 2019-1022 | QBL0003 | 1 | 1145 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-06-20 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2020-04-13 | 2020-07-06 | 2021-07-27 | Weather | NA | FALSE | 2270.915 | NA ¦ NA | 2591.4673 | 1102.6513 | 3.3797 | 0 | 0 | -6.0159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2025 | 2594.1036 | 3.3797 | 0 | 0 | -6.0159 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0% | [CPUC Status] Exempt
27 | SCRIPPS SUBST RPL 69KV BUS DISC |  |  | San Diego, San Diego | Replace 69KV bus disconnects for BK 30,31 & 32, existing disconnects are breaking down and limited spare parts since these were manuf.; use (3) spare EVB ( 69kv,1200A) switches from Caspian for this work | Substation - Bus Arrangement | Replace | Replace | NA | Reliability | Age/Condition | NA | NA | 2026-05-06 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 1.1 | 69 | 69kV | 4.1 | 2020-1038 | QBL0003 | 1 | 1145 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-07-24 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2022-01-10 | 2020-12-31 | 2023-04-14 | NA | NA | FALSE | 189.161 | NA ¦ NA | 1779.7214 | 323.5922 | 1079.982 | 376.5437 | 0.07194 | -3.7721 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2023 ¦ 2024 ¦ 2025 | 0 | 0 | 1783.4216 | 0.07194 | -3.7721 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
28 | MURRAY RPL RELAY ON TL 618,619, |  |  | San Diego, San Diego | Remove existing control shelter and panels, RTU & CBM cabinets, AC/DC panels; install new control shelter and panels, new CBM & Telecom cabinets, new AC/DC panels. | Substation - Multiple | Removal | New | NA | Reliability | Age/Condition - Replace Other Substation Equipment | NA | NA | 2026-05-08 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 9 | 69 | 69kV | 4.1 | 2014-00247-ZZ | QBL0003 | 1 | 1145 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2017-04-24 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2017-07-25 | 2019-12-31 | 2021-06-09 | Project Design | NA | FALSE | 2832.691 | NA ¦ NA | 3512.7704 | 191.4279 | 0 | 0 | 0 | -19.9885 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2025 | 3532.7589 | 0 | 0 | 0 | -19.9885 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
29 | IMPERIAL VALLEY MAST RPL |  |  | Imperial County | Replacement of Static Mast structures at Imperial Valley | Substation - Structure | Replace | Replace | NA | Reliability | Age/Condition | NA | NA | 2026-06-01 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 55.48 | 500 | 500kV | 4.1 | 2020-1025 | QBL0003 | 1 | 1145 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-04-29 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2021-01-25 | 2019-12-31 | 2024-01-17 | NA | NA | FALSE | 558.815 | NA ¦ NA | 1273.4269 | 225.8838 | 220.1826 | 281.4983 | 31.0638 | -8.2193 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2024 ¦ 2025 | 0 | 0 | 0 | 1281.6462 | -8.2193 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0% | [CPUC Status] Exempt
30 | PENASQUITOS AGING INFRS. 138K B |  |  | San Diego, San Diego | Replace (5)138kV Breakers | Substation - Circuit Breaker | Replace | Upgrade/Retrofit | NA | Reliability | Age/Condition - Replace Breakers | NA | NA | 2026-05-10 | 62; 59; 46; 46 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 13.94 | 138 | 138kV | 4.1 | 2021-2457 | QBL0003 | 1 | 1145 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-05-08 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Planning | NA | 2027-07-23 | 2020-12-31 | 2027-12-29 | Scope Change | Scope Change | TRUE | 1313.224 | NA ¦ NA | 7202.9998 | 48.2835 | 509.533 | 469.8479 | 479.3168 | 43.6618 | 0 | 778.7489 | 3681.0486 | 747.2601 | 0 | 0 | 1550.6429 | NA | NA | 2026 | 0 | 0 | 0 | 0 | 0 | 2774.691 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
31 | SAN YSIDRO AGING INFRAS. 69KV B |  |  | San Diego, San Diego | Replace (3) 69kV circuit breakers at San Ysidro | Substation - Circuit Breaker | Replace | Upgrade/Retrofit | NA | Reliability | Age/Condition - Replace Breakers | NA | NA | 2026-04-07 | 53; 53; 33 | NA | NA | NA | Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 1.57 | 69 | 69kV¦12kV | 4.1 | 2020-1030 | QBL0003 | 1 | 1145 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-05-09 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2021-08-02 | 2020-12-31 | 2023-03-14 | Construction Delays | NA | FALSE | 741.287 | NA ¦ NA | 2150.4546 | 475.4767 | 349.219 | 804.8363 | 122.8656 | -5.7765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2023 ¦ 2024 ¦ 2025 | 0 | 0 | 2033.3655 | 122.8656 | -5.7765 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
32 | TORREY PINES TL662 REPLACEMENT |  |  | San Diego, San Diego | Replace 69kV CB4 and CB5 with new gas breakers Install (2) new 4 inch conduits for each breaker part of replacement Install new cables for each breaker part of replacement Install new zipper box for each breaker part of replacement Repair/install new ground leads for each breaker part of replacement Install (2) new 4 inch conduits to spare breaker pad | Substation - Circuit Breaker | Replace | Upgrade/Retrofit | NA | Reliability | Age/Condition - Replace Breakers | NA | NA | 2026-05-04 | 33; 33 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | TBD |  | NA | 0.79 | 69 | 12kV¦69kV | 4.1 | 2024-4121 | QBL0003 | 1 | 1145 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-10-10 | Work Order Authorization | 2024 | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | CPUC | NA | NA | NA | To be Filed | NA | Construction (50%-75%) | NA | 2024-07-15 | 2025-01-31 | 2026-12-18 | NA | Construction Delays | TRUE | 767.5924 | NA ¦ NA | 5252.4741 | 0 | 0 | 6.1175 | 1586.4526 | 2769.0476 | 418.1224 | 472.7339 | 0 | 0 | 0 | 0 | 4779.7401 | NA | NA | 2026 | 0 | 0 | 0 | 0 | 0 | 5252.4741 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
33 | FELECITAS AGING INFRAS. 69KV BR |  |  | Escondido, San Diego | The purpose of this project is to upgrade the reliability of Felicita Substation by replacing equipment exceeding 47 years in service, adding a new high side bank circuit breaker, and upgrading the line, bank, and bus relay protection associated with the circuit breakers being installed. | Substation - Circuit Breaker | Upgrade/Retrofit | Upgrade/Retrofit | NA | Reliability | Age/Condition | NA | NA | 2026-04-03 | 53; 50; 41 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | TBD |  | NA | 1.51 | 69 | 69KV | 4.1 | 2019-1021 | QBL0003 | 1 | 1145 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-05-08 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Construction (25%-50%) | NA | 2025-04-01 | 2020-12-31 | 2026-11-27 | Project Design | Outage | TRUE | 741.287 | NA ¦ NA | 5731.9313 | 36.1215 | 149.7262 | 428.3646 | 1300.2126 | 1256.4956 | 335.3959 | 1974.6988 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2024 ¦ 2025 ¦ 2026 | 0 | 0 | 0 | 2165.341 | 1256.4956 | 2310.0947 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
34 | [Programmatic] Automated Fault Location (TEAM) |  |  | Multiple | This project provides funds for installation, upgrade, and expansion of SDG&Es Event Reporting Software and hardware to include Automated Fault Locator. This new system known as TEAM will provide accurate fault location within seconds by measuring the parameters at both ends of the line (multiple ends on multi-terminal lines) and time synchronizing the events with GPS clock. | Substation - Multiple | Upgrade/Retrofit | NA | NA | Reliability | Automation | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | Multiple | 373MVA | 4.3 | Multiple | QBL0063 | 3 | 12129 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2022-10-05 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | NA | NA | NA | NA | NA | FALSE | NA | NA ¦ NA | 815.4341 | 422.6652 | 81.1314 | 7.0931 | 0 | -0.42823 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2022 ¦ 2023 ¦ 2025 | 0 | 502.8661 | 43.1545 | 0 | -0.42823 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
35 | AFL VARIOUS SUB |  |  | San Diego, San Diego | Automated Fault Location (TEAM) deployments at multiple substations. | Substation - Other Equipment | Upgrade/Retrofit | NA | NA | Reliability | Relay Upgrades | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69 ¦ 138 | 373MVA | 4.3 | NA | QBL0063 | 1 | 12129 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-04-15 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | NA | 2019-12-31 | 2021-01-30 | Prioritization | NA | FALSE | 161.18 | NA ¦ NA | 1032.2622 | 128.1801 | 0 | 0 | 0 | -2.5099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2025 | 1034.7721 | 0 | 0 | 0 | -2.5099 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
36 | [Programmatic] Substation SCADA Expansion |  |  | Multiple | The project provides funding for the installation, upgrades, and expansion of the Supervisory Control and Data Acquisition (SCADA) system at transmission substations. Additionally, this project improves the protection of SDG&E’s transmission system to provide fast isolation for faults and system disturbances. Includes upgrading relays including increased security, differential protection, and traveling wave fault finding technology to reduce restoration times. | Substation - Multiple | Upgrade/Retrofit | NA | NA | Reliability | Install SCADA/RTU | NERC PRC Compliance | NA | NA | NA | NA | NA | NA | Multiple | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69 | 373MVA | 4.3 | Multiple | QBL0064 | 28 | 12132 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-12-09 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | NA | NA | NA | NA | NA | TRUE | NA | NA ¦ NA | 75458.9569 | 1288.3639 | 1051.704 | 1039.6047 | 1425.0556 | 1009.7748 | 148.8639 | 4510.9817 | 4092.892 | 4565.7379 | 5084.812 | 5654.4722 | 499.4683 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 ¦ 2026 | 2000.6913 | 385.5493 | 2088.1635 | 13.9579 | 975.5364 | 2577.3215 | 0% | NA ¦ NA | 4.42 | NA | 0% | 100% | [CPUC Status] Exempt
37 | T SCADA: TRABUCO RTU |  |  | Laguna Niguel, Orange | Trabuco substation Transmission RTU upgrades | Substation - Protection Relay | Upgrade/Retrofit | NA | NA | Reliability | Relay Upgrades | NA | NA | 2026-04-20 | 4.7 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 1.92 | 69 | 373MVA | 4.3 | 2023-3393 | QBL0064 | 1 | 12132 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2022-09-01 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | NA | NA | cpuc | NA | Exempt | NA | NA [See Notes] | NA | Engineering more than 50% complete | NA | 2026-09-08 | 2023-12-30 | 2027-02-17 | Prioritization | NA | TRUE | 363.9492 | NA ¦ NA | 1470.1325 | 0 | 15.1845 | 245.1148 | 597.3973 | 164.1824 | 84.3484 | 363.9051 | 0 | 0 | 0 | 0 | 1106.2273 | NA | NA | 2026 | 0 | 0 | 0 | 0 | 0 | 1470.1325 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
38 | RANCHO CARMEL T SCADA |  |  | San Diego, San Diego | Rancho Carmel substation Transmission SCADA upgrades. | Substation - Protection Relay | New | NA | NA | Reliability | Relay Upgrades | NA | NA | 2026-04-14 | 6.52 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 1.35 | 69 | 373MVA | 4.3 | 2023-3392 | QBL0064 | 1 | 12132 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2021-09-15 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Construction (under 10%) | NA | 2025-04-30 | 2023-12-31 | 2026-06-10 | Prioritization | NA | TRUE | 298.1449 | NA ¦ NA | 1535.1334 | 0.58867 | 4.3537 | 179.4357 | 700.8313 | 106.9752 | 29.9307 | 513.0181 | 0 | 0 | 0 | 0 | 1022.1153 | NA | NA | 2026 | 0 | 0 | 0 | 0 | 0 | 1535.1334 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
39 | IV 230KV RTU REPLACEMENT |  |  | Imperial County | Install two new RTU panels, remove two SEL PDC's, Remove the RS416, Install 7 SEL 3610's. | Substation - Multiple | New | New | NA | CAISO Transmission Planning Standards [See Notes for NERC Compliance and contingency code, WECC Requirement (and the specific requirement)] | Replace Other Substation Equipment | NERC CIP Compliance | NERC CIP Compliance | 2026-06-01 | NA | NA | NA | NA | Tier 3 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 55.48 | Multiple | 230kV | 4.3 | 2025-4183 | QBL0064 | 1 | 12132 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-07-19 | Work Order Authorization | 2025 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | IS/ND | EIS | NA | NA | Exempt | NA | NA [See Notes] | NA | Planning | NA | 2026-05-19 | 2025-12-31 | 2027-03-05 | Project Design | Prioritization | FALSE | 342.0158 | NA ¦ NA | 1183.8109 | 0 | 0 | 0 | 1.6358 | 395.1335 | 503.4605 | 254.4095 | 29.1716 | 0 | 0 | 0 | 900.2298 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 45.85% | 54.15% | [Primary Purpose] This project supports future interconnection requests since the RTU lacks available points. Forecasts and Cluster 14–15 agreements identified the need to upgrade it for transmission-level growth [CPUC Status] Exempt
40 | [Programmatic] Aerial Marking for Safety |  |  | Multiple | This project will add aerial marker balls and /or lighting at locations identified by Transmission Engineering, Transmission maintenance personnel, or AL&M support team as safety concerns or necessary for FAA compliance. These locations fall under SDG&E’s expanded aerial lighting and marking policy that seeks to reduce the risk of collisions and improve safety. This will be an ongoing project as Transmission Construction & Maintenance may provide additional locations with safety concerns and for the Aerial Lighting and Marking company initiative. The work includes analyzing current structures for strength and clearance to add marking, replacing structures as necessary, and installing aerial marking and/or lighting. | Transmission Line - Multiple | NA | NA | NA | Safety | T-Line Reliability | NA | NA | NA | NA | NA | NA | NA | Tier 1 ¦Tier 2 ¦ Tier 3 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | Multiple | NA | 1.1 | Multiple | QBL0065 | 78 | 12159 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2022-12-09 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | NA | NA | NA | NA | NA | FALSE | NA | NA ¦ NA | 25180.6198 | 337.9964 | 69.5109 | 9.3215 | 0.00105 | -7.5326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 1408.1155 | 75.2202 | 9.3215 | 0.00105 | -7.5326 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 45.85% | 54.15% | [CPUC Status] Exempt
41 | AL&M system wide assessment |  |  | San Diego, San Diego | Aerial Lighting and Marking Project to meet FAA Regulations | Transmission Line - Pole/Tower | New | NA | NA | Safety | T-Line Reliability | NA | NA | NA | NA | NA | NA | NA | Tier 1 ¦Tier 2 ¦ Tier 3 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | NA | NA | 1.1 | ALM-SW | QBL0065 | 1 | 12159 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2012-12-12 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | NA | 2019-12-31 | Multiple | NA | NA | FALSE | 846.516 | NA ¦ NA | 4343.4753 | 361.1757 | 50.3264 | 4.0735 | 0.00168 | -13.3925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 4302.4662 | 50.3264 | 4.0735 | 0.00168 | -13.3925 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] Exempt
42 | [Programmatic] CAST Security Upgrades |  |  | Multiple | CAST is an ongoing program that addresses security for critical substation assets. | Substation - Other Equipment | New | NA | NA | Location, Environmental Conditions | Security Upgrades | NERC CIP Compliance | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | Individual Project/Easement Review Required |  | NA | NA | NA | Multiple | 1.1 | Multiple | QBL0020 | 35 | 15125 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-12-09 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | CPUC | TBD | Exempt | NA | NA [See Notes] | NA | Operational | NA | Multiple | Multiple | Multiple | NA | NA | FALSE | 216954.9592 | NA ¦ NA | 65470.3307 | 333.5327 | 312.9607 | -1002.0375 | 54.0073 | -46.5507 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 94.0047 | 39.8652 | -489.414 | 54.0073 | -46.5507 | 0 | 0% | NA ¦ NA | 1.6 | NA | 100% | 0% | [CPUC Status] Exempt
43 | CAST PENASQUITOS (PQ) |  |  | San Diego, San Diego | Physical security hardening at Penasquitos substation | Other - Physical Security | New | NA | NA | Physical Security | Security Upgrades | NERC CIP Compliance | NA | 2026-05-10 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 13.94 | 230 ¦ 500 | NA | 1.1 | 2023-3286 | QBL0020 | 1 | 15125 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2022-07-27 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2023-05-30 | 2024-12-31 | 2024-08-14 | NA | NA | FALSE | 369.2342 | NA ¦ NA | 18960.4876 | 0 | 1667.5722 | 9071.5199 | 8242.4071 | -21.0117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2024 ¦ 2025 | 0 | 0 | 0 | 18981.4993 | -21.0117 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0% | [CPUC Status] Exempt
44 | CAST EAST CO SUB PERIMETER |  |  | San Diego, San Diego | Physical security hardening at East County substation | Other - Physical Security | New | NA | NA | Physical Security | Security Upgrades | NERC CIP Compliance | NA | 2026-05-29 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 66.56 | 230 ¦ 500 | 230kV¦500kV | 1.1 | 2021-2561 | QBL0020 | 1 | 15125 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-12-28 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | Exempt | NA | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2021-08-20 | 2021-12-31 | 2022-11-22 | Prioritization | Multiple Options [See Notes] | FALSE | 409.5425 | NA ¦ NA | 31493.5957 | 13896.3193 | 17555.2216 | 80.7694 | 25.7432 | -64.4577 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 0 | 31451.5408 | 80.7694 | 25.7432 | -64.4577 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0% | [Reason for Change in In-Service Date] Construction Delays ¦ Scope Change [CPUC Status] Exempt
45 | CAST SYCAMORE CANYON |  |  | San Diego, San Diego | Physical security hardening at Sycamore Canyon substation | Other - Physical Security | New | NA | NA | Physical Security | Security Upgrades | NERC CIP Compliance | NA | 2026-05-06 | NA | NA | NA | NA | Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 10.79 | 230 ¦ 500 | 230kV¦500kV | 1.1 | 2023-3284 | QBL0020 | 1 | 15125 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2022-09-22 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | Exempt | NA | NA | CPUC | Dept of Navy - Miramar | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2023-09-15 | 2024-01-31 | 2024-07-01 | NA | NA | FALSE | 4261.2035 | NA ¦ NA | 14072.6317 | 0 | 864.9117 | 6654.1274 | 6562.1073 | -8.5148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2024 ¦ 2025 | 0 | 0 | 0 | 14081.1465 | -8.5148 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0% | [CPUC Status] Exempt
46 | CAST MISSION FRONT ENTRANCE |  |  | San Diego, San Diego | Physical security hardening at Mission substation | Other - Physical Security | New | NA | NA | Physical Security | Security Upgrades | NERC CIP Compliance | NA | 2026-05-28 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 9 | 230 ¦ 500 | 230kV¦500kV | 1.1 | 2022-2976 | QBL0020 | 1 | 15125 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-12-28 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | Exempt | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2022-08-22 | 2025-12-31 | 2024-08-26 | NA | NA | TRUE | 5847.1004 | NA ¦ NA | 25924.7396 | 772.6935 | 2301.7353 | 7337.3744 | 12821.5414 | 2670.0269 | 21.3681 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2024 ¦ 2025 ¦ 2026 | 0 | 0 | 0 | 23233.3446 | 2670.0269 | 21.3681 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0% | [CPUC Status] Exempt
47 | CAST GUARD SHELTER REBUILD |  |  | Multiple | Physical security hardening for guard shelter rebuild | Other - Physical Security | New | NA | NA | Physical Security | Security Upgrades | NERC CIP Compliance | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 230 ¦ 500 | 230kV¦500kV | 1.1 | 2023-3287 | QBL0020 | 1 | 15125 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2022-08-16 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | Exempt | NA | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2022-12-01 | 2023-12-31 | 2023-12-31 | NA | NA | FALSE | 8105.7854 | NA ¦ NA | 6630.6201 | 0 | -5.4329 | 5728.1337 | 950.2604 | -42.3411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2023 ¦ 2024 ¦ 2025 | 0 | 0 | 5722.7008 | 950.2604 | -42.3411 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0% | [CPUC Status] Exempt
48 | CAST OCOTILLO |  |  | Imperial County | Physical security hardening at Ocotillo substation | Other - Physical Security | New | NA | NA | Physical Security | Security Upgrades | NERC CIP Compliance | NA | 2026-05-30 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 28.98 | 230 ¦ 500 | 230kV¦500kV | 1.1 | 2022-2977 | QBL0020 | 1 | 15125 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2022-02-08 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | Exempt | NA | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2023-10-09 | 2023-12-31 | 2024-12-30 | Prioritization | Multiple Options [See Notes] | TRUE | 362.4209 | NA ¦ NA | 13815.1996 | 0 | 70.8717 | 5204.6986 | 8215.3314 | 313.963 | 10.3349 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2024 ¦ 2025 ¦ 2026 | 0 | 0 | 0 | 13490.9017 | 313.963 | 10.3349 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0% | [Reason for Change in In-Service Date] Construction Delays ¦ Scope Change [CPUC Status] Exempt
49 | CAST SUNCREST SUB PERIMETER |  |  | San Diego, San Diego | Physical security hardening at Suncrest substation | Other - Physical Security | New | NA | NA | Physical Security | Security Upgrades | NERC CIP Compliance | NA | 2026-05-16 | NA | NA | NA | NA | Tier 3 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 40.94 | 230 ¦ 500 | 230kV¦500kV | 1.1 | 2022-2929 | QBL0020 | 1 | 15125 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-12-20 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | Exempt | NA | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2022-05-31 | 2020-12-31 | 2023-09-18 | Prioritization | Multiple Options [See Notes] | FALSE | 371.3412 | NA ¦ NA | 29544.8445 | 5938.8692 | 11745.8702 | 7885.8844 | 3985.379 | -11.1583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2023 ¦ 2024 ¦ 2025 | 0 | 0 | 25570.6238 | 3985.379 | -11.1583 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0% | [Reason for Change in In-Service Date] Construction Delays ¦ Scope Change [CPUC Status] Exempt
50 | CAST TALEGA |  |  | San Clemente, San Diego | Physical security hardening at Talega substation | Other - Physical Security | Upgrade/Retrofit | NA | NA | Physical Security | Security Upgrades | NERC CIP Compliance | NA | 2026-05-26 | NA | NA | NA | NA | Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 6.2 | 230 ¦ 500 | 230kV¦500kV | 1.1 | 2024-3902 | QBL0020 | 1 | 15125 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-08-24 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | Exempt | Exempted | Categorical Exclusion | CPUC | Department of Navy | Exempt | NA | NA [See Notes] | NA | Construction (over 75%) | NA | 2025-02-04 | 2025-03-31 | 2026-06-29 | Scope Change | NA | TRUE | 17520.0262 | NA ¦ NA | 16414.4968 | 0 | 0 | 0.21244 | 3086.2953 | 13220.7811 | 107.208 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2026 | 0 | 0 | 0 | 0 | 0 | 16414.4968 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0% | [CPUC Status] Exempt
51 | CAST OTAY MESA |  |  | Otay Mesa, San Diego | Physical security hardening at Otay Mesa substation | Other - Physical Security | New | NA | NA | Physical Security | Security Upgrades | NERC CIP Compliance | NA | 2026-05-27 | NA | NA | NA | NA | Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 4 | 230 ¦ 500 | 230kV¦500kV | 1.1 | 2024-3903 | QBL0020 | 1 | 15125 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2022-02-08 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | Exempt | NA | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2024-07-30 | 2023-12-31 | 2024-12-24 | Prioritization | NA | FALSE | 362.4209 | NA ¦ NA | 2598.688 | 0 | 0 | 0.0713 | 2557.2477 | 41.369 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2024 ¦ 2025 | 0 | 0 | 0 | 2557.319 | 41.369 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0% | [CPUC Status] Exempt
52 | CAST SAN LUIS REY |  |  | Oceanside, San Diego | Physical security hardening at San Luis Rey substation | Other - Physical Security | Upgrade/Retrofit | NA | NA | Physical Security | Security Upgrades | NERC CIP Compliance | NA | 2026-05-13 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 7.4 | 230 ¦ 500 | 230kV¦500kV | 1.1 | 2024-3904 | QBL0020 | 1 | 15125 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-03-18 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | Exempt | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Construction (under 10%) | NA | 2025-06-30 | 2026-01-31 | 2026-07-31 | NA | NA | TRUE | 26711.4404 | NA ¦ NA | 8781.5831 | 0 | 0 | 0 | 62.5448 | 5335.8079 | 3364.5997 | 18.6308 | 0 | 0 | 0 | 0 | 8762.9523 | NA | NA | 2026 | 0 | 0 | 0 | 0 | 0 | 8781.5831 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0% | [CPUC Status] Exempt
53 | CAST SECURITY VARIOUS SUBS |  |  | Multiple | Physical security hardening at various substations | Other - Physical Security | New | NA | NA | Physical Security | Security Upgrades | NERC CIP Compliance | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | Individual Project/Easement Review Required |  | NA | NA | 230 ¦ 500 | 230kV¦500kV | 1.1 | NA | QBL0020 | 1 | 15125 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2018-04-25 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | Expected PEA Completion | NA | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Canceled | NA | NA | 2019-12-31 | NA | NA | NA | FALSE | 712.577 | NA ¦ NA | 3259.0783 | 634.3393 | 53.9794 | 0.08947 | 0.40581 | -15.8446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 3220.4482 | 53.9794 | 0.08947 | 0.40581 | -15.8446 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0% | [CPUC Status] Exempt
54 | CAST IMPERIAL VLLY SUBS PERIMET |  |  | Imperial County | Physical security hardening at Imperial Valley substation | Other - Physical Security | New | NA | NA | Physical Security | Security Upgrades | NERC CIP Compliance | NA | 2026-06-01 | NA | NA | NA | NA | Tier 3 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 55.48 | 230 ¦ 500 | 230kV¦500kV | 1.1 | 2021-2097 | QBL0020 | 1 | 15125 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-08-28 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | Exempt | Exempted | Other [See Notes] | CPUC | BLM | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2020-11-30 | 2021-12-31 | 2022-01-18 | NA | NA | FALSE | 19307.087 | NA ¦ NA | 20664.2234 | 15252.6844 | 26.6981 | 5.724 | 0 | -34.9987 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2025 | 20666.7999 | 26.6981 | 5.724 | 0 | -34.9987 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0% | [CPUC Status] Exempt
55 | [Programmatic] Advanced Protection |  |  | Multiple | Replaces aging circuit breakers and/or obsolete electromechanical relays, to create a more comprehensive protection system by taking advantage of newer field technologies under installation by the FiRM program, and to create visibility in fire threat areas with installation of Distribution SCADA. Adding distribution SCADA and replacing obsolete distribution relays and aging equipment. Improve distribution reliability and improve fire safety. | Substation - Multiple | Upgrade/Retrofit | NA | NA | Wildfire Mitigation | SCADA Switch Installation | NERC CIP Compliance | NA | NA | NA | NA | NA | NA | Tier 2 ¦ Tier 3 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | NA | NA | Multiple | 120MVA | 1.2 | Multiple | QBL0071 | 55 | 15259 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-12-11 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | NA | NA | NA | NA | NA | TRUE | NA | NA ¦ NA | 4931.9122 | 391.1629 | 744.3182 | 657.3595 | 761.7129 | 514.0282 | 41.2974 | 57.7425 | 0 | 0 | 0 | 0 | 137.6475 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 ¦ 2026 | 537.6631 | 849.8923 | 324.8239 | 310.9945 | 948.8579 | 1321.1596 | 0% | NA ¦ NA | 5.4 | NA | 0% | 100% | [CPUC Status] Exempt
56 | APPWMP: CREELMAN DTRU/TRTU UPG |  |  | Ramona, San Diego | In support of Advanced Protection Program - Wildfire Mitigation Program (APP-WMP); survey, design, procure, construct and replace TRTU/DRTU per current standards. Total equipment, labor and other costs contingent on final job requirements. and other equipment as required at the Creelman substation. | Substation - Multiple | Upgrade/Retrofit | NA | NA | Wildfire Mitigation | SCADA Switch Installation | NERC CIP Compliance | NA | 2026-04-22 | NA | NA | NA | NA | Tier 2 | FALSE ¦ TRUE ¦ FALSE | 0 | NA |  | NA | 1 | 69 | 84MVA | 1.2 | 2022-2747 | QBL0071 | 1 | 15259 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2022-04-05 | Work Order Authorization | 2022 | NA | FALSE | NA | NA | NA | FALSE | NA | exempt | NA | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Construction (over 75%) | NA | 2024-08-11 | 2026-05-28 | 2026-07-31 | NA | NA | TRUE | 555.0677 | NA ¦ NA | 1064.8533 | 0 | 60.2006 | 104.6596 | 534.1319 | 314.4814 | 25.8402 | 25.5396 | 0 | 0 | 0 | 0 | 1039.3138 | NA | NA | 2026 | 0 | 0 | 0 | 0 | 0 | 1064.8533 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
57 | APP WMP: BORDER SUBSTATION |  |  | San Diego, San Diego | Replace existing oil circuit breakers with vacuum, upgrade RTU and associated relay equipment. | Substation - Multiple | Upgrade/Retrofit | NA | NA | Wildfire Mitigation | Install SCADA/RTU | NA | NA | 2026-05-27 | NA | NA | NA | NA | Tier 2 ¦ Tier 3 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | NA | 0.94 | 69 | 373MVA | 1.2 | 2021-2054 | QBL0071 | 1 | 15259 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2021-02-18 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2022-05-18 | 2022-12-31 | 2024-04-23 | Construction Delays | NA | FALSE | 1682.9944 | NA ¦ NA | 1304.9773 | 98.5274 | 618.9882 | 539.5663 | 48.1926 | -0.29723 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2024 ¦ 2025 | 0 | 0 | 0 | 1305.2745 | -0.29723 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
58 | APP WMP: PALA SUBSTATION |  |  | San Diego, San Diego | Replace existing relays and RTU, other supporting equipment. | Substation - Multiple | Upgrade/Retrofit | NA | NA | Wildfire Mitigation | Install SCADA/RTU | NA | NA | 2026-05-21 | NA | NA | NA | NA | Tier 3 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | NA | 0.84 | 69 | 373MVA | 1.2 | 2021-2316 | QBL0071 | 1 | 15259 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2021-02-16 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Construction (50%-75%) | NA | 2023-05-08 | 2022-12-31 | 2026-06-17 | Workforce | NA | TRUE | 437.8891 | NA ¦ NA | 1397.8053 | 0 | 3.8588 | 762.793 | 497.1065 | 111.8733 | 21.7535 | 0.42003 | 0 | 0 | 0 | 0 | 1397.3852 | NA | NA | 2026 | 0 | 0 | 0 | 0 | 0 | 1397.8053 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
59 | APPWMP: PENDLETON SUBSTATION |  |  | Camp Pendleton | The work will include installing the 12kV DRTU, upgrading Bank 30 & Bank 31 relays and replacing the 12kV West & East bus protection relays all to our current standards. Also, we will be replacing the existing older style Bank Paralleling Scheme with a new Bank Paralleling Scheme utilizing the Beckwith M-2001D tap changer controller. | Substation - Multiple | Upgrade/Retrofit | NA | NA | Wildfire Mitigation | SCADA Switch Installation | NERC CIP Compliance | NA | 2026-04-13 | NA | NA | NA | NA | Tier 2 | FALSE ¦ TRUE ¦ FALSE | 0 | NA |  | NA | 0.7 | 69 | 56MVA | 1.2 | 2021-2056 | QBL0071 | 1 | 15259 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-10-30 | Work Order Authorization | 2021 | NA | FALSE | NA | NA | NA | FALSE | NA | exempt | Exempted | NA | CPUC | Dept. of Navy - Discretionary action not anticipated | Exempt | NA | NA [See Notes] | NA | Construction (25%-50%) | NA | 2024-10-30 | 2026-02-27 | 2026-08-31 | NA | NA | TRUE | 1101.828 | NA ¦ NA | 1337.1024 | 40.6432 | 335.9133 | 96.587 | 94.384 | 61.6625 | 449.1106 | 258.8018 | 0 | 0 | 0 | 0 | 1078.3006 | NA | NA | 2026 | 0 | 0 | 0 | 0 | 0 | 1337.1024 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
60 | SANTA YSABEL 69KV REBUILD |  |  | San Diego, San Diego | Replace existing 69kV bus, circuit breaker, and control shelter. | Substation - Multiple | Upgrade/Retrofit | NA | NA | Wildfire Mitigation | Bus Upgrade | NA | NA | 2026-04-21 | 54 | NA | NA | NA | Tier 3 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | NA | NA | 69 | 373MVA | 1.2 | 2019-0222 | QBL0071 | 1 | 15259 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2018-03-14 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2020-08-31 | 2019-06-01 | 2023-03-23 | Construction Delays | NA | FALSE | 9392.736 | NA ¦ NA | 11225.7544 | 3372.3254 | 2315.9885 | 992.1679 | 16.53 | -59.4819 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2023 ¦ 2024 ¦ 2025 | 0 | 0 | 11268.7064 | 16.53 | -59.4819 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
61 | WMP APP DESCANSO BK30 & YARD |  |  | San Diego, San Diego | Replace bank xfmr, extend yard for access. | Substation - Multiple | Upgrade/Retrofit | NA | NA | Wildfire Mitigation | Replace Transformer | NA | NA | 2026-05-14 | 44 | NA | NA | NA | Tier 3 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | NA | 0.34 | 69 | 373MVA | 1.2 | 2021-2202 | QBL0071 | 1 | 15259 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-12-18 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2022-08-01 | 2021-10-30 | 2023-11-18 | Construction Delays | NA | FALSE | 3469.791 | NA ¦ NA | 4353.1667 | 159.9943 | 2247.369 | 1727.4986 | 227.0474 | -11.9789 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2023 ¦ 2024 ¦ 2025 | 0 | 0 | 4138.0982 | 227.0474 | -11.9789 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
62 | DESCANSO UPGRADE TL626 RELAYING |  |  | San Diego, San Diego | Replace 69/12kV circuit breakers in support of FCP. | Substation - Multiple | Upgrade/Retrofit | NA | NA | Wildfire Mitigation | Relay Upgrades | NA | NA | 2026-05-14 | 3.2 | NA | NA | NA | Tier 3 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | NA | 0.34 | 69 | 373MVA | 1.2 | 2014-00432-ZZ-SUB | QBL0071 | 1 | 15259 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2016-08-31 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2016-11-07 | 2017-12-01 | 2021-06-30 | Construction Delays | NA | FALSE | 4278 | NA ¦ NA | 5027.0106 | 807.0655 | 45.0175 | -0.48344 | 0 | -28.051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2022 ¦ 2023 ¦ 2025 | 0 | 5055.5451 | -0.48344 | 0 | -28.051 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
63 | WARNERS UPGRADE TRANS RELAYING |  |  | San Diego, San Diego | Replace 69/12kV circuit breakers in support of FCP. | Substation - Multiple | Upgrade/Retrofit | NA | NA | Wildfire Mitigation | Relay Upgrades | NA | NA | 2026-04-21 | 3.2 | NA | NA | NA | Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | NA | 1.08 | 69 | 373MVA | 1.2 | 2014-00278-ZZ-SUB | QBL0071 | 1 | 15259 | 2026-06-17 ¦ 2014-00278-ZZ-CIR ¦ NA ¦ NA | TRUE | 2016-08-31 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2016-11-08 | 2017-12-01 | 2021-12-17 | Construction Delays | NA | FALSE | 5090 | NA ¦ NA | 5760.9723 | 905.0979 | 770.9282 | 77.9159 | 0.04789 | -41.9134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2023 ¦ 2024 ¦ 2025 | -0.86438 | 0 | 5803.7023 | 0.04789 | -41.9134 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
64 | APPWMP: POMERADO SUBSTATION |  |  | Poway, San Diego | RTU and Relay Replacement | Substation - Multiple | Upgrade/Retrofit | NA | NA | Wildfire Mitigation | Relay Upgrades | NA | NA | 2026-05-01 | 19; 33; 27 | NA | NA | NA | Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | NA | 1.37 | 69 | 373MVA | 1.2 | 2021-2178 | QBL0071 | 1 | 15259 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2021-02-16 | Work Order Authorization | 2022 | NA | FALSE | NA | NA | NA | FALSE | TBD | TBD | NA | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2023-12-11 | 2022-07-31 | 2024-08-02 | Construction Delays | NA | FALSE | 508.0072 | NA ¦ NA | 1052.8302 | 37.0979 | 58.7327 | 546.5654 | 404.8551 | 5.5791 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2024 ¦ 2025 | 0 | 0 | 0 | 1047.2511 | 5.5791 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
65 | STUART SUBSTATION APP/DCRU |  |  | San Diego, San Diego | Breaker and RTU Replacement | Substation - Multiple | Upgrade/Retrofit | NA | NA | Wildfire Mitigation | Relay Upgrades | NA | NA | 2026-04-13 | 63; 12 | NA | NA | NA | Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | NA | 0.12 | 69 | 373MVA | 1.2 | 2021-2177 | QBL0071 | 1 | 15259 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2018-01-30 | Work Order Authorization | 2021 | NA | FALSE | NA | NA | NA | FALSE | TBD | TBD | NA | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2022-10-25 | 2022-07-31 | 2024-10-25 | Construction Delays | NA | TRUE | 112.179 | NA ¦ NA | 1089.5405 | 87.1562 | 336.3774 | 203.7923 | 152.9362 | -12.0911 | 0.59181 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 ¦ 2026 | 407.934 | 336.3774 | 203.7923 | 152.9362 | -12.0911 | 0.59181 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
66 | CAMERON ADD 69KV BUS TIE |  |  | San Diego, San Diego | Add 69kV bus tie circuit breaker, conductor and associated equipment. | Substation - Circuit Breaker | Upgrade/Retrofit | NA | NA | Wildfire Mitigation | Bus Upgrade | NA | NA | 2026-05-14 | NA | NA | NA | NA | Tier 3 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | NA | NA | 69 | 373MVA | 1.2 | 2014-01075-ZZ | QBL0071 | 1 | 15259 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2018-03-14 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2020-12-07 | 2019-03-01 | 2021-11-01 | Construction Delays | NA | FALSE | 2429 | NA ¦ NA | 3425.6743 | 2084.9862 | 10.2088 | 0 | 0 | -7.6738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2025 | 3423.1392 | 10.2088 | 0 | 0 | -7.6738 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
67 | [Programmatic] Substation Security Installations (16126) |  |  | Multiple | This budget is required to maintain the reliability and integrity of the security of electric substations. The specific work required to meet safety requirements, replace obsolete or failed equipment, and make necessary small capital additions is based on requests from Engineering, Planning, Operations, and Maintenance groups. | Other - Physical Security | New | NA | NA | Physical Security | Security Upgrades | NERC CIP Compliance | NA | NA | NA | NA | Wires - New Substation Alternative | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | Multiple | NA | 4.3 | Multiple | QBL0002 | 36 | 16126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2025-04-28 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | NA | NA | To be Filed | NA | Operational | NA | NA | NA | NA | NA | NA | FALSE | NA | NA ¦ NA | 52281.8157 | 2024.6019 | 1675.1554 | 3034.3998 | -234.536 | -10.6284 | 0 | -1.819e-12 | 0 | 3376.4747 | 3781.2517 | 4190.0212 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 269.1069 | 4148.4855 | 1940.1926 | 1040.115 | -10.6284 | 0 | 0% | NA ¦ NA | 8.53 | NA | 45.85% | 54.15%
68 | NON CAST SECURITY VARIOUS SUBS |  |  | San Diego, San Diego | Security Upgrade and Fence project | Other - Physical Security | Upgrade/Retrofit | NA | NA | Physical Security | Security Upgrades | NA | NA | 2026-04-27 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | NA | NA | 4.3 | NA | QBL0002 | 1 | 16126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2021-01-29 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | NA | 2021-12-31 | 2023-07-30 | Construction Delays | NA | FALSE | 2214.5143 | NA ¦ NA | 9091.0808 | 5152.3225 | 3045.8478 | 938.3538 | -11.6009 | -33.8423 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2023 ¦ 2024 ¦ 2025 | 0 | 0 | 9136.5241 | -11.6009 | -33.8423 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] Exempt
69 | ESCO SUB NONCAST SECURITY |  |  | Escondido, San Diego | This project at ESCO Substation is for new systems installations to modernize this site in accordance with Sempra security standards and industry best practices and is expected to cost $1.1 million fully loaded with no AFUDC. These installations ensure this site will continue to provide the delivery of power to critical SDG&E customers in the near to interim future. The scope of work at ESCO Substation includes the following: the comprehensive replacement and/or installation, wiring, software programming for devices at five (5) security locations; and the installation of video management hardware with an access control management system to support the installed security devices. | Substation - Multiple | New | Upgrade/Retrofit | NA | Reliability | Substation Reliability | NA | NA | 2026-04-14 | NA | NA | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | 0 | NA |  | NA | 0.84 | 69 | 69¦12¦4kV | 4.3 | 2023-3521 | QBL0002 | 1 | 16126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-08-02 | Work Order Authorization | 2023 | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Construction (50%-75%) | NA | 2026-02-23 | 2026-06-11 | 2026-07-22 | NA | NA | TRUE | 1063.5124 | NA ¦ NA | 1501.5946 | 0 | 0 | 150.5095 | 191.6347 | 897.9101 | 172.3143 | 89.226 | 0 | 0 | 0 | 0 | 1412.3686 | NA | NA | 2026 | 0 | 0 | 0 | 0 | 0 | 1501.5946 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
70 | ELLIOT SUB FENCE GATE BROW DITC |  |  | San Diego, San Diego | Elliot Sub fence, gate, and brow ditch rebuild. | Substation - Structure | Upgrade/Retrofit | Replace | NA | Physical Security | Security Upgrades | NA | NA | 2026-05-13 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 0.8 | 69 | NA | 4.3 | 2022-2767 | QBL0002 | 1 | 16126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2021-12-03 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | Exempt | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2022-12-13 | 2022-12-31 | 2023-04-17 | NA | NA | FALSE | 2536.5572 | NA ¦ NA | 1811.3355 | 11.2673 | 674.8257 | 1126.088 | 0 | -0.84556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2023 ¦ 2025 | 0 | 0 | 1812.181 | 0 | -0.84556 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
71 | DEL MAR NONCAST SECURITY |  |  | San Diego, San Diego | This project at Del Mar Substation is for new systems installations to modernize this site in accordance with Sempra security standards and industry best practices and is expected to cost $1.3 million fully loaded with no AFUDC. These installations ensure this site will continue to provide the delivery of power to critical SDG&E customers in the near to interim future. The scope of work at Del Mar Substation includes the following: the comprehensive replacement and/or installation, wiring, software programming for devices at six (6) security locations; and the installation of video management hardware with an access control management system to support the installed security devices. | Substation - Multiple | New | Upgrade/Retrofit | NA | Physical Security | Substation Reliability | NA | NA | 2026-05-11 | NA | NA | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | 0 | NA |  | NA | 1.189 | 69 | 69¦12kV | 4.3 | 2024-3902 / 2024-3904 / 2023-3523 | QBL0002 | 1 | 16126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-08-02 | Work Order Authorization | 2023 | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Planning | NA | 2027-04-16 | 2027-08-09 | 2027-08-09 | NA | NA | FALSE | 1326.8492 | NA ¦ NA | 3038.1741 | 0 | 0 | 9.9402 | 89.3924 | 42.6806 | 31.0912 | 191.2613 | 2673.8085 | 0 | 0 | 0 | 173.1044 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
72 | IMPERIAL BEACH NONCAST SECURIT |  |  | San Diego, San Diego | This project at Imperial Beach Substation is for new systems installations to modernize this site in accordance with Sempra security standards and industry best practices and is expected to cost $834K fully loaded with no AFUDC. These installations ensure this site will continue to provide the delivery of power to critical SDG&E customers in the near to interim future. The scope of work at Imperial Beach Substation includes the following: the comprehensive replacement and/or installation, wiring, software programming for devices at four (4) security locations; and the installation of video management hardware with an access control management system to support the installed security devices. | Substation - Multiple | New | Upgrade/Retrofit | NA | Physical Security | Substation Reliability | NA | NA | 2026-04-15 | NA | NA | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | 0 | NA |  | NA | 0.49 | 69 | 69¦12¦4kV | 4.3 | 2023-3519 | QBL0002 | 1 | 16126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-05-05 | Work Order Authorization | 2023 | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Construction (25%-50%) | NA | 2025-05-05 | 2026-06-16 | 2026-09-08 | NA | NA | TRUE | 1071.0169 | NA ¦ NA | 3370.1087 | 0 | 0 | 73.6701 | 420.983 | 2428.6837 | 310.3398 | 136.4321 | 0 | 0 | 0 | 0 | 2973.1191 | NA | NA | 2024 ¦ 2025 ¦ 2026 | 0 | 0 | 0 | 260.5196 | 0.03779 | 3109.5513 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
73 | STATION F NON CAST SECURITY |  |  | San Diego, San Diego | Install new security system. | Other - Physical Security | Upgrade/Retrofit | New | NA | Physical Security | Security Upgrades | NA | NA | 2026-05-06 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 0.7 | 69 ¦ 12 | 69kV | 4.3 | 2021-2001 | QBL0002 | 1 | 16126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2021-12-07 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2022-12-13 | 2023-06-30 | 2023-12-12 | NA | NA | FALSE | 971.7073 | NA ¦ NA | 1350.0814 | 0 | 65.1837 | 1254.2796 | 32.2543 | -1.6362 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2024 ¦ 2025 | 0 | 0 | 0 | 1351.7176 | -1.6362 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
74 | BORDER SUB NONCAST SECURITY |  |  | San Diego, San Diego | This project at Border Substation is for new security systems installation to modernize this site in accordance with Sempra security standards and industry best practices. These new system installations ensure this site will continue to provide the delivery of power to critical SDG&E customers in the near to interim future and is expected to cost $862,524 fully loaded with no AFUDC. The scope of work at Border Substation includes the following: the comprehensive replacement and/or installation, wiring, software programming for devices at four (4) security locations; and the installation of video management hardware with an access control management system to support the installed security devices. | Substation - Multiple | New | Upgrade/Retrofit | NA | Physical Security | Substation Reliability | NA | NA | 2026-05-27 | NA | NA | NA | NA | Tier 2 | FALSE ¦ FALSE ¦ FALSE | 0 | NA |  | NA | 0.94 | 69 | 69¦12kV | 4.3 | 3-578735 | QBL0002 | 1 | 16126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-08-02 | Work Order Authorization | 2023 | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | CPUC | NA | NA | NA | To be Filed | NA | Operational | NA | 2025-06-02 | 2025-08-21 | 2025-10-09 | NA | NA | TRUE | 911.6949 | NA ¦ NA | 1181.0069 | 0 | 0 | 6.4773 | 179.4003 | 994.8743 | 0.25498 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2026 | 0 | 0 | 0 | 0 | 0 | 1181.0069 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
75 | PACIFIC BEACH NON CAST SECURITY |  |  | San Diego, San Diego | Fence Perimeter: Repair/Replace Fence or fencing material as required. ­Yard: Install low voltage and power conduit for security as required per plan New Pull Boxes, SP­Pads and 2” & 4” conduits will be required for security design. Note: Where possible existing trough, pull boxes, and existing conduit may be utilized for this effort ­Electrical Provide and install new electrical panel where applicable or identify existing panel and position. | Other - Physical Security | Replace | Replace | NA | Physical Security | Security Upgrades | NA | NA | 2026-05-01 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 0.35 | NA | NA | 4.3 | 2021-2004 | QBL0002 | 1 | 16126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-08-19 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2021-10-27 | 2022-05-31 | 2022-12-08 | Weather | NA | TRUE | 878.4705 | NA ¦ NA | 2396.3327 | 272.866 | 1259.3089 | 178.5459 | 158.1129 | 319.4992 | 9.8223 | 129.6763 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2023 ¦ 2024 ¦ 2025 ¦ 2026 | 0.056178 | 0 | 1779.1658 | 158.1129 | 319.4992 | 139.4986 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] Exempt
76 | SAN MARCOS NON CAST |  |  | San Marcos, San Diego | Fence Perimeter repair/replace fencing materials as needed; install low voltage and power conduit from security as required per plan, new pull boxes, SP Pads, where possible use existing pull boxes, conduit and trough | Other - Physical Security | Replace | Upgrade/Retrofit | NA | Physical Security | Security Upgrades | NA | NA | 2026-04-28 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 1.59 | 69 | 69kV | 4.3 | 2021-2381 | QBL0002 | 1 | 16126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2021-07-22 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2021-10-25 | 2022-12-31 | 2024-03-06 | Material | NA | FALSE | 2189.4406 | NA ¦ NA | 1560.8422 | 73.2847 | 293.3693 | 970.6194 | 226.7488 | -3.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2024 ¦ 2025 | 0 | 0 | 0 | 1564.0222 | -3.18 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
77 | VALLEY CENTER NON CAST SECURITY |  |  | Valley Center, San Diego | New Security System Installation | Other - Physical Security | New | New | NA | Physical Security | Security Upgrades | NA | NA | 2026-04-20 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 1.23 | 69 ¦ 12 | 69¦12kV | 4.3 | 2023-3526 | QBL0002 | 1 | 16126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-08-02 | Work Order Authorization | 2023 | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2024-06-06 | 2025-03-27 | 2025-03-28 | NA | NA | FALSE | 911.4247 | NA ¦ NA | 1431.5684 | 0 | 0 | 29.0159 | 908.4324 | 494.1202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2025 | 0 | 0 | 0 | 0 | 1431.5684 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
78 | CHOLLAS WEST NON CAST SECURITY |  |  | Lemon Grove, San Diego | Security Systems Installation | Substation - Multiple | New | New | NA | Physical Security | Security Upgrades | NA | NA | 2026-05-29 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 1.455 | 69 ¦ 12 | 69kV | 4.3 | 2023-3525 | QBL0002 | 1 | 16126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-08-01 | Work Order Authorization | 2023 | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2024-08-05 | 2024-12-13 | 2025-01-21 | NA | NA | FALSE | 1335.6712 | NA ¦ NA | 1428.524 | 0 | 0 | 15.0361 | 1323.281 | 90.2069 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2025 | 0 | 0 | 0 | 0 | 1428.524 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
79 | ENCINA SEURITY/FENCING |  |  | Encinitas, San Diego | New Fencing/Life Cycle Upgrade | Other - Physical Security | Upgrade/Retrofit | Upgrade/Retrofit | NA | Physical Security | Security Upgrades | NA | NA | 2026-05-20 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 4.86 | Multiple | 230kV | 4.3 | 2024-3884 | QBL0002 | 1 | 16126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-02-06 | Work Order Authorization | 2024 | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2024-04-22 | 2024-10-10 | 2024-10-10 | NA | NA | TRUE | 2707.4516 | NA ¦ NA | 1337.8455 | 0 | 0 | 0 | 1252.741 | 84.5036 | 0.60085 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2024 ¦ 2025 ¦ 2026 | 0 | 0 | 0 | 1252.741 | 84.5036 | 0.60085 | 0% | NA ¦ NA | NA ¦ NA | NA | 45.85% | 54.15% | [CPUC Status] Exempt
80 | ROSE CANYON NON CAST SECURITY |  |  | San Diego, San Diego | Non-Cast Security System Life Cycle Upgrade | Other - Physical Security | Upgrade/Retrofit | Upgrade/Retrofit | NA | Physical Security | Security Upgrades | NA | NA | 2026-05-04 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 1.32 | 69 ¦ 12 | 69kV | 4.3 | 2023-3520 | QBL0002 | 1 | 16126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-08-02 | Work Order Authorization | 2023 | NA | FALSE | NA | NA | NA | FALSE | PEA Deemed Complete | NA | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2024-07-08 | 2024-11-27 | 2025-01-22 | NA | NA | FALSE | 1083.7527 | NA ¦ NA | 1521.9069 | 0 | 0 | 32.731 | 1431.8276 | 57.3482 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2025 | 0 | 0 | 0 | 0 | 1521.9069 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
81 | TORREY PINES NON CAST |  |  | San Diego, San Diego | Non Cast New Security System | Other - Physical Security | Upgrade/Retrofit | New | NA | Physical Security | Security Upgrades | NA | NA | 2026-05-04 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | .811 | 69 ¦ 12 | 69kV | 4.3 | 2021-2380 | QBL0002 | 1 | 16126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2021-07-21 | Work Order Authorization | 2021 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Construction (25%-50%) | NA | 2024-07-15 | 2026-12-18 | 2026-12-18 | NA | NA | TRUE | 839.3466 | NA ¦ NA | 1961.4211 | 74.345 | 242.5152 | 110.0629 | 556.1138 | 238.7852 | -65.4734 | 805.0723 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2024 ¦ 2025 ¦ 2026 | 0 | 0 | 0 | 983.037 | 238.7852 | 739.5989 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
82 | CRESTWOOD NON CAST SECURITY |  |  | San Diego, San Diego | NON-CAST New Security System | Other - Physical Security | Upgrade/Retrofit | New | NA | Physical Security | Security Upgrades | NA | NA | 2026-05-18 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | .687 | 69 ¦ 12 | 69kV | 4.3 | 2023-3524 | QBL0002 | 1 | 16126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-08-01 | Work Order Authorization | 2023 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2024-08-12 | 2025-06-23 | 2025-07-10 | NA | NA | FALSE | 900.9477 | NA ¦ NA | 1486.56 | 0 | 0 | 46.1263 | 1039.2304 | 401.7029 | -0.4996 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2025 ¦ 2026 | 0 | 0 | 0 | 0 | 1487.0596 | -0.4996 | 0% | 100.00% ¦ 1,474 | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
83 | [Programmatic] Substation DC Reliability Upgrades |  |  | Multiple | This project installs new assets in existing substation control shelters to support increased power requirements driven by aging infrastructure replacements of telecommunication hardware. Scope includes installation of new communication racks, upgrades to 125V DC systems for power, adding HVAC in transmission substation control shelters to support equipment environmental control requirements, DC-DC power converters, as well as batteries and Station Light & Power (SL&P) upgrades. | Substation - Multiple | Upgrade/Retrofit | NA | NA | Reliability | Replace Other Substation Equipment | NA | NA | NA | NA | NA | NA | NA | Multiple | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | Multiple | 373MVA | 4.3 | Multiple | QBL0094 | 161 | 16138 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2025-01-27 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | NA | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | NA | NA | NA | NA | NA | TRUE | NA | NA ¦ NA | 47192.3899 | 3292.3127 | 2512.89 | 3361.4107 | 5173.1199 | 5928.8941 | 1434.4891 | 2046.0726 | 973.5173 | 2293.9596 | 0 | 0 | 1263.7449 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 ¦ 2026 | 2308.0923 | 3728.1573 | 1446.1603 | 4337.2667 | 8619.6951 | 3664.1956 | 0% | NA ¦ NA | 3.65 | NA | 45.85% | 54.15% | [CPUC Status] Exempt
84 | DCRU: VARIOUS SUBS 2022 |  |  | San Diego, San Diego | DC Reliability Upgrades at multiple substations | Substation - Other Equipment | Upgrade/Retrofit | NA | NA | Reliability | Replace Other Substation Equipment | NA | NA | NA | NA | NA | NA | NA | Multiple | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | Multiple | 373MVA | 4.3 | Multiple | QBL0094 | 1 | 16138 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2021-12-01 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | NA | 2022-12-31 | 2023-09-30 | Prioritization | NA | FALSE | 1428.1784 | NA ¦ NA | 2027.0821 | 25.7325 | 1520.8642 | 473.1137 | 12.782 | -5.4103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2023 ¦ 2024 ¦ 2025 | 0 | 0 | 2019.7105 | 12.782 | -5.4103 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 45.85% | 54.15% | [CPUC Status] Exempt
85 | VARIOUS SUBS DC REL UPGR 2020 |  |  | San Diego, San Diego | DC Reliability Upgrades at multiple substations | Substation - Other Equipment | Upgrade/Retrofit | NA | NA | Reliability | Replace Other Substation Equipment | NA | NA | NA | NA | NA | NA | NA | Multiple | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 5.14 | Multiple | 373MVA | 4.3 | 2021-2057 | QBL0094 | 1 | 16138 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-04-07 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | NA | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2021-05-10 | 2020-12-31 | 2021-11-09 | Prioritization | NA | FALSE | 1420.411 | NA ¦ NA | 2986.2346 | 287.8832 | 0 | 0 | 0 | -1.2575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2025 | 2987.492 | 0 | 0 | 0 | -1.2575 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 45.85% | 54.15% | [CPUC Status] Exempt
86 | DCRU PHASE IV IMPERIAL BEACH |  |  | San Diego, San Diego | Imperial Beach substation DC reliability upgrades | Substation - Other Equipment | Upgrade/Retrofit | NA | NA | Reliability | Replace Other Substation Equipment | NA | NA | 2026-04-15 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69 | 373MVA | 4.3 | 2020-2055 | QBL0094 | 1 | 16138 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-08-20 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | NA | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2021-11-02 | 2021-12-31 | 2022-06-17 | NA | NA | FALSE | 211.161 | NA ¦ NA | 1494.0003 | 523.2661 | 830.3421 | 12.3177 | 2.2148 | 13.4608 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 0.058964 | 1465.948 | 12.3177 | 2.2148 | 13.4608 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
87 | DCRU PHASE IV MIRAMAR |  |  | San Diego, San Diego | Miramar substation DC reliability upgrades | Substation - Protection Relay | New | NA | NA | Reliability | Replace Other Substation Equipment | NA | NA | 2026-05-07 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 0.76 | 69 | 373MVA | 4.3 | 2020-2054 | QBL0094 | 1 | 16138 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-08-20 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | NA | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2024-03-04 | 2021-12-31 | 2025-01-14 | Construction Delays | NA | FALSE | 1868.1833 | NA ¦ NA | 2760.3629 | 124.3884 | 378.0122 | 235.6891 | 1985.4425 | 1.593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2024 ¦ 2025 | 0.0018632 | 0 | 0 | 2636.0175 | 124.3435 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
88 | DCRU: VARIOUS SUBS 2021 |  |  | San Diego, San Diego | DC Reliability Upgrades at multiple substations | Substation - Other Equipment | Upgrade/Retrofit | NA | NA | Reliability | Replace Other Substation Equipment | NA | NA | NA | NA | NA | NA | NA | Multiple | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | Multiple | 373MVA | 4.3 | Multiple | QBL0094 | 1 | 16138 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2021-02-16 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | NA | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | NA | 2021-12-31 | 2021-12-31 | NA | NA | FALSE | 1512.758 | NA ¦ NA | 1928.6418 | 1876.3438 | 54.1322 | 0 | 0 | -1.8342 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2022 ¦ 2025 | 0 | 1930.476 | 0 | 0 | -1.8342 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 45.85% | 54.15% | [CPUC Status] Exempt
89 | DCRU: SONGS (SAN ONOFRE) |  |  | San Diego, San Diego | Install two new 8.5 Ton HVAC units to replace existing end of life units. | Substation - Multiple | New | NA | NA | Reliability | Replace Other Substation Equipment | NA | NA | 2026-05-27 | NA | NA | NA | NA | Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 5.14 | 230 | 373MVA | 4.3 | 2024-3883 | QBL0094 | 1 | 16138 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-10-26 | Work Order Authorization | 2023 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Planning | NA | 2026-01-07 | NA | 2026-05-21 | Prioritization | NA | TRUE | 395.3153 | NA ¦ NA | 1368.031 | 0 | 0.9567 | 45.8754 | 274.5863 | 212.3453 | 816.8059 | 17.4614 | 0 | 0 | 0 | 0 | 816.8059 | NA | NA | 2025 ¦ 2026 | 0 | 0 | 0 | 0 | 533.7636 | 834.2674 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0% | [CPUC Status] Exempt
90 | [Programmatic] Trans Fiber Links HFTD |  |  | Multiple | Install ADSS and or OPGW on existing Transmission overhead structures to support the Wildfire Mitigation Plan | Other | NA | NA | NA | Wildfire Mitigation | System Operations | NA | NA | NA | NA | NA | NA | NA | Tier 2 ¦ Tier 3 | TRUE ¦ TRUE ¦ TRUE | FALSE | NA |  | NA | NA | Multiple | NA | 1.2 | Multiple | QBL0100 | 60 | 19134 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-12-11 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | NA | NA | NA [See Notes] | NA | Operational | NA | NA | NA | NA | NA | NA | TRUE | NA | NA ¦ NA | 356159.7519 | 309.7274 | 742.3499 | 590.9537 | 1236.5793 | 1440.4673 | 1277.7826 | 22929.1436 | 24764.0889 | 22423.0363 | 31390.8346 | 34050.9946 | 3121.7052 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 ¦ 2026 | 150.5151 | 56.1362 | 844.5217 | 846.0627 | 578.9193 | 1142.1417 | 0% | NA ¦ NA | 6.9 | NA | 45.85% | 54.15% | [Wildfire Related] The purpose of this program is to install ADSS and or OPGW on existing Transmission overhead structures to support the Wildfire Mitigation Plan [CPUC Status] Exempt
91 | FBI RED MOUNTAIN TO AVOCADO |  |  | San Diego County | Engineer and construct a total of 3.0 miles of new 96-singlemode fiber optic cable for mountain top fiber installation. 3.0 miles of OH (S197808 / DNA-30411) All-Dielectric Self Support (ADSS) 96-fiber on existing structures. GO95 Compliance review and report will determine any structure/pole replacements, upgrades, or any Distribution underbuild that may be required prior to stringing. GO128 review Splice and test as per SDG&E Fiber Build standards. | Other | NA | NA | NA | Wildfire Mitigation | System Operations | NA | NA | NA | NA | NA | NA | NA | Tier 3 | FALSE ¦ TRUE ¦ FALSE | 0 | This project is all distribution 12kv. It has some BLM but I think it should not be on the list. |  | 6.7 | NA | NA | NA | 1.2 | 2022-3160 | QBL0100 | 1 | 19134 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2022-12-16 | Work Order Authorization | 2023 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | Other [See Notes] | NA | NA | NA | NA | NA [See Notes] | NA | Engineering more than 50% complete | NA | 2026-11-19 | 2026-07-04 | 2027-08-28 | NA | NA | FALSE | 1508.8844 | NA ¦ NA | 1854.6863 | 0 | 0 | 47.5073 | 240.5285 | 1276.5746 | 38.6122 | 111.0471 | 140.4167 | 0 | 0 | 0 | 1603.2225 | NA | NA | 2026 | 0 | 0 | 0 | 0 | 0 | -10.0808 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] Exempt
92 | CMP_T0_LR_TL689_Z614851X_NON_TT |  |  | San Diego, San Diego | Two poles are being replaced with foundation poles (Z12466, Z614851), one pole topped (Z12469), and one RFS pole (Z12467). | Other | New | New | NA | Reliability | System Operations | NA | NA | 2026-01-15 | 68 | NA | NA | NA | Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 7 | NA | NA | NA | 1.2 | TL689 Z614851/Z12466 | QBL0100 | 1 | 19134 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-08-21 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2020-05-28 | 2021-12-31 | 2023-09-18 | NA | NA | TRUE | 999.999 | NA ¦ NA | 1751.1606 | 69.8871 | 225.8063 | 735.6259 | 335.1959 | 32.7997 | 44.0485 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2023 ¦ 2024 ¦ 2025 ¦ 2026 | 0 | 0 | 1339.1165 | 335.1959 | 32.7997 | 44.0485 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] Exempt
93 | FBI TL6945 LH OLV |  |  | San Diego, San Diego | The project will include stringing 3.1 miles of new DNA-30411 ADSS conductor and about 2000 ft of DNO-11177 OPGW conductor, installing fiber attachments on existing transmission/distribution poles and installing fiber splice boxes. The conductor will enter Olivenhain and Lake Hodges substation overhead, attaching to existing substation infrastructure. It will also include lowering the crossarm on Z712320 and resagging the distribution conductor from Z220660 to Z201929 to mitigate clearances between the 69kV conductors and 12kV conductors. | Other | New | New | NA | Reliability | System Operations | NA | NA | 2026-01-27 | NA | NA | NA | NA | Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 4.3 | NA | NA | NA | 1.2 | 2019-4014 | QBL0100 | 1 | 19134 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-03-02 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2023-01-24 | 2022-06-01 | 2023-07-24 | NA | NA | FALSE | 2727.241 | NA ¦ NA | 1597.2942 | 137.8585 | 423.8597 | 681.3389 | 279.2689 | 2.7033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2023 ¦ 2024 ¦ 2025 | 0 | 0 | 1315.3219 | 279.2689 | 2.7033 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] Exempt
94 | FBI TL6930 ESCONDIDO OLIVEHAIN |  |  | Escondido, San Diego | The project will include stringing 2.2 miles of new DNA-30411 ADSS conductor (including 1.1 miles of underground ADSS, 0.1 miles of which will require new trenching), installing fiber attachments, and installing fiber splice boxes. It will also include reframing the transmission insulators on Z510521 and Z712314 to deadend attachments and the subsequent conductor work that follows. | Other | New | New | NA | Reliability | System Operations | NA | NA | 2026-01-27 | NA | NA | NA | NA | Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 3.8 | NA | NA | NA | 1.2 | 2019-4016 | QBL0100 | 1 | 19134 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-04-30 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2023-10-23 | 2022-06-01 | 2024-01-18 | NA | NA | FALSE | 3350.8595 | NA ¦ NA | 1378.0298 | 155.8626 | 284.0907 | 714.4985 | -44.0817 | 231.7879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2024 ¦ 2025 | 0 | 0 | 0 | 1146.2419 | 231.7879 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] Exempt
95 | TL23022/23023 MISSION EL R2 |  |  | San Diego, Lakeside, Rancho San Diego | Reinforcement of all Towers. installing 15.5 miles of OPGW | Other | New | New | NA | Reliability | System Operations | NA | NA | 2026-02-01 | NA | NA | NA | NA | Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 39.57 | NA | NA | NA | 1.2 | 2009-00009-ZZ | QBL0100 | 1 | 19134 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2022-10-21 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2024-08-19 | 2024-10-24 | 2025-06-09 | NA | NA | TRUE | 19458.775 | NA ¦ NA | 10206.6447 | 134.6871 | 340.2847 | 378.6109 | 1703.5783 | 7109.9293 | 297.5144 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2025 ¦ 2026 | 0 | 0 | 0 | 0 | 9909.1302 | 297.5144 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] Exempt
96 | FBI_T2_L3_TL23051_Z873123_NONTT |  |  | Poway, San Diego | Install Fiber Sycamore to Chicarita Sub ( 5.8 miles).. Install Fiber from Chicarita sub to Artesia (5 miles) | Other | New | New | NA | Reliability | System Operations | NA | NA | 2026-03-20 | NA | NA | NA | NA | Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 1.88 | NA | NA | NA | 1.2 | 2009-00014-ZZ | QBL0100 | 1 | 19134 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-02-06 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Engineering more than 50% complete | NA | 2026-05-26 | 2024-12-31 | 2027-03-08 | NA | NA | TRUE | 15134.7583 | NA ¦ NA | 2817.1878 | 48.0817 | 160.7231 | 703.4001 | 1133.6483 | 582.4952 | 52.161 | 68.3141 | 12.5012 | 0 | 0 | 0 | 1156.1935 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 ¦ 2026 | 48.0817 | 156.4773 | 699.3388 | 607.3652 | 13.0527 | 2.7208 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] Exempt
97 | TL23030 6932 PA LI FIBER L3 |  |  | San Diego, San Diego | Engineer and construct 9.3-miles of overhead OPGW-96 fiber optic cable structures between Lilac and Pala substations. | Other | Upgrade/Retrofit | New | NA | Reliability | System Operations | NA | NA | 2026-01-18 | NA | NA | NA | NA | Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 7.97 | NA | NA | NA | 1.2 | 2014-00958-ZZ | QBL0100 | 1 | 19134 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-04-29 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2025-09-25 | 2020-12-15 | 2026-04-07 | NA | NA | TRUE | 6333.0187 | NA ¦ NA | 10233.6718 | 309.0717 | 676.0852 | 1778.0586 | 1266.3898 | 4725.3764 | 342.7526 | 627.9218 | 84.1647 | 0 | 0 | 0 | 0 | NA | NA | 2026 | 0 | 0 | 0 | 0 | 0 | 9187.2077 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] Exempt
98 | TL689 BERNARDO FELECIT R4 |  |  | San Diego, San Diego | Engineer and construct 6.3 Miles of Overhead (OH) ADSS-96 fiber on 87 poles. Replace 9 new steel poles. 800 feet of UG fiber only trench & conduit from last pole to Felicita substation. Terminate, and test at substation control shelters. | Other | New | New | NA | Reliability | System Operations | NA | NA | 2026-01-15 | 40; 79; 79; 49; 60; 55; 58; 53 | NA | NA | NA | Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 7 | NA | NA | NA | 1.2 | 2014-00626-ZZ | QBL0100 | 1 | 19134 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2016-08-30 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2024-01-08 | 2018-06-20 | 2024-04-17 | NA | NA | FALSE | 5422.3961 | NA ¦ NA | 3312.2409 | 171.8393 | 616.8724 | 307.5244 | 1344.5018 | 41.6046 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2024 ¦ 2025 | 0 | 0 | 0 | 3270.6363 | 41.6046 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] Exempt
99 | TL635 LOS COCHES CREELMAN SUBS |  |  | Ramona, San Diego | This project installs a fiber optic connection between Creelman Substation and Los Coches Substation. | Other | New | New | NA | Reliability | System Operations | NA | NA | 2026-01-22 | NA | NA | NA | NA | Tier 3 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 10.5 | NA | NA | NA | 1.2 | 2014-01080-ZZ | QBL0100 | 1 | 19134 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-02-26 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2020-09-30 | 2021-06-01 | 2022-03-22 | NA | NA | FALSE | 4982.346 | NA ¦ NA | 1813.0442 | 3156.3408 | 341.3418 | 65.2845 | -2351.1425 | -6.3957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 0 | 4105.298 | 65.2845 | -2351.1425 | -6.3957 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] Exempt
100 | TL6917 CREELMAN SYCAMORE CYN |  |  | Ramona, San Diego | This project installs a fiber optic connection between Sycamore Canyon Substation and Creelman Substation. | Other | New | New | NA | Reliability | System Operations | NA | NA | 2026-01-22 | 27 | NA | NA | NA | Tier 3 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 12.2 | NA | NA | NA | 1.2 | 2014-01079-ZZ | QBL0100 | 1 | 19134 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-01-16 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2020-09-30 | 2021-06-01 | 2022-02-17 | NA | NA | FALSE | 5467.342 | NA ¦ NA | 2048.2461 | 1183.2743 | 225.2756 | 88.842 | -147.5676 | 50.9506 | -1.03 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2022 ¦ 2023 ¦ 2024 ¦ 2025 ¦ 2026 | 0 | 2057.0512 | 88.842 | -147.5676 | 50.9506 | -1.03 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] Exempt
101 | FBI_T2_L3_TL230001_Z96439_NONTT |  |  | San Diego, San Diego | FBI TL23004-TL23001 MROPS - RBDC Fiber Build | Other | Replace | New | NA | Reliability | System Operations | NA | NA | 2026-04-29 | NA | NA | NA | NA | Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 4.81 | NA | NA | NA | 1.2 | 2014-00950-ZZ | QBL0100 | 1 | 19134 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-07-25 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2024-11-08 | 2020-12-01 | 2025-07-22 | NA | NA | FALSE | 3099.5761 | NA ¦ NA | 6624.2575 | 822.6322 | 547.967 | 1450.8858 | 1001.5417 | 2867.4275 | -69.0111 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2025 ¦ 2026 | 0 | 0 | 0 | 0 | 6693.2685 | -69.0111 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] Exempt
102 | TL6904 ALPINE LOVELAND TRNM FIB |  |  | Alpine, San Diego | Install a level of ADSS fiber on 2.4 miles of TL6904 poles between Alpine Substation and Loveland Substation. Construct ADSS conduit on Z770043 and trench into Loveland Substation. Construct ADSS conduit on Z875063 and trench into Alpine Substation. Construct ADSS conduit on Z770043 and trench into Loveland Substation (to be designed by others). 3 Steel Pole Replacements | Other | New | New | NA | Reliability | System Operations | NA | NA | 2026-01-22 | 54; 54; 54 | NA | NA | NA | Tier 3 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 0.5 | NA | NA | NA | 1.2 | 2019-4008 | QBL0100 | 1 | 19134 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-01-08 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2023-06-19 | 2022-08-20 | 2023-11-15 | NA | NA | FALSE | 2201.0696 | NA ¦ NA | 1948.9911 | 113.6317 | 338.6923 | 1082.199 | 284.3364 | 52.7563 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2023 ¦ 2024 ¦ 2025 | 0 | 0 | 1611.8985 | 284.3364 | 52.7563 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] Exempt
103 | TL23022/23 MISSION TO LOS COCHE |  |  | San Diego ¦ Santee ¦ Granite Hills, San Diego | Remove and replace 19miles of OHGW with OPGW. | Other | Replace | Upgrade/Retrofit | NA | Reliability | System Operations | NA | NA | 2026-02-01 | NA | NA | NA | NA | Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 39.57 | NA | NA | NA | 1.2 | 2023-3234 | QBL0100 | 1 | 19134 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-01-11 | Work Order Authorization | 2023 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Construction (10%-25%) | NA | 2027-07-21 | 2025-12-01 | 2028-09-29 | NA | NA | FALSE | 16508.676 | NA ¦ NA | 2909.5098 | 0 | 0 | 476.3328 | 1163.8882 | 625.6678 | 94.8764 | 160.4302 | 231.2265 | 157.0878 | 0 | 0 | 2360.7652 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] Exempt
104 | FBI TL23002/23010 SOSA |  |  | Camp Pendleton, San Diego | Remove and replace 18 miles of OHGW with OPGW | Other | Replace | Upgrade/Retrofit | NA | Reliability | System Operations | NA | NA | 2026-01-04 | NA | NA | NA | NA | Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | TBD |  | 17.74 | NA | NA | NA | 1.2 | 2023-3433 | QBL0100 | 1 | 19134 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-06-28 | Work Order Authorization | 2024 | NA | FALSE | NA | NA | NA | FALSE | TBD | NA | Exempted | NA | CPUC | NA | Exempt | 2023-10-07 | NA [See Notes] | NA | Engineering more than 50% complete | NA | 2027-07-14 | 2027-04-30 | 2028-01-12 | NA | NA | FALSE | 0 | NA ¦ NA | 5818.0321 | 0 | 0 | 24.3011 | 2129.6834 | 2134.0259 | 546.5597 | 324.9455 | 468.3408 | 190.1756 | 0 | 0 | 4834.5701 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] Exempt
105 | FBI TL23006 SO SA |  |  | Camp Pendleton, San Diego | Remove and replace 18 miles of OHGW with OPGW | Other | Upgrade/Retrofit | Upgrade/Retrofit | NA | Reliability | System Operations | NA | NA | 2026-01-04 | NA | NA | NA | NA | Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | TBD |  | 17.74 | NA | NA | NA | 1.2 | 2023-3431 | QBL0100 | 1 | 19134 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-06-28 | Work Order Authorization | 2024 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Engineering more than 50% complete | NA | 2027-07-14 | 2027-01-30 | 2028-01-12 | NA | NA | FALSE | 2256.547 | NA ¦ NA | 6336.9543 | 0 | 0 | 165.3863 | 2911.161 | 2097.024 | 193.1462 | 367.3356 | 529.4372 | 73.464 | 0 | 0 | 5366.7175 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] Exempt
106 | FBI TL23052/23007 SO TA |  |  | Camp Pendleton, San Diego | Remove and replace 7 miles of OHGW with OPGW | Other | New | Upgrade/Retrofit | NA | Reliability | System Operations | NA | NA | 2026-01-18 | NA | NA | NA | NA | Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | TBD |  | 8.23 | NA | NA | NA | 1.2 | 2023-3434 | QBL0100 | 1 | 19134 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-06-30 | Work Order Authorization | 2024 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Engineering more than 50% complete | NA | 2026-12-21 | 2026-11-15 | 2027-10-08 | NA | NA | FALSE | 0 | NA ¦ NA | 3156.5265 | 0 | 0 | 176.1924 | 1232.9519 | 1256.5825 | 110.0826 | 188.6713 | 192.0459 | 0 | 0 | 0 | 2775.8093 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] Exempt
107 | FBI TL23004/23001 SAN LUIS REY |  |  | San Diego, San Diego | Remove and replace 6miles of OHGW with OPGW | Other | New | Upgrade/Retrofit | NA | Reliability | System Operations | NA | NA | 2026-04-29 | NA | NA | NA | NA | Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | TBD |  | 41.64 | NA | NA | NA | 1.2 | 2023-3412 | QBL0100 | 1 | 19134 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-06-07 | Work Order Authorization | 2023 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Engineering less than 50% complete | NA | 2027-10-07 | 2025-12-31 | 2028-04-21 | NA | NA | FALSE | 2143.4765 | NA ¦ NA | 3016.9959 | 0 | 0 | 369.4347 | 1366.2285 | 713.1718 | 71.8093 | 171.3228 | 246.9259 | 78.1029 | 0 | 0 | 2520.6443 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] Exempt
108 | TL685 SANTA YSABEL TO WA R1 |  |  | San Diego, San Diego | Install approximately 11 miles of 96 count fiber optic DNA-30411. Installation will begin at Warner Springs Substation and terminate at Santa Ysabel Substation. There are a total of 155 structures along the TL at which fiber optic will be installed. | Other | New | New | NA | Reliability | System Operations | NA | NA | 2026-01-22 | NA | NA | NA | NA | Tier 2 ¦ Tier 3 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 13.33 | NA | NA | NA | 1.2 | 2014-00624-ZZ | QBL0100 | 1 | 19134 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-01-14 | Work Order Authorization | 2019 | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2020-05-18 | 2020-11-30 | 2022-09-28 | NA | NA | TRUE | 7336.2692 | NA ¦ NA | 2673.0361 | 201.6687 | 244.7681 | 320.4627 | 268.1965 | 803.8774 | 52.5192 | 27.8676 | 40.1654 | 27.287 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 ¦ 2026 | 13.407 | 972.4056 | 84.7003 | 586.2986 | 438.5269 | 29.0456 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] Exempt
109 | FBI_T2_L2_TL683_Z518466_NONTT |  |  | Valley Center, San Diego | This project installs 9.7 miles of ADSS fiber | Other | New | New | NA | Reliability | System Operations | NA | NA | 2026-02-03 | 54; 54; 25; 54; 37; 54; 54; 42 | NA | NA | NA | Tier 2 ¦ Tier 3 | FALSE ¦ TRUE ¦ FALSE | FALSE | TBD |  | 11.86 | NA | NA | NA | 1.2 | 2014-00983-ZZ | QBL0100 | 1 | 19134 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-01-08 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Engineering more than 50% complete | NA | 2021-07-09 | 2022-12-01 | 2026-10-30 | NA | NA | TRUE | 4223.5163 | NA ¦ NA | 4659.4488 | 50.311 | 291.743 | 445.0976 | 2380.9844 | 892.7559 | 242.3595 | 296.9097 | 54.3097 | 0 | 0 | 0 | 4306.1862 | NA | NA | 2025 ¦ 2026 | 0 | 0 | 0 | 0 | -2.9349 | 19.22 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] Exempt
110 | RINCON SUB TO PALOMAR MT C214 |  |  | San Diego, San Diego | Engineer and construct a total of 9.0 miles of new 96-single mode fiber optic cable for mountaintop fiber installation. Install 9.0 miles of OH (S197808 / DNA-30411) All-Dielectric Self Support (ADSS) 96-fiber on existing distribution structures. GO95 Compliance review and report ( 30% pass/fail to report) will determine any structure/pole replacements, upgrades, or any Distribution underbuild that may be required prior to stringing. Splice and test as per SDG&E Fiber Build standards. | Substation - Multiple | New | New | NA | Reliability | System Operations | NA | NA | NA | NA | NA | NA | NA | Tier 3 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 9 | NA | 69 | NA | 1.2 | Rincon to Palomar | QBL0100 | 1 | 19134 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2022-12-14 | Work Order Authorization | 2023 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | On Hold | NA | NA | NA | NA | NA | NA | TRUE | 1590.7568 | NA ¦ NA | 1695.5026 | 0 | 0 | 61.1034 | 1344.3693 | 149.1773 | 36.4422 | 104.4105 | 0 | 0 | 0 | 0 | 1592 | NA | NA | 2025 ¦ 2026 | 0 | 0 | 0 | 0 | -0.68717 | 1696.1898 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
111 | FBI TL694 Z31079 Z317898 |  |  | Oceanside, San Diego | San Diego Gas and Electric (SDG&E) proposes to install approximately 3.2 miles of 96-count ADSS fiber optic cable. 3.2 miles of OH (S197808 / DNA-30411) All-Dielectric Self Support (ADSS) 96-fiber on existing structures. GO95 Compliance review and report will determine any structure/pole replacements, upgrades, or any Distribution underbuild that may be required prior to stringing. GO128 review and report to determine if any existing handholes will require upgrades or new handholes installations. Splice and test as per SDG&E Fiber Build standards. | Substation - Multiple | New | New | NA | Reliability | System Operations | NA | NA | 2026-01-29 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 9.51 | NA | 69 | NA | 1.2 | 2020-4024 | QBL0100 | 1 | 19134 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2022-02-24 | Work Order Authorization | 2022 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2024-09-09 | 2024-07-22 | 2025-07-18 | NA | NA | TRUE | 5767.7932 | NA ¦ NA | 4466.7268 | 0 | 62.6967 | 350.1312 | 2320.4702 | 1545.5216 | 187.907 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2025 ¦ 2026 | 0 | 0 | 0 | 0 | 4278.8197 | 187.907 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
112 | FBI TL694 NVY OCR ME PHASE 1 UG |  |  | Oceanside, San Diego | Engineer and construct a total of 6.5 miles of new 96-singlemode fiber optic cable for relay protection and network communications. Install 3X inner-ducts and (S197826 / DNL-4599) All-Dielectric 96-fiber through existing UG ducts, and 3.5 miles of OH (S197808 / DNA-30411) All-Dielectric Self Support (ADSS) 96-fiber on existing structures. GO95 Compliance review and report will determine any structure/pole replacements, upgrades, or any Distribution underbuild that may be required prior to stringing. GO128 review and report to determine if any existing handholes will require upgrades or new handholes installations. Splice and test as per SDG&E Fiber Build standards. | Substation - Multiple | New | New | NA | Reliability | 3rd Party Damage | NA | NA | 2026-01-29 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 9.51 | NA | 69 | NA | 1.2 | 2020-4024 | QBL0100 | 1 | 19134 | 2026-06-17 ¦ 2014-00979-ZZ ¦ NA ¦ NA | TRUE | 2022-01-31 | Work Order Authorization | 2023 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2024-01-22 | 2022-12-10 | 2025-06-12 | NA | NA | TRUE | 5814.2996 | NA ¦ NA | 5179.155 | 0 | 100.6571 | 332.9439 | 2833.091 | 1847.2649 | 65.1981 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2025 ¦ 2026 | 0 | 0 | 0 | 0 | 5113.9569 | 65.1981 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
113 | TL681 VALLEY ASH FIB R3 |  |  | Escondido ¦ Valley Center, San Diego | This project installs a fiber optic connection between Valley Center Substation and Ash Substation. | Substation - Multiple | New | New | NA | Reliability | 3rd Party Damage | NA | NA | 2026-02-03 | NA | NA | NA | NA | Tier 1 ¦ Tier 2 ¦ Tier 3 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 8 | NA | 69 | NA | 1.2 | 2014-00949-ZZ | QBL0100 | 1 | 19134 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2018-03-02 | Work Order Authorization | 2019 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Construction (50%-75%) | NA | 2026-03-16 | 2024-12-01 | 2026-05-28 | NA | NA | TRUE | 4090.086 | NA ¦ NA | 6844.6143 | 151.5426 | 186.7552 | 284.8158 | 4234.9117 | 1138.4375 | 222.7139 | 421.492 | 0 | 0 | 0 | 0 | 6242 | NA | NA | 2024 ¦ 2025 ¦ 2026 | 0 | 0 | 0 | -11.963 | -10.5579 | 6867.1352 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
114 | FBI MIGUEL TO MIGUEL |  |  | San Diego, San Diego | This is a fiber project to add communication cable ADSS 7.8 miles UG & OH from Miguel tower to Miguel substation | Other | New | New | NA | Reliability | System Operations | NA | NA | NA | NA | NA | NA | NA | Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | TBD |  | NA | 12.37 | 69 | NA | 1.2 | 2022-3158 | QBL0100 | 1 | 19134 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2022-12-16 | Work Order Authorization | 2023 | NA | FALSE | NA | NA | NA | FALSE | TBD | NA | NA | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Engineering more than 50% complete | NA | 2026-04-30 | 2026-09-28 | 2027-09-17 | NA | NA | FALSE | 1508.8844 | NA ¦ NA | 2362.3922 | 0 | 0 | 89.4503 | 251.7647 | 1669.2182 | 47.4179 | 142.2606 | 162.2804 | 0 | 0 | 0 | 2057.8512 | NA | NA | 2026 | 0 | 0 | 0 | 0 | 0 | -4.7542 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
115 | GLENCLIFF SUB-MONUMENTPEAKC440 |  |  | San Diego, San Diego | This is a fiber project to add communication cable ADSS 11.5 miles UG & OH from Glencliff to Monument peak substation | Other | New | New | NA | Reliability | System Operations | NA | NA | NA | NA | NA | NA | NA | Tier 3 | FALSE ¦ FALSE ¦ FALSE | FALSE | TBD |  | NA | 0.15 | 69 | NA | 1.2 | 2022-3136 | QBL0100 | 1 | 19134 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2022-12-14 | Work Order Authorization | 2023 | NA | FALSE | NA | NA | NA | FALSE | TBD | NA | Exempted | Other [See Notes] | CPUC | CNF / BLM | Exempt | NA | NA [See Notes] | NA | Engineering more than 50% complete | NA | 2027-05-27 | 2026-09-18 | 2027-12-21 | NA | NA | FALSE | 1590.7568 | NA ¦ NA | 1346.223 | 0 | 0 | 44.7336 | 224.7437 | 799.2439 | 28.8368 | 75.6239 | 108.996 | 64.0451 | 0 | 0 | 1097.5579 | NA | NA | 2026 | 0 | 0 | 0 | 0 | 0 | -0.44859 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
116 | [Programmatic] PSPS Engineering Enhancements |  |  | Multiple | Mitigate the impact to customers and communities involved in PSPS events by installing additional remote distribution sectionalizing devices (reclosers) within the HFTD. ​ | Other | Upgrade/Retrofit | Upgrade/Retrofit | NA | Wildfire Mitigation | Fire Protection | NA | NA | NA | NA | NA | NA | NA | Tier 2 ¦ Tier 3 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | NA | NA | NA | NA | 1.2 | Multiple | QBL0080 | 7 | 19245 | 2026-06-17 ¦ NA ¦ NA ¦ NA | TRUE | 2023-11-16 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | CPUC | NA | NA | NA | NA [See Notes] | NA | Operational | NA | NA | NA | NA | NA | NA | FALSE | NA | NA ¦ NA | 1656.864 | 140.7236 | 86.0347 | 54.0949 | 85.3059 | 21.0342 | 0.73289 | 19.7251 | 150.6143 | 246.2311 | 14.3731 | 6.4362 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 ¦ 2026 | 117.009 | 904.8739 | 62.5786 | 74.5874 | 26.4487 | -0.010352 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] Exempt
117 | [Programmatic] HFTD Undergrounding |  |  | Multiple | Program budget for overhead to underground projects within the High Fire Threat Districts (HFTD) of Tier 2 and 3 as outlined in SDG&E's Wildfire Mitiagation Plan (WMP). This is an electric distribution programmatic (aka Blanket) budget. The forecasted costs shown for this program include the FERC-specific transmission costs only related to the program. | Other | Replace | NA | NA | Wildfire Mitigation | Facility Relocation | NA | NA | NA | NA | NA | NA | NA | Tier 2 ¦ Tier 3 | FALSE ¦ TRUE ¦ FALSE | FALSE | Individual project reviews required |  | NA | NA | Multiple | NA | 1.2 | Multiple | QBL0081 | 7 | 19246 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2025-03-17 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Construction (over 75%) | NA | Multiple | Multiple | Multiple | NA | NA | TRUE | NA | NA ¦ NA | 65.5443 | -259.1355 | -20.1032 | 747.9368 | -724.5059 | -46.8853 | 2.6845 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2026 | 55.9535 | 11.0168 | 24.1834 | -59.4965 | 0 | 33.8871 | 0% | NA ¦ NA | NA ¦ NA | NA | 45.85% | 54.15% | [CPUC Status] Exempt
118 | HFTD Undergrounding |  |  | Multiple | Program budget for overhead to underground projects within the High Fire Threat Districts (HFTD) of Tier 2 and 3 as outlined in SDG&E's Wildfire Mitiagation Plan (WMP). This is an electric distribution programmatic (aka Blanket) budget. The forecasted costs shown for this program include the FERC-specific transmission costs only related to the program. | Other | Replace | NA | NA | Wildfire Mitigation | Facility Relocation | NA | NA | NA | NA | NA | NA | NA | Tier 2 ¦ Tier 3 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | NA | NA | Multiple | NA | 1.2 | NA | QBL0081 | 1 | 19246 | 2026-06-17 ¦ NA ¦ NA ¦ NA | TRUE | 2025-03-17 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Construction (over 75%) | NA | Multiple | Multiple | Multiple | NA | NA | TRUE | 0 | NA ¦ NA | 3813.2396 | 33.6557 | 2349.5081 | 154.8362 | 523.1324 | 714.7637 | 30.3714 | 0 | 0 | 0 | 0 | 0 | 1259.3559 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 ¦ 2026 | 19.8374 | 267.2411 | 2238.4636 | 17.5389 | 3.8307 | 4.5469 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] Exempt
119 | [Programmatic] Fire Science Enhancement |  |  | Multiple | This project will enhance the fire science capabilities at SDGE. New tools and technologies will be developed to greatly enhance current technologies such as the fire potential index and create the next generation of fire weather tools. Partnerships with leading academic innovators on the cutting edge of research and development in fire science will ensure SDGE remains an industry leader. | Other - Operations Tech | NA | NA | NA | Wildfire Mitigation | Fire Protection | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | NA | NA | 1.2 | Multiple | QBL0096 | 4 | 19248 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-11-22 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Operational | NA | NA | NA | NA | NA | NA | FALSE | NA | NA ¦ NA | 1006.726 | 240.0384 | 283.2154 | 233.0757 | 210.3933 | -206.6508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 486.6925 | 283.2154 | 233.0757 | 210.3933 | -206.6508 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] Exempt
120 | [Programmatic] Transmission CMP Non HFTD |  |  | Multiple | Remediate CMP Issues in the Non-HFTD Zone | Transmission Line - Pole/Tower | Replace | NA | NA | Asset Condition | Age/Condition | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | Multiple | NA | 1.1 | Multiple | QBL0098 | 1080 | 20126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-12-11 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | TBD | NA | Exempted | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | NA | NA | NA | NA | NA | TRUE | NA | NA ¦ NA | 690556.0851 | 33046.6022 | 31003.703 | 33632.6142 | 28581.4942 | 28835.1803 | 7509.8727 | 30047.3339 | 35963.0024 | 37498.0528 | 39755.51 | 38972.5038 | 6818.1891 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 ¦ 2026 | 33341.7208 | 32468.2266 | 35537.917 | 29402.283 | 25041.1301 | 15414.9734 | 0% | NA ¦ NA | 2.1 | NA | 45.85% | 54.15% | [CPUC Status] Exempt
121 | CMP_T0_L2_TL6925_Z273965_14637 |  |  | El Cajon, San Diego | Remediate CMP Issues in the Non-HFTD Zone | Transmission Line - Pole/Tower | Replace | Upgrade/Retrofit | NA | Other [See Notes] | Age/Condition | NA | NA | 2026-02-12 | 65 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.1 | NA | Multiple | NA | 1.1 | 2023-3297 | QBL0098 | 1 | 20126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-06-19 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Permitting | NA | 2024-07-12 | 2022-12-31 | 2027-03-10 | Permitting | Scope Change | TRUE | 582.9629 | NA ¦ NA | 2071.4567 | 186.6442 | 343.7054 | 266.8045 | 964.9894 | 239.0797 | 2.7354 | 0.40929 | 0.027511 | 0 | 0 | 0 | 0 | NA | NA | 2024 ¦ 2025 ¦ 2026 | 0 | 0 | 0 | 1828.7101 | 235.0008 | 1.367 | 0% | NA ¦ NA | NA ¦ NA | NA | 45.85% | 54.15% | [Primary Purpose] Fire Damage [CPUC Status] Exempt
122 | CMP_T0_TL630_Z475724_TT13577 |  |  | El Cajon, San Diego | Remediate CMP Issues in the Non-HFTD Zone | Transmission Line - Pole/Tower | Replace | Upgrade/Retrofit | NA | Asset Condition | Age/Condition | NA | NA | 2026-01-27 | 63 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.1 | NA | 69 | NA | 1.1 | TL630 Z475724 | QBL0098 | 1 | 20126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2018-02-20 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2022-12-16 | 2020-02-14 | 2023-12-09 | Permitting | Material | FALSE | 84.4165 | NA ¦ NA | 2981.682 | 283.6215 | 547.349 | 1233.3298 | 659.4369 | 26.5806 | 0.11369 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2024 ¦ 2025 ¦ 2026 | 0 | 0 | 0 | 2954.9876 | 26.5806 | 0.11369 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
123 | CMP_T0_LX_TL644_Z187464_TT16696 |  |  | National City, San Diego | Remediate CMP Issues in the Non-HFTD Zone | Transmission Line - Pole/Tower | Replace | Upgrade/Retrofit | NA | Safety | T-Line Reliability | NA | NA | 2026-02-05 | 66; 40; 46; 72 | NA | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | 0 | NA |  | 0.1 | NA | 69 | NA | 1.1 | 2024-3699 | QBL0098 | 1 | 20126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-02-01 | Work Order Authorization | 2024 | NA | FALSE | NA | NA | NA | FALSE | NA | Exempt | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Construction (25%-50%) | NA | 2026-03-09 | 2026-01-25 | 2026-09-08 | Project Design | Material | TRUE | 1044.4704 | NA ¦ NA | 1226.6503 | 0 | 0 | 0 | 295.3843 | 788.1844 | 93.4844 | 49.5973 | 0 | 0 | 0 | 0 | 1177 | NA | NA | 2026 | 0 | 0 | 0 | 0 | 0 | 1226.6503 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
124 | CMP_T0_L2_TL600_Z91160_14180 |  |  | San Diego, San Diego | Remediate CMP Issues in the Non-HFTD Zone | Transmission Line - Pole/Tower | Replace | Upgrade/Retrofit | NA | Asset Condition | Age/Condition | NA | NA | 2026-02-12 | 73 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69 | NA | 1.1 | TL600 Z91160 | QBL0098 | 1 | 20126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-08-21 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2022-02-04 | 2020-12-31 | 2023-06-11 | Permitting | Material | FALSE | 999.999 | NA ¦ NA | 1438.2262 | 121.8526 | 736.2249 | 396.4809 | 26.0207 | -3.7591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2023 ¦ 2024 ¦ 2025 | 0 | 0 | 1415.9646 | 26.0207 | -3.7591 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
125 | CMP_T0_L2_TL6908_Z618845_11163 |  |  | Escondido, San Diego | Remediate CMP Issues in the Non-HFTD Zone | Transmission Line - Pole/Tower | Replace | Upgrade/Retrofit | NA | Asset Condition | Age/Condition | NA | NA | 2026-01-06 | 32 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69 | NA | 1.1 | TL6908 Z618845 | QBL0098 | 1 | 20126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-03-06 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2021-07-01 | 2021-10-04 | 2021-09-22 | NA | NA | FALSE | 80 | NA ¦ NA | 1015.6931 | 876.3129 | 33.283 | 22.972 | 0.00052 | -0.48146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 959.9189 | 33.283 | 22.972 | 0.00052 | -0.48146 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
126 | CMP_T0_L3_TL13815_Z731374_TT119 |  |  | San Diego, San Diego | Remediate CMP Issues in the Non-HFTD Zone | Transmission Line - Pole/Tower | Replace | Upgrade/Retrofit | NA | Asset Condition | Age/Condition | NA | NA | 2026-02-09 | 48 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 138 | NA | 1.1 | TL13815 Z731374 | QBL0098 | 1 | 20126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2015-06-09 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2020-04-21 | 2017-12-31 | 2020-08-23 | Permitting | Permitting | FALSE | 229.4765 | NA ¦ NA | 1585.2144 | 121.7024 | 77.7803 | 11.3399 | 0.56295 | -3.8024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 1499.3336 | 77.7803 | 11.3399 | 0.56295 | -3.8024 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
127 | TL23026 13815 Z189540 IN R3 |  |  | National City, San Diego | Remediate CMP Issues in the Non-HFTD Zone | Transmission Line - Other Equipment | Replace | NA | NA | Asset Condition | Age/Condition | NA | NA | 2026-02-05 | 18 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.1 | NA | 138¦230 | NA | 1.1 | 2019-4001 | QBL0098 | 1 | 20126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2018-10-01 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2020-10-08 | 2021-08-22 | 2021-04-08 | NA | NA | FALSE | 3804.368 | NA ¦ NA | 3472.4338 | 2840.4149 | 1.8014 | 0 | 0 | -4.4611 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2025 | 3475.0934 | 1.8014 | 0 | 0 | -4.4611 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 45.85% | 54.15% | [CPUC Status] Exempt
128 | CMP_T0_L2_TL652_Z214987X_15018 |  |  | San Diego, San Diego | Remediate CMP Issues in the Non-HFTD Zone | Transmission Line - Pole/Tower | Replace | Upgrade/Retrofit | NA | Asset Condition | Age/Condition | NA | NA | 2026-02-12 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.1 | NA | 69 | NA | 1.1 | TL652 Group 01 | QBL0098 | 1 | 20126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2018-10-23 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2020-12-31 | 2021-10-17 | 2021-05-17 | NA | NA | FALSE | 9.999 | NA ¦ NA | 1216.7988 | 495.9643 | 29.2382 | 104.0368 | 51.842 | -2.7445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 1034.4264 | 29.2382 | 104.0368 | 51.842 | -2.7445 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
129 | CMP_T0_L2_TL684_Z210594X_NON_TT |  |  | San Marcos, San Diego | TL684 Group 01- CMP- Non-TT (Pole Loading) | Transmission Line - Pole/Tower | Replace | NA | NA | Asset Condition | Age/Condition | NA | NA | 2026-02-19 | 46; 46; 34; 40; 40; 40 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.3 | NA | 69 | NA | 1.1 | TL684 Group 01 | QBL0098 | 1 | 20126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-09-27 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | False | NA | NA | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2021-03-01 | 2021-12-31 | 2020-12-13 | NA | NA | FALSE | 999.999 | NA ¦ NA | 1054.8276 | 427.1028 | 45.6275 | 30.9775 | 85.4049 | 22.5038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 870.3139 | 45.6275 | 30.9775 | 85.4049 | 22.5038 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
130 | CMP_T0_L2_TL684_Z114414X_NON_TT |  |  | San Marcos, San Diego | Remediate CMP Issues in the Non-HFTD Zone | Transmission Line - Pole/Tower | Replace | NA | NA | Asset Condition | Age/Condition | NA | NA | 2026-02-19 | 30 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.1 | NA | 69 | NA | 1.1 | TL684 Group 03 | QBL0098 | 1 | 20126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-09-27 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2021-01-15 | 2020-12-31 | 2021-06-28 | NA | NA | FALSE | 999.999 | NA ¦ NA | 1023.2157 | 611.2737 | 64.1403 | 25.0141 | 49.0023 | -0.51841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 885.5775 | 64.1403 | 25.0141 | 49.0023 | -0.51841 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
131 | CMP_T0_L2_TL684_Z815163X_NON_TT |  |  | San Marcos, San Diego | Remediate CMP Issues in the Non-HFTD Zone | Transmission Line - Pole/Tower | Replace | Replace | NA | Asset Condition | Age/Condition | NA | NA | 2026-02-19 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.1 | NA | 69 | NA | 1.1 | TL684 Group 05 | QBL0098 | 1 | 20126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-09-27 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2021-03-02 | 2020-12-31 | 2021-07-24 | Project Design | NA | FALSE | 999.999 | NA ¦ NA | 1320.7577 | 133.553 | -25.3601 | 704.0905 | 66.2854 | 5.8681 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 569.8737 | -25.3601 | 704.0905 | 66.2854 | 5.8681 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
132 | CMP_T0_L3_TL655/699_ STRUCTURES |  |  | San Diego, San Diego | Remediate CMP Issues in the Non-HFTD Zone | Transmission Line - Pole/Tower | Replace | Upgrade/Retrofit | NA | Asset Condition | Age/Condition | NA | NA | 2026-02-14 | 28 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.1 | NA | 69 | NA | 1.1 | 2022-2738 | QBL0098 | 1 | 20126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2015-02-11 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2023-11-06 | 2020-12-31 | 2026-01-28 | Permitting | Material | TRUE | 229.4765 | NA ¦ NA | 3664.6675 | 63.8882 | 374.4783 | 703.2602 | 351.7115 | 1567.9864 | 307.1683 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2026 | 0 | 0 | 0 | 0 | 0 | 3664.6675 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
133 | CMP_T0_L3_TL651_Z730387_TT13534 |  |  | San Diego, San Diego | Remediate CMP Issues in the Non-HFTD Zone | Transmission Line - Pole/Tower | Replace | Upgrade/Retrofit | NA | Field Test Results | Age/Condition | NA | NA | 2026-02-19 | 54 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.1 | NA | 69 | NA | 1.1 | TL651 Z730387 | QBL0098 | 1 | 20126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2018-01-31 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2021-04-09 | 2019-12-31 | 2023-05-21 | Permitting | Permitting | FALSE | 138.8568 | NA ¦ NA | 2794.3709 | 1419.8572 | 805.0292 | 30.8096 | 324.9223 | -0.95209 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 0 | 2439.591 | 30.8096 | 324.9223 | -0.95209 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
134 | CMP_T0_L2_TL608_Z371845X_NON_TT |  |  | Lemon Grove, San Diego | Remediate CMP Issues in the Non-HFTD Zone | Transmission Line - Pole/Tower | Replace | NA | NA | Asset Condition | Age/Condition | NA | NA | 2026-02-05 | 73 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.1 | NA | 69 | NA | 1.1 | TL608 Group 01 | QBL0098 | 1 | 20126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-08-13 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2022-06-17 | 2021-12-31 | 2023-04-24 | Project Design | Permitting | FALSE | 999.999 | NA ¦ NA | 1363.5644 | 82.5021 | 1006.9006 | 92.0874 | 195.0773 | 2.0123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2023 ¦ 2024 ¦ 2025 | 0 | 0 | 1166.4749 | 195.0773 | 2.0123 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
135 | CMP_T0_L2_TL617_2320469X_NON_TT |  |  | San Diego, San Diego | Remediate CMP Issues in the Non-HFTD Zone | Transmission Line - Pole/Tower | Replace | NA | NA | Asset Condition | Age/Condition | NA | NA | 2026-02-12 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.1 | NA | 69 | NA | 1.1 | TL617 Group 01 | QBL0098 | 1 | 20126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-09-27 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2021-11-25 | 2020-12-31 | 2022-04-10 | Project Design | Permitting | FALSE | 999.999 | NA ¦ NA | 1378.158 | 315.8678 | 464.5618 | 61.7387 | 114.9573 | -14.3525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 0 | 1215.8144 | 61.7387 | 114.9573 | -14.3525 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
136 | CMP_T0_L2_TL624_Z371343X_NON_TT |  |  | El Cajon, San Diego | Remediate CMP Issues in the Non-HFTD Zone | Transmission Line - Pole/Tower | Replace | Upgrade/Retrofit | NA | Asset Condition | Age/Condition | NA | NA | 2026-02-12 | 36 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.1 | NA | 69 | NA | 1.1 | TL624 Group 04 | QBL0098 | 1 | 20126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-10-11 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2022-03-26 | 2020-12-31 | 2022-12-10 | Permitting | Project Design | FALSE | 1128.8568 | NA ¦ NA | 1559.3189 | 212.0273 | 1071.6213 | 184.3504 | 10.6037 | -2.8983 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 0 | 418.6886 | 1132.9248 | 10.6037 | -2.8983 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
137 | CMP_T0_L2_TL603_Z183889X_14421 |  |  | National City, San Diego | Remediate CMP Issues in the Non-HFTD Zone | Transmission Line - Pole/Tower | Replace | Upgrade/Retrofit | NA | Asset Condition | Age/Condition | NA | NA | 2026-02-12 | 76 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.1 | NA | 69 | NA | 1.1 | TL603 Z1838893443 | QBL0098 | 1 | 20126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-12-12 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2023-01-10 | 2023-06-15 | 2026-05-26 | Permitting | Project Design | TRUE | 1314.2046 | NA ¦ NA | 3102.6969 | 567.0094 | 295.5462 | 707.1126 | 1191.9796 | 98.9842 | 4.6458 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2022 ¦ 2023 ¦ 2024 ¦ 2025 ¦ 2026 | 0 | 1094.8542 | 78.7618 | 1825.451 | 98.9842 | 4.6458 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
138 | CMP_T0_L2_TL681_Z12922,X_NON_TT |  |  | Escondido, San Diego | Remediate CMP Issues in the Non-HFTD Zone | Transmission Line - Pole/Tower | Replace | NA | NA | Asset Condition | Age/Condition | NA | NA | 2026-02-03 | 62; 62; 62; 46; 52; 43 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.1 | NA | 69 | NA | 1.1 | TL681 Group 03 | QBL0098 | 1 | 20126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-02-21 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2021-11-01 | 2021-01-09 | 2022-03-19 | Project Design | NA | FALSE | 999.999 | NA ¦ NA | 1022.5453 | 222.4498 | 670.626 | 111.0577 | 1.6852 | -0.2901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 0 | 910.0924 | 111.0577 | 1.6852 | -0.2901 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
139 | CMP_T0_LX_TL662 TL6905_COASTAL |  |  | San Diego, San Diego | Remediate CMP Issues in the Non-HFTD Zone | Transmission Line - Pole/Tower | Replace | NA | NA | Asset Condition | Age/Condition | NA | NA | 2026-02-03 | 34; 34; 34; 34; 34; 45; 34; 45 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | Coastal |  | 0.1 | NA | 69 | NA | 1.1 | 2023-3590 | QBL0098 | 1 | 20126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-11-15 | Work Order Authorization | 2024 | NA | FALSE | NA | NA | NA | FALSE | CEQA Final Published | TBD | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2024-08-12 | 2024-08-30 | 2025-03-09 | Construction Delays | Outage | FALSE | 513.5659 | NA ¦ NA | 1786.4633 | 0 | 0 | 3.5589 | 1292.1099 | 522.958 | -32.1635 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2025 ¦ 2026 | 0 | 0 | 0 | 0 | 1818.6268 | -32.1635 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
140 | CMP_T0_L3_TL13840_Z579784_11835 |  |  | San Diego, San Diego | Remediate CMP Issues in the Non-HFTD Zone | Transmission Line - Pole/Tower | Replace | Upgrade/Retrofit | NA | Asset Condition | Age/Condition | NA | NA | 2026-02-24 | 55 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | TBD |  | 0.1 | NA | 138 | NA | 1.1 | TL13840 Z579784 | QBL0098 | 1 | 20126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2017-05-03 | Work Order Authorization | 2019 | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2025-07-28 | 2018-12-31 | 2026-03-21 | Permitting | NA | TRUE | 80 | NA ¦ NA | 6404.361 | 17.2361 | 74.0575 | 147.9806 | 3329.3827 | 1270.6533 | 727.4619 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 ¦ 2026 | 17.2361 | 74.0575 | 147.9806 | 3329.3827 | 1270.6533 | 727.4619 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
141 | CMP_T0_L2_TL642_Z184518X_12827 |  |  | San Diego, San Diego | Remediate CMP Issues in the Non-HFTD Zone | Transmission Line - Pole/Tower | Replace | Upgrade/Retrofit | NA | Asset Condition | Age/Condition | NA | NA | 2026-02-12 | 50; 50 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | TBD |  | 0.32 | NA | 69 | NA | 1.1 | 2022-2728 | QBL0098 | 1 | 20126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2016-08-15 | Work Order Authorization | 2019 | NA | FALSE | NA | NA | NA | FALSE | TBD | TBD | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2022-05-25 | 2017-12-31 | 2024-08-03 | Permitting | Project Design | FALSE | 396.5096 | NA ¦ NA | 3409.6494 | 76.776 | 388.9158 | 528.5947 | 2077.9765 | -0.56642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2024 ¦ 2025 | 0 | 0 | 0 | 3410.2158 | -0.56642 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
142 | CMP_T0_L3_TL618/619_Z579013X_12 |  |  | San Diego, San Diego | Remediate CMP Issues | Transmission Line - Pole/Tower | Replace | Upgrade/Retrofit | NA | Asset Condition | Age/Condition | NA | NA | 2026-02-05 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 1 | NA | 69 | NA | 1.1 | 2024-3689 | QBL0098 | 1 | 20126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2025-06-24 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Construction (50%-75%) | NA | 2025-07-22 | 2018-12-31 | 2026-10-19 | Permitting | Multiple Options [See Notes] | TRUE | 179.998 | NA ¦ NA | 5426.8223 | 124.2953 | 179.7872 | 1712.4795 | 978.8069 | 741.8808 | 219.3716 | 16.447 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 ¦ 2026 | 79.6352 | 9.5287 | 1248.8687 | 3111.0903 | 741.0026 | 236.6968 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [Reason for Change in In-Service Date (2)] Access, Design, and Procurement. [CPUC Status] Exempt
143 | CMP_T0_LX_TL687_GROUP03_NONTT |  |  | Borrego Springs, San Diego | Remediate CMP Issues in the Non-HFTD Zone | Transmission Line - Pole/Tower | Replace | NA | NA | Asset Condition | Age/Condition | NA | NA | 2026-02-12 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 1.2 | NA | 69 | NA | 1.1 | 2023-3531 | QBL0098 | 1 | 20126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-09-25 | Work Order Authorization | 2024 | NA | FALSE | NA | NA | NA | False | CEQA Final Published | NA | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2024-08-19 | 2024-10-02 | 2024-11-21 | NA | NA | FALSE | 2159.3121 | NA ¦ NA | 1037.4602 | 0 | 0 | 72.539 | 1199.7895 | -234.8683 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2024 ¦ 2025 | 0 | 0 | 0 | 1272.3285 | -234.8683 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
144 | CMP_T0_LX_TL688 Z214887_TT15487 |  |  | Escondido, San Diego | Remediate CMP Issues in the Non-HFTD Zone | Transmission Line - Pole/Tower | Replace | NA | NA | Asset Condition | Age/Condition | NA | NA | 2026-01-22 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.2 | NA | 69 | NA | 1.1 | 2021-2354 | QBL0098 | 1 | 20126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2021-08-16 | Work Order Authorization | 2022 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2024-05-30 | 2021-12-31 | 2024-11-24 | Permitting | Project Design | FALSE | 361.0344 | NA ¦ NA | 2130.9502 | 14.9283 | 65.4007 | 372.4411 | 1340.3077 | 337.8724 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2024 ¦ 2025 | 0 | 0 | 0 | 1793.0778 | 337.8724 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
145 | CMP_T0_L2_664_Z96050_NON_TT |  |  | San Diego, San Diego | CMP_T0_Lx_TL664_Group03_NonTT | Transmission Line - Pole/Tower | Replace | NA | NA | Asset Condition | Age/Condition | NA | NA | 2026-01-06 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.3 | NA | 69 | NA | 1.1 | 2021-2545 | QBL0098 | 1 | 20126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2021-12-06 | Work Order Authorization | 2022 | NA | FALSE | NA | NA | NA | False | NA | NA | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2022-11-14 | 2023-02-14 | 2023-11-12 | Outage | Project Design | FALSE | 361.3033 | NA ¦ NA | 1101.3659 | 0 | 350.8379 | 512.586 | 142.1545 | 95.7875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2024 ¦ 2025 | 0 | 0 | 0 | 1005.5784 | 95.7875 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
146 | CMP_T0_L2_TL688 (99901)_Z214887 |  |  | Escondido, San Diego | Remediate CMP Issues in the Non-HFTD Zone | Transmission Line - Pole/Tower | Replace | NA | NA | Asset Condition | Age/Condition | NA | NA | 2026-01-22 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.1 | NA | 69 | NA | 1.1 | 2022-2639 | QBL0098 | 1 | 20126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-03-06 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | False | NA | NA | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2024-05-29 | 2021-12-31 | 2024-11-24 | Permitting | Material | FALSE | 80 | NA ¦ NA | 1126.1983 | 142.0736 | 289.7707 | 101.3229 | 351.3769 | 34.515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2024 ¦ 2025 | 0 | 0 | 0 | 1091.6833 | 34.515 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
147 | CMP_T0_L2_TL13834_Z128033_13605 |  |  | Laguna Niguel, Orange | Remediate CMP Issues in the Non-HFTD Zone | Transmission Line/Substation | Replace | NA | NA | Asset Condition | Age/Condition | NA | NA | 2026-01-06 | 29; 23; 52 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.2 | NA | 138 | NA | 1.1 | TL13834 Z128033 | QBL0098 | 1 | 20126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2018-03-11 | Work Order Authorization | 2019 | NA | FALSE | NA | NA | NA | False | NA | NA | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2023-07-19 | 2020-12-31 | 2024-10-02 | Permitting | Project Design | TRUE | 9.999 | NA ¦ NA | 1813.0336 | 132.2845 | 216.1809 | 63.9558 | 757.01 | 178.4386 | 108.5896 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2024 ¦ 2025 ¦ 2026 | 0 | 0 | 0 | 1526.0054 | 178.4386 | 108.5896 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
148 | [Programmatic] Transmission CMP HFTD |  |  | Multiple | Transmission CMP HFTD | Transmission Line - Pole/Tower | Replace | NA | NA | Asset Condition | Age/Condition | NA | NA | NA | NA | NA | NA | NA | Tier 2 ¦ Tier 3 | FALSE ¦ FALSE ¦ FALSE | FALSE | Individual Project Review Required |  | NA | NA | Multiple | NA | 1.1 | Multiple | QBL0092 | 394 | 20127 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-12-11 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | TBD | TBD | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | NA | NA | NA | NA | NA | TRUE | NA | NA ¦ NA | 213204.936 | 10747.9351 | 13177.0211 | 15499.088 | 11379.2252 | 11037.3042 | 1807.41 | 7643.0778 | 9974.6171 | 10434.4815 | 11026.651 | 10802.6753 | 4723.4878 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 ¦ 2026 | 10686.1059 | 11193.4569 | 16820.15 | 11242.4118 | 8982.3713 | 5306.348 | 0% | NA ¦ NA | 3.3 | NA | 45.85% | 54.15% | [CPUC Status] Exempt
149 | CMP_T3_L3_TL50003_Z123862X_1498 |  |  | San Diego, San Diego | Remediate CMP Issues | Transmission Line - Other Equipment | Replace | NA | NA | Asset Condition | Age/Condition - Insulator Replacement - Wood | NA | NA | 2025-07-05 | 10 | NA | NA | NA | Tier 3 | TRUE ¦ FALSE ¦ FALSE | FALSE | NA |  | 6 | NA | 500 | NA | 1.1 | TL50003 Group 01 | QBL0092 | 1 | 20127 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-12-05 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2021-08-30 | 2021-11-03 | 2021-12-18 | NA | NA | FALSE | 2255.5422 | NA ¦ NA | 1414.736 | 1215.4861 | 87.6968 | 111.5707 | 0 | -0.0176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2022 ¦ 2023 ¦ 2025 | 0 | 1303.183 | 111.5707 | 0 | -0.0176 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0% | [CPUC Status] Exempt
150 | CMP_T2_LX_TL99901_Z613913X |  |  | Hidden Meadows, San Diego | CMP_T2_Lx_TL99901_Z613913, Z613912, Z613915 Z613914_TT17191 TT17192 TT17198 TT17199 TT17200 CMP Pole Replacements | Transmission Line - Multiple | Replace | NA | NA | Safety | T-Line Reliability | NA | NA | 2026-01-06 | 54; 54; 54; 54 | NA | NA | NA | Tier 2 | FALSE ¦ FALSE ¦ FALSE | 0 | NA |  | 0.11 | NA | 69 | NA | 1.1 | 2918224 | QBL0092 | 1 | 20127 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-10-01 | Work Order Authorization | 2024 | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | CPUC | TBD | NA | NA | NA [See Notes] | NA | Operational | NA | 2025-06-03 | 2025-09-18 | 2025-10-17 | NA | NA | TRUE | 552.7332 | NA ¦ NA | 1125.9816 | 0 | 0 | 0 | 42.6109 | 1060.3753 | 22.9954 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2025 ¦ 2026 | 0 | 0 | 0 | 0 | 1102.9862 | 22.9954 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
151 | CMP_T0_L2_TL6908_ Z10637 Z11785 |  |  | Escondido, San Diego | TWO POLE REPLACEMENT, CMP job turned from the Fiber TL6908 Pass fail analysis, poles are overloaded and need to be replaced. This is a freeway crossing | Transmission Line - Multiple | Replace | Upgrade/Retrofit | NA | Safety | T-Line Reliability | NA | NA | 2026-01-06 | 51; 51; 77 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | 0 | NA |  | 0.1 | NA | 69 | NA | 1.1 | 2024-4064 | QBL0098 | 1 | 20127 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2021-02-25 | Work Order Authorization | 2021 | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | NA | NA | CPUC | TBD | NA | NA | NA [See Notes] | NA | Engineering more than 50% complete | NA | 2027-01-16 | 2025-05-23 | 2027-06-29 | Permitting | Scope Change | TRUE | 391.6005 | NA ¦ NA | 1044.1294 | 128.3808 | 645.5287 | 116.0782 | -155.8364 | 293.78 | 16.1981 | 0 | 0 | 0 | 0 | 0 | 16 | NA | NA | 2024 ¦ 2025 ¦ 2026 | 0 | 0 | 0 | 734.1513 | 293.78 | 16.1981 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
152 | CMP_T0_L2_TL13840_Z234863_15247 |  |  | San Diego, San Diego | CMP_T0_TL13840_Z234863_TT15247 Complete Wood Pole - Replacement Needed. Pole appears burn with possible hole between top guy and top bolt of top post. Recommend replacement | Transmission Line - Multiple | Replace | NA | na | Safety | T-Line Reliability | NA | NA | 2026-02-24 | 53; 53; 53 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | 0 | NA |  | 0.1 | NA | 138 | NA | 1.1 | TL13840_Z234863 | QBL0092 | 1 | 20127 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2021-06-03 | Work Order Authorization | 2021 | NA | FALSE | NA | NA | NA | FALSE | NA | exempt | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2022-03-19 | 2022-06-02 | 2026-03-21 | Scope Change | Permitting | TRUE | 223.8909 | NA ¦ NA | 1207.7959 | 86.2349 | 193.4879 | 55.3847 | 31.7385 | 546.0615 | 220.5413 | 74.347 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2026 | 0 | 0 | 0 | 0 | 0 | 1207.7959 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
153 | CMP_T0_L3_TL13834_Z29678_10182 |  |  | San Juan Capistrano, Orange | Remediate CMP Issues | Transmission Line - Pole/Tower | Replace | NA | NA | Asset Condition | Age/Condition | NA | NA | 2026-01-06 | 51 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.1 | NA | 138 | NA | 1.1 | TL13834 Z29678 | QBL0092 | 1 | 20127 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2014-09-10 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2022-10-03 | 2019-03-18 | 2023-06-11 | Permitting | NA | FALSE | 80 | NA ¦ NA | 1216.8018 | 104.0399 | 460.2218 | 365.1485 | 63.1036 | -21.3978 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2023 ¦ 2024 ¦ 2025 | 0 | 0 | 1175.096 | 63.1036 | -21.3978 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
154 | CMP_T0_L2_TL694_Z317855_10167 |  |  | Oceanside, San Diego | Remediate CMP Issues | Transmission Line - Pole/Tower | Replace | NA | NA | Asset Condition | Age/Condition | NA | NA | 2026-01-29 | 38 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.1 | NA | 69 | NA | 1.1 | TL694 Z317855 | QBL0092 | 1 | 20127 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2018-03-09 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2021-12-01 | 2020-12-31 | 2023-10-15 | Permitting | Land Rights | TRUE | 9.999 | NA ¦ NA | 1513.8721 | 125.2839 | 215.0283 | 753.0893 | 126.6958 | -3.9304 | 0.10273 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2023 ¦ 2024 ¦ 2025 ¦ 2026 | 0 | 0 | 1391.004 | 126.6958 | -3.9304 | 0.10273 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
155 | CMP_T2_L2_TL23010/02_Z223661_TT |  |  | San Diego, San Diego | Remediate CMP Issues in the HFTD Zone (Tier 2 & Tier 3) | Transmission Line - Conductor | Upgrade/Retrofit | NA | NA | Asset Condition | Age/Condition | NA | NA | 2026-01-29 | NA | NA | NA | NA | Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 0.3 | NA | 230 | NA | 1.1 | TL23002 Z223661 | QBL0092 | 1 | 20127 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-06-17 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2024-05-15 | 2020-12-31 | 2024-12-22 | Permitting | Multiple Options [See Notes] | TRUE | 999.999 | NA ¦ NA | 1807.6139 | 481.4532 | -246.0084 | 1041.3942 | 443.8809 | 71.1886 | 0.93787 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2023 ¦ 2024 ¦ 2025 ¦ 2026 | 0 | 0 | 1291.6065 | 443.8809 | 71.1886 | 0.93787 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0% | [Reason for Change in In-Service Date] Permitting, Design delays, Constructuability constraints. [Project Description - Action Taken] Wire remediation, gun shot damage in 3 spans. [CPUC Status] Exempt
156 | ET/OH&UG MISC CONST INST/RFS |  |  | Multiple | Remediate CMP Issues | Transmission Line - Pole/Tower | Replace | NA | NA | Asset Condition | Age/Condition | NA | NA | NA | NA | NA | NA | NA | Tier 2 ¦ Tier 3 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69 ¦500 | NA | 1.1 | TL627 Z971741, Z971739 | QBL0092 | 1 | 20127 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2025-01-01 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2020-10-16 | 2024-12-31 | 2020-10-16 | NA | NA | FALSE | 0 | NA ¦ NA | 7699.5732 | 398.5445 | 175.5652 | 453.7483 | 146.8314 | 6.8311 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 398.5445 | 175.5652 | 453.7483 | 146.8314 | 6.8311 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 45.85% | 54.15% | [CPUC Status] Exempt
157 | [Programmatic] Overhead System Traditional Hardening |  |  | Multiple | Program budget for overhead distribution system in fire prone areas including Hight Fire Thread District (HFTD) Tier 2, Tier 3, and Wildland Urban Interface that replaces wood pole with steel, bare conductor with new bare conductor, and other associated materials as necessary. In some cases the distribution lines are underbuilt on transmission structures or telecommunicatins equipment that require some amount of FERC spend. | Other | Replace | NA | NA | Wildfire Mitigation | Line Reconductoring | NA | NA | NA | NA | NA | NA | NA | Tier 2 ¦ Tier 3 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | NA | NA | Multiple | NA | 1.2 | Multiple | QBL0118 | 351 | 20284 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2021-01-21 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Construction (over 75%) | NA | Multiple | Multiple | Multiple | NA | NA | TRUE | NA | NA ¦ NA | 3293.7517 | 358.0998 | 133.5155 | 42.6517 | 52.4895 | 25.5977 | 9.8879 | 74.451 | 26.5564 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 ¦ 2026 | 924.6159 | 124.5997 | 50.8098 | 16.2163 | 29.2105 | 70.4385 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
158 | FIRE RISK MITIGATION(FIRM) CWIP |  |  | San Diego, San Diego | Program budget for overhead distribution system in fire prone areas including Hight Fire Thread District (HFTD) Tier 2, Tier 3, and Wildland Urban Interface that replaces wood pole with steel, bare conductor with new bare conductor, and other associated materials as necessary. In some cases the distribution lines are underbuilt on transmission structures or telecommunicatins equipment that require some amount of FERC spend. | Other | Replace | NA | NA | Wildfire Mitigation | Line Reconductoring | NA | NA | NA | NA | NA | NA | NA | Tier 2 ¦ Tier 3 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | NA | NA | Multiple | NA | 1.2 | NA | QBL0118 | 1 | 20284 | 2026-06-17 ¦ NA ¦ NA ¦ NA | TRUE | 2019-08-26 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Construction (over 75%) | NA | Multiple | Multiple | Multiple | NA | NA | FALSE | 24956.77 | NA ¦ NA | 3550.4199 | 1110.6252 | 824.0799 | 293.8148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2023 | 0 | 0 | 3550.4199 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
159 | [Programmatic] Overhead System Covered Conductor |  |  | Multiple | Program budget for overhead distribution system in fire prone areas including Hight Fire Thread District (HFTD) Tier 2, Tier 3, and Wildland Urban Interface that replaces wood pole with steel, bare conductor with new covered conductor, and other associated materials as necessary. In some cases the distribution lines are underbuilt on transmission structures or telecommunicatins equipment that require some amount of FERC spend. | Other | Replace | NA | NA | Wildfire Mitigation | Line Reconductoring | NA | NA | NA | NA | NA | NA | NA | Tier 2 ¦ Tier 3 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | NA | NA | Multiple | NA | 1.2 | Multiple | QBL0117 | 11 | 20285 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-12-16 | Work Order Authorization | 2021 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Construction (25%-50%) | NA | Multiple | Multiple | Multiple | NA | NA | TRUE | NA | NA ¦ NA | 4256.4512 | 26.183 | 140.9086 | 203.2484 | 124.4595 | 176.0549 | 43.4576 | 440.6756 | 611.8848 | 668.7156 | 723.1826 | 545.9341 | 52.5223 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 ¦ 2026 | 28.7601 | 134.7849 | 164.8418 | 139.6661 | 193.7368 | 9.8549 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
160 | FIRM COVERED CONDUCTOR CWIP |  |  | San Diego, San Diego | Program budget for overhead distribution system in fire prone areas including Hight Fire Thread District (HFTD) Tier 2, Tier 3, and Wildland Urban Interface that replaces wood pole with steel, bare conductor with new covered conductor, and other associated materials as necessary. In some cases the distribution lines are underbuilt on transmission structures or telecommunicatins equipment that require some amount of FERC spend. | Other | Replace | NA | NA | Wildfire Mitigation | Line Reconductoring | NA | NA | NA | NA | NA | NA | NA | Tier 2 ¦ Tier 3 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | NA | NA | Multiple | NA | 1.2 | NA | QBL0117 | 1 | 20285 | 2026-06-17 ¦ NA ¦ NA ¦ NA | TRUE | 2020-09-17 | Work Order Authorization | 2021 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Construction (25%-50%) | NA | Multiple | Multiple | Multiple | NA | NA | TRUE | 306.6309 | NA ¦ NA | 4289.0452 | 220.8903 | 515.3381 | 651.7329 | 1023.953 | 1346.9262 | 252.2748 | 269.9971 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2026 | 0 | 0 | 0 | 0 | 0 | 4289.0452 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
161 | [Programmatic] Drone Assessments |  |  | Multiple | The project was focused on flying and assessing all structures within the HFTD (Tier 2) with the purpose of mitigating any fire-related issues. | Other | Replace | NA | NA | Wildfire Mitigation | Fire Protection | NA | NA | NA | NA | NA | NA | NA | Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | Multiple | NA | 1.2 | Multiple | QBL0124 | 2 | 20286 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-12-17 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | NA | NA | NA | NA | NA | NA | To be Filed | NA | Operational | NA | NA | NA | NA | NA | NA | TRUE | NA | NA ¦ NA | 130.2111 | 49.4976 | 0.0020165 | 0.61774 | 2.2466 | 17.4388 | 0.15654 | 60.2518 | 0 | 0 | 0 | 0 | 6.5827 | NA | NA | 2022 ¦ 2023 ¦ 2024 ¦ 2025 ¦ 2026 | 0 | 49.4996 | 0.48685 | 2.2101 | 11.1801 | 66.8345 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
162 | DRONE INVESTIGATION ASSESSMENT |  |  | Multiple | Perform drone inspections for all of Tier 2 HFTD and higher risk WUI areas and complete follow-up repairs of any infractions identified. | Other | Replace | Replace | NA | Wildfire Mitigation | Age/Condition | NERC CIP Compliance | NERC CIP Compliance | NA | NA | NA | NA | NA | Tier 2 ¦ Tier 3 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | NA | NA | NA | NA | 1.2 | NA | QBL0124 | 1 | 20286 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-02-14 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | NA | 2023-12-31 | 2023-12-31 | NA | NA | FALSE | 818.022 | NA ¦ NA | 3269.0617 | 773.2967 | 1314.0803 | 843.8187 | -189.2602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2024 | 0 | 0 | 0 | 3269.0617 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] Exempt
163 | [Programmatic] Electric Distribution Tools & Equipment |  |  | NA | This blanket budget provides funding for new tools and equipment required by field personnel to inspect, operate and maintain the electric distribution system. | Other | Replace | NA | NA | Safety | Automation | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | Multiple | NA | 1.3 | Multiple | QB00028 | 10 | 206 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2025-01-24 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | NA | NA | To be Filed | NA | Operational | NA | NA | NA | NA | NA | NA | TRUE | NA | NA ¦ NA | 4509.7172 | 0.50352 | 0 | 0 | -0.0052359 | 0 | 28.6337 | 158.4142 | 375.6033 | 388.756 | 402.3613 | 412.4182 | 0 | NA | NA | 2021 ¦ 2024 ¦ 2026 | 40.0083 | 0 | 0 | -0.0052359 | 0 | 181.0889 | 0% | NA ¦ NA | 1.5 | NA | 0% | 100%
164 | INTERIM CAPITAL TOOLS C&O |  |  | NA | Provides the necessary tools and equipment to economically and safely inspect, operate and maintain the electric distribution facilities. Failure to replace outdated, old or worn-out tools will result in decreased crew productivity, increase accident frequency and increase system failure. | Other | Replace | Multiple Options [See Notes] | NA | Safety | 3rd Party Damage | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | Individual Project Review Required |  | NA | NA | NA | NA | 1.3 | NA | QB00028 | 1 | 206 | NA ¦ NA ¦ NA ¦ NA | TRUE | NA | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | NA | NA | NA | NA | NA | NA | To be Filed | NA | Operational | NA | NA | 2024-12-31 | Monthly | NA | NA | TRUE | 100 | NA ¦ NA | 3358.3887 | 547.5016 | 196.3277 | 171.4613 | 189.0856 | 97.3079 | 0.45241 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 ¦ 2026 | 547.5016 | 196.3277 | 171.4613 | 189.0856 | 97.3079 | 0.45241 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [Project Description - Action Taken (2)] The main purpose of the project is to improve safety so multiple options are taken.
165 | [Programmatic] ELEC TRANS SMALL RELIABILITY - HFTD |  |  | San Diego, San Diego | This budget code is all Electric Transmission projects under $4M, including shared equipment on the structures for both Transmission and Distribution. The funds are applied to the infrastructure to meet SDGE’s obligation to increase safety and reliability of the electric system. Budget includes proactive system upgrades and reactive projects that include poles, insulators, conductor and other electric infrastructure when reliability issues are identified in the HFTD. | Transmission Line - Multiple | Replace | Upgrade/Retrofit | NA | Reliability | T-Line Reliability | NA | NA | NA | NA | NA | NA | NA | Tier 2 ¦ Tier 3 | FALSE ¦ FALSE ¦ FALSE | FALSE | Individual Project Review Required |  | NA | NA | Multiple | NA | 1.2 | Multiple | QBL0125 | 122 | 21134 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-12-16 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | TBD | TBD | Exempted | NA | CPUC | NA | NA | NA | NA [See Notes] | NA | Operational | NA | NA | NA | NA | NA | NA | TRUE | NA | NA ¦ NA | 261610.8711 | 2648.1519 | 6622.3288 | 8440.6487 | 7898.7988 | 7554.3959 | 4842.0636 | 9620.7732 | 14853.7875 | 16360.9018 | 18293.2153 | 20420.5761 | 4142.8981 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 ¦ 2026 | 1938.3898 | 5624.7522 | 7030.5473 | 10095.8723 | 9173.928 | 2763.3724 | 0% | NA ¦ NA | 1.8 | NA | 0% | 100% | [CPUC Status] Transmission Reliability scope exempt from CPUC permitting requirements.
166 | REL_T2_TL678_Z104100_W2S |  |  | San Diego, San Diego | 3 poles in HFTD 2 to be replaced from wood to steel, and a total of 0.247 miles of existing 636 ACSS/AW to be reconductored. Structure #s: Z104100 636 ACSS/AW Z170670 636 ACSS/AW Z75086 636 ACSS/AW ​​ | Transmission Line - Pole/Tower | New | NA | NA | Reliability | Age/Condition - Replace Wood Poles | NA | NA | 2026-01-22 | 32; 37; 48; 55; 32; 55 | NA | NA | NA | Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 0.3 | NA | 69 | NA | 1.2 | 2020-0283 | QBL0125 | 1 | 21134 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-08-05 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2025-09-26 | 2024-12-30 | 2026-03-15 | Prioritization | Other[See Notes] | TRUE | 1746.2787 | NA ¦ NA | 1819.811 | 331.3782 | 234.8051 | 274.5971 | 495.1763 | 216.313 | 158.8737 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 ¦ 2026 | 331.3782 | 234.8051 | 274.5971 | 495.1763 | 216.313 | 158.8737 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [Reason for Change in In-Service Date (2)] CPUC budget constraint [CPUC Status] The scope of this project is exempt from CPUC
167 | REL_WUI_TL690_Z323626_GROUP01 |  |  | Oceanside, San Diego | REL_T0_Lx_TL690_Z323626_Group01_NonTT Z323623, Z323622, Z323620, Z323619, Z323618 Pole Replacement | Transmission Line - Pole/Tower | New | NA | NA | Reliability | Age/Condition - Replace Wood Poles | NA | NA | 2026-01-11 | 45 | NA | NA | NA | NA | FALSE ¦ TRUE ¦ FALSE | 0 | NA |  | 0.2 | NA | 69 | NA | 1.2 | 2021-2501 | QBL0125 | 1 | 21134 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2022-09-27 | Work Order Authorization | 2022 | NA | FALSE | NA | NA | NA | FALSE | NA | Exempt | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2025-04-07 | 2025-05-30 | 2025-05-30 | NA | NA | TRUE | 2099.0464 | NA ¦ NA | 1888.4318 | 0 | 24.7298 | 212.6651 | 362.6494 | 1285.2155 | 3.172 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2024 ¦ 2025 ¦ 2026 | 0 | 0 | 0 | 523.1553 | 1362.1045 | 3.172 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] The scope of this project is exempt from CPUC permitting.
168 | W2S_T2_TL6917_4 STRUCTURES |  |  | Camp Pendleton, San Diego | 6 poles in HFTD 2 to be replaced from wood to steel, and a total of 0.416 miles of existing 1/0 CU B.S. & 394.5 5005 AL to be reconductored. Structure #s: Z21282 1/0 CU B.S. Z22190 394.5 5005 AL Z22191 394.5 5005 AL Z22192 394.5 5005 AL Z22193 394.5 5005 AL Z22194 394.5 5005 AL ​​ | Transmission Line - Pole/Tower | Replace | NA | NA | Reliability | Age/Condition - Replace Wood Poles | NA | NA | 2026-01-22 | 30; 30; 70; 30; 20 | NA | NA | NA | Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 0.42 | NA | 69 | NA | 1.2 | 2020-0285 | QBL0125 | 1 | 21134 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-08-05 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2023-12-11 | 2024-12-30 | 2023-12-16 | NA | NA | FALSE | 2013.332 | NA ¦ NA | 1582.4686 | 198.2888 | 243.3452 | 1004.9807 | -18.9952 | 75.7595 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2024 ¦ 2025 | 0 | 0 | 0 | 1506.7091 | 75.7595 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
169 | REL_TL621_Z118874 W2S |  |  | San Diego, San Diego | 2 Poles in HFTD 2 to be replaced from wood to steel, and a total of 0.0356 miles (188’) of existing 1033.5 ACSR/AW. Structure #: Z118874 1033.5 ACSR/AW Dead-End | Transmission Line - Pole/Tower | New | NA | NA | Reliability | Age/Condition - Replace Wood Poles | NA | NA | 2026-01-11 | 21 | NA | NA | NA | Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 0.1 | NA | 69 | NA | 1.2 | 2021-0382 | QBL0125 | 1 | 21134 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2021-04-07 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Construction (10%-25%) | NA | 2026-03-24 | 2025-12-31 | 2026-08-15 | Prioritization | Other[See Notes] | TRUE | 546.3001 | NA ¦ NA | 1731.6734 | 50.6354 | 186.6723 | 668.7086 | 753.344 | 60.7111 | 11.6019 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2022 ¦ 2023 ¦ 2024 ¦ 2025 ¦ 2026 | 0 | 9.1051 | 34.7216 | 1414.8728 | 261.372 | 11.6019 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [Reason for Change in In-Service Date (2)] CPUC budget constraint [CPUC Status] Exempt
170 | REL_TL632_Z118872_W2S |  |  | San Diego, San Diego | 1 Pole in HFTD to be replaced from wood to steel | Transmission Line - Pole/Tower | Replace | NA | NA | Reliability | Age/Condition - Replace Wood Poles | NA | NA | 2026-01-27 | 21 | NA | NA | NA | Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | TBD |  | 0.1 | NA | 69 | NA | 1.2 | 2021-0387 | QBL0125 | 1 | 21134 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2021-04-07 | Work Order Authorization | 2022 | NA | FALSE | NA | NA | NA | FALSE | TBD | TBD | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Construction (10%-25%) | NA | 2026-03-24 | 2025-12-31 | 2026-08-15 | Prioritization | Other[See Notes] | TRUE | 546.149 | NA ¦ NA | 1426.861 | 41.7975 | 172.7752 | 472.0808 | 617.9386 | 111.6649 | 10.6039 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2023 ¦ 2024 ¦ 2025 ¦ 2026 | 0 | 0 | 34.0326 | 1270.5596 | 111.6649 | 10.6039 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [Reason for Change in In-Service Date (2)] CPUC budget constraint [CPUC Status] Exempt
171 | REL_TL6924 W2S 3 STRUCTURES |  |  | San Diego, San Diego | 4 Poles in HFTD 2 to be replaced from wood to steel, and a total of 0.1591 miles of existing 900 ACSS/AW. | Substation - Multiple | Replace | New | NA | Reliability | 3rd Party Damage | NERC CIP Compliance | NERC CIP Compliance | 2026-01-15 | NA | NA | NA | NA | Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.3 | NA | 69 | NA | 1.2 | 2021-0388 | QBL0125 | 1 | 21134 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2021-04-07 | Work Order Authorization | 2021 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | CPUC | Dept of Navy discretionary action not anticipated | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2023-12-04 | 2025-03-24 | 2023-12-16 | NA | Weather | FALSE | 685.7119 | NA ¦ NA | 1053.7671 | 106.6484 | 239.9213 | 492.6213 | 204.0273 | 10.5487 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2023 ¦ 2024 ¦ 2025 | 0 | 0 | 839.1911 | 204.0273 | 10.5487 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
172 | REL_WUI_TL6970_GRP01_Z89852 |  |  | Bonita, San Diego | REL_T0_Lx_TL6970_Group01_Z89852_Z89850_Z132487_NonTT 3 Risk and Asset Management (RAM) structures identified for pole change out | Transmission Line - Pole/Tower | New | NA | NA | Reliability | Age/Condition - Replace Wood Poles | NA | NA | 2026-02-05 | NA | NA | NA | NA | NA | FALSE ¦ TRUE ¦ FALSE | 0 | NA |  | 0.1 | NA | 69 | NA | 1.2 | 2022-3186 | QBL0125 | 1 | 21134 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-01-04 | Work Order Authorization | 2023 | NA | FALSE | NA | NA | NA | FALSE | NA | Exempt | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2025-07-16 | 2025-10-28 | 2025-10-28 | NA | NA | TRUE | 1519.7013 | NA ¦ NA | 1061.6878 | 0 | 0 | 229.0513 | 177.4549 | 639.0134 | 16.1682 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2025 ¦ 2026 | 0 | 0 | 0 | 0 | 1045.5196 | 16.1682 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Scope of this project is exempt from CPUC permitting.
173 | W2S_T2_TL684_3 STRUCTURES |  |  | San Marcos, San Diego | 3 poles in HFTD 2 to be replaced from wood to steel, and a total of 0.405 miles of existing 1033.5 ACSR/AW to be reconductored. | Substation - Multiple | New | New | NA | Reliability | 3rd Party Damage | NERC CIP Compliance | NERC CIP Compliance | 2026-02-19 | 25 | NA | NA | NA | Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.4 | NA | 69 | NA | 1.2 | 2020-0284 | QBL0125 | 1 | 21134 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-08-07 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2024-05-06 | 2025-08-22 | 2025-01-30 | NA | NA | FALSE | 1740.62 | NA ¦ NA | 1895.8163 | 147.0336 | 162.1242 | 238.9549 | 347.7033 | 914.5664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2025 | 0 | 0 | 0 | 0 | 1895.8163 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
174 | REL_TL634 _Z11815_Z11816_W2S |  |  | Poway, San Diego | REL_TL634 _Z11815_Z11816 Two wood poles to be changed out to steel. OH and UG Transmission. Poles not adjacent. | Transmission Line - Pole/Tower | New | NA | NA | Reliability | Age/Condition - Replace Wood Poles | NA | NA | 2026-03-16 | NA | NA | NA | NA | Tier 2 | FALSE ¦ TRUE ¦ FALSE | 0 | NA |  | 0.1 | NA | 69 | NA | 1.2 | 2021-0385 | QBL0125 | 1 | 21134 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2021-04-29 | Work Order Authorization | 2021 | NA | FALSE | NA | NA | NA | FALSE | NA | Exempt | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2025-02-19 | 2025-06-29 | 2025-06-29 | NA | NA | TRUE | 721.4201 | NA ¦ NA | 1784.2962 | 110.2924 | 187.2635 | 501.3581 | 168.5762 | 792.2179 | 24.5881 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2023 ¦ 2024 ¦ 2025 ¦ 2026 | 0 | 0 | 11.2335 | 956.2567 | 792.2179 | 24.5881 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] This project is exempt from CPUC permitting.
175 | REL_TL6935_ W2S 3 STRUCTURES |  |  | San Marcos, San Diego | REL_T2_TL6935 Z118746, Z118747, Z118748 3 Wood pole to be changed to steel | Transmission Line - Pole/Tower | New | NA | NA | Reliability | Age/Condition - Replace Wood Poles | NA | NA | 2026-01-13 | 22 | NA | NA | NA | Tier 2 | FALSE ¦ TRUE ¦ FALSE | 0 | NA |  | 0.4 | NA | 69 | NA | 1.2 | 2021-0391 | QBL0125 | 1 | 21134 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2021-04-07 | Work Order Authorization | 2021 | NA | FALSE | NA | NA | NA | FALSE | NA | Stat Exe | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2025-07-28 | 2025-06-24 | 2025-06-24 | NA | NA | TRUE | 1054.0783 | NA ¦ NA | 1627.1486 | 110.1683 | 155.0727 | 364.8879 | 103.6419 | 891.5977 | 1.7801 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2025 ¦ 2026 | 0 | 0 | 0 | 0 | 1625.3684 | 1.7801 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] This project is exempt from CPUC permitting.
176 | [Programmatic] ELEC TRANS SMALL RELIABILITY – non HFTD |  |  | Multiple | This budget code is all Electric Transmission projects under $2M, including shared equipment on the structures for both Transmission and Distribution. The funds are applied to the infrastructure to meet SDGE’s obligation to increase safety and reliability of the electric system. Budget includes proactive system upgrades and reactive projects that include poles, insulators, conductor and other electric infrastructure when reliability issues are identified in the non-HFTD. | Transmission Line - Multiple | Upgrade/Retrofit | Upgrade/Retrofit | NA | Reliability | T-Line Reliability | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | NA | NA | 4.1 | Multiple | QBL0126 | 176 | 21135 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-12-16 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | NA | NA | NA [See Notes] | NA | Operational | NA | NA | NA | NA | NA | NA | TRUE | NA | NA ¦ NA | 300871.2015 | 2579.9499 | 6280.8302 | 11486.1927 | 13088.0654 | 13348.3028 | 3088.5202 | 17146.8391 | 15898.0308 | 17749.8699 | 19708.2602 | 21911.6251 | 14939.8821 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 ¦ 2026 | 2250.2353 | 2080.6793 | 6928.5365 | 14561.5121 | 9111.0158 | 6538.7361 | 0% | NA ¦ NA | 5.1 | NA | 0% | 0%
177 | 5 RELIABILITY (NON CMP) POLES |  |  | Vista, San Diego | TL680B-Z218305, Z218306, Z218309, Z218301, Z115895. | Transmission Line - Pole/Tower | Replace | NA | 2988970 | Reliability | Age/Condition - Replace Wood Poles | NA | NA | 2026-01-13 | 50.7 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.5 | NA | 69 | NA | 4.1 | TL680B Group-Fndtn | QBL0126 | 1 | 21135 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-03-15 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2018-12-05 | 2022-12-31 | 2019-02-17 | NA | NA | FALSE | 2762.0811 | NA ¦ NA | 3364.3662 | 1324.7403 | 481.3731 | -324.3732 | 65.5999 | -2.0924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 249.97 | 3038.3338 | -324.3732 | 65.5999 | -2.0924 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
178 | REL_TL612_TL604_Z279897 |  |  | San Diego, San Diego | FTD to be replaced from wood to steel | Transmission Line - Pole/Tower | New | NA | NA | Reliability | Age/Condition - Wood Pole Reframe | NA | NA | 2026-02-14 | 22 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | TBD |  | 0.1 | NA | 69 | NA | 4.1 | 2021-0406 | QBL0126 | 1 | 21135 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2022-08-02 | Work Order Authorization | 2023 | NA | FALSE | NA | NA | NA | FALSE | TBD | TBD | Exempted | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Engineering more than 50% complete | NA | 2026-10-27 | 2023-12-31 | 2026-12-11 | Prioritization | Other[See Notes] | FALSE | 2143.4324 | NA ¦ NA | 1048.9782 | 0 | 20.4055 | 479.0869 | 278.9653 | 149.195 | -33.5471 | 61.5857 | 88.7629 | 4.5241 | 0 | 0 | 894.1056 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [Reason for Change in In-Service Date (2)] CPUC budget constraint [CPUC Status] Exempt
179 | REL_T0_TL615_Z730769 |  |  | San Diego, San Diego | The purpose of the TL615 REL Project is to replace structures Z730769, Z730764, Z730774, from wood to steel. Replacing existing Z730769 with a new 70’-H3 Galvanized SW pole • Replacing existing Z730764 with a new 70’-H3 Galvanized SW pole • Replacing existing Z730774 with a new 75’-H3 Galvanized SW pole • Replacing existing Z730770 with a new 80’-H3 Galvanized SW pole • Replacing existing pole top configuration on Z730773 with current standard. • Retaining Wall Scope: o Remove a portion of the existing masonry retaining wall, concrete foundation, and sidewalk at (2) locations o Install new concrete masonry retaining wall and concrete foundation set back from existing wall at (2) locations | Transmission Line - Pole/Tower | New | Upgrade/Retrofit | NA | Reliability | Age/Condition | NERC CIP Compliance | NERC CIP Compliance | 2026-01-29 | 57; 57; 57; 58 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | TBD |  | 0.32 | NA | 69 | NA | 4.1 | 2021-2501 | QBL0126 | 1 | 21135 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2021-11-19 | Work Order Authorization | 2022 | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | CPUC | NA | NA | NA | To be Filed | NA | Operational | NA | 2024-05-22 | 2024-02-04 | 2025-04-04 | Prioritization | Other[See Notes] | FALSE | 1101.2271 | NA ¦ NA | 1233.3637 | 12.7453 | 144.7113 | 203.6647 | 155.6819 | 716.5604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2023 ¦ 2024 ¦ 2025 | 0 | 0 | 361.1213 | 155.6819 | 716.5604 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [Reason for Change in In-Service Date (2)] Budget constraints
180 | [Programmatic] TRANSMISSION CONSTRUCTION & MAINT |  |  | Multiple | Transmission jobs in the HFTD to comply with SDG&Es obligation to serve and meet safety requirements. Most of the activities that fall under this blanket budget are necessary to comply with Federal, State, and Local regulations. Activities include poles that need to be replaced due to reaching life expectancy, capital repairs related to inspections (visual, infrared, LiDAR, etc.), and emergency situations. This work is scheduled and managed by Transmission, Construction & Maintenance. | Transmission Line - Multiple | New | Replace | NA | Safety | Age/Condition | NA | NA | NA | NA | NA | NA | NA | Tier 2 ¦ Tier 3 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | NA | NA | Multiple | NA | 1.1 | Multiple | QBL0127 | 424 | 21136 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-12-16 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | NA | NA | NA [See Notes] | NA | Operational | NA | NA | NA | NA | NA | NA | TRUE | NA | NA ¦ NA | 113959.0136 | 887.1519 | 1638.4009 | 3392.394 | 4010.892 | 3469.6818 | 1276.0408 | 5275.4929 | 6989.268 | 7160.3497 | 7973.1314 | 8867.5666 | 3267.5156 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 ¦ 2026 | 1263.927 | 748.7844 | 2830.8089 | 3867.0768 | 2696.4486 | 2569.3075 | 0% | NA ¦ NA | 1.3 | NA | 45.85% | 54.15% | [CPUC Status] Blanket budget - multiple projects under this budget
181 | 2022 CIVIL ENG CAPITAL PROJECTS |  |  | San Diego, San Diego | The purpose of this work is mandatory Environmental Site restoration. | Other - Civil | Upgrade/Retrofit | NA | NA | Safety | Construct Roads/Gates/Culverts | NA | NA | 2026-02-14 | 29 | NA | NA | NA | Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | NA | NA | 1.1 | 2022-3126 | QBL0127 | 1 | 21136 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2022-11-17 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2021-02-03 | NA | 2023-06-11 | NA | NA | FALSE | 1606.935 | NA ¦ NA | 1712.5269 | 0 | 1535.07 | 197.8079 | -20.2609 | -0.0901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2024 ¦ 2025 | 0 | 0 | 0 | 1712.617 | -0.0901 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] Exempt
182 | [Programmatic] HATS |  |  | San Diego, San Diego | The Helicopter Access for Transmission Structures (HATS) program will facilitate ongoing compliance and safe and efficient operations and maintenance of the transmission system by addressing helicopter access constraints. It involves installation of two types of helicopter landing facilities at various locations along Company’s transmission system. One type is a Tower Staging Access Pad (TSAP) which is a level, bare ground area cleared and maintained of vegetation used for intermittent landing of Company or authorized contractor helicopters. The other type is an engineered structural steel helicopter landing platform (Platform or HLP) used for intermittent landing of Company or authorized contractor helicopters. These facilities are generally located in steep, rugged and mountainous terrain and are necessary due to lack of available roads for vehicle access and will assist in the safe and efficient maintenance and operation of electric transmission facilities. | Other | Upgrade/Retrofit | NA | NA | Safety | Safety - Line Right of Way Access | NA | NA | NA | NA | NA | NA | NA | Tier 1 ¦ Tier 2 ¦ Tier 3 ¦ Zone 1 | FALSE ¦ FALSE ¦ TRUE | FALSE | NA |  | NA | NA | Multiple | NA | 1.3 | Multiple | QBL0130 | 0 | 21146 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2025-04-12 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | Multiple | Muliple | Multiple | NA | NA | FALSE | NA | NA ¦ NA | 179674.1976 | 0 | 0 | 0 | 0 | 0 | 0 | -5.0932e-11 | 0 | 14371.1665 | 21248.7962 | 21992.5086 | 0 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | 25.8 | NA | 45.85% | 54.15% | [Wildfire Related] HATS program has a secondary benefit of wildfire response capabilities [CPUC Status] Exempt
183 | HATS WORK RELEASE 6 |  |  | Multiple | The Helicopter Access for Transmission Structures (HATS) program will facilitate ongoing compliance and safe and efficient operations and maintenance of the transmission system by addressing helicopter access constraints. It involves installation of two types of helicopter landing facilities at various locations along Company’s transmission system. One type is a Tower Staging Access Pad (TSAP) which is a level, bare ground area cleared and maintained of vegetation used for intermittent landing of Company or authorized contractor helicopters. The other type is an engineered structural steel helicopter landing platform (Platform or HLP) used for intermittent landing of Company or authorized contractor helicopters. These facilities are generally located in steep, rugged and mountainous terrain and are necessary due to lack of available roads for vehicle access and will assist in the safe and efficient maintenance and operation of electric transmission facilities. | Other | Upgrade/Retrofit | NA | NA | Safety | Safety - Line Right of Way Access | NA | NA | NA | NA | NA | NA | NA | TBD | FALSE ¦ FALSE ¦ TRUE | 0 | Individual Project/Easement Review Required |  | NA | NA | 69 ¦ 230 ¦ 500 | NA | 1.3 | NA | QBL0130 | 1 | 21146 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2025-09-30 | Work Order Authorization | 2025 | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | NA | NA | TBD | TBD | Exempt | NA | NA [See Notes] | NA | Planning | NA | TBD | 2028-12-31 | TBD | NA | NA | TRUE | 2002.669 | NA ¦ NA | 21477.2799 | 0 | 0 | 0 | 0 | 7.4009 | 131.3795 | 1172.9142 | 14006.5138 | 6159.0714 | 0 | 0 | 138.7805 | NA | NA | 2026 | 0 | 0 | 0 | 0 | 0 | 1311.6947 | 0% | NA ¦ NA | NA ¦ NA | NA | 45.85% | 54.15% | [Wildfire Related] HATS program has a secondary benefit of wildfire response capabilities; CPUC Fire Threat Zone is noted as TBD since locations for work release 6 are still being scoped. [CPUC Status] Exempt
184 | HATS WORK RELEASE 3 |  |  | San Diego, San Diego | The Helicopter Access for Transmission Structures (HATS) program will facilitate ongoing compliance and safe and efficient operations and maintenance of the transmission system by addressing helicopter access constraints. It involves installation of two types of helicopter landing facilities at various locations along Company’s transmission system. One type is a Tower Staging Access Pad (TSAP) which is a level, bare ground area cleared and maintained of vegetation used for intermittent landing of Company or authorized contractor helicopters. The other type is an engineered structural steel helicopter landing platform (Platform or HLP) used for intermittent landing of Company or authorized contractor helicopters. These facilities are generally located in steep, rugged and mountainous terrain and are necessary due to lack of available roads for vehicle access and will assist in the safe and efficient maintenance and operation of electric transmission facilities. | Other | New | NA | NA | Safety | Safety - Line Right of Way Access | NA | NA | NA | NA | NA | NA | NA | Tier 2 ¦ Tier 3 | FALSE ¦ FALSE ¦ TRUE | FALSE | NA |  | NA | NA | 230 ¦ 500 | NA | 1.3 | 2022-2623 | QBL0130 | 1 | 21146 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2021-10-23 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2023-07-31 | 2023-12-31 | 2024-05-07 | NA | NA | TRUE | 12044.5322 | NA ¦ NA | 14611.6785 | 0 | 336.5763 | 12184.1401 | 2078.2014 | 11.1003 | 1.6603 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2024 ¦ 2025 ¦ 2026 | 0 | 0 | 0 | 14598.9178 | 11.1003 | 1.6603 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0% | [Wildfire Related] HATS program has a secondary benefit of wildfire response capabilities [CPUC Status] Exempt
185 | HATS WORK RELEASE 2 |  |  | San Diego, San Diego | The Helicopter Access for Transmission Structures (HATS) program will facilitate ongoing compliance and safe and efficient operations and maintenance of the transmission system by addressing helicopter access constraints. It involves installation of two types of helicopter landing facilities at various locations along Company’s transmission system. One type is a Tower Staging Access Pad (TSAP) which is a level, bare ground area cleared and maintained of vegetation used for intermittent landing of Company or authorized contractor helicopters. The other type is an engineered structural steel helicopter landing platform (Platform or HLP) used for intermittent landing of Company or authorized contractor helicopters. These facilities are generally located in steep, rugged and mountainous terrain and are necessary due to lack of available roads for vehicle access and will assist in the safe and efficient maintenance and operation of electric transmission facilities. | Other | New | NA | NA | Safety | Safety - Line Right of Way Access | NA | NA | NA | NA | NA | NA | NA | Tier 2 ¦ Tier 3 | FALSE ¦ FALSE ¦ TRUE | FALSE | NA |  | NA | NA | 230 ¦ 500 | NA | 1.3 | 2022-2622 | QBL0130 | 1 | 21146 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2021-09-08 | Work Order Authorization | 2021 | 2021 | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2021-01-22 | 2021-12-31 | 2022-09-27 | Weather | NA | FALSE | 13068.4013 | NA ¦ NA | 20474.768 | 11684.9933 | 8457.9153 | 215.5547 | 117.4167 | -1.112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 11684.9933 | 8457.9153 | 215.5547 | 117.4167 | -1.112 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0% | [Wildfire Related] HATS program has a secondary benefit of wildfire response capabilities [CPUC Status] Exempt
186 | HATS Release 4 |  |  | San Diego, San Diego | The Helicopter Access for Transmission Structures (HATS) program will facilitate ongoing compliance and safe and efficient operations and maintenance of the transmission system by addressing helicopter access constraints. It involves installation of two types of helicopter landing facilities at various locations along Company’s transmission system. One type is a Tower Staging Access Pad (TSAP) which is a level, bare ground area cleared and maintained of vegetation used for intermittent landing of Company or authorized contractor helicopters. The other type is an engineered structural steel helicopter landing platform (Platform or HLP) used for intermittent landing of Company or authorized contractor helicopters. These facilities are generally located in steep, rugged and mountainous terrain and are necessary due to lack of available roads for vehicle access and will assist in the safe and efficient maintenance and operation of electric transmission facilities. | Other | New | Upgrade/Retrofit | NA | Safety | Safety - Line Right of Way Access | NA | NA | NA | NA | NA | NA | NA | Tier 2 ¦ Tier 3 | FALSE ¦ FALSE ¦ TRUE | FALSE | NA |  | NA | NA | 230 ¦ 500 | NA | 1.3 | 2024-3824 | QBL0130 | 1 | 21146 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-08-15 | Work Order Authorization | 2024 | 2024 | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2024-10-21 | 2024-12-31 | 2025-08-16 | Weather | Land Rights | TRUE | 1126.3555 | NA ¦ NA | 29362.4744 | 0 | 0 | 35.6888 | 6278.6164 | 23010.8928 | 37.2764 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2025 ¦ 2026 | 0 | 0 | 0 | 0 | 29325.198 | 37.2764 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0% | [Wildfire Related] HATS program has a secondary benefit of wildfire response capabilities [CPUC Status] Exempt
187 | HATS Release 5 |  |  | San Diego, San Diego | The Helicopter Access for Transmission Structures (HATS) program will facilitate ongoing compliance and safe and efficient operations and maintenance of the transmission system by addressing helicopter access constraints. It involves installation of two types of helicopter landing facilities at various locations along Company’s transmission system. One type is a Tower Staging Access Pad (TSAP) which is a level, bare ground area cleared and maintained of vegetation used for intermittent landing of Company or authorized contractor helicopters. The other type is an engineered structural steel helicopter landing platform (Platform or HLP) used for intermittent landing of Company or authorized contractor helicopters. These facilities are generally located in steep, rugged and mountainous terrain and are necessary due to lack of available roads for vehicle access and will assist in the safe and efficient maintenance and operation of electric transmission facilities. | Other | New | Upgrade/Retrofit | NA | Safety | Safety - Line Right of Way Access | NA | NA | NA | NA | NA | NA | NA | Tier 2 ¦ Tier 3 | FALSE ¦ FALSE ¦ TRUE | FALSE | TBD |  | NA | NA | 69 ¦ 230 ¦ 500 | NA | 1.3 | 2025-4253 | QBL0130 | 1 | 21146 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-08-06 | Work Order Authorization | 2025 | NA | FALSE | NA | NA | NA | FALSE | TBD | TBD | Exempted | NA | CPUC | CNF, BLM | Exempt | NA | NA [See Notes] | NA | Construction (under 10%) | NA | 2026-06-02 | 2027-03-12 | 2026-12-10 | NA | NA | FALSE | 769.7092 | NA ¦ NA | 64072.4147 | 0 | 0 | 0 | 19.1756 | 939.7014 | 291.2788 | 16423.8552 | 5779.7703 | 18566.9368 | 0 | 0 | 1250.1558 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 45.85% | 54.15% | [Wildfire Related] HATS program has a secondary benefit of wildfire response capabilities [CPUC Status] Exempt
188 | [Programmatic] TCM Non-HFTD |  |  | Multiple | Transmission jobs in the non-HFTD to comply with SDG&Es obligation to serve and meet safety requirements set by General Orders 95,128, and other regulations. Budget provides resources to provide support to reactive issues that arise such as storm, fire and pole car contact. The majority of the activities that fall under this blanket budget are necessary to comply with Federal, State , and Local regulations. Activities include poles that need to be replaced due to deterioration, capital repairs related to inspections (visual, infrared, LiDAR, etc.), and emergency situations. This work is scheduled and managed by Transmission, Construction & Maintenance. | Transmission Line - Multiple | Upgrade/Retrofit | NA | NA | Safety | Construct Roads/Gates/Culverts | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | Multiple | NA | 1.1 | Multiple | QBL0135 | 536 | 21150 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-12-16 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | NA | NA | NA [See Notes] | NA | Operational | NA | NA | NA | NA | NA | NA | TRUE | NA | NA ¦ NA | 97980.3802 | 1089.7304 | 800.338 | 2420.8718 | 6750.8275 | 4472.3296 | 792.7293 | 5047.8389 | 5357.6265 | 5830.9181 | 6488.415 | 7214.74 | 1893.7455 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 ¦ 2026 | 1657.1346 | 716.1609 | 1184.3818 | 7640.1828 | 3235.221 | 2160.1975 | 0% | NA ¦ NA | 2.1 | NA | 45.85% | 54.15% | [CPUC Status] Blanket budget - multiple projects under this budget
189 | TL676 Z96677 NEW ACCESS RD AND |  |  | San Diego, San Diego | Mobilize, Clear and Grub Pad, Place BMPs Rough Grade, Over Excavate and Compact Pad, Place 9" of Class 2 base, Over excavate and compact Access Rd, Place 9" of class 2 base on road, Form and construct wall footings and CMU wall, Waterproof and Backfill Wall, Construct Brow and Wall ditch, Construct Cross Gutter, Install Rip-rap Dissipater with Filter Fabric, Construct Type D Brow ditch, install Cable railing at CMU wall. Demobilize. | Other - Civil | Upgrade/Retrofit | NA | NA | Safety | Construct Roads/Gates/Culverts | NA | NA | 2026-02-12 | 50 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69 | NA | 1.1 | 2023-3244 | QBL0135 | 1 | 21150 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-01-13 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | CPUC | TBD | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2023-02-06 | NA | 2023-07-12 | NA | NA | FALSE | 1421.7099 | NA ¦ NA | 1307.1541 | 0 | 0 | 1303.151 | 4.8774 | -0.87436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2023 ¦ 2024 ¦ 2025 | 0 | 0 | 1303.151 | 4.8774 | -0.87436 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
190 | ET/OH CORRECTIVE MAINT PROGRAM |  |  | Multiple | Transmission jobs in the Non-HFTD to comply with SDG&Es obligation to serve and meet safety requirements. Most of the activities that fall under this blanket budget are necessary to comply with Federal, State, and Local regulations. Activities include poles that need to be replaced due to reaching life expectancy, capital repairs related to inspections (visual, infrared, LiDAR, etc.), and emergency situations. This work is scheduled and managed by Transmission, Construction & Maintenance. | Transmission Line - Multiple | Upgrade/Retrofit | Replace | NA | Safety | Age/Condition | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | Multiple | NA | 1.1 | Multiple | QBL0135 | 1 | 21150 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2025-01-01 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | NA | NA | NA [See Notes] | NA | Operational | NA | 2022-04-15 | NA | Multiple | NA | NA | FALSE | 0 | NA ¦ NA | 13759.2103 | 6268.6902 | 1463.9724 | 68.5797 | 0.06983 | -68.759 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 6268.6902 | 1463.9724 | 68.5797 | 0.06983 | -68.759 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 45.85% | 54.15% | [CPUC Status] Blanket budget - multiple projects under this budget [Utility Unique ID #1(Most Specific)] 2022-3131 , 2022-2726 , 2022-3133
191 | TL23012 Z710036 BRIDGE CROSSING |  |  | San Diego, San Diego | Installing a new bridge to allow SDG&E vehicles to cross over drainage. | Transmission Line - Right of Way | Upgrade/Retrofit | New | NA | Safety | Construct Roads/Gates/Culverts | NA | NA | 2026-02-12 | 53 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | TBD |  | 0.41 | NA | 230 | NA | 1.1 | 2022-3123 | QBL0135 | 1 | 21150 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2022-11-08 | Work Order Authorization | 2023 | NA | FALSE | NA | NA | NA | FALSE | TBD | TBD | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2025-01-20 | NA | 2025-05-02 | NA | NA | FALSE | 670.3235 | NA ¦ NA | 1774.9381 | 0 | 7.519 | 75.4535 | 168.9869 | 1522.9788 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2025 | 0 | 0 | 0 | 0 | 1774.9381 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0% | [CPUC Status] Exempt
192 | [Programmatic] Generation Interconnection Projects |  |  | Multiple | This is a blanket authorization for a multitude of CAISO mandated projects. CAISO approval for these projects is made in the form of a Three Party Interconnection Agreement. SDG&E has historically undertaken work for many of these types of projects to enhance and maintain reliability of the transmission grid. These projects are typically Battery Energy Storage (BESS) or other renewable projects from external parties where infrastructure is created in order to connect to SDG&Es grid through genties connecting to one of the companys many existing 69kV and above substations. Typical scope of these projects include the construction of Interconnection Facilities (ICF) which are 100% customer funded as well as Reliability Network Upgrades (RNUs) will be charged to ratepayers. | Multiple Options [See Notes] | NA | NA | NA | Generator Interconnection | Generation Interconnection | CAISO Requirement | NA | NA | NA | NA | Other - Status Quo | NA | Tier 1 ¦ Tier 2 ¦ Tier 3 | FALSE ¦ FALSE ¦ FALSE | FALSE | Individual Project Review Required |  | NA | NA | 69 ¦ 500 | 69kV - 500kV | 2.1 | Multiple | QBL0141 | 132 | 21156 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-12-09 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | TRUE | NA | NA | NA | NA | TBD | TBD | Exempt | NA | NA [See Notes] | NA | Planning | NA | NA | NA | Multiple | NA | NA | TRUE | NA | Based on per MW for Reliability Network Upgrades (RNU)¦ CAISO GIDAP | 50749.6934 | 5110.2225 | 288.374 | -3186.0935 | 2582.1711 | -4360.5536 | -16.1656 | 14038.5033 | 1782.1403 | 6827.9875 | 51.3395 | 347.6987 | 994.9454 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 ¦ 2026 | 4861.7289 | 1236.0261 | -4348.0554 | -1506.5488 | 886.4986 | 225.0006 | 0% | NA ¦ NA | 3.63 | NA | 45.85% | 54.15% | [Project Description - What] Project scope and description varies for projects; Permitting and CEQA responsibility of 3rd party interconnection customers (not SDG&E); status varies by project [CPUC Status] Exempt [Cost Cap ($000)] Cost Cap is calculated based on Commercial Operation Date (COD). Latest rate released by CAISO for period ending 6/30/2025 is $96K/MW output. Projects with COD in later years are calculated at an assumed escalated rate utilizing an inflation factor of 1.1248 per year (provided by CAISO)
193 | Q1171 MCFARLAND SOLAR |  |  | Imperial County | This order is for the payable amount due to Arizona Public Service (APS) due to shared ownership of the Network Upgrades at Hoodoo Wash 500kV Switchyard related to the McFarland Solar Interconnection project (CAISO Q1171/APS Q227). | Substation - Multiple | New | Upgrade/Retrofit | NA | Generator Interconnection | Generator Interconnection | CAISO Requirement | NA | NA | NA | NA | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 500 | 500kV | 2.1 | NA | QBL0141 | 1 | 21156 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2025-08-28 | Work Order Authorization | 2025 | NA | FALSE | NA | NA | NA | TRUE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | NA | NA | NA | Other [See Notes] | NA | FALSE | 10030.1416 | $48,000 ¦ CAISO GIDAP | 10563.1807 | 0 | 0 | 0 | 0 | 10563.1807 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2025 | 0 | 0 | 0 | 0 | 10563.1807 | 0 | 76.22% ¦ APS | 100.00% ¦ $10,563 | NA ¦ NA | NA | 100% | 0% | [Wildfire Related] The project is not located in California so it doesn't have a CPUC Fire Threat Zone designation [CPUC Status] Exempt [Reason for Change in In-Service Date] Project date fields are shown as NA due to project and scheduled being managed by APS
194 | Q1657 Sandpiper Energy Storage |  |  | Orange County | Sandpiper Energy Storage, LLC, an Interconnection Customer (IC), submitted a completed Interconnection Request (IR) to the California Independent System Operator Corporation (CAISO) to interconnect Sandpiper Storage (Project) to the CAISO Controlled Grid. The Project is a battery energy storage system (BESS) generating facility with a requested net output of 200 MW at the Point of Interconnection (POI). The IC requested that the POI for the Project be at Talega 138 kV substation. | Substation - Multiple | Upgrade/Retrofit | NA | NA | Generator Interconnection | Generation Interconnection | CAISO Requirement | NA | 2025-10-21 | NA | NA | NA | NA | Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 6.92 | 138 | 138kV | 2.1 | 2021-2433 | QBL0141 | 1 | 21156 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2021-10-27 | Work Order Authorization | 2021 | NA | FALSE | NA | NA | NA | TRUE | NA | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Canceled | NA | 2024-10-07 | 2023-03-31 | NA | Customer Action | NA | FALSE | 629.0521 | NA ¦ NA | 1018.9669 | 8.5397 | 330.3811 | 791.9919 | 1070.3444 | -1357.8484 | 322.8333 | -142.3153 | -4.9597 | 0 | 0 | 0 | 1166.2419 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0.00% ¦ $0 | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Project is withdrawn from CAISO queue [Reason for Change in In-Service Date] SDG&E received customer cancellation notice on 5/13/2026 [Current Projected Total or Actual Final Cost ($000)] The noted value is from financial data pull that was generated prior to notification from customer that the project will be canceled. Projected total cost will net to zero in future TPR submission once the financials systems are updated.
195 | Q1673 NIGHTHAWK ENERGY STORAGE |  |  | San Diego, San Diego | The Nighthawk Storage Project is a 300 MW battery energy storage system. The scope of this project will be to install applicable equipment and Reliability Network Upgrades (RNUs) at Sycamore Canyon Substation to the ISO grid. The project will connect to the PTO’s transmission system via the project’s 138kV gentie emanating from SDG&E's Sycamore Canyon Substation. | Substation - Multiple | New | Upgrade/Retrofit | NA | Generator Interconnection | Generator Interconnection | CAISO Requirement | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | Work complete |  | NA | 10.79 | 138 | 138kV | 2.1 | 2021-2393 | QBL0141 | 1 | 21156 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2021-10-25 | Work Order Authorization | 2021 | NA | FALSE | NA | NA | NA | TRUE | NA | Exempt | Exempted | NA | CPUC | Dept. of Navy - Discretionary Action not anticipated | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2023-11-01 | 2023-03-31 | 2026-02-27 | Customer Action | NA | TRUE | 636.9917 | $32,423 ¦ CAISO GIDAP | 1128.2715 | 9.6794 | 177.8479 | 753.1513 | 902.5662 | -669.715 | 35.4886 | -80.7469 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2026 | 0 | 0 | 0 | 0 | 0 | 1128.2715 | 0% | 100.00% ¦ $1,187 | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
196 | Q1532 KETTLE SOLAR ONE |  |  | San Diego, San Diego | Generation interconnection project; interconnection customer responsible for design, procurement, and construction of new 138kV Carrizo Gorge switchyard and 138 kV loop in; SDG&E will purchase these high voltage assets from the interconnection customer; SDG&E providing design and construction oversight | Substation - Multiple | New | NA | NA | Generator Interconnection | New Substation | CAISO Requirement | NA | 2026-01-06 | 33 | NA | NA | NA | Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | SDGE work is exempt |  | NA | 1.94 | 138 | 138kV | 2.1 | 2019-0227 | QBL0141 | 1 | 21156 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2018-11-29 | Work Order Authorization | 2019 | NA | FALSE | NA | NA | NA | TRUE | NA | EIR | NA | NA | County of San Diego | NA | 851 | TBD | To be Filed | TBD | Construction (25%-50%) | NA | 2025-10-06 | 2022-10-01 | 2027-05-14 | Customer Action | NA | TRUE | 9681 | $11,751 ¦ CAISO GIDAP | 11750.9955 | 158.2769 | 423.928 | 202.6255 | 285.6264 | 665.8809 | 221.2325 | 3726.8463 | 5938.4176 | 0 | 0 | 0 | 1957.5703 | NA | NA | 2026 | 0 | 0 | 0 | 0 | 0 | 5812.5779 | 0% | 100.00% ¦ $11,751 | NA ¦ NA | NA | 0% | 100%
197 | Q1429 MOUNT LAGUNA WIND 2 |  |  | San Diego, San Diego | Boulder Brush, LLC Q1429 is a 400MW Generation Facility that requires a new 500kV swithcyard between Suncrest-Ocotillo 500kV line located on the Campo Indian Reservation in Mountain Empire in San Diego County, CA. | Substation - Multiple | New | NA | NA | Generator Interconnection | New Substation | CAISO Requirement | NA | 2026-05-16 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | Project is Canceled |  | 0.38 | NA | 500 | 500kV | 2.1 | 2018-3004 | QBL0141 | 1 | 21156 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2018-09-05 | Work Order Authorization | 2024 | NA | FALSE | NA | NA | NA | TRUE | NA | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Canceled | NA | NA | 2029-06-29 | NA | Customer Action | NA | FALSE | 4013.44 | NA ¦ NA | 76696.7361 | 26.4104 | 36.2602 | 18.0665 | -7.7302 | 6.5632 | 0.62224 | 0 | 0 | 0 | 0 | 13479.804 | 80.1925 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0.00% ¦ $0 | NA ¦ NA | NA | 100% | 0% | [CPUC Status] Project is withdrawn from CAISO queue [Reason for Change in In-Service Date] Project withdrawn from CAISO Queue on 6/19/2026 [Current Projected Total or Actual Final Cost ($000)] The noted value is from financial data pull that was generated prior to notification from customer that the project will be canceled. Projected total cost will net to zero in future TPR submission once the financials systems are updated.
198 | Q1670 PEREGRINE |  |  | San Diego, San Diego | The Project is a 200 MW battery energy storage system (“BESS”). The Point of Interconnection is at the 230 kV bus of PTO’s existing Silvergate Substation. Point of Change of Ownership (“POCO”) is located where the IC’s 230 kV generation tie line (“gen-tie”) crosses the vertical plane of the PTO’s property line surrounding the Silvergate Substation. The IC’s Interconnection Facilities include 230 kV underground cable and conduit package from the POCO to the Project’s substation. | Substation - Multiple | Upgrade/Retrofit | NA | NA | Generator Interconnection | Generation Interconnection | CAISO Requirement | NA | 2026-05-22 | 3 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | TBD |  | NA | NA | 230 | 230kV | 2.1 | 2021-2091 | QBL0141 | 1 | 21156 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2021-04-28 | Work Order Authorization | 2022 | NA | FALSE | NA | NA | NA | TRUE | NA | NA | NA | NA | CPUC | NA | 851 [4401-E] | 2024-03-01 | Approved | 2024 | Operational | NA | 2024-03-11 | 2022-09-30 | 2025-01-03 | Customer Action | NA | TRUE | 359.7892 | $21,615¦ CAISO GIDAP | 1457.9313 | 73.8802 | 504.359 | 913.3779 | 1960.9864 | -2069.4722 | 74.7999 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2025 ¦ 2026 | 0 | 0 | 0 | 0 | 1383.1314 | 74.7999 | 0% | 100.00% ¦ $1,458 | NA ¦ NA | NA | 100% | 0%
199 | Q1810 EAST FIELD ENERGY CNTR |  |  | San Diego, San Diego | The project will connect to the PTOs transmission system via the Projects 230kV gen-tie emanation from the Otay Mesa substation. | Substation - Multiple | Upgrade/Retrofit | NA | NA | Generator Interconnection | Generation Interconnection | CAISO Requirement | NA | 2026-05-27 | NA | NA | NA | NA | Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | TBD |  | NA | 32.81 | 230 | 230kV | 2.1 | 2024-3985 | QBL0141 | 1 | 21156 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-05-02 | Work Order Authorization | 2024 | NA | FALSE | NA | NA | NA | TRUE | TBD | NA | NA | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | On Hold | NA | NA | 2027-08-20 | 2030-03-25 | Customer Action | NA | FALSE | 4897 | $58,367¦ CAISO GIDAP | 4749.4568 | 0 | 0 | 0 | 52.5932 | 106.5939 | 16.6373 | 12.0588 | 17.3802 | 244.4338 | 1626.3906 | 2673.369 | 175.8243 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100.00% ¦ $4,749 | NA ¦ NA | NA | 100% | 0% | [CPUC Status] Exempt
200 | Q2166 UMBRIEL |  |  | Imperial County | New 500kV Switchyard supporting 1150 MW solar PV | Substation - Multiple | New | NA | NA | Generator Interconnection | New Substation | CAISO Requirement | NA | 2026-06-01 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 2.0 | 19.38 | 500 | 500kV | 2.1 | 2023-3247 | QBL0141 | 1 | 21156 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-06-08 | Work Order Authorization | 2024 | NA | FALSE | NA | NA | NA | TRUE | CEQA Draft Published | NA | Exempted | NA | CPUC | BLM | AL | TBD | To be Filed | TBD | Engineering less than 50% complete | NA | 2031-06-30 | 2028-12-15 | 2034-01-27 | Customer Action | NA | FALSE | 4493.2716 | $177,000 ¦ CAISO GIDAP | 115493.2126 | 0 | 0 | 40.205 | 341.4856 | 918.0075 | 132.5746 | 1262.5244 | 4018.7589 | 4392.0134 | 5124.0462 | 5318.3535 | 1432.2727 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100.00% ¦ $115,493 | NA ¦ NA | NA | 100% | 0%
201 | Q1806 Captiva Energy Storage |  |  | San Juan Capistrano, CA | New 138kV Switchyard to support 250MW BESS | Substation - Multiple | New | NA | NA | Generator Interconnection | New Substation | CAISO Requirement | NA | NA | NA | NA | NA | NA | Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 1.0 | 3.06 | 138 | 138kV | 2.1 | 2021-2462 | QBL0141 | 1 | 21156 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2021-09-03 | Work Order Authorization | 2023 | NA | FALSE | NA | NA | NA | TRUE | NA | NA | Exempted | NA | TBD | NA | Exempt | NA | NA [See Notes] | NA | Engineering more than 50% complete | NA | 2024-05-16 | 2025-05-20 | 2028-01-31 | Customer Action | NA | FALSE | 48.0858 | $27,500 ¦ CAISO | 26231.7302 | 19.7099 | 146.5325 | 297.1727 | 339.751 | 60.1833 | 150.1418 | 385.9301 | 2373.8042 | 22458.5048 | 0 | 0 | 1013.4911 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100.00% ¦ $26,232 | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
202 | Q1665 Kingsley Solar |  |  | Imperial County | 135 MW (Phase 1) and 225 MW (Phase 2) solar PV and battery energy storage system (BESS) with POI at Imperial Valley Substation 230kV bus | Substation - Multiple | New | New | NA | Generator Interconnection | Generation Interconnection | CAISO Requirement | NA | 2026-06-01 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | TBD |  | NA | 55.48 | 230 | 230kV | 2.1 | 2025-4218 | QBL0141 | 1 | 21156 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-12-06 | Work Order Authorization | 2025 | NA | FALSE | NA | NA | NA | TRUE | TBD | TBD | Exempted | NA | TBD | BLM | TBD | TBD | Other [See Notes] | TBD | Engineering less than 50% complete | NA | 2026-05-04 | 2029-10-05 | 2030-01-03 | NA | NA | FALSE | 2488.0003 | $62,271 ¦ CAISO | 3684.7912 | 0 | 0 | 0 | 0 | 35.3947 | 43.4303 | 236.0088 | 526.0907 | 1494.3676 | 1349.4991 | 0 | 78.825 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100.00% ¦ $3,685 | NA ¦ NA | NA | 100% | 0% | [CPUC Status] TBD
203 | [Programmatic] Transmission Power Quality |  |  | Multiple | This project will deploy Power Quality Meters in SDG&E electric substations on transmission circuits to enable the collection of time-series analog data used to detect incipient failures of electrical equipment and locate that failing equipment before it can cause significant damage. | Substation - Multiple | Relocate | NA | NA | Reliability | Replace Other Substation Equipment | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | Multiple | 373MVA | 4.3 | Multiple | QBL0157 | 9 | 22126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-12-11 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | NA | NA | NA | NA | NA | TRUE | NA | NA ¦ NA | 4574.8485 | 33.6898 | 491.093 | 866.1993 | 531.5391 | 1037.5971 | 219.0079 | 469.7998 | 665.4665 | 133.7335 | 0 | 0 | 1645.2429 | NA | NA | 2021 ¦ 2023 ¦ 2024 ¦ 2025 ¦ 2026 | 0.023536 | 0 | 664.4589 | 615.9295 | 253.4713 | 1480.3399 | 0% | NA ¦ NA | 26.1 | NA | 45.85% | 54.15% | [CPUC Status] Exempt
204 | [Programmatic] Early Fault Detection |  |  | Multiple | This project will deploy Power Quality Meters and advanced Radio Frequency (RF) Sensors in SDG&E electric substations and electric distribution circuits within the High Fire Threat District to enable the collection of time-series analog data used to detect incipient failures of electrical equipment and locate that failing equipment before it can cause significant damage. The program will also fund various analytical / software tools utilized to aggregate this highly sampled data, analyze it and use it to triangulate the failure locations so crews may be dispatched to proactively inspect / investigate with a goal of preventing significant damage. | Substation - Multiple | New | NA | NA | Wildfire Mitigation | Automation | NA | NA | NA | NA | NA | NA | NA | Tier 2 ¦ Tier 3 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | NA | NA | NA | NA | 1.2 | Multiple | QBL0148 | 3 | 22256 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-12-11 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | NA | NA | NA | NA | NA | FALSE | NA | NA ¦ NA | 194.1203 | 0 | 0 | 0 | 194.1129 | 0.0073828 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2024 ¦ 2025 | 0 | 0 | 0 | 194.1129 | 0.0073828 | 0 | 0% | NA ¦ NA | 7.3 | NA | 0% | 0% | [CPUC Status] Exempt
205 | EFD WMP IPREDICT |  |  | San Diego, San Diego | Internal development of iPredict software platform | Other - Operations Tech | New | NA | NA | Wildfire Mitigation | Automation | NA | NA | NA | NA | NA | NA | NA | Tier 2 ¦ Tier 3 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | NA | NA | NA | NA | 1.2 | NA | QBL0148 | 1 | 22256 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2022-10-31 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | NA | 2026-12-31 | 2025-04-24 | NA | NA | FALSE | 26582.4918 | NA ¦ NA | 2562.1009 | 0 | 1224.6787 | 1043.8824 | 291.2447 | 2.2951 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2025 | 0 | 0 | 0 | 0 | 2562.1009 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] Exempt
206 | [Programmatic] CNF PLRP PROJ MGMT/PMO |  |  | Multiple | The scope for this project includes post-construction habitat restoration that is required by project permits for temporarily impacted mitigatable vegetation communities. This includes restoration implementation (weed control and seeding), supplemental seeding, monitoring and maintenance, reporting, and agency meetings/site visits. | Other | NA | NA | NA | Location, Environmental Conditions | Environmental | NA | NA | NA | NA | NA | NA | NA | Tier 2 ¦ Tier 3 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | NA | NA | 2.2 | NA | QBL0159 | 1 | 23128 | 2026-06-17 ¦ Multiple ¦ NA ¦ NA | TRUE | 2023-12-15 | Work Order Authorization | 2024 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | Multiple | Muliple | Multiple | NA | NA | FALSE | 271.3179 | NA ¦ NA | 1185.7562 | 0 | 0 | 0 | 60.3979 | 58.9423 | 22.1474 | 398.0698 | 197.6892 | 216.0501 | 232.4596 | 0 | 141.4876 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 45.85% | 54.15% | [CPUC Status] Exempt
207 | [Programmatic] Substation External Routable Connectivity (SERC) |  |  | Multiple | The SERC program deploys secure routable protocol connections providing event retrieval, password management and remote secure event access to all CIP Medium, Low and No Impact substations. It achieves this by deploying Advanced Relay Event Retrieval (ARER) hardware, Siemens Crossbow devices, and deployment of systems in support thereof. The program also analyses and tests emerging ERC technology use cases and solutions. | Substation - Other Equipment | New | NA | NA | Reliability | System Operations | NA | NA | NA | NA | NA | NA | NA | Multiple | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | Multiple | 373MVA | 4.3 | Multiple | QBL0160 | 49 | 23129 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-12-11 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Engineering less than 50% complete | NA | NA | NA | NA | NA | NA | TRUE | 3560 | NA ¦ NA | 67294.121 | 0 | 0 | 1.9057 | 1423.4601 | 3173.0579 | 1214.7071 | 2386.4263 | 4079.812 | 4589.2981 | 5148.7415 | 5726.32 | 4158.3119 | NA | NA | 2024 ¦ 2025 ¦ 2026 | 0 | 0 | 0 | 521.5564 | 1133.2624 | 5161.0041 | 0% | NA ¦ NA | 3.4 | NA | 45.85% | 54.15% | [CPUC Status] Exempt
208 | [Programmatic] Customer Relocation Projects |  |  | Multiple | Blanket budget code for internally funded customer relocation projects. | Transmission Line - Multiple | Upgrade/Retrofit | NA | NA | Work Requested by Others | Facility Relocation | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | Multiple | Multiple | 3.1 | Multiple | QBL0166 | 2 | 23130 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-12-13 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | Multiple | Muliple | Multiple | NA | NA | TRUE | NA | NA ¦ NA | 358.5877 | 32.0058 | 126.7428 | 105.877 | 37.4745 | 50.7664 | 5.6189 | 0.1022 | 0 | 0 | 0 | 0 | 7.1411 | NA | NA | 2025 ¦ 2026 | 0 | 0 | 0 | 0 | 351.3445 | 7.2433 | 0% | NA ¦ NA | 6.2 | NA | 0% | 100% | [CPUC Status] Exempt
209 | TL651 BOUNDARY ST RELOCATION |  |  | San Diego, San Diego | Internally-funded relocation project to replace three (3) transmission poles with 69 kV/4 kV/Communication and install approximately 800 ft. of new transmission and distribution conductor. Relocate Z730600 away from an eroding drainage bank. Replace structures adjacent to HWY-15 (Z730600 and Z2034273419) with self-supporting steel structures. Replace Z730598 with a direct-bury steel pole. | Transmission Line - Multiple | Replace | New | NA | Work Requested by Others | Facility Relocation | NA | NA | 2026-02-19 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.44 | NA | 69 | NA | 3.1 | 2017-0118 | QBL0166 | 1 | 23130 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2022-08-01 | Work Order Authorization | 2021 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Engineering more than 50% complete | NA | 2026-08-19 | 2026-12-15 | 2026-11-04 | NA | NA | TRUE | 4358.261 | NA ¦ NA | 2871.5893 | 0 | 14.9572 | 150.9451 | 251.7517 | 727.2077 | 654.9179 | 1071.8097 | 0 | 0 | 0 | 0 | 1799.7796 | NA | NA | 2026 | 0 | 0 | 0 | 0 | 0 | 2871.5893 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
210 | TL683 COLE GRADE ROAD |  |  | Valley Center, San Diego | The TL683 Cole Grade Road Project is a part of the Customer Relocation Program. This project is located along Cole Grade Road near the intersection of Hilldale Road in Valley Center, CA. The County has requested two transmission structures on the west side of the road and any associated stub poles on the east side of the road from their current franchise position to be relocated due to the road widening. | Substation - Multiple | New | Replace | NA | Work Requested by Others | Facility Relocation | NA | NA | 2026-02-03 | NA | NA | NA | NA | Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.1 | NA | 69 | NA | 3.1 | 2016-0001-A | QBL0166 | 1 | 23130 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2021-09-30 | Work Order Authorization | 2021 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | CPUC | NA | AL [4081-E] | 2022-09-23 | Approved | 2022 | Operational | NA | 2025-04-14 | 2025-05-09 | 2025-05-23 | NA | NA | TRUE | 2870.5547 | NA ¦ NA | 1756.8908 | 59.709 | 178.4254 | 294.2508 | 199.1644 | 958.513 | 66.8283 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2025 ¦ 2026 | 0 | 0 | 0 | 0 | 1690.0625 | 66.8283 | 0% | 100.00% ¦ $1,757 | NA ¦ NA | NA | 0% | 100%
211 | TL634 JUNIPER ST CRP |  |  | Escondido, San Diego | The City of Escondido has provided SDGE with plans for the Safe Routes to School Juniper Street Improvements PROJECT which will require approximately seven (7) SDGE structures to be relocated or modified due to the improvements. The project is located along Juniper Street near Idaho Avenue and Felicita Avenue. SDGE (AI Conde) performed a conflict check for the City of Escondido and identified the following structures may result in potential conflicts: Z16648, P516576, Z16649, P513748, Z16643, P512805, and Z16644. | Transmission Line - Multiple | New | New | NA | Work Requested by Others | Facility Relocation | NA | NA | 2026-03-16 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.3 | NA | 69 | NA | 3.1 | 2021-2096 | QBL0166 | 1 | 23130 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2021-08-30 | Work Order Authorization | 2021 | NA | FALSE | NA | NA | NA | FALSE | PEA Deemed Complete | NA | Exempted | NA | TBD | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2024-04-30 | 2024-11-26 | 2024-11-26 | NA | NA | TRUE | 2359.0354 | NA ¦ NA | 1518.5339 | 14.6157 | 203.4255 | 301.4164 | 724.0287 | 270.0606 | 2.9786 | 2.0084 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2025 ¦ 2026 | 0 | 0 | 0 | 0 | 1513.5469 | 4.987 | 0% | 100.00% ¦ $1,519 | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
212 | [Programmatic] Transmission Failing Cable Replacement |  |  | San Diego, San Diego | Replace underground cable systems targeting hand taped splices exhibiting degradation leading to failure. | Transmission Line - Underground | New | NA | NA | Reliability | Age/Condition | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 23 | NA | 69 | NA | 4.1 | Multiple | QBL0171 | 0 | 24129 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-12-16 | Work Order Authorization | 2024 | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Construction (25%-50%) | NA | NA | NA | NA | NA | NA | FALSE | 31289.7138 | NA ¦ NA | 36249.3728 | 0 | 0 | 0 | 0 | 0 | 1344.4825 | 12601.0982 | 22303.7922 | 0 | 0 | 0 | 1344.4825 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | 37.4 | NA | 0% | 100% | [CPUC Status] Exempt
213 | UG TRANS CABLE REPL: 2024 SCOPE |  |  | San Diego, San Diego | Replace underground cable systems targeting hand taped splices exhibiting degradation leading to failure. | Transmission Line - Underground | New | NA | NA | Reliability | Age/Condition - Replace Underground System | NA | NA | 2026-02-03 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 3 | NA | 69 | NA | 4.1 | Multiple | QBL0171 | 1 | 24129 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-06-04 | Work Order Authorization | 2024 | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2024-10-01 | 2024-12-31 | 2024-12-31 | NA | NA | TRUE | 134697.3219 | NA ¦ NA | 67875.1956 | 0 | 0 | 0 | 23601.4129 | 40048.5395 | 4225.2432 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2025 ¦ 2026 | 0 | 0 | 0 | 0 | 63649.9524 | 4225.2432 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt [Utility Unique ID #1(Most Specific)] 2025-4236, 2025-4410, 2024-3828
214 | Golden Pacific Powerlink (GPP) Project |  |  | Multiple | New CAISO-approved 500kV transmission line connecting IV Substation to a new Substation north of SONGS near border of San Diego and Orange County. | Transmission Line - Pole/Tower | New | NA | NA | Policy | New T-Line | CAISO Requirement | CAISO Requirement | NA | NA | NA | Wires - New T-Line Alternative | Over $500 Mil | TBD | FALSE ¦ FALSE ¦ FALSE | FALSE | TBD |  | ~150 | NA | 500 | NA | 2.1 | 2025-4735 | QS00794 | 1 | 25150 | NA ¦ NA ¦ NA ¦ NA | FALSE | 2025-09-03 | Work Order Authorization | 2025 | 2022-2023 | TRUE | 2022 ¦ 2023 | 2022 ¦ 2023 | https://stakeholdercenter.caiso.com/InitiativeDocuments/ISO-Board-Approved-2022-2023-Transmission-Plan.pdf | FALSE | TBD | TBD | EIR | EIS | CPUC | TBD | CPCN | 2026-11-20 | To be Filed | 2027 | Planning | NA | 2029-09-30 | 2032-01-31 | 2032-01-24 | NA | NA | FALSE | 1,300,000 - 2,200,000 | NA ¦ NA | 1624309 | 0 | 0 | 0 | 0 | 985 | 5244 | 21010 | 49156 | 130829 | 346982 | 388225 | 985 | NA | 3 | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0%
215 | [Programmatic] CBM Reliability Upgrade Program |  |  | Multiple | Decommission SMP16 gateways and replace with 1 SEL 3355 RTAC and Crossbow 4650 passthrough appliance at each of the 128 substations. | Substation - Other Equipment | Replace | Upgrade/Retrofit | NA | Reliability | Replace Other Substation Equipment | NA | NA | NA | NA | NA | NA | NA | Multiple | FALSE ¦ FALSE ¦ FALSE | 0 | NA |  | NA | NA | NA | NA | 4.1 | Multiple | QBL0174 | 0 | 25155 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2026-01-23 | Work Order Authorization | 2026 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Engineering less than 50% complete | NA | NA | NA | NA | NA | NA | FALSE | NA | NA ¦ NA | 22416.0396 | 0 | 0 | 0 | 0 | 0 | 16.0531 | 1346.4357 | 2822.8845 | 3085.0689 | 3371.6045 | 3684.753 | 16.0531 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] Exempt
216 | [Programmatic] Transmission System Automation |  |  | Multiple | To enhance transmission system reliability, capital projects are required to 1) install new transmission SCADA systems and 2) replace/upgrade existing transmission SCADA systems to provide control and monitoring capability for grid operations. In addition, there is a requirement to install systems to provide monitoring of certain critical substation apparatus to provide data for enhanced scheduling of maintenance. There are also new security requirements based upon NERC guidelines and the SEMPRA Control System security policy, which mandate the need to install equipment to control access to equipment installed in substations. The budget also allows us to enable remote event retrieval in non-Medium Impact substations to significantly reduce the time it takes to obtain event records and situational awareness during system disturbances. | Substation - Multiple | New | NA | NA | Reliability | Relay Upgrades | NERC CIP Compliance | NA | NA | NA | NA | NA | NA | Multiple | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69 ¦ 500 | 373MVA | 2.1 | Multiple | QBL0001 | 58 | 3171 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-12-11 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | NA | NA | NA | NA | NA | TRUE | NA | NA ¦ NA | 63112.2223 | 1813.0371 | 2170.6237 | 870.2163 | 412.9849 | 1160.7604 | 271.1531 | 2080.7781 | 4413.8554 | 4457.8774 | 4502.2747 | 5009.9336 | 883.4129 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 ¦ 2026 | 265.5254 | 2165.6105 | 2291.4535 | 882.4913 | 210.2818 | 2522.648 | 0% | NA ¦ NA | 3.1 | NA | 45.85% | 54.15% | [CPUC Status] Exempt
217 | TSA_QUANTA CORE PHASE 2 |  |  | San Diego County, Orange County, Imperial County | To enhance transmission system reliability, capital projects are required to 1) install new transmission SCADA systems and 2) replace/upgrade existing transmission SCADA systems to provide control and monitoring capability for grid operations. In addition, there is a requirement to install systems to provide monitoring of certain critical substation apparatus to provide data for enhanced scheduling of maintenance. There are also new security requirements based upon NERC guidelines and the SEMPRA Control System security policy, which mandate the need to install equipment to control access to equipment installed in substations. | Substation - Other Equipment | Upgrade/Retrofit | NA | NA | Reliability | Replace Other Substation Equipment | NA | NA | NA | NA | NA | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | 0 | Individual Project Review Required |  | NA | NA | NA | NA | 2.1 | NA | QBL0001 | 1 | 3171 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2025-12-01 | Work Order Authorization | 2025 | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | NA | NA | TBD | TBD | Exempt | NA | NA [See Notes] | NA | Engineering less than 50% complete | NA | NA | NA | 2029-12-31 | NA | NA | FALSE | 6258.288 | NA ¦ NA | 6733.4587 | 0 | 0 | 0 | 0 | 3133.9011 | -119.2988 | 1502.227 | 1597.4949 | 347.73 | 271.4045 | 0 | 3014.6024 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] Exempt
218 | CEC RAS SONGS |  |  | San Diego, San Diego | SONGS substation CEC-RAS upgrades | Substation - Protection Relay | Upgrade/Retrofit | NA | NA | Reliability | Relay Upgrades | NA | NA | 2026-05-27 | 3.85 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 230 | NA | 2.1 | 2022-2912 | QBL0001 | 1 | 3171 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2022-05-11 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2023-03-06 | 2023-08-03 | 2023-08-20 | NA | NA | FALSE | 2114.7965 | NA ¦ NA | 2181.2727 | 0 | 104.6216 | 1965.4913 | 53.7741 | 57.3857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2023 ¦ 2024 ¦ 2025 | 0 | 0 | 2070.1128 | 53.7741 | 57.3857 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0% | [CPUC Status] Exempt
219 | TSA ICON SOUTH BAY 230KV RING |  |  | San Diego, San Diego | To enhance transmission system reliability, capital projects are required to 1) install new transmission SCADA systems and 2) replace/upgrade existing transmission SCADA systems to provide control and monitoring capability for grid operations. In addition, there is a requirement to install systems to provide monitoring of certain critical substation apparatus to provide data for enhanced scheduling of maintenance. There are also new security requirements based upon NERC guidelines and the SEMPRA Control System security policy, which mandate the need to install equipment to control access to equipment installed in substations. | Substation - Protection Relay | Replace | Upgrade/Retrofit | NA | Reliability | Relay Upgrades | NA | NA | 2026-05-12 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | 0 | NA |  | NA | 2.78 | NA | NA | 2.1 | 2022-3075 | QBL0001 | 1 | 3171 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2022-06-20 | Work Order Authorization | 2022 | NA | FALSE | NA | NA | NA | FALSE | TBD | TBD | NA | NA | TBD | TBD | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2024-11-15 | 2026-06-16 | 2026-06-16 | NA | NA | TRUE | 1072.722 | NA ¦ NA | 1580.4728 | 0 | 80.0413 | 419.8221 | 589.3408 | 448.7441 | 38.8307 | 3.6938 | 0 | 0 | 0 | 0 | 38.8307 | NA | NA | 2023 ¦ 2024 ¦ 2025 ¦ 2026 | 0 | 0 | 499.8635 | 337.9332 | 700.1516 | 42.5245 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] Exempt
220 | SYSTEM AUTOMATION CROSSBOW |  |  | San Diego, San Diego | Siemens Crossbow deployments at multiple substations | Substation - Protection Relay | Upgrade/Retrofit | NA | NA | Reliability | Relay Upgrades | NA | NA | NA | NA | NA | NA | NA | Multiple | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69 ¦ 138 | 373MVA | 2.1 | NA | QBL0001 | 1 | 3171 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-05-11 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | NA | 2023-12-31 | 2024-10-31 | Prioritization | NA | FALSE | 5626.5931 | NA ¦ NA | 3333.4919 | 659.0243 | 741.0698 | 441.3229 | 305.2445 | -17.0108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2024 ¦ 2025 | 0 | 0 | 0 | 3350.5026 | -17.0108 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
221 | SYSTEM AUTOMATION VARIOUS SUBS |  |  | San Diego, San Diego | Transmission System Automation (TSA) upgrades at multiple substations | Substation - Protection Relay | Upgrade/Retrofit | NA | NA | Reliability | Relay Upgrades | NA | NA | NA | NA | NA | NA | NA | Multiple | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69 | 373MVA | 2.1 | 2020-2045 | QBL0001 | 1 | 3171 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-03-04 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2020-08-12 | 2020-04-01 | 2021-04-08 | Prioritization | NA | FALSE | 685.319 | NA ¦ NA | 5043.2239 | 2370.1925 | 178.7026 | -6.2042 | 0.00179 | -13.8829 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 0.36639 | 5062.9427 | -6.2042 | 0.00179 | -13.8829 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
222 | ADVANCED RLY EVENT RETRVL SUBS |  |  | San Diego, San Diego | Advanced Relay Event Retrieval (ARER) deployments at multiple substations | Substation - Protection Relay | Upgrade/Retrofit | NA | NA | Reliability | Relay Upgrades | NA | NA | 2026-04-02 | NA | NA | NA | NA | Multiple | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69 | 373MVA | 2.1 | Multiple | QBL0001 | 1 | 3171 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-08-07 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2022-09-12 | 2023-12-31 | 2022-08-30 | NA | NA | FALSE | 4466.8942 | NA ¦ NA | 3124.9259 | 930.75 | 1331.2285 | 597.451 | 210.5402 | 53.9415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 0 | 2262.9932 | 597.451 | 210.5402 | 53.9415 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt [Utility Unique ID #1(Most Specific)] 2019-2110 , 2014-00646-ZZ , 2022-2975 , 2021-2053 , 2021-2130 , 2021-2134 , 2023-3594 , 2023-3600 , 2023-3602 , 2021-2023 , 2021-2022 , 2021-2020 , 2021-2024 , 2021-2461 , 2022-2919 , 2022-2927 , 2021-2131 , 2020-2051 , 2020-2080 , 2021-2003 , 2021-2315
223 | MISSION SUBSTATION: PILOT TELEP |  |  | San Diego, San Diego | Pilot Telephony deployment at Mission Substation | Substation - Protection Relay | Upgrade/Retrofit | NA | NA | Reliability | Relay Upgrades | NA | NA | 2026-05-28 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 1.83 | 69 | NA | 2.1 | NA | QBL0001 | 1 | 3171 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2015-10-16 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | NA | 2016-12-31 | 2022-05-30 | Prioritization | NA | FALSE | 200 | NA ¦ NA | 1885.3737 | 741.5454 | 287.3885 | 4.9655 | 0 | -8.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2025 | -17.6185 | 1906.5367 | 4.9655 | 0 | -8.51 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
224 | BERNARDO SUBST. RPL TL689 RLY |  |  | San Diego, San Diego | Upgrade 69kV relays and supporting equipment for TL689. | Substation - Protection Relay | Upgrade/Retrofit | NA | NA | Reliability | Relay Upgrades | NA | NA | 2026-05-27 | 4.32 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 2.51 (BE) / 4.66 (ES) | 69 | 373MVA | 2.1 | 2014-01115-ZZ | QBL0001 | 1 | 3171 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-01-25 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2023-03-06 | 2023-11-14 | 2023-08-20 | NA | NA | FALSE | 10428.1179 | NA ¦ NA | 11850.7941 | 1207.5322 | 4046.0331 | 1806.6638 | 1679.0852 | 183.9414 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2024 ¦ 2025 | 1.2305 | -0.25875 | 0 | 3352.0871 | 8497.7353 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
225 | [Programmatic] Emergency Equipment Purchase |  |  | Multiple | This budget supports the restoration of service to our distribution customers following outages caused by equipment failure by purchasing additional emergency spare and mobile equipment. Spare equipment is necessary to provide construction and operations with the appropriate spares to replacement equipment under failure conditions. Spare equipment is typically use for critical situations and the stock must be kept up to date to minimize chances for mismatch in field. | Substation - Multiple | New | NA | NA | Reliability | Substation Reliability | NERC TPL Standards | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | Multiple | 28MVA | 4.1 | Multiple | QBL0024 | 38 | 6254 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-12-16 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | NA | NA | NA | NA | NA | NA | To be Filed | NA | Operational | NA | NA | NA | NA | NA | NA | TRUE | NA | NA ¦ NA | 38203.4648 | 994.4584 | 280.2973 | 319.7617 | 264.9001 | 149.959 | 841.3472 | 622.6309 | 362.5185 | 1175.4678 | 2792.5103 | 3605.9123 | 739.9891 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 ¦ 2026 | 1171.5107 | 333.7874 | 266.4494 | 318.2124 | 20.7748 | 1300.6346 | 0% | NA ¦ NA | 8.1 | NA | 0% | 100%
226 | ES SPARE 69KV & 138KV CBS |  |  | Escondido, San Diego | The purchase of (2) spare 69kV, 3000A, 63kA Circuit Breakers, and (2) spare 138kV, 3000A, 63kA Circuit Breakers. These breakers will be used on substation capital projects and emergency breaker replacements | Substation - Multiple | New | New | NA | Reliability | 3rd Party Damage | NERC CIP Compliance | NERC CIP Compliance | 2026-05-20 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 4.66 | 69 ¦ 13 | 69kV and 138kV | 4.1 | NA | QBL0024 | 1 | 6254 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-03-07 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | CPUC | NA | NA | NA | To be Filed | NA | Operational | NA | 2023-03-07 | 2024-04-30 | 2025-04-04 | Material | NA | FALSE | 512.7173 | NA ¦ NA | 1017.9542 | 0 | 0 | 0.39574 | 804.8984 | 212.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2025 | 0 | 0 | 0 | 0 | 1017.9542 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
227 | [Programmatic] Fiber Build Initiative |  |  | Multiple | Install ADSS and or OPGW fiber optic cables on existing Transmission overhead structures and build UG facilities as required. | Other | New | NA | NA | Reliability | System Operations | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | Individual project reviews would be required. |  | NA | NA | Multiple | NA | 4.3 | Multiple | QBL0025 | 192 | 7144 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-12-16 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | Other [See Notes] | CPUC | TBD | NA | NA | NA [See Notes] | NA | Operational | NA | NA | NA | NA | NA | NA | TRUE | NA | NA ¦ NA | 185045.8841 | 768.2183 | 572.6841 | 2038.0258 | 4143.4498 | 4728.418 | 1425.1356 | 10747.1084 | 13202.2379 | 15303.1727 | 13039.7328 | 14244.1621 | 6872.8918 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 ¦ 2026 | 868.9017 | 164.8547 | 1269.4058 | 943.7186 | 3404.8478 | 3485.0012 | 0% | NA ¦ NA | 2.1 | NA | 45.85% | 54.15% | [CPUC Status] Exempt
228 | TL674 STRUCTURE RPL GRP 8 |  |  | Rancho SantaFe, San Diego | pole replacement for Z14345, Z14346, Z14347 | Other | NA | NA | NA | Wildfire Mitigation | System Operations | NA | NA | 2026-01-27 | NA | NA | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | 0 | NA |  | 0.3 | NA | NA | NA | 4.3 | 2022-2995 | QBL0025 | 1 | 7144 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2022-09-23 | Work Order Authorization | 2022 | NA | FALSE | NA | NA | NA | FALSE | NA | Exempt | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2025-05-30 | 2023-12-13 | 2025-10-03 | NA | NA | FALSE | 1475.0955 | NA ¦ NA | 1213.0581 | 0 | 16.4589 | 209.3149 | 193.7627 | 802.3627 | -8.8411 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2023 ¦ 2024 ¦ 2025 ¦ 2026 | 0 | 0 | 225.7738 | 165.6821 | 830.4433 | -8.8411 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] Exempt
229 | FBI TL23012/53/674(Z710041 ENC) |  |  | Encinitas, San Diego | TL674/6973 EN-DM with OPGW attachments on TL23012/23053. | Other | New | New | NA | Reliability | System Operations | NA | NA | 2026-02-24 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 8.05 | NA | NA | NA | 4.3 | 2019-4010 | QBL0025 | 1 | 7144 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-01-20 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Engineering less than 50% complete | NA | 2026-05-01 | 2021-10-30 | 2029-02-05 | NA | NA | FALSE | 6204.8081 | NA ¦ NA | 4193.8315 | 96.4412 | 352.8243 | 215.2307 | 1835.7889 | 1227.4041 | 99.9423 | 86.2879 | 121.7199 | 65.8403 | 0 | 0 | 3919.9833 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] Exempt
230 | FBI_TL23027 TL23028 MS OT |  |  | San Diego, San Diego | This project installs a fiber optic connection between Mission Substation and Oldtown Substation. | Other | New | New | NA | Reliability | System Operations | NA | NA | 2026-02-23 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 1.84 | NA | NA | NA | 4.3 | 2009-00015-ZZ | QBL0025 | 1 | 7144 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2018-09-13 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2020-09-15 | 2021-09-30 | 2022-05-24 | NA | NA | TRUE | 2930.258 | NA ¦ NA | 4078.245 | 2619.098 | 357.1686 | 46.1213 | 118.8947 | 16.3507 | 104.4649 | 3.8882 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2022 ¦ 2023 ¦ 2024 ¦ 2025 ¦ 2026 | 0 | 3787.4726 | 46.1068 | 118.8795 | -12.8681 | 138.6541 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] Exempt
231 | TL 654 MISSIONSTATION F R3 |  |  | San Diego, San Diego | This project installs fiber optic approximately 2.2 miles of 96-count ADSS Fiber Optic Cable on TL654 between Station F and Mission Substation as well as 5 pole replacement, and installation of 2 new Fiber-only poles, 3 fiber optic splice boxes and 10ft UG trench. | Other | New | New | NA | Reliability | System Operations | NA | NA | 2026-02-12 | 34; 34; 34; 34; 61 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | TBD |  | 5.28 | NA | NA | NA | 4.3 | 2014-00430-ZZ | QBL0025 | 1 | 7144 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-02-10 | Work Order Authorization | 2019 | NA | FALSE | NA | NA | NA | FALSE | NA | Exempt | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2021-02-24 | 2021-04-01 | 2021-08-23 | NA | NA | FALSE | 1921.408 | NA ¦ NA | 1139.5726 | 499.5178 | 84.4468 | 39.4489 | 57.6668 | -1.6257 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 949.3488 | 94.7337 | 39.4489 | 57.6668 | -1.6257 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] Exempt
232 | TL608 STREAMVIEWCHOLLAS R4 |  |  | San Diego, San Diego | This project installs ADSS fiber from Streamview to Chollas | Other | New | New | NA | Reliability | System Operations | NA | NA | 2026-02-05 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | TBD |  | 2.54 | NA | NA | NA | 4.3 | 2010-00005-ZZ | QBL0025 | 1 | 7144 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2013-05-13 | Work Order Authorization | 2019 | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Engineering less than 50% complete | NA | 2027-04-28 | 2013-12-31 | 2029-07-10 | NA | NA | TRUE | 390 | NA ¦ NA | 1612.8172 | 89.4288 | 166.7859 | 94.8248 | 350.0449 | 0.46004 | 18.3212 | 100.7855 | 0 | 0 | 0 | 0 | 1512.0317 | NA | NA | 2026 | 0 | 0 | 0 | 0 | 0 | 1612.8172 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] Exempt
233 | TL 621 PARADISEMIGUEL F R2 |  |  | San Diego, San Diego | This projects installs 6.7miles of ADSS friber from Paradise to Miguel | Other | New | New | NA | Reliability | System Operations | NA | NA | 2026-01-11 | NA | NA | NA | NA | Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | TBD |  | 7.484 | NA | NA | NA | 4.3 | 2010-00007-ZZ | QBL0025 | 1 | 7144 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2018-04-10 | Work Order Authorization | 2019 | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | On Hold | NA | 2026-04-30 | 2019-12-01 | NA | NA | NA | TRUE | 2794.298 | NA ¦ NA | 2200.321 | 320.6091 | 509.3656 | 6.7301 | 1277.3612 | -117.7319 | 5.3493 | 0 | 0 | 0 | 0 | 0 | 2200.321 | NA | NA | 2025 ¦ 2026 | 0 | 0 | 0 | 0 | -0.0079696 | 2194.9123 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] Exempt
234 | TL697 SAN LUIS REY OCE R7 |  |  | Oceanside, San diego | This project consists of installing 1 cable (192-Fiber DNA-33029 ADSS) on TL697 between structures Z229374 to Z28268, approximately 1 mile. Project includes installing 3 fiber optic splice locations and 26 ADSS connections. | Other | New | New | NA | Reliability | System Operations | NA | NA | 2026-02-03 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | TBD |  | 1.49 | NA | NA | NA | 4.3 | 2014-00465-ZZ | QBL0025 | 1 | 7144 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-01-16 | Work Order Authorization | 2019 | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2021-11-05 | 2020-11-01 | 2022-09-28 | NA | NA | FALSE | 135.665 | NA ¦ NA | 1262.3 | 99.7911 | 493.3866 | 52.2351 | 212.6971 | -1.0307 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 0 | 998.3985 | 52.2351 | 212.6971 | -1.0307 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] Exempt
235 | TL631 EL CAJON LOS COC R2 |  |  | San Diego, San Diego | Install ADSS and or OPGW fiber optic cables on existing Transmission overhead structures and build UG facilities as required. 2020 has (20) active projects at various stages of engineering and construction. All projects to date are exempt from CPUC permitting. | Other | NA | NA | NA | Wildfire Mitigation | System Operations | NA | NA | 2026-02-12 | NA | NA | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | 0 | NA |  | 2.2 | NA | NA | NA | NA | 2014-00956-ZZ | QBL0025 | 1 | 7144 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2022-07-13 | Work Order Authorization | 2021 | NA | FALSE | NA | NA | NA | FALSE | NA | Exempt | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Engineering less than 50% complete | NA | 2027-02-11 | 2023-08-01 | 2028-12-14 | NA | NA | TRUE | 3688.524 | NA ¦ NA | 1895.6657 | 110.7806 | 132.5111 | 1.3269 | 0 | 1415.0984 | 13.2494 | 117.8582 | 0 | 0 | 0 | 0 | 1777.8076 | NA | NA | 2026 | 0 | 0 | 0 | 0 | 0 | 1895.6657 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] Exempt
236 | FIBER BUILD TL6973 DM NCW |  |  | San Diego, San Diego | Project consists of installing two miles of UG fiber & 1 mile of OPGW to connect DM-NCW | Other | New | New | NA | Reliability | System Operations | NA | NA | 2026-02-05 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 3 | NA | 230 | NA | 4.3 | 2020-4032 | QBL0025 | 1 | 7144 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-02-21 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2024-07-15 | 2024-12-10 | 2025-08-26 | NA | NA | TRUE | 3018.685 | NA ¦ NA | 3627.1306 | 22.597 | 121.1329 | 297.4802 | 1278.8991 | 1736.6682 | 165.3513 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2025 ¦ 2026 | 0 | 0 | 0 | 0 | 2535.0444 | 1092.0862 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0% | [CPUC Status] Exempt
237 | TL608 STRUCTURE RPL GRP 1 |  |  | San Diego, San Diego | Pole Replacements for Z371045, Z473553. This project is only a pole replacement and does not include any mileage. | Other | New | New | NA | Reliability | System Operations | NA | NA | 2026-02-05 | 57 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.1 | NA | NA | NA | 4.3 | 2022-3097 | QBL0025 | 1 | 7144 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2022-10-10 | Work Order Authorization | 2023 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Construction (over 75%) | NA | 2025-08-26 | 2024-08-07 | 2026-07-15 | NA | NA | TRUE | 2017.4396 | NA ¦ NA | 3262.8166 | 0 | 1.7024 | 268.7547 | 879.72 | 1334.1613 | 578.1013 | 200.3769 | 0 | 0 | 0 | 0 | 3062.4398 | NA | NA | 2026 | 0 | 0 | 0 | 0 | 0 | 3262.8166 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] Exempt
238 | FBI TL652/653 METRO STATION F |  |  | San Diego, San Diego | This is a fiber project for reverse engineering from Metro- Station F Sub, to bring this TL up to SDGE standards | Other | New | New | NA | Reliability | System Operations | NA | NA | 2026-01-27 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 3.7 | NA | NA | NA | 4.3 | 2021-2218 | QBL0025 | 1 | 7144 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2021-07-14 | Work Order Authorization | 2022 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Engineering more than 50% complete | NA | 2026-09-01 | 2023-12-10 | 2027-02-17 | NA | NA | FALSE | 382.1892 | NA ¦ NA | 1748.2953 | 0.23163 | 57.4894 | 295.9945 | 475.5031 | 693.0828 | 35.5351 | 107.3057 | 83.1529 | 0 | 0 | 0 | 1557.8366 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] Exempt
239 | FBI MISSION STATION F |  |  | San Diego, San Diego | Engineer and construct 3.0 miles of ADSS-96 to upgrade existing ADSS-12 on existing overhead/underground. | Other | NA | NA | NA | Wildfire Mitigation | System Operations | NA | NA | NA | NA | NA | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | 0 | NA |  | 2.16 | NA | NA | NA | 4.3 | 2021-2217 | QBL0025 | 1 | 7144 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2021-07-14 | Work Order Authorization | 2022 | NA | FALSE | NA | NA | NA | FALSE | NA | Exempt | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Construction (25%-50%) | NA | 2026-03-30 | 2025-12-30 | 2026-08-13 | NA | NA | TRUE | 382.1892 | NA ¦ NA | 1004.5915 | 0.47466 | 70.3644 | 164.0117 | 396.0312 | 285.447 | 26.4247 | 61.8378 | 0 | 0 | 0 | 0 | 942.7537 | NA | NA | 2026 | 0 | 0 | 0 | 0 | 0 | 1004.5793 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] Exempt
240 | TL674 RANCHO SANTA FE TO Z12322 |  |  | San Diego, Rancho Santa Fe | this Fiber Build Project involves installation of 3.5-miles of fiber optic cable (ADSS) on existing TL674 between structures Z710041 (TL23012/23053) and Z192874 (TL674). | Other | New | New | NA | Reliability | System Operations | NA | NA | 2026-01-27 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 3.5 | NA | NA | NA | 4.3 | 2019-40131 | QBL0025 | 1 | 7144 | 2026-06-17 ¦ 2019-4013 ¦ NA ¦ NA | TRUE | 2020-01-08 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Engineering more than 50% complete | NA | 2027-06-18 | 2024-03-10 | 2028-02-15 | NA | NA | FALSE | 5140.496 | NA ¦ NA | 2897.4095 | 87.8171 | 206.9926 | 1.0593 | 1261.672 | 737.4986 | 24.8842 | 168.132 | 242.327 | 55.057 | 0 | 0 | 2431.8935 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] Exempt
241 | TL674 STRUCTURE RPL GRP 2 |  |  | San Diego, San Diego | Compliance Pole Replacement for structures Z12326, Z12327, Z33209, Z12328. Also mitigation of clearance issues. | Other | NA | NA | NA | Wildfire Mitigation | System Operations | NA | NA | 2026-01-27 | NA | NA | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | 0 | NA |  | 0.25 | NA | NA | NA | 4.3 | 2022-2989 | QBL0025 | 1 | 7144 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2022-09-21 | Work Order Authorization | 2022 | NA | FALSE | NA | NA | NA | FALSE | NA | Exempt | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2025-02-07 | 2023-12-27 | 2025-09-01 | NA | NA | TRUE | 1413.6332 | NA ¦ NA | 1982.4488 | 0 | 18.4744 | 270.9402 | 261.2526 | 1415.0555 | 16.726 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2023 ¦ 2024 ¦ 2025 ¦ 2026 | 0 | 0 | 289.4146 | 261.2526 | 1415.0555 | 16.726 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] Exempt
242 | TL652 STATION F WABASH F R4 |  |  | San Diego, San Diego | TL652 F-WAC Fiber Build | Other | New | New | NA | Reliability | System Operations | NA | NA | 2026-02-12 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 2.48 | NA | NA | NA | 4.3 | 2010-00003-ZZ | QBL0025 | 1 | 7144 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-02-10 | Work Order Authorization | 2019 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | On Hold | NA | 2027-05-13 | 2023-01-15 | 2029-10-10 | NA | NA | FALSE | 1940.972 | NA ¦ NA | 2404.1648 | 146.6675 | 143.9066 | 0.76998 | 1504.9648 | 57.7953 | 23.6882 | 135.0762 | 194.684 | 79.0539 | 0 | 0 | 1995.3506 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] Exempt
243 | TL607 WABASH STREAMVIEW R4 |  |  | San Diego, San Diego | TL607 WAC-SR Fiber Build | Other | Replace | New | NA | Reliability | System Operations | NA | NA | 2026-01-27 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 3.19 | NA | NA | NA | 4.3 | 2010-00004-ZZ | QBL0025 | 1 | 7144 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-02-10 | Work Order Authorization | 2019 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | On Hold | NA | 2027-06-01 | 2023-01-10 | 2028-01-26 | NA | NA | TRUE | 2794.924 | NA ¦ NA | 1625.8047 | 65.4742 | 135.9631 | 81.9072 | 1188.4923 | 22.0165 | 4.0407 | 0 | 0 | 0 | 0 | 0 | 1497.894 | NA | NA | 2025 ¦ 2026 | 0 | 0 | 0 | 0 | 0.0062476 | 1622.7007 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] Exempt
244 | TL 624 JAMACHA EL CAJON R4 |  |  | El Cajon, San Diego | Install a level of ADSS fiber on 4.8 miles of TL624 poles between Jamacha Substation and El Cajon Substation (0.7 miles from Z371408 to El Cajon Substation is double circuit with TL 630), 7 Steel Pole Replacement, Construct ADSS conduit on Z778064 (inside of Jamacha Substation) and trench into Jamacha Substation. Construct ADSS conduits on Z75142 for TL624 Fiber Build and TL630 FIber Build and trench into El Cajon Substation. Construct ADSS conduit on P100483 and Z371410 and trench 0.2 miles in between. Correct all non-compliance, both existing and caused by proposed ADSS addition. This to be done be replacing poles and reframing distribution. | Other | Replace | New | NA | Reliability | System Operations | NA | NA | 2026-02-12 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 4.8 | NA | NA | NA | 4.3 | 2010-00010-ZZ | QBL0025 | 1 | 7144 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-02-10 | Work Order Authorization | 2019 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Engineering less than 50% complete | NA | 2026-11-20 | 2024-12-02 | 2029-02-07 | NA | NA | FALSE | 3133.983 | NA ¦ NA | 1680.3913 | 38.6457 | 361.0917 | 74.7756 | 898.548 | -14.8227 | 16.8138 | 77.7572 | 108.0166 | 0 | 0 | 0 | 1494.6175 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] Exempt
245 | TL 600 ROSECANYON CLAIRE R3 |  |  | San Diego, San Diego | The proposed Project aims to install approximately 4 miles of 96-Count ADSS Fiber Optic Cable between these substations, along existing TL 600 structures. The proposed route would attach to 72 existing structures supporting TL 600 conductor. There are 5 proposed new structures proposed specifically for the fiber addition. At each substation, the fiber will convert from an overhead to underground configuration at the last pole outside the substation. From there, SDG&E will install fiber in existing underground conduit into each substation. | Other | New | New | NA | Reliability | System Operations | NA | NA | 2026-02-12 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 4.76 | NA | NA | NA | 4.3 | TM2010-00012-ZZ | QBL0025 | 1 | 7144 | 2026-06-17 ¦ 2010-00012-ZZ ¦ NA ¦ NA | TRUE | 2020-02-10 | Work Order Authorization | 2019 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Engineering less than 50% complete | NA | 2027-07-02 | 2022-12-10 | 2029-08-30 | NA | NA | FALSE | 2465.449 | NA ¦ NA | 1321.0125 | 285.9957 | 82.8769 | 14.74 | 690.3848 | -69.8735 | 11.0235 | 76.6025 | 110.4065 | 54.8158 | 0 | 0 | 1079.1877 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] Exempt
246 | TL674 STURCTURE RPL GRP 1 |  |  | San Diego, San Diego | Compliance pole replacements for structures Z12322 & Z12323 | Other | Replace | New | NA | Reliability | System Operations | NA | NA | 2026-01-27 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.04 | NA | NA | NA | 4.3 | 2022-2988 | QBL0025 | 1 | 7144 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2022-09-20 | Work Order Authorization | 2022 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | CPUC | NA | Exempt | 2025-10-23 | NA [See Notes] | NA | Construction (over 75%) | NA | 2024-07-12 | 2024-04-03 | 2025-07-17 | NA | NA | FALSE | 983.397 | NA ¦ NA | 1237.987 | 0 | 18.4744 | 355.2612 | 197.5604 | 677.9339 | -11.2429 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2023 ¦ 2024 ¦ 2025 ¦ 2026 | 0 | 0 | 373.7356 | 170.7371 | 704.7572 | -11.2429 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] Exempt
247 | TL680B MELROSE MELROSE T R6 |  |  | Vista, San Diego | The project will include stringing 4.0 miles of new DNA-30411 ADSS conductor (including 2.0 miles of underground ADSS from Z115895 to Melrose Substation, 0.2 miles of which will require new trenching), installing fiber attachments, and installing fiber splice boxes. Fiber connection to substation to utilize existing infrastructure. | Other | Replace | New | NA | Reliability | System Operations | NA | NA | 2026-01-13 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 6.2 | NA | NA | NA | 4.3 | 2015-00015-ZZ | QBL0025 | 1 | 7144 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-01-28 | Work Order Authorization | 2019 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Engineering less than 50% complete | NA | 2027-05-26 | 2023-12-10 | 2029-09-04 | NA | NA | FALSE | 6070.021 | NA ¦ NA | 3420.7898 | 187.8281 | 127.8449 | 4.9681 | 2626.6664 | 48.7663 | 8.551 | 0 | 0 | 0 | 0 | 0 | 3420.7898 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] Exempt
248 | FBI_TL652POLE REPLACEMENTS SR94 |  |  | San Diego, San Diego | Replacing 2 poles (Z730989, Z730996) with ESPs on TL652, crossing 94 freeway. No newfiber stringing. Mitigating L2 issues due to overutilization.​ | Other | Replace | New | NA | Reliability | System Operations | NA | NA | 2026-02-12 | 70 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | TBD |  | 2.48 | NA | NA | NA | 4.3 | 2024-3974 | QBL0025 | 1 | 7144 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-07-23 | Work Order Authorization | 2024 | NA | FALSE | NA | NA | NA | FALSE | TBD | TBD | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Engineering more than 50% complete | NA | 2026-08-04 | 2026-04-03 | 2026-12-03 | NA | NA | TRUE | 1174.8215 | NA ¦ NA | 1470.8754 | 0 | 0 | 0 | 465.0492 | 836.1047 | 62.4992 | 92.1855 | 15.0369 | 0 | 0 | 0 | 1363.653 | NA | NA | 2026 | 0 | 0 | 0 | 0 | 0 | 162.6911 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] Exempt
249 | [Programmatic] Overstressed Breakers |  |  | Multiple | Replace overstressed breakers as identified at the following substations : Bay Boulevard, Mission, Sycamore Canyon, San Luis Rey, Miguel | Substation - Circuit Breaker | Replace | NA | NA | Reliability | Age/Condition | NERC TPL Standards | NA | NA | NA | NA | Wires - Replacement Alternative | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | Multiple | NA | 2.1 | Multiple | QBL0061 | 13 | 9170 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-12-16 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | NA | NA | To be Filed | NA | Planning | NA | NA | NA | NA | NA | NA | FALSE | NA | NA ¦ NA | 57627.1098 | 0 | 0 | 0 | 0 | 0 | 0.7617 | 0.052465 | 2874.1167 | 3069.3935 | 3367.1783 | 3693.0173 | 0.7617 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
250 | ASH OVERSTRESSED BREAKER |  |  | Escondido, San Diego | Replace overstressed breakers as identified at the following substations - Bay Boulevard - Mission - Sycamore Canyon - San Luis Rey - Miguel | Substation - Multiple | New | Upgrade/Retrofit | NA | Reliability | Substation Reliability | NA | NA | 2026-06-01 | NA | NA | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | 0 | Individual Project Review Required |  | NA | 1.1 | 69 | 69¦12kV | 2.1 | 2021-1001 | QBL0061 | 1 | 9170 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-10-03 | Work Order Authorization | 2022 | NA | FALSE | NA | NA | NA | FALSE | NA | tbd | NA | NA | CPUC | TBD | Exempt | NA | NA [See Notes] | NA | Construction (50%-75%) | NA | 2025-04-08 | 2025-11-29 | 2026-07-28 | Material | NA | TRUE | 257.9884 | NA ¦ NA | 1466.2175 | 18.8614 | 42.2006 | 301.2157 | 237.0847 | 795.3753 | -2.9977 | 66.404 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2024 ¦ 2025 ¦ 2026 | 0 | 0 | 0 | 607.4359 | 795.3753 | 63.4063 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
251 | SAN LUIS RAY OVERSTRES |  |  | Oceanside, San Diego | Replace breakers based on short circuit study | Substation - Circuit Breaker | Replace | Upgrade/Retrofit | NA | Reliability | Replace Breakers | NA | NA | 2026-05-13 | 51; 51; 51; 54; 51; 51; 54; 54; 54; 51; 54; 54; 54; 54 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 6.12 | 69 | 230kV¦69kV | 2.1 | 2022-2943 | QBL0061 | 1 | 9170 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2021-06-18 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Construction (10%-25%) | NA | 2026-07-15 | 2023-12-31 | 2027-02-23 | Weather | Construction Delays | TRUE | 3106.3706 | NA ¦ NA | 6688.6324 | 1659.8046 | 335.3891 | 307.8147 | 610.7175 | 810.4217 | 457.7709 | 2506.7138 | 0 | 0 | 0 | 0 | 4181.9186 | NA | NA | 2026 | 0 | 0 | 0 | 0 | 0 | 6688.6324 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
252 | MIGUEL OVERSTRESSED BREAKER |  |  | San Diego, San Diego | Miguel - 69kV Overduty CB/DC Motor Retrofit | Substation - Circuit Breaker | Replace | Upgrade/Retrofit | NA | Reliability | Age/Condition - Replace Breakers | NA | NA | 2026-05-19 | 52 | NA | NA | NA | Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 12.37 | 69 | 69kV | 2.1 | 2021-2498 | QBL0061 | 1 | 9170 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-10-13 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2024-01-17 | 2021-09-01 | 2024-04-17 | Weather | NA | FALSE | 300.6063 | NA ¦ NA | 1497.655 | 103.6174 | 499.083 | 225.32 | 657.3331 | 12.3016 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2024 ¦ 2025 | 0 | 0 | 0 | 1485.3535 | 12.3016 | 0 | 46% | 100.00% ¦ 1,921 | NA ¦ NA | NA | 0% | 100%
253 | SYCAMORE CYN OVERSTRESSED BKR R |  |  | San Diego, San Diego | Sycamore Canyon Overstressed Breaker Replacement | Substation - Circuit Breaker | Replace | Upgrade/Retrofit | NA | Reliability | Age/Condition - Replace Breakers | NA | NA | 2026-05-06 | 17; 17; 17; 17; 17; 17; 17; 32; 33; 33; 33; 33; 33; 33; 34; 26; 26; 32 | NA | NA | NA | Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 10.79 | 69 | 138kV¦69kV | 2.1 | 2019-1023 | QBL0061 | 1 | 9170 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-04-23 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2020-05-04 | 2020-12-31 | 2022-06-13 | Weather | NA | FALSE | 6052.048 | NA ¦ NA | 8522.4987 | 1815.8743 | 1495.8071 | 109.4131 | -0.12432 | -47.2078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 0 | 8460.4178 | 109.4131 | -0.12432 | -47.2078 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
254 | [Programmatic] IT Enterprise Network Operation Support |  |  | Multiple | IT Enterprise Network Operation Support | Other - IT | Replace | Multiple Options [See Notes] | NA | Other [See Notes] | System Operations | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | NA | NA | NA | Multiple | Multiple | 86 | 925 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-12-09 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | NA | NA | NA [See Notes] | NA | Operational | NA | NA | NA | NA | NA | NA | TRUE | NA | NA ¦ NA | 20691.1739 | 861.883 | 1373.2652 | 1288.9571 | 1655.3502 | 1817.7775 | 3611.1345 | 0 | 3664.8337 | 0 | 0 | 0 | 3611.1345 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 ¦ 2026 | 667.6486 | 1497.317 | 1088.4337 | 1065.3399 | 2678.4939 | 3650.0825 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [Primary Purpose] Age/End of Life and Reliability [Project Description - Action Taken (2)] NA [CPUC Status] Exempt
255 | SDGE DC Network Core Refresh (Plan) T000021 |  |  | Multiple | Replacing End of Support Data Centers | Other - IT | Replace | Upgrade/Retrofit | NA | Age/End of Life | Age/Condition | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | NA | NA | NA | T000021 | P000021 | 1 | 925 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-10-14 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | NA | NA | To be Filed | NA | Operational | NA | 2020-09-30 | 2024-12-31 | 2024-12-31 | NA | NA | FALSE | 16033.1912 | NA ¦ NA | 3689.9031 | 1179.2323 | 581.6243 | 415.6746 | 261.4921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2023 ¦ 2024 | 0 | 0 | 957.3909 | 2732.5123 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0%
256 | SDGE LAN Refresh (P) T19005 |  |  | Multiple | Replacing End of Support SDGE IT Network Hardware | Other - IT | Replace | NA | NA | Age/End of Life | Age/Condition | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | NA | NA | NA | T19005 | PT19005 | 1 | 925 | NA ¦ NA ¦ NA ¦ NA | TRUE | NA | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | NA | NA | NA [See Notes] | NA | Operational | NA | 2019-03-15 | 2023-02-28 | 2023-02-28 | NA | NA | FALSE | 4104.536 | NA ¦ NA | 3245.0817 | 661.6256 | 91.0149 | 7.454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 | 3146.6129 | 91.0149 | 7.454 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] Exempt
257 | SDGE WAN Refresh T19027 |  |  | Multiple | Replacing End of Support SDGE IT Network Hardware, Retrofit Communications Towers | Other - IT | Replace | Upgrade/Retrofit | NA | Age/End of Life | System Operations | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | NA | NA | NA | T19027 | PT19027 | 1 | 925 | NA ¦ NA ¦ NA ¦ NA | TRUE | NA | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | NA | NA | To be Filed | NA | Operational | NA | 2019-07-28 | 2024-03-31 | 2024-03-31 | NA | NA | FALSE | 3665.389 | NA ¦ NA | 2416.3344 | 634.0038 | 580.1764 | 21.156 | -0.00028957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2022 ¦ 2023 ¦ 2024 | 0 | 2395.1787 | 21.156 | -0.00028957 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0%
258 | PRIVATE LTE BROADBAND COMMUNICATIONS INI T18018 |  |  | Multiple | Install a Private LTE network to serve HFTD 2 and 3 | Other - Operations Tech | New | Upgrade/Retrofit | NA | Reliability | System Operations | NA | NA | NA | NA | NA | NA | NA | Tier 2 ¦ Tier 3 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | NA | NA | NA | T18018 | PT18018 | 1 | 925 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2018-09-06 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | NA | NA | NA [See Notes] | NA | Operational | NA | 2018-09-27 | 2022-12-31 | 2022-12-31 | NA | NA | FALSE | 16219.699 | NA ¦ NA | 1295.8398 | 99.2211 | 4.0466 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 | 1291.7932 | 4.0466 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] Exempt
259 | SDGE LMR 2027 (P) BD25125 |  |  | Multiple | Project updates/upgrades our switches used to protect and route on the edge of our data center | Other - IT | Replace | Upgrade/Retrofit | NA | Age/End of Life | Age/Condition | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | NA | NA | NA | BD25125 | NA | 1 | 925 | NA ¦ NA ¦ NA ¦ NA | TRUE | NA | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | NA | NA | NA [See Notes] | NA | Planning | NA | NA | NA | NA | NA | NA | FALSE | 1032.0992 | NA ¦ NA | 1027.8812 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1027.8812 | 0 | 0 | 0 | 0 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] Exempt
260 | 2027 SDGE Cisco Enterprise Agreement (P) BD25094 |  |  | Multiple | Project upgrades/updates the network switches that serve our corporate sites. Critical updates are needed to mitigate EOL systems | Other - IT | Replace | Upgrade/Retrofit | NA | Age/End of Life | Age/Condition | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | NA | NA | NA | BD25094 | NA | 1 | 925 | NA ¦ NA ¦ NA ¦ NA | TRUE | NA | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | NA | NA | NA [See Notes] | NA | Planning | NA | NA | NA | NA | NA | NA | FALSE | 1063.1425 | NA ¦ NA | 1062.7623 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1062.7623 | 0 | 0 | 0 | 0 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] Exempt
261 | 2027 SDGE Network Modernization (P) BD25075 |  |  | Multiple | Project updates/upgrades the network switches/routes within our data center. Replaced end of life equipment. | Other - IT | Upgrade/Retrofit | Upgrade/Retrofit | NA | Age/End of Life | System Operations | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | NA | NA | NA | BD25075 | NA | 1 | 925 | NA ¦ NA ¦ NA ¦ NA | TRUE | NA | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | NA | NA | NA [See Notes] | NA | Planning | NA | NA | NA | NA | NA | NA | FALSE | 1898.9064 | NA ¦ NA | 1322.7934 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1322.7934 | 0 | 0 | 0 | 0 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] Exempt
262 | 2027 SDGE DCN Refresh (P) BD24037 |  |  | Multiple | Project updates/upgrades the network switches/routes within our data center. Replaced end of life equipment. | Other - IT | Upgrade/Retrofit | Upgrade/Retrofit | NA | Age/End of Life | System Operations | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | NA | NA | NA | BD24037 | NA | 1 | 925 | NA ¦ NA ¦ NA ¦ NA | TRUE | NA | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | NA | NA | NA [See Notes] | NA | Planning | NA | NA | NA | NA | NA | NA | FALSE | 1213.4625 | NA ¦ NA | 1210.4738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1210.4738 | 0 | 0 | 0 | 0 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] Exempt
263 | TL690E – Camp Pendleton – Wood to Steel |  |  | Camp Pendleton, San Diego | Replace ~72 wood poles with overhead steel poles and/or underground cabling. Reconductor ~5.5 mi from Stuart Tap to Las Pulgas Substation. | Transmission Line - Multiple | Upgrade/Retrofit | Upgrade/Retrofit | NA | Wildfire Mitigation | T-Line Reliability | NERC TPL Standards | NA | 2026-01-11 | 58.5556 | Steady State Power Flow System Analysis | Wires - Reconductor/Line Rebuild Alternative | NA | Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | OPEN, Coastal |  | 5.350611 | NA | 69 | NA | 1.2 | 2014-00050-ZZ | QS00040 | 1 | 10143 | NA ¦ NA ¦ NA ¦ NA | FALSE | NA | Work Order Authorization | 2012 | 2014 | FALSE | 2014 | NA | https://www.caiso.com/planning/Pages/TransmissionPlanning/2013-2014TransmissionPlanningProcess.aspx | FALSE | NA | NA | Exempted | NA | CPUC | MCBCP | Exempt | NA | NA [See Notes] | NA | Permitting | NA | 2029-04-12 | 2015-06-01 | 2030-06-26 | Permitting | Project Design | FALSE | 142840.7251 | NA ¦ NA | 50995.1625 | 1383.3476 | 1527.0309 | 1676.1514 | 1964.336 | 2115.3927 | 619.4686 | 1825.8196 | 2729.4049 | 7491.9335 | 15843.334 | 8024.4471 | 9285.7273 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | 4.8 | NA | 0% | 100% | [Reason for Change in In-Service Date (2)] Designed both underground and overhead options to determine proposed project given lack of input by MCBCP [CPUC Status] Exempt
264 | TL691 Avocado to Camp Pendleton |  |  | Fallbrook, San Diego ¦ Camp Pendleton North, San Diego ¦ Fallbrook Naval Weapons Station | This project replaced approx 140 existing wood poles along TL691 within the Fire Threat Zone with new steel poles and associated hardware. | Transmission Line - Multiple | Replace | NA | NA | Wildfire Mitigation | T-Line Reliability | NA | NA | 2026-01-11 | 50.4247 | NA | NA | NA | Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 11.548521 | NA | 69 | NA | 1.2 | 2014-00051-ZZ | QS00041 | 1 | 10144 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2022-12-19 | Work Order Authorization | 2012 | NA | FALSE | NA | NA | NA | FALSE | NA | 2019-11-01 | Exempted | Categorical Exclusion | CPUC | MCBCP | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2023-04-28 | 2024-02-29 | 2024-01-17 | NA | NA | TRUE | 43446.3952 | NA ¦ NA | 47103.7037 | 3971.736 | 2405.8417 | 28254.1162 | 6952.0503 | 441.8389 | 33.2117 | 19.366 | 0 | 0 | 0 | 0 | 33.2117 | NA | NA | 2024 ¦ 2025 ¦ 2026 | 0 | 0 | 0 | 46609.287 | 441.8389 | 52.5777 | 0% | NA ¦ NA | 4.1 | NA | 0% | 100% | [CPUC Status] Exempt
265 | TL692 Horno Pulgas (Camp Pend) |  |  | Camp Pendleton, San Diego | This project will replace approx 87 existing wood poles along TL692 within the Fire Threat Zone with new steel poles and associated hardware. | Transmission Line - Multiple | Replace | NA | NA | Wildfire Mitigation | T-Line Reliability | NA | NA | 2026-01-11 | 58.9452 | NA | NA | NA | Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 6.653334 | NA | 69 | NA | 1.2 | 2014-00225-ZZ | QS00042 | 1 | 10145 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-02-19 | Work Order Authorization | 2012 | 2015 | FALSE | 2015 | NA | https://www.caiso.com/documents/board-approved2014-2015transmissionplan.pdf | FALSE | NA | 2019-07-19 | Exempted | Categorical Exclusion | CPUC | MCBCP | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2021-05-17 | 2021-11-01 | 2021-11-01 | NA | NA | FALSE | 24755.7706 | NA ¦ NA | 17765.781 | 11169.0268 | 1339.9907 | 43.5217 | 3.2178 | -32.0505 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 16411.1014 | 1339.9907 | 43.5217 | 3.2178 | -32.0505 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
266 | TL695/6971 Talega Cristianitos Japanese (Camp Pend) |  |  | Camp Pendleton, San Diego | Replace ~72 existing poles with 69 new steel poles and install approximately 9.7 miles of 69kV conductor and approximately 2.5 miles of distribution underbuild between Talega Substation to Basilone Substation (TL695) and the prior Japanese Mesa Substation location to Basilone substation (Originally TL6971 but now TL692). Approximately 2.4 miles of TL695 is being rerouted onto an existing tower line occupied by TL99904 (2.5 miles) and that section of TL99904 will become TL692. | Transmission Line - Multiple | Replace | New | NA | Wildfire Mitigation | T-Line Reliability | NERC TPL Standards | NA | 2026-01-11 | 54.7193 | Steady State Power Flow System Analysis | Wires - Reconductor/Line Rebuild Alternative | NA | Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | OPEN, Coastal |  | 7.800761 | NA | 69 | NA | 1.2 | 2014-00074-ZZ | QS00043 | 1 | 10146 | NA ¦ NA ¦ NA ¦ NA | FALSE | NA | Work Order Authorization | 2012 | 2012 | FALSE | 2012 | NA | https://www.caiso.com/planning/Pages/TransmissionPlanning/2011-2012TransmissionPlanningProcess.aspx | FALSE | CEQA Draft Published | 2017-07-07 | IS/MND | EA | CPUC | MCBCP | PTC [A.16-04-022] | 2016-04-25 | Approved | 2018 | Permitting | NA | 2027-06-16 | 2028-01-26 | 2029-03-21 | Permitting | NA | FALSE | 44272.5792 | NA ¦ NA | 66167.0491 | 2875.0483 | 2320.4083 | 1770.8854 | 1940.217 | 1895.8504 | 507.4431 | 2146.7467 | 10274.8036 | 26199.3448 | 8924.3197 | 0 | 18490.3783 | NA | NA | 2023 ¦ 2025 | 0 | 0 | 132.2838 | 0 | -0.82783 | 0 | 0% | NA ¦ NA | 1.4 | NA | 0% | 100%
267 | TL663 Reconductor (Mission Kearny) |  |  | San Diego, San Diego | Construction of this project provides a long term “wires” mitigation for the identified NERC CAT B reliability criteria indications. Availability of the short term non wires option of depending on the pre contingency dispatch of the Kearny gas turbines to provide loading relief is no longer available after 2013. | Transmission Line - Conductor | Upgrade/Retrofit | NA | NA | Local Capacity Requirement | T-Line Capacity | NERC TPL Standards | NA | 2026-02-12 | 29; 61; 39 | Steady State Power Flow System Analysis | Wires - Reconductor/Line Rebuild Alternative | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 6.590164 | NA | 69 | NA | 2.1 | 2011-00018-ZZ | QS00049 | 1 | 11126 | NA ¦ NA ¦ NA ¦ NA | FALSE | NA | Work Order Authorization | 2012 | 2011 | FALSE | 2011 | NA | https://www.caiso.com/planning/Pages/TransmissionPlanning/2010-2011TransmissionPlanningProcess.aspx | FALSE | NA | TBD | Exempted | NA | NA | NA | Other [See Notes] | 2017-05-31 | Approved | 2017 | Operational | NA | 2017-12-13 | 2015-06-01 | 2020-02-26 | Bundling Dependencies | NA | FALSE | 8171.0385 | NA ¦ NA | 39938.6691 | 249.7861 | 550.5743 | 59.2286 | 39.4769 | -1.2863 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 1177.3096 | 590.6773 | 59.2286 | 39.4769 | -1.2863 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
268 | TL644 Reconductor (Bay Blvd Sweetwater) |  |  | National City, San Diego ¦ Chula Vista, San Diego | The purpose of the TL644 Reconductor Project is to improve the reliability of the Transmission System by mitigating potential NERC Category B Criteria violations. The Project will increase the ampacity of TL644 to 204MVA (1,708A) by replacing the single-circuit underground 1750kCMIL aluminum cable to a twin-circuit underground 3000kCMIL copper cable system. Upon completion, the upgrades will mitigate overloads on TL644 in the event of an outage on TL642. | Transmission Line - Conductor | Upgrade/Retrofit | NA | NA | Reliability | T-Line Capacity | NERC TPL Standards | NA | 2026-02-05 | 26; 26 | Steady State Power Flow System Analysis | Wires - Reconductor/Line Rebuild Alternative | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | Coastal |  | 1 | NA | 69 | NA | 2.1 | 2011-00021-ZZ | QS00054 | 1 | 11154 | NA ¦ NA ¦ NA ¦ NA | FALSE | NA | Work Order Authorization | 2012 | 2011 | FALSE | 2011 | NA | https://www.caiso.com/planning/Pages/TransmissionPlanning/2010-2011TransmissionPlanningProcess.aspx | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | Other [See Notes] | NA | Operational | NA | 2021-12-06 | 2013-06-01 | 2022-05-15 | Prioritization | Prioritization | FALSE | 9464.457 | NA ¦ NA | 10760.5085 | 2906.133 | 2524.9442 | 709.313 | 72.0071 | -43.0616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 0 | 10022.2501 | 709.313 | 72.0071 | -43.0616 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
269 | TL639 Wood to Steel Replacement |  |  | San Diego, San Diego | The TL639 Fire Hardening and Reconductor Project consists of installing new steel structures along the 69kV tie line between Elliott Substation and Structure Z100981, located inside Sycamore Canyon. The replacement structures from TL639 Elliott to Structure Z379545 will be constructed in conjunction with TL636, since most of the structures in that portion are single pole double circuit. TL639 Wood to Steel will cover pole replacements starting at Sycamore Canyon Substation to Structure Z379545. The project spans approximately 4.8 miles. | Transmission Line - Multiple | Replace | Upgrade/Retrofit | NA | Wildfire Mitigation | Priority 1 Steel Structure Replacement | NA | NA | 2026-01-11 | 41.7273 | NA | NA | NA | Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 8.176705 | NA | 69 | NA | 1.2 | 2012-00005-ZZ | QS00066 | 1 | 12136 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-09-18 | Work Order Authorization | 2015 | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2022-10-31 | 2024-01-31 | 2023-10-07 | NA | NA | TRUE | 241.5125 | NA ¦ NA | 12765.8997 | 874.9164 | 2296.9075 | 7361.9751 | 894.4513 | 55.4275 | 1.0371 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2022 ¦ 2023 ¦ 2024 ¦ 2025 ¦ 2026 | 0 | 53.9001 | 1.445 | 12654.0899 | 55.4275 | 1.0371 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
270 | TL6916 Wood to Steel Replacement |  |  | San Diego, San Diego | Approximately 5 miles of fire hardening on TL6916 wood to steel project. All existing wood transmission poles will be removed from service/replaced with pre-engineered poles or engineered steel poles and associated distribution wood poles on C434 and C920 will be replaced with steel poles. New conductor 900ACSS will replace existing 900ACSS conductor due to construction and outage constraints of existing configuration. Distribution conductor will be upgraded to 636 and #2 ACSR Conductor. 1-96CT ADSS will be installed from Z678465 to Z100980. 31 new SW poles will be installed along with 12 new engineered steel poles. We predict 9 drilled pier foundations and 3 new micropile foundations will be installed. | Transmission Line - Pole/Tower | Replace | NA | NA | Wildfire Mitigation | T-Line Reliability | NA | NA | 2026-01-11 | 47.8049 | NA | NA | NA | Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 4.767863 | NA | 69 | NA | 1.2 | 2012-00006-ZZ | QS00067 | 1 | 12137 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-07-22 | Work Order Authorization | 2015 | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2022-03-07 | 2022-07-01 | 2022-07-11 | NA | NA | FALSE | 104.0282 | NA ¦ NA | 14656.2394 | 1495.1294 | 11255.3314 | 221.3696 | 64.1849 | -18.8603 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 0 | 14371.4153 | 239.4994 | 64.1849 | -18.8603 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
271 | TL615 TL659 Direct Buried Cable Replacement (Cabrillo Point Loma) |  |  | San Diego, San Diego | Replace approximately six (6) miles of direct buried cable on TL615 and TL659 within the streets of Point Loma into a new double circuit 69kV duct package infrastructure with off-setting substructures in an effort to mitigate reliability issues associated with aging direct buried cable systems. | Transmission Line - Underground | Upgrade/Retrofit | NA | NA | Reliability | Age/Condition | NA | NA | 2026-02-05 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 4 | NA | 69 | NA | 4.1 | 2012-00011-ZZ | QS00068 | 1 | 12138 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-07-03 | Work Order Authorization | 2012 | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | CPUC | NA | Exempt | NA | Other [See Notes] | NA | Construction (25%-50%) | NA | 2024-01-08 | 2026-12-31 | 2026-11-10 | NA | NA | TRUE | 46528 | NA ¦ NA | 86581.0422 | 13695.3243 | 2707.0372 | 4920.9316 | 13359.7809 | 35001.393 | 2673.5858 | 6011.3478 | 0 | 0 | 0 | 0 | 72358.0528 | NA | NA | 2026 | 0 | 0 | 0 | 0 | 0 | 86581.0422 | 0% | NA ¦ NA | 6.00 | NA | 0% | 100% | [CPUC Status] Exempt
272 | TL636 Wood to Steel Replacement |  |  | San Diego, San Diego | Replacing wood pole with steel equivalent from Northern structure at Z200694 to Elliott Substation. The purpose for this project is for fire hardening of this corridor due to it being within the FTZ and classified as high to extreme fire danger. The project spans approximately 6.07 miles. | Transmission Line - Multiple | Replace | Upgrade/Retrofit | NA | Wildfire Mitigation | Priority 1 Steel Structure Replacement | NA | NA | 2026-01-08 | 46.1475 | NA | NA | NA | Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 5.86719 | NA | 69 | NA | 1.2 | 2012-00015-ZZ | QS00071 | 1 | 12144 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2022-05-19 | Work Order Authorization | 2015 | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2022-03-18 | 2022-12-31 | 2022-10-17 | NA | NA | FALSE | 25131.9882 | NA ¦ NA | 21506.2263 | 2745.577 | 15752.6745 | 152.8457 | 100.6546 | -14.0301 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 0 | 21266.7562 | 152.8457 | 100.6546 | -14.0301 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
273 | TL694 Wood to Steel Replacement |  |  | Fallbrook, San Diego ¦ Oceanside, San Diego | Replace 4.8 miles, approximately 80 wood structures, to direct-embed and engineered steel poles and replace the existing 636 ASCR/AW conductor to harden the electric transmission and distribution systems and increase reliability in the region. This project will also mitigate some existing access issues to the structures. | Transmission Line - Pole/Tower | Replace | NA | NA | Wildfire Mitigation | T-Line Reliability | NA | NA | 2026-01-29 | 61.4051 | NA | NA | NA | Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 4.85 | NA | 69 | NA | 1.2 | 2012-00014-ZZ | QS00073 | 1 | 12149 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-11-06 | Work Order Authorization | 2015 | NA | FALSE | NA | NA | NA | FALSE | TBD | NA | Exempted | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Construction (50%-75%) | NA | 2026-02-11 | 2020-12-31 | 2027-01-04 | Project Design | NA | TRUE | 36464.0897 | NA ¦ NA | 27417.4031 | 720.4648 | 576.5602 | 639.7541 | 2933.1438 | 3797.7143 | 1625.4468 | 13075.1287 | 2097.9537 | 0 | 0 | 0 | 12244.3208 | NA | NA | 2026 | 0 | 0 | 0 | 0 | 0 | 25319.4495 | 0% | NA ¦ NA | 11.6 | NA | 0% | 100% | [CPUC Status] Exempt
274 | TL13831 Wood to Steel Replacement (Talega Racho Mission Viejo) |  |  | Orange County | The purpose of project is to replace approximately 72 wood poles for steel equivalent from Rancho Mission Viejo to Talega Substation for fire hardening. The project spans approximately 6.46 miles. | Transmission Line - Multiple | Replace | Upgrade/Retrofit | NA | Wildfire Mitigation | Priority 1 Wood Structure Replacement | NA | NA | 2026-02-14 | 29.2055 | NA | NA | NA | Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 6.377019 | NA | 138 | NA | 1.2 | 2012-00019-ZZ | QS00074 | 1 | 12150 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-12-05 | Work Order Authorization | 2015 | NA | FALSE | NA | NA | NA | FALSE | NA | Stat Ex | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2022-08-15 | 2024-12-30 | 2023-04-23 | NA | NA | FALSE | 317.2364 | NA ¦ NA | 21783.74 | 2288.5516 | 11949.8744 | 5638.7274 | 101.9908 | 37.0138 | -0.088349 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 ¦ 2026 | 2280.3549 | 11932.3906 | 5667.4972 | 101.9908 | 37.0138 | -0.088349 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
275 | TL13838 Wood to Steel Replacement (Magarita Rancho Mission Viejo) |  |  | Orange County | This project replaces nine poles with steel, approximately 1.4 miles of 1033.5ACSR/AW, insulators and hardware. | Transmission Line - Multiple | Replace | Upgrade/Retrofit | NA | Wildfire Mitigation | Priority 1 Steel Structure Replacement | NA | NA | 2026-02-01 | 29; 29; 29; 29; 8; 29; 29; 29; 11; 2 | NA | NA | NA | Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 1.674834 | NA | 138 | NA | 1.2 | 2012-00020-ZZ | QS00075 | 1 | 12152 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-11-06 | Work Order Authorization | 2015 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2021-09-24 | 2024-12-30 | 2022-01-17 | NA | NA | FALSE | 249.9409 | NA ¦ NA | 2573.9917 | 1149.8398 | 408.9902 | 232.709 | 1.4772 | -5.3943 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 1146.3368 | 412.4949 | 232.709 | 1.4772 | -5.3943 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
276 | TL600 Reliability Pole Replacements |  |  | San Diego, San Diego | This project replaces 32 transmission and 1 distribution structures to current standards on TL600 across 3 phases of work. | Transmission Line - Pole/Tower | Replace | Upgrade/Retrofit | NA | Reliability | T-Line Reliability | NA | NA | 2026-02-12 | 56.1429 | NA | Wires - Reconductor/Line Rebuild Alternative | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 3.999067 | NA | 69 | NA | 4.1 | 2012-00023-ZZ | QS00077 | 1 | 12156 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-10-06 | Work Order Authorization | 2015 | NA | FALSE | NA | NA | NA | FALSE | Expected PEA Completion | TBD | Exempted | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2013-02-01 | 2021-04-30 | 2022-08-29 | Vendor Quality/Delays | Workforce | FALSE | 1260.0786 | NA ¦ NA | 8321.3284 | 1913.5322 | 1043.6201 | 406.0304 | 465.9009 | 25.1555 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 0 | 6109.9589 | 406.0304 | 465.9009 | 25.1555 | 0 | 93% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
277 | TL674A Loop in Del Mar |  |  | Del Mar, San Diego ¦ Solano Beach, San Diego ¦ San Diego, San Diego | Eliminate the need for ongoing O&M work in environmentally sensitive areas (San Dieguito Lagoon, Torrey Pines State Park and Los Penasquitos Lagoon) by removing TL666D from service (Phase IV). Install a new underground 69kV transmission line segment along Via de la Valle, which will provide a new TL connecting the Del Mar Substation to the North City West Substation. This will replace the existing TL 674A tap that will be eliminated in Phase II as part of the Rancho Santa Fe Tap reconfiguration. | Transmission Line - Multiple | Upgrade/Retrofit | Relocate | NA | Reliability | Environmental | NA | NA | 2026-01-27 | NA | Steady State Power Flow System Analysis | Wires - Replacement Alternative | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 7.248895 | NA | 69 | NA | 2.1 | 2013-00010-ZZ | QS00082 | 1 | 13130 | NA ¦ NA ¦ NA ¦ NA | FALSE | NA | Work Order Authorization | 2015 | 2013 | FALSE | 2013 | NA | https://www.caiso.com/planning/Pages/TransmissionPlanning/2012-2013TransmissionPlanningProcess.aspx | FALSE | Final Certified | 2019-03-21 | IS/MND | NA | CPUC | NA | PTC [A.17-06-029] | 2017-06-28 | Approved | 2019 | Operational | NA | 2020-12-30 | 2015-06-01 | 2023-12-15 | Permitting | NA | TRUE | 17532.6862 | NA ¦ NA | 28109.9114 | 3327.1239 | 16089.0943 | 1267.4146 | 167.5427 | -18.1953 | 0.0014441 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2022 ¦ 2023 ¦ 2024 ¦ 2025 ¦ 2026 | 0 | 26693.2096 | 1267.4146 | 167.5427 | -18.1953 | 0.0014441 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
278 | CBM Gas Breakers |  |  | Multiple | This project is a continuing effort to sustain GCB SF6 Tracking and implement Condition Based Maintenance by installing monitors on approximately 900 Gas Circuit Breakers (GCBs). | Substation - Circuit Breaker | Replace | NA | NA | Reliability | Age/Condition - Replace Breakers | NA | NA | NA | NA | NA | NA | NA | Tier 1 ¦ Tier 2 ¦ Tier 3 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69 ¦500 | NA | 4.3 | 2014-00186-ZZ | QS00086 | 1 | 13139 | 2026-06-17 ¦ NA ¦ NA ¦ NA | TRUE | 2020-09-21 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | NA | NA | NA [See Notes] | NA | Operational | NA | 2020-02-10 | 2025-12-31 | 2026-06-30 | NA | NA | TRUE | 2971.124 | NA ¦ NA | 34204.4932 | 5194.7858 | 2671.1227 | 2323.3223 | 2073.2266 | 1959.9925 | 404.0361 | 324.6273 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 ¦ 2026 | 3570.9276 | 3687.4675 | 1351.3365 | 917.8003 | 12476.7594 | 728.6634 | 0% | NA ¦ NA | NA ¦ NA | NA | 45.85% | 54.15% | [CPUC Status] Exempt
279 | Streamview |  |  | San Diego, San Diego | Initially expand the existing 69 ¦12 kV substation from two to three banks to increase capacity on the system, with future expansion to four banks. | Transmission Line/Substation | Replace | New | NA | Reliability | Age/Condition | NA | NA | 2026-04-26 | 22; 55; 22; 53; 7; 3 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 0.388157 | 69 | 12kV¦69kV ¦28MVA | 4.2 | 2014-00062-ZZ | QS00089 | 1 | 13244 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-12-19 | Work Order Authorization | 2015 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Construction (50%-75%) | NA | 2020-03-11 | 2027-05-31 | 2030-07-18 | Workforce | Multiple Options [See Notes] | TRUE | 543 | NA ¦ NA | 48463.9667 | 761.4417 | 3181.6008 | 2184.3822 | 10982.4692 | 10453.5405 | 2861.589 | 8522.0194 | 2608.0804 | 0 | 0 | 0 | 3497.8763 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2025 ¦ 2026 | 3622.8086 | 299.6637 | 33.7723 | 0 | 29879.7459 | 6905.3754 | 0% | NA ¦ NA | 5.16 | NA | 0% | 100% | [Reason for Change in In-Service Date] Construction Delays ¦ Land Rights ¦ Permitting [CPUC Status] Exempt
280 | Artesian 230kV Sub Expansion |  |  | San Diego, San Diego | Per the CAISO 2013-2014 Final Plan, SDG&E will expand the existing 69 ¦12kV Artesian Substation to a 230 ¦69 ¦12kV Substation (Artesian East Substation) to alleviate the existing 69kV congestion at Sycamore Canyon Substation. In addition, the project will help mitigate Cat B contingencies and increase reliability to the Poway Area Load Pocket which is expected to grow by as much as 12% in the next 10 years. The project will be built on existing SDG&E Artesian Substation land and adjacent land east of the current substation site, also owned by SDG&E. Transmission work includes the loop-in of TL23051 (SX-PEN), terminating TL616C into the Artesian 69kV substation to form two (2) 69 kV Artesian - Bernardo lines; reconductoring both Artesian - Bernardo lines to achieve a 145 ¦179 rating (TL6939 & segment of TLNew), and replacing underground getaways at Artesian, Bernardo, Rancho Carmel, and Poway to achieve new ratings. Permitting and Environmental will be required for the expanded 230 ¦69 ¦12kV substation, in addition to the reconductor work associated with the project. | Substation - Multiple | Upgrade/Retrofit | NA | NA | Reliability | Substation Capacity | NERC TPL Standards | NA | 2026-05-22 | 22; 22; 22; 16; 24; 16; 24; 16; 24; 16; 16 | Steady State Power Flow System Analysis | Wires - Bus Upgrade Alternative | NA | Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 1.937683 | 230 | 69kV¦230kV¦224MVA | 2.1 | 2014-00056-ZZ | QS00099 | 1 | 14128 | NA ¦ NA ¦ NA ¦ NA | FALSE | NA | Work Order Authorization | 2015 | 2014 | FALSE | 2014 | NA | https://www.caiso.com/planning/Pages/TransmissionPlanning/2013-2014TransmissionPlanningProcess.aspx | FALSE | Final Certified | 2019-03-22 | IS/MND | NA | CPUC | NA | PTC [A.16-08-010] | 2019-10-07 | Approved | 2019 | Operational | NA | 2020-04-17 | 2016-06-01 | 2022-12-04 | Construction Delays | NA | TRUE | 17140 | NA ¦ NA | 131931.1772 | 32690.8213 | 20376.5233 | 1653.6356 | 1245.4533 | 0.63734 | 115.6057 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 ¦ 2026 | 50361.7741 | 74652.8038 | 1653.6356 | 1245.4533 | 0.63734 | 115.6057 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0%
281 | TL6975 Escondido San Marcos |  |  | San Marcos, San Diego ¦ Carlsbad, San Diego ¦ Lake San Marcos, San Diego ¦ Escondido, San Diego | Segment 1: Rebuild approximately 1.8 miles of an existing 69kV circuit (TL 680C) to create a double circuit from San Marcos Substation to Melrose Tap. Construction at San Marcos Substation including installation of a new circuit breaker par, seven piers, and an A-frame for the new line. Along Segment 1, all wood pole structures would be replaced with steel poles; porcelain insulators would be replaced with polymer insulators. Segment 2: Construct 2.8 miles of new single-circuit 69kV overhead power line on new steel poles in the existing transmission corridor from Melrose Tap to Meadowlark Junction adjacent to existing TL 13811/13825 power line, approximately 50-feet east of the centerline of the existing structures. Segment 3: Transition new line (described under Segment 2, above) and reconductor approximately 7.4 miles of power line; remove and replace existing copper conductors with new 636 ACSS/AW conductors and existing porcelain insulators with polymer insulators; construction at the existing Escondido Substation to accommodate new circuit. | Transmission Line - Multiple | New | NA | NA | Load Growth | New T-Line | NERC TPL Standards | NA | 2026-01-29 | NA | Steady State Power Flow System Analysis | Wires - New T-Line Alternative | NA | Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 11.903558 | NA | 69 | 69kV | 2.1 | 2014-00078-ZZ | QS00101 | 1 | 14137 | NA ¦ NA ¦ NA ¦ NA | FALSE | NA | Work Order Authorization | 2015 | 2014 | FALSE | 2014 | NA | https://www.caiso.com/planning/Pages/TransmissionPlanning/2013-2014TransmissionPlanningProcess.aspx | FALSE | Expected PEA Completion | 2018-03-16 | IS/MND | NA | NA | NA | PTC [A.17-11-010] | 2017-11-15 | Approved | 2020 | Operational | NA | 2021-10-19 | 2015-06-01 | 2023-02-28 | Permitting | Land Rights | FALSE | 5626.42 | NA ¦ NA | 52262.4335 | 9221.2832 | 32210.4332 | 2820.3867 | 1777.4885 | 13.3136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 529.1659 | 332.0915 | 49610.3741 | 1777.4885 | 13.3136 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
282 | TL698 W2S PROJECT |  |  | Fallbrook, San Diego | The TL698 Fire Hardening & Reconductor Project consists of replacing existing structures and installing new steel structures along the 69kV tie line 698 in FTZ from Z10213, north of Monserate Substation, to structure Z293941, south of Avocado Substation, with new light duty and heavy engineered steel poles. This project is needed to mitigate loss of service due to wildfires by replacing existing wood poles with new steel structures. The new steel poles shall be designed to 138kV specifications and accommodate existing and future 12kV distribution underbuild and communications circuits. TL698 is located within existing easements. TL698 will be designed for (3)-636 ACSS/AW conductors and the existing 336 ACSR/AW conductors will be retired. There will be one SDG&E 96-count ADSS and one position for a third party installed along the line from Z10212 to Z293941. Additional installs: P219762J Removals: P253660S, Z208037S, P253653S | Transmission Line - Pole/Tower | Replace | NA | NA | Wildfire Mitigation | 3rd Party Damage | NA | NA | 2026-01-06 | 48.6154 | NA | NA | NA | Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 5.16 | NA | 69 | NA | 1.2 | 2014-00009-ZZ | QS00103 | 1 | 14140 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2025-04-30 | Work Order Authorization | 2023 | NA | FALSE | NA | NA | NA | FALSE | PEA Deemed Complete | NA | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2023-11-01 | 2024-08-31 | 2024-08-23 | NA | NA | FALSE | 28671.0689 | NA ¦ NA | 21125.6873 | 525.7454 | 1287.7238 | 5494.102 | 10217.1935 | 2249.3202 | -162.104 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 ¦ 2026 | 2039.4517 | 1287.3471 | 3337.4987 | 12374.1735 | 2249.3202 | -162.104 | 0% | NA ¦ NA | 8 | NA | 0% | 100% | [CPUC Status] Exempt
283 | Poway 69kV Substation Rebuild |  |  | Poway, San Diego | The purpose of this project is to rebuild Poway Substation to a low profile distribution substation with an ultimate capacity of 120MVA. The current substation consists of aging infrastructure, no SCADA control, and a control shelter that cannot accommodate new panels for any SCADA upgrades. Adding SCADA control and replacing old equipment will increase the reliability of this sub and allow room for any future expansion. Substation, Transmission, and Distribution work are required for this rebuild. Installing SCADA to Poway Sub will increase reliability by giving Mission Control remote access to operate the equipment. Replacing aging infrastructure also increases reliability. Building a new control shelter allows for any future expansion. | Substation - Multiple | Upgrade/Retrofit | Removal | NA | Reliability | Age/Condition | NA | NA | 2026-05-21 | 25; 32; 48; 32; 49; 51 | NA | Wires - Minimum Required Scope (spot repair) Alternative | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 0.369559229 | 69 | 120MVA | 4.1 | 2014-01061-ZZ | QS00104 | 1 | 14143 | 2026-06-17 ¦ 2017-0095 ¦ NA ¦ NA | TRUE | 2019-04-03 | Work Order Authorization | 2015 | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2020-08-10 | 2023-03-31 | 2022-04-22 | NA | NA | FALSE | 1727.9587 | NA ¦ NA | 21951.9132 | 389.6282 | 804.5641 | 10.3026 | -16.3174 | -2.4867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 2.4422 | 1398.6141 | 10.3026 | -16.3174 | -2.4867 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
284 | HATS Legacy Work Order |  |  | San Diego, San Diego | The Helicopter Access for Transmission Structures (HATS) program will facilitate ongoing compliance and safe and efficient operations and maintenance of the transmission system by addressing helicopter access constraints. It involves installation of two types of helicopter landing facilities at various locations along Company’s transmission system. One type is a Tower Staging Access Pad (TSAP) which is a level, bare ground area cleared and maintained of vegetation used for intermittent landing of Company or authorized contractor helicopters. The other type is an engineered structural steel helicopter landing platform (Platform or HLP) used for intermittent landing of Company or authorized contractor helicopters. These facilities are generally located in steep, rugged and mountainous terrain and are necessary due to lack of available roads for vehicle access and will assist in the safe and efficient maintenance and operation of electric transmission facilities. | Other | New | NA | NA | Safety | Safety - Line Right of Way Access | NA | NA | NA | 45 | NA | NA | NA | Tier 3 ¦ Zone 1 | FALSE ¦ FALSE ¦ TRUE | FALSE | NA |  | NA | NA | 230 ¦ 500 | NA | 1.3 | 2014-00060-ZZ | QS00105 | 1 | 14145 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-01-27 | Work Order Authorization | 2015 | 2019 | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2019-06-24 | 2021-12-31 | 2020-12-28 | NA | NA | FALSE | 499 | NA ¦ NA | 15069.4956 | 4215.1246 | -185.8243 | 0 | 0 | -16.8794 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2025 | 4215.1246 | -185.8243 | 0 | 0 | -16.8794 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0% | [Wildfire Related] HATS program has a secondary benefit of wildfire response capabilities [CPUC Status] Exempt
285 | Rancho Santa Fe Substation Fire Hardening |  |  | Rancho Santa Fe, San Diego | The Rancho Santa Fe Substation fire hardening project will consist of removing the aging 69/4 kV substation, cutting it over to existing 12 kV circuits, replacing aging infrastructure on the 12kV and 69 kV equipment, replacing the 12 kV circuit getaways, replacing the 12.5 MVA 69/12 kV spare with a 28 MVA transformer, and installing distribution SCADA | Substation - Multiple | Upgrade/Retrofit | NA | NA | Reliability | Substation Reliability | NA | NA | 2026-05-12 | 66; 71; 63 | NA | Wires - Minimum Required Scope (spot repair) Alternative | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.120944 | NA | 69 | 69kV | 1.2 | 2014-00289-ZZ | QS00123 | 1 | 15246 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-03-05 | Work Order Authorization | 2015 | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2017-07-10 | 2020-11-18 | 2020-11-18 | NA | NA | FALSE | 5719.0763 | NA ¦ NA | 7912.6428 | 1461.0882 | 8.9299 | 0 | 0 | -24.4083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2025 | 7548.5966 | 8.9299 | 0 | 0 | -24.4083 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
286 | Mid Coast Trolley Electric |  |  | San Diego, San Diego | Mid-Coast: As part of SANDAGs Mid Coast Trolley Extension Project, SDG&E will be relocating multiple electric and gas services from the Santa Fe Depot in downtown San Diego to the University City community. | Transmission Line - Multiple | Relocate | NA | NA | Work Requested by Others | Facility Relocation | NA | NA | 2026-01-29 | 34.875 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 4.21246 | NA | 69 | NA | 3.1 | 2015-00016 | QS00125 | 1 | 15258 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-04-12 | Work Order Authorization | 2017 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2016-10-03 | 2022-02-03 | 2022-08-17 | Construction Delays | Other [See Notes] | FALSE | 8347.5827 | NA ¦ NA | 7394.5855 | 1272.7225 | 2232.3897 | 392.8702 | 5.7645 | -3.7318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 165.6965 | 3503.5331 | 392.8702 | 5.7645 | -3.7318 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [Reason for Change in In-Service Date (2)] Design complexity [CPUC Status] Exempt
287 | TL605 Reconductor (Silvergate Urban) |  |  | San Diego, San Diego | Reconductor TL605 with 2-636ACSS (200MVA) or equivalent Note: there is an active project (ID:2015-00013; budget code: 16158) with ISD of 6/26/2024. This new summited cost request is to upgrade the current design line rating from 137 MVA to 200MVA | Transmission Line - Conductor | Upgrade/Retrofit | NA | NA | Local Capacity Requirement | Line Reconductoring | NERC TPL Standards | NA | 2026-01-06 | 17 | Steady State Power Flow System Analysis | Wires - Reconductor/Line Rebuild Alternative | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | Coastal |  | 2 | NA | 69 | NA | 2.1 | 2015-00013 | QS00144 | 1 | 16158 | NA ¦ NA ¦ NA ¦ NA | FALSE | NA | Work Order Authorization | 2017 | 2016 | FALSE | 2016 | NA | https://www.caiso.com/planning/Pages/TransmissionPlanning/2015-2016TransmissionPlanningProcess.aspx | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | Other [See Notes] | NA | Operational | NA | 2024-01-15 | 2018-06-01 | 2024-11-20 | ISO Action | ISO Action | FALSE | 545 | NA ¦ NA | 32517.7367 | 5495.897 | 773.0469 | 8170.9024 | 15142.4978 | 2343.8949 | -13.4636 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2024 ¦ 2025 ¦ 2026 | 0 | 0 | 0 | 30129.8042 | 2401.3962 | -13.4636 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
288 | TL632A Loop In (Granite) |  |  | El Cajon, San Diego ¦ Crest, San Diego ¦ Granite Hills, San Diego | Convert TL632 from a tap into Granite Substation to a loop-in. Based on routing study, underground along La Cresta Rd to Granite Substation is most feasible route. 1.9 miles of 69kV underground. | Transmission Line - Multiple | Replace | NA | NA | Reliability | T-Line Reliability | NERC TPL Standards | NA | 2026-01-27 | 19 | Steady State Power Flow System Analysis | Wires - System Configuration Alternative | $10 Mil -$15 Mil | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 2.5 | NA | 69 | NA | 2.1 | 2015-00005 | QS00158 | 1 | 17125 | NA ¦ NA ¦ NA ¦ NA | FALSE | NA | Work Order Authorization | 2017 | 2015 | FALSE | 2015 | NA | https://www.caiso.com/planning/Pages/TransmissionPlanning/2014-2015TransmissionPlanningProcess.aspx | FALSE | TBD | NA | Exempted | NA | CPUC | NA | AL [4597-E] | 2025-01-30 | Approved | 2025 | Construction (over 75%) | NA | 2025-09-02 | 2017-06-01 | 2026-12-17 | Project Design | NA | TRUE | 14057.888 | NA ¦ NA | 43933.6105 | 333.8327 | 325.5874 | 7751.4818 | 1404.4027 | 10473.3558 | 4057.4308 | 15633.5019 | 1774.0542 | 0 | 0 | 0 | 24346.0911 | NA | NA | 2026 | 0 | 0 | 0 | 0 | 0 | 613.6498 | 0% | NA ¦ NA | 3.4 | NA | 0% | 100%
289 | TL611 Direct Buried Cable Replacement (Old Town Point Loma) |  |  | San Diego, San Diego | Direct-Buried Cable Replacement (Approx. 1-mile trench and substructures) | Transmission Line - Underground | Upgrade/Retrofit | NA | NA | Reliability | Age/Condition | NA | NA | 2026-02-04 | 58; 58 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 2 | NA | 69 | NA | 4.1 | 2012-00002-ZZ | QS00720 | 1 | 17127 | 2026-06-17 ¦ 2012-0002-ZZ ¦ NA ¦ NA | TRUE | 2023-11-25 | Work Order Authorization | 2017 | NA | FALSE | NA | NA | NA | FALSE | TBD | NA | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Engineering less than 50% complete | NA | 2027-08-10 | 2026-12-31 | 2027-12-31 | Outage | Outage | TRUE | 28043.924 | NA ¦ NA | 26176.3416 | 0 | 0 | 112.2093 | 948.6228 | 6396.9193 | 390.0786 | 10645.0645 | 7683.4472 | 0 | 0 | 0 | 7847.8299 | NA | NA | 2026 | 0 | 0 | 0 | 0 | 0 | 18492.8944 | 0% | NA ¦ NA | 3.4 | NA | 0% | 100% | [CPUC Status] Exempt
290 | TL603 Loop in (Sweetwater, National City, and Naval Station Metering) |  |  | National City, San Diego | Open Sweetwater Tap and make TL603D and TL603B one continuous 69kV line from national City to Sweetwater. | Transmission Line - Multiple | Replace | NA | NA | Reliability | T-Line Reliability | NERC TPL Standards | NA | 2026-02-12 | NA | Steady State Power Flow System Analysis | Wires - System Configuration Alternative | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 2 | NA | 69 | NA | 2.1 | 2015-00066 | QS00159 | 1 | 17129 | NA ¦ NA ¦ NA ¦ NA | FALSE | NA | Work Order Authorization | 2017 | 2013 | FALSE | 2013 | NA | https://www.caiso.com/planning/Pages/TransmissionPlanning/2012-2013TransmissionPlanningProcess.aspx | FALSE | TBD | NA | Exempted | NA | CPUC | NA | Exempt | NA | Other [See Notes] | 2025 | Construction (25%-50%) | NA | 2022-11-29 | 2017-06-01 | 2026-11-20 | Permitting | Permitting | TRUE | 13584.367 | NA ¦ NA | 46576.9484 | 5306.3214 | 210.5866 | 681.428 | 835.5795 | 11257.0218 | 6361.6607 | 19347.831 | 0 | 0 | 0 | 0 | 24652.598 | NA | NA | 2026 | 0 | 0 | 0 | 0 | 0 | 46576.9484 | 0% | NA ¦ NA | 4.3 | NA | 0% | 100% | [CPUC Status] Exempt
291 | TL690 Direct Buried Cable Replacement (Oceanside Oceanside Tap) |  |  | Oceanside, San Diego ¦ Camp Pendleton South, San Diego | Direct-Buried Cable Replacement. Approx. 1-mile trench and substructures. | Transmission Line - Underground | Replace | NA | NA | Reliability | Age/Condition | NA | NA | 2026-01-11 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 1.5 | NA | 69 | NA | 4.1 | 2014-00017-ZZ | QS00163 | 1 | 17142 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-08-31 | Work Order Authorization | 2017 | NA | FALSE | NA | NA | NA | FALSE | TBD | NA | Exempted | NA | CPUC | NA | TBD | 2027-06-14 | Other [See Notes] | TBD | On Hold | NA | NA | 2028-11-13 | NA | NA | NA | FALSE | 905.761 | NA ¦ NA | 1058.4019 | 0 | 0 | 0 | 127.688 | 160.9325 | 0 | 0 | 0 | 0 | 0 | 0 | 922.9809 | NA | NA | 2024 ¦ 2025 | 0 | 0 | 0 | 140.9282 | -5.5072 | 0 | 0% | NA ¦ NA | 2.6 | NA | 0% | 100% | [CPUC Status] TBD
292 | TL628 Direct Buried Cable Replacement (Rancho Del Rey & H St.) |  |  | Chula Vista, San Diego | Direct-Buried Cable Replacement | Transmission Line - Underground | New | NA | NA | Reliability | Age/Condition | NA | NA | 2026-01-27 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 2 | NA | 69 | NA | 4.1 | 2017-0021 | QS00164 | 1 | 17143 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2018-09-04 | Work Order Authorization | 2018 | NA | FALSE | NA | NA | NA | FALSE | TBD | NA | Exempted | NA | CPUC | NA | TBD | NA | Other [See Notes] | TBD | On Hold | NA | 2027-12-02 | 2021-04-01 | 2028-03-17 | NA | NA | FALSE | 360 | NA ¦ NA | 1296.3802 | 15.6756 | 54.4923 | 45.6665 | 8.6489 | -6.923 | 0 | 0 | 0 | 0 | 0 | 0 | 1296.3802 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | 3.7 | NA | 0% | 100% | [CPUC Status] TBD
293 | TL697 Direct Buried Cable Replacement (Oceaside Sub Getaway) |  |  | Oceanside, San Diego | Direct-Buried Cable Replacement | Transmission Line - Underground | Upgrade/Retrofit | NA | NA | Reliability | Age/Condition | NA | NA | 2026-02-03 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.5 | NA | 69 | NA | 4.1 | 2017-0025 | QS00167 | 1 | 17147 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-06-05 | Work Order Authorization | 2017 | NA | FALSE | NA | NA | NA | FALSE | TBD | NA | Exempted | NA | CPUC | NA | TBD | 2027-03-24 | Other [See Notes] | TBD | On Hold | NA | NA | 2027-12-31 | NA | NA | NA | FALSE | 1500.416 | NA ¦ NA | 3780.1522 | 0 | 0 | 0 | 0 | -1.0102 | 0 | 0 | 3424.89 | 0 | 0 | 0 | 355.2622 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | 8.1 | NA | 0% | 100% | [CPUC Status] TBD
294 | TL667 Direct Buried Cable Replacement (El Camino Real) |  |  | San Diego, San Diego | Direct-Buried Cable Replacement | Transmission Line - Underground | Replace | NA | NA | Reliability | Age/Condition | NA | NA | 2026-02-05 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 5 | NA | 69 | NA | 4.1 | 2017-0022 | QS00169 | 1 | 17151 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2017-09-18 | Work Order Authorization | 2018 | NA | FALSE | NA | NA | NA | FALSE | TBD | NA | Exempted | NA | NA | NA | TBD | 2024-12-26 | Other [See Notes] | TBD | On Hold | NA | 2027-11-05 | 2020-12-31 | 2028-01-26 | NA | NA | FALSE | 15490.906 | NA ¦ NA | 1881.475 | 23.9228 | 23.2003 | 23.4068 | 13.9001 | -1.9623 | 0 | 0 | 0 | 0 | 0 | 0 | 1881.475 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | 11 | NA | 0% | 100% | [CPUC Status] TBD
295 | TL673 Direct Buried Cable Replacement (Rose Canyon La Jolla) |  |  | San Diego, San Diego | Currently TL673 consist entirely of aging 69kV direct-buried cable from Rose Canyon to La Jolla substations at approximately three miles. This existing direct-buried cable is of 1967 vintage year and has far exceeded its designed operational expectancy of 30 years. Transmission Engineering anticipates an increase rate in outages caused by failures on this existing aging cable system in the near future. This project will replace all existing direct-buried cable from Rose Canyon to La Jolla substations within a newly constructed underground trench conduit package and substructures which will improve electric transmission reliability to the La Jolla area as well as resolve the ongoing maintenance issue for TL673. | Transmission Line - Underground | Upgrade/Retrofit | NA | NA | Reliability | Age/Condition | NA | NA | 2026-01-11 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 5 | NA | 69 | NA | 4.1 | 2017-0023 | QS00170 | 1 | 17152 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2022-12-13 | Work Order Authorization | 2018 | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2021-07-26 | 2023-06-30 | 2023-06-30 | NA | NA | FALSE | 2600 | NA ¦ NA | 64053.9995 | 13885.5181 | 19644.0673 | 15451.8939 | -48.4234 | 209.9562 | -37.8524 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 ¦ 2026 | -170.835 | 244.5547 | 58056.242 | -48.4234 | 209.9562 | -37.8524 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
296 | Avocado Substation 69kV Rebuild |  |  | San Diego, San Diego | Substation Rebuild, Transformers, Control Shelter & Relays & CS equipment, expanded the substation, change out 69kV circuit breakers, PT, and disconnects. | Substation - Multiple | Upgrade/Retrofit | NA | NA | Reliability | Substation Reliability | NA | NA | 2026-04-09 | 51; 51; 62 | NA | Wires - Replacement Alternative | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 3.128295 | 1.719191 | 69 | 60MVA | 2.1 | 2014-00941-ZZ | QS00171 | 1 | 17153 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2022-06-28 | Work Order Authorization | 2017 | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2018-09-17 | 2021-10-14 | 2020-11-16 | NA | NA | FALSE | 2020 | NA ¦ NA | 16715.2497 | 2428.5638 | 3.1856 | 0 | 179.3453 | -62.9744 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2024 ¦ 2025 | 16499.6679 | 3.1856 | 0 | 179.3453 | -62.9744 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
297 | TL662 TL666 Reliability Project |  |  | San Diego, San Diego | Project involves installing two new retaining walls to mitigate potential landslide risk for overhead electric poles within existing SDG&E utility easement located in Torrey Pines. | Other - Civil | Replace | NA | NA | Safety | Age/Condition | NA | NA | 2026-03-19 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69 | NA | 4.1 | 2023-3558 | QS00196 | 1 | 18126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2018-02-21 | Work Order Authorization | 2024 | NA | FALSE | NA | NA | NA | FALSE | TBD | NA | NA | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Engineering more than 50% complete | NA | 2027-08-03 | 2021-12-31 | 2028-01-24 | Scope Change | NA | TRUE | 6808.179 | NA ¦ NA | 7750.2445 | 157.1544 | 259.0357 | 82.0949 | 5.7561 | 845.0342 | 216.7452 | 494.1075 | 5312.334 | 0 | 0 | 0 | 216.7452 | NA | NA | 2024 ¦ 2025 ¦ 2026 | 0 | 0 | 0 | 882.0236 | 845.0342 | 710.8527 | 0% | NA ¦ NA | 4.2 | NA | 0% | 100% | [CPUC Status] Exempt
298 | Escondido Substation 230kV Rebuild |  |  | Escondido, San Diego | The Escondido 230kV rebuild includes: replacing aging equipment, bringing the substation up to current seismic standards and upgrading the undersized bus. The rebuild will also replace existing control shelter and will make room within the substation to accommodate new bay additions. | Substation - Multiple | Replace | Upgrade/Retrofit | NA | Reliability | Substation Reliability | NA | NA | 2026-05-20 | 41; 45; 47; 17; 17; 17; 24; 17; 17; 25; 25 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 4.66311 | 230 | 230kV | 4.1 | 2024-4134 | QS00197 | 1 | 18127 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-05-18 | Work Order Authorization | 2018 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | NA | NA | TBD | TBD | Other [See Notes] | TBD | Planning | NA | 2028-05-17 | 2022-12-31 | 2033-06-30 | Project Design | NA | FALSE | 982 | NA ¦ NA | 198080.2038 | 5.867 | 14.0554 | 45.3664 | 87.018 | 848.9175 | 226.1182 | 15227.9733 | 26646.9671 | 42948.1932 | 45126.8016 | 43308.7086 | 24821.56 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | 1.6 | NA | 100% | 0% | [CPUC Status] TBD
299 | Mission 69kV Sub Rebuild |  |  | San Diego, San Diego | Install shoo-flys for TL618, TL663 & TL13822 in conflict and replace 69kV AIS with a GIS | Substation - Multiple | Replace | Upgrade/Retrofit | NA | Reliability | Substation Reliability | NA | NA | 2026-05-28 | 52 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 8.996664 | 69 ¦ 138 | 69kV | 4.1 | 2019-1012 | QS00198 | 1 | 18128 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-02-01 | Work Order Authorization | 2018 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2022-12-05 | 2025-12-01 | 2026-04-12 | NA | NA | TRUE | 97625.0096 | NA ¦ NA | 137230.8549 | 821.6072 | 16116.6832 | 27651.0585 | 39500.8664 | 37659.2638 | 4939.3065 | 10491.7573 | 0 | 0 | 0 | 0 | 5897.5721 | NA | NA | 2023 ¦ 2025 ¦ 2026 | 0 | 0 | 1.9299 | 0 | 120841.5255 | 16387.3994 | 0% | NA ¦ NA | 1.3 | NA | 0% | 100% | [CPUC Status] Exempt
300 | Skills Training Center – Transmission Yard Expansion |  |  | San Diego, San Diego | The purpose of this project is to expand the transmission yard at Skills Training Center for crews to train safely on. A new OH potion will be installed, along with an UG portion, a 500kV Insulator Replica, and an SW pole with a new stepping pattern will be installed. | Transmission Line - Conductor | Upgrade/Retrofit | NA | NA | Other [See Notes] | System Operations | NA | NA | NA | 55 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.076428 | NA | NA | NA | 1.3 | 2018-4002 | QS00380 | 1 | 18136 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-06-28 | Work Order Authorization | 2019 | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2020-05-18 | 2021-11-29 | 2022-04-01 | NA | NA | TRUE | 2475.891 | NA ¦ NA | 1944.2609 | 972.9268 | 558.2736 | 1.8695 | 0 | -3.7755 | 0.20436 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2022 ¦ 2023 ¦ 2025 ¦ 2026 | 0 | 1945.9625 | 1.8695 | 0 | -3.7755 | 0.20436 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [Primary Purpose] Infrastructure not connected to the grid for training purposes. [CPUC Status] Exempt
301 | Miguel Substation 230kV Rebuild |  |  | San Diego, San Diego | Upgrade relaying for Bk70/71, replace 32 disconnects, replace 32 switch stands to meet our new seismic standards, replace one overstressed breaker, and eight (8) panel changeouts. Remove existing relaying panels #403 & #406 | Substation - Multiple | Upgrade/Retrofit | NA | NA | Reliability | Age/Condition - Replace 230/115/70/60 kV Breakers | NA | NA | 2026-05-19 | NA | NA | Wires - Replacement Alternative | NA | Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 12.37 | 230 | 660MVA | 4.1 | 2014-01074-ZZ | QS00350 | 1 | 18139 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-12-18 | Work Order Authorization | 2019 | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2019-09-23 | 2022-07-31 | 2022-03-23 | NA | NA | FALSE | 10503 | NA ¦ NA | 11509.4514 | 2385.1998 | 974.2539 | 5.9404 | 0.00208 | -58.7632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 0 | 11562.2721 | 5.9404 | 0.00208 | -58.7632 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0% | [CPUC Status] Exempt
302 | Mission Substation 230kV Rebuild |  |  | San Diego, San Diego | Rebuilding the Mission Substation, increase 230kV bus rating to 3k Amps. Replacing 230kV disconnects to latest standards. Replacing control shelter and equipment. Equipment was upgraded to meet standards, increase reliability and replace aging infrastructure | Substation - Multiple | Upgrade/Retrofit | NA | NA | Reliability | Age/Condition | NA | NA | 2026-05-28 | NA | NA | Wires - Replacement Alternative | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 9 | 230 | 230kV | 4.1 | 2014-01071-ZZ | QS00373 | 1 | 18140 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2022-08-17 | Work Order Authorization | 2019 | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2018-08-22 | 2022-06-30 | 2021-04-23 | NA | NA | FALSE | 39512 | NA ¦ NA | 35996.2989 | 3769.3878 | 545.109 | 0 | -0.07175 | -161.3539 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2024 ¦ 2025 | 3834.7014 | 9573.6459 | 0 | -0.07175 | -161.3539 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0% | [CPUC Status] Exempt
303 | NEW DOWNTOWN 69/12KV |  |  | San Diego, San Diego | Install new 69/12kV substation to serve Downtown San Diego and neighboring communities. Install new 12kV distribution circuits and loop in 69kV as needed. | Substation - Multiple | New | NA | NA | Load Growth | New Substation | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.5 | 2 | 69 | 12kV¦69kV | 4.2 | 2024-9876 | QS00318 | 1 | 18251 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2025-05-07 | Work Order Authorization | 2019 | NA | FALSE | NA | NA | NA | FALSE | Expected PEA Completion | PTC | NA | NA | CPUC | NA | PTC | TBD | To be Filed | TBD | Planning | NA | 2031-04-09 | 2031-12-31 | 2033-01-27 | Project Design | NA | TRUE | 501 | NA ¦ NA | 98247.5265 | 54.0713 | 10.0565 | 193.879 | 305.3035 | 1174.7873 | 245.5429 | 223.6559 | 1245.3247 | 3504.4744 | 3116.9474 | 2823.7332 | 245.5429 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 ¦ 2026 | 54.0713 | 10.0565 | 193.879 | 305.3035 | 1174.7873 | 126.2149 | 0% | NA ¦ NA | 3.8 | NA | 0% | 100%
304 | TL13831 Rancho Mission Viejo Customer Relocation |  |  | Orange County | Install ten (10) transmission poles with pier foundation​ Install around one (1) mile of transmission conductor and ADSS fiber​ RFS fourteen (14) transmission poles and associated hardware​ RFS around 1.2 miles of transmission conductor | Transmission Line - Multiple | Relocate | New | NA | Work Requested by Others | 3rd Party Damage | NA | NA | 2026-02-14 | NA | NA | NA | NA | Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | SDGE work exempt |  | 1.38 | NA | 138 | NA | 3.1 | 2017-0128 | QS00364 | 1 | 19129 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2021-01-07 | Work Order Authorization | 2019 | NA | FALSE | NA | NA | NA | FALSE | Other [See Notes] | EIR | EIR | NA | County of Orange | NA | AL | NA | To be Filed | NA | Planning | NA | 2020-07-13 | 2020-12-31 | 2020-11-20 | NA | NA | FALSE | 6738.5499 | NA ¦ NA | -1.8454 | 2351.4874 | 97.1672 | -892.8598 | -161.0921 | -1.8504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 2351.4874 | 97.1672 | -892.8598 | -161.0921 | -1.8504 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
305 | Urban Substation Rebuild |  |  | San Diego, San Diego | Urban Substation - new perimeter wall construction and 12kV switchgear & capacitor bank replacement | Substation - Other Equipment | Replace | NA | NA | Reliability | Age/Condition - Replace Other Substation Equipment | NA | NA | 2026-05-20 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 0.566344 | 69 | 69kV¦12kV | 4.1 | 2021-2065 | QS00397 | 1 | 19252 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-08-22 | Work Order Authorization | 2019 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Construction (25%-50%) | NA | 2020-02-18 | 2027-03-31 | 2028-10-16 | Workforce | Scope Change | TRUE | 5891.5596 | NA ¦ NA | 21381.309 | 311.129 | 640.6636 | 1245.1791 | 10027.7029 | 918.0668 | 369.1878 | 2196.884 | 2644.8703 | 2365.9212 | 435.6244 | 0 | 1488.0853 | NA | NA | 2024 ¦ 2025 ¦ 2026 | 0 | 0 | 0 | 11899.0971 | 350.8267 | 37.9683 | 0% | NA ¦ NA | 31.5 | NA | 0% | 100% | [CPUC Status] Exempt
306 | Electric Transmission EMS/SCADA Replacement |  |  | San Diego, San Diego | Replacement of Energy Management System (EMS) software, applications, and supporting infrastructure at Electric Transmissions Mission Control Center and Metro Control Center. The EMS is used by Grid Operators to monitor and control the transmission grid. | Other - Operations Tech | Replace | NA | NA | Reliability | NERC CIP Compliance | NERC CIP Compliance | NA | NA | 47 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69 ¦500 | NA | 1.1 | NA | QS00452 | 1 | 20125 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-02-16 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | NA | NA | To be Filed | NA | Engineering more than 50% complete | NA | NA | 2022-06-30 | 2026-12-31 | Other [See Notes] | NA | TRUE | 16373.37 | NA ¦ NA | 10778.1185 | 0 | 0 | 0 | 3874.0547 | 3341.0355 | 2515.1947 | 595.2286 | 452.605 | 0 | 0 | 0 | 9730.2849 | NA | NA | 2026 | 0 | 0 | 0 | 0 | 0 | 10325.5135 | 0% | NA ¦ NA | 1.3 | NA | 45.85% | 54.15% | [Reason for Change in In-Service Date] Delays were due to project suspension during COVID
307 | TL610 Tier 2 W2S Project |  |  | San Diego, San Diego | Replace 12 wood pole structures in HFTD Tier 2 with steel pole structures and transfer approximately 1.6 miles of overhead conductor. | Transmission Line - Pole/Tower | Replace | NA | 20139 | Wildfire Mitigation | T-Line Reliability | NA | NA | 2026-01-27 | 37.0833 | NA | NA | NA | Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 1.6 | NA | 69 | NA | 1.2 | 2020-0272 | QS00474 | 1 | 20133 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-06-18 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | TBD | NA | Exempted | NA | CPUC | NA | TBD | TBD | Other [See Notes] | NA | Engineering more than 50% complete | NA | 2027-10-01 | 2024-12-31 | 2027-12-20 | Land Rights | Project Design | TRUE | 1979.963 | NA ¦ NA | 9335.4159 | 112.1826 | 110.4849 | 125.6946 | 162.5457 | 121.4148 | 57.9079 | 150.4537 | 8457.0859 | 0 | 0 | 0 | 20.262 | NA | NA | 2025 ¦ 2026 | 0 | 0 | 0 | 0 | 669.9684 | 208.3616 | 0% | NA ¦ NA | 3.4 | NA | 0% | 100% | [CPUC Status] TBD
308 | TL627 Tier 2 W2S Project |  |  | Rancho San Diego, San Diego ¦ Spring Valley, San Diego | The TL627 Wood-to-Steel project consists of installing new steel pole structures, re-frame existing steel structures, and conductor along the existing 69kV tie line between Structure Z777999 and Structure Z971734 located in Spring Valley. As part of TL627 rebuild, C91 & C524 will be reconductored as well. This project was initiated as part of SDG&E’s continuous effort to improve reliability and reduce fire risks in fire-prone areas. | Transmission Line - Multiple | Replace | NA | NA | Wildfire Mitigation | Fire Protection | NA | NA | 2026-02-01 | 45.9091 | NA | NA | NA | Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 2.1 | NA | 69 | NA | 1.2 | 2019-0257 | QS00473 | 1 | 20134 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-07-30 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | CPUC | NA | Exempt | NA | Other [See Notes] | NA | Permitting | NA | 2027-01-01 | 2027-04-30 | 2027-06-30 | NA | NA | TRUE | 1979.963 | NA ¦ NA | 14904.2021 | 110.013 | 423.3457 | 504.2678 | 3145.6159 | 1140.5659 | 28.898 | 497.3207 | 7614.0222 | 1370.1365 | 0 | 0 | 28.898 | NA | NA | 2025 ¦ 2026 | 0 | 0 | 0 | 0 | 5393.8247 | 24.043 | 0% | NA ¦ NA | 1.6 | NA | 0% | 100% | [Reason for Change in In-Service Date (2)] Dependency on C75 SUG completion to start the construction of TL627 W2S. [CPUC Status] Exempt
309 | TL649 Tier 2 W2S Project |  |  | San Diego, San Diego ¦ Chula Vista, San Diego | 23 wood poles in HFTD2 to be replaced from wood to steel. Two of the poles (Z192597 and Z82136), are multi-transmission wood pole structures (two poles). 1.162 Miles to be re-conductored. | Transmission Line - Pole/Tower | Upgrade/Retrofit | NA | NA | Wildfire Mitigation | T-Line Reliability | NA | NA | 2026-01-13 | 40.4483 | NA | NA | NA | Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 1.682637 | NA | 69 | NA | 1.2 | 2019-0268 | QS00472 | 1 | 20135 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-06-10 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | Final Certified | 2018-10-05 | IS/MND | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2024-06-24 | 2024-12-31 | 2024-12-16 | NA | NA | TRUE | 1486.209 | NA ¦ NA | 7869.5439 | 189.4133 | 612.1586 | 829.9482 | 5451.9799 | 310.1567 | 371.9043 | 67.8149 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2024 ¦ 2025 ¦ 2026 | 0 | 0 | 0 | 7114.3608 | 315.4638 | 439.7193 | 0% | NA ¦ NA | 43.6 | NA | 0% | 100% | [CPUC Status] Exempt
310 | TL13804 Wood to Steel |  |  | Encinitas, San Diego ¦ Rancho Santa Fe, San Diego ¦ Carlsbad, San Diego ¦ San Diego, San Diego | Replace 15 existing wood structures (h-frames) with steel structures. Project spans approximately 5 miles of TL13804 and includes ~0.6 miles of reconductoring with transferring of existing conductor and fiber optic cable to new structures for the remainder. | Transmission Line - Pole/Tower | Replace | Removal | NA | Wildfire Mitigation | T-Line Reliability | NA | NA | 2026-02-03 | NA | NA | NA | NA | Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | Project In Coastal Zone; Requires Galvanized Steel Poles |  | 2.7 | NA | 138 | NA | 1.2 | 2019-0255 | QS00490 | 1 | 20136 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-07-25 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | NA | Stat Ex | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2024-09-10 | 2025-02-12 | 2024-12-19 | NA | NA | TRUE | 3628.655 | NA ¦ NA | 10279.2004 | 229.5117 | 297.0474 | 477.1188 | 8433.2258 | 771.3874 | 14.7205 | 6.4225 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2024 ¦ 2025 ¦ 2026 | 0 | 0 | 0 | 9486.67 | 771.3874 | 21.143 | 0% | NA ¦ NA | 8.1 | NA | 0% | 100% | [CPUC Status] Exempt
311 | TL23001/04 Insulator and Hardware Replacement |  |  | Encinitas, San Diego ¦ Rancho Santa Fe, San Diego ¦ Carlsbad, San Diego ¦ San Diego, San Diego ¦ Oceanside, San Diego | TL23001 TL23004 Insulator and Hardware Replacement | Transmission Line - Other Equipment | Upgrade/Retrofit | NA | NA | Reliability | Age/Condition - Replace Insulators | NA | NA | 2026-04-29 | NA | NA | NA | NA | Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 34.828406 | NA | 230 | NA | 4.1 | 2019-4004 | QS00479 | 1 | 20138 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2022-07-07 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2022-03-01 | 2022-07-29 | 2022-10-11 | NA | NA | FALSE | 8040.059 | NA ¦ NA | 10607.5569 | 3593.8105 | 6816.3403 | 81.5084 | 126.4645 | -23.9403 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 0 | 10423.5243 | 81.5084 | 126.4645 | -23.9403 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0% | [CPUC Status] Exempt
312 | TL6952 Tier 2 W2S Project |  |  | San Diego, San Diego | Replace 9 wood pole structures in HFTD Tier 2 with steel pole structures and transfer approximately 1.5 miles of overhead conductor. | Transmission Line - Pole/Tower | Replace | NA | 20133 | Wildfire Mitigation | T-Line Reliability | NA | NA | 2026-02-01 | NA | NA | NA | NA | Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | Coastal |  | 1.5 | NA | 69 | NA | 1.2 | 2020-0287 | QS00466 | 1 | 20139 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-06-18 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | TBD | NA | Exempted | NA | CPUC | NA | TBD | TBD | Other [See Notes] | NA | Engineering more than 50% complete | NA | 2027-10-01 | 2022-12-31 | 2027-12-20 | Land Rights | Project Design | TRUE | 1810.588 | NA ¦ NA | 8579.7973 | 85.2687 | 108.168 | 115.8357 | 186.8303 | 110.3414 | 37.073 | 150.4537 | 7772.0351 | 0 | 0 | 0 | 37.073 | NA | NA | 2025 ¦ 2026 | 0 | 0 | 0 | 0 | 620.2355 | 187.5267 | 0% | NA ¦ NA | 0.8 | NA | 0% | 100% | [CPUC Status] TBD
313 | TL661/TL664 Tier 2 W2S Project |  |  | San Diego, San Diego | Replace 14 wood pole structures in HFTD Tier 2 with steel pole structures and install approximately 1.16 miles of overhead conductor. | Transmission Line - Pole/Tower | Replace | NA | NA | Wildfire Mitigation | T-Line Reliability | NA | NA | 2026-01-13 | NA | NA | NA | NA | Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | Coastal |  | 1.16 | NA | 69 | NA | 1.2 | 2020-0289 | QS00471 | 1 | 20140 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-06-18 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | CPUC | NA | TBD | TBD | Other [See Notes] | TBD | Engineering less than 50% complete | NA | 2031-01-02 | 2022-12-31 | 2031-08-04 | Project Design | Scope Change | FALSE | 1810.588 | NA ¦ NA | 18828.537 | 150.0426 | 274.8061 | 558.0351 | 226.0215 | 504.0671 | -11.7475 | 445.1724 | 429.408 | 474.9914 | 387.9849 | 2509.992 | 0 | NA | NA | 2025 ¦ 2026 | 0 | 0 | 0 | 0 | 1739.1331 | -41.7896 | 0% | NA ¦ NA | 2.5 | NA | 0% | 100% | [CPUC Status] TBD
314 | TL691 Tier 2 W2S Project |  |  | Fallbrook, San Diego ¦ Camp Pendleton North | The TL691 Fire Hardening & Reconductor Project consists of replacing existing structures and installing new steel structures along the 69kV tie line 691 in FTZ from Z19800, north of Camp Pendleton to structure Z293940, south of Avocado Substation, with new light duty and heavy engineered steel poles. This project is needed to mitigate loss of service due to wildfires by replacing existing wood poles with new steel structures. The new steel poles shall be designed to 138kV specifications and accommodate existing and future 12kV distribution underbuild and communications circuits. | Transmission Line - Pole/Tower | Replace | NA | NA | Wildfire Mitigation | T-Line Reliability | NA | NA | 2026-01-11 | 52.5091 | NA | NA | NA | Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 6.177837 | NA | 69 | NA | 1.2 | 2019-0269 | QS00469 | 1 | 20141 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-06-18 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | CPUC | NA | TBD | TBD | Other [See Notes] | TBD | Planning | NA | 2029-03-30 | 2024-12-31 | 2029-10-04 | Project Design | NA | TRUE | 1979.963 | NA ¦ NA | 21807.7155 | 177.1658 | 521.1869 | 373.7411 | 328.1684 | 277.1665 | 45.0573 | 121.5524 | 19919.083 | 0 | 0 | 0 | 1767.08 | NA | NA | 2026 | 0 | 0 | 0 | 0 | 0 | 1888.6324 | 0% | NA ¦ NA | 4.1 | NA | 0% | 100% | [CPUC Status] TBD
315 | TL675 Tier 2 W2S Project |  |  | San Diego, San Diego | ​57 poles to be replaced from wood to steel, and 6 miles to be reconductored. | Transmission Line - Pole/Tower | Replace | NA | NA | Wildfire Mitigation | T-Line Reliability | NA | NA | 2026-04-29 | 33.6154 | NA | NA | NA | Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | Coastal |  | 5.450292 | NA | 69 | NA | 1.2 | 2019-0251 | QS00470 | 1 | 20142 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-08-29 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2025-10-30 | 2026-12-31 | 2026-05-05 | NA | NA | TRUE | 1979.963 | NA ¦ NA | 18022.2503 | 257.9922 | 292.5942 | 545.0621 | 3288.587 | 6272.8342 | 4245.8378 | 3066.9333 | 25.0942 | 0 | 0 | 0 | 14930.2229 | NA | NA | 2026 | 0 | 0 | 0 | 0 | 0 | 17997.1561 | 0% | NA ¦ NA | 1.9 | NA | 0% | 100% | [CPUC Status] Exempt
316 | TL6939 Tier 2 W2S Project |  |  | San Diego, San Diego | This project upgrades approximately 2.15 miles of TL6939 east of the Artesian Ranch Substation by replacing aging infrastructure to improve reliability and reduce fire risk. The work includes removing 19 wood poles in a Tier 2 High Fire Threat District, reframing 9 existing steel poles to increase phase spacing, and replacing all remaining wood poles in this segment with steel structures. | Transmission Line - Multiple | Replace | New | NA | Wildfire Mitigation | Priority 1 Wood Structure Replacement | NA | NA | 2026-01-27 | NA | NA | NA | NA | Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 2.15 | NA | 69 | NA | 1.2 | 2019-0256 | QS00467 | 1 | 20143 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-06-18 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Engineering less than 50% complete | NA | 2027-06-30 | 2024-12-31 | 2027-12-31 | Workforce | Project Design | TRUE | 1973 | NA ¦ NA | 4725.574 | 56.2863 | 139.3699 | 257.6459 | 125.859 | 335.2556 | 68.7189 | 75.2269 | 3667.2115 | 0 | 0 | 0 | 983.1356 | NA | NA | 2026 | 0 | 0 | 0 | 0 | 0 | 1058.3625 | 0% | NA ¦ NA | 2.1 | NA | 0% | 100% | [CPUC Status] Exempt
317 | TL6910 Tier 2 W2S Project |  |  | Chula Vista, San Diego | This project will enhance fire resilience along approximately 2.6 miles of TL6910, extending from Z122122 to Z135595, located north of Border Substation within SDG&E right-of-way and easement areas. The scope includes replacing all remaining wood poles within the Tier 2 High Fire Threat District (HFTD) with steel poles. In addition, the project includes reconductoring approximately 0.6 miles of line from Z122122 to Z34280. A total of sixteen (16) wood poles within the Tier 2 HFTD will be removed from service, resulting in improved system reliability and reduced wildfire risk. | Transmission Line - Multiple | Replace | New | NA | Wildfire Mitigation | Priority 1 Wood Structure Replacement | NA | NA | 2026-01-22 | 32.6875 | NA | NA | NA | Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 2.6 | NA | 69 | NA | 1.2 | 2019-0254 | QS00468 | 1 | 20144 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-06-18 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | CPUC | NA | TBD | NA | Other [See Notes] | TBD | Engineering less than 50% complete | NA | 2027-06-30 | 2024-12-31 | 2029-05-18 | Project Design | Project Design | FALSE | 1973.076 | NA ¦ NA | 6057.6032 | 56.6194 | 46.5005 | 93.7415 | 354.0428 | 571.4491 | 76.0951 | 412.2006 | 4212.26 | 189.8878 | 44.8066 | 0 | 1198.4483 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | 1.1 | NA | 0% | 100% | [CPUC Status] TBD
318 | TL13811 W2S |  |  | San Marcos San Diego ¦ Encinitas, San Diego ¦ San Diego, San Diego | TL13811 W2S is a hardening project driven by the circuit’s location within the High Fire Threat District (HFTD) Tier 2. This project will replace all transmission structures from Chicarita Sub to Z312843, and then again from Z200897 to North County Metering Station. Throughout these sections (approximately 11.25 miles in length) the 138 kV mainline will be replaced with 636 kcmil 24/7 Strand “Rook” ACSS/AW. 96 Count OPGW will be installed from Z872457 – Z312843 (approximately 10.75 miles in length). Distribution circuits C1101 and C182 that are in the underbuild position of TL13811 will be reconductored with Covered 336.4 kcmil 26/7 Strands “Linnet” ACSR, and covered 1/0 6/1 Strands “Raven” ACSR, respectively. | Transmission Line - Multiple | Replace | New | NA | Wildfire Mitigation | T-Line Reliability | NA | NA | 2026-01-11 | 62.1818 | NA | NA | NA | Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 13.000333 | NA | 138 | NA | 1.2 | 2019-0253 | QS00465 | 1 | 20145 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-04-23 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Construction (25%-50%) | NA | 2025-02-24 | 2024-12-31 | 2027-05-14 | Project Design | NA | FALSE | 88878 | NA ¦ NA | 62249.622 | 811.9706 | 1536.3214 | 1213.4383 | 3719.1329 | 6776.993 | 58.5606 | 29803.1828 | 18140.9113 | 0 | 0 | 0 | 14305.5279 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | 3.8 | NA | 0% | 100% | [CPUC Status] Exempt
319 | IV Shunt Reactor Replacement |  |  | Imperial County | Replace the existing 500kV shunt reactors at Imperial Valley substation with spares at Miguel substation. | Substation - Reactive Equipment | Replace | NA | NA | Reliability | 3rd Party Damage | NA | NA | 2026-06-01 | 42; 42; 42 | NA | Wires - Minimum Required Scope (spot repair) Alternative | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 55.477548 | 500 | 500kV | 4.1 | 2021-2176 | QS00482 | 1 | 20148 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-08-06 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Construction (50%-75%) | NA | 2022-06-01 | 2024-08-31 | 2024-06-15 | NA | NA | FALSE | 3742.255 | NA ¦ NA | 4238.1507 | 1479.6704 | 1043.8368 | 472.7717 | 1205.2794 | 29.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2024 ¦ 2025 | 0 | 0 | 0 | 4209.0907 | 29.06 | 0 | 0% | NA ¦ NA | 18.5 | NA | 100% | 0% | [CPUC Status] Exempt
320 | TL6920 Wood to Steel |  |  | San Diego, San Diego | 7 poles in HFTD 2 to be replaced from wood to steel, and a total of 0.584 miles of existing 1033.5 ACSR/AW to be reconductored. | Transmission Line - Pole/Tower | Replace | NA | NA | Wildfire Mitigation | T-Line Reliability | NA | NA | 2026-01-15 | 29; 29; 29; 29; 29 | NA | NA | NA | Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.286309 | NA | 69 | NA | 1.2 | 2020-0286 | QS00504 | 1 | 20149 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-06-30 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2023-05-08 | 2024-01-18 | 2023-08-02 | NA | NA | FALSE | 1959.396 | NA ¦ NA | 4263.0251 | 171.0337 | 300.7648 | 3682.8958 | 110.8792 | -3.2955 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2023 ¦ 2024 ¦ 2025 | 0 | 0 | 4155.4414 | 110.8792 | -3.2955 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
321 | TL690C Camp Pendleton Wood to Steel |  |  | Camp Pendleton South, San Diego | approx 8 poles in HFTD 2 to be replaced from wood to steel. A total of 0.57 miles of existing 1/0 CU and 336.4 ACSR/AW to be reconductored. | Transmission Line - Multiple | Replace | Upgrade/Retrofit | NA | Wildfire Mitigation | T-Line Reliability | NA | NA | 2026-01-11 | NA | NA | NA | NA | Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 0.499472 | NA | 69 | NA | 1.2 | 2020-0273 | QS00496 | 1 | 20152 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-08-02 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | Categorical Exclusion | CPUC | MCBCP | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2024-06-18 | 2024-10-31 | 2024-07-31 | NA | NA | TRUE | 3977.8055 | NA ¦ NA | 2999.9945 | 140.182 | 218.2715 | 631.0719 | 1777.3783 | 212.608 | 19.6284 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2023 ¦ 2024 ¦ 2025 ¦ 2026 | 0 | 0 | 990.3798 | 1777.3783 | 212.608 | 19.6284 | 0% | NA ¦ NA | 0.32 | NA | 0% | 100% | [CPUC Status] Exempt
322 | Granite 12kV Breaker and Switchgear Replacements |  |  | Granite Hills, San Diego | Rebuild of the 69kV bus reconfiguring it from an ultimate 2 tie line bus to an ultimate 3 tie line substation. Replace all seven (qty: 7) 69kV kV circuit breakers (5 OCB and 2 GCB ¦older style). Install new 69kV Potential Transformers. Replace 12kV open rack bus and (qty. 8) 12kV circuit breakers and (qty:2) 12kV 1 ¦4 section Switchgear at Granite Substation, due to operational problems, again infrastructure, environmental concerns, in addition to meeting current reliability standards. Rebuilding the 69kV bus and rotating the phases at the transmission pole will allow for a third tie line position. Replacing the 12kV open rack will RFS the OCBs and address the some 12kV reliability issues, will update relaying to support WMP initiatives (advance protection). The new control shelter will assist with updating relaying to include TCRI, new 69kV BT, and increase operational ability. | Substation - Circuit Breaker | Replace | New | NA | Reliability | Age/Condition - Replace Breakers | NA | NA | 2026-05-04 | NA | NA | Wires - Replacement Alternative | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 1.38 | 12 ¦69 | 12kV¦69kV | 4.1 | 2021-2405 | QS00430 | 1 | 20244 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-10-24 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Construction (50%-75%) | NA | 2024-02-14 | 2028-12-31 | 2028-03-15 | NA | NA | TRUE | 4693.6589 | NA ¦ NA | 20139.8008 | 30.2266 | 440.1786 | 1135.9573 | 5398.2963 | 9669.1709 | 2161.6844 | 0 | 201.4794 | 223.103 | 0 | 0 | 19912.2131 | NA | NA | 2024 ¦ 2025 ¦ 2026 | 0 | 0 | 0 | 241.6657 | -196.9947 | 19670.5473 | 0% | NA ¦ NA | 2.4 | NA | 0% | 100% | [CPUC Status] Exempt
323 | Kettner Substation 69/12kV Rebuild Project |  |  | San Diego, San Diego | The Kettner Substation Rebuild includes the installation of two 69kV GCB, six 12kV VCB, and one 12kV Capacitor Bank with stepwise switching. This will make Kettner Substation an ultimate 30MVA. The project also includes the construction of a new concrete block control shelter and a new perimeter fence/wall. The project includes removal of old infrastructure no longer in use, including two 12kV cap banks, eleven 12kV OCBs, one 12kV VCB, and two 69kV OCB. The current shipping container control shelter will also be removed once cutover is complete to the new concrete block control shelter. | Substation - Multiple | Upgrade/Retrofit | Removal | NA | Reliability | Replace Other Substation Equipment | NA | NA | 2026-05-05 | 44; 44; 27 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 0.3 | 69 | 30MVA | 4.1 | 2014-00599-ZZ | QS00478 | 1 | 20251 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-05-10 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2021-07-01 | 2024-12-31 | 2024-09-20 | NA | NA | TRUE | 6659.3357 | NA ¦ NA | 10096.0068 | 1836.4478 | 1386.0173 | 3480.4105 | 1834.7917 | 1346.059 | 8.8189 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2022 ¦ 2023 ¦ 2024 ¦ 2025 ¦ 2026 | 0 | 704.9014 | 13.3813 | 7245.8922 | 2123.0131 | 8.8189 | 0% | NA ¦ NA | 17.3 | NA | 0% | 100% | [CPUC Status] Exempt
324 | Suncrest Tertiary Reactor Replacement |  |  | San Diego, San Diego | The BK80/81 tertiary 12kV reactors are failing at a high rate (one in 2016, one in 2020, and two in 2021). Reactors are necessary to allow critical 500kV voltage control for grid operations. Newer, better designed, and insulated reactors are available to replace units that are failing at a quick rate. | Substation - Reactive Equipment | Upgrade/Retrofit | Replace | NA | Safety | Substation Reliability | NA | NA | 2026-05-16 | 13 | NA | Wires - Replacement Alternative | NA | Tier 3 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 40.94 | 500 | 12kV | 4.1 | 2021-2012 | QS00580 | 1 | 21137 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2022-07-19 | Work Order Authorization | 2021 | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2022-03-07 | 2022-06-30 | 2022-06-30 | NA | NA | FALSE | 28561.627 | NA ¦ NA | 2109.8366 | 1904.6749 | 203.0249 | 0 | 0 | -1.9889 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2022 ¦ 2025 | 0 | 2111.8255 | 0 | 0 | -1.9889 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0% | [CPUC Status] Exempt
325 | TL623C Wood to Steel Project |  |  | San Diego, San Diego | This project replaces 4/0 B.S. CU Conductor. OH Full Rebuild approx. 1.30 miles from structure Z180990 to Z181008 South of Otay Valley Regional Park Removes 19 existing wood structures. | Transmission Line - Multiple | Replace | Upgrade/Retrofit | NA | Wildfire Mitigation | System Design Upgrade | NERC TPL Standards | NA | 2026-01-11 | 70.0833 | NA | NA | NA | Tier 2 | FALSE ¦ FALSE ¦ TRUE | FALSE | NA |  | 1.6 | NA | 69 | NA | 2.1 | 2020-0327 | QS00634 | 1 | 21148 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2021-12-14 | Work Order Authorization | 2022 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | CPUC | NA | NA | NA | Other [See Notes] | NA | Engineering more than 50% complete | NA | 2027-01-19 | 2027-12-31 | 2027-04-05 | NA | NA | TRUE | 2699 | NA ¦ NA | 5241.6051 | 0 | 0.52013 | 30.4255 | 202.4276 | 396.4049 | 69.0452 | 739.1978 | 3803.584 | 0 | 0 | 0 | 69.0452 | NA | NA | 2024 ¦ 2025 ¦ 2026 | 0 | 0 | 0 | 233.3732 | 396.4049 | 808.243 | 0% | NA ¦ NA | 15.4 | NA | 0% | 100% | [Wildfire Related] Being in or out of the HFTD is not a bright-line litmus test. The CEQA categorical exemption for emergencies is based on why we are proposing the project. In or out notwithstanding, we should be able to utilize the emergency exemption for CEQA clearance if the purpose is to avoid the risk of wildfire. [CPUC Status] TBD
326 | Twin Engine Medium Lift Helicopter |  |  | Gillespie Field, San Diego | Purchase of a twin engine, multi­mission, medium lift helicopter for primary use of external load work. The helicopter allows for heavier lift capability for continual distribution and transmission work in the high fire threat district. The helicopter also has fire fighting capabilities | Other | New | NA | NA | Wildfire Mitigation | Safety - Line Right of Way Access | NA | NA | NA | 61 | NA | NA | NA | Tier 1 ¦ Tier 2 | TRUE ¦ TRUE ¦ FALSE | FALSE | NA |  | NA | NA | NA | NA | 1.2 | NA | QS00609 | 1 | 21256 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2025-05-06 | Work Order Authorization | 2021 | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | NA | NA | NA | NA | NA | NA | To be Filed | NA | Operational | NA | 2021-12-30 | 2022-12-31 | 2023-01-23 | NA | NA | FALSE | 1876.6324 | NA ¦ NA | 2544.6126 | 368.2172 | 1658.298 | 208.6423 | 116.6109 | 192.8442 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2023 ¦ 2024 ¦ 2025 | 0 | 0 | 2235.1575 | 116.6109 | 192.8442 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0%
327 | Smart Meter 2.0 |  |  | Multiple | Deployment of next generation smart metering technology and hardware | Multiple Options [See Notes] | Replace | Upgrade/Retrofit | NA | Age/End of Life | Age/Condition | NA | NA | NA | NA | NA | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | NA | NA | NA | NA | QS00654 | 1 | 21881 | 2026-06-17 ¦ T0092 ¦ QBL0141 ¦ NA | TRUE | 2023-11-29 | Work Order Authorization | 2022 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | Other [See Notes] | CPUC | NA | Other [See Notes] | 2025-12-28 | Filed and Under Administrative Review | NA | Planning | NA | 2027-07-01 | 2027-07-01 | 2027-07-01 | NA | NA | TRUE | 3782.466 | NA ¦ NA | 27853.5264 | 0 | 130.9574 | 499.4895 | 2253.9494 | 339.3819 | 126.336 | 1570.5524 | 13641.8072 | 2334.2064 | 1242.261 | 4994.2497 | 3350.1142 | NA | NA | 2026 | 0 | 0 | 0 | 0 | 0 | 458.8703 | 0% | NA ¦ NA | 1.1 | NA | 0% | 0% | [Project Description - What] Deployment of next generation smart metering technology and hardware
328 | Miguel-Sycamore Canyon 230kV Loop-in Suncrest |  |  | San Diego, San Diego | Mitigate the CAISO identified constraints consisting of the following: A 14.5-mile double circuit 230kV transmission line that will loop-in the existing TL23021 Miguel-Sycamore Canyon into Suncrest substation; and Install new 500/230kV bank at Suncrest Substation. | Transmission Line/Substation | New | NA | NA | CAISO Transmission Planning Standards [See Notes for NERC Compliance and contingency code, WECC Requirement (and the specific requirement)] | T-Line Reliability | CAISO Requirement | NA | 2026-05-16 | NA | Steady State Power Flow System Analysis | NA | $0 Mil – $1 Mil | Tier 3 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 14.5 | 55.48 | 230 | 230kV¦500kV | 2.1 | 2024-3714 | QS00734 | 1 | 23127 | NA ¦ NA ¦ NA ¦ NA | TRUE | NA | Work Order Authorization | 2023 | 2023 | FALSE | 2023 | NA | https://www.caiso.com/Documents/ISO-Board-Approved-2022-2023-Transmission-Plan.pdf | FALSE | Other [See Notes] | EIR filed 5/8/2026 | EIR | Other [See Notes] | CPUC | USFS | PTC [A.26-05-005] | 2026-05-08 | Administratively Complete and Under Technical Review | 2026 | Permitting | NA | 2028-02-08 | 2032-12-31 | 2031-07-31 | NA | NA | FALSE | 35000 | NA ¦ NA | 523465.5204 | 0 | 0 | 0.29146 | 1768.5276 | 3667.8229 | 1141.2161 | 10852.5465 | 29211.9048 | 176416.1052 | 84287.5813 | 114355.7923 | 6577.8581 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0%
329 | BK30, BD: New Bank 30 |  |  | San Diego, San Diego | Installation of a 69/12 kV substation transformer and associated equipment to mitgate overload. | Substation - Multiple | New | New | NA | Load Growth | Substation Capacity | NA | NA | 2026-05-27 | NA | NA | NA | NA | Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 0.94 | 69 | 28MVA | 1.4 | 3-578735 | QS00703 | 1 | 23242 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-09-21 | Work Order Authorization | 2024 | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational |  | 2024-08-02 | 2025-12-31 | 2025-12-27 | NA | NA | TRUE | 11703.4576 | NA ¦ NA | 5164.7967 | 0 | 0 | 110.2998 | 3040.3095 | 2081.7714 | -67.5841 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2026 | 0 | 0 | 0 | 0 | 0 | 5164.7967 | 0% | NA ¦ NA | 18.5 | NA | 0% | 100% | [CPUC Status] Exempt
330 | OT33, OT: New Sub Bank 33 |  |  | San Diego, San Diego | Installation of a 69/12 kV substation transformer and associated equipment to mitgate overload. | Substation - Multiple | New | NA | NA | Load Growth | Substation Capacity | NA | NA | 2026-05-12 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 2.78 | Multiple | 28MVA | 1.4 | 3-684733 | QS00713 | 1 | 23258 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-05-01 | Work Order Authorization | 2024 | NA | FALSE | NA | NA | NA | FALSE | TBD | TBD | Exempted | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Engineering less than 50% complete |  | 2027-02-24 | 2024-12-31 | 2028-08-15 | Vendor Quality/Delays | NA | FALSE | 8648.8448 | NA ¦ NA | 1448.5751 | 0 | 0 | 0.41068 | 159.9399 | 173.2888 | 19.4583 | 183.3516 | 728.4997 | 183.6261 | 0 | 0 | 353.0977 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | 13.5 | NA | 0% | 100% | [CPUC Status] Exempt
331 | FERC Order 881 23882 |  |  | NA | Transmission Equipment Rating Group (TERG) Database Digitization & Automation New application & user interface to be built Ambient Adjusted Ratings interface to EMS System CAISO Integration -10 days Hourly Forecast Data TERG application data integration | Other - IT | New | Upgrade/Retrofit | NA | Load Growth | System Operations | NA | NA | NA | NA | NA | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | 0 | NA |  | NA | NA | NA | NA | NA | NA | NA | 1 | 23882 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-12-06 | Work Order Authorization | 2023 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Planning |  | 2024-12-14 | 2027-10-31 | 2027-10-31 | NA | NA | TRUE | 3554.1845 | NA ¦ NA | 2853.1701 | 0 | 0 | 2.8926 | 1113.1164 | 1108.809 | 388.0856 | 0 | 240.2665 | 0 | 0 | 0 | 2612.9036 | NA | NA | 2025 ¦ 2026 | 0 | 0 | 0 | 0 | -0.049725 | 88.5852 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] Exempt
332 | TL631 UG Cable Replacement Project |  |  | El Cajon, San Diego | Project Scope: Remove and replace failing underground cables on TL631 that have been in operation for ~30years. The hand-taped splices are exhibiting significant degradation with (3) cable failures in the past 3 years. | Transmission Line - Underground | Upgrade/Retrofit | NA | NA | Reliability | Age/Condition | NA | NA | 2026-02-12 | 32; 32 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 1 | NA | 69 | NA | 4.1 | 2024-3662 | QS00731 | 1 | 24125 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-01-16 | Work Order Authorization | 2024 | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational |  | 2024-02-26 | 2024-08-30 | 2024-04-21 | NA | NA | TRUE | 6625.166 | NA ¦ NA | 6633.3287 | 0 | 0 | 0 | 6630.5525 | 2.7687 | 0.00744 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2024 ¦ 2025 ¦ 2026 | 0 | 0 | 0 | 6630.5525 | 2.7687 | 0.00744 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
333 | 3 ohm Series Reactor on Sycamore Penasquitos 230 kV line |  |  | San Diego, San Diego | Install a new 3 ohm series reactor on the Sycamore – Penasquitos 230 kV line; reactor will be installed at Sycamore Canyon Substation due to physical space requirements. | Substation - Reactive Equipment | New | NA | NA | CAISO Transmission Planning Standards [See Notes for NERC Compliance and contingency code, WECC Requirement (and the specific requirement)] | T-Line Reliability | CAISO Requirement | NA | 2026-02-03 | NA | Steady State Power Flow System Analysis | NA | $5 Mil - $10 Mil | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 13.94 | 230 | NA | 2.1 | 2022-3181 | QS00735 | 1 | 24126 | NA ¦ NA ¦ NA ¦ NA | FALSE | NA | Work Order Authorization | 2024 | 2023 | FALSE | 2023 | NA | https://www.caiso.com/Documents/ISO-Board-Approved-2022-2023-Transmission-Plan.pdf | TRUE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Construction (25%-50%) |  | 2025-12-15 | 2032-12-31 | 2027-06-22 | NA | NA | FALSE | 7290 | NA ¦ NA | 22007.5515 | 0 | 0 | 0 | 429.623 | 4627.0578 | 1851.1483 | 4667.11 | 10432.6123 | 0 | 0 | 0 | 6907.8291 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0% | [CPUC Status] Substation Exemption
334 | Rearrange TL23013 PQ OT and TL6959 PQ Mira Sorrento |  |  | San Diego, San Diego | ​Per CAISO request to SDG&E to identify potential solutions to address the overload problems on TL13810 (FR-DD-PQ) caused by credible P7 (N-2: TL23013 & TL23071) contingency. The overload has created some system operation congestions that will increase ​the operating cost to address system reliability. This project is proposed to swap TL23013 and TL6959 from PQ (2 miles between Z479065 and Z100258). To do that it will require to upgrade 2 miles of existing TL13810 structures to 230kV double circuit structures for TL23013 with 2-1033 ACSR and TL13810 with 1-1033 ACSR. TL23013 & TL13810 will share the same structures and TL23071 and TL6959 will be on the other structures. This will eliminate the credible P7 outage (N-2 TL23013 & TL23071)​. | Transmission Line - Multiple | Relocate | New | NA | CAISO Transmission Planning Standards [See Notes for NERC Compliance and contingency code, WECC Requirement (and the specific requirement)] | T-Line Reliability | CAISO Requirement | NA | 2026-02-24 | NA | Steady State Power Flow System Analysis | NA | $20 Mil - $30 Mil | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 2 | NA | 69 ¦ 138 ¦ 230 | NA | 2.1 | 2020-0294 | QS00736 | 1 | 24127 | NA ¦ NA ¦ NA ¦ NA | FALSE | NA | Work Order Authorization | 2024 | 2023 | FALSE | 2023 | NA | https://www.caiso.com/Documents/ISO-Board-Approved-2022-2023-Transmission-Plan.pdf | TRUE | NA | NA | NA | NA | NA | NA | TBD | TBD | Other [See Notes] | TBD | Engineering less than 50% complete |  | 2031-08-19 | 2032-06-01 | 2032-03-25 | NA | NA | FALSE | 17942 | NA ¦ NA | 20601.8707 | 0 | 0 | 0 | 209.6776 | 331.9369 | 57.5718 | 144.7793 | 364.3561 | 398.1969 | 435.1807 | 475.5995 | 599.1864 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 45.85% | 54.15% | [CPUC Status] TBD
335 | TL680C MELROSE RECONDUCTOR |  |  | Oceanside, San Marcos, Carlsbad, Vista, San Diego | Address the existing San Marcos Substation-Melrose Tap constraint by reconductoring the line to continuous/4 hour emergency rating of 102/234MVA | Transmission Line - Conductor | Upgrade/Retrofit | New | NA | CAISO Transmission Planning Standards [See Notes for NERC Compliance and contingency code, WECC Requirement (and the specific requirement)] | T-Line Capacity | CAISO Requirement | NA | 2026-01-29 | 46.1889 | Steady State Power Flow System Analysis | Wires - Reconductor/Line Rebuild Alternative | $15 Mil - $20 Mil | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 6.3 | NA | 69 | NA | 2.1 | 2024-4035 | QS00743 | 1 | 24130 | NA ¦ NA ¦ NA ¦ NA | FALSE | NA | Work Order Authorization | 2024 | 2023 | FALSE | 2023 | NA | https://www.caiso.com/Documents/ISO-Board-Approved-2022-2023-Transmission-Plan.pdf | TRUE | NA | NA | NA | NA | NA | NA | TBD | TBD | Other [See Notes] | TBD | Engineering less than 50% complete |  | 2029-05-23 | 2032-12-31 | 2032-12-31 | NA | NA | FALSE | 2000 | NA ¦ NA | 26492.5479 | 0 | 0 | 0 | 55.5192 | 893.6063 | 103.6823 | 560.2274 | 1206.9806 | 1315.5144 | 1437.5455 | 1570.9084 | 1052.8078 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | 6.8 | NA | 0% | 100% | [CPUC Status] TBD
336 | TL13820 CHICARITA RECONDUCTOR |  |  | San Diego ¦ Poway, San Diego | Reconductor the line to 250MVA from Chicarita Substation to Sycamore Canyon | Transmission Line - Conductor | Upgrade/Retrofit | NA | NA | CAISO Transmission Planning Standards [See Notes for NERC Compliance and contingency code, WECC Requirement (and the specific requirement)] | T-Line Capacity | CAISO Requirement | NA | 2026-01-27 | NA | Steady State Power Flow System Analysis | Wires - Reconductor/Line Rebuild Alternative | $15 Mil - $20 Mil | Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 5.2 | NA | 138 | NA | 2.1 | 2024-4036 | QS00744 | 1 | 24131 | NA ¦ NA ¦ NA ¦ NA | FALSE | NA | Work Order Authorization | 2024 | 2023 | FALSE | 2023 | NA | https://www.caiso.com/Documents/ISO-Board-Approved-2022-2023-Transmission-Plan.pdf | TRUE | TBD | NA | NA | NA | NA | NA | TBD | TBD | Other [See Notes] | TBD | Engineering less than 50% complete |  | 2026-10-30 | 2032-12-31 | 2032-12-31 | NA | NA | FALSE | 2000 | NA ¦ NA | 59307.8233 | 0 | 0 | 0 | 79.0354 | 778.9454 | 160.9421 | 485.1854 | 704.4106 | 769.835 | 841.3358 | 53551.4026 | 1018.9229 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | 0.8 | NA | 0% | 100% | [CPUC Status] TBD
337 | Oceanside Area Sub: Electrification |  |  | Oceanside, San Diego | Oceanside load pocket consists of Cannon, Oceanside, San Luis Rey, and Stewart substations. Based on Distribution planning 2025 Forecast refresh (issued on March 10th, 2025), this load pocket will reach 85% in 2028 and 100% in 2036 of current capacity. In order to mitigate forecasted overload for load pocket, the project scope will include a new 69/12kV greenfield substation. | Substation - Multiple | New | New | NA | Load Growth | Substation Reliability | NA | NA | 2026-04-10 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 0.22 | 69 | 69kV ¦12kV | 2.1 | 2025-4308 | QS00750 | 1 | 24133 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-08-30 | Work Order Authorization | 2025 | NA | FALSE | NA | NA | NA | FALSE | TBD | NA | IS/MND | NA | CPUC | NA | PTC | TBD | To be Filed | TBD | Planning |  | 2030-01-22 | 2031-12-31 | 2035-07-25 | Project Design | NA | TRUE | 21121.7902 | NA ¦ NA | 80303.0237 | 0 | 0 | 0 | 113.6741 | 768.049 | 12208.9747 | 854.3119 | 5531.9884 | 9378.6202 | 26141.3998 | 24556.6314 | 13090.6977 | NA | NA | 2026 | 0 | 0 | 0 | 0 | 0 | 12133.9726 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0%
338 | BORDER-SAN YSIDRO SUBSTATION |  |  | San Diego, San Diego | The Border-San Ysidro substation project is part of the Electrification Capital Plan to ensure SDGE is meeting the growing load demands of the area. Current project scope includes a new substation and ~ 2 miles of underground transmission lines to mitigate overload conditions and ensure reliability of SDG&E electrical system | Substation - Multiple | New | Upgrade/Retrofit | NA | Load Growth | New Substation | NA | NA | 2026-05-27 | NA | NA | NA | NA | Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69 | 69kV ¦12kV | 4.2 | 2024-4111 | QS00752 | 1 | 24134 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-09-12 | Work Order Authorization | 2025 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | CPUC | NA | PTC | TBD | To be Filed | TBD | On Hold |  | 2027-03-16 | 2035-12-31 | 2033-06-01 | NA | NA | FALSE | 1932.7565 | NA ¦ NA | 178013.7866 | 0 | 0 | 0 | 26.124 | 806.068 | 58.2681 | 59.3748 | 85.5761 | 30812.3537 | 57072.4814 | 26133.5933 | 890.4601 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | 2 | NA | 0% | 100%
339 | Pacific Beach - Rose Canyon Electrification |  |  | San Diego, San Diego | Increase overall capacity in the Pacific Beach - Rose Canyon load pocket to meet expected loads per the 10+ year forecast. | Substation - Multiple | New | Upgrade/Retrofit | NA | Load Growth | Substation Capacity | NA | NA | 2026-05-01 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 0.35 | NA | 30MVA | 4.2 | 2025-4180 | QS00756 | 1 | 24135 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-09-30 | Work Order Authorization | 2025 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | CPUC | NA | TBD | TBD | Other [See Notes] | TBD | On Hold |  | TBD | 2033-12-31 | TBD | NA | NA | FALSE | 1932.7565 | NA ¦ NA | 118086.5127 | 0 | 0 | 0 | 26.2579 | 97.3144 | 3.0052 | 8.277 | 11.9296 | 13.0376 | 14.2485 | 1847.5186 | 126.5775 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] TBD
340 | Coronado Island Reliability Reinforcement |  |  | Coronado, San Diego | Coronado Island Reliability Reinforcement: To support in increased Coronado Island load forecast SDGE will install a new 69kV transmission line (TL6977) from downtown San Diego to Coronado Island and reconductor existing transmission lines (TL650 and TL655). | Substation - Multiple | New | New | NA | CAISO Transmission Planning Standards [See Notes for NERC Compliance and contingency code, WECC Requirement (and the specific requirement)] | T-Line Capacity | CAISO Requirement | NA | 2026-02-19 | NA | Steady State Power Flow System Analysis | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 0.44 | 69 | NA | 2.1 | 2025-4220 | QS00755 | 1 | 24136 | 2026-06-17 ¦ 2024-3886 ¦ NA ¦ NA | TRUE | NA | Work Order Authorization | 2025 | 2025 | FALSE | 2025 | NA | https://www.caiso.com/documents/iso-board-approved-2024-2025-transmission-plan.pdf | FALSE | NA | NA | NA | NA | CPUC | NA | AL [4862-E] | 2026-06-19 | Filed and Under Administrative Review | 2026 | Engineering less than 50% complete |  | 2026-10-06 | 2027-08-30 | 2028-08-17 | Project Design | NA | TRUE | 3000.2772 | NA ¦ NA | 153456.704 | 0 | 0 | 0 | 41.7452 | 14593.6562 | 1076.3171 | 17903.7504 | 56920.9898 | 62920.2452 | 0 | 0 | 15711.7184 | NA | NA | 2026 | 0 | 0 | 0 | 0 | 0 | 769.7485 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
341 | Escondido Area Substation - Electrification |  |  | Escondido, San Diego | Escondido load pocket consists of Ash, Batiquitos, Esco, Escondido, Olivenhain and San Marcos substations. Based on Distribution Planning 2025 Forecast refresh (issued on March 10, 2025), this load pocket will reach 85% in 2030 and 100% in 2034 of current capacity. In order to mitigate forecasted overload for load pocket, the business unit is considering adding capacity to transfer load to rebuild, or expansion of existing Esco substations. | Substation - Multiple | New | New | NA | Load Growth | Substation Reliability | NA | NA | 2026-05-20 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 7.18 | 4.66 | NA | NA | 4.2 | 2025-4356 | QS00759 | 1 | 24138 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-10-30 | Work Order Authorization | 2025 | NA | FALSE | NA | NA | NA | FALSE | TBD | NA | NA | NA | CPUC | NA | TBD | TBD | Other [See Notes] | TBD | On Hold |  | TBD | 2033-12-31 | TBD | NA | NA | FALSE | 1927.4041 | NA ¦ NA | 3873.3459 | 0 | 0 | 0 | 7.9416 | 178.2184 | 27.0943 | 267.1804 | 385.0845 | 420.8504 | 459.9381 | 495.7588 | 213.2543 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | 3.6 | NA | 0% | 0% | [CPUC Status] TBD
342 | IV Sub Short Circuit Mitigation |  |  | Imperial County | Imperial Valley Short Circuit: CAISO, as part of the 2023-2024 Transmission Plan, approved a reliability solution to address short circuit concerns at the SDG&E Imperial Valley Substation. The solution involves installing two sets of current-limiting reactors (CLRs) on the 230kV buses and rearranging related 230kV transmission lines that connect at IV Substation. | Substation - Multiple | New | Upgrade/Retrofit | NA | CAISO Transmission Planning Standards [See Notes for NERC Compliance and contingency code, WECC Requirement (and the specific requirement)] | Substation Reliability | CAISO Requirement | NA | 2026-06-01 | NA | Short Circuit Duty Analysis | Wires - System Configuration Alternative | $100 Mil – $125 Mil | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 55.48 | 230 | NA | 2.1 | 2025-4217 | QS00763 | 1 | 24139 | NA ¦ NA ¦ NA ¦ NA | TRUE | NA | Work Order Authorization | 2025 | 2024 | FALSE | 2024 | NA | https://www.caiso.com/documents/iso-board-approved-2023-2024-transmission-plan.pdf | FALSE | TBD | NA | NA | Other [See Notes] | CPUC | BLM | PTC | TBD | To be Filed | TBD | Planning |  | 2032-09-08 | 2035-06-30 | 2035-08-23 | NA | NA | FALSE | 4099.974 | NA ¦ NA | 124527.2505 | 0 | 0 | 0 | 10.2178 | 357.4135 | 162.1227 | 885.2777 | 6472.0929 | 11946.4651 | 4210.7355 | 34252.9045 | 529.754 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0%
343 | Miguel BK 82 Expansion |  |  | San Diego, San Diego | Project scope includes a new 500/230 kV bank. The Miguel substation 500 kV yard is expected to be expanded for the new Bank (BK) 82 addition. This project will require significant grading and site development, expansion of the water retention area, a CAST fence, transmission & distribution line relocations, and modifications to the 500 kV gas insulated substation (GIS). | Substation - Multiple | Upgrade/Retrofit | NA | NA | CAISO Transmission Planning Standards [See Notes for NERC Compliance and contingency code, WECC Requirement (and the specific requirement)] | System Operations | CAISO Requirement | NA | 2026-05-19 | 9; 9 | Lifecycle Replacement Analysis | Non-Wires - Large Scale Energy Alternative | $250 Mil – $300 Mil | Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | TBD |  | NA | 12.37 | 500 | 500kV | 2.1 | 2024-4097 | QS00769 | 1 | 24140 | NA ¦ NA ¦ NA ¦ NA | FALSE | NA | Work Order Authorization | 2025 | 2023 | FALSE | 2023 | NA | https://stakeholdercenter.caiso.com/InitiativeDocuments/ISO-Board-Approved-2022-2023-Transmission-Plan.pdf | FALSE | TBD | exempt | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Engineering less than 50% complete |  | 2027-01-21 | 2033-01-03 | 2032-01-06 | NA | NA | FALSE | 186278 | NA ¦ NA | 162640.6201 | 0 | 0 | 0 | 76.2813 | 1117.8736 | 293.6834 | 5416.8858 | 11333.0387 | 37030.8688 | 15526.653 | 47878.0505 | 1487.8383 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0% | [CPUC Status] Exempt
344 | BK33, PD: New Bank 33 |  |  | San Diego, San Diego | Installation of a 69/12 kV substation transformer and associated equipment to mitgate overload. | Substation - Multiple | New | New | NA | Load Growth | Substation Capacity | NA | NA | 2026-04-23 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 2.78 | 69 | 28MVA | 1.4 | 3-719759 | QS00767 | 1 | 24246 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2025-01-16 | Work Order Authorization | 2025 | NA | FALSE | NA | NA | NA | FALSE | TBD | NA | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Construction (10%-25%) |  | 2026-11-30 | 2028-06-01 | 2028-01-06 | NA | NA | FALSE | 24229.4004 | NA ¦ NA | 1149.3315 | 0 | 0 | 0 | 0 | 128.3737 | 22.0046 | 212.6759 | 786.2773 | 0 | 0 | 0 | 150.3783 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | 11.5 | NA | 0% | 100% | [CPUC Status] Exempt
345 | BK30, VN: New Bank 30 |  |  | San Diego, San Diego | Installation of a 69/12 kV substation transformer and associated equipment to mitgate overload | Substation - Multiple | New | New | NA | Load Growth | Substation Capacity | NA | NA | 2026-05-05 | NA | NA | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | 0 | NA |  | NA | 4.66 | 69 | 28MVA | 1.4 | 3-739825 | QS00768 | 1 | 24248 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2025-01-06 | Work Order Authorization | 2022 | NA | FALSE | NA | NA | NA | FALSE | TBD | TBD | NA | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Engineering less than 50% complete |  | 2027-06-07 | 2027-01-15 | 2028-01-19 | Vendor Quality/Delays | NA | FALSE | 9342.8262 | NA ¦ NA | 1292.7779 | 0 | 0.1837 | 179.316 | 9.4207 | 36.1959 | 14.3388 | 218.3577 | 834.965 | 0 | 0 | 0 | 239.4552 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | 22 | NA | 0% | 100% | [CPUC Status] Exempt
346 | Jamacha 69/12kV Substation Rebuild |  |  | La Mesa, San Diego | Reliability transmission solution to address several thermal overloads in the 69kV transmission system around Valley Center area due to the charging/discharging of Valley Center energy storage. Construct new 5-mile double circuit 69kV line to create two new lines to Valley Center substation. | Substation - Multiple | Upgrade/Retrofit | NA | NA | Wildfire Mitigation | System Design Upgrade | NA | NA | 2026-05-11 | 53 | NA | NA | NA | Tier 2 ¦ Tier 3 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | NA | NA | 69 | 373MVA | 1.2 | 2020-1016 | QS00762 | 1 | 24251 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2025-01-16 | Work Order Authorization | 2025 | NA | FALSE | NA | NA | NA | FALSE | TBD | NA | Exempted | NA | CPUC | NA | Exempt | NA | Other [See Notes] | NA | Engineering less than 50% complete |  | 2022-07-18 | 2022-12-31 | 2027-05-31 | Scope Change | Construction Delays | TRUE | 34252.457 | NA ¦ NA | 40619.5101 | 1577.9954 | 5352.3547 | 8586.9166 | 7706.451 | 9136.1785 | 1869.4193 | 5169.2553 | 472.2789 | 0 | 0 | 0 | 9533.4269 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 ¦ 2026 | 2.5985 | 208.7487 | 251.0339 | 306.4601 | 24675.7078 | 10359.9986 | 0% | NA ¦ NA | 34 | NA | 0% | 100% | [CPUC Status] Exempt
347 | North Valley 69/12kV Substation Rebuild |  |  | Oceanside, San Diego | Rebuild and expand the existing North Valley Substation (69/12kV) to improve safety, reliability, and system capacity amid regional growth. Scope includes removal of overhead 12kV distribution lines and undergrounding along North River Road, replacement of aging infrastructure, and expansion of current substation. | Substation - Multiple | Upgrade/Retrofit | NA | NA | Reliability | System Design Upgrade | NA | NA | NA | 46 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.34 | 2.17 | 69 | 69kV ¦12kV | 4.1 | 2020-2092 | QS00770 | 1 | 24252 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2025-01-24 | Work Order Authorization | 2025 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Construction (10%-25%) |  | 2025-12-19 | 2027-02-27 | 2028-03-10 | Scope Change | NA | TRUE | 21262.2381 | NA ¦ NA | 21253.0282 | 713.0957 | 1066.6295 | 1525.8894 | 1113.2468 | 2770.1806 | 2378.0686 | 7728.2298 | 3927.2079 | 20.6141 | 0 | 0 | 5063.2447 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 ¦ 2026 | 0.0026326 | 17.0071 | 2421.2163 | 855.4289 | 1210.2109 | 9790.2093 | 0% | NA ¦ NA | 7.3 | NA | 0% | 100% | [CPUC Status] Exempt
348 | EMS Firewall Replacement FERC 24879 |  |  | NA | This is FERC funded. The OSII Bulk Electric System (BES) and energy management system (EMS) is the new system replacing the current Energy Management System from General Electric that is going end of life and need to be replaced. The new OSII EMS will be SDGE’s primary means of controlling the Transmission Bulk Electric System / Grid Operations. This project is to replace Palo Alto hardware firewalls in support of the new OSII Energy Management System. | Other - IT | Replace | Upgrade/Retrofit | NA | Age/End of Life | System Operations | NA | NA | NA | NA | NA | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | 0 | NA |  | NA | NA | NA | NA | NA | NA | NA | 1 | 24879 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-05-30 | Work Order Authorization | 2024 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Operational |  | 2024-07-09 | 2026-02-24 | 2026-02-24 | NA | NA | TRUE | 1417.4381 | NA ¦ NA | 1505.2648 | 0 | 0 | 0 | 1446.8259 | 54.9197 | 3.5192 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2026 | 0 | 0 | 0 | 0 | 0 | 1505.2648 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] Exempt
349 | TCRI 2025 ET Only (25142) 25142 |  |  | NA | The TCRI (Transmission Communication Reliability Improvement) 2025 project will continue to deploy Multiprotocol Label Switching (MPLS) routers and supporting equipment to SDGE sites in its current service territory and migrating circuits to the new MPLS equipment. This is Electric Transmission only and purely funded from FERC. This is telecom equipment to support electric Transmission Operations. | Other - IT | Replace | Upgrade/Retrofit | NA | Age/End of Life | System Operations | NA | NA | NA | NA | NA | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | 0 | NA |  | NA | NA | NA | NA | NA | NA | NA | 1 | 25142 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2025-02-17 | Work Order Authorization | 2025 | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | NA | NA | TBD | TBD | NA | NA | NA [See Notes] | NA | Operational |  | 2025-01-01 | 2025-12-31 | 2025-12-31 | NA | NA | TRUE | 5570.5657 | NA ¦ NA | 5934.2365 | 0 | 0 | 0 | 0 | 5856.8101 | 77.4265 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2026 | 0 | 0 | 0 | 0 | 0 | 5934.2365 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] Exempt
350 | Miguel Short Circuit Mitigation |  |  | Bonita - San Diego ¦ Chula Vista - San Diego | Reliability transmission solution to address the Short Circuit Duty (SCD) concerns at Miguel: Install a 3-Ohm series reactor on TL23026 Silvergate –Bay Boulevard 230 kV line which will be located at Bay Boulevard substation | Substation - Other Equipment | New | New | NA | CAISO Transmission Planning Standards [See Notes for NERC Compliance and contingency code, WECC Requirement (and the specific requirement)] | System Operations | CAISO Requirement | NA | 2026-05-19 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 2 | 230 | 230kV | 2.1 | 2025-4352 | QS00777 | 1 | 25143 | NA ¦ NA ¦ NA ¦ NA | FALSE | NA | Work Order Authorization | 2025 | 2024 | FALSE | 2024 | NA | https://www.caiso.com/documents/iso-board-approved-2023-2024-transmission-plan.pdf | FALSE | NA | NA | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Engineering less than 50% complete |  | 2027-07-16 | 2035-06-01 | 2035-06-01 | NA | NA | FALSE | 15000 | NA ¦ NA | 74739.4129 | 0 | 0 | 0 | 0 | 75.377 | 146.3864 | 628.5129 | 23128.0826 | 24154.7654 | 26165.16 | 441.1286 | 221.7634 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0% | [CPUC Status] Exempt
351 | Valley Center system Improvement |  |  | Valley Center ¦ Escondido, San Diego | Reliability transmission solution to address several thermal overloads in the 69kV transmission system around Valley Center area due to the charging/discharging of Valley Center energy storage. Construct new 5-mile double circuit 69kV line to create two new lines to Valley Center substation. | Transmission Line/Substation | New | Replace | NA | CAISO Transmission Planning Standards [See Notes for NERC Compliance and contingency code, WECC Requirement (and the specific requirement)] | Substation Reliability | CAISO Requirement | NA | NA | NA | NA | NA | NA | Tier 3 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 5 | 1 | 69 | 69kV | 2.1 | 2025-4354 | QS00776 | 1 | 25144 | NA ¦ NA ¦ NA ¦ NA | FALSE | NA | Work Order Authorization | 2025 | 2024 | FALSE | 2024 | NA | https://www.caiso.com/documents/iso-board-approved-2023-2024-transmission-plan.pdf | FALSE | TBD | TBD | NA | NA | CPUC | NA | PTC | TBD | To be Filed | TBD | Engineering less than 50% complete |  | 2029-10-11 | 2028-06-01 | 2030-02-15 | Permitting | NA | FALSE | 10000 | NA ¦ NA | 70202.2713 | 0 | 0 | 0 | 0 | 930.6912 | 675.6458 | 1215.8841 | 3205.6683 | 14297.1146 | 24217.3296 | 23471.0412 | 1606.337 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
352 | Palo Alto Firewall 25145 |  |  | NA | SDGE Palo Alto ELA Licenses: FERC The Network Security Infrastructure program is focused on providing Sempra with a modernized infrastructure that is flexible, modular and resilient. The pillars of the program are to: Reduce costly and disruptive maintenance windows for our critical applications and services Prioritize the survivability of Tier 0 applications Reduce reliance on single systems with large failure domains Add resiliency to improve business continuity On premises server-based software | Other - IT | Replace | Upgrade/Retrofit | NA | Age/End of Life | System Operations | NA | NA | NA | NA | NA | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | 0 | NA |  | NA | NA | NA | NA | NA | NA | NA | 1 | 25145 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2025-03-18 | Work Order Authorization | 2025 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Operational |  | 2025-03-19 | 2025-04-30 | 2025-04-30 | NA | NA | FALSE | 3545 | NA ¦ NA | 3438.0538 | 0 | 0 | 0 | 0 | 3438.0538 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2025 | 0 | 0 | 0 | 0 | 3438.0538 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] Exempt
353 | Mission 138kV Rebuild |  |  | San Diego, San Diego | Rebuild Mission 138kV substation to upgrade existing breaker infrastructure with new Gas Insulated Substation (GIS) system. | Substation - Circuit Breaker | Upgrade/Retrofit | NA | NA | Reliability | Substation Reliability | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | TBD |  | NA | 9 | 138 | 138kV | 4.1 | TBD | TBD | 1 | 25146 | NA ¦ NA ¦ NA ¦ NA | TRUE | NA | Work Order Authorization | 2025 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | CPUC | NA | NA | NA | Other [See Notes] | NA | Planning |  | TBD | TBD | TBD | NA | NA | FALSE | NA | NA ¦ NA | 33342.4906 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2821.3963 | 6886.9819 | 0 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] TBD
354 | Transmission Work Management Modernization (P) 25147 |  |  | NA | Implement new On-Prem system replacing existing TCMData application with following high-level scope- Business Processes in Scope - TCM Data & Corrective work process migration to SAP TCM -> SAP Technology changes - Implementation of SAP EAM & GEF for Transmission Assets - Integration between SAP & GIS using SAP Connector - Integration from Cityworks to SAP for corrective work Mobile Capabilities - Neptune as the mobility solution for corrective work Reporting - 9 custom reports in SAP for TCM Operational Reports - AWS Asset 360 Report remediation - WMP Data Reporting remediation SAP EHSM Upgrade - Brownfield upgrade of EHSM from 1809 to 2023 (required for full GEF capabilities) | Other - IT | Replace | Replace | NA | Age/End of Life | System Operations | NA | NA | NA | NA | NA | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | 0 | NA |  | NA | NA | NA | NA | NA | NA | NA | 1 | 25147 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2025-07-23 | Work Order Authorization | 2025 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Planning |  | 2025-08-01 | 2026-10-26 | 2026-10-26 | NA | NA | TRUE | 12359.157 | NA ¦ NA | 9689.8968 | 0 | 0 | 0 | 0 | 1810.8628 | 7879.0341 | 0 | 0 | 0 | 0 | 0 | 9689.8968 | NA | NA | 2026 | 0 | 0 | 0 | 0 | 0 | 9689.8968 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] Exempt
355 | Vine Substation 230kV Expansion |  |  | San Diego, San Diego | Expand the existing Vine 69/12 kV substation to a 230/69/12 kV substation; loop TL23029 (Old Town – Silvergate) into the newly expanded Vine substation; install a new 230/69 kV bank (BK70) at Vine substation. Project is part of the overall Downtown Reliability Reinforcement project, which was approved in the CAISO 2024-25 Transmission Plan as a reliability transmission solution to address the thermal overload of Old Town 230/69 kV banks and TL604 Old Town – Vine 69 kV line. | Substation - Multiple | Upgrade/Retrofit | NA | NA | CAISO Transmission Planning Standards [See Notes for NERC Compliance and contingency code, WECC Requirement (and the specific requirement)] | Substation Reliability | CAISO Requirement | NA | 2026-05-05 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | 0 | NA |  | NA | 1.39 | 69 ¦ 230 | 230kV ¦ 69kV ¦ 12kV | 2.1 | VINE230KV | QS00788 | 1 | 25148 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2025-08-07 | Work Order Authorization | 2025 | NA | FALSE | NA | NA | NA | FALSE | TBD | TBD | NA | NA | CPUC | NA | TBD | TBD | Other [See Notes] | TBD | Planning |  | TBD | 2037-12-31 | TBD | NA | NA | TRUE | 29999.3552 | NA ¦ NA | 589699.3055 | 0 | 0 | 0 | 0 | 22158.2241 | 61.3067 | 254.0741 | 715.5819 | 2036.1082 | 2189.871 | 2356.1334 | 22219.5308 | NA | NA | 2025 ¦ 2026 | 0 | 0 | 0 | 0 | 22099.1316 | 12.0986 | 0% | NA ¦ NA | NA ¦ NA | NA | 45.85% | 54.15% | [CPUC Status] TBD
356 | TL50001 Tower Remediation |  |  | San Diego County, Imperial County | Remediate 56 towers to meet GO95 local wind rating of 85 mph. This remediation scope will reduce the risk of de-energizing TL50001 during a PSPS event. There are 41 towers that require simple cross arm reinforcement, 14 towers with moderate cross arm reinforcement, and 1 tower with complex cross arm reinforcement with wire unloading required. | Transmission Line - Pole/Tower | New | NA | NA | Reliability | Age/Condition - Replace Wood Poles | NA | NA | 2026-01-22 | 48 | NA | NA | NA | Tier 2, Tier 3 | FALSE ¦ TRUE ¦ FALSE | 0 | NEPA nexus depends on specific location. |  | 53.4 | NA | 500 | NA | 1.3 | 2025-4460 | QS00793 | 1 | 25149 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2025-08-28 | Work Order Authorization | 2025 | NA | FALSE | NA | NA | NA | FALSE | NA | Exempt | NA | NA | CPUC | BIA, USFS - Discretionary action not anticipated | Exempt | NA | NA [See Notes] | NA | Engineering more than 50% complete |  | 2026-08-04 | 2026-12-15 | 2026-12-15 | NA | NA | TRUE | 4024.241 | NA ¦ NA | 2843.6786 | 0 | 0 | 0 | 0 | 45.9615 | 71.5983 | 2726.1187 | 0 | 0 | 0 | 0 | 117.5598 | NA | NA | 2026 | 0 | 0 | 0 | 0 | 0 | 2843.6786 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0% | [CPUC Status] This project is exempt from CPUC permitting.
357 | BK33, SYO: New Bank 33 |  |  | San Diego, San Diego | Installation of a 69/12 kV substation transformer and associated equipment to mitgate overload. | Substation - Multiple | New | New | NA | Load Growth | Substation Capacity | NA | NA | 2026-04-07 | NA | NA | NA | NA | Tier 2 | FALSE ¦ FALSE ¦ FALSE | 0 | NA |  | NA | 1.57 | 69 | 28MVA | 1.4 | 3-789519 | QS00800 | 1 | 25254 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2025-10-31 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | Exempt | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Engineering less than 50% complete |  | TBD | 2029-06-01 | 2029-06-01 | NA | NA | FALSE | 22087.6005 | NA ¦ NA | 1180.6949 | 0 | 0 | 0 | 0 | 0.36775 | 5.1818 | 131.4894 | 146.5923 | 313.5089 | 583.5546 | 0 | 5.5496 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
358 | BK33, BD: New Bank 33 |  |  | San Diego, San Diego | Installation of a 69/12 kV substation transformer and associated equipment to mitgate overload. | Substation - Multiple | New | New | NA | Load Growth | Substation Capacity | NA | NA | 2026-05-27 | NA | NA | NA | NA | Tier 2 | FALSE ¦ FALSE ¦ FALSE | 0 | NA |  | NA | 0.94 | 69 | 28MVA | 2.3 | NA | QS00815 | 1 | 25255 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2026-03-02 | Work Order Authorization | 2026 | NA | FALSE | NA | NA | NA | FALSE | NA | Exempt | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | On Hold |  | TBD | NA | NA | NA | NA | FALSE | 29326.5388 | NA ¦ NA | 1966.2586 | 0 | 0 | 0 | 0 | 0 | 9.6858 | 361.0947 | 912.5924 | 404.6488 | 278.2369 | 0 | 9.6858 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
359 | BK30, RN: New Bank 30 |  |  | San Diego, San Diego | Installation of a 69/12 kV substation transformer and associated equipment to mitgate overload. | Substation - Multiple | New | New | NA | Load Growth | Substation Capacity | NA | NA | 2026-05-04 | NA | NA | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | 0 | NA |  | NA | 1.22 | 69 | 28MVA | 1.4 | 3-806143 | QS00801 | 1 | 25258 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2025-10-31 | Work Order Authorization | 2025 | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Engineering less than 50% complete |  | TBD | 2028-06-01 | 2028-06-01 | NA | NA | FALSE | 27771.6057 | NA ¦ NA | 1789.5794 | 0 | 0 | 0 | 0 | 0.41036 | 17.0565 | 60.8116 | 267.9115 | 1278.1776 | 165.2119 | 0 | 17.4668 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Exempt
360 | Smart Meter 1.0 Refundable |  |  | Multiple | The 2024 GRC denied the SM2.0 and the Smart Meter Upgrade projects and directed SDGE to file a separate application to seek recovery of the costs for both projects as well as to file a Tier 2 Advice Letter to establish a memorandum account to record its O&M and capital expenses for a future cost-reasonableness review. Smart Meter Network Device Mitigation was not included in the 2024 GRC, hence SDGE is including Smart Meter Network Mitigation in this application to seek recover of costs as well. 1. Smart Meter Upgrade - Openway Collection System, Meter Data Management System and Certicom 2. Smart Meter Operation Persistent Team is required to enhance and develop new software applications and tools for the core Meter to Cash applications: SmartMeter, Meter Data Management System, Openway Collection Engine (OWCE), What’s Up Gold (WUG) MV90, COKE, DataMart, CEN, Meter Shop Activity Portal(MSAP) and SCG Core Balancing.Upgrade CEN system which provides consumption data to be downloaded by 3rd parties. 3. Smart Meter Network Device Mitigation: a. Mitigate communication issues to effectively recover stranded capital assets (2,527 non communicating Smart Meters b. Purchase and install Smart Meter hardware to accommodate the annual expansion of gas and electric meters. This project will test and deploy new network hardware and advanced communication devices to effectively resolve communication issues for approximately 25% of stranded meters in the field. Mitigation and infrastructure expansion are a fundamental, perpetual part of Smart Meter Operation. | Multiple Options [See Notes] | Replace | Upgrade/Retrofit | NA | Age/End of Life | Age/Condition | NA | NA | NA | NA | NA | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | 0 | NA |  | NA | NA | NA | NA | NA | NA | QS00806 | 1 | 25883 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2025-12-12 | Work Order Authorization | 2022 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | CPUC | NA | Other [See Notes] | 2025-12-28 | Filed and Under Administrative Review | NA | Planning |  | 2027-07-01 | 2027-07-01 | 2027-07-01 | NA | NA | TRUE | 15597.216 | NA ¦ NA | 8259.4227 | 0 | 258.1472 | 595.2288 | 749.7584 | 508.3505 | 107.1414 | 554.1785 | 1231.1688 | 1481.7875 | 938.3329 | 1144.2587 | 107.1414 | NA | NA | 2024 ¦ 2025 ¦ 2026 | 0 | 0 | 0 | 1603.1344 | 508.3505 | 661.3199 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [Project Description - What] Deployment of next generation smart metering technology and hardware
361 | Sampson 69kV Overstressed Breaker Replacement |  |  | San Diego, San Diego | Breaker replacement is a part of the greater Downtown Reliability Project. Replacing (9) 69kV circuit breakers with 63kA-rated units to improve substation reliability and support new customer loads. | Substation - Multiple | New | Upgrade/Retrofit | NA | Reliability | Substation Reliability | NA | NA | 2026-04-20 | NA | Short Circuit Duty Analysis | NA | $400 Mil - $500 Mil | NA | FALSE ¦ FALSE ¦ FALSE | 0 | NA |  | NA | 0.71 | 69 | 69¦12kV | 2.1 | TBD | NA | 1 | 26156 | NA ¦ NA ¦ NA ¦ NA | FALSE | NA | Work Order Authorization | 2026 | 2024-2025 | FALSE | 2024 ¦ 2025 | 2024 ¦ 2025 | https://stakeholdercenter.caiso.com/InitiativeDocuments/BoardApproved-2024-2025-TransmissionPlan.pdf | FALSE | TBD | NA | NA | NA | NA | NA | NA | NA | Other [See Notes] | NA | Planning |  | TBD | TBD | TBD | NA | NA | FALSE | NA | NA ¦ NA | 13809.572 | 0 | 0 | 0 | 0 | 0 | 2.7682 | 8.6831 | 1502.6548 | 6716.8008 | 5578.665 | 0 | 2.7682 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] TBD
362 | SDGE TCRI 2026 26157 |  |  | NA | The TCRI (Transmission Communication Reliability Improvement) 2026 project will continue to deploy Multiprotocol Label Switching (MPLS) routers and supporting equipment to SDGE sites in its current service territory and migrating circuits to the new MPLS equipment. This is Electric Transmission only and purely funded from FERC | Other - IT | Replace | Upgrade/Retrofit | NA | Age/End of Life | System Operations | NA | NA | NA | NA | NA | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | 0 | NA |  | NA | NA | NA | NA | NA | NA | NA | 1 | 26157 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2026-01-22 | Work Order Authorization | 2026 | NA | FALSE | NA | NA | NA | FALSE | NA | TBD | NA | NA | CPUC | TBD | NA | NA | NA [See Notes] | NA | Planning |  | 2026-01-01 | 2026-12-31 | 2026-12-31 | NA | NA | TRUE | 10742.46 | NA ¦ NA | 29912.6828 | 0 | 0 | 0 | 0 | 0 | 9272.6828 | 0 | 10320 | 0 | 0 | 0 | 9272.6828 | NA | NA | 2026 | 0 | 0 | 0 | 0 | 0 | 9272.6828 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] Exempt
363 | SOCRE (South Orange County Reliability Enhancement) |  |  | San Juan Capistrano, Orange ¦ San Clemente, Orange | To rebuild the existing Capistrano Substation, which is currently a 138/12kV distribution substation to a 230/138/12kV. Remove TL13835 (SMO-LNL) between Talega Substation and Capistrano Substation. Open TL23007 (SONGS-TA) at Talega Substation and loop into Capistrano Substation two new 230kV TLs (SONGS-CP230kV & CP-TA 230kV). Re-arrange 138kV TLs 13833, 138736, and 13812 bay positions at Talega to allow for the termination of TL13835 (SMO-TA) at Talega Substation. | Transmission Line/Substation | Upgrade/Retrofit | New | NA | Load Growth | Substation Capacity | NERC TPL Standards | NA | 2026-05-26 | 56; 63; 53; 57; 55; 20 | Steady State Power Flow System Analysis | Wires - Reconductor/Line Rebuild Alternative | Multiple Options [See Notes] | Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | Transmission Foundations At Talega Canyon Containing High Levels Of Sulfate. Mitigated By Installing Cmp To Protect Concrete Foundations |  | 9.133859 | 6 | 230 | 230kV | 2.1 | 2014-00068-ZZ | QS00009 | 1 | 6129 | NA ¦ NA ¦ NA ¦ NA | FALSE | NA | Work Order Authorization | 2006 | 2011 | FALSE | 2011 | NA | https://www.caiso.com/planning/Pages/TransmissionPlanning/2010-2011TransmissionPlanningProcess.aspx | FALSE | Final Certified | 2016-04-25 | EIR | NA | CPUC | NA | CPCN [A.12-05-020] | 2012-05-18 | Approved | 2016 | Operational |  | 2018-06-29 | 2015-05-18 | 2024-08-15 | Construction Delays | NA | TRUE | 363363 | $410,000 ¦ CPUC | 363308.4963 | 46910.7232 | 29821.7373 | 39636.0331 | 15518.8887 | 631.0566 | 1047.0297 | 1612.6835 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 ¦ 2026 | 132700.278 | 5577.5856 | 129956.0519 | 15600.8675 | 631.0566 | 2659.7132 | 0% | NA ¦ NA | 10.6 | NA | 100% | 0%
364 | TL6926 Rincon to Valley Center Fire Hardening |  |  | Valley Center, San Diego | Fire harden a portion of TL6926 by replacing approximately 50 wood poles with equivalent steel poles in the high fire threat and wind-prone areas. TL6926 is a single circuit 69 kV transmission line located between the Valley Center Substation and the Rincon Substation. Approximately one mile of the line will be reconductored. The line will be fire hardened between poles Z12820 and Z114811, with the exception of the portion located adjacent to Valley Center Road near the Rincon Casino. Approximately one mile of the transmission line will be reconductored. | Transmission Line - Multiple | Replace | Removal | NA | Wildfire Mitigation | T-Line Reliability | NA | NA | 2026-02-03 | NA | NA | NA | NA | Tier 3 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 4.637369 | NA | 69 | NA | 1.2 | 2014-00061-ZZ | QS00025 | 1 | 9132 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2011-12-08 | Work Order Authorization | 2009 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | NA | NA | AL [3460-E] | 2019-11-13 | Approved | 2020 | Operational |  | 2020-10-19 | 2013-01-31 | 2022-12-15 | Permitting | Multiple Options [See Notes] | FALSE | 65729 | NA ¦ NA | 104571.112 | 57303.6517 | 16554.1531 | 2325.7931 | 333.3879 | -369.0542 | 0 | 0 | 1891.3275 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 1.1761 | 99114.3707 | 3515.0473 | 333.3879 | -369.0542 | 0 | 0% | NA ¦ NA | 21.6 | NA | 0% | 100% | [Reason for Change in In-Service Date] Project Design ¦ Construction delays, County of Valley Center issuing a stop work order due to dewatering issues.
365 | TL686 W2S_Wind |  |  | San Diego, San Diego | TL686 Wood-to-Steel will include the replacement of 182 wood and wood equivalent steel (SW) poles with 120 new poles. Scope includes the reconductoring of 14.6 miles of 69kV transmission and associated 12kV distribution underbuild (where underbuild is present) from Warners substation to just outside the Tier 2 HFTD (ending at structure Z118409). All replacements will be either direct-buried SW poles or foundation steel poles. Per SDG&E’s fire hardening standards, traditional 69 kV design and construction standards with additional phase spacing and insulation shall be used and guy anchors shall be avoided. Shield wire with a fiber (OPGW) will be added to protect phase conductors from lightning damage. All transmission conductors in this project shall be reconductored. All poles will be designed to accommodate one level of third-party communication. | Transmission Line - Pole/Tower | Replace | Removal | 23126 | Wildfire Mitigation | T-Line Reliability | NA | NA | 2026-01-22 | 47.7975 | NA | NA | NA | Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | Project On Hold |  | 14.6 | NA | 69 | NA | 1.2 | 2018-0161 | QS00027 | 1 | 9142 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-11-06 | Work Order Authorization | 2012 | NA | FALSE | NA | NA | NA | FALSE | NA | Stat Ex | Exempted | NA | CPUC | BLM | Exempt | NA | NA [See Notes] | NA | On Hold |  | 2036-07-15 | 2027-08-24 | 2038-01-04 | Bundling Dependencies | NA | FALSE | 5446.0598 | NA ¦ NA | 146731.2655 | 1923.6474 | 1337.7718 | 1315.6179 | -66.3227 | 982.4966 | 88.2421 | 609.6849 | 723.2407 | 786.0152 | 858.8678 | 938.4845 | 5581.453 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | 7.2 | NA | 0% | 100% | [CPUC Status] Exempt
366 | CNF MSUP |  |  | Multiple | Design, procure materials for and construct Cleveland National Forest (CNF) Master Special Use Permit (MSUP) fire hardening program | Other | NA | NA | NA | Wildfire Mitigation | Fire Protection | NA | NA | NA | NA | NA | NA | NA | Tier 2 ¦ Tier 3 | FALSE ¦ FALSE ¦ FALSE | FALSE | Complete |  | NA | NA | Multiple | NA | 1.2 | Multiple | NA | 1 | 8165 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2016-06-15 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | TBD | NA | NA | NA | CPUC | CNF | PTC [A.12-10-009] | 2012-10-17 | Approved | 2016 | Operational |  | Multiple | Multiple | Multiple | NA | NA | FALSE | 418777 | NA ¦ NA | 423436.973 | 16335.9501 | 686.2607 | 94.14 | 13.5584 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 | 14926.9032 | 686.2607 | 94.14 | 15.8146 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 45.85% | 54.15% | [Utility Unique ID #1(Most Specific)] CNF-C157, CNF-C222, CNF-C440 I, CNF-C440 II, CNF-C442, CNF-C449, CNF-C79A, CNF-C79B, CNF-EPC-63, CNF-TL625C, CNF-TL626, CNF-TL629A, CNF-TL629C, CNF-TL682, CNF-TL6923, CNF-TL6931,CNF-TL6957, CNF-TL6958
367 | CIS Envision |  |  | NA | Replacing SDG&Es legacy Customer Information System (CIS) with a new SAP system | Other - IT | Replace | NA | NA | Age/End of Life | Age/Condition | NA | NA | NA | 60 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | NA | NA | NA | NA | QS00194 | 1 | CIS001 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2018-09-11 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | TBD | NA | NA | NA | NA | NA | Application 17-04-027 | 2017-04-27 | Approved | 2018 | Operational |  | NA | 2021-01-31 | NA | NA | NA | FALSE | 187200.951 | NA ¦ NA | 30267.6924 | 7032.298 | 2.6294 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 | 29155.1242 | 2.6294 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0%
[65 empty] | actual | [5 empty] | forecast
[65 empty] | 25976.3098 | [5 empty] | 181994.3695
2028-2030
126183.3265

## Options List
06. Project Description - What | 07. Project Description - Action taken | 09. Primary Purpose | 10. Secondary Purpose | 11. NERC/WECC/CAISO Standard/Requirement/Contingency | 14. Types of Analyses | 15a. Alternative Solutions and Costs - Solutions | 15b. Alternative Solutions and Costs - Costs | 40. CEQA Status | 41a. CEQA Document Type | 41b. NEPA Document Type | 45. CPUC Status | 47. Project Status | 48. AACE Class | 52. Reason for Change in In-Service Date | Complete
Substation - Multiple | New | CAISO Transmission Planning Standards [See Notes for NERC Compliance and contingency code, WECC Requirement (and the specific requirement)] | 3rd Party Damage | NERC CIP Compliance | Lifecycle Replacement Analysis | Wires - System Configuration Alternative | $0 Mil – $1 Mil | Expected PEA Completion | IS/ND | EIS | To be Filed | Planning | 1 | Weather | Yes
Substation - Other Equipment | Replace | Reliability | Age/Condition | NERC BAL Compliance | Steady State Power Flow System Analysis | Wires - Location/Route Alternative | $1 Mil - $2 Mil | PEA Deemed Complete | IS/MND | EA | Filed and Under Administrative Review | Engineering less than 50% complete | 2 | Permitting | No
Substation - Transformer | Upgrade/Retrofit | Load Growth | Age/Condition - 230/115/70/60 kV Relay Replacement | NERC FAC Compliance | Dynamic System Analysis | Wires - Reconductor/Line Rebuild Alternative | $2 Mil - $3 Mil | CEQA Draft Published | EIR | Categorical Exclusion | Administratively Complete and Under Technical Review | Engineering more than 50% complete | 3 | Clearances
Substation - Circuit Breaker | Relocate | Local Capacity Requirement | Age/Condition - 500 kV Relay Replacement | WECC Audit Findings | Short Circuit Duty Analysis | Wires - Replacement Alternative | $3 Mil -$5 Mil | CEQA Final Published | Exempted | Other [See Notes] | Approved | Permitting | 4 | Material
Substation - Line Termination | Removal | Address Results of Power Flow Analysis | Age/Condition - Anti Climb Guards | NERC PRC Compliance | Protection Studies | Wires - Minimum Required Scope (spot repair) Alternative | $5 Mil - $10 Mil | Final Certified | Other [See Notes] | NA | Rejected | Construction (under 10%) | 5 | Workforce
Substation - Voltage Support Equipment | NA | Address Results of Protection Studies | Age/Condition - Insulator Replacement - Steel | NERC TPL Standards | Interconnection System Impact/Facilities Studies | Wires - Voltage Support/Reactive Support Alternative | $10 Mil -$15 Mil | TBD | NA |  | Advice Letter Filed and In-Process | Construction (10%-25%) | NA | Prioritization
Substation - Bus Arrangement | Multiple Options [See Notes] | Physical Security | Age/Condition - Insulator Replacement - Wood | CAISO Requirement | Other [See Notes] | Wires - New Substation Alternative | $15 Mil - $20 Mil | Other [See Notes] |  |  | Other [See Notes] | Construction (25%-50%) |  | Bundling Dependencies
Substation - Switch |  | Policy | Age/Condition - Raptor Protection - Steel | Other [See Notes] | Multiple Options [See Notes] | Wires - Bus Upgrade Alternative | $20 Mil - $30 Mil | NA |  |  | NA [See Notes] | Construction (50%-75%) |  | Customer Action
Substation - Modular Protection and Automation Control Building |  | Economic | Age/Condition - Replace 230/115/70/60 kV Breakers | NA | NA | Wires - New T-Line Alternative | $30 Mil - $40 Mil |  |  |  |  | Construction (over 75%) |  | ISO Action
Substation - Protection Relay |  | Generator Interconnection | Age/Condition - Replace 230/115/70/60 kV Transformers | Multiple Options [See Notes] |  | Non-Wires - Large Scale Energy Alternative | $40 Mil - $50 Mil |  |  |  |  | Operational |  | Completed Early
Substation - Reactive Equipment |  | Work Requested by Others | Age/Condition - Replace 500 kV Breakers |  |  | Non-Wires - System DER Alternative | $50 Mil – $75 Mil |  |  |  |  | On Hold |  | Construction Delays
Substation - Structure |  | Age/End of Life | Age/Condition - Replace 500 kV Transformers |  |  | Other - Status Quo | $75 Mil – $100 Mil |  |  |  |  | Canceled |  | Outage
Other - IT |  | Wildfire Mitigation | Age/Condition - Replace Boardwalks |  |  | Other - Deferral | $100 Mil – $125 Mil |  |  |  |  | Abandoned |  | Project Design
Other - Physical Security |  | Field Test Results | Age/Condition - Replace Breakers |  |  | TBD | $125 Mil - $150 Mil | [6 empty] | Input Error
Other - Operations Tech |  | Emergency Event | Age/Condition - Replace Civil Structures |  |  | NA | $150 Mil - $175 Mil | [6 empty] | Vendor Quality/Delays
Other - Cybersecurity |  | Location, Environmental Conditions | Age/Condition - Replace Conductor |  |  |  | $175 Mil - $200 Mil | [6 empty] | Scope Change
Other - Remedial Action Scheme/Special Protection Scheme |  | Safety | Age/Condition - Replace Insulators |  |  |  | $200 Mil - $250 Mil | [6 empty] | Land Rights
Other |  | Asset Condition | Age/Condition - Replace Other Substation Equipment |  |  |  | $250 Mil – $300 Mil | [6 empty] | Other [See Notes]
Other - Environmental |  | Other [See Notes] | Age/Condition - Replace Other T-Line Equipment |  |  |  | $300 Mil - $350 Mil | [6 empty] | NA
Other - Civil |  |  | Age/Condition - Replace Reactors, Age/Condition - Replace Relays |  |  |  | $350 Mil – $400 Mil | [6 empty] | Multiple Options [See Notes]
Transmission Line/Substation |  |  | Age/Condition - Replace Relays |  |  |  | $400 Mil - $500 Mil
Transmission Line - Multiple |  |  | Age/Condition - Replace SCADA/RTU |  |  |  | Over $500 Mil
Transmission Line - Switch |  |  | Age/Condition - Replace Steel Poles |  |  |  | Multiple Options [See Notes]
Transmission Line - Underground |  |  | Age/Condition - Replace Switches, Age/Condition - Replace Transformers |  |  |  | NA
Transmission Line - Pole/Tower |  |  | Age/Condition - Replace Underground System
Transmission Line - Conductor |  |  | Age/Condition - Replace Wood Poles
Transmission Line - Other Equipment |  |  | Age/Condition - Switch Replacement - Steel
Transmission Line - Right of Way |  |  | Age/Condition - Switch Replacement - Wood
Multiple Options [See Notes] |  |  | Age/Condition - Targeted Relay Replacement
Age/Condition - Wood Pole Reframe
Animal Abatement
Automation
Bus Upgrade
Compliance - Remove Idle Facilities
Construct Roads/Gates/Culverts
Emergency Response - Fire Related
Emergency Response - Storm Related
Environmental
Facility Relocation
Fire Protection
Generation Interconnection
GO95 Mitigation - Steel
Install SCADA/RTU
Line Reconductoring
Line Termination
Load Interconnection
Modular Protection and Automation Control
NERC CIP Compliance
NERC Compliance - GO 95
New Substation
New T-Line
Priority 1 Steel Structure Replacement
Priority 1 Wood Structure Replacement
Protection NERC Compliance
Relay Upgrades
Replace Breakers
Replace Other Substation Equipment
Replace Transformer
Safety - Line Right of Way Access
SCADA Emergency Replacement
SCADA Switch Installation
Security Upgrades
Seismic Upgrade - Replace Conductor
Special Protection Scheme
Substation Capacity
Substation Reliability
System Design Upgrade
System Operations
Targeted Line Reliability
T-Line Capacity
T-Line Emergency
T-Line Reliability
Tools, Transformer Addition/Replacement
Underground Emergency
Voltage Conversion
Voltage Support

## Definitions
Category | Sorting Order | Data Field # | Transmission Project Data Field | Format | Example | Input Terms and Descriptions
Project Description | 1 | 1 | Row/Line No. | Number (whole number) | 4 | Row/line number in spreadsheet. Include separate project lines, as described and required in data fields 26-28, for all subparts, i.e., ID #1 of all FERC-jurisdictional electric transmission projects, including generator interconnection-related network upgrades: 1. the total cost of which At Unique ID #2 will at any point equal or exceed $1 million. In the event that there is no ID#2 to provide, the million-dollar threshold applies to ID #1. and 2. for which there were capital expenditures in the last five years OR for which any capital expenditures are anticipated in the current or next four years, regardless of the actual or anticipated operative date. Each project should have at least one Row/Line No. in this spreadsheet, as subparts of projects will require additional project lines.
Project Description | 2 | 2 | Project Name | Text String, separated by " ¦ " as necessary | Manzanita Substation | Include Project Name at date of report filing. Identify all prior names of the project and other names currently used in different venues, including the name as approved and included in the CAISO's TPP.
Project Description | 3 | 3a | Latitude | Number (decimal), separated by " ¦ " for multiple locations; NA if no geolocation | 20.234 ¦ 19.983 | Positive number indicates north of equator. Subject to redaction in the public data.
Project Description | 4 | 3b | Longitude | Number (decimal), separated by " ¦ " for multiple locations; NA if no geolocation | -132.018 ¦ -132.231 | Negative number indicates west of Prime Meridian. Subject to redaction in the public data.
Project Description | 5 | 4 | Location 2 | Text String, with comma separator between City and County. Multiple entries separated by " ¦ ". Order of values to be consistent with latitude and longitude values * City1, County1 ¦ City2, County2 | Berkeley, Alameda ¦ Concord, Contra Costa | All Cities and Counties included in the scope of the project.
Project Description | 6 | 5 | Project Description | Text String | This project will repair the transmission line connecting 4th and Townsend to the East Northfork station which failed as consequence of the 2019 San Clemente Hedge Fire. Assets to be replaced include... at ....kV. | General project overview: what, where, and why. Discuss all assets to be installed and include all capacities (MVA) and voltages (kV).
Project Description | 7 | 6 | Project Description - What | Select text from drop-down menu | Substation - Circuit Breaker | Transmission line (new, reconductor, relocation), substation (breaker, transformer relay protection), etc.
Project Description | 8 | 7 | Project Description - Action Taken (2) | Select text from drop-down menu(s) | Upgrade/Retrofit | See drop-down menu for options. If more than two options are required, select "Multiple Options" in second column and provide remaining responses, pipe-delimited, in "Notes" data field. If the primary or secondary purpose relates to complying with a NERC, WECC, or CAISO requirement, list the specific standard(s), requirement(s), and/or any contingencies that are being addressed.
Project Description | 9 | 7 | Project Description - Action Taken | Select text from drop-down menu(s) | Upgrade/Retrofit | See drop-down menu for options. If more than two options are required, select "Multiple Options" in second column and provide remaining responses, pipe-delimited, in "Notes" data field. If the primary or secondary purpose relates to complying with a NERC, WECC, or CAISO requirement, list the specific standard(s), requirement(s), and/or any contingencies that are being addressed.
Project Description | 10 | 8 | Project Dependencies | Number (whole) indicating required project or projects' Unique ID #(s), separated by " ¦ " as necessary | 235435 ¦ 432787 | Identify all other projects (Unique ID #1) in the spreadsheet that this project depends on and/or whose construction will be bundled with this project.
Project Description | 11 | 9 | Primary Purpose | Select text from drop-down menu | Reliability | May include, but not limited to: CAISO Transmission Planning Standards (NERC Compliance and contingency code, WECC Requirement (and the specific requirement)), Reliability, Load Growth, Local Capacity Requirement, Address Results of Power Flow Analysis, Address Results of Protection Studies, Physical Security, Policy, Economic, Generator Interconnection, Work Requested by Others, Age/End of Life, Wildfire Mitigation, Field Test Results, Emergency Event, Location, Environmental Conditions, Safety, Asset Condition, or Other. In the "Notes" data field, please explain a purpose identified as "Other" or provide additional details on the purpose identified.
Project Description | 12 | 10 | Secondary Purpose | Select text from drop-down menu | Age/Condition - Anti Climb Guards | May include, but not limited to: 3rd Party Damage, Age/Condition, Age/Condition - 230/115/70/60 kV Relay Replacement, Age/Condition - 500 kV Relay Replacement, Age/Condition - Anti Climb Guards, Age/Condition - Insulator Replacement - Steel, Age/Condition - Insulator Replacement - Wood, Age/Condition - Raptor Protection - Steel, Age/Condition - Replace 230/115/70/60 kV Breakers, Age/Condition - Replace 230/115/70/60 kV Transformers, Age/Condition - Replace 500 kV Breakers, Age/Condition - Replace 500 kV Transformers, Age/Condition - Replace Boardwalks, Age/Condition - Replace Breakers, Age/Condition - Replace Civil Structures, Age/Condition - Replace Conductor, Age/Condition - Replace Insulators, Age/Condition - Replace Other Substation Equipment, Age/Condition - Replace Other T-Line Equipment, Age/Condition - Replace Reactors, Age/Condition - Replace Relays, Age/Condition - Replace Relays, Age/Condition - Replace SCADA/RTU, Age/Condition - Replace Steel Poles, Age/Condition - Replace Switches, Age/Condition - Replace Transformers, Age/Condition - Replace Underground System, Age/Condition - Replace Wood Poles, Age/Condition - Switch Replacement - Steel, Age/Condition - Switch Replacement - Wood, Age/Condition - Targeted Relay Replacement, Age/Condition - Wood Pole Reframe, Animal Abatement, Automation, Bus Upgrade, Compliance - Remove Idle Facilities, Construct Roads/Gates/Culverts, Emergency Response - Fire Related, Emergency Response - Storm Related, Environmental, Facility Relocation, Fire Protection, Generation Interconnection, GO95 Mitigation - Steel, Install SCADA/RTU, Line Reconductoring, Line Termination, Load Interconnection, Modular Protection and Automation Control, NERC CIP Compliance, NERC Compliance - GO 95, New Substation, New T-Line, Priority 1 Steel Structure Replacement, Priority 1 Wood Structure Replacement, Protection NERC Compliance, Relay Upgrades, Replace Breakers, Replace Other Substation Equipment, Replace Transformers, Safety - Line Right of Way Access, SCADA Emergency Replacement, SCADA Switch Installation, Security Upgrades, Seismic Upgrade - Replace Conductor, Special Protection Scheme, Substation Capacity, Substation Reliability, System Design Upgrade, System Operations, Targeted Line Reliability, T-Line Capacity, T-Line Emergency, T-Line Reliability, Tools, Transformer Addition/Replacement, Underground Emergency, Voltage Conversion, Voltage Support. If the secondary purpose is to comply with a NERC, WECC, or CAISO requirement, list the standard, requirement, and/or any contingencies that are being addressed in the "Notes" data field.
Project Description | 13 | 11 | NERC / WECC / CAISO Standard / Requirement / Contingency | Select text from drop-down menu(s) | CIP-006 | See drop-down menu for options. If more than two options are required, select "Multiple Options" in second column and provide remaining responses, pipe-delimited, in "Notes" data field. If the primary or secondary purpose relates to complying with a NERC, WECC, or CAISO requirement, list the specific standard(s), requirement(s), and/or any contingencies that are being addressed in the "Notes" data field.
Project Description | 14 | 11 | NERC/WECC/CAISO Standard/Requirement/Contingency (2) | Select text from drop-down menu(s) | CIP-006 | See drop-down menu for options. If more than two options are required, select "Multiple Options" in second column and provide remaining responses, pipe-delimited, in "Notes" data field. If the primary or secondary purpose relates to complying with a NERC, WECC, or CAISO requirement, list the specific standard(s), requirement(s), and/or any contingencies that are being addressed in the "Notes" data field.
Project Description | 15 | 12 | Last Inspection | Date, formatted YYYY-MM-DD if text; NA if not yet inspected | 2019-12-10 | Specific date when the last inspection of the asset being repaired, replaced, or upgraded occurred.
Project Description | 16 | 13 | Age of Asset | Number (whole number) | 12 | Age in years from original in-service date of the asset being repaired, replaced, or upgraded.
Project Description | 17 | 14 | Types of Analyses | Select text from drop-down menu | Load Flow | Types of analyses that have been performed on the asset being repaired, replaced, or upgraded (e.g., load flow, short circuit, corrosion). List all field test and results that indicated the need for the project, and include inspector ID, when available in the "Notes" data field.
Project Description | 18 | 15a | Alternative Solutions and Costs - Solutions | Select text from drop-down menu(s) | Dynamic System Analysis | See drop-down menu for options. If more than two options are required, select "Multiple Options" in second column and provide remaining responses, pipe-delimited, in "Notes" data field. Include all alternative solutions to the project that were considered and the costs of all alternatives considered.
Project Description | 19 | 15b | Alternative Solutions and Costs - Costs | Select text from drop-down menu(s) | $5 Mil - $10 Mil | See drop-down menu for options. If more than two options are required, select "Multiple Options" in second column and provide remaining responses, pipe-delimited, in "Notes" data field. If multiple responses as included for the Sulutions and Costs fields, please provide costs in the same order as solutions.
Project Description | 20 | 16 | CPUC Fire Threat Zone/Rating | Text String, separated by " ¦ " as necessary, or NA | HFTD Tier 2 | Indicate whether the project is located in Tier1, Tier 2, or Tier 3 of CPUC's High Fire-Threat Districts (HFTD) or Zone 1 in CalFire/USFS High Hazard Zone (HHZ).
Project Description | 21 | 17 | Wildfire Related | Boolean, TRUE or FALSE, divided by " ¦ " | TRUE ¦ TRUE ¦ FALSE | Indicate whether the project is 1. related to repairing wildfire damage, 2. a measure identified in the Wildfire Mitigation Plan, or 3. is related to wildfire in some other way. If #3, please explain in the "Notes" data field.
Project Description | 22 | 18 | RAMP | Boolean, TRUE or FALSE | TRUE | Indicate whether the project is a proposed mitigation measure in the utility's Risk Assessment & Mitigation Phase (RAMP).
Project Description | 23 | 19 | Other Environmental Factors | Text String, or NA | Project exists in CA Building Climate Zone 3 which presents a high risk of accelerated oxidation or steel structures due to coastal humidity and salt exposure. | Environmental factors in the project's location that may affect the length of the asset's service life.
Project Description | 24 | 20 | Project Manager | Text String: Last, First | Doe, John | Person in charge of the implementation of this project for the Utility.
Project Description | 25 | 21 | Transmission Project Size (length in miles) | Number (decimal), or NA | 42.66 | Miles of transmission power lines included in the project.
Project Description | 26 | 22 | Substation Project Footprint (acres) | Number (decimal), or NA | 12.25 | Acres of substation footprint included in the project.
Project Description | 27 | 23 | Transmission Voltage Level (kV) | Number (whole), or NA | 230 | Use kV for transmission power lines ratings.
Project Description | 28 | 24 | Substation or Transformer Capacity (MVA and/or kV) | Text String, or NA if unrelated | 115kV | Use MVA and/or kV for substations.
Project Description | 29 | 25 | Utility Prioritization Ranking | Number (whole), in reference to ranking system identified in field name | 1 | Using the Utility's prioritization ranking. If multiple metrics are used to prioritize projects, please include a separate data subfield for each. (Sub-columns can be created to accommodate multiple or tiered ranking methodologies.)
Project Description | 30 | 26 | Project ID (Utility Unique ID #1) | Text String | 78493 | Most specific (PG&E = Planning Order, SCE = SCE ID, SDG&E = Project ID)
Project Description | 31 | 27 | Parent Work Order (Utility Unique ID #2) | Text String | 432 | Less specific (PG&E = T.dot, SCE = Capital Work Breakdown Structure, SDG&E = Parent Work Order)
Project Description | 32 | 28 | Budget Code (Utility Unique ID #3) | Text String | 92 | Least specific (PG&E = Major Work Category, SCE = Project Identification Number , SDG&E = Budget Code)
Project Description | 33 | 29 | Changes in Unique IDs | Date, formatted YYYY-MM-DD, and former identifiers: YYYY-MM-DD ¦ UID1 ¦ UID2 ¦ UID 3 If any components remain unchanged, use NA for those UIDs | 2022-05-05 ¦ NA ¦ NA ¦ 78322 | If any of the Unique IDs above changed at any time, please note the date of change and the former ID.
Utility/CAISO Approval and FERC Rate Cases | 34 | 30 | Utility Approval | Boolean: TRUE or FALSE | TRUE | "TRUE" if the Utility self-approved the project; "FALSE" if not.
Utility/CAISO Approval and FERC Rate Cases | 35 | 31 | Year of Internal Utility Approval | Date, formatted YYYY-MM-DD, or NA | 2022-01-02 | If utility has approved the project, insert first year of internal approval. If not insert "NA."
Utility/CAISO Approval and FERC Rate Cases | 36 | 32 | Process(es) for Utility Approval | Text String, or NA | Annual Capital Operating Plan Process | If utility has approved the project, insert utility approval process for which a description has been provided to the CPUC and Stakeholders.
Utility/CAISO Approval and FERC Rate Cases | 37 | 33 | Long term Transmission Investment Plan Inclusion | Year, formatted YYYY | 2022 | The year in which the project was first included in the utility's long-term transmission investment plan.
Utility/CAISO Approval and FERC Rate Cases | 38 | 34 | CAISO Year | Year, formatted YYYY, or NA | 2019 | Insert the year when approved by CAISO. If not a CAISO-approved project, insert "NA".
Utility/CAISO Approval and FERC Rate Cases | 39 | 35 | Transmission Planning Process ("TPP") Phase 3 | Boolean: TRUE or FALSE | FALSE | Please indicate with "TRUE" if any part of this project was subject to the competitive solicitation process in the TPP. In the "Notes" section briefly describe any portion of the project awarded to another developer and how it relates to the project in this Spreadsheet.
Utility/CAISO Approval and FERC Rate Cases | 40 | 36 | Year(s) when considered in CAISO TPP | Years, formatted YYYY and separated by " ¦ ", or NA | 2020 ¦ 2021 | Indicate years in which the project was considered in the TPP. If considered in year(s) prior to CAISO approval, please indicate all years.
Utility/CAISO Approval and FERC Rate Cases | 41 | 37 | Year when expected to be considered in CAISO TPP | Years, formatted YYYY and separated by " ¦ ", or NA | 2025 | If not yet considered in the CAISO TPP, indicate the year when it is expected to be considered in the CAISO TPP.
Utility/CAISO Approval and FERC Rate Cases | 42 | 38 | Link to TPP where project has been considered, approved, and/or expected to be considered | URL | http://www.caiso.com/Documents/BoardApproved-2017-2018_Transmission_Plan.pdf | Insert active hyperlink to any TPP where project was considered, including years in which the project was not approved.
Utility/CAISO Approval and FERC Rate Cases | 43 | 39 | Generator Interconnection and Deliverability Allocation Procedures (GIDAP) Related | Boolean: TRUE or FALSE | TRUE | Please indicate with TRUE or FALSE whether this transmission project is a transmission network upgrade related to generator interconnection(s).
CPUC Permit Status | 44 | 40a | CEQA Status | Select text from drop-down menu | Final Certified | See drop-down menu for options. Include one of the following: Expected PEA Completion, PEA Deemed Complete, CEQA Draft Published, CEQA Final Published, Final Certified, TBD, Other [See Notes], or NA.
CPUC Permit Status | 45 | 40b | CEQA Status - Date | Date, formatted YYYY-MM-DD, or NA | 2020-03-29 | Include the date that corresponds with the CEQA status.
CPUC Permit Status | 46 | 41a | CEQA Document Type | Select text from drop-down menu | EIR | Examples include: IS/ND, IS/MND, EIR, Exempted, Other, or NA (If "Other," include explanation in the "Notes" data field.).
CPUC Permit Status | 47 | 41b | NEPA Document Type | Select text from drop-down menu | EIS | Examples include: EIS, EA, Categorical Exclusion, Other, or NA (If "Other," include explanation in the "Notes" data field.).
CPUC Permit Status | 48 | 42a | CEQA Lead Agency | Text String, separated by " ¦ " as necessary, or NA | CPUC | Examples include: CPUC, SWRCB, CSLC, NA etc. If more than two options are required, enter each, pipe-delimited.
CPUC Permit Status | 49 | 42b | NEPA Lead Agency | Text String, separated by " ¦ " as necessary, or NA | USFS | Examples include: USFS, NA etc. If more than two options are required, enter each, pipe-delimited.
CPUC Permit Status | 50 | 43 | CPUC Filing Type | Text String, or NA | PG&E AL 2355-E | NOC Advice Letter (AL), Application for 851, PTC, CPCN, or NA. If an AL, include the number. If an Application, include number.
CPUC Permit Status | 51 | 44 | CPUC Date Filed | Date, formatted YYYY-MM-DD, or NA | 2022-04-08 | The year filed at the CPUC or insert "Not yet filed" with the expected filing date.
CPUC Permit Status | 52 | 45 | CPUC Status | Select text from drop-down menu | Approved | Indicate "Approved", "Rejected", "To be Filed", "Filed and Under Review," "Other," or "NA" (If "Other" or "NA", include explanation in the "Notes" data field.).
CPUC Permit Status | 53 | 46 | CPUC Status: Year | Year, formatted YYYY, or NA | 2019 | Insert the year this CPUC Status was determined.
Project status | 54 | 47 | Project Status | Select text from drop-down menu | Construction (10%-25%) | See drop-down menu for options. Examples include: Planning, Engineering less than 50% complete, Engineering more than 50% complete, Permitting, Construction (include percentage of construction completed at the time this data spreadsheet is provided (i.e., less than 10%, 10%-25%, 25%-50%, 50%-75%, greater than 75%), Operational, On Hold, Canceled, or Abandoned (if On Hold, Canceled, or Abandoned, include explanation in the "Notes" data field.).
Project status | 55 | 48 | AACE Class | Select text from drop-down menu | 3 | The current Estimate Class in AACE International's Cost Estimate Classification System at the time this data spreadsheet is provided.
Project status | 56 | 49 | Construction Start Date | Date, formatted YYYY-MM-DD, or NA | 45809 | The date on which construction began or is expected to begin.
Project status | 57 | 50 | Original Planned In- Service Date | Date, formatted YYYY-MM-DD, or NA* | 45809 | What was the expected in-service date when the project was first approved by the CAISO? If not a CAISO-approved project, provide the expected in-service date when the project was approved internally by the Utility.
Project status | 58 | 51 | Current Projected or Actual In-Service Date | Date, formatted YYYY-MM-DD, followed by OAI indicator if applicable (or NA) | 2021-01-01 ¦ NA 2021-01-01 ¦ OAI | At the time the data was extracted from the Utility’s Database(s) as provided in Section 2.1.5 of the Transmission Project Review Process Description. Projects without identified in-service dates that are "Operative as Installed" should be identified as "OAI".
Project status | 59 | 52 | Reason for Change in In- Service Date | Select text from drop-down menu(s) | Customer Action | See drop-down menu for options. If the current projected or actual in-service date varies more than six months from the original in-service date, please select all reasons for this change. If more than two options are required, select "Multiple Options" in second column and provide remaining responses, pipe-delimited, in "Notes" data field.
Project status | 60 | 52 | Reason for Change in In-Service Date (2) | Select text from drop-down menu(s) | Customer Action | See drop-down menu for options. If the current projected or actual in-service date varies more than six months from the original in-service date, please select all reasons for this change. If more than two options are required, select "Multiple Options" in second column and provide remaining responses, pipe-delimited, in "Notes" data field.
Project status | 61 | 53 | In-Flight Projects | Boolean: TRUE or FALSE | TRUE | For projects with costs expected to go into rate base in the current rate year or in the following rate year at FERC, please indicate with "TRUE." If there will be no additions to rate base in either year, indicate with "FALSE."
Costs | 62 | 54 | Original Projected Cost or Cost Range ($000) | Dollar value, or dollar value range, separated by " ¦ " | 2100 ¦ 2500 | Forecast cost or forecast cost range for Utility Unique ID #2, i.e., the totality of the project, at the earliest of CAISO, CPUC, or utility internal approval.
Costs | 63 | 55 | Cost Cap ($000) | Dollar value and Text String, separated by " ¦ ", or NA | 2500 ¦ CAISO TPP | Insert Cost Cap on project if available, as well as the authority imposing the cost cap. This shall include any maximum cost determined to be reasonable and prudent in a CPUC proceeding or a cost cap set for a competitively bid project in the CAISO's Transmission Planning Process.
Costs | 64 | 56 | Current Projected Total or Actual Final Cost ($000) | Dollar value | 78 | Updated projected fully-loaded total or actual fully loaded final cost of project. Projected total should be the anticipated sum of all capital expenditures, overhead,and AFUDC. Actual cost should be the total expenditures, overhead and AFUDC in the addition to rate base. Operational projects and all data must remain in this report for at least five (5) years after the last of the project's expenditures and capital additions.
Costs | 65 | 57 | 2019 Actual Capital Expenditures ($000) | Dollar value | 12 | Please include separate columns for each of the previous five (5) years and one for actual expenditures for the current year as of the date the data was extracted. If these expenditures do not include overheads and AFUDC, please provide those year-by-year.
Costs | 66 | 57 B | 2020 Actual Capital Expenditures ($000) | Dollar value | 12 | Please include separate columns for each of the previous five (5) years and one for actual expenditures for the current year as of the date the data was extracted. If these expenditures do not include overheads and AFUDC, please provide those year-by-year.
Costs | 67 | 57 C | 2021 Actual Capital Expenditures ($000) | Dollar value | 12 | Please include separate columns for each of the previous five (5) years and one for actual expenditures for the current year as of the date the data was extracted. If these expenditures do not include overheads and AFUDC, please provide those year-by-year.
Costs | 68 | 57 D | 2022 Actual Capital Expenditures ($000) | Dollar value | 12 | Please include separate columns for each of the previous five (5) years and one for actual expenditures for the current year as of the date the data was extracted. If these expenditures do not include overheads and AFUDC, please provide those year-by-year.
Costs | 69 | Internal | October 2023 YTD Actual Capital Expenditures ($000) | Dollar value | 12 | Please include separate columns for each of the previous five (5) years and one for actual expenditures for the current year as of the date the data was extracted. If these expenditures do not include overheads and AFUDC, please provide those year-by-year.
Costs | 70 | 58 | Nov & Dec 2023 Projected Capital Expenditures ($000) | Dollar value | 4650 | For the current year and four (4) future years, provide the year-by-year fully-loaded forecast capital expenditures for the project. Please include separate columns for each year. If these expenditures do not include overheads and AFUDC, please provide those year-by-year.
Costs | 71 | 58 B | 2024 Projected Capital Expenditures ($000) | Dollar value | 4650 | For the current year and four (4) future years, provide the year-by-year fully-loaded forecast capital expenditures for the project. Please include separate columns for each year. If these expenditures do not include overheads and AFUDC, please provide those year-by-year.
Costs | 72 | 58 C | 2025 Projected Capital Expenditures ($000) | Dollar value | 4650 | For the current year and four (4) future years, provide the year-by-year fully-loaded forecast capital expenditures for the project. Please include separate columns for each year. If these expenditures do not include overheads and AFUDC, please provide those year-by-year.
Costs | 73 | 58 D | 2026 Projected Capital Expenditures ($000) | Dollar value | 4650 | For the current year and four (4) future years, provide the year-by-year fully-loaded forecast capital expenditures for the project. Please include separate columns for each year. If these expenditures do not include overheads and AFUDC, please provide those year-by-year.
Costs | 74 | 58 E | 2027 Projected Capital Expenditures ($000) | Dollar value | 4650 | For the current year and four (4) future years, provide the year-by-year fully-loaded forecast capital expenditures for the project. Please include separate columns for each year. If these expenditures do not include overheads and AFUDC, please provide those year-by-year.
Costs | 75 | 58 F | 2028 Projected Capital Expenditures ($000) | Dollar value | 4650 | For the current year and four (4) future years, provide the year-by-year fully-loaded forecast capital expenditures for the project. Please include separate columns for each year. If these expenditures do not include overheads and AFUDC, please provide those year-by-year.
Costs | 76 | 59 | Construction Work in Progress Expenditures ($000) | Dollar value | 2350 | Total amount of money that has been spent so far for the project through the last calendar year.
Costs | 77 | 60 | Accrued Overhead | Dollar value | 12 | If the capital expenditures provided in Data Field #57 do not include Overhead, please provide the accrued Overhead through the last calendar year.
Costs | 78 | 61 | Accrued AFUDC | Dollar value | 0 | If the capital expenditures provided in Data Field #57 do not include AFUDC, please provide the accrued AFUDC through the last calendar year.
Costs | 79 | 62 | FERC: Year(s) | Years, separated by " ¦ ", or NA | 2023 ¦ 2024 ¦ 2025 ¦ 2026 ¦ 2027 | Insert ALL rate years when any costs of this project went - or are forecast to go - into FERC jurisdictional transmission rate base.
Costs | 80 | 63 | 2020 Actual FERC Dollars Ratebased ($000) | Dollar Value, per year column e.g., FERC_dollars_in_rate_base_2022 | 500000 | Insert the year(s) and actual dollars added to FERC jursidictional transmission rate base on the project for each of the four prior years and the present year. This should include additional costs added to rate base in years after operation first occurred.
Costs | 81 | 63 B | 2021 Actual FERC Dollars Ratebased ($000) | Dollar Value, per year column e.g., FERC_dollars_in_rate_base_2023 | 500000 | Insert the year(s) and actual dollars added to FERC jursidictional transmission rate base on the project for each of the four prior years and the present year. This should include additional costs added to rate base in years after operation first occurred.
Costs | 82 | 63 C | 2022 Actual FERC Dollars Ratebased ($000) | Dollar Value, per year column e.g., FERC_dollars_in_rate_base_2024 | 500000 | Insert the year(s) and actual dollars added to FERC jursidictional transmission rate base on the project for each of the four prior years and the present year. This should include additional costs added to rate base in years after operation first occurred.
Costs | 83 | 63 D | October 2023 YTD Actual FERC Dollars Ratebased ($000) | Dollar Value, per year column e.g., FERC_dollars_in_rate_base_2025 | 500000 | Insert the year(s) and actual dollars added to FERC jursidictional transmission rate base on the project for each of the four prior years and the present year. This should include additional costs added to rate base in years after operation first occurred.
Costs | 84 | 63 E | Nov & Dec 2023 Projected FERC Dollars Ratebased ($000) | Dollar Value, per year column e.g., FERC_dollars_in_rate_base_2026 | 500000 | Insert the year(s) and actual dollars added to FERC jursidictional transmission rate base on the project for each of the four prior years and the present year. This should include additional costs added to rate base in years after operation first occurred.
Costs | 85 | 63 F | 2024 Projected FERC Dollars Ratebased ($000) | Dollar Value, per year column e.g., FERC_dollars_in_rate_base_2027 | 500000 | Insert the year(s) and actual dollars added to FERC jursidictional transmission rate base on the project for each of the four prior years and the present year. This should include additional costs added to rate base in years after operation first occurred.
Costs | 86 | 64 | Percentage of Bid | Percentage to two decimals, and Text String, separated by " ¦ " | 33.33% ¦ "SuperPower LLC is developing a third of the project as part of its "TransValley Electrification" project. See http://.... | Percentage (or actual cost) of project implemented by outside developer, as opposed to the incumbent utility. If there is a project being developed by a non-incumbent utility that relates to this project, please indicate the name of the project as approved in the CAISO TPP.
Costs | 87 | 65 | Percentage of Work Requested by Others Passed onto Ratepayers | Percentage to two decimals and/or dollar value. If both, separate by " ¦ ". If either is not provided, please enter NA. | 25.00% ¦ 2300 35% ¦ NA NA ¦ 50000 | If the project is work requested by others or customer-driven, what percentage of the projects costs has been - or is expected to be - passed onto ratepayers? If the dollar amount being passed onto ratepayers is fixed, then this number can be expressed as a dollar amount.
Costs | 88 | 66 | Cost-Benefit Analysis | Percentage to two decimals, and ranking system identifier, separated by " ¦ " | 25.00% ¦ EnergyRank | The Cost-to-Benefit ratio. If the Utility's Cost-Benefit analysis related to its Risk-Based Decision-Making Framework (RDF) has not already been included in the "Utility Prioritization Ranking" data field above, please include it here.
Costs | 89 | 67 | FERC Incentives | Test Strings, separated by " ¦ ", or NA | Abandoned Plant ¦ CWIP | List any project-specific transmission incentives granted under any FERC Orders.
Costs | 90 | 68 | Percentage of Cost in High Voltage TAC | Percentage to two decimals | 0.2305 | Insert % of project cost recovered in the high-voltage TAC.
Costs | 91 | 69 | Percentage of Cost in Low Voltage TAC | Percentage to two decimals | 0 | Insert % of project cost recovered in the low-voltage TAC.
Notes | 92 | 70 | Notes | Strings, inclusive of field identifiers in brackets, separated by 3 linebreaks ("\n\n\n"), or NA [ID1] String1 [ID2] String2 | [CEQA/NEPA Document Type] Form STD762 [CPUC Status] Approved in part following bifurcation. Details indeterminate as of 5/6/2024. Expected update and clarification by 8/1/2024. | Any additionally requested information or other needed details about the project that were not otherwise covered.