## Project List
| Project Description | [32 empty] | Utility ¦CAISO Approval and FERC Rate Cases | [9 empty] | CPUC Permit Status | [9 empty] | Project Status | [7 empty] | Cost
1 | 2 | 3a | 3b | 4 | 5 | 6 | 7 | 7 | 8 | 9 | 10 | 11 | 11 | 12 | 13 | 14 | 15a | 15b | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 27b | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40a | 40b | 41a | 41b | 42a | 42b | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 52 | 53 | 54 | 55 | 56 | 57 | 57 | 57 | 57 | 57 | 57 | 58 | 58 | 58 | 58 | 58 | 59 | 60 | 61 | 62 | 63 | 63 | 63 | 63 | 63 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70
Row ¦Line No. | Project Name(s) | Latitude | Longitude | Location | Project Description | Project Description - What | Project Description - Action Taken | Project Description - Action Taken (2) | Project Dependencies | Primary Purpose | Secondary Purpose | NERC/WECC/CAISO Standard/Requirement/Contingency | NERC/WECC/CAISO Standard/Requirement/Contingency (2) | Last Inspection | Age of Asset | Types of Analyses | Alternative Solutions and Costs - Solutions | Alternative Solutions and Costs - Costs | CPUC Fire Threat Zone/Rating | Wildfire Related | RAMP | Other Environmental Factors | Project Manager | Transmission Project Size (length in miles) | Substation Project Footprint (acres) | Transmission Voltage Level (kV) | Substation or Transformer Capacity (MVA and/or kV) | Utility Prioritization Ranking | Utility Unique ID #1(Most Specific) | Utility Unique ID #2 (Less Specific) | Total Number of Projects under Parent Work Order | Utility Unique ID #3 (Least Specific) | Changes in Unique IDs | Utility Approval | Year of Internal Utility Approval | Process(es) for Utility Approval | Long term Transmission Investment Plan Inclusion | CAISO Year | TPP Phase 3 | Year(s) when considered in CAISO TPP | Year when expected to be considered in CAISO TPP | Link to TPP where project has been considered, approved, and/or expected to be considered | GIDAP-Related | CEQA Status | CEQA Status - Date | CEQA Document Type | NEPA Document Type | CEQA Lead Agency | NEPA Lead Agency | CPUC Filing Type | CPUC Date Filed | CPUC Status | CPUC Status - Year | Project Status | AACE Class | Construction Start Date | Original Planned In-Service Date | Current Projected or Actual In-Service Date | Reason for Change in In-Service Date | Reason for Change in In-Service Date (2) | In-Flight Projects | Original Projected Cost or Cost Range ($000) | Cost Cap ($000) | Current Projected Total or Actual Final Cost ($000) | Actual Capital Expenditures 2020 ($000) | Actual Capital Expenditures 2021 ($000) | Actual Capital Expenditures 2022 ($000) | Actual Capital Expenditures 2023 ($000) | Actual Capital Expenditures 2024 ($000) | Projected Capital Expenditures 2024 ($000) | Projected Capital Expenditures 2025 ($000) | Projected Capital Expenditures 2026 ($000) | Projected Capital Expenditures 2027 ($000) | Projected Capital Expenditures 2028 ($000) | Projected Capital Expenditures 2029 ($000) | Construction Work in Progress ($000) | Accrued Overhead ($000) | Accrued AFUDC ($000) | FERC: Year(s) | 2020 Actual FERC Dollars Ratebased ($000) | 2021 Actual FERC Dollars Ratebased ($000) | 2022 Actual FERC Dollars Ratebased ($000) | 2023 Actual FERC Dollars Ratebased ($000) | 2024 Actual FERC Dollars Ratebased ($000) | 2025 Projected FERC Dollars Ratebased ($000) | Percentage of Bid | Percentage and Value ($000) of Work Requested by Others Passed onto Ratepayers | Cost-Benefit Analysis | FERC Incentives | Percentage of Cost in High Voltage TAC | Percentage of Cost in Low Voltage TAC | Notes
1 | [Programmatic] Transmission Substation Responsive Asset Replacement |  |  | NA | This budget is set based on historical averages and is financially authorized on an annual basis. This annual authorization requires a new funding request at the beginning of the year, which must be internally approved in order to be included within the Five-year Plan. The budget is then adjusted throughout the year to address safety and failure related issues. This budget is required to maintain the reliability and integrity of Transmission substations. The specific work required to meet safety requirements, replace obsolete or failed equipment, and make necessary small capital additions is based on requests from Engineering, Planning, Operations, and Maintenance groups. | Substation - Multiple | Replace | Upgrade/Retrofit | NA | Reliability | Substation Reliability | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | Multiple | NA | 4.1 | Multiple | QB00012 | 125 | 103 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-11-17 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Operational | NA | NA | 2024-12-31 | NA | NA | NA | TRUE | NA | NA ¦ NA | 0 | 1538.2149 | 1006.8256 | 463.7028 | 2041.3528 | 1810.8875 | 1050.8362 | 4689.1843 | 5085.6812 | 6284.0684 | 7712.1454 | 9031.3834 | 0 | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 2438.3022 | 1754.0005 | 472.0742 | 1265.2904 | 1217.0102 | 2620.3429 | 0% | NA ¦ NA | 6.1 | NA | 13.55% | 86.45% | [Types of Analyses] Responsive budget due to reactive work at substation; projects are under Programmatic budget; [Age of Asset] Unable to provide age of asset for Programmatic budget codes [CPUC Fire Threat] - Depends on the substation, can be 1, 2 or 3.
2 | A IID, SRP, APS SDGE SHARE ON CAP |  |  | NA | Capital upgrades between Arizona Public Services, Salt River Project and IID | Substation - Other Equipment | Upgrade/Retrofit | NA | NA | Work Requested by Others | Substation Reliability | NA | NA | 2024-01-13 12:00 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | NA | NA | 4.1 | NA | QB00012 | 1 | 103 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2021-12-27 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | 2022-12-28 | 2022-12-31 | NA | Other [See Notes] | NA | TRUE | NA | NA ¦ NA | 11695.2798 | 0 | 0 | 12271.1182 | -586.1013 | 10.2628 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2022 ¦ 2023 ¦ 2024 | 0 | 0 | 12271.1182 | -586.1013 | 10.2628 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [Reason for Change in In-Service Date] SDGE does not manage the construction of these projects and that it up to the APS and IID to manage the construction that would be great, other wise I would say customer action
3 | A KYOCERA BK 30 REPLACEMENT |  |  | San Diego | Replace Bk30 at Kyocera Substation | Substation - Transformer | Replace | Upgrade/Retrofit | NA | Reliability | Substation Reliability | NA | NA | 2024-09-25 | 6 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 0.17 | 69 | 69 kV | 4.1 | 2019-1024 | QB00012 | 1 | 103 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-09-25 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Construction (50%-75%) | NA | 2023-06-12 | 2020-12-31 | 2025-01-01 | NA | NA | TRUE | NA | NA ¦ NA | 2136.0726 | 537.4027 | 188.5972 | 184.1777 | 958.5305 | 240.9498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2023 ¦ 2024 | 0 | 0 | 0 | 1895.1228 | 240.9498 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
4 | A IID, SRP, APS SDGE SHARE ON CAP |  |  | NA | Capital upgrades between Arizona Public Services, Salt River Project and IID | Substation - Other Equipment | Upgrade/Retrofit | NA | NA | Work Requested by Others | Substation Reliability | NA | NA | 2024-01-13 12:00 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | NA | NA | 4.1 | NA | QB00012 | 1 | 103 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-04-03 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | 2020-04-03 | 2020-12-31 | NA | Other [See Notes] | NA | FALSE | NA | NA ¦ NA | 2577.8396 | 1539.6221 | 1037.2104 | 1.0071 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2020 ¦ 2021 ¦ 2022 | 1539.6221 | 1037.2104 | 1.0071 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [Reason for Change in In-Service Date] SDGE does not manage the construction of these projects and that it up to the APS and IID to manage the construction that would be great, other wise I would say customer action
5 | A APS SDGE PORTION APS 2016 2017 |  |  | NA | Capital upgrades between Arizona Public Services, Salt River Project and IID | Substation - Other Equipment | Upgrade/Retrofit | Replace | NA | Work Requested by Others | Replace Other Substation Equipment | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | NA | NA | 4.1 | NA | QB00012 | 1 | 103 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2016-10-17 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | 2016-10-31 | 2017-12-30 | NA | NA | NA | FALSE | NA | NA ¦ NA | 8619.1112 | 1126.0044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2020 | 1126.0044 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0%
6 | A MIGUEL BK80 12KV TERTIARY BREAK |  |  | Unincorporated San Diego County | Replace (3) 12kv Tertiary breakers; install two SEL487 relay panels | Substation - Circuit Breaker | Replace | Upgrade/Retrofit | NA | Reliability | Substation Reliability | NA | NA | 2024-10-22 | 23; 23; 23 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 12.37 | 12 | 230 kV ¦ 69 kV ¦ 12 kV | 4.1 | 2019-1018 | QB00012 | 1 | 103 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-02-08 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | 2020-05-04 | 2019-12-31 | 2024-06-30 | NA | NA | TRUE | NA | NA ¦ NA | 1173.609 | 240.6139 | 135.6585 | 118.4374 | 288.7443 | 161.4683 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2023 ¦ 2024 | 0 | 0 | 0 | 1012.1408 | 161.4683 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
7 | X BAY BLVD BANK 70 REPLACEMENT |  |  | Chula Vista, San Diego | Remove and replace BK 70 AT Bay Boulevard | Substation - Transformer | Replace | Replace | NA | Reliability | Substation Reliability | NA | NA | 2024-10-28 | 10 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 10.21 | 230 | 230 kV | 4.1 | 2020-1008 | QB00012 | 1 | 103 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-04-01 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | 2020-07-21 | 2020-12-31 | 2021-06-01 | NA | NA | TRUE | NA | NA ¦ NA | 2037.6779 | 2515.8158 | -923.8237 | -430.4456 | -160.1004 | -620.9019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 ¦ 2024 | 4172.9494 | -923.8237 | -430.4456 | -160.1004 | -620.9019 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0%
8 | A BAY BLVD DRAINAGE IMPROVEMENTS |  |  | Chula Vista, San Diego | Site improvements at Bay Blvd | Other - Civil | Upgrade/Retrofit | Upgrade/Retrofit | NA | Location, Environmental Conditions | Construct Roads/Gates/Culverts | NA | NA | 2024-10-28 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 9.6 | 69 | 69 kV | 4.1 | NA | QB00012 | 1 | 103 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-05-02 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | 2019-05-07 | 2019-12-31 | NA | NA | NA | FALSE | NA | NA ¦ NA | 3026.7512 | 108.8305 | 1.2712 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2020 ¦ 2021 | 3025.48 | 1.2712 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [Age of Asset] Site development project. No Asset IDs
9 | [Programmatic] Renewal of Electric Transmission Line Easements |  |  | NA | Placeholder. The purpose of this parent work order is to renew various easements and/or permits for transmission rights of way that will expire within the next 5 years. These easements will allow SDGE to install and maintain electric transmission facilities across public and private lands. These transmission lines are an integral part of our electric transmission system. | Transmission Line - Right of Way | NA | NA | NA | Other [See Notes] | System Operations | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | Multiple | NA | NA | Multiple | QB00008 | 7 | 104 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-11-28 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Planning | NA | NA | 2024-12-31 | NA | NA | NA | TRUE | NA | NA ¦ NA | 0 | 61.774 | 30.7355 | 71.7872 | 16.0811 | 78.1787 | 1108.3247 | 769.7886 | 775.5418 | 781.5176 | 787.6747 | 790.7806 | 0 | NA | NA | 2020 ¦ 2021 ¦ 2024 ¦ 2025 | 559.1767 | 30.8162 | 0 | 0 | 165.8587 | 769.7886 | 0% | NA ¦ NA | 12.6 | NA | 13.55% | 86.45% | [Primary Purpose] Easement review
10 | A TL 682 LA JOLLA ET EASEMENT |  |  | NA | Renewal of TL 682 Transmission Easement | Transmission Line - Right of Way | NA | NA | NA | Other [See Notes] | Safety - Line Right of Way Access | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | NA | NA | NA | NA | QB00008 | 1 | 104 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2022-06-27 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | BIA | Exempt | NA | NA | NA | Permitting | NA | NA | 2023-12-31 | NA | NA | NA | FALSE | NA | NA ¦ NA | 1567.9434 | 0 | 0 | 440.5826 | 709.3057 | 390.8866 | 27.1686 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [Primary Purpose] Easement review [Age of Asset] Unable to provide age of asset for Programmatic budget codes
11 | [Programmatic] Electric Transmission Tools & Equipment |  |  | NA | Purchase tools and test equipment to support the safe and reliable operations of substation and transmission equipment. | Substation - Multiple | New | Replace | NA | Reliability | Substation Reliability | Other [See Notes] | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | Multiple | NA | 1.3 | Multiple | QB00145 | 2 | 106 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-11-22 | Work Order Authorization | 2019 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Operational | NA | NA | 2024-12-31 | NA | NA | NA | FALSE | NA | NA ¦ NA | 0 | 0 | 0 | 0 | 0 | 1e-07 | 36.594 | 132.5303 | 147.3818 | 162.254 | 178.4901 | 196.2153 | 0 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | 3 | NA | 13.55% | 86.45% | [Project Description - Action Taken] Easements are required to protect the placement, access to, and maintenance of SDG&E facilities. [NERC / WECC / CAISO Standard / Requirement / Contingency] In order to comply with CAISO standards, appropriate tools are required to test the operational function of our substation and transmission equipment and facilities.
12 | A BLANKET ELEC TRANS TOOLS & R6 |  |  | NA | Purchase tools and test equipment to support the safe and reliable operations of substation and transmission equipment. | Substation - Multiple | New | Replace | NA | Reliability | Substation Reliability | Other [See Notes] | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | NA | NA | 1.3 | NA | QB00145 | 1 | 106 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-02-01 | Work Order Authorization | 2019 | NA | FALSE | NA | NA | NA | FALSE | TBD | NA | NA | NA | CPUC | NA | NA | NA | NA | NA | Operational | NA | NA | 2019-12-31 | NA | NA | NA | TRUE | NA | NA ¦ NA | 543.4393 | 82.7465 | 86.2931 | 83.1998 | 93.5771 | 59.5741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 ¦ 2024 | 82.7465 | 86.2931 | 83.1998 | 93.5771 | 59.5741 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [Project Description - Action Taken] Easements are required to protect the placement, access to, and maintenance of SDG&E facilities. [NERC / WECC / CAISO Standard / Requirement / Contingency] In order to comply with CAISO standards, appropriate tools are required to test the operational function of our substation and transmission equipment and facilities.
13 | [Programmatic] Electric Distribution Tools & Equipment |  |  | NA | This blanket budget provides funding for new tools and equipment required by field personnel to inspect, operate and maintain the electric distribution system. | Other | New | NA | NA | Safety | Automation | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | Multiple | NA | 1 | Multiple | QB00028 | 12 | 206 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-11-16 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Operational | NA | NA | 2024-12-31 | NA | NA | NA | TRUE | NA | NA ¦ NA | 0 | 32.7315 | 0.50352 | 0 | 0 | -0.0052359 | 43.8455 | 19.948 | 361.3043 | 373.9391 | 387.0335 | 400.5785 | 0 | NA | NA | 2020 ¦ 2021 ¦ 2024 ¦ 2025 | 25.1583 | 40.0083 | 0 | 0 | -0.0052359 | 46.0891 | 0% | NA ¦ NA | 2.3 | NA | 0% | 100% | [CPUC Fire Threat Zone/Rating] it is not a physical project and therefore does not have an HFTD location.
14 | A INTERIM CAPITAL TOOLS C&O |  |  | NA | Provides the necessary tools and equipment to economically and safely inspect, operate and maintain the electric distribution facilities. Failure to replace outdated, old or worn-out tools will result in decreased crew productivity, increase accident frequency and increase system failure. | Other | Upgrade/Retrofit | Multiple Options [See Notes] | NA | Safety | Tools, Transformer Addition/Replacement | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | NA | NA | 1 | NA | QB00028 | 1 | 206 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-11-16 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Operational | NA | NA | 2024-12-31 | NA | NA | NA | TRUE | NA | NA ¦ NA | 3260.3585 | 408.1143 | 547.5016 | 196.3277 | 171.4613 | 188.8157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 ¦ 2024 | 408.1143 | 547.5016 | 196.3277 | 171.4613 | 188.8157 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [Wildfire Related] is related to wildfire in some other way. Provides the necessary tools and equipment as needed. [Project Description - What] Other, provides funding for new tools and equipment required by field personnel to inspect, operate and maintain the electric distribution system. [Project Description - Action Taken (2)] The main purpose of the project is to improve safety so multiple options are taken. [CPUC Fire Threat Zone/Rating] it is not a physical project and therefore does not have an HFTD location.
15 | [Programmatic] IT Enterprise Network Operation Support |  |  | Multiple | IT Enterprise Network Operation Support | Other - IT | New | Multiple Options [See Notes] | NA | Other [See Notes] | System Operations | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | NA | NA | NA | Multiple | Multiple | 50 | 925 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-11-10 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Operational | NA | NA | 2024-12-31 | NA | NA | NA | TRUE | NA | NA ¦ NA | 0 | 274.7546 | 862 | 1337.7996 | 1288.9571 | 1801.0563 | 0 | 2389.7896 | 2750.4818 | 0 | 0 | 0 | 0 | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 ¦ 2024 | 274.7546 | 667.7656 | 1473.5764 | 1087.5038 | 2037.4371 | 0 | 0 | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [Age of Asset] IT Projects no asset [Project Description - Action Taken (2)] new replace, upgrade/retrofit [Primary Purpose] multiple choices - Age/end of life and reliability
16 | Data Center Network Core Implementation |  |  | Multiple | Replacing End of Support Data Centers | Other - IT | Replace | Upgrade/Retrofit | NA | Age/End of Life | Age/Condition | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | NA | NA | NA | T000021 | P000021 | 1 | 925 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-10-13 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Engineering more than 50% complete | NA | 2020-9-30 | 2021-07-31 | 2023-02-07 for 3441272 & 2024-6-30 for 3591996 | NA | NA | TRUE | NA | NA ¦ NA | 0 | 1251.8799 | 1179.2323 | 581.6243 | 415.6746 | 206.5122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2023 ¦ 2024 | 0 | 0 | 0 | 957.3909 | 2677.5323 | 0 | 0 | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [Age of Asset] IT Projects no asest
17 | SDGE LAN Refresh |  |  | Multiple | Replacing End of Support SDGE IT Network Hardware | Other - IT | Replace | NA | NA | Age/End of Life | Age/Condition | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | NA | NA | NA | T19005 | PT19005 | 1 | 925 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-03-19 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Operational | NA | 2019-3-15 | 2019-12-31 | 2022-12-31 | NA | NA | FALSE | NA | NA ¦ NA | 0 | 1804.9318 | 661.6256 | 91.0149 | 7.454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 | 0 | 3146.6129 | 91.0149 | 7.454 | 0 | 0 | 0 | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [Age of Asset] IT Projects no asset
18 | SDGE WAN and PNER Network Refresh |  |  | Multiple | Replacing End of Support SDGE IT Network Hardware, Retrofit Communications Towers | Other - IT | Replace | Upgrade/Retrofit | NA | Age/End of Life | System Operations | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | NA | NA | NA | T19027 | PT19027 | 1 | 925 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-11-10 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Operational | NA | 2019-7-28 | 2019-12-31 | 2022-12-31 | NA | NA | TRUE | NA | NA ¦ NA | 0 | 701.0483 | 634.0038 | 580.1764 | 21.156 | -0.00028957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2022 ¦ 2023 ¦ 2024 | 0 | 0 | 2395.1787 | 21.156 | -0.00028957 | 0 | 0 | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [Age of Asset] IT Projects no asset
19 | SDGE FAN VOICE RADIO & DISPATCH PROJECT |  |  | Multiple | Upgrade voice radio system. | Other - Operations Tech | Replace | Removal | NA | Age/End of Life | Automation | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | NA | NA | NA | T17027 | PT17027 | 1 | 925 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-11-10 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Operational | NA | 2017-11-15 | 2019-12-10 | Various | NA | NA | FALSE | NA | NA ¦ NA | 0 | 768.6367 | -0.11699 | 35.4657 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2020 ¦ 2021 ¦ 2022 | 2239.3083 | -0.11699 | 35.4657 | 0 | 0 | 0 | 0 | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [Age of Asset] IT Projects no asest
20 | Distributed Communications Reliability Initiative |  |  | Multiple | Install a Private LTE network to serve HFTD 2 and 3 | Other - Operations Tech | New | Upgrade/Retrofit | NA | Reliability | System Operations | NA | NA | NA | NA | NA | NA | NA | HFTD Tier 2 ¦ HFTD Tier 3 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | NA | NA | NA | T18018 | PT18018 | 1 | 925 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2018-09-06 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Operational | NA | 2018-9-27 | 2020-10-31 | Various | NA | NA | FALSE | NA | NA ¦ NA | 0 | 151.8158 | 99.2211 | 4.0466 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 | 0 | 1291.7932 | 4.0466 | 0 | 0 | 0 | 0 | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [Age of Asset] IT Projects no asset [Project Description - What] Reliability and Wildfire Mitigation
21 | 2026 SDGE Network Refresh |  |  | Multiple | Replacing End of Support SDGE IT Network Hardware | Other - IT | Replace | NA | NA | Age/End of Life | Age/Condition | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | NA | NA | NA | BD23021 | NA | 1 | 925 | NA ¦ NA ¦ NA ¦ NA | TRUE | NA | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Planning | NA | 2026-1-15 | NA | 2026-12-31 | NA | NA | FALSE | NA | NA ¦ NA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1182.0804 | 0 | 0 | 0 | 0 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [Age of Asset] IT Projects no asest
22 | [Programmatic] Transmission Substation Proactive Asset Program |  |  | NA | The Substation Equipment Assessment Team will develop alternatives to replace or remove obsolete and problematic equipment. A condition assessment process and evaluation criteria have been created using probability and risk analysis, financial impacts and present value analysis to justify projects. Equipment that is truly obsolete such as equipment that cannot be maintained (no spare parts available), or which poses a safety risk will be replaced. Each year the average age of all substation equipment increases, with the oldest transformer currently 60+ years old. The ranking of substation equipment is an ongoing process and involves identifying equipment that presents a significant risk to the system. Based on the cost availability of raw materials and global demand, the lead times for major substation equipment have increased to 6 months for breakers and at least 1.5 years for transformers. | Substation - Multiple | Replace | Upgrade/Retrofit | NA | Reliability | Substation Reliability | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | Multiple | NA | 4.1 | Multiple | QBL0003 | 246 | 1145 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-11-17 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Planning | NA | NA | 2024-12-31 | NA | NA | NA | TRUE | NA | NA ¦ NA | 0 | 3784.9412 | 1799.6581 | 3125.1507 | 2483.8538 | 2446.935 | -711.3385 | 7161.9357 | 8239.8735 | 8925.0491 | 10207.9987 | 11152.3009 | 10716.447 | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 6994.7741 | 1450.7638 | 3832.8418 | 3061.5392 | 3009.515 | -473.9838 | 0% | NA ¦ NA | 31.6 | NA | 13.55% | 86.45%
23 | A MIGUEL FIRE PROTECTION SYS REPR |  |  | Unincorporated San Diego County | Repair of Fire protection system at Miguel | Other - Civil | Upgrade/Retrofit | Upgrade/Retrofit | NA | Safety | Fire Protection | NA | NA | 2024-10-22 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 2.9 | 69 ¦500 | NA | 4.1 | NA | QBL0003 | 1 | 1145 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-10-01 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | 2019-10-03 | 2020-12-31 | 2021-05-18 | NA | NA | FALSE | NA | NA ¦ NA | 1746.3209 | 981.5308 | 759.4003 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 | 0 | 1746.3209 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 13.55% | 86.45% | [Age of Asset] Site development project. No Asset IDs
24 | A GLENCLIFF SUB ADD 69KV BREAKER |  |  | San Diego County | Install 69kv Bank Breaker and SCADA | Substation - Circuit Breaker | New | New | NA | Reliability | Substation Reliability | NA | NA | 2024-09-18 | 6 | NA | NA | NA | HFTD Tier 3 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 0.15 | 69 | 69 kV | 4.1 | 2014-01091-ZZ | QBL0003 | 1 | 1145 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2018-03-04 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | 2020-07-27 | 2019-03-01 | 2022-06-30 | NA | NA | TRUE | NA | NA ¦ NA | 2025.8242 | 1585.3071 | 280.8401 | 72.345 | 0 | 0.99921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2022 ¦ 2024 | 0 | 0 | 2024.825 | 0 | 0.99921 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
25 | G MERCHANT REPLACE 3 230KV BRKR |  |  | Nevada | Replace (3) Oil circuit breakers due to leaking hydraulic fluid | Substation - Circuit Breaker | Replace | Upgrade/Retrofit | NA | Safety | Substation Reliability | NA | NA | 2024-07-15 | 27; 27; 27 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 72.12 | 230 | NA | 4.1 | 2020-1020 | QBL0003 | 1 | 1145 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-06-07 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Construction (over 75%) | NA | 2022-03-31 | 2020-11-30 | 2025-05-23 | NA | NA | TRUE | NA | NA ¦ NA | 6036.3637 | 559.0598 | 750.5718 | 1271.3793 | 2355.3583 | 1099.4466 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2024 | 0 | 0 | 0 | 0 | 6036.3637 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0%
26 | A PENAQUITOS SUBST 230KV DISCON R |  |  | San Diego, San Diego | Replace (8) 230kv disconnect switches, (8) 230kv disconnect stands, and upgrade the associated concrete pads | Substation - Switch | Replace | Upgrade/Retrofit | NA | Reliability | Substation Reliability | NA | NA | 2024-10-09 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 13.94 | 230 | 230 kV | 4.1 | 2019-1022 | QBL0003 | 1 | 1145 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-06-20 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | 2020-04-13 | 2020-07-06 | 2022-01-31 | Multiple Options [See Notes] | NA | FALSE | NA | NA ¦ NA | 2597.4832 | 1200.2864 | 1102.6513 | 3.3797 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 | 0 | 2594.1036 | 3.3797 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0% | [Age of Asset] DISCONNECTS NO ASSET ID [Reason for Change in In-Service Date] In-service dates are estimated during preliminary design and permitting stages of a project; date shifted to reflect actual design and construction schedule.
27 | 5983087 - A KEARNY 69/12KV SUBSTATION DEMO |  |  | San Diego | Remove all equipment associated with Kearny Substation | Other | Removal | Removal | NA | Age/End of Life | Compliance - Remove Idle Facilities | NA | NA | 2024-09-12 | NA | NA | Wires - New Substation Alternative | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69 | 69 kV | 4.1 | NA | QBL0003 | 1 | 1145 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-11-17 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | 2019-06-08 | 2019-12-30 | NA | NA | NA | FALSE | NA | NA ¦ NA | 647.6039 | 81.3208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2020 | 647.6039 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [Project Description - What] The description of this project is demolish the existing equipment at the substation [Age of Asset]Demolition of substation structures (i.e. steel and foundations). No asset IDs.
28 | A MIGUEL 500 BATTERY BANK 12KV SH |  |  | Unincorporated San Diego County | Remove existing 500 station battery banks 1 &2, install new EC-17M, 670AH Batteries with 150ADC chargers, remove existing 12kv reactor bank 1,2 &3, install new reactor bank 1,2 &3 | Substation - Other Equipment | Replace | Upgrade/Retrofit | NA | Safety | Age/Condition - Replace Other Substation Equipment | NA | NA | 2024-10-22 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 2.9 | 500 | 500KV | 4.1 | 2019-1018 | QBL0003 | 1 | 1145 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-12-10 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | 2020-05-04 | 2020-12-31 | 2023-11-14 | NA | NA | TRUE | NA | NA ¦ NA | 2775.8688 | 1270.7679 | 201.1086 | 111.4663 | 1046.7919 | 142.9033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2024 | 0 | 0 | 0 | 0 | 2775.8688 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0% | [Age of Asset] BATTERY BANK NO ASSET ID
29 | A SCRIPPS SUBST RPL 69KV BUS DISC |  |  | San Diego, San Diego | Replace 69KV bus disconnects for BK 30,31 & 32, existing disconnects are breaking down and limited spare parts since these were manuf.; use (3) spare EVB ( 69kv,1200A) switches from Caspian for this work | Substation - Bus Arrangement | Replace | Replace | NA | Age/End of Life | Age/Condition | NA | NA | 2024-10-03 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 1.1 | 69 | 69 kV | 4.1 | 2020-1038 | QBL0003 | 1 | 1145 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-07-24 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | 2022-01-10 | 2020-12-31 | 2023-05-08 | NA | NA | TRUE | NA | NA ¦ NA | 1783.4936 | 3.3037 | 323.5922 | 1079.982 | 376.5437 | 0.07194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2023 ¦ 2024 | 0 | 0 | 0 | 1783.4216 | 0.07194 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [Age of Asset] DISCONNECTS NO ASSEST ID
30 | A MELROSE VISTA ENERGY STORAGE |  |  | Vista, San Diego | This work order is for the preliminary engineering required to expand ME substation to create an interconnection for the Vista Energy Storage 69kV TL | Substation - Structure | NA | NA | NA | Generator Interconnection | Generation Interconnection | NA | NA | 2024-10-16 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 1.13 | 69 | 69 kV | 4.1 | 2014-00582-ZZ | QBL0003 | 1 | 1145 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2017-04-24 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | 2017-09-18 | 2018-12-01 | 2018-07-04 | NA | NA | FALSE | NA | NA ¦ NA | 4692.7356 | -46.903 | 40.308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2020 ¦ 2021 | 4652.4276 | 40.308 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [Age of Asset] TL position added. No assets replaced.
31 | A MURRAY RPL RELAY ON TL 618,619, |  |  | San Diego, San Diego | Remove existing control shelter and panels (100,101,102,103,104,105,201,202,203,204,205,206, RTU & CBM cabinets, AC/DC panels; install new control shelter and panels (100,101,102,103,104,108,109,200,201,202,203,204,207, new CBM & Telecom cabinets, new AC/DC panels) | Substation - Multiple | Removal | New | NA | Reliability | Age/Condition - Replace Other Substation Equipment | NA | NA | 2024-09-06 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 9 | 69 | 69 kV | 4.1 | 2014-00247-ZZ | QBL0003 | 1 | 1145 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2017-04-24 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | 2017-07-25 | 2019-12-31 | 2021-04-21 | NA | NA | FALSE | NA | NA ¦ NA | 3532.7589 | 690.455 | 191.4279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 | 0 | 3532.7589 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [Age of Asset] RELAY NO ASSET ID
32 | A MIRAMAR SUBST RPL 12KV BRKERS |  |  | San Diego | Replace (16) 12kv obsolete breakers and relays at Miramar Substation as part of FLSR PROJECT | Substation - Circuit Breaker | Replace | Upgrade/Retrofit | NA | Reliability | Substation Reliability | NA | NA | 2024-10-02 | 58; 36; 36; 36 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 0.76 | 69 | 69kV | 4.1 | 2014-01096-ZZ | QBL0003 | 1 | 1145 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2017-12-12 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | 2019-02-20 | 2018-12-01 | NA | NA | NA | FALSE | NA | NA ¦ NA | 2200.9086 | 65.5911 | 0 | 0 | 0.14587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2020 ¦ 2023 | 2200.7627 | 0 | 0 | 0.14587 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
33 | A IMPERIAL VALLEY MAST RPL |  |  | Imperial County | Replacement of Static Mast structures at Imperial Valley | Substation - Structure | Replace | Replace | NA | Age/End of Life | Age/Condition | NA | NA | 2024-10-30 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 55.48 | 500 | 500 kV | 4.1 | 2020-1025 | QBL0003 | 1 | 1145 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-04-29 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | 2021-01-25 | 2019-12-31 | 2024-02-02 | NA | NA | TRUE | NA | NA ¦ NA | 1281.6462 | -21.7421 | 225.8838 | 220.1826 | 281.4983 | 31.0638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2024 | 0 | 0 | 0 | 0 | 1281.6462 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0% | [Age of Asset] Static Mast replacement. No Asset IDs.
34 | A MELROSE SUBST SITE DEV IMPROV |  |  | Vista, San Diego | Site improvements at Melrose | Other - Civil | Upgrade/Retrofit | Upgrade/Retrofit | NA | Other [See Notes] | Construct Roads/Gates/Culverts | NA | NA | 2024-10-16 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 1.2 | NA | NA | 4.1 | NA | QBL0003 | 1 | 1145 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-12-10 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | 2019-05-15 | 2019-12-31 | NA | NA | NA | FALSE | NA | NA ¦ NA | 1097.4383 | 124.9518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2020 | 1097.4384 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [Primary Purpose] This is a site development project. [Age of Asset] Site development project. No Asset IDs [Current Projected or Actual In-Service Date] No date, it is a construction project. No asset.
35 | A PENASQUITOS AGING INFRS. 138K B |  |  | San Diego, San Diego | Replace (5)138kV Breakers | Substation - Circuit Breaker | Replace | Upgrade/Retrofit | NA | Reliability | Age/Condition - Replace Breakers | NA | NA | 2024-10-09 | 61; 58; 45; 45 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 13.94 | 138 | 138 kV | 4.1 | 2021-2457 | QBL0003 | 1 | 1145 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-05-08 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | On Hold | NA | 2025-09-05 | 2020-12-31 | 2027-07-07 | NA | NA | FALSE | NA | NA ¦ NA | 2245.0819 | 37.1837 | 48.2835 | 509.533 | 469.8479 | 417.0845 | 41.8469 | 176.8769 | 136.31 | 0 | 0 | 0 | 1890.048 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
36 | A SAN YSIDRO AGING INFRAS. 69KV B |  |  | San Diego, San Diego | Replace (3) 69kV circuit breakers at San Ysidro | Substation - Circuit Breaker | Replace | Upgrade/Retrofit | NA | Reliability | Age/Condition - Replace Breakers | NA | NA | 2024-10-25 | 52; 52; 32 | NA | NA | NA | HFTD Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 1.57 | 69 | 69 kV ¦ 12 kV | 4.1 | 2020-1030 | QBL0003 | 1 | 1145 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-05-08 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | 2021-08-02 | 2020-12-31 | 2023-03-14 | NA | NA | TRUE | NA | NA ¦ NA | 2156.2311 | 229.567 | 475.4767 | 349.219 | 804.8363 | 122.8656 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2023 ¦ 2024 | 0 | 0 | 0 | 2033.3655 | 122.8656 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
37 | A TORREY PINES TL662 REPLACEMENT |  |  | San Diego, San Diego County | Replace 69kV CB4 and CB5 with new gas breakers Install (2) new 4 inch conduits for each breaker part of replacement Install new cables for each breaker part of replacement Install new zipper box for each breaker part of replacement Repair/install new ground leads for each breaker part of replacement Install (2) new 4 inch conduits to spare breaker pad | Substation - Circuit Breaker | Replace | Upgrade/Retrofit | NA | Reliability | Age/Condition - Replace Breakers | NA | NA | 2024-09-27 | 32;32 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | TBD |  | NA | 0.79 | 69KV | 12 kV ¦ 69KV | 4.1 | 2024-4121 | QBL0003 | 1 | 1145 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-10-10 | Work Order Authorization | 2024 | NA | FALSE | NA | NA | NA | FALSE | TBD | NA | NA | NA | CPUC | NA | NA | NA | NA [See Notes] | NA | Construction (under 10%) | NA | 2024-07-15 | 2025-01-31 | 2025-08-06 | NA | NA | TRUE | NA | NA ¦ NA | 2206.9547 | 0 | 0 | 0 | 6.1175 | 2143.8315 | 47.6837 | 9.322 | 0 | 0 | 0 | 0 | 2149.949 | NA | NA | 2025 | 0 | 0 | 0 | 0 | 0 | 2206.9547 | NA | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] - new project no construction date
38 | A FELECITAS AGING INFRAS. 69KV BR |  |  | Escondido, San Diego County | The purpose of this project is to upgrade the reliability of Felicita Substation by replacing equipment exceeding 47 years in service, adding a new high side bank circuit breaker, and upgrading the line, bank, and bus relay protection associated with the circuit breakers being installed. | Substation - Circuit Breaker | Upgrade/Retrofit | New | NA | Reliability | Age/Condition | NA | NA | 2024-10-04 | 52;49;40 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | TBD |  | NA | 1.51 | 69KV | 69KV | 4.1 | 2019-1021 | QBL0003 | 1 | 1145 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-05-08 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | TBD | NA | NA | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Engineering more than 50% complete | NA | 2025-03-06 | 2020-12-31 | 2025-08-28 | NA | NA | TRUE | NA | NA ¦ NA | 1781.5944 | 23.7489 | 36.1215 | 149.7262 | 428.3646 | 916.4659 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2024 | 0 | 0 | 0 | 0 | 1781.5944 | 0 | NA | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] NA
39 | Transmission System Automation |  |  | NA | To enhance transmission system reliability, capital projects are required to 1) install new transmission SCADA systems and 2) replace/upgrade existing transmission SCADA systems to provide control and monitoring capability for grid operations. In addition, there is a requirement to install systems to provide monitoring of certain critical substation apparatus to provide data for enhanced scheduling of maintenance. There are also new security requirements based upon NERC guidelines and the SEMPRA Control System security policy, which mandate the need to install equipment to control access to equipment installed in substations. The budget also allows us to enable remote event retrieval in non-Medium Impact substations to significantly reduce the time it takes to obtain event records and situational awareness during system disturbances. | Substation - Multiple | Upgrade/Retrofit | NA | NA | Reliability | Relay Upgrades | NERC CIP Compliance | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69 ¦ 500 | 373MVA | 2 | Multiple | QBL0001 | 66 | 3171 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-11-22 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | NA | 2024-12-31 | NA | NA | NA | TRUE | NA | NA ¦ NA | 0 | 369.2806 | 1813.0371 | 1652.3139 | 1882.5746 | 546.0724 | 210.9949 | 1958.0701 | 3123.1158 | 3516.3175 | 3914.29 | 3237.5208 | 2803.5023 | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 89.2931 | 265.5254 | 2153.7936 | 2797.504 | 319.451 | 2033.4564 | 0% | NA ¦ NA | 15.4 | NA | 13.55% | 86.45% | [Types of Analyses] Information security
40 | A CEC RAS SONGS |  |  | San Diego County | SONGS substation CEC-RAS upgrades | Substation - Protection Relay | Upgrade/Retrofit | NA | NA | Reliability | Relay Upgrades | NA | NA | 2024-10-30 | 2.85 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 230 | NA | 2 | 2022-2912 | QBL0001 | 1 | 3171 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2022-05-11 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | 2023-03-06 | 2023-08-03 | 2023-08-20 | NA | NA | TRUE | NA | NA ¦ NA | 1051.2247 | 0 | 0 | 22.411 | 994.6953 | 34.1183 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2023 ¦ 2024 | 0 | 0 | 0 | 1017.1063 | 34.1183 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0% | [Types of Analyses] Information security
41 | A TSA VSUBS 2022 |  |  | San Diego County | Transmission System Automation (TSA) upgrades at multiple substations | Substation - Protection Relay | Upgrade/Retrofit | NA | NA | Reliability | Relay Upgrades | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69 | NA | 2 | NA | QBL0001 | 1 | 3171 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2021-11-14 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | NA | 2023-12-31 | NA | NA | NA | TRUE | NA | NA ¦ NA | 1483.3948 | 0 | 0 | 668.7447 | 389.9539 | -89.9591 | 85.7759 | 428.8794 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2023 ¦ 2024 ¦ 2025 | 0 | 0 | 0 | 1058.6986 | -89.9591 | 3862.2233 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
42 | A SYSTEM AUTOMATION CROSSBOW |  |  | San Diego County | Siemens Crossbow deployments at multiple substations | Substation - Protection Relay | Upgrade/Retrofit | NA | NA | Reliability | Relay Upgrades | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69 ¦ 138 | NA | 2 | NA | QBL0001 | 1 | 3171 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-10-24 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | NA | 2023-12-31 | NA | NA | NA | FALSE | NA | NA ¦ NA | 3433.3439 | 354.202 | 659.0243 | 741.0698 | 441.3229 | 267.7223 | 80.8942 | 39.4693 | 0 | 0 | 0 | 0 | 3239.302 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
43 | A SYSTEM AUTOMATION VARIOUS SUBS |  |  | San Diego County | Transmission System Automation (TSA) upgrades at multiple substations | Substation - Protection Relay | Upgrade/Retrofit | NA | NA | Reliability | Relay Upgrades | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69 | NA | 2 | 2020-2045 | QBL0001 | 1 | 3171 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-03-04 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | 2020-08-12 | 2020-04-01 | 2021-04-08 | NA | NA | TRUE | NA | NA ¦ NA | 5056.6582 | 1244.82 | 2370.1925 | 178.7026 | -6.2042 | -0.44674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 | 0 | 0.36639 | 5062.9427 | -6.2042 | -0.44674 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
44 | 53531 A ADVANCED RLY EVENT RETRVL SUBS |  |  | Chula Vista, San Diego | Advanced Relay Event Retrieval (ARER) deployments at multiple substations | Substation - Protection Relay | Upgrade/Retrofit | NA | NA | Reliability | Relay Upgrades | NA | NA | 2024-10-08 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69 | NA | 2 | Multiple | QBL0001 | 21 | 3171 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-10-25 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | 2022-09-12 | 2023-12-31 | 6/12/2020 ¦ 1/18/2021 ¦ 9/4/2020 ¦ 9/8/2020 ¦ 9/8/2020 ¦ 2/24/2022 ¦ 9/1/2020 ¦ 9/1/2020 ¦ 1/21/2022 ¦ 9/1/2020 ¦ 1/21/2022 ¦ 12/7/2021 | NA | NA | TRUE | NA | NA ¦ NA | 3061.3601 | 1.0147 | 930.75 | 1331.2285 | 597.451 | 187.9716 | 12.9443 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2022 ¦ 2023 ¦ 2024 | 0 | 0 | 2262.9932 | 597.451 | 187.9716 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [Utility Unique ID #1] 2019-2110 , 2014-00646-ZZ , 2022-2975 , 2021-2053 , 2021-2130 , 2021-2134 , 2023-3594 , 2023-3600 , 2023-3602 , 2021-2023 , 2021-2022 , 2021-2020 , 2021-2024 , 2021-2461 , 2022-2919 , 2022-2927 , 2021-2131 , 2020-2051 , 2020-2080 , 2021-2003 , 2021-2315
45 | A MISSION SUBSTATION: PILOT TELEP |  |  | San Diego, San Diego | Pilot Telephony deployment at Mission Substation | Substation - Protection Relay | Upgrade/Retrofit | NA | NA | Reliability | Relay Upgrades | NA | NA | 2024-10-30 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 1.83 | 69 | NA | 2 | NA | QBL0001 | 1 | 3171 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2015-10-16 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | NA | 2016-12-31 | NA | NA | NA | FALSE | NA | NA ¦ NA | 1893.8837 | 269.587 | 741.5454 | 287.3885 | 4.9655 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 | 0 | -17.6185 | 1906.5367 | 4.9655 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
46 | A BERNARDO SUBST. RPL TL689 RLY |  |  | San Diego, San Diego | Upgrade 69kV relays and supporting equipment for TL689. | Substation - Protection Relay | Upgrade/Retrofit | NA | NA | Reliability | Relay Upgrades | NA | NA | 2024-10-03 | 3.32 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 2.51 (BE) / 4.66 (ES) | 69 | NA | 2 | 2014-01115-ZZ | QBL0001 | 1 | 3171 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-10-25 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Construction (over 75%) | NA | 2021-04-27 | 2023-11-14 | 2024-12-24 | NA | NA | TRUE | NA | NA ¦ NA | 12057.0243 | 1912.511 | 1207.5322 | 4046.0331 | 1806.6638 | 1478.7073 | 452.1619 | 138.3876 | 0 | 0 | 0 | 0 | 10450.4757 | NA | NA | 2021 ¦ 2022 ¦ 2025 | 0 | 1.2305 | -0.25875 | 0 | 0 | 12056.0526 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
47 | Ocean Ranch Substation |  |  | Oceanside, San Diego | Install a new 69/12kV substation in the North Vista/Oceanside area. Current substations that support this load (Melrose, Morro Hill, Oceanside, and San Luis Rey) are expected to be at 85% aggregate loading in 2016 and 96% in 2021. | Substation - Multiple | New | NA | NA | Load Growth | New Substation | Other [See Notes] | NA | 2024-09-24 | NA | Other [See Notes] | Wires - New Substation Alternative | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | Coastal |  | NA | 1.0084 | 69 | 69kV | 4.2 | 2014-00047-ZZ | QS00008 | 1 | 5253 | NA ¦ NA ¦ NA ¦ NA | FALSE | NA | Work Order Authorization | 2010 | 2016 | FALSE | 2016 | NA | https://www.caiso.com/planning/Pages/TransmissionPlanning/2015-2016TransmissionPlanningProcess.aspx | FALSE | Final Certified | 2017-10-02 | IS/MND | NA | CPUC | NA | PTC | 2017-03-06 | Approved | 2017 | Operational | NA | 2018-01-22 | 2019-06-01 | 2019-07-01 | Completed Early | NA | FALSE | 24115 | NA ¦ NA | 29085.2555 | 309.1136 | 4.6688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2020 ¦ 2021 | 309.1136 | 4.6688 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [NERC / WECC / CAISO Standard / Requirement / Contingency] Load growth in the area (Distribution Planning load forecast driver) [Types of Analyses] Distribution Planning
48 | SOCRE |  |  | San Juan Capistrano, Orange ¦ San Clemente, Orange | To rebuild the existing Capistrano Substation, which is currently a 138/12kV distribution substation to a 230/138/12kV. Remove TL13835 (SMO-LNL) between Talega Substation and Capistrano Substation. Open TL23007 (SONGS-TA) at Talega Substation and loop into Capistrano Substation two new 230kV' TLs (SONGS-CP230kV & CP-TA 230kV). Re-arrange 138kV TL's 13833, 138736, and 13812 bay positions at Talega to allow for the termination of TL13835 (SMO-TA) at Talega Substation. | Transmission Line/Substation | Upgrade/Retrofit | New | NA | Load Growth | Substation Capacity | NERC TPL Standards | NA | 2024-10-23 | 55; 62; 52;56; 54; 19 | Steady State Power Flow System Analysis | Wires - Reconductor/Line Rebuild Alternative | Multiple Options [See Notes] | HFTD Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | Transmission Foundations At Talega Canyon Containing High Levels Of Sulfate. Mitigated By Installing Cmp To Protect Concrete Foundations |  | 9.1339 | 6 | 230 | 230kV | 2.1 | 2014-00068-ZZ | QS00009 | 1 | 6129 | NA ¦ NA ¦ NA ¦ NA | FALSE | NA | Work Order Authorization | 2006 | 2011 | FALSE | 2009 ¦ 2011 | NA | https://www.caiso.com/planning/Pages/TransmissionPlanning/2010-2011TransmissionPlanningProcess.aspx | FALSE | Final Certified | 2016-04-25 | EIR | NA | CPUC | NA | CPCN | 2012-5-18 | Approved | 2016 | Construction (over 75%) | NA | 2018-06-29 | 2015-05-18 | 2024-08-15 | Construction Delays | Construction Delays | TRUE | 363363 | 381000 ¦ CPUC | 362293.8546 | 91113.5757 | 46910.7232 | 29821.7373 | 39636.0331 | 6082.4587 | 10825.0124 | 887.5457 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 67202.3981 | 132700.278 | 5577.5856 | 129956.0519 | 6164.4375 | 887.5457 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0% | [Alternative Solutions and Costs - Costs] SOCRUP Alternative 1: Rebuild Capistrano 230 kV substation, build a new SONGS – Capistrano 230 kV line using existing right-of-way, and build a new Escondido to Capistrano 230 kV line using existing right-of-way. Estimated cost for this alternative is $454.8 million. 2. SOCRUP Alternative 2: Rebuild Capistrano 138kV substation (aging infrastructure maintenance project), reconductor 138kV lines – Talega – Pico, Talega – Laguna Niguel, Talega – Trabuco, Capistrano – Trabuco, Talega – Rancho Mission Viejo, and upgrade SONGS – Talega 230 kV lines. Upgrade two 230/138 kV transformer banks at Talega. Estimated cost for this alternative is $347.6 million. 3. SOCRUP Alternative 3: Rebuild Capistrano 230 kV substation, build a new SONGS – Capistrano 230 kV line using existing right-of-way, and tap off a 230 kV line to Capistrano from existing Escondido – Talega 230 kV line. Estimated cost for this alternative is $364.8 million. Approved Alternative [Types of Analyses] Distribution Planning
49 | [Programmatic] Emergency Equipment Purchase |  |  | NA | This budget supports the restoration of service to our distribution customers following outages caused by equipment failure by purchasing additional emergency spare and mobile equipment. Spare equipment is necessary to provide construction and operations with the appropriate spares to replacement equipment under failure conditions. Spare equipment is typically use for critical situations and the stock must be kept up to date to minimize chances for mismatch in field. | Substation - Multiple | Replace | NA | NA | Reliability | Substation Reliability | NERC TPL Standards | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | Multiple | 28MVA | 4.1 | Multiple | QBL0024 | 34 | 6254 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-11-22 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Operational | NA | NA | 2024-12-31 | NA | NA | NA | TRUE | NA | NA ¦ NA | 0 | 296.3767 | 994.4584 | 280.2973 | 320.1574 | 164.5163 | 1118.4277 | 1182.6012 | 541.7181 | 553.5258 | 565.3233 | 574.4455 | 94.25 | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 521.1663 | 1171.5107 | 333.7874 | 266.4494 | 124.7478 | 1117.3468 | 0% | NA ¦ NA | 3.7 | NA | 100% | 0%
50 | [Programmatic] Fiber Build Initiative |  |  | NA | Install ADSS and or OPGW fiber optic cables on existing Transmission overhead structures and build UG facilities as required. 2020 has (20) active projects at various stages of engineering and construction. All projects to date are exempt from CPUC permitting. | Other | New | NA | NA | Reliability | NERC CIP Compliance | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | Multiple | NA | 4.3 | Multiple | QBL0025 | 210 | 7144 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-11-17 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | Categorical Exclusion | NA | NA | NA | NA | NA | NA | Operational | NA | NA | 2024-12-31 | NA | NA | NA | TRUE | NA | NA ¦ NA | 0 | 1869.8381 | 1758.37 | 2092.7825 | 4081.6185 | 3111.514 | 2596.8846 | 8983.9569 | 12335.3819 | 14043.1789 | 15341.1822 | 14788.6503 | 9402.3348 | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 2028.5002 | 830.1666 | 309.7797 | 2160.5806 | 1210.4656 | 6425.858 | 0% | NA ¦ NA | 6.3 | NA | 13.55% | 86.45%
51 | A FBI TL23012/53/674(Z710041 ENC) |  |  | Encinitas, San Diego | TL674/6973 EN-DM with OPGW attachments on TL23012/23053. | Other | New | New | NA | Reliability | System Operations | NA | NA | 2024-01-23 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 8.05 | NA | NA | NA | 4.3 | 2019-4010 | QBL0025 | 1 | 7144 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-01-20 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Engineering less than 50% complete | NA | 2026-04-27 | 2021-10-30 | 2026-07-27 | NA | NA | FALSE | NA | NA ¦ NA | 1311.179 | 82.3547 | 96.4412 | 352.8243 | 215.2307 | 527.5223 | 4.4299 | 17.8723 | 4.5065 | 0 | 0 | 0 | 1274.3732 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [Project Description - What] Fiber infrastructure build supports all transmission, distribution, substation, and IT equipment/systems for operations, metering, and real time monitoring.
52 | A TL23011 SAN LUIS REY E R4 |  |  | Oceanside, Carlsbad | Engineer and construct 9-miles of overhead OPGW-96 fiber optic cable structures between Encina 230kV and San Luis Rey substations. | Other | New | New | NA | Reliability | System Operations | NA | NA | 2024-01-16 12:00 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 9 | NA | 230 kV | 230 kV | 4.3 | 2014-00482-ZZ | QBL0025 | 1 | 7144 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-04-29 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | 2019-09-20 | 2020-03-31 | 2019-12-28 | NA | NA | FALSE | NA | NA ¦ NA | 2860.506 | 38.5221 | 17.2954 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2020 ¦ 2021 | 2843.2106 | 17.2954 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0% | [Project Description - What] Fiber infrastructure build supports all transmission, distribution, substation, and IT equipment/systems for operations, metering, and real time monitoring.
53 | A TL13809 PROCTOR VLY TO T R2 |  |  | Chula Vista, San Diego | Engineer and construct 3.2 miles of overhead OPGW-96 fiber optic cable from Proctor Valley to Telegraph Canyon substations. | Other | New | New | NA | Reliability | System Operations | NA | NA | 2024-09-23 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 3.2 | NA | NA | NA | 4.3 | 2014-00957-ZZ | QBL0025 | 1 | 7144 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-04-29 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | 2020-01-27 | 2020-03-31 | 2020-03-27 | NA | NA | FALSE | NA | NA ¦ NA | 1753.7239 | 1284.5072 | 49.0658 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2020 ¦ 2021 | 1704.6581 | 49.0658 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [Project Description - What] Fiber infrastructure build supports all transmission, distribution, substation, and IT equipment/systems for operations, metering, and real time monitoring.
54 | A FBI_TL23027 TL23028 MS OT |  |  | San Diego, San Diego | This project installs a fiber optic connection between Mission Substation and Oldtown Substation. | Other | New | New | NA | Reliability | System Operations | NA | NA | 2024-02-13 12:00 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 1.84 | NA | NA | NA | 4.3 | 2009-00015-ZZ | QBL0025 | 1 | 7144 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-09-13 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | 2021-02-15 | 2021-09-30 | 2021-07-12 | NA | NA | TRUE | NA | NA ¦ NA | 3839.5737 | 727.8738 | 2546.6883 | 338.0937 | 46.1068 | 118.8795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2022 ¦ 2023 ¦ 2024 | 0 | 0 | 3674.5874 | 46.1068 | 118.8795 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [Project Description - What] Fiber infrastructure build supports all transmission, distribution, substation, and IT equipment/systems for operations, metering, and real time monitoring.
55 | A TL 654 MISSIONSTATION F R3 |  |  | San Diego, San Diego County | This project installs fiber optic approximately 2.2 miles of 96-count ADSS Fiber Optic Cable on TL654 between Station F and Mission Substation as well as 5 pole replacement, and installation of 2 new Fiber-only poles, 3 fiber optic splice boxes and 10ft UG trench. | Other | New | New | NA | Reliability | System Operations | NA | NA | 2024-03-12 | 33;33;33;33;60 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | TBD |  | 5.28 | NA | NA | NA | 4.3 | 2014-00430-ZZ | QBL0025 | 1 | 7144 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-02-10 | Work Order Authorization | 2019 | NA | FALSE | NA | NA | NA | FALSE | TBD | NA | NA | NA | CPUC | NA | Exempt | NA | NA | NA | Operational | NA | 2021-02-24 | 2021-04-01 | 2021-05-24 | NA | NA | TRUE | NA | NA ¦ NA | 1090.352 | 336.5609 | 476.4009 | 77.6071 | 38.2451 | 52.7771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 | 0 | 921.7226 | 77.6071 | 38.2451 | 52.7771 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0%
56 | A TL608 STREAMVIEWCHOLLAS R4 |  |  | San Diego, San Diego County | This project installs ADSS fiber from Streamview to Chollas | Other | New | New | NA | Reliability | System Operations | NA | NA | 2024-03-16 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | TBD |  | 2.54 | NA | NA | NA | 4.3 | 2010-00005-ZZ | QBL0025 | 1 | 7144 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2013-05-13 | Work Order Authorization | 2019 | NA | FALSE | NA | NA | NA | FALSE | TBD | NA | NA | NA | CPUC | NA | Exempt | NA | NA | NA | On Hold | NA | 2028-02-17 | 2013-12-31 | 2028-05-17 | NA | NA | FALSE | NA | NA ¦ NA | 1143.2056 | 224.0888 | 89.4288 | 166.7859 | 94.8248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1126.502 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0%
57 | A TL 621 PARADISEMIGUEL F R2 |  |  | San Diego, San Diego County | This projects installs 6.7miles of ADSS friber from Paradise to Miguel | Other | New | New | NA | Reliability | System Operations | NA | NA | 2024-02-22 | NA | NA | NA | NA | HFTD Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | TBD |  | 7.484 | NA | NA | NA | 4.3 | 2010-00007-ZZ | QBL0025 | 1 | 7144 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2018-04-10 | Work Order Authorization | 2019 | NA | FALSE | NA | NA | NA | FALSE | TBD | NA | NA | NA | CPUC | NA | Exempt | NA | NA | NA | On Hold | NA | 2026-05-15 | 2019-12-01 | 2026-08-13 | NA | NA | FALSE | NA | NA ¦ NA | 1034.4144 | 40.9505 | 320.5978 | 508.7839 | 6.6927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 877.025 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0%
58 | A TL697 SAN LUIS REY OCE R7 |  |  | Oceanside, San diego County | This project consists of installing 1 cable (192-Fiber DNA-33029 ADSS) on TL697 between structures Z229374 to Z28268, approximately 1 mile. Project includes installing 3 fiber optic splice locations and 26 ADSS connections. | Other | New | New | NA | Reliability | System Operations | NA | NA | 2024-07-25 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | TBD |  | 1.49 | NA | NA | NA | 4.3 | 2014-00465-ZZ | QBL0025 | 1 | 7144 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-01-27 | Work Order Authorization | 2019 | NA | FALSE | NA | NA | NA | FALSE | TBD | NA | NA | NA | CPUC | NA | Exempt | NA | NA | NA | Operational | NA | 2022-04-21 | 2020-11-01 | 2022-09-28 | NA | NA | TRUE | NA | NA ¦ NA | 1246.6779 | 182.7742 | 85.3147 | 495.0539 | 51.1882 | 212.0044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2022 ¦ 2023 ¦ 2024 | 0 | 0 | 983.4853 | 51.1882 | 212.0044 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0%
59 | TL6926 Rincon to Valley Center Fire Hardening |  |  | Valley Center, San Diego | Fire harden a portion of TL6926 by replacing approximately 50 wood poles with equivalent steel poles in the high fire threat and wind-prone areas. TL6926 is a single circuit 69 kV transmission line located between the Valley Center Substation and the Rincon Substation. Approximately one mile of the line will be reconductored. The line will be fire hardened between poles Z12820 and Z114811, with the exception of the portion located adjacent to Valley Center Road near the Rincon Casino. Approximately one mile of the transmission line will be reconductored. | Transmission Line - Multiple | Replace | Removal | NA | Wildfire Mitigation | T-Line Reliability | NA | NA | 2024-11-09 | 38 | NA | NA | NA | HFTD Tier 3 | FALSE ¦ FALSE ¦ TRUE | FALSE | NA |  | 4.6374 | NA | 69 | NA | 1.2 | 2014-00061-ZZ | QS00025 | 1 | 9132 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2011-12-08 | Work Order Authorization | 2009 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | NA | NA | Advice Letter | 2019-11-13 | Approved | 2020 | Operational | NA | 2020-12-14 | 2013-01-31 | 2023-06-20 | Permitting | NA | TRUE | 65729 | NA ¦ NA | 104975.9915 | 16920.3569 | 57303.6517 | 16554.1531 | 2325.7931 | 301.194 | 0 | 1959.3467 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 0 | 1.1761 | 99114.3707 | 3515.0473 | 301.194 | 1959.3467 | 0% | NA ¦ NA | 21.6 | NA | 0% | 100% | [CPUC Filing Type] Advice Letter/ Project Completed with temporary shoo-fly configuration
60 | TL649 W2S |  |  | San Diego, San Diego ¦ Chula Vista, San Diego | A portion of TL649 is within the fire and wind prone area. Replace a portion of TL649 with steel poles in order to maintain existing electric transmission in high fire threat & wind prone areas in SDG&E territory. TL649 is a 69 kV single-circuit transmission line located between pole Z188714 & pole Z31758. The proposed project consists of the following components: Replace approximately 116 existing wood power line and interest distribution line poles with galvanized steel structures. Approx. half of the replacement poles will be direct buried with the other half being engineered foundations (pier & micropile).Reroute approximately 130 feet of existing underground distribution lines. Conduct overhead work on one existing pole and transfer existing power line conductors to the new steel poles. Replace the existing distribution conductor with new ACSR distribution conductor. | Transmission Line - Multiple | Replace | NA | NA | Wildfire Mitigation | T-Line Reliability | NA | NA | 2024-01-16 12:00 | 47 | NA | NA | NA | HFTD Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 7.7111 | NA | 69 | NA | 1.2 | 2017-0120 | QS00026 | 1 | 9137 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-09-04 | Work Order Authorization | 2009 | NA | FALSE | NA | NA | NA | FALSE | Final Certified | NA | IS/MND | NA | CPUC | NA | PTC | 2015-08-10 | Approved | 2019 | Operational | NA | 2019-07-11 | 2020-02-15 | 2020-02-22 | NA | NA | FALSE | NA | NA ¦ NA | 29952.5135 | 5888.1197 | 56.4388 | 1.2259 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2020 ¦ 2021 ¦ 2022 | 5981.7039 | 56.5897 | 1.2259 | 0 | 0 | 0 | 0% | NA ¦ NA | 8.3 | NA | 0% | 100% | [CPUC Filing Type] Advice Letter/ Project Completed with temporary shoo-fly configuration
61 | TL686 W2S_Wind |  |  | San Diego County | TL686 Wood-to-Steel will include the replacement of 182 wood and wood equivalent steel (SW) poles with 120 new poles. Scope includes the reconductoring of 14.6 miles of 69kV transmission and associated 12kV distribution underbuild (where underbuild is present) from Warners substation to just outside the Tier 2 HFTD (ending at structure Z118409). All replacements will be either direct-buried SW poles or foundation steel poles. Direct-buried transmission SW and distribution SW Round (SWR) poles shall be backfilled with concrete and gravel. Engineered steel poles shall have either drilled pier or micropile foundations. Per SDG&E’s fire hardening standards, traditional 69 kV design and construction standards with additional phase spacing and insulation shall be used and guy anchors shall be avoided. Shield wire with a fiber (OPGW) will be added to protect phase conductors from lightning damage. All transmission conductors in this project shall be reconductored. All poles will be designed to accommodate one level of third-party communication. | Transmission Line - Pole/Tower | Replace | Removal | 23126 | Wildfire Mitigation | T-Line Reliability | NA | NA | 2024-01-09 12:00 | 47 | NA | NA | NA | HFTD Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 24.6759 | NA | 69 | NA | 1.2 | 2018-0161 | QS00027 | 1 | 9142 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-10-05 | Work Order Authorization | 2012 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | NA | BLM | Exempt | NA | NA | NA | Operational | NA | 2028-04-14 | 2027-08-25 | 2029-10-02 | Land Rights | Permitting | FALSE | 5446.0598 | NA ¦ NA | 137920.0812 | 1529.5135 | 1923.6474 | 1337.7718 | 1315.6179 | -344.8229 | 241.1386 | 1726.91 | 1850.7545 | 17883.3064 | 46687.981 | 60055.844 | 9533.635 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | 28.6 | NA | 0% | 100%
62 | TL676 Reconductor (Mission Mesa Heights) |  |  | San Diego, San Diego | The TL676 project is a reconductor project between Mesa Heights Substation and Mission Substation. It includes reconductoring approx. 4.3 miles of transmission line (TL676) with single 900 ACSS/AW, reconductoring approx. 3.7 miles of distribution underbuild with single 636 ACRS/AW, and converting sections of the 69kV out of both substations with underground getaways. | Transmission Line - Multiple | Upgrade/Retrofit | NA | NA | Local Capacity Requirement | Age/Condition - Replace Wood Poles | CAISO Requirement | NA | 2024-03-12 12:00 | 47 | Steady State Power Flow System Analysis | Wires - Reconductor/Line Rebuild Alternative | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 7.9515 | NA | 69 ¦138 | NA | 2.1 | 2011-00017-ZZ | QS00343 | 1 | 9153 | NA ¦ NA ¦ NA ¦ NA | FALSE | NA | Work Order Authorization | 2011 | 2011 | FALSE | 2010 ¦ 2011 | NA | https://www.caiso.com/planning/Pages/TransmissionPlanning/2010-2011TransmissionPlanningProcess.aspx | FALSE | NA | NA | NA | NA | NA | NA | Advice Letter | 2017-07-25 | Approved | 2017 | Operational | NA | 2018-06-04 | 2015-06-01 | 2019-06-07 | Prioritization | NA | TRUE | 28730.5269 | NA ¦ NA | 38598.5136 | 186.7196 | 46.9773 | 0.13369 | 0 | -24.7372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2024 | 3934.1667 | 46.9773 | 0.13369 | 0 | -24.7372 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
63 | A SAN LUIS RAY OVERSTRES |  |  | Oceanside, San Diego | Replace breakers based on short circuit study | Substation - Circuit Breaker | Replace | Upgrade/Retrofit | NA | Reliability | Replace Breakers | NA | NA | 2024-10-18 | 50; 50; 50; 53; 50; 50; 53; 53; 53; 50; 53; 53; 53; 53 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 6.12 | 69 | 230 kV ¦ 69 kV | 2.1 | 2022-2943 | QBL0061 | 1 | 9170 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2021-06-18 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Engineering more than 50% complete | NA | 2024-12-09 | 2023-12-31 | 2026-01-01 | Multiple Options [See Notes] | NA | TRUE | NA | NA ¦ NA | 3065.1273 | 0 | 1659.8046 | 335.3891 | 307.8147 | 439.0306 | 59.3891 | 251.0239 | 12.6752 | 0 | 0 | 0 | 2742.039 | NA | NA | 2025 | 0 | 0 | 0 | 0 | 0 | 315.0311 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [Reason for Change in In-Service Date] In-service dates are estimated during preliminary design and permitting stages of a project; date shifted to reflect actual design and construction schedule.
64 | [Programmatic] Overstressed Breakers |  |  | NA | Replace overstressed breakers as identified at the following substations : Bay Boulevard, Mission, Sycamore Canyon, San Luis Rey, Miguel | Substation - Circuit Breaker | Replace | NA | NA | Reliability | Age/Condition | NERC TPL Standards | NA | NA | NA | NA | Wires - Replacement Alternative | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | Multiple | NA | 2.1 | Multiple | QBL0061 | 17 | 9170 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-11-29 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Planning | NA | NA | 2024-12-31 | NA | NA | NA | TRUE | NA | NA ¦ NA | 0 | 44.951 | 18.8614 | 42.2006 | 301.2157 | 195.4875 | 315.0311 | 1820.9776 | 2585.8385 | 2893.1907 | 3231.1721 | 3602.6944 | 574.104 | NA | NA | 2020 ¦ 2024 | 36.8775 | 0 | 0 | 0 | 565.8388 | 0 | 0% | NA ¦ NA | 6.6 | NA | 0% | 100%
65 | A MIGUEL OVERSTRESSED BREAKER |  |  | San Diego County | Miguel - 69kV Overduty CB/DC Motor Retrofit | Substation - Circuit Breaker | Replace | Upgrade/Retrofit | NA | Reliability | Age/Condition - Replace Breakers | NA | NA | 2024-10-22 | 51 | NA | NA | NA | HFTD Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 12.37 | 69 | 69 kV | 2.1 | 2021-2498 | QBL0061 | 1 | 9170 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-10-13 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | 2024-01-17 | 2021-09-01 | 2024-07-16 | Multiple Options [See Notes] | NA | TRUE | NA | NA ¦ NA | 1394.9981 | 0 | 103.6174 | 499.083 | 225.32 | 566.9778 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2024 | 0 | 0 | 0 | 0 | 1394.9981 | 0 | 46% | 100% ¦ 1921 | NA ¦ NA | NA | 0% | 100% | [Reason for Change in In-Service Date] In-service dates are estimated during preliminary design and permitting stages of a project; date shifted to reflect actual design and construction schedule.
66 | A SYCAMORE CYN OVERSTRESSED BKR R |  |  | San Diego County | Sycamore Canyon Overstressed Breaker Replacement | Substation - Circuit Breaker | Replace | Upgrade/Retrofit | NA | Reliability | Age/Condition - Replace Breakers | NA | NA | 2024-10-03 | 16; 16; 16; 16; 16; 16; 16; 31; 32; 32; 32; 32; 32; 32; 33; 25; 25; 31 | NA | NA | NA | HFTD Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 10.79 | 69 | 138 kV ¦ 69 kV | 2.1 | 2019-1023 | QBL0061 | 1 | 9170 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-04-23 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | 2020-05-04 | 2020-12-31 | 2022-12-31 | Multiple Options [See Notes] | NA | FALSE | NA | NA ¦ NA | 8569.8308 | 1704.0793 | 1815.8743 | 1495.8071 | 109.4131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2022 ¦ 2023 | 0 | 0 | 8460.4178 | 109.4131 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [Reason for Change in In-Service Date] In-service dates are estimated during preliminary design and permitting stages of a project; date shifted to reflect actual design and construction schedule.
67 | [Programmatic] Synchrophasors (PMU/WASA) |  |  | NA | Replace relays | Substation - Protection Relay | Replace | Upgrade/Retrofit | NA | Reliability | Relay Upgrades | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | Multiple | 138 kV ¦ 230 kV ¦ 500 kV | 4.3 | Multiple | QBL0062 | 44 | 10138 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-11-22 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | TBD | NA | NA | NA | CPUC | NA | Exempt | NA | NA | NA | Operational | NA | NA | 2024-12-31 | NA | NA | NA | TRUE | NA | NA ¦ NA | 0 | 84.4107 | 639.667 | -147.8552 | 102.4974 | 573.9795 | 451.3744 | 2045.5988 | 3969.9058 | 5349.7757 | 5738.3873 | 5731.6106 | 680.1513 | NA | NA | 2020 ¦ 2021 ¦ 2023 ¦ 2025 | 268.4821 | 11.5456 | 0 | 1058.2385 | 0 | 1333.8389 | 0% | NA ¦ NA | 5.1 | NA | 13.55% | 86.45% | [Age of Asset] Unable to provide age of asset for blanket budget codes
68 | A SYNCHRO VSUBS 2022 |  |  | Escondido, San Diego | PMU/WASA deployments at multiple substations | Substation - Protection Relay | Upgrade/Retrofit | NA | NA | Reliability | Relay Upgrades | NA | NA | 2024-10-14 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69 ¦ 500 | NA | 4.3 | Multiple | QBL0062 | 2 | 10138 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-11-01 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Construction (50%-75%) | NA | 2023-04-17 | 2023-12-31 | 2024-10-25 | NA | NA | TRUE | NA | NA ¦ NA | 7897.0995 | 0 | 674.9986 | 2679.2701 | 2462.7281 | 1230.1448 | 214.5835 | 635.3743 | 0 | 0 | 0 | 0 | 7047.1417 | NA | NA | 2025 | 0 | 0 | 0 | 0 | 0 | 7897.0995 | 0% | NA ¦ NA | NA ¦ NA | NA | 13.55% | 86.45% | [Utility Unique ID #1] 2021-2149 , 2022-3042
69 | A TRANS SYNCHROPHASOR VAR SUB |  |  | NA | PMU/WASA deployments at multiple substations | Substation - Protection Relay | Upgrade/Retrofit | NA | NA | Reliability | Relay Upgrades | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69 ¦ 500 | NA | 4.3 | Multiple | QBL0062 | 22 | 10138 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2018-03-23 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Construction (over 75%) | NA | 2023-04-17 | 2019-03-31 | NA | NA | NA | TRUE | NA | NA ¦ NA | 23781.9168 | 6979.6379 | 6187.6461 | 83.5886 | 271.2511 | 130.0683 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 ¦ 2024 | 6979.6379 | 6187.6461 | 83.5886 | 271.2511 | 130.0683 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 13.55% | 86.45% | [Utility Unique ID #1] 2021-2143 , 2023-3601 , 2021-2051 , 2021-2042 , 2021-2026 , 2022-2933 , 2022-2935 , 2021-2401 , 2021-2130 , 2021-2149 , 2021-2132 , 2021-2134 , 2021-2148 , 2021-2136 , 2023-3594 , 2023-3600 , 2023-3602 , 2018-1009 , 2021-2131 , 2019-2124 , 2023-3595 , 2021-2035
70 | TL690E – Camp Pendleton – Wood to Steel |  |  | Camp Pendleton, San Diego | Replace approx. 72 wood poles with overhead steel poles and/or underground cabling. Reconductor approx. 5.4 mi from Stuart Tap to Las Pulgas Substation. | Transmission Line - Multiple | Replace | Upgrade/Retrofit | NA | Wildfire Mitigation | T-Line Reliability | NERC TPL Standards | NA | 2024-07-25 | 58 | Steady State Power Flow System Analysis | Wires - Reconductor/Line Rebuild Alternative | NA | HFTD Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 5.3506 | NA | 69 | NA | 1.2 | 2014-00050-ZZ | QS00040 | 1 | 10143 | NA ¦ NA ¦ NA ¦ NA | FALSE | NA | Work Order Authorization | 2012 | 2014 | FALSE | 2014 | NA | https://www.caiso.com/planning/Pages/TransmissionPlanning/2013-2014TransmissionPlanningProcess.aspx | FALSE | NA | NA | Exempted | NA | CPUC | MCBCP | PTC | 2024-07-11 | To be Filed | 2026 | Engineering more than 50% complete | NA | 2027-11-18 | 2015-06-01 | 2028-11-08 | Project Design | Permitting | FALSE | 142840.7251 | NA ¦ NA | 44752.3907 | 1457.2392 | 1383.3476 | 1527.0309 | 1676.1514 | 1456.47 | 565.6037 | 2594.0853 | 2635.9194 | 7818.2236 | 17615.567 | 1685.4955 | 7498.5952 | NA | NA | 2020 | 1.6439 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | 4.2 | NA | 0% | 100%
71 | TL691 Avocado to Camp Pendleton |  |  | Fallbrook, San Diego ¦ Camp Pendleton North, San Diego | This project will replace existing wood poles along TL691 within the Fire Threat Zone with new steel poles and associated hardware. | Transmission Line - Multiple | Replace | NA | NA | Wildfire Mitigation | T-Line Reliability | NA | NA | 2024-02-10 | 47 | NA | NA | NA | HFTD Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 11.5485 | NA | 69 | NA | 1.2 | 2014-00051-ZZ | QS00041 | 1 | 10144 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2022-12-22 | Work Order Authorization | 2012 | NA | FALSE | NA | NA | NA | FALSE | NA | 2019-11-01 | Exempted | Categorical Exclusion | CPUC | MCBCP | Advice Letter | 2020-12-03 | NA | 2021 | Operational | NA | 2023-04-28 | 2024-02-29 | 2023-12-21 | NA | NA | TRUE | 43446.3952 | NA ¦ NA | 46277.7525 | 1512.4206 | 3971.736 | 2405.8417 | 28254.1162 | 3841.4976 | 2726.136 | 52.8822 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2024 ¦ 2025 | 0 | 0 | 0 | 0 | 43498.7343 | 52.8822 | 0% | NA ¦ NA | 22.5 | NA | 0% | 100%
72 | TL692 Horno Pulgas (Camp Pend) |  |  | Camp Pendleton, San Diego | This project will replace existing wood poles along TL692 within the Fire Threat Zone with new steel poles and associated hardware. | Transmission Line - Multiple | Replace | NA | NA | Wildfire Mitigation | T-Line Reliability | NA | NA | 2024-06-11 | 52 | NA | NA | NA | HFTD Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 6.6533 | NA | 69 | NA | 1.2 | 2014-00225-ZZ | QS00042 | 1 | 10145 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-02-19 | Work Order Authorization | 2012 | NA | FALSE | NA | NA | NA | FALSE | NA | 2019-07-19 | Exempted | Categorical Exclusion | CPUC | MCBCP | Exempt | NA | NA | 2021 | Operational | NA | 2021-05-17 | 2021-11-01 | 2021-11-01 | NA | NA | TRUE | 24755.7706 | NA ¦ NA | 17797.1491 | 3157.7651 | 11169.0268 | 1339.9907 | 43.5217 | 2.5354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 | 0 | 16411.1014 | 1339.9907 | 43.5217 | 2.5354 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
73 | TL695/6971 Talega Cristianitos Japanese (Camp Pend) |  |  | San Clemente, Orange | Transmission Planning has identified TL695 as a NERC Category B violation therefore the conductor size must be upgraded to an acceptable capacity. This project will also replace existing wood poles along TL695 within the Fire Threat Zone with new steel poles and associated hardware. Transmission Engineering will double circuit TL695 (and future TL6971) from Basilone Substation to Japanese Mesa Substation, cross the Edison 230kV corridor, travel north along the existing 138kV corridor to Talega Substation. | Transmission Line - Multiple | Replace | New | NA | Wildfire Mitigation | T-Line Reliability | NERC TPL Standards | NA | 2024-02-10 12:00 | 56 | Steady State Power Flow System Analysis | Wires - Reconductor/Line Rebuild Alternative | NA | HFTD Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 7.8008 | NA | 69 | NA | 1.2 | 2014-00074-ZZ | QS00043 | 1 | 10146 | NA ¦ NA ¦ NA ¦ NA | FALSE | NA | Work Order Authorization | 2012 | 2012 | FALSE | 2012 | NA | https://www.caiso.com/planning/Pages/TransmissionPlanning/2011-2012TransmissionPlanningProcess.aspx | FALSE | CEQA Draft Published | 2017-07-07 | IS/MND | EA | CPUC | MCBCP | PTC | 2016-04-25 | Approved | 2018 | Permitting | NA | 2026-03-26 | NA | 2027-07-01 | Project Design | Permitting | FALSE | 44272.5792 | NA ¦ NA | 59144.3728 | 1351.8217 | 2875.0483 | 2320.4083 | 1770.8854 | 1461.0082 | 712.164 | 2783.2858 | 16034.7581 | 21435.4157 | 2439.4173 | 0 | 15483.177 | NA | NA | 2023 | 0 | 0 | 0 | 132.2838 | 0 | 0 | 0% | NA ¦ NA | 1.4 | NA | 0% | 100%
74 | TL6912 San Luis Rey to Camp Pendleton |  |  | Oceanside, San Diego ¦ Camp Pendleton North, San Diego | This project will replace existing wood poles along TL6912 within the Fire Threat Zone with new steel poles and associated hardware. | Transmission Line - Multiple | Replace | Upgrade/Retrofit | NA | Wildfire Mitigation | T-Line Reliability | NA | NA | 2024-07-25 | 62 | NA | NA | NA | HFTD Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 7.5058 | NA | 69 | NA | 1.2 | 2014-00073-ZZ | QS00045 | 1 | 10149 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-07-26 | Work Order Authorization | 2012 | NA | FALSE | NA | NA | NA | FALSE | NA | 2017-12-01 | Exempted | Categorical Exclusion | CPUC | MCBCP | NA | NA | NA | NA | Operational | NA | 2020-02-24 | 2020-09-04 | 2020-09-04 | NA | NA | FALSE | 23135.8596 | NA ¦ NA | 14701.5855 | 7812.1557 | 1266.3612 | -375.0751 | 98.0092 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 | 13693.5083 | 1283.0638 | -372.9957 | 98.0092 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
75 | TL663 Reconductor (Mission Kearny) |  |  | San Diego, San Diego | Construction of this project provides a long term “wires” mitigation for the identified NERC CAT B reliability criteria indications. Availability of the short term non wires option of depending on the pre contingency dispatch of the Kearny gas turbines to provide loading relief is no longer available after 2013. | Transmission Line - Conductor | Upgrade/Retrofit | NA | NA | Local Capacity Requirement | T-Line Capacity | NERC TPL Standards | NA | 2024-03-12 | 28;60;38 | Steady State Power Flow System Analysis | Wires - Reconductor/Line Rebuild Alternative | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 6.5902 | NA | 69 | NA | 2.1 | 2011-00018-ZZ | QS00049 | 1 | 11126 | NA ¦ NA ¦ NA ¦ NA | FALSE | NA | Work Order Authorization | 2012 | 2011 | FALSE | 2011 | NA | https://www.caiso.com/planning/Pages/TransmissionPlanning/2010-2011TransmissionPlanningProcess.aspx | FALSE | NA | NA | Exempted | NA | NA | NA | Advice Letter | 2017-05-31 | Approved | 2017 | Operational | NA | 2017-12-13 | 2015-06-01 | 2020-02-26 | Bundling Dependencies | Permitting | TRUE | 8171.0385 | NA ¦ NA | 39941.5012 | 2014.7838 | 249.7861 | 550.5743 | 59.2286 | 41.0228 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 ¦ 2024 | 38073.2629 | 1177.3096 | 590.6773 | 59.2286 | 41.0228 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
76 | TL644 Reconductor (Bay Blvd Sweetwater) |  |  | National City, San Diego ¦ Chula Vista, San Diego | The purpose of the TL644 Reconductor Project is to improve the reliability of the Transmission System by mitigating potential NERC Category B Criteria violations. The Project will increase the ampacity of TL644 to 204MVA (1,708A) by replacing the single-circuit underground 1750kCMIL aluminum cable to a twin-circuit underground 3000kCMIL copper cable system. Upon completion, the upgrades will mitigate overloads on TL644 in the event of an outage on TL642. | Transmission Line - Conductor | Upgrade/Retrofit | NA | NA | CAISO Transmission Planning Standards [See Notes for NERC Compliance and contingency code, WECC Requirement (and the specific requirement)] | T-Line Capacity | NERC TPL Standards | NA | 2024-02-22 | 25;25 | Steady State Power Flow System Analysis | Wires - Reconductor/Line Rebuild Alternative | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | Coastal |  | 1 | NA | 69 | NA | 2.1 | 2011-00021-ZZ | QS00054 | 1 | 11154 | NA ¦ NA ¦ NA ¦ NA | FALSE | NA | Work Order Authorization | 2012 | 2011 | FALSE | 2011 | NA | https://www.caiso.com/planning/Pages/TransmissionPlanning/2010-2011TransmissionPlanningProcess.aspx | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | Approved | 2019 | Operational | NA | 2021-12-06 | 2013-06-01 | 2022-05-15 | Permitting | Prioritization | TRUE | 9464.457 | NA ¦ NA | 10803.5203 | 507.5791 | 2906.133 | 2524.9442 | 709.313 | 71.9572 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2022 ¦ 2023 ¦ 2024 | 0 | 0 | 10022.2501 | 709.313 | 71.9572 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
77 | [Programmatic] Automated Fault Location (TEAM) |  |  | NA | This project provides funds for installation, upgrade, and expansion of SDG&E's Event Reporting Software and hardware to include Automated Fault Locator. This new system known as TEAM will provide accurate fault location within seconds by measuring the parameters at both ends of the line (multiple ends on multi-terminal lines) and time synchronizing the events with GPS clock. | Substation - Multiple | Upgrade/Retrofit | NA | NA | Reliability | Automation | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | Multiple | 373MVA | 4.3 | Multiple | QBL0063 | 5 | 12129 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2022-10-05 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | NA | 2022-12-31 | NA | NA | NA | FALSE | NA | NA ¦ NA | 0 | 11.4471 | 422.6652 | 81.1314 | 7.0931 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2020 ¦ 2022 ¦ 2023 | -2.3134 | 0 | 502.8661 | 43.1545 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0%
78 | A AFL VARIOUS SUB |  |  | San Diego County | Automated Fault Location (TEAM) deployments at multiple substations. | Substation - Other Equipment | Upgrade/Retrofit | NA | NA | Reliability | Relay Upgrades | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69 ¦ 138 | NA | 4.3 | NA | QBL0063 | 1 | 12129 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-04-15 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | NA | 2019-12-31 | NA | NA | NA | FALSE | NA | NA ¦ NA | 1034.7721 | 467.1556 | 128.1801 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 | 0 | 1034.7721 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0%
79 | [Programmatic] Substation SCADA Expansion |  |  | NA | The project provides funding for the installation, upgrades, and expansion of the Supervisory Control and Data Acquisition (SCADA) system at transmission substations. Additionally, this project improves the protection of SDG&E’s transmission system to provide fast isolation for faults and system disturbances. Includes upgrading relays including increased security, differential protection, and traveling wave fault finding technology to reduce restoration times. | Substation - Multiple | Upgrade/Retrofit | NA | NA | Reliability | Install SCADA/RTU | NERC PRC Compliance | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | Multiple | 373MVA | 4.3 | Multiple | QBL0064 | 32 | 12132 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-11-22 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | NA | 2024-12-31 | NA | NA | NA | TRUE | NA | NA ¦ NA | 0 | 817.692 | 1087.1578 | 785.8235 | 517.6639 | 928.8678 | 313.9384 | 2718.8708 | 3803.7399 | 4316.7795 | 4729.6889 | 5253.8927 | 1675.5356 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 0 | 2000.6913 | 385.5493 | 1098.9512 | 325.7019 | 2391.1899 | 0% | NA ¦ NA | 34 | NA | 0% | 100%
80 | A T SCADA: TRABUCO RTU |  |  | Laguna Niguel, Orange | Trabuco substation Transmission RTU upgrades | Substation - Protection Relay | Upgrade/Retrofit | NA | NA | Reliability | Relay Upgrades | NA | NA | 2024-10-21 | 3.7 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 1.92 | 69 | NA | 4.3 | 2023-3393 | QBL0064 | 1 | 12132 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2022-09-01 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Engineering more than 50% complete | NA | 2025-02-21 | 2023-12-30 | 2025-08-29 | NA | NA | TRUE | NA | NA ¦ NA | 1279.2653 | 0 | 0 | 15.1845 | 245.1148 | 527.3861 | 109.4955 | 382.0844 | 0 | 0 | 0 | 0 | 787.6854 | NA | NA | 2025 | 0 | 0 | 0 | 0 | 0 | 1279.2653 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
81 | A RANCHO CARMEL T SCADA |  |  | San Diego, San Diego | Rancho Carmel substation Transmission SCADA upgrades. | Substation - Protection Relay | Upgrade/Retrofit | NA | NA | Reliability | Relay Upgrades | NA | NA | 2024-10-02 | 5.52 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 1.35 | 69 | NA | 4.3 | 2023-3392 | QBL0064 | 1 | 12132 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2021-09-15 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | On Hold | NA | 2024-10-31 | 2023-12-31 | 2025-12-24 | NA | NA | TRUE | NA | NA ¦ NA | 1562.3955 | 0 | 0.58867 | 4.3537 | 179.4357 | 613.1768 | 2.742 | 762.0986 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2025 | 0 | 0 | 0 | 0 | 0 | 762.0986 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
82 | A TRANSMISSION SCADA TL23014_015 |  |  | Escondido, San Diego | Replace (2) GE L-90 relays with latest SDG&E standard, (2) SEL-411L at ES (TL23014/15) | Substation - Protection Relay | Upgrade/Retrofit | NA | NA | Reliability | Relay Upgrades | NA | NA | 2024-03-02 | 6 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 4.66 | 230 | NA | 4.3 | 2021-2013 | QBL0064 | 1 | 12132 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-10-27 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | 2023-02-01 | 2023-12-31 | 2023-11-10 | NA | NA | TRUE | NA | NA ¦ NA | 1001.7985 | 0 | 201.2061 | 265.8805 | 522.1258 | 12.5862 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2023 ¦ 2024 | 0 | 0 | 0 | 989.2124 | 12.5862 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0%
83 | TL639 Wood to Steel Replacement |  |  | San Diego, San Diego | The TL639 Fire Hardening and Reconductor Project consists of installing new steel structures along the 69kV tie line between Elliott Substation and Structure Z100981, located inside Sycamore Canyon. The replacement structures from TL639 Elliott to Structure Z379545 will be constructed in conjunction with TL636, since most of the structures in that portion are single pole double circuit. TL639 Wood to Steel will cover pole replacements starting at Sycamore Canyon Substation to Structure Z379545. The project spans approximately 4.8 miles. | Transmission Line - Multiple | Replace | Upgrade/Retrofit | NA | Wildfire Mitigation | Priority 1 Steel Structure Replacement | NA | NA | 2024-07-30 12:00 | 41 | NA | NA | NA | HFTD Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 8.1767 | NA | 69 | NA | 1.2 | 2012-00005-ZZ | QS00066 | 1 | 12136 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-10-04 | Work Order Authorization | 2015 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | CPUC | NA | Exempt | NA | NA | NA | Operational | NA | 2022-10-31 | 2024-01-31 | 2023-10-07 | NA | NA | TRUE | 241.5125 | NA ¦ NA | 12734.2042 | 506.7398 | 874.9164 | 2296.9075 | 7361.9751 | 860.5381 | 58.6824 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2022 ¦ 2023 ¦ 2024 | 0 | 0 | 53.9001 | 1.445 | 12620.1767 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
84 | TL6916 Wood to Steel Replacement |  |  | San Diego, San Diego | APPROXIMATELY 5 MILES OF FIRE HARDENING ON TL6916 WOOD TO STEEL PROJECT. ALL EXISTING WOOD TRANSMISSION POLES WILL BE REMOVED FROM SERVICE/REPLACED WITH PRE ENGINEERED POLES OR ENGINEERED STEEL POLES AND ASSOCIATED DISTRIBUTION WOOD POLES ON CIR434 AND CIR920 WILL BE REPLACED WITH STEEL POLES. NEW CONDUCTOR 900ACSS WILL REPLACE EXISTING 900ACSS CONDUCTOR DUE TO CONSTRUCTION AND OUTAGE CONSTRAINTS OF EXISTING CONFIGURATION. DISTRIBUTION CONDUCTOR WILL BE UPGRADED TO 636 AND #2 ACSR CONDUCTOR. 1-96CT ADSS WILL BE INSTALLED FROM Z678465 TO Z100980. 31 NEW SW POLES WILL BE INSTALLED ALONG WITH 12 NEW ENGINEERED STEEL POLES. WE PREDICT 9 DRILLED PIER FOUNDATIONS AND 3 NEW MICROPILE FOUNDATIONS WILL BE INSTALLED. | Transmission Line - Pole/Tower | Replace | NA | NA | Wildfire Mitigation | T-Line Reliability | NA | NA | 2024-01-09 12:00 | 47 | NA | NA | NA | HFTD Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 4.7679 | NA | 69 | NA | 1.2 | 2012-00006-ZZ | QS00067 | 1 | 12137 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-11-08 | Work Order Authorization | 2015 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | NA | NA | Exempt | NA | Approved | 2021 | Operational | NA | 2022-03-07 | 2022-07-01 | 2022-07-11 | NA | NA | TRUE | 104.0282 | NA ¦ NA | 14659.369 | 427.3278 | 1495.1294 | 11255.3314 | 221.3696 | 48.4543 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2022 ¦ 2023 ¦ 2024 | 0 | 0 | 14371.4153 | 239.4994 | 48.4543 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
85 | TL615 TL659 Direct Buried Cable Replacement (Cabrillo Point Loma) |  |  | San Diego, San Diego | Replace approximately six (6) miles of direct buried cable on TL615 and TL659 within the streets of Point Loma into a new double circuit 69kV duct package infrastructure with off-setting substructures in an effort to mitigate reliability issues associated with aging direct buried cable systems. | Transmission Line - Underground | Upgrade/Retrofit | NA | NA | Reliability | Age/Condition | NA | NA | 2024-05-22 | 47 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 4 | NA | 69 | NA | 4.1 | 2012-00011-ZZ | QS00068 | 1 | 12138 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-07-20 | Work Order Authorization | 2012 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | 2024-12-13 | Approved | 2024 | Construction (under 10%) | NA | 2024-10-28 | 2026-12-31 | 2026-12-31 | Permitting | Land Rights | FALSE | 46528 | NA ¦ NA | 81923.4105 | 1067.216 | 13695.3243 | 2707.0372 | 4920.9316 | 5287.0831 | 8400.0259 | 24827.504 | 13873.8627 | 0 | 0 | 0 | 35467.922 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | 3.5 | NA | 0% | 100%
86 | TL633 Reconductor (Bernardo Rancho Carmel) |  |  | San Diego, San Diego | The CAISO has approved this reconductor project, which is required to mitigate a projected overload in 2015. In order to accomplish this, the Project will upgrade TL6913 (Poway - Pomerado) and all associated relay and control equipment to achieve a minimum 148 MVA continuous/emergency rating. By reconductoring the existing wire from 1033.5 ACSR/AW to 900 ACSS/AW, the current line rating of 136MW will improve to 174MW. | Transmission Line - Conductor | Upgrade/Retrofit | NA | NA | Load Growth | Line Reconductoring | NA | NA | 2024-01-18 12:00 | 49 | Steady State Power Flow System Analysis | Wires - Reconductor/Line Rebuild Alternative | NA | HFTD Tier 2 | FALSE ¦ FALSE ¦ TRUE | FALSE | NA |  | 2.88 | NA | 69 | NA | 2.1 | 2012-00028-ZZ | QS00069 | 1 | 12139 | NA ¦ NA ¦ NA ¦ NA | FALSE | NA | Work Order Authorization | 2012 | 2012 | FALSE | 2011 ¦ 2012 | NA | https://www.caiso.com/planning/Pages/TransmissionPlanning/2011-2012TransmissionPlanningProcess.aspx | FALSE | NA | NA | Exempted | NA | CPUC | NA | Advice Letter | 2017-11-15 | Approved | 2017 | Operational | NA | 2018-07-09 | 2015-06-01 | 2019-11-07 | Permitting | Land Rights | FALSE | 46190.46 | NA ¦ NA | 48612.9417 | 1102.6842 | 67.1222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2020 ¦ 2021 | 48545.8194 | 67.1222 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
87 | Merchant Switchyard & Merchant Eldorado Transmission |  |  | Nevada | Merchant Switchyard & Merchant Eldorado Transmission | Transmission Line - Multiple | New | New | NA | Load Growth | New T-Line | NA | NA | 2023-04-21 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | TBD |  | NA | 72.12 | 69 ¦500 | NA | 2 | NA | QS00070 | 1 | 12140 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2016-07-22 | Work Order Authorization | 2019 | NA | FALSE | NA | NA | NA | FALSE | TBD | NA | NA | NA | CPUC | NA | NA | NA | Approved | NA | Operational | NA | NA | 2022-12-31 | NA | NA | NA | FALSE | 17134.987 | NA ¦ NA | 15035.1906 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2020 | 15035.1906 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 13.55% | 86.45%
88 | TL636 Wood to Steel Replacement |  |  | San Diego, San Diego | Replacing wood pole with steel equivalent from Northern structure at Z200694 to Elliott Substation. The purpose for this project is for fire hardening of this corridor due to it being within the FTZ and classified as high to extreme fire danger. The project spans approximately 6.07 miles. | Transmission Line - Multiple | Replace | Upgrade/Retrofit | NA | Wildfire Mitigation | Priority 1 Steel Structure Replacement | NA | NA | 2024-01-10 12:00 | 44 | NA | NA | NA | HFTD Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 5.8672 | NA | 69 | NA | 1.2 | 2012-00015-ZZ | QS00071 | 1 | 12144 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2022-07-07 | Work Order Authorization | 2015 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | CPUC | NA | Exempt | NA | NA | NA | Operational | NA | 2022-03-18 | 2022-12-31 | 2022-10-17 | NA | NA | TRUE | 25131.9882 | NA ¦ NA | 21464.2356 | 1057.9842 | 2745.577 | 15752.6745 | 152.8457 | 44.6337 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2022 ¦ 2023 ¦ 2024 | 0 | 0 | 21266.7562 | 152.8457 | 44.6337 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
89 | TL694 Wood to Steel Replacement |  |  | Fallbrook, San Diego ¦ Oceanside, San Diego | This project replaces 4.8 miles, approximately 80 wood structures, to direct-embed and engineered steel poles and replace the existing 636 ASCR/AW conductor to harden the electric transmission and distribution systems and increase reliability in the region. This project will also mitigate some existing access issues to the structures. | Transmission Line - Pole/Tower | Replace | NA | NA | Wildfire Mitigation | T-Line Reliability | NA | NA | 2024-07-22 12:00 | 60 | NA | NA | NA | HFTD Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 4.85 | NA | 69 | NA | 1.2 | 2012-00014-ZZ | QS00073 | 1 | 12149 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-11-06 | Work Order Authorization | 2015 | NA | FALSE | NA | NA | NA | FALSE | TBD | NA | Exempted | NA | NA | NA | Exempt | NA | Approved | 2024 | Permitting | NA | 2025-11-17 | 2020-12-31 | 2027-02-15 | NA | NA | FALSE | 36464.0897 | NA ¦ NA | 27323.8224 | 578.1092 | 720.4648 | 576.5602 | 639.7541 | 1900.449 | 2858.99 | 17470.6425 | 1205.7251 | 0 | 0 | 0 | 5856.676 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | 63.2 | NA | 0% | 100%
90 | TL13831 Wood to Steel Replacement (Talega Racho Mission Viejo) |  |  | Orange County | The purpose of project is to replace approximately 72 wood poles for steel equivalent from Rancho Mission Viejo to Talega Substation for fire hardening. The project spans approximately 6.46 miles. | Transmission Line - Multiple | Replace | Upgrade/Retrofit | NA | Wildfire Mitigation | Priority 1 Wood Structure Replacement | NA | NA | 2024-02-29 | 28 | NA | NA | NA | HFTD Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 6.377 | NA | 138 | NA | 1.2 | 2012-00019-ZZ | QS00074 | 1 | 12150 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-12-05 | Work Order Authorization | 2015 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | CPUC | NA | Exempt | NA | NA | NA | Operational | NA | 2022-08-15 | 2024-12-30 | 2023-04-23 | NA | NA | TRUE | 317.2364 | NA ¦ NA | 21727.4126 | 475.6372 | 2288.5516 | 11949.8744 | 5638.7274 | 82.5889 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 ¦ 2024 | 472.9591 | 2280.3549 | 11932.3906 | 5667.4972 | 82.5889 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
91 | TL13838 Wood to Steel Replacement (Magarita Rancho Mission Viejo) |  |  | Orange County | This project replaces nine poles with steel, approximately 1.4 miles of 1033.5ACSR/AW, insulators and hardware. | Transmission Line - Multiple | Replace | Upgrade/Retrofit | NA | Wildfire Mitigation | Priority 1 Steel Structure Replacement | NA | NA | 2024-02-29 | 28;28;28;7;28;28;28;10;1 | NA | NA | NA | HFTD Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 1.6748 | NA | 138 | NA | 1.2 | 2012-00020-ZZ | QS00075 | 1 | 12152 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-11-06 | Work Order Authorization | 2015 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | CPUC | NA | Exempt | NA | NA | NA | Operational | NA | 2021-09-24 | 2024-12-30 | 2022-01-17 | NA | NA | TRUE | 249.9409 | NA ¦ NA | 2579.386 | 315.7382 | 1149.8398 | 408.9902 | 232.709 | 1.4772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 ¦ 2024 | 315.7382 | 1146.3368 | 412.4949 | 232.709 | 1.4772 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
92 | TL600 Reliability Pole Replacements |  |  | San Diego, San Diego | This project replaces an existing 33 (between Phases 1, 2, and 3) transmission structures on TL600. | Transmission Line - Pole/Tower | Replace | Upgrade/Retrofit | NA | Reliability | T-Line Reliability | NA | NA | 2024-03-12 | 55 | NA | Wires - Reconductor/Line Rebuild Alternative | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 3.9991 | NA | 69 | NA | 4.1 | 2012-00023-ZZ | QS00077 | 1 | 12156 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-10-06 | Work Order Authorization | 2015 | NA | FALSE | NA | NA | NA | FALSE | NA | 2012-01-01 | Exempted | NA | NA | NA | Exempt | NA | Approved | 2018 | Operational | NA | 2013-02-01 | 2021-05-01 | 2022-08-29 | NA | Permitting | TRUE | 1260.0786 | NA ¦ NA | 8712.0498 | 1535.3795 | 1913.5322 | 1043.6201 | 406.0304 | 477.9657 | 403.8122 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2022 ¦ 2023 ¦ 2024 | 0 | 0 | 6109.9589 | 406.0304 | 477.9657 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
93 | [Programmatic] Aerial Marking for Safety |  |  | NA | This project will add aerial marker balls and /or lighting at locations identified by Transmission Engineering, Transmission maintenance personnel, or AL&M support team as safety concerns or necessary for FAA compliance. These locations fall under SDG&E’s expanded aerial lighting and marking policy that seeks to reduce the risk of collisions and improve safety. This will be an ongoing project as Transmission Construction & Maintenance may provide additional locations with safety concerns and for the Aerial Lighting and Marking company initiative. The work includes analyzing current structures for strength and clearance to add marking, replacing structures as necessary, and installing aerial marking and/or lighting. | Transmission Line - Multiple | NA | NA | NA | Safety | T-Line Reliability | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | Multiple | NA | 1.2 | Multiple | QBL0065 | 81 | 12159 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2022-12-09 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Operational | NA | NA | 2023-12-31 | NA | NA | NA | TRUE | NA | NA ¦ NA | 0 | 2549.1466 | 337.9964 | 69.5109 | 9.3215 | -0.34115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 ¦ 2024 | 3236.4467 | 1408.1155 | 75.2202 | 9.3215 | -0.34115 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 13.55% | 86.45%
94 | A ALM TL631 FAA MARKER BAL R2 |  |  | NA | Aerial Lighting and Marking Project to meet FAA Regulations on TL631 | Transmission Line - Pole/Tower | New | NA | NA | Safety | T-Line Reliability | NA | NA | 2024-01-23 | 58 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 69 | NA | NA | NA | 1.2 | ALM-SW | QBL0065 | 1 | 12159 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2018-07-30 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Operational | NA | NA | 2019-12-31 | NA | NA | NA | FALSE | NA | NA ¦ NA | 4356.4169 | 2290.8723 | 361.1757 | 50.3264 | 4.0735 | -0.44925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 | 0 | 4302.4662 | 50.3264 | 4.0735 | -0.44925 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0%
95 | SX PQ 230 kV Line |  |  | San Diego, San Diego | The Proposed Project includes approximately 16.7 linear miles of transmission line as well as associated access roads and work areas, all of which are located primarily within the City of San Diego, a small portion of the City of Poway, and on the extreme northern portion of Marine Corps Air Station (MCAS) Miramar. The Proposed Project will result in a new 230 kV transmission line that will connect the existing Sycamore Canyon and Peñasquitos Substations through utilization of existing SDG&E facilities, ROWs, and City of San Diego franchise position. Segment A - Construction of approximately 8.31 miles of new 230 kV transmission line on new tubular steel poles all within existing SDG&E ROW located between the existing Sycamore Canyon Substation and Carmel Valley Road Segment B - Install new, approximately 2.84-mile 230 kV underground transmission line in Carmel Valley Road utilizing existing franchise position for almost the entire segment Segment C - Install new 230 kV conductor on the existing 230 kV steel structures and one new tubular steel pole all within existing SDG&E ROW located between Carmel Valley Road and Peñasquitos Junction Segment D - Install new 230 kV conductor on existing double-circuit 230 kV steel lattice towers and relocate two existing 69 kV power lines to new tubular steel poles all within existing SDG&E ROW located between the Peñasquitos Junction and the existing Peñasquitos Substation Minor modifications of the existing Sycamore Canyon and Peñasquitos Substations to allow for connection of the new 230 kV transmission line | Transmission Line - Multiple | New | NA | NA | CAISO Transmission Planning Standards [See Notes for NERC Compliance and contingency code, WECC Requirement (and the specific requirement)] | New T-Line | CAISO Requirement | NA | 2024-02-13 12:00 | 55 | Steady State Power Flow System Analysis | Wires - New T-Line Alternative | Multiple Options [See Notes] | HFTD Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 13.3942 | NA | 230 | NA | 2.1 | 2014-00044-ZZ | QS00081 | 1 | 13128 | NA ¦ NA ¦ NA ¦ NA | FALSE | NA | Work Order Authorization | 2013 | 2013 | TRUE | 2013 | NA | https://www.caiso.com/planning/Pages/TransmissionPlanning/2012-2013TransmissionPlanningProcess.aspx | FALSE | Final Certified | 2016-10-13 | EIR | NA | CPUC | NA | CPCN | 2014-04-07 | Approved | 2016 | Operational | NA | 2018-01-11 | 2017-06-01 | 2018-12-03 | Construction Delays | NA | FALSE | 260000 | 260,000 ¦ CPCN | 255981.3002 | 1316.867 | 142.7066 | -0.00046 | -3.8108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 | 1316.867 | 142.7066 | -0.00046 | -3.8108 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0%
96 | TL674A Loop in Del Mar |  |  | Del Mar, San Diego ¦ Solano Beach, San Diego ¦ San Diego, San Diego | Eliminate the need for ongoing O&M work in environmentally sensitive areas (San Dieguito Lagoon, Torrey Pines State Park and Los Penasquitos Lagoon) by removing TL666D from service (Phase IV). Install a new underground 69kV transmission line segment along Via de la Valle, which will provide a new TL connecting the Del Mar Substation to the North City West Substation. This will replace the existing TL 674A tap that will be eliminated in Phase II as part of the Rancho Santa Fe Tap reconfiguration. | Transmission Line - Multiple | Upgrade/Retrofit | Relocate | NA | Reliability | Environmental | NA | NA | 2024-10-07 | NA | Steady State Power Flow System Analysis | Wires - Replacement Alternative | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 7.2489 | NA | 69 | NA | 2.1 | 2013-00010-ZZ | QS00082 | 1 | 13130 | NA ¦ NA ¦ NA ¦ NA | FALSE | NA | Work Order Authorization | 2015 | 2013 | FALSE | 2013 | NA | https://www.caiso.com/planning/Pages/TransmissionPlanning/2012-2013TransmissionPlanningProcess.aspx | FALSE | Final Certified | 2019-03-21 | IS/MND | NA | CPUC | NA | PTC | 2017-06-28 | Approved | 2019 | Operational | NA | 2020-12-30 | 2015-06-01 | 2023-12-15 | Other [See Notes] | NA | TRUE | 17532.6862 | NA ¦ NA | 28122.4858 | 3863.0071 | 3327.1239 | 16089.0943 | 1267.4146 | 240.4434 | -78.5202 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2020 ¦ 2022 ¦ 2023 ¦ 2024 | -0.061572 | 0 | 26693.2096 | 1267.4146 | 240.4434 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [Reason for Change in In-Service Date] In-service dates are estimated during preliminary design and permitting stages of a project; date shifted to reflect actual design and construction schedule.
97 | CBM Gas Breakers |  |  | NA | This project is a continuing effort to sustain GCB SF6 Tracking and implement Condition Based Maintenance by installing monitors on approximately 900 Gas Circuit Breakers (GCBs). | Substation - Circuit Breaker | Upgrade/Retrofit | NA | NA | Reliability | Age/Condition - Replace Breakers | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69 ¦500 | NA | 4.3 | NA | QS00086 | 116 | 13139 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-09-21 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Operational | NA | NA | 2022-12-31 | NA | NA | NA | TRUE | NA | NA ¦ NA | 32650.7492 | 4163.5231 | 5194.7859 | 2671.1227 | 2323.3223 | 1554.0389 | 306.213 | 1347.8866 | 0 | 0 | 0 | 0 | 10237.486 | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 7367.0814 | 3570.9276 | 3687.4676 | 1351.3365 | 10915.3795 | 1347.8866 | 0% | NA ¦ NA | NA ¦ NA | NA | 13.55% | 86.45%
98 | A CBM GCB MONITORING-IMPERIAL VLY |  |  | El Centro, Imperial County | This project is a continuing effort to sustain GCB SF6 Tracking and implement Condition Based Maintenance by installing monitors on Gas Circuit Breakers (GCBs). | Substation - Circuit Breaker | Upgrade/Retrofit | New | NA | Reliability | Age/Condition - Replace Breakers | NA | NA | 2024-10-30 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 500 kV | NA | 4.3 | NA | QS00086 | 1 | 13139 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2014-04-14 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Operational | NA | 2020-12-31 | 2014-12-31 | 2025-12-31 | NA | NA | TRUE | NA | NA ¦ NA | 2285.417 | 885.218 | 364.414 | 521.532 | 348.087 | 164.696 | 0 | 0 | 0 | 0 | 0 | 0 | 2285.417 | NA | NA | 2025 | 0 | 0 | 0 | 0 | 0 | 2285.417 | 0% | NA ¦ NA | NA ¦ NA | NA | 13.55% | 86.45%
99 | A CBM GCB MONITORING-PENASQUITOS |  |  | San Diego County | This project is a continuing effort to sustain GCB SF6 Tracking and implement Condition Based Maintenance by installing monitors on Gas Circuit Breakers (GCBs). | Substation - Circuit Breaker | Upgrade/Retrofit | New | NA | Reliability | Age/Condition - Replace Breakers | NA | NA | 2024-10-09 | NA | NA | NA | NA |  | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 230 ¦ 138 ¦ 69 | NA | 4.3 | NA | QS00086 | 1 | 13139 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2014-05-13 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Operational | NA | 2020-01-31 | 2022-07-25 | 2022-07-25 | NA | NA | FALSE | NA | NA ¦ NA | 1463.295 | 209.361 | 981.054 | 129.245 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2022 | 0 | 0 | 1463.295 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 13.55% | 86.45%
100 | A CBM GCB VARIOUS SUBS |  |  | NA | This project is a continuing effort to sustain GCB SF6 Tracking and implement Condition Based Maintenance by installing monitors on Gas Circuit Breakers (GCBs). | Substation - Circuit Breaker | Upgrade/Retrofit | New | NA | Reliability | Age/Condition - Replace Breakers | NA | NA | NA | NA | NA | NA | NA |  | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | NA | NA | 4.3 | NA | QS00086 | 1 | 13139 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-11-30 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Canceled | NA | NA | 2022-12-31 | NA | NA | NA | TRUE | NA | NA ¦ NA | 4373.977 | 615.109 | 1076.84 | 790.981 | 841.329 | 503.205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2024 | 0 | 0 | 0 | 0 | 4373.977 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 13.55% | 86.45%
101 | Kearny Rebuild |  |  | San Diego, San Diego | The Kearny Substation rebuild will consist of relocating the existing installation to the west side of the Kearny facility on a larger and more suitable location to accommodate a low profile 120MVA substation. The relocation will be on the existing Kearny facility property zoned for utility use, and therefore will not be subject to any permits. It will be rebuilt on the site once utilized by transformer oil tanks, in the southwest corner of the Kearny facility. This site will allow space for all required expansion to meet existing and projected electric distribution load growth and the ultimate arrangement will allow for feeds to existing generators and proposed battery storage area. It is anticipated that the rebuild will improve Kearny’s reliability by 98%. The ultimate arrangement of the substation will consist of five 69kV bays consisting of five 69 kV TL breakers, one 69kV bus tie breaker, four 69 kV bank breakers, one 69kV ground bank and associated breaker, four 30 MVA 69/12 kV low profile transformers, four ¼ sections of switchgear, four 12 kV capacitors, one new control shelter, new relaying, SCADA, five 69 kV transmission lines, and sixteen distribution circuits. | Substation - Multiple | Upgrade/Retrofit | New | NA | Reliability | Substation Reliability | NA | NA | 2024-09-12 | 21; 60; 55; 60; 56; 55; 56; 41; 56; 21; 21; 16 | NA | Wires - New Substation Alternative | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.12046 | NA | 69 | 120MVA | 4.1 | 2014-00210-ZZ | QS00087 | 1 | 13242 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2018-04-22 | Work Order Authorization | 2015 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | 2017-11-06 | 2019-06-27 | 2020-01-10 | NA | NA | FALSE | NA | NA ¦ NA | 20998.2306 | 217.4385 | 14.8608 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2020 ¦ 2021 | 217.4385 | 14.8608 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
102 | Streamview |  |  | San Diego, San Diego | Initially expand the existing 69 ¦12 kV substation from two to three banks to increase capacity on the system, with future expansion to four banks. Scope to construct a new 69 kV tie line between the Station F Substation and the Streamview Substation within an existing transmission corridor has been REMOVED. | Transmission Line/Substation | Upgrade/Retrofit | New | NA | Reliability | Age/Condition | NA | NA | 2024-10-09 | 21; 54; 21; 52;6; 2 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 0.38816 | 69 | 12kV ¦69kV ¦28MVA | 4.2 | 2014-00062-ZZ | QS00089 | 1 | 13244 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-12-12 | Work Order Authorization | 2015 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | Categorical Exclusion | CPUC | NA | Exempt | 2020-11-30 | NA [See Notes] | 2020 | Construction (under 10%) | NA | 2020-03-11 | 2021-09-30 | 2014-02-12 | NA | NA | TRUE | 543 | NA ¦ NA | 47990.1048 | 1552.0545 | 761.4417 | 3181.6008 | 2184.3822 | 8928.9482 | 4626.3797 | 11386.8081 | 9200.3659 | 811.3345 | 0 | 0 | 18690.17 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2025 | 0 | 3622.8086 | 299.6637 | 33.7723 | 0 | 33930.4268 | 0% | NA ¦ NA | 2.1 | NA | 0% | 100% | [CPUC Status] Exempt
103 | Suncrest SVC Interconnection |  |  | San Diego County | In the draft 2013-2014 Transmission Plan, the CAISO has identified a potential policy driven need for installation of a synchronous condenser facility or SVC at the 230kV bus within Suncrest Substation. The preferred alternative will add one +320/-100 MVAr SVC at the Suncrest Substation 230kV bus. SDGE is required to submit a bid to the CAISO by Monday, June 16, 2014 to compete for the right to engineer, procure, and construct an SVC facility connected at the 230kV Suncrest bus. SDGE submitted the bid for Suncrest Substation as requested by the CAISO on June 16, 2014. SDGE submitted a response on July 22, 2014 to the deficiency letter received from the CAISO. An additional follow up request was submitted to the CAISO on August 15, 2014 as part of the CAISO's project qualification process. On September 9, 2014 SDGE was identified by the CAISO as being a qualified project sponsor for the Suncrest policy driven project. | Substation - Voltage Support Equipment | NA | NA | NA | CAISO Transmission Planning Standards [See Notes for NERC Compliance and contingency code, WECC Requirement (and the specific requirement)] | Load Interconnection | CAISO Requirement | NA | 2024-10-09 | NA | Interconnection System Impact/Facilities Studies | Wires - Voltage Support/Reactive Support Alternative | NA | HFTD Tier 3 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 40.9412 | 230 | 300MVA | 2.1 | 2021-2075 | QS00098 | 1 | 14126 | NA ¦ NA ¦ NA ¦ NA | FALSE | NA | Work Order Authorization | 2015 | 2014 | TRUE | 2014 | NA | https://www.caiso.com/planning/Pages/TransmissionPlanning/2013-2014TransmissionPlanningProcess.aspx | FALSE | NA | NA | NA | NA | NA | NA | CPCN | 2019-07-12 | Approved | 2018 | Operational | NA | 2019-05-28 | 1905-07-09 | 2020-02-25 | Permitting | Land Rights | TRUE | 798 | NA ¦ NA | 3718.5085 | 497.4985 | 28.9237 | 0 | 0 | -2.9133 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2020 ¦ 2021 ¦ 2024 | 3672.828 | 28.9237 | 0 | 0 | -2.9133 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0%
104 | Artesian 230kV Sub Expansion |  |  | San Diego, San Diego | Per the CAISO 2013-2014 Final Plan, SDG&E will expand the existing 69 ¦12kV Artesian Substation to a 230 ¦69 ¦12kV Substation (Artesian East Substation) to alleviate the existing 69kV congestion at Sycamore Canyon Substation. In addition, the Proposed Project will help mitigate Cat B contingencies and increase reliability to the Poway Area Load Pocket which is expected to grow by as much as 12% in the next 10 years. The Proposed Project will be built on existing SDG&E Artesian Substation land and adjacent land east of the current substation site, also owned by SDG&E (pending final sale negotiations). Transmission work includes the loop-in of TL23051 (SX-PEN), terminating TL616C into the Artesian 69kV substation to form two (2) 69 kV Artesian - Bernardo lines; reconductoring both Artesian - Bernardo lines to achieve a 145 ¦179 rating (TL6939 & segment of TLNew), and replacing underground getaways at Artesian, Bernardo, Rancho Carmel, and Poway to achieve new ratings. Permitting and Environmental will be required for the expanded 230 ¦69 ¦12kV substation, in addition to the reconductor work associated with the project. Requested ISD of the ISO is June 2016, however the team proposes and ISD of December 2018 depending on application filing, and receipt of approval from the Commission. | Substation - Multiple | Upgrade/Retrofit | NA | NA | Reliability | Substation Capacity | NERC TPL Standards | NA | 2024-10-03 | 21;21;21;15;23;15;23;15;23;15;15 | Steady State Power Flow System Analysis | Wires - Bus Upgrade Alternative | NA | HFTD Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 1.9377 | 230 | 69kV ¦230kV ¦224MVA | 2.1 | 2014-00056-ZZ | QS00099 | 1 | 14128 | NA ¦ NA ¦ NA ¦ NA | FALSE | NA | Work Order Authorization | 2015 | 2014 | FALSE | 2014 | NA | https://www.caiso.com/planning/Pages/TransmissionPlanning/2013-2014TransmissionPlanningProcess.aspx | FALSE | Final Certified | 2019-03-22 | IS/MND | NA | CPUC | NA | PTC | 2019-10-07 | Approved | 2020 | Operational | NA | 2020-04-17 | 2016-06-01 | 2020-05-21 | Permitting | Construction Delays | TRUE | 17140 | NA ¦ NA | 132082.049 | 42618.5685 | 32690.8213 | 20376.5233 | 1653.6356 | 560.803 | 951.7651 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 | 0 | 50361.7741 | 74652.8038 | 1653.6356 | 560.803 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0%
105 | TL6975 Escondido San Marcos |  |  | San Marcos, San Diego ¦ Carlsbad, San Diego ¦ Lake San Marcos, San Diego ¦ Escondido, San Diego | Segment 1: Rebuild approximately 1.8 miles of an existing 69kV circuit (TL 680C) to create a double circuit from San Marcos Substation to Melrose Tap. Construction at San Marcos Substation including installation of a new circuit breaker par, seven piers, and an A-frame for the new line. Along Segment 1, all wood pole structures would be replaced with steel poles; porcelain insulators would be replaced with polymer insulators. Segment 2: Construct 2.8 miles of new single-circuit 69kV overhead power line on new steel poles in the existing transmission corridor from Melrose Tap to Meadowlark Junction adjacent to existing TL 13811/13825 power line, approximately 50-feet east of the centerline of the existing structures. Segment 3: Transition new line (described under Segment 2, above) and reconductor approximately 7.4 miles of power line; remove and replace existing copper conductors with new 636 ACSS/AW conductors and existing porcelain insulators with polymer insulators; construction at the existing Escondido Substation to accommodate new circuit. | Transmission Line - Multiple | New | NA | NA | Load Growth | New T-Line | NERC TPL Standards | NA | 2024-05-06 12:00 | 55 | Steady State Power Flow System Analysis | Wires - New T-Line Alternative | NA | HFTD Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 11.9036 | NA | 69 | 69kV | 2.1 | 2014-00078-ZZ | QS00101 | 1 | 14137 | NA ¦ NA ¦ NA ¦ NA | FALSE | NA | Work Order Authorization | 2015 | 2014 | FALSE | 2014 | NA | https://www.caiso.com/planning/Pages/TransmissionPlanning/2013-2014TransmissionPlanningProcess.aspx | FALSE | NA | NA | NA | NA | NA | NA | PTC | 2017-11-15 | Approved | 2021 | Operational | NA | 2021-10-19 | 2015-06-01 | 2023-02-28 | Permitting | Land Rights | TRUE | 10,000 ¦ 100,000 | NA ¦ NA | 52142.981 | 1799.1409 | 9221.2832 | 32210.4332 | 2820.3867 | 1585.4914 | 85.8581 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 | 0 | 529.1659 | 332.0915 | 49610.3741 | 1585.4914 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
106 | TL698 Wood to Steel Replacement (Monserate Avocado) |  |  | Fallbrook, San Diego | The TL698 Fire Hardening & Reconductor Project consists of replacing existing structures and installing new steel structures along the 69kV tie line 698 in FTZ from Z10213, north of Monserat Substation, to structure Z293941, south of Avocado Substation, with new light duty and heavy engineered steel poles. This project is needed to mitigate loss of service due to wildfires by replacing existing wood poles with new steel structures. The new steel poles shall be designed to 138kV specifications and accommodate existing and future 12kV distribution underbuild and communications circuits. TL698 is located within existing easements. TL698 will be designed for (3)-636 ACSS/AW conductors and the existing 336 ACSR/AW conductors will be retired. There will be one SDG&E 96-count ADSS and one position for a third party installed along the line from Z10212 to Z293941. | Transmission Line - Pole/Tower | Replace | NA | NA | Wildfire Mitigation | T-Line Reliability | NA | NA | 2024-02-22 | 44 | NA | NA | NA | HFTD Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 4.2938 | NA | 69 | NA | 1.2 | 2014-00009-ZZ | QS00103 | 1 | 14140 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-08-19 | Work Order Authorization | 2015 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | NA | NA | Exempt | NA | NA | NA | Construction (under 10%) | NA | 2023-11-01 | 2020-12-31 | 2024-08-23 | NA | NA | TRUE | 431.4964 | NA ¦ NA | 20748.131 | 504.9733 | 525.7454 | 1287.7238 | 5494.102 | 10074.7578 | 619.2764 | 1232.8193 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 0 | 2039.4517 | 1287.3471 | 3337.4987 | 12231.7378 | 1852.0957 | 0% | NA ¦ NA | 15.5 | NA | 0% | 100% | [Last Inspection] TL energized 2023-02-28
107 | Poway 69kV Substation Rebuild |  |  | Poway, San Diego | The purpose of this project is to rebuild Poway Substation to a low profile distribution substation with an ultimate capacity of 120MVA. The current substation consists of aging infrastructure, no SCADA control, and a control shelter that cannot accommodate new panels for any SCADA upgrades. Adding SCADA control and replacing old equipment will increase the reliability of this sub and allow room for any future expansion. Substation, Transmission, and Distribution work are required for this rebuild. Installing SCADA to Poway Sub will increase reliability by giving Mission Control remote access to operate the equipment. Replacing aging infrastructure also increases reliability. Building a new control shelter allows for any future expansion. | Substation - Multiple | Upgrade/Retrofit | Removal | NA | Reliability | Age/Condition | NA | NA | 2024-09-12 | 24; 31; 47; 31; 48; 50 | NA | Wires - Minimum Required Scope (spot repair) Alternative | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 0.36956 | 69 | 120MVA | 4.1 | 2017-0095 | QS00104 | 1 | 14143 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-04-22 | Work Order Authorization | 2015 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | 2015-10-26 | 2023-03-31 | 2018-11-06 | NA | NA | TRUE | 1727.9587 | NA ¦ NA | 21954.3998 | 84.0961 | 389.6282 | 804.5641 | 10.3026 | -16.3174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 ¦ 2024 | -40.9568 | 2.4422 | 1398.6141 | 10.3026 | -16.3174 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
108 | HATS Legacy Work Order |  |  | San Diego County | Obtain the necessary permits, environmental clearance and regulatory authority for the helicopter landing areas along our transmission system. Relocate approximately 6 existing Sunrise Tower Staging Access Pads (TSAP) to locations that are better suited for TCM's O&M requirements. Build platforms at approximately 12 of the TSAPs and create 8 new TSAPs at tower locations to ensure safer and more secure landing areas for TCM. Establish approximately 15 permanent staging/fly yard locations, one acre or less in size, at locations along Sunrise that will best meet TCM's needs. Many of these will be at the same fly yard locations utilized for construction of Sunrise. | Other | New | NA | NA | Other [See Notes] | Safety - Line Right of Way Access | NA | NA | NA | 44 | NA | NA | NA | HFTD Tier 3 ¦ Zone 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 230 ¦500 | NA | 1.3 | 2014-00060-ZZ | QS00105 | 1 | 14145 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-01-27 | Work Order Authorization | 2015 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | 2019-06-24 | 2021-12-31 | 2021-07-16 | Construction Delays | NA | FALSE | 499 | NA ¦ NA | 15086.375 | 6520.2526 | 4215.1246 | -185.8243 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2020 ¦ 2021 ¦ 2022 | 11057.0747 | 4215.1246 | -185.8243 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0% | [Primary Purpose] Remote access landing pads for transmission structures
109 | [Programmatic] CAST Security Upgrades |  |  | NA | CAST is an ongoing program that addresses security for critical substation assets. | Substation - Other Equipment | New | NA | NA | Physical Security | Security Upgrades | NERC CIP Compliance | Other [See Notes] | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | Multiple | 230kV ¦500kV | 1.2 | Multiple | QBL0020 | 48 | 15125 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-11-28 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Operational | NA | NA | 2024-12-31 | NA | NA | NA | TRUE | 216954.9592 | NA ¦ NA | 0 | 981.0616 | 291.5595 | 311.1844 | -1240.5797 | 4.5778 | 0 | 0 | 0 | 0 | 0 | 0 | 54.7492 | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 ¦ 2024 | 3508.9436 | 52.0315 | 38.089 | -727.9563 | 4.5778 | 0 | 0% | NA ¦ NA | 8.4 | NA | 100% | 0% | [NERC / WECC / CAISO Standard / Requirement / Contingency 2 ] NERC CIP Compliance and Security Assessments
110 | A CAST PENASQUITOS (PQ) |  |  | San Diego, San Diego | Physical security hardening | Other - Physical Security | New | NA | NA | Physical Security | Security Upgrades | NERC CIP Compliance | Other [See Notes] | 2024-10-09 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 13.94 | 231 ¦500 | 230kV ¦500kV | 1.2 | 2023-3286 | QBL0020 | 1 | 15125 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2022-07-26 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | TBD | NA | NA | NA | Construction (over 75%) | NA | 2023-05-30 | 2024-12-31 | 2024-08-16 | NA | NA | TRUE | NA | NA ¦ NA | 18991.6012 | 0 | 0 | 1667.5722 | 9071.5199 | 7991.7973 | 260.7117 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2024 | 0 | 0 | 0 | 0 | 18730.8895 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0% | [NERC / WECC / CAISO Standard / Requirement / Contingency 2 ] NERC CIP Compliance and Security Assessments [Age of Asset] Unable to provide age of asset for Programmatic budget codes
111 | A CAST EAST CO SUB PERIMETER |  |  | San Diego County | Physical security hardening | Other - Physical Security | New | NA | NA | Physical Security | Security Upgrades | NERC CIP Compliance | Other [See Notes] | 2024-10-21 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 66.56 | 232 ¦500 | 230kV ¦500kV | 1.2 | 2021-2561 | QBL0020 | 1 | 15125 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-12-27 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | 2021-08-20 | 2021-12-31 | 2022-12-22 | NA | NA | TRUE | NA | NA ¦ NA | 31558.0535 | 0 | 13896.3193 | 17555.2216 | 80.7694 | 25.7432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2022 ¦ 2023 ¦ 2024 | 0 | 0 | 31451.5408 | 80.7694 | 25.7432 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0% | [NERC / WECC / CAISO Standard / Requirement / Contingency 2 ] NERC CIP Compliance and Security Assessments
112 | A CAST SYCAMORE CANYON |  |  | San Diego County | Physical security hardening | Other - Physical Security | New | NA | NA | Physical Security | Security Upgrades | NERC CIP Compliance | Other [See Notes] | 2024-10-03 | NA | NA | NA | NA | HFTD Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 10.79 | 233 ¦500 | 230kV ¦500kV | 1.2 | 2023-3284 | QBL0020 | 1 | 15125 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2022-09-22 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | TBD | NA | NA | NA | Operational | NA | 2023-09-15 | 2024-01-31 | 2024-06-21 | NA | NA | TRUE | NA | NA ¦ NA | 14092.1965 | 0 | 0 | 864.9117 | 6654.1274 | 6573.1574 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2024 | 0 | 0 | 0 | 0 | 14092.1965 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0% | [NERC / WECC / CAISO Standard / Requirement / Contingency 2 ] NERC CIP Compliance and Security Assessments
113 | A CAST MISSION FRONT ENTRANCE |  |  | San Diego, San Diego | Physical security hardening | Other - Physical Security | New | NA | NA | Physical Security | Security Upgrades | NERC CIP Compliance | Multiple Options [See Notes] | 2024-10-30 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 9 | 236 ¦500 | 230kV ¦500kV | 1.2 | 2022-2976 | QBL0020 | 1 | 15125 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-12-28 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | TBD | NA | NA | NA | Construction (over 75%) | NA | 2022-08-22 | 2024-12-31 | 2024-12-20 | NA | NA | TRUE | NA | NA ¦ NA | 24458.8031 | 0 | 772.6935 | 2301.7353 | 7337.3744 | 6477.3126 | 5499.5996 | 2070.0877 | 0 | 0 | 0 | 0 | 20110.693 | NA | NA | 2025 | 0 | 0 | 0 | 0 | 0 | 2070.0877 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0% | [NERC / WECC / CAISO Standard / Requirement / Contingency 2 ] NERC CIP Compliance and Security Assessments
114 | A CAST GUARD SHELTER REBUILD |  |  | NA | Physical security hardening | Other - Physical Security | New | NA | NA | Physical Security | Security Upgrades | NERC CIP Compliance | Other [See Notes] | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 237 ¦500 | 230kV ¦500kV | 1.2 | 2023-3287 | QBL0020 | 1 | 15125 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2022-08-15 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Operational | NA | NA | 2023-12-31 | NA | NA | NA | TRUE | NA | NA ¦ NA | 6619.5956 | 0 | 0 | -5.4329 | 5728.1337 | 903.0409 | -6.1462 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2023 ¦ 2024 | 0 | 0 | 0 | 5722.7008 | 903.0409 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0% | [Last Inspection] The project replaced guard shelters. [NERC / WECC / CAISO Standard / Requirement / Contingency 2] NERC CIP Compliance and Security Assessment [Age of Asset] Fence upgrade. No asset IDs.
115 | A CAST IMPERIAL VLLY SUBS PERIMET |  |  | Imperial County | Physical security hardening | Other - Physical Security | New | NA | NA | Physical Security | Security Upgrades | NERC CIP Compliance | Other [See Notes] | 2024-10-30 | NA | NA | NA | NA | HFTD Tier 3 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 55.48 | 255 ¦500 | 230kV ¦500kV | 1.2 | 2021-2097 | QBL0020 | 1 | 15125 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-08-20 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Operational | NA | 2020-10-19 | 2021-12-31 | 2021-08-31 | NA | NA | FALSE | NA | NA ¦ NA | 20699.222 | 5414.1156 | 15252.6844 | 26.6981 | 5.724 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 | 0 | 20666.7999 | 26.6981 | 5.724 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0% | [NERC / WECC / CAISO Standard / Requirement / Contingency 2 ] TECO/Closed WO replaced by project WO above
116 | A CAST OCOTILLO |  |  | Imperial County | Physical security hardening | Other - Physical Security | New | NA | NA | Physical Security | Security Upgrades | NERC CIP Compliance | Other [See Notes] | 2024-10-24 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 28.98 | 240 ¦500 | 230kV ¦500kV | 1.2 | 2022-2977 | QBL0020 | 1 | 15125 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2022-02-08 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | TBD | NA | NA | NA | Construction (over 75%) | NA | 2023-10-09 | 2023-12-31 | 2024-12-20 | NA | NA | TRUE | NA | NA ¦ NA | 14090.5616 | 0 | 0 | 70.8717 | 5204.6986 | 6211.5497 | 1522.8467 | 1080.5949 | 0 | 0 | 0 | 0 | 12133.363 | NA | NA | 2025 | 0 | 0 | 0 | 0 | 0 | 1080.5949 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0% | [NERC / WECC / CAISO Standard / Requirement / Contingency 2] NERC CIP Compliance and Security Assessments
117 | A CAST SUNCREST SUB PERIMETER |  |  | San Diego County | Physical security hardening | Other - Physical Security | New | NA | NA | Physical Security | Security Upgrades | NERC CIP Compliance | Other [See Notes] | 2024-10-09 | NA | NA | NA | NA | HFTD Tier 3 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 40.94 | 241 ¦500 | 230kV ¦500kV | 1.2 | 2022-2929 | QBL0020 | 1 | 15125 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-12-29 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | TBD | NA | NA | NA | Operational | NA | 2022-05-31 | 2020-12-31 | 2023-07-21 | NA | NA | TRUE | NA | NA ¦ NA | 29470.8094 | 0 | 5938.8692 | 11745.8702 | 7885.8844 | 3934.8213 | -34.6357 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2023 ¦ 2024 | 0 | 0 | 0 | 25570.6238 | 3934.8213 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0% | [NERC / WECC / CAISO Standard / Requirement / Contingency 2 ] NERC CIP Compliance and Security Assessments
118 | A MIGUEL 230KV PHYSICAL SECURITY |  |  | San Diego County | Physical security hardening | Other - Physical Security | New | NA | NA | Physical Security | Security Upgrades | NERC CIP Compliance | NA | 2024-10-22 | NA | NA | NA | NA | HFTD Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 12.37 | 242 ¦500 | 230kV ¦500kV | 1.2 | 2019-1002 | QBL0020 | 1 | 15125 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2018-10-24 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Operational | NA | 2019-04-02 | 2019-04-01 | 2019-12-31 | NA | NA | FALSE | NA | NA ¦ NA | 8980.1346 | 188.0311 | 2.8375 | 1.1318 | 237.1123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 | 8739.0531 | 2.8375 | 1.1318 | 237.1123 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0%
119 | A MIGUEL 500KV PHYSICAL SECURITY |  |  | San Diego County | Physical security hardening | Other - Physical Security | New | NA | NA | Physical Security | Security Upgrades | NERC CIP Compliance | NA | 2024-10-22 | NA | NA | NA | NA | HFTD Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 12.37 | 243 ¦500 | 230kV ¦500kV | 1.2 | 2014-00595-ZZ | QBL0020 | 1 | 15125 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2018-10-24 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | 2018-09-24 | 2019-04-01 | 2020-06-30 | NA | NA | FALSE | NA | NA ¦ NA | 13746.8048 | 4603.7891 | 39.1357 | 0.64443 | 1.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 | 13705.5947 | 39.1357 | 0.64443 | 1.43 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0%
120 | A CAST SECURITY VARIOUS SUBS |  |  | NA | Closed order | Other - Physical Security | New | NA | NA | Physical Security | Security Upgrades | NERC CIP Compliance | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 244 ¦500 | 230kV ¦500kV | 1.2 | NA | QBL0020 | 1 | 15125 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2018-04-25 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Canceled | NA | NA | 2019-12-31 | NA | NA | NA | TRUE | NA | NA ¦ NA | 3274.9228 | 577.0856 | 634.3393 | 53.9794 | 0.08947 | 0.40581 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 | 0 | 3220.4482 | 53.9794 | 0.08947 | 0.40581 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0%
121 | A CAST TALEGA |  |  | San Clemente, San Diego | Physical security hardening | Other - Physical Security | New | NA | NA | Physical Security | Security Upgrades | NERC CIP Compliance | Other [See Notes] | 2024-10-24 | NA | NA | NA | NA | HFTD Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 6.2 | 234 ¦500 | 230kV ¦500kV | 1.2 | 2024-3902 | QBL0020 | 1 | 15125 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-08-24 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Planning | NA | 2023-03-14 | 2015-03-31 | 2025-10-31 | NA | NA | TRUE | NA | NA ¦ NA | 14941.9262 | 0 | 0 | 0 | 0.21244 | 39.3918 | 2134.264 | 12768.0579 | 0 | 0 | 0 | 0 | 1075.558 | NA | NA | 2025 | 0 | 0 | 0 | 0 | 0 | 14941.9262 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0% | [NERC / WECC / CAISO Standard / Requirement / Contingency 2 ] NERC CIP Compliance and Security Assessments
122 | A CAST OTAY MESA |  |  | Otay Mesa, San Diego | Physical security hardening | Other - Physical Security | New | NA | NA | Physical Security | Security Upgrades | NERC CIP Compliance | Other [See Notes] | 2024-10-25 | NA | NA | NA | NA | HFTD Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 4 | 239 ¦500 | 230kV ¦500kV | 1.2 | 2024-3903 | QBL0020 | 1 | 15125 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2022-02-08 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Engineering less than 50% complete | NA | 2023-03-14 | 2023-12-31 | 2024-11-27 | NA | NA | FALSE | NA | NA ¦ NA | 2837.7428 | 0 | 0 | 0 | 0.0713 | 1035.7355 | 1801.936 | 0 | 0 | 0 | 0 | 0 | 1892.853 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0% | [NERC / WECC / CAISO Standard / Requirement / Contingency 2 ] NERC CIP Compliance and Security Assessments
123 | A CAST SAN LUIS REY |  |  | Oceanside, San Diego | Physical security hardening | Other - Physical Security | New | NA | NA | Physical Security | Security Upgrades | NERC CIP Compliance | Other [See Notes] | 2024-10-18 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 7.4 | 235 ¦500 | 230kV ¦500kV | 1.2 | 2024-3904 | QBL0020 | 1 | 15125 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-03-18 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Planning | NA | 2023-03-14 | 2026-01-31 | 2026-06-30 | NA | NA | FALSE | NA | NA ¦ NA | 26692.8323 | 0 | 0 | 0 | 0 | 41.7498 | 8.8653 | 8800.4633 | 17841.754 | 0 | 0 | 0 | 41.7498 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0% | [NERC / WECC / CAISO Standard / Requirement / Contingency 2 ] NERC CIP Compliance and Security Assessments
124 | Rancho Santa Fe Substation Fire Hardening |  |  | Rancho Santa Fe, San Diego | Replace approximately one (1) mile of direct-buried cable along Old Seaworld Drive to a new 69kV duct package infrastructure relocated onto Sea World Drive. | Substation - Multiple | Upgrade/Retrofit | NA | NA | Reliability | Substation Reliability | NA | NA | 2024-09-12 | 65; 70; 62 | NA | Wires - Minimum Required Scope (spot repair) Alternative | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.12094 | NA | 69 | 69kV | 1.2 | 2014-00289-ZZ | QS00123 | 1 | 15246 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-04-21 | Work Order Authorization | 2015 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | 2017-07-10 | 2020-11-18 | 2020-11-18 | NA | NA | FALSE | 5719.0763 | NA ¦ NA | 7937.0511 | 3095.1826 | 1461.0882 | 8.9299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2020 ¦ 2021 ¦ 2022 | 208.2046 | 7548.5966 | 8.9299 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
125 | Mid Coast Trolley Electric |  |  | San Diego, San Diego | Mid-Coast: As part of SANDAG's Mid Coast Trolley Extension Project, SDG&E will be relocating multiple electric and gas services from the Santa Fe Depot in downtown San Diego to the University City community. | Transmission Line - Multiple | Relocate | NA | NA | Work Requested by Others | Facility Relocation | NA | NA | 2024-03-12 | 18 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 4.2125 | NA | 69 | NA | 3.1 | 2015-00016 | QS00125 | 1 | 15258 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-12-05 | Work Order Authorization | 2017 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | CPUC | NA | Exempt | NA | NA | NA | Operational | NA | 2016-10-03 | 2022-02-03 | 2022-08-07 | NA | NA | TRUE | 8347.5827 | NA ¦ NA | 7398.3173 | 624.5146 | 1272.7225 | 2232.3897 | 392.8702 | 5.7645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 ¦ 2024 | 618.849 | 165.6965 | 3503.5331 | 392.8702 | 5.7645 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
126 | [Programmatic] Advanced Protection |  |  | NA | Replaces aging circuit breakers and/or obsolete electromechanical relays, to create a more comprehensive protection system by taking advantage of newer field technologies under installation by the FiRM program, and to create visibility in fire threat areas with installation of Distribution SCADA. Adding distribution SCADA and replacing obsolete distribution relays and aging equipment. Improve distribution reliability and improve fire safety. | Substation - Multiple | Upgrade/Retrofit | NA | NA | Wildfire Mitigation | SCADA Switch Installation | NERC CIP Compliance | NA | NA | NA | NA | NA | NA | HFTD Tier 2 ¦ HFTD Tier 3 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | NA | NA | Multiple | 120MVA | 1.1 | Multiple | QBL0071 | 82 | 15259 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-11-30 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | NA | 2024-12-31 | NA | NA | NA | TRUE | NA | NA ¦ NA | 0 | 1156.8405 | 754.289 | 1689.5478 | 1392.0601 | 1701.0572 | 318.0451 | 63.9509 | 3145.1416 | 0 | 0 | 0 | 4772.7807 | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 89.7673 | 545.0247 | 849.8923 | 1421.7088 | 259.2645 | 893.1451 | 0% | NA ¦ NA | 5.4 | NA | 0% | 100%
127 | A APP WMP: BORDER SUBSTATION |  |  | San Diego, San Diego | Replace existing oil circuit breakers with vacuum, upgrade RTU and associated relay equipment. | Substation - Multiple | Upgrade/Retrofit | NA | NA | Wildfire Mitigation | Install SCADA/RTU | NA | NA | 2024-10-25 | NA | NA | NA | NA | HFTD Tier 2 ¦ HFTD Tier 3 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | NA | 0.94 | 69 | NA | 1.1 | 2021-2054 | QBL0071 | 1 | 15259 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2021-02-18 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Construction (over 75%) | NA | 2022-05-18 | 2022-12-31 | 2024-04-23 | NA | NA | TRUE | NA | NA ¦ NA | 1305.1294 | 0 | 98.5274 | 618.9882 | 539.5663 | 48.0474 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2024 | 0 | 0 | 0 | 0 | 1305.1294 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [Age of Asset] Project completed, age of previous asset(s) unknown.
128 | A APP WMP: PALA SUBSTATION |  |  | San Diego County | Replace existing relays and RTU, other supporting equipment. | Substation - Multiple | Upgrade/Retrofit | NA | NA | Wildfire Mitigation | Install SCADA/RTU | NA | NA | 2024-10-16 | NA | NA | NA | NA | HFTD Tier 3 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | NA | 0.84 | 69 | NA | 1.1 | 2021-2316 | QBL0071 | 1 | 15259 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2021-02-16 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Construction (50%-75%) | NA | 2023-05-08 | 2022-12-31 | 2025-01-06 | NA | NA | FALSE | NA | NA ¦ NA | 1244.9729 | 0 | 0 | 3.8588 | 762.793 | 469.3857 | 8.9353 | 0 | 0 | 0 | 0 | 0 | 1245.129 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
129 | A CAMERON ADD 69KV BUS TIE |  |  | San Diego County | Add 69kV bus tie circuit breaker, conductor and associated equipment. | Substation - Circuit Breaker | Upgrade/Retrofit | NA | NA | Wildfire Mitigation | Bus Upgrade | NA | NA | 2024-09-18 | NA | NA | NA | NA | HFTD Tier 3 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | NA | NA | 69 | NA | 1.1 | 2014-01075-ZZ | QBL0071 | 1 | 15259 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2018-03-14 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | 2020-12-07 | 2019-03-01 | 2021-11-01 | NA | NA | FALSE | NA | NA ¦ NA | 3433.348 | 833.7241 | 2084.9862 | 10.2088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 | 0 | 3423.1392 | 10.2088 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [Age of Asset] New asset installed, no previous asset
130 | A SANTA YSABEL 69KV REBUILD |  |  | San Diego County | Replace existing 69kV bus, circuit breaker, and control shelter. | Substation - Multiple | Upgrade/Retrofit | NA | NA | Wildfire Mitigation | Bus Upgrade | NA | NA | 2024-10-28 | 53 | NA | NA | NA | HFTD Tier 3 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | NA | NA | 69 | NA | 1.1 | 2019-0222 | QBL0071 | 1 | 15259 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2018-03-14 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | 2020-08-31 | 2019-06-01 | 2023-03-23 | NA | NA | TRUE | NA | NA ¦ NA | 10304.2741 | 3353.2363 | 3052.3057 | 1859.5361 | 840.3981 | 16.5299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2023 ¦ 2024 | 0 | 0 | 0 | 10287.7442 | 16.5299 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
131 | A WMP APP DESCANSO BK30 & YARD |  |  | San Diego County | Replace bank xfmr, extend yard for access. | Substation - Multiple | Upgrade/Retrofit | NA | NA | Wildfire Mitigation | Replace Transformer | NA | NA | 2024-09-19 | 43 | NA | NA | NA | HFTD Tier 3 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | NA | 0.34 | 69 | NA | 1.1 | 2021-2202 | QBL0071 | 1 | 15259 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-12-18 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | 2022-08-01 | 2021-10-30 | 2023-11-18 | NA | NA | TRUE | NA | NA ¦ NA | 4368.0021 | 3.2363 | 159.9943 | 2247.369 | 1727.4986 | 229.9039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2023 ¦ 2024 | 0 | 0 | 0 | 4138.0982 | 229.9039 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
132 | A JAMACHA SUB 69KV & 12KV REBUILD |  |  | La Mesa, San Diego | 69/12kV Rebuild. | Substation - Multiple | Upgrade/Retrofit | NA | NA | Wildfire Mitigation | System Design Upgrade | NA | NA | 2024-10-01 | 52 | NA | NA | NA | HFTD Tier 2 ¦ HFTD Tier 3 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | NA | NA | 69 | NA | 1.1 | 2020-1016 | QBL0071 | 1 | 15259 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-12-20 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Construction (25%-50%) | NA | 2022-07-18 | 2022-12-31 | 2026-11-02 | NA | NA | TRUE | NA | NA ¦ NA | 28560.0524 | 748.6604 | 1577.9954 | 5327.3388 | 8254.76 | 6093.1549 | 521.2791 | 5095.7011 | 941.1626 | 0 | 0 | 0 | 20812.6503 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 0 | 2.5985 | 208.7487 | 251.0339 | 205.5989 | 5095.7011 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
133 | A NORTH VALLEY 69/12KV SUB |  |  | Oceanside, San Diego | 69/12kV Rebuild. | Substation - Multiple | Upgrade/Retrofit | NA | NA | Reliability | System Design Upgrade | NA | NA | 2024-10-07 | 45 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 2.17 | 69 | NA | 1.1 | 2020-2092 | QBL0071 | 1 | 15259 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-12-20 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Engineering less than 50% complete | NA | 2024-10-31 | 2022-06-01 | 2027-08-23 | NA | NA | TRUE | NA | NA ¦ NA | 15356.9134 | 9.8658 | 713.0957 | 998.9821 | 1476.3618 | 894.4811 | 168.2525 | 10629.7764 | 466.0981 | 0 | 0 | 0 | 4092.784 | NA | NA | 2022 ¦ 2025 | 0 | 0 | 0.0019805 | 0 | 0 | 10629.7764 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
134 | A DESCANSO UPGRADE TL626 RELAYING |  |  | San Diego County | Replace 69/12kV circuit breakers in support of FCP. | Substation - Multiple | Upgrade/Retrofit | NA | NA | Wildfire Mitigation | Relay Upgrades | NA | NA | 2024-09-19 | 2.2 | NA | NA | NA | HFTD Tier 3 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | NA | 0.34 | 69 | NA | 1.1 | 2014-00432-ZZ-SUB | QBL0071 | 1 | 15259 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2016-03-31 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | 2016-11-07 | 2017-12-01 | 2021-06-30 | NA | NA | FALSE | NA | NA ¦ NA | 5055.0616 | 369.1478 | 807.0655 | 45.0175 | -0.48344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2022 ¦ 2023 | 0 | 0 | 5055.5451 | -0.48344 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
135 | A WARNERS UPGRADE TRANS RELAYING |  |  | San Diego County | Replace 69/12kV circuit breakers in support of FCP. | Substation - Multiple | Upgrade/Retrofit | NA | NA | Wildfire Mitigation | Relay Upgrades | NA | NA | 2024-10-28 | 2.2 | NA | NA | NA | HFTD Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | NA | 1.08 | 69 | NA | 1.1 | 2014-00278-ZZ-SUB | QBL0071 | 1 | 15259 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2016-08-31 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | 2016-11-08 | 2017-12-01 | 2021-12-17 | NA | NA | TRUE | NA | NA ¦ NA | 5802.8858 | 353.7824 | 905.0979 | 770.9282 | 77.9159 | 0.04789 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2023 ¦ 2024 | 0 | -0.86438 | 0 | 5803.7023 | 0.04789 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
136 | A APPWMP: POMERADO SUBSTATION |  |  | Poway, San Diego County | RTU and Relay Replacement | Substation - Multiple | Upgrade/Retrofit | NA | NA | Wildfire Mitigation | Relay Upgrades | NA | NA | 2024-09-12 | 18 - 32;26 | NA | NA | NA | HFTD Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | NA | 1.37 | 69 | NA | 1.1 | 2021-2178 | QBL0071 | 1 | 15259 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2021-02-16 | Work Order Authorization | 2022 | NA | FALSE | NA | NA | NA | FALSE | TBD | NA | NA | NA | CPUC | NA | Exempt | NA | NA | NA | Operational | NA | 2023-12-11 | 2022-07-31 | 2024-08-02 | NA | NA | TRUE | NA | NA ¦ NA | 1049.9061 | 0 | 37.0979 | 58.7327 | 546.5654 | 407.5101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2024 | 0 | 0 | 0 | 0 | 1049.9061 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
137 | A STUART SUBSTATION APP/DCRU |  |  | San Diego County | Breaker and RTU Replacement | Substation - Multiple | Upgrade/Retrofit | NA | NA | Wildfire Mitigation | Relay Upgrades | NA | NA | 2024-10-09 | 62;11 | NA | NA | NA | HFTD Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | NA | 0.12 | 69 | NA | 1.1 | 2021-2177 | QBL0071 | 1 | 15259 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2018-01-30 | Work Order Authorization | 2021 | NA | FALSE | NA | NA | NA | FALSE | TBD | NA | NA | NA | CPUC | NA | Exempt | NA | NA | NA | Operational | NA | 2022-10-25 | 2022-07-31 | 2024-10-25 | NA | NA | TRUE | NA | NA ¦ NA | 1102.7346 | 67.9165 | 87.1562 | 336.3774 | 203.7923 | 117.36 | 37.2709 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 | 0 | 407.934 | 336.3774 | 203.7923 | 117.36 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
138 | [Programmatic] Substation Security Installations (16126) |  |  | NA | This budget is required to maintain the reliability and integrity of the security of electric substations. The specific work required to meet safety requirements, replace obsolete or failed equipment, and make necessary small capital additions is based on requests from Engineering, Planning, Operations, and Maintenance groups. | Other - Physical Security | Upgrade/Retrofit | NA | NA | Reliability | Security Upgrades | NERC CIP Compliance | NA | NA | NA | NA | Wires - New Substation Alternative | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | Multiple | NA | 4.3 | Multiple | QBL0002 | 53 | 16126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-10-29 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Planning | NA | NA | 2024-12-31 | NA | NA | NA | TRUE | NA | NA ¦ NA | 0 | 1072.183 | 1829.84 | 1849.5669 | 3482.706 | 3009.6744 | 4707.2872 | 4794.6743 | 4650.3611 | 5330.2553 | 5903.9135 | 6595.7406 | 4589.807 | NA | NA | 2020 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 1160.6183 | 0 | 4080.3817 | 1914.9295 | 1657.2252 | 9831.3166 | 0% | NA ¦ NA | 5 | NA | 13.55% | 86.45%
139 | A NON CAST SECURITY VARIOUS SUBS |  |  | San Diego, San Diego | Security Upgrade and Fence project | Other - Physical Security | Upgrade/Retrofit | NA | NA | Physical Security | Security Upgrades | NA | NA | 2024-10-21 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | NA | NA | 4.3 | NA | QBL0002 | 1 | 16126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2021-01-29 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | NA | 2021-12-31 | NA | NA | NA | TRUE | NA | NA ¦ NA | 9124.9231 | 0 | 5152.3225 | 3045.8478 | 938.3538 | -11.6009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2023 ¦ 2024 | 0 | 0 | 0 | 9136.5241 | -11.6009 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [Age of Asset] Substation Security upgrades. No asset IDs.
140 | A ELLIOT SUB FENCE GATE BROW DITC |  |  | San Diego, San Diego | Elliot Sub fence, gate, and brow ditch rebuild. | Substation - Structure | Upgrade/Retrofit | Replace | NA | Physical Security | Security Upgrades | NA | NA | 2024-09-12 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 0.8 | 69 | NA | 4.3 | 2022-2767 | QBL0002 | 1 | 16126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2021-12-03 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | 2022-12-13 | 2022-12-31 | 2023-05-08 | NA | NA | FALSE | NA | NA ¦ NA | 1812.181 | 0 | 11.2673 | 674.8257 | 1126.088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2023 | 0 | 0 | 0 | 1812.181 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [Age of Asset] FENCE REPAIR NO ASSET
141 | A STATION F NON CAST SECURITY |  |  | San Diego, San Diego | Install new security system. | Other - Physical Security | Upgrade/Retrofit | New | NA | Physical Security | Security Upgrades | NA | NA | 2024-09-10 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 0.7 | 69 ¦ 12 | 69kV | 4.3 | 2021-2001 | QBL0002 | 1 | 16126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2021-12-07 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | NA | 2023-06-30 | NA | NA | NA | TRUE | NA | NA ¦ NA | 1351.7176 | 0 | 0 | 65.1837 | 1254.2796 | 32.2543 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2024 | 0 | 0 | 0 | 0 | 1351.7176 | 0 | 100% | 100% ¦ 1454 | NA ¦ NA | NA | 0% | 100% | [Age of Asset] Substation Security upgrades. No asset IDs.
142 | A PACIFIC BEACH NON CAST SECURITY |  |  | San Diego, San Diego | Fence Perimeter: Repair/Replace Fence or fencing material as required. ­Yard: Install low voltage and power conduit for security as required per plan New Pull Boxes, SP­Pads and 2” & 4” conduits will be required for security design. Note: Where possible existing trough, pull boxes, and existing conduit may be utilized for this effort ­Electrical Provide and install new electrical panel where applicable or identify existing panel and position. | Other - Physical Security | Replace | Replace | NA | Physical Security | Security Upgrades | NA | NA | 2024-09-03 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 0.35 | NA | NA | 4.3 | 2021-2004 | QBL0002 | 1 | 16126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2021-04-09 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | 2021-10-27 | 2022-05-31 | 2023-02-28 | Multiple Options [See Notes] | NA | TRUE | NA | NA ¦ NA | 1450.9987 | 0 | 128.8945 | 1254.4041 | 50.133 | 17.5671 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2023 ¦ 2024 | 0 | 0 | 0 | 1433.4316 | 17.5671 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [Age of Asset] Substation Security upgrades. No asset IDs. [Reason for Change in In-Service Date] In-service dates are estimated during preliminary design and permitting stages of a project; date shifted to reflect actual design and construction schedule.
143 | A SAN MARCOS NON CAST |  |  | San Marcos, San Diego | Fence Perimeter repair/replace fencing materials as needed; install low voltage and power conduit from security as required per plan, new pull boxes, SP Pads, where possible use existing pull boxes, conduit and trough | Other - Physical Security | Replace | Upgrade/Retrofit | NA | Physical Security | Security Upgrades | NA | NA | 2024-10-17 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 1.59 | 69 | 69 kV | 4.3 | 2021-2381 | QBL0002 | 1 | 16126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2021-07-21 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | 2021-10-25 | 2022-12-31 | 2024-03-06 | NA | NA | TRUE | NA | NA ¦ NA | 1563.9623 | 0 | 73.2847 | 293.3693 | 970.6194 | 226.6888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2024 | 0 | 0 | 0 | 0 | 1563.9623 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [Age of Asset] Substation Security upgrades. No asset IDs.
144 | A SUBSTATION SECURITY VARIOUS SUB |  |  | San Diego County | Blanket WO for preliminary security upgrades at various substations | Substation - Multiple | Multiple Options [See Notes] | NA | NA | Physical Security | Security Upgrades | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | NA | NA | 4.3 | NA | QBL0002 | 1 | 16126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-10-29 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Canceled | NA | NA | 2024-12-31 | NA | NA | NA | FALSE | NA | NA ¦ NA | 1866.8408 | 1329.4355 | 269.1068 | 68.1038 | 25.2631 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 | 1504.3671 | 269.1068 | 68.1038 | 25.2631 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [Project Description - Action Taken] This project has various substations.
145 | Substation Auxilliary Power System (GenCell) |  |  | NA | This project will develop, procure, design, and install three enclosed fuel cell units manufactured by GenCell. One unit will be installed at Descanso Substation, one unit will be installed at Boulevard East Substation, and one unit will be installed at Warners Substation. Each fuel cell will connect to the substation’s DC panel via a DC breaker. | Substation - Multiple | New | NA | NA | Reliability | Emergency Response - Storm Related | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ TRUE | FALSE | NA |  | NA | NA | 138 | 138kV | 4.3 | 2018-4 / 2018-1004 / 2018-3 | QS00137 | 1 | 16133 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2016-04-19 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Operational | NA | NA | 2019-06-20 | NA | NA | NA | FALSE | NA | NA ¦ NA | 5390.2522 | 28.4286 | 7.4317 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2020 ¦ 2021 | 2039.5043 | 7.4317 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
146 | [Programmatic] Substation DC Reliability Upgrades |  |  | NA | This project installs new assets in existing substation control shelters to support increased power requirements driven by aging infrastructure replacements of telecommunication hardware. Scope includes installation of new communication racks, upgrades to 125V DC systems for power, adding HVAC in transmission substation control shelters to support equipment environmental control requirements, DC-DC power converters, as well as batteries and Station Light & Power (SL&P) upgrades. | Substation - Multiple | Upgrade/Retrofit | NA | NA | Reliability | Replace Other Substation Equipment | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | NA | 373MVA | 4.3 | Multiple | QBL0094 | 162 | 16138 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-08-05 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | NA | 2024-12-31 | NA | NA | NA | TRUE | NA | NA ¦ NA | 0 | 1971.7675 | 3406.5425 | 2518.7515 | 3535.699 | 3612.8199 | 1432.0802 | 5521.4964 | 4518.9809 | 4538.2388 | 3115.6455 | 0 | 7308.6967 | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 1815.48 | 2278.4067 | 3728.1573 | 1791.8945 | 3357.91 | 6345.3 | 0% | NA ¦ NA | 2.9 | NA | 0% | 0%
147 | A DCRU: VARIOUS SUBS 2022 |  |  | San Diego County | DC Reliability Upgrades at multiple substations | Substation - Other Equipment | Upgrade/Retrofit | NA | NA | Reliability | Replace Other Substation Equipment | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | NA | NA | 4.3 | Multiple | QBL0094 | 12 | 16138 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2021-12-01 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | NA | 2022-12-31 | NA | NA | NA | TRUE | NA | NA ¦ NA | 2032.4925 | 0 | 25.7325 | 1520.8642 | 473.1137 | 12.782 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2023 ¦ 2024 | 0 | 0 | 0 | 2019.7105 | 12.782 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [Utility Unique ID #1(Less Specific)] 2021-2315 , 2022-2975 , 2022-2766 , 2021-2457 , 2021-2010 , 2024-3883 , 2022-3046 , 2022-2956 , 2022-2948 , 2022-2930 , 2014-00575-ZZ , 2022-3047
148 | A VARIOUS SUB DC REL UPGR TCRI |  |  | San Diego County | DC Reliability Upgrades at multiple substations | Substation - Other Equipment | Upgrade/Retrofit | NA | NA | Reliability | Replace Other Substation Equipment | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | NA | NA | 4.3 | NA | QBL0094 | 1 | 16138 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2018-01-12 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | NA | 2018-12-31 | NA | NA | NA | FALSE | NA | NA ¦ NA | 5449.551 | 382.8666 | 29.7418 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2020 ¦ 2021 | 5419.8092 | 29.7418 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0%
149 | A VARIOUS SUBS DC REL UPGR 2020 |  |  | San Diego County | DC Reliability Upgrades at multiple substations | Substation - Other Equipment | Upgrade/Retrofit | NA | NA | Reliability | Replace Other Substation Equipment | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | NA | NA | 4.3 | 2021-2057 | QBL0094 | 1 | 16138 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-04-07 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | 2021-05-10 | 2020-12-31 | 2021-11-09 | NA | NA | FALSE | NA | NA ¦ NA | 2987.492 | 2699.6088 | 287.8832 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 | 0 | 2987.492 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0%
150 | A ENCINA SUBSTATION TCRI |  |  | Carlsbad, San Diego | Encina substation DC reliability upgrades | Substation - Other Equipment | Upgrade/Retrofit | NA | NA | Reliability | Replace Other Substation Equipment | NA | NA | 2024-10-16 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | NA | NA | 4.3 | 2014-00548-ZZ | QBL0094 | 1 | 16138 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2017-02-23 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | 2019-09-16 | 2017-12-01 | 2020-01-01 | NA | NA | FALSE | NA | NA ¦ NA | 1083.7698 | 266.8588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2020 | 1083.7698 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0%
151 | A DCRU PHASE IV IMPERIAL BEACH |  |  | San Diego, San Diego | Imperial Beach substation DC reliability upgrades | Substation - Other Equipment | Upgrade/Retrofit | NA | NA | Reliability | Replace Other Substation Equipment | NA | NA | 2024-10-18 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | NA | NA | 4.3 | 2020-2055 | QBL0094 | 1 | 16138 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-08-20 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | 2021-11-02 | 2021-12-31 | 2022-06-17 | NA | NA | TRUE | NA | NA ¦ NA | 1477.9921 | 112.3988 | 523.2661 | 830.3421 | 12.3177 | -0.33256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 | 0 | 0.058964 | 1465.948 | 12.3177 | -0.33256 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0%
152 | A DCRU PHASE IV MIRAMAR |  |  | San Diego, San Diego | Miramar substation DC reliability upgrades | Substation - Protection Relay | Upgrade/Retrofit | NA | NA | Reliability | Replace Other Substation Equipment | NA | NA | 2024-10-02 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 0.76 | NA | NA | 4.3 | 2020-2054 | QBL0094 | 1 | 16138 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-08-20 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Construction (over 75%) | NA | 2024-03-04 | 2021-12-31 | 2025-10-01 | NA | NA | TRUE | NA | NA ¦ NA | 2638.9358 | 35.2375 | 124.3884 | 378.0122 | 235.6891 | 1762.0021 | 0 | 103.6064 | 0 | 0 | 0 | 0 | 69.4823 | NA | NA | 2021 ¦ 2024 ¦ 2025 | 0 | 0.0018632 | 0 | 0 | 2465.8453 | 173.0887 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0%
153 | A DCRU: VARIOUS SUBS 2021 |  |  | San Diego County | DC Reliability Upgrades at multiple substations | Substation - Other Equipment | Upgrade/Retrofit | NA | NA | Reliability | Replace Other Substation Equipment | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | NA | NA | 4.3 | Multiple | QBL0094 | 4 | 16138 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2021-02-16 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | NA | 2021-12-31 | NA | NA | NA | FALSE | NA | NA ¦ NA | 1930.476 | 0 | 1876.3438 | 54.1322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2022 | 0 | 0 | 1930.476 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [Utility Unique ID #1] 2021-2178 , 2020-2101 , 2021-2315 , 2022-2765
154 | TL23001 TL23004 Wood to Steel Replacement (Mission San Luis Rey) |  |  | San Diego, San Diego | TL23001 and TL23004 from Mission to San Luis Wood to Steel pole replacement. The scope of work includes replacing 42 existing wood pole structures with engineered steel structures as well as stringing 3.5 miles of new single conductor 1033 ACSR one line of OPGW and one line of 7#8 shield wire for TL23001 and TL23004. | Transmission Line - Conductor | Replace | NA | NA | Wildfire Mitigation | Fire Protection | NA | NA | 2024-01-16 12:00 | 18 | NA | NA | NA | HFTD Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 2.9735 | NA | 230 | NA | 1.2 | 2014-00016-ZZ | QS00142 | 1 | 16150 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-02-20 | Work Order Authorization | 2017 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | NA | NA | Exempt | NA | Approved | 2018 | Operational | NA | 2019-10-18 | 2021-12-31 | 2020-03-31 | NA | NA | FALSE | 22646.466 | NA ¦ NA | 28936.157 | 10511.9187 | 123.4328 | 0.60204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2020 ¦ 2021 ¦ 2022 | 28812.1221 | 123.4328 | 0.60204 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0%
155 | New 2nd Miguel to Bay Blvd. 230 kV Line |  |  | Bonita, San Diego ¦ Chula Vista, San Diego | New 2nd Miguel to Bay Blvd. 230 kV Line | Transmission Line - Conductor | New | NA | NA | CAISO Transmission Planning Standards [See Notes for NERC Compliance and contingency code, WECC Requirement (and the specific requirement)] | New T-Line | NERC TPL Standards | NA | NA | 18 | Steady State Power Flow System Analysis | Wires - New T-Line Alternative | NA | HFTD Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | Coastal |  | 9.8716 | NA | 230 | NA | 2.1 | 2015-00021 | QS00143 | 1 | 16157 | NA ¦ NA ¦ NA ¦ NA | FALSE | NA | Work Order Authorization | 2017 | 2016 | FALSE | 2016 | NA | https://www.caiso.com/planning/Pages/TransmissionPlanning/2015-2016TransmissionPlanningProcess.aspx | FALSE | NA | NA | Exempted | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | 2018-05-23 | 2018-06-01 | 2019-08-21 | Permitting | Construction Delays | TRUE | 24499.998 | NA ¦ NA | 21464.9752 | 691.6827 | 39.4429 | 0.00759 | 0 | -1.8422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2024 | 691.6827 | 39.4429 | 0.00759 | 0 | -1.8422 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0%
156 | TL605 Reconductor (Silvergate Urban) |  |  | San Diego, San Diego | Reconductor TL605 with 2-636ACSS (200MVA) or equivalent Note: there is an active project (ID:2015-00013; budget code: 16158) with ISD of 6/26/2024. This new summited cost request is to upgrade the current design line rating from 137 MVA to 200MVA | Transmission Line - Conductor | Upgrade/Retrofit | NA | NA | Local Capacity Requirement | Line Reconductoring | NERC TPL Standards | NA | 2023-10-24 12:00 | 16 | Steady State Power Flow System Analysis | Wires - Reconductor/Line Rebuild Alternative | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | Coastal |  | 1.9028 | NA | 69 | NA | 2.1 | 2015-00013 | QS00144 | 1 | 16158 | NA ¦ NA ¦ NA ¦ NA | FALSE | NA | Work Order Authorization | 2017 | 2016 | FALSE | 2016 | NA | https://www.caiso.com/planning/Pages/TransmissionPlanning/2015-2016TransmissionPlanningProcess.aspx | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | Approved | 2023 | Operational | NA | 2024-01-15 | 2018-06-01 | 2024-11-20 | Permitting | ISO Action | TRUE | 545 | NA ¦ NA | 32869.6714 | 5.6003 | 5495.897 | 773.0469 | 8170.9024 | 10739.1307 | 4213.8248 | 2871.9085 | 0 | 0 | 0 | 0 | 25783.9382 | NA | NA | 2025 | 0 | 0 | 0 | 0 | 0 | 2871.9085 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
157 | HVDC Conversion of Southwest Powerlink |  |  | San Diego County | The scope of this work encompasses all aspects of engineering and design that is required to plan the HVDC conversion of the Southwest Powerlink. The engineering/planning process will also involve exploring feasible alternatives to this proposed project. | Other | NA | NA | NA | Address Results of Power Flow Analysis | System Operations | NA | NA | NA | 18 | Steady State Power Flow System Analysis | NA | Over $500 Mil | HFTD Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 85 | NA | 525 | 525kV | 4.2 | NA | QS00145 | 1 | 16159 | NA ¦ NA ¦ NA ¦ NA | FALSE | NA | Work Order Authorization | 2017 | 2018 | FALSE | 2018 | NA | https://www.caiso.com/planning/Pages/TransmissionPlanning/2017-2018TransmissionPlanningProcess.aspx | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Canceled | NA | NA | NA | NA | NA | NA | FALSE | 1467 | NA ¦ NA | 1226.7107 | -67.3171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2020 | 1226.7107 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0% | [CPUC Status] Project was Exempt from CPUC filing per GO-131D. project cancelled
158 | San Mateo Substation |  |  | San Clemente, Orange | Rebuild the existing 138/12 kV San Mateo Substation to Enhance reliability and minimize outage impacts in the San Clemente area. | Substation - Multiple | Replace | Upgrade/Retrofit | NA | Reliability | Substation Reliability | NA | NA | 2024-10-15 | 18; 18; 18; 9; 53; 44 | NA | NA | NA | HFTD Tier 2 | FALSE ¦ FALSE ¦ FALSE | TRUE | NA |  | NA | 0.542 | 138 | 12kV ¦ 138kV | 4.1 | 2017-0160 | QS00149 | 1 | 16261 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-09-24 | Work Order Authorization | 2018 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | PTC | NA | NA | NA | On Hold | NA | NA | 2020-12-31 | NA | NA | NA | FALSE | 1240 | NA ¦ NA | 4379.483 | 275.9061 | 302.2602 | 285.4594 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4379.483 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
159 | SCADA HEAD END REPLA |  |  | San Diego County | SCADA Headend software/hardware replacement | Other | New | NA | NA | Local Capacity Requirement | System Operations | NA | NA | NA | 18 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | TRUE | NA |  | NA | NA | 12 ¦69 | NA | 1.3 | NA | QS00154 | 1 | 16276 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2017-01-10 | Work Order Authorization | 2019 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Planning | NA | NA | 2023-07-31 | NA | NA | NA | TRUE | 1356.2742 | NA ¦ NA | 3418.2124 | 588.523 | 100.5682 | 150.6047 | 108.6673 | 2.9962 | 0.0021359 | 0.0090415 | 0.00953 | 0 | 0 | 0 | 0 | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 ¦ 2024 | 2896.5874 | 100.5682 | 150.6047 | 108.6673 | 2.9024 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
160 | TL632A Loop In (Granite) |  |  | El Cajon, San Diego ¦ Crest, San Diego ¦ Granite Hills, San Diego | Convert TL632 from a tap into Granite Substation to a loop-in. Based on routing study, underground along La Cresta Rd to Granite Substation is most feasible route. 1.9 miles of 69kV underground. | Transmission Line - Multiple | Upgrade/Retrofit | NA | NA | Reliability | T-Line Reliability | NERC TPL Standards | NA | 2024-10-29 | 18 | Steady State Power Flow System Analysis | Wires - System Configuration Alternative | $10 Mil -$15 Mil | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 2.1143 | NA | 69 | NA | 2.1 | 2015-00005 | QS00158 | 1 | 17125 | NA ¦ NA ¦ NA ¦ NA | FALSE | NA | Work Order Authorization | 2017 | 2015 | FALSE | 2015 | NA | https://www.caiso.com/planning/Pages/TransmissionPlanning/2014-2015TransmissionPlanningProcess.aspx | FALSE | TBD | NA | NA | NA | NA | NA | Advice Letter | 2025-01-24 | To be Filed | 2025 | Engineering more than 50% complete | NA | 2025-09-11 | 2017-06-01 | 2027-03-09 | Permitting | Land Rights | FALSE | 14057.888 | NA ¦ NA | 50788.5217 | 80.776 | 333.8327 | 325.5874 | 7751.4818 | 1050.8578 | 485.5016 | 11935.3813 | 26725.916 | 0 | 0 | 0 | 27067.064 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | 3.4 | NA | 0% | 100%
161 | TL611 Direct Buried Cable Replacement (Old Town Point Loma) |  |  | San Diego, San Diego | Direct-Buried Cable Replacement (Approx. 1-mile trench and substructures) | Transmission Line - Underground | Replace | NA | NA | Reliability | Age/Condition | NA | NA | 2024-05-22 | 57;57 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | Coastal |  | 1.3221 | NA | 69 | NA | 4.1 | 2012-0002-ZZ | QS00720 | 1 | 17127 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-11-28 | Work Order Authorization | 2017 | NA | FALSE | NA | NA | NA | FALSE | TBD | NA | NA | NA | NA | NA | TBD | NA | To be Filed | 2027 | Engineering less than 50% complete | NA | 2027-12-02 | 2026-12-31 | 2028-04-05 | NA | NA | FALSE | 28043.924 | NA ¦ NA | 28043.924 | 0 | 0 | 0 | 112.2093 | 719.3956 | 81.5519 | 3576.3987 | 19386.7418 | 4167.6268 | 0 | 0 | 831.6049 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | 4.9 | NA | 0% | 100%
162 | TL603 Loop in (Sweetwater, National City, and Naval Station Metering) |  |  | National City, San Diego | Open Sweetwater Tap and make TL603D and TL603B one continuous 69kV line from national City to Sweetwater. | Transmission Line - Multiple | Upgrade/Retrofit | NA | NA | Reliability | T-Line Reliability | NERC TPL Standards | NA | 2024-02-22 | 57 | Steady State Power Flow System Analysis | Wires - System Configuration Alternative | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 2.5607 | NA | 69 | NA | 2.1 | 2015-00066 | QS00159 | 1 | 17129 | NA ¦ NA ¦ NA ¦ NA | FALSE | NA | Work Order Authorization | 2017 | 2013 | FALSE | 2013 | NA | https://www.caiso.com/planning/Pages/TransmissionPlanning/2012-2013TransmissionPlanningProcess.aspx | FALSE | TBD | NA | NA | NA | CPUC | NA | TBD | 2025-05-23 | To be Filed | 2025 | Permitting | NA | 2025-11-05 | 2017-06-01 | 2026-07-16 | Prioritization | Permitting | FALSE | 13584.367 | NA ¦ NA | 33491.4088 | 208.6506 | 5306.3214 | 210.5866 | 681.428 | 410.279 | 176.1761 | 9284.4085 | 14845.6897 | 0 | 0 | 0 | 9185.1345 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | 3.1 | NA | 0% | 100% | [Project Description - What] TL603D (National City – Sweetwater Tap) and TL603B (Sweetwater – Sweetwater Tap) will be made into one continuous line segment running from National City to Sweetwater Substation to achieve a minimum continuous/emergency rating of 102 MVA. The project is expected to cost $10 to $12 million and the expected in-service date is June, 2017.
163 | TL6906 Mesa Rim Rearrangement |  |  | San Diego, San Diego | A CAISO approved reliability project to loop in TL6906 in order to provide two (2) additional feeds to the Mesa Rim Substation, which is currently fed by two (2) transmission lines, TL675 and TL677. The loop-in consists of installation of two (2) cable poles, along with underground trenching and an XLPE cable system to complete the connection. | Transmission Line - Underground | Upgrade/Retrofit | NA | NA | CAISO Transmission Planning Standards [See Notes for NERC Compliance and contingency code, WECC Requirement (and the specific requirement)] | T-Line Capacity | NA | NA | 2024-04-26 12:00 | 27;27 | Steady State Power Flow System Analysis | Wires - System Configuration Alternative | NA | HFTD Tier 2 | FALSE ¦ FALSE ¦ TRUE | FALSE | NA |  | 9.1086 | NA | 69 | NA | 2.1 | 2014-00207-ZZ | QS00160 | 1 | 17130 | NA ¦ NA ¦ NA ¦ NA | FALSE | NA | Work Order Authorization | 2017 | 2014 | FALSE | 2014 | NA | https://www.caiso.com/planning/Pages/TransmissionPlanning/2013-2014TransmissionPlanningProcess.aspx | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | 2018-11-05 | 2018-06-01 | 2020-08-05 | Prioritization | Outage | TRUE | 3000 | NA ¦ NA | 16643.2764 | 8642.3835 | 675.6017 | -344.4169 | 0 | -0.01545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2024 | 16312.107 | 675.6017 | -344.4169 | 0 | -0.01545 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
164 | Imperial Valley Substation: Replace Bank 80 |  |  | Imperial County | Install three (3) new 500/230kV 373MVA single phase transformers. Upgrade 12kV tertiary bus to meet the new MVA rating of Bank 80 and adjust firewalls. Replace existing 480/277V SL&P transformers with new 120/208V transformers to provide the required control power for the new BK80. Remove and demo existing three (3) 500/230kV single phase transformers. Demo the existing spare Bank 80 unit. Upgrade the 3.5" AL bus to 2-2500 KCMIL in the 230kV yard to meet TERG requirements, re-ordered few structural BOMs for the 12kV tertiary, added fiberglass grating, and remobilized Siemens onsite during commissioning to assist KY. | Substation - Transformer | Replace | NA | NA | Reliability | Age/Condition - Replace 230/115/70/60 kV Transformers | NA | NA | 2024-10-30 | 41 | NA | Wires - Minimum Required Scope (spot repair) Alternative | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 55.48 | 500 | 500kV | 2.1 | 2014-01072-ZZ | QS00161 | 1 | 17138 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-05-21 | Work Order Authorization | 2018 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | 2018-10-16 | 2019-06-28 | 2019-05-11 | NA | NA | TRUE | 16986 | NA ¦ NA | 19791.462 | 559.4154 | 4.5065 | 0 | 215.5945 | 210.7717 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2020 ¦ 2021 ¦ 2023 ¦ 2024 | 559.4154 | 4.5065 | 0 | 215.5945 | 210.7717 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0%
165 | TL690 Direct Buried Cable Replacement (Oceanside Oceanside Tap) |  |  | Oceanside, San Diego ¦ Camp Pendleton South, San Diego | Direct-Buried Cable Replacement. Approx. 1-mile trench and substructures. (canceled/suspended) | Transmission Line - Underground | Replace | NA | NA | Reliability | Age/Condition | NA | NA | 2024-07-25 | 27 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 1.0534 | NA | 69 | NA | 4.1 | 2014-00017-ZZ | QS00163 | 1 | 17142 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-08-31 | Work Order Authorization | 2017 | NA | FALSE | NA | NA | NA | FALSE | TBD | NA | NA | NA | NA | NA | TBD | 2027-06-14 | To be Filed | 2027 | On Hold | NA | NA | 2028-11-13 | NA | NA | NA | FALSE | 905.761 | NA ¦ NA | 30645.9038 | 23.7071 | 0 | 0 | 0 | 0 | 67.9543 | 110.5179 | 5540.8974 | 11273.9353 | 12882.8176 | 0 | 769.7813 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | 3.9 | NA | 0% | 100%
166 | TL628 Direct Buried Cable Replacement (Rancho Del Rey & H St.) |  |  | Chula Vista, San Diego | Direct-Buried Cable Replacement (On Hold) | Transmission Line - Underground | Replace | NA | NA | Reliability | Age/Condition | NA | NA | 2024-02-22 | 27 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.63688 | NA | 69 | NA | 4.1 | 2017-0021 | QS00164 | 1 | 17143 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2018-09-04 | Work Order Authorization | 2018 | NA | FALSE | NA | NA | NA | FALSE | TBD | NA | NA | NA | NA | NA | TBD | NA | To be Filed | 2027 | On Hold | NA | 2027-12-02 | 2021-04-01 | 2028-03-17 | NA | NA | FALSE | 360 | NA ¦ NA | 40286.731 | 94.3996 | 15.6756 | 54.4923 | 45.6665 | 8.6489 | 50.1921 | 192.5322 | 8123.2658 | 14037.395 | 16580.0427 | 0 | 1303.3032 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | 4.8 | NA | 0% | 100%
167 | TL698 Direct Buried Cable Replacement (Avocado Sub Getaway) |  |  | Fallbrook, San Diego | This project installs one new engineered steel cable pole and underground facilities to support the replacement of the direct buried cable Getaways of the Avocado Substation on TL698. The underground segment on TL698 is 1500 feet long, a portion of the line will be installed within a double circuit underground duct package, and a single circuit underground duct package. The duct package will be constructed in a franchise position on the north side of Barhaven Lane, crossing Alvarado St. and consists of three conduits for the 69kV segment of cable and one conduits for fiber optic communication. A new steel cable pole (Z293941) will be installed to replace an existing steel cable pole structure (Z713100) on TL698. Time frame for construction is November 2019- March 2020. | Transmission Line - Conductor | Replace | NA | NA | Reliability | Age/Condition - Replace Underground System | NA | NA | 2024-02-22 | 27 | NA | NA | NA | HFTD Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.23906 | NA | 69 | NA | 4.1 | 2017-0026 | QS00166 | 1 | 17145 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-02-01 | Work Order Authorization | 2017 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | 2019-11-22 | 2020-05-01 | 2020-05-01 | NA | NA | FALSE | 326.6588 | NA ¦ NA | 2822.313 | 1620.3057 | 93.9478 | 4.2942 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2020 ¦ 2021 ¦ 2022 | 2724.071 | 93.9478 | 4.2942 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
168 | TL697 Direct Buried Cable Replacement (Oceaside Sub Getaway) |  |  | Oceanside, San Diego | Direct-Buried Cable Replacement (canceled/suspended) | Transmission Line - Underground | Replace | NA | NA | Reliability | Age/Condition | NA | NA | 2024-07-25 | 27 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.065771 | NA | 69 | NA | 4.1 | 2017-0025 | QS00167 | 1 | 17147 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-04-24 | Work Order Authorization | 2017 | NA | FALSE | NA | NA | NA | FALSE | TBD | NA | NA | NA | NA | NA | TBD | 2027-03-24 | To be Filed | 2027 | On Hold | NA | NA | 2027-12-31 | NA | NA | NA | FALSE | 1500.416 | NA ¦ NA | 10313.5735 | 15.148 | 0 | 0 | 0 | 0 | 71.7167 | 476.2298 | 512.9534 | 6525.6622 | 2370.739 | 0 | 356.2724 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | 5.4 | NA | 0% | 100%
169 | TL667 Direct Buried Cable Replacement (El Camino Real) |  |  | San Diego, San Diego | Direct-Buried Cable Replacement (On Hold) | Transmission Line - Underground | Replace | NA | NA | Reliability | Age/Condition | NA | NA | 2024-05-16 12:00 | 27 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 4.0087 | NA | 69 | NA | 4.1 | 2014-0022 | QS00169 | 1 | 17151 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2017-09-08 | Work Order Authorization | 2018 | NA | FALSE | NA | NA | NA | FALSE | TBD | NA | NA | NA | NA | NA | TBD | 2024-12-26 | To be Filed | 2025 | On Hold | NA | 2027-11-05 | 2020-12-31 | 2028-01-26 | NA | NA | FALSE | 15490.906 | NA ¦ NA | 72348.1779 | 19.824 | 23.9228 | 23.2003 | 23.4068 | 13.9001 | 82.7152 | 189.9612 | 1621.0633 | 15906.7301 | 50084.271 | 2579.9999 | 1883.437 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | 0.6 | NA | 0% | 100%
170 | TL673 Direct Buried Cable Replacement (Rose Canyon La Jolla) |  |  | San Diego, San Diego | Currently TL673 consist entirely of aging 69kV direct-buried cable from Rose Canyon to La Jolla substations at approximately three miles. This existing direct-buried cable is of 1967 vintage year and has far exceeded its designed operational expectancy of 30 years. Transmission Engineering anticipates an increase rate in outages caused by failures on this existing aging cable system in the near future. This project will replace all existing direct-buried cable from Rose Canyon to La Jolla substations within a newly constructed underground trench conduit package and substructures which will improve electric transmission reliability to the La Jolla area as well as resolve the ongoing maintenance issue for TL673. | Transmission Line - Underground | Upgrade/Retrofit | NA | NA | Reliability | Age/Condition | NA | NA | NA | 27 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 3.1283 | NA | 69 | NA | 4.1 | 2017-0023 | QS00170 | 1 | 17152 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2022-12-13 | Work Order Authorization | 2018 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | 2021-07-26 | 2023-06-30 | 2023-06-30 | Permitting | Land Rights | TRUE | 2600 | NA ¦ NA | 63860.9368 | 8953.7822 | 13885.5181 | 19644.0673 | 15451.8939 | -69.3824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 ¦ 2024 | 5800.3575 | -170.835 | 244.5547 | 58056.242 | -69.3824 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
171 | Avocado Substation 69kV Rebuild |  |  | San Diego, San Diego | Substation Rebuild, Transformers, Control Shelter & Relays & CS equipment, expanded the substation, change out 69kV circuit breakers, PT, and disconnects. | Substation - Multiple | Upgrade/Retrofit | NA | NA | Reliability | Substation Reliability | NA | NA | 2024-10-15 | 50; 50; 61 | NA | Wires - Replacement Alternative | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 3.1283 | 1.7192 | 69 | 60MVA | 2.1 | 2014-00941-ZZ | QS00171 | 1 | 17153 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-12-20 | Work Order Authorization | 2017 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | 2018-09-17 | 2021-10-14 | 2021-10-14 | NA | NA | TRUE | 2020 | NA ¦ NA | 16778.2241 | 5188.531 | 2428.5638 | 3.1856 | 0 | 179.3453 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2024 | 96.0253 | 16499.6679 | 3.1856 | 0 | 179.3453 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
172 | TL691 Direct Buried Cable Replacement (Avocado Sub Getaway) |  |  | Oceanside, San Diego | This project replaces approximately 900' of direct buried cable on TL698 from Avocado Substation to Structure Z15588 with concrete encased conduit, cable pole and cable. | Transmission Line - Conductor | Replace | NA | NA | Reliability | Age/Condition - Replace Underground System | NA | NA | 2024-02-10 | 27 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.15746 | NA | 69 | NA | 4.1 | 2017-0027 | QS00174 | 1 | 17157 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-10-13 | Work Order Authorization | 2018 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | 2019-11-22 | 2020-11-16 | 2020-11-16 | NA | NA | FALSE | 1947.832 | NA ¦ NA | 2142.2622 | 1179.4149 | 116.3664 | 71.2848 | 168.0996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 | 1786.5114 | 116.3664 | 71.2848 | 168.0996 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
173 | San Marcos Substation 69kV Rebuild & 12kV Switchgear |  |  | San Marcos, San Diego | Upgrade the 69kV bus, replace all 69kV insulators, disconnects, potential transformers, protection and controls. Replace existing control shelter with a new block shelter. Replace Bk 32’s 12kV switchgear with new switchgear (sized to fit on existing foundation) and cutover existing 12kV circuits to new switchgear. Replace and relocate existing 12kV capacitors. Remove and RFS four 69kV oil breakers, two 12kV capacitors, Bk 32's switchgear, and control shelter. | Substation - Multiple | Upgrade/Retrofit | NA | NA | Reliability | Age/Condition | NA | NA | 2024-10-17 | 33; 46; 46; 33 | NA | Wires - Replacement Alternative | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | TRUE | NA |  | NA | 1.5915 | 69 | 60MVA | 4.1 | 2014-01062-ZZ | QS00176 | 1 | 17160 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-02-07 | Work Order Authorization | 2018 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Planning | NA | NA | 2026-09-30 | NA | NA | NA | FALSE | 800 | NA ¦ NA | 585.5195 | 18.2372 | 12.3271 | 7.0906 | 9.2735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 585.5195 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | 1.8 | NA | 0% | 100%
174 | TL662 TL666 Reliability Project |  |  | San Diego, San Diego County | Project involves installing civil engineered mitigation of potential landslide risk for overhead electric poles within existing SDG&E utility easement located in Torrey Pines. | Other - Civil | Upgrade/Retrofit | NA | NA | Asset Condition | Age/Condition - Replace Civil Structures | NA | NA | 2024-05-04 | 55;51 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 2 | NA | 12 ¦69 | NA | 4 | 2023-3558 | QS00196 | 1 | 18126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2018-02-21 | Work Order Authorization | 2024 | NA | FALSE | NA | NA | NA | FALSE | TBD | NA | NA | NA | CPUC | NA | NA | NA | NA [See Notes] | NA | Planning | NA | 2026-07-24 | 2021-12-31 | 2026-09-28 | NA | NA | TRUE | 6808.179 | NA ¦ NA | 6099.3586 | 41.7534 | 157.1544 | 259.0357 | 82.0949 | -53.592 | 50.6091 | 672.9796 | 4177.9317 | 375.1626 | 0 | 0 | 0 | NA | NA | 2024 ¦ 2025 | 0 | 0 | 0 | 0 | 822.6756 | 672.9796 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] N/A - Prescoping efforts. Filing type not yet determined.
175 | Escondido Substation 230kV Rebuild |  |  | Escondido, San Diego | A 230kV transmission line between the existing Sycamore Canyon and Penasquitos substations. The new 230kV line would include the installation of new 138kV and 230kV steel poles, utilize existing overhead structures within the Approved Project Sponsor’s existing right-of-way (ROW), and installation of new underground lines in the Approved Project Sponsor’s franchise position in a city street as outlined in the approved CPCN in the following manner: Installation of new 230-kV line (TL23071) in an underground configuration from Sycamore Substation to a new 230kV single-circuit dulled galvanized cable pole just outside the substation within existing Approved Project Sponsor ROW. Modifications to existing 138-kV line (TL13820) included. Installation of new 230-kV overhead line (TL23071) west from the new 230kV cable pole outside of Sycamore Substation through one (1) new 230-kV dulled galvanized steel tubular monopole to a second new 230kV dulled galvanized cable pole located north of Stonebridge Parkway within existing Approved Project Sponsor ROW. Modifications to existing 138-kV line (TL13820) included. Grade new or refresh existing construction maintenance pads and spur roads for the new 230-kV poles as-needed. Installation of new 230-kV underground line (TL23071) in city streets (Stonebridge Parkway and Pomerado Road) utilizing existing franchise position for almost the entire segment. Underground rights through an existing access road to existing ROW would need to be acquired. Installation of new 230-kV underground line (TL23071) to cross I‐15 via two new cable poles. Installation of new 230-kV underground line (TL23071) in city streets (Miramar Road, Black Mountain Road, Activity Road, Camino Ruiz, Miralani Drive, Arjons Drive, Trade Place, Trade Street, Camino Santa Fe, Carroll Road/Carroll Canyon Road) utilizing existing franchise position for almost the entire segment. Installation of new 230-kV cable pole within existing ROW to transition from underground to overhead and installation of new 230-kV conductor on existing structures located within an existing SDG&E ROW into the Peñasquitos Substation. | Substation - Multiple | Replace | Upgrade/Retrofit | NA | Reliability | Substation Reliability | NA | NA | 2024-10-07 | 40; 44; 46; 16; 16; 16; 23; 16; 16; 24; 24 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 4.6631 | 230 | 230kV | 4.1 | 2024-4134 | QS00197 | 1 | 18127 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-02-01 | Work Order Authorization | 2018 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | NA | NA | TBD | NA | NA [See Notes] | NA | Planning | NA | TBD | 2022-12-31 | TBD | NA | NA | FALSE | 982 | NA ¦ NA | 191791.0065 | 1.1452 | 5.867 | 14.0554 | 45.3664 | 37.4151 | 24.4677 | 502.3619 | 26462.0226 | 26404.3877 | 41107.3391 | 44544.6698 | 213.792 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | 3.6 | NA | 100% | 0% | [CPUC Status] Exempt
176 | Mission 69kV Sub Rebuild |  |  | San Diego, San Diego | Install shoo-fly's for TL618, TL663 & TL13822 in conflict with the proposed Mission 69kV GIS | Substation - Multiple | Replace | Upgrade/Retrofit | NA | Reliability | Substation Reliability | NA | NA | 2024-10-30 | 51 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | Coastal |  | NA | 8.9967 | 69 | 69kV | 4.1 | 2019-1012 | QS00198 | 1 | 18128 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-02-01 | Work Order Authorization | 2018 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | NA | NA | Exempt | NA | NA | NA | Engineering less than 50% complete | NA | 2022-12-05 | 2019-12-30 | 2025-06-16 | NA | NA | TRUE | 97625.0096 | NA ¦ NA | 128764.8964 | 7.7251 | 821.6072 | 16116.6832 | 27651.0585 | 29176.3325 | 14723.9618 | 31431.229 | 8793.7122 | 0 | 0 | 0 | 73815.9934 | NA | NA | 2023 ¦ 2025 | 0 | 0 | 0 | 1.9299 | 0 | 119969.2542 | 0% | NA ¦ NA | 6.7 | NA | 0% | 100%
177 | Oceanside Substation 69kV Rebuild |  |  | Oceanside, San Diego | Rebuild will consist of relocating and rebuilding the 69kV bus and structures on the newly acquired property using a 69kV GIS design. The new 69kV GIS bus will consist of five (5) 69kV breakers to meet the ultimate layout consisting of two (2) TL’s, two (2) transformer positions, and a disconnect used to serve portable transformers. This project will also rebuild the control shelter to a larger, block control enclosure. | Substation - Multiple | Upgrade/Retrofit | NA | NA | Reliability | Substation Reliability | NA | NA | 2024-10-11 | 2; 9; 21; 49; 21 | NA | Wires - New Substation Alternative | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 0.22439 | 69 | 69kV | 4.1 | 2018-1015 | QS00200 | 1 | 18130 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-02-07 | Work Order Authorization | 2018 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | 2022-07-18 | 2021-09-27 | 2022-10-31 | NA | NA | TRUE | 10 | NA ¦ NA | 975.1418 | 84.8977 | 55.5256 | 169.8064 | 402.1695 | 0.25416 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2023 ¦ 2024 | 0 | 0 | 0 | 974.8876 | 0.25416 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
178 | Skills Training Center – Transmission Yard Expansion |  |  | San Diego, San Diego | The purpose of this project is to expand the transmission yard at Skills Training Center for crews to train safely on. A new OH potion will be installed, along with an UG portion, a 500kV Insulator Replica, and an SW pole with a new stepping pattern will be installed. Last phases of construction to begin September 2021, and end before 2022 | Transmission Line - Conductor | Replace | NA | NA | Other [See Notes] | System Operations | NA | NA | NA | 54 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.076428 | NA | 69 ¦230 | NA | 1.3 | 2018-4002 | QS00380 | 1 | 18136 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2018-12-12 | Work Order Authorization | 2019 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | 2020-05-18 | 2021-11-29 | 2022-04-01 | NA | NA | FALSE | 2475.891 | NA ¦ NA | 1948.0361 | 341.3192 | 972.9268 | 558.2736 | 1.8695 | 0 | 0.20408 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2022 ¦ 2023 ¦ 2024 | 0 | 0 | 1945.9625 | 1.8695 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 13.55% | 86.45% | [Primary Purpose] Infrastructure not connected to the grid for training purposes.
179 | Miguel Substation 230kV Rebuild |  |  | San Diego County | Upgrade relaying for Bk70/71, replace 32 disconnects, replace 32 switch stands to meet our new seismic standards, replace one overstressed breaker, and eight (8) panel changeouts. Remove existing relaying panels #403 & #406 | Substation - Multiple | Upgrade/Retrofit | NA | NA | Reliability | Age/Condition - Replace 230/115/70/60 kV Breakers | NA | NA | 2024-10-22 | NA | NA | Wires - Replacement Alternative | NA | HFTD Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 12.37 | 230 | 660MVA | 4.1 | 2014-01074-ZZ | QS00350 | 1 | 18139 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-01-23 | Work Order Authorization | 2019 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | 2019-09-23 | 2022-07-31 | 2022-07-31 | Multiple Options [See Notes] | NA | TRUE | 10503 | NA ¦ NA | 11567.5182 | 2947.2461 | 2385.1998 | 974.2539 | 5.9404 | -0.69433 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2022 ¦ 2023 ¦ 2024 | 0 | 0 | 11562.2721 | 5.9404 | -0.69433 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0% | [Age of Asset] Construction of OH/UG transmission training facilities for SDGE line crews to perform construction and maintenance of transmission lines throughout service territory. [Reason for Change in In-Service Date] In-service dates are estimated during preliminary design and permitting stages of a project; date shifted to reflect actual design and construction schedule.
180 | Mission Substation 230kV Rebuild |  |  | San Diego, San Diego | Rebuilding the Mission Substation, increase 230kV bus rating to 3k Amps. Replacing 230kV disconnects to latest standards. Replacing control shelter and equipment. Equipment was upgraded to meet standards, increase reliability and replace aging infrastructure | Substation - Multiple | Upgrade/Retrofit | NA | NA | Reliability | Age/Condition | NA | NA | 2024-10-30 | NA | NA | Wires - Replacement Alternative | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 9 | 230 | 230kV | 4.1 | 2014-01071-ZZ | QS00373 | 1 | 18140 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-04-22 | Work Order Authorization | 2019 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | 2018-08-22 | 2022-06-30 | 2021-04-23 | Multiple Options [See Notes] | NA | FALSE | 39512 | NA ¦ NA | 36157.7246 | 13053.7802 | 3769.3878 | 545.109 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2020 ¦ 2021 ¦ 2022 | 9716.9998 | 3834.7014 | 9573.6459 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0% | [Reason for Change in In-Service Date] In-service dates are estimated during preliminary design and permitting stages of a project; date shifted to reflect actual design and construction schedule.
181 | 3 ROOTS TL6906, TL677 & TL668 |  |  | San Diego, San Diego | 3 Roots TL6906, TL677 & TL668. It is a costumer Relocation Project. | Transmission Line - Multiple | Relocate | Upgrade/Retrofit | NA | Work Requested by Others | Facility Relocation | NA | NA | 2024-01-09 12:00 | 11 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.8 | NA | 69 | NA | 1.4 | 2018-0188 | QS00361 | 1 | 18143 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-02-07 | Work Order Authorization | 2019 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Advice Letter | 2021-03-05 | Approved | 2021 | Construction (10%-25%) | NA | 2021-06-01 | 2020-12-31 | 2025-12-30 | NA | NA | TRUE | NA | NA ¦ NA | 1446.4533 | 520.7259 | -1006.8419 | 395.3005 | -7747.1456 | 5503.3886 | 2105.6419 | 1915.8813 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 ¦ 2025 | -133.0652 | 207.7765 | 29.3604 | 1.4967 | 0 | 1915.8813 | 0% | NA ¦ NA | 6.4 | NA | 0% | 100% | ; Substation rebuild, see description for upgrades
182 | NEW DOWNTOWN 69/12KV |  |  | San Diego, San Diego | New Downtown Substation 69 ¦12kV | Substation - Multiple | New | NA | NA | Load Growth | New Substation | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 8 | 4.5 | 12 ¦69 | 12kV ¦69kV | 4.2 | 2024-9876 | QS00318 | 1 | 18251 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2018-04-05 | Work Order Authorization | 2019 | NA | FALSE | NA | NA | NA | FALSE | Expected PEA Completion | NA | NA | NA | NA | NA | NA | NA | NA | NA | Planning | NA | NA | 2031-12-31 | NA | Land Rights | NA | TRUE | 501 | NA ¦ NA | 108993.952 | 51.3482 | 54.0713 | 10.0565 | 193.879 | 207.6607 | 25.2125 | 322.5629 | 3636.681 | 2960.4312 | 2380.078 | 2362.1993 | 0 | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 ¦ 2024 | 51.3482 | 54.0713 | 10.0565 | 193.879 | 207.6607 | 0 | 0% | NA ¦ NA | 1.9 | NA | 0% | 100% | [Age of Asset]
183 | [Programmatic] Trans Fiber Links HFTD |  |  | NA | Install ADSS and or OPGW on existing Transmission overhead structures to support the Wildfire Mitigation Plan | Other | New | NA | NA | Wildfire Mitigation | NERC CIP Compliance | NA | NA | NA | NA | NA | NA | NA | HFTD Tier 2 ¦ HFTD Tier 3 | TRUE ¦ TRUE ¦ TRUE | FALSE | NA |  | NA | NA | Multiple | NA | 1.1 | Multiple | QBL0100 | 73 | 19134 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-11-16 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | NA | NA | NA | NA | NA | NA | Operational | NA | NA | 2024-12-31 | NA | NA | NA | TRUE | NA | NA ¦ NA | 0 | 434.8822 | 496.6618 | 1241.9437 | 2396.3754 | 2595.9306 | 8439.0326 | 26941.0742 | 29199.9869 | 33938.448 | 38339.8398 | 35853.0877 | 3615.112 | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 326.8917 | 163.9221 | 152.0779 | 1032.388 | 2021.6798 | 10341.1577 | 0% | NA ¦ NA | 6.9 | NA | 13.55% | 86.45% | [Age of Asset] Unable to provide age of asset for Programmatic budget codes
184 | A CMP_T0_LR_TL689_Z614851X_NON_TT |  |  | San Diego, San Diego | Two poles are being replaced with foundation poles (Z12466, Z614851), one pole topped (Z12469), and one RFS pole (Z12467). | Other | New | New | NA | Reliability | System Operations | NA | NA | 2024-06-20 | 67;44 | NA | NA | NA | HFTD Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 7 | NA | NA | NA | 1.1 | TL689 Z614851/Z12466 | QBL0100 | 1 | 19134 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-08-21 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | 2020-05-28 | 2021-12-31 | 2022-11-30 | NA | NA | TRUE | NA | NA ¦ NA | 1661.2626 | 249.3781 | 69.8871 | 225.8063 | 735.6259 | 322.1461 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2023 ¦ 2024 | 0 | 0 | 0 | 1339.1165 | 322.1461 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [Project Description - What] Fiber infrastructure build supports all transmission, distribution, substation, and IT equipment/systems for operations, metering, and real time monitoring.
185 | A FBI TL6945 LH OLV |  |  | San Diego, San Diego | The project will include stringing 3.1 miles of new DNA-30411 ADSS conductor and about 2000 ft of DNO-11177 OPGW conductor, installing fiber attachments on existing transmission/distribution poles and installing fiber splice boxes. The conductor will enter Olivenhain and Lake Hodges substation overhead, attaching to existing substation infrastructure. It will also include lowering the crossarm on Z712320 and resagging the distribution conductor from Z220660 to Z201929 to mitigate clearances between the 69kV conductors and 12kV conductors. I | Other | New | New | NA | Reliability | System Operations | NA | NA | 2024-04-23 | NA | NA | NA | NA | HFTD Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 4.3 | NA | NA | NA | 1.1 | 2019-4014 | QBL0100 | 1 | 19134 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-03-02 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | 2023-01-04 | 2022-06-01 | 2023-07-04 | NA | NA | TRUE | NA | NA ¦ NA | 1519.0084 | 69.9423 | 132.3647 | 421.6995 | 624.975 | 270.0269 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2023 ¦ 2024 | 0 | 0 | 0 | 1248.9816 | 270.0269 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [Project Description - What] Fiber infrastructure build supports all transmission, distribution, substation, and IT equipment/systems for operations, metering, and real time monitoring.
186 | A FBI TL6930 ESCONDIDO OLIVEHAIN |  |  | Escondido, San Diego | The project will include stringing 2.2 miles of new DNA-30411 ADSS conductor (including 1.1 miles of underground ADSS, 0.1 miles of which will require new trenching), installing fiber attachments, and installing fiber splice boxes. It will also include reframing the transmission insulators on Z510521 and Z712314 to deadend attachments and the subsequent conductor work that follows. | Other | New | New | NA | Reliability | System Operations | NA | NA | 2024-04-23 | NA | NA | NA | NA | HFTD Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 3.8 | NA | NA | NA | 1.1 | 2019-4016 | QBL0100 | 1 | 19134 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-04-30 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | 2023-10-23 | 2022-06-01 | 2024-01-18 | NA | NA | TRUE | NA | NA ¦ NA | 1019.9702 | 35.8459 | 155.8618 | 278.3722 | 608.4003 | -58.5101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2024 | 0 | 0 | 0 | 0 | 1019.9702 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [Project Description - What] Fiber infrastructure build supports all transmission, distribution, substation, and IT equipment/systems for operations, metering, and real time monitoring.
187 | A TL23022/23023 MISSION EL R2 |  |  | San Diego, Lakeside, Rancho San Diego | Reinforcement of all Towers. installing 15.5 miles of OPGW | Other | New | New | NA | Reliability | System Operations | NA | NA | 2024-11-09 | NA | NA | NA | NA | HFTD Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 39.57 | NA | NA | NA | 1.1 | 2009-00009-ZZ | QBL0100 | 1 | 19134 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2022-10-20 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Engineering more than 50% complete | NA | 2025-02-01 | 2024-10-24 | 2025-05-01 | NA | NA | TRUE | NA | NA ¦ NA | 2506.5998 | 3.6165 | 134.6871 | 340.2847 | 378.6109 | 1385.2135 | 8.5584 | 17.2052 | 0 | 0 | 0 | 0 | 2480.8361 | NA | NA | 2025 | 0 | 0 | 0 | 0 | 0 | 2506.5998 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [Project Description - What] Fiber infrastructure build supports all transmission, distribution, substation, and IT equipment/systems for operations, metering, and real time monitoring.
188 | A FBI_T2_L3_TL23051_Z873123_NONTT |  |  | San Diego, Poway | Install Fiber Sycamore to Chicarita Sub ( 5.8 miles).. Install Fiber from Chicarita sub to Artesia (5 miles) | Other | New | New | NA | Reliability | System Operations | NA | NA | 2024-03-02 | NA | NA | NA | NA | HFTD Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 1.88 | NA | NA | NA | 1.1 | 2009-00014-ZZ | QBL0100 | 1 | 19134 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2022-10-20 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Engineering more than 50% complete | NA | 2025-05-25 | 2024-12-31 | 2025-08-23 | NA | NA | TRUE | NA | NA ¦ NA | 1204.8365 | 60.1466 | 48.0817 | 156.4773 | 699.3388 | 245.0754 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 ¦ 2024 | 60.1466 | 48.0817 | 156.4773 | 699.3388 | 245.0754 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [Project Description - What] Fiber infrastructure build supports all transmission, distribution, substation, and IT equipment/systems for operations, metering, and real time monitoring.
189 | A TL23030 6932 PA LI FIBER L3 |  |  | San Diego County | Engineer and construct 9.3-miles of overhead OPGW-96 fiber optic cable structures between Lilac and Pala substations. | Other | New | New | NA | Reliability | System Operations | NA | NA | 2024-02-03 12:00 | NA | NA | NA | NA | HFTD Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 7.97 | NA | NA | NA | 1.1 | 2014-00958-ZZ | QBL0100 | 1 | 19134 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-04-29 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Engineering more than 50% complete | NA | 2025-08-29 | 2020-12-15 | 2025-10-24 | NA | NA | TRUE | NA | NA ¦ NA | 4537.171 | 122.4822 | 309.0717 | 676.0852 | 1731.2528 | 1119.5253 | 95.0262 | 182.3588 | 0 | 0 | 0 | 0 | 4259.786 | NA | NA | 2025 | 0 | 0 | 0 | 0 | 0 | 4537.171 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [Project Description - What] Fiber infrastructure build supports all transmission, distribution, substation, and IT equipment/systems for operations, metering, and real time monitoring.
190 | A TL689 BERNARDO FELECIT R4 |  |  | San Diego, San Diego | Engineer and construct 6.3 Miles of Overhead (OH) ADSS-96 fiber on 87 poles. Replace 9 new steel poles. 800 feet of UG fiber only trench & conduit from last pole to Felicita substation. Terminate, and test at substation control shelters, (Separate work orders for each substation) .Project is in High Fire Threat District (HFTD). This project is CATEX (Categorically Excluded) from CEQA (California Environmental Quality Act) | Other | New | New | NA | Reliability | System Operations | NA | NA | 2024-06-20 | 39;78;78;48;59;54;57;52 | NA | NA | NA | HFTD Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 7 | NA | NA | NA | 1.1 | 2014-00626-ZZ | QBL0100 | 1 | 19134 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2016-08-30 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | 2024-01-08 | 2018-06-20 | 2024-04-17 | NA | NA | TRUE | NA | NA ¦ NA | 2995.7115 | 520.1728 | 171.5073 | 616.5232 | 301.8656 | 1101.1389 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2024 | 0 | 0 | 0 | 0 | 2995.7115 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [Project Description - What] Fiber infrastructure build supports all transmission, distribution, substation, and IT equipment/systems for operations, metering, and real time monitoring.
191 | A TL635 LOS COCHES CREELMAN SUBS |  |  | Ramona, San Diego | This project installs a fiber optic connection between Creelman Substation and Los Coches Substation. | Other | New | New | NA | Reliability | System Operations | NA | NA | 2024-01-09 12:00 | NA | NA | NA | NA | HFTD Tier 3 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 10.5 | NA | NA | NA | 1.1 | 2014-01080-ZZ | QBL0100 | 1 | 19134 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-01-28 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Construction (under 10%) | NA | 2021-11-01 | 2021-06-01 | 2022-03-23 | NA | NA | TRUE | NA | NA ¦ NA | 1778.8453 | 416.4757 | 3151.6998 | 326.408 | 65.2845 | -2342.3427 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2022 ¦ 2023 ¦ 2024 | 0 | 0 | 4055.9034 | 65.2845 | -2342.3427 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [Project Description - What] Fiber infrastructure build supports all transmission, distribution, substation, and IT equipment/systems for operations, metering, and real time monitoring.
192 | A TL6917 CREELMAN SYCAMORE CYN |  |  | Ramona, San Diego | This project installs a fiber optic connection between Sycamore Canyon Substation and Creelman Substation. | Other | New | New | NA | Reliability | System Operations | NA | NA | 2024-01-09 12:00 | 27 | NA | NA | NA | HFTD Tier 3 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 12.2 | NA | NA | NA | 1.1 | 2014-01079-ZZ | QBL0100 | 1 | 19134 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-01-28 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Construction (under 10%) | NA | 2021-11-01 | 2021-06-01 | 2022-02-23 | NA | NA | TRUE | NA | NA ¦ NA | 1951.0693 | 448.6006 | 1162.539 | 211.2685 | 88.8135 | -132.3815 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2022 ¦ 2023 ¦ 2024 | 0 | 0 | 1994.6373 | 88.8135 | -132.3815 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [Project Description - What] Fiber infrastructure build supports all transmission, distribution, substation, and IT equipment/systems for operations, metering, and real time monitoring.
193 | A FBI_T2_L3_TL230001_Z96439_NONTT |  |  | San Diego, San Diego | FBI TL23004-TL23001 MROPS - RBDC Fiber Build | Other | New | New | NA | Reliability | System Operations | NA | NA | 2024-01-16 12:00 | NA | NA | NA | NA | HFTD Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 4.81 | NA | NA | NA | 1.1 | 2014-00950-ZZ | QBL0100 | 1 | 19134 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-07-25 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Engineering more than 50% complete | NA | 2024-12-01 | 2020-12-01 | 2025-02-05 | NA | NA | TRUE | NA | NA ¦ NA | 3799.4439 | 0.085201 | 822.6322 | 547.967 | 1450.8858 | 876.9522 | 82.1357 | 16.0566 | 0 | 0 | 0 | 0 | 3692.076 | NA | NA | 2025 | 0 | 0 | 0 | 0 | 0 | 3799.4439 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [Project Description - What] Fiber infrastructure build supports all transmission, distribution, substation, and IT equipment/systems for operations, metering, and real time monitoring.
194 | A TL6904 ALPINE LOVELAND TRNM FIB |  |  | Alpine, San Diego | Install a level of ADSS fiber on 2.4 miles of TL6904 poles between Alpine Substation and Loveland Substation. Construct ADSS conduit on Z770043 and trench into Loveland Substation. Construct ADSS conduit on Z875063 and trench into Alpine Substation. Construct ADSS conduit on Z770043 and trench into Loveland Substation (to be designed by others). 3 Steel Pole Replacements | Other | New | New | NA | Reliability | System Operations | NA | NA | 2024-03-05 12:00 | 53;53;53 | NA | NA | NA | HFTD Tier 3 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 0.5 | NA | NA | NA | 1.1 | 2019-4008 | QBL0100 | 1 | 19134 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-01-08 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | 2023-06-19 | 2022-08-20 | 2023-11-15 | NA | NA | TRUE | NA | NA ¦ NA | 1706.1822 | 73.2471 | 111.7932 | 327.4758 | 977.8927 | 215.7734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2023 ¦ 2024 | 0 | 0 | 0 | 1490.4089 | 215.7734 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [Project Description - What] Fiber infrastructure build supports all transmission, distribution, substation, and IT equipment/systems for operations, metering, and real time monitoring.
195 | A TL23022/23 MISSION TO LOS COCHE |  |  | San Diego, Santee, Granite Hills, San Diego COunty | Remove and replace 19miles of OHGW with OPGW. | Other | Upgrade/Retrofit | Upgrade/Retrofit | NA | Reliability | System Operations | NA | NA | 2024-11-09 | NA | NA | NA | NA | HFTD Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | TBD |  | 39.57 | NA | NA | NA | 1.1 | 2023-3234 | QBL0100 | 1 | 19134 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-01-11 | Work Order Authorization | 2023 | NA | FALSE | NA | NA | NA | FALSE | TBD | NA | NA | NA | CPUC | NA | Exempt | NA | NA | NA | Engineering more than 50% complete | NA | 2026-07-17 | 2025-12-01 | 2026-08-16 | NA | NA | TRUE | NA | NA ¦ NA | 1665.7305 | 0 | 0 | 0 | 476.3328 | 1024.5013 | 32.5107 | 132.3857 | 0 | 0 | 0 | 0 | 1500.8341 | NA | NA | 2025 | 0 | 0 | 0 | 0 | 0 | 1665.7305 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0%
196 | A FBI TL23002/23010 SOSA |  |  | Camp Pendleton | Remove and replace 18 miles of OHGW with OPGW | Other | Replace | Upgrade/Retrofit | NA | Reliability | System Operations | NA | NA | 2024-02-03 12:00 | NA | NA | NA | NA | HFTD Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | TBD |  | 17.74 | NA | NA | NA | 1.1 | 2023-3433 | QBL0100 | 1 | 19134 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-06-28 | Work Order Authorization | 2024 | NA | FALSE | NA | NA | NA | FALSE | TBD | NA | NA | NA | CPUC | NA | Exempt | NA | NA | NA | Engineering less than 50% complete | NA | 2027-05-07 | 2027-04-30 | 2027-08-05 | NA | NA | FALSE | NA | NA ¦ NA | 1231.8648 | 0 | 0 | 0 | 24.3011 | 1020.6748 | 16.5423 | 69.9206 | 76.3331 | 24.0928 | 0 | 0 | 1044.9759 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0%
197 | A FBI TL23006 SO SA |  |  | Camp Pendleton | Remove and replace 18 miles of OHGW with OPGW | Other | Replace | Upgrade/Retrofit | NA | Reliability | System Operations | NA | NA | 2024-02-03 12:00 | NA | NA | NA | NA | HFTD Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | TBD |  | 17.74 | NA | NA | NA | 1.1 | 2023-3431 | QBL0100 | 1 | 19134 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-06-28 | Work Order Authorization | 2024 | NA | FALSE | NA | NA | NA | FALSE | TBD | NA | NA | NA | CPUC | NA | Exempt | NA | NA | NA | Engineering less than 50% complete | NA | 2027-04-22 | 2027-01-30 | 2027-07-21 | NA | NA | FALSE | NA | NA ¦ NA | 1881.1574 | 0 | 0 | 0 | 165.3863 | 1414.7047 | 29.885 | 126.3167 | 137.9014 | 6.9632 | 0 | 0 | 1580.0911 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0%
198 | A FBI TL23052/23007 SO TA |  |  | Camp Pendleton | Remove and replace 7 miles of OHGW with OPGW | Other | Replace | Upgrade/Retrofit | NA | Reliability | System Operations | NA | NA | 2024-02-03 | NA | NA | NA | NA | HFTD Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | TBD |  | 8.23 | NA | NA | NA | 1.1 | 2023-3434 | QBL0100 | 1 | 19134 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-06-28 | Work Order Authorization | 2024 | NA | FALSE | NA | NA | NA | FALSE | TBD | NA | NA | NA | CPUC | NA | Exempt | NA | NA | NA | Engineering less than 50% complete | NA | 2027-04-15 | 2026-11-15 | 2027-07-14 | NA | NA | FALSE | NA | NA ¦ NA | 1012.0133 | 0 | 0 | 0 | 176.1924 | 656.2647 | 14.8048 | 62.5763 | 68.3152 | 33.8599 | 0 | 0 | 832.4571 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0%
199 | A FBI TL23004/23001 SAN LUIS REY |  |  | San Diego, San Diego County | Remove and replace 6miles of OHGW with OPGW | Other | Upgrade/Retrofit | Upgrade/Retrofit | NA | Reliability | System Operations | NA | NA | 2024-01-16 12:00 | NA | NA | NA | NA | HFTD Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | TBD |  | 41.64 | NA | NA | NA | 1.1 | 2023-3412 | QBL0100 | 1 | 19134 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-06-07 | Work Order Authorization | 2023 | NA | FALSE | NA | NA | NA | FALSE | TBD | NA | NA | NA | CPUC | NA | Exempt | NA | NA | NA | Construction (under 10%) | NA | 2026-10-29 | 2025-12-31 | 2027-01-27 | NA | NA | TRUE | NA | NA ¦ NA | 1790.9554 | 0 | 0 | 0 | 369.4347 | 1264.9922 | 30.8609 | 125.6676 | 0 | 0 | 0 | 0 | 1634.4269 | NA | NA | 2025 | 0 | 0 | 0 | 0 | 0 | 1790.9554 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0%
200 | A TL685 SANTA YSABEL TO WA R1 |  |  | San Diego County | Install approximately 11 miles of 96 count fiber optic DNA-30411. Installation will begin at Warner Springs Substation and terminate at Santa Ysabel Substation. There are a total of 155 structures along the TL at which fiber optic will be installed. | Other | New | New | NA | Reliability | System Operations | NA | NA | 2024-01-09 12:00 | NA | NA | NA | NA | HFTD Tier 2 ¦ HFTD Tier 3 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 13.33 | NA | NA | NA | 1.1 | 2014-00624-ZZ | QBL0100 | 1 | 19134 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-01-27 | Work Order Authorization | 2019 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | 2020-05-29 | 2020-11-30 | 2022-09-28 | NA | NA | FALSE | NA | NA ¦ NA | 1057.108 | 399.3816 | 188.2618 | 146.2065 | 84.7003 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2022 ¦ 2023 | 0 | 0 | 972.4077 | 84.7003 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0%
201 | A FBI_T2_L2_TL683_Z518466_NONTT |  |  | Valley Center, San Diego County | This project installs 9.7 miles of ADSS fiber | Other | New | New | NA | Reliability | System Operations | NA | NA | 2024-02-13 12:00 | 53;53;24;53;36;53;53;41 | NA | NA | NA | HFTD Tier 2 ¦ HFTD Tier 3 | FALSE ¦ TRUE ¦ FALSE | FALSE | TBD |  | 11.86 | NA | NA | NA | 1.1 | 2014-00983-ZZ | QBL0100 | 1 | 19134 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-01-08 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | TBD | NA | NA | NA | CPUC | NA | Exempt | NA | NA | NA | Engineering more than 50% complete | NA | 2025-09-16 | 2022-12-01 | 2025-12-15 | NA | NA | TRUE | NA | NA ¦ NA | 1027.0425 | 4.9781 | 50.311 | 288.6427 | 409.4544 | 182.2426 | 21.0375 | 70.3762 | 0 | 0 | 0 | 0 | 935.6288 | NA | NA | 2025 | 0 | 0 | 0 | 0 | 0 | 1027.0425 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0%
202 | [Programmatic] PSPS Engineering Enhancements |  |  | NA | Mitigate the impact to customers and communities involved in PSPS events by installing additional remote sectionalizing devices within the HFTD. ​ | Other | New | Upgrade/Retrofit | NA | Wildfire Mitigation | Fire Protection | NA | NA | NA | NA | NA | NA | NA | HFTD Tier 2 ¦ HFTD Tier 3 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | NA | NA | NA | NA | 1.2 | Multiple | QS00375 | 7 | 19245 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-11-16 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Operational | NA | NA | 2024-12-31 | NA | NA | NA | TRUE | NA | NA ¦ NA | 0 | 545.5973 | 140.7236 | 86.0347 | 54.0949 | 74.7327 | 16.0985 | 158.2107 | 173.414 | 286.2554 | 312.5083 | 43.738 | 0 | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 | -4.4722 | 117.009 | 904.8739 | 62.5786 | 51.9799 | -47.7773 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0%
203 | [Programmatic] HFTD Undergrounding |  |  | NA | Conversion of OH dist. lines to UG dist. lines within the HFTD | Other | Upgrade/Retrofit | NA | NA | Wildfire Mitigation | Facility Relocation | NA | NA | NA | NA | NA | NA | NA | HFTD Tier 2 ¦ HFTD Tier 3 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | NA | NA | NA | NA | 1.1 | NA | QBL0081 | 7 | 19246 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-12-08 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Operational | NA | NA | 2024-12-31 | NA | NA | NA | TRUE | NA | NA ¦ NA | 0 | 365.5529 | -259.1355 | -20.1032 | 747.9368 | -567.5756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 ¦ 2024 | 362.2653 | -266.5756 | -20.4219 | 758.9833 | -567.5756 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0%
204 | [Programmatic] HFTD Undergrounding |  |  | NA | Blanket budget for High Fire Threat District undergrounding work. This is an electric distribution blanket budget. The forecasted costs shown for this project are only the FERC-specific transmission costs. | Transmission Line/Substation | Upgrade/Retrofit | NA | NA | Reliability | Substation Reliability | NA | NA | NA | NA | NA | NA | NA | Tier 1 ¦ Tier 2 ¦ Tier 3 | FALSE ¦ FALSE ¦ TRUE | FALSE | NA |  | NA | NA | Multiple | NA | 1.1 | Multiple | QBL0081 | 7 | 19246 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-12-08 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Operational | NA | NA | 2024-12-31 | NA | NA | NA | TRUE | NA | NA ¦ NA | 0 | 6.9721 | 33.6557 | 2349.5081 | 144.9496 | 293.508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 | 0 | 19.8374 | 267.2411 | 2238.4636 | 17.4533 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 13.55% | 86.45% | [Wildfire Related ] Project is part of wildfire mitigation program
205 | [Programmatic] Fire Science Enhancement |  |  | NA | This project will enhance the fire science capabilities at SDGE. New tools and technologies will be developed to greatly enhance current technologies such as the fire potential index and create the next generation of fire weather tools. Partnerships with leading academic innovators on the cutting edge of research and development in fire science will ensure SDGE remains an industry leader. | Other - Operations Tech | NA | NA | NA | Wildfire Mitigation | Fire Protection | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | NA | NA | NA | NA | 1.2 | Multiple | QBL0096 | 3 | 19248 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-11-22 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Operational | NA | NA | 2024-12-31 | NA | NA | NA | TRUE | NA | NA ¦ NA | 0 | 201.3864 | 240.0384 | 283.2154 | 233.0757 | 161.077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 | 0 | 486.6925 | 283.2154 | 233.0757 | 161.077 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0%
206 | Urban Substation Rebuild |  |  | San Diego, San Diego | Urban Substation - 12kV Switchgear & Capacitor Replacement | Substation - Other Equipment | Upgrade/Retrofit | NA | NA | Reliability | Age/Condition - Replace Other Substation Equipment | NA | NA | 2024-09-04 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 0.56634 | 69 | 69kV ¦12kV | 4.1 | 2021-2065 | QS00397 | 1 | 19252 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-08-23 | Work Order Authorization | 2019 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Construction (10%-25%) | NA | 2023-07-13 | 2027-03-31 | 2027-09-03 | Other [See Notes] | NA | FALSE | 5891.5596 | NA ¦ NA | 24037.6998 | 222.9403 | 311.129 | 640.6636 | 1245.1791 | 9025.8531 | 1501.48 | 4345.4496 | 4411.5963 | 2330.2694 | 0 | 0 | 11448.9046 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | 31.5 | NA | 0% | 100% | [Reason for Change in In-Service Date] In-service dates are estimated during preliminary design and permitting stages of a project; date shifted to reflect actual design and construction schedule.
207 | Electric Transmission EMS/SCADA Replacement |  |  | NA | Replacement of Energy Management System (EMS) application and supporting infrastructure at Electric Transmission's Mission Control Center and Metro Control Center | Other - Operations Tech | Replace | NA | NA | Reliability | NERC CIP Compliance | NERC CIP Compliance | NA | NA | 46 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69 ¦500 | NA | 1.1 | NA | QS00452 | 1 | 20125 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-04-01 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Engineering less than 50% complete | NA | NA | 2022-06-30 | NA | NA | NA | FALSE | NA | NA ¦ NA | 12485.3403 | 0 | 0 | 0 | 0 | 3358.6619 | 2632.9048 | 4163.5492 | 2330.2245 | 0 | 0 | 0 | 3358.6619 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | 1.8 | NA | 13.55% | 86.45%
208 | [Programmatic] Transmission CMP Non HFTD |  |  | NA | Remediate CMP Issues in the Non-HFTD Zone | Transmission Line - Pole/Tower | Replace | NA | NA | Asset Condition | Age/Condition | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | Multiple | NA | 1.2 | Multiple | QBL0098 | 1037 | 20126 | NA ¦ NA ¦ NA ¦ NA | TRUE | NA | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | NA | NA | NA | NA | NA | TRUE | NA | NA ¦ NA | 0 | 30169.5627 | 33647.9026 | 33235.3717 | 35515.2229 | 24417.6593 | 8422.0971 | 42782.6871 | 45246.5588 | 48071.8105 | 51046.5867 | 54369.9968 | 21384.2451 | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 23417.2039 | 33977.0589 | 32930.6062 | 35580.5058 | 23854.0378 | 27780.5797 | 0% | NA ¦ NA | NA ¦ NA | NA | 13.55% | 86.45%
209 | 53551 ACMP_T0_L2_TL6925_Z273965_14637 |  |  | El Cajon, San Diego | Remediate CMP Issues in the Non-HFTD Zone | Transmission Line - Pole/Tower | Replace | NA | NA | Asset Condition | Age/Condition | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.1 | NA | Multiple | NA | 1.1 | 2023-3297 | QBL0098 | 1 | 20126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-06-14 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Engineering more than 50% complete | NA | 2024-07-12 | 2024-12-31 | 2024-07-12 | NA | NA | TRUE | NA | NA ¦ NA | 1780.7861 | 67.0613 | 186.6442 | 343.7054 | 266.8045 | 916.5706 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2024 | 0 | 0 | 0 | 0 | 1780.7861 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 13.55% | 86.45% | [Age of Asset] Unable to provide age of asset for Programmatic budget codes
210 | A CMP_T0_TL630_Z475724_TT13577 |  |  | El Cajon, San Diego | Remediate CMP Issues in the Non-HFTD Zone | Transmission Line - Pole/Tower | Replace | NA | NA | Asset Condition | Age/Condition | NA | NA | 2024-01-23 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.1 | NA | 69 ¦500 | NA | 1.1 | TL630 Z475724 | QBL0098 | 1 | 20126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2021-03-08 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | 2022-12-16 | 2025-12-31 | 2022-12-16 | NA | NA | TRUE | NA | NA ¦ NA | 2846.6952 | 127.1297 | 283.6215 | 547.349 | 1233.3298 | 551.1445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2024 | 0 | 0 | 0 | 0 | 2846.6952 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 13.55% | 86.45% | [Age of Asset] Unable to provide age of asset for Programmatic budget codes
211 | A CMP_T0_L2_TL600_Z91160_14180 |  |  | San Diego, San Diego | Remediate CMP Issues in the Non-HFTD Zone | Transmission Line - Pole/Tower | Replace | NA | NA | Asset Condition | Age/Condition | NA | NA | 2024-03-12 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69 ¦500 | NA | 1.1 | TL600 Z91160 | QBL0098 | 1 | 20126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-08-21 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | 2022-02-04 | 2020-12-31 | 2022-02-04 | NA | NA | TRUE | NA | NA ¦ NA | 1442.3729 | 161.2135 | 121.8526 | 736.2249 | 396.4809 | 26.4083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2023 ¦ 2024 | 0 | 0 | 0 | 1415.9646 | 26.4083 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 13.55% | 86.45%
212 | A CMP_T0_L2_TL6908_Z618845_11163 |  |  | Escondido, San Diego | Remediate CMP Issues in the Non-HFTD Zone | Transmission Line - Pole/Tower | Replace | NA | NA | Asset Condition | Age/Condition | NA | NA | 2024-07-26 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69 ¦500 | NA | 1.1 | TL6908 Z618845 | QBL0098 | 1 | 20126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-03-06 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | 2021-07-01 | 2023-12-31 | 2021-07-01 | NA | NA | TRUE | NA | NA ¦ NA | 1016.0318 | 83.606 | 876.3129 | 33.283 | 22.972 | -0.14218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 | 0 | 959.9189 | 33.283 | 22.972 | -0.14218 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 13.55% | 86.45%
213 | A TL628 CMP TRANSMISSION P R9 |  |  | San Diego County | Remediate CMP Issues in the Non-HFTD Zone | Transmission Line - Pole/Tower | Replace | NA | NA | Asset Condition | Age/Condition | NA | NA | 2024-02-22 | 47;9 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.1 | NA | 69 ¦500 | NA | 1.1 | TL628 Z282087&Z86824 | QBL0098 | 1 | 20126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2017-09-11 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | 2019-06-03 | 2018-12-31 | 2019-06-03 | NA | NA | FALSE | NA | NA ¦ NA | 1868.355 | 1141.6502 | 228.2153 | -11.9693 | 8.6112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 | 1643.4978 | 228.2153 | -11.9693 | 8.6112 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 13.55% | 86.45%
214 | A CMP_T0_L3_TL655/699_ STRUCTURES |  |  | San Diego, San Diego | Remediate CMP Issues in the Non-HFTD Zone | Transmission Line - Pole/Tower | Replace | NA | NA | Asset Condition | Age/Condition | NA | NA | 2024-03-16 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.1 | NA | 69 ¦500 | NA | 1.1 | 2022-2738 | QBL0098 | 1 | 20126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2015-02-11 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | 2023-11-06 | 2015-12-31 | 2023-11-06 | NA | NA | TRUE | NA | NA ¦ NA | 1714.3941 | 129.4512 | 63.8041 | 373.7149 | 700.6281 | 235.7896 | 37.0414 | 7.2415 | 0 | 0 | 0 | 0 | 1670.1113 | NA | NA | 2025 | 0 | 0 | 0 | 0 | 0 | 1714.3941 | 0% | NA ¦ NA | NA ¦ NA | NA | 13.55% | 86.45% | [Age of Asset] Unable to provide age of asset for Programmatic budget codes
215 | A CMP_T0_L3_TL13815_Z731374_TT119 |  |  | San Diego, San Diego | Remediate CMP Issues in the Non-HFTD Zone | Transmission Line - Pole/Tower | Replace | NA | NA | Asset Condition | Age/Condition | NA | NA | 2024-02-08 12:00 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69 ¦500 | NA | 1.1 | TL13815 Z731374 | QBL0098 | 1 | 20126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2015-06-09 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | 2020-04-21 | 2017-12-31 | 2020-04-21 | NA | NA | FALSE | NA | NA ¦ NA | 1588.4538 | 1150.584 | 121.7024 | 77.7803 | 11.3399 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 | 0 | 1499.3336 | 77.7803 | 11.3399 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 13.55% | 86.45%
216 | A TL638 Z61344 CMP POLE RE R4 |  |  | San Diego, San Diego | Remediate CMP Issues in the Non-HFTD Zone | Transmission Line - Pole/Tower | Replace | NA | NA | Asset Condition | Age/Condition | NA | NA | 2024-03-12 12:00 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69 ¦500 | NA | 1.1 | TL638 Z61344 | QBL0098 | 1 | 20126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2015-11-24 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | 2019-10-12 | 2017-12-31 | 2019-10-12 | NA | NA | FALSE | NA | NA ¦ NA | 1260.3555 | 993.4244 | 2.8199 | 6.8033 | 16.5441 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 | 1234.1882 | 2.8199 | 6.8033 | 16.5441 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 13.55% | 86.45%
217 | A TL680B PASS FAIL REPORT 19 TRAN |  |  | Vista, San Diego | Remediate CMP Issues in the Non-HFTD Zone | Transmission Line - Pole/Tower | Replace | NA | NA | Asset Condition | Age/Condition | NA | NA | 2024-05-24 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69 ¦500 | NA | 1.1 | TL680B Group | QBL0098 | 1 | 20126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2017-06-23 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | 2019-06-29 | 2022-12-31 | 2019-06-29 | NA | NA | TRUE | NA | NA ¦ NA | 2589.5531 | 944.342 | 61.423 | 12.886 | 42.1588 | 61.4424 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 ¦ 2024 | 2411.6429 | 61.423 | 12.886 | 42.1588 | 61.4424 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 13.55% | 86.45%
218 | A CMP_T0_L3_TL651_Z730387_TT13534 |  |  | San Diego, San Diego | Remediate CMP Issues in the Non-HFTD Zone | Transmission Line - Pole/Tower | Replace | NA | NA | Asset Condition | Age/Condition | NA | NA | 2024-03-16 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69 ¦500 | NA | 1.1 | TL651 Z730387 | QBL0098 | 1 | 20126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2018-01-31 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | 2021-04-09 | 2019-12-31 | 2021-04-09 | NA | NA | TRUE | NA | NA ¦ NA | 2793.4327 | 89.7299 | 1419.8572 | 805.0292 | 30.8096 | 323.032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2022 ¦ 2023 ¦ 2024 | 0 | 0 | 2439.591 | 30.8096 | 323.032 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 13.55% | 86.45%
219 | A TL23026 13815 Z189540 IN R3 |  |  | National City, San Diego | Remediate CMP Issues in the Non-HFTD Zone | Transmission Line - Pole/Tower | Replace | NA | NA | Asset Condition | Age/Condition | NA | NA | 2024-02-22 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69 ¦500 | NA | 1.1 | 2019-4001 | QBL0098 | 1 | 20126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2022-06-29 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Planning | NA | 2021-04-08 | 2021-08-22 | 2021-04-08 | NA | NA | FALSE | NA | NA ¦ NA | 3476.8948 | 551.4191 | 2840.4149 | 1.8014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 | 0 | 3475.0934 | 1.8014 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 13.55% | 86.45%
220 | A CMP_T0_L2_TL652_Z214987X_15018 |  |  | San Diego, San Diego | Remediate CMP Issues in the Non-HFTD Zone | Transmission Line - Pole/Tower | Replace | NA | NA | Asset Condition | Age/Condition | NA | NA | 2024-03-12 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69 ¦500 | NA | 1.1 | TL652 Group 01 | QBL0098 | 1 | 20126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-08-19 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | 2020-12-31 | 2020-12-31 | 2020-12-31 | NA | NA | TRUE | NA | NA ¦ NA | 1219.005 | 294.8847 | 495.9643 | 29.2382 | 104.0368 | 51.3037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 | 0 | 1034.4264 | 29.2382 | 104.0368 | 51.3037 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 13.55% | 86.45%
221 | A CMP_T0_L2_TL608_Z371845X_NON_TT |  |  | NA | Remediate CMP Issues in the Non-HFTD Zone | Transmission Line - Pole/Tower | Replace | NA | NA | Asset Condition | Age/Condition | NA | NA | 2024-03-16 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69 ¦500 | NA | 1.1 | TL608 Group 01 | QBL0098 | 1 | 20126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-08-13 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | 2022-06-17 | 2021-12-31 | 2022-06-17 | NA | NA | TRUE | NA | NA ¦ NA | 1360.911 | -15.0152 | 82.5021 | 1006.9006 | 92.0874 | 194.4361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2023 ¦ 2024 | 0 | 0 | 0 | 1166.4749 | 194.4361 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 13.55% | 86.45% | [Age of Asset] Unable to provide age of asset for Programmatic budget codes
222 | A CMP_T0_L2_TL617_2320469X_NON_TT |  |  | San Diego, San Diego | Remediate CMP Issues in the Non-HFTD Zone | Transmission Line - Pole/Tower | Replace | NA | NA | Asset Condition | Age/Condition | NA | NA | 2024-03-12 12:00 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69 ¦500 | NA | 1.1 | TL617 Group 01 | QBL0098 | 1 | 20126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-09-27 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | 2021-11-25 | 2020-12-31 | 2021-11-25 | NA | NA | TRUE | NA | NA ¦ NA | 1391.8988 | 435.3847 | 315.8678 | 464.5618 | 61.7387 | 114.3457 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2022 ¦ 2023 ¦ 2024 | 0 | 0 | 1215.8144 | 61.7387 | 114.3457 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 13.55% | 86.45%
223 | A CMP_T0_L2_TL684_Z114414X_NON_TT |  |  | San Marcos, San Diego | Remediate CMP Issues in the Non-HFTD Zone | Transmission Line - Pole/Tower | Replace | NA | NA | Asset Condition | Age/Condition | NA | NA | 2024-03-02 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69 ¦500 | NA | 1.1 | TL684 Group 03 | QBL0098 | 1 | 20126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-09-27 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | 2021-01-15 | 2020-12-31 | 2021-01-15 | NA | NA | TRUE | NA | NA ¦ NA | 1022.9088 | 274.3038 | 611.2737 | 64.1403 | 25.0141 | 48.177 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 | 0 | 885.5775 | 64.1403 | 25.0141 | 48.177 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 13.55% | 86.45%
224 | A CMP_T0_L2_TL684_Z815163X_NON_TT |  |  | San Marcos, San Diego | Remediate CMP Issues in the Non-HFTD Zone | Transmission Line - Pole/Tower | Replace | NA | NA | Asset Condition | Age/Condition | NA | NA | 2024-03-02 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69 ¦500 | NA | 1.1 | TL684 Group 05 | QBL0098 | 1 | 20126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-09-27 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | 2021-03-02 | 2020-12-31 | 2021-03-02 | NA | NA | TRUE | NA | NA ¦ NA | 1309.6375 | 436.3207 | 133.553 | -25.3601 | 704.0905 | 61.0333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 | 0 | 569.8737 | -25.3601 | 704.0905 | 61.0333 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 13.55% | 86.45%
225 | A CMP_T0_L2_TL624_Z371343X_NON_TT |  |  | El Cajon, San Diego | Remediate CMP Issues in the Non-HFTD Zone | Transmission Line - Pole/Tower | Replace | NA | NA | Asset Condition | Age/Condition | NA | NA | 2024-03-12 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69 ¦500 | NA | 1.1 | TL624 Group 04 | QBL0098 | 1 | 20126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-10-11 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | 2022-03-26 | 2020-12-31 | 2022-03-26 | NA | NA | TRUE | NA | NA ¦ NA | 1141.7534 | 83.6144 | 212.0273 | 652.9327 | 182.8411 | 10.3378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2023 ¦ 2024 | 0 | 0 | 0 | 1131.4156 | 10.3378 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 13.55% | 86.45%
226 | A CMP_T0_L2_TL603_Z183889X_14421 |  |  | National City, San Diego | Remediate CMP Issues in the Non-HFTD Zone | Transmission Line - Pole/Tower | Replace | NA | NA | Asset Condition | Age/Condition | NA | NA | 2024-02-22 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69 ¦500 | NA | 1.1 | TL603 Z1838893443 | QBL0098 | 1 | 20126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-12-12 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Construction (25%-50%) | NA | 2023-01-10 | 2024-12-31 | 2023-01-10 | NA | NA | TRUE | NA | NA ¦ NA | 2885.2501 | 237.4191 | 566.8735 | 294.3714 | 704.2704 | 1082.3157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2022 ¦ 2023 ¦ 2024 | 0 | 0 | 1094.8542 | 78.7618 | 1711.6342 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 13.55% | 86.45%
227 | A CMP_T0_L2_TL681_Z12922,X_NON_TT |  |  | Escondido, San Diego | Remediate CMP Issues in the Non-HFTD Zone | Transmission Line - Pole/Tower | Replace | NA | NA | Asset Condition | Age/Condition | NA | NA | 2024-02-13 12:00 | 61;61;61;45;51;42 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69 ¦500 | NA | 1.1 | TL681 Group 03 | QBL0098 | 1 | 20126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-02-21 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | 2021-11-01 | 2022-12-31 | 2022-03-19 | NA | NA | TRUE | NA | NA ¦ NA | 1022.8371 | 17.0166 | 222.4498 | 670.626 | 111.0577 | 1.687 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2022 ¦ 2023 ¦ 2024 | 0 | 0 | 910.0924 | 111.0577 | 1.687 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 13.55% | 86.45%
228 | A CMP_T0_LX_TL662 TL6905_COASTAL |  |  | San Diego, San Diego County | Remediate CMP Issues in the Non-HFTD Zone | Transmission Line - Pole/Tower | Replace | NA | NA | Asset Condition | Age/Condition | NA | NA | 2024-05-04 | 33;33;33;33;33;44;33;44 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | Coastal |  | NA | NA | 69 ¦500 | NA | 1.1 | 2023-3590 | QBL0098 | 1 | 20126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-11-14 | Work Order Authorization | 2024 | NA | FALSE | NA | NA | NA | FALSE | TBD | NA | NA | NA | CPUC | NA | Exempt | NA | NA | NA | Operational | NA | 2024-08-12 | 2026-12-31 | 2024-08-12 | NA | NA | FALSE | NA | NA ¦ NA | 1091.6308 | 0 | 0 | 0 | 3.5589 | 1077.8697 | 10.2022 | 0 | 0 | 0 | 0 | 0 | 1081.4286 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 13.55% | 86.45%
229 | A CMP_T0_L3_TL13840_Z579784_11835 |  |  | San Diego, San Diego County | Remediate CMP Issues in the Non-HFTD Zone | Transmission Line - Pole/Tower | Replace | NA | NA | Asset Condition | Age/Condition | NA | NA | 2024-03-12 12:00 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | TBD |  | NA | NA | 69 ¦500 | NA | 1.1 | TL13840 Z579784 | QBL0098 | 1 | 20126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2017-05-03 | Work Order Authorization | 2019 | NA | FALSE | NA | NA | NA | FALSE | TBD | NA | NA | NA | CPUC | NA | Exempt | NA | NA | NA | Operational | NA | 2024-10-11 | 2018-12-31 | 2024-10-11 | NA | NA | TRUE | NA | NA ¦ NA | 4474.9307 | 225.2653 | 17.2361 | 74.0575 | 147.9806 | 3398.0674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 ¦ 2024 | 225.2653 | 17.2361 | 74.0575 | 147.9806 | 3398.0674 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 13.55% | 86.45%
230 | A CMP_T0_L2_TL642_Z184518X_12827 |  |  | San Diego, San Diego County | Remediate CMP Issues in the Non-HFTD Zone | Transmission Line - Pole/Tower | Replace | NA | NA | Asset Condition | Age/Condition | NA | NA | 2024-02-22 | 49;49 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | TBD |  | NA | NA | 69 ¦500 | NA | 1.1 | 2022-2728 | QBL0098 | 1 | 20126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2016-08-15 | Work Order Authorization | 2019 | NA | FALSE | NA | NA | NA | FALSE | TBD | NA | NA | NA | CPUC | NA | Exempt | NA | NA | NA | Operational | NA | 2022-05-25 | 2017-12-31 | 2022-05-25 | NA | NA | FALSE | NA | NA ¦ NA | 2037.5379 | 57.1252 | 76.776 | 383.1893 | 118.5395 | 1121.0804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 13.55% | 86.45%
231 | 2986802 - A CMP_T0_L3_TL618/619_Z579013X_12 |  |  | San Diego, San Diego | Remediate CMP Issues | Transmission Line - Pole/Tower | Replace | NA | NA | Asset Condition | Age/Condition | NA | NA | 2024-06-29 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦FALSE | FALSE | NA |  | NA | NA | 69 ¦500 | NA | 1.1 | 2024-3689 | QBL0092 | 1 | 20126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2015-08-31 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Permitting | NA | NA | 2018-12-31 | NA | NA | NA | TRUE | NA | NA ¦ NA | 1728.819 | 1127.8585 | 161.7617 | 174.0038 | 1635.0634 | 886.8574 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 | 0 | 22.1527 | 3.7452 | 1171.4526 | 3019.1409 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 13.55% | 86.45%
232 | [Programmatic] Transmission CMP HFTD |  |  | Multiple | Transmission CMP HFTD | Transmission Line - Pole/Tower | Replace | NA | NA | Asset Condition | Age/Condition | NA | NA | NA | NA | NA | NA | NA | HFTD Tier 2 ¦ HFTD Tier 3 | FALSE ¦ TRUE ¦FALSE | FALSE | NA |  | NA | NA | Multiple | NA | 1.1 | Multiple | QBL0092 | 363 | 20127 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-11-27 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | TBD | NA | NA | NA | CPUC | NA | Exempt | NA | NA | NA | Operational | NA | NA | 2024-12-31 | 2021-12-18 | NA | NA | TRUE | NA | NA ¦ NA | 0 | 13363.2844 | 10747.9351 | 13176.6035 | 15368.9053 | 8591.7941 | 3079.2223 | 12742.0154 | 13478.9805 | 14324.929 | 15239.157 | 16230.5224 | 6194.1619 | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 12714.7546 | 10686.1059 | 11193.4569 | 16820.15 | 8279.5006 | 8957.5636 | 0% | NA ¦ NA | 2.2 | NA | 13.55% | 86.45%
233 | A CMP_T3_L3_TL50003_Z123862X_1498 |  |  | NA | Remediate CMP Issues | Transmission Line - Pole/Tower | Replace | NA | NA | Asset Condition | Age/Condition | NA | NA | 2024-07-13 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦FALSE | FALSE | NA |  | NA | NA | 69 ¦500 | NA | 1.1 | TL50003 Group 01 | QBL0092 | 1 | 20127 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-12-02 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | 2021-08-30 | 2021-12-31 | 2021-08-30 | NA | NA | FALSE | NA | NA ¦ NA | 1414.7536 | 0 | 1215.4861 | 87.6968 | 111.5707 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2022 ¦ 2023 | 0 | 0 | 1303.183 | 111.5707 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 13.55% | 86.45% | [Age of Asset] Unable to provide age of asset for Programmatic budget codes
234 | A CMP_T0_L3_TL13834_Z29678_10182 |  |  | San Juan Capistrano, Orange | Remediate CMP Issues | Transmission Line - Pole/Tower | Replace | NA | NA | Asset Condition | Age/Condition | NA | NA | 2024-02-29 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦FALSE | FALSE | NA |  | NA | NA | 69 ¦500 | NA | 1.1 | TL13834 Z29678 | QBL0092 | 1 | 20127 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2014-09-10 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | 2022-10-03 | 2015-12-31 | 2022-10-03 | NA | NA | TRUE | NA | NA ¦ NA | 1236.4223 | 151.3453 | 104.0399 | 460.2218 | 365.1485 | 61.3263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2023 ¦ 2024 | 0 | 0 | 0 | 1175.096 | 61.3263 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 13.55% | 86.45%
235 | A CMP_T0_L2_TL694_Z317855_10167 |  |  | Oceanside, San Diego | Remediate CMP Issues | Transmission Line - Pole/Tower | Replace | NA | NA | Asset Condition | Age/Condition | NA | NA | 2024-07-22 12:00 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦FALSE | FALSE | NA |  | NA | NA | 69 ¦500 | NA | 1.1 | TL694 Z317855 | QBL0092 | 1 | 20127 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2018-03-09 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | 2021-12-01 | 2020-12-31 | 2021-12-01 | NA | NA | TRUE | NA | NA ¦ NA | 1513.9345 | 167.9805 | 125.2839 | 215.0283 | 753.0893 | 122.9305 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2023 ¦ 2024 | 0 | 0 | 0 | 1391.004 | 122.9305 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 13.55% | 86.45%
236 | A CMP_T0_L2_TL23010/02_Z223661_TT |  |  | San Diego County | Remediate CMP Issues in the HFTD Zone (Tier 2 & Tier 3) | Transmission Line - Pole/Tower | Replace | NA | NA | Asset Condition | Age/Condition | NA | NA | 2024-02-03 | NA | NA | NA | NA | HFTD Tier 2 | FALSE ¦ TRUE ¦FALSE | FALSE | NA |  | NA | NA | 69 ¦500 | NA | 1.1 | TL23002 Z223661 | QBL0092 | 1 | 20127 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-06-17 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Construction (under 10%) | NA | 2023-08-07 | 2020-12-31 | 2023-08-07 | NA | NA | TRUE | NA | NA ¦ NA | 1642.0456 | 13.9313 | 481.4532 | -246.0084 | 1041.3942 | 350.4391 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2023 ¦ 2024 | 0 | 0 | 0 | 1291.6065 | 350.4391 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 13.55% | 86.45%
237 | A ET/OH&UG MISC CONST INST/RFS |  |  | NA | Remediate CMP Issues | Transmission Line - Pole/Tower | Replace | NA | NA | Asset Condition | Age/Condition | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦FALSE | FALSE | NA |  | NA | NA | 69 ¦500 | NA | 1.1 | NA | QBL0092 | 1 | 20127 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-01-01 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | 2020-10-16 | 2024-12-31 | 2020-10-16 | NA | NA | TRUE | NA | NA ¦ NA | 7689.8706 | 279.0951 | 398.5445 | 175.5652 | 453.7483 | 143.9599 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 ¦ 2024 | 279.0951 | 398.5445 | 175.5652 | 453.7483 | 143.9599 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 13.55% | 86.45%
238 | TL610 Tier 2 W2S Project |  |  | San Diego, San Diego | Wood to steel replacement on TL610 less than 2 miles. | Transmission Line - Pole/Tower | Replace | NA | 20133 | Wildfire Mitigation | T-Line Reliability | NA | NA | 2024-01-23 | 49 | NA | NA | NA | HFTD Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 1.35 | NA | 69 | NA | 1.2 | 2020-0272 | QS00474 | 1 | 20133 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-06-12 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | NA | NA | TBD | 2023-02-13 | Approved | 2023 | Operational | NA | 2025-11-05 | 2024-12-31 | 2026-05-31 | NA | NA | TRUE | 1979.963 | NA ¦ NA | 10085.1957 | 37.6458 | 112.1826 | 110.4849 | 125.6946 | 113.4704 | 62.8754 | 1256.1012 | 8266.7409 | 0 | 0 | 0 | 499.4783 | NA | NA | 2025 | 0 | 0 | 0 | 0 | 0 | 1818.4548 | 0% | NA ¦ NA | 28.1 | NA | 0% | 100%
239 | TL627 Tier 2 W2S Project |  |  | Rancho San Diego, San Diego ¦ Spring Valley, San Diego | The TL627 Wood-to-Steel project consists of installing new steel pole structures, re-frame existing steel structures, and conductor along the existing 69kV tie line between Structure Z777999 and Structure Z971734 located in Spring Valley. As part of TL627 rebuild, C91 & C524 will be reconductored as well. This project was initiated as part of SDG&E’s continuous effort to improve reliability and reduce fire risks in fire-prone areas. | Multiple Options [See Notes] | Replace | NA | NA | Reliability | Fire Protection | NA | NA | 2024-02-29 | 46 | NA | NA | NA | HFTD Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 2.1 | NA | 69 | NA | 1.2 | 2019-0257 | QS00473 | 1 | 20134 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-07-30 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | NA | NA | Exempt | NA | Approved | 2023 | Engineering more than 50% complete | NA | 2026-03-12 | 2027-04-30 | 2026-09-26 | Other [See Notes] | NA | TRUE | 1979.963 | NA ¦ NA | 14986.3398 | 70.0166 | 110.013 | 423.3457 | 504.2678 | 2065.1274 | 854.1282 | 167.2367 | 5380.6856 | 5411.5189 | 0 | 0 | 3172.7704 | NA | NA | 2025 | 0 | 0 | 0 | 0 | 0 | 3327.6181 | 0 | NA ¦ NA | 3 | NA | 0% | 100% | [Project Description - What] Project is both structure and conductor replacement. [Reason for Change in In-Service Date] - Dependency on C75 SUG completion to start the construction of TL627 W2S.
240 | TL649 Tier 2 W2S Project |  |  | San Diego, San Diego ¦ Chula Vista, San Diego | 23 wood poles in HFTD2 to be replaced from wood to steel. Two of the poles (Z192597 and Z82136), are multi-transmission wood pole structures (two poles). 1.162 Miles to be re-conductored. | Transmission Line - Pole/Tower | Upgrade/Retrofit | NA | NA | Wildfire Mitigation | T-Line Reliability | NA | NA | 2024-01-16 12:00 | 39 | NA | NA | NA | HFTD Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 1.6826 | NA | 69 | NA | 1.2 | 2019-0268 | QS00472 | 1 | 20135 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-06-10 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | Final Certified | 2018-10-05 | IS/MND | NA | CPUC | NA | Exempt | NA | NA | NA | Engineering less than 50% complete | NA | 2024-06-24 | 2024-12-31 | 2024-11-21 | NA | NA | TRUE | 1486.209 | NA ¦ NA | 7533.6822 | 36.1679 | 189.4133 | 612.1586 | 829.9482 | 4389.2003 | 974.7763 | 502.0176 | 0 | 0 | 0 | 0 | 6056.8883 | NA | NA | 2025 | 0 | 0 | 0 | 0 | 0 | 502.0176 | 0% | NA ¦ NA | 43.6 | NA | 0% | 100% | [Project Description - What] Project is both structure and conductor replacement.
241 | TL13804 Wood to Steel |  |  | Encinitas, San Diego ¦ Rancho Santa Fe, San Diego ¦ Carlsbad, San Diego ¦ San Diego, San Diego | Replace 15 existing wood structures (h-frames) with steel structures. Project spans approximately 5 miles of TL13804 and includes ~0.6 miles of reconductoring with transferring of existing conductor and fiber optic cable to new structures for the remainder. | Transmission Line - Pole/Tower | Replace | Removal | NA | Wildfire Mitigation | T-Line Reliability | NA | NA | 2024-03-07 12:00 | 39 | NA | NA | NA | HFTD Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | Project In Coastal Zone; Requires Galvanized Steel Poles |  | 16.3749 | NA | 138 | NA | 1.2 | 2019-0255 | QS00490 | 1 | 20136 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-07-25 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | 2024-09-17 | 2025-02-12 | 2024-12-23 | Other [See Notes] | NA | TRUE | 3628.655 | NA ¦ NA | 8606.521 | 49.7664 | 229.5117 | 297.0474 | 477.1188 | 1525.8008 | 5762.6959 | 264.5802 | 0 | 0 | 0 | 0 | 2579.245 | NA | NA | 2025 | 0 | 0 | 0 | 0 | 0 | 8606.521 | 0% | NA ¦ NA | 8.1 | NA | 0% | 100% | [Reason for Change in In-Service Date] In-service dates are estimated during preliminary design and permitting stages of a project; date shifted to reflect actual design and construction schedule.
242 | TL23001/04 Insulator and Hardware Replacement |  |  | Encinitas, San Diego ¦ Rancho Santa Fe, San Diego ¦ Carlsbad, San Diego ¦ San Diego, San Diego ¦ Oceanside, San Diego | TL23001 TL23004 Insulator and Hardware Replacement | Transmission Line - Other Equipment | Upgrade/Retrofit | NA | NA | Reliability | Age/Condition - Replace Insulators | NA | NA | 2024-01-16 12:00 | 39 | NA | NA | NA | HFTD Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 34.8284 | NA | 230 | NA | 4.1 | 2019-4004 | QS00479 | 1 | 20138 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2022-07-07 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | 2022-03-01 | 2022-07-29 | 2022-10-11 | NA | NA | TRUE | 8040.059 | NA ¦ NA | 10616.6292 | 13.3736 | 3593.8105 | 6816.3403 | 81.5084 | 111.5965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2022 ¦ 2023 ¦ 2024 | 0 | 0 | 10423.5243 | 81.5084 | 111.5965 | 0 | 0 | NA ¦ NA | NA ¦ NA | NA | 100% | 0%
243 | TL6952 Tier 2 W2S Project |  |  | San Diego, San Diego | Replace 10 wood pole structures in HFTD Tier 2 with steel pole structures and transfer approximately 1.5 miles of overhead conductor. | Transmission Line - Pole/Tower | Replace | NA | 20139 | Wildfire Mitigation | T-Line Reliability | NA | NA | 2024-08-29 12:00 | 39 | NA | NA | NA | HFTD Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | Coastal |  | 1.3391 | NA | 69 | NA | 1.2 | 2020-0287 | QS00466 | 1 | 20139 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-06-12 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | NA | NA | TBD | NA | Approved | NA | Operational | NA | 2025-11-05 | 2022-12-31 | 2026-05-31 | NA | NA | TRUE | 1810.588 | NA ¦ NA | 9042.594 | 13.7913 | 85.2687 | 108.168 | 115.8357 | 137.3137 | 62.0082 | 1459.9747 | 7060.2337 | 0 | 0 | 0 | 460.3774 | NA | NA | 2025 | 0 | 0 | 0 | 0 | 0 | 1982.3603 | 0 | NA ¦ NA | 0.2 | NA | 0% | 100%
244 | TL661/TL664 Tier 2 W2S Project |  |  | San Diego, San Diego | Replace 14 wood pole structures in HFTD Tier 2 with steel pole structures and install approximately 1.16 miles of overhead conductor. | Transmission Line - Pole/Tower | Replace | NA | NA | Wildfire Mitigation | T-Line Reliability | NA | NA | 2024-01-09 12:00 | 39 | NA | NA | NA | HFTD Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | Coastal |  | 1.16 | NA | 69 | NA | 1.2 | 2020-0289 | QS00471 | 1 | 20140 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-06-12 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | NA | NA | PTC | 2025-09-22 | To be Filed | 2025 | Operational | NA | NA | 2022-12-31 | 2027-12-31 | NA | NA | TRUE | 1810.588 | NA ¦ NA | 13343.3908 | 26.1607 | 150.0426 | 274.8061 | 558.0351 | 184.4641 | 115.8902 | 453.0815 | 428.9998 | 2876.631 | 8275.2797 | 0 | 1193.5085 | NA | NA | 2025 | 0 | 0 | 0 | 0 | 0 | 1280.0989 | 0 | NA ¦ NA | 2.9 | NA | 0% | 100%
245 | TL691 Tier 2 W2S Project |  |  | Fallbrook, San Diego ¦, Camp Pendleton North | The TL691 Fire Hardening & Reconductor Project consists of replacing existing structures and installing new steel structures along the 69kV tie line 691 in FTZ from Z19800, north of Camp Pendleton to structure Z293940, south of Avocado Substation, with new light duty and heavy engineered steel poles. This project is needed to mitigate loss of service due to wildfires by replacing existing wood poles with new steel structures. The new steel poles shall be designed to 138kV specifications and accommodate existing and future 12kV distribution underbuild and communications circuits. | Transmission Line - Pole/Tower | Replace | NA | NA | Wildfire Mitigation | T-Line Reliability | NA | NA | 2024-02-10 | 52 | NA | NA | NA | HFTD Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 6.1778 | NA | 69 | NA | 1.2 | 2019-0269 | QS00469 | 1 | 20141 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-06-12 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | NA | NA | Exempt | NA | NA | NA | Engineering less than 50% complete | NA | 2027-03-08 | 2024-12-31 | 2027-09-10 | Other [See Notes] | NA | TRUE | 1979.963 | NA ¦ NA | 22943.8634 | 44.5941 | 177.1658 | 521.1869 | 373.7411 | 190.3585 | 86.1694 | 5206.2828 | 16344.3649 | 0 | 0 | 0 | 1307.0464 | NA | NA | 2025 | 0 | 0 | 0 | 0 | 0 | 5083.7604 | 0 | NA ¦ NA | 3.9 | NA | 0% | 100% | [Reason for Change in In-Service Date] In-service dates are estimated during preliminary design and permitting stages of a project; date shifted to reflect actual design and construction schedule.
246 | TL675 Tier 2 W2S Project |  |  | San Diego, San Diego | ​57 poles to be replaced from wood to steel, and 6 miles to be reconductored. | Transmission Line - Pole/Tower | Replace | NA | NA | Wildfire Mitigation | T-Line Reliability | NA | NA | 2024-04-26 | 34 | NA | NA | NA | HFTD Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | Coastal |  | 5.4503 | NA | 69 | NA | 1.2 | 2019-0251 | QS00470 | 1 | 20142 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-08-29 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | NA | NA | Exempt | NA | NA | NA | Permitting | NA | 2025-01-20 | 2026-12-31 | 2025-12-08 | NA | NA | TRUE | 1979.963 | NA ¦ NA | 30037.6374 | 27.3153 | 257.9922 | 292.5942 | 545.0621 | 3089.3633 | 168.8302 | 2736.1274 | 21356.768 | 1563.5847 | 0 | 0 | 4212.3271 | NA | NA | 2025 | 0 | 0 | 0 | 0 | 0 | 2343.0005 | 0 | NA ¦ NA | 8.2 | NA | 0% | 100%
247 | TL6939 Tier 2 W2S Project |  |  | San Diego, San Diego | 42 poles in HFTD 2 to be replaced from wood to steel, and 2.5 miles to be reconductored. | Transmission Line - Multiple | Replace | Upgrade/Retrofit | NA | Wildfire Mitigation | Priority 1 Wood Structure Replacement | NA | NA | 2024-03-13 | 33 | NA | NA | NA | HFTD Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 0.9 | NA | 69 | NA | 1.2 | 2019-0256 | QS00467 | 1 | 20143 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-06-12 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | NA | NA | TBD | NA | NA | NA | Engineering less than 50% complete | NA | NA | 2024-12-31 | NA | NA | NA | FALSE | 1973 | NA ¦ NA | 4379.2366 | 0 | 56.2863 | 139.3699 | 257.6459 | 80.3904 | 17.6914 | 74.7776 | 3753.0751 | 0 | 0 | 0 | 533.6925 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA ¦ NA | 2.1 | NA | 0% | 100%
248 | TL6910 Tier 2 W2S Project |  |  | Chula Vista, San Diego | R​eplace 14 wood poles to steel poles. | Transmission Line - Multiple | Replace | Upgrade/Retrofit | NA | Wildfire Mitigation | Priority 1 Wood Structure Replacement | NA | NA | 2024-01-16 12:00 | 32 | NA | NA | NA | HFTD Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 2.8 | NA | 69 | NA | 1.2 | 2019-0254 | QS00468 | 1 | 20144 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-06-12 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | NA | NA | TBD | NA | NA | NA | Engineering less than 50% complete | NA | 2027-01-25 | 2024-12-31 | 2027-01-25 | Project Design | NA | FALSE | 1973.076 | NA ¦ NA | 5155.3051 | 0 | 56.6194 | 46.5005 | 93.7415 | 284.5296 | 28.2532 | 119.4198 | 4489.9112 | 36.33 | 0 | 0 | 481.3909 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA ¦ NA | 1.1 | NA | 0% | 100%
249 | TL13811 W2S |  |  | San Marcos San Diego ¦ Encinitas, San Diego ¦ San Diego, San Diego | TL13811 W2S is a hardening project driven by the circuit’s location within the High Fire Threat District (HFTD) Tier 2. This project will replace all transmission structures from Chicarita Sub to Z312843, and then again from Z200897 to North County Metering Station. Throughout these sections (approximately 11.25 miles in length) the 138 kV mainline will be replaced with 636 kcmil 24/7 Strand “Rook” ACSS/AW. 96 Count OPGW will be installed from Z872457 – Z312843 (approximately 10.75 miles in length). Distribution circuits C1101 and C182 that are in the underbuild position of TL13811 will be reconductored with Covered 336.4 kcmil 26/7 Strands “Linnet” ACSR, and covered 1/0 6/1 Strands “Raven” ACSR, respectively. | Transmission Line - Multiple | Replace | Removal | NA | Wildfire Mitigation | T-Line Reliability | NA | NA | 2024-05-07 | 60 | NA | NA | NA | HFTD Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 13.0003 | NA | 138 | NA | 1.2 | 2019-0253 | QS00465 | 1 | 20145 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-04-23 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Engineering more than 50% complete | NA | 2024-07-30 | 2024-12-31 | 2025-05-28 | NA | NA | FALSE | 88878 | NA ¦ NA | 79962.9379 | 189.111 | 811.9706 | 1536.3214 | 1213.4383 | 1316.3963 | 576.6019 | 41974.8865 | 32344.2119 | 0 | 0 | 0 | 5067.2376 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | 4.6 | NA | 0% | 100% | [CPUC Status] Project was Exempt from CPUC filing per GO-131D.
250 | IV Shunt Reactor Replacement |  |  | Imperial County | Replace the existing 500kV shunt reactors at Imperial Valley substation with spares at Miguel substation. | Substation - Reactive Equipment | Replace | NA | NA | Reliability | Age/Condition - Replace Reactors, Age/Condition - Replace Relays | NA | NA | 2024-10-30 | 41; 41; 41 | NA | Wires - Minimum Required Scope (spot repair) Alternative | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 55.4775 | 500 | 500kV | 4.1 | 2021-2176 | QS00482 | 1 | 20148 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-08-06 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Construction (50%-75%) | NA | 2022-06-01 | 2024-08-31 | 2024-08-02 | Multiple Options [See Notes] | NA | TRUE | 3742.255 | NA ¦ NA | 4273.3006 | 7.5324 | 1479.6704 | 1043.8368 | 472.7717 | 2096.23 | -826.7407 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2024 | 0 | 0 | 0 | 0 | 5100.0413 | 0 | 0% | NA ¦ NA | 18.5 | NA | 100% | 0% | [Reason for Change in In-Service Date] In-service dates are estimated during preliminary design and permitting stages of a project; date shifted to reflect actual design and construction schedule.
251 | TL6920 Wood to Steel |  |  | San Diego, San Diego | 7 poles in HFTD 2 to be replaced from wood to steel, and a total of 0.584 miles of existing 1033.5 ACSR/AW to be reconductored. | Transmission Line - Pole/Tower | Replace | NA | NA | Wildfire Mitigation | T-Line Reliability | NA | NA | 2024-03-02 | 60 | NA | NA | NA | HFTD Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 0.28631 | NA | 69 | NA | 1.2 | 2020-0286 | QS00504 | 1 | 20149 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-06-30 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | NA | NA | Exempt | NA | Approved | 2022 | Operational | NA | 2023-05-08 | 2024-01-18 | 2023-08-02 | NA | NA | TRUE | 1959.396 | NA ¦ NA | 4312.2766 | 0.7471 | 171.0337 | 300.7648 | 3682.8958 | 107.6439 | 49.1914 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2023 ¦ 2024 | 0 | 0 | 0 | 4155.4414 | 107.6439 | 0 | 0 | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
252 | TL690C Camp Pendleton Wood to Steel |  |  | Camp Pendleton South, San Diego | 10 poles in HFTD 2 to be replaced from wood to steel. A total of 0.57 miles of existing 1/0 CU and 336.4 ACSR/AW to be reconductored. | Transmission Line - Multiple | Replace | Upgrade/Retrofit | NA | Wildfire Mitigation | T-Line Reliability | NA | NA | 2024-07-25 | 60 | NA | NA | NA | HFTD Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 0.49947 | NA | 69 | NA | 1.2 | 2020-0273 | QS00496 | 1 | 20152 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-08-02 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | Categorical Exclusion | CPUC | MCBCP | Exempt | NA | NA | 2023 | Operational | NA | 2024-06-28 | 2024-10-31 | 2024-07-31 | Other [See Notes] | NA | TRUE | 3977.8055 | NA ¦ NA | 3031.3367 | 0.8544 | 140.182 | 218.2715 | 631.0719 | 1657.1276 | 181.2175 | 202.6118 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2023 ¦ 2024 ¦ 2025 | 0 | 0 | 0 | 990.3798 | 1657.1276 | 202.6118 | 0% | NA ¦ NA | 0.32 | NA | 0% | 100% | [Reason for Change in In-Service Date] In-service dates are estimated during preliminary design and permitting stages of a project; date shifted to reflect actual design and construction schedule.
253 | Torrey Pines 12kV Breaker Replacements |  |  | San Diego, San Diego | Replacing oil CB with Vacuum CB, removing Oil containment, upgrades to SL&P, and PT. Upgrading (3) 69kV breakers. Aging equipment is going to be replaced to enhance substation reliability and reduce maintenance needs. Work is on-going. | Substation - Multiple | Upgrade/Retrofit | NA | NA | Reliability | Age/Condition | NA | NA | 2024-09-27 | 54;40;50;60;31; 50; 34; 33; 50; 54; 32; 53; 50 | NA | Wires - Minimum Required Scope (spot repair) Alternative | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 0.79 | 69 | 69kV | 4.1 | 2020-1014 | QS00429 | 1 | 20242 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-02-22 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | 2024-07-15 | 2023-10-31 | 2025-07-29 | Multiple Options [See Notes] | NA | TRUE | 992.6208 | NA ¦ NA | 2242.2652 | 0 | 522.2801 | 532.9887 | 225.6203 | 289.1795 | 143.7003 | 528.4963 | 0 | 0 | 0 | 0 | 1570.0686 | NA | NA | 2025 | 0 | 0 | 0 | 0 | 0 | 2242.2652 | 0% | NA ¦ NA | 10.4 | NA | 0% | 100% | [Reason for Change in In-Service Date] In-service dates are estimated during preliminary design and permitting stages of a project; date shifted to reflect actual design and construction schedule.
254 | Granite 12kV Breaker and Switchgear Replacements |  |  | Granite Hills, San Diego | Rebuild of the 69kV bus reconfiguring it from an ultimate 2 tie line bus to an ultimate 3 tie line substation. Replace all seven (qty: 7) 69kV kV circuit breakers (5 OCB and 2 GCB ¦older style). Install new 69kV Potential Transformers. Replace 12kV open rack bus and (qty. 8) 12kV circuit breakers and (qty:2) 12kV 1 ¦4 section Switchgear at Granite Substation, due to operational problems, again infrastructure, environmental concerns, in addition to meeting current reliability standards. Rebuilding the 69kV bus and rotating the phases at the transmission pole will allow for a third tie line position. Replacing the 12kV open rack will RFS the OCBs and address the some 12kV reliability issues, will update relaying to support WMP initiatives (advance protection). The new control shelter will assist with updating relaying to include TCRI, new 69kV BT, and increase operational ability. | Substation - Circuit Breaker | Replace | Upgrade/Retrofit | NA | Reliability | Age/Condition - Replace Breakers | NA | NA | 2024-09-10 | NA | NA | Wires - Replacement Alternative | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 1.38 | 12 ¦69 | 12kV ¦69kV | 4.1 | 2021-2405 | QS00430 | 1 | 20244 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-10-24 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Construction (under 10%) | NA | 2024-02-14 | 2028-12-31 | 2028-10-19 | NA | NA | FALSE | 4693.6589 | NA ¦ NA | 20403.2406 | 592.9603 | 30.2266 | 440.1786 | 1135.9573 | 4387.7264 | 1035.2784 | 6134.9212 | 2699.6047 | 1529.3989 | 2130.2442 | 0 | 6873.7932 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | 7.7 | NA | 0% | 100%
255 | Kettner Substation 69/12kV Rebuild Project |  |  | San Diego, San Diego | The Kettner Substation Rebuild includes the installation of two 69kV GCB, six 12kV VCB, and one 12kV Capacitor Bank with stepwise switching. This will make Kettner Substation an ultimate 30MVA. The project also includes the construction of a new concrete block control shelter and a new perimeter fence/wall. The project includes removal of old infrastructure no longer in use, including two 12kV cap banks, eleven 12kV OCBs, one 12kV VCB, and two 69kV OCB. The current shipping container control shelter will also be removed once cutover is complete to the new concrete block control shelter. | Substation - Multiple | Upgrade/Retrofit | Removal | NA | Reliability | Replace Other Substation Equipment | NERC CIP Compliance | NA | 2024-09-17 | 43; 43; 26 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 0.3 | 69 | 30MVA | 4.1 | 2014-00599-ZZ | QS00478 | 1 | 20251 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-06-08 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Construction (50%-75%) | NA | 2022-11-28 | 2024-12-31 | 2024-09-20 | Prioritization | Construction Delays | TRUE | 6659.3357 | NA ¦ NA | 9574.072 | 203.4617 | 1836.4478 | 1386.0173 | 3480.4105 | 1071.8196 | 1508.692 | 87.2231 | 0 | 0 | 0 | 0 | 64.1989 | NA | NA | 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 0 | 0 | 704.9014 | 13.3813 | 7195.6753 | 1660.114 | 0% | NA ¦ NA | 17.3 | NA | 0% | 100%
256 | Chicarita 12kV Replacements |  |  | San Diego, San Diego | Replacement of: (Qty:8) 12kV Circuit Breakers, (Qty:3) 138kV Circuit Breakers, and (Qty:1) 12kV Switchgear at Chicarita Rebuild Substation, (Qty:2) Capacitor Banks and (Qty:1) Control Shelter due to proactively replace aging substation equipment to improve future SAIDI impact, Environmental concerns and Operational concerns | Substation - Circuit Breaker | Replace | Upgrade/Retrofit | NA | Reliability | Age/Condition - Replace Breakers | NA | NA | 2024-09-18 | 50; 30; 50 | NA | Wires - Replacement Alternative | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | TRUE | NA |  | NA | 1.73 | 12 ¦69 | 12kV ¦69kV | 4.1 | 2014-00306-ZZ | QS00548 | 1 | 20264 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2021-03-12 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Planning | NA | 2016-06-01 | 2027-12-31 | 2017-01-24 | NA | NA | FALSE | 3291.3585 | NA ¦ NA | 3973.5025 | 77.0345 | 37.8478 | 24.338 | 21.1112 | 0 | 0 | 0 | 0 | 0 | 0 | 2941.2711 | 392.479 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | 1.9 | NA | 0% | 100%
257 | Aviation Firefighting Program |  |  | El Cajon, San Diego | This is a new project. Purchase, equipping and initial training of a new Sikorsky S-70i Firehawk helicopter. | Other | NA | NA | NA | Wildfire Mitigation | Fire Protection | NERC CIP Compliance | NA | NA | 60 | NA | NA | NA | HFTD Tier 2 ¦ HFTD Tier 3 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | NA | NA | Multiple | NA | 1.2 | NA | QS00481 | 1 | 20277 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-10-24 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | To be Filed | NA | Permitting | NA | 2020-7-23 | 2024-10-31 | 2025-07-21 | NA | NA | TRUE | NA | NA ¦ NA | 5373.2547 | 1254.5796 | 1917.2812 | 376.7674 | 290.8835 | 380.904 | 295.1472 | 857.6916 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 0 | 0 | 35.0873 | 18.1185 | 28.9657 | 5272.7959 | 0% | NA ¦ NA | 17.9 | NA | 0% | 100%
258 | [Programmatic] Overhead System Traditional Hardening |  |  | NA | This program (i.e., many projects) focuses on projects that replace OH Distribution system in fire prone areas including HFTD Tier 2, Tier 3, and Wildland Urban Interface. In some cases the distribution lines are underbuilt on transmission structures and require some amount of FERC spend. | Other | Replace | NA | NA | Wildfire Mitigation | Line Reconductoring | Other [See Notes] | NA | NA | NA | NA | NA | NA | HFTD Tier 2 ¦ HFTD Tier 3 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | NA | NA | 12 | NA | 1.1 | Multiple | QBL0118 | 352 | 20284 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-12-08 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | CPUC | NA | Exempt | NA | NA | NA | Construction (25%-50%) | NA | NA | 2024-12-31 | NA | NA | NA | TRUE | NA | NA ¦ NA | 0 | 807.0253 | 358.0998 | 133.5155 | 42.6517 | 23.1217 | 0.14905 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 646.8978 | 924.6159 | 124.5997 | 50.8098 | 2.3044 | -0.015357 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [NERC / WECC / CAISO Standard / Requirement / Contingency] This is a distribution hardening program and there is not one single project. The only case where we should charging FERC are when we are dealing with replacing the distribution assets underbuilt on 69kV and 138kV structures, and in the vast majority of cases we do not replace the transmission structure. We also do not go through any permitting with the CPUC as our distribution system upgrades are exempt from GO 131D.
259 | A FIRE RISK MITIGATION(FIRM) CWIP |  |  | San Diego County | Electric System Hardening program focused on the replacement of wood poles and bare conductor with weathering steel poles and new bare conductor on our 12 kV system, and in some cases includes some underbuilt distribution lines on transmission. | Other | Replace | NA | NA | Wildfire Mitigation | Line Reconductoring | Other [See Notes] | NA | NA | NA | NA | NA | NA | HFTD Tier 2 ¦ HFTD Tier 3 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | NA | NA | 12 | NA | 1.1 | NA | QBL0118 | 1 | 20284 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-08-26 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Construction (25%-50%) | NA | 2024-01-01 | 2020-12-31 | 2024-01-01 | NA | NA | FALSE | NA | NA ¦ NA | 3550.4199 | 1007.279 | 1110.6252 | 824.0799 | 293.8148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2023 | 0 | 0 | 0 | 3550.4199 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [NERC / WECC / CAISO Standard / Requirement / Contingency] This is a distribution hardening program and there is not one single project. The only case where we should charging FERC are when we are dealing with replacing the distribution assets underbuilt on 69kV and 138kV structures, and in the vast majority of cases we do not replace the transmission structure. We also do not go through any permitting with the CPUC as our distribution system upgrades are exempt from GO 131D.
260 | [Programmatic] Overhead System Covered Conductor |  |  | NA | Electric System Hardening program focused on the replacement of wood poles and bare conductor with weathering steel poles and covered conductor on our 12 kV system, and in some cases includes some underbuilt distribution lines on transmission. | Other | Replace | NA | NA | Wildfire Mitigation | Line Reconductoring | Other [See Notes] | NA | NA | NA | NA | NA | NA | HFTD Tier 2 ¦ HFTD Tier 3 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | NA | NA | Multiple | NA | 1.2 | Multiple | QBL0117 | 12 | 20285 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-12-08 | Work Order Authorization | 2021 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Construction (25%-50%) | NA | NA | 2024-12-31 | NA | NA | NA | TRUE | NA | NA ¦ NA | 0 | 5.7953 | 26.183 | 140.9086 | 203.2484 | 94.0321 | -16.732 | 0 | 64.4259 | 42.761 | 48.9573 | 47.6403 | 0 | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 3.2355 | 28.7601 | 134.7849 | 164.8418 | 109.5611 | -16.732 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [NERC / WECC / CAISO Standard / Requirement / Contingency] This is a distribution hardening program and there is not one single project. The only case where we should charging FERC are when we are dealing with replacing the distribution assets underbuilt on 69kV and 138kV structures, and in the vast majority of cases we do not replace the transmission structure. We also do not go through any permitting with the CPUC as our distribution system upgrades are exempt from GO 131D.
261 | A FIRM COVERED CONDUCTOR CWIP |  |  | San Diego County | Electric System Hardening program focused on the replacement of wood poles and bare conductor with weathering steel poles and covered conductor on our 12 kV system, and in some cases includes some underbuilt distribution lines on transmission. | Other | Replace | NA | NA | Wildfire Mitigation | Line Reconductoring | Other [See Notes] | NA | NA | NA | NA | NA | NA | HFTD Tier 2 ¦ HFTD Tier 3 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | NA | NA | 12 | NA | 1.2 | NA | QBL0117 | 1 | 20285 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-09-17 | Work Order Authorization | 2021 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Construction (25%-50%) | NA | 2024-01-01 | 2025-12-31 | 2024-01-01 | NA | NA | TRUE | NA | NA ¦ NA | 2129.2711 | 7.9327 | 220.8903 | 515.3381 | 651.7329 | 733.377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 ¦ 2024 | 7.9327 | 220.8903 | 515.3381 | 651.7329 | 733.377 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [NERC / WECC / CAISO Standard / Requirement / Contingency] This is a distribution hardening program and there is not one single project. The only case where we should charging FERC are when we are dealing with replacing the distribution assets underbuilt on 69kV and 138kV structures, and in the vast majority of cases we do not replace the transmission structure. We also do not go through any permitting with the CPUC as our distribution system upgrades are exempt from GO 131D.
262 | [Programmatic] Drone Assessments |  |  | NA | The project was focused on flying and assessing all structures within the HFTD (Tier 2) with the purpose of mitigating any fire-related issues. | Other | Replace | NA | NA | Wildfire Mitigation | Fire Protection | NA | NA | NA | NA | NA | NA | NA | HFTD Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | NA | NA | Multiple | NA | 1.1 | Multiple | QBL0124 | 4 | 20286 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-12-07 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Operational | NA | NA | 2024-12-31 | NA | NA | NA | TRUE | NA | NA ¦ NA | 0 | 0 | 49.4976 | 0.0020165 | 0.61774 | 585.9621 | 94.7354 | 379.1191 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 0 | 0 | 49.4996 | 0.61774 | 2.3782 | 973.9661 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
263 | A DRONE INVESTIGATION ASSESSMENT |  |  | NA | Perform drone inspections for all of Tier 2 HFTD and higher risk WUI areas and complete follow-up repairs of any infractions identified. | Other | Replace | Replace | NA | Wildfire Mitigation | Age/Condition | Other [See Notes] | Other [See Notes] | NA | NA | NA | NA | NA | HFTD Tier 2 ¦ HFTD Tier 3 ¦ Higher Fire Threat Area | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | NA | NA | NA | NA | 1.1 | NA | QBL0124 | 1 | 20286 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-02-14 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Construction (over 75%) | NA | NA | 2020-12-31 | NA | NA | NA | TRUE | NA | NA ¦ NA | 3521.6971 | 527.1262 | 773.2967 | 1314.0803 | 843.8187 | -189.2602 | 110.805 | 141.8304 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2024 ¦ 2025 | 0 | 0 | 0 | 0 | 3269.0617 | 141.8304 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [NERC / WECC / CAISO Standard / Requirement / Contingency] Project description purpose is to "Repair damaged overhead electric distribution poles". The requirement is based on GO 95 compliance and conformance with the Wildfire Mitigation Plan. [NERC / WECC / CAISO Standard / Requirement / Contingency 2 ] ? [CPUC Status] NA
264 | TL651 Boundary Street Customer Relocation |  |  | San Diego, San Diego | Internally-funded relocation project to replace three (3) transmission poles with 69 kV/4 kV/Communication and install approximately 800 ft. of new transmission and distribution conductor. Relocate Z730600 away from an eroding drainage bank. Replace structures adjacent to HWY-15 (Z730600 and Z2034273419) with self-supporting steel structures. Replace Z730598 with a direct-bury steel pole. | Transmission Line - Multiple | Relocate | NA | NA | Work Requested by Others | Facility Relocation | NA | NA | 2024-01-23 | 60 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | TBD |  | 0.37 | NA | 69 | NA | 1 | 2017-0118 | QS00658 | 1 | 21128 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2022-06-22 | Work Order Authorization | 2022 | NA | FALSE | NA | NA | NA | FALSE | TBD | NA | NA | NA | CPUC | NA | Advice Letter | NA | To be Filed | 2025 | Engineering more than 50% complete | NA | 2026-09-01 | 2025-06-30 | 2027-01-29 | NA | NA | TRUE | 3267.6739 | NA ¦ NA | 1417.2852 | 0 | 0 | 0 | 0 | 0 | 80.2225 | 168.8726 | 1168.1901 | 0 | 0 | 0 | 0 | NA | NA | 2025 | 0 | 0 | 0 | 0 | 0 | 249.0951 | 0% | 100% ¦ 3200 | 5.2 | NA | 0% | 100%
265 | [Programmatic] ELEC TRANS SMALL RELIABILITY - HFTD |  |  | San Diego, San Diego County | This budget code is all Electric Transmission projects under $4M, including shared equipment on the structures for both Transmission and Distribution. The funds are applied to the infrastructure to meet SDGE’s obligation to increase safety and reliability of the electric system. Budget includes proactive system upgrades and reactive projects that include poles, insulators, conductor and other electric infrastructure when reliability issues are identified in the HFTD. | Transmission Line - Multiple | Replace | Upgrade/Retrofit | NA | Reliability | T-Line Reliability | NA | NA | NA | NA | NA | NA | NA | HFTD Tier 2 ¦ Tier 3 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | NA | NA | Multiple | NA | 1.2 | Multiple | QBL0125 | 131 | 21134 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-01-16 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | TBD | NA | NA | NA | CPUC | NA | NA | NA | NA [See Notes] | NA | Operational | NA | NA | 2024-12-31 | NA | NA | NA | TRUE | NA | NA ¦ NA | 0 | 1486.356 | 3119.5072 | 7400.5454 | 10574.061 | 7336.3171 | 2962.0085 | 13556.4063 | 10615.4533 | 14665.0828 | 16335.3855 | 17921.1438 | 13896.2406 | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 1228.4396 | 2192.8043 | 6121.3769 | 9736.876 | 10181.2528 | 2949.6088 | 0 | NA ¦ NA | 1.8 | NA | 13.55% | 86.45% | [CPUC Status] permitting may vary based on projects under this programmatic budget
266 | 53551 AREL_T2_TL678_Z104100_W2S |  |  | San Diego County | 3 poles in HFTD 2 to be replaced from wood to steel, and a total of 0.247 miles of existing 636 ACSS/AW to be reconductored. Structure #s: Z104100 636 ACSS/AW Z170670 636 ACSS/AW Z75086 636 ACSS/AW ​​ | Transmission Line - Pole/Tower | Replace | NA | NA | Reliability | Age/Condition - Replace Wood Poles | NA | NA | 2024-08-10 | NA | NA | NA | NA | HFTD Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 0.3 | NA | 69 | NA | 1.2 | 2020-0283 | QBL0125 | 1 | 21134 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-08-05 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Engineering more than 50% complete | NA | 2025-05-05 | 2024-12-30 | 2025-06-02 | NA | NA | TRUE | NA | NA ¦ NA | 1363.6144 | 108.6676 | 331.3782 | 234.8051 | 274.5971 | 414.1664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 ¦ 2024 | 108.6676 | 331.3782 | 234.8051 | 274.5971 | 414.1664 | 0 | 0 | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
267 | 53551 A W2S_T2_TL6917_4 STRUCTURES |  |  | Camp Pendleton, San Diego | 6 poles in HFTD 2 to be replaced from wood to steel, and a total of 0.416 miles of existing 1/0 CU B.S. & 394.5 5005 AL to be reconductored. Structure #s: Z21282 1/0 CU B.S. Z22190 394.5 5005 AL Z22191 394.5 5005 AL Z22192 394.5 5005 AL Z22193 394.5 5005 AL Z22194 394.5 5005 AL ​​ | Transmission Line - Pole/Tower | Replace | NA | NA | Reliability | Age/Condition - Replace Wood Poles | NA | NA | 2024-02-10 | NA | NA | NA | NA | HFTD Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 0.42 | NA | 69 | NA | 1.2 | 2020-0285 | QBL0125 | 1 | 21134 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-08-05 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | 2023-12-11 | 2024-12-30 | 2023-12-16 | NA | NA | TRUE | NA | NA ¦ NA | 1387.779 | 79.0896 | 198.2888 | 243.3452 | 875.3638 | -8.3085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2023 ¦ 2024 | 0 | 0 | 0 | 11.2335 | 1376.5455 | 0 | 0 | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
268 | A REL_TL621_Z118874 W2S |  |  | San Diego County | 2 Poles in HFTD 2 to be replaced from wood to steel, and a total of 0.0356 miles (188’) of existing 1033.5 ACSR/AW. Structure #: Z118874 1033.5 ACSR/AW Dead-End | Transmission Line - Pole/Tower | Replace | NA | NA | Reliability | Age/Condition - Replace Wood Poles | NA | NA | 2024-02-22 | NA | NA | NA | NA | HFTD Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 0.1 | NA | 69 | NA | 1.2 | 2021-0382 | QBL0125 | 1 | 21134 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2021-04-07 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | 2023-11-03 | Approved | 2023 | Permitting | NA | 2025-07-17 | 2025-12-31 | 2026-05-13 | NA | NA | TRUE | NA | NA ¦ NA | 1449.774 | 0 | 50.6354 | 177.5671 | 633.987 | 563.6067 | 23.9777 | 0 | 0 | 0 | 0 | 0 | 1264.8274 | NA | NA | 2023 ¦ 2024 | 0 | 0 | 0 | 38.2483 | 122.7206 | 0 | 0 | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
269 | A TRNM DYNAMIC LINE RATING PILOT |  |  | Lakeside, California ¦ San Diego County | Install line sensor on bottom conductor on pole Z96557, Z203844, Z138121, Z96968, Z119871, Z119867, Z873096, Z579859, Z873069, Z119879, and Z119883. As Built shows poles on TL668 (Z138121, Z96986, Z91987, Z96075, Z92001 and ground rod at base of Z96986) and TL23023 (Z119881, Z119869, Z873096, Z873081, Z873070, and Z679004). | Transmission Line - Other Equipment | New | NA | NA | Field Test Results | System Operations | NA | NA | 2024-05-09 12:00 | NA | NA | NA | NA | HFTD Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | NA | NA | 1.2 | Multiple | QBL0125 | 10 | 21134 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2019-04-24 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Operational | NA | NA | 2019-12-31 | 2020-04-03 | NA | NA | FALSE | NA | NA ¦ NA | 1018.0544 | 153.796 | 2.7874 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2020 ¦ 2021 | 1015.267 | 2.7874 | 0 | 0 | 0 | 0 | 0 | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [Utility Unique ID #1] 202000-119 , 202000-127 , 202000-131 , 202000-143 , 202000-144 , 202000-145 , 202000-159 , 202000-160 , 202000-161 , 202000-162
270 | A REL_TL632_Z118872_W2S |  |  | San Diego County | 1 Pole in HFTD to be replaced from wood to steel | Transmission Line - Pole/Tower | Replace | NA | NA | Reliability | Age/Condition - Replace Wood Poles | NA | NA | 2024-10-29 | NA | NA | NA | NA | HFTD Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | TBD |  | 0.1 | NA | 69 | NA | 1.2 | 2021-0387 | QBL0125 | 1 | 21134 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2021-04-06 | Work Order Authorization | 2022 | NA | FALSE | NA | NA | NA | FALSE | TBD | NA | NA | NA | CPUC | NA | Exempt | 2023-08-15 | Approved | 2023 | Engineering more than 50% complete | NA | 2025-05-08 | 2025-12-31 | 2026-07-17 | NA | NA | TRUE | NA | NA ¦ NA | 1098.7763 | 0 | 41.7975 | 172.7752 | 438.0483 | 446.1553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2024 | 0 | 0 | 0 | 0 | 1098.7763 | 0 | 0 | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
271 | [Programmatic] ELEC TRANS SMALL RELIABILITY – non HFTD |  |  | NA | This budget code is all Electric Transmission projects under $2M, including shared equipment on the structures for both Transmission and Distribution. The funds are applied to the infrastructure to meet SDGE’s obligation to increase safety and reliability of the electric system. Budget includes proactive system upgrades and reactive projects that include poles, insulators, conductor and other electric infrastructure when reliability issues are identified in the non-HFTD. | Transmission Line - Multiple | Replace | Upgrade/Retrofit | NA | Reliability | T-Line Reliability | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | NA | NA | 4.1 | Multiple | QBL0126 | 179 | 21135 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-11-27 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Operational | NA | NA | 2024-12-31 | NA | NA | NA | TRUE | NA | NA ¦ NA | 0 | 2897.0747 | 3849.5818 | 6901.7154 | 11469.9816 | 9720.7528 | 3536.7748 | 15996.3163 | 11478.56 | 18525.9974 | 20583.8391 | 22580.3617 | 17991.1968 | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 4234.0642 | 2500.2053 | 3563.7698 | 6965.2846 | 10871.3885 | 7688.0775 | 0 | NA ¦ NA | 7.3 | NA | 13.55% | 86.45%
272 | A 5 RELIABILITY (NON CMP) POLES |  |  | Vista, California ¦ San Diego County | TL680B-Z218305, Z218306, Z218309, Z218301, Z115895. The project cost is being split by the ratio of Poles Purchase Cost/ requested by Jaser Marabeh | Transmission Line - Pole/Tower | Replace | NA | 2988970 | Reliability | Age/Condition - Replace Wood Poles | NA | NA | 2024-05-24 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.5 | NA | 69 | NA | 4.1 | Multiple | QBL0126 | 2 | 21135 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-12-11 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | 2020-06-28 | 2022-12-31 | 2021-06-01 | NA | NA | FALSE | NA | NA ¦ NA | 1555.2433 | 1482.1904 | 67.8536 | 5.1993 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2022 | 0 | 0 | 1555.2433 | 0 | 0 | 0 | 0 | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [Utility Unique ID #1] TL612_TL604_Z279897 , TL680B Group-Fndtn
273 | A REL_TL612_TL604_Z279897 |  |  | San Diego, San Diego County | FTD to be replaced from wood to steel | Transmission Line - Pole/Tower | Replace | NA | NA | Reliability | Age/Condition - Wood Pole Reframe | NA | NA | 10/30/2023; 6/30/2023 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | TBD |  | 0.1 | NA | 69 | NA | 4.1 | 2021-0406 | QBL0126 | 1 | 21135 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2022-08-01 | Work Order Authorization | 2023 | NA | FALSE | NA | NA | NA | FALSE | TBD | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Engineering more than 50% complete | NA | 2025-11-25 | 2023-12-31 | 2025-12-24 | NA | NA | FALSE | NA | NA ¦ NA | 1246.3242 | 0 | 0 | 20.4055 | 479.0869 | 679.0589 | 10.9584 | 46.3186 | 10.4959 | 0 | 0 | 0 | 1178.5512 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
274 | [Programmatic] TRANSMISSION CONSTRUCTION & MAINT |  |  | NA | Transmission jobs in the HFTD to comply with SDG&E's obligation to serve and meet safety requirements. Budget provides resources to provide support to reactive issues that arise such as storm, fire and pole car contact. The majority of the activities that fall under this blanket budget are necessary to comply with Federal, State , and Local regulations. Activities include poles that need to be replaced due to deterioration, capital repairs related to inspections (visual, infrared, LiDAR, etc.), and emergency situations. This work is scheduled and managed by Transmission, Construction & Maintenance. | Transmission Line - Multiple | Upgrade/Retrofit | NA | NA | Wildfire Mitigation | Construct Roads/Gates/Culverts | NA | NA | NA | NA | NA | NA | NA | HFTD Tier 2 ¦ HFTD Tier 3 | FALSE ¦ FALSE ¦ TRUE | FALSE | NA |  | NA | NA | Multiple | NA | 1.1 | Multiple | QBL0127 | 372 | 21136 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-09-27 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Operational | NA | NA | 2024-12-31 | NA | NA | NA | TRUE | NA | NA ¦ NA | 0 | 1169.1307 | 887.1519 | 1638.4009 | 3392.394 | 3348.9634 | 1212.1016 | 5229.7746 | 3957.8261 | 4432.557 | 4971.5475 | 5518.403 | 1950.502 | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 803.4085 | 1263.927 | 748.7844 | 2830.8089 | 2693.1372 | 2650.4794 | 0 | NA ¦ NA | NA ¦ NA | NA | 13.55% | 86.45%
275 | A 2022 CIVIL ENG CAPITAL PROJECTS |  |  | San Diego County | The purpose of this work is TCM Cost Consolidation from WO# 5000094 under budgets 100 & 21150 to this new WO# / TCM Reconciliation | Transmission Line - Other Equipment | Replace | Upgrade/Retrofit | NA | Reliability | Construct Roads/Gates/Culverts | NA | NA | NA | NA | NA | NA | NA | HFTD Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | NA | NA | NA | NA | 1.1 | 2022-3126 | QBL0127 | 1 | 21136 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2022-11-17 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | 2021-02-03 | 2023-12-31 | 2023-06-11 | NA | NA | TRUE | NA | NA ¦ NA | 1709.2793 | 0 | 0 | 1535.07 | 197.8079 | -23.5986 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2024 | 0 | 0 | 0 | 0 | 1709.2793 | 0 | 0 | NA ¦ NA | NA ¦ NA | NA | 0% | 0%
276 | Suncrest Tertiary Reactor Replacement |  |  | San Diego County | The BK80/81 tertiary 12kV reactors are failing at a high rate (one in 2016, one in 2020, and two in 2021). Reactors are necessary to allow critical 500kV voltage control for grid operations. Newer, better designed, and insulated reactors are available to replace units that are failing at a quick rate. | Substation - Reactive Equipment | Upgrade/Retrofit | Replace | NA | Safety | Substation Reliability | NA | NA | 2024-10-09 | 12 | NA | Wires - Replacement Alternative | NA | HFTD Tier 3 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 40.94 | 500 | 12kV | 4.1 | 2021-2012 | QS00580 | 1 | 21137 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2021-06-04 | Work Order Authorization | 2021 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | 2022-03-07 | 2022-06-30 | 2022-06-30 | Multiple Options [See Notes] | NA | FALSE | 2699 | NA ¦ NA | 2111.8255 | 4.1257 | 1904.6749 | 203.0249 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2022 | 0 | 0 | 2111.8255 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0% | [Reason for Change in In-Service Date] In-service dates are estimated during preliminary design and permitting stages of a project; date shifted to reflect actual design and construction schedule.
277 | [Programmatic] HATS |  |  | NA | This project will facilitate ongoing compliance and safe and efficient operations and maintenance of the transmission system by addressing helicopter access constraints and supporting the latest work practices. The project will provide additional Helicopter Access for Transmission Structures (HATS) that currently have helicopter access constraints. | Other | New | NA | NA | Other [See Notes] | Safety - Line Right of Way Access | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | Multiple | NA | 1.3 | Multiple | QBL0130 | 6 | 21146 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-11-21 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Operational | NA | NA | 2024-12-31 | NA | NA | NA | TRUE | NA | NA ¦ NA | 0 | 0 | 11684.9933 | 8794.4916 | 12435.3836 | 2872.7507 | 5938.8057 | 12400.796 | 0 | 0 | 0 | 0 | 841.28 | NA | NA | 2024 ¦ 2025 | 0 | 0 | 0 | 0 | 782.9015 | 658.5028 | 0% | NA ¦ NA | 24.4 | NA | 100% | 0% | [Primary Purpose] Specialized Structure Access
278 | A HATS WORK RELEASE 3 |  |  | NA | Contractor shall provide all services, labor, material, equipment, transportation, supervision, and incidental related work necessary for the installation of two types of helicopter landing facilities at various locations along Company’s 230kV and 500kV transmission system. One type is a Transmission Staging Access Pad (TSAP) which is a level, bare ground area cleared and maintained of vegetation used for intermittent landing of Company or authorized contractor helicopters. The TSAP scope includes (2) TSAP locations. The other type is an engineered structural steel helicopter landing platform used for intermittent landing of Company or authorized contractor helicopters (Platform). The Platform scope includes seven (7) permanent, engineered structural landing platforms. These facilities are generally located in steep, rugged and mountainous terrain and are necessary due to lack of available roads for vehicle access and will assist in the safe and efficient maintenance and operation of electric transmission facilities | Other | New | NA | NA | Reliability | Safety - Line Right of Way Access | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 230 ¦ 500 | NA | 1.3 | 2022-2623 | QBL0130 | 1 | 21146 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2021-10-22 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | 2023-07-31 | 2023-12-31 | 2024-7-1 | Construction Delays | Construction Delays | TRUE | NA | NA ¦ NA | 14536.866 | 0 | 0 | 336.5763 | 12184.1401 | 2016.1496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2024 | 0 | 0 | 0 | 0 | 14536.866 | 0 | 100% | NA ¦ NA | NA ¦ NA | NA | 100% | 0% | [Project Description - What] Initiative to provide safe access to the transmission structures where there is no proximate road access. [Primary Purpose] Specialized Structure Access
279 | A HATS WORK RELEASE 2 |  |  | NA | Contractor shall provide all services, labor, material, equipment, transportation, supervision, and incidental related work necessary for the installation of two types of helicopter landing facilities at various locations along Company’s 230kV and 500kV transmission system. One type is a Transmission Staging Access Pad (TSAP) which is a level, bare ground area cleared and maintained of vegetation used for intermittent landing of Company or authorized contractor helicopters. The TSAP scope includes (2) TSAP locations. The other type is an engineered structural steel helicopter landing platform used for intermittent landing of Company or authorized contractor helicopters (Platform). The Platform scope includes seven (7) permanent, engineered structural landing platforms. These facilities are generally located in steep, rugged and mountainous terrain and are necessary due to lack of available roads for vehicle access and will assist in the safe and efficient maintenance and operation of electric transmission facilities | Other | New | NA | NA | Reliability | Safety - Line Right of Way Access | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 230 ¦ 500 | NA | 1.3 | 2022-2622 | QBL0130 | 1 | 21146 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2021-09-08 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | 2021-01-22 | 2021-12-31 | 2022-09-27 | Material | Material | TRUE | NA | NA ¦ NA | 20467.8516 | 0 | 11684.9933 | 8457.9153 | 215.5547 | 109.3883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 | 0 | 11684.9933 | 8457.9153 | 215.5547 | 109.3883 | 0 | 100% | NA ¦ NA | NA ¦ NA | NA | 100% | 0% | [Project Description - What] Initiative to provide safe access to the transmission structures where there is no proximate road access.
280 | HATS Release 4 |  |  | NA | Contractor shall provide all services, labor, material, equipment, transportation, supervision, and incidental related work necessary for the installation of two types of helicopter landing facilities at various locations along Company’s 230kV/500kV transmission system. One type is a Tower Staging Access Pad (TSAP) which is a level, bare ground area cleared and maintained of vegetation used for intermittent landing of Company or authorized contractor helicopters. The TSAP scope includes one (1) TSAP location. The other type is an engineered structural steel helicopter landing platform (Platform or HLP) used for intermittent landing of Company or authorized contractor helicopters. The Platform scope includes six (6) engineered structural landing platforms. These facilities are generally located in steep, rugged and mountainous terrain and are necessary due to lack of available roads for vehicle access and will assist in the safe and efficient maintenance and operation of electric transmission facilities. | Other | New | NA | NA | Reliability | Safety - Line Right of Way Access | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 230 ¦ 500 | NA | 1.3 | 2024-3824 | QBL0130 | 1 | 21146 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-11-21 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Construction (under 10%) | NA | 2024-12-02 | 2024-12-31 | 2025-05-30 | NA | NA | TRUE | NA | NA ¦ NA | 17681.099 | 0 | 0 | 0 | 0 | 0 | 5812.571 | 11868.527 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2025 | 0 | 0 | 0 | 0 | 0 | 11868.5275 | 100% | NA ¦ NA | NA ¦ NA | NA | 100% | 0% | [Project Description - What] Initiative to provide safe access to the transmission structures where there is no proximate road access.
281 | TL623C Wood to Steel Project |  |  | San Diego, San Diego | This project replaces 4/0 B.S. CU Conductor. OH Full Rebuild approx. 1.30 miles from structure Z180990 to Z181008 South of Otay Valley Regional Park Removes 19 existing wood structures. | Transmission Line - Multiple | Replace | NA | NA | Wildfire Mitigation | System Design Upgrade | NERC TPL Standards | NA | 2024-01-16 12:00 | 60 | Steady State Power Flow System Analysis | Wires - Reconductor/Line Rebuild Alternative | $10 Mil -$15 Mil | HFTD Tier 2 | FALSE ¦ FALSE ¦ TRUE | FALSE | NA |  | 1.6 | NA | 69 | NA | 2.1 | 2020-0327 | QS00634 | 1 | 21148 | NA ¦ NA ¦ NA ¦ NA | FALSE | NA | Work Order Authorization | NA | 2018 | FALSE | 2018 | NA | https://www.caiso.com/planning/Pages/TransmissionPlanning/2017-2018TransmissionPlanningProcess.aspx | FALSE | NA | NA | NA | NA | NA | NA | TBD | 2026-10-29 | To be Filed | 2029 | Engineering less than 50% complete | NA | 2026-10-08 | 2026-12-31 | 2026-12-28 | Other [See Notes] | NA | TRUE | NA | NA ¦ NA | 2307.3612 | 0 | 0 | 0.52013 | 30.4255 | 111.4943 | 78.0918 | 196.364 | 1890.4655 | 0 | 0 | 0 | 0 | NA | NA | 2024 ¦ 2025 | 0 | 0 | 0 | 0 | 142.4399 | 196.364 | 0 | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [Reason for Change in In-Service Date] In-service dates are estimated during preliminary design and permitting stages of a project; date shifted to reflect actual design and construction schedule.
282 | TL6905 Headquarters Point UG Customer Relocation |  |  | San Diego, San Diego County | Customer-requested relocation project. Relocate portion of TL6905 from overhead to underground between Structure Z90429 and Z96512. Project is 100% reimbursable. | Transmission Line - Multiple | Relocate | NA | NA | Work Requested by Others | Facility Relocation | NA | NA | 2024-05-04 | 60 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | TBD |  | 0.25 | NA | 69 | NA | 1 | 2021-0341 | QS00624 | 1 | 21149 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2021-10-25 | Work Order Authorization | 2022 | NA | FALSE | NA | NA | NA | FALSE | TBD | NA | NA | NA | CPUC | NA | Advice Letter | 2024-06-28 | Approved | 2024 | Engineering more than 50% complete | NA | 2026-03-16 | 2024-12-31 | 2026-06-30 | NA | NA | TRUE | 7066.8 | NA ¦ NA | 1812.4199 | 0 | 0 | 0 | 0 | 5.8208e-14 | 154.9878 | 1657.4321 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2025 | 0 | 0 | 0 | 0 | 0 | 1657.4321 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
283 | [Programmatic] TCM Non |  |  | NA | Transmission jobs in the non-HFTD to comply with SDG&E's obligation to serve and meet safety requirements set by General Orders 95,128, and other regulations. Budget provides resources to provide support to reactive issues that arise such as storm, fire and pole car contact. The majority of the activities that fall under this blanket budget are necessary to comply with Federal, State , and Local regulations. Activities include poles that need to be replaced due to deterioration, capital repairs related to inspections (visual, infrared, LiDAR, etc.), and emergency situations. This work is scheduled and managed by Transmission, Construction & Maintenance. | Transmission Line - Multiple | Upgrade/Retrofit | NA | NA | Reliability | Construct Roads/Gates/Culverts | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | Multiple | NA | 1.2 | Multiple | QBL0135 | 455 | 21150 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-09-27 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Operational | NA | NA | 2024-12-31 | NA | NA | NA | TRUE | NA | NA ¦ NA | 0 | 5706.8514 | 7358.4206 | 2271.8293 | 3868.056 | 5689.9593 | 1473.0885 | 4208.0299 | 3523.6412 | 3905.5394 | 4335.7944 | 4812.3434 | 4132.873 | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 637.5717 | 1657.1346 | 732.6568 | 1599.5469 | 5662.0042 | 1929.5362 | 0 | NA ¦ NA | NA ¦ NA | NA | 13.55% | 86.45%
284 | A TL676 Z96677 NEW ACCESS RD AND |  |  | San Diego, San Diego | Mobilize, Clear and Grub Pad, Place BMP's Rough Grade, Over Excavate and Compact Pad, Place 9" of Class 2 base, Over excavate and compact Access Rd, Place 9" of class 2 base on road, Form and construct wall footings and CMU wall, Waterproof and Backfill Wall, Construct Brow and Wall ditch, Construct Cross Gutter, Install Rip-rap Dissipater with Filter Fabric, Construct Type D Brow ditch, install Cable railing at CMU wall. Demobilize. | Transmission Line - Right of Way | Upgrade/Retrofit | NA | NA | Safety | Construct Roads/Gates/Culverts | NA | NA | 2024-03-12 12:00 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69 | NA | 1.2 | 2023-3244 | QBL0135 | 1 | 21150 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-01-12 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | 2023-02-06 | 2023-12-31 | 2023-07-12 | NA | NA | TRUE | NA | NA ¦ NA | 1308.0284 | 0 | 0 | 0 | 1303.151 | 4.8774 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2023 ¦ 2024 | 0 | 0 | 0 | 1303.151 | 4.8774 | 0 | 0 | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [Age of Asset] Unable to provide age of asset for Programmatic budget codes
285 | A ET/OH CORRECTIVE MAINT PROGRAM |  |  | NA | Transmission jobs in the Non-HFTD to comply with SDG&E's obligation to serve and meet safety requirements. This work order provides resources to support reactive issues that arise such as storm, fire and pole car contact. The majority of the activities that fall under this blanket work order are necessary to comply with Federal, State , and Local regulations. Activities include poles that need to be replaced due to deterioration, capital repairs related to inspections (visual, infrared, LiDAR, etc.), and emergency situations. This work is scheduled and managed by Transmission, Construction & Maintenance. | Other - Civil | Upgrade/Retrofit | Multiple Options [See Notes] | NA | Asset Condition | T-Line Reliability | NA | NA | 2024-02-03 12:00 | NA | NA | NA | NA | HFTD Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | NA | NA | Multiple | NA | 1.2 | Multiple | QBL0135 | 3 | 21150 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-01-01 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Operational | NA | NA | 2024-12-31 | NA | NA | NA | TRUE | NA | NA ¦ NA | 13827.546 | 4590.6488 | 6268.6902 | 1463.9724 | 68.5797 | -0.35353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 ¦ 2024 | 4590.6488 | 6268.6902 | 1463.9724 | 68.5797 | -0.35353 | 0 | 0 | NA ¦ NA | NA ¦ NA | NA | 13.55% | 86.45% | [Utility Unique ID #1] 2022-3131 , 2022-2726 , 2022-3133 [Project Description - Action Taken (2)] This is a blanket work order for activities that are necessary to comply with Federal, State , and Local regulations. Multiple Options can be selected.
286 | [Programmatic] Generation Interconnection Projects |  |  | NA | This is a blanket authorization for a multitude of CAISO mandated projects. CAISO approval for these projects is made in the form of a Three Party Interconnection Agreement. SDG&E has historically undertaken work for many of these types of projects to enhance and maintain reliability of the transmission grid. These projects are typically Battery Energy Storage (BESS) or other renewable projects from external parties where infrastructure is created in order to connect to SDG&E's grid through genties connecting to one of the company's many existing 69kV and above substations. Typical scope of these projects include the construction of Interconnection Facilities (ICF) which are 100% customer funded as well as Reliability Network Upgrades (RNU's) will be charged to ratepayers. Given the similar nature of many of these projects as well as the fact that the majority of these costs are refundable, our proposal will be to combine the scope of all existing projects with schedules shifting out into next year and future projects into one authorization for 2022 and future years on an annual basis. | Multiple Options [See Notes] | New | Multiple Options [See Notes] | NA | Generator Interconnection | Generation Interconnection | CAISO Requirement | CAISO Requirement | NA | NA | NA | Other - Status Quo | NA | Multiple | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69kV ¦ 500kV | 69kV - 500kV | 2.1 | Multiple | QBL0141 | 120 | 21156 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-11-28 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | TRUE | NA | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Planning | NA | NA | 2024-12-31 | Multiple | NA | Multiple Options [See Notes] | TRUE | NA | NA ¦ NA | 0 | 1421.9087 | 5294.8663 | 3160.592 | -1767.2295 | 3410.6889 | 2338.6223 | -9441.4103 | -2144.3574 | 430.9476 | 44.1944 | 41.7316 | 12001.8105 | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 130.2875 | 4832.135 | 3302.2053 | -4355.54 | -1900.4305 | -1202.6445 | 0% | Multiple | 3.63 | NA | 13.55% | 86.45% | [Project Description - What] Project scope and description varies for projects; Permitting and CEQA responsibility of 3rd party interconnection customers (not SDG&E); status varies by project [CPUC Status] NA Reason for Change in In-Service Date (2) [Project Description - Action Taken (2)] This is a blanket authorization for a multitude of CAISO mandated projects. [Project Description - Action Taken 2] ?
287 | G CAPTIVA STORAGE PTO IF |  |  | San Juan Capistrano, Orange | BRP CA Holdco II LLC, an Interconnection Customer (IC), submitted a completed Interconnection Request (IR) to the California Independent System Operator Corporation (CAISO) to interconnect Captiva Energy Storage (Project) to the CAISO Controlled Grid. The Project is a battery energy storage system (BESS) generating facility with a requested net output of 250 MW at the Point of Interconnection (POI). The IC requested that the POI for the Project be a loop at the Trabuco - Capistrano 138 kV line. | Substation - Multiple | New | NA | NA | Generator Interconnection | New Substation | CAISO Requirement | CAISO Requirement | 2024-02-29 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 4.78 | 138 | 138kV | 2.1 | 2021-2462 | QBL0141 | 1 | 21156 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2021-09-03 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | TRUE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Engineering more than 50% complete | NA | 2026-02-19 | 2024-05-01 | 2026-10-06 | Customer Action | Customer Action | FALSE | NA | NA ¦ NA | 23124.3748 | 0 | 19.7099 | 141.9853 | 283.8416 | 219.4763 | 16.9398 | 31.9664 | 3.5003 | 22406.9553 | 0 | 0 | 665.0131 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [Project Description - What] New 138kV Switchyard and 138kV Transmission loopin for Customer's new 250MW Battery Storage (BESS) facility in San Juan Capistrano ; Permitting in review by CEC; CEQA Determination: The IC is pending discretionary approval – SDG&E Environmental will review the permits and environmental document once received. [Project Status] In Service Date and Construction Date updated from latest customer design and construction schedule dated 11/14/2024 [Age of Asset] NA - New Substation (138kV Switchyard) [CPUC Status] Per SDG&E Infrastructure Review Group Presentation on 8/21/2024, project exempt (IRG Determination: Exempt / No Advice Letter Required) Exempt
288 | A SANDPIPER ENERGY STORAGE RNU |  |  | Orange County | Falcon Energy Storage Holdings, LLC, an Interconnection Customer (IC), submitted a completed Interconnection Request (IR) to the California Independent System Operator Corporation (CAISO) to interconnect Sandpiper Storage (Project) to the CAISO Controlled Grid. The Project is a battery energy storage system (BESS) generating facility with a requested net output of 200 MW at the Point of Interconnection (POI). The IC requested that the POI for the Project be at a Talega 138 kV substation. | Substation - Multiple | Upgrade/Retrofit | Upgrade/Retrofit | NA | Generator Interconnection | Generation Interconnection | CAISO Requirement | CAISO Requirement | 2024-10-24 | NA | NA | NA | NA | HFTD Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 6.92 | 138 | 138kV | 2.1 | 2022-2757 | QBL0141 | 1 | 21156 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2021-10-26 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | TRUE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Construction (50%-75%) | NA | 2024-10-07 | 2023-06-01 | TBD | Customer Action | Customer Action | FALSE | NA | NA ¦ NA | 1202.4224 | 0 | 4.3253 | 261.4703 | 437.8069 | 28.1611 | 62.5975 | 342.224 | 65.8374 | 0 | 0 | 0 | 731.7635 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 6% ¦ 180 | NA ¦ NA | NA | 0% | 100% | [CPUC Status] NA
289 | A Q1170 GATEWAY ENERGY STORAGE |  |  | San Diego County | This project interconnected 250MW of battery storage at the Otay Mesa switchyard | Other | New | New | NA | Generator Interconnection | System Operations | CAISO Requirement | CAISO Requirement | 2024-10-23 | NA | NA | NA | NA | HFTD Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 32.81 | 230 | NA | 2.1 | 2018-1008 | QBL0141 | 1 | 21156 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-07-24 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | TRUE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | 2018-10-24 | 2020-05-31 | 2020-05-28 | NA | NA | TRUE | NA | NA ¦ NA | 1501.4178 | 86.0672 | 0.3199 | 41.6612 | 0 | -2e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2024 | 1459.4367 | 0.3199 | 41.6612 | 0 | -2e-05 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0%
290 | A Q1532 KETTLE SOLAR ONE SANU |  |  | San Diego County | Generation interconnection project; interconnection customer responsible for design, procurement, and construction of new 138kV Carrizo Gorge switchyard and 138 kV loop in; SDG&E will purchase these high voltage assets from the interconnection customer; SDG&E providing design and construction oversight | Multiple Options [See Notes] | New | NA | NA | Generator Interconnection | Generation Interconnection | NA | NA | 2024-01-25 12:00 | NA | NA | NA | NA | HFTD Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 1.94 | 138 | 138kV | 2.1 | 2019-0227 | QBL0141 | 1 | 21156 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2020-07-27 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | TRUE | NA | NA | NA | NA | NA | NA | Advice Letter | 2027-02-16 | To be Filed | 2027 | Engineering less than 50% complete | NA | 2025-10-01 | 2022-10-01 | 2026-08-01 | NA | NA | FALSE | NA | NA ¦ NA | 8838.7372 | 2.9938 | 37.3978 | 104.3318 | 77.6388 | 279.7443 | 32.6663 | 252.418 | 120.6607 | 7930.8857 | 0 | 0 | 502.1065 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 58% ¦ 11200 | NA ¦ NA | NA | 0% | 100% | [Project Description - What] New 138kV switchyard and 138kV loop in [Percentage of Work Requested by Others Passed onto Ratepayers] Percentage of Work Requested by Others Passed onto Ratepayers based: etimated total network upgrade cost of $19.4M; the total maximum reimbursement from SDG&E to the interconnection customer (estimated based on CAISO's Jul 2024 - Jun 2025 rate escalated to late 2026 COD) is ~$121,375/MW; the generator facility is 92MW; so the total amount SDG&E would reimburse the customer is ~$11.2M, or 58% of $19.4M.
291 | A MIRAMAR GT INTCON TOP GUN SRG 6 |  |  | San Diego County | Provide cost estimate for CAISO Cluster 10 request to connect 30MW net output at Point of Interconnection for Battery Storage at Miramar GT 69kV. Cost estimate is for PTO Interconnection Facility Substation assuming an underground connection consisting of: one 69kV Circuit Breaker, two 69kV Disconnects, one 69kV PT, surge arrestor and terminations at the Miramar rack and associated foundations, structures and relaying. Cost estimate is also for PTO IF Transmission consisting of 1000 feet of trench and conduit, 1000 circuit feet of cable and one termination stand at the Miramar GT 69kV rack and redundant line of communications and associated infrastructure.​ | Other | New | New | NA | Generator Interconnection | System Operations | CAISO Requirement | CAISO Requirement | 2024-10-02 | NA | NA | NA | NA | HFTD Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 0.23 | 69 | NA | 2.1 | 2014-01105-ZZ | QBL0141 | 1 | 21156 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2018-05-16 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | TRUE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | 2019-05-13 | 2019-12-01 | 2020-07-22 | NA | NA | FALSE | NA | NA ¦ NA | 1300.8659 | 820.025 | 26.357 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2020 ¦ 2021 | 1274.5088 | 26.357 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
292 | A SANU MT LAGUNA WIND 2 |  |  | San Diego County | Boulder Brush, LLC Q1429 is a 400MW Generation Facility that requires a new 500kV swithcyard between Suncrest-Ocotillo 500kV line located on the Campo Indian Reservation in Mountain Empire in San Diego County, CA. | Substation - Multiple | New | NA | NA | Generator Interconnection | New Substation | CAISO Requirement | CAISO Requirement | 2024-10-09 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | TBD |  | 0.38 | NA | 500 | 500kV | 2.1 | 2017-0140 | QBL0141 | 1 | 21156 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-07-24 | Work Order Authorization | 2024 | NA | FALSE | NA | NA | NA | TRUE | TBD | NA | NA | NA | CPUC | NA | NA | NA | Other [See Notes] | NA | On Hold | NA | NA | 2024-12-31 | NA | NA | NA | FALSE | NA | NA ¦ NA | 36634.6085 | 0 | 0 | 0 | 1.2724 | 153.3565 | 3.4295 | 14.4957 | 15.8251 | 17.2765 | 8.563 | 36420.3898 | 154.6289 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0% | [CPUC Status] NA - On hold due to customer.
293 | G SANDPIPER ENERGY STORAGE PTOIF |  |  | Orange County | Falcon Energy Storage Holdings, LLC, an Interconnection Customer (IC), submitted a completed Interconnection Request (IR) to the California Independent System Operator Corporation (CAISO) to interconnect Sandpiper Storage (Project) to the CAISO Controlled Grid. The Project is a battery energy storage system (BESS) generating facility with a requested net output of 200 MW at the Point of Interconnection (POI). The IC requested that the POI for the Project be at a Talega 138 kV substation. | Substation - Multiple | Upgrade/Retrofit | Upgrade/Retrofit | NA | Generator Interconnection | Generation Interconnection | CAISO Requirement | CAISO Requirement | 2024-10-24 | NA | NA | NA | NA | HFTD Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | TBD |  | NA | 6.92 | 138 | 138kV | 2.1 | 2022-2757 | QBL0141 | 1 | 21156 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2021-10-26 | Work Order Authorization | 2022 | NA | FALSE | NA | NA | NA | TRUE | TBD | NA | NA | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Construction (50%-75%) | NA | 2024-10-07 | 2023-06-01 | TBD | Customer Action | Customer Action | FALSE | NA | NA ¦ NA | -1056.8625 | 0 | 2.2577 | 20.9271 | 294.4463 | 464.6555 | 793.5045 | 1260.2884 | -3892.942 | 0 | 0 | 0 | 782.2866 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] NA
294 | A PEREGRINE RNU |  |  | San Diego, San Diego County | The Project is a 200 MW battery energy storage system (“BESS”). The Point of Interconnection is at the 230 kV bus of PTO’s existing Silvergate Substation. Point of Change of Ownership (“POCO”) is located where the IC’s 230 kV generation tie line (“gen-tie”) crosses the vertical plane of the PTO’s property line surrounding the Silvergate Substation. The IC’s Interconnection Facilities include 230 kV underground cable and conduit package from the POCO to the Project’s substation. | Substation - Multiple | Upgrade/Retrofit | Upgrade/Retrofit | NA | Generator Interconnection | Generation Interconnection | CAISO Requirement | CAISO Requirement | 2024-10-21 | 2 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | TBD |  | NA | 4.58 | 230 | 230kV | 2.1 | 2020-0319 | QBL0141 | 1 | 21156 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2021-04-28 | Work Order Authorization | 2022 | NA | FALSE | NA | NA | NA | TRUE | TBD | NA | NA | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Construction (over 75%) | NA | 2024-03-11 | 2022-09-30 | 2025-01-03 | Customer Action | Customer Action | FALSE | NA | NA ¦ NA | 1418.1753 | 0 | 18.568 | 284.5556 | 495.2361 | 546.077 | 73.7385 | 0 | 0 | 0 | 0 | 0 | 1344.4368 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 60% ¦ 1898 | NA ¦ NA | NA | 100% | 0% | [CPUC Status] NA
295 | A EAST FIELD ENERGY CNTR PTO NU |  |  | San Diego County | The project will connect to the PTO's transmission system via the Project's 230kV gen-tie emanation from the Otay Mesa substation. | Substation - Multiple | Upgrade/Retrofit | Upgrade/Retrofit | NA | Generator Interconnection | Generation Interconnection | CAISO Requirement | CAISO Requirement | 2024-10-23 | NA | NA | NA | NA | HFTD Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | TBD |  | NA | 32.81 | 230 | 230kV | 2.1 | 2024-3985 | QBL0141 | 1 | 21156 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-05-01 | Work Order Authorization | 2024 | NA | FALSE | NA | NA | NA | TRUE | TBD | NA | NA | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Engineering less than 50% complete | NA | 2027-03-11 | 2027-04-30 | 2027-09-27 | Material | NA | FALSE | NA | 5791000 ¦ ISO | 4334.4647 | 0 | 0 | 0 | 0 | 8.0341 | 39.9585 | 434.1435 | 1860.0122 | 1992.3164 | 0 | 0 | 8.0341 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 99% ¦ 4897 | NA ¦ NA | NA | 100% | 0% | Project in 30% design. Material lead time delays [CPUC Status] NA
296 | G Q1170 GATEWAY ENERGY STORAGE |  |  | San Diego County | Energization of additional 75MW on existing infrastructure built out as part of A Q1170 Gateway Energy Storage (Project ID: 2018-1008) | Other | New | New | NA | Generator Interconnection | System Operations | CAISO Requirement | CAISO Requirement | 2024-10-23 | NA | NA | NA | NA | HFTD Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | TBD |  | NA | 32.81 | 69 | NA | 2.1 | 2019-0224 | QBL0141 | 1 | 21156 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2018-07-20 | Work Order Authorization | 2019 | NA | FALSE | NA | NA | NA | TRUE | TBD | NA | NA | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2018-10-24 | 2019-11-01 | 2023-10-10 | NA | NA | FALSE | NA | NA ¦ NA | -2.0972 | 628.0595 | 2.917 | -2107.8404 | 7.4846 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 | 2095.3416 | 2.917 | -2107.8404 | 7.4846 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] NA
297 | Twin Engine Medium Lift Helicopter |  |  | Gillespie Field, San Diego | Purchase of a twin engine, multi­mission, medium lift helicopter for primary use of external load work. The helicopter allows for heavier lift capability for continual distribution and transmission work in the high fire threat district. The helicopter also has fire fighting capabilities | Other | New | NA | NA | Other [See Notes] | Safety - Line Right of Way Access | NA | NA | NA | 60 | NA | NA | NA | Tier 1 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | NA | NA | NA | NA | 1.2 | NA | QS00609 | 1 | 21256 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2021-08-21 | Work Order Authorization | 2021 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Operational | NA | 2017-03-06 | 2022-12-31 | 2023-01-23 | NA | NA | TRUE | 2119.6081 | NA ¦ NA | 2351.7684 | 0 | 368.2172 | 1658.298 | 208.6423 | 116.6109 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2023 ¦ 2024 | 0 | 0 | 0 | 2235.1575 | 116.6109 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [Primary Purpose] Initial investigation of potential projects. [CPUC Fire Threat Zone/Rating] it is not a physical project and therefore does not have an HFTD location.
298 | TL684 Hamann Escondido |  |  | San Diego County | Customer-requested relocation project. Remove four (4) existing transmission structures on TL 684 and replace with three (3) pre-engineered structures to accommodate property development. Project is 100% reimbursable. | Transmission Line - Multiple | Relocate | NA | NA | Work Requested by Others | Facility Relocation | NA | NA | 2024-03-02 | 60 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | TBD |  | 0.24 | NA | 69 | NA | 1 | 2022-2704 | QS00659 | 1 | 22125 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2022-06-28 | Work Order Authorization | 2023 | NA | FALSE | NA | NA | NA | FALSE | TBD | NA | NA | NA | CPUC | NA | Advice Letter | NA | To be Filed | 2025 | Engineering more than 50% complete | NA | 2025-10-20 | 2025-12-31 | 2026-02-23 | NA | NA | TRUE | 3500.4884 | NA ¦ NA | 8538.1788 | 0 | 0 | 0 | 0 | 0 | -79.9326 | 7750.5878 | 867.5235 | 0 | 0 | 0 | 0 | NA | NA | 2025 | 0 | 0 | 0 | 0 | 0 | 7670.6552 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
299 | [Programmatic] Transmission Power Quality |  |  | NA | This project will deploy Power Quality Meters in SDG&E electric substations on transmission circuits to enable the collection of time-series analog data used to detect incipient failures of electrical equipment and locate that failing equipment before it can cause significant damage. | Substation - Multiple | Upgrade/Retrofit | NA | NA | Reliability | Replace Other Substation Equipment | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | Multiple | 373MVA | 4.3 | Multiple | QBL0157 | 10 | 22126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-11-29 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | NA | 2024-12-31 | NA | NA | NA | TRUE | NA | NA ¦ NA | 0 | 28.5471 | 33.6898 | 491.093 | 866.1993 | 198.4672 | 225.8089 | 1338.7094 | 691.7806 | 745.9814 | 819.8485 | 911.0365 | 1077.647 | NA | NA | 2021 ¦ 2023 ¦ 2024 ¦ 2025 | 0 | 0.023536 | 0 | 664.4589 | 578.1482 | 558.6676 | 0% | NA ¦ NA | 26.1 | NA | 100% | 0%
300 | Wildfire Resiliency Platform (WiNGS) |  |  | NA | Predictive analytic capabilities for WiNGS using Digital Twin technology | Other - Operations Tech | New | NA | NA | Wildfire Mitigation | Automation | NA | NA | NA | 60 | NA | NA | NA | Tier 1 | TRUE ¦ TRUE ¦ TRUE | FALSE | NA |  | NA | NA | NA | NA | 1.2 | 53030 | QS00675 | 1 | 22255 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-06-30 | Work Order Authorization | 2022 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Operational | NA | NA | 2023-11-30 | NA | NA | NA | TRUE | 247.3305 | NA ¦ NA | 1157.2209 | 0 | 0 | 381.4164 | 653.8465 | 60.4421 | 0 | 61.5159 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2025 | 0 | 0 | 0 | 0 | 0 | 61.5159 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [Wildfire Related] Provides insights that support wildfire risk assessment and planning.[Primary Purpose] Initial investigation of potential projects.
301 | [Programmatic] Early Fault Detection |  |  | NA | This project will deploy Power Quality Meters and advanced Radio Frequency (RF) Sensors in SDG&E electric substations and electric distribution circuits within the High Fire Threat District to enable the collection of time-series analog data used to detect incipient failures of electrical equipment and locate that failing equipment before it can cause significant damage. The program will also fund various analytical / software tools utilized to aggregate this highly sampled data, analyze it and use it to triangulate the failure locations so crews may be dispatched to proactively inspect / investigate with a goal of preventing significant damage. | Substation - Multiple | Upgrade/Retrofit | NA | NA | Wildfire Mitigation | Automation | NA | NA | NA | NA | NA | NA | NA | HFTD Tier 2 ¦ HFTD Tier 3 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | NA | NA | NA | NA | 1.1 | Multiple | QBL0148 | 3 | 22256 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-11-22 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | NA | 2024-12-31 | NA | NA | NA | TRUE | NA | NA ¦ NA | 0 | 0 | 0 | 1224.6787 | 1043.8824 | 334.9114 | 157.4094 | 680.8005 | 722.2829 | 717.8283 | 7.8183 | 7.8183 | 0 | NA | NA | 2024 | 0 | 0 | 0 | 0 | 194.1129 | 0 | 0% | NA ¦ NA | 7.3 | NA | 0% | 0%
302 | A EFD WMP IPREDICT |  |  | San Diego County | Internal development of iPredict software platform | Other - Operations Tech | Upgrade/Retrofit | NA | NA | Wildfire Mitigation | Automation | NA | NA | NA | NA | NA | NA | NA | HFTD Tier 2 ¦ HFTD Tier 3 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | NA | NA | NA | NA | 1.1 | NA | QBL0148 | 1 | 22256 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2022-10-31 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | NA | 2026-12-31 | NA | NA | NA | FALSE | 0 | NA ¦ NA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0%
303 | Narrows Rebuild |  |  | San Diego County | The Narrows 88/69 kV bank is on Kearny’s “transformer watchlist” and is nearly 100 years old. The transformers are leaking oil and DGA reports indicate increasing furans, poor oil quality, deteriorating insulation, and dielectric breakdown within the transformer. The transformer is also not large enough to carry all load in the area. Grid Ops is operationally limited when using the Narrows interconnection to feed Borrego. Other infrastructure at the site is also well past its useful life. The TL800 circuit breaker is an oil breaker manufactured in 1968. The TL686 circuit breaker recently failed, forcing an unplanned outage, and was replaced with a system spare that has already been in service for 10 years. The steel bus structure likely does not meet seismic requirements, and the brown glass cap and pin insulators are a point of common failure. A TL687 breaker will be added to improve reliability of the connection to Borrego. There is evidence that the ground grid at Narrows is in poor condition. Portions of the ground grid are showing above the finished grade of the site. The grounding grid should be assessed during the design process to ensure that there are no step and touch potential concerns. During construction, any damage found will be repaired. Lastly, an updated fence will be installed to improve site security. | Substation - Multiple | Upgrade/Retrofit | NA | NA | Reliability | Age/Condition | NA | NA | 2024-10-29 | 55; 99; 99; 99 | NA | Wires - Replacement Alternative | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 0.526 | 69 | 69kV | 4.1 | NA | QS00722 | 1 | 23126 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-11-29 | Work Order Authorization | 2023 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | On Hold | NA | 2027-05-03 | 2026-12-31 | NA | NA | NA | FALSE | 3962 | NA ¦ NA | 9223.9462 | 0 | 0 | 0 | 4.6626 | 125.106 | 40.6821 | 3141.0813 | 5912.4142 | 0 | 0 | 0 | 129.7685 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | 38.1 | NA | 0% | 100%
304 | A CAST IV UPS |  |  | Imperial County | Substation Security (IV Substation CAST Fence); Security panel backup. | Substation - Other Equipment | New | NA | NA | Physical Security | Security Upgrades | NERC CIP Compliance | Other [See Notes] | 2024-10-30 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 55.48 | 238 ¦500 | 230kV ¦500kV | 2 | 2021-2097 | QBL0020 | 1 | 23127 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-11-09 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | 2020-11-30 | 2025-06-30 | 2026-01-30 | NA | NA | FALSE | 35000 | NA ¦ NA | 55.0556 | 0 | 0 | 0 | 0.29146 | 1315.5443 | -1286.3843 | 25.6041 | 0 | 0 | 0 | 0 | 1738.57 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0% | [NERC / WECC / CAISO Standard / Requirement / Contingency 2] NERC CIP Compliance and Security Assessments
305 | A CAST IV UPS |  |  | San Diego, San Diego ¦ Santee, San Diego ¦ Lakeside, San Diego ¦ Rancho San Diego ¦ San Diego ¦ Granite Hills, San Diego | Miguel-Sycamore Canyon 230kV Line Loop-in Suncrest | Transmission Line - Multiple | New | Upgrade/Retrofit | NA | Reliability | T-Line Reliability | NERC TPL Standards | NA | 2024-01-10 12:00 | 60 | Steady State Power Flow System Analysis | Wires - System Configuration Alternative | NA | HFTD Tier 2 | FALSE ¦ FALSE ¦ TRUE | FALSE | Coastal |  | 27.8 | NA | 230 | NA | 2 | 2018-0199 | QBL0020 | 1 | 23127 | NA ¦ NA ¦ NA ¦ NA | FALSE | NA | Work Order Authorization | 2023 | 2023 | FALSE | 2022 ¦ 2023 | NA | https://www.caiso.com/Documents/ISO-Board-Approved-2022-2023-Transmission-Plan.pdf | FALSE | TBD | NA | NA | NA | NA | NA | NA | NA | NA | NA | Planning | NA | NA | 2032-12-31 | NA | NA | NA | TRUE | 35000 | NA ¦ NA | 541329.9844 | 0 | 0 | 0 | 0.29146 | 1738.2784 | -1039.4903 | 2045.6897 | 3166.1375 | 119619.0716 | 128883.0278 | 138863.3143 | 0 | NA | NA | 2025 | 0 | 0 | 0 | 0 | 0 | 55.0556 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0% | ; FERC Only - new project
306 | [Programmatic] A CNF PLRP PROJ MGMT/PMO |  |  | NA | The scope for this project includes post-construction habitat restoration that is required by project permits for temporarily impacted mitigatable vegetation communities. This includes restoration implementation (weed control and seeding), supplemental seeding, monitoring and maintenance, reporting, and agency meetings/site visits. | Other | NA | NA | NA | Other [Add Notes in Column AX] | Environmental | NA | NA | NA | NA | NA | NA | NA | HFTD Tier 2 ¦ HFTD Tier 3 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | Multiple | NA | 2 | Multiple | QBL0159 | 1 | 23128 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-12-13 | Work Order Authorization | 2024 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Operational | NA | 2018-12-01 | 2029-12-31 | 2029-12-31 | NA | NA | FALSE | 271.3179 | NA ¦ NA | 1193.1291 | 0 | 0 | 0 | 0 | 31.4572 | 45.5917 | 234.0704 | 236.6879 | 197.6525 | 215.7798 | 231.8897 | 31.4572 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] NA
307 | [Programmatic] Substation External Routable Connectivity (SERC) |  |  | NA | The SERC program deploys secure routable protocol connections providing event retrieval, password management and remote secure event access to all CIP Medium, Low and No Impact substations. It achieves this by deploying Advanced Relay Event Retrieval (ARER) hardware, Siemens Crossbow devices, and deployment of systems in support thereof. The program also analyses and tests emerging ERC technology use cases and solutions. | Substation - Other Equipment | Upgrade/Retrofit | NA | NA | Reliability | System Operations | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | Multiple | NA | 4.3 | Multiple | QBL0160 | 26 | 23129 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-11-22 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | NA | 2024-12-31 | NA | NA | NA | TRUE | 3560 | NA ¦ NA | 0 | 0 | 0 | 0 | 1.9057 | 786.9531 | 2403.0248 | 4540.0849 | 4457.7828 | 5013.3426 | 5625.0419 | 6298.1153 | 733.214 | NA | NA | 2024 ¦ 2025 | 0 | 0 | 0 | 0 | 301.8553 | 4642.8395 | 0% | NA ¦ NA | 11.3 | NA | 0% | 0% | [Age of Asset] New asset installed, no previous asset
308 | [Programmatic] Customer Relocation Projects - Internally Funded |  |  | NA | Blanket budget code for internally funded customer relocation projects. | Transmission Line - Multiple | Relocate | NA | NA | Work Requested by Others | Facility Relocation | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | NA | NA | 3.1 | Multiple | QBL0166 | 5 | 23130 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-02-21 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Operational | NA | NA | 2024-12-31 | NA | NA | NA | TRUE | NA | NA ¦ NA | 0 | 0 | 106.3306 | 523.5509 | 852.4893 | 717.8382 | 190.9053 | 2021.0323 | 90.5933 | 30.9836 | 31.4119 | 31.8461 | 1994.832 | NA | NA | 2025 | 0 | 0 | 0 | 0 | 0 | 2759.1348 | 0% | NA ¦ NA | 3.6 | NA | 0% | 0% | [Long Term Transmission Investment Plan Inclusion] new budget code created in late 2023. [Age of Asset] Programmatic
309 | [Programmatic] Customer Relocation Projects - Externally Funded |  |  | NA | Blanket budget code for externally funded customer relocation projects. | Transmission Line - Multiple | Relocate | NA | NA | Work Requested by Others | Facility Relocation | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | NA | NA | 3.1 | Multiple | QBL0164 | 5 | 23131 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-02-12 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Operational | NA | NA | 2024-12-31 | NA | NA | NA | TRUE | NA | NA ¦ NA | 0 | 0 | -62.8192 | -754.7417 | -651.0941 | 227.0414 | 1122.5585 | 331.9345 | 195.0644 | 84.0166 | 85.1779 | 86.3553 | 961.055 | NA | NA | 2022 ¦ 2023 ¦ 2024 ¦ 2025 | 0 | 0 | -120.2588 | 77.8694 | -133.1808 | -572.9296 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [Long Term Transmission Investment Plan Inclusion] new budget code created in late 2023.
310 | BK30, BD: New Bank 30 |  |  | San Diego, San Diego County | This project will be installing a New Bank 30MVA at Border Substation to address an overload. | Substation - Transformer | New | New | NA | Load Growth | Substation Capacity | NA | NA | 2024-10-03 | NA | NA | NA | NA | HFTD Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 0.94 | NA | NA | 1 | 3-578735 | QS00703 | 1 | 23242 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2023-09-21 | Work Order Authorization | 2024 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Construction (under 10%) | NA | 2025-1-1 | 2025-12-31 | 2025-08-11 | NA | NA | TRUE | 11703.4576 | NA ¦ NA | 3544.34 | 0 | 0 | 0 | 110.2998 | 1614.2154 | 1481.1916 | 338.6332 | 0 | 0 | 0 | 0 | 1724.5152 | NA | NA | 2025 | 0 | 0 | 0 | 0 | 0 | 3544.34 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0% | [CPUC Status] NA
311 | OT33, OT: New Sub Bank 33 |  |  | San Diego, San Diego County | Instatallion of 69/12kv substation transformer and assoicated equipment | Substation - Transformer | New | NA | NA | Load Growth | Load Interconnection | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 2.78 | Multiple | 28 MVA | 1 | 3-684733 | QS00713 | 1 | 23258 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-05-01 | Work Order Authorization | 2024 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Engineering less than 50% complete | NA | 2026-06-01 | 2024-12-31 | 2027-06-01 | NA | NA | TRUE | 8648.8448 | NA ¦ NA | 1493.712 | 0 | 0 | 0 | 0.41068 | 2.5873 | 208.2185 | 1282.4956 | 0 | 0 | 0 | 0 | 2.998 | NA | NA | 2025 | 0 | 0 | 0 | 0 | 0 | 1493.712 | NA ¦ NA | NA ¦ NA | 6.2 | NA | 0% | 0% | [CPUC Status] No CPUC approval is required for this project
312 | TL631 UG Cable Replacement Project |  |  | El Cajon, San Diego | Project Scope: Remove and replace failing underground cables on TL631 that have been in operation for ~30years. The hand-taped splices are exhibiting significant degradation with (3) cable failures in the past 3 years. | Transmission Line - Underground | Upgrade/Retrofit | NA | NA | Reliability | Age/Condition | NA | NA | 2024-01-23 | 60 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 1 | NA | 69 | NA | 4.1 | 2024-3662 | QS00731 | 1 | 24125 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-01-16 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Operational | NA | 2024-02-26 | 2024-08-30 | 2024-04-21 | NA | NA | TRUE | 6625.166 | NA ¦ NA | 6577.1962 | 0 | 0 | 0 | 0 | 6577.1962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2024 | 0 | 0 | 0 | 0 | 6577.1962 | 0 | 0 | NA ¦ NA | NA ¦ NA | NA | 0% | 100%
313 | 3 ohm Series Reactor on Sycamore Penasquitos 230 kV line |  |  | San Diego, San Diego | Install a new 3 ohm series reactor on the Sycamore – Penasquitos 230 kV line | Substation - Reactive Equipment | New | NA | NA | Other [See Notes] | Voltage Support | CAISO Requirement | NA | 2024-02-13 12:00 | NA | Steady State Power Flow System Analysis | NA | $5 Mil - $10 Mil | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 13.94 | 230 | 230 kV | 2.1 | 2022-3181 | QS00735 | 1 | 24126 | NA ¦ NA ¦ NA ¦ NA | FALSE | NA | Work Order Authorization | NA | 2023 | FALSE | 2022 ¦ 2023 | 2023 | https://www.caiso.com/Documents/ISO-Board-Approved-2022-2023-Transmission-Plan.pdf | TRUE | NA | NA | NA | NA | NA | NA | TBD | NA | NA | NA | Engineering less than 50% complete | NA | 2025-10-01 | 2032-12-31 | 2026-06-02 | NA | NA | FALSE | 7290 | NA ¦ NA | 19073.0963 | 0 | 0 | 0 | 0 | 177.6528 | 254.542 | 9244.736 | 9396.1655 | 0 | 0 | 0 | 177.6528 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 100% | 0% | [Primary Purpose] Project identified in 2022-23 CAISO Transmission Planning Process
314 | Rearrange TL23013 PQ OT and TL6959 PQ Mira Sorrento |  |  | San Diego. San Diego | Alternative to 2020-0291 (Relocate OH Section of TL23071 to UG)​Per CAISO request to SDG&E to identify potential solutions to address the overload problems on TL13810 (FR-DD-PQ) caused by credible P7 (N-2: TL23013 & TL23071) contingency. The overload has created some system operation congestions that will increase ​the operating cost to address system reliability. This project is proposed to swap TL23013 and TL6959 from PQ (2 miles between Z479065 and Z100258). To do that it will require to upgrade 2 miles of existing TL13810 structures to 230kV double circuit structures for TL23013 with 2-1033 ACSR and TL13810 with 1-1033 ACSR. TL23013 & TL13810 will share the same structures and TL23071 and TL6959 will be on the other structures. This will eliminate the credible P7 outage (N-2 TL23013 & TL23071)​. | Transmission Line - Multiple | Relocate | NA | NA | Other [See Notes] | T-Line Reliability | CAISO Requirement | NA | 2024-02-13 12:00 | 60 | Steady State Power Flow System Analysis | NA | $20 Mil - $30 Mil | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 2 | NA | 69 kV ¦ 138 kV ¦ 230 kV | NA | 2.1 | 2020-0294 | QS00736 | 1 | 24127 | NA ¦ NA ¦ NA ¦ NA | FALSE | NA | Work Order Authorization | NA | 2023 | FALSE | 2022 ¦ 2023 | 2023 | https://www.caiso.com/Documents/ISO-Board-Approved-2022-2023-Transmission-Plan.pdf | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Planning | NA | NA | 2032-06-01 | NA | NA | NA | FALSE | 17942 | NA ¦ NA | 18418.2132 | 0 | 0 | 0 | 0 | 69.7723 | 136.8626 | 1903.2119 | 2588.4786 | 2211.648 | 2281.648 | 2306.648 | 69.7723 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 13.55% | 86.45% | [Primary Purpose] Project identified in 2022-23 CAISO Transmission Planning Process
315 | [Programmatic] Transmission Failing Cable Replacement |  |  | San Diego County | Replace underground cable systems targeting hand taped splices exhibiting degradation leading to failure. | Transmission Line - Underground | Upgrade/Retrofit | NA | NA | Reliability | Age/Condition | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 23 | NA | Multiple | NA | 4.1 | Multiple | QBL0171 | 2 | 24129 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-05-29 | Work Order Authorization | 2024 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA | NA | Planning | NA | NA | 2024-12-31 | NA | NA | NA | FALSE | 31289.7138 | NA ¦ NA | 116608.8224 | 0 | 0 | 0 | 0 | 0 | 10879.4312 | 21909.6265 | 24511.1175 | 19186.8908 | 20912.1688 | 19209.5875 | 0 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA ¦ NA | 37.4 | NA | 0% | 0%
316 | A UG TRANS CABLE REPL: 2024 SCOPE |  |  | San Diego County | Replace underground cable systems targeting hand taped splices exhibiting degradation leading to failure. | Transmission Line - Underground | Upgrade/Retrofit | NA | NA | Reliability | Age/Condition - Replace Underground System | NA | NA | 4/15/2024; 9/12/2024; 4/15/2024; 9/28/2022 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 3 | NA | 69 | NA | 4.1 | 2024-3828 | QBL0171 | 1 | 24129 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-06-04 | Work Order Authorization | 2024 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Construction (over 75%) | NA | 2024-10-01 | 2024-12-31 | 2025-03-15 | NA | NA | FALSE | 134697.3219 | NA ¦ NA | 8978.2474 | 0 | 0 | 0 | 0 | 8810.5284 | 167.7189 | 0 | 0 | 0 | 0 | 0 | 8810.5284 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] Project was Exempt from CPUC filing per GO-131D.
317 | TL680C MELROSE RECONDUCTOR |  |  | Oceanside, San Marcos, San Diego County | Address the existing San Marcos Substation-Melrose Tap constraint by reconductoring the line to 250MVA | Transmission Line - Conductor | Upgrade/Retrofit | NA | NA | Policy | T-Line Capacity | CAISO Requirement | CAISO Requirement | 2024-05-24 | 60 | Steady State Power Flow System Analysis | Wires - Reconductor/Line Rebuild Alternative | $15 Mil - $20 Mil | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 6.3 | NA | 69kV | NA | 2 | 2024-4035 | QS00743 | 1 | 24130 | NA ¦ NA ¦ NA ¦ NA | FALSE | NA | Work Order Authorization | 2024 | 2023 | FALSE | 2022 ¦ 2023 | 2023 | https://www.caiso.com/Documents/ISO-Board-Approved-2022-2023-Transmission-Plan.pdf | FALSE | NA | NA | NA | NA | NA | NA | TBD | 2028-02-01 | To be Filed | 2030 | Planning | NA | 2026-10-02 | 2032-12-31 | 2031-05-12 | NA | NA | FALSE | 2000 | NA ¦ NA | 27237.8369 | 0 | 0 | 0 | 0 | 19.2209 | 35.1292 | 1444.2371 | 2661.0124 | 2905.0571 | 3171.4835 | 3462.3441 | 19.2209 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA ¦ NA | 0.4 | NA | 0% | 100%
318 | TL13820 CHICARITA RECONDUCTOR |  |  | Poway, San Diego County | Reconductor the line to 250MVA from Chicarita Substation to Sycamore Canyon | Transmission Line - Conductor | Upgrade/Retrofit | NA | NA | Policy | T-Line Capacity | CAISO Requirement | CAISO Requirement | 2024-03-02 | 60 | Steady State Power Flow System Analysis | Wires - Reconductor/Line Rebuild Alternative | $15 Mil - $20 Mil | HFTD Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 6 | NA | 138kV | NA | 2 | 2024-4036 | QS00744 | 1 | 24131 | NA ¦ NA ¦ NA ¦ NA | FALSE | NA | Work Order Authorization | 2024 | 2023 | FALSE | 2022 ¦ 2023 | 2023 | https://www.caiso.com/Documents/ISO-Board-Approved-2022-2023-Transmission-Plan.pdf | FALSE | NA | NA | NA | NA | NA | NA | TBD | TBD | NA [See Notes] | TBD | Planning | NA | TBD | 2032-12-31 | TBD | NA | NA | FALSE | 2000 | NA ¦ NA | 57185.1502 | 0 | 0 | 0 | 0 | 27.1109 | 53.6748 | 2586.0085 | 9642.3993 | 10526.7155 | 11492.1335 | 12546.0912 | 27.1109 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA ¦ NA | 0.8 | NA | 0% | 100% | [CPUC Status] NA
319 | North City West Substation |  |  | San Diego, San Diego County | Add two 28MVA transformer banks to the North City West Substation in order to address the overload conditions expected in 2029. | Substation - Transformer | New | NA | NA | Load Growth | Substation Capacity | NA | NA | 2024-09-10 | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 1.04 | 69/12kV | 69/12kV | 4 | 2024-4028 | QS00748 | 1 | 24132 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2024-06-17 | Work Order Authorization | 2024 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | TBD | TBD | NA [See Notes] | TBD | Planning | NA | TBD | 2029-12-31 | TBD | NA | NA | FALSE | 2003.252 | NA ¦ NA | 82549.0892 | 0 | 0 | 0 | 0 | 36.2213 | 133.2337 | 3000.8613 | 15749.7457 | 17194.6983 | 18772.2186 | 20262.6014 | 36.2213 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [CPUC Status] NA
320 | CIS Envision |  |  | NA | Replacing SDG&E's legacy Customer Information System (CIS) with a new SAP system | Other - IT | Replace | NA | NA | Age/End of Life | Age/Condition | NA | NA | NA | 60 | NA | NA | NA | Tier 1 | FALSE ¦ FALSE¦ FALSE | FALSE | NA |  | NA | NA | NA | NA | NA | NA | QS00194 | 1 | CIS001 | NA ¦ NA ¦ NA ¦ NA | TRUE | 2018-09-11 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Application 17-04-027 | 2017-04-27 | Approved | 2018 | Operational | NA | NA | 2021-01-31 | NA | NA | NA | FALSE | NA | NA ¦ NA | 30554.2341 | 10359.5385 | 7032.298 | 2.6294 | 0 | 0 | 286.5418 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2020 ¦ 2021 ¦ 2022 | 65.1971 | 29155.1242 | 2.6294 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 0% | 0%
321 | Cleveland National Forest Master Special Use Permit |  |  | San Diego County | Cleveland National Forest Master Special Use Permit | Transmission Line - Right of Way | NA | NA | NA | Policy | Environmental | NA | NA | NA | 60 | NA | NA | NA | HFTD Tier 3 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 27 | NA | 69 | NA | 1.2 | NA | QS00342 | 1 | CNF MSUP | NA ¦ NA ¦ NA ¦ NA | TRUE | 2010-06-15 | Work Order Authorization | 2013 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | PTC | 2012-10-17 | Approved | 2016 | Operational | NA | NA | 2020-11-30 | NA | NA | NA | TRUE | 418776.5265 | NA ¦ NA | 3463.5098 | -23818.3585 | 4815.3305 | 479.0452 | 104.4224 | 13.5584 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 ¦ 2024 | -27.1906 | 2858.0988 | 479.0452 | 104.4224 | 13.5584 | 0 | 0 | NA ¦ NA | NA ¦ NA | NA | 0% | 100% | [Construction start date] and add this is the master special use permit. there is no construction associated with that.
322 | SED Future Rebuilds |  |  | NA | Placeholder for future Substation Projects | Substation - Multiple | Upgrade/Retrofit | NA | NA | Reliability | Substation Reliability | NA | NA | NA | NA | NA | NA | NA | Tier 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69 ¦500 | NA | 4.1 | NA | NA | 1 | TBDET002 | NA ¦ NA ¦ NA ¦ NA | TRUE | NA | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Planning | NA | NA | TBD | NA | NA | NA | FALSE | NA | NA ¦ NA | 119789.5616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1816.0704 | 8564.9406 | 22612.4344 | 17509.1825 | 0 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NA ¦ NA | NA ¦ NA | NA | 13.55% | 86.45% | [Utility Unique ID #2] There is no parent work order, it is a placeholder.

## Data-Fields
Category | Sorting Order | Data Field # | Transmission Project Data Field | Format | Example | Input Terms and Descriptions
Project Description | 1 | 1 | Row/Line No. | Number (whole number) | 4 | Row/line number in spreadsheet. Include separate project lines, as described and required in data fields 26-28, for all subparts, i.e., ID #1 of all FERC-jurisdictional electric transmission projects, including generator interconnection-related network upgrades: 1. the total cost of which At Unique ID #2 will at any point equal or exceed $1 million. In the event that there is no ID#2 to provide, the million-dollar threshold applies to ID #1. and 2. for which there were capital expenditures in the last five years OR for which any capital expenditures are anticipated in the current or next four years, regardless of the actual or anticipated operative date. Each project should have at least one Row/Line No. in this spreadsheet, as subparts of projects will require additional project lines.
Project Description | 2 | 2 | Project Name | Text String, separated by " ¦ " as necessary | Manzanita Substation | Include Project Name at date of report filing. Identify all prior names of the project and other names currently used in different venues, including the name as approved and included in the CAISO's TPP.
Project Description | 3 | 3a | Latitude | Number (decimal), separated by " ¦ " for multiple locations; NA if no geolocation | 20.234 ¦ 19.983 | Positive number indicates north of equator. Subject to redaction in the public data.
Project Description | 4 | 3b | Longitude | Number (decimal), separated by " ¦ " for multiple locations; NA if no geolocation | -132.018 ¦ -132.231 | Negative number indicates west of Prime Meridian. Subject to redaction in the public data.
Project Description | 5 | 4 | Location 2 | Text String, with comma separator between City and County. Multiple entries separated by " ¦ ". Order of values to be consistent with latitude and longitude values * City1, County1 ¦ City2, County2 | Berkeley, Alameda ¦ Concord, Contra Costa | All Cities and Counties included in the scope of the project.
Project Description | 6 | 5 | Project Description | Text String | This project will repair the transmission line connecting 4th and Townsend to the East Northfork station which failed as consequence of the 2019 San Clemente Hedge Fire. Assets to be replaced include... at ....kV. | General project overview: what, where, and why. Discuss all assets to be installed and include all capacities (MVA) and voltages (kV).
Project Description | 7 | 6 | Project Description - What | Select text from drop-down menu | Substation - Circuit Breaker | Transmission line (new, reconductor, relocation), substation (breaker, transformer relay protection), etc.
Project Description | 8 | 7 | Project Description - Action Taken (2) | Select text from drop-down menu(s) | Upgrade/Retrofit | See drop-down menu for options. If more than two options are required, select "Multiple Options" in second column and provide remaining responses, pipe-delimited, in "Notes" data field. If the primary or secondary purpose relates to complying with a NERC, WECC, or CAISO requirement, list the specific standard(s), requirement(s), and/or any contingencies that are being addressed.
Project Description | 9 | 7 | Project Description - Action Taken | Select text from drop-down menu(s) | Upgrade/Retrofit | See drop-down menu for options. If more than two options are required, select "Multiple Options" in second column and provide remaining responses, pipe-delimited, in "Notes" data field. If the primary or secondary purpose relates to complying with a NERC, WECC, or CAISO requirement, list the specific standard(s), requirement(s), and/or any contingencies that are being addressed.
Project Description | 10 | 8 | Project Dependencies | Number (whole) indicating required project or projects' Unique ID #(s), separated by " ¦ " as necessary | 235435 ¦ 432787 | Identify all other projects (Unique ID #1) in the spreadsheet that this project depends on and/or whose construction will be bundled with this project.
Project Description | 11 | 9 | Primary Purpose | Select text from drop-down menu | Reliability | May include, but not limited to: CAISO Transmission Planning Standards (NERC Compliance and contingency code, WECC Requirement (and the specific requirement)), Reliability, Load Growth, Local Capacity Requirement, Address Results of Power Flow Analysis, Address Results of Protection Studies, Physical Security, Policy, Economic, Generator Interconnection, Work Requested by Others, Age/End of Life, Wildfire Mitigation, Field Test Results, Emergency Event, Location, Environmental Conditions, Safety, Asset Condition, or Other. In the "Notes" data field, please explain a purpose identified as "Other" or provide additional details on the purpose identified.
Project Description | 12 | 10 | Secondary Purpose | Select text from drop-down menu | Age/Condition - Anti Climb Guards | May include, but not limited to: 3rd Party Damage, Age/Condition, Age/Condition - 230/115/70/60 kV Relay Replacement, Age/Condition - 500 kV Relay Replacement, Age/Condition - Anti Climb Guards, Age/Condition - Insulator Replacement - Steel, Age/Condition - Insulator Replacement - Wood, Age/Condition - Raptor Protection - Steel, Age/Condition - Replace 230/115/70/60 kV Breakers, Age/Condition - Replace 230/115/70/60 kV Transformers, Age/Condition - Replace 500 kV Breakers, Age/Condition - Replace 500 kV Transformers, Age/Condition - Replace Boardwalks, Age/Condition - Replace Breakers, Age/Condition - Replace Civil Structures, Age/Condition - Replace Conductor, Age/Condition - Replace Insulators, Age/Condition - Replace Other Substation Equipment, Age/Condition - Replace Other T-Line Equipment, Age/Condition - Replace Reactors, Age/Condition - Replace Relays, Age/Condition - Replace Relays, Age/Condition - Replace SCADA/RTU, Age/Condition - Replace Steel Poles, Age/Condition - Replace Switches, Age/Condition - Replace Transformers, Age/Condition - Replace Underground System, Age/Condition - Replace Wood Poles, Age/Condition - Switch Replacement - Steel, Age/Condition - Switch Replacement - Wood, Age/Condition - Targeted Relay Replacement, Age/Condition - Wood Pole Reframe, Animal Abatement, Automation, Bus Upgrade, Compliance - Remove Idle Facilities, Construct Roads/Gates/Culverts, Emergency Response - Fire Related, Emergency Response - Storm Related, Environmental, Facility Relocation, Fire Protection, Generation Interconnection, GO95 Mitigation - Steel, Install SCADA/RTU, Line Reconductoring, Line Termination, Load Interconnection, Modular Protection and Automation Control, NERC CIP Compliance, NERC Compliance - GO 95, New Substation, New T-Line, Priority 1 Steel Structure Replacement, Priority 1 Wood Structure Replacement, Protection NERC Compliance, Relay Upgrades, Replace Breakers, Replace Other Substation Equipment, Replace Transformers, Safety - Line Right of Way Access, SCADA Emergency Replacement, SCADA Switch Installation, Security Upgrades, Seismic Upgrade - Replace Conductor, Special Protection Scheme, Substation Capacity, Substation Reliability, System Design Upgrade, System Operations, Targeted Line Reliability, T-Line Capacity, T-Line Emergency, T-Line Reliability, Tools, Transformer Addition/Replacement, Underground Emergency, Voltage Conversion, Voltage Support. If the secondary purpose is to comply with a NERC, WECC, or CAISO requirement, list the standard, requirement, and/or any contingencies that are being addressed in the "Notes" data field.
Project Description | 13 | 11 | NERC / WECC / CAISO Standard / Requirement / Contingency | Select text from drop-down menu(s) | CIP-006 | See drop-down menu for options. If more than two options are required, select "Multiple Options" in second column and provide remaining responses, pipe-delimited, in "Notes" data field. If the primary or secondary purpose relates to complying with a NERC, WECC, or CAISO requirement, list the specific standard(s), requirement(s), and/or any contingencies that are being addressed in the "Notes" data field.
Project Description | 14 | 11 | NERC/WECC/CAISO Standard/Requirement/Contingency (2) | Select text from drop-down menu(s) | CIP-006 | See drop-down menu for options. If more than two options are required, select "Multiple Options" in second column and provide remaining responses, pipe-delimited, in "Notes" data field. If the primary or secondary purpose relates to complying with a NERC, WECC, or CAISO requirement, list the specific standard(s), requirement(s), and/or any contingencies that are being addressed in the "Notes" data field.
Project Description | 15 | 12 | Last Inspection | Date, formatted YYYY-MM-DD if text; NA if not yet inspected | 2019-12-10 | Specific date when the last inspection of the asset being repaired, replaced, or upgraded occurred.
Project Description | 16 | 13 | Age of Asset | Number (whole number) | 12 | Age in years from original in-service date of the asset being repaired, replaced, or upgraded.
Project Description | 17 | 14 | Types of Analyses | Select text from drop-down menu | Load Flow | Types of analyses that have been performed on the asset being repaired, replaced, or upgraded (e.g., load flow, short circuit, corrosion). List all field test and results that indicated the need for the project, and include inspector ID, when available in the "Notes" data field.
Project Description | 18 | 15a | Alternative Solutions and Costs - Solutions | Select text from drop-down menu(s) | Dynamic System Analysis | See drop-down menu for options. If more than two options are required, select "Multiple Options" in second column and provide remaining responses, pipe-delimited, in "Notes" data field. Include all alternative solutions to the project that were considered and the costs of all alternatives considered.
Project Description | 19 | 15b | Alternative Solutions and Costs - Costs | Select text from drop-down menu(s) | $5 Mil - $10 Mil | See drop-down menu for options. If more than two options are required, select "Multiple Options" in second column and provide remaining responses, pipe-delimited, in "Notes" data field. If multiple responses as included for the Sulutions and Costs fields, please provide costs in the same order as solutions.
Project Description | 20 | 16 | CPUC Fire Threat Zone/Rating | Text String, separated by " ¦ " as necessary, or NA | HFTD Tier 2 | Indicate whether the project is located in Tier1, Tier 2, or Tier 3 of CPUC's High Fire-Threat Districts (HFTD) or Zone 1 in CalFire/USFS High Hazard Zone (HHZ).
Project Description | 21 | 17 | Wildfire Related | Boolean, TRUE or FALSE, divided by " ¦ " | TRUE ¦ TRUE ¦ FALSE | Indicate whether the project is 1. related to repairing wildfire damage, 2. a measure identified in the Wildfire Mitigation Plan, or 3. is related to wildfire in some other way. If #3, please explain in the "Notes" data field.
Project Description | 22 | 18 | RAMP | Boolean, TRUE or FALSE | TRUE | Indicate whether the project is a proposed mitigation measure in the utility's Risk Assessment & Mitigation Phase (RAMP).
Project Description | 23 | 19 | Other Environmental Factors | Text String, or NA | Project exists in CA Building Climate Zone 3 which presents a high risk of accelerated oxidation or steel structures due to coastal humidity and salt exposure. | Environmental factors in the project's location that may affect the length of the asset's service life.
Project Description | 24 | 20 | Project Manager | Text String: Last, First | Doe, John | Person in charge of the implementation of this project for the Utility.
Project Description | 25 | 21 | Transmission Project Size (length in miles) | Number (decimal), or NA | 42.66 | Miles of transmission power lines included in the project.
Project Description | 26 | 22 | Substation Project Footprint (acres) | Number (decimal), or NA | 12.25 | Acres of substation footprint included in the project.
Project Description | 27 | 23 | Transmission Voltage Level (kV) | Number (whole), or NA | 230 | Use kV for transmission power lines ratings.
Project Description | 28 | 24 | Substation or Transformer Capacity (MVA and/or kV) | Text String, or NA if unrelated | 115kV | Use MVA and/or kV for substations.
Project Description | 29 | 25 | Utility Prioritization Ranking | Number (whole), in reference to ranking system identified in field name | 1 | Using the Utility's prioritization ranking. If multiple metrics are used to prioritize projects, please include a separate data subfield for each. (Sub-columns can be created to accommodate multiple or tiered ranking methodologies.)
Project Description | 30 | 26 | Work Order (Utility Unique ID #1) | Text String | 78493 | Most specific (PG&E = Planning Order, SCE = SCE ID, SDG&E = Project ID)
Project Description | 31 | 27 | Project ID (Utility Unique ID #2) | Text String | 432 | Less specific (PG&E = T.dot, SCE = Capital Work Breakdown Structure, SDG&E = Budget Code)
Project Description | 32 | 28 | Budget Code (Utility Unique ID #3) | Text String | 92 | Least specific (PG&E = Major Work Category, SCE = Project Identification Number , SDG&E = NA)
Project Description | 33 | 29 | Changes in Unique IDs | Date, formatted YYYY-MM-DD, and former identifiers: YYYY-MM-DD ¦ UID1 ¦ UID2 ¦ UID 3 If any components remain unchanged, use NA for those UIDs | 2022-05-05 ¦ NA ¦ NA ¦ 78322 | If any of the Unique IDs above changed at any time, please note the date of change and the former ID.
Utility/CAISO Approval and FERC Rate Cases | 34 | 30 | Utility Approval | Boolean: TRUE or FALSE | TRUE | "TRUE" if the Utility self-approved the project; "FALSE" if not.
Utility/CAISO Approval and FERC Rate Cases | 35 | 31 | Year of Internal Utility Approval | Date, formatted YYYY-MM-DD, or NA | 2022-01-02 | If utility has approved the project, insert first year of internal approval. If not insert "NA."
Utility/CAISO Approval and FERC Rate Cases | 36 | 32 | Process(es) for Utility Approval | Text String, or NA | Annual Capital Operating Plan Process | If utility has approved the project, insert utility approval process for which a description has been provided to the CPUC and Stakeholders.
Utility/CAISO Approval and FERC Rate Cases | 37 | 33 | Long term Transmission Investment Plan Inclusion | Year, formatted YYYY | 2022 | The year in which the project was first included in the utility's long-term transmission investment plan.
Utility/CAISO Approval and FERC Rate Cases | 38 | 34 | CAISO Year | Year, formatted YYYY, or NA | 2019 | Insert the year when approved by CAISO. If not a CAISO-approved project, insert "NA".
Utility/CAISO Approval and FERC Rate Cases | 39 | 35 | Transmission Planning Process ("TPP") Phase 3 | Boolean: TRUE or FALSE | FALSE | Please indicate with "TRUE" if any part of this project was subject to the competitive solicitation process in the TPP. In the "Notes" section briefly describe any portion of the project awarded to another developer and how it relates to the project in this Spreadsheet.
Utility/CAISO Approval and FERC Rate Cases | 40 | 36 | Year(s) when considered in CAISO TPP | Years, formatted YYYY and separated by " ¦ ", or NA | 2020 ¦ 2021 | Indicate years in which the project was considered in the TPP. If considered in year(s) prior to CAISO approval, please indicate all years.
Utility/CAISO Approval and FERC Rate Cases | 41 | 37 | Year when expected to be considered in CAISO TPP | Years, formatted YYYY and separated by " ¦ ", or NA | 2025 | If not yet considered in the CAISO TPP, indicate the year when it is expected to be considered in the CAISO TPP.
Utility/CAISO Approval and FERC Rate Cases | 42 | 38 | Link to TPP where project has been considered, approved, and/or expected to be considered | URL | http://www.caiso.com/Documents/BoardApproved-2017-2018_Transmission_Plan.pdf | Insert active hyperlink to any TPP where project was considered, including years in which the project was not approved.
Utility/CAISO Approval and FERC Rate Cases | 43 | 39 | Generator Interconnection and Deliverability Allocation Procedures (GIDAP) Related | Boolean: TRUE or FALSE | TRUE | Please indicate with TRUE or FALSE whether this transmission project is a transmission network upgrade related to generator interconnection(s).
CPUC Permit Status | 44 | 40a | CEQA Status | Select text from drop-down menu | Final Certified | See drop-down menu for options. Include one of the following: Expected PEA Completion, PEA Deemed Complete, CEQA Draft Published, CEQA Final Published, Final Certified, TBD, Other [See Notes], or NA.
CPUC Permit Status | 45 | 40b | CEQA Status - Date | Date, formatted YYYY-MM-DD, or NA | 2020-03-29 | Include the date that corresponds with the CEQA status.
CPUC Permit Status | 46 | 41a | CEQA Document Type | Select text from drop-down menu | EIR | Examples include: IS/ND, IS/MND, EIR, Exempted, Other, or NA (If "Other," include explanation in the "Notes" data field.).
CPUC Permit Status | 47 | 41b | NEPA Document Type | Select text from drop-down menu | EIS | Examples include: EIS, EA, Categorical Exclusion, Other, or NA (If "Other," include explanation in the "Notes" data field.).
CPUC Permit Status | 48 | 42a | CEQA Lead Agency | Text String, separated by " ¦ " as necessary, or NA | CPUC | Examples include: CPUC, SWRCB, CSLC, NA etc. If more than two options are required, enter each, pipe-delimited.
CPUC Permit Status | 49 | 42b | NEPA Lead Agency | Text String, separated by " ¦ " as necessary, or NA | USFS | Examples include: USFS, NA etc. If more than two options are required, enter each, pipe-delimited.
CPUC Permit Status | 50 | 43 | CPUC Filing Type | Text String, or NA | PG&E AL 2355-E | NOC Advice Letter (AL), Application for 851, PTC, CPCN, or NA. If an AL, include the number. If an Application, include number.
CPUC Permit Status | 51 | 44 | CPUC Date Filed | Date, formatted YYYY-MM-DD, or NA | 2022-04-08 | The year filed at the CPUC or insert "Not yet filed" with the expected filing date.
CPUC Permit Status | 52 | 45 | CPUC Status | Select text from drop-down menu | Approved | Indicate "Approved", "Rejected", "To be Filed", "Filed and Under Review," "Other," or "NA" (If "Other" or "NA", include explanation in the "Notes" data field.).
CPUC Permit Status | 53 | 46 | CPUC Status: Year | Year, formatted YYYY, or NA | 2019 | Insert the year this CPUC Status was determined.
Project status | 54 | 47 | Project Status | Select text from drop-down menu | Construction (10%-25%) | See drop-down menu for options. Examples include: Planning, Engineering less than 50% complete, Engineering more than 50% complete, Permitting, Construction (include percentage of construction completed at the time this data spreadsheet is provided (i.e., less than 10%, 10%-25%, 25%-50%, 50%-75%, greater than 75%), Operational, On Hold, Canceled, or Abandoned (if On Hold, Canceled, or Abandoned, include explanation in the "Notes" data field.).
Project status | 55 | 48 | AACE Class | Select text from drop-down menu | 3 | The current Estimate Class in AACE International's Cost Estimate Classification System at the time this data spreadsheet is provided.
Project status | 56 | 49 | Construction Start Date | Date, formatted YYYY-MM-DD, or NA | 45809 | The date on which construction began or is expected to begin.
Project status | 57 | 50 | Original Planned In- Service Date | Date, formatted YYYY-MM-DD, or NA* | 45809 | What was the expected in-service date when the project was first approved by the CAISO? If not a CAISO-approved project, provide the expected in-service date when the project was approved internally by the Utility.
Project status | 58 | 51 | Current Projected or Actual In-Service Date | Date, formatted YYYY-MM-DD, followed by OAI indicator if applicable (or NA) | 2021-01-01 ¦ NA 2021-01-01 ¦ OAI | At the time the data was extracted from the Utility’s Database(s) as provided in Section 2.1.5 of the Transmission Project Review Process Description. Projects without identified in-service dates that are "Operative as Installed" should be identified as "OAI".
Project status | 59 | 52 | Reason for Change in In- Service Date | Select text from drop-down menu(s) | Customer Action | See drop-down menu for options. If the current projected or actual in-service date varies more than six months from the original in-service date, please select all reasons for this change. If more than two options are required, select "Multiple Options" in second column and provide remaining responses, pipe-delimited, in "Notes" data field.
Project status | 60 | 52 | Reason for Change in In-Service Date (2) | Select text from drop-down menu(s) | Customer Action | See drop-down menu for options. If the current projected or actual in-service date varies more than six months from the original in-service date, please select all reasons for this change. If more than two options are required, select "Multiple Options" in second column and provide remaining responses, pipe-delimited, in "Notes" data field.
Project status | 61 | 53 | In-Flight Projects | Boolean: TRUE or FALSE | TRUE | For projects with costs expected to go into rate base in the current rate year or in the following rate year at FERC, please indicate with "TRUE." If there will be no additions to rate base in either year, indicate with "FALSE."
Costs | 62 | 54 | Original Projected Cost or Cost Range ($000) | Dollar value, or dollar value range, separated by " ¦ " | 2100 ¦ 2500 | Forecast cost or forecast cost range for Utility Unique ID #2, i.e., the totality of the project, at the earliest of CAISO, CPUC, or utility internal approval.
Costs | 63 | 55 | Cost Cap ($000) | Dollar value and Text String, separated by " ¦ ", or NA | 2500 ¦ CAISO TPP | Insert Cost Cap on project if available, as well as the authority imposing the cost cap. This shall include any maximum cost determined to be reasonable and prudent in a CPUC proceeding or a cost cap set for a competitively bid project in the CAISO's Transmission Planning Process.
Costs | 64 | 56 | Current Projected Total or Actual Final Cost ($000) | Dollar value | 78 | Updated projected fully-loaded total or actual fully loaded final cost of project. Projected total should be the anticipated sum of all capital expenditures, overhead,and AFUDC. Actual cost should be the total expenditures, overhead and AFUDC in the addition to rate base. Operational projects and all data must remain in this report for at least five (5) years after the last of the project's expenditures and capital additions.
Costs | 65 | 57 | 2019 Actual Capital Expenditures ($000) | Dollar value | 12 | Please include separate columns for each of the previous five (5) years and one for actual expenditures for the current year as of the date the data was extracted. If these expenditures do not include overheads and AFUDC, please provide those year-by-year.
Costs | 66 | 57 B | 2020 Actual Capital Expenditures ($000) | Dollar value | 12 | Please include separate columns for each of the previous five (5) years and one for actual expenditures for the current year as of the date the data was extracted. If these expenditures do not include overheads and AFUDC, please provide those year-by-year.
Costs | 67 | 57 C | 2021 Actual Capital Expenditures ($000) | Dollar value | 12 | Please include separate columns for each of the previous five (5) years and one for actual expenditures for the current year as of the date the data was extracted. If these expenditures do not include overheads and AFUDC, please provide those year-by-year.
Costs | 68 | 57 D | 2022 Actual Capital Expenditures ($000) | Dollar value | 12 | Please include separate columns for each of the previous five (5) years and one for actual expenditures for the current year as of the date the data was extracted. If these expenditures do not include overheads and AFUDC, please provide those year-by-year.
Costs | 69 | Internal | October 2023 YTD Actual Capital Expenditures ($000) | Dollar value | 12 | Please include separate columns for each of the previous five (5) years and one for actual expenditures for the current year as of the date the data was extracted. If these expenditures do not include overheads and AFUDC, please provide those year-by-year.
Costs | 70 | 58 | Nov & Dec 2023 Projected Capital Expenditures ($000) | Dollar value | 4650 | For the current year and four (4) future years, provide the year-by-year fully-loaded forecast capital expenditures for the project. Please include separate columns for each year. If these expenditures do not include overheads and AFUDC, please provide those year-by-year.
Costs | 71 | 58 B | 2024 Projected Capital Expenditures ($000) | Dollar value | 4650 | For the current year and four (4) future years, provide the year-by-year fully-loaded forecast capital expenditures for the project. Please include separate columns for each year. If these expenditures do not include overheads and AFUDC, please provide those year-by-year.
Costs | 72 | 58 C | 2025 Projected Capital Expenditures ($000) | Dollar value | 4650 | For the current year and four (4) future years, provide the year-by-year fully-loaded forecast capital expenditures for the project. Please include separate columns for each year. If these expenditures do not include overheads and AFUDC, please provide those year-by-year.
Costs | 73 | 58 D | 2026 Projected Capital Expenditures ($000) | Dollar value | 4650 | For the current year and four (4) future years, provide the year-by-year fully-loaded forecast capital expenditures for the project. Please include separate columns for each year. If these expenditures do not include overheads and AFUDC, please provide those year-by-year.
Costs | 74 | 58 E | 2027 Projected Capital Expenditures ($000) | Dollar value | 4650 | For the current year and four (4) future years, provide the year-by-year fully-loaded forecast capital expenditures for the project. Please include separate columns for each year. If these expenditures do not include overheads and AFUDC, please provide those year-by-year.
Costs | 75 | 58 F | 2028 Projected Capital Expenditures ($000) | Dollar value | 4650 | For the current year and four (4) future years, provide the year-by-year fully-loaded forecast capital expenditures for the project. Please include separate columns for each year. If these expenditures do not include overheads and AFUDC, please provide those year-by-year.
Costs | 76 | 59 | Construction Work in Progress Expenditures ($000) | Dollar value | 2350 | Total amount of money that has been spent so far for the project through the last calendar year.
Costs | 77 | 60 | Accrued Overhead | Dollar value | 12 | If the capital expenditures provided in Data Field #57 do not include Overhead, please provide the accrued Overhead through the last calendar year.
Costs | 78 | 61 | Accrued AFUDC | Dollar value | 0 | If the capital expenditures provided in Data Field #57 do not include AFUDC, please provide the accrued AFUDC through the last calendar year.
Costs | 79 | 62 | FERC: Year(s) | Years, separated by " ¦ ", or NA | 2023 ¦ 2024 ¦ 2025 ¦ 2026 ¦ 2027 | Insert ALL rate years when any costs of this project went - or are forecast to go - into FERC jurisdictional transmission rate base.
Costs | 80 | 63 | 2020 Actual FERC Dollars Ratebased ($000) | Dollar Value, per year column e.g., FERC_dollars_in_rate_base_2022 | 500000 | Insert the year(s) and actual dollars added to FERC jursidictional transmission rate base on the project for each of the four prior years and the present year. This should include additional costs added to rate base in years after operation first occurred.
Costs | 81 | 63 B | 2021 Actual FERC Dollars Ratebased ($000) | Dollar Value, per year column e.g., FERC_dollars_in_rate_base_2023 | 500000 | Insert the year(s) and actual dollars added to FERC jursidictional transmission rate base on the project for each of the four prior years and the present year. This should include additional costs added to rate base in years after operation first occurred.
Costs | 82 | 63 C | 2022 Actual FERC Dollars Ratebased ($000) | Dollar Value, per year column e.g., FERC_dollars_in_rate_base_2024 | 500000 | Insert the year(s) and actual dollars added to FERC jursidictional transmission rate base on the project for each of the four prior years and the present year. This should include additional costs added to rate base in years after operation first occurred.
Costs | 83 | 63 D | October 2023 YTD Actual FERC Dollars Ratebased ($000) | Dollar Value, per year column e.g., FERC_dollars_in_rate_base_2025 | 500000 | Insert the year(s) and actual dollars added to FERC jursidictional transmission rate base on the project for each of the four prior years and the present year. This should include additional costs added to rate base in years after operation first occurred.
Costs | 84 | 63 E | Nov & Dec 2023 Projected FERC Dollars Ratebased ($000) | Dollar Value, per year column e.g., FERC_dollars_in_rate_base_2026 | 500000 | Insert the year(s) and actual dollars added to FERC jursidictional transmission rate base on the project for each of the four prior years and the present year. This should include additional costs added to rate base in years after operation first occurred.
Costs | 85 | 63 F | 2024 Projected FERC Dollars Ratebased ($000) | Dollar Value, per year column e.g., FERC_dollars_in_rate_base_2027 | 500000 | Insert the year(s) and actual dollars added to FERC jursidictional transmission rate base on the project for each of the four prior years and the present year. This should include additional costs added to rate base in years after operation first occurred.
Costs | 86 | 64 | Percentage of Bid | Percentage to two decimals, and Text String, separated by " ¦ " | 33.33% ¦ "SuperPower LLC is developing a third of the project as part of its "TransValley Electrification" project. See http://.... | Percentage (or actual cost) of project implemented by outside developer, as opposed to the incumbent utility. If there is a project being developed by a non-incumbent utility that relates to this project, please indicate the name of the project as approved in the CAISO TPP.
Costs | 87 | 65 | Percentage of Work Requested by Others Passed onto Ratepayers | Percentage to two decimals and/or dollar value. If both, separate by " ¦ ". If either is not provided, please enter NA. | 25.00% ¦ 2300 35% ¦ NA NA ¦ 50000 | If the project is work requested by others or customer-driven, what percentage of the projects costs has been - or is expected to be - passed onto ratepayers? If the dollar amount being passed onto ratepayers is fixed, then this number can be expressed as a dollar amount.
Costs | 88 | 66 | Cost-Benefit Analysis | Percentage to two decimals, and ranking system identifier, separated by " ¦ " | 25.00% ¦ EnergyRank | The Cost-to-Benefit ratio. If the Utility's Cost-Benefit analysis related to its Risk-Based Decision-Making Framework (RDF) has not already been included in the "Utility Prioritization Ranking" data field above, please include it here.
Costs | 89 | 67 | FERC Incentives | Test Strings, separated by " ¦ ", or NA | Abandoned Plant ¦ CWIP | List any project-specific transmission incentives granted under any FERC Orders.
Costs | 90 | 68 | Percentage of Cost in High Voltage TAC | Percentage to two decimals | 0.2305 | Insert % of project cost recovered in the high-voltage TAC.
Costs | 91 | 69 | Percentage of Cost in Low Voltage TAC | Percentage to two decimals | 0 | Insert % of project cost recovered in the low-voltage TAC.
Notes | 92 | 70 | Notes | Strings, inclusive of field identifiers in brackets, separated by 3 linebreaks ("\n\n\n"), or NA [ID1] String1 [ID2] String2 | [CEQA/NEPA Document Type] Form STD762 [CPUC Status] Approved in part following bifurcation. Details indeterminate as of 5/6/2024. Expected update and clarification by 8/1/2024. | Any additionally requested information or other needed details about the project that were not otherwise covered.

## Options List
06. Project Description - What | 07. Project Description - Action taken | 09. Primary Purpose | 10. Secondary Purpose | 11. NERC/WECC/CAISO Standard/Requirement/Contingency | 14. Types of Analyses | 15a. Alternative Solutions and Costs - Solutions | 15b. Alternative Solutions and Costs - Costs | 40. CEQA Status | 41a. CEQA Document Type | 41b. NEPA Document Type | 45. CPUC Status | 47. Project Status | 48. AACE Class | 52. Reason for Change in In-Service Date | Complete
Substation - Multiple | New | CAISO Transmission Planning Standards [See Notes for NERC Compliance and contingency code, WECC Requirement (and the specific requirement)] | 3rd Party Damage | NERC CIP Compliance | Lifecycle Replacement Analysis | Wires - System Configuration Alternative | $0 Mil – $1 Mil | Expected PEA Completion | IS/ND | EIS | To be Filed | Planning | 1 | Weather | Yes
Substation - Other Equipment | Replace | Reliability | Age/Condition | NERC BAL Compliance | Steady State Power Flow System Analysis | Wires - Location/Route Alternative | $1 Mil - $2 Mil | PEA Deemed Complete | IS/MND | EA | Filed and Under Administrative Review | Engineering less than 50% complete | 2 | Permitting | No
Substation - Transformer | Upgrade/Retrofit | Load Growth | Age/Condition - 230/115/70/60 kV Relay Replacement | NERC FAC Compliance | Dynamic System Analysis | Wires - Reconductor/Line Rebuild Alternative | $2 Mil - $3 Mil | CEQA Draft Published | EIR | Categorical Exclusion | Administratively Complete and Under Technical Review | Engineering more than 50% complete | 3 | Clearances
Substation - Circuit Breaker | Relocate | Local Capacity Requirement | Age/Condition - 500 kV Relay Replacement | WECC Audit Findings | Short Circuit Duty Analysis | Wires - Replacement Alternative | $3 Mil -$5 Mil | CEQA Final Published | Exempted | Other [See Notes] | Approved | Permitting | 4 | Material
Substation - Line Termination | Removal | Address Results of Power Flow Analysis | Age/Condition - Anti Climb Guards | NERC PRC Compliance | Protection Studies | Wires - Minimum Required Scope (spot repair) Alternative | $5 Mil - $10 Mil | Final Certified | Other [See Notes] | NA | Rejected | Construction (under 10%) | 5 | Workforce
Substation - Voltage Support Equipment | NA | Address Results of Protection Studies | Age/Condition - Insulator Replacement - Steel | NERC TPL Standards | Interconnection System Impact/Facilities Studies | Wires - Voltage Support/Reactive Support Alternative | $10 Mil -$15 Mil | TBD | NA |  | Advice Letter Filed and In-Process | Construction (10%-25%) | NA | Prioritization
Substation - Bus Arrangement | Multiple Options [See Notes] | Physical Security | Age/Condition - Insulator Replacement - Wood | CAISO Requirement | Other [See Notes] | Wires - New Substation Alternative | $15 Mil - $20 Mil | Other [See Notes] |  |  | Other [See Notes] | Construction (25%-50%) |  | Bundling Dependencies
Substation - Switch |  | Policy | Age/Condition - Raptor Protection - Steel | Other [See Notes] | Multiple Options [See Notes] | Wires - Bus Upgrade Alternative | $20 Mil - $30 Mil | NA |  |  | NA [See Notes] | Construction (50%-75%) |  | Customer Action
Substation - Modular Protection and Automation Control Building |  | Economic | Age/Condition - Replace 230/115/70/60 kV Breakers | NA | NA | Wires - New T-Line Alternative | $30 Mil - $40 Mil |  |  |  |  | Construction (over 75%) |  | ISO Action
Substation - Protection Relay |  | Generator Interconnection | Age/Condition - Replace 230/115/70/60 kV Transformers | Multiple Options [See Notes] |  | Non-Wires - Large Scale Energy Alternative | $40 Mil - $50 Mil |  |  |  |  | Operational |  | Completed Early
Substation - Reactive Equipment |  | Work Requested by Others | Age/Condition - Replace 500 kV Breakers |  |  | Non-Wires - System DER Alternative | $50 Mil – $75 Mil |  |  |  |  | On Hold |  | Construction Delays
Substation - Structure |  | Age/End of Life | Age/Condition - Replace 500 kV Transformers |  |  | Other - Status Quo | $75 Mil – $100 Mil |  |  |  |  | Canceled |  | Outage
Other - IT |  | Wildfire Mitigation | Age/Condition - Replace Boardwalks |  |  | Other - Deferral | $100 Mil – $125 Mil |  |  |  |  | Abandoned |  | Project Design
Other - Physical Security |  | Field Test Results | Age/Condition - Replace Breakers |  |  | TBD | $125 Mil - $150 Mil | [6 empty] | Input Error
Other - Operations Tech |  | Emergency Event | Age/Condition - Replace Civil Structures |  |  | NA | $150 Mil - $175 Mil | [6 empty] | Vendor Quality/Delays
Other - Cybersecurity |  | Location, Environmental Conditions | Age/Condition - Replace Conductor |  |  |  | $175 Mil - $200 Mil | [6 empty] | Scope Change
Other - Remedial Action Scheme/Special Protection Scheme |  | Safety | Age/Condition - Replace Insulators |  |  |  | $200 Mil - $250 Mil | [6 empty] | Land Rights
Other |  | Asset Condition | Age/Condition - Replace Other Substation Equipment |  |  |  | $250 Mil – $300 Mil | [6 empty] | Other [See Notes]
Other - Environmental |  | Other [See Notes] | Age/Condition - Replace Other T-Line Equipment |  |  |  | $300 Mil - $350 Mil | [6 empty] | NA
Other - Civil |  |  | Age/Condition - Replace Reactors, Age/Condition - Replace Relays |  |  |  | $350 Mil – $400 Mil | [6 empty] | Multiple Options [See Notes]
Transmission Line/Substation |  |  | Age/Condition - Replace Relays |  |  |  | $400 Mil - $500 Mil
Transmission Line - Multiple |  |  | Age/Condition - Replace SCADA/RTU |  |  |  | Over $500 Mil
Transmission Line - Switch |  |  | Age/Condition - Replace Steel Poles |  |  |  | Multiple Options [See Notes]
Transmission Line - Underground |  |  | Age/Condition - Replace Switches, Age/Condition - Replace Transformers |  |  |  | NA
Transmission Line - Pole/Tower |  |  | Age/Condition - Replace Underground System
Transmission Line - Conductor |  |  | Age/Condition - Replace Wood Poles
Transmission Line - Other Equipment |  |  | Age/Condition - Switch Replacement - Steel
Transmission Line - Right of Way |  |  | Age/Condition - Switch Replacement - Wood
Multiple Options [See Notes] |  |  | Age/Condition - Targeted Relay Replacement
Age/Condition - Wood Pole Reframe
Animal Abatement
Automation
Bus Upgrade
Compliance - Remove Idle Facilities
Construct Roads/Gates/Culverts
Emergency Response - Fire Related
Emergency Response - Storm Related
Environmental
Facility Relocation
Fire Protection
Generation Interconnection
GO95 Mitigation - Steel
Install SCADA/RTU
Line Reconductoring
Line Termination
Load Interconnection
Modular Protection and Automation Control
NERC CIP Compliance
NERC Compliance - GO 95
New Substation
New T-Line
Priority 1 Steel Structure Replacement
Priority 1 Wood Structure Replacement
Protection NERC Compliance
Relay Upgrades
Replace Breakers
Replace Other Substation Equipment
Replace Transformer
Safety - Line Right of Way Access
SCADA Emergency Replacement
SCADA Switch Installation
Security Upgrades
Seismic Upgrade - Replace Conductor
Special Protection Scheme
Substation Capacity
Substation Reliability
System Design Upgrade
System Operations
Targeted Line Reliability
T-Line Capacity
T-Line Emergency
T-Line Reliability
Tools, Transformer Addition/Replacement
Underground Emergency
Voltage Conversion
Voltage Support