## Capital SRM
2024 RSAR 2023 GRC CYCLE CAPITAL COMPARISON FOR SAFETY, RELIABILITY AND MAINTENANCE WORK (a)(b) (THOUSANDS OF DOLLARS)
| A | B | C1 | C2 | C3 | C4 | C5 | C6 | C7 | D | E | F | G1 | G2 | G3 | H1 | H2 | H3 | I1 | I2 | J1 | J2 | K | L | M | N1 | N2 | N3 | O1 | O2 | O3 | P1 | P2 | Q 2024 | Q2 | R | S | T | U1 | U2 | U3 | V | W
Line No | Type (O&M Expense or Capital) | Functional Area | MWC | MWC Name | MAT | MAT Name | RAMP Risk Name | RAMP Mitigation and/or Control Name | 2023 GRC Testimony Reference | RAMP Roll-up (Yes/No) | Program/ Project Life (years) | Program/ Project Year | 2023 Imputed Adopted Costs | 2024 Imputed Adopted Costs | Imputed Costs for 2023 GRC Cycle to date($) (G1+G2) | 2023 Actual Costs | 2024 Actual Costs | Actual Costs for 2023 GRC Cycle to date($) (H1+H2) | Difference for 2024 ($) (H2-G2) | Difference for 2023 GRC Cycle to Date ($) (H3-G3) | Spending Percent Variance for 2024 (%) ((H-G)/G*100) | Spending Percent Variance for 2023 GRC Cycle (%) ((H3-G3)/G3*100) | Spending Variance Explanation Required (Y/N) | Percentage Variance Explanation Required (Y/N) | Unit Type | 2023 Imputed Adopted Units | 2024 Imputed Adopted Units | Imputed Units for 2023 GRC Cycle to Date (N2+N1) | 2023 Actual Units | 2024 Actual Units | Actual Units for 2023 GRC Cycle to Date (O2+O1) | Difference for 2024 (# of Units) (O2-N2) | Difference for 2023 GRC Cycle to Date (# of Units)​ (O3-N3) | Unit Percent Variance for 2024 (%) ((O2-N2)/N2*100) | Unit Percent Variance for 2023 GRC Cycle to Date (%)​ ((O3-N3)/N3) | Unit Variance Explanation Required (Y/N) | 2024 Cost Variance Explanation | 2024 Unit Variance Explanation | Forecast Scope (U, O, or T) | Schedule (U, O, or T) | Budget (U, O, or T) | Status | Completion Status Statement
1 | Capital | Gas Distribution | 14 | G Dist Pipeline Repl Program | 14A | Pipeline Repl Pgm-Mains & Svcs | SRM Total | SRM Total | Ex 3, Ch 4 | No | On-going | Annual | 102467.7272 | 103701.0957 | 206168.8229 | 97303.4542 | 108139.8325 | 205443.2867 | 4438.7368 | -725.5361 | 4.28% | -0.3519% | N | N | Feet of main | 128832 | 128832 | 257664 | 93523 | 112647 | 206170 | -16185 | -51494 | -12.56% | -19.98% | N | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | N/A
2 | Capital | Gas Distribution | 14 | G Dist Pipeline Repl Program | 14A | Pipeline Repl Pgm-Mains & Svcs | Loss of Containment on Gas Distribution Main or Service | LOCDM-M001 Pipeline Replacement Program (Steel) | Ex 3, Ch 4 | No | On-going | Annual | 102467.7272 | 103701.0957 | 206168.8229 | 97302.4542 | 108139.8325 | 205442.2867 | 4438.7368 | -726.5361 | 4.28% | -0.3524% | N/A | N/A | N/A | 128832 | 128832 | 257664 | 93523 | 112647 | 206170 | -16185 | -51494 | -12.56% | -19.98% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
3 | Capital | Gas Distribution | 14 | G Dist Pipeline Repl Program | 14B | Copper Service Replacements | SRM Total | SRM Total | Ex 3, Ch 4 | No | On-going | Annual | 0 | 0 | 0 | 758.817 | 208.5084 | 967.3254 | 208.5084 | 967.3254 | 100% | 100% | N | N | # of services replaced | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 2 | 0% | N/A | N | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
4 | Capital | Gas Distribution | 14 | G Dist Pipeline Repl Program | 14B | Copper Service Replacements | Loss of Containment on Gas Distribution Main or Service | LOCDM-M007 Copper Service Replacements | Ex 3, Ch 4 | No | On-going | Annual | 0 | 0 | 0 | 757.817 | 208.5084 | 966.3254 | 208.5084 | 966.3254 | 100% | 100% | N/A | N/A | N/A | 0 | - | N/A | 2 | 0 | 2 | N/A | N/A | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5 | Capital | Gas Distribution | 14 | G Dist Pipeline Repl Program | 14D | Plastic Pipe Replace_Main/Svc | SRM Total | SRM Total | Ex 3, Ch 4 | No | On-going | Annual | 407664.7895 | 412571.7092 | 820236.4987 | 372666.7336 | 398172.1975 | 770838.9311 | -14399.5117 | -49397.5676 | -3.49% | -6.022% | N | N | Feet of main | 733920 | 733920 | 1467840 | 444837 | 563665 | 1008502 | -170255 | -459338 | -23.2% | -31.29% | Y | N/A | Actual units were lower than imputed due to units target required a unit cost of $562/ft. Program was able to complete the 2024 portfolio with a unit cost of $706/ft. As such, we did not have sufficient funding to complete the imputed units. | Under | On-Target | Under | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to pre-1985 Aldyl-A and related plastic pipe.
6 | Capital | Gas Distribution | 14 | G Dist Pipeline Repl Program | 14D | Plastic Pipe Replace_Main/Svc | Loss of Containment on Gas Distribution Main or Service | LOCDM-M002 Pipeline Replacement Program (Plastic) | Ex 3, Ch 4 | No | On-going | Annual | 407664.7895 | 412571.7092 | 820236.4987 | 372665.7336 | 398172.1975 | 770837.9311 | -14399.5117 | -49398.5676 | -3.49% | -6.022% | N/A | N/A | N/A | 733920 | 733920 | 1467840 | 444837 | 563665 | 1008502 | -170255 | -459338 | -23.2% | -31.29% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
7 | Capital | Gas Distribution | 27 | Gas Meter Protection-Capital | 27A | Meter Protection-Capital | SRM Total | SRM Total | Ex 3, Ch 8 | Yes | On-going | Annual | 5475.6773 | 5541.6 | 11017.2773 | 245.4286 | 7031.8 | 7277.2286 | 1490.2 | -3740.0487 | 26.89% | -33.95% | N | N | # of service replacements | 7.36 | 184 | 191.36 | 3.56 | 2991 | 2994.56 | 2807 | 2803.2 | 1526% | 1465% | Y | N/A | Actual units were higher than imputed due to the reclassification of Meter Protection Post installations from Expense (MAT EXB) to Capital (MAT 27A). | Over | Over | On-Target | Expanded | MAT 27A now includes the installtion of Meter Protection Work (MPP), previously captured as expense with MAT EXB. Additionally, this MAT also captures costs related to full service relocations due to service meters at risk of vehicular damage not possible to protect via MPP, or unaccessible service valves.
8 | Capital | Gas Distribution | 27 | Gas Meter Protection-Capital | 27A | Meter Protection-Capital | Loss of Containment on Gas Customer Connected Equipment | CCEPQ-C001 Meter Protection | Ex 3, Ch 8 | Yes | On-going | Annual | 219.0271 | 221.7 | 440.7271 | 121.7143 | 281.272 | 402.9863 | 59.572 | -37.7408 | 26.87% | -8.563% | N/A | N/A | N/A | 7.36 | 184 | 191.36 | 3.56 | 2991 | 2994.56 | 2807 | 2803.2 | 1526% | 1465% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
9 | Capital | Gas Distribution | 27 | Gas Meter Protection-Capital | 27A | Meter Protection-Capital | Loss of Containment on Gas Distribution Main or Service | LOCDM-C001 Meter Protection | Ex 3, Ch 8 | Yes | On-going | Annual | 5256.6502 | 5319.9 | 10576.5502 | 123.7143 | 6750.528 | 6874.2423 | 1430.628 | -3702.3079 | 26.89% | -35% | N/A | N/A | N/A | 7.36 | 184 | 191.36 | 3.56 | 2991 | 2994.56 | 2807 | 2803.2 | 1526% | 1465% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
10 | Capital | Gas Distribution | 2K | G Dist Repl/Convert Cust HPR | 2K (a) | Cust HPR Reg Sta Convert Main | SRM Total | SRM Total | Ex 3, Ch 6 | No | On-going | Annual | 0 | 0 | 0 | 18630.5544 | 17329.1714 | 35959.7258 | 17329.1714 | 35959.7258 | 100% | 100% | N | Y | # of HPRs | 0 | 0 | 0 | 73 | 88 | 161 | 88 | 161 | 100% | N/A | Y | Actual costs were higher than imputed due to program having no adopted funding in the 2023 GRC. However, program was deemed important and continued to be performed by Gas Operations | Actual units were higher than imputed due to Program having no adopted funding in the 2023 GRC. However, program was deemed important and continued to be performed by Gas Operations | Over | On-Target | Over | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's GRC period. The purpose of this program is to replace or remove out of spec HPR reg sets to improve reliability and safety. This program will continue to be a lower priority as fewer units remain in the system.
11 | Capital | Gas Distribution | 2K | G Dist Repl/Convert Cust HPR | 2K (a) | Cust HPR Reg Sta Convert Main | 'Large Overpressure Event Downstream of Gas M&C Facility | LRGOP-M005 HPR Replacement | Ex 3, Ch 6 | No | On-going | Annual | 0 | 0 | 0 | 18630.5544 | 17329.1714 | 35959.7258 | 17329.1714 | 35959.7258 | 100% | 100% | N/A | N/A | N/A | 0 | 0 | 0 | 73 | 88 | 161 | 88 | 161 | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
12 | Capital | Gas Distribution | 2K | G Dist Repl/Convert Cust HPR | 2K (a) | Cust HPR Reg Sta Convert Main | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-M002 HPR Replacement | Ex 3, Ch 6 | No | On-going | Annual | 0 | 0 | 0 | 18630.5544 | 17329.1714 | 35959.7258 | 17329.1714 | 35959.7258 | 100% | 100% | N/A | N/A | N/A | 0 | 0 | 0 | 73 | 88 | 161 | 88 | 161 | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
13 | Capital | Gas Distribution | 31 | NGV - Station Infrastructure | 31A | 31A-LNG/CNG Stations | SRM Total | SRM Total | Ex 3, Ch 6 | No | On-going | Annual | 4889.4942 | 4948.3474 | 9837.8416 | 3490.6997 | 4512.0681 | 8002.7678 | -436.2793 | -1835.0739 | -8.817% | -18.65% | N | N | non-unitized: This MAT has no measurable units because it is used to record costs for CNG station upgrades. The type of upgrades performed at stations are not comparable. | NA | - | N/A | NA | - | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
14 | Capital | Gas Distribution | 31 | NGV - Station Infrastructure | 31A | 31A-LNG/CNG Stations | Loss of Containment on CNG Station Equipment | CNGEQ-C001 GV-Station Infrastructure | Ex 3, Ch 6 | No | On-going | Annual | 4889.4942 | 4948.3474 | 9837.8416 | 3489.6997 | 4512.0681 | 8001.7678 | -436.2793 | -1836.0739 | -8.817% | -18.66% | N/A | N/A | N/A | NA | - | N/A | NA | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
15 | Capital | Gas Distribution | 47 | G Dist Capacity | 47B | Cons/Acq New Fac-G-Cap-Mains | SRM Total | SRM Total | Ex 3, Ch 11 | No | On-going | Annual | 35760.9508 | 36191.393 | 71952.3438 | 20683.0323 | 8749.0644 | 29432.0967 | -27442.3286 | -42520.2471 | -75.83% | -59.1% | Y | Y | feet of main installed | 46200 | 46200 | 92400 | 11612 | 13621 | 25233 | -32579 | -67167 | -70.52% | -72.69% | Y | Actual costs were lower than imputed due to reprioritization of funds to higher risk work. | Actual Units were lower than imputed due to reprioritization of funds to higher risk work. | Under | On-Target | Under | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to ensure sufficient gas capacity as determined by system planning.
16 | Capital | Gas Distribution | 47 | G Dist Capacity | 47B | Cons/Acq New Fac-G-Cap-Mains | Insufficient Capacity to Meet Customer Demand | CPCTY-C009 Construct/Acquire New Facilities - Gas - Capital Mains | Ex 3, Ch 11 | No | On-going | Annual | 35760.9508 | 36191.393 | 71952.3438 | 20682.0323 | 8749.0644 | 29431.0967 | -27442.3286 | -42521.2471 | -75.83% | -59.1% | N/A | N/A | N/A | 46200 | 46200 | 92400 | 11612 | 13621 | 25233 | -32579 | -67167 | -70.52% | -72.69% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
17 | Capital | Gas Distribution | 47 | G Dist Capacity | 47C | Cons/Acq New Fac-G-Cap-RegSta | SRM Total | SRM Total | Ex 3, Ch 11 | No | On-going | Annual | 5881.9291 | 5952.7279 | 11834.657 | 923.8518 | 598.3589 | 1522.2107 | -5354.369 | -10312.4464 | -89.95% | -87.14% | N | N | # of reg stations addressed | 3 | 3 | 6 | 1 | 2 | 3 | -1 | -3 | -33.33% | -50% | Y | N/A | Actual units were lower than imputed units due to reprioritization in support of higher risk or compliance work. | Under | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to rebuild/replace capacity driven distribution regulator stations.
18 | Capital | Gas Distribution | 47 | G Dist Capacity | 47C | Cons/Acq New Fac-G-Cap-RegSta | Insufficient Capacity to Meet Customer Demand | CPCTY-C010 Construct/Acquire New Facilities - Gas Capital Regulator Sta | Ex 3, Ch 11 | No | On-going | Annual | 5881.9291 | 5952.7279 | 11834.657 | 922.8518 | 598.3589 | 1521.2107 | -5354.369 | -10313.4464 | -89.95% | -87.15% | N/A | N/A | N/A | 3 | 3 | 6 | 1 | 2 | 3 | -1 | -3 | -33.33% | -50% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
19 | Capital | Gas Distribution | 47 | G Dist Capacity | 47D | Cons/Acq New Fac-G-Cap-ReplReg | SRM Total | SRM Total | Ex 3, Ch 11 | No | On-going | Annual | 128.6485 | 130.197 | 258.8455 | 367.3599 | 249.66 | 617.0199 | 119.463 | 358.1744 | 91.76% | 138.4% | N | N | # of Reg station components | 4 | 4 | 8 | 6 | 0 | 6 | -4 | -2 | -100% | -25% | Y | N/A | Actual units were lower than imputed units due to a need for redesign on the one planned project, which includes all four units, causing adjusted completion forecast of 2025 for these 4 units. | Under | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to replace capacity driven valves/filters in distribution regulator stations.
20 | Capital | Gas Distribution | 47 | G Dist Capacity | 47D | Cons/Acq New Fac-G-Cap-ReplReg | Insufficient Capacity to Meet Customer Demand | CPCTY-C011 Construct/Acquire New Facilities - Gas Capital Replace Regul | Ex 3, Ch 11 | No | On-going | Annual | 128.6485 | 130.197 | 258.8455 | 366.3599 | 249.66 | 616.0199 | 119.463 | 357.1744 | 91.76% | 138% | N/A | N/A | N/A | 4 | 4 | 8 | 6 | 0 | 6 | -4 | -2 | -100% | -25% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
21 | Capital | Gas Distribution | 47 | G Dist Capacity | 47F | Cons/Acquire New Fac G-Cap-Oth | SRM Total | SRM Total | Ex 3, Ch 11 | No | On-going | Annual | 58.9754 | 59.6852 | 118.6606 | 9.0343 | 19.8113 | 28.8456 | -39.8739 | -89.815 | -66.81% | -75.69% | N | N | non-unitized: This MAT has no measurable units because it is used to record capacity related costs that are not captured by any other MAT. | NA | - | N/A | NA | - | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | N/A
22 | Capital | Gas Distribution | 47 | G Dist Capacity | 47F | Cons/Acquire New Fac G-Cap-Oth | Insufficient Capacity to Meet Customer Demand | CPCTY-C012 Construct/Acquire New Facilities - Gas Capital Other | Ex 3, Ch 11 | No | On-going | Annual | 58.9754 | 59.6852 | 118.6606 | 8.0343 | 19.8113 | 27.8456 | -39.8739 | -90.815 | -66.81% | -76.53% | N/A | N/A | N/A | NA | - | N/A | NA | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
23 | Capital | Gas Distribution | 4A | G Dist Ctrl Operations Assets | 4AF | ERX Pressure Monitoring-6 | SRM Total | SRM Total | Ex 3, Ch 11 | No | On-going | Annual | 530.5182 | 536.9039 | 1067.4221 | 376.7331 | 1462.4123 | 1839.1454 | 925.5085 | 771.7233 | 172.4% | 72.3% | N | N | # of Electronic pressure recorders installed | 10 | 10 | 20 | 0 | 7 | 7 | -3 | -13 | -30% | -65% | Y | N/A | Actual units were lower than imputed due to a reduction in total units because of high actual costs of completed projects. Costs at reg stations are much higher due to permits, easements and work required to complete projects. | Under | On-Target | On-Target | Proceeding as planned | This program is on going and will continue until no SCADA installations are required for system visability.
24 | Capital | Gas Distribution | 4A | G Dist Ctrl Operations Assets | 4AF | ERX Pressure Monitoring-6 | Insufficient Capacity to Meet Customer Demand | CPCTY-M005 SCADA Service Monitor | Ex 3, Ch 11 | No | On-going | Annual | 530.5182 | 536.9039 | 1067.4221 | 375.7331 | 1462.4123 | 1838.1454 | 925.5085 | 770.7233 | 172.4% | 72.2% | N/A | N/A | N/A | 10 | 10 | 20 | 0 | 7 | 7 | -3 | -13 | -30% | -65% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
25 | Capital | Gas Distribution | 4A | G Dist Ctrl Operations Assets | 4AF | ERX Pressure Monitoring-6 | Large Overpressure Event Downstream of Gas M&C Facility | LRGOP-M006 SCADA Service Monitor | Ex 3, Ch 11 | No | On-going | Annual | 530.5182 | 536.9039 | 1067.4221 | 377.7331 | 1462.4123 | 1840.1454 | 925.5085 | 772.7233 | 172.4% | 72.39% | N/A | N/A | N/A | 10 | 10 | 20 | 0 | 7 | 7 | -3 | -13 | -30% | -65% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
26 | Capital | Gas Distribution | 4A | G Dist Ctrl Operations Assets | 4AF | ERX Pressure Monitoring-6 | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-M005 SCADA Service Monitor | Ex 3, Ch 11 | No | On-going | Annual | 530.5182 | 536.9039 | 1067.4221 | 378.7331 | 1462.4123 | 1841.1454 | 925.5085 | 773.7233 | 172.4% | 72.49% | N/A | N/A | N/A | 10 | 10 | 20 | 0 | 7 | 7 | -3 | -13 | -30% | -65% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
27 | Capital | Gas Distribution | 4A | G Dist Ctrl Operations Assets | 4AM | Reg Stat Mntr Dual No Flow-3 | SRM Total | SRM Total | Ex 3, Ch 11 | No | On-going | Annual | 0 | 0 | 0 | 11317.3585 | 7298.991 | 18616.3496 | 7298.991 | 18616.3496 | 100% | 100% | N | N | # of remote terminal units installed | 0 | - | N/A | 27 | 34 | 61 | N/A | N/A | 100% | N/A | Y | N/A | Actual units were higher than imputed due to program having no adopted units in the 2023 GRC. However, program was deemed important and continued to be performed by Gas Operations. | Over | On-Target | On-Target | Proceeding as planned | This program is on going and will continue until no SCADA installations are required for system visability.
28 | Capital | Gas Distribution | 50 | G Dist Reliability General | 50F | Impr Rel/Dep Gas Other Equip | SRM Total | SRM Total | Ex 3, Ch 4 | No | On-going | Annual | 487.9761 | 493.8497 | 981.8258 | 1194.8606 | 1758.9183 | 2953.7788 | 1265.0686 | 1971.953 | 256.2% | 200.8% | N | N | non-unitized: This MAT has no measurable units because units of measure such as number of deactivated services, valves, and mains are not comparable. | NA | - | N/A | NA | - | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
29 | Capital | Gas Distribution | 50 | G Dist Reliability General | 50F | Impr Rel/Dep Gas Other Equip | Loss of Containment on Gas Distribution Main or Service | LOCDM-C005 Improve Reliability/Dependability - Gas Other Equipment | Ex 3, Ch 4 | No | On-going | Annual | 487.9761 | 493.8497 | 981.8258 | 1193.8606 | 1758.9183 | 2952.7788 | 1265.0686 | 1970.953 | 256.2% | 200.7% | N/A | N/A | N/A | NA | - | N/A | NA | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
30 | Capital | Gas Distribution | 50 | G Dist Reliability General | 50I | Impr Rel/Dep-Deac Only-M/R/V | SRM Total | SRM Total | Ex 3, Ch 4 | No | On-going | Annual | 8924.1659 | 9031.583 | 17955.7489 | 10240.5205 | 9219.5867 | 19460.1072 | 188.0037 | 1504.3583 | 2.082% | 8.378% | N | N | non-unitized: This MAT has no measurable units because units of measure such as number of deactivated services, valves, and mains are not comparable. | NA | - | N/A | NA | - | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
31 | Capital | Gas Distribution | 50 | G Dist Reliability General | 50I | Impr Rel/Dep-Deac Only-M/R/V | Loss of Containment on Gas Distribution Main or Service | LOCDM-C007 Improve ReM/R/V | Ex 3, Ch 4 | No | On-going | Annual | 8924.1659 | 9031.583 | 17955.7489 | 10239.5205 | 9219.5867 | 19459.1072 | 188.0037 | 1503.3583 | 2.082% | 8.373% | N/A | N/A | N/A | NA | - | N/A | NA | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
32 | Capital | Gas Distribution | 50 | G Dist Reliability General | 50N | GD Over Pressure Protection | SRM Total | SRM Total | Ex 3, Ch 6 | No | On-going | Annual | 0 | 0 | 0 | 10260.3774 | 6764.8005 | 17025.1779 | 6764.8005 | 17025.1779 | 100% | 100% | N | N | # of secondary OPP installed | 0 | - | N/A | 68 | 60 | 128 | N/A | N/A | 100% | N/A | Y | #N/A | Actual units were higher than imputed due to Program having no adopted funding in the 2023 GRC. However, program was deemed important and continued to be performed by Gas Operations. | Over | On-Target | On-Target | Proceeding as planned | THis program is ongoing to install over pressure protection at reg stations. Program wll continue until OPP is installed at all locations.
33 | Capital | Gas Distribution | 50 | G Dist Reliability General | 50N | GD Over Pressure Protection | Large Overpressure Event Downstream of Gas M&C Facility | LRGOP-M003 GD Overpressure Protection | Ex 3, Ch 6 | No | On-going | Annual | 0 | 0 | 0 | 10259.3774 | 6764.8005 | 17024.1779 | 6764.8005 | 17024.1779 | 100% | 100% | N/A | N/A | N/A | 0 | - | N/A | 68 | 60 | 128 | N/A | N/A | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
34 | Capital | Gas Distribution | 50 | G Dist Reliability General | 50B | Impr Rel/Dep - Gas Services | SRM Total | SRM Total | Ex 3, Ch 4 | No | On-going | Annual | 12094.9319 | 12240.5143 | 24335.4462 | 25006.9426 | 20884.4298 | 45891.3724 | 8643.9155 | 21555.9262 | 70.62% | 88.58% | N | N | # of services replaced | 427 | 427 | 854 | 608 | 571 | 1179 | 144 | 325 | 33.72% | 38.06% | Y | N/A | Actual units were higher than imputed due to significantly more service replacements executed under MAT 50B due to emergent other corrective and compliance work. This includes copper service replacements, shallow/exposed services, and other corrective gas service replacements. | Over | On-Target | Over | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to replace gas services due to deterioration or reduced reliability (including corrosion, copper services, exposed/shallow services). For the remainder of the GRC cycle, PG&E will prioritize compliance-driven service replacements due to atmospheric corrosion.
35 | Capital | Gas Distribution | 50 | G Dist Reliability General | 50B | Impr Rel/Dep - Gas Services | Loss of Containment on Gas Distribution Main or Service | LOCDM-C003 Improve Reliability/System Dependability - Gas Services | Ex 3, Ch 4 | No | On-going | Annual | 12094.9319 | 12240.5143 | 24335.4462 | 25005.9426 | 20884.4298 | 45890.3724 | 8643.9155 | 21554.9262 | 70.62% | 88.57% | N/A | N/A | N/A | 427 | 427 | 854 | 608 | 571 | 1179 | 144 | 325 | 33.72% | 38.06% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
36 | Capital | Gas Distribution | 50 | G Dist Reliability General | 50D | Impr Rel/Dep Gas CP Systems | SRM Total | SRM Total | Ex 3, Ch 9 | No | On-going | Annual | 1383.4625 | 1400.1148 | 2783.5773 | 1291.9819 | 1894.0557 | 3186.0376 | 493.9409 | 402.4603 | 35.28% | 14.46% | N | N | # of Rectifiers Replaced (50D) | 80 | 80 | 160 | 11 | 82 | 93 | 2 | -67 | 2.5% | -41.88% | N | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | Regarding the coating work in 50D - this program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to maintain and re-coat facilities that have observed corrosion or have deteriorated coating.
37 | Capital | Gas Distribution | 50 | G Dist Reliability General | 50D | Impr Rel/Dep Gas CP Systems | Loss of Containment on Gas Distribution Main or Service | LOCDM-C018 Distribution Corrosion Control Program | Ex 3, Ch 9 | No | On-going | Annual | 1383.4625 | 1400.1148 | 2783.5773 | 1290.9819 | 1894.0557 | 3185.0376 | 493.9409 | 401.4603 | 35.28% | 14.42% | N/A | N/A | N/A | 80 | 80 | 160 | 11 | 82 | 93 | 2 | -67 | 2.5% | -41.88% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
38 | Capital | Gas Distribution | 50 | G Dist Reliability General | 50H | Impr Rel/Dep-CutOff Idle G Svc | SRM Total | SRM Total | Ex 3, Ch 4 | No | On-going | Annual | 3160.9599 | 3199.0072 | 6359.9671 | 3925.998 | 5622.3895 | 9548.3875 | 2423.3823 | 3188.4204 | 75.75% | 50.13% | N | N | # of cut off idle services | 313 | 313 | 626 | 215 | 295 | 510 | -18 | -116 | -5.751% | -18.53% | N | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
39 | Capital | Gas Distribution | 50 | G Dist Reliability General | 50H | Impr Rel/Dep-CutOff Idle G Svc | Loss of Containment on Gas Distribution Main or Service | LOCDM-C006 Improve Reliability/System Dependability - Cut-Off Idle Gas | Ex 3, Ch 4 | No | On-going | Annual | 3160.9599 | 3199.0072 | 6359.9671 | 3924.998 | 5622.3895 | 9547.3875 | 2423.3823 | 3187.4204 | 75.75% | 50.12% | N/A | N/A | N/A | 313 | 313 | 626 | 215 | 295 | 510 | -18 | -116 | -5.751% | -18.53% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
40 | Capital | Gas Distribution | 50 | G Dist Reliability General | 50G/3PB (b) | Impr Rel/Dep-Gas Svc Repl Leak | SRM Total | SRM Total | Ex 3, Ch 10 | No | On-going | Annual | 14809.3646 | 14988 | 29797.3646 | 24303.9804 | 20037 | 44340.9803 | 5049 | 14543.6157 | 33.69% | 48.81% | N | N | # of services replaced (NERBA BG Grade 3 unit) | 978 | 978 | 1956 | 1036 | 877 | 1913 | -101 | -43 | -10.33% | -2.198% | N | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | N/A
41 | Capital | Gas Distribution | 50 | G Dist Reliability General | 50G/3PB (b) | Impr Rel/Dep-Gas Svc Repl Leak | Loss of Containment on Gas Distribution Main or Service | LOCDM-C014 Distribution Leak Management | Ex 3, Ch 10 | No | On-going | Annual | 14809.3646 | 14988 | 29797.3646 | 24302.9804 | 20037 | 44339.9803 | 5049 | 14542.6157 | 33.69% | 48.81% | N/A | N/A | N/A | 978 | 978 | 1956 | 1036 | 877 | 1913 | -101 | -43 | -10.33% | -2.198% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
42 | Capital | Gas Distribution | 50 | G Dist Reliability General | 50A | Impr Rel/ Dep - Gas Mains | SRM Total | SRM Total | Ex 3, Ch 4 | No | On-going | Annual | 52051.0914 | 52677.6123 | 104728.7037 | 47052.57 | 55122.2757 | 102174.8457 | 2444.6634 | -2553.858 | 4.641% | -2.439% | N | N | Feet of main | 79200 | 79200 | 158400 | 50495 | 65082 | 115577 | -14118 | -42823 | -17.83% | -27.03% | N | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | N/A
43 | Capital | Gas Distribution | 50 | G Dist Reliability General | 50A | Impr Rel/ Dep - Gas Mains | Loss of Containment on Gas Distribution Main or Service | LOCDM-C002 Improve Reliability/System Dependability - Gas Main | Ex 3, Ch 4 | No | On-going | Annual | 52051.0914 | 52677.6123 | 104728.7037 | 47051.57 | 55122.2757 | 102173.8457 | 2444.6634 | -2554.858 | 4.641% | -2.44% | N/A | N/A | N/A | 79200 | 79200 | 158400 | 50495 | 65082 | 115577 | -14118 | -42823 | -17.83% | -27.03% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
44 | Capital | Gas Distribution | 50 | G Dist Reliability General | 50R | Rep/Inst EmerShtdwn&SafeOpsVal | SRM Total | SRM Total | Ex 3, Ch 4 | No | On-going | Annual | 5775.7869 | 5845.308 | 11621.0948 | 3245.4239 | 7060.1728 | 10305.5967 | 1214.8648 | -1315.4982 | 20.78% | -11.32% | N | N | # of valves installed | 100 | 100 | 200 | 36 | 76 | 112 | -24 | -88 | -24% | -44% | Y | N/A | Actual units were lower than imputed units due to reprioritization in support of higher risk or compliance work. | Under | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to install new valves, 2 inch or greater in size.
45 | Capital | Gas Distribution | 50 | G Dist Reliability General | 50R | Rep/Inst EmerShtdwn&SafeOpsVal | Loss of Containment on Gas Distribution Main or Service | LOCDM-M004 New Valve Installations | Ex 3, Ch 4 | No | On-going | Annual | 5775.7869 | 5845.308 | 11621.0948 | 3244.4239 | 7060.1728 | 10304.5967 | 1214.8648 | -1316.4982 | 20.78% | -11.33% | N/A | N/A | N/A | 100 | 100 | 200 | 36 | 76 | 112 | -24 | -88 | -24% | -44% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
46 | Capital | Gas Distribution | 50 | G Dist Reliability General | 50P | ImprRelb/SysDepd-G-DpWellAnode | SRM Total | SRM Total | Ex 3, Ch 9 | No | On-going | Annual | 17989.1148 | 18205.6435 | 36194.7583 | 14506.1367 | 12898.4571 | 27404.5939 | -5307.1864 | -8790.1644 | -29.15% | -24.29% | N | N | # of Groundbeds Installed | 65 | 65 | 130 | 58 | 43 | 101 | -22 | -29 | -33.85% | -22.31% | Y | N/A | Actual units were lower than imputed units due to lower planned units and the delayed construction activities to claim the unit in the year. | Under | On-Target | On-Target | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The purpose of this program is to install impressed current ground bed to mitigate the threat of external corrosion (49 CFR Subpart I, Requirement for Corrosion Control).
47 | Capital | Gas Distribution | 50 | G Dist Reliability General | 50P | ImprRelb/SysDepd-G-DpWellAnode | Loss of Containment on Gas Distribution Main or Service | LOCDM-C018 Distribution Corrosion Control Program | Ex 3, Ch 9 | No | On-going | Annual | 17989.1148 | 18205.6435 | 36194.7583 | 14505.1367 | 12898.4571 | 27403.5939 | -5307.1864 | -8791.1644 | -29.15% | -24.29% | N/A | N/A | N/A | 65 | 65 | 130 | 58 | 43 | 101 | -22 | -29 | -33.85% | -22.31% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
48 | Capital | Gas Distribution | 50 | G Dist Reliability General | 50K | Emergent Leaking Main Replace | SRM Total | SRM Total | Ex 3, Ch 10 | No | On-going | Annual | 5757.345 | 5826.6442 | 11583.9892 | 2558.077 | 4941.2833 | 7499.3603 | -885.3609 | -4084.6289 | -15.2% | -35.26% | N | N | feet of main installed | 7707 | 7707 | 15414 | 1947 | 4907 | 6854 | -2800 | -8560 | -36.33% | -55.53% | Y | N/A | Actual units lower than imputted due to decreased leak find rates in the last three years resulting in reduced leaks qualifying for main pipe replacements > 100' | Under | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to fix gradeable leaks by replacing >100' of main distribution pipeline.
49 | Capital | Gas Distribution | 50 | G Dist Reliability General | 50K | Emergent Leaking Main Replace | Loss of Containment on Gas Distribution Main or Service | LOCDM-C014 Distribution Leak Management | Ex 3, Ch 10 | No | On-going | Annual | 5757.345 | 5826.6442 | 11583.9892 | 2557.077 | 4941.2833 | 7498.3603 | -885.3609 | -4085.6289 | -15.2% | -35.27% | N/A | N/A | N/A | 7707 | 7707 | 15414 | 1947 | 4907 | 6854 | -2800 | -8560 | -36.33% | -55.53% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
50 | Capital | Gas Distribution | 50 | G Dist Reliability General | 50J | Gas Overbuild - G | SRM Total | SRM Total | Ex 3, Ch 4 | No | On-going | Annual | 16738.3637 | 16939.8376 | 33678.2013 | 21050.6232 | 16515.05 | 37565.6733 | -424.7875 | 3887.472 | -2.508% | 11.54% | N | N | # of services replaced | 578 | 578 | 1156 | 462 | 348 | 810 | -230 | -346 | -39.79% | -29.93% | Y | N/A | Actual units were less than imputed due to the Encroachment program is based on find-it-fix-it work that needs to be field verified to determine capital or expense scope. Less work was field verified as capital encroachments (full service replacement and/or greater than 100' of main relocation based on overbuilt gas pipe) than imputed. | Under | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to relocate gas main (>100 continuous feet) and/or complete gas service replacements to clear overbuild conflicts. For the remainder of the GRC cycle, PG&E will prioritize this work and execute within six months of identification (subject to extension with notification to regulators).
51 | Capital | Gas Distribution | 50 | G Dist Reliability General | 50J | Gas Overbuild - G | Loss of Containment on Gas Distribution Main or Service | LOCDM-C009 Encroachment Program | Ex 3, Ch 4 | No | On-going | Annual | 16738.3637 | 16939.8376 | 33678.2013 | 21049.6232 | 16515.05 | 37564.6733 | -424.7875 | 3886.472 | -2.508% | 11.54% | N/A | N/A | N/A | 578 | 578 | 1156 | 462 | 348 | 810 | -230 | -346 | -39.79% | -29.93% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
52 | Capital | Gas Distribution | 50 | G Dist Reliability General | 50E | Impr Rel/Dep Gas Valves | SRM Total | SRM Total | Ex 3, Ch 4 | No | On-going | Annual | 5775.7869 | 5845.308 | 11621.0948 | 10230.83 | 4916.8981 | 15147.7281 | -928.4099 | 3526.6333 | -15.88% | 30.35% | N | N | # of valves replaced | 100 | 100 | 200 | 74 | 58 | 132 | -42 | -68 | -42% | -34% | Y | N/A | Actual units were lower than imputed units as PG&E performed fewer find-it/fix-it valve replacements than expected. This is because the find rate was lower compared to previous years. | Under | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to replace the existing valves, 2 inch or greater in size.
53 | Capital | Gas Distribution | 50 | G Dist Reliability General | 50E | Impr Rel/Dep Gas Valves | Loss of Containment on Gas Distribution Main or Service | LOCDM-C004 Improve Reliability/Dependability - Gas Valves | Ex 3, Ch 4 | No | On-going | Annual | 5775.7869 | 5845.308 | 11621.0948 | 10229.83 | 4916.8981 | 15146.7281 | -928.4099 | 3525.6333 | -15.88% | 30.34% | N/A | N/A | N/A | 100 | 100 | 200 | 74 | 58 | 132 | -42 | -68 | -42% | -34% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
54 | Capital | Gas Distribution | 50 | G Dist Reliability General | 50L | Impr Rel Dep Gas Reg Component | SRM Total | SRM Total | Ex 3, Ch 6 | No | On-going | Annual | 10669.2951 | 10797.7177 | 21467.0127 | 13724.2722 | 11002.8427 | 24727.1149 | 205.1251 | 3260.1021 | 1.9% | 15.19% | N | N | # of Reg station components | 150 | 150 | 300 | 130 | 85 | 215 | -65 | -85 | -43.33% | -28.33% | Y | N/A | Actual units were lower than imputed units because unit costs were higher than expected (for example, some projects could only be completed at night, with higher labor costs). | Under | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to replace valves and filters in distribution regulator stations.
55 | Capital | Gas Distribution | 50 | G Dist Reliability General | 50L | Impr Rel Dep Gas Reg Component | Large Overpressure Event Downstream of Gas M&C Facility | LRGOP-C009 Gas Distribution Reg Station Component Replacements | Ex 3, Ch 6 | No | On-going | Annual | 10669.2951 | 10797.7177 | 21467.0127 | 13723.2722 | 11002.8427 | 24726.1149 | 205.1251 | 3259.1021 | 1.9% | 15.18% | N/A | N/A | N/A | 150 | 150 | 300 | 130 | 85 | 215 | -65 | -85 | -43.33% | -28.33% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
56 | Capital | Gas Distribution | 50 | G Dist Reliability General | 50L | Impr Rel Dep Gas Reg Component | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C010 Gas Distribution Reg Station Component Replacements | Ex 3, Ch 6 | No | On-going | Annual | 10669.2951 | 10797.7177 | 21467.0127 | 13725.2722 | 11002.8427 | 24728.1149 | 205.1251 | 3261.1021 | 1.9% | 15.19% | N/A | N/A | N/A | 150 | 150 | 300 | 130 | 85 | 215 | -65 | -85 | -43.33% | -28.33% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
57 | Capital | Gas Distribution | 50 | G Dist Reliability General | 50C | Impr Rel/Dep Gas Regulation | SRM Total | SRM Total | Ex 3, Ch 6 | No | On-going | Annual | 49887.2427 | 50487.7181 | 100374.9609 | 45584.3776 | 36695.0629 | 82279.4405 | -13792.6552 | -18095.5204 | -27.32% | -18.03% | N | Y | # of Reg stations | 25 | 25 | 50 | 16 | 14 | 30 | -11 | -20 | -44% | -40% | Y | Actual costs were lower than imputed costs due to reprioritization in support of higher risk or compliance work. (Unit costs were higher due increased costs of construction and scope of work in 2024 projects) | Actual units were lower than imputed units due to reprioritization in support of higher risk or compliance work.(Unit costs were higher due increased costs of construction and scope of work in 2024 projects) | Under | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to rebuild/replace distribution regulator stations.
58 | Capital | Gas Distribution | 50 | G Dist Reliability General | 50C | Impr Rel/Dep Gas Regulation | Large Overpressure Event Downstream of Gas M&C Facility | LRGOP-C008 Gas Distribution Reg Station Rebuild | Ex 3, Ch 6 | No | On-going | Annual | 49887.2427 | 50487.7181 | 100374.9609 | 45583.3776 | 36695.0629 | 82278.4405 | -13792.6552 | -18096.5204 | -27.32% | -18.03% | N/A | N/A | N/A | 25 | 25 | 50 | 16 | 14 | 30 | -11 | -20 | -44% | -40% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
59 | Capital | Gas Distribution | 50 | G Dist Reliability General | 50C | Impr Rel/Dep Gas Regulation | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C009 Gas Distribution Reg Station Rebuild | Ex 3, Ch 6 | No | On-going | Annual | 49887.2427 | 50487.7181 | 100374.9609 | 45585.3776 | 36695.0629 | 82280.4405 | -13792.6552 | -18094.5204 | -27.32% | -18.03% | N/A | N/A | N/A | 25 | 25 | 50 | 16 | 14 | 30 | -11 | -20 | -44% | -40% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
60 | Capital | Gas Distribution | 50 | G Dist Reliability General | 50Q | Casings | SRM Total | SRM Total | Ex 3, Ch 9 | No | On-going | Annual | 2698.4499 | 2730.9302 | 5429.3801 | 3138.0424 | 2483.6831 | 5621.7254 | -247.2472 | 192.3453 | -9.054% | 3.543% | N | N | # of Casings Remediated (50Q) | 10 | 10 | 20 | 8 | 5 | 13 | -5 | -7 | -50% | -35% | Y | N/A | Actual units were lower than imputed units due to: 1) cancellation of jobs (found isolated during testing), 2) permitting delays and challenges with external agencies 3) Scope change (converted to expense) | Under | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. This program is to mitigate casings over or equal to 40 feet to meet the requirement of 49 CFR § 192.467 External corrosion control.
61 | Capital | Gas Distribution | 50 | G Dist Reliability General | 50Q | Casings | Loss of Containment on Gas Distribution Main or Service | LOCDM-C019 Casings | Ex 3, Ch 9 | No | On-going | Annual | 2698.4499 | 2730.9302 | 5429.3801 | 3137.0424 | 2483.6831 | 5620.7254 | -247.2472 | 191.3453 | -9.054% | 3.524% | N/A | N/A | N/A | 10 | 10 | 20 | 8 | 5 | 13 | -5 | -7 | -50% | -35% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
62 | Capital | Gas Distribution | 50 | G Dist Reliability General | 50M/ 3PC (b) | Complex-Gas Svc Repl Leak | SRM Total | SRM Total | Ex 3, Ch 10 | No | On-going | Annual | 1125.0113 | 1139 | 2264.0113 | 1718.262 | 989 | 2707.262 | -150 | 443.2508 | -13.17% | 19.58% | N | N | # of services (NERBA BG Grade 3 unit) | 63 | 63 | 126 | 40 | 24 | 64 | -39 | -62 | -61.9% | -49.21% | Y | N/A | Actual units lower than imputed due to lower leak find rates than planned resulting in a decrease of leaks repaired via complex service replacement | Under | On-Target | On-Target | Proceeding as planned | N/A
63 | Capital | Gas Distribution | 50 | G Dist Reliability General | 50M/ 3PC (b) | Complex-Gas Svc Repl Leak | Loss of Containment on Gas Distribution Main or Service | LOCDM-C014 Distribution Leak Management | Ex 3, Ch 10 | No | On-going | Annual | 1125.0113 | 1139 | 2264.0113 | 1717.262 | 989 | 2706.262 | -150 | 442.2508 | -13.17% | 19.53% | N/A | N/A | N/A | 63 | 63 | 126 | 40 | 24 | 64 | -39 | -62 | -61.9% | -49.21% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
64 | Capital | Gas Distribution | 52 | G Dist Leak Repl/Emergency | 52# | Not assigned | SRM Total | SRM Total | Ex 3, Ch 10 | No | On-going | Annual | 0 | 0 | 0 | 82 | 0 | 82 | 0 | 82 | 0% | 100% | N | N | non-unitized: This MAT has no measurable units because it is used to record other support costs for third party damage service repair | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A | N/A | N/A | N/A | N/A | N/A | N/A
65 | Capital | Gas Distribution | 52 | G Dist Leak Repl/Emergency | 52B | Emerg Resp-G-Dig-Ins-Svcs | SRM Total | SRM Total | Ex 3, Ch 10 | No | On-going | Annual | 1343.9403 | 1360.1168 | 2704.0571 | 2856.3368 | 2194.0595 | 5050.3962 | 833.9426 | 2346.3391 | 61.31% | 86.77% | N | N | # of services replaced | 178 | 178 | 356 | 151 | 128 | 279 | -50 | -77 | -28.09% | -21.63% | Y | N/A | Actual units were lower than imputed due to reduced number of emergencies and 3rd party damages reported that required full service replacement or deactivation. | Under | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to fix distribution service damages caused by natural forces and 3rd parties. This MAT includes the replacement and deactivation of entire services.
66 | Capital | Gas Distribution | 52 | G Dist Leak Repl/Emergency | 52B | Emerg Resp-G-Dig-Ins-Svcs | Loss of Containment on Gas Distribution Main or Service | LOCDM-C014 Distribution Leak Management | Ex 3, Ch 10 | No | On-going | Annual | 1343.9403 | 1360.1168 | 2704.0571 | 2855.3368 | 2194.0595 | 5049.3962 | 833.9426 | 2345.3391 | 61.31% | 86.73% | N/A | N/A | N/A | 178 | 178 | 356 | 151 | 128 | 279 | -50 | -77 | -28.09% | -21.63% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
67 | Capital | Gas Distribution | 52 | G Dist Leak Repl/Emergency | 52C | Emerg Resp-G-Dig-Ins-Main | SRM Total | SRM Total | Ex 3, Ch 10 | No | On-going | Annual | 296.5481 | 300.1175 | 596.6656 | 1711.2389 | 58.6897 | 1769.9287 | -241.4278 | 1173.263 | -80.44% | 196.6% | N | N | feet of main replaced | 1122 | 1122 | 2244 | 1288 | 262.1 | 1550.1 | -859.9 | -693.9 | -76.64% | -30.92% | Y | N/A | Actual units were lower than imputed units due to reduced number of emergencies and 3rd party damages reported that required main deactivation or the replacement of >100 ft of main pipe. | Under | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to fix distribution main pipeline damages caused by natural forces and 3rd parties. This MAT includes the repalcement of > 100' of pipe or pipe deactivation.
68 | Capital | Gas Distribution | 52 | G Dist Leak Repl/Emergency | 52C | Emerg Resp-G-Dig-Ins-Main | Loss of Containment on Gas Distribution Main or Service | LOCDM-C014 Distribution Leak Management | Ex 3, Ch 10 | No | On-going | Annual | 296.5481 | 300.1175 | 596.6656 | 1710.2389 | 58.6897 | 1768.9287 | -241.4278 | 1172.263 | -80.44% | 196.5% | N/A | N/A | N/A | 1122 | 1122 | 2244 | 1288 | 262.1 | 1550.1 | -859.9 | -693.9 | -76.64% | -30.92% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
69 | Capital | Gas Distribution | 74 | Install New Gas Meters | 74A | Install Regulators | SRM Total | SRM Total | Ex 3, Ch 8 | No | On-going | Annual | 2257.3937 | 2284.5652 | 4541.9589 | 10297.827 | 8882.9085 | 19180.7355 | 6598.3433 | 14638.7765 | 288.8% | 322.3% | N | N | # of regulators | 6833 | 6833 | 13666 | 28283 | 25263 | 53546 | 18430 | 39880 | 269.7% | 291.8% | Y | N/A | Actual units were higher than imputed units due to a change in reporting practice which resulted in more regulator replacement units being captured in this MAT. Historically, regulator changes completed while in the field performing other gas field services work was captured in the MAT that drove the initial job. | Over | On-Target | On-Target | Proceeding as Planned | Ongoing and will continue in PG&E's 2023 GRC period
70 | Capital | Gas Distribution | 74 | Install New Gas Meters | 74A | Install Regulators | Loss of Containment on Gas Customer Connected Equipment | CCEPQ-C016 Gas Reg Replacement | Ex 3, Ch 8 | No | On-going | Annual | 2257.3937 | 2284.5652 | 4541.9589 | 10296.827 | 8882.9085 | 19179.7355 | 6598.3433 | 14637.7765 | 288.8% | 322.3% | N/A | N/A | N/A | 6833 | 6833 | 13666 | 28283 | 25263 | 53546 | 18430 | 39880 | 269.7% | 291.8% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
71 | Capital | GT&S | 21 | Misc Capital | 21C | GPOM Non-Engineering Capital | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | N/A | No | On-going | Annual | 0 | 0 | 0 | 1373.1321 | 696.0272 | 2069.1593 | 696.0272 | 2069.1593 | 100% | 100% | N | N | non-unitized: This MAT has no measurable units because it encompasses a variety of different activities – it is used to capture GPOM non-engineering capital routine transmission spend. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | N/A
72 | Capital | GT&S | 3K | Gas Trans Remediate Corrosion | 3K1 | Drip Replacement | SRM Total | SRM Total | Ex 3, Ch 9 | No | On-going | Annual | 14161.4891 | 13753.7138 | 27915.2029 | 2622.5309 | 290.789 | 2913.3199 | -13462.9248 | -25001.883 | -97.89% | -89.56% | Y | Y | # of drips replaced | 5 | 5 | 10 | 5 | 4 | 9 | -1 | -1 | -20% | -10% | YES | Actual costs were lower than imputed due to work bundling with projects near a drip resulting in a lower unit cost and work cancellation due to transmission definition change in 2024. | Actual units were lower than imputed units due to the cancellation of bundled drip removal units. Bundled drip removals are executed opportunistically as part of pipeline replacement, strength test or retirement projects, but the planned projects were cancelled due to the TransDef change on the pipelines to which they are installed. | Under | On-Target | Under | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to mitigate Internal Corrosion as required by 49 CFR § 192.475.
73 | Capital | GT&S | 3K | Gas Trans Remediate Corrosion | 3K1 | Drip Replacement | Loss of Containment on Gas Transmission Pipeline | LOCTM-C032 Internal Corrosion Program | Ex 3, Ch 9 | No | On-going | Annual | 14161.4891 | 13753.7138 | 27915.2029 | 2622.5309 | 290.789 | 2913.3199 | -13462.9248 | -25001.883 | -97.89% | -89.56% | N/A | N/A | N/A | 5 | 5 | 10 | 5 | 4 | 9 | -1 | -1 | -20% | -10% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
74 | Capital | GT&S | 3K | Gas Trans Remediate Corrosion | 3K1 | Drip Replacement | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C017 Facility Corrosion Control Program | Ex 3, Ch 9 | No | On-going | Annual | 14161.4891 | 13753.7138 | 27915.2029 | 2622.5309 | 290.789 | 2913.3199 | -13462.9248 | -25001.883 | -97.89% | -89.56% | N/A | N/A | N/A | 5 | 5 | 10 | 5 | 4 | 9 | -1 | -1 | -20% | -10% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
75 | Capital | GT&S | 3K | Gas Trans Remediate Corrosion | 3K4 | AC Interf Mitigation | SRM Total | SRM Total | Ex 3, Ch 9 | No | On-going | Annual | 3276.5505 | 3171.2 | 6447.7505 | 3813.16 | 5831.2941 | 9644.4541 | 2660.0941 | 3196.7036 | 83.88% | 49.58% | N | N | Various | 14 | 14 | 28 | 9.41 | 33 | 42.41 | 19 | 14.41 | 135.7% | 51.46% | YES | N/A | Actual units were higher than imputed units due to the new timeline requirement in Mega Rule Part 2 to mitigate AC Interference within 12-15 months after the idenfitication of AC Interference starting from 2024. | Over | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to mitigate AC Interference as required by 49 CFR § 192.467 and 473.
76 | Capital | GT&S | 3K | Gas Trans Remediate Corrosion | 3K4 | AC Interf Mitigation | Loss of Containment on Gas Transmission Pipeline | LOCTM-C033 Electrical Interference Program | Ex 3, Ch 9 | No | On-going | Annual | 3276.5505 | 3171.2 | 6447.7505 | 3813.16 | 5831.2941 | 9644.4541 | 2660.0941 | 3196.7036 | 83.88% | 49.58% | N/A | N/A | N/A | 14 | 14 | 28 | 9.41 | 33 | 42.41 | 19 | 14.41 | 135.7% | 51.46% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
77 | Capital | GT&S | 3K | Gas Trans Remediate Corrosion | 3K5 | Casing Mitigation | SRM Total | SRM Total | Ex 3, Ch 9 | No | On-going | Annual | 14765.6005 | 14294.3 | 29059.9005 | 12540.6064 | 8657.2865 | 21197.893 | -5637.0135 | -7862.0076 | -39.44% | -27.05% | N | N | Various | 11 | 11 | 22 | 14 | 2 | 16 | -9 | -6 | -81.82% | -27.27% | YES | N/A | Actual units were lower than imputed units due to the postponement of project execution to future years. | Under | On-Target | On-Target | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The purpose of this program is to mitigate contacted casing to ensure each buried or submerged pipeline being electrically isolated from the metallic casing it is within (49 CFR § 192.467).
78 | Capital | GT&S | 3K | Gas Trans Remediate Corrosion | 3K5 | Casing Mitigation | Loss of Containment on Gas Transmission Pipeline | LOCTM-C035 Transmission Corrosion Control Program | Ex 3, Ch 9 | No | On-going | Annual | 14765.6005 | 14294.3 | 29059.9005 | 12540.6064 | 8657.2865 | 21197.893 | -5637.0135 | -7862.0076 | -39.44% | -27.05% | N/A | N/A | N/A | 11 | 11 | 22 | 14 | 2 | 16 | -9 | -6 | -81.82% | -27.27% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
79 | Capital | GT&S | 3K | Gas Trans Remediate Corrosion | 3K6 | Cathodic Protection-New | SRM Total | SRM Total | Ex 3, Ch 9 | No | On-going | Annual | 1644.0063 | 1591.5289 | 3235.5351 | 2765.7421 | 2928.8464 | 5694.5885 | 1337.3175 | 2459.0534 | 84.03% | 76% | N | N | # of new CP systems installed | 5 | 5 | 10 | 5 | 6 | 11 | 1 | 1 | 20% | 10% | YES | N/A | Actual units were higher than imputed units due to a higher volume of groundbed installations required to maintain effective levels of cathodic protection. | Over | On-Target | On-Target | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The purpose of this program is to install cathodic protection (CP) to buried metallic pipeline to mitigate the threat of external corrosion, and if CP levels are inadequate and cannot be made adequate through troubleshooting, PG&E must either replace existing systems or install new equipment (49 CFR § 192.463).
80 | Capital | GT&S | 3K | Gas Trans Remediate Corrosion | 3K6 | Cathodic Protection-New | Loss of Containment on Gas Transmission Pipeline | LOCTM-C019 Cathodic Protection | Ex 3, Ch 9 | No | On-going | Annual | 1644.0063 | 1591.5289 | 3235.5351 | 2763.186 | 2928.8464 | 5692.0324 | 1337.3175 | 2456.4973 | 84.03% | 75.92% | N/A | N/A | N/A | 5 | 5 | 10 | 5 | 6 | 11 | 1 | 1 | 20% | 10% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
81 | Capital | GT&S | 3K | Gas Trans Remediate Corrosion | 3K6 | Cathodic Protection-New | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C018 Cathodic Protection | Ex 3, Ch 9 | No | On-going | Annual | 1644.0063 | 1591.5289 | 3235.5351 | 2765.7421 | 2928.8464 | 5694.5885 | 1337.3175 | 2459.0534 | 84.03% | 76% | N/A | N/A | N/A | 5 | 5 | 10 | 5 | 6 | 11 | 1 | 1 | 20% | 10% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
82 | Capital | GT&S | 3K | Gas Trans Remediate Corrosion | 3K6 | Cathodic Protection-New | Loss of Containment at Natural Gas Storage Well or Reservoir | NGSWR-C007 Cathodic Protection | Ex 3, Ch 9 | No | On-going | Annual | 1644.0063 | 1591.5289 | 3235.5351 | 2765.7421 | 2928.8464 | 5694.5885 | 1337.3175 | 2459.0534 | 84.03% | 76% | N/A | N/A | N/A | 5 | 5 | 10 | 5 | 6 | 11 | 1 | 1 | 20% | 10% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
83 | Capital | GT&S | 3K | Gas Trans Remediate Corrosion | 3K7 (a) | Cathodic Protection-Replacement | SRM Total | SRM Total | Ex 3, Ch 9 | No | On-going | Annual | 4174.7083 | 4041 | 8215.7083 | 7192.2261 | 7063.4841 | 14255.7102 | 3022.4841 | 6040.0018 | 74.8% | 73.52% | N | N | Various | 22 | 22.01 | 44.01 | 30 | 28 | 58 | 5.99 | 13.99 | 27.21% | 31.79% | YES | N/A | Actual units were higher than imputed units due to a higher volume of groundbed replacement required to maintain effective levels of cathodic protection. | Over | On-Target | On-Target | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The purpose of this program is to install cathodic protection (CP) to buried metallic pipeline to mitigate the threat of external corrosion, and if CP levels are inadequate and cannot be made adequate through troubleshooting, PG&E must either replace existing systems or install new equipment (49 CFR § 192.463).
84 | Capital | GT&S | 3K | Gas Trans Remediate Corrosion | 3K7 (a) | Cathodic Protection-Replacement | Loss of Containment on Gas Transmission Pipeline | LOCTM-C019 Cathodic Protection | Ex 3, Ch 9 | No | On-going | Annual | 4174.7083 | 4041 | 8215.7083 | 7192.2261 | 7063.4841 | 14255.7102 | 3022.4841 | 6040.0018 | 74.8% | 73.52% | N/A | N/A | N/A | 22 | 22.01 | 44.01 | 30 | 28 | 58 | 5.99 | 13.99 | 27.21% | 31.79% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
85 | Capital | GT&S | 3K | Gas Trans Remediate Corrosion | 3K7 (a) | Cathodic Protection-Replacement | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C018 Cathodic Protection | Ex 3, Ch 9 | No | On-going | Annual | 4174.7083 | 4041 | 8215.7083 | 7192.2261 | 7063.4841 | 14255.7102 | 3022.4841 | 6040.0018 | 74.8% | 73.52% | N/A | N/A | N/A | 22 | 22.01 | 44.01 | 30 | 28 | 58 | 5.99 | 13.99 | 27.21% | 31.79% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
86 | Capital | GT&S | 3K | Gas Trans Remediate Corrosion | 3K7 (a) | Cathodic Protection-Replacement | Loss of Containment at Natural Gas Storage Well or Reservoir | NGSWR-C007 Cathodic Protection | Ex 3, Ch 9 | No | On-going | Annual | 4174.7083 | 4041 | 8215.7083 | 7192.2261 | 7063.4841 | 14255.7102 | 3022.4841 | 6040.0018 | 74.8% | 73.52% | N/A | N/A | N/A | 22 | 22.01 | 44.01 | 30 | 28 | 58 | 5.99 | 13.99 | 27.21% | 31.79% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
87 | Capital | GT&S | 3K | Gas Trans Remediate Corrosion | 3K8 | Test Station Installation | SRM Total | SRM Total | Ex 3, Ch 9 | No | On-going | Annual | 129.9423 | 125.7636 | 255.706 | 7.2883 | 0.86179 | 8.1501 | -124.9018 | -247.5558 | -99.31% | -96.81% | N | N | # of test stations installed | 5 | 5 | 10 | 0 | 0 | 0 | -5 | -10 | -100% | -100% | YES | N/A | Actual units were lower than imputed units because no capital test station (CTS) installations (over 5 units) needed to be installed to meet requirement for 1 CTS per mile. | Under | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to install test station to meet the requirement of "sufficient test stations" required via 49 § 192.469.
88 | Capital | GT&S | 3K | Gas Trans Remediate Corrosion | 3K8 | Test Station Installation | Loss of Containment on Gas Transmission Pipeline | LOCTM-C019 Cathodic Protection | Ex 3, Ch 9 | No | On-going | Annual | 129.9423 | 125.7636 | 255.706 | 7.2883 | 0.86179 | 8.1501 | -124.9018 | -247.5558 | -99.31% | -96.81% | N/A | N/A | N/A | 5 | 5 | 10 | 0 | 0 | 0 | -5 | -10 | -100% | -100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
89 | Capital | GT&S | 3K | Gas Trans Remediate Corrosion | 3K9 | Electrical Interference - DC | SRM Total | SRM Total | Ex 3, Ch 9 | No | On-going | Annual | 6254.13 | 6053 | 12307.13 | 4724.782 | 9307.0639 | 14031.8459 | 3254.0639 | 1724.7159 | 53.76% | 14.01% | N | N | Dynamic Electrical Interference - DC (# of Projects Completed) | 40 | 40 | 80 | 6 | 23 | 29 | -17 | -51 | -42.5% | -63.75% | YES | N/A | Actual units were lower than imputed units due to the permits and land acquisition delays, which resulted in delayed construction activities. | Under | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to mitigate DC Interference as required by 49 CFR § 192.467 and 473.
90 | Capital | GT&S | 3K | Gas Trans Remediate Corrosion | 3K9 | Electrical Interference - DC | Loss of Containment on Gas Transmission Pipeline | LOCTM-C033 Electrical Interference Program | Ex 3, Ch 9 | No | On-going | Annual | 6254.13 | 6053 | 12307.13 | 4724.782 | 9307.0639 | 14031.8459 | 3254.0639 | 1724.7159 | 53.76% | 14.01% | N/A | N/A | N/A | 40 | 40 | 80 | 6 | 23 | 29 | -17 | -51 | -42.5% | -63.75% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
91 | Capital | GT&S | 3K | Gas Trans Remediate Corrosion | 3KA | Atmospheric Corrosion | SRM Total | SRM Total | Ex 3, Ch 9 | No | On-going | Annual | 326.3529 | 315.9356 | 642.2885 | 2047.7624 | 9459.0169 | 11506.7793 | 9143.0813 | 10864.4908 | 2894% | 1692% | Y | Y | # of spans recoated/ upgraded | 5 | 5 | 10 | 1 | 23 | 24 | 18 | 14 | 360% | 140% | YES | Actual costs were higher than imputed due to the majority of the units were on line 300/400, which are large pipelines and complex jobs. In 2024, asbestos abatement became a common mitigating factor which increased unit cost. | Actual units were higher than imputed due to in 2024 the threshold for capitalizing span re-coates changed from 100 feet to 40 feet, so actual units increased in 3KA and dropped in GJB. | Over | On-Target | Over | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to maintain and re-coat facilities that have observed corrosion or have deteriorated coating.
92 | Capital | GT&S | 3K | Gas Trans Remediate Corrosion | 3KA | Atmospheric Corrosion | Loss of Containment on Gas Transmission Pipeline | LOCTM-C034 Atmospheric Corrosion Program | Ex 3, Ch 9 | No | On-going | Annual | 326.3529 | 315.9356 | 642.2885 | 2047.7624 | 9459.0169 | 11506.7793 | 9143.0813 | 10864.4908 | 2894% | 1692% | N/A | N/A | N/A | 5 | 5 | 10 | 1 | 23 | 24 | 18 | 14 | 360% | 140% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
93 | Capital | GT&S | 3L | Gas Trans Storage Wells | 3L1 | WELL - Drilling | SRM Total | SRM Total | Ex 3, Ch 7 | No | On-going | Annual | 19867.0445 | 47373.4 | 67240.4445 | 23992.2606 | 39437.1706 | 63429.4313 | -7936.2294 | -3811.0132 | -16.75% | -5.668% | Y | Y | # of wells drilled | 3 | 4 | 7 | 1 | 3 | 4 | -1 | -3 | -25% | -42.86% | YES | Actual costs were higher than imputed due to pre-mobiliztion material purchase for 2025 well drilling. | Actual units were lower than imputed units due to permit timing pushing completion of units into 2025. Overall unit plan for driling of new wells during the 2023-2026 rate case is expected to be achieved. | Under | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
94 | Capital | GT&S | 3L | Gas Trans Storage Wells | 3L1 | WELL - Drilling | Loss of Containment at Natural Gas Storage Well or Reservoir | NGSWR-M001 Well - Drilling | Ex 3, Ch 7 | No | On-going | Annual | 19867.0445 | 47373.4 | 67240.4445 | 23992.2606 | 39437.1706 | 63429.4313 | -7936.2294 | -3811.0132 | -16.75% | -5.668% | N/A | N/A | N/A | 3 | 4 | 7 | 1 | 3 | 4 | -1 | -3 | -25% | -42.86% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
95 | Capital | GT&S | 3L | Gas Trans Storage Wells | 3L3 (b) | WELL - Reworks | SRM Total | SRM Total | Ex 3, Ch 7 | No | On-Going | Annual | 66326.1588 | 58802.5929 | 125128.7517 | 89198.912 | 86161.2804 | 175360.1924 | 27358.6875 | 50231.4407 | 46.53% | 40.14% | Y | Y | Various | 19.43 | 17.17 | 36.6 | 25 | 21 | 46 | 3.83 | 9.4 | 22.31% | 25.68% | YES | Actual costs were lower than imputed due to carryover work from 2022 and 2023 that hit in 2024. | Actual units were higher than imputed units due to incremental wells scheduled and required by CalGEM. | Over | On-Target | Over | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period.
96 | Capital | GT&S | 3L | Gas Trans Storage Wells | 3L3 (b) | WELL - Reworks | Loss of Containment at Natural Gas Storage Well or Reservoir | NGSWR-C003 Well Inspections and Rework | Ex 3, Ch 7 | No | On-Going | Annual | 66326.1588 | 58802.5929 | 125128.7517 | 89198.912 | 86161.2804 | 175360.1924 | 27358.6875 | 50231.4407 | 46.53% | 40.14% | N/A | N/A | N/A | 19.43 | 17.17 | 36.6 | 25 | 21 | 46 | 3.83 | 9.4 | 22.31% | 25.68% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
97 | Capital | GT&S | 3L | Gas Trans Storage Wells | 3L4 (c) | WELL - Repair and Replace | SRM Total | SRM Total | Ex 3, Ch 7 | No | On-Going | Annual | 0 | 0 | 0 | 2290.3426 | 5188.0488 | 7478.3913 | 5188.0488 | 7478.3913 | 100% | 100% | N | N | non-unitized: This MAT has no measurable units because it contains a mix of rework units and other project work which is not unitized. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
98 | Capital | GT&S | 3L | Gas Trans Storage Wells | 3L4 (c) | WELL - Repair and Replace | Loss of Containment at Natural Gas Storage Well or Reservoir | NGSWR-C008 Well Repair and Replace | Ex 3, Ch 7 | No | On-Going | Annual | 0 | 0 | 0 | 2290.3426 | 5188.0488 | 7478.3913 | 5188.0488 | 7478.3913 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
99 | Capital | GT&S | 3L | Gas Trans Storage Wells | 3L5 (d) | WELL - Cntrls & Conts Monitrng | SRM Total | SRM Total | Ex 3, Ch 7 | No | On-Going | Annual | 1436.8 | 7782.8029 | 9219.603 | 154.358 | 337.7732 | 492.1311 | -7445.0297 | -8727.4718 | -95.66% | -94.66% | N | N | non-unitized: This MAT has no measurable units because it contains miscellaneous component work. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
100 | Capital | GT&S | 3L | Gas Trans Storage Wells | 3L5 (d) | WELL - Cntrls & Conts Monitrng | Loss of Containment at Natural Gas Storage Well or Reservoir | NGSWR-C002 Well Control Monitoring | Ex 3, Ch 7 | No | On-Going | Annual | 1436.8 | 7782.8029 | 9219.603 | 154.358 | 337.7732 | 492.1311 | -7445.0297 | -8727.4718 | -95.66% | -94.66% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
101 | Capital | GT&S | 44 | Gas Capital:GasTrans-Sub | 44A (e) | Stan-Pac Capital | SRM Total | SRM Total | Ex 3, Ch 13 | No | On-Going | Annual | 3242.5869 | 3060.943 | 6303.5299 | 434.1505 | 475.458 | 909.6085 | -2585.485 | -5393.9214 |  | -85.57% | N | N | Various | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
102 | Capital | GT&S | 44 | Gas Capital:GasTrans-Sub | 44A (e) | Stan-Pac Capital | Loss of Containment on Gas Transmission Pipeline | LOCTM-C037 Stan-Pac Capital | Ex 3, Ch 13 | No | On-Going | Annual | 3242.5869 | 3060.943 | 6303.5299 | 434.1505 | 475.458 | 909.6085 | -2585.485 | -5393.9214 |  | -85.57% | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
103 | Capital | GT&S | 73 | GT Pipeline Capacity | 73A | Capacity for Load Growth | SRM Total | SRM Total | Ex 3, Ch 11 | No | On-going | Annual | 6757.3396 | 6540.0377 | 13297.3773 | 22032.5611 | 3489.2485 | 25521.8096 | -3050.7892 | 12224.4323 | -46.65% | 91.93% | N | N | non-unitized: This MAT has no measurable units because the program features multiple asset types without a common unit. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | On-Target | On-Target | Over | Proceeding as planned | N/A
104 | Capital | GT&S | 73 | GT Pipeline Capacity | 73A | Capacity for Load Growth | Insufficient Capacity to Meet Customer Demand | CPCTY-M001 Capacity for Load Growth | Ex 3, Ch 11 | No | On-going | Annual | 6757.3396 | 6540.0377 | 13297.3774 | 22032.5611 | 3489.2485 | 25521.8096 | -3050.7892 | 12224.4322 | -46.65% | 91.93% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
105 | Capital | GT&S | 73 | GT Pipeline Capacity | 73B | Capacity Betterment | SRM Total | SRM Total | Ex 3, Ch 11 | No | On-going | Annual | 984.3329 | 952.6788 | 1937.0117 | 2691.7916 | 0.49012 | 2692.2817 | -952.1887 | 755.27 | -99.95% | 38.99% | N | N | non-unitized: This MAT has no measurable units because the program captures expenditures for the incremental capacity work only; costs (and units) for the original capacity projects are captured in the originating MWC or MAT. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | N/A
106 | Capital | GT&S | 73 | GT Pipeline Capacity | 73B | Capacity Betterment | Insufficient Capacity to Meet Customer Demand | CPCTY-M002 Capacity Betterment | Ex 3, Ch 11 | No | On-going | Annual | 984.3329 | 952.6788 | 1937.0117 | 2691.7916 | 0.49012 | 2692.2817 | -952.1887 | 755.27 | -99.95% | 38.99% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
107 | Capital | GT&S | 73 | GT Pipeline Capacity | 73D | LNG / CNG | SRM Total | SRM Total | Ex 3, Ch 5 | No | On-going | Annual | 4489.5278 | 4345.154 | 8834.6819 | 5780.9886 | 9346.12 | 15127.1086 | 5000.966 | 6292.4267 | 115.1% | 71.22% | N | N | non-unitized: This MAT has no measurable units due to the extensive variability of the work portfolio. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | N/A
108 | Capital | GT&S | 73 | GT Pipeline Capacity | 73D | LNG / CNG | Loss of Containment on LNG/CNG Portable Equipment | LNCNG-C001 LNG/CNG Portable Capital | Ex 3, Ch 5 | No | On-going | Annual | 4489.5278 | 4345.154 | 8834.6819 | 5780.9886 | 9346.12 | 15127.1086 | 5000.966 | 6292.4267 | 115.1% | 71.22% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
109 | Capital | GT&S | 73 | GT Pipeline Capacity | 73D | LNG / CNG | Loss of Containment on Gas Transmission Pipeline | LOCTM-C002 LNG/CNG to Support Strength Testing | Ex 3, Ch 5 | No | On-going | Annual | 4489.5278 | 4345.154 | 8834.6819 | 5780.9886 | 9346.12 | 15127.1086 | 5000.966 | 6292.4267 | 115.1% | 71.22% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
110 | Capital | GT&S | 75 | GT Pipeline Reliability | 75C | Routine Spend M&C - Capital | SRM Total | SRM Total | Ex 3, Ch 6 | No | On-going | Annual | 18442.8033 | 17849.7214 | 36292.5247 | 11510.8926 | 11705.4875 | 23216.3801 | -6144.2339 | -13076.1446 | -34.42% | -36.03% | N | N | non-unitized: This MAT has no measurable units because it includes a wide assortment of “find-it and fix-it" projects that are typically routine or unique occurrences and do not qualify for another program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | On-Target | On-Target | Under | Proceeding as planned | N/A
111 | Capital | GT&S | 75 | GT Pipeline Reliability | 75C | Routine Spend M&C - Capital | Large Overpressure Event Downstream of Gas M&C Facility | LRGOP-C004 Routine Spend M&C | Ex 3, Ch 6 | No | On-going | Annual | 18442.8033 | 17849.7214 | 36292.5247 | 11510.8926 | 11705.4875 | 23216.3801 | -6144.2339 | -13076.1446 | -34.42% | -36.03% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
112 | Capital | GT&S | 75 | GT Pipeline Reliability | 75C | Routine Spend M&C - Capital | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C007 Routine Spend M&C | Ex 3, Ch 6 | No | On-going | Annual | 18442.8033 | 17849.7214 | 36292.5247 | 11510.8926 | 11705.4875 | 23216.3801 | -6144.2339 | -13076.1446 | -34.42% | -36.03% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
113 | Capital | GT&S | 75 | GT Pipeline Reliability | 75D | Valve Program | SRM Total | SRM Total | Ex 3, Ch 5 | No | On-going | Annual | 45830.2626 | 44356.4575 | 90186.7202 | 24644.4969 | 26480.3018 | 51124.7987 | -17876.1557 | -39061.9214 | -40.3% | -43.31% | Y | Y | non-unitized: This MAT has no measurable units because it is used to record costs for various of “find it/fix it" valve replacement work. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | NO | Actual costs were lower than imputed due to Gas prioritization in support of higher risk or compliance work. | N/A | On-Target | On-Target | Under | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to replace inoperable valves, valves that are leaking, or presenting a dafety or reliability threat.
114 | Capital | GT&S | 75 | GT Pipeline Reliability | 75D | Valve Program | Loss of Containment on Gas Transmission Pipeline | LOCTM-C024 Valve Safety and Reliability | Ex 3, Ch 5 | No | On-going | Annual | 45830.2626 | 44356.4575 | 90186.7202 | 24644.4969 | 26480.3018 | 51124.7987 | -17876.1557 | -39061.9214 | -40.3% | -43.31% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
115 | Capital | GT&S | 75 | GT Pipeline Reliability | 75E | Vintage Pipe Replacement | SRM Total | SRM Total | Ex 3, Ch 5 | No | on-going | annual | 4146.4466 | 4013.1056 | 8159.5522 | 2250.169 | 1747.9369 | 3998.1059 | -2265.1687 | -4161.4463 | -56.44% | -51% | N | N | Miles | 0.27 | 0 | 0.27 | 0 | 0 | 0 | 0 | -0.27 | N/A | -100% | NO | N/A | N/A | Under | Under | On-Target | Rescheduled | N/A
116 | Capital | GT&S | 75 | GT Pipeline Reliability | 75E | Vintage Pipe Replacement | Loss of Containment on Gas Transmission Pipeline | LOCTM-M001 Vintage Pipe Replacement | Ex 3, Ch 5 | No | on-going | annual | 4146.4466 | 4013.1056 | 8159.5522 | 2250.169 | 1747.9369 | 3998.1059 | -2265.1687 | -4161.4463 | -56.44% | -51% | N/A | N/A | N/A | 0.27 | 0.27 | 0.54 | 0 | 0 | 0 | -0.27 | -0.54 | -100% | -100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
117 | Capital | GT&S | 75 | GT Pipeline Reliability | 75H | Pipe Replacement Class Loctn | SRM Total | SRM Total | Ex 3, Ch 5 | No | On-going | Annual | 8587.4198 | 8311.2664 | 16898.6862 | 8846.7668 | 25022.1843 | 33868.9511 | 16710.9179 | 16970.2648 | 201.1% | 100.4% | Y | Y | non-unitized: This MAT is non-unitized since scope is identified during LIDAR analysis. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | NO | Actual costs were higher than imputed due to the program expenditures exceeded imputed due to a larger volume of class location pipe replacements being completed. PG&E completed 6 replacements in 2024 driven by 611 flags and assets operating 2 classes out. | N/A | On-Target | On-Target | Over | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The purpose of this program is the mitigation of identified class location changes via pipe replacement as required by 49 CFR § 192.611.
118 | Capital | GT&S | 75 | GT Pipeline Reliability | 75H | Pipe Replacement Class Loctn | Loss of Containment on Gas Transmission Pipeline | LOCTM-C025 Class Location Change | Ex 3, Ch 5 | No | On-going | Annual | 8587.4198 | 8311.2664 | 16898.6862 | 8846.7668 | 25022.1843 | 33868.9511 | 16710.9179 | 16970.2648 | 201.1% | 100.4% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
119 | Capital | GT&S | 75 | GT Pipeline Reliability | 75I | Valve Automation | SRM Total | SRM Total | Ex 3, Ch 5 | No | On-going | Annual | 23608.1685 | 22848.9794 | 46457.1479 | 5006.1807 | 10314.0233 | 15320.204 | -12534.9561 | -31136.9439 | -54.86% | -67.02% | Y | Y | Valves | 18 | 18 | 36 | 2 | 9 | 11 | -9 | -25 | -50% | -69.44% | YES | Actual costs were lower than imputed due to Gas prioritization in support of higher risk or compliance work. | Actual units were lower than imputed units due to reprioritization in support of higher risk or compliance work. | Under | Under | Under | Rescheduled | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to enhance emergency response by installing automated valves to reduce risks associated with pipeline ruptures.
120 | Capital | GT&S | 75 | GT Pipeline Reliability | 75I | Valve Automation | Loss of Containment on Gas Transmission Pipeline | LOCTM-M004 Valve Automation | Ex 3, Ch 5 | No | On-going | Annual | 23608.1685 | 22848.9794 | 46457.1479 | 5006.1807 | 10314.0233 | 15320.204 | -12534.9561 | -31136.9439 | -54.86% | -67.02% | N/A | N/A | N/A | 18 | 18 | 36 | 2 | 9 | 11 | -9 | -25 | -50% | -69.44% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
121 | Capital | GT&S | 75 | GT Pipeline Reliability | 75J | Geo-Hazard Mitigations | SRM Total | SRM Total | Ex 3, Ch 5 | No | on-going | annual | 8486.1046 | 8213.2093 | 16699.3139 | 5199.4349 | 9042.5206 | 14241.9556 | 829.3113 | -2457.3583 | 10.1% | -14.72% | N | N | non-unitized: This MAT has no measurable units because it is used to record costs for mitigating geo-hazards such as soil-creep, dormant landslides with potential to re-activate, and subsidence. The type of mitigation work performed are not comparable. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
122 | Capital | GT&S | 75 | GT Pipeline Reliability | 75J | Geo-Hazard Mitigations | Loss of Containment on Gas Transmission Pipeline | LOCTM-C001 Geo-Hazard Threat Identification and Mitigation | Ex 3, Ch 5 | No | on-going | annual | 8486.1046 | 8213.2093 | 16699.3139 | 5199.4349 | 9042.5206 | 14241.9556 | 829.3113 | -2457.3583 | 10.1% | -14.72% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
123 | Capital | GT&S | 75 | GT Pipeline Reliability | 75K | Water and Levee Crossings | SRM Total | SRM Total | Ex 3, Ch 5 | No | on-going | annual | 2549.8581 | 2467.86 | 5017.7182 | 12771.9118 | 2916.4718 | 15688.3836 | 448.6117 | 10670.6654 | 18.18% | 212.7% | N | N | Projects | 1 | 1 | 2 | 1 | 0 | 1 | -1 | -1 | -100% | -50% | YES | N/A | Actual units were lower than imputed units due to reprioritization in support of higher risk or compliance work. MATs 75M, 75T, and 75K collectively form the Shallow/Exposed/Water and Levee Crossings Mitigation program. Funds and units can be reallocated flexibly among these MATs as required depending on the highest risk. | Under | On-Target | Over | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to address the risks posed by shallow and exposed pipe on locations of water/levee crossings.
124 | Capital | GT&S | 75 | GT Pipeline Reliability | 75K | Water and Levee Crossings | Loss of Containment on Gas Transmission Pipeline | LOCTM-M002 Shallow and Exposed Pipe (Including Water and Levee Crossing | Ex 3, Ch 5 | No | on-going | annual | 2549.8581 | 2467.86 | 5017.7182 | 12771.9118 | 2916.4718 | 15688.3836 | 448.6117 | 10670.6654 | 18.18% | 212.7% | N/A | N/A | N/A | 1 | 1 | 2 | 1 | 0 | 1 | -1 | -1 | -100% | -50% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
125 | Capital | GT&S | 75 | GT Pipeline Reliability | 75L | Fault Crossings | SRM Total | SRM Total | Ex 3, Ch 5 | No | on-going | annual | 13542.1384 | 13106.6516 | 26648.79 | 9749.3144 | 16625.9264 | 26375.2408 | 3519.2748 | -273.5493 | 26.85% | -1.026% | N | N | Projects | 8 | 8 | 16 | 2 | 3 | 5 | -5 | -11 | -62.5% | -68.75% | YES | N/A | Actual units were lower than imputed units due to reprioritization in support of higher risk or compliance work. | Under | On-Target | On-Target | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The purpose of this program is to addresses the specific threat of land movement strains at known earthquake faults damaging a pipeline due to seismic events.
126 | Capital | GT&S | 75 | GT Pipeline Reliability | 75L | Fault Crossings | Loss of Containment on Gas Transmission Pipeline | LOCTM-C004 Earthquake Fault Crossings | Ex 3, Ch 5 | No | on-going | annual | 13542.1384 | 13106.6516 | 26648.79 | 9749.3144 | 16625.9264 | 26375.2408 | 3519.2748 | -273.5493 | 26.85% | -1.026% | N/A | N/A | N/A | 8 | 8 | 16 | 2 | 3 | 5 | -5 | -11 | -62.5% | -68.75% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
127 | Capital | GT&S | 75 | GT Pipeline Reliability | 75M | Shallow Pipe | SRM Total | SRM Total | Ex 3, Ch 5 | No | on-going | annual | 10178.4298 | 9851.1129 | 20029.5427 | 328.2224 | 539.9355 | 868.1579 | -9311.1773 | -19161.3848 | -94.52% | -95.67% | N | N | Projects | 4 | 4 | 8 | 0 | 0 | 0 | -4 | -8 | -100% | -100% | YES | N/A | Actual units were lower than imputed units due to reprioritization in support of higher risk or compliance work. MATs 75M, 75T, and 75K collectively form the Shallow/Exposed/Water and Levee Crossings Mitigation program. Funds and units can be reallocated flexibly among these MATs as required depending on the highest risk. | Under | On-Target | Under | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The purpose of this program is to address the risks posed by shallow pipe on land.
128 | Capital | GT&S | 75 | GT Pipeline Reliability | 75M | Shallow Pipe | Loss of Containment on Gas Transmission Pipeline | LOCTM-M002 Shallow and Exposed Pipe (Including Water and Levee Crossing | Ex 3, Ch 5 | No | on-going | annual | 10178.4298 | 9851.1129 | 20029.5427 | 328.2224 | 539.9355 | 868.1579 | -9311.1773 | -19161.3848 | -94.52% | -95.67% | N/A | N/A | N/A | 4 | 4 | 8 | 0 | 0 | 0 | -4 | -8 | -100% | -100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
129 | Capital | GT&S | 75 | GT Pipeline Reliability | 75N | Hydrostatic Testing | SRM Total | SRM Total | Ex 3, Ch 5 | No | On-going | Annual | 44061.9104 | 42644.9717 | 86706.8821 | 9545.3329 | 2581.7023 | 12127.0352 | -40063.2694 | -74579.847 | -93.95% | -86.01% | Y | Y | non-unitized: This MAT has no measurable units since scope is identified as capital upgrades during the engineering practice. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | NO | Actual costs were lower than imputed due to a lower volume of identified capital work being executed such as capital upgrades needed to facilitate a strength test. A procedural update to the working assessment plan was implemented to align with Transdef initiative, resulting in a lower amount of scheduled strength tests in 2024 that required capital work. | N/A | On-Target | On-Target | Under | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to assist in faciliating a hydrotest with any captial units of measure either installed, removed or replaced including captial equipment puchases, replacements and piggability improvements driven by the hydrotest.
130 | Capital | GT&S | 75 | GT Pipeline Reliability | 75N | Hydrostatic Testing | Loss of Containment on Gas Transmission Pipeline | LOCTM-M003 Non-TIMP Strength Testing | Ex 3, Ch 5 | No | On-going | Annual | 44061.9104 | 42644.9717 | 86706.8821 | 9545.3329 | 2581.7023 | 12127.0352 | -40063.2694 | -74579.847 | -93.95% | -86.01% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
131 | Capital | GT&S | 75 | GT Pipeline Reliability | 75O | Pipe Rplcmnt - Oth PL Sfty Inv | SRM Total | SRM Total | Ex 3, Ch 5 | No | On-going | Annual | 33831.499 | 32743.5489 | 66575.0479 | 34385.3613 | 49877.5126 | 84262.8739 | 17133.9637 | 17687.826 | 52.33% | 26.57% | Y | Y | non-unitized: This MAT is non-unitized because it is used to record costs for various types of work. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | NO | Actual costs were higher than imputed due to a higher volume of projects, largely driven by higher risk scopes and compliance-related requirements. | N/A | On-Target | On-Target | Over | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to mitigate graded leaks and reliability risks along gas transmission pipelines.
132 | Capital | GT&S | 75 | GT Pipeline Reliability | 75O | Pipe Rplcmnt - Oth PL Sfty Inv | Loss of Containment on Gas Transmission Pipeline | LOCTM-C008 Pipeline Safety and Reliability | Ex 3, Ch 5 | No | On-going | Annual | 33831.499 | 32743.5489 | 66575.0479 | 34385.3613 | 49877.5126 | 84262.8739 | 17133.9637 | 17687.826 | 52.33% | 26.57% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
133 | Capital | GT&S | 75 | GT Pipeline Reliability | 75P | ILI Capital Repair (Non-BA) | SRM Total | SRM Total | Ex 3, Ch 5 | No | On-going | Annual | 14431.0731 | 13967.0001 | 28398.0732 | 1983.6869 | 23769.4825 | 25753.1694 | 9802.4825 | -2644.9037 | 70.18% | -9.314% | N | N | non-unitized: This MAT has no measurable units since work is not known until anomalous results from previous year's Traditional and Non-Traditional ILI inspections are found. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
134 | Capital | GT&S | 75 | GT Pipeline Reliability | 75P | ILI Capital Repair (Non-BA) | Loss of Containment on Gas Transmission Pipeline | LOCTM-C005 In-Line Inspection | Ex 3, Ch 5 | No | On-going | Annual | 14431.0731 | 13967.0001 | 28398.0732 | 1983.6869 | 23769.4825 | 25753.1694 | 9802.4825 | -2644.9037 | 70.18% | -9.314% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
135 | Capital | GT&S | 75 | GT Pipeline Reliability | 75Q | Pipe Replacement (IM) | SRM Total | SRM Total | Ex 3, Ch 5 | No | On-going | Annual | 20044.568 | 19399.9768 | 39444.5448 | 12948.4234 | 30419.4833 | 43367.9066 | 11019.5065 | 3923.3618 | 56.8% | 9.947% | Y | Y | Miles | 0.16 | 0.16 | 0.32 | 0.437 | 0.41 | 0.847 | 0.25 | 0.527 | 156.2% | 164.7% | YES | Actual costs were higher than imputed due to program expenditures exceeded imputed due to a larger volume of projects classified as capital (>50ft and/or capital installation/replacement) and due to more Integrity Management threats coming due in 2024 that required replacement. | Actual units were higher than imputed units due to more projects classified as capital (>50ft and/or capital installation/replacement) and more Integrity Managerment driven threat assessments coming due in 2024 | Over | On-Target | On-Target | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The purpose of this program is to implement TIMP (49 CFR Part 192, Subpart O) capital pipe replacements in lieu of testing when it is a more prudent option.
136 | Capital | GT&S | 75 | GT Pipeline Reliability | 75Q | Pipe Replacement (IM) | Loss of Containment on Gas Transmission Pipeline | LOCTM-C026 TIMP Strength Testing | Ex 3, Ch 5 | No | On-going | Annual | 20044.568 | 19399.9768 | 39444.5448 | 12948.4234 | 30419.4833 | 43367.9066 | 11019.5065 | 3923.3618 | 56.8% | 9.947% | N/A | N/A | N/A | 0.16 | 0.16 | 0.32 | 0.437 | 0.41 | 0.847 | 0.25 | 0.527 | 156.2% | 164.7% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
137 | Capital | GT&S | 75 | GT Pipeline Reliability | 75R | Pipe Rplcmnt In-Lieu of Hydro | SRM Total | SRM Total | Ex 3, Ch 5 | No | On-going | Annual | 41134.578 | 39811.7763 | 80946.3543 | 23753.2066 | 19017.7506 | 42770.9573 | -20794.0256 | -38175.397 | -52.23% | -47.16% | Y | Y | Miles | 0.71 | 0.71 | 1.42 | 2.27 | 0.702 | 2.972 | -0.008 | 1.552 | -1.127% | 109.3% | NO | Actual costs were lower than imputed regulatory values due to project cancellations driven by working assessment plan (WAP) updates and Transdef changes as well as other assessment methods selected over replacement. | N/A | On-Target | On-Target | Under | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The purpose of this program is to implement Non-TIMP capital pipe replacements in lieu of testing when it is a more prudent option.
138 | Capital | GT&S | 75 | GT Pipeline Reliability | 75R | Pipe Rplcmnt In-Lieu of Hydro | Loss of Containment on Gas Transmission Pipeline | LOCTM-M003 Non-TIMP Strength Testing | Ex 3, Ch 5 | No | On-going | Annual | 41134.578 | 39811.7763 | 80946.3543 | 23753.2066 | 19017.7506 | 42770.9573 | -20794.0256 | -38175.397 | -52.23% | -47.16% | N/A | N/A | N/A | 0.71 | 0.71 | 1.42 | 2.27 | 0.702 | 2.972 | -0.008 | 1.552 | -1.127% | 109.3% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
139 | Capital | GT&S | 75 | GT Pipeline Reliability | 75S | Direct Assessment | SRM Total | SRM Total | Ex 3, Ch 5 | No | On-going | Annual | 1774.1918 | 1717.1376 | 3491.3294 | 549.2132 | 204.4489 | 753.6621 | -1512.6886 | -2737.6673 | -88.09% | -78.41% | N | N | non-unitized: This MAT has no measurable units because it is used to record costs for direct assessment capital repairs that arise from ECDA, ICDA, SCCDA or Direct Examination findings. The types of repair work performed are not comparable. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
140 | Capital | GT&S | 75 | GT Pipeline Reliability | 75S | Direct Assessment | Loss of Containment on Gas Transmission Pipeline | LOCTM-C022 Direct Assessment | Ex 3, Ch 5 | No | On-going | Annual | 1774.1918 | 1717.1376 | 3491.3294 | 549.2132 | 204.4489 | 753.6621 | -1512.6886 | -2737.6673 | -88.09% | -78.41% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
141 | Capital | GT&S | 75 | GT Pipeline Reliability | 75T | Exposed Pipe | SRM Total | SRM Total | Ex 3, Ch 5 | No | on-going | annual | 10178.4298 | 9851.1129 | 20029.5427 | 7012.5263 | 3685.7192 | 10698.2455 | -6165.3936 | -9331.2972 | -62.59% | -46.59% | N | N | Projects | 4 | 4 | 8 | 0 | 1 | 1 | -3 | -7 | -75% | -87.5% | YES | N/A | Actual units were lower than imputed units due to reprioritization in support of higher risk or compliance work. MATs 75M, 75T, and 75K collectively form the Shallow/Exposed/Water and Levee Crossings Mitigation program. Funds and units can be reallocated flexibly among these MATs as required depending on the highest risk. | Under | On-Target | On-Target | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The purpose of this program is to address the risks posed by exposed pipe on land.
142 | Capital | GT&S | 75 | GT Pipeline Reliability | 75T | Exposed Pipe | Loss of Containment on Gas Transmission Pipeline | LOCTM-M002 Shallow and Exposed Pipe (Including Water and Levee Crossing | Ex 3, Ch 5 | No | on-going | annual | 10178.4298 | 9851.1129 | 20029.5427 | 7012.5263 | 3685.7192 | 10698.2455 | -6165.3936 | -9331.2972 | -62.59% | -46.59% | N/A | N/A | N/A | 4 | 4 | 8 | 0 | 1 | 1 | -3 | -7 | -75% | -87.5% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
143 | Capital | GT&S | 75 | GT Pipeline Reliability | 75U | Non-TIMP Strength Testing | SRM Total | SRM Total | Ex 3, Ch 5 | No | On-going | Annual | 69859.2382 | 67612.7116 | 137471.9497 | 18663.647 | -5245.744 | 13417.903 | -72858.4555 | -124054.0467 | -107.8% | -90.24% | Y | Y | Miles; historically expense program in MAT MC1 | 39.4 | 39.4 | 78.8 | 9 | 0 | 9 | -39.4 | -69.8 | -100% | -88.58% | YES | Actual costs were lower than imputed due to a mid year accounting guidance change, which altered the allocation process for previously tested Non IM Driven footage and their respective costs. This adjustment led to a one time conversion of all existing scopes, causing MAT 75U to reflect a negative spend ( $5 million in 2024). This issue is not expected to recur, as future projects will be scoped according to the new guidance. Furthermore, Transdef initiative delayed or cancelled existing work out from 2024 to allow for asset classification reviews. | Actual units were lower than imputed due to two drivers - 1) a mid year FERC accounting guidance change, which altered the allocation process for previously tested Non IM Driven footage. This adjustment led to a one time conversion of all existing scopes, causing MAT 75U to have no recorded units in 2024. This issue is not expected to recur, as future projects will be scoped according to the new guidance. 2)Transdef initiative delayed or cancelled work out from 2024 to allow for asset classification reviews. | Under | On-Target | Under | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The purpose of this program is to validate the integrity and assure a margin of safety by strength testing in accordance with 49 CFR § 192.619 for those gas transmission pipelines that: 1) Lack a documented TVC strength test record that is consistent with D.11-06-017, D.12-12-030, and NTSB Safety Recommendation P-10-4 (prioritizing strength testing of gas transmission pipelines with the highest risk factors); 2) Need to have MAOP re-confirmed under 49 CFR §192.624 via either a strength test or pipe replacement; or 3) Need to be either tested or replaced to comply with 49 CFR §192.917 because the manufacturing threat is deemed unstable because it either does not have a TVC record of a test or does not have a 49 CFR Subpart J test to at least 1.25 times MAOP.
144 | Capital | GT&S | 75 | GT Pipeline Reliability | 75U | Non-TIMP Strength Testing | Loss of Containment on Gas Transmission Pipeline | LOCTM-M003 Non-TIMP Strength Testing | Ex 3, Ch 5 | No | On-going | Annual | 69859.2382 | 67612.7116 | 137471.9497 | 18663.647 | -5245.744 | 13417.903 | -72858.4555 | -124054.0467 | -107.8% | -90.24% | N/A | N/A | N/A | 39.4 | 39.4 | 78.8 | 9 | 0 | 9 | -39.4 | -69.8 | -100% | -88.58% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
145 | Capital | GT&S | 75 | GT Pipeline Reliability | 75V | TIMP Direct Exam-Captal Recoat | SRM Total | SRM Total | Ex 3, Ch 5 | No | On-going | Annual | 2328.1523 | 2253.2838 | 4581.436 | 329.8791 | 5789.7573 | 6119.6364 | 3536.4736 | 1538.2004 | 156.9% | 33.57% | N | N | # of DE Projects with Capital Repair/Recoat | 2 | 2 | 4 | 0 | 4 | 4 | 2 | 0 | 100% | 0% | YES | N/A | Actal units were higher than imputed units due to recapitalization of recoating from 100 feet to 40 feet. This led to more work scopes of work materializing that meets the 40 foot threshold. | Over | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to perform 100% Direct Examinations on pipeline segments greater than 40 feet.
146 | Capital | GT&S | 75 | GT Pipeline Reliability | 75V | TIMP Direct Exam-Captal Recoat | Loss of Containment on Gas Transmission Pipeline | LOCTM-C022 Direct Assessment | Ex 3, Ch 5 | No | On-going | Annual | 2328.1523 | 2253.2838 | 4581.436 | 329.8791 | 5789.7573 | 6119.6364 | 3536.4736 | 1538.2004 | 156.9% | 33.57% | N/A | N/A | N/A | 2 | 2 | 4 | 0 | 4 | 4 | 2 | 0 | 100% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
147 | Capital | GT&S | 76 | GT Pipeline Reliability | 762 | Gill Ranch Capital | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 3, Ch 6 | No | On-going | Annual | 999.1173 | 967 | 1966.1173 | 289.8077 | 1896.7209 | 2186.5286 | 929.7209 | 220.4113 | 96.14% | 11.21% | N | N | non-unitized: This MAT has no measurable units due to various types of projects included. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
148 | Capital | GT&S | 76 | GT Station Reliability | 763 | Perform Simple Station Rblds | SRM Total | SRM Total | Ex 3, Ch 6 | No | On-going | Annual | 7394.0865 | 7156.3082 | 14550.3948 | 10429.0422 | 8954.1065 | 19383.1487 | 1797.7983 | 4832.7539 | 25.12% | 33.21% | N | N | # of Simple Stations Rebuilt | 2 | 2 | 4 | 2 | 1 | 3 | -1 | -1 | -50% | -25% | YES | N/A | Actual units were lower than imputed due to Project execution delayed due to project redesign as original design was determined to not be up to current standard and to avoid year end weather and clearance challenges. | Under | Under | On-Target | Rescheduled | This program's work is ongoing and will continue in PG&E's 2023 GRC period
149 | Capital | GT&S | 76 | GT Station Reliability | 763 | Perform Simple Station Rblds | Large Overpressure Event Downstream of Gas M&C Facility | LRGOP-C001 Perform Simple Station Rebuilds | Ex 3, Ch 6 | No | On-going | Annual | 7394.0865 | 7156.3082 | 14550.3948 | 10429.0422 | 8954.1065 | 19383.1487 | 1797.7983 | 4832.7539 | 25.12% | 33.21% | N/A | N/A | N/A | 2 | 2 | 4 | 2 | 1 | 3 | -1 | -1 | -50% | -25% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
150 | Capital | GT&S | 76 | GT Station Reliability | 763 | Perform Simple Station Rblds | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C004 Perform Simple Station Rebuilds | Ex 3, Ch 6 | No | On-going | Annual | 7394.0865 | 7156.3082 | 14550.3948 | 10429.0422 | 8954.1065 | 19383.1487 | 1797.7983 | 4832.7539 | 25.12% | 33.21% | N/A | N/A | N/A | 2 | 2 | 4 | 2 | 1 | 3 | -1 | -1 | -50% | -25% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
151 | Capital | GT&S | 76 | GT Station Reliability | 764 | Perform Complex Station Rblds | SRM Total | SRM Total | Ex 3, Ch 6 | No | On-going | Annual | 47094.1854 | 45579.7352 | 92673.9205 | 21179.6493 | 55504.3061 | 76683.9554 | 9924.5709 | -15989.9652 | 21.77% | -17.25% | N | N | # of Complex Stations Rebuilt | 1.5 | 1.5 | 3 | 1 | 1 | 2 | -0.5 | -1 | -33.33% | -33.33% | YES | N/A | Actual units were lower than imputed due to the program being impacted by Gas prioritization in support of higher risk/compliance work that needed to be funded which impacted construction at Panoche and engineering at Irvington. | Under | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period
152 | Capital | GT&S | 76 | GT Station Reliability | 764 | Perform Complex Station Rblds | Large Overpressure Event Downstream of Gas M&C Facility | LRGOP-C002 Perform Complex Station Rebuilds | Ex 3, Ch 6 | No | On-going | Annual | 47094.1854 | 45579.7352 | 92673.9205 | 21179.6493 | 55504.3061 | 76683.9554 | 9924.5709 | -15989.9652 | 21.77% | -17.25% | N/A | N/A | N/A | 1.5 | 1.5 | 3 | 0 | 1 | 1 | -0.5 | -2 | -33.33% | -66.67% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
153 | Capital | GT&S | 76 | GT Station Reliability | 764 | Perform Complex Station Rblds | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C005 Perform Complex Station Rebuilds | Ex 3, Ch 6 | No | On-going | Annual | 47094.1854 | 45579.7352 | 92673.9205 | 21179.6493 | 55504.3061 | 76683.9554 | 9924.5709 | -15989.9652 | 21.77% | -17.25% | N/A | N/A | N/A | 1.5 | 1.5 | 3 | 0 | 1 | 1 | -0.5 | -2 | -33.33% | -66.67% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
154 | Capital | GT&S | 76 | GT Station Reliability | 765 | Perform Transm Terminal Upgrd | SRM Total | SRM Total | Ex 3, Ch 6 | No | On-going | Annual | 10771.9092 | 10425.5 | 21197.4092 | 8749.9469 | 5281.2737 | 14031.2206 | -5144.2263 | -7166.1885 | -49.34% | -33.81% | N | N | non-unitized: This MAT has no measurable units because it captures individual projects that address specific upgrades inside the terminals in addition to routine terminal work. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | N/A
155 | Capital | GT&S | 76 | GT Station Reliability | 765 | Perform Transm Terminal Upgrd | Large Overpressure Event Downstream of Gas M&C Facility | LRGOP-C003 Perform Transmission Terminal Upgrade | Ex 3, Ch 6 | No | On-going | Annual | 10771.9092 | 10425.5 | 21197.4092 | 8749.9469 | 5281.2737 | 14031.2206 | -5144.2263 | -7166.1885 | -49.34% | -33.81% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
156 | Capital | GT&S | 76 | GT Station Reliability | 765 | Perform Transm Terminal Upgrd | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C006 Perform Transmission Terminal Upgrade | Ex 3, Ch 6 | No | On-going | Annual | 10771.9092 | 10425.5 | 21197.4092 | 8749.9469 | 5281.2737 | 14031.2206 | -5144.2263 | -7166.1885 | -49.34% | -33.81% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
157 | Capital | GT&S | 76 | GT Station Reliability | 766 | Becker Sys Upgrade | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 3, Ch 6 | No | On-Going | Annual | 0 | 0 | 0 | 0.85722 | 157.7847 | 158.6419 | 157.7847 | 158.6419 | 100% | 100% | N | N | non-unitized: This MAT was not forecast in the 2023 GRC and includes Becker control valve system upgrade activities. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | N/A
158 | Capital | GT&S | 76 | GT Station Reliability | 76G | GT Over Pressure Protection | SRM Total | SRM Total | Ex 3, Ch 6 | No | On-going | Annual | 0 | 0 | 0 | 24613.493 | 22015.7559 | 46629.2489 | 22015.7559 | 46629.2489 | 100% | 100% | Y | Y | # Rebuilds and Retrofits | 0 | 0 | 0 | 0 | 28 | 28 | 28 | 28 | 100 | N/A | YES | Actual costs were higher than imputed due to program having no adopted funding in the 2023 GRC. However, program was deemed important and continued to be performed by Gas Operations | Actual units were higher than imputed due to program having no adopted units in the 2023 GRC. However, program was deemed important and continued to be performed by Gas Operations. | On-Target | On-Target | Over | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period
159 | Capital | GT&S | 76 | GT Station Reliability | 76G | GT Over Pressure Protection | Large Overpressure Event Downstream of Gas M&C Facility | LRGOP-M002 GT Overpressure Protection | Ex 3, Ch 6 | No | On-going | Annual | 0 | 0 | 0 | 24613.493 | 22015.7559 | 46629.2489 | 22015.7559 | 46629.2489 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
160 | Capital | GT&S | 76 | GT Station Reliability | 76M | GT SCADA Visibility | SRM Total | SRM Total | Ex 3, Ch 11 | No | On-going | Annual | 3106 | 3006.1987 | 6112.1987 | 2419.8668 | 1264.1081 | 3683.9749 | -1742.0907 | -2428.2238 | -57.95% | -39.73% | N | N | # of Remote Terminal Units Installed | 8 | 8 | 16 | 5 | 1 | 6 | -7 | -10 | -87.5% | -62.5% | YES | N/A | Actual units were lower than imputed adopted units due to either upgrading from the SCADAPack 350 to a newer version of the SCADAPack, permitting delays, or both. | Under | Under | On-Target | Rescheduled | This program's work is ongoing and will continue in PG&E's 2023 GRC period
161 | Capital | GT&S | 76 | GT Station Reliability | 76M | GT SCADA Visibility | Insufficient Capacity to Meet Customer Demand | CPCTY-M003 GT SCADA Visibility | Ex 3, Ch 11 | No | On-going | Annual | 3106 | 3006.1987 | 6112.1987 | 2419.8668 | 1264.1081 | 3683.9749 | -1742.0907 | -2428.2238 | -57.95% | -39.73% | N/A | N/A | N/A | 8 | 8 | 16 | 5 | 1 | 6 | -7 | -10 | -87.5% | -62.5% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
162 | Capital | GT&S | 76 | GT Station Reliability | 76M | GT SCADA Visibility | Large Overpressure Event Downstream of Gas M&C Facility | LRGOP-M001 GT SCADA Visibility | Ex 3, Ch 11 | No | On-going | Annual | 3106 | 3006.1987 | 6112.1987 | 2419.8668 | 1264.1081 | 3683.9749 | -1742.0907 | -2428.2238 | -57.95% | -39.73% | N/A | N/A | N/A | 8 | 8 | 16 | 5 | 1 | 6 | -7 | -10 | -87.5% | -62.5% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
163 | Capital | GT&S | 76 | GT Station Reliability | 76M | GT SCADA Visibility | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-M003 GT SCADA Visibility | Ex 3, Ch 11 | No | On-going | Annual | 3106 | 3006.1987 | 6112.1987 | 2419.8668 | 1264.1081 | 3683.9749 | -1742.0907 | -2428.2238 | -57.95% | -39.73% | N/A | N/A | N/A | 8 | 8 | 16 | 5 | 1 | 6 | -7 | -10 | -87.5% | -62.5% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
164 | Capital | GT&S | 76 | GT Station Reliability | 76N | Routine Spend C&P Capital | SRM Total | SRM Total | Ex 3, Ch 6 | No | On-going | Annual | 58989.1699 | 57710.2766 | 116699.4465 | 33868.6951 | 41534.0143 | 75402.7095 | -16176.2622 | -41296.737 | -28.03% | -35.39% | Y | Y | non-unitized: This MAT has no measurable units because it includes a wide assortment of “find-it and fix-it” projects that are typically routine or unique occurrences and do not qualify for another program. | N/A | N/A | N/A | N/A | - | N/A | N/A | N/A | N/A | N/A | NO | Actual costs were lower due to the program being impacted by Gas prioritization in support of higher risk/compliance work that needed to be funded which impacted project start and construction | N/A | On-Target | On-Target | Under | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period
165 | Capital | GT&S | 76 | GT Station Reliability | 76N | Routine Spend C&P Capital | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C020 Routine Spend C&P | Ex 3, Ch 6 | No | On-going | Annual | 58989.1699 | 57710.2766 | 116699.4465 | 33868.6951 | 41534.0143 | 75402.7095 | -16176.2622 | -41296.737 | -28.03% | -35.39% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
166 | Capital | GT&S | 76 | GT Station Reliability | 76P | GT Elect Upgrd-Hinkley&Topock | SRM Total | SRM Total | Ex 3, Ch 6 | No | On-going | Annual | 6303.6591 | 6100.9466 | 12404.6057 | 4040.5185 | 7840.1393 | 11880.6578 | 1739.1927 | -523.9479 | 28.51% | -4.224% | N | N | # of upgrades | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as planned | N/A
167 | Capital | GT&S | 76 | GT Station Reliability | 76P | GT Elect Upgrd-Hinkley&Topock | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C021 GT Elect Upgrd-Hinkley&Topock | Ex 3, Ch 6 | No | On-going | Annual | 6303.6591 | 6100.9466 | 12404.6057 | 4040.5185 | 7840.1393 | 11880.6578 | 1739.1927 | -523.9479 | 28.51% | -4.224% | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
168 | Capital | GT&S | 76 | GT Station Reliability | 76S | Engineering Critical Assmnt 2 | SRM Total | SRM Total | Ex 3, Ch 6 | No | 20+ | 9 | 9848.5551 | 9531.8462 | 19380.4012 | 1090.0053 | 1371.5149 | 2461.5202 | -8160.3313 | -16918.881 | -85.61% | -87.3% | N | N | non-unitized: This MAT has no measurable units because project work that occurs under this MAT is non-fungible and covers a wide range of asset types, and scope of assets requiring work. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | On-Target | On-Target | Under | Proceeding as Planned | N/A
169 | Capital | GT&S | 76 | GT Station Reliability | 76S | Engineering Critical Assmnt 2 | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-M008 Engineering Critical Assessment 2 | Ex 3, Ch 6 | No | 20+ | 9 | 9848.5551 | 9531.8462 | 19380.4012 | 1090.0053 | 1371.5149 | 2461.5202 | -8160.3313 | -16918.881 | -85.61% | -87.3% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
170 | Capital | GT&S | 76 | GT Station Reliability | 76T | Compressor Control Upgrades | SRM Total | SRM Total | Ex 3, Ch 6 | No | On-going | Annual | 12090.221 | 11838.8719 | 23929.0929 | 6475.0489 | 13549.0196 | 20024.0685 | 1710.1477 | -3905.0244 | 14.45% | -16.32% | N | N | # of Station Upgrades | 1 | 1 | 2 | 2 | 0 | 2 | -1 | 0 | -100% | 0% | YES | N/A | Actual Units were lower than imputed due to Project is being delayed by the required CPCN permit approval process. | Under | Under | On-Target | Rescheduled | This program's work is ongoing and will continue in PG&E's 2023 GRC period
171 | Capital | GT&S | 76 | GT Station Reliability | 76T | Compressor Control Upgrades | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C023 Compressor Control Upgrades | Ex 3, Ch 6 | No | On-going | Annual | 12090.221 | 11838.8719 | 23929.0929 | 6475.0489 | 13549.0196 | 20024.0685 | 1710.1477 | -3905.0244 | 14.45% | -16.32% | N/A | N/A | N/A | 1 | 1 | 2 | 2 | 0 | 2 | -1 | 0 | -100% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
172 | Capital | GT&S | 76 | GT Station Reliability | 76V | Station Strength Tst - Capital | SRM Total | SRM Total | Ex 3, Ch 6 | No | 12 | 9 | 16745.3354 | 16206.8405 | 32952.1759 | 2431.3486 | 1469.3404 | 3900.689 | -14737.5001 | -29051.4869 | -90.93% | -88.16% | Y | Y | non-unitized: This MAT has no measurable units because project work that occurs under this MAT is non-fungible and covers a wide range of asset types, and scope of assets requiring work. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | NO | Actual costs were lower due to Station Strength Test projects subject to disallowance based on install date and test record of various features. Disallowed costs are moved to MAT JTU. Projects executed in this year were significantly more disallowed than expected over the rate case period. | N/A | On-Target | On-Target | Under | Proceeding as Planned | Program that includes 76V , 76S, JTV, LV2 to be rolled into single MAT codes for Exp/Capital: 76S and LV2.
173 | Capital | GT&S | 76 | GT Station Reliability | 76V | Station Strength Tst - Capital | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-M006 Station Strength Test | Ex 3, Ch 6 | No | 12 | 9 | 16745.3354 | 16206.8405 | 32952.1759 | 2431.3486 | 1469.3404 | 3900.689 | -14737.5001 | -29051.4869 | -90.93% | -88.16% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
174 | Capital | GT&S | 76 | GT Station Reliability | 76X | Compressor Replacements | SRM Total | SRM Total | Ex 3, Ch 6 | No | On-going | Annual | 10487.5673 | 10562.2588 | 21049.8261 | 18757.0257 | 12428.2945 | 31185.3202 | 1866.0357 | 10135.4941 | 17.67% | 48.15% | N | N | # of Compressor Unit Replacements | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | N/A | N/A | NO | N/A | N/A | Over | On-Target | Over | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period
175 | Capital | GT&S | 76 | GT Station Reliability | 76X | Compressor Replacements | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C024 Compressor Replacements | Ex 3, Ch 6 | No | On-going | Annual | 10487.5673 | 10562.2588 | 21049.8261 | 18757.0257 | 12428.2945 | 31185.3202 | 1866.0357 | 10135.4941 | 17.67% | 48.15% | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
176 | Capital | GT&S | 76 | GT Station Reliability | 76Z | Physical Security - Capital | SRM Total | SRM Total | Ex 3, Ch 6 | No | On-going | Annual | 9654.748 | 9344.2715 | 18999.0195 | 585.1428 | 3764.8654 | 4350.0082 | -5579.4061 | -14649.0113 | -59.71% | -77.1% | N | N | # Stations | 2 | 2 | 4 | 0 | 0 | 0 | -2 | -4 | -100% | -100% | YES | N/A | Actual units were lower than imputed units due to 2 parallel security projects expected to execute in 2024, however, due to scope changes from Corporate Security and internal IT as a result of changing standards during design (i.e. rack configurations) and third-party utility design timelines for new telecommunications lines, both projects did not execute as planned. Unit capture (2 units) expected in 2025. | Under | Under | Under | Rescheduled | This program's work is ongoing and will continue in PG&E's 2023 GRC period
177 | Capital | GT&S | 76 | GT Station Reliability | 76Z | Physical Security - Capital | Loss of Contnm at Gas Measrm & Cntrl / Cmprsn & Prcssn Facil | MCCPF-C025 Physical Security - Capital | Ex 3, Ch 6 | No | On-going | Annual | 9654.748 | 9344.2715 | 18999.0195 | 585.1428 | 3764.8654 | 4350.0082 | -5579.4061 | -14649.0113 | -59.71% | -77.1% | N/A | N/A | N/A | 2 | 2 | 4 | 0 | 0 | 0 | -2 | -4 | -100% | -100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
178 | Capital | GT&S | 84 | GT Gas Gathering System Manage | 84C | GG- Reliability/Safety | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 3, Ch 5 | No | On-going | Annual | 0 | 0 | 0 | 4.447 | 2.3778 | 6.8248 | 2.3778 | 6.8248 | 100% | 100% | N | N | non-unitized: This MAT has no measurable units as this is no longer used to capture work and reflects close out costs for odorizer installation projects on gas gathering lines. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
179 | Capital | GT&S | 84 | GT Gas Gathering System Manage | 84D | Gas Gathering | SRM Total | SRM Total | Ex 3, Ch 5 | No | On-Going | Annual | 12290.6286 | 11895.3878 | 24186.0164 | 3278.7936 | 10388.896 | 13667.6897 | -1506.4918 | -10518.3268 | -12.66% | -43.49% | N | N | Meters | 11 | 11 | 22 | 2 | 6 | 8 | -5 | -14 | -45.45% | -63.64% | YES | N/A | Actual units were lower than imputed adopted units due to reprioritization in support of higher risk or compliance work. | Under | Under | Under | Rescheduled | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to divest idle gas gathering assets to minimize operating risks.
180 | Capital | GT&S | 84 | GT Gas Gathering System Manage | 84D | Gas Gathering | Loss of Containment on Gas Transmission Pipeline | LOCTM-C006 Gas Gathering Divestiture | Ex 3, Ch 5 | No | On-Going | Annual | 12290.6286 | 11895.3878 | 24186.0164 | 3278.7936 | 10388.896 | 13667.6897 | -1506.4918 | -10518.3268 | -12.66% | -43.49% | N/A | N/A | N/A | 11 | 11 | 22 | 2 | 6 | 8 | -5 | -14 | -45.45% | -63.64% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
181 | Capital | GT&S | 98 | GT Integrity Management | 98C | ILI Upgrades | SRM Total | SRM Total | Ex 3, Ch 5 | No | On-going | Annual | 61141.5927 | 59175.4073 | 120317.0001 | 145155.4964 | 100827.3117 | 245982.808 | 41651.9043 | 125665.8079 | 70.39% | 104.4% | Y | Y | # of Projects | 4 | 4 | 8 | 6 | 1 | 7 | -3 | -1 | -75% | -12.5% | YES | Actual costs were higher than imputed regulatory values due to several drivers. Program is working through more complex scopes of work compared to historical upgrades such as smaller diameter pipe projects. The program has also completed a significant amount of non-unitized work (roughly $16M) in 2024 which resulted in a higher program cost without that work being reflected in unit totals | The actual units were lower than imputed adopted units due to exceeding the target in 2023. PG&E forecasted 2 units for 2024 to balance the plan, as the program completed 6 units in 2023 which was 2 units over the imputed target. Of the 2 units forecasted for 2024, one was completed, while the other unit was carried over into 2025 due to risk of tie-in during the critical winter month of December | Under | On-Target | Over | Proceeding as Planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The purpose of this program is to upgrade natural GT pipelines in order to be capable of in-line inspection (where warranted) as outlined in PG&E's Pipeline Safety Enhancement Plan. This includes the installation of traditional pig launchers/receivers, replacement of pipe, elbows and main line valves, and additional retrofits required due to new technology.
182 | Capital | GT&S | 98 | GT Integrity Management | 98C | ILI Upgrades | Loss of Containment on Gas Transmission Pipeline | LOCTM-M005 Traditional ILI Upgrades | Ex 3, Ch 5 | No | On-going | Annual | 61141.5927 | 59175.4073 | 120317.0001 | 145155.4964 | 100827.3117 | 245982.808 | 41651.9043 | 125665.8079 | 70.39% | 104.4% | N/A | N/A | N/A | 4 | 4 | 8 | 6 | 1 | 7 | -3 | -1 | -75% | -12.5% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
183 | Capital | Electric Distribution | 05 | Tools & Equipment | N/A | Not assigned | SRM Total | SRM Total | Ex 4, Ch 22 | No | On-going | Annual | 7607.7394 | 7913.0622 | 15520.8016 | 9412.6643 | 12978.765 | 22391.4293 | 5065.7028 | 6870.6277 | 64.02% | 44.27% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | This is an ongoing program that includes the cost of tools and test equipment used by Maintenance, Construction, Substation, Test, and Restoration employees to perform distribution-related work.
184 | Capital | Electric Distribution | 05 | Tools & Equipment | N/A | Not assigned | Wildfire | WLDFR-M020: Enhanced Powerline Safety Settings | Ex 4, Ch 22 | Yes | N/A | N/A | 0 | 0 | 0 | 89.9042 | 190.41 | 280.3142 | 190.41 | 280.3142 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
185 | Capital | Electric Distribution | 05 | Tools & Equipment | N/A | Not assigned | SRM (NON-RAMP) | SRM (NON-RAMP) | Ex 4, Ch 22 | Yes | N/A | N/A | 7607.7394 | 7913.0622 | 15520.8016 | 9322.7601 | 12788.355 | 22111.1151 | 4875.2928 | 6590.3135 | 61.61% | 42.46% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
186 | Capital | Electric Distribution | 06 | E Dist. Line Capacity | 06A | Fdr Prj Assoc w/Subst Capacity | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 17 | No | On-going | Annual | 10498.7578 | 10964.7954 | 21463.5532 | 24351.0927 | 38077.5071 | 62428.5998 | 27112.7117 | 40965.0466 | 247.3% | 190.9% | YES | YES | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Program expenditures exceeded imputed regulatory values due to additional capacity funding deployed in 2024 via SB 410 and Energization Capacity New Business Interim Memorandum Account (ECNBIMA) to provide distribution line capacity to energize customer loads. | N/A | Over | Over | Over | Expanded | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to conduct distribution capacity line work associated with substation capacity projects. PG&E expects to continue to do more work in this program than forecasted due to SB410 requirements, as discussed in PG&E's 2023 GRC capacity phase filing.
187 | Capital | Electric Distribution | 06 | E Dist Line Capacity | 06B | Transformer Repl Overloaded | SRM Total | SRM Total | Ex 4, Ch 17 | No | On-going | Annual | 8523.8734 | 8902.2463 | 17426.1197 | 1383.8001 | 10254.0898 | 11637.8899 | 1351.8435 | -5788.2298 | 15.19% | -33.22% | NO | NO | # transformers | 240 | 240 | 480 | 34 | 320 | 354 | 80 | -126 | 33.33% | -26.25% | YES | Below variance threshold. | Actual units were higher than imputed units because additional funding was provided in 2024, because of SB 410 and Energization Capacity New Business Interim Memorandum Account (ECNBIMA) to provide distribution line capacity to energize customer loads. | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to perform overloaded secondary transformer replacements. In the 2023 GRC cycle, PG&E expects to replace overloaded transformers at a higher pace than in 2023 and 2024, in support of the Distribution Overhead risk.
188 | Capital | Electric Distribution | 06 | E Dist Line Capacity | 06B | Transformer Repl Overloaded | Distribution Overhead | DOVHD-C09A: Overloaded Transformers Replacement | Ex 4, Ch 17 | No | N/A | N/A | 8523.8734 | 8902.2463 | 17426.1197 | 1383.8001 | 10254.0898 | 11637.8899 | 1351.8435 | -5788.2298 | 15.19% | -33.22% | N/A | N/A | # transformers | 240 | 240 | 480 | 34 | 320 | 354 | 80 | -126 | 33.33% | -26.25% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
189 | Capital | Electric Distribution | 06 | E Dist Line Capacity | 06D | Circuits Reinforce-DP Managed | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 17 | No | On-going | Annual | 4674.2293 | 4881.7173 | 9555.9467 | 377.4545 | 881.7948 | 1259.2493 | -3999.9225 | -8296.6974 | -81.94% | -86.82% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | This is an ongoing program which performs distribution circuit reinforcements. This is part of a continuing effort to mitigate distribution line overloads and planning criteria violations.
190 | Capital | Electric Distribution | 06 | E Dist Line Capacity | 06E | Circuits Reinforce-PS Managed | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 17 | No | On-going | Annual | 25025.8287 | 26136.7196 | 51162.5483 | 12634.5253 | 23951.6321 | 36586.1574 | -2185.0875 | -14576.3909 | -8.36% | -28.49% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | This is an ongoing program which performs distribution circuit reinforcements. This is part of a continuing effort to mitigate distribution line overloads and planning criteria violations.
191 | Capital | Electric Distribution | 06 | E Dist Line Capacity | 06G | Voltage Correct Secondary | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 17 | No | On-going | Annual | 2869.6654 | 2997.0492 | 5866.7145 | 4022.729 | 4451.4666 | 8474.1955 | 1454.4174 | 2607.481 | 48.53% | 44.45% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | This is an ongoing program which addresses secondary voltage violations through work such as service replacements.
192 | Capital | Electric Distribution | 06 | E Dist Line Capacity | 06H | Dist Line New Business Perf | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 17 | No | On-going | Annual | 74966.2895 | 78294.0263 | 153260.3158 | 102998.7147 | 137056.0211 | 240054.7357 | 58761.9948 | 86794.42 | 75.05% | 56.63% | YES | YES | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Program expenditures exceeded imputed regulatory values due to additional capacity funding deployed in 2024 via SB 410 and Energization Capacity New Business Interim Memorandum Account (ECNBIMA) to provide distribution line capacity to energize customer loads. | N/A | Over | Over | Over | Expanded | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to provides the capacity necessary to complete new customer applications for service. There has been an increase in new applications for service and added loads that require capacity work to serve, especially in the areas of: transportation electrification, internet based distribution centers, high tech campuses, state and local infrastructure, agricultural well pumping, dairy bio digesters, and indoor cultivation. PG&E expects to continue to do more work in this program than forecasted due to SB410 requirements, as discussed in PG&E's 2023 GRC capacity Phase filing.
193 | Capital | Electric Distribution | 06 | E Dist Line Capacity | 06I | Operational Capacity Proj | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 17 | No | On-going | Annual | 7014.6541 | 7326.033 | 14340.6872 | 1975.9135 | 2347.5295 | 4323.443 | -4978.5035 | -10017.2441 | -67.96% | -69.85% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | This is an ongoing program which improves operational capacity for clearances and emergencies, and will continue through the remainder of the 2023 GRC cycle.
194 | Capital | Electric Distribution | 06 | E Dist Line Capacity | 06K | Power Factor Management | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 17 | No | On-going | Annual | 1167.3831 | 1219.203 | 2386.5861 | 162.4885 | -4.3113 | 158.1772 | -1223.5143 | -2228.4089 | -100.4% | -93.37% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | This is an ongoing program which improves distribution power factor for more efficient use of distribution line and substation assets. PG&E underspent in this program due to increased spending in MAT 06H, which provides capacity for new customer applications for service.
195 | Capital | Electric Distribution | 06 | E Dist Line Capacity | 06P | 06P_Enable DG Dist Line | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 17 | No | On-going | Annual | 1401.3385 | 1463.5436 | 2864.8821 | 109.1745 | 0.4291 | 109.6036 | -1463.1145 | -2755.2785 | -99.97% | -96.17% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | This is an ongoing program which replaces voltage regulator controls to enable two-way power flow on distribution lines. PG&E underspent in this program due to increased spending in MAT 06H, which provides capacity for new customer applications for service.
196 | Capital | Electric Distribution | 06 | E Dist Line Capacity | 06# | Not assigned | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 17 | No | On-going | Annual | 7438.2606 | 7768.4433 | 15206.704 | 7246.1295 | 706.1002 | 7952.2296 | -7062.3432 | -7254.4743 | -90.91% | -47.71% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | The purpose of the MAT 06# is to provide line voltage regulator revolving stock. This MAT centrally managed equipment stock to use as needed which minimizes surplus stock, and is expected to continue through the remainder of PG&E's 2023 GRC period.
197 | Capital | Electric Distribution | 07 | E Dist Inst/Repl OH Poles | 07A | Tree Connect VM Assessments | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 12 | No | On-going | Annual | 0 | 0 | 0 | -1366.6593 | -173.216 | -1539.8754 | -173.216 | -1539.8754 | -100% | -100% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | Under | Proceeding as Planned | This program records costs and reimbursements for joint utility pole replacements and arborist assessments as part of vegetation management. This program will continue through the remainder of PG&E's 2023 GRC period.
198 | Capital | Electric Distribution | 07 | E Dist Inst/Repl OH Poles | 07C | Special Criteria Pole Repl | SRM Total | SRM Total | Ex 4, Ch 12 | No | On-going | Annual | 3150.422 | 3290.2686 | 6440.6906 | 15717.3808 | 11218.7095 | 26936.0903 | 7928.4409 | 20495.3997 | 241% | 318.2% | NO | NO | # poles | 269.69 | 269.6914 | 539.3814 | 581 | 469 | 1050 | 199.3086 | 510.6186 | 73.9% | 94.67% | YES | Below variance threshold. | Actual units were higher than imputed units due to higher volume of tree connect attachments identified as needing replacement than forecast in the 2023 GRC. Tree connects are identified during inspections and prioritized according to the urgency for replacement. For this program the costs are directly associated with the number of poles installed. | Over | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to proactively replace dead, dying, and declining trees being used as a utility power pole prior to premature failure. This program is demand driven based on find rates and associated notifications, and the urgency of the notifications. In the 2023 GRC Final Decision, the Commission adopted a lower unit cost than PG&E forecasted, also contributing to the higher amount of actuals for this program.
199 | Capital | Electric Distribution | 07 | E Dist Inst/Repl OH Poles | 07C | Special Criteria Pole Repl | Wildfire | WLDFR-M013: Pole Programs - Replace Tree Attachments | Ex 4, Ch 12 | No | N/A | N/A | 3150.422 | 3290.2686 | 6440.6906 | 15717.3808 | 11218.7095 | 26936.0903 | 7928.4409 | 20495.3997 | 241% | 318.2% | N/A | N/A | # poles | 269.69 | 269.6914 | 539.3814 | 581 | 469 | 1050 | 199.3086 | 510.6186 | 73.9% | 94.67% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
200 | Capital | Electric Distribution | 07 | E Dist Inst/Repl OH Poles | 07D | Pole Repl | SRM Total | SRM Total | Ex 4, Ch 12 | No | On-going | Annual | 352006.1026 | 367631.5748 | 719637.6774 | 333775.75 | 543832.6285 | 877608.3785 | 176201.0537 | 157970.7012 | 47.93% | 21.95% | YES | YES | # poles | 15963.85 | 15963.8524 | 31927.7024 | 13786 | 17546 | 31332 | 1582.1476 | -595.7024 | 9.911% | -1.866% | NO | Program expenditures exceeded imputed regulatory values due to larger volume of units completed to address notifications in HFTD and higher unit cost than was adopted in the 2023 GRC. | Below variance threshold | On-Target | On-Target | Over | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is a continuing effort to proactively replace degraded or deteriorated poles, prior to premature failure. PG&E will prioritize this work for the remainder of the 2023 GRC cycle to meet WMP commitments. PG&E anticipates the program scope will remain on target and spending will remain higher than imputed over the remainder of the cycle due to higher volumes of degraded pole replacements to address the maintenance log.
201 | Capital | Electric Distribution | 07 | E Dist Inst/Repl OH Poles | 07D | Pole Repl | Distribution Overhead | DOVHD-C011: Pole Programs | Ex 4, Ch 12 | No | N/A | N/A | 352006.1026 | 367631.5748 | 719637.6774 | 333775.75 | 543832.6285 | 877608.3785 | 176201.0537 | 157970.7012 | 47.93% | 21.95% | N/A | N/A | # poles | 15963.85 | 15963.8524 | 31927.7024 | 13786 | 17546 | 31332 | 1582.1476 | -595.7024 | 9.911% | -1.866% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
202 | Capital | Electric Distribution | 07 | E Dist Inst/Repl OH Poles | 07D | Pole Repl | Wildfire | WLDFR-C12C: Pole Replacement | Ex 4, Ch 12 | No | N/A | N/A | 352006.1026 | 367631.5748 | 719637.6774 | 333775.75 | 543832.6285 | 877608.3785 | 176201.0537 | 157970.7012 | 47.93% | 21.95% | N/A | N/A | # poles | 15963.85 | 15963.8524 | 31927.7024 | 13786 | 17546 | 31332 | 1582.1476 | -595.7024 | 9.911% | -1.866% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
203 | Capital | Electric Distribution | 07 | E Dist Inst/Repl OH Poles | 07G | Pole Joint Util Telco Reimb | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 12 | No | On-going | Annual | 0 | 0 | 0 | 0.0001 | 0.08685 | 0.08695 | 0.08685 | 0.08695 | 100% | 100% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | Over | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is for reimbursement of costs incurred with other utilities for joint use of poles.
204 | Capital | Electric Distribution | 07 | E Dist Inst/Repl OH Poles | 07L | Steel Lattice Structures | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 12 | No | On-going | Annual | 0 | 0 | 0 | 7.1779 | 0.61025 | 7.7882 | 0.61025 | 7.7882 | 100% | 100% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | Over | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is for steel lattice tower - pole replacements in non-HFTD zones.
205 | Capital | Electric Distribution | 07 | E Dist Inst/Repl OH Poles | 07O | Overloaded Pole Replacements | SRM Total | SRM Total | Ex 4, Ch 12 | No | On-going | Annual | 7488.796 | 7821.222 | 15310.018 | 12424.3815 | 8228.4568 | 20652.8383 | 407.2348 | 5342.8203 | 5.207% | 34.9% | NO | NO | # poles | 261.88 | 261.8795 | 523.7595 | 304 | 163 | 467 | -98.8795 | -56.7595 | -37.76% | -10.84% | YES | Below variance threshold. | Actual units were lower than imputed units due to higher unit cost of external contractors. | Under | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is a continuing effort to proactively replaced all overloaded poles, prior to premature failure.
206 | Capital | Electric Distribution | 07 | E Dist Inst/Repl OH Poles | 07O | Overloaded Pole Replacements | Distribution Overhead | DOVHD-C011: Pole Programs | Ex 4, Ch 12 | No | N/A | N/A | 7488.796 | 7821.222 | 15310.018 | 12424.3815 | 8228.4568 | 20652.8383 | 407.2348 | 5342.8203 | 5.207% | 34.9% | N/A | N/A | # poles | 261.88 | 261.8795 | 523.7595 | 304 | 163 | 467 | -98.8795 | -56.7595 | -37.76% | -10.84% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
207 | Capital | Electric Distribution | 07 | E Dist Inst/Repl OH Poles | 07O | Overloaded Pole Replacements | Wildfire | WLDFR-C12D: Overloaded Pole Replacement | Ex 4, Ch 12 | No | N/A | N/A | 7488.796 | 7821.222 | 15310.018 | 12424.3815 | 8228.4568 | 20652.8383 | 407.2348 | 5342.8203 | 5.207% | 34.9% | N/A | N/A | # poles | 261.88 | 261.8795 | 523.7595 | 304 | 163 | 467 | -98.8795 | -56.7595 | -37.76% | -10.84% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
208 | Capital | Electric Distribution | 07 | E Dist Inst/Repl OH Poles | 07R | Dist Pole Reinforce | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 12 | No | On-going | Annual | 0 | 0 | 0 | 0 | 10531.2996 | 10531.2996 | 10531.2996 | 10531.2996 | 100% | 100% | NO | YES | # poles | 0 | 0 | 0 | 0 | 5139 | 5139 | 5139 | 5139 | 100% | 100% | YES | Program expenditures exceeded imputed regulatory values because imputed costs are in MAT GAD but starting in 2024 PG&E started managing this program in MAT 07R. In comparing imputed costs in GAD to recorded costs in 07R, this program is over imputed amounts and above the percentage variance threshold, but below the minimum variance it is subject to ($10M). | Actual units were higher than imputed units because this program was forecasted in MAT GAD. In comparing imputed units in GAD to recorded in 07R, this program is over imputed but within the variance threshold for units. | Over | Over | Over | Emergent | This program's work is ongoing and will continue in PG&E's 2023 GRC period. Work that was previously performed under MAT GAD for pole reinforcements will be completed under MAT 07R moving forward. In 2024 PG&E determined that this program could be capitalized.
209 | Capital | Electric Distribution | 07 | E Dist Inst/Repl OH Poles | 07R | Dist Pole Reinforce | Distribution Overhead | DOVHD-C011: Pole Programs | Ex 4, Ch 12 | No | N/A | N/A | 0 | 0 | 0 | 0 | 10531.2996 | 10531.2996 | 10531.2996 | 10531.2996 | 100% | 100% | N/A | N/A | # poles | 0 | 0 | 0 | 0 | 5139 | 5139 | 5139 | 5139 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
210 | Capital | Electric Distribution | 07 | E Dist Inst/Repl OH Poles | 07R | Dist Pole Reinforce | Wildfire | WLDFR-C12E: Pole Restoration Program | Ex 4, Ch 12 | No | N/A | N/A | 0 | 0 | 0 | 0 | 10531.2996 | 10531.2996 | 10531.2996 | 10531.2996 | 100% | 100% | N/A | N/A | # poles | 0 | 0 | 0 | 0 | 5139 | 5139 | 5139 | 5139 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
211 | Capital | Electric Distribution | 07 | E Dist Inst/Repl OH Poles | 07# | Not assigned | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 12 | No | On-going | Annual | 0 | 0 | 0 | 426.3886 | -2023.3251 | -1596.9366 | -2023.3251 | -1596.9366 | -100% | -100% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | Under | Proceeding as Planned | PG&E expects to continue using this MAT to record other costs for installing or replacing overhead poles if needed.
212 | Capital | Electric Distribution | 08 | E Dist Replace OH Asset | 08J | Repl Deteriorated OH Conductor | SRM Total | SRM Total | Ex 4, Ch 13 | No | On-going | Annual | 44888.0629 | 46880.634 | 91768.697 | 17008.8034 | 4948.2993 | 21957.1027 | -41932.3347 | -69811.5943 | -89.44% | -76.07% | YES | YES | # circuit miles | 73.6 | 73.6354 | 147.2354 | 26.8 | 0 | 26.8 | -73.6354 | -120.4354 | -100% | -81.8% | YES | Program expenditures were below imputed regulatory values due to reprioritization to System Hardening work in HFTD areas to reduce ignition risk. | Actual units were lower than imputed units due to reprioritization of the MWC to focus on System Hardening work (08W) in HFTD areas, to reduce ignition risk. | Under | Under | Under | Rescheduled | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to replace deteriorated OH conductor in non-HFTDs prior to premature failure. For the remainder of the GRC cycle, PG&E anticipates that this program will continue to be lower priority than other work in Electric Distribution like wildfire mitigation and capacity work.
213 | Capital | Electric Distribution | 08 | E Dist Replace OH Asset | 08J | Repl Deteriorated OH Conductor | Distribution Overhead | DOVHD-C004: Overhead Conductor Replacement | Ex 4, Ch 13 | No | N/A | N/A | 44888.0629 | 46880.634 | 91768.697 | 17008.8034 | 4948.2993 | 21957.1027 | -41932.3347 | -69811.5943 | -89.44% | -76.07% | N/A | N/A | # circuit miles | 73.6 | 73.6354 | 147.2354 | 26.8 | 0 | 26.8 | -73.6354 | -120.4354 | -100% | -81.8% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
214 | Capital | Electric Distribution | 08 | E Dist Replace OH Asset | 08S | Replace Obsolete OH Switches | SRM Total | SRM Total | Ex 4, Ch 13 | No | On-going | Annual | 314.8767 | 328.854 | 643.7306 | 124.9971 | 910.3932 | 1035.3902 | 581.5392 | 391.6596 | 176.8% | 60.84% | NO | NO | # of Switches Installed/replaced | 9.29 | 9.2898 | 18.5798 | 1 | 15 | 16 | 5.7102 | -2.5798 | 61.47% | -13.89% | YES | Below variance threshold. | Actual units were higher than imputed units due to performing work that was originally planned for 2023, but was delayed due to reprioritization of the MWC to focus on System Hardening work (08W) in HFTD areas, to reduce ignition risk. | Under | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is a continuing effort to replace obsolete OH switches and minimize potential safety issues.
215 | Capital | Electric Distribution | 08 | E Dist Replace OH Asset | 08S | Replace Obsolete OH Switches | Distribution Overhead | DOVHD-M006: Grasshopper and KPF Switch Replacement | Ex 4, Ch 13 | No | N/A | N/A | 314.8767 | 328.854 | 643.7306 | 124.9971 | 910.3932 | 1035.3902 | 581.5392 | 391.6596 | 176.8% | 60.84% | N/A | N/A | # of Switches Installed/replaced | 9.29 | 9.2898 | 18.5798 | 1 | 15 | 16 | 5.7102 | -2.5798 | 61.47% | -13.89% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
216 | Capital | Electric Distribution | 08 | E Dist Replace OH Asset | 08# | Not assigned | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 13 | No | On-going | Annual | 0 | 0 | 0 | -89.4184 | -1757.2754 | -1846.6938 | -1757.2754 | -1846.6938 | -100% | -100% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | Under | Proceeding as Planned | N/A
217 | Capital | Electric Distribution | 08/3U | E Dist Replace OH Asset | 08W/3UG | Wildfire Resiliency projects | SRM Total | SRM Total | Ex 4, Ch 4.3 | No | On-going | Annual | 768193.114 | 1011990.476 | 1780183.59 | 1091088.0691 | 990537.8456 | 2081625.9147 | -21452.6304 | 301442.3247 | -2.12% | 16.93% | YES | NO | # circuit miles | 303.56 | 414 | 717.56 | 424.9 | N/A | 424.9 | -414 | -292.66 | -100% | -40.79% | YES | Program expenditures were below imputed regulatory values due to a lower volume of Underground and Overhead miles completed. The program executed mileage in 2024 in closer alignment to the 2023-2025 Wildfire Mitigation Plan 2024 Change Order, resulting in an underrun in dollars and miles. | Actual units were lower than imputed units due to a lower volume of Underground and Overhead miles completed. The program executed mileage in 2024 in closer alignment to the 2023-2025 Wildfire Mitigation Plan 2024 Change Order, resulting in an underrun in dollars and miles. | On-Target | On-Target | Over | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to conduct System Hardening for wildfire mitigation. Since filing the 2023 GRC, PG&E began recording undergrounding costs associated with this program to new MAT code 3UG, so PG&E is combining the codes because the work is the same as what was imputed in 08W. PG&E is reporting the status as "Proceeding as Planned" because PG&E intends, over the 2023 GRC cycle, to manage the program according to the 2023 GRC Final Decision; adjusting volumes of units in the later years to account for overage in year 2023.
218 | Capital | Electric Distribution | 08/3U | E Dist Replace OH Asset | 08W/3UG | Wildfire Resiliency projects | Distribution Overhead | DOVHD-M002: System Hardening | Ex 4, Ch 4.3 | No | N/A | N/A | 768193.114 | 1011990.476 | 1780183.59 | 1090579.7795 | 990457.307 | 2081037.0866 | -21533.169 | 300853.4966 | -2.128% | 16.9% | N/A | N/A | # circuit miles | 303.56 | 414 | 717.56 | 424.9 | 326 | 750.9 | -88 | 33.34 | -21.26% | 4.646% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
219 | Capital | Electric Distribution | 08/3U | E Dist Replace OH Asset | 08W/3UG | Wildfire Resiliency projects | Wildfire | WLDFR-M002: System Hardening | Ex 4, Ch 4.3 | No | N/A | N/A | 768193.114 | 1011990.476 | 1780183.59 | 1090579.7795 | 990457.307 | 2081037.0866 | -21533.169 | 300853.4966 | -2.128% | 16.9% | N/A | N/A | # circuit miles | 303.56 | 414 | 717.56 | 424.9 | 326 | 750.9 | -88 | 33.34 | -21.26% | 4.646% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
220 | Capital | Electric Distribution | 09 | E Dist Automation & Protection | 09A | ED Line SCADA Inst/Repl | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 16 | No | On-going | Annual | 0 | 0 | 0 | 3.046 | 0.5084 | 3.5544 | 0.5084 | 3.5544 | 100% | 100% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | Over | Proceeding as Planned | This program work for SCADA / RTU replacements outside of substations is ongoing and is recorded in MAT 49A. Minimal costs may still be recorded but MAT 09A has been retired.
221 | Capital | Electric Distribution | 09 | E Dist Automation & Protection | 09B | ED Sub SCADA/RTU Replace | SRM Total | SRM Total | Ex 4, Ch 16 | No | On-going | Annual | 20074.1028 | 20879.7403 | 40953.8431 | 16712.95 | 29257.2056 | 45970.1556 | 8377.4653 | 5016.3125 | 40.12% | 12.25% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | This program has no end date and will continue through the remainder of the 2023 GRC cycle. The purpose of this program is a continuing effort to replace aging infrastructure.
222 | Capital | Electric Distribution | 09 | E Dist Automation & Protection | 09B | ED Sub SCADA/RTU Replace | Distribution Overhead | DOVHD-C007: Supervisory Control and Data Acquisition | Ex 4, Ch 16 | Yes | N/A | N/A | 20074.1028 | 20879.7403 | 40953.8431 | 2825.896 | 11253.5883 | 14079.4843 | -9626.152 | -26874.3588 | -46.1% | -65.62% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
223 | Capital | Electric Distribution | 09 | E Dist Automation & Protection | 09B | ED Sub SCADA/RTU Replace | Wildfire | WLDFR-M020: Enhanced Powerline Safety Settings | Ex 4, Ch 16 | Yes | N/A | N/A | 0 | 0 | 0 | 13887.054 | 18003.6173 | 31890.6713 | 18003.6173 | 31890.6713 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
224 | Capital | Electric Distribution | 09 | E Dist Automation & Protection | 09D | ED Sub SCADA/RTU Install | SRM Total | SRM Total | Ex 4, Ch 16 | No | On-going | Annual | 517.6538 | 538.4289 | 1056.0828 | 421.6553 | 866.9467 | 1288.602 | 328.5178 | 232.5192 | 61.01% | 22.02% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | This program has no end date and will continue through the remainder of the 2023 GRC cycle. The purpose of this program is a continuing effort to implement new infrastructure.
225 | Capital | Electric Distribution | 09 | E Dist Automation & Protection | 09D | ED Sub SCADA/RTU Install | Distribution Overhead | DOVHD-C007: Supervisory Control and Data Acquisition | Ex 4, Ch 16 | No | N/A | N/A | 517.6538 | 538.4289 | 1056.0828 | 421.6553 | 866.9467 | 1288.602 | 328.5178 | 232.5192 | 61.01% | 22.02% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
226 | Capital | Electric Distribution | 09 | E Dist Automation & Protection | 09E | ED Sub Protect Relay Inst/Repl | SRM Total | SRM Total | Ex 4, Ch 16 | No | On-going | Annual | 3032.8639 | 3167.492 | 6200.3559 | 226.3845 | 2520.3042 | 2746.6887 | -647.1878 | -3453.6672 | -20.43% | -55.7% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | This program has no end date and will continue through the remainder of the 2023 GRC cycle. The purpose of this program is a continuing effort to replace aging infrastructure. The recorded values were lower that imputed due to increase in emergency replacements of failed equipment as described in the emergency work MWC 09F.
227 | Capital | Electric Distribution | 09 | E Dist Automation & Protection | 09E | ED Sub Protect Relay Inst/Repl | Distribution Overhead | DOVHD-C007: Supervisory Control and Data Acquisition | Ex 4, Ch 16 | No | N/A | N/A | 3032.8639 | 3167.492 | 6200.3559 | 226.3845 | 2520.3042 | 2746.6887 | -647.1878 | -3453.6672 | -20.43% | -55.7% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
228 | Capital | Electric Distribution | 09 | E Dist Automation & Protection | 09F | ED Sub SCADA Emergency Repl | SRM Total | SRM Total | Ex 4, Ch 16 | No | On-going | Annual | 5970.5152 | 6210.1309 | 12180.6461 | 11181.4725 | 11110.7664 | 22292.2389 | 4900.6355 | 10111.5928 | 78.91% | 83.01% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | This program has no end date and will continue through the remainder of the 2023 GRC cycle. PG&E's recorded amount is higher than the imputed due to an increase is equipment failure higher than the 3-year average used to develop the forecast.
229 | Capital | Electric Distribution | 09 | E Dist Automation & Protection | 09F | ED Sub SCADA Emergency Repl | Distribution Overhead | DOVHD-C007: Supervisory Control and Data Acquisition | Ex 4, Ch 16 | No | N/A | N/A | 5970.5152 | 6210.1309 | 12180.6461 | 11181.4725 | 11110.7664 | 22292.2389 | 4900.6355 | 10111.5928 | 78.91% | 83.01% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
230 | Capital | Electric Distribution | 17 | E Dist Routine Emergency | N/A | Not assigned | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 6 | No | On-going | Annual | 249483.0313 | 260557.5273 | 510040.5587 | 395409.8326 | 480188.8797 | 875598.7123 | 219631.3524 | 365558.1537 | 84.29% | 71.67% | YES | YES | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Program expenditures exceeded imputed regulatory values due to higher than forecast volume of emergency events, driving higher overall contract spend, over head costs, and higher labor charges. | N/A | Over | Over | Over | Emergent | This program's work is ongoing and will continue in PG&E's 2023 GRC period. This is a demand driven program. The purpose of this program is to address routine emergencies and conditions in the field that require immediate attention. PG&E expects to continue to spend more on this program than forecasted.
231 | Capital | Electric Distribution | 21 | Misc Capital | N/A | Not assigned | SRM Total | SRM Total | Ex 4, Ch 4.1 Ex 4, Ch 4.2 Ex 4, Ch 4.3 Ex 4, Ch 5 Ex 4, Ch 20-22 | No | On-going | Annual | 28274.9198 | 29475.8313 | 57750.7511 | 33687.5719 | 40138.2776 | 73825.8494 | 10662.4463 | 16075.0983 | 36.17% | 27.84% | NO | YES | # weather stations | 150 | 150 | 300 | 102 | 50 | 152 | -100 | -148 | -66.67% | -49.33% | YES | Program expenditures exceeded imputed regulatory values due to increases in environmental and federal permitting costs since forecasted in the 2023 GRC. Lower costs for EP&R and the Sensor IQ program, which has been discontinued, was off-set by 1) costs for wildfire risk model development which were not forecasted in the 2023 GRC; and 2) new budgeting, forecasting for integrated grid planning (IGP) systems. | Actual units were lower than imputed units due to two factors: 1) through 2022, weather stations were installed ahead of plan allowing for a scale back of program units in 2024; 2) and costs for environmental and federal land permitting has increased since the GRC was forecasted; therefore fewer program units were completed for the costs allocated. | Under | On-Target | Over | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is for various capital activities that enable electric operations. This program includes costs for activities like the Emergency Operating Centers (EOCs), facilities upgrades, IT enhancements, and Applied Technology Services (ATS) lab safety and upgrades. For the remainder of the GRC cycle this program will proceed with some program costs being lower, off-set by some being higher than forecasted.
232 | Capital | Electric Distribution | 21 | Misc Capital | N/A | Not assigned | Emergency Preparedness & Response | EPNDR-C000: EP&R Controls | Ex 4, Ch 4.1 Ex 4, Ch 4.2 Ex 4, Ch 4.3 Ex 4, Ch 5 Ex 4, Ch 20-22 | Yes | N/A | N/A | 0 | 0 | 0 | 0 | 2427.2369 | 2427.2369 | 2427.2369 | 2427.2369 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
233 | Capital | Electric Distribution | 21 | Misc Capital | N/A | Not assigned | Emergency Preparedness & Response | EPNDR-C002: Situational Awareness and Forecasting Initiatives - WSOC | Ex 4, Ch 4.1 Ex 4, Ch 4.2 Ex 4, Ch 4.3 Ex 4, Ch 5 Ex 4, Ch 20-22 | Yes | N/A | N/A | 113.14 | 118.1621 | 231.3021 | 21.2327 | -88.4717 | -67.2391 | -206.6338 | -298.5411 | -174.9% | -129.1% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
234 | Capital | Electric Distribution | 21 | Misc Capital | N/A | Not assigned | Emergency Preparedness & Response | EPNDR-C004: EP&R Field Operations Technology | Ex 4, Ch 4.1 Ex 4, Ch 4.2 Ex 4, Ch 4.3 Ex 4, Ch 5 Ex 4, Ch 20-22 | Yes | N/A | N/A | 3582.896 | 3726.6888 | 7309.5848 | 1471.8155 | 0 | 1471.8155 | -3726.6888 | -5837.7693 | -100% | -79.86% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
235 | Capital | Electric Distribution | 21 | Misc Capital | N/A | Not assigned | Emergency Preparedness & Response | EPNDR-M000: EP&R Mitigations | Ex 4, Ch 4.1 Ex 4, Ch 4.2 Ex 4, Ch 4.3 Ex 4, Ch 5 Ex 4, Ch 20-22 | Yes | N/A | N/A | 2235.569 | 2334.8052 | 4570.3742 | 4574.6291 | 1985.9211 | 6560.5502 | -348.8841 | 1990.176 | -14.94% | 43.55% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
236 | Capital | Electric Distribution | 21 | Misc Capital | N/A | Not assigned | Distribution Overhead | DOVHD-M002: System Hardening | Ex 4, Ch 4.1 Ex 4, Ch 4.2 Ex 4, Ch 4.3 Ex 4, Ch 5 Ex 4, Ch 20-22 | No | N/A | N/A | 0 | 0 | 0 | 0 | 2906.4889 | 2906.4889 | 2906.4889 | 2906.4889 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
237 | Capital | Electric Distribution | 21 | Misc Capital | N/A | Not assigned | Wildfire | WLDFR-M002: System Hardening | Ex 4, Ch 4.1 Ex 4, Ch 4.2 Ex 4, Ch 4.3 Ex 4, Ch 5 Ex 4, Ch 20-22 | Yes | N/A | N/A | 0 | 0 | 0 | 0 | 2906.4889 | 2906.4889 | 2906.4889 | 2906.4889 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
238 | Capital | Electric Distribution | 21 | Misc Capital | N/A | Not assigned | Wildfire | WLDFR-M006: PSPS Reduction Initiatives | Ex 4, Ch 4.1 Ex 4, Ch 4.2 Ex 4, Ch 4.3 Ex 4, Ch 5 Ex 4, Ch 20-22 | Yes | N/A | N/A | 276.9734 | 289.2665 | 566.2399 | 4.9574 | 3.0238 | 7.9812 | -286.2427 | -558.2587 | -98.95% | -98.59% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
239 | Capital | Electric Distribution | 21 | Misc Capital | N/A | Not assigned | Wildfire | WLDFR-M07B: Situational Awareness and Forecasting Initiatives - Weather Station | Ex 4, Ch 4.1 Ex 4, Ch 4.2 Ex 4, Ch 4.3 Ex 4, Ch 5 Ex 4, Ch 20-22 | Yes | N/A | N/A | 3587.1379 | 3731.0793 | 7318.2172 | 3955.822 | 1991.0631 | 5946.8851 | -1740.0162 | -1371.3321 | -46.64% | -18.74% | N/A | N/A | # weather stations | 150 | 150 | 300 | 102 | 50 | 152 | -100 | -148 | -66.67% | -49.33% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
240 | Capital | Electric Distribution | 21 | Misc Capital | N/A | Not assigned | Wildfire | WLDFR-M07F: Situational Awareness and Forecasting Initiatives - Sensor IQ | Ex 4, Ch 4.1 Ex 4, Ch 4.2 Ex 4, Ch 4.3 Ex 4, Ch 5 Ex 4, Ch 20-22 | Yes | N/A | N/A | 11118.9587 | 11612 | 22730.9587 | -0.00012 | 0 | -0.00012 | -11612 | -22730.9588 | -100% | -100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
241 | Capital | Electric Distribution | 21 | Misc Capital | N/A | Not assigned | Wildfire | WLDFR-M07G: Situational Awareness and Forecasting Initiatives - Partial Voltage Detection | Ex 4, Ch 4.1 Ex 4, Ch 4.2 Ex 4, Ch 4.3 Ex 4, Ch 5 Ex 4, Ch 20-22 | Yes | N/A | N/A | 0 | 0 | 0 | 0.1292 | 0 | 0.1292 | 0 | 0.1292 | 0% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
242 | Capital | Electric Distribution | 21 | Misc Capital | N/A | Not assigned | Wildfire | WLDFR-M07J: Situational Awareness and Forecasting Initiatives - Meteorology | Ex 4, Ch 4.1 Ex 4, Ch 4.2 Ex 4, Ch 4.3 Ex 4, Ch 5 Ex 4, Ch 20-22 | Yes | N/A | N/A | 1187.7069 | 1235.3662 | 2423.0731 | 904.3723 | 2609.1909 | 3513.5631 | 1373.8247 | 1090.49 | 111.2% | 45% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
243 | Capital | Electric Distribution | 21 | Misc Capital | N/A | Not assigned | Wildfire | WLDFR-M008: Safety and Infrastructure Protection Teams | Ex 4, Ch 4.1 Ex 4, Ch 4.2 Ex 4, Ch 4.3 Ex 4, Ch 5 Ex 4, Ch 20-22 | Yes | N/A | N/A | 262.2296 | 273.8683 | 536.0979 | 6.1137 | 224.0285 | 230.1422 | -49.8398 | -305.9558 | -18.2% | -57.07% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
244 | Capital | Electric Distribution | 21 | Misc Capital | N/A | Not assigned | Wildfire | WLDFR-M009: Community Wildfire Safety Program PMO | Ex 4, Ch 4.1 Ex 4, Ch 4.2 Ex 4, Ch 4.3 Ex 4, Ch 5 Ex 4, Ch 20-22 | Yes | N/A | N/A | 0 | 0 | 0 | 12915.1254 | 6503.9591 | 19419.0845 | 6503.9591 | 19419.0845 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
245 | Capital | Electric Distribution | 21 | Misc Capital | N/A | Not assigned | Wildfire | WLDFR-M017: System Hardening - Remote Grid | Ex 4, Ch 4.1 Ex 4, Ch 4.2 Ex 4, Ch 4.3 Ex 4, Ch 5 Ex 4, Ch 20-22 | Yes | N/A | N/A | 0 | 0 | 0 | 4538.5339 | 1614.6187 | 6153.1526 | 1614.6187 | 6153.1526 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
246 | Capital | Electric Distribution | 21 | Misc Capital | N/A | Not assigned | Wildfire | WLDFR-M020: Enhanced Powerline Safety Settings | Ex 4, Ch 4.1 Ex 4, Ch 4.2 Ex 4, Ch 4.3 Ex 4, Ch 5 Ex 4, Ch 20-22 | Yes | N/A | N/A | 0 | 0 | 0 | 0 | 2282.2344 | 2282.2344 | 2282.2344 | 2282.2344 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
247 | Capital | Electric Distribution | 21 | Misc Capital | N/A | Not assigned | Wildfire | POST-GRC: Post 2023 GRC Mitigation | Ex 4, Ch 4.1 Ex 4, Ch 4.2 Ex 4, Ch 4.3 Ex 4, Ch 5 Ex 4, Ch 20-22 | Yes | N/A | N/A | 0 | 0 | 0 | 0 | 1627.5547 | 1627.5547 | 1627.5547 | 1627.5547 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
248 | Capital | Electric Distribution | 21 | Misc Capital | N/A | Not assigned | SRM (NON-RAMP) | SRM (NON-RAMP) | Ex 4, Ch 4.1 Ex 4, Ch 4.2 Ex 4, Ch 4.3 Ex 4, Ch 5 Ex 4, Ch 20-22 | Yes | N/A | N/A | 5910.309 | 6154.1363 | 12064.4453 | 5294.8408 | 16051.4292 | 21346.27 | 9897.2929 | 9281.8247 | 160.8% | 76.94% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
249 | Capital | Electric Distribution | 25 | Install New Electric Meters | N/A | Not assigned | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 8 | No | On-going | Annual | 31396.1237 | 32789.7907 | 64185.9144 | 30468.9532 | 31179.4303 | 61648.3836 | -1610.3603 | -2537.5308 | -4.911% | -3.953% | NO | NO | # of Field Orders | 129889.51 | 129889.5111 | 259779.0211 | 142998 | 151935 | 294933 | 22045.4889 | 35153.9789 | 16.97% | 13.53% | NO | Below variance threshold. | Below variance threshold | On-Target | On-Target | On-Target | Proceeding as Planned | This program has no end date and will continue through the remainder of the 2023 GRC cycle. The purpose of this program is a continuing effort to perform electric meter installations, exchanges, and removals at customer locations.
250 | Capital | Electric Distribution | 2A | E Dist Inst/Repl OH General | 2AA | OH Genl Repl | SRM Total | SRM Total | Ex 4, Ch 11 | No | On-going | Annual | 138779.5103 | 144939.9018 | 283719.4121 | 291909.6035 | 252206.6457 | 544116.2492 | 107266.7439 | 260396.8371 | 74.01% | 91.78% | YES | YES | # notifications | 19547.77 | 19547.7738 | 39095.5438 | 20136 | 17825 | 37961 | -1722.7738 | -1134.5438 | -8.813% | -2.902% | NO | Program expenditures exceeded imputed regulatory values due to higher unit costs than adopted in the 2023 GRC Final Decision. | Below variance threshold | On-Target | On-Target | Over | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of the program is to replace deteriorated overhead facilities that are not an imminent hazard. PG&E will continue to prioritize this work throughout the 2023 GRC cycle to meet WMP commitments. PG&E anticipates the program scope will remain on target and spending will remain higher than imputed over the remainder of the cycle, due to higher unit costs than the GRC imputed adopted unit costs and higher volumes to address the maintenance log.
251 | Capital | Electric Distribution | 2A | E Dist Inst/Repl OH General | 2AA | OH Genl Repl | Distribution Overhead | DOVHD-C003: Equipment Maintenance and Replacement - Distribution Overhead | Ex 4, Ch 11 | No | N/A | N/A | 138779.5103 | 144939.9018 | 283719.4121 | 291909.6035 | 252206.6457 | 544116.2492 | 107266.7439 | 260396.8371 | 74.01% | 91.78% | N/A | N/A | # notifications | 19547.77 | 19547.7738 | 39095.5438 | 20136 | 17825 | 37961 | -1722.7738 | -1134.5438 | -8.813% | -2.902% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
252 | Capital | Electric Distribution | 2A | E Dist Inst/Repl OH General | 2AA | OH Genl Repl | Wildfire | WLDFR-C008: Equipment Maintenance and Replacement - Distribution Overhead | Ex 4, Ch 11 | No | N/A | N/A | 138779.5103 | 144939.9018 | 283719.4121 | 291909.6035 | 252206.6457 | 544116.2492 | 107266.7439 | 260396.8371 | 74.01% | 91.78% | N/A | N/A | # notifications | 19547.77 | 19547.7738 | 39095.5438 | 20136 | 17825 | 37961 | -1722.7738 | -1134.5438 | -8.813% | -2.902% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
253 | Capital | Electric Distribution | 2A | E Dist Inst/Repl OH General | 2AB | Bird Safe Inst/Repl | SRM Total | SRM Total | Ex 4, Ch 11 | No | On-going | Annual | 3623.2476 | 3784.0828 | 7407.3304 | 2018.6656 | 1430.9482 | 3449.6138 | -2353.1346 | -3957.7166 | -62.19% | -53.43% | NO | NO | # notifications | 967 | 966.7397 | 1933.7397 | 407 | 354 | 761 | -612.7397 | -1172.7397 | -63.38% | -60.65% | YES | Below variance threshold. | Actual units were lower than imputed units because there was a lower occurrence of bird-safety incidents and associated notifications for this program in 2024. | Under | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of the program is to perform capital modifications to bird-safe incident and/or adjacent poles in response to a bird electrocution, per US Fish and Wildlife Services (USFWS) requirements and utility operating standard S2321. Spending in this program is based on volume of bird-safe incidents and the prioritization of tags within the 2A MWC.
254 | Capital | Electric Distribution | 2A | E Dist Inst/Repl OH General | 2AB | Bird Safe Inst/Repl | Distribution Overhead | DOVHD-C003: Equipment Maintenance and Replacement - Distribution Overhead | Ex 4, Ch 11 | No | N/A | N/A | 3623.2476 | 3784.0828 | 7407.3304 | 2018.6656 | 1430.9482 | 3449.6138 | -2353.1346 | -3957.7166 | -62.19% | -53.43% | N/A | N/A | # notifications | 967 | 966.7397 | 1933.7397 | 407 | 354 | 761 | -612.7397 | -1172.7397 | -63.38% | -60.65% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
255 | Capital | Electric Distribution | 2A | E Dist Inst/Repl OH General | 2AB | Bird Safe Inst/Repl | Wildfire | WLDFR-C011: Animal Abatement | Ex 4, Ch 11 | No | N/A | N/A | 3623.2476 | 3784.0828 | 7407.3304 | 2018.6656 | 1430.9482 | 3449.6138 | -2353.1346 | -3957.7166 | -62.19% | -53.43% | N/A | N/A | # notifications | 967 | 966.7397 | 1933.7397 | 407 | 354 | 761 | -612.7397 | -1172.7397 | -63.38% | -60.65% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
256 | Capital | Electric Distribution | 2A | E Dist Inst/Repl OH General | 2AC | Bird Safe Inst/Repl Annual | SRM Total | SRM Total | Ex 4, Ch 11 | No | On-going | Annual | 3770.4302 | 3937.7988 | 7708.2291 | 1728.3523 | 5142.0416 | 6870.3939 | 1204.2428 | -837.8352 | 30.58% | -10.87% | NO | NO | # notifications | 977.7 | 977.6961 | 1955.3961 | 296 | 879 | 1175 | -98.6961 | -780.3961 | -10.09% | -39.91% | NO | Below variance threshold. | Below variance threshold | On-Target | On-Target | On-Target | Proceeding as Planned | This program is ongoing. The purpose of this program is to perform capital work as part of an annual pole retrofit program to prevent bird electrocutions, per US Fish and Wildlife Services (USFWS) requirements and utility operating standard.
257 | Capital | Electric Distribution | 2A | E Dist Inst/Repl OH General | 2AC | Bird Safe Inst/Repl Annual | Wildfire | WLDFR-C011: Animal Abatement | Ex 4, Ch 11 | No | N/A | N/A | 3770.4302 | 3937.7988 | 7708.2291 | 1728.3523 | 5142.0416 | 6870.3939 | 1204.2428 | -837.8352 | 30.58% | -10.87% | N/A | N/A | # notifications | 977.7 | 977.6961 | 1955.3961 | 296 | 879 | 1175 | -98.6961 | -780.3961 | -10.09% | -39.91% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
258 | Capital | Electric Distribution | 2A | E Dist Inst/Repl OH General | 2AE | OH COE Repl | SRM Total | SRM Total | Ex 4, Ch 11 | No | On-going | Annual | 29330.0649 | 30632.02 | 59962.0849 | 65524.2854 | 68336.649 | 133860.9344 | 37704.629 | 73898.8495 | 123.1% | 123.2% | YES | YES | # of Notifications Completed | 822.85 | 822.848 | 1645.698 | 1031 | 1050 | 2081 | 227.152 | 435.302 | 27.61% | 26.45% | YES | Program expenditures exceeded imputed regulatory values due to the higher volume of tags completed, increased unit costs, and increased costs associated with the types of facilities addressed in 2024. | Actual units were higher than imputed units because PG&E needed to complete more program units to improve customer reliability and prevent outages. | Over | On-Target | Over | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to identify equipment (through failure/inspections) that impacts the reliability of system operations. Spending in this program is based on find rates and the prioritization of tags within the MWC 2A.
259 | Capital | Electric Distribution | 2A | E Dist Inst/Repl OH General | 2AE | OH COE Repl | Distribution Overhead | DOVHD-C003: Equipment Maintenance and Replacement - Distribution Overhead | Ex 4, Ch 11 | No | N/A | N/A | 29330.0649 | 30632.02 | 59962.0849 | 65524.2854 | 68336.649 | 133860.9344 | 37704.629 | 73898.8495 | 123.1% | 123.2% | N/A | N/A | # of Notifications Completed | 822.85 | 822.848 | 1645.698 | 1031 | 1050 | 2081 | 227.152 | 435.302 | 27.61% | 26.45% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
260 | Capital | Electric Distribution | 2A | E Dist Inst/Repl OH General | 2AF | OH Idle Facility Remove | SRM Total | SRM Total | Ex 4, Ch 11 | No | On-going | Annual | 2843.6999 | 2969.9311 | 5813.631 | 9538.3149 | 16500.6034 | 26038.9182 | 13530.6723 | 20225.2873 | 455.6% | 347.9% | NO | YES | # facilities | 322.86 | 322.861 | 645.721 | 1005 | 1877 | 2882 | 1554.139 | 2236.279 | 481.4% | 346.3% | YES | Program expenditures exceeded imputed regulatory values due to higher volume of idle faculties identified for removal combined with the mix in the scope of the work/type of facility removed. | Actual units were higher than imputed units because of the volume of idle facilities identified and PG&E's commitment to wildfire mitigation; more program units were completed to mitigate fire risk and reduce system hazards. | Over | On-Target | Over | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to identify overhead idle facilities through investigations and take appropriate remedial measures. In the 2023 GRC cycle, PG&E expects to continue to complete more units than imputed as idle facility removals are an important wildfire mitigation.
261 | Capital | Electric Distribution | 2A | E Dist Inst/Repl OH General | 2AF | OH Idle Facility Remove | Distribution Overhead | DOVHD-C003: Equipment Maintenance and Replacement - Distribution Overhead | Ex 4, Ch 11 | No | N/A | N/A | 2843.6999 | 2969.9311 | 5813.631 | 9538.3149 | 16500.6034 | 26038.9182 | 13530.6723 | 20225.2873 | 455.6% | 347.9% | N/A | N/A | # facilities | 322.86 | 322.861 | 645.721 | 1005 | 1877 | 2882 | 1554.139 | 2236.279 | 481.4% | 346.3% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
262 | Capital | Electric Distribution | 2A | E Dist Inst/Repl OH General | 2AF | OH Idle Facility Remove | Wildfire | WLDFR-C008: Equipment Maintenance and Replacement - Distribution Overhead | Ex 4, Ch 11 | No | N/A | N/A | 2843.6999 | 2969.9311 | 5813.631 | 9538.3149 | 16500.6034 | 26038.9182 | 13530.6723 | 20225.2873 | 455.6% | 347.9% | N/A | N/A | # facilities | 322.86 | 322.861 | 645.721 | 1005 | 1877 | 2882 | 1554.139 | 2236.279 | 481.4% | 346.3% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
263 | Capital | Electric Distribution | 2A | E Dist Inst/Repl OH General | 2AG | SF Series Streetlights | SRM Total | SRM Total | Ex 4, Ch 11 | No | 12 | 11 | 2594.9448 | 2710.1338 | 5305.0786 | 280.8016 | 302.2637 | 583.0653 | -2407.8701 | -4722.0133 | -88.85% | -89.01% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period as the remaining streetlights are changed out. This program replaces regulated output (“RO”) streetlights, also referred to as constant current streetlight systems, in San Francisco.
264 | Capital | Electric Distribution | 2A | E Dist Inst/Repl OH General | 2AG | SF Series Streetlights | Distribution Overhead | DOVHD-M007: Regulated Output Streetlight Replacement | Ex 4, Ch 11 | No | 12 | 11 | 2594.9448 | 2710.1338 | 5305.0786 | 280.8016 | 302.2637 | 583.0653 | -2407.8701 | -4722.0133 | -88.85% | -89.01% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
265 | Capital | Electric Distribution | 2A | E Dist Inst/Repl OH General | 2AH | LED Streetlights | SRM Total | SRM Total | Ex 4, Ch 11 | No | On-going | Annual | 7379.7059 | 7707.2894 | 15086.9952 | 608.8757 | 1706.5052 | 2315.3809 | -6000.7842 | -12771.6143 | -77.86% | -84.65% | NO | NO | # of Streetlights | 8000 | 8000 | 16000 | 392 | 1130 | 1522 | -6870 | -14478 | -85.88% | -90.49% | YES | Below variance threshold. | Actual units were lower than imputed units because wildfire risk mitigation work in HFTD was prioritized and the work in this MAT code shifted to higher unit cost items (decorative pole replacements) due to the lower cost items (Cobrahead replacement) being completed. | Under | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to replace PG&E's LS-1 streetlights with Light Emitting Diode (LED) fixtures and new photocells. The vast majority of fixtures remaining to be converted are decorative (LS-1D).
266 | Capital | Electric Distribution | 2A | E Dist Inst/Repl OH General | 2AH | LED Streetlights | Distribution Overhead | DOVHD-C003: Equipment Maintenance and Replacement - Distribution Overhead | Ex 4, Ch 11 | No | N/A | N/A | 7379.7059 | 7707.2894 | 15086.9952 | 608.8757 | 1706.5052 | 2315.3809 | -6000.7842 | -12771.6143 | -77.86% | -84.65% | N/A | N/A | # of Streetlights | 8000 | 8000 | 16000 | 392 | 1130 | 1522 | -6870 | -14478 | -85.88% | -90.49% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
267 | Capital | Electric Distribution | 2A | E Dist Inst/Repl OH General | 2AI | SF Historical Streetlights | SRM Total | SRM Total | Ex 4, Ch 11 | No | On-going | Annual | 1037.9781 | 1084.0537 | 2122.0319 | 8.006 | -1.1603 | 6.8457 | -1085.214 | -2115.1862 | -100.1% | -99.68% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Rescheduled | The high priority poles identified during the comprehensive inspection program as needing refurbishment or replacement were addressed between 2019-2022, earlier than expected. Currently, the program is expected to continue to refurbish or replace poles as identified by inspection results in a future round of comprehensive inspections.
268 | Capital | Electric Distribution | 2A | E Dist Inst/Repl OH General | 2AI | SF Historical Streetlights | Distribution Overhead | DOVHD-C003: Equipment Maintenance and Replacement - Distribution Overhead | Ex 4, Ch 11 | No | N/A | N/A | 1037.9781 | 1084.0537 | 2122.0319 | 8.006 | -1.1603 | 6.8457 | -1085.214 | -2115.1862 | -100.1% | -99.68% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
269 | Capital | Electric Distribution | 2A | E Dist Inst/Repl OH General | 2AJ | CWSP Non-Exempt Fuse Replacement | SRM Total | SRM Total | Ex 4, Ch 11 Ex 4, Ch 4.3 | No | On-going | Annual | 0 | 0 | 0 | 18271.0254 | 0 | 18271.0254 | 0 | 18271.0254 | 0% | 100% | NO | NO | # replacements | 0 | 0 | 0 | 3114 | 0 | 3114 | 0 | 3114 | 0% | 100% | NO | Below variance threshold. | Below variance threshold | On-Target | On-Target | Over | Proceeding as Planned | This program was reflected in MAT 2AP imputed adopted costs for the 2023 GRC cycle, but recorded to MAT 2AJ in 2023 and 3UT in 2024. The non-exempt fuse replacement program data can be found under the new MAT 3UT.
270 | Capital | Electric Distribution | 2A | E Dist Inst/Repl OH General | 2AJ | CWSP Non-Exempt Fuse Replacement | Distribution Overhead | DOVHD-M004: Expulsion Fuse Replacement | Ex 4, Ch 11 Ex 4, Ch 4.3 | No | N/A | N/A | 0 | 0 | 0 | 18271.0254 | 0 | 18271.0254 | 0 | 18271.0254 | 0% | 100% | N/A | N/A | # replacements | 0 | 0 | 0 | 3114 | 0 | 3114 | 0 | 3114 | 0% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
271 | Capital | Electric Distribution | 2A | E Dist Inst/Repl OH General | 2AJ | CWSP Non-Exempt Fuse Replacement | Wildfire | WLDFR-M004: Expulsion Fuse Replacement | Ex 4, Ch 11 Ex 4, Ch 4.3 | No | N/A | N/A | 0 | 0 | 0 | 18271.0254 | 0 | 18271.0254 | 0 | 18271.0254 | 0% | 100% | N/A | N/A | # replacements | 0 | 0 | 0 | 3114 | 0 | 3114 | 0 | 3114 | 0% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
272 | Capital | Electric Distribution | 2A | E Dist Inst/Repl OH General | 2AP | OH CAP Projects | SRM Total | SRM Total | Ex 4, Ch 11 Ex 4, Ch 4.3 | No | On-going | Annual | 17835.374 | 18627.0823 | 36462.4563 | 1808.121 | 1967.2188 | 3775.3398 | -16659.8635 | -32687.1165 | -89.44% | -89.65% | NO | YES | # of Locations | 1186.03 | 1186.03 | 2372.06 | 0 | 0 | 0 | -1186.03 | -2372.06 | -100% | -100% | YES | Program expenditures were below imputed adopted costs because the imputed adopted costs for MAT 2AP in 2024 ($18,627) included imputed adopted costs for replacing non-exempt fuses ($17, 495). The actual costs for replacing non-exempt fuses were recorded under MAT 2AJ in 2023 and MAT 3UT in 2024. If the 2024 actual costs for replacing non-exempt fuses recorded in MAT 3UT ($16,932) were recorded to MAT 2AP in 2024, MAT 2AP actual costs would be in line with the imputed adopted costs for 2024. | Actual units were lower than imputed units because recorded costs and units for this program are now tracked in MAT 3UT for the Wildfire and Distribution Overhead mitigations. The remaining non-RAMP portion of this program is not unitized because it is project based work that varies in volume, scope, and costs. | Under | On-Target | Under | Proceeding as Planned | For the reminder of the 2023 GRC cycle, PG&E will continue to record only project based work in MAT 2AP. MAT 2AP will no longer be unitized as project based work varies in volume, scope and costs and has no meaningful units of measure. Costs and units for the wildfire and distribution overhead mitigations were recorded in MAT 2AJ in 2023 and finally in 3UT starting in 2024. PG&E plans to record costs and units for the mitigation in MAT 3UT for the remainder of the GRC cycle.
273 | Capital | Electric Distribution | 2A | E Dist Inst/Repl OH General | 2AP | OH CAP Projects | Distribution Overhead | DOVHD-M004: Expulsion Fuse Replacement | Ex 4, Ch 11 Ex 4, Ch 4.3 | Yes | N/A | N/A | 16635.8756 | 17374.3384 | 34010.2141 | 1808.121 | 1967.2188 | 3775.3398 | -15407.1 | -30234.9 | -88.7% | -88.9% | N/A | N/A | # of Locations | 1186.03 | 1186.03 | 2372.06 | 0 | 0 | 0 | -1186.03 | -2372.06 | -100% | -100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
274 | Capital | Electric Distribution | 2A | E Dist Inst/Repl OH General | 2AP | OH CAP Projects | Wildfire | WLDFR-M004: Expulsion Fuse Replacement | Ex 4, Ch 11 Ex 4, Ch 4.3 | Yes | N/A | N/A | 16635.8756 | 17374.3384 | 34010.2141 | 1808.121 | 1967.2188 | 3775.3398 | -15407.1 | -30234.9 | -88.7% | -88.9% | N/A | N/A | # of Locations | 1186.03 | 1186.03 | 2372.06 | 0 | 0 | 0 | -1186.03 | -2372.06 | -100% | -100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
275 | Capital | Electric Distribution | 2A | E Dist Inst/Repl OH General | 2AP | OH CAP Projects | SRM (NON-RAMP) | SRM (NON-RAMP) | Ex 4, Ch 11 Ex 4, Ch 4.3 | Yes | N/A | N/A | 1199.4984 | 1252.7439 | 2452.2423 | 0 | 0 | 0 | 0 | 0 | -100% | -100% | N/A | N/A | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
276 | Capital | Electric Distribution | 2A | E Dist Inst/Repl OH General | 2AQ | Ceramic Post Insulators | SRM Total | SRM Total | Ex 4, Ch 11 | No | On-going | Annual | 6071.0807 | 6340.5746 | 12411.6553 | -8.7619 | 0 | -8.7619 | -6340.5746 | -12420.4172 | -100% | -100.1% | NO | NO | # of Ceramic Post Insulators Replaced | 2092.57 | 2092.5679 | 4185.1379 | 0 | 0 | 0 | -2092.5679 | -4185.1379 | -100% | -100% | YES | Below variance threshold. | Actual units were lower than imputed units due to the bundling of ceramic post insulator replacements with cross-arm replacements recorded in MAT Code 2AA. The majority of locations with old ceramic post insulators also have deteriorated cross-arms that are replaced under one maintenance tag. As a result, the recording of individual ceramic post insulators is no longer captured. | Under | Under | Under | Canceled | This program's work is the replacement of ceramic post insulators that were manufactured in or prior to 1972 and are currently installed on PG&E poles and cross-arms. These ceramic post insulators are addressed proactively during pole and crossarm replacements and a dedicated program is no longer needed to support the insulator replacements. This replacement work is bundled with pole and cross-arm replacements, and will continue through the 2023 GRC cycle.
277 | Capital | Electric Distribution | 2A | E Dist Inst/Repl OH General | 2AQ | Ceramic Post Insulators | Distribution Overhead | DOVHD-M008: Ceramic Post Insulator Replacement | Ex 4, Ch 11 | No | N/A | N/A | 6071.0807 | 6340.5746 | 12411.6553 | -8.7619 | 0 | -8.7619 | -6340.5746 | -12420.4172 | -100% | -100.1% | N/A | N/A | # of Ceramic Post Insulators Replaced | 2092.57 | 2092.5679 | 4185.1379 | 0 | 0 | 0 | -2092.5679 | -4185.1379 | -100% | -100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
278 | Capital | Electric Distribution | 2A | E Dist Inst/Repl OH General | 2AR | Surge Arrester Replacement | SRM Total | SRM Total | Ex 4, Ch 11 | No | On-going | Annual | 18522.9745 | 19345.2052 | 37868.1796 | 5194.563 | 7643.3056 | 12837.8686 | -11701.8996 | -25030.311 | -60.49% | -66.1% | NO | YES | # replacements | 3952.06 | 3952.0624 | 7904.1224 | 663 | 756 | 1419 | -3196.0624 | -6485.1224 | -80.87% | -82.05% | YES | Program expenditures were below imputed regulatory values in 2024 because PG&E met its 2023-2025 WMP target for surge arrestor removals in 2023. Actual costs in 2024 reflect completed remediation work on newly identified surge arrestors in 2024. | Actual units were lower than imputed units because PG&E met its WMP target for surge arrestor removal in 2023 and in 2024 work was limited to remediation work on newly identified surge arrestors. | Under | On-Target | Under | Proceeding as Planned | PG&E met its 2023‑2025 WMP target for surge arrestor removals in 2023 and completed remediation work on identified surge arrestors in 2024. However, some costs are forecasted in 2025 and 2026 for the mapping of constructed jobs from prior years, addressing QA findings, and closure of orders.
279 | Capital | Electric Distribution | 2A | E Dist Inst/Repl OH General | 2AR (k) | Surge Arrester Replacement | Distribution Overhead | DOVHD-M003: Non-Exempt Surge Arrester Replacement | Ex 4, Ch 11 | No | N/A | N/A | 18522.9745 | 19345.2052 | 37868.1796 | 5194.563 | 7643.3056 | 12837.8686 | -11701.8996 | -25030.311 | -60.49% | 33.9% | N/A | N/A | # replacements | 3952.06 | 3952.0624 | 7904.1224 | 663 | 756 | 1419 | -3196.0624 | -6485.1224 | -80.87% | -82.05% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
280 | Capital | Electric Distribution | 2A | E Dist Inst/Repl OH General | 2AR (k) | Surge Arrester Replacement | Wildfire | WLDFR-M003: Non-Exempt Surge Arrester Replacement | Ex 4, Ch 11 | No | N/A | N/A | 18522.9745 | 19345.2052 | 37868.1796 | 5194.563 | 7643.3056 | 12837.8686 | -11701.8996 | -25030.311 | -60.49% | -66.1% | N/A | N/A | # replacements | 3952.06 | 3952.0624 | 7904.1224 | 663 | 756 | 1419 | -3196.0624 | -6485.1224 | -80.87% | -82.05% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
281 | Capital | Electric Distribution | 2A | E Dist Inst/Repl OH General | 2AS | FAS Overhead Capital | SRM Total | SRM Total | Ex 4, Ch 11 | No | On-going | Annual | 865.3244 | 903.736 | 1769.0604 | 330.9953 | 301.1842 | 632.1795 | -602.5517 | -1136.8809 | -66.67% | -64.26% | NO | NO | # of Notifications Completed | 2624.75 | 2624.7529 | 5249.5029 | 0 | 0 | 0 | -2624.7529 | -5249.5029 | -100% | -100% | YES | Below variance threshold. | Actual units were lower than imputed units because this program is no longer recording actual units as the work is identified during a field job and completed by a single PG&E Troubleshooter. The work could involve either replacing or installing overhead facilities such as: electric distribution conductors, components, structures, and associated equipment constructed above ground level. As such there is no meaningful single unit of measure. | Under | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The program either replaces or installs overhead facilities identified during a field job and completed by a single PG&E Troubleshooter. The work could involve either replacing or installing overhead facilities such as: electric distribution conductors, components, structures, and associated equipment constructed above ground level.
282 | Capital | Electric Distribution | 2A | E Dist Inst/Repl OH General | 2AS | FAS Overhead Capital | Distribution Overhead | DOVHD-C003: Equipment Maintenance and Replacement - Distribution Overhead | Ex 4, Ch 11 | No | N/A | N/A | 865.3244 | 903.736 | 1769.0604 | 330.9953 | 301.1842 | 632.1795 | -602.5517 | -1136.8809 | -66.67% | -64.26% | N/A | N/A | # of Notifications Completed | 2624.75 | 2624.7529 | 5249.5029 | 0 | 0 | 0 | -2624.7529 | -5249.5029 | -100% | -100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
283 | Capital | Electric Distribution | 2A | E Dist Inst/Repl OH General | 2A# | Not assigned | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 11 | No | On-going | Annual | 0 | 0 | 0 | -90.1955 | 2192.1838 | 2101.9883 | 2192.1838 | 2101.9883 | 100% | 100% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | Over | Proceeding as Planned | MAT 2A# covers Standard Cost Variance (SCV) for the Electric Distribution Preventative Maintenance OH program. SCV is the difference between actual costs incurred and the amount charged out by employees at a pre-determined rate. PG&E does not forecast Standard Cost Variance.
284 | Capital | Electric Distribution | 2B | E Dist Inst/Repl UG | 2BA | UG Genl Repl | SRM Total | SRM Total | Ex 4, Ch 11 | No | On-going | Annual | 49864.3218 | 52077.7879 | 101942.1097 | 73659.2773 | 97293.0995 | 170952.3769 | 45215.3116 | 69010.2671 | 86.82% | 67.7% | YES | YES | # of Notifications Completed | 1816.54 | 1816.5422 | 3633.0822 | 2235 | N/A | 2235 | -1816.5422 | -1398.0822 | -100% | -38.48% | YES | Program expenditures exceeded imputed regulatory values due to higher than forecasted unit costs and the completion of a higher volume of units than forecasted, in addition to an increased spend in contract labor and material costs. | Actual units were lower than imputed units because more work was identified than forecasted. | Under | On-Target | Over | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to provide underground preventative maintenance for deteriorated facilities that are not an imminent hazard, and have not caused an outage. Facilities include transformers, conduit, enclosures, pads, and idle equipment.
285 | Capital | Electric Distribution | 2B | E Dist Inst/Repl UG | 2BA | UG Genl Repl | Underground | DUNGD-C003: Equipment Maintenance and Replacement | Ex 4, Ch 11 | No | N/A | N/A | 49864.3218 | 52077.7879 | 101942.1097 | 73659.2773 | 97293.0995 | 170952.3769 | 45215.3116 | 69010.2671 | 86.82% | 67.7% | N/A | N/A | # of Notifications Completed | 1816.54 | 1816.5422 | 3633.0822 | 2235 | 2861 | 5096 | 1044.4578 | 1462.9178 | 57.5% | 40.27% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
286 | Capital | Electric Distribution | 2B | E Dist Inst/Repl UG | 2BB | Fault Indicator Replacements | SRM Total | SRM Total | Ex 4, Ch 11 | No | On-going | Annual | 899.6593 | 939.5949 | 1839.2542 | 566.4909 | 484.6311 | 1051.1219 | -454.9639 | -788.1322 | -48.42% | -42.85% | NO | NO | # of Notifications Completed | 3238.2 | 3238.1975 | 6476.3975 | 2241 | N/A | 2241 | -3238.1975 | -4235.3975 | -100% | -65.4% | YES | Below variance threshold. | Actual units were lower than imputed units because fewer than expected Fault Indicators were identified as needing replacement during inspections. | Under | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is for the replacement of deteriorated fault indicators that are not an imminent hazard, and have not caused an outage. Spending in this program is based on inspection find rates.
287 | Capital | Electric Distribution | 2B | E Dist Inst/Repl UG | 2BB | Fault Indicator Replacements | Underground | DUNGD-C003: Equipment Maintenance and Replacement | Ex 4, Ch 11 | No | N/A | N/A | 899.6593 | 939.5949 | 1839.2542 | 566.4909 | 484.6311 | 1051.1219 | -454.9639 | -788.1322 | -48.42% | -42.85% | N/A | N/A | # of Notifications Completed | 3238.2 | 3238.1975 | 6476.3975 | 2241 | 1685 | 3926 | -1553.1975 | -2550.3975 | -47.96% | -39.38% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
288 | Capital | Electric Distribution | 2B | E Dist Inst/Repl UG | 2BD | UG COE Repl | SRM Total | SRM Total | Ex 4, Ch 11 | No | On-going | Annual | 7223.8884 | 7544.5552 | 14768.4435 | 9026.6331 | 9089.6097 | 18116.2427 | 1545.0545 | 3347.7992 | 20.48% | 22.67% | NO | NO | # of Tags Completed | 144 | 144 | 288 | 88 | 100 | 188 | -44 | -100 | -30.56% | -34.72% | YES | Below variance threshold. | Actual units were lower than imputed units because unit costs were above forecasted. In order to manage overall costs in the 2BD program, PG&E did fewer program units. | Under | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is the replacement of Underground Critical Operating Equipment (COE), which is equipment determined to be necessary for operations. COE is identified for replacement by the division operators, M&C, & restoration, and validated by Distribution Engineers based on damage and criticality to operations. For the GRC cycle, PG&E expects that it will continue to prioritize other work in MWC 2B over work in MAT 2BD. Going forward, PG&E may spend the imputed amount but anticipates completing fewer units than imputed due to the increase in unit costs.
289 | Capital | Electric Distribution | 2B | E Dist Inst/Repl UG | 2BD | UG COE Repl | Underground | DUNGD-C003: Equipment Maintenance and Replacement | Ex 4, Ch 11 | No | N/A | N/A | 7223.8884 | 7544.5552 | 14768.4435 | 9026.6331 | 9089.6097 | 18116.2427 | 1545.0545 | 3347.7992 | 20.48% | 22.67% | N/A | N/A | # of Tags Completed | 144 | 144 | 288 | 88 | 100 | 188 | -44 | -100 | -30.56% | -34.72% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
290 | Capital | Electric Distribution | 2B | E Dist Inst/Repl UG | 2BF | UG Idle Facility Remove | SRM Total | SRM Total | Ex 4, Ch 11 | No | On-going | Annual | 29.6349 | 30.9504 | 60.5853 | 317.2541 | 194.0678 | 511.3219 | 163.1174 | 450.7365 | 527% | 744% | NO | NO | # locations | 2 | 2 | 4 | 14 | N/A | 14 | -2 | 10 | -100% | 250% | YES | Below variance threshold. | Actual units were lower than imputed units because more idle facilities were identified for removal than forecasted. | Over | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is the removal of underground idle facilities deemed necessary for removal.
291 | Capital | Electric Distribution | 2B | E Dist Inst/Repl UG | 2BF | UG Idle Facility Remove | Underground | DUNGD-C005: UG Idle Facility Removal | Ex 4, Ch 11 | No | N/A | N/A | 29.6349 | 30.9504 | 60.5853 | 317.2541 | 194.0678 | 511.3219 | 163.1174 | 450.7365 | 527% | 744% | N/A | N/A | # locations | 2 | 2 | 4 | 14 | 6 | 20 | 4 | 16 | 200% | 400% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
292 | Capital | Electric Distribution | 2B | E Dist Inst/Repl UG | 2BP | UG CAP Projects | SRM Total | SRM Total | Ex 4, Ch 11 | No | On-going | Annual | 8456.6769 | 8832.0669 | 17288.7439 | 2988.0757 | 196.5628 | 3184.6385 | -8635.5041 | -14104.1054 | -97.77% | -81.58% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | This program has no end date and performs major project (underground) work that meets the financial threshold between $25,000 and $100,000. Completion of work is dependent on the scope of the project.
293 | Capital | Electric Distribution | 2B | E Dist Inst/Repl UG | 2BP | UG CAP Projects | Underground | DUNGD-C004: Planned Major Projects | Ex 4, Ch 11 | No | N/A | N/A | 8456.6769 | 8832.0669 | 17288.7439 | 2988.0757 | 196.5628 | 3184.6385 | -8635.5041 | -14104.1054 | -97.77% | -81.58% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
294 | Capital | Electric Distribution | 2B | E Dist Inst/Repl UG | 2B# | Not assigned | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 11 | No | On-going | Annual | 0 | 0 | 0 | 31.6759 | 890.1578 | 921.8337 | 890.1578 | 921.8337 | 100% | 100% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | Over | Proceeding as Planned | MAT 2B# covers Standard Cost Variance (SCV) for the Electric Distribution Preventative Maintenance UG program. SCV is the difference between actual costs incurred and the amount charged out by employees at a pre-determined rate. PG&E does not forecast Standard Cost Variance.
295 | Capital | Electric Distribution | 2C | E Dist Inst/Repl Network | 2CA | Network Misc | SRM Total | SRM Total | Ex 4, Ch 14 | No | On-going | Annual | 338.948 | 353.9938 | 692.9418 | 6.9008 | 3.4623 | 10.3631 | -350.5315 | -682.5787 | -99.02% | -98.5% | NO | NO | # relays replaced | 25 | 25 | 50 | 3 | N/A | 3 | -25 | -47 | -100% | -94% | YES | Below variance threshold. | Actual units were lower than imputed units due to priority relay replacements related to weather-related events which depleted inventory that could be used for MAT 2CA. In addition many of the failures of relays required the replacement of entire network protector units, which is recorded to MAT 2CC, resulting in fewer 2CA units. Relay installations and replacements are performed for both reliability (2CA), and in connection with emergency or weather-related events in other MWC like 17. | Under | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to replace network protector relays to maintain a safe and reliable distribution network system. Relay installations and replacements are performed for both reliability in MAT 2CA, and in connection with emergency or weather-related events in other programs, both of which are dependent of PG&E's available inventory. This is a defect demand-driven program.
296 | Capital | Electric Distribution | 2C | E Dist Inst/Repl Network | 2CA | Network Misc | Distribution Network | DNTWK-C003: Network Component Replacements - Condition Based | Ex 4, Ch 14 | No | N/A | N/A | 338.948 | 353.9938 | 692.9418 | 6.9008 | 3.4623 | 10.3631 | -350.5315 | -682.5787 | -99.02% | -98.5% | N/A | N/A | # relays replaced | 25 | 25 | 50 | 3 | 7 | 10 | -18 | -40 | -72% | -80% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
297 | Capital | Electric Distribution | 2C | E Dist Inst/Repl Network | 2CB | Fiber/SCADA Communication Repl | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 14 | No | On-going | Annual | 0 | 0 | 0 | 2.6261 | 1.4042 | 4.0303 | 1.4042 | 4.0303 | 100% | 100% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | Over | Proceeding as Planned | The SCADA communication replacements work has shifted from being recorded under this MAT code to Install/Replace Network MAT 2CE.
298 | Capital | Electric Distribution | 2C | E Dist Inst/Repl Network | 2CC | Transformer & Protector Repl | SRM Total | SRM Total | Ex 4, Ch 14 | No | On-going | Annual | 4057.4911 | 4237.6022 | 8295.0933 | 6051.3747 | 6809.8419 | 12861.2166 | 2572.2397 | 4566.1233 | 60.7% | 55.05% | NO | NO | # transformers/network protector replaced | 25 | 25 | 50 | 46 | 39 | 85 | 14 | 35 | 56% | 70% | YES | Below variance threshold. | Actual units were higher than imputed units due to an unexpected high volume of condition-based replacements due to adverse weather events and, as explained in MAT 2CA above, the failure of many relays requiring replacement of entire network protector units. | Over | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is a continuing effort to replace network transformers and protectors to maintain a safe and reliable distribution network system.
299 | Capital | Electric Distribution | 2C | E Dist Inst/Repl Network | 2CC | Transformer & Protector Repl | Distribution Network | DNTWK-C003: Network Component Replacements - Condition Based | Ex 4, Ch 14 | Yes | N/A | N/A | 1029.0203 | 1074.725 | 2103.7453 | 3206.279 | 6809.8419 | 10016.1209 | 5735.1169 | 7912.3756 | 533.6% | 376.1% | N/A | N/A | # transformers/network protector replaced | 2 | 2 | 4 | 27 | 39 | 66 | 37 | 62 | 1850% | 1550% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
300 | Capital | Electric Distribution | 2C | E Dist Inst/Repl Network | 2CC | Transformer & Protector Repl | Distribution Network | DNTWK-M005: Network Component Replacements - High-Rise Dry-Type Transformers | Ex 4, Ch 14 | Yes | N/A | N/A | 2799.75 | 2924 | 5723.75 | 2092.554 | 6809.8419 | 8902.3959 | 3885.8419 | 3178.6459 | 132.9% | 55.53% | N/A | N/A | # transformers/network protector replaced | 8 | 8 | 16 | 4 | 0 | 4 | -8 | -12 | -100% | -75% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
301 | Capital | Electric Distribution | 2C | E Dist Inst/Repl Network | 2CC | Transformer & Protector Repl | Distribution Network | DNTWK-M006: Network Component Replacements - Targeted Network Protector Replacements | Ex 4, Ch 14 | Yes | N/A | N/A | 228.6761 | 238.827 | 467.5031 | 752.542 | 0 | 752.542 | -238.827 | 285.0389 | -100% | 60.97% | N/A | N/A | # transformers/network protector replaced | 15 | 15 | 30 | 15 | 0 | 15 | -15 | -15 | -100% | -50% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
302 | Capital | Electric Distribution | 2C | E Dist Inst/Repl Network | 2CD | Venting Manhole Covers Repl | SRM Total | SRM Total | Ex 4, Ch 14 | No | On-going | Annual | 0 | 0 | 0 | 88.2583 | 9.3661 | 97.6244 | 9.3661 | 97.6244 | 100% | 100% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | Over | Proceeding as Planned | This program was completed for the network areas. Venting-manhole cover replacements will continue for non-Network locations under the 2BP program. The work is not canceled but PG&E is recording the work in those other MAT codes.
303 | Capital | Electric Distribution | 2C | E Dist Inst/Repl Network | 2CD | Venting Manhole Covers Repl | Distribution Network | DNTWK-M002: Venting Manhole Cover Replacements | Ex 4, Ch 14 | No | N/A | N/A | 0 | 0 | 0 | 88.2583 | 9.3661 | 97.6244 | 9.3661 | 97.6244 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
304 | Capital | Electric Distribution | 2C | E Dist Inst/Repl Network | 2CE | SCADA Communications Upgrade | SRM Total | SRM Total | Ex 4, Ch 14 | No | On-going | Annual | 9738.8839 | 10171.1908 | 19910.0748 | 9937.5503 | 9461.1168 | 19398.6672 | -710.074 | -511.4076 | -6.981% | -2.569% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | Over | Proceeding as Planned | This program has no end date. The purpose of this program is a continuing effort to upgrade the Distribution Network SCADA system to maintain a safe and reliable distribution network system. Starting in 2021, PG&E began recording SCADA communication replacements under 2CB under the 2CE program.
305 | Capital | Electric Distribution | 2C | E Dist Inst/Repl Network | 2CE | SCADA Communications Upgrade | Distribution Network | DNTWK-M003: Installation of SCADA Equipment for Safety Monitoring | Ex 4, Ch 14 | No | N/A | N/A | 9738.8839 | 10171.1908 | 19910.0748 | 9937.5503 | 9461.1168 | 19398.6672 | -710.074 | -511.4076 | -6.981% | -2.569% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
306 | Capital | Electric Distribution | 2C | E Dist Inst/Repl Network | 2C# | Not assigned | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 14 | No | On-going | Annual | 0 | 0 | 0 | -22.5286 | -109.4638 | -131.9924 | -109.4638 | -131.9924 | -100% | -100% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | Under | Proceeding as Planned | MAT 2C# covers Standard Cost Variance for the Electric Distribution Preventative Maintenance Network program. SCV is the difference between actual costs incurred and the amount charged out by employees at a predetermined rate. PG&E does not forecast Standard Cost Variance.
307 | Capital | Electric Distribution | 2F | Build IT Apps & Infra | N/A | Not assigned | SRM Total | SRM Total | Ex 4, Ch 4.5 Ex 4, Ch 20-21 | No | On-going | Annual | 70173.5 | 72989.7811 | 143163.2811 | 105258.7746 | 139198.3082 | 244457.0827 | 66208.527 | 101293.8016 | 90.71% | 70.75% | YES | YES | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Program expenditures exceeded imputed regulatory values for Wildfire Mitigations due to the capitalization of a five year pre-paid agreement for a software as a service (SaaS) application (Foundry) that provides the capability of harnessing highly available data to analyze, build, visualize and deploy technology solutions that support Wildfire Mitigations. Electric Distribution technology program expenditures were above imputed regulatory values due to unplanned general IT expenditures on Field Area Network assets that experienced performance issues. The asset replacements have been prioritized to address the areas of greatest risk first. | N/A | On-Target | On-Target | Over | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is 1) provide technology solution support for the development and implementation of the Integrated Grid Platform; and 2) provide technology solutions that support wildfire mitigations. The program specifically provides hardware and software network and telecommunications solutions as well as enhancements to software planning tools in support of wildfire mitigation.
308 | Capital | Electric Distribution | 2F | Build IT Apps & Infra | N/A | Not assigned | Distribution Overhead | DOVHD-M005: Additional Asset Data Capture | Ex 4, Ch 4.5 Ex 4, Ch 20-21 | Yes | N/A | N/A | 0 | 0 | 0 | 677.8 | 0 | 677.8 | 0 | 677.8 | 0% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
309 | Capital | Electric Distribution | 2F | Build IT Apps & Infra | N/A | Not assigned | IT Asset Failure | ITAFL-M005: Multi-Faceted Mitigations | Ex 4, Ch 4.5 Ex 4, Ch 20-21 | Yes | N/A | N/A | 0 | 0 | 0 | 34788.0418 | 23275.123 | 58063.1648 | 23275.123 | 58063.1648 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
310 | Capital | Electric Distribution | 2F | Build IT Apps & Infra | N/A | Not assigned | Emergency Preparedness & Response | EPNDR-C002: Situational Awareness and Forecasting Initiatives - WSOC | Ex 4, Ch 4.5 Ex 4, Ch 20-21 | Yes | N/A | N/A | 0 | 0 | 0 | 2408 | 0 | 2408 | 0 | 2408 | 0% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
311 | Capital | Electric Distribution | 2F | Build IT Apps & Infra | N/A | Not assigned | Wildfire | WLDFR-M0IT: Wildfire IT Work | Ex 4, Ch 4.5 Ex 4, Ch 20-21 | Yes | N/A | N/A | 27890.2385 | 29009.5624 | 56899.8009 | 45036.3254 | 76595.7747 | 121632.1001 | 47586.2124 | 64732.2993 | 164% | 113.8% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
312 | Capital | Electric Distribution | 2F | Build IT Apps & Infra | N/A | Not assigned | Wildfire | POST-GRC: Post-GRC Mitigation | Ex 4, Ch 4.5 Ex 4, Ch 20-21 | Yes | N/A | N/A | 0 | 0 | 0 | 4257.9144 | 0 | 4257.9144 | 0 | 4257.9144 | 0% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
313 | Capital | Electric Distribution | 2F | Build IT Apps & Infra | N/A | Not assigned | SRM (NON-RAMP) | SRM (NON-RAMP) | Ex 4, Ch 4.5 Ex 4, Ch 20-21 | Yes | N/A | N/A | 42283.2615 | 43980.2188 | 86263.4802 | 18090.6758 | 39327.4104 | 57418.0863 | -4652.8083 | -28845.394 | -10.58% | -33.44% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
314 | Capital | Electric Distribution | 49/3U | Inst/Rpl WildFire Mitgt Eqpmnt | 49M/3UA (a) | ED WFM PIH Microgrids | SRM Total | SRM Total | Ex 4, Ch 4.3 | No | 5 | 7 | 0 | 0 | 0 | 262.3767 | 652.3173 | 914.694 | 652.3173 | 914.694 | 100% | 100% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | Over | Proceeding as Planned | This program is for the instillation of temporary distribution microgrids to reduce the number of customers impacted by PSPS events. This program began in 2018 and was forecasted to be completed in 2022. PG&E now anticipates that this program will be completed in 2025.
315 | Capital | Electric Distribution | 49/3U | Inst/Rpl WildFire Mitgt Eqpmnt | 49M/3UA | ED WFM PIH Microgrids | Wildfire | WLDFR-M006: PSPS Reduction Initiatives | Ex 4, Ch 4.3 | No | N/A | N/A | 0 | 0 | 0 | 262.3767 | 652.3173 | 914.694 | 652.3173 | 914.694 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A | N/A
316 | Capital | Electric Distribution | 3U | Inst/Rpl WildFire Mitgt Eqpmnt | 3UC (b) | ED WFM Dist Line MSO Device | SRM Total | SRM Total | Ex 4, Ch 4.3 | No | 4 | 6 | 0 | 0 | 0 | 0 | 2352.5784 | 2352.5784 | 2352.5784 | 2352.5784 | 100% | 100% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | Over | Over | Over | Emergent | This program is to address ignition risk created by some Motorized Switch Operators (MSO) that were initially installed by PG&E in 2019 as sectionalizing devices. Despite the switches being understood to meet CalFire's exempt criteria for not posing an ignition risk during normal operations, PG&E crews noted that some MSO switches exhibited an arc flash during the opening operation requiring replacement. In the 2023 GRC, PG&E had planned to replace or retrofit all MSO switches by 2022. However, the program required expansion to mitigate wildfire risk, and PG&E continued to replace MSO switches in 2024.
317 | Capital | Electric Distribution | 3U | Inst/Rpl WildFire Mitgt Eqpmnt | 3UC | ED WFM Dist Line MSO Device | Wildfire | WLDFR-M006: PSPS Reduction Initiatives | Ex 4, Ch 4.3 | No | N/A | N/A | 0 | 0 | 0 | 0 | 2352.5784 | 2352.5784 | 2352.5784 | 2352.5784 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A | N/A
318 | Capital | Electric Distribution | 49/3U | Inst/Rpl WildFire Mitgt Eqpmnt | 49I/3UD (c) | ED WFM Dist Fault Anticipation | SRM Total | SRM Total | Ex 4, Ch 4.3 | No | On-going | Annual | 9468.4874 | 9888.7914 | 19426.0244 | 180.3752 | 2394.9425 | 2575.3177 | -7493.849 | -16850.7067 | -75.78% | -86.74% | NO | NO | # of sensor locations | 116 | 116 | 232 | 5 | 17 | 22 | -99 | -210 | -85.34% | -90.52% | YES | Below variance threshold. | Actual units were lower than imputed units because PG&E is aligning the work to meet the current WMP commitment for this program. PG&E installed 17 DFA sensors in 2024 exceeding the WMP Commit, rather than the 116 units imputed in the GRC (See PG&E's 2023-2025 WMP Revision 8, Initiative Activity Tracking ID SA-10, Section 8.3.3.1) | Under | Under | Under | Rescheduled | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to install distribution grid sensors in substations which individually and in combination with other sensors, provide real-time monitoring capability of the grid. During the 2023 GRC cycle PG&E anticipates that it will continue to be below GRC imputed amounts but will meet its WMP commitments.
319 | Capital | Electric Distribution | 49/3U | Inst/Rpl WildFire Mitgt Eqpmnt | 49I/3UD | ED WFM Dist Fault Anticipation | Wildfire | WLDFR-M012: Situational Awareness and Forecasting Initiatives - DFA | Ex 4, Ch 4.3 | No | N/A | N/A | 9468.4874 | 9888.7914 | 19426.0244 | 180.3752 | 2394.9425 | 2575.3177 | -7493.849 | -16850.7067 | -75.78% | -86.74% | N/A | N/A | # of sensor locations | 116 | 116 | 232 | 5 | 17 | 22 | -99 | -210 | -85.34% | -90.52% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
320 | Capital | Electric Distribution | 49/3U | Inst/Rpl WildFire Mitgt Eqpmnt | 49I/3UE (d) | ED WFM Dist Fault Anticipation | SRM Total | SRM Total | Ex 4, Ch 4.3 | No | On-going | Annual | 5739.5277 | 5994.3041 | 11733.8318 | 890.9217 | 2802.7873 | 3693.709 | -3191.5168 | -8040.1228 | -53.24% | -68.52% | NO | NO | # of sensor locations | 250 | 250 | 500 | 55 | 97 | 152 | -153 | -348 | -61.2% | -69.6% | YES | Below variance threshold. | Actual units were lower than imputed units because PG&E is aligning the work to meet the current WMP commitment for this program. The current commitment is 2 circuits for 2024. PG&E met that commitment which only resulted in the need for 97 units rather than the 250 units imputed in the GRC. (See PG&E's 2023-2025 WMP Revision 8, Initiative Activity Tracking ID SA-11, Section 8.3.3.1). | Under | Under | Under | Rescheduled | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to install distribution grid sensors that use radio frequency signals to locate the source of a disturbance along a conductor. During the 2023 GRC cycle PG&E anticipates that it will continue to be below GRC imputed amounts but will meet its WMP commitments.
321 | Capital | Electric Distribution | 49/3U | Inst/Rpl WildFire Mitgt Eqpmnt | 49I/3UE (d) | ED WFM Dist Fault Anticipation | Wildfire | WLDFR-M011: Situational Awareness and Forecasting Initiatives - EFD | Ex 4, Ch 4.3 | No | N/A | N/A | 5739.5277 | 5994.3041 | 11733.8318 | 890.9217 | 2802.7873 | 3693.709 | -3191.5168 | -8040.1228 | -53.24% | -68.52% | N/A | N/A | # of sensor locations | 250 | 250 | 500 | 55 | 97 | 152 | -153 | -348 | -61.2% | -69.6% | N/A |  |  | N/A | N/A | N/A | N/A | N/A
322 | Capital | Electric Distribution | 49/3U | Inst/Rpl WildFire Mitgt Eqpmnt | 49T/3UF (e) | ED FuseSaver | SRM Total | SRM Total | Ex 4, Ch 4.3 | No | On-going | Annual | 3105.025 | 3242.8563 | 6347.8813 | 7061.8317 | 4033.1964 | 11095.028 | 790.3401 | 4747.1468 | 24.37% | 74.78% | NO | NO | # of FuseSavers installed | 79.72 | 80 | 159.72 | 49 | 35 | 84 | -45 | -75.72 | -56.25% | -47.41% | YES | Below variance threshold. | Actual units were lower than imputed units because unit costs went up and priority was given to EPSS capital programs in WLDFR-M020. | Under | Under | On-Target | Rescheduled | The purpose of this program is to install Fuse Savers. PG&E anticipated that it will reallocate funding to other priorities like EPSS capital programs, for the remainder of the GRC cycle. The budget is listed as on-target because it is likely that overspend in 2023-2024 will balance out with underspend in 2025-2026 due to fewer, if any installations, because of reprioritization of other wildfire capital programs, like EPSS.
323 | Capital | Electric Distribution | 49/3U | Inst/Rpl WildFire Mitgt Eqpmnt | 49T/3UF | ED FuseSaver | Wildfire | WLDFR-M10B: Additional System Automation and Protection - FuseSaver | Ex 4, Ch 4.3 | No | N/A | N/A | 3105.025 | 3242.8563 | 6347.8813 | 7061.8317 | 4033.1964 | 11095.028 | 790.3401 | 4747.1468 | 24.37% | 74.78% | N/A | N/A | # of FuseSavers installed | 79.72 | 80 | 159.72 | 49 | 35 | 84 | -45 | -75.72 | -56.25% | -47.41% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
324 | Capital | Electric Distribution | 49/3U | Inst/Rpl WildFire Mitgt Eqpmnt | 49I/3UL (f) | ED WFM Dist Fault Anticipation | SRM Total | SRM Total | Ex 4, Ch 4.3 | No | On-going | Annual | 8717.0196 | 9103.9662 | 17820.9858 | 3037.2378 | 1682.5363 | 4719.7742 | -7421.4298 | -13101.2116 | -81.52% | -73.52% | NO | NO | # of sensor locations | 900 | 900 | 1800 | 247 | 194 | 441 | -706 | -1359 | -78.44% | -75.5% | YES | Below variance threshold. | Actual units were lower than imputed units because PG&E planned the work to meet the WMP commitment for this program which was 40 circuits for 2024. PG&E did 45 circuits which only resulted in the need for 194 units rather than the 900 units imputed in the GRC (see PG&E's 2023-2025 WMP Revision 8, Initiative Activity Tracking ID SA-02, Section 8.3.3.1). | Under | Under | Under | Rescheduled | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to install distribution grid sensors which individually and in combination with other sensors, provide real-time monitoring capability of the grid. During the 2023 GRC cycle PG&E anticipates that it will continue to be below GRC imputed amounts but will meet its WMP commitments.
325 | Capital | Electric Distribution | 49/3U | Inst/Rpl WildFire Mitgt Eqpmnt | 49I/3UL | ED WFM Dist Fault Anticipation | Wildfire | WLDFR-M07A: Situational Awareness and Forecasting Initiatives - Line Sensors | Ex 4, Ch 4.3 | No | N/A | N/A | 8717.0196 | 9103.9662 | 17820.9858 | 3037.2378 | 1682.5363 | 4719.7742 | -7421.4298 | -13101.2116 | -81.52% | -73.52% | N/A | N/A | # of sensor locations | 900 | 900 | 1800 | 741 | 194 | 935 | -706 | -865 | -78.44% | -48.06% | N/A |  |  | N/A | N/A | N/A | N/A | N/A
326 | Capital | Electric Distribution | 49/3U | Inst/Rpl WildFire Mitgt Eqpmnt | 49H/3UP (g) | ED WFM Dist Protective Device | SRM Total | SRM Total | Ex. 4, Ch 4.3 | No | On-going | Annual | 12602.4165 | 13161.835 | 25764.2515 | 13992.6051 | 4040.0563 | 18032.6615 | -9121.7786 | -7731.5901 | -69.3% | -30.01% | NO | NO | # of installations or replacements of sectionalizing devices | 100 | 100 | 200 | 82 | 38 | 120 | -62 | -80 | -62% | -40% | YES | Below variance threshold. | Actual units were lower than imputed units because most of the highest impact locations have already been sectionalized with automated equipment, so there is a reduced benefit (in terms of number of customers likely to benefit from such devices during PSPS events) when compared to work performed in previous years. Therefore PG&E will focus on reducing reliability impacts with additional protective devices as part of the WMP GH-07 initiative (Distribution Sectionalizing Devices). See PG&E's 2023-2025 WMP Revision 8, Section 8.1.2.11.2. | Under | Under | Under | Rescheduled | This program is ongoing and will continue in PG&E 2023 GRC time period though at a slower pace than forecasted driven by current WMP commitments. The purpose of this program is to install automated electrical equipment designed to isolate faulted lines, limit line reclosing and facilitate the remote opening and closing of switches necessary to efficiently implement PSPS. PG&E anticipated that it will continue to reallocate funding to other priority wildfire mitigation work for the remainder of the GRC cycle.
327 | Capital | Electric Distribution | 49/3U | Inst/Rpl WildFire Mitgt Eqpmnt | 49H/3UP | ED WFM Dist Protective Device | Wildfire | WLDFR-M006: PSPS Reduction Initiatives | Ex. 4, Ch 4.3 | No | N/A | N/A | 12602.4165 | 13161.835 | 25764.2515 | 13992.6051 | 4040.0563 | 18032.6615 | -9121.7786 | -7731.5901 | -69.3% | -30.01% | N/A | N/A | # of installations or replacements of sectionalizing devices | 100 | 100 | 200 | 82 | 38 | 120 | -62 | -80 | -62% | -40% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
328 | Capital | Electric Distribution | 49/3U | Inst/Rpl WildFire Mitgt Eqpmnt | 49R/3UR ( e) | ED WFM REFCL | SRM Total | SRM Total | Ex 4, Ch 4.3 | No | On-going | Annual | 18304.0778 | 19116.592 | 37420.6698 | 71.5858 | 4.4605 | 76.0463 | -19112.1315 | -37344.6234 | -99.98% | -99.8% | NO | YES | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Program expenditures were below imputed regulatory values because of delays in the Rapid Earth Fault Current Limiter (REFCL) demonstration project due to technology and system integration challenges. | N/A | Under | Under | Under | Rescheduled | The purpose of this program is the evaluation of the effectiveness of the REFCL technology to mitigate the need for PSPS. PG&E may continue to evaluate REFCL if challenges with the technology are resolved, but is not pursuing it as a widespread solution for wildfire mitigation at this time. Funding has been reallocated to other priority Wildfire programs like EPSS capital.
329 | Capital | Electric Distribution | 49/3U | Inst/Rpl WildFire Mitgt Eqpmnt | 49R/3UR | ED WFM REFCL | Wildfire | WLDFR-M10C: Additional System Automation and Protection - REFCL | Ex 4, Ch 4.3 | Yes | N/A | N/A | 17901.0778 | 19116.592 | 37017.6698 | 71.5858 | 4.4605 | 76.0463 | -19112.1315 | -36941.6234 | -99.98% | -99.79% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
330 | Capital | Electric Distribution | 49/3U | Inst/Rpl WildFire Mitgt Eqpmnt | 49R/3UR | ED WFM REFCL | SRM (NON-RAMP) | SRM (NON-RAMP) | Ex 4, Ch 4.3 | Yes | N/A | N/A | 403 | 0 | 403 | 0 |  | 0 | 0 | -403 | 0% | -100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
331 | Capital | Electric Distribution | 49/3U | Inst/Rpl WildFire Mitgt Eqpmnt | 49A/3US | ED WFM SCADA Non Reclose | SRM Total | SRM Total | Ch 4.3, Ch 4.6 | No | On-going | Annual | 0 | 0 | 0 | 12795.0286 | 11576.517 | 24371.5456 | 11576.517 | 24371.5456 | 100% | 100% | NO | YES | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Program expenditures exceeded imputed regulatory values due to the introduction of the Downed Conductor Detection (DCD) program. In 2023 PG&E began the DCD program for EPSS and recorded costs and units to MAT 49A. In 2024 PG&E began recording this work in MAT 3US. The DCD program mitigates ignitions for high impedance faults and is a wildfire mitigation. Note that PG&E did not forecast EPSS capital costs in the 2023 GRC. | N/A | Over | Over | Over | Emergent | This program's work is ongoing and will continue in PG&E's 2023 GRC period. PG&E is listing the status of this program as Emergent because we did not forecast EPSS capital or the EPSS DCD program in the 2023 GRC.
332 | Capital | Electric Distribution | 49/3U | Inst/Rpl WildFire Mitgt Eqpmnt | 49A/3US (b) | ED WFM SCADA Non Reclose | Wildfire | WLDFR-M020: Enhanced Powerline Safety Settings | Ch 4.3, Ch 4.6 | Yes | N/A | N/A | 0 | 0 | 0 | 12744.4235 | 11576.517 | 24320.9404 | 11576.517 | 24320.9404 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
333 | Capital | Electric Distribution | 49/3U | Inst/Rpl WildFire Mitgt Eqpmnt | 49A/3US (b) | ED WFM SCADA Non Reclose | Wildfire | WLDFR-M10A: Additional System Automation and Protection | Ch 4.3, Ch 4.6 | Yes | N/A | N/A | 0 | 0 | 0 | 50.6051 | 0 | 50.6051 | 0 | 50.6051 | 0% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
334 | Capital | Electric Distribution | 3U | Inst/Rpl WildFire Mitgt Eqpmnt | 3UT (j) | ED WFM Non-Exempt Expulsion | SRM Total | SRM Total | Ex 4, Ch 11 Ex 4, Ch 4.3 | No | 7 | 6 | 0 | 0 | 0 | 0 | 16932.2832 | 16932.2832 | 16932.2832 | 16932.2832 | 100% | 100% | NO | YES | # Expulsion Fuses Replaced | 0 | 0 | 0 | 0 | 3106 | 3106 | 3106 | 3106 | 100% | 100% | YES | Program expenditures exceeded imputed regulatory values because the imputed adopted costs for replacing non-exempt fuses ($17, 495) was included in MAT 2AP total imputed adopted costs ($18,627). The actual costs for replacing non-exempt fuses were recorded under MAT 2AJ in 2023 and MAT 3UT in 2024. If the 2024 imputed adopted costs for replacing non-exempt fuses ($17,495) in MAT 2AP were compared to the recorded costs in MAT 3UT ($16,932) for 2024, the actual costs would be in line with the imputed adopted costs for 2024. | Actual units were higher than imputed units because 1) this programs was imputed in MAT 2AP and 2) PG&E ramped up the program to focus on approximately 3,000 replacements in HFTDs per year to meet our 2023-2025 WMP commitments. | Over | On-Target | Over | Proceeding as Planned | PG&E is on-target to replace the remaining known population of non exempt fuses in HFTDs and conclude the program at the end of 2025.
335 | Capital | Electric Distribution | 3U | Inst/Rpl WildFire Mitgt Eqpmnt | 3UT (j) | ED WFM Non-Exempt Expulsion | Distribution Overhead | DOVHD-M004: Expulsion Fuse Replacement | Ex 4, Ch 11 Ex 4, Ch 4.3 | No | N/A | N/A | 0 | 0 | 0 | 0 | 16932.2832 | 16932.2832 | 16932.2832 | 16932.2832 | 100% | 100% | N/A | N/A | # Expulsion Fuses Replaced | 0 | 0 | 0 | 0 | 3106 | 3106 | 3106 | 3106 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
336 | Capital | Electric Distribution | 3U | Inst/Rpl WildFire Mitgt Eqpmnt | 3UT (j) | ED WFM Non-Exempt Expulsion | Wildfire | WLDFR-M004: Expulsion Fuse Replacement | Ex 4, Ch 11 Ex 4, Ch 4.3 | No | N/A | N/A | 0 | 0 | 0 | 0 | 16932.2832 | 16932.2832 | 16932.2832 | 16932.2832 | 100% | 100% | N/A | N/A | # Expulsion Fuses Replaced | 0 | 0 | 0 | 0 | 3106 | 3106 | 3106 | 3106 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
337 | Capital | Electric Distribution | 46 | E Dist Subst Capacity | 46A | DSub Nor Capacity | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 17 | No | On-going | Annual | 16420.3602 | 17149.2563 | 33569.6165 | 18203.8827 | 20546.4814 | 38750.3642 | 3397.2252 | 5180.7477 | 19.81% | 15.43% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. This program includes projects to support general distribution substation capacity increases.
338 | Capital | Electric Distribution | 46 | E Dist Subst Capacity | 46F | DSub Em and Op Capacity | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 17 | No | On-going | Annual | 1019.1721 | 1064.4129 | 2083.585 | 2547.3234 | 2930.4395 | 5477.7628 | 1866.0266 | 3394.1779 | 175.3% | 162.9% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. MAT 46F includes: (1) work to address emergency capacity deficiencies; and (2) operational capacity work to reduce the number of customers on a circuit to no more than 6,000 and circuit loading to a maximum of 600 amperes (amps).
339 | Capital | Electric Distribution | 46 | E Dist Subst Capacity | 46H | DSub New Bus Related Capacity | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 17 | No | On-going | Annual | 43142.8658 | 45057.968 | 88200.8337 | 46817.4292 | 76589.4811 | 123406.9103 | 31531.5131 | 35206.0765 | 69.98% | 39.92% | YES | YES | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Program expenditures exceeded imputed regulatory values due to additional capacity funding deployed in 2024 via SB 410 and Energization Capacity New Business Interim Memorandum Account (ECNBIMA) to provide distribution line capacity to energize customer loads. | N/A | Over | Over | Over | Expanded | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to provides substation capacity necessary to complete new customer applications for service. PG&E expects to continue to do more work in this program than forecasted due to SB410 requirements, as discussed in PG&E's 2023 GRC capacity phase filing.
340 | Capital | Electric Distribution | 46 | E Dist Subst Capacity | 46N | DSub Land Purchase_ New Sub | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 17 | No | On-going | Annual | 0 | 0 | 0 | -286.038 | 173.6568 | -112.3812 | 173.6568 | -112.3812 | 100% | -100% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | Under | Proceeding as Planned | N/A
341 | Capital | Electric Distribution | 48 | E Dist Subst Repl Other Equip | 48A | Repl Dsub Other Equipment | SRM Total | SRM Total | Ex 4, Ch 15 | No | On-going | Annual | 4401.5604 | 4596.9447 | 8998.5051 | 769.6422 | 1974.7278 | 2744.37 | -2622.2169 | -6254.1352 | -57.04% | -69.5% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | Under | Under | Under | Rescheduled | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is ongoing capital infrastructure replacement work to maintain system operations and reliability. In 2023 & 2024, PG&E prioritized substation work (for example in MAT 48L, 54A, and MWC 59) over MAT 48A. For the 2023 GRC cycle, PG&E anticipates that this work will continue to be lower priority than other Substation work.
342 | Capital | Electric Distribution | 48 | E Dist Subst Repl Other Equip | 48A | Repl Dsub Other Equipment | Substation | SBSTN-C16A: Proactive Asset Replacement - Ground Grid | Ex 4, Ch 15 | Yes | N/A | N/A | 4401.5604 | 4596.9447 | 8998.5051 | 769.6422 | 1974.7278 | 2744.37 | -2622.2169 | -6254.1352 | -57.04% | -69.5% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
343 | Capital | Electric Distribution | 48 | E Dist Subst Repl Other Equip | 48A | Repl Dsub Other Equipment | Wildfire | WLDFR-C10A: Substation Proactive Asset Replacement - Ground Grid | Ex 4, Ch 15 | Yes | N/A | N/A | 4401.5604 | 4596.9447 | 8998.5051 | 759.3567 | 1974.7278 | 2734.0845 | -2622.2169 | -6264.4206 | -57.04% | -69.62% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
344 | Capital | Electric Distribution | 48 | E Dist Subst Repl Other Equip | 48A | Repl Dsub Other Equipment | Wildfire | POST-GRC: Post-GRC Mitigation | Ex 4, Ch 15 | Yes | N/A | N/A | 0 | 0 | 0 | 10.2854 | 0 | 10.2854 | 0 | 10.2854 | 0% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
345 | Capital | Electric Distribution | 48 | E Dist Subst Repl Other Equip | 48B | Repl DSub Regulators | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 15 | No | On-going | Annual | 0 | 0 | 0 | 2.1574 | 1.1531 | 3.3105 | 1.1531 | 3.3105 | 100% | 100% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | Over | Proceeding as Planned | This program was not forecasted in the 2023 GRC. Replacement of distribution substation regulators is integrated under MAT 54A. The program has not been canceled but this MAT code is no longer being used for that purpose.
346 | Capital | Electric Distribution | 48 | E Dist Subst Repl Other Equip | 48C | Repl DSub Batteries | SRM Total | SRM Total | Ex 4, Ch 15 | No | On-going | Annual | 3389.481 | 3539.9393 | 6929.4204 | 2.1074 | 40.4627 | 42.5702 | -3499.4766 | -6886.8502 | -98.86% | -99.39% | NO | NO | # of Batteries | 10 | 10 | 20 | 0 | 0 | 0 | -10 | -20 | -100% | -100% | YES | Below variance threshold. | Actual units were lower than imputed units because of the decision to reschedule proactive battery replacements to support higher priority substation work. Rescheduling of these proactive replacements does not compromise safety or reliability. | Under | Under | Under | Rescheduled | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is capital infrastructure replacement work to maintain system operations and reliability. In 2023, PG&E prioritized substation work (for example in MAT 48L, 54A, and MWC 59) over MAT 48C. At this time, PG&E anticipates that this program will continue to be prioritized below other substation work.
347 | Capital | Electric Distribution | 48 | E Dist Subst Repl Other Equip | 48C | Repl DSub Batteries | Substation | SBSTN-C16C: Proactive Asset Replacement - Batteries | Ex 4, Ch 15 | No | N/A | N/A | 3389.481 | 3539.9393 | 6929.4204 | 2.1074 | 40.4627 | 42.5702 | -3499.4766 | -6886.8502 | -98.86% | -99.39% | N/A | N/A | N/A | 10 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
348 | Capital | Electric Distribution | 48 | E Dist Subst Repl Other Equip | 48C | Repl DSub Batteries | Wildfire | WLDFR-C10C: Substation Proactive Asset Replacement - Batteries | Ex 4, Ch 15 | No | N/A | N/A | 3389.481 | 3539.9393 | 6929.4204 | 2.1074 | 40.4627 | 42.5702 | -3499.4766 | -6886.8502 | -98.86% | -99.39% | N/A | N/A | N/A | 10 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
349 | Capital | Electric Distribution | 48 | E Dist Subst Repl Other Equip | 48D | Repl DSub Breakers | SRM Total | SRM Total | Ex 4, Ch 15 | No | On-going | Annual | 29793.9318 | 31116.4778 | 60910.4096 | 9239.0055 | 13632.274 | 22871.2796 | -17484.2038 | -38039.1301 | -56.19% | -62.45% | NO | YES | # of circuit breakers | 40 | 40 | 80 | 9 | 3 | 12 | -37 | -68 | -92.5% | -85% | YES | Program expenditures were below imputed regulatory values due to prioritizing work in Emergency Replacements (MWC 17 and 59), and Overhead Maintenance Replacements (MWC 2A). | Actual units were lower than imputed units due to reprioritization of funding as explained in the cost variance explanation for this MAT code. | Under | Under | Under | Rescheduled | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is capital infrastructure replacement work, like breakers, to maintain system operations and reliability. For 2023, PG&E reprioritized funding from MAT 48D to higher priority work in other programs as described in the cost variance explanation. At this time, PG&E anticipates that this program will continue to be lower priority for the remainder of the GRC cycle. Breakers may be replaced under MWC 59, on an just-in-time basis.
350 | Capital | Electric Distribution | 48 | E Dist Subst Repl Other Equip | 48D | Repl DSub Breakers | Substation | SBSTN-C16D: Proactive Asset Replacement - Circuit Breakers | Ex 4, Ch 15 | Yes | N/A | N/A | 29793.9318 | 31116.4778 | 60910.4096 | 4708.8085 | 13632.274 | 18341.0826 | -17484.2038 | -42569.3271 | -56.19% | -69.89% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
351 | Capital | Electric Distribution | 48 | E Dist Subst Repl Other Equip | 48D | Repl DSub Breakers | Wildfire | WLDFR-C10D: Substation Proactive Asset Replacement - Circuit Breakers | Ex 4, Ch 15 | Yes | N/A | N/A | 29793.9318 | 31116.4778 | 60910.4096 | 4708.8085 | 13632.274 | 18341.0826 | -17484.2038 | -42569.3271 | -56.19% | -69.89% | N/A | N/A | # of circuit breakers | 40 | 40 | 80 | 9 | 3 | 12 | -37 | -68 | -93% | -85% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
352 | Capital | Electric Distribution | 48 | E Dist Subst Repl Other Equip | 48D | Repl DSub Breakers | Wildfire | WLDFR-M020: Enhanced Powerline Safety Settings | Ex 4, Ch 15 | Yes | N/A | N/A | 0 | 0 | 0 | 4530.197 | 0 | 4530.197 | 0 | 4530.197 | 0% | 100% | N/A | N/A | # of circuit breakers | 40 | 40 | 80 | 9 | 3 | 12 | -37 | -68 | -93% | -85% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
353 | Capital | Electric Distribution | 48 | E Dist Subst Repl Other Equip | 48E | Repl DSub Switches | SRM Total | SRM Total | Ex 4, Ch 15 | No | On-going | Annual | 2303.9531 | 2406.2251 | 4710.1781 | -244.0113 | 1067.6994 | 823.6881 | -1338.5257 | -3886.4901 | -55.63% | -82.51% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | Under | Under | Under | Rescheduled | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is ongoing capital infrastructure replacement work to maintain system operations and reliability. In 2023 & 2024, PG&E prioritized substation work (for example in MAT 48L, 54A, and MWC 59) over MAT 48E. For the 2023 GRC cycle, PG&E anticipates that this work will continue to be lower priority than other Substation work.
354 | Capital | Electric Distribution | 48 | E Dist Subst Repl Other Equip | 48E | Repl DSub Switches | Substation | SBSTN-C16E: Substation Proactive Asset Replacement Switches | Ex 4, Ch 15 | No | N/A | N/A | 2303.9531 | 2406.2251 | 4710.1781 | -244.0113 | 1067.6994 | 823.6881 | -1338.5257 | -3886.4901 | -55.63% | -82.51% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
355 | Capital | Electric Distribution | 48 | E Dist Subst Repl Other Equip | 48E | Repl DSub Switches | Wildfire | WLDFR-C10E: Substation Proactive Asset Replacement - Switches | Ex 4, Ch 15 | No | N/A | N/A | 2303.9531 | 2406.2251 | 4710.1781 | -244.0113 | 1067.6994 | 823.6881 | -1338.5257 | -3886.4901 | -55.63% | -82.51% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
356 | Capital | Electric Distribution | 48 | E Dist Subst Repl Other Equip | 48F | Repl DSub Switchgear | SRM Total | SRM Total | Ex 4, Ch 15 | No | On-going | Annual | 33829.2322 | 35330.9042 | 69160.1364 | 17542.3511 | 20310.948 | 37853.2992 | -15019.9562 | -31306.8372 | -42.51% | -45.27% | NO | YES | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Program expenditures were below imputed regulatory values to support higher priority emergency work in MWC 59. | N/A | Under | Under | Under | Rescheduled | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is capital infrastructure replacement work to maintain system operations and reliability. PG&E reprioritized this work to higher priority emergency work in MWC 59. At this time, PG&E foresees this program will continue to be lower priority.
357 | Capital | Electric Distribution | 48 | E Dist Subst Repl Other Equip | 48F | Repl DSub Switchgear | Substation | SBSTN-C16F: Substation Proactive Asset Replacement - Switchgear | Ex 4, Ch 15 | No | N/A | N/A | 33829.2322 | 35330.9042 | 69160.1364 | 17542.3511 | 20310.948 | 37853.2992 | -15019.9562 | -31306.8372 | -42.51% | -45.27% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
358 | Capital | Electric Distribution | 48 | E Dist Subst Repl Other Equip | 48F | Repl DSub Switchgear | Wildfire | WLDFR-C10F: Substation Proactive Asset Replacement - Switchgear | Ex 4, Ch 15 | No | N/A | N/A | 33829.2322 | 35330.9042 | 69160.1364 | 17542.3511 | 20310.948 | 37853.2992 | -15019.9562 | -31306.8372 | -42.51% | -45.27% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
359 | Capital | Electric Distribution | 48 | E Dist Subst Repl Other Equip | 48H | Repl DSub Civil Structures | SRM Total | SRM Total | Ex 4, Ch 15 | No | On-going | Annual | 5649.1347 | 5899.8985 | 11549.0332 | 832.961 | 653.1139 | 1486.075 | -5246.7846 | -10062.9583 | -88.93% | -87.13% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | Under | Under | Under | Rescheduled | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is ongoing capital infrastructure replacement work to maintain system operations and reliability. In 2023 & 2024, PG&E prioritized substation work (for example in MAT 48L, 54A, and MWC 59) over MAT 48H. For the 2023 GRC cycle, PG&E anticipates that this work will continue to be lower priority than other Substation work.
360 | Capital | Electric Distribution | 48 | E Dist Subst Repl Other Equip | 48H | Repl DSub Civil Structures | Substation | SBSTN-C005: Civil Structures Replacement | Ex 4, Ch 15 | Yes | N/A | N/A | 4230.5805 | 4418.375 | 8648.9555 | 835.5416 | 653.1139 | 1488.6555 | -3765.2611 | -7160.3 | -85.22% | -82.79% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
361 | Capital | Electric Distribution | 48 | E Dist Subst Repl Other Equip | 48H | Repl DSub Civil Structures | Substation | SBSTN-M006: Minimize Wood in Substations | Ex 4, Ch 15 | Yes | N/A | N/A | 1418.5542 | 1481.5235 | 2900.0777 | -2.5806 | 0 | -2.5806 | -1481.5235 | -2902.6583 | -100% | -100.1% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
362 | Capital | Electric Distribution | 48 | E Dist Subst Repl Other Equip | 48L | Dist Line Work Support Substat | SRM Total | SRM Total | Ex 4, Ch 15 | No | On-going | Annual | 9496.7522 | 9918.3109 | 19415.063 | 29062.35 | 38379.321 | 67441.671 | 28461.0101 | 48026.608 | 287% | 247.4% | YES | YES | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Program expenditures exceeded imputed regulatory values due to a higher volume of substation replacements, in MWC 59, requiring a higher volume of distribution line support work in MAT 48L. | N/A | Over | Over | Over | Emergent | This program's work is ongoing and will continue in PG&E's 2023 GRC period. This is a demand driven program. The purpose of this program is substation capital infrastructure replacement work which to support distribution line work. This program includes both proactive and emergency substation replacements. Due to aging infrastructure and the reprioritization of funding in related areas of MWC 48, PG&E anticipates there will continue to be an increased amount of costs than forecasted through the 2023 GRC cycle.
363 | Capital | Electric Distribution | 48 | E Dist Subst Repl Other Equip | 48L | Dist Line Work Support Substat | Substation | SBSTN-C16G: Proactive Asset Replacement - Line Support Work | Ex 4, Ch 15 | No | N/A | N/A | 9496.7522 | 9918.3109 | 19415.063 | 29062.35 | 38379.321 | 67441.671 | 28461.0101 | 48026.608 | 287% | 247.4% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
364 | Capital | Electric Distribution | 48 | E Dist Subst Repl Other Equip | 48L | Dist Line Work Support Substat | Wildfire | WLDFR-C10H: Substation Proactive Asset Replacement - Line Support Work | Ex 4, Ch 15 | No | N/A | N/A | 9496.7522 | 9918.3109 | 19415.063 | 29062.35 | 38379.321 | 67441.671 | 28461.0101 | 48026.608 | 287% | 247.4% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
365 | Capital | Electric Distribution | 48 | E Dist Subst Repl Other Equip | 48N | DSub Insulators | SRM Total | SRM Total | Ex 4, Ch 15 | No | On-going | Annual | 5649.1347 | 5899.8985 | 11549.0332 | 0.30676 | 0.16404 | 0.4708 | -5899.7345 | -11548.5624 | -100% | -100% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | Under | Under | Under | Rescheduled | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is ongoing capital infrastructure replacement work to maintain system operations and reliability. In 2023 & 2024, PG&E prioritized substation work (for example in MAT 48L, 54A, and MWC 59) over MAT 48N. For the 2023 GRC cycle, PG&E anticipates that this work will continue to be lower priority than other Substation work.
366 | Capital | Electric Distribution | 48 | E Dist Subst Repl Other Equip | 48N | DSub Insulators | Substation | SBSTN-C16H: Proactive Asset Replacement - Insulators | Ex 4, Ch 15 | No | N/A | N/A | 5649.1347 | 5899.8985 | 11549.0332 | 0.30676 | 0.16404 | 0.4708 | -5899.7345 | -11548.5624 | -100% | -100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
367 | Capital | Electric Distribution | 48 | E Dist Subst Repl Other Equip | 48N | DSub Insulators | Wildfire | WLDFR-C10I: Substation Proactive Asset Replacement - Insulators | Ex 4, Ch 15 | No | N/A | N/A | 5649.1347 | 5899.8985 | 11549.0332 | 0.30676 | 0.16404 | 0.4708 | -5899.7345 | -11548.5624 | -100% | -100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
368 | Capital | Electric Distribution | 48 | E Dist Subst Repl Other Equip | 48X | DSub Animal Abatement | SRM Total | SRM Total | Ex 4, Ch 15 | No | On-going | Annual | 6008.154 | 6274.8546 | 12283.0085 | 149.0098 | 62.3456 | 211.3555 | -6212.509 | -12071.6531 | -99.01% | -98.28% | NO | NO | # of locations | 17 | 17 | 34 | 0 | 0 | 0 | -17 | -34 | -100% | -100% | YES | Below variance threshold. | Actual units were lower than imputed units due to reprioritization of proactive animal abatement work to support higher priority work in MWC 48, such as distribution line work to support substation work under MAT 48L. | Under | Under | Under | Rescheduled | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is capital infrastructure replacement work, like Animal Abatement, to maintain system operations and reliability. At this time, PG&E foresees this program to continue to be lower priority than other programs.
369 | Capital | Electric Distribution | 48 | E Dist Subst Repl Other Equip | 48X | DSub Animal Abatement | Substation | SBSTN-C002: Animal Abatement Substation | Ex 4, Ch 15 | No | N/A | N/A | 6008.154 | 6274.8546 | 12283.0085 | 149.0098 | 62.3456 | 211.3555 | -6212.509 | -12071.6531 | -99.01% | -98.28% | N/A | N/A | N/A | 17 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
370 | Capital | Electric Distribution | 49 | E Dist Reliability Ckt/Zone | 49A | Distribution Line Automation | SRM Total | SRM Total | Ex 4, Ch 13 Ex 4, Ch 4.3 | No | On-going | Annual | 1920.7057 | 2005.9654 | 3926.671 | -9.493 | -3.6884 | -13.1813 | -2009.6537 | -3939.8524 | -100.2% | -100.3% | NO | NO | # of Devices | 18 | 18 | 36 | 0 | 0 | 0 | -18 | -36 | -100% | -100% | YES | Below variance threshold. | Actual units were lower than imputed units due to a change in how the program mitigates risk from what was forecasted in the 2023 GRC. In 2023 PG&E began recording work associated with the new Downed Conductor Detection (DCD) program. The DCD program mitigate ignitions for high impedance faults and is a wildfire risk mitigation. The DCD program uses harmonic analysis to detect arching present during high impedance faults and provides an immediate trip response. Note that the program units forecasted in 49A for risk DOVHD-M010 were completed in MAT 49B. | Under | On-Target | Under | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. This program was forecasted in the 2023 GRC for the replacement of Reclosers and Recloser controllers for reliability and wildfire risks. In 2023 PG&E began implementing the Downed Conductor Detection (DCD) program and recording costs to 49A. In 2024 PG&E began recording the DCD costs to MAT 3US. For the forecasted costs for risk DOVHD-M010, the costs and units that were forecasted to MAT 49A in 2023 were recorded in MAT 49B. For the remaining GRC cycle, PG&E will continue to record DCD costs to 3US and DOVHD-M010 to MAT 49B. Therefore for 49A, even though work is continuing on other MAT codes, scope and budget will be reported as under but the overall status is proceeding as planned because the work will continue being done but recorded elsewhere.
371 | Capital | Electric Distribution | 49 | E Dist Reliability Ckt/Zone | 49A | Distribution Line Automation | Distribution Overhead | DOVHD-M010: 3A and 4C Line Recloser Replacement | Ex 4, Ch 13 Ex 4, Ch 4.3 | No | N/A | N/A | 1920.7057 | 2005.9654 | 3926.671 | -9.493 | -3.6884 | -13.1813 | -2009.6537 | -3939.8524 | -100.2% | -100.3% | N/A | N/A | # of Devices | 18 | 18 | 36 | 0 | 0 | 0 | -18 | -36 | -100% | -100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
372 | Capital | Electric Distribution | 49 | E Dist Reliability Ckt/Zone | 49B | Recl Ctrls Inst/Repl | SRM Total | SRM Total | Ex 4, Ch 13 | No | On-going | Annual | 4587.0978 | 4790.718 | 9377.8158 | 1684.8762 | 2913.5386 | 4598.4148 | -1877.1794 | -4779.401 | -39.18% | -50.96% | NO | NO | # of line recloser locations | 44 | 44 | 88 | 18 | 36 | 54 | -8 | -34 | -18.18% | -38.64% | NO | Below variance threshold. | Below variance threshold | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is the replacement of line reclosers and controllers. For the remainder of the GRC cycle, PG&E will continue to record to 49B the costs and units that were forecasted in 49A for DOVHD-M010. In addition costs for EPSS, WLDFR-M020 are being recorded here that were not forecasted in the 2023 GRC.
373 | Capital | Electric Distribution | 49 | E Dist Reliability Ckt/Zone | 49B | Recl Ctrls Inst/Repl | Distribution Overhead | DOVHD-M010: 3A and 4C Line Recloser Replacement | Ex 4, Ch 13 | Yes | N/A | N/A | 4587.0978 | 4790.718 | 9377.8158 | 1684.8762 | 591.3909 | 2276.2671 | -4199.3271 | -7101.5487 | -87.66% | -75.73% | N/A | N/A | # of line recloser locations | 44 | 44 | 88 | 18 | 36 | 54 | -8 | -34 | -18.18% | -38.64% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
374 | Capital | Electric Distribution | 49 | E Dist Reliability Ckt/Zone | 49B | Recl Ctrls Inst/Repl | Wildfire | WLDFR-M020: Enhanced Powerline Safety Settings | Ex. 4, Ch 4.3 | Yes | N/A | N/A | 0 | 0 | 0 | 0 | 2332.1477 | 2332.1477 | 2332.1477 | 2332.1477 | 100% | 100% | N/A | N/A | # of line recloser locations | 44 | 44 | 88 | 18 | 36 | 54 | -8 | -34 | -18.18% | -38.64% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
375 | Capital | Electric Distribution | 49 | E Dist Reliability Ckt/Zone | 49C | OH Fuses Inst/Repl | SRM Total | SRM Total | Ex 4, Ch 13 | No | On-going | Annual | 1626.9506 | 1699.1706 | 3326.1212 | 2178.1721 | 2483.6664 | 4661.8385 | 784.4958 | 1335.7173 | 46.17% | 40.16% | NO | NO | # of Fused locations | 128.86 | 128.8596 | 257.7196 | 75 | 86 | 161 | -42.8596 | -96.7196 | -33.26% | -37.53% | YES | Below variance threshold. | Actual units were lower than imputed units due to recent updates to the standard requirements for this program, which have triggered additional work such as the full replacement of the pole. | Under | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is the installation and replacement of overhead fuses. As noted in the unit variance explanation, total cost for this work has increased driven by higher unit costs. In addition, there can be an annual disconnect between when dollars are spent and units are recorded for this program. For the remainder of the GRC cycle, PG&E expects to complete fewer units for the costs allocated.
376 | Capital | Electric Distribution | 49 | E Dist Reliability Ckt/Zone | 49C | OH Fuses Inst/Repl | Distribution Overhead | DOVHD-C003: Equipment Maintenance and Replacement - Distribution Overhead | Ex 4, Ch 13 | No | N/A | N/A | 1626.9506 | 1699.1706 | 3326.1212 | 2178.1721 | 2483.6664 | 4661.8385 | 784.4958 | 1335.7173 | 46.17% | 40.16% | N/A | N/A | N/A | 128.86 | 129 | 258 | 75 | 86 | 161 | -43 | -97 | -33.33% | -37.6% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
377 | Capital | Electric Distribution | 49 | E Dist Reliability Ckt/Zone | 49D | OH Recl/Sect/Swch Inst/Repl | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 13 | No | On-going | Annual | 0 | 0 | 0 | 1537.5867 | -52.0482 | 1485.5385 | -52.0482 | 1485.5385 | -100% | 100% | NO | NO | # of TripSavers installed | 0 | 0 | 0 | 35 | 1 | 36 | 1 | 36 | 100% | 100% | YES | Below variance threshold. | Actual units were higher than imputed units due to the installation of trip savers that remained in inventory and were not forecasted in the 2023 GRC. | Over | Over | Over | Emergent | The purpose of this program is the installation of Trip Saver devices and was not forecasted in the 2023 GRC because similar work is now being performed in MAT 49T. In 2024, PG&E conducted a one-time effort to install 1 trip saver remaining in inventory. The program has completed and the MAT Code has been re-purposed.
378 | Capital | Electric Distribution | 49 | E Dist Reliability Ckt/Zone | 49E | Genl Inst/Repl Circuit/Zone | SRM Total | SRM Total | Ex 4, Ch 13 | No | On-going | Annual | 0 | 0 | 0 | 1597.5643 | 1955.9164 | 3553.4807 | 1955.9164 | 3553.4807 | 100% | 100% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | Over | Proceeding as Planned | The work for this program is recorded costs for circuit installation / replacement to enable EPSS for wildfire mitigation. The program work will continue through the remainder of the 2023 GRC period.
379 | Capital | Electric Distribution | 49 | E Dist Reliability Ckt/Zone | 49E | Genl Inst/Repl Circuit/Zone | Wildfire | WLDFR-M020: Enhanced Powerline Safety Settings | Ex 4, Ch 13 | Yes | N/A | N/A | 0 | 0 | 0 | 6.4337 | 0 | 6.4337 | 0 | 6.4337 | 0% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
380 | Capital | Electric Distribution | 49 | E Dist Reliability Ckt/Zone | 49E | Genl Inst/Repl Circuit/Zone | SRM (NON-RAMP) | SRM (NON-RAMP) | Ex 4, Ch 13 | Yes | N/A | N/A | 0 | 0 | 0 | 1591.1306 | 1955.9164 | 3547.0469 | 1955.9164 | 3547.0469 | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
381 | Capital | Electric Distribution | 49 | E Dist Reliability Ckt/Zone | 49G | UG Recl/Sect/Swch Inst/Repl | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 13 | No | On-going | Annual | 0 | 0 | 0 | 0.06224 | 0.18723 | 0.24947 | 0.18723 | 0.24947 | 100% | 100% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | Over | Proceeding as Planned | This program was not forecast in the 2023 GRC. Any recorded amounts are from prior years' carry-over work.
382 | Capital | Electric Distribution | 49 | E Dist Reliability Ckt/Zone | 49S | Elect Reliability Inst FLISR | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 13 | No | On-going | Annual | 3881.6561 | 4053.9619 | 7935.618 | 964.3304 | 1175.6303 | 2139.9607 | -2878.3317 | -5795.6573 | -71% | -73.03% | NO | NO | # of FLISR Circuit Activations | 12 | 12 | 24 | 1 | 2 | 3 | -10 | -21 | -83.33% | -87.5% | YES | Below variance threshold. | Actual units were lower than imputed units due to reprioritization to other higher priority programs like Emergency Replacements (MWC 17 and 59), and Overhead Maintenance Replacements (MWC 2A). | Under | Under | Under | Rescheduled | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is the installation of technology to detect and isolate outages, and restore service to customers. PG&E anticipates that this program will continue to be lower priority for the remainder of the GRC cycle.
383 | Capital | Electric Distribution | 49 | E Dist Reliability Ckt/Zone | 49T | D-Single Phase Recloser | SRM Total | SRM Total | Ex 4, Ch 13 Ex 4, Ch 4.3 | No | On-going | Annual | 1452.7636 | 1517.2515 | 2970.0151 | 0 | 0 | 0 | -1517.2515 | -2970.0151 | -100% | -100% | NO | NO | # FuseSavers installed | 37.77 | 38 | 75.77 | 0 | 0 | 84 | -3 | 8.23 | -7.895% | 10.86% | NO | Below variance threshold. | Below variance threshold | On-Target | On-Target | Under | Canceled | The installation of fuse savers previously forecast and recorded under MAT 49T has transitioned to a new MAT 3UF. The original scope of trip saver work under MAT 49T has sunsetted.
384 | Capital | Electric Distribution | 49 | E Dist Reliability Ckt/Zone | 49T | D-Single Phase Recloser | Distribution Overhead | DOVHD-C014: Additional System Automation and Protection - FuseSaver | Ex 4, Ch 13 Ex 4, Ch 4.3 | No | N/A | N/A | 1452.7636 | 1517.2515 | 2970.0151 | 0 | 0 | 0 | -1517.2515 | -2970.0151 | -100% | -100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
385 | Capital | Electric Distribution | 49 | E Dist Reliability Ckt/Zone | 49X | Emerging Dist Rel Improvements | SRM Total | SRM Total | Ex 4, Ch 13 | No | On-going | Annual | 3868.2593 | 4039.9704 | 7908.2297 | 16114.6244 | 32322.9499 | 48437.5744 | 28282.9795 | 40529.3447 | 700.1% | 512.5% | YES | YES | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Program expenditures exceeded imputed regulatory values due to EPSS work being recorded to this program. PG&E did not forecast EPSS capital work in the 2023 GRC due to the program was new and PG&E was not able to develop a forecast for the 2023 GRC. | N/A | Over | Over | Over | Emergent | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is reliability work to address routine, localized reliability issues as they emerge. In 2023, PG&E recorded to this MAT non-forecasted costs for EPSS sectionalizing, which reduces customer impact of EPSS. Starting in 2024 through 2025, the EPSS work is being recorded to 49D.
386 | Capital | Electric Distribution | 49 | E Dist Reliability Ckt/Zone | 49X | Emerging Dist Rel Improvements | Distribution Overhead | DOVHD-C012: Targeted Reliability Programs | Ex 4, Ch 13 | Yes | N/A | N/A | 3868.2593 | 4039.9704 | 7908.2297 | 9114.6262 | 32322.9499 | 41437.5761 | 28282.9795 | 33529.3464 | 700.1% | 424% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
387 | Capital | Electric Distribution | 49 | E Dist Reliability Ckt/Zone | 49X | Emerging Dist Rel Improvements | Wildfire | WLDFR-M020: Enhanced Powerline Safety Settings | Ex 4, Ch 13 | Yes | N/A | N/A | 0 | 0 | 0 | 6999.9982 | 0 | 6999.9982 | 0 | 6999.9982 | 0% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
388 | Capital | Electric Distribution | 49 | E Dist Reliability Ckt/Zone | 49# | Not assigned | SRM Total | SRM Total | Ex 4, Ch 13 | No | On-going | Annual | 13025.7745 | 13603.9857 | 26629.7602 | -294.1035 | 1540.8805 | 1246.777 | -12063.1052 | -25382.9832 | -88.67% | -95.32% | NO | YES | # of line reclosers inventory received | 694 | 693.7919 | 1387.7919 | 1307 | 671 | 1978 | -22.7919 | 590.2081 | -3.285% | 42.53% | NO | Program expenditures were below imputed regulatory values due to PG&E's decision to record the associated material costs to the actual projects in various other programs such as critical operating equipment, EPSS related work, and capacity projects, rather than to this MAT code. This program purchases and maintains inventory of line reclosers. | Below variance threshold | On-Target | On-Target | Under | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is for purchases and maintains inventory of line reclosers; the costs were centrally forecasted in 49# in the 2023 GRC. In the 2023 GRC cycle, PG&E will record the recloser material costs to individual projects in various programs however the reclosers will be captured here in 49#.
389 | Capital | Electric Distribution | 49 | E Dist Reliability Ckt/Zone | 49# | Not assigned | Wildfire | WLDFR-M006: PSPS Reduction Initiatives | Ex 4, Ch 13 | Yes | N/A | N/A | 0 | 0 | 0 | 31.7594 | 0 | 31.7594 | 0 | 31.7594 | 0% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
390 | Capital | Electric Distribution | 49 | E Dist Reliability Ckt/Zone | 49# | Not assigned | SRM (NON-RAMP) | SRM (NON-RAMP) | Ex 4, Ch 13 | Yes | N/A | N/A | 13025.7745 | 13603.9857 | 26629.7602 | -325.8629 | 1540.8805 | 1215.0176 | -12063.1052 | -25414.7426 | -88.67% | -95.44% | N/A | N/A | # of line reclosers inventory received | 694 | 693.7919 | 1387.7919 | 1307 | 671 | 1978 | -22.7919 | 590.2081 | -3.285% | 42.53% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
391 | Capital | Electric Distribution | 54 | E Dist Subst Repl Transformer | 54A | E Dist Subst-Repl Transfm | SRM Total | SRM Total | Ex 4, Ch 15 | No | On-going | Annual | 18767.4771 | 19600.5612 | 38368.0383 | 24806.1031 | 7094.1477 | 31900.2507 | -12506.4136 | -6467.7876 | -63.81% | -16.86% | NO | YES | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Program expenditures were below imputed regulatory values due to prioritizing work in Emergency Replacements (MWC 59). | N/A | Under | Under | Under | Rescheduled | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is capital infrastructure replacement work, like transformers, to maintain system operations and reliability. For 2023, PG&E reprioritized funding from MAT 54A to higher priority work in other programs as described in the cost variance explanation. At this time, PG&E anticipates that this program will continue to be lower priority for the remainder of the GRC cycle. Transformers may be replaced under MWC 59.
392 | Capital | Electric Distribution | 54 | E Dist Subst Repl Transformer | 54A | E Dist Subst-Repl Transfm | Substation | SBSTN-C16J: Proactive Asset Replacement - Transformer | Ex 4, Ch 15 | Yes | N/A | N/A | 16703.0546 | 17444.4995 | 34147.5541 | 22502.5842 | 3859.8901 | 26362.4744 | -13584.6094 | -7785.0797 | -77.87% | -22.8% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
393 | Capital | Electric Distribution | 54 | E Dist Subst Repl Transformer | 54A | E Dist Subst-Repl Transfm | Substation | SBSTN-M002: Increase Capitalized Emergency (CEM) Stock for Transformers, Emergency Mobile Transformers | Ex 4, Ch 15 | Yes | N/A | N/A | 2064.4225 | 2156.0617 | 4220.4842 | 2204.8708 | 3234.2575 | 5439.1283 | 1078.1958 | 1218.6441 | 50.01% | 28.87% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
394 | Capital | Electric Distribution | 54 | E Dist Subst Repl Transformer | 54A | E Dist Subst-Repl Transfm | Wildfire | WLDFR-C10K: Substation Proactive Asset Replacement - Transformer | Ex 4, Ch 15 | Yes | N/A | N/A | 16703.0546 | 17444.4995 | 34147.5541 | 22502.5842 | 3859.8901 | 26362.4744 | -13584.6093 | -7785.0797 | -77.87% | -22.8% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
395 | Capital | Electric Distribution | 54 | E Dist Subst Repl Transformer | 54A | E Dist Subst-Repl Transfm | SRM (NON-RAMP) | SRM (NON-RAMP) | Ex 4, Ch 15 | Yes | N/A | N/A | 0 | 0 | 0 | 98.648 | 0 | 98.648 | 0 | 98.648 | 0% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
396 | Capital | Electric Distribution | 54 | E Dist Subst Repl Transformer | 54L | E Dist Subst-Life Ext Transfm | SRM Total | SRM Total | Ex 4, Ch 15 | No | On-going | Annual | 3389.481 | 3539.9393 | 6929.4204 | 15.4234 | 504.4323 | 519.8557 | -3035.5071 | -6409.5647 | -85.75% | -92.5% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | Under | Under | Under | Rescheduled | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to recondition older substation transformers to extend their life expectancy by replacing a specific combination of components. For 2024, PG&E re-prioritized funding from MAT 54L to higher priority work in MAT 54A. Over the GRC cycle, PG&E expects to continue to reprioritize this program to higher priority work within the MWC 54 program.
397 | Capital | Electric Distribution | 54 | E Dist Subst Repl Transformer | 54L | E Dist Subst-Life Ext Transfm | Substation | SBSTN-M001: Transformer Life Extension | Ex 4, Ch 15 | No | N/A | N/A | 3389.481 | 3539.9393 | 6929.4204 | 15.4234 | 504.4323 | 519.8557 | -3035.5071 | -6409.5647 | -85.75% | -92.5% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
398 | Capital | Electric Distribution | 56 | E Dist Replace UG Asset-Gen | 56# | Not assigned | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 14 | No | On-going | Annual | 0 | 0 | 0 | -226.305 | -413.5741 | -639.8791 | -413.5741 | -639.8791 | -100% | -100% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | Under | Proceeding as Planned | This program covers miscellaneous standard costs and adjustments that are not directly attributable to a specific MAT code. PG&E does not forecast costs for these activities.
399 | Capital | Electric Distribution | 56 | E Dist Replace UG Asset-Gen | 56A | UG Cable Other Repl | SRM Total | SRM Total | Ex 4, Ch 13 | No | On-going | Annual | 38567.0412 | 40279.0235 | 78846.0648 | 20512.8025 | 24281.3748 | 44794.1773 | -15997.6487 | -34051.8875 | -39.72% | -43.19% | NO | YES | # miles | 17.5 | 17.5 | 35 | 6.87 | 12.4 | 19.27 | -5.1 | -15.73 | -29.14% | -44.94% | YES | Program expenditures were below imputed regulatory values due to reprioritizing to emergency replacements (MWC 17), and capacity improvements (MWC 06, 46). | Actual units were lower than imputed units due to reprioritization as discussed in the cost variance explanation. | Under | Under | Under | Rescheduled | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to replace underground primary cables in areas with history of failures.
400 | Capital | Electric Distribution | 56 | E Dist Replace UG Asset-Gen | 56A | UG Cable Other Repl | Underground | DUNGD-C06A: Primary Cable Replacement Program | Ex 4, Ch 13 | No | N/A | N/A | 38567.0412 | 40279.0235 | 78846.0648 | 20512.8025 | 24281.3748 | 44794.1773 | -15997.6487 | -34051.8875 | -39.72% | -43.19% | N/A | N/A | # miles | 17.5 | 17.5 | 35 | 6.87 | 12.4 | 19.27 | -5.1 | -15.73 | -29.14% | -44.94% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
401 | Capital | Electric Distribution | 56 | E Dist Replace UG Asset-Gen | 56B | UG Cable Inject | SRM Total | SRM Total | Ex 4, Ch 13 | No | On-going | Annual | 1164.6483 | 1216.3467 | 2380.995 | 45.8496 | 119.069 | 164.9186 | -1097.2777 | -2216.0765 | -90.21% | -93.07% | NO | NO | # of Miles | 6 | 6 | 12 | 0 | 0 | 0 | -6 | -12 | -100% | -100% | YES | Below variance threshold. | Actual units were lower than imputed units due to reprioritizing emergency replacements (MWC 17) and underground/network maintenance replacements (MWCs 2B & 2C). | Under | Under | Under | Rescheduled | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to test or rejuvenate UG primary cables as part of targeted replacement strategy. PG&E anticipates that this program will continue to be lower priority for the remainder of the GRC cycle.
402 | Capital | Electric Distribution | 56 | E Dist Replace UG Asset-Gen | 56B | UG Cable Inject | Underground | DUNGD-C06B: Primary Cable Rejuvenation Program | Ex 4, Ch 13 | No | N/A | N/A | 1164.6483 | 1216.3467 | 2380.995 | 45.8496 | 119.069 | 164.9186 | -1097.2777 | -2216.0765 | -90.21% | -93.07% | N/A | N/A | # of Miles | 5.5 | 6 | 11.5 | 0 | 0 | 0 | -6 | -11.5 | -100% | -100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
403 | Capital | Electric Distribution | 56 | E Dist Replace UG Asset-Gen | 56C | UG Cable COE Repl | SRM Total | SRM Total | Ex 4, Ch 13 | No | On-going | Annual | 37551.0869 | 39217.9713 | 76769.0582 | 7943.626 | 782.2413 | 8725.8674 | -38435.7299 | -68043.1908 | -98.01% | -88.63% | YES | YES | # projects | 197 | 197 | 394 | 23 | 1 | 24 | -196 | -370 | -99.49% | -93.91% | YES | Program expenditures were below imputed regulatory values due to reprioritizing emergency replacements (MWC 17). | Actual units were lower than imputed units due to reprioritization as discussed in the cost variance explanation. | Under | Under | Under | Rescheduled | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program to replace failed underground primary cables in 200A loop systems.
404 | Capital | Electric Distribution | 56 | E Dist Replace UG Asset-Gen | 56C | UG Cable COE Repl | Underground | DUNGD-C003: Equipment Maintenance and Replacement | Ex 4, Ch 13 | No | N/A | N/A | 37551.0869 | 39217.9713 | 76769.0582 | 7943.626 | 782.2413 | 8725.8674 | -38435.7299 | -68043.1908 | -98.01% | -88.63% | N/A | N/A | # projects | 197 | 197 | 394 | 23 | 1 | 24 | -196 | -370 | -99.49% | -93.91% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
405 | Capital | Electric Distribution | 56 | E Dist Replace UG Asset-Gen | 56D | TGram/TGral Switch Replacement | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 13 | No | On-going | Annual | 0 | 0 | 0 | -7.6184 | 0.64595 | -6.9724 | 0.64595 | -6.9724 | 100% | -100% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | Under | Proceeding as Planned | The purpose of this program is to replace UG switches to the extent that TGRAM/TGRAL switches are identified. This program will continue through the remainder of the 2023 GRC period.
406 | Capital | Electric Distribution | 56 | E Dist Replace UG Asset-Gen | 56N(l) | Network Cable Replacement | SRM Total | SRM Total | Ex 4, Ch 14 | No | On-going | Annual | 32200.0672 | 33629.421 | 65829.4882 | 261.3623 | 382.4805 | 643.8428 | -33246.9405 | -65185.6454 | -98.86% | -99.02% | YES | YES | # of Circuit Feet | 56889.32 | 56889.32 | 113778.64 | 0 | 0 | 0 | -56889.32 | -113778.64 | -100% | -100% | YES | Program expenditures were below imputed regulatory values due to reprioritizing work to emergency replacements (MWC 17), and capacity improvements (MWC 06, 46). | Actual units were lower than imputed units due to reprioritization as discussed in the cost variance explanation. | Under | Under | Under | Rescheduled | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is a to replace network cable assets, prior to premature failure. PG&E anticipates that this program will continue to be lower priority for the remainder of the GRC cycle.
407 | Capital | Electric Distribution | 56 | E Dist Replace UG Asset-Gen | 56N | Network Cable Replacement | Distribution Network | DNTWK-C001: Network Cable Replacement | Ex 4, Ch 14 | No | N/A | N/A | 32200.0672 | 33629.421 | 65829.4882 | 261.3623 | 382.4805 | 643.8428 | -33246.9405 | -65185.6454 | -98.86% | -99.02% | N/A | N/A | # of Circuit Feet | 56889.32 | 56889.32 | 113778.64 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
408 | Capital | Electric Distribution | 56 | E Dist Replace UG Asset-Gen | 56S | Replace Obsolete UG Switches | SRM Total | SRM Total | Ex 4, Ch 13 | No | On-going | Annual | 8473.8585 | 8850.0112 | 17323.8697 | -834.7214 | 11151.9769 | 10317.2555 | 2301.9657 | -7006.6142 | 26.01% | -40.44% | NO | NO | # of LBOR Switch Replacements | 77 | 77 | 154 | 0 | 39 | 39 | -38 | -115 | -49.35% | -74.68% | YES | Below variance threshold. | Actual units were lower than imputed units due to delays in construction due to permitting and unforeseen additions, such as cable replacement, to some jobs that were only identified at the time of construction. | Under | Under | Under | Rescheduled | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is to replace older oil-filled LBOR switches with no oil inspection sight glass which poses a greater safety risk than other types of switches.
409 | Capital | Electric Distribution | 56 | E Dist Replace UG Asset-Gen | 56S | Replace Obsolete UG Switches | Underground | DUNGD-C007: LBOR Switch Replacement | Ex 4, Ch 13 | No | N/A | N/A | 8473.8585 | 8850.0112 | 17323.8697 | -834.7214 | 11151.9769 | 10317.2555 | 2301.9657 | -7006.6142 | 26.01% | -40.44% | N/A | N/A | # of LBOR Switch Replacements | 77 | 77 | 154 | 0 | 39 | 39 | -38 | -115 | -49.35% | -74.68% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
410 | Capital | Electric Distribution | 56 | E Dist Replace UG Asset-Gen | 56T | Install Temperature Indicator | SRM Total | SRM Total | Ex 4, Ch 13 | No | On-going | Annual | 8837.6017 | 9229.9009 | 18067.5026 | 3575.1812 | 5432.7437 | 9007.9248 | -3797.1572 | -9059.5777 | -41.14% | -50.14% | NO | NO | # of Installations | 2294 | 2294 | 4588 | 0 | 1019 | 1019 | -1275 | -3569 | -55.58% | -77.79% | YES | Below variance threshold. | Actual units were lower than imputed units due to quality and performance issues with the TAD devices. PG&E switched to a different manufacturer but did not receive TAD units until later in the year, impacting the ability to install the imputed amount of units. | Under | Under | Under | Rescheduled | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is a continuing effort to install temperature alarm devices to monitor UG asset condition and identify proactive replacements, prior to premature failure.
411 | Capital | Electric Distribution | 56 | E Dist Replace UG Asset-Gen | 56T | Install Temperature Indicator | Underground | DUNGD-C008: UG Transformers Temperature Sensor | Ex 4, Ch 13 | No | N/A | N/A | 8837.6017 | 9229.9009 | 18067.5026 | 3575.1812 | 5432.7437 | 9007.9248 | -3797.1572 | -9059.5777 | -41.14% | -50.14% | N/A | N/A | # of Installations | 2294 | 2294 | 4588 | 0 | 1019 | 1019 | -1275 | -3569 | -55.58% | -77.79% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
412 | Capital | Electric Distribution | 58 | E Dist Repl Substation Safety | 58A | DSub Safety&Envir&Fire Protect | SRM Total | SRM Total | Ex 4, Ch 15 | No | On-going | Annual | 3389.481 | 3539.9393 | 6929.4204 | -4.7059 | 36.0829 | 31.377 | -3503.8564 | -6898.0433 | -98.98% | -99.55% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | Under | Under | Under | Rescheduled | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program concerns fire protection and suppression installs, replacements, or upgrades as required by local fire marshals and state regulations. PG&E foresees this program to continue to be lower priority than other programs.
413 | Capital | Electric Distribution | 58 | E Dist Repl Substation Safety | 58A | DSub Safety&Envir&Fire Protect | Substation | SBSTN-C009: Fire Protection / Suppression Systems | Ex 4, Ch 15 | No | N/A | N/A | 3389.481 | 3539.9393 | 6929.4204 | -4.7059 | 36.0829 | 31.377 | -3503.8564 | -6898.0433 | -98.98% | -99.55% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
414 | Capital | Electric Distribution | 58 | E Dist Repl Substation Safety | 58A | DSub Safety&Envir&Fire Protect | Wildfire | WLDFR-C018: Fire Protection / Suppression Systems | Ex 4, Ch 15 | No | N/A | N/A | 3389.481 | 3539.9393 | 6929.4204 | -4.7059 | 36.0829 | 31.377 | -3503.8564 | -6898.0433 | -98.98% | -99.55% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
415 | Capital | Electric Distribution | 58 | E Dist Repl Substation Safety | 58B | Repl Dist Sub Civil Structures | SRM Total | SRM Total | Ex 4, Ch 15 | No | On-going | Annual | 0 | 0 | 0 | 0 | 95.2426 | 95.2426 | 95.2426 | 95.2426 | 100% | 100% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | Over | Proceeding as Planned | This MAT 58B program is for as-needed civil structure improvements driven by environmental & security requirements i.e., concrete reinforcements and seismic work. Work may continue to be charged to this MAT program through the remainder of the 2023 GRC period.
416 | Capital | Electric Distribution | 58 | E Dist Repl Substation Safety | 58C | Repl Dist Sub Misc Equip | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 15 | No | On-going | Annual | 0 | 0 | 0 | 9.2229 | 0 | 9.2229 | 0 | 9.2229 | 0% | 100% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | Over | Proceeding as Planned | This program is for replacement of miscellaneous substation equipment may incur minimal carry-over costs through the remainder of the 2023 GRC peiod.
417 | Capital | Electric Distribution | 58 | E Dist Repl Substation Safety | 58S | DSub Security Upgrades | SRM Total | SRM Total | Ex 4, Ch 15 | No | On-going | Annual | 5197.2044 | 5427.9071 | 10625.1115 | 3405.633 | 7752.3435 | 11157.9765 | 2324.4363 | 532.8649 | 42.82% | 5.015% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | Over | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is installs, upgrades, or replacements of physical security measures within substations. This program represents ongoing capital infrastructure replacement work to maintain system operations and reliability. For the remainder of the 2023 GRC PG&E expects to spend more than imputed on the program in order to include physical security improvement at five substations to meet CPUC Decision 19-01-018 (SB 699) requirements. This decision has requirements for critical distribution security commitments. PG&E developed and revised a mitigation plan to upgrade the physical security at five critical distribution substations by 2026.
418 | Capital | Electric Distribution | 58 | E Dist Repl Substation Safety | 58S | DSub Security Upgrades | Substation | SBSTN-C001: Substation Security Enhancements | Ex 4, Ch 15 | No | N/A | N/A | 5197.2044 | 5427.9071 | 10625.1115 | 3405.633 | 7752.3435 | 11157.9765 | 2324.4363 | 532.8649 | 42.82% | 5.015% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
419 | Capital | Electric Distribution | 58 | E Dist Repl Substation Safety | 58S | DSub Security Upgrades | Wildfire | WLDFR-C10M: Substation Security Enhancements | Ex 4, Ch 15 | No | N/A | N/A | 5197.2044 | 5427.9071 | 10625.1115 | 3405.633 | 7752.3435 | 11157.9765 | 2324.4363 | 532.8649 | 42.82% | 5.015% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
420 | Capital | Electric Distribution | 59 | E Dist Subst Emergency Repl | N/A | Not assigned | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 15 | No | On-going | Annual | 85866.848 | 89678.4582 | 175545.3061 | 172615.2136 | 184247.2258 | 356862.4394 | 94568.7677 | 181317.1333 | 105.5% | 103.3% | YES | YES | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Program expenditures exceeded imputed regulatory values due to a higher volume of emergency replacement work than forecasted in the 2023 GRC. | N/A | On-Target | On-Target | Over | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is for emergency capital infrastructure replacement work to maintain system operations and reliability. PG&E anticipates that a higher volume of work in this program may materialize due to reprioritization of other substation work.
421 | Capital | Electric Distribution | 63 | E T&D Control System/ Facility | 63C | Advanced Dist Mgmt System Dev | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 21 | No | 7 | 6 | 113742.7965 | 118791.8138 | 232534.6102 | 112433.5182 | 104114.1288 | 216547.647 | -14677.685 | -15986.9633 | -12.36% | -6.875% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | This program includes ongoing work to design, build, and test the Advanced Distribution Management System (ADMS).
422 | Capital | Electric Distribution | 63 | E T&D Control System/ Facility | 63D | Distribution Operational Tech | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 7 | No | On-going | Annual | 4776.4117 | 4968.1043 | 9744.516 | 4878.2743 | 5942.8016 | 10821.0758 | 974.6973 | 1076.5599 | 19.62% | 11.05% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | On-Target | Proceeding as Planned | This is an ongoing program that includes minor enhancements & bug fixes to distribution operations technology, and the development of reporting capabilities used in PG&E distribution operations. The work will continue through the remainder of the 2023 GRC period.
423 | Capital | Electric Distribution | 63 | E T&D Control System/ Facility | 63# | Not assigned | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 7 | No | On-going | Annual | 0 | 0 | 0 | 7055.8779 | 8553.0284 | 15608.9064 | 8553.0284 | 15608.9064 | 100% | 100% | NO | NO | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Below variance threshold. | N/A | On-Target | On-Target | Over | Proceeding as Planned | This program includes work in PG&E's Distribution Energy Resource Management Systems (DERMS), is on-going and will continue through the remainder of the 2023 GRC period. The DERMS costs that were forecast in the 2023 GRC in MAT 63C, are being been recorded in MAT 63#.
424 | Capital | Electric Distribution | 95 | E Dist Major Emergency | N/A | Not assigned | SRM Total (NON-RAMP) | SRM Total (NON-RAMP) | Ex 4, Ch 6 | No | On-going | Annual | 66359.7164 | 69305.4093 | 135665.1257 | 49287.4677 | 192225.3094 | 241512.7771 | 122919.9001 | 105847.6514 | 177.4% | 78.02% | YES | YES | Not Unitized – There is no applicable unit of measure for this program. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Program expenditures exceeded imputed regulatory values due the February Winter Storms and the July Weather Event which caused a significant deviation from historical trends | N/A | On-Target | On-Target | Over | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. This is a demand driven program. The purpose of this program is for major emergencies. This program has no end and is responsive to conditions that require immediate attention.
425 | Capital | Nuclear Generation | 20 | DCPP Capital |  |  | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 5, Ch 3 | No | On-going | annual | 10243.7821 | 5914.3196 | 16158.1017 | 8768.1264 | 4040.2912 | 12808.4175 | -1874.0285 | -3349.6842 | -31.69% | -20.73% | NO | NO |  | N/A: Below variance threshold. | On-Target | On-Target | On-Target | Proceeding as planned | N/A
426 | Capital | Power Generation | 2L | Instl/Rpl for Hydro Safety&Reg |  |  | SRM Total | SRM Total | Ex 5, Ch 4 | No | On-going | annual | 63080.1525 | 47169.5723 | 110249.7248 | 25395.9211 | 69798.2683 | 95194.1894 | 22628.696 | -15055.5354 | 47.97% | -13.66% | YES | YES |  | N/A: Program expenses were above imputed adopted values due to rescheduled work from 2023 into the 2024-2026 period, including the following work: Fordyce Dam Leakage Reduction, Pit 3 Powerhouse Seismic Retrofit. | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is a continuing effort to support capital costs primarily related to employee or public safety and regulatory requirements that are not connected with relicensing for hydroelectric generation.
427 | Capital | Power Generation | 2L | Instl/Rpl for Hydro Safety&Reg |  |  | Large Uncontrolled Water Release | M1 - Internal Erosion Mitigation | Ex 5, Ch 2, p. 2-13; p. WP 2-2 | Yes | N/A | N/A | 25100.8543 | 27825.3307 | 52926.185 | 6464.5766 | 41163.5218 | 47628.0984 | 13338.1911 | -5298.0866 | 47.94% | -10.01% | N/A | N/A |  | N/A: N/A | N/A | N/A | N/A | N/A | N/A
428 | Capital | Power Generation | 2L | Instl/Rpl for Hydro Safety&Reg |  |  | Large Uncontrolled Water Release | M2 - Spillway Remediation | Ex 5, Ch 2, p. 2-13; p. WP 2-2 | Yes | N/A | N/A | 4225.3609 | 339.6209 | 4564.9819 | 577.827 | 502.4199 | 1080.2469 | 162.7989 | -3484.735 | 47.94% | -76.34% | N/A | N/A |  | N/A: N/A | N/A | N/A | N/A | N/A | N/A
429 | Capital | Power Generation | 2L | Instl/Rpl for Hydro Safety&Reg |  |  | Large Uncontrolled Water Release | M3 - Seismic Retrofit | Ex 5, Ch 2, p. 2-13; p. WP 2-2 | Yes | N/A | N/A | 26938.3791 | 292.4513 | 27230.8305 | 333.5723 | 432.639 | 766.2113 | 140.1877 | -26464.6191 | 47.94% | -97.19% | N/A | N/A |  | N/A: N/A | N/A | N/A | N/A | N/A | N/A
430 | Capital | Power Generation | 2L | Instl/Rpl for Hydro Safety&Reg |  |  | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 5, Ch 4, p. 4-78 | Yes | N/A | N/A | 6814.5489 | 18712.1694 | 25526.7182 | 18019.91 | 27699.6876 | 45719.5976 | 8987.5182 | 20192.8794 | 48.03% | 79.1% | N/A | N/A |  | N/A: N/A | N/A | N/A | N/A | N/A | N/A
431 | Capital | Power Generation | 2M | Instal/Repl Hydro Gneratng Eqp |  |  | SRM Total | SRM Total |  | No | On-going | annual | 84621.5813 | 92060.5492 | 176682.1305 | 115907.7139 | 196325.8908 | 312233.6047 | 104265.3416 | 135551.4742 | 113.3% | 76.72% | YES | YES |  | N/A: Program expenses were above imputed adopted values due to: 1) emergent work and 2) rescheduled work. The emergent work includes Spaulding Pressure Relief Valve Discharge Liner Replacement, Runner and Wicket Gate Replacement, Stanislaus Powerhouse Replace Thrust Bearing Cooling Coil, Kings River Replace Turbine Shut-off Valve. The rescheduled work includes Caribou Units 2-5 Generator Rewind, Bucks Creek Powerhouse Replace Unit 2 Turbine Bearing / Shaft, and Helms Units 1, 2 and 3 Replace Turbine Shut-off Valves. | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is a continuing effort to support capital costs to install/replace generating equipment or components to support hydroelectric generation activities.
432 | Capital | Power Generation | 2M | Instal/Repl Hydro Gneratng Eqp |  |  | Large Uncontrolled Water Release | M4 - LLO Refurbishments |  | Yes | N/A | N/A | 0 | 18.4121 | 18.4121 | 0 | 39.265 | 39.265 | 20.8529 | 20.8529 | 113.3% | 113.3% | N/A | N/A |  | N/A: N/A | N/A | N/A | N/A | N/A | N/A
433 | Capital | Power Generation | 2M | Instal/Repl Hydro Gneratng Eqp |  |  | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 5, Ch 4 | Yes | N/A | N/A | 84621.5813 | 92042.137 | 176663.7184 | 115907.7139 | 196286.6258 | 312194.3397 | 104244.4888 | 135530.6214 | 113.3% | 76.72% | N/A | N/A |  | N/A: N/A | N/A | N/A | N/A | N/A | N/A
434 | Capital | Power Generation | 2N | Instal/Repl Resv,Dams&Waterway |  |  | SRM Total | SRM Total | Ex 5, Ch 4 | No | On-going | annual | 42763.8477 | 30166.7524 | 72930.6001 | 46960.5066 | 102332.5806 | 149293.0872 | 72165.8282 | 76362.4872 | 239.2% | 104.7% | YES | YES |  | N/A: Program expenses were above imputed adopted values due to: 1) emergent work and 2) rescheduled work. The emergent work includes South Yuba Pipe Replacement, Lake Almanor Canyon Dam Low Level Outlet Replace Gate 1 Stem, and Courtright Dam Concrete Liner Repairs. The rescheduled work includes Courtright Dam Upgrade I/D Gate Control, J.B. Black Iron Canyon Dam Low Level Outlet Replace Actuator and Piping, Helms Install Incline Tunnel Liner, and Rock Creek Cresta Coffer Dam Installation. | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is a continuing effort to support capital costs to install/replace reservoirs, dams and waterways.
435 | Capital | Power Generation | 2N | Instal/Repl Resv,Dams&Waterway |  |  | Large Uncontrolled Water Release | C1 - Dam Safety Program | Ex 5, Ch 4, p. 4-78 | Yes | N/A | N/A | 0 | 199.1006 | 199.1006 | 1034.5864 | 675.3953 | 1709.9817 | 476.2947 | 1510.8811 | 239.2% | 758.9% | N/A | N/A |  | N/A: N/A | N/A | N/A | N/A | N/A | N/A
436 | Capital | Power Generation | 2N | Instal/Repl Resv,Dams&Waterway |  |  | Large Uncontrolled Water Release | M1 - Internal Erosion Mitigation | Ex 5, Ch 2, p. 2-13; p. WP 2-2 | Yes | N/A | N/A | 416.4343 | 2292.6732 | 2709.1075 | 3433.495 | 7777.2762 | 11210.7712 | 5484.6031 | 8501.6637 | 239.2% | 313.8% | N/A | N/A |  | N/A: N/A | N/A | N/A | N/A | N/A | N/A
437 | Capital | Power Generation | 2N | Instal/Repl Resv,Dams&Waterway |  |  | Large Uncontrolled Water Release | M2 - Spillway Remediation | Ex 5, Ch 2, p. 2-13; p. WP 2-2 | Yes | N/A | N/A | 173.4929 | 2190.1062 | 2363.5992 | 4727.3818 | 7429.3457 | 12156.7275 | 5239.2395 | 9793.1284 | 239.2% | 414.3% | N/A | N/A |  | N/A: N/A | N/A | N/A | N/A | N/A | N/A
438 | Capital | Power Generation | 2N | Instal/Repl Resv,Dams&Waterway |  |  | Large Uncontrolled Water Release | M3 - Seismic Retrofit | Ex 5, Ch 2, p. 2-13; p. WP 2-2 | Yes | N/A | N/A | 0 | 90.5003 | 90.5003 | 51.4262 | 306.9977 | 358.4239 | 216.4974 | 267.9237 | 239.2% | 296% | N/A | N/A |  | N/A: N/A | N/A | N/A | N/A | N/A | N/A
439 | Capital | Power Generation | 2N | Instal/Repl Resv,Dams&Waterway |  |  | Large Uncontrolled Water Release | M4 - LLO Refurbishments | Ex 5, Ch 2, p. 2-13; p. WP 2-2 | Yes | N/A | N/A | 8825.6029 | 8051.5062 | 16877.1091 | 8428.131 | 27312.5653 | 35740.6963 | 19261.0591 | 18863.5872 | 239.2% | 111.8% | N/A | N/A |  | N/A: N/A | N/A | N/A | N/A | N/A | N/A
440 | Capital | Power Generation | 2N | Instal/Repl Resv,Dams&Waterway |  |  | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 5, Ch 4, p. 4-78 | Yes | N/A | N/A | 33348.1037 | 17342.8659 | 50690.9696 | 29285.4841 | 58831.0003 | 88116.4845 | 41488.1344 | 37425.5148 | 239.2% | 73.83% | N/A | N/A |  | N/A: N/A | N/A | N/A | N/A | N/A | N/A
441 | Capital | Power Generation | 2P | Instl/Repl Hydr BldgGrndInfrst |  |  | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 5, Ch 4 | No | On-going | annual | 26624.6872 | 14275.4778 | 40900.1649 | 41827.1777 | 37028.1366 | 78855.3143 | 22752.6589 | 37955.1494 | 159.4% | 92.8% | YES | YES |  | N/A: Program expenses were above imputed adopted values due to emergent work. The emergent work includes DeSabla Powerhouse Road Improvements, Caribou Road Improvements, Pit 5 Powerhouse Road, Cedar Mill Property Purchase, Spaulding Tram Improvements, and Auburn Regional Service Center Power Generation Command Center. | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is a continuing effort to support capital costs to install/replace buildings, grounds and infrastructure to support hydroelectric generation activities, including roads and bridges.
442 | Capital | Power Generation | 2R | Instl/Rpl for Fosil Safety&Reg |  |  | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 5, Ch 4 | No | On-going | annual | 0 | 0 | 0 | 0 | 118.6012 | 118.6012 | 118.6012 | 118.6012 | 100.0% | 100.0% | NO | NO |  | N/A: Below variance threshold. | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
443 | Capital | Power Generation | 2S | Instal/Repl Fosil Gneratng Eqp |  |  | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 5, Ch 5 | No | On-going | annual | 0 | 5524.3601 | 5524.3601 | 0 | 17887.1264 | 17887.1264 | 12362.7663 | 12362.7663 | 223.8% | 223.8% | YES | YES |  | N/A: Program expenditures were above imputed adopted values due to: 1) the Humboldt Bay Generating Station annual capital outage program spend, driven by the continued wear and tear of the units, 2) the Humboldt Bay Generating Station UNIC engine control system upgrades, and 3) the Gateway Generating Station Main Steam Stop/Control Valve Replacement following a failure. | On-Target | On-Target | On-Target | Proceeding as planned | This program's work is ongoing and will continue in PG&E's 2023 GRC period. The purpose of this program is a continuing effort to support capital costs to install new or replace existing generating equipment or components to support fossil generation activities. As the fossil generating facilities age, the capital replacement costs accelerate.
444 | Capital | Power Generation | 2T | Instl/Repl Fosl BldgGrndInfrst |  |  | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 5, Ch 5 | No | On-going | annual | 0 | 108.9352 | 108.9352 | 0 | 1251.4916 | 1251.4916 | 1142.5564 | 1142.5564 | 1049% | 1049% | NO | NO |  | N/A: Below variance threshold. | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
445 | Capital | Power Generation | 3A | Instl/Rpl for AltGen Safty&Reg |  |  | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 5, Ch 5 | No | On-going | annual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100.0% | 100.0% | NO | NO |  | N/A: Below variance threshold. | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
446 | Capital | Power Generation | 3B | Instal/Repl AltGen GneratngEqp |  |  | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 5, Ch 5 | No | On-going | annual | 0 | 0 | 0 | 0 | 5307.5563 | 5307.5563 | 5307.5563 | 5307.5563 | 100.0% | 100.0% | NO | YES |  | N/A: Below variance threshold. | On-Target | On-Target | On-Target | Proceeding as Planned | N/A
447 | Capital | Power Generation | 3H | Hydroelec Lic & Lic Conditions |  |  | SRM Total | SRM Total | Ex 5, Ch 4 | No | On-going | annual | 145223.769 | 154204.4812 | 299428.2502 | 35356.672 | 40795.2604 | 76151.9324 | -113409.2207 | -223276.3178 | -73.54% | -74.57% | YES | YES |  | N/A: Program expenses were below imputed adopted values due to two key drivers: (1) a delay in the regulatory process related to FERC operating license renewals for the Drum-Spaulding license, McCloud-Pit license and the Upper North Fork Feather River license. Delays in license renewals create delays in the forecasted start date of the capital work required as part of the new operating license; and (2) rescheduled capital projects originating from the spillway assessment recommendations resulting from the 2017 Oroville spillway incident. The rescheduled projects include McCloud Spillway improvement and Tiger Creek Regulator Spillway Improvement. | Under | Under | Under | Rescheduled | This program's work is ongoing and will continue in PG&E's 2023 GRC period. Some work has been rescheduled to future GRC periods. The purpose of this program is a continuing effort to support capital costs assigned to the HLBA. This MWC includes: costs for relicensing existing FERC licenses; obtaining major license amendments; surrendering licenses for facilities that are no longer economic; complying with the conditions required by existing and newly issued FERC licenses and major license amendments; and anticipated to be required by pending new FERC licenses for licenses. This includes costs for all pending licenses as of January 1, 2014, and new licenses applied for after January 1, 2014. This MWC also includes the costs associated with work required because of the 2017 Oroville spillway incident.
448 | Capital | Power Generation | 3H | Hydroelec Lic & Lic Conditions |  |  | Large Uncontrolled Water Release | M2 - Spillway Remediation | Ex 5, Ch 2, p. 2-13; p. WP 2-2 | Yes | N/A | N/A | 73892.7582 | 81296.6025 | 155189.3606 | 18869.1714 | 21507.2614 | 40376.4328 | -59789.3411 | -114812.9278 | -73.54% | -73.98% | N/A | N/A |  | N/A: N/A | N/A | N/A | N/A | N/A | N/A
449 | Capital | Power Generation | 3H | Hydroelec Lic & Lic Conditions |  |  | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 5, Ch 4, p. 4-78 | Yes | N/A | N/A | 71329.5586 | 72907.8787 | 144237.4373 | 16477.501 | 19287.999 | 35765.5 | -53619.8797 | -108471.9373 | -73.54% | -75.2% | N/A | N/A |  | N/A: N/A | N/A | N/A | N/A | N/A | N/A
450 | Capital | Customer and Communications | 05 | Tools & Equipment |  |  | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 6, Ch 7 | No | On-going | Annual | 110.2381 | 114.6623 | 224.9004 | 71.6862 | 18.1785 | 89.8648 | -96.4838 | -135.0356 | -84.15% | -60.04% | NO | NO |  | N/A: Below variance threshold. | On-Target | On-Target | On-Target | Proceeding as planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The purpose of this program is to provide tools and equipment used by field technicians and meter repair facilities to perform field metering and meter repair activities.
451 | Capital | Customer and Communications | 25 | Install New Electric Meters |  |  | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 6, Ch 7 | No | On-going | Annual | 28992.0772 | 30279.0291 | 59271.1063 | 29176.1234 | 31533.7789 | 60709.9023 | 1254.7499 | 1438.796 | 4.144% | 2.427% | NO | NO |  | N/A: Below variance threshold. | On-Target | On-Target | On-Target | Proceeding as planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The purpose of this program is to provide new electric meter purchases for new customer growth, replacement of failed units, and the associated installation labor necessary to perform electric meter installations, exchanges, removals, and retirements.
452 | Capital | Customer and Communications | 3M | Install/Repl Var Bal Acct |  |  | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | NA - Emergent work, not included in 2023 GRC forecast | No | On-going | Annual | 0 | 0 | 0 | 5462.6678 | 11169.4029 | 16632.0706 | 11169.4029 | 16632.0706 | 100.0% | 100.0% | YES | YES |  | N/A: Program expenses exceeded imputed adopted annual costs of $0 due to emergent work which was not included in the 2023 GRC forecast. | Over | Over | Over | Emergent | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The purpose of this program is to perform wildfire risk mitigation work that is not otherwise recovered in PG&E’s adopted revenue requirements.
453 | Capital | Customer and Communications | 74 | Install New Gas Meters |  |  | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 6, Ch 7 | No | On-going | Annual | 82311.1995 | 83789.3819 | 166100.5814 | 68078.4142 | 61172.4603 | 129250.8745 | -22616.9217 | -36849.7069 | -26.99% | -22.19% | YES | YES |  | N/A: Decrease due to fewer gas meters purchased and replaced than planned. | On-Target | On-Target | Under | Proceeding as planned | This program’s work is ongoing and will continue in PG&E’s 2023 GRC period. The purpose of this program is to provide new gas meter purchases for new customer growth, replacement of failed units, and the associated installation labor necessary to perform gas meter installations, exchanges, removals and retirements.
454 | Capital | Shared Services | 21 | Miscellaneous Capital |  |  | SRM Total | SRM Total | Ex 7, Ch 1 | No | On-going | Annual | 0 | 0 | 0 | 0 | 1291.6975 | 1291.6975 | 1291.6975 | 1291.6975 | 100.0% | 100.0% | NO | NO |  | N/A: Below threshold variance. | On-Target | On-Target | On-Target | Proceeding as planned | N/A
455 | Capital | Shared Services | 21 | Miscellaneous Capital |  |  | Motor Vehicle Safety Incident (MTRSI) | In-Cab Cameras (MRTSI-M21) | Ex 7, Ch 1 | Yes | On-going | Annual | 0 | 0 | 0 | 0 | 1291.6975 | 1291.6975 | 1291.6975 | 1291.6975 | 100.0% | 100.0% | N/A | N/A |  | N/A: N/A | N/A | N/A | N/A | N/A | N/A
456 | Capital | Shared Services | 22 | Maintain Buildings |  |  | SRM Total | SRM Total | Ex 7, Ch 5 | No | On-going | Annual | 41008.5721 | 46002.0909 | 87010.6629 | 59406.8998 | 39823.8192 | 99230.719 | -6178.2717 | 12220.0561 | -13.43% | 14.04% | NO | NO |  | N/A: Below threshold variance. | On-Target | On-Target | On-Target | Proceeding as planned | N/A
457 | Capital | Shared Services | 22 | Maintain Buildings |  |  | Real Estate and Facilities Failure (REFFL) | Regional Optimization (REFFL-C001) | Ex 7, Ch 5 | Yes | On-going | Annual | 0 | 0 | 0 | 2730.3461 | 1.1421 | 2731.4883 | 1.1421 | 2731.4883 | 100.0% | 100.0% | N/A | N/A |  | N/A: N/A | N/A | N/A | N/A | N/A | N/A
458 | Capital | Shared Services | 22 | Maintain Buildings |  |  | Real Estate and Facilities Failure (REFFL) | Facilities Mgmt and Prevent Maint Prgm (REFFL-C004) | Ex 7, Ch 5 | Yes | On-going | Annual | 0 | 0 | 0 | 41175.7615 | 20440.0485 | 61615.81 | 20440.0485 | 61615.81 | 100.0% | 100.0% | N/A | N/A |  | N/A: N/A | N/A | N/A | N/A | N/A | N/A
459 | Capital | Shared Services | 22 | Maintain Buildings |  |  | Real Estate and Facilities Failure (REFFL) | Renovate / Relocate Facilities Other than SFGO (REFFL-M006) | Ex 7, Ch 5 | Yes | On-going | Annual | 0 | 0 | 0 | 6258.4091 | 418.9646 | 6677.3738 | 418.9646 | 6677.3738 | 100.0% | 100.0% | N/A | N/A |  | N/A: N/A | N/A | N/A | N/A | N/A | N/A
460 | Capital | Shared Services | 22 | Maintain Buildings |  |  | Real Estate and Facilities Failure (REFFL) | Service Center Optimization (REFFL-C002) | Ex 7, Ch 5 | Yes | On-going | Annual | 0 | 0 | 0 | 8746.853 | 510.937 | 9257.79 | 510.937 | 9257.79 | 100.0% | 100.0% | N/A | N/A |  | N/A: N/A | N/A | N/A | N/A | N/A | N/A
461 | Capital | Shared Services | 22 | Maintain Buildings |  |  | Real Estate and Facilities Failure (REFFL) | Security System Hardening (REFFL-C008) | Ex 7, Ch 5 | Yes | On-going | Annual | 0 | 0 | 0 | 0 | 2829.5295 | 2829.5295 | 2829.5295 | 2829.5295 | 100.0% | 100.0% | N/A | N/A |  | N/A: N/A | N/A | N/A | N/A | N/A | N/A
462 | Capital | Shared Services | 22 | Maintain Buildings |  |  | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 7, Ch 5 | No | On-going | Annual | 0 | 0 | 0 | 495.53 | 15623.1962 | 16118.7262 | 15623.1962 | 16118.7262 | 100.0% | 100.0% | N/A | N/A |  | N/A: N/A | N/A | N/A | N/A | N/A | N/A
463 | Capital | Shared Services | 23 | Implement RealEstate Strategy |  |  | SRM Total | SRM Total | Ex 7, Ch 5 | No | On-going | Annual | 99788.265 | 155877.5885 | 255665.8535 | 68462.1439 | 131413.592 | 199875.7359 | -24463.9965 | -55790.1177 | -15.69% | -21.82% | YES | NO |  | N/A: Program expenditures were below imputed regulatory values due to work forecast and adopted across both MWC 22 and MWC 23 but executed in MWC 22 more than in MWC 23. Other drivers include a credit received in the General Office Sale Memorandum Account (GOSMA) for re-scheduled capital work which was partially offset by ongoing efforts in Service Center Investments, specifically Stockton properties, as well as Regionalization improvements in the Merced Warehouse and Napa Regional center. | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC. The purpose of this program is to focus on the purchase and acquisition of facilities, associated land, and required infrastructure to operationalize new facilities. In addition, this program develops and deploys the strategy to optimize the real estate portfolio at the company level. The majority of these investments are in support of reducing the Real Estate and Facilities Failure risk.
464 | Capital | Shared Services | 23 | Implement RealEstate Strategy |  |  | Real Estate and Facilities Failure (REFFL) | Regional Optimization (REFFL-C001) | Ex 7, Ch 5 | Yes | On-going | Annual | 0 | 0 | 0 | 62494.5216 | 22697.0316 | 85191.5532 | 22697.0316 | 85191.5532 | 100.0% | 100.0% | N/A | N/A |  | N/A: N/A | N/A | N/A | N/A | N/A | N/A
465 | Capital | Shared Services | 23 | Implement RealEstate Strategy |  |  | Real Estate and Facilities Failure (REFFL) | Facilities Mgmt and Prevent Maint Prgm (REFFL-C004) | Ex 7, Ch 5 | Yes | On-going | Annual | 0 | 0 | 0 | 2185.2332 | 10759.6198 | 12944.853 | 10759.6198 | 12944.853 | 100.0% | 100.0% | N/A | N/A |  | N/A: N/A | N/A | N/A | N/A | N/A | N/A
466 | Capital | Shared Services | 23 | Implement RealEstate Strategy |  |  | Real Estate and Facilities Failure (REFFL) | Renovate / Relocate Facilities Other than SFGO (REFFL-M006) | Ex 7, Ch 5 | Yes | On-going | Annual | 0 | 0 | 0 | 10174.93 | 47330.5298 | 57505.4597 | 47330.5298 | 57505.4597 | 100.0% | 100.0% | N/A | N/A |  | N/A: N/A | N/A | N/A | N/A | N/A | N/A
467 | Capital | Shared Services | 23 | Implement RealEstate Strategy |  |  | Real Estate and Facilities Failure (REFFL) | Service Center Optimization (REFFL-C002) | Ex 7, Ch 5 | Yes | On-going | Annual | 0 | 0 | 0 | 17050.0005 | 36591.3673 | 53641.3678 | 36591.3673 | 53641.3678 | 100.0% | 100.0% | N/A | N/A |  | N/A: N/A | N/A | N/A | N/A | N/A | N/A
468 | Capital | Shared Services | 23 | Implement RealEstate Strategy |  |  | Real Estate and Facilities Failure (REFFL) | Security System Hardening (REFFL-C008) | Ex 7, Ch 5 | Yes | On-going | Annual | 0 | 0 | 0 | 6123.0415 | 2912.5757 | 9035.6172 | 2912.5757 | 9035.6172 | 100.0% | 100.0% | N/A | N/A |  | N/A: N/A | N/A | N/A | N/A | N/A | N/A
469 | Capital | Shared Services | 23 | Implement RealEstate Strategy |  |  | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 7, Ch 5 | No | On-going | Annual | 0 | 0 | 0 | -29565.5829 | 11122.4674 | -18443.1155 | 11122.4674 | -18443.1155 | 100.0% | 100.0% | N/A | N/A |  | N/A: N/A | N/A | N/A | N/A | N/A | N/A
470 | Capital | Shared Services | 2F | Build IT Apps & Infra |  |  | SRM Total | SRM Total | Ex 7, Ch 7 Ex 7, Ch 9 | No | On-going | Annual | 36141.56 | 39770.6194 | 75912.1794 | 36316.206 | 31151.707 | 67467.913 | -8618.9124 | -8444.2664 | -21.67% | -11.12% | NO | NO |  | N/A: Below threshold variance. | On-Target | On-Target | On-Target | Proceeding as planned | N/A
471 | Capital | Shared Services | 2F | Build IT Apps & Infra |  |  | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 7, Ch 1 Ex 7, Ch 2 Ex 7, Ch 6 | No | On-going | Annual | 0 | 0 | 0 | 4891.2257 | 5027.912 | 9919.1377 | 5027.912 | 9919.1377 | 100.0% | 100.0% | N/A | N/A |  | N/A: N/A | N/A | N/A | N/A | N/A | N/A
472 | Capital | Shared Services | 2F | Build IT Apps & Infra |  |  | Records and Information Management (RECIM) | Unstructured Mitigations (RECIM-M007) | Ex 7, Ch 7 | Yes | On-going | Annual | 0 | 0 | 0 | 0 | 6055.7104 | 6055.7104 | 6055.7104 | 6055.7104 | 100.0% | 100.0% | N/A | N/A |  | N/A: N/A | N/A | N/A | N/A | N/A | N/A
473 | Capital | Shared Services | 2F | Build IT Apps & Infra |  |  | Cyber Security Incident (CYBER) | Identify (CYBER-M001) | Ex 7, Ch 9 | Yes | On-going | Annual | 0 | 0 | 0 | 1509.819 | 332.091 | 1841.91 | 332.091 | 1841.91 | 100.0% | 100.0% | N/A | N/A |  | N/A: N/A | N/A | N/A | N/A | N/A | N/A
474 | Capital | Shared Services | 2F | Build IT Apps & Infra |  |  | Cyber Security Incident (CYBER) | Protect (CYBER-M002) | Ex 7, Ch 9 | Yes | On-going | Annual | 0 | 0 | 0 | 24702.81 | 14364.807 | 39067.617 | 14364.807 | 39067.617 | 100.0% | 100.0% | N/A | N/A |  | N/A: N/A | N/A | N/A | N/A | N/A | N/A
475 | Capital | Shared Services | 2F | Build IT Apps & Infra |  |  | Cyber Security Incident (CYBER) | Detect (CYBER-M003) | Ex 7, Ch 9 | Yes | On-going | Annual | 0 | 0 | 0 | 1533.962 | 4605.314 | 6139.276 | 4605.314 | 6139.276 | 100.0% | 100.0% | N/A | N/A |  | N/A: N/A | N/A | N/A | N/A | N/A | N/A
476 | Capital | Shared Services | 2F | Build IT Apps & Infra |  |  | Cyber Security Incident (CYBER) | Respond (CYBER-M004) | Ex 7, Ch 9 | Yes | On-going | Annual | 0 | 0 | 0 | 3678.389 | 765.873 | 4444.262 | 765.873 | 4444.262 | 100.0% | 100.0% | N/A | N/A |  | N/A: N/A | N/A | N/A | N/A | N/A | N/A
477 | Capital | Shared Services | 3N | Security Install/Replace |  |  | SRM Total | SRM Total | Ex 7, Ch 9 | No | On-going | Annual | 14690.3288 | 15279.8983 | 29970.2271 | 11808.9614 | 21858.888 | 33667.8494 | 6578.9897 | 3697.6222 | 43.06% | 12.34% | NO | NO |  | N/A: Below threshold variance. | On-Target | On-Target | On-Target | Proceeding as planned | N/A
478 | Capital | Shared Services | 3N | Security Install/Replace |  |  | Physical Attack (PHYSA) | Prevent (PHYSA-M001) | Ex 7, Ch 9 | Yes | On-going | Annual | 0 | 0 | 0 | 8313.636 | 5986.18 | 14299.816 | 5986.18 | 14299.816 | 100.0% | 100.0% | N/A | N/A |  | N/A: N/A | N/A | N/A | N/A | N/A | N/A
479 | Capital | Shared Services | 3N | Security Install/Replace |  |  | Physical Attack (PHYSA) | Detect (PHYSA-M002) | Ex 7, Ch 9 | Yes | On-going | Annual | 0 | 0 | 0 | 3495.3254 | 15872.708 | 19368.0334 | 15872.708 | 19368.0334 | 100.0% | 100.0% | N/A | N/A |  | N/A: N/A | N/A | N/A | N/A | N/A | N/A
480 | Capital | IT | 2F | Build IT Apps & Infra |  |  | SRM Total | SRM Total | Ex 7, Ch 8 | No | On-going | Annual | 286508.8139 | 298007.3224 | 584516.1363 | 245521.0151 | 361196.3943 | 606717.4094 | 63189.0719 | 22201.2731 | 21.2% | 3.798% | YES | YES |  | N/A: Program expenditures were above imputed regulatory values due to enterprise design costs for the Propel program which will upgrade, advance and improve PG&E's SAP system and related processes. This scope goes beyond a standard technology upgrade and optimzes the way the system is used. Other key drivers of the variance include increased investment in software application upgrades, capital licensing agreements, and data center infrastructure resiliency (ITAFL-M005). | On-Target | On-Target | On-Target | Proceeding as Planned | This program's work is ongoing and will continue in PG&E's 2023 GRC. The purpose of this program is to address the ongoing development and deployment of software and hardware technology solutions, the majority of the program will focus spend on mitigation investments to improve the IT Asset Failure risk.
481 | Capital | IT | 2F | Build IT Apps & Infra |  |  | IT Asset Failure (ITAFL) | Lifecycle Obsolete and Low Health #Assets (ITAFL-M004) | Ex 7, Ch 8 | Yes | On-going | Annual | 0 | 0 | 0 | 86042 | 130354.901 | 216396.901 | 130354.901 | 216396.901 | 100.0% | 100.0% | N/A | N/A |  | N/A: N/A | N/A | N/A | N/A | N/A | N/A
482 | Capital | IT | 2F | Build IT Apps & Infra |  |  | IT Asset Failure (ITAFL) | Multi-Faceted Mitigations (ITAFL-M005) | Ex 7, Ch 8 | Yes | On-going | Annual | 0 | 0 | 0 | 61471 | 74737.767 | 136208.767 | 74737.767 | 136208.767 | 100.0% | 100.0% | N/A | N/A |  | N/A: N/A | N/A | N/A | N/A | N/A | N/A
483 | Capital | IT | 2F | Build IT Apps & Infra |  |  | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 7, Ch 8 | No | On-going | Annual | 0 | 0 | 0 | 98007.7 | 156103.727 | 254111.427 | 156103.727 | 254111.427 | 100.0% | 100.0% | N/A | N/A |  | N/A: N/A | N/A | N/A | N/A | N/A | N/A
484 | Capital | Human Resources | 5 | PG&E Academy |  |  | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 8, Ch 6 | No | On-going | Annual | 30.6219 | 31.8509 | 62.4728 | 21.5596 | 78.9011 | 100.4607 | 47.0502 | 37.9878 | 147.7% | 60.81% | NO | NO |  | N/A: Below variance threshold. | Target | Target | Target | Proceeding as Planned | N/A
485 | Capital | Human Resources | 22 | PG&E Academy |  |  | SRM Total (Non-RAMP) | SRM Total (Non-RAMP) | Ex 8, Ch 6 | No | On-going | Annual | 1071.759 | 1114.7721 | 2186.5311 | 517.508 | 2535.1305 | 3052.6385 | 1420.3584 | 866.1074 | 127.4% | 39.61% | NO | NO |  | N/A: Below variance threshold. | Target | Target | Target | Proceeding as Planned | N/A
(a) Consolidated tables do not include footnotes from the 2024 RSAR.
(b) Shaded cells reflect areas that were not included in the 2024 RSAR tables because they did not apply for that Functional Area.