## SampleBudget
Equity and Access Grant Budget Table
To be used for both Equity, Engagement, and Education and Clean Energy Access Grant Accounts
Task Number | Budget Item | Explanation | Rate | Unit | Number of Units | Cost
Objective1 | Develop plan to build capacity to engage on the Distributed Energy Resources proceeding by hiring legal consultant and educating organizing staff
Task 1.1 | Hire legal consultant to become party to proceeding and organize internal staff team to keep track of proceeding
| Gordon Wu, Executive Director | 5 hours/week x 50 weeks @ $30/hour | 30 | hour | 250 | 7500
| Miriam Hernandez, Policy Director | 25 hours/week x 2 weeks @ $20 hour | 20 | hour | 50 | 1000
| Penelope Marbella, HR Director | 6 hours/week x 6 weeks @ $25/hour | 25 | hour | 36 | 900
Task 1.2 | Train community organizers on DER proceeding and plan community outreach
| Consultant: Melanie Harris, Trainer | 8 hours/week x 1 week @ $20/hour | 40 | hour | 8 | 320
| Sam Cachu, Senior Community Organizer | 25 hours/week x 50 weeks @ $18 hour | 18 | hour | 1250 | 22500
Task 1.3 | Prepare and conduct meeting with 20 interested community residents and informed youth educators
| George Williams, Organizing Director | 8 hours/week x 20 weeks @ $17.00/hour | 17 | hour | 160 | 2720
Objective 2 | Become Party to DER Proceeding
Task 2.1 | Submit paperwork and prepare to submit comments
| Imelda Jackson, Attorney | 20 hours/week x 1 weeks @ $175/hour | 175 | hour | 20 | 3500
| Miriam Hernandez, Policy Director | 15 hours/week x 2 weeks @ $20 hour | 20 | hour | 30 | 600
Objective 3 | Develop and Disseminate Outreach Collateral
Task 3.1 | Develop and Design 6"x 11" postcard
| Graham Singer, Graphic Designer | 3 hours/week x 1 week @ $50/hour | 50 | hour | 3 | 150
0
|  |  | Total Grant Budget |  |  | 39040

## Budget_Blank
California Public Utilities Commission, Equity, Engagement, and Eduction Grant Account
Detailed Budget Request
Task Number | Budget Item | Explanation | Rate | Unit | Number of Units | Cost
Objective 1
Task 1.1 | [5 empty] | 0
0
0
0
0
0
0
0
0
0
Objective 2
Task 2.1 | [5 empty] | 0
0
0
0
0
0
0
0
0
|  |  |  | TOTAL BUDGET |  | 0

## Sample Workplan Template
Equity and Access Grant Work Plan
To be used for both Equity, Engagement, and Education and Clean Energy Access Grant Accounts
Task Number | Activities to Accomplish Stated Goals | Project Staff Involved | Start Date | End Date | Performance Measures (used to measure goals) | Expected Outcomes (The outcomes you get when accomplishing your goals)
Goal 1 | Build Legal Capacity | Ben Kinney, Executive Director |  |  | Hire one in-house attorney and build a new regulatory function for our organization. | Our organization will become a Party to MIP Proceeding and will file reply comments.
Task 1.1 | Draft Scope of Work | Ben Kinney, Executive Director | 2023-07-07 | 2023-07-12
| Interview attonreys and consultants | Ben Kinney, Executive Director, Concepcion Rui, Chair of the Board | 2023-07-18 | 2023-08-06
| Hire legal resource | Ben Kinney, Executive Director, Concepcion Rui, Chair of the Board | 2023-08-10 | 2023-08-15
| Create plan for CPUC engagement with new legal resource | Ben Kinney, Executive Director | 2023-08-24 | 2023-08-26
Task 1.2
Task 1.3
Goal 2 | Build Staff Capacity to educate community on CPUC proceedings | Darla Ramirez, Organizing Director |  |  | Trained 5 organizers to educate the community on active proceedings | The community will become aware and educated on the High DER proceeding and will provide input on the impacts of the proposed regulations.
Task 2.1 | Hold 2 staff trainings on High DER Proceeding | Darla Ramirez, Organizing Director | 2023-08-21 | 2023-09-15
Task 2.2 | Hold 2 staff trainings on Microgrid Icentive Program Proceeding | Darla Ramirez, Organizing Director | 2023-08-08 | 2023-09-26
Task 2.3 | Prepare community materials and presentation | Darla Ramirez, Organizing Director
Goal 3
Task 3.1

## WorkPlan_Blank
Equity and Access Grant Work Plan
To be used for both Equity, Engagement, and Education and Clean Energy Access Grant Accounts
Task Number | Activities to Accomplish Stated Goals | Project Staff Involved | Start Date | End Date | Performance Measures (used to measure goals) | Expected Outcomes (The outcomes you get when accomplishing your goals)
Goal 1
Task 1.1
Task 1.2
Task 1.3
Goal 2
Task 2.1
Task 2.2
Task 2.3
Goal 3
Task 3.1