## Sample Workplan Template
Clean Energy Access: Los Angeles County TECH Grant Work Plan
Task Number | Activities to Accomplish Stated Goals | Project Staff Involved | Start Date | End Date | Performance Measures (used to measure goals) | Expected Outcomes (The outcomes you get when accomplishing your goals)
Goal 1 | Build Staff Knowledge of building decarbonization, healthy homes, and TECH |  |  |  |  | Community members can consult qualified outreach staff, able to provide detailed explanations of building decarbonization, healthy homes, and TECH Initiative rules, processses, and benefits.
Task 1.1 | Draft Scope of Work | Ben Kinney, Executive Director | 2026-01-01 | 2026-01-15 | Scope of work completed on time | 2 qualified outreach assistants hired and prepared to conduct outreach and education
| Interviews for outreach assistants | Ben Kinney, Executive Director; Concepcion Rui, Chair of the Board | 2026-01-18 | 2026-01-31 | Number of interviews held
| Hire 2 outreach assistants | Ben Kinney, Executive Director; Concepcion Rui, Chair of the Board | 2026-02-01 | 2026-02-15 | Number of Outreach Assistants Hired and Trained by End of March
| Training 2 new outreach assistants | Anny Adams, Outreach Manager; Adalie Amarro, Outreach Associate; 2 new outreach assistants | 2026-02-15 | 2026-03-31 | Hours of training
Task 1.2 | In-depth staff research on building decarbonization, healthy homes, heat pumps, and TECH | Anny Adams, Outreach Manager; Adalie Amarro, Outreach Associate; 2 new outreach assistants | 2026-01-01 | 2026-03-07 | Summary report from staff | Staff become knowledgeable about TECH and identify relevant topics for community and topics in need of clarification
| Meet with Energy Solutions staff | Anny Adams, Outreach Manager; Adalie Amarro, Outreach Associate; 2 new outreach assistants | 2026-03-07 | 2026-03-14 | Meeting held with Energy Solutions | Staff knowledge gaps filled
Goal 2 | Create, Conduct, and Evaluate Educational Workshop Series | Darla Ramirez, Organizing Director |  |  | Trained 5 organizers to educate the community on active proceedings | The community will become aware and educated on the High DER proceeding and will provide input on the impacts of the proposed regulations.
Task 2.1 | Secure venues for educational workshops | Anny Adams, Outreach Manager | 2026-03-14 | 2026-03-31
Task 2.2 | Create educational presentations and followup surveys | Adalie Amarro, Outreach Associate; Outreach Assisant #1 | 2026-04-01 | 2026-04-30
Task 2.3 | Continuous review and updates of workshop materials and structure | Adalie Amarro, Outreach Associate; Outreach Assisant #1 | 2026-05-15 | 2026-08-15
Task 2.4 | Create marketing materials (flyers, registration pages, etc) | Adalie Amarro, Outreach Associate; Outreach Assisant #1 | 2026-04-15 | 2026-04-23
Task 2.5 | Market educational workshops | Adalie Amarro, Outreach Associate; Outreach Assisant #1 | 2026-04-23 | 2026-08-01
Task 2.6 | Hold 6 educational workshops | Anny Adams, Outreach Manager; Adalie Amarro, Outreach Associate; Outreach Assistant #1 | 2026-05-15 | 2026-08-15
Task 2.7 | Conduct 3-month followup surveys | Adalie Amarro, Outreach Associate; Outreach Assisant #1 | Month 8 | Month 10
Task 2.8 | Conduct 6-month followup surveys | Adalie Amarro, Outreach Associate; Outreach Assisant #1 | Month 11 | Month 14
Task 2.9 | Write summary report analyzing workshop series success and survey data | Anny Adams, Outreach Manager; Adalie Amarro, Outreach Associate; Outreach Assistant #1 | Month 5 | Month 15
Goal 3 | Create, Conduct, and Evaluate Door-to-Door Outreach
Task 3.1
Goal 3 | Provide Follow-Up Support for Education and Outreach Participants pursuing a TECH incentive
Task 4.1
*Start and end dates for each task may be specific or written in a generalized fashion to accommodate different start dates. See rows 17-19 for an example.

## WorkPlan_Blank
Clean Energy Access: Los Angeles County TECH Grant Work Plan
Task Number | Activities to Accomplish Stated Goals | Project Staff Involved | Start Date | End Date | Performance Measures (used to measure goals) | Expected Outcomes (The outcomes you get when accomplishing your goals)
Goal 1
Task 1.1
Task 1.2
Task 1.3
Goal 2
Task 2.1
Task 2.2
Task 2.3
Goal 3
Task 3.1

## SampleBudget
Clean Energy Access: Los Angeles County TECH Grant Budget Table
Task Number | Budget Item | Explanation | Rate | Unit | Number of Units | Cost
Goal 1 | Develop plan to build capacity to educate on TECH by hiring consultant and educating organizing staff
Task 1.1 | Hire consultant to provide expertise on buidling decarbonization and heat pump technology
| Gordon Wu, Executive Director | 5 hours/week x 50 weeks @ $30/hour | 30 | hour | 250 | 7500
| Miriam Hernandez, Policy Director | 25 hours/week x 2 weeks @ $20 hour | 20 | hour | 50 | 1000
| Penelope Marbella, HR Director | 6 hours/week x 6 weeks @ $25/hour | 25 | hour | 36 | 900
Task 1.2 | Train community organizers and plan community outreach
| Consultant: Melanie Harris, Trainer | 8 hours/week x 1 week @ $20/hour | 40 | hour | 10 | 400
| Sam Cachu, Senior Community Organizer | 25 hours/week x 50 weeks @ $18 hour | 18 | hour | 1250 | 22500
Task 1.3 | Prepare and conduct meeting with 20 interested community residents and informed youth educators
| George Williams, Organizing Director | 8 hours/week x 20 weeks @ $17.00/hour | 17 | hour | 180 | 3060
| Travel Stipends | Cover travel to encourage attendee participation | 10 | participant | 20 | 200
| Printed surveys | Surveys to gather feedback and data from participants | 1 | participant | 20 | 20
| Stipend for attendance and completion of survey | Participant compensation for community work product | 25 | participant | 20 | 500
Goal 2 | Educate Building Owners and their Residents on Tenant Rights, Healthy Homes Standards, Heat Pumps and Building Decarbonization, and the TECH Initiative
Task 2.1 | Prepare materials for building owners
| Imelda Jackson, Attorney | 20 hours/week x 1 weeks @ $175/hour | 175 | hour | 22 | 3850
| Miriam Hernandez, Policy Director | 15 hours/week x 2 weeks @ $20 hour | 20 | hour | 30 | 600
Task 2.2 | Prepare materials for tenants
Goal 3 | Develop and Disseminate Outreach Collateral
Task 3.1 | Develop and Design 6"x 11" postcard
| Graham Singer, Graphic Designer | 3 hours/week x 1 week @ $50/hour | 50 | hour | 3 | 150
| Postcards |  | 0.75 | cards | 200 | 150
Indirect costs (15%)
| Payroll staff and systems, rent, etc |  |  |  |  | 6124.5
|  |  | Total Grant Budget |  |  | 46954.5

## Budget_Blank
Clean Energy Access: Los Angeles County TECH Grant
Detailed Budget Request
Task Number | Budget Item | Explanation | Rate | Unit | Number of Units | Cost
Goal 1
Task 1.1 | [5 empty] | 0
0
0
0
0
0
0
0
0
0
Goal 2
Task 2.1 | [5 empty] | 0
0
0
0
0
0
0
0
0
|  |  |  | TOTAL BUDGET |  | 0