## CA FHCA
2020 California Fire Tracker
Every Year
District | Forester | Fire Threat | Work ID | Substation | Work ID Description | Work Code | DST-DHS scheduled work current yr | Work Code Discription | Miles | Inspection Miles Complete | % of Inspections Complete | Miles Complete | % Complete
Yreka | Phillips | 2 | 4G1 | Shastina | Lake | FIN | DST | Fire Inspection | 26.12 | 26.12 | 100%
Yreka | Phillips | 2 | 4G1 | Shastina | Lake | FMD | DST | Fire Mitigation Distribution | 26.12 |  |  | 26.12 | 100%
Yreka | Phillips | 2 | 4G1 | Shastina | Lake | FOD |  | Fire Overhang Distribution
Yreka | Phillips | 2 | 4G1 | Shastina | Lake | FPD
Yreka | Phillips | 2 | 4G1 | Shastina | Lake | LRA |  | Local Response Area Fire Pole Clearing
Yreka | Phillips | 2 | 5G1 | Ft Jones | Greenview | FIN | DST | Fire Inspection | 53.71 | 53.71 | 100%
Yreka | Phillips | 2 | 5G1 | Ft Jones | Greenview | FMD | DST | Fire Mitigation Distribution | 53.71 |  |  | 53.71 | 100%
Yreka | Phillips | 2 | 5G1 | Ft Jones | Greenview | FOD |  | Fire Overhang Distribution
Yreka | Phillips | 2 | 5G1 | Ft Jones | Greenview | FPD
Yreka | Phillips | 2 | 5G1 | Ft Jones | Greenview | LRA |  | Local Response Area Fire Pole Clearing
Yreka | Phillips | 2 | 5G14 | Happy Camp | Mill | FIN | DST | Fire Inspection | 4.59 | 4.59 | 100%
Yreka | Phillips | 2 | 5G14 | Happy Camp | Mill | FMD | DST | Fire Mitigation Distribution | 4.59 |  |  | 4.59 | 100%
Yreka | Phillips | 2 | 5G14 | Happy Camp | Mill | FOD |  | Fire Overhang Distribution
Yreka | Phillips | 2 | 5G14 | Happy Camp | Mill | FPD |  |  | 4.59 | 4.59 | 100% | 4.59 | 100%
Yreka | Phillips | 2 | 5G14 | Happy Camp | Mill | LRA |  | Local Response Area Fire Pole Clearing
Yreka | Phillips | 2 | 5G149 | Yreka | Highland | FIN | DST | Fire Inspection | 53.86 | 53.86 | 100%
Yreka | Phillips | 2 | 5G149 | Yreka | Highland | FMD | DST | Fire Mitigation Distribution | 53.86 |  |  | 53.86 | 100%
Yreka | Phillips | 2 | 5G149 | Yreka | Highland | FOD |  | Fire Overhang Distribution
Yreka | Phillips | 2 | 5G149 | Yreka | Highland | FPD
Yreka | Phillips | 2 | 5G149 | Yreka | Highland | LRA |  | Local Response Area Fire Pole Clearing
Yreka | Phillips | 2 | 5G151 | Yreka | Center Town | FIN | DHS | Fire Inspection | 9.73 | 9.73 | 100%
Yreka | Phillips | 2 | 5G151 | Yreka | Center Town | FMD | DHS | Fire Mitigation Distribution | 9.73 |  |  | 9.73 | 100%
Yreka | Phillips | 2 | 5G151 | Yreka | Center Town | FOD |  | Fire Overhang Distribution
Yreka | Phillips | 2 | 5G151 | Yreka | Center Town | FPD
Yreka | Phillips | 2 | 5G151 | Yreka | Center Town | LRA |  | Local Response Area Fire Pole Clearing
Yreka | Phillips | 2 | 5G16 | Happy Camp | Town | FIN | DHS | Fire Inspection | 36.89 | 36.89 | 100%
Yreka | Phillips | 2 | 5G16 | Happy Camp | Town | FMD | DHS | Fire Mitigation Distribution | 36.89 |  |  | 36.89 | 100%
Yreka | Phillips | 2 | 5G16 | Happy Camp | Town | FOD |  | Fire Overhang Distribution
Yreka | Phillips | 2 | 5G16 | Happy Camp | Town | FPD |  |  | 36.89 | 36.89 | 100% | 36.89 | 100%
Yreka | Phillips | 2 | 5G16 | Happy Camp | Town | LRA |  | Local Response Area Fire Pole Clearing
Yreka | Phillips | 2 | 5G163 | Yreka | Lennox | FIN | DHS | Fire Inspection | 11.19 | 11.19 | 100%
Yreka | Phillips | 2 | 5G163 | Yreka | Lennox | FMD | DHS | Fire Mitigation Distribution | 11.19 |  |  | 11.19 | 100%
Yreka | Phillips | 2 | 5G163 | Yreka | Lennox | FOD |  | Fire Overhang Distribution
Yreka | Phillips | 2 | 5G163 | Yreka | Lennox | FPD
Yreka | Phillips | 2 | 5G163 | Yreka | Lennox | LRA |  | Local Response Area Fire Pole Clearing
Yreka | Phillips | 2 | 5G19 | Hornbrook | Town | FIN |  | Fire Inspection | 96.6 | 96.6 | 100%
Yreka | Phillips | 2 | 5G19 | Hornbrook | Town | FMD |  | Fire Mitigation Distribution | 96.6 |  |  | 96.6 | 100%
Yreka | Phillips | 2 | 5G19 | Hornbrook | Town | FOD |  | Fire Overhang Distribution
Yreka | Phillips | 2 | 5G19 | Hornbrook | Town | FPD
Yreka | Phillips | 2 | 5G19 | Hornbrook | Town | LRA |  | Local Response Area Fire Pole Clearing
Yreka | Phillips | 2 | 5G2 | Ft Jones | Peach Orchrd | FIN |  | Fire Inspection | 87.45 | 87.45 | 100%
Yreka | Phillips | 2 | 5G2 | Ft Jones | Peach Orchrd | FMD |  | Fire Mitigation Distribution | 87.45 |  |  | 87.45 | 100%
Yreka | Phillips | 2 | 5G2 | Ft Jones | Peach Orchrd | FOD |  | Fire Overhang Distribution
Yreka | Phillips | 2 | 5G2 | Ft Jones | Peach Orchrd | FPD
Yreka | Phillips | 2 | 5G2 | Ft Jones | Peach Orchrd | LRA |  | Local Response Area Fire Pole Clearing
Yreka | Phillips | 2 | 5G21 | Lucerne | Gazelle Grda | FIN |  | Fire Inspection | 77.2 | 77.2 | 100%
Yreka | Phillips | 2 | 5G21 | Lucerne | Gazelle Grda | FMD |  | Fire Mitigation Distribution | 77.2 |  |  | 77.2 | 100%
Yreka | Phillips | 2 | 5G21 | Lucerne | Gazelle Grda | FOD |  | Fire Overhang Distribution
Yreka | Phillips | 2 | 5G21 | Lucerne | Gazelle Grda | FPD
Yreka | Phillips | 2 | 5G21 | Lucerne | Gazelle Grda | LRA |  | Local Response Area Fire Pole Clearing
Yreka | Phillips | 2 | 5G23 | Big Springs | White Mt | FIN | DHS | Fire Inspection | 96.74 | 96.74 | 100%
Yreka | Phillips | 2 | 5G23 | Big Springs | White Mt | FMD | DHS | Fire Mitigation Distribution | 96.74 |  |  | 96.74 | 100%
Yreka | Phillips | 2 | 5G23 | Big Springs | White Mt | FOD |  | Fire Overhang Distribution
Yreka | Phillips | 2 | 5G23 | Big Springs | White Mt | FPD
Yreka | Phillips | 2 | 5G23 | Big Springs | White Mt | LRA |  | Local Response Area Fire Pole Clearing
Yreka | Phillips | 2 | 5G39 | Seiad | Seiad Creek | FIN | DHS | Fire Inspection | 24.83 | 24.83 | 100%
Yreka | Phillips | 2 | 5G39 | Seiad | Seiad Creek | FMD | DHS | Fire Mitigation Distribution | 24.83 |  |  | 24.83 | 100%
Yreka | Phillips | 2 | 5G39 | Seiad | Seiad Creek | FOD |  | Fire Overhang Distribution
Yreka | Phillips | 2 | 5G39 | Seiad | Seiad Creek | FPD |  |  | 24.83 | 24.83 | 100% | 24.83 | 100%
Yreka | Phillips | 2 | 5G39 | Seiad | Seiad Creek | LRA |  | Local Response Area Fire Pole Clearing
Yreka | Phillips | 2 | 5G40 | Scott Bar | Scott Bar | FIN |  | Fire Inspection | 60.9 | 60.9 | 100%
Yreka | Phillips | 2 | 5G40 | Scott Bar | Scott Bar | FMD |  | Fire Mitigation Distribution | 60.9 |  |  | 60.9 | 100%
Yreka | Phillips | 2 | 5G40 | Scott Bar | Scott Bar | FOD |  | Fire Overhang Distribution
Yreka | Phillips | 2 | 5G40 | Scott Bar | Scott Bar | FPD
Yreka | Phillips | 2 | 5G40 | Scott Bar | Scott Bar | FRD |  | Fire Row Mitigation
Yreka | Phillips | 2 | 5G40 | Scott Bar | Scott Bar | LRA |  | Local Response Area Fire Pole Clearing
Yreka | Phillips | 2 | 5G41 | Walker-Bryan | Etna Tie | FIN | DST | Fire Inspection | 87.63 | 87.63 | 100%
Yreka | Phillips | 2 | 5G41 | Walker-Bryan | Etna Tie | FMD | DST | Fire Mitigation Distribution | 87.63 |  |  | 65 | 74.18%
Yreka | Phillips | 2 | 5G41 | Walker-Bryan | Etna Tie | FOD |  | Fire Overhang Distribution
Yreka | Phillips | 2 | 5G41 | Walker-Bryan | Etna Tie | FPD |  |  | 87.63 | 87.63 | 100% | 87.63 | 100%
Yreka | Phillips | 2 | 5G41 | Walker-Bryan | Etna Tie | LRA |  | Local Response Area Fire Pole Clearing
Mt Shasta | Phillips | 3 | 5G45 | Weed | Shastina | FIN | DST | Fire Inspection | 8.1 | 8.1 | 100%
Mt Shasta | Phillips | 3 | 5G45 | Weed | Shastina | FMD | DST | Fire Mitigation Distribution | 8.1 |  |  | 5 | 61.73%
Mt Shasta | Phillips | 3 | 5G45 | Weed | Shastina | FOD |  | Fire Overhang Distribution
Mt Shasta | Phillips | 3 | 5G45 | Weed | Shastina | FPD |  |  | 8.1 | 8.1 | 100% | 8.1 | 100%
Mt Shasta | Phillips | 3 | 5G45 | Weed | Shastina | LRA |  | Local Response Area Fire Pole Clearing
Yreka | Phillips | 2 | 5G5 | Greenhorn | Main Street | FIN | DST | Fire Inspection | 10.38 | 10.38 | 100%
Yreka | Phillips | 2 | 5G5 | Greenhorn | Main Street | FMD | DST | Fire Mitigation Distribution | 10.38 |  |  | 10.38 | 100%
Yreka | Phillips | 2 | 5G5 | Greenhorn | Main Street | FOD |  | Fire Overhang Distribution
Yreka | Phillips | 2 | 5G5 | Greenhorn | Main Street | FPD
Yreka | Phillips | 2 | 5G5 | Greenhorn | Main Street | LRA |  | Local Response Area Fire Pole Clearing
Yreka | Phillips | 2 | 5G6 | Copco 2 | Daggett | FIN |  | Fire Inspection | 38.14 | 38.14 | 100%
Yreka | Phillips | 2 | 5G6 | Copco 2 | Daggett | FMD |  | Fire Mitigation Distribution | 38.14 |  |  | 38.14 | 100%
Yreka | Phillips | 2 | 5G6 | Copco 2 | Daggett | FOD |  | Fire Overhang Distribution
Yreka | Phillips | 2 | 5G6 | Copco 3 | Daggett | FPD
Yreka | Phillips | 2 | 5G6 | Copco 2 | Daggett | LRA |  | Local Response Area Fire Pole Clearing
Yreka | Phillips | 2 | 5G63 | Yuba | Callahan | FIN |  | Fire Inspection | 89.56 | 89.56 | 100%
Yreka | Phillips | 2 | 5G63 | Yuba | Callahan | FMD |  | Fire Mitigation Distribution | 89.56 |  |  | 89.56 | 100%
Yreka | Phillips | 2 | 5G63 | Yuba | Callahan | FOD |  | Fire Overhang Distribution
Yreka | Phillips | 2 | 5G63 | Yuba | Callahan | FPD
Yreka | Phillips | 2 | 5G63 | Yuba | Callahan | LRA |  | Local Response Area Fire Pole Clearing
Mt Shasta | Phillips | 3 | 5G69 | North Dunsmuir | Shasta Springs | FIN | DST | Fire Inspection | 11.64 | 11.64 | 100%
Mt Shasta | Phillips | 3 | 5G69 | North Dunsmuir | Shasta Springs | FMD | DST | Fire Mitigation Distribution | 11.64 |  |  | 11.5 | 98.8%
Mt Shasta | Phillips | 3 | 5G69 | North Dunsmuir | Shasta Springs | FOD |  | Fire Overhang Distribution
Mt Shasta | Phillips | 3 | 5G69 | North Dunsmuir | Shasta Springs | FPD |  |  | 11.64 | 11.64 | 100% | 11.64 | 100%
Mt Shasta | Phillips | 3 | 5G69 | North Dunsmuir | Shasta Springs | LRA |  | Local Response Area Fire Pole Clearing
Yreka | Phillips | 2 | 5G7 | Greenhorn | Fairlane | FIN | DHS | Fire Inspection | 66.2 | 66.2 | 100%
Yreka | Phillips | 2 | 5G7 | Greenhorn | Fairlane | FMD | DHS | Fire Mitigation Distribution | 66.2 |  |  | 66.2 | 100%
Yreka | Phillips | 2 | 5G7 | Greenhorn | Fairlane | FOD |  | Fire Overhang Distribution
Yreka | Phillips | 2 | 5G7 | Greenhorn | Fairlane | FPD
Yreka | Phillips | 2 | 5G7 | Greenhorn | Fairlane | LRA |  | Local Response Area Fire Pole Clearing
Mt Shasta | Phillips | 3 | 5G77 | Mt Shasta | Black Butte | FIN |  | Fire Inspection | 45.46 | 45.46 | 100%
Mt Shasta | Phillips | 3 | 5G77 | Mt Shasta | Black Butte | FMD |  | Fire Mitigation Distribution | 45.46 |  |  | 45.46 | 100%
Mt Shasta | Phillips | 3 | 5G77 | Mt Shasta | Black Butte | FOD |  | Fire Overhang Distribution | 45.46 | 45.46 | 100% | 45.46 | 100%
Mt Shasta | Phillips | 3 | 5G77 | Mt Shasta | Black Butte | FPD
Mt Shasta | Phillips | 3 | 5G77 | Mt Shasta | Black Butte | FRD |  | Fire Row Mitigation
Mt Shasta | Phillips | 3 | 5G77 | Mt Shasta | Black Butte | LRA |  | Local Response Area Fire Pole Clearing
Mt Shasta | Phillips | 3 | 5G79 | Mt Shasta | Pioneer | FIN |  | Fire Inspection | 37.15 | 37.15 | 100%
Mt Shasta | Phillips | 3 | 5G79 | Mt Shasta | Pioneer | FMD |  | Fire Mitigation Distribution | 37.15 |  |  | 37.15 | 100%
Mt Shasta | Phillips | 3 | 5G79 | Mt Shasta | Pioneer | FOD |  | Fire Overhang Distribution
Mt Shasta | Phillips | 3 | 5G79 | Mt Shasta | Pioneer | FPD
Mt Shasta | Phillips | 3 | 5G79 | Mt Shasta | Pioneer | FRD |  | Fire Row Mitigation
Mt Shasta | Phillips | 3 | 5G79 | Mt Shasta | Pioneer | LRA |  | Local Response Area Fire Pole Clearing
Mt Shasta | Phillips | 3 | 5G83 | Weed | School Town | FIN | DHS | Fire Inspection | 79.23 | 79.23 | 100%
Mt Shasta | Phillips | 3 | 5G83 | Weed | School Town | FMD | DHS | Fire Mitigation Distribution | 79.23 |  |  | 79.23 | 100%
Mt Shasta | Phillips | 3 | 5G83 | Weed | School Town | FOD |  | Fire Overhang Distribution
Mt Shasta | Phillips | 3 | 5G83 | Weed | School Town | FPD |  |  | 79.23 | 79.23 | 100% | 79.23 | 100%
Mt Shasta | Phillips | 3 | 5G83 | Weed | School Town | LRA |  | Local Response Area Fire Pole Clearing
Mt Shasta | Phillips | 2 | 5G93 | McCloud | School Town | FIN |  | Fire Inspection | 37.21 | 37.21 | 100%
Mt Shasta | Phillips | 2 | 5G93 | McCloud | School Town | FMD |  | Fire Mitigation Distribution | 37.21 |  |  | 37.21 | 100%
Mt Shasta | Phillips | 2 | 5G93 | McCloud | School Town | FOD |  | Fire Overhang Distribution
Mt Shasta | Phillips | 2 | 5G93 | McCloud | School Town | FPD
Mt Shasta | Phillips | 2 | 5G93 | McCloud | School Town | FRD |  | Fire Row Mitigation
Mt Shasta | Phillips | 2 | 5G93 | McCloud | School Town | LRA |  | Local Response Area Fire Pole Clearing
Mt Shasta | Phillips | 2 | 5G97 | Shotgun | North | FIN |  | Fire Inspection | 9.2 | 9.2 | 100%
Mt Shasta | Phillips | 2 | 5G97 | Shotgun | North | FMD |  | Fire Mitigation Distribution | 9.2 |  |  | 9.2 | 100%
Mt Shasta | Phillips | 2 | 5G97 | Shotgun | North | LRA |  | Local Response Area Fire Pole Clearing
Mt Shasta | Phillips | 2 | 5G99 | Shotgun | South | FIN |  | Fire Inspection | 15.52 | 15.52 | 100%
Mt Shasta | Phillips | 2 | 5G99 | Shotgun | South | FMD |  | Fire Mitigation Distribution | 15.52 |  |  | 15.52 | 100%
Mt Shasta | Phillips | 2 | 5G99 | Shotgun | South | FPD
Mt Shasta | Phillips | 2 | 5G99 | Shotgun | South | LRA |  | Local Response Area Fire Pole Clearing
Alturas | Phillips | 2 | 5L105A | Alturas | New Pine | FIN |  | Fire Inspection | 13.23 | 13.23 | 100%
Alturas | Phillips | 2 | 5L105A | Alturas | New Pine | FMD |  | Fire Mitigation Distribution | 13.23 |  |  | 13.23 | 100%
Alturas | Phillips | 2 | 5L105A | Alturas | New Pine | FPD
Alturas | Phillips | 2 | 5L105A | Alturas | New Pine | LRA |  | Local Response Area Fire Pole Clearing
Alturas | Phillips | 2 | 5L87 | Alturas | Hydro | FIN |  | Fire Inspection | 65.99 | 65.99 | 100%
Alturas | Phillips | 2 | 5L87 | Alturas | Hydro | FMD |  | Fire Mitigation Distribution | 65.99 |  |  | 65.99 | 100%
Alturas | Phillips | 2 | 5L87 | Alturas | Hydro | FPD
Alturas | Phillips | 2 | 5L87 | Alturas | Hydro | LRA |  | Local Response Area Fire Pole Clearing
Alturas | Phillips | 2 | 5L97 | Cedarville | Cedarville | FIN | DST | Fire Inspection | 18.6 | 18.6 | 100%
Alturas | Phillips | 2 | 5L97 | Cedarville | Cedarville | FMD | DST | Fire Mitigation Distribution | 18.6 |  |  | 18.6 | 100%
Alturas | Phillips | 2 | 5L97 | Cedarville | Cedarville | FOD |  | Fire Overhang Distribution
Alturas | Phillips | 2 | 5L97 | Cedarville | Cedarville | FPD |  |  | 18.6 | 18.6 | 100% | 18.6 | 100%
Alturas | Phillips | 2 | 5L97 | Cedarville | Cedarville | LRA |  | Local Response Area Fire Pole Clearing
Crescent City | Hooley | 2 | 5R106C | New O'Brien | O'Brien (CA) | FIN | DST | Fire Inspection | 3.44 | 3.44 | 100%
Crescent City | Hooley | 2 | 5R106C | New O'Brien | O'Brien (CA) | FMD | DST | Fire Mitigation Distribution | 3.44 |  |  | 3.44 | 100%
Crescent City | Hooley | 2 | 5R106C | New O'Brien | O'Brien (CA) | FOD |  | Fire Overhang Distribution
Crescent City | Hooley | 2 | 5R106C | New O'Brien | O'Brien (CA) | FPD
Crescent City | Hooley | 2 | 5R165 | Smith River | South Bank | FIN |  | Fire Inspection | 20.72 | 20.72 | 100%
Crescent City | Hooley | 2 | 5R165 | Smith River | South Bank | FMD |  | Fire Mitigation Distribution | 20.72 |  |  | 20.72 | 100%
Crescent City | Hooley | 2 | 5R165 | Smith River | South Bank | FPD
Crescent City | Hooley | 2 | 5R170 | Yurok | North | FIN | DST | Fire Inspection | 0.7 | 0.7 | 100%
Crescent City | Hooley | 2 | 5R170 | Yurok | North | FMD | DST | Fire Mitigation Distribution | 0.7 |  |  | 0.7 | 100%
Crescent City | Hooley | 2 | 5R170 | Yurok | North | FPD
Crescent City | Hooley | 2 | 5R171 | Yurok | Sawmill | FIN | DST | Fire Inspection | 1.9 | 1.9 | 100%
Crescent City | Hooley | 2 | 5R171 | Yurok | Sawmill | FMD | DST | Fire Mitigation Distribution | 1.9 |  |  | 1.9 | 100%
Crescent City | Hooley | 2 | 5R171 | Yurok | Sawmill | FPD
Crescent City | Hooley | 2 | 5R96 | Gasquet | East West | FIN |  | Fire Inspection | 10.19 | 10.19 | 100%
Crescent City | Hooley | 2 | 5R96 | Gasquet | East West | FMD |  | Fire Mitigation Distribution | 10.19 |  |  | 10.19 | 100%
Crescent City | Hooley | 2 | 5R96 | Gasquet | East West | FPD
Mt Shasta | Phillips | 3 | 6G101 | Snowbush | Snowbush | FIN | DHS | Fire Inspection | 4.21 | 4.21 | 100%
Mt Shasta | Phillips | 3 | 6G101 | Snowbush | Snowbush | FMD | DHS | Fire Mitigation Distribution | 4.21 |  |  | 4.21 | 100%
Mt Shasta | Phillips | 3 | 6G101 | Snowbush | Snowbush | FOD |  | Fire Overhang Distribution
Mt Shasta | Phillips | 3 | 6G101 | Snowbush | Snowbush | FPD |  |  | 4.21 | 4.21 | 100% | 4.21 | 100%
Mt Shasta | Phillips | 3 | 6G101 | Snowbush | Snowbush | LRA |  | Local Response Area Fire Pole Clearing
Crescent City | Hooley | 2 | 6R3 | Patricks Creek | Patricks Creek | FIN | DST | Fire Inspection | 7.1 | 7.1 | 100%
Crescent City | Hooley | 2 | 6R3 | Patricks Creek | Patricks Creek | FMD | DST | Fire Mitigation Distribution | 7.1 |  |  | 7.1 | 100%
Crescent City | Hooley | 2 | 6R3 | Patricks Creek | Patricks Creek | FOD |  | Fire Overhang Distribution
Crescent City | Hooley | 2 | 6R3 | Patricks Creek | Patricks Creek | FPD
Mt Shasta | Phillips | 3 | 7G71 | North Dunsmuir | Florence Ave | FIN | DST | Fire Inspection | 4.02 | 4.02 | 100%
Mt Shasta | Phillips | 3 | 7G71 | North Dunsmuir | Florence Ave | FMD | DST | Fire Mitigation Distribution | 4.02 |  |  | 4.02 | 100%
Mt Shasta | Phillips | 3 | 7G71 | North Dunsmuir | Florence Ave | FOD |  | Fire Overhang Distribution
Mt Shasta | Phillips | 3 | 7G71 | North Dunsmuir | Florence Ave | FPD |  |  | 4.02 | 4.02 | 100% | 4.02 | 100%
Mt Shasta | Phillips | 3 | 7G71 | North Dunsmuir | Florence Ave | LRA |  | Local Response Area Fire Pole Clearing
Mt Shasta | Phillips | 3 | 7G73 | North Dunsmuir | Sacremento Ave | FIN | DST | Fire Inspection | 2.07 | 2.07 | 100%
Mt Shasta | Phillips | 3 | 7G73 | North Dunsmuir | Sacremento Ave | FMD | DST | Fire Mitigation Distribution | 2.07 |  |  | 2.07 | 100%
Mt Shasta | Phillips | 3 | 7G73 | North Dunsmuir | Sacremento Ave | FOD |  | Fire Overhang Distribution
Mt Shasta | Phillips | 3 | 7G73 | North Dunsmuir | Sacremento Ave | FPD |  |  | 2.07 | 2.07 | 100% | 2.07 | 100%
Mt Shasta | Phillips | 3 | 7G73 | North Dunsmuir | Sacremento Ave | LRA |  | Local Response Area Fire Pole Clearing
Mt Shasta | Phillips | 2 | 7G75 | South Dunsmuir | South Dunsmuir | FIN | DST | Fire Inspection | 3.69 | 3.69 | 100%
Mt Shasta | Phillips | 2 | 7G75 | South Dunsmuir | South Dunsmuir | FMD | DST | Fire Mitigation Distribution | 3.69 |  |  | 3.69 | 100%
Mt Shasta | Phillips | 2 | 7G75 | South Dunsmuir | South Dunsmuir | FOD |  | Fire Overhang Distribution
Mt Shasta | Phillips | 2 | 7G75 | South Dunsmuir | South Dunsmuir | FPD |  |  | 3.69 | 3.69 | 100% | 3.69 | 100%
Mt Shasta | Phillips | 2 | 7G75 | South Dunsmuir | South Dunsmuir | LRA |  | Local Response Area Fire Pole Clearing
Mt Shasta | Phillips | 2 | 7G81 | Mt Shasta | Center Town | FIN |  | Fire Inspection | 0.48 | 0.48 | 100%
Mt Shasta | Phillips | 2 | 7G81 | Mt Shasta | Center Town | FMD |  | Fire Mitigation Distribution | 0.48 |  |  | 0.48 | 100%
Mt Shasta | Phillips | 2 | 7G81 | Mt Shasta | Center Town | FOD |  | Fire Overhang Distribution
Mt Shasta | Phillips | 2 | 7G81 | Mt Shasta | Center Town | FPD
Mt Shasta | Phillips | 2 | 7G81 | Mt Shasta | Center Town | LRA |  | Local Response Area Fire Pole Clearing
Mt Shasta | Phillips | 2 | 7G82 | Mt Shasta | North Town | FIN |  | Fire Inspection | 3.17 | 3.17 | 100%
Mt Shasta | Phillips | 2 | 7G82 | Mt Shasta | North Town | FMD |  | Fire Mitigation Distribution | 3.17 |  |  | 3.17 | 100%
Mt Shasta | Phillips | 2 | 7G82 | Mt Shasta | North Town | FOD |  | Fire Overhang Distribution
Mt Shasta | Phillips | 2 | 7G82 | Mt Shasta | North Town | FPD
Mt Shasta | Phillips | 2 | 7G82 | Mt Shasta | North Town | LRA |  | Local Response Area Fire Pole Clearing
Mt Shasta | Phillips | 2 | 8G103 | Dog Creek | Volmers | FIN |  | Fire Inspection | 2.17 | 2.17 | 100%
Mt Shasta | Phillips | 2 | 8G103 | Dog Creek | Volmers | FMD |  | Fire Mitigation Distribution | 2.17 |  |  | 2.17 | 100%
Mt Shasta | Phillips | 2 | 8G103 | Dog Creek | Volmers | FOD |  | Fire Overhang Distribution
Mt Shasta | Phillips | 2 | 8G103 | Dog Creek | Volmers | FPD
Mt Shasta | Phillips | 2 | 8G103 | Dog Creek | Volmers | LRA |  | Local Response Area Fire Pole Clearing
Yreka | Phillips | 2 | 8G27 | Hamburg | Hamburg | FIN | DST | Fire Inspection | 4.97 | 4.97 | 100%
Yreka | Phillips | 2 | 8G27 | Hamburg | Hamburg | FMD | DST | Fire Mitigation Distribution | 4.97 |  |  | 4.97 | 100%
Yreka | Phillips | 2 | 8G27 | Hamburg | Hamburg | FOD |  | Fire Overhang Distribution
Yreka | Phillips | 2 | 8G27 | Hamburg | Hamburg | FPD |  |  | 4.97 | 4.97 | 100% | 4.97 | 100%
Yreka | Phillips | 2 | 8G27 | Hamburg | Hamburg | LRA |  | Local Response Area Fire Pole Clearing
Mt Shasta | Phillips | 2 | 8G40 | Intl Paper | Int Paper | FIN | DST | Fire Inspection | 0.12 | 0.12 | 100%
Mt Shasta | Phillips | 2 | 8G40 | Intl Paper | Int Paper | FMD | DST | Fire Mitigation Distribution | 0.12 |  |  | 0.12 | 100%
Mt Shasta | Phillips | 2 | 8G40 | Intl Paper | Int Paper | FOD |  | Fire Overhang Distribution
Mt Shasta | Phillips | 2 | 8G40 | Intl Paper | Int Paper | FPD |  |  | 0.12 | 0.12 | 100% | 0.12 | 100%
Mt Shasta | Phillips | 2 | 8G40 | Intl Paper | Int Paper | LRA |  | Local Response Area Fire Pole Clearing
Mt Shasta | Phillips | 2 | 8G65 | Castella | Castella | FIN | DST | Fire Inspection | 6.36 | 6.36 | 100%
Mt Shasta | Phillips | 2 | 8G65 | Castella | Castella | FMD | DST | Fire Mitigation Distribution | 6.36 |  |  | 6.36 | 100%
Mt Shasta | Phillips | 2 | 8G65 | Castella | Castella | FOD |  | Fire Overhang Distribution
Mt Shasta | Phillips | 2 | 8G65 | Castella | Castella | FPD |  |  | 6.36 | 6.36 | 100% | 6.36 | 100%
Mt Shasta | Phillips | 2 | 8G65 | Castella | Castella | LRA |  | Local Response Area Fire Pole Clearing
Mt Shasta | Phillips | 2 | 8G95 | Nutglade | Nutglade | FIN | DST | Fire Inspection | 8.34 | 8.34 | 100%
Mt Shasta | Phillips | 2 | 8G95 | Nutglade | Nutglade | FMD | DST | Fire Mitigation Distribution | 8.34 |  |  | 8.34 | 100%
Mt Shasta | Phillips | 2 | 8G95 | Nutglade | Nutglade | FOD |  | Fire Overhang Distribution
Mt Shasta | Phillips | 2 | 8G95 | Nutglade | Nutglade | FPD |  |  | 8.34 | 8.34 | 100% | 8.34 | 100%
Mt Shasta | Phillips | 2 | 8G95 | Nutglade | Nutglade | LRA |  | Local Response Area Fire Pole Clearing
Alturas | Phillips | 2 | ALT668036 |  | Lakeview-Alturas 115kV #36 LOC | FIN |  | Fire Inspection | 16.02 | 16.02 | 100%
Alturas | Phillips | 2 | ALT668036 |  | Lakeview-Alturas 115kV #36 LOC | FMT |  | Fire Mitigation Transmission | 16.02 |  |  | 16.02 | 100%
Crescent City | Hooley | 2 | CRE668038 | Del Norte | Cave Jct-Del Norte115#38(CA) LOC | FMT |  | Fire Mitigation Transmission | 25.3 |  |  | 25.3 | 100%
Crescent City | Hooley | 2 | CRE668038 | Del Norte | Cave Jct-Del Norte115#38(CA) LOC | FIN |  | Fire Inspection | 25.3 | 25.3 | 100%
Crescent City | Hooley | 2 | CRE668044 | Del Norte | Grants Pass-Del Norte115 #44 LOC | FIN |  | Fire Inspection | 25.29 | 25.29 | 100%
Crescent City | Hooley | 2 | CRE668044 | Del Norte | Grants Pass-Del Norte115 #44 LOC | FMT |  | Fire Mitigation Transmission | 25.29 |  |  | 25.29 | 100%
Klamath Falls CA | Phillips | 2 | KFC668004 |  | Copco 2-K Falls 69kV #4(CA) LOC | FIN |  | Fire Inspection | 13.81 | 13.81 | 100%
Klamath Falls CA | Phillips | 2 | KFC668004 |  | Copco 2-K Falls 69kV #4(CA) LOC | FMT |  | Fire Mitigation Transmission | 13.81 |  |  | 13.81 | 100%
Klamath Falls CA | Phillips | 2 | KFC668018 |  | Copco 2-Westside 69 #18(CA) LOC | FIN |  | Fire Inspection | 9.79 | 9.79 | 100%
Klamath Falls CA | Phillips | 2 | KFC668018 |  | Copco 2-Westside 69 #18(CA) LOC | FMT |  | Fire Mitigation Transmission | 9.79 |  |  | 9.79 | 100%
Mt Shasta | Phillips | 2,3 | MTS668002 |  | Copco 2-Delta 69kV #2 LOC | FIN |  | Fire Inspection | 89.17 | 89.17 | 100%
Mt Shasta | Phillips | 2,3 | MTS668002 |  | Copco 2-Delta 69kV #2 LOC | FMT |  | Fire Mitigation Transmission | 89.17 |  |  | 89.17 | 100%
Yreka | Phillips | 2 | YRE668001 |  | Montague-Weed Jct 69kV Ln #1 | FIN |  | Fire Inspection | 5.53 | 5.53 | 100%
Yreka | Phillips | 2 | YRE668001 |  | Montague-Weed Jct 69kV Ln #1 | FMT |  | Fire Mitigation Transmission | 5.53 |  |  | 5.53 | 100%
Yreka | Phillips | 2 | YRE668003 |  | Copco 1-Fall Creek 69kV #3 LOC | FIN |  | Fire Inspection | 2.24 | 2.24 | 100%
Yreka | Phillips | 2 | YRE668003 |  | Copco 1-Fall Creek 69kV #3 LOC | FMT |  | Fire Mitigation Transmission | 2.24 |  |  | 2.24 | 100%
Yreka | Phillips | 2 | YRE668010 |  | Montague-Yuba 69kV #10 LOC | FIN |  | Fire Inspection | 38.77 | 38.77 | 100%
Yreka | Phillips | 2 | YRE668010 |  | Montague-Yuba 69kV #10 LOC | FMT |  | Fire Mitigation Transmission | 38.77 |  |  | 38.77 | 100%
Yreka | Phillips | 2 | YRE668015 |  | Copco 1-Copco-2 69kV #15 LOC | FIN |  | Fire Inspection | 1.7 | 1.7 | 100%
Yreka | Phillips | 2 | YRE668015 |  | Copco 1-Copco-2 69kV #15 LOC | FMT |  | Fire Mitigation Transmission | 1.7 |  |  | 1.7 | 100%
Yreka | Phillips | 2 | YRE668019 |  | Copco 2-Prospect 115kV #19 LOC | FIN |  | Fire Inspection | 2.79 | 2.79 | 100%
Yreka | Phillips | 2 | YRE668019 |  | Copco 2-Prospect 115kV #19 LOC | FMT |  | Fire Mitigation Transmission | 2.79 |  |  | 2.79 | 100%
Yreka | Phillips | 2 | YRE668026 |  | Copco 1-Copco-1 Sw 69kV #26 LOC | FIN |  | Fire Inspection | 0.2 | 0.2 | 100%
Yreka | Phillips | 2 | YRE668026 |  | Copco 1-Copco-1 Sw 69kV #26 LOC | FMT |  | Fire Mitigation Transmission | 0.2 |  |  | 0.2 | 100%
Yreka | Phillips | 2 | YRE668033 |  | Cave Jct-Indian Crk69#33(CA) LOC | FIN |  | Fire Inspection | 72.45 | 72.45 | 100%
Yreka | Phillips | 2 | YRE668033 |  | Cave Jct-Indian Crk69#33(CA) LOC | FMT |  | Fire Mitigation Transmission | 72.45 |  |  | 72.45 | 100%
Yreka | Phillips | 2 | YRE668047 |  | Yreka-Ft Jones 69kV Ln #47 LOC | FIN |  | Fire Inspection | 20.3 | 20.3 | 100%
Yreka | Phillips | 2 | YRE668047 |  | Yreka-Ft Jones 69kV Ln #47 LOC | FMT |  | Fire Mitigation Transmission | 20.3 |  |  | 20.3 | 100%
Yreka | Phillips | 2 | YRE668062 |  | Iron Gate-Copco-2 69kV #62 LOC | FIN |  | Fire Inspection | 0.72 | 0.72 | 100%
Yreka | Phillips | 2 | YRE668062 |  | Iron Gate-Copco-2 69kV #62 LOC | FMT |  | Fire Mitigation Transmission | 0.72 |  |  | 0.72 | 100%
Yreka | Phillips | 2 | YRE668067 |  | Copco 2 Sw-Yreka 115kV #67 LOC | FIN |  | Fire Inspection | 5.35 | 5.35 | 100%
Yreka | Phillips | 2 | YRE668067 |  | Copco 2 Sw-Yreka 115kV #67 LOC | FMT |  | Fire Mitigation Transmission | 5.35 |  |  | 5.35 | 100%
Yreka | Phillips | 2 | YRE668075 |  | Hart Sw Sta-Yreka 115kV #75 LOC | FIN |  | Fire Inspection | 18.52 | 18.52 | 100%
Yreka | Phillips | 2 | YRE668075 |  | Hart Sw Sta-Yreka 115kV #75 LOC | FMT |  | Fire Mitigation Transmission | 18.52 |  |  | 18.52 | 100%
TOTAL | [7 empty] | TOTAL | 2055.4 | 2030.1 | 98.77% | 2004.23 | 97.51%
1015.63