## Summary
2024 YTD Actuals
| On Time | Past Due | % On Time
Transmission | 7103 | 3306 | 68.24%
Distribution | 12886 | 75972 | 14.5%
Vegetation | 149816 | 1006 | 99.33%
Consolidated | 169805 | 80284 | 67.9%

## YTD Actuals
2024 Target | [32 empty] | 0.8
|  | On-time | [12 empty] | Past Due | [13 empty] | 2024 Annual Target |  |  | Notes
|  | 2024 | [12 empty] | 2024
LOB | Type | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total On Time | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total Past Due | Grand Total | On Time | Past Due | % On Time |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Tx | Level 2 | 108 | 635 | 802 | 1400 | 2024 | 1791 | 311 | 194 | 293 | 331 | 408 | 233 | 8530 | 38 | 143 | 182 | 311 | 446 | 395 | 69 | 55 | 92 | 133 | 171 | 98 | 2133 | 10663 | 8530 | 2133 | 80% | our tags with 2024 due dates will be 2023 and 2024 finds, which we are supposed to do by their required end dates. I think we should choose a target that's informed by our YTD performance with 2023 finds in Tier 3, which we have been trying to do by their due dates. We're at roughly 85% for these tags. Picking 80% as a target would give some additional margin. For reference, the 2023 target is 52% and the 2027 target is 99%, so 80% would allow further ramp up in 2025-2026 to the 2027 target level. | 146 | 778 | 984 | 1711 | 2470 | 2186 | 380 | 249 | 385 | 464 | 579 | 331 | 10663
Tx | Tx Total | 108 | 635 | 802 | 1400 | 2024 | 1791 | 311 | 194 | 293 | 331 | 408 | 233 | 8530 | 38 | 143 | 182 | 311 | 446 | 395 | 69 | 55 | 92 | 133 | 171 | 98 | 2133 | 10663 | 8530 | 2133 | 80%
Tx Monthly Target |  | 73.97% | 81.62% | 81.5% | 81.82% | 81.94% | 81.93% | 81.84% | 77.91% | 76.1% | 71.34% | 70.47% | 70.39% | 80%
Dx | B | 382 | 134 | 122 | 213 | 650 | 1176 | 1300 | 1684 | 1302 | 888 | 40 | 41 | 7932 | 12 | 13 | 22 | 40 | 19 | 20 | 19 | 11 | 2 | 25 | 10 | 39 | 232 | 8164 | 7932 | 232 | 97.16% | Tier 2 based on 2024 wpml jan thru Oct; nov thru Dec based on 2022 actuals Tier 3 based on 2024 wpml jan thru April; May thru Dec based on 2022 actuals
Dx | B from E | 17 | 9 | 12 | 15 | 23 | 41 | 15 | 5 | 21 | 15 | 23 | 76 | 272 | 46 | 7 | 35 | 138 | 144 | 210 | 111 | 15 | 10 | 21 | 8 | 23 | 768 | 1040 | 272 | 768 | 26.15% | Based on 2022 actuals | [13 empty] | 2024 Target | [31 empty] | 2024 Annual Target - Revised 1/30/2014
Dx | E | 50 | 34 | 25 | 36 | 105 | 272 | 107 | 4 | 1 | 0 | 0 |  | 634 | 738 | 454 | 395 | 1503 | 6659 | 14150 | 13536 | 15124 | 10544 | 7356 | 336 |  | 70795 | 71429 | 634 | 70795 | 0.8876% | based on 2024 work plan as of 11/7/23 adjusted for 2023 YTD work adherence | [15 empty] | On-time | [12 empty] | Past Due | [13 empty] | 2024 Annual Target
Dx | Dx Total | 449 | 177 | 159 | 264 | 778 | 1489 | 1422 | 1693 | 1324 | 903 | 63 | 117 | 8838 | 796 | 474 | 452 | 1681 | 6822 | 14380 | 13666 | 15150 | 10556 | 7402 | 354 | 62 | 71795 | 80633 | 8838 | 71795 | 10.96% | [16 empty] | 2024 | [12 empty] | 2024
Dx Monthly Target |  | 36.06% | 27.19% | 26.02% | 13.57% | 10.24% | 9.383% | 9.425% | 10.05% | 11.14% | 10.87% | 15.11% | 65.36% | 10.96% | [18 empty] | 0.99 | [12 empty] | LOB | Type | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total On Time | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total Past Due | Grand Total | On Time | Past Due | % On Time | On Time | Past Due | % On Time
Veg | Dead/Dying | 10496 | 9583 | 9583 | 9583 | 10039 | 10496 | 9127 | 10496 | 10039 | 9583 | 10496 | 10039 | 119560 | 214 | 196 | 196 | 196 | 205 | 214 | 186 | 214 | 205 | 196 | 214 | 204 | 2440 | 122000 | 119560 | 2440 | 98% | consistent with 2023; update 1/31: Veg Mgmt is shifting some inspections/tree work to new programs in 2024 (FTI, TRI, VMOM) so 2024 forecasting totals have been adjusted to be more conservative, reducing overall totals slightly to avoid over forecasting. Target Percentage of 98% is staying the same. | [13 empty] | Veg | Dead/Dying | 8988.7806 | 8207.1475 | 8207.1475 | 8207.1475 | 8597.964 | 8988.7806 | 7816.3309 | 8988.7806 | 8597.964 | 8207.1475 | 8988.7806 | 8597.964 | 102393.9352 | 213.4983 | 194.9332 | 194.9332 | 194.9332 | 204.2157 | 213.4983 | 185.6507 | 213.4983 | 204.2157 | 194.9332 | 213.4983 | 204.2157 | 2432.0239 | 104825.959 | 102393.9352 | 2432.0239 | 97.68% | 119560 | 2440 | 0.98
Veg | Priority 2 | 2433 | 2222 | 2222 | 2222 | 2328 | 2433 | 2116 | 2433 | 2328 | 2222 | 2433 | 2328 | 27720 | 25 | 22 | 22 | 22 | 24 | 25 | 21 | 25 | 24 | 22 | 25 | 23 | 280 | 28000 | 27720 | 280 | 99% | [14 empty] | Veg | Priority 2 | 2234.6189 | 2040.3042 | 2040.3042 | 2040.3042 | 2137.4616 | 2234.6189 | 1943.1469 | 2234.6189 | 2137.4616 | 2040.3042 | 2234.6189 | 2137.4616 | 25455.2244 | 0.88536 | 0.80837 | 0.80837 | 0.80837 | 0.84687 | 0.88536 | 0.76988 | 0.88536 | 0.84687 | 0.80837 | 0.88536 | 0.84687 | 10.0854 | 25465.3098 | 25455.2244 | 10.0854 | 99.96% | 27720 | 280 | 0.99
Veg | EVM | 688 | 628 | 628 | 628 | 658 | 688 | 598 | 688 | 659 | 629 | 689 | 659 | 7840 | 14 | 13 | 13 | 13 | 13 | 14 | 12 | 14 | 13 | 13 | 14 | 14 | 160 | 8000 | 7840 | 160 | 98% | [14 empty] | Veg | EVM | 3700.2646 | 3378.5025 | 3378.5025 | 3378.5025 | 3539.3835 | 3700.2646 | 3217.6214 | 3700.2646 | 3539.3835 | 3378.5025 | 3700.2646 | 3539.3835 | 42150.8404 | 90.1803 | 82.3385 | 82.3385 | 82.3385 | 86.2594 | 90.1803 | 78.4176 | 90.1803 | 86.2594 | 82.3385 | 90.1803 | 86.2594 | 1027.2707 | 43178.1111 | 42150.8404 | 1027.2707 | 97.62% | 7840 | 160 | 0.98
Veg | Veg Total | 13617 | 12433 | 12433 | 12433 | 13025 | 13617 | 11841 | 13617 | 13026 | 12434 | 13618 | 13026 | 155120 | 253 | 231 | 231 | 231 | 242 | 253 | 219 | 253 | 242 | 231 | 253 | 241 | 2880 | 158000 | 155120 | 2880 | 98.18% |  | 14924 | 13626 | 13626 | 13626 | 14275 | 14924 | 12977 | 14924 | 14275 | 13626 | 14924 | 14275 | 170000 | Veg | Veg Total | 14923.6641 | 13625.9542 | 13625.9542 | 13625.9542 | 14274.8092 | 14923.6641 | 12977.0992 | 14923.6641 | 14274.8092 | 13625.9542 | 14923.6641 | 14274.8092 | 170000 | 304.5639 | 278.0801 | 278.0801 | 278.0801 | 291.322 | 304.5639 | 264.8382 | 304.5639 | 291.322 | 278.0801 | 304.5639 | 291.322 | 3469.38 | 173469.38 | 170000 | 3469.38 | 98% | 155120 | 2880 | 98.18%
Veg Monthly Target |  | 98.18% | 98.18% | 98.18% | 98.18% | 98.18% | 98.18% | 98.18% | 98.18% | 98.18% | 98.18% | 98.18% | 98.18% | 98.18% | [31 empty] | Veg Monthly Target |  | 98% | 98% | 98% | 98% | 98% | 98% | 98% | 98% | 98% | 98% | 98% | 98% | 98%
Grand Total |  | 14174 | 13245 | 13394 | 14097 | 15827 | 16897 | 13574 | 15504 | 14643 | 13668 | 14089 | 13376 | 172488 | 1087 | 848 | 865 | 2223 | 7510 | 15028 | 13954 | 15458 | 10890 | 7766 | 778 | 401 | 76808 | 249296 | 172488 | 76808 | 69.19% | 87.49%
Total Monthly Target |  | 92.88% | 93.98% | 93.93% | 86.38% | 67.82% | 52.93% | 49.31% | 50.07% | 57.35% | 63.77% | 94.77% | 97.09% | 69.19%
| YTD Target | 92.88% | 93.41% | 93.58% | 91.62% | 84.95% | 76.07% | 70.91% | 67.2% | 65.94% | 65.72% | 67.56% | 69.19% | 69.19%
2024 Actuals
|  | On-time | [12 empty] | Past Due | [13 empty] | 2024 YTD Actuals
|  | 2024 | [12 empty] | 2024
LOB | Type | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | YTD On Time | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | YTD Late | Grand Total | On Time | Past Due | % On Time
Tx | Level 2 | 104 | 549 | 572 | 1032 | 1267 | 1197 | 217 | 131 | 506 | 562 | 718 | 239 | 7094 | 11 | 170 | 290 | 492 | 840 | 687 | 136 | 77 | 158 | 140 | 215 | 89 | 3305 | 10399 | 7094 | 3305 | 68.22%
Tx | Tx Total | 104 | 549 | 572 | 1032 | 1267 | 1197 | 217 | 131 | 506 | 562 | 718 | 239 | 7094 | 11 | 170 | 290 | 492 | 840 | 687 | 136 | 77 | 158 | 140 | 215 | 89 | 3305 | 10399 | 7094 | 3305 | 68.22%
Tx Monthly Act |  | 90.43% | 76.36% | 66.36% | 67.72% | 60.13% | 63.54% | 61.47% | 62.98% | 76.2% | 80.06% | 76.96% | 72.87% | 68.22%
Dx | B | 321 | 119 | 110 | 189 | 567 | 1029 | 1206 | 1562 | 1300 | 987 | 518 | 253 | 8161 | 50 | 13 | 13 | 18 | 51 | 70 | 56 | 59 | 78 | 96 | 50 | 35 | 589 | 8750 | 8161 | 589 | 93.27%
Dx | B from E | 7 |  | 4 | 18 | 57 | 127 | 42 | 41 | 23 | 15 | 15 | 9 | 358 | 24 | 8 | 8 | 23 | 92 | 194 | 137 | 105 | 84 | 35 | 9 | 4 | 723 | 1081 | 358 | 723 | 33.12%
Dx | E | 264 | 27 | 52 | 121 | 588 | 1466 | 457 | 94 | 97 | 156 | 143 | 637 | 4102 | 436 | 399 | 332 | 1295 | 5812 | 12014 | 12350 | 14425 | 11114 | 9678 | 4390 | 2415 | 74660 | 78762 | 4102 | 74660 | 5.208%
Dx | X | 2024 Sep: 10; 2024 Oct: 66; 2024 Nov: 72; 2024 Dec: 117 | 265 | [12 empty] | 0 | 265 | 265 | 0 | 100%
Dx | Dx Total | 592 | 146 | 166 | 328 | 1212 | 2622 | 1705 | 1697 | 1430 | 1224 | 748 | 1016 | 12886 | 510 | 420 | 353 | 1336 | 5955 | 12278 | 12543 | 14589 | 11276 | 9809 | 4449 | 2454 | 75972 | 88858 | 12886 | 75972 | 14.5%
Dx Monthly Act |  | 53.72% | 25.8% | 31.98% | 19.71% | 16.91% | 17.6% | 11.97% | 10.42% | 11.25% | 11.09% | 14.39% | 29.28% | 14.5%
Veg | Dead/Dying | 6986 | 7775 | 6611 | 9298 | 9011 | 6170 | 9037 | 9444 | 10062 | 9952 | 5003 | 8130 | 97479 | 133 | 52 | 93 | 66 | 253 | 159 | 55 | 23 | 20 | 16 | 11 | 4 | 885 | 98364 | 97479 | 885 | 99.1% | Oct report update; over 3.7K were constrained and on time; updated numbers to include and take credit for it
Veg | Priority 2 | 3170 | 3545 | 3337 | 3327 | 3604 | 3258 | 3707 | 4924 | 4740 | 4555 | 3663 | 4330 | 46160 | 11 | 10 | 21 | 3 | 15 | 9 | 4 | 1 | 2 | 1 | 3 | 1 | 81 | 46241 | 46160 | 81 | 99.82%
Veg | EVM | 1081 | 536 | 561 | 751 | 891 | 335 | 447 | 588 | 550 | 315 | 70 | 52 | 6177 | 3 | 9 | 2 | 2 | 3 | 3 | 7 | 7 | 2 | 2 | 0 | 0 | 40 | 6217 | 6177 | 40 | 99.36%
Veg | Veg Total | 11237 | 11856 | 10509 | 13376 | 13506 | 9763 | 13191 | 14956 | 15352 | 14822 | 8736 | 12512 | 149816 | 147 | 71 | 116 | 71 | 271 | 171 | 66 | 31 | 24 | 19 | 14 | 5 | 1006 | 150822 | 149816 | 1006 | 99.33%
Veg Monthly Act |  | 98.71% | 99.4% | 98.91% | 99.47% | 98.03% | 98.28% | 99.5% | 99.79% | 99.84% | 99.87% | 99.84% | 99.96% | 99.33%
Grand Total |  | 11933 | 12551 | 11247 | 14736 | 15985 | 13582 | 15113 | 16784 | 17288 | 16608 | 10202 | 13767 | 169796 | 668 | 661 | 759 | 1899 | 7066 | 13136 | 12745 | 14697 | 11458 | 9968 | 4678 | 2548 | 80283 | 250079 | 169796 | 80283 | 67.9%
Total Monthly Actuals |  | 94.7% | 95% | 93.68% | 88.58% | 69.35% | 50.83% | 54.25% | 53.31% | 60.14% | 62.49% | 68.56% | 84.38% | 67.9%
|  | 94.7% | 94.85% | 94.48% | 92.68% | 85.74% | 76.79% | 72.04% | 68.43% | 67.19% | 66.62% | 66.75% | 67.9% | 67.9%
2946
|  |  | 24484 | 35731 | 50467 | 66452 | 80034 | 95147 | 111931 | 129219 | 145827 | 156029 |  |  |  | 1329 | 2088 | 3987 | 11053 | 24189 | 36934 | 51631 | 63089 | 73057 | 77735
|  | 2024 Nov: 6855 | [11 empty] | 3216 |  | 68.07%
|  | 2024 Nov: 11870 | [11 empty] | 73518 |  | 13.9%
|  | 2024 Nov: 149816 | [11 empty] | 1006 |  | 99.33%
|  | 2024 Nov: 168541 | [11 empty] | 77740 |  | 68.43%
|  | 2024 Nov: 8297 | [11 empty] | 2035 |  | 80.3%
|  | 2024 Nov: 8721 | [11 empty] | 71733 |  | 10.84%
|  | 2024 Nov: 142094 | [11 empty] | 2639 |  | 98.18%
|  | 2024 Nov: 159112 | [11 empty] | 76407 |  | 67.56%