## Slide 1: DRAM Evaluation Plan & Metrics Workshop
Cathy Fogel & Bruce Kaneshiro
Demand Response Section
California Public Utilities Commission
March 1, 2017

## Slide 2: Safety Instructions Meeting Spot: Garden Plaza, next to War Memorial Opera House

## Slide 3: Agenda
Time | Topic
9:00 - 9:15 | Introductions, Purpose of Workshop
9:15 – 10:00 | Presentation of Criterions 1-2
10:00 – 10:45 | Presentation of Criterions 3-4
10:45 -11:30 | Presentation of Criterions 5-6
11:30 – noon | Data Collection & Analysis Timing
Noon – 12:30 | Data Collection – confidentiality, granularity, sources
12:30 – 1:00 | Any additional issues Written Comment deadline: March 13
TBD | Additional discussion, as needed, see below

## Slide 4: Introduction
Goal 1: Research the full DRAM I and DRAM II pilots and the solicitation phase of DRAM III
Goal 2: Provide recommendations based on the research and analysis to guide the Commission in determining if the auction mechanism pilots may be deemed successful

## Slide 5: Project Objectives
Objective 1: Assess the DRAM pilots based on the Commission’s adopted criteria for determining its success
Objective 2: Explore these criteria using metrics based on input from Parties to R.13-09-011
Objective 3: Provide data and factual analysis to guide recommendations
Objective 4: Undertake a balanced analysis based on input from the range of market, utility and regulatory actors

## Slide 6: Project Management Team
Project Direction
D.1609056
ED Project Manager
Cathleen Fogel
Project Oversight
Bruce Kaneshiro
Project Guidance
Simon Baker
Data Management Guidance
David Miller, Jamie Rose Gannon
CAISO BID & Dispatch Data Analysis
CPUC Modeling Team
Non-financially interested ies

## Slide 7: Success Criteria Adopted in D.16-09-056
Were new, viable third-party providers engaged?
Were new customers engaged?
Were bid prices competitive?
Were offer prices competitive in the wholesale markets?
Did demand response providers aggregate the capacity they contracted, or replace it with demand response from another source in a timely manner?
Were resources reliable when dispatched, i.e., did customers perform appropriately?

## Slide 8: Additional Direction in D.16-09-056
Final DRAM Eval Plan & Metrics- by April 1, 2017
ED to release a draft Resolution with findings / recommendations by June 1, 2018
If Resolution approved, workshop within 30 days
First auction in spring 2019 for 2020 delivery
  Adopts eight provisions for possible future DRAM

## Slide 9
Criteria & Proposed Metrics |  | Assess by or Compare to: |  | Data Source | C?
Were new, viable third-party providers engaged? |  |  |  |  | 
1.1 | Number of participating third party providers bidding into and winning bids; Number of DRPs registered with CPUC | Aggregators, DRPs, SCs; New 3Ps, or those previously operating in California DRAM I - III |  | IOUs / CAISO / IE report | N
1.2 | Quantity (MW) and percentage of accepted bids compared to all bids | New 3P, returning MW, number, budget DRAM I – III |  | IOUs | N
What were the challenges to third-party engagement- general? |  |  |  |  | 
1.3 | Third party perceptions of: Ease of participation; Fairness / transparency of bid selection process; Primary barriers to participation; Primary source of transaction costs; Market confidence; Understanding of CAISO products, performance requirements and markets |  | Compare perceptions of winning and non-winning aggregators | ED survey and/or interviews with Aggregators, SCs, DRPs, IOUs; IOU surveys from bidders conferences | N

## Slide 10
Criteria & Proposed Metrics |  | Assess by or Compare to: | Data Source | C?
What were the challenges to third-party engagement- in the IOU auction process? (Were there barriers to participation?) |  |  |  | 
1.4 | Number of potential third party providers contacted by IOUs | Aggregators DRAM I - III | IOUs | N
1.5 | Number of potential third party providers attending DRAM bidding conference(s) | Aggregators, DRPs, SCs DRAM I - III | IOUs | N
1.6 | Number of questions at bidding conference by potential third party providers, the topics and average IOU response times | (optional, time permitting) | IOUs | N
1.7 | Number/ percentage of potential third party providers bidding into DRAM compared to attendees at conference | (optional, time permitting) New or returning aggregators | IOUs | N
1.8 | Number / percent of DRAM bidders with conformance check issues | New or returning aggregators | IOUs | N
1.9 | Number / percent of winning bidders unwilling to sign contracts and reasons. |  | ED interviews withAggregators, SCs, DRPs, IOUs; | Y

## Slide 11
Criteria & Proposed Metrics |  | Assess by or Compare to: |  | Data Source | C?
What were the challenges to third party engagement – in the customer enrollment process? (Were there barriers to signing up customers?) |  |  |  |  | 
1.10 | Number and percent of DRPs or aggregators experiencing integration challenges with processes to enroll customers. Type of challenge and status. | This will include exploration of barriers due to lack of availability of needed customer data due to Green Button, MyConnect, and/or other issues. | Interviews with Aggregators, SCs, DRPs, IOUs; Quantitative data when available |  | N
1.11 | DRP, SC and/or aggregator perceptions of differences between DRAM and IOU DR programs that could limit customer participation. |  |  |  | 
 |  |  |  |  | N
What were the challenges to third party participation the CAISO bidding process ? (Were there barriers to making bids?) |  |  |  |  | 
1.12 | Number and percent of DRPs or SCs experiencing supply-side integration challenges with CAISO processes. Type of challenge and status. | By customer class By Aggregator By new / returning third party providers ; By PDR or RDR resource By type of RA: System / Flexible / Local capacity; By August, month and year DRAM I & II only | Interviews with SCs, DRPs, Agg Quantitative data when available |  | N
1.13 | Quantity (MW) of DRAM resources in Supply Plans and quantity bid into CAISO Compare to IOU DR resources Supply Plans and quantity bid into CAISO |  |  |  | 
 |  |  | IOUs |  | N

## Slide 12
Criteria & Proposed Metrics |  | Assess by or Compare to: |  | Data Source | C?
Were new customers engaged? |  |  |  |  | 
2.1 | -Number and percentage of new customers; -Number and percentage of customers shifted from IOU DR programs to DRAM -Quantity (MW) and percentage capacity provided by shifted and new DRP customers | As indicated by registrations; By customer class, DRP; PDR / RDRR; By type of RA: System / Flexible / Local capacity; Type of resource – DR / storage / EV; By August; annual | IOUs / DRPs |  | N
2.2 | Average duration of customer participation in DRAM and IOU DR programs and reasons for withdrawal | As indicated by registrations; By customer class, DRP PDR / RDRR | ED review of DRP and IOU surveys; or, ED surveys or interviews (optional, time permitting) |  | Y
2.3 | Customer perception of differences between direct participation and IOU DR programs that could limit customer participation. |  |  |  | N
2.4 | Location of DRAM customers (number and percent)? | By county By subLAP By local reliability area and/or transmission constrained areas? In disadvantaged communities? | IOUs/ 3Ps: Geo-map or list by county of location of registrations |  | N
2.5 | Total and percentage of participating customers on CARE rates, ESA participants, in multifamily dwellings and/or in top 5% of electricity consumers | (optional, time permitting) | IOUs |  | N
2.6 | Number / percent of registrations requested in non-winning bids [due to: 1) budget; 2) registration; or 3) “outlier” limitations] |  | IOUs |  | N

## Slide 13
Criteria & Proposed Metrics |  | Assess by or Compare to: | Data Source | C?
2.A. High level characterization of new customers [Optional, time permitting] |  |  |  | 
2.A.1 | Percent of customers with automated response capabilities | As indicated by registrations; By customer class, DRP; By PDR / RDRR; By type of RA: System / By Flexible / Local capacity; By Type of resource – DR / storage / EV; By August; annual | IOUs / DRPs | N
2.A.2 | Number and percent of DRAM customers participating via storage-tied response systems |  | IOUs / DRPs | N
2.A.3 | Number and percent of DRAM customers participating via storage-tied response systems that have additional onsite DER resources such as EVs, PV, or EE incentives. |  | IOUs/ DRP / ED survey of participating customers with storage | N
2.A.4 | High, low and average participating NR and Res customer loads for August and peak days. |  | IOUs | N

## Slide 14
Criteria & Proposed Metrics |  |  | Assess by or Compare to: | Data Source | C?
3, Were bid (auction, capacity) prices competitive? |  |  |  |  | 
3.1 | High, low and average bid (auction, capacity) bid prices | As bid; procured; By PDR / RDR; By resource type: system, flexible and local capacity; By customer class; DRP; By New /returning 3P; with / without scheduling coordinator costs included; for August / by month / by year) |  | IOUs / IE reports | Y
3.2 | High, low and average Scheduling Coordinator costs | By customer class |  | IOUs / IE reports | Y
3.3 | -High, low and average procured DRAM August capacity prices -Average non-procured bid August capacity prices | As compared to the following benchmarks: DR from IOU programs All RA CAISO Capacity Procurement Mechanism the cost-effectiveness requirements of R. 14-10-003 |  | IOUs | Y
3.4 | Other metrics on procured DRAM such as: Net Present Value (NPV) All-in-cost | As compared to the following benchmarks: DR from IOU programs All RA CAISO Capacity Procurement Mechanism costs Cost-effectiveness requirements of R. 14-10-003 |  | IOUs | Y

## Slide 15
Criteria & Proposed Metrics |  | Assess by or Compare to: | Data Source |  | C? | 
Were bid offer prices competitive in the wholesale market? (Defined as wholesale energy bid prices in CAISO markets) |  |  |  |  |  | 
4.1 | Quantity (MW) of DR resources bid into CAISO and quantity and percent dispatched | See below. |  | CAISO / DRPs |  | N
4.2 | Quantity (MW) and percent of DR resources bid into CAISO below the monthly NBT threshold? | For what hours? During these hours, what quantity of DR resources were dispatched? |  | CAISO / DRPs |  | Y
4.3 | Quantity (MW) and percent of DR resources dispatched compared to total resources dispatched by CAISO | As bid; procured; By PDR / RDR; By resource type: system, flexible and local capacity; By customer class; DRP; By New /returning 3P; with / without scheduling coordinator costs included; for August / by month / by year) |  | CAISO / DRPs |  | N
4.4 | High, low and weighted average August DR bid price not dispatched as compared to high, low and weighted average price of dispatched resources |  |  | CAISO / DRPs |  | Y

## Slide 16
Criteria & Proposed Metrics |  | Assess by or Compare to: |  |  | Data Source | C? | 
Did demand response providers aggregate the capacity they contracted, or replace it with demand response from another source in a timely manner? |  |  |  |  |  |  | 
5.1 | Quantity (MW) and percent of DRAM resources in Supply Plans as compared contracted amounts. Compare to IOU DR resources |  | By customer class; By Aggregator By new / returning third party providers ; By PDR or RDR resource By type of RA: System / Flexible / Local capacity | IOUs |  |  | N
5.2 | Quantity (MW) and percentage of DR resources using each of the three contractually-approved methods of receiving capacity payments |  |  | DRPs |  |  | Y
5.3 | Number of capacity payments withheld, reasons, and MW/value affected |  |  | IOUs / DRPs ED interviews |  |  | Y
5.4 | Quantity and value of contracts terminated and/or penalized by IOUs for non-performance; Value of any assessed fees on 3Ps |  |  | ED interviews with DRPs, IOUs; Quantitative data |  |  | Y
5.5 | Total and percentage of bidders found to have engaged in non-competitive behavior |  |  | ED staff / IE reports |  |  | Y
5.6 | Quantity and percent of DRAM resources in Supply Plans provided to CAISO (by SCs at 45 days+) as compared to Supply Plans provided to IOUs (by 3Ps) |  |  | CAISO / IOUs |  |  | N
5.7 | Quantity and percent of contracted capacity for which CAISO registrations occurred after SC’s Supply Plans provided to CAISO (at 45 days+) |  |  | CAISO /DRPs |  |  | N
5.8 | Quantity (MW) and percent of contracts for which Seller provided capacity from non-residential meters, when contracted for residential |  |  | IOUs |  |  | N

## Slide 17
Criteria & Proposed Metrics |  | Assess by or Compare to: | Data Source |  | C?
Were resources reliable when dispatched, i.e. did customers perform appropriately? |  |  |  |  | 
6.1 | Quantity (MW) and percentage of total dispatched DR resources subject to RRAIM penalties Compare to IOU DR | DRAM II only PDR / RDRR August, annual, peak days |  | CAISO | Y
6.2 | Quantity (MW) and percent of total dispatched DR resources subject to Uninstructed Energy Imbalance (UEI) fines | RDRR / PDR resources DRAM and IOU DR Annually, peak days, August |  | CAISO | Y
6.3 | Load impacts of DRAM resources during CAISO dispatch events | RDRR / PDR resources DRAM and IOU DR Annually, peak days, August |  | CAISO; DRPs | N
6.4 | Response time and quantity (MW) of response to dispatch | RDRR / PDR resources DRAM and IOU DR Annually, peak days, August |  | CAISO | Y

## Slide 18: Project Timeline
Phase 1 DRAM I and II auctions. DRAM I delivery; first half of DRAM II deliveries (Jan- June).
Phase 2 DRAM III auction
Second half of DRAM II deliveries (July – December). Interviews with DRAM market participants and IOUs.

## Slide 19: Treatment of Confidential Data
Will abide by Commission Decisions, Resolutions & PUC codes:
  Resolution E-4728
  PUC Code Section 314, Subdivision (b)
  PUC Code Section 583, Subdivision (b)
  Commission General Order 66-C
  D.16-08-024 at page 19
  D.06-06-066

## Slide 20: Data Granularity / Sources ?
Granularity
  Will generally use smallest granularity available
  Have requested 5 min dispatch data from CAISO
  Input ?
Sources
  Are there additional data sources not yet discussed?

## Slide 21: Any Additional Questions / Comments?
Deadline for written comments March 13
Please send your comments to cathleen.fogel@cpuc.ca.gov and copy the Service List of R.13-09-011
Request comments not exceed five pages, double spaced.
Some questions for comment are in Appendix A of the draft Plan (and next slide)
Energy Division will release a final DRAM Evaluation Plan & Metrics by April 1, 2017.

## Slide 22: Specific Questions for Comment (not required)
Are the goals & objectives complete?
Concerns / suggestions about handling and/or presentation of confidential data?
Missing metrics?
Data source / granularity suggestions? Can your organization provide data not mentioned?
What metrics are the most important to demonstrate the success of the DRAM?
What ones do you see as least important or fully optional?
Overall project and/or individual phase timeline?
Additional comments.