## Detailed Project Information
Pacific Gas and Electric Company data for R.17-05-010 submitted on 4/17/2020
(I.d-g, II.a-c) Detailed Project Information
Rule 20A Community | Project Details | [11 empty] | Number of Projects Per Community (Totals) | [6 empty] | Project Timelines | [9 empty] | Project Execution Details |  |  |  |  | Who Perfromed the Work |  |  |  | Costs | [20 empty] | Work Credits | [10 empty] | Delays, Challenges to Completion | [7 empty] | Environmental and Cultural Issues
| Project Name | Unique Project Identifier (e.g. Work Order No.) | Undergrounding District Name | Zip Code | Census Tract | Disadvantaged Community Census Tract | Percent of CARE Customers in Census Tracts Affected by the Project | Street location of the project, or the location boundary (if more than one street) | Fire Hazard Severity Zone | Please describe the reason(s) the project was qualified under Rule 20A project criteria* | Please Cite the Original Document(s) by Name in which Rule 20A Project Qualifications were Assessed for the Project | Is the Project Compelete? | Number of Projects with Undergrounding District that Were Formed** | Number of Projects Initiated for the next ten years (Project has started but no utilities conversion plan)** | Number of Projects in planning phase with a Utilities Conversion Plan** | Number of Projects in progress (construction)** | Number of Projects Completed** | Urban/ Suburban/ Rural | Disadvantaged Community? | Project Resolution Pass Date/Date of Undergrounding District Formation | Project Design Start Date | Project Construction Start Date | Project Construction End Date | Project Completed | Date Rule 20A Work Credits are Redeemed | Please Explain if Credits were Transferred Over Additional Days | Total Business Days (S5-R5) | If Project not completed, Expected Completion Date | Date Cancelled, if Cancelled | Number of Poles Removed | Number of meters converted to underground services | Circuit miles of primary underground lines installed | Project Trenched Footage | Characterization of Project Area | Were Contractors Hired for any Portion of Project Completion? | % of Project Work Performed by Electric Utility (In-house) and funded by Rule 20A Work Credits | % of Project Work Performed by Contractors and funded by Rule 20A Work Credits | Total % Work Performed that was funded by Rule 20A Work Credits | Estimated Cost of Projects Initiated/ in Progress | Work Credits Redeemed | Factor for 2018 Real Dollars | Work Credits Redeemed in 2018 Real Dollars | Cost per foot – Nominal Dollars | Cost per foot – 2018 Real Dollars | Non-Ratepayer Repaving Costs | Non-Ratepayer Communications Infrastructure Costs | Non-Ratepayer Streetlighting Costs | Non-Ratepayer City Department Staff Time Costs | Subsurface Transformers Costs funded by Rule 20A Work Credits (if any) | Percent of Subsurface Transformers funded by Rule 20A Work Credits (N/A if none) | Grid Hardening work funded by Rule 20A Work Credits (if any) | Percent of Grid Hardening work funded by Rule 20A Work Credits (N/A if none) | Direct Payment by Community to Utility for Insufficient Rule 20A funds | Total Non-Ratepayer Costs (sum of AK5 through AO5) | Total Cost of Completed Project AJ5 + AP5 (Equals AJ5 if no known Non-Ratepayer Costs) | Difference Between Total Cost and Esitmated Cost (AO5-AP5) | Identify and Quantify Factors that Contribute to Cost Variances | Adjustments to Previously Completed Projects | Date of Adjustments | Value of Work Credits (in USD) used for the Project | All Eligible Work Credits Available to Community at the Time When Work Credits are Redeemed (Excluding Borrowing Forward and Purchasing from Other Communities) | Value of Work Credits Borrowed Forward up to 5 Years | Value of Work Credits Borrowed Forward Beyond 5 Years | Please Cite by Name of Document(s) in Which Utility Gained CPUC Approval to Permit Communities to Borrow Forward Beyond 5 Years | Did the Project (completed or underway) rely on purchased credits from other communities? | Value of Credits Purchased from other communities | Source of Purchased Work Credits | Percent of Ratepayer Project Funding from Credits Purchased from other communities | Cost of Acquiring Those Credits (e.g. $0.50 per each $1 of Credits, if known) | Please Cite Document(s) by Name in Which Utility Granted Approval of Credit Purchasing Transaction Between Communities | Delays Due to IOU and/or Third Party Contractor Design & Construction | Delays to Local Government Coordination Challenges | Delays Due to Challenges with Communication Providers or Sewage Entities | Delays Due to Unexpected Events | Delays Due to Insufficient Work Credits at Initiation or During the Project Lifecycle | Delays Due to Other Causes | Unknown Cause of Delays | Additional Challenges to Project Completion (if Unfinished) and Experienced by Projects (if completed) | Environmental Issues (e.g. contaminated soils) | Amount Paid for Remediation (if any) | Amount of Rule 20A Credits Paid for Remediation (if any) | Cultural Issues | Amount Paid for Resolving Cultural Issues (if any) | Amount of Rule 20A Credits Paid for Resolving Cultural Issues (if any)
| Name | Name | Name | Number | Number | Yes/No/Uncertain | % | Address | Zone 1/Tier 2/Tier 3/None/Unknown | Explanation | Explanation | Yes/No/Unknown | Total Number | Total Number | Total Number | Total Number | Total Number | Explanation | Yes/No/Unknown | Date | Date | Date | Date | Date | Date | Explanation | Number | Date | Date | Number | Number | Miles | Feet | Explanation | Explanation | % | % | % | Nominal $ | Nominal $ | 2018 Real $ | 2018 Real $ | Nominal $ | 2018 Real $ | Nominal $ | Nominal $ | Nominal $ | Nominal $ | Nominal $ | % | Nominal $ | % | Nominal $ | Nominal $ | Nominal $ | Nominal $ | Explanation & Nominal $ | Nominal $ | Date | Nominal $ | Nominal $ | Nominal $ | Nominal $ | Explanation | Yes/No/Unknown | Nominal $ | Explanation | % | Nominal $ | Explanation | Yes/No/Unknown | Yes/No/Unknown | Yes/No/Unknown | Yes/No/Unknown | Yes/No/Unknown | Yes/No/Unknown | Yes/No/Unknown | Explanation | Explanation | Nominal $ | Nominal $ | Explanation | Nominal $ | Nominal $
Alameda County
ALAMEDA COUNTY | *CANC* E14TH ST PH 3 | 30633334 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | 43 | 11 | 8 | 3 | 25 | N/A | N/A | 1998-05-12 | TBD | TBD | TBD | N/A | 2015-01-15 | N/A | #VALUE! | N/A | 2014-08-03 | N/A | N/A | Cancelled project | Cancelled project | N/A | N/A | N/A | N/A | N/A | N/A | 34151.88 | 1.0677 | 36464.7534 | [6 empty] | N/A | N/A |  |  | 0 |  |  |  | N/A, project cancelled |  |  | 34151.88 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALAMEDA COUNTY | E 14TH PH II | 30308833 | E 14TH PH 2 | 94578 | 6001434000 | No | 17.94% | E 14TH ST, 162ND & HWY 238 | None | TBD | Resolution# 2000-77 | Yes | 43 | 11 | 8 | 3 | 25 | Unknown | No | 1998-05-12 | 2003-04-29 | 2005-09-01 | 2012-12-11 | 2016 | 2016-10-19 | N/A | 1813 | N/A | N/A |  |  | 4.14 | 15100.8 | Unknown | Unknown |  |  |  | N/A | 8618365.16 | 1.0668 | 9194347.3224 | [10 empty] | 0 |  |  |  | Unknown |  |  | 8618365.16 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
ALAMEDA COUNTY | E14TH I R20A | 30082775 | E 14TH PH 1 | 94578 | 6001433800 | No | 11.55% | E 14TH PH 1 | None | TBD | TBD | Yes | 43 | 11 | 8 | 3 | 25 | Urban | No | TBD | 2000-01-20 | 2003-04-02 | 2003-07-28 | 2006 | 2007-03-24 | N/A | #VALUE! | N/A | N/A |  | 57 | 2.52 | 5976.96 | Commercial | Yes |  |  |  | N/A | 2918232.14 | 1.591 | 4642808.2965 | [6 empty] | 0 | N/A |  |  | 0 |  |  |  | Restrictive work conditions |  |  | 2918232.14 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | Yes | No | No | No | No | No | None | None | N/A | N/A | None | N/A | N/A
ALAMEDA COUNTY | HESPERIAN BLVD, ALAMEDA COUNTY | 74001557 | HESPERIAN BLVD, UUD# 19 | 94541 | Unknown | Unknown | Unknown | HESPERIAN BLVD, HWY 880 & WEST A ST | Unknown | Project met one or more Rule 20A criteria | Ordinance# 2009-6 | No | 43 | 11 | 8 | 3 | 25 | Urban | Unknown | 2009-01-13 | 2015-05-21 | 2019-03-04 | TBD | TBD | N/A | N/A | 2319 | 2019-12-18 | N/A | TBD | TBD | Project not completed or closed | Project not completed or closed | Commercial | Yes | TBD | TBD | TBD | 4608907.02 | N/A | TBD | N/A | [6 empty] | TBD | TBD |  |  | 0 |  |  |  | Project in progress |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Yes | Yes | No | No | No | No | No | Scope change after new business project was cancelled | None | N/A | N/A | None | N/A | N/A
ALAMEDA COUNTY | LEWELLING BLVD | 30387770 | LEWELLING BLVD | 94580 | 6001433700 | No | 12.13% | LEWELLING BLVD | None | TBD | Resolution# 2004-820 | Yes | 43 | 11 | 8 | 3 | 25 | Unknown | No | TBD | TBD | TBD | 2011-04-15 | 2013 | 2014-02-28 | N/A | #VALUE! | N/A | N/A |  |  | 2.52 | 7814.4 | Unknown | Unknown |  |  |  | N/A | 3361081 | 1.1048 | 3713335.4408 | [10 empty] | 0 |  |  |  | Unknown |  |  | 3361081 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
ALBANY | BUCHANAN ST & MARIN AVE PH 1, ALBANY | 74001549 | BUCHANAN/MARIN | 94706 | 6001420400 | No | 0% | MARIN AVE, SAN PABLO AVE & MASONIC AVE | None | Project met one or more Rule 20A criteria | Resolution# 2010-32 | Yes | 43 | 11 | 8 | 3 | 25 | Urban | No | 2010-06-21 | 2016-01-25 | 2017-09-14 | 2018-10-12 | 2019 | 2019-11-21 | N/A | 2044 | N/A | N/A | 24 | 34 | 0.62276 | 3288.1833 | Residential | Yes | TBD | TBD | TBD | N/A | 3100967.09 | TBD | 3100967.09 |  |  | Unknown | Unknown | Unknown | Unknown | 400000 | 100% |  |  | 0 |  |  |  | Unexpected field conditions |  |  | 3100967.09 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Yes | Yes | No | Yes | Yes | No | No | Insufficient allocation. Design issues. | None | N/A | N/A | None | N/A | N/A
BERKELEY | GRIZZLY PEAK BLVD, BERKELEY | 74001486 | GRIZZLY PEAK BLVD, UUD# 48 | 94704 | 6001421600 | No | 1.18% | GRIZZLY PEAK BLVD, HILL RD, SUMMIT RD, SUMMIT LN, SENIOR AVE, HARVARD CIR, FAIRLAWN & AVENIDA DR | Tier 2 | Project met one or more Rule 20A criteria | Resolution# 56,934 - N.S. | No | 43 | 11 | 8 | 3 | 25 | Urban | No | 1993-04-27 | 2014-07-07 | TBD | TBD | TBD | N/A | N/A | 7741 | 2021-09-03 | N/A | TBD | TBD | Project not completed or closed | Project not completed or closed | Residential | Yes | TBD | TBD | TBD | 8625793.09 | N/A | TBD | N/A | [6 empty] | TBD | TBD |  |  | 0 |  |  |  | Project in progress |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Yes | Yes | Yes | Yes | No | No | No | Easement acquisitions. Retaining wall design. | None | N/A | N/A | None | N/A | N/A
BERKELEY | MILLER/STEVENSON | 30454814 | MILLER/STEVENSON | 94708 | 6001421500 | No | 1.264% | MILLER/STEVENSON | Tier 2 | TBD | TBD | Yes | 43 | 11 | 8 | 3 | 25 | Suburban | No | 1992-01-07 | 2005-11-15 | 2006-10-26 | 2009-12-14 | 2012 | 2012-09-13 | N/A | 5061 | N/A | N/A |  |  | 2.32 | 6547.2 | Residential | Unknown |  |  |  | N/A | 5118222.1 | 1.121 | 5737738.3213 | [6 empty] | Unknown | TBD |  |  | 0 |  |  |  | Unexpected field conditions |  |  | 5118222.1 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
BERKELEY | VISTAMONT AVE, BERKELEY | 30817976 | VISATMONT AVE, UUD# 35A | 94704 | 6001421100 | No | 0.8534% | VISTAMONT AVE, WILD CAT CANYON RD, MY WAY, ROCHDALE WAY, ROSEMONT AVE | Tier 2 (part of project in or adjacent to Tier 3) | Project met one or more Rule 20A criteria | Resolution# 56,972-N.S. | No | 43 | 11 | 8 | 3 | 25 | Unknown | No | 1992-12-10 | TBD | TBD | TBD | TBD | N/A | N/A | #VALUE! | 2023-04-01 | N/A |  |  | Project not completed or closed | Project not completed or closed | Unknown | Unknown | TBD | TBD | TBD | 10476994.43 | N/A | TBD | N/A | [6 empty] | TBD | TBD |  |  | 0 |  |  |  | Project in planning phase |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | Yes | No | No | Insufficient allocation | None | N/A | N/A | None | N/A | N/A
DUBLIN | DOUGHERTY | 30408801 | DOUGHERTY | 94568 | 6001450300 | No | 3.823% | DOUGHERTY | None | TBD | TBD | Yes | 43 | 11 | 8 | 3 | 25 | Unknown | No | 2004-02-03 | 2005-01-26 | 2006-04-26 | 2006-12-19 | 2008 | 2008-08-18 | N/A | 358 | N/A | N/A |  |  | 0.69 | 5438.4 | Unknown | Unknown |  |  |  | N/A | 1215529.2 | 1.3051 | 1586439.1626 | [10 empty] | 0 |  |  |  | Unknown |  |  | 1215529.2 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
DUBLIN | DUBLIN BLVD, DUBLIN | 31052180 | DUBLIN BLVD | 94568 | 6001450300 | No | 3.823% | DUBLIN BLVD, CIVIC DR, DUBLIN CT | None | Project met one or more Rule 20A criteria | Ordinance# 4-13 | Yes | 43 | 11 | 8 | 3 | 25 | Unknown | No | 2013-08-20 | 2015-06-26 | 2017-08-17 | 2017-09-29 | TBD | TBD | N/A | 675 | 2020-02-29 | N/A |  |  | Project not completed or closed | Project not completed or closed | Unknown | Unknown |  |  |  | 1667848.68 | 1230651.02 | TBD | 1230651.02 | [10 empty] | 0 |  |  |  | Unknown |  |  | 1230651.02 |  |  |  |  | Yes | 750000 | Vallejo | 60.94% | 300000 | PG&E does not grant approval for credit transfer transactions. Credit transfers are agreed upon between communities. | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
FREMONT | BAY ST | 30155006 | BAY ST | 94538 | 6001442302 | No | 12.03% | BAY ST | None | TBD | TBD | Yes | 43 | 11 | 8 | 3 | 25 | Suburban | No | 2004-11-02 | 2007-12-11 | 2009-08-12 | 2009-11-23 | 2011 | 2012-02-07 | N/A | 1134 | N/A | N/A |  |  | 0.48 | 1900.8 | Commercial | Unknown |  |  |  | N/A | 1251374 | 1.1878 | 1486349.4996 | [10 empty] | 0 | [6 empty] | 1251374 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
FREMONT | CENTRAL AVE | 30276150 | CENTRAL AVE | 94536 | 6001442602 | No | 4.986% | CENTRAL AVE | None | TBD | TBD | Yes | 43 | 11 | 8 | 3 | 25 | Unknown | No | 2003-09-23 | 2004-08-10 | 2005-08-18 | 2007-05-10 | 2009 | 2010-03-16 | N/A | 322 | N/A | N/A |  |  | 0.78 | 2270.4 | Unknown | Unknown |  |  |  | N/A | 1916781.12 | 1.2297 | 2357024.8912 | [10 empty] | 0 |  |  |  | Unknown |  |  | 1916781.12 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
FREMONT | FREMONT BLVD-IRVINGTON | 30155281 | FREMONT BLVD-IRVINGTON | 94538 | 6001442301 | No | 5.492% | FREMONT BLVD-IRVINGTON | None | TBD | TBD | Yes | 43 | 11 | 8 | 3 | 25 | Unknown | No | TBD | 2001-05-14 | 2002-06-03 | 2002-11-06 | 2007 | 2007-07-31 | N/A | #VALUE! | N/A | N/A |  |  | 1.42 | 4012.8 | Unknown | Unknown |  |  |  | N/A | 1216245.94 | 1.4306 | 1739933.7448 | [10 empty] | 0 |  |  |  | Unknown |  |  | 1216245.94 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
FREMONT | WASH/680 | 30242356 | WASH/680 | 94539 | 6001442200 | No | 2.473% | WASH/680 | None | TBD | TBD | Yes | 43 | 11 | 8 | 3 | 25 | Suburban | No | TBD | TBD | TBD | 2004-05-27 | 2008 | 2008-08-18 | N/A | #VALUE! | N/A | N/A | 15 | 17 | 0.88 | 2851.2 | Residential | No |  |  |  | N/A | 1087762.28 | 1.3051 | 1419685.0891 | [6 empty] | 0 | N/A |  |  | 0 |  |  |  | Other |  |  | 1087762.28 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | No | No | None | None | N/A | N/A | None | N/A | N/A
FREMONT | WASHINGTON & ROBERTS | 30242352 | WASHINGTON BLVD & ROBERTS AVE, UUD# 35 | 94539 | 6001442200 | No | 2.473% | WASHINGTON BLVD & ROBERTS AVE, OSGOOD/DRISCOLL RD & ALICE ST | None | TBD | Ordinance# 2520 | Yes | 43 | 11 | 8 | 3 | 25 | Unknown | No | TBD | TBD | TBD | 2010-03-29 | 2015 | 2016-01-13 | N/A | #VALUE! | N/A | N/A |  |  | 1.29 | 9028.8 | Unknown | Unknown |  |  |  | N/A | 3501281.81 | 1.0677 | 3738399.6917 | [10 empty] | 0 | [6 empty] | 3501281.81 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
FREMONT | FREMONT BLVD, FREMONT | No Order | UUD# 38 | 94536 | 6001441302 | No | 2.701% | FREMONT BLVD BETWEEN ALDER AVE & THORNTON AVE | None | Project met one or more Rule 20A criteria | Ordinance# 12-2018 | No | 43 | 11 | 8 | 3 | 25 | Suburban | No | 2018-04-17 | TBD | TBD | TBD | TBD | N/A | N/A | #VALUE! | 0 | N/A | 0 | 0 | Project not completed or closed | Project not completed or closed | Commercial | Unknown | TBD | TBD | TBD | 2133372.62 | N/A | TBD | N/A | [6 empty] | TBD | TBD | [6 empty] | Project in planning phase |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | Yes | No | No | Insufficient allocation | None | N/A | N/A | No | N/A | N/A
FREMONT | PERALTA BLVD, FREMONT | No Order | UUD 37 | 94536 | 6001441700 | No | 7.275% | PERALTA BLVD FROM FREMONT BLVD TO SEQUOIA RD | None | Project met one or more Rule 20A criteria | Ordinance# 11-2018 | No | 43 | 11 | 8 | 3 | 25 | Rural | No | 2018-04-17 | TBD | TBD | TBD | TBD | N/A | N/A | #VALUE! | 0 | N/A | 0 | 0 | Project not completed or closed | Project not completed or closed | Residential | Unknown | TBD | TBD | TBD | 1660709.48 | N/A | TBD | N/A | [6 empty] | TBD | TBD | [6 empty] | Project in planning phase |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | Yes | No | No | Insufficient allocation | None | N/A | N/A | No | N/A | N/A
HAYWARD | *CANC* EP WATKINS ST HAYWARD R20A | 30677630 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | 43 | 11 | 8 | 3 | 25 | N/A | N/A | 2008-09-23 | TBD | TBD | TBD | N/A | N/A | N/A | #VALUE! | N/A | 2012-11-04 | N/A | N/A | Cancelled project | Cancelled project | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [6 empty] | N/A | N/A |  |  | 0 |  |  |  | N/A, project cancelled |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HAYWARD | MISSION BLVD DIST 25 | 30677789 | MISSION BLVD, DIST 25 | 94542 | 6001436500 | No | 10.65% | MISSION BLVD, HARDER RD & SYCAMORE RD | None | TBD | Resolution# 01-025 | Yes | 43 | 11 | 8 | 3 | 25 | Urban | No | 2001-01-09 | 2009-06-01 | 2011-08-31 | 2012-06-27 | 2014 | 2015-01-15 | N/A | 3065 | N/A | N/A | 95 |  | 3.48 | 9028.8 | Commercial | Yes |  |  |  | N/A | 7211391.06 | 1.0831 | 7810529.9113 | [6 empty] | 3 subsurface transformers | Unknown |  |  | 0 |  |  |  | Unexpected field conditions |  |  | 7211391.06 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Yes | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
HAYWARD | MISSION BLVD DIST 29 HAYWARD R20A | 30882110 | MISSION BLVD DIST 29 | 94541 | 6001435400 | No | 11.66% | MISSION BLVD, A ST; PAST ROSE ST TO CITY LIMIT | None | Project met one or more Rule 20A criteria | Resolution# 10-183 | No | 43 | 11 | 8 | 3 | 25 | Unknown | No | 2010-12-07 | TBD | TBD | TBD | TBD | N/A | N/A | #VALUE! | TBD | N/A |  |  | Project not completed or closed | Project not completed or closed | Unknown | Unknown | TBD | TBD | TBD | N/A | N/A | TBD | N/A | [6 empty] | TBD | TBD |  |  | 0 |  |  |  | Project in planning phase |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | Yes | No | No | Insufficient allocation | None | N/A | N/A | None | N/A | N/A
HAYWARD | MISSION BLVD DIST 30 HAYWARD R20A | 74011982 | MISSION BLVD DIST 30 | 94544 | Unknown | Unknown | Unknown | MISSION BLVD, SOUTH OF ARROWHEAD & GRESEL ST | Unknown | Project met one or more Rule 20A criteria | Resolution# 10-184 | No | 43 | 11 | 8 | 3 | 25 | Urban | Unknown | 2010-12-07 | 2017-07-05 | 2019-01-07 | 2019-07-03 | TBD | N/A | N/A | 2402 | 2019-06-17 | N/A | TBD | TBD | Project not completed or closed | Project not completed or closed | Commercial | Yes | TBD | TBD | TBD | 2760977.86 | N/A | TBD | N/A | [6 empty] | TBD | TBD |  |  | 0 |  |  |  | Project in progress |  |  | N/A |  |  |  |  | Yes | 1249697 | Corcoran | N/A | Unknown | PG&E does not grant approval for credit transfer transactions. Credit transfers are agreed upon between communities. | No | No | No | No | Yes | No | No | Insufficient allocation | None | N/A | N/A | None | N/A | N/A
HAYWARD | MISSION OVERHILL DIST 27 | 30677628 | MISSION OVERHILL, DIST 27 | 94544 | 6001435104 | No | 13.57% | MISSION BLVD, CALHOUN & OVERHILL DR | None | TBD | Resolution# 07-135 | Yes | 43 | 11 | 8 | 3 | 25 | Urban | No | 2007-09-11 | 2009-08-20 | 2012-05-01 | 2012-06-27 | 2014 | 2015-01-15 | N/A | 709 | N/A | N/A | 73 |  | 2.57 | 7180.8 | Commercial | Yes |  |  |  | N/A | 4975614.31 | 1.0831 | 5388999.7189 | [6 empty] | 7 subsurface transformers | Unknown |  |  | 0 |  |  |  | Unexpected field conditions |  |  | 4975614.31 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Yes | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
HAYWARD | MISSION/CALHOUN | 30146944 | MISSION/CALHOUN | 94544 | 6001437900 | No | 7.228% | MISSION/CALHOUN | None | TBD | TBD | Yes | 43 | 11 | 8 | 3 | 25 | Suburban | No | 2002-02-19 | 2002-05-24 | 2003-05-20 | 2008-04-07 | 2012 | 2012-09-13 | N/A | 94 | N/A | N/A |  |  | 2.1 | 5174.4 | Commercial | Unknown |  |  |  | N/A | 3371422.79 | 1.121 | 3779504.164 | [10 empty] | 0 | [6 empty] | 3371422.79 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
LIVERMORE | *CANC* NORTH L ST | 30647110 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | 43 | 11 | 8 | 3 | 25 | N/A | N/A | 2007-09-10 | TBD | TBD | TBD | N/A | 2015-01-15 | N/A | #VALUE! | N/A | 2014-09-24 | N/A | N/A | Cancelled project | Cancelled project | N/A | N/A | N/A | N/A | N/A | N/A | 103735.05 | 1.0677 | 110760.3158 | [6 empty] | N/A | N/A |  |  | 0 |  |  |  | N/A, project cancelled |  |  | 103735.05 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LIVERMORE | CONCANNON | 30384525 | CONCANNON | 94550 | 6001451704 | No | 2.45% | CONCANNON | None | TBD | TBD | Yes | 43 | 11 | 8 | 3 | 25 | Unknown | No | 1999-04-12 | 2004-07-06 | 2005-06-06 | 2006-04-10 | 2007 | 2007-07-31 | N/A | 1912 | N/A | N/A |  |  | 0.4 | 1372.8 | Unknown | Unknown |  |  |  | N/A | 637872.59 | 1.4306 | 912526.0013 | [10 empty] | 0 |  |  |  | Unknown |  |  | 637872.59 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
LIVERMORE | ISABEL AVE, LIVERMORE | 31064287 | ISABEL AVE | 94550 | 6001451703 | No | 1.969% | ISABEL AVE, VINEYARD AVE/NORTH OF CONANNON BLVD | None | Project met one or more Rule 20A criteria | Resolution# 2014-026 | Yes | 43 | 11 | 8 | 3 | 25 | Suburban | No | 2014-02-24 | 2014-05-01 | 2017-08-17 | 2017-11-29 | 2018 | 2018-10-23 | N/A | 66 | N/A | N/A | 24 | 3 | 1.0813 | 5709.4123 | Residential | Yes |  |  |  | N/A | 1781725 | TBD | 1781725 | [6 empty] | 0 | N/A |  |  | 0 |  |  |  | Restrictive work conditions |  |  | 1781725 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | Yes | No | No | No | No | No | None | None | N/A | N/A | None | N/A | N/A
NEWARK | NEWARK BLVD, NEWARK | No Order | NEWARK UNDERGROUND DISTRICT NO. 15 | 94560 | 6001444400 | No | 7.333% | NEWARK BLVD BTW FAIR AVE & BELLHAVEN AVE | None | Project met one or more Rule 20A criteria | Resolution# 10,966 | No | 43 | 11 | 8 | 3 | 25 | Rural | No | 2019-07-25 | TBD | TBD | TBD | TBD | N/A | N/A | #VALUE! | 0 | N/A | 0 | 0 | Project not completed or closed | Project not completed or closed | Residential | Unknown | TBD | TBD | TBD | 1748975.56 | N/A | TBD | N/A | [6 empty] | TBD | TBD | [6 empty] | Project in planning phase |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | Yes | No | No | Insufficient allocation | None | N/A | N/A | No | N/A | N/A
OAKLAND | MACARTHUR PH 1 | 30215963 | MACARTHUR PH 1 | 94605 | 6001410100 | No | 15.92% | MACARTHUR PH 1 | None | TBD | TBD | Yes | 43 | 11 | 8 | 3 | 25 | Unknown | No | TBD | TBD | TBD | 2007-05-18 | 2012 | 2012-09-13 | N/A | #VALUE! | N/A | N/A |  |  | 2.77 | 7814.4 | Unknown | Unknown |  |  |  | N/A | 4295231.71 | 1.121 | 4815132.1103 | [10 empty] | 0 |  |  |  | Unknown |  |  | 4295231.71 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
OAKLAND | MACARTHUR PH 2 | 30240908 | MACARTHUR PH 2 | 94605 | 6001409800 | No | 11.78% | MACARTHUR PH 2 | None | TBD | TBD | Yes | 43 | 11 | 8 | 3 | 25 | Unknown | No | 2001-09-25 | 2002-02-05 | 2004-10-15 | 2007-08-09 | 2012 | 2012-09-13 | N/A | 133 | N/A | N/A |  |  | 2.34 | 6969.6 | Unknown | Unknown |  |  |  | N/A | 4043229.39 | 1.121 | 4532627.1036 | [10 empty] | 0 |  |  |  | Unknown |  |  | 4043229.39 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
OAKLAND | MACARTHUR PH 3 | 30240911 | MACARTHUR PH 3 | 94605 | 6001408300 | No | 10.15% | MACARTHUR PH 3 | None | TBD | TBD | Yes | 43 | 11 | 8 | 3 | 25 | Unknown | No | 2001-09-25 | 2002-01-24 | 2006-06-12 | 2008-04-28 | 2012 | 2012-09-13 | N/A | 121 | N/A | N/A |  |  | 2.5 | 4963.2 | Unknown | Unknown |  |  |  | N/A | 4966230.4 | 1.121 | 5567349.3494 | [10 empty] | 0 |  |  |  | Unknown |  |  | 4966230.4 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
OAKLAND | PIEDMONT PINES PH 1 | 30618097 | PIEDMONT PINES PH 1 | 94611 | 6001404600 | No | 1.126% | PIEDMONT PINES, MONTEREY BLVD & WILTON DR | Tier 3 (part of project in or adjacent to Tier 2) | Project met one or more Rule 20A criteria | Resolution# 75652 | Yes | 43 | 11 | 8 | 3 | 25 | Suburban | No | 2000-05-02 | 2008-07-03 | 2012-01-10 | 2013-06-07 | 2017 | 2017-07-17 | N/A | 2984 | N/A | N/A | 137 | 2236 | 4.56 | 15153.6 | Residential | Yes |  |  |  | N/A | 13740062.12 | 1.048 | 14400188.9493 | [6 empty] | 0 | N/A |  |  | 0 |  |  |  | Restrictive work conditions |  |  | 13740062.12 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | Yes | No | No | No | No | No | None | None | N/A | N/A | None | N/A | N/A
OAKLAND | PIEDMONT PINES PH 2, OAKLAND | No Order | PIEDMONT PINES PH 2 | 94611 | Unknown | Unknown | Unknown | CHELTON DR, SKYLINE BLVD & SCARBOROUGH DR | Unknown | TBD | Resolution# 75652 | No | 43 | 11 | 8 | 3 | 25 | Unknown | Unknown | 2000-05-02 | TBD | TBD | TBD | TBD | N/A | N/A | #VALUE! | TBD | N/A |  |  | Project not completed or closed | Project not completed or closed | Unknown | Unknown | TBD | TBD | TBD | 12547677 | N/A | TBD | N/A | [6 empty] | TBD | TBD |  |  | 0 |  |  |  | Project in planning phase |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | No | No | Unknown | None | N/A | N/A | None | N/A | N/A
OAKLAND | PIEDMONT PINES PH 3, OAKLAND | No Order | PIEDMONT PINES AREA, UUD# 232 | 94611 | Unknown | Unknown | Unknown | CASTLE DR/SKYLINE BLVD FROM MOUNTAINGATE WAY TO ASCOT DR | Unknown | Project met one or more Rule 20A criteria | Resolution# 75652 | No | 43 | 11 | 8 | 3 | 25 | Unknown | Unknown | 2000-05-02 | TBD | TBD | TBD | TBD | N/A | N/A | #VALUE! | TBD | N/A |  |  | Project not completed or closed | Project not completed or closed | Unknown | Unknown | TBD | TBD | TBD | 14975842 | N/A | TBD | N/A | [6 empty] | TBD | TBD |  |  | 0 |  |  |  | Project in planning phase |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | No | No | Unknown | None | N/A | N/A | None | N/A | N/A
PLEASANTON | FIRST ST | 30060281 | FIRST ST | 94566 | 6001450607 | No | 7.789% | FIRST ST | None | TBD | TBD | Yes | 43 | 11 | 8 | 3 | 25 | Unknown | No | TBD | TBD | TBD | 2005-08-04 | 2009 | 2009-07-29 | N/A | #VALUE! | N/A | N/A |  |  | 2.53 | 5068.8 | Unknown | Unknown |  |  |  | N/A | 2634710.77 | 1.2297 | 3239847.6807 | [10 empty] | 0 |  |  |  | Unknown |  |  | 2634710.77 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
PLEASANTON | STANLEY BLVD, PLEASANTON | 30937193 | STANLEY BLVD | 94566 | 6001450746 | No | 2.951% | STANLEY BLVD, SANTA RITA RD, FIRST ST | None | Project met one or more Rule 20A criteria | Resolution# 12-513 | Yes | 43 | 11 | 8 | 3 | 25 | Suburban | No | 2012-04-03 | 2014-05-01 | 2016-11-09 | 2017-01-30 | 2018 | 2018-04-30 | N/A | 758 | N/A | N/A | 20 | 16 | 1.4953 | 7895.1579 | Residential | Yes |  |  |  | N/A | 1681105.26 | TBD | 1681105.26 | [6 empty] | 0 | N/A |  |  | 0 |  |  |  | Restoration work |  |  | 1681105.26 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | No | No | None | None | N/A | N/A | None | N/A | N/A
SAN LEANDRO | BAYFAIR | 30055034 | BAYFAIR MALL | 94578 | 6001433102 | No | 8.874% | BAYFAIR MALL, E 14TH ST | None | TBD | TBD | Yes | 43 | 11 | 8 | 3 | 25 | Unknown | No | TBD | TBD | TBD | 2010-11-18 | 2014 | 2015-01-15 | N/A | #VALUE! | N/A | N/A |  |  | 1.96 | 4276.8 | Unknown | Unknown |  |  |  | N/A | 3179509.83 | 1.0831 | 3443670.7736 | [10 empty] | 0 | [6 empty] | 3179509.83 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
SAN LEANDRO | E 14TH ST N/O BAYFAIR, SAN LEANDRO | 30616108 | BAYFAIR PH 2 | 94578 | Unknown | Unknown | Unknown | E 14TH ST, 150TH & THORNTON AVE | Unknown | Project met one or more Rule 20A criteria | Resolution# 09-065 | No | 43 | 11 | 8 | 3 | 25 | Urban | Unknown | 2003-04-07 | 2013-08-13 | TBD | TBD | TBD | N/A | N/A | 3781 | 2020-06-30 | N/A | TBD | TBD | Project not completed or closed | Project not completed or closed | Commercial | No | TBD | TBD | TBD | 5086524.27 | N/A | TBD | N/A | [6 empty] | TBD | TBD |  |  | 0 |  |  |  | Project in progress |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Yes | Yes | No | No | No | No | No | None | None | N/A | N/A | None | N/A | N/A
SAN LEANDRO | EDEN RD SAN LEANDRO R20A | 30882109 | EDEN RD | 94577 | 6001432400 | Yes | 9.46% | EDEN RD, DOOLITTLE DR TO END OF POLE LINE | None | Project met one or more Rule 20A criteria | Resolution# 2011-106 | No | 43 | 11 | 8 | 3 | 25 | Unknown | Yes | 2011-06-06 | TBD | TBD | TBD | N/A | N/A | N/A | #VALUE! | N/A | TBD |  |  | Project not completed or closed | Project not completed or closed | Unknown | Unknown | TBD | TBD | TBD | N/A | N/A | TBD | N/A | [6 empty] | TBD | TBD |  |  | 0 |  |  |  | Project in planning phase |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | Yes | No | No | Insufficient allocation | None | N/A | N/A | None | N/A | N/A
SAN LEANDRO | W. ESTUDILLO | 30311335 | W ESTUDILLO | 94577 | 6001432600 | No | 10.57% | W ESTUDILLO | None | TBD | TBD | Yes | 43 | 11 | 8 | 3 | 25 | Suburban | No | 2003-04-07 | 2003-04-24 | 2004-02-24 | 2006-06-14 | 2009 | 2009-07-29 | N/A | 17 | N/A | N/A | 16 | 18 | 0.77 | 2534.4 | Residential | Yes |  |  |  | N/A | 989664.97 | 1.2297 | 1216969.921 | [6 empty] | 0 | N/A |  |  | 0 |  |  |  | Other |  |  | 989664.97 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | No | No | None | None | N/A | N/A | None | N/A | N/A
UNION CITY | C:EP SMITH STREET RULE 20A CITY OF *CANC | 30166271 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | 43 | 11 | 8 | 3 | 25 | N/A | N/A | TBD | TBD | TBD | TBD | N/A | 2007-03-24 | N/A | #VALUE! | N/A | 2004-12-31 | N/A | N/A | Cancelled project | Cancelled project | N/A | N/A | N/A | N/A | N/A | N/A | 12542.21 | 1.4306 | 17942.6 | [6 empty] | N/A | N/A |  |  | 0 |  |  |  | N/A, project cancelled |  |  | 12542.21 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
UNION CITY | MISSION & DECOTO RD, UNION CITY | 30616111 | MISSION BLVD, UUD# 19 | 94587 | 6001440335 | No | 4.464% | MISSION BLVD, DECOTO RD & 7TH ST/APPIAN WAY | None | Project met one or more Rule 20A criteria | Resolution# 3755-09 | Yes | 43 | 11 | 8 | 3 | 25 | Unknown | No | 2009-02-10 | 2013-08-13 | 2015-07-09 | 2016-03-01 | 2017 | 2017-04-14 | N/A | 1645 | N/A | N/A |  |  | 1.42 | 6336 | Unknown | Unknown |  |  |  | N/A | 2549343.6 | 1.048 | 2671824.1312 | [10 empty] | 0 |  |  |  | Unknown |  |  | 2549343.6 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
Alameda County Total | [41 empty] | 0
Amador County | [41 empty] | 0
AMADOR COUNTY | FIDDLETOWN | 30326713 | FIDDLETOWN | 95629 | 6005000200 | No | 9.889% | FIDDLETOWN | Part of project in or adjacent to Zone 1 | TBD | TBD | Yes | 1 | 0 | 0 | 0 | 1 | Suburban | No | 2002-12-10 | 2004-09-27 | 2006-10-03 | 2007-08-31 | 2009 | 2009-07-29 | N/A | 657 | N/A | N/A | 13 | 20 | 0.66 | 2270.4 | Residential | Yes |  |  |  | N/A | 1191231.55 | 1.2297 | 1464832.0485 | [6 empty] | 0 | N/A |  |  | 0 |  |  |  | Unexpected field conditions |  |  | 1191231.55 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | No | No | None | None | N/A | N/A | Yes | 0 | 0
Amador County Total | [41 empty] | 0
Butte County | [41 empty] | 0
BUTTE COUNTY | COHASSET RD AND EAST AVE, CHICO | 30167443 | COHASSET RD AND EAST AVE, CHICO | 95926 | 6007000104 | No | 15.53% | COHASSET RD AND EAST AVE, CHICO | None | TBD | TBD | Yes | 11 | 4 | 3 | 1 | 6 | Unknown | No | 2001-03-20 | 2003-02-18 | 2004-04-20 | 2004-11-17 | 2007 | 2007-07-31 | N/A | 700 | N/A | N/A |  |  | 0.98 | 4593.6 | Unknown | Unknown |  |  |  | N/A | 801892.36 | 1.4306 | 1147168.9491 | [10 empty] | 0 |  |  |  | Unknown |  |  | 801892.36 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
BUTTE COUNTY, CHICO | EAST AVE COHASSET TO CEONOTHUS | 30411562 | EAST AVE COHASSET TO CEONOTHUS | 95926 | 6007000102 | No | 15.97% | EAST AVE COHASSET TO CEONOTHUS | None | TBD | TBD | Yes | 11 | 4 | 3 | 1 | 6 | Urban | No | 2005-04-29 | 2005-07-18 | 2006-10-05 | 2008-04-28 | 2009 | 2010-03-16 | N/A | 80 | N/A | N/A |  |  | 3.42 | 9377.28 | Residential | No |  |  |  | N/A | 3457228.08 | 1.2297 | 4251279.6866 | [6 empty] | 0 | N/A |  |  | 0 | [6 empty] | 3457228.08 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | No | No | None | None | N/A | N/A | None | N/A | N/A
CHICO | BRUCE RD DIST 16, CHICO | 74009861 | BRUCE RD DIST 16 | 95928 | Unknown | Unknown | Unknown | BRUCE RD, EAST 20TH ST & STATE HWY 32 | Unknown | Project met one or more Rule 20A criteria | Resolution# 73-16 & 16-141 | No | 11 | 4 | 3 | 1 | 6 | Urban | Unknown | 2016-08-02 | 2017-05-15 | 2018-08-20 | 2019-10-17 | TBD | N/A | N/A | 286 | 2019-11-01 | N/A | TBD | TBD | Project not completed or closed | Project not completed or closed | Commercial | Yes | TBD | TBD | TBD | 4301989.98 | N/A | TBD | N/A | [6 empty] | TBD | TBD |  |  | 0 |  |  |  | Unexpected field conditions |  |  | N/A |  |  |  |  | Yes | 2442000 | Butte County | N/A | 0 | PG&E does not grant approval for credit transfer transactions. Credit transfers are agreed upon between communities. | Yes | Yes | Yes | Yes | No | Yes | No | Communication participants' slow response to required RFI's. City's additonal future road improvement plans resulted in adjustments to design. Internal resource limitation. During construction, rock was encountered and rock trenching/boring had to be performed. Easement acquisition challenges. Weather impacted schedule and site access. | None | N/A | N/A | None | N/A | N/A
CHICO | GEPEAST AVE RULE 20; CEONOTHUS TO CACT | 30099494 | EAST AVE; CEONOTHUS TO CACT | 95973 | 6007000103 | No | 9.687% | EAST AVE; CEONOTHUS TO CACT | None | TBD | TBD | Yes | 11 | 4 | 3 | 1 | 6 | Unknown | No | TBD | TBD | TBD | 2002-11-15 | 2005 | 2007-03-24 | N/A | #VALUE! | N/A | N/A |  |  | 0.29 | 2798.4 | Unknown | Unknown |  |  |  | N/A | 547886.7798 | 1.7065 | 934974.6555 | [10 empty] | 0 |  |  |  | Unknown |  |  | 547886.7798 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
CHICO | NORTH ESPLANADE DIST 17, CHICO | 74010863 | NORTH ESPLANADE DIST 17 | 95973 | Unknown | Unknown | Unknown | NORTH ESPLANADE, EATON RD & LEORA CT | Unknown | Project met one or more Rule 20A criteria | Resolution# 74-16 & 16-142 | No | 11 | 4 | 3 | 1 | 6 | Urban | Unknown | 2016-08-02 | TBD | TBD | TBD | TBD | N/A | N/A | #VALUE! | 2022-01-01 | N/A | TBD | TBD | Project not completed or closed | Project not completed or closed | Commercial | Unknown | TBD | TBD | TBD | 3605010.9 | N/A | TBD | N/A | [6 empty] | TBD | TBD |  |  | 0 |  |  |  | Project in progress |  |  | N/A |  |  |  |  | Yes | 1163000 | Butte County | N/A | 0 | PG&E does not grant approval for credit transfer transactions. Credit transfers are agreed upon between communities. | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | None | N/A | N/A | None | N/A | N/A
CHICO | WARNER ST DIST 18, CHICO | 74010864 | WARNER ST DIST 18 | 95926 | Unknown | Unknown | Unknown | WARNER ST, SACRAMENTO AVE & 1ST W ST | Unknown | Project met one or more Rule 20A criteria | Resolution# 75-16 & 16-143 | No | 11 | 4 | 3 | 1 | 6 | Urban | Unknown | 2016-08-02 | 2018-07-30 | TBD | TBD | TBD | N/A | N/A | 727 | 2019-12-30 | N/A | TBD | TBD | Project not completed or closed | Project not completed or closed | Commercial | Yes | TBD | TBD | TBD | 1547897.6 | N/A | TBD | N/A | [6 empty] | TBD | TBD |  |  | 0 |  |  |  | Project in progress |  |  | N/A |  |  |  |  | Yes | 1395000 | Butte County | N/A | 0 | PG&E does not grant approval for credit transfer transactions. Credit transfers are agreed upon between communities. | Unknown | Unknown | Unknown | Yes | Unknown | Yes | No | Unknown | None | N/A | N/A | None | N/A | N/A
OROVILLE | C:E PC R-20A TABLE MT,OROVILLE SUB ORDER | 30199109 | TABLE MT, OROVILLE | 95965 | 6007002500 | No | 18.82% | TABLE MT, OROVILLE | None | TBD | TBD | Yes | 11 | 4 | 3 | 1 | 6 | Unknown | No | TBD | 2001-05-16 | 2002-05-07 | 2002-11-15 | 2006 | 2007-03-24 | N/A | #VALUE! | N/A | N/A |  |  | 0.41 | 1689.6 | Unknown | Unknown |  |  |  | N/A | 396069 | 1.591 | 630132.3373 | [10 empty] | 0 |  |  |  | Unknown |  |  | 396069 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
OROVILLE | C:E PC R-20A TBL MT.ST LTS,SUBORDER*CANC | 30308489 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | 11 | 4 | 3 | 1 | 6 | N/A | N/A | TBD | TBD | TBD | TBD | N/A | N/A | N/A | #VALUE! | N/A | 2006-02-27 | N/A | N/A | Cancelled project | Cancelled project | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [6 empty] | N/A | N/A |  |  | 0 |  |  |  | N/A, project cancelled |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
OROVILLE | E PC R-20A MONTGOMERY STREET,OROVILLE | 30024946 | MONTGOMERY ST, OROVILLE | 95965 | 6007002800 | No | 28.09% | MONTGOMERY ST, OROVILLE | None | TBD | TBD | Yes | 11 | 4 | 3 | 1 | 6 | Unknown | No | TBD | 2000-12-07 | 2001-12-27 | 2004-01-28 | 2005 | 2007-03-24 | N/A | #VALUE! | N/A | N/A |  |  | 0.43 | 2059.2 | Unknown | Unknown |  |  |  | N/A | 646674.8411 | 1.7065 | 1103557.5399 | [10 empty] | 0 |  |  |  | Unknown |  |  | 646674.8411 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
OROVILLE, BUTTE COUNTY | MYERS ST, OROVILLE | 30938105 | MYERS ST | 95965 | 6007003001 | No | 19.97% | MYERS ST, ORO DAM BLVD & LINCOLN BLVD | None | Project met one or more Rule 20A criteria | Resolution# 11-128 | No | 11 | 4 | 3 | 1 | 6 | Unknown | No | 2011-11-22 | TBD | TBD | TBD | TBD | N/A | N/A | #VALUE! | 2022-07-01 | N/A |  |  | Project not completed or closed | Project not completed or closed | Unknown | Unknown | TBD | TBD | TBD | 6113460.03 | N/A | TBD | N/A | [6 empty] | TBD | TBD |  |  | 0 |  |  |  | Project in planning phase |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | Yes | No | City lacks funding for costs not covered by allocation | None | N/A | N/A | None | N/A | N/A
PARADISE | ALMOND ST PARADISE R20A | 74010581 | ALMOND ST | 95969 | Unknown | Unknown | Unknown | ALMOND ST, PEARSON RD & ELLIOTT RD | Unknown | Project met one or more Rule 20A criteria | Resolution# 16-76 | No | 11 | 4 | 3 | 1 | 6 | Urban | Unknown | 2016-11-07 | 2017-08-14 | 2019-12-06 | TBD | TBD | N/A | N/A | 280 | 2019-12-31 | N/A | 48 | 21 | Project not completed or closed | Project not completed or closed | Commercial | Yes | TBD | TBD | TBD | 4592557.68 | N/A | TBD | N/A | [6 empty] | TBD | TBD |  |  | 0 |  |  |  | Project in progress |  |  | N/A |  |  |  |  | Yes | 1400000 | Butte County | N/A | 0 | PG&E does not grant approval for credit transfer transactions. Credit transfers are agreed upon between communities. | Yes | Yes | Yes | No | No | No | No | Easement acquisitions. Future improvements caused design conflicts and re-design. Communication utility's delayed responses to design questions. Internal resource limitation. | None | N/A | N/A | None | N/A | N/A
PARADISE | CLARK RD & SKYWAY | 30269575 | CLARK RD & SKYWAY | 95969 | 6007001800 | No | 21.08% | CLARK RD & SKYWAY | Tier 3 | TBD | TBD | Yes | 11 | 4 | 3 | 1 | 6 | Unknown | No | 2002-04-09 | 2002-10-30 | 2005-10-11 | 2006-05-18 | 2007 | 2007-07-31 | N/A | 204 | N/A | N/A |  |  | 0.75 | 2217.6 | Unknown | Unknown |  |  |  | N/A | 753334.25 | 1.4306 | 1077702.8227 | [10 empty] | 0 |  |  |  | Unknown |  |  | 753334.25 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
Butte County Total | [41 empty] | 0
Calaveras County | [41 empty] | 0
CALAVERAS COUNTY | MTN. RANCH ROAD PH 1, CALAVERAS COUNTY | 30695567 | MOUNTAIN RANCH RD PH 1, UUD# 8 | 95249 | 6009000300 | No | 11.91% | MOUNTAIN RANCH RD, PARK DR & POPE ST | None | Project met one or more Rule 20A criteria | Resolution# 05-310 | No | 5 | 3 | 3 | 0 | 1 | Unknown | No | 2005-11-25 | TBD | TBD | TBD | TBD | N/A | N/A | #VALUE! | 2019-12-31 | N/A |  |  | Project not completed or closed | Project not completed or closed | Unknown | Unknown | TBD | TBD | TBD | 1075202.61 | N/A | TBD | N/A | [6 empty] | TBD | TBD |  |  | 0 |  |  |  | Project in planning phase |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | Yes | No | No | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
CALAVERAS COUNTY | MTN. RANCH ROAD PH 2, CALAVERAS COUNTY | 30695568 | MOUNTAIN RANCH RD PH 2, UUD# 8 | 95249 | Unknown | Unknown | Unknown | MOUNTAIN RANCH RD, E ST CHARLES ST & MARSHALL AVE | Unknown | Project met one or more Rule 20A criteria | Resolution# 05-310 | No | 5 | 3 | 3 | 0 | 1 | Suburban | Unknown | 2005-11-25 | 2012-09-05 | TBD | TBD | TBD | N/A | N/A | 2476 | 2022-12-31 | N/A | TBD | TBD | Project not completed or closed | Project not completed or closed | Residential | Yes | TBD | TBD | TBD | 1676435.75 | N/A | TBD | N/A | [6 empty] | TBD | TBD |  |  | 0 |  |  |  | Project in progress |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Yes | Yes | Yes | Yes | No | Yes | Yes | Cultural resource review and monitoring | TBD | TBD | TBD | TBD | TBD | TBD
CALAVERAS COUNTY | SAN ANDREAS RULE PH #1 RULE 20A | 30084561 | SAN ANDREAS PH 1 | 95249 | 6009000300 | No | 11.91% | SAN ANDREAS PH 1 | None | TBD | TBD | Yes | 5 | 3 | 3 | 0 | 1 | Unknown | No | TBD | 1999-06-21 | 2001-11-19 | 2002-11-27 | 2005 | 2007-03-24 | N/A | #VALUE! | N/A | N/A |  |  | 1.55 | 6494.4 | Unknown | Unknown |  |  |  | N/A | 1476404.69 | 1.7065 | 2519500.4102 | [10 empty] | 0 |  |  |  | Unknown |  |  | 1476404.69 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
CALAVERAS COUNTY | ST CHARLES (HWY 49) SAN ANDREAS | 30780266 | ST CHARLES ST, HWY 49, UUD# 9 | 95249 | 6009000300 | No | 11.91% | ST CHARLES ST, HWY 49 | None | Project met one or more Rule 20A criteria | Resolution# 99-100 | No | 5 | 3 | 3 | 0 | 1 | Unknown | No | 1999-04-12 | TBD | TBD | TBD | TBD | N/A | N/A | #VALUE! | 2020-09-01 | N/A |  |  | Project not completed or closed | Project not completed or closed | Unknown | Unknown | TBD | TBD | TBD | 4824588.36 | N/A | TBD | N/A | [6 empty] | TBD | TBD |  |  | 0 |  |  |  | Project in planning phase |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | Yes | Unknown | No | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
CALAVERAS COUNTY | STATE HWY 49 PH3 SAN ANDREAS R20A | 30695972 | N/A | N/A | 6009000300 | No | 11.91% | N/A | None | N/A | N/A | No | 5 | 3 | 3 | 0 | 1 | N/A | No | 2006-01-23 | TBD | TBD | TBD | N/A | N/A | N/A | #VALUE! | N/A | 2015-09-30 | N/A | N/A | Cancelled project | Cancelled project | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [6 empty] | N/A | N/A |  |  | 0 |  |  |  | N/A, project cancelled |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Calaveras County Total | [41 empty] | 0
Colusa County | [41 empty] | 0
COLUSA, COLUSA COUNTY | BRIDGE ST, COLUSA | 74008524 | BRUCE ST | 95932 | Unknown | Unknown | Unknown | BRIDGE ST, MARKET ST & TUTTLE LN | Unknown | Project met one or more Rule 20A criteria | Resolution# 16-34 & 16-036 | No | 0 | 0 | 0 | 0 | 0 | Urban | Unknown | TBD | 2016-08-01 | 2018-09-11 | 2019-09-30 | TBD | N/A | N/A | #VALUE! | 2019-10-31 | N/A | TBD | TBD | Project not completed or closed | Project not completed or closed | Commercial | Yes | TBD | TBD | TBD | 5896056.67 | N/A | TBD | N/A | [6 empty] | TBD | TBD |  |  | 0 |  |  |  | Unexpected field conditions |  |  | N/A |  |  |  |  | Yes | 2000000 | Butte County | N/A | 500000 | PG&E does not grant approval for credit transfer transactions. Credit transfers are agreed upon between communities. | Yes | Yes | Yes | No | Yes | Yes | No | Insufficient allocation. Project costs higher than expected. Complicated design due to future Caltrans road improvements. Encountered ground water during excavation and unmarked fiber optics. | None | N/A | N/A | None | N/A | N/A
Colusa County Total | [41 empty] | 0
Contra Costa County | [41 empty] | 0
ANTIOCH | *CANC* R1 EP JAMES DONLON BLVD-ANT 20A | 30482073 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | 29 | 7 | 6 | 1 | 20 | N/A | N/A | 1988-07-26 | TBD | TBD | TBD | N/A | 2011-03-16 | N/A | #VALUE! | N/A | 2010-10-28 | N/A | N/A | Cancelled project | Cancelled project | N/A | N/A | N/A | N/A | N/A | N/A | 72304 | 1.1878 | 85880.8112 | [6 empty] | N/A | N/A |  |  | 0 |  |  |  | N/A, project cancelled |  |  | 72304 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ANTIOCH | GEP-RULE 20A SOMERSVILLE RD-ANTIOCH | 30200879 | SOMERSVILLE RD, ANTIOCH | 94509 | 6013305000 | Yes | 19.91% | SOMERSVILLE RD, ANTIOCH | None | TBD | TBD | Yes | 29 | 7 | 6 | 1 | 20 | Urban | Yes | TBD | 2001-06-11 | 2002-03-23 | 2003-11-03 | 2005 | 2007-03-24 | N/A | #VALUE! | N/A | N/A | 22 | 1 | 1.08 | 3220.8 | Commercial | Yes |  |  |  | N/A | 1113831.62 | 1.7065 | 1900765.5845 | [6 empty] | 0 | N/A |  |  | 0 |  |  |  | Other |  |  | 1113831.62 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | No | Unknown | None | None | N/A | N/A | None | N/A | N/A
ANTIOCH | HILLCREST AVE | 30629323 | HILLCREST AVE, ANTIOCH | 94509 | 6013306003 | No | 16.78% | HILLCREST AVE, E 18TH AVE & UNION PACIFIC RAILROAD TRACKS | None | TBD | Resolution# 2005-117 | Yes | 29 | 7 | 6 | 1 | 20 | Unknown | No | 2005-10-25 | 2008-06-03 | 2010-05-11 | 2011-03-09 | 2013 | 2014-02-28 | N/A | 952 | N/A | N/A | 23 |  | 1.84 | 4118.4 | Unknown | Unknown |  |  |  | N/A | 2303558 | 1.1048 | 2544979.8923 | [10 empty] | 0 | [6 empty] | 2303558 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
ANTIOCH | SOMERSVILLE ROAD | 30699814 | SOMERSVILLE RD, UUD# 21 | 94509 | 6013307205 | No | 18.76% | SOMERSVILLE RD, MAHOGANY WY & DELTA FAIR BLVD | None | TBD | Resolution# 2008/108 | Yes | 29 | 7 | 6 | 1 | 20 | Unknown | No | 2008-12-16 | 2009-09-10 | 2011-03-14 | 2013-05-14 | 2014 | 2015-01-15 | N/A | 268 | N/A | N/A |  |  | 0.59 | 2587.2 | Unknown | Unknown |  |  |  | N/A | 1009094.21 | 1.0831 | 1092932.0633 | [10 empty] | 0 |  |  |  | Unknown |  |  | 1009094.21 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
BRENTWOOD | FAIRVIEW AVE, BRENTWOOD | 30959527 | FAIRVIEW AVE | 94513 | 6013303202 | No | 4.35% | FAIRVIEW AVE, SAN JOSE AVE, SAN CREEK CHANNEL | None | Project met one or more Rule 20A criteria | Ordinance# 903 | Yes | 29 | 7 | 6 | 1 | 20 | Urban | No | 2012-05-22 | 2015-09-28 | 2018-06-18 | 2018-11-02 | 2019 | 2019-07-31 | N/A | 1224 | N/A | N/A | TBD | TBD | 1.4165 | 7479.1895 | Residential | Yes | TBD | TBD | TBD | N/A | 1476839.79 | TBD | 1476839.79 | [6 empty] | TBD | TBD |  |  | 0 |  |  |  | Labor costs |  |  | 1476839.79 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | Yes | No | No | No | No | None | None | N/A | N/A | None | N/A | N/A
CLAYTON | C:ES RULE 20, CENTER ST, CLAYTON | 30123866 | CENTER ST, CLAYTON | 94517 | 6013355306 | No | 1.646% | CENTER ST, CLAYTON | None | TBD | TBD | Yes | 29 | 7 | 6 | 1 | 20 | Unknown | No | TBD | 2000-02-15 | 2000-11-17 | 2001-03-29 | 2004 | 2006 | N/A | #VALUE! | N/A | N/A |  |  | 0.59 | 2112 | Unknown | Unknown |  |  |  | N/A | 143887 | 1.8496 | 266130.5385 | [10 empty] | 0 |  |  |  | Unknown |  |  | 143887 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
CONCORD | EAST STREET R20A | 30134049 | EAST ST | 94520 | 6013328000 | No | 11.09% | EAST ST | None | TBD | TBD | Yes | 29 | 7 | 6 | 1 | 20 | Unknown | No | 2000-01-25 | 2000-10-27 | 2005-01-10 | 2006-08-08 | 2010 | 2010-08-26 | N/A | 276 | N/A | N/A |  |  | 0.84 | 4382.4 | Unknown | Unknown |  |  |  | N/A | 1850650 | 1.249 | 2311424.3974 | [10 empty] | 0 |  |  |  | Unknown |  |  | 1850650 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
CONCORD | MARKET ST, CONCORD | No Order | MARKET ST | 94520 | Unknown | Unknown | Unknown | MARKET ST, WILLOW PASS RD & 1945 MARKET ST | Unknown | Project met one or more Rule 20A criteria | Resolution# 10-30 | No | 29 | 7 | 6 | 1 | 20 | Unknown | Unknown | 2010-04-27 | TBD | TBD | TBD | TBD | N/A | N/A | #VALUE! | TBD | N/A |  |  | Project not completed or closed | Project not completed or closed | Unknown | Unknown | TBD | TBD | TBD | 1069180 | N/A | TBD | N/A | [6 empty] | TBD | TBD |  |  | 0 |  |  |  | Project in planning phase |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | No | No | Unknown | None | N/A | N/A | None | N/A | N/A
CONCORD | RULE 20A WILLOW PASS RD & LANDANA, CON | 30240959 | WILLOW PASS RD & LANDANA, CONCORD | 94519 | 6013332000 | No | 5.588% | WILLOW PASS RD & LANDANA, CONCORD | None | TBD | TBD | Yes | 29 | 7 | 6 | 1 | 20 | Urban | No | TBD | 2002-04-24 | 2002-10-18 | 2004-01-07 | 2005 | 2007-03-24 | N/A | #VALUE! | N/A | N/A | 10 | 5 | 0.25 | 1003.2 | Residential | Yes |  |  |  | N/A | 563911.57 | 1.7065 | 962321.1316 | [6 empty] | 5000 | 50% |  |  | 0 |  |  |  | Other |  |  | 563911.57 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | Unknown | No | Unknown | No | No | Unknown | None | None | N/A | N/A | None | N/A | N/A
CONCORD | THE ALAMEDA | 30411405 | THE ALAMEDA | 94519 | 6013331000 | No | 7.429% | THE ALAMEDA, CLAYTON RD & CORDOVA WY | None | TBD | TBD | Yes | 29 | 7 | 6 | 1 | 20 | Suburban | No | 2004-01-06 | 2008-05-30 | 2010-05-18 | 2012-10-04 | 2015 | 2015-10-06 | N/A | 1606 | N/A | N/A | 11 | 1 | 0.23 | 997.92 | Residential | Yes |  |  |  | N/A | 1467091.4 | 1.0677 | 1566447.4713 | [10 empty] | 0 | [6 empty] | 1467091.4 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Customer service conversion issues | None | N/A | N/A | None | N/A | N/A
CONCORD | WILLOW PASS RD, CONCORD | No Order | WILLOW PASS RD UUD PH 2 | 94519 | Unknown | Unknown | Unknown | WILLOW PASS RD, ASHDALE DR & LANDANA DR | Unknown | Project met one or more Rule 20A criteria | Resolution# 02-53 | No | 29 | 7 | 6 | 1 | 20 | Unknown | Unknown | 2002-09-03 | TBD | TBD | TBD | N/A | N/A | N/A | #VALUE! | TBD | N/A |  |  | Cancelled project | Cancelled project | Unknown | N/A | N/A | N/A | N/A | N/A | N/A | TBD | N/A | [6 empty] | TBD | TBD |  |  | 0 |  |  |  | N/A, project cancelled |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | No | No | Unknown | None | N/A | N/A | None | N/A | N/A
CONTRA COSTA COUNTY | BAILEY RD, CONTRA COSTA COUNTY | 74001485 | WILLOW PASS RD/BAILEY RD, BAY POINT AREA, UUD# 31 | 94565 | Unknown | Unknown | Unknown | BAILEY RD, CANAL RD & WILLOW PASS RD, WILLOW PASS RD, BAILEY RD & CRIVELLO AVE | Unknown | Project met one or more Rule 20A criteria | Resolution# 2013/351 | No | 29 | 7 | 6 | 1 | 20 | Urban | Unknown | 2013-09-10 | 2015-11-23 | 2019-09-27 | TBD | TBD | N/A | N/A | 804 | 2020-08-31 | N/A | TBD | TBD | Project not completed or closed | Project not completed or closed | Residential | Yes | TBD | TBD | TBD | 7000867.97 | N/A | TBD | N/A | [6 empty] | TBD | TBD |  |  | 0 |  |  |  | Project in progress |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | Yes | No | No | No | No | Revocable license agreement with EBMUD has challenged Joint trench design completion. Trenching depth for water and nitrogen crossings add duration to project schedule. | None | N/A | N/A | None | N/A | N/A
CONTRA COSTA COUNTY | PARKER R20A-PARKER AVENUE-RODEO | 30160625 | PARKER AVE, RODEO | 94572 | 6013358000 | Yes | 12.93% | PARKER AVE, RODEO | None | TBD | TBD | Yes | 29 | 7 | 6 | 1 | 20 | Unknown | Yes | 2000-03-14 | 2000-09-12 | 2004-03-08 | 2005-05-06 | 2010 | 2010-08-26 | N/A | 182 | N/A | N/A |  |  | 1.53 | 6336 | Unknown | Unknown |  |  |  | N/A | 2300334 | 1.249 | 2873070.6129 | [10 empty] | 0 |  |  |  | Unknown | 39610 | 2015-07-14 | 2300334 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
DANVILLE | CAMINO TASSAJARA 20A, DANVILLE | 30344715 | CAMINO TASSAJARA, DANVILLE | 94526 | 6013346204 | No | 0.632% | CAMINO TASSAJARA, DANVILLE | None | TBD | TBD | Yes | 29 | 7 | 6 | 1 | 20 | Unknown | No | 2003-10-08 | 2004-05-03 | 2006-01-17 | 2007-08-24 | 2010 | 2010-08-26 | N/A | 208 | N/A | N/A |  |  | 2.37 | 9979.2 | Unknown | Unknown |  |  |  | N/A | 2371997 | 1.249 | 2962576.2496 | [10 empty] | 0 |  |  |  | Unknown |  |  | 2371997 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
DANVILLE | CAMINO TASSAJARA PH2, DANVILLE | No Order | CAMINO TASSAJARA | 94506 | Unknown | Unknown | Unknown | CAMINO TASSAJARA, WOODSIDE DR & CROW CANYON RD | Unknown | Project met one or more Rule 20A criteria | Resolution# 97-2003 | No | 29 | 7 | 6 | 1 | 20 | Unknown | Unknown | 2003-10-08 | TBD | TBD | TBD | TBD | N/A | N/A | #VALUE! | TBD | N/A |  |  | Project not completed or closed | Project not completed or closed | Unknown | Unknown | TBD | TBD | TBD | 5370000 | N/A | TBD | N/A | [6 empty] | TBD | TBD |  |  | 0 |  |  |  | Project in planning phase |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | Yes | No | No | Insufficient allocation | None | N/A | N/A | None | N/A | N/A
EL CERRITO | FAIRMOUNT R 20A | 30154072 | FAIRMOUNT | 94530 | 6013389100 | No | 5.694% | FAIRMOUNT | None | TBD | TBD | Yes | 29 | 7 | 6 | 1 | 20 | Urban | No | 2000-06-19 | 2000-08-14 | 2003-06-23 | 2004-08-23 | 2006 | 2007-03-24 | N/A | 56 | N/A | N/A | 15 | 7 | 0.96 | 2217.6 | Commercial | Yes |  |  |  | N/A | 1817783.13 | 1.591 | 2892031.2683 | [6 empty] | 0 | N/A |  |  | 0 |  |  |  | Unexpected field conditions |  |  | 1817783.13 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Yes | No | No | Unknown | No | No | Unknown | None | None | N/A | N/A | None | N/A | N/A
EL CERRITO | CIVIC CENTER, EL CERRITO | No Order | CIVIC CENTER | 94530 | 6013387000 | No | 6.714% | MANILA AVE BTW RICHMOND ST & SAN PABLO AVE, KEARNEY ST BTW MANILA AVE & SCHMIDT LN | None | Project met one or more Rule 20A criteria | Resolution# 2019-47 | No | 29 | 7 | 6 | 1 | 20 | Rural | No | 2019-07-16 | TBD | TBD | TBD | TBD | N/A | N/A | #VALUE! | 0 | N/A | 0 | 0 | Project not completed or closed | Project not completed or closed | Residential | Unknown | TBD | TBD | TBD | 3266321.05 | N/A | TBD | N/A | [6 empty] | TBD | TBD | [6 empty] | Project in planning phase |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | Yes | No | No | Insufficient allocation | None | N/A | N/A | No | N/A | N/A
LAFAYETTE | LAFAYETTE CIR & FIESTA LN | 30636534 | LAFAYETTE CIR & FIESTA LN | 94549 | 6013350000 | No | 2.304% | LAFAYETTE CIR & FIESTA LN | None | TBD | TBD | Yes | 29 | 7 | 6 | 1 | 20 | Urban | No | 2008-05-15 | 2008-09-27 | 2008-12-18 | 2009-12-14 | 2011 | 2012-02-07 | N/A | 135 | N/A | N/A |  |  | 0.52 | 2059.2 | Commercial | Unknown |  |  |  | N/A | 1049391 | 1.1878 | 1246439.344 | [6 empty] | Unknown | TBD |  |  | 0 |  |  |  | Other |  |  | 1049391 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
MARTINEZ | MARINA VISTA | 30679737 | MARINA VISTA, UUD# 2005-1 | 94553 | 6013316000 | No | 13.15% | MARINA VISTA, BERRELLESA ST & FERRY ST | None | TBD | Resolution# 081-05 | Yes | 29 | 7 | 6 | 1 | 20 | Unknown | No | 2005-07-20 | 2009-03-16 | 2010-04-12 | 2011-12-07 | 2015 | 2015-10-06 | N/A | 1335 | N/A | N/A | 25 |  | 0.52 | 2376 | Unknown | Unknown |  |  |  | N/A | 1828333.89 | 1.0677 | 1952154.4456 | [10 empty] | 0 | [6 empty] | 1828333.89 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
MORAGA | MORAGA RD, MORAGA | 31160902 | MORAGA RD | 94556 | 6013352101 | No | 0.2865% | MORAGA RD, CORLISS DR & DEVIN DR | Part of project in or adjacent to Tier 2 | Project met one or more Rule 20A criteria | Resolution# 29-2015 | Yes | 29 | 7 | 6 | 1 | 20 | Suburban | No | 2015-03-11 | 2015-09-08 | 2016-08-02 | 2017-01-19 | 2017 | 2017-10-13 | N/A | 181 | N/A | N/A | 17 | 12 | 0.72 | 2640 | Residential | Yes |  |  |  | N/A | 1434611.76 | 1.048 | 1503536.1727 | [6 empty] | 32800 | 100% |  |  | 0 | [6 empty] | 1434611.76 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | Unknown | No | No | No | No | Easement acquisitions. Customer issues. | None | N/A | N/A | None | N/A | N/A
ORINDA | *CANC* MINER RD | 30519332 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | 29 | 7 | 6 | 1 | 20 | N/A | N/A | 2004-10-05 | TBD | TBD | TBD | N/A | 2015-10-06 | N/A | #VALUE! | N/A | 2015-08-05 | N/A | N/A | Cancelled project | Cancelled project | N/A | N/A | N/A | N/A | N/A | N/A | 122000 | 1.0677 | 130262.226 | [6 empty] | N/A | N/A |  |  | 0 |  |  |  | N/A, project cancelled |  |  | 122000 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PINOLE | PINOLE VALLEY RD, PINOLE | 31269303 | PINOLE VALLEY RD | 94564 | Unknown | Unknown | Unknown | PINOLE VALLEY RD, RAMONA & HELENA | Unknown | Project met one or more Rule 20A criteria | Resolution# 2016-59 | No | 29 | 7 | 6 | 1 | 20 | Suburban | Unknown | 2016-07-19 | 2017-02-13 | TBD | TBD | TBD | N/A | N/A | 209 | 2020-07-31 | N/A | TBD | TBD | Project not completed or closed | Project not completed or closed | Residential | Yes | TBD | TBD | TBD | 1403156.61 | N/A | TBD | N/A | [6 empty] | TBD | TBD |  |  | 0 |  |  |  | Project in progress |  |  | N/A |  |  |  |  | Yes | 631104 | Trinity County | N/A | 315552 | PG&E does not grant approval for credit transfer transactions. Credit transfers are agreed upon between communities. | Unknown | Yes | Unknown | Unknown | Unknown | Unknown | Unknown | Coordination issues between City and School District | TBD | TBD | TBD | TBD | TBD | TBD
PITTSBURG | WEST LELAND RD, PITTSBURG | 30754659 | WEST LELAND RD | 94565 | 6013313206 | No | 16.66% | WEST LELAND RD, RAILROAD AVE TO BURTON AVE | None | Project met one or more Rule 20A criteria | Resolution# 09-1133 | No | 29 | 7 | 6 | 1 | 20 | Urban | No | 2009-11-16 | 2013-08-13 | TBD | TBD | TBD | N/A | N/A | 1366 | 2020-06-18 | N/A | TBD | TBD | Project not completed or closed | Project not completed or closed | Residential | Yes | TBD | TBD | TBD | 2985874.52 | N/A | TBD | N/A | [6 empty] | TBD | TBD |  |  | 0 |  |  |  | Project in progress |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Yes | Yes | Yes | Yes | Yes | No | No | Easement acquisitions. Insufficient allocation. Scope reduction and full project re-design. | None | N/A | N/A | None | N/A | N/A
PLEASANT HILL | BUSKIRK AVE | 30769201 | BUSKIRK AVE | 94523 | 6013324001 | No | 11.7% | BUSKIRK AVE, MONUMENT BLVD & HOOKSTON AVE | None | TBD | Resolution# 11-07 | Yes | 29 | 7 | 6 | 1 | 20 | Urban | No | 2007-03-05 | 2012-09-12 | 2013-05-06 | 2013-10-15 | 2014 | 2015-01-15 | N/A | 2018 | N/A | N/A | 19 | 0 | 0.83 | 2534.4 | Commercial | Yes |  |  |  | N/A | 2115155.64 | 1.0831 | 2290887.6049 | [6 empty] | 0 | N/A |  |  | 0 |  |  |  | Other | 48000.24 | 2015-10-06 | 2115155.64 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | No | No | None | None | N/A | N/A | None | N/A | N/A
RICHMOND | MACDONALD AVE, RICHMOND | 30631393 | MACDONALD AVE | 94801 | 6013377000 | Yes | 21.03% | MACDONALD AVE, RICHMOND PKWY & 6TH ST | None | TBD | Resolution# USRB-2 | Yes | 29 | 7 | 6 | 1 | 20 | Urban | Yes | 2007-10-02 | 2008-06-09 | 2013-11-20 | 2014-04-02 | 2017 | 2017-04-14 | N/A | 251 | N/A | N/A | 19 | 37 | 1.03 | 6072 | Commercial | Yes |  |  |  | N/A | 4335386.23 | 1.048 | 4543675.3004 | [6 empty] | 0 | N/A |  |  | 0 |  |  |  | Unexpected field conditions |  |  | 4335386.23 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | No | No | None | None | N/A | N/A | None | N/A | N/A
SAN PABLO | EL PORTAL DR, SAN PABLO | 30837018 | EL PORTAL DR | 94806 | 6013367200 | No | 13.15% | EL PORTAL DR, MISSION BELL DR TO ROLLINGWOOD DR | None | Project met one or more Rule 20A criteria | Resolution# 2010-110 | Yes | 29 | 7 | 6 | 1 | 20 | Urban | No | 2010-09-20 | 2014-02-03 | 2017-08-21 | 2017-10-12 | 2018 | 2018-07-17 | N/A | 1232 | N/A | N/A | 10 | 0 | 1.0913 | 5762.2168 | Commercial | Yes |  |  |  | N/A | 1251314.97 | TBD | 1251314.97 | [6 empty] | 100000 | 100% |  |  | 0 |  |  |  | Unexpected field conditions |  |  | 1251314.97 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | No | No | Easement acquisitions | None | N/A | N/A | None | N/A | N/A
SAN PABLO | SAN PABLO DAM R20A | 30243988 | SAN PABLO DAM | 94806 | 6013369002 | No | 12.24% | SAN PABLO DAM | None | TBD | TBD | Yes | 29 | 7 | 6 | 1 | 20 | Unknown | No | TBD | 2002-04-02 | 2002-10-10 | 2004-03-08 | 2006 | 2007-03-24 | N/A | #VALUE! | N/A | N/A |  |  | 0.81 | 2164.8 | Unknown | Unknown |  |  |  | N/A | 915637.91 | 1.591 | 1456748.8401 | [10 empty] | 0 |  |  |  | Unknown |  |  | 915637.91 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
SAN RAMON | SAN RAMON VALLEY BLVD | 30170978 | SAN RAMON VALLEY BLVD | 94583 | 6013345115 | No | 2.302% | SAN RAMON VALLEY BLVD | None | TBD | TBD | Yes | 29 | 7 | 6 | 1 | 20 | Unknown | No | 2000-05-23 | 2000-12-18 | 2004-06-28 | 2005-09-19 | 2007 | 2007-07-31 | N/A | 209 | N/A | N/A |  |  | 0.65 | 3115.2 | Unknown | Unknown |  |  |  | N/A | 1034452.89 | 1.4306 | 1479864.7474 | [10 empty] | 0 |  |  |  | Unknown |  |  | 1034452.89 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
WALNUT CREEK | BONANZA ST WALNUT CREEK R20A | 74014381 | BONANZA ST, UUD# 15-1 | 94596 | Unknown | Unknown | Unknown | BONANZA ST, CALIFORNIA BLVD & MT DIABLO BLVD | Unknown | Project met one or more Rule 20A criteria | Resolution# 16-23 | No | 29 | 7 | 6 | 1 | 20 | Suburban | Unknown | 2016-04-05 | 2018-09-04 | TBD | TBD | TBD | N/A | N/A | 882 | 2021-01-21 | N/A | TBD | TBD | Project not completed or closed | Project not completed or closed | Commercial | Yes | TBD | TBD | TBD | 1642210.36 | N/A | TBD | N/A | [6 empty] | TBD | TBD |  |  | 0 |  |  |  | Project in progress |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | TBD | TBD | TBD | TBD | TBD | TBD
WALNUT CREEK | RULE 20A WALNUT CREEK, N MAIN | 30069379 | WALNUT CREEK, N MAIN | 94596 | 6013339002 | No | 3.463% | WALNUT CREEK, N MAIN | None | TBD | TBD | Yes | 29 | 7 | 6 | 1 | 20 | Unknown | No | TBD | 1999-05-11 | 1999-08-09 | 2002-12-11 | 2005 | 2007-03-24 | N/A | #VALUE! | N/A | N/A |  |  | 2.35 | 6441.6 | Unknown | Unknown |  |  |  | N/A | 4018496.78 | 1.7065 | 6857607.7781 | [10 empty] | 0 |  |  |  | Unknown |  |  | 4018496.78 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
Contra Costa County Total | [41 empty] | 0
El Dorado County | [41 empty] | 0
EL DORADO COUNTY | C:EPC GREEN VALLEY ROAD,EL DORADO WKR | 30025981 | GREEN VALLEY RD, EL DORADO | 95762 | 6017031700 | No | 1.322% | GREEN VALLEY RD, EL DORADO | None | TBD | TBD | Yes | 6 | 4 | 4 | 0 | 2 | Unknown | No | TBD | 2000-11-09 | 2002-03-28 | 2004-08-23 | 2006 | 2007-03-24 | N/A | #VALUE! | N/A | N/A |  |  | 1.49 | 6230.4 | Unknown | Unknown |  |  |  | N/A | 1147767.13 | 1.591 | 1826058.5512 | [10 empty] | 0 |  |  |  | Unknown |  |  | 1147767.13 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
EL DORADO COUNTY | DIAMOND SPRINGS 1C, EL DORADO CNTY R20A | 74013925 | DIAMOND SPRINGS 1C | 95619 | Unknown | Unknown | Unknown | MISSOURI FLAT RD, EL DORADO TRAIL & OLD DEPOT RD | Unknown | Project met one or more Rule 20A criteria | Resolution# 008-2014 | No | 6 | 4 | 4 | 0 | 2 | Rural | Unknown | 2014-02-04 | 2017-08-11 | TBD | TBD | TBD | N/A | N/A | 1284 | 2019-12-31 | N/A | TBD | TBD | Project not completed or closed | Project not completed or closed | Commercial | Yes | TBD | TBD | TBD | 1596648.66 | N/A | TBD | N/A | [6 empty] | TBD | TBD |  |  | 0 |  |  |  | Project in progress |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | Unknown | Yes | No | Unknown | Unknown | Unknown | TBD | TBD | TBD | TBD | TBD | TBD
EL DORADO COUNTY | DIAMOND SPRINGS PH1, EL DORADO COUNTY | 31066255 | DIAMOND SPRINGS PH 1 | 95619 | Unknown | Unknown | Unknown | HWY 49, BRADLEY DR & PLEASANT VALLEY RD | Unknown | Project met one or more Rule 20A criteria | Resolution# 008-2014 | No | 6 | 4 | 4 | 0 | 2 | Rural | Unknown | 2014-02-04 | 2016-06-29 | TBD | TBD | TBD | N/A | N/A | 876 | 2020-02-07 | N/A | TBD | TBD | Project not completed or closed | Project not completed or closed | Residential | Yes | TBD | TBD | TBD | 4004400.44 | N/A | TBD | N/A | [6 empty] | TBD | TBD |  |  | 0 |  |  |  | Project in progress |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | Unknown | Yes | No | Yes | Unknown | Construction dependent on County road improvement project to set new grade. County moved their project to 2019 Construction. | TBD | TBD | TBD | TBD | TBD | TBD
EL DORADO COUNTY | GREEN VALLEY RD, EL DORADO COUNTY | 74010582 | GREEN VALLEY RD | 95667 | Unknown | Unknown | Unknown | GREEN VALLEY RD, POODLE LN & MORTARA CIR | Unknown | Project met one or more Rule 20A criteria | Resolution# 205-2016 | No | 6 | 4 | 4 | 0 | 2 | Rural | Unknown | 2016-12-13 | 2017-05-15 | TBD | TBD | TBD | N/A | N/A | 153 | 2019-09-30 | N/A | TBD | TBD | Project not completed or closed | Project not completed or closed | Residential | Unknown | TBD | TBD | TBD | 2062356.41 | N/A | TBD | N/A | [6 empty] | TBD | TBD |  |  | 0 |  |  |  | Project in progress |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | Yes | Unknown | No | Unknown | Unknown | Unknown | TBD | TBD | TBD | TBD | TBD | TBD
EL DORADO COUNTY | MISSOURI FLAT RD EL DORADO CNTY R20A | 35047931 | MISSOURI FLAT RD WITHIN DIAMOND SPRINGS & EL DORADO UUD | 95667 | 6017031502 | No | 13.15% | MISSOURI FLAT RD BETWEEN PLEASANT VALLEY RD & CHINA GARDEN RD | None | Project met one or more Rule 20A criteria | Resolution# 081-2018 | No | 6 | 4 | 4 | 0 | 2 | Rural | No | 2018-05-08 | 2018-07-17 | TBD | TBD | TBD | N/A | N/A | 70 | 2019-12-31 | N/A | 0 | 0 | Project not completed or closed | Project not completed or closed | Residential | Unknown | TBD | TBD | TBD | 4055226.41 | N/A | TBD | N/A | [6 empty] | TBD | TBD | [6 empty] | Project in planning phase |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | Yes | No | No | Insufficient allocation | None | N/A | N/A | No | N/A | N/A
PLACERVILLE | MAIN ST/PLACERVILLE DR | 30547671 | MAIN ST & PLACERVILLE DR | 95667 | 6017031200 | No | 8.627% | MAIN ST & PLACERVILLE DR | Tier 2 | TBD | TBD | Yes | 6 | 4 | 4 | 0 | 2 | Unknown | No | 2003-10-25 | 2007-01-16 | 2008-03-26 | 2008-10-18 | 2014 | 2015-01-15 | N/A | 1179 | N/A | N/A |  |  | 0.84 | 3009.6 | Unknown | Unknown |  |  |  | N/A | 1993373.79 | 1.0831 | 2158987.8404 | [10 empty] | 0 |  |  |  | Unknown |  |  | 1993373.79 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
El Dorado County Total | [41 empty] | 0
Fresno County | [41 empty] | 0
CLOVIS | FIFTH STREET | 30403106 | FIFTH ST | 93612 | 6019005701 | No | 15.96% | FIFTH ST | None | TBD | TBD | Yes | 47 | 9 | 9 | 0 | 31 | Urban | No | 2004-02-17 | 2005-02-15 | 2006-06-07 | 2007-01-08 | 2009 | 2010-03-16 | N/A | 364 | N/A | N/A | 18 | 4 | 0.89 | 3220.8 | Commercial | Yes |  |  |  | N/A | 1123323.65 | 1.2297 | 1381327.1512 | [6 empty] | 8209 | Unknown |  |  | 0 |  |  |  | Labor and material costs |  |  | 1123323.65 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | None | None | N/A | N/A | None | N/A | N/A
CLOVIS | VILLA AVE. (BULLARD2HERNDON) | 30421018 | VILLA AVE (BULLARD & HERNDON) | 93612 | 6019005602 | Yes | 24.13% | VILLA AVE (BULLARD & HERNDON) | None | TBD | TBD | Yes | 47 | 9 | 9 | 0 | 31 | Urban | Yes | 2004-02-17 | 2005-07-15 | 2006-10-03 | 2007-11-12 | 2009 | 2010-03-16 | N/A | 514 | N/A | N/A | 23 | 10 | 1.01 | 2904 | Residential | Yes |  |  |  | N/A | 2378715.45 | 1.2297 | 2925055.6917 | [6 empty] | Unknown | Unknown |  |  | 0 |  |  |  | Labor, material, and contract costs |  |  | 2378715.45 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | None | None | N/A | N/A | None | N/A | N/A
CLOVIS | BULLARD AVE, CLOVIS | No Order | UUD NO. 8 | 93612 | 6019005602 | Unknown | 24.14% | BULLARD AVE BETWEEN MINNEWAWA AVE & WOODWORTH AVE | None | Project met one or more Rule 20A criteria | Resolutions 19-92 & 19-127 | No | 47 | 9 | 9 | 0 | 31 | Rural | Unknown | 2019-07-01 | TBD | TBD | TBD | TBD | N/A | N/A | #VALUE! | 0 | N/A | 0 | 0 | Project not completed or closed | Project not completed or closed | Residential | Unknown | TBD | TBD | TBD | 1571431.98 | N/A | TBD | N/A | [6 empty] | TBD | TBD | [6 empty] | Project in planning phase |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | Yes | No | No | Insufficient allocation | None | N/A | N/A | No | N/A | N/A
COALINGA | ELM AVE, COALINGA | 74013924 | ELM AVE | 93210 | 6019008000 | No | 13.95% | ELM AVE, CHERRY LN TO LOS GATOS CREEK BRIDGE | None | Project met one or more Rule 20A criteria | Resolution# 3451 | No | 47 | 9 | 9 | 0 | 31 | Unknown | No | 2011-07-02 | TBD | TBD | TBD | TBD | N/A | N/A | #VALUE! | 2019-12-01 | N/A |  |  | Project not completed or closed | Project not completed or closed | Unknown | Unknown | TBD | TBD | TBD | 1366846.11 | N/A | TBD | N/A | [6 empty] | TBD | TBD |  |  | 0 |  |  |  | Project in planning phase |  |  | N/A |  |  |  |  | Yes | 675000 | Fresno County | N/A | 0 | PG&E does not grant approval for credit transfer transactions. Credit transfers are agreed upon between communities. | No | Yes | No | No | Yes | No | No | Insufficient allocation | None | N/A | N/A | None | N/A | N/A
FIREBAUGH | 13TH ST | 30675529 | 13TH ST | 93622 | 6019008401 | Yes | 19.82% | 13TH ST, SAN JOAQUIN RIVER BRIDGE & N ST | None | TBD | Resolution# 08-28 | Yes | 47 | 9 | 9 | 0 | 31 | Suburban | Yes | 2008-08-04 | 2011-07-19 | 2013-04-04 | 2013-11-17 | 2015 | 2015-07-14 | N/A | 1079 | N/A | N/A | 16 | 4 | 0.98 | 3537.6 | Residential | Yes |  |  |  | N/A | 2423475.29 | 1.0677 | 2587600.7041 | [6 empty] | 0 | N/A |  |  | 0 |  |  |  | Labor costs |  |  | 2423475.29 |  |  |  |  | Yes | 750000 | Fresno County | 30.95% | 0 | PG&E does not grant approval for credit transfer transactions. Credit transfers are agreed upon between communities. | Yes | No | Yes | Yes | Yes | Yes | No | Insufficient allocation | None | N/A | N/A | None | N/A | N/A
FOWLER | EP MERCED & 10TH STS. RULE 20A, FOWLER | 30304212 | MERCED ST & 10TH ST, FOWLER | 93625 | 6019001700 | Yes | 12.86% | MERCED ST & 10TH ST, FOWLER | None | TBD | TBD | Yes | 47 | 9 | 9 | 0 | 31 | Urban | Yes | TBD | 2003-08-29 | 2005-12-08 | 2004-07-12 | 2006 | 2007-03-24 | N/A | #VALUE! | N/A | N/A |  | 4 | 0.49 | 1795.2 | Residential | No |  |  |  | N/A | 455361 | 1.591 | 724463.8971 | [6 empty] | Unknown | Unknown |  |  | 0 |  |  |  | Other |  |  | 455361 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | None | None | N/A | N/A | None | N/A | N/A
FOWLER | FOWLER LIBRARY, 7TH ST | 30676929 | FOWLER LIBRARY, 7TH ST | 93625 | 6019001600 | Yes | 15.26% | FOWLER LIBRARY, 7TH ST, MERCED ST & VINE ST | None | TBD | Resolution# 2108 | Yes | 47 | 9 | 9 | 0 | 31 | Unknown | Yes | 2007-05-22 | 2011-11-17 | 2013-03-23 | 2013-03-20 | 2014 | 2015-01-15 | N/A | 1640 | N/A | N/A |  |  | 0.68 | 2270.4 | Unknown | Unknown |  |  |  | N/A | 879266.34 | 1.0831 | 952317.7971 | [10 empty] | 0 |  |  |  | Unknown |  |  | 879266.34 |  |  |  |  | Yes | 450000 | Fresno County | 51.18% | Unknown | PG&E does not grant approval for credit transfer transactions. Credit transfers are agreed upon between communities. | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
FRESNO | *CANC* ORANGE AVE | 30676935 | N/A | N/A | 6019001500 | Yes | 15.32% | N/A | None | N/A | N/A | No | 47 | 9 | 9 | 0 | 31 | N/A | Yes | 2006-10-24 | TBD | TBD | TBD | N/A | 2014-02-28 | N/A | #VALUE! | N/A | 2013-11-04 | N/A | N/A | Cancelled project | Cancelled project | N/A | N/A | N/A | N/A | N/A | N/A | 4036.46 | 1.0831 | 4371.8183 | [6 empty] | N/A | N/A |  |  | 0 |  |  |  | N/A, project cancelled |  |  | 4036.46 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FRESNO | BELMONT AVE [FWY 41 TO CHESTNUT], FRESNO | 30676931 | BELMONT AVE [FWY 41 TO CHESTNUT], FRESNO | 93702 | 6019002800 | Yes | 18.58% | BELMONT AVE [FWY 41 TO CHESTNUT], FRESNO | None | Project met one or more Rule 20A criteria | TBD | Yes | 47 | 9 | 9 | 0 | 31 | Urban | Yes | 2007-06-26 | 2014-10-21 | 2016-07-12 | 2017-05-16 | 2018 | 2019-02-19 | N/A | 2674 | N/A | N/A | 61 | 13 | 3.7981 | 20053.9376 | Commercial | Yes |  |  |  | N/A | 6542609.88 | TBD | 6542609.88 | [6 empty] | 0 | N/A |  |  | 0 |  |  |  | Restrictive work conditions |  |  | 6542609.88 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Yes | Yes | Yes | Yes | No | No | No | Extreme amount of traffic at project location. Easement acquisitions. Contract costs exceeded job estimate. | None | N/A | N/A | None | N/A | N/A
FRESNO | BLACKSTONE AVE & ABBY ST, FRESNO | 74009342 | BLACKSTONE AVE & ABBY ST | 93721 | 6019003500 | Yes | 19.56% | BLACKSTONE AVE & ABBY ST, SHEILDS TO BELMONT & BELMONT TO HEDGES | None | Project met one or more Rule 20A criteria | Resolution# 2007-318 | No | 47 | 9 | 9 | 0 | 31 | Urban | Yes | 2007-09-25 | 2017-02-01 | TBD | TBD | TBD | N/A | N/A | 3417 | 2020-07-15 | N/A | TBD | TBD | Project not completed or closed | Project not completed or closed | Commercial | Yes | TBD | TBD | TBD | 12889755.5 | N/A | TBD | N/A | [6 empty] | TBD | TBD |  |  | 0 |  |  |  | Project in progress |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
FRESNO | E. NEES & N. MAPLE AVE | 31106363 | E NEES AVE & N MAPLE AVE | 93721 | 6019005507 | No | 8.252% | E NEES AVE & N MAPLE AVE, HAYSTON AVE & N MAPLE AVE | None | Project met one or more Rule 20A criteria | Resolution# 2014-116 | Yes | 47 | 9 | 9 | 0 | 31 | Urban | No | 2014-07-17 | 2014-10-13 | 2015-07-28 | 2016-01-26 | 2016 | 2016-07-20 | N/A | 88 | N/A | N/A | 8 | 0 | 0.26 | 1214.4 | Residential | Yes |  |  |  | N/A | 785014.09 | 1.0668 | 837478.1136 | [6 empty] | 0 | N/A |  |  | 0 | [6 empty] | 785014.09 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Yes | No | Yes | No | No | No | No | AT&T delayed removal of their facility almost a year. | None | N/A | N/A | None | N/A | N/A
FRESNO | EP ELM AVE. (JENSEN - NORTH) RULE 20A | 30303447 | ELM AVE (JENSEN - NORTH) | 93706 | 6019001800 | Yes | 13.24% | ELM AVE (JENSEN - NORTH) | None | TBD | TBD | Yes | 47 | 9 | 9 | 0 | 31 | Suburban | Yes | 2003-02-04 | 2003-03-20 | 2003-09-22 | 2005-03-17 | 2006 | 2007-03-24 | N/A | 44 | N/A | N/A |  | 7 | 2.39 | 6811.2 | Residential | No |  |  |  | N/A | 1757772.85 | 1.591 | 2796556.9495 | [6 empty] | Unknown | Unknown |  |  | 0 |  |  |  | Other |  |  | 1757772.85 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | None | None | N/A | N/A | None | N/A | N/A
FRESNO | EP GRANITE PARK RULE 20A (BARTON AVE.) | 30321943 | GRANITE PARK (BARTON AVE) | 93726 | 6019005202 | Yes | 20.61% | GRANITE PARK (BARTON AVE) | None | TBD | TBD | Yes | 47 | 9 | 9 | 0 | 31 | Urban | Yes | 2003-03-11 | 2003-08-12 | 2003-10-08 | 2003-12-04 | 2005 | 2007-03-24 | N/A | 154 | N/A | N/A | 9 | 1 | 0.41 | 1900.8 | Residential | No |  |  |  | N/A | 233285.445 | 1.7065 | 398104.1096 | [6 empty] | Unknown | Unknown |  |  | 0 |  |  |  | Other |  |  | 233285.445 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | None | None | N/A | N/A | None | N/A | N/A
FRESNO | EP HWY 180 R20A-TEMPERANCE-K.CYN TO TULA | 30313838 | HWY 180, TEMPERANCE-K CYN TO TULA | 93727 | 6019001412 | Yes | 11.04% | HWY 180, TEMPERANCE-K CYN TO TULA | None | TBD | TBD | Yes | 47 | 9 | 9 | 0 | 31 | Rural | Yes | TBD | TBD | TBD | 2005-05-03 | 2006 | 2007-03-24 | N/A | #VALUE! | N/A | N/A |  |  | 0.79 | 2904 | Agricultural | No |  |  |  | N/A | 663412.21 | 1.591 | 1055466.3114 | [6 empty] | Unknown | Unknown |  |  | 0 |  |  |  | Other |  |  | 663412.21 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | None | None | N/A | N/A | None | N/A | N/A
FRESNO | EP KNGS CNYN PH 3 20A (MAPLE-WILLW) | 30126926 | KNGS CNYN PH 3 (MAPLE-WILLW) | 93702 | 6019001301 | Yes | 18.79% | KNGS CNYN PH 3 (MAPLE-WILLW) | None | TBD | TBD | Yes | 47 | 9 | 9 | 0 | 31 | Urban | Yes | 1997-10-28 | 2000-07-05 | 2007-07-25 | 2008-11-24 | 2010 | 2010-08-26 | N/A | 981 | N/A | N/A | 27 | 3 | 2.31 | 6758.4 | Commercial | Yes |  |  |  | N/A | 3403646 | 1.249 | 4251084.9725 | [6 empty] | Unknown | Unknown |  |  | 0 |  |  |  | Labor, material, overhead, and AFUDC costs |  |  | 3403646 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | None | None | N/A | N/A | None | N/A | N/A
FRESNO | EP SHAW & MARKS PH III RULE 20A | 30220640 | SHAW & MARKS PH 3 | 93705 | 6019004701 | Yes | 20.1% | SHAW & MARKS PH 3 | None | TBD | TBD | Yes | 47 | 9 | 9 | 0 | 31 | Urban | Yes | TBD | 2001-12-06 | 2002-04-26 | 2003-03-18 | 2005 | 2007-03-24 | N/A | #VALUE! | N/A | N/A | 22 | 0 | 0.71 | 3115.2 | Commercial | No |  |  |  | N/A | 989810.2419 | 1.7065 | 1689121.7749 | [6 empty] | Unknown | Unknown |  |  | 0 |  |  |  | Other |  |  | 989810.2419 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | None | None | N/A | N/A | None | N/A | N/A
FRESNO | FRIANT ROAD SHOO FLY (RULE 20A) | 30472856 | FRIANT ROAD SHOO FLY | 93730 | 6019005503 | No | 5.994% | FRIANT ROAD SHOO FLY | None | TBD | TBD | Yes | 47 | 9 | 9 | 0 | 31 | Rural | No | 1998-08-25 | 2005-11-29 | 2006-10-10 | 2007-02-12 | 2010 | 2010-08-26 | N/A | 2653 | N/A | N/A | 41 |  | 0.4 | 1953.6 | Agricultural | Yes |  |  |  | N/A | 492448 | 1.249 | 615057.5861 | [6 empty] | Unknown | Unknown |  |  | 0 |  |  |  | Overhead and material costs |  |  | 492448 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | None | None | N/A | N/A | None | N/A | N/A
FRESNO | PEACH AVE - LANE | 30225680 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | 47 | 9 | 9 | 0 | 31 | N/A | N/A | 2001-09-18 | TBD | TBD | TBD | N/A | 2007-07-31 | N/A | #VALUE! | N/A | 2007-02-26 | N/A | N/A | Cancelled project | Cancelled project | N/A | N/A | N/A | N/A | N/A | N/A | 45352.65 | 1.4306 | 64880.4683 | [6 empty] | N/A | N/A |  |  | 0 |  |  |  | N/A, project cancelled |  |  | 45352.65 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FRESNO | PEACH AVE [KINGS CANYON TO BELMONT] | 30676934 | PEACH AVE | 93727 | 6019002904 | Yes | 16.85% | PEACH AVE, KINGS CANYON & BELMONT | None | TBD | Resolution# FRE-77 | Yes | 47 | 9 | 9 | 0 | 31 | Unknown | Yes | 2001-09-18 | 2009-11-09 | 2011-03-09 | 2012-11-15 | 2016 | 2016-07-20 | N/A | 2974 | N/A | N/A |  |  | 1.89 | 9187.2 | Unknown | Unknown |  |  |  | N/A | 5685407.53 | 1.0668 | 6065374.4103 | [10 empty] | 0 |  |  |  | Unknown |  |  | 5685407.53 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
FRESNO | PEACH AVE 20A - LYELL | 30252291 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | 47 | 9 | 9 | 0 | 31 | N/A | N/A | 2001-09-18 | TBD | TBD | TBD | N/A | 2007-07-31 | N/A | #VALUE! | N/A | 2007-02-26 | N/A | N/A | Cancelled project | Cancelled project | N/A | N/A | N/A | N/A | N/A | N/A | 857.61 | 1.4306 | 1226.8773 | [6 empty] | N/A | N/A |  |  | 0 |  |  |  | N/A, project cancelled |  |  | 857.61 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FRESNO | SHAW & CEDAR AVENUES | 30354147 | SHAW AVE & CEDAR AVE | 93710 | 6019005302 | No | 22.81% | SHAW AVE & CEDAR AVE | None | TBD | TBD | Yes | 47 | 9 | 9 | 0 | 31 | Urban | No | TBD | TBD | TBD | 2006-03-31 | 2007 | 2007-07-31 | N/A | #VALUE! | N/A | N/A |  |  | 0.53 | 2270.4 | Commercial | No |  |  |  | N/A | 924176.55 | 1.4306 | 1322105.9266 | [6 empty] | Unknown | Unknown |  |  | 0 |  |  |  | Other |  |  | 924176.55 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | None | None | N/A | N/A | None | N/A | N/A
FRESNO | VENTURA AVE, FRESNO | 30676932 | VENTURA AVE, UUD# FRE-85 | 93702 | 6019000600 | Yes | 21.85% | VENTURA AVE, M ST & STATE RT 99 | None | Project met one or more Rule 20A criteria | Resolution# 2007-225 | No | 47 | 9 | 9 | 0 | 31 | Unknown | Yes | 2007-03-27 | TBD | TBD | TBD | TBD | N/A | N/A | #VALUE! | 2020-05-01 | N/A |  |  | Project not completed or closed | Project not completed or closed | Unknown | Unknown | TBD | TBD | TBD | 2248023.93 | N/A | TBD | N/A | [6 empty] | TBD | TBD |  |  | 0 |  |  |  | Project in planning phase |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | Yes | No | No | No | No | No | Unknown | None | N/A | N/A | None | N/A | N/A
FRESNO | WILLOW AVE S/O NEES | 30676933 | WILLOW AVE & NEES, UUD# 68 | 93611 | 6019005509 | No | 10.94% | WILLOW AVE & NEES | None | TBD | Resolution# 2008-69 | Yes | 47 | 9 | 9 | 0 | 31 | Urban | No | 2008-04-01 | 2013-02-11 | 2014-01-13 | 2014-04-04 | 2016 | 2016-04-09 | N/A | 1777 | N/A | N/A | 19 | 6 | 0.81 | 3168 | Residential | Yes |  |  |  | N/A | 1255533 | 1.0668 | 1339442.7206 | [6 empty] | Unknown | Unknown |  |  | 0 |  |  |  | Contract costs |  |  | 1255533 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | No | No | None | None | N/A | N/A | None | N/A | N/A
FRESNO | WILLOW AVE, PH 2 | 30679601 | WILLOW AVE, PH 2 | 93730 | 6019005505 | No | 5.761% | WILLOW AVE, YEARGIN & BEHYMER | None | TBD | Resolution# 2006-426 | Yes | 47 | 9 | 9 | 0 | 31 | Urban | No | 2006-09-19 | 2009-05-19 | 2010-01-05 | 2010-09-27 | 2013 | 2014-02-28 | N/A | 973 | N/A | N/A | 26 | 3 | 1.58 | 6811.2 | Residential | Yes |  |  |  | N/A | 1558816 | 1.1048 | 1722186.0165 | [6 empty] | 0 | N/A |  |  | 0 |  |  |  | Labor, material, overhead, and AFUDC costs |  |  | 1558816 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | None | None | N/A | N/A | None | N/A | N/A
FRESNO | WILLOW R20A(TEAGUE TO 660' N/O SHEPH | 30526916 | WILLOW, TEAGUE & SHEPH | 93720 | 6019005508 | No | 5.901% | WILLOW, TEAGUE & SHEPH | None | TBD | TBD | Yes | 47 | 9 | 9 | 0 | 31 | Urban | No | 2006-09-19 | 2007-01-10 | 2008-01-30 | 2009-02-27 | 2010 | 2010-08-26 | N/A | 113 | N/A | N/A | 24 | 3 | 1.5 | 6652.8 | Residential | Yes |  |  |  | N/A | 1140852 | 1.249 | 1424901.06 | [6 empty] | Unknown | Unknown |  |  | 0 |  |  |  | Labor and material costs |  |  | 1140852 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | None | None | N/A | N/A | None | N/A | N/A
FRESNO | CHURCH AVE, FRESNO | 35067381 | FRE-96 | 93706 | 6019000901 | Yes | 17.45% | CHURCH AVE BETWEEN WALNUT & MARTIN LUTHER KING BLVD, WALNUT AVE BETWEEN CHURCH AVE & GROVE AVE AND MARTIN LUTHER KING BLVD BETWEEN CHURCH AVE & GROVE AVE | None | Project met one or more Rule 20A criteria | Resolution# 2018-201 | No | 47 | 9 | 9 | 0 | 31 | Rural | Yes | 2018-08-06 | TBD | TBD | TBD | TBD | N/A | N/A | #VALUE! | 2020-11-29 | N/A | 0 | 0 | Project not completed or closed | Project not completed or closed | Residential | Unknown | TBD | TBD | TBD | 3557802.45 | N/A | TBD | N/A | [6 empty] | TBD | TBD | [6 empty] | Project in planning phase |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | Yes | No | No | Insufficient allocation | None | N/A | N/A | No | N/A | N/A
FRESNO COUNTY | *CANC* WILLIAMS ST, TRANQUILITY | 30675531 | N/A | N/A | 6019008200 | Yes | 16.7% | N/A | None | N/A | N/A | No | 47 | 9 | 9 | 0 | 31 | N/A | Yes | 2008-08-26 | TBD | TBD | TBD | N/A | 2014-02-28 | N/A | #VALUE! | N/A | 2013-11-15 | N/A | N/A | Cancelled project | Cancelled project | N/A | N/A | N/A | N/A | N/A | N/A | 1693.33 | 1.0831 | 1834.0157 | [6 empty] | N/A | N/A |  |  | 0 |  |  |  | N/A, project cancelled |  |  | 1693.33 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FRESNO COUNTY | ACADEMY AVE 20A JEFFERSON AVE, SANGER | 30566254 | ACADEMY AVE, JEFFERSON AVE, SANGER | 93616 | 6019006900 | Yes | 14.26% | ACADEMY AVE, JEFFERSON AVE, SANGER | None | TBD | TBD | Yes | 47 | 9 | 9 | 0 | 31 | Urban | Yes | 2005-08-02 | 2008-08-02 | 2008-12-23 | 2009-07-29 | 2010 | 2010-08-26 | N/A | 1096 | N/A | N/A | 13 | 5 | 0.36 | 2745.6 | Agricultural | No |  |  |  | N/A | 461520 | 1.249 | 576429.14 | [6 empty] | 0 | N/A |  |  | 0 |  |  |  | Labor costs |  |  | 461520 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | Unknown | Unknown | None | None | N/A | N/A | None | N/A | N/A
FRESNO COUNTY | ACADEMY, R20A, HWY 180 TO CALIF | 30444991 | ACADEMY, HWY 180 TO CALIF | 93657 | 6019006202 | Yes | 18.04% | ACADEMY, HWY 180 TO CALIF | None | TBD | TBD | Yes | 47 | 9 | 9 | 0 | 31 | Rural | Yes | 2005-07-12 | 2008-01-22 | 2008-05-06 | 2008-06-04 | 2010 | 2010-08-26 | N/A | 924 | N/A | N/A | 21 | 0 | 1.21 | 5596.8 | Agricultural | Yes |  |  |  | N/A | 815808 | 1.249 | 1018927.682 | [6 empty] | 0 | N/A |  |  | 0 |  |  |  | Labor costs |  |  | 815808 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Yes | No | No | No | No | No | No | None | None | N/A | N/A | None | N/A | N/A
FRESNO COUNTY | ASHLAN AVE, FRESNO COUNTY | 31150408 | ASHLAN AVE | 93704 | 6019004602 | No | 7.319% | ASHLAN AVE, PALM AVE & THORNE AVE | None | Project met one or more Rule 20A criteria | Resolution# 15-009 | Yes | 47 | 9 | 9 | 0 | 31 | Urban | No | 2014-07-15 | 2016-04-25 | 2017-08-21 | 2017-12-28 | 2018 | 2018-07-17 | N/A | 650 | N/A | N/A | 14 | 3 | 1.0442 | 5513.2315 | Residential | Yes |  |  |  | N/A | 2260300.36 | TBD | 2260300.36 | [6 empty] | 0 | N/A |  |  | 0 |  |  |  | Restrictive work conditions |  |  | 2260300.36 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Yes | Yes | Yes | No | No | No | No | Heavy traffic area resulted in a traffic incident. Work hours restricted due to proximity to school and residential traffic. | None | N/A | N/A | None | N/A | N/A
FRESNO COUNTY | EP HWY 180 R20A-BELMONT-FOWLER TO ARMSTR | 30313837 | HWY 180, BELMONT-FOWLER TO ARMSTR | 93727 | 6019005805 | No | 13.74% | HWY 180, BELMONT-FOWLER TO ARMSTR | None | TBD | TBD | Yes | 47 | 9 | 9 | 0 | 31 | Rural | No | TBD | 2003-04-28 | 2003-09-29 | 2004-04-09 | 2006 | 2018-10-23 | N/A | #VALUE! | N/A | N/A |  |  | 0.76 | 3115.2 | Agricultural | No |  |  |  | N/A | 414821.35 | 1.591 | 659966.6897 | [6 empty] | Unknown | Unknown |  |  | 0 |  |  |  | Other |  |  | 414821.35 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | None | None | N/A | N/A | None | N/A | N/A
FRESNO COUNTY | EP SQUAW VALLEY RULE 20A | 30236509 | SQUAW VALLEY | 93675 | 6019006403 | No | 12.17% | SQUAW VALLEY | Tier 2 | TBD | TBD | Yes | 47 | 9 | 9 | 0 | 31 | Suburban | No | 2000-06-13 | 2002-01-04 | 2002-06-24 | 2003-06-04 | 2005 | 2007-03-24 | N/A | 570 | N/A | N/A | 19 | 5 | 0.56 | 2904 | Residential | No |  |  |  | N/A | 439700.2653 | 1.7065 | 750353.2103 | [6 empty] | Unknown | Unknown |  |  | 0 |  |  |  | Other |  |  | 439700.2653 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | None | None | N/A | N/A | None | N/A | N/A
FRESNO COUNTY | FRIANT RD BTWN BUGG & NO. FORK | 30467134 | FRIANT RD, BUGG & NO FORK | 93626 | 6019005515 | No | 6.231% | FRIANT RD, BUGG & NO FORK | None | TBD | TBD | Yes | 47 | 9 | 9 | 0 | 31 | Urban | No | 2004-08-03 | 2007-04-17 | 2007-09-20 | 2008-02-26 | 2010 | 2011-03-16 | N/A | 987 | N/A | N/A | 9 | 0 | 0.02 | 2376 | Residential | No |  |  |  | N/A | 609176 | 1.249 | 760848.4958 | [6 empty] | Unknown | Unknown |  |  | 0 |  |  |  | Labor costs |  |  | 609176 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | None | None | N/A | N/A | None | N/A | N/A
FRESNO COUNTY | FRIANT ROAD RULE 20A | 30513231 | FRIANT RD | 93626 | 6019005515 | No | 6.231% | FRIANT RD | None | TBD | TBD | Yes | 47 | 9 | 9 | 0 | 31 | Rural | No | 1998-08-25 | 2005-10-12 | 2008-02-20 | 2008-04-30 | 2010 | 2010-08-26 | N/A | 2605 | N/A | N/A | 10 | 1 | 1.99 | 3326.4 | Agricultural | No |  |  |  | N/A | 1118261 | 1.249 | 1396685.3581 | [6 empty] | Unknown | Unknown |  |  | 0 |  |  |  | Contract costs |  |  | 1118261 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | None | None | N/A | N/A | None | N/A | N/A
FRESNO COUNTY | GEP ACADEMY AVE., HWY 180 TO MCKINLEY | 30258442 | ACADEMY AVE, HWY 180 TO MCKINLEY | 93657 | 6019005906 | Yes | 7.143% | ACADEMY AVE, HWY 180 TO MCKINLEY | None | TBD | TBD | Yes | 47 | 9 | 9 | 0 | 31 | Unknown | Yes | TBD | 2002-05-01 | 2004-10-07 | 2003-05-19 | 2006 | 2007-03-24 | N/A | #VALUE! | N/A | N/A |  |  | 2.59 | 9820.8 | Unknown | Unknown |  |  |  | N/A | 1537727.52 | 1.591 | 2446472.2973 | [10 empty] | 0 |  |  |  | Unknown |  |  | 1537727.52 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
FRESNO COUNTY, SANGER | ACADEMY, SANGER | 30444989 | ACADEMY, SANGER | 93657 | 6019006100 | Yes | 17.49% | ACADEMY AVE, JENSEN & 10TH | None | TBD | TBD | Yes | 47 | 9 | 9 | 0 | 31 | Urban | Yes | 2005-03-15 | 2008-07-21 | 2009-05-04 | 2010-08-26 | 2013 | 2014-02-28 | N/A | 1224 | N/A | N/A | 21 | 5 | 0.32 | 5332.8 | Commercial | Yes |  |  |  | N/A | 1125908 | 1.1048 | 1243907.5641 | [6 empty] | Unknown | unknown |  |  | 0 |  |  |  | Labor costs |  |  | 1125908 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Yes | No | No | No | No | No | No | None | None | N/A | N/A | None | N/A | N/A
HURON | LASSEN AVE PH 3, HURON | No Order | LASSEN AVE PH 3 | 93234 | 6019007802 | Yes | 14.54% | LASSEN AVE BTW 9TH ST & PALMER AVE | None | Project met one or more Rule 20A criteria | Resolution# 2019-2048 | No | 47 | 9 | 9 | 0 | 31 | Suburban | Yes | 2019-07-17 | TBD | TBD | TBD | TBD | N/A | N/A | #VALUE! | 0 | N/A | 0 | 0 | Project not completed or closed | Project not completed or closed | Commercial | Unknown | TBD | TBD | TBD | 3226138.04 | N/A | TBD | N/A | [6 empty] | TBD | TBD | [6 empty] | Project in planning phase |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | Yes | No | No | Insufficient allocation | None | N/A | N/A | No | N/A | N/A
KERMAN | WHITESBRIDGE | 30450302 | WHITESBRIDGE | 93630 | 6019004001 | Yes | 18.78% | WHITESBRIDGE | None | TBD | TBD | Yes | 47 | 9 | 9 | 0 | 31 | Urban | Yes | 2001-10-17 | 2005-08-09 | 2007-08-28 | 2008-04-11 | 2011 | 2012-02-07 | N/A | 1392 | N/A | N/A | 13 | 1 | 0.51 | 2164.8 | Commercial | Yes |  |  |  | N/A | 1097272 | 1.1878 | 1303311.1509 | [6 empty] | Unknown | Unknown |  |  | 0 |  |  |  | Labor and material costs |  |  | 1097272 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | None | None | N/A | N/A | None | N/A | N/A
KINGSBURG | *CANC* SIERRA AVE KINGSBURG R20A | 30708926 | N/A | N/A | 6019007201 | No | 10.51% | N/A | None | N/A | N/A | No | 47 | 9 | 9 | 0 | 31 | N/A | No | 2005-01-25 | TBD | TBD | TBD | N/A | N/A | N/A | #VALUE! | N/A | 2015-08-25 | N/A | N/A | Cancelled project | Cancelled project | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [6 empty] | N/A | N/A |  |  | 0 |  |  |  | N/A, project cancelled |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KINGSBURG | 10TH STREET [ROOSEVELT SCHOOL], KINGSBURG | 30768527 | 10TH ST (ROOSEVELT SCHOOL) | 93631 | 6019007202 | Yes | 14.99% | 10TH ST (ROOSEVELT SCHOOL), NEVADA & KERN | None | Project met one or more Rule 20A criteria | Resolution# 2010-16 | No | 47 | 9 | 9 | 0 | 31 | Unknown | Yes | 2010-03-03 | TBD | TBD | TBD | TBD | N/A | N/A | #VALUE! | 2019-04-02 | N/A |  |  | Project not completed or closed | Project not completed or closed | Unknown | Unknown | TBD | TBD | TBD | 1619478.78 | N/A | TBD | N/A |  |  | 0 | 0 | 0 | 0 | 0 | N/A |  |  | 0 |  |  |  | Project in planning phase |  |  | N/A |  |  |  |  | Yes | 500000 | Fresno County | N/A | 0 | PG&E does not grant approval for credit transfer transactions. Credit transfers are agreed upon between communities. | No | Yes | No | No | No | No | No | Unknown | None | N/A | N/A | None | N/A | N/A
ORANGE COVE | ANCHOR AVE, ORANGE COVE | 31221681 | ANCHOR AVE | 93646 | Unknown | Unknown | Unknown | ACHOR AVE, NORTH OF PARK BLVD TO MARTINEZ ST | Unknown | Project met one or more Rule 20A criteria | Resolution# 2016-02 | No | 47 | 9 | 9 | 0 | 31 | Unknown | Unknown | 2016-01-13 | TBD | TBD | TBD | TBD | N/A | N/A | #VALUE! | 2019-11-01 | N/A |  |  | Project not completed or closed | Project not completed or closed | Unknown | Unknown | TBD | TBD | TBD | 2552769.8 | N/A | TBD | N/A | [6 empty] | TBD | TBD |  |  | 0 |  |  |  | Project in planning phase |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | Yes | No | No | Insufficient allocation | None | N/A | N/A | None | N/A | N/A
PARLIER | *CANC* PARLIER AVE, PARLIER R20A | 30767369 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | 47 | 9 | 9 | 0 | 31 | N/A | N/A | 2009-04-28 | TBD | TBD | TBD | N/A | N/A | N/A | #VALUE! | N/A | 2015-09-05 | N/A | N/A | Cancelled project | Cancelled project | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [6 empty] | N/A | N/A |  |  | 0 |  |  |  | N/A, project cancelled |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PARLIER | MENDOCINO AVE, PARLIER | 30676928 | MENDOCINO AVE, PARLIER | 93648 | 6019008502 | Yes | 19.26% | MENDOCINO AVE, PARLIER | None | Project met one or more Rule 20A criteria | TBD | Yes | 47 | 9 | 9 | 0 | 31 | Urban | Yes | 2007-02-07 | 2015-12-01 | 2017-01-04 | 2017-04-24 | 2018 | 2018-04-30 | N/A | 3219 | N/A | N/A | 11 | 2 | 0.96717 | 5106.6721 | Residential | Yes |  |  |  | N/A | 1636581.27 | TBD | 1636581.27 | [6 empty] | 0 | N/A |  |  | 0 |  |  |  | Overhead costs |  |  | 1636581.27 |  |  |  |  | Yes | 1719530 | Fresno County | 105.1% | 0 | PG&E does not grant approval for credit transfer transactions. Credit transfers are agreed upon between communities. | No | Yes | No | No | Yes | No | No | Easement acquisitions. Insufficient allocation. | None | N/A | N/A | None | N/A | N/A
REEDLEY | *CANC* FRANKWOOD AVENUE REEDLEY R20A | 30678560 | N/A | N/A | 6019006604 | Yes | 16.4% | N/A | None | N/A | N/A | No | 47 | 9 | 9 | 0 | 31 | N/A | Yes | 2008-09-23 | TBD | TBD | TBD | N/A | N/A | N/A | #VALUE! | N/A | 2015-09-08 | N/A | N/A | Cancelled project | Cancelled project | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [6 empty] | N/A | N/A |  |  | 0 |  |  |  | N/A, project cancelled |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
REEDLEY | BUTTONWILLOW & DINUBA | 30676927 | BUTTONWILLOW & DINUBA | 93654 | 6019006300 | Yes | 11.19% | BUTTONWILLOW & DINUBA | None | TBD | TBD | Yes | 47 | 9 | 9 | 0 | 31 | Unknown | Yes | 2007-09-11 | 2009-08-31 | 2010-09-08 | 2011-05-02 | 2012 | 2013-01-25 | N/A | 720 | N/A | N/A |  |  | 0.37 | 1636.8 | Unknown | Unknown |  |  |  | N/A | 588819 | 1.121 | 660090.4132 | [10 empty] | 0 |  |  |  | Unknown |  |  | 588819 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
REEDLEY | DINUBA AVE - SPORTS PARK, REEDLEY | 30675532 | DINUBA AVE, UUD# 1 | 93654 | Unknown | Unknown | Unknown | DINUBA AVE, BUTTONWILLOW & TRAVER CHANNEL | Unknown | Project met one or more Rule 20A criteria | Resolution# 08-212 | No | 47 | 9 | 9 | 0 | 31 | Unknown | Unknown | 2008-09-09 | TBD | TBD | TBD | TBD | N/A | N/A | #VALUE! | 2021-09-08 | N/A |  |  | Project not completed or closed | Project not completed or closed | Unknown | Unknown | TBD | TBD | TBD | 3414429.24 | N/A | TBD | N/A | [6 empty] | TBD | TBD |  |  | 0 |  |  |  | Project in planning phase |  |  | N/A |  |  |  |  | Yes | 2000000 | Fresno County | N/A | 0 | PG&E does not grant approval for credit transfer transactions. Credit transfers are agreed upon between communities. | No | No | No | No | Yes | No | No | Insufficient allocation | None | N/A | N/A | None | N/A | N/A
REEDLEY | REED AVE, REEDLEY | 74003532 | REED AVE | 93654 | 6019006603 | Yes | 14.8% | REED AVE, MANNING & SOUTH | None | Project met one or more Rule 20A criteria | Resolution# 2009-086 | Yes | 47 | 9 | 9 | 0 | 31 | Urban | Yes | 2009-12-08 | 2016-09-20 | 2017-09-22 | TBD | 2019 | 2020-01-14 | N/A | 2478 | N/A | N/A | TBD | TBD | 1.8203 | 9611.068 | Residential | Yes | TBD | TBD | TBD | N/A | 2493012.88 | TBD | 2493012.88 | [6 empty] | TBD | TBD |  |  | 0 |  |  |  | Unexpected field conditions |  |  | 2493012.88 |  |  |  |  | Yes | 2000000 | Fresno County | 80.22% | 0 | PG&E does not grant approval for credit transfer transactions. Credit transfers are agreed upon between communities. | No | No | No | No | No | No | No | None | None | N/A | N/A | None | N/A | N/A
Fresno County Total | [41 empty] | 0
Glenn County | [41 empty] | 0
ORLAND | PAPST AVE, ORLAND | No Order | PAPST AVE | 95963 | 6021010100 | No | 20.34% | PAPST AVE BTW SOUTH ST & E. SWIFT ST | None | Project met one or more Rule 20A criteria | Resolution# 2019-18 | No | 1 | 1 | 1 | 0 | 0 | Rural | No | 2019-07-15 | TBD | TBD | TBD | TBD | N/A | N/A | #VALUE! | 0 | N/A | 0 | 0 | Project not completed or closed | Project not completed or closed | Residential | Unknown | TBD | TBD | TBD | 2700000 | N/A | TBD | N/A | [6 empty] | TBD | TBD | [6 empty] | Project in planning phase |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | Yes | No | No | Insufficient allocation | None | N/A | N/A | No | N/A | N/A
Glenn County Total | [41 empty] | 0
Humboldt County | [41 empty] | 0
ARCATA | G & H STREETS, FROM 7TH TO 11TH STS. | 30171622 | G ST & H ST, FROM 7TH ST TO 11TH ST | 95521 | 6023001000 | No | 10.41% | G ST & H ST, FROM 7TH ST TO 11TH ST | None | TBD | TBD | Yes | 11 | 6 | 5 | 1 | 4 | Unknown | No | 1993-07-21 | 2000-11-17 | 2000-12-10 | 2005-11-08 | 2007 | 2007-07-31 | N/A | 2676 | N/A | N/A |  |  | 0.5 | 2851.2 | Unknown | Unknown |  |  |  | N/A | 1109690.86 | 1.4306 | 1587498.4739 | [10 empty] | 0 |  |  |  | Unknown |  |  | 1109690.86 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
EUREKA | EUREKA WATERFRONT RULE 20A *CANC | 30232261 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | 11 | 6 | 5 | 1 | 4 | N/A | N/A | TBD | TBD | TBD | TBD | N/A | 2007-03-24 | N/A | #VALUE! | N/A | 2005-04-13 | N/A | N/A | Cancelled project | Cancelled project | N/A | N/A | N/A | N/A | N/A | N/A | 3513.06 | 1.4306 | 5025.7036 | [6 empty] | N/A | N/A |  |  | 0 |  |  |  | N/A, project cancelled |  |  | 3513.06 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EUREKA | R20A - 4TH ST EUREKA | 74014380 | 4TH ST | 95501 | Unknown | Unknown | Unknown | 4TH ST, O ST & Y ST | Unknown | Project met one or more Rule 20A criteria | Resolution# 2017-21 | No | 11 | 6 | 5 | 1 | 4 | Urban | Unknown | 2017-04-04 | 2017-10-02 | TBD | TBD | TBD | N/A | N/A | 181 | 2020-05-31 | N/A | TBD | TBD | Project not completed or closed | Project not completed or closed | Commercial | Yes | TBD | TBD | TBD | 5213348.46 | N/A | TBD | N/A | [6 empty] | 0 | N/A |  |  | 0 |  |  |  | Project in progress |  |  | N/A |  |  |  |  | Yes | 1500000 | Humboldt County | N/A | 0 | PG&E does not grant approval for credit transfer transactions. Credit transfers are agreed upon between communities. | No | No | Yes | No | No | No | No | Unknown | Unknown | 0 | 0 | Unknown | 0 | 0
EUREKA | TRUESDALE ST | 30975304 | TRUESDALE ST | 95503 | 6023000200 | No | 16.57% | TRUESDALE ST, CHRISTIE ST & HOWELL ST | None | Project met one or more Rule 20A criteria | Resolution# 2012-20 | Yes | 11 | 6 | 5 | 1 | 4 | Urban | No | 2012-04-03 | 2013-11-18 | 2015-04-20 | 2015-06-11 | 2016 | 2016-10-19 | N/A | 594 | N/A | N/A | 7 | 5 | 0.22 | 897.6 | Commercial | Yes |  |  |  | N/A | 654697.39 | 1.0668 | 698452.0942 | [6 empty] | 0 | N/A |  |  | 0 | [6 empty] | 654697.39 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | Yes | Yes | No | No | Yes | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
FERNDALE | FRANCIS ST, FERNDALE | No Order | FRANCIS ST | 95536 | 6023011200 | No | 9.348% | FRANCIS ST BTW OCEAN AVE & END OF FRANCIS ST | None | Project met one or more Rule 20A criteria | Resolution# 2019-10 | No | 11 | 6 | 5 | 1 | 4 | Suburban | No | 2019-06-19 | TBD | TBD | TBD | TBD | N/A | N/A | #VALUE! | 0 | N/A | 0 | 0 | Project not completed or closed | Project not completed or closed | Commercial | Unknown | TBD | TBD | TBD | 1756219.29 | N/A | TBD | N/A | [6 empty] | TBD | TBD | [6 empty] | Project in planning phase |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | Yes | No | No | Insufficient allocation | None | N/A | N/A | No | N/A | N/A
FERNDALE | MAIN ST, FERNDALE | No Order | SHAW TO HERBERT | 95536 | 6023011200 | No | 9.348% | MAIN ST | None | Project met one or more Rule 20A criteria | Resolution# 2019-11 | No | 11 | 6 | 5 | 1 | 4 | Suburban | No | 2019-06-19 | TBD | TBD | TBD | TBD | N/A | N/A | #VALUE! | 0 | N/A | 0 | 0 | Project not completed or closed | Project not completed or closed | Commercial | Unknown | TBD | TBD | TBD | 3194539.05 | N/A | TBD | N/A | [6 empty] | TBD | TBD | [6 empty] | Project in planning phase |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | Yes | No | No | Insufficient allocation | None | N/A | N/A | No | N/A | N/A
FORTUNA | 12TH STREET, FORTUNA | 74004300 | 12TH ST | 95540 | Unknown | Unknown | Unknown | 12TH ST, L ST & NEWBERG | Unknown | Project met one or more Rule 20A criteria | Resolution# 2013-08 | No | 11 | 6 | 5 | 1 | 4 | Suburban | Unknown | 2013-04-15 | 2016-05-23 | 2019-06-17 | TBD | TBD | N/A | N/A | 1134 | 2019-12-01 | N/A | 45 | 40 | Project not completed or closed | Project not completed or closed | Residential | Yes | TBD | TBD | TBD | 4341180.96 | N/A | TBD | N/A | [6 empty] | 0 | N/A |  |  | 0 |  |  |  | Project in progress |  |  | N/A |  |  |  |  | Yes | 2474346 | Humboldt County | N/A | 0 | PG&E does not grant approval for credit transfer transactions. Credit transfers are agreed upon between communities. | No | Yes | Yes | Yes | No | Yes | Unknown | 0 | None | 0 | 0 | None | 0 | 0
HUMBOLDT COUNTY | SCHOOL RD | 30406159 | SCHOOL RD | 95519 | 6023010501 | No | 12.58% | SCHOOL RD IN MCKINLEYVILLE, CENTRAL AVE TO HWY 101 | None | Project met one or more Rule 20A criteria | Resolution# 09-68 | Yes | 11 | 6 | 5 | 1 | 4 | Suburban | No | 2009-09-01 | 2011-12-20 | 2014-06-02 | 2014-08-26 | 2015 | 2015-07-14 | N/A | 840 | N/A | N/A | 38 | 23 | 1.69 | 4857.6 | Residential | Yes |  |  |  | N/A | 3663855.44 | 1.0677 | 3911983.3223 | [6 empty] | 0 | N/A |  |  | 0 | [6 empty] | 3663855.44 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Yes | Yes | Yes | Unknown | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
HUMBOLDT COUNTY | GARBERVILLE TOWN SQUARE, GARBERVILLE | No Order | TOWN SQUARE UUD | 95542 | 6023011600 | No | 7.283% | SECOND ST BTW CHURCH ST & CONGER ST AND ON CHURCH ST BTW LOCUST ST & REDWOOD DR | Tier 2 | Project met one or more Rule 20A criteria | Resolution# 19-102 | No | 11 | 6 | 5 | 1 | 4 | Suburban | No | 2019-10-15 | TBD | TBD | TBD | TBD | N/A | N/A | #VALUE! | 0 | N/A | 0 | 0 | Project not completed or closed | Project not completed or closed | Commercial | Unknown | TBD | TBD | TBD | 2000000 | N/A | TBD | N/A | [6 empty] | TBD | TBD | [6 empty] | Project in planning phase |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | Yes | No | No | Insufficient allocation | None | N/A | N/A | No | N/A | N/A
HUMBOLDT COUNTY, TRINIDAD | E TRINIDAD | 30311450 | E TRINIDAD | 95570 | 6023010200 | No | 8.85% | E TRINIDAD | None | TBD | TBD | Yes | 11 | 6 | 5 | 1 | 4 | Unknown | No | 2002-11-05 | 2003-04-14 | 2008-01-16 | 2008-04-24 | 2009 | 2010-03-16 | N/A | 160 | N/A | N/A |  |  | 0.08 | 4224 | Unknown | Unknown |  |  |  | N/A | 249877 | 1.2297 | 307268.4213 | [10 empty] | 0 |  |  |  | Unknown |  |  | 249877 |  |  |  |  | Yes | 25000 | Humboldt County | 10% | 0 | PG&E does not grant approval for credit transfer transactions. Credit transfers are agreed upon between communities. | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
RIO DELL | WILDWOOD AVE PH 2, RIO DELL | No Order | UUD NO. 2 | 95562 | 6023011100 | No | 14.61% | WILDWOOD AVE FROM ASH ST TO WEST BRIDGE/EAST BRIDGE STREETS | Part of project adjacent to Tier 2 | Project met one or more Rule 20A criteria | Resolution# 683 | No | 11 | 6 | 5 | 1 | 4 | Rural | No | 1995-04-04 | TBD | TBD | TBD | TBD | N/A | N/A | #VALUE! | 0 | N/A | 0 | 0 | Project not completed or closed | Project not completed or closed | Residential | Unknown | TBD | TBD | TBD | 434994.86 | N/A | TBD | N/A | [6 empty] | TBD | TBD | [6 empty] | Project in planning phase |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | Yes | No | No | Insufficient allocation | None | N/A | N/A | No | N/A | N/A
Humboldt County Total | [41 empty] | 0
Kern County | [41 empty] | 0
ARVIN | VARSITY RD, ARVIN | No Order | UUD #1 | 93203 | 6029006301 | No | 18.11% | VARSITY RD BTW COMANCHE DR & CAMPUS DR | None | Project met one or more Rule 20A criteria | Resolution# 2019-65 | No | 24 | 4 | 2 | 2 | 15 | Rural | No | 2019-07-23 | TBD | TBD | TBD | TBD | N/A | N/A | #VALUE! | 0 | N/A | 0 | 0 | Project not completed or closed | Project not completed or closed | Residential | Unknown | TBD | TBD | TBD | 3025242.88 | N/A | TBD | N/A | [6 empty] | TBD | TBD | [6 empty] | Project in planning phase |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | Yes | No | No | Insufficient allocation | None | N/A | N/A | No | N/A | N/A
BAKERSFIELD | *CANC* EP ASHE ROAD BAKERSFIELD *CANC | 80045879 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | 24 | 4 | 2 | 2 | 15 | N/A | N/A | 2007-06-20 | TBD | TBD | TBD | N/A | N/A | N/A | #VALUE! | N/A | 2008-07-25 | N/A | N/A | Cancelled project | Cancelled project | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [6 empty] | N/A | N/A |  |  | 0 |  |  |  | N/A, project cancelled |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BAKERSFIELD | *CANC* EP TAFT HWY BAKERSFIELD *CANC | 80045878 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | 24 | 4 | 2 | 2 | 15 | N/A | N/A | 2007-06-20 | TBD | TBD | TBD | N/A | N/A | N/A | #VALUE! | N/A | 2008-07-25 | N/A | N/A | Cancelled project | Cancelled project | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [6 empty] | N/A | N/A |  |  | 0 |  |  |  | N/A, project cancelled |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BAKERSFIELD | 34TH ST, BAKERSFIELD | 74012450 | 34TH ST | 93301 | Unknown | Unknown | Unknown | 34TH ST, CHESTER AVE TO UNION AVE | Unknown | Project met one or more Rule 20A criteria | Resolution# 151-14 | No | 24 | 4 | 2 | 2 | 15 | Urban | Unknown | 2014-08-13 | 2018-04-09 | TBD | TBD | TBD | N/A | N/A | 1335 | 2020-12-01 | N/A | TBD | tbd | Project not completed or closed | Project not completed or closed | Commercial | Yes | TBD | TBD | TBD | 3457753.54 | N/A | TBD | N/A | [6 empty] | TBD | TBD |  |  | 0 |  |  |  | Project in progress |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | TBD | TBD | TBD | TBD | TBD | TBD
BAKERSFIELD | CALIFORNIA AVE | 30764513 | CALIFORNIA AVE | 93301 | 6029001600 | Yes | 47.77% | CALIFORNIA AVE, S ST TO UNION AVE | None | TBD | Resolution# 138-09 | Yes | 24 | 4 | 2 | 2 | 15 | Unknown | Yes | 2009-12-16 | 2011-04-06 | 2012-01-23 | 2013-02-22 | 2014 | 2015-01-15 | N/A | 476 | N/A | N/A |  |  | 0.27 | 1795.2 | Unknown | Unknown |  |  |  | N/A | 932892.42 | 1.0831 | 1010399.2544 | [10 empty] | 0 |  |  |  | Unknown |  |  | 932892.42 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
BAKERSFIELD | CALLOWAY, BAKERSFIELD | 30764510 | CALLOWAY DR | 93301 | 6029003807 | No | 10.01% | CALLOWAY DR, HAGEMAN TO MEACHAM | None | Project met one or more Rule 20A criteria | Resolution# 139-09 | Yes | 24 | 4 | 2 | 2 | 15 | Suburban | No | 2009-12-16 | 2015-01-20 | 2016-07-01 | 2016-11-14 | 2017 | 2017-07-17 | N/A | 1861 | N/A | N/A | 18 | 0 | 1.52 | 3220.8 | Residential | Yes |  |  |  | N/A | 3425178.54 | 1.048 | 3589737.6395 | [6 empty] | 0 | N/A |  |  | 0 |  |  |  | Labor costs |  |  | 3425178.54 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Yes | Yes | No | No | No | Yes | No | Easement acquisitions. Trench participation backed out by CATV. | None | N/A | N/A | None | N/A | N/A
BAKERSFIELD | EP AQUATIC PARK/ICE CENTER RULE 20A | 30316645 | AQUATIC PARK/ICE CENTER | 93301 | 6029001600 | Yes | 47.77% | AQUATIC PARK/ICE CENTER | None | TBD | TBD | Yes | 24 | 4 | 2 | 2 | 15 | Urban | Yes | TBD | 2003-06-23 | 2003-09-18 | 2003-10-29 | 2006 | 2007-03-24 | N/A | #VALUE! | N/A | N/A |  |  | 0.16 | 739.2 | Commercial | No |  |  |  | N/A | 217265.8 | 1.591 | 345662.5143 | [6 empty] | Unknown | Unknown |  |  | 0 |  |  |  | Other |  |  | 217265.8 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | None | None | N/A | N/A | None | N/A | N/A
BAKERSFIELD | EP ROSEDALE HIGHWAY RULE 20A | 30294146 | ROSEDALE HIGHWAY | 93308 | 6029000507 | Yes | 7.449% | ROSEDALE HIGHWAY | None | TBD | TBD | Yes | 24 | 4 | 2 | 2 | 15 | Urban | Yes | TBD | 2003-01-25 | 2004-05-20 | 2004-12-28 | 2006 | 2007-03-24 | N/A | #VALUE! | N/A | N/A |  | 2 | 0.33 | 1425.6 | Commercial | No |  |  |  | N/A | 525841.05 | 1.591 | 836595.2647 | [6 empty] | Unknown | Unknown |  |  | 0 |  |  |  | Other |  |  | 525841.05 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | None | None | N/A | N/A | None | N/A | N/A
BAKERSFIELD | GOSFORD RD | 30726360 | GOSFORD RD | 93313 | 6029003206 | Yes | 21.36% | GOSFORD RD | None | TBD | TBD | Yes | 24 | 4 | 2 | 2 | 15 | Rural | Yes | 2007-06-20 | 2010-09-17 | 2011-04-14 | 2011-08-30 | 2012 | 2013-01-25 | N/A | 1185 | N/A | N/A | 7 | 1 | 0.43 | 2217.6 | Agricultural | Yes |  |  |  | N/A | 688009 | 1.121 | 771286.499 | [6 empty] | Unknown | Unknown |  |  | 0 |  |  |  | Labor, material, and overhead costs |  |  | 688009 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | None | None | N/A | N/A | None | N/A | N/A
BAKERSFIELD | SOUTH MILL CREEK | 30656093 | SOUTH MILL CREEK | 93301 | 6029001600 | Yes | 47.77% | SOUTH MILL CREEK | None | TBD | TBD | Yes | 24 | 4 | 2 | 2 | 15 | Urban | Yes | 2008-05-21 | 2008-09-04 | 2008-10-13 | 2009-02-13 | 2011 | 2012-02-07 | N/A | 106 | N/A | N/A | 38 | 11 | 0.53 | 5649.6 | Commercial | Yes |  |  |  | N/A | 1518177 | 1.1878 | 1803251.1657 | [6 empty] | Unknown | Unknown |  |  | 0 |  |  |  | Labor and material costs |  |  | 1518177 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | None | None | N/A | N/A | None | N/A | N/A
BAKERSFIELD | SPORTS VILLAGE- ASHE RD SEG. 1 BKSF | 30629431 | SPORTS VILLAGE- ASHE RD SEG 1 BKSF | 93313 | 6029003206 | Yes | 21.36% | SPORTS VILLAGE- ASHE RD SEG 1 BKSF | None | TBD | TBD | Yes | 24 | 4 | 2 | 2 | 15 | Rural | Yes | 2007-06-20 | 2008-11-03 | 2009-02-07 | 2009-08-18 | 2010 | 2011-03-16 | N/A | 502 | N/A | N/A | 10 | 0 | 0.6 | 2956.8 | Agricultural | No |  |  |  | N/A | 787398 | 1.249 | 983444.167 | [6 empty] | Unknown | Unknown |  |  | 0 |  |  |  | Labor and material costs |  |  | 787398 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | None | None | N/A | N/A | None | N/A | N/A
BAKERSFIELD | STINE RD, BAKERSFIELD | 74001555 | STINE RD, UUD# 2 | 93313 | Unknown | Unknown | Unknown | STINE RD, PANAMA LN & RYZONA ST | Unknown | Project met one or more Rule 20A criteria | Resolution# 149-14 | No | 24 | 4 | 2 | 2 | 15 | Suburban | Unknown | 2014-08-13 | 2016-04-13 | 2017-09-08 | TBD | TBD | N/A | N/A | 609 | 2020-01-19 | N/A | TBD | TBD | Project not completed or closed | Project not completed or closed | Residential | Yes | TBD | TBD | TBD | 4655378.98 | N/A | TBD | N/A | [6 empty] | TBD | TBD |  |  | 0 |  |  |  | Project in progress |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Yes | Yes | Yes | No | No | Yes | No | Easement acquisitions. Trench participation backed out by CATV. | None | N/A | N/A | None | N/A | N/A
BAKERSFIELD | STOCKDALE HWY PH 20A - COFFEE ROAD | 30271365 | STOCKDALE HWY PH 20A - COFFEE ROAD | 93309 | 6029001802 | No | 13.52% | STOCKDALE HWY PH 20A - COFFEE ROAD | None | TBD | TBD | Yes | 24 | 4 | 2 | 2 | 15 | Unknown | No | 2001-03-14 | 2002-09-10 | 2003-11-03 | 2004-08-04 | 2005 | 2007-03-24 | N/A | 545 | N/A | N/A |  |  | 1.43 | 6969.6 | Unknown | No |  |  |  | N/A | 1749618.3667 | 1.7065 | 2985742.4747 | [6 empty] | Unknown | Unknown |  |  | 0 |  |  |  | Other |  |  | 1749618.3667 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | None | None | N/A | N/A | None | N/A | N/A
BAKERSFIELD | STOCKDALE HWY PH II RULE 20A | 30366094 | STOCKDALE HWY PH 2 | 93309 | 6029001801 | Yes | 18.07% | STOCKDALE HWY PH 2 | None | TBD | TBD | Yes | 24 | 4 | 2 | 2 | 15 | Urban | Yes | 2001-03-14 | 2004-04-05 | 2004-11-12 | 2005-01-19 | 2006 | 2007-03-24 | N/A | 1118 | N/A | N/A | 10 |  | 0.53 | 2059.2 | Residential | No |  |  |  | N/A | 560214.1 | 1.591 | 891281.6207 | [6 empty] | Unknown | Unknown |  |  | 0 |  |  |  | Other |  |  | 560214.1 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | None | None | N/A | N/A | None | N/A | N/A
BAKERSFIELD | WIBLE RD | 30909576 | WIBLE RD | 93313 | 6029003205 | Yes | 15.2% | WIBLE RD, BERKSHIRE RD & PANAMA LN | None | Project met one or more Rule 20A criteria | Resolution# 017-12 | Yes | 24 | 4 | 2 | 2 | 15 | Unknown | Yes | 2012-02-01 | TBD | TBD | 2013-07-12 | 2015 | 2016-01-13 | N/A | #VALUE! | N/A | N/A |  |  | 1.41 | 4593.6 | Unknown | Unknown |  |  |  | N/A | 2860709.76 | 1.0677 | 3054446.0758 | [10 empty] | 0 |  |  |  | Unknown |  |  | 2860709.76 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
KERN COUNTY | COTTONWOOD ROAD, BAKERSFIELD | 30675530 | COTTONWOOD RD, BAKERSFIELD | 93307 | 6029002400 | Yes | 19.2% | TBD | None | TBD | Resolution# 2004421 | Yes | 24 | 4 | 2 | 2 | 15 | Urban | Yes | 2004-11-30 | 2009-08-27 | 2009-11-09 | 2010-10-06 | 2013 | 2014-02-28 | N/A | 1731 | N/A | N/A | 33 | 16 | 1.64 | 4910.4 | Residential | Yes |  |  |  | N/A | 2734351 | 1.1048 | 3020921.6844 | [6 empty] | Unknown | Unknown |  |  | 0 |  |  |  | Increase in AFUDC |  |  | 2734351 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | None | None | N/A | N/A | None | N/A | N/A
KERN COUNTY | EP FORT TEJON RULE 20A - LEBEC | 30558119 | FORT TEJON, LEBEC | 93225 | 6029003306 | No | 2.45% | FORT TEJON, LEBEC | Tier 2 | TBD | TBD | Yes | 24 | 4 | 2 | 2 | 15 | Rural | No | 2004-08-03 | 2007-03-14 | 2008-09-02 | 2008-11-20 | 2010 | 2010-08-26 | N/A | 953 | N/A | N/A | 7 | 0 | 0.35 | 1900.8 | Agricultural | No |  |  |  | N/A | 209282 | 1.249 | 261388.9826 | [6 empty] | Unknown | Unknown |  |  | 0 |  |  |  | Labor and material costs |  |  | 209282 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | None | None | N/A | N/A | None | N/A | N/A
KERN COUNTY | EP SHAFTER MEMORIAL PARK RULE 20A | 30218464 | SHAFTER MEMORIAL PARK | 93263 | 6029003900 | Unknown | 4.089% | SHAFTER MEMORIAL PARK | None | TBD | TBD | Yes | 24 | 4 | 2 | 2 | 15 | Rural | Unknown | 1999-12-14 | 2001-09-17 | 2001-12-05 | 2002-02-07 | 2005 | 2007-03-24 | N/A | 643 | N/A | N/A | 7 | 3 | 0.2 | 1742.4 | Agricultural | No |  |  |  | N/A | 155202.62 | 1.7065 | 264854.9327 | [6 empty] | Unknown | Unknown |  |  | 0 |  |  |  | Other |  |  | 155202.62 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | None | None | N/A | N/A | None | N/A | N/A
KERN COUNTY | OLIVE AVE. (FRUITVALE - COFFEE) RULE 20A | 30366845 | OLIVE AVE (FRUITVALE - COFFEE) | 93308 | 6029000504 | Yes | 18.21% | OLIVE AVE (FRUITVALE - COFFEE) | None | TBD | TBD | Yes | 24 | 4 | 2 | 2 | 15 | Urban | Yes | 2004-02-24 | 2005-04-26 | 2006-01-06 | 2007-02-12 | 2010 | 2011-03-16 | N/A | 427 | N/A | N/A | 35 | 12 | 1.73 | 6388.8 | Residential | No |  |  |  | N/A | 1947899 | 1.249 | 2432886.4303 | [6 empty] | 8613 | Unknown |  |  | 0 |  |  |  | Labor costs |  |  | 1947899 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | None | None | N/A | N/A | None | N/A | N/A
KERN COUNTY | SEVENTH STANDARD ROAD RULE 20A | 30382278 | SEVENTH STANDARD RD | 93308 | 6029000101 | Yes | 17.36% | SEVENTH STANDARD RD | None | TBD | TBD | Yes | 24 | 4 | 2 | 2 | 15 | Suburban | Yes | TBD | TBD | TBD | 2004-12-15 | 2006 | 2007-03-24 | N/A | #VALUE! | N/A | N/A |  |  | 0.32 | 2006.4 | Industrial | No |  |  |  | N/A | 208971.61 | 1.591 | 332466.7395 | [6 empty] | Unknown |  |  |  | 0 |  |  |  | Other |  |  | 208971.61 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | None | None | N/A | N/A | None | N/A | N/A
KERN COUNTY | STATE ROUTE 43 KERN CNTY R20A | 35040079 | STATE ROUTE 43 | 93276 | 6029003700 | Yes | 12.22% | STATE ROUTE 43 BETWEEN STATE ROUTE 119 & I-5 | None | Project met one or more Rule 20A criteria | Resolution# 2018-072 | No | 24 | 4 | 2 | 2 | 15 | Rural | Yes | 2018-03-20 | TBD | TBD | TBD | N/A | N/A | N/A | #VALUE! | N/A | TBD | N/A | N/A | Cancelled project | Cancelled project | Residential | N/A | N/A | N/A | N/A | N/A | N/A | TBD | N/A | [6 empty] | N/A | N/A | [6 empty] | N/A, project cancelled |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | Yes | No | No | Insufficient allocation | None | N/A | N/A | No | N/A | N/A
MCFARLAND | GARZOLI AVE, MCFARLAND | 74003981 | GARZOLI AVE | 93250 | Unknown | Unknown | Unknown | GARZOLI AVE, KYRA AVE TO W. PERKINS AVE | Unknown | Project met one or more Rule 20A criteria | Resolution# 2015-0243 | No | 24 | 4 | 2 | 2 | 15 | Suburban | Unknown | 2015-10-22 | 2016-10-31 | TBD | TBD | TBD | N/A | N/A | 375 | 2019-05-01 | N/A | 18 | 1 | Project not completed or closed | Project not completed or closed | Residential | Yes | TBD | TBD | TBD | 2799707.77 | N/A | TBD | N/A | [6 empty] | None | N/A |  |  | 0 |  |  |  | Project in progress |  |  | N/A |  |  |  |  | Yes | 3912000 | Kern County | N/A | 0 | PG&E does not grant approval for credit transfer transactions. Credit transfers are agreed upon between communities. | No | Yes | Yes | Yes | No | No | No | Communication utility backed out of trench. Insufficient allocation. Scope reduction due to unresolved issue with Private water line. | None | N/A | N/A | None | N/A | N/A
TAFT | ET CENTER ST. RULE20A -CITYOF TAFT *CANC | 30253349 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | 24 | 4 | 2 | 2 | 15 | N/A | N/A | TBD | TBD | TBD | TBD | N/A | 2007-03-24 | N/A | #VALUE! | N/A | 2005-07-27 | N/A | N/A | Cancelled project | Cancelled project | N/A | N/A | N/A | N/A | N/A | N/A | 10088 | 1.4306 | 14431.6631 | [6 empty] | N/A | N/A |  |  | 0 |  |  |  | N/A, project cancelled |  |  | 10088 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WASCO | EP BECKES ST. RULE 20A *CANC *CANC | 30329651 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | 24 | 4 | 2 | 2 | 15 | N/A | N/A | TBD | TBD | TBD | TBD | N/A | 2007-03-24 | N/A | #VALUE! | N/A | 2005-09-02 | N/A | N/A | Cancelled project | Cancelled project | N/A | N/A | N/A | N/A | N/A | N/A | 393 | 1.4306 | 562.2169 | [6 empty] | N/A | N/A |  |  | 0 |  |  |  | N/A, project cancelled |  |  | 393 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Kern County Total | [41 empty] | 0
Kings County | [41 empty] | 0
KINGS COUNTY, LEMOORE | LEMOORE AVE | 30178490 | LEMOORE AVE | 93245 | 6031000405 | No | 17.67% | LEMOORE AVE | None | TBD | TBD | Yes | 1 | 0 | 0 | 0 | 1 | Urban | No | 2003-05-20 | 2004-03-23 | 2007-10-11 | 2009-05-28 | 2012 | 2012-09-13 | N/A | 308 | N/A | N/A | 48 | 18 | 2.21 | 7075.2 | Residential | Yes |  |  |  | N/A | 4290373.44 | 1.121 | 4809685.789 | [6 empty] | Unknown | Unknown |  |  | 0 |  |  |  | Unexpected field conditions |  |  | 4290373.44 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Yes | No | No | No | No | Unknown | Unknown | Unforseen substructures | None | N/A | N/A | None | N/A | N/A
Kings County Total | [41 empty] | 0
Lake County | [41 empty] | 0
CLEARLAKE | OLYMPIC DR - CANCELLATION | 30058339 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | 6 | 2 | 2 | 0 | 3 | N/A | N/A | 1993-04-12 | TBD | TBD | TBD | N/A | 2012-02-07 | N/A | #VALUE! | N/A | 2011-09-03 | N/A | N/A | Cancelled project | Cancelled project | N/A | N/A | N/A | N/A | N/A | N/A | 89805 | 1.121 | 100675.1133 | [6 empty] | N/A | N/A |  |  | 0 |  |  |  | N/A, project cancelled |  |  | 89805 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LAKE COUNTY | ISLAND DRIVE, CLEARLAKE | 30383780 | ISLAND DR, CLEARLAKE | 95423 | 6033000600 | No | 21.48% | TBD | None | TBD | TBD | Yes | 6 | 2 | 2 | 0 | 3 | Rural | No | 1999-09-07 | 2004-06-09 | 2010-05-05 | 2012-09-28 | 2013 | 2014-02-28 | N/A | 1737 | N/A | N/A | 5 | 1 | 0.16 | 792 | Commercial | Yes |  |  |  | N/A | 808835 | 1.1048 | 893604.073 | [10 empty] | 0 | [6 empty] | 808835 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
LAKE COUNTY | NICE RULE 20A | 30381109 | NICE | 95464 | 6033000502 | No | 22.01% | NICE | Tier 2 | TBD | TBD | Yes | 6 | 2 | 2 | 0 | 3 | Unknown | No | 2001-09-18 | 2004-05-25 | 2004-06-16 | 2006-11-10 | 2010 | 2010-08-26 | N/A | 980 | N/A | N/A |  |  | 0.7 | 2112 | Unknown | Unknown |  |  |  | N/A | 784282 | 1.249 | 979552.3461 | [10 empty] | 0 |  |  |  | Unknown |  |  | 784282 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
LAKE COUNTY | SOUTH MAIN AND SODA BAY RD, LAKE COUNTY | 74001800 | SOUTH MAIN ST - SODA BAY RD, LAKEPORT AREA, COUNTY OF LAKE | 95453 | Unknown | Unknown | Unknown | PHASE 1: SODA BAY RD & SOUTH MAIN ST, SYLVA LN | Unknown | Project met one or more Rule 20A criteria | Resolution# 2001-73 | No | 6 | 2 | 2 | 0 | 3 | Suburban | Unknown | 2001-04-17 | 2015-12-14 | TBD | TBD | TBD | N/A | N/A | 5354 | 2020-08-03 | N/A | TBD | TBD | Project not completed or closed | Project not completed or closed | Commercial | Yes | TBD | TBD | TBD | 5223378.67 | N/A | TBD | N/A | [6 empty] | TBD | TBD |  |  | 0 |  |  |  | Project in progress |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | Yes | No | No | No | Yes | No | Unknown | Unknown | 0 | 0 | 0 | 0 | 0
LAKE COUNTY | UPPER LAKE | 30384129 | UPPER LAKE | 95485 | 6033000100 | No | 15.03% | UPPER LAKE | None | TBD | TBD | Yes | 6 | 2 | 2 | 0 | 3 | Unknown | No | 2004-11-02 | 2005-06-30 | 2007-06-15 | 2008-04-07 | 2009 | 2010-03-16 | N/A | 240 | N/A | N/A |  |  | 0.49 | 1742.4 | Unknown | Unknown |  |  |  | N/A | 943679.53 | 1.2297 | 1160422.6055 | [10 empty] | 0 |  |  |  | Unknown |  |  | 943679.53 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
LAKEPORT | 11TH ST, LAKEPORT | No Order | 11TH ST | 95453 | 6033000400 | No | 19.25% | 11TH ST & NORTH MAIN ST | Tier 2 | Project met one or more Rule 20A criteria | Resolution# 2730 (2019) | No | 6 | 2 | 2 | 0 | 3 | Suburban | No | 2019-10-01 | TBD | TBD | TBD | TBD | N/A | N/A | #VALUE! | 0 | N/A | 0 | 0 | Project not completed or closed | Project not completed or closed | Residential | Unknown | TBD | TBD | TBD | 8617739.26 | N/A | TBD | N/A | [6 empty] | TBD | TBD | [6 empty] | Project in planning phase |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | Yes | No | No | Insufficient allocation | None | N/A | N/A | No | N/A | N/A
Lake County Total | [41 empty] | 0
Madera County | [41 empty] | 0
CHOWCHILLA | DIST. 5 2ND- 6TH STREET, CHOWCHILLA | 30675657 | 2ND-6TH ST DIST 5 | 93610 | 6039000300 | No | 22.83% | 2ND-6TH ST, ROBERTSON BLVD & TRINITY AVE | None | Project met one or more Rule 20A criteria | Resolution# 66-11 | No | 9 | 0 | 0 | 0 | 6 | Urban | No | 2003-10-13 | 2012-10-15 | TBD | TBD | TBD | N/A | N/A | 3290 | N/A | TBD | TBD | TBD | Project not completed or closed | Project not completed or closed | Commercial | Yes | TBD | TBD | TBD | 654671.44 | N/A | TBD | N/A | [6 empty] | TBD | TBD |  |  | 0 |  |  |  | Project in progress |  |  | N/A |  |  |  |  | Yes | 1000000 | Madera County | N/A | N/A | PG&E does not grant approval for credit transfer transactions. Credit transfers are agreed upon between communities. | Yes | Yes | No | No | Yes | Unknown | Unknown | Easement acquisitions. Insufficient allocation. | Yes | 0 | 0 | None | N/A | N/A
MADERA | *CANC* LAKE STREET, MADERA, RULE 20A | 30746199 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | 9 | 0 | 0 | 0 | 6 | N/A | N/A | 2009-10-08 | TBD | TBD | TBD | N/A | N/A | N/A | #VALUE! | N/A | 2012-07-05 | N/A | N/A | Cancelled project | Cancelled project | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [6 empty] | N/A | N/A |  |  | 0 |  |  |  | N/A, project cancelled |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MADERA | C & D STREETS | 30267067 | C ST & D ST, UUD# 12 | 93638 | 6039000800 | Yes | 19.5% | C ST & D ST, CLINTON ST & 6TH ST | None | TBD | TBD | Yes | 9 | 0 | 0 | 0 | 6 | Urban | Yes | 2002-04-17 | 2003-02-22 | 2013-01-11 | 2013-08-02 | 2014 | 2015-01-15 | N/A | 311 | N/A | N/A | 16 | 26 | 0.77 | 1848 | Commercial | Yes |  |  |  | N/A | 1990497.66 | 1.0831 | 2155872.755 | [6 empty] | 34803 | 48% |  |  | 0 |  |  |  | 3rd party cost variance |  |  | 1990497.66 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Yes | Yes | Yes | Yes | No | No | No | Project boundaries within an alley. City installed new decorative streetlighting. Added coordination efforts. Property line issues. | None | N/A | N/A | None | N/A | N/A
MADERA | MADERA YOUTH CENTER | 30675659 | MADERA YOUTH CENTER | 93638 | 6039000900 | Yes | 19.53% | 5TH ST, FLUME ST & HIGH ST | None | Project met one or more Rule 20A criteria | Resolution# 08-208 | Yes | 9 | 0 | 0 | 0 | 6 | Urban | Yes | 2008-08-20 | 2012-10-08 | 2013-09-09 | 2013-11-20 | 2014 | 2015-01-15 | N/A | 1510 | N/A | N/A | 7 | 11 | 0.47 | 1267.2 | Residential | Yes |  |  |  | N/A | 993088.73 | 1.0831 | 1075596.8114 | [6 empty] | 0 | 0% |  |  | 0 | [6 empty] | 993088.73 |  |  |  |  | Yes | 500000 | Madera County | 50.35% | 0 | PG&E does not grant approval for credit transfer transactions. Credit transfers are agreed upon between communities. | No | No | No | No | No | No | No | None | None | N/A | N/A | None | N/A | N/A
MADERA | RULE 20A - OLIVE AVE & M STREET, MADERA | 30222042 | OLIVE AVE & M ST, MADERA | 93637 | 6039000800 | Yes | 19.5% | OLIVE AVE & M ST, MADERA | None | TBD | TBD | Yes | 9 | 0 | 0 | 0 | 6 | Unknown | Yes | TBD | 2001-10-23 | 2002-12-19 | 2004-02-10 | 2005 | 2007-03-24 | N/A | #VALUE! | N/A | N/A |  |  | 1.18 | 4224 | Unknown | Unknown |  |  |  | N/A | 1492305.5444 | 1.7065 | 2546635.3885 | [10 empty] | 0 |  |  |  | Unknown |  |  | 1492305.5444 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
MADERA COUNTY | DISTRICT 4 (FRONT ST. TO 9TH), CHOWCHILLA | 30520215 | CHOWCHILLA, UUD# 4 | 93610 | 6039000300 | No | 22.83% | ROBERTSON RD & KINGS AVE, FRONT ST & NINTH ST | None | Project met one or more Rule 20A criteria | Resolution# 2002-131 | Yes | 9 | 0 | 0 | 0 | 6 | Urban | No | 2003-09-08 | 2008-01-09 | 2008-06-20 | 2011-06-24 | 2013 | 2014-02-28 | N/A | 1584 | N/A | N/A | 26 | 47 | 1.59 | 3907.2 | Residential | Yes |  |  |  | N/A | 3382558 | 1.1048 | 3737063.3145 | [6 empty] | 0 | 0% |  |  | 0 |  |  |  | 3rd party cost variance |  |  | 3382558 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Yes | No | Yes | Yes | Yes | Yes | No | Insufficient allocation. Location-specific challenges. Construction resource issues. | Yes | 0 | 0 | None | N/A | N/A
MADERA COUNTY | MARTIN ST | 30746320 | MARTIN ST | 93637 | 6039000507 | No | 13.95% | MARTIN ST, ROAD 26 & D ST | None | Project met one or more Rule 20A criteria | Resolution# 2009-131 | Yes | 9 | 0 | 0 | 0 | 6 | Suburban | No | 2009-05-19 | 2010-02-02 | 2014-07-28 | 2014-11-12 | 2016 | 2016-07-20 | N/A | 259 | N/A | N/A | 21 | 12 | 1.12 | 4171.2 | Commercial | Yes |  |  |  | N/A | 1533550.22 | 1.0668 | 1636040.3739 | [6 empty] | 0 | N/A |  |  | 0 |  |  |  | Unexpected field conditions |  |  | 1533550.22 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Yes | No | Yes | No | No | No | No | None | None | N/A | N/A | None | N/A | N/A
MADERA COUNTY | OAKHURST RD 427 | 30528244 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | 9 | 0 | 0 | 0 | 6 | N/A | N/A | 2006-08-15 | TBD | TBD | TBD | N/A | 2009-07-29 | N/A | #VALUE! | N/A | 2009-03-18 | N/A | N/A | Cancelled project | Cancelled project | N/A | N/A | N/A | N/A | N/A | N/A | 6256.21 | 1.2297 | 7693.1281 | [6 empty] | N/A | N/A |  |  | 0 |  |  |  | N/A, project cancelled |  |  | 6256.21 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MADERA COUNTY | ROAD 26, MADERA COUNTY | 74001556 | ROAD 26, MADERA COUNTY, UUD# 16 | 93638 | 6039000506 | Yes | 13.47% | ROAD 26, AVENUE 17 & AVENUE 18 | None | Project met one or more Rule 20A criteria | Resolution# 2009-131 | Yes | 9 | 0 | 0 | 0 | 6 | Urban | Yes | 2009-05-19 | 2016-01-24 | 2018-01-29 | 2018-11-27 | 2019 | 2019-11-21 | N/A | 2441 | N/A | N/A | 52 | TBD | 3.6097 | 19059.097 | Commercial | Yes | TBD | TBD | TBD | N/A | 3246486.15 | TBD | 3246486.15 | [6 empty] | TBD | TBD |  |  | 0 |  |  |  | Other |  |  | 3246486.15 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | Yes | Yes | Yes | No | Unknown | Unknown | Easement acquisitions. Re-design due to County requirements provided after project design completed and bid. | None | N/A | N/A | None | N/A | N/A
Madera County Total | [41 empty] | 0
Marin County | [41 empty] | 0
BELVEDERE | MID SAN RAFAEL AVE | 30809002 | MID SAN RAFAEL AVE, BELVEDERE | 94920 | 6041123000 | No | 0.9643% | MID SAN RAFAEL AVE, GOLDEN GATE AVE & LAUREL AVE | None | TBD | Resolution# 2007-18 | Yes | 15 | 5 | 5 | 0 | 8 | Suburban | No | 2007-06-09 | 2010-12-16 | 2011-07-19 | 2012-04-09 | 2013 | 2014-02-28 | N/A | 1286 | N/A | N/A | 9 | 0 | 0.58 | 2587.2 | Residential | Yes |  |  |  | N/A | 463327 | 1.1048 | 511885.4826 | [6 empty] | Unknown | 100% |  |  | 0 | [6 empty] | 463327 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
BELVEDERE | SAN RAFAEL AVE | 30419337 | SAN RAFAEL AVE | 94920 | 6041123000 | No | 0.9643% | SAN RAFAEL AVE | None | TBD | TBD | Yes | 15 | 5 | 5 | 0 | 8 | Suburban | No | 2004-12-13 | 2006-10-03 | 2007-11-05 | 2008-07-24 | 2009 | 2010-03-16 | N/A | 659 | N/A | N/A |  |  | 0.26 | 1267.2 | Residential | Unknown |  |  |  | N/A | 122129 | 1.2297 | 150179.4284 | [6 empty] | 0 | N/A |  |  | 0 | [6 empty] | 122129 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
CORTE MADERA | TAMALPAIS BLVD. | 30185815 | TAMALPAIS BLVD | 94925 | 6041121100 | No | 2.744% | TAMALPAIS BLVD | Part of project in or adjacent to Tier 2 | TBD | TBD | Yes | 15 | 5 | 5 | 0 | 8 | Unknown | No | 2001-04-17 | 2003-09-16 | 2007-05-22 | 2007-12-17 | 2009 | 2009-07-29 | N/A | 882 | N/A | N/A |  |  | 0.96 | 1584 | Unknown | Unknown |  |  |  | N/A | 1231589.52 | 1.2297 | 1514459.3841 | [6 empty] | Unknown | Unknown |  |  | 0 | [6 empty] | 1231589.52 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
FAIRFAX | BANK ST, FAIRFAX | No Order | BANK ST UUD #7 | 94930 | 6041114100 | No | 3.76% | BANK ST & MONO AVE | Tier 3 | Project met one or more Rule 20A criteria | Resolution# 19-28 | No | 15 | 5 | 5 | 0 | 8 | Suburban | No | 2019-07-17 | TBD | TBD | TBD | TBD | N/A | N/A | #VALUE! | 0 | N/A | 0 | 0 | Project not completed or closed | Project not completed or closed | Commercial | Unknown | TBD | TBD | TBD | 700785.69 | N/A | TBD | N/A | [6 empty] | TBD | TBD | [6 empty] | Project in planning phase |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | No | No | None | None | N/A | N/A | No | N/A | N/A
LARKSPUR | DOHERTY DR LARKSPUR R20A | 74013527 | DOHERTY DR, UUD# 2017-01 | 94939 | Unknown | Unknown | Unknown | DOHERTY DR, MAGNOLIA AVE & LUCKY DR | Unknown | Project met one or more Rule 20A criteria | Resolution# 19/17 | No | 15 | 5 | 5 | 0 | 8 | Urban | Unknown | 2017-04-05 | 2018-07-17 | TBD | TBD | TBD | N/A | N/A | 468 | 2020-12-31 | N/A | TBD | TBD | Project not completed or closed | Project not completed or closed | Commercial | Yes | TBD | TBD | TBD | 2072002.95 | N/A | TBD | N/A | [6 empty] | TBD | TBD |  |  | 0 |  |  |  | Project in progress |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Yes | No | No | No | No | Yes | No | Unknown | Unknown | 0 | 0 | 0 | 0 | 0
MARIN COUNTY | NORTH SAN PEDRO | 30185077 | NORTH SAN PEDRO | 94903 | 6041106002 | No | 5.316% | NORTH SAN PEDRO | None | TBD | TBD | Yes | 15 | 5 | 5 | 0 | 8 | Unknown | No | 2001-12-12 | 2002-09-18 | 2004-10-28 | 2007-03-21 | 2009 | 2009-07-29 | N/A | 280 | N/A | N/A |  |  | 2.48 | 7497.6 | Unknown | Unknown |  |  |  | N/A | 4409610.81 | 1.2297 | 5422404.4317 | [6 empty] | Unknown | Unknown |  |  | 0 | [6 empty] | 4409610.81 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
MARIN COUNTY | R20A - ALMEDA DEL PRADO, MA CNTY | 30616113 | ALMEDA DEL PRADO, MARIN COUNTY | 94949 | 6041104200 | No | 4.299% | ALMEDA DEL PRADO, MARIN COUNTY | Part of project in or adjacent to Tier 2 | TBD | TBD | Yes | 15 | 5 | 5 | 0 | 8 | Urban | No | 2007-11-27 | 2008-07-23 | 2009-02-09 | 2009-07-30 | 2010 | 2010-08-26 | N/A | 239 | N/A | N/A | 17 | 27 | 1.08 | 2904 | Residential | Yes |  |  |  | N/A | 1544188 | 1.249 | 1928659.5614 | [6 empty] | 0 | N/A |  |  | 0 | [6 empty] | 1544188 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | No | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
MILL VALLEY | E BLITHEDALE | 30249966 | E BLITHEDALE | 94941 | 6041126100 | No | 1.102% | E BLITHEDALE | Part of project in or adjacent to Tier 3 | TBD | TBD | Yes | 15 | 5 | 5 | 0 | 8 | Unknown | No | 2000-10-16 | 2002-03-20 | 2004-07-26 | 2004-12-23 | 2008 | 2008-08-18 | N/A | 520 | N/A | N/A |  |  | 1.45 | 3009.6 | Unknown | Unknown |  |  |  | N/A | 3000582.66 | 1.3051 | 3916188.8028 | [6 empty] | Unknown | Unknown |  |  | 0 | [6 empty] | 3000582.66 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
NOVATO | NOVATO BLVD, NOVATO | 30899832 | NOVATO BLVD, UUD# 16 | 94947 | 6041103200 | No | 6.35% | NOVATO BLVD, DIABLO AVE & BOULEVARD TERRACE | None | Project met one or more Rule 20A criteria | Resolution# 62-11 | No | 15 | 5 | 5 | 0 | 8 | Unknown | No | 2011-08-23 | 2019-07-15 | TBD | TBD | TBD | N/A | N/A | 2883 | 2020-11-30 | N/A |  |  | Project not completed or closed | Project not completed or closed | Unknown | Unknown | TBD | TBD | TBD | 2870038.06 | N/A | TBD | N/A | [6 empty] | TBD | TBD |  |  | 0 |  |  |  | Project in planning phase |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | Yes | No | No | No | No | No | Issues with City's environmental study and final decision on road improvements | None | N/A | N/A | None | N/A | N/A
ROSS | SIR FRANCIS DRAKE BLVD, ROSS | No Order | SIR FRANCIS DRAKE BLVD - TOWN ADMINISTRATION UUD NO. 1 | 94957 | 6041118100 | No | 0.8725% | SIR FRANCIS DRAKE BLVD BETWEEN PRIOR LAGUNITAS RD & PASSED LAUREL GROVE AVE | Tier 3 | Project met one or more Rule 20A criteria | Resolution# 2118 | No | 15 | 5 | 5 | 0 | 8 | Rural | No | 2019-07-11 | TBD | TBD | TBD | TBD | N/A | N/A | #VALUE! | 0 | N/A | 0 | 0 | Project not completed or closed | Project not completed or closed | Residential | Unknown | TBD | TBD | TBD | 1237411.59 | N/A | TBD | N/A | [6 empty] | TBD | TBD | [6 empty] | Project in planning phase |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | Yes | No | No | Insufficient allocation | None | N/A | N/A | No | N/A | N/A
SAN ANSELMO | GREENFIELD RD | 30615999 | GREENFIELD RD, SAN ANSELMO | 94960 | 6041117000 | No | 3.623% | GREENFIELD RD, LINCOLN PARK & GREENFIELD CT | Part of project in or adjacent to Tier 3 | TBD | TBD | Yes | 15 | 5 | 5 | 0 | 8 | Suburban | No | 2001-09-27 | 2008-06-09 | 2008-08-14 | 2010-02-26 | 2013 | 2014-02-28 | N/A | 2447 | N/A | N/A | 13 | 12 | 0.71 | 2270.4 | Commercial | Yes |  |  |  | N/A | 1468753 | 1.1048 | 1622684.0617 | [6 empty] | 0 | N/A |  |  | 0 | [6 empty] | 1468753 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
SAN RAFAEL | W FRANCISCO BLVD | 30264400 | W FRANCISCO BLVD | 94901 | 6041112100 | No | 6.767% | W FRANCISCO BLVD | None | TBD | TBD | Yes | 15 | 5 | 5 | 0 | 8 | Unknown | No | TBD | TBD | TBD | 2006-09-21 | 2008 | 2008-08-18 | N/A | #VALUE! | N/A | N/A |  |  | 0.47 | 2217.6 | Unknown | Unknown |  |  |  | N/A | 444675.96 | 1.3051 | 580365.6199 | [6 empty] | Unknown | Unknown |  |  | 0 | [6 empty] | 444675.96 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
SAN RAFAEL | FREITAS PARKWAY, SAN RAFAEL | No Order | MANUAL T. FREITAS PARKWAY | 94903 | 6041108200 | No | 5.954% | MANUAL T. FREITAS PARKWAY FROM HWY 101 TO LAS GALLINAS AVE | None | Project met one or more Rule 20A criteria | Resolution# 14710 | No | 15 | 5 | 5 | 0 | 8 | Suburban | No | 2019-07-15 | TBD | TBD | TBD | TBD | N/A | N/A | #VALUE! | 0 | N/A | 0 | 0 | Project not completed or closed | Project not completed or closed | Commercial | Unknown | TBD | TBD | TBD | 4553946.87 | N/A | TBD | N/A | [6 empty] | TBD | TBD | [6 empty] | Project in planning phase |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | Yes | No | No | Insufficient allocation | None | N/A | N/A | No | N/A | N/A
SAUSALITO | R20A - SAN CARLOS, SAUSALITO *CANC*CANC | 30309875 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | 15 | 5 | 5 | 0 | 8 | N/A | N/A | TBD | TBD | TBD | TBD | N/A | 2007-03-24 | N/A | #VALUE! | N/A | 2005-12-21 | N/A | N/A | Cancelled project | Cancelled project | N/A | N/A | N/A | N/A | N/A | N/A | 98446.12 | 1.4306 | 140834.7774 | [6 empty] | N/A | N/A |  |  | 0 |  |  |  | N/A, project cancelled |  |  | 98446.12 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TIBURON | TIBURON BLVD | 31172652 | TIBURON BLVD | 94920 | Unknown | Unknown | Unknown | TIBURON BLVD, LYFORD DR & NED'S WY | Unknown | Project met one or more Rule 20A criteria | Resolution# 16-2014 | No | 15 | 5 | 5 | 0 | 8 | Urban | Unknown | 2014-05-21 | 2016-11-30 | TBD | TBD | TBD | N/A | N/A | 924 | N/A | TBD | N/A | N/A | Cancelled project | Cancelled project | Commercial | Yes | TBD | TBD | TBD | 168936.15 | N/A | TBD | N/A | [6 empty] | TBD | TBD |  |  | 0 |  |  |  | N/A, project cancelled |  |  | N/A |  |  |  |  | Yes | 438080 | Rocklin | N/A | 109520 | PG&E does not grant approval for credit transfer transactions. Credit transfers are agreed upon between communities. | No | Yes | No | Yes | Yes | Yes | No | Unknown | Unknown | 0 | 0 | 0 | 0 | 0
Marin County Total | [41 empty] | 0
Mendocino County | [41 empty] | 0
MENDOCINO COUNTY | *CANC* GUALALA PH2 MENDOCINO CNTY R20A | 30709622 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | 5 | 2 | 2 | 0 | 1 | N/A | N/A | 2007-08-01 | TBD | TBD | TBD | N/A | N/A | N/A | #VALUE! | N/A | 2013-03-04 | N/A | N/A | Cancelled project | Cancelled project | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [6 empty] | N/A | N/A |  |  | 0 |  |  |  | N/A, project cancelled |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MENDOCINO COUNTY | CASPER RULE 20A *CANC | 30264707 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | 5 | 2 | 2 | 0 | 1 | N/A | N/A | TBD | TBD | TBD | TBD | N/A | 2007-03-24 | N/A | #VALUE! | N/A | 2004-12-10 | N/A | N/A | Cancelled project | Cancelled project | N/A | N/A | N/A | N/A | N/A | N/A | 3032.56 | 1.4306 | 4338.3113 | [6 empty] | N/A | N/A |  |  | 0 |  |  |  | N/A, project cancelled |  |  | 3032.56 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MENDOCINO COUNTY | GUALALA, PH 1 | 30172470 | GUALALA, PH 1 | 95445 | 6045011102 | No | 10.86% | GUALALA, PH 1 | Part of project in or adjacent to Tier 2 | TBD | TBD | Yes | 5 | 2 | 2 | 0 | 1 | Suburban | No | TBD | TBD | TBD | 2012-03-30 | 2013 | 2014-02-28 | N/A | #VALUE! | N/A | N/A | 59 | 57 | 2.3 | 4118.4 | Commercial | Yes |  |  |  | N/A | 4067720 | 1.1048 | 4494032.9731 | [6 empty] | 3543 | 100% |  |  | 0 | [6 empty] | 4067720 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
POINT ARENA | SCHOOL ST, POINT ARENA | No Order | SCHOOL ST | 95468 | 6045011102 | No | 10.86% | SCHOOL ST & PASSED LAKE ST | Part of project adjacent to Tier 2 | Project met one or more Rule 20A criteria | Resolution# 2019-19 | No | 5 | 2 | 2 | 0 | 1 | Rural | No | 2019-07-22 | TBD | TBD | TBD | TBD | N/A | N/A | #VALUE! | 0 | N/A | 0 | 0 | Project not completed or closed | Project not completed or closed | Residential | Unknown | TBD | TBD | TBD | 4061766.96 | N/A | TBD | N/A | [6 empty] | TBD | TBD | [6 empty] | Project in planning phase |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | Yes | No | No | Insufficient allocation | None | N/A | N/A | No | N/A | N/A
WILLITS | SNIDER PARK, WILLITS | No Order | SNIDER PARK | 95490 | 6045010700 | No | 17.72% | SNIDER PARK ALONG STATE ST, MARIN ST, HUMBOLDT ST, E. COMMERCIAL ST | Part of project adjacent to Tier 2 | Project met one or more Rule 20A criteria | Resolution# 2019-32 | No | 5 | 2 | 2 | 0 | 1 | Rural | No | 2019-07-24 | TBD | TBD | TBD | TBD | N/A | N/A | #VALUE! | 0 | N/A | 0 | 0 | Project not completed or closed | Project not completed or closed | Residential | Unknown | TBD | TBD | TBD | 2348039.11 | N/A | TBD | N/A | [6 empty] | TBD | TBD | [6 empty] | Project in planning phase |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | Yes | No | No | Insufficient allocation | None | N/A | N/A | No | N/A | N/A
Mendocino County Total | [41 empty] | 0
Merced County | [41 empty] | 0
ATWATER | *CANC* BELLEVUE RD, PHASE 2 ATWATER R20A | 30755274 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | 16 | 3 | 2 | 1 | 8 | N/A | N/A | 2009-04-13 | TBD | TBD | TBD | N/A | N/A | N/A | #VALUE! | N/A | 2015-09-05 | N/A | N/A | Cancelled project | Cancelled project | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [6 empty] | N/A | N/A |  |  | 0 |  |  |  | N/A, project cancelled |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ATWATER | BELLEVUE RD | 30660879 | BELLEVUE RD | 95301 | 6047000603 | No | 17.27% | BELLEVUE RD, REDWOOD RD & LIVINGSTON CANAL | None | TBD | Resolution# 1896-04 | Yes | 16 | 3 | 2 | 1 | 8 | Urban | No | 2004-04-26 | 2009-05-14 | 2012-12-14 | 2013-08-02 | 2014 | 2015-01-15 | N/A | 1844 | N/A | N/A | 27 |  | 1.33 | 4593.6 | Residential | Yes |  |  |  | N/A | 3286906.52 | 1.0831 | 3559990.2261 | [6 empty] | 23202 | 17% |  |  | 0 |  |  |  | 3rd party cost variance |  |  | 3286906.52 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Yes | No | Yes | Yes | No | Yes | No | Easement acquisitions. Construction resource issues. Additional work required due to construction issue. | None | N/A | N/A | None | N/A | N/A
DOS PALOS | BLOSSOM ST, DOS PALOS | No Order | BLOSSOM ST UUD NO. 1 | 93620 | 6047002402 | Yes | 21.57% | BLOSSOM ST | None | Project met one or more Rule 20A criteria | Resolution# 2019-06 | No | 16 | 3 | 2 | 1 | 8 | Rural | Yes | 2019-05-21 | TBD | TBD | TBD | TBD | N/A | N/A | #VALUE! | 0 | N/A | 0 | 0 | Project not completed or closed | Project not completed or closed | Residential | Unknown | TBD | TBD | TBD | 1808696 | N/A | TBD | N/A | [6 empty] | TBD | TBD | [6 empty] | Project in planning phase |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | Yes | No | No | Insufficient allocation | None | N/A | N/A | No | N/A | N/A
LOS BANOS | *CANC* 7TH ST DIST 8 LOS BANOS R20A | 30778320 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | 16 | 3 | 2 | 1 | 8 | N/A | N/A | 2006-08-16 | TBD | TBD | TBD | N/A | N/A | N/A | #VALUE! | N/A | 2014-05-31 | N/A | N/A | Cancelled project | Cancelled project | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [6 empty] | N/A | N/A |  |  | 0 |  |  |  | N/A, project cancelled |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LOS BANOS | *CANC* H ST DIST 7B, LOS BANOS R20A | 30776761 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | 16 | 3 | 2 | 1 | 8 | N/A | N/A | 2006-08-16 | TBD | TBD | TBD | N/A | N/A | N/A | #VALUE! | N/A | 2014-05-31 | N/A | N/A | Cancelled project | Cancelled project | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [6 empty] | N/A | N/A |  |  | 0 |  |  |  | N/A, project cancelled |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LOS BANOS | 7TH STREET, FROM H TO E STREETS | 30488767 | 7TH ST, H ST TO E ST | 93635 | 6047002201 | Yes | 21.86% | 7TH ST, H ST TO E ST | None | TBD | TBD | Yes | 16 | 3 | 2 | 1 | 8 | Urban | Yes | 2004-06-02 | 2005-04-09 | 2006-07-31 | 2006-10-30 | 2007 | 2008-02-15 | N/A | 311 | N/A | N/A |  | 0 | 0.93 | 1848 | commercial | No |  |  |  | N/A | 959318.81 | 1.4306 | 1372379.6435 | [6 empty] | 0 | N/A |  |  | 0 |  |  |  | Labor costs |  |  | 959318.81 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | No | Unknown | None | None | N/A | N/A | None | N/A | N/A
LOS BANOS | DISTRICT 7C, LOS BANOS | 30692635 | DIST 7C, LOS BANOS | 93635 | Unknown | Unknown | Unknown | H ST, 2ND ST & 7TH ST | Unknown | Project met one or more Rule 20A criteria | Resolution# 4765 | No | 16 | 3 | 2 | 1 | 8 | Urban | Unknown | 2006-08-16 | 2015-12-01 | TBD | TBD | N/A | 2018-10-23 | N/A | 3394 | N/A | 2018-08-22 | TBD | TBD | Cancelled project | Cancelled project | Commercial | No | TBD | TBD | TBD | N/A | 207191.51 | TBD | 207191.51 | [6 empty] | TBD | TBD |  |  | 0 |  |  |  | N/A, project cancelled |  |  | 207191.51 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | Yes | No | No | Insufficient allocation | None | N/A | N/A | None | N/A | N/A
LOS BANOS | EP 7TH ST. FROM H ST TO E ST, *CANC*CANC | 30488766 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | 16 | 3 | 2 | 1 | 8 | N/A | N/A | 2004-06-02 | TBD | TBD | TBD | N/A | N/A | N/A | #VALUE! | N/A | 2006-02-15 | N/A | N/A | Cancelled project | Cancelled project | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [6 empty] | N/A | N/A |  |  | 0 |  |  |  | N/A, project cancelled |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LOS BANOS | EP HENRY MILLER PLAZA RULE 20A PH 1,LB | 30421025 | HENRY MILLER PLAZA PH 1, LOS BANOS | 93635 | 6047002201 | Yes | 21.86% | HENRY MILLER PLAZA PH 1, LOS BANOS | None | TBD | TBD | Yes | 16 | 3 | 2 | 1 | 8 | Unknown | Yes | 2004-06-02 | 2005-01-19 | 2005-06-09 | 2005-08-15 | 2006 | 2007-03-24 | N/A | 231 | N/A | N/A |  |  | 0.15 | 1214.4 | Unknown | Unknown |  |  |  | N/A | 131963.7 | 1.591 | 209949.7681 | [10 empty] | 0 |  |  |  | Unknown |  |  | 131963.7 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
MERCED | BRADLEY OVERPASS HWY 140 | 30492230 | BRADLEY OVERPASS HWY 140 | 95340 | 6047001401 | Yes | 21.5% | BRADLEY OVERPASS HWY 140 | None | TBD | TBD | Yes | 16 | 3 | 2 | 1 | 8 | Urban | Yes | 2005-06-22 | 2006-03-13 | 2009-05-29 | 2011-06-17 | 2013 | 2014-02-28 | N/A | 264 | N/A | N/A | 13 | 3 | 0.82 | 3168 | Commercial | No |  |  |  | N/A | 2167700 | 1.1048 | 2394883.4423 | [6 empty] | 9678 | 67% |  |  | 0 |  |  |  | Restrictive work conditions |  |  | 2167700 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Yes | Yes | No | Unknown | No | Yes | No | Caltrans design changes | None | N/A | N/A | None | N/A | N/A
MERCED | C:GEP RULE 20A YOSEMITE PKWY,MERCED | 30140609 | YOSEMITE PKWY, MERCED | 95341 | 6047001700 | Yes | 16.75% | YOSEMITE PKWY, MERCED | None | TBD | TBD | Yes | 16 | 3 | 2 | 1 | 8 | Unknown | Yes | TBD | 2000-06-19 | 2001-05-03 | 2002-02-22 | 2006 | 2007-03-24 | N/A | #VALUE! | N/A | N/A |  |  | 1.81 | 4963.2 | Unknown | Unknown |  |  |  | N/A | 1510567.83 | 1.591 | 2403262.1522 | [10 empty] | 0 |  |  |  | Unknown |  |  | 1510567.83 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
MERCED | PARSONS AVE | 30835217 | PARSONS AVE, PH 1, UUD# 11 | 95340 | 6047001700 | Yes | 16.75% | PARSONS AVE, E CHILDS RD & MERCED AVE | None | TBD | Resolution# 2010-92 | Yes | 16 | 3 | 2 | 1 | 8 | Urban | Yes | 2010-10-19 | 2011-04-14 | 2014-12-02 | 2015-05-08 | 2015 | 2016-01-13 | N/A | 177 | N/A | N/A | 17 | 6 | 0.74 | 1795.2 | Residential | Yes |  |  |  | N/A | 1569890 | 1.0677 | 1676207.9177 | [6 empty] | 0 | N/A |  |  | 0 |  |  |  | Other |  |  | 1569890 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Yes | Yes | Yes | Yes | Yes | No | No | Insufficient allocation | None | N/A | N/A | None | N/A | N/A
MERCED COUNTY | DAN WARD RD, MERCED COUNTY | 74003380 | DAN WARD RD, MERCED COUNTY | 95348 | Unknown | Unknown | Unknown | DAN WARD RD, FRANKLIN RD & BEACHWOOD DR | Unknown | Project met one or more Rule 20A criteria | Resolution# 2015-13 | No | 16 | 3 | 2 | 1 | 8 | Unknown | Unknown | 2015-03-03 | TBD | TBD | TBD | TBD | N/A | N/A | #VALUE! | 2020-12-31 | N/A |  |  | Project not completed or closed | Project not completed or closed | Unknown | Unknown | TBD | TBD | TBD | 4562906.64 | N/A | TBD | N/A | [6 empty] | TBD | TBD |  |  | 0 |  |  |  | Project in planning phase |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | Yes | No | Unknown | Insufficient allocation | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
MERCED COUNTY | LOBO AVE, MERCED COUNTY | 74001558 | LOBO AVE, UUD# 11 | 95341 | Unknown | Unknown | Unknown | LOBO AVE, SUNRISE AVE & DRAKE AVE | Unknown | Project met one or more Rule 20A criteria | Resolution# 2014-98 | No | 16 | 3 | 2 | 1 | 8 | Suburban | Unknown | 2014-10-07 | 2016-05-11 | 2019-06-03 | TBD | TBD | N/A | N/A | 582 | 2019-07-31 | N/A | TBD | TBD | Project not completed or closed | Project not completed or closed | Residential | Yes | TBD | TBD | TBD | 4808557.66 | N/A | TBD | N/A | [6 empty] | TBD | TBD |  |  | 0 |  |  |  | Unexpected field conditions |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Yes | Yes | Yes | Yes | No | Yes | Yes | Easement acquisitions. Inaccurate and outdated road widening plans. | None | N/A | N/A | None | N/A | N/A
MERCED COUNTY | SUTTER HOSPITAL | 30317644 | SUTTER HOSPITAL | 95340 | 6047001601 | Yes | 17.1% | SUTTER HOSPITAL | None | TBD | TBD | Yes | 16 | 3 | 2 | 1 | 8 | Urban | Yes | 2000-10-30 | 2003-05-15 | 2009-06-26 | 2010-03-24 | 2012 | 2012-09-13 | N/A | 927 | N/A | N/A | 33 | 1 | 1.45 | 4540.8 | Residential | No |  |  |  | N/A | 2026094.22 | 1.121 | 2271335.2843 | [6 empty] | 8477 | 100% |  |  | 0 |  |  |  | Unexpected field conditions |  |  | 2026094.22 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Yes | Yes | Unknown | Yes | No | Yes | No | Delay in AT&T paying invoice for actual Joint Trench Costs | None | N/A | N/A | None | N/A | N/A
MERCED COUNTY | WALNUT AVE, WINTON | 30616106 | WALNUT AVE, WINTON | 95388 | 6047000504 | Yes | 19.55% | WALNUT AVE, CALIFORNIA ST & SANTA FE DR | None | Project met one or more Rule 20A criteria | Resolution# 2006-93 | Yes | 16 | 3 | 2 | 1 | 8 | Urban | Yes | 2006-06-15 | 2013-07-15 | 2015-07-20 | 2016-01-26 | 2017 | 2017-04-14 | N/A | 2587 | N/A | N/A | 46 | 68 | 1.74 | 3854.4 | Commercial | Yes |  |  |  | N/A | 4247347.82 | 1.048 | 4451407.1776 | [6 empty] | 0 | 0% |  |  | 0 |  |  |  | 3rd party cost variance |  |  | 4247347.82 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Yes | No | No | Yes | No | No | No | Customer service conversion issues | None | N/A | N/A | None | N/A | N/A
Merced County Total | [41 empty] | 0
Monterey County | [41 empty] | 0
GREENFIELD | EL CAMINO REAL, GREENFIELD | No Order | EL CAMINO REAL | 93927 | 6053011204 | No | 17.9% | EL CAMINO REAL BETWEEN THORNE RD & CHERRY AVE | None | Project met one or more Rule 20A criteria | Resolution# 2019-77 | No | 16 | 7 | 7 | 0 | 7 | Suburban | No | 2019-07-23 | TBD | TBD | TBD | TBD | N/A | N/A | #VALUE! | 0 | N/A | 0 | 0 | Project not completed or closed | Project not completed or closed | Commercial | Unknown | TBD | TBD | TBD | 2326381.53 | N/A | TBD | N/A | [6 empty] | TBD | TBD | [6 empty] | Project in planning phase |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | Yes | No | No | Insufficient allocation | None | N/A | N/A | No | N/A | N/A
KING CITY | C:EP 20 A BROADWAY/ 2ND ST-KC *CANC | 30105758 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | 16 | 7 | 7 | 0 | 7 | N/A | N/A | TBD | TBD | TBD | TBD | N/A | 2007-03-24 | N/A | #VALUE! | N/A | 2005-09-15 | N/A | N/A | Cancelled project | Cancelled project | N/A | N/A | N/A | N/A | N/A | N/A | 7622.96 | 1.4306 | 10905.233 | [6 empty] | N/A | N/A |  |  | 0 |  |  |  | N/A, project cancelled |  |  | 7622.96 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MARINA | RESERVATION RD, MARINA | 30649669 | RESERVATION RD, UUD# 2008-1 | 93933 | Unknown | Unknown | Unknown | RESERVATION RD, DE FOREST AVE & CALIFORNIA AVE | Unknown | Project met one or more Rule 20A criteria | Resolution# 2008-69 | No | 16 | 7 | 7 | 0 | 7 | Unknown | Unknown | 2008-04-01 | TBD | TBD | TBD | TBD | N/A | N/A | #VALUE! | 2020-02-02 | N/A |  |  | Project not completed or closed | Project not completed or closed | Unknown | Unknown | TBD | TBD | TBD | 3117784.39 | N/A | TBD | N/A | [6 empty] | TBD | TBD |  |  | 0 |  |  |  | Project in planning phase |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | Yes | No | No | No | No | No | Unknown | None | N/A | N/A | None | N/A | N/A
MONTEREY | *CANC* DEL MONTE AVE | 30098410 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | 16 | 7 | 7 | 0 | 7 | N/A | N/A | 2000-06-06 | TBD | TBD | TBD | N/A | 2016-10-19 | N/A | #VALUE! | N/A | 2016-08-03 | N/A | N/A | Cancelled project | Cancelled project | N/A | N/A | N/A | N/A | N/A | N/A | 94618.84 | 1.0668 | 100942.4017 | [6 empty] | N/A | N/A |  |  | 0 |  |  |  | N/A, project cancelled |  |  | 94618.84 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MONTEREY COUNTY | C: CV RD RULE 20A SUBSTRUCTURE ONLY | 30244030 | CARMEL VALLEY RD | TBD | Unknown | Unknown | Unknown | CARMEL VALLEY RD | Unknown | TBD | TBD | Yes | 16 | 7 | 7 | 0 | 7 | Unknown | Unknown | TBD | 2002-02-19 | 2002-06-05 | 2004-03-11 | 2006 | 2007-03-24 | N/A | #VALUE! | N/A | N/A |  |  | No primary UG circuit data found | 0 | Unknown | Unknown |  |  |  | N/A | 194765.92 | 1.591 | 309865.9688 | [10 empty] | 0 |  |  |  | Unknown |  |  | 194765.92 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
MONTEREY COUNTY | CARMEL VALLEY RD PH 2, MONTEREY COUNTY | No Order | CARMEL VALLEY AREA, UUD# 15 | 93923 | Unknown | Unknown | Unknown | CARMEL VALLEY RD, PILOT RD & OAK MEADOW LN | Unknown | Project met one or more Rule 20A criteria | Resolution# 13-055 | No | 16 | 7 | 7 | 0 | 7 | Unknown | Unknown | 2013-07-30 | TBD | TBD | TBD | TBD | N/A | N/A | #VALUE! | TBD | N/A |  |  | Project not completed or closed | Project not completed or closed | Unknown | Unknown | TBD | TBD | TBD | 19304129 | N/A | TBD | N/A | [6 empty] | TBD | TBD |  |  | 0 |  |  |  | Project in planning phase |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | Yes | Yes | No | No | No | No | Unknown | None | N/A | N/A | None | N/A | N/A
MONTEREY COUNTY | CARMEL VALLEY RD, CARMEL-BY-THE-SEA | 30075639 | CARMEL VALLEY RD, CARMEL-BY-THE-SEA | 93923 | 6053011602 | No | 1.557% | CARMEL VALLEY RD, CARMEL-BY-THE-SEA | Tier 2 | TBD | TBD | Yes | 16 | 7 | 7 | 0 | 7 | Unknown | No | 1996-04-06 | 1999-05-12 | 1999-08-13 | 2003-10-22 | 2007 | 2008-02-15 | N/A | 1131 | N/A | N/A |  |  | 2.16 | 8923.2 | Unknown | Unknown |  |  |  | N/A | 1707828.55 | 1.4306 | 2443180.6321 | [10 empty] | 0 |  |  |  | Unknown |  |  | 1707828.55 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
MONTEREY COUNTY | MOSS LANDING, MONTEREY COUNTY | 74004303 | MOSS LANDING RD, MONTEREY COUNTY | 95039 | Unknown | Unknown | Unknown | MOSS LANDING RD, POTRERO RD & SANDHOLDT RD | Unknown | Project met one or more Rule 20A criteria | Resolution# 05-120 | No | 16 | 7 | 7 | 0 | 7 | Suburban | Unknown | 2005-06-07 | 2010-01-15 | 2019-05-15 | TBD | TBD | N/A | N/A | 1683 | 2020-03-30 | N/A | TBD | TBD | Project not completed or closed | Project not completed or closed | Commercial | Yes | TBD | TBD | TBD | 5984263.31 | N/A | TBD | N/A | [6 empty] | TBD | TBD |  |  | 0 |  |  |  | Project in progress |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Yes | Yes | Yes | Yes | No | Yes | Unknown | Easement acquisitions. Design issues. Joint Trench. Removing poles. | None | N/A | N/A | None | N/A | N/A
PACIFIC GROVE | LOWER FOREST AVE | 30233278 | LOWER FOREST AVE | 93950 | 6053012401 | No | 6.599% | LOWER FOREST AVE | None | TBD | TBD | Yes | 16 | 7 | 7 | 0 | 7 | Unknown | No | 1999-08-04 | 2003-03-31 | 2003-08-01 | 2005-05-11 | 2008 | 2008-08-18 | N/A | 1335 | N/A | N/A |  |  | 0.42 | 2059.2 | Unknown | Unknown |  |  |  | N/A | 751389.03 | 1.3051 | 980669.9695 | [10 empty] | 0 |  |  |  | Unknown |  |  | 751389.03 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
PACIFIC GROVE | CENTRAL AVE DISTRICT, PACIFIC GROVE | No Order | CENTRAL AVE | 93950 | 6053012401 | No | 6.54% | CENTRAL AVE BETWEEN 2ND ST AND FOUNTAIN AVE | None | Project met one or more Rule 20A criteria | Resolution# 19-022 | No | 16 | 7 | 7 | 0 | 7 | Rural | No | 2019-07-17 | TBD | TBD | TBD | TBD | N/A | N/A | #VALUE! | 0 | N/A | 0 | 0 | Project not completed or closed | Project not completed or closed | Residential | Unknown | TBD | TBD | TBD | 3144489.6 | N/A | TBD | N/A | [6 empty] | TBD | TBD | [6 empty] | Project in planning phase |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | Yes | No | No | Insufficient allocation | None | N/A | N/A | No | N/A | N/A
SALINAS | E. MARKET PH1, SALINAS | 30393476 | E MARKET ST PH 1 | 93905 | 6053000501 | No | 16.27% | E MARKET ST, POPLAR ST & W HWY 101 | None | Project met one or more Rule 20A criteria | Ordinance# 2432, Resolution# 18597 & 18598 | Yes | 16 | 7 | 7 | 0 | 7 | Unknown | No | 2004-07-20 | 2008-04-08 | 2009-08-24 | 2011-10-13 | 2018 | 2019-02-19 | N/A | 1358 | N/A | N/A |  |  | 3.7873 | 19997.0829 | Unknown | Unknown |  |  |  | N/A | 4057060.88 | TBD | 4057060.88 | [10 empty] | 0 | [6 empty] | 4057060.88 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
SALINAS | E. MARKET PH2, SALINAS | 30616115 | E MARKET ST PH 2 | 93901 | 6053001802 | No | 12.47% | E MARKET ST, W HWY 101 & SHERWOOD | None | Project met one or more Rule 20A criteria | Resolution# 18597 & 18598 | Yes | 16 | 7 | 7 | 0 | 7 | Unknown | No | 2004-07-20 | 2008-10-21 | 2012-08-28 | 2013-03-06 | 2018 | 2018-04-30 | N/A | 1554 | N/A | N/A | 15 |  | 1.6911 | 8929.2692 | Unknown | Unknown |  |  |  | N/A | 2703867.16 | TBD | 2703867.16 | [10 empty] | 0 | [6 empty] | 2703867.16 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
SALINAS | EAST ALISAL RULE 20-A-SALINAS | 30142636 | EAST ALISAL, SALINAS | 93901 | 6053014500 | Yes | 9.909% | EAST ALISAL, SALINAS | None | TBD | TBD | Yes | 16 | 7 | 7 | 0 | 7 | Unknown | Yes | TBD | 2000-06-21 | 2001-10-18 | 2003-05-30 | 2005 | 2007-03-24 | N/A | #VALUE! | N/A | N/A |  |  | 0.72 | 2640 | Unknown | Unknown |  |  |  | N/A | 917800.11 | 1.7065 | 1566235.7139 | [10 empty] | 0 |  |  |  | Unknown |  |  | 917800.11 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
SALINAS | WILLIAMS RD PH 1, SALINAS | No Order | WILLIAMS RD, PH 1, UUD# 24 | 93905 | Unknown | Unknown | Unknown | WILLIAMS RD, ALISAL ST & BARDIN RD | Unknown | Project met one or more Rule 20A criteria | Resolution# 20387, Ordinance# 2539 | No | 16 | 7 | 7 | 0 | 7 | Unknown | Unknown | 2013-06-04 | TBD | TBD | TBD | TBD | N/A | N/A | #VALUE! | TBD | N/A |  |  | Project not completed or closed | Project not completed or closed | Unknown | Unknown | TBD | TBD | TBD | 4198841.33 | N/A | TBD | N/A | [6 empty] | TBD | TBD |  |  | 0 |  |  |  | Project in planning phase |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | Yes | No | No | No | No | No | Unknown | None | N/A | N/A | None | N/A | N/A
SAND CITY | UUD #1, SAND CITY | No Order | SAND CITY UNDERGROUND DISTRICT NO. 1 | 93955 | 6053014000 | No | 10.73% | CALIFORNIA AVE BETWEEN HICKORY ST AND ORLAND ST | None | Project met one or more Rule 20A criteria | Resolution# 189 (1975) | No | 16 | 7 | 7 | 0 | 7 | Rural | No | 1975-06-17 | TBD | TBD | TBD | TBD | N/A | N/A | #VALUE! | 0 | N/A | 0 | 0 | Project not completed or closed | Project not completed or closed | Residential | Unknown | TBD | TBD | TBD | 1851638.96 | N/A | TBD | N/A | [6 empty] | TBD | TBD | [6 empty] | Project in planning phase |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | Yes | No | No | Insufficient allocation | None | N/A | N/A | No | N/A | N/A
SEASIDE | UPPER BROADWAY | 30072595 | UPPER BROADWAY | 93955 | 6053013700 | No | 11.38% | UPPER BROADWAY | None | TBD | TBD | Yes | 16 | 7 | 7 | 0 | 7 | Unknown | No | 1989-04-06 | 2002-07-08 | 2010-02-11 | 2011-03-17 | 2012 | 2013-01-25 | N/A | 4841 | N/A | N/A |  |  | 0.64 | 2428.8 | Unknown | Unknown |  |  |  | N/A | 2678450 | 1.121 | 3002653.0515 | [10 empty] | 0 |  |  |  | Unknown |  |  | 2678450 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
Monterey County Total | [41 empty] | 0
Napa County | [41 empty] | 0
AMERICAN CANYON | GREEN ISLAND DR, AMERICAN CANYON | 31363065 | GREEN ISLAND DR | 94503 | Unknown | Unknown | Unknown | GREEN ISLAND DR, COMMERCE BLVD & PAOLI LOOP | Unknown | Project met one or more Rule 20A criteria | Resolution# 2017-69 | No | 5 | 3 | 3 | 0 | 2 | Suburban | Unknown | 2017-09-05 | 2017-12-14 | TBD | TBD | TBD | N/A | N/A | 100 | 2019-09-03 | N/A | TBD | TBD | Project not completed or closed | Project not completed or closed | Commercial | Unknown | TBD | TBD | TBD | 262380.44 | N/A | TBD | N/A | [6 empty] | 0 | N/A |  |  | 0 |  |  |  | Project in progress |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | Yes | Unknown | Yes | No | Unknown | Unknown |  | Unknown | 0 | 0 | Unknown | 0 | 0
NAPA | JEFFERSON ST, NAPA | 74003533 | JEFFERSON ST | 94558 | Unknown | Unknown | Unknown | JEFFERSON ST, LINCOLN AVE & TRANCAS ST | Unknown | Project met one or more Rule 20A criteria | Resolution# 2014-80 | No | 5 | 3 | 3 | 0 | 2 | Urban | Unknown | 2014-05-06 | 2016-02-10 | TBD | TBD | TBD | N/A | N/A | 645 | 2019-10-28 | N/A | TBD | TBD | Project not completed or closed | Project not completed or closed | Commercial | No | TBD | TBD | TBD | 5166907.54 | N/A | TBD | N/A | [6 empty] | TBD | TBD |  |  | 0 |  |  |  | Project in progress |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | Yes | Yes | No | No | Unknown | No |  | None | N/A | N/A | None | N/A | N/A
NAPA COUNTY | EP 1ST&2ND ST, NAPA RULE 20A | 30219331 | 1ST ST & 2ND ST, NAPA | 94559 | 6055200201 | No | 8.829% | 1ST ST & 2ND ST, NAPA | None | TBD | TBD | Yes | 5 | 3 | 3 | 0 | 2 | Urban | No | 2000-12-01 | 2005-03-23 | 2007-04-02 | 2008-08-01 | 2010 | 2010-08-26 | N/A | 1573 | N/A | N/A | 59 | 108 | 1.7 | 4276.8 | Residential | Yes |  |  |  | N/A | 3008083 | 1.249 | 3757034.7908 | [6 empty] | Unknown | Unknown |  |  | 0 | [6 empty] | 3008083 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
NAPA COUNTY, ST HELENA | HIGHWAY 29 | 30185719 | HWY 29, UUD# 7 | 94574 | 6055201500 | Yes | 2.784% | HWY 29, GALLERON DR & SULPHUR SPRINGS CREEK | None | TBD | Resolution# 2006-55 | Yes | 5 | 3 | 3 | 0 | 2 | Suburban | Yes | 2006-04-25 | 2010-03-27 | 2012-04-25 | 2013-10-02 | 2015 | 2015-07-14 | N/A | 1432 | N/A | N/A | 181 | 86 | 7.41 | 24552 | Commercial | Yes |  |  |  | N/A | 17048835.58 | 1.0677 | 18203436.6653 | [6 empty] | 57250 | 100% |  |  | 0 | [6 empty] | 17048835.58 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
YOUNTVILLE | YOUNTVILLE PARK, YOUNTVILLE | No Order | YOUNTVILLE PARK UNDERGROUND UTILITY ZONE | 94599 | 6055201300 | No | 3.375% | YOUNTVILLE PARK BETWEEN YOUNT MILL RD & PASSED WASHINGTON ST | None | Project met one or more Rule 20A criteria | Resolution# 19-3560 | No | 5 | 3 | 3 | 0 | 2 | Rural | No | 2019-06-04 | TBD | TBD | TBD | TBD | N/A | N/A | #VALUE! | 0 | N/A | 0 | 0 | Project not completed or closed | Project not completed or closed | Residential | Unknown | TBD | TBD | TBD | 1571431.98 | N/A | TBD | N/A | [6 empty] | TBD | TBD | [6 empty] | Project in planning phase |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | Yes | No | No | Insufficient allocation | None | N/A | N/A | No | N/A | N/A
Napa County Total | [41 empty] | 0
Nevada County | [41 empty] | 0
GRASS VALLEY | EAST MAIN ST, GRASS VALLEY | No Order | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | 6 | 3 | 2 | 1 | 2 | N/A | N/A | 1998-04-28 | TBD | TBD | TBD | TBD | N/A | N/A | #VALUE! | N/A | TBD | N/A | N/A | Cancelled project | Cancelled project | N/A | N/A | N/A | N/A | N/A | N/A | N/A | TBD | N/A | [6 empty] | N/A | N/A |  |  | 0 |  |  |  | N/A, project cancelled |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GRASS VALLEY | GEP MILL ST RULE 20A GRASS VALLEY | 30169003 | MILL ST, GRASS VALLEY | 95945 | 6057000502 | No | 14.75% | MILL ST, GRASS VALLEY | None | TBD | TBD | Yes | 6 | 3 | 2 | 1 | 2 | Suburban | No | TBD | 2000-11-01 | 2001-07-23 | 2003-03-06 | 2005 | 2007-03-24 | N/A | #VALUE! | N/A | N/A |  |  | 1.4 | 3379.2 | Residential | Unknown |  |  |  | N/A | 970238.61 | 1.7065 | 1655722.5756 | [6 empty] | Unknown | Unknown |  |  | 0 | [6 empty] | 970238.61 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
GRASS VALLEY | E. MAIN ST, GRASS VALLEY | No Order | E MAIN ST | 95945 | 6057000501 | Unknown | Unknown | E MAIN ST BETWEEN RICHARDSON ST & PASSED EUREKA ST | Part of project adjacent to Tier 2 | Project met one or more Rule 20A criteria | Resolution# 2019-30 | No | 6 | 3 | 2 | 1 | 2 | Suburban | Unknown | 2019-06-11 | TBD | TBD | TBD | TBD | N/A | N/A | #VALUE! | 0 | N/A | 0 | 0 | Project not completed or closed | Project not completed or closed | Commercial | Unknown | TBD | TBD | TBD | 2071110 | N/A | TBD | N/A | [6 empty] | TBD | TBD | [6 empty] | Project in planning phase |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | Yes | No | No | Insufficient allocation | None | N/A | N/A | No | N/A | N/A
NEVADA CITY | BROAD ST NEVADA CITY R20A | 74013926 | BROAD ST | 95959 | Unknown | Unknown | Unknown | BROAD ST, COTTAGE ST & BENNETS RD | Unknown | Project met one or more Rule 20A criteria | Resolution# 2017-44 | No | 6 | 3 | 2 | 1 | 2 | Rural | Unknown | 2017-06-28 | 2017-10-02 | TBD | TBD | TBD | N/A | N/A | 96 | 2019-12-27 | N/A | TBD | TBD | Project not completed or closed | Project not completed or closed | Residential | No | TBD | TBD | TBD | 1704939.48 | N/A | TBD | N/A | [6 empty] | TBD | TBD |  |  | 0 |  |  |  | Project in progress |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | Yes | No | No | Insufficient allocation. Project costs higher than expected. | TBD | TBD | TBD | TBD | TBD | TBD
NEVADA COUNTY | COMBIE RD PHASE II | 30027068 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | 6 | 3 | 2 | 1 | 2 | N/A | N/A | 1996-04-03 | TBD | TBD | TBD | N/A | 2007-07-31 | N/A | #VALUE! | N/A | 2007-02-07 | N/A | N/A | Cancelled project | Cancelled project | N/A | N/A | N/A | N/A | N/A | N/A | 88884.27 | 1.4306 | 127155.8125 | [6 empty] | N/A | N/A |  |  | 0 |  |  |  | N/A, project cancelled |  |  | 88884.27 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NEVADA COUNTY | COMBIE RD PH2, NEVADA CNTY | 30616100 | COMBIE RD PH 2 | 95949 | 6057000103 | No | 5.473% | COMBIE RD, WEST HACIENDA DR | Part of project in or adjacent to Tier 2 | Project met one or more Rule 20A criteria | Resolution# 96-154 | Yes | 6 | 3 | 2 | 1 | 2 | Unknown | No | 1996-04-03 | 2012-12-06 | 2015-08-10 | 2015-11-16 | 2017 | 2017-10-13 | N/A | 6091 | N/A | N/A |  |  | 1.49 | 4276.8 | Unknown | Unknown |  |  |  | N/A | 2938685.84 | 1.048 | 3079871.9095 | [10 empty] | 0 |  |  |  | Unknown |  |  | 2938685.84 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
NEVADA COUNTY | COMBIE RD/MAGNOLIA RD PH 3A, NEVADA COUNTY | 31144652 | COMBIE RD PH 3A | 95602 | Unknown | Unknown | Unknown | COMBIE RD, HWY 49 & COMBIE RD | Unknown | Project met one or more Rule 20A criteria | Resolution# 14-455 | No | 6 | 3 | 2 | 1 | 2 | Suburban | Unknown | 2014-09-16 | 2015-06-22 | 2019-04-08 | 2019-05-31 | TBD | N/A | N/A | 279 | 2019-09-18 | N/A | 12 | TBD | Project not completed or closed | Project not completed or closed | Residential | Yes | TBD | TBD | TBD | 1901595.89 | N/A | TBD | N/A | [6 empty] | TBD | TBD |  |  | 0 |  |  |  | 3rd party cost variance |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Yes | Yes | No | No | No | Yes | Unknown | Easement acquisitions. County design delays. | None | N/A | N/A | None | N/A | N/A
Nevada County Total | [41 empty] | 0
Placer County | [41 empty] | 0
AUBURN | LINCOLN WY & HIGH ST | 30642311 | LINCOLN WY & HIGH ST | 95603 | 6061020401 | No | 14.04% | LINCOLN WY & HIGH ST, LEWIS ST & LINDEN WY | None | TBD | Resolution# 08-53 | Yes | 11 | 2 | 2 | 0 | 4 | Unknown | No | 2008-04-28 | 2008-09-16 | 2009-07-31 | 2009-12-29 | 2015 | 2015-07-14 | N/A | 141 | N/A | N/A |  |  | 0.4 | 1320 | Unknown | Unknown |  |  |  | N/A | 1544684.4 | 1.0677 | 1649295.3147 | [10 empty] | 0 |  |  |  | Unknown |  |  | 1544684.4 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
COLFAX | *CANC* MAIN ST | 31138035 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | 11 | 2 | 2 | 0 | 4 | N/A | N/A | 2014-08-13 | TBD | TBD | TBD | N/A | 2015-10-06 | N/A | #VALUE! | N/A | 2015-09-11 | N/A | N/A | Cancelled project | Cancelled project | N/A | N/A | N/A | N/A | N/A | N/A | 6534.83 | 1.0677 | 6977.3894 | [6 empty] | N/A | N/A |  |  | 0 |  |  |  | N/A, project cancelled |  |  | 6534.83 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LINCOLN | CIVIC CENTER PLAZA, LINCOLN | 74015721 | CIVIC CENTER PLAZA | 95649 | Unknown | Unknown | Unknown | ALLEY BETWEEN 5TH ST & 6TH ST, LINCOLN BLVD | Unknown | Project met one or more Rule 20A criteria | Resolution# 2017-217 | No | 11 | 2 | 2 | 0 | 4 | Suburban | Unknown | 2017-09-26 | 2018-05-21 | TBD | TBD | TBD | N/A | N/A | 237 | 2020-02-28 | N/A | TBD | TBD | Project not completed or closed | Project not completed or closed | Commercial | Unknown | TBD | TBD | TBD | 1572102.99 | N/A | TBD | N/A | [6 empty] | TBD | TBD |  |  | 0 |  |  |  | Project in progress |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | Yes | No | Unknown | Unknown | Unknown | Unknown | TBD | TBD | TBD | TBD | TBD | TBD
LOOMIS | SIERRA COLLEGE, LOOMIS | No Order | SIERRA COLLEGE BLVD, LOOMIS | 95650 | 6061021203 | No | 5.737% | SIERRA COLLEGE BLVD, BRACE RD & GRANITE DR | None | Project met one or more Rule 20A criteria | Resolution# 17-34 | No | 11 | 2 | 2 | 0 | 4 | Unknown | No | 2017-12-12 | 2018-05-22 | TBD | TBD | TBD | N/A | N/A | 161 | TBD | N/A |  |  | Project not completed or closed | Project not completed or closed |  | Unknown |  |  |  | 813851.42 | N/A | TBD | N/A | [10 empty] | 0 | [6 empty] | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | Yes | Unknown | Unknown | Unknown | Yes | Unknown | Easement acquisitions | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
PLACER COUNTY | BOWMAN RD PH1 AUBURN PLACER CNTY R20A | 30817978 | N/A | N/A | 6061021502 | No | 8.638% | N/A | Part of project in or adjacent to Tier 2 | N/A | N/A | No | 11 | 2 | 2 | 0 | 4 | N/A | No | 1998-12-01 | TBD | TBD | TBD | N/A | N/A | N/A | #VALUE! | N/A | 2015-09-05 | N/A | N/A | Cancelled project | Cancelled project | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [6 empty] | N/A | N/A |  |  | 0 |  |  |  | N/A, project cancelled |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PLACER COUNTY | BOWMAN RD PH2 AUBURN PLACER CNTY R20A | 30837081 | N/A | N/A | 6061021502 | No | 8.638% | N/A | None | N/A | N/A | No | 11 | 2 | 2 | 0 | 4 | N/A | No | 1998-12-01 | TBD | TBD | TBD | N/A | N/A | N/A | #VALUE! | N/A | 2015-09-05 | N/A | N/A | Cancelled project | Cancelled project | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [6 empty] | N/A | N/A |  |  | 0 |  |  |  | N/A, project cancelled |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PLACER COUNTY | HIGHWAY 49 - PAC BELL LEAD | 30170818 | HWY 49 | 95603 | 6061021501 | No | 6.64% | HWY 49 | None | TBD | TBD | Yes | 11 | 2 | 2 | 0 | 4 | Unknown | No | 2000-12-19 | 2003-03-21 | 2010-01-07 | 2010-12-14 | 2013 | 2014-02-28 | N/A | 822 | N/A | N/A |  |  | 1.85 | 5385.6 | Unknown | Unknown |  |  |  | N/A | 2761892 | 1.1048 | 3051349.089 | [10 empty] | 0 |  |  |  | Unknown |  |  | 2761892 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
PLACER COUNTY | HWY 49 - PG&E LEAD | 30170714 | HWY 49 | 95603 | 6061021802 | No | 8.51% | HWY 49, COTTAGE DR & BELL RD | None | Project met one or more Rule 20A criteria | Resolution# 2000-298 | Yes | 11 | 2 | 2 | 0 | 4 | Unknown | No | 2000-12-19 | 2002-10-09 | 2004-11-23 | 2013-12-05 | 2016 | 2016-07-20 | N/A | 659 | N/A | N/A |  |  | 1.72 | 4857.6 | Unknown | Unknown |  |  |  | N/A | 4568193.44 | 1.0668 | 4873494.7224 | [10 empty] | 0 |  |  |  | Unknown |  |  | 4568193.44 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
PLACER COUNTY | MAIN ST NEWCASTLE PLACER CNTY R20A | 30817979 | N/A | N/A | 6061020501 | No | 4.272% | N/A | None | N/A | N/A | No | 11 | 2 | 2 | 0 | 4 | N/A | No | 1998-12-01 | TBD | TBD | TBD | N/A | N/A | N/A | #VALUE! | N/A | 2015-09-05 | N/A | N/A | Cancelled project | Cancelled project | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [6 empty] | N/A | N/A |  |  | 0 |  |  |  | N/A, project cancelled |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PLACER COUNTY | MEADOW VISTA | 30169463 | MEADOW VISTA, UUD# 1 | 95722 | 6061021902 | No | 5.254% | MEADOW VISTA, PLACER HILLS RD & LIVINGSTON RD & COMBIE RD | Tier 2 | TBD | Resolution# 2000-297 | Yes | 11 | 2 | 2 | 0 | 4 | Unknown | No | 2000-12-19 | 2001-08-10 | 2011-08-05 | 2013-03-26 | 2016 | 2016-04-09 | N/A | 234 | N/A | N/A |  |  | 1.45 | 4382.4 | Unknown | Unknown |  |  |  | N/A | 5084512.58 | 1.0668 | 5424320.4782 | [10 empty] | 0 |  |  |  | Unknown |  |  | 5084512.58 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
PLACER COUNTY | R4 ATWOOD RD AUBURN PLACER CNTY R20A | 30817975 | N/A | N/A | 6061021501 | No | 6.64% | N/A | None | N/A | N/A | No | 11 | 2 | 2 | 0 | 4 | N/A | No | 1998-12-01 | TBD | TBD | TBD | N/A | N/A | N/A | #VALUE! | N/A | 2015-09-18 | N/A | N/A | Cancelled project | Cancelled project | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [6 empty] | N/A | N/A |  |  | 0 |  |  |  | N/A, project cancelled |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Placer County Total | [41 empty] | 0
Plumas County | [41 empty] | 0
PLUMAS COUNTY | MAIN ST, GREENVILLE | 30733248 | MAIN ST | 95947 | 6063000400 | No | 17.16% | MAIN ST | Part of project in or adjacent to Tier 2 | Project met one or more Rule 20A criteria | Resolution# 08-7518 | Yes | 1 | 0 | 0 | 0 | 1 | Unknown | No | 2008-10-01 | 2013-05-28 | 2015-07-31 | 2015-12-29 | 2016 | 2016-10-19 | N/A | 1700 | N/A | N/A |  |  | 0.47 | 1953.6 | Unknown | Unknown |  |  |  | N/A | 1555870.62 | 1.0668 | 1659852.4898 | [10 empty] | 0 |  |  |  | Unknown |  |  | 1555870.62 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
Plumas County Total | [41 empty] | 0
Sacramento County | [41 empty] | 0
ISLETON | JACKSON BLVD, ISLETON | No Order | JACKSON BLVD | 95641 | 6067009800 | No | 11.49% | JACKSON BLVD FROM SECOND ST TO FOURTH ST | None | Project met one or more Rule 20A criteria | Resolution# 09-19 | No | 1 | 1 | 1 | 0 | 0 | Suburban | No | 2019-06-09 | TBD | TBD | TBD | TBD | N/A | N/A | #VALUE! | 0 | N/A | 0 | 0 | Project not completed or closed | Project not completed or closed | Commercial | Unknown | TBD | TBD | TBD | 606570 | N/A | TBD | N/A | [6 empty] | TBD | TBD | [6 empty] | Project in planning phase |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | Yes | No | No | Insufficient allocation | None | N/A | N/A | No | N/A | N/A
Sacramento County Total | [41 empty] | 0
San Benito County | [41 empty] | 0
SAN BENITO COUNTY | HIGHWAY 156, SAN BENITO COUNTY | No Order | HIGHWAY 156 | 95023 | 6069000200 | No | 5.123% | 100 YARDS ON EITHER SIDE OF HWY 156 BTW UNION RD & BREEN RD | Part of project adjacent to Tier 1 & 2 | Project met one or more Rule 20A criteria | Resolution# 2019-71 | No | 1 | 1 | 1 | 0 | 0 | Suburban | No | 2019-07-23 | TBD | TBD | TBD | TBD | N/A | N/A | #VALUE! | 0 | N/A | 0 | 0 | Project not completed or closed | Project not completed or closed | Commercial | Unknown | TBD | TBD | TBD | 24811514.81 | N/A | TBD | N/A | [6 empty] | TBD | TBD | [6 empty] | Project in planning phase |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | Yes | No | No | Insufficient allocation | None | N/A | N/A | No | N/A | N/A
San Benito County Total | [41 empty] | 0
San Francisco County | [41 empty] | 0
SAN FRANCISCO | 25TH STREET W/GPRP | 30334789 | 25TH ST | 94114 | 6075021400 | No | 1.93% | 25TH ST | None | TBD | TBD | Yes | 81 | 0 | 0 | 0 | 80 | Unknown | No | 1999-09-30 | 2003-11-03 | 2004-06-24 | 2005-12-07 | 2008 | 2009-03-17 | N/A | 1495 | N/A | N/A |  |  | 0.53 | 1425.6 | Unknown | Yes |  |  |  | N/A | 955472.96 | 1.3051 | 1247028.6379 | [10 empty] | 0 |  |  |  |  | -1149.05 | 2017-12-29 | 955472.96 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | Yes | No | Customer electrical panel conversion | None | N/A | N/A | None | N/A | N/A
SAN FRANCISCO | 3RD ST LIGHT RAIL, PHASE 3 | 30215433 | 3RD ST LIGHT RAIL, PH 3 | 94134 | 6075026403 | No | 8.285% | 3RD ST LIGHT RAIL, PH 3 | None | TBD | TBD | Yes | 81 | 0 | 0 | 0 | 80 | Urban | No | 1999-12-23 | 2002-03-05 | 2002-09-09 | 2004-04-29 | 2009 | 2009-07-29 | N/A | 803 | N/A | N/A | 40 | 10 | 1.32 | 2904 | Commercial | No |  |  |  | N/A | 2810321.26 | 1.2297 | 3455792.1575 | [6 empty] | Unknown | Unknown |  |  | 0 |  |  |  | Labor costs |  |  | 2810321.26 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | Yes | No | Customer electrical panel conversion | None | N/A | N/A | None | N/A | N/A
SAN FRANCISCO | 3RD STREET / XING 2 | 30223284 | 3RD ST / XING 2 | 94124 | 6075061200 | Yes | 11.84% | 3RD ST / XING 2 | None | TBD | TBD | Yes | 81 | 0 | 0 | 0 | 80 | Unknown | Yes | 1999-12-23 | 2002-06-10 | 2003-08-23 | 2005-05-23 | 2007 | 2007-07-31 | N/A | 900 | N/A | N/A |  |  | 0.94 | 3748.8 | Unknown | No |  |  |  | N/A | 214111.14 | 1.4306 | 306302.521 | [10 empty] | 0 | [6 empty] | 214111.14 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | Yes | No | Customer electrical panel conversion | None | N/A | N/A | None | N/A | N/A
SAN FRANCISCO | 3RD STREET / XING -3 | 30236749 | 3RD ST / XING -3 | 94124 | 6075023200 | Yes | 9.406% | 3RD ST / XING -3 | None | TBD | TBD | Yes | 81 | 0 | 0 | 0 | 80 | Unknown | Yes | 1999-12-23 | 2002-04-30 | 2003-08-08 | 2005-01-20 | 2007 | 2008-02-15 | N/A | 859 | N/A | N/A |  |  | 0.04 | 158.4 | Unknown | No |  |  |  | N/A | 290630.24 | 1.4306 | 415769.003 | [10 empty] | 0 | [6 empty] | 290630.24 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | Yes | No | Customer electrical panel conversion | None | N/A | N/A | None | N/A | N/A
SAN FRANCISCO | 3RD STREET LIGHT RAIL / PHASE 1 | 30200858 | 3RD ST LIGHT RAIL / PH 1 | 94124 | 6075980900 | Yes | 3.714% | 3RD ST LIGHT RAIL / PH 1 | None | TBD | TBD | Yes | 81 | 0 | 0 | 0 | 80 | Unknown | Yes | 1999-12-23 | 2001-06-01 | 2002-01-30 | 2002-12-09 | 2008 | 2008-08-18 | N/A | 526 | N/A | N/A |  |  | 0.99 | 2640 | Unknown | No |  |  |  | N/A | 2196860.4 | 1.3051 | 2867216.4958 | [10 empty] | 0 |  |  |  | Unknown |  |  | 2196860.4 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | Yes | No | Customer electrical panel conversion | None | N/A | N/A | None | N/A | N/A
SAN FRANCISCO | 3RD STREET LIGHT RAIL / PHASE 2 | 30211896 | 3RD ST LIGHT RAIL / PH 2 | 94124 | 6075023300 | Yes | 17.68% | 3RD ST LIGHT RAIL / PH 2 | None | TBD | TBD | Yes | 81 | 0 | 0 | 0 | 80 | Urban | Yes | 1999-12-23 | 2001-08-01 | 2002-05-16 | 2003-02-12 | 2008 | 2008-08-18 | N/A | 587 | N/A | N/A | 77 | 44 | 2.53 | 4224 | Commercial | No |  |  |  | N/A | 5416349.67 | 1.3051 | 7069109.6807 | [6 empty] | Unknown | Unknown |  |  | 0 |  |  |  | Labor costs | 1578.76 | 2017-12-29 | 5416349.67 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | Yes | No | Customer electrical panel conversion | None | N/A | N/A | None | N/A | N/A
SAN FRANCISCO | 3RD STREET LIGHT RAIL / XING - A | 30223280 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | 81 | 0 | 0 | 0 | 80 | N/A | N/A | 1999-12-23 | TBD | TBD | TBD | N/A | 2007-07-31 | N/A | #VALUE! | N/A | 2007-02-24 | N/A | N/A | Cancelled project | Cancelled project | N/A | N/A | N/A | N/A | N/A | N/A | 57429.87 | 1.4306 | 82157.8642 | [6 empty] | N/A | N/A |  |  | 0 |  |  |  | N/A, project cancelled |  |  | 57429.87 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SAN FRANCISCO | ALPINE TERRACE (CABLING PORTION) | 30181165 | ALPINE TERRACE | 94114 | 6075016700 | No | 3.138% | ALPINE TERRACE | None | TBD | TBD | Yes | 81 | 0 | 0 | 0 | 80 | Urban | No | 1996-04-24 | 2001-01-22 | 2001-09-13 | 2002-02-25 | 2008 | 2009-03-17 | N/A | 1734 | N/A | N/A | 21 | 93 | 0.57 | 1689.6 | Residential | No |  |  |  | N/A | 312250.44 | 1.3051 | 407531.4082 | [6 empty] | Unknown | Unknown |  |  | 0 |  |  |  | Labor costs |  |  | 312250.44 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | Yes | No | Customer electrical panel conversion | None | N/A | N/A | None | N/A | N/A
SAN FRANCISCO | ARGUELLO - 7TH & LINCOLN-KIRK | 30184983 | ARGUELLO - 7TH & LINCOLN-KIRK, SAN FRANCISCO | 94122 | 6075030101 | No | 2.646% | ARGUELLO - 7TH & LINCOLN-KIRK, SAN FRANCISCO | None | TBD | TBD | Yes | 81 | 0 | 0 | 0 | 80 | Urban | No | 1996-11-05 | 2001-08-07 | 2002-05-20 | 2003-02-27 | 2009 | 2009-07-29 | N/A | 1736 | N/A | N/A | 230 | 475 | 3.05 | 12249.6 | Residential | Yes |  |  |  | N/A | 1706112.77 | 1.2297 | 2097970.5111 | [6 empty] | Unknown | Unknown |  |  | 0 |  |  |  | Labor costs |  |  | 1706112.77 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | Yes | No | Customer electrical panel conversion | None | N/A | N/A | None | N/A | N/A
SAN FRANCISCO | BANKS/CHAPMAN (SUBSTRUCTURE PORTION) W/GPRP | 30034755 | BANKS/CHAPMAN | 94110 | 6075025100 | No | 2.632% | BANKS/CHAPMAN | None | TBD | TBD | Yes | 81 | 0 | 0 | 0 | 80 | Urban | No | 1998-03-31 | 1999-03-15 | 2002-09-09 | 2005-01-19 | 2008 | 2009-03-17 | N/A | 349 | N/A | N/A | 123 | 312 | No primary UG circuit data found | 792 | Residential | Yes |  |  |  | N/A | 3440952.05 | 1.3051 | 4490933.7339 | [6 empty] | Unknown | Unknown |  |  | 0 |  |  |  | Labor costs |  |  | 3440952.05 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | Yes | No | Customer electrical panel conversion | None | N/A | N/A | None | N/A | N/A
SAN FRANCISCO | BANKS/CHAPMAN RULE 20A | 30333103 | BANKS/CHAPMAN | 94110 | 6075025200 | No | 3.874% | BANKS/CHAPMAN | None | TBD | TBD | Yes | 81 | 0 | 0 | 0 | 80 | Unknown | No | 1998-03-31 | 2003-08-26 | 2004-04-12 | 2005-08-18 | 2010 | 2010-08-26 | N/A | 1974 | N/A | N/A |  |  | 0.15 | 739.2 | Unknown | Yes |  |  |  | N/A | 1787842 | 1.249 | 2232978.4765 | [10 empty] | 0 |  |  |  |  | 10971.72 | 2017-12-29 | 1787842 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | Yes | No | Customer electrical panel conversion | None | N/A | N/A | None | N/A | N/A
SAN FRANCISCO | BANKS/CHAPMAN, REPLACE POLE | 30459828 | BANKS/CHAPMAN | 94110 | Unknown | Unknown | Unknown | BANKS/CHAPMAN | Unknown | TBD | TBD | Yes | 81 | 0 | 0 | 0 | 80 | Unknown | Unknown | 1998-03-31 | 2005-09-02 | 2005-12-28 | 2006-06-26 | 2008 | 2008-08-18 | N/A | 2712 | N/A | N/A |  |  | No primary UG circuit data found | 0 | Unknown | Unknown |  |  |  | N/A | 25514.23 | 1.3051 | 33299.7131 | [10 empty] | 0 |  |  |  | Unknown |  |  | 25514.23 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
SAN FRANCISCO | C:E PC ALPINE TERRACE - R20A (W/GPRP), S | 30010943 | ALPINE TERRACE | 94117 | 6075017000 | No | 1.789% | ALPINE TERRACE | None | TBD | TBD | Yes | 81 | 0 | 0 | 0 | 80 | Unknown | No | TBD | 1998-07-13 | 2001-02-02 | 2002-05-13 | 2006 | 2007-03-24 | N/A | #VALUE! | N/A | N/A |  |  | No primary UG circuit data found | 1267.2 | Unknown | No |  |  |  | N/A | 997312.72 | 1.591 | 1586690.691 | [10 empty] | 0 | [6 empty] | 997312.72 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | Yes | No | Customer electrical panel conversion | None | N/A | N/A | None | N/A | N/A
SAN FRANCISCO | C:E PC ARGUELLO-7TH&LINCOLN-KIRK,SAN FRA | 30014020 | ARGUELLO - 7TH & LINCOLN-KIRK, SAN FRANCISCO | 94122 | 6075030101 | No | 2.646% | ARGUELLO - 7TH & LINCOLN-KIRK, SAN FRANCISCO | None | TBD | TBD | Yes | 81 | 0 | 0 | 0 | 80 | Unknown | No | TBD | 1998-09-14 | 1999-11-13 | 2003-02-12 | 2006 | 2007-03-24 | N/A | #VALUE! | N/A | N/A |  |  | 0.85 | 4012.8 | Unknown | Yes |  |  |  | N/A | 4659316.46 | 1.591 | 7412814.3611 | [10 empty] | 0 | [6 empty] | 4659316.46 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | Yes | No | Customer electrical panel conversion | None | N/A | N/A | None | N/A | N/A
SAN FRANCISCO | C:E PC LAGUNA,BUSH-CALIF,R20A(W/GPRP)SF | 30118499 | LAGUNA, BUSH-CALIF, SAN FRANCISCO | 94115 | 6075015200 | No | 4.093% | LAGUNA, BUSH-CALIF, SAN FRANCISCO | None | TBD | TBD | Yes | 81 | 0 | 0 | 0 | 80 | Unknown | No | TBD | 1999-12-30 | 2001-10-24 | 2003-02-12 | 2006 | 2007-03-24 | N/A | #VALUE! | N/A | N/A |  |  | 0.56 | 1900.8 | Unknown | Yes |  |  |  | N/A | 635984.86 | 1.591 | 1011830.3284 | [10 empty] | 0 | [6 empty] | 635984.86 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | Yes | No | Customer electrical panel conversion | None | N/A | N/A | None | N/A | N/A
SAN FRANCISCO | C:E PC PRESIDIO HTS (6TH / LAKE) | 30177649 | PRESIDIO HTS (6TH / LAKE) | 94118 | 6075040100 | No | 4.574% | PRESIDIO HTS (6TH / LAKE) | None | TBD | TBD | Yes | 81 | 0 | 0 | 0 | 80 | Unknown | No | TBD | 2001-01-04 | 2002-02-15 | 2002-10-04 | 2006 | 2007-03-24 | N/A | #VALUE! | N/A | N/A |  |  | 0.38 | 1795.2 | Unknown | Yes |  |  |  | N/A | 798692 | 1.591 | 1270691.8662 | [10 empty] | 0 | [6 empty] | 798692 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | Yes | No | Customer electrical panel conversion | None | N/A | N/A | None | N/A | N/A
SAN FRANCISCO | C:E POTOMAC & WALLER-R20A, SF CBLG | 30138317 | POTOMAC & WALLER, SAN FRANCISCO | 94117 | 6075016700 | No | 3.138% | POTOMAC & WALLER, SAN FRANCISCO | None | TBD | TBD | Yes | 81 | 0 | 0 | 0 | 80 | Unknown | No | TBD | 2002-04-15 | 2002-07-09 | 2003-05-09 | 2006 | 2007-03-24 | N/A | #VALUE! | N/A | N/A |  |  | 1.08 | 3643.2 | Unknown | Yes |  |  |  | N/A | 530922.15 | 1.591 | 844679.1223 | [10 empty] | 0 | [6 empty] | 530922.15 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | Yes | No | Customer electrical panel conversion | None | N/A | N/A | None | N/A | N/A
SAN FRANCISCO | C:EPC DOLORES HTS 2 - R20A (W/GPRP), SF | 30010785 | DOLORES HTS 2, SAN FRANCISCO | 94114 | 6075020600 | No | 2.547% | DOLORES HTS 2, SAN FRANCISCO | None | TBD | TBD | Yes | 81 | 0 | 0 | 0 | 80 | Unknown | No | TBD | 1998-07-11 | 1999-09-14 | 2001-01-19 | 2006 | 2007-03-24 | N/A | #VALUE! | N/A | N/A |  |  | 0.85 | 2956.8 | Unknown | No |  |  |  | N/A | 1521687.91 | 1.591 | 2420953.8221 | [10 empty] | 0 | [6 empty] | 1521687.91 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | Yes | No | Customer electrical panel conversion | None | N/A | N/A | None | N/A | N/A
SAN FRANCISCO | CHINATOWN ALLEYS (BECKETT) | 30443282 | CHINATOWN ALLEYS (BECKETT) | 94133 | 6075061100 | No | 13.58% | CHINATOWN ALLEYS (BECKETT) | None | TBD | TBD | Yes | 81 | 0 | 0 | 0 | 80 | Unknown | No | TBD | 2005-07-01 | 2005-10-08 | 2006-10-16 | 2008 | 2008-08-18 | N/A | #VALUE! | N/A | N/A |  |  | No primary UG circuit data found | 0 | Unknown | No |  |  |  | N/A | 186532.49 | 1.3051 | 243451.5331 | [10 empty] | 0 | [6 empty] | 186532.49 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | Yes | No | Customer electrical panel conversion | None | N/A | N/A | None | N/A | N/A
SAN FRANCISCO | CHINATOWN ALLEYS (WAVERLY ) | 30391234 | CHINATOWN ALLEYS (WAVERLY ) | 94108 | Unknown | Unknown | Unknown | CHINATOWN ALLEYS (WAVERLY ) | Unknown | TBD | TBD | Yes | 81 | 0 | 0 | 0 | 80 | Unknown | Unknown | TBD | 2004-07-31 | 2004-10-06 | 2006-01-23 | 2007 | 2008-02-15 | N/A | #VALUE! | N/A | N/A |  |  | No primary UG circuit data found | 0 | Unknown | No |  |  |  | N/A | 319526.64 | 1.4306 | 457107.5348 | [10 empty] | 0 | [6 empty] | 319526.64 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | Yes | No | Customer electrical panel conversion | None | N/A | N/A | None | N/A | N/A
SAN FRANCISCO | CHINATOWN ALLEYS (WENTWORTH) | 30443283 | CHINATOWN ALLEYS (WENTWORTH) | 94108 | 6075061100 | No | 13.58% | CHINATOWN ALLEYS (WENTWORTH) | None | TBD | TBD | Yes | 81 | 0 | 0 | 0 | 80 | Unknown | No | TBD | 2005-07-06 | 2005-10-08 | 2006-10-16 | 2008 | 2008-08-18 | N/A | #VALUE! | N/A | N/A |  |  | No primary UG circuit data found | 0 | Unknown | No |  |  |  | N/A | 284499.38 | 1.3051 | 371312.3125 | [10 empty] | 0 | [6 empty] | 284499.38 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | Yes | No | Customer electrical panel conversion | None | N/A | N/A | None | N/A | N/A
SAN FRANCISCO | CORBETT AVE - DIST.#311 - PH 2 | 30334782 | CORBETT AVE - DIST# 311 - PH 2 | 94114 | 6075020401 | No | 1.757% | CORBETT AVE - DIST# 311 - PH 2 | None | TBD | TBD | Yes | 81 | 0 | 0 | 0 | 80 | Unknown | No | 1980-01-11 | 2003-10-29 | 2004-10-05 | 2007-07-26 | 2012 | 2012-09-13 | N/A | 8692 | N/A | N/A |  |  | 1.24 | 3432 | Unknown | Yes |  |  |  | N/A | 3374542.84 | 1.121 | 3783001.8689 | [10 empty] | 0 |  |  |  |  | 53489 | 2017-12-29 | 3374542.84 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | Yes | No | Customer electrical panel conversion | None | N/A | N/A | None | N/A | N/A
SAN FRANCISCO | COURTLAND CONNECT - DIST.#339 - PH 1 | 30249359 | COURTLAND CONNECT - DIST# 339 - PH 1 | 94110 | 6075025200 | No | 3.874% | COURTLAND CONNECT - DIST# 339 - PH 1 | None | TBD | TBD | Yes | 81 | 0 | 0 | 0 | 80 | Unknown | No | 1998-03-30 | 2002-05-16 | 2004-11-03 | 2006-07-10 | 2012 | 2012-09-13 | N/A | 1508 | N/A | N/A |  |  | 1.53 | 8764.8 | Unknown | Yes |  |  |  | N/A | 4105893.35 | 1.121 | 4602875.9904 | [10 empty] | 0 |  |  |  |  | 81991.22 | 2017-12-29 | 4105893.35 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | Yes | No | Customer electrical panel conversion | None | N/A | N/A | None | N/A | N/A
SAN FRANCISCO | COURTLAND CONNECT - DIST.#339 - PH 2 | 30334699 | COURTLAND CONNECT - DIST# 339 - PH 2 | 94110 | 6075025100 | No | 2.632% | COURTLAND CONNECT - DIST# 339 - PH 2 | None | TBD | TBD | Yes | 81 | 0 | 0 | 0 | 80 | Unknown | No | 1998-03-30 | 2004-04-12 | 2004-12-28 | 2006-07-10 | 2012 | 2012-09-13 | N/A | 2205 | N/A | N/A |  |  | 1.67 | 4382.4 | Unknown | Yes |  |  |  | N/A | 4549044.93 | 1.121 | 5099667.2106 | [10 empty] | 0 |  |  |  |  | 35533 | 2017-12-29 | 4549044.93 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | Yes | No | Customer electrical panel conversion | None | N/A | N/A | None | N/A | N/A
SAN FRANCISCO | DUBOCE/CHURCH - DIST.#324 | 30410006 | DUBOCE/CHURCH - DIST# 324 | 94114 | 6075016900 | No | 3.386% | DUBOCE/CHURCH - DIST# 324 | None | TBD | TBD | Yes | 81 | 0 | 0 | 0 | 80 | Unknown | No | 1996-11-05 | 2005-02-17 | 2005-04-05 | 2006-08-29 | 2012 | 2012-09-13 | N/A | 3026 | N/A | N/A |  |  | 0.95 | 2481.6 | Unknown | Yes |  |  |  | N/A | 2999614.83 | 1.121 | 3362692.0878 | [10 empty] | 0 |  |  |  |  | 43513 | 2017-12-29 | 2999614.83 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | Yes | No | Customer electrical panel conversion | None | N/A | N/A | None | N/A | N/A
SAN FRANCISCO | DUNCAN/NEWBURG - DIST.#332 | 30410007 | DUNCAN/NEWBURG - DIST# 332 | 94131 | 6075021600 | No | 1.929% | DUNCAN/NEWBURG - DIST# 332 | None | TBD | TBD | Yes | 81 | 0 | 0 | 0 | 80 | Unknown | No | 1998-03-27 | 2005-02-04 | 2005-03-29 | 2006-10-13 | 2012 | 2012-09-13 | N/A | 2506 | N/A | N/A |  |  | 0.92 | 2534.4 | Unknown | Yes |  |  |  | N/A | 2565688.28 | 1.121 | 2876242.5071 | [10 empty] | 0 |  |  |  |  | 31589 | 2017-12-29 | 2565688.28 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | Yes | No | Customer electrical panel conversion | None | N/A | N/A | None | N/A | N/A
SAN FRANCISCO | E PC C&CSF DISTRICT,SAN FRANC | 30010765 | C&CSF DISTRICT, SAN FRANCISCO | 94103 | Unknown | Unknown | Unknown | C&CSF DISTRICT, SAN FRANCISCO | Unknown | TBD | TBD | Yes | 81 | 0 | 0 | 0 | 80 | Unknown | Unknown | TBD | TBD | TBD | TBD | 2005 | 2007-03-24 | N/A | #VALUE! | N/A | N/A |  |  | No primary UG circuit data found | 0 | Unknown | Unknown |  |  |  | N/A | 1425471.75 | 1.7065 | 2432582.8028 | [10 empty] | 0 |  |  |  | Unknown |  |  | 1425471.75 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
SAN FRANCISCO | E PC MONTEZUMA/AZTEC,SAN FRANC | 30011696 | MONTEZUMA/AZTEC, SAN FRANCISCO | 94110 | Unknown | Unknown | Unknown | MONTEZUMA/AZTEC, SAN FRANCISCO | Unknown | TBD | TBD | Yes | 81 | 0 | 0 | 0 | 80 | Unknown | Unknown | TBD | 1998-07-13 | 1999-07-15 | 1999-08-17 | 2005 | 2007-03-24 | N/A | #VALUE! | N/A | N/A |  |  | No primary UG circuit data found | 369.6 | Unknown | Yes |  |  |  | N/A | 261704.18 | 1.7065 | 446600.985 | [10 empty] | 0 | [6 empty] | 261704.18 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | Yes | No | Customer electrical panel conversion | None | N/A | N/A | None | N/A | N/A
SAN FRANCISCO | EC POTOMAC & WALLER - R20A, SF | 30011832 | POTOMAC & WALLER, SAN FRANCISCO | 94117 | Unknown | Unknown | Unknown | POTOMAC & WALLER, SAN FRANCISCO | Unknown | TBD | TBD | Yes | 81 | 0 | 0 | 0 | 80 | Unknown | Unknown | TBD | 1999-07-15 | 2002-02-22 | 2002-08-13 | 2005 | 2007-03-24 | N/A | #VALUE! | N/A | N/A |  |  | No primary UG circuit data found | 1320 | Unknown | Yes |  |  |  | N/A | 1132966.6422 | 1.7065 | 1933419.7047 | [10 empty] | 0 | [6 empty] | 1132966.6422 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | Yes | No | Customer electrical panel conversion | None | N/A | N/A | None | N/A | N/A
SAN FRANCISCO | EP - BROAD/RANDOLPH R20A | 30249357 | BROAD/RANDOLPH | 94112 | 6075031400 | No | 6.681% | BROAD/RANDOLPH | None | TBD | TBD | Yes | 81 | 0 | 0 | 0 | 80 | Unknown | No | 1998-02-26 | 2002-03-26 | 2003-05-13 | 2006-07-18 | 2010 | 2010-08-26 | N/A | 1489 | N/A | N/A |  |  | 3.03 | 8025.6 | Unknown | Yes |  |  |  | N/A | 5954541 | 1.249 | 7437101.2037 | [10 empty] | 0 |  |  |  |  | 115428.74 | 2017-12-29 | 5954541 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | Yes | No | Customer electrical panel conversion | None | N/A | N/A | None | N/A | N/A
SAN FRANCISCO | EP CHINATOWN ALLEYS (JOHN) WO/GPRP | 30249434 | CHINATOWN ALLEYS (JOHN) | 94133 | 6075011300 | No | 13.9% | CHINATOWN ALLEYS (JOHN) | None | TBD | TBD | Yes | 81 | 0 | 0 | 0 | 80 | Unknown | No | TBD | 2002-05-26 | 2002-10-03 | 2003-02-11 | 2005 | 2007-03-24 | N/A | #VALUE! | N/A | N/A |  |  | No primary UG circuit data found | 792 | Unknown | No |  |  |  | N/A | 190460.48 | 1.7065 | 325022.8482 | [10 empty] | 0 | [6 empty] | 190460.48 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | Unknown | Yes | No | Customer electrical panel conversion | None | N/A | N/A | None | N/A | N/A
SAN FRANCISCO | EP CHINATOWN ALLEYS (SPOFFORD) WO/GPRP | 30263286 | CHINATOWN ALLEYS (SPOFFORD) | 94108 | 6075061100 | No | 13.58% | CHINATOWN ALLEYS (SPOFFORD) | None | TBD | TBD | Yes | 81 | 0 | 0 | 0 | 80 | Unknown | No | TBD | 2002-07-16 | 2003-03-26 | 2004-10-01 | 2006 | 2007-03-24 | N/A | #VALUE! | N/A | N/A |  |  | No primary UG circuit data found | 211.2 | Unknown | No |  |  |  | N/A | 138224.51 | 1.591 | 219910.5044 | [10 empty] | 0 | [6 empty] | 138224.51 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | Yes | No | Customer electrical panel conversion | None | N/A | N/A | None | N/A | N/A
SAN FRANCISCO | FLINT/16TH ST W/GPRP | 30334790 | FLINT/16TH ST | 94114 | 6075017000 | No | 1.789% | FLINT/16TH ST | None | TBD | TBD | Yes | 81 | 0 | 0 | 0 | 80 | Unknown | No | 1998-05-01 | 2004-07-15 | 2005-06-30 | 2006-04-04 | 2008 | 2009-03-17 | N/A | 2267 | N/A | N/A |  |  | 0.12 | 580.8 | Unknown | Yes |  |  |  | N/A | 457893.43 | 1.3051 | 597616.3054 | [10 empty] | 0 |  |  |  |  | 8401.72 | 2017-12-29 | 457893.43 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | Yes | No | Customer electrical panel conversion | None | N/A | N/A | None | N/A | N/A
SAN FRANCISCO | FUNSTON AVE W/ GPRP | 30223375 | FUNSTON AVE | 94118 | 6075045200 | No | 4.34% | FUNSTON AVE | None | TBD | TBD | Yes | 81 | 0 | 0 | 0 | 80 | Urban | No | 1999-05-19 | 2001-10-08 | 2003-02-18 | 2003-11-19 | 2008 | 2008-08-18 | N/A | 873 | N/A | N/A |  |  | 1.03 | 3537.6 | Commercial | Yes |  |  |  | N/A | 2729141.09 | 1.3051 | 3561918.7967 | [6 empty] | Yes | N/A |  |  | 0 | [6 empty] | 2729141.09 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
SAN FRANCISCO | GEP DOLORES STREET 2 R20A | 30250175 | DOLORES ST 2 | 94110 | 6075021100 | No | 1.817% | DOLORES ST 2 | None | TBD | TBD | Yes | 81 | 0 | 0 | 0 | 80 | Unknown | No | 1998-03-31 | 2002-12-18 | 2004-02-06 | 2005-12-21 | 2010 | 2010-08-26 | N/A | 1723 | N/A | N/A |  |  | 0.54 | 2745.6 | Unknown | No |  |  |  | N/A | 2575673 | 1.249 | 3216963.4517 | [10 empty] | 0 |  |  |  |  | 12622.69 | 2017-12-29 | 2575673 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | Yes | No | Customer electrical panel conversion | None | N/A | N/A | None | N/A | N/A
SAN FRANCISCO | GEP DOLORES STREET 3 R20A | 30334698 | DOLORES ST 3 | 94110 | 6075021500 | No | 2.963% | DOLORES ST 3 | None | TBD | TBD | Yes | 81 | 0 | 0 | 0 | 80 | Unknown | No | 1998-03-31 | 2003-10-20 | 2004-11-02 | 2006-06-05 | 2010 | 2010-08-26 | N/A | 2029 | N/A | N/A |  |  | 2.58 | 9451.2 | Unknown | No |  |  |  | N/A | 4558682 | 1.249 | 5693701.5614 | [10 empty] | 0 |  |  |  |  | 16041.76 | 2017-12-29 | 4558682 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | Yes | No | Customer electrical panel conversion | None | N/A | N/A | None | N/A | N/A
SAN FRANCISCO | GEP MID LAKE R20A | 30249629 | MID LAKE | 94121 | 6075042800 | No | 1.221% | MID LAKE | None | TBD | TBD | Yes | 81 | 0 | 0 | 0 | 80 | Unknown | No | 1999-09-30 | 2002-06-01 | 2003-07-12 | 2005-12-07 | 2010 | 2010-08-26 | N/A | 975 | N/A | N/A |  |  | 1.06 | 6019.2 | Unknown | Yes |  |  |  | N/A | 2463511 | 1.249 | 3076875.3836 | [10 empty] | 0 |  |  |  |  | 10245.4 | 2017-12-29 | 2463511 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | Yes | No | Customer electrical panel conversion | None | N/A | N/A | None | N/A | N/A
SAN FRANCISCO | GEP OAKDALE/PALOU 1 R20A | 30334785 | OAKDALE/PALOU 1 | 94124 | 6075061200 | Yes | 11.84% | OAKDALE/PALOU 1 | None | TBD | TBD | Yes | 81 | 0 | 0 | 0 | 80 | Unknown | Yes | 1999-11-22 | 2003-12-09 | 2004-04-05 | 2006-06-30 | 2010 | 2010-08-26 | N/A | 1478 | N/A | N/A |  |  | 1.76 | 6705.6 | Unknown | Yes |  |  |  | N/A | 4772907 | 1.249 | 5961264.2511 | [10 empty] | 0 |  |  |  |  | -38006.63 | 2017-12-29 | 4772907 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | Yes | No | Customer electrical panel conversion | None | N/A | N/A | None | N/A | N/A
SAN FRANCISCO | GEP TARAVEL ST. R20A | 30334788 | TARAVEL ST | 94116 | 6075035300 | No | 5.453% | TARAVEL ST | None | TBD | TBD | Yes | 81 | 0 | 0 | 0 | 80 | Unknown | No | 1999-02-17 | 2003-12-30 | 2005-11-04 | 2006-02-06 | 2010 | 2010-08-26 | N/A | 1777 | N/A | N/A |  |  | 2.5 | 6864 | Unknown | No |  |  |  | N/A | 3675619 | 1.249 | 4590773.7455 | [10 empty] | 0 | [6 empty] | 3675619 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | Yes | No | Customer electrical panel conversion | None | N/A | N/A | None | N/A | N/A
SAN FRANCISCO | GEP: OCTAVIA ST R20A | 30314814 | OCTAVIA ST | 94102 | 6075016802 | No | 7.108% | OCTAVIA ST | None | TBD | TBD | Yes | 81 | 0 | 0 | 0 | 80 | Unknown | No | 1999-01-15 | 2003-05-21 | 2003-10-15 | 2004-05-24 | 2010 | 2010-08-26 | N/A | 1587 | N/A | N/A |  |  | 0.79 | 2481.6 | Unknown | Yes |  |  |  | N/A | 1590802 | 1.249 | 1986879.5041 | [10 empty] | 0 |  |  |  |  | -12311.54 | 2017-12-29 | 1590802 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | Yes | No | Customer electrical panel conversion | None | N/A | N/A | None | N/A | N/A
SAN FRANCISCO | GEPC OCEAN AVE.-R20A PHASE I CABLING | 30237177 | OCEAN AVE, PH 1 | 94127 | 6075030900 | No | 1.747% | OCEAN AVE, PH 1 | None | TBD | TBD | Yes | 81 | 0 | 0 | 0 | 80 | Urban | No | TBD | 2001-12-26 | 2002-05-02 | 2002-10-17 | 2005 | 2007-03-24 | N/A | #VALUE! | N/A | N/A |  |  | 1.11 | 2692.8 | Commercial | Yes |  |  |  | N/A | 398529.84 | 1.7065 | 680095.4387 | [6 empty] | Unknown | Unknown |  |  | 0 | [6 empty] | 398529.84 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | Yes | No | Customer electrical panel conversion | None | N/A | N/A | None | N/A | N/A
SAN FRANCISCO | GES 9TH & 10TH AVE/ORTEGA R20A W/GPRP | 30222283 | 9TH & 10TH AVE/ORTEGA | 94116 | 6075030302 | No | 2.395% | 9TH & 10TH AVE/ORTEGA | None | TBD | TBD | Yes | 81 | 0 | 0 | 0 | 80 | Unknown | No | TBD | 2002-01-30 | 2003-07-25 | 2005-12-21 | 2006 | 2007-03-24 | N/A | #VALUE! | N/A | N/A |  |  | No primary UG circuit data found | 9768 | Unknown | Unknown |  |  |  | N/A | 2383495.97 | 1.591 | 3792061.1977 | [10 empty] | 0 |  |  |  | Unknown |  |  | 2383495.97 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
SAN FRANCISCO | GES LAIDLEY ST R20A W/GPRP SAN FRANCISCO | 30216820 | LAIDLEY ST, SAN FRANCISCO | 94131 | 6075021800 | No | 1.953% | LAIDLEY ST, SAN FRANCISCO | None | TBD | TBD | Yes | 81 | 0 | 0 | 0 | 80 | Unknown | No | TBD | 2001-09-25 | 2002-11-14 | 2004-02-11 | 2006 | 2007-03-24 | N/A | #VALUE! | N/A | N/A |  |  | 0.34 | 2798.4 | Unknown | Yes |  |  |  | N/A | 1425443.06 | 1.591 | 2267831.5321 | [10 empty] | 0 | [6 empty] | 1425443.06 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | Yes | No | Customer electrical panel conversion | None | N/A | N/A | None | N/A | N/A
SAN FRANCISCO | GES MISSION ST R20A | 30223376 & 31370088 | MISSION ST | 94112 | 6075025401 | No | 6.522% | MISSION ST | None | TBD | TBD | Yes | 81 | 0 | 0 | 0 | 80 | Unknown | No | 1997-11-07 | 2001-10-03 | 2002-09-07 | 2005-12-21 | 2010 | 2010-08-26 | N/A | 1426 | N/A | N/A |  |  | 1.97 | 5966.4 | Unknown | No |  |  |  | N/A | 5122168.34 | 1.249 | 6397484.5965 | [10 empty] | 0 |  |  |  |  | 15046.98 | 2017-12-29 | 5122168.34 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | Yes | No | Customer electrical panel conversion | None | N/A | N/A | None | N/A | N/A
SAN FRANCISCO | GOUGH & GREEN (CABLING PORTION) W/GPRP | 30192420 | GOUGH & GREEN | 94123 | 6075013000 | No | 1.335% | GOUGH & GREEN | None | TBD | TBD | Yes | 81 | 0 | 0 | 0 | 80 | Urban | No | 1997-11-07 | 2001-03-26 | 2002-07-11 | 2003-02-27 | 2008 | 2009-03-17 | N/A | 1235 | N/A | N/A | 67 | 182 | 1.39 | 5913.6 | Residential | Yes |  |  |  | N/A | 1012903.58 | 1.3051 | 1321983.7971 | [6 empty] | Unknown | Unknown |  |  | 0 |  |  |  | Labor costs |  |  | 1012903.58 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | Yes | No | Customer electrical panel conversion | None | N/A | N/A | None | N/A | N/A
SAN FRANCISCO | GOUGH & GREEN W/GPRP | 30011097 | GOUGH & GREEN | 94123 | Unknown | Unknown | Unknown | GOUGH & GREEN | Unknown | TBD | TBD | Yes | 81 | 0 | 0 | 0 | 80 | Rural | Unknown | 1997-11-07 | 1998-11-09 | 2000-03-31 | 2003-02-12 | 2008 | 2008-08-18 | N/A | 367 | N/A | N/A | 67 | 182 | No primary UG circuit data found | 0 | Residential | Yes |  |  |  | N/A | 2075842.58 | 1.3051 | 2709270.9614 | [6 empty] | Unknown | Unknown |  |  | 0 |  |  |  | Labor costs |  |  | 2075842.58 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | Yes | No | Customer electrical panel conversion | None | N/A | N/A | None | N/A | N/A
SAN FRANCISCO | GREAT HWY W/GPRP | 30376352 | GREAT HWY | 94116 | 6075035400 | No | 5.515% | GREAT HWY | None | TBD | TBD | Yes | 81 | 0 | 0 | 0 | 80 | Unknown | No | 2001-03-19 | 2004-05-03 | 2005-07-07 | 2006-08-24 | 2009 | 2010-03-16 | N/A | 1141 | N/A | N/A |  |  | 0.86 | 2323.2 | Unknown | Yes |  |  |  | N/A | 1349572.27 | 1.2297 | 1659540.2572 | [10 empty] | 0 | [6 empty] | 1349572.27 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | Yes | No | Customer electrical panel conversion | None | N/A | N/A | None | N/A | N/A
SAN FRANCISCO | LAIDLEY ST - DIST.#330 - PH 2 | 30278150 | LAIDLEY ST - DIST# 330 - PH 2 | 94131 | 6075021800 | No | 1.953% | LAIDLEY ST - DIST# 330 - PH 2 | None | TBD | TBD | Yes | 81 | 0 | 0 | 0 | 80 | Unknown | No | 1998-03-27 | 2002-10-07 | 2004-03-22 | 2005-12-07 | 2012 | 2012-09-13 | N/A | 1655 | N/A | N/A |  |  | 0.49 | 2745.6 | Unknown | Yes |  |  |  | N/A | 1366056.96 | 1.121 | 1531406.2609 | [10 empty] | 0 |  |  |  |  | 38364 | 2017-12-29 | 1366056.96 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | Yes | No | Customer electrical panel conversion | None | N/A | N/A | None | N/A | N/A
SAN FRANCISCO | LIBERTY HILL - DIST.#329 - PH 1 | 30250174 | LIBERTY HILL - DIST# 329 - PH 1 | 94110 | 6075020700 | No | 4.854% | LIBERTY HILL - DIST# 329 - PH 1 | None | TBD | TBD | Yes | 81 | 0 | 0 | 0 | 80 | Unknown | No | 1998-01-14 | 2002-06-05 | 2004-01-22 | 2005-12-07 | 2012 | 2012-09-13 | N/A | 1603 | N/A | N/A |  |  | 1.28 | 6124.8 | Unknown | Yes |  |  |  | N/A | 4416283.62 | 1.121 | 4950836.3 | [10 empty] | 0 |  |  |  |  | 28234 | 2017-12-29 | 4416283.62 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | Yes | No | Customer electrical panel conversion | None | N/A | N/A | None | N/A | N/A
SAN FRANCISCO | LINCOLN #3 (CABLING PORTION, 2001 PROJECT) | 30137189 | LINCOLN #3 | 94122 | 6075032601 | No | 5.072% | LINCOLN #3 | None | TBD | TBD | Yes | 81 | 0 | 0 | 0 | 80 | Rural | No | 1999-03-01 | 2001-03-08 | 2002-02-25 | 2002-10-11 | 2008 | 2009-03-17 | N/A | 738 | N/A | N/A | 22 | 32 | 0.41 | 1320 | Residential | Yes |  |  |  | N/A | 290756.65 | 1.3051 | 379478.9433 | [6 empty] | Unknown | Unknown |  |  | 0 |  |  |  | Labor costs |  |  | 290756.65 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | Yes | No | Customer electrical panel conversion | None | N/A | N/A | None | N/A | N/A
SAN FRANCISCO | LINCOLN WAY #2 (CABLING PORTION) W/ GPRP | 30222280 | LINCOLN WAY #2 | 94122 | 6075035202 | No | 5.854% | LINCOLN WAY #2 | None | TBD | TBD | Yes | 81 | 0 | 0 | 0 | 80 | Rural | No | 1999-08-06 | 2001-10-29 | 2002-12-04 | 2003-06-02 | 2008 | 2009-03-17 | N/A | 815 | N/A | N/A | 31 | 46 | 0.59 | 4329.6 | Residential | Yes |  |  |  | N/A | 1114744.99 | 1.3051 | 1454901.3783 | [6 empty] | Unknown | Unknown |  |  | 0 |  |  |  | Labor costs |  |  | 1114744.99 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | Yes | No | Customer electrical panel conversion | None | N/A | N/A | None | N/A | N/A
SAN FRANCISCO | LINCOLN WAY 4 W/GPRP | 30334791 | LINCOLN WAY 4 | 94122 | 6075032700 | No | 4.337% | LINCOLN WAY 4 | None | TBD | TBD | Yes | 81 | 0 | 0 | 0 | 80 | Unknown | No | 1999-03-01 | 2003-11-05 | 2004-09-24 | 2005-12-15 | 2008 | 2008-08-18 | N/A | 1710 | N/A | N/A |  |  | 0.1 | 1056 | Unknown | Unknown |  |  |  | N/A | 272358.39 | 1.3051 | 355466.587 | [10 empty] | 0 |  |  |  | Unknown |  |  | 272358.39 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
SAN FRANCISCO | LINCOLN WAY 6 W/GPRP | 30271350 | LINCOLN WAY 6 | 94122 | 6075035100 | No | 4.833% | LINCOLN WAY 6 | None | TBD | TBD | Yes | 81 | 0 | 0 | 0 | 80 | Urban | No | 1999-03-01 | 2002-09-30 | 2003-10-01 | 2004-08-16 | 2008 | 2008-08-18 | N/A | 1309 | N/A | N/A |  |  | 0.23 | 1425.6 | Commercial | Yes |  |  |  | N/A | 677422.82 | 1.3051 | 884133.5044 | [6 empty] | Yes | N/A |  |  | 0 | [6 empty] | 677422.82 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
SAN FRANCISCO | LOWER CLAYTON W/GPRP | 30040767 | LOWER CLAYTON | 94117 | 6075020401 | No | 1.757% | LOWER CLAYTON | None | TBD | TBD | Yes | 81 | 0 | 0 | 0 | 80 | Rural | No | 1980-01-11 | 2001-02-01 | 2002-06-12 | 2002-09-18 | 2008 | 2009-03-17 | N/A | 7692 | N/A | N/A | 25 | 60 | 0.22 | 1161.6 | Residential | Yes |  |  |  | N/A | 771641.88 | 1.3051 | 1007102.8306 | [6 empty] | Unknown | Unknown |  |  | 0 |  |  |  | Labor costs |  |  | 771641.88 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | Yes | No | Customer electrical panel conversion | None | N/A | N/A | None | N/A | N/A
SAN FRANCISCO | MID-24TH | 30249353 | MID-24TH | 94110 | 6075020900 | No | 8.349% | MID-24TH | None | TBD | TBD | Yes | 81 | 0 | 0 | 0 | 80 | Unknown | No | 1999-05-18 | 2003-02-05 | 2004-04-07 | 2005-12-07 | 2011 | 2012-02-07 | N/A | 1359 | N/A | N/A |  |  | 1.24 | 5332.8 | Unknown | Yes |  |  |  | N/A | 2920534 | 1.1878 | 3468934.3469 | [10 empty] | 0 |  |  |  |  | 32401.96 | 2017-12-29 | 2920534 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | Yes | No | Customer electrical panel conversion | None | N/A | N/A | None | N/A | N/A
SAN FRANCISCO | MID-FOLSOM ST - DIST.#350 - PH 1 | 30249631 | MID-FOLSOM ST - DIST# 350 - PH 1 | 94110 | 6075022901 | No | 8.491% | MID-FOLSOM ST - DIST# 350 - PH 1 | None | TBD | TBD | Yes | 81 | 0 | 0 | 0 | 80 | Unknown | No | 1999-05-18 | 2002-10-22 | 2004-02-26 | 2006-01-04 | 2012 | 2012-09-13 | N/A | 1253 | N/A | N/A |  |  | 1.31 | 3960 | Unknown | Yes |  |  |  | N/A | 3272662.79 | 1.121 | 3668790.1259 | [10 empty] | 0 |  |  |  |  | 88016 | 2017-12-29 | 3272662.79 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | Yes | No | Customer electrical panel conversion | None | N/A | N/A | None | N/A | N/A
SAN FRANCISCO | MID-FOLSOM ST. | 30334783 | MID-FOLSOM ST | 94110 | 6075022801 | No | 5.573% | MID-FOLSOM ST | None | TBD | TBD | Yes | 81 | 0 | 0 | 0 | 80 | Unknown | No | 1999-05-18 | 2004-02-03 | 2004-12-15 | 2006-03-31 | 2012 | 2012-09-13 | N/A | 1722 | N/A | N/A |  |  | 1.99 | 7708.8 | Unknown | Yes |  |  |  | N/A | 3565078.06 | 1.121 | 3996599.7183 | [10 empty] | 0 |  |  |  |  | 86612 | 2017-12-29 | 3565078.06 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | Yes | No | Customer electrical panel conversion | None | N/A | N/A | None | N/A | N/A
SAN FRANCISCO | OAK STREET (STANYAN- OAK) | 30400105 | OAK ST (STANYAN- OAK) | 94117 | 6075016600 | No | 2.762% | OAK ST (STANYAN- OAK) | None | TBD | TBD | Yes | 81 | 0 | 0 | 0 | 80 | Urban | No | 1999-06-21 | 2004-09-23 | 2005-05-05 | 2006-05-01 | 2008 | 2008-08-18 | N/A | 1921 | N/A | N/A |  |  | 0.52 | 2534.4 | Commercial | Yes |  |  |  | N/A | 1744118.29 | 1.3051 | 2276323.3985 | [6 empty] | Yes | N/A |  |  | 0 | [6 empty] | 1744118.29 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
SAN FRANCISCO | OAK STREET RULE 20A | 30297408 | OAK ST | 94117 | 6075016600 | No | 2.762% | OAK ST | None | TBD | TBD | Yes | 81 | 0 | 0 | 0 | 80 | Urban | No | 1999-06-21 | 2003-02-25 | 2003-05-02 | 2005-12-21 | 2010 | 2010-08-26 | N/A | 1345 | N/A | N/A |  |  | 0.13 | 105.6 | Commercial | Yes |  |  |  | N/A | 2037687 | 1.249 | 2545029.8252 | [6 empty] | Yes | N/A |  |  | 0 |  |  |  |  | 90704.33 | 2017-12-29 | 2037687 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
SAN FRANCISCO | OAKDALE/PALOU PH 2 | 30334786 | OAKDALE/PALOU PH 2 | 94124 | 6075023001 | No | 8.455% | OAKDALE ST, 3RD ST & KEITH ST | None | TBD | TBD | Yes | 81 | 0 | 0 | 0 | 80 | Unknown | No | 1999-11-22 | 2004-03-15 | 2005-08-05 | 2006-09-29 | 2014 | 2015-01-15 | N/A | 1575 | N/A | N/A | 1 |  | 2.95 | 8078.4 | Unknown | Yes |  |  |  | N/A | 7097063.45 | 1.0831 | 7686703.7022 | [10 empty] | 0 | [6 empty] | 7097063.45 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | Yes | No | Customer electrical panel conversion | None | N/A | N/A | None | N/A | N/A
SAN FRANCISCO | OAKDALE/PALOU/MENDELL PLAZA | 30340559 | OAKDALE/PALOU/MENDELL PLAZA | 94124 | Unknown | Unknown | Unknown | OAKDALE/PALOU/MENDELL PLAZA | Unknown | TBD | TBD | Yes | 81 | 0 | 0 | 0 | 80 | Unknown | Unknown | 1999-11-22 | 2003-10-14 | 2004-05-05 | 2006-02-02 | 2008 | 2008-08-18 | N/A | 1422 | N/A | N/A |  |  | No primary UG circuit data found | 0 | Unknown | Yes |  |  |  | N/A | 212547.3 | 1.3051 | 277404.5746 | [10 empty] | 0 | [6 empty] | 212547.3 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | Yes | No | Customer electrical panel conversion | None | N/A | N/A | None | N/A | N/A
SAN FRANCISCO | OC1 9TH & 10TH AVE/ORTEGA R20A CABLING | 30303305 | 9TH & 10TH AVE/ORTEGA | 94122 | 6075030301 | No | 2.58% | 9TH & 10TH AVE/ORTEGA | None | TBD | TBD | Yes | 81 | 0 | 0 | 0 | 80 | Unknown | No | 1999-10-27 | 2003-05-30 | 2003-07-29 | 2005-12-21 | 2010 | 2011-03-16 | N/A | 1311 | N/A | N/A |  |  | 2.53 | 7814.4 | Unknown | Yes |  |  |  | N/A | 2076535 | 1.249 | 2593550.191 | [10 empty] | 0 |  |  |  |  | 101627.18 | 2017-12-29 | 2076535 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | Yes | No | Customer electrical panel conversion | None | N/A | N/A | None | N/A | N/A
SAN FRANCISCO | OC1 EP CORBETT 1B - RULE 20A | 30249355 | CORBETT 1B | 94131 | 6075020402 | No | 3.903% | CORBETT 1B | None | TBD | TBD | Yes | 81 | 0 | 0 | 0 | 80 | Unknown | No | 1980-01-11 | 2002-05-07 | 2002-07-30 | 2006-09-06 | 2010 | 2011-03-16 | N/A | 8152 | N/A | N/A |  |  | 2.25 | 6758.4 | Unknown | Yes |  |  |  | N/A | 4673749 | 1.249 | 5837417.9158 | [10 empty] | 0 |  |  |  |  | 6701.6 | 2017-12-29 | 4673749 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | Yes | No | Customer electrical panel conversion | None | N/A | N/A | None | N/A | N/A
SAN FRANCISCO | OC1 GEP LIBERTY HILL 2 R20A W/GPRP | 30334696 | LIBERTY HILL 2 | 94114 | 6075021100 | No | 1.817% | LIBERTY HILL 2 | None | TBD | TBD | Yes | 81 | 0 | 0 | 0 | 80 | Unknown | No | 1998-01-14 | 2004-02-28 | 2004-10-26 | 2006-06-05 | 2010 | 2011-03-16 | N/A | 2236 | N/A | N/A |  |  | 1.14 | 3379.2 | Unknown | Yes |  |  |  | N/A | 3077951 | 1.249 | 3844298.5088 | [10 empty] | 0 |  |  |  |  | 8639.1 | 2017-12-29 | 3077951 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | Yes | No | Customer electrical panel conversion | None | N/A | N/A | None | N/A | N/A
SAN FRANCISCO | OC1 GEP LINCOLN WAY 5 RULE 20A W/GPRP | 30334792 | LINCOLN WAY 5 | 94122 | 6075030202 | No | 3.292% | LINCOLN WAY 5 | None | TBD | TBD | Yes | 81 | 0 | 0 | 0 | 80 | Unknown | No | 1999-03-01 | 2003-12-01 | 2005-06-07 | 2006-03-14 | 2010 | 2011-03-16 | N/A | 1736 | N/A | N/A | 67 |  | 1.97 | 4593.6 | Unknown | Yes |  |  |  | N/A | 3021505 | 1.249 | 3773798.5971 | [10 empty] | 0 |  |  |  |  | 33312.81 | 2017-12-29 | 3021505 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | Yes | No | Customer electrical panel conversion | None | N/A | N/A | None | N/A | N/A
SAN FRANCISCO | OC1 GES DOLORES ST R20/A PHASE 1 W/GPRP | 30222282 | DOLORES ST, PH 1 | 94114 | 6075020200 | No | 8.183% | DOLORES ST, PH 1 | None | TBD | TBD | Yes | 81 | 0 | 0 | 0 | 80 | Unknown | No | 1998-03-31 | 2001-10-13 | 2003-01-09 | 2005-05-12 | 2010 | 2011-03-16 | N/A | 1292 | N/A | N/A |  |  | 1.97 | 5596.8 | Unknown | No |  |  |  | N/A | 2871615 | 1.249 | 3586589.0205 | [10 empty] | 0 |  |  |  |  | 14493.21 | 2017-12-29 | 2871615 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | Yes | No | Customer electrical panel conversion | None | N/A | N/A | None | N/A | N/A
SAN FRANCISCO | OC1 GES SAN BRUNO 2 R20A PH1 W/GPRP,SF | 30223377 | SAN BRUNO 2 PH 1, SAN FRANCISCO | 94134 | 6075025702 | No | 8.403% | SAN BRUNO 2 PH 1, SAN FRANCISCO | None | TBD | TBD | Yes | 81 | 0 | 0 | 0 | 80 | Unknown | No | 1998-12-24 | 2001-10-29 | 2001-12-10 | 2005-05-17 | 2010 | 2011-03-16 | N/A | 1040 | N/A | N/A |  |  | 0.92 | 3009.6 | Unknown | Yes |  |  |  | N/A | 2077580 | 1.249 | 2594855.3749 | [10 empty] | 0 |  |  |  |  | 15528.52 | 2017-12-29 | 2077580 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | Yes | No | Customer electrical panel conversion | None | N/A | N/A | None | N/A | N/A
SAN FRANCISCO | OC1 GES SAN BRUNO 2 R20A PH2 W/GPRP SF | 30242967 | SAN BRUNO 2 PH 2, SAN FRANCISCO | 94134 | 6075025800 | No | 9.286% | SAN BRUNO 2 PH 2, SAN FRANCISCO | None | TBD | TBD | Yes | 81 | 0 | 0 | 0 | 80 | Unknown | No | 1998-12-24 | 2002-09-30 | 2004-03-15 | 2007-07-16 | 2010 | 2011-03-16 | N/A | 1376 | N/A | N/A |  |  | 2.77 | 6864 | Unknown | No |  |  |  | N/A | 3927267 | 1.249 | 4905077.0047 | [10 empty] | 0 |  |  |  |  | 12573.14 | 2017-12-29 | 3927267 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | Yes | No | Customer electrical panel conversion | None | N/A | N/A | None | N/A | N/A
SAN FRANCISCO | OC1 GES TEXAS/19TH ST. SF RL20A W/GPRP | 30222281 | TEXAS/19TH ST, SAN FRANCISCO | 94107 | 6075022702 | No | 1.602% | TEXAS/19TH ST, SAN FRANCISCO | None | TBD | TBD | Yes | 81 | 0 | 0 | 0 | 80 | Unknown | No | 1998-03-27 | 2001-11-03 | 2003-03-04 | 2005-12-07 | 2010 | 2011-03-16 | N/A | 1317 | N/A | N/A |  |  | 1.25 | 7286.4 | Unknown | Yes |  |  |  | N/A | 2348558 | 1.249 | 2933301.4129 | [10 empty] | 0 |  |  |  |  | -5427.54 | 2017-12-29 | 2348558 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | Yes | No | Customer electrical panel conversion | None | N/A | N/A | None | N/A | N/A
SAN FRANCISCO | OCEAN AVE - DIST.#338 - PH 4 | 30400280 | OCEAN AVE - DIST# 338 - PH 4 | 94112 | 6075025500 | No | 4.84% | OCEAN AVE - DIST# 338 - PH 4 | None | TBD | TBD | Yes | 81 | 0 | 0 | 0 | 80 | Unknown | No | 1998-03-31 | 2004-09-27 | 2005-10-14 | 2006-05-10 | 2012 | 2012-09-13 | N/A | 2372 | N/A | N/A |  |  | 2.06 | 4963.2 | Unknown | Yes |  |  |  | N/A | 3741504.31 | 1.121 | 4194380.8298 | [10 empty] | 0 |  |  |  |  | 51019.14 | 2017-12-29 | 3741504.31 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | Yes | No | Customer electrical panel conversion | None | N/A | N/A | None | N/A | N/A
SAN FRANCISCO | OCEAN AVE PH 2 (SUBSTRUCTURE PORTION) | 30180213 | OCEAN AVE, PH 2 | TBD | Unknown | Unknown | Unknown | OCEAN AVE, PH 2 | Unknown | TBD | TBD | Yes | 81 | 0 | 0 | 0 | 80 | Urban | Unknown | 1998-03-31 | 2001-04-21 | 2002-04-03 | 2003-02-12 | 2008 | 2009-03-17 | N/A | 1117 | N/A | N/A |  |  | No primary UG circuit data found | 7814.4 | Commercial | No |  |  |  | N/A | 2000195.42 | 1.3051 | 2610540.6165 | [6 empty] | Unknown | Unknown |  |  | 0 | [6 empty] | 2000195.42 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | Yes | No | Customer electrical panel conversion | None | N/A | N/A | None | N/A | N/A
SAN FRANCISCO | OCEAN AVE, PHASE 1 | 30011544 | OCEAN AVE, PH 1 | TBD | Unknown | Unknown | Unknown | OCEAN AVE, PH 1 | Unknown | TBD | TBD | Yes | 81 | 0 | 0 | 0 | 80 | Urban | Unknown | 1998-03-31 | 1998-10-19 | 2001-04-09 | 2001-07-23 | 2008 | 2008-08-18 | N/A | 202 | N/A | N/A | 20 | 7 | No primary UG circuit data found | 12566.4 | Commercial | Yes |  |  |  | N/A | 1726898.3 | 1.3051 | 2253848.8528 | [6 empty] | Unknown | Unknown |  |  | 0 | [6 empty] | 1726898.3 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | Yes | No | Customer electrical panel conversion | None | N/A | N/A | None | N/A | N/A
SAN FRANCISCO | OCEAN AVE, PHASE 3A | 30235385 | OCEAN AVE, PH 3A | TBD | Unknown | Unknown | Unknown | OCEAN AVE, PH 3A | Unknown | TBD | TBD | Yes | 81 | 0 | 0 | 0 | 80 | Unknown | Unknown | 1998-03-31 | 2001-12-06 | 2002-04-12 | 2003-03-27 | 2008 | 2008-08-18 | N/A | 1346 | N/A | N/A |  |  | No primary UG circuit data found | 211.2 | Unknown | Yes |  |  |  | N/A | 1535301.74 | 1.3051 | 2003787.9853 | [10 empty] | 0 | [6 empty] | 1535301.74 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | Yes | No | Customer electrical panel conversion | None | N/A | N/A | None | N/A | N/A
SAN FRANCISCO | OCEAN AVE, PHASE 3A/B CBL/OH | 30267444 | OCEAN AVE, PH 3A/B | 94112 | 6075031201 | No | 6.583% | OCEAN AVE, PH 3A/B | None | TBD | TBD | Yes | 81 | 0 | 0 | 0 | 80 | Unknown | No | 1998-03-31 | 2002-07-01 | 2002-11-01 | 2003-03-27 | 2007 | 2007-07-31 | N/A | 1553 | N/A | N/A |  |  | 2.16 | 5702.4 | Unknown | Yes |  |  |  | N/A | 1312087.82 | 1.4306 | 1877042.9558 | [10 empty] | 0 | [6 empty] | 1312087.82 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | Yes | No | Customer electrical panel conversion | None | N/A | N/A | None | N/A | N/A
SAN FRANCISCO | OCEAN AVE, PHASE II CABLING | 30237178 | OCEAN AVE, PH 2 | 94127 | 6075030900 | No | 1.747% | OCEAN AVE, PH 2 | None | TBD | TBD | Yes | 81 | 0 | 0 | 0 | 80 | Unknown | No | 1998-03-31 | 2002-01-31 | 2002-07-26 | 2002-10-17 | 2007 | 2007-07-31 | N/A | 1402 | N/A | N/A |  |  | 1.51 | 5121.6 | Unknown | Yes |  |  |  | N/A | 989722.61 | 1.4306 | 1415874.6274 | [10 empty] | 0 | [6 empty] | 989722.61 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | Yes | No | Customer electrical panel conversion | None | N/A | N/A | None | N/A | N/A
SAN FRANCISCO | OCEAN AVE, PHASE III-B SUBST | 30239753 | OCEAN AVE, PH 3-B | TBD | Unknown | Unknown | Unknown | OCEAN AVE, PH 3-B | Unknown | TBD | TBD | Yes | 81 | 0 | 0 | 0 | 80 | Unknown | Unknown | 1998-03-31 | 2002-01-15 | 2003-01-14 | 2003-01-14 | 2007 | 2007-07-31 | N/A | 1386 | N/A | N/A |  |  | No primary UG circuit data found | 792 | Unknown | No |  |  |  | N/A | 697184.43 | 1.4306 | 997376.1689 | [10 empty] | 0 | [6 empty] | 697184.43 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | Yes | No | Customer electrical panel conversion | None | N/A | N/A | None | N/A | N/A
SAN FRANCISCO | PC PRESIDIO HTS 4A, SF | 30014022 | PRESIDIO HTS 4A, SAN FRANCISCO | 94118 | 6075015400 | No | 3.256% | PRESIDIO HTS 4A, SAN FRANCISCO | None | TBD | TBD | Yes | 81 | 0 | 0 | 0 | 80 | Unknown | No | 1979-05-18 | 1998-07-01 | 1998-10-14 | 2000-06-21 | 2010 | 2010-08-26 | N/A | 6984 | N/A | N/A |  |  | 0.94 | 2851.2 | Unknown | Yes |  |  |  | N/A | 2203646 | 1.249 | 2752309.2576 | [10 empty] | 0 | [6 empty] | 2203646 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | Yes | No | Customer electrical panel conversion | None | N/A | N/A | None | N/A | N/A
SAN FRANCISCO | PRESIDIO HTS. 4C W/GPRP | 30249633 | PRESIDIO HTS 4C | 94118 | 6075013300 | No | 0.6853% | PRESIDIO HTS 4C | None | TBD | TBD | Yes | 81 | 0 | 0 | 0 | 80 | Unknown | No | 1979-05-18 | 2003-11-18 | 2003-11-20 | 2006-06-30 | 2009 | 2009-07-29 | N/A | 8950 | N/A | N/A |  |  | 1.28 | 3748.8 | Unknown | Yes |  |  |  | N/A | 2918860.03 | 1.2297 | 3589259.9697 | [10 empty] | 0 | [6 empty] | 2918860.03 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | Yes | No | Customer electrical panel conversion | None | N/A | N/A | None | N/A | N/A
SAN FRANCISCO | PRESIDIO HTS., PHASE 3 | 30245221 | PRESIDIO HTS, PH 3 | 94118 | 6075013300 | No | 0.6853% | PRESIDIO HTS, PH 3 | None | TBD | TBD | Yes | 81 | 0 | 0 | 0 | 80 | Unknown | No | 1979-05-18 | 2002-03-12 | 2002-11-12 | 2004-08-10 | 2009 | 2009-07-29 | N/A | 8334 | N/A | N/A |  |  | 1.58 | 8606.4 | Unknown | Yes |  |  |  | N/A | 2312220.27 | 1.2297 | 2843287.986 | [10 empty] | 0 | [6 empty] | 2312220.27 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | Yes | No | Customer electrical panel conversion | None | N/A | N/A | None | N/A | N/A
SAN FRANCISCO | STILLMAN STREET | 30328762 | STILLMAN ST | 94107 | 6075061500 | No | 3.738% | STILLMAN ST | None | TBD | TBD | Yes | 81 | 0 | 0 | 0 | 80 | Unknown | No | 2000-07-28 | 2003-07-29 | 2004-01-05 | 2004-04-19 | 2007 | 2008-02-15 | N/A | 1096 | N/A | N/A |  |  | 0.2 | 686.4 | Unknown | No |  |  |  | N/A | 496270.32 | 1.4306 | 709953.0185 | [10 empty] | 0 | [6 empty] | 496270.32 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | Yes | No | Customer electrical panel conversion | None | N/A | N/A | None | N/A | N/A
SAN FRANCISCO | TARAVAL - DIST.#346 - PH 2 | 30383452 | TARAVAL - DIST# 346 - PH 2 | 94116 | 6075032801 | No | 4.106% | TARAVAL - DIST# 346 - PH 2 | None | TBD | TBD | Yes | 81 | 0 | 0 | 0 | 80 | Unknown | No | 1999-02-17 | 2004-06-14 | 2005-11-15 | 2006-11-01 | 2012 | 2012-09-13 | N/A | 1944 | N/A | N/A |  |  | 2.8 | 6600 | Unknown | Yes |  |  |  | N/A | 8860553.91 | 1.121 | 9933046.8127 | [10 empty] | 0 |  |  |  |  | 274970 | 2017-12-29 | 8860553.91 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | Yes | No | Customer electrical panel conversion | None | N/A | N/A | None | N/A | N/A
San Francisco County Total | [41 empty] | 0
San Joaquin County | [41 empty] | 0
ESCALON | FIRST STREET, ESCALON | No Order | FIRST STREET | 95320 | 6077004901 | No | 9.44% | FIRST STREET BTW STATE ROUTE 120 & MCHENRY AVE | None | Project met one or more Rule 20A criteria | Resolution# 34-19 | No | 23 | 3 | 3 | 0 | 17 | Suburban | No | 2019-07-15 | TBD | TBD | TBD | TBD | N/A | N/A | #VALUE! | 0 | N/A | 0 | 0 | Project not completed or closed | Project not completed or closed | Commercial | Unknown | TBD | TBD | TBD | 2150178.89 | N/A | TBD | N/A | [6 empty] | TBD | TBD | [6 empty] | Project in planning phase |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | Yes | No | No | Insufficient allocation | None | N/A | N/A | No | N/A | N/A
LATHROP | LOUISE AVE | 30306856 | LOUISE AVE | 95330 | 6077005129 | Yes | 13.46% | LOUISE AVE | None | TBD | TBD | Yes | 23 | 3 | 3 | 0 | 17 | Unknown | Yes | 2002-02-19 | 2005-03-14 | 2005-07-15 | 2005-10-31 | 2007 | 2007-07-31 | N/A | 1119 | N/A | N/A |  |  | 0.34 | 1795.2 | Unknown | Unknown |  |  |  | N/A | 520569.47 | 1.4306 | 744714.8291 | [10 empty] | 0 |  |  |  | Unknown |  |  | 520569.47 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
RIPON | 259 N. WILMA AVE, RIPON | 30406567 | 259 N WILMA AVE, RIPON | 95366 | 6077005001 | No | 8.152% | 259 N WILMA AVE, RIPON | None | TBD | TBD | Yes | 23 | 3 | 3 | 0 | 17 | Unknown | No | 2003-05-20 | 2005-04-25 | 2006-08-28 | 2007-03-06 | 2008 | 2009-03-17 | N/A | 706 | N/A | N/A |  |  | 0.82 | 3115.2 | Unknown | Unknown |  |  |  | N/A | 866091.4 | 1.3051 | 1130372.9399 | [10 empty] | 0 |  |  |  | Unknown |  |  | 866091.4 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
RIPON | STOCKTON AVE, RIPON | No Order | UUD 05-1 STOCKTON AVE | 95366 | 6077005001 | No | 8.116% | STOCKTON AVE BTW FIFTH ST & MAIN ST | None | Project met one or more Rule 20A criteria | Resolution# 05-63 | No | 23 | 3 | 3 | 0 | 17 | Rural | No | 2005-08-06 | TBD | TBD | TBD | TBD | N/A | N/A | #VALUE! | 0 | N/A | 0 | 0 | Project not completed or closed | Project not completed or closed | Residential | Unknown | TBD | TBD | TBD | 3084183 | N/A | TBD | N/A | [6 empty] | TBD | TBD | [6 empty] | Project in planning phase |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | Yes | No | No | Insufficient allocation | None | N/A | N/A | No | N/A | N/A
SAN JOAQUIN COUNTY | EP WOODBRIDGE RULE 20A | 30112580 | WOODBRIDGE | 95258 | 6077004105 | No | 6.85% | WOODBRIDGE | None | TBD | TBD | Yes | 23 | 3 | 3 | 0 | 17 | Unknown | No | TBD | 1999-12-30 | 2003-05-07 | 2003-12-11 | 2006 | 2007-03-24 | N/A | #VALUE! | N/A | N/A |  |  | 1.01 | 3326.4 | Unknown | Unknown |  |  |  | N/A | 1165390.96 | 1.591 | 1854097.4666 | [10 empty] | 0 |  |  |  | Unknown |  |  | 1165390.96 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
SAN JOAQUIN COUNTY | HAMMER LANE RULE 20A-SJ CO. PART | 30292479 | HAMMER LN, SAN JOAQUIN COUNTY | 95212 | 6077003500 | Yes | 10.06% | HAMMER LN, SAN JOAQUIN COUNTY | None | TBD | TBD | Yes | 23 | 3 | 3 | 0 | 17 | Unknown | Yes | 2003-01-21 | 2003-02-24 | 2004-11-01 | 2005-05-25 | 2010 | 2010-08-26 | N/A | 34 | N/A | N/A |  |  | 1.21 | 5068.8 | Unknown | Unknown |  |  |  | N/A | 994499 | 1.249 | 1242109.1248 | [10 empty] | 0 |  |  |  | Unknown |  |  | 994499 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
SAN JOAQUIN COUNTY | LOWER SACRAMENTO, SAN JOAQUIN CNTY | 30771373 | LOWER SACRAMENTO | 95242 | 6077004102 | No | 9.638% | LOWER SACRAMENTO, EIGHT MILE RD & HARNEY LN | None | Project met one or more Rule 20A criteria | Resolution# 10-139 | Yes | 23 | 3 | 3 | 0 | 17 | Suburban | No | 2010-04-06 | 2011-01-12 | 2015-03-16 | 2015-12-14 | 2017 | 2017-04-14 | N/A | 281 | N/A | N/A | 82 | 26 | 5.62 | 15364.8 | Agricultural | Yes |  |  |  | N/A | 7303864.04 | 1.048 | 7654770.5037 | [6 empty] | 0 | N/A |  |  | 0 |  |  |  | Unexpected field conditions |  |  | 7303864.04 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Yes | Yes | Unknown | Yes | No | Yes | Yes | Communication decided to install their own separate trench | None | N/A | N/A | None | N/A | N/A
STOCKTON | *CANC* AIRPORT WAY PH2 STOCKTON R20A | 30766533 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | 23 | 3 | 3 | 0 | 17 | N/A | N/A | 2005-01-25 | TBD | TBD | TBD | N/A | N/A | N/A | #VALUE! | N/A | 2012-11-04 | N/A | N/A | Cancelled project | Cancelled project | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [6 empty] | N/A | N/A |  |  | 0 |  |  |  | N/A, project cancelled |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
STOCKTON | AIRPORT WAY | 30454611 | AIRPORT WAY | 95206 | 6077002201 | Yes | 20.89% | AIRPORT WAY | None | TBD | TBD | Yes | 23 | 3 | 3 | 0 | 17 | Urban | Yes | 2005-01-04 | 2006-02-08 | 2007-01-25 | 2007-07-12 | 2009 | 2009-07-29 | N/A | 400 | N/A | N/A | 19 | 2 | 0.87 | 4171.2 | Commercial | Yes |  |  |  | N/A | 1082550.78 | 1.2297 | 1331189.6219 | [6 empty] | 0 | N/A |  |  | 0 |  |  |  | Unexpected field conditions |  |  | 1082550.78 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | No | No | None | None | N/A | N/A | None | N/A | N/A
STOCKTON | EL DORADO ST, PH 1 | 30402155 | EL DORADO ST, PH 1 | 95204 | 6077001400 | Yes | 18.33% | EL DORADO ST, PH 1 | None | TBD | TBD | Yes | 23 | 3 | 3 | 0 | 17 | Urban | Yes | 1998-08-25 | 2004-12-21 | 2006-09-28 | 2007-05-18 | 2009 | 2009-07-29 | N/A | 2310 | N/A | N/A | 36 | 16 | 0.68 | 2217.6 | Commercial | Yes |  |  |  | N/A | 1284245.91 | 1.2297 | 1579209.8246 | [6 empty] | 6000 | 1% |  |  | 0 |  |  |  | Restrictive work conditions |  |  | 1284245.91 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Yes | No | No | No | No | No | No | None | None | N/A | N/A | None | N/A | N/A
STOCKTON | EL DORADO ST, PH 2 | 30469953 | EL DORADO ST, PH 2 | 95204 | 6077001400 | Yes | 18.33% | EL DORADO ST, PH 2 | None | TBD | TBD | Yes | 23 | 3 | 3 | 0 | 17 | Urban | Yes | 1998-08-25 | 2005-11-18 | 2006-10-20 | 2008-01-28 | 2009 | 2009-07-29 | N/A | 2642 | N/A | N/A | 16 | 0 | 0.72 | 2428.8 | Residential | No |  |  |  | N/A | 1018164.47 | 1.2297 | 1252015.1488 | [6 empty] | 0 | N/A |  |  | 0 |  |  |  | Unexpected field conditions |  |  | 1018164.47 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Yes | Yes | Unknown | Yes | No | Yes | No | Easement acquisitions | None | N/A | N/A | None | N/A | N/A
STOCKTON | EP CITY OF STKN EL DORADO ST -RULE 20A | 30194569 | CITY OF STOCKTON EL DORADO ST | 95207 | 6077003312 | Yes | 21.24% | CITY OF STOCKTON EL DORADO ST | None | TBD | TBD | Yes | 23 | 3 | 3 | 0 | 17 | Unknown | Yes | TBD | 2001-06-01 | 2002-01-14 | 2003-01-23 | 2005 | 2007-03-24 | N/A | #VALUE! | N/A | N/A |  |  | 0.48 | 3168 | Unknown | Unknown |  |  |  | N/A | 386955.72 | 1.7065 | 660344.079 | [10 empty] | 0 |  |  |  | Unknown |  |  | 386955.72 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
STOCKTON | EP RULE 20A, LOWER SACRAMENTO RD., STKN. | 30222303 | LOWER SACRAMENTO RD, STOCKTON | 95210 | 6077003311 | No | 19.5% | LOWER SACRAMENTO RD, STOCKTON | None | TBD | TBD | Yes | 23 | 3 | 3 | 0 | 17 | Unknown | No | 1998-08-25 | 2002-01-22 | 2003-05-06 | 2003-11-14 | 2006 | 2007-03-24 | N/A | 1246 | N/A | N/A |  |  | 1.3 | 5438.4 | Unknown | Unknown |  |  |  | N/A | 939974.34 | 1.591 | 1495467.2743 | [10 empty] | 0 |  |  |  | Unknown |  |  | 939974.34 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
STOCKTON | FREMONT STREET PH2 STOCKTON R20A | 30657289 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | 23 | 3 | 3 | 0 | 17 | N/A | N/A | 2003-09-23 | TBD | TBD | TBD | N/A | N/A | N/A | #VALUE! | N/A | 2015-09-21 | N/A | N/A | Cancelled project | Cancelled project | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [6 empty] | N/A | N/A |  |  | 0 |  |  |  | N/A, project cancelled |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
STOCKTON | HAMMER LANE, STOCKTON | 30292474 | HAMMER LN, STOCKTON | 95212 | 6077003500 | Yes | 10.06% | HAMMER LN, STOCKTON | None | TBD | TBD | Yes | 23 | 3 | 3 | 0 | 17 | Unknown | Yes | 2002-08-27 | 2003-02-04 | 2004-08-06 | 2005-05-25 | 2008 | 2009-03-17 | N/A | 161 | N/A | N/A |  |  | 0.53 | 2798.4 | Unknown | Unknown |  |  |  | N/A | 486964.2 | 1.3051 | 635557.8111 | [10 empty] | 0 |  |  |  | Unknown |  |  | 486964.2 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
STOCKTON | PERSHING AVE, PH 2 | 30613816 | PERSHING AVE, PH 2 | 95204 | 6077001200 | Yes | 6.298% | PERSHING AVE, PH 2 | None | TBD | TBD | Yes | 23 | 3 | 3 | 0 | 17 | Urban | Yes | 2003-03-23 | 2008-04-29 | 2009-04-16 | 2010-03-10 | 2012 | 2012-09-13 | N/A | 1864 | N/A | N/A | 51 | 4 | 1.93 | 5491.2 | Residential | Yes |  |  |  | N/A | 3406041.39 | 1.121 | 3818313.0442 | [6 empty] | 20000 | 0.003% |  |  | 0 |  |  |  | Restrictive work conditions |  |  | 3406041.39 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Yes | No | Yes | No | No | No | No | None | None | N/A | N/A | None | N/A | N/A
STOCKTON | PERSHING STREET | 30339035 | PERSHING ST | 95203 | 6077000900 | Yes | 18.48% | PERSHING ST | None | TBD | TBD | Yes | 23 | 3 | 3 | 0 | 17 | Unknown | Yes | 2003-03-23 | 2003-10-16 | 2004-05-07 | 2004-12-03 | 2007 | 2008-02-15 | N/A | 207 | N/A | N/A |  |  | 0.43 | 1689.6 | Unknown | Unknown |  |  |  | N/A | 697055.19 | 1.4306 | 997191.2811 | [10 empty] | 0 |  |  |  | Unknown |  |  | 697055.19 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
STOCKTON | RULE 20A - FREMONT STREET - STOCKTON | 30339206 | FREMONT ST, STOCKTON | 95203 | 6077000300 | Yes | 30.47% | FREMONT ST, STOCKTON | None | TBD | TBD | Yes | 23 | 3 | 3 | 0 | 17 | Unknown | Yes | TBD | 2003-12-17 | 2004-07-07 | 2004-08-24 | 2006 | 2007-03-24 | N/A | #VALUE! | N/A | N/A |  |  | 0.44 | 1795.2 | Unknown | Unknown |  |  |  | N/A | 624415.42 | 1.591 | 993423.742 | [10 empty] | 0 |  |  |  | Unknown |  |  | 624415.42 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
STOCKTON | SOUTHSHORE PH2 STOCKTON R20A | 30425691 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | 23 | 3 | 3 | 0 | 17 | N/A | N/A | 1986-03-04 | TBD | TBD | TBD | N/A | N/A | N/A | #VALUE! | N/A | 2015-09-08 | N/A | N/A | Cancelled project | Cancelled project | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [6 empty] | N/A | N/A |  |  | 0 |  |  |  | N/A, project cancelled |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
STOCKTON | SOUTHSHORE PHASE 1 | 30359162 | SOUTHSHORE PH 1 | 95203 | 6077000300 | Yes | 30.47% | SOUTHSHORE PH 1 | None | TBD | TBD | Yes | 23 | 3 | 3 | 0 | 17 | Unknown | Yes | 1986-03-04 | 2004-03-02 | 2004-04-27 | 2005-05-10 | 2007 | 2007-07-31 | N/A | 6573 | N/A | N/A |  |  | 0.18 | 950.4 | Unknown | Unknown |  |  |  | N/A | 164931.5 | 1.4306 | 235947.248 | [10 empty] | 0 |  |  |  | Unknown |  |  | 164931.5 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
STOCKTON | DOWNTOWN STOCKTON R20A | 35029720 | STOCKTON DOWNTOWN AREA | 95202 | 6077000100 | Yes | 28.11% | MINER AVE, AURORA ST, WEBER AVE, SUTTER ST | None | Project met one or more Rule 20A criteria | Resolution# 2017-10-17-1113 | No | 23 | 3 | 3 | 0 | 17 | Rural | Yes | 2017-11-07 | 2018-11-01 | TBD | TBD | TBD | N/A | N/A | 359 | 2020-12-31 | N/A | 0 | 0 | Project not completed or closed | Project not completed or closed | Residential | Yes | TBD | TBD | TBD | 2744000 | N/A | TBD | N/A | [6 empty] | TBD | TBD | [6 empty] | Project in planning phase |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | Yes | No | No | Insufficient allocation | None | N/A | N/A | No | N/A | N/A
TRACY | EP: RULE 20 CITY OF TRACY [FIREHOUSE] | 30229236 | CITY OF TRACY [FIREHOUSE] | 95376 | 6077005308 | No | 12.51% | CITY OF TRACY [FIREHOUSE] | None | TBD | TBD | Yes | 23 | 3 | 3 | 0 | 17 | Unknown | No | TBD | 2003-03-31 | 2003-09-24 | 2004-08-10 | 2005 | 2007-03-24 | N/A | #VALUE! | N/A | N/A |  |  | 0.11 | 844.8 | Unknown | Unknown |  |  |  | N/A | 242942.7034 | 1.7065 | 414584.3243 | [10 empty] | 0 |  |  |  | Unknown |  |  | 242942.7034 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
TRACY | GRANT LINE RD, PH 2 | 30767869 | GRANT LINE RD, PH 2 | 95376 | 6077005303 | Yes | 15.94% | GRANT LINE RD, PARKER AVE & HOLLY DR | None | TBD | Resolution# 96-347 | Yes | 23 | 3 | 3 | 0 | 17 | Urban | Yes | 1996-11-19 | 2010-04-22 | 2001-02-14 | 2012-05-22 | 2013 | 2014-02-28 | N/A | 4902 | N/A | N/A | 9 | 6 | 0.48 | 2534.4 | Commercial | Yes |  |  |  | N/A | 749975 | 1.1048 | 828575.3147 | [6 empty] | 0 | N/A |  |  | 0 |  |  |  | 3rd party cost variance |  |  | 749975 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | Unknown | Unknown | Unknown | No | No | No | None | None | N/A | N/A | None | N/A | N/A
San Joaquin County Total | [41 empty] | 0
San Luis Obispo County | [41 empty] | 0
ARROYO GRANDE | E PC GRAND AVE-101 TO HALCYON,AG | 30093824 | GRAND AVE, HWY 101 TO HALCYON, ARROYO GRANDE | 93420 | 6079011901 | No | 6.227% | GRAND AVE, HWY 101 TO HALCYON, ARROYO GRANDE | None | TBD | TBD | Yes | 20 | 3 | 2 | 1 | 12 | Unknown | No | TBD | 1999-08-09 | 1999-09-14 | 2000-08-24 | 2005 | 2007-03-24 | N/A | #VALUE! | N/A | N/A |  |  | 0.5 | 2376 | Unknown | Yes |  |  |  | N/A | 727377.37 | 1.7065 | 1241277.2694 | [10 empty] | 0 | [6 empty] | 727377.37 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | No | No | None | None | N/A | N/A | None | N/A | N/A
ARROYO GRANDE | GRAND AVE [ELM TO HALCYON], ARROYO GRANDE | 30485630 | EAST GRAND AVE, UUD# 6 | 93420 | Unknown | Unknown | Unknown | EAST GRAND AVE, ELM & HALCYON | Unknown | Project met one or more Rule 20A criteria | Resolution# 3896 | No | 20 | 3 | 2 | 1 | 12 | Unknown | Unknown | 2005-12-13 | TBD | TBD | TBD | TBD | N/A | N/A | #VALUE! | 2022-12-31 | N/A |  |  | Project not completed or closed | Project not completed or closed | Unknown | Unknown | TBD | TBD | TBD | 2861028.07 | N/A | TBD | N/A | [6 empty] | TBD | TBD |  |  | 0 |  |  |  | Project in planning phase |  |  | N/A |  |  |  |  | Yes | 3000000 | San Luis Obispo County | N/A | 150000 | PG&E does not grant approval for credit transfer transactions. Credit transfers are agreed upon between communities. | No | Yes | No | No | Yes | No | No | Insufficient allocation | None | N/A | N/A | None | N/A | N/A
ARROYO GRANDE | GRAND AVE [OAK PARK TO ELM] | 30323741 | GRAND AVE | 93420 | 6079011902 | No | 8.927% | EAST GRAND AVE, ELM ST & HALCYON RD | None | TBD | Resolution# 3896 | Yes | 20 | 3 | 2 | 1 | 12 | Suburban | No | 2003-03-25 | 2003-10-16 | 2013-02-18 | 2013-08-16 | 2015 | 2016-01-13 | N/A | 205 | N/A | N/A | 26 | 9 | 1.13 | 3115.2 | Commercial | Yes |  |  |  | N/A | 2312479.78 | 1.0677 | 2469088.227 | [6 empty] | 52545 | 100% |  |  | 0 |  |  |  | Other |  |  | 2312479.78 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | Yes | No | No | No | No | Removing poles | None | N/A | N/A | None | N/A | N/A
GROVER BEACH | *CANC*RAMONA AVE GROVER BEACH R20A | 30794542 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | 20 | 3 | 2 | 1 | 12 | N/A | N/A | 2009-11-02 | TBD | TBD | TBD | N/A | N/A | N/A | #VALUE! | N/A | 2015-10-03 | N/A | N/A | Cancelled project | Cancelled project | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [6 empty] | N/A | N/A |  |  | 0 |  |  |  | N/A, project cancelled |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GROVER BEACH | OAK PARK BLVD | 30323751 | OAK PARK BLVD | 93433 | 6079012000 | No | 8.739% | OAK PARK BLVD | None | TBD | TBD | Yes | 20 | 3 | 2 | 1 | 12 | Suburban | No | 2002-12-16 | 2003-10-30 | 2010-09-23 | 2011-02-03 | 2012 | 2012-09-13 | N/A | 318 | N/A | N/A | 14 | 11 | 0.52 | 2481.6 | Residential | No |  |  |  | N/A | 1169785.93 | 1.121 | 1311378.3316 | [6 empty] | 9000 | 100% |  |  | 0 |  |  |  | Initial job estimate incomplete, labor costs |  |  | 1169785.93 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | No | No | No | None | None | N/A | N/A | None | N/A | N/A
MORRO BAY | C:EP MORRO BAY BLVD, 20A, MORRO BAY | 30186000 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | 20 | 3 | 2 | 1 | 12 | N/A | N/A | 1998-04-13 | TBD | TBD | TBD | N/A | 2007-03-24 | N/A | #VALUE! | N/A | 2006-09-30 | N/A | N/A | Cancelled project | Cancelled project | N/A | N/A | N/A | N/A | N/A | N/A | 3811 | 1.4306 | 5451.9298 | [6 empty] | N/A | N/A |  |  | 0 |  |  |  | N/A, project cancelled |  |  | 3811 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MORRO BAY | MAIN & BEACH STREETS., MORRO BAY | 74001552 | MAIN & BEACH ST, UUD# 7 | 93442 | Unknown | Unknown | Unknown | MAIN ST, DUNES ST & STATE HWY 1 & BEACH ST, MAIN ST & WEST ST | Unknown | Project met one or more Rule 20A criteria | Resolution# 02-06 | No | 20 | 3 | 2 | 1 | 12 | Suburban | Unknown | 2006-01-09 | 2014-09-24 | TBD | TBD | N/A | 2018-10-23 | N/A | 3180 | N/A | 2018-05-22 | TBD | TBD | Cancelled project | Cancelled project | Commercial | No | TBD | TBD | TBD | N/A | 332719.22 | TBD | 332719.22 | [6 empty] | TBD | TBD |  |  | 0 |  |  |  | N/A, project cancelled |  |  | 332719.22 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | Yes | No | No | Insufficient allocation | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
PASO ROBLES | *CANC*RULE 20A 6TH-9TH & 9TH-10TH, *CANC | 80006843 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | 20 | 3 | 2 | 1 | 12 | N/A | N/A | 2005-10-28 | TBD | TBD | TBD | N/A | N/A | N/A | #VALUE! | N/A | 2009-06-26 | N/A | N/A | Cancelled project | Cancelled project | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [6 empty] | N/A | N/A |  |  | 0 |  |  |  | N/A, project cancelled |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PASO ROBLES | RIVERSIDE AVE | 30794479 | RIVERSIDE AVE | 93446 | 6079010102 | No | 13.82% | RIVERSIDE AVE, 10TH ST & 24TH ST | None | Project met one or more Rule 20A criteria | Resolution# 08-155 | Yes | 20 | 3 | 2 | 1 | 12 | Suburban | No | 2008-10-21 | 2014-04-01 | 2014-09-29 | 2015-04-28 | 2016 | 2016-07-20 | N/A | 1988 | N/A | N/A | 14 | 15 | 1.1 | 3168 | Commercial | Yes |  |  |  | N/A | 2720690.18 | 1.0668 | 2902519.2142 | [6 empty] | 21621 | 100% |  |  | 0 |  |  |  | Material costs |  |  | 2720690.18 |  |  |  |  | Yes | 500000 | Atascadero | 18.38% | 0 | PG&E does not grant approval for credit transfer transactions. Credit transfers are agreed upon between communities. | No | No | No | No | No | No | No | Cultural issues | None | N/A | N/A | Yes | None - Taken care of by the city | 0
PISMO BEACH | SHELL BEACH RD, PISMO BEACH | 74001553 | SHELL BEACH RD, PISMO BEACH | 93449 | Unknown | Unknown | Unknown | SHELL BEACH RD, VISTA DEL MAR & CLIFF AVE | Unknown | Project met one or more Rule 20A criteria | Resolution# 2006-035 | No | 20 | 3 | 2 | 1 | 12 | Suburban | Unknown | 2006-05-01 | 2014-12-11 | 2018-09-28 | 2019-11-19 | TBD | N/A | N/A | 3146 | 2019-11-01 | N/A | 49 | 8 | Project not completed or closed | Project not completed or closed | Commercial | Yes | TBD | TBD | TBD | 5394264.66 | N/A | TBD | N/A | [6 empty] | TBD | TBD |  |  | 0 |  |  |  | Unexpected field conditions |  |  | N/A |  |  |  |  | Yes | 3449511 | San Luis Obispo County, King City, Kings County | N/A | 400000 | PG&E does not grant approval for credit transfer transactions. Credit transfers are agreed upon between communities. | No | No | No | No | No | No | No | 0 | None | N/A | N/A | None | N/A | N/A
SAN LUIS OBISPO COUNTY | C:EP CO OF SLO 20A, N. MORRO BAY HWY 1 R | 30148680 | COUNTY OF SAN LUIS OBISPO, N MORRO BAY HWY 1 | 93430 | 6079010504 | No | 5.054% | COUNTY OF SAN LUIS OBISPO, N MORRO BAY HWY 1 | None | TBD | TBD | Yes | 20 | 3 | 2 | 1 | 12 | Rural | No | TBD | 2000-08-02 | 2004-09-30 | 2004-11-04 | 2006 | 2007-03-24 | N/A | #VALUE! | N/A | N/A |  |  | 1 | 5280 | Commercial | Yes |  |  |  | N/A | 637238.65 | 1.591 | 1013825.0657 | [10 empty] | 0 | [6 empty] | 637238.65 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | No | No | None | None | N/A | N/A | None | N/A | N/A
SAN LUIS OBISPO COUNTY | C:EP CO OF SLO-TEFFT ST, NIPOMO 20A R | 30197775 | COUNTY OF SAN LUIS OBISPO-TEFFT ST, NIPOMO | 93444 | 6079012401 | No | 9.122% | COUNTY OF SAN LUIS OBISPO-TEFFT ST, NIPOMO | None | TBD | TBD | Yes | 20 | 3 | 2 | 1 | 12 | Rural | No | TBD | 2001-05-11 | 2003-06-04 | 2003-11-14 | 2006 | 2007-03-24 | N/A | #VALUE! | N/A | N/A |  |  | 1.38 | 4118.4 | Commercial | Yes |  |  |  | N/A | 792110.21 | 1.591 | 1260220.4617 | [10 empty] | 0 | [6 empty] | 792110.21 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | No | No | None | None | N/A | N/A | None | N/A | N/A
SAN LUIS OBISPO COUNTY | CO. OF SLO-AVILA BCH RL 20A,SAN MIGUEL R | 30323748 | COUNTY OF SAN LUIS OBISPO-AVILA BEACH, SAN MIGUEL | 93424 | 6079011600 | No | 1.841% | COUNTY OF SAN LUIS OBISPO-AVILA BEACH, SAN MIGUEL | Tier 2 | TBD | TBD | Yes | 20 | 3 | 2 | 1 | 12 | Suburban | No | TBD | 2003-10-28 | 2005-11-22 | 2006-01-20 | 2006 | 2007-03-24 | N/A | #VALUE! | N/A | N/A | 9 | 18 | 0.21 | 1320 | Residential | Yes |  |  |  | N/A | 253068.68 | 1.591 | 402623.6813 | [6 empty] | 0 | N/A |  |  | 0 |  |  |  | Other |  |  | 253068.68 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | No | No | None | None | N/A | N/A | None | N/A | N/A
SAN LUIS OBISPO COUNTY | EL CAMINO REAL, SANTA MARGARITA | 30563618 | EL CAMINO REAL | 93453 | 6079012702 | No | 4.626% | EL CAMINO REAL, WILHELMINA AVE & ESTRADA DR | None | Project met one or more Rule 20A criteria | Resolution# 2004-310 | Yes | 20 | 3 | 2 | 1 | 12 | Suburban | No | 2004-09-21 | 2014-08-12 | 2015-10-01 | 2016-02-29 | 2016 | 2016-07-20 | N/A | 3612 | N/A | N/A | 11 | 12 | 0.68 | 4224 | Commercial | Yes |  |  |  | N/A | 2085205.56 | 1.0668 | 2224563.9169 | [6 empty] | 0 | N/A |  |  | 0 |  |  |  | Other |  |  | 2085205.56 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | No | No | None | None | N/A | N/A | None | N/A | N/A
SAN LUIS OBISPO COUNTY | LOS OSOS VALLEY RD, SAN LUIS OBISPO COUNTY | 30563617 | LOS OSOS VALLEY RD, SAN LUIS OBISPO COUNTY | 93402 | 6079010707 | No | 6.242% | LOS OSOS VALLEY RD, SAN LUIS OBISPO COUNTY | Tier 2 | Project met one or more Rule 20A criteria | TBD | Yes | 20 | 3 | 2 | 1 | 12 | Suburban | No | 2004-09-21 | 2015-01-22 | 2017-06-21 | TBD | 2018 | 2019-02-19 | N/A | 3775 | N/A | N/A | TBD | TBD | 3.8412 | 20281.647 | Residential | Yes | TBD | TBD | TBD | N/A | 5318373.62 | TBD | 5318373.62 | [6 empty] | TBD | TBD |  |  | 0 |  |  |  | Other |  |  | 5318373.62 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | Yes | No | No | No | No | No | Re-design due to County requirements provided after project design completed and bid. | None | N/A | N/A | None | N/A | N/A
SAN LUIS OBISPO COUNTY | MAIN ST, TEMPLETON | 30563619 | MAIN ST, TEMPLETON | 93465 | 6079012900 | No | 5.646% | MAIN ST, TEMPLETON | None | TBD | TBD | Yes | 20 | 3 | 2 | 1 | 12 | Suburban | No | 2003-09-09 | 2008-06-20 | 2010-12-10 | 2012-02-06 | 2012 | 2013-01-25 | N/A | 1746 | N/A | N/A | 5 | 1 | 0.6 | 2481.6 | Commercial | No |  |  |  | N/A | 937277 | 1.121 | 1050726.2201 | [6 empty] | Unknown | N/A |  |  | 0 |  |  |  | Restrictive work conditions, additional substructure work, increase in AFUDC |  |  | 937277 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | No | No | None | None | N/A | N/A | None | N/A | N/A
SAN LUIS OBISPO COUNTY | SAN LUIS DRIVE, AVILA BEACH | No Order | SAN LUIS DR, UUD# 31 | 93424 | Unknown | Unknown | Unknown | SAN LUIS DR, SAN RAFAEL ST & FIRST ST | Unknown | Project met one or more Rule 20A criteria | Resolution# 2014-235 | No | 20 | 3 | 2 | 1 | 12 | Unknown | Unknown | 2014-08-27 | TBD | TBD | TBD | TBD | N/A | N/A | #VALUE! | TBD | N/A |  |  | Project not completed or closed | Project not completed or closed | Unknown | Unknown | TBD | TBD | TBD | 2163186 | N/A | TBD | N/A | [6 empty] | TBD | TBD |  |  | 0 |  |  |  | Project in planning phase |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | Yes | No | No | Insufficient allocation | None | N/A | N/A | None | N/A | N/A
SAN LUIS OBISPO COUNTY | SOUTH BAY BLVD, SLO COUNTY | No Order | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | 20 | 3 | 2 | 1 | 12 | N/A | N/A | 2014-08-12 | TBD | TBD | TBD | TBD | N/A | N/A | #VALUE! | N/A | TBD | N/A | N/A | Cancelled project | Cancelled project | N/A | N/A | N/A | N/A | N/A | N/A | N/A | TBD | N/A | [6 empty] | N/A | N/A |  |  | 0 |  |  |  | N/A, project cancelled |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SAN LUIS OBISPO, SAN LUIS OBISPO COUNTY | BROAD STREET PH 2, SAN LUIS OBISPO | 30677482 | BROAD ST PH 2, SAN LUIS OBISPO | 93401 | 6079011503 | No | 2.759% | BROAD ST PH 2, SAN LUIS OBISPO | Part of project in or adjacent to Tier 2 | TBD | TBD | Yes | 20 | 3 | 2 | 1 | 12 | Urban | No | 2003-10-21 | 2008-12-10 | 2012-02-06 | 2013-04-18 | 2013 | 2014-02-28 | N/A | 1877 | N/A | N/A | 23 |  | 1.64 | 4118.4 | Commercial | Yes |  |  |  | N/A | 3267025 | 1.1048 | 3609422.004 |  |  | Unknown | 0 |  | Unknown |  |  |  |  | 0 | [6 empty] | 3267025 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | Yes | No | No | No | No | Communications utilities were not part of the joint trench and took the space where the PG&E conduits were to be installed. | None | N/A | N/A | None | N/A | N/A
SAN LUIS OBISPO, SAN LUIS OBISPO COUNTY | CITY OF SLO BROAD ST PH 1 | 30563616 | BROAD ST PH 1, HWY 227, UUD# 15 & 27 | 93401 | 6079011103 | No | 5.7% | BROAD ST, ORCUTT RD & FARM HOUSE LN | Part of project in or adjacent to Tier 2 | Project met one or more Rule 20A criteria | Resolution# 2003-427, Ordinance# 1442 | Yes | 20 | 3 | 2 | 1 | 12 | Urban | No | 2003-10-21 | 2007-05-01 | 2009-04-17 | 2011-03-21 | 2014 | 2015-01-15 | N/A | 1288 | N/A | N/A | 46 |  | 2.62 | 6969.6 | Commercial | Yes |  |  |  | N/A | 5094590.98 | 1.0831 | 5517861.2426 |  |  | Unknown | 0 | Unknown | Unknown |  |  |  |  | 0 | [6 empty] | 5094590.98 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | Yes | Yes | No | No | Yes | Communications utilities decided not to be part of the joint trench after the design then later damaged a section of conduit | None | N/A | N/A | None | N/A | N/A
San Luis Obispo County Total | [41 empty] | 0
San Mateo County | [41 empty] | 0
BELMONT, SAN MATEO COUNTY | OLD COUNTY ROAD PH 1, BELMONT | 30827391 | OLD COUNTY RD & MASONIC WAY | 94002 | 6081608600 | No | 3.877% | OLD COUNTY RD, HARBOR BLVD & MASONIC WAY, OLD COUNTY RD & GRANADA ST | None | Project met one or more Rule 20A criteria | Resolution# 9389 | Yes | 28 | 10 | 9 | 1 | 15 | Urban | No | 2003-05-27 | 2015-04-02 | 2017-09-01 | TBD | 2019 | 2020-01-14 | N/A | 4328 | N/A | N/A | TBD | TBD | 2.1406 | 11302.6303 | Commercial | Yes | TBD | TBD | TBD | N/A | 4435363.48 | TBD | 4435363.48 | [6 empty] | TBD | TBD |  |  | 0 |  |  |  | Unexpected field conditions |  |  | 4435363.48 |  |  |  |  | Yes | 1835626 | Foster City | 41.39% | Unknown | PG&E does not grant approval for credit transfer transactions. Credit transfers are agreed upon between communities. | Yes | Unknown | No | Yes | No | Yes | Yes | Easement acquisitions. Design issues. Joint Trench. Removing poles. | None | N/A | N/A | None | N/A | N/A
BURLINGAME | EL CAMINO REAL PH 1, BURLINGAME | No Order | EL CAMINO REAL UUD 2019-1 | 94401 | 6081605900 | No | Unknown | EL CAMINO REAL BETWEEN WARREN RD & PASSED DAVIS DR | None | Project met one or more Rule 20A criteria | Resolution# 76-2019 | No | 28 | 10 | 9 | 1 | 15 | Suburban | No | 2019-06-17 | TBD | TBD | TBD | TBD | N/A | N/A | #VALUE! | 0 | N/A | 0 | 0 | Project not completed or closed | Project not completed or closed | Commercial | Unknown | TBD | TBD | TBD | 5000000 | N/A | TBD | N/A | [6 empty] | TBD | TBD | [6 empty] | Project in planning phase |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | Yes | No | No | Insufficient allocation | None | N/A | N/A | No | N/A | N/A
COLMA, DALY CITY, SAN MATEO COUNTY | EL CAMINO REAL | 30010732 | EL CAMINO REAL | 94014 | 6081601300 | No | 9.241% | EL CAMINO REAL | None | TBD | TBD | Yes | 28 | 10 | 9 | 1 | 15 | Unknown | No | 1994-12-14 | 2002-04-03 | 2008-03-11 | 2009-05-26 | 2011 | 2012-02-07 | N/A | 2667 | N/A | N/A |  |  | 0.82 | 3748.8 | Unknown | Unknown |  |  |  | N/A | 2238614 | 1.1878 | 2658967.5019 | [10 empty] | 0 | [6 empty] | 2238614 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
DALY CITY | *CANC* HILLSIDE BLVD PH 1 | 30487832 | N/A | N/A | 6081600600 | No | 6.801% | N/A | None | N/A | N/A | No | 28 | 10 | 9 | 1 | 15 | N/A | No | 2005-07-25 | TBD | TBD | TBD | N/A | 2014-02-28 | N/A | #VALUE! | N/A | 2013-10-28 | N/A | N/A | Cancelled project | Cancelled project | N/A | N/A | N/A | N/A | N/A | N/A | 14125.69 | 1.0831 | 15299.2846 | [6 empty] | N/A | N/A |  |  | 0 |  |  |  | N/A, project cancelled |  |  | 14125.69 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DALY CITY | *CANC* HILLSIDE BLVD PH 2 | 30487833 | N/A | N/A | 6081601300 | No | 9.241% | N/A | None | N/A | N/A | No | 28 | 10 | 9 | 1 | 15 | N/A | No | 2005-07-25 | TBD | TBD | TBD | N/A | 2014-02-28 | N/A | #VALUE! | N/A | 2013-10-28 | N/A | N/A | Cancelled project | Cancelled project | N/A | N/A | N/A | N/A | N/A | N/A | 10241.37 | 1.0831 | 11092.2464 | [6 empty] | N/A | N/A |  |  | 0 |  |  |  | N/A, project cancelled |  |  | 10241.37 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DALY CITY | GENEVA AVE PH 1 | 30669061 | GENEVA AVE PH 1 | 94014 | 6081600200 | No | 7.968% | GENEVA AVE, SANTOS ST & SCHERWIN ST | None | Project met one or more Rule 20A criteria | Resolution# 05-161 | Yes | 28 | 10 | 9 | 1 | 15 | Urban | No | 2005-09-21 | 2010-11-20 | 2014-08-04 | 2014-11-12 | 2016 | 2016-10-19 | N/A | 1886 | N/A | N/A | 48 | 26 | 2.02 | 5068.8 | Commercial | Yes |  |  |  | N/A | 6011029.78 | 1.0668 | 6412758.6308 | [6 empty] | 600000 | 100% |  |  | 0 |  |  |  | Unexpected field conditions |  |  | 6011029.78 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | Yes | No | Yes | No | No | No | Design issues | None | N/A | N/A | None | N/A | N/A
DALY CITY | GENEVA AVE PH 2, DALY CITY | 30707682 | GENEVA AVE PH 2 | 94014 | Unknown | Unknown | Unknown | GENEVA AVE, SCHERWIN ST & BAYSHORE BLVD | Unknown | Project met one or more Rule 20A criteria | Resolution# 05-161 | No | 28 | 10 | 9 | 1 | 15 | Unknown | Unknown | 2005-09-21 | TBD | TBD | TBD | TBD | N/A | N/A | #VALUE! | 2023-06-30 | N/A |  |  | Project not completed or closed | Project not completed or closed | Unknown | Unknown | TBD | TBD | TBD | 5157375.05 | N/A | TBD | N/A | [6 empty] | TBD | TBD |  |  | 0 |  |  |  | Project in planning phase |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Yes | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
EAST PALO ALTO | BAY RD, EAST PALO ALTO | 31059780 | BAY RD | 94303 | 6081611900 | Yes | 10.29% | BAY RD, PULGAS AVE & DIRT RD | None | Project met one or more Rule 20A criteria | Resolution# 4433 | Yes | 28 | 10 | 9 | 1 | 15 | Urban | Yes | 2013-07-06 | 2014-11-13 | 2017-05-15 | 2017-06-05 | 2019 | 2019-04-12 | N/A | 495 | N/A | N/A | 17 | 4 | 0.81838 | 4321.0457 | Commercial | Yes |  |  |  | N/A | 1920415.41 | TBD | 1920415.41 | [6 empty] | 0 | N/A |  |  | 0 |  |  |  | Unexpected field conditions |  |  | 1920415.41 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Yes | Unknown | No | Yes | No | Yes | Yes | Design issues. Joint Trench. Removing poles. | None | N/A | N/A | None | N/A | N/A
HALF MOON BAY | CORREAS ST, HALF MOON BAY | 31271654 | CORREAS ST | 94019 | 6081613700 | No | 5.928% | CORREAS ST, CHURCH & PURISSIMA | None | Project met one or more Rule 20A criteria | Resolution# C-2016-57 | No | 28 | 10 | 9 | 1 | 15 | Urban | No | 2016-06-21 | 2016-12-13 | TBD | TBD | TBD | N/A | N/A | 175 | 2018-03-09 | N/A | TBD | TBD | Project not completed or closed | Project not completed or closed | Residential | Yes | TBD | TBD | TBD | 1210829.25 | N/A | TBD | N/A |  |  | TBD | TBD | TBD | TBD | TBD | TBD |  |  | 0 |  |  |  | Project in progress |  |  | N/A |  |  |  |  | Yes | 891619 | Foster City, Sonora | N/A | 200000 | PG&E does not grant approval for credit transfer transactions. Credit transfers are agreed upon between communities. | No | Yes | No | No | Yes | No | 0 | Location-specific challenges. Coordination with new Library and new business project. | None | N/A | N/A | None | N/A | N/A
HALF MOON BAY | HWY 92/MAIN ST | 30206851 | HWY 92/MAIN ST | 94019 | 6081613700 | No | 5.928% | HWY 92/MAIN ST | Part of project in or adjacent to Tier 2 | TBD | TBD | Yes | 28 | 10 | 9 | 1 | 15 | Unknown | No | 1999-07-20 | 2001-08-01 | 2006-12-07 | 2007-11-28 | 2011 | 2012-02-07 | N/A | 743 | N/A | N/A |  |  | 2.45 | 7392 | Unknown | Unknown |  |  |  | N/A | 845737 | 1.1878 | 1004544.4182 | [10 empty] | 0 | [6 empty] | 845737 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
HILLSBOROUGH | RALSTON/EUCALYPTUS AVENUES | 30367568 | RALSTON AVE/EUCALYPTUS AVE | 94010 | 6081605600 | No | 0.252% | RALSTON AVE/EUCALYPTUS AVE | None | TBD | TBD | Yes | 28 | 10 | 9 | 1 | 15 | Unknown | No | 2003-08-27 | 2004-06-07 | 2006-06-13 | 2009-02-27 | 2012 | 2012-09-13 | N/A | 285 | N/A | N/A |  |  | 0.82 | 1953.6 | Unknown | Unknown |  |  |  | N/A | 2058774.42 | 1.121 | 2307971.138 | [10 empty] | 0 | [6 empty] | 2058774.42 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
PACIFICA | ESPLANADE AVE | 30166232 | ESPLANADE AVE | 94044 | Unknown | Unknown | Unknown | ESPLANADE AVE | Unknown | TBD | TBD | Yes | 28 | 10 | 9 | 1 | 15 | Unknown | Unknown | 1999-09-27 | 2002-02-19 | 2006-12-18 | 2007-04-12 | 2009 | 2009-07-29 | N/A | 876 | N/A | N/A |  |  | No primary UG circuit data found | 0 | Unknown | Unknown |  |  |  | N/A | 165487.87 | 1.2297 | 203496.9067 | [10 empty] | 0 | [6 empty] | 165487.87 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
PACIFICA | PALMETTO AVE, PACIFICA | 30700370 | PALMETTO AVE | 94044 | 6081603000 | No | 4.224% | PALMETTO AVE, BELLA VISTA & CLARENDON | None | Project met one or more Rule 20A criteria | Resolution# 64-2008 | Yes | 28 | 10 | 9 | 1 | 15 | Unknown | No | 2008-11-24 | 2012-02-16 | 2013-10-21 | 2013-12-30 | 2019 | 2020-01-14 | N/A | 1179 | N/A | N/A | 49 |  | 2.7759 | 14656.7917 | Unknown | Yes |  |  |  | N/A | 5555654.92 | TBD | 5555654.92 | [10 empty] | 0 | [6 empty] | 5555654.92 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Yes | Yes | Yes | No | No | No | No | Customer service conversion issues | None | N/A | N/A | None | N/A | N/A
PACIFICA | SAN PEDRO CREEK PHASE 1 | 30195251 | SAN PEDRO CREEK PH 1 | 94044 | 6081603200 | No | 2.194% | SAN PEDRO CREEK PH 1 | None | TBD | TBD | Yes | 28 | 10 | 9 | 1 | 15 | Unknown | No | 1999-09-27 | 2001-06-01 | 2003-06-09 | 2003-08-29 | 2007 | 2007-07-31 | N/A | 613 | N/A | N/A |  |  | 0.56 | 2323.2 | Unknown | Unknown |  |  |  | N/A | 401204.26 | 1.4306 | 573953.6779 | [10 empty] | 0 |  |  |  | Unknown |  |  | 401204.26 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
PORTOLA VALLEY | ALPINE RD, PORTOLA VALLEY | 30992944 | ALPINE RD | 94028 | Unknown | Unknown | Unknown | ALPINE RD, NATHHORST AVE & HILLBROOK DR | Unknown | Project met one or more Rule 20A criteria | Resolution# 2576-2013 | No | 28 | 10 | 9 | 1 | 15 | Rural | Unknown | 2013-01-23 | 2014-04-28 | TBD | TBD | TBD | N/A | N/A | 460 | 2021-07-13 | N/A | TBD | TBD | Project not completed or closed | Project not completed or closed | Residential | Yes | TBD | TBD | TBD | 641571.57 | N/A | TBD | N/A | [6 empty] | TBD | TBD |  |  | 0 |  |  |  | Project in progress |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Yes | No | No | No | Yes | No | No | Insufficient allocation | None | N/A | N/A | None | N/A | N/A
REDWOOD CITY | ES ROOSEVELT AVE, REDWOOD CITY RULE 20A | 30208461 | ROOSEVELT AVE, REDWOOD CITY | 94061 | 6081611000 | No | 4.871% | ROOSEVELT AVE, REDWOOD CITY | None | TBD | TBD | Yes | 28 | 10 | 9 | 1 | 15 | Unknown | No | 2000-12-13 | 2001-08-02 | 2002-08-21 | 2003-07-16 | 2006 | 2007-03-24 | N/A | 232 | N/A | N/A |  |  | 1.39 | 4276.8 | Unknown | Unknown |  |  |  | N/A | 1218971.72 | 1.591 | 1939342.6373 | [10 empty] | 0 |  |  |  | Unknown |  |  | 1218971.72 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
REDWOOD CITY | MIDDLEFIELD RD, REDWOOD CITY | 74001642 | MIDDLEFIELD RD, UUD# 2011-1 | 94063 | 6081610203 | No | 12.46% | MIDDLEFIELD RD, MAIN ST & MANZANITA ST | None | Project met one or more Rule 20A criteria | Ordinance# 2376 | No | 28 | 10 | 9 | 1 | 15 | Urban | No | 2012-02-07 | 2014-03-14 | TBD | TBD | TBD | N/A | N/A | 766 | 2020-04-30 | N/A | TBD | TBD | Project not completed or closed | Project not completed or closed | Residential | Yes | TBD | TBD | TBD | 8379619.5 | N/A | TBD | N/A | [6 empty] | TBD | TBD |  |  | 0 |  |  |  | Project in progress |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Yes | Yes | No | No | Yes | No | No | Insufficient allocation | None | N/A | N/A | None | N/A | N/A
SAN CARLOS | *CANC*C:EP INDUSTRIAL RULE 20A, S.C. | 30417989 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | 28 | 10 | 9 | 1 | 15 | N/A | N/A | 1999-01-25 | TBD | TBD | TBD | N/A | 2007-07-31 | N/A | #VALUE! | N/A | 2007-03-20 | N/A | N/A | Cancelled project | Cancelled project | N/A | N/A | N/A | N/A | N/A | N/A | 451.35 | 1.4306 | 645.691 | [6 empty] | N/A | N/A |  |  | 0 |  |  |  | N/A, project cancelled |  |  | 451.35 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SAN CARLOS | INDUSTRIAL | 30098043 | INDUSTRIAL | 94070 | 6081609100 | No | 2.557% | INDUSTRIAL | None | TBD | TBD | Yes | 28 | 10 | 9 | 1 | 15 | Unknown | No | 1999-01-25 | 1999-10-12 | 2002-10-21 | 2005-03-30 | 2008 | 2008-08-18 | N/A | 260 | N/A | N/A |  |  | 3.29 | 7022.4 | Unknown | Unknown |  |  |  | N/A | 2934893.06 | 1.3051 | 3830454.4954 | [10 empty] | 0 |  |  |  | Unknown |  |  | 2934893.06 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
SAN CARLOS | OLD COUNTY RD | 30906266 | OLD COUNTY RD | 94070 | 6081609100 | No | 2.557% | OLD COUNTY RD, RIVERTON DR & TERMINAL WAY | None | Project met one or more Rule 20A criteria | Resolution# 2012-002 | Yes | 28 | 10 | 9 | 1 | 15 | Urban | No | 2012-01-09 | 2013-03-07 | 2014-09-18 | 2014-10-24 | 2016 | 2016-04-09 | N/A | 423 | N/A | N/A | 27 | 15 | 1.58 | 2904 | Industrial | Yes |  |  |  | N/A | 3072449.62 | 1.0668 | 3277787.424 | [6 empty] | 0 | N/A |  |  | 0 |  |  |  | Unexpected field conditions |  |  | 3072449.62 |  |  |  |  | Yes | 1140000 | Humboldt County, Brisbane | 37.1% | 635000 | PG&E does not grant approval for credit transfer transactions. Credit transfers are agreed upon between communities. | Yes | Unknown | No | Yes | No | Yes | Yes | Easement acquisitions. Design issues. Joint Trench. Removing poles. | None | N/A | N/A | None | N/A | N/A
SAN MATEO | 25TH AVE PH 1, SAN MATEO | 30665355 | 25TH AVE PH 1 | 94403 | 6081607400 | No | 7.1% | 25TH AVE, HACIENDA ST & EL CAMINO REAL | None | Project met one or more Rule 20A criteria | Resolution# 2-87 | Yes | 28 | 10 | 9 | 1 | 15 | Urban | No | 1987-04-06 | 2015-09-24 | 2016-03-01 | 2016-07-26 | 2018 | 2018-07-17 | N/A | 10398 | N/A | N/A | 11 | 16 | 1.1161 | 5892.9285 | Commercial | Yes |  |  |  | N/A | 3088685.06 | TBD | 3088685.06 | [6 empty] | 0 | N/A |  |  | 0 |  |  |  | Unexpected field conditions |  |  | 3088685.06 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Yes | Unknown | No | Yes | No | Yes | Yes | Design issues. Joint Trench. Removing poles. | None | N/A | N/A | None | N/A | N/A
SAN MATEO | 25TH AVE PH 2, SAN MATEO | 30692251 | 25TH AVE PH 2, SAN MATEO, UUD# 87-2 | 94403 | Unknown | Unknown | Unknown | E 25TH AVE, SOUTH DELAWARE ST & S EL CAMINO REAL | Unknown | Project met one or more Rule 20A criteria | Resolution# 2-87 | No | 28 | 10 | 9 | 1 | 15 | Unknown | Unknown | 1987-04-06 | TBD | TBD | TBD | TBD | N/A | N/A | #VALUE! | 2021-09-30 | N/A |  |  | Project not completed or closed | Project not completed or closed | Unknown | Unknown | TBD | TBD | TBD | 1368754.76 | N/A | TBD | N/A | [6 empty] | TBD | TBD |  |  | 0 |  |  |  | Project in planning phase |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Yes | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
SAN MATEO | CITY SAN MATEO, ES/101 @ END/LA SALVA | 30182523 | CITY SAN MATEO, ES/101 & END/LA SALVA | 94403 | 6081608400 | No | 4.273% | CITY SAN MATEO, ES/101 & END/LA SALVA | None | TBD | TBD | Yes | 28 | 10 | 9 | 1 | 15 | Unknown | No | TBD | 2001-03-23 | 2001-08-01 | 2001-10-19 | 2005 | 2007-03-24 | N/A | #VALUE! | N/A | N/A |  |  | 0.34 | 1689.6 | Unknown | Unknown |  |  |  | N/A | 354040.51 | 1.7065 | 604173.9208 | [10 empty] | 0 |  |  |  | Unknown |  |  | 354040.51 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
SAN MATEO COUNTY | MIDDLEFIELD RD PH 2, SAN MATEO COUNTY | 74004302 | MIDDLEFIELD RD PH 2 | 94063 | Unknown | Unknown | Unknown | MIDDLEFIELD RD, FIFTH AVE & MACARTHUR AVE | Unknown | Project met one or more Rule 20A criteria | Resolution# 065657 | No | 28 | 10 | 9 | 1 | 15 | Urban | Unknown | 2002-10-08 | 2019-01-02 | TBD | TBD | TBD | N/A | N/A | 5930 | 2019-07-31 | N/A | TBD | TBD | Project not completed or closed | Project not completed or closed | Commercial | Yes | TBD | TBD | TBD | 5786832.29 | N/A | TBD | N/A | [6 empty] | TBD | TBD |  |  | 0 |  |  |  | Project in progress |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Yes | Unknown | No | Yes | No | Yes | Yes | Design issues. Joint Trench. Removing poles. | None | N/A | N/A | None | N/A | N/A
SAN MATEO COUNTY | MIRADA RD | 30944299 | MIRADA RD | 94019 | 6081613502 | No | 2.059% | MIRADA RD | None | TBD | Resolution# 64869 | Yes | 28 | 10 | 9 | 1 | 15 | Urban | No | 2001-11-20 | 2013-07-25 | 2014-07-30 | 2014-06-30 | 2015 | 2016-01-13 | N/A | 4265 | N/A | N/A | 7 | 16 | 0.3 | 1425.6 | Residential | Yes |  |  |  | N/A | 833659.07 | 1.0677 | 890117.0998 | [6 empty] | 0 | N/A |  |  | 0 | [6 empty] | 833659.07 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Yes | Unknown | No | Yes | No | Yes | Yes | Easement acquisitions. Design issues. Joint Trench. Removing poles. | None | N/A | N/A | None | N/A | N/A
SOUTH SAN FRANCISCO | ANTOINETTE LANE SOUTH SAN FRANCISCO R20A | 74015280 | ANTOINETTE LANE | 94080 | Unknown | Unknown | Unknown | ANTOINETTE LN, CENTENNIAL WAY TRAIL, PENINSULA PINES APTS. | Unknown | Project met one or more Rule 20A criteria | Ordinance# 1540-2017 | No | 28 | 10 | 9 | 1 | 15 | Urban | Unknown | 2017-07-26 | 2017-10-02 | 2019-08-30 | TBD | TBD | N/A | N/A | 68 | 2019-08-31 | N/A | TBD | TBD | Project not completed or closed | Project not completed or closed | Commercial | Yes | TBD | TBD | TBD | 2360218.77 | N/A | TBD | N/A | [6 empty] | TBD | TBD |  |  | 0 |  |  |  | Project in progress |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Yes | Unknown | No | Yes | No | Yes | Yes | Design issues. Joint Trench. Removing poles. | None | N/A | N/A | None | N/A | N/A
SOUTH SAN FRANCISCO | SPRUCE AVE, SOUTH SAN FRANCISCO | 74009301 | SPRUCE AVE | 94080 | Unknown | Unknown | Unknown | SPRUCE AVE, LUX AVE & RAILROAD AVE | Unknown | Project met one or more Rule 20A criteria | Ordinance# 1509-2016 | No | 28 | 10 | 9 | 1 | 15 | Unknown | Unknown | 2016-02-10 | TBD | TBD | TBD | TBD | N/A | N/A | #VALUE! | 2024-04-30 | N/A |  |  | Project not completed or closed | Project not completed or closed | Unknown | Unknown | TBD | TBD | TBD | 4209308.12 | N/A | TBD | N/A | [6 empty] | TBD | TBD |  |  | 0 |  |  |  | Project in planning phase |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Yes | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
SOUTH SAN FRANCISCO | MISSION RD SOUTH SAN FRANCISCO R20A | 35118760 | MISSION RD UUD (CIP PROJECT ST1904) | 94080 | 6081601902 | No | 5.657% | ALONG MISSION RD FROM GRAND AVE TO THE SOUTHERN BART STATION ENTRANCE | None | Project met one or more Rule 20A criteria | Ordinance# 1561-2018 | No | 28 | 10 | 9 | 1 | 15 | Rural | No | 2018-08-22 | TBD | TBD | TBD | TBD | N/A | N/A | #VALUE! | 2022-10-31 | N/A | 0 | 0 | Project not completed or closed | Project not completed or closed | Residential | Unknown | TBD | TBD | TBD | 2871057.26 | N/A | TBD | N/A | [6 empty] | TBD | TBD | [6 empty] | Project in planning phase |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | Yes | No | No | Insufficient allocation | None | N/A | N/A | No | N/A | N/A
San Mateo County Total | [41 empty] | 0
Santa Barbara County | [41 empty] | 0
SANTA BARBARA COUNTY | BASELINE AVE, BALLARD | 30442255 | BASELINE AVE, BALLARD | 93463 | 6083001906 | No | 1.891% | BASELINE AVE, BALLARD | None | TBD | TBD | Yes | 4 | 3 | 3 | 0 | 1 | Unknown | No | 2003-02-04 | 2005-05-23 | 2005-08-15 | 2012-08-24 | 2013 | 2014-02-28 | N/A | 839 | N/A | N/A | 7 | 3 | 0.67 | 2692.8 | Residential | Yes |  |  |  | N/A | 1337063 | 1.1048 | 1477192.4344 |  |  | Unknown | Unknown | Unknown | Unknown | None | N/A |  |  | 0 | [6 empty] | 1337063 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | Yes | No | Easement acquisition. Location-specific challenges. | None | N/A | N/A | None | N/A | N/A
SANTA BARBARA COUNTY | BRADLEY RD, SANTA MARIA | 74009862 | BRADLEY RD | 93455 | Unknown | Unknown | Unknown | BRADLEY RD, AMETHYST DR & LARCH AVE | Unknown | Project met one or more Rule 20A criteria | Resolution# 09-180 | No | 4 | 3 | 3 | 0 | 1 | Suburban | Unknown | 2009-06-02 | 2017-08-29 | TBD | TBD | TBD | N/A | N/A | 3010 | 2019-08-05 | N/A | TBD | TBD | Project not completed or closed | Project not completed or closed | Commercial | Yes | TBD | TBD | TBD | 4003677.06 | N/A | TBD | N/A | [6 empty] | TBD | TBD |  |  | 0 |  |  |  | Project in progress |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Yes | Unknown | Unknown | Unknown | Unknown | None | TBD | TBD | TBD | TBD | TBD | TBD
SANTA MARIA | CIVIC CENTER, SANTA MARIA | 74005712 | CIVIC CENTER | 93458 | Unknown | Unknown | Unknown | CIVIC CENTER, BROADWAY TO COOK TO MILLER TO OAK | Unknown | Project met one or more Rule 20A criteria | Resolution# 2014-36 | No | 4 | 3 | 3 | 0 | 1 | Unknown | Unknown | 2014-04-15 | TBD | TBD | TBD | TBD | N/A | N/A | #VALUE! | 2020-04-05 | N/A |  |  | Project not completed or closed | Project not completed or closed | Unknown | Unknown | TBD | TBD | TBD | 5389466.76 | N/A | TBD | N/A | [6 empty] | TBD | TBD |  |  | 0 |  |  |  | Project in planning phase |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | No | No | None | None | N/A | N/A | None | N/A | N/A
SOLVANG | MISSION DRIVE/5TH ST, SOLVANG | 31056750 | MISSION DR/5TH ST | 93463 | Unknown | Unknown | Unknown | MISSION & 5TH, 5TH & COPENHAGEN | Unknown | Project met one or more Rule 20A criteria | Resolution# 13-928 | No | 4 | 3 | 3 | 0 | 1 | Suburban | Unknown | 2013-11-12 | 2018-01-05 | TBD | TBD | TBD | N/A | N/A | 1515 | TBD | N/A | TBD | TBD | Project not completed or closed | Project not completed or closed | Commercial | Unknown | TBD | TBD | TBD | 198615.24 | N/A | TBD | N/A | [6 empty] | TBD | TBD |  |  | 0 |  |  |  | Project in progress |  |  | N/A |  |  |  |  | Yes | 550000 | Santa Barbara County | N/A | 275000 | PG&E does not grant approval for credit transfer transactions. Credit transfers are agreed upon between communities. | Unknown | Unknown | Unknown | Unknown | Yes | Unknown | Unknown | Insufficient allocation | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
Santa Barbara County Total | [41 empty] | 0
Santa Clara County | [41 empty] | 0
CAMPBELL | WINCHESTER BLVD | 30720578 | WINCHESTER BLVD | 95008 | 6085506503 | No | 7.577% | WINCHESTER BLVD, HAMILTON AVE & BUDD AVE | None | TBD | Resolution# 11015 | Yes | 38 | 14 | 13 | 1 | 24 | Unknown | No | 2009-03-29 | 2012-08-16 | 2012-12-06 | 2013-08-08 | 2015 | 2016-01-13 | N/A | 1236 | N/A | N/A | 60 |  | 3.52 | 7867.2 | Unknown | Unknown |  |  |  | N/A | 6429730.09 | 1.0677 | 6865171.7543 | [10 empty] | 0 | [6 empty] | 6429730.09 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
CUPERTINO | STEVENS CREEK BLVD DIST 16, CUPERTINO | No Order | STEVENS CREEK BLVD, UUD# 16 | 95014 | Unknown | Unknown | Unknown | STEVENS CREEK BLVD, PHAR LAP DR & JANICE AVE | Unknown | Project met one or more Rule 20A criteria | Resolution# 99-100 | No | 38 | 14 | 13 | 1 | 24 | Unknown | Unknown | 1999-04-05 | TBD | TBD | TBD | TBD | N/A | N/A | #VALUE! | TBD | N/A |  |  | Project not completed or closed | Project not completed or closed | Unknown | Unknown | TBD | TBD | TBD | 2700000 | N/A | TBD | N/A | [6 empty] | TBD | TBD |  |  | 0 |  |  |  | Project in planning phase |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Yes | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
CUPERTINO, SAN JOSE | STEVENS CREEK BLVD | 30344383 | STEVENS CREEK BLVD | 95014 | 6085508004 | No | 1.412% | STEVENS CREEK BLVD | None | TBD | TBD | Yes | 38 | 14 | 13 | 1 | 24 | Urban | No | 2004-02-10 | 2004-04-20 | 2005-04-26 | 2012-06-01 | 2013 | 2014-02-28 | N/A | 70 | N/A | N/A | 11 | 5 | 0.47 | 1900.8 | Commercial | Yes |  |  |  | N/A | 1536350 | 1.1048 | 1697365.4918 | [6 empty] | 0 | N/A |  |  | 0 |  |  |  | Unexpected field conditions |  |  | 1536350 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Yes | Unknown | No | Yes | No | Yes | Yes | Easement acquisitions. Design issues. Joint Trench. Removing poles. | None | N/A | N/A | None | N/A | N/A
LOS ALTOS | FIRST ST PH 2, LOS ALTOS | 30899980 | FIRST ST PH 2 | 94022 | 6085510300 | No | 0.8955% | FIRST ST PH2, MAIN ST & SAN ANTONIO RD | None | Project met one or more Rule 20A criteria | Resolution# 10-356 | Yes | 38 | 14 | 13 | 1 | 24 | Urban | No | 2010-08-24 | 2014-09-17 | 2016-03-01 | 2017-01-24 | 2017 | 2017-10-13 | N/A | 1485 | N/A | N/A | 10 | 11 | 0.56 | 2851.2 | Commercial | Yes |  |  |  | N/A | 1630968.37 | 1.048 | 1709326.5295 |  |  | Unknown | 803604 |  | Unknown |  |  |  |  | 0 | [6 empty] | 1630968.37 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | Yes | No | No | 0 | Oil tanks discovered during excavation so construction stopped in that area for testing and remediation | Yes | 0 | 0 | 0 | 0 | 0
LOS ALTOS | FIRST STREET | 30706328 | FIRST ST | 94022 | 6085510300 | No | 0.8955% | FIRST ST | None | TBD | TBD | Yes | 38 | 14 | 13 | 1 | 24 | Urban | No | 2009-01-27 | 2009-06-12 | 2010-10-12 | 2011-06-20 | 2013 | 2014-02-28 | N/A | 136 | N/A | N/A | 9 |  | 0.55 | 686.4 | Commercial | Yes |  |  |  | N/A | 2250164 | 1.1048 | 2485989.9922 |  |  | Unknown | 397927 |  | Unknown |  |  |  |  | 0 | [6 empty] | 2250164 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Yes | No | No | No | No | No | No | Coordination issues with City's streetscape project, vacant lot and future development plans, future construction plans for Safeway | None | N/A | N/A | None | N/A | N/A
LOS ALTOS HILLS | PURISSIMA/ALTAMONT ROADS | 30449755 | PURISSIMA/ALTAMONT ROADS | 94022 | 6085511701 | No | 0.1992% | PURISSIMA/ALTAMONT ROADS | None | TBD | TBD | Yes | 38 | 14 | 13 | 1 | 24 | Rural | No | 2005-08-03 | 2006-11-15 | 2007-02-27 | 2008-03-20 | 2009 | 2010-03-16 | N/A | 469 | N/A | N/A | 21 |  | 1.17 | 3220.8 | residential | No |  |  |  | N/A | 815900.21 | 1.2297 | 1003295.0991 | [6 empty] | 0 | N/A |  |  | 0 |  |  |  | 3rd party cost variance |  |  | 815900.21 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | No | No | City was trench lead | None | N/A | N/A | Yes | 5000 | 5000
LOS ALTOS HILLS | EL MONTE RD PH 1, LOS ALTOS HILLS | No Order | AREA AROUND THE EL MONTE FIRE STATION | 94022 | 6085511704 | No | 0.2876% | EL MONTE RD AND MOODY RD BTW ALTAMONT RD/TEPA WAY & ONEONTA DR | None | Project met one or more Rule 20A criteria | Resolution# 40-19 | No | 38 | 14 | 13 | 1 | 24 | Suburban | No | 2019-06-20 | TBD | TBD | TBD | TBD | N/A | N/A | #VALUE! | 0 | N/A | 0 | 0 | Project not completed or closed | Project not completed or closed | Commercial | Unknown | TBD | TBD | TBD | 1000000 | N/A | TBD | N/A | [6 empty] | TBD | TBD | [6 empty] | Project in planning phase |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | Yes | No | No | Insufficient allocation | None | N/A | N/A | No | N/A | N/A
LOS GATOS | LOS GATOS BLVD, LOS GATOS | 31269308 | LOS GATOS BLVD | 95032 | Unknown | Unknown | Unknown | LOS GATOS BLVD, LARK AVE & CHIRCO DR | Unknown | Project met one or more Rule 20A criteria | Resolution# 2016-008 | No | 38 | 14 | 13 | 1 | 24 | Urban | Unknown | 2016-03-01 | TBD | TBD | TBD | TBD | N/A | N/A | #VALUE! | 2021-12-24 | N/A | TBD | TBD | Project not completed or closed | Project not completed or closed | Commercial | Yes | TBD | TBD | TBD | 2810922.28 | N/A | TBD | N/A | [6 empty] | TBD | TBD |  |  | 0 |  |  |  | Project in progress |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Yes | Unknown | No | Yes | No | Yes | Yes | Design issues. Joint Trench. Removing poles. | None | N/A | N/A | None | N/A | N/A
MILPITAS | SOUTH MAIN ST MILPITAS R20A | 74010862 | SOUTH MAIN ST | 95035 | Unknown | Unknown | Unknown | SOUTH MAIN ST, CORNING AVE & CURTIS AVE | Unknown | Project met one or more Rule 20A criteria | Resolution# 8626 | No | 38 | 14 | 13 | 1 | 24 | Suburban | Unknown | 2017-01-03 | 2017-02-28 | TBD | TBD | TBD | N/A | N/A | 56 | 2019-10-31 | N/A | TBD | TBD | Project not completed or closed | Project not completed or closed | Commercial | Unknown | TBD | TBD | TBD | 4946920.34 | N/A | TBD | N/A | [6 empty] | TBD | TBD |  |  | 0 |  |  |  | Project in progress |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Original estimator re-assigned to Santa Rosa fires, creating 1 year delay. | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
MORGAN HILL | MONTEREY ROAD, MORGAN HILL | 30618077 | MONTEREY RD | 95037 | 6085512313 | Yes | 6.766% | MONTEREY RD, DUNNE AVE & COSMO AVE | None | Project met one or more Rule 20A criteria | Resolution# 5908 | Yes | 38 | 14 | 13 | 1 | 24 | Urban | Yes | 2005-06-01 | 2014-07-30 | 2016-08-01 | 2016-12-07 | 2017 | 2017-10-13 | N/A | 3346 | N/A | N/A | 27 | 18 | 0.87 | 3643.2 | Commercial | Yes |  |  |  | N/A | 2372458.8 | 1.048 | 2486441.0871 | [6 empty] | 0 | N/A |  |  | 0 | [6 empty] | 2372458.8 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Yes | Yes | Yes | Unknown | Yes | No | No | Communication utility pulled out of project. Insufficient allocation. | None | N/A | N/A | None | N/A | N/A
MOUNTAIN VIEW | CALIFORNIA ST, MOUNTAIN VIEW | 31081035 | CALIFORNIA ST | 94041 | Unknown | Unknown | Unknown | CALIFORNIA ST, ESCUELA AVE & MARIPOSA AVE | Unknown | Project met one or more Rule 20A criteria | Resolution# 17831 | No | 38 | 14 | 13 | 1 | 24 | Urban | Unknown | 2013-12-10 | 2017-01-04 | TBD | TBD | TBD | N/A | N/A | 1121 | 2018-12-31 | N/A | TBD | TBD | Project not completed or closed | Project not completed or closed | Residential | Unknown | TBD | TBD | TBD | 2163943.91 | N/A | TBD | N/A |  |  | TBD | TBD | TBD | TBD | TBD | TBD |  |  | 0 |  |  |  | Project in progress |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Yes | Unknown | Unknown | Unknown | No | Unknown | Unknown | Internal resource limitation | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
MOUNTAIN VIEW | RENGSTORFF AVE | 30431045 | RENGSTORFF AVE | 94043 | 6085509304 | No | 4.842% | RENGSTORFF AVE, HWY 101 & MIDDLEFIELD RD | None | Project met one or more Rule 20A criteria | Resolution# 16326 | Yes | 38 | 14 | 13 | 1 | 24 | Unknown | No | 1999-02-23 | 2007-04-20 | 2010-08-02 | 2012-08-28 | 2015 | 2015-07-14 | N/A | 2978 | N/A | N/A | 9 | 17 | 1.21 | 4699.2 | Residential | Yes |  |  |  | N/A | 2986716.5 | 1.0677 | 3188986.3909 |  |  | Unknown | 950480 |  | Unknown |  |  |  |  | 0 | [6 empty] | 2986716.5 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | Yes | No | No | No | No | No | City's paving requirements and traffic control plans | None | N/A | N/A | Unknown | Unknown | Unknown
SAN JOSE | ABORN RD | 30702293 | ABORN RD | 95121 | 6085503315 | No | 7.86% | ABORN RD, PUMPHERSTON WAY & WHITE RD | None | Project met one or more Rule 20A criteria | Ordinance# 28401 | Yes | 38 | 14 | 13 | 1 | 24 | Urban | No | 2008-09-30 | 2013-07-25 | 2014-08-25 | 2014-11-09 | 2016 | 2016-04-09 | N/A | 1759 | N/A | N/A | 19 | 6 | 0.45 | 1372.8 | Residential | Yes |  |  |  | N/A | 1772317.3 | 1.0668 | 1890764.7238 | [6 empty] | 0 | N/A |  |  | 0 | [6 empty] | 1772317.3 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Yes | Unknown | No | Yes | No | Yes | Yes | Easement acquisitions. Design issues. Joint Trench. Removing poles. | None | N/A | N/A | None | N/A | N/A
SAN JOSE | C:GEP VTA PHASE 4 R20A C-225 SAN JOSE | 30140824 | VTA PH 4 C-225, SAN JOSE | 95116 | 6085504002 | No | 12.54% | VTA PH 4 C-225, SAN JOSE | None | TBD | TBD | Yes | 38 | 14 | 13 | 1 | 24 | Urban | No | TBD | 2000-11-07 | 2001-10-15 | 2002-02-03 | 2006 | 2007-03-24 | N/A | #VALUE! | N/A | N/A |  |  | 0.55 | 2851.2 | Residential | No |  |  |  | N/A | 1045126.85 | 1.591 | 1662761.3491 | [6 empty] | 0 | N/A |  |  | 0 | [6 empty] | 1045126.85 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | No | No | None | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
SAN JOSE | CIVIC CENTER, PHASE 2 | 30415847 | CIVIC CENTER, PH 2 | 95192 | 6085501000 | No | 10.86% | CIVIC CENTER, PH 2 | None | TBD | TBD | Yes | 38 | 14 | 13 | 1 | 24 | Urban | No | 2002-05-07 | 2005-01-03 | 2005-02-03 | 2006-08-29 | 2007 | 2008-02-15 | N/A | 972 | N/A | N/A |  |  | 2.02 | 8131.2 | Residential | No |  |  |  | N/A | 2174100.57 | 1.4306 | 3110218.7657 | [6 empty] | 0 | N/A |  |  | 0 | [6 empty] | 2174100.57 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
SAN JOSE | COLEMAN AVE PH 2, SAN JOSE | 30776258 | COLEMAN AVE PH 2, SAN JOSE | 95110 | Unknown | Unknown | Unknown | COLEMAN AVE, WEST HEDDING ST & SPRING ST | Unknown | Project met one or more Rule 20A criteria | Ordinance# 28581 | No | 38 | 14 | 13 | 1 | 24 | Unknown | Unknown | 2009-06-16 | TBD | TBD | TBD | TBD | N/A | N/A | #VALUE! | 2025-12-31 | N/A |  |  | Project not completed or closed | Project not completed or closed | Unknown | Unknown | TBD | TBD | TBD | 2423106.22 | N/A | TBD | N/A | [6 empty] | TBD | TBD |  |  | 0 |  |  |  | Project in planning phase |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Yes | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
SAN JOSE | COLEMAN AVE PH1 | 30776251 | COLEMAN AVE PH1 | 95113 | 6085500800 | No | 10.04% | COLEMAN AVE, DEVINE ST & MARKET ST | None | TBD | Ordinance# 28581 | Yes | 38 | 14 | 13 | 1 | 24 | Unknown | No | 2009-06-16 | 2013-12-20 | 2015-02-23 | 2015-06-02 | 2015 | 2015-10-06 | N/A | 1648 | N/A | N/A |  |  | 0.05 | 316.8 | Unknown | Unknown |  |  |  | N/A | 432091.19 | 1.0677 | 461353.7725 | [10 empty] | 0 |  |  |  | Unknown |  |  | 432091.19 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
SAN JOSE | DELMAS & PARK AVE | 30648282 | DELMAS & PARK AVE | 95126 | 6085500800 | No | 10.04% | DELMAS AVE & PARK AVE, AUZERIAS AVE & W SAN FERNANDO | None | TBD | Resolution# 28231 | Yes | 38 | 14 | 13 | 1 | 24 | Urban | No | 2008-01-29 | 2008-09-12 | 2009-09-23 | 2014-12-16 | 2016 | 2016-04-09 | N/A | 227 | N/A | N/A | 53 | 72 | 2.45 | 7339.2 | Residential | Yes |  |  |  | N/A | 5742948.96 | 1.0668 | 6126761.4464 |  |  | Unknown | 912270 |  | Unknown |  |  |  |  | 0 | [6 empty] | 5742948.96 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | Yes | Unknown | Easement acquisitions | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
SAN JOSE | EVERGREEN PARK | 30920922 | EVERGREEN PARK | 95135 | 6085503331 | No | 8.226% | EVERGREEN PARK, SAN FELIPE RD & YERBA BUENA RD | None | TBD | Resolution# 60654 | Yes | 38 | 14 | 13 | 1 | 24 | Urban | No | 1998-06-21 | 2013-05-02 | 2013-09-20 | 2013-12-30 | 2015 | 2016-01-13 | N/A | 5429 | N/A | N/A | 25 |  | 1.49 | 5649.6 | Commercial | Yes |  |  |  | N/A | 2794110.84 | 1.0677 | 2983336.8662 |  |  | Unknown | 207200 |  | Unknown |  |  |  |  | 0 | [6 empty] | 2794110.84 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | Yes | Yes | During excavation, contaminated soil was discovered | Yes | 0 | 0 | None | N/A | N/A
SAN JOSE | GEP VTA PHASE 1 R20A C-225 SAN JOSE | 30126235 | VTA PH 1 C-225, SAN JOSE | 95133 | 6085504307 | No | 5.105% | VTA PH 1 C-225, SAN JOSE | None | TBD | TBD | Yes | 38 | 14 | 13 | 1 | 24 | Urban | No | TBD | 2000-02-09 | 2001-03-08 | 2001-10-01 | 2005 | 2007-03-24 | N/A | #VALUE! | N/A | N/A |  |  | 0.31 | 1425.6 | Residential | No |  |  |  | N/A | 720044.6 | 1.7065 | 1228763.8189 | [6 empty] | 0 | N/A |  |  | 0 | [6 empty] | 720044.6 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | Unknown | Unknown | No | Unknown | Unknown | None | Yes | Unknown | Unknown | Unknown | Unknown | Unknown
SAN JOSE | GUADALUPE GARDENS, PH 1 | 30514516 | GUADALUPE GARDENS, PH 1 | 95110 | 6085500300 | No | 5.478% | GUADALUPE GARDENS, PH 1 | None | TBD | TBD | Yes | 38 | 14 | 13 | 1 | 24 | Urban | No | 2003-01-14 | 2006-07-11 | 2006-10-24 | 2008-03-13 | 2013 | 2014-02-28 | N/A | 1274 | N/A | N/A | 17 | 16 | 4.87 | 13094.4 | Commercial | No |  |  |  | N/A | 953720 | 1.1048 | 1053673.5879 | [6 empty] | Yes | 100% |  |  | 0 |  |  |  | Restrictive work conditions |  |  | 953720 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Yes | Yes | No | No | No | Yes | No | Coordination issues between City and Guadalupe Gardens. Easement acquisitions. | None | N/A | N/A | None | N/A | N/A
SAN JOSE | GUADALUPE GARDENS, PH 2 | 30576193 | GUADALUPE GARDENS, PH 2 | 95110 | 6085500300 | No | 5.478% | GUADALUPE GARDENS, PH 2 | None | TBD | TBD | Yes | 38 | 14 | 13 | 1 | 24 | Urban | No | 2003-01-14 | 2007-05-17 | 2007-10-04 | 2009-12-07 | 2012 | 2012-09-13 | N/A | 1584 | N/A | N/A | 118 | 17 | 0.17 | 1689.6 | Residential | No |  |  |  | 6795.35 | 4992592.56 | 1.121 | 5596902.4193 | [6 empty] | Yes | 100% |  |  | 0 |  |  |  | Increase in AFUDC |  |  | 4992592.56 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | Yes | No | No | No | Yes | No | Coordination issues between City and Guadalupe Gardens. Easement acquisitions. | Yes | 3500 | 3500 | None | N/A | N/A
SAN JOSE | JACKSON/TAYLOR | 30354298 | JACKSON/TAYLOR | 95112 | 6085501101 | Yes | 9.254% | JACKSON/TAYLOR, N 1ST ST & N 7TH ST | None | Project met one or more Rule 20A criteria | Ordinance# 27562 | Yes | 38 | 14 | 13 | 1 | 24 | Urban | Yes | 2005-11-18 | 2007-04-09 | 2009-03-26 | 2011-01-03 | 2014 | 2015-01-15 | N/A | 507 | N/A | N/A | 26 | 34 | 2.22 | 6811.2 | Commercial | Yes |  |  |  | N/A | 4135751.22 | 1.0831 | 4479358.8839 |  |  | N/A | N/A | N/A | N/A | Yes | 100% |  |  | 0 |  |  |  |  | 64906.02 | 2015-10-06 | 4135751.22 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Yes | Yes | Yes | No | No | Yes | No | Project was coordinated with a Rule 20B that included an underground rail crossing and Union Pacific Railroad. Additional issues with City requiring PG&E to ground and bond the service conversion panels. City delay in signing General Conditions Agreement. | No | N/A | N/A | Yes. Joint trench sections had to be moniitored as it was near the old historically significant Chinatown of San Jose. Trnech sections had to be monitored and some portions were hand sifted prior to completion | 25000 | 25000
SAN JOSE | KIRK PARK, SAN JOSE | 31085931 | KIRK PARK | 95124 | Unknown | Unknown | Unknown | FOXWORTHY AVE, YUCCA AVE & BRIARWOOD AVE | Unknown | Project met one or more Rule 20A criteria | Ordinance# 28881 | No | 38 | 14 | 13 | 1 | 24 | Unknown | Unknown | 2011-01-25 | TBD | TBD | TBD | TBD | N/A | N/A | #VALUE! | 2021-11-30 | N/A |  |  | Project not completed or closed | Project not completed or closed | Unknown | Unknown | TBD | TBD | TBD | 2306301.83 | N/A | TBD | N/A | [6 empty] | TBD | TBD |  |  | 0 |  |  |  | Project in planning phase |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Yes | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
SAN JOSE | LINCOLN AVE, SAN JOSE | 31085930 | LINCOLN AVE | 95126 | 6085501900 | No | 9.653% | LINCOLN AVE, WEST SAN CARLOS ST & COE AVE | None | Project met one or more Rule 20A criteria | Ordinance# 28750 | No | 38 | 14 | 13 | 1 | 24 | Unknown | No | 2010-06-08 | TBD | TBD | TBD | TBD | N/A | N/A | #VALUE! | 2022-03-31 | N/A |  |  | Project not completed or closed | Project not completed or closed | Unknown | Unknown | TBD | TBD | TBD | 4180639.27 | N/A | TBD | N/A | [6 empty] | TBD | TBD |  |  | 0 |  |  |  | Project in planning phase |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Yes | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
SAN JOSE | MARKET/ALMADEN | 30567652 | MARKET/ALMADEN | 95110 | 6085501700 | No | 10.5% | MARKET/ALMADEN | None | TBD | TBD | Yes | 38 | 14 | 13 | 1 | 24 | Urban | No | 2006-06-01 | 2007-05-30 | 2008-11-12 | 2010-01-14 | 2013 | 2014-02-28 | N/A | 363 | N/A | N/A | 49 |  | 1.14 | 4435.2 | Residential | No |  |  |  | N/A | 4693194 | 1.1048 | 5185059.0958 | [6 empty] | Yes | 100% |  |  | 0 |  |  |  | Unexpected field conditions |  |  | 4693194 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | Yes | No | No | No | No | No | Panel conversion issues between City and property owners. Project re-design due to complexity of major AT&T fiber bundle. | None | N/A | N/A | None | N/A | N/A
SAN JOSE | MONTEREY ROAD, SAN JOSE | 74001554 | MONTEREY HWY, WILLOW ST TO CURTNER AVE | 95125 | Unknown | Unknown | Unknown | MONTEREY HWY, WILLOW ST TO CURTNER AVE | Unknown | Project met one or more Rule 20A criteria | Ordinance# 23191 | No | 38 | 14 | 13 | 1 | 24 | Urban | Unknown | 1989-06-20 | 2014-08-06 | TBD | TBD | TBD | N/A | N/A | 9178 | 2020-01-24 | N/A | TBD | TBD | Project not completed or closed | Project not completed or closed | Commercial | Yes | TBD | TBD | TBD | 4654054.93 | N/A | TBD | N/A | [6 empty] | TBD | TBD |  |  | 0 |  |  |  | Project in progress |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Yes | Yes | Yes | Yes | No | No | No | Trench path issue. Easement acquisitions. | None | N/A | N/A | None | N/A | N/A
SAN JOSE | PARK/NAGLEE | 30575460 | PARK/NAGLEE | 95126 | 6085500500 | No | 4.929% | PARK AVE & NAGLEE AVE, N BASCOM AVE & HANCHETT AVE | None | TBD | Ordinance# 27687, Resolution# 73088 | Yes | 38 | 14 | 13 | 1 | 24 | Urban | No | 2006-05-12 | 2007-05-16 | 2008-02-06 | 2013-12-27 | 2015 | 2015-10-06 | N/A | 369 | N/A | N/A | 52 | 36 | 3.94 | 9081.6 | Residential | Yes |  |  |  | N/A | 6472553.42 | 1.0677 | 6910895.2157 | [6 empty] | 0 | N/A |  |  | 0 |  |  |  |  | 36197.93 | 10/19/2016 & 10/13/2017 | 6472553.42 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Yes | Unknown | No | Yes | No | Yes | Yes | Easement acquisitions. Design issues. Joint Trench. Removing poles. | None | N/A | N/A | None | N/A | N/A
SAN JOSE | SANTA CLARA CIVIC CENTER, SAN JOSE | 30222768 | SANTA CLARA CIVIC CENTER, SAN JOSE | 95192 | 6085500901 | No | 11.01% | SANTA CLARA CIVIC CENTER, SAN JOSE | None | TBD | TBD | Yes | 38 | 14 | 13 | 1 | 24 | Unknown | No | TBD | TBD | TBD | 2005-08-28 | 2008 | 2009-03-17 | N/A | #VALUE! | N/A | N/A |  |  | 0.56 | 2587.2 | Unknown | Unknown |  |  |  | N/A | 647311.72 | 1.3051 | 844834.2196 | [10 empty] | 0 | [6 empty] | 647311.72 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
SAN JOSE | TULLY RD | 30650716 | TULLY RD | 95122 | 6085503122 | Yes | 17.19% | TULLY RD, KENOGA DR & SENTER RD | None | Project met one or more Rule 20A criteria | Ordinance# 28528 | Yes | 38 | 14 | 13 | 1 | 24 | Urban | Yes | 2009-05-29 | 2014-04-01 | 2014-11-03 | 2015-04-02 | 2015 | 2016-01-13 | N/A | 1768 | N/A | N/A | 28 | 7 | 1.4 | 6230.4 | Commercial | Yes | 0 | 0 | 0 | N/A | 3105826.78 | 1.0677 | 3316163.1959 | [6 empty] | 0 | N/A |  |  | 0 |  |  |  | Unexpected field conditions |  |  | 3105826.78 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Yes | Unknown | No | Yes | No | Yes | Yes | Easement acquisitions. Design issues. Joint Trench. Removing poles. | None | N/A | N/A | None | N/A | N/A
SAN JOSE | WHITE ROAD, SAN JOSE | 30677172 | WHITE ROAD, SAN JOSE | 95127 | Unknown | Unknown | Unknown | WHITE RD, ROSE AVE & ALUM ROCK AVE | Unknown | Project met one or more Rule 20A criteria | Ordinance# 28357 | No | 38 | 14 | 13 | 1 | 24 | Suburban | Unknown | 2008-08-05 | 2015-12-01 | 2018-08-09 | 2019-01-08 | TBD | N/A | N/A | 2674 | 2019-05-28 | N/A | TBD | TBD | Project not completed or closed | Project not completed or closed | Residential | Yes | TBD | TBD | TBD | 2928264.65 | N/A | TBD | N/A | [6 empty] | TBD | TBD |  |  | 0 |  |  |  | Project in progress |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | Yes | Yes | No | No | No | No | Easement acquisitions. Customer issues. | None | N/A | N/A | None | N/A | N/A
SAN JOSE, SANTA CLARA COUNTY | CAMDEN AVE | 30647467 & 30071453 | CAMDEN AVE | 95124 | 6085502800 | No | 2.901% | CAMDEN AVE, BASCOM AVE & LEIGH AVE | None | TBD | TBD | Yes | 38 | 14 | 13 | 1 | 24 | Urban | No | 1993-08-17 | 2011-12-06 | 2015-02-23 | 2015-04-14 | 2016 | 2016-04-09 | N/A | 6685 | N/A | N/A | 12 | 9 | 1.31 | 9504 | Commercial | Yes |  |  |  | N/A | 3523227.04 | 1.0668 | 3758691.1787 | [6 empty] | 0 | N/A |  |  | 0 |  |  |  |  | 39899.43 | 2018-01-23 | 3523227.04 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Yes | Unknown | No | Yes | No | Yes | Yes | Easement acquisitions. Design issues. Joint Trench. Removing poles. | None | N/A | N/A | None | N/A | N/A
SANTA CLARA COUNTY | ALMADEN EXPWY, SANTA CLARA COUNTY | 30767366 | ALMADEN EXPWY, SANTA CLARA COUNTY, UUD# 2 | 95118 | 6085511915 | No | 13.5% | ALMADEN EXPWY, COLEMAN AVE & MESA DR | None | Project met one or more Rule 20A criteria | Ordinance# NS-705.26 | No | 38 | 14 | 13 | 1 | 24 | Unknown | No | 2007-11-13 | TBD | TBD | TBD | TBD | N/A | N/A | #VALUE! | 2021-12-31 | N/A |  |  | Project not completed or closed | Project not completed or closed | Unknown | Unknown | TBD | TBD | TBD | 2682750.28 | N/A | TBD | N/A | [6 empty] | TBD | TBD |  |  | 0 |  |  |  | Project in planning phase |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Yes | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
SANTA CLARA COUNTY | LINCOLN PARK LOS ALTOS R20A | 74011843 | LINCOLN PARK | 94022 | Unknown | Unknown | Unknown | UNIVERSITY AVE & LINCOLN AVE, EDITH AVE & SHERMAN ST | Unknown | Project met one or more Rule 20A criteria | Ordinance# 2017-430 | No | 38 | 14 | 13 | 1 | 24 | Suburban | Unknown | 2017-02-14 | 2019-09-09 | TBD | TBD | TBD | N/A | N/A | 937 | 2020-07-31 | N/A | TBD | TBD | Project not completed or closed | Project not completed or closed | Residential | Yes | TBD | TBD | TBD | 3354345.08 | N/A | TBD | N/A | [6 empty] | TBD | TBD |  |  | 0 |  |  |  | Project in progress |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Yes | Unknown | No | Yes | No | Yes | Yes | Design issues. Joint Trench. Removing poles. | None | N/A | N/A | None | N/A | N/A
SANTA CLARA COUNTY, MILPITAS | MONTAGUE EXPWY MILPITAS R20A | 31330811 | MONTAGUE EXPWY | 95035 | Unknown | Unknown | Unknown | MONTAGUE EXPWY, SOUTH MILPITAS BLVD, GLADDING CT & WATSON CT | Unknown | Project met one or more Rule 20A criteria | Resolution# 8627 | No | 38 | 14 | 13 | 1 | 24 | Suburban | Unknown | 2016-12-06 | 2017-10-16 | TBD | TBD | TBD | N/A | N/A | 314 | 2019-08-31 | N/A | TBD | TBD | Project not completed or closed | Project not completed or closed | Commercial | Unknown | TBD | TBD | TBD | 883035 | N/A | TBD | N/A | [6 empty] | TBD | TBD |  |  | 0 |  |  |  | Project in progress |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | None | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
SUNNYVALE | FAIR OAKS AVE, SUNNYVALE | 30721972 | FAIR OAKS AVE | 94086 | 6085508602 | No | 5.001% | FAIR OAKS AVE, EL CAMINO REAL & EVELYN AVE | None | Project met one or more Rule 20A criteria | Resolution# 394-09 | Yes | 38 | 14 | 13 | 1 | 24 | Suburban | No | 2009-06-23 | 2013-09-19 | 2015-07-01 | 2015-11-04 | 2017 | 2017-10-13 | N/A | 1549 | N/A | N/A | 38 | 21 | 2.15 | 7286.4 | Commercial | Yes |  |  |  | N/A | 4906621.16 | 1.048 | 5142354.6116 | [6 empty] | 0 | N/A |  |  | 0 | [6 empty] | 4906621.16 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Yes | Unknown | No | Yes | No | Yes | Yes | Easement acquisitions. Design issues. Joint Trench. Removing poles. | None | N/A | N/A | None | N/A | N/A
SUNNYVALE | HOLLENBECK, RULE 20A | 30260633 | HOLLENBECK | 94087 | 6085508403 | No | 1.1% | HOLLENBECK | None | TBD | TBD | Yes | 38 | 14 | 13 | 1 | 24 | Urban | No | 2002-01-08 | 2002-05-20 | 2002-08-16 | 2003-08-16 | 2005 | 2007-03-24 | N/A | 132 | N/A | N/A |  |  | 0.24 | 686.4 | Residential | Unknown |  |  |  | N/A | 143963.1 | 1.7065 | 245674.5715 | [6 empty] | 6300 | Unknown |  |  | 0 |  |  |  | Other |  |  | 143963.1 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
SUNNYVALE | WOLFE ROAD, SUNNYVALE | 74001551 | WOLFE RD, SUNNYVALE | 94087 | Unknown | Unknown | Unknown | WOLFE RD, OLD SAN FRANCISCO RD & HOMESTEAD RD | Unknown | Project met one or more Rule 20A criteria | Resolution# 409-09 | No | 38 | 14 | 13 | 1 | 24 | Urban | Unknown | 2009-11-17 | 2015-06-12 | TBD | TBD | TBD | N/A | N/A | 2033 | 2019-10-30 | N/A | TBD | TBD | Project not completed or closed | Project not completed or closed | Residential | Unknown | TBD | TBD | TBD | 7957363.76 | N/A | TBD | N/A |  |  | TBD | TBD | TBD | TBD | TBD | TBD |  |  | 0 |  |  |  | Project in progress |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Yes | Yes | Unknown | Unknown | No | Unknown | Unknown | Easement acquisitions. City streetlight delays. Internal resource limitation. | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
Santa Clara County Total | [41 empty] | 0
Santa Cruz County | [41 empty] | 0
CAPITOLA | C:CAPITOLA RULE 20A *CANC | 30125135 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | 11 | 4 | 4 | 0 | 5 | N/A | N/A | 2000-11-21 | TBD | TBD | TBD | N/A | 2007-03-24 | N/A | #VALUE! | N/A | 2005-04-21 | N/A | N/A | Cancelled project | Cancelled project | N/A | N/A | N/A | N/A | N/A | N/A | 11817.22 | 1.4306 | 16905.4458 | [6 empty] | N/A | N/A |  |  | 0 |  |  |  | N/A, project cancelled |  |  | 11817.22 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CAPITOLA | MONTEREY AVE & BAY AVE, CAPITOLA | 74013860 | MONTEREY AVE & BAY AVE | 95010 | Unknown | Unknown | Unknown | BAY AVE, OAK & CHERRY AVE | Unknown | Project met one or more Rule 20A criteria | Resolution# 3098 | No | 11 | 4 | 4 | 0 | 5 | Unknown | Unknown | 2000-11-21 | 2018-12-13 | TBD | TBD | TBD | N/A | N/A | 6596 | 2020-02-01 | N/A |  |  | Project not completed or closed | Project not completed or closed | Unknown | Unknown | TBD | TBD | TBD | 1925465.2 | N/A | TBD | N/A | [6 empty] | TBD | TBD |  |  | 0 |  |  |  | Project in planning phase |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | Yes | No | No | Yes | No | No | Insufficient allocation | None | N/A | N/A | None | N/A | N/A
SANTA CRUZ | C:GEPC MISSION HILL RULE 20A,SANTA CRUZ | 30070717 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | 11 | 4 | 4 | 0 | 5 | N/A | N/A | TBD | TBD | TBD | TBD | N/A | 2007-03-24 | N/A | #VALUE! | N/A | 2006-08-26 | N/A | N/A | Cancelled project | Cancelled project | N/A | N/A | N/A | N/A | N/A | N/A | 8838 | 1.4306 | 12643.4415 | [6 empty] | N/A | N/A |  |  | 0 |  |  |  | N/A, project cancelled |  |  | 8838 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SANTA CRUZ | MISSION ST - PHASE 1, RULE 20A | 30136844 | MISSION ST - PH 1 | 95060 | 6087100600 | No | 2.903% | MISSION ST - PH 1 | None | TBD | TBD | Yes | 11 | 4 | 4 | 0 | 5 | Urban | No | TBD | 2001-06-02 | 2002-10-07 | 2004-01-16 | 2006 | 2007-03-24 | N/A | #VALUE! | N/A | N/A |  |  | 1.78 | 5016 | Commercial | Unknown |  |  |  | N/A | 3091119.09 | 1.591 | 4917865.5665 | [6 empty] | Unknown | N/A |  |  | 0 | [6 empty] | 3091119.09 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Yes | Unknown | Unknown | Unknown | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
SANTA CRUZ | MISSION ST PH 3, SANTA CRUZ | 74001550 | MISSION ST, PH 3, SANTA CRUZ | 95060 | Unknown | Unknown | Unknown | MISSION ST, CENTER ST & CHESTNUT ST | Unknown | Project met one or more Rule 20A criteria | Resolution# NS-22,951 | No | 11 | 4 | 4 | 0 | 5 | Urban | Unknown | 1996-09-10 | 2014-03-14 | TBD | TBD | TBD | N/A | N/A | 6394 | 2021-05-14 | N/A | TBD | TBD | Project not completed or closed | Project not completed or closed | Residential | Unknown | TBD | TBD | TBD | 2023307.07 | N/A | TBD | N/A | [6 empty] | TBD | TBD |  |  | 0 |  |  |  | Project in progress |  |  | N/A |  |  |  |  | Yes | Unknown | Vallejo | N/A | Unknown | PG&E does not grant approval for credit transfer transactions. Credit transfers are agreed upon between communities. | No | Yes | Unknown | Yes | Yes | Yes | No | Insufficient allocation | None | N/A | N/A | None | N/A | N/A
SANTA CRUZ | MISSION ST, PH 2 | 30240320 | MISSION ST, PH 2 | 95060 | 6087100600 | No | 2.903% | MISSION ST, PH 2 | None | TBD | TBD | Yes | 11 | 4 | 4 | 0 | 5 | Urban | No | 2001-03-27 | 2002-01-25 | 2006-11-06 | 2008-03-19 | 2012 | 2012-09-13 | N/A | 304 | N/A | N/A | 35 | 52 | 3.34 | 8448 | Commercial | No |  |  |  | N/A | 3897340.59 | 1.121 | 4369079.7346 | [6 empty] | 0 | N/A |  |  | 0 |  |  |  | Unexpected field conditions |  |  | 3897340.59 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Yes | No | No | No | Yes | No | No | City was trench lead. Form B agreement/execution issues. Hydrocarbons found near an abandoned gas station. City delay while site was remediated. | Yes | N/A | N/A | None | N/A | N/A
SANTA CRUZ | RIVERSIDE AVE, SANTA CRUZ | 31218473 | RIVERSIDE AVE | 95060 | Unknown | Unknown | Unknown | RIVERSIDE AVE, 3RD ST & BEACH ST | Unknown | Project met one or more Rule 20A criteria | Resolution# NS-29,016 | No | 11 | 4 | 4 | 0 | 5 | Urban | Unknown | 2015-11-10 | 2016-11-01 | TBD | TBD | TBD | N/A | N/A | 357 | 2020-12-30 | N/A | TBD | TBD | Project not completed or closed | Project not completed or closed | Commercial | Yes | TBD | TBD | TBD | 1108357.8 | N/A | TBD | N/A | [6 empty] | TBD | TBD |  |  | 0 |  |  |  | Project in progress |  |  | N/A |  |  |  |  | Yes | Unknown | Vallejo | N/A | Unknown | PG&E does not grant approval for credit transfer transactions. Credit transfers are agreed upon between communities. | No | Yes | Yes | Yes | No | No | No | City is trench lead. Project costs higher than expected. Communication utility pulled out of project. | None | N/A | N/A | None | N/A | N/A
SANTA CRUZ COUNTY | CITY OF DAVENPORT | 30071191 | CITY OF DAVENPORT | 95017 | 6087120200 | No | 2.545% | CITY OF DAVENPORT | Part of project in or adjacent to Tier 2 | TBD | TBD | Yes | 11 | 4 | 4 | 0 | 5 | Rural | No | TBD | TBD | TBD | 2006-09-18 | 2007 | 2007-07-31 | N/A | #VALUE! | N/A | N/A |  |  | 0.97 | 3643.2 | Residential | No |  |  |  | N/A | 1594312.61 | 1.4306 | 2280787.3134 | [6 empty] | 0 | N/A |  |  | 0 |  |  |  | Unexpected field conditions |  |  | 1594312.61 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Yes | Yes | Yes | Yes | Yes | Unknown | No | Communication utility was trench lead and hired an inexperienced trenching contractor. Trench failed after first large rainstorm post joint trench construction phase. County issues with adopting ordinance. Coordination challenges with panel conversions. | None | N/A | N/A | None | N/A | N/A
SANTA CRUZ COUNTY | STATE PARK DRIVE, SEA CLIFF | 30261740 | STATE PARK DR, SEA CLIFF | 95003 | 6087122100 | No | 5.693% | STATE PARK DR, SEA CLIFF | None | Project met one or more Rule 20A criteria | TBD | Yes | 11 | 4 | 4 | 0 | 5 | Suburban | No | 2004-05-18 | 2012-11-26 | 2017-08-18 | TBD | 2018 | 2019-02-19 | N/A | 3114 | N/A | N/A | TBD | TBD | 1.6909 | 8927.799 | Commercial | Yes | TBD | TBD | TBD | N/A | 2023838.48 | TBD | 2023838.48 | [6 empty] | TBD | TBD |  |  | 0 |  |  |  | Increase in AFUDC |  |  | 2023838.48 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Yes | Yes | Yes | No | No | No | No | Communication utility was trench lead | None | N/A | N/A | None | N/A | N/A
WATSONVILLE | FREEDOM BLVD, WATSONVILLE | 31001028 | FREEDOM BLVD | 95076 | 6087110501 | No | 13.33% | FREEDOM BLVD, WEST HIGH ST & MILES LN | None | Project met one or more Rule 20A criteria | Resolution# 135-12 | Yes | 11 | 4 | 4 | 0 | 5 | Suburban | No | 2012-09-11 | 2014-03-10 | 2016-03-18 | 2016-06-14 | 2018 | 2018-04-30 | N/A | 545 | N/A | N/A | 18 | 47 | 1.1971 | 6320.4331 | Residential | Yes |  |  |  | N/A | 1368203.78 | TBD | 1368203.78 | [6 empty] | 0 | N/A |  |  | 0 |  |  |  | Increase in AFUDC |  |  | 1368203.78 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | No | No | Unknown | None | N/A | N/A | None | N/A | N/A
WATSONVILLE | LAKE AVE, WATSONVILLE | No Order | LAKE AVE, UUD# 21 | 95076 | Unknown | Unknown | Unknown | LAKE AVE, RODRIGUEZ ST & BRENNAN ST & UNION ST | Unknown | Project met one or more Rule 20A criteria | Resolution# 48-14 | No | 11 | 4 | 4 | 0 | 5 | Unknown | Unknown | 2014-04-22 | TBD | TBD | TBD | TBD | N/A | N/A | #VALUE! | TBD | N/A |  |  | Project not completed or closed | Project not completed or closed | Unknown | Unknown | TBD | TBD | TBD | 2386616 | N/A | TBD | N/A | [6 empty] | TBD | TBD |  |  | 0 |  |  |  | Project in planning phase |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | Yes | No | No | No | No | No | Unknown | None | N/A | N/A | None | N/A | N/A
Santa Cruz County Total | [41 empty] | 0
Shasta County | [41 empty] | 0
ANDERSON | BALLS FERRY RD | 30644207 | BALLS FERRY RD | 96007 | 6089012102 | No | 28.65% | BALLS FERRY RD, SOUTH ST | None | Project met one or more Rule 20A criteria | Resolution# 08-23 | Yes | 7 | 0 | 0 | 0 | 6 | Urban | No | 2008-03-04 | 2009-08-31 | 2013-07-18 | 2013-12-13 | 2015 | 2015-10-06 | N/A | 545 | N/A | N/A | 26 | 27 | 1.11 | 3960 | Commercial | Yes |  |  |  | N/A | 3333295.26 | 1.0677 | 3559036.561 | [6 empty] | 0 | N/A |  |  | 0 |  |  |  | Other |  |  | 3333295.26 |  |  |  |  | Yes | 500000 | Shasta County | 15% | 0 | PG&E does not grant approval for credit transfer transactions. Credit transfers are agreed upon between communities. | No | Yes | Yes | No | Yes | Unknown | Unknown | Easement acquisitions. Communication utility backed out of trench. City not supportive in finding resolution to easement issues. | None | N/A | N/A | None | N/A | N/A
ANDERSON | NORTH STREET, ANDERSON RULE 20A *CANC | 30406410 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | 7 | 0 | 0 | 0 | 6 | N/A | N/A | TBD | TBD | TBD | TBD | N/A | 2007-03-24 | N/A | #VALUE! | N/A | 2006-02-27 | N/A | N/A | Cancelled project | Cancelled project | N/A | N/A | N/A | N/A | N/A | N/A | 542.12 | 1.4306 | 775.5445 | [6 empty] | N/A | N/A |  |  | 0 |  |  |  | N/A, project cancelled |  |  | 542.12 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SHASTA COUNTY | EP-SHINGLETOWN RULE 20A | 30050139 | SHINGLETOWN | 96088 | 6089012603 | No | 15.38% | SHINGLETOWN | Tier 3 | TBD | TBD | Yes | 7 | 0 | 0 | 0 | 6 | Unknown | No | TBD | 2001-08-17 | 2003-07-10 | 2003-12-21 | 2005 | 2007-03-24 | N/A | #VALUE! | N/A | N/A |  |  | 1.46 | 4593.6 | Unknown | Unknown |  |  |  | N/A | 1003999.67 | 1.7065 | 1713336.1859 | [10 empty] | 0 |  |  |  | Unknown |  |  | 1003999.67 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
SHASTA COUNTY | OC4 EP RULE 20A CYPRESS & HILLTOP REDING | 30533492 | CYPRESS & HILLTOP REDING | 96002 | 6089010300 | No | 7.931% | CYPRESS & HILLTOP REDING | None | TBD | TBD | Yes | 7 | 0 | 0 | 0 | 6 | Urban | No | 2006-03-26 | 2007-05-11 | 2008-09-15 | 2008-10-30 | 2010 | 2011-03-16 | N/A | 411 | N/A | N/A | 9 | 0 | 0.19 | 1214.4 | Residential | No |  |  |  | N/A | 193839 | 1.249 | 242100.9882 | [6 empty] | 0 | N/A |  |  | 0 | [6 empty] | 193839 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | No | No | None | None | N/A | N/A | None | N/A | N/A
SHASTA COUNTY | PARKVIEW AVE, REDDING | 30321001 | PARKVIEW AVE, REDDING | 96001 | 6089010400 | No | 7.698% | PARKVIEW AVE, REDDING | None | TBD | TBD | Yes | 7 | 0 | 0 | 0 | 6 | Unknown | No | 2003-06-17 | 2003-08-06 | 2006-03-16 | 2006-11-03 | 2007 | 2008-02-15 | N/A | 50 | N/A | N/A |  |  | 0.45 | 1953.6 | Unknown | Unknown |  |  |  | N/A | 709869.62 | 1.4306 | 1015523.3129 | [10 empty] | 0 |  |  |  | Unknown |  |  | 709869.62 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
SHASTA COUNTY | SHASTA DAM BLVD, SHASTA LAKE | 30302872 | SHASTA DAM BLVD, SHASTA LAKE | 96019 | 6089011702 | No | 11.05% | SHASTA DAM BLVD, SHASTA LAKE | Part of project in or adjacent to Tier 2 | TBD | TBD | Yes | 7 | 0 | 0 | 0 | 6 | Unknown | No | 2003-04-01 | 2003-12-05 | 2004-09-23 | 2005-05-03 | 2008 | 2008-08-18 | N/A | 248 | N/A | N/A |  |  | 0.5 | 2640 | Unknown | Unknown |  |  |  | N/A | 275197.53 | 1.3051 | 359172.0701 | [10 empty] | 0 |  |  |  | Unknown |  |  | 275197.53 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
SHASTA COUNTY | XP-SHINGLTWN RL 20A INSTALL UG WETLANDS | 30280632 | SHINGLETOWN | 93636 | 6039000509 | No | 6.992% | SHINGLETOWN | None | TBD | TBD | Yes | 7 | 0 | 0 | 0 | 6 | Unknown | No | TBD | 2002-09-27 | 2002-10-30 | 2003-11-10 | 2005 | 2007-03-24 | N/A | #VALUE! | N/A | N/A |  |  | No primary UG circuit data found | 52.8 | Unknown | Unknown |  |  |  | N/A | 173635.43 | 1.7065 | 296310.7203 | [10 empty] | 0 |  |  |  | Unknown |  |  | 173635.43 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
Shasta County Total | [41 empty] | 0
Sierra County | [41 empty] | 0
SIERRA COUNTY | MAIN STREET, SIERRA CITY | No Order | THE SIERRA CITY MAIN STREET PROJECT AND UUD | 96125 | Unknown | No | Unknown | MAIN ST SIERRA CITY | Tier 2 | Project met one or more Rule 20A criteria | Resolution# 2019-112 | No | 1 | 1 | 1 | 0 | 0 | Rural | No | 2019-07-23 | TBD | TBD | TBD | TBD | N/A | N/A | #VALUE! | 0 | N/A | 0 | 0 | Project not completed or closed | Project not completed or closed | Residential | Unknown | TBD | TBD | TBD | 7165277 | N/A | TBD | N/A | [6 empty] | TBD | TBD | [6 empty] | Project in planning phase |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | Yes | No | No | Insufficient allocation | None | N/A | N/A | No | N/A | N/A
Sierra County Total | [41 empty] | 0
Solano County | [41 empty] | 0
DIXON | EAST A STREET, DIXON | No Order | EAST A STREET DIXON R20A UUD | 95620 | 6095253402 | No | 13.86% | EAST A STREET BTW N. 2ND ST AND DOYLE LN | None | Project met one or more Rule 20A criteria | Resolution# 19-136 | No | 10 | 3 | 3 | 0 | 5 | Suburban | No | 2019-07-16 | TBD | TBD | TBD | TBD | N/A | N/A | #VALUE! | 0 | N/A | 0 | 0 | Project not completed or closed | Project not completed or closed | Commercial | Unknown | TBD | TBD | TBD | 2790534.48 | N/A | TBD | N/A | [6 empty] | TBD | TBD | [6 empty] | Project in planning phase |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | Yes | No | No | Insufficient allocation | None | N/A | N/A | No | N/A | N/A
FAIRFIELD | C:GEP PURGE CABLE, N. TEXAS/ TRAVIS, R20 | 30025922 | N TEXAS/ TRAVIS | 94533 | 6095252607 | No | 15.71% | N TEXAS/ TRAVIS | None | TBD | TBD | Yes | 10 | 3 | 3 | 0 | 5 | Unknown | No | TBD | 1998-11-02 | 2000-11-06 | 2002-12-31 | 2005 | 2007-03-24 | N/A | #VALUE! | N/A | N/A |  |  | 1.6 | 5174.4 | Unknown | Unknown |  |  |  | N/A | 1451380.782 | 1.7065 | 2476796.8433 | [10 empty] | 0 |  |  |  | Unknown |  |  | 1451380.782 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
FAIRFIELD | TRAVIS BLVD, FAIRFIELD | 30674762 | TRAVIS BLVD, FAIRFIELD | 94534 | 6095252606 | No | 15.56% | TRAVIS BLVD | None | Project met one or more Rule 20A criteria | Resolution# 2006-16 | No | 10 | 3 | 3 | 0 | 5 | Unknown | No | 2006-09-19 | TBD | TBD | TBD | N/A | N/A | N/A | #VALUE! | N/A | TBD |  |  | Cancelled project | Cancelled project | Unknown | N/A | N/A | N/A | N/A | 7428.77 | N/A | TBD | N/A | [6 empty] | N/A | N/A |  |  | 0 |  |  |  | N/A, project cancelled |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | Unknown | Unknown | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
RIO VISTA | MAIN ST PH 2, RIO VISTA | No Order | MAIN ST PH 2 | 94571 | 6095253500 | Unknown | 10.13% | MAIN ST FROM 4TH ST TO HWY 12 | None | Project met one or more Rule 20A criteria | Resolution# 2019-029 | No | 10 | 3 | 3 | 0 | 5 | Suburban | Unknown | 2019-06-18 | TBD | TBD | TBD | TBD | N/A | N/A | #VALUE! | 0 | N/A | 0 | 0 | Project not completed or closed | Project not completed or closed | Commercial | Unknown | TBD | TBD | TBD | 2405502 | N/A | TBD | N/A | [6 empty] | TBD | TBD | [6 empty] | Project in planning phase |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | Yes | No | No | Insufficient allocation | None | N/A | N/A | No | N/A | N/A
VACAVILLE | *CANC* R4 VACAVILLE / BUCK AVE RULE 20A | 30550905 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | 10 | 3 | 3 | 0 | 5 | N/A | N/A | 2004-07-13 | TBD | TBD | TBD | N/A | 2010-08-26 | N/A | #VALUE! | N/A | 2010-05-26 | N/A | N/A | Cancelled project | Cancelled project | N/A | N/A | N/A | N/A | N/A | N/A | 93924 | 1.249 | 117309.1752 | [6 empty] | N/A | N/A |  |  | 0 |  |  |  | N/A, project cancelled |  |  | 93924 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
VACAVILLE | LOVERS LANE | 30288220 | LOVERS LANE | 95688 | 6095253101 | No | 10.23% | LOVERS LANE | Part of project in or adjacent to Tier 2 | TBD | TBD | Yes | 10 | 3 | 3 | 0 | 5 | Unknown | No | 2002-09-24 | 2003-01-13 | 2003-07-11 | 2004-04-12 | 2007 | 2007-07-31 | N/A | 111 | N/A | N/A |  |  | 0.57 | 2059.2 | Unknown | Unknown |  |  |  | N/A | 258582.97 | 1.4306 | 369922.9083 | [10 empty] | 0 |  |  |  | Unknown |  |  | 258582.97 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
VACAVILLE | MASON ST. (DAVIS-MERCHANT) | 30155323 | MASON ST (DAVIS-MERCHANT) | 95688 | 6095253101 | No | 10.23% | MASON ST (DAVIS-MERCHANT) | None | TBD | TBD | Yes | 10 | 3 | 3 | 0 | 5 | Unknown | No | TBD | TBD | TBD | 2006-08-29 | 2007 | 2007-07-31 | N/A | #VALUE! | N/A | N/A |  |  | 0.55 | 1425.6 | Unknown | Unknown |  |  |  | N/A | 576142.84 | 1.4306 | 824216.8267 | [10 empty] | 0 |  |  |  | Unknown |  |  | 576142.84 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
VACAVILLE | VANDEN RD | 31038742 | VANDEN RD | 95687 | 6095252915 | No | 4.335% | VANDEN RD, LEISURE TOWN RD | None | Project met one or more Rule 20A criteria | Resolution# 2013-042 | Yes | 10 | 3 | 3 | 0 | 5 | Suburban | No | 2013-06-11 | 2014-06-09 | 2015-06-10 | 2015-09-11 | 2016 | 2016-07-20 | N/A | 363 | N/A | N/A | 9 | 0 | 0.28 | 1531.2 | Residential | Yes |  |  |  | N/A | 708335.83 | 1.0668 | 755675.2958 | [6 empty] | 0 | N/A |  |  | 0 |  |  |  | Restrictive work conditions |  |  | 708335.83 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | No | No | Heavy traffic control and work hour restrictions | None | N/A | N/A | None | N/A | N/A
VALLEJO | WILSON AVE PHII, RULE 20, VALLEJO | 30213683 | WILSON AVE PH 2, VALLEJO | 94590 | 6095251701 | No | 17.67% | WILSON AVE PH 2, VALLEJO | None | TBD | TBD | Yes | 10 | 3 | 3 | 0 | 5 | Suburban | No | TBD | TBD | TBD | 2008-11-17 | 2010 | 2010-08-26 | N/A | #VALUE! | N/A | N/A | 22 |  | 0.4 | 2112 | Residential | Unknown |  |  |  | N/A | 491493 | 1.249 | 613864.8104 | [6 empty] | 0 | N/A |  |  | 0 | [6 empty] | 491493 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
VALLEJO | SACRAMENTO ST, VALLEJO | No Order | UUD NO. 19-1 | 94590 | 6095251702 | No | 12.57% | SACRAMENTO ST BTW PIKE ST & FRISBIE ST | None | Project met one or more Rule 20A criteria | Resolution# 19-083 N.C. | No | 10 | 3 | 3 | 0 | 5 | Rural | No | 2019-07-23 | TBD | TBD | TBD | TBD | N/A | N/A | #VALUE! | 0 | N/A | 0 | 0 | Project not completed or closed | Project not completed or closed | Residential | Unknown | TBD | TBD | TBD | 5681452.83 | N/A | TBD | N/A | [6 empty] | TBD | TBD | [6 empty] | Project in planning phase |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | Yes | No | No | Insufficient allocation | None | N/A | N/A | No | N/A | N/A
Solano County Total | [41 empty] | 0
Sonoma County | [41 empty] | 0
HEALDSBURG | HEALDSBURG AVE BRIDGE | 31051957 | HEALDSBURG AVE BRIDGE | 95448 | 6097153902 | No | 5.787% | HEALDSBURG AVE BRIDGE | None | TBD | TBD | Yes | 16 | 5 | 5 | 0 | 9 | Unknown | No | TBD | 2014-03-24 | 2014-09-05 | 2014-10-03 | 2016 | 2016-04-09 | N/A | #VALUE! | N/A | N/A |  |  | 0.12 | 633.6 | Unknown | Unknown |  |  |  | N/A | 81345.13 | 1.0668 | 86781.5838 | [10 empty] | 0 |  |  |  | Unknown |  |  | 81345.13 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
PETALUMA | BODEGA AVE | 30395065 | BODEGA AVE | 94952 | 6097150902 | No | 4.687% | BODEGA AVE | None | TBD | TBD | Yes | 16 | 5 | 5 | 0 | 9 | Suburban | No | 2004-09-13 | 2006-12-04 | 2008-06-19 | 2010-09-07 | 2012 | 2012-09-13 | N/A | 812 | N/A | N/A | 12 | 29 | 0.94 | 2745.6 | Residential | Yes |  |  |  | N/A | 2622095.72 | 1.121 | 2939477.5765 | [6 empty] | 0 | N/A |  |  | 0 | [6 empty] | 2622095.72 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
PETALUMA | BODEGA AVE PH 2, PETALUMA | 30762469 | BODEGA AVE PH 2 | 94952 | Unknown | Unknown | Unknown | BODEGA AVE, NORTH WEBSTER ST & KEOKUK ST | Unknown | Project met one or more Rule 20A criteria | Resolution# 2004-168 | No | 16 | 5 | 5 | 0 | 9 | Unknown | Unknown | 2004-09-13 | TBD | TBD | TBD | TBD | N/A | N/A | #VALUE! | 2021-10-01 | N/A |  |  | Project not completed or closed | Project not completed or closed | Unknown | Unknown | TBD | TBD | TBD | 4547596.36 | N/A | TBD | N/A | [6 empty] | TBD | TBD |  |  | 0 |  |  |  | Project in planning phase |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | Yes | Yes | No | Insufficient allocation. City lacks funding for streetlights. | None | N/A | N/A | None | N/A | N/A
PETALUMA | PETALMA BLVD NORTH | 30692249 | PETALMA BLVD NORTH | 94952 | 6097151000 | No | 4.02% | PETALUMA BLVD NORTH, INDUSTRIAL RD & STONY PT RD | None | TBD | Resolution# 2008-216 | Yes | 16 | 5 | 5 | 0 | 9 | Suburban | No | 2008-10-17 | 2012-01-03 | 2012-10-31 | 2013-05-08 | 2015 | 2015-07-14 | N/A | 1173 | N/A | N/A | 17 | 4 | 0.41 | 2745.6 | Commercial | Yes |  |  |  | N/A | 1767994.75 | 1.0677 | 1887728.9481 | [6 empty] | 5774 | 100% |  |  | 0 | [6 empty] | 1767994.75 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | Unknown | Unknown | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
ROHNERT PARK | ADRIAN DRIVE, ROHNERT PARK | 30247819 | ADRIAN DR, PH 2, UUD# 6 | 94928 | Unknown | Unknown | Unknown | ADRIAN DR, BRUCE AVE & E COTATI AVE | Unknown | Project met one or more Rule 20A criteria | Resolution# 93-150 | No | 16 | 5 | 5 | 0 | 9 | Unknown | Unknown | 1993-12-14 | TBD | TBD | TBD | TBD | N/A | N/A | #VALUE! | N/A | TBD |  |  | Cancelled project | Cancelled project | Unknown | N/A | N/A | N/A | N/A | 75135.64 | N/A | TBD | N/A | [6 empty] | N/A | N/A |  |  | 0 |  |  |  | N/A, project cancelled |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | Yes | No | No | Insufficient allocation | None | N/A | N/A | None | N/A | N/A
ROHNERT PARK | SNYDER LANE | 31068171 | SNYDER LANE | 94928 | 6097151310 | No | 4.493% | SNYDER LN, RANCHO COTATE HIGH SCHOOL | None | Project met one or more Rule 20A criteria | Resolution# 2014-048 | Yes | 16 | 5 | 5 | 0 | 9 | Suburban | No | 2014-05-13 | 2014-07-01 | 2015-03-10 | 2015-05-29 | 2016 | 2016-04-09 | N/A | 49 | N/A | N/A | 9 | 0 | 0.55 | 1742.4 | Commercial | Yes |  |  |  | N/A | 991808.18 | 1.0668 | 1058092.6562 | [6 empty] | 3517 | 100% |  |  | 0 | [6 empty] | 991808.18 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | No | Unknown | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
ROHNERT PARK | E COTATI AVE ROHNERT PARK R20A | 35051448 | E COTATI AVE | 94928 | 6097151310 | No | 4.493% | ALONG PORTION OF E COTATI AVE | None | Project met one or more Rule 20A criteria | Resolution# 2018-073 | No | 16 | 5 | 5 | 0 | 9 | Rural | No | 2018-05-08 | 2018-08-31 | TBD | TBD | TBD | N/A | N/A | 115 | 2020-01-31 | N/A | 0 | 0 | Project not completed or closed | Project not completed or closed | Residential | Yes | TBD | TBD | TBD | 2489805.95 | N/A | TBD | N/A | [6 empty] | TBD | TBD | [6 empty] | Project in planning phase |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | Yes | No | No | Insufficient allocation | None | N/A | N/A | No | N/A | N/A
SANTA ROSA | *CANC* E-STONY POINT RULE 20A, SANT*CANC | 30312923 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | 16 | 5 | 5 | 0 | 9 | N/A | N/A | TBD | TBD | TBD | TBD | N/A | 2007-07-31 | N/A | #VALUE! | N/A | 2007-03-02 | N/A | N/A | Cancelled project | Cancelled project | N/A | N/A | N/A | N/A | N/A | N/A | 5086 | 1.4306 | 7275.9158 | [6 empty] | N/A | N/A |  |  | 0 |  |  |  | N/A, project cancelled |  |  | 5086 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SANTA ROSA | STONY PT RD | 30256639 | STONY PT RD | 95407 | 6097153103 | No | 13.21% | STONY POINT RD, SEBASTOPOL RD & HEARN ST | None | Project met one or more Rule 20A criteria | Resolution# 27678 | Yes | 16 | 5 | 5 | 0 | 9 | Suburban | No | 2002-10-08 | 2012-01-24 | 2014-07-07 | 2015-02-05 | 2016 | 2017-01-13 | N/A | 3395 | N/A | N/A | 41 | 50 | 2.14 | 7550.4 | Residential | Yes |  |  |  | N/A | 8853447.51 | 1.0668 | 9445140.6846 | [6 empty] | 0 | N/A |  |  | 0 | [6 empty] | 8853447.51 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | Unknown | Yes | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
SANTA ROSA | WEST STEELE LANE | 30282030 | WEST STEELE LANE | 95403 | 6097152903 | No | 9.66% | WEST STEELE LANE | None | TBD | TBD | Yes | 16 | 5 | 5 | 0 | 9 | Unknown | No | TBD | TBD | TBD | 2005-05-18 | 2007 | 2007-07-31 | N/A | #VALUE! | N/A | N/A |  |  | 1.13 | 4329.6 | Unknown | Unknown |  |  |  | N/A | 1019413.14 | 1.4306 | 1458349.2235 | [6 empty] | Unknown | Unknown |  |  | 0 | [6 empty] | 1019413.14 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
SANTA ROSA, SONOMA COUNTY | R20A - FULTON RD SANTA ROSA | 74013528 | FULTON RD | 95403 | Unknown | Unknown | Unknown | FULTON RD, GUERNEVILLE RD & PINER RD | Unknown | Project met one or more Rule 20A criteria | Resolution# 2017-026 | No | 16 | 5 | 5 | 0 | 9 | Suburban | Unknown | 2017-02-14 | 2017-12-01 | TBD | TBD | TBD | N/A | N/A | 290 | 2020-07-20 | N/A | TBD | TBD | Project not completed or closed | Project not completed or closed | Residential | Yes | TBD | TBD | TBD | 4542387.82 | N/A | TBD | N/A | [6 empty] | TBD | TBD |  |  | 0 |  |  |  | Project in progress |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Yes | No | No | Yes | No | No | No |  | Unknown | 0 | 0 | Unknown | 0 | 0
SONOMA COUNTY | FREESTONE, SONOMA COUNTY | 30256790 | FREESTONE, UUD# 1 | 95472 | Unknown | Unknown | Unknown | BOHEMIAN HWY, FREESTONE ST, EL CAMINO BODEGA | Unknown | Project met one or more Rule 20A criteria | Resolution# 99-0725 | No | 16 | 5 | 5 | 0 | 9 | Unknown | Unknown | 1999-06-08 | 2018-09-27 | TBD | TBD | TBD | N/A | N/A | 7051 | 2021-12-31 | N/A |  |  | Project not completed or closed | Project not completed or closed | Unknown | Unknown | TBD | TBD | TBD | 4304938.26 | N/A | TBD | N/A | [6 empty] | TBD | TBD |  |  | 0 |  |  |  | Project in planning phase |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | No | No | Cultural issues | None | N/A | N/A | Yes | TBD | TBD
SONOMA COUNTY | GRATON RD, SONOMA COUNTY | 30766668 | GRATON RD | 95444 | 6097153600 | No | 4.524% | GRATON RD, RAILROAD AVE & S BRUSH ST | None | Project met one or more Rule 20A criteria | Resolution# 99-0964 | No | 16 | 5 | 5 | 0 | 9 | Unknown | No | 1999-07-30 | TBD | TBD | TBD | TBD | N/A | N/A | #VALUE! | 2022-01-01 | N/A |  |  | Project not completed or closed | Project not completed or closed | Unknown | Unknown | TBD | TBD | TBD | 2004343.18 | N/A | TBD | N/A | [6 empty] | TBD | TBD |  |  | 0 |  |  |  | Project in planning phase |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | No | No | Unknown | None | N/A | N/A | None | N/A | N/A
SONOMA COUNTY | HIGHWAY 12, PH 3 | 30069479 | HIGHWAY 12, PH 3 | 95476 | 6097150305 | No | 9.277% | HIGHWAY 12, PH 3 | None | TBD | TBD | Yes | 16 | 5 | 5 | 0 | 9 | Suburban | No | 1999-04-13 | 1999-05-12 | 2002-04-22 | 2011-09-20 | 2013 | 2014-02-28 | N/A | 29 | N/A | N/A | 36 |  | 1.9 | 6916.8 | Residential | Yes |  |  |  | N/A | 7371678 | 1.1048 | 8144258.7001 | [6 empty] | 3244 | 100% |  |  | 0 |  |  |  | Labor costs |  |  | 7371678 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
SONOMA COUNTY | SALMON CREEK, SONOMA COUNTY | No Order | SALMON CREEK, UUD# 1 | 94923 | Unknown | Unknown | Unknown | SALMON CREEK, HWY 12 & MARYANA DR | Unknown | Project met one or more Rule 20A criteria | Resolution# 97-1247 | No | 16 | 5 | 5 | 0 | 9 | Unknown | Unknown | 1997-09-09 | TBD | TBD | TBD | TBD | N/A | N/A | #VALUE! | TBD | N/A |  |  | Project not completed or closed | Project not completed or closed | Unknown | Unknown | TBD | TBD | TBD | 1280000 | N/A | TBD | N/A | [6 empty] | TBD | TBD |  |  | 0 |  |  |  | Project in planning phase |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | No | No | Unknown | None | N/A | N/A | None | N/A | N/A
SONOMA COUNTY | STATE HWY 1 - JENNER | 30069477 | STATE HWY 1 - JENNER | 95450 | 6097154304 | No | 7.25% | STATE HWY 1 - JENNER | None | TBD | TBD | Yes | 16 | 5 | 5 | 0 | 9 | Unknown | No | 1997-09-16 | 1999-05-12 | 2004-03-26 | 2004-08-17 | 2007 | 2007-07-31 | N/A | 603 | N/A | N/A |  |  | 0.64 | 3273.6 | Unknown | Unknown |  |  |  | N/A | 1007477.46 | 1.4306 | 1441274.3115 | [10 empty] | 0 |  |  |  | Unknown |  |  | 1007477.46 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
SONOMA, SONOMA COUNTY | BROADWAY | 30302192 | BROADWAY | 95476 | 6097150203 | No | 6.371% | BROADWAY | None | TBD | TBD | Yes | 16 | 5 | 5 | 0 | 9 | Suburban | No | 2002-09-18 | 2003-02-12 | 2009-04-27 | 2010-03-01 | 2012 | 2012-09-13 | N/A | 147 | N/A | N/A | 24 | 13 | 1.42 | 3854.4 | Commercial | Yes |  |  |  | N/A | 2141796.78 | 1.121 | 2401042.6318 | [6 empty] | Unknown | 100% |  |  | 0 | [6 empty] | 2141796.78 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
Sonoma County Total | [41 empty] | 0
Stanislaus County | [41 empty] | 0
NEWMAN | CITY OF NEWMAN, PH 1 | 30579877 | CITY OF NEWMAN PH 1, UUD# 5 | 95360 | 6099003500 | No | 16.06% | TULARE ST, N ST, FRESNO ST, MAIN ST | None | Project met one or more Rule 20A criteria | Resolution# 2007-48 | Yes | 6 | 0 | 0 | 0 | 4 | Suburban | No | 2003-06-05 | 2008-04-11 | 2008-05-02 | 2008-11-03 | 2009 | 2009-07-29 | N/A | 1772 | N/A | N/A | 3 | 7 | 0.21 | 686.4 | Commercial | Yes |  |  |  | N/A | 312071.45 | 1.2297 | 383747.6109 | [6 empty] | 0 | N/A |  |  | 0 |  |  |  | Labor costs |  |  | 312071.45 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Yes | Yes | Yes | No | Yes | Yes | No | After PG&E completed trench design, Communication utility did not agree with trench costs but refused to take the trench lead | None | N/A | N/A | None | N/A | N/A
NEWMAN | KERN TO MERCED PH 2, NEWMAN | 30657421 | KERN ST & MERCED ST PH 2, UUD# 5-A & 5-B | 95360 | Unknown | Unknown | Unknown | MARIPOSA ST, N ST, TULARE ST, MAIN ST & FRESNO ST, N ST, MERCED ST, MAIN ST | Unknown | Project met one or more Rule 20A criteria | Resolution# 2007-48 | No | 6 | 0 | 0 | 0 | 4 | Suburban | Unknown | 2003-06-05 | TBD | TBD | TBD | N/A | N/A | N/A | #VALUE! | N/A | TBD | N/A | N/A | Cancelled project | Cancelled project | Residential | N/A | N/A | N/A | N/A | 286572.16 | N/A | TBD | N/A | [6 empty] | TBD | TBD |  |  | 0 |  |  |  | N/A, project cancelled |  |  | N/A |  |  |  |  | Yes | Unknown | Stanislaus County | N/A | 0 | PG&E does not grant approval for credit transfer transactions. Credit transfers are agreed upon between communities. | Yes | Yes | Yes | Yes | No | Yes | Yes | Lack of adequate space in the alley to install a joint trench | TBD | TBD | TBD | TBD | TBD | TBD
NEWMAN | KERN TO MERCED PH 3, NEWMAN | 30709856 | KERN ST & MERCED ST PH 3, UUD# 5-C | 95360 | Unknown | Unknown | Unknown | KERN ST, MAIN ST, MERCED ST, P ST | Unknown | Project met one or more Rule 20A criteria | Resolution# 2007-48 | No | 6 | 0 | 0 | 0 | 4 | Unknown | Unknown | 2003-06-05 | TBD | TBD | TBD | N/A | N/A | N/A | #VALUE! | N/A | TBD |  |  | Cancelled project | Cancelled project | Unknown | N/A | N/A | N/A | N/A | 4815.27 | N/A | TBD | N/A | [6 empty] | N/A | N/A |  |  | 0 |  |  |  | N/A, project cancelled |  |  | N/A |  |  |  |  | Yes | Unknown | Stanislaus County | N/A | 0 | PG&E does not grant approval for credit transfer transactions. Credit transfers are agreed upon between communities. | No | Yes | No | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
OAKDALE | HWY 108 "F" OAKDALE | 30339515 | HWY 108 "F" OAKDALE | 95361 | 6099000201 | Yes | 12.56% | HWY 108 "F" OAKDALE | None | TBD | TBD | Yes | 6 | 0 | 0 | 0 | 4 | Unknown | Yes | 2003-07-07 | 2003-12-01 | 2004-01-12 | 2005-03-22 | 2007 | 2007-07-31 | N/A | 147 | N/A | N/A |  |  | 1.28 | 6019.2 | Unknown | Unknown |  |  |  | N/A | 1370320.68 | 1.4306 | 1960349.5592 | [10 empty] | 0 |  |  |  | Unknown |  |  | 1370320.68 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
OAKDALE | SOUTH YOSEMITE AVE, OAKDALE | 31059557 | SOUTH YOSEMITE AVE | 95361 | 6099000203 | Yes | 14.22% | SOUTH YOSEMITE AVE, E H ST TO E J ST | None | Project met one or more Rule 20A criteria | Resolution# 2013-04 | Yes | 6 | 0 | 0 | 0 | 4 | Urban | Yes | 2013-01-07 | 2014-07-07 | 2015-07-13 | 2015-12-29 | 2017 | 2017-07-17 | N/A | 546 | N/A | N/A | 11 | 15 | 0.59 | 2217.6 | Commercial | Yes |  |  |  | N/A | 1735838.73 | 1.048 | 1819235.2756 | [6 empty] | 0 | 0% |  |  | 0 |  |  |  | Other |  |  | 1735838.73 |  |  |  |  | Yes | 1150000 | Stanislaus County | 66.25% | 0 | PG&E does not grant approval for credit transfer transactions. Credit transfers are agreed upon between communities. | Yes | Yes | Yes | Yes | No | No | No | Soil conditions required additional materials and work during construction. Initial Buy America designation incorrect. | None | N/A | N/A | None | N/A | N/A
RIVERBANK, STANISLAUS COUNTY | CITY OF RIVERBANK | 30406568 | CITY OF RIVERBANK, UUD# 4 | 95367 | 6099000303 | Yes | 12.48% | PATTERSON RD (HWY 108), OAKDALE RD & CALLENDAR Y | None | Project met one or more Rule 20A criteria | Resolution# 2002-131 | Yes | 6 | 0 | 0 | 0 | 4 | Urban | Yes | 2001-11-12 | 2008-05-28 | 2008-12-30 | 2011-09-12 | 2014 | 2015-01-15 | N/A | 2389 | N/A | N/A | 21 | 24 | 1 | 3643.2 | Commercial | Yes |  |  |  | N/A | 3010033.41 | 1.0831 | 3260113.8653 | [6 empty] | 0 | 0% |  |  | 0 |  |  |  | Other |  |  | 3010033.41 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Yes | No | Yes | Yes | Yes | No | No | Insufficient allocation. Caltrans inspection requirements. | None | N/A | N/A | None | N/A | N/A
Stanislaus County Total | [41 empty] | 0
Sutter County | [41 empty] | 0
LIVE OAK | LIVE OAK BLVD, LIVE OAK | 74015720 | LIVE OAK BLVD | 95953 | Unknown | Unknown | Unknown | LIVE OAK BLVD, ASH ST & RAMSDELL DR | Unknown | Project met one or more Rule 20A criteria | Resolution# 45-2017 | No | 7 | 3 | 2 | 1 | 2 | Urban | Unknown | 2017-08-16 | 2018-03-01 | 2019-05-17 | TBD | TBD | N/A | N/A | 197 | 2021-02-04 | N/A | TBD | TBD | Project not completed or closed | Project not completed or closed | Commercial | Yes | TBD | TBD | TBD | 6124583.11 | N/A | TBD | N/A | [6 empty] | TBD | TBD |  |  | 0 |  |  |  | Unexpected field conditions |  |  | N/A |  |  |  |  | Yes | 3300000 | Sutter County, Rocklin | N/A | 500000 | PG&E does not grant approval for credit transfer transactions. Credit transfers are agreed upon between communities. | Yes | Yes | Yes | Yes | Yes | Yes | No | Insufficient allocation. Response times from Communication utility delayed design slightly. Caltrans future improvements caused re-design. Multiple unmarked utilities encountered during construction. | None | N/A | N/A | None | N/A | N/A
SUTTER COUNTY | BARRY RD, SUTTER COUNTY | 31242522 | BARRY RD | 95991 | Unknown | Unknown | Unknown | BARRY RD, HWY 99 | Unknown | Project met one or more Rule 20A criteria | Resolution# 16-022 | No | 7 | 3 | 2 | 1 | 2 | Suburban | Unknown | 2016-04-12 | 2016-07-18 | 2019-07-01 | TBD | TBD | N/A | N/A | 97 | 2019-07-30 | N/A | TBD | TBD | Project not completed or closed | Project not completed or closed | Residential | Yes | TBD | TBD | TBD | 1082551.09 | N/A | TBD | N/A | [6 empty] | TBD | TBD |  |  | 0 |  |  |  | Project in progress |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | Yes | No | Yes | No | Yes | Unknown | Easement acquisitions. Caltrans permit. | None | N/A | N/A | None | N/A | N/A
YUBA CITY | BRIDGE ST, YUBA CITY | 30177662 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | 7 | 3 | 2 | 1 | 2 | N/A | N/A | 2004-12-31 | TBD | TBD | TBD | N/A | 2008-02-15 | N/A | #VALUE! | N/A | 2007-08-03 | N/A | N/A | Cancelled project | Cancelled project | N/A | N/A | N/A | N/A | N/A | N/A | 6763.46 | 1.3051 | 8827.281 | [6 empty] | N/A | N/A |  |  | 0 |  |  |  | N/A, project cancelled |  |  | 6763.46 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
YUBA CITY | SECOND ST YUBA CITY PH II | 74010531 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | 7 | 3 | 2 | 1 | 2 | N/A | N/A | 2012-03-20 | TBD | TBD | TBD | TBD | N/A | N/A | #VALUE! | N/A | TBD | N/A | N/A | Cancelled project | Cancelled project | N/A | N/A | N/A | N/A | N/A | N/A | N/A | TBD | N/A | [6 empty] | N/A | N/A |  |  | 0 |  |  |  | N/A, project cancelled |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
YUBA CITY | SECOND ST, YUBA CITY | 30918673 | SECOND ST | 95993 | 6101050202 | No | 22.05% | SECOND ST, B ST & TEEGARDEN AVE | None | Project met one or more Rule 20A criteria | Resolution# 12-014 | Yes | 7 | 3 | 2 | 1 | 2 | Urban | No | 2012-03-20 | 2014-04-25 | 2017-05-08 | 2017-09-06 | 2018 | 2019-02-19 | N/A | 766 | N/A | N/A | 7 | 1 | 0.48526 | 2562.1587 | Commercial | Yes |  |  |  | N/A | 1726573 | TBD | 1726573 | [6 empty] | 0 | N/A |  |  | 0 |  |  |  | Labor costs |  |  | 1726573 |  |  |  |  | Yes | 2800000 | Sutter County | 162.2% | 0 | PG&E does not grant approval for credit transfer transactions. Credit transfers are agreed upon between communities. | No | Yes | No | Yes | No | No | No | Easement acquisitions. Cultural issues. | None | N/A | N/A | Yes | 0 | 0
YUBA CITY | WALTON AVE | 30348512 | WALTON AVE | 95993 | Unknown | Unknown | Unknown | WALTON AVE | Unknown | TBD | TBD | Yes | 7 | 3 | 2 | 1 | 2 | Unknown | Unknown | 2002-03-19 | 2004-02-15 | Unknown | 2007-09-05 | 2007 | 2008-02-15 | N/A | 698 | N/A | N/A |  |  | No primary UG circuit data found | 0 | Unknown | Unknown |  |  |  | N/A | 207406.39 | 1.4306 | 296710.8584 | [10 empty] | 0 |  |  |  | Unknown |  |  | 207406.39 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
YUBA CITY | BRIDGE ST YUBA CITY R20A | 35131205 | UUD NO. 18-1 | 95991 | 6101050201 | No | 21.14% | BRIDGE ST BETWEEN STATE ROUTE 99 & SECOND ST | None | Project met one or more Rule 20A criteria | Resolution# 18-080 | No | 7 | 3 | 2 | 1 | 2 | Rural | No | 2018-11-20 | TBD | TBD | TBD | TBD | N/A | N/A | #VALUE! | 2023-12-31 | N/A | 0 | 0 | Project not completed or closed | Project not completed or closed | Residential | Unknown | TBD | TBD | TBD | 2962393.02 | N/A | TBD | N/A | [6 empty] | TBD | TBD | [6 empty] | Project in planning phase |  |  | N/A |  |  |  |  | Yes | 900000 | Sutter County | N/A | 0 |  | No | No | No | No | Yes | No | No | Insufficient allocation | None | N/A | N/A | No | N/A | N/A
Sutter County Total | [41 empty] | 0
Tehama County | [41 empty] | 0
CORNING | C:E PC R20A SOLANO/HOAG RD,CORNING | 30024623 | SOLANO/HOAG RD, CORNING | 96021 | 6103001000 | No | 16.08% | SOLANO/HOAG RD, CORNING | None | TBD | TBD | Yes | 5 | 3 | 3 | 0 | 1 | Unknown | No | TBD | 1998-11-16 | 1999-02-09 | 2003-04-07 | 2005 | 2007-03-24 | N/A | #VALUE! | N/A | N/A |  |  | 1.48 | 5280 | Unknown | Unknown |  |  |  | N/A | 888092.1134 | 1.7065 | 1515538.6997 | [10 empty] | 0 |  |  |  | Unknown |  |  | 888092.1134 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
CORNING | CITY PLAZA, CORNING | No Order | CORNING CITY PLAZA | 95963 | 6103001100 | Unknown | 20.78% | SOLANO ST & MARIN ST BETWEEN 3RD ST & 4TH ST | None | Project met one or more Rule 20A criteria | Resolution# 07-23-2019-07 | No | 5 | 3 | 3 | 0 | 1 | Rural | Unknown | 2019-07-23 | TBD | TBD | TBD | TBD | N/A | N/A | #VALUE! | 0 | N/A | 0 | 0 | Project not completed or closed | Project not completed or closed | Residential | Unknown | TBD | TBD | TBD | 649711.63 | N/A | TBD | N/A | [6 empty] | TBD | TBD | [6 empty] | Project in planning phase |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | Yes | No | No | Insufficient allocation | None | N/A | N/A | No | N/A | N/A
TEHAMA | 5TH STREET, TEHAMA | No Order | 5TH STREET | 96090 | 6103000900 | No | 16.83% | 5TH STREET BETWEEN C AND I STREETS | None | Project met one or more Rule 20A criteria | Resolution# 2019-6-1 | No | 5 | 3 | 3 | 0 | 1 | Rural | No | 2019-06-11 | TBD | TBD | TBD | TBD | N/A | N/A | #VALUE! | 0 | N/A | 0 | 0 | Project not completed or closed | Project not completed or closed | Residential | Unknown | TBD | TBD | TBD | 1636421.42 | N/A | TBD | N/A | [6 empty] | TBD | TBD | [6 empty] | Project in planning phase |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | Yes | No | No | Insufficient allocation | None | N/A | N/A | No | N/A | N/A
TEHAMA COUNTY | *CANC* HWY 99 LOS MOLINOS TEHAMA CNTY R2 | 30258465 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | 5 | 3 | 3 | 0 | 1 | N/A | N/A | 2003-10-01 | TBD | TBD | TBD | N/A | N/A | N/A | #VALUE! | N/A | 2012-10-04 | N/A | N/A | Cancelled project | Cancelled project | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [6 empty] | N/A | N/A |  |  | 0 |  |  |  | N/A, project cancelled |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TEHAMA COUNTY | HWY 99 EAST, TEHAMA COUNTY | No Order | HIGHWAY 99E LOS MOLINOS UUD# 6 | 96055 | 6103000900 | No | 16.83% | HIGHWAY 99E LOS MOLINOS | None | Project met one or more Rule 20A criteria | Resolution# 2018-123 | No | 5 | 3 | 3 | 0 | 1 | Suburban | No | 2018-12-18 | TBD | TBD | TBD | TBD | N/A | N/A | #VALUE! | 0 | N/A | 0 | 0 | Project not completed or closed | Project not completed or closed | Commercial | Unknown | TBD | TBD | TBD | 5000000 | N/A | TBD | N/A | [6 empty] | TBD | TBD | [6 empty] | Project in planning phase |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | Yes | No | No | Insufficient allocation | None | N/A | N/A | No | N/A | N/A
Tehama County Total | [41 empty] | 0
Tulare County | [41 empty] | 0
DINUBA | TRANSIT CENTER, DINUBA | 30959525 | TRANSIT CENTER | 93618 | 6107000501 | Yes | 22.96% | L ST & M ST, FRESNO ST & MARIPOSA ST | None | Project met one or more Rule 20A criteria | Resolution# 2011-48 | No | 1 | 1 | 1 | 0 | 0 | Suburban | Yes | 2011-11-22 | 2014-03-14 | TBD | TBD | TBD | N/A | N/A | 843 | 2019-02-22 | N/A | TBD | TBD | Project not completed or closed | Project not completed or closed | Residential | Yes | TBD | TBD | TBD | 73825.1 | N/A | TBD | N/A | [6 empty] | TBD | TBD |  |  | 0 |  |  |  | Project in progress |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Yes | Unknown | Unknown | Insufficient allocation. City personnel changes have made communication difficult. | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
Tulare County Total | [41 empty] | 0
Tuolumne County | [41 empty] | 0
TUOLUMNE COUNTY | COLUMBIA | 30563720 | COLUMBIA | 95310 | 6109002100 | No | 13.81% | COLUMBIA | Tier 2 | TBD | TBD | Yes | 2 | 1 | 1 | 0 | 1 | Rural | No | 2005-06-14 | 2008-06-02 | 2012-07-10 | 2012-11-29 | 2013 | 2014-02-28 | N/A | 1084 | N/A | N/A | 8 | 10 | 0.48 | 2112 | Commercial | No |  |  |  | N/A | 2053328 | 1.1048 | 2268524.8091 | [6 empty] | 0 | 0% |  |  | 0 |  |  |  | Unexpected field conditions |  |  | 2053328 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | No | No | No | Cultural resource review and monitoring | None | N/A | N/A | None | N/A | N/A
TUOLUMNE COUNTY | TUOLUMNE TOWNSITE, TUOLUMNE COUNTY | No Order | TUOLUMNE CITY UUD | 95379 | 6109003200 | No | 12.58% | WILLOW AVE & PASSED ROZIER ST BETWEEN CHERRY LOOP & PASSED CARTER ST | None | Project met one or more Rule 20A criteria | Resolution# 58-19 | No | 2 | 1 | 1 | 0 | 1 | Rural | No | 2019-08-06 | TBD | TBD | TBD | TBD | N/A | N/A | #VALUE! | 0 | N/A | 0 | 0 | Project not completed or closed | Project not completed or closed | Residential | Unknown | TBD | TBD | TBD | 5667279.63 | N/A | TBD | N/A | [6 empty] | TBD | TBD | [6 empty] | Project in planning phase |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | Yes | No | No | Insufficient allocation | None | N/A | N/A | No | N/A | N/A
Tuolumne County Total | [41 empty] | 0
Yolo County | [41 empty] | 0
DAVIS | 3RD ST PH 1 | 30917227 | 3RD ST PH 1 | 95616 | 6113010701 | No | 4.562% | 3RD ST, A ST & B ST | None | Project met one or more Rule 20A criteria | Resolution# 2382 | Yes | 9 | 1 | 1 | 0 | 7 | Unknown | No | 2011-11-15 | 2012-07-19 | 2014-06-23 | 2014-09-23 | 2016 | 2016-04-09 | N/A | 247 | N/A | N/A |  |  | 0.69 | 2798.4 | Unknown | Unknown |  |  |  | N/A | 1717193.27 | 1.0668 | 1831956.6473 | [10 empty] | 0 |  |  |  | Unknown |  |  | 1717193.27 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
WEST SACRAMENTO | 3RD AND C STREETS | 30178098 | 3RD ST AND C ST | 95605 | 6113010101 | Yes | 18.24% | 3RD ST AND C ST | None | TBD | TBD | Yes | 9 | 1 | 1 | 0 | 7 | Unknown | Yes | 2000-12-06 | 2001-12-20 | 2003-10-13 | 2004-12-03 | 2007 | 2007-07-31 | N/A | 379 | N/A | N/A |  |  | 0.19 | 1056 | Unknown | Unknown |  |  |  | N/A | 830239.12 | 1.4306 | 1187721.1785 | [10 empty] | 0 |  |  |  | Unknown |  |  | 830239.12 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
WEST SACRAMENTO | 5TH STREET | 30614607 | 5TH ST | 95605 | 6113010101 | Yes | 18.24% | 5TH ST | None | TBD | TBD | Yes | 9 | 1 | 1 | 0 | 7 | Unknown | Yes | 2007-10-10 | 2008-03-05 | 2009-10-05 | 2009-12-23 | 2012 | 2012-09-13 | N/A | 147 | N/A | N/A |  |  | 0.6 | 2164.8 | Unknown | Unknown |  |  |  | N/A | 1835344.56 | 1.121 | 2057497.0388 | [10 empty] | 0 |  |  |  | Unknown |  |  | 1835344.56 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
WEST SACRAMENTO | C:EP JEFFERSON RULE 20A, WEST SAC | 30102918 | JEFFERSON, WEST SACRAMENTO | 95691 | 6113010201 | No | 13.4% | JEFFERSON, WEST SACRAMENTO | None | TBD | TBD | Yes | 9 | 1 | 1 | 0 | 7 | Unknown | No | TBD | 1999-11-10 | 2000-03-23 | 2002-10-29 | 2006 | 2007-03-24 | N/A | #VALUE! | N/A | N/A |  |  | 0.94 | 4012.8 | Unknown | Unknown |  |  |  | N/A | 909130.76 | 1.591 | 1446396.1853 | [10 empty] | 0 |  |  |  | Unknown |  |  | 909130.76 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
WINTERS | NEWT'S EXPRESSWAY WINTERS R20A | 35051251 | NEWT'S EXPRESSWAY | 95694 | 6113011300 | No | 10.42% | ALLEY BETWEEN FIRST & RAILROAD AND BETWEEN ABBEY & MAIN | None | Project met one or more Rule 20A criteria | Resolution# 2018-34 | No | 9 | 1 | 1 | 0 | 7 | Rural | No | 2018-06-19 | 2019-05-01 | TBD | TBD | TBD | N/A | N/A | 316 | 2019-12-31 | N/A | 0 | 0 | Project not completed or closed | Project not completed or closed | Residential | Yes | TBD | TBD | TBD | 996475.65 | N/A | TBD | N/A | [6 empty] | TBD | TBD | [6 empty] | Project in planning phase |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | No | No | No | No | Yes | No | No | Insufficient allocation | None | N/A | N/A | No | N/A | N/A
WOODLAND | *CANC* DEAD CAT ALLEY | 30864665 | N/A | N/A | 6113010800 | No | 15.05% | N/A | None | N/A | N/A | No | 9 | 1 | 1 | 0 | 7 | N/A | No | 2011-02-01 | TBD | TBD | TBD | N/A | 2014-02-28 | N/A | #VALUE! | N/A | 2013-07-18 | N/A | N/A | Cancelled project | Cancelled project | N/A | N/A | N/A | N/A | N/A | N/A | 6681.85 | 1.0831 | 7236.9934 | [6 empty] | N/A | N/A |  |  | 0 |  |  |  | N/A, project cancelled |  |  | 6681.85 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WOODLAND | EAST ST | 30616114 | EAST ST | 95776 | 6113010800 | No | 15.05% | EAST ST | None | TBD | Resolution# 4734 | Yes | 9 | 1 | 1 | 0 | 7 | Unknown | No | 2006-05-16 | 2008-06-19 | 2009-12-07 | 2010-05-07 | 2015 | 2015-07-14 | N/A | 765 | N/A | N/A |  |  | 0.49 | 1742.4 | Unknown | Unknown |  |  |  | N/A | 1292764.29 | 1.0677 | 1380314.3778 | [10 empty] | 0 |  |  |  | Unknown |  |  | 1292764.29 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
WOODLAND | EAST STREET | 30418943 | EAST ST | 95776 | 6113011206 | No | 7.436% | EAST ST | None | TBD | TBD | Yes | 9 | 1 | 1 | 0 | 7 | Unknown | No | 2004-05-18 | 2005-01-04 | 2006-10-25 | 2007-01-30 | 2007 | 2008-02-15 | N/A | 231 | N/A | N/A |  |  | 0.23 | 1214.4 | Unknown | Unknown |  |  |  | N/A | 221351.79 | 1.4306 | 316660.83 | [10 empty] | 0 |  |  |  | Unknown |  |  | 221351.79 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
YOLO COUNTY | COUNTY ROADS 98 AND 27 | 30762587 | COUNTY RD 98 & COUNTY RD 27 | 95695 | 6113010505 | No | 4.14% | COUNTY RD 98 & COUNTY RD 27 | None | TBD | Resolution# 1395 | Yes | 9 | 1 | 1 | 0 | 7 | Unknown | No | 2009-12-15 | 2012-04-27 | 2012-09-21 | 2013-06-17 | 2015 | 2015-07-14 | N/A | 864 | N/A | N/A |  |  | 0.91 | 3379.2 | Unknown | Unknown |  |  |  | N/A | 1891504.37 | 1.0677 | 2019603.0304 | [10 empty] | 0 |  |  |  | Unknown |  |  | 1891504.37 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
Yolo County Total | [41 empty] | 0
Yuba County | [41 empty] | 0
YUBA COUNTY | *CANC* EP YUBA COUNTY RULE 20A MCGO*CANC | 30237025 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | 2 | 0 | 0 | 0 | 1 | N/A | N/A | 2002-04-02 | TBD | TBD | TBD | N/A | N/A | N/A | #VALUE! | N/A | 2007-02-26 | N/A | N/A | Cancelled project | Cancelled project | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [6 empty] | N/A | N/A |  |  | 0 |  |  |  | N/A, project cancelled |  |  | N/A |  |  |  |  | No | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
YUBA COUNTY | OLIVEHURST AVE, YUBA CNTY | 30959427 | OLIVEHURST AVE | 95961 | 6115040600 | No | 18.04% | OLIVEHURST AVE, 8TH AVE & MCGOWAN PKWY | None | Project met one or more Rule 20A criteria | Resolution# 2012-97 | Yes | 2 | 0 | 0 | 0 | 1 | Unknown | No | 2012-10-23 | 2014-09-23 | 2015-01-13 | 2015-02-03 | 2017 | 2017-04-14 | N/A | 700 | N/A | N/A |  |  | 2.67 | 12355.2 | Unknown | Unknown |  |  |  | N/A | 4616250.25 | 1.048 | 4838033.1367 | [10 empty] | 0 |  |  |  | Unknown |  |  | 4616250.25 |  |  |  |  | No | N/A | N/A | N/A | N/A |  | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown
Yuba County Total
PG&E Total | - | [11 empty] | 0 | 0 | 0 | 0 | 0
Note on E5: Note: As additional documentation becomes available, data will be updated
Note on F5: Note: As additional documentation becomes available, data will be updated
Note on G5: Note: If project location is in multiple census tracts, used predominant census tract. In some instances, data may not be available in PG&E's mapping database.
Note on H5: Note: Census Tract on column G used to determine if project is in a disadvantaged community. In some instances, data may not be available in PG&E's mapping database.
Note on I5: Note: Census Tract on column G used to determine counts for population and CARE customers in tract. To calculate % of CARE customers affected by project, divided # of CARE customers by total # of people/population in census tract. In some instances, data may not be available in PG&E's mapping database.
Note on J5: Note: As additional documentation becomes available, data will be updated
Note on K5: Note: If project location is in multiple High Fire Threat Districts (HFTD), used predominant HFTD. In some instances, data may not be available in PG&E's mapping database.
Note on L5: Note: As additional documentation becomes available, data will be updated
Note on M5: Note: As additional documentation becomes available, data will be updated
Note on O5: Note: PG&E interprets column O to equal column Q plus column R plus cancelled or inactive projects
Note on P5: Note: PG&E interprets column P to equal column O less column S less cancelled or inactive projects
Note on Q5: Note: PG&E interprets "projects in planning phase" to include all activities prior to construction
Note on R5: Note: PG&E interprets "projects in progress (construction)" to mean projects that are in construction phase or in closing phase without being closed
Note on S5: Note: PG&E interprets "completed" to mean projects that have completely closed
Note on U5: Note: Per CPUC note, "a project is in a DAC if it is “in or partially in a Disadvantaged Community”." In some instances, data may not be available in PG&E's Mapping database.
Note on V5: Note: As additional documentation becomes available, data will be updated
Note on W5: Note: As additional documentation becomes available, data will be updated
Note on X5: Note: As additional documentation becomes available, data will be updated
Note on Y5: Note: Date in which service was restored. PG&E does not track last pole removed. As additional documentation becomes available, data will be updated.
Note on Z5: Note: Based on Annual Report of Rule 20A Conversions. PG&E does not track last pole removed.
Note on AH5: Note: Changed from Miles of Overhead Lines Converted to underground
Note on AK5: Note: PG&E will work to find requested data
Note on AP5: Note: Changed column header from Rule 20A Ratepayer Costs
Note on AQ5: Note: Added column for Jonathan Frost's request dated 11/28/2018; factor to be used to calculate work credits redeemed in 2018 real dollars; based on data in "Project Completed" column
Note on AR5: Note: Added column for Jonathan Frost's request dated 11/28/2018; used factor to calculate work credits redeemed in 2018 real dollars
Note on AS5: Note: Added column per Jonathan Frost's email dated 11/28/2018; used trenched footage to calculate cost per foot
Note on AT5: Note: Added column per Jonathan Frost's email dated 11/28/2018; used trenched footage to calculate cost per foot
Note on BU5: Note: Information not tracked in a central database. Information may be found in multiple locations but will require intensive manual labor.
Note on BV5: Note: Information not tracked in a central database. Information may be found in multiple locations but will require intensive manual labor.
Note on BW5: Note: Information not tracked in a central database. Information may be found in multiple locations but will require intensive manual labor.
Note on BX5: Note: Information not tracked in a central database. Information may be found in multiple locations but will require intensive manual labor.
Note on BY5: Note: Information not tracked in a central database. Information may be found in multiple locations but will require intensive manual labor.
Note on BZ5: Note: Information not tracked in a central database. Information may be found in multiple locations but will require intensive manual labor.
Note on CA5: Note: Information not tracked in a central database. Information may be found in multiple locations but will require intensive manual labor.
Note on CB5: Note: Information not tracked in a central database. Information may be found in multiple locations but will require intensive manual labor.
Note on CC5: Note: Costs associated with contamination or cultural discoveries are covered by cities/counties. Information not tracked in a central database.
Note on CD5: Note: Costs associated with contamination or cultural discoveries are covered by cities/counties. Information not tracked in a central database.
Note on CE5: Note: Costs associated with contamination or cultural discoveries are covered by cities/counties. Information not tracked in a central database.
Note on CF5: Note: Costs associated with contamination or cultural discoveries are covered by cities/counties. Information not tracked in a central database.
Note on CG5: Note: Costs associated with contamination or cultural discoveries are covered by cities/counties. Information not tracked in a central database.
Note on CH5: Note: Costs associated with contamination or cultural discoveries are covered by cities/counties. Information not tracked in a central database.
Note on AA18: Note: When project costs are finalized, costs will be deducted from work credit balance.
Note on AA34: Note: When project costs are finalized, costs will be deducted from work credit balance.
Note on D40: Note: Design not yet started, no order created
Note on D41: Note: Design not yet started, no order created
Note on AA43: Note: When project costs are finalized, costs will be deducted from work credit balance.
Note on BO57: Note: Credits not purchased but gifted
Note on BO59: Note: Credits not purchased but gifted
Note on BO60: Note: Credits not purchased but gifted
Note on BO65: Note: Credits not purchased but gifted
Note on D86: Note: Design not yet started, no order created
Note on D89: Note: Design not yet started, no order created
Note on D93: Note: Design not yet started, no order created
Note on AA104: Note: When project costs are finalized, costs will be deducted from work credit balance.
Note on BO122: Note: Credits not purchased but gifted
Note on AA127: Note: When project costs are finalized, costs will be deducted from work credit balance.
Note on BJ127: Note: To be deducted from work credit balance when project costs are finalized.
Note on AA148: Note: When project costs are finalized, costs will be deducted from work credit balance.
Note on BJ148: Note: To be deducted from work credit balance when project costs are finalized.
Note on BO158: Note: Credits not purchased but gifted
Note on AA161: Note: When project costs are finalized, costs will be deducted from work credit balance.
Note on BJ161: Note: To be deducted from work credit balance when project costs are finalized.
Note on BO164: Note: Credits not purchased but gifted
Note on BO165: Note: Credits not purchased but gifted
Note on BO177: Note: Credits not purchased but gifted
Note on BO180: Note: Credits not purchased but gifted
Note on BO205: Note: Credits not purchased but gifted
Note on D279: Note: Design not yet started, no order created
Note on AA284: Note: When project costs are finalized, costs will be deducted from work credit balance.
Note on BJ284: Note: To be deducted from work credit balance when project costs are finalized.
Note on AA285: Note: When project costs are finalized, costs will be deducted from work credit balance.
Note on BJ285: Note: To be deducted from work credit balance when project costs are finalized.
Note on D287: Note: Design not yet started, no order created
Note on D299: Note: Design not yet started, no order created
Note on D311: Note: Design not yet started, no order created
Note on AH340: Note: Circuit miles of primary underground for sub-orders were found, which may increase total circuit miles for project
Note on AH352: Note: Circuit miles of primary underground for sub-orders were found, which may increase total circuit miles for project
Note on AH383: Note: Circuit miles of primary underground for sub-orders were found, which may increase total circuit miles for project
Note on AH417: Note: Circuit miles of primary underground for sub-orders were found, which may increase total circuit miles for project
Note on AH423: Note: Circuit miles of primary underground for sub-orders were found, which may increase total circuit miles for project
Note on D454: Note: Design not yet started, no order created
Note on D455: Note: Design not yet started, no order created
Note on AA467: Note: When project costs are finalized, costs will be deducted from work credit balance.
Note on BJ467: Note: To be deducted from work credit balance when project costs are finalized.
Note on AA472: Note: When project costs are finalized, costs will be deducted from work credit balance.
Note on BJ472: Note: To be deducted from work credit balance when project costs are finalized.
Note on AA480: Note: When project costs are finalized, costs will be deducted from work credit balance.
Note on BJ480: Note: To be deducted from work credit balance when project costs are finalized.
Note on AH496: Note: Circuit miles of primary underground for sub-orders were found, which may increase total circuit miles for project
Note on D497: Note: Design not yet started, no order created
Note on AA545: Note: When project costs are finalized, costs will be deducted from work credit balance.
Note on BJ545: Note: To be deducted from work credit balance when project costs are finalized.
Note on D546: Note: Design not yet started, no order created
Note on BO549: Note: Credits not purchased but gifted
Note on D587: Note: Design not yet started, no order created
Note on AA604: Note: When project costs are finalized, costs will be deducted from work credit balance.
Note on BJ604: Note: To be deducted from work credit balance when project costs are finalized.
Note on AH624: Note: Circuit miles of primary underground for sub-orders were found, which may increase total circuit miles for project

## Historical Project Level Data
Pacific Gas and Electric Company data for R.17-05-010 submitted on 4/17/2020; Note: Data provide for 2005-2019 only
(I.h) Historical Project Data Since Program Inception
Project Name | Community | Unique Project Identifier | County | Dollar Amount (Nominal) provided via Rule 20A | Year Completed | Date Paid
| Name | Name | Name | Nominal $ | Year | Date
E14TH I R20A | ALAMEDA COUNTY | 30082775 | ALAMEDA | 2918232.14 | 2006 | 2007-03-24
E 14TH PH II | ALAMEDA COUNTY | 30308833 | ALAMEDA | 8618365.16 | 2016 | 2016-10-19
LEWELLING BLVD | ALAMEDA COUNTY | 30387770 | ALAMEDA | 3361081 | 2013 | 2014-02-28
*CANC* E14TH ST PH 3 | ALAMEDA COUNTY | 30633334 | ALAMEDA | 34151.88 | N/A | 2015-01-15
HESPERIAN BLVD, ALAMEDA COUNTY | ALAMEDA COUNTY | 74001557 | ALAMEDA | N/A | TBD | N/A
BUCHANAN ST & MARIN AVE PH 1, ALBANY | ALBANY | 74001549 | ALAMEDA | 3100967.09 | 2019 | 2019-11-21
MILLER/STEVENSON | BERKELEY | 30454814 | ALAMEDA | 5118222.1 | 2012 | 2012-09-13
VISTAMONT AVE, BERKELEY | BERKELEY | 30817976 | ALAMEDA | N/A | TBD | N/A
GRIZZLY PEAK BLVD, BERKELEY | BERKELEY | 74001486 | ALAMEDA | N/A | TBD | N/A
DOUGHERTY | DUBLIN | 30408801 | ALAMEDA | 1215529.2 | 2008 | 2008-08-18
DUBLIN BLVD, DUBLIN | DUBLIN | 31052180 | ALAMEDA | 1230651.02 | TBD | TBD
BAY ST | FREMONT | 30155006 | ALAMEDA | 1251374 | 2011 | 2012-02-07
FREMONT BLVD-IRVINGTON | FREMONT | 30155281 | ALAMEDA | 1216245.94 | 2007 | 2007-07-31
WASHINGTON & ROBERTS | FREMONT | 30242352 | ALAMEDA | 3501281.81 | 2015 | 2016-01-13
WASH/680 | FREMONT | 30242356 | ALAMEDA | 1087762.28 | 2008 | 2008-08-18
CENTRAL AVE | FREMONT | 30276150 | ALAMEDA | 1916781.12 | 2009 | 2010-03-16
FREMONT BLVD, FREMONT | FREMONT | No Order | ALAMEDA | N/A | TBD | N/A
PERALTA BLVD, FREMONT | FREMONT | No Order | ALAMEDA | N/A | TBD | N/A
MISSION/CALHOUN | HAYWARD | 30146944 | ALAMEDA | 3371422.79 | 2012 | 2012-09-13
MISSION OVERHILL DIST 27 | HAYWARD | 30677628 | ALAMEDA | 4975614.31 | 2014 | 2015-01-15
*CANC* EP WATKINS ST HAYWARD R20A | HAYWARD | 30677630 | ALAMEDA | N/A | N/A | N/A
MISSION BLVD DIST 25 | HAYWARD | 30677789 | ALAMEDA | 7211391.06 | 2014 | 2015-01-15
MISSION BLVD DIST 29 HAYWARD R20A | HAYWARD | 30882110 | ALAMEDA | N/A | TBD | N/A
MISSION BLVD DIST 30 HAYWARD R20A | HAYWARD | 74011982 | ALAMEDA | N/A | TBD | N/A
CONCANNON | LIVERMORE | 30384525 | ALAMEDA | 637872.59 | 2007 | 2007-07-31
*CANC* NORTH L ST | LIVERMORE | 30647110 | ALAMEDA | 103735.05 | N/A | 2015-01-15
ISABEL AVE, LIVERMORE | LIVERMORE | 31064287 | ALAMEDA | 1781725 | 2018 | 2018-10-23
NEWARK BLVD, NEWARK | NEWARK | No Order | ALAMEDA | N/A | TBD | N/A
MACARTHUR PH 1 | OAKLAND | 30215963 | ALAMEDA | 4295231.71 | 2012 | 2012-09-13
MACARTHUR PH 2 | OAKLAND | 30240908 | ALAMEDA | 4043229.39 | 2012 | 2012-09-13
MACARTHUR PH 3 | OAKLAND | 30240911 | ALAMEDA | 4966230.4 | 2012 | 2012-09-13
PIEDMONT PINES PH 1 | OAKLAND | 30618097 | ALAMEDA | 13740062.12 | 2017 | 2017-07-17
PIEDMONT PINES PH 2, OAKLAND | OAKLAND | No Order | ALAMEDA | N/A | TBD | N/A
PIEDMONT PINES PH 3, OAKLAND | OAKLAND | No Order | ALAMEDA | N/A | TBD | N/A
FIRST ST | PLEASANTON | 30060281 | ALAMEDA | 2634710.77 | 2009 | 2009-07-29
STANLEY BLVD, PLEASANTON | PLEASANTON | 30937193 | ALAMEDA | 1681105.26 | 2018 | 2018-04-30
BAYFAIR | SAN LEANDRO | 30055034 | ALAMEDA | 3179509.83 | 2014 | 2015-01-15
W. ESTUDILLO | SAN LEANDRO | 30311335 | ALAMEDA | 989664.97 | 2009 | 2009-07-29
E 14TH ST N/O BAYFAIR, SAN LEANDRO | SAN LEANDRO | 30616108 | ALAMEDA | N/A | TBD | N/A
EDEN RD SAN LEANDRO R20A | SAN LEANDRO | 30882109 | ALAMEDA | N/A | N/A | N/A
C:EP SMITH STREET RULE 20A CITY OF *CANC | UNION CITY | 30166271 | ALAMEDA | 12542.21 | N/A | 2007-03-24
MISSION & DECOTO RD, UNION CITY | UNION CITY | 30616111 | ALAMEDA | 2549343.6 | 2017 | 2017-04-14
FIDDLETOWN | AMADOR COUNTY | 30326713 | AMADOR | 1191231.55 | 2009 | 2009-07-29
COHASSET RD AND EAST AVE, CHICO | BUTTE COUNTY | 30167443 | BUTTE | 801892.36 | 2007 | 2007-07-31
EAST AVE COHASSET TO CEONOTHUS | BUTTE COUNTY, CHICO | 30411562 | BUTTE | 3457228.08 | 2009 | 2010-03-16
GEPEAST AVE RULE 20; CEONOTHUS TO CACT | CHICO | 30099494 | BUTTE | 547886.7798 | 2005 | 2007-03-24
BRUCE RD DIST 16, CHICO | CHICO | 74009861 | BUTTE | N/A | TBD | N/A
NORTH ESPLANADE DIST 17, CHICO | CHICO | 74010863 | BUTTE | N/A | TBD | N/A
WARNER ST DIST 18, CHICO | CHICO | 74010864 | BUTTE | N/A | TBD | N/A
E PC R-20A MONTGOMERY STREET,OROVILLE | OROVILLE | 30024946 | BUTTE | 646674.8411 | 2005 | 2007-03-24
C:E PC R-20A TABLE MT,OROVILLE SUB ORDER | OROVILLE | 30199109 | BUTTE | 396069 | 2006 | 2007-03-24
C:E PC R-20A TBL MT.ST LTS,SUBORDER*CANC | OROVILLE | 30308489 | BUTTE | N/A | N/A | N/A
MYERS ST, OROVILLE | OROVILLE, BUTTE COUNTY | 30938105 | BUTTE | N/A | TBD | N/A
CLARK RD & SKYWAY | PARADISE | 30269575 | BUTTE | 753334.25 | 2007 | 2007-07-31
ALMOND ST PARADISE R20A | PARADISE | 74010581 | BUTTE | N/A | TBD | N/A
SAN ANDREAS RULE PH #1 RULE 20A | CALAVERAS COUNTY | 30084561 | CALAVERAS | 1476404.69 | 2005 | 2007-03-24
MTN. RANCH ROAD PH 1, CALAVERAS COUNTY | CALAVERAS COUNTY | 30695567 | CALAVERAS | N/A | TBD | N/A
MTN. RANCH ROAD PH 2, CALAVERAS COUNTY | CALAVERAS COUNTY | 30695568 | CALAVERAS | N/A | TBD | N/A
STATE HWY 49 PH3 SAN ANDREAS R20A | CALAVERAS COUNTY | 30695972 | CALAVERAS | N/A | N/A | N/A
ST CHARLES (HWY 49) SAN ANDREAS | CALAVERAS COUNTY | 30780266 | CALAVERAS | N/A | TBD | N/A
BRIDGE ST, COLUSA | COLUSA, COLUSA COUNTY | 74008524 | COLUSA | N/A | TBD | N/A
GEP-RULE 20A SOMERSVILLE RD-ANTIOCH | ANTIOCH | 30200879 | CONTRA COSTA | 1113831.62 | 2005 | 2007-03-24
*CANC* R1 EP JAMES DONLON BLVD-ANT 20A | ANTIOCH | 30482073 | CONTRA COSTA | 72304 | N/A | 2011-03-16
HILLCREST AVE | ANTIOCH | 30629323 | CONTRA COSTA | 2303558 | 2013 | 2014-02-28
SOMERSVILLE ROAD | ANTIOCH | 30699814 | CONTRA COSTA | 1009094.21 | 2014 | 2015-01-15
FAIRVIEW AVE, BRENTWOOD | BRENTWOOD | 30959527 | CONTRA COSTA | 1476839.79 | 2019 | 2019-07-31
C:ES RULE 20, CENTER ST, CLAYTON | CLAYTON | 30123866 | CONTRA COSTA | 143887 | 2004 | 2006
EAST STREET R20A | CONCORD | 30134049 | CONTRA COSTA | 1850650 | 2010 | 2010-08-26
RULE 20A WILLOW PASS RD & LANDANA, CON | CONCORD | 30240959 | CONTRA COSTA | 563911.57 | 2005 | 2007-03-24
THE ALAMEDA | CONCORD | 30411405 | CONTRA COSTA | 1467091.4 | 2015 | 2015-10-06
MARKET ST, CONCORD | CONCORD | No Order | CONTRA COSTA | N/A | TBD | N/A
WILLOW PASS RD, CONCORD | CONCORD | No Order | CONTRA COSTA | N/A | N/A | N/A
PARKER R20A-PARKER AVENUE-RODEO | CONTRA COSTA COUNTY | 30160625 | CONTRA COSTA | 2300334 | 2010 | 2010-08-26
BAILEY RD, CONTRA COSTA COUNTY | CONTRA COSTA COUNTY | 74001485 | CONTRA COSTA | N/A | TBD | N/A
CAMINO TASSAJARA 20A, DANVILLE | DANVILLE | 30344715 | CONTRA COSTA | 2371997 | 2010 | 2010-08-26
CAMINO TASSAJARA PH2, DANVILLE | DANVILLE | No Order | CONTRA COSTA | N/A | TBD | N/A
FAIRMOUNT R 20A | EL CERRITO | 30154072 | CONTRA COSTA | 1817783.13 | 2006 | 2007-03-24
CIVIC CENTER, EL CERRITO | EL CERRITO | No Order | CONTRA COSTA | N/A | TBD | N/A
LAFAYETTE CIR & FIESTA LN | LAFAYETTE | 30636534 | CONTRA COSTA | 1049391 | 2011 | 2012-02-07
MARINA VISTA | MARTINEZ | 30679737 | CONTRA COSTA | 1828333.89 | 2015 | 2015-10-06
MORAGA RD, MORAGA | MORAGA | 31160902 | CONTRA COSTA | 1434611.76 | 2017 | 2017-10-13
*CANC* MINER RD | ORINDA | 30519332 | CONTRA COSTA | 122000 | N/A | 2015-10-06
PINOLE VALLEY RD, PINOLE | PINOLE | 31269303 | CONTRA COSTA | N/A | TBD | N/A
WEST LELAND RD, PITTSBURG | PITTSBURG | 30754659 | CONTRA COSTA | N/A | TBD | N/A
BUSKIRK AVE | PLEASANT HILL | 30769201 | CONTRA COSTA | 2115155.64 | 2014 | 2015-01-15
MACDONALD AVE, RICHMOND | RICHMOND | 30631393 | CONTRA COSTA | 4335386.23 | 2017 | 2017-04-14
SAN PABLO DAM R20A | SAN PABLO | 30243988 | CONTRA COSTA | 915637.91 | 2006 | 2007-03-24
EL PORTAL DR, SAN PABLO | SAN PABLO | 30837018 | CONTRA COSTA | 1251314.97 | 2018 | 2018-07-17
SAN RAMON VALLEY BLVD | SAN RAMON | 30170978 | CONTRA COSTA | 1034452.89 | 2007 | 2007-07-31
RULE 20A WALNUT CREEK, N MAIN | WALNUT CREEK | 30069379 | CONTRA COSTA | 4018496.78 | 2005 | 2007-03-24
BONANZA ST WALNUT CREEK R20A | WALNUT CREEK | 74014381 | CONTRA COSTA | N/A | TBD | N/A
C:EPC GREEN VALLEY ROAD,EL DORADO WKR | EL DORADO COUNTY | 30025981 | EL DORADO | 1147767.13 | 2006 | 2007-03-24
DIAMOND SPRINGS PH1, EL DORADO COUNTY | EL DORADO COUNTY | 31066255 | EL DORADO | N/A | TBD | N/A
MISSOURI FLAT RD EL DORADO CNTY R20A | EL DORADO COUNTY | 35047931 | EL DORADO | N/A | TBD | N/A
GREEN VALLEY RD, EL DORADO COUNTY | EL DORADO COUNTY | 74010582 | EL DORADO | N/A | TBD | N/A
DIAMOND SPRINGS 1C, EL DORADO CNTY R20A | EL DORADO COUNTY | 74013925 | EL DORADO | N/A | TBD | N/A
MAIN ST/PLACERVILLE DR | PLACERVILLE | 30547671 | EL DORADO | 1993373.79 | 2014 | 2015-01-15
FIFTH STREET | CLOVIS | 30403106 | FRESNO | 1123323.65 | 2009 | 2010-03-16
VILLA AVE. (BULLARD2HERNDON) | CLOVIS | 30421018 | FRESNO | 2378715.45 | 2009 | 2010-03-16
BULLARD AVE, CLOVIS | CLOVIS | No Order | FRESNO | N/A | TBD | N/A
ELM AVE, COALINGA | COALINGA | 74013924 | FRESNO | N/A | TBD | N/A
13TH ST | FIREBAUGH | 30675529 | FRESNO | 2423475.29 | 2015 | 2015-07-14
EP MERCED & 10TH STS. RULE 20A, FOWLER | FOWLER | 30304212 | FRESNO | 455361 | 2006 | 2007-03-24
FOWLER LIBRARY, 7TH ST | FOWLER | 30676929 | FRESNO | 879266.34 | 2014 | 2015-01-15
EP KNGS CNYN PH 3 20A (MAPLE-WILLW) | FRESNO | 30126926 | FRESNO | 3403646 | 2010 | 2010-08-26
EP SHAW & MARKS PH III RULE 20A | FRESNO | 30220640 | FRESNO | 989810.2419 | 2005 | 2007-03-24
PEACH AVE - LANE | FRESNO | 30225680 | FRESNO | 45352.65 | N/A | 2007-07-31
PEACH AVE 20A - LYELL | FRESNO | 30252291 | FRESNO | 857.61 | N/A | 2007-07-31
EP ELM AVE. (JENSEN - NORTH) RULE 20A | FRESNO | 30303447 | FRESNO | 1757772.85 | 2006 | 2007-03-24
EP HWY 180 R20A-TEMPERANCE-K.CYN TO TULA | FRESNO | 30313838 | FRESNO | 663412.21 | 2006 | 2007-03-24
EP GRANITE PARK RULE 20A (BARTON AVE.) | FRESNO | 30321943 | FRESNO | 233285.445 | 2005 | 2007-03-24
SHAW & CEDAR AVENUES | FRESNO | 30354147 | FRESNO | 924176.55 | 2007 | 2007-07-31
FRIANT ROAD SHOO FLY (RULE 20A) | FRESNO | 30472856 | FRESNO | 492448 | 2010 | 2010-08-26
WILLOW R20A(TEAGUE TO 660' N/O SHEPH | FRESNO | 30526916 | FRESNO | 1140852 | 2010 | 2010-08-26
BELMONT AVE [FWY 41 TO CHESTNUT], FRESNO | FRESNO | 30676931 | FRESNO | 6542609.88 | 2018 | 2019-02-19
VENTURA AVE, FRESNO | FRESNO | 30676932 | FRESNO | N/A | TBD | N/A
WILLOW AVE S/O NEES | FRESNO | 30676933 | FRESNO | 1255533 | 2016 | 2016-04-09
PEACH AVE [KINGS CANYON TO BELMONT] | FRESNO | 30676934 | FRESNO | 5685407.53 | 2016 | 2016-07-20
*CANC* ORANGE AVE | FRESNO | 30676935 | FRESNO | 4036.46 | N/A | 2014-02-28
WILLOW AVE, PH 2 | FRESNO | 30679601 | FRESNO | 1558816 | 2013 | 2014-02-28
E. NEES & N. MAPLE AVE | FRESNO | 31106363 | FRESNO | 785014.09 | 2016 | 2016-07-20
CHURCH AVE, FRESNO | FRESNO | 35067381 | FRESNO | N/A | TBD | N/A
BLACKSTONE AVE & ABBY ST, FRESNO | FRESNO | 74009342 | FRESNO | N/A | TBD | N/A
EP SQUAW VALLEY RULE 20A | FRESNO COUNTY | 30236509 | FRESNO | 439700.2653 | 2005 | 2007-03-24
GEP ACADEMY AVE., HWY 180 TO MCKINLEY | FRESNO COUNTY | 30258442 | FRESNO | 1537727.52 | 2006 | 2007-03-24
EP HWY 180 R20A-BELMONT-FOWLER TO ARMSTR | FRESNO COUNTY | 30313837 | FRESNO | 414821.35 | 2006 | 2018-10-23
ACADEMY, R20A, HWY 180 TO CALIF | FRESNO COUNTY | 30444991 | FRESNO | 815808 | 2010 | 2010-08-26
FRIANT RD BTWN BUGG & NO. FORK | FRESNO COUNTY | 30467134 | FRESNO | 609176 | 2010 | 2011-03-16
FRIANT ROAD RULE 20A | FRESNO COUNTY | 30513231 | FRESNO | 1118261 | 2010 | 2010-08-26
ACADEMY AVE 20A JEFFERSON AVE, SANGER | FRESNO COUNTY | 30566254 | FRESNO | 461520 | 2010 | 2010-08-26
*CANC* WILLIAMS ST, TRANQUILITY | FRESNO COUNTY | 30675531 | FRESNO | 1693.33 | N/A | 2014-02-28
ASHLAN AVE, FRESNO COUNTY | FRESNO COUNTY | 31150408 | FRESNO | 2260300.36 | 2018 | 2018-07-17
ACADEMY, SANGER | FRESNO COUNTY, SANGER | 30444989 | FRESNO | 1125908 | 2013 | 2014-02-28
LASSEN AVE PH 3, HURON | HURON | No Order | FRESNO | N/A | TBD | N/A
WHITESBRIDGE | KERMAN | 30450302 | FRESNO | 1097272 | 2011 | 2012-02-07
*CANC* SIERRA AVE KINGSBURG R20A | KINGSBURG | 30708926 | FRESNO | N/A | N/A | N/A
10TH STREET [ROOSEVELT SCHOOL], KINGSBURG | KINGSBURG | 30768527 | FRESNO | N/A | TBD | N/A
ANCHOR AVE, ORANGE COVE | ORANGE COVE | 31221681 | FRESNO | N/A | TBD | N/A
MENDOCINO AVE, PARLIER | PARLIER | 30676928 | FRESNO | 1636581.27 | 2018 | 2018-04-30
*CANC* PARLIER AVE, PARLIER R20A | PARLIER | 30767369 | FRESNO | N/A | N/A | N/A
DINUBA AVE - SPORTS PARK, REEDLEY | REEDLEY | 30675532 | FRESNO | N/A | TBD | N/A
BUTTONWILLOW & DINUBA | REEDLEY | 30676927 | FRESNO | 588819 | 2012 | 2013-01-25
*CANC* FRANKWOOD AVENUE REEDLEY R20A | REEDLEY | 30678560 | FRESNO | N/A | N/A | N/A
REED AVE, REEDLEY | REEDLEY | 74003532 | FRESNO | 2493012.88 | 2019 | 2020-01-14
PAPST AVE, ORLAND | ORLAND | No Order | GLENN | N/A | TBD | N/A
G & H STREETS, FROM 7TH TO 11TH STS. | ARCATA | 30171622 | HUMBOLDT | 1109690.86 | 2007 | 2007-07-31
EUREKA WATERFRONT RULE 20A *CANC | EUREKA | 30232261 | HUMBOLDT | 3513.06 | N/A | 2007-03-24
TRUESDALE ST | EUREKA | 30975304 | HUMBOLDT | 654697.39 | 2016 | 2016-10-19
R20A - 4TH ST EUREKA | EUREKA | 74014380 | HUMBOLDT | N/A | TBD | N/A
FRANCIS ST, FERNDALE | FERNDALE | No Order | HUMBOLDT | N/A | TBD | N/A
MAIN ST, FERNDALE | FERNDALE | No Order | HUMBOLDT | N/A | TBD | N/A
12TH STREET, FORTUNA | FORTUNA | 74004300 | HUMBOLDT | N/A | TBD | N/A
SCHOOL RD | HUMBOLDT COUNTY | 30406159 | HUMBOLDT | 3663855.44 | 2015 | 2015-07-14
GARBERVILLE TOWN SQUARE, GARBERVILLE | HUMBOLDT COUNTY | No Order | HUMBOLDT | N/A | TBD | N/A
E TRINIDAD | HUMBOLDT COUNTY, TRINIDAD | 30311450 | HUMBOLDT | 249877 | 2009 | 2010-03-16
WILDWOOD AVE PH 2, RIO DELL | RIO DELL | No Order | HUMBOLDT | N/A | TBD | N/A
VARSITY RD, ARVIN | ARVIN | No Order | KERN | N/A | TBD | N/A
STOCKDALE HWY PH 20A - COFFEE ROAD | BAKERSFIELD | 30271365 | KERN | 1749618.3667 | 2005 | 2007-03-24
EP ROSEDALE HIGHWAY RULE 20A | BAKERSFIELD | 30294146 | KERN | 525841.05 | 2006 | 2007-03-24
EP AQUATIC PARK/ICE CENTER RULE 20A | BAKERSFIELD | 30316645 | KERN | 217265.8 | 2006 | 2007-03-24
STOCKDALE HWY PH II RULE 20A | BAKERSFIELD | 30366094 | KERN | 560214.1 | 2006 | 2007-03-24
SPORTS VILLAGE- ASHE RD SEG. 1 BKSF | BAKERSFIELD | 30629431 | KERN | 787398 | 2010 | 2011-03-16
SOUTH MILL CREEK | BAKERSFIELD | 30656093 | KERN | 1518177 | 2011 | 2012-02-07
GOSFORD RD | BAKERSFIELD | 30726360 | KERN | 688009 | 2012 | 2013-01-25
CALLOWAY, BAKERSFIELD | BAKERSFIELD | 30764510 | KERN | 3425178.54 | 2017 | 2017-07-17
CALIFORNIA AVE | BAKERSFIELD | 30764513 | KERN | 932892.42 | 2014 | 2015-01-15
WIBLE RD | BAKERSFIELD | 30909576 | KERN | 2860709.76 | 2015 | 2016-01-13
STINE RD, BAKERSFIELD | BAKERSFIELD | 74001555 | KERN | N/A | TBD | N/A
34TH ST, BAKERSFIELD | BAKERSFIELD | 74012450 | KERN | N/A | TBD | N/A
*CANC* EP TAFT HWY BAKERSFIELD *CANC | BAKERSFIELD | 80045878 | KERN | N/A | N/A | N/A
*CANC* EP ASHE ROAD BAKERSFIELD *CANC | BAKERSFIELD | 80045879 | KERN | N/A | N/A | N/A
EP SHAFTER MEMORIAL PARK RULE 20A | KERN COUNTY | 30218464 | KERN | 155202.62 | 2005 | 2007-03-24
OLIVE AVE. (FRUITVALE - COFFEE) RULE 20A | KERN COUNTY | 30366845 | KERN | 1947899 | 2010 | 2011-03-16
SEVENTH STANDARD ROAD RULE 20A | KERN COUNTY | 30382278 | KERN | 208971.61 | 2006 | 2007-03-24
EP FORT TEJON RULE 20A - LEBEC | KERN COUNTY | 30558119 | KERN | 209282 | 2010 | 2010-08-26
COTTONWOOD ROAD, BAKERSFIELD | KERN COUNTY | 30675530 | KERN | 2734351 | 2013 | 2014-02-28
STATE ROUTE 43 KERN CNTY R20A | KERN COUNTY | 35040079 | KERN | N/A | N/A | N/A
GARZOLI AVE, MCFARLAND | MCFARLAND | 74003981 | KERN | N/A | TBD | N/A
ET CENTER ST. RULE20A -CITYOF TAFT *CANC | TAFT | 30253349 | KERN | 10088 | N/A | 2007-03-24
EP BECKES ST. RULE 20A *CANC *CANC | WASCO | 30329651 | KERN | 393 | N/A | 2007-03-24
LEMOORE AVE | KINGS COUNTY, LEMOORE | 30178490 | KINGS | 4290373.44 | 2012 | 2012-09-13
OLYMPIC DR - CANCELLATION | CLEARLAKE | 30058339 | LAKE | 89805 | N/A | 2012-02-07
NICE RULE 20A | LAKE COUNTY | 30381109 | LAKE | 784282 | 2010 | 2010-08-26
ISLAND DRIVE, CLEARLAKE | LAKE COUNTY | 30383780 | LAKE | 808835 | 2013 | 2014-02-28
UPPER LAKE | LAKE COUNTY | 30384129 | LAKE | 943679.53 | 2009 | 2010-03-16
SOUTH MAIN AND SODA BAY RD, LAKE COUNTY | LAKE COUNTY | 74001800 | LAKE | N/A | TBD | N/A
11TH ST, LAKEPORT | LAKEPORT | No Order | LAKE | N/A | TBD | N/A
DIST. 5 2ND- 6TH STREET, CHOWCHILLA | CHOWCHILLA | 30675657 | MADERA | N/A | TBD | N/A
RULE 20A - OLIVE AVE & M STREET, MADERA | MADERA | 30222042 | MADERA | 1492305.5444 | 2005 | 2007-03-24
C & D STREETS | MADERA | 30267067 | MADERA | 1990497.66 | 2014 | 2015-01-15
MADERA YOUTH CENTER | MADERA | 30675659 | MADERA | 993088.73 | 2014 | 2015-01-15
*CANC* LAKE STREET, MADERA, RULE 20A | MADERA | 30746199 | MADERA | N/A | N/A | N/A
DISTRICT 4 (FRONT ST. TO 9TH), CHOWCHILLA | MADERA COUNTY | 30520215 | MADERA | 3382558 | 2013 | 2014-02-28
OAKHURST RD 427 | MADERA COUNTY | 30528244 | MADERA | 6256.21 | N/A | 2009-07-29
MARTIN ST | MADERA COUNTY | 30746320 | MADERA | 1533550.22 | 2016 | 2016-07-20
ROAD 26, MADERA COUNTY | MADERA COUNTY | 74001556 | MADERA | 3246486.15 | 2019 | 2019-11-21
SAN RAFAEL AVE | BELVEDERE | 30419337 | MARIN | 122129 | 2009 | 2010-03-16
MID SAN RAFAEL AVE | BELVEDERE | 30809002 | MARIN | 463327 | 2013 | 2014-02-28
TAMALPAIS BLVD. | CORTE MADERA | 30185815 | MARIN | 1231589.52 | 2009 | 2009-07-29
BANK ST, FAIRFAX | FAIRFAX | No Order | MARIN | N/A | TBD | N/A
DOHERTY DR LARKSPUR R20A | LARKSPUR | 74013527 | MARIN | N/A | TBD | N/A
NORTH SAN PEDRO | MARIN COUNTY | 30185077 | MARIN | 4409610.81 | 2009 | 2009-07-29
R20A - ALMEDA DEL PRADO, MA CNTY | MARIN COUNTY | 30616113 | MARIN | 1544188 | 2010 | 2010-08-26
E BLITHEDALE | MILL VALLEY | 30249966 | MARIN | 3000582.66 | 2008 | 2008-08-18
NOVATO BLVD, NOVATO | NOVATO | 30899832 | MARIN | N/A | TBD | N/A
SIR FRANCIS DRAKE BLVD, ROSS | ROSS | No Order | MARIN | N/A | TBD | N/A
GREENFIELD RD | SAN ANSELMO | 30615999 | MARIN | 1468753 | 2013 | 2014-02-28
W FRANCISCO BLVD | SAN RAFAEL | 30264400 | MARIN | 444675.96 | 2008 | 2008-08-18
FREITAS PARKWAY, SAN RAFAEL | SAN RAFAEL | No Order | MARIN | N/A | TBD | N/A
R20A - SAN CARLOS, SAUSALITO *CANC*CANC | SAUSALITO | 30309875 | MARIN | 98446.12 | N/A | 2007-03-24
TIBURON BLVD | TIBURON | 31172652 | MARIN | N/A | TBD | N/A
GUALALA, PH 1 | MENDOCINO COUNTY | 30172470 | MENDOCINO | 4067720 | 2013 | 2014-02-28
CASPER RULE 20A *CANC | MENDOCINO COUNTY | 30264707 | MENDOCINO | 3032.56 | N/A | 2007-03-24
*CANC* GUALALA PH2 MENDOCINO CNTY R20A | MENDOCINO COUNTY | 30709622 | MENDOCINO | N/A | N/A | N/A
SCHOOL ST, POINT ARENA | POINT ARENA | No Order | MENDOCINO | N/A | TBD | N/A
SNIDER PARK, WILLITS | WILLITS | No Order | MENDOCINO | N/A | TBD | N/A
BELLEVUE RD | ATWATER | 30660879 | MERCED | 3286906.52 | 2014 | 2015-01-15
*CANC* BELLEVUE RD, PHASE 2 ATWATER R20A | ATWATER | 30755274 | MERCED | N/A | N/A | N/A
BLOSSOM ST, DOS PALOS | DOS PALOS | No Order | MERCED | N/A | TBD | N/A
EP HENRY MILLER PLAZA RULE 20A PH 1,LB | LOS BANOS | 30421025 | MERCED | 131963.7 | 2006 | 2007-03-24
EP 7TH ST. FROM H ST TO E ST, *CANC*CANC | LOS BANOS | 30488766 | MERCED | N/A | N/A | N/A
7TH STREET, FROM H TO E STREETS | LOS BANOS | 30488767 | MERCED | 959318.81 | 2007 | 2008-02-15
DISTRICT 7C, LOS BANOS | LOS BANOS | 30692635 | MERCED | 207191.51 | N/A | 2018-10-23
*CANC* H ST DIST 7B, LOS BANOS R20A | LOS BANOS | 30776761 | MERCED | N/A | N/A | N/A
*CANC* 7TH ST DIST 8 LOS BANOS R20A | LOS BANOS | 30778320 | MERCED | N/A | N/A | N/A
C:GEP RULE 20A YOSEMITE PKWY,MERCED | MERCED | 30140609 | MERCED | 1510567.83 | 2006 | 2007-03-24
BRADLEY OVERPASS HWY 140 | MERCED | 30492230 | MERCED | 2167700 | 2013 | 2014-02-28
PARSONS AVE | MERCED | 30835217 | MERCED | 1569890 | 2015 | 2016-01-13
SUTTER HOSPITAL | MERCED COUNTY | 30317644 | MERCED | 2026094.22 | 2012 | 2012-09-13
WALNUT AVE, WINTON | MERCED COUNTY | 30616106 | MERCED | 4247347.82 | 2017 | 2017-04-14
LOBO AVE, MERCED COUNTY | MERCED COUNTY | 74001558 | MERCED | N/A | TBD | N/A
DAN WARD RD, MERCED COUNTY | MERCED COUNTY | 74003380 | MERCED | N/A | TBD | N/A
EL CAMINO REAL, GREENFIELD | GREENFIELD | No Order | MONTEREY | N/A | TBD | N/A
C:EP 20 A BROADWAY/ 2ND ST-KC *CANC | KING CITY | 30105758 | MONTEREY | 7622.96 | N/A | 2007-03-24
RESERVATION RD, MARINA | MARINA | 30649669 | MONTEREY | N/A | TBD | N/A
*CANC* DEL MONTE AVE | MONTEREY | 30098410 | MONTEREY | 94618.84 | N/A | 2016-10-19
CARMEL VALLEY RD, CARMEL-BY-THE-SEA | MONTEREY COUNTY | 30075639 | MONTEREY | 1707828.55 | 2007 | 2008-02-15
C: CV RD RULE 20A SUBSTRUCTURE ONLY | MONTEREY COUNTY | 30244030 | MONTEREY | 194765.92 | 2006 | 2007-03-24
MOSS LANDING, MONTEREY COUNTY | MONTEREY COUNTY | 74004303 | MONTEREY | N/A | TBD | N/A
CARMEL VALLEY RD PH 2, MONTEREY COUNTY | MONTEREY COUNTY | No Order | MONTEREY | N/A | TBD | N/A
LOWER FOREST AVE | PACIFIC GROVE | 30233278 | MONTEREY | 751389.03 | 2008 | 2008-08-18
CENTRAL AVE DISTRICT, PACIFIC GROVE | PACIFIC GROVE | No Order | MONTEREY | N/A | TBD | N/A
EAST ALISAL RULE 20-A-SALINAS | SALINAS | 30142636 | MONTEREY | 917800.11 | 2005 | 2007-03-24
E. MARKET PH1, SALINAS | SALINAS | 30393476 | MONTEREY | 4057060.88 | 2018 | 2019-02-19
E. MARKET PH2, SALINAS | SALINAS | 30616115 | MONTEREY | 2703867.16 | 2018 | 2018-04-30
WILLIAMS RD PH 1, SALINAS | SALINAS | No Order | MONTEREY | N/A | TBD | N/A
UUD #1, SAND CITY | SAND CITY | No Order | MONTEREY | N/A | TBD | N/A
UPPER BROADWAY | SEASIDE | 30072595 | MONTEREY | 2678450 | 2012 | 2013-01-25
GREEN ISLAND DR, AMERICAN CANYON | AMERICAN CANYON | 31363065 | NAPA | N/A | TBD | N/A
JEFFERSON ST, NAPA | NAPA | 74003533 | NAPA | N/A | TBD | N/A
EP 1ST&2ND ST, NAPA RULE 20A | NAPA COUNTY | 30219331 | NAPA | 3008083 | 2010 | 2010-08-26
HIGHWAY 29 | NAPA COUNTY, ST HELENA | 30185719 | NAPA | 17048835.58 | 2015 | 2015-07-14
YOUNTVILLE PARK, YOUNTVILLE | YOUNTVILLE | No Order | NAPA | N/A | TBD | N/A
GEP MILL ST RULE 20A GRASS VALLEY | GRASS VALLEY | 30169003 | NEVADA | 970238.61 | 2005 | 2007-03-24
E. MAIN ST, GRASS VALLEY | GRASS VALLEY | No Order | NEVADA | N/A | TBD | N/A
EAST MAIN ST, GRASS VALLEY | GRASS VALLEY | No Order | NEVADA | N/A | TBD | N/A
BROAD ST NEVADA CITY R20A | NEVADA CITY | 74013926 | NEVADA | N/A | TBD | N/A
COMBIE RD PHASE II | NEVADA COUNTY | 30027068 | NEVADA | 88884.27 | N/A | 2007-07-31
COMBIE RD PH2, NEVADA CNTY | NEVADA COUNTY | 30616100 | NEVADA | 2938685.84 | 2017 | 2017-10-13
COMBIE RD/MAGNOLIA RD PH 3A, NEVADA COUNTY | NEVADA COUNTY | 31144652 | NEVADA | N/A | TBD | N/A
LINCOLN WY & HIGH ST | AUBURN | 30642311 | PLACER | 1544684.4 | 2015 | 2015-07-14
*CANC* MAIN ST | COLFAX | 31138035 | PLACER | 6534.83 | N/A | 2015-10-06
CIVIC CENTER PLAZA, LINCOLN | LINCOLN | 74015721 | PLACER | N/A | TBD | N/A
SIERRA COLLEGE, LOOMIS | LOOMIS | No Order | PLACER | N/A | TBD | N/A
MEADOW VISTA | PLACER COUNTY | 30169463 | PLACER | 5084512.58 | 2016 | 2016-04-09
HWY 49 - PG&E LEAD | PLACER COUNTY | 30170714 | PLACER | 4568193.44 | 2016 | 2016-07-20
HIGHWAY 49 - PAC BELL LEAD | PLACER COUNTY | 30170818 | PLACER | 2761892 | 2013 | 2014-02-28
R4 ATWOOD RD AUBURN PLACER CNTY R20A | PLACER COUNTY | 30817975 | PLACER | N/A | N/A | N/A
BOWMAN RD PH1 AUBURN PLACER CNTY R20A | PLACER COUNTY | 30817978 | PLACER | N/A | N/A | N/A
MAIN ST NEWCASTLE PLACER CNTY R20A | PLACER COUNTY | 30817979 | PLACER | N/A | N/A | N/A
BOWMAN RD PH2 AUBURN PLACER CNTY R20A | PLACER COUNTY | 30837081 | PLACER | N/A | N/A | N/A
MAIN ST, GREENVILLE | PLUMAS COUNTY | 30733248 | PLUMAS | 1555870.62 | 2016 | 2016-10-19
JACKSON BLVD, ISLETON | ISLETON | No Order | SACRAMENTO | N/A | TBD | N/A
HIGHWAY 156, SAN BENITO COUNTY | SAN BENITO COUNTY | No Order | SAN BENITO | N/A | TBD | N/A
E PC C&CSF DISTRICT,SAN FRANC | SAN FRANCISCO | 30010765 | SAN FRANCISCO | 1425471.75 | 2005 | 2007-03-24
C:EPC DOLORES HTS 2 - R20A (W/GPRP), SF | SAN FRANCISCO | 30010785 | SAN FRANCISCO | 1521687.91 | 2006 | 2007-03-24
C:E PC ALPINE TERRACE - R20A (W/GPRP), S | SAN FRANCISCO | 30010943 | SAN FRANCISCO | 997312.72 | 2006 | 2007-03-24
GOUGH & GREEN W/GPRP | SAN FRANCISCO | 30011097 | SAN FRANCISCO | 2075842.58 | 2008 | 2008-08-18
OCEAN AVE, PHASE 1 | SAN FRANCISCO | 30011544 | SAN FRANCISCO | 1726898.3 | 2008 | 2008-08-18
E PC MONTEZUMA/AZTEC,SAN FRANC | SAN FRANCISCO | 30011696 | SAN FRANCISCO | 261704.18 | 2005 | 2007-03-24
EC POTOMAC & WALLER - R20A, SF | SAN FRANCISCO | 30011832 | SAN FRANCISCO | 1132966.6422 | 2005 | 2007-03-24
C:E PC ARGUELLO-7TH&LINCOLN-KIRK,SAN FRA | SAN FRANCISCO | 30014020 | SAN FRANCISCO | 4659316.46 | 2006 | 2007-03-24
PC PRESIDIO HTS 4A, SF | SAN FRANCISCO | 30014022 | SAN FRANCISCO | 2203646 | 2010 | 2010-08-26
BANKS/CHAPMAN (SUBSTRUCTURE PORTION) W/GPRP | SAN FRANCISCO | 30034755 | SAN FRANCISCO | 3440952.05 | 2008 | 2009-03-17
LOWER CLAYTON W/GPRP | SAN FRANCISCO | 30040767 | SAN FRANCISCO | 771641.88 | 2008 | 2009-03-17
C:E PC LAGUNA,BUSH-CALIF,R20A(W/GPRP)SF | SAN FRANCISCO | 30118499 | SAN FRANCISCO | 635984.86 | 2006 | 2007-03-24
LINCOLN #3 (CABLING PORTION, 2001 PROJECT) | SAN FRANCISCO | 30137189 | SAN FRANCISCO | 290756.65 | 2008 | 2009-03-17
C:E POTOMAC & WALLER-R20A, SF CBLG | SAN FRANCISCO | 30138317 | SAN FRANCISCO | 530922.15 | 2006 | 2007-03-24
C:E PC PRESIDIO HTS (6TH / LAKE) | SAN FRANCISCO | 30177649 | SAN FRANCISCO | 798692 | 2006 | 2007-03-24
OCEAN AVE PH 2 (SUBSTRUCTURE PORTION) | SAN FRANCISCO | 30180213 | SAN FRANCISCO | 2000195.42 | 2008 | 2009-03-17
ALPINE TERRACE (CABLING PORTION) | SAN FRANCISCO | 30181165 | SAN FRANCISCO | 312250.44 | 2008 | 2009-03-17
ARGUELLO - 7TH & LINCOLN-KIRK | SAN FRANCISCO | 30184983 | SAN FRANCISCO | 1706112.77 | 2009 | 2009-07-29
GOUGH & GREEN (CABLING PORTION) W/GPRP | SAN FRANCISCO | 30192420 | SAN FRANCISCO | 1012903.58 | 2008 | 2009-03-17
3RD STREET LIGHT RAIL / PHASE 1 | SAN FRANCISCO | 30200858 | SAN FRANCISCO | 2196860.4 | 2008 | 2008-08-18
3RD STREET LIGHT RAIL / PHASE 2 | SAN FRANCISCO | 30211896 | SAN FRANCISCO | 5416349.67 | 2008 | 2008-08-18
3RD ST LIGHT RAIL, PHASE 3 | SAN FRANCISCO | 30215433 | SAN FRANCISCO | 2810321.26 | 2009 | 2009-07-29
GES LAIDLEY ST R20A W/GPRP SAN FRANCISCO | SAN FRANCISCO | 30216820 | SAN FRANCISCO | 1425443.06 | 2006 | 2007-03-24
LINCOLN WAY #2 (CABLING PORTION) W/ GPRP | SAN FRANCISCO | 30222280 | SAN FRANCISCO | 1114744.99 | 2008 | 2009-03-17
OC1 GES TEXAS/19TH ST. SF RL20A W/GPRP | SAN FRANCISCO | 30222281 | SAN FRANCISCO | 2348558 | 2010 | 2011-03-16
OC1 GES DOLORES ST R20/A PHASE 1 W/GPRP | SAN FRANCISCO | 30222282 | SAN FRANCISCO | 2871615 | 2010 | 2011-03-16
GES 9TH & 10TH AVE/ORTEGA R20A W/GPRP | SAN FRANCISCO | 30222283 | SAN FRANCISCO | 2383495.97 | 2006 | 2007-03-24
3RD STREET LIGHT RAIL / XING - A | SAN FRANCISCO | 30223280 | SAN FRANCISCO | 57429.87 | N/A | 2007-07-31
3RD STREET / XING 2 | SAN FRANCISCO | 30223284 | SAN FRANCISCO | 214111.14 | 2007 | 2007-07-31
FUNSTON AVE W/ GPRP | SAN FRANCISCO | 30223375 | SAN FRANCISCO | 2729141.09 | 2008 | 2008-08-18
OC1 GES SAN BRUNO 2 R20A PH1 W/GPRP,SF | SAN FRANCISCO | 30223377 | SAN FRANCISCO | 2077580 | 2010 | 2011-03-16
OCEAN AVE, PHASE 3A | SAN FRANCISCO | 30235385 | SAN FRANCISCO | 1535301.74 | 2008 | 2008-08-18
3RD STREET / XING -3 | SAN FRANCISCO | 30236749 | SAN FRANCISCO | 290630.24 | 2007 | 2008-02-15
GEPC OCEAN AVE.-R20A PHASE I CABLING | SAN FRANCISCO | 30237177 | SAN FRANCISCO | 398529.84 | 2005 | 2007-03-24
OCEAN AVE, PHASE II CABLING | SAN FRANCISCO | 30237178 | SAN FRANCISCO | 989722.61 | 2007 | 2007-07-31
OCEAN AVE, PHASE III-B SUBST | SAN FRANCISCO | 30239753 | SAN FRANCISCO | 697184.43 | 2007 | 2007-07-31
OC1 GES SAN BRUNO 2 R20A PH2 W/GPRP SF | SAN FRANCISCO | 30242967 | SAN FRANCISCO | 3927267 | 2010 | 2011-03-16
PRESIDIO HTS., PHASE 3 | SAN FRANCISCO | 30245221 | SAN FRANCISCO | 2312220.27 | 2009 | 2009-07-29
MID-24TH | SAN FRANCISCO | 30249353 | SAN FRANCISCO | 2920534 | 2011 | 2012-02-07
OC1 EP CORBETT 1B - RULE 20A | SAN FRANCISCO | 30249355 | SAN FRANCISCO | 4673749 | 2010 | 2011-03-16
EP - BROAD/RANDOLPH R20A | SAN FRANCISCO | 30249357 | SAN FRANCISCO | 5954541 | 2010 | 2010-08-26
COURTLAND CONNECT - DIST.#339 - PH 1 | SAN FRANCISCO | 30249359 | SAN FRANCISCO | 4105893.35 | 2012 | 2012-09-13
EP CHINATOWN ALLEYS (JOHN) WO/GPRP | SAN FRANCISCO | 30249434 | SAN FRANCISCO | 190460.48 | 2005 | 2007-03-24
GEP MID LAKE R20A | SAN FRANCISCO | 30249629 | SAN FRANCISCO | 2463511 | 2010 | 2010-08-26
MID-FOLSOM ST - DIST.#350 - PH 1 | SAN FRANCISCO | 30249631 | SAN FRANCISCO | 3272662.79 | 2012 | 2012-09-13
PRESIDIO HTS. 4C W/GPRP | SAN FRANCISCO | 30249633 | SAN FRANCISCO | 2918860.03 | 2009 | 2009-07-29
LIBERTY HILL - DIST.#329 - PH 1 | SAN FRANCISCO | 30250174 | SAN FRANCISCO | 4416283.62 | 2012 | 2012-09-13
GEP DOLORES STREET 2 R20A | SAN FRANCISCO | 30250175 | SAN FRANCISCO | 2575673 | 2010 | 2010-08-26
EP CHINATOWN ALLEYS (SPOFFORD) WO/GPRP | SAN FRANCISCO | 30263286 | SAN FRANCISCO | 138224.51 | 2006 | 2007-03-24
OCEAN AVE, PHASE 3A/B CBL/OH | SAN FRANCISCO | 30267444 | SAN FRANCISCO | 1312087.82 | 2007 | 2007-07-31
LINCOLN WAY 6 W/GPRP | SAN FRANCISCO | 30271350 | SAN FRANCISCO | 677422.82 | 2008 | 2008-08-18
LAIDLEY ST - DIST.#330 - PH 2 | SAN FRANCISCO | 30278150 | SAN FRANCISCO | 1366056.96 | 2012 | 2012-09-13
OAK STREET RULE 20A | SAN FRANCISCO | 30297408 | SAN FRANCISCO | 2037687 | 2010 | 2010-08-26
OC1 9TH & 10TH AVE/ORTEGA R20A CABLING | SAN FRANCISCO | 30303305 | SAN FRANCISCO | 2076535 | 2010 | 2011-03-16
GEP: OCTAVIA ST R20A | SAN FRANCISCO | 30314814 | SAN FRANCISCO | 1590802 | 2010 | 2010-08-26
STILLMAN STREET | SAN FRANCISCO | 30328762 | SAN FRANCISCO | 496270.32 | 2007 | 2008-02-15
BANKS/CHAPMAN RULE 20A | SAN FRANCISCO | 30333103 | SAN FRANCISCO | 1787842 | 2010 | 2010-08-26
OC1 GEP LIBERTY HILL 2 R20A W/GPRP | SAN FRANCISCO | 30334696 | SAN FRANCISCO | 3077951 | 2010 | 2011-03-16
GEP DOLORES STREET 3 R20A | SAN FRANCISCO | 30334698 | SAN FRANCISCO | 4558682 | 2010 | 2010-08-26
COURTLAND CONNECT - DIST.#339 - PH 2 | SAN FRANCISCO | 30334699 | SAN FRANCISCO | 4549044.93 | 2012 | 2012-09-13
CORBETT AVE - DIST.#311 - PH 2 | SAN FRANCISCO | 30334782 | SAN FRANCISCO | 3374542.84 | 2012 | 2012-09-13
MID-FOLSOM ST. | SAN FRANCISCO | 30334783 | SAN FRANCISCO | 3565078.06 | 2012 | 2012-09-13
GEP OAKDALE/PALOU 1 R20A | SAN FRANCISCO | 30334785 | SAN FRANCISCO | 4772907 | 2010 | 2010-08-26
OAKDALE/PALOU PH 2 | SAN FRANCISCO | 30334786 | SAN FRANCISCO | 7097063.45 | 2014 | 2015-01-15
GEP TARAVEL ST. R20A | SAN FRANCISCO | 30334788 | SAN FRANCISCO | 3675619 | 2010 | 2010-08-26
25TH STREET W/GPRP | SAN FRANCISCO | 30334789 | SAN FRANCISCO | 955472.96 | 2008 | 2009-03-17
FLINT/16TH ST W/GPRP | SAN FRANCISCO | 30334790 | SAN FRANCISCO | 457893.43 | 2008 | 2009-03-17
LINCOLN WAY 4 W/GPRP | SAN FRANCISCO | 30334791 | SAN FRANCISCO | 272358.39 | 2008 | 2008-08-18
OC1 GEP LINCOLN WAY 5 RULE 20A W/GPRP | SAN FRANCISCO | 30334792 | SAN FRANCISCO | 3021505 | 2010 | 2011-03-16
OAKDALE/PALOU/MENDELL PLAZA | SAN FRANCISCO | 30340559 | SAN FRANCISCO | 212547.3 | 2008 | 2008-08-18
GREAT HWY W/GPRP | SAN FRANCISCO | 30376352 | SAN FRANCISCO | 1349572.27 | 2009 | 2010-03-16
TARAVAL - DIST.#346 - PH 2 | SAN FRANCISCO | 30383452 | SAN FRANCISCO | 8860553.91 | 2012 | 2012-09-13
CHINATOWN ALLEYS (WAVERLY ) | SAN FRANCISCO | 30391234 | SAN FRANCISCO | 319526.64 | 2007 | 2008-02-15
OAK STREET (STANYAN- OAK) | SAN FRANCISCO | 30400105 | SAN FRANCISCO | 1744118.29 | 2008 | 2008-08-18
OCEAN AVE - DIST.#338 - PH 4 | SAN FRANCISCO | 30400280 | SAN FRANCISCO | 3741504.31 | 2012 | 2012-09-13
DUBOCE/CHURCH - DIST.#324 | SAN FRANCISCO | 30410006 | SAN FRANCISCO | 2999614.83 | 2012 | 2012-09-13
DUNCAN/NEWBURG - DIST.#332 | SAN FRANCISCO | 30410007 | SAN FRANCISCO | 2565688.28 | 2012 | 2012-09-13
CHINATOWN ALLEYS (BECKETT) | SAN FRANCISCO | 30443282 | SAN FRANCISCO | 186532.49 | 2008 | 2008-08-18
CHINATOWN ALLEYS (WENTWORTH) | SAN FRANCISCO | 30443283 | SAN FRANCISCO | 284499.38 | 2008 | 2008-08-18
BANKS/CHAPMAN, REPLACE POLE | SAN FRANCISCO | 30459828 | SAN FRANCISCO | 25514.23 | 2008 | 2008-08-18
GES MISSION ST R20A | SAN FRANCISCO | 30223376 & 31370088 | SAN FRANCISCO | 5122168.34 | 2010 | 2010-08-26
FIRST STREET, ESCALON | ESCALON | No Order | SAN JOAQUIN | N/A | TBD | N/A
LOUISE AVE | LATHROP | 30306856 | SAN JOAQUIN | 520569.47 | 2007 | 2007-07-31
259 N. WILMA AVE, RIPON | RIPON | 30406567 | SAN JOAQUIN | 866091.4 | 2008 | 2009-03-17
STOCKTON AVE, RIPON | RIPON | No Order | SAN JOAQUIN | N/A | TBD | N/A
EP WOODBRIDGE RULE 20A | SAN JOAQUIN COUNTY | 30112580 | SAN JOAQUIN | 1165390.96 | 2006 | 2007-03-24
HAMMER LANE RULE 20A-SJ CO. PART | SAN JOAQUIN COUNTY | 30292479 | SAN JOAQUIN | 994499 | 2010 | 2010-08-26
LOWER SACRAMENTO, SAN JOAQUIN CNTY | SAN JOAQUIN COUNTY | 30771373 | SAN JOAQUIN | 7303864.04 | 2017 | 2017-04-14
EP CITY OF STKN EL DORADO ST -RULE 20A | STOCKTON | 30194569 | SAN JOAQUIN | 386955.72 | 2005 | 2007-03-24
EP RULE 20A, LOWER SACRAMENTO RD., STKN. | STOCKTON | 30222303 | SAN JOAQUIN | 939974.34 | 2006 | 2007-03-24
HAMMER LANE, STOCKTON | STOCKTON | 30292474 | SAN JOAQUIN | 486964.2 | 2008 | 2009-03-17
PERSHING STREET | STOCKTON | 30339035 | SAN JOAQUIN | 697055.19 | 2007 | 2008-02-15
RULE 20A - FREMONT STREET - STOCKTON | STOCKTON | 30339206 | SAN JOAQUIN | 624415.42 | 2006 | 2007-03-24
SOUTHSHORE PHASE 1 | STOCKTON | 30359162 | SAN JOAQUIN | 164931.5 | 2007 | 2007-07-31
EL DORADO ST, PH 1 | STOCKTON | 30402155 | SAN JOAQUIN | 1284245.91 | 2009 | 2009-07-29
SOUTHSHORE PH2 STOCKTON R20A | STOCKTON | 30425691 | SAN JOAQUIN | N/A | N/A | N/A
AIRPORT WAY | STOCKTON | 30454611 | SAN JOAQUIN | 1082550.78 | 2009 | 2009-07-29
EL DORADO ST, PH 2 | STOCKTON | 30469953 | SAN JOAQUIN | 1018164.47 | 2009 | 2009-07-29
PERSHING AVE, PH 2 | STOCKTON | 30613816 | SAN JOAQUIN | 3406041.39 | 2012 | 2012-09-13
FREMONT STREET PH2 STOCKTON R20A | STOCKTON | 30657289 | SAN JOAQUIN | N/A | N/A | N/A
*CANC* AIRPORT WAY PH2 STOCKTON R20A | STOCKTON | 30766533 | SAN JOAQUIN | N/A | N/A | N/A
DOWNTOWN STOCKTON R20A | STOCKTON | 35029720 | SAN JOAQUIN | N/A | TBD | N/A
EP: RULE 20 CITY OF TRACY [FIREHOUSE] | TRACY | 30229236 | SAN JOAQUIN | 242942.7034 | 2005 | 2007-03-24
GRANT LINE RD, PH 2 | TRACY | 30767869 | SAN JOAQUIN | 749975 | 2013 | 2014-02-28
E PC GRAND AVE-101 TO HALCYON,AG | ARROYO GRANDE | 30093824 | SAN LUIS OBISPO | 727377.37 | 2005 | 2007-03-24
GRAND AVE [OAK PARK TO ELM] | ARROYO GRANDE | 30323741 | SAN LUIS OBISPO | 2312479.78 | 2015 | 2016-01-13
GRAND AVE [ELM TO HALCYON], ARROYO GRANDE | ARROYO GRANDE | 30485630 | SAN LUIS OBISPO | N/A | TBD | N/A
OAK PARK BLVD | GROVER BEACH | 30323751 | SAN LUIS OBISPO | 1169785.93 | 2012 | 2012-09-13
*CANC*RAMONA AVE GROVER BEACH R20A | GROVER BEACH | 30794542 | SAN LUIS OBISPO | N/A | N/A | N/A
C:EP MORRO BAY BLVD, 20A, MORRO BAY | MORRO BAY | 30186000 | SAN LUIS OBISPO | 3811 | N/A | 2007-03-24
MAIN & BEACH STREETS., MORRO BAY | MORRO BAY | 74001552 | SAN LUIS OBISPO | 332719.22 | N/A | 2018-10-23
RIVERSIDE AVE | PASO ROBLES | 30794479 | SAN LUIS OBISPO | 2720690.18 | 2016 | 2016-07-20
*CANC*RULE 20A 6TH-9TH & 9TH-10TH, *CANC | PASO ROBLES | 80006843 | SAN LUIS OBISPO | N/A | N/A | N/A
SHELL BEACH RD, PISMO BEACH | PISMO BEACH | 74001553 | SAN LUIS OBISPO | N/A | TBD | N/A
C:EP CO OF SLO 20A, N. MORRO BAY HWY 1 R | SAN LUIS OBISPO COUNTY | 30148680 | SAN LUIS OBISPO | 637238.65 | 2006 | 2007-03-24
C:EP CO OF SLO-TEFFT ST, NIPOMO 20A R | SAN LUIS OBISPO COUNTY | 30197775 | SAN LUIS OBISPO | 792110.21 | 2006 | 2007-03-24
CO. OF SLO-AVILA BCH RL 20A,SAN MIGUEL R | SAN LUIS OBISPO COUNTY | 30323748 | SAN LUIS OBISPO | 253068.68 | 2006 | 2007-03-24
LOS OSOS VALLEY RD, SAN LUIS OBISPO COUNTY | SAN LUIS OBISPO COUNTY | 30563617 | SAN LUIS OBISPO | 5318373.62 | 2018 | 2019-02-19
EL CAMINO REAL, SANTA MARGARITA | SAN LUIS OBISPO COUNTY | 30563618 | SAN LUIS OBISPO | 2085205.56 | 2016 | 2016-07-20
MAIN ST, TEMPLETON | SAN LUIS OBISPO COUNTY | 30563619 | SAN LUIS OBISPO | 937277 | 2012 | 2013-01-25
SAN LUIS DRIVE, AVILA BEACH | SAN LUIS OBISPO COUNTY | No Order | SAN LUIS OBISPO | N/A | TBD | N/A
SOUTH BAY BLVD, SLO COUNTY | SAN LUIS OBISPO COUNTY | No Order | SAN LUIS OBISPO | N/A | TBD | N/A
CITY OF SLO BROAD ST PH 1 | SAN LUIS OBISPO, SAN LUIS OBISPO COUNTY | 30563616 | SAN LUIS OBISPO | 5094590.98 | 2014 | 2015-01-15
BROAD STREET PH 2, SAN LUIS OBISPO | SAN LUIS OBISPO, SAN LUIS OBISPO COUNTY | 30677482 | SAN LUIS OBISPO | 3267025 | 2013 | 2014-02-28
OLD COUNTY ROAD PH 1, BELMONT | BELMONT, SAN MATEO COUNTY | 30827391 | SAN MATEO | 4435363.48 | 2019 | 2020-01-14
EL CAMINO REAL PH 1, BURLINGAME | BURLINGAME | No Order | SAN MATEO | N/A | TBD | N/A
EL CAMINO REAL | COLMA, DALY CITY, SAN MATEO COUNTY | 30010732 | SAN MATEO | 2238614 | 2011 | 2012-02-07
*CANC* HILLSIDE BLVD PH 1 | DALY CITY | 30487832 | SAN MATEO | 14125.69 | N/A | 2014-02-28
*CANC* HILLSIDE BLVD PH 2 | DALY CITY | 30487833 | SAN MATEO | 10241.37 | N/A | 2014-02-28
GENEVA AVE PH 1 | DALY CITY | 30669061 | SAN MATEO | 6011029.78 | 2016 | 2016-10-19
GENEVA AVE PH 2, DALY CITY | DALY CITY | 30707682 | SAN MATEO | N/A | TBD | N/A
BAY RD, EAST PALO ALTO | EAST PALO ALTO | 31059780 | SAN MATEO | 1920415.41 | 2019 | 2019-04-12
HWY 92/MAIN ST | HALF MOON BAY | 30206851 | SAN MATEO | 845737 | 2011 | 2012-02-07
CORREAS ST, HALF MOON BAY | HALF MOON BAY | 31271654 | SAN MATEO | N/A | TBD | N/A
RALSTON/EUCALYPTUS AVENUES | HILLSBOROUGH | 30367568 | SAN MATEO | 2058774.42 | 2012 | 2012-09-13
ESPLANADE AVE | PACIFICA | 30166232 | SAN MATEO | 165487.87 | 2009 | 2009-07-29
SAN PEDRO CREEK PHASE 1 | PACIFICA | 30195251 | SAN MATEO | 401204.26 | 2007 | 2007-07-31
PALMETTO AVE, PACIFICA | PACIFICA | 30700370 | SAN MATEO | 5555654.92 | 2019 | 2020-01-14
ALPINE RD, PORTOLA VALLEY | PORTOLA VALLEY | 30992944 | SAN MATEO | N/A | TBD | N/A
ES ROOSEVELT AVE, REDWOOD CITY RULE 20A | REDWOOD CITY | 30208461 | SAN MATEO | 1218971.72 | 2006 | 2007-03-24
MIDDLEFIELD RD, REDWOOD CITY | REDWOOD CITY | 74001642 | SAN MATEO | N/A | TBD | N/A
INDUSTRIAL | SAN CARLOS | 30098043 | SAN MATEO | 2934893.06 | 2008 | 2008-08-18
*CANC*C:EP INDUSTRIAL RULE 20A, S.C. | SAN CARLOS | 30417989 | SAN MATEO | 451.35 | N/A | 2007-07-31
OLD COUNTY RD | SAN CARLOS | 30906266 | SAN MATEO | 3072449.62 | 2016 | 2016-04-09
CITY SAN MATEO, ES/101 @ END/LA SALVA | SAN MATEO | 30182523 | SAN MATEO | 354040.51 | 2005 | 2007-03-24
25TH AVE PH 1, SAN MATEO | SAN MATEO | 30665355 | SAN MATEO | 3088685.06 | 2018 | 2018-07-17
25TH AVE PH 2, SAN MATEO | SAN MATEO | 30692251 | SAN MATEO | N/A | TBD | N/A
MIRADA RD | SAN MATEO COUNTY | 30944299 | SAN MATEO | 833659.07 | 2015 | 2016-01-13
MIDDLEFIELD RD PH 2, SAN MATEO COUNTY | SAN MATEO COUNTY | 74004302 | SAN MATEO | N/A | TBD | N/A
MISSION RD SOUTH SAN FRANCISCO R20A | SOUTH SAN FRANCISCO | 35118760 | SAN MATEO | N/A | TBD | N/A
SPRUCE AVE, SOUTH SAN FRANCISCO | SOUTH SAN FRANCISCO | 74009301 | SAN MATEO | N/A | TBD | N/A
ANTOINETTE LANE SOUTH SAN FRANCISCO R20A | SOUTH SAN FRANCISCO | 74015280 | SAN MATEO | N/A | TBD | N/A
BASELINE AVE, BALLARD | SANTA BARBARA COUNTY | 30442255 | SANTA BARBARA | 1337063 | 2013 | 2014-02-28
BRADLEY RD, SANTA MARIA | SANTA BARBARA COUNTY | 74009862 | SANTA BARBARA | N/A | TBD | N/A
CIVIC CENTER, SANTA MARIA | SANTA MARIA | 74005712 | SANTA BARBARA | N/A | TBD | N/A
MISSION DRIVE/5TH ST, SOLVANG | SOLVANG | 31056750 | SANTA BARBARA | N/A | TBD | N/A
WINCHESTER BLVD | CAMPBELL | 30720578 | SANTA CLARA | 6429730.09 | 2015 | 2016-01-13
STEVENS CREEK BLVD DIST 16, CUPERTINO | CUPERTINO | No Order | SANTA CLARA | N/A | TBD | N/A
STEVENS CREEK BLVD | CUPERTINO, SAN JOSE | 30344383 | SANTA CLARA | 1536350 | 2013 | 2014-02-28
FIRST STREET | LOS ALTOS | 30706328 | SANTA CLARA | 2250164 | 2013 | 2014-02-28
FIRST ST PH 2, LOS ALTOS | LOS ALTOS | 30899980 | SANTA CLARA | 1630968.37 | 2017 | 2017-10-13
PURISSIMA/ALTAMONT ROADS | LOS ALTOS HILLS | 30449755 | SANTA CLARA | 815900.21 | 2009 | 2010-03-16
EL MONTE RD PH 1, LOS ALTOS HILLS | LOS ALTOS HILLS | No Order | SANTA CLARA | N/A | TBD | N/A
LOS GATOS BLVD, LOS GATOS | LOS GATOS | 31269308 | SANTA CLARA | N/A | TBD | N/A
SOUTH MAIN ST MILPITAS R20A | MILPITAS | 74010862 | SANTA CLARA | N/A | TBD | N/A
MONTEREY ROAD, MORGAN HILL | MORGAN HILL | 30618077 | SANTA CLARA | 2372458.8 | 2017 | 2017-10-13
RENGSTORFF AVE | MOUNTAIN VIEW | 30431045 | SANTA CLARA | 2986716.5 | 2015 | 2015-07-14
CALIFORNIA ST, MOUNTAIN VIEW | MOUNTAIN VIEW | 31081035 | SANTA CLARA | N/A | TBD | N/A
GEP VTA PHASE 1 R20A C-225 SAN JOSE | SAN JOSE | 30126235 | SANTA CLARA | 720044.6 | 2005 | 2007-03-24
C:GEP VTA PHASE 4 R20A C-225 SAN JOSE | SAN JOSE | 30140824 | SANTA CLARA | 1045126.85 | 2006 | 2007-03-24
SANTA CLARA CIVIC CENTER, SAN JOSE | SAN JOSE | 30222768 | SANTA CLARA | 647311.72 | 2008 | 2009-03-17
JACKSON/TAYLOR | SAN JOSE | 30354298 | SANTA CLARA | 4135751.22 | 2014 | 2015-01-15
CIVIC CENTER, PHASE 2 | SAN JOSE | 30415847 | SANTA CLARA | 2174100.57 | 2007 | 2008-02-15
GUADALUPE GARDENS, PH 1 | SAN JOSE | 30514516 | SANTA CLARA | 953720 | 2013 | 2014-02-28
MARKET/ALMADEN | SAN JOSE | 30567652 | SANTA CLARA | 4693194 | 2013 | 2014-02-28
PARK/NAGLEE | SAN JOSE | 30575460 | SANTA CLARA | 6472553.42 | 2015 | 2015-10-06
GUADALUPE GARDENS, PH 2 | SAN JOSE | 30576193 | SANTA CLARA | 4992592.56 | 2012 | 2012-09-13
DELMAS & PARK AVE | SAN JOSE | 30648282 | SANTA CLARA | 5742948.96 | 2016 | 2016-04-09
TULLY RD | SAN JOSE | 30650716 | SANTA CLARA | 3105826.78 | 2015 | 2016-01-13
WHITE ROAD, SAN JOSE | SAN JOSE | 30677172 | SANTA CLARA | N/A | TBD | N/A
ABORN RD | SAN JOSE | 30702293 | SANTA CLARA | 1772317.3 | 2016 | 2016-04-09
COLEMAN AVE PH1 | SAN JOSE | 30776251 | SANTA CLARA | 432091.19 | 2015 | 2015-10-06
COLEMAN AVE PH 2, SAN JOSE | SAN JOSE | 30776258 | SANTA CLARA | N/A | TBD | N/A
EVERGREEN PARK | SAN JOSE | 30920922 | SANTA CLARA | 2794110.84 | 2015 | 2016-01-13
LINCOLN AVE, SAN JOSE | SAN JOSE | 31085930 | SANTA CLARA | N/A | TBD | N/A
KIRK PARK, SAN JOSE | SAN JOSE | 31085931 | SANTA CLARA | N/A | TBD | N/A
MONTEREY ROAD, SAN JOSE | SAN JOSE | 74001554 | SANTA CLARA | N/A | TBD | N/A
CAMDEN AVE | SAN JOSE, SANTA CLARA COUNTY | 30647467 & 30071453 | SANTA CLARA | 3523227.04 | 2016 | 2016-04-09
ALMADEN EXPWY, SANTA CLARA COUNTY | SANTA CLARA COUNTY | 30767366 | SANTA CLARA | N/A | TBD | N/A
LINCOLN PARK LOS ALTOS R20A | SANTA CLARA COUNTY | 74011843 | SANTA CLARA | N/A | TBD | N/A
MONTAGUE EXPWY MILPITAS R20A | SANTA CLARA COUNTY, MILPITAS | 31330811 | SANTA CLARA | N/A | TBD | N/A
HOLLENBECK, RULE 20A | SUNNYVALE | 30260633 | SANTA CLARA | 143963.1 | 2005 | 2007-03-24
FAIR OAKS AVE, SUNNYVALE | SUNNYVALE | 30721972 | SANTA CLARA | 4906621.16 | 2017 | 2017-10-13
WOLFE ROAD, SUNNYVALE | SUNNYVALE | 74001551 | SANTA CLARA | N/A | TBD | N/A
C:CAPITOLA RULE 20A *CANC | CAPITOLA | 30125135 | SANTA CRUZ | 11817.22 | N/A | 2007-03-24
MONTEREY AVE & BAY AVE, CAPITOLA | CAPITOLA | 74013860 | SANTA CRUZ | N/A | TBD | N/A
C:GEPC MISSION HILL RULE 20A,SANTA CRUZ | SANTA CRUZ | 30070717 | SANTA CRUZ | 8838 | N/A | 2007-03-24
MISSION ST - PHASE 1, RULE 20A | SANTA CRUZ | 30136844 | SANTA CRUZ | 3091119.09 | 2006 | 2007-03-24
MISSION ST, PH 2 | SANTA CRUZ | 30240320 | SANTA CRUZ | 3897340.59 | 2012 | 2012-09-13
RIVERSIDE AVE, SANTA CRUZ | SANTA CRUZ | 31218473 | SANTA CRUZ | N/A | TBD | N/A
MISSION ST PH 3, SANTA CRUZ | SANTA CRUZ | 74001550 | SANTA CRUZ | N/A | TBD | N/A
CITY OF DAVENPORT | SANTA CRUZ COUNTY | 30071191 | SANTA CRUZ | 1594312.61 | 2007 | 2007-07-31
STATE PARK DRIVE, SEA CLIFF | SANTA CRUZ COUNTY | 30261740 | SANTA CRUZ | 2023838.48 | 2018 | 2019-02-19
FREEDOM BLVD, WATSONVILLE | WATSONVILLE | 31001028 | SANTA CRUZ | 1368203.78 | 2018 | 2018-04-30
LAKE AVE, WATSONVILLE | WATSONVILLE | No Order | SANTA CRUZ | N/A | TBD | N/A
NORTH STREET, ANDERSON RULE 20A *CANC | ANDERSON | 30406410 | SHASTA | 542.12 | N/A | 2007-03-24
BALLS FERRY RD | ANDERSON | 30644207 | SHASTA | 3333295.26 | 2015 | 2015-10-06
EP-SHINGLETOWN RULE 20A | SHASTA COUNTY | 30050139 | SHASTA | 1003999.67 | 2005 | 2007-03-24
XP-SHINGLTWN RL 20A INSTALL UG WETLANDS | SHASTA COUNTY | 30280632 | SHASTA | 173635.43 | 2005 | 2007-03-24
SHASTA DAM BLVD, SHASTA LAKE | SHASTA COUNTY | 30302872 | SHASTA | 275197.53 | 2008 | 2008-08-18
PARKVIEW AVE, REDDING | SHASTA COUNTY | 30321001 | SHASTA | 709869.62 | 2007 | 2008-02-15
OC4 EP RULE 20A CYPRESS & HILLTOP REDING | SHASTA COUNTY | 30533492 | SHASTA | 193839 | 2010 | 2011-03-16
MAIN STREET, SIERRA CITY | SIERRA COUNTY | No Order | SIERRA | N/A | TBD | N/A
EAST A STREET, DIXON | DIXON | No Order | SOLANO | N/A | TBD | N/A
C:GEP PURGE CABLE, N. TEXAS/ TRAVIS, R20 | FAIRFIELD | 30025922 | SOLANO | 1451380.782 | 2005 | 2007-03-24
TRAVIS BLVD, FAIRFIELD | FAIRFIELD | 30674762 | SOLANO | N/A | N/A | N/A
MAIN ST PH 2, RIO VISTA | RIO VISTA | No Order | SOLANO | N/A | TBD | N/A
MASON ST. (DAVIS-MERCHANT) | VACAVILLE | 30155323 | SOLANO | 576142.84 | 2007 | 2007-07-31
LOVERS LANE | VACAVILLE | 30288220 | SOLANO | 258582.97 | 2007 | 2007-07-31
*CANC* R4 VACAVILLE / BUCK AVE RULE 20A | VACAVILLE | 30550905 | SOLANO | 93924 | N/A | 2010-08-26
VANDEN RD | VACAVILLE | 31038742 | SOLANO | 708335.83 | 2016 | 2016-07-20
WILSON AVE PHII, RULE 20, VALLEJO | VALLEJO | 30213683 | SOLANO | 491493 | 2010 | 2010-08-26
SACRAMENTO ST, VALLEJO | VALLEJO | No Order | SOLANO | N/A | TBD | N/A
HEALDSBURG AVE BRIDGE | HEALDSBURG | 31051957 | SONOMA | 81345.13 | 2016 | 2016-04-09
BODEGA AVE | PETALUMA | 30395065 | SONOMA | 2622095.72 | 2012 | 2012-09-13
PETALMA BLVD NORTH | PETALUMA | 30692249 | SONOMA | 1767994.75 | 2015 | 2015-07-14
BODEGA AVE PH 2, PETALUMA | PETALUMA | 30762469 | SONOMA | N/A | TBD | N/A
ADRIAN DRIVE, ROHNERT PARK | ROHNERT PARK | 30247819 | SONOMA | N/A | TBD | N/A
SNYDER LANE | ROHNERT PARK | 31068171 | SONOMA | 991808.18 | 2016 | 2016-04-09
E COTATI AVE ROHNERT PARK R20A | ROHNERT PARK | 35051448 | SONOMA | N/A | TBD | N/A
STONY PT RD | SANTA ROSA | 30256639 | SONOMA | 8853447.51 | 2016 | 2017-01-13
WEST STEELE LANE | SANTA ROSA | 30282030 | SONOMA | 1019413.14 | 2007 | 2007-07-31
*CANC* E-STONY POINT RULE 20A, SANT*CANC | SANTA ROSA | 30312923 | SONOMA | 5086 | N/A | 2007-07-31
R20A - FULTON RD SANTA ROSA | SANTA ROSA, SONOMA COUNTY | 74013528 | SONOMA | N/A | TBD | N/A
STATE HWY 1 - JENNER | SONOMA COUNTY | 30069477 | SONOMA | 1007477.46 | 2007 | 2007-07-31
HIGHWAY 12, PH 3 | SONOMA COUNTY | 30069479 | SONOMA | 7371678 | 2013 | 2014-02-28
FREESTONE, SONOMA COUNTY | SONOMA COUNTY | 30256790 | SONOMA | N/A | TBD | N/A
GRATON RD, SONOMA COUNTY | SONOMA COUNTY | 30766668 | SONOMA | N/A | TBD | N/A
SALMON CREEK, SONOMA COUNTY | SONOMA COUNTY | No Order | SONOMA | N/A | TBD | N/A
BROADWAY | SONOMA, SONOMA COUNTY | 30302192 | SONOMA | 2141796.78 | 2012 | 2012-09-13
CITY OF NEWMAN, PH 1 | NEWMAN | 30579877 | STANISLAUS | 312071.45 | 2009 | 2009-07-29
KERN TO MERCED PH 2, NEWMAN | NEWMAN | 30657421 | STANISLAUS | N/A | N/A | N/A
KERN TO MERCED PH 3, NEWMAN | NEWMAN | 30709856 | STANISLAUS | N/A | N/A | N/A
HWY 108 "F" OAKDALE | OAKDALE | 30339515 | STANISLAUS | 1370320.68 | 2007 | 2007-07-31
SOUTH YOSEMITE AVE, OAKDALE | OAKDALE | 31059557 | STANISLAUS | 1735838.73 | 2017 | 2017-07-17
CITY OF RIVERBANK | RIVERBANK, STANISLAUS COUNTY | 30406568 | STANISLAUS | 3010033.41 | 2014 | 2015-01-15
LIVE OAK BLVD, LIVE OAK | LIVE OAK | 74015720 | SUTTER | N/A | TBD | N/A
BARRY RD, SUTTER COUNTY | SUTTER COUNTY | 31242522 | SUTTER | N/A | TBD | N/A
BRIDGE ST, YUBA CITY | YUBA CITY | 30177662 | SUTTER | 6763.46 | N/A | 2008-02-15
WALTON AVE | YUBA CITY | 30348512 | SUTTER | 207406.39 | 2007 | 2008-02-15
SECOND ST, YUBA CITY | YUBA CITY | 30918673 | SUTTER | 1726573 | 2018 | 2019-02-19
BRIDGE ST YUBA CITY R20A | YUBA CITY | 35131205 | SUTTER | N/A | TBD | N/A
SECOND ST YUBA CITY PH II | YUBA CITY | 74010531 | SUTTER | N/A | TBD | N/A
C:E PC R20A SOLANO/HOAG RD,CORNING | CORNING | 30024623 | TEHAMA | 888092.1134 | 2005 | 2007-03-24
CITY PLAZA, CORNING | CORNING | No Order | TEHAMA | N/A | TBD | N/A
5TH STREET, TEHAMA | TEHAMA | No Order | TEHAMA | N/A | TBD | N/A
*CANC* HWY 99 LOS MOLINOS TEHAMA CNTY R2 | TEHAMA COUNTY | 30258465 | TEHAMA | N/A | N/A | N/A
HWY 99 EAST, TEHAMA COUNTY | TEHAMA COUNTY | No Order | TEHAMA | N/A | TBD | N/A
TRANSIT CENTER, DINUBA | DINUBA | 30959525 | TULARE | N/A | TBD | N/A
COLUMBIA | TUOLUMNE COUNTY | 30563720 | TUOLOMNE | 2053328 | 2013 | 2014-02-28
TUOLUMNE TOWNSITE, TUOLUMNE COUNTY | TUOLUMNE COUNTY | No Order | TUOLOMNE | N/A | TBD | N/A
3RD ST PH 1 | DAVIS | 30917227 | YOLO | 1717193.27 | 2016 | 2016-04-09
C:EP JEFFERSON RULE 20A, WEST SAC | WEST SACRAMENTO | 30102918 | YOLO | 909130.76 | 2006 | 2007-03-24
3RD AND C STREETS | WEST SACRAMENTO | 30178098 | YOLO | 830239.12 | 2007 | 2007-07-31
5TH STREET | WEST SACRAMENTO | 30614607 | YOLO | 1835344.56 | 2012 | 2012-09-13
NEWT'S EXPRESSWAY WINTERS R20A | WINTERS | 35051251 | YOLO | N/A | TBD | N/A
EAST STREET | WOODLAND | 30418943 | YOLO | 221351.79 | 2007 | 2008-02-15
EAST ST | WOODLAND | 30616114 | YOLO | 1292764.29 | 2015 | 2015-07-14
*CANC* DEAD CAT ALLEY | WOODLAND | 30864665 | YOLO | 6681.85 | N/A | 2014-02-28
COUNTY ROADS 98 AND 27 | YOLO COUNTY | 30762587 | YOLO | 1891504.37 | 2015 | 2015-07-14
*CANC* EP YUBA COUNTY RULE 20A MCGO*CANC | YUBA COUNTY | 30237025 | YUBA | N/A | N/A | N/A
OLIVEHURST AVE, YUBA CNTY | YUBA COUNTY | 30959427 | YUBA | 4616250.25 | 2017 | 2017-04-14
Note on F3: Note: "Value of Work Credits (in USD) used for the Project" from Detailed Project Information tab
Note on G3: Note: "Project Completed" from Detailed Project Information tab
Note on H3: Note: "Date Rule 20A Work Credits are Redeemed" from Detailed Project Information tab

## Historical Community Level Data
Pacific Gas and Electric Company data for R.17-05-010 submitted on 4/17/2020; Note: Data provided for 2007-2019 only. Data for 2005-2006 will require additional analysis.
(I. h) Historical Community Data Since Program Inception
Rule 20A Community | Year | Number of work credits at beginning of year | The Rule 20A work credit allocation amount (per allocation rule) | Budgeted amount (internally at IOU) | Number of work credits added through borrowing forward from Utility | Number of work credits added through trading with another community | Breakdown of trading amounts by trading partners | Amount of work credits spent | Value of total projects in a community completed for the year (estimated if not known) | Ending number of credits | If there is a negative balance, please explain why
| Date | Nominal $ | Nominal $ | Nominal $ | Nominal $ | Nominal $ | Nominal $ & (Name) | Nominal $ | Nominal $ | Nominal $ | Explanation
Alameda County
Alameda County | 2019 | 6899981.96 | 505472 | N/A | 0 | 0 |  | 0 | 0 | 7405453.96
Alameda County | 2018 | 6395295.96 | 504686 | N/A | 0 | 0 |  | 0 | 0 | 6899981.96
Alameda County | 2017 | 5890248.96 | 505047 | N/A | 0 | 0 |  | 0 | 0 | 6395295.96
Alameda County | 2016 | 14007317.12 | 501297 | N/A | 0 | 0 |  | 8618365.16 | 8618365.16 | 5890248.96
Alameda County | 2015 | 13501208.12 | 506109 | N/A | 0 | 0 |  | 0 | 0 | 14007317.12
Alameda County | 2014 | 13026607 | 508753 | N/A | 0 | 0 |  | 34151.88 | 0 | 13501208.12
Alameda County | 2013 | 15881112 | 506576 | N/A | 0 | 0 |  | 3361081 | 3361081 | 13026607
Alameda County | 2012 | 15366249 | 514863 | N/A | 0 | 0 |  | 0 | 0 | 15881112
Alameda County | 2011 | 14848530 | 517719 | N/A | 0 | 0 |  | 0 | 0 | 15366249
Alameda County | 2010 | 13740070 | 1108460 | N/A | 0 | 0 |  | 0 | 0 | 14848530
Alameda County | 2009 | 12634328 | 1105742 | N/A | 0 | 0 |  | 0 | 0 | 13740070
Alameda County | 2008 | 11522412 | 1105958 | N/A | 0 | 0 |  | 0 | 0 | 12634328
Alameda County | 2007 | 10416419 | 1105993 | N/A | 0 | 0 |  | 0 | 0 | 11522412
Albany | 2019 | 3109233 | 71447 | N/A | 0 | 0 |  | 3100967.09 | 3100967.09 | 79712.91
Albany | 2018 | 3037563 | 71670 | N/A | 0 | 0 |  | 0 | 0 | 3109233
Albany | 2017 | 2965751 | 71812 | N/A | 0 | 0 |  | 0 | 0 | 3037563
Albany | 2016 | 2894483 | 71268 | N/A | 0 | 0 |  | 0 | 0 | 2965751
Albany | 2015 | 2822475 | 72008 | N/A | 0 | 0 |  | 0 | 0 | 2894483
Albany | 2014 | 2750091 | 72384 | N/A | 0 | 0 |  | 0 | 0 | 2822475
Albany | 2013 | 2678425 | 71666 | N/A | 0 | 0 |  | 0 | 0 | 2750091
Albany | 2012 | 2606864 | 71561 | N/A | 0 | 0 |  | 0 | 0 | 2678425
Albany | 2011 | 2535211 | 71653 | N/A | 0 | 0 |  | 0 | 0 | 2606864
Albany | 2010 | 2381220 | 153991 | N/A | 0 | 0 |  | 0 | 0 | 2535211
Albany | 2009 | 2227277 | 153943 | N/A | 0 | 0 |  | 0 | 0 | 2381220
Albany | 2008 | 2072187 | 154256 | N/A | 0 | 0 |  | 0 | 0 | 2227277
Albany | 2007 | 1917668 | 154519 | N/A | 0 | 0 |  | 0 | 0 | 2072187
Berkeley | 2019 | 8477016.9 | 532078 | N/A | 0 | 0 |  | -360 | -360 | 9009454.9
Berkeley | 2018 | 7947444.9 | 529572 | N/A | 0 | 0 |  | 0 | 0 | 8477016.9
Berkeley | 2017 | 7418132.9 | 529312 | N/A | 0 | 0 |  | 0 | 0 | 7947444.9
Berkeley | 2016 | 6894244.9 | 523888 | N/A | 0 | 0 |  | 0 | 0 | 7418132.9
Berkeley | 2015 | 6365850.9 | 528394 | N/A | 0 | 0 |  | 0 | 0 | 6894244.9
Berkeley | 2014 | 5835482.9 | 530368 | N/A | 0 | 0 |  | 0 | 0 | 6365850.9
Berkeley | 2013 | 5308775.9 | 526707 | N/A | 0 | 0 |  | 0 | 0 | 5835482.9
Berkeley | 2012 | 9899350 | 527648 | N/A | 0 | 0 |  | 5118222.1 | 5118222.1 | 5308775.9
Berkeley | 2011 | 9371413 | 527937 | N/A | 0 | 0 |  | 0 | 0 | 9899350
Berkeley | 2010 | 8192658 | 1178755 | N/A | 0 | 0 |  | 0 | 0 | 9371413
Berkeley | 2009 | 7015125 | 1177533 | N/A | 0 | 0 |  | 0 | 0 | 8192658
Berkeley | 2008 | 5829176 | 1179826 | N/A | 0 | 0 |  | 0 | 0 | 7015125
Berkeley | 2007 | 4648430 | 1180746 | N/A | 0 | 0 |  | 0 | 0 | 5829176
Dublin | 2019 | 1560229.8 | 126524 | N/A | 0 | 0 |  | 0 | 0 | 1686753.8
Dublin | 2018 | 1437000.8 | 123229 | N/A | 0 | 0 |  | 0 | 0 | 1560229.8
Dublin | 2017 | 566785.8 | 120215 | N/A | 0 | 750000 | $750,000 (Vallejo) | 0 | 0 | 1437000.8
Dublin | 2016 | 450522.8 | 116263 | N/A | 0 | 0 |  | 0 | 0 | 566785.8
Dublin | 2015 | 335481.8 | 115041 | N/A | 0 | 0 |  | 0 | 0 | 450522.8
Dublin | 2014 | 222797.8 | 112684 | N/A | 0 | 0 |  | 0 | 0 | 335481.8
Dublin | 2013 | 114081.8 | 108716 | N/A | 0 | 0 |  | 0 | 0 | 222797.8
Dublin | 2012 | 10401.8 | 103680 | N/A | 0 | 0 |  | 0 | 0 | 114081.8
Dublin | 2011 | -91881.2 | 102283 | N/A | 0 | 0 |  | 0 | 0 | 10401.8
Dublin | 2010 | -257357.2 | 165476 | N/A | 0 | 0 |  | 0 | 0 | -91881.2 | Within 5-year borrow
Dublin | 2009 | -422137.2 | 164780 | N/A | 0 | 0 |  | 0 | 0 | -257357.2 | Within 5-year borrow
Dublin | 2008 | 629438 | 162822 | N/A | 0 | 0 |  | 1215529.2 | 1215529.2 | -422137.2 | Within 5-year borrow
Dublin | 2007 | 468445 | 160993 | N/A | 0 | 0 |  | 0 | 0 | 629438
Emeryville | 2019 | 898178 | 41725 | N/A | 0 | 0 |  | 0 | 0 | 939903
Emeryville | 2018 | 856060 | 42118 | N/A | 0 | 0 |  | 0 | 0 | 898178
Emeryville | 2017 | 813658 | 42402 | N/A | 0 | 0 |  | 0 | 0 | 856060
Emeryville | 2016 | 771875 | 41783 | N/A | 0 | 0 |  | 0 | 0 | 813658
Emeryville | 2015 | 730533 | 41342 | N/A | 0 | 0 |  | 0 | 0 | 771875
Emeryville | 2014 | 689061 | 41472 | N/A | 0 | 0 |  | 0 | 0 | 730533
Emeryville | 2013 | 648420 | 40641 | N/A | 0 | 0 |  | 0 | 0 | 689061
Emeryville | 2012 | 610921 | 37499 | N/A | 0 | 0 |  | 0 | 0 | 648420
Emeryville | 2011 | 573108 | 37813 | N/A | 0 | 0 |  | 0 | 0 | 610921
Emeryville | 2010 | 503408 | 69700 | N/A | 0 | 0 |  | 0 | 0 | 573108
Emeryville | 2009 | 433950 | 69458 | N/A | 0 | 0 |  | 0 | 0 | 503408
Emeryville | 2008 | 364127 | 69392 | N/A | 0 | 0 |  | 0 | 0 | 433950
Emeryville | 2007 | 295450 | 68677 | N/A | 0 | 0 |  | 0 | 0 | 364127
Fremont | 2019 | 7521429.85 | 492877 | N/A | 0 | 0 |  | 0 | 0 | 8014306.85
Fremont | 2018 | 7029867.85 | 491562 | N/A | 0 | 0 |  | 0 | 0 | 7521429.85
Fremont | 2017 | 6537995.85 | 491872 | N/A | 0 | 0 |  | 0 | 0 | 7029867.85
Fremont | 2016 | 6050123.85 | 487872 | N/A | 0 | 0 |  | 0 | 0 | 6537995.85
Fremont | 2015 | 9057994.66 | 493411 | N/A | 0 | 0 |  | 3501281.81 | 3501281.81 | 6050123.85
Fremont | 2014 | 8561922.66 | 496072 | N/A | 0 | 0 |  | 0 | 0 | 9057994.66
Fremont | 2013 | 8070285.66 | 491637 | N/A | 0 | 0 |  | 0 | 0 | 8561922.66
Fremont | 2012 | 7578318.66 | 491967 | N/A | 0 | 0 |  | 0 | 0 | 8070285.66
Fremont | 2011 | 8353806.66 | 493216 | N/A | 0 | 0 |  | 1268704 | 1268704 | 7578318.66
Fremont | 2010 | 7388303.66 | 965503 | N/A | 0 | 0 |  | 0 | 0 | 8353806.66
Fremont | 2009 | 8340433.78 | 964651 | N/A | 0 | 0 |  | 1916781.12 | 1916781.12 | 7388303.66
Fremont | 2008 | 8457575.06 | 964928 | N/A | 0 | 0 |  | 1087762.28 | 1087762.28 | 8340433.78
Fremont | 2007 | 8705905 | 967916 | N/A | 0 | 0 |  | 1216245.94 | 1216245.94 | 8457575.06
Hayward | 2019 | 1215717.84 | 440614 | N/A | 0 | 38880 | Corcoran ($38,880) | 0 | 0 | 1695211.84
Hayward | 2018 | 241321.84 | 439434 | N/A | 0 | 38962 | Corcoran ($39,962) | 0 | 0 | 1215717.84
Hayward | 2017 | -236463.16 | 438884 | N/A | 0 | 38901 | $38,901 (Corcoran) | 0 | 0 | 241321.84
Hayward | 2016 | -837280.16 | 434681 | N/A | 0 | 38577 | $38,577 (Corcoran) | -127559 | -127559 | -236463.16 | Within 5-year borrow
Hayward | 2015 | -2369436.16 | 437779 | N/A | 0 | 1094377 | $1,094,377 (Corcoran) | 0 | 0 | -837280.16 | Within 5-year borrow
Hayward | 2014 | 9377260.21 | 440309 | N/A | 0 | 0 |  | 12187005.37 | 12187005.37 | -2369436.16 | Borrowed beyond 5 years (see AL 2445-E)
Hayward | 2013 | 8939655.21 | 437605 | N/A | 0 | 0 |  | 0 | 0 | 9377260.21
Hayward | 2012 | 11872216 | 438862 | N/A | 0 | 0 |  | 3371422.79 | 3371422.79 | 8939655.21
Hayward | 2011 | 11433686 | 438530 | N/A | 0 | 0 |  | 0 | 0 | 11872216
Hayward | 2010 | 10589994 | 843692 | N/A | 0 | 0 |  | 0 | 0 | 11433686
Hayward | 2009 | 9744877 | 845117 | N/A | 0 | 0 |  | 0 | 0 | 10589994
Hayward | 2008 | 8894281 | 845507 | N/A | 0 | 0 |  | 0 | 0 | 9744877
Hayward | 2007 | 8049446 | 844835 | N/A | 0 | 0 |  | 0 | 0 | 8894281
Livermore | 2019 | 3081884.36 | 213332 | N/A | 0 | 0 |  | 0 | 0 | 3295216.36
Livermore | 2018 | 4650597.36 | 213012 | N/A | 0 | 0 |  | 1781725 | 1781725 | 3081884.36
Livermore | 2017 | 4438310.36 | 212287 | N/A | 0 | 0 |  | 0 | 0 | 4650597.36
Livermore | 2016 | 4228593.36 | 209717 | N/A | 0 | 0 |  | 0 | 0 | 4438310.36
Livermore | 2015 | 4017607.36 | 210986 | N/A | 0 | 0 |  | 0 | 0 | 4228593.36
Livermore | 2014 | 3909270.41 | 212072 | N/A | 0 | 0 |  | 103735.05 | 0 | 4017607.36
Livermore | 2013 | 3699255.41 | 210015 | N/A | 0 | 0 |  | 0 | 0 | 3909270.41
Livermore | 2012 | 3489288.41 | 209967 | N/A | 0 | 0 |  | 0 | 0 | 3699255.41
Livermore | 2011 | 3269088.41 | 210200 | N/A | 0 | 0 |  | -10000 | -10000 | 3489288.41
Livermore | 2010 | 2892003.41 | 377085 | N/A | 0 | 0 |  | 0 | 0 | 3269088.41
Livermore | 2009 | 2515736.41 | 376267 | N/A | 0 | 0 |  | 0 | 0 | 2892003.41
Livermore | 2008 | 2136950.41 | 376366 | N/A | 0 | 0 |  | 0 | 0 | 2515736.41
Livermore | 2007 | 2397994 | 376829 | N/A | 0 | 0 |  | 637872.59 | 637872.59 | 2136950.41
Newark | 2019 | 2611127 | 112400 | N/A | 0 | 0 |  | 0 | 0 | 2723527
Newark | 2018 | 2500485 | 110642 | N/A | 0 | 0 |  | 0 | 0 | 2611127
Newark | 2017 | 2391839 | 108646 | N/A | 0 | 0 |  | 0 | 0 | 2500485
Newark | 2016 | 2284554 | 107285 | N/A | 0 | 0 |  | 0 | 0 | 2391839
Newark | 2015 | 2176288 | 108266 | N/A | 0 | 0 |  | 0 | 0 | 2284554
Newark | 2014 | 2067274 | 109014 | N/A | 0 | 0 |  | 0 | 0 | 2176288
Newark | 2013 | 1959186 | 108088 | N/A | 0 | 0 |  | 0 | 0 | 2067274
Newark | 2012 | 1850773 | 108413 | N/A | 0 | 0 |  | 0 | 0 | 1959186
Newark | 2011 | 1742135 | 108638 | N/A | 0 | 0 |  | 0 | 0 | 1850773
Newark | 2010 | 1526042 | 216093 | N/A | 0 | 0 |  | 0 | 0 | 1742135
Newark | 2009 | 1310046 | 215996 | N/A | 0 | 0 |  | 0 | 0 | 1526042
Newark | 2008 | 1092205 | 216574 | N/A | 0 | 0 |  | 0 | 0 | 1310046
Newark | 2007 | 875011 | 217194 | N/A | 0 | 0 |  | 0 | 0 | 1092205
Oakland | 2019 | 22065101.38 | 1692256 | N/A | 0 | 0 |  | 0 | 0 | 23757357.38
Oakland | 2018 | 20372497.38 | 1692604 | N/A | 0 | 0 |  | 0 | 0 | 22065101.38
Oakland | 2017 | 32416859.5 | 1695700 | N/A | 0 | 0 |  | 13740062.12 | 13740062.12 | 20372497.38
Oakland | 2016 | 30734859.5 | 1682000 | N/A | 0 | 0 |  | 0 | 0 | 32416859.5
Oakland | 2015 | 29037987.5 | 1696872 | N/A | 0 | 0 |  | 0 | 0 | 30734859.5
Oakland | 2014 | 27335230.5 | 1702757 | N/A | 0 | 0 |  | 0 | 0 | 29037987.5
Oakland | 2013 | 25638825.5 | 1696405 | N/A | 0 | 0 |  | 0 | 0 | 27335230.5
Oakland | 2012 | 37246663 | 1696854 | N/A | 0 | 0 |  | 13304691.5 | 13304691.5 | 25638825.5
Oakland | 2011 | 35546799 | 1698864 | N/A | 0 | 0 |  | -1000 | -1000 | 37246663
Oakland | 2010 | 31937902 | 3608897 | N/A | 0 | 0 |  | 0 | 0 | 35546799
Oakland | 2009 | 28331581 | 3606321 | N/A | 0 | 0 |  | 0 | 0 | 31937902
Oakland | 2008 | 24708126 | 3603831 | N/A | 0 | 0 |  | 0 | 0 | 28331581
Oakland | 2007 | 21099441 | 3608685 | N/A | 0 | 0 |  | 0 | 0 | 24708126
Piedmont | 2019 | 707516 | 37038 | N/A | 0 | 0 |  | 0 | 0 | 744554
Piedmont | 2018 | 670604 | 36912 | N/A | 0 | 0 |  | 0 | 0 | 707516
Piedmont | 2017 | 633728 | 36876 | N/A | 0 | 0 |  | 0 | 0 | 670604
Piedmont | 2016 | 597144 | 36584 | N/A | 0 | 0 |  | 0 | 0 | 633728
Piedmont | 2015 | 414093 | 37026 | N/A | 0 | 0 |  | 0 | 0 | 597144
Piedmont | 2014 | 376884 | 37209 | N/A | 0 | 0 |  | 0 | 0 | 414093
Piedmont | 2013 | 340158 | 36726 | N/A | 0 | 0 |  | 0 | 0 | 376884
Piedmont | 2012 | 303064 | 37094 | N/A | 0 | 0 |  | 0 | 0 | 340158
Piedmont | 2011 | 600372 | 37266 | N/A | 0 | 0 |  | 0 | 0 | 303064
Piedmont | 2010 | 512949 | 87423 | N/A | 0 | 0 |  | 0 | 0 | 600372
Piedmont | 2009 | 425576 | 87373 | N/A | 0 | 0 |  | 0 | 0 | 512949
Piedmont | 2008 | 465873 | 87572 | N/A | 0 | 0 |  | 0 | 0 | 425576
Piedmont | 2007 | 378057 | 87816 | N/A | 0 | 0 |  | 0 | 0 | 465873
Pleasanton | 2019 | 287947.97 | 147861 | N/A | 0 | 0 |  | 0 | 0 | 435808.97
Pleasanton | 2018 | 1821088.23 | 147965 | N/A | 0 | 0 |  | 1681105.26 | 1681105.26 | 287947.97
Pleasanton | 2017 | 1675899.23 | 145189 | N/A | 0 | 0 |  | 0 | 0 | 1821088.23
Pleasanton | 2016 | 1532933.23 | 142966 | N/A | 0 | 0 |  | 0 | 0 | 1675899.23
Pleasanton | 2015 | 1389324.23 | 143609 | N/A | 0 | 0 |  | 0 | 0 | 1532933.23
Pleasanton | 2014 | 1244780.23 | 144544 | N/A | 0 | 0 |  | 0 | 0 | 1389324.23
Pleasanton | 2013 | 1101315.23 | 143465 | N/A | 0 | 0 |  | 0 | 0 | 1244780.23
Pleasanton | 2012 | 957653.23 | 143662 | N/A | 0 | 0 |  | 0 | 0 | 1101315.23
Pleasanton | 2011 | 813749.23 | 143904 | N/A | 0 | 0 |  | 0 | 0 | 957653.23
Pleasanton | 2010 | 557403.23 | 256346 | N/A | 0 | 0 |  | 0 | 0 | 813749.23
Pleasanton | 2009 | 2936129 | 255985 | N/A | 0 | 0 |  | 2634710.77 | 2634710.77 | 557403.23
Pleasanton | 2008 | 2678051 | 256409 | N/A | 0 | 0 |  | 0 | 0 | 2936129
Pleasanton | 2007 | 2420945 | 257106 | N/A | 0 | 0 |  | 0 | 0 | 2678051
San Leandro | 2019 | 6888045.2 | 312628 | N/A | 0 | 0 |  | 0 | 0 | 7200673.2
San Leandro | 2018 | 6576712.2 | 311333 | N/A | 0 | 0 |  | 0 | 0 | 6888045.2
San Leandro | 2017 | 6264624.2 | 312088 | N/A | 0 | 0 |  | 0 | 0 | 6576712.2
San Leandro | 2016 | 5955173.2 | 309451 | N/A | 0 | 0 |  | 0 | 0 | 6264624.2
San Leandro | 2015 | 5642506.2 | 312667 | N/A | 0 | 0 |  | 0 | 0 | 5955173.2
San Leandro | 2014 | 8507596.03 | 314420 | N/A | 0 | 0 |  | 3179509.83 | 3179509.83 | 5642506.2
San Leandro | 2013 | 8196775.03 | 310821 | N/A | 0 | 0 |  | 0 | 0 | 8507596.03
San Leandro | 2012 | 7884378.03 | 312397 | N/A | 0 | 0 |  | 0 | 0 | 8196775.03
San Leandro | 2011 | 7562319.03 | 313059 | N/A | 0 | 0 |  | -9000 | -9000 | 7884378.03
San Leandro | 2010 | 6897756.03 | 664563 | N/A | 0 | 0 |  | 0 | 0 | 7562319.03
San Leandro | 2009 | 7223392 | 664029 | N/A | 0 | 0 |  | 989664.97 | 989664.97 | 6897756.03
San Leandro | 2008 | 6555278 | 664487 | N/A | 0 | 0 |  | 0 | 0 | 7223392
San Leandro | 2007 | 5889434 | 665844 | N/A | 0 | 0 |  | 0 | 0 | 6555278
Union City | 2019 | 850783.19 | 112069 | N/A | 0 | 0 |  | 0 | 0 | 962852.19
Union City | 2018 | 739619.19 | 111164 | N/A | 0 | 0 |  | 0 | 0 | 850783.19
Union City | 2017 | 3178210.79 | 110752 | N/A | 0 | 0 |  | 2549343.6 | 2549343.6 | 739619.19
Union City | 2016 | 3068126.79 | 110084 | N/A | 0 | 0 |  | 0 | 0 | 3178210.79
Union City | 2015 | 2956697.79 | 111429 | N/A | 0 | 0 |  | 0 | 0 | 3068126.79
Union City | 2014 | 2844409.79 | 112288 | N/A | 0 | 0 |  | 0 | 0 | 2956697.79
Union City | 2013 | 2732344.79 | 112065 | N/A | 0 | 0 |  | 0 | 0 | 2844409.79
Union City | 2012 | 2619936.79 | 112408 | N/A | 0 | 0 |  | 0 | 0 | 2732344.79
Union City | 2011 | 2508165.79 | 111771 | N/A | 0 | 0 |  | 0 | 0 | 2619936.79
Union City | 2010 | 2300078.79 | 208087 | N/A | 0 | 0 |  | 0 | 0 | 2508165.79
Union City | 2009 | 2093453.79 | 206625 | N/A | 0 | 0 |  | 0 | 0 | 2300078.79
Union City | 2008 | 1885302.79 | 206876 | N/A | 0 | 0 |  | 0 | 0 | 2093453.79
Union City | 2007 | 1678793.79 | 206509 | N/A | 0 | 0 |  | 0 | 0 | 1885302.79
Alameda County Total |  |  | 82926948 |  |  | 1999697 |  | 86452021.43 | 86314134.5
Alpine County
Alpine County | 2019 | 18358 | 2835 | N/A | 0 | 0 |  | 0 | 0 | 21193
Alpine County | 2018 | 15500 | 2858 | N/A | 0 | 0 |  | 0 | 0 | 18358
Alpine County | 2017 | 12629 | 2871 | N/A | 0 | 0 |  | 0 | 0 | 15500
Alpine County | 2016 | 9767 | 2862 | N/A | 0 | 0 |  | 0 | 0 | 12629
Alpine County | 2015 | 6868 | 2899 | N/A | 0 | 0 |  | 0 | 0 | 9767
Alpine County | 2014 | 3944 | 2924 | N/A | 0 | 0 |  | 0 | 0 | 6868
Alpine County | 2013 | 1071 | 2873 | N/A | 0 | 0 |  | 0 | 0 | 3944
Alpine County | 2012 | -1805 | 2876 | N/A | 0 | 0 |  | 0 | 0 | 1071
Alpine County | 2011 | -4651 | 2846 | N/A | 0 | 0 |  | 0 | 0 | -1805 | Within 5-year borrow
Alpine County | 2010 | -10213 | 5562 | N/A | 0 | 0 |  | 0 | 0 | -4651 | Within 5-year borrow
Alpine County | 2009 | -15774 | 5561 | N/A | 0 | 0 |  | 0 | 0 | -10213 | Within 5-year borrow
Alpine County | 2008 | -21310 | 5504 | N/A | 0 | 0 |  | 0 | 0 | -15774 | Within 5-year borrow
Alpine County | 2007 | -26809 | 5499 | N/A | 0 | 0 |  | 0 | 0 | -21310 | Within 5-year borrow
Alpine County Total |  |  | 47970 |  |  | 0 |  | 0 | 0
Amador County
Amador City | 2019 | 50097 | 1383 | N/A | 0 | 0 |  | 0 | 0 | 51480
Amador City | 2018 | 48715 | 1382 | N/A | 0 | 0 |  | 0 | 0 | 50097
Amador City | 2017 | 47339 | 1376 | N/A | 0 | 0 |  | 0 | 0 | 48715
Amador City | 2016 | 45972 | 1367 | N/A | 0 | 0 |  | 0 | 0 | 47339
Amador City | 2015 | 44609 | 1363 | N/A | 0 | 0 |  | 0 | 0 | 45972
Amador City | 2014 | 43231 | 1378 | N/A | 0 | 0 |  | 0 | 0 | 44609
Amador City | 2013 | 41856 | 1375 | N/A | 0 | 0 |  | 0 | 0 | 43231
Amador City | 2012 | 40487 | 1369 | N/A | 0 | 0 |  | 0 | 0 | 41856
Amador City | 2011 | 39175 | 1312 | N/A | 0 | 0 |  | 0 | 0 | 40487
Amador City | 2010 | 36186 | 2989 | N/A | 0 | 0 |  | 0 | 0 | 39175
Amador City | 2009 | 33231 | 2955 | N/A | 0 | 0 |  | 0 | 0 | 36186
Amador City | 2008 | 30254 | 2962 | N/A | 0 | 0 |  | 0 | 0 | 33231
Amador City | 2007 | 27284 | 2970 | N/A | 0 | 0 |  | 0 | 0 | 30254
Amador County | 2019 | 3429588.45 | 136849 | N/A | 0 | 0 |  | 0 | 0 | 3566437.45
Amador County | 2018 | 3293813.45 | 135775 | N/A | 0 | 0 |  | 0 | 0 | 3429588.45
Amador County | 2017 | 3158031.45 | 135782 | N/A | 0 | 0 |  | 0 | 0 | 3293813.45
Amador County | 2016 | 3023237.45 | 134794 | N/A | 0 | 0 |  | 0 | 0 | 3158031.45
Amador County | 2015 | 2887143.45 | 136094 | N/A | 0 | 0 |  | 0 | 0 | 3023237.45
Amador County | 2014 | 2750479.45 | 136664 | N/A | 0 | 0 |  | 0 | 0 | 2887143.45
Amador County | 2013 | 2613737.45 | 136742 | N/A | 0 | 0 |  | 0 | 0 | 2750479.45
Amador County | 2012 | 2476825.45 | 136912 | N/A | 0 | 0 |  | 0 | 0 | 2613737.45
Amador County | 2011 | 2311499.45 | 135025 | N/A | 0 | 0 |  | -30301 | -30301 | 2476825.45
Amador County | 2010 | 2061420.45 | 250079 | N/A | 0 | 0 |  | 0 | 0 | 2311499.45
Amador County | 2009 | 3003053 | 249599 | N/A | 0 | 0 |  | 1191231.55 | 1191231.55 | 2061420.45
Amador County | 2008 | 2751949 | 249551 | N/A | 0 | 0 |  | 0 | 0 | 3003053
Amador County | 2007 | 2503043 | 248906 | N/A | 0 | 0 |  | 0 | 0 | 2751949
Ione | 2019 | 518559 | 14373 | N/A | 0 | 0 |  | 0 | 0 | 532932
Ione | 2018 | 504429 | 14130 | N/A | 0 | 0 |  | 0 | 0 | 518559
Ione | 2017 | 490444 | 13985 | N/A | 0 | 0 |  | 0 | 0 | 504429
Ione | 2016 | 476647 | 13797 | N/A | 0 | 0 |  | 0 | 0 | 490444
Ione | 2015 | 462743 | 13904 | N/A | 0 | 0 |  | 0 | 0 | 476647
Ione | 2014 | 448741 | 14002 | N/A | 0 | 0 |  | 0 | 0 | 462743
Ione | 2013 | 435634 | 13107 | N/A | 0 | 0 |  | 0 | 0 | 448741
Ione | 2012 | 422764 | 12870 | N/A | 0 | 0 |  | 0 | 0 | 435634
Ione | 2011 | 398746 | 14018 | N/A | 0 | 0 |  | 0 | 0 | 422764
Ione | 2010 | 374171 | 24575 | N/A | 0 | 0 |  | 0 | 0 | 398746
Ione | 2009 | 349614 | 24557 | N/A | 0 | 0 |  | 0 | 0 | 374171
Ione | 2008 | 324905 | 24548 | N/A | 0 | 0 |  | 0 | 0 | 349614
Ione | 2007 | 300462 | 24443 | N/A | 0 | 0 |  | 0 | 0 | 324905
Jackson | 2019 | 328889 | 21285 | N/A | 0 | 0 |  | 0 | 0 | 350174
Jackson | 2018 | 307509 | 21380 | N/A | 0 | 0 |  | 0 | 0 | 328889
Jackson | 2017 | 286128 | 21381 | N/A | 0 | 0 |  | 0 | 0 | 307509
Jackson | 2016 | 264894 | 21234 | N/A | 0 | 0 |  | 0 | 0 | 286128
Jackson | 2015 | 243574 | 21320 | N/A | 0 | 0 |  | 0 | 0 | 264894
Jackson | 2014 | 222342 | 21232 | N/A | 0 | 0 |  | 0 | 0 | 243574
Jackson | 2013 | 200793 | 21549 | N/A | 0 | 0 |  | 0 | 0 | 222342
Jackson | 2012 | 179217 | 21576 | N/A | 0 | 0 |  | 0 | 0 | 200793
Jackson | 2011 | 157022 | 22195 | N/A | 0 | 0 |  | 0 | 0 | 179217
Jackson | 2010 | 116001 | 41021 | N/A | 0 | 0 |  | 0 | 0 | 157022
Jackson | 2009 | 75027 | 40974 | N/A | 0 | 0 |  | 0 | 0 | 116001
Jackson | 2008 | 33731 | 41038 | N/A | 0 | 0 |  | 0 | 0 | 75027
Jackson | 2007 | -7246 | 40977 | N/A | 0 | 0 |  | 0 | 0 | 33731
Plymouth | 2019 | 223697 | 4452 | N/A | 0 | 0 |  | 0 | 0 | 228149
Plymouth | 2018 | 219377 | 4320 | N/A | 0 | 0 |  | 0 | 0 | 223697
Plymouth | 2017 | 215092 | 4285 | N/A | 0 | 0 |  | 0 | 0 | 219377
Plymouth | 2016 | 210770 | 4322 | N/A | 0 | 0 |  | 0 | 0 | 215092
Plymouth | 2015 | 206381 | 4389 | N/A | 0 | 0 |  | 0 | 0 | 210770
Plymouth | 2014 | 201943 | 4438 | N/A | 0 | 0 |  | 0 | 0 | 206381
Plymouth | 2013 | 196974 | 4969 | N/A | 0 | 0 |  | 0 | 0 | 201943
Plymouth | 2012 | 192033 | 4941 | N/A | 0 | 0 |  | 0 | 0 | 196974
Plymouth | 2011 | 187318 | 4715 | N/A | 0 | 0 |  | 0 | 0 | 192033
Plymouth | 2010 | 178616 | 8702 | N/A | 0 | 0 |  | 0 | 0 | 187318
Plymouth | 2009 | 169912 | 8704 | N/A | 0 | 0 |  | 0 | 0 | 178616
Plymouth | 2008 | 161157 | 8700 | N/A | 0 | 0 |  | 0 | 0 | 169912
Plymouth | 2007 | 152520 | 8637 | N/A | 0 | 0 |  | 0 | 0 | 161157
Sutter Creek | 2019 | 599981 | 14435 | N/A | 0 | 0 |  | 0 | 0 | 614416
Sutter Creek | 2018 | 585771 | 14210 | N/A | 0 | 0 |  | 0 | 0 | 599981
Sutter Creek | 2017 | 571504 | 14267 | N/A | 0 | 0 |  | 0 | 0 | 585771
Sutter Creek | 2016 | 557435 | 14069 | N/A | 0 | 0 |  | 0 | 0 | 571504
Sutter Creek | 2015 | 543292 | 14143 | N/A | 0 | 0 |  | 0 | 0 | 557435
Sutter Creek | 2014 | 529072 | 14220 | N/A | 0 | 0 |  | 0 | 0 | 543292
Sutter Creek | 2013 | 514992 | 14080 | N/A | 0 | 0 |  | 0 | 0 | 529072
Sutter Creek | 2012 | 500972 | 14020 | N/A | 0 | 0 |  | 0 | 0 | 514992
Sutter Creek | 2011 | 467221 | 14451 | N/A | 0 | 0 |  | 0 | 0 | 500972
Sutter Creek | 2010 | 439579 | 27642 | N/A | 0 | 0 |  | 0 | 0 | 467221
Sutter Creek | 2009 | 411979 | 27600 | N/A | 0 | 0 |  | 0 | 0 | 439579
Sutter Creek | 2008 | 384190 | 27622 | N/A | 0 | 0 |  | 0 | 0 | 411979
Sutter Creek | 2007 | 356621 | 27569 | N/A | 0 | 0 |  | 0 | 0 | 384190
Amador County Total |  |  | 3140326 |  |  | 0 |  | 1160930.55 | 1160930.55
Butte County
Biggs | 2019 | 14498 | 214 | N/A | 0 | 0 |  | 0 | 0 | 14712
Biggs | 2018 | 14274 | 224 | N/A | 0 | 0 |  | 0 | 0 | 14498
Biggs | 2017 | 14060 | 214 | N/A | 0 | 0 |  | 0 | 0 | 14274
Biggs | 2016 | 13877 | 183 | N/A | 0 | 0 |  | 0 | 0 | 14060
Biggs | 2015 | 1103 | 12774 | N/A | 0 | 0 |  | 0 | 0 | 13877
Biggs | 2014 | 928 | 175 | N/A | 0 | 0 |  | 0 | 0 | 1103
Biggs | 2013 | 680 | 248 | N/A | 0 | 0 |  | 0 | 0 | 928
Biggs | 2012 | 442 | 238 | N/A | 0 | 0 |  | 0 | 0 | 680
Biggs | 2011 | 269 | 173 | N/A | 0 | 0 |  | 0 | 0 | 442
Biggs | 2010 | 135 | 134 | N/A | 0 | 0 |  | 0 | 0 | 269
Biggs | 2009 | 0 | 135 | N/A | 0 | 0 |  | 0 | 0 | 135
Butte County | 2019 | 6181535 | 416476 | N/A | 0 | 0 |  | 0 | 0 | 6598011
Butte County | 2018 | 8323821 | 413714 | N/A | 0 | 0 |  | 0 | 0 | 6181535
Butte County | 2017 | 11312069 | 413752 | N/A | 0 | 0 |  | 0 | 0 | 8323821
Butte County | 2016 | 13331657 | 422412 | N/A | 0 | 0 |  | 0 | 0 | 11312069
Butte County | 2015 | 12905548 | 426109 | N/A | 0 | 0 |  | 0 | 0 | 13331657
Butte County | 2014 | 12477967 | 427581 | N/A | 0 | 0 |  | 0 | 0 | 12905548
Butte County | 2013 | 12047167 | 430800 | N/A | 0 | 0 |  | 0 | 0 | 12477967
Butte County | 2012 | 11611940 | 435227 | N/A | 0 | 0 |  | 0 | 0 | 12047167
Butte County | 2011 | 11178010 | 433930 | N/A | 0 | 0 |  | 0 | 0 | 11611940
Butte County | 2010 | 10211826 | 966184 | N/A | 0 | 0 |  | 0 | 0 | 11178010
Butte County | 2009 | 10737096 | 968155 | N/A | 0 | 0 |  | 1493425 | 1493425 | 10211826
Butte County | 2008 | 9762950 | 969085 | N/A | 0 | 0 |  | 0 | 0 | 10737096
Butte County | 2007 | 9538069 | 981542 | N/A | 0 | 0 |  | 756661 | 756661 | 9762950
Chico | 2019 | 8102940.78 | 294692 | N/A | 0 | 0 |  | 0 | 0 | 8397632.78
Chico | 2018 | 7810274.78 | 292666 | N/A | 0 | 0 |  | 0 | 0 | 8102940.78
Chico | 2017 | 4960804.78 | 291470 | N/A | 0 | 2558000 | $1,163,000 (Butte County), $1,395,000 (Butte County) | 0 | 0 | 7810274.78
Chico | 2016 | 2231932.78 | 286872 | N/A | 0 | 2442000 | $2,442,000 (Butte County) | 0 | 0 | 4960804.78
Chico | 2015 | 1943258.78 | 288674 | N/A | 0 | 0 |  | 0 | 0 | 2231932.78
Chico | 2014 | 1653801.78 | 289457 | N/A | 0 | 0 |  | 0 | 0 | 1943258.78
Chico | 2013 | 1367079.78 | 286722 | N/A | 0 | 0 |  | 0 | 0 | 1653801.78
Chico | 2012 | 1085269.78 | 281810 | N/A | 0 | 0 |  | 0 | 0 | 1367079.78
Chico | 2011 | 804366.78 | 280903 | N/A | 0 | 0 |  | 0 | 0 | 1085269.78
Chico | 2010 | 401985.78 | 402381 | N/A | 0 | 0 |  | 0 | 0 | 804366.78
Chico | 2009 | 1963802.86 | 401986 | N/A | 0 | 0 |  | 1963803.08 | 1963803.08 | 401985.78
Chico | 2008 | 1557921.86 | 402637 | N/A | 0 | 0 |  | 0 | 0 | 1963802.86
Chico | 2007 | 1214063.22 | 389090 | N/A | 0 | 0 |  | 45231.36 | 45231.36 | 1557921.86
Oroville | 2019 | 1145212.16 | 78433 | N/A | 0 | 0 |  | 0 | 0 | 1223645.16
Oroville | 2018 | 1068431.16 | 76781 | N/A | 0 | 0 |  | 0 | 0 | 1145212.16
Oroville | 2017 | 991447.16 | 76984 | N/A | 0 | 0 |  | 0 | 0 | 1068431.16
Oroville | 2016 | 925739.16 | 65708 | N/A | 0 | 0 |  | 0 | 0 | 991447.16
Oroville | 2015 | 859264.16 | 66475 | N/A | 0 | 0 |  | 0 | 0 | 925739.16
Oroville | 2014 | 792532.16 | 66732 | N/A | 0 | 0 |  | 0 | 0 | 859264.16
Oroville | 2013 | 727551.16 | 64981 | N/A | 0 | 0 |  | 0 | 0 | 792532.16
Oroville | 2012 | 661775.16 | 65776 | N/A | 0 | 0 |  | 0 | 0 | 727551.16
Oroville | 2011 | 595957.16 | 65818 | N/A | 0 | 0 |  | 0 | 0 | 661775.16
Oroville | 2010 | 471555.16 | 124402 | N/A | 0 | 0 |  | 0 | 0 | 595957.16
Oroville | 2009 | 350622.16 | 120933 | N/A | 0 | 0 |  | 0 | 0 | 471555.16
Oroville | 2008 | 229629.16 | 120290 | N/A | 0 | 0 |  | 0 | 0 | 350622.16
Oroville | 2007 | 109377.16 | 120252 | N/A | 0 | 0 |  | 0 | 0 | 229629.16
Paradise | 2019 | 6000353.75 | 130293 | N/A | 0 | 0 |  | 0 | 0 | 6130646.75
Paradise | 2018 | 5314631.75 | 129722 | N/A | 0 | 556000 | Butte County ($556,000) | 0 | 0 | 6000353.75
Paradise | 2017 | 4341243.75 | 129388 | N/A | 0 | 844000 | $844,000 (Butte County) | 0 | 0 | 5314631.75
Paradise | 2016 | 4212758.75 | 128485 | N/A | 0 | 0 |  | 0 | 0 | 4341243.75
Paradise | 2015 | 4083126.75 | 129632 | N/A | 0 | 0 |  | 0 | 0 | 4212758.75
Paradise | 2014 | 3952800.75 | 130326 | N/A | 0 | 0 |  | 0 | 0 | 4083126.75
Paradise | 2013 | 3823465.75 | 129335 | N/A | 0 | 0 |  | 0 | 0 | 3952800.75
Paradise | 2012 | 3693920.75 | 129545 | N/A | 0 | 0 |  | 0 | 0 | 3823465.75
Paradise | 2011 | 3562906.75 | 131014 | N/A | 0 | 0 |  | 0 | 0 | 3693920.75
Paradise | 2010 | 3298553.75 | 264353 | N/A | 0 | 0 |  | 0 | 0 | 3562906.75
Paradise | 2009 | 3034453.75 | 264100 | N/A | 0 | 0 |  | 0 | 0 | 3298553.75
Paradise | 2008 | 2768495.75 | 264440 | N/A | 0 | 0 |  | 0 | 0 | 3034453.75
Paradise | 2007 | 3257053 | 264777 | N/A | 0 | 0 |  | 753334.25 | 753334.25 | 2768495.75
Butte County Total |  |  | 15248014 |  |  | 6400000 |  | 5012454.69 | 5012454.69
Calaveras County
Angels Camp | 2019 | -641510 | 16682 | N/A | 0 | 0 |  | 0 | 0 | -624828 | Exempt from 5-year borrow limit because it pre-dates 2001 CPUC decision to limit borrowing to 5 years.
Angels Camp | 2018 | -657971 | 16461 | N/A | 0 | 0 |  | 0 | 0 | -641510 | Exempt from 5-year borrow limit because it pre-dates 2001 CPUC decision to limit borrowing to 5 years.
Angels Camp | 2017 | -674389 | 16418 | N/A | 0 | 0 |  | 0 | 0 | -657971 | Exempt from 5-year borrow limit because it pre-dates 2001 CPUC decision to limit borrowing to 5 years.
Angels Camp | 2016 | -690660 | 16271 | N/A | 0 | 0 |  | 0 | 0 | -674389 | Exempt from 5-year borrow limit because it pre-dates 2001 CPUC decision to limit borrowing to 5 years.
Angels Camp | 2015 | -706743 | 16083 | N/A | 0 | 0 |  | 0 | 0 | -690660 | Exempt from 5-year borrow limit because it pre-dates 2001 CPUC decision to limit borrowing to 5 years.
Angels Camp | 2014 | -722918 | 16175 | N/A | 0 | 0 |  | 0 | 0 | -706743 | Exempt from 5-year borrow limit because it pre-dates 2001 CPUC decision to limit borrowing to 5 years.
Angels Camp | 2013 | -739159 | 16241 | N/A | 0 | 0 |  | 0 | 0 | -722918 | Exempt from 5-year borrow limit because it pre-dates 2001 CPUC decision to limit borrowing to 5 years.
Angels Camp | 2012 | -755414 | 16255 | N/A | 0 | 0 |  | 0 | 0 | -739159 | Exempt from 5-year borrow limit because it pre-dates 2001 CPUC decision to limit borrowing to 5 years.
Angels Camp | 2011 | -771985 | 16571 | N/A | 0 | 0 |  | 0 | 0 | -755414 | Exempt from 5-year borrow limit because it pre-dates 2001 CPUC decision to limit borrowing to 5 years.
Angels Camp | 2010 | -804015 | 32030 | N/A | 0 | 0 |  | 0 | 0 | -771985 | Exempt from 5-year borrow limit because it pre-dates 2001 CPUC decision to limit borrowing to 5 years.
Angels Camp | 2009 | -836032 | 32017 | N/A | 0 | 0 |  | 0 | 0 | -804015 | Exempt from 5-year borrow limit because it pre-dates 2001 CPUC decision to limit borrowing to 5 years.
Angels Camp | 2008 | -868289 | 32065 | N/A | 0 | 0 |  | 0 | 0 | -836032 | Exempt from 5-year borrow limit because it pre-dates 2001 CPUC decision to limit borrowing to 5 years.
Angels Camp | 2007 | -900293 | 32004 | N/A | 0 | 0 |  | 0 | 0 | -868289 | Exempt from 5-year borrow limit because it pre-dates 2001 CPUC decision to limit borrowing to 5 years.
Calaveras County | 2019 | 8828732.31 | 277561 | N/A | 0 | 0 |  | 0 | 0 | 9106293.31
Calaveras County | 2018 | 8553949.31 | 274783 | N/A | 0 | 0 |  | 0 | 0 | 8828732.31
Calaveras County | 2017 | 8279887.31 | 274062 | N/A | 0 | 0 |  | 0 | 0 | 8553949.31
Calaveras County | 2016 | 8005556.31 | 274331 | N/A | 0 | 0 |  | 0 | 0 | 8279887.31
Calaveras County | 2015 | 7728460.31 | 277096 | N/A | 0 | 0 |  | 0 | 0 | 8005556.31
Calaveras County | 2014 | 7450417.31 | 278043 | N/A | 0 | 0 |  | 0 | 0 | 7728460.31
Calaveras County | 2013 | 7172764.31 | 277653 | N/A | 0 | 0 |  | 0 | 0 | 7450417.31
Calaveras County | 2012 | 6894924.31 | 277840 | N/A | 0 | 0 |  | 0 | 0 | 7172764.31
Calaveras County | 2011 | 6617335.31 | 277589 | N/A | 0 | 0 |  | 0 | 0 | 6894924.31
Calaveras County | 2010 | 6126602.31 | 490733 | N/A | 0 | 0 |  | 0 | 0 | 6617335.31
Calaveras County | 2009 | 5636775.31 | 489827 | N/A | 0 | 0 |  | 0 | 0 | 6126602.31
Calaveras County | 2008 | 5144404.31 | 489184 | N/A | 0 | 0 |  | 0 | 0 | 5636775.31
Calaveras County | 2007 | 4656909.31 | 487495 | N/A | 0 | 0 |  | 0 | 0 | 5144404.31
Calaveras County Total |  |  | 4721470 |  |  | 0 |  | 0 | 0
Colusa County
Colusa | 2019 | 985580 | 23836 | N/A | 0 | 0 |  | 0 | 0 | 1009416
Colusa | 2018 | 961786 | 23794 | N/A | 0 | 0 |  | 0 | 0 | 985580
Colusa | 2017 | 937985 | 23801 | N/A | 0 | 0 |  | 0 | 0 | 961786
Colusa | 2016 | 914681 | 23304 | N/A | 0 | 0 |  | 0 | 0 | 937985
Colusa | 2015 | 891109 | 23572 | N/A | 0 | 0 |  | 0 | 0 | 914681
Colusa | 2014 | 867964 | 23145 | N/A | 0 | 0 |  | 0 | 0 | 891109
Colusa | 2013 | 844930 | 23034 | N/A | 0 | 0 |  | 0 | 0 | 867964
Colusa | 2012 | 821816 | 23114 | N/A | 0 | 0 |  | 0 | 0 | 844930
Colusa | 2011 | 798391 | 23425 | N/A | 0 | 0 |  | 0 | 0 | 821816
Colusa | 2010 | 751530 | 46861 | N/A | 0 | 0 |  | 0 | 0 | 798391
Colusa | 2009 | 704674 | 46856 | N/A | 0 | 0 |  | 0 | 0 | 751530
Colusa | 2008 | 657750 | 46656 | N/A | 0 | 0 |  | 0 | 0 | 704674
Colusa | 2007 | 611042 | 46708 | N/A | 0 | 0 |  | 0 | 0 | 657750
Colusa County | 2019 | 5148230 | 73469 | N/A | 0 | 0 |  | 0 | 0 | 5221699
Colusa County | 2018 | 3075821 | 72409 | N/A | 0 | 2000000 | Butte County ($2,000,000) | 0 | 0 | 5148230
Colusa County | 2017 | 3003332 | 72489 | N/A | 0 | 0 |  | 0 | 0 | 3075821
Colusa County | 2016 | 2931506 | 71826 | N/A | 0 | 0 |  | 0 | 0 | 3003332
Colusa County | 2015 | 2859543 | 71963 | N/A | 0 | 0 |  | 0 | 0 | 2931506
Colusa County | 2014 | 2787722 | 71821 | N/A | 0 | 0 |  | 0 | 0 | 2859543
Colusa County | 2013 | 2714823 | 72899 | N/A | 0 | 0 |  | 0 | 0 | 2787722
Colusa County | 2012 | 2642279 | 72544 | N/A | 0 | 0 |  | 0 | 0 | 2714823
Colusa County | 2011 | 2570890 | 71389 | N/A | 0 | 0 |  | 0 | 0 | 2642279
Colusa County | 2010 | 2423418 | 147472 | N/A | 0 | 0 |  | 0 | 0 | 2570890
Colusa County | 2009 | 2276803 | 146615 | N/A | 0 | 0 |  | 0 | 0 | 2423418
Colusa County | 2008 | 2129611 | 146385 | N/A | 0 | 0 |  | 0 | 0 | 2276803
Colusa County | 2007 | 1983566 | 146045 | N/A | 0 | 0 |  | 0 | 0 | 2129611
Williams | 2019 | 498789 | 13954 | N/A | 0 | 0 |  | 0 | 0 | 512743
Williams | 2018 | 484901 | 13888 | N/A | 0 | 0 |  | 0 | 0 | 498789
Williams | 2017 | 471072 | 13829 | N/A | 0 | 0 |  | 0 | 0 | 484901
Williams | 2016 | 457355 | 13717 | N/A | 0 | 0 |  | 0 | 0 | 471072
Williams | 2015 | 443438 | 13917 | N/A | 0 | 0 |  | 0 | 0 | 457355
Williams | 2014 | 429611 | 13827 | N/A | 0 | 0 |  | 0 | 0 | 443438
Williams | 2013 | 415835 | 13776 | N/A | 0 | 0 |  | 0 | 0 | 429611
Williams | 2012 | 402053 | 13782 | N/A | 0 | 0 |  | 0 | 0 | 415835
Williams | 2011 | 387602 | 14451 | N/A | 0 | 0 |  | 0 | 0 | 402053
Williams | 2010 | 362933 | 24669 | N/A | 0 | 0 |  | 0 | 0 | 387602
Williams | 2009 | 338318 | 24615 | N/A | 0 | 0 |  | 0 | 0 | 362933
Williams | 2008 | 313531 | 24622 | N/A | 0 | 0 |  | 0 | 0 | 338318
Williams | 2007 | 288905 | 24626 | N/A | 0 | 0 |  | 0 | 0 | 313531
Colusa County Total |  |  | 1859105 |  |  | 2000000 |  | 0 | 0
Contra Costa County
Antioch | 2019 | 582597.17 | 211767 | N/A | 0 | 0 |  | 0 | 0 | 794364.17
Antioch | 2018 | 371111.17 | 211486 | N/A | 0 | 0 |  | 0 | 0 | 582597.17
Antioch | 2017 | 158848.17 | 212263 | N/A | 0 | 0 |  | 0 | 0 | 371111.17
Antioch | 2016 | -50822.83 | 209671 | N/A | 0 | 0 |  | 0 | 0 | 158848.17
Antioch | 2015 | -263069.83 | 212247 | N/A | 0 | 0 |  | 0 | 0 | -50822.83 | Within 5-year borrow
Antioch | 2014 | 532611.38 | 213413 | N/A | 0 | 0 |  | 1009094.21 | 1009094.21 | -263069.83 | Within 5-year borrow
Antioch | 2013 | 2624052.38 | 212117 | N/A | 0 | 0 |  | 2303558 | 2303558 | 532611.38
Antioch | 2012 | 2412245.38 | 211807 | N/A | 0 | 0 |  | 0 | 0 | 2624052.38
Antioch | 2011 | 2200384.38 | 211861 | N/A | 0 | 0 |  | 0 | 0 | 2412245.38
Antioch | 2010 | 1911497.38 | 361191 | N/A | 0 | 0 |  | 72304 | 0 | 2200384.38
Antioch | 2009 | 1550630.38 | 360867 | N/A | 0 | 0 |  | 0 | 0 | 1911497.38
Antioch | 2008 | 1186963.38 | 361216 | N/A | 0 | 0 |  | 0 | 0 | 1550630.38
Antioch | 2007 | 824984.38 | 361979 | N/A | 0 | 0 |  | 0 | 0 | 1186963.38
Brentwood | 2019 | 1505931 | 97261 | N/A | 0 | 0 |  | 1476839.79 | 1476839.79 | 126352.21
Brentwood | 2018 | 1409678 | 96253 | N/A | 0 | 0 |  | 0 | 0 | 1505931
Brentwood | 2017 | 1315017 | 94661 | N/A | 0 | 0 |  | 0 | 0 | 1409678
Brentwood | 2016 | 1222370 | 92647 | N/A | 0 | 0 |  | 0 | 0 | 1315017
Brentwood | 2015 | 1130101 | 92269 | N/A | 0 | 0 |  | 0 | 0 | 1222370
Brentwood | 2014 | 1039164 | 90937 | N/A | 0 | 0 |  | 0 | 0 | 1130101
Brentwood | 2013 | 947478 | 91686 | N/A | 0 | 0 |  | 0 | 0 | 1039164
Brentwood | 2012 | 856314 | 91164 | N/A | 0 | 0 |  | 0 | 0 | 947478
Brentwood | 2011 | 763751 | 92563 | N/A | 0 | 0 |  | 0 | 0 | 856314
Brentwood | 2010 | 667258 | 96493 | N/A | 0 | 0 |  | 0 | 0 | 763751
Brentwood | 2009 | 570787 | 96471 | N/A | 0 | 0 |  | 0 | 0 | 667258
Brentwood | 2008 | 474506 | 95235 | N/A | 0 | 0 |  | 0 | 0 | 570787
Brentwood | 2007 | 381261 | 93245 | N/A | 0 | 0 |  | 0 | 0 | 474506
Clayton | 2019 | 340852 | 20588 | N/A | 0 | 0 |  | 0 | 0 | 361440
Clayton | 2018 | 320188 | 20664 | N/A | 0 | 0 |  | 0 | 0 | 340852
Clayton | 2017 | 299412 | 20776 | N/A | 0 | 0 |  | 0 | 0 | 320188
Clayton | 2016 | 278680 | 20732 | N/A | 0 | 0 |  | 0 | 0 | 299412
Clayton | 2015 | 257688 | 20992 | N/A | 0 | 0 |  | 0 | 0 | 278680
Clayton | 2014 | 236503 | 21185 | N/A | 0 | 0 |  | 0 | 0 | 257688
Clayton | 2013 | 215469 | 21034 | N/A | 0 | 0 |  | 0 | 0 | 236503
Clayton | 2012 | 194426 | 21043 | N/A | 0 | 0 |  | 0 | 0 | 215469
Clayton | 2011 | 173392 | 21034 | N/A | 0 | 0 |  | 0 | 0 | 194426
Clayton | 2010 | 143914 | 29478 | N/A | 0 | 0 |  | 0 | 0 | 173392
Clayton | 2009 | 114425 | 29489 | N/A | 0 | 0 |  | 0 | 0 | 143914
Clayton | 2008 | 84659 | 29521 | N/A | 0 | 0 |  | 0 | 0 | 114425
Clayton | 2007 | 55028 | 29631 | N/A | 0 | 0 |  | 0 | 0 | 84659
Concord | 2019 | 7932404.03 | 381309 | N/A | 0 | 0 |  | 0 | 0 | 8313713.03
Concord | 2018 | 7551743.03 | 380661 | N/A | 0 | 0 |  | 0 | 0 | 7932404.03
Concord | 2017 | 7169896.03 | 381847 | N/A | 0 | 0 |  | 0 | 0 | 7551743.03
Concord | 2016 | 6790504.03 | 379392 | N/A | 0 | 0 |  | 0 | 0 | 7169896.03
Concord | 2015 | 7874118.43 | 383477 | N/A | 0 | 0 |  | 1467091.4 | 1467091.4 | 6790504.03
Concord | 2014 | 7488318.43 | 385800 | N/A | 0 | 0 |  | 0 | 0 | 7874118.43
Concord | 2013 | 7106919.43 | 381399 | N/A | 0 | 0 |  | 0 | 0 | 7488318.43
Concord | 2012 | 6724304.43 | 382615 | N/A | 0 | 0 |  | 0 | 0 | 7106919.43
Concord | 2011 | 6340165.43 | 384139 | N/A | 0 | 0 |  | 0 | 0 | 6724304.43
Concord | 2010 | 7418329.43 | 772486 | N/A | 0 | 0 |  | 1850650 | 1850650 | 6340165.43
Concord | 2009 | 6645768.43 | 772561 | N/A | 0 | 0 |  | 0 | 0 | 7418329.43
Concord | 2008 | 5868232.43 | 773074 | N/A | 0 | 0 |  | 0 | 0 | 6645768.43
Concord | 2007 | 5092700.43 | 775532 | N/A | 0 | 0 |  | 0 | 0 | 5868232.43
Contra Costa County | 2019 | 16946499 | 525944 | N/A | 0 | 0 |  | 0 | 0 | 17472443
Contra Costa County | 2018 | 16421391 | 525108 | N/A | 0 | 0 |  | 0 | 0 | 16946499
Contra Costa County | 2017 | 15894798 | 526593 | N/A | 0 | 0 |  | 0 | 0 | 16421391
Contra Costa County | 2016 | 15371163 | 523635 | N/A | 0 | 0 |  | 0 | 0 | 15894798
Contra Costa County | 2015 | 14882810 | 527963 | N/A | 0 | 0 |  | 39610 | 39610 | 15371163
Contra Costa County | 2014 | 14352988 | 529822 | N/A | 0 | 0 |  | 0 | 0 | 14882810
Contra Costa County | 2013 | 13822561 | 530427 | N/A | 0 | 0 |  | 0 | 0 | 14352988
Contra Costa County | 2012 | 13292197 | 530364 | N/A | 0 | 0 |  | 0 | 0 | 13822561
Contra Costa County | 2011 | 12761003 | 531194 | N/A | 0 | 0 |  | 0 | 0 | 13292197
Contra Costa County | 2010 | 13863935 | 1157792 | N/A | 0 | 0 |  | 2260724 | 2260724 | 12761003
Contra Costa County | 2009 | 12706726 | 1157209 | N/A | 0 | 0 |  | 0 | 0 | 13863935
Contra Costa County | 2008 | 11542050 | 1158531 | N/A | 0 | 0 |  | 0 | 0 | 12706726
Contra Costa County | 2007 | 10382681 | 1159369 | N/A | 0 | 0 |  | 0 | 0 | 11542050
Danville | 2019 | 772968 | 95090 | N/A | 0 | 0 |  | 0 | 0 | 868058
Danville | 2018 | 677790 | 95178 | N/A | 0 | 0 |  | 0 | 0 | 772968
Danville | 2017 | 582428 | 95362 | N/A | 0 | 0 |  | 0 | 0 | 677790
Danville | 2016 | 487652 | 94776 | N/A | 0 | 0 |  | 0 | 0 | 582428
Danville | 2015 | 391584 | 96068 | N/A | 0 | 0 |  | 0 | 0 | 487652
Danville | 2014 | 295166 | 96418 | N/A | 0 | 0 |  | 0 | 0 | 391584
Danville | 2013 | 199004 | 96162 | N/A | 0 | 0 |  | 0 | 0 | 295166
Danville | 2012 | 102628 | 96376 | N/A | 0 | 0 |  | 0 | 0 | 199004
Danville | 2011 | 6330 | 96298 | N/A | 0 | 0 |  | 0 | 0 | 102628
Danville | 2010 | 2201300 | 177027 | N/A | 0 | 0 |  | 2371997 | 2371997 | 6330
Danville | 2009 | 2024312 | 176988 | N/A | 0 | 0 |  | 0 | 0 | 2201300
Danville | 2008 | 1846068 | 177126 | N/A | 0 | 0 |  | 0 | 0 | 2024312
Danville | 2007 | 1668362 | 177706 | N/A | 0 | 0 |  | 0 | 0 | 1846068
El Cerrito | 2019 | 2504925 | 115671 | N/A | 0 | 0 |  | 0 | 0 | 2620596
El Cerrito | 2018 | 2389500 | 115425 | N/A | 0 | 0 |  | 0 | 0 | 2504925
El Cerrito | 2017 | 2274240 | 115260 | N/A | 0 | 0 |  | 0 | 0 | 2389500
El Cerrito | 2016 | 2159836 | 114404 | N/A | 0 | 0 |  | 0 | 0 | 2274240
El Cerrito | 2015 | 2044484 | 115352 | N/A | 0 | 0 |  | 0 | 0 | 2159836
El Cerrito | 2014 | 1928391 | 116093 | N/A | 0 | 0 |  | 0 | 0 | 2044484
El Cerrito | 2013 | 1813427 | 114964 | N/A | 0 | 0 |  | 0 | 0 | 1928391
El Cerrito | 2012 | 1697558 | 115869 | N/A | 0 | 0 |  | 0 | 0 | 1813427
El Cerrito | 2011 | 1581495 | 116063 | N/A | 0 | 0 |  | 0 | 0 | 1697558
El Cerrito | 2010 | 1327253 | 254242 | N/A | 0 | 0 |  | 0 | 0 | 1581495
El Cerrito | 2009 | 1073219 | 254034 | N/A | 0 | 0 |  | 0 | 0 | 1327253
El Cerrito | 2008 | 817234 | 254635 | N/A | 0 | 0 |  | 0 | 0 | 1073219
El Cerrito | 2007 | 561901 | 255333 | N/A | 0 | 0 |  | 0 | 0 | 817234
Hercules | 2019 | 1074526 | 35749 | N/A | 0 | 0 |  | 0 | 0 | 1110275
Hercules | 2018 | 1038767 | 35759 | N/A | 0 | 0 |  | 0 | 0 | 1074526
Hercules | 2017 | 1002849 | 35918 | N/A | 0 | 0 |  | 0 | 0 | 1038767
Hercules | 2016 | 967675 | 35174 | N/A | 0 | 0 |  | 0 | 0 | 1002849
Hercules | 2015 | 932113 | 35562 | N/A | 0 | 0 |  | 0 | 0 | 967675
Hercules | 2014 | 899422 | 32691 | N/A | 0 | 0 |  | 0 | 0 | 932113
Hercules | 2013 | 866695 | 32727 | N/A | 0 | 0 |  | 0 | 0 | 899422
Hercules | 2012 | 833711 | 32984 | N/A | 0 | 0 |  | 0 | 0 | 866695
Hercules | 2011 | 800599 | 33112 | N/A | 0 | 0 |  | 0 | 0 | 833711
Hercules | 2010 | 738926 | 61673 | N/A | 0 | 0 |  | 0 | 0 | 800599
Hercules | 2009 | 677247 | 61679 | N/A | 0 | 0 |  | 0 | 0 | 738926
Hercules | 2008 | 615083 | 61778 | N/A | 0 | 0 |  | 0 | 0 | 677247
Hercules | 2007 | 553130 | 61953 | N/A | 0 | 0 |  | 0 | 0 | 615083
Lafayette | 2019 | 745356 | 103849 | N/A | 0 | 0 |  | 0 | 0 | 849205
Lafayette | 2018 | 641882 | 103474 | N/A | 0 | 0 |  | 0 | 0 | 745356
Lafayette | 2017 | 538075 | 103807 | N/A | 0 | 0 |  | 0 | 0 | 641882
Lafayette | 2016 | 435168 | 102907 | N/A | 0 | 0 |  | 0 | 0 | 538075
Lafayette | 2015 | 331329 | 103839 | N/A | 0 | 0 |  | 0 | 0 | 435168
Lafayette | 2014 | 227116 | 104213 | N/A | 0 | 0 |  | 0 | 0 | 331329
Lafayette | 2013 | 123702 | 103414 | N/A | 0 | 0 |  | 0 | 0 | 227116
Lafayette | 2012 | 20134 | 103568 | N/A | 0 | 0 |  | 0 | 0 | 123702
Lafayette | 2011 | 966151 | 103374 | N/A | 0 | 0 |  | 1049391 | 1049391 | 20134
Lafayette | 2010 | 739759 | 226392 | N/A | 0 | 0 |  | 0 | 0 | 966151
Lafayette | 2009 | 513563 | 226196 | N/A | 0 | 0 |  | 0 | 0 | 739759
Lafayette | 2008 | 285923 | 226433 | N/A | 0 | 0 |  | 0 | 0 | 513563
Lafayette | 2007 | 58797 | 227126 | N/A | 0 | 0 |  | 0 | 0 | 285923
Martinez | 2019 | 1321300.11 | 109801 | N/A | 0 | 0 |  | 0 | 0 | 1431101.11
Martinez | 2018 | 1211523.11 | 109777 | N/A | 0 | 0 |  | 0 | 0 | 1321300.11
Martinez | 2017 | 1101716.11 | 109807 | N/A | 0 | 0 |  | 0 | 0 | 1211523.11
Martinez | 2016 | 992602.11 | 109114 | N/A | 0 | 0 |  | 0 | 0 | 1101716.11
Martinez | 2015 | 2710810 | 110126 | N/A | 0 | 0 |  | 1828333.89 | 1828333.89 | 992602.11
Martinez | 2014 | 2600234 | 110576 | N/A | 0 | 0 |  | 0 | 0 | 2710810
Martinez | 2013 | 2491183 | 109051 | N/A | 0 | 0 |  | 0 | 0 | 2600234
Martinez | 2012 | 2381536 | 109647 | N/A | 0 | 0 |  | 0 | 0 | 2491183
Martinez | 2011 | 2186347 | 110600 | N/A | 0 | 0 |  | -84589 | -84589 | 2381536
Martinez | 2010 | 1975767 | 210580 | N/A | 0 | 0 |  | 0 | 0 | 2186347
Martinez | 2009 | 1765227 | 210540 | N/A | 0 | 0 |  | 0 | 0 | 1975767
Martinez | 2008 | 1553129 | 210814 | N/A | 0 | 0 |  | 0 | 0 | 1765227
Martinez | 2007 | 1341764 | 211365 | N/A | 0 | 0 |  | 0 | 0 | 1553129
Moraga | 2019 | 236284.24 | 43387 | N/A | 0 | 0 |  | 0 | 0 | 279671.24
Moraga | 2018 | 192991.24 | 43293 | N/A | 0 | 0 |  | 0 | 0 | 236284.24
Moraga | 2017 | 1584096 | 43507 | N/A | 0 | 0 |  | 1434611.76 | 1434611.76 | 192991.24
Moraga | 2016 | 1540913 | 43183 | N/A | 0 | 0 |  | 0 | 0 | 1584096
Moraga | 2015 | 1497113 | 43800 | N/A | 0 | 0 |  | 0 | 0 | 1540913
Moraga | 2014 | 1453021 | 44092 | N/A | 0 | 0 |  | 0 | 0 | 1497113
Moraga | 2013 | 1409320 | 43701 | N/A | 0 | 0 |  | 0 | 0 | 1453021
Moraga | 2012 | 1365491 | 43829 | N/A | 0 | 0 |  | 0 | 0 | 1409320
Moraga | 2011 | 1321143 | 44348 | N/A | 0 | 0 |  | 0 | 0 | 1365491
Moraga | 2010 | 1230148 | 90995 | N/A | 0 | 0 |  | 0 | 0 | 1321143
Moraga | 2009 | 1139144 | 91004 | N/A | 0 | 0 |  | 0 | 0 | 1230148
Moraga | 2008 | 1047363 | 91263 | N/A | 0 | 0 |  | 0 | 0 | 1139144
Moraga | 2007 | 955768 | 91595 | N/A | 0 | 0 |  | 0 | 0 | 1047363
Oakley | 2019 | 927088 | 67844 | N/A | 0 | 0 |  | 0 | 0 | 994932
Oakley | 2018 | 859887 | 67201 | N/A | 0 | 0 |  | 0 | 0 | 927088
Oakley | 2017 | 793221 | 66666 | N/A | 0 | 0 |  | 0 | 0 | 859887
Oakley | 2016 | 727736 | 65485 | N/A | 0 | 0 |  | 0 | 0 | 793221
Oakley | 2015 | 661881 | 65855 | N/A | 0 | 0 |  | 0 | 0 | 727736
Oakley | 2014 | 596050 | 65831 | N/A | 0 | 0 |  | 0 | 0 | 661881
Oakley | 2013 | 530153 | 65897 | N/A | 0 | 0 |  | 0 | 0 | 596050
Oakley | 2012 | 464669 | 65484 | N/A | 0 | 0 |  | 0 | 0 | 530153
Oakley | 2011 | 400200 | 64469 | N/A | 0 | 0 |  | 0 | 0 | 464669
Oakley | 2010 | 346444 | 53756 | N/A | 0 | 0 |  | 0 | 0 | 400200
Oakley | 2009 | 293171 | 53273 | N/A | 0 | 0 |  | 0 | 0 | 346444
Oakley | 2008 | 240965 | 51499 | N/A | 0 | 0 |  | 0 | 0 | 293171
Oakley | 2007 | 190685 | 50280 | N/A | 0 | 0 |  | 0 | 0 | 240965
Orinda | 2019 | 2374400 | 72203 | N/A | 0 | 0 |  | 0 | 0 | 2446603
Orinda | 2018 | 2302433 | 71967 | N/A | 0 | 0 |  | 0 | 0 | 2374400
Orinda | 2017 | 2230535 | 71898 | N/A | 0 | 0 |  | 0 | 0 | 2302433
Orinda | 2016 | 2159307 | 71228 | N/A | 0 | 0 |  | 0 | 0 | 2230535
Orinda | 2015 | 2209529 | 71778 | N/A | 0 | 0 |  | 122000 | 0 | 2159307
Orinda | 2014 | 2138002 | 71527 | N/A | 0 | 0 |  | 0 | 0 | 2209529
Orinda | 2013 | 2066955 | 71047 | N/A | 0 | 0 |  | 0 | 0 | 2138002
Orinda | 2012 | 1995799 | 71156 | N/A | 0 | 0 |  | 0 | 0 | 2066955
Orinda | 2011 | 1924572 | 71227 | N/A | 0 | 0 |  | 0 | 0 | 1995799
Orinda | 2010 | 1774206 | 150366 | N/A | 0 | 0 |  | 0 | 0 | 1924572
Orinda | 2009 | 1623747 | 150459 | N/A | 0 | 0 |  | 0 | 0 | 1774206
Orinda | 2008 | 1472289 | 150630 | N/A | 0 | 0 |  | 0 | 0 | 1623747
Orinda | 2007 | 1321205 | 151084 | N/A | 0 | 0 |  | 0 | 0 | 1472289
Pinole | 2019 | 2167433 | 55719 | N/A | 0 | 0 |  | 0 | 0 | 2223152
Pinole | 2018 | 1480586 | 55743 | N/A | 0 | 631104 | Trinity County ($631,104) | 0 | 0 | 2167433
Pinole | 2017 | 1424674 | 55912 | N/A | 0 | 0 |  | 0 | 0 | 1480586
Pinole | 2016 | 1369111 | 55563 | N/A | 0 | 0 |  | 0 | 0 | 1424674
Pinole | 2015 | 1312927 | 56184 | N/A | 0 | 0 |  | 0 | 0 | 1369111
Pinole | 2014 | 1256377 | 56550 | N/A | 0 | 0 |  | 0 | 0 | 1312927
Pinole | 2013 | 1200175 | 56202 | N/A | 0 | 0 |  | 0 | 0 | 1256377
Pinole | 2012 | 1143892 | 56283 | N/A | 0 | 0 |  | 0 | 0 | 1200175
Pinole | 2011 | 1087531 | 56361 | N/A | 0 | 0 |  | 0 | 0 | 1143892
Pinole | 2010 | 977592 | 109939 | N/A | 0 | 0 |  | 0 | 0 | 1087531
Pinole | 2009 | 867648 | 109944 | N/A | 0 | 0 |  | 0 | 0 | 977592
Pinole | 2008 | 756773 | 110219 | N/A | 0 | 0 |  | 0 | 0 | 867648
Pinole | 2007 | 646334 | 110439 | N/A | 0 | 0 |  | 0 | 0 | 756773
Pittsburg | 2019 | 2777873 | 129112 | N/A | 0 | 0 |  | 0 | 0 | 2906985
Pittsburg | 2018 | 2649206 | 128667 | N/A | 0 | 0 |  | 0 | 0 | 2777873
Pittsburg | 2017 | 2520609 | 128597 | N/A | 0 | 0 |  | 0 | 0 | 2649206
Pittsburg | 2016 | 2393855 | 126754 | N/A | 0 | 0 |  | 0 | 0 | 2520609
Pittsburg | 2015 | 2266698 | 127157 | N/A | 0 | 0 |  | 0 | 0 | 2393855
Pittsburg | 2014 | 2139423 | 127275 | N/A | 0 | 0 |  | 0 | 0 | 2266698
Pittsburg | 2013 | 2011831 | 127592 | N/A | 0 | 0 |  | 0 | 0 | 2139423
Pittsburg | 2012 | 1884706 | 127125 | N/A | 0 | 0 |  | 0 | 0 | 2011831
Pittsburg | 2011 | 1757606 | 127100 | N/A | 0 | 0 |  | 0 | 0 | 1884706
Pittsburg | 2010 | 1515994 | 241612 | N/A | 0 | 0 |  | 0 | 0 | 1757606
Pittsburg | 2009 | 1273517 | 242477 | N/A | 0 | 0 |  | 0 | 0 | 1515994
Pittsburg | 2008 | 1029385 | 242659 | N/A | 0 | 0 |  | 0 | 0 | 1273517
Pittsburg | 2007 | 787024 | 242361 | N/A | 0 | 0 |  | 0 | 0 | 1029385
Pleasant Hill | 2019 | 2347563.36 | 113331 | N/A | 0 | 0 |  | 0 | 0 | 2460894.36
Pleasant Hill | 2018 | 2234791.36 | 112772 | N/A | 0 | 0 |  | 0 | 0 | 2347563.36
Pleasant Hill | 2017 | 2121473.36 | 113318 | N/A | 0 | 0 |  | 0 | 0 | 2234791.36
Pleasant Hill | 2016 | 2008843.36 | 112630 | N/A | 0 | 0 |  | 0 | 0 | 2121473.36
Pleasant Hill | 2015 | 1942356.6 | 114487 | N/A | 0 | 0 |  | 48000.24 | 48000.24 | 2008843.36
Pleasant Hill | 2014 | 3894296 | 115216 | N/A | 0 | 0 |  | 2067155.4 | 2067155.4 | 1942356.6
Pleasant Hill | 2013 | 3779897 | 114399 | N/A | 0 | 0 |  | 0 | 0 | 3894296
Pleasant Hill | 2012 | 3665354 | 114543 | N/A | 0 | 0 |  | 0 | 0 | 3779897
Pleasant Hill | 2011 | 3551924 | 113430 | N/A | 0 | 0 |  | 0 | 0 | 3665354
Pleasant Hill | 2010 | 3315754 | 236170 | N/A | 0 | 0 |  | 0 | 0 | 3551924
Pleasant Hill | 2009 | 3079655 | 236099 | N/A | 0 | 0 |  | 0 | 0 | 3315754
Pleasant Hill | 2008 | 2841508 | 236824 | N/A | 0 | 0 |  | 0 | 0 | 3079655
Pleasant Hill | 2007 | 2604240 | 237268 | N/A | 0 | 0 |  | 0 | 0 | 2841508
Richmond | 2019 | 6235809.77 | 362129 | N/A | 0 | 0 |  | 0 | 0 | 6597938.77
Richmond | 2018 | 5874691.77 | 361118 | N/A | 0 | 0 |  | 0 | 0 | 6235809.77
Richmond | 2017 | 9848797 | 361281 | N/A | 0 | 0 |  | 4335386.23 | 4335386.23 | 5874691.77
Richmond | 2016 | 9490495 | 358302 | N/A | 0 | 0 |  | 0 | 0 | 9848797
Richmond | 2015 | 9128867 | 361628 | N/A | 0 | 0 |  | 0 | 0 | 9490495
Richmond | 2014 | 8765160 | 363707 | N/A | 0 | 0 |  | 0 | 0 | 9128867
Richmond | 2013 | 8400949 | 364211 | N/A | 0 | 0 |  | 0 | 0 | 8765160
Richmond | 2012 | 8035063 | 365886 | N/A | 0 | 0 |  | 0 | 0 | 8400949
Richmond | 2011 | 7563457 | 365701 | N/A | 0 | 0 |  | -105905 | -105905 | 8035063
Richmond | 2010 | 6821933 | 741524 | N/A | 0 | 0 |  | 0 | 0 | 7563457
Richmond | 2009 | 6080908 | 741025 | N/A | 0 | 0 |  | 0 | 0 | 6821933
Richmond | 2008 | 5334592 | 742082 | N/A | 0 | 0 |  | 0 | 0 | 6080908
Richmond | 2007 | 4591732 | 742860 | N/A | 0 | 0 |  | 0 | 0 | 5334592
San Pablo | 2019 | 569702.03 | 92021 | N/A | 0 | 0 |  | 0 | 0 | 661723.03
San Pablo | 2018 | 1729146 | 91871 | N/A | 0 | 0 |  | 1251314.97 | 1251314.97 | 569702.03
San Pablo | 2017 | 1637108 | 92038 | N/A | 0 | 0 |  | 0 | 0 | 1729146
San Pablo | 2016 | 1545789 | 91319 | N/A | 0 | 0 |  | 0 | 0 | 1637108
San Pablo | 2015 | 1453794 | 91995 | N/A | 0 | 0 |  | 0 | 0 | 1545789
San Pablo | 2014 | 1361288 | 92506 | N/A | 0 | 0 |  | 0 | 0 | 1453794
San Pablo | 2013 | 1269259 | 92029 | N/A | 0 | 0 |  | 0 | 0 | 1361288
San Pablo | 2012 | 1178093 | 91166 | N/A | 0 | 0 |  | 0 | 0 | 1269259
San Pablo | 2011 | 1086880 | 91213 | N/A | 0 | 0 |  | 0 | 0 | 1178093
San Pablo | 2010 | 899196 | 187684 | N/A | 0 | 0 |  | 0 | 0 | 1086880
San Pablo | 2009 | 711608 | 187588 | N/A | 0 | 0 |  | 0 | 0 | 899196
San Pablo | 2008 | 523031 | 187522 | N/A | 0 | 0 |  | 0 | 0 | 711608
San Pablo | 2007 | 335626 | 187405 | N/A | 0 | 0 |  | 0 | 0 | 523031
San Ramon | 2019 | 1762735.11 | 129001 | N/A | 0 | 0 |  | 0 | 0 | 1891736.11
San Ramon | 2018 | 1634490.11 | 128245 | N/A | 0 | 0 |  | 0 | 0 | 1762735.11
San Ramon | 2017 | 1506631.11 | 127859 | N/A | 0 | 0 |  | 0 | 0 | 1634490.11
San Ramon | 2016 | 1380309.11 | 126322 | N/A | 0 | 0 |  | 0 | 0 | 1506631.11
San Ramon | 2015 | 1253447.11 | 126862 | N/A | 0 | 0 |  | 0 | 0 | 1380309.11
San Ramon | 2014 | 1126394.11 | 127053 | N/A | 0 | 0 |  | 0 | 0 | 1253447.11
San Ramon | 2013 | 1000487.11 | 125907 | N/A | 0 | 0 |  | 0 | 0 | 1126394.11
San Ramon | 2012 | 876031.11 | 124456 | N/A | 0 | 0 |  | 0 | 0 | 1000487.11
San Ramon | 2011 | 751497.11 | 124534 | N/A | 0 | 0 |  | 0 | 0 | 876031.11
San Ramon | 2010 | 559809.11 | 191688 | N/A | 0 | 0 |  | 0 | 0 | 751497.11
San Ramon | 2009 | 369337.11 | 190472 | N/A | 0 | 0 |  | 0 | 0 | 559809.11
San Ramon | 2008 | 179292.11 | 188658 | N/A | 0 | 0 |  | 0 | 0 | 369337.11
San Ramon | 2007 | 1027004 | 186741 | N/A | 0 | 0 |  | 1034452.89 | 1034452.89 | 179292.11
Walnut Creek | 2019 | 3990212.22 | 222847 | N/A | 0 | 0 |  | 0 | 0 | 4213059.22
Walnut Creek | 2018 | 3768154.22 | 222058 | N/A | 0 | 0 |  | 0 | 0 | 3990212.22
Walnut Creek | 2017 | 3545779.22 | 222375 | N/A | 0 | 0 |  | 0 | 0 | 3768154.22
Walnut Creek | 2016 | 3325320.22 | 220459 | N/A | 0 | 0 |  | 0 | 0 | 3545779.22
Walnut Creek | 2015 | 3103097.22 | 222223 | N/A | 0 | 0 |  | 0 | 0 | 3325320.22
Walnut Creek | 2014 | 2878554.22 | 224543 | N/A | 0 | 0 |  | 0 | 0 | 3103097.22
Walnut Creek | 2013 | 2656104.22 | 222450 | N/A | 0 | 0 |  | 0 | 0 | 2878554.22
Walnut Creek | 2012 | 2432860.22 | 223244 | N/A | 0 | 0 |  | 0 | 0 | 2656104.22
Walnut Creek | 2011 | 2210983.22 | 221877 | N/A | 0 | 0 |  | 0 | 0 | 2432860.22
Walnut Creek | 2010 | 1761060.22 | 449923 | N/A | 0 | 0 |  | 0 | 0 | 2210983.22
Walnut Creek | 2009 | 1311735.22 | 449325 | N/A | 0 | 0 |  | 0 | 0 | 1761060.22
Walnut Creek | 2008 | 859557.22 | 449608 | N/A | 0 | 0 |  | 0 | 0 | 1311735.22
Walnut Creek | 2007 | 409358.22 | 450199 | N/A | 0 | 0 |  | 0 | 0 | 859557.22
Contra Costa County Total |  |  | 50001129 |  |  | 631104 |  | 25832020.78 | 25637716.78
El Dorado County
El Dorado County | 2019 | 16928302 | 551416 | N/A | 0 | 0 |  | 0 | 0 | 17479718
El Dorado County | 2018 | 16381480 | 546822 | N/A | 0 | 0 |  | 0 | 0 | 16928302
El Dorado County | 2017 | 15836285 | 545195 | N/A | 0 | 0 |  | 0 | 0 | 16381480
El Dorado County | 2016 | 15297831 | 538454 | N/A | 0 | 0 |  | 0 | 0 | 15836285
El Dorado County | 2015 | 14755946 | 541885 | N/A | 0 | 0 |  | 0 | 0 | 15297831
El Dorado County | 2014 | 14212193 | 543753 | N/A | 0 | 0 |  | 0 | 0 | 14755946
El Dorado County | 2013 | 13673919 | 538274 | N/A | 0 | 0 |  | 0 | 0 | 14212193
El Dorado County | 2012 | 13135619 | 538300 | N/A | 0 | 0 |  | 0 | 0 | 13673919
El Dorado County | 2011 | 12591840 | 543779 | N/A | 0 | 0 |  | 0 | 0 | 13135619
El Dorado County | 2010 | 11679287 | 912553 | N/A | 0 | 0 |  | 0 | 0 | 12591840
El Dorado County | 2009 | 10768040 | 911247 | N/A | 0 | 0 |  | 0 | 0 | 11679287
El Dorado County | 2008 | 9851473 | 910310 | N/A | 0 | 0 |  | 0 | 0 | 10768040
El Dorado County | 2007 | 8943060 | 908413 | N/A | 0 | 0 |  | 0 | 0 | 9851473
Placerville | 2019 | -336004.79 | 46362 | N/A | 0 | 0 |  | 0 | 0 | -289642.79 | Borrowed beyond 5 years (see AL 4553-E)
Placerville | 2018 | -382124.79 | 46120 | N/A | 0 | 0 |  | 0 | 0 | -336004.79 | Borrowed beyond 5 years (see AL 4553-E)
Placerville | 2017 | -428321.79 | 46197 | N/A | 0 | 0 |  | 0 | 0 | -382124.79 | Borrowed beyond 5 years (see AL 4553-E)
Placerville | 2016 | -473984.79 | 45663 | N/A | 0 | 0 |  | 0 | 0 | -428321.79 | Borrowed beyond 5 years (see AL 4553-E)
Placerville | 2015 | -520116.79 | 46132 | N/A | 0 | 0 |  | 0 | 0 | -473984.79 | Borrowed beyond 5 years (see AL 4553-E)
Placerville | 2014 | 1426817 | 46440 | N/A | 0 | 0 |  | 1993373.79 | 1993373.79 | -520116.79 | Borrowed beyond 5 years (see AL 4553-E)
Placerville | 2013 | 1380476 | 46341 | N/A | 0 | 0 |  | 0 | 0 | 1426817
Placerville | 2012 | 1360081 | 46414 | N/A | 0 | 0 |  | 0 | 0 | 1380476
Placerville | 2011 | 1318630 | 41451 | N/A | 0 | 0 |  | 0 | 0 | 1360081
Placerville | 2010 | 1240433 | 78197 | N/A | 0 | 0 |  | 0 | 0 | 1318630
Placerville | 2009 | 1162265 | 78168 | N/A | 0 | 0 |  | 0 | 0 | 1240433
Placerville | 2008 | 1083497 | 78284 | N/A | 0 | 0 |  | 0 | 0 | 1162265
Placerville | 2007 | 1005242 | 78255 | N/A | 0 | 0 |  | 0 | 0 | 1083497
El Dorado County Total |  |  | 9254425 |  |  | 0 |  | 1993373.79 | 1993373.79
Fresno County
Clovis | 2019 | 1379241.9 | 212815 | N/A | 0 | 0 |  | 0 | 0 | 1592056.9
Clovis | 2018 | 1170247.9 | 208994 | N/A | 0 | 0 |  | 0 | 0 | 1379241.9
Clovis | 2017 | 963866.9 | 206381 | N/A | 0 | 0 |  | 0 | 0 | 1170247.9
Clovis | 2016 | 760952.9 | 202914 | N/A | 0 | 0 |  | 0 | 0 | 963866.9
Clovis | 2015 | 557711.9 | 203241 | N/A | 0 | 0 |  | 0 | 0 | 760952.9
Clovis | 2014 | 355780.9 | 201931 | N/A | 0 | 0 |  | 0 | 0 | 557711.9
Clovis | 2013 | 153311.9 | 202469 | N/A | 0 | 0 |  | 0 | 0 | 355780.9
Clovis | 2012 | -47692.1 | 201004 | N/A | 0 | 0 |  | 0 | 0 | 153311.9
Clovis | 2011 | -248084.1 | 200392 | N/A | 0 | 0 |  | 0 | 0 | -47692.1 | Within 5-year borrow
Clovis | 2010 | -567045.1 | 318961 | N/A | 0 | 0 |  | 0 | 0 | -248084.1 | Within 5-year borrow
Clovis | 2009 | 2617498 | 317496 | N/A | 0 | 0 |  | 3502039.1 | 3502039.1 | -567045.1 | Within 5-year borrow
Clovis | 2008 | 2298848 | 316383 | N/A | 0 | 0 |  | 0 | 0 | 2617498
Clovis | 2007 | 1984234 | 314614 | N/A | 0 | 0 |  | 0 | 0 | 2298848
Coalinga | 2019 | 1787291 | 36546 | N/A | 0 | 0 |  | 0 | 0 | 1823837
Coalinga | 2018 | 1750956 | 36335 | N/A | 0 | 0 |  | 0 | 0 | 1787291
Coalinga | 2017 | 1039432 | 36524 | N/A | 0 | 675000 | $675,000 (Fresno County) | 0 | 0 | 1750956
Coalinga | 2016 | 1003318 | 36114 | N/A | 0 | 0 |  | 0 | 0 | 1039432
Coalinga | 2015 | 967131 | 36187 | N/A | 0 | 0 |  | 0 | 0 | 1003318
Coalinga | 2014 | 930726 | 36405 | N/A | 0 | 0 |  | 0 | 0 | 967131
Coalinga | 2013 | 894306 | 36420 | N/A | 0 | 0 |  | 0 | 0 | 930726
Coalinga | 2012 | 857839 | 36467 | N/A | 0 | 0 |  | 0 | 0 | 894306
Coalinga | 2011 | 821313 | 36526 | N/A | 0 | 0 |  | 0 | 0 | 857839
Coalinga | 2010 | 749820 | 71493 | N/A | 0 | 0 |  | 0 | 0 | 821313
Coalinga | 2009 | 678406 | 71414 | N/A | 0 | 0 |  | 0 | 0 | 749820
Coalinga | 2008 | 606509 | 71474 | N/A | 0 | 0 |  | 0 | 0 | 678406
Coalinga | 2007 | 535531 | 70978 | N/A | 0 | 0 |  | 0 | 0 | 606509
Firebaugh | 2019 | -1006836.29 | 17599 | N/A | 0 | 0 |  | 0 | 0 | -989237.29 | Borrowed beyond 5 years (see AL 4553-E)
Firebaugh | 2018 | -1024331.29 | 17495 | N/A | 0 | 0 |  | 0 | 0 | -1006836.29 | Borrowed beyond 5 years (see AL 4553-E)
Firebaugh | 2017 | -1041897.29 | 17566 | N/A | 0 | 0 |  | 0 | 0 | -1024331.29 | Borrowed beyond 5 years (see AL 4553-E)
Firebaugh | 2016 | -1059413.29 | 17516 | N/A | 0 | 0 |  | 0 | 0 | -1041897.29 | Borrowed beyond 5 years (see AL 4553-E)
Firebaugh | 2015 | 1346475 | 17587 | N/A | 0 | 0 |  | 2423475.29 | 2423475.29 | -1059413.29 | Borrowed beyond 5 years (see AL 4553-E)
Firebaugh | 2014 | 578726 | 17749 | N/A | 0 | 750000 | $750,000 (Fresno County) | 0 | 0 | 1346475
Firebaugh | 2013 | 560768 | 17958 | N/A | 0 | 0 |  | 0 | 0 | 578726
Firebaugh | 2012 | 543649 | 17119 | N/A | 0 | 0 |  | 0 | 0 | 560768
Firebaugh | 2011 | 526694 | 16955 | N/A | 0 | 0 |  | 0 | 0 | 543649
Firebaugh | 2010 | 497623 | 29071 | N/A | 0 | 0 |  | 0 | 0 | 526694
Firebaugh | 2009 | 468656 | 28967 | N/A | 0 | 0 |  | 0 | 0 | 497623
Firebaugh | 2008 | 439494 | 28969 | N/A | 0 | 0 |  | 0 | 0 | 468656
Firebaugh | 2007 | 410582 | 28912 | N/A | 0 | 0 |  | 0 | 0 | 439494
Fowler | 2019 | -286715.34 | 16848 | N/A | 0 | 0 |  | 0 | 0 | -269867.34 | Borrowed beyond 5 years (see AL 4553-E)
Fowler | 2018 | -303241.34 | 16526 | N/A | 0 | 0 |  | 0 | 0 | -286715.34 | Borrowed beyond 5 years (see AL 4553-E)
Fowler | 2017 | -319790.34 | 16549 | N/A | 0 | 0 |  | 0 | 0 | -303241.34 | Borrowed beyond 5 years (see AL 4553-E)
Fowler | 2016 | -336127.34 | 16337 | N/A | 0 | 0 |  | 0 | 0 | -319790.34 | Borrowed beyond 5 years (see AL 4553-E)
Fowler | 2015 | -352527.34 | 16400 | N/A | 0 | 0 |  | 0 | 0 | -336127.34 | Borrowed beyond 5 years (see AL 4553-E)
Fowler | 2014 | 60382 | 16357 | N/A | 0 | 450000 | $450,000 (Fresno County) | 879266.34 | 879266.34 | -352527.34 | Borrowed beyond 5 years (see AL 4553-E)
Fowler | 2013 | 43624 | 16758 | N/A | 0 | 0 |  | 0 | 0 | 60382
Fowler | 2012 | 26856 | 16768 | N/A | 0 | 0 |  | 0 | 0 | 43624
Fowler | 2011 | 10067 | 16789 | N/A | 0 | 0 |  | 0 | 0 | 26856
Fowler | 2010 | -19445 | 29512 | N/A | 0 | 0 |  | 0 | 0 | 10067
Fowler | 2009 | -48832 | 29387 | N/A | 0 | 0 |  | 0 | 0 | -19445 | Within 5-year borrow
Fowler | 2008 | -78274 | 29254 | N/A | 0 | 0 |  | 0 | 0 | -48832 | Within 5-year borrow
Fowler | 2007 | -107199 | 28925 | N/A | 0 | 0 |  | 0 | 0 | -78274 | Within 5-year borrow
Fresno | 2019 | 9429538.54 | 1308906 | N/A | 0 | 0 |  | 0 | 0 | 10738444.54
Fresno | 2018 | 14666716.42 | 1305432 | N/A | 0 | 0 |  | 6542609.88 | 6542609.88 | 9429538.54
Fresno | 2017 | 13360972.42 | 1305744 | N/A | 0 | 0 |  | 0 | 0 | 14666716.42
Fresno | 2016 | 19790794.04 | 1296133 | N/A | 0 | 0 |  | 7725954.62 | 7725954.62 | 13360972.42
Fresno | 2015 | 18483167.04 | 1307627 | N/A | 0 | 0 |  | 0 | 0 | 19790794.04
Fresno | 2014 | 17170206.04 | 1312961 | N/A | 0 | 0 |  | 0 | 0 | 18483167.04
Fresno | 2013 | 17426659.5 | 1316399 | N/A | 0 | 0 |  | 1562852.46 | 1558816 | 17170206.04
Fresno | 2012 | 16103186.5 | 1323473 | N/A | 0 | 0 |  | 0 | 0 | 17426659.5
Fresno | 2011 | 13888145.5 | 1315765 | N/A | 0 | 0 |  | -899276 | -899276 | 16103186.5
Fresno | 2010 | 16001432.5 | 2431211 | N/A | 0 | 0 |  | 4544498 | 4544498 | 13888145.5
Fresno | 2009 | 13578085.5 | 2423347 | N/A | 0 | 0 |  | 0 | 0 | 16001432.5
Fresno | 2008 | 11142752.5 | 2420307 | N/A | 0 | 0 |  | 0 | 0 | 13578085.5
Fresno | 2007 | 9697590.31 | 2415549 | N/A | 0 | 0 |  | 970386.81 | 924176.55 | 11142752.5
Fresno County | 2019 | 12567180.04 | 881727 | N/A | 0 | 0 |  | 0 | 0 | 12048907.04
Fresno County | 2018 | 13954493.4 | 872987 | N/A | 0 | 0 |  | 2260300.36 | 2260300.36 | 12567180.04
Fresno County | 2017 | 13755299.4 | 874194 | N/A | 0 | 0 |  | 0 | 0 | 13954493.4
Fresno County | 2016 | 12786245.4 | 868584 | N/A | 0 | 0 |  | 0 | 0 | 13755299.4
Fresno County | 2015 | 12061317.4 | 874928 | N/A | 0 | 0 |  | 0 | 0 | 12786245.4
Fresno County | 2014 | 17154443.4 | 876874 | N/A | 0 | 0 |  | 0 | 0 | 12061317.4
Fresno County | 2013 | 17588588.73 | 897548 | N/A | 0 | 0 |  | 1331693.33 | 1330000 | 17154443.4
Fresno County | 2012 | 16699281.73 | 889307 | N/A | 0 | 0 |  | 0 | 0 | 17588588.73
Fresno County | 2011 | 15795778.73 | 892903 | N/A | 0 | 0 |  | -10600 | -10600 | 16699281.73
Fresno County | 2010 | 17257315.73 | 2035676 | N/A | 0 | 0 |  | 3497213 | 3497213 | 15795778.73
Fresno County | 2009 | 15225945.73 | 2031370 | N/A | 0 | 0 |  | 0 | 0 | 17257315.73
Fresno County | 2008 | 13184562.73 | 2031132 | N/A | 0 | 0 |  | 0 | 0 | 15225945.73
Fresno County | 2007 | 11154825.73 | 2029737 | N/A | 0 | 0 |  | 0 | 0 | 13184562.73
Huron | 2019 | 180255 | 11408 | N/A | 0 | 0 |  | 0 | 0 | 191663
Huron | 2018 | 168809 | 11446 | N/A | 0 | 0 |  | 0 | 0 | 180255
Huron | 2017 | 157301 | 11508 | N/A | 0 | 0 |  | 0 | 0 | 168809
Huron | 2016 | 145904 | 11397 | N/A | 0 | 0 |  | 0 | 0 | 157301
Huron | 2015 | 134339 | 11565 | N/A | 0 | 0 |  | 0 | 0 | 145904
Huron | 2014 | 122685 | 11654 | N/A | 0 | 0 |  | 0 | 0 | 134339
Huron | 2013 | 111068 | 11617 | N/A | 0 | 0 |  | 0 | 0 | 122685
Huron | 2012 | 99272 | 11796 | N/A | 0 | 0 |  | 0 | 0 | 111068
Huron | 2011 | 87448 | 11824 | N/A | 0 | 0 |  | 0 | 0 | 99272
Huron | 2010 | 68060 | 19388 | N/A | 0 | 0 |  | 0 | 0 | 87448
Huron | 2009 | 48706 | 19354 | N/A | 0 | 0 |  | 0 | 0 | 68060
Huron | 2008 | 29716 | 18860 | N/A | 0 | 0 |  | 0 | 0 | 48706
Huron | 2007 | 10819 | 18897 | N/A | 0 | 0 |  | 0 | 0 | 29716
Kerman | 2019 | 543997 | 27828 | N/A | 0 | 0 |  | 0 | 0 | 571825
Kerman | 2018 | 516387 | 27610 | N/A | 0 | 0 |  | 0 | 0 | 543997
Kerman | 2017 | 488879 | 27508 | N/A | 0 | 0 |  | 0 | 0 | 516387
Kerman | 2016 | 461662 | 27217 | N/A | 0 | 0 |  | 0 | 0 | 488879
Kerman | 2015 | 434158 | 27504 | N/A | 0 | 0 |  | 0 | 0 | 461662
Kerman | 2014 | 406489 | 27669 | N/A | 0 | 0 |  | 0 | 0 | 434158
Kerman | 2013 | -351343 | 27832 | N/A | 0 | 0 |  | -730000 | -730000 | 406489
Kerman | 2012 | -378689 | 27346 | N/A | 0 | 0 |  | 0 | 0 | -351343 | Additional research required
Kerman | 2011 | 691245 | 27338 | N/A | 0 | 0 |  | 1097272 | 1097272 | -378689 | Additional research required
Kerman | 2010 | 648452 | 42793 | N/A | 0 | 0 |  | 0 | 0 | 691245
Kerman | 2009 | 605835 | 42617 | N/A | 0 | 0 |  | 0 | 0 | 648452
Kerman | 2008 | 563319 | 42210 | N/A | 0 | 0 |  | 0 | 0 | 605835
Kerman | 2007 | 521371 | 41948 | N/A | 0 | 0 |  | 0 | 0 | 563319
Kingsburg | 2019 | 1228113 | 34041 | N/A | 0 | 0 |  | 0 | 0 | 1262154
Kingsburg | 2018 | 1194277 | 33836 | N/A | 0 | 0 |  | 0 | 0 | 1228113
Kingsburg | 2017 | 1160503 | 33774 | N/A | 0 | 0 |  | 0 | 0 | 1194277
Kingsburg | 2016 | 1127203 | 33300 | N/A | 0 | 0 |  | 0 | 0 | 1160503
Kingsburg | 2015 | 1093860 | 33343 | N/A | 0 | 0 |  | 0 | 0 | 1127203
Kingsburg | 2014 | 560355 | 33505 | N/A | 0 | 500000 | $500,000 (Fresno County) | 0 | 0 | 1093860
Kingsburg | 2013 | 526363 | 33992 | N/A | 0 | 0 |  | 0 | 0 | 560355
Kingsburg | 2012 | 492363 | 34000 | N/A | 0 | 0 |  | 0 | 0 | 526363
Kingsburg | 2011 | 458428 | 33935 | N/A | 0 | 0 |  | 0 | 0 | 492363
Kingsburg | 2010 | 400874 | 57554 | N/A | 0 | 0 |  | 0 | 0 | 458428
Kingsburg | 2009 | 343442 | 57432 | N/A | 0 | 0 |  | 0 | 0 | 400874
Kingsburg | 2008 | 285819 | 57236 | N/A | 0 | 0 |  | 0 | 0 | 343442
Kingsburg | 2007 | 228411 | 57408 | N/A | 0 | 0 |  | 0 | 0 | 285819
Mendota | 2019 | 850182 | 20531 | N/A | 0 | 0 |  | 0 | 0 | 870713
Mendota | 2018 | 829995 | 20187 | N/A | 0 | 0 |  | 0 | 0 | 850182
Mendota | 2017 | 810019 | 19976 | N/A | 0 | 0 |  | 0 | 0 | 829995
Mendota | 2016 | 790239 | 19780 | N/A | 0 | 0 |  | 0 | 0 | 810019
Mendota | 2015 | 770236 | 20003 | N/A | 0 | 0 |  | 0 | 0 | 790239
Mendota | 2014 | 750228 | 20008 | N/A | 0 | 0 |  | 0 | 0 | 770236
Mendota | 2013 | 730124 | 20104 | N/A | 0 | 0 |  | 0 | 0 | 750228
Mendota | 2012 | 710386 | 19738 | N/A | 0 | 0 |  | 0 | 0 | 730124
Mendota | 2011 | 601778 | 19675 | N/A | 0 | 0 |  | 0 | 0 | 710386
Mendota | 2010 | 568577 | 33201 | N/A | 0 | 0 |  | 0 | 0 | 601778
Mendota | 2009 | 535403 | 33174 | N/A | 0 | 0 |  | 0 | 0 | 568577
Mendota | 2008 | 502194 | 32985 | N/A | 0 | 0 |  | 0 | 0 | 535403
Mendota | 2007 | 469647 | 32547 | N/A | 0 | 0 |  | 0 | 0 | 502194
Orange Cove | 2019 | 968088 | 20844 | N/A | 0 | 0 |  | 0 | 0 | 988932
Orange Cove | 2018 | 947303 | 20785 | N/A | 0 | 0 |  | 0 | 0 | 968088
Orange Cove | 2017 | 926480 | 20823 | N/A | 0 | 0 |  | 0 | 0 | 947303
Orange Cove | 2016 | 905819 | 20661 | N/A | 0 | 0 |  | 0 | 0 | 926480
Orange Cove | 2015 | 884931 | 20888 | N/A | 0 | 0 |  | 0 | 0 | 905819
Orange Cove | 2014 | 863960 | 20971 | N/A | 0 | 0 |  | 0 | 0 | 884931
Orange Cove | 2013 | 842964 | 20996 | N/A | 0 | 0 |  | 0 | 0 | 863960
Orange Cove | 2012 | 822023 | 20941 | N/A | 0 | 0 |  | 0 | 0 | 842964
Orange Cove | 2011 | 712533 | 20821 | N/A | 0 | 0 |  | 0 | 0 | 822023
Orange Cove | 2010 | 674868 | 37665 | N/A | 0 | 0 |  | 0 | 0 | 712533
Orange Cove | 2009 | 637256 | 37612 | N/A | 0 | 0 |  | 0 | 0 | 674868
Orange Cove | 2008 | 599350 | 37666 | N/A | 0 | 0 |  | 0 | 0 | 637256
Orange Cove | 2007 | 562596 | 36754 | N/A | 0 | 0 |  | 0 | 0 | 599350
Parlier | 2019 | 554809.73 | 24577 | N/A | 0 | 0 |  | 0 | 0 | 579386.73
Parlier | 2018 | 2166623 | 24768 | N/A | 0 | 0 |  | 1636581.27 | 1636581.27 | 554809.73
Parlier | 2017 | 2141969 | 24654 | N/A | 0 | 0 |  | 0 | 0 | 2166623
Parlier | 2016 | 2218305 | 24134 | N/A | 0 | 49530 | $49,530 (Fresno County) | 0 | 0 | 2141969
Parlier | 2015 | 2043834 | 24471 | N/A | 0 | 0 |  | 0 | 0 | 2218305
Parlier | 2014 | 349170 | 24664 | N/A | 0 | 1670000 | $750,000 (Fresno County), $920,000 (Fresno County) | 0 | 0 | 2043834
Parlier | 2013 | 324468 | 24702 | N/A | 0 | 0 |  | 0 | 0 | 349170
Parlier | 2012 | 300022 | 24446 | N/A | 0 | 0 |  | 0 | 0 | 324468
Parlier | 2011 | 275800 | 24222 | N/A | 0 | 0 |  | 0 | 0 | 300022
Parlier | 2010 | 235268 | 40532 | N/A | 0 | 0 |  | 0 | 0 | 275800
Parlier | 2009 | 194910 | 40358 | N/A | 0 | 0 |  | 0 | 0 | 235268
Parlier | 2008 | 154300 | 40334 | N/A | 0 | 0 |  | 0 | 0 | 194910
Parlier | 2007 | 114439 | 39861 | N/A | 0 | 0 |  | 0 | 0 | 154300
Reedley | 2019 | 3560697 | 56901 | N/A | 0 | 1400000 | Fresno County ($1,400,000) | 2493012.88 | 2493012.88 | 2524585.12
Reedley | 2018 | 3503601 | 57096 | N/A | 0 | 0 |  | 0 | 0 | 3560697
Reedley | 2017 | 3446493 | 57108 | N/A | 0 | 0 |  | 0 | 0 | 3503601
Reedley | 2016 | 3389837 | 56656 | N/A | 0 | 0 |  | 0 | 0 | 3446493
Reedley | 2015 | 3332519 | 57318 | N/A | 0 | 0 |  | 0 | 0 | 3389837
Reedley | 2014 | 675445 | 57074 | N/A | 0 | 2600000 | $600,000 (Fresno County), $2,000,000 (Fresno County) | 0 | 0 | 3332519
Reedley | 2013 | 617911 | 57534 | N/A | 0 | 0 |  | 0 | 0 | 675445
Reedley | 2012 | 1149442 | 57288 | N/A | 0 | 0 |  | 588819 | 588819 | 617911
Reedley | 2011 | 1092011 | 57431 | N/A | 0 | 0 |  | 0 | 0 | 1149442
Reedley | 2010 | 988538 | 103473 | N/A | 0 | 0 |  | 0 | 0 | 1092011
Reedley | 2009 | 885296 | 103242 | N/A | 0 | 0 |  | 0 | 0 | 988538
Reedley | 2008 | 781434 | 103205 | N/A | 0 | 0 |  | 0 | 0 | 885296
Reedley | 2007 | 678740 | 102694 | N/A | 0 | 0 |  | 0 | 0 | 781434
San Joaquin | 2019 | 365227 | 7584 | N/A | 0 | 0 |  | 0 | 0 | 372811
San Joaquin | 2018 | 357667 | 7560 | N/A | 0 | 0 |  | 0 | 0 | 365227
San Joaquin | 2017 | 349977 | 7690 | N/A | 0 | 0 |  | 0 | 0 | 357667
San Joaquin | 2016 | 342284 | 7693 | N/A | 0 | 0 |  | 0 | 0 | 349977
San Joaquin | 2015 | 334476 | 7808 | N/A | 0 | 0 |  | 0 | 0 | 342284
San Joaquin | 2014 | 326622 | 7854 | N/A | 0 | 0 |  | 0 | 0 | 334476
San Joaquin | 2013 | 318633 | 7989 | N/A | 0 | 0 |  | 0 | 0 | 326622
San Joaquin | 2012 | 310731 | 7902 | N/A | 0 | 0 |  | 0 | 0 | 318633
San Joaquin | 2011 | 285998 | 8033 | N/A | 0 | 0 |  | 0 | 0 | 310731
San Joaquin | 2010 | 272034 | 13964 | N/A | 0 | 0 |  | 0 | 0 | 285998
San Joaquin | 2009 | 258083 | 13951 | N/A | 0 | 0 |  | 0 | 0 | 272034
San Joaquin | 2008 | 244068 | 13924 | N/A | 0 | 0 |  | 0 | 0 | 258083
San Joaquin | 2007 | 230348 | 13720 | N/A | 0 | 0 |  | 0 | 0 | 244068
Sanger | 2019 | 1168016 | 58524 | N/A | 0 | 0 |  | 0 | 0 | 1226540
Sanger | 2018 | 1109719 | 58297 | N/A | 0 | 0 |  | 0 | 0 | 1168016
Sanger | 2017 | 1051616 | 58103 | N/A | 0 | 0 |  | 0 | 0 | 1109719
Sanger | 2016 | 993935 | 57681 | N/A | 0 | 0 |  | 0 | 0 | 1051616
Sanger | 2015 | 936249 | 57686 | N/A | 0 | 0 |  | 0 | 0 | 993935
Sanger | 2014 | 878524 | 57725 | N/A | 0 | 0 |  | 0 | 0 | 936249
Sanger | 2013 | 1346854 | 57578 | N/A | 0 | 0 |  | 525908 | 525908 | 878524
Sanger | 2012 | 1288775 | 58079 | N/A | 0 | 0 |  | 0 | 0 | 1346854
Sanger | 2011 | 1230585 | 58190 | N/A | 0 | 0 |  | 0 | 0 | 1288775
Sanger | 2010 | 1124080 | 106505 | N/A | 0 | 0 |  | 0 | 0 | 1230585
Sanger | 2009 | 1017693 | 106387 | N/A | 0 | 0 |  | 0 | 0 | 1124080
Sanger | 2008 | 910611 | 106406 | N/A | 0 | 0 |  | 0 | 0 | 1017693
Sanger | 2007 | 804793 | 105818 | N/A | 0 | 0 |  | 0 | 0 | 910611
Selma | 2019 | 1668789 | 57464 | N/A | 0 | 0 |  | 0 | 0 | 1726253
Selma | 2018 | 1611477 | 57312 | N/A | 0 | 0 |  | 0 | 0 | 1668789
Selma | 2017 | 1553900 | 57577 | N/A | 0 | 0 |  | 0 | 0 | 1611477
Selma | 2016 | 1496837 | 57063 | N/A | 0 | 0 |  | 0 | 0 | 1553900
Selma | 2015 | 1439256 | 57581 | N/A | 0 | 0 |  | 0 | 0 | 1496837
Selma | 2014 | 1381169 | 58087 | N/A | 0 | 0 |  | 0 | 0 | 1439256
Selma | 2013 | 1322573 | 58596 | N/A | 0 | 0 |  | 0 | 0 | 1381169
Selma | 2012 | 1264151 | 58422 | N/A | 0 | 0 |  | 0 | 0 | 1322573
Selma | 2011 | 1205746 | 58405 | N/A | 0 | 0 |  | 0 | 0 | 1264151
Selma | 2010 | 1102938 | 102808 | N/A | 0 | 0 |  | 0 | 0 | 1205746
Selma | 2009 | 1000152 | 102786 | N/A | 0 | 0 |  | 0 | 0 | 1102938
Selma | 2008 | 896714 | 102764 | N/A | 0 | 0 |  | 0 | 0 | 1000152
Selma | 2007 | 793935 | 102779 | N/A | 0 | 0 |  | 0 | 0 | 896714
Fresno County Total |  |  | 46894036 |  |  | 8094530 |  | 39942006.34 | 39890066.29
Glenn County
Glenn County | 2019 | 3394209 | 96439 | N/A | 0 | 0 |  | 0 | 0 | 3490648
Glenn County | 2018 | 3298634 | 95575 | N/A | 0 | 0 |  | 0 | 0 | 3394209
Glenn County | 2017 | 3202827 | 95807 | N/A | 0 | 0 |  | 0 | 0 | 3298634
Glenn County | 2016 | 3108312 | 94515 | N/A | 0 | 0 |  | 0 | 0 | 3202827
Glenn County | 2015 | 3013157 | 95155 | N/A | 0 | 0 |  | 0 | 0 | 3108312
Glenn County | 2014 | 2918314 | 94843 | N/A | 0 | 0 |  | 0 | 0 | 3013157
Glenn County | 2013 | 2822249 | 96065 | N/A | 0 | 0 |  | 0 | 0 | 2918314
Glenn County | 2012 | 2726463 | 95786 | N/A | 0 | 0 |  | 0 | 0 | 2822249
Glenn County | 2011 | 2630557 | 95906 | N/A | 0 | 0 |  | 0 | 0 | 2726463
Glenn County | 2010 | 2426468 | 204089 | N/A | 0 | 0 |  | 0 | 0 | 2630557
Glenn County | 2009 | 2222955 | 203513 | N/A | 0 | 0 |  | 0 | 0 | 2426468
Glenn County | 2008 | 2018704 | 203155 | N/A | 0 | 0 |  | 0 | 0 | 2222955
Glenn County | 2007 | 1815580 | 203124 | N/A | 0 | 0 |  | 0 | 0 | 2018704
Orland | 2019 | 1116243 | 28521 | N/A | 0 | 0 |  | 0 | 0 | 1144764
Orland | 2018 | 1087915 | 28328 | N/A | 0 | 0 |  | 0 | 0 | 1116243
Orland | 2017 | 1059633 | 28282 | N/A | 0 | 0 |  | 0 | 0 | 1087915
Orland | 2016 | 1031645 | 27988 | N/A | 0 | 0 |  | 0 | 0 | 1059633
Orland | 2015 | 1003405 | 28240 | N/A | 0 | 0 |  | 0 | 0 | 1031645
Orland | 2014 | 974971 | 28434 | N/A | 0 | 0 |  | 0 | 0 | 1003405
Orland | 2013 | 946300 | 28671 | N/A | 0 | 0 |  | 0 | 0 | 974971
Orland | 2012 | 917547 | 28753 | N/A | 0 | 0 |  | 0 | 0 | 946300
Orland | 2011 | 889385 | 28162 | N/A | 0 | 0 |  | 0 | 0 | 917547
Orland | 2010 | 836099 | 53286 | N/A | 0 | 0 |  | 0 | 0 | 889385
Orland | 2009 | 782950 | 53149 | N/A | 0 | 0 |  | 0 | 0 | 836099
Orland | 2008 | 729528 | 53099 | N/A | 0 | 0 |  | 0 | 0 | 782950
Orland | 2007 | 677097 | 52431 | N/A | 0 | 0 |  | 0 | 0 | 729528
Willows | 2019 | 787192 | 25802 | N/A | 0 | 0 |  | 0 | 0 | 812994
Willows | 2018 | 761575 | 25617 | N/A | 0 | 0 |  | 0 | 0 | 787192
Willows | 2017 | 735741 | 25834 | N/A | 0 | 0 |  | 0 | 0 | 761575
Willows | 2016 | 710105 | 25636 | N/A | 0 | 0 |  | 0 | 0 | 735741
Willows | 2015 | 684348 | 25757 | N/A | 0 | 0 |  | 0 | 0 | 710105
Willows | 2014 | 658393 | 25955 | N/A | 0 | 0 |  | 0 | 0 | 684348
Willows | 2013 | 632567 | 25826 | N/A | 0 | 0 |  | 0 | 0 | 658393
Willows | 2012 | 606667 | 25900 | N/A | 0 | 0 |  | 0 | 0 | 632567
Willows | 2011 | 580994 | 25673 | N/A | 0 | 0 |  | 0 | 0 | 606667
Willows | 2010 | 527697 | 53297 | N/A | 0 | 0 |  | 0 | 0 | 580994
Willows | 2009 | 474424 | 53273 | N/A | 0 | 0 |  | 0 | 0 | 527697
Willows | 2008 | 420751 | 53374 | N/A | 0 | 0 |  | 0 | 0 | 474424
Willows | 2007 | 367438 | 53313 | N/A | 0 | 0 |  | 0 | 0 | 420751
Glenn County Total |  |  | 2586573 |  |  | 0 |  | 0 | 0
Humboldt County
Arcata | 2019 | 1666657.14 | 72628 | N/A | 0 | 0 |  | 0 | 0 | 1739285.14
Arcata | 2018 | 1595265.14 | 71392 | N/A | 0 | 0 |  | 0 | 0 | 1666657.14
Arcata | 2017 | 1523996.14 | 71269 | N/A | 0 | 0 |  | 0 | 0 | 1595265.14
Arcata | 2016 | 1453363.14 | 70633 | N/A | 0 | 0 |  | 0 | 0 | 1523996.14
Arcata | 2015 | 1382352.14 | 71011 | N/A | 0 | 0 |  | 0 | 0 | 1453363.14
Arcata | 2014 | 1311230.14 | 71122 | N/A | 0 | 0 |  | 0 | 0 | 1382352.14
Arcata | 2013 | 1240812.14 | 70418 | N/A | 0 | 0 |  | 0 | 0 | 1311230.14
Arcata | 2012 | 1170891.14 | 69921 | N/A | 0 | 0 |  | 0 | 0 | 1240812.14
Arcata | 2011 | 1101013.14 | 69878 | N/A | 0 | 0 |  | 0 | 0 | 1170891.14
Arcata | 2010 | 974707.14 | 126306 | N/A | 0 | 0 |  | 0 | 0 | 1101013.14
Arcata | 2009 | 848520.14 | 126187 | N/A | 0 | 0 |  | 0 | 0 | 974707.14
Arcata | 2008 | 721513.14 | 126199 | N/A | 0 | 0 |  | 0 | 0 | 848520.14
Arcata | 2007 | 1705149 | 126055 | N/A | 0 | 0 |  | 1109690.86 | 1109690.86 | 721513.14
Blue Lake | 2019 | 361760 | 6597 | N/A | 0 | 0 |  | 0 | 0 | 368357
Blue Lake | 2018 | 355189 | 6571 | N/A | 0 | 0 |  | 0 | 0 | 361760
Blue Lake | 2017 | 348610 | 6579 | N/A | 0 | 0 |  | 0 | 0 | 355189
Blue Lake | 2016 | 342125 | 6485 | N/A | 0 | 0 |  | 0 | 0 | 348610
Blue Lake | 2015 | 335643 | 6482 | N/A | 0 | 0 |  | 0 | 0 | 342125
Blue Lake | 2014 | 329101 | 6542 | N/A | 0 | 0 |  | 0 | 0 | 335643
Blue Lake | 2013 | 322366 | 6735 | N/A | 0 | 0 |  | 0 | 0 | 329101
Blue Lake | 2012 | 315587 | 6779 | N/A | 0 | 0 |  | 0 | 0 | 322366
Blue Lake | 2011 | 234430 | 6757 | N/A | 0 | 0 |  | 0 | 0 | 315587
Blue Lake | 2010 | 220864 | 13566 | N/A | 0 | 0 |  | 0 | 0 | 234430
Blue Lake | 2009 | 207306 | 13558 | N/A | 0 | 0 |  | 0 | 0 | 220864
Blue Lake | 2008 | 193685 | 13543 | N/A | 0 | 0 |  | 0 | 0 | 207306
Blue Lake | 2007 | 180119 | 13566 | N/A | 0 | 0 |  | 0 | 0 | 193685
Eureka | 2019 | 4262137.55 | 145527 | N/A | 0 | 1500000 | Humboldt County ($1,500,000) | 0 | 0 | 5907664.55
Eureka | 2018 | 4117150.55 | 144987 | N/A | 0 | 0 |  | 0 | 0 | 4262137.55
Eureka | 2017 | 3972028.55 | 145122 | N/A | 0 | 0 |  | 0 | 0 | 4117150.55
Eureka | 2016 | 4482669.94 | 144056 | N/A | 0 | 0 |  | 654697.39 | 654697.39 | 3972028.55
Eureka | 2015 | 4337306.94 | 145363 | N/A | 0 | 0 |  | 0 | 0 | 4482669.94
Eureka | 2014 | 4191252.94 | 146054 | N/A | 0 | 0 |  | 0 | 0 | 4337306.94
Eureka | 2013 | 4046014.94 | 145238 | N/A | 0 | 0 |  | 0 | 0 | 4191252.94
Eureka | 2012 | 3900656.94 | 145358 | N/A | 0 | 0 |  | 0 | 0 | 4046014.94
Eureka | 2011 | 3754901.94 | 145755 | N/A | 0 | 0 |  | 0 | 0 | 3900656.94
Eureka | 2010 | 3444777.94 | 310124 | N/A | 0 | 0 |  | 0 | 0 | 3754901.94
Eureka | 2009 | 3134894.94 | 309883 | N/A | 0 | 0 |  | 0 | 0 | 3444777.94
Eureka | 2008 | 2822890.94 | 310315 | N/A | 0 | 0 |  | 0 | 0 | 3134894.94
Eureka | 2007 | 2512182.94 | 310708 | N/A | 0 | 0 |  | 0 | 0 | 2822890.94
Ferndale | 2019 | 2902006 | 9102 | N/A | 0 | 0 |  | 0 | 0 | 2911108
Ferndale | 2018 | 2892983 | 9023 | N/A | 0 | 0 |  | 0 | 0 | 2902006
Ferndale | 2017 | 2883931 | 9052 | N/A | 0 | 0 |  | 0 | 0 | 2892983
Ferndale | 2016 | 2874944 | 8987 | N/A | 0 | 0 |  | 0 | 0 | 2883931
Ferndale | 2015 | 468908 | 9036 | N/A | 0 | 2397000 | $2,397,000 (Humboldt County) | 0 | 0 | 2874944
Ferndale | 2014 | 459820 | 9088 | N/A | 0 | 0 |  | 0 | 0 | 468908
Ferndale | 2013 | 450819 | 9001 | N/A | 0 | 0 |  | 0 | 0 | 459820
Ferndale | 2012 | 441846 | 8973 | N/A | 0 | 0 |  | 0 | 0 | 450819
Ferndale | 2011 | 362937 | 9009 | N/A | 0 | 0 |  | 0 | 0 | 441846
Ferndale | 2010 | 343974 | 18963 | N/A | 0 | 0 |  | 0 | 0 | 362937
Ferndale | 2009 | 325020 | 18954 | N/A | 0 | 0 |  | 0 | 0 | 343974
Ferndale | 2008 | 305984 | 18932 | N/A | 0 | 0 |  | 0 | 0 | 325020
Ferndale | 2007 | 287004 | 18980 | N/A | 0 | 0 |  | 0 | 0 | 305984
Fortuna | 2019 | 3730846 | 48616 | N/A | 0 | 0 |  | 0 | 0 | 3779462
Fortuna | 2018 | 3682534 | 48312 | N/A | 0 | 0 |  | 0 | 0 | 3730846
Fortuna | 2017 | 3634438 | 48096 | N/A | 0 | 0 |  | 0 | 0 | 3682534
Fortuna | 2016 | 3586990 | 47448 | N/A | 0 | 0 |  | 0 | 0 | 3634438
Fortuna | 2015 | 2167719 | 47726 | N/A | 0 | 1371545 | $1,371,545 (Humboldt County) | 0 | 0 | 3586990
Fortuna | 2014 | 1016955 | 47963 | N/A | 0 | 1102801 | $1,102,801 (Humboldt County) | 0 | 0 | 2167719
Fortuna | 2013 | 969529 | 47426 | N/A | 0 | 0 |  | 0 | 0 | 1016955
Fortuna | 2012 | 921995 | 47534 | N/A | 0 | 0 |  | 0 | 0 | 969529
Fortuna | 2011 | 873703 | 48292 | N/A | 0 | 0 |  | 0 | 0 | 921995
Fortuna | 2010 | 780518 | 93185 | N/A | 0 | 0 |  | 0 | 0 | 873703
Fortuna | 2009 | 687471 | 93047 | N/A | 0 | 0 |  | 0 | 0 | 780518
Fortuna | 2008 | 593787 | 93126 | N/A | 0 | 0 |  | 0 | 0 | 687471
Fortuna | 2007 | 500934 | 92853 | N/A | 0 | 0 |  | 0 | 0 | 593787
Humboldt County | 2019 | 2586224.56 | 349909 | N/A | 0 | 0 |  | 0 | 0 | 1436133.56
Humboldt County | 2018 | 2240460.56 | 345764 | N/A | 0 | 0 |  | 0 | 0 | 2586224.56
Humboldt County | 2017 | 1893682.56 | 346778 | N/A | 0 | 0 |  | 0 | 0 | 2240460.56
Humboldt County | 2016 | 1550058.56 | 343624 | N/A | 0 | 0 |  | 0 | 0 | 1893682.56
Humboldt County | 2015 | 8534474 | 342985 | N/A | 0 | 0 |  | 3663855.44 | 3663855.44 | 1550058.56
Humboldt County | 2014 | 9162167 | 345108 | N/A | 0 | 0 |  | 0 | 0 | 8534474
Humboldt County | 2013 | 9413228 | 348939 | N/A | 0 | 0 |  | 0 | 0 | 9162167
Humboldt County | 2012 | 9064647 | 348581 | N/A | 0 | 0 |  | 0 | 0 | 9413228
Humboldt County | 2011 | 8718119 | 346528 | N/A | 0 | 0 |  | 0 | 0 | 9064647
Humboldt County | 2010 | 8022840 | 695279 | N/A | 0 | 0 |  | 0 | 0 | 8718119
Humboldt County | 2009 | 7453963 | 693877 | N/A | 0 | 0 |  | 125000 | 125000 | 8022840
Humboldt County | 2008 | 6756484 | 693502 | N/A | 0 | 0 |  | 0 | 0 | 7453963
Humboldt County | 2007 | 6063430 | 693054 | N/A | 0 | 0 |  | 0 | 0 | 6756484
Rio Dell | 2019 | 442263 | 15095 | N/A | 0 | 0 |  | 0 | 0 | 457358
Rio Dell | 2018 | 427263 | 15000 | N/A | 0 | 0 |  | 0 | 0 | 442263
Rio Dell | 2017 | 412354 | 14909 | N/A | 0 | 0 |  | 0 | 0 | 427263
Rio Dell | 2016 | 397649 | 14705 | N/A | 0 | 0 |  | 0 | 0 | 412354
Rio Dell | 2015 | 382792 | 14857 | N/A | 0 | 0 |  | 0 | 0 | 397649
Rio Dell | 2014 | 367892 | 14900 | N/A | 0 | 0 |  | 0 | 0 | 382792
Rio Dell | 2013 | 353071 | 14821 | N/A | 0 | 0 |  | 0 | 0 | 367892
Rio Dell | 2012 | 338309 | 14762 | N/A | 0 | 0 |  | 0 | 0 | 353071
Rio Dell | 2011 | 323597 | 14712 | N/A | 0 | 0 |  | 0 | 0 | 338309
Rio Dell | 2010 | 292627 | 30970 | N/A | 0 | 0 |  | 0 | 0 | 323597
Rio Dell | 2009 | 261729 | 30898 | N/A | 0 | 0 |  | 0 | 0 | 292627
Rio Dell | 2008 | 230616 | 30946 | N/A | 0 | 0 |  | 0 | 0 | 261729
Rio Dell | 2007 | 199645 | 30971 | N/A | 0 | 0 |  | 0 | 0 | 230616
Trinidad | 2019 | -4466 | 1914 | N/A | 0 | 0 |  | 0 | 0 | -2552 | Within 5-year borrow
Trinidad | 2018 | -6360 | 1894 | N/A | 0 | 0 |  | 0 | 0 | -4466 | Within 5-year borrow
Trinidad | 2017 | -8251 | 1891 | N/A | 0 | 0 |  | 0 | 0 | -6360 | Within 5-year borrow
Trinidad | 2016 | -10116 | 1865 | N/A | 0 | 0 |  | 0 | 0 | -8251 | Within 5-year borrow
Trinidad | 2015 | -37122 | 2006 | N/A | 0 | 25000 | $25,000 (Humboldt County) | 0 | 0 | -10116 | Additional research required
Trinidad | 2014 | -39142 | 2020 | N/A | 0 | 0 |  | 0 | 0 | -37122 | Additional research required
Trinidad | 2013 | -41183 | 2041 | N/A | 0 | 0 |  | 0 | 0 | -39142 | Additional research required
Trinidad | 2012 | -43205 | 2022 | N/A | 0 | 0 |  | 0 | 0 | -41183 | Additional research required
Trinidad | 2011 | -45245 | 2040 | N/A | 0 | 0 |  | 0 | 0 | -43205 | Additional research required
Trinidad | 2010 | -49839 | 4594 | N/A | 0 | 0 |  | 0 | 0 | -45245 | Additional research required
Trinidad | 2009 | 70447 | 4591 | N/A | 0 | 0 |  | 124877 | 124877 | -49839 | Additional research required
Trinidad | 2008 | 65847 | 4577 | N/A | 0 | 0 |  | 0 | 0 | 70447
Trinidad | 2007 | 61263 | 4584 | N/A | 0 | 0 |  | 0 | 0 | 65847
Humboldt County Total |  |  | 10953506 |  |  | 6396346 |  | 5678120.69 | 5678120.69
Kern County
Arvin | 2019 | 795234 | 34533 | N/A | 0 | 0 |  | 0 | 0 | 829767
Arvin | 2018 | 761121 | 34113 | N/A | 0 | 0 |  | 0 | 0 | 795234
Arvin | 2017 | 726971 | 34150 | N/A | 0 | 0 |  | 0 | 0 | 761121
Arvin | 2016 | 693213 | 33758 | N/A | 0 | 0 |  | 0 | 0 | 726971
Arvin | 2015 | 659511 | 33702 | N/A | 0 | 0 |  | 0 | 0 | 693213
Arvin | 2014 | 626065 | 33446 | N/A | 0 | 0 |  | 0 | 0 | 659511
Arvin | 2013 | 592297 | 33768 | N/A | 0 | 0 |  | 0 | 0 | 626065
Arvin | 2012 | 558741 | 33556 | N/A | 0 | 0 |  | 0 | 0 | 592297
Arvin | 2011 | 525251 | 33490 | N/A | 0 | 0 |  | 0 | 0 | 558741
Arvin | 2010 | 465929 | 59322 | N/A | 0 | 0 |  | 0 | 0 | 525251
Arvin | 2009 | 406696 | 59233 | N/A | 0 | 0 |  | 0 | 0 | 465929
Arvin | 2008 | 347185 | 59130 | N/A | 0 | 0 |  | 0 | 0 | 406696
Arvin | 2007 | 288698 | 58487 | N/A | 0 | 0 |  | 0 | 0 | 347185
Bakersfield | 2019 | 8103886.28 | 820803 | N/A | 0 | 0 |  | 0 | 0 | 8924689.28
Bakersfield | 2018 | 7287258.28 | 816628 | N/A | 0 | 0 |  | 0 | 0 | 8103886.28
Bakersfield | 2017 | 9896202.82 | 816234 | N/A | 0 | 0 |  | 3425178.54 | 3425178.54 | 7287258.28
Bakersfield | 2016 | 9089654.82 | 806548 | N/A | 0 | 0 |  | 0 | 0 | 9896202.82
Bakersfield | 2015 | 11142616.58 | 807748 | N/A | 0 | 0 |  | 2860709.76 | 2860709.76 | 9089654.82
Bakersfield | 2014 | 11268362 | 807147 | N/A | 0 | 0 |  | 932892.42 | 932892.42 | 11142616.58
Bakersfield | 2013 | 10465129 | 803233 | N/A | 0 | 0 |  | 0 | 0 | 11268362
Bakersfield | 2012 | 10352199 | 800939 | N/A | 0 | 0 |  | 688009 | 688009 | 10465129
Bakersfield | 2011 | 11076429.63 | 799248 | N/A | 0 | 0 |  | 1523478.63 | 1523478.63 | 10352199
Bakersfield | 2010 | 10549191.63 | 1314636 | N/A | 0 | 0 |  | 787398 | 787398 | 11076429.63
Bakersfield | 2009 | 9238839.63 | 1310352 | N/A | 0 | 0 |  | 0 | 0 | 10549191.63
Bakersfield | 2008 | 7927586.63 | 1301998 | N/A | 0 | 0 |  | 0 | 0 | 9238839.63
Bakersfield | 2007 | 6638571.63 | 1289015 | N/A | 0 | 0 |  | 0 | 0 | 7927586.63
Kern County | 2019 | 22514166.38 | 803754 | N/A | 0 | 0 |  | 0 | 0 | 23317920.38
Kern County | 2018 | 22628822.38 | 797344 | N/A | 0 | 0 |  | 0 | 0 | 22514166.38
Kern County | 2017 | 21828930.38 | 799892 | N/A | 0 | 0 |  | 0 | 0 | 22628822.38
Kern County | 2016 | 21034305.38 | 794625 | N/A | 0 | 0 |  | 0 | 0 | 21828930.38
Kern County | 2015 | 23233547.38 | 800758 | N/A | 0 | 0 |  | 0 | 0 | 21034305.38
Kern County | 2014 | 22428942.38 | 804605 | N/A | 0 | 0 |  | 0 | 0 | 23233547.38
Kern County | 2013 | 24336205.38 | 827088 | N/A | 0 | 0 |  | 2734351 | 2734351 | 22428942.38
Kern County | 2012 | 23510397.38 | 825808 | N/A | 0 | 0 |  | 0 | 0 | 24336205.38
Kern County | 2011 | 22686986.38 | 823411 | N/A | 0 | 0 |  | 0 | 0 | 23510397.38
Kern County | 2010 | 23034648.38 | 1809519 | N/A | 0 | 0 |  | 2157181 | 2157181 | 22686986.38
Kern County | 2009 | 21229476.38 | 1805172 | N/A | 0 | 0 |  | 0 | 0 | 23034648.38
Kern County | 2008 | 19412521.38 | 1807690 | N/A | 0 | 0 |  | 0 | 0 | 21229476.38
Kern County | 2007 | 17602832.38 | 1809689 | N/A | 0 | 0 |  | 0 | 0 | 19412521.38
Maricopa | 2019 | 316737 | 5612 | N/A | 0 | 0 |  | 0 | 0 | 322349
Maricopa | 2018 | 311126 | 5611 | N/A | 0 | 0 |  | 0 | 0 | 316737
Maricopa | 2017 | 305490 | 5636 | N/A | 0 | 0 |  | 0 | 0 | 311126
Maricopa | 2016 | 299875 | 5615 | N/A | 0 | 0 |  | 0 | 0 | 305490
Maricopa | 2015 | 294192 | 5683 | N/A | 0 | 0 |  | 0 | 0 | 299875
Maricopa | 2014 | 288478 | 5714 | N/A | 0 | 0 |  | 0 | 0 | 294192
Maricopa | 2013 | 282706 | 5772 | N/A | 0 | 0 |  | 0 | 0 | 288478
Maricopa | 2012 | 276918 | 5788 | N/A | 0 | 0 |  | 0 | 0 | 282706
Maricopa | 2011 | 271158 | 5760 | N/A | 0 | 0 |  | 0 | 0 | 276918
Maricopa | 2010 | 259015 | 12143 | N/A | 0 | 0 |  | 0 | 0 | 271158
Maricopa | 2009 | 246901 | 12114 | N/A | 0 | 0 |  | 0 | 0 | 259015
Maricopa | 2008 | 234721 | 12114 | N/A | 0 | 0 |  | 0 | 0 | 246901
Maricopa | 2007 | 222624 | 12097 | N/A | 0 | 0 |  | 0 | 0 | 234721
Mcfarland | 2019 | 4420179 | 16359 | N/A | 0 | 0 |  | 0 | 0 | 4436538
Mcfarland | 2018 | 3491931 | 16248 | N/A | 0 | 912000 | Kern County ($912,000) | 0 | 0 | 4420179
Mcfarland | 2017 | 3475614 | 16317 | N/A | 0 | 0 |  | 0 | 0 | 3491931
Mcfarland | 2016 | 3459566 | 16048 | N/A | 0 | 0 |  | 0 | 0 | 3475614
Mcfarland | 2015 | 443551 | 16015 | N/A | 0 | 3000000 | $3,000,000 (Kern County) | 0 | 0 | 3459566
Mcfarland | 2014 | 427954 | 15597 | N/A | 0 | 0 |  | 0 | 0 | 443551
Mcfarland | 2013 | 412535 | 15419 | N/A | 0 | 0 |  | 0 | 0 | 427954
Mcfarland | 2012 | 397330 | 15205 | N/A | 0 | 0 |  | 0 | 0 | 412535
Mcfarland | 2011 | 382533 | 14797 | N/A | 0 | 0 |  | 0 | 0 | 397330
Mcfarland | 2010 | 356987 | 25546 | N/A | 0 | 0 |  | 0 | 0 | 382533
Mcfarland | 2009 | 331666 | 25321 | N/A | 0 | 0 |  | 0 | 0 | 356987
Mcfarland | 2008 | 306244 | 25260 | N/A | 0 | 0 |  | 0 | 0 | 331666
Mcfarland | 2007 | 281444 | 24800 | N/A | 0 | 0 |  | 0 | 0 | 306244
Shafter | 2019 | 1326825 | 45130 | N/A | 0 | 0 |  | 0 | 0 | 1371955
Shafter | 2018 | 1282625 | 44200 | N/A | 0 | 0 |  | 0 | 0 | 1326825
Shafter | 2017 | 1239071 | 43554 | N/A | 0 | 0 |  | 0 | 0 | 1282625
Shafter | 2016 | 1196449 | 42622 | N/A | 0 | 0 |  | 0 | 0 | 1239071
Shafter | 2015 | 1153527 | 42922 | N/A | 0 | 0 |  | 0 | 0 | 1196449
Shafter | 2014 | 1110587 | 42940 | N/A | 0 | 0 |  | 0 | 0 | 1153527
Shafter | 2013 | 1066986 | 43601 | N/A | 0 | 0 |  | 0 | 0 | 1110587
Shafter | 2012 | 1023358 | 43628 | N/A | 0 | 0 |  | 0 | 0 | 1066986
Shafter | 2011 | 979013 | 44345 | N/A | 0 | 0 |  | 0 | 0 | 1023358
Shafter | 2010 | 905739 | 73274 | N/A | 0 | 0 |  | 0 | 0 | 979013
Shafter | 2009 | 832664 | 73075 | N/A | 0 | 0 |  | 0 | 0 | 905739
Shafter | 2008 | 759614 | 72551 | N/A | 0 | 0 |  | 0 | 0 | 832664
Shafter | 2007 | 687629 | 71985 | N/A | 0 | 0 |  | 0 | 0 | 759614
Taft | 2019 | 1211306 | 28537 | N/A | 0 | 0 |  | 0 | 0 | 1239843
Taft | 2018 | 1183056 | 28250 | N/A | 0 | 0 |  | 0 | 0 | 1211306
Taft | 2017 | 1154733 | 28323 | N/A | 0 | 0 |  | 0 | 0 | 1183056
Taft | 2016 | 1126595 | 28138 | N/A | 0 | 0 |  | 0 | 0 | 1154733
Taft | 2015 | 1098143 | 28452 | N/A | 0 | 0 |  | 0 | 0 | 1126595
Taft | 2014 | 1069559 | 28584 | N/A | 0 | 0 |  | 0 | 0 | 1098143
Taft | 2013 | 1040606 | 28953 | N/A | 0 | 0 |  | 0 | 0 | 1069559
Taft | 2012 | 1011619 | 28987 | N/A | 0 | 0 |  | 0 | 0 | 1040606
Taft | 2011 | 981860 | 29759 | N/A | 0 | 0 |  | 0 | 0 | 1011619
Taft | 2010 | 923578 | 58282 | N/A | 0 | 0 |  | 0 | 0 | 981860
Taft | 2009 | 865311 | 58267 | N/A | 0 | 0 |  | 0 | 0 | 923578
Taft | 2008 | 806835 | 58134 | N/A | 0 | 0 |  | 0 | 0 | 865311
Taft | 2007 | 748777 | 58058 | N/A | 0 | 0 |  | 0 | 0 | 806835
Wasco | 2019 | 1744109 | 49641 | N/A | 0 | 0 |  | 0 | 0 | 1793750
Wasco | 2018 | 1695939 | 48170 | N/A | 0 | 0 |  | 0 | 0 | 1744109
Wasco | 2017 | 1647865 | 48074 | N/A | 0 | 0 |  | 0 | 0 | 1695939
Wasco | 2016 | 1600317 | 47548 | N/A | 0 | 0 |  | 0 | 0 | 1647865
Wasco | 2015 | 1552402 | 47915 | N/A | 0 | 0 |  | 0 | 0 | 1600317
Wasco | 2014 | 1504255 | 48147 | N/A | 0 | 0 |  | 0 | 0 | 1552402
Wasco | 2013 | 1455496 | 48759 | N/A | 0 | 0 |  | 0 | 0 | 1504255
Wasco | 2012 | 1406980 | 48516 | N/A | 0 | 0 |  | 0 | 0 | 1455496
Wasco | 2011 | 1357226 | 49754 | N/A | 0 | 0 |  | 0 | 0 | 1406980
Wasco | 2010 | 1267738 | 89488 | N/A | 0 | 0 |  | 0 | 0 | 1357226
Wasco | 2009 | 1178363 | 89375 | N/A | 0 | 0 |  | 0 | 0 | 1267738
Wasco | 2008 | 1089072 | 88728 | N/A | 0 | 0 |  | 0 | 0 | 1178363
Wasco | 2007 | 1001282 | 87790 | N/A | 0 | 0 |  | 0 | 0 | 1089072
Kern County Total |  |  | 29853619 |  |  | 3912000 |  | 15109198.35 | 15109198.35
Kings County
Avenal | 2019 | 797783 | 23582 | N/A | 0 | 0 |  | 0 | 0 | 821365
Avenal | 2018 | 774280 | 23503 | N/A | 0 | 0 |  | 0 | 0 | 797783
Avenal | 2017 | 750683 | 23597 | N/A | 0 | 0 |  | 0 | 0 | 774280
Avenal | 2016 | 727444 | 23239 | N/A | 0 | 0 |  | 0 | 0 | 750683
Avenal | 2015 | 704034 | 23410 | N/A | 0 | 0 |  | 0 | 0 | 727444
Avenal | 2014 | 680543 | 23491 | N/A | 0 | 0 |  | 0 | 0 | 704034
Avenal | 2013 | 657011 | 23532 | N/A | 0 | 0 |  | 0 | 0 | 680543
Avenal | 2012 | 633448 | 23563 | N/A | 0 | 0 |  | 0 | 0 | 657011
Avenal | 2011 | 610219 | 23229 | N/A | 0 | 0 |  | 0 | 0 | 633448
Avenal | 2010 | 565679 | 44540 | N/A | 0 | 0 |  | 0 | 0 | 610219
Avenal | 2009 | 521211 | 44468 | N/A | 0 | 0 |  | 0 | 0 | 565679
Avenal | 2008 | 476812 | 44136 | N/A | 0 | 0 |  | 0 | 0 | 521211
Avenal | 2007 | 432627 | 44185 | N/A | 0 | 0 |  | 0 | 0 | 476812
Corcoran | 2019 | 0 | 38880 | N/A | 0 | 0 |  | 0 | 0 | 0
Corcoran | 2018 | 0 | 38962 | N/A | 0 | 0 |  | 0 | 0 | 0
Corcoran | 2017 | 0 | 38901 | N/A | 0 | 0 |  | 0 | 0 | 0
Corcoran | 2016 | 0 | 38577 | N/A | 0 | 0 |  | 0 | 0 | 0
Corcoran | 2015 | 1055361 | 39016 | N/A | 0 | 0 |  | 0 | 0 | 0
Corcoran | 2014 | 1016115 | 39246 | N/A | 0 | 0 |  | 0 | 0 | 1055361
Corcoran | 2013 | 976469 | 39646 | N/A | 0 | 0 |  | 0 | 0 | 1016115
Corcoran | 2012 | 936743 | 39726 | N/A | 0 | 0 |  | 0 | 0 | 976469
Corcoran | 2011 | 901168 | 35575 | N/A | 0 | 0 |  | 0 | 0 | 936743
Corcoran | 2010 | 836406 | 64762 | N/A | 0 | 0 |  | 0 | 0 | 901168
Corcoran | 2009 | 771995 | 64411 | N/A | 0 | 0 |  | 0 | 0 | 836406
Corcoran | 2008 | 707334 | 64257 | N/A | 0 | 0 |  | 0 | 0 | 771995
Corcoran | 2007 | 643713 | 63621 | N/A | 0 | 0 |  | 0 | 0 | 707334
Kings County | 2019 | 1697811 | 103326 | N/A | 0 | 0 |  | 0 | 0 | 1801137
Kings County | 2018 | 2264855 | 102956 | N/A | 0 | 0 |  | 0 | 0 | 1697811
Kings County | 2017 | 2161397 | 103458 | N/A | 0 | 0 |  | 0 | 0 | 2264855
Kings County | 2016 | 2058562 | 102835 | N/A | 0 | 0 |  | 0 | 0 | 2161397
Kings County | 2015 | 1956018 | 102544 | N/A | 0 | 0 |  | 0 | 0 | 2058562
Kings County | 2014 | 1853170 | 102848 | N/A | 0 | 0 |  | 0 | 0 | 1956018
Kings County | 2013 | 1747010 | 106160 | N/A | 0 | 0 |  | 0 | 0 | 1853170
Kings County | 2012 | 3991416 | 105594 | N/A | 0 | 0 |  | 2350000 | 2350000 | 1747010
Kings County | 2011 | 3880800 | 110616 | N/A | 0 | 0 |  | 0 | 0 | 3991416
Kings County | 2010 | 3638265 | 242535 | N/A | 0 | 0 |  | 0 | 0 | 3880800
Kings County | 2009 | 3397681 | 240584 | N/A | 0 | 0 |  | 0 | 0 | 3638265
Kings County | 2008 | 3156476 | 239968 | N/A | 0 | 0 |  | 0 | 0 | 3397681
Kings County | 2007 | 2917222 | 239254 | N/A | 0 | 0 |  | 0 | 0 | 3156476
Lemoore | 2019 | -488464.44 | 61847 | N/A | 0 | 0 |  | 0 | 0 | -426617.44 | Borrowed beyond 5 years (see CPUC Decision 11-05-018)
Lemoore | 2018 | -550037.44 | 61573 | N/A | 0 | 0 |  | 0 | 0 | -488464.44 | Borrowed beyond 5 years (see CPUC Decision 11-05-018)
Lemoore | 2017 | -611379.44 | 61342 | N/A | 0 | 0 |  | 0 | 0 | -550037.44 | Borrowed beyond 5 years (see CPUC Decision 11-05-018)
Lemoore | 2016 | -671713.44 | 60334 | N/A | 0 | 0 |  | 0 | 0 | -611379.44 | Borrowed beyond 5 years (see CPUC Decision 11-05-018)
Lemoore | 2015 | -732468.44 | 60755 | N/A | 0 | 0 |  | 0 | 0 | -671713.44 | Borrowed beyond 5 years (see CPUC Decision 11-05-018)
Lemoore | 2014 | -793314.44 | 60846 | N/A | 0 | 0 |  | 0 | 0 | -732468.44 | Borrowed beyond 5 years (see CPUC Decision 11-05-018)
Lemoore | 2013 | -853842.44 | 60528 | N/A | 0 | 0 |  | 0 | 0 | -793314.44 | Borrowed beyond 5 years (see CPUC Decision 11-05-018)
Lemoore | 2012 | 1026613 | 59918 | N/A | 0 | 0 |  | 1940373.44 | 1940373.44 | -853842.44 | Borrowed beyond 5 years (see CPUC Decision 11-05-018)
Lemoore | 2011 | 967027 | 59586 | N/A | 0 | 0 |  | 0 | 0 | 1026613
Lemoore | 2010 | 865743 | 101284 | N/A | 0 | 0 |  | 0 | 0 | 967027
Lemoore | 2009 | 764389 | 101354 | N/A | 0 | 0 |  | 0 | 0 | 865743
Lemoore | 2008 | 662431 | 101272 | N/A | 0 | 0 |  | 0 | 0 | 764389
Lemoore | 2007 | 561616 | 100815 | N/A | 0 | 0 |  | 0 | 0 | 662431
Kings County Total |  |  | 3848187 |  |  | 0 |  | 4290373.44 | 4290373.44
Lake County
Clearlake | 2019 | 3144109 | 84732 | N/A | 0 | 0 |  | 0 | 0 | 3228841
Clearlake | 2018 | 3058702 | 85407 | N/A | 0 | 0 |  | 0 | 0 | 3144109
Clearlake | 2017 | 2972878 | 85824 | N/A | 0 | 0 |  | 0 | 0 | 3058702
Clearlake | 2016 | 2887955 | 84923 | N/A | 0 | 0 |  | 0 | 0 | 2972878
Clearlake | 2015 | 2801769 | 86186 | N/A | 0 | 0 |  | 0 | 0 | 2887955
Clearlake | 2014 | 2715125 | 86644 | N/A | 0 | 0 |  | 0 | 0 | 2801769
Clearlake | 2013 | 2627302 | 87823 | N/A | 0 | 0 |  | 0 | 0 | 2715125
Clearlake | 2012 | 2539406 | 87896 | N/A | 0 | 0 |  | 0 | 0 | 2627302
Clearlake | 2011 | 2541878 | 87333 | N/A | 0 | 0 |  | 89805 | 0 | 2539406
Clearlake | 2010 | 2371568 | 170310 | N/A | 0 | 0 |  | 0 | 0 | 2541878
Clearlake | 2009 | 2201513 | 170055 | N/A | 0 | 0 |  | 0 | 0 | 2371568
Clearlake | 2008 | 2031026 | 169487 | N/A | 0 | 0 |  | 0 | 0 | 2201513
Clearlake | 2007 | 1863034 | 167992 | N/A | 0 | 0 |  | 0 | 0 | 2031026
Lake County | 2019 | 8431163.47 | 282929 | N/A | 0 | 0 |  | 0 | 0 | 8714092.47
Lake County | 2018 | 8151023.47 | 280140 | N/A | 0 | 0 |  | 0 | 0 | 8431163.47
Lake County | 2017 | 7870884.47 | 280139 | N/A | 0 | 0 |  | 0 | 0 | 8151023.47
Lake County | 2016 | 7584644.47 | 286240 | N/A | 0 | 0 |  | 0 | 0 | 7870884.47
Lake County | 2015 | 7295771.47 | 288873 | N/A | 0 | 0 |  | 0 | 0 | 7584644.47
Lake County | 2014 | 7005803.47 | 289968 | N/A | 0 | 0 |  | 0 | 0 | 7295771.47
Lake County | 2013 | 7523674.47 | 290964 | N/A | 0 | 0 |  | 808835 | 808835 | 7005803.47
Lake County | 2012 | 7232796.47 | 290878 | N/A | 0 | 0 |  | 0 | 0 | 7523674.47
Lake County | 2011 | 6941696.47 | 291100 | N/A | 0 | 0 |  | 0 | 0 | 7232796.47
Lake County | 2010 | 7165432.47 | 560546 | N/A | 0 | 0 |  | 784282 | 784282 | 6941696.47
Lake County | 2009 | 7549580 | 559532 | N/A | 0 | 0 |  | 943679.53 | 943679.53 | 7165432.47
Lake County | 2008 | 6987172 | 559061 | N/A | 0 | 0 |  | 0 | 0 | 7549580
Lake County | 2007 | 6429541 | 557631 | N/A | 0 | 0 |  | 0 | 0 | 6987172
Lakeport | 2019 | 960016 | 27629 | N/A | 0 | 0 |  | 0 | 0 | 987645
Lakeport | 2018 | 932513 | 27503 | N/A | 0 | 0 |  | 0 | 0 | 960016
Lakeport | 2017 | 904901 | 27612 | N/A | 0 | 0 |  | 0 | 0 | 932513
Lakeport | 2016 | 877499 | 27402 | N/A | 0 | 0 |  | 0 | 0 | 904901
Lakeport | 2015 | 849814 | 27685 | N/A | 0 | 0 |  | 0 | 0 | 877499
Lakeport | 2014 | 822205 | 27609 | N/A | 0 | 0 |  | 0 | 0 | 849814
Lakeport | 2013 | 794678 | 27527 | N/A | 0 | 0 |  | 0 | 0 | 822205
Lakeport | 2012 | 767086 | 27592 | N/A | 0 | 0 |  | 0 | 0 | 794678
Lakeport | 2011 | 738912 | 28174 | N/A | 0 | 0 |  | 0 | 0 | 767086
Lakeport | 2010 | 681089 | 57823 | N/A | 0 | 0 |  | 0 | 0 | 738912
Lakeport | 2009 | 623269 | 57820 | N/A | 0 | 0 |  | 0 | 0 | 681089
Lakeport | 2008 | 565611 | 57339 | N/A | 0 | 0 |  | 0 | 0 | 623269
Lakeport | 2007 | 508434 | 57177 | N/A | 0 | 0 |  | 0 | 0 | 565611
Lake County Total |  |  | 6751505 |  |  | 0 |  | 2626601.53 | 2536796.53
Lassen County
Lassen County | 2019 | 410587 | 10133 | N/A | 0 | 0 |  | 0 | 0 | 420720
Lassen County | 2018 | 401085 | 9502 | N/A | 0 | 0 |  | 0 | 0 | 410587
Lassen County | 2017 | 391568 | 9517 | N/A | 0 | 0 |  | 0 | 0 | 401085
Lassen County | 2016 | 382100 | 9468 | N/A | 0 | 0 |  | 0 | 0 | 391568
Lassen County | 2015 | 372633 | 9467 | N/A | 0 | 0 |  | 0 | 0 | 382100
Lassen County | 2014 | 363175 | 9458 | N/A | 0 | 0 |  | 0 | 0 | 372633
Lassen County | 2013 | 353452 | 9723 | N/A | 0 | 0 |  | 0 | 0 | 363175
Lassen County | 2012 | 343756 | 9696 | N/A | 0 | 0 |  | 0 | 0 | 353452
Lassen County | 2011 | 334057 | 9699 | N/A | 0 | 0 |  | 0 | 0 | 343756
Lassen County | 2010 | 313351 | 20706 | N/A | 0 | 0 |  | 0 | 0 | 334057
Lassen County | 2009 | 292699 | 20652 | N/A | 0 | 0 |  | 0 | 0 | 313351
Lassen County | 2008 | 271924 | 20664 | N/A | 0 | 0 |  | 0 | 0 | 292699
Lassen County | 2007 | 250954 | 20970 | N/A | 0 | 0 |  | 0 | 0 | 271924
Lassen County Total |  |  | 169655 |  |  | 0 |  | 0 | 0
Madera County
Chowchilla | 2019 | 2350807 | 35130 | N/A | 0 | 0 |  | 0 | 0 | 2385937
Chowchilla | 2018 | 2315991 | 34816 | N/A | 0 | 0 |  | 0 | 0 | 2350807
Chowchilla | 2017 | 2281160 | 34831 | N/A | 0 | 0 |  | 0 | 0 | 2315991
Chowchilla | 2016 | 2246699 | 34461 | N/A | 0 | 0 |  | 0 | 0 | 2281160
Chowchilla | 2015 | 2211693 | 35006 | N/A | 0 | 0 |  | 0 | 0 | 2246699
Chowchilla | 2014 | 1176608 | 35085 | N/A | 0 | 1000000 | $1,000,000 (Madera County) | 0 | 0 | 2211693
Chowchilla | 2013 | 1141214 | 35394 | N/A | 0 | 0 |  | 0 | 0 | 1176608
Chowchilla | 2012 | 1105429 | 35785 | N/A | 0 | 0 |  | 0 | 0 | 1141214
Chowchilla | 2011 | 1071099 | 34330 | N/A | 0 | 0 |  | 0 | 0 | 1105429
Chowchilla | 2010 | 1008779 | 62320 | N/A | 0 | 0 |  | 0 | 0 | 1071099
Chowchilla | 2009 | 946503 | 62276 | N/A | 0 | 0 |  | 0 | 0 | 1008779
Chowchilla | 2008 | 883980 | 62132 | N/A | 0 | 0 |  | 0 | 0 | 946503
Chowchilla | 2007 | 822005 | 61975 | N/A | 0 | 0 |  | 0 | 0 | 883980
Madera | 2019 | -17369.38 | 131195 | N/A | 0 | 0 |  | 0 | 0 | 113825.62
Madera | 2018 | -147981.38 | 130612 | N/A | 0 | 0 |  | 0 | 0 | -17369.38 | Within 5-year borrow
Madera | 2017 | -278561.38 | 130580 | N/A | 0 | 0 |  | 0 | 0 | -147981.38 | Within 5-year borrow
Madera | 2016 | -407679.38 | 129118 | N/A | 0 | 0 |  | 0 | 0 | -278561.38 | Within 5-year borrow
Madera | 2015 | -1037393.38 | 129714 | N/A | 0 | 500000 | $500,000 (Madera County) | 0 | 0 | -407679.38 | Within 5-year borrow
Madera | 2014 | 1816165.01 | 130028 | N/A | 0 | 0 |  | 2983586.39 | 2983586.39 | -1037393.38 | Borrowed beyond 5 years (see AL 4553-E)
Madera | 2013 | 1685677.01 | 130488 | N/A | 0 | 0 |  | 0 | 0 | 1816165.01
Madera | 2012 | 1555466.01 | 130211 | N/A | 0 | 0 |  | 0 | 0 | 1685677.01
Madera | 2011 | 1331080.46 | 130676 | N/A | 0 | 0 |  | -93709.55 | -93709.55 | 1555466.01
Madera | 2010 | 1112446.46 | 218634 | N/A | 0 | 0 |  | 0 | 0 | 1331080.46
Madera | 2009 | 893945.46 | 218501 | N/A | 0 | 0 |  | 0 | 0 | 1112446.46
Madera | 2008 | 675145.46 | 217308 | N/A | 0 | 0 |  | 0 | 0 | 893945.46
Madera | 2007 | 459311.46 | 215834 | N/A | 0 | 0 |  | 0 | 0 | 675145.46
Madera County | 2019 | 6323766.02 | 408469 | N/A | 0 | 0 |  | 3246486.15 | 3246486.15 | 3485748.87
Madera County | 2018 | 5919815.02 | 403951 | N/A | 0 | 0 |  | 0 | 0 | 6323766.02
Madera County | 2017 | 5516842.02 | 402973 | N/A | 0 | 0 |  | 0 | 0 | 5919815.02
Madera County | 2016 | 6651125.24 | 399267 | N/A | 0 | 0 |  | 1533550.22 | 1533550.22 | 5516842.02
Madera County | 2015 | 6748916.24 | 402209 | N/A | 0 | 0 |  | 0 | 0 | 6651125.24
Madera County | 2014 | 7346141.24 | 402775 | N/A | 0 | 0 |  | 0 | 0 | 6748916.24
Madera County | 2013 | 10317088.24 | 411611 | N/A | 0 | 0 |  | 3382558 | 3382558 | 7346141.24
Madera County | 2012 | 9906703.24 | 410385 | N/A | 0 | 0 |  | 0 | 0 | 10317088.24
Madera County | 2011 | 9582053.79 | 410571 | N/A | 0 | 0 |  | 85921.55 | 85921.55 | 9906703.24
Madera County | 2010 | 8841599.79 | 740454 | N/A | 0 | 0 |  | 0 | 0 | 9582053.79
Madera County | 2009 | 8110626 | 737230 | N/A | 0 | 0 |  | 6256.21 | 0 | 8841599.79
Madera County | 2008 | 7370325 | 735637 | N/A | 0 | 0 |  | 0 | 0 | 8110626
Madera County | 2007 | 6637124 | 733201 | N/A | 0 | 0 |  | 0 | 0 | 7370325
Madera County Total |  |  | 9205173 |  |  | 1500000 |  | 11144648.97 | 11138392.76
Marin County
Belvedere | 2019 | -268409 | 6036 | N/A | 0 | 0 |  | 0 | 0 | -262373 | Borrowed beyond 5 years (see AL 4553-E)
Belvedere | 2018 | -274439 | 6030 | N/A | 0 | 0 |  | 0 | 0 | -268409 | Borrowed beyond 5 years (see AL 4553-E)
Belvedere | 2017 | -280494 | 6055 | N/A | 0 | 0 |  | 0 | 0 | -274439 | Borrowed beyond 5 years (see AL 4553-E)
Belvedere | 2016 | -286529 | 6035 | N/A | 0 | 0 |  | 0 | 0 | -280494 | Borrowed beyond 5 years (see AL 4553-E)
Belvedere | 2015 | -292637 | 6108 | N/A | 0 | 0 |  | 0 | 0 | -286529 | Borrowed beyond 5 years (see AL 4553-E)
Belvedere | 2014 | -298795 | 6158 | N/A | 0 | 0 |  | 0 | 0 | -292637 | Borrowed beyond 5 years (see AL 4553-E)
Belvedere | 2013 | 158062 | 6470 | N/A | 0 | 0 |  | 463327 | 463327 | -298795 | Borrowed beyond 5 years (see AL 4553-E)
Belvedere | 2012 | 150667 | 7395 | N/A | 0 | 0 |  | 0 | 0 | 158062
Belvedere | 2011 | 143138 | 7529 | N/A | 0 | 0 |  | 0 | 0 | 150667
Belvedere | 2010 | 124356 | 18782 | N/A | 0 | 0 |  | 0 | 0 | 143138
Belvedere | 2009 | 227295 | 19190 | N/A | 0 | 0 |  | 122129 | 122129 | 124356
Belvedere | 2008 | 207711 | 19486 | N/A | 0 | 0 |  | 0 | 0 | 227295
Belvedere | 2007 | 188151 | 19560 | N/A | 0 | 0 |  | 0 | 0 | 207711
Corte Madera | 2019 | 226016.48 | 40728 | N/A | 0 | 0 |  | 0 | 0 | 266744.48
Corte Madera | 2018 | 185378.48 | 40638 | N/A | 0 | 0 |  | 0 | 0 | 226016.48
Corte Madera | 2017 | 144560.48 | 40818 | N/A | 0 | 0 |  | 0 | 0 | 185378.48
Corte Madera | 2016 | 104098.48 | 40462 | N/A | 0 | 0 |  | 0 | 0 | 144560.48
Corte Madera | 2015 | 63822.48 | 40276 | N/A | 0 | 0 |  | 0 | 0 | 104098.48
Corte Madera | 2014 | 23336.48 | 40486 | N/A | 0 | 0 |  | 0 | 0 | 63822.48
Corte Madera | 2013 | -16962.52 | 40299 | N/A | 0 | 0 |  | 0 | 0 | 23336.48
Corte Madera | 2012 | -57365.52 | 40403 | N/A | 0 | 0 |  | 0 | 0 | -16962.52 | Within 5-year borrow
Corte Madera | 2011 | -97988.52 | 40623 | N/A | 0 | 0 |  | 0 | 0 | -57365.52 | Within 5-year borrow
Corte Madera | 2010 | -180853.52 | 82865 | N/A | 0 | 0 |  | 0 | 0 | -97988.52 | Within 5-year borrow
Corte Madera | 2009 | 967912 | 82824 | N/A | 0 | 0 |  | 1231589.52 | 1231589.52 | -180853.52 | Within 5-year borrow
Corte Madera | 2008 | 884298 | 83139 | N/A | 0 | 0 |  | 0 | 0 | 967912
Corte Madera | 2007 | 801015 | 83283 | N/A | 0 | 0 |  | 0 | 0 | 884298
Fairfax | 2019 | 611201 | 36159 | N/A | 0 | 0 |  | 0 | 0 | 647360
Fairfax | 2018 | 575173 | 36028 | N/A | 0 | 0 |  | 0 | 0 | 611201
Fairfax | 2017 | 539020 | 36153 | N/A | 0 | 0 |  | 0 | 0 | 575173
Fairfax | 2016 | 503120 | 35900 | N/A | 0 | 0 |  | 0 | 0 | 539020
Fairfax | 2015 | 466962 | 36158 | N/A | 0 | 0 |  | 0 | 0 | 503120
Fairfax | 2014 | 430632 | 36330 | N/A | 0 | 0 |  | 0 | 0 | 466962
Fairfax | 2013 | 394340 | 36292 | N/A | 0 | 0 |  | 0 | 0 | 430632
Fairfax | 2012 | 357740 | 36600 | N/A | 0 | 0 |  | 0 | 0 | 394340
Fairfax | 2011 | 321132 | 36608 | N/A | 0 | 0 |  | 0 | 0 | 357740
Fairfax | 2010 | 240197 | 80935 | N/A | 0 | 0 |  | 0 | 0 | 321132
Fairfax | 2009 | 159317 | 80880 | N/A | 0 | 0 |  | 0 | 0 | 240197
Fairfax | 2008 | 77880 | 81012 | N/A | 0 | 0 |  | 0 | 0 | 159317
Fairfax | 2007 | -3293 | 81173 | N/A | 0 | 0 |  | 0 | 0 | 77880
Larkspur | 2019 | 1426966 | 47308 | N/A | 0 | 0 |  | 0 | 0 | 1474274
Larkspur | 2018 | 1379682 | 47284 | N/A | 0 | 0 |  | 0 | 0 | 1426966
Larkspur | 2017 | 1332210 | 47472 | N/A | 0 | 0 |  | 0 | 0 | 1379682
Larkspur | 2016 | 1285051 | 47159 | N/A | 0 | 0 |  | 0 | 0 | 1332210
Larkspur | 2015 | 1237477 | 47574 | N/A | 0 | 0 |  | 0 | 0 | 1285051
Larkspur | 2014 | 1189818 | 47659 | N/A | 0 | 0 |  | 0 | 0 | 1237477
Larkspur | 2013 | 1142113 | 47705 | N/A | 0 | 0 |  | 0 | 0 | 1189818
Larkspur | 2012 | 1094307 | 47806 | N/A | 0 | 0 |  | 0 | 0 | 1142113
Larkspur | 2011 | 1046518 | 47789 | N/A | 0 | 0 |  | 0 | 0 | 1094307
Larkspur | 2010 | 951008 | 95510 | N/A | 0 | 0 |  | 0 | 0 | 1046518
Larkspur | 2009 | 855638 | 95370 | N/A | 0 | 0 |  | 0 | 0 | 951008
Larkspur | 2008 | 759570 | 95515 | N/A | 0 | 0 |  | 0 | 0 | 855638
Larkspur | 2007 | 663737 | 95833 | N/A | 0 | 0 |  | 0 | 0 | 759570
Marin County | 2019 | 3865254.19 | 269354 | N/A | 0 | 0 |  | 0 | 0 | 4134608.19
Marin County | 2018 | 3596916.19 | 268338 | N/A | 0 | 0 |  | 0 | 0 | 3865254.19
Marin County | 2017 | 3327758.19 | 269158 | N/A | 0 | 0 |  | 0 | 0 | 3596916.19
Marin County | 2016 | 3060473.19 | 267285 | N/A | 0 | 0 |  | 0 | 0 | 3327758.19
Marin County | 2015 | 2790570.19 | 269903 | N/A | 0 | 0 |  | 0 | 0 | 3060473.19
Marin County | 2014 | 2519502.19 | 271068 | N/A | 0 | 0 |  | 0 | 0 | 2790570.19
Marin County | 2013 | 2248362.19 | 271140 | N/A | 0 | 0 |  | 0 | 0 | 2519502.19
Marin County | 2012 | 1976783.19 | 271579 | N/A | 0 | 0 |  | 0 | 0 | 2248362.19
Marin County | 2011 | 1705419.19 | 271364 | N/A | 0 | 0 |  | 0 | 0 | 1976783.19
Marin County | 2010 | 2683901.19 | 565706 | N/A | 0 | 0 |  | 1544188 | 1544188 | 1705419.19
Marin County | 2009 | 6527881 | 565631 | N/A | 0 | 0 |  | 4409610.81 | 4409610.81 | 2683901.19
Marin County | 2008 | 5958530 | 566202 | N/A | 0 | 0 |  | 0 | 0 | 6527881
Marin County | 2007 | 5390984 | 567546 | N/A | 0 | 0 |  | 0 | 0 | 5958530
Mill Valley | 2019 | -736197.66 | 61858 | N/A | 0 | 0 |  | 0 | 0 | -674339.66 | Borrowed beyond 5 years (see AL 2426-E)
Mill Valley | 2018 | -797850.66 | 61653 | N/A | 0 | 0 |  | 0 | 0 | -736197.66 | Borrowed beyond 5 years (see AL 2426-E)
Mill Valley | 2017 | -859721.66 | 61871 | N/A | 0 | 0 |  | 0 | 0 | -797850.66 | Borrowed beyond 5 years (see AL 2426-E)
Mill Valley | 2016 | -921322.66 | 61601 | N/A | 0 | 0 |  | 0 | 0 | -859721.66 | Borrowed beyond 5 years (see AL 2426-E)
Mill Valley | 2015 | -983422.66 | 62100 | N/A | 0 | 0 |  | 0 | 0 | -921322.66 | Borrowed beyond 5 years (see AL 2426-E)
Mill Valley | 2014 | -1045841.66 | 62419 | N/A | 0 | 0 |  | 0 | 0 | -983422.66 | Borrowed beyond 5 years (see AL 2426-E)
Mill Valley | 2013 | -1109007.66 | 63166 | N/A | 0 | 0 |  | 0 | 0 | -1045841.66 | Borrowed beyond 5 years (see AL 2426-E)
Mill Valley | 2012 | -1172236.66 | 63229 | N/A | 0 | 0 |  | 0 | 0 | -1109007.66 | Borrowed beyond 5 years (see AL 2426-E)
Mill Valley | 2011 | -1234968.66 | 62732 | N/A | 0 | 0 |  | 0 | 0 | -1172236.66 | Borrowed beyond 5 years (see AL 2426-E)
Mill Valley | 2010 | -1373259.66 | 138291 | N/A | 0 | 0 |  | 0 | 0 | -1234968.66 | Borrowed beyond 5 years (see AL 2426-E)
Mill Valley | 2009 | -1511379.66 | 138120 | N/A | 0 | 0 |  | 0 | 0 | -1373259.66 | Borrowed beyond 5 years (see AL 2426-E)
Mill Valley | 2008 | 1350386 | 138097 | N/A | 0 | 0 |  | 3000582.66 | 3000582.66 | -1511379.66 | Borrowed beyond 5 years (see AL 2426-E)
Mill Valley | 2007 | 1212347 | 138039 | N/A | 0 | 0 |  | 0 | 0 | 1350386
Novato | 2019 | 4271592 | 155889 | N/A | 0 | 0 |  | 0 | 0 | 4427481
Novato | 2018 | 4115685 | 155907 | N/A | 0 | 0 |  | 0 | 0 | 4271592
Novato | 2017 | 3959265 | 156420 | N/A | 0 | 0 |  | 0 | 0 | 4115685
Novato | 2016 | 3803635 | 155630 | N/A | 0 | 0 |  | 0 | 0 | 3959265
Novato | 2015 | 3646222 | 157413 | N/A | 0 | 0 |  | 0 | 0 | 3803635
Novato | 2014 | 3487890 | 158332 | N/A | 0 | 0 |  | 0 | 0 | 3646222
Novato | 2013 | 3330524 | 157366 | N/A | 0 | 0 |  | 0 | 0 | 3487890
Novato | 2012 | 3173071 | 157453 | N/A | 0 | 0 |  | 0 | 0 | 3330524
Novato | 2011 | 3019246 | 157809 | N/A | 0 | 0 |  | 3984 | 3984 | 3173071
Novato | 2010 | 2714476 | 304770 | N/A | 0 | 0 |  | 0 | 0 | 3019246
Novato | 2009 | 2409455 | 305021 | N/A | 0 | 0 |  | 0 | 0 | 2714476
Novato | 2008 | 2101798 | 305814 | N/A | 0 | 0 |  | 0 | 0 | 2409455
Novato | 2007 | 1794940 | 306858 | N/A | 0 | 0 |  | 0 | 0 | 2101798
Ross | 2019 | 250630 | 9811 | N/A | 0 | 0 |  | 0 | 0 | 260441
Ross | 2018 | 240822 | 9808 | N/A | 0 | 0 |  | 0 | 0 | 250630
Ross | 2017 | 230962 | 9860 | N/A | 0 | 0 |  | 0 | 0 | 240822
Ross | 2016 | 221228 | 9734 | N/A | 0 | 0 |  | 0 | 0 | 230962
Ross | 2015 | 211391 | 9837 | N/A | 0 | 0 |  | 0 | 0 | 221228
Ross | 2014 | 201523 | 9868 | N/A | 0 | 0 |  | 0 | 0 | 211391
Ross | 2013 | 191403 | 10120 | N/A | 0 | 0 |  | 0 | 0 | 201523
Ross | 2012 | 181266 | 10137 | N/A | 0 | 0 |  | 0 | 0 | 191403
Ross | 2011 | 171239 | 10027 | N/A | 0 | 0 |  | 0 | 0 | 181266
Ross | 2010 | 149756 | 21483 | N/A | 0 | 0 |  | 0 | 0 | 171239
Ross | 2009 | 128294 | 21462 | N/A | 0 | 0 |  | 0 | 0 | 149756
Ross | 2008 | 106747 | 21432 | N/A | 0 | 0 |  | 0 | 0 | 128294
Ross | 2007 | 85279 | 21468 | N/A | 0 | 0 |  | 0 | 0 | 106747
San Anselmo | 2019 | 738931 | 60785 | N/A | 0 | 0 |  | 0 | 0 | 799716
San Anselmo | 2018 | 678215 | 60716 | N/A | 0 | 0 |  | 0 | 0 | 738931
San Anselmo | 2017 | 617290 | 60925 | N/A | 0 | 0 |  | 0 | 0 | 678215
San Anselmo | 2016 | 556820 | 60470 | N/A | 0 | 0 |  | 0 | 0 | 617290
San Anselmo | 2015 | 495861 | 60959 | N/A | 0 | 0 |  | 0 | 0 | 556820
San Anselmo | 2014 | 434611 | 61250 | N/A | 0 | 0 |  | 0 | 0 | 495861
San Anselmo | 2013 | 1842280 | 61084 | N/A | 0 | 0 |  | 1468753 | 1468753 | 434611
San Anselmo | 2012 | 1781270 | 61010 | N/A | 0 | 0 |  | 0 | 0 | 1842280
San Anselmo | 2011 | 1719788 | 61482 | N/A | 0 | 0 |  | 0 | 0 | 1781270
San Anselmo | 2010 | 1578974 | 140814 | N/A | 0 | 0 |  | 0 | 0 | 1719788
San Anselmo | 2009 | 1438298 | 140676 | N/A | 0 | 0 |  | 0 | 0 | 1578974
San Anselmo | 2008 | 1296543 | 141036 | N/A | 0 | 0 |  | 0 | 0 | 1438298
San Anselmo | 2007 | 1155294 | 141249 | N/A | 0 | 0 |  | 0 | 0 | 1296543
San Rafael | 2019 | 4879552.04 | 227280 | N/A | 0 | 0 |  | 0 | 0 | 5106832.04
San Rafael | 2018 | 4652769.04 | 226783 | N/A | 0 | 0 |  | 0 | 0 | 4879552.04
San Rafael | 2017 | 4425416.04 | 227353 | N/A | 0 | 0 |  | 0 | 0 | 4652769.04
San Rafael | 2016 | 4199655.04 | 225761 | N/A | 0 | 0 |  | 0 | 0 | 4425416.04
San Rafael | 2015 | 3971549.04 | 228106 | N/A | 0 | 0 |  | 0 | 0 | 4199655.04
San Rafael | 2014 | 3742194.04 | 229355 | N/A | 0 | 0 |  | 0 | 0 | 3971549.04
San Rafael | 2013 | 3513791.04 | 228403 | N/A | 0 | 0 |  | 0 | 0 | 3742194.04
San Rafael | 2012 | 3284848.04 | 228943 | N/A | 0 | 0 |  | 0 | 0 | 3513791.04
San Rafael | 2011 | 3055125.04 | 229723 | N/A | 0 | 0 |  | 0 | 0 | 3284848.04
San Rafael | 2010 | 2594081.04 | 461044 | N/A | 0 | 0 |  | 0 | 0 | 3055125.04
San Rafael | 2009 | 2133315.04 | 460766 | N/A | 0 | 0 |  | 0 | 0 | 2594081.04
San Rafael | 2008 | 2112802 | 462507 | N/A | 0 | 0 |  | 444675.96 | 444675.96 | 2133315.04
San Rafael | 2007 | 1648998 | 463804 | N/A | 0 | 0 |  | 0 | 0 | 2112802
Sausalito | 2019 | 1875795.88 | 44109 | N/A | 0 | 0 |  | 0 | 0 | 1919904.88
Sausalito | 2018 | 1831772.88 | 44023 | N/A | 0 | 0 |  | 0 | 0 | 1875795.88
Sausalito | 2017 | 1787522.88 | 44250 | N/A | 0 | 0 |  | 0 | 0 | 1831772.88
Sausalito | 2016 | 1743522.88 | 44000 | N/A | 0 | 0 |  | 0 | 0 | 1787522.88
Sausalito | 2015 | 1698897.88 | 44625 | N/A | 0 | 0 |  | 0 | 0 | 1743522.88
Sausalito | 2014 | 1654034.88 | 44863 | N/A | 0 | 0 |  | 0 | 0 | 1698897.88
Sausalito | 2013 | 1608645.88 | 45389 | N/A | 0 | 0 |  | 0 | 0 | 1654034.88
Sausalito | 2012 | 1563225.88 | 45420 | N/A | 0 | 0 |  | 0 | 0 | 1608645.88
Sausalito | 2011 | 1517929.88 | 45296 | N/A | 0 | 0 |  | 0 | 0 | 1563225.88
Sausalito | 2010 | 1421002.88 | 96927 | N/A | 0 | 0 |  | 0 | 0 | 1517929.88
Sausalito | 2009 | 1324135.88 | 96867 | N/A | 0 | 0 |  | 0 | 0 | 1421002.88
Sausalito | 2008 | 1226667.88 | 96943 | N/A | 0 | 0 |  | 0 | 0 | 1324135.88
Sausalito | 2007 | 1129718.88 | 96949 | N/A | 0 | 0 |  | 0 | 0 | 1226667.88
Tiburon | 2019 | 1201429 | 29322 | N/A | 0 | 0 |  | 0 | 0 | 1230751
Tiburon | 2018 | 734005 | 29344 | N/A | 0 | 438080 | Rocklin ($438,080) | 0 | 0 | 1201429
Tiburon | 2017 | 704566 | 29439 | N/A | 0 | 0 |  | 0 | 0 | 734005
Tiburon | 2016 | 675225 | 29341 | N/A | 0 | 0 |  | 0 | 0 | 704566
Tiburon | 2015 | 645571 | 29654 | N/A | 0 | 0 |  | 0 | 0 | 675225
Tiburon | 2014 | 614645 | 30926 | N/A | 0 | 0 |  | 0 | 0 | 645571
Tiburon | 2013 | 583010 | 31635 | N/A | 0 | 0 |  | 0 | 0 | 614645
Tiburon | 2012 | 551396 | 31614 | N/A | 0 | 0 |  | 0 | 0 | 583010
Tiburon | 2011 | 519622 | 31774 | N/A | 0 | 0 |  | 0 | 0 | 551396
Tiburon | 2010 | 454963 | 64659 | N/A | 0 | 0 |  | 0 | 0 | 519622
Tiburon | 2009 | 390387 | 64576 | N/A | 0 | 0 |  | 0 | 0 | 454963
Tiburon | 2008 | 325330 | 64688 | N/A | 0 | 0 |  | 0 | 0 | 390387
Tiburon | 2007 | 258753 | 66577 | N/A | 0 | 0 |  | 0 | 0 | 325330
Marin County Total |  |  | 17244563 |  |  | 438080 |  | 12688839.95 | 12688839.95
Mariposa County
Mariposa County | 2019 | 3255283 | 121654 | N/A | 0 | 0 |  | 0 | 0 | 3376937
Mariposa County | 2018 | 3134051 | 121232 | N/A | 0 | 0 |  | 0 | 0 | 3255283
Mariposa County | 2017 | 3013068 | 120983 | N/A | 0 | 0 |  | 0 | 0 | 3134051
Mariposa County | 2016 | 2893358 | 119710 | N/A | 0 | 0 |  | 0 | 0 | 3013068
Mariposa County | 2015 | 2772830 | 120528 | N/A | 0 | 0 |  | 0 | 0 | 2893358
Mariposa County | 2014 | 2652063 | 120767 | N/A | 0 | 0 |  | 0 | 0 | 2772830
Mariposa County | 2013 | 2531732 | 120331 | N/A | 0 | 0 |  | 0 | 0 | 2652063
Mariposa County | 2012 | 2411737 | 119995 | N/A | 0 | 0 |  | 0 | 0 | 2531732
Mariposa County | 2011 | 2291414 | 120323 | N/A | 0 | 0 |  | 0 | 0 | 2411737
Mariposa County | 2010 | 2079150 | 212264 | N/A | 0 | 0 |  | 0 | 0 | 2291414
Mariposa County | 2009 | 1867558 | 211592 | N/A | 0 | 0 |  | 0 | 0 | 2079150
Mariposa County | 2008 | 1655028 | 211157 | N/A | 0 | 0 |  | 0 | 0 | 1867558
Mariposa County | 2007 | 1444898 | 210130 | N/A | 0 | 0 |  | 0 | 0 | 1655028
Mariposa County Total |  |  | 1930666 |  |  | 0 |  | 0 | 0
Mendocino County
Fort Bragg | 2019 | 1215827 | 36678 | N/A | 0 | 0 |  | 0 | 0 | 1252505
Fort Bragg | 2018 | 1179176 | 36651 | N/A | 0 | 0 |  | 0 | 0 | 1215827
Fort Bragg | 2017 | 1142424 | 36752 | N/A | 0 | 0 |  | 0 | 0 | 1179176
Fort Bragg | 2016 | 1106115 | 36309 | N/A | 0 | 0 |  | 0 | 0 | 1142424
Fort Bragg | 2015 | 1069418 | 36697 | N/A | 0 | 0 |  | 0 | 0 | 1106115
Fort Bragg | 2014 | 1032690 | 36728 | N/A | 0 | 0 |  | 0 | 0 | 1069418
Fort Bragg | 2013 | 995861 | 36829 | N/A | 0 | 0 |  | 0 | 0 | 1032690
Fort Bragg | 2012 | 958980 | 36881 | N/A | 0 | 0 |  | 0 | 0 | 995861
Fort Bragg | 2011 | 921746 | 37234 | N/A | 0 | 0 |  | 0 | 0 | 958980
Fort Bragg | 2010 | 847570 | 74176 | N/A | 0 | 0 |  | 0 | 0 | 921746
Fort Bragg | 2009 | 773462 | 74108 | N/A | 0 | 0 |  | 0 | 0 | 847570
Fort Bragg | 2008 | 698864 | 74168 | N/A | 0 | 0 |  | 0 | 0 | 773462
Fort Bragg | 2007 | 624674 | 74190 | N/A | 0 | 0 |  | 0 | 0 | 698864
Mendocino County | 2019 | 7826035.44 | 319142 | N/A | 0 | 0 |  | 0 | 0 | 8145177.44
Mendocino County | 2018 | 7509138.44 | 316897 | N/A | 0 | 0 |  | 0 | 0 | 7826035.44
Mendocino County | 2017 | 7192483.44 | 316655 | N/A | 0 | 0 |  | 0 | 0 | 7509138.44
Mendocino County | 2016 | 6878700.44 | 313783 | N/A | 0 | 0 |  | 0 | 0 | 7192483.44
Mendocino County | 2015 | 6562237.44 | 316463 | N/A | 0 | 0 |  | 0 | 0 | 6878700.44
Mendocino County | 2014 | 6244815.44 | 317422 | N/A | 0 | 0 |  | 0 | 0 | 6562237.44
Mendocino County | 2013 | 9993365.44 | 319170 | N/A | 0 | 0 |  | 4067720 | 4067720 | 6244815.44
Mendocino County | 2012 | 9673611.44 | 319754 | N/A | 0 | 0 |  | 0 | 0 | 9993365.44
Mendocino County | 2011 | 9354392.44 | 319219 | N/A | 0 | 0 |  | 0 | 0 | 9673611.44
Mendocino County | 2010 | 8728719.44 | 625673 | N/A | 0 | 0 |  | 0 | 0 | 9354392.44
Mendocino County | 2009 | 8104358.44 | 624361 | N/A | 0 | 0 |  | 0 | 0 | 8728719.44
Mendocino County | 2008 | 7476748.44 | 623944 | N/A | 0 | 0 |  | 0 | 0 | 8104358.44
Mendocino County | 2007 | 6853175.44 | 623573 | N/A | 0 | 0 |  | 0 | 0 | 7476748.44
Point Arena | 2019 | 141357 | 2949 | N/A | 0 | 0 |  | 0 | 0 | 144306
Point Arena | 2018 | 138421 | 2936 | N/A | 0 | 0 |  | 0 | 0 | 141357
Point Arena | 2017 | 135464 | 2957 | N/A | 0 | 0 |  | 0 | 0 | 138421
Point Arena | 2016 | 132545 | 2919 | N/A | 0 | 0 |  | 0 | 0 | 135464
Point Arena | 2015 | 129617 | 2928 | N/A | 0 | 0 |  | 0 | 0 | 132545
Point Arena | 2014 | 126682 | 2935 | N/A | 0 | 0 |  | 0 | 0 | 129617
Point Arena | 2013 | 123723 | 2959 | N/A | 0 | 0 |  | 0 | 0 | 126682
Point Arena | 2012 | 120809 | 2914 | N/A | 0 | 0 |  | 0 | 0 | 123723
Point Arena | 2011 | 117943 | 2866 | N/A | 0 | 0 |  | 0 | 0 | 120809
Point Arena | 2010 | 111063 | 6880 | N/A | 0 | 0 |  | 0 | 0 | 117943
Point Arena | 2009 | 104199 | 6864 | N/A | 0 | 0 |  | 0 | 0 | 111063
Point Arena | 2008 | 97299 | 6867 | N/A | 0 | 0 |  | 0 | 0 | 104199
Point Arena | 2007 | 90455 | 6844 | N/A | 0 | 0 |  | 0 | 0 | 97299
Willits | 2019 | 793853 | 23000 | N/A | 0 | 0 |  | 0 | 0 | 816853
Willits | 2018 | 771057 | 22796 | N/A | 0 | 0 |  | 0 | 0 | 793853
Willits | 2017 | 748273 | 22784 | N/A | 0 | 0 |  | 0 | 0 | 771057
Willits | 2016 | 725682 | 22591 | N/A | 0 | 0 |  | 0 | 0 | 748273
Willits | 2015 | 702869 | 22813 | N/A | 0 | 0 |  | 0 | 0 | 725682
Willits | 2014 | 679908 | 22961 | N/A | 0 | 0 |  | 0 | 0 | 702869
Willits | 2013 | 656555 | 23353 | N/A | 0 | 0 |  | 0 | 0 | 679908
Willits | 2012 | 633247 | 23308 | N/A | 0 | 0 |  | 0 | 0 | 656555
Willits | 2011 | 610004 | 23243 | N/A | 0 | 0 |  | 0 | 0 | 633247
Willits | 2010 | 565848 | 44156 | N/A | 0 | 0 |  | 0 | 0 | 610004
Willits | 2009 | 521775 | 44073 | N/A | 0 | 0 |  | 0 | 0 | 565848
Willits | 2008 | 477481 | 44027 | N/A | 0 | 0 |  | 0 | 0 | 521775
Willits | 2007 | 433561 | 43920 | N/A | 0 | 0 |  | 0 | 0 | 477481
Mendocino County Total |  |  | 6420300 |  |  | 0 |  | 4067720 | 4067720
Merced County
Atwater | 2019 | -944337.52 | 68848 | N/A | 0 | 0 |  | 0 | 0 | -875489.52 | Borrowed beyond 5 years (see AL 4553-E)
Atwater | 2018 | -1011369.52 | 67032 | N/A | 0 | 0 |  | 0 | 0 | -944337.52 | Borrowed beyond 5 years (see AL 4553-E)
Atwater | 2017 | -1078778.52 | 67409 | N/A | 0 | 0 |  | 0 | 0 | -1011369.52 | Borrowed beyond 5 years (see AL 4553-E)
Atwater | 2016 | -1145733.52 | 66955 | N/A | 0 | 0 |  | 0 | 0 | -1078778.52 | Borrowed beyond 5 years (see AL 4553-E)
Atwater | 2015 | -1213408.52 | 67675 | N/A | 0 | 0 |  | 0 | 0 | -1145733.52 | Borrowed beyond 5 years (see AL 4553-E)
Atwater | 2014 | 2005364 | 68134 | N/A | 0 | 0 |  | 3286906.52 | 3286906.52 | -1213408.52 | Borrowed beyond 5 years (see AL 4553-E)
Atwater | 2013 | 1937492 | 67872 | N/A | 0 | 0 |  | 0 | 0 | 2005364
Atwater | 2012 | 1869473 | 68019 | N/A | 0 | 0 |  | 0 | 0 | 1937492
Atwater | 2011 | 1803879 | 65594 | N/A | 0 | 0 |  | 0 | 0 | 1869473
Atwater | 2010 | 1684684 | 119195 | N/A | 0 | 0 |  | 0 | 0 | 1803879
Atwater | 2009 | 1565850 | 118834 | N/A | 0 | 0 |  | 0 | 0 | 1684684
Atwater | 2008 | 1446432 | 118669 | N/A | 0 | 0 |  | 0 | 0 | 1565850
Atwater | 2007 | 1327993 | 118439 | N/A | 0 | 0 |  | 0 | 0 | 1446432
Dos Palos | 2019 | 748505 | 17260 | N/A | 0 | 0 |  | 0 | 0 | 765765
Dos Palos | 2018 | 731321 | 17184 | N/A | 0 | 0 |  | 0 | 0 | 748505
Dos Palos | 2017 | 714207 | 17114 | N/A | 0 | 0 |  | 0 | 0 | 731321
Dos Palos | 2016 | 697404 | 16803 | N/A | 0 | 0 |  | 0 | 0 | 714207
Dos Palos | 2015 | 680417 | 16987 | N/A | 0 | 0 |  | 0 | 0 | 697404
Dos Palos | 2014 | 663316 | 17101 | N/A | 0 | 0 |  | 0 | 0 | 680417
Dos Palos | 2013 | 646199 | 17117 | N/A | 0 | 0 |  | 0 | 0 | 663316
Dos Palos | 2012 | 629003 | 17196 | N/A | 0 | 0 |  | 0 | 0 | 646199
Dos Palos | 2011 | 611311 | 17692 | N/A | 0 | 0 |  | 0 | 0 | 629003
Dos Palos | 2010 | 576952 | 34359 | N/A | 0 | 0 |  | 0 | 0 | 611311
Dos Palos | 2009 | 542640 | 34312 | N/A | 0 | 0 |  | 0 | 0 | 576952
Dos Palos | 2008 | 508179 | 34257 | N/A | 0 | 0 |  | 0 | 0 | 542640
Dos Palos | 2007 | 474047 | 34132 | N/A | 0 | 0 |  | 0 | 0 | 508179
Gustine | 2019 | 357320 | 19546 | N/A | 0 | 0 |  | 0 | 0 | 376866
Gustine | 2018 | 337950 | 19370 | N/A | 0 | 0 |  | 0 | 0 | 357320
Gustine | 2017 | 318465 | 19485 | N/A | 0 | 0 |  | 0 | 0 | 337950
Gustine | 2016 | 299225 | 19240 | N/A | 0 | 0 |  | 0 | 0 | 318465
Gustine | 2015 | 279757 | 19468 | N/A | 0 | 0 |  | 0 | 0 | 299225
Gustine | 2014 | 260177 | 19580 | N/A | 0 | 0 |  | 0 | 0 | 279757
Gustine | 2013 | 240709 | 19468 | N/A | 0 | 0 |  | 0 | 0 | 260177
Gustine | 2012 | 221306 | 19403 | N/A | 0 | 0 |  | 0 | 0 | 240709
Gustine | 2011 | 201922 | 19384 | N/A | 0 | 0 |  | 0 | 0 | 221306
Gustine | 2010 | 164616 | 37306 | N/A | 0 | 0 |  | 0 | 0 | 201922
Gustine | 2009 | 127351 | 37265 | N/A | 0 | 0 |  | 0 | 0 | 164616
Gustine | 2008 | 89867 | 37262 | N/A | 0 | 0 |  | 0 | 0 | 127351
Gustine | 2007 | 52530 | 37337 | N/A | 0 | 0 |  | 0 | 0 | 89867
Livingston | 2019 | 740979 | 18529 | N/A | 0 | 0 |  | 0 | 0 | 759508
Livingston | 2018 | 722235 | 18744 | N/A | 0 | 0 |  | 0 | 0 | 740979
Livingston | 2017 | 703440 | 18795 | N/A | 0 | 0 |  | 0 | 0 | 722235
Livingston | 2016 | 684758 | 18682 | N/A | 0 | 0 |  | 0 | 0 | 703440
Livingston | 2015 | 665953 | 18805 | N/A | 0 | 0 |  | 0 | 0 | 684758
Livingston | 2014 | 647014 | 18939 | N/A | 0 | 0 |  | 0 | 0 | 665953
Livingston | 2013 | 628180 | 18834 | N/A | 0 | 0 |  | 0 | 0 | 647014
Livingston | 2012 | 609326 | 18854 | N/A | 0 | 0 |  | 0 | 0 | 628180
Livingston | 2011 | 590728 | 18598 | N/A | 0 | 0 |  | 0 | 0 | 609326
Livingston | 2010 | 556886 | 33842 | N/A | 0 | 0 |  | 0 | 0 | 590728
Livingston | 2009 | 523041 | 33845 | N/A | 0 | 0 |  | 0 | 0 | 556886
Livingston | 2008 | 488939 | 33887 | N/A | 0 | 0 |  | 0 | 0 | 523041
Livingston | 2007 | 454924 | 34015 | N/A | 0 | 0 |  | 0 | 0 | 488939
Los Banos | 2019 | 1246483.68 | 85221 | N/A | 0 | 0 |  | 0 | 0 | 1331704.68
Los Banos | 2018 | 1369573.19 | 84102 | N/A | 0 | 0 |  | 207191.51 | 0 | 1246483.68
Los Banos | 2017 | 1286381.19 | 83192 | N/A | 0 | 0 |  | 0 | 0 | 1369573.19
Los Banos | 2016 | 1204502.19 | 81879 | N/A | 0 | 0 |  | 0 | 0 | 1286381.19
Los Banos | 2015 | 1122262.19 | 82240 | N/A | 0 | 0 |  | 0 | 0 | 1204502.19
Los Banos | 2014 | 1039476.19 | 82786 | N/A | 0 | 0 |  | 0 | 0 | 1122262.19
Los Banos | 2013 | 956536.19 | 82940 | N/A | 0 | 0 |  | 0 | 0 | 1039476.19
Los Banos | 2012 | 873369.19 | 83167 | N/A | 0 | 0 |  | 0 | 0 | 956536.19
Los Banos | 2011 | 790225.19 | 83144 | N/A | 0 | 0 |  | 0 | 0 | 873369.19
Los Banos | 2010 | 657280.19 | 132945 | N/A | 0 | 0 |  | 0 | 0 | 790225.19
Los Banos | 2009 | 524723.19 | 132557 | N/A | 0 | 0 |  | 0 | 0 | 657280.19
Los Banos | 2008 | 391560.19 | 132215 | N/A | 0 | 0 |  | 0 | 0 | 524723.19
Los Banos | 2007 | 1219300 | 131579 | N/A | 0 | 0 |  | 959318.81 | 959318.81 | 391560.19
Merced | 2019 | 116181 | 182743 | N/A | 0 | 0 |  | 0 | 0 | 298924
Merced | 2018 | -66939 | 183120 | N/A | 0 | 0 |  | 0 | 0 | 116181
Merced | 2017 | -250378 | 183439 | N/A | 0 | 0 |  | 0 | 0 | -66939 | Within 5-year borrow
Merced | 2016 | -433096 | 182718 | N/A | 0 | 0 |  | 0 | 0 | -250378 | Within 5-year borrow
Merced | 2015 | 951646 | 185148 | N/A | 0 | 0 |  | 1569890 | 1569890 | -433096 | Within 5-year borrow
Merced | 2014 | 765436 | 186210 | N/A | 0 | 0 |  | 0 | 0 | 951646
Merced | 2013 | 2745324 | 187812 | N/A | 0 | 0 |  | 2167700 | 2167700 | 765436
Merced | 2012 | 2556579 | 188745 | N/A | 0 | 0 |  | 0 | 0 | 2745324
Merced | 2011 | 2370855 | 185724 | N/A | 0 | 0 |  | 0 | 0 | 2556579
Merced | 2010 | 2012255 | 358600 | N/A | 0 | 0 |  | 0 | 0 | 2370855
Merced | 2009 | 1653815 | 358440 | N/A | 0 | 0 |  | 0 | 0 | 2012255
Merced | 2008 | 1292898 | 358760 | N/A | 0 | 0 |  | 0 | 0 | 1653815
Merced | 2007 | 934261 | 358637 | N/A | 0 | 0 |  | 0 | 0 | 1292898
Merced County | 2019 | 5582775.96 | 299493 | N/A | 0 | 0 |  | 0 | 0 | 5882268.96
Merced County | 2018 | 5281063.96 | 301712 | N/A | 0 | 0 |  | 0 | 0 | 5582775.96
Merced County | 2017 | 9226356.78 | 302055 | N/A | 0 | 0 |  | 4247347.82 | 4247347.82 | 5281063.96
Merced County | 2016 | 8927360.78 | 298996 | N/A | 0 | 0 |  | 0 | 0 | 9226356.78
Merced County | 2015 | 8627869.78 | 299491 | N/A | 0 | 0 |  | 0 | 0 | 8927360.78
Merced County | 2014 | 8328873.78 | 298996 | N/A | 0 | 0 |  | 0 | 0 | 8627869.78
Merced County | 2013 | 8021013.78 | 307860 | N/A | 0 | 0 |  | 0 | 0 | 8328873.78
Merced County | 2012 | 9740796 | 306312 | N/A | 0 | 0 |  | 2026094.22 | 2026094.22 | 8021013.78
Merced County | 2011 | 9430111 | 310685 | N/A | 0 | 0 |  | 0 | 0 | 9740796
Merced County | 2010 | 8808849 | 621262 | N/A | 0 | 0 |  | 0 | 0 | 9430111
Merced County | 2009 | 8190139 | 618710 | N/A | 0 | 0 |  | 0 | 0 | 8808849
Merced County | 2008 | 7569709 | 616912 | N/A | 0 | 0 |  | 0 | 0 | 8190139
Merced County | 2007 | 6954437 | 615272 | N/A | 0 | 0 |  | 0 | 0 | 7569709
Merced County Total |  |  | 11578491 |  |  | 0 |  | 14464448.88 | 14257257.37
Monterey County
Carmel | 2019 | 849085 | 35739 | N/A | 0 | 0 |  | 0 | 0 | 884824
Carmel | 2018 | 813350 | 35735 | N/A | 0 | 0 |  | 0 | 0 | 849085
Carmel | 2017 | 777528 | 35822 | N/A | 0 | 0 |  | 0 | 0 | 813350
Carmel | 2016 | 742111 | 35417 | N/A | 0 | 0 |  | 0 | 0 | 777528
Carmel | 2015 | 706308 | 35803 | N/A | 0 | 0 |  | 0 | 0 | 742111
Carmel | 2014 | 670302 | 36006 | N/A | 0 | 0 |  | 0 | 0 | 706308
Carmel | 2013 | 632951 | 37351 | N/A | 0 | 0 |  | 0 | 0 | 670302
Carmel | 2012 | 595576 | 37375 | N/A | 0 | 0 |  | 0 | 0 | 632951
Carmel | 2011 | 556441 | 39135 | N/A | 0 | 0 |  | 0 | 0 | 595576
Carmel | 2010 | 473142 | 83299 | N/A | 0 | 0 |  | 0 | 0 | 556441
Carmel | 2009 | 390000 | 83142 | N/A | 0 | 0 |  | 0 | 0 | 473142
Carmel | 2008 | 306413 | 83136 | N/A | 0 | 0 |  | 0 | 0 | 390000
Carmel | 2007 | 223338 | 83075 | N/A | 0 | 0 |  | 0 | 0 | 306413
Del Rey Oaks | 2019 | 374637 | 7370 | N/A | 0 | 0 |  | 0 | 0 | 382007
Del Rey Oaks | 2018 | 367293 | 7344 | N/A | 0 | 0 |  | 0 | 0 | 374637
Del Rey Oaks | 2017 | 359937 | 7356 | N/A | 0 | 0 |  | 0 | 0 | 367293
Del Rey Oaks | 2016 | 352621 | 7316 | N/A | 0 | 0 |  | 0 | 0 | 359937
Del Rey Oaks | 2015 | 345236 | 7385 | N/A | 0 | 0 |  | 0 | 0 | 352621
Del Rey Oaks | 2014 | 337818 | 7418 | N/A | 0 | 0 |  | 0 | 0 | 345236
Del Rey Oaks | 2013 | 330484 | 7334 | N/A | 0 | 0 |  | 0 | 0 | 337818
Del Rey Oaks | 2012 | 323204 | 7280 | N/A | 0 | 0 |  | 0 | 0 | 330484
Del Rey Oaks | 2011 | 315908 | 7296 | N/A | 0 | 0 |  | 0 | 0 | 323204
Del Rey Oaks | 2010 | 300053 | 15855 | N/A | 0 | 0 |  | 0 | 0 | 315908
Del Rey Oaks | 2009 | 284197 | 15856 | N/A | 0 | 0 |  | 0 | 0 | 300053
Del Rey Oaks | 2008 | 268217 | 15895 | N/A | 0 | 0 |  | 0 | 0 | 284197
Del Rey Oaks | 2007 | 252278 | 15939 | N/A | 0 | 0 |  | 0 | 0 | 268217
Gonzales | 2019 | 482728 | 15819 | N/A | 0 | 0 |  | 0 | 0 | 498547
Gonzales | 2018 | 466951 | 15777 | N/A | 0 | 0 |  | 0 | 0 | 482728
Gonzales | 2017 | 451112 | 15839 | N/A | 0 | 0 |  | 0 | 0 | 466951
Gonzales | 2016 | 435360 | 15752 | N/A | 0 | 0 |  | 0 | 0 | 451112
Gonzales | 2015 | 419463 | 15897 | N/A | 0 | 0 |  | 0 | 0 | 435360
Gonzales | 2014 | 403461 | 16002 | N/A | 0 | 0 |  | 0 | 0 | 419463
Gonzales | 2013 | 387514 | 15947 | N/A | 0 | 0 |  | 0 | 0 | 403461
Gonzales | 2012 | 371759 | 15755 | N/A | 0 | 0 |  | 0 | 0 | 387514
Gonzales | 2011 | 355974 | 15785 | N/A | 0 | 0 |  | 0 | 0 | 371759
Gonzales | 2010 | 326534 | 29440 | N/A | 0 | 0 |  | 0 | 0 | 355974
Gonzales | 2009 | 296910 | 29624 | N/A | 0 | 0 |  | 0 | 0 | 326534
Gonzales | 2008 | 267170 | 29556 | N/A | 0 | 0 |  | 0 | 0 | 296910
Gonzales | 2007 | 237673 | 29497 | N/A | 0 | 0 |  | 0 | 0 | 267170
Greenfield | 2019 | 914836 | 26942 | N/A | 0 | 0 |  | 0 | 0 | 941778
Greenfield | 2018 | 887955 | 26881 | N/A | 0 | 0 |  | 0 | 0 | 914836
Greenfield | 2017 | 861068 | 26887 | N/A | 0 | 0 |  | 0 | 0 | 887955
Greenfield | 2016 | 834527 | 26541 | N/A | 0 | 0 |  | 0 | 0 | 861068
Greenfield | 2015 | 807862 | 26665 | N/A | 0 | 0 |  | 0 | 0 | 834527
Greenfield | 2014 | 781239 | 26623 | N/A | 0 | 0 |  | 0 | 0 | 807862
Greenfield | 2013 | 754491 | 26748 | N/A | 0 | 0 |  | 0 | 0 | 781239
Greenfield | 2012 | 728448 | 26043 | N/A | 0 | 0 |  | 0 | 0 | 754491
Greenfield | 2011 | 702332 | 26116 | N/A | 0 | 0 |  | 0 | 0 | 728448
Greenfield | 2010 | 657899 | 44433 | N/A | 0 | 0 |  | 0 | 0 | 702332
Greenfield | 2009 | 613477 | 44422 | N/A | 0 | 0 |  | 0 | 0 | 657899
Greenfield | 2008 | 569115 | 44067 | N/A | 0 | 0 |  | 0 | 0 | 613477
Greenfield | 2007 | 525611 | 43504 | N/A | 0 | 0 |  | 0 | 0 | 569115
King City | 2019 | 27385 | 27741 | N/A | 0 | 0 |  | 0 | 0 | 55126
King City | 2018 | 0 | 27385 | N/A | 0 | 0 |  | 0 | 0 | 27385
King City | 2017 | 0 | 27363 | N/A | 0 | 0 |  | 0 | 0 | 0
King City | 2016 | 725055.04 | 27093 | N/A | 0 | 0 |  | 0 | 0 | 0
King City | 2015 | 697752.04 | 27303 | N/A | 0 | 0 |  | 0 | 0 | 725055.04
King City | 2014 | 670584.04 | 27168 | N/A | 0 | 0 |  | 0 | 0 | 697752.04
King City | 2013 | 643402.04 | 27182 | N/A | 0 | 0 |  | 0 | 0 | 670584.04
King City | 2012 | 616197.04 | 27205 | N/A | 0 | 0 |  | 0 | 0 | 643402.04
King City | 2011 | 588966.04 | 27231 | N/A | 0 | 0 |  | 0 | 0 | 616197.04
King City | 2010 | 539586.04 | 49380 | N/A | 0 | 0 |  | 0 | 0 | 588966.04
King City | 2009 | 490183.04 | 49403 | N/A | 0 | 0 |  | 0 | 0 | 539586.04
King City | 2008 | 440462.04 | 49405 | N/A | 0 | 0 |  | 0 | 0 | 490183.04
King City | 2007 | 391474.04 | 48988 | N/A | 0 | 0 |  | 0 | 0 | 440462.04
Marina | 2019 | 1666637 | 59339 | N/A | 0 | 0 |  | 0 | 0 | 1725976
Marina | 2018 | 1608218 | 58419 | N/A | 0 | 0 |  | 0 | 0 | 1666637
Marina | 2017 | 1550140 | 58078 | N/A | 0 | 0 |  | 0 | 0 | 1608218
Marina | 2016 | 1492810 | 57330 | N/A | 0 | 0 |  | 0 | 0 | 1550140
Marina | 2015 | 1435119 | 57691 | N/A | 0 | 0 |  | 0 | 0 | 1492810
Marina | 2014 | 1377662 | 57457 | N/A | 0 | 0 |  | 0 | 0 | 1435119
Marina | 2013 | 1320453 | 57209 | N/A | 0 | 0 |  | 0 | 0 | 1377662
Marina | 2012 | 1263128 | 57325 | N/A | 0 | 0 |  | 0 | 0 | 1320453
Marina | 2011 | 1205732 | 57396 | N/A | 0 | 0 |  | 0 | 0 | 1263128
Marina | 2010 | 1097875 | 107857 | N/A | 0 | 0 |  | 0 | 0 | 1205732
Marina | 2009 | 990051 | 107824 | N/A | 0 | 0 |  | 0 | 0 | 1097875
Marina | 2008 | 881363 | 108021 | N/A | 0 | 0 |  | 0 | 0 | 990051
Marina | 2007 | 773323 | 108040 | N/A | 0 | 0 |  | 0 | 0 | 881363
Monterey | 2019 | 4214301.16 | 131972 | N/A | 0 | 0 |  | 0 | 0 | 4346273.16
Monterey | 2018 | 4082986.16 | 131315 | N/A | 0 | 0 |  | 0 | 0 | 4214301.16
Monterey | 2017 | 3951913.16 | 131073 | N/A | 0 | 0 |  | 0 | 0 | 4082986.16
Monterey | 2016 | 3916434 | 130098 | N/A | 0 | 0 |  | 94618.84 | 0 | 3951913.16
Monterey | 2015 | 3784990 | 131444 | N/A | 0 | 0 |  | 0 | 0 | 3916434
Monterey | 2014 | 3652697 | 132293 | N/A | 0 | 0 |  | 0 | 0 | 3784990
Monterey | 2013 | 3521176 | 131521 | N/A | 0 | 0 |  | 0 | 0 | 3652697
Monterey | 2012 | 3388563 | 132613 | N/A | 0 | 0 |  | 0 | 0 | 3521176
Monterey | 2011 | 3255767 | 132796 | N/A | 0 | 0 |  | 0 | 0 | 3388563
Monterey | 2010 | 2983529 | 272238 | N/A | 0 | 0 |  | 0 | 0 | 3255767
Monterey | 2009 | 2711535 | 271994 | N/A | 0 | 0 |  | 0 | 0 | 2983529
Monterey | 2008 | 2437396 | 272597 | N/A | 0 | 0 |  | 0 | 0 | 2711535
Monterey | 2007 | 2164592 | 272804 | N/A | 0 | 0 |  | 0 | 0 | 2437396
Monterey County | 2019 | 13868313.45 | 424842 | N/A | 0 | 0 |  | 0 | 0 | 14293155.45
Monterey County | 2018 | 13446377.45 | 421936 | N/A | 0 | 0 |  | 0 | 0 | 13868313.45
Monterey County | 2017 | 13023951.45 | 422426 | N/A | 0 | 0 |  | 0 | 0 | 13446377.45
Monterey County | 2016 | 12605728.45 | 418223 | N/A | 0 | 0 |  | 0 | 0 | 13023951.45
Monterey County | 2015 | 12184231.45 | 421497 | N/A | 0 | 0 |  | 0 | 0 | 12605728.45
Monterey County | 2014 | 11760252.45 | 423979 | N/A | 0 | 0 |  | 0 | 0 | 12184231.45
Monterey County | 2013 | 11332389.45 | 427863 | N/A | 0 | 0 |  | 0 | 0 | 11760252.45
Monterey County | 2012 | 10903844.45 | 428545 | N/A | 0 | 0 |  | 0 | 0 | 11332389.45
Monterey County | 2011 | 9565051.45 | 427715 | N/A | 0 | 0 |  | -911078 | -911078 | 10903844.45
Monterey County | 2010 | 8712565.45 | 852486 | N/A | 0 | 0 |  | 0 | 0 | 9565051.45
Monterey County | 2009 | 7860360.45 | 852205 | N/A | 0 | 0 |  | 0 | 0 | 8712565.45
Monterey County | 2008 | 7002857.45 | 852552 | N/A | 0 | 0 |  | 0 | 0 | 7860360.45
Monterey County | 2007 | 7858118 | 852568 | N/A | 0 | 0 |  | 1707828.55 | 1707828.55 | 7002857.45
Pacific Grove | 2019 | 2167633.97 | 84585 | N/A | 0 | 0 |  | 0 | 0 | 2252218.97
Pacific Grove | 2018 | 2083423.97 | 84210 | N/A | 0 | 0 |  | 0 | 0 | 2167633.97
Pacific Grove | 2017 | 1998918.97 | 84505 | N/A | 0 | 0 |  | 0 | 0 | 2083423.97
Pacific Grove | 2016 | 1914952.97 | 83966 | N/A | 0 | 0 |  | 0 | 0 | 1998918.97
Pacific Grove | 2015 | 1830232.97 | 84720 | N/A | 0 | 0 |  | 0 | 0 | 1914952.97
Pacific Grove | 2014 | 1745159.97 | 85073 | N/A | 0 | 0 |  | 0 | 0 | 1830232.97
Pacific Grove | 2013 | 1660417.97 | 84742 | N/A | 0 | 0 |  | 0 | 0 | 1745159.97
Pacific Grove | 2012 | 1575493.97 | 84924 | N/A | 0 | 0 |  | 0 | 0 | 1660417.97
Pacific Grove | 2011 | 1490461.97 | 85032 | N/A | 0 | 0 |  | 0 | 0 | 1575493.97
Pacific Grove | 2010 | 1301326.97 | 189135 | N/A | 0 | 0 |  | 0 | 0 | 1490461.97
Pacific Grove | 2009 | 1112349.97 | 188977 | N/A | 0 | 0 |  | 0 | 0 | 1301326.97
Pacific Grove | 2008 | 1673417 | 189336 | N/A | 0 | 0 |  | 751389.03 | 751389.03 | 1112349.97
Pacific Grove | 2007 | 1483889 | 189528 | N/A | 0 | 0 |  | 0 | 0 | 1673417
Salinas | 2019 | 2612418.85 | 333871 | N/A | 0 | 0 |  | 0 | 0 | 2946289.85
Salinas | 2018 | 9039936.89 | 333410 | N/A | 0 | 0 |  | 6760928.04 | 6760928.04 | 2612418.85
Salinas | 2017 | 8705553.89 | 334383 | N/A | 0 | 0 |  | 0 | 0 | 9039936.89
Salinas | 2016 | 8373336.89 | 332217 | N/A | 0 | 0 |  | 0 | 0 | 8705553.89
Salinas | 2015 | 8037856.89 | 335480 | N/A | 0 | 0 |  | 0 | 0 | 8373336.89
Salinas | 2014 | 7700007.89 | 337849 | N/A | 0 | 0 |  | 0 | 0 | 8037856.89
Salinas | 2013 | 7365052.89 | 334955 | N/A | 0 | 0 |  | 0 | 0 | 7700007.89
Salinas | 2012 | 7027919.89 | 337133 | N/A | 0 | 0 |  | 0 | 0 | 7365052.89
Salinas | 2011 | 6690689.89 | 337230 | N/A | 0 | 0 |  | 0 | 0 | 7027919.89
Salinas | 2010 | 6046036.89 | 644653 | N/A | 0 | 0 |  | 0 | 0 | 6690689.89
Salinas | 2009 | 5402410.89 | 643626 | N/A | 0 | 0 |  | 0 | 0 | 6046036.89
Salinas | 2008 | 4754583.89 | 643929 | N/A | 0 | 0 |  | 0 | 0 | 5402410.89
Salinas | 2007 | 4109222.89 | 645361 | N/A | 0 | 0 |  | 0 | 0 | 4754583.89
Sand City | 2019 | 205228 | 4195 | N/A | 0 | 0 |  | 0 | 0 | 209423
Sand City | 2018 | 201003 | 4225 | N/A | 0 | 0 |  | 0 | 0 | 205228
Sand City | 2017 | 196831 | 4172 | N/A | 0 | 0 |  | 0 | 0 | 201003
Sand City | 2016 | 192674 | 4157 | N/A | 0 | 0 |  | 0 | 0 | 196831
Sand City | 2015 | 188517 | 4157 | N/A | 0 | 0 |  | 0 | 0 | 192674
Sand City | 2014 | 184362 | 4155 | N/A | 0 | 0 |  | 0 | 0 | 188517
Sand City | 2013 | 180172 | 4190 | N/A | 0 | 0 |  | 0 | 0 | 184362
Sand City | 2012 | 175971 | 4201 | N/A | 0 | 0 |  | 0 | 0 | 180172
Sand City | 2011 | 171790 | 4181 | N/A | 0 | 0 |  | 0 | 0 | 175971
Sand City | 2010 | 163531 | 8259 | N/A | 0 | 0 |  | 0 | 0 | 171790
Sand City | 2009 | 155295 | 8236 | N/A | 0 | 0 |  | 0 | 0 | 163531
Sand City | 2008 | 146992 | 8255 | N/A | 0 | 0 |  | 0 | 0 | 155295
Sand City | 2007 | 138724 | 8268 | N/A | 0 | 0 |  | 0 | 0 | 146992
Seaside | 2019 | 283396 | 94143 | N/A | 0 | 0 |  | 0 | 0 | 377539
Seaside | 2018 | 189257 | 94139 | N/A | 0 | 0 |  | 0 | 0 | 283396
Seaside | 2017 | 94840 | 94417 | N/A | 0 | 0 |  | 0 | 0 | 189257
Seaside | 2016 | 1039 | 93801 | N/A | 0 | 0 |  | 0 | 0 | 94840
Seaside | 2015 | -93790 | 94829 | N/A | 0 | 0 |  | 0 | 0 | 1039
Seaside | 2014 | -189112 | 95322 | N/A | 0 | 0 |  | 0 | 0 | -93790 | Within 5-year borrow
Seaside | 2013 | -287999 | 98887 | N/A | 0 | 0 |  | 0 | 0 | -189112 | Within 5-year borrow
Seaside | 2012 | 2291287 | 99164 | N/A | 0 | 0 |  | 2678450 | 2678450 | -287999 | Within 5-year borrow
Seaside | 2011 | 2191237 | 100050 | N/A | 0 | 0 |  | 0 | 0 | 2291287
Seaside | 2010 | 2015458 | 175779 | N/A | 0 | 0 |  | 0 | 0 | 2191237
Seaside | 2009 | 1839712 | 175746 | N/A | 0 | 0 |  | 0 | 0 | 2015458
Seaside | 2008 | 1662388 | 176175 | N/A | 0 | 0 |  | 0 | 0 | 1839712
Seaside | 2007 | 1485709 | 176679 | N/A | 0 | 0 |  | 0 | 0 | 1662388
Soledad | 2019 | 749980 | 26955 | N/A | 0 | 0 |  | 0 | 0 | 776935
Soledad | 2018 | 723169 | 26811 | N/A | 0 | 0 |  | 0 | 0 | 749980
Soledad | 2017 | 696697 | 26472 | N/A | 0 | 0 |  | 0 | 0 | 723169
Soledad | 2016 | 670477 | 26220 | N/A | 0 | 0 |  | 0 | 0 | 696697
Soledad | 2015 | 643968 | 26509 | N/A | 0 | 0 |  | 0 | 0 | 670477
Soledad | 2014 | 617260 | 26708 | N/A | 0 | 0 |  | 0 | 0 | 643968
Soledad | 2013 | 590460 | 26800 | N/A | 0 | 0 |  | 0 | 0 | 617260
Soledad | 2012 | 564130 | 26330 | N/A | 0 | 0 |  | 0 | 0 | 590460
Soledad | 2011 | 537805 | 26325 | N/A | 0 | 0 |  | 0 | 0 | 564130
Soledad | 2010 | 497379 | 40426 | N/A | 0 | 0 |  | 0 | 0 | 537805
Soledad | 2009 | 457338 | 40041 | N/A | 0 | 0 |  | 0 | 0 | 497379
Soledad | 2008 | 417066 | 39974 | N/A | 0 | 0 |  | 0 | 0 | 457338
Soledad | 2007 | 377352 | 39714 | N/A | 0 | 0 |  | 0 | 0 | 417066
Monterey County Total |  |  | 21515566 |  |  | 0 |  | 11082136.46 | 10987517.62
Napa County
American Canyon | 2019 | 480713 | 31394 | N/A | 0 | 0 |  | 0 | 0 | 512107
American Canyon | 2018 | 449628 | 31085 | N/A | 0 | 0 |  | 0 | 0 | 480713
American Canyon | 2017 | 419137 | 30491 | N/A | 0 | 0 |  | 0 | 0 | 449628
American Canyon | 2016 | 388997 | 30140 | N/A | 0 | 0 |  | 0 | 0 | 419137
American Canyon | 2015 | 358500 | 30497 | N/A | 0 | 0 |  | 0 | 0 | 388997
American Canyon | 2014 | 327722 | 30778 | N/A | 0 | 0 |  | 0 | 0 | 358500
American Canyon | 2013 | 297074 | 30648 | N/A | 0 | 0 |  | 0 | 0 | 327722
American Canyon | 2012 | 266463 | 30611 | N/A | 0 | 0 |  | 0 | 0 | 297074
American Canyon | 2011 | 235736 | 30727 | N/A | 0 | 0 |  | 0 | 0 | 266463
American Canyon | 2010 | 210385 | 25351 | N/A | 0 | 0 |  | 0 | 0 | 235736
American Canyon | 2009 | 185156 | 25229 | N/A | 0 | 0 |  | 0 | 0 | 210385
American Canyon | 2008 | 159800 | 25008 | N/A | 0 | 0 |  | 0 | 0 | 185156
American Canyon | 2007 | 135346 | 24454 | N/A | 0 | 0 |  | 0 | 0 | 159800
Calistoga | 2019 | 768751 | 19957 | N/A | 0 | 0 |  | 0 | 0 | 788708
Calistoga | 2018 | 749121 | 19630 | N/A | 0 | 0 |  | 0 | 0 | 768751
Calistoga | 2017 | 729447 | 19674 | N/A | 0 | 0 |  | 0 | 0 | 749121
Calistoga | 2016 | 709937 | 19510 | N/A | 0 | 0 |  | 0 | 0 | 729447
Calistoga | 2015 | 690522 | 19415 | N/A | 0 | 0 |  | 0 | 0 | 709937
Calistoga | 2014 | 670948 | 19574 | N/A | 0 | 0 |  | 0 | 0 | 690522
Calistoga | 2013 | 651308 | 19640 | N/A | 0 | 0 |  | 0 | 0 | 670948
Calistoga | 2012 | 631662 | 19646 | N/A | 0 | 0 |  | 0 | 0 | 651308
Calistoga | 2011 | 612174 | 19488 | N/A | 0 | 0 |  | 0 | 0 | 631662
Calistoga | 2010 | 573976 | 38198 | N/A | 0 | 0 |  | 0 | 0 | 612174
Calistoga | 2009 | 535912 | 38064 | N/A | 0 | 0 |  | 0 | 0 | 573976
Calistoga | 2008 | 497737 | 37953 | N/A | 0 | 0 |  | 0 | 0 | 535912
Calistoga | 2007 | 459779 | 37958 | N/A | 0 | 0 |  | 0 | 0 | 497737
Napa | 2019 | 8947639 | 243048 | N/A | 0 | 0 |  | 0 | 0 | 9190687
Napa | 2018 | 8705131 | 242508 | N/A | 0 | 0 |  | 0 | 0 | 8947639
Napa | 2017 | 8462039 | 243092 | N/A | 0 | 0 |  | 0 | 0 | 8705131
Napa | 2016 | 8220621 | 241418 | N/A | 0 | 0 |  | 0 | 0 | 8462039
Napa | 2015 | 7976781 | 243840 | N/A | 0 | 0 |  | 0 | 0 | 8220621
Napa | 2014 | 7732204 | 244577 | N/A | 0 | 0 |  | 0 | 0 | 7976781
Napa | 2013 | 7488701 | 243503 | N/A | 0 | 0 |  | 0 | 0 | 7732204
Napa | 2012 | 7244947 | 243754 | N/A | 0 | 0 |  | 0 | 0 | 7488701
Napa | 2011 | 7001414 | 243533 | N/A | 0 | 0 |  | 0 | 0 | 7244947
Napa | 2010 | 6536162 | 465252 | N/A | 0 | 0 |  | 0 | 0 | 7001414
Napa | 2009 | 6071321 | 464841 | N/A | 0 | 0 |  | 0 | 0 | 6536162
Napa | 2008 | 5602891 | 465611 | N/A | 0 | 0 |  | 0 | 0 | 6071321
Napa | 2007 | 5136659 | 466232 | N/A | 0 | 0 |  | 0 | 0 | 5602891
Napa County | 2019 | -11483628.58 | 152605 | N/A | 0 | 0 |  | 0 | 0 | -11331023.58 | Borrowed beyond 5 years (see AL 4553-E)
Napa County | 2018 | -11638550.58 | 154922 | N/A | 0 | 0 |  | 0 | 0 | -11483628.58 | Borrowed beyond 5 years (see AL 4553-E)
Napa County | 2017 | -11793649.58 | 155099 | N/A | 0 | 0 |  | 0 | 0 | -11638550.58 | Borrowed beyond 5 years (see AL 4553-E)
Napa County | 2016 | -11947777.58 | 154128 | N/A | 0 | 0 |  | 0 | 0 | -11793649.58 | Borrowed beyond 5 years (see AL 4553-E)
Napa County | 2015 | 3791364 | 155792 | N/A | 0 | 0 |  | 15894933.58 | 15894933.58 | -11947777.58 | Borrowed beyond 5 years (see AL 4553-E)
Napa County | 2014 | 3634475 | 156889 | N/A | 0 | 0 |  | 0 | 0 | 3791364
Napa County | 2013 | 3469350 | 165125 | N/A | 0 | 0 |  | 0 | 0 | 3634475
Napa County | 2012 | 3304537 | 164813 | N/A | 0 | 0 |  | 0 | 0 | 3469350
Napa County | 2011 | 3138475 | 166062 | N/A | 0 | 0 |  | 0 | 0 | 3304537
Napa County | 2010 | 5786578 | 359980 | N/A | 0 | 0 |  | 3008083 | 3008083 | 3138475
Napa County | 2009 | 5427092 | 359486 | N/A | 0 | 0 |  | 0 | 0 | 5786578
Napa County | 2008 | 5065526 | 359648 | N/A | 0 | 0 |  | 0 | 0 | 5427092
Napa County | 2007 | 4705878 | 359648 | N/A | 0 | 0 |  | 0 | 0 | 5065526
St Helena | 2019 | -30417 | 27750 | N/A | 0 | 0 |  | 0 | 0 | -2667 | Within 5-year borrow
St Helena | 2018 | -58042 | 27625 | N/A | 0 | 0 |  | 0 | 0 | -30417 | Within 5-year borrow
St Helena | 2017 | -85840 | 27798 | N/A | 0 | 0 |  | 0 | 0 | -58042 | Within 5-year borrow
St Helena | 2016 | -113522 | 27682 | N/A | 0 | 0 |  | 0 | 0 | -85840 | Within 5-year borrow
St Helena | 2015 | 1012527 | 27853 | N/A | 0 | 0 |  | 1153902 | 1153902 | -113522 | Within 5-year borrow
St Helena | 2014 | 984252 | 28275 | N/A | 0 | 0 |  | 0 | 0 | 1012527
St Helena | 2013 | 955551 | 28701 | N/A | 0 | 0 |  | 0 | 0 | 984252
St Helena | 2012 | 926924 | 28627 | N/A | 0 | 0 |  | 0 | 0 | 955551
St Helena | 2011 | 898442 | 28482 | N/A | 0 | 0 |  | 0 | 0 | 926924
St Helena | 2010 | 843181 | 55261 | N/A | 0 | 0 |  | 0 | 0 | 898442
St Helena | 2009 | 787984 | 55197 | N/A | 0 | 0 |  | 0 | 0 | 843181
St Helena | 2008 | 732527 | 55129 | N/A | 0 | 0 |  | 0 | 0 | 787984
St Helena | 2007 | 677282 | 55245 | N/A | 0 | 0 |  | 0 | 0 | 732527
Yountville | 2019 | 166843 | 7231 | N/A | 0 | 0 |  | 0 | 0 | 174074
Yountville | 2018 | 159603 | 7240 | N/A | 0 | 0 |  | 0 | 0 | 166843
Yountville | 2017 | 152354 | 7249 | N/A | 0 | 0 |  | 0 | 0 | 159603
Yountville | 2016 | 145079 | 7275 | N/A | 0 | 0 |  | 0 | 0 | 152354
Yountville | 2015 | 137800 | 7279 | N/A | 0 | 0 |  | 0 | 0 | 145079
Yountville | 2014 | 130537 | 7263 | N/A | 0 | 0 |  | 0 | 0 | 137800
Yountville | 2013 | 123046 | 7491 | N/A | 0 | 0 |  | 0 | 0 | 130537
Yountville | 2012 | 115406 | 7640 | N/A | 0 | 0 |  | 0 | 0 | 123046
Yountville | 2011 | 107886 | 7520 | N/A | 0 | 0 |  | 0 | 0 | 115406
Yountville | 2010 | 93822 | 14064 | N/A | 0 | 0 |  | 0 | 0 | 107886
Yountville | 2009 | 79785 | 14037 | N/A | 0 | 0 |  | 0 | 0 | 93822
Yountville | 2008 | 65654 | 14045 | N/A | 0 | 0 |  | 0 | 0 | 79785
Yountville | 2007 | 51566 | 14088 | N/A | 0 | 0 |  | 0 | 0 | 65654
Napa County Total |  |  | 8216573 |  |  | 0 |  | 20056918.58 | 20056918.58
Nevada County
Grass Valley | 2019 | 693340.39 | 55345 | N/A | 0 | 0 |  | 0 | 0 | 748685.39
Grass Valley | 2018 | 638155.39 | 55185 | N/A | 0 | 0 |  | 0 | 0 | 693340.39
Grass Valley | 2017 | 582780.39 | 55375 | N/A | 0 | 0 |  | 0 | 0 | 638155.39
Grass Valley | 2016 | 528586.39 | 54194 | N/A | 0 | 0 |  | 0 | 0 | 582780.39
Grass Valley | 2015 | 473850.39 | 54736 | N/A | 0 | 0 |  | 0 | 0 | 528586.39
Grass Valley | 2014 | 418917.39 | 54933 | N/A | 0 | 0 |  | 0 | 0 | 473850.39
Grass Valley | 2013 | 364288.39 | 54629 | N/A | 0 | 0 |  | 0 | 0 | 418917.39
Grass Valley | 2012 | 309678.39 | 54610 | N/A | 0 | 0 |  | 0 | 0 | 364288.39
Grass Valley | 2011 | 255584.39 | 54094 | N/A | 0 | 0 |  | 0 | 0 | 309678.39
Grass Valley | 2010 | 162545.39 | 93039 | N/A | 0 | 0 |  | 0 | 0 | 255584.39
Grass Valley | 2009 | 69574.39 | 92971 | N/A | 0 | 0 |  | 0 | 0 | 162545.39
Grass Valley | 2008 | -23894.61 | 92846 | N/A | 0 | 0 |  | 0 | 0 | 69574.39
Grass Valley | 2007 | -116087.61 | 92193 | N/A | 0 | 0 |  | 0 | 0 | -23894.61 | Borrowed beyond 5 years (see CPUC Decision 11-05-018)
Nevada City | 2019 | 625468 | 18963 | N/A | 0 | 0 |  | 0 | 0 | 644431
Nevada City | 2018 | 606593 | 18875 | N/A | 0 | 0 |  | 0 | 0 | 625468
Nevada City | 2017 | 587690 | 18903 | N/A | 0 | 0 |  | 0 | 0 | 606593
Nevada City | 2016 | 568873 | 18817 | N/A | 0 | 0 |  | 0 | 0 | 587690
Nevada City | 2015 | 549928 | 18945 | N/A | 0 | 0 |  | 0 | 0 | 568873
Nevada City | 2014 | 530958 | 18970 | N/A | 0 | 0 |  | 0 | 0 | 549928
Nevada City | 2013 | 512234 | 18724 | N/A | 0 | 0 |  | 0 | 0 | 530958
Nevada City | 2012 | 493514 | 18720 | N/A | 0 | 0 |  | 0 | 0 | 512234
Nevada City | 2011 | 474429 | 19085 | N/A | 0 | 0 |  | 0 | 0 | 493514
Nevada City | 2010 | 438339 | 36090 | N/A | 0 | 0 |  | 0 | 0 | 474429
Nevada City | 2009 | 402287 | 36052 | N/A | 0 | 0 |  | 0 | 0 | 438339
Nevada City | 2008 | 365996 | 36072 | N/A | 0 | 0 |  | 0 | 0 | 402287
Nevada City | 2007 | 330022 | 35974 | N/A | 0 | 0 |  | 0 | 0 | 365996
Nevada County | 2019 | 8690768.89 | 341250 | N/A | 0 | 0 |  | 0 | 0 | 9032018.89
Nevada County | 2018 | 8440331.16 | 339322 | N/A | 0 | 0 |  | 88884.27 | 0 | 8690768.89
Nevada County | 2017 | 11039754 | 339263 | N/A | 0 | 0 |  | 2938685.84 | 2938685.84 | 8440331.16
Nevada County | 2016 | 10703993 | 335761 | N/A | 0 | 0 |  | 0 | 0 | 11039754
Nevada County | 2015 | 10365573 | 338420 | N/A | 0 | 0 |  | 0 | 0 | 10703993
Nevada County | 2014 | 10025965 | 339608 | N/A | 0 | 0 |  | 0 | 0 | 10365573
Nevada County | 2013 | 9688927 | 337038 | N/A | 0 | 0 |  | 0 | 0 | 10025965
Nevada County | 2012 | 9351665 | 337262 | N/A | 0 | 0 |  | 0 | 0 | 9688927
Nevada County | 2011 | 9014142 | 337523 | N/A | 0 | 0 |  | 0 | 0 | 9351665
Nevada County | 2010 | 8371369 | 642773 | N/A | 0 | 0 |  | 0 | 0 | 9014142
Nevada County | 2009 | 7729558 | 641811 | N/A | 0 | 0 |  | 0 | 0 | 8371369
Nevada County | 2008 | 7083889 | 641779 | N/A | 0 | 0 |  | 0 | 0 | 7729558
Nevada County | 2007 | 6442133 | 641756 | N/A | 0 | 0 |  | 0 | 0 | 7083889
Nevada County Total |  |  | 6791906 |  |  | 0 |  | 3027570.11 | 2938685.84
Placer County
Auburn | 2019 | -47890.4 | 56521 | N/A | 0 | 0 |  | 0 | 0 | 8630.6
Auburn | 2018 | -104025.4 | 56135 | N/A | 0 | 0 |  | 0 | 0 | -47890.4 | Within 5-year borrow
Auburn | 2017 | -160098.4 | 56073 | N/A | 0 | 0 |  | 0 | 0 | -104025.4 | Within 5-year borrow
Auburn | 2016 | -215857.4 | 55759 | N/A | 0 | 0 |  | 0 | 0 | -160098.4 | Within 5-year borrow
Auburn | 2015 | 1272555 | 56272 | N/A | 0 | 0 |  | 1544684.4 | 1544684.4 | -215857.4 | Within 5-year borrow
Auburn | 2014 | 1216262 | 56293 | N/A | 0 | 0 |  | 0 | 0 | 1272555
Auburn | 2013 | 1160575 | 55687 | N/A | 0 | 0 |  | 0 | 0 | 1216262
Auburn | 2012 | 1104701 | 55874 | N/A | 0 | 0 |  | 0 | 0 | 1160575
Auburn | 2011 | 1048106 | 56595 | N/A | 0 | 0 |  | 0 | 0 | 1104701
Auburn | 2010 | 945184 | 102922 | N/A | 0 | 0 |  | 0 | 0 | 1048106
Auburn | 2009 | 842263 | 102921 | N/A | 0 | 0 |  | 0 | 0 | 945184
Auburn | 2008 | 739021 | 102592 | N/A | 0 | 0 |  | 0 | 0 | 842263
Auburn | 2007 | 636628 | 102393 | N/A | 0 | 0 |  | 0 | 0 | 739021
Colfax | 2019 | 198354.17 | 9320 | N/A | 0 | 0 |  | 0 | 0 | 207674.17
Colfax | 2018 | 189148.17 | 9206 | N/A | 0 | 0 |  | 0 | 0 | 198354.17
Colfax | 2017 | 179802.17 | 9346 | N/A | 0 | 0 |  | 0 | 0 | 189148.17
Colfax | 2016 | 170446.17 | 9356 | N/A | 0 | 0 |  | 0 | 0 | 179802.17
Colfax | 2015 | 167594 | 9387 | N/A | 0 | 0 |  | 6534.83 | 0 | 170446.17
Colfax | 2014 | 158131 | 9463 | N/A | 0 | 0 |  | 0 | 0 | 167594
Colfax | 2013 | 148677 | 9454 | N/A | 0 | 0 |  | 0 | 0 | 158131
Colfax | 2012 | 139226 | 9451 | N/A | 0 | 0 |  | 0 | 0 | 148677
Colfax | 2011 | 129930 | 9296 | N/A | 0 | 0 |  | 0 | 0 | 139226
Colfax | 2010 | 112868 | 17062 | N/A | 0 | 0 |  | 0 | 0 | 129930
Colfax | 2009 | 95996 | 16872 | N/A | 0 | 0 |  | 0 | 0 | 112868
Colfax | 2008 | 78948 | 16943 | N/A | 0 | 0 |  | 0 | 0 | 95996
Colfax | 2007 | 62044 | 16904 | N/A | 0 | 0 |  | 0 | 0 | 78948
Lincoln | 2019 | 1110026 | 87831 | N/A | 0 | 0 |  | 0 | 0 | 1197857
Lincoln | 2018 | 1022196 | 87830 | N/A | 0 | 0 |  | 0 | 0 | 1110026
Lincoln | 2017 | 935307 | 86889 | N/A | 0 | 0 |  | 0 | 0 | 1022196
Lincoln | 2016 | 849331 | 85976 | N/A | 0 | 0 |  | 0 | 0 | 935307
Lincoln | 2015 | 763069 | 86262 | N/A | 0 | 0 |  | 0 | 0 | 849331
Lincoln | 2014 | 677259 | 85810 | N/A | 0 | 0 |  | 0 | 0 | 763069
Lincoln | 2013 | 592353 | 84906 | N/A | 0 | 0 |  | 0 | 0 | 677259
Lincoln | 2012 | 507605 | 84748 | N/A | 0 | 0 |  | 0 | 0 | 592353
Lincoln | 2011 | 423249 | 84356 | N/A | 0 | 0 |  | 0 | 0 | 507605
Lincoln | 2010 | 329247 | 94002 | N/A | 0 | 0 |  | 0 | 0 | 423249
Lincoln | 2009 | 235658 | 93589 | N/A | 0 | 0 |  | 0 | 0 | 329247
Lincoln | 2008 | 141714 | 92986 | N/A | 0 | 0 |  | 0 | 0 | 235658
Lincoln | 2007 | 51082 | 90632 | N/A | 0 | 0 |  | 0 | 0 | 141714
Loomis | 2019 | 963229 | 24135 | N/A | 0 | 0 |  | 0 | 0 | 987364
Loomis | 2018 | 939266 | 23963 | N/A | 0 | 0 |  | 0 | 0 | 963229
Loomis | 2017 | 915287 | 23979 | N/A | 0 | 0 |  | 0 | 0 | 939266
Loomis | 2016 | 891650 | 23637 | N/A | 0 | 0 |  | 0 | 0 | 915287
Loomis | 2015 | 867788 | 23862 | N/A | 0 | 0 |  | 0 | 0 | 891650
Loomis | 2014 | 843895 | 23893 | N/A | 0 | 0 |  | 0 | 0 | 867788
Loomis | 2013 | 820040 | 23855 | N/A | 0 | 0 |  | 0 | 0 | 843895
Loomis | 2012 | 796164 | 23876 | N/A | 0 | 0 |  | 0 | 0 | 820040
Loomis | 2011 | 772498 | 23666 | N/A | 0 | 0 |  | 0 | 0 | 796164
Loomis | 2010 | 729240 | 43258 | N/A | 0 | 0 |  | 0 | 0 | 772498
Loomis | 2009 | 686037 | 43203 | N/A | 0 | 0 |  | 0 | 0 | 729240
Loomis | 2008 | 642497 | 43266 | N/A | 0 | 0 |  | 0 | 0 | 686037
Loomis | 2007 | 599214 | 43283 | N/A | 0 | 0 |  | 0 | 0 | 642497
Placer County | 2019 | -1432355.02 | 378603 | N/A | 0 | 0 |  | 0 | 0 | -1053752.02 | Within 5-year borrow
Placer County | 2018 | -1896834.29 | 375595 | N/A | 0 | 0 |  | -88884.27 | 0 | -1432355.02 | Within 5-year borrow
Placer County | 2017 | -2274227.29 | 377393 | N/A | 0 | 0 |  | 0 | 0 | -1896834.29 | Borrowed beyond 5 years (see AL 4553-E)
Placer County | 2016 | 7005451.73 | 373027 | N/A | 0 | 0 |  | 9652706.02 | 9652706.02 | -2274227.29 | Borrowed beyond 5 years (see AL 4553-E)
Placer County | 2015 | 6629629.73 | 375822 | N/A | 0 | 0 |  | 0 | 0 | 7005451.73
Placer County | 2014 | 6252714.73 | 376915 | N/A | 0 | 0 |  | 0 | 0 | 6629629.73
Placer County | 2013 | 8637215.73 | 377391 | N/A | 0 | 0 |  | 2761892 | 2761892 | 6252714.73
Placer County | 2012 | 8260023.73 | 377192 | N/A | 0 | 0 |  | 0 | 0 | 8637215.73
Placer County | 2011 | 7883141.73 | 376882 | N/A | 0 | 0 |  | 0 | 0 | 8260023.73
Placer County | 2010 | 7184424.73 | 698717 | N/A | 0 | 0 |  | 0 | 0 | 7883141.73
Placer County | 2009 | 6486384.73 | 698040 | N/A | 0 | 0 |  | 0 | 0 | 7184424.73
Placer County | 2008 | 5784165.73 | 697876 | N/A | 0 | 0 |  | 0 | 0 | 6486384.73
Placer County | 2007 | 5175585 | 697465 | N/A | 0 | 0 |  | 88884.27 | 0 | 5784165.73
Rocklin | 2019 | 0 | 125157 | N/A | 0 | 0 |  | 0 | 0 | 125157
Rocklin | 2018 | 315136 | 122944 | N/A | 0 | 0 |  | 0 | 0 | 0
Rocklin | 2017 | 2196293 | 118843 | N/A | 0 | 0 |  | 0 | 0 | 315136
Rocklin | 2016 | 2080256 | 116037 | N/A | 0 | 0 |  | 0 | 0 | 2196293
Rocklin | 2015 | 1964299 | 115957 | N/A | 0 | 0 |  | 0 | 0 | 2080256
Rocklin | 2014 | 1848500 | 115799 | N/A | 0 | 0 |  | 0 | 0 | 1964299
Rocklin | 2013 | 1733786 | 114714 | N/A | 0 | 0 |  | 0 | 0 | 1848500
Rocklin | 2012 | 1619234 | 114552 | N/A | 0 | 0 |  | 0 | 0 | 1733786
Rocklin | 2011 | 1504446 | 114788 | N/A | 0 | 0 |  | 0 | 0 | 1619234
Rocklin | 2010 | 1353273 | 151173 | N/A | 0 | 0 |  | 0 | 0 | 1504446
Rocklin | 2009 | 1202815 | 150458 | N/A | 0 | 0 |  | 0 | 0 | 1353273
Rocklin | 2008 | 1051973 | 149550 | N/A | 0 | 0 |  | 0 | 0 | 1202815
Rocklin | 2007 | 904215 | 147758 | N/A | 0 | 0 |  | 0 | 0 | 1051973
Roseville | 2019 | 19040 | 203 | N/A | 0 | 0 |  | 0 | 0 | 19243
Roseville | 2018 | 18830 | 210 | N/A | 0 | 0 |  | 0 | 0 | 19040
Roseville | 2017 | 18594 | 236 | N/A | 0 | 0 |  | 0 | 0 | 18830
Roseville | 2016 | 18363 | 231 | N/A | 0 | 0 |  | 0 | 0 | 18594
Roseville | 2015 | 1334 | 17029 | N/A | 0 | 0 |  | 0 | 0 | 18363
Roseville | 2014 | 1103 | 231 | N/A | 0 | 0 |  | 0 | 0 | 1334
Roseville | 2013 | 951 | 152 | N/A | 0 | 0 |  | 0 | 0 | 1103
Roseville | 2012 | 842 | 109 | N/A | 0 | 0 |  | 0 | 0 | 951
Roseville | 2011 | 514 | 328 | N/A | 0 | 0 |  | 0 | 0 | 842
Roseville | 2010 | 254 | 260 | N/A | 0 | 0 |  | 0 | 0 | 514
Roseville | 2009 | 0 | 254 | N/A | 0 | 0 |  | 0 | 0 | 254
Placer County Total |  |  | 10459681 |  |  | 0 |  | 13965817.25 | 13959282.42
Plumas County
Plumas County | 2019 | 1141962.38 | 101351 | N/A | 0 | 0 |  | 0 | 0 | 1243313.38
Plumas County | 2018 | 1041334.38 | 100628 | N/A | 0 | 0 |  | 0 | 0 | 1141962.38
Plumas County | 2017 | 940539.38 | 100795 | N/A | 0 | 0 |  | 0 | 0 | 1041334.38
Plumas County | 2016 | 2396216 | 100194 | N/A | 0 | 0 |  | 1555870.62 | 1555870.62 | 940539.38
Plumas County | 2015 | 2295151 | 101065 | N/A | 0 | 0 |  | 0 | 0 | 2396216
Plumas County | 2014 | 2193546 | 101605 | N/A | 0 | 0 |  | 0 | 0 | 2295151
Plumas County | 2013 | 2091838 | 101708 | N/A | 0 | 0 |  | 0 | 0 | 2193546
Plumas County | 2012 | 1990111 | 101727 | N/A | 0 | 0 |  | 0 | 0 | 2091838
Plumas County | 2011 | 1888314 | 101797 | N/A | 0 | 0 |  | 0 | 0 | 1990111
Plumas County | 2010 | 1688021 | 200293 | N/A | 0 | 0 |  | 0 | 0 | 1888314
Plumas County | 2009 | 1487982 | 200039 | N/A | 0 | 0 |  | 0 | 0 | 1688021
Plumas County | 2008 | 1286721 | 200087 | N/A | 0 | 0 |  | 0 | 0 | 1487982
Plumas County | 2007 | 1087235 | 199486 | N/A | 0 | 0 |  | 0 | 0 | 1286721
Plumas County Total |  |  | 1710775 |  |  | 0 |  | 1555870.62 | 1555870.62
Sacramento County
Folsom | 2019 | 0 | 0 | N/A | 0 | 0 |  | 0 | 0 | 0
Folsom | 2018 | 0 | 0 | N/A | 0 | 0 |  | 0 | 0 | 0
Folsom | 2017 | 0 | 0 | N/A | 0 | 0 |  | 0 | 0 | 0
Folsom | 2016 | 0 | 0 | N/A | 0 | 0 |  | 0 | 0 | 0
Folsom | 2015 | 0 | 0 | N/A | 0 | 0 |  | 0 | 0 | 0
Folsom | 2014 | 0 | 0 | N/A | 0 | 0 |  | 0 | 0 | 0
Folsom | 2013 | 0 | 0 | N/A | 0 | 0 |  | 0 | 0 | 0
Folsom | 2012 | 0 | 0 | N/A | 0 | 0 |  | 0 | 0 | 0
Folsom | 2011 | 0 | 0 | N/A | 0 | 0 |  | 0 | 0 | 0
Folsom | 2010 | 0 | 0 | N/A | 0 | 0 |  | 0 | 0 | 0
Folsom | 2009 | 0 | 9 | N/A | 0 | 0 |  | 0 | 0 | 0
Isleton | 2019 | 299799 | 4833 | N/A | 0 | 0 |  | 0 | 0 | 304632
Isleton | 2018 | 295005 | 4794 | N/A | 0 | 0 |  | 0 | 0 | 299799
Isleton | 2017 | 290185 | 4820 | N/A | 0 | 0 |  | 0 | 0 | 295005
Isleton | 2016 | 285482 | 4703 | N/A | 0 | 0 |  | 0 | 0 | 290185
Isleton | 2015 | 280675 | 4807 | N/A | 0 | 0 |  | 0 | 0 | 285482
Isleton | 2014 | 275844 | 4831 | N/A | 0 | 0 |  | 0 | 0 | 280675
Isleton | 2013 | 270861 | 4983 | N/A | 0 | 0 |  | 0 | 0 | 275844
Isleton | 2012 | 265727 | 5134 | N/A | 0 | 0 |  | 0 | 0 | 270861
Isleton | 2011 | 260579 | 5148 | N/A | 0 | 0 |  | 0 | 0 | 265727
Isleton | 2010 | 249108 | 11471 | N/A | 0 | 0 |  | 0 | 0 | 260579
Isleton | 2009 | 237628 | 11480 | N/A | 0 | 0 |  | 0 | 0 | 249108
Isleton | 2008 | 226070 | 11498 | N/A | 0 | 0 |  | 0 | 0 | 237628
Isleton | 2007 | 214609 | 11461 | N/A | 0 | 0 |  | 0 | 0 | 226070
Sacramento County | 2019 | 1044533 | 20098 | N/A | 0 | 0 |  | 0 | 0 | 1064631
Sacramento County | 2018 | 1024902 | 19631 | N/A | 0 | 0 |  | 0 | 0 | 1044533
Sacramento County | 2017 | 1005119 | 19783 | N/A | 0 | 0 |  | 0 | 0 | 1024902
Sacramento County | 2016 | 985449 | 19670 | N/A | 0 | 0 |  | 0 | 0 | 1005119
Sacramento County | 2015 | 965454 | 19995 | N/A | 0 | 0 |  | 0 | 0 | 985449
Sacramento County | 2014 | 945334 | 20120 | N/A | 0 | 0 |  | 0 | 0 | 965454
Sacramento County | 2013 | 924766 | 20568 | N/A | 0 | 0 |  | 0 | 0 | 945334
Sacramento County | 2012 | 904434 | 20332 | N/A | 0 | 0 |  | 0 | 0 | 924766
Sacramento County | 2011 | 884106 | 20328 | N/A | 0 | 0 |  | 0 | 0 | 904434
Sacramento County | 2010 | 833372 | 50734 | N/A | 0 | 0 |  | 0 | 0 | 884106
Sacramento County | 2009 | 782670 | 50693 | N/A | 0 | 0 |  | 0 | 0 | 833372
Sacramento County | 2008 | 731612 | 50821 | N/A | 0 | 0 |  | 0 | 0 | 782670
Sacramento County | 2007 | 680615 | 50997 | N/A | 0 | 0 |  | 0 | 0 | 731612
Sacramento County Total |  |  | 473742 |  |  | 0 |  | 0 | 0
San Benito County
Hollister | 2019 | 600747 | 72295 | N/A | 0 | 0 |  | 0 | 0 | 673042
Hollister | 2018 | 529515 | 71232 | N/A | 0 | 0 |  | 0 | 0 | 600747
Hollister | 2017 | 459990 | 69525 | N/A | 0 | 0 |  | 0 | 0 | 529515
Hollister | 2016 | 391758 | 68232 | N/A | 0 | 0 |  | 0 | 0 | 459990
Hollister | 2015 | 323086 | 68672 | N/A | 0 | 0 |  | 0 | 0 | 391758
Hollister | 2014 | 254404 | 68682 | N/A | 0 | 0 |  | 0 | 0 | 323086
Hollister | 2013 | 186199 | 68205 | N/A | 0 | 0 |  | 0 | 0 | 254404
Hollister | 2012 | 117961 | 68238 | N/A | 0 | 0 |  | 0 | 0 | 186199
Hollister | 2011 | 51007 | 66954 | N/A | 0 | 0 |  | 0 | 0 | 117961
Hollister | 2010 | -64442 | 115449 | N/A | 0 | 0 |  | 0 | 0 | 51007
Hollister | 2009 | -179715 | 115273 | N/A | 0 | 0 |  | 0 | 0 | -64442 | Within 5-year borrow
Hollister | 2008 | -295931 | 115443 | N/A | 0 | 0 |  | 0 | 0 | -179715 | Within 5-year borrow
Hollister | 2007 | -411609 | 115678 | N/A | 0 | 0 |  | 0 | 0 | -295931 | Within 5-year borrow
San Benito County | 2019 | 3539154 | 82122 | N/A | 0 | 0 |  | 0 | 0 | 3621276
San Benito County | 2018 | 3457621 | 81533 | N/A | 0 | 0 |  | 0 | 0 | 3539154
San Benito County | 2017 | 3375968 | 81653 | N/A | 0 | 0 |  | 0 | 0 | 3457621
San Benito County | 2016 | 3295280 | 80688 | N/A | 0 | 0 |  | 0 | 0 | 3375968
San Benito County | 2015 | 3213770 | 81510 | N/A | 0 | 0 |  | 0 | 0 | 3295280
San Benito County | 2014 | 3131905 | 81865 | N/A | 0 | 0 |  | 0 | 0 | 3213770
San Benito County | 2013 | 3049196 | 82709 | N/A | 0 | 0 |  | 0 | 0 | 3131905
San Benito County | 2012 | 2966287 | 82909 | N/A | 0 | 0 |  | 0 | 0 | 3049196
San Benito County | 2011 | 2883056 | 83231 | N/A | 0 | 0 |  | 0 | 0 | 2966287
San Benito County | 2010 | 2715800 | 167256 | N/A | 0 | 0 |  | 0 | 0 | 2883056
San Benito County | 2009 | 2548637 | 167163 | N/A | 0 | 0 |  | 0 | 0 | 2715800
San Benito County | 2008 | 2380117 | 167552 | N/A | 0 | 0 |  | 0 | 0 | 2548637
San Benito County | 2007 | 2212417 | 167700 | N/A | 0 | 0 |  | 0 | 0 | 2380117
San Juan Bautista | 2019 | 367581 | 7725 | N/A | 0 | 0 |  | 0 | 0 | 375306
San Juan Bautista | 2018 | 359909 | 7672 | N/A | 0 | 0 |  | 0 | 0 | 367581
San Juan Bautista | 2017 | 352223 | 7686 | N/A | 0 | 0 |  | 0 | 0 | 359909
San Juan Bautista | 2016 | 344653 | 7570 | N/A | 0 | 0 |  | 0 | 0 | 352223
San Juan Bautista | 2015 | 336980 | 7673 | N/A | 0 | 0 |  | 0 | 0 | 344653
San Juan Bautista | 2014 | 329289 | 7691 | N/A | 0 | 0 |  | 0 | 0 | 336980
San Juan Bautista | 2013 | 321632 | 7657 | N/A | 0 | 0 |  | 0 | 0 | 329289
San Juan Bautista | 2012 | 313965 | 7667 | N/A | 0 | 0 |  | 0 | 0 | 321632
San Juan Bautista | 2011 | 306004 | 7961 | N/A | 0 | 0 |  | 0 | 0 | 313965
San Juan Bautista | 2010 | 290122 | 15882 | N/A | 0 | 0 |  | 0 | 0 | 306004
San Juan Bautista | 2009 | 274247 | 15875 | N/A | 0 | 0 |  | 0 | 0 | 290122
San Juan Bautista | 2008 | 258178 | 15976 | N/A | 0 | 0 |  | 0 | 0 | 274247
San Juan Bautista | 2007 | 242340 | 15838 | N/A | 0 | 0 |  | 0 | 0 | 258178
San Benito County Total |  |  | 2624642 |  |  | 0 |  | 0 | 0
San Francisco County
San Francisco | 2019 | -45669325.55 | 2970435 | N/A | 0 | 0 |  | 0 | 0 | -42698890.55 | Borrowed beyond 5 years (see AL 2445-E)
San Francisco | 2018 | -48798923.19 | 3141237 | N/A | 0 | 0 |  | 11639.36 | 11639.36 | -45669325.55 | Borrowed beyond 5 years (see AL 2445-E)
San Francisco | 2017 | -50670843.97 | 3134676 | N/A | 0 | 0 |  | 1262755.22 | 1262755.22 | -48798923.19 | Borrowed beyond 5 years (see AL 2445-E)
San Francisco | 2016 | -53760781.97 | 3089938 | N/A | 0 | 0 |  | 0 | 0 | -50670843.97 | Borrowed beyond 5 years (see AL 2445-E)
San Francisco | 2015 | -56870071.97 | 3109290 | N/A | 0 | 0 |  | 0 | 0 | -53760781.97 | Borrowed beyond 5 years (see AL 2445-E)
San Francisco | 2014 | -52880580.52 | 3107572 | N/A | 0 | 0 |  | 7097063.45 | 7097063.45 | -56870071.97 | Borrowed beyond 5 years (see AL 2445-E)
San Francisco | 2013 | -55952484.52 | 3071904 | N/A | 0 | 0 |  | 0 | 0 | -52880580.52 | Borrowed beyond 5 years (see AL 2445-E)
San Francisco | 2012 | -16203661.64 | 3068101 | N/A | 0 | 0 |  | 42816923.88 | 42816923.88 | -55952484.52 | Borrowed beyond 5 years (see AL 2445-E)
San Francisco | 2011 | -33353382.64 | 3069182 | N/A | 0 | 0 |  | -3442842 | -3442842 | -16203661.64 | Borrowed beyond 5 years (see AL 2445-E)
San Francisco | 2010 | 21365017.36 | 6072752 | N/A | 0 | 0 |  | 60791152 | 60791152 | -33353382.64 | Borrowed beyond 5 years (see AL 2445-E)
San Francisco | 2009 | 26396588.96 | 6065515 | N/A | 0 | 0 |  | 11097086.6 | 11097086.6 | 21365017.36
San Francisco | 2008 | 49726996.04 | 6074339 | N/A | 0 | 0 |  | 29440198.08 | 29440198.08 | 26396588.96
San Francisco | 2007 | 48000825.11 | 6103134 | N/A | 0 | 0 |  | 4376963.07 | 4376963.07 | 49726996.04
San Francisco County Total |  |  | 52078075 |  |  | 0 |  | 153450939.66 | 153450939.66
San Joaquin County
Escalon | 2019 | 643201 | 18031 | N/A | 0 | 0 |  | 0 | 0 | 661232
Escalon | 2018 | 625013 | 18188 | N/A | 0 | 0 |  | 0 | 0 | 643201
Escalon | 2017 | 606784 | 18229 | N/A | 0 | 0 |  | 0 | 0 | 625013
Escalon | 2016 | 588681 | 18103 | N/A | 0 | 0 |  | 0 | 0 | 606784
Escalon | 2015 | 570352 | 18329 | N/A | 0 | 0 |  | 0 | 0 | 588681
Escalon | 2014 | 551864 | 18488 | N/A | 0 | 0 |  | 0 | 0 | 570352
Escalon | 2013 | 533271 | 18593 | N/A | 0 | 0 |  | 0 | 0 | 551864
Escalon | 2012 | 514634 | 18637 | N/A | 0 | 0 |  | 0 | 0 | 533271
Escalon | 2011 | 495861 | 18773 | N/A | 0 | 0 |  | 0 | 0 | 514634
Escalon | 2010 | 462326 | 33535 | N/A | 0 | 0 |  | 0 | 0 | 495861
Escalon | 2009 | 428790 | 33536 | N/A | 0 | 0 |  | 0 | 0 | 462326
Escalon | 2008 | 394970 | 33602 | N/A | 0 | 0 |  | 0 | 0 | 428790
Escalon | 2007 | 361285 | 33685 | N/A | 0 | 0 |  | 0 | 0 | 394970
Lathrop | 2019 | 361264.53 | 31487 | N/A | 0 | 0 |  | 0 | 0 | 392751.53
Lathrop | 2018 | 330217.53 | 31047 | N/A | 0 | 0 |  | 0 | 0 | 361264.53
Lathrop | 2017 | 299281.53 | 30936 | N/A | 0 | 0 |  | 0 | 0 | 330217.53
Lathrop | 2016 | 265625.53 | 33656 | N/A | 0 | 0 |  | 0 | 0 | 299281.53
Lathrop | 2015 | 232179.53 | 33446 | N/A | 0 | 0 |  | 0 | 0 | 265625.53
Lathrop | 2014 | 198436.53 | 33743 | N/A | 0 | 0 |  | 0 | 0 | 232179.53
Lathrop | 2013 | 167339.53 | 31097 | N/A | 0 | 0 |  | 0 | 0 | 198436.53
Lathrop | 2012 | 136580.53 | 30759 | N/A | 0 | 0 |  | 0 | 0 | 167339.53
Lathrop | 2011 | 108372.53 | 28208 | N/A | 0 | 0 |  | 0 | 0 | 136580.53
Lathrop | 2010 | 65576.53 | 42796 | N/A | 0 | 0 |  | 0 | 0 | 108372.53
Lathrop | 2009 | 22947.53 | 42629 | N/A | 0 | 0 |  | 0 | 0 | 65576.53
Lathrop | 2008 | -19516.47 | 42156 | N/A | 0 | 0 |  | 0 | 0 | 22947.53
Lathrop | 2007 | 459392 | 41661 | N/A | 0 | 0 |  | 520569.47 | 520569.47 | -19516.47 | Within 5-year borrow
Manteca | 2019 | 4011940 | 157689 | N/A | 0 | 0 |  | 0 | 0 | 4169629
Manteca | 2018 | 3856726 | 155214 | N/A | 0 | 0 |  | 0 | 0 | 4011940
Manteca | 2017 | 3703334 | 153392 | N/A | 0 | 0 |  | 0 | 0 | 3856726
Manteca | 2016 | 3552000 | 151334 | N/A | 0 | 0 |  | 0 | 0 | 3703334
Manteca | 2015 | 3400359 | 151641 | N/A | 0 | 0 |  | 0 | 0 | 3552000
Manteca | 2014 | 3249179 | 151180 | N/A | 0 | 0 |  | 0 | 0 | 3400359
Manteca | 2013 | 3098083 | 151096 | N/A | 0 | 0 |  | 0 | 0 | 3249179
Manteca | 2012 | 2948779 | 149304 | N/A | 0 | 0 |  | 0 | 0 | 3098083
Manteca | 2011 | 2799051 | 149728 | N/A | 0 | 0 |  | 0 | 0 | 2948779
Manteca | 2010 | 2553671 | 245380 | N/A | 0 | 0 |  | 0 | 0 | 2799051
Manteca | 2009 | 2309121 | 244550 | N/A | 0 | 0 |  | 0 | 0 | 2553671
Manteca | 2008 | 2065173 | 242274 | N/A | 0 | 0 |  | 0 | 0 | 2309121
Manteca | 2007 | 1825007 | 240166 | N/A | 0 | 0 |  | 0 | 0 | 2065173
Ripon | 2019 | 15718.6 | 26638 | N/A | 0 | 0 |  | 0 | 0 | 42356.6
Ripon | 2018 | -10944.4 | 26663 | N/A | 0 | 0 |  | 0 | 0 | 15718.6
Ripon | 2017 | -37677.4 | 26733 | N/A | 0 | 0 |  | 0 | 0 | -10944.4 | Within 5-year borrow
Ripon | 2016 | -63809.4 | 26132 | N/A | 0 | 0 |  | 0 | 0 | -37677.4 | Within 5-year borrow
Ripon | 2015 | -90179.4 | 26370 | N/A | 0 | 0 |  | 0 | 0 | -63809.4 | Within 5-year borrow
Ripon | 2014 | -116760.4 | 26581 | N/A | 0 | 0 |  | 0 | 0 | -90179.4 | Within 5-year borrow
Ripon | 2013 | -143980.4 | 27220 | N/A | 0 | 0 |  | 0 | 0 | -116760.4 | Within 5-year borrow
Ripon | 2012 | -171268.4 | 27288 | N/A | 0 | 0 |  | 0 | 0 | -143980.4 | Additional research required
Ripon | 2011 | -198272.4 | 27004 | N/A | 0 | 0 |  | 0 | 0 | -171268.4 | Additional research required
Ripon | 2010 | -245797.4 | 47525 | N/A | 0 | 0 |  | 0 | 0 | -198272.4 | Within 5-year borrow
Ripon | 2009 | -293263.4 | 47466 | N/A | 0 | 0 |  | 0 | 0 | -245797.4 | Additional research required
Ripon | 2008 | 525228 | 47291 | N/A | 0 | 0 |  | 866091.4 | 866091.4 | -293263.4 | Additional research required
Ripon | 2007 | 477802 | 47426 | N/A | 0 | 0 |  | 0 | 0 | 525228
San Joaquin County | 2019 | 16183720.96 | 621379 | N/A | 0 | 0 |  | 0 | 0 | 16805099.96
San Joaquin County | 2018 | 15569368.96 | 614352 | N/A | 0 | 0 |  | 0 | 0 | 16183720.96
San Joaquin County | 2017 | 22257986 | 615247 | N/A | 0 | 0 |  | 7303864.04 | 7303864.04 | 15569368.96
San Joaquin County | 2016 | 21651190 | 606796 | N/A | 0 | 0 |  | 0 | 0 | 22257986
San Joaquin County | 2015 | 21038709 | 612481 | N/A | 0 | 0 |  | 0 | 0 | 21651190
San Joaquin County | 2014 | 20424791 | 613918 | N/A | 0 | 0 |  | 0 | 0 | 21038709
San Joaquin County | 2013 | 19794328 | 630463 | N/A | 0 | 0 |  | 0 | 0 | 20424791
San Joaquin County | 2012 | 19164032 | 630296 | N/A | 0 | 0 |  | 0 | 0 | 19794328
San Joaquin County | 2011 | 18547927 | 629924 | N/A | 0 | 0 |  | 13819 | 13819 | 19164032
San Joaquin County | 2010 | 18214236 | 1328190 | N/A | 0 | 0 |  | 994499 | 994499 | 18547927
San Joaquin County | 2009 | 16883482 | 1330754 | N/A | 0 | 0 |  | 0 | 0 | 18214236
San Joaquin County | 2008 | 15542336 | 1333778 | N/A | 0 | 0 |  | 0 | 0 | 16883482
San Joaquin County | 2007 | 14207345 | 1334991 | N/A | 0 | 0 |  | 0 | 0 | 15542336
Stockton | 2019 | 12691622.84 | 702395 | N/A | 0 | 0 |  | 0 | 0 | 13394017.84
Stockton | 2018 | 11990832.84 | 700790 | N/A | 0 | 0 |  | 0 | 0 | 12691622.84
Stockton | 2017 | 11289104.84 | 701728 | N/A | 0 | 0 |  | 0 | 0 | 11990832.84
Stockton | 2016 | 10591171.84 | 697933 | N/A | 0 | 0 |  | 0 | 0 | 11289104.84
Stockton | 2015 | 9885646.84 | 705525 | N/A | 0 | 0 |  | 0 | 0 | 10591171.84
Stockton | 2014 | 9174366.84 | 711280 | N/A | 0 | 0 |  | 0 | 0 | 9885646.84
Stockton | 2013 | 8457727.84 | 716639 | N/A | 0 | 0 |  | 0 | 0 | 9174366.84
Stockton | 2012 | 11145526.23 | 718243 | N/A | 0 | 0 |  | 3406041.39 | 3406041.39 | 8457727.84
Stockton | 2011 | 10221492.23 | 718192 | N/A | 0 | 0 |  | -205842 | -205842 | 11145526.23
Stockton | 2010 | 8905547.23 | 1315945 | N/A | 0 | 0 |  | 0 | 0 | 10221492.23
Stockton | 2009 | 10980396.39 | 1310112 | N/A | 0 | 0 |  | 3384961.16 | 3384961.16 | 8905547.23
Stockton | 2008 | 10146781.59 | 1312310 | N/A | 0 | 0 |  | 486964.2 | 486964.2 | 10980396.39
Stockton | 2007 | 9697456.28 | 1311312 | N/A | 0 | 0 |  | 861986.69 | 861986.69 | 10146781.59
Tracy | 2019 | 2938784.3 | 160314 | N/A | 0 | 0 |  | 0 | 0 | 3099098.3
Tracy | 2018 | 2779974.3 | 158810 | N/A | 0 | 0 |  | 0 | 0 | 2938784.3
Tracy | 2017 | 2622141.3 | 157833 | N/A | 0 | 0 |  | 0 | 0 | 2779974.3
Tracy | 2016 | 2466304.3 | 155837 | N/A | 0 | 0 |  | 0 | 0 | 2622141.3
Tracy | 2015 | 2309401.3 | 156903 | N/A | 0 | 0 |  | 0 | 0 | 2466304.3
Tracy | 2014 | 2151904.3 | 157497 | N/A | 0 | 0 |  | 0 | 0 | 2309401.3
Tracy | 2013 | 2743774.3 | 158105 | N/A | 0 | 0 |  | 749975 | 749975 | 2151904.3
Tracy | 2012 | 2585215.3 | 158559 | N/A | 0 | 0 |  | 0 | 0 | 2743774.3
Tracy | 2011 | 2424579.3 | 160636 | N/A | 0 | 0 |  | 0 | 0 | 2585215.3
Tracy | 2010 | 2177865.3 | 246714 | N/A | 0 | 0 |  | 0 | 0 | 2424579.3
Tracy | 2009 | 1931180.3 | 246685 | N/A | 0 | 0 |  | 0 | 0 | 2177865.3
Tracy | 2008 | 1682602.3 | 246717 | N/A | 0 | 0 |  | 0 | 0 | 1931180.3
Tracy | 2007 | 1436191.3 | 246411 | N/A | 0 | 0 |  | 0 | 0 | 1682602.3
San Joaquin County Total |  |  | 28462629 |  |  | 0 |  | 18382929.35 | 18382929.35
San Luis Obispo County
Arroyo Grande | 2019 | 1948419.85 | 60223 | N/A | 0 | 0 |  | 0 | 0 | 2008642.85
Arroyo Grande | 2018 | 1888272.85 | 60147 | N/A | 0 | 0 |  | 0 | 0 | 1948419.85
Arroyo Grande | 2017 | 1827920.85 | 60352 | N/A | 0 | 0 |  | 0 | 0 | 1888272.85
Arroyo Grande | 2016 | 1768126.85 | 59794 | N/A | 0 | 0 |  | 0 | 0 | 1827920.85
Arroyo Grande | 2015 | 4020246.63 | 60360 | N/A | 0 | 0 |  | 2312479.78 | 2312479.78 | 1768126.85
Arroyo Grande | 2014 | 959784.63 | 60462 | N/A | 0 | 3000000 | $3,000,000 (San Luis Obispo County) | 0 | 0 | 4020246.63
Arroyo Grande | 2013 | 898899.63 | 60885 | N/A | 0 | 0 |  | 0 | 0 | 959784.63
Arroyo Grande | 2012 | 837850.63 | 61049 | N/A | 0 | 0 |  | 0 | 0 | 898899.63
Arroyo Grande | 2011 | 774580.63 | 63270 | N/A | 0 | 0 |  | 0 | 0 | 837850.63
Arroyo Grande | 2010 | 660696.63 | 113884 | N/A | 0 | 0 |  | 0 | 0 | 774580.63
Arroyo Grande | 2009 | 546828.63 | 113868 | N/A | 0 | 0 |  | 0 | 0 | 660696.63
Arroyo Grande | 2008 | 432115.63 | 113979 | N/A | 0 | 0 |  | 0 | 0 | 546828.63
Arroyo Grande | 2007 | 318229.63 | 113886 | N/A | 0 | 0 |  | 0 | 0 | 432115.63
Atascadero | 2019 | 3107860 | 115342 | N/A | 0 | 0 |  | 0 | 0 | 3223202
Atascadero | 2018 | 2993362 | 114498 | N/A | 0 | 0 |  | 0 | 0 | 3107860
Atascadero | 2017 | 2878941 | 114421 | N/A | 0 | 0 |  | 0 | 0 | 2993362
Atascadero | 2016 | 2680768 | 113357 | N/A | 0 | 0 |  | 0 | 0 | 2878941
Atascadero | 2015 | 2566797 | 113971 | N/A | 0 | 0 |  | 0 | 0 | 2680768
Atascadero | 2014 | 2953163 | 113634 | N/A | 0 | 0 |  | 0 | 0 | 2566797
Atascadero | 2013 | 2839972 | 113191 | N/A | 0 | 0 |  | 0 | 0 | 2953163
Atascadero | 2012 | 2726738 | 113234 | N/A | 0 | 0 |  | 0 | 0 | 2839972
Atascadero | 2011 | 2613284 | 113454 | N/A | 0 | 0 |  | 0 | 0 | 2726738
Atascadero | 2010 | 2395574 | 217710 | N/A | 0 | 0 |  | 0 | 0 | 2613284
Atascadero | 2009 | 2177853 | 217721 | N/A | 0 | 0 |  | 0 | 0 | 2395574
Atascadero | 2008 | 1958775 | 217764 | N/A | 0 | 0 |  | 0 | 0 | 2177853
Atascadero | 2007 | 1741527 | 217248 | N/A | 0 | 0 |  | 0 | 0 | 1958775
Grover Beach | 2019 | 969141.07 | 59261 | N/A | 0 | 0 |  | 0 | 0 | 1028402.07
Grover Beach | 2018 | 910122.07 | 59019 | N/A | 0 | 0 |  | 0 | 0 | 969141.07
Grover Beach | 2017 | 851012.07 | 59110 | N/A | 0 | 0 |  | 0 | 0 | 910122.07
Grover Beach | 2016 | 792404.07 | 58608 | N/A | 0 | 0 |  | 0 | 0 | 851012.07
Grover Beach | 2015 | 733263.07 | 59141 | N/A | 0 | 0 |  | 0 | 0 | 792404.07
Grover Beach | 2014 | 673811.07 | 59452 | N/A | 0 | 0 |  | 0 | 0 | 733263.07
Grover Beach | 2013 | 614360.07 | 59451 | N/A | 0 | 0 |  | 0 | 0 | 673811.07
Grover Beach | 2012 | 1724639 | 59507 | N/A | 0 | 0 |  | 1169785.93 | 1169785.93 | 614360.07
Grover Beach | 2011 | 1665030 | 59609 | N/A | 0 | 0 |  | 0 | 0 | 1724639
Grover Beach | 2010 | 1548382 | 116648 | N/A | 0 | 0 |  | 0 | 0 | 1665030
Grover Beach | 2009 | 1431841 | 116541 | N/A | 0 | 0 |  | 0 | 0 | 1548382
Grover Beach | 2008 | 1314735 | 116421 | N/A | 0 | 0 |  | 0 | 0 | 1431841
Grover Beach | 2007 | 1198307 | 116428 | N/A | 0 | 0 |  | 0 | 0 | 1314735
Morro Bay | 2019 | 2161547.78 | 67433 | N/A | 0 | 0 |  | 0 | 0 | 2228980.78
Morro Bay | 2018 | 2427167 | 67100 | N/A | 0 | 0 |  | 332719.22 | 0 | 2161547.78
Morro Bay | 2017 | 2359988 | 67179 | N/A | 0 | 0 |  | 0 | 0 | 2427167
Morro Bay | 2016 | 2293559 | 66429 | N/A | 0 | 0 |  | 0 | 0 | 2359988
Morro Bay | 2015 | 2226573 | 66986 | N/A | 0 | 0 |  | 0 | 0 | 2293559
Morro Bay | 2014 | 2159277 | 67296 | N/A | 0 | 0 |  | 0 | 0 | 2226573
Morro Bay | 2013 | 2091422 | 67855 | N/A | 0 | 0 |  | 0 | 0 | 2159277
Morro Bay | 2012 | 2023500 | 67922 | N/A | 0 | 0 |  | 0 | 0 | 2091422
Morro Bay | 2011 | 1955467 | 68033 | N/A | 0 | 0 |  | 0 | 0 | 2023500
Morro Bay | 2010 | 1820136 | 135331 | N/A | 0 | 0 |  | 0 | 0 | 1955467
Morro Bay | 2009 | 1685031 | 135105 | N/A | 0 | 0 |  | 0 | 0 | 1820136
Morro Bay | 2008 | 1549318 | 134931 | N/A | 0 | 0 |  | 0 | 0 | 1685031
Morro Bay | 2007 | 1414455 | 134863 | N/A | 0 | 0 |  | 0 | 0 | 1549318
Paso Robles | 2019 | -243277.18 | 84886 | N/A | 0 | 0 |  | 0 | 0 | -158391.18 | Within 5-year borrow
Paso Robles | 2018 | -327632.18 | 84355 | N/A | 0 | 0 |  | 0 | 0 | -243277.18 | Within 5-year borrow
Paso Robles | 2017 | -412029.18 | 84397 | N/A | 0 | 0 |  | 0 | 0 | -327632.18 | Within 5-year borrow
Paso Robles | 2016 | 2309872 | 83605 | N/A | 0 | 0 |  | 2720690.18 | 2720690.18 | -412029.18 | Within 5-year borrow
Paso Robles | 2015 | 2225249 | 84623 | N/A | 0 | 0 |  | 0 | 0 | 2309872
Paso Robles | 2014 | 1640433 | 84816 | N/A | 0 | 500000 | $500,000 (Atascadero) | 0 | 0 | 2225249
Paso Robles | 2013 | 1554981 | 85452 | N/A | 0 | 0 |  | 0 | 0 | 1640433
Paso Robles | 2012 | 1469659 | 85322 | N/A | 0 | 0 |  | 0 | 0 | 1554981
Paso Robles | 2011 | 1383847 | 85812 | N/A | 0 | 0 |  | 0 | 0 | 1469659
Paso Robles | 2010 | 1238235 | 145612 | N/A | 0 | 0 |  | 0 | 0 | 1383847
Paso Robles | 2009 | 1092819 | 145416 | N/A | 0 | 0 |  | 0 | 0 | 1238235
Paso Robles | 2008 | 946387 | 145443 | N/A | 0 | 0 |  | 0 | 0 | 1092819
Paso Robles | 2007 | 800970 | 145417 | N/A | 0 | 0 |  | 0 | 0 | 946387
Pismo Beach | 2019 | 4860517.04 | 40466 | N/A | 0 | 0 |  | 0 | 0 | 4900983.04
Pismo Beach | 2018 | 4150248.04 | 40269 | N/A | 0 | 670000 | Kings County ($670,000) | 0 | 0 | 4860517.04
Pismo Beach | 2017 | 4082759.04 | 40126 | N/A | 0 | 27363 | $27,363 (King City) | 0 | 0 | 4150248.04
Pismo Beach | 2016 | 3290865 | 39746 | N/A | 0 | 752148.04 | $752,148.04 (King City) | 0 | 0 | 4082759.04
Pismo Beach | 2015 | 3250968 | 39897 | N/A | 0 | 0 |  | 0 | 0 | 3290865
Pismo Beach | 2014 | 1210884 | 40084 | N/A | 0 | 2000000 | $2,000,000 (San Luis Obispo County) | 0 | 0 | 3250968
Pismo Beach | 2013 | 1169830 | 41054 | N/A | 0 | 0 |  | 0 | 0 | 1210884
Pismo Beach | 2012 | 1128915 | 40915 | N/A | 0 | 0 |  | 0 | 0 | 1169830
Pismo Beach | 2011 | 1088125 | 40790 | N/A | 0 | 0 |  | 0 | 0 | 1128915
Pismo Beach | 2010 | 1014701 | 73424 | N/A | 0 | 0 |  | 0 | 0 | 1088125
Pismo Beach | 2009 | 941403 | 73298 | N/A | 0 | 0 |  | 0 | 0 | 1014701
Pismo Beach | 2008 | 867776 | 73160 | N/A | 0 | 0 |  | 0 | 0 | 941403
Pismo Beach | 2007 | 794566 | 73210 | N/A | 0 | 0 |  | 0 | 0 | 867776
San Luis Obispo | 2019 | -1056799.87 | 178751 | N/A | 0 | 0 |  | 0 | 0 | -878048.87 | Within 5-year borrow
San Luis Obispo | 2018 | -1235034.87 | 178235 | N/A | 0 | 0 |  | 0 | 0 | -1056799.87 | Borrowed beyond 5 years (see AL 4553-E)
San Luis Obispo | 2017 | -1413331.87 | 178297 | N/A | 0 | 0 |  | 0 | 0 | -1235034.87 | Borrowed beyond 5 years (see AL 4553-E)
San Luis Obispo | 2016 | -1589970.87 | 176639 | N/A | 0 | 0 |  | 0 | 0 | -1413331.87 | Borrowed beyond 5 years (see AL 4553-E)
San Luis Obispo | 2015 | -1767847.87 | 177877 | N/A | 0 | 0 |  | 0 | 0 | -1589970.87 | Borrowed beyond 5 years (see AL 4553-E)
San Luis Obispo | 2014 | 1517931 | 178543 | N/A | 0 | 0 |  | 3464321.87 | 3464321.87 | -1767847.87 | Borrowed beyond 5 years (see AL 4553-E)
San Luis Obispo | 2013 | 3560344 | 179164 | N/A | 0 | 0 |  | 2221577 | 2221577 | 1517931
San Luis Obispo | 2012 | 3380218 | 180126 | N/A | 0 | 0 |  | 0 | 0 | 3560344
San Luis Obispo | 2011 | 1517708 | 180092 | N/A | 0 | 0 |  | -1682418 | -1682418 | 3380218
San Luis Obispo | 2010 | 1183193 | 334515 | N/A | 0 | 0 |  | 0 | 0 | 1517708
San Luis Obispo | 2009 | 849258 | 333935 | N/A | 0 | 0 |  | 0 | 0 | 1183193
San Luis Obispo | 2008 | 514832 | 332379 | N/A | 0 | 0 |  | 0 | 0 | 849258
San Luis Obispo | 2007 | 183020 | 331812 | N/A | 0 | 0 |  | 0 | 0 | 514832
San Luis Obispo County | 2019 | -1332808.29 | 511924 | N/A | 0 | 0 |  | 0 | 0 | -820884.29 | Within 5-year borrow
San Luis Obispo County | 2018 | 3477300.33 | 508265 | N/A | 0 | 0 |  | 5318373.62 | 5318373.62 | -1332808.29 | Within 5-year borrow
San Luis Obispo County | 2017 | 2969145.33 | 508155 | N/A | 0 | 0 |  | 0 | 0 | 3477300.33
San Luis Obispo County | 2016 | 4551626.89 | 502724 | N/A | 0 | 0 |  | 2085205.56 | 2085205.56 | 2969145.33
San Luis Obispo County | 2015 | 4044969.89 | 506657 | N/A | 0 | 0 |  | 0 | 0 | 4551626.89
San Luis Obispo County | 2014 | 10168083 | 507156 | N/A | 0 | 0 |  | 1630269.11 | 1630269.11 | 4044969.89
San Luis Obispo County | 2013 | 10704539 | 508992 | N/A | 0 | 0 |  | 1045448 | 1045448 | 10168083
San Luis Obispo County | 2012 | 11134474 | 507342 | N/A | 0 | 0 |  | 937277 | 937277 | 10704539
San Luis Obispo County | 2011 | 11442677 | 502749 | N/A | 0 | 0 |  | 810952 | 810952 | 11134474
San Luis Obispo County | 2010 | 10530269 | 912408 | N/A | 0 | 0 |  | 0 | 0 | 11442677
San Luis Obispo County | 2009 | 9619977 | 910292 | N/A | 0 | 0 |  | 0 | 0 | 10530269
San Luis Obispo County | 2008 | 8705109 | 909120 | N/A | 0 | 0 |  | 0 | 0 | 9619977
San Luis Obispo County | 2007 | 7798041 | 907068 | N/A | 0 | 0 |  | 0 | 0 | 8705109
San Luis Obispo County Total |  |  | 18188175 |  |  | 6949511.04 |  | 22366681.27 | 22033962.05
San Mateo County
Atherton | 2019 | 1376998 | 25336 | N/A | 0 | 0 |  | 0 | 0 | 1402334
Atherton | 2018 | 1351511 | 25487 | N/A | 0 | 0 |  | 0 | 0 | 1376998
Atherton | 2017 | 1325846 | 25665 | N/A | 0 | 0 |  | 0 | 0 | 1351511
Atherton | 2016 | 1300405 | 25441 | N/A | 0 | 0 |  | 0 | 0 | 1325846
Atherton | 2015 | 1274747 | 25658 | N/A | 0 | 0 |  | 0 | 0 | 1300405
Atherton | 2014 | 1248892 | 25855 | N/A | 0 | 0 |  | 0 | 0 | 1274747
Atherton | 2013 | 1221859 | 27033 | N/A | 0 | 0 |  | 0 | 0 | 1248892
Atherton | 2012 | 1194794 | 27065 | N/A | 0 | 0 |  | 0 | 0 | 1221859
Atherton | 2011 | 1167754 | 27040 | N/A | 0 | 0 |  | 0 | 0 | 1194794
Atherton | 2010 | 1104157 | 63597 | N/A | 0 | 0 |  | 0 | 0 | 1167754
Atherton | 2009 | 1040622 | 63535 | N/A | 0 | 0 |  | 0 | 0 | 1104157
Atherton | 2008 | 976528 | 63780 | N/A | 0 | 0 |  | 0 | 0 | 1040622
Atherton | 2007 | 912676 | 63852 | N/A | 0 | 0 |  | 0 | 0 | 976528
Belmont | 2019 | 5704507 | 104679 | N/A | 0 | 0 |  | 4435363.4777 | 4435363.4777 | 1373822.5223
Belmont | 2018 | 5599377 | 105130 | N/A | 0 | 0 |  | 0 | 0 | 5704507
Belmont | 2017 | 5493970 | 105407 | N/A | 0 | 0 |  | 0 | 0 | 5599377
Belmont | 2016 | 5389297 | 104673 | N/A | 0 | 0 |  | 0 | 0 | 5493970
Belmont | 2015 | 5283496 | 105801 | N/A | 0 | 0 |  | 0 | 0 | 5389297
Belmont | 2014 | 5177105 | 106391 | N/A | 0 | 0 |  | 0 | 0 | 5283496
Belmont | 2013 | 5072053 | 105052 | N/A | 0 | 0 |  | 0 | 0 | 5177105
Belmont | 2012 | 4966679 | 105374 | N/A | 0 | 0 |  | 0 | 0 | 5072053
Belmont | 2011 | 4861179 | 105500 | N/A | 0 | 0 |  | 0 | 0 | 4966679
Belmont | 2010 | 4635865 | 225314 | N/A | 0 | 0 |  | 0 | 0 | 4861179
Belmont | 2009 | 2574794 | 225445 | N/A | 0 | 1835626 | $1,835,626 (Foster City) | 0 | 0 | 4635865
Belmont | 2008 | 2347726 | 225837 | N/A | 0 | 0 |  | 0 | 0 | 2574794
Belmont | 2007 | 2121303 | 226423 | N/A | 0 | 0 |  | 0 | 0 | 2347726
Brisbane | 2019 | -16556 | 19434 | N/A | 0 | 0 |  | 0 | 0 | 2878
Brisbane | 2018 | -35894 | 19338 | N/A | 0 | 0 |  | 0 | 0 | -16556 | Within 5-year borrow
Brisbane | 2017 | -55289 | 19395 | N/A | 0 | 0 |  | 0 | 0 | -35894 | Within 5-year borrow
Brisbane | 2016 | -74550 | 19261 | N/A | 0 | 0 |  | 0 | 0 | -55289 | Within 5-year borrow
Brisbane | 2015 | -93862 | 19312 | N/A | 0 | 0 |  | 0 | 0 | -74550 | Within 5-year borrow
Brisbane | 2014 | 26871 | 19267 | N/A | 0 | 0 |  | 0 | 0 | -93862 | Within 5-year borrow
Brisbane | 2013 | 407719 | 19152 | N/A | 0 | 0 |  | 0 | 0 | 26871
Brisbane | 2012 | 388620 | 19099 | N/A | 0 | 0 |  | 0 | 0 | 407719
Brisbane | 2011 | 369546 | 19074 | N/A | 0 | 0 |  | 0 | 0 | 388620
Brisbane | 2010 | 332475 | 37071 | N/A | 0 | 0 |  | 0 | 0 | 369546
Brisbane | 2009 | 295441 | 37034 | N/A | 0 | 0 |  | 0 | 0 | 332475
Brisbane | 2008 | 258216 | 37005 | N/A | 0 | 0 |  | 0 | 0 | 295441
Brisbane | 2007 | 221213 | 37003 | N/A | 0 | 0 |  | 0 | 0 | 258216
Burlingame | 2019 | 5606875 | 138111 | N/A | 0 | 0 |  | 0 | 0 | 5744986
Burlingame | 2018 | 5467741 | 139134 | N/A | 0 | 0 |  | 0 | 0 | 5606875
Burlingame | 2017 | 5328052 | 139689 | N/A | 0 | 0 |  | 0 | 0 | 5467741
Burlingame | 2016 | 5189297 | 138755 | N/A | 0 | 0 |  | 0 | 0 | 5328052
Burlingame | 2015 | 5049397 | 139900 | N/A | 0 | 0 |  | 0 | 0 | 5189297
Burlingame | 2014 | 4908740 | 140657 | N/A | 0 | 0 |  | 0 | 0 | 5049397
Burlingame | 2013 | 4769353 | 139387 | N/A | 0 | 0 |  | 0 | 0 | 4908740
Burlingame | 2012 | 4629851 | 139502 | N/A | 0 | 0 |  | 0 | 0 | 4769353
Burlingame | 2011 | 4490352 | 139499 | N/A | 0 | 0 |  | 0 | 0 | 4629851
Burlingame | 2010 | 4196579 | 293773 | N/A | 0 | 0 |  | 0 | 0 | 4490352
Burlingame | 2009 | 3902520 | 294059 | N/A | 0 | 0 |  | 0 | 0 | 4196579
Burlingame | 2008 | 3606570 | 294325 | N/A | 0 | 0 |  | 0 | 0 | 3902520
Burlingame | 2007 | 3311798 | 294772 | N/A | 0 | 0 |  | 0 | 0 | 3606570
Colma | 2019 | 2012 | 3936 | N/A | 0 | 0 |  | 0 | 0 | 5948
Colma | 2018 | -2278 | 4290 | N/A | 0 | 0 |  | 0 | 0 | 2012
Colma | 2017 | -6547 | 4269 | N/A | 0 | 0 |  | 0 | 0 | -2278 | Within 5-year borrow
Colma | 2016 | -10837 | 4290 | N/A | 0 | 0 |  | 0 | 0 | -6547 | Within 5-year borrow
Colma | 2015 | -15183 | 4346 | N/A | 0 | 0 |  | 0 | 0 | -10837 | Within 5-year borrow
Colma | 2014 | -19574 | 4391 | N/A | 0 | 0 |  | 0 | 0 | -15183 | Within 5-year borrow
Colma | 2013 | -24152 | 4578 | N/A | 0 | 0 |  | 0 | 0 | -19574 | Within 5-year borrow
Colma | 2012 | -28615 | 4463 | N/A | 0 | 0 |  | 0 | 0 | -24152
Colma | 2011 | 191849 | 5093 | N/A | 0 | 0 |  | 225557 | 225557 | -28615 | Additional research required
Colma | 2010 | 180707 | 11142 | N/A | 0 | 0 |  | 0 | 0 | 191849
Colma | 2009 | 169547 | 11160 | N/A | 0 | 0 |  | 0 | 0 | 180707
Colma | 2008 | 158289 | 11202 | N/A | 0 | 0 |  | 0 | 0 | 169547
Colma | 2007 | 146918 | 11371 | N/A | 0 | 0 |  | 0 | 0 | 158289
Daly City | 2019 | 860469.16 | 266008 | N/A | 0 | 0 |  | 0 | 0 | 1126477.16
Daly City | 2018 | 594332.16 | 266137 | N/A | 0 | 0 |  | 0 | 0 | 860469.16
Daly City | 2017 | 328051.16 | 266281 | N/A | 0 | 0 |  | 0 | 0 | 594332.16
Daly City | 2016 | 6074858.94 | 264222 | N/A | 0 | 0 |  | 6011029.78 | 6011029.78 | 328051.16
Daly City | 2015 | 5807388.94 | 267470 | N/A | 0 | 0 |  | 0 | 0 | 6074858.94
Daly City | 2014 | 5537983.94 | 269405 | N/A | 0 | 0 |  | 0 | 0 | 5807388.94
Daly City | 2013 | 5296571 | 265780 | N/A | 0 | 0 |  | 24367.06 | 0 | 5537983.94
Daly City | 2012 | 5029925 | 266646 | N/A | 0 | 0 |  | 0 | 0 | 5296571
Daly City | 2011 | 5830537 | 266308 | N/A | 0 | 0 |  | 1066920 | 1066920 | 5029925
Daly City | 2010 | 5298524 | 532013 | N/A | 0 | 0 |  | 0 | 0 | 5830537
Daly City | 2009 | 4767244 | 531280 | N/A | 0 | 0 |  | 0 | 0 | 5298524
Daly City | 2008 | 4232032 | 532123 | N/A | 0 | 0 |  | 0 | 0 | 4767244
Daly City | 2007 | 3698386 | 533646 | N/A | 0 | 0 |  | 0 | 0 | 4232032
East Palo Alto | 2019 | 2670282 | 67454 | N/A | 0 | 0 |  | 1920415.41 | 1920415.41 | 817320.59
East Palo Alto | 2018 | 2603520 | 66762 | N/A | 0 | 0 |  | 0 | 0 | 2670282
East Palo Alto | 2017 | 2536699 | 66821 | N/A | 0 | 0 |  | 0 | 0 | 2603520
East Palo Alto | 2016 | 2470453 | 66246 | N/A | 0 | 0 |  | 0 | 0 | 2536699
East Palo Alto | 2015 | 2403437 | 67016 | N/A | 0 | 0 |  | 0 | 0 | 2470453
East Palo Alto | 2014 | 2336178 | 67259 | N/A | 0 | 0 |  | 0 | 0 | 2403437
East Palo Alto | 2013 | 2269351 | 66827 | N/A | 0 | 0 |  | 0 | 0 | 2336178
East Palo Alto | 2012 | 2203446 | 65905 | N/A | 0 | 0 |  | 0 | 0 | 2269351
East Palo Alto | 2011 | 2137388 | 66058 | N/A | 0 | 0 |  | 0 | 0 | 2203446
East Palo Alto | 2010 | 1975473 | 161915 | N/A | 0 | 0 |  | 0 | 0 | 2137388
East Palo Alto | 2009 | 1813620 | 161853 | N/A | 0 | 0 |  | 0 | 0 | 1975473
East Palo Alto | 2008 | 1650884 | 161969 | N/A | 0 | 0 |  | 0 | 0 | 1813620
East Palo Alto | 2007 | 1488619 | 162265 | N/A | 0 | 0 |  | 0 | 0 | 1650884
Foster City | 2019 | 558 | 55063 | N/A | 0 | 0 |  | 0 | 0 | 0
Foster City | 2018 | 0 | 54988 | N/A | 0 | 0 |  | 0 | 0 | 558
Foster City | 2017 | 0 | 54430 | N/A | 0 | 0 |  | 0 | 0 | 0
Foster City | 2016 | 0 | 437189 | N/A | 0 | 0 |  | 0 | 0 | 0
Foster City | 2015 | 0 | 0 | N/A | 0 | 0 |  | 0 | 0 | 0
Foster City | 2014 | 0 | 0 | N/A | 0 | 0 |  | 0 | 0 | 0
Foster City | 2013 | 0 | 0 | N/A | 0 | 0 |  | 0 | 0 | 0
Foster City | 2012 | 0 | 0 | N/A | 0 | 0 |  | 0 | 0 | 0
Foster City | 2011 | 0 | 0 | N/A | 0 | 0 |  | 0 | 0 | 0
Foster City | 2010 | 0 | 0 | N/A | 0 | 0 |  | 0 | 0 | 0
Foster City | 2009 | 1721711 | 113915 | N/A | 0 | 0 |  | 0 | 0 | 0
Foster City | 2008 | 1606761 | 114318 | N/A | 0 | 0 |  | 0 | 0 | 1721711
Foster City | 2007 | 1491884 | 114877 | N/A | 0 | 0 |  | 0 | 0 | 1606761
Half Moon Bay | 2019 | 1228550 | 34084 | N/A | 0 | 55621 | Foster City ($55,621) | 0 | 0 | 1318255
Half Moon Bay | 2018 | 1140129 | 33991 | N/A | 0 | 54430 | Foster City ($54,430) | 0 | 0 | 1228550
Half Moon Bay | 2017 | 651716 | 33983 | N/A | 0 | 454430 | $54,430 (Foster City), $400,000 (Sonora) | 0 | 0 | 1140129
Half Moon Bay | 2016 | 180867 | 33660 | N/A | 0 | 437189 | $437,189 (Foster City) | 0 | 0 | 651716
Half Moon Bay | 2015 | 147134 | 33733 | N/A | 0 | 0 |  | 0 | 0 | 180867
Half Moon Bay | 2014 | 112739 | 34395 | N/A | 0 | 0 |  | 0 | 0 | 147134
Half Moon Bay | 2013 | 78066 | 34673 | N/A | 0 | 0 |  | 0 | 0 | 112739
Half Moon Bay | 2012 | 43325 | 34741 | N/A | 0 | 0 |  | 0 | 0 | 78066
Half Moon Bay | 2011 | 852682 | 36380 | N/A | 0 | 0 |  | 845737 | 845737 | 43325
Half Moon Bay | 2010 | 790419 | 62263 | N/A | 0 | 0 |  | 0 | 0 | 852682
Half Moon Bay | 2009 | 728268 | 62151 | N/A | 0 | 0 |  | 0 | 0 | 790419
Half Moon Bay | 2008 | 665442 | 62404 | N/A | 0 | 0 |  | 0 | 0 | 728268
Half Moon Bay | 2007 | 603105 | 62337 | N/A | 0 | 0 |  | 0 | 0 | 665442
Hillsborough | 2019 | -889226.42 | 28109 | N/A | 0 | 0 |  | 0 | 0 | -861117.42 | Borrowed beyond 5 years (see AL 4553-E)
Hillsborough | 2018 | -918927.42 | 29701 | N/A | 0 | 0 |  | 0 | 0 | -889226.42 | Borrowed beyond 5 years (see AL 4553-E)
Hillsborough | 2017 | -948780.42 | 29853 | N/A | 0 | 0 |  | 0 | 0 | -918927.42 | Borrowed beyond 5 years (see AL 4553-E)
Hillsborough | 2016 | -978587.42 | 29807 | N/A | 0 | 0 |  | 0 | 0 | -948780.42 | Borrowed beyond 5 years (see AL 4553-E)
Hillsborough | 2015 | -1008717.42 | 30130 | N/A | 0 | 0 |  | 0 | 0 | -978587.42 | Borrowed beyond 5 years (see AL 4553-E)
Hillsborough | 2014 | -1039060.42 | 30343 | N/A | 0 | 0 |  | 0 | 0 | -1008717.42 | Borrowed beyond 5 years (see AL 4553-E)
Hillsborough | 2013 | -1069761.42 | 30701 | N/A | 0 | 0 |  | 0 | 0 | -1039060.42 | Borrowed beyond 5 years (see AL 4553-E)
Hillsborough | 2012 | 958226 | 30787 | N/A | 0 | 0 |  | 2058774.42 | 2058774.42 | -1069761.42 | Borrowed beyond 5 years (see AL 4553-E)
Hillsborough | 2011 | 927307 | 30919 | N/A | 0 | 0 |  | 0 | 0 | 958226
Hillsborough | 2010 | 861829 | 65478 | N/A | 0 | 0 |  | 0 | 0 | 927307
Hillsborough | 2009 | 796243 | 65586 | N/A | 0 | 0 |  | 0 | 0 | 861829
Hillsborough | 2008 | 730228 | 65654 | N/A | 0 | 0 |  | 0 | 0 | 796243
Hillsborough | 2007 | 664496 | 65732 | N/A | 0 | 0 |  | 0 | 0 | 730228
Menlo Park | 2019 | 5918820 | 135416 | N/A | 0 | 0 |  | 0 | 0 | 6054236
Menlo Park | 2018 | 5783460 | 135360 | N/A | 0 | 0 |  | 0 | 0 | 5918820
Menlo Park | 2017 | 5649402 | 134058 | N/A | 0 | 0 |  | 0 | 0 | 5783460
Menlo Park | 2016 | 5517152 | 132250 | N/A | 0 | 0 |  | 0 | 0 | 5649402
Menlo Park | 2015 | 5383528 | 133624 | N/A | 0 | 0 |  | 0 | 0 | 5517152
Menlo Park | 2014 | 5249116 | 134412 | N/A | 0 | 0 |  | 0 | 0 | 5383528
Menlo Park | 2013 | 5115027 | 134089 | N/A | 0 | 0 |  | 0 | 0 | 5249116
Menlo Park | 2012 | 4980353 | 134674 | N/A | 0 | 0 |  | 0 | 0 | 5115027
Menlo Park | 2011 | 4845593 | 134760 | N/A | 0 | 0 |  | 0 | 0 | 4980353
Menlo Park | 2010 | 4558581 | 287012 | N/A | 0 | 0 |  | 0 | 0 | 4845593
Menlo Park | 2009 | 4271880 | 286701 | N/A | 0 | 0 |  | 0 | 0 | 4558581
Menlo Park | 2008 | 3983787 | 286539 | N/A | 0 | 0 |  | 0 | 0 | 4271880
Menlo Park | 2007 | 3694308 | 289479 | N/A | 0 | 0 |  | 0 | 0 | 3983787
Millbrae | 2019 | 3260562 | 78345 | N/A | 0 | 0 |  | 0 | 0 | 3338907
Millbrae | 2018 | 3182301 | 78261 | N/A | 0 | 0 |  | 0 | 0 | 3260562
Millbrae | 2017 | 3103777 | 78524 | N/A | 0 | 0 |  | 0 | 0 | 3182301
Millbrae | 2016 | 3025818 | 77959 | N/A | 0 | 0 |  | 0 | 0 | 3103777
Millbrae | 2015 | 2947042 | 78776 | N/A | 0 | 0 |  | 0 | 0 | 3025818
Millbrae | 2014 | 2868091 | 78951 | N/A | 0 | 0 |  | 0 | 0 | 2947042
Millbrae | 2013 | 2789950 | 78141 | N/A | 0 | 0 |  | 0 | 0 | 2868091
Millbrae | 2012 | 2711575 | 78375 | N/A | 0 | 0 |  | 0 | 0 | 2789950
Millbrae | 2011 | 2633129 | 78446 | N/A | 0 | 0 |  | 0 | 0 | 2711575
Millbrae | 2010 | 2468305 | 164824 | N/A | 0 | 0 |  | 0 | 0 | 2633129
Millbrae | 2009 | 2303597 | 164708 | N/A | 0 | 0 |  | 0 | 0 | 2468305
Millbrae | 2008 | 2138077 | 164621 | N/A | 0 | 0 |  | 0 | 0 | 2303597
Millbrae | 2007 | 1973494 | 164583 | N/A | 0 | 0 |  | 0 | 0 | 2138077
Pacifica | 2019 | 4922541.87 | 137840 | N/A | 0 | 0 |  | 5555654.92 | 5555654.92 | -495273.05 | Within 5-year borrow
Pacifica | 2018 | 4784975.87 | 137566 | N/A | 0 | 0 |  | 0 | 0 | 4922541.87
Pacifica | 2017 | 4646782.87 | 138193 | N/A | 0 | 0 |  | 0 | 0 | 4784975.87
Pacifica | 2016 | 4509390.87 | 137392 | N/A | 0 | 0 |  | 0 | 0 | 4646782.87
Pacifica | 2015 | 4370475.87 | 138915 | N/A | 0 | 0 |  | 0 | 0 | 4509390.87
Pacifica | 2014 | 4229851.87 | 140624 | N/A | 0 | 0 |  | 0 | 0 | 4370475.87
Pacifica | 2013 | 4090981.87 | 138870 | N/A | 0 | 0 |  | 0 | 0 | 4229851.87
Pacifica | 2012 | 3951828.87 | 139153 | N/A | 0 | 0 |  | 0 | 0 | 4090981.87
Pacifica | 2011 | 3812446.87 | 139382 | N/A | 0 | 0 |  | 0 | 0 | 3951828.87
Pacifica | 2010 | 3523515.87 | 288931 | N/A | 0 | 0 |  | 0 | 0 | 3812446.87
Pacifica | 2009 | 3400132.74 | 288871 | N/A | 0 | 0 |  | 165487.87 | 165487.87 | 3523515.87
Pacifica | 2008 | 3109082.74 | 289428 | N/A | 0 | 0 |  | 0 | 0 | 3400132.74
Pacifica | 2007 | 3220341 | 289946 | N/A | 0 | 0 |  | 401204.26 | 401204.26 | 3109082.74
Portola Valley | 2019 | 498648 | 14970 | N/A | 0 | 0 |  | 0 | 0 | 513618
Portola Valley | 2018 | 483707 | 14941 | N/A | 0 | 0 |  | 0 | 0 | 498648
Portola Valley | 2017 | 468813 | 14894 | N/A | 0 | 0 |  | 0 | 0 | 483707
Portola Valley | 2016 | 454092 | 14721 | N/A | 0 | 0 |  | 0 | 0 | 468813
Portola Valley | 2015 | 439199 | 14893 | N/A | 0 | 0 |  | 0 | 0 | 454092
Portola Valley | 2014 | 424125 | 15074 | N/A | 0 | 0 |  | 0 | 0 | 439199
Portola Valley | 2013 | 408940 | 15185 | N/A | 0 | 0 |  | 0 | 0 | 424125
Portola Valley | 2012 | 393595 | 15345 | N/A | 0 | 0 |  | 0 | 0 | 408940
Portola Valley | 2011 | 378191 | 15404 | N/A | 0 | 0 |  | 0 | 0 | 393595
Portola Valley | 2010 | 346771 | 31420 | N/A | 0 | 0 |  | 0 | 0 | 378191
Portola Valley | 2009 | 315397 | 31374 | N/A | 0 | 0 |  | 0 | 0 | 346771
Portola Valley | 2008 | 283884 | 31336 | N/A | 0 | 0 |  | 0 | 0 | 315397
Portola Valley | 2007 | 252494 | 31390 | N/A | 0 | 0 |  | 0 | 0 | 283884
Redwood City | 2019 | 8349928 | 286904 | N/A | 0 | 0 |  | 0 | 0 | 8636832
Redwood City | 2018 | 8063997 | 285931 | N/A | 0 | 0 |  | 0 | 0 | 8349928
Redwood City | 2017 | 7777974 | 286023 | N/A | 0 | 0 |  | 0 | 0 | 8063997
Redwood City | 2016 | 7496884 | 281090 | N/A | 0 | 0 |  | 0 | 0 | 7777974
Redwood City | 2015 | 7214307 | 282577 | N/A | 0 | 0 |  | 0 | 0 | 7496884
Redwood City | 2014 | 6932337 | 281970 | N/A | 0 | 0 |  | 0 | 0 | 7214307
Redwood City | 2013 | 6654105 | 278232 | N/A | 0 | 0 |  | 0 | 0 | 6932337
Redwood City | 2012 | 6375028 | 279077 | N/A | 0 | 0 |  | 0 | 0 | 6654105
Redwood City | 2011 | 6096283 | 278745 | N/A | 0 | 0 |  | 0 | 0 | 6375028
Redwood City | 2010 | 5518061 | 578222 | N/A | 0 | 0 |  | 0 | 0 | 6096283
Redwood City | 2009 | 4940076 | 577985 | N/A | 0 | 0 |  | 0 | 0 | 5518061
Redwood City | 2008 | 4357823 | 579021 | N/A | 0 | 0 |  | 0 | 0 | 4940076
Redwood City | 2007 | 3777675 | 580148 | N/A | 0 | 0 |  | 0 | 0 | 4357823
San Bruno | 2019 | 5964303 | 149908 | N/A | 0 | 0 |  | 0 | 0 | 6114211
San Bruno | 2018 | 5814756 | 149547 | N/A | 0 | 0 |  | 0 | 0 | 5964303
San Bruno | 2017 | 5664794 | 149962 | N/A | 0 | 0 |  | 0 | 0 | 5814756
San Bruno | 2016 | 5515942 | 148852 | N/A | 0 | 0 |  | 0 | 0 | 5664794
San Bruno | 2015 | 5365530 | 150412 | N/A | 0 | 0 |  | 0 | 0 | 5515942
San Bruno | 2014 | 5214799 | 150731 | N/A | 0 | 0 |  | 0 | 0 | 5365530
San Bruno | 2013 | 5064966 | 149833 | N/A | 0 | 0 |  | 0 | 0 | 5214799
San Bruno | 2012 | 4914936 | 150030 | N/A | 0 | 0 |  | 0 | 0 | 5064966
San Bruno | 2011 | 4765226 | 149710 | N/A | 0 | 0 |  | 0 | 0 | 4914936
San Bruno | 2010 | 4443120 | 322106 | N/A | 0 | 0 |  | 0 | 0 | 4765226
San Bruno | 2009 | 4121324 | 321796 | N/A | 0 | 0 |  | 0 | 0 | 4443120
San Bruno | 2008 | 3797223 | 322372 | N/A | 0 | 0 |  | 0 | 0 | 4121324
San Bruno | 2007 | 3475235 | 321988 | N/A | 0 | 0 |  | 0 | 0 | 3797223
San Carlos | 2019 | -222134.03 | 135547 | N/A | 0 | 0 |  | 0 | 0 | -86587.03 | Within 5-year borrow
San Carlos | 2018 | -356340.03 | 134206 | N/A | 0 | 0 |  | 0 | 0 | -222134.03 | Within 5-year borrow
San Carlos | 2017 | -490929.03 | 134589 | N/A | 0 | 0 |  | 0 | 0 | -356340.03 | Within 5-year borrow
San Carlos | 2016 | 2447749.59 | 133771 | N/A | 0 | 0 |  | 3072449.62 | 3072449.62 | -490929.03 | Within 5-year borrow
San Carlos | 2015 | 2442516.59 | 135233 | N/A | 0 | 0 |  | 0 | 0 | 2447749.59
San Carlos | 2014 | 2296058.59 | 136458 | N/A | 0 | 140000 | $140,000 (Brisbane) | 0 | 0 | 2442516.59
San Carlos | 2013 | 1160927.59 | 135131 | N/A | 0 | 1000000 | $600,000 (Humboldt County), $400,000 (Brisbane) | 0 | 0 | 2296058.59
San Carlos | 2012 | 1025613.59 | 135314 | N/A | 0 | 0 |  | 0 | 0 | 1160927.59
San Carlos | 2011 | 890344.59 | 135269 | N/A | 0 | 0 |  | 0 | 0 | 1025613.59
San Carlos | 2010 | 605243.59 | 285101 | N/A | 0 | 0 |  | 0 | 0 | 890344.59
San Carlos | 2009 | 320560.59 | 284683 | N/A | 0 | 0 |  | 0 | 0 | 605243.59
San Carlos | 2008 | 2968832.65 | 285056 | N/A | 0 | 0 |  | 2934893.06 | 2934893.06 | 320560.59
San Carlos | 2007 | 2683760 | 285524 | N/A | 0 | 0 |  | 451.35 | 0 | 2968832.65
San Mateo | 2019 | 9410166.43 | 377739 | N/A | 0 | 0 |  | 26193.23 | 26193.23 | 9761712.2
San Mateo | 2018 | 12121692.49 | 377159 | N/A | 0 | 0 |  | 3088685.06 | 3088685.06 | 9410166.43
San Mateo | 2017 | 11744687.49 | 377005 | N/A | 0 | 0 |  | 0 | 0 | 12121692.49
San Mateo | 2016 | 11370203.49 | 374484 | N/A | 0 | 0 |  | 0 | 0 | 11744687.49
San Mateo | 2015 | 10992803.49 | 377400 | N/A | 0 | 0 |  | 0 | 0 | 11370203.49
San Mateo | 2014 | 10615507.49 | 377296 | N/A | 0 | 0 |  | 0 | 0 | 10992803.49
San Mateo | 2013 | 10243212.49 | 372295 | N/A | 0 | 0 |  | 0 | 0 | 10615507.49
San Mateo | 2012 | 9870261.49 | 372951 | N/A | 0 | 0 |  | 0 | 0 | 10243212.49
San Mateo | 2011 | 9966308.49 | 373953 | N/A | 0 | 0 |  | 470000 | 470000 | 9870261.49
San Mateo | 2010 | 9181851.49 | 784457 | N/A | 0 | 0 |  | 0 | 0 | 9966308.49
San Mateo | 2009 | 8398053.49 | 783798 | N/A | 0 | 0 |  | 0 | 0 | 9181851.49
San Mateo | 2008 | 7609048.49 | 784672 | N/A | 0 | 0 |  | 0 | 0 | 8398053.49
San Mateo | 2007 | 6822557.49 | 786491 | N/A | 0 | 0 |  | 0 | 0 | 7609048.49
San Mateo County | 2019 | 7769339.93 | 247165 | N/A | 0 | 0 |  | 2044349.4223 | 2044349.4223 | 5972155.5077
San Mateo County | 2018 | 7523973.93 | 245366 | N/A | 0 | 0 |  | 0 | 0 | 7769339.93
San Mateo County | 2017 | 7277990.93 | 245983 | N/A | 0 | 0 |  | 0 | 0 | 7523973.93
San Mateo County | 2016 | 7033998.93 | 243992 | N/A | 0 | 0 |  | 0 | 0 | 7277990.93
San Mateo County | 2015 | 7621094 | 246564 | N/A | 0 | 0 |  | 833659.07 | 833659.07 | 7033998.93
San Mateo County | 2014 | 7373593 | 247501 | N/A | 0 | 0 |  | 0 | 0 | 7621094
San Mateo County | 2013 | 7126378 | 247215 | N/A | 0 | 0 |  | 0 | 0 | 7373593
San Mateo County | 2012 | 6878287 | 248091 | N/A | 0 | 0 |  | 0 | 0 | 7126378
San Mateo County | 2011 | 7578732 | 245692 | N/A | 0 | 0 |  | 946137 | 946137 | 6878287
San Mateo County | 2010 | 6966334 | 612398 | N/A | 0 | 0 |  | 0 | 0 | 7578732
San Mateo County | 2009 | 6354758 | 611576 | N/A | 0 | 0 |  | 0 | 0 | 6966334
San Mateo County | 2008 | 5739817 | 612099 | N/A | 0 | 0 |  | 0 | 0 | 6354758
San Mateo County | 2007 | 5129679 | 610138 | N/A | 0 | 0 |  | 0 | 0 | 5739817
South San Francisco | 2019 | 6780977 | 203445 | N/A | 0 | 0 |  | 0 | 0 | 6984422
South San Francisco | 2018 | 6578321 | 202656 | N/A | 0 | 0 |  | 0 | 0 | 6780977
South San Francisco | 2017 | 6375132 | 203189 | N/A | 0 | 0 |  | 0 | 0 | 6578321
South San Francisco | 2016 | 6173446 | 201686 | N/A | 0 | 0 |  | 0 | 0 | 6375132
South San Francisco | 2015 | 5969710 | 203736 | N/A | 0 | 0 |  | 0 | 0 | 6173446
South San Francisco | 2014 | 5764881 | 204829 | N/A | 0 | 0 |  | 0 | 0 | 5969710
South San Francisco | 2013 | 5562117 | 202764 | N/A | 0 | 0 |  | 0 | 0 | 5764881
South San Francisco | 2012 | 5359154 | 202963 | N/A | 0 | 0 |  | 0 | 0 | 5562117
South San Francisco | 2011 | 5155790 | 203364 | N/A | 0 | 0 |  | 0 | 0 | 5359154
South San Francisco | 2010 | 4750966 | 404824 | N/A | 0 | 0 |  | 0 | 0 | 5155790
South San Francisco | 2009 | 4346098 | 404868 | N/A | 0 | 0 |  | 0 | 0 | 4750966
South San Francisco | 2008 | 3938862 | 404880 | N/A | 0 | 0 |  | 0 | 0 | 4346098
South San Francisco | 2007 | 3533661 | 405201 | N/A | 0 | 0 |  | 0 | 0 | 3938862
Woodside | 2019 | 897128 | 22155 | N/A | 0 | 0 |  | 0 | 0 | 919283
Woodside | 2018 | 875155 | 21973 | N/A | 0 | 0 |  | 0 | 0 | 897128
Woodside | 2017 | 853067 | 22088 | N/A | 0 | 0 |  | 0 | 0 | 875155
Woodside | 2016 | 831163 | 21904 | N/A | 0 | 0 |  | 0 | 0 | 853067
Woodside | 2015 | 809014 | 22149 | N/A | 0 | 0 |  | 0 | 0 | 831163
Woodside | 2014 | 786688 | 22326 | N/A | 0 | 0 |  | 0 | 0 | 809014
Woodside | 2013 | 764144 | 22544 | N/A | 0 | 0 |  | 0 | 0 | 786688
Woodside | 2012 | 741474 | 22670 | N/A | 0 | 0 |  | 0 | 0 | 764144
Woodside | 2011 | 718765 | 22709 | N/A | 0 | 0 |  | 0 | 0 | 741474
Woodside | 2010 | 670859 | 47906 | N/A | 0 | 0 |  | 0 | 0 | 718765
Woodside | 2009 | 623009 | 47850 | N/A | 0 | 0 |  | 0 | 0 | 670859
Woodside | 2008 | 574926 | 47821 | N/A | 0 | 0 |  | 0 | 0 | 623009
Woodside | 2007 | 526995 | 47931 | N/A | 0 | 0 |  | 0 | 0 | 574926
San Mateo County Total |  |  | 44251864 |  |  | 3977296 |  | 36127329.01 | 36102510.6
Santa Barbara County
Buellton | 2019 | 168676 | 11342 | N/A | 0 | 0 |  | 0 | 0 | 180018
Buellton | 2018 | 157243 | 11433 | N/A | 0 | 0 |  | 0 | 0 | 168676
Buellton | 2017 | 146200 | 11043 | N/A | 0 | 0 |  | 0 | 0 | 157243
Buellton | 2016 | 135270 | 10930 | N/A | 0 | 0 |  | 0 | 0 | 146200
Buellton | 2015 | 124150 | 11120 | N/A | 0 | 0 |  | 0 | 0 | 135270
Buellton | 2014 | 112965 | 11185 | N/A | 0 | 0 |  | 0 | 0 | 124150
Buellton | 2013 | 101752 | 11213 | N/A | 0 | 0 |  | 0 | 0 | 112965
Buellton | 2012 | 90536 | 11216 | N/A | 0 | 0 |  | 0 | 0 | 101752
Buellton | 2011 | 79313 | 11223 | N/A | 0 | 0 |  | 0 | 0 | 90536
Buellton | 2010 | 69988 | 9325 | N/A | 0 | 0 |  | 0 | 0 | 79313
Buellton | 2009 | 60792 | 9196 | N/A | 0 | 0 |  | 0 | 0 | 69988
Buellton | 2008 | 51499 | 9166 | N/A | 0 | 0 |  | 0 | 0 | 60792
Buellton | 2007 | 42193 | 9306 | N/A | 0 | 0 |  | 0 | 0 | 51499
Guadalupe | 2019 | 390975 | 16270 | N/A | 0 | 0 |  | 0 | 0 | 407245
Guadalupe | 2018 | 374915 | 16060 | N/A | 0 | 0 |  | 0 | 0 | 390975
Guadalupe | 2017 | 359022 | 15893 | N/A | 0 | 0 |  | 0 | 0 | 374915
Guadalupe | 2016 | 343228 | 15794 | N/A | 0 | 0 |  | 0 | 0 | 359022
Guadalupe | 2015 | 327301 | 15927 | N/A | 0 | 0 |  | 0 | 0 | 343228
Guadalupe | 2014 | 311303 | 15998 | N/A | 0 | 0 |  | 0 | 0 | 327301
Guadalupe | 2013 | 295130 | 16173 | N/A | 0 | 0 |  | 0 | 0 | 311303
Guadalupe | 2012 | 279237 | 15893 | N/A | 0 | 0 |  | 0 | 0 | 295130
Guadalupe | 2011 | 263316 | 15921 | N/A | 0 | 0 |  | 0 | 0 | 279237
Guadalupe | 2010 | 232984 | 30332 | N/A | 0 | 0 |  | 0 | 0 | 263316
Guadalupe | 2009 | 202650 | 30334 | N/A | 0 | 0 |  | 0 | 0 | 232984
Guadalupe | 2008 | 172074 | 30392 | N/A | 0 | 0 |  | 0 | 0 | 202650
Guadalupe | 2007 | 141690 | 30384 | N/A | 0 | 0 |  | 0 | 0 | 172074
Santa Barbara County | 2019 | 5280880 | 222990 | N/A | 0 | 0 |  | 0 | 0 | 5503870
Santa Barbara County | 2018 | 5059426 | 221454 | N/A | 0 | 0 |  | 0 | 0 | 5280880
Santa Barbara County | 2017 | 5387693 | 221733 | N/A | 0 | 0 |  | 0 | 0 | 5059426
Santa Barbara County | 2016 | 5167958 | 219735 | N/A | 0 | 0 |  | 0 | 0 | 5387693
Santa Barbara County | 2015 | 4946584 | 221374 | N/A | 0 | 0 |  | 0 | 0 | 5167958
Santa Barbara County | 2014 | 4724580 | 222004 | N/A | 0 | 0 |  | 0 | 0 | 4946584
Santa Barbara County | 2013 | 5838545 | 223098 | N/A | 0 | 0 |  | 1337063 | 1337063 | 4724580
Santa Barbara County | 2012 | 5615245 | 223300 | N/A | 0 | 0 |  | 0 | 0 | 5838545
Santa Barbara County | 2011 | 5394346 | 220899 | N/A | 0 | 0 |  | 0 | 0 | 5615245
Santa Barbara County | 2010 | 4955050 | 439296 | N/A | 0 | 0 |  | 0 | 0 | 5394346
Santa Barbara County | 2009 | 4516590 | 438460 | N/A | 0 | 0 |  | 0 | 0 | 4955050
Santa Barbara County | 2008 | 4074271 | 439761 | N/A | 0 | 0 |  | 0 | 0 | 4516590
Santa Barbara County | 2007 | 3634288 | 439983 | N/A | 0 | 0 |  | 0 | 0 | 4074271
Santa Maria | 2019 | 6528107 | 212809 | N/A | 0 | 0 |  | 0 | 0 | 6740916
Santa Maria | 2018 | 6317406 | 210701 | N/A | 0 | 0 |  | 0 | 0 | 6528107
Santa Maria | 2017 | 6106526 | 210880 | N/A | 0 | 0 |  | 0 | 0 | 6317406
Santa Maria | 2016 | 5898931 | 207595 | N/A | 0 | 0 |  | 0 | 0 | 6106526
Santa Maria | 2015 | 5690653 | 208278 | N/A | 0 | 0 |  | 0 | 0 | 5898931
Santa Maria | 2014 | 5481280 | 209373 | N/A | 0 | 0 |  | 0 | 0 | 5690653
Santa Maria | 2013 | 5273052 | 208228 | N/A | 0 | 0 |  | 0 | 0 | 5481280
Santa Maria | 2012 | 5064467 | 208585 | N/A | 0 | 0 |  | 0 | 0 | 5273052
Santa Maria | 2011 | 4853473 | 210994 | N/A | 0 | 0 |  | 0 | 0 | 5064467
Santa Maria | 2010 | 4471197 | 382276 | N/A | 0 | 0 |  | 0 | 0 | 4853473
Santa Maria | 2009 | 4089209 | 381988 | N/A | 0 | 0 |  | 0 | 0 | 4471197
Santa Maria | 2008 | 3705770 | 381012 | N/A | 0 | 0 |  | 0 | 0 | 4089209
Santa Maria | 2007 | 3325018 | 380752 | N/A | 0 | 0 |  | 0 | 0 | 3705770
Solvang | 2019 | 1135217 | 20323 | N/A | 0 | 0 |  | 0 | 0 | 1155540
Solvang | 2018 | 1114927 | 20290 | N/A | 0 | 0 |  | 0 | 0 | 1135217
Solvang | 2017 | 544584 | 20343 | N/A | 0 | 550000 | $550,000 (Santa Barbara County) | 0 | 0 | 1114927
Solvang | 2016 | 524666 | 19918 | N/A | 0 | 0 |  | 0 | 0 | 544584
Solvang | 2015 | 504641 | 20025 | N/A | 0 | 0 |  | 0 | 0 | 524666
Solvang | 2014 | 484633 | 20008 | N/A | 0 | 0 |  | 0 | 0 | 504641
Solvang | 2013 | 464737 | 19896 | N/A | 0 | 0 |  | 0 | 0 | 484633
Solvang | 2012 | 444791 | 19946 | N/A | 0 | 0 |  | 0 | 0 | 464737
Solvang | 2011 | 424980 | 19811 | N/A | 0 | 0 |  | 0 | 0 | 444791
Solvang | 2010 | 386276 | 38704 | N/A | 0 | 0 |  | 0 | 0 | 424980
Solvang | 2009 | 347586 | 38690 | N/A | 0 | 0 |  | 0 | 0 | 386276
Solvang | 2008 | 308683 | 38674 | N/A | 0 | 0 |  | 0 | 0 | 347586
Solvang | 2007 | 270019 | 38664 | N/A | 0 | 0 |  | 0 | 0 | 308683
Santa Barbara County Total |  |  | 7905919 |  |  | 550000 |  | 1337063 | 1337063
Santa Clara County
Campbell | 2019 | -3073722.09 | 162665 | N/A | 0 | 0 |  | 0 | 0 | -2911057.09 | Borrowed beyond 5 years (see AL 4553-E)
Campbell | 2018 | -3235602.09 | 161880 | N/A | 0 | 0 |  | 0 | 0 | -3073722.09 | Borrowed beyond 5 years (see AL 4553-E)
Campbell | 2017 | -3397677.09 | 162075 | N/A | 0 | 0 |  | 0 | 0 | -3235602.09 | Borrowed beyond 5 years (see AL 4553-E)
Campbell | 2016 | -3558670.09 | 160993 | N/A | 0 | 0 |  | 0 | 0 | -3397677.09 | Borrowed beyond 5 years (see AL 4553-E)
Campbell | 2015 | 2709738 | 161322 | N/A | 0 | 0 |  | 6429730.09 | 6429730.09 | -3558670.09 | Borrowed beyond 5 years (see AL 4553-E)
Campbell | 2014 | 2547790 | 161948 | N/A | 0 | 0 |  | 0 | 0 | 2709738
Campbell | 2013 | 2389247 | 158543 | N/A | 0 | 0 |  | 0 | 0 | 2547790
Campbell | 2012 | 2231785 | 157462 | N/A | 0 | 0 |  | 0 | 0 | 2389247
Campbell | 2011 | 2075682 | 156103 | N/A | 0 | 0 |  | 0 | 0 | 2231785
Campbell | 2010 | 1772639 | 303043 | N/A | 0 | 0 |  | 0 | 0 | 2075682
Campbell | 2009 | 1469707 | 302932 | N/A | 0 | 0 |  | 0 | 0 | 1772639
Campbell | 2008 | 1164753 | 303144 | N/A | 0 | 0 |  | 0 | 0 | 1469707
Campbell | 2007 | 863511 | 301242 | N/A | 0 | 0 |  | 0 | 0 | 1164753
Cupertino | 2019 | 4528156 | 169001 | N/A | 0 | 0 |  | 0 | 0 | 4697157
Cupertino | 2018 | 4359584 | 168572 | N/A | 0 | 0 |  | 0 | 0 | 4528156
Cupertino | 2017 | 4190880 | 168704 | N/A | 0 | 0 |  | 0 | 0 | 4359584
Cupertino | 2016 | 4023415 | 167465 | N/A | 0 | 0 |  | 0 | 0 | 4190880
Cupertino | 2015 | 3854068 | 169347 | N/A | 0 | 0 |  | 0 | 0 | 4023415
Cupertino | 2014 | 3684860 | 169208 | N/A | 0 | 0 |  | 0 | 0 | 3854068
Cupertino | 2013 | 4496315 | 171809 | N/A | 0 | 0 |  | 983264 | 983264 | 3684860
Cupertino | 2012 | 4325856 | 170459 | N/A | 0 | 0 |  | 0 | 0 | 4496315
Cupertino | 2011 | 4155589 | 170267 | N/A | 0 | 0 |  | 0 | 0 | 4325856
Cupertino | 2010 | 3858017 | 297572 | N/A | 0 | 0 |  | 0 | 0 | 4155589
Cupertino | 2009 | 3560686 | 297331 | N/A | 0 | 0 |  | 0 | 0 | 3858017
Cupertino | 2008 | 3261350 | 297370 | N/A | 0 | 0 |  | 0 | 0 | 3560686
Cupertino | 2007 | 2964192 | 297158 | N/A | 0 | 0 |  | 0 | 0 | 3261350
Gilroy | 2019 | 3050206 | 109138 | N/A | 0 | 0 |  | 0 | 0 | 3159344
Gilroy | 2018 | 2942600 | 107606 | N/A | 0 | 0 |  | 0 | 0 | 3050206
Gilroy | 2017 | 2835574 | 107026 | N/A | 0 | 0 |  | 0 | 0 | 2942600
Gilroy | 2016 | 2730223 | 105351 | N/A | 0 | 0 |  | 0 | 0 | 2835574
Gilroy | 2015 | 2625117 | 105106 | N/A | 0 | 0 |  | 0 | 0 | 2730223
Gilroy | 2014 | 2520124 | 104993 | N/A | 0 | 0 |  | 0 | 0 | 2625117
Gilroy | 2013 | 2415161 | 104963 | N/A | 0 | 0 |  | 0 | 0 | 2520124
Gilroy | 2012 | 2309063 | 106098 | N/A | 0 | 0 |  | 0 | 0 | 2415161
Gilroy | 2011 | 2203324 | 105739 | N/A | 0 | 0 |  | 0 | 0 | 2309063
Gilroy | 2010 | 2019482 | 183842 | N/A | 0 | 0 |  | 0 | 0 | 2203324
Gilroy | 2009 | 1835944 | 183538 | N/A | 0 | 0 |  | 0 | 0 | 2019482
Gilroy | 2008 | 1651296 | 183434 | N/A | 0 | 0 |  | 0 | 0 | 1835944
Gilroy | 2007 | 1467941 | 183355 | N/A | 0 | 0 |  | 0 | 0 | 1651296
Los Altos | 2019 | 559805.63 | 119347 | N/A | 0 | 0 |  | 0 | 0 | 679152.63
Los Altos | 2018 | 440881.63 | 118924 | N/A | 0 | 0 |  | 0 | 0 | 559805.63
Los Altos | 2017 | 1952342 | 119508 | N/A | 0 | 0 |  | 1630968.37 | 1630968.37 | 440881.63
Los Altos | 2016 | 1833837 | 118505 | N/A | 0 | 0 |  | 0 | 0 | 1952342
Los Altos | 2015 | 1715133 | 118704 | N/A | 0 | 0 |  | 0 | 0 | 1833837
Los Altos | 2014 | 1596219 | 118914 | N/A | 0 | 0 |  | 0 | 0 | 1715133
Los Altos | 2013 | 3722086 | 124297 | N/A | 0 | 0 |  | 2250164 | 2250164 | 1596219
Los Altos | 2012 | 3598312 | 123774 | N/A | 0 | 0 |  | 0 | 0 | 3722086
Los Altos | 2011 | 3475426 | 122886 | N/A | 0 | 0 |  | 0 | 0 | 3598312
Los Altos | 2010 | 3222267 | 253159 | N/A | 0 | 0 |  | 0 | 0 | 3475426
Los Altos | 2009 | 2969867 | 252400 | N/A | 0 | 0 |  | 0 | 0 | 3222267
Los Altos | 2008 | 2716562 | 251908 | N/A | 0 | 0 |  | 0 | 0 | 2969867
Los Altos | 2007 | 2465672 | 250890 | N/A | 0 | 0 |  | 0 | 0 | 2716562
Los Altos Hills | 2019 | 222258.79 | 27692 | N/A | 0 | 0 |  | 0 | 0 | 249950.79
Los Altos Hills | 2018 | 194893.79 | 27365 | N/A | 0 | 0 |  | 0 | 0 | 222258.79
Los Altos Hills | 2017 | 167466.79 | 27427 | N/A | 0 | 0 |  | 0 | 0 | 194893.79
Los Altos Hills | 2016 | 140151.79 | 27315 | N/A | 0 | 0 |  | 0 | 0 | 167466.79
Los Altos Hills | 2015 | 112678.79 | 27473 | N/A | 0 | 0 |  | 0 | 0 | 140151.79
Los Altos Hills | 2014 | 85036.79 | 27642 | N/A | 0 | 0 |  | 0 | 0 | 112678.79
Los Altos Hills | 2013 | 56524.79 | 28512 | N/A | 0 | 0 |  | 0 | 0 | 85036.79
Los Altos Hills | 2012 | 28146.79 | 28378 | N/A | 0 | 0 |  | 0 | 0 | 56524.79
Los Altos Hills | 2011 | -587.21 | 28734 | N/A | 0 | 0 |  | 0 | 0 | 28146.79
Los Altos Hills | 2010 | -57993.21 | 57406 | N/A | 0 | 0 |  | 0 | 0 | -587.21 | Within 5-year borrow
Los Altos Hills | 2009 | 700641 | 57266 | N/A | 0 | 0 |  | 815900.21 | 815900.21 | -57993.21 | Within 5-year borrow
Los Altos Hills | 2008 | 643761 | 56560 | N/A | 0 | 0 |  | 0 | 0 | 700641
Los Altos Hills | 2007 | 587190 | 56571 | N/A | 0 | 0 |  | 0 | 0 | 643761
Los Gatos | 2019 | 3740630 | 121647 | N/A | 0 | 0 |  | 0 | 0 | 3862277
Los Gatos | 2018 | 3619403 | 121227 | N/A | 0 | 0 |  | 0 | 0 | 3740630
Los Gatos | 2017 | 3498024 | 121379 | N/A | 0 | 0 |  | 0 | 0 | 3619403
Los Gatos | 2016 | 3377420 | 120604 | N/A | 0 | 0 |  | 0 | 0 | 3498024
Los Gatos | 2015 | 3255488 | 121932 | N/A | 0 | 0 |  | 0 | 0 | 3377420
Los Gatos | 2014 | 3132998 | 122490 | N/A | 0 | 0 |  | 0 | 0 | 3255488
Los Gatos | 2013 | 3009317 | 123681 | N/A | 0 | 0 |  | 0 | 0 | 3132998
Los Gatos | 2012 | 2885781 | 123536 | N/A | 0 | 0 |  | 0 | 0 | 3009317
Los Gatos | 2011 | 2761902 | 123879 | N/A | 0 | 0 |  | 0 | 0 | 2885781
Los Gatos | 2010 | 2510153 | 251749 | N/A | 0 | 0 |  | 0 | 0 | 2761902
Los Gatos | 2009 | 2258410 | 251743 | N/A | 0 | 0 |  | 0 | 0 | 2510153
Los Gatos | 2008 | 2005299 | 251679 | N/A | 0 | 0 |  | 0 | 0 | 2258410
Los Gatos | 2007 | 1754523 | 250776 | N/A | 0 | 0 |  | 0 | 0 | 2005299
Milpitas | 2019 | 4324416 | 145663 | N/A | 0 | 0 |  | 0 | 0 | 4470079
Milpitas | 2018 | 4183207 | 141209 | N/A | 0 | 0 |  | 0 | 0 | 4324416
Milpitas | 2017 | 4041750 | 141457 | N/A | 0 | 0 |  | 0 | 0 | 4183207
Milpitas | 2016 | 3902433 | 139317 | N/A | 0 | 0 |  | 0 | 0 | 4041750
Milpitas | 2015 | 3763679 | 138754 | N/A | 0 | 0 |  | 0 | 0 | 3902433
Milpitas | 2014 | 3627650 | 136029 | N/A | 0 | 0 |  | 0 | 0 | 3763679
Milpitas | 2013 | 3494446 | 133204 | N/A | 0 | 0 |  | 0 | 0 | 3627650
Milpitas | 2012 | 3362278 | 132168 | N/A | 0 | 0 |  | 0 | 0 | 3494446
Milpitas | 2011 | 3230195 | 132083 | N/A | 0 | 0 |  | 0 | 0 | 3362278
Milpitas | 2010 | 2987955 | 242240 | N/A | 0 | 0 |  | 0 | 0 | 3230195
Milpitas | 2009 | 2746357 | 241598 | N/A | 0 | 0 |  | 0 | 0 | 2987955
Milpitas | 2008 | 2504461 | 240398 | N/A | 0 | 0 |  | 0 | 0 | 2746357
Milpitas | 2007 | 2264835 | 239626 | N/A | 0 | 0 |  | 0 | 0 | 2504461
Monte Sereno | 2019 | 498119 | 11630 | N/A | 0 | 0 |  | 0 | 0 | 509749
Monte Sereno | 2018 | 486424 | 11695 | N/A | 0 | 0 |  | 0 | 0 | 498119
Monte Sereno | 2017 | 474799 | 11625 | N/A | 0 | 0 |  | 0 | 0 | 486424
Monte Sereno | 2016 | 463203 | 11596 | N/A | 0 | 0 |  | 0 | 0 | 474799
Monte Sereno | 2015 | 451511 | 11692 | N/A | 0 | 0 |  | 0 | 0 | 463203
Monte Sereno | 2014 | 439666 | 11845 | N/A | 0 | 0 |  | 0 | 0 | 451511
Monte Sereno | 2013 | 427157 | 12509 | N/A | 0 | 0 |  | 0 | 0 | 439666
Monte Sereno | 2012 | 414715 | 12442 | N/A | 0 | 0 |  | 0 | 0 | 427157
Monte Sereno | 2011 | 402219 | 12496 | N/A | 0 | 0 |  | 0 | 0 | 414715
Monte Sereno | 2010 | 375310 | 26909 | N/A | 0 | 0 |  | 0 | 0 | 402219
Monte Sereno | 2009 | 348467 | 26843 | N/A | 0 | 0 |  | 0 | 0 | 375310
Monte Sereno | 2008 | 321550 | 26775 | N/A | 0 | 0 |  | 0 | 0 | 348467
Monte Sereno | 2007 | 294779 | 26771 | N/A | 0 | 0 |  | 0 | 0 | 321550
Morgan Hill | 2019 | 167145.2 | 80307 | N/A | 0 | 0 |  | 0 | 0 | 247452.2
Morgan Hill | 2018 | 88128.2 | 79017 | N/A | 0 | 0 |  | 0 | 0 | 167145.2
Morgan Hill | 2017 | 2382254 | 78333 | N/A | 0 | 0 |  | 2372458.8 | 2372458.8 | 88128.2
Morgan Hill | 2016 | 2304416 | 77838 | N/A | 0 | 0 |  | 0 | 0 | 2382254
Morgan Hill | 2015 | 2226737 | 77679 | N/A | 0 | 0 |  | 0 | 0 | 2304416
Morgan Hill | 2014 | 2149951 | 76786 | N/A | 0 | 0 |  | 0 | 0 | 2226737
Morgan Hill | 2013 | 2073606 | 76345 | N/A | 0 | 0 |  | 0 | 0 | 2149951
Morgan Hill | 2012 | 1998098 | 75508 | N/A | 0 | 0 |  | 0 | 0 | 2073606
Morgan Hill | 2011 | 1922973 | 75125 | N/A | 0 | 0 |  | 0 | 0 | 1998098
Morgan Hill | 2010 | 1794726 | 128247 | N/A | 0 | 0 |  | 0 | 0 | 1922973
Morgan Hill | 2009 | 1666655 | 128071 | N/A | 0 | 0 |  | 0 | 0 | 1794726
Morgan Hill | 2008 | 1538159 | 127637 | N/A | 0 | 0 |  | 0 | 0 | 1666655
Morgan Hill | 2007 | 1411270 | 126889 | N/A | 0 | 0 |  | 0 | 0 | 1538159
Mountain View | 2019 | 3881397.5 | 282535 | N/A | 0 | 0 |  | 0 | 0 | 4163932.5
Mountain View | 2018 | 3600525.5 | 280872 | N/A | 0 | 0 |  | 0 | 0 | 3881397.5
Mountain View | 2017 | 3319374.5 | 281151 | N/A | 0 | 0 |  | 0 | 0 | 3600525.5
Mountain View | 2016 | 3040878.5 | 278496 | N/A | 0 | 0 |  | 0 | 0 | 3319374.5
Mountain View | 2015 | 5746837 | 280758 | N/A | 0 | 0 |  | 2986716.5 | 2986716.5 | 3040878.5
Mountain View | 2014 | 5463812 | 283025 | N/A | 0 | 0 |  | 0 | 0 | 5746837
Mountain View | 2013 | 5182503 | 281309 | N/A | 0 | 0 |  | 0 | 0 | 5463812
Mountain View | 2012 | 4899122 | 283381 | N/A | 0 | 0 |  | 0 | 0 | 5182503
Mountain View | 2011 | 4615553 | 283569 | N/A | 0 | 0 |  | 0 | 0 | 4899122
Mountain View | 2010 | 4048855 | 566698 | N/A | 0 | 0 |  | 0 | 0 | 4615553
Mountain View | 2009 | 3482550 | 566305 | N/A | 0 | 0 |  | 0 | 0 | 4048855
Mountain View | 2008 | 2911681 | 567579 | N/A | 0 | 0 |  | 0 | 0 | 3482550
Mountain View | 2007 | 2343638 | 568043 | N/A | 0 | 0 |  | 0 | 0 | 2911681
San Jose | 2019 | 31636192.57 | 2290519 | N/A | 0 | 0 |  | 0 | 0 | 33926711.57
San Jose | 2018 | 29349840.57 | 2286352 | N/A | 0 | 0 |  | 0 | 0 | 31636192.57
San Jose | 2017 | 27120471.06 | 2287161 | N/A | 0 | 0 |  | 57791.49 | 57791.49 | 29349840.57
San Jose | 2016 | 34746386.05 | 2263875 | N/A | 0 | 0 |  | 9889789.99 | 9889789.99 | 27120471.06
San Jose | 2015 | 45304662.37 | 2275014 | N/A | 0 | 0 |  | 12833290.32 | 12833290.32 | 34746386.05
San Jose | 2014 | 47098968.57 | 2276539 | N/A | 0 | 0 |  | 4070845.2 | 4070845.2 | 45304662.37
San Jose | 2013 | 51043099.57 | 2255869 | N/A | 0 | 0 |  | 6200000 | 6200000 | 47098968.57
San Jose | 2012 | 53783062.13 | 2252630 | N/A | 0 | 0 |  | 4992592.56 | 4992592.56 | 51043099.57
San Jose | 2011 | 50818366.53 | 2237828 | N/A | 0 | 0 |  | -726867.6 | -726867.6 | 53783062.13
San Jose | 2010 | 46544322.53 | 4274044 | N/A | 0 | 0 |  | 0 | 0 | 50818366.53
San Jose | 2009 | 42535235.11 | 4249962 | N/A | 0 | 0 |  | 240874.58 | 240874.58 | 46544322.53
San Jose | 2008 | 38908050.83 | 4249033 | N/A | 0 | 0 |  | 647311.72 | 647311.72 | 42535235.11
San Jose | 2007 | 36831850.4 | 4250301 | N/A | 0 | 0 |  | 2174100.57 | 2174100.57 | 38908050.83
Santa Clara County | 2019 | 16675569.83 | 264375 | N/A | 0 | 0 |  | 0 | 0 | 16939944.83
Santa Clara County | 2018 | 16412512.83 | 263057 | N/A | 0 | 0 |  | 0 | 0 | 16675569.83
Santa Clara County | 2017 | 16159499.68 | 263786 | N/A | 0 | 0 |  | 10772.85 | 10772.85 | 16412512.83
Santa Clara County | 2016 | 16772955 | 262007 | N/A | 0 | 0 |  | 875462.32 | 875462.32 | 16159499.68
Santa Clara County | 2015 | 16508273 | 264682 | N/A | 0 | 0 |  | 0 | 0 | 16772955
Santa Clara County | 2014 | 16241876 | 266397 | N/A | 0 | 0 |  | 0 | 0 | 16508273
Santa Clara County | 2013 | 15967891 | 273985 | N/A | 0 | 0 |  | 0 | 0 | 16241876
Santa Clara County | 2012 | 15690853 | 277038 | N/A | 0 | 0 |  | 0 | 0 | 15967891
Santa Clara County | 2011 | 15069856 | 296481 | N/A | 0 | 0 |  | -324516 | -324516 | 15690853
Santa Clara County | 2010 | 14160474 | 909382 | N/A | 0 | 0 |  | 0 | 0 | 15069856
Santa Clara County | 2009 | 13233668 | 926806 | N/A | 0 | 0 |  | 0 | 0 | 14160474
Santa Clara County | 2008 | 12300876 | 928969 | N/A | 0 | 0 |  | 0 | 0 | 13233668
Santa Clara County | 2007 | 11363780 | 937096 | N/A | 0 | 0 |  | 0 | 0 | 12300876
Saratoga | 2019 | 3861275 | 94923 | N/A | 0 | 0 |  | 0 | 0 | 3956198
Saratoga | 2018 | 3765917 | 95358 | N/A | 0 | 0 |  | 0 | 0 | 3861275
Saratoga | 2017 | 3670203 | 95714 | N/A | 0 | 0 |  | 0 | 0 | 3765917
Saratoga | 2016 | 3575159 | 95044 | N/A | 0 | 0 |  | 0 | 0 | 3670203
Saratoga | 2015 | 3479150 | 96009 | N/A | 0 | 0 |  | 0 | 0 | 3575159
Saratoga | 2014 | 3382724 | 96426 | N/A | 0 | 0 |  | 0 | 0 | 3479150
Saratoga | 2013 | 3284995 | 97729 | N/A | 0 | 0 |  | 0 | 0 | 3382724
Saratoga | 2012 | 3187102 | 97893 | N/A | 0 | 0 |  | 0 | 0 | 3284995
Saratoga | 2011 | 3088768 | 98334 | N/A | 0 | 0 |  | 0 | 0 | 3187102
Saratoga | 2010 | 2895499 | 193269 | N/A | 0 | 0 |  | 0 | 0 | 3088768
Saratoga | 2009 | 2702300 | 193199 | N/A | 0 | 0 |  | 0 | 0 | 2895499
Saratoga | 2008 | 2507886 | 193276 | N/A | 0 | 0 |  | 0 | 0 | 2702300
Saratoga | 2007 | 2315146 | 192740 | N/A | 0 | 0 |  | 0 | 0 | 2507886
Sunnyvale | 2019 | 10556560.74 | 447598 | N/A | 0 | 0 |  | 0 | 0 | 11004158.74
Sunnyvale | 2018 | 10112026.74 | 444534 | N/A | 0 | 0 |  | 0 | 0 | 10556560.74
Sunnyvale | 2017 | 14575650.9 | 442997 | N/A | 0 | 0 |  | 4906621.16 | 4906621.16 | 10112026.74
Sunnyvale | 2016 | 14137366.9 | 438284 | N/A | 0 | 0 |  | 0 | 0 | 14575650.9
Sunnyvale | 2015 | 13694994.9 | 442372 | N/A | 0 | 0 |  | 0 | 0 | 14137366.9
Sunnyvale | 2014 | 13251815.9 | 443179 | N/A | 0 | 0 |  | 0 | 0 | 13694994.9
Sunnyvale | 2013 | 12812160.9 | 439655 | N/A | 0 | 0 |  | 0 | 0 | 13251815.9
Sunnyvale | 2012 | 12373768.9 | 438392 | N/A | 0 | 0 |  | 0 | 0 | 12812160.9
Sunnyvale | 2011 | 11936750.9 | 437018 | N/A | 0 | 0 |  | 0 | 0 | 12373768.9
Sunnyvale | 2010 | 11063120.9 | 873630 | N/A | 0 | 0 |  | 0 | 0 | 11936750.9
Sunnyvale | 2009 | 10189780.9 | 873340 | N/A | 0 | 0 |  | 0 | 0 | 11063120.9
Sunnyvale | 2008 | 9310516.9 | 874198 | N/A | 0 | 0 |  | 0 | 0 | 10189780.9
Sunnyvale | 2007 | 8434313.9 | 876203 | N/A | 0 | 0 |  | 0 | 0 | 9310516.9
Santa Clara County Total |  |  | 72860262 |  |  | 0 |  | 63317271.13 | 63317271.13
Santa Cruz County
Capitola | 2019 | 2050841.78 | 45842 | N/A | 0 | 0 |  | 0 | 0 | 2096683.78
Capitola | 2018 | 2004171.78 | 46670 | N/A | 0 | 0 |  | 0 | 0 | 2050841.78
Capitola | 2017 | 1957305.78 | 46866 | N/A | 0 | 0 |  | 0 | 0 | 2004171.78
Capitola | 2016 | 1910767.78 | 46538 | N/A | 0 | 0 |  | 0 | 0 | 1957305.78
Capitola | 2015 | 1863785.78 | 46982 | N/A | 0 | 0 |  | 0 | 0 | 1910767.78
Capitola | 2014 | 1816535.78 | 47250 | N/A | 0 | 0 |  | 0 | 0 | 1863785.78
Capitola | 2013 | 1768901.78 | 47634 | N/A | 0 | 0 |  | 0 | 0 | 1816535.78
Capitola | 2012 | 1721230.78 | 47671 | N/A | 0 | 0 |  | 0 | 0 | 1768901.78
Capitola | 2011 | 1673732.78 | 47498 | N/A | 0 | 0 |  | 0 | 0 | 1721230.78
Capitola | 2010 | 1579893.78 | 93839 | N/A | 0 | 0 |  | 0 | 0 | 1673732.78
Capitola | 2009 | 1486321.78 | 93572 | N/A | 0 | 0 |  | 0 | 0 | 1579893.78
Capitola | 2008 | 1392117.78 | 93661 | N/A | 0 | 0 |  | 0 | 0 | 1486321.78
Capitola | 2007 | 1298244.78 | 93873 | N/A | 0 | 0 |  | 0 | 0 | 1392117.78
Santa Cruz | 2019 | 3267350.41 | 209346 | N/A | 0 | 0 |  | 0 | 0 | 3268696.41
Santa Cruz | 2018 | 3267329.41 | 208021 | N/A | 0 | 0 |  | 0 | 0 | 3267350.41
Santa Cruz | 2017 | 3267138.41 | 208191 | N/A | 0 | 0 |  | 0 | 0 | 3267329.41
Santa Cruz | 2016 | 3268650.41 | 206488 | N/A | 0 | 0 |  | 0 | 0 | 3267138.41
Santa Cruz | 2015 | 60796.41 | 207854 | N/A | 0 | 3000000 | $3,000,000 (Vallejo) | 0 | 0 | 3268650.41
Santa Cruz | 2014 | -147655.59 | 208452 | N/A | 0 | 0 |  | 0 | 0 | 60796.41
Santa Cruz | 2013 | -355571.59 | 207916 | N/A | 0 | 0 |  | 0 | 0 | -147655.59 | Within 5-year borrow
Santa Cruz | 2012 | 3333029 | 208740 | N/A | 0 | 0 |  | 3897340.59 | 3897340.59 | -355571.59 | Within 5-year borrow
Santa Cruz | 2011 | 3208560 | 208918 | N/A | 0 | 0 |  | 84449 | 84449 | 3333029
Santa Cruz | 2010 | 2785873 | 422687 | N/A | 0 | 0 |  | 0 | 0 | 3208560
Santa Cruz | 2009 | 2364134 | 421739 | N/A | 0 | 0 |  | 0 | 0 | 2785873
Santa Cruz | 2008 | 1939922 | 421805 | N/A | 0 | 0 |  | 0 | 0 | 2364134
Santa Cruz | 2007 | 1518164 | 421758 | N/A | 0 | 0 |  | 0 | 0 | 1939922
Santa Cruz County | 2019 | 16430512.91 | 539134 | N/A | 0 | 0 |  | 0 | 0 | 16969646.91
Santa Cruz County | 2018 | 17918135.39 | 536216 | N/A | 0 | 0 |  | 2023838.48 | 2023838.48 | 16430512.91
Santa Cruz County | 2017 | 17381233.39 | 536902 | N/A | 0 | 0 |  | 0 | 0 | 17918135.39
Santa Cruz County | 2016 | 16848173.39 | 533060 | N/A | 0 | 0 |  | 0 | 0 | 17381233.39
Santa Cruz County | 2015 | 16309898.39 | 538275 | N/A | 0 | 0 |  | 0 | 0 | 16848173.39
Santa Cruz County | 2014 | 15768639.39 | 541259 | N/A | 0 | 0 |  | 0 | 0 | 16309898.39
Santa Cruz County | 2013 | 15227492.39 | 541147 | N/A | 0 | 0 |  | 0 | 0 | 15768639.39
Santa Cruz County | 2012 | 14685335.39 | 542157 | N/A | 0 | 0 |  | 0 | 0 | 15227492.39
Santa Cruz County | 2011 | 14063181.39 | 542154 | N/A | 0 | 0 |  | -80000 | -80000 | 14685335.39
Santa Cruz County | 2010 | 12921863.39 | 1141318 | N/A | 0 | 0 |  | 0 | 0 | 14063181.39
Santa Cruz County | 2009 | 11781381.39 | 1140482 | N/A | 0 | 0 |  | 0 | 0 | 12921863.39
Santa Cruz County | 2008 | 10634008.39 | 1141103 | N/A | 0 | 0 |  | 0 | 0 | 11781381.39
Santa Cruz County | 2007 | 11086667 | 1141654 | N/A | 0 | 0 |  | 1594312.61 | 1594312.61 | 10634008.39
Scotts Valley | 2019 | 1165688 | 34075 | N/A | 0 | 0 |  | 0 | 0 | 1199763
Scotts Valley | 2018 | 1132392 | 33296 | N/A | 0 | 0 |  | 0 | 0 | 1165688
Scotts Valley | 2017 | 1099031 | 33361 | N/A | 0 | 0 |  | 0 | 0 | 1132392
Scotts Valley | 2016 | 1065914 | 33117 | N/A | 0 | 0 |  | 0 | 0 | 1099031
Scotts Valley | 2015 | 1032369 | 33545 | N/A | 0 | 0 |  | 0 | 0 | 1065914
Scotts Valley | 2014 | 998660 | 33709 | N/A | 0 | 0 |  | 0 | 0 | 1032369
Scotts Valley | 2013 | 965393 | 33267 | N/A | 0 | 0 |  | 0 | 0 | 998660
Scotts Valley | 2012 | 932109 | 33284 | N/A | 0 | 0 |  | 0 | 0 | 965393
Scotts Valley | 2011 | 898825 | 33284 | N/A | 0 | 0 |  | 0 | 0 | 932109
Scotts Valley | 2010 | 836152 | 62673 | N/A | 0 | 0 |  | 0 | 0 | 898825
Scotts Valley | 2009 | 773527 | 62625 | N/A | 0 | 0 |  | 0 | 0 | 836152
Scotts Valley | 2008 | 710345 | 62796 | N/A | 0 | 0 |  | 0 | 0 | 773527
Scotts Valley | 2007 | 647415 | 62930 | N/A | 0 | 0 |  | 0 | 0 | 710345
Watsonville | 2019 | 1747611.22 | 113507 | N/A | 0 | 0 |  | 0 | 0 | 1861118.22
Watsonville | 2018 | 3002362 | 113453 | N/A | 0 | 0 |  | 1368203.78 | 1368203.78 | 1747611.22
Watsonville | 2017 | 2888527 | 113835 | N/A | 0 | 0 |  | 0 | 0 | 3002362
Watsonville | 2016 | 2774915 | 113612 | N/A | 0 | 0 |  | 0 | 0 | 2888527
Watsonville | 2015 | 2660296 | 114619 | N/A | 0 | 0 |  | 0 | 0 | 2774915
Watsonville | 2014 | 2545318 | 114978 | N/A | 0 | 0 |  | 0 | 0 | 2660296
Watsonville | 2013 | 2430995 | 114323 | N/A | 0 | 0 |  | 0 | 0 | 2545318
Watsonville | 2012 | 2318483 | 112512 | N/A | 0 | 0 |  | 0 | 0 | 2430995
Watsonville | 2011 | 2205881 | 112602 | N/A | 0 | 0 |  | 0 | 0 | 2318483
Watsonville | 2010 | 2008242 | 197639 | N/A | 0 | 0 |  | 0 | 0 | 2205881
Watsonville | 2009 | 1810734 | 197508 | N/A | 0 | 0 |  | 0 | 0 | 2008242
Watsonville | 2008 | 1611495 | 197935 | N/A | 0 | 0 |  | 0 | 0 | 1810734
Watsonville | 2007 | 1413087 | 198408 | N/A | 0 | 0 |  | 0 | 0 | 1611495
Santa Cruz County Total |  |  | 16141565 |  |  | 3000000 |  | 8888144.46 | 8888144.46
Shasta County
Anderson | 2019 | -2056986.38 | 40122 | N/A | 0 | 0 |  | 0 | 0 | -2016864.38 | Borrowed beyond 5 years (see AL 4553-E)
Anderson | 2018 | -2096863.38 | 39877 | N/A | 0 | 0 |  | 0 | 0 | -2056986.38 | Borrowed beyond 5 years (see AL 4553-E)
Anderson | 2017 | -2136707.38 | 39844 | N/A | 0 | 0 |  | 0 | 0 | -2096863.38 | Borrowed beyond 5 years (see AL 4553-E)
Anderson | 2016 | -2176117.38 | 39410 | N/A | 0 | 0 |  | 0 | 0 | -2136707.38 | Borrowed beyond 5 years (see AL 4553-E)
Anderson | 2015 | 1117163.88 | 40014 | N/A | 0 | 0 |  | 3333295.26 | 3333295.26 | -2176117.38 | Borrowed beyond 5 years (see AL 4553-E)
Anderson | 2014 | 576569.88 | 40594 | N/A | 0 | 500000 | $500,000 (Shasta County) | 0 | 0 | 1117163.88
Anderson | 2013 | 535926.88 | 40643 | N/A | 0 | 0 |  | 0 | 0 | 576569.88
Anderson | 2012 | 495255.88 | 40671 | N/A | 0 | 0 |  | 0 | 0 | 535926.88
Anderson | 2011 | 454590.88 | 40665 | N/A | 0 | 0 |  | 0 | 0 | 495255.88
Anderson | 2010 | 380910.88 | 73680 | N/A | 0 | 0 |  | 0 | 0 | 454590.88
Anderson | 2009 | 307273.88 | 73637 | N/A | 0 | 0 |  | 0 | 0 | 380910.88
Anderson | 2008 | 233423.88 | 73385 | N/A | 0 | 0 |  | 0 | 0 | 307273.88
Anderson | 2007 | 160001.88 | 73422 | N/A | 0 | 0 |  | 0 | 0 | 233423.88
Shasta County | 2019 | 9047609.75 | 329087 | N/A | 0 | 0 |  | 0 | 0 | 9376696.75
Shasta County | 2018 | 8719487.75 | 328122 | N/A | 0 | 0 |  | 0 | 0 | 9047609.75
Shasta County | 2017 | 8391013.75 | 328474 | N/A | 0 | 0 |  | 0 | 0 | 8719487.75
Shasta County | 2016 | 8065264.75 | 325749 | N/A | 0 | 0 |  | 0 | 0 | 8391013.75
Shasta County | 2015 | 7735800.75 | 329464 | N/A | 0 | 0 |  | 0 | 0 | 8065264.75
Shasta County | 2014 | 7904191.75 | 331609 | N/A | 0 | 0 |  | 0 | 0 | 7735800.75
Shasta County | 2013 | 7569627.75 | 334564 | N/A | 0 | 0 |  | 0 | 0 | 7904191.75
Shasta County | 2012 | 7234783.75 | 334844 | N/A | 0 | 0 |  | 0 | 0 | 7569627.75
Shasta County | 2011 | 6900343.75 | 334520 | N/A | 0 | 0 |  | 80 | 80 | 7234783.75
Shasta County | 2010 | 6428185.75 | 665997 | N/A | 0 | 0 |  | 193839 | 193839 | 6900343.75
Shasta County | 2009 | 5763068.75 | 665117 | N/A | 0 | 0 |  | 0 | 0 | 6428185.75
Shasta County | 2008 | 5369403.28 | 665009 | N/A | 0 | 0 |  | 275197.53 | 275197.53 | 5763068.75
Shasta County | 2007 | 5414426.9 | 664846 | N/A | 0 | 0 |  | 709869.62 | 709869.62 | 5369403.28
Shasta Lake | 2019 | 7560 | 522 | N/A | 0 | 0 |  | 0 | 0 | 8082
Shasta Lake | 2018 | 7061 | 499 | N/A | 0 | 0 |  | 0 | 0 | 7560
Shasta Lake | 2017 | 6550 | 511 | N/A | 0 | 0 |  | 0 | 0 | 7061
Shasta Lake | 2016 | 6043 | 507 | N/A | 0 | 0 |  | 0 | 0 | 6550
Shasta Lake | 2015 | 5531 | 512 | N/A | 0 | 0 |  | 0 | 0 | 6043
Shasta Lake | 2014 | 5016 | 515 | N/A | 0 | 0 |  | 0 | 0 | 5531
Shasta Lake | 2013 | 4477 | 539 | N/A | 0 | 0 |  | 0 | 0 | 5016
Shasta Lake | 2012 | 3936 | 541 | N/A | 0 | 0 |  | 0 | 0 | 4477
Shasta Lake | 2011 | 3405 | 531 | N/A | 0 | 0 |  | 0 | 0 | 3936
Shasta Lake | 2010 | 2979 | 426 | N/A | 0 | 0 |  | 0 | 0 | 3405
Shasta Lake | 2009 | 2552 | 427 | N/A | 0 | 0 |  | 0 | 0 | 2979
Shasta Lake | 2008 | 2116 | 430 | N/A | 0 | 0 |  | 0 | 0 | 2552
Shasta Lake | 2007 | 1692 | 424 | N/A | 0 | 0 |  | 0 | 0 | 2116
Shasta County Total |  |  | 6299750 |  |  | 500000 |  | 4512281.41 | 4512281.41
Sierra County
Sierra County | 2019 | 439181 | 12346 | N/A | 0 | 0 |  | 0 | 0 | 451527
Sierra County | 2018 | 426859 | 12322 | N/A | 0 | 0 |  | 0 | 0 | 439181
Sierra County | 2017 | 414503 | 12356 | N/A | 0 | 0 |  | 0 | 0 | 426859
Sierra County | 2016 | 402264 | 12239 | N/A | 0 | 0 |  | 0 | 0 | 414503
Sierra County | 2015 | 389951 | 12313 | N/A | 0 | 0 |  | 0 | 0 | 402264
Sierra County | 2014 | 377561 | 12390 | N/A | 0 | 0 |  | 0 | 0 | 389951
Sierra County | 2013 | 365148 | 12413 | N/A | 0 | 0 |  | 0 | 0 | 377561
Sierra County | 2012 | 352736 | 12412 | N/A | 0 | 0 |  | 0 | 0 | 365148
Sierra County | 2011 | 340392 | 12344 | N/A | 0 | 0 |  | 0 | 0 | 352736
Sierra County | 2010 | 313230 | 27162 | N/A | 0 | 0 |  | 0 | 0 | 340392
Sierra County | 2009 | 286087 | 27143 | N/A | 0 | 0 |  | 0 | 0 | 313230
Sierra County | 2008 | 258808 | 27136 | N/A | 0 | 0 |  | 0 | 0 | 286087
Sierra County | 2007 | 231636 | 27172 | N/A | 0 | 0 |  | 0 | 0 | 258808
Sierra County Total |  |  | 219748 |  |  | 0 |  | 0 | 0
Siskiyou County
Siskiyou County | 2019 | 38624 | 478 | N/A | 0 | 0 |  | 0 | 0 | 39102
Siskiyou County | 2018 | 38157 | 467 | N/A | 0 | 0 |  | 0 | 0 | 38624
Siskiyou County | 2017 | 37688 | 469 | N/A | 0 | 0 |  | 0 | 0 | 38157
Siskiyou County | 2016 | 37218 | 470 | N/A | 0 | 0 |  | 0 | 0 | 37688
Siskiyou County | 2015 | 36754 | 464 | N/A | 0 | 0 |  | 0 | 0 | 37218
Siskiyou County | 2014 | 36287 | 467 | N/A | 0 | 0 |  | 0 | 0 | 36754
Siskiyou County | 2013 | 35787 | 500 | N/A | 0 | 0 |  | 0 | 0 | 36287
Siskiyou County | 2012 | 35274 | 513 | N/A | 0 | 0 |  | 0 | 0 | 35787
Siskiyou County | 2011 | 34771 | 503 | N/A | 0 | 0 |  | 0 | 0 | 35274
Siskiyou County | 2010 | 33457 | 1314 | N/A | 0 | 0 |  | 0 | 0 | 34771
Siskiyou County | 2009 | 32143 | 1314 | N/A | 0 | 0 |  | 0 | 0 | 33457
Siskiyou County | 2008 | 30820 | 1317 | N/A | 0 | 0 |  | 0 | 0 | 32143
Siskiyou County | 2007 | 29509 | 1311 | N/A | 0 | 0 |  | 0 | 0 | 30820
Siskiyou County Total |  |  | 9587 |  |  | 0 |  | 0 | 0
Solano County
Benicia | 2019 | 2339163 | 76360 | N/A | 0 | 0 |  | 0 | 0 | 2415523
Benicia | 2018 | 2262906 | 76257 | N/A | 0 | 0 |  | 0 | 0 | 2339163
Benicia | 2017 | 2186536 | 76370 | N/A | 0 | 0 |  | 0 | 0 | 2262906
Benicia | 2016 | 2110674 | 75862 | N/A | 0 | 0 |  | 0 | 0 | 2186536
Benicia | 2015 | 2033991 | 76683 | N/A | 0 | 0 |  | 0 | 0 | 2110674
Benicia | 2014 | 1956801 | 77190 | N/A | 0 | 0 |  | 0 | 0 | 2033991
Benicia | 2013 | 1879774 | 77027 | N/A | 0 | 0 |  | 0 | 0 | 1956801
Benicia | 2012 | 1802526 | 77248 | N/A | 0 | 0 |  | 0 | 0 | 1879774
Benicia | 2011 | 1724987 | 77539 | N/A | 0 | 0 |  | 0 | 0 | 1802526
Benicia | 2010 | 1577898 | 147089 | N/A | 0 | 0 |  | 0 | 0 | 1724987
Benicia | 2009 | 1430955 | 146943 | N/A | 0 | 0 |  | 0 | 0 | 1577898
Benicia | 2008 | 1282719 | 147335 | N/A | 0 | 0 |  | 0 | 0 | 1430955
Benicia | 2007 | 1135391 | 147328 | N/A | 0 | 0 |  | 0 | 0 | 1282719
Dixon | 2019 | 699605 | 41674 | N/A | 0 | 0 |  | 0 | 0 | 741279
Dixon | 2018 | 658283 | 41322 | N/A | 0 | 0 |  | 0 | 0 | 699605
Dixon | 2017 | 617092 | 41191 | N/A | 0 | 0 |  | 0 | 0 | 658283
Dixon | 2016 | 576462 | 40630 | N/A | 0 | 0 |  | 0 | 0 | 617092
Dixon | 2015 | 535650 | 40812 | N/A | 0 | 0 |  | 0 | 0 | 576462
Dixon | 2014 | 494912 | 40738 | N/A | 0 | 0 |  | 0 | 0 | 535650
Dixon | 2013 | 454539 | 40373 | N/A | 0 | 0 |  | 0 | 0 | 494912
Dixon | 2012 | 414110 | 40429 | N/A | 0 | 0 |  | 0 | 0 | 454539
Dixon | 2011 | 372262 | 41848 | N/A | 0 | 0 |  | 0 | 0 | 414110
Dixon | 2010 | 303459 | 68803 | N/A | 0 | 0 |  | 0 | 0 | 372262
Dixon | 2009 | 234674 | 68785 | N/A | 0 | 0 |  | 0 | 0 | 303459
Dixon | 2008 | 165263 | 68927 | N/A | 0 | 0 |  | 0 | 0 | 234674
Dixon | 2007 | 96180 | 69083 | N/A | 0 | 0 |  | 0 | 0 | 165263
Fairfield | 2019 | 5736379.22 | 222337 | N/A | 0 | 0 |  | 0 | 0 | 5958716.22
Fairfield | 2018 | 5514580.22 | 221799 | N/A | 0 | 0 |  | 0 | 0 | 5736379.22
Fairfield | 2017 | 5293451.22 | 221129 | N/A | 0 | 0 |  | 0 | 0 | 5514580.22
Fairfield | 2016 | 5075145.22 | 218306 | N/A | 0 | 0 |  | 0 | 0 | 5293451.22
Fairfield | 2015 | 4855617.22 | 219528 | N/A | 0 | 0 |  | 0 | 0 | 5075145.22
Fairfield | 2014 | 4635515.22 | 220102 | N/A | 0 | 0 |  | 0 | 0 | 4855617.22
Fairfield | 2013 | 4416322.22 | 219193 | N/A | 0 | 0 |  | 0 | 0 | 4635515.22
Fairfield | 2012 | 4196374.22 | 219948 | N/A | 0 | 0 |  | 0 | 0 | 4416322.22
Fairfield | 2011 | 3976451.22 | 219923 | N/A | 0 | 0 |  | 0 | 0 | 4196374.22
Fairfield | 2010 | 3590612.22 | 385839 | N/A | 0 | 0 |  | 0 | 0 | 3976451.22
Fairfield | 2009 | 3205186.22 | 385426 | N/A | 0 | 0 |  | 0 | 0 | 3590612.22
Fairfield | 2008 | 2816973.22 | 385681 | N/A | 0 | 0 |  | 0 | 0 | 3205186.22
Fairfield | 2007 | 2430690.22 | 386283 | N/A | 0 | 0 |  | 0 | 0 | 2816973.22
Rio Vista | 2019 | 702013 | 31423 | N/A | 0 | 0 |  | 0 | 0 | 733436
Rio Vista | 2018 | 671475 | 30538 | N/A | 0 | 0 |  | 0 | 0 | 702013
Rio Vista | 2017 | 641349 | 30126 | N/A | 0 | 0 |  | 0 | 0 | 671475
Rio Vista | 2016 | 611998 | 29351 | N/A | 0 | 0 |  | 0 | 0 | 641349
Rio Vista | 2015 | 582831 | 29167 | N/A | 0 | 0 |  | 0 | 0 | 611998
Rio Vista | 2014 | 553912 | 28919 | N/A | 0 | 0 |  | 0 | 0 | 582831
Rio Vista | 2013 | 525182 | 28730 | N/A | 0 | 0 |  | 0 | 0 | 553912
Rio Vista | 2012 | 496522 | 28660 | N/A | 0 | 0 |  | 0 | 0 | 525182
Rio Vista | 2011 | 467873 | 28649 | N/A | 0 | 0 |  | 0 | 0 | 496522
Rio Vista | 2010 | 420802 | 47071 | N/A | 0 | 0 |  | 0 | 0 | 467873
Rio Vista | 2009 | 373821 | 46981 | N/A | 0 | 0 |  | 0 | 0 | 420802
Rio Vista | 2008 | 326642 | 46851 | N/A | 0 | 0 |  | 0 | 0 | 373821
Rio Vista | 2007 | 280083 | 46559 | N/A | 0 | 0 |  | 0 | 0 | 326642
Solano County | 2019 | 3885502 | 116186 | N/A | 0 | 0 |  | 0 | 0 | 4001688
Solano County | 2018 | 3770831 | 114671 | N/A | 0 | 0 |  | 0 | 0 | 3885502
Solano County | 2017 | 3656366 | 114465 | N/A | 0 | 0 |  | 0 | 0 | 3770831
Solano County | 2016 | 3543018 | 113348 | N/A | 0 | 0 |  | 0 | 0 | 3656366
Solano County | 2015 | 3428692 | 114326 | N/A | 0 | 0 |  | 0 | 0 | 3543018
Solano County | 2014 | 3313936 | 114756 | N/A | 0 | 0 |  | 0 | 0 | 3428692
Solano County | 2013 | 3196141 | 117795 | N/A | 0 | 0 |  | 0 | 0 | 3313936
Solano County | 2012 | 3079953 | 116188 | N/A | 0 | 0 |  | 0 | 0 | 3196141
Solano County | 2011 | 2966370 | 113583 | N/A | 0 | 0 |  | 0 | 0 | 3079953
Solano County | 2010 | 2724393 | 241977 | N/A | 0 | 0 |  | 0 | 0 | 2966370
Solano County | 2009 | 2482925 | 241468 | N/A | 0 | 0 |  | 0 | 0 | 2724393
Solano County | 2008 | 2239791 | 241819 | N/A | 0 | 0 |  | 0 | 0 | 2482925
Solano County | 2007 | 1997628 | 242163 | N/A | 0 | 0 |  | 0 | 0 | 2239791
Suisun City | 2019 | 1068756 | 43066 | N/A | 0 | 0 |  | 0 | 0 | 1111822
Suisun City | 2018 | 1025547 | 43209 | N/A | 0 | 0 |  | 0 | 0 | 1068756
Suisun City | 2017 | 982169 | 43378 | N/A | 0 | 0 |  | 0 | 0 | 1025547
Suisun City | 2016 | 939215 | 42954 | N/A | 0 | 0 |  | 0 | 0 | 982169
Suisun City | 2015 | 895742 | 43473 | N/A | 0 | 0 |  | 0 | 0 | 939215
Suisun City | 2014 | 851996 | 43746 | N/A | 0 | 0 |  | 0 | 0 | 895742
Suisun City | 2013 | 808409 | 43587 | N/A | 0 | 0 |  | 0 | 0 | 851996
Suisun City | 2012 | 764614 | 43795 | N/A | 0 | 0 |  | 0 | 0 | 808409
Suisun City | 2011 | 720252 | 44362 | N/A | 0 | 0 |  | 0 | 0 | 764614
Suisun City | 2010 | 636365 | 83887 | N/A | 0 | 0 |  | 0 | 0 | 720252
Suisun City | 2009 | 552566 | 83799 | N/A | 0 | 0 |  | 0 | 0 | 636365
Suisun City | 2008 | 468764 | 83296 | N/A | 0 | 0 |  | 0 | 0 | 552566
Suisun City | 2007 | 385380 | 83384 | N/A | 0 | 0 |  | 0 | 0 | 468764
Vacaville | 2019 | 3902306.36 | 189253 | N/A | 0 | 0 |  | 0 | 0 | 4091559.36
Vacaville | 2018 | 3713819.36 | 188487 | N/A | 0 | 0 |  | 0 | 0 | 3902306.36
Vacaville | 2017 | 3525822.36 | 187997 | N/A | 0 | 0 |  | 0 | 0 | 3713819.36
Vacaville | 2016 | 4049011.19 | 185147 | N/A | 0 | 0 |  | 708335.83 | 708335.83 | 3525822.36
Vacaville | 2015 | 3862625.19 | 186386 | N/A | 0 | 0 |  | 0 | 0 | 4049011.19
Vacaville | 2014 | 3676068.19 | 186557 | N/A | 0 | 0 |  | 0 | 0 | 3862625.19
Vacaville | 2013 | 3490689.19 | 185379 | N/A | 0 | 0 |  | 0 | 0 | 3676068.19
Vacaville | 2012 | 3305035.19 | 185654 | N/A | 0 | 0 |  | 0 | 0 | 3490689.19
Vacaville | 2011 | 3118182.19 | 186853 | N/A | 0 | 0 |  | 0 | 0 | 3305035.19
Vacaville | 2010 | 2887257.19 | 324849 | N/A | 0 | 0 |  | 93924 | 0 | 3118182.19
Vacaville | 2009 | 2563213.19 | 324044 | N/A | 0 | 0 |  | 0 | 0 | 2887257.19
Vacaville | 2008 | 2237455.19 | 323624 | N/A | 0 | 0 |  | 0 | 0 | 2563213.19
Vacaville | 2007 | 2748952 | 323229 | N/A | 0 | 0 |  | 834725.81 | 834725.81 | 2237455.19
Vallejo | 2019 | 9320675 | 344514 | N/A | 0 | 0 |  | 0 | 0 | 9873189
Vallejo | 2018 | 8768784 | 343891 | N/A | 0 | 0 |  | 0 | 0 | 9320675
Vallejo | 2017 | 8965346 | 345438 | N/A | 0 | 0 |  | 0 | 0 | 8768784
Vallejo | 2016 | 8414120 | 343226 | N/A | 0 | 0 |  | 0 | 0 | 8965346
Vallejo | 2015 | 11067145 | 346975 | N/A | 0 | 0 |  | 0 | 0 | 8414120
Vallejo | 2014 | 10718019 | 349126 | N/A | 0 | 0 |  | 0 | 0 | 11067145
Vallejo | 2013 | 10371671 | 346348 | N/A | 0 | 0 |  | 0 | 0 | 10718019
Vallejo | 2012 | 10024019 | 347652 | N/A | 0 | 0 |  | 0 | 0 | 10371671
Vallejo | 2011 | 9675970 | 348049 | N/A | 0 | 0 |  | 0 | 0 | 10024019
Vallejo | 2010 | 9485627 | 681836 | N/A | 0 | 0 |  | 491493 | 491493 | 9675970
Vallejo | 2009 | 8803842 | 681785 | N/A | 0 | 0 |  | 0 | 0 | 9485627
Vallejo | 2008 | 8116944 | 682852 | N/A | 0 | 0 |  | 0 | 0 | 8803842
Vallejo | 2007 | 7432909 | 684035 | N/A | 0 | 0 |  | 0 | 0 | 8116944
Solano County Total |  |  | 17454232 |  |  | 0 |  | 2128478.64 | 2034554.64
Sonoma County
Cloverdale | 2019 | 824937 | 24903 | N/A | 0 | 0 |  | 0 | 0 | 849840
Cloverdale | 2018 | 800117 | 24820 | N/A | 0 | 0 |  | 0 | 0 | 824937
Cloverdale | 2017 | 775309 | 24808 | N/A | 0 | 0 |  | 0 | 0 | 800117
Cloverdale | 2016 | 750678 | 24631 | N/A | 0 | 0 |  | 0 | 0 | 775309
Cloverdale | 2015 | 725728 | 24950 | N/A | 0 | 0 |  | 0 | 0 | 750678
Cloverdale | 2014 | 700547 | 25181 | N/A | 0 | 0 |  | 0 | 0 | 725728
Cloverdale | 2013 | 675491 | 25056 | N/A | 0 | 0 |  | 0 | 0 | 700547
Cloverdale | 2012 | 650423 | 25068 | N/A | 0 | 0 |  | 0 | 0 | 675491
Cloverdale | 2011 | 625629 | 24794 | N/A | 0 | 0 |  | 0 | 0 | 650423
Cloverdale | 2010 | 582505 | 43124 | N/A | 0 | 0 |  | 0 | 0 | 625629
Cloverdale | 2009 | 539415 | 43090 | N/A | 0 | 0 |  | 0 | 0 | 582505
Cloverdale | 2008 | 495947 | 43180 | N/A | 0 | 0 |  | 0 | 0 | 539415
Cloverdale | 2007 | 452914 | 43033 | N/A | 0 | 0 |  | 0 | 0 | 495947
Cotati | 2019 | 593667 | 20727 | N/A | 0 | 0 |  | 0 | 0 | 614394
Cotati | 2018 | 573122 | 20545 | N/A | 0 | 0 |  | 0 | 0 | 593667
Cotati | 2017 | 552566 | 20556 | N/A | 0 | 0 |  | 0 | 0 | 573122
Cotati | 2016 | 532126 | 20440 | N/A | 0 | 0 |  | 0 | 0 | 552566
Cotati | 2015 | 511456 | 20670 | N/A | 0 | 0 |  | 0 | 0 | 532126
Cotati | 2014 | 490687 | 20769 | N/A | 0 | 0 |  | 0 | 0 | 511456
Cotati | 2013 | 469849 | 20838 | N/A | 0 | 0 |  | 0 | 0 | 490687
Cotati | 2012 | 449025 | 20824 | N/A | 0 | 0 |  | 0 | 0 | 469849
Cotati | 2011 | 428072 | 20953 | N/A | 0 | 0 |  | 0 | 0 | 449025
Cotati | 2010 | 389599 | 38473 | N/A | 0 | 0 |  | 0 | 0 | 428072
Cotati | 2009 | 351105 | 38494 | N/A | 0 | 0 |  | 0 | 0 | 389599
Cotati | 2008 | 312288 | 38573 | N/A | 0 | 0 |  | 0 | 0 | 351105
Cotati | 2007 | 273697 | 38591 | N/A | 0 | 0 |  | 0 | 0 | 312288
Healdsburg | 2019 | 34570.87 | 1799 | N/A | 0 | 0 |  | 0 | 0 | 36369.87
Healdsburg | 2018 | 32807.87 | 1763 | N/A | 0 | 0 |  | 0 | 0 | 34570.87
Healdsburg | 2017 | 30985.87 | 1822 | N/A | 0 | 0 |  | 0 | 0 | 32807.87
Healdsburg | 2016 | 110533 | 1798 | N/A | 0 | 0 |  | 81345.13 | 81345.13 | 30985.87
Healdsburg | 2015 | 11979 | 98554 | N/A | 0 | 0 |  | 0 | 0 | 110533
Healdsburg | 2014 | 9930 | 2049 | N/A | 0 | 0 |  | 0 | 0 | 11979
Healdsburg | 2013 | 7943 | 1987 | N/A | 0 | 0 |  | 0 | 0 | 9930
Healdsburg | 2012 | 5957 | 1986 | N/A | 0 | 0 |  | 0 | 0 | 7943
Healdsburg | 2011 | 3674 | 2283 | N/A | 0 | 0 |  | 0 | 0 | 5957
Healdsburg | 2010 | 1785 | 1889 | N/A | 0 | 0 |  | 0 | 0 | 3674
Healdsburg | 2009 | 0 | 1785 | N/A | 0 | 0 |  | 0 | 0 | 1785
Petaluma | 2019 | 1522313.53 | 161794 | N/A | 0 | 0 |  | 0 | 0 | 1684107.53
Petaluma | 2018 | 1361085.53 | 161228 | N/A | 0 | 0 |  | 0 | 0 | 1522313.53
Petaluma | 2017 | 1199547.53 | 161538 | N/A | 0 | 0 |  | 0 | 0 | 1361085.53
Petaluma | 2016 | 1039642.53 | 159905 | N/A | 0 | 0 |  | 0 | 0 | 1199547.53
Petaluma | 2015 | 2646366.28 | 161271 | N/A | 0 | 0 |  | 1767994.75 | 1767994.75 | 1039642.53
Petaluma | 2014 | 2484286.28 | 162080 | N/A | 0 | 0 |  | 0 | 0 | 2646366.28
Petaluma | 2013 | 2322962.28 | 161324 | N/A | 0 | 0 |  | 0 | 0 | 2484286.28
Petaluma | 2012 | 4783845 | 161213 | N/A | 0 | 0 |  | 2622095.72 | 2622095.72 | 2322962.28
Petaluma | 2011 | 4622193 | 161652 | N/A | 0 | 0 |  | 0 | 0 | 4783845
Petaluma | 2010 | 4328605 | 293588 | N/A | 0 | 0 |  | 0 | 0 | 4622193
Petaluma | 2009 | 4035047 | 293558 | N/A | 0 | 0 |  | 0 | 0 | 4328605
Petaluma | 2008 | 3739562 | 293608 | N/A | 0 | 0 |  | 0 | 0 | 4035047
Petaluma | 2007 | 3446406 | 293156 | N/A | 0 | 0 |  | 0 | 0 | 3739562
Rohnert Park | 2019 | 1523672.82 | 79898 | N/A | 0 | 0 |  | 0 | 0 | 1603570.82
Rohnert Park | 2018 | 1444313.82 | 79359 | N/A | 0 | 0 |  | 0 | 0 | 1523672.82
Rohnert Park | 2017 | 1365252.82 | 79061 | N/A | 0 | 0 |  | 0 | 0 | 1444313.82
Rohnert Park | 2016 | 2278738 | 78323 | N/A | 0 | 0 |  | 991808.18 | 991808.18 | 1365252.82
Rohnert Park | 2015 | 2200324 | 78414 | N/A | 0 | 0 |  | 0 | 0 | 2278738
Rohnert Park | 2014 | 2121337 | 78987 | N/A | 0 | 0 |  | 0 | 0 | 2200324
Rohnert Park | 2013 | 2043157 | 78180 | N/A | 0 | 0 |  | 0 | 0 | 2121337
Rohnert Park | 2012 | 1964704 | 78453 | N/A | 0 | 0 |  | 0 | 0 | 2043157
Rohnert Park | 2011 | 1886114 | 78590 | N/A | 0 | 0 |  | 0 | 0 | 1964704
Rohnert Park | 2010 | 1736426 | 149688 | N/A | 0 | 0 |  | 0 | 0 | 1886114
Rohnert Park | 2009 | 1586685 | 149741 | N/A | 0 | 0 |  | 0 | 0 | 1736426
Rohnert Park | 2008 | 1435531 | 150235 | N/A | 0 | 0 |  | 0 | 0 | 1586685
Rohnert Park | 2007 | 1285019 | 150512 | N/A | 0 | 0 |  | 0 | 0 | 1435531
Santa Rosa | 2019 | 3644023.35 | 480952 | N/A | 0 | 0 |  | 0 | 0 | 4124975.35
Santa Rosa | 2018 | 3178420.35 | 465603 | N/A | 0 | 0 |  | 0 | 0 | 3644023.35
Santa Rosa | 2017 | 2711566.35 | 466854 | N/A | 0 | 0 |  | 0 | 0 | 3178420.35
Santa Rosa | 2016 | 11101057.86 | 463956 | N/A | 0 | 0 |  | 8853447.51 | 8853447.51 | 2711566.35
Santa Rosa | 2015 | 10633268.86 | 467789 | N/A | 0 | 0 |  | 0 | 0 | 11101057.86
Santa Rosa | 2014 | 10163058.86 | 470210 | N/A | 0 | 0 |  | 0 | 0 | 10633268.86
Santa Rosa | 2013 | 9695616.86 | 467442 | N/A | 0 | 0 |  | 0 | 0 | 10163058.86
Santa Rosa | 2012 | 9229064.86 | 466552 | N/A | 0 | 0 |  | 0 | 0 | 9695616.86
Santa Rosa | 2011 | 8762470.86 | 466594 | N/A | 0 | 0 |  | 0 | 0 | 9229064.86
Santa Rosa | 2010 | 7921446.86 | 841024 | N/A | 0 | 0 |  | 0 | 0 | 8762470.86
Santa Rosa | 2009 | 7081417.86 | 840029 | N/A | 0 | 0 |  | 0 | 0 | 7921446.86
Santa Rosa | 2008 | 6235919.86 | 840103 | N/A | 0 | 0 |  | 0 | 0 | 7081417.86
Santa Rosa | 2007 | 6421833 | 838586 | N/A | 0 | 0 |  | 1024499.14 | 1019413.14 | 6235919.86
Sebastopol | 2019 | 961920 | 32455 | N/A | 0 | 0 |  | 0 | 0 | 994375
Sebastopol | 2018 | 929707 | 32213 | N/A | 0 | 0 |  | 0 | 0 | 961920
Sebastopol | 2017 | 897445 | 32262 | N/A | 0 | 0 |  | 0 | 0 | 929707
Sebastopol | 2016 | 865474 | 31971 | N/A | 0 | 0 |  | 0 | 0 | 897445
Sebastopol | 2015 | 833226 | 32248 | N/A | 0 | 0 |  | 0 | 0 | 865474
Sebastopol | 2014 | 800885 | 32341 | N/A | 0 | 0 |  | 0 | 0 | 833226
Sebastopol | 2013 | 768594 | 32291 | N/A | 0 | 0 |  | 0 | 0 | 800885
Sebastopol | 2012 | 736143 | 32451 | N/A | 0 | 0 |  | 0 | 0 | 768594
Sebastopol | 2011 | 703634 | 32509 | N/A | 0 | 0 |  | 0 | 0 | 736143
Sebastopol | 2010 | 643299 | 60335 | N/A | 0 | 0 |  | 0 | 0 | 703634
Sebastopol | 2009 | 584075 | 59224 | N/A | 0 | 0 |  | 0 | 0 | 643299
Sebastopol | 2008 | 524404 | 59310 | N/A | 0 | 0 |  | 0 | 0 | 584075
Sebastopol | 2007 | 464949 | 59455 | N/A | 0 | 0 |  | 0 | 0 | 524404
Sonoma | 2019 | -182488.78 | 42029 | N/A | 0 | 0 |  | 0 | 0 | -140459.78 | Within 5-year borrow
Sonoma | 2018 | -223527.78 | 41039 | N/A | 0 | 0 |  | 0 | 0 | -182488.78 | Within 5-year borrow
Sonoma | 2017 | -264841.78 | 41314 | N/A | 0 | 0 |  | 0 | 0 | -223527.78 | Borrowed beyond 5 years (see AL 4553-E)
Sonoma | 2016 | -305746.78 | 40905 | N/A | 0 | 0 |  | 0 | 0 | -264841.78 | Borrowed beyond 5 years (see AL 4553-E)
Sonoma | 2015 | -347200.78 | 41454 | N/A | 0 | 0 |  | 0 | 0 | -305746.78 | Borrowed beyond 5 years (see AL 4553-E)
Sonoma | 2014 | -388849.78 | 41649 | N/A | 0 | 0 |  | 0 | 0 | -347200.78 | Borrowed beyond 5 years (see AL 4553-E)
Sonoma | 2013 | -430422.78 | 41573 | N/A | 0 | 0 |  | 0 | 0 | -388849.78 | Borrowed beyond 5 years (see AL 4553-E)
Sonoma | 2012 | 1269464 | 41910 | N/A | 0 | 0 |  | 1741796.78 | 1741796.78 | -430422.78 | Borrowed beyond 5 years (see AL 4553-E)
Sonoma | 2011 | 1226960 | 42504 | N/A | 0 | 0 |  | 0 | 0 | 1269464
Sonoma | 2010 | 1150799 | 76161 | N/A | 0 | 0 |  | 0 | 0 | 1226960
Sonoma | 2009 | 1074683 | 76116 | N/A | 0 | 0 |  | 0 | 0 | 1150799
Sonoma | 2008 | 998043 | 76144 | N/A | 0 | 0 |  | 0 | 0 | 1074683
Sonoma | 2007 | 922257 | 75786 | N/A | 0 | 0 |  | 0 | 0 | 998043
Sonoma County | 2019 | 15763348.54 | 710140 | N/A | 0 | 0 |  | 0 | 0 | 16473488.54
Sonoma County | 2018 | 15027572.54 | 735776 | N/A | 0 | 0 |  | 0 | 0 | 15763348.54
Sonoma County | 2017 | 14291066.54 | 736506 | N/A | 0 | 0 |  | 0 | 0 | 15027572.54
Sonoma County | 2016 | 13560501.54 | 730565 | N/A | 0 | 0 |  | 0 | 0 | 14291066.54
Sonoma County | 2015 | 12823625.54 | 736876 | N/A | 0 | 0 |  | 0 | 0 | 13560501.54
Sonoma County | 2014 | 12083390.54 | 740235 | N/A | 0 | 0 |  | 0 | 0 | 12823625.54
Sonoma County | 2013 | 18713532.54 | 741536 | N/A | 0 | 0 |  | 7371678 | 7371678 | 12083390.54
Sonoma County | 2012 | 18371070.54 | 742462 | N/A | 0 | 0 |  | 400000 | 400000 | 18713532.54
Sonoma County | 2011 | 16914772.54 | 741632 | N/A | 0 | 0 |  | -714666 | -714666 | 18371070.54
Sonoma County | 2010 | 15346607.54 | 1568165 | N/A | 0 | 0 |  | 0 | 0 | 16914772.54
Sonoma County | 2009 | 13779695.54 | 1566912 | N/A | 0 | 0 |  | 0 | 0 | 15346607.54
Sonoma County | 2008 | 12203511.54 | 1567615 | N/A | 0 | 0 |  | 0 | 0 | 13779695.54
Sonoma County | 2007 | 11642699 | 1568290 | N/A | 0 | 0 |  | 1007477.46 | 1007477.46 | 12203511.54
Windsor | 2019 | 606864 | 44092 | N/A | 0 | 0 |  | 0 | 0 | 650956
Windsor | 2018 | 562669 | 44195 | N/A | 0 | 0 |  | 0 | 0 | 606864
Windsor | 2017 | 518443 | 44226 | N/A | 0 | 0 |  | 0 | 0 | 562669
Windsor | 2016 | 474508 | 43935 | N/A | 0 | 0 |  | 0 | 0 | 518443
Windsor | 2015 | 430129 | 44379 | N/A | 0 | 0 |  | 0 | 0 | 474508
Windsor | 2014 | 385414 | 44715 | N/A | 0 | 0 |  | 0 | 0 | 430129
Windsor | 2013 | 340465 | 44949 | N/A | 0 | 0 |  | 0 | 0 | 385414
Windsor | 2012 | 295419 | 45046 | N/A | 0 | 0 |  | 0 | 0 | 340465
Windsor | 2011 | 250807 | 44612 | N/A | 0 | 0 |  | 0 | 0 | 295419
Windsor | 2010 | 213134 | 37673 | N/A | 0 | 0 |  | 0 | 0 | 250807
Windsor | 2009 | 175458 | 37676 | N/A | 0 | 0 |  | 0 | 0 | 213134
Windsor | 2008 | 137197 | 37744 | N/A | 0 | 0 |  | 0 | 0 | 175458
Windsor | 2007 | 99454 | 37743 | N/A | 0 | 0 |  | 0 | 0 | 137197
Sonoma County Total |  |  | 27011200 |  |  | 0 |  | 25147476.67 | 25142390.67
Stanislaus County
Newman | 2019 | 1150460.55 | 23741 | N/A | 0 | 0 |  | 0 | 0 | 1174201.55
Newman | 2018 | 1126990.55 | 23470 | N/A | 0 | 0 |  | 0 | 0 | 1150460.55
Newman | 2017 | 1103729.55 | 23261 | N/A | 0 | 0 |  | 0 | 0 | 1126990.55
Newman | 2016 | 1080828.55 | 22901 | N/A | 0 | 0 |  | 0 | 0 | 1103729.55
Newman | 2015 | 279780.55 | 23048 | N/A | 0 | 778000 | $778,000 (Stanislaus County) | 0 | 0 | 1080828.55
Newman | 2014 | 256597.55 | 23183 | N/A | 0 | 0 |  | 0 | 0 | 279780.55
Newman | 2013 | 232828.55 | 23769 | N/A | 0 | 0 |  | 0 | 0 | 256597.55
Newman | 2012 | 208922.55 | 23906 | N/A | 0 | 0 |  | 0 | 0 | 232828.55
Newman | 2011 | 185256.55 | 23666 | N/A | 0 | 0 |  | 0 | 0 | 208922.55
Newman | 2010 | 145961.55 | 39295 | N/A | 0 | 0 |  | 0 | 0 | 185256.55
Newman | 2009 | 418679 | 39354 | N/A | 0 | 0 |  | 312071.45 | 312071.45 | 145961.55
Newman | 2008 | 379081 | 39324 | N/A | 0 | 0 |  | 0 | 0 | 418679
Newman | 2007 | 339964 | 39117 | N/A | 0 | 0 |  | 0 | 0 | 379081
Oakdale | 2019 | -192486.41 | 56419 | N/A | 0 | 0 |  | 0 | 0 | -136067.41 | Within 5-year borrow
Oakdale | 2018 | -248147.41 | 55661 | N/A | 0 | 0 |  | 0 | 0 | -192486.41 | Within 5-year borrow
Oakdale | 2017 | 1431912.32 | 55779 | N/A | 0 | 0 |  | 1735838.73 | 1735838.73 | -248147.41 | Within 5-year borrow
Oakdale | 2016 | 1376979.32 | 54933 | N/A | 0 | 0 |  | 0 | 0 | 1431912.32
Oakdale | 2015 | 1321492.32 | 55487 | N/A | 0 | 0 |  | 0 | 0 | 1376979.32
Oakdale | 2014 | 115630.32 | 55862 | N/A | 0 | 1150000 | $1,150,000 (Stanislaus County) | 0 | 0 | 1321492.32
Oakdale | 2013 | 59240.32 | 56390 | N/A | 0 | 0 |  | 0 | 0 | 115630.32
Oakdale | 2012 | 2959.32 | 56281 | N/A | 0 | 0 |  | 0 | 0 | 59240.32
Oakdale | 2011 | -53569.68 | 56529 | N/A | 0 | 0 |  | 0 | 0 | 2959.32
Oakdale | 2010 | -152618.68 | 99049 | N/A | 0 | 0 |  | 0 | 0 | -53569.68 | Within 5-year borrow
Oakdale | 2009 | -251617.68 | 98999 | N/A | 0 | 0 |  | 0 | 0 | -152618.68 | Within 5-year borrow
Oakdale | 2008 | -351458.68 | 99185 | N/A | 0 | 0 |  | 0 | 0 | -251617.68 | Within 5-year borrow
Oakdale | 2007 | 920900 | 97962 | N/A | 0 | 0 |  | 1370320.68 | 1370320.68 | -351458.68 | Within 5-year borrow
Patterson | 2019 | 0 | 0 | N/A | 0 | 0 |  | 0 | 0 | 0
Patterson | 2018 | 0 | 0 | N/A | 0 | 0 |  | 0 | 0 | 0
Patterson | 2017 | 0 | 0 | N/A | 0 | 0 |  | 0 | 0 | 0
Patterson | 2016 | 0 | 0 | N/A | 0 | 0 |  | 0 | 0 | 0
Patterson | 2015 | 0 | 0 | N/A | 0 | 0 |  | 0 | 0 | 0
Patterson | 2014 | 0 | 0 | N/A | 0 | 0 |  | 0 | 0 | 0
Patterson | 2013 | 0 | 0 | N/A | 0 | 0 |  | 0 | 0 | 0
Patterson | 2012 | 0 | 0 | N/A | 0 | 0 |  | 0 | 0 | 0
Patterson | 2011 | 0 | 0 | N/A | 0 | 0 |  | 0 | 0 | 0
Patterson | 2010 | 0 | 0 | N/A | 0 | 0 |  | 0 | 0 | 0
Patterson | 2009 | 0 | 0 | N/A | 0 | 0 |  | 0 | 0 | 0
Patterson | 2008 | 476464 | 0 | N/A | 0 | 0 |  | 0 | 0 | 0
Patterson | 2007 | 476464 | 0 | N/A | 0 | 0 |  | 0 | 0 | 476464
Riverbank | 2019 | -1688582.41 | 35243 | N/A | 0 | 0 |  | 0 | 0 | -1653339.41 | Borrowed beyond 5 years (see AL 4553-E)
Riverbank | 2018 | -1723720.41 | 35138 | N/A | 0 | 0 |  | 0 | 0 | -1688582.41 | Borrowed beyond 5 years (see AL 4553-E)
Riverbank | 2017 | -1758708.41 | 34988 | N/A | 0 | 0 |  | 0 | 0 | -1723720.41 | Borrowed beyond 5 years (see AL 4553-E)
Riverbank | 2016 | -1793524.41 | 34816 | N/A | 0 | 0 |  | 0 | 0 | -1758708.41 | Borrowed beyond 5 years (see AL 4553-E)
Riverbank | 2015 | -1828697.41 | 35173 | N/A | 0 | 0 |  | 0 | 0 | -1793524.41 | Borrowed beyond 5 years (see AL 4553-E)
Riverbank | 2014 | 587407 | 35429 | N/A | 0 | 0 |  | 2451533.41 | 2451533.41 | -1828697.41 | Borrowed beyond 5 years (see AL 4553-E)
Riverbank | 2013 | 551781 | 35626 | N/A | 0 | 0 |  | 0 | 0 | 587407
Riverbank | 2012 | 515962 | 35819 | N/A | 0 | 0 |  | 0 | 0 | 551781
Riverbank | 2011 | 480109 | 35853 | N/A | 0 | 0 |  | 0 | 0 | 515962
Riverbank | 2010 | 423069 | 57040 | N/A | 0 | 0 |  | 0 | 0 | 480109
Riverbank | 2009 | 365870 | 57199 | N/A | 0 | 0 |  | 0 | 0 | 423069
Riverbank | 2008 | 308139 | 57315 | N/A | 0 | 0 |  | 0 | 0 | 365870
Riverbank | 2007 | 250738 | 57401 | N/A | 0 | 0 |  | 0 | 0 | 308139
Stanislaus County | 2019 | 1090506 | 86816 | N/A | 0 | 0 |  | 0 | 0 | 1177322
Stanislaus County | 2018 | 1004039 | 86467 | N/A | 0 | 0 |  | 0 | 0 | 1090506
Stanislaus County | 2017 | 917973 | 86066 | N/A | 0 | 0 |  | 0 | 0 | 1004039
Stanislaus County | 2016 | 832538 | 85435 | N/A | 0 | 0 |  | 0 | 0 | 917973
Stanislaus County | 2015 | 1524958 | 85580 | N/A | 0 | 0 |  | 0 | 0 | 832538
Stanislaus County | 2014 | 3147985 | 85473 | N/A | 0 | 0 |  | 558500 | 558500 | 1524958
Stanislaus County | 2013 | 3061021 | 86964 | N/A | 0 | 0 |  | 0 | 0 | 3147985
Stanislaus County | 2012 | 2974636 | 86385 | N/A | 0 | 0 |  | 0 | 0 | 3061021
Stanislaus County | 2011 | 2888726 | 85910 | N/A | 0 | 0 |  | 0 | 0 | 2974636
Stanislaus County | 2010 | 2683817 | 204909 | N/A | 0 | 0 |  | 0 | 0 | 2888726
Stanislaus County | 2009 | 2479484 | 204333 | N/A | 0 | 0 |  | 0 | 0 | 2683817
Stanislaus County | 2008 | 2274238 | 204264 | N/A | 0 | 0 |  | 0 | 0 | 2479484
Stanislaus County | 2007 | 2069057 | 205181 | N/A | 0 | 0 |  | 0 | 0 | 2274238
Stanislaus County Total |  |  | 3407394 |  |  | 1928000 |  | 6428264.27 | 6428264.27
Sutter County
Live Oak | 2019 | 3960965 | 19014 | N/A | 0 | 0 |  | 0 | 0 | 3979979
Live Oak | 2018 | 3942053 | 18912 | N/A | 0 | 0 |  | 0 | 0 | 3960965
Live Oak | 2017 | 623168 | 18885 | N/A | 0 | 3300000 | $1,300,000 (Sutter County), $2,000,000 (Rocklin) | 0 | 0 | 3942053
Live Oak | 2016 | 604627 | 18541 | N/A | 0 | 0 |  | 0 | 0 | 623168
Live Oak | 2015 | 585853 | 18774 | N/A | 0 | 0 |  | 0 | 0 | 604627
Live Oak | 2014 | 566887 | 18966 | N/A | 0 | 0 |  | 0 | 0 | 585853
Live Oak | 2013 | 547524 | 19363 | N/A | 0 | 0 |  | 0 | 0 | 566887
Live Oak | 2012 | 528530 | 18994 | N/A | 0 | 0 |  | 0 | 0 | 547524
Live Oak | 2011 | 509832 | 18698 | N/A | 0 | 0 |  | 0 | 0 | 528530
Live Oak | 2010 | 476448 | 33384 | N/A | 0 | 0 |  | 0 | 0 | 509832
Live Oak | 2009 | 443065 | 33383 | N/A | 0 | 0 |  | 0 | 0 | 476448
Live Oak | 2008 | 409491 | 33359 | N/A | 0 | 0 |  | 0 | 0 | 443065
Live Oak | 2007 | 376260 | 33231 | N/A | 0 | 0 |  | 0 | 0 | 409491
Sutter County | 2019 | 2050115 | 136690 | N/A | 0 | 0 |  | 0 | 0 | 2186805
Sutter County | 2018 | 2814438 | 135677 | N/A | 0 | 0 |  | 0 | 0 | 2050115
Sutter County | 2017 | 3978583 | 135855 | N/A | 0 | 0 |  | 0 | 0 | 2814438
Sutter County | 2016 | 3843684 | 134899 | N/A | 0 | 0 |  | 0 | 0 | 3978583
Sutter County | 2015 | 3707977 | 135707 | N/A | 0 | 0 |  | 0 | 0 | 3843684
Sutter County | 2014 | 6370544 | 137433 | N/A | 0 | 0 |  | 0 | 0 | 3707977
Sutter County | 2013 | 6230059 | 140485 | N/A | 0 | 0 |  | 0 | 0 | 6370544
Sutter County | 2012 | 6089620 | 140439 | N/A | 0 | 0 |  | 0 | 0 | 6230059
Sutter County | 2011 | 5949778 | 139842 | N/A | 0 | 0 |  | 0 | 0 | 6089620
Sutter County | 2010 | 5605074 | 344704 | N/A | 0 | 0 |  | 0 | 0 | 5949778
Sutter County | 2009 | 5260923 | 344151 | N/A | 0 | 0 |  | 0 | 0 | 5605074
Sutter County | 2008 | 4914637 | 344670 | N/A | 0 | 0 |  | 0 | 0 | 5260923
Sutter County | 2007 | 4569876 | 344761 | N/A | 0 | 0 |  | 0 | 0 | 4914637
Yuba City | 2019 | 5763703.15 | 169702 | N/A | 0 | 0 |  | 0 | 0 | 5933405.15
Yuba City | 2018 | 6420783.15 | 169493 | N/A | 0 | 900000 | Sutter County ($900,000) | 1726573 | 1726573 | 5763703.15
Yuba City | 2017 | 6250711.15 | 170072 | N/A | 0 | 0 |  | 0 | 0 | 6420783.15
Yuba City | 2016 | 6082067.15 | 168644 | N/A | 0 | 0 |  | 0 | 0 | 6250711.15
Yuba City | 2015 | 5911609.15 | 170458 | N/A | 0 | 0 |  | 0 | 0 | 6082067.15
Yuba City | 2014 | 2941699.15 | 169910 | N/A | 0 | 2800000 | $2,800,000 (Sutter County) | 0 | 0 | 5911609.15
Yuba City | 2013 | 2771966.15 | 169733 | N/A | 0 | 0 |  | 0 | 0 | 2941699.15
Yuba City | 2012 | 2601880.15 | 170086 | N/A | 0 | 0 |  | 0 | 0 | 2771966.15
Yuba City | 2011 | 2430911.15 | 170969 | N/A | 0 | 0 |  | 0 | 0 | 2601880.15
Yuba City | 2010 | 2170574.15 | 260337 | N/A | 0 | 0 |  | 0 | 0 | 2430911.15
Yuba City | 2009 | 1910321.15 | 260253 | N/A | 0 | 0 |  | 0 | 0 | 2170574.15
Yuba City | 2008 | 1648498.15 | 259849 | N/A | 0 | 0 |  | 0 | 0 | 1910321.15
Yuba City | 2007 | 1602547 | 260121 | N/A | 0 | 0 |  | 214169.85 | 214169.85 | 1648498.15
Sutter County Total |  |  | 5488444 |  |  | 7000000 |  | 1940742.85 | 1940742.85
Tehama County
Corning | 2019 | 382661.89 | 29311 | N/A | 0 | 0 |  | 0 | 0 | 411972.89
Corning | 2018 | 353734.89 | 28927 | N/A | 0 | 0 |  | 0 | 0 | 382661.89
Corning | 2017 | 324666.89 | 29068 | N/A | 0 | 0 |  | 0 | 0 | 353734.89
Corning | 2016 | 295791.89 | 28875 | N/A | 0 | 0 |  | 0 | 0 | 324666.89
Corning | 2015 | 266549.89 | 29242 | N/A | 0 | 0 |  | 0 | 0 | 295791.89
Corning | 2014 | 237193.89 | 29356 | N/A | 0 | 0 |  | 0 | 0 | 266549.89
Corning | 2013 | 207913.89 | 29280 | N/A | 0 | 0 |  | 0 | 0 | 237193.89
Corning | 2012 | 178588.89 | 29325 | N/A | 0 | 0 |  | 0 | 0 | 207913.89
Corning | 2011 | 149004.89 | 29584 | N/A | 0 | 0 |  | 0 | 0 | 178588.89
Corning | 2010 | 91412.89 | 57592 | N/A | 0 | 0 |  | 0 | 0 | 149004.89
Corning | 2009 | 33887.89 | 57525 | N/A | 0 | 0 |  | 0 | 0 | 91412.89
Corning | 2008 | -23692.11 | 57242 | N/A | 0 | 0 |  | 0 | 0 | 33887.89
Corning | 2007 | -80828.11 | 57136 | N/A | 0 | 0 |  | 0 | 0 | -23692.11 | Within 5-year borrow
Red Bluff | 2019 | 1489159 | 56101 | N/A | 0 | 0 |  | 0 | 0 | 1545260
Red Bluff | 2018 | 1433271 | 55888 | N/A | 0 | 0 |  | 0 | 0 | 1489159
Red Bluff | 2017 | 1377246 | 56025 | N/A | 0 | 0 |  | 0 | 0 | 1433271
Red Bluff | 2016 | 1321564 | 55682 | N/A | 0 | 0 |  | 0 | 0 | 1377246
Red Bluff | 2015 | 1265268 | 56296 | N/A | 0 | 0 |  | 0 | 0 | 1321564
Red Bluff | 2014 | 1208418 | 56850 | N/A | 0 | 0 |  | 0 | 0 | 1265268
Red Bluff | 2013 | 1151227 | 57191 | N/A | 0 | 0 |  | 0 | 0 | 1208418
Red Bluff | 2012 | 1093956 | 57271 | N/A | 0 | 0 |  | 0 | 0 | 1151227
Red Bluff | 2011 | 1037381 | 56575 | N/A | 0 | 0 |  | 0 | 0 | 1093956
Red Bluff | 2010 | 927475 | 109906 | N/A | 0 | 0 |  | 0 | 0 | 1037381
Red Bluff | 2009 | 817960 | 109515 | N/A | 0 | 0 |  | 0 | 0 | 927475
Red Bluff | 2008 | 707821 | 109492 | N/A | 0 | 0 |  | 0 | 0 | 817960
Red Bluff | 2007 | 598476 | 109345 | N/A | 0 | 0 |  | 0 | 0 | 707821
Tehama | 2019 | 66337 | 2361 | N/A | 0 | 0 |  | 0 | 0 | 68698
Tehama | 2018 | 63985 | 2352 | N/A | 0 | 0 |  | 0 | 0 | 66337
Tehama | 2017 | 61637 | 2348 | N/A | 0 | 0 |  | 0 | 0 | 63985
Tehama | 2016 | 59317 | 2320 | N/A | 0 | 0 |  | 0 | 0 | 61637
Tehama | 2015 | 56973 | 2344 | N/A | 0 | 0 |  | 0 | 0 | 59317
Tehama | 2014 | 54605 | 2368 | N/A | 0 | 0 |  | 0 | 0 | 56973
Tehama | 2013 | 52178 | 2427 | N/A | 0 | 0 |  | 0 | 0 | 54605
Tehama | 2012 | 49773 | 2405 | N/A | 0 | 0 |  | 0 | 0 | 52178
Tehama | 2011 | 47329 | 2444 | N/A | 0 | 0 |  | 0 | 0 | 49773
Tehama | 2010 | 42001 | 5328 | N/A | 0 | 0 |  | 0 | 0 | 47329
Tehama | 2009 | 36676 | 5325 | N/A | 0 | 0 |  | 0 | 0 | 42001
Tehama | 2008 | 31320 | 5328 | N/A | 0 | 0 |  | 0 | 0 | 36676
Tehama | 2007 | 26007 | 5313 | N/A | 0 | 0 |  | 0 | 0 | 31320
Tehama County | 2019 | 8419494 | 232519 | N/A | 0 | 0 |  | 0 | 0 | 8652013
Tehama County | 2018 | 8188838 | 230656 | N/A | 0 | 0 |  | 0 | 0 | 8419494
Tehama County | 2017 | 7958186 | 230652 | N/A | 0 | 0 |  | 0 | 0 | 8188838
Tehama County | 2016 | 7729907 | 228279 | N/A | 0 | 0 |  | 0 | 0 | 7958186
Tehama County | 2015 | 7500648 | 229259 | N/A | 0 | 0 |  | 0 | 0 | 7729907
Tehama County | 2014 | 7271102 | 229546 | N/A | 0 | 0 |  | 0 | 0 | 7500648
Tehama County | 2013 | 7039313 | 231789 | N/A | 0 | 0 |  | 0 | 0 | 7271102
Tehama County | 2012 | 6807690 | 231623 | N/A | 0 | 0 |  | 0 | 0 | 7039313
Tehama County | 2011 | 6629769 | 231845 | N/A | 0 | 0 |  | 53924 | 53924 | 6807690
Tehama County | 2010 | 6208692 | 421077 | N/A | 0 | 0 |  | 0 | 0 | 6629769
Tehama County | 2009 | 5788792 | 419900 | N/A | 0 | 0 |  | 0 | 0 | 6208692
Tehama County | 2008 | 5366885 | 419255 | N/A | 0 | 0 |  | 0 | 0 | 5788792
Tehama County | 2007 | 4949642 | 417243 | N/A | 0 | 0 |  | 0 | 0 | 5366885
Tehama County Total |  |  | 5234906 |  |  | 0 |  | 53924 | 53924
Trinity County
Trinity County | 2019 | 415443 | 19530 | N/A | 0 | 0 |  | 0 | 0 | 434973
Trinity County | 2018 | 1027255 | 19292 | N/A | 0 | 0 |  | 0 | 0 | 415443
Trinity County | 2017 | 1007934 | 19321 | N/A | 0 | 0 |  | 0 | 0 | 1027255
Trinity County | 2016 | 988834 | 19100 | N/A | 0 | 0 |  | 0 | 0 | 1007934
Trinity County | 2015 | 969573 | 19261 | N/A | 0 | 0 |  | 0 | 0 | 988834
Trinity County | 2014 | 950286 | 19287 | N/A | 0 | 0 |  | 0 | 0 | 969573
Trinity County | 2013 | 930705 | 19581 | N/A | 0 | 0 |  | 0 | 0 | 950286
Trinity County | 2012 | 911103 | 19602 | N/A | 0 | 0 |  | 0 | 0 | 930705
Trinity County | 2011 | 891616 | 19487 | N/A | 0 | 0 |  | 0 | 0 | 911103
Trinity County | 2010 | 790581 | 101035 | N/A | 0 | 0 |  | 0 | 0 | 891616
Trinity County | 2009 | 689820 | 100761 | N/A | 0 | 0 |  | 0 | 0 | 790581
Trinity County | 2008 | 588795 | 100802 | N/A | 0 | 0 |  | 0 | 0 | 689820
Trinity County | 2007 | 488053 | 100742 | N/A | 0 | 0 |  | 0 | 0 | 588795
Trinity County Total |  |  | 577801 |  |  | 0 |  | 0 | 0
Tulare County
Dinuba | 2019 | 1164806 | 55687 | N/A | 0 | 0 |  | 0 | 0 | 1220493
Dinuba | 2018 | 1109857 | 54949 | N/A | 0 | 0 |  | 0 | 0 | 1164806
Dinuba | 2017 | 1055053 | 54804 | N/A | 0 | 0 |  | 0 | 0 | 1109857
Dinuba | 2016 | 1000754 | 54299 | N/A | 0 | 0 |  | 0 | 0 | 1055053
Dinuba | 2015 | 946505 | 54249 | N/A | 0 | 0 |  | 0 | 0 | 1000754
Dinuba | 2014 | 892202 | 54303 | N/A | 0 | 0 |  | 0 | 0 | 946505
Dinuba | 2013 | 837738 | 54464 | N/A | 0 | 0 |  | 0 | 0 | 892202
Dinuba | 2012 | 782797 | 54941 | N/A | 0 | 0 |  | 0 | 0 | 837738
Dinuba | 2011 | 729840 | 52957 | N/A | 0 | 0 |  | 0 | 0 | 782797
Dinuba | 2010 | 634545 | 95295 | N/A | 0 | 0 |  | 0 | 0 | 729840
Dinuba | 2009 | 539517 | 95028 | N/A | 0 | 0 |  | 0 | 0 | 634545
Dinuba | 2008 | 444469 | 94453 | N/A | 0 | 0 |  | 0 | 0 | 539517
Dinuba | 2007 | 349657 | 94812 | N/A | 0 | 0 |  | 0 | 0 | 444469
Tulare County | 2019 | 6695796 | 166896 | N/A | 0 | 0 |  | 0 | 0 | 6862692
Tulare County | 2018 | 6529775 | 166021 | N/A | 0 | 0 |  | 0 | 0 | 6695796
Tulare County | 2017 | 6363858 | 165917 | N/A | 0 | 0 |  | 0 | 0 | 6529775
Tulare County | 2016 | 6199752 | 164106 | N/A | 0 | 0 |  | 0 | 0 | 6363858
Tulare County | 2015 | 6034226 | 165526 | N/A | 0 | 0 |  | 0 | 0 | 6199752
Tulare County | 2014 | 5868111 | 166115 | N/A | 0 | 0 |  | 0 | 0 | 6034226
Tulare County | 2013 | 5697183 | 170928 | N/A | 0 | 0 |  | 0 | 0 | 5868111
Tulare County | 2012 | 5527544 | 169639 | N/A | 0 | 0 |  | 0 | 0 | 5697183
Tulare County | 2011 | 5356630 | 170914 | N/A | 0 | 0 |  | 0 | 0 | 5527544
Tulare County | 2010 | 4999081 | 357549 | N/A | 0 | 0 |  | 0 | 0 | 5356630
Tulare County | 2009 | 4642818 | 356263 | N/A | 0 | 0 |  | 0 | 0 | 4999081
Tulare County | 2008 | 4285686 | 355194 | N/A | 0 | 0 |  | 0 | 0 | 4642818
Tulare County | 2007 | 3931660 | 354026 | N/A | 0 | 0 |  | 0 | 0 | 4285686
Tulare County Total |  |  | 3799335 |  |  | 0 |  | 0 | 0
Tuolomne County
Sonora | 2019 | 856238 | 30059 | N/A | 0 | 0 |  | 0 | 0 | 886297
Sonora | 2018 | 826284 | 29954 | N/A | 0 | 0 |  | 0 | 0 | 856238
Sonora | 2017 | 1196292 | 29992 | N/A | 0 | 0 |  | 0 | 0 | 826284
Sonora | 2016 | 1166449 | 29843 | N/A | 0 | 0 |  | 0 | 0 | 1196292
Sonora | 2015 | 1136274 | 30175 | N/A | 0 | 0 |  | 0 | 0 | 1166449
Sonora | 2014 | 1105947 | 30327 | N/A | 0 | 0 |  | 0 | 0 | 1136274
Sonora | 2013 | 1075431 | 30516 | N/A | 0 | 0 |  | 0 | 0 | 1105947
Sonora | 2012 | 1044901 | 30530 | N/A | 0 | 0 |  | 0 | 0 | 1075431
Sonora | 2011 | 1014463 | 30438 | N/A | 0 | 0 |  | 0 | 0 | 1044901
Sonora | 2010 | 954937 | 59526 | N/A | 0 | 0 |  | 0 | 0 | 1014463
Sonora | 2009 | 895417 | 59520 | N/A | 0 | 0 |  | 0 | 0 | 954937
Sonora | 2008 | 835447 | 59617 | N/A | 0 | 0 |  | 0 | 0 | 895417
Sonora | 2007 | 775738 | 59709 | N/A | 0 | 0 |  | 0 | 0 | 835447
Tuolumne County | 2019 | 9101808 | 311192 | N/A | 0 | 0 |  | 0 | 0 | 9413000
Tuolumne County | 2018 | 8792225 | 309583 | N/A | 0 | 0 |  | 0 | 0 | 9101808
Tuolumne County | 2017 | 8482289 | 309936 | N/A | 0 | 0 |  | 0 | 0 | 8792225
Tuolumne County | 2016 | 8175110 | 307179 | N/A | 0 | 0 |  | 0 | 0 | 8482289
Tuolumne County | 2015 | 7865272 | 309838 | N/A | 0 | 0 |  | 0 | 0 | 8175110
Tuolumne County | 2014 | 7553840 | 311432 | N/A | 0 | 0 |  | 0 | 0 | 7865272
Tuolumne County | 2013 | 9296132 | 311036 | N/A | 0 | 0 |  | 2053328 | 2053328 | 7553840
Tuolumne County | 2012 | 8984900 | 311232 | N/A | 0 | 0 |  | 0 | 0 | 9296132
Tuolumne County | 2011 | 8674373 | 310527 | N/A | 0 | 0 |  | 0 | 0 | 8984900
Tuolumne County | 2010 | 8073178 | 601195 | N/A | 0 | 0 |  | 0 | 0 | 8674373
Tuolumne County | 2009 | 7472854 | 600324 | N/A | 0 | 0 |  | 0 | 0 | 8073178
Tuolumne County | 2008 | 6869058 | 600219 | N/A | 0 | 0 |  | 0 | 0 | 7472854
Tuolumne County | 2007 | 6269158 | 599900 | N/A | 0 | 0 |  | 0 | 0 | 6869058
Tuolomne County Total |  |  | 5703799 |  |  | 0 |  | 2053328 | 2053328
Yolo County
Davis | 2019 | 3398469.73 | 156082 | N/A | 0 | 0 |  | 0 | 0 | 3554551.73
Davis | 2018 | 3242494.73 | 155975 | N/A | 0 | 0 |  | 0 | 0 | 3398469.73
Davis | 2017 | 3083899.73 | 158595 | N/A | 0 | 0 |  | 0 | 0 | 3242494.73
Davis | 2016 | 4643687 | 157406 | N/A | 0 | 0 |  | 1717193.27 | 1717193.27 | 3083899.73
Davis | 2015 | 4484504 | 159183 | N/A | 0 | 0 |  | 0 | 0 | 4643687
Davis | 2014 | 4324367 | 160137 | N/A | 0 | 0 |  | 0 | 0 | 4484504
Davis | 2013 | 4163758 | 160609 | N/A | 0 | 0 |  | 0 | 0 | 4324367
Davis | 2012 | 4004061 | 159697 | N/A | 0 | 0 |  | 0 | 0 | 4163758
Davis | 2011 | 3843620 | 160441 | N/A | 0 | 0 |  | 0 | 0 | 4004061
Davis | 2010 | 3554180 | 289440 | N/A | 0 | 0 |  | 0 | 0 | 3843620
Davis | 2009 | 3264763 | 289417 | N/A | 0 | 0 |  | 0 | 0 | 3554180
Davis | 2008 | 2972693 | 290202 | N/A | 0 | 0 |  | 0 | 0 | 3264763
Davis | 2007 | 2681799 | 290894 | N/A | 0 | 0 |  | 0 | 0 | 2972693
West Sacramento | 2019 | 1341440.32 | 145008 | N/A | 0 | 0 |  | 0 | 0 | 1486448.32
West Sacramento | 2018 | 1197769.32 | 143671 | N/A | 0 | 0 |  | 0 | 0 | 1341440.32
West Sacramento | 2017 | 1053751.32 | 144018 | N/A | 0 | 0 |  | 0 | 0 | 1197769.32
West Sacramento | 2016 | 911335.32 | 142416 | N/A | 0 | 0 |  | 0 | 0 | 1053751.32
West Sacramento | 2015 | 768979.32 | 142356 | N/A | 0 | 0 |  | 0 | 0 | 911335.32
West Sacramento | 2014 | 626461.32 | 142518 | N/A | 0 | 0 |  | 0 | 0 | 768979.32
West Sacramento | 2013 | 484385.32 | 142076 | N/A | 0 | 0 |  | 0 | 0 | 626461.32
West Sacramento | 2012 | 2177657.88 | 142072 | N/A | 0 | 0 |  | 1835344.56 | 1835344.56 | 484385.32
West Sacramento | 2011 | 2036765.88 | 140892 | N/A | 0 | 0 |  | 0 | 0 | 2177657.88
West Sacramento | 2010 | 1776757.88 | 260008 | N/A | 0 | 0 |  | 0 | 0 | 2036765.88
West Sacramento | 2009 | 1517080.88 | 259677 | N/A | 0 | 0 |  | 0 | 0 | 1776757.88
West Sacramento | 2008 | 1255377.88 | 260076 | N/A | 0 | 0 |  | 0 | 0 | 1517080.88
West Sacramento | 2007 | 1826804 | 258813 | N/A | 0 | 0 |  | 830239.12 | 830239.12 | 1255377.88
Winters | 2019 | 473005 | 17328 | N/A | 0 | 0 |  | 0 | 0 | 490333
Winters | 2018 | 455700 | 17305 | N/A | 0 | 0 |  | 0 | 0 | 473005
Winters | 2017 | 438470 | 17230 | N/A | 0 | 0 |  | 0 | 0 | 455700
Winters | 2016 | 421489 | 16981 | N/A | 0 | 0 |  | 0 | 0 | 438470
Winters | 2015 | 404346 | 17143 | N/A | 0 | 0 |  | 0 | 0 | 421489
Winters | 2014 | 387107 | 17239 | N/A | 0 | 0 |  | 0 | 0 | 404346
Winters | 2013 | 369753 | 17354 | N/A | 0 | 0 |  | 0 | 0 | 387107
Winters | 2012 | 352225 | 17528 | N/A | 0 | 0 |  | 0 | 0 | 369753
Winters | 2011 | 334981 | 17244 | N/A | 0 | 0 |  | 0 | 0 | 352225
Winters | 2010 | 304340 | 30641 | N/A | 0 | 0 |  | 0 | 0 | 334981
Winters | 2009 | 273710 | 30630 | N/A | 0 | 0 |  | 0 | 0 | 304340
Winters | 2008 | 242941 | 30571 | N/A | 0 | 0 |  | 0 | 0 | 273710
Winters | 2007 | 212246 | 30695 | N/A | 0 | 0 |  | 0 | 0 | 242941
Woodland | 2019 | 2481459.07 | 146494 | N/A | 0 | 0 |  | 0 | 0 | 2627953.07
Woodland | 2018 | 2335720.07 | 145739 | N/A | 0 | 0 |  | 0 | 0 | 2481459.07
Woodland | 2017 | 2189813.07 | 145907 | N/A | 0 | 0 |  | 0 | 0 | 2335720.07
Woodland | 2016 | 2045560.07 | 144253 | N/A | 0 | 0 |  | 0 | 0 | 2189813.07
Woodland | 2015 | 3193250.36 | 145074 | N/A | 0 | 0 |  | 1292764.29 | 1292764.29 | 2045560.07
Woodland | 2014 | 3047542.36 | 145708 | N/A | 0 | 0 |  | 0 | 0 | 3193250.36
Woodland | 2013 | 2909206.21 | 145018 | N/A | 0 | 0 |  | 6681.85 | 0 | 3047542.36
Woodland | 2012 | 2764010.21 | 145196 | N/A | 0 | 0 |  | 0 | 0 | 2909206.21
Woodland | 2011 | 2614476.21 | 146614 | N/A | 0 | 0 |  | -2920 | -2920 | 2764010.21
Woodland | 2010 | 2346947.21 | 267529 | N/A | 0 | 0 |  | 0 | 0 | 2614476.21
Woodland | 2009 | 2080119.21 | 266828 | N/A | 0 | 0 |  | 0 | 0 | 2346947.21
Woodland | 2008 | 1811785.21 | 266654 | N/A | 0 | 0 |  | 0 | 0 | 2080119.21
Woodland | 2007 | 1767933 | 265204 | N/A | 0 | 0 |  | 221351.79 | 221351.79 | 1811785.21
Yolo County | 2019 | 3022593.63 | 120056 | N/A | 0 | 0 |  | 0 | 0 | 3142649.63
Yolo County | 2018 | 2904294.63 | 118299 | N/A | 0 | 0 |  | 0 | 0 | 3022593.63
Yolo County | 2017 | 2786212.63 | 118082 | N/A | 0 | 0 |  | 0 | 0 | 2904294.63
Yolo County | 2016 | 2669448.63 | 116764 | N/A | 0 | 0 |  | 0 | 0 | 2786212.63
Yolo County | 2015 | 4443450 | 117503 | N/A | 0 | 0 |  | 1891504.37 | 1891504.37 | 2669448.63
Yolo County | 2014 | 4326074 | 117376 | N/A | 0 | 0 |  | 0 | 0 | 4443450
Yolo County | 2013 | 4208814 | 117260 | N/A | 0 | 0 |  | 0 | 0 | 4326074
Yolo County | 2012 | 4092097 | 116717 | N/A | 0 | 0 |  | 0 | 0 | 4208814
Yolo County | 2011 | 3977768 | 114329 | N/A | 0 | 0 |  | 0 | 0 | 4092097
Yolo County | 2010 | 3737540 | 240228 | N/A | 0 | 0 |  | 0 | 0 | 3977768
Yolo County | 2009 | 3498399 | 239141 | N/A | 0 | 0 |  | 0 | 0 | 3737540
Yolo County | 2008 | 3259199 | 237919 | N/A | 0 | 0 |  | 0 | 0 | 3498399
Yolo County | 2007 | 3022707 | 236492 | N/A | 0 | 0 |  | 0 | 0 | 3259199
Yolo County Total |  |  | 9575952 |  |  | 0 |  | 7792159.25 | 7785477.4
Yuba County
Marysville | 2019 | 2543127 | 53191 | N/A | 0 | 0 |  | 0 | 0 | 2596318
Marysville | 2018 | 2490189 | 52938 | N/A | 0 | 0 |  | 0 | 0 | 2543127
Marysville | 2017 | 2436976 | 53213 | N/A | 0 | 0 |  | 0 | 0 | 2490189
Marysville | 2016 | 2384183 | 52793 | N/A | 0 | 0 |  | 0 | 0 | 2436976
Marysville | 2015 | 2330799 | 53384 | N/A | 0 | 0 |  | 0 | 0 | 2384183
Marysville | 2014 | 2277137 | 53662 | N/A | 0 | 0 |  | 0 | 0 | 2330799
Marysville | 2013 | 2223045 | 54092 | N/A | 0 | 0 |  | 0 | 0 | 2277137
Marysville | 2012 | 2168946 | 54099 | N/A | 0 | 0 |  | 0 | 0 | 2223045
Marysville | 2011 | 2114668 | 54278 | N/A | 0 | 0 |  | 0 | 0 | 2168946
Marysville | 2010 | 1998693 | 115975 | N/A | 0 | 0 |  | 0 | 0 | 2114668
Marysville | 2009 | 1882836 | 115857 | N/A | 0 | 0 |  | 0 | 0 | 1998693
Marysville | 2008 | 1766224 | 115983 | N/A | 0 | 0 |  | 0 | 0 | 1882836
Marysville | 2007 | 1650305 | 115919 | N/A | 0 | 0 |  | 0 | 0 | 1766224
Wheatland | 2019 | 376077 | 10504 | N/A | 0 | 0 |  | 0 | 0 | 386581
Wheatland | 2018 | 365662 | 10415 | N/A | 0 | 0 |  | 0 | 0 | 376077
Wheatland | 2017 | 355166 | 10496 | N/A | 0 | 0 |  | 0 | 0 | 365662
Wheatland | 2016 | 344849 | 10317 | N/A | 0 | 0 |  | 0 | 0 | 355166
Wheatland | 2015 | 334554 | 10295 | N/A | 0 | 0 |  | 0 | 0 | 344849
Wheatland | 2014 | 324204 | 10350 | N/A | 0 | 0 |  | 0 | 0 | 334554
Wheatland | 2013 | 313937 | 10267 | N/A | 0 | 0 |  | 0 | 0 | 324204
Wheatland | 2012 | 303922 | 10015 | N/A | 0 | 0 |  | 0 | 0 | 313937
Wheatland | 2011 | 293979 | 9943 | N/A | 0 | 0 |  | 0 | 0 | 303922
Wheatland | 2010 | 276735 | 17244 | N/A | 0 | 0 |  | 0 | 0 | 293979
Wheatland | 2009 | 259517 | 17218 | N/A | 0 | 0 |  | 0 | 0 | 276735
Wheatland | 2008 | 242178 | 17224 | N/A | 0 | 0 |  | 0 | 0 | 259517
Wheatland | 2007 | 225022 | 17156 | N/A | 0 | 0 |  | 0 | 0 | 242178
Yuba County | 2019 | 1924631.75 | 209509 | N/A | 0 | 0 |  | 0 | 0 | 2134140.75
Yuba County | 2018 | 1717150.75 | 207481 | N/A | 0 | 0 |  | 0 | 0 | 1924631.75
Yuba County | 2017 | 6126085 | 207316 | N/A | 0 | 0 |  | 4616250.25 | 4616250.25 | 1717150.75
Yuba County | 2016 | 5920742 | 205343 | N/A | 0 | 0 |  | 0 | 0 | 6126085
Yuba County | 2015 | 5713272 | 207470 | N/A | 0 | 0 |  | 0 | 0 | 5920742
Yuba County | 2014 | 5505714 | 207558 | N/A | 0 | 0 |  | 0 | 0 | 5713272
Yuba County | 2013 | 5296188 | 209526 | N/A | 0 | 0 |  | 0 | 0 | 5505714
Yuba County | 2012 | 5086353 | 209835 | N/A | 0 | 0 |  | 0 | 0 | 5296188
Yuba County | 2011 | 4876800 | 209553 | N/A | 0 | 0 |  | 0 | 0 | 5086353
Yuba County | 2010 | 4481633 | 395167 | N/A | 0 | 0 |  | 0 | 0 | 4876800
Yuba County | 2009 | 4087746 | 393887 | N/A | 0 | 0 |  | 0 | 0 | 4481633
Yuba County | 2008 | 3692146 | 393207 | N/A | 0 | 0 |  | 0 | 0 | 4087746
Yuba County | 2007 | 3300804 | 391342 | N/A | 0 | 0 |  | 0 | 0 | 3692146
Yuba County Total |  |  | 4554022 |  |  | 0 |  | 4616250.25 | 4616250.25
PG&E Total |  |  | 695653205 |  |  | 55276564.04 |  | 638694335.63 | 637353684.51
Note on H4: Only incoming transfers, excludes loan repayments

## Annual Spending
Pacific Gas and Electric Company data for R.17-05-010 submitted on 4/17/2020; Note: Dollar value of projects completed from Annual Completion Reports and excludes canceled projects(if any) and excludes subsequent adjustments to projects originally reported in a previous year(if any).
(II.e) Annual Rule 20A Spending by Community (Nominal Terms)
Rule 20A Community | 2005 |  | 2006 |  | 2007 |  | 2008 |  | 2009 |  | 2010 |  | 2011 |  | 2012 |  | 2013 |  | 2014 |  | 2015 |  | 2016 |  | 2017 |  | 2018 |  | 2019
| Utility's total Rule 20A spending by Community | Total Dollar Value of projects completed | Utility's total Rule 20A spending by Community | Total Dollar Value of projects completed | Utility's total Rule 20A spending by Community | Total Dollar Value of projects completed | Utility's total Rule 20A spending by Community | Total Dollar Value of projects completed | Utility's total Rule 20A spending by Community | Total Dollar Value of projects completed | Utility's total Rule 20A spending by Community | Total Dollar Value of projects completed | Utility's total Rule 20A spending by Community | Total Dollar Value of projects completed | Utility's total Rule 20A spending by Community | Total Dollar Value of projects completed | Utility's total Rule 20A spending by Community | Total Dollar Value of projects completed | Utility's total Rule 20A spending by Community | Total Dollar Value of projects completed | Utility's total Rule 20A spending by Community | Total Dollar Value of projects completed | Utility's total Rule 20A spending by Community | Total Dollar Value of projects completed | Utility's total Rule 20A spending by Community | Total Dollar Value of projects completed | Utility's total Rule 20A spending by Community | Total Dollar Value of projects completed | Utility's total Rule 20A spending by Community | Total Dollar Value of projects completed
| Nominal $ | Nominal $ | Nominal $ | Nominal $ | Nominal $ | Nominal $ | Nominal $ | Nominal $ | Nominal $ | Nominal $ | Nominal $ | Nominal $ | Nominal $ | Nominal $ | Nominal $ | Nominal $ | Nominal $ | Nominal $ | Nominal $ | Nominal $ | Nominal $ | Nominal $ | Nominal $ | Nominal $ | Nominal $ | Nominal $ | Nominal $ | Nominal $ | Nominal $ | Nominal $
Alameda County
ALAMEDA COUNTY | 184920.73 | 0 | 338718.11 | 2918232.14 | 472510.4 | 0 | 319356.22 | 0 | 886980.22 | 0 | 1137775.58 | 0 | 3296402.95 | 0 | 7149004.87 | 0 | -693223.22 | 3361081 | -28013.83 | 0 | 37632.03 | 0 | 130537.46 | 8618365.16 | 76499.21 | 0 | 148632.85 |  | 3207794.51
ALBANY | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 7464.54 |  | 177887.39 |  | 34050.86 |  | 49213.31 |  | 770553.3 |  | 2084286.1 |  | 11967.59 | 3100967.09
BERKELEY | 15336.07 | 0 | 90696.68 | 0 | 231394.88 | 0 | 2910220.4 | 0 | 763506.47 | 0 | 1109979.13 | 0 | 43320.47 | 0 | 4738.09 | 5118222.1 | 14159.26 | 0 | 68469.31 | 0 | 41629.73 | 0 | 389498.64 | 0 | 433719.55 | 0 | 303946.31 |  | 127580.08
DUBLIN | 27365.74 | 0 | 912334.52 | 0 | 275266.56 | 0 | -4025 | 1215529.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27756.38 | 0 | 21338.11 | 0 | 1620848.09 |  | -22035.22 |  | 19941.32
EMERYVILLE | [26 empty] | 0 |  | 0
FREMONT | 143734.45 | 0 | 1564719.76 | 0 | 282852.02 | 1216245.94 | 984309.92 | 1087762.28 | 2473087.74 | 1916781.12 | 1208364.69 | 0 | 7756.34 | 1251374 | 0 | 0 | 0 | 0 | 0 | 0 | -3019.48 | 3501281.81 | 0 | 0 | 0 | 0 | 0 |  | 0
HAYWARD | 94254.91 | 0 | 254776.22 | 0 | 1897034.46 | 0 | 682061.15 | 0 | 418916.6 | 0 | 3593728.16 | 0 | 834164.15 | 0 | 7762707.67 | 3371422.79 | -292873.45 | 0 | 29463 | 12187005.37 | 0 | 0 | 0 | 0 | 11543.77 | 0 | 1428481.44 |  | 1320952.65
LIVERMORE | 348184.22 | 0 | 187722.42 | 0 | 1569.86 | 637872.59 | 2742.32 | 0 | 85640.23 | 0 | 9002.69 | 0 | 11747.06 | 0 | 22732.74 | 0 | 12394.32 | 0 | -126761.52 | 0 | 48767.48 | 0 | 858541.93 | 0 | 1228624.12 |  | -29410.37 | 1781725 | 0
NEWARK | [26 empty] | 0 |  | 0
OAKLAND | 252211.08 | 0 | 5180027.41 | 0 | 3641798.23 | 0 | 981623.28 | 0 | 1957885.39 | 0 | 1065257.88 | 0 | 1041974.91 | 0 | 6043116.36 | 13304691.5 | 5899099.15 | 0 | 372124.16 | 0 | 17207.9 | 0 | 17886.58 | 0 | 5868.71 | 13740062.12 | 0 |  | 0
PIEDMONT | [26 empty] | 0 |  | 0
PLEASANTON | 820477.26 | 0 | 399151.7 | 0 | 15886.76 | 0 | -18889.7 | 0 | 16608.68 | 2634710.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8580.06 | 0 | 25038 | 0 | 1510535.92 | 0 | 366250.62 |  | -186275.34 | 1681105.26 | 0
SAN LEANDRO | 545883.7 | 0 | 326252.91 | 0 | 22202.76 | 0 | 411102.41 | 0 | 1597701.62 | 989664.97 | 677517.95 | 0 | 661170.29 | 0 | 61388.25 | 0 | 13827.96 | 0 | 63546.23 | 3179509.83 | 39476.47 | 0 | 92790.36 | 0 | 59892.35 | 0 | 57362.81 |  | 36687.66
UNION CITY | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2488.77 | 0 | 11538.28 | 0 | 33408 | 0 | 10436.91 | 0 | 32653.34 | 0 | 27950.6 | 0 | 666697.09 | 0 | 1750184.61 |  | 0 | 2549343.6 | 0 |  | 0
Alameda County Total | 2432368.16 | 0 | 9254399.73 | 2918232.14 | 6840515.93 | 1854118.53 | 6268501 | 2303291.48 | 8202815.72 | 5541156.86 | 8813164.36 | 0 | 5929944.17 | 1251374 | 21054124.89 | 21794336.39 | 4993501.9 | 3361081 | 593245.4 | 15366515.2 | 935236.46 | 3501281.81 | 4820526.92 | 8618365.16 | 4573799.72 | 16289405.72 | 3784988.58 | 3462830.26 | 4724923.81 | 3100967.09
Alpine County
ALPINE COUNTY | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Alpine County Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Amador County
AMADOR CITY | [26 empty] | 0 |  | 0
AMADOR COUNTY | 21143.84 | 0 | 310012.59 | 0 | 799429.93 | 0 | 9799.01 | 0 | 734.11 | 1191231.55 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0
IONE | [26 empty] | 0 |  | 0
JACKSON | [26 empty] | 0 |  | 0
PLYMOUTH | [26 empty] | 0 |  | 0
SUTTER CREEK | [16 empty] | 0 |  | 0 | [7 empty] | 0 |  | 0
Amador County Total | 21143.84 | 0 | 310012.59 | 0 | 799429.93 | 0 | 9799.01 | 0 | 734.11 | 1191231.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Butte County
BIGGS | [26 empty] | 0 |  | 0
BUTTE COUNTY | 21334.522 | 0 | 420776.18 | 0 | 480737.1844 | 801892.36 | 591114.5416 | 0 | -12507.7128 | 1493425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32.36 | 0 | 2.6 | 0 | 2.77 | 0 | 3.1154 |  | 2.183
CHICO | -302834.202 | 547886.7798 | 553939.04 | 0 | 611847.3256 | 0 | 752327.5984 | 0 | -15918.9072 | 1963803.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 210297.37 | 0 | 2773867.21 |  | 2024611.71
OROVILLE | -239157.43 | 646674.8411 | -123.49 | 396069 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.54 | 0 | 1.17 | 0 | 1.24 | 0 | 1.0946 |  | 0.767
PARADISE | 444285.14 | 0 | 242835.78 | 0 | 0 | 753334.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 145843.25 | 0 | 293370.95 |  | 5004237.48
Butte County Total | -76371.97 | 1194561.6209 | 1217427.51 | 396069 | 1092584.51 | 1555226.61 | 1343442.14 | 0 | -28426.62 | 3457228.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46.9 | 0 | 3.77 | 0 | 356144.63 | 0 | 3067242.37 | 0 | 7028852.14 | 0
Calaveras County
ANGELS CAMP | [26 empty] | 0 |  | 0
CALAVERAS COUNTY | 13463.2 | 1476404.69 | 29957.7 | 0 | 8381.85 | 0 | 26187.4 | 0 | 131772.06 | 0 | -12558.4 | 0 | 22770.43 | 0 | 40383.15 | 0 | 60525.81 | 0 | 43698.8 | 0 | 49306.82 | 0 | 138574.44 | 0 | 54772.09 | 0 | 59293.74 |  | 39187.69
Calaveras County Total | 13463.2 | 1476404.69 | 29957.7 | 0 | 8381.85 | 0 | 26187.4 | 0 | 131772.06 | 0 | -12558.4 | 0 | 22770.43 | 0 | 40383.15 | 0 | 60525.81 | 0 | 43698.8 | 0 | 49306.82 | 0 | 138574.44 | 0 | 54772.09 | 0 | 59293.74 | 0 | 39187.69 | 0
Colusa County
COLUSA | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 11180.56 |  | 93839.43 |  | 288523.6656 |  | 760497.8943
COLUSA COUNTY | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 34795 |  | 292037.55 |  | 1279539.7344 |  | 3372642.8357
WILLIAMS | [26 empty] | 0 |  | 0
Colusa County Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45975.56 | 0 | 385876.98 | 0 | 1568063.4 | 0 | 4133140.73 | 0
Contra Costa County
ANTIOCH | 26148.12 | 1113831.62 | 52459.09 | 0 | 27323.66 | 0 | 147760.71 | 0 | 152484.81 | 0 | 965968.25 | 0 | 1198778.8 | 0 | 212716.41 | 0 | 739854.71 | 2303558 | 0 | 1009094.21 | -1585 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
BRENTWOOD | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 8319.1 |  | 31035.35 |  | 53613.17 |  | 1378933.69 |  | -2916.52 | 1476839.79
CLAYTON | [26 empty] | 0 |  | 0
CONCORD | 1118756.96 | 563911.57 | 517684.08 | 0 | 27512.73 | 0 | 92737.35 | 0 | 21548.76 | 0 | 771738.09 | 1850650 | 307699.93 | 0 | 345748.66 | 0 | 39965.25 | 0 | -1398 | 0 | 0 | 1467091.4 | 0 | 0 | 0 | 0 | 0 |  | 0
CONTRA COSTA COUNTY | 509041.51 | 0 | 50838.52 | 0 | 208288.21 | 0 | 29256.66 | 0 | -46929.1 | 0 | 27375.95 | 2300334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48635.4 | 0 | 245903.58 | 0 | 259372.37 | 0 | 329389.49 |  | 1155119.2
DANVILLE | 41497.52 | 0 | 1561708.98 | 0 | 662101.93 | 0 | 24473.57 | 0 | 397.47 | 0 | 0 | 2371997 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0
EL CERRITO | -95681.03 | 0 | 0 | 1817783.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0
HERCULES | [26 empty] | 0 |  | 0
LAFAYETTE | 0 | 0 | 0 | 0 | 0 | 0 | 86286.31 | 0 | 1015276.96 | 0 | -28091.22 | 0 | 0 | 1049391 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0
MARTINEZ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94996 | 0 | 620306.52 | 0 | 711774.21 | 0 | 141591.51 | 0 | 287710.65 | 0 | 0 | 0 | -5715 | 1828333.89 | 0 | 0 | 0 | 0 | 0 |  | 0
MORAGA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14759.45 | 0 | 1092981.71 | 0 | 312732.6 | 1434611.76 | 0 |  | 0
OAKLEY | [26 empty] | 0 |  | 0
ORINDA | 0 |  | 129.98 |  | 11.03 |  | 49210.23 |  | 45670.21 |  | 15363.81 |  | 12072.55 |  | 31640.35 |  | 144272.5 |  | 68711.58 |  | -367082.24 |  | 0 |  | 0 |  | 0 |  | 0
PINOLE | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2764.71 |  | 139052.77 |  | 78494.14 |  | 50760.14
PITTSBURG | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 30.17 |  | 40214.73 |  | 625401.48 |  | 82852.8 |  | 126040.08 |  | -103711.57 |  | 83077.61 |  | 88966.71
PLEASANT HILL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7401.73 | 0 | 15620.09 | 0 | 2004233.53 | 0 | 63246.05 | 2115155.64 | 48000.24 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
RICHMOND | 0 | 0 | 0 | 0 | 0 | 0 | 51815.65 | 0 | 126497.61 | 0 | 27851.79 | 0 | 27865.41 | 0 | 49065.98 | 0 | 524771.55 | 0 | 3613852.48 | 0 | -487.62 | 0 | 40091.07 |  | 4901.31 | 4335386.23 | 0 |  | 0
SAN PABLO | 5929.87 | 0 | 0 | 915637.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5637.81 | 0 | 461.07 | 0 | 483.25 | 0 | 5180.94 | 0 | 347645.65 | 0 | 965509.57 |  | -61775.32 | 1251314.97 | 0
SAN RAMON | 909901.52 | 0 | 9977.32 | 0 | 0 | 1034452.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0
WALNUT CREEK | 16568.73 | 4018496.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6381.85 | 0 | 89834.32 |  | 131426.82
Contra Costa County Total | 2532163.2 | 5696239.97 | 2192797.97 | 2733421.04 | 925237.56 | 1034452.89 | 481540.48 | 0 | 1409942.72 | 0 | 2400513.19 | 6522981 | 2265592.63 | 1049391 | 802050.98 | 0 | 3781483.99 | 2303558 | 4370296.84 | 3124249.85 | -167121.93 | 3295425.29 | 1886462.15 | 0 | 1637852.07 | 5769997.99 | 1897953.93 | 1251314.97 | 1423356.35 | 1476839.79
El Dorado County
EL DORADO COUNTY | 4545.1 | 0 | 3419.41 | 1147767.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14525.77 | 0 | 15883.95 | 0 | 99342.57 | 0 | 244738.66 | 0 | 317363.7 |  | 107300.47
PLACERVILLE | 67674.28 | 0 | 29972.54 | 0 | 84353.64 | 0 | 1768668.71 | 0 | -115053.66 | 0 | 71098.5 | 0 | 13629.9 | 0 | 0 | 0 |  | 0 |  | 1993373.79 |  | 0 |  | 0 |  | 0 | 0 |  | 0
El Dorado County Total | 72219.38 | 0 | 33391.95 | 1147767.13 | 84353.64 | 0 | 1768668.71 | 0 | -115053.66 | 0 | 71098.5 | 0 | 13629.9 | 0 | 0 | 0 | 0 | 0 | 14525.77 | 1993373.79 | 15883.95 | 0 | 99342.57 | 0 | 244738.66 | 0 | 317363.7 | 0 | 107300.47 | 0
Fresno County
CLOVIS | 138945.63 | 0 | 1262316.39 | 0 | 1989662.9 | 0 | 114595.4 | 0 | 11208.78 | 3502039.1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0
COALINGA | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 484.8 |  | 37.49 |  | 27.77
FIREBAUGH | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3300.28 | 0 | 2458.92 | 0 | 22773.22 | 0 | 74029.28 | 0 | 2274327.66 | 0 | 27234.93 | 0 | 82 | 2423475.29 | 0 | 0 | 0 | 0 | 0 |  | 0
FOWLER | 8087.63 | 0 | 2987.88 | 455361 | 0 | 0 | 0 | 0 | 9502.32 | 0 | 11446.22 | 0 | 26217.7 | 0 | 47766.62 | 0 | 764942.48 | 0 | 783 | 879266.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
FRESNO | 906607.78 | 1223095.6869 | 474967.49 | 2421185.06 | 716497.71 | 924176.55 | 2784889.16 | 0 | 890696.83 | 0 | 1609837.39 | 5036946 | 680295.74 | 0 | 3819771.87 | 0 | 1182716.14 | 1558816 | 1213513.74 | 0 | 857247.33 | 0 | 5597048.18 | 7725954.62 | 1559621.24 |  | 319492.23 | 6542609.88 | 182842.53
FRESNO COUNTY | 384438.5077 | 439700.2653 | 243923.9773 | 1952548.87 | 1281367.538 | 0 | 2100762.3642 | 0 | 646979.531 | 0 | 461714.235 | 3004765 | 2525.13 | 0 | 128.38 | 0 | -1585.02 | 600000 | 0 | 0 | 46.9 | 0 | 198961.94 | 0 | 2088646.62 |  | -36657.1 | 2260300.36 | 0
HURON | [26 empty] | 0 |  | 0
KERMAN | -10099.1399 | 0 | 5336.7949 | 0 | 200065.8228 | 0 | 184279.0624 | 0 | 10793.714 | 0 | 0 | 0 | 0 | 1097272 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0
KINGSBURG | 455.4072 |  | 128.2428 |  | 129.3192 |  | -1750.3416 |  | 1002.1 |  | 5603.36 |  | 4810.26 |  | 1005.83 |  | 1015.86 |  | 1064.72 |  | -14502.13 |  | 5756.23 |  | 1800.58 |  | 584.39 |  | 1158.68
MENDOTA | [26 empty] | 0 |  | 0
ORANGE COVE | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 354.94 |  | 28.24 |  | 29.64 |  | 21.61
PARLIER | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8155.92 | 0 | 11653.69 | 0 | 13485.98 | 0 | 24946.59 | 0 | 21979.29 | 0 | 18405.64 | 0 | 21125.4 | 0 | 159365.46 | 0 | 1439256.3 |  | 0 | 1636581.27 | 0
REEDLEY | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27412.35 | 0 | 116690.96 | 0 | 486000.98 | 0 | -1584.45 | 588819 | 2779.97 | 0 | 2913.65 | 0 | -16096.2 | 0 | 71602.03 | 0 | 713114.14 | 0 | 1635294.25 |  | 13683.11 | 2493012.88
SAN JOAQUIN | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [11 empty] | 0 |  | 0
SANGER | 912.525 | 0 | -912.525 | 0 | 0 | 0 | 50422.735 | 0 | 93644.795 | 0 | 456984.265 | 0 | 2222.12 | 0 | 0 | 0 |  | 525908 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0
SELMA | [26 empty] | 0 |  | 0
Fresno County Total | 1429348.34 | 1662795.9522 | 1988748.25 | 4829094.93 | 4187723.29 | 924176.55 | 5233198.38 | 0 | 1702696.62 | 3502039.1 | 2676389.04 | 8041711 | 1238331.13 | 1097272 | 3966064.12 | 588819 | 4246176.38 | 2684724 | 1263915.68 | 879266.34 | 847903.3 | 2423475.29 | 6033088.78 | 7725954.62 | 5802951.92 | 0 | 1918780.9 | 10439491.51 | 197733.7 | 2493012.88
Glenn County
GLENN COUNTY
ORLAND | [26 empty] | 0 |  | 0
WILLOWS | [16 empty] | 0 |  | 0 | [7 empty] | 0 |  | 0
Glenn County Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Humboldt County
ARCATA | 664365.64 | 0 | 77316.51 | 0 | 0 | 1109690.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0
BLUE LAKE | [26 empty] | 0 |  | 0
EUREKA | -3513.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13396.76 | 0 | 58205.19 | 0 | 572900.78 | 0 | 1405.66 | 654697.39 | 50547.06 | 0 | 273680.5 |  | 93522.51
FERNDALE | [26 empty] | 0 |  | 0
FORTUNA | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 180.7 |  | 142.59 |  | 238389.57 |  | 197495.08 |  | 82011.62 |  | 3671368.96
HUMBOLDT COUNTY | 11517.176 | 0 | 4163.3593 | 0 | 24490.9355 | 0 | 140134.5968 | 0 | 15110.37 | 125000 | 17007.33 | 0 | 19969.38 | 0 | 121358.54 | 0 | 348520.79 | 0 | 3289737.77 | 0 | 243293.42 | 3663855.44 | -2911.64 | 0 | 0 | 0 | 0 |  | 0
RIO DELL | [26 empty] | 0 |  | 0
TRINIDAD | 804.824 | 0 | 477.7107 | 0 | 12145.5645 | 0 | 78112.3132 | 0 | 333.74 | 124877 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0
Humboldt County Total | 673174.58 | 0 | 81957.58 | 0 | 36636.5 | 1109690.86 | 218246.91 | 0 | 15444.11 | 249877 | 17007.33 | 0 | 19969.38 | 0 | 121358.54 | 0 | 361917.55 | 0 | 3348123.66 | 0 | 816336.79 | 3663855.44 | 236883.59 | 654697.39 | 248042.14 | 0 | 355692.12 | 0 | 3764891.47 | 0
Kern County
ARVIN | [26 empty] | 0 |  | 0
BAKERSFIELD | 357881.54 | 1749618.3667 | -8830.1 | 1303320.95 | 0 | 0 | 337100.22 | 0 | 1820982.6 | 0 | 133714.78 | 787398 | 675677.69 | 1518177 | 698997.43 | 688009 | 3047226.41 | 0 | -9087.38 | 932892.42 | 41043.86 | 2860709.76 | 3367892.06 |  | 1167396.57 | 3425178.54 | 3633022.79 |  | 70846.1
KERN COUNTY | 206644.14 | 155202.62 | 1400811.33 | 208971.61 | 317428.33 | 0 | 218398.57 | 0 | 291439.81 | 0 | 2382106.08 | 2157181 | 215135.19 | 0 | 25772.15 | 0 | 0 | 2734351 | -12633 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82739.37 |  | 41939.04
MARICOPA | [26 empty] | 0 |  | 0
MCFARLAND | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 54841.77 |  | 202004.09 |  | 455244.07 |  | 10496.05
SHAFTER | [26 empty] | 0 |  | 0
TAFT | -10347.77 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [11 empty] | 0 |  | 0
WASCO | -403.88 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [11 empty] | 0 |  | 0
Kern County Total | 553774.03 | 1904820.9867 | 1391981.23 | 1512292.56 | 317428.33 | 0 | 555498.79 | 0 | 2112422.41 | 0 | 2515820.86 | 2944579 | 890812.88 | 1518177 | 724769.58 | 688009 | 3047226.41 | 2734351 | -21720.38 | 932892.42 | 41043.86 | 2860709.76 | 3422733.83 | 0 | 1369400.66 | 3425178.54 | 4171006.23 | 0 | 123281.19 | 0
Kings County
AVENAL | [26 empty] | 0 |  | 0
CORCORAN | [26 empty] | 0 |  | 0
KINGS COUNTY | 6746.7492 | 0 | 5910.8796 | 0 | 69071.7852 | 0 | 743101.0956 | 0 | 747516.3696 | 0 | -35422.4196 | 0 | 0 | 0 | 0 | 2350000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0
LEMOORE | 11994.2208 | 0 | 10508.2304 | 0 | 122794.2848 | 0 | 1321068.6144 | 0 | 1328917.9904 | 0 | -62973.1904 | 0 | 0 | 0 | 0 | 1940373.44 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0
Kings County Total | 18740.97 | 0 | 16419.11 | 0 | 191866.07 | 0 | 2064169.71 | 0 | 2076434.36 | 0 | -98395.61 | 0 | 0 | 0 | 0 | 4290373.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lake County
CLEARLAKE | 11319.52 |  | 6588.86 |  | 5618.2 |  | 38.91 |  | 8992.29 |  | -112481.43 |  | 0 |  | 0 | [11 empty] | 0 |  | 0
LAKE COUNTY | 59364.21 | 0 | 698128.18 | 0 | 709387.88 | 0 | 232048.98 | 0 | 70879.15 | 943679.53 | 40211.96 | 784282 | 86437.38 | 0 | 639419.25 | 0 | 61708.93 | 808835 | 26615.19 | 0 | 52320.33 | 0 | 88706.34 | 0 | 52689.93 | 0 | 45247.09 |  | 46397.77
LAKEPORT | [26 empty] | 0 |  | 0
Lake County Total | 70683.73 | 0 | 704717.04 | 0 | 715006.08 | 0 | 232087.89 | 0 | 79871.44 | 943679.53 | -72269.47 | 784282 | 86437.38 | 0 | 639419.25 | 0 | 61708.93 | 808835 | 26615.19 | 0 | 52320.33 | 0 | 88706.34 | 0 | 52689.93 | 0 | 45247.09 | 0 | 46397.77 | 0
Lassen County
LASSEN COUNTY | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lassen County Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Madera County
CHOWCHILLA | 0 |  | 0 |  | 1571.71 |  | -1571.71 |  | 335.38 |  | 473.87 |  | 5898.26 |  | 9469.22 |  | 21312.38 |  | 22623.94 |  | 19838.51 |  | 435676.63 |  | 62267.76 |  | 62654.32 |  | 14121.17
MADERA | -13686.3 | 1492305.5444 | 3628.03 | 0 | 2777.58 | 0 | 43945.6 | 0 | 50733.57 | 0 | 39705.11 | 0 | 32165.61 | 0 | 227369.65 | 0 | 2605936.62 | 0 | -72118.22 | 2983586.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
MADERA COUNTY | 0 | 0 | 1733.6 | 0 | 10353.18 | 0 | 111870.71 | 0 | 45010.24 | 0 | 874413.27 | 0 | 3076319.03 | 0 | -691475.35 | 0 | 50233.81 | 3382558 | 1505014.97 | 0 | 9886.85 | 0 | 216934.41 | 1533550.22 | 578448.17 | 0 | 3063361.88 |  | -187183.6 | 3246486.15
Madera County Total | -13686.3 | 1492305.5444 | 5361.63 | 0 | 14702.47 | 0 | 154244.6 | 0 | 96079.19 | 0 | 914592.25 | 0 | 3114382.9 | 0 | -454636.48 | 0 | 2677482.81 | 3382558 | 1455520.69 | 2983586.39 | 29725.36 | 0 | 652611.04 | 1533550.22 | 640715.93 | 0 | 3126016.2 | 0 | -173062.43 | 3246486.15
Marin County
BELVEDERE | 2988.33 | 0 | 12081.21 | 0 | 148076.21 | 0 | 322184.68 | 0 | -4983.55 | 122129 | 1676.83 | 0 | 419887.68 | 0 | 28065.33 | 0 |  | 463327 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0
CORTE MADERA | 39984.07 | 0 | 24722.48 | 0 | 1060364.11 | 0 | 7458.61 | 0 | 0 | 1231589.52 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0
FAIRFAX | [26 empty] | 0 |  | 0
LARKSPUR | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 1691.23 |  | 38944.68 |  | 181416.9
MARIN COUNTY | 2040421.35 | 0 | 757896.65 | 0 | 1119640.51 | 0 | 142927.45 | 0 | 1442325.75 | 4409610.81 | -2644 | 1544188 | 0 | 0 | 3621.89 | 0 | 7147 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
MILL VALLEY | 980205.39 | 0 | 788278.19 | 0 | 42028.02 | 0 | 0 | 3000582.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0
NOVATO | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 46.37 |  | 5786.69 |  | 1027.52 |  | 642.59 |  | 803.62 |  | 661.31 |  | 1198.46 |  | 60161.52
ROSS | [26 empty] | 0 |  | 0
SAN ANSELMO | 46140.53 | 0 | 11050.12 | 0 | 20314.23 | 0 | 198151.38 | 0 | 931471.06 | 0 | 221070.74 | 0 | -2570 | 0 | 0 | 0 | 0 | 1468753 | 503.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
SAN RAFAEL | 6533.45 | 0 | 433312.08 | 0 | 391.61 | 0 | 1381.94 | 444675.96 | 0 | 0 | -34663.5 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0
SAUSALITO | -92649.31 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [11 empty] | 0 |  | 0
TIBURON | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 46.9 |  | 2197.9 |  | 72040.29 |  | 94355.77 |  | 295.04
Marin County Total | 3023623.81 | 0 | 2027340.73 | 0 | 2390814.69 | 0 | 672104.06 | 3445258.62 | 2368813.26 | 5763329.33 | 185440.07 | 1544188 | 417317.68 | 0 | 31733.59 | 0 | 12933.69 | 1932080 | 1531.01 | 0 | 689.49 | 0 | 3001.52 | 0 | 74392.83 | 0 | 134498.91 | 0 | 241873.46 | 0
Mariposa County
MARIPOSA COUNTY | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mariposa County Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mendocino County
FORT BRAGG | [26 empty] | 0 |  | 0
MENDOCINO COUNTY | 35947.02 | 0 | 20070.02 | 0 | 21972.11 | 0 | 63719.84 | 0 | 699837.79 | 0 | 575322.34 | 0 | 1244264.03 | 0 | 1458464.19 | 0 | -386.34 | 4067720 | 21197.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
POINT ARENA | [26 empty] | 0 |  | 0
WILLITS | 1466.43 |  | 1081.4 |  | -6583.12 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [11 empty] | 0 |  | 0
Mendocino County Total | 37413.45 | 0 | 21151.42 | 0 | 15388.99 | 0 | 63719.84 | 0 | 699837.79 | 0 | 575322.34 | 0 | 1244264.03 | 0 | 1458464.19 | 0 | -386.34 | 4067720 | 21197.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Merced County
ATWATER | 0 | 0 | 0 | 0 | 0 | 0 | 89.72 | 0 | 56154.54 | 0 | 37790.19 | 0 | 15576.33 | 0 | 36099.08 | 0 | 3256102.41 | 0 | -104310.75 | 3286906.52 | -5465 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
DOS PALOS | [26 empty] | 0 |  | 0
GUSTINE | [26 empty] | 0 |  | 0
LIVINGSTON | [26 empty] | 0 |  | 0
LOS BANOS | 156037.38 | 0 | 851957.26 | 131963.7 | 77397.87 | 959318.81 | 0 | 0 | 6230.96 | 0 | 2517.09 | 0 | 289.26 | 0 | 312.77 | 0 | 315.85 | 0 | 2842.08 | 0 | 5481.24 | 0 | 122716.31 | 0 | 49912.28 | 0 | -185129.84 |  | 0
MERCED | 1450.4 | 0 | 58206.03 | 1510567.83 | 10721.75 | 0 | 20933.91 | 0 | 60366.78 | 0 | 60921.51 | 0 | 1982533.76 | 0 | 190045.76 | 0 | 27217.37 | 2167700 | 125398.9 | 0 | 1516639.51 | 1569890 | 0 | 0 | 0 | 0 | 0 |  | 0
MERCED COUNTY | 10869.48 | 0 | 5774.58 | 0 | 5475.66 | 0 | 118562.33 | 0 | 1580906.28 | 0 | 581921.7 | 0 | -261279.1 | 0 | 15088.49 | 2026094.22 | 15419.85 | 0 | 329575.45 | 0 | 3331917.11 | 0 | 570235.9 |  | 182173.31 | 4247347.82 | 242521.93 |  | 4526880.24
Merced County Total | 168357.26 | 0 | 915937.87 | 1642531.53 | 93595.28 | 959318.81 | 139585.96 | 0 | 1703658.56 | 0 | 683150.49 | 0 | 1737120.25 | 0 | 241546.1 | 2026094.22 | 3299055.48 | 2167700 | 353505.68 | 3286906.52 | 4848572.86 | 1569890 | 692952.21 | 0 | 232085.59 | 4247347.82 | 57392.09 | 0 | 4526880.24 | 0
Monterey County
CARMEL | [26 empty] | 0 |  | 0
DEL REY OAKS | [26 empty] | 0 |  | 0
GONZALES | [26 empty] | 0 |  | 0
GREENFIELD | [26 empty] | 0 |  | 0
KING CITY | -9128.31 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [11 empty] | 0 |  | 0
MARINA | 0 |  | 0 |  | 0 |  | 500.92 |  | 881.77 |  | 1182.47 |  | 362.03 |  | 257.92 |  | 260.5 |  | 273.01 |  | 347.37 |  | 323.93 |  | 465.65 |  | 375.49 |  | 277.43
MONTEREY | 1680.97 |  | 1712.1 |  | 1126.88 |  | 31329.02 |  | 38521.58 |  | 5431.02 |  | 9231.7 |  | 11666.17 |  | 10323.15 |  | 7121.02 |  | 13051.29 |  | -135384.48 |  | 0 |  | 0 |  | 0
MONTEREY COUNTY | 89465.23 | 0 | 34646.78 | 194765.92 | 1440.3 | 1707828.55 | 77104.45 | 0 | 15167.45 | 0 | 12953.27 | 0 | 25142.95 | 0 | 135763.39 | 0 | 19275.84 | 0 | 18385.8 | 0 | 61917.03 | 0 | 220069.06 | 0 | 81884.51 | 0 | 230532.89 |  | 2202695.06
PACIFIC GROVE | 251498.07 | 0 | 135137.48 | 0 | 23999.19 | 0 | 24.11 | 751389.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0
SALINAS | 490.83 | 917800.11 | 1719.95 | 0 | 5451.11 | 0 | 149217.18 | 0 | 611917.43 | 0 | 788100.73 | 0 | 1872545.28 | 0 | 2244847.56 | 0 | 1369502.86 | 0 | 0 | 0 | -40927 | 0 | 0 |  | 0 | 0 | 0 | 6760928.04 | 0
SAND CITY | [26 empty] | 0 |  | 0
SEASIDE | 21589.56 | 0 | 12399.99 | 0 | 7486.79 | 0 | 91297.36 | 0 | 115629.2 | 0 | 1918281.04 | 0 | 683740.28 | 0 | -6632 | 2678450 | 0 | 0 | 0 | 0 | 6021 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
SOLEDAD | [26 empty] | 0 |  | 0
Monterey County Total | 355596.35 | 917800.11 | 185616.3 | 194765.92 | 39504.27 | 1707828.55 | 349473.04 | 751389.03 | 782117.43 | 0 | 2725948.53 | 0 | 2591022.24 | 0 | 2385903.04 | 2678450 | 1399362.35 | 0 | 25779.83 | 0 | 40409.69 | 0 | 85008.51 | 0 | 82350.16 | 0 | 230908.38 | 6760928.04 | 2202972.49 | 0
Napa County
AMERICAN CANYON | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 1927.82 |  | 9364.15 |  | 14104.32
CALISTOGA | [26 empty] | 0 |  | 0
NAPA | 54257.66 |  | 187955.92 |  | 1232506.42 |  | 2289265.33 |  | -805215.58 |  | 0 |  | 0 |  | 0 |  | 0 |  | 44.95 |  | 46.14 |  | 109727.43 |  | 145417.19 |  | 73848.19 |  | 39072.22
NAPA COUNTY | 965.1354 | 0 | 11570.0297 | 0 | 13760.49 | 0 | 25305.6388 | 0 | 41690.9697 | 0 | 163203.4781 | 3008083 | 435192.0021 | 0 | 5316769.5358 | 0 | 11127586.7048 | 0 | 13284.0655 | 0 | -26103.03 | 15894933.58 | 0 | 0 | 0 | 0 | 0 |  | 0
ST HELENA | 70.0646 | 0 | -218.8997 | 0 | 0 | 0 | 3894.8612 | 0 | 3026.5803 | 0 | 11847.8519 | 0 | 31593.0179 | 0 | 385973.9942 | 0 | 807813.6652 | 0 | 964.3645 | 0 | -1894.97 | 1153902 | 0 | 0 | 0 | 0 | 0 |  | 0
YOUNTVILLE | [26 empty] | 0 |  | 0
Napa County Total | 55292.86 | 0 | 199307.05 | 0 | 1246266.91 | 0 | 2318465.83 | 0 | -760498.03 | 0 | 175051.33 | 3008083 | 466785.02 | 0 | 5702743.53 | 0 | 11935400.37 | 0 | 14293.38 | 0 | -27951.86 | 17048835.58 | 109727.43 | 0 | 147345.01 | 0 | 83212.34 | 0 | 53176.54 | 0
Nevada County
GRASS VALLEY |  | 970238.61 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0
NEVADA CITY | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 34231.55 |  | 34920.61 |  | 8391.56
NEVADA COUNTY | 7459.43 | 0 | 4436.42 | 0 | -104751.77 | 0 | 3550.51 | 0 | 14193.97 | 0 | 5100.42 | 0 | 4322.11 | 0 | 6075.88 | 0 | 58673.83 | 0 | 83621.57 | 0 | 2715256.45 | 0 | 417797.1 |  | 89229.64 | 2938685.84 | 99925.34 |  | 1638170.11
Nevada County Total | 7459.43 | 970238.61 | 4436.42 | 0 | -104751.77 | 0 | 3550.51 | 0 | 14193.97 | 0 | 5100.42 | 0 | 4322.11 | 0 | 6075.88 | 0 | 58673.83 | 0 | 83621.57 | 0 | 2715256.45 | 0 | 417797.1 | 0 | 123461.19 | 2938685.84 | 134845.95 | 0 | 1646561.67 | 0
Placer County
AUBURN | 0 | 0 | 0 | 0 | 0 | 0 | 27895.22 | 0 | 1459237.8 | 0 | 61179.68 | 0 | -3179.52 | 0 | 1542.22 | 0 |  | 0 |  | 0 |  | 1544684.4 |  | 0 |  | 0 | 0 |  | 0
COLFAX | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 386.97 |  | -386.97 |  | 0 |  | 0 |  | 0 |  | 0
LINCOLN | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | -7990.49 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2733.42 |  | 115914.07 |  | 39988.14
LOOMIS | [26 empty] | 72144.39 |  | 8589.67
PLACER COUNTY | 82174.65 | 0 | 66591.87 | 0 | 53911.49 | 0 | 66300.82 | 0 | 256703.6 | 0 | 2388437.46 | 0 | 369463.33 | 0 | 3734887.27 | 0 | 4794724.31 | 2761892 | 601348.86 | 0 | -30783.71 | 0 | 741.62 | 9652706.02 | 0 | 0 | 0 |  | 0
ROCKLIN | [26 empty] | 0 |  | 0
ROSEVILLE | [26 empty] | 0 |  | 0
Placer County Total | 82174.65 | 0 | 66591.87 | 0 | 53911.49 | 0 | 94196.04 | 0 | 1715941.4 | 0 | 2449617.14 | 0 | 366283.81 | 0 | 3728439 | 0 | 4794724.31 | 2761892 | 601735.83 | 0 | -31170.68 | 1544684.4 | 741.62 | 9652706.02 | 2733.42 | 0 | 188058.46 | 0 | 48577.81 | 0
Plumas County
PLUMAS COUNTY | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1376.34 | 0 | 1735.25 | 0 | 3247.54 | 0 | 4294.13 | 0 | 61015.8 | 0 | 42712.39 | 0 | 1410480.3 | 0 | 14775.87 | 1555870.62 | 0 | 0 | 0 |  | 0
Plumas County Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1376.34 | 0 | 1735.25 | 0 | 3247.54 | 0 | 4294.13 | 0 | 61015.8 | 0 | 42712.39 | 0 | 1410480.3 | 0 | 14775.87 | 1555870.62 | 0 | 0 | 0 | 0 | 0 | 0
Sacramento County
ISLETON | [26 empty] | 0 |  | 0
SACRAMENTO COUNTY | [16 empty] | 0 |  | 0
Sacramento County Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
San Benito County
HOLLISTER | [26 empty] | 0 |  | 0
SAN BENITO COUNTY
SAN JUAN BAUTISTA | [16 empty] | 0 |  | 0 | [7 empty] | 0 |  | 0
San Benito County Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
San Francisco County
SAN FRANCISCO | 24401979.18 | 3409132.8922 | 43157132.62 | 13091079.64 | 17531285.7 | 4319533.2 | 6369521.29 | 29440198.08 | 1593892.45 | 11097086.6 | -445778.23 | 60817838.34 | -103589.92 | 2920534 | 0 | 42816923.88 | 54962.7 | 0 | 105.71 | 7097063.45 | 0 | 0 | 0 | 0 | 10775.72 | 0 | 863.64 |  | 0
San Francisco County Total | 24401979.18 | 3409132.8922 | 43157132.62 | 13091079.64 | 17531285.7 | 4319533.2 | 6369521.29 | 29440198.08 | 1593892.45 | 11097086.6 | -445778.23 | 60817838.34 | -103589.92 | 2920534 | 0 | 42816923.88 | 54962.7 | 0 | 105.71 | 7097063.45 | 0 | 0 | 0 | 0 | 10775.72 | 0 | 863.64 | 0 | 0 | 0
San Joaquin County
ESCALON | [26 empty] | 0 |  | 0
LATHROP | 463301.11 | 0 | 50104.28 | 0 | 1434.03 | 520569.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0
MANTECA | [26 empty] | 0 |  | 0
RIPON | 50514.53 | 0 | 411783.2 | 0 | 390844.76 | 0 | 3791.41 | 866091.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0
SAN JOAQUIN COUNTY | 666515.89 | 0 | 15558.09 | 1165390.96 | -1031.63 | 0 | 11068.05 | 0 | 0 | 0 | 3705.73 | 994499 | 12588.51 | 0 | 20802.17 | 0 | 248282.45 | 0 | 39526.53 | 0 | 6746070.29 | 0 | 100990.36 |  | 0 | 7303864.04 | 0 |  | 0
STOCKTON | 216899.38 | 386955.72 | 652769.53 | 1564389.76 | 2271820.77 | 861986.69 | 542169.2 | 486964.2 | 1179826.48 | 3384961.16 | 1727349.17 | 0 | 387838.07 | 0 | -25794.5 | 3406041.39 | 2483.53 | 0 | 2603.01 | 0 | -37473.35 | 0 | 0 | 0 | 0 | 0 | 89739.83 |  | 96435.02
TRACY | 0 | 242942.7034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91059.05 | 0 | 153717.2 | 0 | 477757.46 | 0 | 20632.46 | 749975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
San Joaquin County Total | 1397230.91 | 629898.4234 | 1130215.1 | 2729780.72 | 2663067.93 | 1382556.16 | 557028.66 | 1353055.6 | 1179826.48 | 3384961.16 | 1822113.95 | 994499 | 554143.78 | 0 | 472765.13 | 3406041.39 | 271398.44 | 749975 | 42129.54 | 0 | 6708596.94 | 0 | 100990.36 | 0 | 0 | 7303864.04 | 89739.83 | 0 | 96435.02 | 0
San Luis Obispo County
ARROYO GRANDE | 5942.65 | 727377.37 | -8587.81 | 0 | 4173.71 | 0 | 5205.51 | 0 | 13507.39 | 0 | 13047.85 | 0 | 32848.02 | 0 | 39883.81 | 0 | 2026149.48 | 0 | 49666.05 | 0 | 54207.94 | 2312479.78 | 822.5 | 0 | 1110.51 | 0 | 987.98 |  | 702.78
ATASCADERO | [26 empty] | 0 |  | 0
GROVER BEACH | 15443.85 | 0 | 7272.63 | 0 | 8454.77 | 0 | 49064.28 | 0 | 152292.18 | 0 | 480627.81 | 0 | 397079.99 | 0 | -909.95 | 1169785.93 | 194.46 | 0 | 203.79 | 0 | -2775.85 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
MORRO BAY | -209473.67 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 16969.61 |  | 15962.56 |  | 161976.25 |  | 119763.59 |  | -314672.01 |  | 0
PASO ROBLES | 0 | 0 | 57.21 | 0 | 3.52 | 0 | 485.76 | 0 | -546.52 | 0 | 2726.07 | 0 | 241.87 | 0 | 261.51 | 0 | 14062.32 | 0 | 1376273.36 | 0 | 1246519.08 | 0 | 0 | 2720690.18 | 0 | 0 | 0 |  | 0
PISMO BEACH | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 1613.96 |  | 80049.49 |  | 102154.25 |  | 234319.19 |  | 1609873.79 |  | 3470078.98
SAN LUIS OBISPO | 171333.5111 | 0 | 8848.2647 | 0 | -1400.3646 | 0 | 113517.8575 | 0 | 1639937.5125 | 0 | 1072685.7211 | 0 | 674633.8011 | 0 | 1808996.2141 | 0 | 515612.6248 | 2221577 | 0 | 3464321.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
SAN LUIS OBISPO COUNTY | -8884.4311 | 0 | 14408.7653 | 1682417.54 | 476.2646 | 0 | 114545.0925 | 0 | 842805.0175 | 0 | 682909.1789 | 0 | 725073.9989 | 0 | 1148650.5959 | 937277 | 257112.4752 | 1045448 | 47945.37 | 1630269.11 | 1172272.22 | 0 | 1796648.06 | 2085205.56 | 3891421.96 | 0 | 386811.32 | 5318373.62 | 0
San Luis Obispo County Total | -25638.09 | 727377.37 | 21999.06 | 1682417.54 | 11707.9 | 0 | 282818.5 | 0 | 2647995.58 | 0 | 2251996.63 | 0 | 1829877.68 | 0 | 2996882.18 | 2107062.93 | 2813131.36 | 3267025 | 1492672.14 | 5094590.98 | 2566235.44 | 2312479.78 | 2061601.06 | 4805895.74 | 4246615.25 | 0 | 1683001.08 | 5318373.62 | 3470781.76 | 0
San Mateo County
ATHERTON | [26 empty] | 0 |  | 0
BELMONT | 106372.7419 |  | 62940.6048 |  | 19844.11 |  | 860150.5867 |  | 122810.1592 |  | 131512.6806 |  | 110685.3863 |  | -383175.7418 |  | 86925.9275 |  | 94854.1289 |  | 147088.76 |  | 265045.68 |  | 1506569 |  | 1386737.5306 |  | 0 | 4435363.48
BRISBANE | [26 empty] | 0 |  | 0
BURLINGAME | [26 empty] | 0 |  | 0
COLMA | 3355.641 | 0 | 1289.567 | 0 | 6252.151 | 0 | 161681.883 | 0 | 41851.771 | 0 | 2555.339 | 0 | 0 | 225557 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0
DALY CITY | 14093.6922 | 0 | 20948.4914 | 0 | 27222.8942 | 0 | 679233.3886 | 0 | 320289.7882 | 0 | 60395.9238 | 0 | 32988.88 | 1066920 | 68744.5 | 0 | 34997.53 | 0 | 5269471.77 | 0 | 651544.86 | 0 | 17.88 | 6011029.78 | 200.73 | 0 | 736.67 |  | 4224.51
EAST PALO ALTO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19201.68 | 0 | 39660.06 | 0 | 640699.07 | 0 | 1180146.6 |  | 0 |  | 0 | 1920415.41
FOSTER CITY | [26 empty] | 0 |  | 0
HALF MOON BAY | 71633.64 | 0 | 42769.08 | 0 | 609553.8 | 0 | 70076.72 | 0 | 9556.13 | 0 | 0 | 0 | 0 | 845737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17971.87 | 0 | 164523.62 | 0 | 1040764.4 |  | -12430.64
HILLSBOROUGH | 8330.43 | 0 | 13477.665 | 0 | 2960.5154 | 0 | 1552553.4296 | 0 | 474629.02 | 0 | 10241.42 | 0 | -4262.87 | 0 | 0 | 2058774.42 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0
MENLO PARK | [26 empty] | 0 |  | 0
MILLBRAE | [26 empty] | 0 |  | 0
PACIFICA | -188428.48 | 0 | 266910.5 | 0 | 51450.23 | 401204.26 | 0 | 0 | 525.46 | 165487.87 | 46.62 | 0 | 9042.1 | 0 | 390532.33 | 0 | 4832710.12 | 0 | 160324.92 | 0 | 1307.51 | 0 | 0 |  | 634.95 | 0 | 104964.22 |  | 472.11 | 5555654.92
PORTOLA VALLEY | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 5378.76 |  | 26314.23 |  | 12565.48 |  | 4165.59 |  | 3981.53 |  | 5453.28 |  | 5226.65
REDWOOD CITY | 0 | 0 | 0 | 1218971.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1747.79 | 0 | 33405.28 | 0 | 81219.24 | 0 | 76088.93 | 0 | 86380.91 | 0 | 102954.86 | 0 | 2301843.2 |  | 3158235.97
SAN BRUNO | [26 empty] | 0 |  | 0
SAN CARLOS | 730315.48 | 0 | 106727.01 | 0 | 4558.87 | 0 | 0 | 2934893.06 | 0 | 0 | -41771.76 | 0 | 0 | 0 | 24757.08 | 0 | 514102.37 | 0 | 2439738.82 | 0 | 13993.35 | 0 | 0 | 3072449.62 | 0 | 0 | 0 |  | 0
SAN MATEO | 0 | 354040.51 | 0 | 0 | 0 | 0 | 1853.51 | 0 | 82049.61 | 0 | 9006.16 | 0 | 8496.25 | 0 | 58624.44 | 0 | 26918.1 | 0 | 53296.85 | 0 | 528193.2 | 0 | 2209143.98 |  | 31405.95 | 0 | 24854.91 | 3088685.06 | 35.39
SAN MATEO COUNTY | 63236.9049 | 0 | 37270.6418 | 0 | 44715.6094 | 0 | 979092.1921 | 0 | 253551.1516 | 0 | 57926.8666 | 0 | 40959.2937 | 946137 | 252763.3218 | 0 | 113473.1525 | 0 | 735329.5411 | 0 | 99193.7 | 833659.07 | 250130.68 | 0 | 801695.73 | 0 | 769537.4094 |  | 49579.37 | 2044349.42
SOUTH SAN FRANCISCO | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 524.42 |  | 157.7 |  | 157462.52 |  | 1527617.15
WOODSIDE | [26 empty] | 0 |  | 0
San Mateo County Total | 808910.05 | 354040.51 | 552333.56 | 1218971.72 | 766558.18 | 401204.26 | 4304641.71 | 2934893.06 | 1305263.09 | 165487.87 | 229913.25 | 0 | 197909.04 | 3084351 | 413993.72 | 2058774.42 | 5647911.24 | 0 | 8879751.18 | 0 | 1569635.85 | 833659.07 | 3474080.08 | 9083479.4 | 3792270.67 | 0 | 5792354.14 | 3088685.06 | 4732960.51 | 13955783.23
Santa Barbara County
BUELLTON | [26 empty] | 0 |  | 0
GUADALUPE | [26 empty] | 0 |  | 0
SANTA BARBARA COUNTY | 6624.61 | 0 | 7283.11 | 0 | 19103.36 | 0 | 131061.46 | 0 | 45041.14 | 0 | 50257.94 | 0 | 305126.04 | 0 | 795856.05 | 0 | 238.98 | 1337063 | 250.55 | 0 | 448.46 | 0 | 12120.48 | 0 | 77634.14 | 0 | 200026.87 |  | 60970.58
SANTA MARIA | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 129.73 |  | 11385.18 |  | 890.48 |  | 4067.34
SOLVANG | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 4645.38 |  | 11339.04 |  | 172528.31 |  | 10102.51
Santa Barbara County Total | 6624.61 | 0 | 7283.11 | 0 | 19103.36 | 0 | 131061.46 | 0 | 45041.14 | 0 | 50257.94 | 0 | 305126.04 | 0 | 795856.05 | 0 | 238.98 | 1337063 | 250.55 | 0 | 448.46 | 0 | 16895.59 | 0 | 100358.36 | 0 | 373445.66 | 0 | 75140.43 | 0
Santa Clara County
CAMPBELL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8504.94 | 0 | 313141.12 | 0 | 202821.91 | 0 | 5618123.15 | 0 | 5910.05 | 0 | 107725.92 | 6429730.09 | 0 | 0 | 0 | 0 | 0 |  | 0
CUPERTINO | 29723.1424 | 0 | 9774.4448 | 0 | 4751.0848 | 0 | 12360.2688 | 0 | 23560.3136 | 0 | 31037.7536 | 0 | 450100.8768 | 0 | 435447.104 | 0 |  | 983264 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0
GILROY | [26 empty] | 0 |  | 0
LOS ALTOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 123199.88 | 0 | 733887.53 | 0 | 1472717.62 | 0 | -1510.21 | 0 | 0.36 | 2250164 | 17619.95 | 0 | 37658.14 | 0 | 1537121.31 | 0 | -5511.45 | 1630968.37 | 0 |  | 0
LOS ALTOS HILLS | 2986.36 | 0 | 30957.93 | 0 | 26867.94 | 0 | 758962.24 | 0 | -8797.61 | 815900.21 | -2712.93 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0
LOS GATOS | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 314.21 |  | 66960.52 |  | 75698 |  | 15805.62
MILPITAS | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 17276.81 |  | 167618.886 |  | 231203.048
MONTE SERENO | [26 empty] | 0 |  | 0
MORGAN HILL | 0 | 0 | 0 | 0 | 1393.73 | 0 | 121548.16 | 0 | 16374.08 | 0 | 17555.28 | 0 | 36587.25 | 0 | 82665.61 | 0 | 27392.41 | 0 | 65158.17 | 0 | 39269.11 | 0 | 1983123.87 | 0 | 32493.13 | 2372458.8 | 0 |  | 0
MOUNTAIN VIEW | 7794.27 | 0 | 8920.82 | 0 | 72587.61 | 0 | 88682.16 | 0 | 58507.06 | 0 | 255340.8 | 0 | 1440683.91 | 0 | 1358961.33 | 0 | 5772.25 | 0 | 6555.29 | 0 | -296.48 | 2986716.5 | 38281.9 | 0 | 112146.44 | 0 | 73973.26 |  | 25929.18
SAN JOSE | 1893949.1176 | 720044.6 | 450393.5252 | 1045126.85 | 1936179.6952 | 2174100.57 | 3931563.6001 | 647311.72 | 6508587.9759 | 0 | 2117034.8514 | 0 | 1137297.596 | 0 | 1227660.9344 | 4992592.56 | 8747611.5183 | 6200000 | 9024601.1148 | 4135751.22 | 3753466.86 | 12804582.23 | 311005.82 | 10152258.13 | 490005.78 | 0 | 2582142.64 |  | 67388.87
SANTA CLARA COUNTY | 0 | 0 | 0 | 0 | 0 | 0 | 16904.6811 | 0 | 3842.9505 | 0 | 2294.055 | 0 | 3665.0772 | 0 | 6585.3816 | 0 | 11798.0217 | 0 | 13409.4752 | 0 | 828008.51 | 0 | 1179.96 | 886235.17 | 21605.92 | 0 | 86922.374 |  | 194051.762
SARATOGA | [26 empty] | 0 |  | 0
SUNNYVALE | 0 | 143963.1 | 0 | 0 | 0 | 0 | 0 | 0 | 4431.46 | 0 | 7888.59 | 0 | 1630.83 | 0 | 3637.5 | 0 | 248808.84 | 0 | 120974.22 | 0 | 4328261.33 | 0 | 325132.3 |  | 105712.02 | 4906621.16 | 70090.74 |  | 126806.01
Santa Clara County Total | 1934452.89 | 864007.7 | 500046.72 | 1045126.85 | 2041780.06 | 2174100.57 | 4930021.11 | 647311.72 | 6729706.11 | 815900.21 | 3170830.87 | 0 | 4855824.28 | 0 | 3316269.56 | 4992592.56 | 14659506.55 | 9433428 | 9254228.27 | 4135751.22 | 9094093.39 | 22221028.82 | 4196159.37 | 11038493.3 | 840689.17 | 8910048.33 | 3056445.9 | 0 | 661184.49 | 0
Santa Cruz County
CAPITOLA | -11692.91 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 161.59 |  | 55502.05 |  | 51152.29
SANTA CRUZ | 118045.51 | 0 | 361994.85 | 3091119.09 | 3010593.86 | 0 | 223497.17 | 0 | 4293.04 | 0 | 1876.6 | 0 | 0 | 0 | 0 | 3897340.59 | 22450.87 | 0 | 36765.86 | 0 | 18579.66 | 0 | 132208.23 | 0 | 164034.43 | 0 | 85556.56 |  | 29656.68
SANTA CRUZ COUNTY | 680700.57 | 0 | 593360.18 | 0 | 3778.46 | 1594312.61 | 71905.11 | 0 | 11537.08 | 0 | 13242.14 | 0 | 15703.37 | 0 | 34727.85 | 0 | 58327.68 | 0 | 92002.98 | 0 | 53083.01 | 0 | 389722.46 | 0 | 1278996.83 | 0 | 23100.78 | 2023838.48 | 0
SCOTTS VALLEY | [26 empty] | 0 |  | 0
WATSONVILLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6094.88 | 0 | 23091.74 | 0 | 64268.41 | 0 | 1417255.38 |  | -14555.63 | 0 | 0 | 1368203.78 | 0
Santa Cruz County Total | 787053.17 | 0 | 955355.03 | 3091119.09 | 3014372.32 | 1594312.61 | 295402.28 | 0 | 15830.12 | 0 | 15118.74 | 0 | 15703.37 | 0 | 34727.85 | 3897340.59 | 86873.43 | 0 | 151860.58 | 0 | 135931.08 | 0 | 1939186.07 | 0 | 1428637.22 | 0 | 164159.39 | 3392042.26 | 80808.97 | 0
Shasta County
ANDERSON | 0 | 0 | 0 | 0 | 0 | 0 | 540.29 | 0 | 87403.25 | 0 | 75383.12 | 0 | 55612.04 | 0 | 64705.7 | 0 | 2992258.77 | 0 | 44930.01 | 0 | -213 | 3333295.26 | 0 | 0 | 0 | 0 | 0 |  | 0
SHASTA COUNTY | 2316.52 | 1177635.1 | 716451.57 | 0 | 2960.54 | 709869.62 | 172670.71 | 275197.53 | 6689.81 | 0 | 3319.06 | 193839 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0
SHASTA LAKE | [26 empty] | 0 |  | 0
Shasta County Total | 2316.52 | 1177635.1 | 716451.57 | 0 | 2960.54 | 709869.62 | 173211 | 275197.53 | 94093.06 | 0 | 78702.18 | 193839 | 55612.04 | 0 | 64705.7 | 0 | 2992258.77 | 0 | 44930.01 | 0 | -213 | 3333295.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sierra County
SIERRA COUNTY | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sierra County Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Siskiyou County
SISKIYOU COUNTY | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Siskiyou County Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Solano County
BENICIA | [26 empty] | 0 |  | 0
DIXON | [26 empty] | 0 |  | 0
FAIRFIELD | 605.99 | 1451380.782 | 0 | 0 | 717.01 | 0 | 0 | 0 | 491.42 | 0 | 2667.95 | 0 | 982.73 | 0 | 364.97 | 0 | 368.6 | 0 | 386.34 | 0 | 472.1 | 0 | 456.85 | 0 | 492.85 | 0 | 518.52 |  | 226.44
RIO VISTA | [26 empty] | 0 |  | 0
SOLANO COUNTY
SUISUN CITY | [26 empty] | 0 |  | 0
VACAVILLE | 171301.44 | 0 | 241750.37 | 0 | 48314.55 | 834725.81 | 50558.81 | 0 | 0 | 0 | -91717.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26603.53 | 0 | 714942.3 | 0 | 0 | 708335.83 | 0 | 0 | 0 |  | 0
VALLEJO | 15077.49 | 0 | 42135.12 | 0 | 180990.42 | 0 | 182483.61 | 0 | 834.11 | 0 | 0 | 491493 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0
Solano County Total | 186984.92 | 1451380.782 | 283885.49 | 0 | 230021.98 | 834725.81 | 233042.42 | 0 | 1325.53 | 0 | -89049.93 | 491493 | 982.73 | 0 | 364.97 | 0 | 368.6 | 0 | 26989.87 | 0 | 715414.4 | 0 | 456.85 | 708335.83 | 492.85 | 0 | 518.52 | 0 | 226.44 | 0
Sonoma County
CLOVERDALE | [26 empty] | 0 |  | 0
COTATI | [26 empty] | 0 |  | 0
HEALDSBURG | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 421497.7 | 0 | -108756.57 | 0 | 0 | 81345.13 | 0 | 0 | 0 |  | 0
PETALUMA | 1640.03 | 0 | 5426.4 | 0 | 5408.91 | 0 | 62313.85 | 0 | 869797.1 | 0 | 1702050.46 | 0 | 48909.06 | 0 | 672577.58 | 2622095.72 | 1018562.72 | 0 | 2522.07 | 0 | 1317.71 | 1767994.75 | 1516.88 | 0 | 1549.75 | 0 | 1649.86 |  | 1201.69
ROHNERT PARK | 1511.53 | 0 | 1339.09 | 0 | 1671.14 | 0 | 368.51 | 0 | 2788.23 | 0 | 11711.63 | 0 | 4460.05 | 0 | 4821.99 | 0 | 4870.01 | 0 | 34884.32 | 0 | 1371971.26 | 0 | 6044.37 | 991808.18 | 6594.09 | 0 | 39792.6 |  | 47992.83
SANTA ROSA | 98364.07 | 0 | 57901.13 | 0 | -33253.33 | 1019413.14 | 4141.29 | 0 | 27818.17 | 0 | 16945.4 | 0 | 19996.42 | 0 | 749515.73 | 0 | -74407.08 | 0 | 5764951.55 | 0 | 2249383.61 | 0 | 20547.56 | 8853447.51 | 18851.87 | 0 | 148233.1488 |  | 39447.9272
SEBASTOPOL | [26 empty] | 0 |  | 0
SONOMA | 26331.061 | 0 | 56996.9372 | 0 | 27049.258 | 0 | 46800.6226 | 0 | 1152665.923 | 0 | 440406.3052 | 0 | -7162.1014 | 0 | 0 | 1741796.78 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0
SONOMA COUNTY | -156714.881 | 0 | 54754.6628 | 0 | 117246.902 | 1007477.46 | 63720.0774 | 0 | 981690.877 | 0 | 2453280.8348 | 0 | 4832031.7114 | 0 | -155830.35 | 400000 | 1790.13 | 7371678 | 2147.67 | 0 | 2262.7 | 0 | 2384.13 | 0 | 5339.5 | 0 | 28117.3212 |  | 16489.1628
WINDSOR | [26 empty] | 0 |  | 0
Sonoma County Total | -28868.19 | 0 | 176418.22 | 0 | 118122.88 | 2026890.6 | 177344.35 | 0 | 3034760.3 | 0 | 4624394.63 | 0 | 4898235.14 | 0 | 1271084.95 | 4763892.5 | 950815.78 | 7371678 | 6226003.31 | 0 | 3516178.71 | 1767994.75 | 30492.94 | 9926600.82 | 32335.21 | 0 | 217792.93 | 0 | 105131.61 | 0
Stanislaus County
NEWMAN | 0 | 0 | 0 | 0 | 4569.9852 | 0 | 162115.1448 | 0 | 215877.54 | 312071.45 | 42873.36 | 0 | 14438.2 | 0 | 17711.19 | 0 | 23531.87 | 0 | 24573.01 | 0 | 18648.58 | 0 | 18049.9 | 0 | 19446.69 | 0 | 19346.22 |  | 9975.46
OAKDALE | 859781.14 | 0 | 5416.26 | 0 | 0 | 1370320.68 | 5330 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24952.17 | 0 | 1951596.08 | 0 | -89383.38 | 0 | 31559.86 | 1735838.73 | 0 |  | 0
RIVERBANK | 1614.9806 | 0 | -435.6206 | 0 | 1825.401 | 0 | 92266.8864 | 0 | 38768.2575 | 0 | 1063758.6776 | 0 | 1511658.2834 | 0 | -462262.0277 | 0 | 275768.6211 | 0 | 0 | 2451533.41 | 0 | 0 | 0 | 0 | 353074.72 | 0 | 0 |  | 0
STANISLAUS COUNTY | 367.9194 | 0 | 2383.9206 | 0 | 13537.7238 | 0 | 5414.8988 | 0 | 8832.0525 | 0 | 242341.8824 | 0 | 344380.8466 | 0 | -105310.9623 | 0 | 62824.6689 | 0 | 0 | 558500 | 0 | 0 | 0 | 0 | 80436.28 | 0 | 0 |  | 0
Stanislaus County Total | 861764.04 | 0 | 7364.56 | 0 | 19933.11 | 1370320.68 | 265126.93 | 0 | 263477.85 | 312071.45 | 1348973.92 | 0 | 1870477.33 | 0 | -549861.8 | 0 | 362125.16 | 0 | 49525.18 | 3010033.41 | 1970244.66 | 0 | -71333.48 | 0 | 484517.55 | 1735838.73 | 19346.22 | 0 | 9975.46 | 0
Sutter County
LIVE OAK | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 7020.07 |  | 362938.65 |  | 6283833.84
SUTTER COUNTY | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 63189.12 |  | 95664.47 |  | 24466.55 |  | 651328.76
YUBA CITY | 15267.48 | 0 | 15625.27 | 0 | 10896.21 | 207406.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46.05 | 0 | 9073.2 | 0 | 37129.94 | 0 | 58649.05 | 0 | 546625.15 | 0 | 1180161.88 |  | -18753.93 | 1726573 | 2.56
Sutter County Total | 15267.48 | 0 | 15625.27 | 0 | 10896.21 | 207406.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46.05 | 0 | 9073.2 | 0 | 37129.94 | 0 | 58649.05 | 0 | 609814.27 | 0 | 1282846.42 | 0 | 368651.27 | 1726573 | 6935165.16 | 0
Tehama County
CORNING | 4046.87 | 888092.1134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0
RED BLUFF | [26 empty] | 0 |  | 0
TEHAMA | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [11 empty] | 0 |  | 0
TEHAMA COUNTY | 1029.69 |  | -246.52 |  | 384.18 |  | 103.28 |  | 1725.81 |  | 7724.28 |  | 4710.51 |  | -19027.65 |  | 0 |  | 0 | [7 empty] | 0 |  | 0
Tehama County Total | 5076.56 | 888092.1134 | -246.52 | 0 | 384.18 | 0 | 103.28 | 0 | 1725.81 | 0 | 7724.28 | 0 | 4710.51 | 0 | -19027.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Trinity County
TRINITY COUNTY | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Trinity County Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tulare County
DINUBA | [16 empty] | 4350.89 |  | 5822.57 |  | 13058.28 |  | 11928.8 |  | 14942.84 |  | 9579.84 |  | 8836.22
TULARE COUNTY
Tulare County Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4350.89 | 0 | 5822.57 | 0 | 13058.28 | 0 | 11928.8 | 0 | 14942.84 | 0 | 9579.84 | 0 | 8836.22 | 0
Tuolomne County
SONORA | [26 empty] | 0 |  | 0
TUOLUMNE COUNTY | 0 | 0 | 7825.68 | 0 | 5038.09 | 0 | 43630.35 | 0 | 87979.18 | 0 | 37405.21 | 0 | 107954.42 | 0 | 1792180.17 | 0 | 2604.91 | 2053328 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Tuolomne County Total | 0 | 0 | 7825.68 | 0 | 5038.09 | 0 | 43630.35 | 0 | 87979.18 | 0 | 37405.21 | 0 | 107954.42 | 0 | 1792180.17 | 0 | 2604.91 | 2053328 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yolo County
DAVIS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38309.04 | 0 | 181594.26 | 0 | 1463807.24 | 0 | 2918.73 | 0 | 0 | 1717193.27 | 0 | 0 | 0 |  | 0
WEST SACRAMENTO | 155125.94 | 0 | 5145.72 | 909130.76 | 115.11 | 830239.12 | 139035.43 | 0 | 1505487.97 | 0 | 184475.86 | 0 | 35583.19 | 0 | 0 | 1835344.56 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0
WINTERS | [26 empty] | 336.62 |  | 50556.16
WOODLAND | 31691.65 | 0 | 171680.23 | 0 | 18136.19 | 221351.79 | 60187.84 | 0 | 516430.41 | 0 | 753779.07 | 0 | 21017.05 | 0 | 4902.3 | 0 | -6422.49 | 0 | 0 | 0 | 0 | 1292764.29 | 0 | 0 | 0 | 0 | 0 |  | 0
YOLO COUNTY | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3913.77 | 0 | 8480.31 | 0 | 1418193.09 | 0 | 458647.31 | 0 | 1240.89 | 0 | 0 | 1891504.37 | 0 | 0 | 0 | 0 | 0 |  | 0
Yolo County Total | 186817.59 | 0 | 176825.95 | 909130.76 | 18251.3 | 1051590.91 | 199223.27 | 0 | 2021918.38 | 0 | 942168.7 | 0 | 65080.55 | 0 | 1461404.43 | 1835344.56 | 633819.08 | 0 | 1465048.13 | 0 | 2918.73 | 3184268.66 | 0 | 1717193.27 | 0 | 0 | 336.62 | 0 | 50556.16 | 0
Yuba County
MARYSVILLE | [26 empty] | 0 |  | 0
WHEATLAND | [26 empty] | 0 |  | 0
YUBA COUNTY | 1254.33 | 0 | 1311.96 | 0 | -17360.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 297.01 | 0 | 92725.51 | 0 | 937523.51 | 0 | 3511779.31 | 0 | 2637.91 |  | 0 | 4616250.25 | 0 |  | 0
Yuba County Total | 1254.33 | 0 | 1311.96 | 0 | -17360.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 297.01 | 0 | 92725.51 | 0 | 937523.51 | 0 | 3511779.31 | 0 | 2637.91 | 0 | 0 | 4616250.25 | 0 | 0 | 0 | 0
Other Expenditures | [26 empty] | 13568.87 |  | 614280.58
OTHER EXPENDITURES | 0 |  | 0 |  | 0 |  | -43130.9 |  | -73960.71 |  | -1461342.12 |  | -1441926.76 |  | -78318.33 |  | 5429.14 |  | 264395.02 |  | 445355.87 |  | 1248.54 |  | -8497.8 |  | 13568.87 |  | 614280.58
Other Expenditures Total | 0 | 0 | 0 | 0 | 0 | 0 | -43130.9 | 0 | -73960.71 | 0 | -1461342.12 | 0 | -1441926.76 | 0 | -78318.33 | 0 | 5429.14 | 0 | 264395.02 | 0 | 445355.87 | 0 | 1248.54 | 0 | -8497.8 | 0 | 13568.87 | 0 | 614280.58 | 0
PG&E Total | 41998164.94 | 24816732.3753 | 68357381.33 | 39141800.57 | 45384718.92 | 25217323.61 | 39915726.01 | 41150595.12 | 41159047.55 | 36424048.74 | 36610157.64 | 85343493.34 | 33628353.71 | 10921099 | 52426103.48 | 97944054.88 | 69378397.01 | 50416996 | 41116964.74 | 47904229.57 | 41885295.26 | 69560883.91 | 31123071.61 | 67021142.39 | 28255336.39 | 55236617.26 | 32930368.3 | 35440238.72 | 46977527.91 | 24273089.14

## Credits Redeemed
Pacific Gas and Electric Company data for R.17-05-010 submitted on 4/17/2020; Note: Data provide for 1993-2019 only
(VIII.) Community Rule 20 A Credits Redeemed (Nominal Terms)
Rule 20A Community | County | Is the Community a DAC? | Number of Overhead Line Miles Converted to Underground | Number of Credits Redeemed | Rank
| Name | Yes/No/Unsure | Miles | Nominal $ | Number
ALAMEDA COUNTY | ALAMEDA | Unsure |  | 15984518.04 | 10
ALBANY | ALAMEDA | No |  | 4042169.09 | 58
BERKELEY | ALAMEDA | No |  | 16254558.1 | 9
DUBLIN | ALAMEDA | No |  | 2119194.2 | 92
EMERYVILLE | ALAMEDA | No |  | 485487 | 165
FREMONT | ALAMEDA | No |  | 12702851.15 | 15
HAYWARD | ALAMEDA | No |  | 19667522.16 | 6
LIVERMORE | ALAMEDA | No |  | 4637039.64 | 53
NEWARK | ALAMEDA | No |  | 1763151 | 107
OAKLAND | ALAMEDA | No |  | 59290181.62 | 2
PLEASANTON | ALAMEDA | No |  | 4533757.03 | 54
SAN LEANDRO | ALAMEDA | No |  | 6217834.8 | 39
UNION CITY | ALAMEDA | No |  | 3467613.81 | 64
AMADOR CITY | AMADOR | Yes |  | 30301 | 207
AMADOR COUNTY | AMADOR | Unsure |  | 2143897.55 | 89
JACKSON | AMADOR | Yes |  | 465191 | 166
BUTTE COUNTY | BUTTE | Unsure |  | 5750648 | 41
CHICO | BUTTE | Yes |  | 4446246.22 | 55
OROVILLE | BUTTE | Yes |  | 1265235.84 | 123
PARADISE | BUTTE | Yes |  | 753334.25 | 148
ANGELS CAMP | CALAVERAS | No |  | 871298 | 141
CALAVERAS COUNTY | CALAVERAS | Unsure |  | 1594757.69 | 112
ANTIOCH | CONTRA COSTA | No |  | 6357105.83 | 38
BRENTWOOD | CONTRA COSTA | No |  | 1476839.79 | 114
CLAYTON | CONTRA COSTA | No |  | 275021 | 181
CONCORD | CONTRA COSTA | No |  | 7512103.97 | 30
CONTRA COSTA COUNTY | CONTRA COSTA | Unsure |  | 6404964 | 37
DANVILLE | CONTRA COSTA | No |  | 3023914 | 71
EL CERRITO | CONTRA COSTA | No |  | 2845462 | 78
HERCULES | CONTRA COSTA | No |  | 196762 | 187
LAFAYETTE | CONTRA COSTA | No |  | 4005707 | 59
MARTINEZ | CONTRA COSTA | No |  | 2748725.89 | 79
MORAGA | CONTRA COSTA | No |  | 1632342.76 | 110
ORINDA | CONTRA COSTA | No |  | 1141616 | 128
PINOLE | CONTRA COSTA | No |  | 677613 | 150
PITTSBURG | CONTRA COSTA | No |  | 1819849 | 104
PLEASANT HILL | CONTRA COSTA | No |  | 2133834.64 | 91
RICHMOND | CONTRA COSTA | No |  | 7828433.23 | 28
SAN PABLO | CONTRA COSTA | Yes |  | 2599414.97 | 82
SAN RAMON | CONTRA COSTA | No |  | 2063245.89 | 97
WALNUT CREEK | CONTRA COSTA | No |  | 5154610.78 | 45
EL DORADO COUNTY | EL DORADO | Unsure |  | 1964107 | 100
PLACERVILLE | EL DORADO | Yes |  | 1993373.79 | 99
CLOVIS | FRESNO | No |  | 4805681.1 | 49
FIREBAUGH | FRESNO | Yes |  | 2449964.29 | 84
FOWLER | FRESNO | Yes |  | 1334627.34 | 119
FRESNO | FRESNO | Yes |  | 41379446.46 | 4
FRESNO COUNTY | FRESNO | Unsure |  | 22747286.96 | 5
HURON | FRESNO | Yes |  | 285801 | 180
KERMAN | FRESNO | Yes |  | 489228 | 164
KINGSBURG | FRESNO | No |  | 362184 | 172
PARLIER | FRESNO | Yes |  | 2067838.27 | 96
REEDLEY | FRESNO | Yes |  | 3935390.88 | 61
SANGER | FRESNO | Yes |  | 828981 | 145
SELMA | FRESNO | Yes |  | 527574 | 161
ARCATA | HUMBOLDT | Yes |  | 1109690.86 | 129
EUREKA | HUMBOLDT | Yes |  | 1945931.45 | 101
FORTUNA | HUMBOLDT | Yes |  | -81767 | 219
HUMBOLDT COUNTY | HUMBOLDT | Unsure |  | 6678732.44 | 35
RIO DELL | HUMBOLDT | Yes |  | 392007 | 170
TRINIDAD | HUMBOLDT | Yes |  | 124877 | 193
ARVIN | KERN | Yes |  | 439541 | 168
BAKERSFIELD | KERN | No |  | 18755163.72 | 8
KERN COUNTY | KERN | Unsure |  | 11211868.62 | 19
MCFARLAND | KERN | Yes |  | 160948 | 189
SHAFTER | KERN | Yes |  | 36690 | 206
TAFT | KERN | Yes |  | 10088 | 213
WASCO | KERN | Yes |  | 393 | 217
AVENAL | KINGS | Yes |  | 114293 | 195
CORCORAN | KINGS | Yes |  | 54063 | 204
KINGS COUNTY | KINGS | Unsure |  | 2697526 | 80
LEMOORE | KINGS | Yes |  | 2268786.44 | 87
CLEARLAKE | LAKE | Yes |  | 430576 | 169
LAKE COUNTY | LAKE | Unsure |  | 2967470.53 | 76
MADERA | MADERA | Yes |  | 5447319.38 | 43
MADERA COUNTY | MADERA | Unsure |  | 11482902.13 | 18
BELVEDERE | MARIN | No |  | 670056 | 151
CORTE MADERA | MARIN | No |  | 1231589.52 | 124
FAIRFAX | MARIN | No |  | 854054 | 144
LARKSPUR | MARIN | No |  | 550503 | 159
MARIN COUNTY | MARIN | Unsure |  | 8529332.81 | 25
MILL VALLEY | MARIN | No |  | 3603263.66 | 62
NOVATO | MARIN | No |  | 899569 | 137
ROSS | MARIN | No |  | 290943 | 179
SAN ANSELMO | MARIN | No |  | 2136875 | 90
SAN RAFAEL | MARIN | No |  | 4924605.96 | 47
SAUSALITO | MARIN | No |  | 98446.12 | 196
TIBURON | MARIN | No |  | 453642 | 167
FORT BRAGG | MENDOCINO | Yes |  | 321554 | 175
MENDOCINO COUNTY | MENDOCINO | Unsure |  | 5055413.56 | 46
WILLITS | MENDOCINO | Yes |  | 356489 | 173
ATWATER | MERCED | Yes |  | 3286906.52 | 66
GUSTINE | MERCED | Yes |  | 223875 | 184
LOS BANOS | MERCED | Yes |  | 1586535.32 | 113
MERCED | MERCED | Yes |  | 6991046 | 32
MERCED COUNTY | MERCED | Unsure |  | 8040914.04 | 27
CARMEL | MONTEREY | No |  | 661512 | 152
GONZALES | MONTEREY | No |  | 64418 | 203
KING CITY | MONTEREY | Yes |  | 91148.96 | 198
MARINA | MONTEREY | No |  | 891355 | 139
MONTEREY | MONTEREY | No |  | 1469892.84 | 115
MONTEREY COUNTY | MONTEREY | Unsure |  | 4825792.55 | 48
PACIFIC GROVE | MONTEREY | No |  | 1700452.03 | 109
SALINAS | MONTEREY | No |  | 10991963.15 | 20
SEASIDE | MONTEREY | No |  | 2924871 | 77
NAPA | NAPA | No |  | 515438 | 163
NAPA COUNTY | NAPA | Unsure |  | 19189271.58 | 7
ST HELENA | NAPA | No |  | 1191788 | 126
YOUNTVILLE | NAPA | No |  | 197009 | 186
GRASS VALLEY | NEVADA | Yes |  | 1068911.61 | 130
NEVADA CITY | NEVADA | Yes |  | 94890 | 197
NEVADA COUNTY | NEVADA | Unsure |  | 4703429.11 | 51
AUBURN | PLACER | No |  | 1923383.4 | 103
COLFAX | PLACER | Yes |  | 6534.83 | 216
LINCOLN | PLACER | No |  | 594947 | 157
LOOMIS | PLACER | No |  | 29064 | 208
PLACER COUNTY | PLACER | Unsure |  | 14273476.02 | 14
ROCKLIN | PLACER | No |  | 627793 | 155
PLUMAS COUNTY | PLUMAS | Unsure |  | 3017786.62 | 72
SAN FRANCISCO | SAN FRANCISCO | No |  | 174206172.55 | 1
ESCALON | SAN JOAQUIN | No |  | 11818 | 211
LATHROP | SAN JOAQUIN | No |  | 520569.47 | 162
MANTECA | SAN JOAQUIN | No |  | 386493 | 171
RIPON | SAN JOAQUIN | No |  | 866091.4 | 143
SAN JOAQUIN COUNTY | SAN JOAQUIN | Unsure |  | 12157630.04 | 17
STOCKTON | SAN JOAQUIN | Yes |  | 14672229.16 | 13
TRACY | SAN JOAQUIN | No |  | 1804819.7 | 105
ARROYO GRANDE | SAN LUIS OBISPO | No |  | 3039857.15 | 70
ATASCADERO | SAN LUIS OBISPO | No |  | 1284492 | 122
GROVER BEACH | SAN LUIS OBISPO | No |  | 1612137.93 | 111
MORRO BAY | SAN LUIS OBISPO | No |  | 691007.22 | 149
PASO ROBLES | SAN LUIS OBISPO | No |  | 3236275.18 | 67
PISMO BEACH | SAN LUIS OBISPO | No |  | 9849 | 214
SAN LUIS OBISPO | SAN LUIS OBISPO | Yes |  | 7642995.87 | 29
SAN LUIS OBISPO COUNTY | SAN LUIS OBISPO | Unsure |  | 15801209.29 | 11
BELMONT | SAN MATEO | No |  | 5199360.4777 | 44
BURLINGAME | SAN MATEO | No |  | 184162 | 188
COLMA | SAN MATEO | No |  | 273740 | 182
DALY CITY | SAN MATEO | No |  | 10694991.84 | 21
EAST PALO ALTO | SAN MATEO | No |  | 2106376.41 | 94
HALF MOON BAY | SAN MATEO | No |  | 960003 | 133
HILLSBOROUGH | SAN MATEO | No |  | 2058774.42 | 98
MILLBRAE | SAN MATEO | No |  | 561737 | 158
PACIFICA | SAN MATEO | No |  | 6409331.05 | 36
PORTOLA VALLEY | SAN MATEO | No |  | 156167 | 190
REDWOOD CITY | SAN MATEO | No |  | 2170148 | 88
SAN BRUNO | SAN MATEO | No |  | 866113 | 142
SAN CARLOS | SAN MATEO | No |  | 6687392.03 | 34
SAN MATEO | SAN MATEO | No |  | 8760258.8 | 22
SAN MATEO COUNTY | SAN MATEO | Unsure |  | 6860208.4923 | 33
SOUTH SAN FRANCISCO | SAN MATEO | No |  | 1944396 | 102
WOODSIDE | SAN MATEO | No |  | 91002 | 199
BUELLTON | SANTA BARBARA | No |  | 15917 | 210
GUADALUPE | SANTA BARBARA | Yes |  | 272910 | 183
SANTA BARBARA COUNTY | SANTA BARBARA | Unsure |  | 3210080 | 68
SANTA MARIA | SANTA BARBARA | No |  | 1200264 | 125
SOLVANG | SANTA BARBARA | No |  | 114855 | 194
CAMPBELL | SANTA CLARA | No |  | 8653526.09 | 24
CUPERTINO | SANTA CLARA | No |  | 1295070 | 121
GILROY | SANTA CLARA | No |  | 654171 | 153
LOS ALTOS | SANTA CLARA | No |  | 4711925.37 | 50
LOS ALTOS HILLS | SANTA CLARA | No |  | 815900.21 | 147
LOS GATOS | SANTA CLARA | No |  | 1443826 | 116
MILPITAS | SANTA CLARA | No |  | 1165844 | 127
MORGAN HILL | SANTA CLARA | No |  | 2390707.8 | 85
MOUNTAIN VIEW | SANTA CLARA | No |  | 8440272.5 | 26
SAN JOSE | SANTA CLARA | No |  | 54445341.43 | 3
SANTA CLARA COUNTY | SANTA CLARA | Unsure |  | 893508.17 | 138
SUNNYVALE | SANTA CLARA | No |  | 7104923.26 | 31
CAPITOLA | SANTA CRUZ | No |  | 11817.22 | 212
SANTA CRUZ | SANTA CRUZ | No |  | 8669115.59 | 23
SANTA CRUZ COUNTY | SANTA CRUZ | Unsure |  | 5592559.09 | 42
SCOTTS VALLEY | SANTA CRUZ | No |  | 67755 | 201
WATSONVILLE | SANTA CRUZ | Yes |  | 2460851.78 | 83
ANDERSON | SHASTA | Yes |  | 3982121.38 | 60
SHASTA COUNTY | SHASTA | Unsure |  | 4222876.25 | 56
BENICIA | SOLANO | No |  | 650573 | 154
DIXON | SOLANO | No |  | 900503 | 136
FAIRFIELD | SOLANO | No |  | 2336180.78 | 86
RIO VISTA | SOLANO | No |  | 151604 | 191
SOLANO COUNTY | SOLANO | Unsure |  | 946254 | 134
SUISUN CITY | SOLANO | No |  | 532473 | 160
VACAVILLE | SOLANO | No |  | 2970283.64 | 74
VALLEJO | SOLANO | No |  | 2069269 | 95
COTATI | SONOMA | No |  | 211235 | 185
HEALDSBURG | SONOMA | No |  | 81345.13 | 200
PETALUMA | SONOMA | No |  | 4651307.47 | 52
ROHNERT PARK | SONOMA | No |  | 1383331.18 | 117
SANTA ROSA | SONOMA | No |  | 12451191.65 | 16
SEBASTOPOL | SONOMA | No |  | 308031 | 178
SONOMA | SONOMA | No |  | 1764548.78 | 106
SONOMA COUNTY | SONOMA | Unsure |  | 15489381.46 | 12
WINDSOR | SONOMA | No |  | 150000 | 192
NEWMAN | STANISLAUS | No |  | 312071.45 | 176
OAKDALE | STANISLAUS | No |  | 3336356.41 | 65
PATTERSON | STANISLAUS | No |  | -26832 | 218
RIVERBANK | STANISLAUS | No |  | 2969490.41 | 75
STANISLAUS COUNTY | STANISLAUS | Unsure |  | 1324001 | 120
SUTTER COUNTY | SUTTER | Unsure |  | 998641 | 131
YUBA CITY | SUTTER | Yes |  | 2997261.85 | 73
CORNING | TEHAMA | Yes |  | 888092.11 | 140
RED BLUFF | TEHAMA | Yes |  | 617772 | 156
TEHAMA COUNTY | TEHAMA | Unsure |  | 311842 | 177
DINUBA | TULARE | Yes |  | 910996 | 135
TULARE COUNTY | TULARE | Unsure |  | 961940 | 132
SONORA | TUOLUMNE | Yes |  | 18070 | 209
TUOLUMNE COUNTY | TUOLUMNE | Unsure |  | 3568309 | 63
DAVIS | YOLO | No |  | 2621534.27 | 81
WEST SACRAMENTO | YOLO | No |  | 4204489.68 | 57
WINTERS | YOLO | No |  | 66275 | 202
WOODLAND | YOLO | No |  | 3199802.93 | 69
YOLO COUNTY | YOLO | Unsure |  | 2110980.37 | 93
YUBA COUNTY | YUBA | Unsure |  | 6097853.25 | 40
GLENN COUNTY | GLENN | Unsure |  | 828227 | 146
WILLOWS | GLENN | Yes |  | 338351 | 174
MARIPOSA COUNTY | MARIPOSA | Unsure |  | 1373558 | 118
ISLETON | SACRAMENTO | Yes |  | 9084 | 215
HOLLISTER | SAN BENITO | No |  | 1704048 | 108
TRINITY COUNTY | TRINITY | Unsure |  | 52638 | 205
PG&E Total |  |  |  | 1005569990.25
* Note: a project is in a DAC if it is if it is “in or partially in a Disadvantaged Community”

## Cost to Residential Customers
Pacific Gas and Electric Company data for R.17-05-010 submitted on 4/17/2020
(IX.) Cost of Rule 20 A Program for Residential Customers
Year | Annual cost to average residential customer | Annual gross cost to residential customers
Date | Nominal $ | Nominal $
2017
2016
2015
…
Note: Jonathan Frost's presentation at the OIR Workshop on April 22-23, 2019 included the slide below. PG&E provided the data for that slide.

## SaturationCompletionbyCommunity
Pacific Gas and Electric Company data for R.17-05-010 submitted on 4/17/2020
Rule 20A Saturation/Completion by Community
Remaining Project Proposals
Rule 20A Community | Number of Miles Converted in downtowns and other areas (major roads/arterials/collectors) | Number of Overhead Miles Remaining in downtowns and other areas (major roads/arterials/collectors) | Percentage of Miles Converted in downtown and other areas to Total Miles Converted and Remaining Overhead Miles | Percentage of Overhead Miles Remaining in downtown and other areas to Total Miles Converted and Remaining Overhead Miles | Potential Project Name | Potential Detail Street Location/Project Boundary | Potential Cost | Potential Cost - Low | Potential Cost - High | Potential Miles of Lines to be Converted
| Miles | Miles | % | % | Name | Address | Nominal $ | Nominal $ | Nominal $ | Miles
ALAMEDA COUNTY |  |  |  |  | TESLA RD, ALAMEDA COUNTY | S LIVERMORE AVE & GREENVILLE RD | Unknown | Unknown | Unknown | 2.8
ATASCADERO |  |  |  |  | EL CAMINO REAL, ATASCADERO | SAN ANSELMO ROAD E TO 1000' SOUTH OF DEL RIO RD | 7403562.31 | 3701781.155 | 14807124.62 | 1.2299
BAKERSFIELD |  |  |  |  | COLUMBUS | MT VERNON TO AUBURN | Unknown | Unknown | Unknown | Unknown
BAKERSFIELD |  |  |  |  | STOCKDALE | ALLEN TO CLAUDIA AUTUMN | Unknown | Unknown | Unknown | Unknown
BELMONT |  |  |  |  | OLD COUNTY RD PH2 | OLD COUNTY RD FROM MASONIC WAY TO STERLING VIEW AVE | 11605305 | 5802652.5 | 23210610 | 1.0078
CALAVERAS COUNTY |  |  |  |  | SEQUOIA AVE | UNKNOWN | Unknown | Unknown | Unknown | Unknown
CARMEL |  |  |  |  | OCEAN AVE | SAN ANTONIO AVE TO OCEAN TO SAN ANTONIO AVE | 2039343.74 | 1019671.87 | 4078687.48 | 0.30303
COLMA |  |  |  |  | EL CAMINO REAL | EL CAMINO REAL FROM SERRAMONTE BLVD TO JUST PAST OLIVET PKWY | 682524 | 341262 | 1365048 | 0.11648
CORNING |  |  |  |  | HOUGHTON AVE, CORNING | RICE AVE & SOUTH ST | 1000000 | 500000 | 2000000 | 0.23674
CORNING |  |  |  |  | SOUTH ST, CORNING | HOUGHTON AVE & WEST AVE | 1000000 | 500000 | 2000000 | 0.14678
CUPERTINO |  |  |  |  | STEVENS CREEK BLVD DIST 16 | STEVENS CREEK BLVD FROM JANICE AVE TO PHAR LAPP DR | 2620162 | 1310081 | 5240324 | 0.45189
CUPERTINO/SAN JOSE |  |  |  |  | DE ANZA BLVD | S DE ANZA BLVD FROM PROSPECT RD TO ROUTE 85 | 2317637 | 1158818.5 | 4635274 | 0.39886
DAVIS |  |  |  |  | POWER LINE RD | GREENBELT OFF POWER LINE RD | Unknown | Unknown | Unknown | Unknown
EL DORADO COUNTY |  |  |  |  | CAMINO | UNKNOWN | Unknown | Unknown | Unknown | Unknown
EL DORADO COUNTY |  |  |  |  | DIAMOND SPRINGS TOWNSIGHT | FROM CANYON VALLEY RD TO MISSOURI FLAT RD | 7200000 | 3600000 | 14400000 | 1.1364
EL DORADO COUNTY |  |  |  |  | HISTORIC DIAMOND SPRINGS | EL DORADO RD TO MISSOURI FLAT RD | 13000000 | 6500000 | 26000000 | 2.0833
EL DORADO COUNTY |  |  |  |  | PONDEROSA INTERCHANGE UUD | UNKNOWN | Unknown | Unknown | Unknown | Unknown
FAIRFIELD |  |  |  |  | EMPIRE ST | GREAT JONES TO MADISON ST | 3279600 | 1639800 | 6559200 | 0.51761
FAIRFIELD |  |  |  |  | GREGORY ST | LINCOLN HWY TO PARK LN | 628800 | 314400 | 1257600 | 0.099242
FAIRFIELD |  |  |  |  | TAYLOR ST TO MADISON ST | DELEWARE TO BROADWAY ST | 1574400 | 787200 | 3148800 | 0.24848
FAIRFIELD |  |  |  |  | UNION ST | EMPIRE TO KENTUCKY ST | 648000 | 324000 | 1296000 | 0.10227
FAIRFIELD |  |  |  |  | WEBSTER ST | KENTUCKY TO DELAWARE ST | 3445200 | 1722600 | 6890400 | 0.54375
FAIRFIELD |  |  |  |  | WOOLNER AVE | PENNSYLANIA AVE TO GREGORY LN | 1872000 | 936000 | 3744000 | 0.29545
FAIRFIELD |  |  |  |  | WOOLNER AVE | GREGORY LN TO VINE DR | 2304000 | 1152000 | 4608000 | 0.36364
FIREBAUGH |  |  |  |  | HAZEL M BAILEY SCHOOL | AROUND SCHOOL | Unknown | Unknown | Unknown | Unknown
FREMONT |  |  |  |  | EGGERS DR, FREMONT | FREMONT BLVD & CAMDEN ST | 2110853 | 1055426.5 | 4221706 | 0.37121
FRESNO COUNTY |  |  |  |  | BULLARD AVE | LOCAN TO ENTERPRISE | Unknown | Unknown | Unknown | Unknown
FRESNO COUNTY |  |  |  |  | GOLDEN STATE BLVD | KINGSBURG TO FOWLER | Unknown | Unknown | Unknown | Unknown
FRESNO COUNTY |  |  |  |  | MILLERTON RD | UNKNOWN | Unknown | Unknown | Unknown | Unknown
GILROY |  |  |  |  | MONTEREY RD | MONTEREY RD FROM W 7TH ST TO W 10TH ST | 2085065 | 1042532.5 | 4170130 | 0.32121
GUADALUPE |  |  |  |  | 11th ST | PERALTA TO ESCALANTE | 1183704.32 | 591852.16 | 2367408.64 | Unknown
GUADALUPE |  |  |  |  | HWY 1 GUADALUPE | MAIN TO 6TH | 4091420.42 | 2045710.21 | 8182840.84 | 0.68807
GUSTINE |  |  |  |  | 1ST AVE PROJECT | HWY 33 & 1ST | Unknown | Unknown | Unknown | Unknown
HOLLISTER |  |  |  |  | SAN JUAN RD | UNKNOWN | Unknown | Unknown | Unknown | Unknown
IONE |  |  |  |  | S CHURCH ST | UNKNOWN | Unknown | Unknown | Unknown | Unknown
KERN COUNTY |  |  |  |  | BELLE TERRACE | UNKNOWN | Unknown | Unknown | Unknown | Unknown
KERN COUNTY |  |  |  |  | MADISON RD | UNKNOWN | Unknown | Unknown | Unknown | Unknown
KINGS COUNTY |  |  |  |  | GENERAL PETROLEUM AVE | HWY 41 TO END OF WEST FIRST ST | Unknown | Unknown | Unknown | Unknown
LIVINGSTON |  |  |  |  | WINTON PKWY PH1 | WINTON TO BRIARWOOD | 2040000 | 1020000 | 4080000 | 0.32197
LIVINGSTON |  |  |  |  | WINTON PKWY PH2 | WINTON TO PRUSSO | 3720000 | 1860000 | 7440000 | 0.58712
LIVINGSTON |  |  |  |  | WINTON PKWY PH3 | WINTON TO 2ND ST | 4560000 | 2280000 | 9120000 | 0.7197
LOS BANOS |  |  |  |  | PLACE RD | UNKNOWN | Unknown | Unknown | Unknown | Unknown
MADERA COUNTY |  |  |  |  | AVENUE 14, MADERA COUNTY | ON AVE 14 FROM RD 28 TO THE EAST 1400 FT | 1700000 | 850000 | 3400000 | 0.26515
MADERA COUNTY |  |  |  |  | SUNRISE AVE | LILLY ST | 600000 | 300000 | 1200000 | 0.094697
MANTECA |  |  |  |  | AIRPORT RD | UNKNOWN | Unknown | Unknown | Unknown | Unknown
MARIN COUNTY |  |  |  |  | NICASIO VALLEY RD, MARIN COUNTY | OLD RANCHERIA RD & LUCAS VALLEY RD | 3504469 | 1752234.5 | 7008938 | 0.62216
MARIN COUNTY |  |  |  |  | REDWOOD HWY, MARIN COUNTY | BELVEDERE DR & SEMINARY DR | 1922036 | 961018 | 3844072 | 0.33996
MENDOCINO COUNTY |  |  |  |  | CASPAR RD, MENDOCINO COUNTY | PACIFICA DR & CASPAR FRONTAGE RD | 1139578 | 569789 | 2279156 | 0.18939
MENDOTA |  |  |  |  | CITY HALL | 6TH ST TO 7TH ST | 600000 | 300000 | 1200000 | 0.094697
MENLO PARK |  |  |  |  | DOWNTOWN MENLO PARK | MENLO AVE, OAK GROVE AVE FROM UNIVERSITY DR TO DOYLE ST & MALONEY LANE & ALL STREETS IN BETWEEN | 10892417 | 5446208.5 | 21784834 | 1.7157
MERCED |  |  |  |  | PARSON PH2 | YOSEMITE PKWY TO MERCED AVE | 1680000 | 840000 | 3360000 | 0.26515
MONTEREY |  |  |  |  | FREMONT ST MONTEREY | PALO VERDE AVENUE TO CASANOVA | 5154580.4 | 2577290.2 | 10309160.8 | 0.86364
NEVADA COUNTY |  |  |  |  | LABARR MEADOWS RD | LABARR MEADOWS RD | Unknown | Unknown | Unknown | Unknown
PARADISE |  |  |  |  | SKYWAY, PARADISE | NEAL RD & JEWELL RD | 3395979 | 1697989.5 | 6791958 | 0.56818
PLYMOUTH |  |  |  |  | MAIN ST | UNKNOWN | Unknown | Unknown | Unknown | Unknown
RICHMOND |  |  |  |  | MARINA WAY S, RICHMOND | CUTTING BLVD & MACDONALD AVE | 5613757 | 2806878.5 | 11227514 | 0.90909
RICHMOND |  |  |  |  | PIERCE ST, RICHMOND | PIERCE ST & SAN MATEO ST | 1446229 | 723114.5 | 2892458 | 0.39
ROHNERT PARK |  |  |  |  | SNYDER LN, ROHNERT PARK | SAN FRANCISCO DR TO N OF KEISER AVE | 883072 | 441536 | 1766144 | 0.16
SAN JOAQUIN COUNTY |  |  |  |  | COUNTRY CLUB RD | UNKNOWN | Unknown | Unknown | Unknown | Unknown
SAN JOSE |  |  |  |  | BLOSSOM HILL | BLOSSOM HILL RD FROM SNELL AVE TO JUDITH ST & SNELL AVE FROM GIUFFRIDA AVE TO BLOSSOM HILL RD | 3277835 | 1638917.5 | 6555670 | 0.56818
SAN JOSE |  |  |  |  | CROPLEY/MORILL | UNKNOWN | Unknown | Unknown | Unknown | Unknown
SAN JOSE |  |  |  |  | GROESBECK PARK | KLEIN RD, FROM GROESBECK HILL DR TO NORWOOD AVE | 1874970 | 937485 | 3749940 | 0.33788
SAN JOSE |  |  |  |  | MCABEE RD | MCABEE RD FROM PERALTA CT TO CAMDEN AVE | 1007805 | 503902.5 | 2015610 | 0.17538
SAN JOSE |  |  |  |  | MINNESOTA AVE | UNKNOWN | Unknown | Unknown | Unknown | Unknown
SAN JOSE |  |  |  |  | MUNICIPAL GOLF COURSE | UNKNOWN | Unknown | Unknown | Unknown | Unknown
SAN JOSE |  |  |  |  | N FIRST ST | UNKNOWN | Unknown | Unknown | Unknown | Unknown
SAN JOSE |  |  |  |  | NORTH 4TH ST | UNKNOWN | Unknown | Unknown | Unknown | Unknown
SAN JOSE |  |  |  |  | NORTH 5TH ST | UNKNOWN | Unknown | Unknown | Unknown | Unknown
SAN LUIS OBISPO COUNTY |  |  |  |  | CA STATE HWY #1 | SAN BERNARDO CREEK RD TO CANET | Unknown | Unknown | Unknown | Unknown
SAN LUIS OBISPO COUNTY |  |  |  |  | CIENAGA RD OCEANO | HALCYON RD TO FRONT STREET | Unknown | Unknown | Unknown | Unknown
SAN LUIS OBISPO COUNTY |  |  |  |  | MISSION STREET, SAN MIGUEL | MISSION TO 14TH STREET | Unknown | Unknown | Unknown | Unknown
SAN LUIS OBISPO COUNTY |  |  |  |  | ORCHARD AVE NIPOMO | STORY AVENUE TO TEFFT STREET | Unknown | Unknown | Unknown | Unknown
SAN LUIS OBISPO COUNTY |  |  |  |  | QUINTANA ROAD | SOUTH BAY BLVD TO SAN BERNARDO CREEK | Unknown | Unknown | Unknown | Unknown
SAN LUIS OBISPO COUNTY |  |  |  |  | SANTA YSABEL AVE, BAYWOOD PARK | 3RD STREET TO SOUTH BAY BLVD | Unknown | Unknown | Unknown | Unknown
SAN LUIS OBISPO COUNTY |  |  |  |  | SOUTH BAY BOULEVARD SAN LUIS OBISPO | SOUTH SIDE OF CHORRO CREEK BRIDGE TO CITY LIMITS | 9124163.61 | 4562081.805 | 18248327.22 | 1.35
SAN MATEO |  |  |  |  | THIRD AVE | 3RD AVE & E 4TH AVE FROM S RAILROAD AVE TO LAST POLE PAST S CLAREMONT ST | 2385499 | 1192749.5 | 4770998 | 0.34451
SAN RAMON |  |  |  |  | BROADMOOR DR, SAN RAMON | ALCOSTA BLVD & HILLSBORO AVE | 5199231 | 2599615.5 | 10398462 | 0.89962
SAN RAMON |  |  |  |  | DAVONA DR, SAN RAMON | ALCOSTA BLVD & WINTHROP AVE | 5764159 | 2882079.5 | 11528318 | 0.99621
SAND CITY |  |  |  |  | CATALINA STREET | UNKNOWN | Unknown | Unknown | Unknown | Unknown
SAND CITY |  |  |  |  | CONTRA COSTA STREET | UNKNOWN | Unknown | Unknown | Unknown | Unknown
SANTA BARBARA COUNTY |  |  |  |  | CLARK AVE | UNKNOWN | Unknown | Unknown | Unknown | Unknown
SANTA BARBARA COUNTY |  |  |  |  | MISSION HILLS | UNKNOWN | Unknown | Unknown | Unknown | Unknown
SANTA CRUZ COUNTY |  |  |  |  | E CLIFF DR SANTA CRUZ COUNTY | 5TH AVE TO 18TH AVE | 4361057.77 | 2180528.885 | 8722115.54 | 0.54072
SHAFTER |  |  |  |  | SHAFTER AVE SHAFTER | LERDO TO LOS ANGELES | 3884883.15 | 1942441.575 | 7769766.3 | 0.67992
SHASTA COUNTY |  |  |  |  | HWY 299, SHASTA COUNTY | SECOND ST & MIDDLE CREEK RD | 1845059 | 922529.5 | 3690118 | 0.32765
SOLANO COUNTY |  |  |  |  | SUISUN VALLEY RD | COMMUNITY COLLEGE & THE CEMETERY | Unknown | Unknown | Unknown | Unknown
SONORA |  |  |  |  | S WASHINGTON ST | UNKNOWN | Unknown | Unknown | Unknown | Unknown
SOUTH SAN FRANCISCO |  |  |  |  | MISSION RD | MISSION RD FROM 1265 MISSION RD TO GRAND AVE | 6415204 | 3207602 | 12830408 | 0.81648
SUNNYVALE/CUPERTINO |  |  |  |  | E HOMESTEAD RD | E HOMESTEAD RD FROM BLUE JAY DR TO 1174 E HOMESTEAD RD | 10600326 | 5300163 | 21200652 | 1.722
SUNNYVALE/CUPERTINO |  |  |  |  | W HOMESTEAD RD | W HOMESTEAD RD FROM BELLEVILLE WAY TO FORGE WAY | 7751962 | 3875981 | 15503924 | 1.292
TAFT |  |  |  |  | SUPPLY ROW TAFT | 2ND TO 10TH | 2700784.52 | 1350392.26 | 5401569.04 | 0.48466
TRACY |  |  |  |  | CORRAL HOLLOW RD | W LINNE RD TO I-5 | 6480000 | 3240000 | 12960000 | 1.0227
TRACY |  |  |  |  | CORRAL HOLLOW RD | PEONY TO SCHULTE RD | 8520000 | 4260000 | 17040000 | 1.3447
TRACY |  |  |  |  | MT OSO AVE | S CENTRAL AVE TO TRACY BLVD | 1440000 | 720000 | 2880000 | 0.22727
TRACY |  |  |  |  | VALPICO RD | S MACARTHUR DR TO TRACY BLVD | 3600000 | 1800000 | 7200000 | 0.56818
TULARE COUNTY |  |  |  |  | MERRITT AVE TULARE | 6TH TO CANAL | 3257876.08 | 1628938.04 | 6515752.16 | 0.56818
TULARE COUNTY |  |  |  |  | SR 63 OROSI | UNKNOWN | Unknown | Unknown | Unknown | Unknown
TUOLUMNE COUNTY |  |  |  |  | JAMESTOWN | AREA AROUND RAILROAD PARK | Unknown | Unknown | Unknown | Unknown
VACAVILLE |  |  |  |  | JEPSON PKWY | UNKNOWN | Unknown | Unknown | Unknown | Unknown
VACAVILLE |  |  |  |  | PEABODY RD | UNKNOWN | Unknown | Unknown | Unknown | Unknown
WEST SACRAMENTO |  |  |  |  | 5TH ST | 15 ST TO MILL ST | 1860000 | 930000 | 3720000 | 0.29356
WINDSOR |  |  |  |  | WINDSOR RD, WINDSOR | REIMAN LN & PLANT RD | 1000000 | 500000 | 2000000 | 0.20833
WINDSOR |  |  |  |  | WINDSOR RD, WINDSOR | JONES & SHILOH | 2500000 | 1250000 | 5000000 | 0.50189
YUBA CITY |  |  |  |  | BRIDGE ST PH1 | GRAY AVE TO COOPER AVE | 2400000 | 1200000 | 4800000 | 0.37879
YUBA CITY |  |  |  |  | BRIDGE ST PH2 | SHASTA ST TO SECOND ST | 2280000 | 1140000 | 4560000 | 0.35985
YUBA CITY |  |  |  |  | BRIDGE ST PH3 | COOPER AVE TO PLUMAS ST | 3000000 | 1500000 | 6000000 | 0.47348
YUBA CITY |  |  |  |  | BRIDGE ST PH4 | STATE ROUTE 99 TO GRAY AVE | 1440000 | 720000 | 2880000 | 0.22727
PG&E Total
Note on I5: Note: Based on updated planning calculator, if available. If not, based on Google Earth measurement.
Note on J5: Note: Per AACE Class 5, +100% to -50% of Potential Cost
Note on K5: Note: Per AACE Class 5, +100% to -50% of Potential Cost
Note on L5: Note: Based on updated planning calculator, if available. If not, based on Google Earth measurement.