## Instructions
PROJECT VIABILITY CALCULATOR | Version 2.0
updated May 2011
purpose and use
The project viability calculator (PVC) is a tool for the utilities to evaluate the viability of a renewable energy project, relative to all other projects that bid into the California investor-owned utilities' Renewables Portfolio Standard (RPS) solicitations. The Commission requires the utilities to use the PVC to evaluate all bids received in response to their RPS solicitations. (See Decision (D.) 09-06-018.)
The objective of the PVC is to serve as a renewable project evaluation tool which increases transparency of the RPS procurement process, employs standardized evaluation criteria and produces meaningful results. RPS stakeholders made significant contributions in developing the PVC in 2009. In preparation for the 2011 RPS solicitation, Energy Division staff sought input from stakeholders to refine the PVC to ensure that the criteria by which projects are assessed is consistent with current renewable project development processes and market conditions, and to better differentiate projects in various stages of development. Staff considered all comments and recommendations it received.
The PVC uses standardized categories and criteria to quantify a project's strengths and weaknesses in key areas of renewable project development. A project's score is only indicative of a project's likelihood to achieve commercial development. Specifically, the PVC is used as a screening tool, not to determine the exact merit of a particular project or contract. Utilities ultimately remain responsible for the recommendations they make regarding projects to meet their RPS Program targets.
Each project viability criteria is defined to guide scoring between zero and ten (0 - 10). Refer to the Criteria_Scoring Guidelines tab.
Utilities may modify the PVC, with conditions, if necessary. For example, the utilities may adjust the priority ranking of criteria and may add criteria. Pursuant to D.09-06-018, the utilities may not add new categories, may not change or delete criteria, and cannot modify the criteria scoring guidelines. Any addition or change must be documented.
Yellow highlighted cells identify areas where the user will input criteria scores, and may adjust weighting percentages and criteria priority ranking. Refer to the Calculator tab.

## Calculator
Project Summary | [14 empty] | <bid number>
<project name>
Bidder Information
| Project Name |  |  |  |  | <project name>
| Solicitation Bid Number (1,2,3…) |  |  |  |  | <bid number>
| Company Name |  |  |  |  | <company>
| New or Existing Facility? |  |  |  |  | <select one>
Project Information
| Technology |  |  |  |  | <select one>
Nameplate Capacity (MW)
Annual Generation (GWh)
Annual Capacity Factor (%)
| Type of cooling |  |  |  |  | <select one>
Contract Length (years)
| Commercial Operation Date |  |  |  |  | <01/15/10>
Project Detail
Interconnection Status
Interconnection Point / Substation
Levelized Price ($/MWh)
TOD-adjusted Levelized Price ($/MWh)
Project Viability Calculator
Version 2.0
Category and Criteria Weighting
Criteria Ranking
[10 empty] | Priority | VH | H | M | L
| Category |  |  | Criteria |  |  |  | Priority | Weight | Weight | 4 | 3 | 2 | 1
| Company / Development Team |  |  | Project Development Experience |  |  |  | VH | 4
|  |  |  | Ownership / O&M Experience |  |  |  | L | 1
| Category Weight |  | 25%
| Technology |  |  | Technical Feasibility |  |  |  | VH | 4
|  |  |  | Resource Quality |  |  |  | M | 2
|  |  |  | Manufacturing Supply Chain |  |  |  | H | 3
| Category Weight |  | 25%
| Development Milestones |  |  | Site Control |  |  |  | VH | 4
|  |  |  | Permitting Status |  |  |  | VH | 4
|  |  |  | Project Financing Status |  |  |  | VH | 4
|  |  |  | Interconnection Progress |  |  |  | VH | 4
|  |  |  | Transmission Requirements |  |  |  | H | 3
|  |  |  | Reasonableness of COD |  |  |  | H | 3
| Category Weight |  | 50%
|  | must equal 100% --> | 100%
- score card -
| Project Scoring |  | range 0 - | 10 | Utility | IE | Comments
weight
25% | Company / Development Team
4 | Project Development Experience
1 | Ownership / O&M Experience
|  |  |  | Total Category | 0 | 0
|  |  |  | Weighted Criteria | 0 | 0
|  |  |  | Normalized Category | 0 | 0
|  |  |  | Weighted Category | 0 | 0
25% | Technology
4 | Technical Feasibility
2 | Resource Quality
3 | Manufacturing Supply Chain
|  |  |  | Total Category | 0 | 0
|  |  |  | Weighted Criteria | 0 | 0
|  |  |  | Normalized Category | 0 | 0
|  |  |  | Weighted Category | 0 | 0
50% | Development Milestones
4 | Site Control
4 | Permitting Status
4 | Project Financing Status
4 | Interconnection Progress
3 | Transmission Requirements
3 | Reasonableness of COD
|  |  |  | Total Category | 0 | 0
|  |  |  | Weighted Criteria | 0 | 0
|  |  |  | Normalized Category | 0 | 0
|  |  |  | Weighted Category | 0 | 0
|  |  |  | Total Weighted Score | 0 | 0
| Project Strengths |  |  |  |  | Project Weaknesses
<select one>
| 1 | Biomass
| 2 | Digester Gas
| 3 | Biodiesel
| 4 | Landfill Gas
| 5 | Muni Solid Waste
| 6 | Geothermal
| 7 | Small Hydro
| 8 | Conduit Hydro
| 9 | Solar PV
| 10 | Solar Thermal
| 11 | Wind
| 12 | Ocean/Tidal
| 13 | Fuel Cells
Note on G53: Independent Evaluator
Note on M32: Very High
Note on E47: COD: Commercial Online Date
Note on P32: Low
"Normalized Category" makes each category the same range of values while incorporating the weighting within each category. Therefore, a normalized category score should be "100" if the project receives the maximum score (10) for each criteria, regardless of the criteria weighting (1 - 4).

## Criteria_Scoring Guidelines
Criteria: Scoring Guidelines |  |  |  |  | - Scale -
Version 2.0
Score Card
|  |  | Utility | IE
Company / Development Team
| Project Development Experience |  | 0 | 0 | 10 | The company and/or the development team has completed 2 or more projects of similar technology and similar or larger capacity.
[5 empty] | 7 | The company and/or the development team has either (i) completed one project of similar technology and similar or larger capacity; (ii) begun construction of and completed financing for at least one project of similar technology and similar or larger capacity; or (iii) completed 2 or more projects of any technology and of similar capacity.
[5 empty] | 4 | The company and/or the development team has completed 2 or more projects of any technology but less capacity per project (wholesale generation).
[5 empty] | 2 | The company and/or the development team has either (i) completed at least one project of any technology and capacity (wholesale generation); or (ii) begun construction of and completed financing for at least one other similar project.
[5 empty] | 0 | None of the above.
| Ownership / O&M Experience |  | 0 | 0 | 10 | The company, development team or subcontractor has experience with 2 or more projects of similar technology and capacity. (e.g., 20 MW photovoltaic facility (thin-film))
[5 empty] | 7 | The company, development team or subcontractor has experience with at least 1 project with similar technology.
[5 empty] | 4 | The company, development team or subcontractor has experience with 2 or more projects of any technology (wholesale generation).
[5 empty] | 2 | The company, development team or subcontractor has experience with at least 1 project of any technology and capacity (wholesale generation).
[5 empty] | 0 | None of the above.
Technology
| Technical Feasibility |  | 0 | 0 | 10 | Project will use commercialized technology or commercialized technology that is nearly identical (e.g., a wind turbine with modest upgrades from the last model) to technology that is currently in use at a minimum of 2 operating facilities of similar or larger capacity (worldwide).
[5 empty] | 5 | Project will use commercialized technology that is currently in use at a minimum of 2 operating facilities, but at first-of-its-kind scale. For example, existing projects do not exceed 20 MW and the proposed project is for greater than 100 MW.
[5 empty] | 2 | Either (i) the project will use key components of commercialized technology, but in an application that has not yet been commercially proven; or (ii) project feasibility is supported by third party, independent engineer's report that verifies the cost and performance. (Technology is not commercially proven)
[5 empty] | 0 | None of the above.
| Resource Quality |  | 0 | 0 | 10 | Bidder demonstrated that the resource can support the production profile. For example:
- Geothermal: Based on results of test wells or verified third party resource assessment.
- Wind: Based on credible meteorological data or verified third party resource assessment.
- Biomass: Sufficient quantities of fuel stock under control or contract for a minimum of five years.
- Solar: Based on credible solar radiation meteorological data or verified third party solar radiation resource assessment.
[5 empty] | 7 | Biomass project demonstrated sufficient quantities of fuel stock under control or contract for a minimum of two years.
[5 empty] | 5 | The resource appears sufficient to support the project's production profile. Assumptions are reasonable, for example, based on comparable facilities in the same resource area, but not demonstrated by bidder, data, and/or resource assessment as described above.
[5 empty] | 0 | None of the above.
| Manufacturing Supply Chain |  | 0 | 0 | 10 | There are no known or anticipated supply chain constraints.
[5 empty] | 5 | Project scored within the top two tiers in the Technical Feasibility category, but project development is dependent on new manufacturing capacity.
[5 empty] | 0 | Project will rely on proprietary technical design for its key component(s), not currently in use commercially, and project development is dependent on new manufacturing capacity.
Development Milestones
| Site Control |  | 0 | 0 | 10 | Project has 100% site control for the project site and gen-tie line corridor connecting the facility to the grid. Site control is achieved through either (i) direct ownership, (ii) a lease, or (iii) an option to lease or purchase; including the equivalent process for securing site control on public lands, as applicable.
[5 empty] | 6 | Project has a majority control (≥ 50% and <100%) over the project site and gen-tie line corridor connecting the facility to the grid.
[5 empty] | 2 | Project has a minority control (< 50%) over the project site and gen-tie line corridor connecting the facility to the grid.
[5 empty] | 0 | None of the above.
| Permitting Status |  | 0 | 0 | 10 | Project has received its Conditional Use Permit (CUP), Application for Certification (AFC), Record of Decision from the BLM or equivalent federal agency, or other definitive permit based on the project's jurisdiction, as applicable.
[5 empty] | 5 | Project has applied for its CUP or AFC, or other definitive permit based on the project's jurisdiction, as applicable. The applicable permit or application has been deemed data adequate and/or the designated agency has initiated its review. No fatal flaws have been identified (e.g., protected species and/or land, high land mitigation requirement) that will prevent project development.
[5 empty] | 2 | Bidder has not initiated permitting. No fatal flaws have been identified (e.g., protected species and/or land, high land mitigation requirement) that will prevent project development.
[5 empty] | 0 | None of the above.
| Project Financing Status |  | 0 | 0 | 10 | The bidder demonstrated that project financing has been secured either through "balance sheet" financing or power purchase agreement (PPA) financing.
[5 empty] | 5 | The bidder has obtained financing for at least 1 project of similar technology and similar or larger capacity.
[5 empty] | 2 | The bidder has obtained financing for at least 1 project of any technology and capacity (wholesale generation).
[5 empty] | 0 | None of the above.
| Interconnection Progress |  | 0 | 0 | 10 | The project has executed its Interconnection Agreement.
[5 empty] | 9 | The project has completed its Phase II studies of the Generator Interconnection Process (GIP), or has completed its Facilities Study, or has passed the Fast Track screens. If the project will interconnect outside the CAISO's or the investor-owned utility's jurisdiction, it has achieved the equivalent interconnection progress.
[5 empty] | 6 | The project is in Phase II of the GIP, has posted necessary deposits, and is in compliance with all CAISO or utility requirements for maintaining queue position, or the project has initiated its Facilities Study. If the project will interconnect outside the CAISO's or the investor-owned utility's jurisdiction, it has achieved the equivalent interconnection progress.
[5 empty] | 3 | The project is in Phase I of the GIP, or has initiated the System Impact Study, or has submitted its Interconnection Request to the CAISO or utility, and has posted necessary deposits and is in compliance with all CAISO or utility requirements for maintaining queue position. If the project will interconnect outside the CAISO's or the investor-owned utility's jurisdiction, it has achieved the equivalent interconnection progress.
[5 empty] | 0 | None of the above.
| Transmission System Upgrade Requirements |  | 0 | 0 | 10 | No transmission system upgrades are required for the project pursuant to the most recent interconnection study, or the project has passed the Fast Track screens.
[5 empty] | 9 | Transmission system upgrades required for the project pursuant to the most recent interconnection study have received any and all required CAISO and CPUC approvals.
[5 empty] | 8 | Transmission system upgrades required for the project pursuant to the most recent interconnection study require a Permit to Construct or an approved Notice of Construction from the CPUC, for which an application or advice letter, as applicable, has been filed.
[5 empty] | 5 | Transmission system upgrades required for the project pursuant to the most recent interconnection study require a Permit to Construct or an approved Notice of Construction from the CPUC, for which an application or advice letter, as applicable, has not been filed.
[5 empty] | 4 | Transmission system upgrades required for the project pursuant to the most recent interconnection study require a Certificate of Public Convenience and Necessity from the CPUC, for which an application has been filed.
[5 empty] | 1 | Transmission system upgrades required for the project pursuant to the most recent interconnection study require a Certificate of Public Convenience and Necessity from the CPUC, for which an application has not been filed.
[5 empty] | 0 | None of the above.
| Reasonableness of COD |  | 0 | 0 | 10 | Utility reasonably expects the project will achieve its COD.
| Utility should validate the reasonableness of project's commercial online date (COD) based on the scores given for criteria above. |  |  |  | 5 | Utility reasonably expects project's COD to occur within 12 months of the proposed COD.
[5 empty] | 3 | Utility reasonably expects project's COD to occur within 12 - 24 months of the proposed COD.
[5 empty] | 0 | Utility reasonably expects project's COD to occur more than 24 months after the proposed online date.
- end -
Note on G4: Independent Evaluator
Administrative requirements for transmission system upgrades (See General Order 131-D for complete legal requirements) A Certificate of Public Convenience and Necessity (CPCN) is required for a new transmission line or upgrade – greater than 200 kV. A CPCN requires CEQA review and a determination of need. A Permit to Construct (PTC) is required for a new transmission line or upgrade – 50 kV to 200 kV, or a substation upgrade only. A PTC requires CEQA review. Some exemptions to the above that would allow only a Notice of Construction to be sufficient: - The replacement of existing power line facilities or supporting structures with equivalent facilities or structures. - The placing of new or additional conductors, insulators, or their accessories on supporting structures already built. - Power lines or substations to be relocated or constructed which have undergone environmental review pursuant to CEQA as part of a larger project, and for which the final CEQA document finds no significant unavoidable environmental impacts caused by the proposed line or substation.